## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer/Manager | PCH | Regional Manager | Project Manager | Section Incharge | Supervisor
TA 413 | 765 KV D/C Bikaner III - Neemrana II TL02 | PGCIL | 2024-03-12 | 2025-12-11 | Mr. Santosh Mishra | Mr. N.K Gupta | Mr. Rajnish Pandey | Mr. Md. Aftab Ahmad | Surendra Kumar Patel | Raju Mahto
[9 empty] | Kartik Jhorar | Sushil Kumar
[9 empty] | Govind Bhardwaj | Haridashn
Sanjay Kumar
Akil hussain
Niwash Kumar
Kamal Ravidas
Manirul Islam
Tarique Anwar
Raju Prasad
Abhay Ojha

## Erection Compiled
SL No. | Location No. | Tower Type | Classification | Starting Date | Tower Weight | Status | Completion Date | Gang Name | Gang Strength | Number of Fitters | Tower Tightening | Remark
1 | 29A/2 | DA+6 |  | 2024-09-12 | 43.8044 | COMPLETED | 2024-09-21 | Bhagwan construction
2 | 29/5 | DA+0 |  | 2024-09-21 | 36.1598 | COMPLETED | 2024-09-27 | Bhagwan construction
3 | 29/3 | DA+0 |  | 2024-09-28 | 36.1598 | COMPLETED | 2024-10-03 | Bhagwan construction
4 | 29/4 | DA+3 |  | 2024-10-03 | 37.9311 | COMPLETED | 2024-10-08 | Bhagwan construction
5 | 29A/6 | DA+9 |  | 2024-10-03 | 45.697 | COMPLETED | 2024-10-14 | Bhagwan construction
6 | 30/1 | DA+0 |  | 2024-10-09 | 36.1598 | COMPLETED | 2024-10-17 | Bhagwan construction
7 | 29A/1 | DA+6 |  | 2024-10-14 | 43.8044 | COMPLETED | 2024-10-25 | Bhagwan construction
8 | 34/8 | DA+0 |  | 2024-11-12 | 36.1598 | COMPLETED | 2024-11-24 | Vasu dev singh-1
9 | 34/12 | DA+3 |  | 2024-11-14 | 37.9311 | COMPLETED | 2024-11-25 | Vasu dev singh-2
10 | 34/4 | DA+6 |  | 2024-11-25 | 43.8044 | COMPLETED | 2024-12-04 | Vasu dev singh-1
11 | 34/7 | DA+0 |  | 2024-11-26 | 36.1598 | COMPLETED | 2024-12-12 | Vasu dev singh-2
12 | 34/3 | DA+1.5 |  | 2024-12-05 | 37.1383 | COMPLETED | 2024-12-16 | Vasu dev singh-1
13 | 8/1 | DA-3 |  | 2024-12-07 | 34.7898 | COMPLETED | 2024-12-16 | Punam Devi-2
14 | 34/9 | DA+1.5 |  | 2024-12-13 | 37.1383 | COMPLETED | 2024-12-21 | Vasu dev singh-2
15 | 35/7 | DA+3 |  | 2024-12-13 | 37.9311 | COMPLETED | 2024-12-22 | Punam Devi-2
16 | 7A/5 | DA+3 |  | 2024-12-17 | 37.9311 | COMPLETED | 2024-12-24 | Punam Devi-2
17 | 36A/1 | DA+3 |  | 2024-12-13 | 37.9311 | COMPLETED | 2024-12-25 | Punam Devi-3
18 | 7/1 | DA-3 |  | 2024-12-15 | 34.7898 | COMPLETED | 2024-12-26 | Punam Devi-1
19 | 35/8 | DA+6 |  | 2024-12-23 | 43.8044 | COMPLETED | 2024-12-28 | Punam Devi-2
20 | 34/5 | DA+9 |  | 2024-12-17 | 45.697 | COMPLETED | 2024-12-29 | Vasu dev singh-1
21 | 34/10 | DA-3 |  | 2024-12-22 | 34.7898 | COMPLETED | 2024-12-29 | Vasu dev singh-2
22 | 7A/4 | DA+3 |  | 2024-12-24 | 37.9311 | COMPLETED | 2024-12-31 | Punam Devi-2
23 | 7/2 | DA+6 |  | 2024-12-27 | 43.8044 | COMPLETED | 2025-01-03 | Punam Devi-1
24 | 35/11 | DA+3 |  | 2024-12-24 | 37.9311 | COMPLETED | 2025-01-03 | Punam Devi-3
25 | 35/6 | DA+6 |  | 2024-12-29 | 43.8044 | COMPLETED | 2025-01-05 | Punam Devi-2
26 | 34/11 | DA+1.5 |  | 2024-12-30 | 37.1383 | COMPLETED | 2025-01-07 | Vasu dev singh-2
27 | 7A/3 | DA+3 |  | 2025-01-01 | 37.9311 | COMPLETED | 2025-01-08 | Punam Devi-2
28 | 34/6 | DA+3 |  | 2024-12-30 | 37.9311 | COMPLETED | 2025-01-09 | Vasu dev singh-1
29 | 8/5 | DA+9 |  | 2025-01-04 | 45.697 | COMPLETED | 2025-01-09 | Punam Devi-1
30 | 36A/2 | DA+9 |  | 2025-01-04 | 45.697 | COMPLETED | 2025-01-11 | Punam Devi-3
31 | 35/5 | DA+9 |  | 2025-01-06 | 45.697 | COMPLETED | 2025-01-13 | Punam Devi-2
32 | 8/6 | DA+3 |  | 2025-01-10 | 37.9311 | COMPLETED | 2025-01-15 | Punam Devi-1
33 | 7A/2 | DA+3 |  | 2025-01-08 | 37.9311 | COMPLETED | 2025-01-16 | Punam Devi-2
34 | 35/1 | DA+6 |  | 2025-01-07 | 43.8044 | COMPLETED | 2025-01-19 | Vasu dev singh-2
35 | 35/4 | DA+9 |  | 2025-01-14 | 45.697 | COMPLETED | 2025-01-19 | Punam Devi-2
36 | 8/7 | DA+3 |  | 2025-01-16 | 37.9311 | COMPLETED | 2025-01-20 | Punam Devi-1
37 | 34/2 | DA+9 |  | 2025-01-10 | 45.697 | COMPLETED | 2025-01-21 | Vasu dev singh-1
38 | 37/4 | DA+9 |  | 2025-01-11 | 45.697 | COMPLETED | 2025-01-22 | Punam Devi-3
39 | 7A/1 | DA+1.5 |  | 2025-01-17 | 37.1383 | COMPLETED | 2025-01-22 | Punam Devi-2
40 | 35/9 | DA+1.5 |  | 2025-01-17 | 37.1383 | COMPLETED | 2025-01-24 | Punam Devi-2
41 | 8/8 | DA+9 |  | 2025-01-20 | 45.697 | COMPLETED | 2025-01-25 | Punam Devi-1
42 | 34/1 | DA+9 |  | 2025-01-21 | 45.697 | COMPLETED | 2025-01-29 | Vasu dev singh-1
43 | 38/3 | DA+3 |  | 2025-01-24 | 37.9311 | COMPLETED | 2025-01-29 | Punam Devi-2
44 | 8/9 | DA+3 |  | 2025-01-25 | 37.9311 | COMPLETED | 2025-01-30 | Punam Devi-4
45 | 37/5 | DA+3 |  | 2025-01-22 | 37.9311 | COMPLETED | 2025-01-30 | Punam Devi-3
46 | 7A/0 | DB1+6 |  | 2025-01-22 | 65.0278 | COMPLETED | 2025-01-31 | Punam Devi-2
47 | 34/0 | DB1+6 |  | 2025-01-17 | 65.0278 | COMPLETED | 2025-01-31 | Vasu dev singh-1
48 | 8/10 | DA+0 |  | 2025-01-30 | 36.1598 | COMPLETED | 2025-02-03 | Punam Devi-4
49 | 38/6 | DA+6 |  | 2025-01-29 | 43.8044 | COMPLETED | 2025-02-04 | Punam Devi-1
50 | 37A/2 | DA+1.5 |  | 2025-01-29 | 37.1383 | COMPLETED | 2025-02-07 | Punam Devi-3
51 | 33/6 | DA+6 |  | 2025-01-29 | 43.8044 | COMPLETED | 2025-02-08 | Vasu dev singh-2
52 | 8/2 | DA+6 |  | 2025-02-03 | 43.8044 | COMPLETED | 2025-02-08 | Punam Devi-4
53 | 7/6 | DA-1.5 |  | 2025-01-31 | 35.6018 | COMPLETED | 2025-02-10 | Punam Devi-2
54 | 38/4 | DA+1.5 |  | 2025-02-05 | 37.1383 | COMPLETED | 2025-02-10 | Punam Devi-1
55 | 8/0 | DB1+0 |  | 2025-02-09 | 55.4509 | COMPLETED | 2025-02-14 | Punam Devi-4
56 | 38/5 | DA+3 |  | 2025-02-11 | 37.9311 | COMPLETED | 2025-02-15 | Punam Devi-1
57 | 37A/1 | DA+3 |  | 2025-02-08 | 37.9311 | COMPLETED | 2025-02-16 | Punam Devi-3
58 | 33/5 | DA+0 |  | 2025-01-31 | 36.1598 | COMPLETED | 2025-02-18 | Vasu dev singh-1
59 | 38/9 | DA+0 |  | 2025-02-15 | 36.1598 | COMPLETED | 2025-02-18 | Punam Devi-1
60 | 7/5 | DA+6 |  | 2025-02-11 | 43.8044 | COMPLETED | 2025-02-19 | Punam Devi-2
61 | 8/3 | DA+9 |  | 2025-02-14 | 45.697 | COMPLETED | 2025-02-19 | Punam Devi-4
62 | 35/0 | DB2+0 |  | 2025-02-09 | 59.5006 | COMPLETED | 2025-02-23 | Vasu dev singh-2
63 | 38/10 | DA+3 |  | 2025-02-18 | 37.9311 | COMPLETED | 2025-02-24 | Punam Devi-1
64 | 8/4 | DA+6 |  | 2025-02-20 | 43.8044 | COMPLETED | 2025-02-24 | Punam Devi-4
65 | 37A/3 | DA+3 |  | 2025-02-16 | 37.9311 | COMPLETED | 2025-02-25 | Punam Devi-3
66 | 7/4 | DA+6 |  | 2025-02-20 | 43.8044 | COMPLETED | 2025-02-27 | Punam Devi-2
67 | 9/1 | DA+3 |  | 2025-02-24 | 37.9311 | COMPLETED | 2025-02-28 | Punam Devi-4
68 | 37A/5 | DA+3 |  | 2025-02-24 | 37.9311 | COMPLETED | 2025-02-28 | Punam Devi-1
69 | 33/8 | DA+3 |  | 2025-02-18 | 37.9311 | COMPLETED | 2025-03-04 | Vasu dev singh-1
70 | 9/3 | DA+0 |  | 2025-03-01 | 36.1598 | COMPLETED | 2025-03-04 | Punam Devi-4 |  |  |  |  | 3 | [14 empty] | 3 | 2 | 2 | 1 | 1 | 4 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 2 | 1 | 3
71 | 38/1 | DA+0 |  | 2025-03-01 | 36.1598 | COMPLETED | 2025-03-06 | Punam Devi-1
72 | 37A/4 | DA+9 |  | 2025-02-25 | 45.697 | COMPLETED | 2025-03-06 | Punam Devi-3
73 | 37A/6 | DA+3 |  | 2025-02-24 | 37.9311 | COMPLETED | 2025-03-08 | Vasu dev singh-2
74 | 9/4 | DA+6 |  | 2025-03-05 | 43.8044 | COMPLETED | 2025-03-09 | Punam Devi-4
75 | 37A/0 | DB1+0 |  | 2025-02-28 | 55.4509 | COMPLETED | 2025-03-11 | Punam Devi-2 |  |  |  |  | 3 | 1 | 7 | 2 | 6 | 1 | 6 | 5 | 2 | 1 | [20 empty] | 1
76 | 38/2 | DA+0 |  | 2025-03-07 | 36.1598 | COMPLETED | 2025-03-11 | Punam Devi-1 |  |  |  |  | 1 | 2 | 2 | 3 | 17 | 6 | 3 | 15 | 2 | 1 | 9 | 2
77 | 39/7 | DA+3 |  | 2025-03-07 | 37.9311 | COMPLETED | 2025-03-13 | Punam Devi-3 | [6 empty] | 5.91 | 8.93 | 9.52 | 1.67 | 1.87
78 | 9/2 | DA+3 |  | 2025-03-10 | 37.9311 | COMPLETED | 2025-03-13 | Punam Devi-4
79 | 15/2 | DA+3 |  | 2025-03-14 | 37.9311 | COMPLETED | 2025-03-18 | Punam Devi-4
80 | 38/7 | DA+9 |  | 2025-03-12 | 45.697 | COMPLETED | 2025-03-18 | Punam Devi-1 | [12 empty] | 1 | 2 | 10 | 13 | 3
81 | 39/2 | DA+3 |  | 2025-03-12 | 37.9311 | COMPLETED | 2025-03-19 | Punam Devi-2
82 | 39/5 | DA+1.5 |  | 2025-03-14 | 37.1383 | COMPLETED | 2025-03-20 | Punam Devi-3 | [15 empty] | 3.88 | 3.74 | 2.37 | 2.87 | 4.33 | 1.63 | 3.32 | 4.2 | 1.91 | 0.98 | 4.07
83 | 39/0 | DB2+0 |  | 2025-03-09 | 59.5006 | COMPLETED | 2025-03-21 | Vasu dev singh-2 | [17 empty] | 5.56 | 6.8 | 8.93 | 2.19 | 2.48 | 2.29 | 5.28 | 6.24 | 3.45 | 3.31 | 3.19 | 1.98
84 | 15/3 | DA+3 |  | 2025-03-19 | 37.9311 | COMPLETED | 2025-03-22 | Punam Devi-4 | [19 empty] | 17 | 15 | 4 | 3 | 2 | 14 | 1 | 4
85 | 38/8 | DA+1.5 |  | 2025-03-19 | 37.1383 | COMPLETED | 2025-03-24 | Punam Devi-1
86 | 39/3 | DA+1.5 |  | 2025-03-20 | 37.1383 | COMPLETED | 2025-03-25 | Punam Devi-2
87 | 39/4 | DA+3 |  | 2025-03-21 | 37.9311 | COMPLETED | 2025-03-27 | Punam Devi-3
88 | 15/4 | DA+6 |  | 2025-03-23 | 43.8044 | COMPLETED | 2025-03-27 | Punam Devi-4
89 | 39/1 | DA-1.5 |  | 2025-03-22 | 35.6018 | COMPLETED | 2025-03-29 | Vasu dev singh-2
90 | 39/9 | DA+6 |  | 2025-03-25 | 43.8044 | COMPLETED | 2025-03-30 | Punam Devi-1
91 | 40/2 | DA+6 |  | 2025-03-26 | 43.8044 | COMPLETED | 2025-03-31 | Punam Devi-2
92 | 15/5 | DA+3 |  | 2025-03-26 | 37.9311 | COMPLETED | 2025-03-31 | Punam Devi-4
93 | 39/8 | DA+1.5 |  | 2024-03-26 | 37.1383 | COMPLETED | 2025-03-31 | Punam Devi-3
94 | 39/10 | DA+3 |  | 2025-03-31 | 37.9311 | COMPLETED | 2025-04-05 | Punam Devi-3
95 | 15/6 | DA+9 |  | 2025-03-31 | 45.697 | COMPLETED | 2025-04-06 | Punam Devi-4
96 | 39/11 | DA+6 |  | 2025-03-30 | 43.8044 | COMPLETED | 2025-04-09 | Punam Devi-1
97 | 40/3 | DA+3 |  | 2025-03-31 | 37.9311 | COMPLETED | 2025-04-09 | Punam Devi-2
98 | 38/0 | DB1+3 |  | 2025-03-29 | 57.9632 | COMPLETED | 2025-04-11 | Vasu dev singh-2
99 | 40/5 | DA+9 |  | 2025-04-05 | 45.697 | COMPLETED | 2025-04-14 | Punam Devi-3
100 | 40/4 | DA+6 |  | 2025-04-09 | 43.8044 | COMPLETED | 2025-04-18 | Punam Devi-2
101 | 39/6 | DA+1.5 |  | 2025-04-09 | 37.1383 | COMPLETED | 2025-04-18 | Punam Devi-1
102 | 40/6 | DA+9 |  | 2025-04-14 | 45.697 | COMPLETED | 2025-04-22 | Punam Devi-3
103 | 36A/0 | DB1+9 |  | 2025-04-18 | 66.7809 | COMPLETED | 2025-04-30 | Punam Devi-2
104 | 40/0 | DB1+6 |  | 2025-04-18 | 65.0278 | COMPLETED | 2025-04-30 | Punam Devi-1
105 | 32/6 | DA+9 |  | 2025-07-06 | 45.697 | COMPLETED | 2025-07-15 | Punam Kumari
106 | 32/1 | DA+6 |  | 2025-07-05 | 43.8044 | COMPLETED | 2025-07-17 | Amit Kumar Singh
107 | 7/3 | DA+9 |  | 2025-07-09 | 45.697 | COMPLETED | 2025-07-21 | Pritam Enterprises
108 | 32/5 | DA+9 |  | 2025-07-16 | 45.697 | COMPLETED | 2025-07-25 | Punam Kumari
109 | 6/1 | DA+9 |  | 2025-07-16 | 45.697 | COMPLETED | 2025-07-26 | Jwala Singh-1
110 | 32/2 | DA+9 |  | 2025-07-18 | 45.697 | COMPLETED | 2025-07-26 | Amit Kumar Singh
111 | 7/0 | DB2+0 |  | 2025-07-22 | 59.5006 | COMPLETED | 2025-07-31 | Pritam Enterprises
112 | 32/7 | DA+3 |  | 2025-07-26 | 37.9311 | COMPLETED | 2025-07-31 | Punam Kumari
113 | 31/0 | DB1+0 |  | 2025-07-16 | 55.4509 | COMPLETED | 2025-08-01 | SK Samiul -1
114 | 42/0 | DB2+0 |  | 2025-07-21 | 59.5006 | COMPLETED | 2025-08-02 | Fouzi Ratto
115 | 8/11 | DA+9 |  | 2025-07-15 | 45.697 | COMPLETED | 2025-08-03 | Jwala Singh-1
116 | 30/10 | DA+3 |  | 2025-07-18 | 37.9311 | COMPLETED | 2025-08-03 | SK.Samiul -2
117 | 32/3 | DA+6 |  | 2025-07-27 | 43.8044 | COMPLETED | 2025-08-05 | Amit Kumar Singh
118 | 42/1 | DA+3 |  | 2025-08-02 | 37.9311 | COMPLETED | 2025-08-06 | Fouzi Ratto
119 | 40/1 | DA+9 |  | 2025-07-06 | 45.697 | COMPLETED | 2025-08-07 | Bambole Traders
120 | 6/2 | DA+6 |  | 2025-08-04 | 43.8044 | COMPLETED | 2025-08-08 | Jwala Singh-1
121 | 32A/0 | DB1+9 |  | 2025-08-01 | 66.7809 | COMPLETED | 2025-08-09 | Punam Kumari
122 | 35/2 | DA+6 |  | 2025-08-01 | 43.8044 | COMPLETED | 2025-08-09 | Jwala Singh-2
123 | 6/12 | DA+1.5 |  | 2025-08-01 | 37.1383 | COMPLETED | 2025-08-09 | Pritam Enterprises-1
124 | 31/1 | DA+3 |  | 2025-08-02 | 37.9311 | COMPLETED | 2025-08-10 | SK Samiul -1
125 | 31/2 | DA+1.5 |  | 2025-08-04 | 37.1383 | COMPLETED | 2025-08-11 | SK.Samiul -2
126 | 42/2 | DA+9 |  | 2025-08-07 | 45.697 | COMPLETED | 2025-08-11 | Fouzi Ratto
127 | 40/9 | DA+9 |  | 2025-08-01 | 45.697 | COMPLETED | 2025-08-13 | Pinki Devi
128 | 6/5 | DA+9 |  | 2025-08-02 | 45.697 | COMPLETED | 2025-08-13 | Pritam Enterprises-2
129 | 32/4 | DA+9 |  | 2025-08-07 | 45.697 | COMPLETED | 2025-08-14 | Amit Kumar Singh
130 | 6/3 | DA+3 |  | 2025-08-08 | 37.9311 | COMPLETED | 2025-08-14 | Jwala Singh-1
131 | 8A/0 | DB1+12 |  | 2025-08-07 | 70.7883 | COMPLETED | 2025-08-14 | Punam Kumari-2
132 | 33/2 | DA+9 |  | 2025-08-09 | 45.697 | COMPLETED | 2025-08-17 | Punam Kumari-1
133 | 6/10 | DA+1.5 |  | 2025-08-09 | 37.1383 | COMPLETED | 2025-08-18 | Pritam Enterprises-1
134 | 9/5 | DA+3 |  | 2025-08-15 | 37.9311 | COMPLETED | 2025-08-19 | Punam Kumari-2
135 | 42/3 | DB1+9 |  | 2025-08-12 | 66.7809 | COMPLETED | 2025-08-19 | Fouzi Ratto
136 | 5/6 | DA+3 |  | 2025-08-08 | 37.9311 | COMPLETED | 2025-08-20 | Pritam Enterprises-4
137 | 40/7 | DA+3 |  | 2025-08-14 | 37.9311 | COMPLETED | 2025-08-20 | Pinki Devi
138 | 1/0 | DD60+0 |  | 2025-08-07 | 83.1335 | COMPLETED | 2025-08-21 | Pritam Enterprises-3
139 | 6/0 | DB1+9 |  | 2025-08-13 | 66.7809 | COMPLETED | 2025-08-21 | Jwala Singh-2
140 | 6/6 | DA-3 |  | 2025-08-14 | 34.7898 | COMPLETED | 2025-08-21 | Pritam Enterprises-2
141 | 6/4 | DA+9 |  | 2025-08-15 | 45.697 | COMPLETED | 2025-08-21 | Jwala Singh-1
142 | 30/9 | DA-3 |  | 2025-08-12 | 34.7898 | COMPLETED | 2025-08-21 | SK.Samiul -2
143 | 31/3 | DA+3 |  | 2025-08-12 | 37.9311 | COMPLETED | 2025-08-22 | SK Samiul -1
144 | 33/9 | DA+1.5 |  | 2025-08-18 | 37.1383 | COMPLETED | 2025-08-22 | Punam Kumari-1
145 | 6/11 | DA-1.5 |  | 2025-08-19 | 35.6018 | COMPLETED | 2025-08-25 | Pritam Enterprises-1
146 | 9/6 | DA+3 |  | 2025-08-20 | 37.9311 | COMPLETED | 2025-08-25 | Punam Kumari-2
147 | 43/2 | DA+6 |  | 2025-08-20 | 43.8044 | COMPLETED | 2025-08-25 | Fouzi Ratto
148 | 31/10 | DA+4.5 |  | 2025-08-15 | 42.9218 | COMPLETED | 2025-08-25 | Amit Kumar Singh
149 | 2A/1 | DA+0 |  | 2025-08-21 | 36.1598 | COMPLETED | 2025-08-27 | Pritam Enterprises-3
150 | 4A/4 | DA+6 |  | 2025-08-18 | 43.8044 | COMPLETED | 2025-08-28 | Govind Mahto-1
151 | 5/5 | DA+6 |  | 2025-08-20 | 43.8044 | COMPLETED | 2025-08-28 | Pritam Enterprises-4
152 | 6/7 | DA+1.5 |  | 2025-08-22 | 37.1383 | COMPLETED | 2025-08-28 | Pritam Enterprises-2
153 | 5/10 | DA+9 |  | 2025-08-22 | 45.697 | COMPLETED | 2025-08-28 | Jwala Singh-1
154 | 9/7 | DA+9 |  | 2025-08-23 | 45.697 | COMPLETED | 2025-08-29 | Punam Kumari-2
155 | 33/7 | DA+6 |  | 2025-08-23 | 43.8044 | COMPLETED | 2025-08-30 | Punam Kumari-1
156 | 31/4 | DA-1.5 |  | 2025-08-22 | 35.6018 | COMPLETED | 2025-08-31 | SK.Samiul -2
157 | 5A/0 | DB1+12 |  | 2025-08-22 | 70.7883 | COMPLETED | 2025-09-01 | Jwala Singh-2
158 | 32A/1 | DA+6 |  | 2025-08-14 | 43.8044 | COMPLETED | 2025-09-02 | Amar Kumar Singh
159 | 6/9 | DA+6 |  | 2025-08-23 | 43.8044 | COMPLETED | 2025-09-02 | Pritam Enterprises-2
160 | 2A/2 | DA+3 |  | 2025-08-28 | 37.9311 | COMPLETED | 2025-09-02 | Pritam Enterprises-3
161 | 43/3 | DA-1.5 |  | 2025-08-23 | 35.6018 | COMPLETED | 2025-09-02 | Fouzi Ratto
162 | 31/5 | DA+6 |  | 2025-08-23 | 43.8044 | COMPLETED | 2025-09-03 | SK Samiul -1
163 | 31/9 | DA+1.5 |  | 2025-08-23 | 37.1383 | COMPLETED | 2025-09-03 | Amit Kumar Singh
164 | 44/1 | DA+3 |  | 2025-08-25 | 37.9311 | COMPLETED | 2025-09-03 | Ved Prakash
165 | 33/3 | DA+3 |  | 2025-08-31 | 37.9311 | COMPLETED | 2025-09-04 | Punam Kumari-1
166 | 5/9 | DA+6 |  | 2025-08-29 | 43.8044 | COMPLETED | 2025-09-05 | Jwala Singh-1
167 | 6/8 | DA+3 |  | 2025-08-29 | 37.9311 | COMPLETED | 2025-09-06 | Pritam Enterprises-2
168 | 9/0 | DB1+12 |  | 2025-08-30 | 70.7883 | COMPLETED | 2025-09-06 | Punam Kumari-2
169 | 4A/3 | DA+9 |  | 2025-08-29 | 45.697 | COMPLETED | 2025-09-06 | Govind Mahto-1
170 | 43/4 | DA+0 |  | 2025-09-03 | 36.1598 | COMPLETED | 2025-09-07 | Fouzi Ratto
171 | 5/4 | DA-1.5 |  | 2025-08-29 | 35.6018 | COMPLETED | 2025-09-08 | Pritam Enterprises-4
172 | 2A/3 | DA+3 |  | 2025-09-03 | 37.9311 | COMPLETED | 2025-09-08 | Pritam Enterprises-3
173 | 4A/5 | DA+9 |  | 2025-08-25 | 45.697 | COMPLETED | 2025-09-08 | Govind Mahto-2
174 | 30/6 | DA+6 |  | 2025-08-29 | 43.8044 | COMPLETED | 2025-09-08 | Punam Kumari-3
175 | 5/7 | DA+9 |  | 2025-09-02 | 45.697 | COMPLETED | 2025-09-09 | Jwala Singh-2
176 | 44/2 | DA+3 |  | 2025-09-04 | 37.9311 | COMPLETED | 2025-09-09 | Ved Prakash
177 | 33/4 | DA+3 |  | 2025-09-05 | 37.9311 | COMPLETED | 2025-09-09 | Punam Kumari-1
178 | 33/1 | DA+9 |  | 2025-08-25 | 45.697 | COMPLETED | 2025-09-10 | Bhairaw Mahto
179 | 3A/1 | DA+3 |  | 2025-09-03 | 37.9311 | COMPLETED | 2025-09-11 | Pritam Enterprises-1
180 | 43/6 | DA+3 |  | 2025-09-08 | 37.9311 | COMPLETED | 2025-09-11 | Fouzi Ratto
181 | 4/5 | DA+6 |  | 2025-09-06 | 43.8044 | COMPLETED | 2025-09-12 | Jwala Singh-1
182 | 30/7 | DA-3 |  | 2025-09-09 | 34.7898 | COMPLETED | 2025-09-13 | Punam Kumari-3
183 | 32/0 | DB2+0 |  | 2025-09-04 | 59.5006 | COMPLETED | 2025-09-14 | Amit Kumar Singh
184 | 30/4 | DA+9 |  | 2025-09-09 | 45.697 | COMPLETED | 2025-09-15 | Punam Kumari-4
185 | 18/0 | DB2+6 |  | 2025-09-07 | 69.376 | COMPLETED | 2025-09-15 | Punam Kumari-2
186 | 2A/4 | DA+3 |  | 2025-09-09 | 37.9311 | COMPLETED | 2025-09-15 | Pritam Enterprises-3
187 | 5/8 | DA+6 |  | 2025-09-10 | 43.8044 | COMPLETED | 2025-09-15 | Jwala Singh-2
188 | 44/3 | DA+3 |  | 2025-09-10 | 37.9311 | COMPLETED | 2025-09-15 | Ved Prakash
189 | 3A/5 | DA+3 |  | 2025-09-07 | 37.9311 | COMPLETED | 2025-09-15 | Pritam Enterprises-2
190 | 4A/2 | DA+6 |  | 2025-09-07 | 43.8044 | COMPLETED | 2025-09-16 | Govind Mahto-1
191 | 31/7 | DA+0 |  | 2025-09-10 | 36.1598 | COMPLETED | 2025-09-16 | Punam Kumari-1
192 | 31/6 | DA+9 |  | 2025-09-04 | 45.697 | COMPLETED | 2025-09-18 | SK Samiul -1
193 | 4A/6 | DA+9 |  | 2025-09-09 | 45.697 | COMPLETED | 2025-09-18 | Govind Mahto-2
194 | 43/8 | DA+9 |  | 2025-09-14 | 45.697 | COMPLETED | 2025-09-19 | Fouzi Ratto
195 | 44/4 | DA+0 |  | 2025-09-16 | 36.1598 | COMPLETED | 2025-09-19 | Ved Prakash
196 | 3A/2 | DA+3 |  | 2025-09-12 | 37.9311 | COMPLETED | 2025-09-19 | Pritam Enterprises-1
197 | 40A/0 | DB1+9 |  | 2025-09-04 | 66.7809 | COMPLETED | 2025-09-20 | Kartik Mahto
198 | 33/0 | DB1+9 |  | 2025-09-03 | 66.7809 | COMPLETED | 2025-09-20 | Amar Kumar Singh
199 | 18/1 | DA+3 |  | 2025-09-16 | 37.9311 | COMPLETED | 2025-09-20 | Punam Kumari-2
200 | 31/8 | DA+0 |  | 2025-09-15 | 36.1598 | COMPLETED | 2025-09-21 | Amit Kumar Singh
201 | 30/8 | DA+3 |  | 2025-09-14 | 37.9311 | COMPLETED | 2025-09-22 | Punam Kumari-3
202 | 2A/5 | DA+3 |  | 2025-09-16 | 37.9311 | COMPLETED | 2025-09-23 | Pritam Enterprises-3
203 | 44/5 | DA+0 |  | 2025-09-20 | 36.1598 | COMPLETED | 2025-09-23 | Ved Prakash
204 | 3A/6 | DA+0 |  | 2025-09-16 | 36.1598 | COMPLETED | 2025-09-24 | Pritam Enterprises-2
205 | 4A/0 | DB1+3 |  | 2025-09-13 | 57.9632 | COMPLETED | 2025-09-24 | Jwala Singh-1
206 | 30/0 | DB1+0 |  | 2025-09-11 | 55.4509 | COMPLETED | 2025-09-25 | Punam Kumari-4
207 | 5/1 | DA+6 |  | 2025-09-13 | 43.8044 | COMPLETED | 2025-09-25 | Jwala Singh-2
208 | 4A/1 | DA+6 |  | 2025-09-18 | 43.8044 | COMPLETED | 2025-09-25 | Govind Mahto-1
209 | 20/1 | DA-3 |  | 2025-09-19 | 34.7898 | COMPLETED | 2025-09-25 | Punam Kumari-1
210 | 18/2 | DA+1.5 |  | 2025-09-21 | 37.1383 | COMPLETED | 2025-09-25 | Punam Kumari-2
211 | 12/0 | DB1+9 |  | 2025-09-11 | 66.7809 | COMPLETED | 2025-09-26 | Bhairaw Mahto
212 | 3A/3 | DA+0 |  | 2025-09-20 | 36.1598 | COMPLETED | 2025-09-27 | Pritam Enterprises-1
213 | 43/7 | DA+0 |  | 2025-09-24 | 36.1598 | COMPLETED | 2025-09-28 | Ved Prakash
214 | 44/0 | DB1+6 |  | 2025-09-20 | 65.0278 | COMPLETED | 2025-09-29 | Fouzi Ratto
215 | 40/11 | DA+9 |  | 2025-09-21 | 45.697 | COMPLETED | 2025-09-29 | Kartik Mahto
216 | 5/0 | DB1+6 |  | 2025-09-19 | 65.0278 | COMPLETED | 2025-09-30 | Govind Mahto-2
217 | 20/2 | DA-3 |  | 2025-09-26 | 34.7898 | COMPLETED | 2025-09-30 | Punam Kumari-1
218 | 18/3 | DA+6 |  | 2025-09-26 | 43.8044 | COMPLETED | 2025-09-30 | Punam Kumari-2
219 | 2A/6 | DA+6 |  | 2025-09-24 | 43.8044 | COMPLETED | 2025-09-30 | Pritam Enterprises-3
220 | 5/3 | DA+9 |  | 2025-09-09 | 45.697 | COMPLETED | 2025-09-30 | Pritam Enterprises-4
221 | 5/2 | DA+9 |  | 2025-09-26 | 45.697 | COMPLETED | 2025-09-30 | Jwala Singh-2
222 | 30/2 | DA+9 |  | 2025-09-24 | 45.697 | COMPLETED | 2025-10-04 | SK Samiul -1
223 | 41/1 | DA+9 |  | 2025-09-24 | 45.697 | COMPLETED | 2025-10-04 | Amar Kumar Singh
224 | 29A/5 | DA+6 |  | 2025-09-26 | 43.8044 | COMPLETED | 2025-10-04 | Punam Kumari-4
225 | 15/8 | DA+1.5 |  | 2025-09-27 | 37.1383 | COMPLETED | 2025-10-04 | Bhairaw Mahto
226 | 18/4 | DA-3 |  | 2025-10-01 | 34.7898 | COMPLETED | 2025-10-06 | Punam Kumari-2
227 | 3B/2 | DA+9 |  | 2025-09-26 | 45.697 | COMPLETED | 2025-10-07 | Govind Mahto-1
228 | 45/0 | DB1+9 |  | 2025-09-28 | 66.7809 | COMPLETED | 2025-10-09 | Ved Prakash
229 | 40/10 | DA+3 |  | 2025-09-30 | 37.9311 | COMPLETED | 2025-10-09 | Kartik Mahto
230 | 29A/4 | DA+3 |  | 2025-10-05 | 37.9311 | COMPLETED | 2025-10-10 | Punam Kumari-4
231 | 3A/4 | DA+0 |  | 2025-10-01 | 36.1598 | COMPLETED | 2025-10-10 | Pritam Enterprises-3
232 | 18/5 | DA+0 |  | 2025-10-07 | 36.1598 | COMPLETED | 2025-10-10 | Punam Kumari-2
233 | 3B/0 | DB1+9 |  | 2025-09-25 | 66.7809 | COMPLETED | 2025-10-12 | Pritam Enterprises-2
234 | 4/0 | DB2+9 |  | 2025-09-25 | 72.1555 | COMPLETED | 2025-10-12 | Jwala Singh-1
235 | 46/0 | DB1+12 |  | 2025-09-30 | 70.7883 | COMPLETED | 2025-10-12 | Fouzi Ratto
236 | 29/1 | DA+6 |  | 2025-10-07 | 43.8044 | COMPLETED | 2025-10-12 | Jwala Singh-2
237 | 18/6 | DA+9 |  | 2025-10-11 | 45.697 | COMPLETED | 2025-10-15 | Punam Kumari-2
238 | 20/0 | DD60+3 |  | 2025-10-01 | 87.0213 | COMPLETED | 2025-10-15 | Punam Kumari-1
239 | 3B/1 | DA+3 |  | 2025-10-09 | 37.9311 | COMPLETED | 2025-10-16 | Govind Mahto-1
240 | 10/0 | DB1+6 |  | 2025-10-02 | 65.0278 | COMPLETED | 2025-10-17 | Pritam Enterprises-1
241 | 40/8 | DA-1.5 |  | 2025-10-10 | 35.6018 | COMPLETED | 2025-10-19 | Kartik Mahto
242 | 41/0 | DB1+9 |  | 2025-10-08 | 66.7809 | COMPLETED | 2025-10-22 | Amar Kumar Singh
243 | 29A/0 | DB1+0 |  | 2025-10-06 | 55.4509 | COMPLETED | 2025-10-22 | SK Samiul -1
244 | 30/3 | DA+3 |  | 2025-10-12 | 37.9311 | COMPLETED | 2025-10-22 | Jwala Singh-2
245 | 18/7 | DA+1.5 |  | 2025-10-16 | 37.1383 | COMPLETED | 2025-10-22 | Punam Kumari-2
246 | 20/6 | DA-3 |  | 2025-10-17 | 34.7898 | COMPLETED | 2025-10-23 | Govind Mahto-1
247 | 29/0 | DC1+0 |  | 2025-10-08 | 62.4437 | COMPLETED | 2025-10-25 | Pritam Enterprises-4
248 | 3A/0 | DD45+3 |  | 2025-10-11 | 77.0769 | COMPLETED | 2025-10-26 | Pritam Enterprises-3
249 | 23/0 | DB2+9 |  | 2025-10-12 | 72.1555 | COMPLETED | 2025-10-27 | Bhairaw Mahto
250 | 19/0 | DD60+3 |  | 2025-10-16 | 87.0213 | COMPLETED | 2025-10-28 | Punam Kumari-1
251 | 9/11 | DA+3 |  | 2025-10-18 | 37.9311 | COMPLETED | 2025-10-28 | Pritam Enterprises-1
252 | 21/0 | DB1+0 |  | 2025-10-20 | 55.4509 | COMPLETED | 2025-10-29 | Kartik Mahto
253 | 21/1 | DA+0 |  | 2025-10-24 | 36.1598 | COMPLETED | 2025-10-29 | Govind Mahto-1
254 | 15/0 | DD60+25 |  | 2025-10-05 | 137.0461 | COMPLETED | 2025-10-30 | Govind Mahto-2
255 | 27/5 | DA-1.5 |  | 2025-10-23 | 35.6018 | COMPLETED | 2025-10-30 | Jwala Singh-2
256 | 10/1 | DA+3 |  | 2025-10-12 | 37.9311 | COMPLETED | 2025-10-31 | Jwala Singh-1
257 | 20/5 | DA+0 |  | 2025-10-28 | 36.1598 | COMPLETED | 2025-10-31 | Punam Kumari-1
258 | 20/3 | DA+1.5 |  | 2025-10-30 | 37.1383 | COMPLETED | 2025-11-05 | Govind Mahto-1
259 | 9/10 | DA+3 |  | 2025-10-31 | 37.9311 | COMPLETED | 2025-11-05 | Govind Mahto-2
260 | 20/4 | DA+3 |  | 2025-11-01 | 37.9311 | COMPLETED | 2025-11-06 | Punam Kumari-1
261 | 26/0 | DD60+35 |  | 2025-10-10 | 173.5609 | COMPLETED | 2025-11-07 | Ved Prakash
262 | 3B/3 | DA+6 |  | 2025-10-27 | 43.8044 | COMPLETED | 2025-11-08 | Pritam Enterprises-3
263 | 10/2 | DA+3 |  | 2025-11-01 | 37.9311 | COMPLETED | 2025-11-09 | Jwala Singh-1
264 | 9/9 | DA+0 |  | 2025-11-06 | 36.1598 | COMPLETED | 2025-11-12 | Govind Mahto-2
265 | 28/0 | DC2-3 |  | 2025-10-31 | 64.8843 | COMPLETED | 2025-11-12 | Jwala Singh-2
266 | 21/5 | DA+0 |  | 2025-11-07 | 36.1598 | COMPLETED | 2025-11-12 | Punam Kumari-1
267 | 21/2 | DA+6 |  | 2025-11-06 | 43.8044 | COMPLETED | 2025-11-13 | Govind Mahto-1
268 | 22/0 | DC2+15 |  | 2025-10-28 | 96.8799 | COMPLETED | 2025-11-13 | Bhairaw Mahto
269 | 15/7 | DA+0 |  | 2025-11-10 | 36.1598 | COMPLETED | 2025-11-15 | Jwala Singh-1
270 | 27/4 | DA+1.5 |  | 2025-10-27 | 37.1383 | COMPLETED | 2025-11-15 | Pritam Enterprises-4
271 | 21/4 | DA+0 |  | 2025-11-13 | 36.1598 | COMPLETED | 2025-11-20 | Punam Kumari-1
272 | 27/6 | DA-3 |  | 2025-11-13 | 34.7898 | COMPLETED | 2025-11-20 | Jwala Singh-2
273 | 15/10 | DA-1.5 |  | 2025-11-16 | 35.6018 | COMPLETED | 2025-11-21 | Jwala Singh-1
274 | 11/0 | DD45+0 |  | 2025-11-13 | 73.2445 | COMPLETED | 2025-11-26 | Govind Mahto-2
275 | 24/0 | DD60+18 |  | 2025-11-13 | 124.95 | COMPLETED | 2025-11-27 | Fouzi Ratto
276 | 27/2 | DA-1.5 |  | 2025-11-21 | 35.6018 | COMPLETED | 2025-11-27 | Jwala Singh-2
277 | 23A/0 | DB1+9 |  | 2025-11-14 | 66.7809 | COMPLETED | 2025-11-27 | Govind Mahto-1
278 | 21/3 | DA+6 |  | 2025-11-21 | 43.8044 | COMPLETED | 2025-11-27 | Punam Kumari-1
279 | 15/9 | DA+0 |  | 2025-11-22 | 36.1598 | COMPLETED | 2025-11-28 | Jwala Singh-1
280 | 27/0 | DD60+35 |  | 2025-11-08 | 173.5609 | COMPLETED | 2025-11-29 | Ved Prakash
281 | 25/0 | DD60+18 |  | 2025-11-12 | 124.95 | COMPLETED | 2025-11-29 | Pritam Enterprises-3
282 | 15/1 | DA+6 |  | 2025-11-27 | 43.8044 | COMPLETED | 2025-12-03 | Govind Mahto-2
283 | 27/3 | DA+1.5 |  | 2025-11-28 | 37.1383 | COMPLETED | 2025-12-05 | Jwala Singh-2
284 | 15/12 | DA+6 |  | 2025-11-29 | 43.8044 | COMPLETED | 2025-12-06 | Jwala Singh-1
285 | 9/8 | DA+0 |  | 2025-12-04 | 36.1598 | COMPLETED | 2025-12-12 | Govind Mahto-2
286 | 27/1 | DA+9 |  | 2025-12-05 | 45.697 | COMPLETED | 2025-12-14 | Jwala Singh-2
287 | 14/0 | DD60+18 |  | 2025-11-30 | 124.95 | COMPLETED | 2025-12-17 | Ved Prakash
288 | 29/2 | DA+0 |  | 2025-12-12 | 36.1598 | COMPLETED | 2025-12-20 | Jwala Singh-1
289 | 43/5 | DCT+0 |  | 2025-11-30 | 82.998 | COMPLETED | 2025-12-21 | Pritam Enterprises-2
290 | 15/11 | DA+0 |  | 2025-12-07 | 36.1598 | COMPLETED | 2025-12-21 | Govind Mahto-1
291 | 17/0 | DC1+3 |  | 2025-11-16 | 65.8725 | COMPLETED | 2025-12-23 | Pritam Enterprises-1
292 | 30/5 | DA+0 |  | 2025-12-21 | 36.1598 | COMPLETED | 2025-12-26 | Jwala Singh-1
293 | 43/1 | DA-1.5 |  | 2025-12-22 | 35.6018 | COMPLETED | 2025-12-31 | Pritam Enterprises-2
294 | 13/0 | DD60+9 |  | 2025-12-18 | 101.9526 | COMPLETED | 2025-12-31 | Ved Prakash
295 | 29A/3 | DA+6 |  | 2025-12-27 | 43.8044 | COMPLETED | 2026-01-06 | Jwala Singh-1
296 | 35/3 | DA-3 |  | 2026-01-07 | 34.7898 | COMPLETED | 2026-01-11 | Jwala Singh-1
297 | 13A/0 | DB1+9 |  | 2026-01-01 | 66.7809 | COMPLETED | 2026-01-20 | Ved Prakash
298 | 37/2 | DA+3 |  | 2026-01-12 | 37.9311 | COMPLETED | 2026-01-22 | Jwala Singh-1
299 | 2A/0 | DD45+0 |  | 2026-01-01 | 73.2445 | COMPLETED | 2026-01-25 | Pritam Enterprises-2
300 | 37/3 | DA-1.5 |  | 2026-01-23 | 35.6018 | COMPLETED | 2026-01-29 | Jwala Singh-1
301 | 36/0 | DB2+3 |  | 2026-01-22 | 62.1162 | COMPLETED | 2026-02-04 | Ved Prakash
302 | 43/0 | DB1+0 |  | 2026-02-01 | 55.4509 | COMPLETED | 2026-02-14 | Jwala Singh
303 | 35/10 | DA+3 |  | 2026-02-07 | 37.9311 | COMPLETED | 2026-02-16 | Ved Prakash

## Stringing Compiled
|  | Number of TSE | 2
S.no | From AP | To AP | Location Nos. | Span (M) | Method | Section Readiness | Insulator Hoisting | P/O Starting Date | P/O Completion Date | P/O | F/S Starting Date | F/S/ Completion Date | Jumpering | Spacering | Clipping | Length | Status | Gang Name | Gang Strength | Number of Fitters | Hindrance | Remarks
1 | Gantry | 1/0 |  | 150.014 | Manual | Ready
2 | 1/0 | 2A/0 |  | 290.21 | Manual | Ready |  | 2026-02-14 | 2026-02-18 | 290.21 | 2026-03-09 | 2026-03-13 |  |  |  | 290.21 | Completed | Rahim Khan
3 | 2A/0 | 3A/0 |  | 2836.992 | TSE | Ready |  | 2026-02-18 | 2026-02-26 | 2836.992 | 2026-02-27 | 2026-03-03 |  |  |  | 2836.992 | Completed | Rahim Khan
4 | 3A/0 | 3B/0 |  | 2691.467 | TSE | Ready |  | 2026-02-08 | 2026-02-13 | 2691.467 | 2026-02-27 | 2026-03-03 |  |  |  | 2691.467 | Completed | Rahim Khan
5 | 3B/0 | 4/0 |  | 1627.07 | TSE | Ready |  | 2026-01-14 | 2026-01-17 | 1627.07 | 2026-01-24 | 2026-01-27 |  |  |  | 1627.07 | Completed | Rahim Khan
6 | 4/0 | 4A/0 |  | 709.163 | TSE | Ready |  | 2025-12-27 | 2025-12-31 | 709.163 | 2026-01-14 | 2026-01-18 |  |  |  | 709.163 | Completed | Rahim Khan
7 | 4A/0 | 5/0 |  | 2681.611 | TSE | Ready |  | 2025-12-15 | 2025-12-22 | 2681.611 | 2025-12-30 | 2025-12-31 |  |  |  | 2681.611 | Completed | Rahim Khan
8 | 5/0 | 5A/0 |  | 4418.389 | TSE | Ready |  | 2025-12-07 | 2025-12-12 | 4418.389 | 2025-12-21 | 2025-12-22 |  |  |  | 4418.389 | Completed | Rahim Khan
9 | 5A/0 | 6/0 |  | 419.48 | Manual | Ready |  | 2025-11-05 | 2025-11-09 | 419.48 | 2025-12-11 | 2025-12-12 |  |  |  | 419.48 | Completed | Rahim Khan
10 | 6/0 | 7/0 |  | 4901.236 | TSE | Ready |  | 2025-11-19 | 2025-11-23 | 4901.236 | 2025-11-27 | 2025-11-28 |  |  |  | 4901.236 | Completed | Rahim Khan
11 | 7/0 | 7A/0 |  | 2699.284 | TSE | Ready |  | 2025-08-27 | 2025-09-04 | 2699.284 | 2025-09-17 | 2025-09-18 |  |  |  | 2699.284 | Completed | Rahim Khan
12 | 7A/0 | 8/0 |  | 2434.77 | TSE | Ready |  | 2025-09-12 | 2025-09-16 | 2434.77 | 2025-09-24 | 2025-09-25 |  |  |  | 2434.77 | Completed | Rahim Khan
13 | 8/0 | 8A/0 |  | 4455 | TSE | Ready |  | 2025-10-05 | 2025-10-15 | 4455 | 2025-10-21 | 2025-10-22 |  |  |  | 4455 | Completed | Rahim Khan
14 | 8A/0 | 9/0 |  | 466.63 | Manual | Ready |  | 2025-10-03 | 2025-10-05 | 466.63 | 2025-10-26 | 2025-10-27 |  |  |  | 466.63 | Completed | Rahim Khan
15 | 9/0 | 10/0 |  | 4964.92 | TSE | Ready |  | 2026-03-28 | 2026-04-02 | 4964.92 | 2026-03-06 | 2026-04-10 |  |  |  | 4964.92 | Completed | Rahim Khan
16 | 10/0 | 11/0 |  | 1004.183 | TSE | Ready |  | 2026-04-07 | 2026-04-09 | 1004.183
17 | 11/0 | 12/0 |  | 242.89 | Manual | Ready
18 | 12/0 | 13/0 |  | 329.73 | Manual | Ready
19 | 13/0 | 13A/0 |  | 416.88 | Manual | Ready
20 | 13A/0 | 14/0 |  | 480.27 | Manual | Ready
21 | 14/0 | 15/0 |  | 223.82 | Manual | Ready
22 | 15/0 | 16/0 |  | 5019.34 | TSE | Ready
23 | 16/0 | 17/0 |  | 392.69 | Manual | Ready
24 | 17/0 | 18/0 |  | 398.4 | Manual | Ready
25 | 18/0 | 19/0 |  | 3030.029 | TSE | Ready
26 | 19/0 | 20/0 |  | 279.36 | Manual | Ready
27 | 20/0 | 21/0 |  | 2550.167 | TSE | Ready
28 | 21/0 | 22/0 |  | 2283.535 | TSE | Ready
29 | 22/0 | 23/0 |  | 259.05 | Manual | Ready
30 | 23/0 | 23A/0 |  | 440.46 | Manual | Ready
31 | 23A/0 | 24/0 |  | 496.69 | Manual | Ready
32 | 24/0 | 25/0 |  | 244.03 | Manual | Ready
33 | 25/0 | 26/0 |  | 237.43 | Manual | Ready
34 | 26/0 | 27/0 |  | 203.48 | Manual | Ready
35 | 27/0 | 28/0 |  | 2548.275 | TSE | Ready
36 | 28/0 | 29/0 |  | 211.21 | Manual | Ready
37 | 29/0 | 29A/0 |  | 2379.204 | TSE | Ready
38 | 29A/0 | 30/0 |  | 2669.008 | TSE | Ready |  | 2026-04-22 | 2026-04-28 | 2669.008 | 2026-04-30 | 2026-05-03 |  |  |  | 2669.008 | Completed | SK Infratech
39 | 30/0 | 31/0 |  | 4124.232 | TSE | Ready |  | 2026-02-27 | 2026-03-06 | 4124.232 | 2026-03-12 | 2026-03-16 |  |  |  | 4124.232 | Completed | SK Infratech
40 | 31/0 | 32/0 |  | 4333.369 | TSE | Ready |  | 2026-02-10 | 2026-02-15 | 4333.369 | 2026-03-02 | 2026-03-10 |  |  |  | 4333.369 | Completed | SK Infratech
41 | 32/0 | 32A/0 |  | 3283.51 | TSE | Ready |  | 2026-01-25 | 2026-01-30 | 3283.51 | 2026-01-31 | 2026-02-06 |  |  |  | 3283.51 | Completed | SK Infratech
42 | 32A/0 | 33/0 |  | 840.439 | TSE | Ready |  | 2026-01-16 | 2026-01-19 | 840.439 | 2026-01-31 | 2026-02-06 |  |  |  | 840.439 | Completed | SK Infratech
43 | 33/0 | 34/0 |  | 4049.763 | TSE | Ready |  | 2026-01-07 | 2026-01-13 | 4049.763 | 2026-01-21 | 2026-01-24 |  |  |  | 4049.763 | Completed | SK Infratech
44 | 34/0 | 35/0 |  | 4898.588 | TSE | Ready |  | 2025-02-21 | 2025-02-26 | 4898.588 | 2025-03-01 | 2025-03-04 |  |  |  | 4898.588 | Completed | SK Infratech
45 | 35/0 | 36/0 |  | 4916.293 | TSE | Ready
46 | 36/0 | 36A/0 |  | 454 | Manual | Ready
47 | 36A/0 | 36B/0 |  | 826.7 | TSE | Ready
48 | 36B/0 | N37/0 |  | 420.81 | Manual | Ready
49 | N37/0 | N37A/0 |  | 469.33 | Manual | Ready
50 | N37A/0 | 37A/0 |  | 2076.28 | TSE | Ready
51 | 37A/0 | 38/0 |  | 2583.589 | TSE | Ready |  | 2025-03-17 | 2025-03-20 | 2583.589 | 2025-04-12 | 2025-04-16 |  |  |  | 2583.589 | Completed | SK Infratech
52 | 38/0 | 39/0 |  | 4163.677 | TSE | Ready |  | 2025-03-29 | 2025-04-05 | 4163.677 | 2025-04-10 | 2025-04-16 |  |  |  | 4163.677 | Completed | SK Infratech
53 | 39/0 | 40/0 |  | 4716.811 | TSE | Ready |  | 2025-04-20 | 2025-04-25 | 4716.811 | 2025-04-25 | 2025-04-30 |  |  |  | 4716.811 | Completed | SK Infratech
54 | 40/0 | 40A/0 |  | 4665.918 | TSE | Ready
55 | 40A/0 | 41/0 |  | 410.61 | Manual | Ready
56 | 41/0 | 42/0 |  | 823.782 | TSE | Ready
57 | 42/0 | 42/3 |  | 1258.998 | TSE | Ready
58 | 42/3 | 43/0 |  | 424.891 | Manual | Ready
59 | 43/0 | 43/5 |  | 1851.866 | TSE | Ready
60 | 43/5 | 44/0 |  | 1584.546 | TSE | Ready
61 | 44/0 | 45/0 |  | 2383.155 | TSE | Ready
62 | 45/0 | 46/0 |  | 208.53 | Manual | Ready
|  | Total |  | 117.8561 | [5 empty] | 72.2634 | [5 empty] | 71.2592
Formulas:
F/S Starting Date = [F/S/ Completion Date]-1