## Visual Chart (hidden)
VISUAL PROGRESS CHART
TL-02 765 KV D/C Kurnool IV - Bidar Transmission Line
Foundation (Nos.):- |  | 0 | / 297 | Erection (Nos.):- |  |  | / 297 | Earthing (Nos.):- |  |  | / 297 | Rough Sag (Kms):- |  |  | 113.292 | Final Sag (Kms):- |  |  | 113.292 | Date:- | 46151
COMPLETION CHART | -3 | +0 | +3 | +6 | +9 | Total | Line Qty
[8 empty] | ERECTION | [5 empty] | Rough Sag |  | SH / NH Road Crossing
[8 empty] | WIP | [11 empty] | River
DA | [5 empty] | 0 |  |  | Type |  | Angle Tower |  |  |  |  | Gas Pipeline
DB1 | [5 empty] | 0 |  | FOUNDATION
DB2 | [5 empty] | 0 | [6 empty] | Final Sag
DC1 | [5 empty] | 0
DC2 | [5 empty] | 0 | [10 empty] | Railway
DCT | [5 empty] | 0 | [8 empty] | WIP
DD45 | [5 empty] | 0 |  | Section Tower | SC | [7 empty] | Crossing |  |  | 110-800 KV
DD60 | [5 empty] | 0 |  | TP | TT |  | Earthing |  |  | OPGW | [5 empty] | Line
Total Completed Foundations | [5 empty] | 0 | 0
110kv OHTL
SH -122
| 411 |  | 432 |  | 408 |  | 433 |  | 409 |  | 432 |  | 375 |  | 414 |  | 403 |  | 406 |  | 319 |  | 384
48/0 |  | 48/1 |  | 48/2 |  | 48/3 |  | 48/4 |  | 48/5 |  | 48/6 |  | 48/7 |  | 49/0 |  | 49/1 |  | 49/2 |  | 49/3
3DB1+0 |  | 3DA+6 |  | 3DA+0 |  | 3DA+6 |  | 3DA+3 |  | 3DA+3 |  | 3DA+3 |  | 3DA+6 |  | 3DC1+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0
| 385 |  | 409 |  | 369 |  | 350 |  | 395 |  | 412 |  | 366 |  | 383 |  | 300 |  | 393 |  | 414 |  | 412
49/4 |  | 49/5 |  | 49/6 |  | 49/7 |  | 49/8 |  | 49/9 |  | 49/10 |  | 49/11 |  | 50/0 |  | 50/1 |  | 50/2 |  | 50/3
3DA+0 |  | 3DA+6 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DC2+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3
| 377 |  | 369 |  | 369 |  | 403 |  | 374 |  | 416 |  | 424 |  | 401 |  | 437 |  | 369 |  | 361 |  | 458
51/0 |  | 51/1 |  | 51/2 |  | 51/3 |  | 51/4 |  | 51/5 |  | 51/6 |  | 51/7 |  | 51/8 |  | 51/9 |  | 51/10 |  | 52/0
3DC2+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DB2+0
[22 empty] | RWY Xing | TDR-VBD
| 355 |  | 347 |  | 430 |  | 408 |  | 402 |  | 411 |  | 397 |  | 404 |  | 398 |  | 430 |  | 320 |  | 230
52/1 |  | 52/2 |  | 52/3 |  | 52/4 |  | 53/0 |  | 53/1 |  | 53/2 |  | 53/3 |  | 53/4 |  | 53/5 |  | 53/6 |  | 54/0
3DA+9 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DB2+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DD60+0
| 339 |  | 365 |  | 409 |  | 343 |  | 352 |  | 419 |  | 410 |  | 413 |  | 407 |  | 352 |  | 405 |  | 393
55/0 |  | 55/1 |  | 55/2 |  | 55/3 |  | 56/0 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | 56/6 |  | 56/7
3DD60+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DC1+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0
220KV D/C OHTL
TDR-GBL
| 439 |  | 398 |  | 445 |  | 355 |  | 447 |  | 215 |  | 498 |  | 325 |  | 388 |  | 381 |  | 349 |  | 373
56/8 |  | 56/9 |  | 56/10 |  | 56/11 |  | 56/12 |  | 57/0 |  | 58/0 |  | 58/1 |  | 58/2 |  | 58/3 |  | 59/0 |  | 59/1
3DA+0 |  | 3DA+6 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DC1+9 |  | 3DB2+6 |  | 3DA+6 |  | 3DA+0 |  | 3DA+3 |  |  |  | 3DA+0
| 386 |  | 429 |  | 377 |  | 405 |  | 425 |  | 344 |  | 399 |  | 439 |  | 403 |  | 480 |  | 535 |  | 389
59/2 |  | 59/3 |  | 59/4 |  | 59/5 |  | 60/0 |  | 60/1 |  | 60/2 |  | 60/3 |  | 60/4 |  | 60/5 |  | 60/6 |  | 60/7
3DA+0 |  | 3DA+0 |  | 3DA+6 |  | 3DA+0 |  | 3DB2+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+6 |  | 3DA+0 |  | 3DB1+6 |  | 3DB1+9 |  | 3DB1+9
NH-163
KDL-HYD
| 454 |  | 247 |  | 373 |  | 401 |  | 388 |  | 328 |  | 330 |  | 331 |  | 361 |  | 306 |  | 336 |  | 278
60/8 |  | 61/0 |  | 62/0 |  | 62/1 |  | 62/2 |  | 62/3 |  | 62/4 |  | 63/0 |  | 63/1 |  | 63/2 |  | 63/3 |  | 63/4
3DA+3 |  | 3DB1+0 |  | 3DC1+0 |  | 3DA+0 |  | 3DA+9 |  | 3DA+0 |  | 3DA+0 |  | 3DC2+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0
| 439 |  | 401 |  | 350 |  | 335 |  | 314 |  | 421 |  | 466 |  | 352 |  | 403 |  | 373 |  | 362 |  | 351
64/0 |  | 65/0 |  | 65/1 |  | 65/2 |  | 65/3 |  | 66/0 |  | 66/1 |  | 67/0 |  | 67/1 |  | 67/2 |  | 67/3 |  | 67/4
3DC2+0 |  | 3DC2+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DC1+3 |  | 3DB1+6 |  | 3DD45+6 |  | 3DA+9 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3
220KV D/C OHTL
TDR-MBR
| 361 |  | 375 |  | 425 |  | 429 |  | 350 |  | 483 |  | 453 |  | 388 |  | 317 |  | 324 |  | 485 |  | 249
68/0 |  | 68/1 |  | 68/2 |  | 69/0 |  | 69/1 |  | 69/2 |  | 70/0 |  | 70/1 |  | 70/2 |  | 70/3 |  | 70/4 |  | 71/0
3DB2+0 |  | 3DA+3 |  | 3DA+6 |  | 3DB2+6 |  | 3DA+9 |  | 3DA+6 |  | 3DC2+3 |  | 3DA+9 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DC2+9
[11 empty] | NH-167N | [9 empty] | 132KV S/C OHTL
[11 empty] | KDL-KSG | [9 empty] | KSG-PRG
| 429 |  | 399 |  | 435 |  | 404 |  | 374 |  | 250 |  | 398 |  | 364 |  | 380 |  | 459 |  | 206 |  | 385
72/0 |  | 72/1 |  | 73/0 |  | 73/1 |  | 73/2 |  | 74/0 |  | 75/0 |  | 75/1 |  | 75/2 |  | 75/3 |  | 76/0 |  | 77/0
3DB2+9 |  | 3DA+3 |  | 3DB2+0 |  | 3DA+6 |  | 3DA+0 |  | 3DC1+0 |  | 3DC1+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DC1+9 |  | 3DD45+6
| 372 |  | 384 |  | 400 |  | 386 |  | 398 |  | 393 |  | 387 |  | 378 |  | 410 |  | 368 |  | 396 |  | 395
77/1 |  | 77/2 |  | 77/3 |  | 77/4 |  | 77/5 |  | 77/6 |  | 77/7 |  | 77/8 |  | 77/9 |  | 77/10 |  | 78/0 |  | 78/1
3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DC1+0 |  | 3DA+3
NH-161B
| 414 |  | 350 |  | 356 |  | 460 |  | 379 |  | 383 |  | 400 |  | 421 |  | 323 |  | 312 |  | 360 |  | 301
78/2 |  | 78/3 |  | 79/0 |  | 79/1 |  | 79/2 |  | 79/3 |  | 80/0 |  | 80/1 |  | 80/2 |  | 80/3 |  | 80/4 |  | 80/5
3DA+3 |  | 3DA+0 |  | 3DC1+0 |  | 3DA+3 |  | 3DA+6 |  | 3DA+9 |  | 3DB2+9 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0
| 379 |  | 394 |  | 410 |  | 404 |  | 436 |  | 437 |  | 406 |  | 438 |  | 412 |  | 413 |  | 328 |  | 385
80/6 |  | 81/0 |  | 81/1 |  | 81/2 |  | 81/3 |  | 82/0 |  | 82/1 |  | 82/2 |  | 83/0 |  | 83/1 |  | 83/2 |  | 84/0
3DA+0 |  | 3DD45+9 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DC1+9 |  | 3DA+0 |  | 3DA+6 |  | 3DB2+6 |  | 3DA+0 |  | 3DA+3 |  | 3DB1+0
| 415 |  | 394 |  | 362 |  | 386 |  | 425 |  | 412 |  | 337 |  | 323 |  | 329 |  | 315 |  | 465 |  | 374
84/1 |  | 84/2 |  | 84/3 |  | 84/4 |  | 84/5 |  | 84/6 |  | 84/7 |  | 85/0 |  | 85/1 |  | 85/2 |  | 85/3 |  | 85/4
3DA+6 |  | 3DA+6 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DB1+6 |  | 3DA+9 |  | 3DA+6 |  | 3DA+3 |  | 3DA+3
| 400 |  | 359 |  | 468 |  | 287 |  | 416 |  | 352 |  | 361 |  | 426 |  | 394 |  | 384 |  | 414 |  | 480
86/0 |  | 86/1 |  | 87/0 |  | 88/0 |  | 89/0 |  | 89/1 |  | 90/0 |  | 90/1 |  | 90/2 |  | 90/3 |  | 90/4 |  | 90/5
3DC1+6 |  | 3DA+3 |  | 3DC1+3 |  | 3DB1+9 |  | 3DC1+6 |  | 3DA+0 |  | 3DB2+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DB1+9
| 395 |  | 329 |  | 418 |  | 467 |  | 443 |  | 311 |  | 479 |  | 321 |  | 506 |  | 421 |  | 421 |  | 406
91/0 |  | 91/1 |  | 91/2 |  | 92/0 |  | 92/1 |  | 92/2 |  | 93/0 |  | 93/1 |  | 93/2 |  | 93/3 |  | 94/0 |  | 94/1
3DC2+3 |  | 3DA+3 |  | 3DA+6 |  | 3DD45+0 |  | 3DB1+9 |  | 3DA+0 |  | 3DB2+3 |  | 3DA+3 |  | 3DA+9 |  | 3DB1+9 |  | 3DC1+3 |  | 3DA+0
| 435 |  | 533 |  | 265 |  | 484 |  | 611 |  | 367 |  | 469 |  | 371 |  | 370 |  | 327 |  | 318 |  | 340
94/2 |  | 94/3 |  | 95/0 |  | 96/0 |  | 96/1 |  | 96/2 |  | 96/3 |  | 96/4 |  | 96/5 |  | 96/6 |  | 96/7 |  | 96/8
3DA+3 |  | 3DB1+9 |  | 3DD45+9 |  | 3DD45+9 |  | 3DB1+0 |  | 3DB1+0 |  | 3DA+6 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0
| 396 |  | 377 |  | 398 |  | 393 |  | 374 |  | 363 |  | 349 |  | 386 |  | 390 |  | 417 |  | 423 |  | 340
97/0 |  | 97/1 |  | 97/2 |  | 97/3 |  | 97/4 |  | 98/0 |  | 98/1 |  | 98/2 |  | 98/3 |  | 98/4 |  | 98/5 |  | 99/0
3DB2+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DC1+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+6 |  | 3DC1+0
| 365 |  | 403 |  | 382 |  | 395 |  | 385 |  | 381 |  | 395 |  | 403 |  | 383 |  | 386 |  | 397 |  | 371
99/1 |  | 99/2 |  | 99/3 |  | 99/4 |  | 99/5 |  | 99/6 |  | 99/7 |  | 99/8 |  | 99/9 |  | 99/10 |  | 99/11 |  | 99/12
3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0
| 422 |  | 417 |  | 400 |  | 421 |  | 419 |  | 402 |  | 402 |  | 411 |  | 355 |  | 390 |  | 380 |  | 390
100/0 |  | 100/1 |  | 100/2 |  | 100/3 |  | 100/4 |  | 100/5 |  | 100/6 |  | 100/7 |  | 100/8 |  | 101/0 |  | 101/1 |  | 101/2
3DB2+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DB1+0 |  | 3DA+0 |  | 3DA+0
| 422 |  | 417 |  | 400 |  | 421 |  | 419 |  | 402 |  | 402 |  | 411 |  | 355 |  | 390 |  | 380 |  | 390
100/0 |  | 100/1 |  | 100/2 |  | 100/3 |  | 100/4 |  | 100/5 |  | 100/6 |  | 100/7 |  | 100/8 |  | 101/0 |  | 101/1 |  | 101/2
3DB2+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DB1+0 |  | 3DA+0 |  | 3DA+0
C

## Master Sheet
| Project Code | TA-601 |  |  | Date as on | 2026-05-09 | SBU Head | Mr. Rajinder Gupta
| Project Name | 765kV D/C Kurnool IV - Bidar trnasmission line (Part II) |  |  | LOA Start Date | 13.05.2025 | PCH | Mr. Arun Felbin R
| Client Name | POWERGRID KURNOOL IV TRANSMISSION LIMITED |  |  | LOA End Date | 12.04.2027 | Regional Manager | Mr. Ajith Kumar MG
| Duration | 23 Months |  |  | Planning Engineer | Mr. Siddhesh Bhoyar | Chief Manger | Mr. Senthil Jayaraman
Survey Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Completed till Last Month | Approved till Last Month | Balance to Submit | Plan for Current Month | Balance to Approve | L2 Submission Plan for Current Month | Approved till Current Month | Remarks
Detailed Survey | kms | 113.286 | 113.286 | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 113.286
Check Survey | kms | 113.286 | 113.286 | 113.286 | 113.266 | 0 | 0.4 | 0.4 | 0 | 113.266
Foundation Status
Activity | Scope Quantity | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month | Plan for the Month | Today's Progress | Progress for Current Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks
Foundation | 292 | 252 | 113 | 25 | 40 | 0 | 2 | 277 | 115 | 177 | 4 | 3
Earthing | 292 | 252 | 89 | 25 | 40 | 0 | 2 | 277 | 91 | 201
Tower Erection | 292 | 290 | 70 | 35 | 35 | 0 | 0 | 225 | 70 | 222
Stringing -R/S | 113.286 | 17 | 0 | 12 | 0 | 0 | 0 | 29 | 0 | 113.286
Stringing -F/S | 113.286 | 17 | 0 | 12 | 0 | 0 | 0 | 29 | 0 | 113.286
OPGW | 113.286 | 17 | 0 | 12 | 0 | 0 | 0 | 29 | 0 | 113.286
NH Crossing | 3 | [8 empty] | 3
SH Crossing | 1 | [8 empty] | 1
Railway crossing | 2 | [8 empty] | 2
Power Line Crossing | 6 | [8 empty] | 6
WIP - Foundations | Pit A | Pit B | Pit C | Pit D | Gang |  |  |  | WIP-Erection | Status | Gang
48/7 | RCC (F&B) | RCC (F&B) | RCC (F&B) | RCC (F&B) | BALAJI Services |  |  |  | 60/0 | 1st Section WIP | 1st Section Completed
48/1 | Blasting | Blasting | Blasting | Blasting | BALAJI Services
48/2 | Block Level | Block Level | Blasting | Blasting | BALAJI Services
69/0 | Dewatering | Steel Binding | Dewatering | RCC (F&B) | ATK
Supply Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Received till Last Month | Balance | L2 Plan for Current Month | Plan for Current Month | Progress for the Month | Received till Current Month | Gap between Supply & Cumm.L2 | Remarks
Stub | Set | 292 | 292 | 235 | 57 | 0 | 0 | 0 | 235 | 57
Tower | No's | 292 | 230 | 230 | 62 | 60 | 60 | 0 | 230 | 60
AL59 Conductor | kms | 4314 | 3000 | 3285.198 | 1028.802 | 300 | 300 | 0 | 3285.198 | 14.802 | 1104 Drums Received
Support Required :
1) RC Foundation Drawings Required- DB,DC,DD45,DD60 (1MRC,2MRC,3MRC)

## Progress Sheet
Survey Status
Activity | Unit | Final Est. Qty | L2 till Last Month |  | Completed till Last Month | Approved till Last Month | Balance to Submit | Balance to Approve | L2 Submission Plan for Current Month | Progress For Month | Approved till Current Month | Remarks
Detailed Survey | kms | 113.286 | 113.286 |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 113.286
Check Survey | kms | 113.286 | 113.286 |  | 113.286 | 113.266 | 0 | 0.4 | 20 | 0.4 | 113.266
PROGRESS - Check Survey
S.No | Section |  | Length |  | Check survey status
115
PROGRESS - FDN & EREC
S.No | Location No. | Tower Type | Classification | ROW cleared date | Start Date | Conc Volume | Foundation Status |  |  |  | End Date | Gang Name | Erection Status | Gang Strength | Remarks
1 | 81/2 | DA+3 | DFR | 2025-07-16 | 2025-07-16 | 26.43 | Foundation completed. |  |  |  | 2025-08-07 | MARC |  | 10
2 | 82/1 | DA+0 | WC | 2025-07-10 | 2025-07-11 | 22.4 | Foundation completed. |  |  |  | 2025-08-22 | MARC |  | 10
3 | 81/1 | DA+0 | DFR | 0 | 2025-08-23 | 23.27 | Foundation completed. |  |  |  | 2025-09-13 | MARC |  | 10
4 | 80/5 | DA+0 | DRY | 2025-08-29 | 2025-09-02 | 21.96 | Foundation completed. |  |  |  | 2025-09-18 | MARC |  | 10
5 | 80/1 | DA+6 | WFR | 2025-08-28 | 2025-08-29 | 36.66 | Foundation completed. |  |  |  | 2025-10-10 | MARC |  | 10
6 | 59/5 | DA+0 | DRY | 2025-09-30 | 2025-10-08 | 21.96 | Foundation completed. |  |  |  | 2025-10-19 | SHRIARSHINI |  | 10
7 | 84/3 | DA+0 | DRY | 2025-09-19 | 2025-10-10 | 21.96 | Foundation completed. |  |  |  | 2025-10-19 | SHIVRATHIRI BALRAJ |  | 10
8 | 59/4 | DA+6 | DRY | 2025-10-03 | 2025-10-08 | 25.04 | Foundation completed. |  |  |  | 2025-10-21 | SHRIARSHINI |  | 20
9 | 84/4 | DA+0 | DRY | 2025-09-25 | 2025-10-11 | 21.96 | Foundation completed. |  |  |  | 2025-10-24 | SHIVRATHIRI BALRAJ |  | 10
10 | 60/2 | DA+0 | DFR |  | 2025-10-14 | 23.27 | Foundation completed. |  |  |  | 2025-10-25 | SHRIARSHINI |  | 20
11 | 80/4 | DA+3 | WFR | 2025-09-19 | 2025-09-23 | 36.66 | Foundation completed. |  |  |  | 2025-10-27 | MARC |  | 10
12 | 77/4 | DA+0 | DRY | 2025-09-16 | 2025-09-17 | 21.96 | Foundation completed. |  |  |  | 2025-10-31 | SHIVRATHIRI BALRAJ |  | 10
13 | 77/10 | DA+3 | DRY |  | 2025-10-27 | 25.04 | Foundation completed. |  |  |  | 2025-11-05 | SHIVRATHIRI BALRAJ |  | 10
14 | 59/2 | DA+0 | DRY |  | 2025-10-29 | 21.96 | Foundation completed. |  |  |  | 2025-11-08 | SHRIARSHINI |  | 15
15 | 77/7 | DA+0 | DFR |  | 2025-11-02 | 23.27 | Foundation completed. |  |  |  | 2025-11-09 | SHIVRATHIRI BALRAJ |  | 10
16 | 77/8 | DA+0 | DFR |  | 2025-11-02 | 23.27 | Foundation completed. |  |  |  | 2025-11-13 | MARC |  | 10
17 | 60/3 | DA+6 | DRY |  | 2025-10-23 | 25.04 | Foundation completed. |  |  |  | 2025-11-15 | SHRIARSHINI |  | 15
18 | 77/3 | DA+0 | DFR |  | 2025-11-07 | 23.27 | Foundation completed. |  |  |  | 2025-11-19 | MARC |  | 10
19 | 60/8 | DA+3 | DFR |  | 2025-11-12 | 26.43 | Foundation completed. |  |  |  | 2025-11-23 | SHRIARSHINI |  | 10
20 | 77/1 | DA+0 | DRY |  | 2025-11-07 | 21.96 | Foundation completed. |  |  |  | 2025-11-25 | MARC |  | 10
21 | 59/1 | DA+0 | DFR |  | 2025-11-23 | 23.27 | Foundation completed. |  |  |  | 2025-11-29 | SHRIARSHINI |  | 10
22 | 77/2 | DA+0 | DRY |  | 2025-11-18 | 21.96 | Foundation completed. |  |  |  | 2025-11-30 | MARC |  | 10
23 | 58/2 | DA+0 | DRY |  | 2025-11-27 | 21.96 | Foundation completed. |  |  |  | 2025-12-03 | SHRIARSHINI |  | 16
24 | 58/1 | DA+6 | DRY |  | 2025-12-01 | 25.04 | Foundation completed. |  |  |  | 2025-12-08 | SHRIARSHINI |  | 16
25 | 77/6 | DA+0 | WC |  | 2025-11-27 | 22.4 | Foundation completed. |  |  |  | 2025-12-12 | MARC |  | 15
26 | 58/3 | DA+0 | DRY |  | 2025-12-09 | 21.96 | Foundation completed. |  |  |  | 2025-12-14 | SHRIARSHINI |  | 21
27 | 99/7 | DA+0 | DRY |  | 2025-12-07 | 21.96 | Foundation Completed. |  |  |  | 2025-12-15 | SAI SREE VARSHINI |  | 17
28 | 73/1 | DA+6 | WC |  | 2025-12-04 | 25.77 | Foundation completed. |  |  |  | 2025-12-18 | BALAJI INFRA |  | 10
29 | 56/3 | DA+0 | DFR |  | 2025-12-14 | 23.27 | Foundation Completed. |  |  |  | 2025-12-19 | SHRIARSHINI |  | 21
30 | 99/6 | DA+0 | DFR |  | 2025-12-07 | 23.27 | Foundation Completed. |  |  |  | 2025-12-20 | SAI SREE VARSHINI |  | 17
31 | 99/9 | DA+0 | DRY |  | 2025-12-14 | 21.96 | Foundation Completed. |  |  |  | 2025-12-23 | SAI SREE VARSHINI |  | 17
32 | 73/2 | DA+0 | WC |  | 2025-12-04 | 22.4 | Foundation completed. |  |  |  | 2025-12-24 | BALAJI INFRA |  | 10
33 | 56/1 | DA+3 | DFR |  | 2025-12-21 | 26.43 | Foundation Completed. |  |  |  | 2025-12-24 | SHRIARSHINI |  | 21
34 | 79/1 | DA+3 | WET |  | 2025-12-06 | 38.98 | Foundation Completed. |  |  |  | 2025-12-25 | MARC |  | 18
35 | 99/8 | DA+0 | DFR |  | 2025-12-14 | 23.27 | Foundation Completed. |  |  |  | 2025-12-26 | SAI SREE VARSHINI |  | 17
36 | 56/2 | DA+3 | DRY |  | 2025-12-17 | 25.04 | Foundation Completed. |  |  |  | 2025-12-27 | SHRIARSHINI |  | 21
37 | 99/10 | DA+0 | DFR |  | 2025-12-22 | 23.27 | Foundation Completed. |  |  |  | 2025-12-29 | SAI SREE VARSHINI |  | 17
38 | 79/3 | DA+9 | DFR |  | 2025-12-19 | 26.43 | Foundation Completed. |  |  |  | 2025-12-30 | MARC |  | 18
39 | 94/1 | DA+0 | DRY |  | 2025-12-10 | 21.96 | Foundation Completed. |  |  |  | 2025-12-31 | VKP TRADERS |  | 10
40 | 55/3 | DA+0 | DRY |  | 2025-12-25 | 21.96 | Foundation Completed. |  |  |  | 2025-12-31 | SHRIARSHINI |  | 21
41 | 99/11 | DA+0 | DFR |  | 2025-12-27 | 23.27 | Foundation Completed. |  |  |  | 2025-12-31 | SAI SREE VARSHINI |  | 17
42 | 84/6 | DA+0 | WC |  | 2026-12-21 | 22.4 | Foundation Completed. |  |  |  | 2025-12-31 | BALAJI INFRA |  | 10
43 | 79/2 | DA+6 | DFR |  | 2025-12-26 | 26.43 | Foundation Completed. |  |  |  | 2026-01-05 | MARC |  | 18
44 | 56/4 | DA+3 | WET |  | 2025-12-01 | 38.98 | Foundation Completed. |  |  |  | 2026-01-06 | SHRIARSHINI |  | 21
45 | 99/12 | DA+0 | DRY |  | 2025-12-31 | 21.96 | Foundation Completed. |  |  |  | 2026-01-06 | SAI SREE VARSHINI |  | 17
46 | 84/5 | DA+9 | DRY |  | 2026-01-02 | 25.04 | Foundation Completed. |  |  |  | 2026-01-08 | BALAJI INFRA |  | 10
47 | 56/9 | DA+6 | DRY |  | 2026-01-04 | 25.04 | Foundation Completed. |  |  |  | 2026-01-10 | SHRIARSHINI |  | 21
48 | 100/2 | DA+3 | DFR |  | 2026-01-05 | 26.43 | Foundation Completed. |  |  |  | 2026-01-12 | SAI SREE VARSHINI |  | 17
49 | 84/1 | DA+6 | DRY |  | 2026-01-04 | 25.04 | Foundation Completed. |  |  |  | 2026-01-12 | BALAJI INFRA |  | 12
50 | 100/3 | DA+0 | DFR |  | 2026-01-10 | 23.27 | Foundation Completed. |  |  |  | 2026-01-14 | SAI SREE VARSHINI |  | 17
51 | 83/0 | DB2+6 | DFR |  | 2026-01-06 | 55.74 | Foundation Completed. |  |  |  | 2026-01-14 | MARC |  | 20
52 | 56/7 | DB1+0 | DRY |  | 2026-01-07 | 45.33 | Foundation Completed. |  |  |  | 2026-01-16 | SHRIARSHINI |  | 21
53 | 56/6 | DA+0 | DRY |  | 2026-01-09 | 21.96 | Foundation Completed. |  |  |  | 2026-01-17 | SHRIARSHINI |  | 21
54 | 56/8 | DA+0 | WC |  | 2026-01-17 | 22.4 | Foundation Completed. |  |  |  | 2026-01-21 | SHRIARSHINI |  | 15
55 | 85/2 | DA+0 | WET/WFR |  | 2026-01-06 | 33.655 | Foundation Completed. |  |  |  | 2026-01-22 | BALAJI INFRA |  | 12
56 | 101/2 | DA+0 | DFR |  | 2026-01-18 | 23.27 | Foundation Completed. |  |  |  | 2026-01-22 | VKP TRADERS |  | 11
57 | 100/1 | DA+3 | WFR |  | 2026-01-04 | 36.66 | Foundation Completed. |  |  |  | 2026-01-23 | SAI SREE VARSHINI |  | 17
58 | 100/4 | DA+0 | DFR |  | 2026-01-21 | 23.27 | Foundation Completed. |  |  |  | 2026-01-24 | SAI SREE VARSHINI |  | 12
59 | 84/0 | DB1+0 | DFR |  | 2026-01-22 | 55.74 | Foundation Completed. |  |  |  | 2026-01-26 | MARC |  | 20
60 | 59/0 | DC1+0 | DFR |  | 2026-01-07 | 61.57 | Foundation Completed. |  |  |  | 2026-01-26 | SHRIARSHINI - 2 |  | 21
61 | 102/4 | DA+0 | DFR |  | 2026-01-22 | 23.27 | Foundation Completed. |  |  |  | 2026-01-26 | BALAJI INFRA-2 |  | 11
62 | 100/5 | DA+0 | DFR |  | 2026-01-22 | 23.27 | Foundation Completed. |  |  |  | 2026-01-27 | SAI SREE VARSHINI |  | 20
63 | 101/1 | DA+0 | DRY |  | 2026-01-24 | 21.96 | Foundation Completed. |  |  |  | 2026-01-28 | VKP TRADERS |  | 11
64 | 55/1 | DA+0 | DRY |  | 2026-01-25 | 21.96 | Foundation Completed. |  |  |  | 2026-01-28 | SHRIARSHINI |  | 15
65 | 53/2 | DA+0 | DRY |  | 2026-01-26 | 21.96 | Foundation Completed. |  |  |  | 2026-01-30 | SHRIARSHINI |  | 20
66 | 102/5 | DA+0 | WFR |  | 2026-01-11 | 33.01 | Foundation Completed. |  |  |  | 2026-01-31 | BALAJI INFRA-2 |  | 11
67 | 52/0 | DB2+0 | DFR |  | 2026-01-23 | 55.59 | Foundation Completed. |  |  |  | 2026-01-31 | SHRIARSHINI |  | 15
68 | 101/3 | DA+0 | DRY |  | 2026-01-26 | 21.96 | Foundation Completed. |  |  |  | 2026-01-31 | VKP TRADERS |  | 11
69 | 101/0 | DB1+0 | DRY |  | 2026-01-27 | 45.33 | Foundation Completed. |  |  |  | 2026-01-31 | SAI SREE VARSHINI |  | 20
70 | 51/9 | DA+3 | DFR |  | 2026-02-01 | 26.43 | Foundation Completed. |  |  |  | 2026-02-05 | SHRIARSHINI |  | 20
71 | 78/3 | DA+0 | DRY |  | 2026-01-26 | 21.96 | Foundation Completed. |  |  |  | 2026-02-06 | MARC |  | 20
72 | 53/1 | 3DA+3 | DFR |  | 2026-01-28 | 26.43 | Foundation Completed. |  |  |  | 2026-02-08 | SHRIARSHINI |  | 20
73 | 102/3 | DA+0 | DFR |  | 2026-01-26 | 23.27 | Foundation Completed. |  |  |  | 2026-02-08 | BALAJI INFRA-2 |  | 11
74 | 77/9 | DA+0 | DFR |  | 2026-02-02 | 23.27 | Foundation Completed. |  |  |  | 2026-02-10 | MARC |  | 20
75 | 102/2 | DA+0 | DFR |  | 2026-02-02 | 23.27 | Foundation Completed. |  |  |  | 2026-02-11 | BALAJI INFRA |  | 14
76 | 50/1 | DA+0 | DFR |  | 2026-02-07 | 23.27 | Foundation Completed. |  |  |  | 2026-02-12 | SHRIARSHINI |  | 20
77 | 101/5 | DA+0 | DRY |  | 2026-02-02 | 21.96 | Foundation Completed. |  |  |  | 2026-02-14 | VKP TRADERS |  | 11
78 | 102/1 | DA+0 | DFR |  | 2026-02-02 | 23.27 | Foundation Completed. |  |  |  | 2026-02-14 | BALAJI INFRA |  | 14
79 | 83/1 | DA+0 | DFR |  | 2026-02-08 | 23.27 | Foundation Completed. |  |  |  | 2026-02-15 | MARC |  | 20
80 | 50/2 | DA+0 | WET |  | 2026-02-06 | 34.3 | Foundation Completed. |  |  |  | 2026-02-17 | SHRIARSHINI |  | 20
81 | 101/6 | DA+0 | DFR |  | 2026-02-09 | 23.27 | Foundation Completed. |  |  |  | 2026-02-22 | VKP TRADERS |  | 20
82 | 100/6 | DA+0 | DFR |  | 2026-01-26 | 23.27 | Foundation Completed. |  |  |  | 2026-02-24 | BALAJI INFRA |  | 20
83 | 85/1 | DA+9 | WET |  | 2026-01-27 | 38.98 | Foundation Completed. |  |  |  | 2026-02-25 | MARC |  | 18
84 | 100/8 | DA+0 | DFR |  | 2026-02-12 | 23.27 | Foundation Completed. |  |  |  | 2026-02-26 | BALAJI INFRA |  | 16
85 | 101/7 | DA+0 | DFR |  | 2026-02-16 | 23.27 | Foundation Completed. |  |  |  | 2026-02-28 | VKP TRADERS |  | 11
86 | 100/7 | DA+3 | DFR |  | 2026-01-27 | 26.43 | Foundation Completed. |  |  |  | 2026-02-28 | BALAJI INFRA |  | 16
87 | 89/1 | DA+0 | DFR |  | 2026-02-23 | 23.27 | Foundation Completed. |  |  |  | 2026-03-03 | MARC |  | 18
88 | 53/4 | DA+0 | WET |  | 2026-02-05 | 34.3 | Foundation Completed. |  |  |  | 2026-03-06 | SHRIARSHINI |  | 20
89 | 53/5 | DA+0 | DRY |  | 2026-02-02 | 21.96 | Foundation Completed. |  |  |  | 2026-03-08 | SHRIARSHINI |  | 20
90 | 49/10 | DA+0 | DFR |  | 2026-02-24 | 23.27 | Foundation Completed. |  |  |  | 2026-03-11 | VEER TEJA CONSTRUCTION |  | 10
91 | 51/7 | 3DA+3 | DFR |  | 2026-03-06 | 26.43 | Foundation Completed. |  |  |  | 2026-03-13 | SHRIARSHINI |  | 20
92 | 49/11 | DA+0 | WFR |  | 2026-02-24 | 33.01 | Foundation Completed. |  |  |  | 2026-03-14 | VEER TEJA CONSTRUCTION |  | 10
93 | 51/8 | DA+0 | DFR |  | 2026-03-07 | 23.27 | Foundation Completed. |  |  |  | 2026-03-14 | SHRIARSHINI |  | 20
94 | 51/10 | DA+0 | WET |  | 2026-03-09 | 34.3 | Foundation Completed. |  |  |  | 2026-03-17 | SHRIARSHINI |  | 20
95 | 90/0 | DB2+0 | DFR |  | 2026-03-06 | 55.59 | Foundation Completed. |  |  |  | 2026-03-18 | MARC |  | 18
96 | 100/0 | 3DB2+0 | DFR |  | 2026-03-24 | 55.59 | Foundation Completed. |  |  |  | 2026-03-18 | BALAJI INFRA |  | 16
97 | 51/6 | DA+3 | DFR |  | 2026-03-11 | 26.43 | Foundation Completed. |  |  |  | 2026-03-19 | SHRIARSHINI |  | 20
98 | 52/1 | DA+9 | DFR |  | 2026-03-17 | 26.43 | Foundation Completed. |  |  |  | 2026-03-22 | SHRIARSHINI |  | 20
99 | 50/3 | DA+3 | DFR |  | 2026-03-20 | 26.43 | Foundation Completed. |  |  |  | 2026-03-25 | SHRIARSHINI |  | 20
100 | 51/2 | DA+0 | DFR |  | 2026-03-21 | 23.27 | Foundation Completed. |  |  |  | 2026-03-27 | SHRIARSHINI |  | 20
101 | 53/3 | DA+3 | WET |  | 2026-03-25 | 38.98 | Foundation Completed. |  |  |  | 2026-03-31 | SHRIARSHINI |  | 20
102 | 60/0 | DB2+0 | DFR |  | 2026-03-16 | 55.59 | Foundation Completed. |  |  |  | 2026-04-06 | SHRIARSHINI - 2 |  | 20
103 | 70/1 | DA+9 | DFR |  | 2026-03-25 | 26.43 | Foundation Completed. |  |  |  | 2026-04-11 | ATK |  | 30
104 | 70/2 | DA+0 | DFR |  | 2026-03-26 | 23.27 | Foundation Completed. |  |  |  | 2026-04-13 | ATK |  | 30
105 | 53/0 | DB1+3 | DFR/WFR |  | 2026-03-30 | 52.21 | Foundation Completed. |  |  |  | 2026-04-13 | SHRIHARSHINI |  | 20
106 | 50/0 | DC2+0 | WFR |  | 2026-02-24 | 99.96 | Foundation Completed. |  |  |  | 2026-04-16 | VEER TEJA CONSTRUCTION |  | 10
107 | 70/4 | DA+6 | DFR |  | 2026-03-26 | 26.43 | Foundation Completed. |  |  |  | 2026-04-16 | ATK |  | 30
108 | 70/3 | DA+0 | DFR |  | 2026-04-09 | 23.27 | Foundation Completed. |  |  |  | 2026-04-18 | ATK |  | 30
109 | 66/1 | DB1+9 | DFR |  | 2026-04-17 | 46.6 | Foundation Completed. |  |  |  | 2026-04-21 | ATK |  | 30
110 | 49/9 | DA+0 | DFR |  | 2026-04-15 | 23.27 | Foundation Completed. |  |  |  | 2026-04-23 | VEER TEJA CONSTRUCTION |  | 10
111 | 67/0 | 3DD45+3 | DFR |  | 2026-04-21 | 90.34 | Foundation Completed. |  |  |  | 2026-04-26 | ATK |  | 30
112 | 65/3 | DA+0 | DFR |  | 2026-04-27 | 23.27 | Foundation Completed. |  |  |  | 2026-04-29 | ATK |  | 16
113 | 49/8 | DA+0 | DFR | 2026-04-16 | 2026-04-24 | 23.27 | Foundation Completed. |  |  |  | 2026-04-30 | VEER TEJA CONSTRUCTION |  | 10
114 | 66/0 | 3DB2+0 | DFR |  | 2026-04-30 | 55.59 | Foundation Completed. |  |  |  | 2025-05-03 | ATK |  | 17
115 | 67/1 | DA+6 | WC |  | 2026-04-29 | 25.77 | Foundation Completed. |  |  |  | 2026-05-05 | ATK |  | 17
116 | 84/2 | DA+0 |  |  |  |  | WIP: Excavation Hard Rock Encounted |  |  |  |  | BALAJI INFRA
117 | 60/1 | DA+0 |  |  |  |  | Trial Pit Excavated, Hard Rock encounted |  |  |  |  | SHRIARSHINI-2 |  | 15
118 | 101/4 | DA+0 |  |  | 2026-01-30 |  | WIP: Excavated | [6 empty] | 11
119 | 85/0 | DB1+0 |  |  | 2026-02-14 |  | WIP: Pit Marking | [6 empty] | 18
120 | 90/1 | DA+3 |  |  | 2026-02-24 |  | WIP: Pit Marking | [6 empty] | 18
121 | 102/0 | 3DB2+0 |  |  | 2026-03-09 |  | WIP: Pit Marking | [6 empty] | 10
122 | 90/3 | DA+3 | DFR |  | 2026-03-02 | 26.43 | WIP: Blasting | [6 empty] | 18
123 | 90/2 | DA+0 |  |  | 2026-02-26 |  | WIP: Blasting | [6 empty] | 18
124 | 99/5 | DA+0 |  |  | 2026-03-13 |  | WIP: Excavation | [6 empty] | 16
125 | 49/7 | DA+0 |  |  | 2026-03-31 |  | WIP: Pit Marking
126 | 56/10 | DA+0 |  |  | 2026-04-10 |  | WIP: Trial Pit
127 | 56/5 | DA+3 |  |  | 2026-04-09 |  | WIP: Excavation
128 | 49/1 | DA+0 |  |  |  |  | WIP: Trial Pit
129 | 48/1 | DA+6 |  |  | 2026-04-13 |  | WIP: Blasting |  |  |  |  | BALAJI Services
130 | 48/3 | DA+6 |  |  | 2026-04-15 |  | WIP: Excavated |  |  |  |  | BALAJI Services
131 | 48/7 | DA+0 |  |  | 2026-04-20 |  | WIP: RCC (F&B) |  |  |  |  | BALAJI Services |  | 10
132 | 48/2 | DA+0 |  |  | 2026-04-16 |  | WIP: Block Level |  |  |  |  | BALAJI Services
133 | 48/4 | DA+3 |  |  | 2026-04-16 |  | WIP: Blasting |  |  |  |  | BALAJI Services
134 | 69/0 | DB2+6 | WET |  | 2026-05-06 |  | WIP: RCC (F&B) |  |  |  |  | ATK
<Alt+i+r>
EARTHING
SL No. | Location No. | Tower Type | Classification | ROW cleared date | Start Date | Status |  |  |  | End Date | Gang Name | Remark | Revenue
1 | 82/1 | DA+0 | WC | 2025-07-10 | 2025-09-08 | Earthing Completed. |  |  |  | 2025-09-08 | MARC
2 | 80/5 | DA+0 | DRY | 2025-08-29 | 2025-09-24 | Earthing Completed. |  |  |  | 2025-09-24 | MARC
3 | 59/4 | DA+6 | DRY | 2025-10-03 | 2025-10-19 | Earthing Completed. |  |  |  | 2025-10-19 | SHRIARSHINI - 1
4 | 77/1 | DA+0 | DRY |  | 2025-12-01 | Earthing Completed. |  |  |  | 2025-12-01 | MARC
5 | 77/2 | DA+0 | DRY |  | 2025-12-19 | Earthing Completed. |  |  |  | 2025-12-19 | MARC
6 | 77/6 | DA+0 | WC |  | 2025-12-20 | Earthing Completed. |  |  |  | 2025-12-20 | MARC
7 | 56/3 | DA+0 | DFR |  | 2025-12-25 | Earthing Completed. |  |  |  | 2025-12-25 | SHRIARSHINI - 1
8 | 79/1 | DA+3 | WET |  | 2025-12-29 | Earthing Completed. |  |  |  | 2025-12-29 | MARC
9 | 80/1 | DA+6 | WFR |  | 2025-12-30 | Earthing Completed. |  |  |  | 2025-12-30 | MARC
10 | 99/9 | DA+0 | DRY |  | 2026-01-01 | Earthing Completed. |  |  |  | 2026-01-01 | SAI SREE VARSHINI
11 | 99/8 | DA+0 | DFR |  | 2026-01-06 | Earthing Completed. |  |  |  | 2026-01-06 | SAI SREE VARSHINI
12 | 99/10 | DA+0 | DFR |  | 2026-01-06 | Earthing Completed. |  |  |  | 2026-01-06 | SAI SREE VARSHINI
13 | 99/11 | DA+0 | DFR |  | 2026-01-06 | Earthing Completed. |  |  |  | 2026-01-06 | SAI SREE VARSHINI
14 | 99/6 | DA+0 | DFR |  | 2026-01-07 | Earthing Completed. |  |  |  | 2026-01-07 | SAI SREE VARSHINI
15 | 99/7 | DA+0 | DRY |  | 2026-01-07 | Earthing Completed. |  |  |  | 2026-01-07 | SAI SREE VARSHINI
16 | 73/1 | DA+6 | WET |  | 2026-01-11 | Earthing Completed. |  |  |  | 2026-01-11 | BALAJI INFRA -1
17 | 73/2 | DA+0 | WC |  | 2026-01-11 | Earthing Completed. |  |  |  | 2026-01-11 | BALAJI INFRA -1
18 | 56/2 | DA+3 | DRY |  | 2026-01-15 | Earthing Completed. |  |  |  | 2026-01-15 | SHRIARSHINI - 1
19 | 56/4 | DA+3 | WET |  | 2026-01-15 | Earthing Completed. |  |  |  | 2026-01-15 | SHRIARSHINI - 1
20 | 58/2 | DA+0 | DRY |  | 2026-01-16 | Earthing Completed. |  |  |  | 2026-01-16 | SHRIARSHINI - 1
21 | 58/3 | DA+0 | DRY |  | 2026-01-16 | Earthing Completed. |  |  |  | 2026-01-16 | SHRIARSHINI - 1
22 | 56/7 | DB1+0 | DRY |  | 2026-01-18 | Earthing Completed. |  |  |  | 2026-01-18 | SHRIARSHINI - 1
23 | 56/6 | DA+0 | DRY |  | 2026-01-21 | Earthing Completed. |  |  |  | 2026-01-21 | SHRIARSHINI - 1
24 | 59/1 | DA+0 | DFR |  | 2026-01-22 | Earthing Completed. |  |  |  | 2026-01-22 | SHRIARSHINI - 1
25 | 58/1 | DA+6 | DRY |  | 2026-01-22 | Earthing Completed. |  |  |  | 2026-01-22 | SHRIARSHINI - 1
26 | 60/2 | DA+0 | DFR |  | 2026-01-23 | Earthing Completed. |  |  |  | 2026-01-23 | SHRIARSHINI - 1
27 | 60/8 | DA+3 | DFR |  | 2026-01-24 | Earthing Completed. |  |  |  | 2026-01-24 | SHRIARSHINI - 1
28 | 100/3 | DA+3 | DRY |  | 2026-01-23 | Earthing Completed. |  |  |  | 2026-01-25 | SAI SREE VARSHINI
29 | 59/0 | DC1+0 | DFR |  | 2026-01-28 | Earthing Completed. |  |  |  | 2026-01-28 | SHRIARSHINI - 1
30 | 101/0 | DB1+0 | DRY |  | 2026-02-01 | Earthing Completed. |  |  |  | 2026-02-01 | SAI SREE VARSHINI
31 | 100/5 | DA+0 | DFR |  | 2026-02-02 | Earthing Completed. |  |  |  | 2026-02-02 | SAI SREE VARSHINI
32 | 52/0 | DB2+0 | DFR |  | 2026-02-03 | Earthing Completed. |  |  |  | 2026-02-03 | SHRIARSHINI - 1
33 | 77/9 | DA+0 | DFR |  | 2026-02-13 | Earthing Completed. |  |  |  | 2026-02-13 | MARC
34 | 102/4 | DA+0 | DFR |  | 2026-02-14 | Earthing Completed. |  |  |  | 2026-02-14 | BALAJI INFRA -1
35 | 78/3 | DA+0 | DRY |  | 2026-02-14 | Earthing Completed. |  |  |  | 2026-02-14 | MARC
36 | 50/1 | DA+0 | DFR |  | 2026-02-15 | Earthing Completed. |  |  |  | 2026-02-15 | SHRIARSHINI - 1
37 | 51/9 | DA+3 | DFR |  | 2026-02-16 | Earthing Completed. |  |  |  | 2026-02-16 | SHRIARSHINI - 1
38 | 53/1 | 3DA+3 | DFR |  | 2026-02-17 | Earthing Completed. |  |  |  | 2026-02-17 | SHRIARSHINI - 1
39 | 102/1 | DA+0 | DFR |  | 2026-02-18 | Earthing Completed. |  |  |  | 2026-02-17 | BALAJI INFRA
40 | 50/2 | DA+0 | WET |  | 2026-02-18 | Earthing Completed. |  |  |  | 2026-02-17 | SHRIARSHINI - 1
41 | 56/8 | DA+0 | WC |  | 2026-02-19 | Earthing Completed. |  |  |  | 2026-02-19 | SHRIARSHINI - 1
42 | 56/9 | DA+6 | DRY |  | 2026-02-19 | Earthing Completed. |  |  |  | 2026-02-19 | SHRIARSHINI - 1
43 | 53/2 | DA+0 | DRY |  | 2026-02-19 | Earthing Completed. |  |  |  | 2026-02-19 | SHRIARSHINI - 1
44 | 55/1 | DA+0 | DRY |  | 2026-02-19 | Earthing Completed. |  |  |  | 2026-02-19 | SHRIARSHINI - 1
45 | 55/3 | DA+0 | DRY |  | 2026-02-22 | Earthing Completed. |  |  |  | 2026-02-22 | SHRIARSHINI - 1
46 | 60/3 | DA+6 | DRY |  | 2026-02-22 | Earthing Completed. |  |  |  | 2026-02-22 | SHRIARSHINI - 1
47 | 59/5 | DA+0 | DRY |  | 2026-02-22 | Earthing Completed. |  |  |  | 2026-02-22 | SHRIARSHINI - 1
48 | 59/2 | DA+0 | DRY |  | 2026-02-22 | Earthing Completed. |  |  |  | 2026-02-22 | SHRIARSHINI - 1
49 | 83/1 | DA+0 | DFR |  | 2026-02-24 | Earthing Completed. |  |  |  | 2026-02-24 | MARC
50 | 101/1 | DA+0 | DRY |  | 2026-03-02 | Earthing Completed. |  |  |  | 2026-03-02 | VKP TRADERS
51 | 101/2 | DA+0 | DFR |  | 2026-03-02 | Earthing Completed. |  |  |  | 2026-03-02 | VKP TRADERS
52 | 101/3 | DA+0 | DRY |  | 2026-03-02 | Earthing Completed. |  |  |  | 2026-03-02 | VKP TRADERS
53 | 101/5 | DA+0 | DRY |  | 2026-03-02 | Earthing Completed. |  |  |  | 2026-03-02 | VKP TRADERS
54 | 101/6 | DA+0 | DFR |  | 2026-03-03 | Earthing Completed. |  |  |  | 2026-03-03 | VKP TRADERS
55 | 101/7 | DA+0 | DFR |  | 2026-03-03 | Earthing Completed. |  |  |  | 2026-03-03 | VKP TRADERS
56 | 100/8 | DA+0 | DFR |  | 2026-03-03 | Earthing Completed. |  |  |  | 2026-03-03 | BALAJI INFRA -1
57 | 100/6 | DA+0 | DFR |  | 2026-03-07 | Earthing Completed. |  |  |  | 2026-03-07 | BALAJI INFRA -1
58 | 100/7 | DA+3 | DFR |  | 2026-03-07 | Earthing Completed. |  |  |  | 2026-03-07 | BALAJI INFRA -1
59 | 85/1 | DA+9 | WET |  | 2026-03-08 | Earthing Completed. |  |  |  | 2026-03-08 | MARC
60 | 89/1 | DA+0 | DFR |  | 2026-03-13 | Earthing Completed. |  |  |  | 2026-03-13 | MARC
61 | 51/7 | 3DA+3 | DFR |  | 2026-03-13 | Earthing Completed. |  |  |  | 2026-03-14 | SHRIHARSHINI
62 | 51/8 | DA+0 | DFR | DFR | 2026-03-17 | Earthing Completed. |  |  |  | 2026-03-17 | SHRIHARSHINI
63 | 100/0 | 3DB2+0 | DFR |  | 2026-03-20 | Earthing Completed. |  |  |  | 2026-03-23 | BALAJI INFRA
64 | 52/1 | DA+9 | DFR | 2026-03-17 | 2026-03-31 | Earthing Completed. |  |  |  | 2026-03-31 | SHRIARSHINI
65 | 51/6 | DA+3 | DFR |  | 2026-03-29 | Earthing Completed. |  |  |  | 2026-03-29 | SHRIARSHINI
66 | 50/3 | DA+3 | DFR |  | 2026-03-29 | Earthing Completed. |  |  |  | 2026-03-29 | SHRIARSHINI
67 | 51/2 | DA+0 | DFR | DFR | 2026-03-31 | Earthing Completed. |  |  |  | 2026-03-31 | SHRIARSHINI
68 | 53/3 | DA+3 | WET | WET | 2026-04-13 | Earthing Completed. |  |  |  | 2026-04-13 | SHRIARSHINI
69 | 53/4 | DA+0 | WET | WET | 2026-04-13 | Earthing Completed. |  |  |  | 2026-04-13 | SHRIARSHINI
70 | 53/5 | DA+0 | DRY | DRY | 2026-04-13 | Earthing Completed. |  |  |  | 2026-04-13 | SHRIARSHINI
71 | 53/0 | DB1+3 | DFR/WFR |  | 2026-04-13 | Earthing Completed. |  |  |  | 2026-04-13 | SHRIARSHINI
72 | 70/1 | DA+9 | DFR |  | 2026-04-13 | Earthing Completed. |  |  |  | 2026-04-13 | ATK
73 | 60/0 | DB2+0 | DFR |  | 2026-04-14 | Earthing Completed. |  |  |  | 2026-04-15 | SHRIARSHINI
74 | 70/2 | DA+0 | DFR | DFR | 2026-04-15 | Earthing Completed. |  |  |  | 2026-04-15 | ATK
75 | 51/10 | DA+0 | WET |  | 2026-04-15 | Earthing Completed. |  |  |  | 2026-04-15 | SHRIARSHINI
76 | 79/2 | DA+6 | DFR |  | 2026-04-17 | Earthing Completed. |  |  |  | 2026-04-17 | BALAJI ELECTRICAL
77 | 79/3 | DA+9 | DFR |  | 2026-04-17 | Earthing Completed. |  |  |  | 2026-04-17 | BALAJI ELECTRICAL
78 | 84/0 | DB1+0 | DFR | DFR | 2026-04-18 | Earthing Completed. |  |  |  | 2026-04-18 | BALAJI ELECTRICAL
79 | 70/4 | DA+6 | DFR | DFR | 2026-04-19 | Earthing Completed. |  |  |  | 2026-04-19 | ATK
80 | 83/0 | DB2+6 | DFR |  | 2026-04-19 | Earthing Completed. |  |  |  | 2026-04-19 | BALAJI ELECTRICAL
81 | 84/1 | DA+6 | DRY |  | 2026-04-19 | Earthing Completed. |  |  |  | 2026-04-19 | BALAJI ELECTRICAL
82 | 70/3 | DA+0 | DFR |  | 2026-04-19 | Earthing Completed. |  |  |  | 2026-04-19 | ATK
83 | 84/4 | DA+0 | DRY |  | 2026-04-22 | Earthing Completed. |  |  |  | 2026-04-22 | BALAJI ELECTRICAL
84 | 50/0 | 3DC2+0 | WFR |  | 2026-04-22 | Earthing Completed. |  |  |  | 2026-04-02 | ATK
85 | 49/10 | DA+0 | DFR |  | 2026-04-24 | Earthing Completed. |  |  |  | 2026-04-24 | VEER TEJA CONSTRUCTION
86 | 49/11 | DA+0 | WFR |  | 2026-04-24 | Earthing Completed. |  |  |  | 2026-04-24 | VEER TEJA CONSTRUCTION
87 | 66/1 | DB1+9 | DFR |  | 2026-04-24 | Earthing Completed. |  |  |  | 2026-04-25 | ATK
88 | 67/0 | 3DD45+3 | DFR |  | 2026-04-28 | Earthing Completed. |  |  |  | 2026-04-28 | ATK
89 | 49/8 | DA+0 | DFR |  | 2026-04-30 | Earthing Completed. |  |  |  | 2026-04-30 | VEER TEJA CONSTRUCTION
90 | 65/3 | DA+0 | DFR |  | 2026-05-01 | Earthing Completed. |  |  |  | 2026-05-01 | ATK
91 | 66/0 | 3DB2+0 | DFR |  | 2026-05-04 | Earthing Completed. |  |  |  | 2026-05-05 | ATK
Stringing
S.No | Section | Length | Status |  |  |  |  | Gang Name | Gang Strength | RouGH SaG | F!n@L sAG | E@rthwire
OPGW Stringing | [5 empty] | *-
S.No | Section | Length | Status |  |  |  |  | Gang Name | Gang Strength | Remarks
Erection
SL No. | Location No. | Tower Type | Classification |  | Start Date | MT | Status |  |  |  | End Date | Gang Name | Gang Strength | Remark
1 | 59/1 | DA+0 | DFR |  | 2025-12-15 | 35.089 | Erection Completed. |  |  |  | 2025-12-20 | NASIRUDDIN | 35
2 | 59/2 | DA+0 | DRY |  | 2025-12-22 | 35.089 | Erection Completed. |  |  |  | 2025-12-27 | NASIRUDDIN | 35
3 | 77/3 | DA+0 | DFR |  | 2025-12-22 | 35.089 | Erection Completed. |  |  |  | 2025-12-31 | CRANE | 49
4 | 58/2 | DA+0 | DRY |  | 2025-12-25 | 35.089 | Erection Completed. |  |  |  | 2026-01-10 | NASIRUDDIN | 35
5 | 77/2 | DA+0 | DRY |  | 2025-12-25 | 35.089 | Erection Completed. |  |  |  | 2026-01-08 | CRANE | 49
6 | 58/1 | DA+6 | DRY |  | 2026-01-02 | 41.88 | Erection Completed. |  |  |  | 2026-01-10 | NASIRUDDIN | 35
7 | 77/1 | DA+0 | DRY |  | 2026-01-01 | 35.089 | Erection Completed. |  |  |  | 2026-01-13 | CRANE | 49
8 | 58/3 | DA+0 | DRY |  | 2026-01-09 | 35.089 | Erection Completed. |  |  |  | 2026-01-14 | NASIRUDDIN | 35
9 | 77/4 | DA+0 | DRY |  | 2026-01-07 | 35.089 | Erection Completed. |  |  |  | 2026-01-16 | DK VERMA | 21
10 | 82/1 | DA+0 | WC |  | 2026-01-11 | 35.089 | Erection Completed. |  |  |  | 2026-01-16 | SHAKILA KHATUN | 31
11 | 80/5 | DA+0 | DFR |  | 2026-01-15 | 35.089 | Erection Completed. |  |  |  | 2026-01-20 | SHAKILA KHATUN | 31
12 | 59/4 | DA+6 | DRY |  | 2026-01-15 | 41.88 | Erection Completed. |  |  |  | 2026-01-21 | NASIRUDDIN | 35
13 | 77/7 | DA+0 | DFR |  | 2026-01-17 | 35.089 | Erection Completed. |  |  |  | 2026-01-21 | DK VERMA | 21
14 | 84/3 | DA+0 | DRY |  | 2026-01-16 | 35.089 | Erection Completed. |  |  |  | 2026-01-21 | SUBHASH | 32
15 | 99/11 | DA+0 | DFR |  | 2026-01-17 | 35.089 | Erection Completed. |  |  |  | 2026-01-21 | GOURI SHANKAR | 45
16 | 84/4 | DA+0 | DRY |  | 2026-01-19 | 35.089 | Erection Completed. |  |  |  | 2026-01-24 | SUBHASH | 32
17 | 80/1 | DA+6 | WFR |  | 2026-01-19 | 41.88 | Erection Completed. |  |  |  | 2026-01-25 | SHAKILA KHATUN | 31
18 | 59/5 | DA+0 | DRY |  | 2026-01-22 | 35.089 | Erection Completed. |  |  |  | 2026-01-27 | NASIRUDDIN | 35
19 | 99/10 | DA+0 | DFR |  | 2026-01-23 | 35.089 | Erection Completed. |  |  |  | 2026-01-27 | GOURI SHANKAR | 45
20 | 84/1 | DA+6 | DRY |  | 2026-01-25 | 41.88 | Erection Completed. |  |  |  | 2026-01-28 | SUBHASH | 32
21 | 99/7 | DA+0 | DRY |  | 2026-01-12 | 35.089 | Erection Completed. |  |  |  | 2026-01-29 | CRANE | 49
22 | 77/10 | DA+3 | DRY |  | 2026-01-26 | 36.771 | Erection Completed. |  |  |  | 2026-01-30 | DK VERMA | 21
23 | 79/2 | DA+6 | DFR |  | 2026-01-27 | 41.88 | Erection Completed. |  |  |  | 2026-01-31 | SHAKILA KHATUN | 31
24 | 100/2 | DA+3 | DFR |  | 2026-01-27 | 36.771 | Erection Completed. |  |  |  | 2026-01-31 | GOURI SHANKAR | 45
25 | 60/2 | DA+0 | DFR |  | 2026-01-27 | 35.089 | Erection Completed. |  |  |  | 2026-02-02 | NASIRUDDIN | 35
26 | 99/8 | DA+0 | DFR |  | 2026-01-30 | 35.089 | Erection Completed. |  |  |  | 2026-02-03 | CRANE | 49
27 | 85/2 | DA+0 | WET/WFR |  | 2026-01-31 | 35.089 | Erection Completed. |  |  |  | 2026-02-03 | SUBHASH | 32
28 | 79/3 | DA+9 | DFR |  | 2026-02-01 | 43.575 | Erection Completed. |  |  |  | 2026-02-04 | SHAKILA KHATUN | 31
29 | 84/5 | DA+9 | DRY |  | 2026-01-28 | 43.575 | Erection Completed. |  |  |  | 2026-02-05 | SUBHASH | 32
30 | 100/1 | DA+3 | WFR |  | 2026-01-30 | 36.771 | Erection Completed. |  |  |  | 2026-02-05 | GOURI SHANKAR | 45
31 | 56/8 | DA+0 | WC |  | 2026-02-06 | 35.089 | Erection Completed. |  |  |  | 2026-02-09 | SHAKILA KHATUN | 35
32 | 99/6 | DA+0 | DFR |  | 2026-12-05 | 35.089 | Erection Completed. |  |  |  | 2026-02-09 | CRANE | 49
33 | 84/0 | DB1+0 | DFR |  | 2026-02-05 | 54.72 | Erection Completed. |  |  |  | 2026-02-10 | SUBHASH | 32
34 | 56/6 | DA+0 | DRY |  | 2026-02-03 | 35.089 | Erection Completed. |  |  |  | 2026-02-11 | NASIRUDDIN | 35
35 | 101/2 | DA+0 | DFR |  | 2026-02-05 | 35.089 | Erection Completed. |  |  |  | 2026-02-12 | GOURI SHANKAR | 45
36 | 56/9 | DA+6 | DRY |  | 2026-02-10 | 41.88 | Erection Completed. |  |  |  | 2026-02-13 | SHAKILA KHATUN | 31
37 | 81/1 | DA+0 | DFR |  | 2026-02-10 | 35.089 | Erection Completed. |  |  |  | 2026-02-13 | SUBHASH | 32
38 | 99/9 | DA+0 | DRY |  | 2026-01-31 | 35.089 | Erection Completed. |  |  |  | 2026-02-16 | CRANE | 49
39 | 101/3 | DA+0 | DRY |  | 2026-02-12 | 35.089 | Erection Completed. |  |  |  | 2026-02-16 | GOURI SHANKAR | 45
40 | 102/4 | DA+0 | DFR |  | 2026-02-14 | 35.089 | Erection Completed. |  |  |  | 2026-02-17 | SUBHASH | 32
41 | 55/1 | DA+0 | DRY |  | 2026-02-14 | 35.089 | Erection Completed. |  |  |  | 2026-02-17 | SHAKILA KHATUN | 35
42 | 102/5 | DA+0 | WFR |  | 2026-02-15 | 35.089 | Erection Completed. |  |  |  | 2026-02-19 | SUBHASH | 32
43 | 56/7 | DB1+0 | DRY |  | 2026-02-12 | 54.72 | Erection Completed. |  |  |  | 2026-02-20 | NASIRUDDIN | 35
44 | 101/1 | DA+0 | DRY |  | 2026-02-16 | 35.089 | Erection Completed. |  |  |  | 2026-02-20 | GOURI SHANKAR | 45
45 | 52/0 | DB2+0 | DFR |  | 2026-02-17 | 54.72 | Erection Completed. |  |  |  | 2026-02-21 | SHAKILA KHATUN | 35
46 | 102/2 | DA+0 | DFR |  | 2026-02-20 | 35.089 | Erection Completed. |  |  |  | 2026-02-22 | SUBHASH | 32
47 | 100/5 | DA+0 | DFR |  | 2026-02-08 | 35.089 | Erection Completed. |  |  |  | 2026-02-24 | GOURI SHANKAR | 45
48 | 102/3 | DA+0 | DFR |  | 2026-02-22 | 35.089 | Erection Completed. |  |  |  | 2026-02-24 | SUBHASH | 32
49 | 53/1 | DA+3 | DFR |  | 2026-02-22 | 36.771 | Erection Completed. |  |  |  | 2026-02-25 | SHAKILA KHATUN | 40
50 | 56/2 | DA+3 | DRY |  | 2026-02-20 | 36.771 | Erection Completed. |  |  |  | 2026-02-26 | NASIRUDDIN | 30
51 | 102/1 | DA+0 | DFR |  | 2026-02-24 | 35.089 | Erection Completed. |  |  |  | 2026-02-27 | SUBHASH | 32
52 | 77/9 | DA+0 | DFR |  | 2026-02-24 | 35.089 | Erection Completed. |  |  |  | 2026-02-28 | TNR INFA | 24
53 | 53/2 | DA+0 | DRY |  | 2026-02-25 | 35.089 | Erection Completed. |  |  |  | 2026-02-28 | SHAKILA KHATUN | 40
54 | 101/5 | DA+0 | DRY |  | 2026-02-27 | 35.089 | Erection Completed. |  |  |  | 2026-03-02 | SUBHASH | 32
55 | 101/0 | DB1+0 | DRY |  | 2026-02-20 | 54.72 | Erection Completed. |  |  |  | 2026-03-03 | GOURI SHANKAR | 45
56 | 51/9 | DA+3 | DFR |  | 2026-02-28 | 36.771 | Erection Completed. |  |  |  | 2026-03-05 | SHAKILA KHATUN | 40
57 | 56/3 | DA+0 | DFR |  | 2026-02-25 | 35.089 | Erection Completed. |  |  |  | 2026-03-07 | NASIRUDDIN | 30
58 | 83/1 | DA+0 | DFR |  | 2026-02-24 | 35.089 | Erection Completed. |  |  |  | 2026-03-09 | TNR INFA | 24
59 | 85/1 | DA+9 | WET |  | 2026-03-08 | 43.575 | Erection Completed. |  |  |  | 2026-03-11 | SHAKILA KHATUN | 40
60 | 100/6 | DA+0 | DFR |  | 2026-03-10 | 35.089 | Erection Completed. |  |  |  | 2026-03-16 | TNR INFA | 24
61 | 101/6 | DA+0 | DFR |  | 2026-03-13 | 35.089 | Erection Completed. |  |  |  | 2026-03-16 | SHAKILA KHATUN | 40
62 | 55/3 | DA+0 | DRY |  | 2026-03-11 | 35.089 | Erection Completed. |  |  |  | 2026-03-18 | NASIRUDDIN | 30
63 | 101/7 | DA+0 | DFR |  | 2026-03-16 | 35.089 | Erection Completed. |  |  |  | 2026-03-20 | SHAKILA KHATUN | 40
64 | 100/7 | DA+3 | DFR |  | 2026-03-16 | 36.771 | Erection Completed. |  |  |  | 2026-03-23 | TNR INFA | 24
65 | 56/4 | DA+3 | WET |  | 2026-03-18 | 36.771 | Erection Completed. |  |  |  | 2026-03-25 | NASIRUDDIN | 30
66 | 100/4 | DA+0 | DFR |  | 2026-03-20 | 35.089 | Erection Completed. |  |  |  | 2026-03-29 | TNR INFA | 24
67 | 53/4 | DA+0 | WET |  | 2026-03-26 | 35.089 | Erection Completed. |  |  |  | 2026-04-01 | NASIRUDDIN | 30
68 | 100/8 | DA+0 | DFR |  | 2026-03-30 | 35.089 | Erection Completed. |  |  |  | 2026-04-04 | TNR INFA | 24
69 | 53/5 | DA+0 | DRY |  | 02.04-2026 | 35.089 | Erection Completed. |  |  |  | 2026-04-07 | NASIRUDDIN | 30
70 | 100/0 | DB2+0 | DFR |  | 2026-04-05 | 54.72 | Erection Completed. |  |  |  | 2026-04-12 | TNR INFA | 24
71 | 60/0 | DB2+0 | DFR |  | 2026-05-05 | 54.72 | WIP: 1st Section |  |  |  |  | NASIRUDDIN | 24
Formulas:
ROW cleared date = [Completed till Last Month]

## ROW
TL-02 765kV Kurnool IV - Bidar line
Foundation
Sr. No. | Location no. | Type of tower | ISSUE
1 | 50/0 | DC2+0
2 | 51/1 | DA+3
3 | 51/0 | DC2+0
4 | 51/5 | DA+0
5 | 52/2 | DA+0
6 | 52/3 | DA+0
7 | 52/4 | DA+0
8 | 53/0 | DB1+3
9 | 85/3 | DA+0
10 | 85/4 | DA+0

## SUPPLY
Supply Status - Stubs & Towers
Stub Details
SL No | Description | Unit | Line Qty | Received | Balance
1 | 3DA Stub | Set |  | 181
2 | 3DB Stub | Set |  | 27
3 | 3DC Stub | Set |  | 17
4 | 3D45 Stub | Set |  | 6
5 | 3D60 Stub | Set |  | 4
| Total | Set | 0 | 235 | 0 | 0 | 0
Tower Details
SL No | Tower Type | Description | Line Qty | Received | Balance |  |  | Remarks
1 | 3DA Type | Basic body |  | 169
|  | +0m BE |  | 129
|  | +3m BE |  | 40
|  | +6m BE |  | 18
|  | +9m BE |  | 12
2 | 3DB Type | Basic body |  | 31
|  | +0m BE |  | 27
|  | +3m BE |  | 0
|  | +6m BE |  | 0
|  | +9m BE |  | 7
3 | 3DC Type | Basic body |  | 21
|  | +0m BE |  | 18
|  | +3m BE |  | 3
|  | +6m BE |  | 0
|  | +9m BE |  | 3
4 | 3DD45 Type | Basic body |  | 7
|  | +0m BE |  | 6
|  | +3m BE |  | 1
|  | +6m BE |  | 0
|  | +9m BE |  | 4
5 | 3DD60 Type | Basic body |  | 2
|  | +0m BE |  | 0
|  | +3m BE |  | 0
|  | +6m BE |  | O
|  | +9m BE |  | 0
|  | Total |  | 230
Activity | Unit | Final Est. Qty | L2 till Last Month | Received till Last Month | Balance | L2 Plan for Current Month | Plan for Current Month | Progress for the Month | Received till Current Month | Gap between Suppy & Cumm.L2 | Remarks
Stub | Set | 292 | 292 | 235 | 57 | 0 | 0 | 0 | 235 | Gap between Supply & Cumm.L2
Tower | No's | 292 | 230 | 230 | 62 | 60 | 60 | 0 | 230 | 57
Conductor | kms | 4314 | 3000 | 3285.198 | 1028.802 | 300 | 300 | 0 | 3285.198 | 60
Cummulative progress till Previous Month
S No | Item | Unit | Total QTY | Planned L2 till Previous Month (MAR'26) | Completed till Previous month (MAR' 26) | L2 Planned for Current Month (Approved L2) | Balance after MAR'26 | March 26 Month Plan | MARCH MONTH PROGRESS | Cummulative Completed | Balance
1 | Supply of Stubs | Sets | 292 | 292 | 235 | 0 | 57 | 0 | 2 | 235 | 57
2 | Supply of Towers | Nos | 292 | 230 | 230 | 0 | 62 | 0 | 0 | 160 | 132
3 | Supply of Earthwire | Km | 121 | 85 | 86 | 0 | 35 | 0 | 0 | 86 | 35
4 | Supply of Conductor | Km | 4314 | 3000 | 3285.198 | 300 | 1028.802 | 300 | 478.825 | 3202.437 | 1111.563
5 | Supply of H/W Fittings | % | 100% | 70% | 75% | 0% | 100% | 0% | 0 |  | 100%
6 | Supply of Insultor | Nos | 7200 | 9200 | 0 | 0 | 7200 | 2450 | 0 | 0 | 7200
7 | Supply of OPGW | km | 123 | 0 | 0 | 0% | 123 | 0 | 0 | 0 | 123
8 | Supply of OPGW Accessories | % | 100% | 50% | 0% | 0% | 100% | 0 | 0 | 0 | 100%
9 | Supply of Earthing Materials | % | 100% | 100% | 75% | 0% | 25% | 0% | 0% | 75% | 25% | 0.16892
10 | Supply of Earthwire Accessories | % | 100% | 75% | 75% | 0% | 25% | 0% | 0% | 75% | 25% | 0.44595
11 | Supply of Tower Accessories | % | 100% | 20% | 0% | 0 | 100% | 0% | 0% | 0 | 100%
12 | Supply of Conductor Accessories | % | 100% | 70% | 75% | 0% | 25% | 40% | 75% | 1.5 | -50%

## Erection Compiled
SL No. | Location No. | Tower Type | Classification | Start Date | MT | Status | End Date | Gang Name | Gang Strength
1 | 56/7 | DA+0 | DFR | 2025-12-15 | 35.089 | Erection Completed. | 2025-12-20 | NASIRUDDIN | 35
2 | 59/2 | DA+0 | DRY | 2025-12-22 | 35.089 | Erection Completed. | 2025-12-27 | NASIRUDDIN | 35
3 | 77/3 | DA+0 | DFR | 2025-12-22 | 35.089 | Erection Completed. | 2025-12-31 | CRANE | 49
4 | 58/2 | DA+0 | DRY | 2025-12-25 | 35.089 | Erection Completed. | 2026-01-10 | NASIRUDDIN | 35
5 | 77/2 | DA+0 | DRY | 2025-12-25 | 35.089 | Erection Completed. | 2026-01-08 | CRANE | 49
6 | 58/1 | DA+6 | DRY | 2026-01-02 | 41.88 | Erection Completed. | 2026-01-10 | NASIRUDDIN | 35
7 | 77/1 | DA+0 | DRY | 2026-01-01 | 35.089 | Erection Completed. | 2026-01-13 | CRANE | 49
8 | 58/3 | DA+0 | DRY | 2026-01-09 | 35.089 | Erection Completed. | 2026-01-14 | NASIRUDDIN | 35
9 | 77/4 | DA+0 | DRY | 2026-01-07 | 35.089 | Erection Completed. | 2026-01-16 | DK VERMA | 21
10 | 82/1 | DA+0 | WC | 2026-01-11 | 35.089 | Erection Completed. | 2026-01-16 | SHAKILA KHATUN | 31
11 | 80/5 | DA+0 | DFRY | 2026-01-15 | 35.089 | Erection Completed. | 2026-01-20 | SHAKILA KHATUN | 31
12 | 59/4 | DA+6 | DRY | 2026-01-15 | 41.88 | Erection Completed. | 2026-01-21 | NASIRUDDIN | 35
13 | 77/7 | DA+0 | DFR | 2026-01-17 | 35.089 | Erection Completed. | 2026-01-21 | DK VERMA | 21
14 | 84/3 | DA+0 | DRY | 2026-01-16 | 35.089 | Erection Completed. | 2026-01-21 | SUBHASH | 32
15 | 99/11 | DA+0 | DFR | 2026-01-17 | 35.089 | Erection Completed. | 2026-01-21 | GOURI SHANKAR | 45
16 | 84/4 | DA+0 | DRY | 2026-01-19 | 35.089 | Erection Completed. | 2026-01-24 | SUBHASH | 32
17 | 80/1 | DA+6 | WFR | 2026-01-19 | 41.88 | Erection Completed. | 2026-01-25 | SHAKILA KHATUN | 31
18 | 59/5 | DA+0 | DRY | 2026-01-22 | 35.089 | Erection Completed. | 2026-01-27 | NASIRUDDIN | 35
19 | 99/10 | DA+0 | DFR | 2026-01-23 | 35.089 | Erection Completed. | 2026-01-27 | GOURI SHANKAR | 45
20 | 84/1 | DA+6 | DRY | 2026-01-25 | 41.88 | Erection Completed. | 2026-01-28 | SUBHASH | 32
21 | 99/7 | DA+0 | DRY | 2026-01-12 | 35.089 | Erection Completed. | 2026-01-29 | CRANE | 49
22 | 77/10 | DA+3 | DRY | 2026-01-26 | 36.771 | Erection Completed. | 2026-01-30 | DK VERMA | 21
23 | 79/2 | DA+6 | DFR | 2026-01-27 | 41.88 | Erection Completed. | 2026-01-31 | SHAKILA KHATUN | 31
24 | 100/2 | DA+3 | DFR | 2026-01-27 | 36.771 | Erection Completed. | 2026-01-31 | GOURI SHANKAR | 45
25 | 60/2 | DA+0 | DFR | 2026-01-27 | 35.089 | Erection Completed. | 2026-02-02 | NASIRUDDIN | 35
26 | 99/8 | DA+0 | DFR | 2026-01-30 | 35.089 | Erection Completed. | 2026-02-03 | CRANE | 49
27 | 85/2 | DA+0 | WET/WFR | 2026-01-31 | 35.089 | Erection Completed. | 2026-02-03 | SUBHASH | 32
28 | 79/3 | DA+9 | DFR | 2026-02-01 | 43.575 | Erection Completed. | 2026-02-04 | SHAKILA KHATUN | 31
29 | 84/5 | DA+9 | DRY | 2026-01-28 | 43.575 | Erection Completed. | 2026-02-05 | SUBHASH | 32
30 | 100/1 | DA+3 | WFR | 2026-01-30 | 36.771 | Erection Completed. | 2026-02-05 | GOURI SHANKAR | 45
31 | 56/8 | DA+0 | WC | 2026-02-06 | 35.089 | Erection Completed. | 2026-02-09 | SHAKILA KHATUN | 35
32 | 99/6 | DA+0 | DFR | 2026-12-05 | 35.089 | Erection Completed. | 2026-02-09 | CRANE | 49
33 | 84/0 | DB1+0 | DFR | 2026-02-05 | 54.72 | Erection Completed. | 2026-02-10 | SUBHASH | 32
34 | 56/6 | DA+0 | DRY | 2026-02-03 | 35.089 | Erection Completed. | 2026-02-11 | NASIRUDDIN | 35
35 | 101/2 | DA+0 | DFR | 2026-02-05 | 35.089 | Erection Completed. | 2026-02-12 | GOURI SHANKAR | 45
36 | 56/9 | DA+6 | DRY | 2026-02-10 | 41.88 | Erection Completed. | 2026-02-13 | SHAKILA KHATUN | 31
37 | 81/1 | DA+0 | DFR | 2026-02-10 | 35.089 | Erection Completed. | 2026-02-13 | SUBHASH | 32
38 | 99/9 | DA+0 | DRY | 2026-01-31 | 35.089 | Erection Completed. | 2026-02-16 | CRANE | 49
39 | 101/3 | DA+0 | DRY | 2026-02-12 | 35.089 | Erection Completed. | 2026-02-16 | GOURI SHANKAR | 45
40 | 102/4 | DA+0 | DFR | 2026-02-14 | 35.089 | Erection Completed. | 2026-02-17 | SUBHASH | 32
41 | 55/1 | DA+0 | DRY | 2026-02-14 | 35.089 | Erection Completed. | 2026-02-17 | SHAKILA KHATUN | 35
42 | 102/5 | DA+0 | WFR | 2026-02-15 | 35.089 | Erection Completed. | 2026-02-19 | SUBHASH | 32
43 | 56/7 | DB1+0 | DRY | 2026-02-12 | 54.72 | Erection Completed. | 2026-02-20 | NASIRUDDIN | 35
44 | 101/1 | DA+0 | DRY | 2026-02-16 | 35.089 | Erection Completed. | 2026-02-20 | GOURI SHANKAR | 45
45 | 52/0 | DB2+0 | DFR | 2026-02-17 | 54.72 | Erection Completed. | 2026-02-21 | SHAKILA KHATUN | 35
46 | 102/2 | DA+0 | DFR | 2026-02-20 | 35.089 | Erection Completed. | 2026-02-22 | SUBHASH | 32
47 | 100/5 | DA+0 | DFR | 2026-02-08 | 35.089 | Erection Completed. | 2026-02-24 | GOURI SHANKAR | 45
48 | 102/3 | DA+0 | DFR | 2026-02-22 | 35.089 | Erection Completed. | 2026-02-24 | SUBHASH | 32
49 | 53/1 | 3DA+3 | DFR | 2026-02-22 | 36.771 | Erection Completed. | 2026-02-25 | SHAKILA KHATUN | 40
50 | 56/2 | DA+3 | DRY | 2026-02-20 | 36.771 | Erection Completed. | 2026-02-26 | NASIRUDDIN | 30
51 | 102/1 | DA+0 | DFR | 2026-02-24 | 35.089 | Erection Completed. | 2026-02-27 | SUBHASH | 32
52 | 77/9 | DA+0 | DFR | 2026-02-24 | 35.089 | Erection Completed. | 2026-02-28 | TNR INFA | 24
53 | 53/2 | DA+0 | DRY | 2026-02-25 | 35.089 | Erection Completed. | 2026-02-28 | SHAKILA KHATUN | 40
54 | 101/5 | DA+0 | DRY | 2026-02-27 | 35.089 | Erection Completed. | 2026-03-02 | SUBHASH | 32
55 | 101/0 | DB1+0 | DRY | 2026-02-20 | 54.72 | Erection Completed. | 2026-03-03 | GOURI SHANKAR | 45
56 | 51/9 | DA+3 | DFR | 2026-02-28 | 36.771 | Erection Completed. | 2026-03-05 | SHAKILA KHATUN | 40
57 | 56/3 | DA+0 | DFR | 2026-02-25 | 35.089 | Erection Completed. | 2026-03-08 | NASIRUDDIN | 30
58 | 83/1 | DA+0 | DFR | 2026-02-24 | 35.089 | Erection Completed. | 2026-03-09 | TNR INFA | 24
59 | 85/1 | DA+9 | WET | 2026-03-08 | 43.575 | Erection Completed. | 2026-03-11 | SHAKILA KHATUN | 40
60 | 100/6 | DA+0 | DFR | 2026-03-10 | 35.089 | Erection Completed. | 2026-03-16 | TNR INFA | 24
61 | 101/6 | DA+0 | DFR | 2026-03-13 | 35.089 | Erection Completed. | 2026-03-16 | SHAKILA KHATUN | 40
62 | 55/3 | DA+0 | DRY | 2026-03-11 | 35.089 | Erection Completed. | 2026-03-18 | NASIRUDDIN | 30
63 | 101/7 | DA+0 | DFR | 2026-03-16 | 35.089 | Erection Completed. | 2026-03-20 | SHAKILA KHATUN | 40
64 | 100/7 | DA+3 | DFR | 2026-03-16 | 36.771 | Erection Completed. | 2025-03-23 | TNR INFA | 24
65 | 56/4 | DA+3 | WET | 2026-03-18 | 36.771 | Erection Completed. | 2026-03-25 | NASIRUDDIN | 24
66 | 100/4 | DA+0 | DFR | 2026-03-20 | 35.089 | Erection Completed. | 2026-03-29 | TNR INFA | 24
67 | 53/4 | DA+0 | WET | 2026-03-26 | 35.089 | Erection Completed. | 2026-04-01 | NASIRUDDIN | 30
68 | 100/8 | DA+0 | DFR | 2026-03-30 | 35.089 | Erection Completed. | 2026-03-04 | TNR INFA | 24
69 | 53/5 | DA+0 | DRY | 02.04-2026 | 35.089 | Erection Completed. | 2026-04-07 | NASIRUDDIN | 30
70 | 100/0 | DB2+0 | DFR | 2026-04-05 | 54.72 | Erection Completed. | 2026-04-12 | TNR INFA | 24

## X-ing Details
CROSSINGS PROPOSAL STATUS : 765 KV D/C Kurnool IV - Bidar TL (Part-2)
Crossing Type | 132 KV | 220kV | SH-Xing | NH-Xing | Railway-Xing | Total
Total Nos | 4 | 2 | 1 | 3 | 2 | 12
Submitted Till Date | 4 | 2 | 0 | 3 | 2 | 11
Approved Till Date | 0 | 0 | 0 | 0 | 0 | 0
Balance to Execute | 0 | 0 | 1 | 0 | 0 | 0
Crossings Details
Sl. No. | FROM (AP) | TO (AP) | Name of the Line | NAME OF CROSSING | Date of First Submission | Joint Inspection Status | Provisional approval status
1 | AP54 | AP55 | Railway crossing (Tandur - Vikarabad) | Railway crossing | 2025-11-26
2 | AP57 | AP58 | 220kV D/C transmission line Tandur - Gachibowli (HYD) | Power line | 2025-10-16
3 | AP61 | AP62 | NATIONAL HIGHWAY-163 (Kodangal - Hyderabad) | National highway crossing | 2025-11-28
4 | AP71 | AP72 | 132kV D/C transmission line Tandur - Mahabubnagar | Power line | 2025-10-14
5 | AP74 | AP75 | NATIONAL HIGHWAY-167N (Kodangal - Kosgi) | National highway crossing | 2025-11-28
6 | AP76 | AP77 | 220kV D/C transmission line Kosgi - Pargi | Power line | 2025-10-16
7 | AP88 | AP89 | 132kV S/C transmission line Maddur - Mahabubnagar | Power line | 2025-10-16
8 | AP95 | AP96 | 132kV S/C transmission line Maddur - Makthal | Power line | 2025-10-16
9 | AP98 | AP99 | STATE HIGHWAY-22 (Narayanpet - Marikal) | State highway crossing | Not Required
10 | AP106 | AP107 | Railway crossing (Raichur - Makthal) | Railway crossing | 2025-11-27
11 | AP109 | AP110 | 132kV S/C transmission line Makthal - Krishna Railway junction | Power line | 08.12.2025
12 | AP110 | AP111 | NATIONAL HIGHWAY-167N (Raichur - Marikal) | National highway crossing | 08.12.2025

## Visual Chart
VISUAL PROGRESS CHART
765 kV DC Kurnool IV - Bidar Transmission Line (TL-02)
| Foundation (Nos.):- |  | 115 | /292 | Erection (Nos.):- |  | 70 | /292 | Earthing (Nos.):- |  | 91 | /292 | Rough Sag (Kms):- |  | 0 / | 113.292 | Final Sag (Kms):- |  | 0 / | 113.292 | Date:- | 2026-05-09
| COMPLETION CHART | Unit | 0 | +3 | 6 | +9 | Total | Line Qty |  |  | s
[9 empty] | ERECTION | [5 empty] | Rough Sag |  | SH / NH Road Crossing
[9 empty] | WIP | [11 empty] | River
| DA | Nos | 135 | 48 | 21 | 12 | 216 | 216 | FOUNDATION | Type |  | Angle Tower |  |  |  |  | Gas Pipeline
| DB1 | Nos | 5 | 3 | 1 | 8 | 17 | 17
| DB2 | Nos | 13 | 2 | 4 | 2 | 21 | 21 | [5 empty] | Final Sag
| DCT | Nos | 1 |  |  |  | 1 | 1
| DC1 | Nos | 10 | 2 | 1 | 3 | 16 | 16 | [9 empty] | Railway
| DC2 | Nos | 3 | 3 | 1 | 0 | 7 | 7 | [7 empty] | WIP |  | Crossing
| DCT | Nos | 0 | 0 | 0 | 0 | 0 | 0 | Section Tower | SC | [10 empty] | 110kV - 800kV |  |  |  | Foundation | Erection | Earthing
| DD45 | Nos | 3 | 1 | 1 | 4 | 9 | 9 | TP | TT |  | Earthing |  |  | OPGW | [5 empty] | Line
| DD60 | Nos | 2 | 1 | 1 | 1 | 5 | 5
| Total Completed Foundations | [5 empty] | 115 | 177 | [16 empty] | 115 | 70 | 91
Wind Zone - 3 [AP48 - AP111]
COMMON TOWER (TL-1&2) | [28 empty] | DS | CS | SI | FDN | EAR | ERN | TW | PO | FS | OPGW
[28 empty] | TOTAL | 4.8324 | 4.8324 |  | 12 | 12 | 12 | 12 |  | 4.8324
[28 empty] | COMPLETED | FDN: #VALUE!
|  | 411 | Balaji Service | 432 | Balaji Service | 411 | Balaji Service | 432 |  | 411 |  | 432 |  | 411 | Balaji Service | 374.437 |  | 376.003 |  | 405 |  | 340 |  | 397 |  |  |  | BALANCE
| AP48/0 |  | 48/1 |  | 48/2 |  | 48/3 |  | 48/4 |  | 48/5 |  | 48/6 |  | 48/7 |  | AP49/0 |  | 49/1 |  | 49/2 |  | 49/3
| 3DCT+0 |  | 3DA+6 |  | 3DA+0 |  | 3DA+6 |  | 3DA+3 |  | 3DA+3 |  | 3DA+3 |  | 3DA+3 | 3.3144 | 3DC1+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0
[7 empty] | Trail pit |  |  |  | Trail pit
|  | 399 |  | 393 |  | 370 | VEER TEJA | 350 | VEER TEJA | 395 | VEER TEJA | 413 | VEER TEJA | 366 | VEER TEJA | 377.77 | VEER TEJA | 300 | SRI HARSH-1 | 393 | SRI HARSH-1 | 415 | SRI HARSH-1 | 411 | 8 |  | 7
| 49/4 |  | 49/5 |  | 49/6 |  | 49/7 |  | 49/8 |  | 49/9 |  | 49/10 |  | 49/11 |  | AP50/0 |  | 50/1 |  | 50/2 |  | 50/3
| 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 | 4.5818 | 3DC2+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 | 1.519
|  | 378 |  | 370 | SRI HARSH-1 | 370 |  | 404 |  | 374 |  | 416 | SRI HARSH-1 | 425 | SRI HARSH-1 | 411 | SRI HARSH-1 | 427 | SRI HARSH-1 | 370 | SRI HARSH-1 | 356 | SRI HARSHI-1 | 459
[25 empty] | 7 | 2 | 7
| AP51/0 |  | 51/1 |  | 51/2 |  | 51/3 |  | 51/4 |  | 51/5 |  | 51/6 |  | 51/7 |  | 51/8 |  | 51/9 |  | 51/10 |  | AP52/0
| 3DC2+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 | 4.301 | 3DB2+0
| SRI HARSH-1 | 355 |  | 348 |  | 434 |  | 401 | SRI HARSH-1 | 400 | SRI HARSH-1 | 413 | SRI HARSH-1 | 406 | SRI HARSH-1 | 390 | SRI HARSH-1 | 390 | SRI HARSH-1 | 430 |  | 332 |  | 229.642
[25 empty] | 7 | 4 | 7
| 52/1 |  | 52/2 |  | 52/3 |  | 52/4 |  | AP53/0 |  | 53/1 |  | 53/2 |  | 53/3 |  | 53/4 |  | 53/5 |  | 53/6 |  | AP54/0
| 3DA+9 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 | 1.997 | 3DB1+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 | 2.761 | 3DD60+0 | 0.22964
Rly X-ing
|  | 339 | SRI HARSH-1 | 365 |  | 409 | SRI HARSH-1 | 340.462 |  | 352 | SRI HARSH-1 | 419 | SRI HARSH-1 | 410 | SRI HARSH-1 | 413 | SRI HARSH-1 | 407 | RC | 351 | SRI HARSH-1 | 405 | SRI HARSH-1 | 393
[25 empty] | 8 | 7 | 7
| AP55/0 |  | 55/1 |  | 55/2 |  | 55/3 |  | AP56/0 |  | 56/1 |  | 56/2 |  | 56/3 |  | 56/4 |  | 56/5 |  | 56/6 |  | 56/7
| 3DD60+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 | 1.4535 | 3DB2+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 | 2.757 | 3DB1+0
| Rly X-ing | [9 empty] | Garden
| SRI HARSH-1 | 439 | SRI HARSH-1 | 398 | RC | 445 | RC | 355 |  | 445.645 |  | 214.742 |  | 498 | SRI HARSH-1 | 325 | SRI HARSH-1 | 372 | SRI HARSH-1 | 393.054 | SRI HARSH-1 | 349 | SRI HARSH-1 | 373 | 7 | 6 | 7
s
| 56/8 |  | 56/9 |  | 56/10 |  | 56/11 |  | 56/12 |  | AP57/0 |  | AP58/0 |  | 58/1 |  | 58/2 |  | 58/3 |  | AP59/0 |  | 59/1
| 3DA+0 |  | 3DA+6 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 | 2.4756 | 3DC1+9 | 0.21474 | 3DB2+6 |  | 3DA+6 |  | 3DA+0 |  | 3DA+0 | 1.5881 | 3DC1+0 |  | 3DA+0
RC Removed
[11 empty] | POWER LINE |  | POWER LINE
| SRI HARSH-1 | 386 | ROW | 429 | SRI HARSH-1 | 377 | SRI HARSH-1 | 401.837 | SRI HARSH | 402 |  | 344 | SRI HARSH-1 | 399 | SRI HARSH-1 | 439 |  | 403 |  | 480 | RC | 535 | RC | 389.004
[25 empty] | 6 | 4 | 6
| 59/2 |  | 59/3 |  | 59/4 |  | 59/5 |  | AP60/0 |  | 60/1 |  | 60/2 |  | 60/3 |  | 60/4 |  | 60/5 |  | 60/6 |  | 60/7
| 3DA+0 |  | 3DA+0 |  | 3DA+6 |  | 3DA+0 | 2.3158 | 3DB2+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+6 |  | 3DA+0 | 1.987 | 3DB1+6 | 0.48 | 3DB1+9 | 0.535 | 3DB1+9
Hydrabad owner
| SRI HARSH-1 | 454.047 |  | 247.492 |  | 373 | RC | 401 |  | 388 | RC | 328 | RC | 329.982 |  | 433 |  | 410 | RC | 307 | RC | 461.927 | RC | 439.047
[25 empty] | 1 |  | 1
| 60/8 |  | AP61/0 |  | AP62/0 |  | 62/1 |  | 62/2 |  | 62/3 |  | 62/4 |  | AP63/0 |  | 63/1 |  | 63/2 |  | 63/3 |  | AP64/0
| 3DA+3 | 0.84305 | 3DB1+0 | 0.24749 | 3DC1+0 |  | 3DA+0 |  | 3DA+9 |  | 3DA+0 |  | 3DA+0 | 1.82 | 3DC2+0 |  | 3DA+9 |  | 3DA+3 |  | 3DA+9 | 1.6119 | 3DD45+9 | 0.43905
|  |  | NH - X-ING |  | NH - X-ING |  |  |  | ROW | [7 empty] | ROW CLEAR
| RC | 401 |  | 350 | RC | 335 | ATK | 313.49 | ATK | 421 | ATK | 465.818 | ATK | 352 | ATK | 403 | RC | 373 | RC | 362 | RC | 351.24 |  | 361
[25 empty] | 5 |  | 4
| AP65/0 |  | 65/1 |  | 65/2 |  | 65/3 |  | AP66/0 |  | 66/1 |  | AP67/0 |  | 67/1 |  | 67/2 |  | 67/3 |  | 67/4 |  | AP68/0
| 3DC2+3 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 | 1.3995 | 3DB2+0 | 0.421 | 3DB1+9 | 0.46582 | 3DD45+3 |  | 3DA+6 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 | 1.8412 | 3DB2+0
|  |  | ROW CLEAR |  |  |  | ROW CLEAR | [7 empty] | ROW CLEAR
| RC | 375 |  | 424.851 | ATK | 414 | ATK | 345 | ATK | 502.628 | RC | 453 | ATK | 388 | ATK | 317 | ATK | 324 | ATK | 484.984 | RC | 248.518 |  | 429 | 4 |  | 4
| 68/1 |  | 68/2 |  | AP69/0 |  | 69/1 |  | 69/2 |  | AP70/0 |  | 70/1 |  | 70/2 |  | 70/3 |  | 70/4 |  | AP71/0 |  | AP72/0
| 3DA+3 |  | 3DA+3 | 1.1609 | 3DB2+6 |  | 3DA+9 |  | 3DA+6 | 1.2616 | 3DC2+3 |  | 3DA+9 |  | 3DA+0 |  | 3DA+0 |  | 3DA+6 | 1.967 | 3DC2+6 | 0.24852 | 3DB2+6
[17 empty] | Garden |  |  |  | RC Removed
[21 empty] | POWER LINE |  | POWER LINE
|  | 398.684 |  | 435 | (BALAJI INFRA) | 404 | (BALAJI INFRA) | 374.353 |  | 250.119 | RC | 398 | RC | 364 |  | 380 | RC | 459.272 | RC | 206.441 | RC | 385 | MARC | 372 | 3 | 1 | 3
| 72/1 |  | AP73/0 |  | 73/1 |  | 73/2 |  | AP74/0 |  | AP75/0 |  | 75/1 |  | 75/2 |  | 75/3 |  | AP76/0 |  | AP77/0 |  | 77/1
| 3DA+3 | 0.82768 | 3DB2+0 |  | 3DA+6 |  | 3DA+0 | 1.2134 | 3DC1+0 | 0.25012 | 3DC1+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 | 1.6013 | 3DC1+9 | 0.20644 | 3DD45+9 |  | 3DA+0
[9 empty] | NH : X-ING |  | NH : X-ING | [7 empty] | POWER LINE |  | POWER LINE
| MARC | 384 | MARC | 400 | BALRAJ | 386 |  | 398 | MARC | 393 | BALRAJ | 387 | MARC | 378 | MARC | 410 | BALRAJ | 367.58 | RC | 396 | RC | 395 |  | 414
[25 empty] | 8 | 6 | 3
| 77/2 |  | 77/3 |  | 77/4 |  | 77/5 |  | 77/6 |  | 77/7 |  | 77/8 |  | 77/9 |  | 77/10 |  | AP78/0 |  | 78/1 |  | 78/2
| 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 | 4.2606 | 3DC1+0 |  | 3DA+3 |  | 3DA+3
[7 empty] | Paddy Field | [15 empty] | Paddy Field
ROW CLEAR
| MARC | 350.09 |  | 364 | MARC | 452 | MARC | 392 | MARC | 369.645 | RC | 446 | MARC | 386 |  | 451 |  | 428.504 | MARC | 354.496 | MARC | 430.207 | RC | 394
[25 empty] | 7 | 4 | 6
| 78/3 |  | AP79/0 |  | 79/1 |  | 79/2 |  | 79/3 |  | AP80/0 |  | 80/1 |  | 80/2 |  | 80/3 |  | 80/4 |  | 80/5 |  | AP81/0
| 3DA+0 | 1.5551 | 3DC1+0 |  | 3DA+3 |  | 3DA+6 |  | 3DA+9 | 1.5776 | 3DB2+9 |  | 3DA+6 |  | 3DA+9 | 1.283 | 3DB1+3 |  | 3DA+3 |  | 3DA+0 | 1.2132 | 3DD45+9
| Paddy Field | [15 empty] | Paddy Field
ROW CLEAR
| MARC | 415 | MARC | 399 |  | 436.295 |  | 437 | MARC | 406 | RC | 437.796 | MARC | 412 | MARC | 356.628 | RC | 384.624 | MARC | 391 | BALAJI INFA | 436 |  | 406 | 7 | 5 | 5
| 81/1 |  | 81/2 |  | 81/3 |  | AP82/0 |  | 82/1 |  | 82/2 |  | AP83/0 |  | 83/1 |  | 83/2 |  | AP 84/0 |  | 84/1 |  | 84/2
| 3DA+0 |  | 3DA+3 |  | 3DA+0 | 1.6443 | 3DC1+9 |  | 3DA+0 |  | 3DA+6 | 1.2808 | 3DB2+6 |  | 3DA+0 |  | 3DA+9 | 1.1533 | 3DB1+0 |  | 3DA+6 |  | 3DA+0
[5 empty] | Paddy Field |  | Paddy Field
[17 empty] | ROW CLEAR | [5 empty] | ROW CLEAR
| BALRAJ | 359 | BALRAJ | 439 | BALRAJ | 393 | BALAJI INF | 314.949 | MARC | 437.001 | BALAJI INF-1 | 399 | BALAJI INF-1 | 303 | ROW | 337 | ROW | 339.169 | RC | 400 |  | 358.849 | RC | 468.492
[25 empty] | 6 | 5 | 2
| 84/3 |  | 84/4 |  | 84/5 |  | 84/6 |  | AP 85/0 |  | 85/1 |  | 85/2 |  | 85/3 |  | 85/4 |  | AP 86/0 |  | 86/1 |  | AP 87/0
| 3DA+0 |  | 3DA+0 |  | 3DA+9 |  | 3DA+0 | 2.7389 | 3DB1+0 |  | 3DA+9 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 | 1.8152 | 3DC1+6 |  | 3DA+3 | 0.75885 | 3DC1+3 | 0.46849
|  | 287.352 |  | 416 | MARC | 352.354 | MARC | 361 |  | 426 |  | 394 |  | 384 | RC | 414 | RC | 480 |  | 395 |  | 329 |  | 417.945 | 2 |  | 1
| AP 88/0 |  | AP 89/0 |  | 89/1 |  | AP 90/0 |  | 90/1 |  | 90/2 |  | 90/3 |  | 90/4 |  | 90/5 |  | AP 91/0 |  | 91/1 |  | 91/2
| 3DB1+9 | 0.28735 | 3DB2+9 |  | 3DA+0 | 0.76835 | 3DB2+0 |  | 3DA+3 |  | 3DA+3 |  | 3DA+3 |  | 3DA+0 | 1.979 | 3DB1+3 | 0.48 | 3DC2+3 |  | 3DA+3 |  | 3DA+6 | 1.1419
|  | 467 |  | 443 |  | 310.743 |  | 479 | RC | 321 |  | 506 |  | 421.207 |  | 421 | VKP | 406 |  | 435 |  | 532.759 | RC | 265.465
1
| AP 92/0 |  | 92/1 |  | 92/2 |  | AP 93/0 |  | 93/1 |  | 93/2 |  | 93/3 |  | AP 94/0 |  | 94/1 |  | 94/2 |  | 94/3 |  | AP 95/0
| 3DD45+0 | 0.467 | 3DB1+9 |  | 3DA+0 | 0.75374 | 3DB2+3 |  | 3DA+3 |  | 3DA+9 | 1.306 | 3DB1+9 | 0.42121 | 3DC1+3 |  | 3DA+0 |  | 3DA+3 | 1.262 | 3DB1+9 | 0.53276 | 3DD45+9 | 0.26546
Water Logged
ROW CLEAR
|  | 484 | RC | 611 |  | 367 | RC | 468.584 |  | 371.416 |  | 370 |  | 327 |  | 318 |  | 339.769 |  | 395.999 |  | 377 |  | 398
| AP 96/0 |  | 96/1 |  | 96/2 |  | 96/3 |  | 96/4 |  | 96/5 |  | 96/6 |  | 96/7 |  | 96/8 |  | AP 97/0 |  | 97/1 |  | 97/2
| 3DD45+6 | 0.484 | 3DB2+0 | 0.611 | 3DB2+0 |  | 3DA+6 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 | 2.5618 | 3DB2+0 |  | 3DA+3 |  | 3DA+0
|  | 393 |  | 373.66 |  | 363 |  | 349 |  | 386 |  | 390 |  | 417 |  | 422.997 |  | 340 |  | 365 |  | 403 |  | 382
| 97/3 |  | 97/4 |  | AP 98/0 |  | 98/1 |  | 98/2 |  | 98/3 |  | 98/4 |  | 98/5 |  | AP 99/0 |  | 99/1 |  | 99/2 |  | 99/3
| 3DA+0 |  | 3DA+0 | 1.9377 | 3DC1+0 |  | 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+6 | 2.328 | 3DC1+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3
ROW CLEAR
|  | 395 |  | 385 | SS VARSHINI | 381 | SS VARSHINI | 395 | SS VARSHINI | 403 | SS VARSHINI | 383 | SS VARSHINI | 386 | SS VARSHINI | 397 | SS VARSHINI | 370.834 | Balaji Infra | 422 | SSVC | 417 | SSVC | 400
[25 empty] | 10 | 9 | 7
| 99/4 |  | 99/5 |  | 99/6 |  | 99/7 |  | 99/8 |  | 99/9 |  | 99/10 |  | 99/11 |  | 99/12 |  | AP 100/0 |  | 100/1 |  | 100/2
| 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 | 4.9858 | 3DB2+0 |  | 3DA+3 |  | 3DA+3
| SSVC | 421 | SSVC | 419 | SSVC | 402 | BALAJI INFRA-2 | 402 | BALAJI INFRA-2 | 411 | BALAJI INFRA-2 | 355.169 | SSVC | 390 | VKP | 380 | VKP | 390 | VKP | 398 |  | 406 | VKP | 371 | 11 | 10 | 10
| 100/3 |  | 100/4 |  | 100/5 |  | 100/6 |  | 100/7 |  | 100/8 |  | AP 101/0 |  | 101/1 |  | 101/2 |  | 101/3 |  | 101/4 |  | 101/5
| 3DA+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+3 |  | 3DA+0 | 3.6492 | 3DB1+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0
[5 empty] | RC Removed | [7 empty] | RC Removed
| VKP | 392 | VKP | 390 | RC | 401 | RC | 406.005 |  | 385 | BALAJI INFRA-2 | 380 | BALAJI INFRA-2 | 380 | BALAJI INFRA-2 | 382 | BALAJI INFRA-2 | 383.991 | BALAJI INFRA-2 | 392.295 |  | 401.31 |  | 352
[25 empty] | 7 | 7 | 4
| 101/6 |  | 101/7 |  | 101/8 |  | 101/9 |  | AP 102/0 |  | 102/1 |  | 102/2 |  | 102/3 |  | 102/4 |  | 102/5 |  | 102/6 |  | AP 103/0
| 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 | 3.924 | 3DB2+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 | 2.7046 | 3DB2+0
RC Removed
|  | 368 |  | 440 |  | 364.132 |  | 407 |  | 375 |  | 313 |  | 388 | RC | 414 | RC | 385 |  | 360 |  | 382 |  | 415
| 103/1 |  | 103/2 |  | 103/3 |  | AP 104/0 |  | 104/1 |  | 104/2 |  | 104/3 |  | 104/4 |  | 104/5 |  | 104/6 |  | 104/7 |  | 104/8
| 3DA+0 |  | 3DA+0 |  | 3DA+6 | 1.5241 | 3DC1+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+6 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0
| RC | 429 |  | 383 |  | 447.107 | RC | 416 |  | 389 |  | 380 | RC | 362.384 | RC | 263.31 |  | 393 | RC | 384.17 |  | 348 |  | 350
| 104/9 |  | 104/10 |  | 104/11 |  | AP 105/0 |  | 105/1 |  | 105/2 |  | 105/3 |  | AP 106/0 |  | AP 107/0 |  | 107/1 |  | AP 108/0 |  | 108/1
| 3DA+3 |  | 3DA+6 |  | 3DA+6 | 4.6981 | 3DB2+3 |  | 3DA+0 |  | 3DA+0 |  | 3DA+0 | 1.5474 | 3DD60+3 | 0.26331 | 3DD60+6 |  | 3DA+0 | 0.77717 | 3DD45+0 |  | 3DA+0
Rly X-ing
Rly X-ing
|  | 428.526 | RC | 194.628 |  | 203.141 | [11 empty] | 1 | G1 | MARC |  | Closed
[18 empty] | 2 | G4 | SREE HARSHINI |  | Working
| 108/2 |  | AP 109/0 |  | AP 110/0 |  | AP 111/0 | [10 empty] | 3 | G5 | BALAJI INFRA |  | Closed
| 3DA+0 | 1.1265 | 3DB1+9 | 0.19463 | 3DD60+9 | 0.20314 | 3DD45+0 | [10 empty] | 4 | G7 | VKP TRADERS |  | Closed
[7 empty] | COMMON TOWER TL-2&3 | [10 empty] | 5 | G11 | VEER TEJA |  | Working
[5 empty] | Hold |  | Hold | [10 empty] | 6 | G6 | SAI SRI VARSHNI |  | Closed
[18 empty] | 7 | G10 | AMMU ENGG |  | Closed
The round mareked location can not be able taken up foundation, due to RC, RLY, P'LINE,NH | [17 empty] | 8 | G2 | NANDITA |  | Closed
[18 empty] | 9 | G3 | BALRAJ |  | Closed
[18 empty] | 10 | G12 | ATK |  | Working
C

## Foundation & Erection
Description | [5 empty] | FOUNDATION DETAILS |  |  |  |  | EARTHING DETAILS |  | Erection Details
SL. No | Loc No. | Type of Tower | Type of FDN | RC Fdn Y/N | RC Drawing Status | Stub Availbility Y/N | Fdn ROW | Date of Starting | Date of Completion | Gang Name | Type of Earthing Cp/Pipe | Date of Earthing Completed | Tower Parts Availbility | Tonnage MT | Erection ROW | Date of Starting | Date of Completion | Gang Name
1 | 48/0 | 3DCT+0 | DFR | No | -
2 | 48/1 | 3DA+6 | DFR | No | Yes | Yes | Excavated | [5 empty] | Yes | 41.88
3 | 48/2 | 3DA+0 | DFR | No | Yes | Yes | Excavated | [5 empty] | Yes | 35.089
4 | 48/3 | 3DA+6 | DFR | No | Yes | Yes | Excavated | [5 empty] | Yes | 41.88
5 | 48/4 | 3DA+3 | DFR | No | Yes | Yes | Excavated | [5 empty] | Yes | 36.771
6 | 48/5 | 3DA+3 | DFR | No | Yes | Yes | Wip | [5 empty] | Yes | 36.771
7 | 48/6 | 3DA+3 | DFR | No | Yes | Yes | Pit A&B Row | [5 empty] | Yes | 36.771
8 | 48/7 | 3DA+3 | DFR | No | Yes | Yes | Excavated | [5 empty] | Yes | 36.771
9 | 49/0 | 3DC1+0 | DFR | No | - | Yes | Clear | [5 empty] | Yes | 62.501
10 | 49/1 | 3DA+0 | DFR | No | Yes | Yes | Trial pit | [5 empty] | Yes | 35.089
11 | 49/2 | 3DA+0 | DFR | Yes | Yes | Yes | Clear | [5 empty] | Yes | 35.089
12 | 49/3 | 3DA+0 | DFR | No | Yes | Yes | Clear | [5 empty] | Yes | 35.089
13 | 49/4 | 3DA+0 | DFR | No | Yes | Yes | Clear | [5 empty] | Yes | 35.089
14 | 49/5 | 3DA+3 | DFR | No | Yes | Yes | Clear | [5 empty] | Yes | 36.771
15 | 49/6 | 3DA+0 | DFR | No | Yes | Yes | Clear | [5 empty] | Yes | 35.089
16 | 49/7 | 3DA+0 | DFR | No | Yes | Yes | Clear | [5 empty] | Yes | 35.089
17 | 49/8 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-04-24 | 2026-04-30 | VEER TEJA CONSTRUCTION | C P | 2026-04-30 | Yes | 35.089
18 | 49/9 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-04-15 | 2026-04-23 | VEER TEJA CONSTRUCTION |  |  | Yes | 35.089 | Completed
19 | 49/10 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-02-24 | 2026-03-11 | VEER TEJA CONSTRUCTION | C P | 2026-04-24 | Yes | 35.089 | Completed
20 | 49/11 | 3DA+0 | WFR | No | Yes | Yes | Completed | 2026-02-24 | 2026-03-14 | VEER TEJA CONSTRUCTION | C P | 2026-04-24 | Yes | 35.089 | Completed
21 | 50/0 | 3DC2+0 | WFR | No | - | Yes | Completed | 2026-02-24 | 2026-04-16 | VEER TEJA CONSTRUCTION | C P | 2026-04-02 | Yes | 62.501 | Completed
22 | 50/1 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-02-07 | 2026-02-12 | SHRIARSHINI | C P | 2026-02-15 | Yes | 35.089 | Completed
23 | 50/2 | 3DA+0 | WET | No | Yes | Yes | Completed | 2026-02-06 | 2026-02-17 | SHRIARSHINI | PTE | 2026-02-17 | Yes | 35.089 | Completed
24 | 50/3 | 3DA+3 | DFR | No | Yes | Yes | Completed | 2026-03-20 | 2026-03-25 | SHRIARSHINI | C P | 2026-03-29 | Yes | 36.771 | Completed
25 | 51/0 | 3DC2+0 | DFR | No | - | Yes | Row | [5 empty] | Yes | 62.501
26 | 51/1 | 3DA+3 | DFR | No | Yes | Yes | Row | [5 empty] | Yes | 36.771
27 | 51/2 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-03-21 | 2026-03-27 | SHRIARSHINI | C P | 2026-03-31 | Yes | 35.089 | Completed
28 | 51/3 | 3DA+0 | DFR | No | Yes | Yes | Row | [5 empty] | Yes | 35.089
29 | 51/4 | 3DA+0 | WET | No | Yes | Yes | Paddy | [5 empty] | Yes | 35.089
30 | 51/5 | 3DA+0 | DFR | No | Yes | Yes | Paddy | [5 empty] | Yes | 35.089
31 | 51/6 | 3DA+3 | DFR | No | Yes | Yes | Completed | 2026-03-11 | 2026-03-19 | SHRIARSHINI | C P | 2026-03-29 | Yes | 36.771 | Completed
32 | 51/7 | 3DA+3 | DFR | No | Yes | Yes | Completed | 2026-03-06 | 2026-03-13 | SHRIARSHINI | C P | 2026-03-14 | Yes | 36.771 | Completed
33 | 51/8 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-03-07 | 2026-03-14 | SHRIARSHINI | C P | 2026-03-17 | Yes | 35.089 | Completed
34 | 51/9 | 3DA+3 | DFR | No | Yes | Yes | Completed | 2026-02-01 | 2026-02-05 | SHRIARSHINI | C P | 2026-02-16 | Yes | 36.771 | Completed | 2026-02-28 | 2026-03-05 | #REF!
35 | 51/10 | 3DA+0 | WET | No | Yes | Yes | Completed | 2026-03-09 | 2026-03-17 | SHRIARSHINI | P T E | 2026-04-15 | Yes | 35.089 | Completed
36 | 52/0 | 3DB2+0 | DFR | No |  | Yes | Completed | 2026-01-23 | 2026-01-31 | SHRIARSHINI | C P | 2026-02-03 | Yes | 54.72 | Completed | 2026-02-17 | 2026-02-21 | #REF!
37 | 52/1 | 3DA+9 | DFR | No | Yes | Yes | Completed | 2026-03-17 | 2026-03-22 | SHRIARSHINI | C P | 2026-03-31 | Yes | 43.575 | Completed
38 | 52/2 | 3DA+0 | WFR | No | Yes | Yes | Paddy | [5 empty] | Yes | 35.089
39 | 52/3 | 3DA+0 | DFR | No | Yes | Yes | Row | [5 empty] | Yes | 35.089
40 | 52/4 | 3DA+0 | DFR | No | Yes | Yes | Row | [5 empty] | Yes | 35.089
41 | 53/0 | 3DB1+3 | DFR/WFR | No | Yes | Yes | Completed | 2026-03-30 | 2026-04-13 | SHRIHARSHINI | C P | 2026-04-13 | Yes | 57.484 | Completed
42 | 53/1 | 3DA+3 | DFR | No | Yes | Yes | Completed | 2026-01-28 | 2026-02-08 | SHRIARSHINI | C P | 2026-02-17 | Yes | 36.771 | Completed | 2026-02-22 | 2026-02-25 | #REF!
43 | 53/2 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2026-01-26 | 2026-01-30 | SHRIARSHINI | P T E | 2026-02-19 | Yes | 35.089 | Completed | 2026-02-25 | 2026-02-28 | #REF!
44 | 53/3 | 3DA+3 | WET | No | Yes | Yes | Completed | 2026-03-25 | 2026-03-31 | SHRIARSHINI | P T E | 2026-04-13 | Yes | 36.771 | Completed
45 | 53/4 | 3DA+0 | WET | No | Yes | Yes | Completed | 2026-02-05 | 2026-03-06 | SHRIARSHINI | P T E | 2026-04-13 | Yes | 35.089 | Completed | 2026-03-26 | 2026-04-01 | #REF!
46 | 53/5 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2026-02-02 | 2026-03-08 | SHRIARSHINI | P T E | 2026-04-13 | Yes | 35.089 | Completed | 02.04-2026 | 2026-04-07 | #REF!
47 | 53/6 | 3DA+3 | DRY | No | Yes | Yes | Clear | [5 empty] | Yes | 36.771
48 | 54/0 | 3DD60+0 | WFR | No | - | Yes | [6 empty] | Yes | 74.189
49 | 55/0 | 3DD60+0 | WFR | No | - | Yes | [6 empty] | Yes | 74.189
50 | 55/1 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2026-01-25 | 2026-01-28 | SHRIARSHINI | P T E | 2026-02-19 | Yes | 35.089 | Completed | 2026-02-14 | 2026-02-17 | #REF!
51 | 55/2 | 3DA+0 | DFR | No | Yes | Yes | Row | [5 empty] | Yes | 35.089
52 | 55/3 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2025-12-25 | 2025-12-31 | SHRIARSHINI | P T E | 2026-02-22 | Yes | 35.089 | Completed | 2026-03-11 | 2026-03-18 | #REF!
53 | 56/0 | 3DB2+0 | DFR | No |  | Yes | Clear | [5 empty] | Yes | 54.72
54 | 56/1 | 3DA+3 | DFR | No | Yes | Yes | Completed | 2025-12-21 | 2025-12-24 | SHRIARSHINI |  |  | Yes | 36.771 | Completed
55 | 56/2 | 3DA+3 | DRY | No | Yes | Yes | Completed | 2025-12-17 | 2025-12-27 | SHRIARSHINI | P T E | 2026-01-15 | Yes | 36.771 | Completed | 2026-02-20 | 2026-02-26 | #REF!
56 | 56/3 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2025-12-14 | 2025-12-19 | SHRIARSHINI | C P | 2025-12-25 | Yes | 35.089 | Completed | 2026-02-25 | 2026-03-07 | #REF!
57 | 56/4 | 3DA+3 | WET | No | Yes | Yes | Completed | 2025-12-01 | 2026-01-06 | SHRIARSHINI | P T E | 2026-01-15 | Yes | 36.771 | Completed | 2026-03-18 | 2026-03-25 | #REF!
58 | 56/5 | 3DA+3 | WC | Yes | Yes | Yes | Excavated | [5 empty] | Yes | 36.771
59 | 56/6 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2026-01-09 | 2026-01-17 | SHRIARSHINI | P T E | 2026-01-21 | Yes | 35.089 | Completed | 2026-02-03 | 2026-02-11 | #REF!
60 | 56/7 | 3DB1+0 | DRY | No | Yes | Yes | Completed | 2026-01-07 | 2026-01-16 | SHRIARSHINI | P T E | 2026-01-18 | Yes | 54.72 | Completed | 2026-02-12 | 2026-02-20 | #REF!
61 | 56/8 | 3DA+0 | WC | No | Yes | Yes | Completed | 2026-01-17 | 2026-01-21 | SHRIARSHINI | P T E | 2026-02-19 | Yes | 35.089 | Completed | 2026-02-06 | 2026-02-09 | #REF!
62 | 56/9 | 3DA+6 | DRY | No | Yes | Yes | Completed | 2026-01-04 | 2026-01-10 | SHRIARSHINI | P T E | 2026-02-19 | Yes | 41.88 | Completed | 2026-02-10 | 2026-02-13 | #REF!
63 | 56/10 | 3DA+0 | DFR | Yes | Yes | Yes | Clear | [5 empty] | Yes | 35.089
64 | 56/11 | 3DA+0 | WFR | Yes | Yes | Yes | Paddy | [5 empty] | Yes | 35.089
65 | 56/12 | 3DA+0 | DFR | No | Yes | Yes | Paddy | [5 empty] | Yes | 35.089
66 | 57/0 | 3DC1+9 | WET | No | - | Yes | [6 empty] | Yes | 75.874
67 | 58/0 | 3DB2+6 | WET | No |  | Yes | [6 empty] | Yes | 64.672
68 | 58/1 | 3DA+6 | DRY | No | Yes | Yes | Completed | 2025-12-01 | 2025-12-08 | SHRIARSHINI | P T E | 2026-01-22 | Yes | 41.88 | Completed | 2026-01-02 | 2026-01-10 | #REF!
69 | 58/2 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2025-11-27 | 2025-12-03 | SHRIARSHINI | P T E | 2026-01-16 | Yes | 35.089 | Completed | 2025-12-25 | 2026-01-10 | #REF!
70 | 58/3 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2025-12-09 | 2025-12-14 | SHRIARSHINI | P T E | 2026-01-16 | Yes | 35.089 | Completed | 2026-01-09 | 2026-01-14 | #REF!
71 | 59/0 | 3DC1+0 | DFR | No | - | Yes | Completed | 2026-01-07 | 2026-01-26 | SHRIARSHINI - 2 | C P | 2026-01-28 | Yes | 62.501 | Completed
72 | 59/1 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2025-11-23 | 2025-11-29 | SHRIARSHINI | C P | 2026-01-22 | Yes | 35.089 | Completed | 2025-12-15 | 2025-12-20 | #REF!
73 | 59/2 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2025-10-29 | 2025-11-08 | SHRIARSHINI | P T E | 2026-02-22 | Yes | 35.089 | Completed | 2025-12-22 | 2025-12-27 | #REF!
74 | 59/3 | 3DA+0 | DFR | No | Yes | Yes | Row | [5 empty] | Yes | 35.089
75 | 59/4 | 3DA+6 | DRY | No | Yes | Yes | Completed | 2025-10-08 | 2025-10-21 | SHRIARSHINI | P T E | 2025-10-19 | Yes | 41.88 | Completed | 2026-01-15 | 2026-01-21 | #REF!
76 | 59/5 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2025-10-08 | 2025-10-19 | SHRIARSHINI | P T E | 2026-02-22 | Yes | 35.089 | Completed | 2026-01-22 | 2026-01-27 | #REF!
77 | 60/0 | 3DB2+0 | DFR | No |  | Yes | Completed | 2026-03-16 | 2026-04-06 | SHRIARSHINI - 2 | C P | 2026-04-15 | Yes | 54.72 | Completed
78 | 60/1 | 3DA+0 | DFR | No | Yes | Yes | Clear | [5 empty] | Yes | 35.089
79 | 60/2 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2025-10-14 | 2025-10-25 | SHRIARSHINI | C P | 2026-01-23 | Yes | 35.089 | Completed | 2026-01-27 | 2026-02-02 | #REF!
80 | 60/3 | 3DA+6 | DRY | No | Yes | Yes | Completed | 2025-10-23 | 2025-11-15 | SHRIARSHINI | P T E | 2026-02-22 | Yes | 41.88 | Completed
81 | 60/4 | 3DA+0 | WFR | No | Yes | Yes | One Pit Paddy | [5 empty] | Yes | 35.089
82 | 60/5 | 3DB1+6 | WFR | No | Yes | Yes | Paddy | [5 empty] | Yes | 64.672
83 | 60/6 | 3DB1+9 | SFR | Yes | Yes | Yes | Paddy | [5 empty] | Yes | 66.436
84 | 60/7 | 3DB1+9 | SFR | Yes | Yes | Yes | Paddy | [5 empty] | Yes | 66.436
85 | 60/8 | 3DA+3 | DFR | No | Yes | Yes | Completed | 2025-11-12 | 2025-11-23 | SHRIARSHINI | C P | 2026-01-24 | Yes | 36.771 | Completed
86 | 61/0 | 3DB1+0 | DFR | No | Yes | Yes | [6 empty] | Yes | 54.72
87 | 62/0 | 3DC1+0 | DFR | No | - | Yes | [6 empty] | Yes | 62.501
88 | 62/1 | 3DA+0 | DFR | Yes | Yes | Yes | [6 empty] | Yes | 35.089
89 | 62/2 | 3DA+9 | DFR | No | Yes | Yes | [6 empty] | Yes | 43.575
90 | 62/3 | 3DA+0 | DFR | Yes | Yes | Yes | [6 empty] | Yes | 35.089
91 | 62/4 | 3DA+0 | DFR | Yes | Yes | Yes | [6 empty] | Yes | 35.089
92 | 63/0 | 3DC2+0 | DFR | No | - | Yes
93 | 63/1 | 3DA+9 | DFR | No | Yes | Yes | [6 empty] | Yes | 43.575
94 | 63/2 | 3DA+3 | WET | Yes | Yes | Yes | [6 empty] | Yes | 36.771
95 | 63/3 | 3DA+9 | WFR | Yes | Yes | Yes | [6 empty] | Yes | 43.575
96 | 64/0 | 3DD45+9 | WC | Yes | - | Yes | [6 empty] | Yes | 83.716
97 | 65/0 | 3DC2+3 | DFR | Yes | - | Yes | [6 empty] | Yes | 65.37
98 | 65/1 | 3DA+0 | WFR | No | Yes | Yes | [6 empty] | Yes | 35.089
99 | 65/2 | 3DA+3 | DFR | Yes | Yes | Yes | [6 empty] | Yes | 36.771
100 | 65/3 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-04-27 | 2026-04-29 | ATK | CPE | 2026-05-01 | Yes | 35.089
101 | 66/0 | 3DB2+0 | DFR | No |  | Yes | Completed | 2026-04-30 | 2026-05-03 | ATK | CP | 2026-05-05 | Yes | 54.72
102 | 66/1 | 3DB1+9 | DRY | No | Yes | Yes | Completed | 2026-04-17 | 2026-04-21 | ATK | CP | 2026-04-24 | Yes | 66.436 | Completed
103 | 67/0 | 3DD45+3 | DFR | No | - | Yes | Completed | 2026-04-20 | 2026-04-26 | ATK | CP | 2026-04-28 | Yes | 72.045
104 | 67/1 | 3DA+6 | WC | No | Yes | Yes | Completed | 2026-04-29 | 2026-05-05 | ATK |  |  | Yes | 41.88
105 | 67/2 | 3DA+0 | DFR | Yes | Yes | Yes | [6 empty] | Yes | 35.089
106 | 67/3 | 3DA+0 | DFR | Yes | Yes | Yes | [6 empty] | Yes | 35.089
107 | 67/4 | 3DA+3 | DFR | Yes | Yes | Yes | [6 empty] | Yes | 36.771
108 | 68/0 | 3DB2+0 | DFR | No |  | Yes | [6 empty] | Yes | 54.72
109 | 68/1 | 3DA+3 | DFR | Yes | Yes | Yes | [6 empty] | Yes | 36.771
110 | 68/2 | 3DA+3 | DFR | No | Yes | Yes | [6 empty] | Yes | 36.771
111 | 69/0 | 3DB2+6 | WC | No |  | Yes | [6 empty] | Yes | 64.672
112 | 69/1 | 3DA+9 | DFR | No | Yes | Yes | [6 empty] | Yes | 43.575
113 | 69/2 | 3DA+6 | WFR | No | Yes | Yes | [6 empty] | Yes | 41.88
114 | 70/0 | 3DC2+3 | WFR | Yes | - | Yes
115 | 70/1 | 3DA+9 | DFR | No | Yes | Yes | Completed | 2026-03-25 | 2026-04-11 | ATK | C P | 2026-04-13 | Yes | 43.575 | Completed
116 | 70/2 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-03-26 | 2026-04-13 | ATK | C P | 2026-04-15 | Yes | 35.089 | Completed
117 | 70/3 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-04-09 | 2026-04-18 | ATK | C P | 2026-04-19 | Yes | 35.089 | Completed
118 | 70/4 | 3DA+6 | DFR | No | Yes | Yes | Completed | 2026-03-26 | 2026-04-16 | ATK | C P | 2026-04-19 | Yes | 41.88 | Completed
119 | 71/0 | 3DC2+6 | DFR | No | - | Yes | [6 empty] | Yes | 73.494
120 | 72/0 | 3DB2+6 | DFR | No |  | Yes | [6 empty] | Yes | 64.672
121 | 72/1 | 3DA+3 | DRY | No | Yes | Yes | [6 empty] | Yes | 36.771
122 | 73/0 | 3DB2+0 | DFR | No |  | Yes | [6 empty] | Yes | 54.72
123 | 73/1 | 3DA+6 | WC | No | Yes | Yes | Completed | 2025-12-04 | 2025-12-18 | BALAJI INFRA | P T E | 2026-01-11 | Yes | 41.88 | Completed
124 | 73/2 | 3DA+0 | WC | No | Yes | Yes | Completed | 2025-12-04 | 2025-12-24 | BALAJI INFRA | P T E | 2026-01-11 | Yes | 35.089 | Completed
125 | 74/0 | 3DC1+0 | WFR | No | - | Yes | [6 empty] | Yes | 62.501
126 | 75/0 | 3DC1+0 | WFR | Yes | - | Yes | [6 empty] | Yes | 62.501
127 | 75/1 | 3DA+3 | WET | Yes | Yes | Yes | [6 empty] | Yes | 36.771
128 | 75/2 | 3DA+0 | WET | No | Yes | Yes | [6 empty] | Yes | 35.089
129 | 75/3 | 3DA+0 | WET | Yes | Yes | Yes | [6 empty] | Yes | 35.089
130 | 76/0 | 3DC1+9 | DFR | Yes | - | Yes | [6 empty] | Yes | 75.874
131 | 77/0 | 3DD45+9 | DFR | Yes | - | Yes | [6 empty] | Yes | 83.716
132 | 77/1 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2025-11-07 | 2025-11-25 | MARC | P T E | 2025-12-01 | Yes | 35.089 | Completed | 2026-01-01 | 2026-01-13 | #REF!
133 | 77/2 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2025-11-18 | 2025-11-30 | MARC | P T E | 2025-12-19 | Yes | 35.089 | Completed | 2025-12-25 | 2026-01-08 | #REF!
134 | 77/3 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2025-11-07 | 2025-11-19 | MARC |  |  | Yes | 35.089 | Completed | 2025-12-22 | 2025-12-31 | #REF!
135 | 77/4 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2025-09-17 | 2025-10-31 | SHIVRATHIRI BALRAJ |  |  | Yes | 35.089 | Completed | 2026-01-07 | 2026-01-16 | #REF!
136 | 77/5 | 3DA+0 | WC | No | Yes | Yes | [6 empty] | Yes | 35.089
137 | 77/6 | 3DA+0 | WC | No | Yes | Yes | Completed | 2025-11-27 | 2025-12-12 | MARC | P T E | 2025-12-20 | Yes | 35.089 | Completed
138 | 77/7 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2025-11-02 | 2025-11-09 | SHIVRATHIRI BALRAJ |  |  | Yes | 35.089 | Completed | 2026-01-17 | 2026-01-21 | #REF!
139 | 77/8 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2025-11-02 | 2025-11-13 | MARC |  |  | Yes | 35.089 | Completed
140 | 77/9 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-02-02 | 2026-02-10 | MARC | C P | 2026-02-13 | Yes | 35.089 | Completed | 2026-02-24 | 2026-02-28 | #REF!
141 | 77/10 | 3DA+3 | DRY | No | Yes | Yes | Completed | 2025-10-27 | 2025-11-05 | SHIVRATHIRI BALRAJ |  |  | Yes | 36.771 | Completed | 2026-01-26 | 2026-01-30 | #REF!
142 | 78/0 | 3DC1+0 | WFR | Yes | - | Yes | [6 empty] | Yes | 62.501
143 | 78/1 | 3DA+3 | WFR | Yes | Yes | Yes | [6 empty] | Yes | 36.771
144 | 78/2 | 3DA+3 | WFR | No | Yes | Yes
145 | 78/3 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2026-01-26 | 2026-02-06 | MARC | P T E | 2026-02-14 | Yes | 35.089 | Completed
146 | 79/0 | 3DC1+0 | DFR | No | - | Yes | [6 empty] | Yes | 62.501
147 | 79/1 | 3DA+3 | WET | No | Yes | Yes | Completed | 2025-12-06 | 2025-12-25 | MARC | P T E | 2025-12-29 | Yes | 36.771 | Completed
148 | 79/2 | 3DA+6 | DFR | No | Yes | Yes | Completed | 2025-12-26 | 2026-01-05 | MARC | C P | 2026-04-17 | Yes | 41.88 | Completed | 2026-01-27 | 2026-01-31 | #REF!
149 | 79/3 | 3DA+9 | DFR | No | Yes | Yes | Completed | 2025-12-19 | 2025-12-30 | MARC | C P | 2026-04-17 | Yes | 43.575 | Completed | 2026-02-01 | 2026-02-04 | #REF!
150 | 80/0 | 3DB2+9 | DFR | Yes |  | Yes | [6 empty] | Yes | 66.436
151 | 80/1 | 3DA+6 | WFR | No | Yes | Yes | Completed | 2025-08-29 | 2025-10-10 | MARC | C P | 2025-12-30 | Yes | 41.88 | Completed | 2026-01-19 | 2026-01-25 | #REF!
152 | 80/2 | 3DA+9 | WFR | No | Yes | Yes | [6 empty] | Yes | 43.575
153 | 80/3 | 3DB1+3 | WFR | No | Yes | Yes | [6 empty] | Yes | 57.484
154 | 80/4 | 3DA+3 | WFR | No | Yes | Yes | Completed | 2025-09-23 | 2025-10-27 | MARC |  |  | Yes | 36.771 | Completed
155 | 80/5 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2025-09-02 | 2025-09-18 | MARC | P T E | 2025-09-24 | Yes | 35.089 | Completed | 2026-01-15 | 2026-01-20 | #REF!
156 | 81/0 | 3DD45+9 | DFR | Yes | - | Yes | [6 empty] | Yes | 83.716
157 | 81/1 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2025-08-23 | 2025-09-13 | MARC |  |  | Yes | 35.089 | Completed | 2026-02-10 | 2026-02-13 | #REF!
158 | 81/2 | 3DA+3 | DFR | No | Yes | Yes | Completed | 2025-07-16 | 2025-08-07 | MARC |  |  | Yes | 36.771 | Completed
159 | 81/3 | 3DA+0 | WFR | No | Yes | Yes | [6 empty] | Yes | 35.089
160 | 82/0 | 3DC1+9 | WFR | No | - | No | [6 empty] | Yes | 75.874
161 | 82/1 | 3DA+0 | WC | No | Yes | Yes | Completed | 2025-07-11 | 2025-08-22 | MARC | P T E | 2025-09-08 | Yes | 35.089 | Completed | 2026-01-11 | 2026-01-16 | #REF!
162 | 82/2 | 3DA+6 | DFR | Yes | Yes | Yes | [6 empty] | Yes | 41.88
163 | 83/0 | 3DB2+6 | DFR | No |  | Yes | Completed | 2026-01-06 | 2026-01-14 | MARC | C P | 2026-04-19 | Yes | 64.672 | Completed
164 | 83/1 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-02-08 | 2026-02-15 | MARC | C P | 2026-02-24 | Yes | 35.089 | Completed | 2026-02-24 | 2026-03-09 | #REF!
165 | 83/2 | 3DA+9 | DFR | Yes | Yes | Yes | [6 empty] | Yes | 43.575
166 | 84/0 | 3DB1+0 | DFR | No | Yes | Yes | Completed | 2026-01-22 | 2026-01-26 | MARC | C P | 2026-04-18 | Yes | 54.72 | Completed | 2026-02-05 | 2026-02-10 | #REF!
167 | 84/1 | 3DA+6 | DRY | No | Yes | Yes | Completed | 2026-01-04 | 2026-01-12 | BALAJI INFRA | P T E | 2026-04-19 | Yes | 41.88 | Completed | 2026-01-25 | 2026-01-28 | #REF!
168 | 84/2 | 3DA+0 | DFR | No | Yes | Yes | [6 empty] | Yes | 35.089
169 | 84/3 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2025-10-10 | 2025-10-19 | SHIVRATHIRI BALRAJ |  |  | Yes | 35.089 | Completed | 2026-01-16 | 2026-01-21 | #REF!
170 | 84/4 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2025-10-11 | 2025-10-24 | SHIVRATHIRI BALRAJ | P T E | 2026-04-22 | Yes | 35.089 | Completed | 2026-01-19 | 2026-01-24 | #REF!
171 | 84/5 | 3DA+9 | DRY | No | Yes | Yes | Completed | 2026-01-02 | 2026-01-08 | BALAJI INFRA |  |  | Yes | 43.575 | Completed | 2026-01-28 | 2026-02-05 | #REF!
172 | 84/6 | 3DA+0 | WC | No | Yes | Yes | Completed | 2026-12-21 | 2025-12-31 | BALAJI INFRA |  |  | Yes | 35.089 | Completed
173 | 85/0 | 3DB1+0 | WFR | No | Yes | Yes | Wip | [5 empty] | Yes | 54.72
174 | 85/1 | 3DA+9 | WET | No | Yes | Yes | Completed | 2026-01-27 | 2026-02-25 | MARC | P T E | 2026-03-08 | Yes | 43.575 | Completed | 2026-03-08 | 2026-03-11 | #REF!
175 | 85/2 | 3DA+0 | WET/WFR | No | Yes | Yes | Completed | 2026-01-06 | 2026-01-22 | BALAJI INFRA |  |  | Yes | 35.089 | Completed | 2026-01-31 | 2026-02-03 | #REF!
176 | 85/3 | 3DA+0 | WFR | No | Yes | Yes | [6 empty] | Yes | 35.089
177 | 85/4 | 3DA+0 | WET | No | Yes | Yes | [6 empty] | Yes | 35.089
178 | 86/0 | 3DC1+6 | DFR | Yes | - | Yes | [6 empty] | Yes | 73.494
179 | 86/1 | 3DA+3 | WC | No | Yes | Yes | [6 empty] | Yes | 36.771
180 | 87/0 | 3DC1+3 | DFR | Yes | - | Yes | [6 empty] | Yes | 65.37
181 | 88/0 | 3DB1+9 | WC | No | Yes | Yes
182 | 89/0 | 3DC1+9 | DFR | No | - | No | [6 empty] | Yes | 75.874
183 | 89/1 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-02-23 | 2026-03-03 | MARC | C P | 2026-03-13 | Yes | 35.089 | Completed
184 | 90/0 | 3DB2+0 | DFR | No |  | Yes | Completed | 2026-03-06 | 2026-03-18 | MARC |  |  | Yes | 54.72 | Completed
185 | 90/1 | 3DA+3 | DFR | No | Yes | Yes | Wip | [5 empty] | Yes | 36.771
186 | 90/2 | 3DA+3 | DFR | No | Yes | Yes | Wip | [5 empty] | Yes | 36.771
187 | 90/3 | 3DA+3 | DFR | No | Yes | Yes | Wip | [5 empty] | Yes | 36.771
188 | 90/4 | 3DA+0 | WFR | Yes | Yes | Yes | [6 empty] | Yes | 35.089
189 | 90/5 | 3DB1+9 | DFR | No | Yes | Yes
190 | 91/0 | 3DC2+3 | DFR | No | - | No | [6 empty] | Yes | 65.37
191 | 91/1 | 3DA+3 | DFR | No | Yes | Yes | [6 empty] | Yes | 36.771
192 | 91/2 | 3DA+6 | DFR | No | Yes | Yes | [6 empty] | Yes | 41.88
193 | 92/0 | 3DD45+0 | WFR | No | - | Yes | [6 empty] | Yes | 68.265
194 | 92/1 | 3DB1+9 | DFR | No | Yes | Yes | [6 empty] | Yes | 66.436
195 | 92/2 | 3DA+0 | DFR | No | Yes | Yes | [6 empty] | Yes | 35.089
196 | 93/0 | 3DB2+3 | WFR | No |  | No | [6 empty] | Yes | 57.484
197 | 93/1 | 3DA+3 | DFR | Yes | Yes | Yes | [6 empty] | Yes | 36.771
198 | 93/2 | 3DA+9 | DFR | No | Yes | Yes
199 | 93/3 | 3DB1+9 | WFR | No | Yes | No | [6 empty] | Yes | 66.436
200 | 94/0 | 3DC1+3 | DFR | No | - | No | [6 empty] | Yes | 65.37
201 | 94/1 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2025-12-10 | 2025-12-31 | VKP TRADERS |  |  | Yes | 35.089 | Completed
202 | 94/2 | 3DA+3 | DFR | No | Yes | No
203 | 94/3 | 3DB1+9 | DFR | No | Yes | No | [6 empty] | Yes | 66.436
204 | 95/0 | 3DD45+9 | DFR | Yes | - | Yes | [6 empty] | Yes | 83.716
205 | 96/0 | 3DD45+6 | DFR | No | - | No
206 | 96/1 | 3DB2+0 | DFR | Yes |  | No
207 | 96/2 | 3DB2+0 | DFR | No |  | No | [6 empty] | Yes | 54.72
208 | 96/3 | 3DA+6 | DFR | Yes | Yes | Yes
209 | 96/4 | 3DA+3 | DFR | No | Yes | No
210 | 96/5 | 3DA+0 | DFR | No | Yes | No
211 | 96/6 | 3DA+0 | DFR | No | Yes | No
212 | 96/7 | 3DA+0 | WET | No | Yes | No
213 | 96/8 | 3DA+0 | WET | No | Yes | Yes
214 | 97/0 | 3DB2+0 | WET | No |  | No | [6 empty] | Yes | 54.72
215 | 97/1 | 3DA+3 | WFR | No | Yes | No
216 | 97/2 | 3DA+0 | WFR | No | Yes | No
217 | 97/3 | 3DA+0 | WFR | No | Yes | No
218 | 97/4 | 3DA+0 | DFR | No | Yes | No
219 | 98/0 | 3DC1+0 | DFR | No | - | No | [6 empty] | Yes | 62.501
220 | 98/1 | 3DA+3 | DFR | No | Yes | No
221 | 98/2 | 3DA+0 | DFR | No | Yes | No
222 | 98/3 | 3DA+0 | DFR | No | Yes | No
223 | 98/4 | 3DA+0 | DFR | No | Yes | No
224 | 98/5 | 3DA+6 | DFR | No | Yes | No
225 | 99/0 | 3DC1+0 | DFR | No | - | No
226 | 99/1 | 3DA+0 | DFR | No | Yes | No
227 | 99/2 | 3DA+0 | DFR | No | Yes | Yes
228 | 99/3 | 3DA+3 | DFR | No | Yes | Yes
229 | 99/4 | 3DA+3 | DFR | No | Yes | Yes
230 | 99/5 | 3DA+0 | DFR | No | Yes | Yes | Wip
231 | 99/6 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2025-12-07 | 2025-12-20 | SAI SREE VARSHINI | C P | 2026-01-07 | Yes | 35.089 | Completed | 2026-12-05 | 2026-02-09 | #REF!
232 | 99/7 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2025-12-07 | 2025-12-15 | SAI SREE VARSHINI | P T E | 2026-01-07 | Yes | 35.089 | Completed | 2026-01-12 | 2026-01-29 | #REF!
233 | 99/8 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2025-12-14 | 2025-12-26 | SAI SREE VARSHINI | C P | 2026-01-06 | Yes | 35.089 | Completed | 2026-01-30 | 2026-02-03 | #REF!
234 | 99/9 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2025-12-14 | 2025-12-23 | SAI SREE VARSHINI | P T E | 2026-01-01 | Yes | 35.089 | Completed | 2026-01-31 | 2026-02-16 | #REF!
235 | 99/10 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2025-12-22 | 2025-12-29 | SAI SREE VARSHINI | C P | 2026-01-06 | Yes | 35.089 | Completed | 2026-01-23 | 2026-01-27 | #REF!
236 | 99/11 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2025-12-27 | 2025-12-31 | SAI SREE VARSHINI | C P | 2026-01-06 | Yes | 35.089 | Completed | 2026-01-17 | 2026-01-21 | #REF!
237 | 99/12 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2025-12-31 | 2026-01-06 | SAI SREE VARSHINI |  |  | Yes | 35.089 | Completed
238 | 100/0 | 3DB2+0 | DFR | No |  | Yes | Completed | 2026-03-24 | 2026-03-18 | BALAJI INFRA | C P | 2026-03-23 | Yes | 54.72 | Completed | 2026-04-05 | 2026-04-12 | #REF!
239 | 100/1 | 3DA+3 | WFR | No | Yes | Yes | Completed | 2026-01-04 | 2026-01-23 | SAI SREE VARSHINI |  |  | Yes | 36.771 | Completed | 2026-01-30 | 2026-02-05 | #REF!
240 | 100/2 | 3DA+3 | DFR | No | Yes | Yes | Completed | 2026-01-05 | 2026-01-12 | SAI SREE VARSHINI |  |  | Yes | 36.771 | Completed | 2026-01-27 | 2026-01-31 | #REF!
241 | 100/3 | 3DA+3 | DRY | No | Yes | Yes | Completed | 2026-01-10 | 2026-01-14 | SAI SREE VARSHINI | P T E | 2026-01-25 | Yes | 36.771 | Completed
242 | 100/4 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-01-21 | 2026-01-24 | SAI SREE VARSHINI |  |  | Yes | 35.089 | Completed | 2026-03-20 | 2026-03-29 | #REF!
243 | 100/5 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-01-22 | 2026-01-27 | SAI SREE VARSHINI | C P | 2026-02-02 | Yes | 35.089 | Completed | 2026-02-08 | 2026-02-24 | #REF!
244 | 100/6 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-01-26 | 2026-02-24 | BALAJI INFRA | C P | 2026-03-07 | Yes | 35.089 | Completed | 2026-03-10 | 2026-03-16 | #REF!
245 | 100/7 | 3DA+3 | DFR | No | Yes | Yes | Completed | 2026-01-27 | 2026-02-28 | BALAJI INFRA | C P | 2026-03-07 | Yes | 36.771 | Completed | 2026-03-16 | 2026-03-23 | #REF!
246 | 100/8 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-02-12 | 2026-02-26 | BALAJI INFRA | C P | 2026-03-03 | Yes | 35.089 | Completed | 2026-03-30 | 2026-04-04 | #REF!
247 | 101/0 | 3DB1+0 | DRY | No | Yes | Yes | Completed | 2026-01-27 | 2026-01-31 | SAI SREE VARSHINI | P T E | 2026-02-01 | Yes | 54.72 | Completed | 2026-02-20 | 2026-03-03 | #REF!
248 | 101/1 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2026-01-24 | 2026-01-28 | VKP TRADERS | P T E | 2026-03-02 | Yes | 35.089 | Completed | 2026-02-16 | 2026-02-20 | #REF!
249 | 101/2 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-01-18 | 2026-01-22 | VKP TRADERS | C P | 2026-03-02 | Yes | 35.089 | Completed | 2026-02-05 | 2026-02-12 | #REF!
250 | 101/3 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2026-01-26 | 2026-01-31 | VKP TRADERS | P T E | 2026-03-02 | Yes | 35.089 | Completed | 2026-02-12 | 2026-02-16 | #REF!
251 | 101/4 | 3DA+0 | WET | No | Yes | Yes | Wip
252 | 101/5 | 3DA+0 | DRY | No | Yes | Yes | Completed | 2026-02-02 | 2026-02-14 | VKP TRADERS | P T E | 2026-03-02 | Yes | 35.089 | Completed | 2026-02-27 | 2026-03-02 | #REF!
253 | 101/6 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-02-09 | 2026-02-22 | VKP TRADERS | C P | 2026-03-03 | Yes | 35.089 | Completed | 2026-03-13 | 2026-03-16 | #REF!
254 | 101/7 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-02-16 | 2026-02-28 | VKP TRADERS | C P | 2026-03-03 | Yes | 35.089 | Completed | 2026-03-16 | 2026-03-20 | #REF!
255 | 101/8 | 3DA+0 | WET | Yes | Yes | Yes
256 | 101/9 | 3DA+0 | DFR | Yes | Yes | Yes
257 | 102/0 | 3DB2+0 | DFR | No |  | No | Wip
258 | 102/1 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-02-02 | 2026-02-14 | BALAJI INFRA | C P | 2026-02-17 | Yes | 35.089 | Completed | 2026-02-24 | 2026-02-27 | #REF!
259 | 102/2 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-02-02 | 2026-02-11 | BALAJI INFRA |  |  | Yes | 35.089 | Completed | 2026-02-20 | 2026-02-22 | #REF!
260 | 102/3 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-01-26 | 2026-02-08 | BALAJI INFRA-2 |  |  | Yes | 35.089 | Completed | 2026-02-22 | 2026-02-24 | #REF!
261 | 102/4 | 3DA+0 | DFR | No | Yes | Yes | Completed | 2026-01-22 | 2026-01-26 | BALAJI INFRA-2 | C P | 2026-02-14 | Yes | 35.089 | Completed | 2026-02-14 | 2026-02-17 | #REF!
262 | 102/5 | 3DA+0 | WFR | No | Yes | Yes | Completed | 2026-01-11 | 2026-01-31 | BALAJI INFRA-2 |  |  | Yes | 35.089 | Completed | 2026-02-15 | 2026-02-19 | #REF!
263 | 102/6 | 3DA+0 | WFR | No | Yes | Yes
264 | 103/0 | 3DB2+0 | DFR | No |  | No | [6 empty] | Yes | 54.72
265 | 103/1 | 3DA+0 | DFR | No | Yes | No
266 | 103/2 | 3DA+0 | DFR | No | Yes | No
267 | 103/3 | 3DA+6 | DFR | No | Yes | No
268 | 104/0 | 3DC1+0 | DFR | No | - | No | [6 empty] | Yes | 62.501
269 | 104/1 | 3DA+0 | WET | No | Yes | No
270 | 104/2 | 3DA+0 | WET | No | Yes | No
271 | 104/3 | 3DA+0 | DFR | No | Yes | No
272 | 104/4 | 3DA+6 | DFR | No | Yes | No
273 | 104/5 | 3DA+0 | DFR | No | Yes | No
274 | 104/6 | 3DA+0 | DFR | No | Yes | No
275 | 104/7 | 3DA+0 | DFR | No | Yes | No
276 | 104/8 | 3DA+0 | DFR | No | Yes | No
277 | 104/9 | 3DA+3 | DFR | No | Yes | No
278 | 104/10 | 3DA+6 | DFR | No | Yes | No
279 | 104/11 | 3DA+6 | DFR | No | Yes | No
280 | 105/0 | 3DB2+3 | DFR | Yes |  | No
281 | 105/1 | 3DA+0 | DFR | No | Yes | No
282 | 105/2 | 3DA+0 | DFR | No | Yes | No
283 | 105/3 | 3DA+0 | DFR | No | Yes | No
284 | 106/0 | 3DD60+3 | DFR | No | - | Yes
285 | 107/0 | 3DD60+6 | DFR | No | - | Yes
286 | 107/1 | 3DA+0 | DFR | No | Yes | No
287 | 108/0 | 3DD45+0 | DFR | No | - | No | [6 empty] | Yes | 68.265
288 | 108/1 | 3DA+0 | DRY | No | Yes | No
289 | 108/2 | 3DA+0 | DRY | No | Yes | No
290 | 109/0 | 3DB1+9 | DFR | Yes | Yes | No
291 | 110/0 | 3DD60+9 | DFR | No | - | No
292 | 111/0 | 3DD45+0 | DFR | No | - | No
Grand Total

## STRG Stretch
765KV D/C K4 - Bidar TL Package -II
Stringing Stretches | [11 empty] | Legend | FS Completed | RS Completed | WIP | Row
S.No | Section From | Section TO | LENGTH (km) | T(T) / M(M) | Total Fdns | Fdn completed | Pending Fdns | Fdn WIP | Total erection | Erection completed | Pending erection | Erection WIP | Stringing Status | Streach Ready Y/N | OPGW Status | District | POWER/ NH/ Railway crossings | 11kV | 33kV | Tree Cutting status Pending/Clear
1 | AP48 | AP49 | 3.3066 | M | 8 |  | 8 |  | 8 |  | 8 |  |  |  |  | Vikarabad
2 | AP49 | AP50 | 4.5818 | M | 12 | 4 | 8 |  | 12 |  | 12 |  |  |  |  | Vikarabad
3 | AP50 | AP51 | 1.519 | M | 4 | 4 | 0 | AP51 | 4 |  | 4 |  |  |  |  | Vikarabad
4 | AP51 | AP52 | 4.3004 | M | 11 | 6 | 5 |  | 11 | 1 | 10 |  |  | Y |  | Vikarabad
5 | AP52 | AP53 | 1.9959 | M | 5 | 2 | 3 |  | 5 | 1 | 4 |  |  |  |  | Vikarabad
6 | AP53 | AP54 | 2.7717 | M | 7 | 6 | 1 | AP53 | 7 | 4 | 3 |  |  |  |  | Vikarabad
7 | AP54 | AP55 | 0.23844 | T | 1 | 0 | 1 |  | 1 |  | 1 |  |  |  |  | Vikarabad | Railway Crossing LOC-54/0 | 1
8 | AP55 | AP56 | 1.4365 | M | 4 | 2 | 2 |  | 4 | 2 | 2 |  |  |  |  | Vikarabad | Railway Crossing LOC-55/0
9 | AP56 | AP57 | 5.2326 | M | 13 | 8 | 5 | AP56 | 13 | 7 | 6 |  |  |  |  | Vikarabad |  |  | 2
10 | AP57 | AP58 | 0.21474 | T | 1 |  | 1 |  | 1 |  | 1 |  |  |  |  | Vikarabad | Power Line Crossing LOC-57/0
11 | AP58 | AP59 | 1.5881 | M | 4 | 3 | 1 |  | 4 | 3 | 1 |  |  |  |  | Vikarabad | Power Line Crossing LOC-58/0
12 | AP59 | AP60 | 2.3158 | M | 6 | 5 | 1 |  | 6 | 4 | 2 |  |  |  |  | Vikarabad
13 | AP60 | AP61 | 3.8451 | M | 9 | 4 | 5 |  | 9 |  | 9 |  |  |  |  | Vikarabad
14 | AP61 | AP62 | 0.24749 | T | 1 |  | 1 |  | 1 |  | 1 |  |  |  |  | Vikarabad | NH Crossing LOC-61/0
15 | AP62 | AP63 | 1.82 | M | 5 |  | 5 |  | 5 |  | 5 |  |  |  |  | Vikarabad | NH Crossing LOC-62/0
16 | AP63 | AP64 | 1.6119 | M | 4 |  | 4 |  | 4 |  | 4 |  |  |  |  | Vikarabad
17 | AP64 | AP65 | 0.43905 | T | 1 |  | 1 |  | 1 |  | 1 |  |  |  |  | Vikarabad |  |  | 2
18 | AP65 | AP66 | 1.3995 | M | 4 | 1 | 3 |  | 4 |  | 4 |  |  |  |  | Vikarabad |  | 1
19 | AP66 | AP67 | 0.88682 | M | 2 | 1 | 1 |  | 2 |  | 2 |  |  |  |  | Vikarabad
20 | AP67 | AP68 | 1.8412 | M | 5 | 1 | 4 |  | 5 |  | 5 |  |  |  |  | Vikarabad
21 | AP68 | AP69 | 1.1609 | M | 3 |  | 3 |  | 3 |  | 3 |  |  |  |  | Vikarabad
22 | AP69 | AP70 | 1.2616 | M | 3 |  | 3 |  | 3 |  | 3 |  |  |  |  | Vikarabad
23 | AP70 | AP71 | 1.967 | M | 5 | 4 | 1 | AP70 | 5 |  | 5 |  |  |  |  | Vikarabad
24 | AP71 | AP72 | 0.24852 | T | 1 |  | 1 |  | 1 |  | 1 |  |  |  |  | NarayanPet | Power Line Crossing LOC-71/0
25 | AP72 | AP73 | 0.82768 | M | 2 |  | 2 |  | 2 |  | 2 |  |  |  |  | NarayanPet | Power Line Crossing LOC-72/0
26 | AP73 | AP74 | 1.2134 | M | 3 | 2 | 1 |  | 3 |  | 3 |  |  |  |  | NarayanPet
27 | AP74 | AP75 | 0.25012 | T | 1 |  | 1 |  | 1 |  | 1 |  |  |  |  | NarayanPet
28 | AP75 | AP76 | 1.6107 | M | 4 |  | 4 |  | 4 |  | 4 |  |  |  |  | NarayanPet
29 | AP76 | AP77 | 0.19645 | T | 1 |  | 1 |  | 1 |  | 1 |  | Fs completed |  |  | NarayanPet | Power Line Crossing LOC-76/0
30 | AP77 | AP78 | 4.2606 | M | 11 | 9 | 2 |  | 11 | 7 | 4 |  |  |  |  | NarayanPet | Power Line Crossing LOC-77/0
31 | AP78 | AP79 | 1.5551 | M | 4 | 1 | 3 |  | 4 |  | 4 |  |  |  |  | NarayanPet
32 | AP79 | AP80 | 1.5776 | M | 4 | 3 | 1 |  | 4 | 2 | 2 |  |  |  |  | NarayanPet
33 | AP80 | AP81 | 2.4962 | M | 6 | 3 | 3 |  | 6 | 2 | 4 |  |  |  |  | NarayanPet
34 | AP81 | AP82 | 1.6443 | M | 4 | 2 | 2 |  | 4 | 1 | 3 |  |  |  |  | NarayanPet
35 | AP82 | AP83 | 1.2808 | M | 3 | 1 | 2 |  | 3 | 1 | 2 |  |  |  |  | NarayanPet
36 | AP83 | AP84 | 1.1533 | M | 3 | 2 | 1 |  | 3 | 2 | 1 |  |  |  |  | NarayanPet
37 | AP84 | AP85 | 2.7389 | M | 7 | 6 | 1 |  | 7 | 5 | 2 |  |  |  |  | NarayanPet
38 | AP85 | AP86 | 1.8152 | M | 5 | 2 | 3 |  | 5 | 2 | 3 |  |  |  |  | NarayanPet
39 | AP86 | AP87 | 0.75885 | M | 2 |  | 2 |  | 2 |  | 2 |  |  |  |  | NarayanPet
40 | AP87 | AP88 | 0.46849 | T | 1 |  | 1 |  | 1 |  | 1 |  |  |  |  | NarayanPet
41 | AP88 | AP89 | 0.292 | T | 1 |  | 1 |  | 1 |  | 1 |  |  |  |  | NarayanPet | Power Line Crossing LOC-88/0
42 | AP89 | AP90 | 0.7625 | M | 2 | 1 | 1 |  | 2 |  | 2 |  |  |  |  | NarayanPet | Power Line Crossing LOC-89/0
43 | AP90 | AP91 | 2.4599 | M | 6 | 1 | 5 |  | 6 |  | 6 |  |  |  |  | NarayanPet
44 | AP91 | AP92 | 1.1419 | M | 3 |  | 3 |  | 3 |  | 3 |  |  |  |  | NarayanPet
45 | AP92 | AP93 | 1.2207 | M | 3 |  | 3 |  | 3 |  | 3 |  |  |  |  | NarayanPet
46 | AP93 | AP94 | 1.7272 | M | 4 |  | 4 |  | 4 |  | 4 |  |  |  |  | NarayanPet
47 | AP94 | AP95 | 1.7948 | M | 4 | 1 | 3 |  | 4 |  | 4 |  |  |  |  | NarayanPet
48 | AP95 | AP96 | 0.26546 | T | 1 |  | 1 |  | 1 |  | 1 |  |  |  |  | NarayanPet | Power Line Crossing LOC-95/0
49 | AP96 | AP97 | 3.6581 | M | 9 |  | 9 |  | 9 |  | 9 |  |  |  |  | NarayanPet | Power Line Crossing LOC-96/0
50 | AP97 | AP98 | 1.9377 | M | 5 |  | 5 |  | 5 |  | 5 |  |  |  | Completed | NarayanPet
51 | AP98 | AP99 | 2.328 | M | 6 |  | 6 |  | 6 |  | 6 |  |  |  |  | NarayanPet | NH Crossing LOC-98/0 And NH Crossing LOC-98/0 | 1
52 | AP99 | AP100 | 4.9858 | M | 13 | 7 | 6 |  | 13 | 6 | 7 |  |  |  |  | NarayanPet
53 | AP100 | AP101 | 3.6492 | M | 9 | 9 | 0 |  | 9 | 8 | 1 |  |  |  |  | NarayanPet
54 | AP101 | AP102 | 3.924 | M | 10 | 7 | 3 |  | 10 | 7 | 3 |  |  |  |  | NarayanPet
55 | AP102 | AP103 | 2.7046 | M | 7 | 5 | 2 |  | 7 | 5 | 2 |  |  |  |  | NarayanPet
56 | AP103 | AP104 | 1.5241 | M | 4 |  | 4 |  | 4 |  | 4 |  |  |  |  | NarayanPet
57 | AP104 | AP105 | 4.6981 | M | 12 |  | 12 |  | 12 |  | 12 |  |  |  |  | NarayanPet
58 | AP105 | AP106 | 1.5484 | M | 4 |  | 4 |  | 4 |  | 4 |  | Row |  |  | NarayanPet
59 | AP106 | AP107 | 0.26332 | T | 1 |  | 1 |  | 1 |  | 1 |  |  |  |  | NarayanPet | Railway Crossing LOC-106/0
60 | AP107 | AP108 | 0.78081 | M | 2 |  | 2 |  | 2 |  | 2 |  |  |  |  | NarayanPet | Railway Crossing LOC-107/0
61 | AP108 | AP109 | 1.1265 | M | 4 |  | 4 |  | 4 |  | 4 |  |  |  | Completed | NarayanPet | Power Line Crossing LOC-109/0
62 | AP109 | AP110 | 0.19463 | T | 1 |  | 1 |  | 1 |  | 1 |  |  |  | Completed | NarayanPet | Power Line Crossing LOC-110/0
63 | AP110 | AP111 | 0.20314 | T | 1 |  | 1 |  | 1 |  | 1 |  |  |  |  | NarayanPet | NH Crossing LOC-110/0 And NH Crossing LOC-111/0
| Grand Total |  | 113.2692 |  | 292 | 113 | 179 | 0 | 292 | 70 | 222 | 0 | 0 | 0 | 0 |  |  | 3 | 4 | 0
S.No | T/ M | Total Section |  | Final Sag Complted |  | Rough Sag Completed |  | Ready for STR |  | WIP |  | Row |  | Balance |  | OPGW
|  | KM | Nos | km | Nos | km | Nos | km | Nos | km | Nos | KM | Nos | KM | Nos | Completed | Balance
1 | * M | 109.7473 | 50 | 0 | 0 | 0 | 0 | 4.3004 | 1 | 0 | 0 | 1.5484 | 1 | 109.7473 | 50 | 3.0642 | 106.6832
2 | * T | 3.5218 | 13 | 0.19645 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3.3254 | 12 | 0.19463 | 3.3272
| Total | 113.2692 | 63 | 0.19645 | 1 | 0 | 0 | 4.3004 | 1 | 0 | 0 | 1.5484 | 2 | 113.0727 | 62 | 3.2588 | 110.0104
[5 empty] | District | Total Kms | Total fdns | fdns cmpld | Erc cmpld | Str Cmpld
[5 empty] | NarayanPet | 67.2871 | 174 | 62 | 48 | 0.19645
[5 empty] | Vikarabad | 45.9821 | 118 | 51 | 22 | 0
[5 empty] | Total | 113.2692 | 292 | 113 | 70 | 0.19645

## Stringing Compiled
S.no | Sec | From AP | To AP | Span (M) | Method | Section Readiness | Insulator Hoisting | P/O Starting Date | P/O Completion Date | P/O | F/S Starting Date | F/S/ Completion Date | Jumpering | Spacering | Clipping | Length | Status | Gang Name | Gang Strength | Number of Fitters | Hindrance | Remarks