## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer/Manager | PCH | Regional Manager | Project Manager | Section Incharge | Supervisor
TB-408 | 765 KV Fathegarh -3 Beawer Transmission Line, PKG F | Resonia Limited | 2023-12-06 | 2025-10-30 | Mr. Raghav Ranjan | Mr. N. K. Gupta | Mr. Rajnish Pandey | Mr. Virendra Gupta | Dev Saran Swarakar | Ganesh Singh
[8 empty] | Mr. Dhiraj Adhikari | Rajeev Kumar | Umesh Prashad
[9 empty] | Vivek Shukla | Rajesh Paul
[9 empty] | Ram Tirath Singh | Aslam Ansari
[9 empty] | Jitendra Saini | Lal Babu Patel
V Challe Durai
Vimal Chandra
Soumitra Knor
R N Yadav
Ramji Tanti
Mahesh Dhaka
Pradeep Kumar
Dineshwar Mahto
Niraj Kumar
Milan
Sonkaran Patel
Rakesh Pramanik
Jyoti Kumar
Baleswar Mahto
Sunder Lal

## Erection Compiled
SL No. | Location No. | Tower Type | Classification | Starting Date | Tower Weight | Status | Completion Date | Gang Name | Gang Strength | Number of Fitters | Tower Tightening | Remark
1 | 1/0 | DD60+0 | DRY | 2025-07-07 | 86.1293 | COMPLETED | 2025-08-20 | Bhairo Mahto+Kewat |  |  | Yes
2 | 1A/0 | DD60+0 | DRY | 2025-07-01 | 86.1293 | COMPLETED | 2025-07-29 | Bhairo Mahto+Priyanka Devi (Subodh) |  |  | Yes
3 | 1A/1 | DA+6 | DFR | 2025-01-31 | 45.413 | COMPLETED | 2025-02-10 | Bina Devi |  |  | Yes
4 | 1A/2 | DA+0 | DRY | 2025-02-11 | 37.5044 | COMPLETED | 2025-02-18 | Bina Devi |  |  | Yes
5 | 1A/3 | DA+0 | DRY | 2025-02-19 | 37.5044 | COMPLETED | 2025-02-28 | Bina Devi |  |  | Yes
6 | 1A/4 | DA+3 | DFR | 2025-05-10 | 38.8476 | COMPLETED | 2025-06-11 | Bhairo Mahto |  |  | Yes
7 | 1A/5 | DA+0 | DRY | 2025-07-10 | 37.5044 | COMPLETED | 2025-07-26 | Bhairo Mahto+Kewat |  |  | Yes
8 | 1A/6 | DA+0 | Sandy | 2025-06-11 | 37.5044 | COMPLETED | 2025-06-20 | Bhairo Mahto |  |  | Yes
9 | 1A/7 | DA+3 | Sandy | 2025-06-04 | 38.8476 | COMPLETED | 2025-06-30 | Anil Kumar+Kewat |  |  | Yes
10 | 1A/8 | DA+0 | Sandy | 2025-06-11 | 37.5044 | COMPLETED | 2025-07-15 | Anil Kumar+Kewat |  |  | Yes
11 | 2/0 | DC1+0 | DRY | 2025-07-29 | 66.3811 | COMPLETED | 2025-08-13 | Priyanka Devi (Subodh) |  |  | Yes
12 | 2/1 | DA+3 | Sandy | 2025-09-03 | 38.8476 | COMPLETED | 2025-09-13 | Sheetal Singh-1 |  |  | Yes
13 | 2/2 | DA+3 | Sandy | 2025-09-09 | 38.8476 | COMPLETED | 2025-09-22 | Priyanka Devi (Subodh) |  |  | Yes
14 | 2/3 | DA+3 | Sandy | 2025-08-04 | 38.8476 | COMPLETED | 2025-08-17 | Sheetal Singh |  |  | Yes
15 | 2/4 | DA+3 | Sandy | 2025-08-24 | 38.8476 | COMPLETED | 2025-09-09 | Sheetal Singh-2 |  |  | Yes
16 | 2/5 | DA+3 | Sandy | 2025-08-04 | 38.8476 | COMPLETED | 2025-08-19 | Usha Tower |  |  | Yes
17 | 2/6 | DA+3 | Sandy | 2025-08-24 | 38.8476 | COMPLETED | 2025-09-09 | Anvi Construction |  |  | Yes
18 | 2/7 | DA+3 | Sandy | 2025-07-23 | 38.8476 | COMPLETED | 2025-07-30 | Arawali-2 |  |  | Yes
19 | 2/8 | DA+0 | Sandy | 2025-07-11 | 37.5044 | COMPLETED | 2025-07-16 | Arawali-2 |  |  | Yes
20 | 2/9 | DA+0 | DRY | 2025-07-16 | 37.5044 | COMPLETED | 2025-07-23 | Arawali-2 |  |  | Yes
21 | 3/0 | DD60+6 | DRY | 2025-10-07 | 100.968 | COMPLETED | 2025-11-10 | Panva Devi |  |  | Yes
22 | 4/0 | DD60+6 | DRY | 2025-10-25 | 100.968 | COMPLETED | 2025-11-08 | Devi Construction |  |  | Yes
23 | 4/1 | DA+0 | DRY | 2025-07-25 | 37.5044 | COMPLETED | 2025-08-09 | Bhairo Mahto |  |  | Yes
24 | 4/2 | DA+0 | DRY | 2025-07-30 | 37.5044 | COMPLETED | 2025-08-22 | Bhairo Mahto |  |  | Yes
25 | 4/3 | DA+0 | DRY | 2025-08-29 | 37.5044 | COMPLETED | 2025-08-31 | Pusplata (Ashok) |  |  | Yes
26 | 4/4 | DA+0 | DRY | 2025-08-20 | 37.5044 | COMPLETED | 2025-08-25 | Pusplata (Ashok) |  |  | Yes
27 | 5/0 | DB1+9 | DRY | 2025-10-29 | 70.7017 | COMPLETED | 2025-11-16 | Kamlesh Kumar |  |  | Yes
28 | 6/0 | DB2+9 | DRY | 2025-11-23 | 70.7017 | COMPLETED | 2025-12-07 | Panva Devi |  |  | Yes
29 | 6/1 | DA+0 | DFR | 2025-09-25 | 37.5044 | COMPLETED | 2025-10-03 | Sheetal Singh-1 |  |  | Yes
30 | 6/2 | DA+0 | DFR | 2025-09-05 | 37.5044 | COMPLETED | 2025-09-12 | Usha Tower |  |  | Yes
31 | 7/0 | DB1+0 | DRY | 2025-11-19 | 57.5972 | COMPLETED | 2025-11-28 | Devi Construction |  |  | Yes
32 | 8/0 | DB1+0 | DRY | 2025-11-09 | 57.5972 | COMPLETED | 2025-11-18 | Devi Construction |  |  | Yes
33 | 8/1 | DA+3 | DRY | 2025-08-23 | 38.8476 | COMPLETED | 2025-08-31 | Bhairo Mahto |  |  | Yes
34 | 8/2 | DA+3 | DRY | 2025-09-12 | 38.8476 | COMPLETED | 2025-09-23 | Bhairo Mahto |  |  | Yes
35 | 8/3 | DA+0 | DRY | 2025-11-10 | 37.5044 | COMPLETED | 2025-11-27 | Priyanka Devi |  |  | Yes
36 | 8/4 | DA+3 | DRY | 2025-08-29 | 38.8476 | COMPLETED | 2025-09-04 | Jwala Singh |  |  | Yes
37 | 8/5 | DA+3 | DRY | 2025-09-12 | 38.8476 | COMPLETED | 2025-09-18 | Jwala Singh-2 |  |  | Yes
38 | 8/6 | DA+3 | DRY | 2026-02-17 | 38.8476 | COMPLETED | 2026-02-27 | Shobha Devi |  |  | Yes
39 | 8/7 | DB1+0 | DRY | 2026-02-25 | 57.5972 | COMPLETED | 2026-03-07 | Sunny Construction |  |  | Yes
40 | 8/8 | DA+6 | DRY | 2026-02-17 | 45.413 | COMPLETED | 2026-02-22 | Shobha Devi |  |  | Yes
41 | 8/9 | DA+3 | DFR | 2025-06-27 | 38.8476 | COMPLETED | 2025-07-01 | Jwala Singh |  |  | Yes
42 | 8/10 | DA+3 | DFR | 2025-07-07 | 38.8476 | COMPLETED | 2025-07-19 | Jwala Singh |  |  | Yes
43 | 8/11 | DA+0 | DRY | 2026-02-19 | 37.5044 | COMPLETED | 2026-02-24 | Sunny Construction |  |  | Yes
44 | 8/12 | DA+0 | DRY | 2025-08-04 | 37.5044 | COMPLETED | 2025-08-09 | Jwala Singh |  |  | Yes
45 | 9/0 | DD60+18 | DRY | 2025-12-02 | 129.111 | COMPLETED | 2025-12-22 | Devi Construction |  |  | Yes
46 | 10/0 | DD60+25 | DFR | 2026-03-02 | 143.6019 | COMPLETED | 2026-03-25 | Shobha Devi |  |  | Yes
47 | 10/1 | DA+0 | DRY | 2025-10-03 | 37.5044 | COMPLETED | 2025-10-10 | Priyanka Devi (Subodh) |  |  | Yes
48 | 10/2 | DA+0 | DFR | 2026-02-16 | 37.5044 | COMPLETED | 2026-02-19 | Sunny Construction |  |  | Yes
49 | 10/3 | DA+0 | DFR | 2024-08-28 | 37.5044 | COMPLETED | 2024-09-06 | Jagdish Mahto |  |  | Yes
50 | 10/4 | DA+3 | DFR | 2024-10-12 | 38.8476 | COMPLETED | 2024-10-17 | Jagdish Mahto |  |  | Yes
51 | 10/5 | DA+3 | DRY | 2025-12-25 | 38.8476 | COMPLETED | 2025-12-31 | Devi Construction |  |  | Yes
52 | 10/6 | DA+0 | DFR | 2024-09-25 | 37.5044 | COMPLETED | 2024-09-29 | Jagdish Mahto |  |  | Yes
53 | 10/7 | DA+3 | DRY | 2025-11-28 | 38.8476 | COMPLETED | 2025-12-06 | Priyanka Devi |  |  | Yes
54 | 10/8 | DA+3 | DFR | 2024-10-19 | 38.8476 | COMPLETED | 2024-10-22 | Jagdish Mahto |  |  | Yes
55 | 10/9 | DA+0 | DRY | 2024-10-05 | 37.5044 | COMPLETED | 2024-10-08 | Jagdish Mahto |  |  | Yes
56 | 10/10 | DA+3 | Sandy | 2025-12-07 | 38.8476 | COMPLETED | 2025-12-14 | Priyanka Devi |  |  | Yes
57 | 10/11 | DA+3 | DRY | 2024-11-02 | 38.8476 | COMPLETED | 2024-11-05 | Jagdish Mahto |  |  | Yes
58 | 10/12 | DB1+0 | DRY | 2024-11-30 | 57.5972 | COMPLETED | 2024-12-11 | Jagdish Mahto |  |  | Yes
59 | 10/13 | DA+3 | DRY | 2025-12-15 | 38.8476 | COMPLETED | 2025-12-27 | Kamlesh Kumar |  |  | Yes
60 | 10/14 | DA+3 | DRY | 2024-09-27 | 38.8476 | COMPLETED | 2024-10-06 | Khublal Mahto |  |  | Yes
61 | 10/15 | DA+3 | DRY | 2025-12-03 | 38.8476 | COMPLETED | 2025-12-14 | Kamlesh Kumar |  |  | Yes
62 | 10/16 | DA+3 | DRY | 2025-11-17 | 38.8476 | COMPLETED | 2025-11-30 | Kamlesh Kumar |  |  | Yes
63 | 10/17 | DA+3 | DFR | 2024-08-30 | 38.8476 | COMPLETED | 2024-09-08 | Yogendra Mahto |  |  | Yes
64 | 10/18 | DA+3 | DFR | 2024-08-23 | 38.8476 | COMPLETED | 2024-08-30 | Yogendra Mahto |  |  | Yes
65 | 10/19 | DA+0 | DRY | 2024-09-09 | 37.5044 | COMPLETED | 2024-09-18 | Yogendra Mahto |  |  | Yes
66 | 10/20 | DA+3 | DFR | 2024-09-19 | 38.8476 | COMPLETED | 2024-09-25 | Yogendra Mahto |  |  | Yes
67 | 10/21 | DA+3 | DFR | 2024-10-07 | 38.8476 | COMPLETED | 2024-10-10 | Bina Devi |  |  | Yes
68 | 10/22 | DA+0 | Sandy | 2025-10-04 | 37.5044 | COMPLETED | 2025-12-10 | Vedanta Construction |  |  | Yes
69 | 10/23 | DA+0 | Sandy | 2025-12-11 | 37.5044 | COMPLETED | 2025-12-17 | Vedanta Construction |  |  | Yes
70 | 11/0 | DB1+0 | Sandy | 2025-11-25 | 57.5972 | COMPLETED | 2025-12-31 | Nirmal Mahto |  |  | Yes |  | 3 | [14 empty] | 3 | 2 | 2 | 1 | 1 | 4 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 2 | 1 | 3
71 | 11/1 | DA+0 | Sandy | 2025-12-05 | 37.5044 | COMPLETED | 2025-12-12 | Nirmal Mahto |  |  | Yes
72 | 11/2 | DA+0 | Sandy | 2025-12-12 | 37.5044 | COMPLETED | 2025-12-18 | Nirmal Mahto |  |  | Yes
73 | 11/3 | DA+0 | Sandy | 2025-12-18 | 37.5044 | COMPLETED | 2025-12-25 | Nirmal Mahto |  |  | Yes
74 | 11/4 | DA+0 | Sandy | 2025-10-17 | 37.5044 | COMPLETED | 2025-10-24 | Devi Construction |  |  | Yes
75 | 11/5 | DA+0 | DFR | 2024-11-10 | 37.5044 | COMPLETED | 2024-11-18 | Rafikul Islam |  |  | Yes |  | 3 | 1 | 7 | 2 | 6 | 1 | 6 | 5 | 2 | 1 | [20 empty] | 1
76 | 11A/0 | DB1+0 | DRY | 2024-10-16 | 57.5972 | COMPLETED | 2024-11-02 | Rafikul Islam |  |  | Yes |  | 1 | 2 | 2 | 3 | 17 | 6 | 3 | 15 | 2 | 1 | 9 | 2
77 | 11A/1 | DA+3 | DRY | 2024-10-18 | 38.8476 | COMPLETED | 2024-11-08 | Rafikul Islam |  |  | Yes |  |  |  | 5.91 | 8.93 | 9.52 | 1.67 | 1.87
78 | 11A/2 | DA+0 | DRY | 2024-09-27 | 37.5044 | COMPLETED | 2024-10-07 | Rafikul Islam |  |  | Yes
79 | 11A/3 | DA+3 | DRY | 2024-12-01 | 38.8476 | COMPLETED | 2024-12-07 | Deglal Mahto |  |  | Yes
80 | 11A/4 | DA+3 | DRY | 2026-02-25 | 38.8476 | COMPLETED | 2026-03-16 | Chinta Devi |  |  | Yes | [9 empty] | 1 | 2 | 10 | 13 | 3
81 | 11A/5 | DA+3 | DRY | 2024-12-25 | 38.8476 | COMPLETED | 2025-01-04 | Deglal Mahto |  |  | Yes
82 | 11A/6 | DA+6 | DRY | 2024-12-09 | 45.413 | COMPLETED | 2024-12-16 | Deglal Mahto |  |  | Yes | [12 empty] | 3.88 | 3.74 | 2.37 | 2.87 | 4.33 | 1.63 | 3.32 | 4.2 | 1.91 | 0.98 | 4.07
83 | 11A/7 | DA+9 | Sandy | 2024-11-28 | 47.1844 | COMPLETED | 2024-12-06 | Jailal Ageria |  |  | Yes | [14 empty] | 5.56 | 6.8 | 8.93 | 2.19 | 2.48 | 2.29 | 5.28 | 6.24 | 3.45 | 3.31 | 3.19 | 1.98
84 | 11A/8 | DA+6 | Sandy | 2025-12-05 | 45.413 | COMPLETED | 2025-12-16 | Sheetal Singh |  |  | Yes | [16 empty] | 17 | 15 | 4 | 3 | 2 | 14 | 1 | 4
85 | 11A/9 | DA+3 | DRY | 2024-11-24 | 38.8476 | COMPLETED | 2024-11-30 | Deglal Mahto |  |  | Yes
86 | 12/0 | DD60+0 | DRY | 2025-07-25 | 86.1293 | COMPLETED | 2025-08-02 | Arawali-1 |  |  | Yes
87 | 13/0 | DD60+3 | DRY | 2026-02-25 | 89.9096 | COMPLETED | 2026-03-05 | Chinta Devi |  |  | No
88 | 13/1 | DA+9 | DRY | 2025-12-13 | 47.1844 | COMPLETED | 2025-12-18 | Santosh Singh / Laxmi |  |  | Yes
89 | 13/2 | DA+3 | DRY | 2024-11-11 | 38.8476 | COMPLETED | 2024-11-18 | Jailal Ageria |  |  | Yes
90 | 13/3 | DA+3 | Sandy | 2025-12-16 | 38.8476 | COMPLETED | 2025-12-23 | Vivek Ganju |  |  | Yes
91 | 13/4 | DA+3 | DRY | 2025-12-24 | 38.8476 | COMPLETED | 2025-12-30 | Vivek Ganju |  |  | Yes
92 | 14/0 | DC2+0 | Sandy | 2025-12-17 | 66.3811 | COMPLETED | 2025-12-31 | Sheetal Singh |  |  | Yes
93 | 14A/0 | DC1+0 | DRY | 2025-08-26 | 66.3811 | COMPLETED | 2025-09-03 | Pusplata (Santosh/Pankaj Singh) |  |  | Yes
94 | 14A/1 | DA+3 | DRY | 2024-09-28 | 38.8476 | COMPLETED | 2024-10-03 | Jailal Ageria |  |  | Yes
95 | 14A/2 | DA+0 | DRY | 2026-01-03 | 37.5044 | COMPLETED | 2026-01-14 | Sheetal Singh |  |  | No
96 | 15/0 | DC1+0 | DRY | 2026-03-26 | 66.3811 | COMPLETED | 2026-03-31 | Shobha Devi |  |  | Yes
97 | 15/1 | DA+3 | DRY | 2024-09-21 | 38.8476 | COMPLETED | 2024-09-26 | Jailal Ageria |  |  | Yes
98 | 16/0 | DC1+0 | DRY | 2024-10-18 | 66.3811 | COMPLETED | 2024-10-27 | Jailal Ageria |  |  | Yes
99 | 16/1 | DA+0 | DRY | 2024-11-05 | 37.5044 | COMPLETED | 2024-11-09 | Jailal Ageria |  |  | Yes
100 | 16/2 | DA+0 | DRY | 2024-10-20 | 37.5044 | COMPLETED | 2024-10-26 | Nirmal Mahto |  |  | Yes
101 | 16/3 | DA+3 | DRY | 2024-09-06 | 38.8476 | COMPLETED | 2024-09-13 | Nirmal Mahto |  |  | Yes
102 | 16/4 | DA+0 | DRY | 2024-09-28 | 37.5044 | COMPLETED | 2024-10-03 | Nirmal Mahto |  |  | Yes
103 | 16/5 | DA+3 | DRY | 2024-11-03 | 38.8476 | COMPLETED | 2024-11-09 | Bina Devi |  |  | Yes
104 | 17/0 | DB2+3 | DRY | 2024-11-04 | 60.0968 | COMPLETED | 2024-11-14 | Nirmal Mahto |  |  | Yes
105 | 17/1 | DA+3 | DRY | 2024-10-05 | 38.8476 | COMPLETED | 2024-10-10 | Nirmal Mahto |  |  | Yes
106 | 17/2 | DA+6 | DRY | 2024-10-11 | 45.413 | COMPLETED | 2024-10-19 | Nirmal Mahto |  |  | Yes
107 | 17/3 | DA+0 | DRY | 2024-10-21 | 37.5044 | COMPLETED | 2024-10-27 | Bina Devi |  |  | Yes
108 | 17/4 | DA+3 | DRY | 2025-08-13 | 38.8476 | COMPLETED | 2025-08-18 | Pusplata_Pankaj |  |  | Yes
109 | 17/5 | DA+3 | DRY | 2024-11-22 | 38.8476 | COMPLETED | 2024-11-30 | Bina Devi |  |  | Yes
110 | 18/0 | DC2+0 | DRY | 2025-08-18 | 66.3811 | COMPLETED | 2025-08-25 | Pusplata |  |  | Yes
111 | 18/1 | DA+0 | DRY | 2024-10-04 | 37.5044 | COMPLETED | 2024-10-08 | Deglal Mahto |  |  | Yes
112 | 18/2 | DA+0 | DRY | 2024-09-18 | 37.5044 | COMPLETED | 2024-09-22 | Deglal Mahto |  |  | Yes
113 | 18/3 | DA+0 | DRY | 2025-07-14 | 37.5044 | COMPLETED | 2025-07-23 | Priyanka Devi-2 |  |  | Yes
114 | 18/4 | DA+0 | DRY | 2024-09-23 | 37.5044 | COMPLETED | 2024-09-27 | Deglal Mahto |  |  | No
115 | 19/0 | DC2+0 | DRY | 2024-10-19 | 66.3811 | COMPLETED | 2024-10-26 | Deglal Mahto |  |  | No
116 | 19/1 | DA+0 | DRY | 2025-12-31 | 37.5044 | COMPLETED | 2026-01-07 | Vedanta Construction |  |  | No
117 | 19/2 | DA+0 | DRY | 2025-10-20 | 37.5044 | COMPLETED | 2025-10-31 | Shri Shyam Construction |  |  | Yes
118 | 19/3 | DA+0 | DRY | 2025-12-25 | 37.5044 | COMPLETED | 2025-12-30 | Vedanta Construction |  |  | No
119 | 19/4 | DA+0 | DRY | 2025-12-19 | 37.5044 | COMPLETED | 2025-12-24 | Vedanta Construction |  |  | Yes
120 | 19/5 | DA+0 | DRY | 2025-08-01 | 37.5044 | COMPLETED | 2025-08-05 | Priyanka Devi |  |  | Yes
121 | 20/0 | DB2+0 | Sandy | 2025-09-20 | 57.5972 | COMPLETED | 2025-09-29 | Priyanka Devi (Sontosh) |  |  | No
122 | 20/1 | DA+0 | Sandy | Balance | 37.5044 | COMPLETED |  | Yet to attend |  |  | No
123 | 20/2 | DA+0 | DRY | 2025-09-02 | 37.5044 | COMPLETED | 2025-09-07 | Priyanka Devi (Sudheer) |  |  | Yes
124 | 20/3 | DA+0 | DRY | 2025-08-26 | 37.5044 | COMPLETED | 2025-09-03 | Priyanka Devi (Santosh) |  |  | No
125 | 21/0 | DB2+0 | DRY | 2025-09-02 | 57.5972 | COMPLETED | 2025-09-05 | Sudheer-2 (Priyanka Devi) |  |  | No
126 | 21/1 | DA+6 | DRY | Balance | 45.413 | COMPLETED |  | Yet to attend |  |  | No
127 | 21/2 | DA+0 | Sandy | 2026-03-28 | 37.5044 | COMPLETED | 2026-03-31 | Sunny Construction |  |  | No
128 | 21/3 | DA+6 | Sandy | 2025-09-10 | 45.413 | COMPLETED | 2025-09-30 | Shri Shyam Construction |  |  | Yes
129 | 21/4 | DA+3 | Sandy | 2025-09-09 | 38.8476 | COMPLETED | 2025-09-12 | Priyanka Devi (Sudheer) |  |  | No
130 | 21/5 | DA+6 | DFR | 2025-09-19 | 45.413 | COMPLETED | 2025-09-22 | Priyanka Devi (Sudheer) |  |  | No
131 | 21/6 | DA+3 | DRY | Balance | 38.8476 | COMPLETED |  | Yet to attend |  |  | No
132 | 21/7 | DA+3 | DFR | 2026-04-16 | 38.8476 | COMPLETED | 2026-04-27 | Shobha Devi |  |  | No
133 | 21/8 | DA+6 | DRY | 2026-03-26 | 45.413 | COMPLETED | 2026-03-31 | Chinta Devi |  |  | No
134 | 21/9 | DA+3 | DFR | 2026-03-18 | 38.8476 | COMPLETED | 2026-03-26 | Chinta Devi |  |  | No
135 | 21/10 | DA+6 | DRY | 2026-04-10 | 45.413 | COMPLETED | 2026-04-20 | Sunny Construction |  |  | No
136 | 22/0 | DB2+3 | DRY | Balance | 60.0968 | COMPLETED |  | Yet to attend |  |  | No
137 | 22/1 | DA+9 | Sandy | 2026-04-11 | 47.1844 | COMPLETED | 2026-04-20 | Chinta Devi |  |  | No
138 | 22/2 | DA+6 | Sandy | 2025-12-23 | 45.413 | COMPLETED | 2025-12-31 | Vinay Gupta |  |  | No
139 | 22/3 | DA+9 | Sandy | 2026-01-03 | 47.1844 | COMPLETED | 2026-01-09 | Sunny Construction |  |  | No
140 | 22/4 | DA+9 | Sandy | Balance | 47.1844 | COMPLETED |  | Yet to attend |  |  | No
141 | 22/5 | DA+9 | DRY | 2025-12-27 | 47.1844 | COMPLETED | 2025-12-31 | Sunny Construction |  |  | No
142 | 22/6 | DA+0 | Sandy | 2025-12-21 | 37.5044 | COMPLETED | 2025-12-26 | Sunny Construction |  |  | No
143 | 22/7 | DA+0 | Sandy | 2025-12-16 | 37.5044 | COMPLETED | 2025-12-21 | Sunny Construction |  |  | Yes
144 | 22/8 | DB1+0 | Sandy | 2026-02-16 | 57.5972 | COMPLETED | 2026-02-28 | Sheetal Singh |  |  | No
145 | 22/9 | DA+6 | Sandy | 2026-03-18 | 45.413 | COMPLETED | 2026-03-27 | Sunny Construction |  |  | No
146 | 22/10 | DA+6 | Sandy | 2026-03-11 | 45.413 | COMPLETED | 2026-03-16 | Sunny Construction |  |  | Yes
147 | 22/11 | DA+6 | Sandy | 2025-12-27 | 45.413 | COMPLETED | 2025-12-31 | Shobha Devi |  |  | Yes
148 | 22/12 | DA+3 | Sandy | 2026-04-23 | 38.8476 | COMPLETED | 2026-05-04 | Sunny Construction |  |  | No
149 | 22/13 | DA+6 | Sandy | 2026-01-03 | 45.413 | COMPLETED | 2026-01-09 | Shobha Devi |  |  | Yes
150 | 23/0 | DD45+3 | DRY | WIP | 89.9096 | COMPLETED |  | Chinta Devi | 36 | 16 | No
151 | 24/0 | DD45+3 | DRY | 2025-08-26 | 89.9096 | COMPLETED | 2025-09-07 | Pusplata (Praphul) |  |  | Yes
152 | 25/0 | DC1+6 | DRY | 2026-01-22 | 78.132 | COMPLETED | 2026-01-30 | Chinta Devi |  |  | No
153 | 25/1 | DA+3 | DRY | 2026-01-14 | 38.8476 | COMPLETED | 2026-01-18 | Chinta Devi |  |  | Yes
154 | 25/2 | DA+0 | DRY | 2026-01-06 | 37.5044 | COMPLETED | 2026-01-13 | Chinta Devi |  |  | Yes
155 | 25/3 | DA+0 | Sandy | 2025-07-31 | 37.5044 | COMPLETED | 2025-08-09 | Pusplata (Praful) |  |  | No
156 | 25/4 | DA+0 | Sandy | 2025-07-27 | 37.5044 | COMPLETED | 2025-07-31 | Pusplata (Praful) |  |  | Yes
157 | 26/0 | DB1+0 | DFR | 2025-08-26 | 57.5972 | COMPLETED | 2025-09-06 | Pusplata (rajaram) |  |  | Yes
158 | 26/1 | DA+0 | DRY | 2025-09-07 | 37.5044 | COMPLETED | 2025-09-16 | Pusplata (rajaram) |  |  | No
159 | 26/2 | DA+3 | DFR | 2025-07-21 | 38.8476 | COMPLETED | 2025-07-24 | Hazarilal Yadav-Poonam Kumari |  |  | No
160 | 26/3 | DA+0 | DRY | 2025-07-25 | 37.5044 | COMPLETED | 2025-07-28 | Hazarilal Yadav-Poonam Kumari |  |  | No
161 | 26/4 | DA+6 | Sandy | 2026-01-30 | 45.413 | COMPLETED | 2026-02-06 | Chinta Devi |  |  | Yes
162 | 26/5 | DA+6 | Sandy | 2025-11-21 | 45.413 | COMPLETED | 2025-11-27 | Chinta Devi |  |  | No
163 | 26/6 | DA+6 | Sandy | 2025-12-03 | 45.413 | COMPLETED | 2026-01-11 | Chinta Devi |  |  | No
164 | 26/7 | DA+0 | DFR | 2025-12-07 | 37.5044 | COMPLETED | 2025-12-11 | Chinta Devi |  |  | Yes
165 | 26/8 | DA+6 | DFR | 2025-11-26 | 45.413 | COMPLETED | 2025-11-30 | Ganesh Sinha |  |  | Yes
166 | 27/0 | DC1+0 | DFR | 2025-08-23 | 66.3811 | COMPLETED | 2025-09-03 | Pusplata (Dharamveer) |  |  | No
167 | 27/1 | DA+3 | DFR | 2025-08-16 | 38.8476 | COMPLETED | 2025-08-23 | Pusplata (Dharamveer) |  |  | Yes
168 | 27/2 | DA+3 | DFR | 2025-07-21 | 38.8476 | COMPLETED | 2025-07-31 | Dharmendra-Munnilal (Pusplata) |  |  | Yes
169 | 27/3 | DA+3 | DFR | 2025-07-27 | 38.8476 | COMPLETED | 2025-07-31 | Pusplata (Kailash) |  |  | Yes
170 | 27/4 | DA+3 | DFR | 2025-08-09 | 38.8476 | COMPLETED | 2025-08-17 | Pusplata (Ramchandra) |  |  | Yes
171 | 27/5 | DA+0 | DRY | 2025-11-08 | 37.5044 | COMPLETED | 2025-11-30 | Dular chand Patel |  |  | Yes
172 | 27/6 | DA+0 | Sandy | 2025-12-04 | 37.5044 | COMPLETED | 2026-01-05 | Dular chand Patel |  |  | Yes
173 | 27/7 | DB1+0 | DFR | 2025-12-12 | 57.5972 | COMPLETED | 2025-12-20 | Chinta Devi |  |  | Yes
174 | 27/8 | DA+0 | DFR | 2025-11-18 | 37.5044 | COMPLETED | 2025-11-26 | Jirwa Devi |  |  | Yes
175 | 27/9 | DA+0 | DFR | 2025-12-13 | 37.5044 | COMPLETED | 2025-12-19 | Ganesh Sinha |  |  | No
176 | 27/10 | DA+3 | DFR | 2025-12-28 | 38.8476 | COMPLETED | 2026-01-07 | Ganesh Sinha |  |  | Yes
177 | 27/11 | DA+3 | DRY | 2025-08-29 | 38.8476 | COMPLETED | 2025-09-26 | Pusplata (Ramchandra) |  |  | Yes
178 | 27/12 | DA+3 | Sandy | 2025-11-27 | 38.8476 | COMPLETED | 2025-12-04 | Jirwa Devi |  |  | Yes
179 | 28/0 | DB2+0 | DFR | 2025-09-03 | 57.5972 | COMPLETED | 2025-09-12 | Jwala Singh-1 |  |  | Yes
180 | 28/1 | DA+0 | DRY | 2025-11-10 | 37.5044 | COMPLETED | 2025-11-17 | Chinta Devi |  |  | Yes
181 | 28/2 | DA+0 | DFR | 2025-08-19 | 37.5044 | COMPLETED | 2025-08-25 | Jwala Singh |  |  | Yes
182 | 28/3 | DA+0 | DFR | 2025-12-21 | 37.5044 | COMPLETED | 2025-12-24 | Chinta Devi |  |  | No
183 | 28/4 | DA+0 | Sandy | 2025-12-21 | 37.5044 | COMPLETED | 2025-12-27 | Ganesh Sinha |  |  | No
184 | 28/5 | DA+9 | Sandy | 2025-08-12 | 47.1844 | COMPLETED | 2025-08-19 | Jwala Singh |  |  | Yes
185 | 28/6 | DA+6 | Sandy | 2025-12-29 | 45.413 | COMPLETED | 2026-01-08 | Jirwa Devi |  |  | Yes
186 | 28/7 | DA+3 | Sandy | 2025-12-10 | 38.8476 | COMPLETED | 2025-12-20 | Panva Devi |  |  | Yes
187 | 28/8 | DA+3 | Sandy | 2025-12-21 | 38.8476 | COMPLETED | 2025-12-28 | Panva Devi |  |  | Yes
188 | 29/0 | DB1+0 | DRY | 2025-07-30 | 57.5972 | COMPLETED | 2025-08-12 | Jwala Singh |  |  | Yes
189 | 29/1 | DA+3 | DRY | 2025-07-30 | 38.8476 | COMPLETED | 2025-08-04 | Jwala Singh |  |  | No
190 | 29/2 | DA+3 | DRY | 2025-11-10 | 38.8476 | COMPLETED | 2025-11-13 | Chinta Devi |  |  | Yes
191 | 29/3 | DA+0 | Sandy | 2025-09-10 | 37.5044 | COMPLETED | 2025-09-23 | Jwala Singh-1 |  |  | No
192 | 29/4 | DA+6 | DRY | 2025-10-13 | 45.413 | COMPLETED | 2025-10-23 | Jirwa Devi |  |  | Yes
193 | 30/0 | DC1+0 | DRY | 2025-11-14 | 66.3811 | COMPLETED | 2025-11-26 | Ganesh Sinha |  |  | No
194 | 30/1 | DA+0 | Sandy | 2025-08-25 | 37.5044 | COMPLETED | 2025-08-30 | Pusplata (Deepak) |  |  | Yes
195 | 30/2 | DA+0 | Sandy | 2025-09-30 | 37.5044 | COMPLETED | 2025-10-12 | Jirwa Devi |  |  | Yes
196 | 30/3 | DA+3 | Sandy | 2025-08-01 | 38.8476 | COMPLETED | 2025-08-06 | Pusplata (Kailash) |  |  | Yes
197 | 30/4 | DA+3 | DRY | 2025-12-26 | 38.8476 | COMPLETED | 2025-12-30 | Chinta Devi |  |  | Yes
198 | 30/5 | DA+3 | DRY | 2025-08-06 | 38.8476 | COMPLETED | 2025-08-17 | Pusplata (Kailash) |  |  | Yes
199 | 30/6 | DA+0 | DRY | 2025-08-17 | 37.5044 | COMPLETED | 2025-08-21 | Pusplata (Kailash) |  |  | Yes
200 | 31/0 | DB2+0 | Sandy | 2025-12-16 | 57.5972 | COMPLETED | 2025-12-20 | Jirwa Devi |  |  | Yes
201 | 31/1 | DA+0 | DRY | 2025-08-22 | 37.5044 | COMPLETED | 2025-08-26 | Pusplata (Kailash) |  |  | Yes
202 | 31/2 | DA+0 | DRY | 2025-08-26 | 37.5044 | COMPLETED | 2025-09-02 | Pusplata (Kailash) |  |  | Yes
203 | 32/0 | DC1+0 | DRY | 2025-11-08 | 66.3811 | COMPLETED | 2025-11-18 | Jirwa Devi |  |  | Yes
204 | 32/1 | DA+3 | Sandy | 2025-09-03 | 38.8476 | COMPLETED | 2025-09-10 | Pusplata (Kailash) |  |  | Yes
205 | 32/2 | DA+3 | DRY | 2025-11-08 | 38.8476 | COMPLETED | 2025-11-13 | Ganesh Sinha |  |  | Yes
206 | 32/3 | DA+0 | Sandy | 2025-10-31 | 37.5044 | COMPLETED | 2025-11-07 | Ganesh Sinha |  |  | Yes
207 | 32/4 | DA+0 | Sandy | 2025-11-11 | 37.5044 | COMPLETED | 2025-11-18 | Santosh Singh |  |  | Yes
208 | 33/0 | DC1+0 | DRY | 2025-10-22 | 66.3811 | COMPLETED | 2025-11-08 | Santosh Singh |  |  | Yes
209 | 33/1 | DA+0 | DRY | 2025-11-05 | 37.5044 | COMPLETED | 2025-11-11 | Sanjeev Kumar |  |  | Yes
210 | 34/0 | DB2+0 | DRY | 2025-11-22 | 57.5972 | COMPLETED | 2025-12-05 | Sanjeev Kumar |  |  | Yes
211 | 34/1 | DA+9 | Sandy | 2025-10-31 | 47.1844 | COMPLETED | 2025-11-07 | Nirmal Mahto |  |  | Yes
212 | 34/2 | DA+6 | Sandy | 2025-11-11 | 45.413 | COMPLETED | 2025-11-21 | Sanjeev Kumar |  |  | Yes
213 | 34/3 | DA+0 | Sandy | 2025-09-03 | 37.5044 | COMPLETED | 2025-09-11 | Satyam Enterprises (Vijay) |  |  | Yes
214 | 34/4 | DA+0 | Sandy | 2025-10-27 | 37.5044 | COMPLETED | 2025-11-04 | Sanjeev Kumar |  |  | Yes
215 | 35/0 | DB2+6 | Sandy | 2025-10-16 | 67.8737 | COMPLETED | 2025-10-26 | Sanjeev Kumar |  |  | Yes
216 | 35/1 | DA+9 | Sandy | 2025-10-22 | 47.1844 | COMPLETED | 2025-10-31 | Nirmal Mahto |  |  | Yes
217 | 35/2 | DB1+0 | Sandy | 2025-10-14 | 57.5972 | COMPLETED | 2025-10-22 | Nirmal Mahto |  |  | Yes
218 | 35/3 | DB1+6 | Sandy | 2025-12-13 | 67.8737 | COMPLETED | 2025-12-19 | Shobha Devi |  |  | Yes
219 | 35/4 | DA+0 | DRY | 2025-10-07 | 37.5044 | COMPLETED | 2025-10-13 | Nirmal Mahto |  |  | Yes
220 | 35/5 | DA+0 | Sandy | 2025-09-27 | 37.5044 | COMPLETED | 2025-10-06 | Nirmal Mahto |  |  | Yes
221 | 36/0 | DB2+0 | Sandy | 2025-09-16 | 57.5972 | COMPLETED | 2025-09-27 | Nirmal Mahto |  |  | Yes
222 | 36/1 | DA+3 | Sandy | 2025-08-29 | 38.8476 | COMPLETED | 2025-09-16 | Nirmal Mahto |  |  | Yes
223 | 36/2 | DA+0 | Sandy | 2025-08-22 | 37.5044 | COMPLETED | 2025-08-30 | Ganesh Sinha |  |  | Yes
224 | 36/3 | DA+0 | Sandy | 2025-08-30 | 37.5044 | COMPLETED | 2025-09-06 | Ganesh Sinha |  |  | Yes
225 | 36/4 | DA+6 | Sandy | 2025-09-07 | 45.413 | COMPLETED | 2025-09-16 | Ganesh Sinha |  |  | Yes
226 | 37/0 | DB2+0 | Sandy | 2025-09-16 | 57.5972 | COMPLETED | 2025-09-27 | Ganesh Sinha |  |  | Yes
227 | 37/1 | DA+9 | Sandy | 2025-10-10 | 47.1844 | COMPLETED | 2025-10-17 | Ganesh Sinha |  |  | No
228 | 37/2 | DA+3 | Sandy | 2025-10-18 | 38.8476 | COMPLETED | 2025-10-24 | Ganesh Sinha |  |  | No
229 | 37/3 | DA+0 | Sandy | 2025-10-25 | 37.5044 | COMPLETED | 2025-10-30 | Ganesh Sinha |  |  | No
230 | 38/0 | DB2+6 | Sandy | 2025-10-27 | 67.8737 | COMPLETED | 2025-10-31 | Shobha Devi |  |  | Yes
231 | 38/1 | DA+0 | Sandy | 2025-12-07 | 37.5044 | COMPLETED | 2025-12-12 | Shobha Devi |  |  | Yes
232 | 38/2 | DA+6 | Sandy | 2025-11-18 | 45.413 | COMPLETED | 2025-11-22 | Shobha Devi |  |  | Yes
233 | 38/3 | DA+9 | Sandy | 2025-10-09 | 47.1844 | COMPLETED | 2025-11-07 | Shobha Devi |  |  | Yes
234 | 38/4 | DA+9 | Sandy | 2025-10-22 | 47.1844 | COMPLETED | 2025-10-26 | Shobha Devi |  |  | Yes
235 | 39/0 | DB2+6 | Sandy | 2025-10-14 | 67.8737 | COMPLETED | 2025-10-18 | Shobha Devi |  |  | Yes
236 | 39/1 | DA+0 | Sandy | 2025-10-18 | 37.5044 | COMPLETED | 2025-10-22 | Shobha Devi |  |  | Yes
237 | 40/0 | DC2+0 | Sandy | 2025-09-29 | 66.3811 | COMPLETED | 2025-10-08 | Shobha Devi |  |  | Yes
238 | 40/1 | DA+6 | Sandy | 2025-11-01 | 45.413 | COMPLETED | 2025-11-06 | Shobha Devi |  |  | Yes
239 | 40/2 | DA+3 | Sandy | 2025-08-18 | 38.8476 | COMPLETED | 2025-08-24 | Rahul Kumar |  |  | Yes
240 | 40/3 | DA+3 | Sandy | 2025-08-10 | 38.8476 | COMPLETED | 2025-08-17 | Rahul Kumar |  |  | Yes
241 | 41/0 | DC1+6 | Sandy | 2025-11-23 | 78.132 | COMPLETED | 2025-11-30 | Shobha Devi |  |  | Yes
242 | 41/1 | DB1+9 | Sandy | 2025-08-10 | 70.7017 | COMPLETED | 2025-08-21 | Gauri Shankar |  |  | Yes
243 | 41/2 | DA+0 | Sandy | 2025-10-10 | 37.5044 | COMPLETED | 2025-10-27 | Vinay Construction |  |  | Yes
244 | 42/0 | DC1+0 | Sandy | 2025-10-27 | 66.3811 | COMPLETED | 2025-11-09 | Chinta Devi |  |  | Yes
245 | 42/1 | DA+6 | Sandy | 2025-11-10 | 45.413 | COMPLETED | 2025-11-21 | Vinay Construction |  |  | Yes
246 | 42/2 | DA+6 | Sandy | 2025-10-27 | 45.413 | COMPLETED | 2025-11-09 | Vinay Construction |  |  | Yes
247 | 42/3 | DA+0 | Sandy | 2025-11-15 | 37.5044 | COMPLETED | 2025-11-17 | Sobha Devi |  |  | Yes
248 | 42/4 | DA+0 | Sandy | 2025-11-08 | 37.5044 | COMPLETED | 2025-11-14 | Shobha Devi |  |  | Yes
249 | 42/5 | DA+9 | Sandy | 2025-12-03 | 47.1844 | COMPLETED | 2025-12-06 | Shobha Devi |  |  | Yes
250 | 42/6 | DA+0 | Sandy | 2025-09-22 | 37.5044 | COMPLETED | 2025-10-07 | Vivek Ganju |  |  | Yes
251 | 43/0 | DB1+0 | Sandy | 2024-12-25 | 57.5972 | COMPLETED | 2025-01-07 | Yogendra Mahto |  |  | Yes
252 | 43/1 | DA+3 | Sandy | 2025-01-08 | 38.8476 | COMPLETED | 2025-01-17 | Yogendra Mahto |  |  | Yes
253 | 43/2 | DA+0 | Sandy | 2025-11-22 | 37.5044 | COMPLETED | 2025-11-30 | Vinay Construction |  |  | Yes
254 | 43/3 | DA+0 | DRY | 2025-09-09 | 37.5044 | COMPLETED | 2025-09-22 | Vivek Ganju |  |  | Yes
255 | 43/4 | DA+3 | Sandy | 2025-12-03 | 38.8476 | COMPLETED | 2025-12-10 | Vinay Construction |  |  | Yes
256 | 43/5 | DA+3 | DRY | 2025-08-29 | 38.8476 | COMPLETED | 2025-09-03 | Satyam Enterprises (Manish) |  |  | Yes
257 | 43/6 | DA+3 | Sandy | 2025-01-19 | 38.8476 | COMPLETED | 2025-01-29 | Bina Devi |  |  | Yes
258 | 43/7 | DA+3 | Sandy | 2025-01-11 | 38.8476 | COMPLETED | 2025-01-18 | Bina Devi |  |  | Yes
259 | 43/8 | DA+9 | Sandy | 2024-11-19 | 47.1844 | COMPLETED | 2024-11-27 | Yogendra Mahto |  |  | Yes
260 | 43/9 | DA+9 | Sandy | 2024-11-07 | 47.1844 | COMPLETED | 2024-11-18 | Yogendra Mahto |  |  | Yes
261 | 43/10 | DA+3 | Sandy | 2025-08-25 | 38.8476 | COMPLETED | 2025-08-30 | Satyam Enterprises (Pawan) |  |  | Yes
262 | 43/11 | DA+3 | Sandy | 2025-08-12 | 38.8476 | COMPLETED | 2025-08-18 | Satyam-Manish |  |  | Yes
263 | 44/0 | DB1+3 | Sandy | 2025-07-29 | 60.0968 | COMPLETED | 2025-08-03 | Satyam Enterprises |  |  | Yes
264 | 44/1 | DA+0 | Sandy | 2025-07-26 | 37.5044 | COMPLETED | 2025-07-29 | Satyam Enterprises |  |  | Yes
265 | 44/2 | DA+0 | Sandy | 2025-07-23 | 37.5044 | COMPLETED | 2025-07-26 | Satyam Enterprises |  |  | Yes
266 | 44/3 | DA+0 | Sandy | 2025-07-19 | 37.5044 | COMPLETED | 2025-07-22 | Satyam Enterprises |  |  | Yes
267 | 44/4 | DA+9 | Sandy | 2025-07-23 | 47.1844 | COMPLETED | 2025-07-28 | Satyam Enterprises |  |  | Yes
268 | 44/5 | DA+9 | Sandy | 2025-08-04 | 47.1844 | COMPLETED | 2025-08-09 | Satyam Enterprises |  |  | Yes
269 | 44/6 | DB1+3 | Sandy | 2025-08-09 | 60.0968 | COMPLETED | 2025-08-16 | Satyam Enterprises |  |  | Yes
270 | 44/7 | DA+9 | Sandy | 2025-07-28 | 47.1844 | COMPLETED | 2025-08-03 | Satyam Enterprises |  |  | Yes
271 | 44/8 | DCT+0 | Sandy | 2025-10-18 | 94.2199 | COMPLETED | 2025-10-31 | Chinta Devi |  |  | Yes
272 | 44/9 | DA+9 | Sandy | 2025-08-17 | 47.1844 | COMPLETED | 2025-08-24 | Satyam Enterprises |  |  | Yes
273 | 44/10 | DB1+9 | Sandy | 2025-07-28 | 70.7017 | COMPLETED | 2025-08-06 | Satyam Enterprises |  |  | Yes
274 | 44/11 | DA+0 | Sandy | 2025-08-19 | 37.5044 | COMPLETED | 2025-08-25 | Chinta Devi |  |  | Yes
275 | 45/0 | DC2+0 | Sandy | 2025-08-06 | 66.3811 | COMPLETED | 2025-08-17 | Sintu_Pawan (Satyam Enterprises) |  |  | Yes
276 | 45/1 | DA+9 | Sandy | 2025-08-25 | 47.1844 | COMPLETED | 2025-08-31 | Chinta Devi |  |  | Yes
277 | 46/0 | DD60+25 | Sandy | 2025-09-29 | 143.6019 | COMPLETED | 2025-10-18 | Chinta Devi |  |  | Yes
278 | 47/0 | DD60+25 | Sandy | 2025-09-09 | 143.6019 | COMPLETED | 2025-09-25 | Chinta Devi |  |  | Yes
279 | 47/1 | DA+3 | Sandy | 2025-09-01 | 38.8476 | COMPLETED | 2025-09-07 | Chinta Devi |  |  | Yes
280 | 47/2 | DA+9 | Sandy | 2025-08-04 | 47.1844 | COMPLETED | 2025-08-16 | Vinay Construction |  |  | Yes
281 | 47/3 | DA+9 | Sandy | 2025-08-17 | 47.1844 | COMPLETED | 2025-08-29 | Vinay Construction |  |  | Yes
282 | 47/4 | DA+3 | Sandy | 2025-08-06 | 38.8476 | COMPLETED | 2025-08-22 | Vinay Construction |  |  | Yes
283 | 47/5 | DA+0 | Sandy | 2025-09-07 | 37.5044 | COMPLETED | 2025-09-29 | Vinay Construction/ Chinta Devi |  |  | Yes
284 | 47/6 | DA+3 | Sandy | 2025-08-22 | 38.8476 | COMPLETED | 2025-09-06 | Vinay Construction |  |  | Yes
285 | 47/7 | DA+3 | Sandy | 2025-07-26 | 38.8476 | COMPLETED | 2025-08-05 | Vinay Construction |  |  | Yes
286 | 47/8 | DA+0 | Sandy | 2025-04-03 | 37.5044 | COMPLETED | 2025-04-06 | Sobha Devi |  |  | Yes
287 | 47/9 | DA+3 | Sandy | 2025-03-31 | 38.8476 | COMPLETED | 2025-04-02 | Sobha Devi |  |  | Yes
288 | 47/10 | DA+6 | Sandy | 2024-11-02 | 45.413 | COMPLETED | 2024-11-22 | Kaushalya const |  |  | Yes
289 | 48/0 | DC2+0 | Sandy | 2024-09-28 | 66.3811 | COMPLETED | 2024-10-19 | Kaushalya const |  |  | Yes
290 | 48/1 | DA+9 | Sandy | 2024-09-08 | 47.1844 | COMPLETED | 2024-09-25 | Kaushalya const |  |  | Yes
291 | 49/0 | DD45+0 | Sandy | 2025-02-05 | 86.1293 | COMPLETED | 2025-02-14 | Sobha Devi |  |  | Yes
292 | 49/1 | DA+0 | Sandy | 2024-12-06 | 37.5044 | COMPLETED | 2024-12-09 | Sobha Devi |  |  | Yes
293 | 49/2 | DA+3 | Sandy | 2024-11-27 | 38.8476 | COMPLETED | 2024-11-30 | Sobha Devi |  |  | Yes
294 | 49/3 | DA+3 | Sandy | 2024-12-02 | 38.8476 | COMPLETED | 2024-12-05 | Sobha Devi |  |  | Yes
295 | 49/4 | DA+3 | Sandy | 2024-11-18 | 38.8476 | COMPLETED | 2024-11-22 | Sobha Devi |  |  | Yes
296 | 49/5 | DA+3 | Sandy | 2024-11-23 | 38.8476 | COMPLETED | 2024-11-27 | Sobha Devi |  |  | Yes
297 | 49/6 | DA+0 | Sandy | 2024-11-15 | 37.5044 | COMPLETED | 2024-11-18 | Sobha Devi |  |  | Yes
298 | 49/7 | DA+0 | Sandy | 2024-11-11 | 37.5044 | COMPLETED | 2024-11-14 | Sobha Devi |  |  | Yes
299 | 50/0 | DB2+0 | Sandy | 2024-10-02 | 57.5972 | COMPLETED | 2024-10-07 | Sobha devi |  |  | Yes
300 | 50/1 | DA+6 | Sandy | 2024-10-07 | 45.413 | COMPLETED | 2024-10-15 | Sobha Devi |  |  | Yes
301 | 50/2 | DA+9 | Sandy | 2024-10-18 | 47.1844 | COMPLETED | 2024-10-24 | Sobha Devi |  |  | Yes
302 | 50/3 | DA+6 | Sandy | 2024-10-13 | 45.413 | COMPLETED | 2024-10-18 | Sobha Devi |  |  | Yes
303 | 50/4 | DA+9 | Sandy | 2024-10-24 | 47.1844 | COMPLETED | 2024-10-30 | Sobha Devi |  |  | Yes
304 | 50/5 | DA+9 | Sandy | 2025-02-15 | 47.1844 | COMPLETED | 2025-02-20 | Sobha Devi |  |  | Yes
305 | 50/6 | DA+9 | Sandy | 2024-11-04 | 47.1844 | COMPLETED | 2024-11-10 | Sobha Devi |  |  | Yes
306 | 50/7 | DA+0 | Sandy | 2024-11-01 | 37.5044 | COMPLETED | 2024-11-04 | Sobha Devi |  |  | Yes
307 | 50/8 | DA+9 | Sandy | 2024-10-07 | 47.1844 | COMPLETED | 2024-10-16 | Uma const |  |  | Yes
308 | 50/9 | DA+0 | Sandy | 2024-08-28 | 37.5044 | COMPLETED | 2024-09-09 | Uma const |  |  | Yes
309 | 50/10 | DA+0 | Sandy | 2024-09-10 | 37.5044 | COMPLETED | 2024-09-19 | Uma const |  |  | Yes
310 | 51/0 | DC2+0 | Sandy | 2025-01-31 | 66.3811 | COMPLETED | 2025-02-07 | Sunny Const. |  |  | Yes
311 | 51/1 | DA+0 | Sandy | 2024-09-19 | 37.5044 | COMPLETED | 2024-09-26 | Uma const |  |  | Yes
312 | 51/2 | DA+0 | Sandy | 2024-09-26 | 37.5044 | COMPLETED | 2024-10-04 | Uma const |  |  | Yes
313 | 52/0 | DC2+0 | Sandy | 2025-02-08 | 66.3811 | COMPLETED | 2025-02-14 | Sunny Const. |  |  | Yes
314 | 52/1 | DA+6 | Sandy | 2025-09-20 | 45.413 | COMPLETED | 2025-09-30 | Jirwa Devi |  |  | Yes
315 | 52/2 | DA+6 | Sandy | 2025-09-10 | 45.413 | COMPLETED | 2025-09-20 | Jirwa Devi |  |  | Yes
316 | 52/3 | DA+9 | Sandy | 2025-08-17 | 47.1844 | COMPLETED | 2025-08-30 | Jirwa Devi |  |  | Yes
317 | 52/4 | DA+9 | Sandy | 2025-09-01 | 47.1844 | COMPLETED | 2025-09-10 | Jirwa Devi |  |  | Yes
318 | 52/5 | DA+9 | Sandy | 2024-08-27 | 47.1844 | COMPLETED | 2024-09-19 | Ganesh Sinha |  |  | Yes
319 | 52/6 | DA+6 | Sandy | 2024-09-19 | 45.413 | COMPLETED | 2024-09-30 | Ganesh Sinha |  |  | Yes
320 | 52/7 | DA+3 | Sandy | 2024-10-01 | 38.8476 | COMPLETED | 2024-10-07 | Ganesh Sinha |  |  | Yes
321 | 52/8 | DA+6 | Sandy | 2024-10-08 | 45.413 | COMPLETED | 2024-10-19 | Ganesh Sinha |  |  | Yes
322 | 52/9 | DA+3 | Sandy | 2024-11-26 | 38.8476 | COMPLETED | 2024-12-05 | Ganesh Sinha |  |  | Yes
323 | 52/10 | DA+9 | Sandy | 2024-11-13 | 47.1844 | COMPLETED | 2024-11-25 | Ganesh Sinha |  |  | Yes
324 | 53/0 | DB2+9 | Sandy | 2025-04-12 | 70.7017 | COMPLETED | 2025-04-28 | Ganesh Sinha |  |  | Yes
325 | 53/1 | DA+9 | Sandy | 2025-04-02 | 47.1844 | COMPLETED | 2025-04-11 | Ganesh Sinha |  |  | Yes
326 | 53/2 | DA+0 | Sandy | 2025-03-26 | 37.5044 | COMPLETED | 2025-03-31 | Ganesh Sinha |  |  | Yes
327 | 53/3 | DA+6 | Sandy | 2025-03-18 | 45.413 | COMPLETED | 2025-03-25 | Ganesh Sinha |  |  | Yes
328 | 53/4 | DA+0 | Sandy | 2025-03-09 | 37.5044 | COMPLETED | 2025-03-17 | Ganesh Sinha |  |  | Yes
329 | 53/5 | DA+3 | Sandy | 2025-03-01 | 38.8476 | COMPLETED | 2025-03-07 | Ganesh Sinha |  |  | Yes
330 | 53/6 | DA+6 | Sandy | 2025-01-19 | 45.413 | COMPLETED | 2025-01-30 | Ganesh Sinha |  |  | Yes
331 | 53/7 | DA+3 | Sandy | 2025-01-10 | 38.8476 | COMPLETED | 2025-01-18 | Ganesh Sinha |  |  | Yes
332 | 53/8 | DA+3 | Sandy | 2025-01-04 | 38.8476 | COMPLETED | 2025-01-09 | Ganesh Sinha |  |  | Yes
333 | 54/0 | DB1+6 | Sandy | 2025-09-22 | 67.8737 | COMPLETED | 2025-09-30 | Sunny Construction |  |  | Yes
334 | 54/1 | DA+3 | Sandy | 2025-09-13 | 38.8476 | COMPLETED | 2025-09-18 | Sunny Construction |  |  | Yes
335 | 54/2 | DA+3 | Sandy | 2025-09-19 | 38.8476 | COMPLETED | 2025-09-22 | Sunny Construction |  |  | Yes
336 | 54/3 | DA+6 | Sandy | 2025-09-07 | 45.413 | COMPLETED | 2025-09-12 | Sunny Construction |  |  | Yes
337 | 54/4 | DA+9 | Sandy | 2025-09-01 | 47.1844 | COMPLETED | 2025-09-06 | Sunny Construction |  |  | Yes
338 | 54/5 | DA+9 | Sandy | 2025-08-17 | 47.1844 | COMPLETED | 2025-08-31 | Sunny Construction |  |  | Yes
339 | 55/0 | DB1+6 | Sandy | 2025-09-30 | 67.8737 | COMPLETED | 2025-10-11 | Sunny Construction |  |  | Yes
340 | 55/1 | DA+0 | WFR | 2025-08-17 | 37.5044 | COMPLETED | 2025-08-24 | Sunny Construction |  |  | Yes
341 | 55/2 | DA+0 | WFR | 2025-10-12 | 37.5044 | COMPLETED | 2025-10-14 | Sunny Construction |  |  | Yes
342 | 55/3 | DA+0 | Sandy | 2024-05-12 | 37.5044 | COMPLETED | 2024-05-31 | Mansukh lal |  |  | Yes
343 | 55/4 | DA+0 | Sandy | 2024-06-01 | 37.5044 | COMPLETED | 2024-06-19 | Mansukh lal |  |  | Yes
344 | 55/5 | DA+0 | Sandy | 2024-11-01 | 37.5044 | COMPLETED | 2024-11-12 | Jirwa Devi |  |  | Yes
345 | 55/6 | DA+0 | Sandy | 2024-10-23 | 37.5044 | COMPLETED | 2024-11-01 | Jirwa Devi |  |  | Yes
346 | 55/7 | DA+0 | Sandy | 2025-08-13 | 37.5044 | COMPLETED | 2025-08-17 | Shobha Devi |  |  | Yes
347 | 55/8 | DA+6 | Sandy | 2025-08-07 | 45.413 | COMPLETED | 2025-08-13 | Shobha Devi |  |  | Yes
348 | 56/0 | DD60+25 | Sandy | 2025-08-30 | 143.6019 | COMPLETED | 2025-09-14 | Shobha Devi |  |  | Yes
349 | 57/0 | DD60+25 | Sandy | 2025-09-15 | 143.6019 | COMPLETED | 2025-09-29 | Shobha Devi |  |  | Yes
350 | 57/1 | DA+0 | Sandy | 2025-08-21 | 37.5044 | COMPLETED | 2025-08-29 | Sobha Devi |  |  | Yes
351 | 57/2 | DA+3 | DRY | 2025-08-21 | 38.8476 | COMPLETED | 2025-08-25 | Sobha Devi |  |  | Yes
352 | 57/3 | DA+0 | DRY | 2024-05-29 | 37.5044 | COMPLETED | 2024-06-11 | Bhuvneshwar |  |  | Yes
353 | 57/4 | DA+0 | Sandy | 2024-06-12 | 37.5044 | COMPLETED | 2024-06-27 | Bhuvneshwar |  |  | Yes
354 | 57/5 | DA+3 | Sandy | 2024-08-20 | 38.8476 | COMPLETED | 2024-08-26 | Sobha devi |  |  | Yes
355 | 57/6 | DA+3 | Sandy | 2024-08-13 | 38.8476 | COMPLETED | 2024-08-20 | Sobha devi |  |  | Yes
356 | 57/7 | DA+3 | DFR | 2024-09-27 | 38.8476 | COMPLETED | 2024-10-01 | Sobha devi |  |  | Yes
357 | 58/0 | DC1+3 | DFR | 2025-02-26 | 69.2287 | COMPLETED | 2025-03-10 | Jirwa Devi |  |  | Yes
358 | 59/0 | DC2+0 | DRY | 2024-12-03 | 66.3811 | COMPLETED | 2024-12-16 | Jirwa Devi |  |  | Yes
359 | 59/1 | DA+3 | DRY | 2024-11-25 | 38.8476 | COMPLETED | 2024-12-03 | Jirwa Devi |  |  | Yes
360 | 59/2 | DA+3 | DFR | 2024-11-12 | 38.8476 | COMPLETED | 2024-11-24 | Jirwa Devi |  |  | Yes
361 | 59/3 | DA+3 | DFR | 2024-10-27 | 38.8476 | COMPLETED | 2024-11-02 | Uma const |  |  | Yes
362 | 59/4 | DA+3 | DFR | 2024-11-01 | 38.8476 | COMPLETED | 2024-11-09 | Uma const |  |  | Yes
363 | 59/5 | DA+3 | DFR | 2024-02-05 | 38.8476 | COMPLETED | 2024-02-11 | Ganesh Const |  |  | Yes
364 | 59/6 | DA+3 | DFR | 2024-02-12 | 38.8476 | COMPLETED | 2024-02-18 | Ganesh Const |  |  | Yes
365 | 59/7 | DA+3 | DRY | 2024-02-18 | 38.8476 | COMPLETED | 2024-02-24 | Ganesh Const |  |  | Yes
366 | 59/8 | DB1+3 | DRY | 2024-02-24 | 60.0968 | COMPLETED | 2024-02-29 | Ganesh Const |  |  | Yes
367 | 59/9 | DA+3 | DRY | 2024-02-24 | 38.8476 | COMPLETED | 2024-02-28 | Chinta Devi |  |  | Yes
368 | 59/10 | DA+0 | DRY | 2024-02-20 | 37.5044 | COMPLETED | 2024-02-24 | Chinta Devi |  |  | Yes
369 | 59/11 | DA+6 | DFR | 2024-10-17 | 45.413 | COMPLETED | 2024-10-26 | Uma const |  |  | Yes
370 | 59/12 | DA+6 | DFR | 2024-02-13 | 45.413 | COMPLETED | 2024-02-20 | Chinta Devi |  |  | Yes
371 | 59/13 | DA+3 | DRY | 2024-02-01 | 38.8476 | COMPLETED | 2024-02-07 | Chinta Devi |  |  | Yes
372 | 59/14 | DA+6 | DRY | 2024-02-08 | 45.413 | COMPLETED | 2024-02-13 | Chinta Devi |  |  | Yes
373 | 59/15 | DA+6 | DRY | 2024-05-18 | 45.413 | COMPLETED | 2024-05-30 | Ganesh |  |  | Yes
374 | 59/16 | DA+9 | Dry | 2024-02-29 | 47.1844 | COMPLETED | 2024-03-11 | Ganesh Const. |  |  | Yes
375 | 60/0 | DC1+0 | DRY | 2024-05-05 | 66.3811 | COMPLETED | 2024-05-18 | Ganesh |  |  | Yes
376 | 60/1 | DA+6 | DRY | 2024-04-18 | 45.413 | COMPLETED | 2024-04-25 | Ganesh Const. |  |  | Yes
377 | 60/2 | DA+3 | DFR | 2024-03-31 | 38.8476 | COMPLETED | 2024-04-07 | Ganesh Const. |  |  | Yes
378 | 60/3 | DA+3 | DFR | 2024-03-23 | 38.8476 | COMPLETED | 2024-03-31 | Ganesh Const. |  |  | Yes
379 | 60/4 | DA+3 | DFR | 2024-03-18 | 38.8476 | COMPLETED | 2024-03-23 | Ganesh Const. |  |  | Yes
380 | 60/5 | DA+3 | DRY | 2024-03-11 | 38.8476 | COMPLETED | 2024-03-17 | Ganesh Const. |  |  | Yes
381 | 60/6 | DA+0 | DRY | 2024-02-26 | 37.5044 | COMPLETED | 2024-02-29 | Suraj const |  |  | Yes
382 | 60/7 | DA+3 | DRY | 2024-01-28 | 38.8476 | COMPLETED | 2024-02-04 | Suraj const |  |  | Yes
383 | 60/8 | DA+0 | DRY | 2024-02-09 | 37.5044 | COMPLETED | 2024-02-15 | Suraj const |  |  | Yes
384 | 60/9 | DA+3 | DRY | 2024-04-29 | 38.8476 | COMPLETED | 2024-05-05 | Sobha Devi |  |  | Yes
385 | 60/10 | DA+0 | DFR | 2024-02-15 | 37.5044 | COMPLETED | 2024-02-21 | Suraj const |  |  | Yes
386 | 60/11 | DA+3 | DRY | 2024-02-21 | 38.8476 | COMPLETED | 2024-02-26 | Suraj const |  |  | Yes
387 | 61/0 | DB2+0 | DRY | 2024-04-06 | 57.5972 | COMPLETED | 2024-04-11 | Sobha Devi |  |  | Yes
388 | 61/1 | DA+6 | DFR | 2024-04-22 | 45.413 | COMPLETED | 2024-04-29 | Sobha Devi |  |  | Yes
389 | 61/2 | DA+6 | DFR | 2024-04-16 | 45.413 | COMPLETED | 2024-04-22 | Sobha Devi |  |  | Yes
390 | 61/3 | DA+6 | DRY | 2024-05-05 | 45.413 | COMPLETED | 2024-05-11 | Sobha Devi |  |  | Yes
391 | 61/4 | DA+3 | DRY | 2024-05-11 | 38.8476 | COMPLETED | 2024-05-16 | Sobha Devi |  |  | Yes
392 | 61/5 | DA+3 | DRY | 2024-05-16 | 38.8476 | COMPLETED | 2024-05-22 | Sobha Devi |  |  | Yes
393 | 61/6 | DA+3 | DRY | 2024-03-18 | 38.8476 | COMPLETED | 2024-03-22 | Sobha Devi |  |  | Yes
394 | 61/7 | DA+9 | Dry | 2024-03-22 | 47.1844 | COMPLETED | 2024-03-28 | Sobha Devi |  |  | Yes
395 | 61/8 | DA+6 | DRY | 2024-05-23 | 45.413 | COMPLETED | 2024-05-30 | Suraj const |  |  | Yes
396 | 61/9 | DA+0 | Dry | 2024-05-19 | 37.5044 | COMPLETED | 2024-05-23 | Suraj const |  |  | Yes
397 | 61/10 | DA+9 | DRY | 2024-05-12 | 47.1844 | COMPLETED | 2024-05-19 | Suraj const |  |  | Yes
398 | 62/0 | DB2+0 | DRY | 2024-08-31 | 57.5972 | COMPLETED | 2024-09-08 | Sobha devi |  |  | Yes
399 | 62/1 | DA+3 | Sandy | 2024-07-04 | 38.8476 | COMPLETED | 2024-07-12 | Bhuvneshwar |  |  | Yes
400 | 62/2 | DA+3 | DRY | 2024-02-29 | 38.8476 | COMPLETED | 2024-03-03 | Sobha Devi |  |  | Yes
401 | 62/3 | DA+0 | DRY | 2024-02-26 | 37.5044 | COMPLETED | 2024-02-28 | Sobha Devi |  |  | Yes
402 | 62/4 | DA+3 | DRY | 2024-02-22 | 38.8476 | COMPLETED | 2024-02-26 | Sobha Devi |  |  | Yes
403 | 62/5 | DA+0 | DRY | 2024-02-17 | 37.5044 | COMPLETED | 2024-02-22 | Sobha Devi |  |  | Yes
404 | 62/6 | DA+3 | DRY | 2024-07-15 | 38.8476 | COMPLETED | 2024-07-26 | Bhuvneshwar |  |  | Yes
405 | 62/7 | DA+3 | DRY | 2024-03-04 | 38.8476 | COMPLETED | 2024-03-07 | Sobha Devi |  |  | Yes
406 | 62/8 | DA+0 | DFR | 2024-03-07 | 37.5044 | COMPLETED | 2024-03-11 | Sobha Devi |  |  | Yes
407 | 62/9 | DA+3 | DFR | 2024-03-11 | 38.8476 | COMPLETED | 2024-03-15 | Sobha Devi |  |  | Yes
408 | 62/10 | DA+0 | DFR | 2024-03-15 | 37.5044 | COMPLETED | 2024-03-18 | Sobha Devi |  |  | Yes
409 | 62/11 | DA+3 | DRY | 2024-04-27 | 38.8476 | COMPLETED | 2024-05-03 | Suraj const |  |  | Yes
410 | 63/0 | DC1+0 | DFR | 2024-05-03 | 66.3811 | COMPLETED | 2024-05-12 | Suraj const |  |  | Yes
411 | 63/1 | DA+3 | DFR | 2024-04-22 | 38.8476 | COMPLETED | 2024-04-27 | Suraj const |  |  | Yes
412 | 63/2 | DA+0 | DFR | 2024-04-17 | 37.5044 | COMPLETED | 2024-04-22 | Suraj const |  |  | Yes
413 | 63/3 | DA+3 | DFR | 2024-04-13 | 38.8476 | COMPLETED | 2024-04-17 | Suraj Const |  |  | Yes
414 | 63/4 | DA+0 | DRY | 2024-04-07 | 37.5044 | COMPLETED | 2024-04-13 | Suraj Const |  |  | Yes
415 | 63/5 | DA+3 | DFR | 2024-04-01 | 38.8476 | COMPLETED | 2024-04-07 | Suraj Const |  |  | Yes
416 | 63/6 | DA+3 | DRY | 2024-02-03 | 38.8476 | COMPLETED | 2024-02-10 | Sunny Const. |  |  | Yes
417 | 63/7 | DA+3 | DRY | 2024-02-11 | 38.8476 | COMPLETED | 2024-02-15 | Sunny Const. |  |  | Yes
418 | 63/8 | DA+3 | DRY | 2024-02-15 | 38.8476 | COMPLETED | 2024-02-20 | Sunny Const. |  |  | Yes
419 | 64/0 | DB2+0 | DRY | 2024-04-27 | 57.5972 | COMPLETED | 2024-05-05 | Sunny Const. |  |  | Yes
420 | 64/1 | DA+0 | DRY | 2024-02-20 | 37.5044 | COMPLETED | 2024-02-24 | Sunny Const. |  |  | Yes
421 | 64/2 | DA+3 | DRY | 2024-04-16 | 38.8476 | COMPLETED | 2024-04-21 | Sunny Const. |  |  | Yes
422 | 64/3 | DA+0 | DRY | 2024-04-21 | 37.5044 | COMPLETED | 2024-04-26 | Sunny Const. |  |  | Yes
423 | 64/4 | DA+3 | DRY | 2024-02-24 | 38.8476 | COMPLETED | 2024-02-29 | Sunny Const. |  |  | Yes
424 | 64/5 | DA+3 | DRY | 2024-02-29 | 38.8476 | COMPLETED | 2024-03-04 | Sunny Const. |  |  | Yes
425 | 64/6 | DA+0 | DRY | 2024-03-21 | 37.5044 | COMPLETED | 2024-03-26 | Sunny Const. |  |  | Yes
426 | 64/7 | DA+3 | DRY | 2024-03-26 | 38.8476 | COMPLETED | 2024-03-30 | Sunny Const. |  |  | Yes
427 | 64/8 | DA+3 | DRY | 2024-03-30 | 38.8476 | COMPLETED | 2024-04-03 | Sunny Const. |  |  | Yes
428 | 64/9 | DA+3 | DRY | 2024-04-03 | 38.8476 | COMPLETED | 2024-04-08 | Sunny Const. |  |  | Yes
429 | 64/10 | DA+3 | DRY | 2024-04-15 | 38.8476 | COMPLETED | 2024-04-20 | Chinta Devi |  |  | Yes
430 | 64/11 | DA+3 | DRY | 2024-10-20 | 38.8476 | COMPLETED | 2024-10-24 | Chinta devi |  |  | Yes
431 | 65/0 | DB1+0 | DRY | 2024-04-21 | 57.5972 | COMPLETED | 2024-04-27 | Chinta Devi |  |  | Yes
432 | 65/1 | DA+0 | DRY | 2024-04-27 | 37.5044 | COMPLETED | 2024-05-03 | Chinta Devi |  |  | Yes
433 | 65/2 | DA+0 | DRY | 2024-02-29 | 37.5044 | COMPLETED | 2024-03-06 | Chinta Devi |  |  | Yes
434 | 65/3 | DA+3 | DRY | 2024-03-11 | 38.8476 | COMPLETED | 2024-03-16 | Chinta Devi |  |  | Yes
435 | 65/4 | DA+0 | DRY | 2024-03-06 | 37.5044 | COMPLETED | 2024-03-11 | Chinta Devi |  |  | Yes
436 | 65/5 | DA+0 | DRY | 2024-03-16 | 37.5044 | COMPLETED | 2024-03-20 | Chinta Devi |  |  | Yes
437 | 65/6 | DA+0 | DRY | 2024-03-20 | 37.5044 | COMPLETED | 2024-03-26 | Chinta Devi |  |  | Yes
438 | 65/7 | DA+0 | DRY | 2024-12-28 | 37.5044 | COMPLETED | 2025-01-04 | Sanjeev Kumar |  |  | Yes
439 | 65/8 | DA+0 | DRY | 2024-12-20 | 37.5044 | COMPLETED | 2024-12-27 | Sanjeev Kumar |  |  | Yes
440 | 65/9 | DA+0 | DRY | 2024-03-26 | 37.5044 | COMPLETED | 2024-03-31 | Chinta Devi |  |  | Yes
441 | 65/10 | DA+0 | DRY | 2025-01-29 | 37.5044 | COMPLETED | 2025-02-06 | Sanjeev Kumar |  |  | Yes
442 | 65/11 | DA+0 | DRY | 2024-03-31 | 37.5044 | COMPLETED | 2024-04-04 | Chinta Devi |  |  | Yes
443 | 66/0 | DC2+6 | DRY | 2025-01-11 | 78.132 | COMPLETED | 2025-01-29 | Sanjeev Kumar |  |  | Yes
444 | 67/0 | DC1+9 | DRY | 2025-05-20 | 81.4946 | COMPLETED | 2025-05-29 | Sunny Construction |  |  | Yes
445 | 67/1 | DA+0 | DRY | 2024-04-06 | 37.5044 | COMPLETED | 2024-04-10 | Chinta Devi |  |  | Yes
446 | 67/2 | DA+0 | DRY | 2024-04-10 | 37.5044 | COMPLETED | 2024-04-15 | Chinta Devi |  |  | Yes
447 | 68/0 | DD45+0 | DRY | 2025-03-13 | 86.1293 | COMPLETED | 2025-04-14 | Sunny Const. |  |  | Yes
448 | 69/0 | DB2+0 | DFR | 2025-07-14 | 57.5972 | COMPLETED | 2025-07-21 | Jwala Singh (Suraj Kumar) |  |  | Yes
449 | 69/1 | DA+3 | DRY | 2025-06-28 | 38.8476 | COMPLETED | 2025-07-03 | Jwala Singh (Suraj Kumar) |  |  | Yes
450 | 70/0 | DC1+0 | DRY | 2025-07-03 | 66.3811 | COMPLETED | 2025-07-14 | Jwala Singh (Suraj Kumar) |  |  | Yes
451 | 70/1 | DA+3 | DRY | 2025-07-01 | 38.8476 | COMPLETED | 2025-07-08 | Satyam Enterprises (Vijay) |  |  | Yes
452 | 70/2 | DA+3 | DRY | 2025-06-22 | 38.8476 | COMPLETED | 2025-06-30 | Satyam Enterprises (Vijay) |  |  | Yes
453 | 70/3 | DA+3 | DRY | 2025-03-08 | 38.8476 | COMPLETED | 2025-03-16 | Sanjeev kumar |  |  | Yes
454 | 70/4 | DA+3 | DRY | 2025-04-27 | 38.8476 | COMPLETED | 2025-05-02 | Chinta devi |  |  | Yes
455 | 70/5 | DA+3 | DRY | 2025-03-20 | 38.8476 | COMPLETED | 2025-03-29 | Sanjeev kumar |  |  | Yes
456 | 70/6 | DA+3 | DRY | 2025-05-19 | 38.8476 | COMPLETED | 2025-06-28 | Satyam Enterprises (Santosh) |  |  | Yes
457 | 70/7 | DA+3 | DRY | 2025-06-17 | 38.8476 | COMPLETED | 2025-06-22 | Jwala Singh |  |  | Yes
458 | 70/8 | DA+3 | DRY | 2025-07-08 | 38.8476 | COMPLETED | 2025-07-14 | Satyam Enterprises (Vijay) |  |  | Yes
459 | 70/9 | DA+3 | DRY | 2025-04-06 | 38.8476 | COMPLETED | 2025-04-09 | Chinta Devi |  |  | Yes
460 | 70/10 | DA+3 | DRY | 2025-03-31 | 38.8476 | COMPLETED | 2025-04-04 | Chinta Devi |  |  | Yes
461 | 70/11 | DA+3 | DRY | 2025-03-26 | 38.8476 | COMPLETED | 2025-03-31 | Chinta Devi |  |  | Yes
462 | 71/0 | DB2+3 | DRY | 2025-03-19 | 60.0968 | COMPLETED | 2025-03-25 | Chinta Devi |  |  | Yes
463 | 71/1 | DA+3 | DRY | 2025-03-13 | 38.8476 | COMPLETED | 2025-03-18 | Chinta Devi |  |  | Yes
464 | 71/2 | DA+3 | DRY | 2025-03-08 | 38.8476 | COMPLETED | 2025-03-12 | Chinta Devi |  |  | Yes
465 | 71/3 | DA+6 | DRY | 2025-03-02 | 45.413 | COMPLETED | 2025-03-07 | Chinta Devi |  |  | Yes
466 | 71/4 | DA+3 | DRY | 2025-02-25 | 38.8476 | COMPLETED | 2025-03-01 | Chinta Devi |  |  | Yes
467 | 71/5 | DA+3 | DRY | 2025-02-20 | 38.8476 | COMPLETED | 2025-02-24 | Chinta Devi |  |  | Yes
468 | 71/6 | DA+0 | DRY | 2025-02-16 | 37.5044 | COMPLETED | 2025-02-19 | Chinta Devi |  |  | Yes
469 | 71/7 | DA+3 | DRY | 2025-02-11 | 38.8476 | COMPLETED | 2025-02-15 | Chinta Devi |  |  | Yes
470 | 71/8 | DA+3 | DRY | 2025-02-07 | 38.8476 | COMPLETED | 2025-02-10 | Chinta Devi |  |  | Yes
471 | 72/0 | DB2+3 | DRY | 2025-01-21 | 60.0968 | COMPLETED | 2025-01-27 | Chinta Devi |  |  | Yes
472 | 72/1 | DA+3 | DRY | 2025-01-28 | 38.8476 | COMPLETED | 2025-02-02 | Chinta Devi |  |  | Yes
473 | 72/2 | DA+0 | DRY | 2025-02-02 | 37.5044 | COMPLETED | 2025-02-06 | Chinta Devi |  |  | Yes
474 | 72/3 | DA+3 | DRY | 2024-11-24 | 38.8476 | COMPLETED | 2024-11-30 | Sanjeev Kumar |  |  | Yes
475 | 73/0 | DB2+0 | DRY | 2025-01-03 | 57.5972 | COMPLETED | 2025-01-09 | Chinta devi |  |  | Yes
476 | 73/1 | DA+0 | DRY | 2024-10-21 | 37.5044 | COMPLETED | 2024-10-29 | Sanjeev Kumar |  |  | Yes
477 | 73/2 | DA+0 | DRY | 2024-10-10 | 37.5044 | COMPLETED | 2024-10-20 | Sanjeev Kumar |  |  | Yes
478 | 73/3 | DA+0 | DRY | 2024-12-09 | 37.5044 | COMPLETED | 2024-12-13 | Chinta devi |  |  | Yes
479 | 73/4 | DA+0 | DRY | 2025-01-10 | 37.5044 | COMPLETED | 2025-01-14 | Chinta devi |  |  | Yes
480 | 73/5 | DA+0 | DRY | 2025-01-15 | 37.5044 | COMPLETED | 2025-01-19 | Chinta devi |  |  | Yes
481 | 73/6 | DA+0 | DRY | 2024-11-17 | 37.5044 | COMPLETED | 2024-11-20 | Chinta devi |  |  | Yes
482 | 73/7 | DA+0 | DRY | 2025-01-14 | 37.5044 | COMPLETED | 2025-01-19 | Sunny Const |  |  | Yes
483 | 73/8 | DA+3 | DRY | 2024-11-13 | 38.8476 | COMPLETED | 2024-11-17 | Chinta devi |  |  | Yes
484 | 73/9 | DA+0 | DRY | 2024-11-09 | 37.5044 | COMPLETED | 2024-11-13 | Chinta devi |  |  | Yes
485 | 74/0 | DB2+0 | Sandy | 2025-01-05 | 57.5972 | COMPLETED | 2025-01-13 | Sunny Const |  |  | Yes

## Stringing Compiled
Number of TSE
S.no | Sec | From AP | To AP | Location Nos. | Span (M) | Method | Section Readiness | Insulator Hoisting | P/O Starting Date | P/O Completion Date | P/O | F/S Starting Date | F/S/ Completion Date | Jumpering | Spacering | Clipping | Length | Status | Gang Name | Gang Strength | Number of Fitters | Hindrance | Remarks
| Section-1 | Gty | 1/0 | 1/0 | 0.122 | M | Ready | Completed | 2026-03-27 | 2026-03-30 | 0.122 | 2026-03-27 | 2026-03-30 | Completed | Completed | Completed | 0.122 | Completed | Devi Power
| Section-1 | 1/0 | 1A/0 | 1A/0 | 0.09 | M | Ready | Completed | 2026-03-24 | 2026-03-31 | 0.09 | 2026-03-24 | 2026-03-31 | Completed | Completed | Completed | 0.09 | Completed | Devi Power
| Section-1 | 1A/0 | 2/0 | 1/1, 1/2, 1/3, 1/4, 1/5, 1/6, 1/7, 1/8, 2/0 | 3.426 | TSE | Ready | Completed | 2025-11-21 | 2025-11-28 | 3.426 | 2025-11-28 | 2025-11-30 | Completed | Completed | Completed | 3.426 | Completed | Devi Power
| Section-1 | 2/0 | 3/0 | 2/1, 2/2, 2/3, 2/4, 2/5, 2/6, 2/7, 2/8, 2/9, 3/0 | 3.8236 | TSE | Ready | Completed | 2025-11-13 | 2025-11-18 | 3.8236 | 2025-12-30 | 2026-01-14 | Completed | Completed | Completed | 3.8236 | Completed | Devi Power
| Section-1 | 3/0 | 4/0 | 4/0 | 0.227 | M | Ready | Completed | 2026-01-10 | 2026-01-16 | 0.227 | 2026-01-11 | 2026-01-16 |  | Completed | Completed | 0.227 | Completed | Gopal Associate, Hotline
| Section-1 | 4/0 | 5/0 | 4/1, 4/2, 4/3, 4/4, 5/0 | 1.8731 | TSE | Ready | Balance | [9 empty] | Balance
| Section-1 | 5/0 | 6/0 | 6/0 | 0.246 | M | Ready | Completed | 2026-04-24 | 2026-04-30 | 0.246 | 2026-04-24 | 2026-04-30 |  | Completed | Completed | 0.246 | Completed | Gopal Associate, Hotline
| Section-1 | 6/0 | 7/0 | 6/1, 6/2, 7/0 | 1.14 | TSE | Ready | Completed | 2025-03-19 | 2026-04-15 | 1.14 | 2026-03-24 | 2026-04-30 | Completed | Completed | Completed | 1.14 | Completed | Deepak Sarkar / Nasiruddin
| Section-1 | 7/0 | 8/0 | 8/0 | 0.211 | M | Ready | Completed | 2026-02-20 | 2026-02-26 | 0.211 | 2026-02-20 | 2026-02-26 | Completed | Completed | Completed | 0.211 | Completed | Gopal Associate, Hotline
| Section-1 | 8/0 | 8/7 | 8/1, 8/2, 8/3, 8/4, 8/5, 8/6, 8/7 | 2.8614 | TSE | Ready | Completed | 2026-04-06 | 2026-04-09 | 2.8614 | 2026-04-08 | 2026-04-11 | Completed | Completed | Completed | 2.8614 | Completed | Devi Power
| Section-1 | 8/7 | 9/0 | 8/8, 8/9, 8/10, 8/11, 8/12, 9/0 | 2.456 | TSE | Ready | Completed | 2026-03-30 | 2026-04-03 | 2.456 | 2026-04-06 | 2026-04-08 | Completed | Completed | Completed | 2.456 | Completed | Deepak Sarkar
| Section-1 | 9/0 | 10/0 | 10/0 | 0.233 | M | Ready | Completed | 2026-04-03 | 2026-04-09 | 0.233 | 2026-04-03 | 2026-04-10 | Completed | Completed | Completed | 0.233 | Completed | Gopal Associate, Hotline
| Section-1 | 10/0 | 10/12 | 10/1, 10/2, 10/3, 10/4, 10/5, 10/6, 10/7, 10/8, 10/9, 10/10, 10/11, 10/12 | 4.8945 | TSE | Ready | Completed | 2026-03-09 | 2026-03-15 | 4.8945 | 2026-04-04 | 2026-04-08 | Completed | Completed | Completed | 4.8945 | Completed | Deepak Sarkar
| Section-1 | 10/12 | 11/0 | 10/13, 10/14, 10/15, 10/16, 10/17, 10/18, 10/19, 10/20, 10/21, 10/22, 10/23, 11/0 | 4.9466 | TSE | Ready | Completed | 2026-01-14 | 2026-01-22 | 4.9466 | 2026-02-05 | 2026-02-07 | Completed | Completed | Completed | 4.9466 | Completed | Deepak Sarkar
| Section-1 | 11/0 | 11A/0 | 11/1, 11/2, 11/3, 11/4, 11/5, 11A/0 | 2.238 | TSE | Ready | Balance | [9 empty] | Balance
| Section-1 | 11A/0 | 12/0 | 11A/1, 11A/2, 11A/3, 11A/4, 11A/5, 11A/6, 11A/7, 11A/8, 11A/9, 12/0 | 4.11 | TSE | Ready | Balance | [9 empty] | Balance | Nasiruddin
| Section-1 | 12/0 | 13/0 | 13/0 | 0.212 | M | Not Ready | Balance | [9 empty] | Balance
| Section-1 | 13/0 | 14/0 | 13/1, 13/2, 13/3, 13/4, 14/0 | 2.078 | TSE | Ready | Completed | 2026-03-30 | 2026-04-04 | 2.078 | [6 empty] | WIP | Nasiruddin
| Section-1 | 14/0 | 14A/0 | 14A/0 | 0.381 | M | Ready | Completed | 2026-03-30 | 2026-04-06 | 0.381 | 2026-04-05 | 2026-04-06 | Balance | Balance | Balance | 0.381 | Completed | Nasiruddin
| Section-1 | 14A/0 | 15/0 | 14A/1, 14A/2, 15/0 | 1.192 | TSE | Ready | Completed | 2026-04-25 | 2026-05-04 | 1.192 | 2026-05-02 | 2026-05-04 | Balance | Balance | Balance |  | Balance | Nasiruddin
| Section-1 | 15/0 | 16/0 | 15/1, 16/0 | 0.8179 | TSE | Ready | Balance | [9 empty] | Balance
| Section-1 | 16/0 | 17/0 | 16/1, 16/2, 16/3, 16/4, 16/5, 17/0 | 2.3363 | TSE | Ready | Balance | [9 empty] | Balance
| Section-1 | 17/0 | 18/0 | 17/1, 17/2, 17/3, 17/4, 17/5, 18/0 | 2.451 | TSE | Ready | Balance | [9 empty] | Balance
| Section-1 | 18/0 | 19/0 | 18/1, 18/2, 18/3, 18/4, 19/0 | 1.9031 | TSE | Ready | Balance | [9 empty] | Balance
| Section-1 | 19/0 | 20/0 | 19/1, 19/2, 19/3, 19/4, 19/5, 20/0 | 2.2568 | TSE | Ready | Balance | [9 empty] | Balance
| Section-1 | 20/0 | 21/0 | 20/1, 20/2, 20/3, 21/0 | 1.4773 | TSE | Not Ready | Balance | [9 empty] | Balance
| Section-1 | 21/0 | 22/0 | 21/1, 21/2, 21/3, 21/4, 21/5, 21/6, 21/7, 21/8, 21/9, 21/10, 22/0 | 4.579 | TSE | Not Ready | Balance | [9 empty] | Balance
| Section-1 | 22/0 | 22/8 | 22/1, 22/2, 22/3, 22/4, 22/5, 22/6, 22/7, 22/8 | 3.177 | TSE | Not Ready | Balance | [9 empty] | Balance
| Section-1 | 22/8 | 23/0 | 22/9, 22/10, 22/11, 22/12, 22/13, 23/0 | 2.3018 | TSE | Not Ready | Balance | [9 empty] | Balance
| Section-1 | 23/0 | 24/0 | 24/0 | 0.222 | M | Not Ready | Balance | [9 empty] | Balance
| Section-1 | 24/0 | 25/0 | 25/0 | 0.434 | M | Ready | Balance | [9 empty] | Balance
| Section-1 | 25/0 | 26/0 | 25/1, 25/2, 25/3, 25/4, 26/0 | 1.9702 | TSE | Ready | Balance | [9 empty] | Balance
| Section-1 | 26/0 | 27/0 | 26/1, 26/2, 26/3, 26/4, 26/5, 26/6, 26/7, 26/8, 27/0 | 3.6643 | TSE | Ready | Balance | [9 empty] | Balance
| Section-1 | 27/0 | 27/7 | 27/1, 27/2, 27/3, 27/4, 27/5, 27/6, 27/7 | 2.8104 | TSE | Ready | Completed | [8 empty] | 2.8104 | Tata Scope
| Section-1 | 27/7 | 28/0 | 27/8, 27/9, 27/10, 27/11, 27/12, 28/0 | 2.3869 | TSE | Ready | Completed | [8 empty] | 2.3869 | Tata Scope
| Section-1 | 28/0 | 29/0 | 28/1, 28/2, 28/3, 28/4, 28/5, 28/6, 28/7, 28/8, 29/0 | 3.6391 | TSE | Ready | Completed | [8 empty] | 3.6391 | Tata Scope
| Section-1 | 29/0 | 30/0 | 29/1, 29/2, 29/3, 29/4, 30/0 | 2.0107 | TSE | Ready | Completed | [8 empty] | 2.0107 | Tata Scope
| Section-1 | 30/0 | 31/0 | 30/1, 30/2, 30/3, 30/4, 30/5, 30/6, 31/0 | 2.7193 | TSE | Ready | Completed | [8 empty] | 2.7193 | Tata Scope
| Section-1 | 31/0 | 32/0 | 31/1, 31/2, 32/0 | 1.0825 | TSE | Ready | Completed | [8 empty] | 1.0825 | Tata Scope
| Section-1 | 32/0 | 33/0 | 32/1, 32/2, 32/3, 32/4, 33/0 | 2.075 | TSE | Ready | Completed | [8 empty] | 2.075 | Tata Scope
| Section-2 | 33/0 | 34/0 | 33/1, 34/0 | 0.6721 | TSE | Ready | Completed | [8 empty] | 0.6721 | Tata Scope
| Section-2 | 34/0 | 35/0 | 34/1, 34/2, 34/3, 34/4, 35/0 | 2.0482 | TSE | Ready | Completed | [8 empty] | 2.0482 | Tata Scope
| Section-2 | 35/0 | 35/2 | 35/1, 35/2 | 0.758 | TSE | Ready | Completed | [8 empty] | 0.758 | Tata Scope
| Section-2 | 35/2 | 35/3 | 35/3 | 0.522 | TSE | Ready | Completed | [8 empty] | 0.522 | Tata Scope
| Section-2 | 35/3 | 36/0 | 35/4, 35/5, 36/0 | 1.183 | TSE | Ready | Completed | [8 empty] | 1.183 | Tata Scope
| Section-2 | 36/0 | 37/0 | 36/1,36/2, 36/3, 36/4, 37/0 | 1.885 | TSE | Ready | Completed | [8 empty] | 1.885 | Tata Scope
| Section-2 | 37/0 | 38/0 | 37/1, 37/2, 37/3, 38/0 | 1.64 | TSE | Ready | Completed | [8 empty] | 1.64 | Tata Scope
| Section-2 | 38/0 | 39/0 | 38/1, 38/2, 38/3, 38/4, 39/0 | 2.101 | TSE | Ready | Completed | [8 empty] | 2.101 | Tata Scope
| Section-2 | 39/0 | 40/0 | 39/1,40/0 | 0.735 | TSE | Ready | Completed | [8 empty] | 0.735 | Tata Scope
| Section-2 | 40/0 | 41/0 | 40/1, 40/2, 40/3, 41/0 | 1.66 | TSE | Ready | Completed | [8 empty] | 1.66 | Tata Scope
| Section-2 | 41/0 | 41/1 | 41/1, 41/0 | 0.341 | M | Ready | Completed | [8 empty] | 0.341 | Tata Scope
| Section-2 | 41/1 | 42/0 | 41/1, 41/2, 42/0 | 0.83 | TSE | Ready | Completed | [8 empty] | 0.83 | Tata Scope
| Section-2 | 42/0 | 43/0 | 42/1, 42/2, 42/3, 42/4, 42/5, 42/6, 43/0 | 2.6671 | TSE | Ready | Completed | [8 empty] | 2.6671 | Tata Scope
| Section-2 | 43/0 | 44/0 | 43/1,43/2, 43/3, 43/4, 43/5, 43/6, 43/7, 43/8,43/9, 43/10, 43/11, 44/0 | 4.8527 | TSE | Ready | Completed | 2026-04-08 | 2026-04-15 | 4.8527 | 2026-04-16 | 2026-04-18 | Balance | Balance | Balance | 4.8527 | Completed | Krishna-1
| Section-2 | 44/0 | 44/6 | 44/0,1,2,3,4,5 | 2.312 | TSE | Ready | Completed | 2026-03-27 | 2026-03-31 | 2.312 | 2026-03-28 | 2026-03-31 | Completed | Completed | Completed | 2.312 | Completed | Krishna-1
| Section-2 | 44/6 | 44/8 | 44/8/9/10/11 | 0.84 | TSE | Ready | Completed | 2026-03-20 | 2026-03-23 | 0.84 | 2026-03-28 | 2026-03-31 | Completed | Completed | Completed | 0.84 | Completed | Krishna-1
| Section-2 | 44/8 | 44/10 | 44/8, 9, 10 | 0.795 | TSE | Ready | Completed | 2026-02-16 | 2026-02-19 | 0.795 | 2026-03-10 | 2026-03-13 | Completed | Completed | Completed | 0.795 | Completed | Krishna-1
| Section-2 | 44/10 | 45/0 | 44/11, 45/0 | 0.755 | TSE | Ready | Completed | 2026-02-09 | 2026-02-12 | 0.755 | 2026-02-17 | 2026-02-20 | Completed | Completed | Completed | 0.755 | Completed | Krishna-1
| Section-2 | 45/0 | 46/0 | 45/1, 46/0 | 0.701 | TSE | Ready | Completed | 2026-02-07 | 2026-02-08 | 0.701 | 2026-02-10 | 2026-02-13 | Completed | Completed | Completed | 0.701 | Completed | Krishna-1
| Section-2 | 46/0 | 47/0 | 47/0 | 0.199 | M | Ready | Completed | 2025-12-06 | 2025-12-11 | 0.199 | 2025-12-06 | 2025-12-11 | Completed | Completed | Completed | 0.199 | Completed | Gopal Associate, Hotline
| Section-2 | 47/0 | 48/0 | 47/0,1,2,3,4,5,6,7,8, 9, 48/0 | 4.478 | TSE | Ready | Completed | 2026-01-26 | 2026-01-31 | 4.478 | 2026-01-28 | 2026-01-31 | Completed | Completed | Completed | 4.478 | Completed | Krishna-1
| Section-2 | 48/0 | 49/0 | 48/1, 49/0 | 0.832 | TSE | Ready | Completed | 2026-01-17 | 2026-01-20 | 0.832 | 2026-01-20 | 2026-01-23 | Completed | Completed | Completed | 0.832 | Completed | Krishna-1
| Section-2 | 49/0 | 50/0 | 49/1,2,3,4,5,6,7,50/0 | 3.227 | TSE | Ready | Completed | 2025-02-06 | 2025-02-19 | 3.227 | 2025-05-01 | 2025-05-05 | Completed | Completed | Completed | 3.227 | Completed | Gopal Associate
| Section-2 | 50/0 | 51/0 | 50/1,2,3,4,5,6,7,8,9,10,11, 51/0 | 4.4441 | TSE | Ready | Completed | 2025-03-12 | 2025-03-23 | 4.4441 | 2025-03-17 | 2025-03-24 | Completed | Completed | Completed | 4.4441 | Completed | Gopal Associate
| Section-2 | 51/0 | 52/0 | 51/1, 2, 52/0 | 1.049 | TSE | Ready | Completed | 2025-04-02 | 2025-04-08 | 1.049 | 2025-04-04 | 2025-04-09 | Completed | Completed | Completed | 1.049 | Completed | Gopal Associate
| Section-2 | 52/0 | 53/0 | 52/1,2,3,4,5,6,7,8,9,10,11, 53/0 | 4.535 | TSE | Ready | Completed | [9 empty] | Paying out WIP. | MC Power
| Section-2 | 53/0 | 54/0 | 53/1,2,3,4,5,6,7,8,54/0 | 3.69 | TSE | Ready | Completed | 2025-04-18 | 2026-04-26 | 3.69 | 2026-04-30 | 2026-04-30 | Completed | Completed | Completed | 3.69 | Completed | MC Power
| Section-2 | 54/0 | 55/0 | 54/0,1,2,3,4,5 | 2.411 | TSE | Ready | Completed | 2026-04-03 | 2026-04-09 | 2.411 | 2026-04-08 | 2026-04-11 | Completed | Completed | Completed | 2.411 | Completed | MC Power
| Section-2 | 55/0 | 56/0 | 55/1,2,3,4,5,6,7,8,56/0 | 3.318 | TSE | Ready | Completed | 2026-02-12 | 2026-03-25 | 3.318 | 2026-03-27 | 2026-03-31 | Completed | Completed | Completed | 3.318 | Completed | MC Power
| Section-2 | 56/0 | 57/0 | 57/0 | 0.22 | M | Ready | Completed | 2025-11-20 | 2025-11-26 | 0.22 | 2025-11-20 | 2025-11-26 | Completed | Completed | Completed | 0.22 | Completed | Gopal Associate, Hotline
| Section-2 | 57/0 | 58/0 | 57/1,2,3,4,5,6,7,58/0 | 3.288 | TSE | Ready | Completed | 2026-01-19 | 2026-01-24 | 3.288 | 2026-01-29 | 2026-01-31 | Completed | Completed | Completed | 3.288 | Completed | MC Power
| Section-2 | 58/0 | 59/0 | 59/0 | 0.239 | M | Ready | Completed | 2026-01-28 | 2026-01-28 | 0.239 | 2026-01-28 | 2026-01-28 | Completed | Completed | Completed | 0.239 | Completed | MC Power
| Section-2 | 59/0 | 59/8 | 59/1,2,3,4,5,6,7,8 | 3.337 | TSE | Ready | Completed | 2025-01-02 | 2025-01-08 | 3.337 | 2025-01-12 | 2025-01-15 | Completed | Completed | Completed | 3.337 | Completed | Gopal Associate
| Section-2 | 59/8 | 60/0 | 59/10,11,12,13,14,15,16,17,60/0 | 3.778 | TSE | Ready | Completed | 2024-12-22 | 2024-12-27 | 3.778 | 2025-01-04 | 2025-01-09 | Completed | Completed | Completed | 3.778 | Completed | Gopal Associate
| Section-2 | 60/0 | 61/0 | 60/1,2,3,4,5,6,7,8,9,10,11, 61/0 | 4.878 | TSE | Ready | Completed | 2024-08-21 | 2024-08-28 | 4.878 | 2024-09-09 | 2024-09-16 | Completed | Completed | Completed | 4.878 | Completed | Kuddus ali
| Section-2 | 61/0 | 62/0 | 61/1,2,3,4,5,6,7,8,9,10,62/0 | 4.568 | TSE | Ready | Completed | 2024-09-06 | 2024-09-16 | 4.568 | 2024-09-26 | 2024-10-03 | Completed | Completed | Completed | 4.568 | Completed | Kuddus ali
| Section-2 | 62/0 | 63/0 | 62/1,2,3,4,5,6,7,8,9,10,11, 63/0 | 4.863 | TSE | Ready | Completed | 2024-09-23 | 2024-10-02 | 4.863 | 2024-10-17 | 2024-10-22 | Completed | Completed | Completed | 4.863 | Completed | Kuddus ali
| Section-2 | 63/0 | 64/0 | 63/1,2,3,4,5,6,7,8, 64/0 | 3.711 | TSE | Ready | Completed | 2024-10-14 | 2024-10-21 | 3.711 | 2024-10-31 | 2024-11-06 | Completed | Completed | Completed | 3.711 | Completed | Kuddus ali
| Section-2 | 64/0 | 65/0 | 64/1,2,3,4,5,6,7,8,9,10,11, 65/0 | 4.918 | TSE | Ready | Completed | 2024-10-30 | 2024-11-05 | 4.918 | 2024-11-13 | 2024-11-16 | Completed | Completed | Completed | 4.918 | Completed | Kuddus ali
| Section-2 | 65/0 | 66/0 | 65/1,2,3,4,5,6,7,8,9,10,11, 66/0 | 4.736 | TSE | Ready | Completed | 2025-02-03 | 2025-03-22 | 4.736 | 2025-03-10 | 2025-03-23 | Completed | Completed | Completed | 4.736 | Completed | MR Power
| Section-2 | 66/0 | 67/0 | 67/0 | 0.208 | M | Ready | Completed | 2026-01-03 | 2026-01-03 | 0.208 | 2026-01-03 | 2026-01-03 | Completed | Completed | Completed | 0.208 | Completed | MC Power
| Section-2 | 67/0 | 68/0 | 67/1,2, 68/0 | 1.061 | TSE | Ready | Completed | 2025-12-26 | 2025-12-28 | 1.061 | 2026-01-06 | 2026-01-08 | Completed | Completed | Completed | 1.061 | Completed | MC Power
| Section-2 | 68/0 | 69/0 | 68/0 | 0.201 | M | Ready | Completed | 2025-12-29 | 2025-12-29 | 0.201 | 2025-12-29 | 2025-12-29 | Completed | Completed | Completed | 0.201 | Completed | MC Power
| Section-2 | 69/0 | 70/0 | 69/0,1 | 0.769 | TSE | Ready | Completed | 2025-12-18 | 2025-12-24 | 0.769 | 2025-12-21 | 2025-12-25 | Completed | Completed | Completed | 0.769 | Completed | MC Power
| Section-2 | 70/0 | 71/0 | 70/0,1,2,3,4,5,6,7,8,9,10,11, 71/0 | 4.967 | TSE | Ready | Completed | 2025-12-08 | 2025-12-16 | 4.967 | 2025-12-12 | 2025-12-17 | Completed | Completed | Completed | 4.967 | Completed | MC Power
| Section-2 | 71/0 | 72/0 | 71/1,2,3,4,5,6,7,72/0 | 3.676 | TSE | Ready | Completed | 2025-11-20 | 2025-11-25 | 3.676 | 2025-11-28 | 2025-11-30 | Completed | Completed | Completed | 3.676 | Completed | MC Power
| Section-2 | 72/0 | 73/0 | 72/1, 2, 3, 73/0 | 1.629 | TSE | Ready | Completed | 2025-11-03 | 2025-11-08 | 1.629 | 2025-11-21 | 2025-11-25 | Completed | Completed | Completed | 1.629 | Completed | JPJ Construction/MC Power
| Section-2 | 73/0 | 74/0 | 73/1,2,3,4,5,6,7,8,9,10, 73/0 | 3.788 | TSE | Ready | Completed | 2025-06-01 | 2025-06-21 | 3.788 | 2025-09-26 | 2025-09-30 | Completed | Completed | Completed | 3.788 | Completed | JPJ Construction/MC Power
|  |  | Total |  | 191.3919