## DailyExpanded
Work Date | Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name | Location No. | Status
2024-01-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-01-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-02-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-02-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-03-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-03-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-04-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-04-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-05-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-05-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-06-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-06-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-07-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-07-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-08-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-08-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-09-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-09-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-09 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-10 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-11 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-12 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-13 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-14 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-15 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-16 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-17 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-18 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-19 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-20 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-21 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-22 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-23 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-24 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-25 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-26 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-27 | 2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-28 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-10-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-29 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-10-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-30 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-10-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-10-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-10-31 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-10-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-01 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-11-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-02 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-11-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-03 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-11-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-04 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-11-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-05 | 2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-11-05 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-06 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-07 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-08 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-09 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-10 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-11 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-12 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-13 | 2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-14 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 34/3 | COMPLETED
2024-11-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-15 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 34/3 | COMPLETED
2024-11-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-16 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 34/3 | COMPLETED
2024-11-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-17 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 34/3 | COMPLETED
2024-11-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-18 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 34/3 | COMPLETED
2024-11-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-19 | 2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 34/3 | COMPLETED
2024-11-19 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 35/4 | COMPLETED
2024-11-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-20 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 35/4 | COMPLETED
2024-11-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-21 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 35/4 | COMPLETED
2024-11-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-22 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 35/4 | COMPLETED
2024-11-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-23 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 35/4 | COMPLETED
2024-11-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-24 | 2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 35/4 | COMPLETED
2024-11-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-26 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 40/1 | COMPLETED
2024-11-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-27 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 40/1 | COMPLETED
2024-11-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-28 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 40/1 | COMPLETED
2024-11-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-29 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 40/1 | COMPLETED
2024-11-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-11-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-11-30 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 40/1 | COMPLETED
2024-11-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-01 | 2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 40/1 | COMPLETED
2024-12-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-02 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418 | 40/2 | COMPLETED
2024-12-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-03 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418 | 40/2 | COMPLETED
2024-12-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-03 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-04 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418 | 40/2 | COMPLETED
2024-12-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-04 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-05 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418 | 40/2 | COMPLETED
2024-12-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-05 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-06 | 2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418 | 40/2 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 41/3 | COMPLETED
2024-12-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-06 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 41/3 | COMPLETED
2024-12-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-07 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 41/3 | COMPLETED
2024-12-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-08 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 41/3 | COMPLETED
2024-12-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-09 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 41/3 | COMPLETED
2024-12-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-10 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 41/3 | COMPLETED
2024-12-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-11 | 2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-12 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-12 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418 | 41/4 | COMPLETED
2024-12-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-12 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418 | 42/1 | COMPLETED
2024-12-13 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-13 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418 | 41/4 | COMPLETED
2024-12-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-13 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418 | 42/1 | COMPLETED
2024-12-14 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-14 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418 | 41/4 | COMPLETED
2024-12-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-14 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418 | 42/1 | COMPLETED
2024-12-15 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-15 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418 | 41/4 | COMPLETED
2024-12-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-15 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418 | 42/1 | COMPLETED
2024-12-16 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-16 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418 | 41/4 | COMPLETED
2024-12-16 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-16 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418 | 42/1 | COMPLETED
2024-12-17 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-17 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418 | 41/4 | COMPLETED
2024-12-17 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-17 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418 | 42/1 | COMPLETED
2024-12-18 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-18 | 2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418 | 41/4 | COMPLETED
2024-12-18 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-18 | 2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418 | 42/1 | COMPLETED
2024-12-19 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-19 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-19 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-19 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-20 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-20 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-20 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-20 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-21 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-21 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-21 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-21 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-22 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-22 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-22 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-22 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-23 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-23 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-23 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-23 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-24 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-24 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-24 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-24 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-25 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-25 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-25 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-25 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-26 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-26 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-26 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-26 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-27 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-27 | 2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-27 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-27 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-28 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-28 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-28 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-29 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-29 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-29 | 2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-30 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-30 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2024-12-31 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-12-31 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-01 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-01 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-02 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-02 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-03 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-03 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-04 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-04 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-05 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-05 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-06 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-06 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-07 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-07 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-08 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-08 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-09 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-09 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-10 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-10 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-11 | 2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2025-01-11 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-12 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-13 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 46/8 | COMPLETED
2025-01-13 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-14 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 46/8 | COMPLETED
2025-01-14 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-15 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 46/8 | COMPLETED
2025-01-15 | 2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-16 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 46/8 | COMPLETED
2025-01-16 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-16 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-17 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 46/8 | COMPLETED
2025-01-17 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-17 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-18 | 2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 46/8 | COMPLETED
2025-01-18 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-18 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-19 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-19 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-20 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-20 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-21 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-21 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-22 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-22 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-23 | 2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-23 | 2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-24 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418 | 34/2 | COMPLETED
2025-01-24 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-25 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418 | 34/2 | COMPLETED
2025-01-25 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-25 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-01-26 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418 | 34/2 | COMPLETED
2025-01-26 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-26 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-01-27 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418 | 34/2 | COMPLETED
2025-01-27 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-27 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-01-28 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418 | 34/2 | COMPLETED
2025-01-28 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-28 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-01-29 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418 | 34/2 | COMPLETED
2025-01-29 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-29 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-01-30 | 2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418 | 34/2 | COMPLETED
2025-01-30 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-30 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-01-31 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 35/8 | COMPLETED
2025-01-31 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-31 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-02-01 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 35/8 | COMPLETED
2025-02-01 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-01 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-02-02 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 35/8 | COMPLETED
2025-02-02 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-02 | 2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-02-03 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 35/8 | COMPLETED
2025-02-03 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-04 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 35/8 | COMPLETED
2025-02-04 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-05 | 2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 35/8 | COMPLETED
2025-02-05 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-06 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418 | 41/1 | COMPLETED
2025-02-06 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-07 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418 | 41/1 | COMPLETED
2025-02-07 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-08 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418 | 41/1 | COMPLETED
2025-02-08 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-09 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418 | 41/1 | COMPLETED
2025-02-09 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-10 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418 | 41/1 | COMPLETED
2025-02-10 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-11 | 2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418 | 41/1 | COMPLETED
2025-02-11 | 2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-02-12 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 41/2 | COMPLETED
2025-02-12 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-13 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 41/2 | COMPLETED
2025-02-13 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-14 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 41/2 | COMPLETED
2025-02-14 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-15 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 41/2 | COMPLETED
2025-02-15 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-16 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 41/2 | COMPLETED
2025-02-16 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-17 | 2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 41/2 | COMPLETED
2025-02-17 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-18 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-19 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-20 | 2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-21 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 41/0 | COMPLETED
2025-02-22 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 41/0 | COMPLETED
2025-02-23 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 41/0 | COMPLETED
2025-02-24 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 41/0 | COMPLETED
2025-02-25 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 41/0 | COMPLETED
2025-02-26 | 2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 41/0 | COMPLETED
2025-02-26 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 43/0 | COMPLETED
2025-02-27 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 43/0 | COMPLETED
2025-02-28 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 43/0 | COMPLETED
2025-03-01 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 43/0 | COMPLETED
2025-03-02 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 43/0 | COMPLETED
2025-03-03 | 2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 43/0 | COMPLETED
2025-03-03 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 46/0 | COMPLETED
2025-03-04 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 46/0 | COMPLETED
2025-03-05 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 46/0 | COMPLETED
2025-03-06 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 46/0 | COMPLETED
2025-03-06 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/9 | COMPLETED
2025-03-07 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 46/0 | COMPLETED
2025-03-07 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/9 | COMPLETED
2025-03-08 | 2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 46/0 | COMPLETED
2025-03-08 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/9 | COMPLETED
2025-03-09 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/9 | COMPLETED
2025-03-10 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/9 | COMPLETED
2025-03-11 | 2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/9 | COMPLETED
2025-03-12 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418 | 46/7 | COMPLETED
2025-03-13 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418 | 46/7 | COMPLETED
2025-03-14 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418 | 46/7 | COMPLETED
2025-03-15 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418 | 46/7 | COMPLETED
2025-03-16 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418 | 46/7 | COMPLETED
2025-03-17 | 2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418 | 46/7 | COMPLETED
2025-03-18 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418 | 45/0 | COMPLETED
2025-03-18 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-19 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418 | 45/0 | COMPLETED
2025-03-19 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-20 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418 | 45/0 | COMPLETED
2025-03-20 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-21 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418 | 45/0 | COMPLETED
2025-03-21 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-22 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418 | 45/0 | COMPLETED
2025-03-22 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-23 | 2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418 | 45/0 | COMPLETED
2025-03-23 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-24 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-25 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-26 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-27 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-28 | 2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-28 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418 | 45/2 | COMPLETED
2025-03-29 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418 | 45/2 | COMPLETED
2025-03-30 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418 | 45/2 | COMPLETED
2025-03-31 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418 | 45/2 | COMPLETED
2025-04-01 | 2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418 | 45/2 | COMPLETED
2025-04-02 | 2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | TA418 | 40/3 | COMPLETED
2025-04-03 | 2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | TA418 | 40/3 | COMPLETED
2025-04-04 | 2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | TA418 | 40/3 | COMPLETED
2025-04-05 | 2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | TA418 | 40/3 | COMPLETED
2025-04-05 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418 | 42/0 | COMPLETED
2025-04-06 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418 | 42/0 | COMPLETED
2025-04-07 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418 | 42/0 | COMPLETED
2025-04-08 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418 | 42/0 | COMPLETED
2025-04-09 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418 | 42/0 | COMPLETED
2025-04-10 | 2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418 | 42/0 | COMPLETED
2025-04-11 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-12 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418 | 55/4 | COMPLETED
2025-04-13 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418 | 55/4 | COMPLETED
2025-04-14 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418 | 55/4 | COMPLETED
2025-04-15 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418 | 55/4 | COMPLETED
2025-04-16 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418 | 55/4 | COMPLETED
2025-04-17 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418 | 55/4 | COMPLETED
2025-04-18 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418 | 55/4 | COMPLETED
2025-04-18 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-19 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-19 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-20 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-20 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-21 | 2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-21 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-22 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-22 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-23 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-23 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-24 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-24 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-25 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-25 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-26 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-26 | 2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-27 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-27 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418 | 46/15 | COMPLETED
2025-04-28 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-28 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418 | 46/15 | COMPLETED
2025-04-29 | 2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-29 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-04-29 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418 | 46/15 | COMPLETED
2025-04-30 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-04-30 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418 | 46/15 | COMPLETED
2025-05-01 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-05-01 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418 | 46/15 | COMPLETED
2025-05-02 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-05-02 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418 | 46/15 | COMPLETED
2025-05-03 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-05-03 | 2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418 | 46/15 | COMPLETED
2025-05-04 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-05-05 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-05-05 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/2 | COMPLETED
2025-05-06 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-05-06 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/2 | COMPLETED
2025-05-07 | 2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-05-07 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/2 | COMPLETED
2025-05-08 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/2 | COMPLETED
2025-05-08 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-09 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/2 | COMPLETED
2025-05-09 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-10 | 2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/2 | COMPLETED
2025-05-10 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-11 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-11 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-11 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-12 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-12 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-12 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-13 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-13 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-13 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-14 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-14 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-14 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-15 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-15 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-15 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-16 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-16 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-16 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-17 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-17 | 2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-17 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-18 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-18 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-19 | 2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-19 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-20 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-21 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-22 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418 | 34/4 | COMPLETED
2025-05-22 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-23 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418 | 34/4 | COMPLETED
2025-05-23 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-24 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418 | 34/4 | COMPLETED
2025-05-24 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-25 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418 | 34/4 | COMPLETED
2025-05-25 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-26 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418 | 34/4 | COMPLETED
2025-05-26 | 2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-27 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418 | 34/4 | COMPLETED
2025-05-28 | 2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418 | 34/4 | COMPLETED
2025-05-29 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418 | 40/5 | COMPLETED
2025-05-30 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418 | 40/5 | COMPLETED
2025-05-30 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 35/3 | COMPLETED
2025-05-31 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418 | 40/5 | COMPLETED
2025-05-31 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 35/3 | COMPLETED
2025-06-01 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418 | 40/5 | COMPLETED
2025-06-01 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 35/3 | COMPLETED
2025-06-02 | 2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418 | 40/5 | COMPLETED
2025-06-02 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 35/3 | COMPLETED
2025-06-03 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 35/3 | COMPLETED
2025-06-03 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 33/7 | COMPLETED
2025-06-04 | 2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 35/3 | COMPLETED
2025-06-04 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 33/7 | COMPLETED
2025-06-05 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 33/7 | COMPLETED
2025-06-06 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 33/7 | COMPLETED
2025-06-07 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 33/7 | COMPLETED
2025-06-08 | 2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 33/7 | COMPLETED
2025-06-09 | 2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | TA418 | 33/8 | COMPLETED
2025-06-10 | 2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | TA418 | 33/8 | COMPLETED
2025-06-11 | 2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | TA418 | 33/8 | COMPLETED
2025-06-12 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418 | 33/9 | COMPLETED
2025-06-12 | 2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | TA418 | 33/8 | COMPLETED
2025-06-13 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418 | 33/9 | COMPLETED
2025-06-14 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418 | 33/9 | COMPLETED
2025-06-14 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-15 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418 | 33/9 | COMPLETED
2025-06-15 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-16 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418 | 33/9 | COMPLETED
2025-06-16 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-17 | 2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418 | 33/9 | COMPLETED
2025-06-17 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-18 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-19 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-19 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-20 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-20 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-21 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-21 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-22 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-22 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-23 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-23 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-24 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-24 | 2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-25 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-26 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-27 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-28 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-29 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-29 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-06-30 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-06-30 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-01 | 2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-07-01 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-02 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-03 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-03 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-03 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-03 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-04 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-04 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-04 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-04 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-05 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-05 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-05 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-05 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-06 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-06 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-06 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-06 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-07 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-07 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-07 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-07 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-08 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-08 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-08 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-08 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-09 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-09 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-09 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-09 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-10 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-10 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-10 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-10 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-11 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-11 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-11 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-11 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-12 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-12 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-12 | 2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-12 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-13 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-13 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-13 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-14 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-14 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-14 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418 | 37/2 | COMPLETED
2025-07-14 | 2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-15 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-15 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-15 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418 | 37/2 | COMPLETED
2025-07-15 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-16 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-16 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-16 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418 | 37/2 | COMPLETED
2025-07-16 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-17 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-17 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-17 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418 | 37/2 | COMPLETED
2025-07-17 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-18 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-18 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-18 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418 | 37/2 | COMPLETED
2025-07-18 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-19 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-19 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-19 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418 | 37/2 | COMPLETED
2025-07-19 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-20 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-20 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-20 | 2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418 | 37/2 | COMPLETED
2025-07-20 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-21 | 2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-21 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-21 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-21 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-21 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-22 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-22 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-22 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-22 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-22 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-23 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-23 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-23 | 2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-23 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-23 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-24 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-24 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-24 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-24 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-25 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-25 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-25 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-25 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-26 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-26 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-26 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-26 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-27 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-27 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-27 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-27 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-28 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-28 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-28 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-28 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-29 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-29 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-29 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-29 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-30 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-30 | 2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-30 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-30 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-31 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-07-31 | 2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-31 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-08-01 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-08-01 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-08-02 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-08-02 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-08-03 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-08-03 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-08-04 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-08-04 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-08-05 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-08-05 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-08-06 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-08-06 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-06 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-08-07 | 2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-08-07 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-07 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-07 | 2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-08-07 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-08 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-08 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-08 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-09 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-09 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-09 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-09 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-10 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-10 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-10 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-10 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-11 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-11 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-11 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-11 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-12 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-12 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-12 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-12 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-13 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-13 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-13 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-13 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-14 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-14 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-14 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-14 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-15 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-15 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-15 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-15 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-16 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-16 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-16 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-16 | 2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-16 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-17 | 2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-17 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-17 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-17 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-18 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-18 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-18 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-18 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-19 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-19 | 2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-19 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-19 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-19 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-20 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-20 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-20 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-20 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-21 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-21 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-21 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-21 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-22 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-22 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418 | 46/3 | COMPLETED
2025-08-22 | 2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-22 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-22 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-23 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-23 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418 | 46/3 | COMPLETED
2025-08-23 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-23 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-24 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-24 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418 | 46/3 | COMPLETED
2025-08-24 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-24 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-25 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-25 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418 | 46/3 | COMPLETED
2025-08-25 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-25 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-26 | 2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-26 | 2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418 | 46/3 | COMPLETED
2025-08-26 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-26 | 2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-27 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-28 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-29 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-30 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-31 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-08-31 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-09-01 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-01 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-01 | 2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-09-02 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-02 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-03 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-03 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418 | 46/12 | COMPLETED
2025-09-04 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-04 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418 | 46/12 | COMPLETED
2025-09-05 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-05 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418 | 46/12 | COMPLETED
2025-09-06 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-06 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418 | 46/12 | COMPLETED
2025-09-07 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-07 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418 | 46/12 | COMPLETED
2025-09-08 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-08 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-09 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-09 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418 | 48/2 | COMPLETED
2025-09-10 | 2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-10 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418 | 48/2 | COMPLETED
2025-09-11 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418 | 48/2 | COMPLETED
2025-09-12 | 2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418 | 48/2 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418 | 48/2 | COMPLETED
2025-09-14 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-15 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-16 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-16 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-17 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-17 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-18 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-18 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-19 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-19 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-20 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-20 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-21 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-21 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-22 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-22 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-23 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-23 | 2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-24 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-25 | 2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2024-03-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-03-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-03-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-03-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-03-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-03-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-12 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-13 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-14 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-15 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-16 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-17 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-18 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-19 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-20 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-21 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-21 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-22 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-23 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-24 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-25 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-26 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-27 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-28 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-09-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-29 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-09-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-30 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-09-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-01 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-10-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-02 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-10-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-03 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-10-03 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-03 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-04 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-04 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-05 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-05 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-06 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-06 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-07 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-07 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-08 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-08 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-09 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-09 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-10 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-10 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-11 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-11 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-12 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-12 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-13 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-13 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-14 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-14 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-14 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-15 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-15 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-16 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-16 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-17 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-17 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-18 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-19 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-20 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-21 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-22 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-23 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-24 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-25 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-12 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-13 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-14 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-14 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-15 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-15 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-16 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-16 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-17 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-17 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-18 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-18 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-19 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-19 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-20 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-20 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-21 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-21 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-22 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-22 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-23 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-23 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-24 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-24 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-25 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-25 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-26 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-26 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-11-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-27 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-27 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-11-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-28 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-28 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-11-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-29 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-29 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-11-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-30 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-30 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-01 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-12-01 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-02 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-12-02 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-03 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-12-03 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-04 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-12-04 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-05 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-05 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-06 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-06 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-07 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-07 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-07 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-08 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-08 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-08 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-09 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-09 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-09 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-10 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-10 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-10 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-11 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-11 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-11 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-12 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-12 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-12 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-13 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-13 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-13 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-13 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-13 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-14 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-14 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-14 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-14 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-14 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-15 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-15 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-15 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-15 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-15 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-15 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-16 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-16 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-16 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-16 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-16 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-16 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-17 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-17 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-17 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-17 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-17 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-17 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-18 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-18 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-18 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-18 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-18 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-18 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-19 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-19 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-19 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-19 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-19 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-19 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-20 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-20 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-20 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-20 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-20 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-20 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-21 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-21 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-21 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-21 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-21 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-21 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-22 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-22 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-22 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-22 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-22 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-22 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-23 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-23 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-23 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-23 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-23 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-23 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-24 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-24 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-24 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-24 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-24 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-24 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-24 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-24 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-25 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-25 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-25 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-25 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-25 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-25 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-25 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-26 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-26 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-26 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-26 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-26 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-26 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-27 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2024-12-27 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-27 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-27 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-27 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-27 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-28 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2024-12-28 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-28 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-28 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-28 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-28 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-29 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2024-12-29 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-29 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2024-12-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-29 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-29 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-29 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-30 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2024-12-30 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-30 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2024-12-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-30 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-30 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2024-12-30 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2024-12-31 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2024-12-31 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-31 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2024-12-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-31 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-31 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2024-12-31 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-01 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2025-01-01 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2025-01-01 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-01 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2025-01-01 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-01 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-02 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2025-01-02 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2025-01-02 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-02 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2025-01-02 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-02 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-03 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2025-01-03 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2025-01-03 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-03 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2025-01-03 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-03 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-04 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-04 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2025-01-04 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-04 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-04 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-04 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-05 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-05 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2025-01-05 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-05 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-05 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-05 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-06 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-06 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-06 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-06 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-06 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-06 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-07 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-07 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-07 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-07 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-07 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-07 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-07 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-08 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-08 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-08 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-08 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-08 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-08 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-08 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-09 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-09 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-09 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-09 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-09 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-09 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-10 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-10 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-10 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-10 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-10 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-10 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-11 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-11 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-11 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-11 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-11 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-11 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-11 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-12 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-12 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-12 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-12 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-12 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-12 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-13 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-13 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-13 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-13 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-13 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-13 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-14 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-14 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-14 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-14 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-14 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-14 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-15 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-15 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-15 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-15 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-15 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-15 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-16 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | COMPLETED
2025-01-16 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-16 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-16 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-16 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-16 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-17 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | COMPLETED
2025-01-17 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-17 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-17 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-17 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-17 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-17 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-17 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-18 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | COMPLETED
2025-01-18 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-18 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-18 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-18 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-18 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-18 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-18 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-19 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | COMPLETED
2025-01-19 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-19 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-19 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-19 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-19 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-19 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-19 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-20 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | COMPLETED
2025-01-20 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-20 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-20 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-20 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-20 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-20 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-21 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-21 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-21 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-21 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-21 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-21 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-21 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-22 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-22 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-22 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-22 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-22 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-22 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-22 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-22 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-23 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-23 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-23 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-23 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-23 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-23 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-24 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-24 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-24 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-24 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-24 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-24 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-24 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-25 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-25 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-25 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-25 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-25 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-25 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-25 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-26 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-26 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-26 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-26 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-26 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-26 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-27 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-27 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-27 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-27 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-27 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-27 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-28 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-28 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-28 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-28 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-28 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-28 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-29 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-01-29 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-29 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-29 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-29 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-01-29 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-29 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-29 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-29 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-01-30 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-01-30 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-30 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-30 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-01-30 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-30 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | COMPLETED
2025-01-30 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-30 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-01-31 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-01-31 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-31 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-01-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-31 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-01-31 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | COMPLETED
2025-01-31 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-31 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-01-31 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-01 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-02-01 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-01 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-01 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | COMPLETED
2025-02-01 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-01 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-02 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-02-02 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-02 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-02 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | COMPLETED
2025-02-02 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-02 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-03 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-02-03 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-03 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-03 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | COMPLETED
2025-02-03 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-03 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-03 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-04 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-02-04 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-04 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-04 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-04 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-04 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-05 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-05 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-05 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-05 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-05 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-05 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-06 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-06 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-06 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-06 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-06 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-06 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-07 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-07 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-07 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-07 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-07 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-07 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-08 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-08 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-08 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-08 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-08 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-08 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-09 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-09 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-09 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-09 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-09 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-09 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-10 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-10 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-10 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-10 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-10 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-10 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-11 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | COMPLETED
2025-02-11 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-11 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-11 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-11 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-11 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-12 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | COMPLETED
2025-02-12 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-12 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-12 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-12 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-12 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-13 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | COMPLETED
2025-02-13 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-13 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-13 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-13 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-13 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-14 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | COMPLETED
2025-02-14 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-14 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-14 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-14 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-14 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-14 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-15 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | COMPLETED
2025-02-15 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | COMPLETED
2025-02-15 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-15 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-15 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-15 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-15 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-16 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | COMPLETED
2025-02-16 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-16 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-16 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-16 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-16 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-16 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-17 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | COMPLETED
2025-02-17 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-17 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-17 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-17 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-17 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-18 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | COMPLETED
2025-02-18 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-18 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-18 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-18 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-18 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-18 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-18 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-19 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-19 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-19 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-19 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-19 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-19 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-20 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-20 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-20 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-20 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | COMPLETED
2025-02-20 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-20 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-21 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-21 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-21 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-21 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | COMPLETED
2025-02-21 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-21 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-22 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-22 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-22 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-22 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | COMPLETED
2025-02-22 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-22 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-23 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-23 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-23 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-23 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | COMPLETED
2025-02-23 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-23 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-24 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-24 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | COMPLETED
2025-02-24 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-24 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-24 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | COMPLETED
2025-02-24 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | COMPLETED
2025-02-24 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-24 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-02-25 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | COMPLETED
2025-02-25 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-25 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-25 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-02-25 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | COMPLETED
2025-02-25 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-25 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-02-26 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | COMPLETED
2025-02-26 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-26 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-02-26 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | COMPLETED
2025-02-26 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-26 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-02-27 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | COMPLETED
2025-02-27 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-27 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-02-27 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | COMPLETED
2025-02-27 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-27 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-02-28 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | COMPLETED
2025-02-28 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-02-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-28 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-02-28 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | COMPLETED
2025-02-28 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-28 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-01 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-01 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | COMPLETED
2025-03-01 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-03-01 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-02 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-02 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | COMPLETED
2025-03-02 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-03-02 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-03 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-03 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | COMPLETED
2025-03-03 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-03-03 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-04 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-04 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | COMPLETED
2025-03-04 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-03-04 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-05 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-05 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-05 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | COMPLETED
2025-03-05 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-06 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-06 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-06 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | COMPLETED
2025-03-06 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-07 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | COMPLETED
2025-03-07 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-07 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-07 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | COMPLETED
2025-03-07 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-08 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | COMPLETED
2025-03-08 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-08 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-08 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | COMPLETED
2025-03-08 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-09 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | COMPLETED
2025-03-09 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-09 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-09 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | COMPLETED
2025-03-09 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-10 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | COMPLETED
2025-03-10 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-10 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-10 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | COMPLETED
2025-03-10 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-11 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | COMPLETED
2025-03-11 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-11 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-11 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | COMPLETED
2025-03-11 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-12 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-12 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-12 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-12 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | COMPLETED
2025-03-12 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-13 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-13 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-13 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-13 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | COMPLETED
2025-03-13 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-14 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-14 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-14 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-14 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | COMPLETED
2025-03-14 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-15 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-15 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-15 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-15 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | COMPLETED
2025-03-15 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-16 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-16 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-16 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-16 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | COMPLETED
2025-03-16 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-17 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-17 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-17 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-17 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | COMPLETED
2025-03-17 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-18 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-18 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-18 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-18 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | COMPLETED
2025-03-18 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-19 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-19 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-19 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-19 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | COMPLETED
2025-03-19 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-20 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-20 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-20 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-20 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | COMPLETED
2025-03-20 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-21 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-21 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-21 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-21 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | COMPLETED
2025-03-21 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-22 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-22 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-22 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-22 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | COMPLETED
2025-03-22 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-23 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-23 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-23 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-23 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | COMPLETED
2025-03-23 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-24 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-24 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-24 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-24 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | COMPLETED
2025-03-24 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-25 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-25 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-25 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-25 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | COMPLETED
2025-03-25 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-26 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-26 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-26 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-26 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | COMPLETED
2025-03-26 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-26 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-27 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-27 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-27 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-27 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | COMPLETED
2025-03-27 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-27 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-28 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-28 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-28 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-28 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-29 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-29 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-29 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-29 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-29 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-03-30 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-30 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-03-30 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-30 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-30 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-03-31 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-03-31 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-31 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-03-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-31 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-03-31 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-31 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-03-31 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-01 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-01 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-01 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-04-01 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-01 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-02 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-02 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-02 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-04-02 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-02 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-03 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-03 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-03 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-04-03 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-03 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-04 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-04 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-04 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-04-04 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-04 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-05 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-05 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-05 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-04-05 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-05 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-05 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-06 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-06 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-06 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-06 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-06 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-07 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-07 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-07 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-07 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-08 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-08 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-08 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-08 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-09 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-09 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-09 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-09 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-09 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-09 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-10 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-10 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-10 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-10 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-11 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-11 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-11 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-11 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-12 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-12 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-12 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-13 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-13 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-13 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-14 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-14 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-14 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-14 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-15 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-15 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-15 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-16 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-16 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-16 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-17 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-17 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-17 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-18 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-18 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-18 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-18 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-18 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-19 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-19 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-19 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-20 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-20 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-20 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-21 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-21 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-21 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-22 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-22 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-22 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-23 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-23 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-24 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-24 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-25 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-25 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-26 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-26 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-27 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-27 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-28 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-28 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-29 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-29 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-30 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-30 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-07-05 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-06 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-06 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-07 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-07 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-08 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-08 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-09 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-09 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-09 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-10 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-10 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-10 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-11 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-11 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-11 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-12 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-12 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-12 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-13 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-13 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-13 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-14 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-14 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-14 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-15 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-15 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-15 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-15 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-16 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-16 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-16 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-16 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-16 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-16 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-17 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-17 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-17 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-17 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-17 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-17 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-18 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-18 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-18 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-18 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-18 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-18 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-18 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-19 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-19 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-19 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-19 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-19 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-19 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-19 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-20 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-20 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-20 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-20 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-20 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-20 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-20 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-21 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-21 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-21 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-21 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-21 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-21 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-21 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-21 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-22 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-22 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-22 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-22 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-22 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-22 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-22 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-22 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-23 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-23 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-23 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-23 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-23 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-23 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-23 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-23 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-24 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-24 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-24 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-24 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-24 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-24 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-24 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-24 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-25 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-25 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-25 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-25 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-25 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-25 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-25 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-25 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-26 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-26 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-26 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-26 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-26 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-26 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-26 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-26 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-27 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-07-27 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-27 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-27 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-27 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-27 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-27 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-28 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-07-28 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-28 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-28 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-28 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-28 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-28 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-29 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-07-29 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-29 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-29 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-29 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-29 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-29 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-30 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-07-30 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-30 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-30 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-30 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-30 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-30 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-31 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-07-31 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-31 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-31 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-31 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-31 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-31 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-08-01 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-08-01 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-08-01 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-08-01 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-01 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-01 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-01 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-01 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-08-01 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-08-02 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-08-02 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-08-02 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | COMPLETED
2025-08-02 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-08-02 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-02 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-02 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-02 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-02 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-02 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-02 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-08-03 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-08-03 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | COMPLETED
2025-08-03 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-08-03 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-03 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-03 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-03 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-03 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-03 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-03 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-08-04 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-08-04 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | COMPLETED
2025-08-04 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | COMPLETED
2025-08-04 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-04 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-04 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-04 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-04 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-04 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-04 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-05 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-08-05 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | COMPLETED
2025-08-05 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | COMPLETED
2025-08-05 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-05 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-05 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-05 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-05 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-05 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-05 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-06 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | COMPLETED
2025-08-06 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | COMPLETED
2025-08-06 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-06 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-06 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-06 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-06 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-06 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-06 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-07 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-07 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | COMPLETED
2025-08-07 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | COMPLETED
2025-08-07 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-07 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-07 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-07 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-07 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-07 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-07 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-07 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-07 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-08 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-08 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | COMPLETED
2025-08-08 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | COMPLETED
2025-08-08 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-08 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-08 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-08 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-08 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-08 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-08 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-08 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-08 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-08 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-08 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-09 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-09 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | COMPLETED
2025-08-09 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-09 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-09 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-09 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-09 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-09 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-09 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-09 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-09 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-09 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-09 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-09 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-09 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-10 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-10 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | COMPLETED
2025-08-10 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-10 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-10 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-10 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-10 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-10 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-10 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-10 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-10 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-10 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-11 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-11 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | COMPLETED
2025-08-11 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-11 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-11 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-11 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-11 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-11 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-11 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-11 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-11 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-12 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-12 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-12 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-12 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-12 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-12 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-12 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-12 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-12 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-12 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-12 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-12 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-13 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-13 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-13 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-13 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-13 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-13 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-13 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-13 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-13 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-13 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-13 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-13 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-13 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-14 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-14 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-14 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-14 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-14 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-14 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-14 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-14 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-14 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-14 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-14 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-14 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-14 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-14 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-15 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-15 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-15 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-15 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-15 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-15 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-15 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-15 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-15 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-15 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-15 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-15 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | COMPLETED
2025-08-15 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-15 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-16 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-16 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-16 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-16 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-16 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-16 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-16 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-16 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-16 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-16 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-16 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-16 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | COMPLETED
2025-08-16 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-16 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-17 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-17 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-17 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-17 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-17 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-17 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-17 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-17 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-17 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-17 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-17 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-17 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | COMPLETED
2025-08-17 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-17 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-18 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-18 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-18 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-18 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-18 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-18 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-18 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-18 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-18 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-18 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-18 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-18 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | COMPLETED
2025-08-18 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | COMPLETED
2025-08-18 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-18 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-19 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-19 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-19 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-19 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-19 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-19 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-19 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-19 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-19 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-19 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-19 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-19 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | COMPLETED
2025-08-19 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | COMPLETED
2025-08-19 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-19 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-20 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-20 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-20 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-20 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-20 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-20 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-20 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-20 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-20 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-20 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-20 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-20 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-20 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | COMPLETED
2025-08-20 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-20 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-20 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-21 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-21 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-21 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-21 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-21 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-21 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-21 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-21 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-21 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-21 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-21 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-21 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | COMPLETED
2025-08-21 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-21 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-21 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-22 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-22 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-22 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-22 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-22 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-22 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-22 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-22 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-22 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-22 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-22 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | COMPLETED
2025-08-22 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-22 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-22 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-23 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-23 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-23 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-23 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-23 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-23 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-23 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-23 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-23 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-23 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-23 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-23 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-24 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-24 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-24 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-24 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-24 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-24 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-24 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-24 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-24 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-24 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-24 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-24 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-25 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-25 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-25 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-25 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-25 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-25 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-25 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-25 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-25 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-25 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-25 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-25 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-25 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-25 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-25 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-26 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-26 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-26 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-26 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-26 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-26 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-26 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-26 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-26 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-26 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-26 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-27 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-27 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-27 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-27 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-27 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-27 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-27 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-27 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-27 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-27 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-27 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-28 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-28 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-28 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-28 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-28 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-28 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-28 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-28 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-08-28 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-28 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-28 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-29 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-29 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-29 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-08-29 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-29 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-08-29 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-29 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-08-29 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-08-29 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-29 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-29 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-29 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-30 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-30 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-30 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-30 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-30 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-08-30 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-30 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-08-30 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-30 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-30 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-08-30 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-08-30 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-08-30 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-30 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-08-30 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-08-30 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-30 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-30 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-31 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-31 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-31 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-31 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-31 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-08-31 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-31 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-08-31 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-31 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-31 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-08-31 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-08-31 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-08-31 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | COMPLETED
2025-08-31 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-08-31 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-08-31 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-31 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-31 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-09-01 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-09-01 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-09-01 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-01 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-09-01 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-01 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-01 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-09-01 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-09-01 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-09-01 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-01 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-09-01 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-01 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | COMPLETED
2025-09-01 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-01 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-01 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-09-01 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-09-02 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-09-02 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-09-02 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-02 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-09-02 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-02 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-02 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-09-02 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-02 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-09-02 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-02 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-09-02 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-02 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | COMPLETED
2025-09-02 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-02 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-02 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-09-02 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-03 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-09-03 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | COMPLETED
2025-09-03 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-03 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-03 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-09-03 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-03 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-03 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-03 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | COMPLETED
2025-09-03 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-03 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-03 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-09-03 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-04 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-04 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | COMPLETED
2025-09-04 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-04 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-04 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-09-04 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-04 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-04 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-04 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-04 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | COMPLETED
2025-09-04 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-04 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-04 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-04 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-05 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-05 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | COMPLETED
2025-09-05 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-05 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-05 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-09-05 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-05 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-05 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-05 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-05 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | COMPLETED
2025-09-05 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-05 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-05 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-05 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-06 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-06 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | COMPLETED
2025-09-06 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-06 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-06 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-06 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-06 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-06 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-06 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-06 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | COMPLETED
2025-09-06 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-06 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-06 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-06 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-07 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-07 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | COMPLETED
2025-09-07 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-07 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-07 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-07 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-07 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-07 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-07 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-07 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | COMPLETED
2025-09-07 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-07 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-07 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-07 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-08 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-08 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-08 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-08 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | COMPLETED
2025-09-08 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-08 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-08 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-08 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-08 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-08 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-08 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-08 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-08 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-08 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | COMPLETED
2025-09-08 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-08 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-08 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-08 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-09 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-09 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-09 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-09 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | COMPLETED
2025-09-09 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-09 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-09 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-09 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-09 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-09 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-09 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | COMPLETED
2025-09-09 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-09 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-09 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-10 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-10 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-10 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-10 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | COMPLETED
2025-09-10 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-10 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-10 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-10 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-10 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-10 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-10 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-10 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-10 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-10 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-11 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-11 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-11 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-11 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | COMPLETED
2025-09-11 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-11 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-11 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-11 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-11 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-11 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-11 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-11 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-11 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-11 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-11 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-12 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-12 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-12 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-12 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-12 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-12 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-12 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-12 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-12 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-12 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-12 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-12 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-12 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-12 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-13 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-13 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-13 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-13 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-13 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-13 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-13 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-13 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-13 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-13 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-13 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-13 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-13 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-13 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-13 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-14 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-14 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-14 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-14 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-14 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-14 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-14 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-14 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-14 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-14 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-14 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-14 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-14 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-14 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-14 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-14 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-14 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-14 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-14 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-14 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-14 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-15 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-15 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-15 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-15 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-15 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-15 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-15 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-15 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-15 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-15 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-15 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-15 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-15 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-15 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-15 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-15 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-15 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-15 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-15 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-15 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-15 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-16 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-16 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-16 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-16 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-16 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-16 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-16 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-16 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-16 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-16 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-16 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-16 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-16 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-16 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-16 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | COMPLETED
2025-09-16 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-16 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-16 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-16 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | COMPLETED
2025-09-17 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-17 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-17 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-17 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-17 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-17 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-17 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-17 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-17 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-17 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-17 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-17 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-17 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | COMPLETED
2025-09-17 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-17 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-17 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-17 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | COMPLETED
2025-09-18 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-18 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-18 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-18 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-18 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-18 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-18 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-18 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-18 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-18 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-18 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-18 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-18 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-18 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | COMPLETED
2025-09-18 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-18 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-18 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-18 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | COMPLETED
2025-09-19 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-19 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-19 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-19 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-19 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-19 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-19 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-19 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-19 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-19 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-19 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-19 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-19 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-19 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-19 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | COMPLETED
2025-09-19 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-19 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-19 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | COMPLETED
2025-09-20 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-20 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-20 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-20 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-20 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-20 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-20 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-20 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-20 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-20 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-20 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-20 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-20 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-20 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-20 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | COMPLETED
2025-09-20 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-20 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-20 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | COMPLETED
2025-09-21 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-21 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-21 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-21 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-21 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-21 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-21 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-21 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-21 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-21 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-21 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-21 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-21 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-21 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | COMPLETED
2025-09-21 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-21 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-21 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | COMPLETED
2025-09-22 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-22 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-22 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-22 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-22 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-22 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-22 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-22 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-22 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-22 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-22 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-22 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-22 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | COMPLETED
2025-09-22 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-22 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-22 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | COMPLETED
2025-09-23 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-23 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-23 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-23 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-23 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-23 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-23 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-23 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-23 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-23 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-23 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-23 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-23 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | COMPLETED
2025-09-23 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-23 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | COMPLETED
2025-09-24 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-24 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-24 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-24 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-24 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-24 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-24 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-24 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-24 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-24 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-24 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-24 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-24 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | COMPLETED
2025-09-24 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-24 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | COMPLETED
2025-09-25 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-25 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-25 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-25 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-25 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-25 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-25 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-25 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-25 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-25 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-25 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | COMPLETED
2025-09-25 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-25 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | COMPLETED
2025-09-26 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-26 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-26 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-26 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | COMPLETED
2025-09-26 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-26 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-26 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-26 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-26 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | COMPLETED
2025-09-26 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | COMPLETED
2025-09-26 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | COMPLETED
2025-09-27 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-27 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-27 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | COMPLETED
2025-09-27 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-27 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-27 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-27 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-27 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | COMPLETED
2025-09-27 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | COMPLETED
2025-09-27 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | COMPLETED
2025-09-28 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-28 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-28 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | COMPLETED
2025-09-28 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-28 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-28 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-28 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | COMPLETED
2025-09-28 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | COMPLETED
2025-09-28 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | COMPLETED
2025-09-29 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-29 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-29 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | COMPLETED
2025-09-29 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-29 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-29 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-29 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | COMPLETED
2025-09-29 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | COMPLETED
2025-09-30 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-30 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | COMPLETED
2025-09-30 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-30 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-30 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | COMPLETED
2025-09-30 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | COMPLETED
2024-09-01 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416 | 2/8 | Completed
2024-09-02 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416 | 2/8 | Completed
2024-09-03 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416 | 2/8 | Completed
2024-09-04 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416 | 2/8 | Completed
2024-09-05 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416 | 2/8 | Completed
2024-09-06 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416 | 2/8 | Completed
2024-09-07 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416 | 2/8 | Completed
2024-09-08 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416 | 2/8 | Completed
2024-09-09 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416 | 2/8 | Completed
2024-09-10 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416 | 2/8 | Completed
2024-09-11 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416 | 2/8 | Completed
2024-09-12 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416 | 2/8 | Completed
2024-09-13 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416 | 2/8 | Completed
2024-09-14 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416 | 2/8 | Completed
2024-09-15 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416 | 2/8 | Completed
2024-09-16 | 2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416 | 2/8 | Completed
2024-09-16 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | Completed
2024-09-16 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | Completed
2024-09-17 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | Completed
2024-09-17 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | Completed
2024-09-18 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | Completed
2024-09-18 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | Completed
2024-09-19 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | Completed
2024-09-19 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | Completed
2024-09-20 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | Completed
2024-09-20 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | Completed
2024-09-21 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | Completed
2024-09-21 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | Completed
2024-09-22 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | Completed
2024-09-22 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | Completed
2024-09-23 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | Completed
2024-09-23 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | Completed
2024-09-24 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | Completed
2024-09-24 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | Completed
2024-09-25 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | Completed
2024-09-25 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | Completed
2024-09-26 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | Completed
2024-09-26 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | Completed
2024-09-27 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | Completed
2024-09-27 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | Completed
2024-09-28 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | Completed
2024-09-28 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | Completed
2024-09-29 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | Completed
2024-09-29 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | Completed
2024-09-30 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | Completed
2024-10-01 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | Completed
2024-10-01 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | Completed
2024-10-02 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | Completed
2024-10-03 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | Completed
2024-10-03 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | Completed
2024-10-04 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | Completed
2024-10-04 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | Completed
2024-10-05 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | Completed
2024-10-05 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | Completed
2024-10-06 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | Completed
2024-10-06 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | Completed
2024-10-07 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | Completed
2024-10-07 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | Completed
2024-10-08 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | Completed
2024-10-08 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | Completed
2024-10-09 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | Completed
2024-10-09 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | Completed
2024-10-10 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | Completed
2024-10-10 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | Completed
2024-10-11 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | Completed
2024-10-11 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | Completed
2024-10-12 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | Completed
2024-10-12 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | Completed
2024-10-13 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | Completed
2024-10-13 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | Completed
2024-10-14 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | Completed
2024-10-14 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | Completed
2024-10-15 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | Completed
2024-10-15 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | Completed
2024-10-15 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | Completed
2024-10-16 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | Completed
2024-10-16 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | Completed
2024-10-17 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | Completed
2024-10-17 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | Completed
2024-10-18 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | Completed
2024-10-18 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | Completed
2024-10-19 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | Completed
2024-10-19 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | Completed
2024-10-20 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | Completed
2024-10-20 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | Completed
2024-10-21 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | Completed
2024-10-21 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | Completed
2024-10-22 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | Completed
2024-10-22 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | Completed
2024-10-23 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | Completed
2024-10-23 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | Completed
2024-10-24 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | Completed
2024-10-24 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | Completed
2024-10-24 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | Completed
2024-10-24 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | Completed
2024-10-25 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | Completed
2024-10-25 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | Completed
2024-10-26 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | Completed
2024-10-26 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | Completed
2024-10-27 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | Completed
2024-10-27 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | Completed
2024-10-28 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | Completed
2024-10-28 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | Completed
2024-10-29 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | Completed
2024-10-29 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | Completed
2024-10-30 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | Completed
2024-10-31 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | Completed
2024-11-01 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | Completed
2024-11-01 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | Completed
2024-11-02 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | Completed
2024-11-02 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | Completed
2024-11-03 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | Completed
2024-11-03 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | Completed
2024-11-04 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | Completed
2024-11-04 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | Completed
2024-11-05 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | Completed
2024-11-05 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | Completed
2024-11-06 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | Completed
2024-11-06 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | Completed
2024-11-07 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | Completed
2024-11-07 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | Completed
2024-11-08 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | Completed
2024-11-08 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | Completed
2024-11-09 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | Completed
2024-11-09 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | Completed
2024-11-10 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-10 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | Completed
2024-11-10 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | Completed
2024-11-10 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | Completed
2024-11-10 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | Completed
2024-11-10 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | Completed
2024-11-10 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-11 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-11 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | Completed
2024-11-11 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | Completed
2024-11-11 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | Completed
2024-11-11 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | Completed
2024-11-11 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-12 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-12 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | Completed
2024-11-12 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | Completed
2024-11-12 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | Completed
2024-11-12 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | Completed
2024-11-12 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-13 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-13 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | Completed
2024-11-13 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | Completed
2024-11-13 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | Completed
2024-11-13 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | Completed
2024-11-13 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-14 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-14 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | Completed
2024-11-14 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | Completed
2024-11-14 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | Completed
2024-11-14 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | Completed
2024-11-14 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | Completed
2024-11-14 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-15 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-15 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | Completed
2024-11-15 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | Completed
2024-11-15 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | Completed
2024-11-15 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | Completed
2024-11-15 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-16 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-16 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | Completed
2024-11-16 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | Completed
2024-11-16 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | Completed
2024-11-16 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | Completed
2024-11-16 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-17 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-17 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | Completed
2024-11-17 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | Completed
2024-11-17 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | Completed
2024-11-17 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | Completed
2024-11-17 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | Completed
2024-11-17 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-18 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-18 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | Completed
2024-11-18 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | Completed
2024-11-18 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | Completed
2024-11-18 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | Completed
2024-11-18 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-19 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-19 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | Completed
2024-11-19 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | Completed
2024-11-19 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | Completed
2024-11-19 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | Completed
2024-11-19 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-20 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-20 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | Completed
2024-11-20 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | Completed
2024-11-20 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | Completed
2024-11-20 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | Completed
2024-11-20 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-21 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-21 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | Completed
2024-11-21 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | Completed
2024-11-21 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | Completed
2024-11-21 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | Completed
2024-11-21 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-22 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-22 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | Completed
2024-11-22 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | Completed
2024-11-22 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | Completed
2024-11-22 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | Completed
2024-11-22 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | Completed
2024-11-22 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-23 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-23 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | Completed
2024-11-23 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | Completed
2024-11-23 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | Completed
2024-11-23 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | Completed
2024-11-23 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-24 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-24 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | Completed
2024-11-24 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | Completed
2024-11-24 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | Completed
2024-11-24 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | Completed
2024-11-24 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-25 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-25 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | Completed
2024-11-25 | 2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | Completed
2024-11-25 | 2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | Completed
2024-11-25 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-26 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-26 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | Completed
2024-11-26 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | Completed
2024-11-26 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-27 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-27 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | Completed
2024-11-27 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | Completed
2024-11-28 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-28 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | Completed
2024-11-28 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | Completed
2024-11-28 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | Completed
2024-11-28 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | Completed
2024-11-29 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-29 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | Completed
2024-11-29 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | Completed
2024-11-29 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | Completed
2024-11-29 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | Completed
2024-11-29 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | Completed
2024-11-30 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | Completed
2024-11-30 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | Completed
2024-11-30 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | Completed
2024-11-30 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | Completed
2024-11-30 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | Completed
2024-11-30 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | Completed
2024-12-01 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | Completed
2024-12-01 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | Completed
2024-12-01 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | Completed
2024-12-01 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | Completed
2024-12-01 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | Completed
2024-12-01 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | Completed
2024-12-01 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | Completed
2024-12-02 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | Completed
2024-12-02 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | Completed
2024-12-02 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | Completed
2024-12-02 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | Completed
2024-12-02 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | Completed
2024-12-02 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | Completed
2024-12-02 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | Completed
2024-12-03 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | Completed
2024-12-03 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | Completed
2024-12-03 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | Completed
2024-12-03 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | Completed
2024-12-03 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | Completed
2024-12-03 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | Completed
2024-12-03 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | Completed
2024-12-04 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | Completed
2024-12-04 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | Completed
2024-12-04 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | Completed
2024-12-04 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | Completed
2024-12-04 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | Completed
2024-12-04 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | Completed
2024-12-05 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | Completed
2024-12-05 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | Completed
2024-12-05 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | Completed
2024-12-05 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | Completed
2024-12-05 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | Completed
2024-12-05 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | Completed
2024-12-06 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | Completed
2024-12-06 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | Completed
2024-12-06 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | Completed
2024-12-06 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | Completed
2024-12-06 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | Completed
2024-12-06 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | Completed
2024-12-06 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | Completed
2024-12-07 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | Completed
2024-12-07 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | Completed
2024-12-07 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | Completed
2024-12-07 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | Completed
2024-12-07 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | Completed
2024-12-07 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | Completed
2024-12-08 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | Completed
2024-12-08 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | Completed
2024-12-08 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | Completed
2024-12-08 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | Completed
2024-12-08 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | Completed
2024-12-08 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | Completed
2024-12-09 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | Completed
2024-12-09 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | Completed
2024-12-09 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | Completed
2024-12-09 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | Completed
2024-12-09 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | Completed
2024-12-09 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | Completed
2024-12-10 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | Completed
2024-12-10 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | Completed
2024-12-10 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | Completed
2024-12-10 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | Completed
2024-12-10 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | Completed
2024-12-10 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | Completed
2024-12-10 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | Completed
2024-12-11 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | Completed
2024-12-11 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | Completed
2024-12-11 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | Completed
2024-12-11 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | Completed
2024-12-11 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | Completed
2024-12-11 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | Completed
2024-12-12 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | Completed
2024-12-12 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | Completed
2024-12-12 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | Completed
2024-12-12 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | Completed
2024-12-12 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | Completed
2024-12-12 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | Completed
2024-12-12 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | Completed
2024-12-12 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | Completed
2024-12-13 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | Completed
2024-12-13 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | Completed
2024-12-13 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | Completed
2024-12-13 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | Completed
2024-12-13 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | Completed
2024-12-13 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | Completed
2024-12-13 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | Completed
2024-12-14 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | Completed
2024-12-14 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | Completed
2024-12-14 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | Completed
2024-12-14 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | Completed
2024-12-14 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | Completed
2024-12-14 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | Completed
2024-12-15 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | Completed
2024-12-15 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | Completed
2024-12-15 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | Completed
2024-12-15 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | Completed
2024-12-15 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | Completed
2024-12-15 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | Completed
2024-12-16 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | Completed
2024-12-16 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | Completed
2024-12-16 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | Completed
2024-12-16 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | Completed
2024-12-16 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | Completed
2024-12-16 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | Completed
2024-12-17 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | Completed
2024-12-17 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | Completed
2024-12-17 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | Completed
2024-12-17 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | Completed
2024-12-17 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | Completed
2024-12-18 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | Completed
2024-12-18 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | Completed
2024-12-18 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | Completed
2024-12-18 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | Completed
2024-12-18 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | Completed
2024-12-18 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | Completed
2024-12-19 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | Completed
2024-12-19 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | Completed
2024-12-19 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | Completed
2024-12-19 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | Completed
2024-12-19 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | Completed
2024-12-19 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | Completed
2024-12-20 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | Completed
2024-12-20 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | Completed
2024-12-20 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | Completed
2024-12-20 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | Completed
2024-12-20 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | Completed
2024-12-20 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | Completed
2024-12-21 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | Completed
2024-12-21 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | Completed
2024-12-21 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | Completed
2024-12-21 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | Completed
2024-12-21 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | Completed
2024-12-21 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | Completed
2024-12-22 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | Completed
2024-12-22 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | Completed
2024-12-22 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | Completed
2024-12-22 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | Completed
2024-12-22 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | Completed
2024-12-22 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | Completed
2024-12-23 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | Completed
2024-12-23 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | Completed
2024-12-23 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | Completed
2024-12-23 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | Completed
2024-12-23 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | Completed
2024-12-24 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | Completed
2024-12-24 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | Completed
2024-12-24 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | Completed
2024-12-24 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | Completed
2024-12-24 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | Completed
2024-12-24 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | Completed
2024-12-24 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | Completed
2024-12-25 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | Completed
2024-12-25 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | Completed
2024-12-25 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | Completed
2024-12-25 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | Completed
2024-12-25 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | Completed
2024-12-25 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | Completed
2024-12-25 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | Completed
2024-12-26 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | Completed
2024-12-26 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | Completed
2024-12-26 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | Completed
2024-12-26 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | Completed
2024-12-26 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | Completed
2024-12-26 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | Completed
2024-12-26 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | Completed
2024-12-27 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | Completed
2024-12-27 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | Completed
2024-12-27 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | Completed
2024-12-27 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | Completed
2024-12-27 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | Completed
2024-12-27 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | Completed
2024-12-27 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | Completed
2024-12-28 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | Completed
2024-12-28 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | Completed
2024-12-28 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | Completed
2024-12-28 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | Completed
2024-12-28 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | Completed
2024-12-28 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | Completed
2024-12-28 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | Completed
2024-12-29 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | Completed
2024-12-29 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | Completed
2024-12-29 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | Completed
2024-12-29 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | Completed
2024-12-29 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | Completed
2024-12-29 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | Completed
2024-12-29 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | Completed
2024-12-30 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | Completed
2024-12-30 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | Completed
2024-12-30 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | Completed
2024-12-30 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | Completed
2024-12-30 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | Completed
2024-12-30 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | Completed
2024-12-30 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | Completed
2024-12-31 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | Completed
2024-12-31 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | Completed
2024-12-31 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | Completed
2024-12-31 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | Completed
2024-12-31 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | Completed
2024-12-31 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | Completed
2024-12-31 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | Completed
2025-01-01 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | Completed
2025-01-01 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | Completed
2025-01-01 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | Completed
2025-01-01 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | Completed
2025-01-01 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | Completed
2025-01-01 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | Completed
2025-01-02 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | Completed
2025-01-02 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | Completed
2025-01-02 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | Completed
2025-01-02 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | Completed
2025-01-02 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | Completed
2025-01-02 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | Completed
2025-01-03 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | Completed
2025-01-03 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | Completed
2025-01-03 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | Completed
2025-01-03 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | Completed
2025-01-03 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | Completed
2025-01-03 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | Completed
2025-01-03 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | Completed
2025-01-04 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | Completed
2025-01-04 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | Completed
2025-01-04 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | Completed
2025-01-04 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | Completed
2025-01-04 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | Completed
2025-01-04 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | Completed
2025-01-05 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | Completed
2025-01-05 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | Completed
2025-01-05 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | Completed
2025-01-05 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | Completed
2025-01-05 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | Completed
2025-01-06 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | Completed
2025-01-06 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | Completed
2025-01-06 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | Completed
2025-01-06 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | Completed
2025-01-06 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | Completed
2025-01-07 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | Completed
2025-01-07 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | Completed
2025-01-07 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | Completed
2025-01-07 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | Completed
2025-01-07 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | Completed
2025-01-07 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | Completed
2025-01-07 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | Completed
2025-01-08 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | Completed
2025-01-08 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | Completed
2025-01-08 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | Completed
2025-01-08 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | Completed
2025-01-08 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/8 | Completed
2025-01-08 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | Completed
2025-01-08 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | Completed
2025-01-09 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | Completed
2025-01-09 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | Completed
2025-01-09 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | Completed
2025-01-09 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | Completed
2025-01-09 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/8 | Completed
2025-01-09 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | Completed
2025-01-09 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | Completed
2025-01-10 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | Completed
2025-01-10 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | Completed
2025-01-10 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416 | 17/3 | Completed
2025-01-10 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | Completed
2025-01-10 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | Completed
2025-01-10 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/8 | Completed
2025-01-10 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | Completed
2025-01-10 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | Completed
2025-01-10 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-11 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | Completed
2025-01-11 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | Completed
2025-01-11 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | Completed
2025-01-11 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416 | 17/3 | Completed
2025-01-11 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | Completed
2025-01-11 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/8 | Completed
2025-01-11 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | Completed
2025-01-11 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | Completed
2025-01-11 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-12 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | Completed
2025-01-12 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | Completed
2025-01-12 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416 | 17/3 | Completed
2025-01-12 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | Completed
2025-01-12 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/8 | Completed
2025-01-12 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | Completed
2025-01-12 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | Completed
2025-01-12 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-13 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | Completed
2025-01-13 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | Completed
2025-01-13 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416 | 17/3 | Completed
2025-01-13 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | Completed
2025-01-13 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/8 | Completed
2025-01-13 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | Completed
2025-01-13 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | Completed
2025-01-13 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-14 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | Completed
2025-01-14 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | Completed
2025-01-14 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416 | 17/3 | Completed
2025-01-14 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | Completed
2025-01-14 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/8 | Completed
2025-01-14 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | Completed
2025-01-14 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | Completed
2025-01-14 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-15 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | Completed
2025-01-15 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | Completed
2025-01-15 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416 | 17/3 | Completed
2025-01-15 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | Completed
2025-01-15 | 2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/8 | Completed
2025-01-15 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | Completed
2025-01-15 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | Completed
2025-01-15 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-16 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416 | 36/5 | Completed
2025-01-16 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | Completed
2025-01-16 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416 | 17/3 | Completed
2025-01-16 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | Completed
2025-01-16 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/7 | Completed
2025-01-16 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | Completed
2025-01-16 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | Completed
2025-01-16 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-17 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416 | 36/5 | Completed
2025-01-17 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | Completed
2025-01-17 | 2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416 | 17/3 | Completed
2025-01-17 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | Completed
2025-01-17 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/7 | Completed
2025-01-17 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | Completed
2025-01-17 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | Completed
2025-01-17 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-18 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416 | 36/5 | Completed
2025-01-18 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | Completed
2025-01-18 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416 | 17/2 | Completed
2025-01-18 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 35/1 | Completed
2025-01-18 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/7 | Completed
2025-01-18 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | Completed
2025-01-18 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 19/9 | Completed
2025-01-18 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-19 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416 | 36/5 | Completed
2025-01-19 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | Completed
2025-01-19 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416 | 17/2 | Completed
2025-01-19 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 35/1 | Completed
2025-01-19 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/7 | Completed
2025-01-19 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | Completed
2025-01-19 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 19/9 | Completed
2025-01-19 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-20 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416 | 36/5 | Completed
2025-01-20 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416 | 17/2 | Completed
2025-01-20 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 35/1 | Completed
2025-01-20 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/7 | Completed
2025-01-20 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | Completed
2025-01-20 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 19/9 | Completed
2025-01-20 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-21 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416 | 36/5 | Completed
2025-01-21 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416 | 17/2 | Completed
2025-01-21 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 35/1 | Completed
2025-01-21 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/7 | Completed
2025-01-21 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | Completed
2025-01-21 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 19/9 | Completed
2025-01-21 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-22 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416 | 36/5 | Completed
2025-01-22 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416 | 17/2 | Completed
2025-01-22 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 35/1 | Completed
2025-01-22 | 2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/7 | Completed
2025-01-22 | 2025-01-22 | 2025-01-25 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 12/4 | Completed
2025-01-22 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 19/9 | Completed
2025-01-22 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-23 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416 | 36/5 | Completed
2025-01-23 | 2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416 | 17/2 | Completed
2025-01-23 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 35/1 | Completed
2025-01-23 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416 | 7/6 | Completed
2025-01-23 | 2025-01-22 | 2025-01-25 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 12/4 | Completed
2025-01-23 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 19/9 | Completed
2025-01-23 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-24 | 2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416 | 36/5 | Completed
2025-01-24 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416 | 17/5 | Completed
2025-01-24 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 35/1 | Completed
2025-01-24 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416 | 7/6 | Completed
2025-01-24 | 2025-01-22 | 2025-01-25 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 12/4 | Completed
2025-01-24 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 19/9 | Completed
2025-01-24 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-25 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | Completed
2025-01-25 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416 | 17/5 | Completed
2025-01-25 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 35/1 | Completed
2025-01-25 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416 | 7/6 | Completed
2025-01-25 | 2025-01-22 | 2025-01-25 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 12/4 | Completed
2025-01-25 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 19/9 | Completed
2025-01-25 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-26 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | Completed
2025-01-26 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/1 | Completed
2025-01-26 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416 | 17/5 | Completed
2025-01-26 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 35/1 | Completed
2025-01-26 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416 | 7/6 | Completed
2025-01-26 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/5 | Completed
2025-01-26 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 19/9 | Completed
2025-01-26 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-27 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | Completed
2025-01-27 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/1 | Completed
2025-01-27 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416 | 17/5 | Completed
2025-01-27 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 35/1 | Completed
2025-01-27 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416 | 7/6 | Completed
2025-01-27 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/5 | Completed
2025-01-27 | 2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 19/9 | Completed
2025-01-27 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-28 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | Completed
2025-01-28 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/1 | Completed
2025-01-28 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416 | 17/5 | Completed
2025-01-28 | 2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 35/1 | Completed
2025-01-28 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416 | 7/6 | Completed
2025-01-28 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/5 | Completed
2025-01-28 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416 | 20/0 | Completed
2025-01-28 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-29 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | Completed
2025-01-29 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/1 | Completed
2025-01-29 | 2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416 | 17/5 | Completed
2025-01-29 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416 | 35/0 | Completed
2025-01-29 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416 | 7/6 | Completed
2025-01-29 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/5 | Completed
2025-01-29 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416 | 20/0 | Completed
2025-01-29 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-30 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | Completed
2025-01-30 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/1 | Completed
2025-01-30 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416 | 17/7 | Completed
2025-01-30 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416 | 35/0 | Completed
2025-01-30 | 2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416 | 7/6 | Completed
2025-01-30 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/5 | Completed
2025-01-30 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416 | 20/0 | Completed
2025-01-30 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-31 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/1 | Completed
2025-01-31 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416 | 17/7 | Completed
2025-01-31 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416 | 35/0 | Completed
2025-01-31 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416 | 7/5 | Completed
2025-01-31 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/5 | Completed
2025-01-31 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416 | 20/0 | Completed
2025-01-31 | 2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-02-01 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/1 | Completed
2025-02-01 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416 | 17/7 | Completed
2025-02-01 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416 | 35/0 | Completed
2025-02-01 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416 | 7/5 | Completed
2025-02-01 | 2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/5 | Completed
2025-02-01 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416 | 20/0 | Completed
2025-02-02 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | Completed
2025-02-02 | 2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/1 | Completed
2025-02-02 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416 | 17/7 | Completed
2025-02-02 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416 | 35/0 | Completed
2025-02-02 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416 | 7/5 | Completed
2025-02-02 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | Completed
2025-02-02 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416 | 20/0 | Completed
2025-02-03 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | Completed
2025-02-03 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | Completed
2025-02-03 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416 | 17/7 | Completed
2025-02-03 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416 | 35/0 | Completed
2025-02-03 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416 | 7/5 | Completed
2025-02-03 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | Completed
2025-02-03 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416 | 20/0 | Completed
2025-02-04 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | Completed
2025-02-04 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | Completed
2025-02-04 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416 | 17/7 | Completed
2025-02-04 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416 | 35/0 | Completed
2025-02-04 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416 | 7/5 | Completed
2025-02-04 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | Completed
2025-02-04 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416 | 20/0 | Completed
2025-02-05 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | Completed
2025-02-05 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | Completed
2025-02-05 | 2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416 | 17/7 | Completed
2025-02-05 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416 | 35/0 | Completed
2025-02-05 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416 | 7/5 | Completed
2025-02-05 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | Completed
2025-02-05 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416 | 20/0 | Completed
2025-02-06 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | Completed
2025-02-06 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | Completed
2025-02-06 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416 | 35/0 | Completed
2025-02-06 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416 | 7/5 | Completed
2025-02-06 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | Completed
2025-02-06 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416 | 20/0 | Completed
2025-02-07 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | Completed
2025-02-07 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | Completed
2025-02-07 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416 | 35/0 | Completed
2025-02-07 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416 | 7/5 | Completed
2025-02-07 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | Completed
2025-02-08 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | Completed
2025-02-08 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416 | 35/0 | Completed
2025-02-08 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416 | 7/5 | Completed
2025-02-08 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | Completed
2025-02-09 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | Completed
2025-02-09 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416 | 35/0 | Completed
2025-02-09 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416 | 7/5 | Completed
2025-02-09 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416 | 8/1 | Completed
2025-02-10 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | Completed
2025-02-10 | 2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416 | 35/0 | Completed
2025-02-10 | 2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416 | 7/5 | Completed
2025-02-10 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416 | 8/1 | Completed
2025-02-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-11 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416 | 7/4 | Completed
2025-02-11 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416 | 8/1 | Completed
2025-02-12 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-02-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-12 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416 | 7/4 | Completed
2025-02-12 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416 | 8/1 | Completed
2025-02-12 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | Completed
2025-02-13 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-02-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-13 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416 | 7/4 | Completed
2025-02-13 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416 | 8/1 | Completed
2025-02-13 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | Completed
2025-02-14 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-02-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-14 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416 | 33/6 | Completed
2025-02-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-14 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416 | 7/4 | Completed
2025-02-14 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416 | 8/1 | Completed
2025-02-14 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | Completed
2025-02-14 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416 | 33/9 | Completed
2025-02-15 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-02-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-15 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416 | 33/6 | Completed
2025-02-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-15 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416 | 7/4 | Completed
2025-02-15 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416 | 8/1 | Completed
2025-02-15 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | Completed
2025-02-15 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416 | 33/9 | Completed
2025-02-16 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-02-16 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416 | 35/7 | Completed
2025-02-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-16 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416 | 33/6 | Completed
2025-02-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-16 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416 | 7/4 | Completed
2025-02-16 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | Completed
2025-02-16 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | Completed
2025-02-16 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416 | 33/9 | Completed
2025-02-17 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-02-17 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416 | 35/7 | Completed
2025-02-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-17 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416 | 33/6 | Completed
2025-02-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-17 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416 | 7/4 | Completed
2025-02-17 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | Completed
2025-02-17 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | Completed
2025-02-17 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416 | 33/9 | Completed
2025-02-18 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-02-18 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416 | 35/7 | Completed
2025-02-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-18 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416 | 33/6 | Completed
2025-02-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-18 | 2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416 | 7/4 | Completed
2025-02-18 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | Completed
2025-02-18 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | Completed
2025-02-18 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416 | 33/9 | Completed
2025-02-19 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-02-19 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416 | 35/7 | Completed
2025-02-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-19 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416 | 33/6 | Completed
2025-02-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-19 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | Completed
2025-02-19 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | Completed
2025-02-19 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | Completed
2025-02-19 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416 | 33/9 | Completed
2025-02-20 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-02-20 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416 | 35/7 | Completed
2025-02-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-20 | 2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416 | 33/6 | Completed
2025-02-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-20 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | Completed
2025-02-20 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | Completed
2025-02-20 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416 | 20/4 | Completed
2025-02-20 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416 | 33/9 | Completed
2025-02-21 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-02-21 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416 | 35/7 | Completed
2025-02-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-21 | 2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416 | 33/7 | Completed
2025-02-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-21 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | Completed
2025-02-21 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | Completed
2025-02-21 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416 | 20/4 | Completed
2025-02-21 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416 | 33/9 | Completed
2025-02-22 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-02-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-22 | 2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416 | 33/7 | Completed
2025-02-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-22 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | Completed
2025-02-22 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416 | 20/4 | Completed
2025-02-22 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416 | 33/9 | Completed
2025-02-23 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-02-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-23 | 2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416 | 33/7 | Completed
2025-02-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-23 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | Completed
2025-02-23 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416 | 20/4 | Completed
2025-02-23 | 2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416 | 33/9 | Completed
2025-02-24 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-02-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-24 | 2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416 | 33/7 | Completed
2025-02-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-24 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | Completed
2025-02-24 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416 | 20/4 | Completed
2025-02-25 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-02-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-25 | 2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416 | 33/7 | Completed
2025-02-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-25 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | Completed
2025-02-25 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416 | 20/4 | Completed
2025-02-26 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-02-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-26 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | Completed
2025-02-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-27 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-02-27 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | Completed
2025-02-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-27 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | Completed
2025-02-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-27 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | Completed
2025-02-27 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416 | 5/0 | Completed
2025-02-28 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-02-28 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | Completed
2025-02-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-28 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | Completed
2025-02-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-28 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | Completed
2025-02-28 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | Completed
2025-02-28 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416 | 5/0 | Completed
2025-03-01 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-01 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | Completed
2025-03-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-01 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | Completed
2025-03-01 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | Completed
2025-03-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-01 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | Completed
2025-03-01 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | Completed
2025-03-01 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | Completed
2025-03-01 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416 | 5/0 | Completed
2025-03-01 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | Completed
2025-03-01 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | Completed
2025-03-02 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-02 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | Completed
2025-03-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-02 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | Completed
2025-03-02 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | Completed
2025-03-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-02 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | Completed
2025-03-02 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | Completed
2025-03-02 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | Completed
2025-03-02 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416 | 5/0 | Completed
2025-03-02 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | Completed
2025-03-02 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | Completed
2025-03-03 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-03 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | Completed
2025-03-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-03 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | Completed
2025-03-03 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | Completed
2025-03-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-03 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | Completed
2025-03-03 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | Completed
2025-03-03 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | Completed
2025-03-03 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416 | 5/0 | Completed
2025-03-03 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | Completed
2025-03-03 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | Completed
2025-03-04 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-04 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | Completed
2025-03-04 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | Completed
2025-03-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-04 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | Completed
2025-03-04 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | Completed
2025-03-04 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | Completed
2025-03-04 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416 | 5/0 | Completed
2025-03-04 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | Completed
2025-03-04 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | Completed
2025-03-05 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-05 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | Completed
2025-03-05 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | Completed
2025-03-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-05 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | Completed
2025-03-05 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | Completed
2025-03-05 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | Completed
2025-03-05 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416 | 5/0 | Completed
2025-03-05 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | Completed
2025-03-05 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | Completed
2025-03-06 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-06 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | Completed
2025-03-06 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | Completed
2025-03-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-06 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | Completed
2025-03-06 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | Completed
2025-03-06 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | Completed
2025-03-06 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416 | 5/0 | Completed
2025-03-06 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | Completed
2025-03-07 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-07 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | Completed
2025-03-07 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | Completed
2025-03-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-07 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | Completed
2025-03-07 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | Completed
2025-03-07 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | Completed
2025-03-07 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416 | 5/0 | Completed
2025-03-07 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | Completed
2025-03-08 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-08 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | Completed
2025-03-08 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | Completed
2025-03-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-08 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | Completed
2025-03-08 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | Completed
2025-03-08 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | Completed
2025-03-08 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | Completed
2025-03-08 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416 | 5/0 | Completed
2025-03-08 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | Completed
2025-03-09 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-09 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | Completed
2025-03-09 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | Completed
2025-03-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-09 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | Completed
2025-03-09 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | Completed
2025-03-09 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416 | 5/0 | Completed
2025-03-09 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | Completed
2025-03-10 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-10 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | Completed
2025-03-10 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | Completed
2025-03-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-10 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | Completed
2025-03-10 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | Completed
2025-03-10 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | Completed
2025-03-10 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416 | 5/0 | Completed
2025-03-10 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | Completed
2025-03-11 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-11 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | Completed
2025-03-11 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | Completed
2025-03-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-11 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | Completed
2025-03-11 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | Completed
2025-03-11 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | Completed
2025-03-11 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416 | 5/0 | Completed
2025-03-11 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | Completed
2025-03-12 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-12 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | Completed
2025-03-12 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | Completed
2025-03-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-12 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | Completed
2025-03-12 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | Completed
2025-03-12 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | Completed
2025-03-12 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416 | 5/0 | Completed
2025-03-13 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-13 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | Completed
2025-03-13 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | Completed
2025-03-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-13 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | Completed
2025-03-13 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | Completed
2025-03-13 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | Completed
2025-03-13 | 2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416 | 5/0 | Completed
2025-03-14 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-14 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | Completed
2025-03-14 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | Completed
2025-03-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-14 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | Completed
2025-03-14 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | Completed
2025-03-14 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | Completed
2025-03-15 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-15 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | Completed
2025-03-15 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | Completed
2025-03-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-15 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | Completed
2025-03-15 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | Completed
2025-03-15 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | Completed
2025-03-16 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-16 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | Completed
2025-03-16 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | Completed
2025-03-16 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | Completed
2025-03-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-16 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | Completed
2025-03-16 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | Completed
2025-03-16 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | Completed
2025-03-16 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | Completed
2025-03-17 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-17 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | Completed
2025-03-17 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | Completed
2025-03-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-17 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | Completed
2025-03-17 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | Completed
2025-03-17 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | Completed
2025-03-17 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | Completed
2025-03-18 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-18 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | Completed
2025-03-18 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | Completed
2025-03-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-18 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | Completed
2025-03-18 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | Completed
2025-03-18 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | Completed
2025-03-18 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | Completed
2025-03-19 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-19 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | Completed
2025-03-19 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | Completed
2025-03-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-19 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | Completed
2025-03-19 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | Completed
2025-03-19 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | Completed
2025-03-20 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-20 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | Completed
2025-03-20 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | Completed
2025-03-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-20 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416 | 35/2 | Completed
2025-03-20 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416 | 7/3 | Completed
2025-03-20 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | Completed
2025-03-20 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | Completed
2025-03-21 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-21 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | Completed
2025-03-21 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | Completed
2025-03-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-21 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416 | 35/2 | Completed
2025-03-21 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416 | 7/3 | Completed
2025-03-21 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | Completed
2025-03-21 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | Completed
2025-03-22 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-22 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | Completed
2025-03-22 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | Completed
2025-03-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-22 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416 | 35/2 | Completed
2025-03-22 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416 | 38/8 | Completed
2025-03-22 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416 | 7/3 | Completed
2025-03-22 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416 | 6/0 | Completed
2025-03-23 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-23 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416 | 35/8 | Completed
2025-03-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-23 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | Completed
2025-03-23 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | Completed
2025-03-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-23 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416 | 35/2 | Completed
2025-03-23 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416 | 38/8 | Completed
2025-03-23 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416 | 7/3 | Completed
2025-03-23 | 2025-03-23 | 2025-03-26 | Pinky Dewi | 42.375 | 10.5938 | TA416 | 8B/1 | Completed
2025-03-23 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416 | 8B/5 | Completed
2025-03-23 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416 | 6/0 | Completed
2025-03-24 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-24 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416 | 35/8 | Completed
2025-03-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-24 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416 | 31/10 | Completed
2025-03-24 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416 | 34/0 | Completed
2025-03-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-24 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416 | 35/2 | Completed
2025-03-24 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416 | 38/8 | Completed
2025-03-24 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416 | 7/3 | Completed
2025-03-24 | 2025-03-23 | 2025-03-26 | Pinky Dewi | 42.375 | 10.5938 | TA416 | 8B/1 | Completed
2025-03-24 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416 | 8B/5 | Completed
2025-03-24 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416 | 6/0 | Completed
2025-03-25 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-25 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416 | 35/8 | Completed
2025-03-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-25 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416 | 31/10 | Completed
2025-03-25 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416 | 34/0 | Completed
2025-03-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-25 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416 | 35/2 | Completed
2025-03-25 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416 | 38/8 | Completed
2025-03-25 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416 | 7/3 | Completed
2025-03-25 | 2025-03-23 | 2025-03-26 | Pinky Dewi | 42.375 | 10.5938 | TA416 | 8B/1 | Completed
2025-03-25 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416 | 8B/5 | Completed
2025-03-25 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416 | 6/0 | Completed
2025-03-26 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-26 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416 | 35/8 | Completed
2025-03-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-26 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416 | 31/10 | Completed
2025-03-26 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416 | 34/0 | Completed
2025-03-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-26 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416 | 35/2 | Completed
2025-03-26 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416 | 38/8 | Completed
2025-03-26 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416 | 7/3 | Completed
2025-03-26 | 2025-03-23 | 2025-03-26 | Pinky Dewi | 42.375 | 10.5938 | TA416 | 8B/1 | Completed
2025-03-26 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416 | 8B/5 | Completed
2025-03-26 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416 | 6/0 | Completed
2025-03-27 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-27 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416 | 35/8 | Completed
2025-03-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-27 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416 | 31/10 | Completed
2025-03-27 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416 | 34/0 | Completed
2025-03-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-27 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416 | 35/2 | Completed
2025-03-27 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416 | 38/8 | Completed
2025-03-27 | 2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416 | 7/3 | Completed
2025-03-27 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416 | 8B/5 | Completed
2025-03-27 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416 | 6/0 | Completed
2025-03-28 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-28 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416 | 35/8 | Completed
2025-03-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-28 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416 | 31/10 | Completed
2025-03-28 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416 | 34/0 | Completed
2025-03-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-28 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416 | 35/2 | Completed
2025-03-28 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416 | 38/8 | Completed
2025-03-28 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416 | 8B/5 | Completed
2025-03-28 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | Completed
2025-03-28 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416 | 6/0 | Completed
2025-03-28 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | Completed
2025-03-29 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-29 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416 | 35/8 | Completed
2025-03-29 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-29 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416 | 31/10 | Completed
2025-03-29 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416 | 34/0 | Completed
2025-03-29 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-29 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416 | 35/2 | Completed
2025-03-29 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416 | 38/8 | Completed
2025-03-29 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416 | 8B/5 | Completed
2025-03-29 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | Completed
2025-03-29 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416 | 6/0 | Completed
2025-03-29 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | Completed
2025-03-30 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-30 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416 | 35/8 | Completed
2025-03-30 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-30 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416 | 31/10 | Completed
2025-03-30 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416 | 34/0 | Completed
2025-03-30 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-30 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416 | 35/2 | Completed
2025-03-30 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416 | 38/8 | Completed
2025-03-30 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416 | 8B/5 | Completed
2025-03-30 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | Completed
2025-03-30 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | Completed
2025-03-31 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-03-31 | 2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416 | 35/8 | Completed
2025-03-31 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-03-31 | 2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416 | 34/0 | Completed
2025-03-31 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416 | 20/11 | Completed
2025-03-31 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-03-31 | 2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416 | 38/8 | Completed
2025-03-31 | 2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416 | 8B/5 | Completed
2025-03-31 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | Completed
2025-03-31 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | Completed
2025-04-01 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-01 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416 | 36/0 | Completed
2025-04-01 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416 | 39/1 | Completed
2025-04-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-01 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416 | 32/0 | Completed
2025-04-01 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416 | 20/11 | Completed
2025-04-01 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416 | 9/0 | Completed
2025-04-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-01 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | Completed
2025-04-01 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416 | 38/6 | Completed
2025-04-01 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | Completed
2025-04-01 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | Completed
2025-04-02 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-02 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416 | 36/0 | Completed
2025-04-02 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416 | 39/1 | Completed
2025-04-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-02 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416 | 32/0 | Completed
2025-04-02 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416 | 20/11 | Completed
2025-04-02 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416 | 9/0 | Completed
2025-04-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-02 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | Completed
2025-04-02 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416 | 38/6 | Completed
2025-04-02 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | Completed
2025-04-02 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | Completed
2025-04-03 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-03 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416 | 36/0 | Completed
2025-04-03 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416 | 39/1 | Completed
2025-04-03 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416 | 52/6 | Completed
2025-04-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-03 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416 | 32/0 | Completed
2025-04-03 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416 | 34/4 | Completed
2025-04-03 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416 | 20/11 | Completed
2025-04-03 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416 | 9/0 | Completed
2025-04-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-03 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | Completed
2025-04-03 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416 | 38/6 | Completed
2025-04-03 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | Completed
2025-04-03 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | Completed
2025-04-04 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-04 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416 | 36/0 | Completed
2025-04-04 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416 | 39/1 | Completed
2025-04-04 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416 | 52/6 | Completed
2025-04-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-04 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416 | 32/0 | Completed
2025-04-04 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416 | 34/4 | Completed
2025-04-04 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416 | 20/11 | Completed
2025-04-04 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416 | 9/0 | Completed
2025-04-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-04 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | Completed
2025-04-04 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416 | 38/6 | Completed
2025-04-04 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | Completed
2025-04-04 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | Completed
2025-04-05 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-05 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416 | 36/0 | Completed
2025-04-05 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416 | 39/1 | Completed
2025-04-05 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416 | 52/6 | Completed
2025-04-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-05 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416 | 32/0 | Completed
2025-04-05 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416 | 34/4 | Completed
2025-04-05 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416 | 20/11 | Completed
2025-04-05 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416 | 9/0 | Completed
2025-04-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-05 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | Completed
2025-04-05 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416 | 38/6 | Completed
2025-04-05 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | Completed
2025-04-05 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | Completed
2025-04-06 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-06 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416 | 36/0 | Completed
2025-04-06 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416 | 39/1 | Completed
2025-04-06 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416 | 52/6 | Completed
2025-04-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-06 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416 | 32/0 | Completed
2025-04-06 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416 | 34/4 | Completed
2025-04-06 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416 | 20/11 | Completed
2025-04-06 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416 | 9/0 | Completed
2025-04-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-06 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | Completed
2025-04-06 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416 | 38/6 | Completed
2025-04-06 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | Completed
2025-04-06 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | Completed
2025-04-07 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-07 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416 | 36/0 | Completed
2025-04-07 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416 | 39/1 | Completed
2025-04-07 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416 | 52/6 | Completed
2025-04-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-07 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416 | 32/0 | Completed
2025-04-07 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416 | 34/4 | Completed
2025-04-07 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416 | 20/11 | Completed
2025-04-07 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416 | 9/0 | Completed
2025-04-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-07 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | Completed
2025-04-07 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416 | 38/6 | Completed
2025-04-07 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | Completed
2025-04-07 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | Completed
2025-04-08 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-08 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416 | 36/0 | Completed
2025-04-08 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416 | 39/1 | Completed
2025-04-08 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416 | 52/6 | Completed
2025-04-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-08 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416 | 32/0 | Completed
2025-04-08 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416 | 34/4 | Completed
2025-04-08 | 2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416 | 20/11 | Completed
2025-04-08 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416 | 9/0 | Completed
2025-04-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-08 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | Completed
2025-04-08 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416 | 38/6 | Completed
2025-04-08 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | Completed
2025-04-09 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-09 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416 | 36/0 | Completed
2025-04-09 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416 | 39/1 | Completed
2025-04-09 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416 | 52/6 | Completed
2025-04-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-09 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416 | 32/0 | Completed
2025-04-09 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416 | 34/4 | Completed
2025-04-09 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416 | 9/0 | Completed
2025-04-09 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416 | 20/10 | Completed
2025-04-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-09 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | Completed
2025-04-09 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416 | 38/6 | Completed
2025-04-09 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | Completed
2025-04-10 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-10 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416 | 36/0 | Completed
2025-04-10 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416 | 39/1 | Completed
2025-04-10 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416 | 52/6 | Completed
2025-04-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-10 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416 | 32/0 | Completed
2025-04-10 | 2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416 | 34/4 | Completed
2025-04-10 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416 | 9/0 | Completed
2025-04-10 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416 | 20/10 | Completed
2025-04-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-10 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | Completed
2025-04-10 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416 | 38/6 | Completed
2025-04-10 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | Completed
2025-04-11 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-11 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416 | 36/0 | Completed
2025-04-11 | 2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416 | 39/1 | Completed
2025-04-11 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416 | 52/6 | Completed
2025-04-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-11 | 2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416 | 32/0 | Completed
2025-04-11 | 2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416 | 9/0 | Completed
2025-04-11 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416 | 20/10 | Completed
2025-04-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-11 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | Completed
2025-04-11 | 2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416 | 38/6 | Completed
2025-04-11 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | Completed
2025-04-12 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-12 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416 | 36/0 | Completed
2025-04-12 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | Completed
2025-04-12 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416 | 52/6 | Completed
2025-04-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-12 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | Completed
2025-04-12 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | Completed
2025-04-12 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416 | 10/1 | Completed
2025-04-12 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416 | 20/10 | Completed
2025-04-12 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416 | 20/1 | Completed
2025-04-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-12 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | Completed
2025-04-12 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | Completed
2025-04-12 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416 | 8B/4 | Completed
2025-04-12 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | Completed
2025-04-12 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416 | 25/2 | Completed
2025-04-13 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-13 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416 | 36/0 | Completed
2025-04-13 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | Completed
2025-04-13 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416 | 52/6 | Completed
2025-04-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-13 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | Completed
2025-04-13 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | Completed
2025-04-13 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416 | 10/1 | Completed
2025-04-13 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416 | 20/10 | Completed
2025-04-13 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416 | 20/1 | Completed
2025-04-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-13 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | Completed
2025-04-13 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416 | 8B/4 | Completed
2025-04-13 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | Completed
2025-04-13 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416 | 25/2 | Completed
2025-04-14 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-14 | 2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416 | 36/0 | Completed
2025-04-14 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | Completed
2025-04-14 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416 | 52/6 | Completed
2025-04-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-14 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | Completed
2025-04-14 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | Completed
2025-04-14 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416 | 10/1 | Completed
2025-04-14 | 2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416 | 20/10 | Completed
2025-04-14 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416 | 20/1 | Completed
2025-04-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-14 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | Completed
2025-04-14 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416 | 8B/4 | Completed
2025-04-14 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | Completed
2025-04-14 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416 | 25/2 | Completed
2025-04-15 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-15 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | Completed
2025-04-15 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416 | 52/6 | Completed
2025-04-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-15 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | Completed
2025-04-15 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | Completed
2025-04-15 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416 | 10/1 | Completed
2025-04-15 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416 | 20/1 | Completed
2025-04-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-15 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | Completed
2025-04-15 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416 | 8B/4 | Completed
2025-04-15 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | Completed
2025-04-15 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416 | 25/2 | Completed
2025-04-16 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-16 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | Completed
2025-04-16 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416 | 52/6 | Completed
2025-04-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-16 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | Completed
2025-04-16 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | Completed
2025-04-16 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416 | 10/1 | Completed
2025-04-16 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416 | 20/1 | Completed
2025-04-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-16 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | Completed
2025-04-16 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416 | 8B/4 | Completed
2025-04-16 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | Completed
2025-04-16 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416 | 25/2 | Completed
2025-04-17 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-17 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | Completed
2025-04-17 | 2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416 | 52/6 | Completed
2025-04-17 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | Completed
2025-04-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-17 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | Completed
2025-04-17 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | Completed
2025-04-17 | 2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416 | 10/1 | Completed
2025-04-17 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416 | 20/1 | Completed
2025-04-17 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | Completed
2025-04-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-17 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | Completed
2025-04-17 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416 | 8B/4 | Completed
2025-04-17 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | Completed
2025-04-17 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416 | 25/2 | Completed
2025-04-18 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-18 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | Completed
2025-04-18 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | Completed
2025-04-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-18 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | Completed
2025-04-18 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | Completed
2025-04-18 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416 | 20/1 | Completed
2025-04-18 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | Completed
2025-04-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-18 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | Completed
2025-04-18 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416 | 8B/4 | Completed
2025-04-18 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416 | 25/2 | Completed
2025-04-19 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-19 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | Completed
2025-04-19 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | Completed
2025-04-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-19 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | Completed
2025-04-19 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | Completed
2025-04-19 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416 | 20/1 | Completed
2025-04-19 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | Completed
2025-04-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-19 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | Completed
2025-04-19 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416 | 8B/4 | Completed
2025-04-19 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416 | 25/2 | Completed
2025-04-20 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-20 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | Completed
2025-04-20 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | Completed
2025-04-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-20 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | Completed
2025-04-20 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | Completed
2025-04-20 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416 | 20/1 | Completed
2025-04-20 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | Completed
2025-04-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-20 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | Completed
2025-04-20 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416 | 8B/4 | Completed
2025-04-20 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416 | 25/2 | Completed
2025-04-21 | 2025-02-12 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-21 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | Completed
2025-04-21 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | Completed
2025-04-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-21 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | Completed
2025-04-21 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | Completed
2025-04-21 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416 | 20/1 | Completed
2025-04-21 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | Completed
2025-04-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-21 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | Completed
2025-04-21 | 2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416 | 8B/4 | Completed
2025-04-21 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416 | 25/2 | Completed
2025-04-22 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | Completed
2025-04-22 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | Completed
2025-04-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-22 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | Completed
2025-04-22 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | Completed
2025-04-22 | 2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416 | 20/1 | Completed
2025-04-22 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | Completed
2025-04-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-22 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | Completed
2025-04-22 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | Completed
2025-04-22 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416 | 25/2 | Completed
2025-04-23 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | Completed
2025-04-23 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | Completed
2025-04-23 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | Completed
2025-04-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-23 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | Completed
2025-04-23 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | Completed
2025-04-23 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | Completed
2025-04-23 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | Completed
2025-04-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-23 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416 | 38/9 | Completed
2025-04-23 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | Completed
2025-04-23 | 2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416 | 25/2 | Completed
2025-04-24 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | Completed
2025-04-24 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | Completed
2025-04-24 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | Completed
2025-04-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-24 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | Completed
2025-04-24 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | Completed
2025-04-24 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | Completed
2025-04-24 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | Completed
2025-04-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-24 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416 | 38/9 | Completed
2025-04-24 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | Completed
2025-04-25 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | Completed
2025-04-25 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | Completed
2025-04-25 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | Completed
2025-04-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-25 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | Completed
2025-04-25 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | Completed
2025-04-25 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | Completed
2025-04-25 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | Completed
2025-04-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-25 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416 | 38/9 | Completed
2025-04-25 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | Completed
2025-04-26 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | Completed
2025-04-26 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | Completed
2025-04-26 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | Completed
2025-04-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-26 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | Completed
2025-04-26 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | Completed
2025-04-26 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | Completed
2025-04-26 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | Completed
2025-04-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-26 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416 | 38/9 | Completed
2025-04-26 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | Completed
2025-04-27 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | Completed
2025-04-27 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/4 | Completed
2025-04-27 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | Completed
2025-04-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-27 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | Completed
2025-04-27 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | Completed
2025-04-27 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | Completed
2025-04-27 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | Completed
2025-04-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-27 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416 | 38/9 | Completed
2025-04-27 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | Completed
2025-04-27 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 25/3 | Completed
2025-04-28 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | Completed
2025-04-28 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/4 | Completed
2025-04-28 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | Completed
2025-04-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-28 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | Completed
2025-04-28 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | Completed
2025-04-28 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | Completed
2025-04-28 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | Completed
2025-04-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-28 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416 | 38/9 | Completed
2025-04-28 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | Completed
2025-04-28 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 25/3 | Completed
2025-04-29 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | Completed
2025-04-29 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/4 | Completed
2025-04-29 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | Completed
2025-04-29 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-29 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | Completed
2025-04-29 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | Completed
2025-04-29 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-29 | 2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416 | 38/9 | Completed
2025-04-29 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | Completed
2025-04-29 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 25/3 | Completed
2025-04-30 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | Completed
2025-04-30 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/4 | Completed
2025-04-30 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-04-30 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | Completed
2025-04-30 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | Completed
2025-04-30 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-04-30 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | Completed
2025-04-30 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 25/3 | Completed
2025-05-01 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | Completed
2025-05-01 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/4 | Completed
2025-05-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-01 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416 | 30/3 | Completed
2025-05-01 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | Completed
2025-05-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-01 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 25/3 | Completed
2025-05-02 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | Completed
2025-05-02 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/4 | Completed
2025-05-02 | 2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/3 | Completed
2025-05-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-02 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416 | 30/3 | Completed
2025-05-02 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | Completed
2025-05-02 | 2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416 | 19/10 | Completed
2025-05-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-02 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 25/3 | Completed
2025-05-03 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | Completed
2025-05-03 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/4 | Completed
2025-05-03 | 2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/3 | Completed
2025-05-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-03 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416 | 30/3 | Completed
2025-05-03 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | Completed
2025-05-03 | 2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416 | 19/10 | Completed
2025-05-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-03 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 25/3 | Completed
2025-05-04 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | Completed
2025-05-04 | 2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/4 | Completed
2025-05-04 | 2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/3 | Completed
2025-05-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-04 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416 | 30/3 | Completed
2025-05-04 | 2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416 | 19/10 | Completed
2025-05-04 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | Completed
2025-05-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-04 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | Completed
2025-05-04 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 25/3 | Completed
2025-05-05 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | Completed
2025-05-05 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | Completed
2025-05-05 | 2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/3 | Completed
2025-05-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-05 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416 | 30/3 | Completed
2025-05-05 | 2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416 | 19/10 | Completed
2025-05-05 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | Completed
2025-05-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-05 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | Completed
2025-05-05 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | Completed
2025-05-05 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 25/3 | Completed
2025-05-06 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | Completed
2025-05-06 | 2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/3 | Completed
2025-05-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-06 | 2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416 | 30/3 | Completed
2025-05-06 | 2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416 | 19/10 | Completed
2025-05-06 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | Completed
2025-05-06 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | Completed
2025-05-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-06 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | Completed
2025-05-06 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | Completed
2025-05-06 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 25/3 | Completed
2025-05-07 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | Completed
2025-05-07 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | Completed
2025-05-07 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | Completed
2025-05-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-07 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | Completed
2025-05-07 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | Completed
2025-05-07 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | Completed
2025-05-07 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | Completed
2025-05-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-07 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | Completed
2025-05-07 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | Completed
2025-05-07 | 2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 25/3 | Completed
2025-05-08 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | Completed
2025-05-08 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | Completed
2025-05-08 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | Completed
2025-05-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-08 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | Completed
2025-05-08 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | Completed
2025-05-08 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | Completed
2025-05-08 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | Completed
2025-05-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-08 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | Completed
2025-05-08 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | Completed
2025-05-09 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | Completed
2025-05-09 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | Completed
2025-05-09 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | Completed
2025-05-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-09 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | Completed
2025-05-09 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | Completed
2025-05-09 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | Completed
2025-05-09 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | Completed
2025-05-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-09 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | Completed
2025-05-09 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | Completed
2025-05-10 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | Completed
2025-05-10 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | Completed
2025-05-10 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | Completed
2025-05-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-10 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | Completed
2025-05-10 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | Completed
2025-05-10 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | Completed
2025-05-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-10 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | Completed
2025-05-10 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | Completed
2025-05-10 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416 | 23/5 | Completed
2025-05-11 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | Completed
2025-05-11 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | Completed
2025-05-11 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | Completed
2025-05-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-11 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | Completed
2025-05-11 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | Completed
2025-05-11 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | Completed
2025-05-11 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | Completed
2025-05-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-11 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | Completed
2025-05-11 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | Completed
2025-05-11 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416 | 23/5 | Completed
2025-05-12 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | Completed
2025-05-12 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | Completed
2025-05-12 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | Completed
2025-05-12 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | Completed
2025-05-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-12 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | Completed
2025-05-12 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | Completed
2025-05-12 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | Completed
2025-05-12 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | Completed
2025-05-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-12 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | Completed
2025-05-12 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | Completed
2025-05-12 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416 | 23/5 | Completed
2025-05-13 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | Completed
2025-05-13 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | Completed
2025-05-13 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | Completed
2025-05-13 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416 | 38/10 | Completed
2025-05-13 | 2025-05-13 | 2025-05-15 | Ananya Traders 2 | 42.3742 | 14.1247 | TA416 | 52/9 | Completed
2025-05-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-13 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | Completed
2025-05-13 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | Completed
2025-05-13 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | Completed
2025-05-13 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | Completed
2025-05-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-13 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | Completed
2025-05-13 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | Completed
2025-05-13 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416 | 23/5 | Completed
2025-05-14 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | Completed
2025-05-14 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | Completed
2025-05-14 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | Completed
2025-05-14 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416 | 38/10 | Completed
2025-05-14 | 2025-05-13 | 2025-05-15 | Ananya Traders 2 | 42.3742 | 14.1247 | TA416 | 52/9 | Completed
2025-05-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-14 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | Completed
2025-05-14 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | Completed
2025-05-14 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | Completed
2025-05-14 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | Completed
2025-05-14 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | Completed
2025-05-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-14 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | Completed
2025-05-14 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | Completed
2025-05-14 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416 | 23/5 | Completed
2025-05-15 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | Completed
2025-05-15 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | Completed
2025-05-15 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | Completed
2025-05-15 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416 | 38/10 | Completed
2025-05-15 | 2025-05-13 | 2025-05-15 | Ananya Traders 2 | 42.3742 | 14.1247 | TA416 | 52/9 | Completed
2025-05-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-15 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | Completed
2025-05-15 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | Completed
2025-05-15 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | Completed
2025-05-15 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | Completed
2025-05-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-15 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | Completed
2025-05-15 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | Completed
2025-05-15 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416 | 23/5 | Completed
2025-05-16 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | Completed
2025-05-16 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | Completed
2025-05-16 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | Completed
2025-05-16 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416 | 38/10 | Completed
2025-05-16 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | Completed
2025-05-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-16 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | Completed
2025-05-16 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | Completed
2025-05-16 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416 | 15/0 | Completed
2025-05-16 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | Completed
2025-05-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-16 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | Completed
2025-05-16 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | Completed
2025-05-16 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416 | 23/5 | Completed
2025-05-17 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | Completed
2025-05-17 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | Completed
2025-05-17 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | Completed
2025-05-17 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416 | 38/10 | Completed
2025-05-17 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | Completed
2025-05-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-17 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | Completed
2025-05-17 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | Completed
2025-05-17 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416 | 15/0 | Completed
2025-05-17 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | Completed
2025-05-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-17 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | Completed
2025-05-17 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | Completed
2025-05-17 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416 | 23/5 | Completed
2025-05-18 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | Completed
2025-05-18 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | Completed
2025-05-18 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | Completed
2025-05-18 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416 | 38/10 | Completed
2025-05-18 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | Completed
2025-05-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-18 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | Completed
2025-05-18 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | Completed
2025-05-18 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416 | 15/0 | Completed
2025-05-18 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | Completed
2025-05-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-18 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | Completed
2025-05-18 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | Completed
2025-05-18 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416 | 23/5 | Completed
2025-05-19 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | Completed
2025-05-19 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | Completed
2025-05-19 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | Completed
2025-05-19 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416 | 38/10 | Completed
2025-05-19 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | Completed
2025-05-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-19 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | Completed
2025-05-19 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | Completed
2025-05-19 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416 | 15/0 | Completed
2025-05-19 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | Completed
2025-05-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-19 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | Completed
2025-05-19 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | Completed
2025-05-19 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416 | 23/5 | Completed
2025-05-20 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | Completed
2025-05-20 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | Completed
2025-05-20 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416 | 38/10 | Completed
2025-05-20 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | Completed
2025-05-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-20 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | Completed
2025-05-20 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | Completed
2025-05-20 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416 | 15/0 | Completed
2025-05-20 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | Completed
2025-05-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-20 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | Completed
2025-05-20 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | Completed
2025-05-20 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416 | 23/5 | Completed
2025-05-21 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | Completed
2025-05-21 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | Completed
2025-05-21 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416 | 38/10 | Completed
2025-05-21 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | Completed
2025-05-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-21 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-05-21 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | Completed
2025-05-21 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416 | 15/0 | Completed
2025-05-21 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | Completed
2025-05-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-21 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | Completed
2025-05-21 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | Completed
2025-05-21 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416 | 23/5 | Completed
2025-05-22 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | Completed
2025-05-22 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | Completed
2025-05-22 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416 | 38/10 | Completed
2025-05-22 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | Completed
2025-05-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-22 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-05-22 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | Completed
2025-05-22 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416 | 15/0 | Completed
2025-05-22 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | Completed
2025-05-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-22 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | Completed
2025-05-22 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416 | 0/2 | Completed
2025-05-22 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416 | 23/5 | Completed
2025-05-23 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | Completed
2025-05-23 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416 | 38/10 | Completed
2025-05-23 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | Completed
2025-05-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-23 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-05-23 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | Completed
2025-05-23 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416 | 15/0 | Completed
2025-05-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-23 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | Completed
2025-05-23 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416 | 0/2 | Completed
2025-05-23 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416 | 23/5 | Completed
2025-05-24 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | Completed
2025-05-24 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416 | 36/10 | Completed
2025-05-24 | 2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416 | 38/10 | Completed
2025-05-24 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | Completed
2025-05-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-24 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-05-24 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | Completed
2025-05-24 | 2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/4 | Completed
2025-05-24 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416 | 15/0 | Completed
2025-05-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-24 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | Completed
2025-05-24 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416 | 0/2 | Completed
2025-05-24 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416 | 23/5 | Completed
2025-05-25 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416 | 36/10 | Completed
2025-05-25 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | Completed
2025-05-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-25 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-05-25 | 2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/4 | Completed
2025-05-25 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416 | 15/0 | Completed
2025-05-25 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416 | 12/8 | Completed
2025-05-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-25 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | Completed
2025-05-25 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416 | 0/2 | Completed
2025-05-25 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416 | 0/3 | Completed
2025-05-25 | 2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416 | 23/5 | Completed
2025-05-26 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416 | 36/10 | Completed
2025-05-26 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | Completed
2025-05-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-26 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-05-26 | 2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/4 | Completed
2025-05-26 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416 | 12/8 | Completed
2025-05-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-26 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | Completed
2025-05-26 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416 | 0/2 | Completed
2025-05-26 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416 | 0/3 | Completed
2025-05-27 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416 | 36/10 | Completed
2025-05-27 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | Completed
2025-05-27 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416 | 51/0 | Completed
2025-05-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-27 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-05-27 | 2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/4 | Completed
2025-05-27 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416 | 12/8 | Completed
2025-05-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-27 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | Completed
2025-05-27 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416 | 0/2 | Completed
2025-05-27 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416 | 0/3 | Completed
2025-05-28 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416 | 36/10 | Completed
2025-05-28 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416 | 38/5 | Completed
2025-05-28 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416 | 51/0 | Completed
2025-05-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-28 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-05-28 | 2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/4 | Completed
2025-05-28 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-05-28 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416 | 12/8 | Completed
2025-05-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-28 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | Completed
2025-05-28 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416 | 23/1 | Completed
2025-05-28 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416 | 0/2 | Completed
2025-05-28 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416 | 0/3 | Completed
2025-05-29 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416 | 36/10 | Completed
2025-05-29 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416 | 38/5 | Completed
2025-05-29 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416 | 51/0 | Completed
2025-05-29 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-29 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-05-29 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-05-29 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416 | 12/8 | Completed
2025-05-29 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-29 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416 | 23/1 | Completed
2025-05-29 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416 | 0/2 | Completed
2025-05-29 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416 | 0/3 | Completed
2025-05-30 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416 | 36/10 | Completed
2025-05-30 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-05-30 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416 | 38/5 | Completed
2025-05-30 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416 | 51/0 | Completed
2025-05-30 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-30 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-05-30 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416 | 56/5 | Completed
2025-05-30 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-05-30 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416 | 12/8 | Completed
2025-05-30 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-30 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416 | 23/1 | Completed
2025-05-30 | 2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416 | 0/2 | Completed
2025-05-30 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416 | 0/3 | Completed
2025-05-31 | 2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416 | 36/10 | Completed
2025-05-31 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-05-31 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416 | 38/5 | Completed
2025-05-31 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416 | 51/0 | Completed
2025-05-31 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-05-31 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-05-31 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416 | 56/5 | Completed
2025-05-31 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-05-31 | 2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416 | 12/8 | Completed
2025-05-31 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-05-31 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416 | 23/1 | Completed
2025-05-31 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416 | 0/3 | Completed
2025-06-01 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-01 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416 | 38/5 | Completed
2025-06-01 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416 | 51/0 | Completed
2025-06-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-01 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-01 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416 | 56/5 | Completed
2025-06-01 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-01 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416 | 23/1 | Completed
2025-06-01 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416 | 0/3 | Completed
2025-06-02 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-02 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416 | 38/5 | Completed
2025-06-02 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416 | 51/0 | Completed
2025-06-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-02 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-02 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416 | 56/5 | Completed
2025-06-02 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-02 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416 | 23/1 | Completed
2025-06-02 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416 | 0/3 | Completed
2025-06-03 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416 | 33/5 | Completed
2025-06-03 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-03 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-03 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416 | 51/0 | Completed
2025-06-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-03 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-03 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416 | 56/5 | Completed
2025-06-03 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-03 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416 | 23/1 | Completed
2025-06-03 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416 | 0/3 | Completed
2025-06-04 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416 | 33/5 | Completed
2025-06-04 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-04 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-04 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416 | 51/0 | Completed
2025-06-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-04 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-04 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416 | 56/5 | Completed
2025-06-04 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-04 | 2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416 | 23/2 | Completed
2025-06-04 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416 | 0/3 | Completed
2025-06-05 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416 | 33/5 | Completed
2025-06-05 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-05 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-05 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416 | 51/0 | Completed
2025-06-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-05 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-05 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-05 | 2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416 | 23/2 | Completed
2025-06-05 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416 | 0/1 | Completed
2025-06-05 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-06 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416 | 33/5 | Completed
2025-06-06 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-06 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-06 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416 | 51/0 | Completed
2025-06-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-06 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-06 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-06 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-06 | 2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416 | 23/2 | Completed
2025-06-06 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416 | 0/1 | Completed
2025-06-06 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-07 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416 | 33/5 | Completed
2025-06-07 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-07 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-07 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416 | 51/0 | Completed
2025-06-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-07 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-07 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-07 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-07 | 2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416 | 23/2 | Completed
2025-06-07 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416 | 0/1 | Completed
2025-06-07 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-08 | 2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416 | 33/5 | Completed
2025-06-08 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-08 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-08 | 2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416 | 50/1 | Completed
2025-06-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-08 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-08 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-08 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-08 | 2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416 | 23/2 | Completed
2025-06-08 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416 | 0/1 | Completed
2025-06-08 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-09 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416 | 34/5 | Completed
2025-06-09 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-09 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-09 | 2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416 | 50/1 | Completed
2025-06-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-09 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-09 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-09 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-09 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416 | 22/0 | Completed
2025-06-09 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416 | 0/1 | Completed
2025-06-09 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-10 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416 | 34/5 | Completed
2025-06-10 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-10 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-10 | 2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416 | 50/1 | Completed
2025-06-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-10 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-10 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-10 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-10 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416 | 22/0 | Completed
2025-06-10 | 2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416 | 0/1 | Completed
2025-06-10 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-11 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416 | 34/5 | Completed
2025-06-11 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-11 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-11 | 2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416 | 50/1 | Completed
2025-06-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-11 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-11 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-11 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-11 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416 | 22/0 | Completed
2025-06-11 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-12 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416 | 34/5 | Completed
2025-06-12 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-12 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-12 | 2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416 | 50/1 | Completed
2025-06-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-12 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-12 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-12 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-12 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416 | 22/0 | Completed
2025-06-12 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-13 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416 | 34/5 | Completed
2025-06-13 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-13 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-13 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-13 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-13 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-13 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416 | 22/0 | Completed
2025-06-13 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-14 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416 | 34/5 | Completed
2025-06-14 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-14 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-14 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416 | 48/0 | Completed
2025-06-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-14 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-14 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-14 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-14 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416 | 22/0 | Completed
2025-06-14 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-15 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416 | 34/5 | Completed
2025-06-15 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-15 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-15 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416 | 48/0 | Completed
2025-06-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-15 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-15 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-15 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-15 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416 | 22/0 | Completed
2025-06-15 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-16 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416 | 34/5 | Completed
2025-06-16 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-16 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-16 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416 | 48/0 | Completed
2025-06-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-16 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-16 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-16 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-16 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416 | 22/0 | Completed
2025-06-16 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-17 | 2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416 | 34/5 | Completed
2025-06-17 | 2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-17 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-17 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416 | 48/0 | Completed
2025-06-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-17 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-17 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-17 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-17 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416 | 22/0 | Completed
2025-06-17 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-18 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-18 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416 | 48/0 | Completed
2025-06-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-18 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-18 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-18 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-18 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416 | 22/0 | Completed
2025-06-18 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-19 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-19 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416 | 48/0 | Completed
2025-06-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-19 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-19 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-19 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-19 | 2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416 | 22/0 | Completed
2025-06-19 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-20 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-06-20 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416 | 53A/3 | Completed
2025-06-20 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-20 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416 | 48/0 | Completed
2025-06-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-20 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-20 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-20 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-20 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416 | 21/2 | Completed
2025-06-20 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-21 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-06-21 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416 | 53A/3 | Completed
2025-06-21 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-21 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416 | 48/0 | Completed
2025-06-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-21 | 2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-21 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-21 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-21 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416 | 21/2 | Completed
2025-06-21 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-22 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-06-22 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416 | 53A/3 | Completed
2025-06-22 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-22 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416 | 48/0 | Completed
2025-06-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-22 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416 | 28/1 | Completed
2025-06-22 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-22 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-22 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416 | 21/2 | Completed
2025-06-22 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-23 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-06-23 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416 | 53A/3 | Completed
2025-06-23 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-23 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416 | 48/0 | Completed
2025-06-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-23 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416 | 28/1 | Completed
2025-06-23 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-23 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-23 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416 | 21/2 | Completed
2025-06-23 | 2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-24 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-06-24 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416 | 53A/3 | Completed
2025-06-24 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-24 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416 | 48/0 | Completed
2025-06-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-24 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416 | 28/1 | Completed
2025-06-24 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-24 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-24 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416 | 21/2 | Completed
2025-06-24 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416 | 12/7 | Completed
2025-06-25 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-06-25 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416 | 53A/3 | Completed
2025-06-25 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-25 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416 | 48/0 | Completed
2025-06-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-25 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416 | 28/1 | Completed
2025-06-25 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-25 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-25 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416 | 21/2 | Completed
2025-06-25 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416 | 12/7 | Completed
2025-06-26 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-06-26 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416 | 53A/3 | Completed
2025-06-26 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-26 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416 | 48/0 | Completed
2025-06-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-26 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416 | 28/1 | Completed
2025-06-26 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-26 | 2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-26 | 2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416 | 21/2 | Completed
2025-06-26 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416 | 12/7 | Completed
2025-06-27 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-06-27 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416 | 53A/3 | Completed
2025-06-27 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-27 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416 | 48/0 | Completed
2025-06-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-27 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416 | 28/1 | Completed
2025-06-27 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-27 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416 | 12/7 | Completed
2025-06-28 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-06-28 | 2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416 | 53A/3 | Completed
2025-06-28 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-28 | 2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416 | 48/0 | Completed
2025-06-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-28 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416 | 28/1 | Completed
2025-06-28 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-28 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416 | 12/7 | Completed
2025-06-29 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-06-29 | 2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-29 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-29 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416 | 28/1 | Completed
2025-06-29 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-29 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-06-29 | 2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416 | 12/7 | Completed
2025-06-30 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-06-30 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-06-30 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416 | 28/1 | Completed
2025-06-30 | 2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-30 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-01 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-01 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416 | 28/1 | Completed
2025-07-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-02 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-02 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416 | 28/1 | Completed
2025-07-02 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-02 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416 | 21/3 | Completed
2025-07-02 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416 | 25/1 | Completed
2025-07-03 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-03 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416 | 28/1 | Completed
2025-07-03 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-03 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416 | 21/3 | Completed
2025-07-03 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416 | 25/1 | Completed
2025-07-04 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-04 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416 | 28/1 | Completed
2025-07-04 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-04 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416 | 21/3 | Completed
2025-07-04 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416 | 25/1 | Completed
2025-07-05 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-05 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | Completed
2025-07-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-05 | 2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416 | 28/1 | Completed
2025-07-05 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-05 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416 | 21/3 | Completed
2025-07-05 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416 | 25/1 | Completed
2025-07-06 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-06 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | Completed
2025-07-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-06 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-06 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416 | 21/3 | Completed
2025-07-06 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416 | 25/1 | Completed
2025-07-07 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-07 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | Completed
2025-07-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-07 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-07 | 2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416 | 21/3 | Completed
2025-07-07 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416 | 25/1 | Completed
2025-07-08 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-08 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | Completed
2025-07-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-08 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-08 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416 | 25/1 | Completed
2025-07-09 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-09 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | Completed
2025-07-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-09 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-09 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416 | 25/1 | Completed
2025-07-10 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-10 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | Completed
2025-07-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-10 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-10 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416 | 25/1 | Completed
2025-07-11 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-11 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | Completed
2025-07-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-11 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-11 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416 | 25/1 | Completed
2025-07-12 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-12 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | Completed
2025-07-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-12 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-12 | 2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416 | 25/1 | Completed
2025-07-13 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-13 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | Completed
2025-07-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-13 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-13 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-14 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-14 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | Completed
2025-07-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-14 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-14 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-15 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-15 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | Completed
2025-07-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-15 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-15 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-16 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-16 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | Completed
2025-07-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-16 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-16 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-17 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-17 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | Completed
2025-07-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-17 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-17 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-18 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-18 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | Completed
2025-07-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-18 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-18 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-19 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-19 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-07-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-19 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-19 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-20 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-20 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-07-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-20 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-20 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-21 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-21 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-07-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-21 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-21 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-22 | 2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-22 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-07-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-22 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-22 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-23 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-07-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-23 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-23 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-24 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-07-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-24 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-24 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-25 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-07-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-25 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-25 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-26 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-07-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-26 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-26 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-27 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-07-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-27 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-27 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-28 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-07-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-28 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-28 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-07-28 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-29 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-07-29 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-29 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-29 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-29 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-07-29 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-30 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-07-30 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-30 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-30 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-30 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-07-30 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-31 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-07-31 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-07-31 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-31 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-07-31 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-07-31 | 2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-08-01 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-08-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-01 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-08-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-01 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-02 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-08-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-02 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-08-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-02 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-03 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-08-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-03 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-08-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-03 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-04 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-08-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-04 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-08-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-04 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-05 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-08-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-05 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-08-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-05 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-06 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-08-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-06 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-08-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-06 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-07 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-08-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-07 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-08-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-07 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-08 | 2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-08-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-08 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-08-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-08 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-09 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-08-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-09 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-10 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-08-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-10 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-11 | 2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-08-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-11 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-12 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-12 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-13 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-13 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-14 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-14 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-15 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-15 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-16 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-08-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-16 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-16 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-17 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-08-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-17 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-17 | 2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-18 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-08-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-18 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-18 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-08-19 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-08-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-19 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-19 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-08-20 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-08-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-20 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-20 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-08-21 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-08-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-21 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-21 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-08-22 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-08-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-22 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-22 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-08-23 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-08-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-23 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-23 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-08-24 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-08-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-24 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-24 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-08-25 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-08-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-25 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-25 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-08-26 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-08-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-26 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-26 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-08-27 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-08-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-27 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-27 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-08-28 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-08-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-28 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-28 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-08-29 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-08-29 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-29 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-29 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-29 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-08-30 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-08-30 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-30 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-30 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-30 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-08-31 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-08-31 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-08-31 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-31 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-08-31 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-09-01 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-09-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-01 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-09-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-01 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-09-02 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-09-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-02 | 2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-09-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-02 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-09-03 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-09-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-03 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-09-04 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-09-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-04 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-09-05 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-09-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-06 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-09-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-07 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-09-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-08 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-09-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-09 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-09-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-10 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-09-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-11 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-09-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-12 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-09-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-13 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-09-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-14 | 2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-09-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-29 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-29 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-09-30 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-09-30 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-21 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-21 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-22 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-22 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-23 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-23 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-24 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-24 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-25 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-25 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-26 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-26 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-27 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-27 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-28 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-28 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-29 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-29 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-30 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-30 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-10-31 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-10-31 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-01 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-01 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-02 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-02 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-03 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-03 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-04 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-04 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-05 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-05 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-06 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-06 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-07 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-07 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-08 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-08 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-09 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-09 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-10 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-10 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-11 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-11 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-12 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-12 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-13 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-13 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-14 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-14 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-15 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-15 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-16 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-16 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-17 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-17 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-18 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-18 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-19 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-19 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-11-20 | 2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-11-20 | 2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-01-14 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-15 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-16 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-17 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-18 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-19 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-21 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-22 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-23 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-24 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-24 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-25 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-26 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-27 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-27 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-28 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-29 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-30 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-31 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-02-01 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-02 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-03 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-04 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-05 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-06 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-07 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-08 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-09 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-10 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-11 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-12 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-13 | 2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-14 | 2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-15 | 2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-17 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-18 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-19 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-20 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-21 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-22 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-23 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-24 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-25 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-02-26 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-02-27 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-02-28 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-03-01 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-02 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-03 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-04 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-05 | 2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-06 | 2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-06 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-07 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-07 | 2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-07 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-08 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-08 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-09 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-09 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-10 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-10 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-11 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-11 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-11 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-12 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-12 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-12 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-13 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-13 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-13 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-14 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-14 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-14 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-15 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-15 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-15 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-15 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-16 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-16 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-16 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-17 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-17 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-17 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-18 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-18 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-18 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-19 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-19 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-19 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-19 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-20 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-20 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-20 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-21 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-21 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-21 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-22 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-22 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-22 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-22 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-23 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-23 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-23 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-24 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-24 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-24 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-25 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-25 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-25 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-26 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-26 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-26 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-26 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-27 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-27 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-27 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-28 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-28 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-28 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-29 | 2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-29 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-29 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-30 | 2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-30 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-03-30 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-30 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-03-30 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-03-31 | 2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-31 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-03-31 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-03-31 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-01 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-01 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-01 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-04-01 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-02 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-02 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-02 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-04-02 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-03 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-03 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-03 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-04-03 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-03 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-04 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-04 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-04 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-04 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-05 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-05 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-05 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-05 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-06 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-06 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-06 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-06 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-06 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-07 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-07 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-07 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-07 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-08 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-08 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-08 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-08 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-09 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-09 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-09 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-09 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-10 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-10 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-10 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-10 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-11 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-11 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-11 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-11 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-12 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-12 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-12 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-12 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-12 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-13 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-13 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-13 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-13 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-14 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-14 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-14 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-14 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-15 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-15 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-15 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-15 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-15 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-16 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-16 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-16 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-16 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-17 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-17 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-17 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-17 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-18 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-18 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-18 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-18 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-18 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-18 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-19 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-19 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-19 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-19 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-20 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-20 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-20 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-20 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-21 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-21 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-21 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-21 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-22 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-22 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-22 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-22 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-22 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-23 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-23 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-23 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-23 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-24 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-24 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-24 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-24 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-25 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-25 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-25 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-25 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-26 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-26 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-26 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-26 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-27 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-27 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-27 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-27 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-27 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-28 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-28 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-28 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-28 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-29 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-29 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-29 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-29 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-30 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-30 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-30 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-04-30 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-05-01 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-05-01 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-01 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-05-02 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-05-02 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-02 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-02 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-02 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-05-02 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-03 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-03 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-03 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-03 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-04 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-04 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-04 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-04 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-05 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-05 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-05 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-05 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-06 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-06 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-06 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-06 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-06 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-07 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-07 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-07 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-07 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-08 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-08 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-08 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-08 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-08 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-08 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-08 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-09 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-09 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-09 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-09 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-09 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-09 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-09 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-10 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-10 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-10 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-10 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-10 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-10 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-11 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-11 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-11 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-11 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-11 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-11 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-12 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-12 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-12 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-12 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-12 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-13 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-13 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-13 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-13 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-13 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-14 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-14 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-14 | 2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-14 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-14 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-14 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-15 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-15 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-15 | 2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-15 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-15 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-15 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-16 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-16 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-16 | 2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-16 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-16 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-16 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-17 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-17 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-17 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-17 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-17 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-17 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-18 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-18 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-18 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-18 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-18 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-18 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-19 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-19 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-19 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-19 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-19 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-19 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-20 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-20 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-20 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-20 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-20 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-20 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-21 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-21 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-21 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-21 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-21 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-21 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-22 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-22 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-22 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-22 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-22 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-22 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-23 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-23 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-23 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-23 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-23 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-23 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-24 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-24 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-24 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-24 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-24 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-24 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-25 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-25 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-25 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-25 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-25 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-25 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-26 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-26 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-26 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-26 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-26 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-26 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-27 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-27 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-27 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-27 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-27 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-27 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-28 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-28 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-28 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-28 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-28 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-28 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-29 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-29 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-29 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-29 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-29 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-29 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-30 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-30 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-30 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-30 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-30 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-30 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-31 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-31 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-31 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-05-31 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-31 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-31 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-01 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-01 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-01 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-01 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-01 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-01 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-02 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-02 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-02 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-02 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-02 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-02 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-03 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-03 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-03 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-03 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-03 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-03 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-04 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-04 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-04 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-04 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-04 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-04 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-05 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-05 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-05 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-05 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-05 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-05 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-06 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-06 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-06 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-06 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-06 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-06 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-07 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-07 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-07 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-07 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-07 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-07 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-08 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-08 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-08 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-08 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-08 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-08 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-09 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-09 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-09 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-09 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-09 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-09 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-10 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-10 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-10 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-10 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-10 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-10 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-11 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-11 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-11 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-11 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-11 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-11 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-12 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-12 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-12 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-12 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-12 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-12 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-13 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-13 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-13 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-13 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-13 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-13 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-14 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-14 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-14 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-14 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-14 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-14 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-15 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-15 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-15 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-15 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-15 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-15 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-16 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-16 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-16 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-16 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-16 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-17 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-17 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-17 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-17 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-17 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-18 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-18 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-18 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-18 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-18 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-19 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-19 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-19 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-19 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-19 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-20 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-20 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-20 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-20 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-20 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-21 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-21 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-21 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-21 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-21 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-22 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-22 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-22 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-22 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-22 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-23 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-23 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-23 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-23 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-24 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-24 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-24 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-25 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-25 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-25 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-26 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-26 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-26 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-27 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-27 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-27 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-27 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-28 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-28 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-28 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-28 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-29 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-29 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-29 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-29 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-30 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-30 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-30 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-30 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-01 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-01 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-01 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-01 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-02 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-02 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-02 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-02 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-03 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-03 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-03 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-03 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-04 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-04 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-04 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-04 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-05 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-05 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-05 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-05 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-06 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-06 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-06 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-06 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-07 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-07 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-07 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-07 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-08 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-08 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-08 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-08 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-09 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-09 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-09 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-09 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-10 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-10 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-10 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-10 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-11 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-11 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-11 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-11 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-12 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-12 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-12 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-12 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-13 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-13 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-13 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-14 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-14 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-14 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-15 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-15 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-15 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-16 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-16 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-16 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-17 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-17 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-17 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-18 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-18 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-18 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-19 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-19 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-19 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-20 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-20 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-20 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-21 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-21 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-21 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-22 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-22 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-22 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-23 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-23 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-23 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-24 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-24 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-24 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-25 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-25 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-25 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-26 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-26 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-26 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-27 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-27 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-27 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-28 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-28 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-28 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-29 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-29 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-30 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-30 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-31 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-31 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-08-01 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-02 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-03 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-04 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-04 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-04 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-05 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-05 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-05 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-06 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-06 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-06 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-07 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-07 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-07 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-08 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-08 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-08 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-09 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-09 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-09 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-10 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-10 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-10 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-11 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-11 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-11 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-12 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-12 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-12 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-12 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-13 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-13 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-13 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-14 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-14 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-14 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-15 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-15 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-15 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-16 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-16 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-16 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-17 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-17 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-17 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-18 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-18 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-18 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-18 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-19 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-19 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-19 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-19 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-20 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-20 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-20 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-20 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-21 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-21 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-21 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-21 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-21 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-22 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-22 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-22 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-22 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-23 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-23 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-23 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-23 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-24 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-24 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-24 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-24 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-25 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-25 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-25 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-25 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-25 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-25 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-25 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-25 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-26 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-26 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-26 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-26 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-26 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-26 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-26 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-26 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-27 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-27 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-27 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-27 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-27 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-27 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-27 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-27 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-28 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-28 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-28 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-28 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-28 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-28 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-28 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-28 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-29 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-29 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-29 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-29 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-29 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-29 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-29 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-29 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-30 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-30 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-30 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-30 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-30 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-30 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-30 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-30 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-31 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-31 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-31 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-31 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-31 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-31 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-31 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-31 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-01 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-01 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-01 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-01 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-01 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-01 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-01 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-01 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-01 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-02 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-02 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-02 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-02 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-02 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-02 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-02 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-02 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-02 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-03 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-03 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-03 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-03 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-03 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-03 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-03 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-03 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-03 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-04 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-04 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-04 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-04 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-04 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-04 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-04 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-04 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-04 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-05 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-05 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-05 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-05 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-05 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-05 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-05 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-05 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-05 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-06 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-06 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-06 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-06 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-06 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-06 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-06 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-06 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-07 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-07 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-07 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-07 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-07 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-07 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-07 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-07 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-08 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-08 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-08 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-08 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-08 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-08 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-08 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-08 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-09 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-09 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-09 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-09 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-09 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-09 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-09 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-09 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-10 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-10 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-10 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-10 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-10 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-10 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-10 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-10 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-10 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-11 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-11 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-11 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-11 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-11 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-11 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-11 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-11 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-11 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-11 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-12 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-12 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-12 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-12 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-12 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-12 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-12 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-12 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-12 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-12 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-13 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-13 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-13 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-13 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-13 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-13 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-13 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-13 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-13 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-13 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-14 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-14 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-14 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-14 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-14 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-14 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-14 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-14 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-14 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-14 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-14 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-15 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-15 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-15 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-15 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-15 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-15 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-15 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-15 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-15 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-15 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-15 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-16 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-16 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-16 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-16 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-16 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-16 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-16 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-16 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-16 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-16 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-16 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-17 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-17 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-17 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-17 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-17 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-17 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-17 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-17 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-17 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-17 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-18 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-18 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-18 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-18 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-18 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-18 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-18 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-18 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-18 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-18 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-18 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-19 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-19 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-19 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-19 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-19 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-19 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-19 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-19 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-19 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-19 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-19 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-20 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-20 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-20 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-20 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-20 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-20 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-20 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-20 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-20 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-20 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-20 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-21 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-21 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-21 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-21 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-21 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-21 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-21 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-21 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-21 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-21 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-21 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-22 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-22 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-22 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-22 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-22 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-22 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-22 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-22 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-22 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-22 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-22 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-23 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-23 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-23 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-23 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-23 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-23 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-23 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-23 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-23 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-23 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-24 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-24 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-24 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-24 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-24 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-24 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-24 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-24 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-24 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-24 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-25 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-25 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-25 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-25 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-25 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-25 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-25 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-25 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-25 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-25 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-26 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-26 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-26 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-26 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-26 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-26 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-26 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-26 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-26 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-27 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-27 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-27 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-27 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-27 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-27 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-27 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-27 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-27 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-28 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-28 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-28 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-28 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-28 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-28 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-28 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-28 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-28 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-29 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-29 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-29 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-29 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-29 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-29 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-29 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-30 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-30 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-30 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-30 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-30 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-10-01 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-01 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-10-02 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-03 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-04 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2023-09-13 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401 | 57/9 | Complete
2023-09-14 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401 | 57/9 | Complete
2023-09-15 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401 | 57/9 | Complete
2023-09-16 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401 | 57/9 | Complete
2023-09-17 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401 | 57/9 | Complete
2023-09-18 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401 | 57/9 | Complete
2023-09-18 | 2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401 | 58/12 | Complete
2023-09-19 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401 | 57/9 | Complete
2023-09-19 | 2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401 | 58/12 | Complete
2023-09-20 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401 | 57/9 | Complete
2023-09-20 | 2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401 | 58/12 | Complete
2023-09-21 | 2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401 | 57/9 | Complete
2023-09-21 | 2023-09-21 | 2023-09-26 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/11 | Complete
2023-09-21 | 2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401 | 58/12 | Complete
2023-09-22 | 2023-09-21 | 2023-09-26 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/11 | Complete
2023-09-22 | 2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401 | 58/12 | Complete
2023-09-23 | 2023-09-21 | 2023-09-26 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/11 | Complete
2023-09-23 | 2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401 | 58/12 | Complete
2023-09-24 | 2023-09-21 | 2023-09-26 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/11 | Complete
2023-09-24 | 2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401 | 58/12 | Complete
2023-09-25 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-09-25 | 2023-09-21 | 2023-09-26 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/11 | Complete
2023-09-25 | 2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401 | 58/12 | Complete
2023-09-25 | 2023-09-25 | 2023-10-01 | Sunny Const | 37.504 | 5.3577 | TB401 | 58/14 | Complete
2023-09-26 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-09-26 | 2023-09-21 | 2023-09-26 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/11 | Complete
2023-09-26 | 2023-09-26 | 2023-10-01 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/13 | Complete
2023-09-26 | 2023-09-25 | 2023-10-01 | Sunny Const | 37.504 | 5.3577 | TB401 | 58/14 | Complete
2023-09-27 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-09-27 | 2023-09-26 | 2023-10-01 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/13 | Complete
2023-09-27 | 2023-09-25 | 2023-10-01 | Sunny Const | 37.504 | 5.3577 | TB401 | 58/14 | Complete
2023-09-28 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-09-28 | 2023-09-26 | 2023-10-01 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/13 | Complete
2023-09-28 | 2023-09-25 | 2023-10-01 | Sunny Const | 37.504 | 5.3577 | TB401 | 58/14 | Complete
2023-09-29 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-09-29 | 2023-09-26 | 2023-10-01 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/13 | Complete
2023-09-29 | 2023-09-25 | 2023-10-01 | Sunny Const | 37.504 | 5.3577 | TB401 | 58/14 | Complete
2023-09-30 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-09-30 | 2023-09-26 | 2023-10-01 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/13 | Complete
2023-09-30 | 2023-09-25 | 2023-10-01 | Sunny Const | 37.504 | 5.3577 | TB401 | 58/14 | Complete
2023-10-01 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-10-01 | 2023-09-26 | 2023-10-01 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/13 | Complete
2023-10-01 | 2023-10-01 | 2023-10-06 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/10 | Complete
2023-10-01 | 2023-09-25 | 2023-10-01 | Sunny Const | 37.504 | 5.3577 | TB401 | 58/14 | Complete
2023-10-01 | 2023-10-01 | 2023-10-07 | Sunny Const | 37.504 | 5.3577 | TB401 | 58/9 | Complete
2023-10-02 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-10-02 | 2023-10-01 | 2023-10-06 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/10 | Complete
2023-10-02 | 2023-10-01 | 2023-10-07 | Sunny Const | 37.504 | 5.3577 | TB401 | 58/9 | Complete
2023-10-03 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-10-03 | 2023-10-01 | 2023-10-06 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/10 | Complete
2023-10-03 | 2023-10-01 | 2023-10-07 | Sunny Const | 37.504 | 5.3577 | TB401 | 58/9 | Complete
2023-10-03 | 2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401 | 52/1 | Complete
2023-10-04 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-10-04 | 2023-10-01 | 2023-10-06 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/10 | Complete
2023-10-04 | 2023-10-01 | 2023-10-07 | Sunny Const | 37.504 | 5.3577 | TB401 | 58/9 | Complete
2023-10-04 | 2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401 | 52/1 | Complete
2023-10-05 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-10-05 | 2023-10-01 | 2023-10-06 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/10 | Complete
2023-10-05 | 2023-10-01 | 2023-10-07 | Sunny Const | 37.504 | 5.3577 | TB401 | 58/9 | Complete
2023-10-05 | 2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401 | 52/1 | Complete
2023-10-06 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-10-06 | 2023-10-01 | 2023-10-06 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/10 | Complete
2023-10-06 | 2023-10-06 | 2023-10-11 | Sobha Devi | 38.847 | 6.4745 | TB401 | 57/12 | Complete
2023-10-06 | 2023-10-01 | 2023-10-07 | Sunny Const | 37.504 | 5.3577 | TB401 | 58/9 | Complete
2023-10-06 | 2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401 | 52/1 | Complete
2023-10-07 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-10-07 | 2023-10-06 | 2023-10-11 | Sobha Devi | 38.847 | 6.4745 | TB401 | 57/12 | Complete
2023-10-07 | 2023-10-01 | 2023-10-07 | Sunny Const | 37.504 | 5.3577 | TB401 | 58/9 | Complete
2023-10-07 | 2023-10-07 | 2023-10-11 | Sunny Const | 37.504 | 7.5008 | TB401 | 58/8 | Complete
2023-10-07 | 2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401 | 52/1 | Complete
2023-10-08 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-10-08 | 2023-10-06 | 2023-10-11 | Sobha Devi | 38.847 | 6.4745 | TB401 | 57/12 | Complete
2023-10-08 | 2023-10-07 | 2023-10-11 | Sunny Const | 37.504 | 7.5008 | TB401 | 58/8 | Complete
2023-10-08 | 2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401 | 52/1 | Complete
2023-10-09 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-10-09 | 2023-10-06 | 2023-10-11 | Sobha Devi | 38.847 | 6.4745 | TB401 | 57/12 | Complete
2023-10-09 | 2023-10-07 | 2023-10-11 | Sunny Const | 37.504 | 7.5008 | TB401 | 58/8 | Complete
2023-10-09 | 2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401 | 52/1 | Complete
2023-10-10 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-10-10 | 2023-10-06 | 2023-10-11 | Sobha Devi | 38.847 | 6.4745 | TB401 | 57/12 | Complete
2023-10-10 | 2023-10-10 | 2023-10-16 | Sobha Devi | 37.504 | 5.3577 | TB401 | 57/2 | Complete
2023-10-10 | 2023-10-07 | 2023-10-11 | Sunny Const | 37.504 | 7.5008 | TB401 | 58/8 | Complete
2023-10-10 | 2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401 | 58/16 | Complete
2023-10-10 | 2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401 | 52/1 | Complete
2023-10-10 | 2023-10-10 | 2023-10-15 | Suraj Const | 37.504 | 6.2507 | TB401 | 51/2 | Complete
2023-10-11 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-10-11 | 2023-10-06 | 2023-10-11 | Sobha Devi | 38.847 | 6.4745 | TB401 | 57/12 | Complete
2023-10-11 | 2023-10-10 | 2023-10-16 | Sobha Devi | 37.504 | 5.3577 | TB401 | 57/2 | Complete
2023-10-11 | 2023-10-07 | 2023-10-11 | Sunny Const | 37.504 | 7.5008 | TB401 | 58/8 | Complete
2023-10-11 | 2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401 | 58/16 | Complete
2023-10-11 | 2023-10-10 | 2023-10-15 | Suraj Const | 37.504 | 6.2507 | TB401 | 51/2 | Complete
2023-10-12 | 2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-10-12 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401 | 58/3 | Complete
2023-10-12 | 2023-10-10 | 2023-10-16 | Sobha Devi | 37.504 | 5.3577 | TB401 | 57/2 | Complete
2023-10-12 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-12 | 2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401 | 58/16 | Complete
2023-10-12 | 2023-10-10 | 2023-10-15 | Suraj Const | 37.504 | 6.2507 | TB401 | 51/2 | Complete
2023-10-13 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401 | 58/3 | Complete
2023-10-13 | 2023-10-10 | 2023-10-16 | Sobha Devi | 37.504 | 5.3577 | TB401 | 57/2 | Complete
2023-10-13 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-13 | 2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401 | 58/16 | Complete
2023-10-13 | 2023-10-10 | 2023-10-15 | Suraj Const | 37.504 | 6.2507 | TB401 | 51/2 | Complete
2023-10-14 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401 | 58/3 | Complete
2023-10-14 | 2023-10-10 | 2023-10-16 | Sobha Devi | 37.504 | 5.3577 | TB401 | 57/2 | Complete
2023-10-14 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-14 | 2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401 | 58/16 | Complete
2023-10-14 | 2023-10-10 | 2023-10-15 | Suraj Const | 37.504 | 6.2507 | TB401 | 51/2 | Complete
2023-10-15 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401 | 58/3 | Complete
2023-10-15 | 2023-10-10 | 2023-10-16 | Sobha Devi | 37.504 | 5.3577 | TB401 | 57/2 | Complete
2023-10-15 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-15 | 2023-10-15 | 2023-10-20 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/3 | Complete
2023-10-15 | 2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401 | 58/16 | Complete
2023-10-15 | 2023-10-10 | 2023-10-15 | Suraj Const | 37.504 | 6.2507 | TB401 | 51/2 | Complete
2023-10-15 | 2023-10-15 | 2023-10-21 | Suraj Const | 38.847 | 5.5496 | TB401 | 51/4 | Complete
2023-10-16 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401 | 58/3 | Complete
2023-10-16 | 2023-10-10 | 2023-10-16 | Sobha Devi | 37.504 | 5.3577 | TB401 | 57/2 | Complete
2023-10-16 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-16 | 2023-10-15 | 2023-10-20 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/3 | Complete
2023-10-16 | 2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401 | 58/16 | Complete
2023-10-16 | 2023-10-15 | 2023-10-21 | Suraj Const | 38.847 | 5.5496 | TB401 | 51/4 | Complete
2023-10-17 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401 | 58/3 | Complete
2023-10-17 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-17 | 2023-10-15 | 2023-10-20 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/3 | Complete
2023-10-17 | 2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401 | 58/16 | Complete
2023-10-17 | 2023-10-17 | 2023-10-23 | Sunny Const | 38.847 | 5.5496 | TB401 | 58/10 | Complete
2023-10-17 | 2023-10-15 | 2023-10-21 | Suraj Const | 38.847 | 5.5496 | TB401 | 51/4 | Complete
2023-10-18 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401 | 58/3 | Complete
2023-10-18 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-18 | 2023-10-15 | 2023-10-20 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/3 | Complete
2023-10-18 | 2023-10-17 | 2023-10-23 | Sunny Const | 38.847 | 5.5496 | TB401 | 58/10 | Complete
2023-10-18 | 2023-10-15 | 2023-10-21 | Suraj Const | 38.847 | 5.5496 | TB401 | 51/4 | Complete
2023-10-19 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401 | 58/3 | Complete
2023-10-19 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-19 | 2023-10-15 | 2023-10-20 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/3 | Complete
2023-10-19 | 2023-10-17 | 2023-10-23 | Sunny Const | 38.847 | 5.5496 | TB401 | 58/10 | Complete
2023-10-19 | 2023-10-15 | 2023-10-21 | Suraj Const | 38.847 | 5.5496 | TB401 | 51/4 | Complete
2023-10-20 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401 | 58/3 | Complete
2023-10-20 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401 | 58/5 | Complete
2023-10-20 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-20 | 2023-10-15 | 2023-10-20 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/3 | Complete
2023-10-20 | 2023-10-20 | 2023-10-26 | Sobha Devi | 37.504 | 5.3577 | TB401 | 57/4 | Complete
2023-10-20 | 2023-10-17 | 2023-10-23 | Sunny Const | 38.847 | 5.5496 | TB401 | 58/10 | Complete
2023-10-20 | 2023-10-15 | 2023-10-21 | Suraj Const | 38.847 | 5.5496 | TB401 | 51/4 | Complete
2023-10-20 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401 | 51/5 | Complete
2023-10-21 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401 | 58/3 | Complete
2023-10-21 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401 | 58/5 | Complete
2023-10-21 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-21 | 2023-10-20 | 2023-10-26 | Sobha Devi | 37.504 | 5.3577 | TB401 | 57/4 | Complete
2023-10-21 | 2023-10-17 | 2023-10-23 | Sunny Const | 38.847 | 5.5496 | TB401 | 58/10 | Complete
2023-10-21 | 2023-10-15 | 2023-10-21 | Suraj Const | 38.847 | 5.5496 | TB401 | 51/4 | Complete
2023-10-21 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401 | 51/5 | Complete
2023-10-22 | 2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401 | 58/3 | Complete
2023-10-22 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401 | 58/5 | Complete
2023-10-22 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-22 | 2023-10-20 | 2023-10-26 | Sobha Devi | 37.504 | 5.3577 | TB401 | 57/4 | Complete
2023-10-22 | 2023-10-17 | 2023-10-23 | Sunny Const | 38.847 | 5.5496 | TB401 | 58/10 | Complete
2023-10-22 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401 | 51/5 | Complete
2023-10-23 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401 | 58/5 | Complete
2023-10-23 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-23 | 2023-10-20 | 2023-10-26 | Sobha Devi | 37.504 | 5.3577 | TB401 | 57/4 | Complete
2023-10-23 | 2023-10-17 | 2023-10-23 | Sunny Const | 38.847 | 5.5496 | TB401 | 58/10 | Complete
2023-10-23 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401 | 58/11 | Complete
2023-10-23 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401 | 51/5 | Complete
2023-10-24 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401 | 58/5 | Complete
2023-10-24 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-24 | 2023-10-20 | 2023-10-26 | Sobha Devi | 37.504 | 5.3577 | TB401 | 57/4 | Complete
2023-10-24 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401 | 58/11 | Complete
2023-10-24 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401 | 51/5 | Complete
2023-10-25 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401 | 58/5 | Complete
2023-10-25 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-25 | 2023-10-20 | 2023-10-26 | Sobha Devi | 37.504 | 5.3577 | TB401 | 57/4 | Complete
2023-10-25 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401 | 58/11 | Complete
2023-10-25 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401 | 51/5 | Complete
2023-10-26 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401 | 58/5 | Complete
2023-10-26 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-26 | 2023-10-20 | 2023-10-26 | Sobha Devi | 37.504 | 5.3577 | TB401 | 57/4 | Complete
2023-10-26 | 2023-10-26 | 2023-10-30 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/5 | Complete
2023-10-26 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401 | 58/11 | Complete
2023-10-26 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401 | 51/5 | Complete
2023-10-27 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401 | 58/5 | Complete
2023-10-27 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-27 | 2023-10-26 | 2023-10-30 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/5 | Complete
2023-10-27 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401 | 58/11 | Complete
2023-10-27 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401 | 51/5 | Complete
2023-10-28 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401 | 58/5 | Complete
2023-10-28 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-28 | 2023-10-26 | 2023-10-30 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/5 | Complete
2023-10-28 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401 | 58/11 | Complete
2023-10-28 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401 | 51/5 | Complete
2023-10-29 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401 | 58/5 | Complete
2023-10-29 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-29 | 2023-10-26 | 2023-10-30 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/5 | Complete
2023-10-29 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401 | 58/11 | Complete
2023-10-29 | 2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401 | 51/5 | Complete
2023-10-29 | 2023-10-29 | 2023-11-04 | Suraj Const | 38.847 | 5.5496 | TB401 | 51/7 | Complete
2023-10-30 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401 | 58/5 | Complete
2023-10-30 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-30 | 2023-10-26 | 2023-10-30 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/5 | Complete
2023-10-30 | 2023-10-30 | 2023-11-03 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/8 | Complete
2023-10-30 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401 | 58/11 | Complete
2023-10-30 | 2023-10-29 | 2023-11-04 | Suraj Const | 38.847 | 5.5496 | TB401 | 51/7 | Complete
2023-10-31 | 2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401 | 58/5 | Complete
2023-10-31 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401 | 58/4 | Complete
2023-10-31 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-10-31 | 2023-10-30 | 2023-11-03 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/8 | Complete
2023-10-31 | 2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401 | 58/11 | Complete
2023-10-31 | 2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401 | 59/6 | Complete
2023-10-31 | 2023-10-29 | 2023-11-04 | Suraj Const | 38.847 | 5.5496 | TB401 | 51/7 | Complete
2023-11-01 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401 | 58/4 | Complete
2023-11-01 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-01 | 2023-10-30 | 2023-11-03 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/8 | Complete
2023-11-01 | 2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401 | 59/6 | Complete
2023-11-01 | 2023-10-29 | 2023-11-04 | Suraj Const | 38.847 | 5.5496 | TB401 | 51/7 | Complete
2023-11-02 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401 | 58/4 | Complete
2023-11-02 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-02 | 2023-10-30 | 2023-11-03 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/8 | Complete
2023-11-02 | 2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401 | 59/6 | Complete
2023-11-02 | 2023-10-29 | 2023-11-04 | Suraj Const | 38.847 | 5.5496 | TB401 | 51/7 | Complete
2023-11-03 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401 | 58/4 | Complete
2023-11-03 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-03 | 2023-10-30 | 2023-11-03 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/8 | Complete
2023-11-03 | 2023-11-03 | 2023-11-07 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/7 | Complete
2023-11-03 | 2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401 | 59/6 | Complete
2023-11-03 | 2023-10-29 | 2023-11-04 | Suraj Const | 38.847 | 5.5496 | TB401 | 51/7 | Complete
2023-11-04 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401 | 58/4 | Complete
2023-11-04 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-04 | 2023-11-03 | 2023-11-07 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/7 | Complete
2023-11-04 | 2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401 | 59/6 | Complete
2023-11-04 | 2023-10-29 | 2023-11-04 | Suraj Const | 38.847 | 5.5496 | TB401 | 51/7 | Complete
2023-11-04 | 2023-11-04 | 2023-11-09 | Suraj Const | 37.504 | 6.2507 | TB401 | 51/3 | Complete
2023-11-05 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401 | 58/4 | Complete
2023-11-05 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-05 | 2023-11-03 | 2023-11-07 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/7 | Complete
2023-11-05 | 2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401 | 59/6 | Complete
2023-11-05 | 2023-11-04 | 2023-11-09 | Suraj Const | 37.504 | 6.2507 | TB401 | 51/3 | Complete
2023-11-06 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401 | 58/4 | Complete
2023-11-06 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-06 | 2023-11-03 | 2023-11-07 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/7 | Complete
2023-11-06 | 2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401 | 59/6 | Complete
2023-11-06 | 2023-11-04 | 2023-11-09 | Suraj Const | 37.504 | 6.2507 | TB401 | 51/3 | Complete
2023-11-07 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401 | 58/4 | Complete
2023-11-07 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-07 | 2023-11-03 | 2023-11-07 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/7 | Complete
2023-11-07 | 2023-11-07 | 2023-11-13 | Sobha Devi | 38.847 | 5.5496 | TB401 | 57/1 | Complete
2023-11-07 | 2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401 | 59/6 | Complete
2023-11-07 | 2023-11-07 | 2023-11-13 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/5 | Complete
2023-11-07 | 2023-11-04 | 2023-11-09 | Suraj Const | 37.504 | 6.2507 | TB401 | 51/3 | Complete
2023-11-08 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401 | 58/4 | Complete
2023-11-08 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-08 | 2023-11-07 | 2023-11-13 | Sobha Devi | 38.847 | 5.5496 | TB401 | 57/1 | Complete
2023-11-08 | 2023-11-07 | 2023-11-13 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/5 | Complete
2023-11-08 | 2023-11-04 | 2023-11-09 | Suraj Const | 37.504 | 6.2507 | TB401 | 51/3 | Complete
2023-11-09 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401 | 58/4 | Complete
2023-11-09 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-09 | 2023-11-07 | 2023-11-13 | Sobha Devi | 38.847 | 5.5496 | TB401 | 57/1 | Complete
2023-11-09 | 2023-11-07 | 2023-11-13 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/5 | Complete
2023-11-09 | 2023-11-04 | 2023-11-09 | Suraj Const | 37.504 | 6.2507 | TB401 | 51/3 | Complete
2023-11-10 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401 | 58/4 | Complete
2023-11-10 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-10 | 2023-11-07 | 2023-11-13 | Sobha Devi | 38.847 | 5.5496 | TB401 | 57/1 | Complete
2023-11-10 | 2023-11-07 | 2023-11-13 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/5 | Complete
2023-11-10 | 2023-11-10 | 2023-11-14 | Suraj Const | 38.847 | 7.7694 | TB401 | 51/10 | Complete
2023-11-11 | 2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401 | 58/4 | Complete
2023-11-11 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-11 | 2023-11-07 | 2023-11-13 | Sobha Devi | 38.847 | 5.5496 | TB401 | 57/1 | Complete
2023-11-11 | 2023-11-07 | 2023-11-13 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/5 | Complete
2023-11-11 | 2023-11-10 | 2023-11-14 | Suraj Const | 38.847 | 7.7694 | TB401 | 51/10 | Complete
2023-11-12 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-12 | 2023-11-07 | 2023-11-13 | Sobha Devi | 38.847 | 5.5496 | TB401 | 57/1 | Complete
2023-11-12 | 2023-11-07 | 2023-11-13 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/5 | Complete
2023-11-12 | 2023-11-10 | 2023-11-14 | Suraj Const | 38.847 | 7.7694 | TB401 | 51/10 | Complete
2023-11-13 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 58/6 | Complete
2023-11-13 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-13 | 2023-11-07 | 2023-11-13 | Sobha Devi | 38.847 | 5.5496 | TB401 | 57/1 | Complete
2023-11-13 | 2023-11-13 | 2023-11-16 | Sobha Devi | 38.847 | 9.7118 | TB401 | 56/9 | Complete
2023-11-13 | 2023-11-07 | 2023-11-13 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/5 | Complete
2023-11-13 | 2023-11-13 | 2023-11-18 | Sunny Const | 37.504 | 6.2507 | TB401 | 59/3 | Complete
2023-11-13 | 2023-11-10 | 2023-11-14 | Suraj Const | 38.847 | 7.7694 | TB401 | 51/10 | Complete
2023-11-14 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 58/6 | Complete
2023-11-14 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-14 | 2023-11-13 | 2023-11-16 | Sobha Devi | 38.847 | 9.7118 | TB401 | 56/9 | Complete
2023-11-14 | 2023-11-13 | 2023-11-18 | Sunny Const | 37.504 | 6.2507 | TB401 | 59/3 | Complete
2023-11-14 | 2023-11-10 | 2023-11-14 | Suraj Const | 38.847 | 7.7694 | TB401 | 51/10 | Complete
2023-11-15 | 2023-11-15 | 2023-11-21 | Chinta Devi | 37.504 | 5.3577 | TB401 | 55/7 | Complete
2023-11-15 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 58/6 | Complete
2023-11-15 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-15 | 2023-11-13 | 2023-11-16 | Sobha Devi | 38.847 | 9.7118 | TB401 | 56/9 | Complete
2023-11-15 | 2023-11-13 | 2023-11-18 | Sunny Const | 37.504 | 6.2507 | TB401 | 59/3 | Complete
2023-11-15 | 2023-11-15 | 2023-11-19 | Suraj Const | 38.847 | 7.7694 | TB401 | 52/2 | Complete
2023-11-16 | 2023-11-15 | 2023-11-21 | Chinta Devi | 37.504 | 5.3577 | TB401 | 55/7 | Complete
2023-11-16 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 58/6 | Complete
2023-11-16 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-16 | 2023-11-13 | 2023-11-16 | Sobha Devi | 38.847 | 9.7118 | TB401 | 56/9 | Complete
2023-11-16 | 2023-11-16 | 2023-11-21 | Sobha Devi | 38.847 | 6.4745 | TB401 | 56/8 | Complete
2023-11-16 | 2023-11-13 | 2023-11-18 | Sunny Const | 37.504 | 6.2507 | TB401 | 59/3 | Complete
2023-11-16 | 2023-11-15 | 2023-11-19 | Suraj Const | 38.847 | 7.7694 | TB401 | 52/2 | Complete
2023-11-17 | 2023-11-15 | 2023-11-21 | Chinta Devi | 37.504 | 5.3577 | TB401 | 55/7 | Complete
2023-11-17 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 58/6 | Complete
2023-11-17 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-17 | 2023-11-16 | 2023-11-21 | Sobha Devi | 38.847 | 6.4745 | TB401 | 56/8 | Complete
2023-11-17 | 2023-11-13 | 2023-11-18 | Sunny Const | 37.504 | 6.2507 | TB401 | 59/3 | Complete
2023-11-17 | 2023-11-15 | 2023-11-19 | Suraj Const | 38.847 | 7.7694 | TB401 | 52/2 | Complete
2023-11-18 | 2023-11-15 | 2023-11-21 | Chinta Devi | 37.504 | 5.3577 | TB401 | 55/7 | Complete
2023-11-18 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 58/6 | Complete
2023-11-18 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-18 | 2023-11-16 | 2023-11-21 | Sobha Devi | 38.847 | 6.4745 | TB401 | 56/8 | Complete
2023-11-18 | 2023-11-13 | 2023-11-18 | Sunny Const | 37.504 | 6.2507 | TB401 | 59/3 | Complete
2023-11-18 | 2023-11-18 | 2023-11-24 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/2 | Complete
2023-11-18 | 2023-11-15 | 2023-11-19 | Suraj Const | 38.847 | 7.7694 | TB401 | 52/2 | Complete
2023-11-19 | 2023-11-15 | 2023-11-21 | Chinta Devi | 37.504 | 5.3577 | TB401 | 55/7 | Complete
2023-11-19 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 58/6 | Complete
2023-11-19 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-19 | 2023-11-16 | 2023-11-21 | Sobha Devi | 38.847 | 6.4745 | TB401 | 56/8 | Complete
2023-11-19 | 2023-11-18 | 2023-11-24 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/2 | Complete
2023-11-19 | 2023-11-15 | 2023-11-19 | Suraj Const | 38.847 | 7.7694 | TB401 | 52/2 | Complete
2023-11-19 | 2023-11-19 | 2023-11-24 | Suraj Const | 38.847 | 6.4745 | TB401 | 52/5 | Complete
2023-11-20 | 2023-11-15 | 2023-11-21 | Chinta Devi | 37.504 | 5.3577 | TB401 | 55/7 | Complete
2023-11-20 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 58/6 | Complete
2023-11-20 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-20 | 2023-11-16 | 2023-11-21 | Sobha Devi | 38.847 | 6.4745 | TB401 | 56/8 | Complete
2023-11-20 | 2023-11-18 | 2023-11-24 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/2 | Complete
2023-11-20 | 2023-11-19 | 2023-11-24 | Suraj Const | 38.847 | 6.4745 | TB401 | 52/5 | Complete
2023-11-21 | 2023-11-15 | 2023-11-21 | Chinta Devi | 37.504 | 5.3577 | TB401 | 55/7 | Complete
2023-11-21 | 2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 58/6 | Complete
2023-11-21 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-21 | 2023-11-16 | 2023-11-21 | Sobha Devi | 38.847 | 6.4745 | TB401 | 56/8 | Complete
2023-11-21 | 2023-11-18 | 2023-11-24 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/2 | Complete
2023-11-21 | 2023-11-19 | 2023-11-24 | Suraj Const | 38.847 | 6.4745 | TB401 | 52/5 | Complete
2023-11-22 | 2023-11-22 | 2023-11-26 | Chinta Devi | 37.504 | 7.5008 | TB401 | 55/5 | Complete
2023-11-22 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401 | 50/4 | Complete
2023-11-22 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-22 | 2023-11-22 | 2023-11-24 | Sobha Devi | 38.847 | 12.949 | TB401 | 56/7 | Complete
2023-11-22 | 2023-11-18 | 2023-11-24 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/2 | Complete
2023-11-22 | 2023-11-19 | 2023-11-24 | Suraj Const | 38.847 | 6.4745 | TB401 | 52/5 | Complete
2023-11-23 | 2023-11-22 | 2023-11-26 | Chinta Devi | 37.504 | 7.5008 | TB401 | 55/5 | Complete
2023-11-23 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401 | 50/4 | Complete
2023-11-23 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-23 | 2023-11-22 | 2023-11-24 | Sobha Devi | 38.847 | 12.949 | TB401 | 56/7 | Complete
2023-11-23 | 2023-11-18 | 2023-11-24 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/2 | Complete
2023-11-23 | 2023-11-19 | 2023-11-24 | Suraj Const | 38.847 | 6.4745 | TB401 | 52/5 | Complete
2023-11-24 | 2023-11-22 | 2023-11-26 | Chinta Devi | 37.504 | 7.5008 | TB401 | 55/5 | Complete
2023-11-24 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401 | 50/4 | Complete
2023-11-24 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-24 | 2023-11-22 | 2023-11-24 | Sobha Devi | 38.847 | 12.949 | TB401 | 56/7 | Complete
2023-11-24 | 2023-11-24 | 2023-11-29 | Sobha Devi | 37.504 | 6.2507 | TB401 | 56/3 | Complete
2023-11-24 | 2023-11-18 | 2023-11-24 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/2 | Complete
2023-11-24 | 2023-11-24 | 2023-11-30 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/1 | Complete
2023-11-24 | 2023-11-19 | 2023-11-24 | Suraj Const | 38.847 | 6.4745 | TB401 | 52/5 | Complete
2023-11-24 | 2023-11-24 | 2023-11-29 | Suraj Const | 38.847 | 6.4745 | TB401 | 53/3 | Complete
2023-11-25 | 2023-11-22 | 2023-11-26 | Chinta Devi | 37.504 | 7.5008 | TB401 | 55/5 | Complete
2023-11-25 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401 | 50/4 | Complete
2023-11-25 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-25 | 2023-11-24 | 2023-11-29 | Sobha Devi | 37.504 | 6.2507 | TB401 | 56/3 | Complete
2023-11-25 | 2023-11-24 | 2023-11-30 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/1 | Complete
2023-11-25 | 2023-11-24 | 2023-11-29 | Suraj Const | 38.847 | 6.4745 | TB401 | 53/3 | Complete
2023-11-26 | 2023-11-22 | 2023-11-26 | Chinta Devi | 37.504 | 7.5008 | TB401 | 55/5 | Complete
2023-11-26 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401 | 50/4 | Complete
2023-11-26 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-26 | 2023-11-24 | 2023-11-29 | Sobha Devi | 37.504 | 6.2507 | TB401 | 56/3 | Complete
2023-11-26 | 2023-11-24 | 2023-11-30 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/1 | Complete
2023-11-26 | 2023-11-24 | 2023-11-29 | Suraj Const | 38.847 | 6.4745 | TB401 | 53/3 | Complete
2023-11-27 | 2023-11-27 | 2023-12-02 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/4 | Complete
2023-11-27 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401 | 50/4 | Complete
2023-11-27 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-27 | 2023-11-24 | 2023-11-29 | Sobha Devi | 37.504 | 6.2507 | TB401 | 56/3 | Complete
2023-11-27 | 2023-11-24 | 2023-11-30 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/1 | Complete
2023-11-27 | 2023-11-24 | 2023-11-29 | Suraj Const | 38.847 | 6.4745 | TB401 | 53/3 | Complete
2023-11-28 | 2023-11-27 | 2023-12-02 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/4 | Complete
2023-11-28 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401 | 50/4 | Complete
2023-11-28 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-28 | 2023-11-24 | 2023-11-29 | Sobha Devi | 37.504 | 6.2507 | TB401 | 56/3 | Complete
2023-11-28 | 2023-11-24 | 2023-11-30 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/1 | Complete
2023-11-28 | 2023-11-24 | 2023-11-29 | Suraj Const | 38.847 | 6.4745 | TB401 | 53/3 | Complete
2023-11-29 | 2023-11-27 | 2023-12-02 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/4 | Complete
2023-11-29 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401 | 50/4 | Complete
2023-11-29 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-29 | 2023-11-24 | 2023-11-29 | Sobha Devi | 37.504 | 6.2507 | TB401 | 56/3 | Complete
2023-11-29 | 2023-11-29 | 2023-12-02 | Sobha Devi | 38.847 | 9.7118 | TB401 | 56/4 | Complete
2023-11-29 | 2023-11-24 | 2023-11-30 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/1 | Complete
2023-11-29 | 2023-11-24 | 2023-11-29 | Suraj Const | 38.847 | 6.4745 | TB401 | 53/3 | Complete
2023-11-29 | 2023-11-29 | 2023-12-03 | Suraj Const | 38.847 | 7.7694 | TB401 | 53/4 | Complete
2023-11-30 | 2023-11-27 | 2023-12-02 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/4 | Complete
2023-11-30 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401 | 50/4 | Complete
2023-11-30 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-11-30 | 2023-11-29 | 2023-12-02 | Sobha Devi | 38.847 | 9.7118 | TB401 | 56/4 | Complete
2023-11-30 | 2023-11-24 | 2023-11-30 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/1 | Complete
2023-11-30 | 2023-11-30 | 2023-12-06 | Sunny Const | 38.847 | 5.5496 | TB401 | 58/15 | Complete
2023-11-30 | 2023-11-29 | 2023-12-03 | Suraj Const | 38.847 | 7.7694 | TB401 | 53/4 | Complete
2023-12-01 | 2023-11-27 | 2023-12-02 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/4 | Complete
2023-12-01 | 2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401 | 50/4 | Complete
2023-12-01 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-01 | 2023-11-29 | 2023-12-02 | Sobha Devi | 38.847 | 9.7118 | TB401 | 56/4 | Complete
2023-12-01 | 2023-11-30 | 2023-12-06 | Sunny Const | 38.847 | 5.5496 | TB401 | 58/15 | Complete
2023-12-01 | 2023-11-29 | 2023-12-03 | Suraj Const | 38.847 | 7.7694 | TB401 | 53/4 | Complete
2023-12-02 | 2023-11-27 | 2023-12-02 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/4 | Complete
2023-12-02 | 2023-12-02 | 2023-12-07 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/6 | Complete
2023-12-02 | 2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 48/1 | Complete
2023-12-02 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-02 | 2023-11-29 | 2023-12-02 | Sobha Devi | 38.847 | 9.7118 | TB401 | 56/4 | Complete
2023-12-02 | 2023-12-02 | 2023-12-06 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/2 | Complete
2023-12-02 | 2023-11-30 | 2023-12-06 | Sunny Const | 38.847 | 5.5496 | TB401 | 58/15 | Complete
2023-12-02 | 2023-11-29 | 2023-12-03 | Suraj Const | 38.847 | 7.7694 | TB401 | 53/4 | Complete
2023-12-03 | 2023-12-02 | 2023-12-07 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/6 | Complete
2023-12-03 | 2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 48/1 | Complete
2023-12-03 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-03 | 2023-12-02 | 2023-12-06 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/2 | Complete
2023-12-03 | 2023-11-30 | 2023-12-06 | Sunny Const | 38.847 | 5.5496 | TB401 | 58/15 | Complete
2023-12-03 | 2023-11-29 | 2023-12-03 | Suraj Const | 38.847 | 7.7694 | TB401 | 53/4 | Complete
2023-12-03 | 2023-12-03 | 2023-12-09 | Suraj Const | 38.847 | 5.5496 | TB401 | 55/1 | Complete
2023-12-04 | 2023-12-02 | 2023-12-07 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/6 | Complete
2023-12-04 | 2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 48/1 | Complete
2023-12-04 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-04 | 2023-12-02 | 2023-12-06 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/2 | Complete
2023-12-04 | 2023-11-30 | 2023-12-06 | Sunny Const | 38.847 | 5.5496 | TB401 | 58/15 | Complete
2023-12-04 | 2023-12-03 | 2023-12-09 | Suraj Const | 38.847 | 5.5496 | TB401 | 55/1 | Complete
2023-12-05 | 2023-12-02 | 2023-12-07 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/6 | Complete
2023-12-05 | 2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 48/1 | Complete
2023-12-05 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-05 | 2023-12-02 | 2023-12-06 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/2 | Complete
2023-12-05 | 2023-11-30 | 2023-12-06 | Sunny Const | 38.847 | 5.5496 | TB401 | 58/15 | Complete
2023-12-05 | 2023-12-03 | 2023-12-09 | Suraj Const | 38.847 | 5.5496 | TB401 | 55/1 | Complete
2023-12-06 | 2023-12-02 | 2023-12-07 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/6 | Complete
2023-12-06 | 2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 48/1 | Complete
2023-12-06 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-06 | 2023-12-02 | 2023-12-06 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/2 | Complete
2023-12-06 | 2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401 | 57/6 | Complete
2023-12-06 | 2023-11-30 | 2023-12-06 | Sunny Const | 38.847 | 5.5496 | TB401 | 58/15 | Complete
2023-12-06 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401 | 61/2 | Complete
2023-12-06 | 2023-12-03 | 2023-12-09 | Suraj Const | 38.847 | 5.5496 | TB401 | 55/1 | Complete
2023-12-07 | 2023-12-02 | 2023-12-07 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/6 | Complete
2023-12-07 | 2023-12-07 | 2023-12-12 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/9 | Complete
2023-12-07 | 2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 48/1 | Complete
2023-12-07 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-07 | 2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401 | 57/6 | Complete
2023-12-07 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401 | 61/2 | Complete
2023-12-07 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-07 | 2023-12-03 | 2023-12-09 | Suraj Const | 38.847 | 5.5496 | TB401 | 55/1 | Complete
2023-12-08 | 2023-12-07 | 2023-12-12 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/9 | Complete
2023-12-08 | 2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 48/1 | Complete
2023-12-08 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-08 | 2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401 | 57/6 | Complete
2023-12-08 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401 | 61/2 | Complete
2023-12-08 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-08 | 2023-12-03 | 2023-12-09 | Suraj Const | 38.847 | 5.5496 | TB401 | 55/1 | Complete
2023-12-09 | 2023-12-07 | 2023-12-12 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/9 | Complete
2023-12-09 | 2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 48/1 | Complete
2023-12-09 | 2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401 | 48/2 | Complete
2023-12-09 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-09 | 2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401 | 57/6 | Complete
2023-12-09 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401 | 61/2 | Complete
2023-12-09 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-09 | 2023-12-03 | 2023-12-09 | Suraj Const | 38.847 | 5.5496 | TB401 | 55/1 | Complete
2023-12-09 | 2023-12-09 | 2023-12-15 | Suraj Const | 38.847 | 5.5496 | TB401 | 55/2 | Complete
2023-12-10 | 2023-12-07 | 2023-12-12 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/9 | Complete
2023-12-10 | 2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401 | 48/2 | Complete
2023-12-10 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-10 | 2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401 | 57/6 | Complete
2023-12-10 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401 | 61/2 | Complete
2023-12-10 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-10 | 2023-12-09 | 2023-12-15 | Suraj Const | 38.847 | 5.5496 | TB401 | 55/2 | Complete
2023-12-11 | 2023-12-07 | 2023-12-12 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/9 | Complete
2023-12-11 | 2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401 | 48/2 | Complete
2023-12-11 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-11 | 2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401 | 57/6 | Complete
2023-12-11 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401 | 61/2 | Complete
2023-12-11 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-11 | 2023-12-09 | 2023-12-15 | Suraj Const | 38.847 | 5.5496 | TB401 | 55/2 | Complete
2023-12-12 | 2023-12-07 | 2023-12-12 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/9 | Complete
2023-12-12 | 2023-12-12 | 2023-12-17 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/10 | Complete
2023-12-12 | 2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401 | 48/2 | Complete
2023-12-12 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-12 | 2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401 | 57/6 | Complete
2023-12-12 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401 | 61/2 | Complete
2023-12-12 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-12 | 2023-12-09 | 2023-12-15 | Suraj Const | 38.847 | 5.5496 | TB401 | 55/2 | Complete
2023-12-13 | 2023-12-12 | 2023-12-17 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/10 | Complete
2023-12-13 | 2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401 | 48/2 | Complete
2023-12-13 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-13 | 2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401 | 57/6 | Complete
2023-12-13 | 2023-12-13 | 2023-12-19 | Sobha Devi | 57.597 | 8.2281 | TB401 | 57/0 | Complete
2023-12-13 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401 | 61/2 | Complete
2023-12-13 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-13 | 2023-12-09 | 2023-12-15 | Suraj Const | 38.847 | 5.5496 | TB401 | 55/2 | Complete
2023-12-14 | 2023-12-12 | 2023-12-17 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/10 | Complete
2023-12-14 | 2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401 | 48/2 | Complete
2023-12-14 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-14 | 2023-12-13 | 2023-12-19 | Sobha Devi | 57.597 | 8.2281 | TB401 | 57/0 | Complete
2023-12-14 | 2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401 | 61/2 | Complete
2023-12-14 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-14 | 2023-12-14 | 2023-12-20 | Sunny Const | 37.504 | 5.3577 | TB401 | 61/1 | Complete
2023-12-14 | 2023-12-09 | 2023-12-15 | Suraj Const | 38.847 | 5.5496 | TB401 | 55/2 | Complete
2023-12-15 | 2023-12-12 | 2023-12-17 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/10 | Complete
2023-12-15 | 2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401 | 48/2 | Complete
2023-12-15 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-15 | 2023-12-13 | 2023-12-19 | Sobha Devi | 57.597 | 8.2281 | TB401 | 57/0 | Complete
2023-12-15 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-15 | 2023-12-14 | 2023-12-20 | Sunny Const | 37.504 | 5.3577 | TB401 | 61/1 | Complete
2023-12-15 | 2023-12-09 | 2023-12-15 | Suraj Const | 38.847 | 5.5496 | TB401 | 55/2 | Complete
2023-12-16 | 2023-12-12 | 2023-12-17 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/10 | Complete
2023-12-16 | 2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401 | 48/2 | Complete
2023-12-16 | 2023-12-16 | 2023-12-22 | Ganesh Kr Sinha | 37.504 | 5.3577 | TB401 | 50/3 | Complete
2023-12-16 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-16 | 2023-12-13 | 2023-12-19 | Sobha Devi | 57.597 | 8.2281 | TB401 | 57/0 | Complete
2023-12-16 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-16 | 2023-12-14 | 2023-12-20 | Sunny Const | 37.504 | 5.3577 | TB401 | 61/1 | Complete
2023-12-16 | 2023-12-16 | 2023-12-19 | Suraj Const | 37.504 | 9.376 | TB401 | 55/3 | Complete
2023-12-17 | 2023-12-12 | 2023-12-17 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/10 | Complete
2023-12-17 | 2023-12-17 | 2023-12-22 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/11 | Complete
2023-12-17 | 2023-12-16 | 2023-12-22 | Ganesh Kr Sinha | 37.504 | 5.3577 | TB401 | 50/3 | Complete
2023-12-17 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-17 | 2023-12-13 | 2023-12-19 | Sobha Devi | 57.597 | 8.2281 | TB401 | 57/0 | Complete
2023-12-17 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-17 | 2023-12-14 | 2023-12-20 | Sunny Const | 37.504 | 5.3577 | TB401 | 61/1 | Complete
2023-12-17 | 2023-12-16 | 2023-12-19 | Suraj Const | 37.504 | 9.376 | TB401 | 55/3 | Complete
2023-12-18 | 2023-12-17 | 2023-12-22 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/11 | Complete
2023-12-18 | 2023-12-16 | 2023-12-22 | Ganesh Kr Sinha | 37.504 | 5.3577 | TB401 | 50/3 | Complete
2023-12-18 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-18 | 2023-12-13 | 2023-12-19 | Sobha Devi | 57.597 | 8.2281 | TB401 | 57/0 | Complete
2023-12-18 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-18 | 2023-12-14 | 2023-12-20 | Sunny Const | 37.504 | 5.3577 | TB401 | 61/1 | Complete
2023-12-18 | 2023-12-16 | 2023-12-19 | Suraj Const | 37.504 | 9.376 | TB401 | 55/3 | Complete
2023-12-19 | 2023-12-17 | 2023-12-22 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/11 | Complete
2023-12-19 | 2023-12-16 | 2023-12-22 | Ganesh Kr Sinha | 37.504 | 5.3577 | TB401 | 50/3 | Complete
2023-12-19 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-19 | 2023-12-13 | 2023-12-19 | Sobha Devi | 57.597 | 8.2281 | TB401 | 57/0 | Complete
2023-12-19 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-19 | 2023-12-14 | 2023-12-20 | Sunny Const | 37.504 | 5.3577 | TB401 | 61/1 | Complete
2023-12-19 | 2023-12-16 | 2023-12-19 | Suraj Const | 37.504 | 9.376 | TB401 | 55/3 | Complete
2023-12-20 | 2023-12-17 | 2023-12-22 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/11 | Complete
2023-12-20 | 2023-12-16 | 2023-12-22 | Ganesh Kr Sinha | 37.504 | 5.3577 | TB401 | 50/3 | Complete
2023-12-20 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-20 | 2023-12-20 | 2023-12-24 | Sobha Devi | 37.504 | 7.5008 | TB401 | 56/5 | Complete
2023-12-20 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-20 | 2023-12-14 | 2023-12-20 | Sunny Const | 37.504 | 5.3577 | TB401 | 61/1 | Complete
2023-12-20 | 2023-12-20 | 2023-12-24 | Suraj Const | 37.504 | 7.5008 | TB401 | 52/4 | Complete
2023-12-21 | 2023-12-17 | 2023-12-22 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/11 | Complete
2023-12-21 | 2023-12-16 | 2023-12-22 | Ganesh Kr Sinha | 37.504 | 5.3577 | TB401 | 50/3 | Complete
2023-12-21 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-21 | 2023-12-20 | 2023-12-24 | Sobha Devi | 37.504 | 7.5008 | TB401 | 56/5 | Complete
2023-12-21 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-21 | 2023-12-20 | 2023-12-24 | Suraj Const | 37.504 | 7.5008 | TB401 | 52/4 | Complete
2023-12-22 | 2023-12-17 | 2023-12-22 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/11 | Complete
2023-12-22 | 2023-12-22 | 2023-12-28 | Chinta Devi | 38.847 | 5.5496 | TB401 | 55/8 | Complete
2023-12-22 | 2023-12-16 | 2023-12-22 | Ganesh Kr Sinha | 37.504 | 5.3577 | TB401 | 50/3 | Complete
2023-12-22 | 2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 47/3 | Complete
2023-12-22 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-22 | 2023-12-20 | 2023-12-24 | Sobha Devi | 37.504 | 7.5008 | TB401 | 56/5 | Complete
2023-12-22 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-22 | 2023-12-20 | 2023-12-24 | Suraj Const | 37.504 | 7.5008 | TB401 | 52/4 | Complete
2023-12-23 | 2023-12-22 | 2023-12-28 | Chinta Devi | 38.847 | 5.5496 | TB401 | 55/8 | Complete
2023-12-23 | 2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 47/3 | Complete
2023-12-23 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-23 | 2023-12-20 | 2023-12-24 | Sobha Devi | 37.504 | 7.5008 | TB401 | 56/5 | Complete
2023-12-23 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-23 | 2023-12-20 | 2023-12-24 | Suraj Const | 37.504 | 7.5008 | TB401 | 52/4 | Complete
2023-12-24 | 2023-12-22 | 2023-12-28 | Chinta Devi | 38.847 | 5.5496 | TB401 | 55/8 | Complete
2023-12-24 | 2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 47/3 | Complete
2023-12-24 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-24 | 2023-12-20 | 2023-12-24 | Sobha Devi | 37.504 | 7.5008 | TB401 | 56/5 | Complete
2023-12-24 | 2023-12-24 | 2023-12-28 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/6 | Complete
2023-12-24 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-24 | 2023-12-20 | 2023-12-24 | Suraj Const | 37.504 | 7.5008 | TB401 | 52/4 | Complete
2023-12-24 | 2023-12-24 | 2023-12-29 | Suraj Const | 38.847 | 6.4745 | TB401 | 51/9 | Complete
2023-12-25 | 2023-12-22 | 2023-12-28 | Chinta Devi | 38.847 | 5.5496 | TB401 | 55/8 | Complete
2023-12-25 | 2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 47/3 | Complete
2023-12-25 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-25 | 2023-12-24 | 2023-12-28 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/6 | Complete
2023-12-25 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-25 | 2023-12-24 | 2023-12-29 | Suraj Const | 38.847 | 6.4745 | TB401 | 51/9 | Complete
2023-12-26 | 2023-12-22 | 2023-12-28 | Chinta Devi | 38.847 | 5.5496 | TB401 | 55/8 | Complete
2023-12-26 | 2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 47/3 | Complete
2023-12-26 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-26 | 2023-12-24 | 2023-12-28 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/6 | Complete
2023-12-26 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-26 | 2023-12-24 | 2023-12-29 | Suraj Const | 38.847 | 6.4745 | TB401 | 51/9 | Complete
2023-12-27 | 2023-12-22 | 2023-12-28 | Chinta Devi | 38.847 | 5.5496 | TB401 | 55/8 | Complete
2023-12-27 | 2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 47/3 | Complete
2023-12-27 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-27 | 2023-12-24 | 2023-12-28 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/6 | Complete
2023-12-27 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-27 | 2023-12-24 | 2023-12-29 | Suraj Const | 38.847 | 6.4745 | TB401 | 51/9 | Complete
2023-12-28 | 2023-12-22 | 2023-12-28 | Chinta Devi | 38.847 | 5.5496 | TB401 | 55/8 | Complete
2023-12-28 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401 | 44/2 | Complete
2023-12-28 | 2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 47/3 | Complete
2023-12-28 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-28 | 2023-12-24 | 2023-12-28 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/6 | Complete
2023-12-28 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401 | 56/0 | Complete
2023-12-28 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-28 | 2023-12-24 | 2023-12-29 | Suraj Const | 38.847 | 6.4745 | TB401 | 51/9 | Complete
2023-12-29 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401 | 44/2 | Complete
2023-12-29 | 2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 47/3 | Complete
2023-12-29 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 47/2 | Complete
2023-12-29 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-29 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401 | 56/0 | Complete
2023-12-29 | 2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-29 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401 | 58/7 | Complete
2023-12-29 | 2023-12-24 | 2023-12-29 | Suraj Const | 38.847 | 6.4745 | TB401 | 51/9 | Complete
2023-12-29 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401 | 51/8 | Complete
2023-12-30 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401 | 44/2 | Complete
2023-12-30 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 47/2 | Complete
2023-12-30 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-30 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401 | 56/0 | Complete
2023-12-30 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401 | 58/7 | Complete
2023-12-30 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401 | 51/8 | Complete
2023-12-31 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401 | 44/2 | Complete
2023-12-31 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 47/2 | Complete
2023-12-31 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2023-12-31 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401 | 56/0 | Complete
2023-12-31 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401 | 58/7 | Complete
2023-12-31 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401 | 51/8 | Complete
2024-01-01 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401 | 44/2 | Complete
2024-01-01 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 47/2 | Complete
2024-01-01 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2024-01-01 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401 | 56/0 | Complete
2024-01-01 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401 | 58/7 | Complete
2024-01-01 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401 | 51/8 | Complete
2024-01-02 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401 | 44/2 | Complete
2024-01-02 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 47/2 | Complete
2024-01-02 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2024-01-02 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401 | 56/0 | Complete
2024-01-02 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401 | 58/7 | Complete
2024-01-02 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401 | 51/8 | Complete
2024-01-03 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401 | 44/2 | Complete
2024-01-03 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 47/2 | Complete
2024-01-03 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2024-01-03 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401 | 56/0 | Complete
2024-01-03 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401 | 58/7 | Complete
2024-01-03 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401 | 51/8 | Complete
2024-01-04 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401 | 44/2 | Complete
2024-01-04 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 47/2 | Complete
2024-01-04 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2024-01-04 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401 | 56/0 | Complete
2024-01-04 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401 | 58/7 | Complete
2024-01-04 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401 | 51/8 | Complete
2024-01-05 | 2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401 | 44/2 | Complete
2024-01-05 | 2024-01-05 | 2024-01-09 | Chinta Devi | 37.504 | 7.5008 | TB401 | 44/4 | Complete
2024-01-05 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 47/2 | Complete
2024-01-05 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2024-01-05 | 2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401 | 56/0 | Complete
2024-01-05 | 2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401 | 41/11 | Complete
2024-01-05 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401 | 58/7 | Complete
2024-01-05 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401 | 51/8 | Complete
2024-01-06 | 2024-01-05 | 2024-01-09 | Chinta Devi | 37.504 | 7.5008 | TB401 | 44/4 | Complete
2024-01-06 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 47/2 | Complete
2024-01-06 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2024-01-06 | 2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401 | 41/11 | Complete
2024-01-06 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401 | 58/7 | Complete
2024-01-06 | 2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401 | 51/8 | Complete
2024-01-06 | 2024-01-06 | 2024-01-11 | Suraj Const | 38.847 | 6.4745 | TB401 | 53/2 | Complete
2024-01-07 | 2024-01-05 | 2024-01-09 | Chinta Devi | 37.504 | 7.5008 | TB401 | 44/4 | Complete
2024-01-07 | 2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 47/2 | Complete
2024-01-07 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401 | 48/0 | Complete
2024-01-07 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2024-01-07 | 2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401 | 41/11 | Complete
2024-01-07 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401 | 58/7 | Complete
2024-01-07 | 2024-01-06 | 2024-01-11 | Suraj Const | 38.847 | 6.4745 | TB401 | 53/2 | Complete
2024-01-08 | 2024-01-05 | 2024-01-09 | Chinta Devi | 37.504 | 7.5008 | TB401 | 44/4 | Complete
2024-01-08 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401 | 48/0 | Complete
2024-01-08 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2024-01-08 | 2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401 | 41/11 | Complete
2024-01-08 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401 | 58/7 | Complete
2024-01-08 | 2024-01-06 | 2024-01-11 | Suraj Const | 38.847 | 6.4745 | TB401 | 53/2 | Complete
2024-01-09 | 2024-01-05 | 2024-01-09 | Chinta Devi | 37.504 | 7.5008 | TB401 | 44/4 | Complete
2024-01-09 | 2024-01-09 | 2024-01-15 | Chinta Devi | 38.847 | 5.5496 | TB401 | 44/3 | Complete
2024-01-09 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401 | 48/0 | Complete
2024-01-09 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2024-01-09 | 2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401 | 41/11 | Complete
2024-01-09 | 2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401 | 58/7 | Complete
2024-01-09 | 2024-01-06 | 2024-01-11 | Suraj Const | 38.847 | 6.4745 | TB401 | 53/2 | Complete
2024-01-10 | 2024-01-09 | 2024-01-15 | Chinta Devi | 38.847 | 5.5496 | TB401 | 44/3 | Complete
2024-01-10 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401 | 48/0 | Complete
2024-01-10 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2024-01-10 | 2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401 | 41/11 | Complete
2024-01-10 | 2024-01-06 | 2024-01-11 | Suraj Const | 38.847 | 6.4745 | TB401 | 53/2 | Complete
2024-01-11 | 2024-01-09 | 2024-01-15 | Chinta Devi | 38.847 | 5.5496 | TB401 | 44/3 | Complete
2024-01-11 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401 | 48/0 | Complete
2024-01-11 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2024-01-11 | 2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401 | 41/11 | Complete
2024-01-11 | 2024-01-06 | 2024-01-11 | Suraj Const | 38.847 | 6.4745 | TB401 | 53/2 | Complete
2024-01-12 | 2024-01-09 | 2024-01-15 | Chinta Devi | 38.847 | 5.5496 | TB401 | 44/3 | Complete
2024-01-12 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401 | 48/0 | Complete
2024-01-12 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2024-01-12 | 2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401 | 41/11 | Complete
2024-01-12 | 2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401 | 46/3 | Complete
2024-01-12 | 2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401 | 51/6 | Complete
2024-01-13 | 2024-01-09 | 2024-01-15 | Chinta Devi | 38.847 | 5.5496 | TB401 | 44/3 | Complete
2024-01-13 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401 | 48/0 | Complete
2024-01-13 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2024-01-13 | 2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401 | 46/3 | Complete
2024-01-13 | 2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401 | 51/6 | Complete
2024-01-14 | 2024-01-09 | 2024-01-15 | Chinta Devi | 38.847 | 5.5496 | TB401 | 44/3 | Complete
2024-01-14 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401 | 48/0 | Complete
2024-01-14 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2024-01-14 | 2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401 | 46/3 | Complete
2024-01-14 | 2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401 | 51/6 | Complete
2024-01-15 | 2024-01-09 | 2024-01-15 | Chinta Devi | 38.847 | 5.5496 | TB401 | 44/3 | Complete
2024-01-15 | 2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401 | 43/4 | Complete
2024-01-15 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401 | 48/0 | Complete
2024-01-15 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2024-01-15 | 2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401 | 46/3 | Complete
2024-01-15 | 2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401 | 51/6 | Complete
2024-01-16 | 2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401 | 43/4 | Complete
2024-01-16 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401 | 48/0 | Complete
2024-01-16 | 2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2024-01-16 | 2024-01-16 | 2024-01-20 | Sobha Devi | 38.847 | 7.7694 | TB401 | 41/7 | Complete
2024-01-16 | 2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401 | 46/3 | Complete
2024-01-16 | 2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401 | 51/6 | Complete
2024-01-17 | 2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401 | 43/4 | Complete
2024-01-17 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401 | 48/0 | Complete
2024-01-17 | 2024-01-16 | 2024-01-20 | Sobha Devi | 38.847 | 7.7694 | TB401 | 41/7 | Complete
2024-01-17 | 2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401 | 46/3 | Complete
2024-01-17 | 2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401 | 51/6 | Complete
2024-01-18 | 2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401 | 43/4 | Complete
2024-01-18 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401 | 48/0 | Complete
2024-01-18 | 2024-01-16 | 2024-01-20 | Sobha Devi | 38.847 | 7.7694 | TB401 | 41/7 | Complete
2024-01-18 | 2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401 | 46/3 | Complete
2024-01-18 | 2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401 | 51/6 | Complete
2024-01-19 | 2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401 | 43/4 | Complete
2024-01-19 | 2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401 | 48/0 | Complete
2024-01-19 | 2024-01-16 | 2024-01-20 | Sobha Devi | 38.847 | 7.7694 | TB401 | 41/7 | Complete
2024-01-19 | 2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401 | 46/3 | Complete
2024-01-19 | 2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401 | 51/6 | Complete
2024-01-20 | 2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401 | 43/4 | Complete
2024-01-20 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401 | 51/0 | Complete
2024-01-20 | 2024-01-16 | 2024-01-20 | Sobha Devi | 38.847 | 7.7694 | TB401 | 41/7 | Complete
2024-01-20 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401 | 47/0 | Complete
2024-01-20 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401 | 52/0 | Complete
2024-01-21 | 2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401 | 43/4 | Complete
2024-01-21 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401 | 51/0 | Complete
2024-01-21 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401 | 47/0 | Complete
2024-01-21 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401 | 52/0 | Complete
2024-01-22 | 2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401 | 43/4 | Complete
2024-01-22 | 2024-01-22 | 2024-01-27 | Chinta Devi | 37.504 | 6.2507 | TB401 | 43/5 | Complete
2024-01-22 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401 | 51/0 | Complete
2024-01-22 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401 | 47/0 | Complete
2024-01-22 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401 | 52/0 | Complete
2024-01-23 | 2024-01-22 | 2024-01-27 | Chinta Devi | 37.504 | 6.2507 | TB401 | 43/5 | Complete
2024-01-23 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401 | 51/0 | Complete
2024-01-23 | 2024-01-23 | 2024-01-28 | Sobha Devi | 47.148 | 7.858 | TB401 | 43/1 | Complete
2024-01-23 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401 | 47/0 | Complete
2024-01-23 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401 | 52/0 | Complete
2024-01-24 | 2024-01-22 | 2024-01-27 | Chinta Devi | 37.504 | 6.2507 | TB401 | 43/5 | Complete
2024-01-24 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401 | 51/0 | Complete
2024-01-24 | 2024-01-23 | 2024-01-28 | Sobha Devi | 47.148 | 7.858 | TB401 | 43/1 | Complete
2024-01-24 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401 | 47/0 | Complete
2024-01-24 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401 | 52/0 | Complete
2024-01-25 | 2024-01-22 | 2024-01-27 | Chinta Devi | 37.504 | 6.2507 | TB401 | 43/5 | Complete
2024-01-25 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401 | 51/0 | Complete
2024-01-25 | 2024-01-23 | 2024-01-28 | Sobha Devi | 47.148 | 7.858 | TB401 | 43/1 | Complete
2024-01-25 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401 | 47/0 | Complete
2024-01-25 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401 | 52/0 | Complete
2024-01-26 | 2024-01-22 | 2024-01-27 | Chinta Devi | 37.504 | 6.2507 | TB401 | 43/5 | Complete
2024-01-26 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401 | 51/0 | Complete
2024-01-26 | 2024-01-23 | 2024-01-28 | Sobha Devi | 47.148 | 7.858 | TB401 | 43/1 | Complete
2024-01-26 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401 | 47/0 | Complete
2024-01-26 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401 | 52/0 | Complete
2024-01-27 | 2024-01-22 | 2024-01-27 | Chinta Devi | 37.504 | 6.2507 | TB401 | 43/5 | Complete
2024-01-27 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401 | 51/0 | Complete
2024-01-27 | 2024-01-23 | 2024-01-28 | Sobha Devi | 47.148 | 7.858 | TB401 | 43/1 | Complete
2024-01-27 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401 | 47/0 | Complete
2024-01-27 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401 | 52/0 | Complete
2024-01-28 | 2024-01-28 | 2024-02-01 | Chinta Devi | 37.504 | 7.5008 | TB401 | 44/1 | Complete
2024-01-28 | 2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401 | 51/0 | Complete
2024-01-28 | 2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 51/1 | Complete
2024-01-28 | 2024-01-23 | 2024-01-28 | Sobha Devi | 47.148 | 7.858 | TB401 | 43/1 | Complete
2024-01-28 | 2024-01-28 | 2024-01-31 | Sobha Devi | 37.504 | 9.376 | TB401 | 41/5 | Bottom complete
2024-01-28 | 2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401 | 47/0 | Complete
2024-01-28 | 2024-01-28 | 2024-02-02 | Sunny Const | 37.504 | 6.2507 | TB401 | 46/2 | Complete
2024-01-28 | 2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401 | 52/0 | Complete
2024-01-29 | 2024-01-28 | 2024-02-01 | Chinta Devi | 37.504 | 7.5008 | TB401 | 44/1 | Complete
2024-01-29 | 2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 51/1 | Complete
2024-01-29 | 2024-01-28 | 2024-01-31 | Sobha Devi | 37.504 | 9.376 | TB401 | 41/5 | Bottom complete
2024-01-29 | 2024-01-28 | 2024-02-02 | Sunny Const | 37.504 | 6.2507 | TB401 | 46/2 | Complete
2024-01-30 | 2024-01-28 | 2024-02-01 | Chinta Devi | 37.504 | 7.5008 | TB401 | 44/1 | Complete
2024-01-30 | 2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 51/1 | Complete
2024-01-30 | 2024-01-28 | 2024-01-31 | Sobha Devi | 37.504 | 9.376 | TB401 | 41/5 | Bottom complete
2024-01-30 | 2024-01-28 | 2024-02-02 | Sunny Const | 37.504 | 6.2507 | TB401 | 46/2 | Complete
2024-01-31 | 2024-01-28 | 2024-02-01 | Chinta Devi | 37.504 | 7.5008 | TB401 | 44/1 | Complete
2024-01-31 | 2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 51/1 | Complete
2024-01-31 | 2024-01-28 | 2024-01-31 | Sobha Devi | 37.504 | 9.376 | TB401 | 41/5 | Bottom complete
2024-01-31 | 2024-01-28 | 2024-02-02 | Sunny Const | 37.504 | 6.2507 | TB401 | 46/2 | Complete
2024-02-01 | 2024-01-28 | 2024-02-01 | Chinta Devi | 37.504 | 7.5008 | TB401 | 44/1 | Complete
2024-02-01 | 2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 51/1 | Complete
2024-02-01 | 2024-02-01 | 2024-02-05 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/4 | Complete
2024-02-01 | 2024-01-28 | 2024-02-02 | Sunny Const | 37.504 | 6.2507 | TB401 | 46/2 | Complete
2024-02-02 | 2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 51/1 | Complete
2024-02-02 | 2024-02-01 | 2024-02-05 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/4 | Complete
2024-02-02 | 2024-01-28 | 2024-02-02 | Sunny Const | 37.504 | 6.2507 | TB401 | 46/2 | Complete
2024-02-03 | 2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 51/1 | Complete
2024-02-03 | 2024-02-01 | 2024-02-05 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/4 | Complete
2024-02-03 | 2024-02-03 | 2024-02-09 | Tejal Construction | 38.847 | 5.5496 | TB401 | 29/8 | Complete
2024-02-04 | 2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 51/1 | Complete
2024-02-04 | 2024-02-01 | 2024-02-05 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/4 | Complete
2024-02-04 | 2024-02-04 | 2024-02-09 | Suraj Const | 37.504 | 6.2507 | TB401 | 53/1 | Complete
2024-02-04 | 2024-02-03 | 2024-02-09 | Tejal Construction | 38.847 | 5.5496 | TB401 | 29/8 | Complete
2024-02-05 | 2024-02-01 | 2024-02-05 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/4 | Complete
2024-02-05 | 2024-02-04 | 2024-02-09 | Suraj Const | 37.504 | 6.2507 | TB401 | 53/1 | Complete
2024-02-05 | 2024-02-03 | 2024-02-09 | Tejal Construction | 38.847 | 5.5496 | TB401 | 29/8 | Complete
2024-02-06 | 2024-02-04 | 2024-02-09 | Suraj Const | 37.504 | 6.2507 | TB401 | 53/1 | Complete
2024-02-06 | 2024-02-03 | 2024-02-09 | Tejal Construction | 38.847 | 5.5496 | TB401 | 29/8 | Complete
2024-02-07 | 2024-02-07 | 2024-02-09 | Sobha Devi | 37.504 | 12.5013 | TB401 | 41/6 | Complete
2024-02-07 | 2024-02-04 | 2024-02-09 | Suraj Const | 37.504 | 6.2507 | TB401 | 53/1 | Complete
2024-02-07 | 2024-02-03 | 2024-02-09 | Tejal Construction | 38.847 | 5.5496 | TB401 | 29/8 | Complete
2024-02-08 | 2024-02-07 | 2024-02-09 | Sobha Devi | 37.504 | 12.5013 | TB401 | 41/6 | Complete
2024-02-08 | 2024-02-04 | 2024-02-09 | Suraj Const | 37.504 | 6.2507 | TB401 | 53/1 | Complete
2024-02-08 | 2024-02-03 | 2024-02-09 | Tejal Construction | 38.847 | 5.5496 | TB401 | 29/8 | Complete
2024-02-09 | 2024-02-07 | 2024-02-09 | Sobha Devi | 37.504 | 12.5013 | TB401 | 41/6 | Complete
2024-02-09 | 2024-02-09 | 2024-02-13 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/8 | Complete
2024-02-09 | 2024-02-04 | 2024-02-09 | Suraj Const | 37.504 | 6.2507 | TB401 | 53/1 | Complete
2024-02-09 | 2024-02-03 | 2024-02-09 | Tejal Construction | 38.847 | 5.5496 | TB401 | 29/8 | Complete
2024-02-10 | 2024-02-09 | 2024-02-13 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/8 | Complete
2024-02-10 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401 | 29/7 | Complete
2024-02-11 | 2024-02-09 | 2024-02-13 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/8 | Complete
2024-02-11 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401 | 29/7 | Complete
2024-02-12 | 2024-02-09 | 2024-02-13 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/8 | Complete
2024-02-12 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401 | 29/7 | Complete
2024-02-13 | 2024-02-09 | 2024-02-13 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/8 | Complete
2024-02-13 | 2024-02-13 | 2024-02-17 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/9 | Complete
2024-02-13 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401 | 29/7 | Complete
2024-02-14 | 2024-02-13 | 2024-02-17 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/9 | Complete
2024-02-14 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401 | 29/7 | Complete
2024-02-15 | 2024-02-13 | 2024-02-17 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/9 | Complete
2024-02-15 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401 | 29/7 | Complete
2024-02-16 | 2024-02-13 | 2024-02-17 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/9 | Complete
2024-02-16 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401 | 29/7 | Complete
2024-02-17 | 2024-02-13 | 2024-02-17 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/9 | Complete
2024-02-17 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401 | 29/7 | Complete
2024-02-18 | 2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401 | 29/7 | Complete
2024-02-18 | 2024-02-18 | 2024-02-24 | Tejal Construction | 37.504 | 5.3577 | TB401 | 29/5 | Complete
2024-02-19 | 2024-02-18 | 2024-02-24 | Tejal Construction | 37.504 | 5.3577 | TB401 | 29/5 | Complete
2024-02-20 | 2024-02-18 | 2024-02-24 | Tejal Construction | 37.504 | 5.3577 | TB401 | 29/5 | Complete
2024-02-21 | 2024-02-18 | 2024-02-24 | Tejal Construction | 37.504 | 5.3577 | TB401 | 29/5 | Complete
2024-02-22 | 2024-02-18 | 2024-02-24 | Tejal Construction | 37.504 | 5.3577 | TB401 | 29/5 | Complete
2024-02-23 | 2024-02-18 | 2024-02-24 | Tejal Construction | 37.504 | 5.3577 | TB401 | 29/5 | Complete
2024-02-24 | 2024-02-18 | 2024-02-24 | Tejal Construction | 37.504 | 5.3577 | TB401 | 29/5 | Complete
2024-03-28 | 2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401 | 55/0 | Complete
2024-03-29 | 2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401 | 55/0 | Complete
2024-03-30 | 2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401 | 55/0 | Complete
2024-03-31 | 2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401 | 55/0 | Complete
2024-04-01 | 2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401 | 55/0 | Complete
2024-04-02 | 2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401 | 55/0 | Complete
2024-04-03 | 2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401 | 55/0 | Complete
2024-04-04 | 2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401 | 55/0 | Complete
2024-04-08 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401 | 53/0 | Complete
2024-04-08 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401 | 58/0 | Complete
2024-04-09 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401 | 53/0 | Complete
2024-04-09 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401 | 58/0 | Complete
2024-04-10 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401 | 53/0 | Complete
2024-04-10 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401 | 58/0 | Complete
2024-04-11 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401 | 53/0 | Complete
2024-04-11 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401 | 58/0 | Complete
2024-04-12 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401 | 53/0 | Complete
2024-04-12 | 2024-04-12 | 2024-04-16 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/1 | Complete
2024-04-12 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401 | 58/0 | Complete
2024-04-13 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401 | 53/0 | Complete
2024-04-13 | 2024-04-12 | 2024-04-16 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/1 | Complete
2024-04-13 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401 | 58/0 | Complete
2024-04-14 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401 | 53/0 | Complete
2024-04-14 | 2024-04-12 | 2024-04-16 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/1 | Complete
2024-04-14 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401 | 58/0 | Complete
2024-04-15 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401 | 53/0 | Complete
2024-04-15 | 2024-04-12 | 2024-04-16 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/1 | Complete
2024-04-15 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401 | 58/0 | Complete
2024-04-16 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401 | 53/0 | Complete
2024-04-16 | 2024-04-12 | 2024-04-16 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/1 | Complete
2024-04-16 | 2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401 | 58/0 | Complete
2024-04-17 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401 | 53/0 | Complete
2024-04-18 | 2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401 | 53/0 | Complete
2024-04-26 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 52/3 | Complete
2024-04-27 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 52/3 | Complete
2024-04-28 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 52/3 | Complete
2024-04-29 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 52/3 | Complete
2024-04-30 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 52/3 | Complete
2024-05-01 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 52/3 | Complete
2024-05-02 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 52/3 | Complete
2024-05-03 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 52/3 | Complete
2024-05-04 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 52/3 | Complete
2024-05-05 | 2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 52/3 | Complete
2024-05-05 | 2024-05-05 | 2024-05-10 | Sunny Const | 37.504 | 6.2507 | TB401 | 58/2 | Complete
2024-05-06 | 2024-05-05 | 2024-05-10 | Sunny Const | 37.504 | 6.2507 | TB401 | 58/2 | Complete
2024-05-07 | 2024-05-05 | 2024-05-10 | Sunny Const | 37.504 | 6.2507 | TB401 | 58/2 | Complete
2024-05-08 | 2024-05-05 | 2024-05-10 | Sunny Const | 37.504 | 6.2507 | TB401 | 58/2 | Complete
2024-05-09 | 2024-05-05 | 2024-05-10 | Sunny Const | 37.504 | 6.2507 | TB401 | 58/2 | Complete
2024-05-10 | 2024-05-05 | 2024-05-10 | Sunny Const | 37.504 | 6.2507 | TB401 | 58/2 | Complete
2024-05-10 | 2024-05-10 | 2024-05-16 | Sunny Const | 37.504 | 5.3577 | TB401 | 65/4 | Complete
2024-05-11 | 2024-05-10 | 2024-05-16 | Sunny Const | 37.504 | 5.3577 | TB401 | 65/4 | Complete
2024-05-12 | 2024-05-10 | 2024-05-16 | Sunny Const | 37.504 | 5.3577 | TB401 | 65/4 | Complete
2024-05-13 | 2024-05-10 | 2024-05-16 | Sunny Const | 37.504 | 5.3577 | TB401 | 65/4 | Complete
2024-05-14 | 2024-05-10 | 2024-05-16 | Sunny Const | 37.504 | 5.3577 | TB401 | 65/4 | Complete
2024-05-15 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-05-15 | 2024-05-10 | 2024-05-16 | Sunny Const | 37.504 | 5.3577 | TB401 | 65/4 | Complete
2024-05-16 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-05-16 | 2024-05-10 | 2024-05-16 | Sunny Const | 37.504 | 5.3577 | TB401 | 65/4 | Complete
2024-05-16 | 2024-05-16 | 2024-05-21 | Sunny Const | 37.504 | 6.2507 | TB401 | 65/3 | Complete
2024-05-16 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401 | 65/5 | Complete
2024-05-17 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-05-17 | 2024-05-16 | 2024-05-21 | Sunny Const | 37.504 | 6.2507 | TB401 | 65/3 | Complete
2024-05-17 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401 | 65/5 | Complete
2024-05-18 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-05-18 | 2024-05-16 | 2024-05-21 | Sunny Const | 37.504 | 6.2507 | TB401 | 65/3 | Complete
2024-05-18 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401 | 65/5 | Complete
2024-05-19 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-05-19 | 2024-05-16 | 2024-05-21 | Sunny Const | 37.504 | 6.2507 | TB401 | 65/3 | Complete
2024-05-19 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401 | 65/5 | Complete
2024-05-20 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-05-20 | 2024-05-16 | 2024-05-21 | Sunny Const | 37.504 | 6.2507 | TB401 | 65/3 | Complete
2024-05-20 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401 | 65/5 | Complete
2024-05-21 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-05-21 | 2024-05-16 | 2024-05-21 | Sunny Const | 37.504 | 6.2507 | TB401 | 65/3 | Complete
2024-05-21 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401 | 65/5 | Complete
2024-05-22 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-05-22 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401 | 65/5 | Complete
2024-05-23 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-05-23 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401 | 65/5 | Complete
2024-05-24 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-05-24 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401 | 65/5 | Complete
2024-05-25 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-05-25 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401 | 65/5 | Complete
2024-05-26 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-05-26 | 2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401 | 65/5 | Complete
2024-05-27 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-05-28 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-05-29 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-05-30 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-05-31 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-06-01 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-06-02 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-06-03 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-06-04 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-06-05 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-06-06 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-06-07 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-06-08 | 2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-06-10 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401 | 29/9
2024-06-11 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401 | 29/9
2024-06-12 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401 | 29/9
2024-06-13 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401 | 29/9
2024-06-14 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401 | 29/9
2024-06-15 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401 | 29/9
2024-06-16 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401 | 29/9
2024-06-17 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401 | 29/9
2024-06-18 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401 | 29/9
2024-06-19 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401 | 29/9
2024-06-20 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401 | 29/9
2024-06-21 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401 | 29/9
2024-06-22 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401 | 29/9
2024-06-23 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401 | 29/9
2024-06-24 | 2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401 | 29/9
2024-06-25 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401 | 29/10
2024-06-26 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401 | 29/10
2024-06-27 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401 | 29/10
2024-06-28 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401 | 29/10
2024-06-29 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401 | 29/10
2024-06-30 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401 | 29/10
2024-07-01 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401 | 29/10
2024-07-02 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401 | 29/10
2024-07-03 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401 | 29/10
2024-07-04 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401 | 29/10
2024-07-05 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401 | 29/10
2024-07-06 | 2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401 | 29/10
2024-07-07 | 2024-07-07 | 2024-07-12 | Departmental Gang | 37.504 | 6.2507 | TB401 | 31/3
2024-07-08 | 2024-07-07 | 2024-07-12 | Departmental Gang | 37.504 | 6.2507 | TB401 | 31/3
2024-07-09 | 2024-07-07 | 2024-07-12 | Departmental Gang | 37.504 | 6.2507 | TB401 | 31/3
2024-07-10 | 2024-07-07 | 2024-07-12 | Departmental Gang | 37.504 | 6.2507 | TB401 | 31/3
2024-07-11 | 2024-07-07 | 2024-07-12 | Departmental Gang | 37.504 | 6.2507 | TB401 | 31/3
2024-07-12 | 2024-07-07 | 2024-07-12 | Departmental Gang | 37.504 | 6.2507 | TB401 | 31/3
2024-07-13 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401 | 31/2
2024-07-14 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401 | 31/2
2024-07-15 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401 | 31/2
2024-07-16 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401 | 31/2
2024-07-17 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401 | 31/2
2024-07-18 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401 | 31/2
2024-07-19 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401 | 31/2
2024-07-20 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401 | 31/2
2024-07-21 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401 | 31/2
2024-07-22 | 2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401 | 31/2
2024-07-22 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401 | 32/5
2024-07-23 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401 | 32/5
2024-07-24 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401 | 32/5
2024-07-25 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401 | 32/5
2024-07-26 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401 | 32/5
2024-07-27 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401 | 32/5
2024-07-28 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401 | 32/5
2024-07-29 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401 | 32/5
2024-07-30 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401 | 32/5
2024-07-31 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401 | 32/5
2024-08-01 | 2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401 | 32/5
2024-08-02 | 2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401 | 32/6
2024-08-03 | 2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401 | 32/6
2024-08-04 | 2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401 | 32/6
2024-08-05 | 2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401 | 32/6
2024-08-06 | 2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401 | 32/6
2024-08-07 | 2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401 | 32/6
2024-08-08 | 2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401 | 32/6
2024-08-09 | 2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401 | 32/6
2024-08-10 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401 | 32/2
2024-08-11 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401 | 32/2
2024-08-12 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401 | 32/2
2024-08-13 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401 | 32/2
2024-08-14 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401 | 32/2
2024-08-15 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401 | 32/2
2024-08-16 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401 | 32/2
2024-08-17 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401 | 32/2
2024-08-18 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401 | 32/2
2024-08-19 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401 | 32/2
2024-08-20 | 2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401 | 32/2
2024-08-25 | 2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401 | 72/3 | Complete
2024-08-26 | 2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401 | 72/3 | Complete
2024-08-27 | 2024-08-27 | 2024-08-30 | Sobha Devi | 37.504 | 9.376 | TB401 | 46/4 | Complete
2024-08-27 | 2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401 | 72/3 | Complete
2024-08-28 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401 | 71/5 | Complete
2024-08-28 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401 | 14/4 | Complete
2024-08-28 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401 | 15/3 | Complete
2024-08-28 | 2024-08-27 | 2024-08-30 | Sobha Devi | 37.504 | 9.376 | TB401 | 46/4 | Complete
2024-08-28 | 2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401 | 72/3 | Complete
2024-08-29 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401 | 71/5 | Complete
2024-08-29 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401 | 14/4 | Complete
2024-08-29 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401 | 15/3 | Complete
2024-08-29 | 2024-08-27 | 2024-08-30 | Sobha Devi | 37.504 | 9.376 | TB401 | 46/4 | Complete
2024-08-29 | 2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401 | 72/3 | Complete
2024-08-30 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401 | 71/5 | Complete
2024-08-30 | 2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401 | 16/2 | Complete
2024-08-30 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401 | 14/4 | Complete
2024-08-30 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401 | 15/3 | Complete
2024-08-30 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-08-30 | 2024-08-27 | 2024-08-30 | Sobha Devi | 37.504 | 9.376 | TB401 | 46/4 | Complete
2024-08-30 | 2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401 | 72/3 | Complete
2024-08-31 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401 | 71/5 | Complete
2024-08-31 | 2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401 | 16/2 | Complete
2024-08-31 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401 | 14/4 | Complete
2024-08-31 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401 | 15/3 | Complete
2024-08-31 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-08-31 | 2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401 | 72/3 | Complete
2024-09-01 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401 | 71/5 | Complete
2024-09-01 | 2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401 | 16/2 | Complete
2024-09-01 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401 | 14/4 | Complete
2024-09-01 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401 | 15/3 | Complete
2024-09-01 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-01 | 2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401 | 72/3 | Complete
2024-09-01 | 2024-09-01 | 2024-09-06 | Sunny Const | 37.504 | 6.2507 | TB401 | 72/4 | Complete
2024-09-01 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401 | 72/5 | Complete
2024-09-02 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401 | 71/5 | Complete
2024-09-02 | 2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401 | 16/2 | Complete
2024-09-02 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401 | 14/4 | Complete
2024-09-02 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401 | 15/3 | Complete
2024-09-02 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-02 | 2024-09-01 | 2024-09-06 | Sunny Const | 37.504 | 6.2507 | TB401 | 72/4 | Complete
2024-09-02 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401 | 72/5 | Complete
2024-09-03 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401 | 71/5 | Complete
2024-09-03 | 2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401 | 16/2 | Complete
2024-09-03 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401 | 14/4 | Complete
2024-09-03 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401 | 15/3 | Complete
2024-09-03 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-03 | 2024-09-01 | 2024-09-06 | Sunny Const | 37.504 | 6.2507 | TB401 | 72/4 | Complete
2024-09-03 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401 | 72/5 | Complete
2024-09-04 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401 | 71/5 | Complete
2024-09-04 | 2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401 | 16/2 | Complete
2024-09-04 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401 | 14/4 | Complete
2024-09-04 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401 | 15/3 | Complete
2024-09-04 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-04 | 2024-09-01 | 2024-09-06 | Sunny Const | 37.504 | 6.2507 | TB401 | 72/4 | Complete
2024-09-04 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401 | 72/5 | Complete
2024-09-05 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401 | 71/5 | Complete
2024-09-05 | 2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401 | 16/2 | Complete
2024-09-05 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401 | 14/4 | Complete
2024-09-05 | 2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401 | 15/3 | Complete
2024-09-05 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-05 | 2024-09-01 | 2024-09-06 | Sunny Const | 37.504 | 6.2507 | TB401 | 72/4 | Complete
2024-09-05 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401 | 72/5 | Complete
2024-09-06 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401 | 10/19 | Complete
2024-09-06 | 2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401 | 71/5 | Complete
2024-09-06 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401 | 72/0 | Complete
2024-09-06 | 2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401 | 16/2 | Complete
2024-09-06 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401 | 14/4 | Complete
2024-09-06 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-06 | 2024-09-01 | 2024-09-06 | Sunny Const | 37.504 | 6.2507 | TB401 | 72/4 | Complete
2024-09-06 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401 | 72/5 | Complete
2024-09-07 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401 | 10/19 | Complete
2024-09-07 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401 | 72/0 | Complete
2024-09-07 | 2024-09-07 | 2024-09-12 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 16/3 | Complete
2024-09-07 | 2024-09-07 | 2024-09-11 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/3 | Complete
2024-09-07 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401 | 14/4 | Complete
2024-09-07 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-07 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401 | 72/5 | Complete
2024-09-08 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401 | 10/19 | Complete
2024-09-08 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401 | 72/0 | Complete
2024-09-08 | 2024-09-07 | 2024-09-12 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 16/3 | Complete
2024-09-08 | 2024-09-07 | 2024-09-11 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/3 | Complete
2024-09-08 | 2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401 | 14/4 | Complete
2024-09-08 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-08 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401 | 72/5 | Complete
2024-09-09 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401 | 10/19 | Complete
2024-09-09 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401 | 72/0 | Complete
2024-09-09 | 2024-09-07 | 2024-09-12 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 16/3 | Complete
2024-09-09 | 2024-09-07 | 2024-09-11 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/3 | Complete
2024-09-09 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-09 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-09 | 2024-09-09 | 2024-09-12 | Sobha Devi | 37.504 | 9.376 | TB401 | 47/1 | Complete
2024-09-09 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401 | 72/5 | Complete
2024-09-10 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401 | 10/19 | Complete
2024-09-10 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401 | 72/0 | Complete
2024-09-10 | 2024-09-07 | 2024-09-12 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 16/3 | Complete
2024-09-10 | 2024-09-07 | 2024-09-11 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/3 | Complete
2024-09-10 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401 | 14/5 | Complete
2024-09-10 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-10 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-10 | 2024-09-09 | 2024-09-12 | Sobha Devi | 37.504 | 9.376 | TB401 | 47/1 | Complete
2024-09-10 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401 | 72/5 | Complete
2024-09-11 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401 | 10/19 | Complete
2024-09-11 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401 | 72/0 | Complete
2024-09-11 | 2024-09-07 | 2024-09-12 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 16/3 | Complete
2024-09-11 | 2024-09-07 | 2024-09-11 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/3 | Complete
2024-09-11 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401 | 14/5 | Complete
2024-09-11 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-11 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-11 | 2024-09-09 | 2024-09-12 | Sobha Devi | 37.504 | 9.376 | TB401 | 47/1 | Complete
2024-09-11 | 2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401 | 72/5 | Complete
2024-09-11 | 2024-09-11 | 2024-09-15 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/6 | Complete
2024-09-12 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401 | 10/19 | Complete
2024-09-12 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401 | 72/0 | Complete
2024-09-12 | 2024-09-07 | 2024-09-12 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 16/3 | Complete
2024-09-12 | 2024-09-12 | 2024-09-16 | Deglal Mahto | 38.847 | 7.7694 | TB401 | 16/4 | Complete
2024-09-12 | 2024-09-12 | 2024-09-16 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/4 | Complete
2024-09-12 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401 | 14/5 | Complete
2024-09-12 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-12 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-12 | 2024-09-09 | 2024-09-12 | Sobha Devi | 37.504 | 9.376 | TB401 | 47/1 | Complete
2024-09-12 | 2024-09-12 | 2024-09-16 | Sobha Devi | 37.504 | 7.5008 | TB401 | 50/2 | Complete
2024-09-12 | 2024-09-11 | 2024-09-15 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/6 | Complete
2024-09-13 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401 | 10/19 | Complete
2024-09-13 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401 | 72/0 | Complete
2024-09-13 | 2024-09-12 | 2024-09-16 | Deglal Mahto | 38.847 | 7.7694 | TB401 | 16/4 | Complete
2024-09-13 | 2024-09-12 | 2024-09-16 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/4 | Complete
2024-09-13 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401 | 14/5 | Complete
2024-09-13 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-13 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-13 | 2024-09-12 | 2024-09-16 | Sobha Devi | 37.504 | 7.5008 | TB401 | 50/2 | Complete
2024-09-13 | 2024-09-11 | 2024-09-15 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/6 | Complete
2024-09-14 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401 | 10/19 | Complete
2024-09-14 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401 | 72/0 | Complete
2024-09-14 | 2024-09-12 | 2024-09-16 | Deglal Mahto | 38.847 | 7.7694 | TB401 | 16/4 | Complete
2024-09-14 | 2024-09-12 | 2024-09-16 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/4 | Complete
2024-09-14 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401 | 14/5 | Complete
2024-09-14 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-14 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-14 | 2024-09-12 | 2024-09-16 | Sobha Devi | 37.504 | 7.5008 | TB401 | 50/2 | Complete
2024-09-14 | 2024-09-11 | 2024-09-15 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/6 | Complete
2024-09-15 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401 | 10/19 | Complete
2024-09-15 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401 | 72/0 | Complete
2024-09-15 | 2024-09-12 | 2024-09-16 | Deglal Mahto | 38.847 | 7.7694 | TB401 | 16/4 | Complete
2024-09-15 | 2024-09-12 | 2024-09-16 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/4 | Complete
2024-09-15 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401 | 14/5 | Complete
2024-09-15 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-15 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-15 | 2024-09-12 | 2024-09-16 | Sobha Devi | 37.504 | 7.5008 | TB401 | 50/2 | Complete
2024-09-15 | 2024-09-11 | 2024-09-15 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/6 | Complete
2024-09-15 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401 | 72/7 | Complete
2024-09-16 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401 | 10/19 | Complete
2024-09-16 | 2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401 | 72/0 | Complete
2024-09-16 | 2024-09-16 | 2024-09-22 | Chinta Devi | 37.504 | 5.3577 | TB401 | 71/4 | Complete
2024-09-16 | 2024-09-12 | 2024-09-16 | Deglal Mahto | 38.847 | 7.7694 | TB401 | 16/4 | Complete
2024-09-16 | 2024-09-12 | 2024-09-16 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/4 | Complete
2024-09-16 | 2024-09-16 | 2024-09-20 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/5 | Complete
2024-09-16 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401 | 14/5 | Complete
2024-09-16 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-16 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-16 | 2024-09-12 | 2024-09-16 | Sobha Devi | 37.504 | 7.5008 | TB401 | 50/2 | Complete
2024-09-16 | 2024-09-16 | 2024-09-20 | Sobha Devi | 37.504 | 7.5008 | TB401 | 50/1 | Complete
2024-09-16 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401 | 72/7 | Complete
2024-09-17 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401 | 10/19 | Complete
2024-09-17 | 2024-09-16 | 2024-09-22 | Chinta Devi | 37.504 | 5.3577 | TB401 | 71/4 | Complete
2024-09-17 | 2024-09-16 | 2024-09-20 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/5 | Complete
2024-09-17 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401 | 14/5 | Complete
2024-09-17 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-17 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-17 | 2024-09-16 | 2024-09-20 | Sobha Devi | 37.504 | 7.5008 | TB401 | 50/1 | Complete
2024-09-17 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401 | 72/7 | Complete
2024-09-18 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401 | 10/19 | Complete
2024-09-18 | 2024-09-16 | 2024-09-22 | Chinta Devi | 37.504 | 5.3577 | TB401 | 71/4 | Complete
2024-09-18 | 2024-09-16 | 2024-09-20 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/5 | Complete
2024-09-18 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401 | 14/5 | Complete
2024-09-18 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-18 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-18 | 2024-09-16 | 2024-09-20 | Sobha Devi | 37.504 | 7.5008 | TB401 | 50/1 | Complete
2024-09-18 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401 | 72/7 | Complete
2024-09-19 | 2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401 | 10/19 | Complete
2024-09-19 | 2024-09-16 | 2024-09-22 | Chinta Devi | 37.504 | 5.3577 | TB401 | 71/4 | Complete
2024-09-19 | 2024-09-16 | 2024-09-20 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/5 | Complete
2024-09-19 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401 | 14/5 | Complete
2024-09-19 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-19 | 2024-09-19 | 2024-09-21 | Nirmal Mahto | 47.148 | 15.716 | TB401 | 15/2 | Complete
2024-09-19 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-19 | 2024-09-16 | 2024-09-20 | Sobha Devi | 37.504 | 7.5008 | TB401 | 50/1 | Complete
2024-09-19 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401 | 72/7 | Complete
2024-09-19 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-09-20 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-09-20 | 2024-09-16 | 2024-09-22 | Chinta Devi | 37.504 | 5.3577 | TB401 | 71/4 | Complete
2024-09-20 | 2024-09-16 | 2024-09-20 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/5 | Complete
2024-09-20 | 2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401 | 14/5 | Complete
2024-09-20 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-20 | 2024-09-19 | 2024-09-21 | Nirmal Mahto | 47.148 | 15.716 | TB401 | 15/2 | Complete
2024-09-20 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-20 | 2024-09-16 | 2024-09-20 | Sobha Devi | 37.504 | 7.5008 | TB401 | 50/1 | Complete
2024-09-20 | 2024-09-20 | 2024-09-26 | Sobha Devi | 69.229 | 9.8899 | TB401 | 50/0 | Complete
2024-09-20 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401 | 72/7 | Complete
2024-09-20 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-09-21 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-09-21 | 2024-09-16 | 2024-09-22 | Chinta Devi | 37.504 | 5.3577 | TB401 | 71/4 | Complete
2024-09-21 | 2024-09-21 | 2024-09-25 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/6 | Complete
2024-09-21 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-21 | 2024-09-19 | 2024-09-21 | Nirmal Mahto | 47.148 | 15.716 | TB401 | 15/2 | Complete
2024-09-21 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-21 | 2024-09-20 | 2024-09-26 | Sobha Devi | 69.229 | 9.8899 | TB401 | 50/0 | Complete
2024-09-21 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401 | 72/7 | Complete
2024-09-21 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-09-22 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-09-22 | 2024-09-16 | 2024-09-22 | Chinta Devi | 37.504 | 5.3577 | TB401 | 71/4 | Complete
2024-09-22 | 2024-09-22 | 2024-09-26 | Chinta Devi | 37.504 | 7.5008 | TB401 | 71/2 | Complete
2024-09-22 | 2024-09-21 | 2024-09-25 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/6 | Complete
2024-09-22 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-22 | 2024-09-22 | 2024-09-27 | Nirmal Mahto | 38.847 | 6.4745 | TB401 | 15/4 | Complete
2024-09-22 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-22 | 2024-09-20 | 2024-09-26 | Sobha Devi | 69.229 | 9.8899 | TB401 | 50/0 | Complete
2024-09-22 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401 | 72/7 | Complete
2024-09-22 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-09-23 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-09-23 | 2024-09-22 | 2024-09-26 | Chinta Devi | 37.504 | 7.5008 | TB401 | 71/2 | Complete
2024-09-23 | 2024-09-21 | 2024-09-25 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/6 | Complete
2024-09-23 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-23 | 2024-09-22 | 2024-09-27 | Nirmal Mahto | 38.847 | 6.4745 | TB401 | 15/4 | Complete
2024-09-23 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-23 | 2024-09-20 | 2024-09-26 | Sobha Devi | 69.229 | 9.8899 | TB401 | 50/0 | Complete
2024-09-23 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401 | 72/7 | Complete
2024-09-23 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-09-24 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-09-24 | 2024-09-22 | 2024-09-26 | Chinta Devi | 37.504 | 7.5008 | TB401 | 71/2 | Complete
2024-09-24 | 2024-09-21 | 2024-09-25 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/6 | Complete
2024-09-24 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-24 | 2024-09-22 | 2024-09-27 | Nirmal Mahto | 38.847 | 6.4745 | TB401 | 15/4 | Complete
2024-09-24 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-24 | 2024-09-20 | 2024-09-26 | Sobha Devi | 69.229 | 9.8899 | TB401 | 50/0 | Complete
2024-09-24 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401 | 72/7 | Complete
2024-09-24 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-09-25 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-09-25 | 2024-09-22 | 2024-09-26 | Chinta Devi | 37.504 | 7.5008 | TB401 | 71/2 | Complete
2024-09-25 | 2024-09-21 | 2024-09-25 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/6 | Complete
2024-09-25 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-25 | 2024-09-22 | 2024-09-27 | Nirmal Mahto | 38.847 | 6.4745 | TB401 | 15/4 | Complete
2024-09-25 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-25 | 2024-09-20 | 2024-09-26 | Sobha Devi | 69.229 | 9.8899 | TB401 | 50/0 | Complete
2024-09-25 | 2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401 | 72/7 | Complete
2024-09-25 | 2024-09-25 | 2024-09-29 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/2 | Complete
2024-09-25 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-09-26 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-09-26 | 2024-09-22 | 2024-09-26 | Chinta Devi | 37.504 | 7.5008 | TB401 | 71/2 | Complete
2024-09-26 | 2024-09-26 | 2024-10-01 | Chinta Devi | 37.504 | 6.2507 | TB401 | 71/1 | Complete
2024-09-26 | 2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-26 | 2024-09-22 | 2024-09-27 | Nirmal Mahto | 38.847 | 6.4745 | TB401 | 15/4 | Complete
2024-09-26 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-26 | 2024-09-20 | 2024-09-26 | Sobha Devi | 69.229 | 9.8899 | TB401 | 50/0 | Complete
2024-09-26 | 2024-09-25 | 2024-09-29 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/2 | Complete
2024-09-26 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-09-26 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401 | 10/21 | Complete
2024-09-27 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-09-27 | 2024-09-26 | 2024-10-01 | Chinta Devi | 37.504 | 6.2507 | TB401 | 71/1 | Complete
2024-09-27 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401 | 43/3 | Complete
2024-09-27 | 2024-09-22 | 2024-09-27 | Nirmal Mahto | 38.847 | 6.4745 | TB401 | 15/4 | Complete
2024-09-27 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-27 | 2024-09-25 | 2024-09-29 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/2 | Complete
2024-09-27 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-09-27 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401 | 10/21 | Complete
2024-09-28 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-09-28 | 2024-09-26 | 2024-10-01 | Chinta Devi | 37.504 | 6.2507 | TB401 | 71/1 | Complete
2024-09-28 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-09-28 | 2024-09-28 | 2024-10-03 | Deglal Mahto | 38.847 | 6.4745 | TB401 | 16/5 | Complete
2024-09-28 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401 | 43/3 | Complete
2024-09-28 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-28 | 2024-09-25 | 2024-09-29 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/2 | Complete
2024-09-28 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-09-28 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401 | 10/21 | Complete
2024-09-29 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-09-29 | 2024-09-26 | 2024-10-01 | Chinta Devi | 37.504 | 6.2507 | TB401 | 71/1 | Complete
2024-09-29 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-09-29 | 2024-09-28 | 2024-10-03 | Deglal Mahto | 38.847 | 6.4745 | TB401 | 16/5 | Complete
2024-09-29 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401 | 43/3 | Complete
2024-09-29 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-29 | 2024-09-25 | 2024-09-29 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/2 | Complete
2024-09-29 | 2024-09-29 | 2024-10-03 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/1 | Complete
2024-09-29 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-09-29 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401 | 10/21 | Complete
2024-09-30 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-09-30 | 2024-09-26 | 2024-10-01 | Chinta Devi | 37.504 | 6.2507 | TB401 | 71/1 | Complete
2024-09-30 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-09-30 | 2024-09-28 | 2024-10-03 | Deglal Mahto | 38.847 | 6.4745 | TB401 | 16/5 | Complete
2024-09-30 | 2024-09-30 | 2024-10-04 | Jagdish Mahto | 45.413 | 9.0826 | TB401 | 10/7 | Complete
2024-09-30 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401 | 43/3 | Complete
2024-09-30 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-09-30 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401 | 66/2 | Complete
2024-09-30 | 2024-09-29 | 2024-10-03 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/1 | Complete
2024-09-30 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-09-30 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401 | 10/21 | Complete
2024-10-01 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-10-01 | 2024-09-26 | 2024-10-01 | Chinta Devi | 37.504 | 6.2507 | TB401 | 71/1 | Complete
2024-10-01 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-01 | 2024-09-28 | 2024-10-03 | Deglal Mahto | 38.847 | 6.4745 | TB401 | 16/5 | Complete
2024-10-01 | 2024-09-30 | 2024-10-04 | Jagdish Mahto | 45.413 | 9.0826 | TB401 | 10/7 | Complete
2024-10-01 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401 | 43/3 | Complete
2024-10-01 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-10-01 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401 | 66/2 | Complete
2024-10-01 | 2024-09-29 | 2024-10-03 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/1 | Complete
2024-10-01 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-10-01 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401 | 10/21 | Complete
2024-10-02 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-10-02 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-02 | 2024-10-02 | 2024-10-05 | Chinta Devi | 38.847 | 9.7118 | TB401 | 68/1 | Complete
2024-10-02 | 2024-09-28 | 2024-10-03 | Deglal Mahto | 38.847 | 6.4745 | TB401 | 16/5 | Complete
2024-10-02 | 2024-09-30 | 2024-10-04 | Jagdish Mahto | 45.413 | 9.0826 | TB401 | 10/7 | Complete
2024-10-02 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401 | 43/3 | Complete
2024-10-02 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-10-02 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401 | 66/2 | Complete
2024-10-02 | 2024-09-29 | 2024-10-03 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/1 | Complete
2024-10-02 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-10-02 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401 | 10/21 | Complete
2024-10-03 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-10-03 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-03 | 2024-10-02 | 2024-10-05 | Chinta Devi | 38.847 | 9.7118 | TB401 | 68/1 | Complete
2024-10-03 | 2024-09-28 | 2024-10-03 | Deglal Mahto | 38.847 | 6.4745 | TB401 | 16/5 | Complete
2024-10-03 | 2024-09-30 | 2024-10-04 | Jagdish Mahto | 45.413 | 9.0826 | TB401 | 10/7 | Complete
2024-10-03 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401 | 43/3 | Complete
2024-10-03 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-10-03 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401 | 66/2 | Complete
2024-10-03 | 2024-09-29 | 2024-10-03 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/1 | Complete
2024-10-03 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401 | 73/0 | Complete
2024-10-03 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-10-03 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401 | 10/21 | Complete
2024-10-04 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-10-04 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-04 | 2024-10-02 | 2024-10-05 | Chinta Devi | 38.847 | 9.7118 | TB401 | 68/1 | Complete
2024-10-04 | 2024-09-30 | 2024-10-04 | Jagdish Mahto | 45.413 | 9.0826 | TB401 | 10/7 | Complete
2024-10-04 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401 | 43/3 | Complete
2024-10-04 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-10-04 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401 | 66/2 | Complete
2024-10-04 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401 | 73/0 | Complete
2024-10-04 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-10-04 | 2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401 | 10/21 | Complete
2024-10-05 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-10-05 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-05 | 2024-10-02 | 2024-10-05 | Chinta Devi | 38.847 | 9.7118 | TB401 | 68/1 | Complete
2024-10-05 | 2024-10-05 | 2024-10-10 | Chinta Devi | 38.847 | 6.4745 | TB401 | 68/2 | Complete
2024-10-05 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401 | 15/0 | Complete
2024-10-05 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401 | 43/3 | Complete
2024-10-05 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-10-05 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401 | 66/2 | Complete
2024-10-05 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401 | 73/0 | Complete
2024-10-05 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-10-06 | 2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-10-06 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-06 | 2024-10-05 | 2024-10-10 | Chinta Devi | 38.847 | 6.4745 | TB401 | 68/2 | Complete
2024-10-06 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401 | 15/0 | Complete
2024-10-06 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401 | 43/3 | Complete
2024-10-06 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-10-06 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401 | 66/2 | Complete
2024-10-06 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401 | 73/0 | Complete
2024-10-06 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-10-07 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-07 | 2024-10-05 | 2024-10-10 | Chinta Devi | 38.847 | 6.4745 | TB401 | 68/2 | Complete
2024-10-07 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401 | 15/0 | Complete
2024-10-07 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401 | 43/3 | Complete
2024-10-07 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-10-07 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401 | 66/2 | Complete
2024-10-07 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401 | 73/0 | Complete
2024-10-07 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-10-08 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-08 | 2024-10-05 | 2024-10-10 | Chinta Devi | 38.847 | 6.4745 | TB401 | 68/2 | Complete
2024-10-08 | 2024-10-08 | 2024-10-11 | Jagdish Mahto | 38.847 | 9.7118 | TB401 | 10/9 | Complete
2024-10-08 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401 | 15/0 | Complete
2024-10-08 | 2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401 | 43/3 | Complete
2024-10-08 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401 | 43/2 | Complete
2024-10-08 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-10-08 | 2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401 | 11/7 | Complete
2024-10-08 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401 | 11/8 | Complete
2024-10-08 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401 | 66/2 | Complete
2024-10-08 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401 | 73/0 | Complete
2024-10-08 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-10-09 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-09 | 2024-10-05 | 2024-10-10 | Chinta Devi | 38.847 | 6.4745 | TB401 | 68/2 | Complete
2024-10-09 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401 | 17/0 | Complete
2024-10-09 | 2024-10-08 | 2024-10-11 | Jagdish Mahto | 38.847 | 9.7118 | TB401 | 10/9 | Complete
2024-10-09 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401 | 15/0 | Complete
2024-10-09 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401 | 43/2 | Complete
2024-10-09 | 2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-10-09 | 2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401 | 11/7 | Complete
2024-10-09 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401 | 11/8 | Complete
2024-10-09 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401 | 66/2 | Complete
2024-10-09 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401 | 73/0 | Complete
2024-10-09 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-10-10 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-10 | 2024-10-05 | 2024-10-10 | Chinta Devi | 38.847 | 6.4745 | TB401 | 68/2 | Complete
2024-10-10 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401 | 67/1 | Complete
2024-10-10 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401 | 17/0 | Complete
2024-10-10 | 2024-10-08 | 2024-10-11 | Jagdish Mahto | 38.847 | 9.7118 | TB401 | 10/9 | Complete
2024-10-10 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401 | 15/0 | Complete
2024-10-10 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401 | 43/2 | Complete
2024-10-10 | 2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401 | 11/7 | Complete
2024-10-10 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401 | 11/8 | Complete
2024-10-10 | 2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401 | 66/2 | Complete
2024-10-10 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401 | 73/0 | Complete
2024-10-10 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-10-11 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401 | 10/18 | Complete
2024-10-11 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-11 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401 | 67/1 | Complete
2024-10-11 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401 | 17/0 | Complete
2024-10-11 | 2024-10-08 | 2024-10-11 | Jagdish Mahto | 38.847 | 9.7118 | TB401 | 10/9 | Complete
2024-10-11 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401 | 15/0 | Complete
2024-10-11 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401 | 43/2 | Complete
2024-10-11 | 2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401 | 11/7 | Complete
2024-10-11 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401 | 11/8 | Complete
2024-10-11 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401 | 73/0 | Complete
2024-10-11 | 2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-10-12 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401 | 10/18 | Complete
2024-10-12 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-12 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401 | 67/1 | Complete
2024-10-12 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401 | 17/0 | Complete
2024-10-12 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401 | 15/0 | Complete
2024-10-12 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401 | 43/2 | Complete
2024-10-12 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-12 | 2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401 | 11/7 | Complete
2024-10-12 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401 | 11/8 | Complete
2024-10-12 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401 | 73/0 | Complete
2024-10-13 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401 | 10/18 | Complete
2024-10-13 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-13 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401 | 67/1 | Complete
2024-10-13 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401 | 17/0 | Complete
2024-10-13 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401 | 15/0 | Complete
2024-10-13 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401 | 43/2 | Complete
2024-10-13 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-13 | 2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401 | 11/7 | Complete
2024-10-13 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401 | 11/8 | Complete
2024-10-13 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401 | 11/9 | Complete
2024-10-13 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401 | 73/0 | Complete
2024-10-13 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401 | 32/0 | Complete
2024-10-14 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401 | 10/18 | Complete
2024-10-14 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-14 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401 | 67/1 | Complete
2024-10-14 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401 | 17/0 | Complete
2024-10-14 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401 | 15/0 | Complete
2024-10-14 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401 | 43/2 | Complete
2024-10-14 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-14 | 2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401 | 11/7 | Complete
2024-10-14 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401 | 11/8 | Complete
2024-10-14 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401 | 11/9 | Complete
2024-10-14 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401 | 73/0 | Complete
2024-10-14 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401 | 32/0 | Complete
2024-10-15 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401 | 10/18 | Complete
2024-10-15 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-15 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401 | 67/1 | Complete
2024-10-15 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401 | 17/0 | Complete
2024-10-15 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401 | 15/0 | Complete
2024-10-15 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401 | 43/2 | Complete
2024-10-15 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-15 | 2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401 | 11/7 | Complete
2024-10-15 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401 | 11/8 | Complete
2024-10-15 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401 | 11/9 | Complete
2024-10-15 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401 | 73/0 | Complete
2024-10-15 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401 | 32/0 | Complete
2024-10-16 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401 | 10/18 | Complete
2024-10-16 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-16 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401 | 67/1 | Complete
2024-10-16 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401 | 17/0 | Complete
2024-10-16 | 2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401 | 15/0 | Complete
2024-10-16 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401 | 43/2 | Complete
2024-10-16 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-16 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401 | 11/8 | Complete
2024-10-16 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401 | 11/9 | Complete
2024-10-16 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401 | 73/0 | Complete
2024-10-16 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401 | 32/0 | Complete
2024-10-17 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401 | 10/18 | Complete
2024-10-17 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-17 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401 | 67/1 | Complete
2024-10-17 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401 | 17/0 | Complete
2024-10-17 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401 | 43/2 | Complete
2024-10-17 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-17 | 2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401 | 11/8 | Complete
2024-10-17 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401 | 11/9 | Complete
2024-10-17 | 2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401 | 73/0 | Complete
2024-10-17 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401 | 32/0 | Complete
2024-10-18 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401 | 10/18 | Complete
2024-10-18 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-18 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401 | 67/1 | Complete
2024-10-18 | 2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401 | 17/0 | Complete
2024-10-18 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401 | 43/2 | Complete
2024-10-18 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-18 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401 | 11/9 | Complete
2024-10-18 | 2024-10-18 | 2024-10-23 | Sunny Const | 37.504 | 6.2507 | TB401 | 71/3 | Complete
2024-10-18 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401 | 32/0 | Complete
2024-10-19 | 2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401 | 10/18 | Complete
2024-10-19 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-19 | 2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401 | 67/1 | Complete
2024-10-19 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401 | 43/2 | Complete
2024-10-19 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-19 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401 | 11/9 | Complete
2024-10-19 | 2024-10-18 | 2024-10-23 | Sunny Const | 37.504 | 6.2507 | TB401 | 71/3 | Complete
2024-10-19 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401 | 32/0 | Complete
2024-10-20 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-20 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401 | 43/2 | Complete
2024-10-20 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-20 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401 | 11/9 | Complete
2024-10-20 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-10-20 | 2024-10-18 | 2024-10-23 | Sunny Const | 37.504 | 6.2507 | TB401 | 71/3 | Complete
2024-10-20 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401 | 32/0 | Complete
2024-10-21 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-21 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401 | 43/2 | Complete
2024-10-21 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-21 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401 | 11/9 | Complete
2024-10-21 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-10-21 | 2024-10-18 | 2024-10-23 | Sunny Const | 37.504 | 6.2507 | TB401 | 71/3 | Complete
2024-10-21 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401 | 32/0 | Complete
2024-10-22 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-22 | 2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401 | 43/2 | Complete
2024-10-22 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-22 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401 | 11/9 | Complete
2024-10-22 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-10-22 | 2024-10-18 | 2024-10-23 | Sunny Const | 37.504 | 6.2507 | TB401 | 71/3 | Complete
2024-10-22 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401 | 32/0 | Complete
2024-10-23 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-23 | 2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401 | 40/11 | Complete
2024-10-23 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-23 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401 | 11/9 | Complete
2024-10-23 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-10-23 | 2024-10-18 | 2024-10-23 | Sunny Const | 37.504 | 6.2507 | TB401 | 71/3 | Complete
2024-10-23 | 2024-10-23 | 2024-10-27 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/6 | Complete
2024-10-23 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401 | 32/0 | Complete
2024-10-24 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-24 | 2024-10-24 | 2024-10-28 | Chinta Devi | 37.504 | 7.5008 | TB401 | 68/3 | Complete
2024-10-24 | 2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401 | 40/11 | Complete
2024-10-24 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401 | 10/8 | Complete
2024-10-24 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-24 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401 | 11/9 | Complete
2024-10-24 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-10-24 | 2024-10-23 | 2024-10-27 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/6 | Complete
2024-10-24 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401 | 32/0 | Complete
2024-10-25 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-25 | 2024-10-24 | 2024-10-28 | Chinta Devi | 37.504 | 7.5008 | TB401 | 68/3 | Complete
2024-10-25 | 2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401 | 40/11 | Complete
2024-10-25 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401 | 10/8 | Complete
2024-10-25 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-25 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401 | 11/9 | Complete
2024-10-25 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-10-25 | 2024-10-23 | 2024-10-27 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/6 | Complete
2024-10-25 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401 | 32/0 | Complete
2024-10-26 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-26 | 2024-10-24 | 2024-10-28 | Chinta Devi | 37.504 | 7.5008 | TB401 | 68/3 | Complete
2024-10-26 | 2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401 | 40/11 | Complete
2024-10-26 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401 | 10/8 | Complete
2024-10-26 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-26 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401 | 11/9 | Complete
2024-10-26 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-10-26 | 2024-10-23 | 2024-10-27 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/6 | Complete
2024-10-26 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401 | 32/0 | Complete
2024-10-27 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-27 | 2024-10-24 | 2024-10-28 | Chinta Devi | 37.504 | 7.5008 | TB401 | 68/3 | Complete
2024-10-27 | 2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401 | 40/11 | Complete
2024-10-27 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401 | 10/8 | Complete
2024-10-27 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401 | 14/2 | Complete
2024-10-27 | 2024-10-27 | 2024-11-02 | Nirmal Mahto | 45.413 | 6.4876 | TB401 | 15/1 | Complete
2024-10-27 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-27 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401 | 11/9 | Complete
2024-10-27 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-10-27 | 2024-10-23 | 2024-10-27 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/6 | Complete
2024-10-27 | 2024-10-27 | 2024-10-31 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/7 | Complete
2024-10-27 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401 | 32/0 | Complete
2024-10-28 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-28 | 2024-10-24 | 2024-10-28 | Chinta Devi | 37.504 | 7.5008 | TB401 | 68/3 | Complete
2024-10-28 | 2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401 | 40/11 | Complete
2024-10-28 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401 | 10/8 | Complete
2024-10-28 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401 | 14/2 | Complete
2024-10-28 | 2024-10-27 | 2024-11-02 | Nirmal Mahto | 45.413 | 6.4876 | TB401 | 15/1 | Complete
2024-10-28 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-28 | 2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401 | 11/9 | Complete
2024-10-28 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-10-28 | 2024-10-27 | 2024-10-31 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/7 | Complete
2024-10-28 | 2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401 | 32/0 | Complete
2024-10-29 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-29 | 2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401 | 40/11 | Complete
2024-10-29 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401 | 10/8 | Complete
2024-10-29 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401 | 14/2 | Complete
2024-10-29 | 2024-10-27 | 2024-11-02 | Nirmal Mahto | 45.413 | 6.4876 | TB401 | 15/1 | Complete
2024-10-29 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-29 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-10-29 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-10-29 | 2024-10-27 | 2024-10-31 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/7 | Complete
2024-10-30 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-30 | 2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401 | 40/11 | Complete
2024-10-30 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401 | 40/10 | Complete
2024-10-30 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401 | 10/8 | Complete
2024-10-30 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401 | 14/2 | Complete
2024-10-30 | 2024-10-27 | 2024-11-02 | Nirmal Mahto | 45.413 | 6.4876 | TB401 | 15/1 | Complete
2024-10-30 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-30 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-10-30 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-10-30 | 2024-10-27 | 2024-10-31 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/7 | Complete
2024-10-31 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-10-31 | 2024-10-31 | 2024-11-03 | Deglal Mahto | 47.148 | 11.787 | TB401 | 15/9 | Complete
2024-10-31 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401 | 40/10 | Complete
2024-10-31 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401 | 10/8 | Complete
2024-10-31 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401 | 14/2 | Complete
2024-10-31 | 2024-10-27 | 2024-11-02 | Nirmal Mahto | 45.413 | 6.4876 | TB401 | 15/1 | Complete
2024-10-31 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-10-31 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-10-31 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-10-31 | 2024-10-27 | 2024-10-31 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/7 | Complete
2024-11-01 | 2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-11-01 | 2024-11-01 | 2024-11-05 | Chinta Devi | 38.847 | 7.7694 | TB401 | 68/6 | Complete
2024-11-01 | 2024-10-31 | 2024-11-03 | Deglal Mahto | 47.148 | 11.787 | TB401 | 15/9 | Complete
2024-11-01 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401 | 40/10 | Complete
2024-11-01 | 2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401 | 10/8 | Complete
2024-11-01 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401 | 14/2 | Complete
2024-11-01 | 2024-10-27 | 2024-11-02 | Nirmal Mahto | 45.413 | 6.4876 | TB401 | 15/1 | Complete
2024-11-01 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-11-01 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-11-01 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-11-01 | 2024-11-01 | 2024-11-05 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/5 | Complete
2024-11-02 | 2024-11-01 | 2024-11-05 | Chinta Devi | 38.847 | 7.7694 | TB401 | 68/6 | Complete
2024-11-02 | 2024-10-31 | 2024-11-03 | Deglal Mahto | 47.148 | 11.787 | TB401 | 15/9 | Complete
2024-11-02 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401 | 40/10 | Complete
2024-11-02 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401 | 14/2 | Complete
2024-11-02 | 2024-10-27 | 2024-11-02 | Nirmal Mahto | 45.413 | 6.4876 | TB401 | 15/1 | Complete
2024-11-02 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-11-02 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-11-02 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-11-02 | 2024-11-01 | 2024-11-05 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/5 | Complete
2024-11-02 | 2024-11-02 | 2024-11-07 | Yogendra Mahto | 38.847 | 6.4745 | TB401 | 32/3 | Complete
2024-11-03 | 2024-11-01 | 2024-11-05 | Chinta Devi | 38.847 | 7.7694 | TB401 | 68/6 | Complete
2024-11-03 | 2024-10-31 | 2024-11-03 | Deglal Mahto | 47.148 | 11.787 | TB401 | 15/9 | Complete
2024-11-03 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401 | 40/10 | Complete
2024-11-03 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401 | 14/2 | Complete
2024-11-03 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-11-03 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-11-03 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-11-03 | 2024-11-01 | 2024-11-05 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/5 | Complete
2024-11-03 | 2024-11-02 | 2024-11-07 | Yogendra Mahto | 38.847 | 6.4745 | TB401 | 32/3 | Complete
2024-11-04 | 2024-11-01 | 2024-11-05 | Chinta Devi | 38.847 | 7.7694 | TB401 | 68/6 | Complete
2024-11-04 | 2024-11-04 | 2024-11-09 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 15/6 | Complete
2024-11-04 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401 | 40/10 | Complete
2024-11-04 | 2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401 | 14/2 | Complete
2024-11-04 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-11-04 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-11-04 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-11-04 | 2024-11-01 | 2024-11-05 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/5 | Complete
2024-11-04 | 2024-11-02 | 2024-11-07 | Yogendra Mahto | 38.847 | 6.4745 | TB401 | 32/3 | Complete
2024-11-05 | 2024-11-01 | 2024-11-05 | Chinta Devi | 38.847 | 7.7694 | TB401 | 68/6 | Complete
2024-11-05 | 2024-11-05 | 2024-11-09 | Chinta Devi | 38.847 | 7.7694 | TB401 | 68/4 | Complete
2024-11-05 | 2024-11-04 | 2024-11-09 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 15/6 | Complete
2024-11-05 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401 | 40/10 | Complete
2024-11-05 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-11-05 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-11-05 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-11-05 | 2024-11-01 | 2024-11-05 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/5 | Complete
2024-11-05 | 2024-11-05 | 2024-11-09 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/4 | Complete
2024-11-05 | 2024-11-02 | 2024-11-07 | Yogendra Mahto | 38.847 | 6.4745 | TB401 | 32/3 | Complete
2024-11-06 | 2024-11-05 | 2024-11-09 | Chinta Devi | 38.847 | 7.7694 | TB401 | 68/4 | Complete
2024-11-06 | 2024-11-04 | 2024-11-09 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 15/6 | Complete
2024-11-06 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401 | 40/10 | Complete
2024-11-06 | 2024-11-06 | 2024-11-10 | Jagdish Mahto | 60.096 | 12.0192 | TB401 | 10/12 | Complete
2024-11-06 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-11-06 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-11-06 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-11-06 | 2024-11-05 | 2024-11-09 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/4 | Complete
2024-11-06 | 2024-11-02 | 2024-11-07 | Yogendra Mahto | 38.847 | 6.4745 | TB401 | 32/3 | Complete
2024-11-07 | 2024-11-05 | 2024-11-09 | Chinta Devi | 38.847 | 7.7694 | TB401 | 68/4 | Complete
2024-11-07 | 2024-11-04 | 2024-11-09 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 15/6 | Complete
2024-11-07 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401 | 40/10 | Complete
2024-11-07 | 2024-11-06 | 2024-11-10 | Jagdish Mahto | 60.096 | 12.0192 | TB401 | 10/12 | Complete
2024-11-07 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-11-07 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-11-07 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-11-07 | 2024-11-05 | 2024-11-09 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/4 | Complete
2024-11-07 | 2024-11-02 | 2024-11-07 | Yogendra Mahto | 38.847 | 6.4745 | TB401 | 32/3 | Complete
2024-11-08 | 2024-11-05 | 2024-11-09 | Chinta Devi | 38.847 | 7.7694 | TB401 | 68/4 | Complete
2024-11-08 | 2024-11-04 | 2024-11-09 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 15/6 | Complete
2024-11-08 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401 | 40/10 | Complete
2024-11-08 | 2024-11-06 | 2024-11-10 | Jagdish Mahto | 60.096 | 12.0192 | TB401 | 10/12 | Complete
2024-11-08 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-11-08 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-11-08 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-11-08 | 2024-11-05 | 2024-11-09 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/4 | Complete
2024-11-09 | 2024-11-05 | 2024-11-09 | Chinta Devi | 38.847 | 7.7694 | TB401 | 68/4 | Complete
2024-11-09 | 2024-11-04 | 2024-11-09 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 15/6 | Complete
2024-11-09 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401 | 40/10 | Complete
2024-11-09 | 2024-11-06 | 2024-11-10 | Jagdish Mahto | 60.096 | 12.0192 | TB401 | 10/12 | Complete
2024-11-09 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-11-09 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-11-09 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-11-09 | 2024-11-05 | 2024-11-09 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/4 | Complete
2024-11-09 | 2024-11-09 | 2024-11-13 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/3 | Complete
2024-11-10 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401 | 16/0 | Complete
2024-11-10 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401 | 40/10 | Complete
2024-11-10 | 2024-11-06 | 2024-11-10 | Jagdish Mahto | 60.096 | 12.0192 | TB401 | 10/12 | Complete
2024-11-10 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-11-10 | 2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-11-10 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-11-10 | 2024-11-09 | 2024-11-13 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/3 | Complete
2024-11-11 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401 | 16/0 | Complete
2024-11-11 | 2024-11-11 | 2024-11-17 | Deglal Mahto | 37.504 | 5.3577 | TB401 | 11/14 | Complete
2024-11-11 | 2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401 | 40/10 | Complete
2024-11-11 | 2024-11-11 | 2024-11-17 | Jagdish Mahto | 38.847 | 5.5496 | TB401 | 10/10 | Complete
2024-11-11 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-11-11 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-11-11 | 2024-11-09 | 2024-11-13 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/3 | Complete
2024-11-12 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401 | 16/0 | Complete
2024-11-12 | 2024-11-11 | 2024-11-17 | Deglal Mahto | 37.504 | 5.3577 | TB401 | 11/14 | Complete
2024-11-12 | 2024-11-11 | 2024-11-17 | Jagdish Mahto | 38.847 | 5.5496 | TB401 | 10/10 | Complete
2024-11-12 | 2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-11-12 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-11-12 | 2024-11-09 | 2024-11-13 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/3 | Complete
2024-11-13 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401 | 16/0 | Complete
2024-11-13 | 2024-11-11 | 2024-11-17 | Deglal Mahto | 37.504 | 5.3577 | TB401 | 11/14 | Complete
2024-11-13 | 2024-11-11 | 2024-11-17 | Jagdish Mahto | 38.847 | 5.5496 | TB401 | 10/10 | Complete
2024-11-13 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-11-13 | 2024-11-09 | 2024-11-13 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/3 | Complete
2024-11-13 | 2024-11-13 | 2024-11-17 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/2 | Complete
2024-11-14 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401 | 16/0 | Complete
2024-11-14 | 2024-11-11 | 2024-11-17 | Deglal Mahto | 37.504 | 5.3577 | TB401 | 11/14 | Complete
2024-11-14 | 2024-11-11 | 2024-11-17 | Jagdish Mahto | 38.847 | 5.5496 | TB401 | 10/10 | Complete
2024-11-14 | 2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-11-14 | 2024-11-13 | 2024-11-17 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/2 | Complete
2024-11-15 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401 | 16/0 | Complete
2024-11-15 | 2024-11-11 | 2024-11-17 | Deglal Mahto | 37.504 | 5.3577 | TB401 | 11/14 | Complete
2024-11-15 | 2024-11-11 | 2024-11-17 | Jagdish Mahto | 38.847 | 5.5496 | TB401 | 10/10 | Complete
2024-11-15 | 2024-11-13 | 2024-11-17 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/2 | Complete
2024-11-16 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401 | 16/0 | Complete
2024-11-16 | 2024-11-11 | 2024-11-17 | Deglal Mahto | 37.504 | 5.3577 | TB401 | 11/14 | Complete
2024-11-16 | 2024-11-11 | 2024-11-17 | Jagdish Mahto | 38.847 | 5.5496 | TB401 | 10/10 | Complete
2024-11-16 | 2024-11-13 | 2024-11-17 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/2 | Complete
2024-11-17 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401 | 16/0 | Complete
2024-11-17 | 2024-11-11 | 2024-11-17 | Deglal Mahto | 37.504 | 5.3577 | TB401 | 11/14 | Complete
2024-11-17 | 2024-11-11 | 2024-11-17 | Jagdish Mahto | 38.847 | 5.5496 | TB401 | 10/10 | Complete
2024-11-17 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401 | 19/7 | Complete
2024-11-17 | 2024-11-13 | 2024-11-17 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/2 | Complete
2024-11-18 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401 | 16/0 | Complete
2024-11-18 | 2024-11-18 | 2024-11-23 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 11/15 | Complete
2024-11-18 | 2024-11-18 | 2024-11-21 | Jagdish Mahto | 38.847 | 9.7118 | TB401 | 10/13 | Complete
2024-11-18 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401 | 19/7 | Complete
2024-11-18 | 2024-11-18 | 2024-11-22 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/1 | Complete
2024-11-19 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401 | 16/0 | Complete
2024-11-19 | 2024-11-18 | 2024-11-23 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 11/15 | Complete
2024-11-19 | 2024-11-18 | 2024-11-21 | Jagdish Mahto | 38.847 | 9.7118 | TB401 | 10/13 | Complete
2024-11-19 | 2024-11-19 | 2024-11-25 | Jailal Ageria | 38.847 | 5.5496 | TB401 | 13/1 | Complete
2024-11-19 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401 | 19/7 | Complete
2024-11-19 | 2024-11-18 | 2024-11-22 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/1 | Complete
2024-11-20 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401 | 16/0 | Complete
2024-11-20 | 2024-11-18 | 2024-11-23 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 11/15 | Complete
2024-11-20 | 2024-11-18 | 2024-11-21 | Jagdish Mahto | 38.847 | 9.7118 | TB401 | 10/13 | Complete
2024-11-20 | 2024-11-19 | 2024-11-25 | Jailal Ageria | 38.847 | 5.5496 | TB401 | 13/1 | Complete
2024-11-20 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401 | 19/7 | Complete
2024-11-20 | 2024-11-18 | 2024-11-22 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/1 | Complete
2024-11-21 | 2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401 | 16/0 | Complete
2024-11-21 | 2024-11-18 | 2024-11-23 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 11/15 | Complete
2024-11-21 | 2024-11-18 | 2024-11-21 | Jagdish Mahto | 38.847 | 9.7118 | TB401 | 10/13 | Complete
2024-11-21 | 2024-11-19 | 2024-11-25 | Jailal Ageria | 38.847 | 5.5496 | TB401 | 13/1 | Complete
2024-11-21 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401 | 19/7 | Complete
2024-11-21 | 2024-11-18 | 2024-11-22 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/1 | Complete
2024-11-22 | 2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401 | 68/0 | Complete
2024-11-22 | 2024-11-18 | 2024-11-23 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 11/15 | Complete
2024-11-22 | 2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401 | 10/11 | Complete
2024-11-22 | 2024-11-19 | 2024-11-25 | Jailal Ageria | 38.847 | 5.5496 | TB401 | 13/1 | Complete
2024-11-22 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401 | 19/7 | Complete
2024-11-22 | 2024-11-18 | 2024-11-22 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/1 | Complete
2024-11-23 | 2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401 | 68/0 | Complete
2024-11-23 | 2024-11-18 | 2024-11-23 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 11/15 | Complete
2024-11-23 | 2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401 | 10/11 | Complete
2024-11-23 | 2024-11-19 | 2024-11-25 | Jailal Ageria | 38.847 | 5.5496 | TB401 | 13/1 | Complete
2024-11-23 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401 | 19/7 | Complete
2024-11-23 | 2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401 | 69/0 | Complete
2024-11-24 | 2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401 | 68/0 | Complete
2024-11-24 | 2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401 | 10/11 | Complete
2024-11-24 | 2024-11-19 | 2024-11-25 | Jailal Ageria | 38.847 | 5.5496 | TB401 | 13/1 | Complete
2024-11-24 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401 | 19/7 | Complete
2024-11-24 | 2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401 | 69/0 | Complete
2024-11-25 | 2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401 | 68/0 | Complete
2024-11-25 | 2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401 | 10/11 | Complete
2024-11-25 | 2024-11-19 | 2024-11-25 | Jailal Ageria | 38.847 | 5.5496 | TB401 | 13/1 | Complete
2024-11-25 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401 | 19/7 | Complete
2024-11-25 | 2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401 | 69/0 | Complete
2024-11-26 | 2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401 | 68/0 | Complete
2024-11-26 | 2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401 | 10/11 | Complete
2024-11-26 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401 | 19/7 | Complete
2024-11-26 | 2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401 | 69/0 | Complete
2024-11-27 | 2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401 | 68/0 | Complete
2024-11-27 | 2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401 | 10/11 | Complete
2024-11-27 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401 | 19/7 | Complete
2024-11-27 | 2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401 | 69/0 | Complete
2024-11-28 | 2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401 | 68/0 | Complete
2024-11-28 | 2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401 | 10/11 | Complete
2024-11-28 | 2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401 | 19/7 | Complete
2024-11-28 | 2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401 | 69/0 | Complete
2024-11-28 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-11-29 | 2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401 | 68/0 | Complete
2024-11-29 | 2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401 | 10/11 | Complete
2024-11-29 | 2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401 | 69/0 | Complete
2024-11-29 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-11-30 | 2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401 | 69/0 | Complete
2024-11-30 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-01 | 2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401 | 67/0 | Complete
2024-12-01 | 2024-12-01 | 2024-12-06 | Sunny Const | 37.504 | 6.2507 | TB401 | 69/9 | Complete
2024-12-01 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-02 | 2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401 | 67/0 | Complete
2024-12-02 | 2024-12-02 | 2024-12-08 | Sanjeev Kumar | 38.847 | 5.5496 | TB401 | 66/1 | Complete
2024-12-02 | 2024-12-01 | 2024-12-06 | Sunny Const | 37.504 | 6.2507 | TB401 | 69/9 | Complete
2024-12-02 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-03 | 2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401 | 67/0 | Complete
2024-12-03 | 2024-12-02 | 2024-12-08 | Sanjeev Kumar | 38.847 | 5.5496 | TB401 | 66/1 | Complete
2024-12-03 | 2024-12-01 | 2024-12-06 | Sunny Const | 37.504 | 6.2507 | TB401 | 69/9 | Complete
2024-12-03 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-04 | 2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401 | 67/0 | Complete
2024-12-04 | 2024-12-02 | 2024-12-08 | Sanjeev Kumar | 38.847 | 5.5496 | TB401 | 66/1 | Complete
2024-12-04 | 2024-12-01 | 2024-12-06 | Sunny Const | 37.504 | 6.2507 | TB401 | 69/9 | Complete
2024-12-04 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-05 | 2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401 | 67/0 | Complete
2024-12-05 | 2024-12-02 | 2024-12-08 | Sanjeev Kumar | 38.847 | 5.5496 | TB401 | 66/1 | Complete
2024-12-05 | 2024-12-01 | 2024-12-06 | Sunny Const | 37.504 | 6.2507 | TB401 | 69/9 | Complete
2024-12-05 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-06 | 2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401 | 67/0 | Complete
2024-12-06 | 2024-12-02 | 2024-12-08 | Sanjeev Kumar | 38.847 | 5.5496 | TB401 | 66/1 | Complete
2024-12-06 | 2024-12-01 | 2024-12-06 | Sunny Const | 37.504 | 6.2507 | TB401 | 69/9 | Complete
2024-12-06 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-07 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401 | 11/12 | Complete
2024-12-07 | 2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401 | 67/0 | Complete
2024-12-07 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-07 | 2024-12-02 | 2024-12-08 | Sanjeev Kumar | 38.847 | 5.5496 | TB401 | 66/1 | Complete
2024-12-07 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401 | 71/0 | Complete
2024-12-07 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-08 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401 | 11/12 | Complete
2024-12-08 | 2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401 | 67/0 | Complete
2024-12-08 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-08 | 2024-12-02 | 2024-12-08 | Sanjeev Kumar | 38.847 | 5.5496 | TB401 | 66/1 | Complete
2024-12-08 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401 | 71/0 | Complete
2024-12-08 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-09 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401 | 11/12 | Complete
2024-12-09 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 41/12 | Complete
2024-12-09 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-09 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401 | 71/0 | Complete
2024-12-09 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-10 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401 | 11/12 | Complete
2024-12-10 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 41/12 | Complete
2024-12-10 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-10 | 2024-12-10 | 2024-12-15 | Sobha Devi | 47.148 | 7.858 | TB401 | 38/3 | Complete
2024-12-10 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401 | 71/0 | Complete
2024-12-10 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-11 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401 | 11/12 | Complete
2024-12-11 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 41/12 | Complete
2024-12-11 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401 | 10/20 | Complete
2024-12-11 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-11 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401 | 58/13 | Complete
2024-12-11 | 2024-12-10 | 2024-12-15 | Sobha Devi | 47.148 | 7.858 | TB401 | 38/3 | Complete
2024-12-11 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401 | 71/0 | Complete
2024-12-11 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-12 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401 | 11/12 | Complete
2024-12-12 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 41/12 | Complete
2024-12-12 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401 | 10/20 | Complete
2024-12-12 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-12 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401 | 58/13 | Complete
2024-12-12 | 2024-12-10 | 2024-12-15 | Sobha Devi | 47.148 | 7.858 | TB401 | 38/3 | Complete
2024-12-12 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401 | 71/0 | Complete
2024-12-12 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-13 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401 | 11/12 | Complete
2024-12-13 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 41/12 | Complete
2024-12-13 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401 | 10/20 | Complete
2024-12-13 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-13 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401 | 58/13 | Complete
2024-12-13 | 2024-12-10 | 2024-12-15 | Sobha Devi | 47.148 | 7.858 | TB401 | 38/3 | Complete
2024-12-13 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401 | 71/0 | Complete
2024-12-13 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-14 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401 | 11/12 | Complete
2024-12-14 | 2024-12-14 | 2024-12-18 | Chinta Devi | 37.504 | 7.5008 | TB401 | 65/6 | Complete
2024-12-14 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 41/12 | Complete
2024-12-14 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401 | 10/20 | Complete
2024-12-14 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-14 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401 | 58/13 | Complete
2024-12-14 | 2024-12-10 | 2024-12-15 | Sobha Devi | 47.148 | 7.858 | TB401 | 38/3 | Complete
2024-12-14 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401 | 71/0 | Complete
2024-12-14 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-15 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401 | 11/12 | Complete
2024-12-15 | 2024-12-14 | 2024-12-18 | Chinta Devi | 37.504 | 7.5008 | TB401 | 65/6 | Complete
2024-12-15 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 41/12 | Complete
2024-12-15 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401 | 10/20 | Complete
2024-12-15 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-15 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401 | 58/13 | Complete
2024-12-15 | 2024-12-10 | 2024-12-15 | Sobha Devi | 47.148 | 7.858 | TB401 | 38/3 | Complete
2024-12-15 | 2024-12-15 | 2024-12-19 | Sobha Devi | 45.413 | 9.0826 | TB401 | 38/2 | Complete
2024-12-15 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401 | 71/0 | Complete
2024-12-15 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-16 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401 | 11/12 | Complete
2024-12-16 | 2024-12-14 | 2024-12-18 | Chinta Devi | 37.504 | 7.5008 | TB401 | 65/6 | Complete
2024-12-16 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 41/12 | Complete
2024-12-16 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401 | 10/20 | Complete
2024-12-16 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-16 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401 | 58/13 | Complete
2024-12-16 | 2024-12-15 | 2024-12-19 | Sobha Devi | 45.413 | 9.0826 | TB401 | 38/2 | Complete
2024-12-16 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401 | 71/0 | Complete
2024-12-16 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-17 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401 | 11/12 | Complete
2024-12-17 | 2024-12-14 | 2024-12-18 | Chinta Devi | 37.504 | 7.5008 | TB401 | 65/6 | Complete
2024-12-17 | 2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401 | 11/11 | Complete
2024-12-17 | 2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 41/12 | Complete
2024-12-17 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401 | 10/20 | Complete
2024-12-17 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-17 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401 | 58/13 | Complete
2024-12-17 | 2024-12-15 | 2024-12-19 | Sobha Devi | 45.413 | 9.0826 | TB401 | 38/2 | Complete
2024-12-17 | 2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401 | 71/0 | Complete
2024-12-17 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-18 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401 | 11/12 | Complete
2024-12-18 | 2024-12-14 | 2024-12-18 | Chinta Devi | 37.504 | 7.5008 | TB401 | 65/6 | Complete
2024-12-18 | 2024-12-18 | 2024-12-22 | Chinta Devi | 37.504 | 7.5008 | TB401 | 65/7 | Complete
2024-12-18 | 2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401 | 11/11 | Complete
2024-12-18 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401 | 10/20 | Complete
2024-12-18 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-18 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401 | 58/13 | Complete
2024-12-18 | 2024-12-15 | 2024-12-19 | Sobha Devi | 45.413 | 9.0826 | TB401 | 38/2 | Complete
2024-12-18 | 2024-12-18 | 2024-12-22 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/8 | Complete
2024-12-18 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-19 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401 | 11/12 | Complete
2024-12-19 | 2024-12-18 | 2024-12-22 | Chinta Devi | 37.504 | 7.5008 | TB401 | 65/7 | Complete
2024-12-19 | 2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401 | 11/11 | Complete
2024-12-19 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401 | 42/0 | Complete
2024-12-19 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401 | 10/20 | Complete
2024-12-19 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-19 | 2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401 | 58/13 | Complete
2024-12-19 | 2024-12-15 | 2024-12-19 | Sobha Devi | 45.413 | 9.0826 | TB401 | 38/2 | Complete
2024-12-19 | 2024-12-18 | 2024-12-22 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/8 | Complete
2024-12-19 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-20 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401 | 11/12 | Complete
2024-12-20 | 2024-12-18 | 2024-12-22 | Chinta Devi | 37.504 | 7.5008 | TB401 | 65/7 | Complete
2024-12-20 | 2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401 | 11/11 | Complete
2024-12-20 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401 | 42/0 | Complete
2024-12-20 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401 | 10/20 | Complete
2024-12-20 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-20 | 2024-12-20 | 2024-12-24 | Sobha Devi | 38.847 | 7.7694 | TB401 | 38/1 | Complete
2024-12-20 | 2024-12-18 | 2024-12-22 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/8 | Complete
2024-12-20 | 2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-21 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401 | 11/12 | Complete
2024-12-21 | 2024-12-18 | 2024-12-22 | Chinta Devi | 37.504 | 7.5008 | TB401 | 65/7 | Complete
2024-12-21 | 2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401 | 11/11 | Complete
2024-12-21 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401 | 42/0 | Complete
2024-12-21 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401 | 10/20 | Complete
2024-12-21 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-21 | 2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401 | 41/2 | Complete
2024-12-21 | 2024-12-20 | 2024-12-24 | Sobha Devi | 38.847 | 7.7694 | TB401 | 38/1 | Complete
2024-12-21 | 2024-12-18 | 2024-12-22 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/8 | Complete
2024-12-22 | 2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401 | 11/12 | Complete
2024-12-22 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401 | 11/13 | Complete
2024-12-22 | 2024-12-18 | 2024-12-22 | Chinta Devi | 37.504 | 7.5008 | TB401 | 65/7 | Complete
2024-12-22 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401 | 66/0 | Complete
2024-12-22 | 2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401 | 11/11 | Complete
2024-12-22 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401 | 42/0 | Complete
2024-12-22 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401 | 10/20 | Complete
2024-12-22 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-22 | 2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401 | 41/2 | Complete
2024-12-22 | 2024-12-20 | 2024-12-24 | Sobha Devi | 38.847 | 7.7694 | TB401 | 38/1 | Complete
2024-12-22 | 2024-12-18 | 2024-12-22 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/8 | Complete
2024-12-22 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401 | 70/0 | Complete
2024-12-23 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401 | 11/13 | Complete
2024-12-23 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401 | 66/0 | Complete
2024-12-23 | 2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401 | 11/11 | Complete
2024-12-23 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401 | 42/0 | Complete
2024-12-23 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401 | 10/20 | Complete
2024-12-23 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-23 | 2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401 | 41/2 | Complete
2024-12-23 | 2024-12-20 | 2024-12-24 | Sobha Devi | 38.847 | 7.7694 | TB401 | 38/1 | Complete
2024-12-23 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401 | 70/0 | Complete
2024-12-24 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401 | 11/13 | Complete
2024-12-24 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401 | 66/0 | Complete
2024-12-24 | 2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401 | 11/11 | Complete
2024-12-24 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401 | 42/0 | Complete
2024-12-24 | 2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401 | 10/20 | Complete
2024-12-24 | 2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-24 | 2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401 | 41/2 | Complete
2024-12-24 | 2024-12-20 | 2024-12-24 | Sobha Devi | 38.847 | 7.7694 | TB401 | 38/1 | Complete
2024-12-24 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401 | 70/0 | Complete
2024-12-25 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401 | 11/13 | Complete
2024-12-25 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401 | 66/0 | Complete
2024-12-25 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401 | 42/0 | Complete
2024-12-25 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401 | 8/6 | Complete
2024-12-25 | 2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401 | 41/2 | Complete
2024-12-25 | 2024-12-25 | 2024-12-28 | Sobha Devi | 37.504 | 9.376 | TB401 | 37/3 | Complete
2024-12-25 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401 | 70/0 | Complete
2024-12-26 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401 | 11/13 | Complete
2024-12-26 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401 | 66/0 | Complete
2024-12-26 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401 | 42/0 | Complete
2024-12-26 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401 | 8/6 | Complete
2024-12-26 | 2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401 | 41/2 | Complete
2024-12-26 | 2024-12-25 | 2024-12-28 | Sobha Devi | 37.504 | 9.376 | TB401 | 37/3 | Complete
2024-12-26 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401 | 70/0 | Complete
2024-12-27 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401 | 11/13 | Complete
2024-12-27 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401 | 66/0 | Complete
2024-12-27 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401 | 42/0 | Complete
2024-12-27 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401 | 8/6 | Complete
2024-12-27 | 2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401 | 41/2 | Complete
2024-12-27 | 2024-12-25 | 2024-12-28 | Sobha Devi | 37.504 | 9.376 | TB401 | 37/3 | Complete
2024-12-27 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401 | 70/0 | Complete
2024-12-28 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401 | 11/13 | Complete
2024-12-28 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401 | 66/0 | Complete
2024-12-28 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401 | 42/0 | Complete
2024-12-28 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401 | 8/6 | Complete
2024-12-28 | 2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401 | 41/2 | Complete
2024-12-28 | 2024-12-25 | 2024-12-28 | Sobha Devi | 37.504 | 9.376 | TB401 | 37/3 | Complete
2024-12-28 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401 | 70/0 | Complete
2024-12-29 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401 | 11/13 | Complete
2024-12-29 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401 | 66/0 | Complete
2024-12-29 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401 | 42/0 | Complete
2024-12-29 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401 | 8/6 | Complete
2024-12-29 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401 | 41/3 | Complete
2024-12-29 | 2024-12-29 | 2025-01-03 | Sobha Devi | 45.413 | 7.5688 | TB401 | 37/4 | Complete
2024-12-29 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401 | 70/0 | Complete
2024-12-30 | 2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401 | 11/13 | Complete
2024-12-30 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401 | 66/0 | Complete
2024-12-30 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401 | 42/0 | Complete
2024-12-30 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401 | 8/6 | Complete
2024-12-30 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401 | 41/3 | Complete
2024-12-30 | 2024-12-29 | 2025-01-03 | Sobha Devi | 45.413 | 7.5688 | TB401 | 37/4 | Complete
2024-12-30 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401 | 70/0 | Complete
2024-12-31 | 2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401 | 66/0 | Complete
2024-12-31 | 2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401 | 42/0 | Complete
2024-12-31 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401 | 8/6 | Complete
2024-12-31 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401 | 41/3 | Complete
2024-12-31 | 2024-12-29 | 2025-01-03 | Sobha Devi | 45.413 | 7.5688 | TB401 | 37/4 | Complete
2024-12-31 | 2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401 | 70/0 | Complete
2025-01-01 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401 | 8/6 | Complete
2025-01-01 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401 | 41/3 | Complete
2025-01-01 | 2024-12-29 | 2025-01-03 | Sobha Devi | 45.413 | 7.5688 | TB401 | 37/4 | Complete
2025-01-02 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401 | 8/6 | Complete
2025-01-02 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401 | 41/3 | Complete
2025-01-02 | 2024-12-29 | 2025-01-03 | Sobha Devi | 45.413 | 7.5688 | TB401 | 37/4 | Complete
2025-01-03 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401 | 8/6 | Complete
2025-01-03 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401 | 41/3 | Complete
2025-01-03 | 2024-12-29 | 2025-01-03 | Sobha Devi | 45.413 | 7.5688 | TB401 | 37/4 | Complete
2025-01-04 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401 | 8/6 | Complete
2025-01-04 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401 | 41/3 | Complete
2025-01-04 | 2025-01-04 | 2025-01-10 | Sobha Devi | 67.873 | 9.6961 | TB401 | 37/2 | Complete
2025-01-05 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401 | 8/6 | Complete
2025-01-05 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401 | 41/3 | Complete
2025-01-05 | 2025-01-04 | 2025-01-10 | Sobha Devi | 67.873 | 9.6961 | TB401 | 37/2 | Complete
2025-01-06 | 2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401 | 8/6 | Complete
2025-01-06 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401 | 41/3 | Complete
2025-01-06 | 2025-01-06 | 2025-01-10 | Sanjeev Kumar | 37.504 | 7.5008 | TB401 | 59/4 | Complete
2025-01-06 | 2025-01-04 | 2025-01-10 | Sobha Devi | 67.873 | 9.6961 | TB401 | 37/2 | Complete
2025-01-07 | 2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401 | 41/3 | Complete
2025-01-07 | 2025-01-06 | 2025-01-10 | Sanjeev Kumar | 37.504 | 7.5008 | TB401 | 59/4 | Complete
2025-01-07 | 2025-01-04 | 2025-01-10 | Sobha Devi | 67.873 | 9.6961 | TB401 | 37/2 | Complete
2025-01-08 | 2025-01-06 | 2025-01-10 | Sanjeev Kumar | 37.504 | 7.5008 | TB401 | 59/4 | Complete
2025-01-08 | 2025-01-04 | 2025-01-10 | Sobha Devi | 67.873 | 9.6961 | TB401 | 37/2 | Complete
2025-01-09 | 2025-01-06 | 2025-01-10 | Sanjeev Kumar | 37.504 | 7.5008 | TB401 | 59/4 | Complete
2025-01-09 | 2025-01-04 | 2025-01-10 | Sobha Devi | 67.873 | 9.6961 | TB401 | 37/2 | Complete
2025-01-10 | 2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401 | 41/1 | Complete
2025-01-10 | 2025-01-06 | 2025-01-10 | Sanjeev Kumar | 37.504 | 7.5008 | TB401 | 59/4 | Complete
2025-01-10 | 2025-01-04 | 2025-01-10 | Sobha Devi | 67.873 | 9.6961 | TB401 | 37/2 | Complete
2025-01-10 | 2025-01-10 | 2025-01-16 | Sobha Devi | 38.847 | 5.5496 | TB401 | 37/5 | Complete
2025-01-10 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-11 | 2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401 | 41/1 | Complete
2025-01-11 | 2025-01-10 | 2025-01-16 | Sobha Devi | 38.847 | 5.5496 | TB401 | 37/5 | Complete
2025-01-11 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-12 | 2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401 | 41/1 | Complete
2025-01-12 | 2025-01-10 | 2025-01-16 | Sobha Devi | 38.847 | 5.5496 | TB401 | 37/5 | Complete
2025-01-12 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-13 | 2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401 | 41/1 | Complete
2025-01-13 | 2025-01-10 | 2025-01-16 | Sobha Devi | 38.847 | 5.5496 | TB401 | 37/5 | Complete
2025-01-13 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-14 | 2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401 | 41/1 | Complete
2025-01-14 | 2025-01-10 | 2025-01-16 | Sobha Devi | 38.847 | 5.5496 | TB401 | 37/5 | Complete
2025-01-14 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-15 | 2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401 | 41/1 | Complete
2025-01-15 | 2025-01-10 | 2025-01-16 | Sobha Devi | 38.847 | 5.5496 | TB401 | 37/5 | Complete
2025-01-15 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-16 | 2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401 | 41/1 | Complete
2025-01-16 | 2025-01-10 | 2025-01-16 | Sobha Devi | 38.847 | 5.5496 | TB401 | 37/5 | Complete
2025-01-16 | 2025-01-16 | 2025-01-20 | Sobha Devi | 45.413 | 9.0826 | TB401 | 37/6 | Complete
2025-01-16 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-17 | 2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401 | 41/1 | Complete
2025-01-17 | 2025-01-16 | 2025-01-20 | Sobha Devi | 45.413 | 9.0826 | TB401 | 37/6 | Complete
2025-01-17 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-18 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401 | 41/0 | Complete
2025-01-18 | 2025-01-16 | 2025-01-20 | Sobha Devi | 45.413 | 9.0826 | TB401 | 37/6 | Complete
2025-01-18 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-19 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401 | 41/0 | Complete
2025-01-19 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-01-19 | 2025-01-16 | 2025-01-20 | Sobha Devi | 45.413 | 9.0826 | TB401 | 37/6 | Complete
2025-01-19 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-20 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401 | 41/0 | Complete
2025-01-20 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-01-20 | 2025-01-16 | 2025-01-20 | Sobha Devi | 45.413 | 9.0826 | TB401 | 37/6 | Complete
2025-01-20 | 2025-01-20 | 2025-01-24 | Sobha Devi | 38.847 | 7.7694 | TB401 | 37/7 | Complete
2025-01-20 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-21 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401 | 41/0 | Complete
2025-01-21 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-01-21 | 2025-01-20 | 2025-01-24 | Sobha Devi | 38.847 | 7.7694 | TB401 | 37/7 | Complete
2025-01-21 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-22 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401 | 41/0 | Complete
2025-01-22 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-01-22 | 2025-01-20 | 2025-01-24 | Sobha Devi | 38.847 | 7.7694 | TB401 | 37/7 | Complete
2025-01-22 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-23 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401 | 41/0 | Complete
2025-01-23 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-01-23 | 2025-01-20 | 2025-01-24 | Sobha Devi | 38.847 | 7.7694 | TB401 | 37/7 | Complete
2025-01-23 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-24 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401 | 41/0 | Complete
2025-01-24 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-01-24 | 2025-01-20 | 2025-01-24 | Sobha Devi | 38.847 | 7.7694 | TB401 | 37/7 | Complete
2025-01-24 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-25 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401 | 41/0 | Complete
2025-01-25 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-01-25 | 2025-01-25 | 2025-01-28 | Sobha Devi | 37.504 | 9.376 | TB401 | 37/8 | Complete
2025-01-25 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-26 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401 | 41/0 | Complete
2025-01-26 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-01-26 | 2025-01-25 | 2025-01-28 | Sobha Devi | 37.504 | 9.376 | TB401 | 37/8 | Complete
2025-01-26 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-27 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401 | 41/0 | Complete
2025-01-27 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-01-27 | 2025-01-25 | 2025-01-28 | Sobha Devi | 37.504 | 9.376 | TB401 | 37/8 | Complete
2025-01-27 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-28 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401 | 41/0 | Complete
2025-01-28 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-01-28 | 2025-01-25 | 2025-01-28 | Sobha Devi | 37.504 | 9.376 | TB401 | 37/8 | Complete
2025-01-28 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-29 | 2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401 | 41/0 | Complete
2025-01-29 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401 | 40/12 | Complete
2025-01-29 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-01-29 | 2025-01-29 | 2025-02-04 | Sobha Devi | 66.381 | 9.483 | TB401 | 38/0 | Complete
2025-01-29 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-30 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401 | 40/12 | Complete
2025-01-30 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-01-30 | 2025-01-29 | 2025-02-04 | Sobha Devi | 66.381 | 9.483 | TB401 | 38/0 | Complete
2025-01-30 | 2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2025-01-31 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-01-31 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401 | 40/12 | Complete
2025-01-31 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-01-31 | 2025-01-29 | 2025-02-04 | Sobha Devi | 66.381 | 9.483 | TB401 | 38/0 | Complete
2025-02-01 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-01 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401 | 40/12 | Complete
2025-02-01 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-01 | 2025-01-29 | 2025-02-04 | Sobha Devi | 66.381 | 9.483 | TB401 | 38/0 | Complete
2025-02-02 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-02 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401 | 40/12 | Complete
2025-02-02 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-02 | 2025-01-29 | 2025-02-04 | Sobha Devi | 66.381 | 9.483 | TB401 | 38/0 | Complete
2025-02-03 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-03 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401 | 40/12 | Complete
2025-02-03 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-03 | 2025-01-29 | 2025-02-04 | Sobha Devi | 66.381 | 9.483 | TB401 | 38/0 | Complete
2025-02-04 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-04 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401 | 40/12 | Complete
2025-02-04 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-04 | 2025-01-29 | 2025-02-04 | Sobha Devi | 66.381 | 9.483 | TB401 | 38/0 | Complete
2025-02-05 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-05 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401 | 40/12 | Complete
2025-02-05 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-06 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-06 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401 | 40/12 | Complete
2025-02-06 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-07 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-07 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401 | 40/12 | Complete
2025-02-07 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401 | 60/0 | Complete
2025-02-07 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-08 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-08 | 2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401 | 40/12 | Complete
2025-02-08 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401 | 60/0 | Complete
2025-02-08 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-09 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-09 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401 | 49/0 | Complete
2025-02-09 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401 | 60/0 | Complete
2025-02-09 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-10 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-10 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401 | 49/0 | Complete
2025-02-10 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401 | 60/0 | Complete
2025-02-10 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-11 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-11 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401 | 49/0 | Complete
2025-02-11 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401 | 60/0 | Complete
2025-02-11 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-12 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-12 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401 | 49/0 | Complete
2025-02-12 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401 | 60/0 | Complete
2025-02-12 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-13 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-13 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401 | 49/0 | Complete
2025-02-13 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401 | 60/0 | Complete
2025-02-13 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-14 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-14 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401 | 49/0 | Complete
2025-02-14 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401 | 60/0 | Complete
2025-02-14 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-15 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-15 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401 | 49/0 | Complete
2025-02-15 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401 | 60/0 | Complete
2025-02-15 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-15 | 2025-02-15 | 2025-02-20 | Sunny Const | 38.847 | 6.4745 | TB401 | 40/6 | Complete
2025-02-16 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-16 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401 | 49/0 | Complete
2025-02-16 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401 | 60/0 | Complete
2025-02-16 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-16 | 2025-02-15 | 2025-02-20 | Sunny Const | 38.847 | 6.4745 | TB401 | 40/6 | Complete
2025-02-17 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-17 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401 | 49/0 | Complete
2025-02-17 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401 | 60/0 | Complete
2025-02-17 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-17 | 2025-02-15 | 2025-02-20 | Sunny Const | 38.847 | 6.4745 | TB401 | 40/6 | Complete
2025-02-18 | 2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-18 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401 | 49/0 | Complete
2025-02-18 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401 | 60/0 | Complete
2025-02-18 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-18 | 2025-02-15 | 2025-02-20 | Sunny Const | 38.847 | 6.4745 | TB401 | 40/6 | Complete
2025-02-19 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401 | 44/0 | Complete
2025-02-19 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401 | 49/0 | Complete
2025-02-19 | 2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401 | 60/0 | Complete
2025-02-19 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-19 | 2025-02-15 | 2025-02-20 | Sunny Const | 38.847 | 6.4745 | TB401 | 40/6 | Complete
2025-02-20 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401 | 44/0 | Complete
2025-02-20 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401 | 49/0 | Complete
2025-02-20 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401 | 61/0 | Complete
2025-02-20 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-20 | 2025-02-15 | 2025-02-20 | Sunny Const | 38.847 | 6.4745 | TB401 | 40/6 | Complete
2025-02-21 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401 | 44/0 | Complete
2025-02-21 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401 | 49/0 | Complete
2025-02-21 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401 | 61/0 | Complete
2025-02-21 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-21 | 2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401 | 39/0 | Complete
2025-02-21 | 2025-02-21 | 2025-02-26 | Sunny Const | 38.847 | 6.4745 | TB401 | 40/7 | Complete
2025-02-22 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401 | 44/0 | Complete
2025-02-22 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401 | 49/0 | Complete
2025-02-22 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401 | 61/0 | Complete
2025-02-22 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-22 | 2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401 | 39/0 | Complete
2025-02-22 | 2025-02-21 | 2025-02-26 | Sunny Const | 38.847 | 6.4745 | TB401 | 40/7 | Complete
2025-02-23 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401 | 44/0 | Complete
2025-02-23 | 2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401 | 49/0 | Complete
2025-02-23 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401 | 61/0 | Complete
2025-02-23 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-23 | 2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401 | 39/0 | Complete
2025-02-23 | 2025-02-21 | 2025-02-26 | Sunny Const | 38.847 | 6.4745 | TB401 | 40/7 | Complete
2025-02-24 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401 | 44/0 | Complete
2025-02-24 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401 | 61/0 | Complete
2025-02-24 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-24 | 2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401 | 39/0 | Complete
2025-02-24 | 2025-02-21 | 2025-02-26 | Sunny Const | 38.847 | 6.4745 | TB401 | 40/7 | Complete
2025-02-25 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401 | 44/0 | Complete
2025-02-25 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401 | 61/0 | Complete
2025-02-25 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-25 | 2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401 | 39/0 | Complete
2025-02-25 | 2025-02-21 | 2025-02-26 | Sunny Const | 38.847 | 6.4745 | TB401 | 40/7 | Complete
2025-02-26 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401 | 44/0 | Complete
2025-02-26 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401 | 61/0 | Complete
2025-02-26 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-26 | 2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401 | 39/0 | Complete
2025-02-26 | 2025-02-21 | 2025-02-26 | Sunny Const | 38.847 | 6.4745 | TB401 | 40/7 | Complete
2025-02-27 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401 | 44/0 | Complete
2025-02-27 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401 | 61/0 | Complete
2025-02-27 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-27 | 2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401 | 39/0 | Complete
2025-02-27 | 2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401 | 40/0 | Complete
2025-02-28 | 2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401 | 44/0 | Complete
2025-02-28 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401 | 61/0 | Complete
2025-02-28 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-02-28 | 2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401 | 39/0 | Complete
2025-02-28 | 2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401 | 40/0 | Complete
2025-03-01 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401 | 1A/1 | Complete
2025-03-01 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401 | 61/0 | Complete
2025-03-01 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-01 | 2025-03-01 | 2025-03-07 | Sobha Devi | 67.873 | 9.6961 | TB401 | 38/9 | Complete
2025-03-01 | 2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401 | 40/0 | Complete
2025-03-02 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401 | 1A/1 | Complete
2025-03-02 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401 | 61/0 | Complete
2025-03-02 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-02 | 2025-03-01 | 2025-03-07 | Sobha Devi | 67.873 | 9.6961 | TB401 | 38/9 | Complete
2025-03-02 | 2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401 | 40/0 | Complete
2025-03-03 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401 | 1A/1 | Complete
2025-03-03 | 2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401 | 61/0 | Complete
2025-03-03 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-03 | 2025-03-01 | 2025-03-07 | Sobha Devi | 67.873 | 9.6961 | TB401 | 38/9 | Complete
2025-03-03 | 2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401 | 40/0 | Complete
2025-03-04 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401 | 1A/1 | Complete
2025-03-04 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-04 | 2025-03-01 | 2025-03-07 | Sobha Devi | 67.873 | 9.6961 | TB401 | 38/9 | Complete
2025-03-04 | 2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401 | 40/0 | Complete
2025-03-05 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401 | 1A/1 | Complete
2025-03-05 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-05 | 2025-03-01 | 2025-03-07 | Sobha Devi | 67.873 | 9.6961 | TB401 | 38/9 | Complete
2025-03-05 | 2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401 | 40/0 | Complete
2025-03-06 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401 | 1A/1 | Complete
2025-03-06 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-06 | 2025-03-01 | 2025-03-07 | Sobha Devi | 67.873 | 9.6961 | TB401 | 38/9 | Complete
2025-03-06 | 2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401 | 40/0 | Complete
2025-03-07 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401 | 1A/1 | Complete
2025-03-07 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-07 | 2025-03-01 | 2025-03-07 | Sobha Devi | 67.873 | 9.6961 | TB401 | 38/9 | Complete
2025-03-08 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401 | 1A/1 | Complete
2025-03-08 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-08 | 2025-03-08 | 2025-03-11 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/8 | Complete
2025-03-08 | 2025-03-08 | 2025-03-12 | Sunny Const | 37.504 | 7.5008 | TB401 | 40/1 | Complete
2025-03-09 | 2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401 | 1A/1 | Complete
2025-03-09 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-09 | 2025-03-08 | 2025-03-11 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/8 | Complete
2025-03-09 | 2025-03-08 | 2025-03-12 | Sunny Const | 37.504 | 7.5008 | TB401 | 40/1 | Complete
2025-03-10 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-10 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-10 | 2025-03-08 | 2025-03-11 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/8 | Complete
2025-03-10 | 2025-03-08 | 2025-03-12 | Sunny Const | 37.504 | 7.5008 | TB401 | 40/1 | Complete
2025-03-11 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-11 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-11 | 2025-03-08 | 2025-03-11 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/8 | Complete
2025-03-11 | 2025-03-08 | 2025-03-12 | Sunny Const | 37.504 | 7.5008 | TB401 | 40/1 | Complete
2025-03-12 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-12 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-12 | 2025-03-08 | 2025-03-12 | Sunny Const | 37.504 | 7.5008 | TB401 | 40/1 | Complete
2025-03-13 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-13 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-13 | 2025-03-13 | 2025-03-17 | Sobha Devi | 37.504 | 7.5008 | TB401 | 38/7 | Complete
2025-03-13 | 2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401 | 40/4 | Complete
2025-03-14 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-14 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-14 | 2025-03-13 | 2025-03-17 | Sobha Devi | 37.504 | 7.5008 | TB401 | 38/7 | Complete
2025-03-14 | 2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401 | 40/4 | Complete
2025-03-15 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-15 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-15 | 2025-03-13 | 2025-03-17 | Sobha Devi | 37.504 | 7.5008 | TB401 | 38/7 | Complete
2025-03-15 | 2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401 | 40/4 | Complete
2025-03-16 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-16 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-16 | 2025-03-13 | 2025-03-17 | Sobha Devi | 37.504 | 7.5008 | TB401 | 38/7 | Complete
2025-03-16 | 2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401 | 40/4 | Complete
2025-03-17 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-17 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-17 | 2025-03-13 | 2025-03-17 | Sobha Devi | 37.504 | 7.5008 | TB401 | 38/7 | Complete
2025-03-17 | 2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401 | 40/4 | Complete
2025-03-18 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-18 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-18 | 2025-03-18 | 2025-03-21 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/6 | Complete
2025-03-18 | 2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401 | 40/4 | Complete
2025-03-19 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-19 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-19 | 2025-03-18 | 2025-03-21 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/6 | Complete
2025-03-19 | 2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401 | 40/4 | Complete
2025-03-20 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-20 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-20 | 2025-03-18 | 2025-03-21 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/6 | Complete
2025-03-20 | 2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401 | 40/4 | Complete
2025-03-21 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-21 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-21 | 2025-03-18 | 2025-03-21 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/6 | Complete
2025-03-21 | 2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401 | 40/5 | Complete
2025-03-22 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-22 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-22 | 2025-03-22 | 2025-03-25 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/5 | Complete
2025-03-22 | 2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401 | 40/5 | Complete
2025-03-23 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-23 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-23 | 2025-03-22 | 2025-03-25 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/5 | Complete
2025-03-23 | 2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401 | 40/5 | Complete
2025-03-24 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-24 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-24 | 2025-03-22 | 2025-03-25 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/5 | Complete
2025-03-24 | 2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401 | 40/5 | Complete
2025-03-25 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-25 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-25 | 2025-03-22 | 2025-03-25 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/5 | Complete
2025-03-25 | 2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401 | 40/5 | Complete
2025-03-26 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-26 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-26 | 2025-03-26 | 2025-03-29 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/4 | Complete
2025-03-26 | 2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401 | 40/5 | Complete
2025-03-27 | 2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
2025-03-27 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-27 | 2025-03-26 | 2025-03-29 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/4 | Complete
2025-03-27 | 2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401 | 40/5 | Complete
2025-03-28 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-28 | 2025-03-26 | 2025-03-29 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/4 | Complete
2025-03-28 | 2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401 | 40/5 | Complete
2025-03-29 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-29 | 2025-03-26 | 2025-03-29 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/4 | Complete
2025-03-30 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-03-31 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-01 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-02 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-03 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-04 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-05 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-06 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-06 | 2025-04-06 | 2025-04-10 | Sobha Devi | 38.847 | 7.7694 | TB401 | 35/9 | Complete
2025-04-07 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-07 | 2025-04-06 | 2025-04-10 | Sobha Devi | 38.847 | 7.7694 | TB401 | 35/9 | Complete
2025-04-08 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-08 | 2025-04-06 | 2025-04-10 | Sobha Devi | 38.847 | 7.7694 | TB401 | 35/9 | Complete
2025-04-09 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-09 | 2025-04-06 | 2025-04-10 | Sobha Devi | 38.847 | 7.7694 | TB401 | 35/9 | Complete
2025-04-10 | 2025-04-10 | 2025-04-15 | Chinta Devi | 38.847 | 6.4745 | TB401 | 63/5 | Complete
2025-04-10 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-10 | 2025-04-06 | 2025-04-10 | Sobha Devi | 38.847 | 7.7694 | TB401 | 35/9 | Complete
2025-04-11 | 2025-04-10 | 2025-04-15 | Chinta Devi | 38.847 | 6.4745 | TB401 | 63/5 | Complete
2025-04-11 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-11 | 2025-04-11 | 2025-04-14 | Sobha Devi | 37.504 | 9.376 | TB401 | 35/8 | Complete
2025-04-12 | 2025-04-10 | 2025-04-15 | Chinta Devi | 38.847 | 6.4745 | TB401 | 63/5 | Complete
2025-04-12 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-12 | 2025-04-11 | 2025-04-14 | Sobha Devi | 37.504 | 9.376 | TB401 | 35/8 | Complete
2025-04-13 | 2025-04-10 | 2025-04-15 | Chinta Devi | 38.847 | 6.4745 | TB401 | 63/5 | Complete
2025-04-13 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-13 | 2025-04-11 | 2025-04-14 | Sobha Devi | 37.504 | 9.376 | TB401 | 35/8 | Complete
2025-04-14 | 2025-04-10 | 2025-04-15 | Chinta Devi | 38.847 | 6.4745 | TB401 | 63/5 | Complete
2025-04-14 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-14 | 2025-04-11 | 2025-04-14 | Sobha Devi | 37.504 | 9.376 | TB401 | 35/8 | Complete
2025-04-15 | 2025-04-10 | 2025-04-15 | Chinta Devi | 38.847 | 6.4745 | TB401 | 63/5 | Complete
2025-04-15 | 2025-04-15 | 2025-04-20 | Chinta Devi | 38.847 | 6.4745 | TB401 | 63/6 | Complete
2025-04-15 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-15 | 2025-04-15 | 2025-04-20 | Sobha Devi | 38.847 | 6.4745 | TB401 | 35/7 | Complete
2025-04-15 | 2025-04-15 | 2025-04-21 | Sunny Const | 45.413 | 6.4876 | TB401 | 63/1 | Complete
2025-04-16 | 2025-04-15 | 2025-04-20 | Chinta Devi | 38.847 | 6.4745 | TB401 | 63/6 | Complete
2025-04-16 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-16 | 2025-04-15 | 2025-04-20 | Sobha Devi | 38.847 | 6.4745 | TB401 | 35/7 | Complete
2025-04-16 | 2025-04-15 | 2025-04-21 | Sunny Const | 45.413 | 6.4876 | TB401 | 63/1 | Complete
2025-04-17 | 2025-04-15 | 2025-04-20 | Chinta Devi | 38.847 | 6.4745 | TB401 | 63/6 | Complete
2025-04-17 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-17 | 2025-04-15 | 2025-04-20 | Sobha Devi | 38.847 | 6.4745 | TB401 | 35/7 | Complete
2025-04-17 | 2025-04-15 | 2025-04-21 | Sunny Const | 45.413 | 6.4876 | TB401 | 63/1 | Complete
2025-04-18 | 2025-04-15 | 2025-04-20 | Chinta Devi | 38.847 | 6.4745 | TB401 | 63/6 | Complete
2025-04-18 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-18 | 2025-04-15 | 2025-04-20 | Sobha Devi | 38.847 | 6.4745 | TB401 | 35/7 | Complete
2025-04-18 | 2025-04-15 | 2025-04-21 | Sunny Const | 45.413 | 6.4876 | TB401 | 63/1 | Complete
2025-04-19 | 2025-04-15 | 2025-04-20 | Chinta Devi | 38.847 | 6.4745 | TB401 | 63/6 | Complete
2025-04-19 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-19 | 2025-04-15 | 2025-04-20 | Sobha Devi | 38.847 | 6.4745 | TB401 | 35/7 | Complete
2025-04-19 | 2025-04-15 | 2025-04-21 | Sunny Const | 45.413 | 6.4876 | TB401 | 63/1 | Complete
2025-04-20 | 2025-04-15 | 2025-04-20 | Chinta Devi | 38.847 | 6.4745 | TB401 | 63/6 | Complete
2025-04-20 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-20 | 2025-04-15 | 2025-04-20 | Sobha Devi | 38.847 | 6.4745 | TB401 | 35/7 | Complete
2025-04-20 | 2025-04-15 | 2025-04-21 | Sunny Const | 45.413 | 6.4876 | TB401 | 63/1 | Complete
2025-04-21 | 2025-04-21 | 2025-04-26 | Chinta Devi | 37.504 | 6.2507 | TB401 | 63/4 | Complete
2025-04-21 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-21 | 2025-04-21 | 2025-04-26 | Sobha Devi | 47.148 | 7.858 | TB401 | 35/6 | Complete
2025-04-21 | 2025-04-15 | 2025-04-21 | Sunny Const | 45.413 | 6.4876 | TB401 | 63/1 | Complete
2025-04-21 | 2025-04-21 | 2025-04-25 | Sunny Const | 37.504 | 7.5008 | TB401 | 63/2 | Complete
2025-04-22 | 2025-04-21 | 2025-04-26 | Chinta Devi | 37.504 | 6.2507 | TB401 | 63/4 | Complete
2025-04-22 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-22 | 2025-04-21 | 2025-04-26 | Sobha Devi | 47.148 | 7.858 | TB401 | 35/6 | Complete
2025-04-22 | 2025-04-21 | 2025-04-25 | Sunny Const | 37.504 | 7.5008 | TB401 | 63/2 | Complete
2025-04-23 | 2025-04-21 | 2025-04-26 | Chinta Devi | 37.504 | 6.2507 | TB401 | 63/4 | Complete
2025-04-23 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-23 | 2025-04-21 | 2025-04-26 | Sobha Devi | 47.148 | 7.858 | TB401 | 35/6 | Complete
2025-04-23 | 2025-04-21 | 2025-04-25 | Sunny Const | 37.504 | 7.5008 | TB401 | 63/2 | Complete
2025-04-24 | 2025-04-21 | 2025-04-26 | Chinta Devi | 37.504 | 6.2507 | TB401 | 63/4 | Complete
2025-04-24 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-04-24 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-24 | 2025-04-21 | 2025-04-26 | Sobha Devi | 47.148 | 7.858 | TB401 | 35/6 | Complete
2025-04-24 | 2025-04-21 | 2025-04-25 | Sunny Const | 37.504 | 7.5008 | TB401 | 63/2 | Complete
2025-04-25 | 2025-04-21 | 2025-04-26 | Chinta Devi | 37.504 | 6.2507 | TB401 | 63/4 | Complete
2025-04-25 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-04-25 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-25 | 2025-04-21 | 2025-04-26 | Sobha Devi | 47.148 | 7.858 | TB401 | 35/6 | Complete
2025-04-25 | 2025-04-21 | 2025-04-25 | Sunny Const | 37.504 | 7.5008 | TB401 | 63/2 | Complete
2025-04-26 | 2025-04-21 | 2025-04-26 | Chinta Devi | 37.504 | 6.2507 | TB401 | 63/4 | Complete
2025-04-26 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-04-26 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-26 | 2025-04-21 | 2025-04-26 | Sobha Devi | 47.148 | 7.858 | TB401 | 35/6 | Complete
2025-04-26 | 2025-04-26 | 2025-04-30 | Sobha Devi | 37.504 | 7.5008 | TB401 | 35/5 | Complete
2025-04-26 | 2025-04-26 | 2025-04-30 | Sunny Const | 38.847 | 7.7694 | TB401 | 63/3 | Complete
2025-04-27 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-04-27 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-27 | 2025-04-26 | 2025-04-30 | Sobha Devi | 37.504 | 7.5008 | TB401 | 35/5 | Complete
2025-04-27 | 2025-04-26 | 2025-04-30 | Sunny Const | 38.847 | 7.7694 | TB401 | 63/3 | Complete
2025-04-28 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-04-28 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-28 | 2025-04-26 | 2025-04-30 | Sobha Devi | 37.504 | 7.5008 | TB401 | 35/5 | Complete
2025-04-28 | 2025-04-26 | 2025-04-30 | Sunny Const | 38.847 | 7.7694 | TB401 | 63/3 | Complete
2025-04-29 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401 | 34/4 | Complete
2025-04-29 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-04-29 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-29 | 2025-04-26 | 2025-04-30 | Sobha Devi | 37.504 | 7.5008 | TB401 | 35/5 | Complete
2025-04-29 | 2025-04-26 | 2025-04-30 | Sunny Const | 38.847 | 7.7694 | TB401 | 63/3 | Complete
2025-04-30 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401 | 34/4 | Complete
2025-04-30 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-04-30 | 2025-04-30 | 2025-05-06 | Satyam Manish | 45.413 | 6.4876 | TB401 | 44/5 | Complete
2025-04-30 | 2025-04-30 | 2025-05-06 | Satyam Nitish | 38.847 | 5.5496 | TB401 | 39/3 | Complete
2025-04-30 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-04-30 | 2025-04-26 | 2025-04-30 | Sobha Devi | 37.504 | 7.5008 | TB401 | 35/5 | Complete
2025-04-30 | 2025-04-26 | 2025-04-30 | Sunny Const | 38.847 | 7.7694 | TB401 | 63/3 | Complete
2025-04-30 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401 | 62/0 | Complete
2025-05-01 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401 | 34/4 | Complete
2025-05-01 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-01 | 2025-04-30 | 2025-05-06 | Satyam Manish | 45.413 | 6.4876 | TB401 | 44/5 | Complete
2025-05-01 | 2025-04-30 | 2025-05-06 | Satyam Nitish | 38.847 | 5.5496 | TB401 | 39/3 | Complete
2025-05-01 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-01 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401 | 62/0 | Complete
2025-05-02 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401 | 34/4 | Complete
2025-05-02 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-02 | 2025-04-30 | 2025-05-06 | Satyam Manish | 45.413 | 6.4876 | TB401 | 44/5 | Complete
2025-05-02 | 2025-04-30 | 2025-05-06 | Satyam Nitish | 38.847 | 5.5496 | TB401 | 39/3 | Complete
2025-05-02 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-02 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401 | 62/0 | Complete
2025-05-03 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401 | 34/4 | Complete
2025-05-03 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-03 | 2025-04-30 | 2025-05-06 | Satyam Manish | 45.413 | 6.4876 | TB401 | 44/5 | Complete
2025-05-03 | 2025-04-30 | 2025-05-06 | Satyam Nitish | 38.847 | 5.5496 | TB401 | 39/3 | Complete
2025-05-03 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-03 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401 | 62/0 | Complete
2025-05-04 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-04 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401 | 34/4 | Complete
2025-05-04 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-04 | 2025-04-30 | 2025-05-06 | Satyam Manish | 45.413 | 6.4876 | TB401 | 44/5 | Complete
2025-05-04 | 2025-04-30 | 2025-05-06 | Satyam Nitish | 38.847 | 5.5496 | TB401 | 39/3 | Complete
2025-05-04 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-04 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401 | 62/0 | Complete
2025-05-05 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-05 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401 | 34/4 | Complete
2025-05-05 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-05 | 2025-04-30 | 2025-05-06 | Satyam Manish | 45.413 | 6.4876 | TB401 | 44/5 | Complete
2025-05-05 | 2025-04-30 | 2025-05-06 | Satyam Nitish | 38.847 | 5.5496 | TB401 | 39/3 | Complete
2025-05-05 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-05 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401 | 62/0 | Complete
2025-05-06 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-06 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401 | 34/4 | Complete
2025-05-06 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-06 | 2025-04-30 | 2025-05-06 | Satyam Manish | 45.413 | 6.4876 | TB401 | 44/5 | Complete
2025-05-06 | 2025-04-30 | 2025-05-06 | Satyam Nitish | 38.847 | 5.5496 | TB401 | 39/3 | Complete
2025-05-06 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-06 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401 | 62/0 | Complete
2025-05-07 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-07 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401 | 34/4 | Complete
2025-05-07 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-07 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-07 | 2025-05-07 | 2025-05-11 | Satyam Nitish | 37.504 | 7.5008 | TB401 | 39/2 | Complete
2025-05-07 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-07 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401 | 62/0 | Complete
2025-05-08 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-08 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401 | 34/4 | Complete
2025-05-08 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-08 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-08 | 2025-05-07 | 2025-05-11 | Satyam Nitish | 37.504 | 7.5008 | TB401 | 39/2 | Complete
2025-05-08 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-08 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401 | 62/0 | Complete
2025-05-09 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-09 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401 | 34/4 | Complete
2025-05-09 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-09 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-09 | 2025-05-07 | 2025-05-11 | Satyam Nitish | 37.504 | 7.5008 | TB401 | 39/2 | Complete
2025-05-09 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-09 | 2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401 | 62/0 | Complete
2025-05-10 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-10 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401 | 34/4 | Complete
2025-05-10 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-10 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-10 | 2025-05-07 | 2025-05-11 | Satyam Nitish | 37.504 | 7.5008 | TB401 | 39/2 | Complete
2025-05-10 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-11 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-11 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401 | 34/4 | Complete
2025-05-11 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-11 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-11 | 2025-05-07 | 2025-05-11 | Satyam Nitish | 37.504 | 7.5008 | TB401 | 39/2 | Complete
2025-05-11 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-12 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-12 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401 | 34/4 | Complete
2025-05-12 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-12 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-12 | 2025-05-12 | 2025-05-17 | Satyam Nitish | 37.504 | 6.2507 | TB401 | 39/4 | Complete
2025-05-12 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-12 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401 | 64/9 | Complete
2025-05-12 | 2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401 | 63/0 | Complete
2025-05-13 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-13 | 2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401 | 34/4 | Complete
2025-05-13 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-13 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-13 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401 | 35/0 | Complete
2025-05-13 | 2025-05-12 | 2025-05-17 | Satyam Nitish | 37.504 | 6.2507 | TB401 | 39/4 | Complete
2025-05-13 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-13 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401 | 64/9 | Complete
2025-05-13 | 2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401 | 63/0 | Complete
2025-05-14 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-14 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-14 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-14 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401 | 35/0 | Complete
2025-05-14 | 2025-05-12 | 2025-05-17 | Satyam Nitish | 37.504 | 6.2507 | TB401 | 39/4 | Complete
2025-05-14 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-14 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401 | 64/9 | Complete
2025-05-14 | 2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401 | 63/0 | Complete
2025-05-15 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-15 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-15 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-15 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401 | 35/0 | Complete
2025-05-15 | 2025-05-12 | 2025-05-17 | Satyam Nitish | 37.504 | 6.2507 | TB401 | 39/4 | Complete
2025-05-15 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-15 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401 | 64/9 | Complete
2025-05-15 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/6 | Complete
2025-05-15 | 2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401 | 63/0 | Complete
2025-05-16 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-16 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-05-16 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-16 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-16 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401 | 35/0 | Complete
2025-05-16 | 2025-05-12 | 2025-05-17 | Satyam Nitish | 37.504 | 6.2507 | TB401 | 39/4 | Complete
2025-05-16 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-16 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401 | 64/9 | Complete
2025-05-16 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/6 | Complete
2025-05-16 | 2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401 | 63/0 | Complete
2025-05-17 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-17 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-05-17 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-17 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-17 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401 | 35/0 | Complete
2025-05-17 | 2025-05-12 | 2025-05-17 | Satyam Nitish | 37.504 | 6.2507 | TB401 | 39/4 | Complete
2025-05-17 | 2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401 | 37/1 | Complete
2025-05-17 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-17 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401 | 64/9 | Complete
2025-05-17 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/6 | Complete
2025-05-17 | 2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401 | 63/0 | Complete
2025-05-18 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-18 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-05-18 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-18 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-18 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401 | 35/0 | Complete
2025-05-18 | 2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401 | 37/1 | Complete
2025-05-18 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-18 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401 | 64/9 | Complete
2025-05-18 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/6 | Complete
2025-05-18 | 2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401 | 63/0 | Complete
2025-05-19 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-19 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-05-19 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-19 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-19 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401 | 35/0 | Complete
2025-05-19 | 2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401 | 37/1 | Complete
2025-05-19 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-19 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401 | 64/9 | Complete
2025-05-19 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/6 | Complete
2025-05-19 | 2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401 | 63/0 | Complete
2025-05-20 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-20 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-05-20 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-05-20 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-20 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-20 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401 | 35/0 | Complete
2025-05-20 | 2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401 | 37/1 | Complete
2025-05-20 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-20 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401 | 64/9 | Complete
2025-05-20 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/6 | Complete
2025-05-21 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-21 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-05-21 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-05-21 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-21 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-21 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401 | 35/0 | Complete
2025-05-21 | 2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401 | 37/1 | Complete
2025-05-21 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-21 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401 | 64/9 | Complete
2025-05-21 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/6 | Complete
2025-05-22 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-22 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-05-22 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-05-22 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-22 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-22 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401 | 35/0 | Complete
2025-05-22 | 2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401 | 37/1 | Complete
2025-05-22 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-22 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401 | 64/9 | Complete
2025-05-22 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/6 | Complete
2025-05-23 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-23 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-05-23 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-05-23 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-23 | 2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-23 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401 | 35/0 | Complete
2025-05-23 | 2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401 | 37/1 | Complete
2025-05-23 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-23 | 2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401 | 64/9 | Complete
2025-05-23 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/6 | Complete
2025-05-24 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-24 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-05-24 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-05-24 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-24 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401 | 46/1 | Complete
2025-05-24 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401 | 35/0 | Complete
2025-05-24 | 2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401 | 37/1 | Complete
2025-05-24 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-24 | 2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401 | 64/8 | Complete
2025-05-24 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/6 | Complete
2025-05-25 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-25 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-05-25 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-05-25 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-25 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401 | 46/1 | Complete
2025-05-25 | 2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401 | 35/0 | Complete
2025-05-25 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-25 | 2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401 | 64/8 | Complete
2025-05-25 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/6 | Complete
2025-05-26 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-26 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-05-26 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-05-26 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-26 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401 | 46/1 | Complete
2025-05-26 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-05-26 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-26 | 2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401 | 64/8 | Complete
2025-05-26 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/6 | Complete
2025-05-27 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-27 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-05-27 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-05-27 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-27 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401 | 46/1 | Complete
2025-05-27 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401 | 34/6 | Complete
2025-05-27 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-05-27 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-27 | 2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401 | 64/8 | Complete
2025-05-27 | 2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/6 | Complete
2025-05-28 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-28 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-05-28 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-05-28 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401 | 64/0 | Complete
2025-05-28 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-28 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401 | 46/1 | Complete
2025-05-28 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401 | 34/6 | Complete
2025-05-28 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-05-28 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-28 | 2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401 | 64/8 | Complete
2025-05-29 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-29 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-05-29 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-05-29 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401 | 64/0 | Complete
2025-05-29 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-29 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401 | 46/1 | Complete
2025-05-29 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401 | 34/6 | Complete
2025-05-29 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-05-29 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-29 | 2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401 | 64/8 | Complete
2025-05-29 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401 | 64/5 | Complete
2025-05-30 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-30 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-05-30 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-05-30 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401 | 64/0 | Complete
2025-05-30 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-30 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401 | 46/1 | Complete
2025-05-30 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401 | 34/6 | Complete
2025-05-30 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-05-30 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-05-30 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-30 | 2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401 | 64/8 | Complete
2025-05-30 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401 | 64/5 | Complete
2025-05-31 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-31 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-05-31 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-05-31 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401 | 64/0 | Complete
2025-05-31 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-05-31 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401 | 46/1 | Complete
2025-05-31 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401 | 34/6 | Complete
2025-05-31 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-05-31 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-05-31 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-05-31 | 2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401 | 64/8 | Complete
2025-05-31 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401 | 64/5 | Complete
2025-06-01 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-06-01 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-06-01 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-01 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401 | 64/0 | Complete
2025-06-01 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-01 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401 | 46/1 | Complete
2025-06-01 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401 | 34/6 | Complete
2025-06-01 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-06-01 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-06-01 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-06-01 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401 | 64/5 | Complete
2025-06-02 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-06-02 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-06-02 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-02 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401 | 64/0 | Complete
2025-06-02 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-02 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401 | 46/1 | Complete
2025-06-02 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401 | 34/6 | Complete
2025-06-02 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-06-02 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-06-02 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-06-02 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401 | 64/5 | Complete
2025-06-03 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-06-03 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-06-03 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-03 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401 | 64/0 | Complete
2025-06-03 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-03 | 2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401 | 46/1 | Complete
2025-06-03 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401 | 34/6 | Complete
2025-06-03 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-06-03 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-06-03 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-06-03 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401 | 64/5 | Complete
2025-06-04 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-06-04 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-06-04 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-04 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401 | 64/0 | Complete
2025-06-04 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-04 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401 | 34/6 | Complete
2025-06-04 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-06-04 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-06-04 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-06-04 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401 | 64/5 | Complete
2025-06-05 | 2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-06-05 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-06-05 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-05 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401 | 64/0 | Complete
2025-06-05 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-05 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401 | 34/6 | Complete
2025-06-05 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-06-05 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-06-05 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-06-05 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401 | 64/5 | Complete
2025-06-06 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-06-06 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-06 | 2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401 | 64/0 | Complete
2025-06-06 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-06 | 2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401 | 34/6 | Complete
2025-06-06 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-06-06 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-06-06 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-06-06 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401 | 64/5 | Complete
2025-06-07 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-06-07 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-07 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401 | 64/1 | Complete
2025-06-07 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-07 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-06-07 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-06-07 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-06-07 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401 | 64/5 | Complete
2025-06-08 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-06-08 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-08 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401 | 64/1 | Complete
2025-06-08 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-08 | 2025-06-08 | 2025-06-13 | Satyam Manish | 37.504 | 6.2507 | TB401 | 40/8 | Complete
2025-06-08 | 2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/1 | Complete
2025-06-08 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-06-08 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-06-08 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-06-08 | 2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401 | 64/5 | Complete
2025-06-09 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-06-09 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-09 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401 | 64/1 | Complete
2025-06-09 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401 | 39/5 | Complete
2025-06-09 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-09 | 2025-06-08 | 2025-06-13 | Satyam Manish | 37.504 | 6.2507 | TB401 | 40/8 | Complete
2025-06-09 | 2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/1 | Complete
2025-06-09 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-06-09 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-06-09 | 2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-06-10 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-06-10 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-10 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401 | 64/1 | Complete
2025-06-10 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401 | 39/5 | Complete
2025-06-10 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-10 | 2025-06-08 | 2025-06-13 | Satyam Manish | 37.504 | 6.2507 | TB401 | 40/8 | Complete
2025-06-10 | 2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/1 | Complete
2025-06-10 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-06-10 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-06-10 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401 | 65/0 | Complete
2025-06-10 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/7 | Complete
2025-06-11 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-06-11 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-11 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401 | 64/1 | Complete
2025-06-11 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401 | 39/5 | Complete
2025-06-11 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-11 | 2025-06-08 | 2025-06-13 | Satyam Manish | 37.504 | 6.2507 | TB401 | 40/8 | Complete
2025-06-11 | 2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/1 | Complete
2025-06-11 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-06-11 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-06-11 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401 | 65/0 | Complete
2025-06-11 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/7 | Complete
2025-06-12 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-06-12 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-12 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401 | 64/1 | Complete
2025-06-12 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401 | 39/5 | Complete
2025-06-12 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-12 | 2025-06-08 | 2025-06-13 | Satyam Manish | 37.504 | 6.2507 | TB401 | 40/8 | Complete
2025-06-12 | 2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/1 | Complete
2025-06-12 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-06-12 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-06-12 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401 | 65/0 | Complete
2025-06-12 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/7 | Complete
2025-06-13 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-06-13 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-13 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401 | 64/1 | Complete
2025-06-13 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401 | 39/5 | Complete
2025-06-13 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-13 | 2025-06-08 | 2025-06-13 | Satyam Manish | 37.504 | 6.2507 | TB401 | 40/8 | Complete
2025-06-13 | 2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/1 | Complete
2025-06-13 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-06-13 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-06-13 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401 | 65/0 | Complete
2025-06-13 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/7 | Complete
2025-06-14 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-06-14 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-14 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401 | 64/1 | Complete
2025-06-14 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401 | 39/5 | Complete
2025-06-14 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-14 | 2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/1 | Complete
2025-06-14 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-06-14 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-06-14 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401 | 65/0 | Complete
2025-06-14 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/7 | Complete
2025-06-15 | 2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-06-15 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-15 | 2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401 | 64/1 | Complete
2025-06-15 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401 | 39/5 | Complete
2025-06-15 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-15 | 2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/1 | Complete
2025-06-15 | 2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-06-15 | 2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-06-15 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401 | 65/0 | Complete
2025-06-15 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/7 | Complete
2025-06-16 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-16 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401 | 39/5 | Complete
2025-06-16 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-16 | 2025-06-16 | 2025-06-18 | Satyam Manish | 37.504 | 12.5013 | TB401 | 40/9 | Complete
2025-06-16 | 2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/2 | Complete
2025-06-16 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401 | 65/0 | Complete
2025-06-16 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/7 | Complete
2025-06-17 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-17 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401 | 39/5 | Complete
2025-06-17 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-17 | 2025-06-16 | 2025-06-18 | Satyam Manish | 37.504 | 12.5013 | TB401 | 40/9 | Complete
2025-06-17 | 2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/2 | Complete
2025-06-17 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401 | 37/0 | Complete
2025-06-17 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401 | 65/0 | Complete
2025-06-17 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/7 | Complete
2025-06-18 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-18 | 2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401 | 39/5 | Complete
2025-06-18 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401 | 24/5 | Complete
2025-06-18 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-18 | 2025-06-16 | 2025-06-18 | Satyam Manish | 37.504 | 12.5013 | TB401 | 40/9 | Complete
2025-06-18 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401 | 46/0 | Complete
2025-06-18 | 2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/2 | Complete
2025-06-18 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401 | 37/0 | Complete
2025-06-18 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401 | 65/0 | Complete
2025-06-18 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/7 | Complete
2025-06-19 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-19 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401 | 24/5 | Complete
2025-06-19 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-19 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401 | 46/0 | Complete
2025-06-19 | 2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/2 | Complete
2025-06-19 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401 | 37/0 | Complete
2025-06-19 | 2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401 | 65/0 | Complete
2025-06-19 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/7 | Complete
2025-06-20 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-20 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401 | 24/5 | Complete
2025-06-20 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-20 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401 | 46/0 | Complete
2025-06-20 | 2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/2 | Complete
2025-06-20 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401 | 37/0 | Complete
2025-06-20 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/7 | Complete
2025-06-21 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-21 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401 | 24/5 | Complete
2025-06-21 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-21 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401 | 46/0 | Complete
2025-06-21 | 2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/2 | Complete
2025-06-21 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401 | 37/0 | Complete
2025-06-21 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/7 | Complete
2025-06-22 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-22 | 2025-06-22 | 2025-06-28 | Jwala Singh 2 | 37.504 | 5.3577 | TB401 | 39/6 | Complete
2025-06-22 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401 | 24/5 | Complete
2025-06-22 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-22 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401 | 46/0 | Complete
2025-06-22 | 2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/2 | Complete
2025-06-22 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401 | 37/0 | Complete
2025-06-22 | 2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/7 | Complete
2025-06-23 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-23 | 2025-06-23 | 2025-06-28 | Jwala Singh 1 | 37.504 | 6.2507 | TB401 | 64/2 | Complete
2025-06-23 | 2025-06-22 | 2025-06-28 | Jwala Singh 2 | 37.504 | 5.3577 | TB401 | 39/6 | Complete
2025-06-23 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401 | 24/5 | Complete
2025-06-23 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401 | 15/7 | Complete
2025-06-23 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-23 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401 | 46/0 | Complete
2025-06-23 | 2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/2 | Complete
2025-06-23 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401 | 37/0 | Complete
2025-06-23 | 2025-06-23 | 2025-06-28 | Satyam Trivedi | 37.504 | 6.2507 | TB401 | 65/2 | Complete
2025-06-23 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-06-24 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401 | 12/0 | Complete
2025-06-24 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-24 | 2025-06-23 | 2025-06-28 | Jwala Singh 1 | 37.504 | 6.2507 | TB401 | 64/2 | Complete
2025-06-24 | 2025-06-22 | 2025-06-28 | Jwala Singh 2 | 37.504 | 5.3577 | TB401 | 39/6 | Complete
2025-06-24 | 2025-06-24 | 2025-06-27 | Jwala Singh 3 | 38.847 | 9.7118 | TB401 | 8/9 | Complete
2025-06-24 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401 | 24/5 | Complete
2025-06-24 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401 | 15/7 | Complete
2025-06-24 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-24 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401 | 46/0 | Complete
2025-06-24 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401 | 37/0 | Complete
2025-06-24 | 2025-06-23 | 2025-06-28 | Satyam Trivedi | 37.504 | 6.2507 | TB401 | 65/2 | Complete
2025-06-24 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-06-25 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401 | 12/0 | Complete
2025-06-25 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-25 | 2025-06-23 | 2025-06-28 | Jwala Singh 1 | 37.504 | 6.2507 | TB401 | 64/2 | Complete
2025-06-25 | 2025-06-22 | 2025-06-28 | Jwala Singh 2 | 37.504 | 5.3577 | TB401 | 39/6 | Complete
2025-06-25 | 2025-06-24 | 2025-06-27 | Jwala Singh 3 | 38.847 | 9.7118 | TB401 | 8/9 | Complete
2025-06-25 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401 | 24/5 | Complete
2025-06-25 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401 | 15/7 | Complete
2025-06-25 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-25 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401 | 46/0 | Complete
2025-06-25 | 2025-06-25 | 2025-06-30 | Satyam Mondal | 37.504 | 6.2507 | TB401 | 35/3 | Complete
2025-06-25 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401 | 37/0 | Complete
2025-06-25 | 2025-06-23 | 2025-06-28 | Satyam Trivedi | 37.504 | 6.2507 | TB401 | 65/2 | Complete
2025-06-25 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-06-26 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401 | 12/0 | Complete
2025-06-26 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-26 | 2025-06-23 | 2025-06-28 | Jwala Singh 1 | 37.504 | 6.2507 | TB401 | 64/2 | Complete
2025-06-26 | 2025-06-22 | 2025-06-28 | Jwala Singh 2 | 37.504 | 5.3577 | TB401 | 39/6 | Complete
2025-06-26 | 2025-06-24 | 2025-06-27 | Jwala Singh 3 | 38.847 | 9.7118 | TB401 | 8/9 | Complete
2025-06-26 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401 | 24/5 | Complete
2025-06-26 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401 | 15/7 | Complete
2025-06-26 | 2025-06-26 | 2025-06-30 | Pusplata 4 | 38.847 | 7.7694 | TB401 | 25/5 | Complete
2025-06-26 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-26 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401 | 46/0 | Complete
2025-06-26 | 2025-06-25 | 2025-06-30 | Satyam Mondal | 37.504 | 6.2507 | TB401 | 35/3 | Complete
2025-06-26 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401 | 37/0 | Complete
2025-06-26 | 2025-06-23 | 2025-06-28 | Satyam Trivedi | 37.504 | 6.2507 | TB401 | 65/2 | Complete
2025-06-26 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-06-27 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401 | 12/0 | Complete
2025-06-27 | 2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-27 | 2025-06-23 | 2025-06-28 | Jwala Singh 1 | 37.504 | 6.2507 | TB401 | 64/2 | Complete
2025-06-27 | 2025-06-22 | 2025-06-28 | Jwala Singh 2 | 37.504 | 5.3577 | TB401 | 39/6 | Complete
2025-06-27 | 2025-06-24 | 2025-06-27 | Jwala Singh 3 | 38.847 | 9.7118 | TB401 | 8/9 | Complete
2025-06-27 | 2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401 | 24/5 | Complete
2025-06-27 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401 | 15/7 | Complete
2025-06-27 | 2025-06-27 | 2025-06-30 | Pusplata 1 | 45.413 | 11.3532 | TB401 | 25/11 | Complete
2025-06-27 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401 | 23/6 | Complete
2025-06-27 | 2025-06-26 | 2025-06-30 | Pusplata 4 | 38.847 | 7.7694 | TB401 | 25/5 | Complete
2025-06-27 | 2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401 | 21/2 | Complete
2025-06-27 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-27 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401 | 46/0 | Complete
2025-06-27 | 2025-06-25 | 2025-06-30 | Satyam Mondal | 37.504 | 6.2507 | TB401 | 35/3 | Complete
2025-06-27 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401 | 37/0 | Complete
2025-06-27 | 2025-06-23 | 2025-06-28 | Satyam Trivedi | 37.504 | 6.2507 | TB401 | 65/2 | Complete
2025-06-27 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-06-28 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401 | 12/0 | Complete
2025-06-28 | 2025-06-23 | 2025-06-28 | Jwala Singh 1 | 37.504 | 6.2507 | TB401 | 64/2 | Complete
2025-06-28 | 2025-06-22 | 2025-06-28 | Jwala Singh 2 | 37.504 | 5.3577 | TB401 | 39/6 | Complete
2025-06-28 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401 | 15/7 | Complete
2025-06-28 | 2025-06-27 | 2025-06-30 | Pusplata 1 | 45.413 | 11.3532 | TB401 | 25/11 | Complete
2025-06-28 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401 | 23/6 | Complete
2025-06-28 | 2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401 | 24/2 | Complete
2025-06-28 | 2025-06-26 | 2025-06-30 | Pusplata 4 | 38.847 | 7.7694 | TB401 | 25/5 | Complete
2025-06-28 | 2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401 | 21/2 | Complete
2025-06-28 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401 | 22/6 | Complete
2025-06-28 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-28 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401 | 46/0 | Complete
2025-06-28 | 2025-06-25 | 2025-06-30 | Satyam Mondal | 37.504 | 6.2507 | TB401 | 35/3 | Complete
2025-06-28 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401 | 37/0 | Complete
2025-06-28 | 2025-06-23 | 2025-06-28 | Satyam Trivedi | 37.504 | 6.2507 | TB401 | 65/2 | Complete
2025-06-28 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-06-29 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401 | 12/0 | Complete
2025-06-29 | 2025-06-29 | 2025-07-02 | Poonam | 37.504 | 9.376 | TB401 | 24/4 | Complete
2025-06-29 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401 | 15/7 | Complete
2025-06-29 | 2025-06-27 | 2025-06-30 | Pusplata 1 | 45.413 | 11.3532 | TB401 | 25/11 | Complete
2025-06-29 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401 | 23/6 | Complete
2025-06-29 | 2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401 | 24/2 | Complete
2025-06-29 | 2025-06-26 | 2025-06-30 | Pusplata 4 | 38.847 | 7.7694 | TB401 | 25/5 | Complete
2025-06-29 | 2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401 | 21/2 | Complete
2025-06-29 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401 | 22/6 | Complete
2025-06-29 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-29 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401 | 46/0 | Complete
2025-06-29 | 2025-06-25 | 2025-06-30 | Satyam Mondal | 37.504 | 6.2507 | TB401 | 35/3 | Complete
2025-06-29 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401 | 37/0 | Complete
2025-06-29 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-06-30 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401 | 12/0 | Complete
2025-06-30 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401 | 29/2 | Complete
2025-06-30 | 2025-06-30 | 2025-07-03 | Jwala Singh 2 | 37.504 | 9.376 | TB401 | 39/7 | Complete
2025-06-30 | 2025-06-29 | 2025-07-02 | Poonam | 37.504 | 9.376 | TB401 | 24/4 | Complete
2025-06-30 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401 | 15/7 | Complete
2025-06-30 | 2025-06-27 | 2025-06-30 | Pusplata 1 | 45.413 | 11.3532 | TB401 | 25/11 | Complete
2025-06-30 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401 | 23/6 | Complete
2025-06-30 | 2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401 | 24/2 | Complete
2025-06-30 | 2025-06-26 | 2025-06-30 | Pusplata 4 | 38.847 | 7.7694 | TB401 | 25/5 | Complete
2025-06-30 | 2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401 | 21/2 | Complete
2025-06-30 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401 | 22/6 | Complete
2025-06-30 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-06-30 | 2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401 | 46/0 | Complete
2025-06-30 | 2025-06-25 | 2025-06-30 | Satyam Mondal | 37.504 | 6.2507 | TB401 | 35/3 | Complete
2025-06-30 | 2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401 | 37/0 | Complete
2025-06-30 | 2025-06-30 | 2025-07-05 | Satyam Trivedi | 38.847 | 6.4745 | TB401 | 65/1 | Complete
2025-06-30 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-07-01 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401 | 12/0 | Complete
2025-07-01 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401 | 29/2 | Complete
2025-07-01 | 2025-06-30 | 2025-07-03 | Jwala Singh 2 | 37.504 | 9.376 | TB401 | 39/7 | Complete
2025-07-01 | 2025-06-29 | 2025-07-02 | Poonam | 37.504 | 9.376 | TB401 | 24/4 | Complete
2025-07-01 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401 | 15/7 | Complete
2025-07-01 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401 | 23/6 | Complete
2025-07-01 | 2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401 | 24/2 | Complete
2025-07-01 | 2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401 | 21/2 | Complete
2025-07-01 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401 | 22/6 | Complete
2025-07-01 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-01 | 2025-07-01 | 2025-07-06 | Satyam Mondal | 38.847 | 6.4745 | TB401 | 35/4 | Complete
2025-07-01 | 2025-06-30 | 2025-07-05 | Satyam Trivedi | 38.847 | 6.4745 | TB401 | 65/1 | Complete
2025-07-01 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-07-02 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401 | 12/0 | Complete
2025-07-02 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401 | 29/2 | Complete
2025-07-02 | 2025-06-30 | 2025-07-03 | Jwala Singh 2 | 37.504 | 9.376 | TB401 | 39/7 | Complete
2025-07-02 | 2025-07-02 | 2025-07-06 | Jwala Singh 3 | 38.847 | 7.7694 | TB401 | 8/10 | Complete
2025-07-02 | 2025-06-29 | 2025-07-02 | Poonam | 37.504 | 9.376 | TB401 | 24/4 | Complete
2025-07-02 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401 | 15/7 | Complete
2025-07-02 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401 | 23/6 | Complete
2025-07-02 | 2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401 | 24/2 | Complete
2025-07-02 | 2025-07-02 | 2025-07-06 | Pusplata 4 | 38.847 | 7.7694 | TB401 | 25/6 | Complete
2025-07-02 | 2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401 | 21/2 | Complete
2025-07-02 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401 | 22/6 | Complete
2025-07-02 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-02 | 2025-07-01 | 2025-07-06 | Satyam Mondal | 38.847 | 6.4745 | TB401 | 35/4 | Complete
2025-07-02 | 2025-06-30 | 2025-07-05 | Satyam Trivedi | 38.847 | 6.4745 | TB401 | 65/1 | Complete
2025-07-02 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-07-03 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401 | 12/0 | Complete
2025-07-03 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401 | 29/2 | Complete
2025-07-03 | 2025-06-30 | 2025-07-03 | Jwala Singh 2 | 37.504 | 9.376 | TB401 | 39/7 | Complete
2025-07-03 | 2025-07-02 | 2025-07-06 | Jwala Singh 3 | 38.847 | 7.7694 | TB401 | 8/10 | Complete
2025-07-03 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401 | 15/7 | Complete
2025-07-03 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401 | 23/6 | Complete
2025-07-03 | 2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401 | 24/2 | Complete
2025-07-03 | 2025-07-02 | 2025-07-06 | Pusplata 4 | 38.847 | 7.7694 | TB401 | 25/6 | Complete
2025-07-03 | 2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401 | 21/2 | Complete
2025-07-03 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401 | 22/6 | Complete
2025-07-03 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401 | 22/3 | Complete
2025-07-03 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-03 | 2025-07-01 | 2025-07-06 | Satyam Mondal | 38.847 | 6.4745 | TB401 | 35/4 | Complete
2025-07-03 | 2025-06-30 | 2025-07-05 | Satyam Trivedi | 38.847 | 6.4745 | TB401 | 65/1 | Complete
2025-07-03 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-07-04 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401 | 12/0 | Complete
2025-07-04 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401 | 29/2 | Complete
2025-07-04 | 2025-07-02 | 2025-07-06 | Jwala Singh 3 | 38.847 | 7.7694 | TB401 | 8/10 | Complete
2025-07-04 | 2025-07-04 | 2025-07-07 | Poonam | 37.504 | 9.376 | TB401 | 24/3 | Complete
2025-07-04 | 2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401 | 15/7 | Complete
2025-07-04 | 2025-07-04 | 2025-07-09 | Pusplata 1 | 37.504 | 6.2507 | TB401 | 25/10 | Complete
2025-07-04 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401 | 23/6 | Complete
2025-07-04 | 2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401 | 24/2 | Complete
2025-07-04 | 2025-07-02 | 2025-07-06 | Pusplata 4 | 38.847 | 7.7694 | TB401 | 25/6 | Complete
2025-07-04 | 2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401 | 21/2 | Complete
2025-07-04 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401 | 22/6 | Complete
2025-07-04 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401 | 22/3 | Complete
2025-07-04 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-04 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401 | 28/9 | Complete
2025-07-04 | 2025-07-04 | 2025-07-09 | Satyam Manish | 60.096 | 10.016 | TB401 | 33/0 | Complete
2025-07-04 | 2025-07-01 | 2025-07-06 | Satyam Mondal | 38.847 | 6.4745 | TB401 | 35/4 | Complete
2025-07-04 | 2025-07-04 | 2025-07-08 | Satyam Nitish | 45.413 | 9.0826 | TB401 | 33/6 | Complete
2025-07-04 | 2025-06-30 | 2025-07-05 | Satyam Trivedi | 38.847 | 6.4745 | TB401 | 65/1 | Complete
2025-07-04 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-07-05 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401 | 12/0 | Complete
2025-07-05 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401 | 29/2 | Complete
2025-07-05 | 2025-07-02 | 2025-07-06 | Jwala Singh 3 | 38.847 | 7.7694 | TB401 | 8/10 | Complete
2025-07-05 | 2025-07-04 | 2025-07-07 | Poonam | 37.504 | 9.376 | TB401 | 24/3 | Complete
2025-07-05 | 2025-07-05 | 2025-07-11 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401 | 15/5 | Complete
2025-07-05 | 2025-07-04 | 2025-07-09 | Pusplata 1 | 37.504 | 6.2507 | TB401 | 25/10 | Complete
2025-07-05 | 2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401 | 23/6 | Complete
2025-07-05 | 2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401 | 24/2 | Complete
2025-07-05 | 2025-07-02 | 2025-07-06 | Pusplata 4 | 38.847 | 7.7694 | TB401 | 25/6 | Complete
2025-07-05 | 2025-07-05 | 2025-07-11 | Pusplata 5 | 37.504 | 5.3577 | TB401 | 21/3 | Complete
2025-07-05 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401 | 22/6 | Complete
2025-07-05 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401 | 22/3 | Complete
2025-07-05 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-05 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401 | 28/9 | Complete
2025-07-05 | 2025-07-04 | 2025-07-09 | Satyam Manish | 60.096 | 10.016 | TB401 | 33/0 | Complete
2025-07-05 | 2025-07-01 | 2025-07-06 | Satyam Mondal | 38.847 | 6.4745 | TB401 | 35/4 | Complete
2025-07-05 | 2025-07-04 | 2025-07-08 | Satyam Nitish | 45.413 | 9.0826 | TB401 | 33/6 | Complete
2025-07-05 | 2025-06-30 | 2025-07-05 | Satyam Trivedi | 38.847 | 6.4745 | TB401 | 65/1 | Complete
2025-07-05 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-07-06 | 2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401 | 12/0 | Complete
2025-07-06 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401 | 29/2 | Complete
2025-07-06 | 2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401 | 28/0 | Complete
2025-07-06 | 2025-07-02 | 2025-07-06 | Jwala Singh 3 | 38.847 | 7.7694 | TB401 | 8/10 | Complete
2025-07-06 | 2025-07-04 | 2025-07-07 | Poonam | 37.504 | 9.376 | TB401 | 24/3 | Complete
2025-07-06 | 2025-07-05 | 2025-07-11 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401 | 15/5 | Complete
2025-07-06 | 2025-07-04 | 2025-07-09 | Pusplata 1 | 37.504 | 6.2507 | TB401 | 25/10 | Complete
2025-07-06 | 2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/7 | Complete
2025-07-06 | 2025-07-02 | 2025-07-06 | Pusplata 4 | 38.847 | 7.7694 | TB401 | 25/6 | Complete
2025-07-06 | 2025-07-05 | 2025-07-11 | Pusplata 5 | 37.504 | 5.3577 | TB401 | 21/3 | Complete
2025-07-06 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401 | 22/6 | Complete
2025-07-06 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401 | 22/3 | Complete
2025-07-06 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-06 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401 | 28/9 | Complete
2025-07-06 | 2025-07-04 | 2025-07-09 | Satyam Manish | 60.096 | 10.016 | TB401 | 33/0 | Complete
2025-07-06 | 2025-07-01 | 2025-07-06 | Satyam Mondal | 38.847 | 6.4745 | TB401 | 35/4 | Complete
2025-07-06 | 2025-07-04 | 2025-07-08 | Satyam Nitish | 45.413 | 9.0826 | TB401 | 33/6 | Complete
2025-07-06 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-07-07 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401 | 29/2 | Complete
2025-07-07 | 2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401 | 28/0 | Complete
2025-07-07 | 2025-07-04 | 2025-07-07 | Poonam | 37.504 | 9.376 | TB401 | 24/3 | Complete
2025-07-07 | 2025-07-05 | 2025-07-11 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401 | 15/5 | Complete
2025-07-07 | 2025-07-04 | 2025-07-09 | Pusplata 1 | 37.504 | 6.2507 | TB401 | 25/10 | Complete
2025-07-07 | 2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/7 | Complete
2025-07-07 | 2025-07-07 | 2025-07-12 | Pusplata 4 | 47.148 | 7.858 | TB401 | 25/7 | Complete
2025-07-07 | 2025-07-05 | 2025-07-11 | Pusplata 5 | 37.504 | 5.3577 | TB401 | 21/3 | Complete
2025-07-07 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401 | 22/6 | Complete
2025-07-07 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401 | 22/3 | Complete
2025-07-07 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-07 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401 | 28/9 | Complete
2025-07-07 | 2025-07-04 | 2025-07-09 | Satyam Manish | 60.096 | 10.016 | TB401 | 33/0 | Complete
2025-07-07 | 2025-07-04 | 2025-07-08 | Satyam Nitish | 45.413 | 9.0826 | TB401 | 33/6 | Complete
2025-07-07 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-07-08 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401 | 14/1 | Complete
2025-07-08 | 2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401 | 29/2 | Complete
2025-07-08 | 2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401 | 28/0 | Complete
2025-07-08 | 2025-07-08 | 2025-07-11 | Poonam | 37.504 | 9.376 | TB401 | 21/6 | Complete
2025-07-08 | 2025-07-05 | 2025-07-11 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401 | 15/5 | Complete
2025-07-08 | 2025-07-04 | 2025-07-09 | Pusplata 1 | 37.504 | 6.2507 | TB401 | 25/10 | Complete
2025-07-08 | 2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/7 | Complete
2025-07-08 | 2025-07-07 | 2025-07-12 | Pusplata 4 | 47.148 | 7.858 | TB401 | 25/7 | Complete
2025-07-08 | 2025-07-05 | 2025-07-11 | Pusplata 5 | 37.504 | 5.3577 | TB401 | 21/3 | Complete
2025-07-08 | 2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401 | 22/6 | Complete
2025-07-08 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401 | 22/3 | Complete
2025-07-08 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-08 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401 | 28/9 | Complete
2025-07-08 | 2025-07-04 | 2025-07-09 | Satyam Manish | 60.096 | 10.016 | TB401 | 33/0 | Complete
2025-07-08 | 2025-07-04 | 2025-07-08 | Satyam Nitish | 45.413 | 9.0826 | TB401 | 33/6 | Complete
2025-07-08 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-07-09 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401 | 14/1 | Complete
2025-07-09 | 2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401 | 28/0 | Complete
2025-07-09 | 2025-07-08 | 2025-07-11 | Poonam | 37.504 | 9.376 | TB401 | 21/6 | Complete
2025-07-09 | 2025-07-05 | 2025-07-11 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401 | 15/5 | Complete
2025-07-09 | 2025-07-04 | 2025-07-09 | Pusplata 1 | 37.504 | 6.2507 | TB401 | 25/10 | Complete
2025-07-09 | 2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/7 | Complete
2025-07-09 | 2025-07-07 | 2025-07-12 | Pusplata 4 | 47.148 | 7.858 | TB401 | 25/7 | Complete
2025-07-09 | 2025-07-05 | 2025-07-11 | Pusplata 5 | 37.504 | 5.3577 | TB401 | 21/3 | Complete
2025-07-09 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/7 | Complete
2025-07-09 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401 | 22/3 | Complete
2025-07-09 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-09 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401 | 28/9 | Complete
2025-07-09 | 2025-07-04 | 2025-07-09 | Satyam Manish | 60.096 | 10.016 | TB401 | 33/0 | Complete
2025-07-09 | 2025-07-09 | 2025-07-14 | Satyam Nitish | 47.148 | 7.858 | TB401 | 33/7 | Complete
2025-07-09 | 2025-07-09 | 2025-07-13 | Satyam Trivedi | 37.504 | 7.5008 | TB401 | 30/2 | Complete
2025-07-09 | 2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-07-10 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401 | 14/1 | Complete
2025-07-10 | 2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401 | 29/3 | Complete
2025-07-10 | 2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401 | 28/0 | Complete
2025-07-10 | 2025-07-08 | 2025-07-11 | Poonam | 37.504 | 9.376 | TB401 | 21/6 | Complete
2025-07-10 | 2025-07-05 | 2025-07-11 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401 | 15/5 | Complete
2025-07-10 | 2025-07-10 | 2025-07-15 | Pusplata 1 | 45.413 | 7.5688 | TB401 | 25/9 | Complete
2025-07-10 | 2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/7 | Complete
2025-07-10 | 2025-07-07 | 2025-07-12 | Pusplata 4 | 47.148 | 7.858 | TB401 | 25/7 | Complete
2025-07-10 | 2025-07-05 | 2025-07-11 | Pusplata 5 | 37.504 | 5.3577 | TB401 | 21/3 | Complete
2025-07-10 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/7 | Complete
2025-07-10 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401 | 22/3 | Complete
2025-07-10 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-10 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401 | 28/9 | Complete
2025-07-10 | 2025-07-10 | 2025-07-13 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/3 | Complete
2025-07-10 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-10 | 2025-07-09 | 2025-07-14 | Satyam Nitish | 47.148 | 7.858 | TB401 | 33/7 | Complete
2025-07-10 | 2025-07-09 | 2025-07-13 | Satyam Trivedi | 37.504 | 7.5008 | TB401 | 30/2 | Complete
2025-07-11 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401 | 14/1 | Complete
2025-07-11 | 2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401 | 29/3 | Complete
2025-07-11 | 2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401 | 28/0 | Complete
2025-07-11 | 2025-07-11 | 2025-07-15 | Jwala Singh 3 | 38.847 | 7.7694 | TB401 | 8/11 | Complete
2025-07-11 | 2025-07-08 | 2025-07-11 | Poonam | 37.504 | 9.376 | TB401 | 21/6 | Complete
2025-07-11 | 2025-07-05 | 2025-07-11 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401 | 15/5 | Complete
2025-07-11 | 2025-07-10 | 2025-07-15 | Pusplata 1 | 45.413 | 7.5688 | TB401 | 25/9 | Complete
2025-07-11 | 2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/7 | Complete
2025-07-11 | 2025-07-07 | 2025-07-12 | Pusplata 4 | 47.148 | 7.858 | TB401 | 25/7 | Complete
2025-07-11 | 2025-07-05 | 2025-07-11 | Pusplata 5 | 37.504 | 5.3577 | TB401 | 21/3 | Complete
2025-07-11 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/7 | Complete
2025-07-11 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401 | 22/3 | Complete
2025-07-11 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-11 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401 | 28/9 | Complete
2025-07-11 | 2025-07-10 | 2025-07-13 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/3 | Complete
2025-07-11 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-11 | 2025-07-09 | 2025-07-14 | Satyam Nitish | 47.148 | 7.858 | TB401 | 33/7 | Complete
2025-07-11 | 2025-07-09 | 2025-07-13 | Satyam Trivedi | 37.504 | 7.5008 | TB401 | 30/2 | Complete
2025-07-11 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-11 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401 | 34/1 | Complete
2025-07-12 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401 | 14/1 | Complete
2025-07-12 | 2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401 | 29/3 | Complete
2025-07-12 | 2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401 | 28/0 | Complete
2025-07-12 | 2025-07-11 | 2025-07-15 | Jwala Singh 3 | 38.847 | 7.7694 | TB401 | 8/11 | Complete
2025-07-12 | 2025-07-12 | 2025-07-16 | Poonam | 57.597 | 11.5194 | TB401 | 21/7 | Complete
2025-07-12 | 2025-07-10 | 2025-07-15 | Pusplata 1 | 45.413 | 7.5688 | TB401 | 25/9 | Complete
2025-07-12 | 2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/7 | Complete
2025-07-12 | 2025-07-07 | 2025-07-12 | Pusplata 4 | 47.148 | 7.858 | TB401 | 25/7 | Complete
2025-07-12 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401 | 21/4 | Complete
2025-07-12 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/7 | Complete
2025-07-12 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401 | 22/3 | Complete
2025-07-12 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-12 | 2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401 | 28/9 | Complete
2025-07-12 | 2025-07-10 | 2025-07-13 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/3 | Complete
2025-07-12 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-12 | 2025-07-09 | 2025-07-14 | Satyam Nitish | 47.148 | 7.858 | TB401 | 33/7 | Complete
2025-07-12 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401 | 26/2 | Complete
2025-07-12 | 2025-07-09 | 2025-07-13 | Satyam Trivedi | 37.504 | 7.5008 | TB401 | 30/2 | Complete
2025-07-12 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-12 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401 | 34/1 | Complete
2025-07-13 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401 | 14/1 | Complete
2025-07-13 | 2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401 | 29/3 | Complete
2025-07-13 | 2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401 | 28/0 | Complete
2025-07-13 | 2025-07-11 | 2025-07-15 | Jwala Singh 3 | 38.847 | 7.7694 | TB401 | 8/11 | Complete
2025-07-13 | 2025-07-12 | 2025-07-16 | Poonam | 57.597 | 11.5194 | TB401 | 21/7 | Complete
2025-07-13 | 2025-07-13 | 2025-07-19 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401 | 15/8 | Complete
2025-07-13 | 2025-07-10 | 2025-07-15 | Pusplata 1 | 45.413 | 7.5688 | TB401 | 25/9 | Complete
2025-07-13 | 2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/7 | Complete
2025-07-13 | 2025-07-13 | 2025-07-18 | Pusplata 4 | 38.847 | 6.4745 | TB401 | 25/1 | Complete
2025-07-13 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401 | 21/4 | Complete
2025-07-13 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/7 | Complete
2025-07-13 | 2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401 | 22/3 | Complete
2025-07-13 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-13 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401 | 29/1 | Complete
2025-07-13 | 2025-07-10 | 2025-07-13 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/3 | Complete
2025-07-13 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-13 | 2025-07-09 | 2025-07-14 | Satyam Nitish | 47.148 | 7.858 | TB401 | 33/7 | Complete
2025-07-13 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401 | 26/2 | Complete
2025-07-13 | 2025-07-09 | 2025-07-13 | Satyam Trivedi | 37.504 | 7.5008 | TB401 | 30/2 | Complete
2025-07-13 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-13 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401 | 34/1 | Complete
2025-07-14 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401 | 14/1 | Complete
2025-07-14 | 2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401 | 29/3 | Complete
2025-07-14 | 2025-07-14 | 2025-07-19 | Jwala Singh 2 | 45.413 | 7.5688 | TB401 | 28/1 | Complete
2025-07-14 | 2025-07-11 | 2025-07-15 | Jwala Singh 3 | 38.847 | 7.7694 | TB401 | 8/11 | Complete
2025-07-14 | 2025-07-12 | 2025-07-16 | Poonam | 57.597 | 11.5194 | TB401 | 21/7 | Complete
2025-07-14 | 2025-07-13 | 2025-07-19 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401 | 15/8 | Complete
2025-07-14 | 2025-07-10 | 2025-07-15 | Pusplata 1 | 45.413 | 7.5688 | TB401 | 25/9 | Complete
2025-07-14 | 2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/8 | Complete
2025-07-14 | 2025-07-13 | 2025-07-18 | Pusplata 4 | 38.847 | 6.4745 | TB401 | 25/1 | Complete
2025-07-14 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401 | 21/4 | Complete
2025-07-14 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/7 | Complete
2025-07-14 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401 | 22/4 | Complete
2025-07-14 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-14 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401 | 29/1 | Complete
2025-07-14 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-14 | 2025-07-09 | 2025-07-14 | Satyam Nitish | 47.148 | 7.858 | TB401 | 33/7 | Complete
2025-07-14 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401 | 26/2 | Complete
2025-07-14 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-14 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401 | 34/1 | Complete
2025-07-15 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401 | 14/1 | Complete
2025-07-15 | 2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401 | 29/3 | Complete
2025-07-15 | 2025-07-14 | 2025-07-19 | Jwala Singh 2 | 45.413 | 7.5688 | TB401 | 28/1 | Complete
2025-07-15 | 2025-07-11 | 2025-07-15 | Jwala Singh 3 | 38.847 | 7.7694 | TB401 | 8/11 | Complete
2025-07-15 | 2025-07-12 | 2025-07-16 | Poonam | 57.597 | 11.5194 | TB401 | 21/7 | Complete
2025-07-15 | 2025-07-13 | 2025-07-19 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401 | 15/8 | Complete
2025-07-15 | 2025-07-10 | 2025-07-15 | Pusplata 1 | 45.413 | 7.5688 | TB401 | 25/9 | Complete
2025-07-15 | 2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/8 | Complete
2025-07-15 | 2025-07-13 | 2025-07-18 | Pusplata 4 | 38.847 | 6.4745 | TB401 | 25/1 | Complete
2025-07-15 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401 | 21/4 | Complete
2025-07-15 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/7 | Complete
2025-07-15 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401 | 22/4 | Complete
2025-07-15 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-15 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401 | 29/1 | Complete
2025-07-15 | 2025-07-15 | 2025-07-18 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/4 | Complete
2025-07-15 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-15 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401 | 34/0 | Complete
2025-07-15 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401 | 26/2 | Complete
2025-07-15 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-15 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401 | 34/1 | Complete
2025-07-16 | 2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401 | 14/1 | Complete
2025-07-16 | 2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401 | 29/3 | Complete
2025-07-16 | 2025-07-14 | 2025-07-19 | Jwala Singh 2 | 45.413 | 7.5688 | TB401 | 28/1 | Complete
2025-07-16 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401 | 10/0 | Complete
2025-07-16 | 2025-07-12 | 2025-07-16 | Poonam | 57.597 | 11.5194 | TB401 | 21/7 | Complete
2025-07-16 | 2025-07-13 | 2025-07-19 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401 | 15/8 | Complete
2025-07-16 | 2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 26/0 | Complete
2025-07-16 | 2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/8 | Complete
2025-07-16 | 2025-07-13 | 2025-07-18 | Pusplata 4 | 38.847 | 6.4745 | TB401 | 25/1 | Complete
2025-07-16 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401 | 21/4 | Complete
2025-07-16 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/7 | Complete
2025-07-16 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401 | 22/4 | Complete
2025-07-16 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-16 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401 | 29/1 | Complete
2025-07-16 | 2025-07-15 | 2025-07-18 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/4 | Complete
2025-07-16 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-16 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401 | 34/0 | Complete
2025-07-16 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401 | 26/2 | Complete
2025-07-16 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-16 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401 | 34/1 | Complete
2025-07-17 | 2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401 | 29/3 | Complete
2025-07-17 | 2025-07-14 | 2025-07-19 | Jwala Singh 2 | 45.413 | 7.5688 | TB401 | 28/1 | Complete
2025-07-17 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401 | 10/0 | Complete
2025-07-17 | 2025-07-17 | 2025-07-21 | Poonam | 37.504 | 7.5008 | TB401 | 21/8 | Complete
2025-07-17 | 2025-07-13 | 2025-07-19 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401 | 15/8 | Complete
2025-07-17 | 2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 26/0 | Complete
2025-07-17 | 2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/8 | Complete
2025-07-17 | 2025-07-17 | 2025-07-23 | Pusplata 3 | 57.597 | 8.2281 | TB401 | 24/0 | Complete
2025-07-17 | 2025-07-13 | 2025-07-18 | Pusplata 4 | 38.847 | 6.4745 | TB401 | 25/1 | Complete
2025-07-17 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401 | 21/4 | Complete
2025-07-17 | 2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/7 | Complete
2025-07-17 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401 | 22/4 | Complete
2025-07-17 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-17 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401 | 29/1 | Complete
2025-07-17 | 2025-07-15 | 2025-07-18 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/4 | Complete
2025-07-17 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-17 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401 | 34/0 | Complete
2025-07-17 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401 | 26/2 | Complete
2025-07-17 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-17 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401 | 34/1 | Complete
2025-07-18 | 2025-07-18 | 2025-07-24 | Arawali Infra 2 | 66.381 | 9.483 | TB401 | 14/0 | Complete
2025-07-18 | 2025-07-18 | 2025-07-24 | Gourishankar | 38.847 | 5.5496 | TB401 | 29/4 | Complete
2025-07-18 | 2025-07-14 | 2025-07-19 | Jwala Singh 2 | 45.413 | 7.5688 | TB401 | 28/1 | Complete
2025-07-18 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401 | 10/0 | Complete
2025-07-18 | 2025-07-17 | 2025-07-21 | Poonam | 37.504 | 7.5008 | TB401 | 21/8 | Complete
2025-07-18 | 2025-07-13 | 2025-07-19 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401 | 15/8 | Complete
2025-07-18 | 2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 26/0 | Complete
2025-07-18 | 2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/8 | Complete
2025-07-18 | 2025-07-17 | 2025-07-23 | Pusplata 3 | 57.597 | 8.2281 | TB401 | 24/0 | Complete
2025-07-18 | 2025-07-13 | 2025-07-18 | Pusplata 4 | 38.847 | 6.4745 | TB401 | 25/1 | Complete
2025-07-18 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401 | 21/4 | Complete
2025-07-18 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/9 | Complete
2025-07-18 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401 | 22/4 | Complete
2025-07-18 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-18 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401 | 29/1 | Complete
2025-07-18 | 2025-07-15 | 2025-07-18 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/4 | Complete
2025-07-18 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-18 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401 | 34/0 | Complete
2025-07-18 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401 | 26/2 | Complete
2025-07-18 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-18 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401 | 34/1 | Complete
2025-07-19 | 2025-07-18 | 2025-07-24 | Arawali Infra 2 | 66.381 | 9.483 | TB401 | 14/0 | Complete
2025-07-19 | 2025-07-18 | 2025-07-24 | Gourishankar | 38.847 | 5.5496 | TB401 | 29/4 | Complete
2025-07-19 | 2025-07-14 | 2025-07-19 | Jwala Singh 2 | 45.413 | 7.5688 | TB401 | 28/1 | Complete
2025-07-19 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401 | 10/0 | Complete
2025-07-19 | 2025-07-17 | 2025-07-21 | Poonam | 37.504 | 7.5008 | TB401 | 21/8 | Complete
2025-07-19 | 2025-07-13 | 2025-07-19 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401 | 15/8 | Complete
2025-07-19 | 2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 26/0 | Complete
2025-07-19 | 2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/8 | Complete
2025-07-19 | 2025-07-17 | 2025-07-23 | Pusplata 3 | 57.597 | 8.2281 | TB401 | 24/0 | Complete
2025-07-19 | 2025-07-19 | 2025-07-22 | Pusplata 4 | 37.504 | 9.376 | TB401 | 25/3 | Complete
2025-07-19 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401 | 21/4 | Complete
2025-07-19 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/9 | Complete
2025-07-19 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401 | 22/4 | Complete
2025-07-19 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-19 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401 | 29/1 | Complete
2025-07-19 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-19 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401 | 34/0 | Complete
2025-07-19 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401 | 26/2 | Complete
2025-07-19 | 2025-07-19 | 2025-07-24 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/5 | Complete
2025-07-19 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-19 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401 | 34/1 | Complete
2025-07-20 | 2025-07-18 | 2025-07-24 | Arawali Infra 2 | 66.381 | 9.483 | TB401 | 14/0 | Complete
2025-07-20 | 2025-07-18 | 2025-07-24 | Gourishankar | 38.847 | 5.5496 | TB401 | 29/4 | Complete
2025-07-20 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401 | 10/0 | Complete
2025-07-20 | 2025-07-17 | 2025-07-21 | Poonam | 37.504 | 7.5008 | TB401 | 21/8 | Complete
2025-07-20 | 2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 26/0 | Complete
2025-07-20 | 2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/8 | Complete
2025-07-20 | 2025-07-17 | 2025-07-23 | Pusplata 3 | 57.597 | 8.2281 | TB401 | 24/0 | Complete
2025-07-20 | 2025-07-19 | 2025-07-22 | Pusplata 4 | 37.504 | 9.376 | TB401 | 25/3 | Complete
2025-07-20 | 2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401 | 21/4 | Complete
2025-07-20 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/9 | Complete
2025-07-20 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401 | 22/4 | Complete
2025-07-20 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-20 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401 | 29/1 | Complete
2025-07-20 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-20 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401 | 34/0 | Complete
2025-07-20 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401 | 26/2 | Complete
2025-07-20 | 2025-07-19 | 2025-07-24 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/5 | Complete
2025-07-20 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-20 | 2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401 | 34/1 | Complete
2025-07-21 | 2025-07-18 | 2025-07-24 | Arawali Infra 2 | 66.381 | 9.483 | TB401 | 14/0 | Complete
2025-07-21 | 2025-07-18 | 2025-07-24 | Gourishankar | 38.847 | 5.5496 | TB401 | 29/4 | Complete
2025-07-21 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401 | 10/0 | Complete
2025-07-21 | 2025-07-17 | 2025-07-21 | Poonam | 37.504 | 7.5008 | TB401 | 21/8 | Complete
2025-07-21 | 2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 26/0 | Complete
2025-07-21 | 2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/8 | Complete
2025-07-21 | 2025-07-17 | 2025-07-23 | Pusplata 3 | 57.597 | 8.2281 | TB401 | 24/0 | Complete
2025-07-21 | 2025-07-19 | 2025-07-22 | Pusplata 4 | 37.504 | 9.376 | TB401 | 25/3 | Complete
2025-07-21 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/9 | Complete
2025-07-21 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401 | 22/4 | Complete
2025-07-21 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-21 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401 | 29/1 | Complete
2025-07-21 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-21 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401 | 34/0 | Complete
2025-07-21 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401 | 26/2 | Complete
2025-07-21 | 2025-07-19 | 2025-07-24 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/5 | Complete
2025-07-21 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-22 | 2025-07-18 | 2025-07-24 | Arawali Infra 2 | 66.381 | 9.483 | TB401 | 14/0 | Complete
2025-07-22 | 2025-07-18 | 2025-07-24 | Gourishankar | 38.847 | 5.5496 | TB401 | 29/4 | Complete
2025-07-22 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401 | 10/0 | Complete
2025-07-22 | 2025-07-22 | 2025-07-28 | Priyanka Devi Sudheer | 38.847 | 5.5496 | TB401 | 18/1 | Complete
2025-07-22 | 2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 26/0 | Complete
2025-07-22 | 2025-07-22 | 2025-07-26 | Pusplata 2 | 38.847 | 7.7694 | TB401 | 23/10 | Complete
2025-07-22 | 2025-07-17 | 2025-07-23 | Pusplata 3 | 57.597 | 8.2281 | TB401 | 24/0 | Complete
2025-07-22 | 2025-07-19 | 2025-07-22 | Pusplata 4 | 37.504 | 9.376 | TB401 | 25/3 | Complete
2025-07-22 | 2025-07-22 | 2025-07-27 | Pusplata 5 | 38.847 | 6.4745 | TB401 | 21/5 | Complete
2025-07-22 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/9 | Complete
2025-07-22 | 2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401 | 22/4 | Complete
2025-07-22 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-22 | 2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401 | 29/1 | Complete
2025-07-22 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-22 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401 | 34/0 | Complete
2025-07-22 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401 | 26/2 | Complete
2025-07-22 | 2025-07-19 | 2025-07-24 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/5 | Complete
2025-07-22 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-23 | 2025-07-18 | 2025-07-24 | Arawali Infra 2 | 66.381 | 9.483 | TB401 | 14/0 | Complete
2025-07-23 | 2025-07-18 | 2025-07-24 | Gourishankar | 38.847 | 5.5496 | TB401 | 29/4 | Complete
2025-07-23 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401 | 10/0 | Complete
2025-07-23 | 2025-07-22 | 2025-07-28 | Priyanka Devi Sudheer | 38.847 | 5.5496 | TB401 | 18/1 | Complete
2025-07-23 | 2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 26/0 | Complete
2025-07-23 | 2025-07-22 | 2025-07-26 | Pusplata 2 | 38.847 | 7.7694 | TB401 | 23/10 | Complete
2025-07-23 | 2025-07-17 | 2025-07-23 | Pusplata 3 | 57.597 | 8.2281 | TB401 | 24/0 | Complete
2025-07-23 | 2025-07-22 | 2025-07-27 | Pusplata 5 | 38.847 | 6.4745 | TB401 | 21/5 | Complete
2025-07-23 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/9 | Complete
2025-07-23 | 2025-07-23 | 2025-07-27 | Pusplata 7 | 38.847 | 7.7694 | TB401 | 22/5 | Complete
2025-07-23 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-23 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-23 | 2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401 | 34/0 | Complete
2025-07-23 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401 | 26/2 | Complete
2025-07-23 | 2025-07-19 | 2025-07-24 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/5 | Complete
2025-07-23 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-24 | 2025-07-18 | 2025-07-24 | Arawali Infra 2 | 66.381 | 9.483 | TB401 | 14/0 | Complete
2025-07-24 | 2025-07-18 | 2025-07-24 | Gourishankar | 38.847 | 5.5496 | TB401 | 29/4 | Complete
2025-07-24 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401 | 10/0 | Complete
2025-07-24 | 2025-07-22 | 2025-07-28 | Priyanka Devi Sudheer | 38.847 | 5.5496 | TB401 | 18/1 | Complete
2025-07-24 | 2025-07-22 | 2025-07-26 | Pusplata 2 | 38.847 | 7.7694 | TB401 | 23/10 | Complete
2025-07-24 | 2025-07-24 | 2025-07-26 | Pusplata 4 | 37.504 | 12.5013 | TB401 | 23/3 | Complete
2025-07-24 | 2025-07-22 | 2025-07-27 | Pusplata 5 | 38.847 | 6.4745 | TB401 | 21/5 | Complete
2025-07-24 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/9 | Complete
2025-07-24 | 2025-07-23 | 2025-07-27 | Pusplata 7 | 38.847 | 7.7694 | TB401 | 22/5 | Complete
2025-07-24 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-24 | 2025-07-24 | 2025-07-29 | Rahul Kumar | 38.847 | 6.4745 | TB401 | 28/8 | Complete
2025-07-24 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-24 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401 | 26/2 | Complete
2025-07-24 | 2025-07-19 | 2025-07-24 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/5 | Complete
2025-07-24 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-24 | 2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401 | 34/3 | Complete
2025-07-25 | 2025-07-25 | 2025-07-31 | Gourishankar | 57.597 | 8.2281 | TB401 | 29/0 | Complete
2025-07-25 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401 | 10/0 | Complete
2025-07-25 | 2025-07-22 | 2025-07-28 | Priyanka Devi Sudheer | 38.847 | 5.5496 | TB401 | 18/1 | Complete
2025-07-25 | 2025-07-25 | 2025-07-30 | Pusplata 1 | 38.847 | 6.4745 | TB401 | 26/1 | Complete
2025-07-25 | 2025-07-22 | 2025-07-26 | Pusplata 2 | 38.847 | 7.7694 | TB401 | 23/10 | Complete
2025-07-25 | 2025-07-24 | 2025-07-26 | Pusplata 4 | 37.504 | 12.5013 | TB401 | 23/3 | Complete
2025-07-25 | 2025-07-22 | 2025-07-27 | Pusplata 5 | 38.847 | 6.4745 | TB401 | 21/5 | Complete
2025-07-25 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/9 | Complete
2025-07-25 | 2025-07-23 | 2025-07-27 | Pusplata 7 | 38.847 | 7.7694 | TB401 | 22/5 | Complete
2025-07-25 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-25 | 2025-07-24 | 2025-07-29 | Rahul Kumar | 38.847 | 6.4745 | TB401 | 28/8 | Complete
2025-07-25 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-25 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401 | 26/2 | Complete
2025-07-25 | 2025-07-25 | 2025-07-30 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/4 | Complete
2025-07-25 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-25 | 2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401 | 34/3 | Complete
2025-07-26 | 2025-07-25 | 2025-07-31 | Gourishankar | 57.597 | 8.2281 | TB401 | 29/0 | Complete
2025-07-26 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401 | 10/0 | Complete
2025-07-26 | 2025-07-22 | 2025-07-28 | Priyanka Devi Sudheer | 38.847 | 5.5496 | TB401 | 18/1 | Complete
2025-07-26 | 2025-07-25 | 2025-07-30 | Pusplata 1 | 38.847 | 6.4745 | TB401 | 26/1 | Complete
2025-07-26 | 2025-07-22 | 2025-07-26 | Pusplata 2 | 38.847 | 7.7694 | TB401 | 23/10 | Complete
2025-07-26 | 2025-07-24 | 2025-07-26 | Pusplata 4 | 37.504 | 12.5013 | TB401 | 23/3 | Complete
2025-07-26 | 2025-07-22 | 2025-07-27 | Pusplata 5 | 38.847 | 6.4745 | TB401 | 21/5 | Complete
2025-07-26 | 2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/9 | Complete
2025-07-26 | 2025-07-23 | 2025-07-27 | Pusplata 7 | 38.847 | 7.7694 | TB401 | 22/5 | Complete
2025-07-26 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-26 | 2025-07-24 | 2025-07-29 | Rahul Kumar | 38.847 | 6.4745 | TB401 | 28/8 | Complete
2025-07-26 | 2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-26 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401 | 26/2 | Complete
2025-07-26 | 2025-07-25 | 2025-07-30 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/4 | Complete
2025-07-26 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-26 | 2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401 | 34/3 | Complete
2025-07-27 | 2025-07-25 | 2025-07-31 | Gourishankar | 57.597 | 8.2281 | TB401 | 29/0 | Complete
2025-07-27 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401 | 10/0 | Complete
2025-07-27 | 2025-07-22 | 2025-07-28 | Priyanka Devi Sudheer | 38.847 | 5.5496 | TB401 | 18/1 | Complete
2025-07-27 | 2025-07-25 | 2025-07-30 | Pusplata 1 | 38.847 | 6.4745 | TB401 | 26/1 | Complete
2025-07-27 | 2025-07-27 | 2025-07-31 | Pusplata 2 | 45.413 | 9.0826 | TB401 | 23/11 | Complete
2025-07-27 | 2025-07-27 | 2025-07-30 | Pusplata 3 | 38.847 | 9.7118 | TB401 | 28/2 | Complete
2025-07-27 | 2025-07-27 | 2025-07-31 | Pusplata 4 | 37.504 | 7.5008 | TB401 | 23/1 | Complete
2025-07-27 | 2025-07-22 | 2025-07-27 | Pusplata 5 | 38.847 | 6.4745 | TB401 | 21/5 | Complete
2025-07-27 | 2025-07-27 | 2025-07-31 | Pusplata 6 | 38.847 | 7.7694 | TB401 | 23/4 | Complete
2025-07-27 | 2025-07-23 | 2025-07-27 | Pusplata 7 | 38.847 | 7.7694 | TB401 | 22/5 | Complete
2025-07-27 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-27 | 2025-07-24 | 2025-07-29 | Rahul Kumar | 38.847 | 6.4745 | TB401 | 28/8 | Complete
2025-07-27 | 2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401 | 26/2 | Complete
2025-07-27 | 2025-07-25 | 2025-07-30 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/4 | Complete
2025-07-27 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-27 | 2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401 | 34/3 | Complete
2025-07-28 | 2025-07-25 | 2025-07-31 | Gourishankar | 57.597 | 8.2281 | TB401 | 29/0 | Complete
2025-07-28 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401 | 10/0 | Complete
2025-07-28 | 2025-07-28 | 2025-07-31 | Poonam | 37.504 | 9.376 | TB401 | 22/2 | Complete
2025-07-28 | 2025-07-22 | 2025-07-28 | Priyanka Devi Sudheer | 38.847 | 5.5496 | TB401 | 18/1 | Complete
2025-07-28 | 2025-07-25 | 2025-07-30 | Pusplata 1 | 38.847 | 6.4745 | TB401 | 26/1 | Complete
2025-07-28 | 2025-07-27 | 2025-07-31 | Pusplata 2 | 45.413 | 9.0826 | TB401 | 23/11 | Complete
2025-07-28 | 2025-07-27 | 2025-07-30 | Pusplata 3 | 38.847 | 9.7118 | TB401 | 28/2 | Complete
2025-07-28 | 2025-07-27 | 2025-07-31 | Pusplata 4 | 37.504 | 7.5008 | TB401 | 23/1 | Complete
2025-07-28 | 2025-07-27 | 2025-07-31 | Pusplata 6 | 38.847 | 7.7694 | TB401 | 23/4 | Complete
2025-07-28 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-28 | 2025-07-24 | 2025-07-29 | Rahul Kumar | 38.847 | 6.4745 | TB401 | 28/8 | Complete
2025-07-28 | 2025-07-25 | 2025-07-30 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/4 | Complete
2025-07-28 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-28 | 2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401 | 34/3 | Complete
2025-07-29 | 2025-07-25 | 2025-07-31 | Gourishankar | 57.597 | 8.2281 | TB401 | 29/0 | Complete
2025-07-29 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401 | 10/0 | Complete
2025-07-29 | 2025-07-28 | 2025-07-31 | Poonam | 37.504 | 9.376 | TB401 | 22/2 | Complete
2025-07-29 | 2025-07-25 | 2025-07-30 | Pusplata 1 | 38.847 | 6.4745 | TB401 | 26/1 | Complete
2025-07-29 | 2025-07-27 | 2025-07-31 | Pusplata 2 | 45.413 | 9.0826 | TB401 | 23/11 | Complete
2025-07-29 | 2025-07-27 | 2025-07-30 | Pusplata 3 | 38.847 | 9.7118 | TB401 | 28/2 | Complete
2025-07-29 | 2025-07-27 | 2025-07-31 | Pusplata 4 | 37.504 | 7.5008 | TB401 | 23/1 | Complete
2025-07-29 | 2025-07-27 | 2025-07-31 | Pusplata 6 | 38.847 | 7.7694 | TB401 | 23/4 | Complete
2025-07-29 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-29 | 2025-07-24 | 2025-07-29 | Rahul Kumar | 38.847 | 6.4745 | TB401 | 28/8 | Complete
2025-07-29 | 2025-07-25 | 2025-07-30 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/4 | Complete
2025-07-29 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-29 | 2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401 | 34/3 | Complete
2025-07-30 | 2025-07-25 | 2025-07-31 | Gourishankar | 57.597 | 8.2281 | TB401 | 29/0 | Complete
2025-07-30 | 2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401 | 10/0 | Complete
2025-07-30 | 2025-07-28 | 2025-07-31 | Poonam | 37.504 | 9.376 | TB401 | 22/2 | Complete
2025-07-30 | 2025-07-25 | 2025-07-30 | Pusplata 1 | 38.847 | 6.4745 | TB401 | 26/1 | Complete
2025-07-30 | 2025-07-27 | 2025-07-31 | Pusplata 2 | 45.413 | 9.0826 | TB401 | 23/11 | Complete
2025-07-30 | 2025-07-27 | 2025-07-30 | Pusplata 3 | 38.847 | 9.7118 | TB401 | 28/2 | Complete
2025-07-30 | 2025-07-27 | 2025-07-31 | Pusplata 4 | 37.504 | 7.5008 | TB401 | 23/1 | Complete
2025-07-30 | 2025-07-27 | 2025-07-31 | Pusplata 6 | 38.847 | 7.7694 | TB401 | 23/4 | Complete
2025-07-30 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-30 | 2025-07-25 | 2025-07-30 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/4 | Complete
2025-07-30 | 2025-07-30 | 2025-07-31 | Satyam Vijay | 37.504 | 18.752 | TB401 | 27/3 | Complete
2025-07-30 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-30 | 2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401 | 34/3 | Complete
2025-07-31 | 2025-07-25 | 2025-07-31 | Gourishankar | 57.597 | 8.2281 | TB401 | 29/0 | Complete
2025-07-31 | 2025-07-31 | 2025-08-05 | Jwala Singh 3 | 37.504 | 6.2507 | TB401 | 8/12 | Complete
2025-07-31 | 2025-07-28 | 2025-07-31 | Poonam | 37.504 | 9.376 | TB401 | 22/2 | Complete
2025-07-31 | 2025-07-27 | 2025-07-31 | Pusplata 2 | 45.413 | 9.0826 | TB401 | 23/11 | Complete
2025-07-31 | 2025-07-31 | 2025-08-04 | Pusplata 3 | 37.504 | 7.5008 | TB401 | 28/3 | Complete
2025-07-31 | 2025-07-27 | 2025-07-31 | Pusplata 4 | 37.504 | 7.5008 | TB401 | 23/1 | Complete
2025-07-31 | 2025-07-27 | 2025-07-31 | Pusplata 6 | 38.847 | 7.7694 | TB401 | 23/4 | Complete
2025-07-31 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-07-31 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401 | 30/0 | Complete
2025-07-31 | 2025-07-30 | 2025-07-31 | Satyam Vijay | 37.504 | 18.752 | TB401 | 27/3 | Complete
2025-07-31 | 2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-31 | 2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401 | 34/3 | Complete
2025-08-01 | 2025-07-31 | 2025-08-05 | Jwala Singh 3 | 37.504 | 6.2507 | TB401 | 8/12 | Complete
2025-08-01 | 2025-08-01 | 2025-08-04 | Poonam | 37.504 | 9.376 | TB401 | 22/1 | Complete
2025-08-01 | 2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 23/0 | Complete
2025-08-01 | 2025-07-31 | 2025-08-04 | Pusplata 3 | 37.504 | 7.5008 | TB401 | 28/3 | Complete
2025-08-01 | 2025-08-01 | 2025-08-05 | Pusplata 4 | 37.504 | 7.5008 | TB401 | 25/4 | Complete
2025-08-01 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-01 | 2025-08-01 | 2025-08-06 | Pusplata Deepak | 37.504 | 6.2507 | TB401 | 23/5 | Complete
2025-08-01 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401 | 30/0 | Complete
2025-08-02 | 2025-07-31 | 2025-08-05 | Jwala Singh 3 | 37.504 | 6.2507 | TB401 | 8/12 | Complete
2025-08-02 | 2025-08-01 | 2025-08-04 | Poonam | 37.504 | 9.376 | TB401 | 22/1 | Complete
2025-08-02 | 2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 23/0 | Complete
2025-08-02 | 2025-07-31 | 2025-08-04 | Pusplata 3 | 37.504 | 7.5008 | TB401 | 28/3 | Complete
2025-08-02 | 2025-08-01 | 2025-08-05 | Pusplata 4 | 37.504 | 7.5008 | TB401 | 25/4 | Complete
2025-08-02 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-02 | 2025-08-01 | 2025-08-06 | Pusplata Deepak | 37.504 | 6.2507 | TB401 | 23/5 | Complete
2025-08-02 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401 | 30/0 | Complete
2025-08-03 | 2025-08-03 | 2025-08-09 | Gourishankar | 47.184 | 6.7406 | TB401 | 31/1 | Complete
2025-08-03 | 2025-07-31 | 2025-08-05 | Jwala Singh 3 | 37.504 | 6.2507 | TB401 | 8/12 | Complete
2025-08-03 | 2025-08-01 | 2025-08-04 | Poonam | 37.504 | 9.376 | TB401 | 22/1 | Complete
2025-08-03 | 2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 23/0 | Complete
2025-08-03 | 2025-07-31 | 2025-08-04 | Pusplata 3 | 37.504 | 7.5008 | TB401 | 28/3 | Complete
2025-08-03 | 2025-08-01 | 2025-08-05 | Pusplata 4 | 37.504 | 7.5008 | TB401 | 25/4 | Complete
2025-08-03 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-03 | 2025-08-01 | 2025-08-06 | Pusplata Deepak | 37.504 | 6.2507 | TB401 | 23/5 | Complete
2025-08-03 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401 | 30/0 | Complete
2025-08-04 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401 | 16/1 | Complete
2025-08-04 | 2025-08-03 | 2025-08-09 | Gourishankar | 47.184 | 6.7406 | TB401 | 31/1 | Complete
2025-08-04 | 2025-07-31 | 2025-08-05 | Jwala Singh 3 | 37.504 | 6.2507 | TB401 | 8/12 | Complete
2025-08-04 | 2025-08-01 | 2025-08-04 | Poonam | 37.504 | 9.376 | TB401 | 22/1 | Complete
2025-08-04 | 2025-08-04 | 2025-08-09 | Priyanka Devi Sudheer | 37.504 | 6.2507 | TB401 | 16/6 | Complete
2025-08-04 | 2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 23/0 | Complete
2025-08-04 | 2025-07-31 | 2025-08-04 | Pusplata 3 | 37.504 | 7.5008 | TB401 | 28/3 | Complete
2025-08-04 | 2025-08-01 | 2025-08-05 | Pusplata 4 | 37.504 | 7.5008 | TB401 | 25/4 | Complete
2025-08-04 | 2025-08-04 | 2025-08-09 | Pusplata 6 | 37.504 | 6.2507 | TB401 | 23/2 | Complete
2025-08-04 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-04 | 2025-08-01 | 2025-08-06 | Pusplata Deepak | 37.504 | 6.2507 | TB401 | 23/5 | Complete
2025-08-04 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401 | 30/0 | Complete
2025-08-04 | 2025-08-04 | 2025-08-07 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/2 | Complete
2025-08-05 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401 | 16/1 | Complete
2025-08-05 | 2025-08-03 | 2025-08-09 | Gourishankar | 47.184 | 6.7406 | TB401 | 31/1 | Complete
2025-08-05 | 2025-07-31 | 2025-08-05 | Jwala Singh 3 | 37.504 | 6.2507 | TB401 | 8/12 | Complete
2025-08-05 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401 | 17/5 | Complete
2025-08-05 | 2025-08-04 | 2025-08-09 | Priyanka Devi Sudheer | 37.504 | 6.2507 | TB401 | 16/6 | Complete
2025-08-05 | 2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 23/0 | Complete
2025-08-05 | 2025-08-01 | 2025-08-05 | Pusplata 4 | 37.504 | 7.5008 | TB401 | 25/4 | Complete
2025-08-05 | 2025-08-04 | 2025-08-09 | Pusplata 6 | 37.504 | 6.2507 | TB401 | 23/2 | Complete
2025-08-05 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-05 | 2025-08-01 | 2025-08-06 | Pusplata Deepak | 37.504 | 6.2507 | TB401 | 23/5 | Complete
2025-08-05 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401 | 30/0 | Complete
2025-08-05 | 2025-08-04 | 2025-08-07 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/2 | Complete
2025-08-06 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401 | 16/1 | Complete
2025-08-06 | 2025-08-03 | 2025-08-09 | Gourishankar | 47.184 | 6.7406 | TB401 | 31/1 | Complete
2025-08-06 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401 | 17/5 | Complete
2025-08-06 | 2025-08-04 | 2025-08-09 | Priyanka Devi Sudheer | 37.504 | 6.2507 | TB401 | 16/6 | Complete
2025-08-06 | 2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 23/0 | Complete
2025-08-06 | 2025-08-04 | 2025-08-09 | Pusplata 6 | 37.504 | 6.2507 | TB401 | 23/2 | Complete
2025-08-06 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-06 | 2025-08-06 | 2025-08-11 | Pusplata Ashok | 45.413 | 7.5688 | TB401 | 21/14 | Complete
2025-08-06 | 2025-08-01 | 2025-08-06 | Pusplata Deepak | 37.504 | 6.2507 | TB401 | 23/5 | Complete
2025-08-06 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401 | 30/0 | Complete
2025-08-06 | 2025-08-04 | 2025-08-07 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/2 | Complete
2025-08-06 | 2025-08-06 | 2025-08-11 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/2 | Complete
2025-08-07 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401 | 16/1 | Complete
2025-08-07 | 2025-08-03 | 2025-08-09 | Gourishankar | 47.184 | 6.7406 | TB401 | 31/1 | Complete
2025-08-07 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401 | 17/5 | Complete
2025-08-07 | 2025-08-04 | 2025-08-09 | Priyanka Devi Sudheer | 37.504 | 6.2507 | TB401 | 16/6 | Complete
2025-08-07 | 2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 23/0 | Complete
2025-08-07 | 2025-08-04 | 2025-08-09 | Pusplata 6 | 37.504 | 6.2507 | TB401 | 23/2 | Complete
2025-08-07 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-07 | 2025-08-06 | 2025-08-11 | Pusplata Ashok | 45.413 | 7.5688 | TB401 | 21/14 | Complete
2025-08-07 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401 | 30/0 | Complete
2025-08-07 | 2025-08-04 | 2025-08-07 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/2 | Complete
2025-08-07 | 2025-08-06 | 2025-08-11 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/2 | Complete
2025-08-08 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401 | 16/1 | Complete
2025-08-08 | 2025-08-03 | 2025-08-09 | Gourishankar | 47.184 | 6.7406 | TB401 | 31/1 | Complete
2025-08-08 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401 | 17/5 | Complete
2025-08-08 | 2025-08-04 | 2025-08-09 | Priyanka Devi Sudheer | 37.504 | 6.2507 | TB401 | 16/6 | Complete
2025-08-08 | 2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 23/0 | Complete
2025-08-08 | 2025-08-04 | 2025-08-09 | Pusplata 6 | 37.504 | 6.2507 | TB401 | 23/2 | Complete
2025-08-08 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-08 | 2025-08-06 | 2025-08-11 | Pusplata Ashok | 45.413 | 7.5688 | TB401 | 21/14 | Complete
2025-08-08 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401 | 30/0 | Complete
2025-08-08 | 2025-08-06 | 2025-08-11 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/2 | Complete
2025-08-09 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401 | 16/1 | Complete
2025-08-09 | 2025-08-03 | 2025-08-09 | Gourishankar | 47.184 | 6.7406 | TB401 | 31/1 | Complete
2025-08-09 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401 | 17/5 | Complete
2025-08-09 | 2025-08-04 | 2025-08-09 | Priyanka Devi Sudheer | 37.504 | 6.2507 | TB401 | 16/6 | Complete
2025-08-09 | 2025-08-04 | 2025-08-09 | Pusplata 6 | 37.504 | 6.2507 | TB401 | 23/2 | Complete
2025-08-09 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-09 | 2025-08-06 | 2025-08-11 | Pusplata Ashok | 45.413 | 7.5688 | TB401 | 21/14 | Complete
2025-08-09 | 2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401 | 30/0 | Complete
2025-08-09 | 2025-08-09 | 2025-08-12 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/1 | Complete
2025-08-09 | 2025-08-06 | 2025-08-11 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/2 | Complete
2025-08-10 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401 | 16/1 | Complete
2025-08-10 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401 | 17/5 | Complete
2025-08-10 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-10 | 2025-08-06 | 2025-08-11 | Pusplata Ashok | 45.413 | 7.5688 | TB401 | 21/14 | Complete
2025-08-10 | 2025-08-09 | 2025-08-12 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/1 | Complete
2025-08-10 | 2025-08-06 | 2025-08-11 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/2 | Complete
2025-08-11 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401 | 16/1 | Complete
2025-08-11 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401 | 17/5 | Complete
2025-08-11 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401 | 18/0 | Complete
2025-08-11 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-11 | 2025-08-06 | 2025-08-11 | Pusplata Ashok | 45.413 | 7.5688 | TB401 | 21/14 | Complete
2025-08-11 | 2025-08-09 | 2025-08-12 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/1 | Complete
2025-08-11 | 2025-08-06 | 2025-08-11 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/2 | Complete
2025-08-12 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401 | 16/1 | Complete
2025-08-12 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401 | 17/5 | Complete
2025-08-12 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401 | 18/0 | Complete
2025-08-12 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-12 | 2025-08-09 | 2025-08-12 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/1 | Complete
2025-08-12 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401 | 27/1 | Complete
2025-08-13 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401 | 16/1 | Complete
2025-08-13 | 2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401 | 17/5 | Complete
2025-08-13 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401 | 18/0 | Complete
2025-08-13 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-13 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401 | 27/1 | Complete
2025-08-14 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401 | 16/1 | Complete
2025-08-14 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401 | 2/0 | Complete
2025-08-14 | 2025-08-14 | 2025-08-19 | Priyanka Devi 2 | 38.847 | 6.4745 | TB401 | 18/8 | Complete
2025-08-14 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401 | 18/0 | Complete
2025-08-14 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-14 | 2025-08-14 | 2025-08-19 | Pusplata Ashok | 37.504 | 6.2507 | TB401 | 4/4 | Complete
2025-08-14 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401 | 27/1 | Complete
2025-08-15 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401 | 16/1 | Complete
2025-08-15 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401 | 2/0 | Complete
2025-08-15 | 2025-08-14 | 2025-08-19 | Priyanka Devi 2 | 38.847 | 6.4745 | TB401 | 18/8 | Complete
2025-08-15 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401 | 18/0 | Complete
2025-08-15 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-15 | 2025-08-14 | 2025-08-19 | Pusplata Ashok | 37.504 | 6.2507 | TB401 | 4/4 | Complete
2025-08-15 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401 | 27/1 | Complete
2025-08-16 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401 | 16/1 | Complete
2025-08-16 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401 | 2/0 | Complete
2025-08-16 | 2025-08-14 | 2025-08-19 | Priyanka Devi 2 | 38.847 | 6.4745 | TB401 | 18/8 | Complete
2025-08-16 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401 | 18/0 | Complete
2025-08-16 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-16 | 2025-08-14 | 2025-08-19 | Pusplata Ashok | 37.504 | 6.2507 | TB401 | 4/4 | Complete
2025-08-16 | 2025-08-16 | 2025-08-19 | Pusplata Deepak | 38.847 | 9.7118 | TB401 | 24/1 | Complete
2025-08-16 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401 | 27/1 | Complete
2025-08-17 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401 | 16/1 | Complete
2025-08-17 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401 | 2/0 | Complete
2025-08-17 | 2025-08-14 | 2025-08-19 | Priyanka Devi 2 | 38.847 | 6.4745 | TB401 | 18/8 | Complete
2025-08-17 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401 | 18/0 | Complete
2025-08-17 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-17 | 2025-08-14 | 2025-08-19 | Pusplata Ashok | 37.504 | 6.2507 | TB401 | 4/4 | Complete
2025-08-17 | 2025-08-16 | 2025-08-19 | Pusplata Deepak | 38.847 | 9.7118 | TB401 | 24/1 | Complete
2025-08-17 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401 | 27/1 | Complete
2025-08-17 | 2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401 | 2/3 | Complete
2025-08-18 | 2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401 | 16/1 | Complete
2025-08-18 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401 | 2/0 | Complete
2025-08-18 | 2025-08-14 | 2025-08-19 | Priyanka Devi 2 | 38.847 | 6.4745 | TB401 | 18/8 | Complete
2025-08-18 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401 | 18/0 | Complete
2025-08-18 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-18 | 2025-08-14 | 2025-08-19 | Pusplata Ashok | 37.504 | 6.2507 | TB401 | 4/4 | Complete
2025-08-18 | 2025-08-16 | 2025-08-19 | Pusplata Deepak | 38.847 | 9.7118 | TB401 | 24/1 | Complete
2025-08-18 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401 | 27/1 | Complete
2025-08-18 | 2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401 | 2/3 | Complete
2025-08-19 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401 | 2/0 | Complete
2025-08-19 | 2025-08-14 | 2025-08-19 | Priyanka Devi 2 | 38.847 | 6.4745 | TB401 | 18/8 | Complete
2025-08-19 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401 | 18/0 | Complete
2025-08-19 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-19 | 2025-08-14 | 2025-08-19 | Pusplata Ashok | 37.504 | 6.2507 | TB401 | 4/4 | Complete
2025-08-19 | 2025-08-16 | 2025-08-19 | Pusplata Deepak | 38.847 | 9.7118 | TB401 | 24/1 | Complete
2025-08-19 | 2025-08-19 | 2025-08-22 | Satyam Manish | 37.504 | 9.376 | TB401 | 32/7 | Complete
2025-08-19 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401 | 27/1 | Complete
2025-08-19 | 2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401 | 2/3 | Complete
2025-08-20 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401 | 2/0 | Complete
2025-08-20 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401 | 18/0 | Complete
2025-08-20 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-20 | 2025-08-19 | 2025-08-22 | Satyam Manish | 37.504 | 9.376 | TB401 | 32/7 | Complete
2025-08-20 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401 | 27/1 | Complete
2025-08-20 | 2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401 | 2/3 | Complete
2025-08-21 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401 | 2/0 | Complete
2025-08-21 | 2025-08-21 | 2025-08-25 | Priyanka Devi 2 | 37.504 | 7.5008 | TB401 | 18/9 | Complete
2025-08-21 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401 | 18/0 | Complete
2025-08-21 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-21 | 2025-08-21 | 2025-08-24 | Pusplata Deepak | 37.504 | 9.376 | TB401 | 25/2 | Complete
2025-08-21 | 2025-08-19 | 2025-08-22 | Satyam Manish | 37.504 | 9.376 | TB401 | 32/7 | Complete
2025-08-21 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401 | 27/1 | Complete
2025-08-21 | 2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401 | 2/3 | Complete
2025-08-21 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401 | 2/4 | Complete
2025-08-22 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401 | 2/0 | Complete
2025-08-22 | 2025-08-21 | 2025-08-25 | Priyanka Devi 2 | 37.504 | 7.5008 | TB401 | 18/9 | Complete
2025-08-22 | 2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401 | 18/0 | Complete
2025-08-22 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-22 | 2025-08-21 | 2025-08-24 | Pusplata Deepak | 37.504 | 9.376 | TB401 | 25/2 | Complete
2025-08-22 | 2025-08-19 | 2025-08-22 | Satyam Manish | 37.504 | 9.376 | TB401 | 32/7 | Complete
2025-08-22 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401 | 27/1 | Complete
2025-08-22 | 2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401 | 2/3 | Complete
2025-08-22 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401 | 2/4 | Complete
2025-08-22 | 2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401 | 2/6 | Complete
2025-08-23 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401 | 2/0 | Complete
2025-08-23 | 2025-08-21 | 2025-08-25 | Priyanka Devi 2 | 37.504 | 7.5008 | TB401 | 18/9 | Complete
2025-08-23 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-23 | 2025-08-21 | 2025-08-24 | Pusplata Deepak | 37.504 | 9.376 | TB401 | 25/2 | Complete
2025-08-23 | 2025-08-23 | 2025-08-27 | Satyam Manish |  |  | TB401 | 32/8 | Complete
2025-08-23 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401 | 27/1 | Complete
2025-08-23 | 2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401 | 2/3 | Complete
2025-08-23 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401 | 2/4 | Complete
2025-08-23 | 2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401 | 2/6 | Complete
2025-08-24 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401 | 2/0 | Complete
2025-08-24 | 2025-08-21 | 2025-08-25 | Priyanka Devi 2 | 37.504 | 7.5008 | TB401 | 18/9 | Complete
2025-08-24 | 2025-08-24 | 2025-08-30 | Priyanka Devi Sudheer | 66.381 | 9.483 | TB401 | 19/0 | Complete
2025-08-24 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-24 | 2025-08-21 | 2025-08-24 | Pusplata Deepak | 37.504 | 9.376 | TB401 | 25/2 | Complete
2025-08-24 | 2025-08-23 | 2025-08-27 | Satyam Manish |  |  | TB401 | 32/8 | Complete
2025-08-24 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401 | 27/1 | Complete
2025-08-24 | 2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401 | 2/3 | Complete
2025-08-24 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401 | 2/4 | Complete
2025-08-24 | 2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401 | 2/6 | Complete
2025-08-25 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401 | 2/0 | Complete
2025-08-25 | 2025-08-21 | 2025-08-25 | Priyanka Devi 2 | 37.504 | 7.5008 | TB401 | 18/9 | Complete
2025-08-25 | 2025-08-24 | 2025-08-30 | Priyanka Devi Sudheer | 66.381 | 9.483 | TB401 | 19/0 | Complete
2025-08-25 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-25 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401 | 28/5 | Complete
2025-08-25 | 2025-08-23 | 2025-08-27 | Satyam Manish |  |  | TB401 | 32/8 | Complete
2025-08-25 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401 | 27/1 | Complete
2025-08-25 | 2025-08-25 | 2025-08-31 | Sital Singh | 37.504 | 5.3577 | TB401 | 2/1 | Complete
2025-08-25 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401 | 2/4 | Complete
2025-08-25 | 2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401 | 2/6 | Complete
2025-08-26 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401 | 2/0 | Complete
2025-08-26 | 2025-08-24 | 2025-08-30 | Priyanka Devi Sudheer | 66.381 | 9.483 | TB401 | 19/0 | Complete
2025-08-26 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-26 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401 | 28/5 | Complete
2025-08-26 | 2025-08-23 | 2025-08-27 | Satyam Manish |  |  | TB401 | 32/8 | Complete
2025-08-26 | 2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401 | 27/1 | Complete
2025-08-26 | 2025-08-25 | 2025-08-31 | Sital Singh | 37.504 | 5.3577 | TB401 | 2/1 | Complete
2025-08-26 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401 | 2/4 | Complete
2025-08-26 | 2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401 | 2/6 | Complete
2025-08-27 | 2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401 | 2/0 | Complete
2025-08-27 | 2025-08-24 | 2025-08-30 | Priyanka Devi Sudheer | 66.381 | 9.483 | TB401 | 19/0 | Complete
2025-08-27 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-27 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401 | 28/5 | Complete
2025-08-27 | 2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401 | 26/6 | Complete
2025-08-27 | 2025-08-23 | 2025-08-27 | Satyam Manish |  |  | TB401 | 32/8 | Complete
2025-08-27 | 2025-08-27 | 2025-08-31 | Satyam Vijay | 38.847 | 7.7694 | TB401 | 26/7 | Complete
2025-08-27 | 2025-08-25 | 2025-08-31 | Sital Singh | 37.504 | 5.3577 | TB401 | 2/1 | Complete
2025-08-27 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401 | 2/4 | Complete
2025-08-27 | 2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401 | 2/6 | Complete
2025-08-28 | 2025-08-24 | 2025-08-30 | Priyanka Devi Sudheer | 66.381 | 9.483 | TB401 | 19/0 | Complete
2025-08-28 | 2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-28 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401 | 28/5 | Complete
2025-08-28 | 2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401 | 26/6 | Complete
2025-08-28 | 2025-08-27 | 2025-08-31 | Satyam Vijay | 38.847 | 7.7694 | TB401 | 26/7 | Complete
2025-08-28 | 2025-08-25 | 2025-08-31 | Sital Singh | 37.504 | 5.3577 | TB401 | 2/1 | Complete
2025-08-28 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401 | 2/4 | Complete
2025-08-28 | 2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401 | 2/6 | Complete
2025-08-29 | 2025-08-24 | 2025-08-30 | Priyanka Devi Sudheer | 66.381 | 9.483 | TB401 | 19/0 | Complete
2025-08-29 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401 | 28/5 | Complete
2025-08-29 | 2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401 | 26/6 | Complete
2025-08-29 | 2025-08-27 | 2025-08-31 | Satyam Vijay | 38.847 | 7.7694 | TB401 | 26/7 | Complete
2025-08-29 | 2025-08-25 | 2025-08-31 | Sital Singh | 37.504 | 5.3577 | TB401 | 2/1 | Complete
2025-08-29 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401 | 2/4 | Complete
2025-08-29 | 2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401 | 2/6 | Complete
2025-08-30 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401 | 2/2 | Complete
2025-08-30 | 2025-08-24 | 2025-08-30 | Priyanka Devi Sudheer | 66.381 | 9.483 | TB401 | 19/0 | Complete
2025-08-30 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401 | 28/5 | Complete
2025-08-30 | 2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401 | 26/6 | Complete
2025-08-30 | 2025-08-27 | 2025-08-31 | Satyam Vijay | 38.847 | 7.7694 | TB401 | 26/7 | Complete
2025-08-30 | 2025-08-25 | 2025-08-31 | Sital Singh | 37.504 | 5.3577 | TB401 | 2/1 | Complete
2025-08-30 | 2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401 | 2/4 | Complete
2025-08-31 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401 | 2/2 | Complete
2025-08-31 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401 | 28/5 | Complete
2025-08-31 | 2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401 | 26/6 | Complete
2025-08-31 | 2025-08-27 | 2025-08-31 | Satyam Vijay | 38.847 | 7.7694 | TB401 | 26/7 | Complete
2025-08-31 | 2025-08-25 | 2025-08-31 | Sital Singh | 37.504 | 5.3577 | TB401 | 2/1 | Complete
2025-08-31 | 2025-08-31 | 2025-09-05 | Usha Tower | 38.847 | 6.4745 | TB401 | 6/2 | Complete
2025-09-01 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401 | 2/2 | Complete
2025-09-01 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401 | 28/5 | Complete
2025-09-01 | 2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401 | 26/6 | Complete
2025-09-01 | 2025-08-31 | 2025-09-05 | Usha Tower | 38.847 | 6.4745 | TB401 | 6/2 | Complete
2025-09-02 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401 | 2/2 | Complete
2025-09-02 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401 | 21/13 | Complete
2025-09-02 | 2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401 | 28/5 | Complete
2025-09-02 | 2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401 | 26/6 | Complete
2025-09-02 | 2025-08-31 | 2025-09-05 | Usha Tower | 38.847 | 6.4745 | TB401 | 6/2 | Complete
2025-09-03 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401 | 2/2 | Complete
2025-09-03 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401 | 21/13 | Complete
2025-09-03 | 2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401 | 26/6 | Complete
2025-09-03 | 2025-08-31 | 2025-09-05 | Usha Tower | 38.847 | 6.4745 | TB401 | 6/2 | Complete
2025-09-04 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401 | 2/2 | Complete
2025-09-04 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401 | 6/0 | Complete
2025-09-04 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401 | 21/13 | Complete
2025-09-04 | 2025-08-31 | 2025-09-05 | Usha Tower | 38.847 | 6.4745 | TB401 | 6/2 | Complete
2025-09-05 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401 | 2/2 | Complete
2025-09-05 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401 | 6/0 | Complete
2025-09-05 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401 | 21/13 | Complete
2025-09-05 | 2025-09-05 | 2025-09-09 | Rahul Kumar | 37.504 | 7.5008 | TB401 | 28/7 | Complete
2025-09-05 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401 | 26/5 | Complete
2025-09-05 | 2025-08-31 | 2025-09-05 | Usha Tower | 38.847 | 6.4745 | TB401 | 6/2 | Complete
2025-09-06 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401 | 2/2 | Complete
2025-09-06 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401 | 6/0 | Complete
2025-09-06 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401 | 21/13 | Complete
2025-09-06 | 2025-09-05 | 2025-09-09 | Rahul Kumar | 37.504 | 7.5008 | TB401 | 28/7 | Complete
2025-09-06 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401 | 26/5 | Complete
2025-09-07 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401 | 2/2 | Complete
2025-09-07 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401 | 6/0 | Complete
2025-09-07 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401 | 21/13 | Complete
2025-09-07 | 2025-09-05 | 2025-09-09 | Rahul Kumar | 37.504 | 7.5008 | TB401 | 28/7 | Complete
2025-09-07 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401 | 26/5 | Complete
2025-09-08 | 2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401 | 2/2 | Complete
2025-09-08 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401 | 6/0 | Complete
2025-09-08 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401 | 21/13 | Complete
2025-09-08 | 2025-09-05 | 2025-09-09 | Rahul Kumar | 37.504 | 7.5008 | TB401 | 28/7 | Complete
2025-09-08 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401 | 26/5 | Complete
2025-09-09 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401 | 6/0 | Complete
2025-09-09 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401 | 21/13 | Complete
2025-09-09 | 2025-09-05 | 2025-09-09 | Rahul Kumar | 37.504 | 7.5008 | TB401 | 28/7 | Complete
2025-09-09 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401 | 26/5 | Complete
2025-09-10 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401 | 6/0 | Complete
2025-09-10 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401 | 21/13 | Complete
2025-09-10 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401 | 26/5 | Complete
2025-09-11 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401 | 6/0 | Complete
2025-09-11 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401 | 21/13 | Complete
2025-09-11 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401 | 26/5 | Complete
2025-09-11 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401 | 10/17 | Complete
2025-09-12 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401 | 6/0 | Complete
2025-09-12 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401 | 21/13 | Complete
2025-09-12 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401 | 26/5 | Complete
2025-09-12 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401 | 10/17 | Complete
2025-09-13 | 2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401 | 6/0 | Complete
2025-09-13 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401 | 21/13 | Complete
2025-09-13 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401 | 26/5 | Complete
2025-09-13 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401 | 10/17 | Complete
2025-09-14 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401 | 21/13 | Complete
2025-09-14 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401 | 26/5 | Complete
2025-09-14 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401 | 10/17 | Complete
2025-09-15 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401 | 21/13 | Complete
2025-09-15 | 2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401 | 26/5 | Complete
2025-09-15 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401 | 10/17 | Complete
2025-09-15 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401 | 6/1 | Complete
2025-09-16 | 2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401 | 21/13 | Complete
2025-09-16 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401 | 10/17 | Complete
2025-09-16 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401 | 6/1 | Complete
2025-09-17 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401 | 10/17 | Complete
2025-09-17 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401 | 6/1 | Complete
2025-09-18 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401 | 10/17 | Complete
2025-09-18 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401 | 6/1 | Complete
2025-09-19 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401 | 10/17 | Complete
2025-09-19 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401 | 6/1 | Complete
2025-09-20 | 2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401 | 10/17 | Complete
2025-09-20 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401 | 6/1 | Complete
2025-09-21 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401 | 10/16 | Complete
2025-09-21 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401 | 6/1 | Complete
2025-09-22 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401 | 10/16 | Complete
2025-09-22 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401 | 6/1 | Complete
2025-09-23 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401 | 10/16 | Complete
2025-09-23 | 2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401 | 6/1 | Complete
2025-09-24 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401 | 10/16 | Complete
2025-09-25 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401 | 10/16 | Complete
2025-09-26 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401 | 10/16 | Complete
2025-09-27 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401 | 10/16 | Complete
2025-09-28 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401 | 10/16 | Complete
2025-09-29 | 2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401 | 10/16 | Complete
2023-09-30 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-01 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-02 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-03 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-04 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-05 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-06 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-07 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-08 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-09 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-10 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-11 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-12 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-13 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-14 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-15 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-16 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-17 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-18 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-19 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-20 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-21 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-22 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-23 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-24 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-25 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-26 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-27 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-28 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-29 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-11-01 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-02 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-03 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-04 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-05 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-06 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-07 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-08 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-09 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-11 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-12 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-13 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-14 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-15 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-16 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-17 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-19 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-20 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-21 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-22 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-23 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-24 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-25 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-26 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-27 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-28 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-29 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-30 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-12-01 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-12-02 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-03 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-04 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-05 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-06 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-07 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-08 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-09 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-10 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-11 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-12 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-13 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-14 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-15 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2024-01-04 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-05 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-06 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-07 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-08 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-09 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-10 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-11 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-12 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-12 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-13 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-14 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-15 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-16 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-17 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-18 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-18 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-19 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-20 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-21 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-22 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-23 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-23 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-24 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-25 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-26 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-27 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-28 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-28 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-01-29 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-01-30 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-01-31 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-02-01 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-02-02 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-02-02 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-03 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-04 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-04 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-04 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-05 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-05 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-05 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-06 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-06 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-06 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-07 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-07 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-07 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-08 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-08 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-08 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-09 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-09 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-09 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-10 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-10 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-11 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-11 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-12 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-12 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-13 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-13 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-13 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-14 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-14 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-15 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-15 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-15 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-16 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-16 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-17 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-17 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-18 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-18 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-19 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-19 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-20 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-20 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-20 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-20 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-21 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-21 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-21 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-22 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-22 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-23 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-23 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-24 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-24 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-25 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-25 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-26 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-26 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-26 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-02-27 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-27 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-02-27 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-02-28 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-28 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-02-28 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-02-29 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-02-29 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-03-01 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-03-01 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-03-02 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-03-02 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-03-02 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-03 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-03-03 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-03 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-04 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-04 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-05 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-05 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-06 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-06 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-07 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-07 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-08 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-08 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-08 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-09 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-09 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-10 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-10 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-11 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-11 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-12 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-12 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-13 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-13 | 2024-03-13 | 2024-03-13 | Lalan Mahto | 37.73 | 37.73 | TA325 | 133A/1 | Completed
2024-03-13 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-14 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-15 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-16 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-17 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-18 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-19 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-20 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-21 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-22 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-23 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-24 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-25 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-26 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-27 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-28 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-29 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-30 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-31 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-01 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-02 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-03 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-04 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-05 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-06 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-07 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-08 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-09 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-10 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-11 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-13 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-14 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-15 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-16 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-17 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-18 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-19 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-20 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325 | 133/4 | Completed
2024-04-21 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325 | 133/4 | Completed
2024-04-22 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325 | 133/4 | Completed
2024-04-23 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325 | 133/4 | Completed
2024-04-24 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325 | 133/4 | Completed
2024-04-25 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-04-26 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-04-27 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-04-28 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-04-29 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-04-30 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-05-01 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-02 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-02 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-03 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-03 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-04 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-04 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-05 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-05 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-06 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-06 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-07 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-07 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-07 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-07 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-07 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-08 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-08 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-08 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-08 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-09 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-09 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-09 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-09 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-10 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-10 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-10 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-10 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-11 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-11 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-11 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-11 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-12 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-12 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-12 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-12 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-13 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-13 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-13 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-14 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-14 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-14 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-15 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-15 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-15 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-16 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-16 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-16 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-17 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-17 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-17 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-18 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-18 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-18 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-19 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-19 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-19 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-19 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-20 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-20 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-20 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-21 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-21 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-21 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-22 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-22 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-22 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-23 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-23 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-23 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-24 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-24 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-24 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-25 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-25 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-25 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-26 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-26 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-26 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-27 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-27 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-27 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-28 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-28 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-28 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-29 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-29 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-29 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-30 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-30 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-30 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-31 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-31 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-05-31 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-31 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-05-31 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-06-01 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-01 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-02 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-02 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-03 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-03 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-04 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-04 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-05 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-05 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-05 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-06 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-06 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-06 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-07 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-07 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-07 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-08 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-08 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-08 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-09 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-09 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-09 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-10 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-10 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-10 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-11 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-11 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/2 | Completed
2024-06-12 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-12 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-12 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/2 | Completed
2024-06-13 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-13 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-13 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/2 | Completed
2024-06-13 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325 | 144/3 | Completed
2024-06-14 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-14 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-14 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/2 | Completed
2024-06-14 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325 | 144/3 | Completed
2024-06-15 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-15 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-15 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/2 | Completed
2024-06-15 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325 | 144/3 | Completed
2024-06-16 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-16 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-16 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/4 | Completed
2024-06-17 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-17 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-17 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/4 | Completed
2024-06-18 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-18 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-18 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/4 | Completed
2024-06-19 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-19 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/4 | Completed
2024-06-20 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-20 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/4 | Completed
2024-06-21 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-21 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-22 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-22 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-23 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-23 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-24 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-24 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-25 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-25 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-26 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-26 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-27 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-28 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-29 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-30 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-30 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-01 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-07-01 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-02 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-07-02 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-02 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-03 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-03 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-04 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-04 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-05 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-05 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-06 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-07 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-08 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-08 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-08 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325 | 119/2 | Completed
2024-07-08 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-09 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-09 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-09 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325 | 119/2 | Completed
2024-07-09 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-10 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-10 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-10 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-10 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325 | 119/2 | Completed
2024-07-10 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-11 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-11 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-11 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-11 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325 | 119/2 | Completed
2024-07-11 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-12 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-12 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-12 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-12 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325 | 119/2 | Completed
2024-07-12 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-13 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-13 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-13 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-13 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-13 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-14 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-14 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-14 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-14 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-14 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-15 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-15 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-15 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-15 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-15 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-16 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-16 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-16 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-16 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-16 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-17 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-17 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-17 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-17 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-17 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-18 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-18 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-18 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-18 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-18 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-19 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-19 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-19 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-19 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-20 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-20 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-20 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-20 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-20 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-21 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-21 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-21 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-21 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-21 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-22 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-22 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-22 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-22 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-22 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-23 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-23 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-23 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-23 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-23 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-24 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-24 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-24 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-24 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-25 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-25 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-25 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-25 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-26 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-26 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-26 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-27 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-27 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-27 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-27 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-07-28 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed.
2024-07-28 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-28 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-28 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-28 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-07-29 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed.
2024-07-29 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-29 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-29 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-29 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-07-30 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed.
2024-07-30 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-30 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed.
2024-07-30 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-30 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-07-31 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed.
2024-07-31 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-31 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed.
2024-07-31 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-31 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-01 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed.
2024-08-01 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-01 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed.
2024-08-01 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-01 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-02 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed.
2024-08-02 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-02 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed.
2024-08-02 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-02 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-03 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed.
2024-08-03 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-03 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed.
2024-08-03 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-03 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-04 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed.
2024-08-04 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-04 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed.
2024-08-04 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-04 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-05 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed.
2024-08-05 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-05 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed.
2024-08-05 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-05 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-06 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed.
2024-08-06 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-06 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed.
2024-08-06 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-06 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-07 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed.
2024-08-07 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-07 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed.
2024-08-07 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-07 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-08 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed.
2024-08-08 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-08 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed.
2024-08-08 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-08 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-08-08 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-09 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-09 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed.
2024-08-09 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-09 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-08-09 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-10 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-10 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed.
2024-08-10 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-10 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-08-10 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-11 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-11 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed.
2024-08-11 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-11 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-11 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-08-11 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-12 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-12 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-12 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-12 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-08-12 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-13 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-13 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-13 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-13 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-08-13 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-14 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-14 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-14 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-14 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-08-14 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-08-15 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-15 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-15 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-15 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-08-15 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-08-16 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-16 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-16 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-16 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-08-16 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-08-17 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-17 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-17 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-17 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-08-17 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-08-18 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-18 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-18 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-18 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-08-18 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-18 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-08-19 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-19 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-19 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-19 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-08-19 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-19 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-08-20 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-20 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-20 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-08-20 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-08-20 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-20 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-08-21 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-21 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-21 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-08-21 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-21 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-08-21 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-08-22 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-22 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-22 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-08-22 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-22 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-08-22 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-08-23 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-23 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-08-23 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-23 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-08-23 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-08-24 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-08-24 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-24 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-08-24 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-08-25 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-25 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-08-25 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-08-26 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-26 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-08-26 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-08-27 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-27 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-08-27 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-08-28 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-28 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-08-28 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-08-29 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-29 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-08-29 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-08-30 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-08-30 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-30 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-08-30 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-08-31 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-08-31 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-31 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-08-31 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-09-01 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-01 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-09-01 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-09-02 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-02 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-02 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-09-02 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-09-03 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-03 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-03 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-09-03 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-09-04 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-04 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-04 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-09-04 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-09-05 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-05 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-05 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-09-05 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-09-06 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-06 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-06 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-09-06 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-09-07 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-07 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-07 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-09-07 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-09-08 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-08 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-08 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-09-08 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2024-09-09 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-09 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-09 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed.
2024-09-09 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-09-09 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-10 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-10 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-10 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-10 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed.
2024-09-10 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-09-10 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-11 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-11 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-11 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-11 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed.
2024-09-11 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-09-11 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-11 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-12 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed.
2024-09-12 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-12 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-12 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-12 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed.
2024-09-12 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-09-12 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-12 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-13 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed.
2024-09-13 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-13 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-13 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-13 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed.
2024-09-13 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-09-13 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-13 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-14 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed.
2024-09-14 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-14 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-14 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed.
2024-09-14 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed.
2024-09-14 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-14 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-09-14 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-15 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed.
2024-09-15 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-15 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-15 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed.
2024-09-15 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed.
2024-09-15 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-15 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-09-15 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-16 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed.
2024-09-16 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed.
2024-09-16 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-16 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-16 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed.
2024-09-16 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed.
2024-09-16 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-16 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-09-16 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed.
2024-09-16 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-17 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed.
2024-09-17 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed.
2024-09-17 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-17 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-17 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed.
2024-09-17 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed.
2024-09-17 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-17 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-09-17 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed.
2024-09-17 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-18 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed.
2024-09-18 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed.
2024-09-18 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-18 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-18 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed.
2024-09-18 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed.
2024-09-18 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-18 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-09-18 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed.
2024-09-18 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-19 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed.
2024-09-19 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed.
2024-09-19 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-19 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-19 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed.
2024-09-19 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed.
2024-09-19 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-19 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-09-19 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed.
2024-09-19 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-20 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed.
2024-09-20 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed.
2024-09-20 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-20 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-20 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed.
2024-09-20 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed.
2024-09-20 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-20 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-09-20 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed.
2024-09-20 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-21 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed.
2024-09-21 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed.
2024-09-21 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-21 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-21 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed.
2024-09-21 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed.
2024-09-21 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-21 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-09-21 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed.
2024-09-22 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed.
2024-09-22 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed.
2024-09-22 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-22 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-22 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed.
2024-09-22 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-22 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-09-22 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed.
2024-09-22 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-23 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed.
2024-09-23 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed.
2024-09-23 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-23 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-23 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-23 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed.
2024-09-23 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-09-23 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-23 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-09-23 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed.
2024-09-23 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-24 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed.
2024-09-24 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed.
2024-09-24 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-24 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-24 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-09-24 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-24 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-09-24 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed.
2024-09-24 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-09-24 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-25 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed.
2024-09-25 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-25 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-25 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-09-25 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-25 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-09-25 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed.
2024-09-25 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-09-25 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-26 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed.
2024-09-26 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed.
2024-09-26 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-26 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-26 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-09-26 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-26 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-09-26 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed.
2024-09-26 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-09-26 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-27 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed.
2024-09-27 | 2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-09-27 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-27 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed.
2024-09-27 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-09-27 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-27 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-09-27 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed.
2024-09-27 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-09-27 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-28 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed.
2024-09-28 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed.
2024-09-28 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-28 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed.
2024-09-28 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-09-28 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-28 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-09-28 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed.
2024-09-28 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-09-28 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-29 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed.
2024-09-29 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed.
2024-09-29 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-29 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed.
2024-09-29 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-09-29 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-29 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-09-29 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed.
2024-09-29 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-09-29 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-30 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed.
2024-09-30 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed.
2024-09-30 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-30 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed.
2024-09-30 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-09-30 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-09-30 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-09-30 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed.
2024-09-30 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-09-30 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-30 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-01 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed.
2024-10-01 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed.
2024-10-01 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-01 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-01 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed.
2024-10-01 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-10-01 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-01 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-01 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-01 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-01 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-02 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed.
2024-10-02 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed.
2024-10-02 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-02 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-02 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed.
2024-10-02 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-10-02 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-02 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-02 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-02 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-02 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-03 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed.
2024-10-03 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed.
2024-10-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-03 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-03 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-03 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed.
2024-10-03 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-10-03 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-03 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-03 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-03 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-03 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-04 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed.
2024-10-04 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed.
2024-10-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-04 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-04 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-04 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed.
2024-10-04 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed.
2024-10-04 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-10-04 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-04 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-04 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-04 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-04 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-05 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed.
2024-10-05 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed.
2024-10-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-05 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-05 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-05 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed.
2024-10-05 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed.
2024-10-05 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-10-05 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-05 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-05 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-05 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-05 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-06 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed.
2024-10-06 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed.
2024-10-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-06 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-06 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-06 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed.
2024-10-06 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed.
2024-10-06 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-10-06 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-06 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-06 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-06 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-06 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-07 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed.
2024-10-07 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed.
2024-10-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-07 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-07 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-07 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed.
2024-10-07 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed.
2024-10-07 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-10-07 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-07 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-07 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-07 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-07 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-08 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed.
2024-10-08 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-08 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed.
2024-10-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-08 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-08 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-08 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed.
2024-10-08 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed.
2024-10-08 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-10-08 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-08 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-08 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-08 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-08 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-09 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed.
2024-10-09 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-09 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed.
2024-10-09 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-09 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-09 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-09 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed.
2024-10-09 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed.
2024-10-09 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-10-09 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-09 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-09 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-09 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-09 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-09 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-10 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed.
2024-10-10 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-10 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed.
2024-10-10 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-10 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-10 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-10 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed.
2024-10-10 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed.
2024-10-10 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-10-10 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-10 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-10 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-10 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-10 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-11 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-11 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed.
2024-10-11 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-11 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-11 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-11 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed.
2024-10-11 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed.
2024-10-11 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-11 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-11 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-11 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-11 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-12 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-12 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed.
2024-10-12 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-12 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-12 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-12 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed.
2024-10-12 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed.
2024-10-12 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-12 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-12 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-12 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-12 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-13 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-13 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-13 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed.
2024-10-13 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-13 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-13 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-13 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed.
2024-10-13 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-13 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-13 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-13 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-13 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-14 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-14 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-14 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-14 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-14 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-14 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed.
2024-10-14 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-14 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-14 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-14 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-14 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-15 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-15 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-15 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-15 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-15 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-15 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed.
2024-10-15 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-10-15 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-15 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-15 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-15 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-15 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-15 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-16 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-16 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-16 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-16 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-16 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-16 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-10-16 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-16 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-16 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-16 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-16 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-16 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-17 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-17 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-17 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-17 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-17 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-17 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-17 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-10-17 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-17 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-17 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-17 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-17 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-17 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-18 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-18 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-18 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-18 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-18 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-18 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-18 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-10-18 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-18 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-18 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-18 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-18 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-18 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-19 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-19 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-19 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-19 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-19 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-19 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-19 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-10-19 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-19 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-19 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-19 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-19 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-19 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-20 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-20 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-20 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-20 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-20 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-20 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-20 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-10-20 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-20 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-20 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-20 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-20 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-20 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-21 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-21 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-21 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-21 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-21 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-21 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-21 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-10-21 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-21 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-21 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-21 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-21 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-21 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-22 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-22 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-22 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-22 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-22 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-22 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-22 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-10-22 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-22 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-22 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-22 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-22 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-22 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-23 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-23 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-23 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-23 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-23 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-23 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-23 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-10-23 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-23 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-10-23 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-23 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-23 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-23 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-23 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-24 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-24 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-24 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-24 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-24 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-24 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-24 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-10-24 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-24 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-10-24 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-24 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-24 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-24 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-24 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-25 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-25 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-25 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-25 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed.
2024-10-25 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-25 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-10-25 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-25 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-10-25 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-25 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-25 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-25 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-25 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-26 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-26 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-26 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-26 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed.
2024-10-26 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-26 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-10-26 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-26 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-10-26 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-26 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-26 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-26 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-26 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-27 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-27 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-27 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-27 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed.
2024-10-27 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-27 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-10-27 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-27 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-10-27 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-27 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-27 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-27 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-27 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-28 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-28 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed.
2024-10-28 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-28 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-28 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed.
2024-10-28 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-28 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-10-28 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-28 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-10-28 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-28 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2024-10-28 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-28 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2024-10-28 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-29 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-29 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed.
2024-10-29 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-29 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-29 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed.
2024-10-29 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-29 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-10-29 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-29 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-10-29 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-29 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-29 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-29 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-10-30 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-30 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed.
2024-10-30 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-30 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-30 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed.
2024-10-30 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-30 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-10-30 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-30 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-10-30 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-30 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-30 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2024-10-30 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-30 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-10-31 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-10-31 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed.
2024-10-31 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-10-31 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-10-31 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed.
2024-10-31 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-31 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-10-31 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-31 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-10-31 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-10-31 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-31 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2024-10-31 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-10-31 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-01 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed.
2024-11-01 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-11-01 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-01 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed.
2024-11-01 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-11-01 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-11-01 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-11-01 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2024-11-01 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-02 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed.
2024-11-02 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-11-02 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-02 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed.
2024-11-02 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed.
2024-11-02 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-11-02 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed.
2024-11-02 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-11-02 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-11-02 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2024-11-02 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-03 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed.
2024-11-03 | 2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-11-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-03 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed.
2024-11-03 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed.
2024-11-03 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-11-03 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed.
2024-11-03 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-11-03 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-11-03 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2024-11-03 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-04 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed.
2024-11-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-04 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed.
2024-11-04 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed.
2024-11-04 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-11-04 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed.
2024-11-04 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-11-04 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-04 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-11-04 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2024-11-04 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-05 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed.
2024-11-05 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed.
2024-11-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-05 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed.
2024-11-05 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed.
2024-11-05 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-11-05 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed.
2024-11-05 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-11-05 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-05 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-11-05 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2024-11-05 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-06 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed.
2024-11-06 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed.
2024-11-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-06 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed.
2024-11-06 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed.
2024-11-06 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-11-06 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed.
2024-11-06 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-11-06 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-06 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-11-06 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2024-11-06 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-07 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed.
2024-11-07 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed.
2024-11-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-07 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed.
2024-11-07 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed.
2024-11-07 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-11-07 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed.
2024-11-07 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-11-07 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-07 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-11-07 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2024-11-07 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-08 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed.
2024-11-08 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed.
2024-11-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-08 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed.
2024-11-08 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-11-08 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-11-08 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-08 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2024-11-08 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-09 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed.
2024-11-09 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed.
2024-11-09 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-09 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed.
2024-11-09 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-11-09 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-11-09 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-09 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2024-11-09 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-10 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed.
2024-11-10 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-10 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed.
2024-11-10 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-10 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed.
2024-11-10 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-10 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-11-10 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-11-10 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-10 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed.
2024-11-10 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2024-11-10 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-11 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed.
2024-11-11 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-11 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed.
2024-11-11 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-11 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed.
2024-11-11 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-11 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-11-11 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-11-11 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-11 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed.
2024-11-11 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2024-11-11 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-12 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-12 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed.
2024-11-12 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-12 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed.
2024-11-12 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-12 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-11-12 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-11-12 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-12 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed.
2024-11-12 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2024-11-12 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-13 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed.
2024-11-13 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-13 | 2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed.
2024-11-13 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-13 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed.
2024-11-13 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-13 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-13 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-11-13 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-13 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-13 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed.
2024-11-13 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2024-11-13 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-14 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed.
2024-11-14 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-14 | 2024-11-14 | 2024-11-20 | Dhaneshwar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed.
2024-11-14 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-14 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-14 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-14 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-11-14 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-14 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-14 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed.
2024-11-14 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2024-11-14 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-15 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed.
2024-11-15 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-15 | 2024-11-14 | 2024-11-20 | Dhaneshwar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed.
2024-11-15 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-15 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-15 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-15 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-11-15 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-15 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-15 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed.
2024-11-15 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2024-11-15 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-16 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed.
2024-11-16 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-16 | 2024-11-14 | 2024-11-20 | Dhaneshwar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed.
2024-11-16 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-16 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-16 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-16 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-11-16 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-16 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed.
2024-11-16 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed.
2024-11-16 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-11-16 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-16 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed.
2024-11-16 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed.
2024-11-16 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-17 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed.
2024-11-17 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-17 | 2024-11-14 | 2024-11-20 | Dhaneshwar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed.
2024-11-17 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-17 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-17 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-17 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-17 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed.
2024-11-17 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed.
2024-11-17 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-11-17 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-17 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed.
2024-11-17 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed.
2024-11-17 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-11-18 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed.
2024-11-18 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-18 | 2024-11-14 | 2024-11-20 | Dhaneshwar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed.
2024-11-18 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-18 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-18 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-18 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed.
2024-11-18 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-11-18 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-18 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed.
2024-11-18 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed.
2024-11-18 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-11-18 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-18 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed.
2024-11-18 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed.
2024-11-18 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-11-19 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed.
2024-11-19 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-19 | 2024-11-14 | 2024-11-20 | Dhaneshwar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed.
2024-11-19 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-19 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-19 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-19 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed.
2024-11-19 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-11-19 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-19 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed.
2024-11-19 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed.
2024-11-19 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-11-19 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-19 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed.
2024-11-19 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed.
2024-11-19 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-11-20 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed.
2024-11-20 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-20 | 2024-11-14 | 2024-11-20 | Dhaneshwar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed.
2024-11-20 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed.
2024-11-20 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-20 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed.
2024-11-20 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-20 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-20 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed.
2024-11-20 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-11-20 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-20 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed.
2024-11-20 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed.
2024-11-20 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-11-20 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-20 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed.
2024-11-20 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed.
2024-11-20 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-11-21 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed.
2024-11-21 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-21 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed.
2024-11-21 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-21 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed.
2024-11-21 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-21 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-21 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed.
2024-11-21 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-11-21 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-21 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed.
2024-11-21 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed.
2024-11-21 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-11-21 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-21 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed.
2024-11-21 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed.
2024-11-21 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-11-22 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed.
2024-11-22 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-11-22 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-22 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed.
2024-11-22 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-22 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed.
2024-11-22 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325 | 187/3 | Completed.
2024-11-22 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-22 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed.
2024-11-22 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-22 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed.
2024-11-22 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-11-22 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-22 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed.
2024-11-22 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed.
2024-11-22 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-11-22 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed.
2024-11-22 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed.
2024-11-22 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-11-23 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed.
2024-11-23 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-11-23 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-23 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed.
2024-11-23 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-23 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-11-23 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed.
2024-11-23 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325 | 187/3 | Completed.
2024-11-23 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-23 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed.
2024-11-23 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-23 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed.
2024-11-23 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-11-23 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-23 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed.
2024-11-23 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-11-23 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed.
2024-11-23 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed.
2024-11-23 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-11-24 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed.
2024-11-24 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-11-24 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-24 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed.
2024-11-24 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-24 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-11-24 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed.
2024-11-24 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325 | 187/3 | Completed.
2024-11-24 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-24 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed.
2024-11-24 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-24 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed.
2024-11-24 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-11-24 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-24 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed.
2024-11-24 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-11-24 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed.
2024-11-24 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed.
2024-11-24 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-11-25 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed.
2024-11-25 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-11-25 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-25 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed.
2024-11-25 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-25 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-11-25 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed.
2024-11-25 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325 | 187/3 | Completed.
2024-11-25 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-25 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed.
2024-11-25 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-25 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-11-25 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-25 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed.
2024-11-25 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-11-25 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed.
2024-11-25 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed.
2024-11-25 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-11-26 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed.
2024-11-26 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-11-26 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-26 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed.
2024-11-26 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-26 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-11-26 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed.
2024-11-26 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325 | 187/3 | Completed.
2024-11-26 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-26 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed.
2024-11-26 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-26 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-11-26 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-26 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed.
2024-11-26 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-11-26 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed.
2024-11-26 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed.
2024-11-26 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-11-27 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed.
2024-11-27 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-11-27 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-27 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed.
2024-11-27 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-27 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-11-27 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed.
2024-11-27 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed.
2024-11-27 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-27 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed.
2024-11-27 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-27 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-11-27 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-27 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed.
2024-11-27 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-11-27 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-11-27 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed.
2024-11-27 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed.
2024-11-27 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-11-28 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed.
2024-11-28 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-11-28 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-28 | 2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed.
2024-11-28 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-28 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-11-28 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed.
2024-11-28 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed.
2024-11-28 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-28 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed.
2024-11-28 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-28 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-11-28 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-11-28 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-11-28 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-28 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed.
2024-11-28 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-11-28 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-11-28 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed.
2024-11-28 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-11-28 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-11-29 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed.
2024-11-29 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-11-29 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-29 | 2024-11-29 | 2024-12-03 | Dhaneshwar Mahto | 36.045 | 7.209 | TA325 | 137A/4 | Completed.
2024-11-29 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-29 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-11-29 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed.
2024-11-29 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed.
2024-11-29 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-29 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed.
2024-11-29 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-29 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-11-29 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-11-29 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-11-29 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-29 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed.
2024-11-29 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-11-29 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-11-29 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed.
2024-11-29 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-11-29 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-11-30 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed.
2024-11-30 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-11-30 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-11-30 | 2024-11-29 | 2024-12-03 | Dhaneshwar Mahto | 36.045 | 7.209 | TA325 | 137A/4 | Completed.
2024-11-30 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-11-30 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-11-30 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed.
2024-11-30 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed.
2024-11-30 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-11-30 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed.
2024-11-30 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-11-30 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-11-30 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-11-30 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-11-30 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-30 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed.
2024-11-30 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-11-30 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-11-30 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed.
2024-11-30 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-11-30 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-12-01 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed.
2024-12-01 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-12-01 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-12-01 | 2024-11-29 | 2024-12-03 | Dhaneshwar Mahto | 36.045 | 7.209 | TA325 | 137A/4 | Completed.
2024-12-01 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-12-01 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-01 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed.
2024-12-01 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed.
2024-12-01 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-01 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-12-01 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-12-01 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-01 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-01 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-01 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-12-01 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-01 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed.
2024-12-01 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-12-01 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-12-02 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed.
2024-12-02 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-12-02 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-12-02 | 2024-11-29 | 2024-12-03 | Dhaneshwar Mahto | 36.045 | 7.209 | TA325 | 137A/4 | Completed.
2024-12-02 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-12-02 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-02 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed.
2024-12-02 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed.
2024-12-02 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-02 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed.
2024-12-02 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-12-02 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-12-02 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-02 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-02 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-02 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-12-02 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-02 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed.
2024-12-02 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-12-02 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-12-03 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed.
2024-12-03 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-12-03 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-12-03 | 2024-11-29 | 2024-12-03 | Dhaneshwar Mahto | 36.045 | 7.209 | TA325 | 137A/4 | Completed.
2024-12-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-12-03 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-03 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed.
2024-12-03 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed.
2024-12-03 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-03 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed.
2024-12-03 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-03 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-12-03 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-03 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-03 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-03 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-12-03 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-03 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-03 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-12-03 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-12-04 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed.
2024-12-04 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-12-04 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-12-04 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2024-12-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-12-04 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-04 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-12-04 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed.
2024-12-04 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-04 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed.
2024-12-04 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-04 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-12-04 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-04 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-04 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-04 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-12-04 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-04 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-04 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-12-04 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-12-05 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed.
2024-12-05 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-12-05 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-12-05 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2024-12-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-12-05 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-05 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-12-05 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed.
2024-12-05 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-05 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed.
2024-12-05 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-05 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-12-05 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-05 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-05 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-05 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-12-05 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-05 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-05 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-12-05 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-12-06 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed.
2024-12-06 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-12-06 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-12-06 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2024-12-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-12-06 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-06 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-12-06 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed.
2024-12-06 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-06 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed.
2024-12-06 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-06 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-12-06 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-06 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-06 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-06 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-12-06 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-06 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-06 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-12-06 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-12-07 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed.
2024-12-07 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-12-07 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2024-12-07 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2024-12-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-12-07 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-07 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-12-07 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed.
2024-12-07 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-07 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed.
2024-12-07 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-07 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-12-07 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-07 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-07 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-07 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-12-07 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-07 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-07 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-12-07 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-12-08 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-12-08 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2024-12-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-12-08 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-08 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-12-08 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed.
2024-12-08 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-08 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed.
2024-12-08 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-08 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2024-12-08 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-08 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-08 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-08 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-12-08 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-08 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-08 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed.
2024-12-08 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-12-08 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-12-09 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-12-09 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2024-12-09 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed.
2024-12-09 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-09 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-12-09 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed.
2024-12-09 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-09 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed.
2024-12-09 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed.
2024-12-09 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-09 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed.
2024-12-09 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-09 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-09 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-09 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-12-09 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-09 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-09 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed.
2024-12-09 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-12-09 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-12-10 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-12-10 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2024-12-10 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed.
2024-12-10 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-10 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-12-10 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed.
2024-12-10 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-10 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed.
2024-12-10 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed.
2024-12-10 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-10 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed.
2024-12-10 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed.
2024-12-10 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-10 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-10 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-10 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-12-10 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-10 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-10 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed.
2024-12-10 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-12-10 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-12-11 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-12-11 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed.
2024-12-11 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2024-12-11 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed.
2024-12-11 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-11 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-12-11 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed.
2024-12-11 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-11 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed.
2024-12-11 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed.
2024-12-11 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-11 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed.
2024-12-11 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed.
2024-12-11 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-11 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-11 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-11 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-12-11 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-11 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-11 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed.
2024-12-11 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-12-11 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-12 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-12-12 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed.
2024-12-12 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2024-12-12 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed.
2024-12-12 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-12 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-12-12 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed.
2024-12-12 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-12 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed.
2024-12-12 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed.
2024-12-12 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-12 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed.
2024-12-12 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed.
2024-12-12 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-12 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-12 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-12 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-12-12 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-12 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-12 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed.
2024-12-12 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-12-12 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-13 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-12-13 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed.
2024-12-13 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2024-12-13 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed.
2024-12-13 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-13 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-12-13 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed.
2024-12-13 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-13 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed.
2024-12-13 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed.
2024-12-13 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-13 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed.
2024-12-13 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed.
2024-12-13 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-13 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-13 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-13 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-13 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-13 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed.
2024-12-13 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-12-13 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-14 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2024-12-14 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed.
2024-12-14 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2024-12-14 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed.
2024-12-14 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-14 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-12-14 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed.
2024-12-14 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-14 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed.
2024-12-14 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed.
2024-12-14 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-14 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed.
2024-12-14 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed.
2024-12-14 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-14 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-14 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-14 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-14 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-14 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed.
2024-12-14 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-12-14 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed.
2024-12-14 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-15 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed.
2024-12-15 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2024-12-15 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed.
2024-12-15 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-15 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-12-15 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed.
2024-12-15 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-15 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed.
2024-12-15 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed.
2024-12-15 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-15 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed.
2024-12-15 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed.
2024-12-15 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-15 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-15 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-15 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-15 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-15 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed.
2024-12-15 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed.
2024-12-15 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-16 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed.
2024-12-16 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2024-12-16 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed.
2024-12-16 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-16 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-12-16 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed.
2024-12-16 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-16 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed.
2024-12-16 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed.
2024-12-16 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-16 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed.
2024-12-16 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed.
2024-12-16 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-16 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-16 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-16 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-16 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-16 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed.
2024-12-16 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed.
2024-12-16 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-17 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed.
2024-12-17 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2024-12-17 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed.
2024-12-17 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-17 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-12-17 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed.
2024-12-17 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-17 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed.
2024-12-17 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-17 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed.
2024-12-17 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed.
2024-12-17 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-17 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-17 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-17 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-17 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-17 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed.
2024-12-17 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed.
2024-12-17 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-18 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed.
2024-12-18 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2024-12-18 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed.
2024-12-18 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-18 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-12-18 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed.
2024-12-18 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-18 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed.
2024-12-18 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-18 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed.
2024-12-18 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed.
2024-12-18 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-18 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2024-12-18 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-18 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-18 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-18 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed.
2024-12-18 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed.
2024-12-18 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-19 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed.
2024-12-19 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed.
2024-12-19 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2024-12-19 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed.
2024-12-19 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-19 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-12-19 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed.
2024-12-19 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-19 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed.
2024-12-19 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-19 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed.
2024-12-19 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed.
2024-12-19 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-19 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-19 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-19 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-19 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed.
2024-12-19 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed.
2024-12-19 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-20 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed.
2024-12-20 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed.
2024-12-20 | 2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2024-12-20 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed.
2024-12-20 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-20 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-12-20 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed.
2024-12-20 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-20 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed.
2024-12-20 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-20 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed.
2024-12-20 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed.
2024-12-20 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-20 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-20 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-20 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-20 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed.
2024-12-20 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed.
2024-12-20 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-21 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed.
2024-12-21 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed.
2024-12-21 | 2024-12-21 | 2024-12-26 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed.
2024-12-21 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed.
2024-12-21 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-21 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed.
2024-12-21 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed.
2024-12-21 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed.
2024-12-21 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-21 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed.
2024-12-21 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-21 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed.
2024-12-21 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed.
2024-12-21 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-21 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-21 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2024-12-21 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-21 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed.
2024-12-21 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed.
2024-12-21 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-22 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed.
2024-12-22 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed.
2024-12-22 | 2024-12-21 | 2024-12-26 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed.
2024-12-22 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-22 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-22 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed.
2024-12-22 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed.
2024-12-22 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-22 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed.
2024-12-22 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed.
2024-12-22 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2024-12-22 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed.
2024-12-22 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed.
2024-12-22 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-22 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-22 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-22 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2024-12-22 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed.
2024-12-22 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed.
2024-12-22 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-23 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed.
2024-12-23 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed.
2024-12-23 | 2024-12-21 | 2024-12-26 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed.
2024-12-23 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-23 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-23 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed.
2024-12-23 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed.
2024-12-23 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed.
2024-12-23 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-12-23 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed.
2024-12-23 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed.
2024-12-23 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed.
2024-12-23 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed.
2024-12-23 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed.
2024-12-23 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-23 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-23 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-23 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2024-12-23 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed.
2024-12-23 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed.
2024-12-23 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-24 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed.
2024-12-24 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed.
2024-12-24 | 2024-12-21 | 2024-12-26 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed.
2024-12-24 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-24 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-24 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed.
2024-12-24 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed.
2024-12-24 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed.
2024-12-24 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed.
2024-12-24 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed.
2024-12-24 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed.
2024-12-24 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed.
2024-12-24 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-24 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-24 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-24 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2024-12-24 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed.
2024-12-24 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed.
2024-12-24 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-25 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed.
2024-12-25 | 2024-12-21 | 2024-12-26 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed.
2024-12-25 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-25 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-25 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed.
2024-12-25 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed.
2024-12-25 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed.
2024-12-25 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed.
2024-12-25 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed.
2024-12-25 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed.
2024-12-25 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed.
2024-12-25 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-25 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-25 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-25 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2024-12-25 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed.
2024-12-25 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed.
2024-12-25 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-26 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed.
2024-12-26 | 2024-12-21 | 2024-12-26 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed.
2024-12-26 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-26 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-26 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed.
2024-12-26 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed.
2024-12-26 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed.
2024-12-26 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed.
2024-12-26 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed.
2024-12-26 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed.
2024-12-26 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed.
2024-12-26 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed.
2024-12-26 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-26 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-26 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-26 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2024-12-26 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed.
2024-12-26 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-27 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed.
2024-12-27 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed.
2024-12-27 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-27 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-27 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed.
2024-12-27 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed.
2024-12-27 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed.
2024-12-27 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed.
2024-12-27 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed.
2024-12-27 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed.
2024-12-27 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed.
2024-12-27 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed.
2024-12-27 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-27 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-27 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-27 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2024-12-27 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed.
2024-12-27 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-28 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed.
2024-12-28 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed.
2024-12-28 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed.
2024-12-28 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-28 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2024-12-28 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed.
2024-12-28 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed.
2024-12-28 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed.
2024-12-28 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed.
2024-12-28 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed.
2024-12-28 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed.
2024-12-28 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2024-12-28 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed.
2024-12-28 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-28 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-28 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2024-12-28 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed.
2024-12-28 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2024-12-28 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed.
2024-12-28 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed.
2024-12-28 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-29 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed.
2024-12-29 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed.
2024-12-29 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed.
2024-12-29 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed.
2024-12-29 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed.
2024-12-29 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed.
2024-12-29 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed.
2024-12-29 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed.
2024-12-29 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed.
2024-12-29 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2024-12-29 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed.
2024-12-29 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-12-29 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-29 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed.
2024-12-29 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2024-12-29 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed.
2024-12-29 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed.
2024-12-29 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-30 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2024-12-30 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed.
2024-12-30 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed.
2024-12-30 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed.
2024-12-30 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed.
2024-12-30 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed.
2024-12-30 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed.
2024-12-30 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed.
2024-12-30 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed.
2024-12-30 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2024-12-30 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed.
2024-12-30 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed.
2024-12-30 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-12-30 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed.
2024-12-30 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2024-12-30 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed.
2024-12-30 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed.
2024-12-30 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-31 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2024-12-31 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed.
2024-12-31 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed.
2024-12-31 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed.
2024-12-31 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed.
2024-12-31 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed.
2024-12-31 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed.
2024-12-31 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed.
2024-12-31 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed.
2024-12-31 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed.
2024-12-31 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed.
2024-12-31 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2024-12-31 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed.
2024-12-31 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed.
2024-12-31 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed.
2024-12-31 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed.
2024-12-31 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2024-12-31 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed.
2024-12-31 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2025-01-01 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-01 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed.
2025-01-01 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed.
2025-01-01 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed.
2025-01-01 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed.
2025-01-01 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed.
2025-01-01 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed.
2025-01-01 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed.
2025-01-01 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed.
2025-01-01 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed.
2025-01-01 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed.
2025-01-01 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2025-01-01 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed.
2025-01-01 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed.
2025-01-01 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed.
2025-01-01 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed.
2025-01-01 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-01 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed.
2025-01-01 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed.
2025-01-02 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-02 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed.
2025-01-02 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed.
2025-01-02 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed.
2025-01-02 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed.
2025-01-02 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed.
2025-01-02 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed.
2025-01-02 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed.
2025-01-02 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed.
2025-01-02 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed.
2025-01-02 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed.
2025-01-02 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2025-01-02 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed.
2025-01-02 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed.
2025-01-02 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed.
2025-01-02 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed.
2025-01-02 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-02 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed.
2025-01-02 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed.
2025-01-03 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-03 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed.
2025-01-03 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed.
2025-01-03 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed.
2025-01-03 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed.
2025-01-03 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed.
2025-01-03 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed.
2025-01-03 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed.
2025-01-03 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed.
2025-01-03 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed.
2025-01-03 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed.
2025-01-03 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2025-01-03 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed.
2025-01-03 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed.
2025-01-03 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed.
2025-01-03 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed.
2025-01-03 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-03 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed.
2025-01-03 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed.
2025-01-04 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-04 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed.
2025-01-04 | 2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed.
2025-01-04 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed.
2025-01-04 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed.
2025-01-04 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed.
2025-01-04 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed.
2025-01-04 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed.
2025-01-04 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed.
2025-01-04 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed.
2025-01-04 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2025-01-04 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed.
2025-01-04 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed.
2025-01-04 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed.
2025-01-04 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed.
2025-01-04 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-04 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed.
2025-01-04 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed.
2025-01-05 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-05 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed.
2025-01-05 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed.
2025-01-05 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed.
2025-01-05 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed.
2025-01-05 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed.
2025-01-05 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed.
2025-01-05 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed.
2025-01-05 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2025-01-05 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed.
2025-01-05 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed.
2025-01-05 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed.
2025-01-05 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed.
2025-01-05 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-05 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed.
2025-01-05 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed.
2025-01-06 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-06 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed.
2025-01-06 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed.
2025-01-06 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed.
2025-01-06 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed.
2025-01-06 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed.
2025-01-06 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2025-01-06 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed.
2025-01-06 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed.
2025-01-06 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed.
2025-01-06 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed.
2025-01-06 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-06 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed.
2025-01-06 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed.
2025-01-07 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-07 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed.
2025-01-07 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed.
2025-01-07 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed.
2025-01-07 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed.
2025-01-07 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed.
2025-01-07 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2025-01-07 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed.
2025-01-07 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed.
2025-01-07 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed.
2025-01-07 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed.
2025-01-07 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-07 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed.
2025-01-07 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed.
2025-01-08 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-08 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed.
2025-01-08 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed.
2025-01-08 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed.
2025-01-08 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed.
2025-01-08 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2025-01-08 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed.
2025-01-08 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed.
2025-01-08 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed.
2025-01-08 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed.
2025-01-08 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-08 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed.
2025-01-08 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed.
2025-01-09 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-09 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed.
2025-01-09 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed.
2025-01-09 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed.
2025-01-09 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-01-09 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed.
2025-01-09 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed.
2025-01-09 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed.
2025-01-09 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed.
2025-01-09 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2025-01-09 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed.
2025-01-09 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed.
2025-01-09 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed.
2025-01-09 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-09 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed.
2025-01-09 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed.
2025-01-10 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-10 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed.
2025-01-10 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed.
2025-01-10 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed.
2025-01-10 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed.
2025-01-10 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-01-10 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed.
2025-01-10 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed.
2025-01-10 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed.
2025-01-10 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed.
2025-01-10 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2025-01-10 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed.
2025-01-10 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed.
2025-01-10 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed.
2025-01-10 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed.
2025-01-10 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-10 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed.
2025-01-10 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed.
2025-01-11 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-11 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed.
2025-01-11 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed.
2025-01-11 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed.
2025-01-11 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed.
2025-01-11 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-01-11 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed.
2025-01-11 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed.
2025-01-11 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed.
2025-01-11 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2025-01-11 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed.
2025-01-11 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed.
2025-01-11 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed.
2025-01-11 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-11 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed.
2025-01-11 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed.
2025-01-12 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-12 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed.
2025-01-12 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-12 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed.
2025-01-12 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed.
2025-01-12 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed.
2025-01-12 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-01-12 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed.
2025-01-12 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed.
2025-01-12 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed.
2025-01-12 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed.
2025-01-12 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2025-01-12 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed.
2025-01-12 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed.
2025-01-12 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed.
2025-01-12 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-12 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed.
2025-01-13 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-13 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed.
2025-01-13 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-13 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed.
2025-01-13 | 2025-01-13 | 2025-01-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed.
2025-01-13 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed.
2025-01-13 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed.
2025-01-13 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-01-13 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed.
2025-01-13 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed.
2025-01-13 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed.
2025-01-13 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed.
2025-01-13 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2025-01-13 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed.
2025-01-13 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed.
2025-01-13 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-01-13 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-13 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed.
2025-01-14 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-14 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed.
2025-01-14 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-14 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed.
2025-01-14 | 2025-01-13 | 2025-01-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed.
2025-01-14 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed.
2025-01-14 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-01-14 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed.
2025-01-14 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed.
2025-01-14 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed.
2025-01-14 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed.
2025-01-14 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2025-01-14 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed.
2025-01-14 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed.
2025-01-14 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-01-14 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-14 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed.
2025-01-15 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-15 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed.
2025-01-15 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-15 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed.
2025-01-15 | 2025-01-13 | 2025-01-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed.
2025-01-15 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed.
2025-01-15 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-01-15 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed.
2025-01-15 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed.
2025-01-15 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed.
2025-01-15 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed.
2025-01-15 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2025-01-15 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed.
2025-01-15 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed.
2025-01-15 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-01-15 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-15 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed.
2025-01-16 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-16 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed.
2025-01-16 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-16 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed.
2025-01-16 | 2025-01-13 | 2025-01-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed.
2025-01-16 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed.
2025-01-16 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-01-16 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed.
2025-01-16 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed.
2025-01-16 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed.
2025-01-16 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed.
2025-01-16 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2025-01-16 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed.
2025-01-16 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed.
2025-01-16 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed.
2025-01-16 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-01-16 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-16 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed.
2025-01-16 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed.
2025-01-17 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-17 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed.
2025-01-17 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-17 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed.
2025-01-17 | 2025-01-13 | 2025-01-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed.
2025-01-17 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed.
2025-01-17 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-01-17 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed.
2025-01-17 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed.
2025-01-17 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed.
2025-01-17 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed.
2025-01-17 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed.
2025-01-17 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed.
2025-01-17 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed.
2025-01-17 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-01-17 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-17 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed.
2025-01-17 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-01-17 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed.
2025-01-18 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2025-01-18 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed.
2025-01-18 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-18 | 2025-01-13 | 2025-01-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed.
2025-01-18 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed.
2025-01-18 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-01-18 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-01-18 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed.
2025-01-18 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed.
2025-01-18 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed.
2025-01-18 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed.
2025-01-18 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed.
2025-01-18 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed.
2025-01-18 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed.
2025-01-18 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-01-18 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-18 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed.
2025-01-18 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-01-18 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed.
2025-01-19 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed.
2025-01-19 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-19 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed.
2025-01-19 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed.
2025-01-19 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-01-19 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-01-19 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed.
2025-01-19 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed.
2025-01-19 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed.
2025-01-19 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed.
2025-01-19 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed.
2025-01-19 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed.
2025-01-19 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-01-19 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-19 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed.
2025-01-19 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-01-19 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed.
2025-01-20 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed.
2025-01-20 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-20 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed.
2025-01-20 | 2025-01-20 | 2025-01-24 | Dhaneshwar Mahto | 46.623 | 9.3246 | TA325 | 137A/6 | Completed.
2025-01-20 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed.
2025-01-20 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-01-20 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-01-20 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed.
2025-01-20 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed.
2025-01-20 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed.
2025-01-20 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed.
2025-01-20 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed.
2025-01-20 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-01-20 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-20 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed.
2025-01-20 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-01-20 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed.
2025-01-21 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed.
2025-01-21 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-21 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed.
2025-01-21 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed.
2025-01-21 | 2025-01-20 | 2025-01-24 | Dhaneshwar Mahto | 46.623 | 9.3246 | TA325 | 137A/6 | Completed.
2025-01-21 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed.
2025-01-21 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-01-21 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-01-21 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed.
2025-01-21 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed.
2025-01-21 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed.
2025-01-21 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed.
2025-01-21 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed.
2025-01-21 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed.
2025-01-21 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-01-21 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed.
2025-01-21 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-01-21 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-21 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed.
2025-01-21 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-01-21 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed.
2025-01-22 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed.
2025-01-22 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-22 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed.
2025-01-22 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed.
2025-01-22 | 2025-01-20 | 2025-01-24 | Dhaneshwar Mahto | 46.623 | 9.3246 | TA325 | 137A/6 | Completed.
2025-01-22 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed.
2025-01-22 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-01-22 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-01-22 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed.
2025-01-22 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed.
2025-01-22 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed.
2025-01-22 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed.
2025-01-22 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed.
2025-01-22 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed.
2025-01-22 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-01-22 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed.
2025-01-22 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-01-22 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed.
2025-01-22 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-01-22 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed.
2025-01-23 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed.
2025-01-23 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-23 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed.
2025-01-23 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed.
2025-01-23 | 2025-01-20 | 2025-01-24 | Dhaneshwar Mahto | 46.623 | 9.3246 | TA325 | 137A/6 | Completed.
2025-01-23 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed.
2025-01-23 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-01-23 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-01-23 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed.
2025-01-23 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed.
2025-01-23 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed.
2025-01-23 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed.
2025-01-23 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed.
2025-01-23 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-01-23 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed.
2025-01-23 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-01-23 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed.
2025-01-23 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-01-23 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed.
2025-01-24 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed.
2025-01-24 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-24 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed.
2025-01-24 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed.
2025-01-24 | 2025-01-20 | 2025-01-24 | Dhaneshwar Mahto | 46.623 | 9.3246 | TA325 | 137A/6 | Completed.
2025-01-24 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed.
2025-01-24 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-01-24 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-01-24 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed.
2025-01-24 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed.
2025-01-24 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed.
2025-01-24 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed.
2025-01-24 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed.
2025-01-24 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed.
2025-01-24 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-01-24 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-01-24 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed.
2025-01-24 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-01-25 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed.
2025-01-25 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-25 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed.
2025-01-25 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed.
2025-01-25 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed.
2025-01-25 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-01-25 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-01-25 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed.
2025-01-25 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed.
2025-01-25 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed.
2025-01-25 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed.
2025-01-25 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed.
2025-01-25 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed.
2025-01-25 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-01-25 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-01-25 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed.
2025-01-25 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed.
2025-01-25 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-01-25 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed.
2025-01-26 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-26 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed.
2025-01-26 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed.
2025-01-26 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed.
2025-01-26 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-01-26 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed.
2025-01-26 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed.
2025-01-26 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed.
2025-01-26 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed.
2025-01-26 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed.
2025-01-26 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed.
2025-01-26 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-01-26 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-01-26 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed.
2025-01-26 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed.
2025-01-26 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-01-26 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed.
2025-01-27 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-01-27 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-27 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed.
2025-01-27 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed.
2025-01-27 | 2025-01-27 | 2025-01-29 | Dhaneshwar Mahto | 44.728 | 14.9093 | TA325 | 137A/1 | Completed.
2025-01-27 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed.
2025-01-27 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-01-27 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed.
2025-01-27 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed.
2025-01-27 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed.
2025-01-27 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed.
2025-01-27 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed.
2025-01-27 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed.
2025-01-27 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed.
2025-01-27 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-01-27 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-01-27 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed.
2025-01-27 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed.
2025-01-27 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed.
2025-01-27 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-01-27 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed.
2025-01-28 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-01-28 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-28 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed.
2025-01-28 | 2025-01-27 | 2025-01-29 | Dhaneshwar Mahto | 44.728 | 14.9093 | TA325 | 137A/1 | Completed.
2025-01-28 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed.
2025-01-28 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-01-28 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed.
2025-01-28 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed.
2025-01-28 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed.
2025-01-28 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed.
2025-01-28 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed.
2025-01-28 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed.
2025-01-28 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-01-28 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-01-28 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-01-28 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed.
2025-01-28 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed.
2025-01-28 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed.
2025-01-28 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-01-28 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed.
2025-01-29 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-01-29 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-29 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed.
2025-01-29 | 2025-01-27 | 2025-01-29 | Dhaneshwar Mahto | 44.728 | 14.9093 | TA325 | 137A/1 | Completed.
2025-01-29 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed.
2025-01-29 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-01-29 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed.
2025-01-29 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed.
2025-01-29 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed.
2025-01-29 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed.
2025-01-29 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed.
2025-01-29 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed.
2025-01-29 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed.
2025-01-29 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-01-29 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-01-29 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-01-29 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed.
2025-01-29 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed.
2025-01-29 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed.
2025-01-29 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-01-29 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed.
2025-01-30 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-01-30 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-30 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed.
2025-01-30 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed.
2025-01-30 | 2025-01-30 | 2025-02-02 | Dhaneshwar Mahto | 37.73 | 9.4325 | TA325 | 137A/2 | Completed.
2025-01-30 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed.
2025-01-30 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-01-30 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed.
2025-01-30 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed.
2025-01-30 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed.
2025-01-30 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed.
2025-01-30 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed.
2025-01-30 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed.
2025-01-30 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-01-30 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-01-30 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed.
2025-01-30 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed.
2025-01-30 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-01-30 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed.
2025-01-31 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-01-31 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-31 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed.
2025-01-31 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed.
2025-01-31 | 2025-01-30 | 2025-02-02 | Dhaneshwar Mahto | 37.73 | 9.4325 | TA325 | 137A/2 | Completed.
2025-01-31 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed.
2025-01-31 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-01-31 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed.
2025-01-31 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed.
2025-01-31 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed.
2025-01-31 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed.
2025-01-31 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed.
2025-01-31 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-01-31 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-01-31 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed.
2025-01-31 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed.
2025-01-31 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-01-31 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed.
2025-02-01 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-01 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-01 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed.
2025-02-01 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed.
2025-02-01 | 2025-01-30 | 2025-02-02 | Dhaneshwar Mahto | 37.73 | 9.4325 | TA325 | 137A/2 | Completed.
2025-02-01 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed.
2025-02-01 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-02-01 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed.
2025-02-01 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed.
2025-02-01 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed.
2025-02-01 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed.
2025-02-01 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed.
2025-02-01 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed.
2025-02-01 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-02-01 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-02-01 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2025-02-01 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed.
2025-02-01 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed.
2025-02-01 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-02-01 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed.
2025-02-02 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-02 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-02 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed.
2025-02-02 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed.
2025-02-02 | 2025-01-30 | 2025-02-02 | Dhaneshwar Mahto | 37.73 | 9.4325 | TA325 | 137A/2 | Completed.
2025-02-02 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed.
2025-02-02 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-02-02 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed.
2025-02-02 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed.
2025-02-02 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed.
2025-02-02 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed.
2025-02-02 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed.
2025-02-02 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-02-02 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-02-02 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2025-02-02 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed.
2025-02-02 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed.
2025-02-02 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-02-02 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed.
2025-02-03 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-03 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-03 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed.
2025-02-03 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed.
2025-02-03 | 2025-02-03 | 2025-02-07 | Dhaneshwar Mahto | 39.459 | 7.8918 | TA325 | 137/5 | Completed.
2025-02-03 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed.
2025-02-03 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-02-03 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed.
2025-02-03 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed.
2025-02-03 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed.
2025-02-03 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed.
2025-02-03 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed.
2025-02-03 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed.
2025-02-03 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-02-03 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-02-03 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2025-02-03 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed.
2025-02-03 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed.
2025-02-03 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-02-04 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-04 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-04 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed.
2025-02-04 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed.
2025-02-04 | 2025-02-03 | 2025-02-07 | Dhaneshwar Mahto | 39.459 | 7.8918 | TA325 | 137/5 | Completed.
2025-02-04 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed.
2025-02-04 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-02-04 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed.
2025-02-04 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed.
2025-02-04 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed.
2025-02-04 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed.
2025-02-04 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed.
2025-02-04 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed.
2025-02-04 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-02-04 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-02-04 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2025-02-04 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed.
2025-02-04 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed.
2025-02-04 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-02-04 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed.
2025-02-05 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-05 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-05 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed.
2025-02-05 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed.
2025-02-05 | 2025-02-03 | 2025-02-07 | Dhaneshwar Mahto | 39.459 | 7.8918 | TA325 | 137/5 | Completed.
2025-02-05 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed.
2025-02-05 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-02-05 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed.
2025-02-05 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325 | 272A/3 | Completed.
2025-02-05 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed.
2025-02-05 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed.
2025-02-05 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed.
2025-02-05 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed.
2025-02-05 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-02-05 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-02-05 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2025-02-05 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed.
2025-02-05 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed.
2025-02-05 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-02-05 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed.
2025-02-06 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-06 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-06 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed.
2025-02-06 | 2025-02-03 | 2025-02-07 | Dhaneshwar Mahto | 39.459 | 7.8918 | TA325 | 137/5 | Completed.
2025-02-06 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed.
2025-02-06 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-02-06 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed.
2025-02-06 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325 | 272A/3 | Completed.
2025-02-06 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed.
2025-02-06 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed.
2025-02-06 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed.
2025-02-06 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed.
2025-02-06 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-02-06 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-02-06 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2025-02-06 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed.
2025-02-06 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed.
2025-02-06 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-02-06 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed.
2025-02-07 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-07 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-07 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed.
2025-02-07 | 2025-02-03 | 2025-02-07 | Dhaneshwar Mahto | 39.459 | 7.8918 | TA325 | 137/5 | Completed.
2025-02-07 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed.
2025-02-07 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-02-07 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed.
2025-02-07 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325 | 272A/3 | Completed.
2025-02-07 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed.
2025-02-07 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed.
2025-02-07 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed.
2025-02-07 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed.
2025-02-07 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-02-07 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-02-07 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2025-02-07 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed.
2025-02-07 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed.
2025-02-07 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed.
2025-02-08 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-08 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-08 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed.
2025-02-08 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed.
2025-02-08 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-02-08 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed.
2025-02-08 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325 | 272A/3 | Completed.
2025-02-08 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed.
2025-02-08 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed.
2025-02-08 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed.
2025-02-08 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-02-08 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-02-08 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2025-02-08 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed.
2025-02-08 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed.
2025-02-09 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-09 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-09 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed.
2025-02-09 | 2025-02-09 | 2025-02-14 | Dhaneshwar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed.
2025-02-09 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed.
2025-02-09 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-02-09 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed.
2025-02-09 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325 | 272A/3 | Completed.
2025-02-09 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed.
2025-02-09 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed.
2025-02-09 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed.
2025-02-09 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-02-09 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-02-09 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2025-02-09 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed.
2025-02-09 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed.
2025-02-09 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed.
2025-02-10 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-10 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-10 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed.
2025-02-10 | 2025-02-09 | 2025-02-14 | Dhaneshwar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed.
2025-02-10 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed.
2025-02-10 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-02-10 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325 | 139/2 | Completed.
2025-02-10 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed.
2025-02-10 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed.
2025-02-10 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-02-10 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-02-10 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2025-02-10 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed.
2025-02-10 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-10 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed.
2025-02-11 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-11 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-11 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed.
2025-02-11 | 2025-02-09 | 2025-02-14 | Dhaneshwar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed.
2025-02-11 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed.
2025-02-11 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2025-02-11 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325 | 139/2 | Completed.
2025-02-11 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed.
2025-02-11 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed.
2025-02-11 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed.
2025-02-11 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-02-11 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-02-11 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2025-02-11 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed.
2025-02-11 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed.
2025-02-11 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-11 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed.
2025-02-12 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-12 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-12 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed.
2025-02-12 | 2025-02-09 | 2025-02-14 | Dhaneshwar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed.
2025-02-12 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed.
2025-02-12 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325 | 139/2 | Completed.
2025-02-12 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed.
2025-02-12 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed.
2025-02-12 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed.
2025-02-12 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2025-02-12 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-02-12 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2025-02-12 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed.
2025-02-12 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed.
2025-02-12 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-12 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed.
2025-02-13 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-13 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-13 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed.
2025-02-13 | 2025-02-09 | 2025-02-14 | Dhaneshwar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed.
2025-02-13 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed.
2025-02-13 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325 | 139/2 | Completed.
2025-02-13 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed.
2025-02-13 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed.
2025-02-13 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed.
2025-02-13 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-02-13 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2025-02-13 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed.
2025-02-13 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed.
2025-02-13 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed.
2025-02-13 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-13 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed.
2025-02-14 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-14 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-14 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed.
2025-02-14 | 2025-02-09 | 2025-02-14 | Dhaneshwar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed.
2025-02-14 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed.
2025-02-14 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed.
2025-02-14 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325 | 139/2 | Completed.
2025-02-14 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed.
2025-02-14 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed.
2025-02-14 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed.
2025-02-14 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed.
2025-02-14 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-02-14 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2025-02-14 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed.
2025-02-14 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed.
2025-02-14 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed.
2025-02-14 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-14 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed.
2025-02-15 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-15 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-15 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed.
2025-02-15 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed.
2025-02-15 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed.
2025-02-15 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed.
2025-02-15 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed.
2025-02-15 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed.
2025-02-15 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed.
2025-02-15 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-02-15 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2025-02-15 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed.
2025-02-15 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed.
2025-02-15 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed.
2025-02-15 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-15 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed.
2025-02-16 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-16 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-16 | 2025-02-16 | 2025-02-22 | Dhaneshwar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed.
2025-02-16 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed.
2025-02-16 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed.
2025-02-16 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed.
2025-02-16 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed.
2025-02-16 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed.
2025-02-16 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed.
2025-02-16 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-02-16 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2025-02-16 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed.
2025-02-16 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed.
2025-02-16 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed.
2025-02-16 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-16 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed.
2025-02-17 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-17 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-17 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed.
2025-02-17 | 2025-02-16 | 2025-02-22 | Dhaneshwar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed.
2025-02-17 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed.
2025-02-17 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed.
2025-02-17 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed.
2025-02-17 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed.
2025-02-17 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed.
2025-02-17 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed.
2025-02-17 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed.
2025-02-17 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2025-02-17 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed.
2025-02-17 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed.
2025-02-17 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed.
2025-02-17 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-17 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed.
2025-02-18 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2025-02-18 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-18 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed.
2025-02-18 | 2025-02-16 | 2025-02-22 | Dhaneshwar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed.
2025-02-18 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed.
2025-02-18 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed.
2025-02-18 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed.
2025-02-18 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed.
2025-02-18 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed.
2025-02-18 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed.
2025-02-18 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed.
2025-02-18 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed.
2025-02-18 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed.
2025-02-18 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-18 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed.
2025-02-19 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-19 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed.
2025-02-19 | 2025-02-16 | 2025-02-22 | Dhaneshwar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed.
2025-02-19 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed.
2025-02-19 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed.
2025-02-19 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed.
2025-02-19 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed.
2025-02-19 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed.
2025-02-19 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed.
2025-02-19 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed.
2025-02-19 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed.
2025-02-19 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed.
2025-02-19 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-19 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed.
2025-02-20 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-02-20 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed.
2025-02-20 | 2025-02-16 | 2025-02-22 | Dhaneshwar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed.
2025-02-20 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed.
2025-02-20 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed.
2025-02-20 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed.
2025-02-20 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed.
2025-02-20 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed.
2025-02-20 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed.
2025-02-20 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed.
2025-02-20 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed.
2025-02-20 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-02-20 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed.
2025-02-20 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-20 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed.
2025-02-21 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed.
2025-02-21 | 2025-02-16 | 2025-02-22 | Dhaneshwar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed.
2025-02-21 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed.
2025-02-21 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed.
2025-02-21 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed.
2025-02-21 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed.
2025-02-21 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed.
2025-02-21 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed.
2025-02-21 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed.
2025-02-21 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed.
2025-02-21 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-02-21 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-02-21 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed.
2025-02-21 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-21 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed.
2025-02-22 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-02-22 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed.
2025-02-22 | 2025-02-16 | 2025-02-22 | Dhaneshwar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed.
2025-02-22 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed.
2025-02-22 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed.
2025-02-22 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed.
2025-02-22 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed.
2025-02-22 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed.
2025-02-22 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed.
2025-02-22 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed.
2025-02-22 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-02-22 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-02-22 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed.
2025-02-22 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed.
2025-02-22 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-22 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed.
2025-02-23 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-02-23 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-02-23 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed.
2025-02-23 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed.
2025-02-23 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed.
2025-02-23 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed.
2025-02-23 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed.
2025-02-23 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed.
2025-02-23 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed.
2025-02-23 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed.
2025-02-23 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-02-23 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-02-23 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed.
2025-02-23 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed.
2025-02-23 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-23 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed.
2025-02-24 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-02-24 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-02-24 | 2025-02-24 | 2025-03-02 | Dhaneshwar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed.
2025-02-24 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed.
2025-02-24 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed.
2025-02-24 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325 | 273/2 | Completed.
2025-02-24 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed.
2025-02-24 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed.
2025-02-24 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed.
2025-02-24 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-02-24 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-02-24 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed.
2025-02-24 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed.
2025-02-24 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-24 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed.
2025-02-25 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-02-25 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-02-25 | 2025-02-24 | 2025-03-02 | Dhaneshwar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed.
2025-02-25 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed.
2025-02-25 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed.
2025-02-25 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325 | 273/2 | Completed.
2025-02-25 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed.
2025-02-25 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed.
2025-02-25 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed.
2025-02-25 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-02-25 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-02-25 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed.
2025-02-25 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325 | 148/5 | Completed.
2025-02-25 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed.
2025-02-25 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-25 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed.
2025-02-26 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-02-26 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-02-26 | 2025-02-24 | 2025-03-02 | Dhaneshwar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed.
2025-02-26 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed.
2025-02-26 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed.
2025-02-26 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325 | 273/2 | Completed.
2025-02-26 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed.
2025-02-26 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed.
2025-02-26 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed.
2025-02-26 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-02-26 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-02-26 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-02-26 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325 | 148/5 | Completed.
2025-02-26 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-02-26 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed.
2025-02-26 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-26 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed.
2025-02-27 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-02-27 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-02-27 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed.
2025-02-27 | 2025-02-24 | 2025-03-02 | Dhaneshwar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed.
2025-02-27 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed.
2025-02-27 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed.
2025-02-27 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325 | 273/2 | Completed.
2025-02-27 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed.
2025-02-27 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed.
2025-02-27 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-02-27 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-02-27 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-02-27 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325 | 148/5 | Completed.
2025-02-27 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-02-27 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed.
2025-02-27 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-27 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed.
2025-02-28 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-02-28 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-02-28 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed.
2025-02-28 | 2025-02-24 | 2025-03-02 | Dhaneshwar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed.
2025-02-28 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed.
2025-02-28 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed.
2025-02-28 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325 | 273/2 | Completed.
2025-02-28 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed.
2025-02-28 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-02-28 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-02-28 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-02-28 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325 | 148/5 | Completed.
2025-02-28 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-02-28 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed.
2025-02-28 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-02-28 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed.
2025-03-01 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-03-01 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-03-01 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed.
2025-03-01 | 2025-02-24 | 2025-03-02 | Dhaneshwar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed.
2025-03-01 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed.
2025-03-01 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed.
2025-03-01 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed.
2025-03-01 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-01 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-03-01 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-01 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed.
2025-03-01 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-01 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed.
2025-03-01 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-03-01 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed.
2025-03-02 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-03-02 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-03-02 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed.
2025-03-02 | 2025-02-24 | 2025-03-02 | Dhaneshwar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed.
2025-03-02 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed.
2025-03-02 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed.
2025-03-02 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325 | 272A/6 | Completed.
2025-03-02 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed.
2025-03-02 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed.
2025-03-02 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-02 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-03-02 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-02 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed.
2025-03-02 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-02 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed.
2025-03-02 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-03-02 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed.
2025-03-03 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-03-03 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-03-03 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed.
2025-03-03 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed.
2025-03-03 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed.
2025-03-03 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325 | 272A/6 | Completed.
2025-03-03 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed.
2025-03-03 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed.
2025-03-03 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-03 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-03-03 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-03 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed.
2025-03-03 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed.
2025-03-03 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-03 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed.
2025-03-03 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-03-03 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed.
2025-03-04 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-03-04 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-03-04 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed.
2025-03-04 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed.
2025-03-04 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed.
2025-03-04 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325 | 272A/6 | Completed.
2025-03-04 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed.
2025-03-04 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed.
2025-03-04 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-04 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-03-04 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-04 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed.
2025-03-04 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed.
2025-03-04 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-04 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed.
2025-03-04 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-03-05 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-03-05 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-03-05 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed.
2025-03-05 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed.
2025-03-05 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed.
2025-03-05 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed.
2025-03-05 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325 | 272A/6 | Completed.
2025-03-05 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed.
2025-03-05 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed.
2025-03-05 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-05 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-03-05 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-05 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed.
2025-03-05 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed.
2025-03-05 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-05 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed.
2025-03-05 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-03-06 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-03-06 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-03-06 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed.
2025-03-06 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed.
2025-03-06 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed.
2025-03-06 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325 | 272A/7 | Completed.
2025-03-06 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed.
2025-03-06 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed.
2025-03-06 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-06 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-03-06 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-06 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed.
2025-03-06 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed.
2025-03-06 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-06 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed.
2025-03-06 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-03-07 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-03-07 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-03-07 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed.
2025-03-07 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed.
2025-03-07 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed.
2025-03-07 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed.
2025-03-07 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325 | 272A/7 | Completed.
2025-03-07 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed.
2025-03-07 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed.
2025-03-07 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-07 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-03-07 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-07 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed.
2025-03-07 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed.
2025-03-07 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-07 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed.
2025-03-07 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-03-08 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-03-08 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-03-08 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed.
2025-03-08 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed.
2025-03-08 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed.
2025-03-08 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed.
2025-03-08 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325 | 272A/7 | Completed.
2025-03-08 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed.
2025-03-08 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed.
2025-03-08 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-08 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed.
2025-03-08 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-03-08 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-08 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed.
2025-03-08 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed.
2025-03-08 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-08 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed.
2025-03-09 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-03-09 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-03-09 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed.
2025-03-09 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed.
2025-03-09 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed.
2025-03-09 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed.
2025-03-09 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325 | 272A/7 | Completed.
2025-03-09 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed.
2025-03-09 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-09 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed.
2025-03-09 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-09 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed.
2025-03-09 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-03-09 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-09 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed.
2025-03-09 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed.
2025-03-09 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-09 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed.
2025-03-10 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-03-10 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-03-10 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed.
2025-03-10 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed.
2025-03-10 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed.
2025-03-10 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed.
2025-03-10 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325 | 272A/7 | Completed.
2025-03-10 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed.
2025-03-10 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-10 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed.
2025-03-10 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-10 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed.
2025-03-10 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-10 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-10 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-10 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed.
2025-03-11 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-03-11 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-03-11 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed.
2025-03-11 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed.
2025-03-11 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed.
2025-03-11 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed.
2025-03-11 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed.
2025-03-11 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-11 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-11 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed.
2025-03-11 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-11 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-11 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-11 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed.
2025-03-12 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-03-12 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed.
2025-03-12 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed.
2025-03-12 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed.
2025-03-12 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed.
2025-03-12 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed.
2025-03-12 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-12 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-12 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed.
2025-03-12 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed.
2025-03-12 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-12 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-12 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-12 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed.
2025-03-13 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-03-13 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed.
2025-03-13 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed.
2025-03-13 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed.
2025-03-13 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed.
2025-03-13 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed.
2025-03-13 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-13 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-13 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed.
2025-03-13 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed.
2025-03-13 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed.
2025-03-13 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-13 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-13 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-13 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed.
2025-03-14 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-03-14 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed.
2025-03-14 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed.
2025-03-14 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed.
2025-03-14 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed.
2025-03-14 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed.
2025-03-14 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-14 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-14 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed.
2025-03-14 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed.
2025-03-14 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed.
2025-03-14 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-14 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-14 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-14 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed.
2025-03-15 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-03-15 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed.
2025-03-15 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed.
2025-03-15 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed.
2025-03-15 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed.
2025-03-15 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed.
2025-03-15 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed.
2025-03-15 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-15 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed.
2025-03-15 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-15 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed.
2025-03-15 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed.
2025-03-15 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed.
2025-03-15 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-15 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-15 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-15 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed.
2025-03-16 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2025-03-16 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed.
2025-03-16 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed.
2025-03-16 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed.
2025-03-16 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325 | 152A/0 | Completed.
2025-03-16 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed.
2025-03-16 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed.
2025-03-16 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-16 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed.
2025-03-16 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-16 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed.
2025-03-16 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed.
2025-03-16 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed.
2025-03-16 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-16 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-16 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-16 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed.
2025-03-17 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed.
2025-03-17 | 2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed.
2025-03-17 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed.
2025-03-17 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325 | 152A/0 | Completed.
2025-03-17 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325 | 272A/4 | Completed.
2025-03-17 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed.
2025-03-17 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-17 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed.
2025-03-17 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-17 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed.
2025-03-17 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed.
2025-03-17 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed.
2025-03-17 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-17 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-17 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed.
2025-03-17 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-18 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-03-18 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed.
2025-03-18 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed.
2025-03-18 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325 | 152A/0 | Completed.
2025-03-18 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325 | 272A/4 | Completed.
2025-03-18 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed.
2025-03-18 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-18 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed.
2025-03-18 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-18 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed.
2025-03-18 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed.
2025-03-18 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed.
2025-03-18 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-03-18 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-18 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed.
2025-03-18 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325 | 150/2 | Completed.
2025-03-18 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-19 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-03-19 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed.
2025-03-19 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed.
2025-03-19 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed.
2025-03-19 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325 | 152A/0 | Completed.
2025-03-19 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325 | 272A/4 | Completed.
2025-03-19 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-19 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed.
2025-03-19 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-19 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed.
2025-03-19 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed.
2025-03-19 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed.
2025-03-19 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-19 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed.
2025-03-19 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325 | 150/2 | Completed.
2025-03-19 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-19 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed.
2025-03-19 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed.
2025-03-20 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-03-20 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed.
2025-03-20 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed.
2025-03-20 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed.
2025-03-20 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325 | 152A/0 | Completed.
2025-03-20 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325 | 272A/4 | Completed.
2025-03-20 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-20 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed.
2025-03-20 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-03-20 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-20 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed.
2025-03-20 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed.
2025-03-20 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed.
2025-03-20 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-20 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed.
2025-03-20 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325 | 150/2 | Completed.
2025-03-20 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-20 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed.
2025-03-20 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed.
2025-03-21 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-03-21 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed.
2025-03-21 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed.
2025-03-21 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed.
2025-03-21 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed.
2025-03-21 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325 | 271/1 | Completed.
2025-03-21 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-03-21 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-21 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed.
2025-03-21 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-03-21 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-21 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed.
2025-03-21 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed.
2025-03-21 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-21 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed.
2025-03-21 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325 | 150/2 | Completed.
2025-03-21 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-21 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed.
2025-03-21 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed.
2025-03-22 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-03-22 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed.
2025-03-22 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed.
2025-03-22 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed.
2025-03-22 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed.
2025-03-22 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed.
2025-03-22 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325 | 271/1 | Completed.
2025-03-22 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-03-22 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-22 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed.
2025-03-22 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-03-22 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-03-22 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed.
2025-03-22 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed.
2025-03-22 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed.
2025-03-22 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-22 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed.
2025-03-22 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325 | 150/2 | Completed.
2025-03-22 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-22 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed.
2025-03-22 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed.
2025-03-23 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-03-23 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed.
2025-03-23 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed.
2025-03-23 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed.
2025-03-23 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed.
2025-03-23 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325 | 271/1 | Completed.
2025-03-23 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-03-23 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-23 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed.
2025-03-23 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-03-23 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed.
2025-03-23 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed.
2025-03-23 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed.
2025-03-23 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-23 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed.
2025-03-23 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-23 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed.
2025-03-23 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed.
2025-03-24 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-03-24 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed.
2025-03-24 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed.
2025-03-24 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed.
2025-03-24 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed.
2025-03-24 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325 | 271/1 | Completed.
2025-03-24 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-03-24 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-24 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed.
2025-03-24 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-03-24 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed.
2025-03-24 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed.
2025-03-24 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed.
2025-03-24 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-24 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed.
2025-03-24 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-24 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed.
2025-03-24 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed.
2025-03-25 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-03-25 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed.
2025-03-25 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed.
2025-03-25 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed.
2025-03-25 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed.
2025-03-25 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325 | 271/1 | Completed.
2025-03-25 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-03-25 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-25 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed.
2025-03-25 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-03-25 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed.
2025-03-25 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-03-25 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed.
2025-03-25 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed.
2025-03-25 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-25 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed.
2025-03-25 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-25 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed.
2025-03-25 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed.
2025-03-26 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-03-26 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed.
2025-03-26 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed.
2025-03-26 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed.
2025-03-26 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed.
2025-03-26 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed.
2025-03-26 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed.
2025-03-26 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-03-26 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-26 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed.
2025-03-26 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-03-26 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed.
2025-03-26 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-03-26 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed.
2025-03-26 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed.
2025-03-26 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-26 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed.
2025-03-26 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-26 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed.
2025-03-26 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed.
2025-03-27 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-03-27 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed.
2025-03-27 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed.
2025-03-27 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed.
2025-03-27 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed.
2025-03-27 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed.
2025-03-27 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed.
2025-03-27 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-03-27 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-27 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed.
2025-03-27 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-03-27 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed.
2025-03-27 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-03-27 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed.
2025-03-27 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed.
2025-03-27 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-27 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed.
2025-03-27 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-27 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed.
2025-03-27 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed.
2025-03-28 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-03-28 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed.
2025-03-28 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed.
2025-03-28 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed.
2025-03-28 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed.
2025-03-28 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed.
2025-03-28 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed.
2025-03-28 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-03-28 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-03-28 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed.
2025-03-28 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-03-28 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-03-28 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed.
2025-03-28 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed.
2025-03-28 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-28 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-28 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed.
2025-03-29 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-03-29 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed.
2025-03-29 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed.
2025-03-29 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed.
2025-03-29 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed.
2025-03-29 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed.
2025-03-29 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed.
2025-03-29 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-03-29 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-03-29 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-03-29 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed.
2025-03-29 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-29 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-03-30 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-03-30 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed.
2025-03-30 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed.
2025-03-30 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed.
2025-03-30 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed.
2025-03-30 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed.
2025-03-30 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed.
2025-03-30 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-03-30 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-03-30 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed.
2025-03-30 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-03-30 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed.
2025-03-30 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-31 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-03-31 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed.
2025-03-31 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed.
2025-03-31 | 2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed.
2025-03-31 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed.
2025-03-31 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed.
2025-03-31 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-03-31 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-03-31 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed.
2025-03-31 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-03-31 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed.
2025-03-31 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-04-01 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-04-01 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed.
2025-04-01 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed.
2025-04-01 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed.
2025-04-01 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed.
2025-04-01 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-04-01 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed.
2025-04-01 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed.
2025-04-01 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-04-01 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed.
2025-04-01 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-04-01 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed.
2025-04-01 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-04-01 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed.
2025-04-01 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed.
2025-04-02 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-04-02 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed.
2025-04-02 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed.
2025-04-02 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-04-02 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed.
2025-04-02 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed.
2025-04-02 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-04-02 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed.
2025-04-02 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-04-02 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed.
2025-04-02 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed.
2025-04-02 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-04-02 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed.
2025-04-02 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-02 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed.
2025-04-03 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-04-03 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed.
2025-04-03 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed.
2025-04-03 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-04-03 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed.
2025-04-03 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed.
2025-04-03 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-04-03 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed.
2025-04-03 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-04-03 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed.
2025-04-03 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed.
2025-04-03 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-03 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-04-03 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed.
2025-04-03 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-03 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed.
2025-04-03 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed.
2025-04-04 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-04-04 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed.
2025-04-04 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed.
2025-04-04 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed.
2025-04-04 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-04-04 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed.
2025-04-04 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed.
2025-04-04 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-04-04 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed.
2025-04-04 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-04-04 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed.
2025-04-04 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed.
2025-04-04 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-04 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-04-04 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed.
2025-04-04 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-04 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed.
2025-04-04 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed.
2025-04-05 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-04-05 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed.
2025-04-05 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed.
2025-04-05 | 2025-04-05 | 2025-04-11 | Dhaneshwar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed.
2025-04-05 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed.
2025-04-05 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-04-05 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed.
2025-04-05 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed.
2025-04-05 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-04-05 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed.
2025-04-05 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-04-05 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed.
2025-04-05 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed.
2025-04-05 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-05 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-04-05 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed.
2025-04-05 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-05 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed.
2025-04-05 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed.
2025-04-06 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-04-06 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed.
2025-04-06 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed.
2025-04-06 | 2025-04-05 | 2025-04-11 | Dhaneshwar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed.
2025-04-06 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-06 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed.
2025-04-06 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed.
2025-04-06 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-04-06 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed.
2025-04-06 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed.
2025-04-06 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-04-06 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed.
2025-04-06 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-04-06 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed.
2025-04-06 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed.
2025-04-06 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed.
2025-04-06 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-06 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-04-06 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed.
2025-04-06 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-06 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed.
2025-04-06 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed.
2025-04-07 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-04-07 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-07 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed.
2025-04-07 | 2025-04-05 | 2025-04-11 | Dhaneshwar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed.
2025-04-07 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-07 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed.
2025-04-07 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed.
2025-04-07 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-04-07 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed.
2025-04-07 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed.
2025-04-07 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed.
2025-04-07 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-04-07 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed.
2025-04-07 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed.
2025-04-07 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed.
2025-04-07 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-07 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed.
2025-04-07 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-07 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed.
2025-04-07 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed.
2025-04-08 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-04-08 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-08 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed.
2025-04-08 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed.
2025-04-08 | 2025-04-05 | 2025-04-11 | Dhaneshwar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed.
2025-04-08 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-08 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed.
2025-04-08 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed.
2025-04-08 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-04-08 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed.
2025-04-08 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed.
2025-04-08 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed.
2025-04-08 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-04-08 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed.
2025-04-08 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed.
2025-04-08 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed.
2025-04-08 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-08 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed.
2025-04-08 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-08 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed.
2025-04-08 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed.
2025-04-09 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-04-09 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-09 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed.
2025-04-09 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed.
2025-04-09 | 2025-04-05 | 2025-04-11 | Dhaneshwar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed.
2025-04-09 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-09 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed.
2025-04-09 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed.
2025-04-09 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-04-09 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed.
2025-04-09 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed.
2025-04-09 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-04-09 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed.
2025-04-09 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed.
2025-04-09 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed.
2025-04-09 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-09 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed.
2025-04-09 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-09 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed.
2025-04-09 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed.
2025-04-10 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-04-10 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-10 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed.
2025-04-10 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed.
2025-04-10 | 2025-04-05 | 2025-04-11 | Dhaneshwar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed.
2025-04-10 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-10 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed.
2025-04-10 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-04-10 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed.
2025-04-10 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed.
2025-04-10 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-04-10 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed.
2025-04-10 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed.
2025-04-10 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed.
2025-04-10 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-10 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed.
2025-04-10 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-10 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed.
2025-04-10 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed.
2025-04-11 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-04-11 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-11 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed.
2025-04-11 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed.
2025-04-11 | 2025-04-05 | 2025-04-11 | Dhaneshwar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed.
2025-04-11 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-11 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed.
2025-04-11 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-11 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-04-11 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed.
2025-04-11 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed.
2025-04-11 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed.
2025-04-11 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2025-04-11 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed.
2025-04-11 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed.
2025-04-11 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-11 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed.
2025-04-11 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-11 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed.
2025-04-11 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed.
2025-04-12 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-12 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed.
2025-04-12 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed.
2025-04-12 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-12 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed.
2025-04-12 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-12 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-04-12 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed.
2025-04-12 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed.
2025-04-12 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed.
2025-04-12 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed.
2025-04-12 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-12 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed.
2025-04-12 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-12 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed.
2025-04-12 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed.
2025-04-13 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-13 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed.
2025-04-13 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-13 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed.
2025-04-13 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-13 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed.
2025-04-13 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed.
2025-04-13 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed.
2025-04-13 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed.
2025-04-13 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-13 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed.
2025-04-13 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed.
2025-04-13 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-13 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed.
2025-04-14 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-04-14 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-14 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed.
2025-04-14 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-14 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-14 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed.
2025-04-14 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed.
2025-04-14 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed.
2025-04-14 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed.
2025-04-14 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-14 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed.
2025-04-14 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed.
2025-04-14 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-14 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed.
2025-04-15 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-04-15 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-15 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed.
2025-04-15 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-15 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-15 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed.
2025-04-15 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed.
2025-04-15 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed.
2025-04-15 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed.
2025-04-15 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed.
2025-04-15 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-15 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed.
2025-04-15 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed.
2025-04-15 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-15 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed.
2025-04-16 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-04-16 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-16 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed.
2025-04-16 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-16 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed.
2025-04-16 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-16 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed.
2025-04-16 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed.
2025-04-16 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed.
2025-04-16 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed.
2025-04-16 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed.
2025-04-16 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed.
2025-04-16 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-16 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed.
2025-04-16 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-16 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed.
2025-04-17 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-04-17 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-17 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed.
2025-04-17 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-17 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed.
2025-04-17 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed.
2025-04-17 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed.
2025-04-17 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-04-17 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed.
2025-04-17 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed.
2025-04-17 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed.
2025-04-17 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-17 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed.
2025-04-17 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-17 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed.
2025-04-17 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed.
2025-04-18 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-04-18 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-18 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed.
2025-04-18 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-04-18 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-18 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed.
2025-04-18 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed.
2025-04-18 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed.
2025-04-18 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-04-18 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed.
2025-04-18 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-04-18 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed.
2025-04-18 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed.
2025-04-18 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed.
2025-04-18 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-04-18 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-18 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed.
2025-04-18 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed.
2025-04-18 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-18 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed.
2025-04-18 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed.
2025-04-19 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-04-19 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-19 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-04-19 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-19 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed.
2025-04-19 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed.
2025-04-19 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed.
2025-04-19 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-04-19 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed.
2025-04-19 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-04-19 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed.
2025-04-19 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed.
2025-04-19 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed.
2025-04-19 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-04-19 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-19 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed.
2025-04-19 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed.
2025-04-19 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-19 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed.
2025-04-19 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed.
2025-04-20 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-04-20 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-20 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed.
2025-04-20 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-04-20 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-20 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed.
2025-04-20 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed.
2025-04-20 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed.
2025-04-20 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-04-20 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed.
2025-04-20 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-04-20 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed.
2025-04-20 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed.
2025-04-20 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed.
2025-04-20 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-04-20 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-20 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed.
2025-04-20 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed.
2025-04-20 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-20 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed.
2025-04-20 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed.
2025-04-21 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-04-21 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-21 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed.
2025-04-21 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-04-21 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-21 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed.
2025-04-21 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed.
2025-04-21 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed.
2025-04-21 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-04-21 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed.
2025-04-21 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-04-21 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed.
2025-04-21 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed.
2025-04-21 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed.
2025-04-21 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-04-21 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-21 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed.
2025-04-21 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed.
2025-04-21 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-21 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed.
2025-04-21 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed.
2025-04-22 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-04-22 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-22 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed.
2025-04-22 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-04-22 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-04-22 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-22 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed.
2025-04-22 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed.
2025-04-22 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed.
2025-04-22 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-04-22 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed.
2025-04-22 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-04-22 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-04-22 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed.
2025-04-22 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed.
2025-04-22 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed.
2025-04-22 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-04-22 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-22 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed.
2025-04-22 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed.
2025-04-22 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-22 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed.
2025-04-23 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-04-23 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-23 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed.
2025-04-23 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-04-23 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-04-23 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-23 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed.
2025-04-23 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed.
2025-04-23 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-04-23 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed.
2025-04-23 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-04-23 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-04-23 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325 | 191/2 | Completed.
2025-04-23 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-04-23 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-23 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed.
2025-04-23 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-23 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed.
2025-04-24 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-04-24 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-24 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed.
2025-04-24 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-04-24 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-04-24 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-24 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed.
2025-04-24 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed.
2025-04-24 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed.
2025-04-24 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-04-24 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed.
2025-04-24 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-04-24 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-04-24 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed.
2025-04-24 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed.
2025-04-24 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325 | 191/2 | Completed.
2025-04-24 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-04-24 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-24 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed.
2025-04-24 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-24 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed.
2025-04-25 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-04-25 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-04-25 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed.
2025-04-25 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-04-25 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-04-25 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-25 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed.
2025-04-25 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed.
2025-04-25 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed.
2025-04-25 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-04-25 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed.
2025-04-25 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-04-25 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-04-25 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed.
2025-04-25 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed.
2025-04-25 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325 | 191/2 | Completed.
2025-04-25 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-04-25 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-25 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed.
2025-04-25 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-25 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed.
2025-04-26 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-04-26 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed.
2025-04-26 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-04-26 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-04-26 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-26 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed.
2025-04-26 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed.
2025-04-26 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-04-26 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed.
2025-04-26 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-04-26 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-04-26 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed.
2025-04-26 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed.
2025-04-26 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325 | 191/2 | Completed.
2025-04-26 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-04-26 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-04-26 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed.
2025-04-26 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-26 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed.
2025-04-27 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-04-27 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed.
2025-04-27 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-04-27 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-04-27 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-27 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed.
2025-04-27 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed.
2025-04-27 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-04-27 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed.
2025-04-27 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-04-27 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-04-27 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed.
2025-04-27 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed.
2025-04-27 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325 | 191/2 | Completed.
2025-04-27 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-04-27 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed.
2025-04-27 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-27 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed.
2025-04-28 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-04-28 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed.
2025-04-28 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-04-28 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-04-28 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed.
2025-04-28 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed.
2025-04-28 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed.
2025-04-28 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-04-28 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed.
2025-04-28 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed.
2025-04-28 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-04-28 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-04-28 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed.
2025-04-28 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed.
2025-04-28 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-04-28 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed.
2025-04-28 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed.
2025-04-28 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-04-28 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed.
2025-04-29 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-04-29 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed.
2025-04-29 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed.
2025-04-29 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-04-29 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-04-29 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed.
2025-04-29 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed.
2025-04-29 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed.
2025-04-29 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-04-29 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed.
2025-04-29 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-04-29 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-04-29 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed.
2025-04-29 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed.
2025-04-29 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed.
2025-04-29 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-04-29 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed.
2025-04-29 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed.
2025-04-29 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed.
2025-04-30 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-04-30 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed.
2025-04-30 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-04-30 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-04-30 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed.
2025-04-30 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed.
2025-04-30 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-04-30 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed.
2025-04-30 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-04-30 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-04-30 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed.
2025-04-30 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed.
2025-04-30 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed.
2025-04-30 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-04-30 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed.
2025-04-30 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed.
2025-04-30 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed.
2025-05-01 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed.
2025-05-01 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-01 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-05-01 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed.
2025-05-01 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed.
2025-05-01 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-01 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed.
2025-05-01 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-05-01 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-05-01 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed.
2025-05-01 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed.
2025-05-01 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-05-01 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed.
2025-05-01 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed.
2025-05-02 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed.
2025-05-02 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-02 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-05-02 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed.
2025-05-02 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed.
2025-05-02 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed.
2025-05-02 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-02 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed.
2025-05-02 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-05-02 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-05-02 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed.
2025-05-02 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed.
2025-05-02 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-05-02 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed.
2025-05-02 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed.
2025-05-02 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed.
2025-05-02 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed.
2025-05-03 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed.
2025-05-03 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-03 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-05-03 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed.
2025-05-03 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed.
2025-05-03 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed.
2025-05-03 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-03 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed.
2025-05-03 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-05-03 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-05-03 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed.
2025-05-03 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed.
2025-05-03 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed.
2025-05-03 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-05-03 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed.
2025-05-03 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed.
2025-05-03 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed.
2025-05-03 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed.
2025-05-04 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed.
2025-05-04 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed.
2025-05-04 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-04 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-05-04 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed.
2025-05-04 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed.
2025-05-04 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-04 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed.
2025-05-04 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-05-04 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-05-04 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed.
2025-05-04 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed.
2025-05-04 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed.
2025-05-04 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed.
2025-05-04 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-05-04 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed.
2025-05-04 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed.
2025-05-04 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed.
2025-05-04 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed.
2025-05-05 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed.
2025-05-05 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed.
2025-05-05 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-05 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-05-05 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed.
2025-05-05 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed.
2025-05-05 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-05 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed.
2025-05-05 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-05-05 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-05-05 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed.
2025-05-05 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed.
2025-05-05 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed.
2025-05-05 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-05-05 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed.
2025-05-05 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed.
2025-05-05 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed.
2025-05-05 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed.
2025-05-06 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed.
2025-05-06 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed.
2025-05-06 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-06 | 2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
2025-05-06 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed.
2025-05-06 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed.
2025-05-06 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed.
2025-05-06 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed.
2025-05-06 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-06 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed.
2025-05-06 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-05-06 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed.
2025-05-06 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed.
2025-05-06 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed.
2025-05-06 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed.
2025-05-06 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed.
2025-05-06 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed.
2025-05-06 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed.
2025-05-07 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed.
2025-05-07 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed.
2025-05-07 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-07 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed.
2025-05-07 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed.
2025-05-07 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed.
2025-05-07 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-07 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed.
2025-05-07 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-05-07 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed.
2025-05-07 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed.
2025-05-07 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed.
2025-05-07 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed.
2025-05-07 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed.
2025-05-07 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed.
2025-05-07 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed.
2025-05-08 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed.
2025-05-08 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed.
2025-05-08 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-08 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed.
2025-05-08 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed.
2025-05-08 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed.
2025-05-08 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-08 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed.
2025-05-08 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-05-08 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed.
2025-05-08 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed.
2025-05-08 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed.
2025-05-08 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed.
2025-05-08 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed.
2025-05-08 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed.
2025-05-08 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed.
2025-05-08 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed.
2025-05-09 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed.
2025-05-09 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed.
2025-05-09 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-09 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed.
2025-05-09 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed.
2025-05-09 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed.
2025-05-09 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-09 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed.
2025-05-09 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-05-09 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed.
2025-05-09 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed.
2025-05-09 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed.
2025-05-09 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed.
2025-05-09 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed.
2025-05-09 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed.
2025-05-09 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed.
2025-05-09 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed.
2025-05-09 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed.
2025-05-10 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed.
2025-05-10 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed.
2025-05-10 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-10 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed.
2025-05-10 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed.
2025-05-10 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed.
2025-05-10 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-10 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed.
2025-05-10 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-05-10 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed.
2025-05-10 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed.
2025-05-10 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed.
2025-05-10 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed.
2025-05-10 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed.
2025-05-10 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed.
2025-05-10 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed.
2025-05-11 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed.
2025-05-11 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed.
2025-05-11 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-11 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed.
2025-05-11 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed.
2025-05-11 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed.
2025-05-11 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-11 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed.
2025-05-11 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-05-11 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed.
2025-05-11 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed.
2025-05-11 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed.
2025-05-11 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed.
2025-05-11 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed.
2025-05-11 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed.
2025-05-11 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed.
2025-05-11 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed.
2025-05-12 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed.
2025-05-12 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-12 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed.
2025-05-12 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed.
2025-05-12 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-12 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-05-12 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed.
2025-05-12 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed.
2025-05-12 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed.
2025-05-12 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed.
2025-05-13 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed.
2025-05-13 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-13 | 2025-05-13 | 2025-05-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed.
2025-05-13 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed.
2025-05-13 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed.
2025-05-13 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-13 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-05-13 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed.
2025-05-13 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed.
2025-05-13 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed.
2025-05-13 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed.
2025-05-13 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed.
2025-05-14 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed.
2025-05-14 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-14 | 2025-05-13 | 2025-05-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed.
2025-05-14 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed.
2025-05-14 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed.
2025-05-14 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-14 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-05-14 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed.
2025-05-14 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed.
2025-05-14 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed.
2025-05-14 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed.
2025-05-14 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed.
2025-05-15 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed.
2025-05-15 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-15 | 2025-05-13 | 2025-05-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed.
2025-05-15 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed.
2025-05-15 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed.
2025-05-15 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed.
2025-05-15 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-15 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-05-15 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed.
2025-05-15 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed.
2025-05-15 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed.
2025-05-15 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed.
2025-05-15 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed.
2025-05-16 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed.
2025-05-16 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed.
2025-05-16 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-16 | 2025-05-13 | 2025-05-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed.
2025-05-16 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed.
2025-05-16 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed.
2025-05-16 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed.
2025-05-16 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-16 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed.
2025-05-16 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed.
2025-05-16 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed.
2025-05-16 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed.
2025-05-16 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed.
2025-05-17 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed.
2025-05-17 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed.
2025-05-17 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-17 | 2025-05-13 | 2025-05-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed.
2025-05-17 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed.
2025-05-17 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed.
2025-05-17 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed.
2025-05-17 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-17 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed.
2025-05-17 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed.
2025-05-17 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed.
2025-05-17 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed.
2025-05-18 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed.
2025-05-18 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed.
2025-05-18 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-05-18 | 2025-05-13 | 2025-05-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed.
2025-05-18 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed.
2025-05-18 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed.
2025-05-18 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed.
2025-05-18 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-18 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed.
2025-05-18 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed.
2025-05-18 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed.
2025-05-18 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed.
2025-05-19 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed.
2025-05-19 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed.
2025-05-19 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed.
2025-05-19 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed.
2025-05-19 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-19 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed.
2025-05-19 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed.
2025-05-19 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed.
2025-05-20 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed.
2025-05-20 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed.
2025-05-20 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed.
2025-05-20 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-20 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed.
2025-05-20 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed.
2025-05-21 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed.
2025-05-21 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed.
2025-05-21 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed.
2025-05-21 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-22 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed.
2025-05-22 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed.
2025-05-22 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-23 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed.
2025-05-23 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed.
2025-05-24 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed.
2025-05-24 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed.
2025-05-24 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed.
2025-05-24 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-25 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed.
2025-05-25 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed.
2025-05-25 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-26 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed.
2025-05-26 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-27 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed.
2025-05-27 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-28 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed.
2025-05-28 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed.
2025-05-28 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-29 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed.
2025-05-29 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed.
2025-05-29 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-29 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed.
2025-05-30 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed.
2025-05-30 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed.
2025-05-30 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-30 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed.
2025-05-31 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed.
2025-05-31 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed.
2025-05-31 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-31 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed.
2025-06-01 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed.
2025-06-01 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed.
2025-06-01 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-01 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed.
2025-06-02 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed.
2025-06-02 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed.
2025-06-02 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-02 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed.
2025-06-03 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed.
2025-06-03 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed.
2025-06-03 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-03 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed.
2025-06-04 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed.
2025-06-04 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed.
2025-06-04 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-04 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed.
2025-06-05 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed.
2025-06-05 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed.
2025-06-05 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-05 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed.
2025-06-06 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed.
2025-06-06 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed.
2025-06-06 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-06 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed.
2025-06-07 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed.
2025-06-07 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed.
2025-06-07 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-08 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed.
2025-06-08 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed.
2025-06-08 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-09 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed.
2025-06-09 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-10 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed.
2025-06-10 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-11 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-11 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed.
2025-06-11 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-12 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-12 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed.
2025-06-12 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-13 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-13 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed.
2025-06-13 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-14 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-14 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-15 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-15 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-16 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-16 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-17 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-17 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-18 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-18 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-19 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-19 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-20 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-20 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-21 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-21 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-22 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-22 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-23 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-23 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-24 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-24 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-25 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-25 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-26 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-26 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-27 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-27 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-28 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-28 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-29 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-29 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-30 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-06-30 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-01 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-07-01 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-02 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-07-02 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-03 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-07-03 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-04 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-07-04 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-05 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-06 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-07 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-08 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-09 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-10 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-11 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-12 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-13 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-14 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-15 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-16 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-17 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-18 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-19 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-20 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-21 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-22 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-23 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-24 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-25 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-26 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-27 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-28 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-29 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-30 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-31 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-01 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-02 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-03 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-04 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-05 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-06 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-06 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-07 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-07 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-08 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-08 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-09 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-09 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-10 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-10 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-11 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-11 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-12 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-12 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-13 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-13 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-14 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-14 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-15 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-15 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-16 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-16 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-17 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-17 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-18 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-18 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-19 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-19 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-20 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-20 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-21 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-21 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-22 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-22 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-23 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-23 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-24 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-24 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-25 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-25 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-26 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-26 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-27 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-27 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-28 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-28 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-29 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-29 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-30 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-30 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-31 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-08-31 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-01 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-09-01 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-02 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-09-02 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-03 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-09-03 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-04 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-09-04 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-05 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-09-05 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-06 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-09-06 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-07 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-09-07 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-08 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-09-08 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-09 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-09-09 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-10 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-09-10 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-11 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-09-11 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-12 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-09-12 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-13 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-09-13 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-14 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
2025-09-14 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-15 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-16 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-17 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-18 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-19 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-20 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-21 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-22 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-23 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2024-01-28 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408 | 60/7 | Completed
2024-01-29 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408 | 60/7 | Completed
2024-01-30 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408 | 60/7 | Completed
2024-01-31 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408 | 60/7 | Completed
2024-02-01 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408 | 59/13 | Completed
2024-02-01 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408 | 60/7 | Completed
2024-02-02 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408 | 59/13 | Completed
2024-02-02 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408 | 60/7 | Completed
2024-02-03 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408 | 59/13 | Completed
2024-02-03 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408 | 63/6 | Completed
2024-02-03 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408 | 60/7 | Completed
2024-02-04 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408 | 59/13 | Completed
2024-02-04 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408 | 63/6 | Completed
2024-02-04 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408 | 60/7 | Completed
2024-02-05 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408 | 59/13 | Completed
2024-02-05 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/5 | Completed
2024-02-05 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408 | 63/6 | Completed
2024-02-06 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408 | 59/13 | Completed
2024-02-06 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/5 | Completed
2024-02-06 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408 | 63/6 | Completed
2024-02-07 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408 | 59/13 | Completed
2024-02-07 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/5 | Completed
2024-02-07 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408 | 63/6 | Completed
2024-02-08 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408 | 59/14 | Completed
2024-02-08 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/5 | Completed
2024-02-08 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408 | 63/6 | Completed
2024-02-09 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408 | 59/14 | Completed
2024-02-09 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/5 | Completed
2024-02-09 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408 | 63/6 | Completed
2024-02-09 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408 | 60/8 | Completed
2024-02-10 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408 | 59/14 | Completed
2024-02-10 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/5 | Completed
2024-02-10 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408 | 63/6 | Completed
2024-02-10 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408 | 60/8 | Completed
2024-02-11 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408 | 59/14 | Completed
2024-02-11 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/5 | Completed
2024-02-11 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408 | 63/7 | Completed
2024-02-11 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408 | 60/8 | Completed
2024-02-12 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408 | 59/14 | Completed
2024-02-12 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/6 | Completed
2024-02-12 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408 | 63/7 | Completed
2024-02-12 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408 | 60/8 | Completed
2024-02-13 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408 | 59/14 | Completed
2024-02-13 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408 | 59/12 | Completed
2024-02-13 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/6 | Completed
2024-02-13 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408 | 63/7 | Completed
2024-02-13 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408 | 60/8 | Completed
2024-02-14 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408 | 59/12 | Completed
2024-02-14 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/6 | Completed
2024-02-14 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408 | 63/7 | Completed
2024-02-14 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408 | 60/8 | Completed
2024-02-15 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408 | 59/12 | Completed
2024-02-15 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/6 | Completed
2024-02-15 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408 | 63/7 | Completed
2024-02-15 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408 | 63/8 | Completed
2024-02-15 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408 | 60/8 | Completed
2024-02-15 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408 | 60/10 | Completed
2024-02-16 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408 | 59/12 | Completed
2024-02-16 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/6 | Completed
2024-02-16 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408 | 63/8 | Completed
2024-02-16 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408 | 60/10 | Completed
2024-02-17 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408 | 59/12 | Completed
2024-02-17 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/6 | Completed
2024-02-17 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408 | 62/5 | Completed
2024-02-17 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408 | 63/8 | Completed
2024-02-17 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408 | 60/10 | Completed
2024-02-18 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408 | 59/12 | Completed
2024-02-18 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/6 | Completed
2024-02-18 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/7 | Completed
2024-02-18 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408 | 62/5 | Completed
2024-02-18 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408 | 63/8 | Completed
2024-02-18 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408 | 60/10 | Completed
2024-02-19 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408 | 59/12 | Completed
2024-02-19 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/7 | Completed
2024-02-19 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408 | 62/5 | Completed
2024-02-19 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408 | 63/8 | Completed
2024-02-19 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408 | 60/10 | Completed
2024-02-20 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408 | 59/12 | Completed
2024-02-20 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 59/10 | Completed
2024-02-20 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/7 | Completed
2024-02-20 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408 | 62/5 | Completed
2024-02-20 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408 | 63/8 | Completed
2024-02-20 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408 | 64/1 | Completed
2024-02-20 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408 | 60/10 | Completed
2024-02-21 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 59/10 | Completed
2024-02-21 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/7 | Completed
2024-02-21 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408 | 62/5 | Completed
2024-02-21 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408 | 64/1 | Completed
2024-02-21 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408 | 60/10 | Completed
2024-02-21 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408 | 60/11 | Completed
2024-02-22 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 59/10 | Completed
2024-02-22 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/7 | Completed
2024-02-22 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408 | 62/5 | Completed
2024-02-22 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 62/4 | Completed
2024-02-22 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408 | 64/1 | Completed
2024-02-22 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408 | 60/11 | Completed
2024-02-23 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 59/10 | Completed
2024-02-23 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/7 | Completed
2024-02-23 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 62/4 | Completed
2024-02-23 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408 | 64/1 | Completed
2024-02-23 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408 | 60/11 | Completed
2024-02-24 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 59/10 | Completed
2024-02-24 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 59/9 | Completed
2024-02-24 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/7 | Completed
2024-02-24 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408 | 59/8 | Completed
2024-02-24 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 62/4 | Completed
2024-02-24 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408 | 64/1 | Completed
2024-02-24 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/4 | Completed
2024-02-24 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408 | 60/11 | Completed
2024-02-25 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 59/9 | Completed
2024-02-25 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408 | 59/8 | Completed
2024-02-25 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 62/4 | Completed
2024-02-25 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/4 | Completed
2024-02-25 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408 | 60/11 | Completed
2024-02-26 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 59/9 | Completed
2024-02-26 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408 | 59/8 | Completed
2024-02-26 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 62/4 | Completed
2024-02-26 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TA408 | 62/3 | Completed
2024-02-26 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/4 | Completed
2024-02-26 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408 | 60/11 | Completed
2024-02-26 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408 | 60/6 | Completed
2024-02-27 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 59/9 | Completed
2024-02-27 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408 | 59/8 | Completed
2024-02-27 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TA408 | 62/3 | Completed
2024-02-27 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/4 | Completed
2024-02-27 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408 | 60/6 | Completed
2024-02-28 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 59/9 | Completed
2024-02-28 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408 | 59/8 | Completed
2024-02-28 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TA408 | 62/3 | Completed
2024-02-28 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/4 | Completed
2024-02-28 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408 | 60/6 | Completed
2024-02-29 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/2 | Completed
2024-02-29 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408 | 59/8 | Completed
2024-02-29 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408 | 59/16 | Completed
2024-02-29 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 62/2 | Completed
2024-02-29 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/4 | Completed
2024-02-29 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/5 | Completed
2024-02-29 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408 | 60/6 | Completed
2024-03-01 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/2 | Completed
2024-03-01 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408 | 59/16 | Completed
2024-03-01 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 62/2 | Completed
2024-03-01 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/5 | Completed
2024-03-02 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/2 | Completed
2024-03-02 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408 | 59/16 | Completed
2024-03-02 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 62/2 | Completed
2024-03-02 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/5 | Completed
2024-03-03 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/2 | Completed
2024-03-03 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408 | 59/16 | Completed
2024-03-03 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 62/2 | Completed
2024-03-03 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/5 | Completed
2024-03-04 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/2 | Completed
2024-03-04 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408 | 59/16 | Completed
2024-03-04 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 62/7 | Completed
2024-03-04 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/5 | Completed
2024-03-05 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/2 | Completed
2024-03-05 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408 | 59/16 | Completed
2024-03-05 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 62/7 | Completed
2024-03-06 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/2 | Completed
2024-03-06 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 65/4 | Completed
2024-03-06 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408 | 59/16 | Completed
2024-03-06 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 62/7 | Completed
2024-03-07 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 65/4 | Completed
2024-03-07 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408 | 59/16 | Completed
2024-03-07 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 62/7 | Completed
2024-03-07 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408 | 62/8 | Completed
2024-03-08 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 65/4 | Completed
2024-03-08 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408 | 59/16 | Completed
2024-03-08 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408 | 62/8 | Completed
2024-03-09 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 65/4 | Completed
2024-03-09 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408 | 59/16 | Completed
2024-03-09 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408 | 62/8 | Completed
2024-03-10 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 65/4 | Completed
2024-03-10 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408 | 59/16 | Completed
2024-03-10 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408 | 62/8 | Completed
2024-03-11 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 65/4 | Completed
2024-03-11 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 65/3 | Completed
2024-03-11 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408 | 59/16 | Completed
2024-03-11 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 60/5 | Completed
2024-03-11 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408 | 62/8 | Completed
2024-03-11 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 62/9 | Completed
2024-03-12 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 65/3 | Completed
2024-03-12 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 60/5 | Completed
2024-03-12 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 62/9 | Completed
2024-03-13 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 65/3 | Completed
2024-03-13 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 60/5 | Completed
2024-03-13 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 62/9 | Completed
2024-03-14 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 65/3 | Completed
2024-03-14 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 60/5 | Completed
2024-03-14 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 62/9 | Completed
2024-03-15 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 65/3 | Completed
2024-03-15 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 60/5 | Completed
2024-03-15 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 62/9 | Completed
2024-03-15 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 62/10 | Completed
2024-03-16 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 65/3 | Completed
2024-03-16 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 65/5 | Completed
2024-03-16 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 60/5 | Completed
2024-03-16 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 62/10 | Completed
2024-03-17 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 65/5 | Completed
2024-03-17 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 60/5 | Completed
2024-03-17 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 62/10 | Completed
2024-03-18 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 65/5 | Completed
2024-03-18 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408 | 60/4 | Completed
2024-03-18 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 62/10 | Completed
2024-03-18 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 61/6 | Completed
2024-03-19 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 65/5 | Completed
2024-03-19 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408 | 60/4 | Completed
2024-03-19 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 61/6 | Completed
2024-03-20 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 65/5 | Completed
2024-03-20 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/6 | Completed
2024-03-20 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408 | 60/4 | Completed
2024-03-20 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 61/6 | Completed
2024-03-21 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/6 | Completed
2024-03-21 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408 | 60/4 | Completed
2024-03-21 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 61/6 | Completed
2024-03-21 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408 | 64/6 | Completed
2024-03-22 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/6 | Completed
2024-03-22 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408 | 60/4 | Completed
2024-03-22 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 61/6 | Completed
2024-03-22 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 61/7 | Completed
2024-03-22 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408 | 64/6 | Completed
2024-03-23 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/6 | Completed
2024-03-23 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408 | 60/4 | Completed
2024-03-23 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408 | 60/3 | Completed
2024-03-23 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 61/7 | Completed
2024-03-23 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408 | 64/6 | Completed
2024-03-24 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/6 | Completed
2024-03-24 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408 | 60/3 | Completed
2024-03-24 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 61/7 | Completed
2024-03-24 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408 | 64/6 | Completed
2024-03-25 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/6 | Completed
2024-03-25 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408 | 60/3 | Completed
2024-03-25 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 61/7 | Completed
2024-03-25 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408 | 64/6 | Completed
2024-03-26 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/6 | Completed
2024-03-26 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 65/9 | Completed
2024-03-26 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408 | 60/3 | Completed
2024-03-26 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 61/7 | Completed
2024-03-26 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408 | 64/6 | Completed
2024-03-26 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/7 | Completed
2024-03-27 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 65/9 | Completed
2024-03-27 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408 | 60/3 | Completed
2024-03-27 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 61/7 | Completed
2024-03-27 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/7 | Completed
2024-03-28 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 65/9 | Completed
2024-03-28 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408 | 60/3 | Completed
2024-03-28 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 61/7 | Completed
2024-03-28 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/7 | Completed
2024-03-29 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 65/9 | Completed
2024-03-29 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408 | 60/3 | Completed
2024-03-29 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/7 | Completed
2024-03-30 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 65/9 | Completed
2024-03-30 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408 | 60/3 | Completed
2024-03-30 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/7 | Completed
2024-03-30 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/8 | Completed
2024-03-31 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 65/9 | Completed
2024-03-31 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 65/11 | Completed
2024-03-31 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408 | 60/3 | Completed
2024-03-31 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408 | 60/2 | Completed
2024-03-31 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/8 | Completed
2024-04-01 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 65/11 | Completed
2024-04-01 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408 | 60/2 | Completed
2024-04-01 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/8 | Completed
2024-04-01 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408 | 63/5 | Completed
2024-04-02 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 65/11 | Completed
2024-04-02 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408 | 60/2 | Completed
2024-04-02 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/8 | Completed
2024-04-02 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408 | 63/5 | Completed
2024-04-03 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 65/11 | Completed
2024-04-03 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408 | 60/2 | Completed
2024-04-03 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/8 | Completed
2024-04-03 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/9 | Completed
2024-04-03 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408 | 63/5 | Completed
2024-04-04 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 65/11 | Completed
2024-04-04 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408 | 60/2 | Completed
2024-04-04 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/9 | Completed
2024-04-04 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408 | 63/5 | Completed
2024-04-05 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408 | 60/2 | Completed
2024-04-05 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/9 | Completed
2024-04-05 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408 | 63/5 | Completed
2024-04-06 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 67/1 | Completed
2024-04-06 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408 | 60/2 | Completed
2024-04-06 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408 | 61/0 | Completed
2024-04-06 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/9 | Completed
2024-04-06 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408 | 63/5 | Completed
2024-04-07 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 67/1 | Completed
2024-04-07 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408 | 60/2 | Completed
2024-04-07 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408 | 61/0 | Completed
2024-04-07 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/9 | Completed
2024-04-07 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408 | 63/5 | Completed
2024-04-07 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408 | 63/4 | Completed
2024-04-08 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 67/1 | Completed
2024-04-08 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408 | 61/0 | Completed
2024-04-08 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/9 | Completed
2024-04-08 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408 | 63/4 | Completed
2024-04-09 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 67/1 | Completed
2024-04-09 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408 | 61/0 | Completed
2024-04-09 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408 | 63/4 | Completed
2024-04-10 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 67/1 | Completed
2024-04-10 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 67/2 | Completed
2024-04-10 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408 | 61/0 | Completed
2024-04-10 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408 | 63/4 | Completed
2024-04-11 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 67/2 | Completed
2024-04-11 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408 | 61/0 | Completed
2024-04-11 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408 | 63/4 | Completed
2024-04-12 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 67/2 | Completed
2024-04-12 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408 | 63/4 | Completed
2024-04-13 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 67/2 | Completed
2024-04-13 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408 | 63/4 | Completed
2024-04-13 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408 | 63/3 | Completed
2024-04-14 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 67/2 | Completed
2024-04-14 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408 | 63/3 | Completed
2024-04-15 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 67/2 | Completed
2024-04-15 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 64/10 | Completed
2024-04-15 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408 | 63/3 | Completed
2024-04-16 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 64/10 | Completed
2024-04-16 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408 | 61/2 | Completed
2024-04-16 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/2 | Completed
2024-04-16 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408 | 63/3 | Completed
2024-04-17 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 64/10 | Completed
2024-04-17 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408 | 61/2 | Completed
2024-04-17 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/2 | Completed
2024-04-17 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408 | 63/3 | Completed
2024-04-17 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408 | 63/2 | Completed
2024-04-18 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 64/10 | Completed
2024-04-18 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408 | 60/1 | Completed
2024-04-18 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408 | 61/2 | Completed
2024-04-18 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/2 | Completed
2024-04-18 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408 | 63/2 | Completed
2024-04-19 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 64/10 | Completed
2024-04-19 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408 | 60/1 | Completed
2024-04-19 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408 | 61/2 | Completed
2024-04-19 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/2 | Completed
2024-04-19 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408 | 63/2 | Completed
2024-04-20 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 64/10 | Completed
2024-04-20 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408 | 60/1 | Completed
2024-04-20 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408 | 61/2 | Completed
2024-04-20 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/2 | Completed
2024-04-20 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408 | 63/2 | Completed
2024-04-21 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408 | 65/0 | Completed
2024-04-21 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408 | 60/1 | Completed
2024-04-21 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408 | 61/2 | Completed
2024-04-21 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/2 | Completed
2024-04-21 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408 | 64/3 | Completed
2024-04-21 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408 | 63/2 | Completed
2024-04-22 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408 | 65/0 | Completed
2024-04-22 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408 | 60/1 | Completed
2024-04-22 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408 | 61/2 | Completed
2024-04-22 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408 | 61/1 | Completed
2024-04-22 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408 | 64/3 | Completed
2024-04-22 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408 | 63/2 | Completed
2024-04-22 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408 | 63/1 | Completed
2024-04-23 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408 | 65/0 | Completed
2024-04-23 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408 | 60/1 | Completed
2024-04-23 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408 | 61/1 | Completed
2024-04-23 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408 | 64/3 | Completed
2024-04-23 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408 | 63/1 | Completed
2024-04-24 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408 | 65/0 | Completed
2024-04-24 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408 | 60/1 | Completed
2024-04-24 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408 | 61/1 | Completed
2024-04-24 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408 | 64/3 | Completed
2024-04-24 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408 | 63/1 | Completed
2024-04-25 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408 | 65/0 | Completed
2024-04-25 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408 | 60/1 | Completed
2024-04-25 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408 | 61/1 | Completed
2024-04-25 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408 | 64/3 | Completed
2024-04-25 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408 | 63/1 | Completed
2024-04-26 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408 | 65/0 | Completed
2024-04-26 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408 | 61/1 | Completed
2024-04-26 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408 | 64/3 | Completed
2024-04-26 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408 | 63/1 | Completed
2024-04-27 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408 | 65/0 | Completed
2024-04-27 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/1 | Completed
2024-04-27 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408 | 61/1 | Completed
2024-04-27 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408 | 64/0 | Completed
2024-04-27 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408 | 63/1 | Completed
2024-04-27 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408 | 62/11 | Completed
2024-04-28 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/1 | Completed
2024-04-28 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408 | 61/1 | Completed
2024-04-28 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408 | 64/0 | Completed
2024-04-28 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408 | 62/11 | Completed
2024-04-29 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/1 | Completed
2024-04-29 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408 | 61/1 | Completed
2024-04-29 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 60/9 | Completed
2024-04-29 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408 | 64/0 | Completed
2024-04-29 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408 | 62/11 | Completed
2024-04-30 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/1 | Completed
2024-04-30 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 60/9 | Completed
2024-04-30 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408 | 64/0 | Completed
2024-04-30 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408 | 62/11 | Completed
2024-05-01 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/1 | Completed
2024-05-01 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 60/9 | Completed
2024-05-01 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408 | 64/0 | Completed
2024-05-01 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408 | 62/11 | Completed
2024-05-02 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/1 | Completed
2024-05-02 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 60/9 | Completed
2024-05-02 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408 | 64/0 | Completed
2024-05-02 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408 | 62/11 | Completed
2024-05-03 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/1 | Completed
2024-05-03 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 60/9 | Completed
2024-05-03 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408 | 64/0 | Completed
2024-05-03 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408 | 62/11 | Completed
2024-05-03 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408 | 63/0 | Completed
2024-05-04 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 60/9 | Completed
2024-05-04 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408 | 64/0 | Completed
2024-05-04 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408 | 63/0 | Completed
2024-05-05 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408 | 60/0 | Completed
2024-05-05 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 60/9 | Completed
2024-05-05 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408 | 61/3 | Completed
2024-05-05 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408 | 64/0 | Completed
2024-05-05 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408 | 63/0 | Completed
2024-05-06 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408 | 60/0 | Completed
2024-05-06 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408 | 61/3 | Completed
2024-05-06 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408 | 63/0 | Completed
2024-05-07 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408 | 60/0 | Completed
2024-05-07 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408 | 61/3 | Completed
2024-05-07 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408 | 63/0 | Completed
2024-05-08 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408 | 60/0 | Completed
2024-05-08 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408 | 61/3 | Completed
2024-05-08 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408 | 63/0 | Completed
2024-05-09 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408 | 60/0 | Completed
2024-05-09 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408 | 61/3 | Completed
2024-05-09 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408 | 63/0 | Completed
2024-05-10 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408 | 60/0 | Completed
2024-05-10 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408 | 61/3 | Completed
2024-05-10 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408 | 63/0 | Completed
2024-05-11 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408 | 60/0 | Completed
2024-05-11 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408 | 61/3 | Completed
2024-05-11 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408 | 61/4 | Completed
2024-05-11 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408 | 63/0 | Completed
2024-05-12 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408 | 60/0 | Completed
2024-05-12 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-12 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408 | 61/4 | Completed
2024-05-12 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408 | 63/0 | Completed
2024-05-12 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408 | 61/10 | Completed
2024-05-13 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408 | 60/0 | Completed
2024-05-13 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-13 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408 | 61/4 | Completed
2024-05-13 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408 | 61/10 | Completed
2024-05-14 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408 | 60/0 | Completed
2024-05-14 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-14 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408 | 61/4 | Completed
2024-05-14 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408 | 61/10 | Completed
2024-05-15 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408 | 60/0 | Completed
2024-05-15 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-15 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408 | 61/4 | Completed
2024-05-15 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408 | 61/10 | Completed
2024-05-16 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408 | 60/0 | Completed
2024-05-16 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-16 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408 | 61/4 | Completed
2024-05-16 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 61/5 | Completed
2024-05-16 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408 | 61/10 | Completed
2024-05-17 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408 | 60/0 | Completed
2024-05-17 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-17 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 61/5 | Completed
2024-05-17 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408 | 61/10 | Completed
2024-05-18 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408 | 60/0 | Completed
2024-05-18 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408 | 59/15 | Completed
2024-05-18 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-18 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 61/5 | Completed
2024-05-18 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408 | 61/10 | Completed
2024-05-19 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408 | 59/15 | Completed
2024-05-19 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-19 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 61/5 | Completed
2024-05-19 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408 | 61/10 | Completed
2024-05-19 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408 | 61/9 | Completed
2024-05-20 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408 | 59/15 | Completed
2024-05-20 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-20 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 61/5 | Completed
2024-05-20 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408 | 61/9 | Completed
2024-05-21 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408 | 59/15 | Completed
2024-05-21 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-21 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 61/5 | Completed
2024-05-21 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408 | 61/9 | Completed
2024-05-22 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408 | 59/15 | Completed
2024-05-22 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-22 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 61/5 | Completed
2024-05-22 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408 | 61/9 | Completed
2024-05-23 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408 | 59/15 | Completed
2024-05-23 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-23 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408 | 61/9 | Completed
2024-05-23 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408 | 61/8 | Completed
2024-05-24 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408 | 59/15 | Completed
2024-05-24 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-24 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408 | 61/8 | Completed
2024-05-25 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408 | 59/15 | Completed
2024-05-25 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-25 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408 | 61/8 | Completed
2024-05-26 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408 | 59/15 | Completed
2024-05-26 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-26 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408 | 61/8 | Completed
2024-05-27 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408 | 59/15 | Completed
2024-05-27 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-27 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408 | 61/8 | Completed
2024-05-28 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408 | 59/15 | Completed
2024-05-28 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-28 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408 | 61/8 | Completed
2024-05-29 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408 | 57/3 | Completed
2024-05-29 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408 | 59/15 | Completed
2024-05-29 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-29 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408 | 61/8 | Completed
2024-05-30 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408 | 57/3 | Completed
2024-05-30 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408 | 59/15 | Completed
2024-05-30 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-30 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408 | 61/8 | Completed
2024-05-31 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408 | 57/3 | Completed
2024-05-31 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-06-01 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408 | 57/3 | Completed
2024-06-01 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-02 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408 | 57/3 | Completed
2024-06-02 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-03 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408 | 57/3 | Completed
2024-06-03 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-04 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408 | 57/3 | Completed
2024-06-04 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-05 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408 | 57/3 | Completed
2024-06-05 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-06 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408 | 57/3 | Completed
2024-06-06 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-07 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408 | 57/3 | Completed
2024-06-07 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-08 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408 | 57/3 | Completed
2024-06-08 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-09 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408 | 57/3 | Completed
2024-06-09 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-10 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408 | 57/3 | Completed
2024-06-10 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-11 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408 | 57/3 | Completed
2024-06-11 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-12 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408 | 57/4 | Completed
2024-06-12 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-13 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408 | 57/4 | Completed
2024-06-13 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-14 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408 | 57/4 | Completed
2024-06-14 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-15 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408 | 57/4 | Completed
2024-06-15 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-16 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408 | 57/4 | Completed
2024-06-16 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-17 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408 | 57/4 | Completed
2024-06-17 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-18 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408 | 57/4 | Completed
2024-06-18 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-19 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408 | 57/4 | Completed
2024-06-19 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-20 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408 | 57/4 | Completed
2024-06-21 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408 | 57/4 | Completed
2024-06-22 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408 | 57/4 | Completed
2024-06-23 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408 | 57/4 | Completed
2024-06-24 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408 | 57/4 | Completed
2024-06-25 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408 | 57/4 | Completed
2024-06-26 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408 | 57/4 | Completed
2024-06-27 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408 | 57/4 | Completed
2024-07-04 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408 | 62/1 | Completed
2024-07-05 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408 | 62/1 | Completed
2024-07-06 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408 | 62/1 | Completed
2024-07-07 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408 | 62/1 | Completed
2024-07-08 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408 | 62/1 | Completed
2024-07-09 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408 | 62/1 | Completed
2024-07-10 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408 | 62/1 | Completed
2024-07-11 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408 | 62/1 | Completed
2024-07-12 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408 | 62/1 | Completed
2024-07-15 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408 | 62/6 | Completed
2024-07-16 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408 | 62/6 | Completed
2024-07-17 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408 | 62/6 | Completed
2024-07-18 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408 | 62/6 | Completed
2024-07-19 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408 | 62/6 | Completed
2024-07-20 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408 | 62/6 | Completed
2024-07-21 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408 | 62/6 | Completed
2024-07-22 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408 | 62/6 | Completed
2024-07-23 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408 | 62/6 | Completed
2024-07-24 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408 | 62/6 | Completed
2024-07-25 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408 | 62/6 | Completed
2024-07-26 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408 | 62/6 | Completed
2024-08-13 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408 | 57/6 | Completed
2024-08-14 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408 | 57/6 | Completed
2024-08-15 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408 | 57/6 | Completed
2024-08-16 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408 | 57/6 | Completed
2024-08-17 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408 | 57/6 | Completed
2024-08-18 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408 | 57/6 | Completed
2024-08-19 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408 | 57/6 | Completed
2024-08-20 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408 | 57/6 | Completed
2024-08-20 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 57/5 | Completed
2024-08-21 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 57/5 | Completed
2024-08-22 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 57/5 | Completed
2024-08-23 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 57/5 | Completed
2024-08-23 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408 | 10/18 | Completed
2024-08-24 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 57/5 | Completed
2024-08-24 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408 | 10/18 | Completed
2024-08-25 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 57/5 | Completed
2024-08-25 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408 | 10/18 | Completed
2024-08-26 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 57/5 | Completed
2024-08-26 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408 | 10/18 | Completed
2024-08-27 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-08-27 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408 | 10/18 | Completed
2024-08-28 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-08-28 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408 | 10/3 | Completed
2024-08-28 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408 | 50/9 | Completed
2024-08-28 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408 | 10/18 | Completed
2024-08-29 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-08-29 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408 | 10/3 | Completed
2024-08-29 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408 | 50/9 | Completed
2024-08-29 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408 | 10/18 | Completed
2024-08-30 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-08-30 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408 | 10/3 | Completed
2024-08-30 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408 | 50/9 | Completed
2024-08-30 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408 | 10/18 | Completed
2024-08-30 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 10/17 | Completed
2024-08-31 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-08-31 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408 | 10/3 | Completed
2024-08-31 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408 | 62/0 | Completed
2024-08-31 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408 | 50/9 | Completed
2024-08-31 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 10/17 | Completed
2024-09-01 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-01 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408 | 10/3 | Completed
2024-09-01 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408 | 62/0 | Completed
2024-09-01 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408 | 50/9 | Completed
2024-09-01 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 10/17 | Completed
2024-09-02 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-02 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408 | 10/3 | Completed
2024-09-02 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408 | 62/0 | Completed
2024-09-02 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408 | 50/9 | Completed
2024-09-02 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 10/17 | Completed
2024-09-03 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-03 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408 | 10/3 | Completed
2024-09-03 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408 | 62/0 | Completed
2024-09-03 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408 | 50/9 | Completed
2024-09-03 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 10/17 | Completed
2024-09-04 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-04 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408 | 10/3 | Completed
2024-09-04 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408 | 62/0 | Completed
2024-09-04 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408 | 50/9 | Completed
2024-09-04 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 10/17 | Completed
2024-09-05 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-05 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408 | 10/3 | Completed
2024-09-05 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408 | 62/0 | Completed
2024-09-05 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408 | 50/9 | Completed
2024-09-05 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 10/17 | Completed
2024-09-06 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-06 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408 | 10/3 | Completed
2024-09-06 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408 | 16/3 | Completed
2024-09-06 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408 | 62/0 | Completed
2024-09-06 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408 | 50/9 | Completed
2024-09-06 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 10/17 | Completed
2024-09-07 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-07 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408 | 16/3 | Completed
2024-09-07 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408 | 62/0 | Completed
2024-09-07 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408 | 50/9 | Completed
2024-09-07 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 10/17 | Completed
2024-09-08 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-08 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-08 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408 | 16/3 | Completed
2024-09-08 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408 | 62/0 | Completed
2024-09-08 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408 | 50/9 | Completed
2024-09-08 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 10/17 | Completed
2024-09-09 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-09 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-09 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408 | 16/3 | Completed
2024-09-09 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408 | 50/9 | Completed
2024-09-09 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408 | 10/19 | Completed
2024-09-10 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-10 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-10 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408 | 16/3 | Completed
2024-09-10 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408 | 50/10 | Completed
2024-09-10 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408 | 10/19 | Completed
2024-09-11 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-11 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-11 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408 | 16/3 | Completed
2024-09-11 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408 | 50/10 | Completed
2024-09-11 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408 | 10/19 | Completed
2024-09-12 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-12 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-12 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408 | 16/3 | Completed
2024-09-12 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408 | 50/10 | Completed
2024-09-12 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408 | 10/19 | Completed
2024-09-13 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-13 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-13 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408 | 16/3 | Completed
2024-09-13 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408 | 50/10 | Completed
2024-09-13 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408 | 10/19 | Completed
2024-09-14 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-14 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-14 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408 | 50/10 | Completed
2024-09-14 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408 | 10/19 | Completed
2024-09-15 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-15 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-15 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408 | 50/10 | Completed
2024-09-15 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408 | 10/19 | Completed
2024-09-16 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-16 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-16 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408 | 50/10 | Completed
2024-09-16 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408 | 10/19 | Completed
2024-09-17 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-17 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-17 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408 | 50/10 | Completed
2024-09-17 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408 | 10/19 | Completed
2024-09-18 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/2 | Completed
2024-09-18 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-18 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-18 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408 | 50/10 | Completed
2024-09-18 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408 | 10/19 | Completed
2024-09-19 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/2 | Completed
2024-09-19 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-19 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/6 | Completed
2024-09-19 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-19 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408 | 50/10 | Completed
2024-09-19 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408 | 51/1 | Completed
2024-09-19 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408 | 10/20 | Completed
2024-09-20 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/2 | Completed
2024-09-20 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/6 | Completed
2024-09-20 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-20 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408 | 51/1 | Completed
2024-09-20 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408 | 10/20 | Completed
2024-09-21 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/2 | Completed
2024-09-21 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/6 | Completed
2024-09-21 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408 | 15/1 | Completed
2024-09-21 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-21 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408 | 51/1 | Completed
2024-09-21 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408 | 10/20 | Completed
2024-09-22 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/2 | Completed
2024-09-22 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/6 | Completed
2024-09-22 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408 | 15/1 | Completed
2024-09-22 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-22 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408 | 51/1 | Completed
2024-09-22 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408 | 10/20 | Completed
2024-09-23 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/4 | Completed
2024-09-23 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/6 | Completed
2024-09-23 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408 | 15/1 | Completed
2024-09-23 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-23 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408 | 51/1 | Completed
2024-09-23 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408 | 10/20 | Completed
2024-09-24 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/4 | Completed
2024-09-24 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/6 | Completed
2024-09-24 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408 | 15/1 | Completed
2024-09-24 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-24 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408 | 51/1 | Completed
2024-09-24 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408 | 10/20 | Completed
2024-09-25 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/4 | Completed
2024-09-25 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/6 | Completed
2024-09-25 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408 | 10/6 | Completed
2024-09-25 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408 | 15/1 | Completed
2024-09-25 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-25 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408 | 51/1 | Completed
2024-09-25 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408 | 10/20 | Completed
2024-09-26 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/4 | Completed
2024-09-26 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/6 | Completed
2024-09-26 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408 | 10/6 | Completed
2024-09-26 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408 | 15/1 | Completed
2024-09-26 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408 | 51/1 | Completed
2024-09-26 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408 | 51/2 | Completed
2024-09-27 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/4 | Completed
2024-09-27 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/6 | Completed
2024-09-27 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408 | 10/6 | Completed
2024-09-27 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408 | 11A/2 | Completed
2024-09-27 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 57/7 | Completed
2024-09-27 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408 | 51/2 | Completed
2024-09-28 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/6 | Completed
2024-09-28 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408 | 10/6 | Completed
2024-09-28 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408 | 14A/1 | Completed
2024-09-28 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-09-28 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408 | 16/4 | Completed
2024-09-28 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408 | 11A/2 | Completed
2024-09-28 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 57/7 | Completed
2024-09-28 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408 | 51/2 | Completed
2024-09-29 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/6 | Completed
2024-09-29 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408 | 10/6 | Completed
2024-09-29 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408 | 14A/1 | Completed
2024-09-29 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-09-29 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408 | 16/4 | Completed
2024-09-29 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408 | 11A/2 | Completed
2024-09-29 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 57/7 | Completed
2024-09-29 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408 | 51/2 | Completed
2024-09-30 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/6 | Completed
2024-09-30 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408 | 14A/1 | Completed
2024-09-30 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-09-30 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408 | 16/4 | Completed
2024-09-30 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408 | 11A/2 | Completed
2024-09-30 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 57/7 | Completed
2024-09-30 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408 | 51/2 | Completed
2024-10-01 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408 | 52/7 | Completed
2024-10-01 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408 | 14A/1 | Completed
2024-10-01 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-01 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408 | 16/4 | Completed
2024-10-01 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408 | 11A/2 | Completed
2024-10-01 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 57/7 | Completed
2024-10-01 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408 | 51/2 | Completed
2024-10-02 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408 | 52/7 | Completed
2024-10-02 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408 | 14A/1 | Completed
2024-10-02 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-02 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408 | 16/4 | Completed
2024-10-02 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408 | 11A/2 | Completed
2024-10-02 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408 | 50/0 | Completed
2024-10-02 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408 | 51/2 | Completed
2024-10-03 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408 | 52/7 | Completed
2024-10-03 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408 | 14A/1 | Completed
2024-10-03 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-03 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408 | 16/4 | Completed
2024-10-03 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408 | 11A/2 | Completed
2024-10-03 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408 | 50/0 | Completed
2024-10-03 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408 | 51/2 | Completed
2024-10-04 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/1 | Completed
2024-10-04 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408 | 52/7 | Completed
2024-10-04 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-04 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408 | 11A/2 | Completed
2024-10-04 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408 | 50/0 | Completed
2024-10-04 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408 | 51/2 | Completed
2024-10-05 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/1 | Completed
2024-10-05 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408 | 52/7 | Completed
2024-10-05 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408 | 10/9 | Completed
2024-10-05 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-05 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408 | 17/1 | Completed
2024-10-05 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408 | 11A/2 | Completed
2024-10-05 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408 | 50/0 | Completed
2024-10-06 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/1 | Completed
2024-10-06 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408 | 52/7 | Completed
2024-10-06 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408 | 10/9 | Completed
2024-10-06 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-06 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408 | 17/1 | Completed
2024-10-06 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408 | 11A/2 | Completed
2024-10-06 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408 | 50/0 | Completed
2024-10-07 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408 | 10/21 | Completed
2024-10-07 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/1 | Completed
2024-10-07 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408 | 52/7 | Completed
2024-10-07 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408 | 10/9 | Completed
2024-10-07 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-07 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408 | 17/1 | Completed
2024-10-07 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408 | 11A/2 | Completed
2024-10-07 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408 | 50/0 | Completed
2024-10-07 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408 | 50/1 | Completed
2024-10-07 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408 | 50/8 | Completed
2024-10-08 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408 | 10/21 | Completed
2024-10-08 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/1 | Completed
2024-10-08 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/8 | Completed
2024-10-08 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408 | 10/9 | Completed
2024-10-08 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-08 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408 | 17/1 | Completed
2024-10-08 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408 | 50/1 | Completed
2024-10-08 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408 | 50/8 | Completed
2024-10-09 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408 | 10/21 | Completed
2024-10-09 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/8 | Completed
2024-10-09 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-09 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408 | 17/1 | Completed
2024-10-09 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408 | 50/1 | Completed
2024-10-09 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408 | 50/8 | Completed
2024-10-10 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408 | 10/21 | Completed
2024-10-10 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/8 | Completed
2024-10-10 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-10 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408 | 17/1 | Completed
2024-10-10 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408 | 73/2 | Completed
2024-10-10 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408 | 50/1 | Completed
2024-10-10 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408 | 50/8 | Completed
2024-10-11 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/8 | Completed
2024-10-11 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-11 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408 | 17/2 | Completed
2024-10-11 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408 | 73/2 | Completed
2024-10-11 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408 | 50/1 | Completed
2024-10-11 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408 | 50/8 | Completed
2024-10-12 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/8 | Completed
2024-10-12 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408 | 10/4 | Completed
2024-10-12 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-12 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408 | 17/2 | Completed
2024-10-12 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408 | 73/2 | Completed
2024-10-12 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408 | 50/1 | Completed
2024-10-12 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408 | 50/8 | Completed
2024-10-13 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/8 | Completed
2024-10-13 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408 | 10/4 | Completed
2024-10-13 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-13 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408 | 17/2 | Completed
2024-10-13 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408 | 73/2 | Completed
2024-10-13 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408 | 50/1 | Completed
2024-10-13 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408 | 50/3 | Completed
2024-10-13 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408 | 50/8 | Completed
2024-10-14 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/8 | Completed
2024-10-14 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408 | 10/4 | Completed
2024-10-14 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-14 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408 | 17/2 | Completed
2024-10-14 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408 | 73/2 | Completed
2024-10-14 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408 | 50/1 | Completed
2024-10-14 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408 | 50/3 | Completed
2024-10-14 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408 | 50/8 | Completed
2024-10-15 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/8 | Completed
2024-10-15 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408 | 10/4 | Completed
2024-10-15 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-15 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408 | 17/2 | Completed
2024-10-15 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408 | 73/2 | Completed
2024-10-15 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408 | 50/1 | Completed
2024-10-15 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408 | 50/3 | Completed
2024-10-15 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408 | 50/8 | Completed
2024-10-16 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/8 | Completed
2024-10-16 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408 | 10/4 | Completed
2024-10-16 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-16 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408 | 17/2 | Completed
2024-10-16 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-10-16 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408 | 73/2 | Completed
2024-10-16 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408 | 50/3 | Completed
2024-10-16 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408 | 50/8 | Completed
2024-10-17 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/8 | Completed
2024-10-17 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408 | 10/4 | Completed
2024-10-17 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-17 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408 | 17/2 | Completed
2024-10-17 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-10-17 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408 | 73/2 | Completed
2024-10-17 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408 | 50/3 | Completed
2024-10-17 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408 | 59/11 | Completed
2024-10-18 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/8 | Completed
2024-10-18 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408 | 16/0 | Completed
2024-10-18 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-18 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408 | 17/2 | Completed
2024-10-18 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-10-18 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-10-18 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408 | 73/2 | Completed
2024-10-18 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408 | 50/3 | Completed
2024-10-18 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/2 | Completed
2024-10-18 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408 | 59/11 | Completed
2024-10-19 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408 | 19/0 | Completed
2024-10-19 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/8 | Completed
2024-10-19 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408 | 10/8 | Completed
2024-10-19 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408 | 16/0 | Completed
2024-10-19 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-19 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408 | 17/2 | Completed
2024-10-19 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-10-19 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-10-19 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408 | 73/2 | Completed
2024-10-19 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/2 | Completed
2024-10-19 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408 | 59/11 | Completed
2024-10-20 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 64/11 | Completed
2024-10-20 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408 | 19/0 | Completed
2024-10-20 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408 | 10/8 | Completed
2024-10-20 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408 | 16/0 | Completed
2024-10-20 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408 | 16/2 | Completed
2024-10-20 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-10-20 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-10-20 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408 | 73/2 | Completed
2024-10-20 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/2 | Completed
2024-10-20 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408 | 59/11 | Completed
2024-10-21 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408 | 17/3 | Completed
2024-10-21 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 64/11 | Completed
2024-10-21 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408 | 19/0 | Completed
2024-10-21 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408 | 10/8 | Completed
2024-10-21 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408 | 16/0 | Completed
2024-10-21 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408 | 16/2 | Completed
2024-10-21 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-10-21 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-10-21 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 73/1 | Completed
2024-10-21 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/2 | Completed
2024-10-21 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408 | 59/11 | Completed
2024-10-22 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408 | 17/3 | Completed
2024-10-22 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 64/11 | Completed
2024-10-22 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408 | 19/0 | Completed
2024-10-22 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408 | 10/8 | Completed
2024-10-22 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408 | 16/0 | Completed
2024-10-22 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408 | 16/2 | Completed
2024-10-22 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-10-22 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-10-22 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 73/1 | Completed
2024-10-22 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/2 | Completed
2024-10-22 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408 | 59/11 | Completed
2024-10-23 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408 | 17/3 | Completed
2024-10-23 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 64/11 | Completed
2024-10-23 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408 | 19/0 | Completed
2024-10-23 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408 | 16/0 | Completed
2024-10-23 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408 | 55/6 | Completed
2024-10-23 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408 | 16/2 | Completed
2024-10-23 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-10-23 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-10-23 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 73/1 | Completed
2024-10-23 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/2 | Completed
2024-10-23 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408 | 59/11 | Completed
2024-10-24 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408 | 17/3 | Completed
2024-10-24 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 64/11 | Completed
2024-10-24 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408 | 19/0 | Completed
2024-10-24 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408 | 16/0 | Completed
2024-10-24 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408 | 55/6 | Completed
2024-10-24 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408 | 16/2 | Completed
2024-10-24 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-10-24 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-10-24 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 73/1 | Completed
2024-10-24 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/2 | Completed
2024-10-24 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/4 | Completed
2024-10-24 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408 | 59/11 | Completed
2024-10-25 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408 | 17/3 | Completed
2024-10-25 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408 | 19/0 | Completed
2024-10-25 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408 | 16/0 | Completed
2024-10-25 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408 | 55/6 | Completed
2024-10-25 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408 | 16/2 | Completed
2024-10-25 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-10-25 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-10-25 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 73/1 | Completed
2024-10-25 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/4 | Completed
2024-10-25 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408 | 59/11 | Completed
2024-10-26 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408 | 17/3 | Completed
2024-10-26 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408 | 19/0 | Completed
2024-10-26 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408 | 16/0 | Completed
2024-10-26 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408 | 55/6 | Completed
2024-10-26 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408 | 16/2 | Completed
2024-10-26 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-10-26 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-10-26 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 73/1 | Completed
2024-10-26 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/4 | Completed
2024-10-26 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408 | 59/11 | Completed
2024-10-27 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408 | 17/3 | Completed
2024-10-27 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408 | 16/0 | Completed
2024-10-27 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408 | 55/6 | Completed
2024-10-27 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-10-27 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-10-27 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 73/1 | Completed
2024-10-27 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/4 | Completed
2024-10-27 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408 | 59/3 | Completed
2024-10-28 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408 | 55/6 | Completed
2024-10-28 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-10-28 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-10-28 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 73/1 | Completed
2024-10-28 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/4 | Completed
2024-10-28 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408 | 59/3 | Completed
2024-10-29 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408 | 55/6 | Completed
2024-10-29 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-10-29 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-10-29 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 73/1 | Completed
2024-10-29 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/4 | Completed
2024-10-29 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408 | 59/3 | Completed
2024-10-30 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408 | 55/6 | Completed
2024-10-30 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-10-30 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-10-30 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/4 | Completed
2024-10-30 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408 | 59/3 | Completed
2024-10-31 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408 | 55/6 | Completed
2024-10-31 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-10-31 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-10-31 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408 | 59/3 | Completed
2024-11-01 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408 | 55/6 | Completed
2024-11-01 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408 | 55/5 | Completed
2024-11-01 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-11-01 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-11-01 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 50/7 | Completed
2024-11-01 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408 | 59/3 | Completed
2024-11-01 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408 | 59/4 | Completed
2024-11-02 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408 | 10/11 | Completed
2024-11-02 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408 | 55/5 | Completed
2024-11-02 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-02 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-11-02 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-11-02 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 50/7 | Completed
2024-11-02 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408 | 59/3 | Completed
2024-11-02 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408 | 59/4 | Completed
2024-11-03 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408 | 16/5 | Completed
2024-11-03 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408 | 10/11 | Completed
2024-11-03 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408 | 55/5 | Completed
2024-11-03 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-03 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-11-03 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 50/7 | Completed
2024-11-03 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408 | 59/4 | Completed
2024-11-04 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408 | 16/5 | Completed
2024-11-04 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408 | 10/11 | Completed
2024-11-04 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408 | 55/5 | Completed
2024-11-04 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-04 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408 | 17/0 | Completed
2024-11-04 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-11-04 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 50/7 | Completed
2024-11-04 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/6 | Completed
2024-11-04 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408 | 59/4 | Completed
2024-11-05 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408 | 16/5 | Completed
2024-11-05 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408 | 10/11 | Completed
2024-11-05 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408 | 16/1 | Completed
2024-11-05 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408 | 55/5 | Completed
2024-11-05 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-05 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408 | 17/0 | Completed
2024-11-05 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-11-05 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/6 | Completed
2024-11-05 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408 | 59/4 | Completed
2024-11-06 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408 | 16/5 | Completed
2024-11-06 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408 | 16/1 | Completed
2024-11-06 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408 | 55/5 | Completed
2024-11-06 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-06 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408 | 17/0 | Completed
2024-11-06 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-11-06 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/6 | Completed
2024-11-06 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408 | 59/4 | Completed
2024-11-07 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408 | 16/5 | Completed
2024-11-07 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408 | 16/1 | Completed
2024-11-07 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408 | 55/5 | Completed
2024-11-07 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-07 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408 | 17/0 | Completed
2024-11-07 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-11-07 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/6 | Completed
2024-11-07 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408 | 59/4 | Completed
2024-11-07 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408 | 43/9 | Completed
2024-11-08 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408 | 16/5 | Completed
2024-11-08 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408 | 16/1 | Completed
2024-11-08 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408 | 55/5 | Completed
2024-11-08 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-08 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408 | 17/0 | Completed
2024-11-08 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-11-08 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/6 | Completed
2024-11-08 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408 | 59/4 | Completed
2024-11-08 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408 | 43/9 | Completed
2024-11-09 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408 | 16/5 | Completed
2024-11-09 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/9 | Completed
2024-11-09 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408 | 16/1 | Completed
2024-11-09 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408 | 55/5 | Completed
2024-11-09 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-09 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408 | 17/0 | Completed
2024-11-09 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/6 | Completed
2024-11-09 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408 | 59/4 | Completed
2024-11-09 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408 | 43/9 | Completed
2024-11-10 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/9 | Completed
2024-11-10 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408 | 55/5 | Completed
2024-11-10 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-10 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408 | 17/0 | Completed
2024-11-10 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408 | 11/5 | Completed
2024-11-10 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/6 | Completed
2024-11-10 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408 | 43/9 | Completed
2024-11-11 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/9 | Completed
2024-11-11 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408 | 13/2 | Completed
2024-11-11 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408 | 55/5 | Completed
2024-11-11 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-11 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408 | 17/0 | Completed
2024-11-11 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408 | 11/5 | Completed
2024-11-11 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 49/7 | Completed
2024-11-11 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408 | 43/9 | Completed
2024-11-12 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/9 | Completed
2024-11-12 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408 | 13/2 | Completed
2024-11-12 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408 | 55/5 | Completed
2024-11-12 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408 | 59/2 | Completed
2024-11-12 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-12 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408 | 17/0 | Completed
2024-11-12 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408 | 11/5 | Completed
2024-11-12 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 49/7 | Completed
2024-11-12 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408 | 43/9 | Completed
2024-11-13 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/9 | Completed
2024-11-13 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 73/8 | Completed
2024-11-13 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408 | 52/10 | Completed
2024-11-13 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408 | 13/2 | Completed
2024-11-13 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408 | 59/2 | Completed
2024-11-13 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-13 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408 | 17/0 | Completed
2024-11-13 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408 | 11/5 | Completed
2024-11-13 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 49/7 | Completed
2024-11-13 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408 | 43/9 | Completed
2024-11-14 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 73/8 | Completed
2024-11-14 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408 | 52/10 | Completed
2024-11-14 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408 | 13/2 | Completed
2024-11-14 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408 | 59/2 | Completed
2024-11-14 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-14 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408 | 17/0 | Completed
2024-11-14 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408 | 11/5 | Completed
2024-11-14 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 49/7 | Completed
2024-11-14 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408 | 43/9 | Completed
2024-11-15 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 73/8 | Completed
2024-11-15 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408 | 52/10 | Completed
2024-11-15 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408 | 13/2 | Completed
2024-11-15 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408 | 59/2 | Completed
2024-11-15 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-15 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408 | 11/5 | Completed
2024-11-15 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 49/6 | Completed
2024-11-15 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408 | 43/9 | Completed
2024-11-16 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 73/8 | Completed
2024-11-16 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408 | 52/10 | Completed
2024-11-16 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408 | 13/2 | Completed
2024-11-16 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408 | 59/2 | Completed
2024-11-16 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-16 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408 | 11/5 | Completed
2024-11-16 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 49/6 | Completed
2024-11-16 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408 | 43/9 | Completed
2024-11-17 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 73/8 | Completed
2024-11-17 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408 | 73/6 | Completed
2024-11-17 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408 | 52/10 | Completed
2024-11-17 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408 | 13/2 | Completed
2024-11-17 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408 | 59/2 | Completed
2024-11-17 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-17 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408 | 11/5 | Completed
2024-11-17 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 49/6 | Completed
2024-11-17 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408 | 43/9 | Completed
2024-11-18 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408 | 73/6 | Completed
2024-11-18 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408 | 52/10 | Completed
2024-11-18 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408 | 13/2 | Completed
2024-11-18 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408 | 59/2 | Completed
2024-11-18 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-18 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408 | 11/5 | Completed
2024-11-18 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 49/6 | Completed
2024-11-18 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 49/4 | Completed
2024-11-18 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408 | 43/9 | Completed
2024-11-19 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408 | 73/6 | Completed
2024-11-19 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408 | 52/10 | Completed
2024-11-19 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408 | 59/2 | Completed
2024-11-19 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-19 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 49/4 | Completed
2024-11-19 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408 | 43/8 | Completed
2024-11-20 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408 | 73/6 | Completed
2024-11-20 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408 | 52/10 | Completed
2024-11-20 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408 | 59/2 | Completed
2024-11-20 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-20 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 49/4 | Completed
2024-11-20 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408 | 43/8 | Completed
2024-11-21 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408 | 52/10 | Completed
2024-11-21 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408 | 59/2 | Completed
2024-11-21 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-21 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 49/4 | Completed
2024-11-21 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408 | 43/8 | Completed
2024-11-22 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408 | 17/5 | Completed
2024-11-22 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408 | 52/10 | Completed
2024-11-22 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408 | 59/2 | Completed
2024-11-22 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-22 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 49/4 | Completed
2024-11-22 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408 | 43/8 | Completed
2024-11-23 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408 | 17/5 | Completed
2024-11-23 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408 | 52/10 | Completed
2024-11-23 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408 | 59/2 | Completed
2024-11-23 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 49/5 | Completed
2024-11-23 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408 | 43/8 | Completed
2024-11-24 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408 | 17/5 | Completed
2024-11-24 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408 | 11A/9 | Completed
2024-11-24 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408 | 52/10 | Completed
2024-11-24 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408 | 59/2 | Completed
2024-11-24 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408 | 72/3 | Completed
2024-11-24 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 49/5 | Completed
2024-11-24 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408 | 43/8 | Completed
2024-11-25 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408 | 17/5 | Completed
2024-11-25 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408 | 11A/9 | Completed
2024-11-25 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408 | 52/10 | Completed
2024-11-25 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408 | 59/1 | Completed
2024-11-25 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408 | 72/3 | Completed
2024-11-25 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 49/5 | Completed
2024-11-25 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408 | 43/8 | Completed
2024-11-26 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408 | 17/5 | Completed
2024-11-26 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408 | 11A/9 | Completed
2024-11-26 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408 | 52/9 | Completed
2024-11-26 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408 | 59/1 | Completed
2024-11-26 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408 | 72/3 | Completed
2024-11-26 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 49/5 | Completed
2024-11-26 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408 | 43/8 | Completed
2024-11-27 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408 | 17/5 | Completed
2024-11-27 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408 | 11A/9 | Completed
2024-11-27 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408 | 52/9 | Completed
2024-11-27 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408 | 59/1 | Completed
2024-11-27 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408 | 72/3 | Completed
2024-11-27 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 49/5 | Completed
2024-11-27 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 49/2 | Completed
2024-11-27 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408 | 43/8 | Completed
2024-11-28 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408 | 17/5 | Completed
2024-11-28 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408 | 11A/9 | Completed
2024-11-28 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408 | 52/9 | Completed
2024-11-28 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408 | 11A/7 | Completed
2024-11-28 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408 | 59/1 | Completed
2024-11-28 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408 | 72/3 | Completed
2024-11-28 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 49/2 | Completed
2024-11-29 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408 | 17/5 | Completed
2024-11-29 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408 | 11A/9 | Completed
2024-11-29 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408 | 52/9 | Completed
2024-11-29 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408 | 11A/7 | Completed
2024-11-29 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408 | 59/1 | Completed
2024-11-29 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408 | 72/3 | Completed
2024-11-29 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 49/2 | Completed
2024-11-30 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408 | 17/5 | Completed
2024-11-30 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408 | 11A/9 | Completed
2024-11-30 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408 | 52/9 | Completed
2024-11-30 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408 | 10/12 | Completed
2024-11-30 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408 | 11A/7 | Completed
2024-11-30 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408 | 59/1 | Completed
2024-11-30 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408 | 72/3 | Completed
2024-11-30 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 49/2 | Completed
2024-12-01 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408 | 11A/3 | Completed
2024-12-01 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408 | 52/9 | Completed
2024-12-01 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408 | 10/12 | Completed
2024-12-01 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408 | 11A/7 | Completed
2024-12-01 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408 | 59/1 | Completed
2024-12-02 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408 | 11A/3 | Completed
2024-12-02 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408 | 52/9 | Completed
2024-12-02 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408 | 10/12 | Completed
2024-12-02 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408 | 11A/7 | Completed
2024-12-02 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408 | 59/1 | Completed
2024-12-02 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 49/3 | Completed
2024-12-03 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408 | 11A/3 | Completed
2024-12-03 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408 | 52/9 | Completed
2024-12-03 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408 | 10/12 | Completed
2024-12-03 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408 | 11A/7 | Completed
2024-12-03 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408 | 59/1 | Completed
2024-12-03 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408 | 59/0 | Completed
2024-12-03 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 49/3 | Completed
2024-12-04 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408 | 11A/3 | Completed
2024-12-04 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408 | 52/9 | Completed
2024-12-04 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408 | 10/12 | Completed
2024-12-04 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408 | 11A/7 | Completed
2024-12-04 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408 | 59/0 | Completed
2024-12-04 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 49/3 | Completed
2024-12-05 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408 | 11A/3 | Completed
2024-12-05 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408 | 52/9 | Completed
2024-12-05 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408 | 10/12 | Completed
2024-12-05 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408 | 11A/7 | Completed
2024-12-05 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408 | 59/0 | Completed
2024-12-05 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 49/3 | Completed
2024-12-06 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408 | 11A/3 | Completed
2024-12-06 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408 | 10/12 | Completed
2024-12-06 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408 | 11A/7 | Completed
2024-12-06 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408 | 59/0 | Completed
2024-12-06 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 49/1 | Completed
2024-12-07 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408 | 11A/3 | Completed
2024-12-07 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408 | 10/12 | Completed
2024-12-07 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408 | 59/0 | Completed
2024-12-07 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 49/1 | Completed
2024-12-08 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408 | 10/12 | Completed
2024-12-08 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408 | 59/0 | Completed
2024-12-08 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 49/1 | Completed
2024-12-09 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/3 | Completed
2024-12-09 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408 | 11A/6 | Completed
2024-12-09 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408 | 10/12 | Completed
2024-12-09 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408 | 59/0 | Completed
2024-12-09 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 49/1 | Completed
2024-12-10 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/3 | Completed
2024-12-10 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408 | 11A/6 | Completed
2024-12-10 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408 | 10/12 | Completed
2024-12-10 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408 | 59/0 | Completed
2024-12-11 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/3 | Completed
2024-12-11 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408 | 11A/6 | Completed
2024-12-11 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408 | 10/12 | Completed
2024-12-11 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408 | 59/0 | Completed
2024-12-12 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/3 | Completed
2024-12-12 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408 | 11A/6 | Completed
2024-12-12 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408 | 59/0 | Completed
2024-12-13 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/3 | Completed
2024-12-13 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408 | 11A/6 | Completed
2024-12-13 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408 | 59/0 | Completed
2024-12-14 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408 | 11A/6 | Completed
2024-12-14 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408 | 59/0 | Completed
2024-12-15 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408 | 11A/6 | Completed
2024-12-15 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408 | 59/0 | Completed
2024-12-16 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408 | 11A/6 | Completed
2024-12-16 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408 | 59/0 | Completed
2024-12-20 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/8 | Completed
2024-12-21 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/8 | Completed
2024-12-22 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/8 | Completed
2024-12-23 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/8 | Completed
2024-12-24 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/8 | Completed
2024-12-25 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408 | 11A/5 | Completed
2024-12-25 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/8 | Completed
2024-12-25 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408 | 43/0 | Completed
2024-12-26 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408 | 11A/5 | Completed
2024-12-26 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/8 | Completed
2024-12-26 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408 | 43/0 | Completed
2024-12-27 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408 | 11A/5 | Completed
2024-12-27 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/8 | Completed
2024-12-27 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408 | 43/0 | Completed
2024-12-28 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408 | 11A/5 | Completed
2024-12-28 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/7 | Completed
2024-12-28 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408 | 43/0 | Completed
2024-12-29 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408 | 11A/5 | Completed
2024-12-29 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/7 | Completed
2024-12-29 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408 | 43/0 | Completed
2024-12-30 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408 | 11A/5 | Completed
2024-12-30 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/7 | Completed
2024-12-30 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408 | 43/0 | Completed
2024-12-31 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408 | 11A/5 | Completed
2024-12-31 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/7 | Completed
2024-12-31 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408 | 43/0 | Completed
2025-01-01 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408 | 11A/5 | Completed
2025-01-01 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/7 | Completed
2025-01-01 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408 | 43/0 | Completed
2025-01-02 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408 | 11A/5 | Completed
2025-01-02 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/7 | Completed
2025-01-02 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408 | 43/0 | Completed
2025-01-03 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408 | 73/0 | Completed
2025-01-03 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408 | 11A/5 | Completed
2025-01-03 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/7 | Completed
2025-01-03 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408 | 43/0 | Completed
2025-01-04 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408 | 73/0 | Completed
2025-01-04 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408 | 11A/5 | Completed
2025-01-04 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408 | 53/8 | Completed
2025-01-04 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/7 | Completed
2025-01-04 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408 | 43/0 | Completed
2025-01-05 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408 | 73/0 | Completed
2025-01-05 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408 | 53/8 | Completed
2025-01-05 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408 | 74/0 | Completed
2025-01-05 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408 | 43/0 | Completed
2025-01-06 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408 | 73/0 | Completed
2025-01-06 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408 | 53/8 | Completed
2025-01-06 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408 | 74/0 | Completed
2025-01-06 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408 | 43/0 | Completed
2025-01-07 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408 | 73/0 | Completed
2025-01-07 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408 | 53/8 | Completed
2025-01-07 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408 | 74/0 | Completed
2025-01-07 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408 | 43/0 | Completed
2025-01-08 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408 | 73/0 | Completed
2025-01-08 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408 | 53/8 | Completed
2025-01-08 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408 | 74/0 | Completed
2025-01-08 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 43/1 | Completed
2025-01-09 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408 | 73/0 | Completed
2025-01-09 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408 | 53/8 | Completed
2025-01-09 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408 | 74/0 | Completed
2025-01-09 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 43/1 | Completed
2025-01-10 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/4 | Completed
2025-01-10 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408 | 53/7 | Completed
2025-01-10 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408 | 74/0 | Completed
2025-01-10 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 43/1 | Completed
2025-01-11 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408 | 43/7 | Completed
2025-01-11 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/4 | Completed
2025-01-11 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408 | 53/7 | Completed
2025-01-11 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-11 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408 | 74/0 | Completed
2025-01-11 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 43/1 | Completed
2025-01-12 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408 | 43/7 | Completed
2025-01-12 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/4 | Completed
2025-01-12 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408 | 53/7 | Completed
2025-01-12 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-12 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408 | 74/0 | Completed
2025-01-12 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 43/1 | Completed
2025-01-13 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408 | 43/7 | Completed
2025-01-13 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/4 | Completed
2025-01-13 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408 | 53/7 | Completed
2025-01-13 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-13 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408 | 74/0 | Completed
2025-01-13 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 43/1 | Completed
2025-01-14 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408 | 43/7 | Completed
2025-01-14 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/4 | Completed
2025-01-14 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408 | 53/7 | Completed
2025-01-14 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-14 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408 | 73/7 | Completed
2025-01-14 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 43/1 | Completed
2025-01-15 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408 | 43/7 | Completed
2025-01-15 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/5 | Completed
2025-01-15 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408 | 53/7 | Completed
2025-01-15 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-15 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408 | 73/7 | Completed
2025-01-15 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 43/1 | Completed
2025-01-16 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408 | 43/7 | Completed
2025-01-16 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/5 | Completed
2025-01-16 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408 | 53/7 | Completed
2025-01-16 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-16 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408 | 73/7 | Completed
2025-01-16 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 43/1 | Completed
2025-01-17 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408 | 43/7 | Completed
2025-01-17 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/5 | Completed
2025-01-17 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408 | 53/7 | Completed
2025-01-17 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-17 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408 | 73/7 | Completed
2025-01-17 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 43/1 | Completed
2025-01-18 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408 | 43/7 | Completed
2025-01-18 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/5 | Completed
2025-01-18 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408 | 53/7 | Completed
2025-01-18 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-18 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408 | 73/7 | Completed
2025-01-19 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408 | 43/6 | Completed
2025-01-19 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/5 | Completed
2025-01-19 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 53/6 | Completed
2025-01-19 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-19 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408 | 73/7 | Completed
2025-01-20 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408 | 43/6 | Completed
2025-01-20 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 53/6 | Completed
2025-01-20 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-21 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408 | 43/6 | Completed
2025-01-21 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408 | 72/0 | Completed
2025-01-21 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 53/6 | Completed
2025-01-21 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-22 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408 | 43/6 | Completed
2025-01-22 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408 | 72/0 | Completed
2025-01-22 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 53/6 | Completed
2025-01-22 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-23 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408 | 43/6 | Completed
2025-01-23 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408 | 72/0 | Completed
2025-01-23 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 53/6 | Completed
2025-01-23 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-24 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408 | 43/6 | Completed
2025-01-24 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408 | 72/0 | Completed
2025-01-24 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 53/6 | Completed
2025-01-24 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-25 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408 | 43/6 | Completed
2025-01-25 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408 | 72/0 | Completed
2025-01-25 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 53/6 | Completed
2025-01-25 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-26 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408 | 43/6 | Completed
2025-01-26 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408 | 72/0 | Completed
2025-01-26 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 53/6 | Completed
2025-01-26 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-27 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408 | 43/6 | Completed
2025-01-27 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408 | 72/0 | Completed
2025-01-27 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 53/6 | Completed
2025-01-27 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-28 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408 | 43/6 | Completed
2025-01-28 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 72/1 | Completed
2025-01-28 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 53/6 | Completed
2025-01-28 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-29 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408 | 43/6 | Completed
2025-01-29 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 72/1 | Completed
2025-01-29 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 53/6 | Completed
2025-01-29 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-29 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 65/10 | Completed
2025-01-30 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 72/1 | Completed
2025-01-30 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 53/6 | Completed
2025-01-30 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 65/10 | Completed
2025-01-31 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408 | 1A/1 | Completed
2025-01-31 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 72/1 | Completed
2025-01-31 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 65/10 | Completed
2025-01-31 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408 | 51/0 | Completed
2025-02-01 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408 | 1A/1 | Completed
2025-02-01 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 72/1 | Completed
2025-02-01 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 65/10 | Completed
2025-02-01 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408 | 51/0 | Completed
2025-02-02 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408 | 1A/1 | Completed
2025-02-02 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 72/1 | Completed
2025-02-02 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 72/2 | Completed
2025-02-02 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 65/10 | Completed
2025-02-02 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408 | 51/0 | Completed
2025-02-03 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408 | 1A/1 | Completed
2025-02-03 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 72/2 | Completed
2025-02-03 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 65/10 | Completed
2025-02-03 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408 | 51/0 | Completed
2025-02-04 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408 | 1A/1 | Completed
2025-02-04 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 72/2 | Completed
2025-02-04 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 65/10 | Completed
2025-02-04 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408 | 51/0 | Completed
2025-02-05 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408 | 1A/1 | Completed
2025-02-05 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 72/2 | Completed
2025-02-05 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 65/10 | Completed
2025-02-05 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408 | 49/0 | Completed
2025-02-05 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408 | 51/0 | Completed
2025-02-06 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408 | 1A/1 | Completed
2025-02-06 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 72/2 | Completed
2025-02-06 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 65/10 | Completed
2025-02-06 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408 | 49/0 | Completed
2025-02-06 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408 | 51/0 | Completed
2025-02-07 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408 | 1A/1 | Completed
2025-02-07 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408 | 71/8 | Completed
2025-02-07 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408 | 49/0 | Completed
2025-02-07 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408 | 51/0 | Completed
2025-02-08 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408 | 1A/1 | Completed
2025-02-08 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408 | 71/8 | Completed
2025-02-08 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408 | 49/0 | Completed
2025-02-08 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408 | 52/0 | Completed
2025-02-09 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408 | 1A/1 | Completed
2025-02-09 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408 | 71/8 | Completed
2025-02-09 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408 | 49/0 | Completed
2025-02-09 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408 | 52/0 | Completed
2025-02-10 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408 | 1A/1 | Completed
2025-02-10 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408 | 71/8 | Completed
2025-02-10 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408 | 49/0 | Completed
2025-02-10 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408 | 52/0 | Completed
2025-02-11 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408 | 1A/2 | Completed
2025-02-11 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/7 | Completed
2025-02-11 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408 | 49/0 | Completed
2025-02-11 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408 | 52/0 | Completed
2025-02-12 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408 | 1A/2 | Completed
2025-02-12 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/7 | Completed
2025-02-12 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408 | 49/0 | Completed
2025-02-12 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408 | 52/0 | Completed
2025-02-13 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408 | 1A/2 | Completed
2025-02-13 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/7 | Completed
2025-02-13 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408 | 49/0 | Completed
2025-02-13 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408 | 52/0 | Completed
2025-02-14 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408 | 1A/2 | Completed
2025-02-14 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/7 | Completed
2025-02-14 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408 | 49/0 | Completed
2025-02-14 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408 | 52/0 | Completed
2025-02-15 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408 | 1A/2 | Completed
2025-02-15 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/7 | Completed
2025-02-15 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408 | 50/5 | Completed
2025-02-16 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408 | 1A/2 | Completed
2025-02-16 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408 | 71/6 | Completed
2025-02-16 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408 | 50/5 | Completed
2025-02-17 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408 | 1A/2 | Completed
2025-02-17 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408 | 71/6 | Completed
2025-02-17 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408 | 50/5 | Completed
2025-02-18 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408 | 1A/2 | Completed
2025-02-18 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408 | 71/6 | Completed
2025-02-18 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408 | 50/5 | Completed
2025-02-19 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408 | 1A/3 | Completed
2025-02-19 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408 | 71/6 | Completed
2025-02-19 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408 | 50/5 | Completed
2025-02-20 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408 | 1A/3 | Completed
2025-02-20 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/5 | Completed
2025-02-20 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408 | 50/5 | Completed
2025-02-21 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408 | 1A/3 | Completed
2025-02-21 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/5 | Completed
2025-02-22 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408 | 1A/3 | Completed
2025-02-22 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/5 | Completed
2025-02-23 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408 | 1A/3 | Completed
2025-02-23 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/5 | Completed
2025-02-24 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408 | 1A/3 | Completed
2025-02-24 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/5 | Completed
2025-02-25 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408 | 1A/3 | Completed
2025-02-25 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/4 | Completed
2025-02-26 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408 | 1A/3 | Completed
2025-02-26 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/4 | Completed
2025-02-26 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408 | 58/0 | Completed
2025-02-27 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408 | 1A/3 | Completed
2025-02-27 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/4 | Completed
2025-02-27 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408 | 58/0 | Completed
2025-02-28 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408 | 1A/3 | Completed
2025-02-28 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/4 | Completed
2025-02-28 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408 | 58/0 | Completed
2025-03-01 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/4 | Completed
2025-03-01 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408 | 53/5 | Completed
2025-03-01 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408 | 58/0 | Completed
2025-03-02 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408 | 71/3 | Completed
2025-03-02 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408 | 53/5 | Completed
2025-03-02 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408 | 58/0 | Completed
2025-03-03 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408 | 71/3 | Completed
2025-03-03 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408 | 53/5 | Completed
2025-03-03 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408 | 58/0 | Completed
2025-03-04 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408 | 71/3 | Completed
2025-03-04 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408 | 53/5 | Completed
2025-03-04 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408 | 58/0 | Completed
2025-03-05 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408 | 71/3 | Completed
2025-03-05 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408 | 53/5 | Completed
2025-03-05 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408 | 58/0 | Completed
2025-03-06 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408 | 71/3 | Completed
2025-03-06 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408 | 53/5 | Completed
2025-03-06 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408 | 58/0 | Completed
2025-03-07 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408 | 71/3 | Completed
2025-03-07 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408 | 53/5 | Completed
2025-03-07 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408 | 58/0 | Completed
2025-03-08 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/2 | Completed
2025-03-08 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408 | 58/0 | Completed
2025-03-08 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408 | 70/3 | Completed
2025-03-09 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/2 | Completed
2025-03-09 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408 | 53/4 | Completed
2025-03-09 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408 | 58/0 | Completed
2025-03-09 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408 | 70/3 | Completed
2025-03-10 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/2 | Completed
2025-03-10 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408 | 53/4 | Completed
2025-03-10 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408 | 58/0 | Completed
2025-03-10 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408 | 70/3 | Completed
2025-03-11 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/2 | Completed
2025-03-11 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408 | 53/4 | Completed
2025-03-11 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408 | 70/3 | Completed
2025-03-12 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/2 | Completed
2025-03-12 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408 | 53/4 | Completed
2025-03-12 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408 | 70/3 | Completed
2025-03-13 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 71/1 | Completed
2025-03-13 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408 | 53/4 | Completed
2025-03-13 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408 | 70/3 | Completed
2025-03-13 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-14 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 71/1 | Completed
2025-03-14 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408 | 53/4 | Completed
2025-03-14 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408 | 70/3 | Completed
2025-03-14 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-15 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 71/1 | Completed
2025-03-15 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408 | 53/4 | Completed
2025-03-15 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408 | 70/3 | Completed
2025-03-15 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-16 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 71/1 | Completed
2025-03-16 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408 | 53/4 | Completed
2025-03-16 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408 | 70/3 | Completed
2025-03-16 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-17 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 71/1 | Completed
2025-03-17 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408 | 53/4 | Completed
2025-03-17 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-18 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 71/1 | Completed
2025-03-18 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408 | 53/3 | Completed
2025-03-18 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-19 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408 | 71/0 | Completed
2025-03-19 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408 | 53/3 | Completed
2025-03-19 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-20 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408 | 71/0 | Completed
2025-03-20 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408 | 53/3 | Completed
2025-03-20 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408 | 70/5 | Completed
2025-03-20 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-21 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408 | 71/0 | Completed
2025-03-21 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408 | 53/3 | Completed
2025-03-21 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408 | 70/5 | Completed
2025-03-21 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-22 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408 | 71/0 | Completed
2025-03-22 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408 | 53/3 | Completed
2025-03-22 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408 | 70/5 | Completed
2025-03-22 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-23 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408 | 71/0 | Completed
2025-03-23 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408 | 53/3 | Completed
2025-03-23 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408 | 70/5 | Completed
2025-03-23 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-24 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408 | 71/0 | Completed
2025-03-24 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408 | 53/3 | Completed
2025-03-24 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408 | 70/5 | Completed
2025-03-24 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-25 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408 | 71/0 | Completed
2025-03-25 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408 | 53/3 | Completed
2025-03-25 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408 | 70/5 | Completed
2025-03-25 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-26 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 70/11 | Completed
2025-03-26 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408 | 53/2 | Completed
2025-03-26 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408 | 70/5 | Completed
2025-03-26 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-27 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 70/11 | Completed
2025-03-27 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408 | 53/2 | Completed
2025-03-27 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408 | 70/5 | Completed
2025-03-27 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-28 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 70/11 | Completed
2025-03-28 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408 | 53/2 | Completed
2025-03-28 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408 | 70/5 | Completed
2025-03-28 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-29 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 70/11 | Completed
2025-03-29 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408 | 53/2 | Completed
2025-03-29 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408 | 70/5 | Completed
2025-03-29 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-30 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 70/11 | Completed
2025-03-30 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408 | 53/2 | Completed
2025-03-30 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-03-31 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 70/11 | Completed
2025-03-31 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 70/10 | Completed
2025-03-31 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408 | 53/2 | Completed
2025-03-31 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TA408 | 47/9 | Completed
2025-03-31 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-04-01 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 70/10 | Completed
2025-04-01 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TA408 | 47/9 | Completed
2025-04-01 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-04-02 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 70/10 | Completed
2025-04-02 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408 | 53/1 | Completed
2025-04-02 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TA408 | 47/9 | Completed
2025-04-02 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-04-03 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 70/10 | Completed
2025-04-03 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408 | 53/1 | Completed
2025-04-03 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 47/8 | Completed
2025-04-03 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-04-04 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 70/10 | Completed
2025-04-04 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408 | 53/1 | Completed
2025-04-04 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 47/8 | Completed
2025-04-04 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-04-05 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408 | 53/1 | Completed
2025-04-05 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 47/8 | Completed
2025-04-05 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-04-06 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408 | 70/9 | Completed
2025-04-06 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408 | 53/1 | Completed
2025-04-06 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 47/8 | Completed
2025-04-06 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-04-07 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408 | 70/9 | Completed
2025-04-07 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408 | 53/1 | Completed
2025-04-07 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-04-08 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408 | 70/9 | Completed
2025-04-08 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408 | 53/1 | Completed
2025-04-08 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-04-09 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408 | 70/9 | Completed
2025-04-09 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408 | 53/1 | Completed
2025-04-09 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-04-10 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408 | 53/1 | Completed
2025-04-10 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-04-11 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408 | 53/1 | Completed
2025-04-11 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-04-12 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-12 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-04-13 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-13 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-04-14 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-14 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-04-15 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-16 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-17 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-18 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-19 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-20 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-21 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-22 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-23 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-24 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-25 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-26 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-27 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 70/4 | Completed
2025-04-27 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-28 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 70/4 | Completed
2025-04-28 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-29 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 70/4 | Completed
2025-04-30 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 70/4 | Completed
2025-05-01 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 70/4 | Completed
2025-05-02 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 70/4 | Completed
2024-07-10 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-11 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-12 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-13 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-14 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-15 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-16 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-17 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-18 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-18 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-19 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-19 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-20 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-21 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-22 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-23 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-24 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-25 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-26 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-27 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-27 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-28 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-28 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-29 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-30 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-31 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-01 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-02 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-02 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-03 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-03 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-04 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-05 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-06 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-07 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-08 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-09 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-09 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-10 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-11 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-12 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-13 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-14 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-16 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-17 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-18 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-19 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-20 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-21 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-22 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-22 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-23 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-23 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-24 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-24 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-25 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-26 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-27 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-28 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-29 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-29 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-29 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-08-30 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-30 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-08-31 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-31 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-01 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-01 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-02 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-02 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-03 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-03 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-04 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-04 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-05 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-05 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-06 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-06 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-07 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-08 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-09 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-09 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-10 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-10 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-11 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-11 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-12 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-12 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-13 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-14 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-14 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-14 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-15 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-15 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-15 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-16 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-16 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-16 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-17 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-17 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-17 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-18 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-18 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-18 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-19 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-19 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-19 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-19 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-20 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-20 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-20 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-21 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-21 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-21 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-22 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-22 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-23 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-23 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-24 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-24 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-25 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-25 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-26 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-26 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-26 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-27 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-27 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-27 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-28 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-28 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-28 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-29 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-09-29 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-29 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-30 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-09-30 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-30 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-01 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-01 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-10-01 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-01 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-01 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-02 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-02 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-10-02 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-02 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-02 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-03 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-03 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-10-03 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-03 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-03 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-03 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-04 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-04 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-04 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-04 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-05 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-05 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-05 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-05 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-05 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-05 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-06 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-06 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-06 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-06 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-06 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-06 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-07 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-07 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-07 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-07 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-07 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-07 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-08 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-08 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-08 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-08 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-08 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-09 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-09 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-09 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-09 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-09 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-10 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-10 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-10 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-10 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-10 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-11 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-11 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-11 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-11 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-11 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-12 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-12 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-12 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-12 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-12 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-13 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-13 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-13 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-13 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-13 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-14 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-14 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-14 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-14 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-14 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-15 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-15 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-15 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-16 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-16 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-16 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-16 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-16 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-17 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-17 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-17 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-17 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-17 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-17 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-18 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-18 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-18 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-18 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-18 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-18 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-19 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-19 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-19 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-19 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-19 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-19 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-19 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-20 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-20 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-20 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-20 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-20 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-20 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-21 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-21 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-21 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-21 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-21 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-21 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-21 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-22 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-22 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-22 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-22 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-22 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-22 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-23 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-23 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-23 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-23 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-23 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-23 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-24 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-24 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-24 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-24 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-24 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-24 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-25 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-25 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-25 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-25 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-25 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-25 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-26 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-26 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-26 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-26 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-26 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-26 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-27 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-27 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-27 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-27 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-27 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-27 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-28 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-28 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-28 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-28 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-29 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-29 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-29 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-29 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-30 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-30 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-30 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-30 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-31 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-31 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-31 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-11-01 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-11-01 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-01 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-01 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-11-02 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-02 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-02 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-02 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-03 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-03 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-03 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-03 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-04 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-04 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-04 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-04 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-05 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-05 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-05 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-05 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-05 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-06 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-06 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-06 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-06 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-06 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-07 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-07 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-07 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-07 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-07 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-07 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-08 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-08 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-08 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-08 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-09 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-09 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-09 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-09 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-09 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-10 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-10 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-10 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-10 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-10 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-11 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-11 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-11 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-11 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-11 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-12 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-12 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-12 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-12 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-12 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-12 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-13 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-13 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-13 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-13 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-13 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-13 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-14 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-14 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-14 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-14 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-14 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-14 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-15 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-15 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-15 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-15 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-15 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-16 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-16 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-16 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-16 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-16 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-17 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-17 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-17 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-17 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-17 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-18 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-18 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-18 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-18 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-18 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-19 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-19 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-19 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-19 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-19 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-20 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-20 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-20 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-20 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-20 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-21 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-21 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-21 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-21 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-21 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-22 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-22 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-22 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-22 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-22 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-23 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-23 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-23 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-23 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-23 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-24 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-24 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-24 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-24 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-24 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-24 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-25 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-25 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-25 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-25 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-25 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-26 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-26 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-26 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-26 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-26 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-27 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-27 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-27 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-27 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-28 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-28 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-28 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-28 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-29 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-29 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-29 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-29 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-30 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-30 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-30 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-30 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-12-01 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-01 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-12-02 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-02 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-02 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-12-03 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-03 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-03 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-03 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-03 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-04 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-04 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-04 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-04 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-04 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-05 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-05 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-05 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-05 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-05 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-06 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-06 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-06 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-06 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-07 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-07 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-07 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-08 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-08 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-08 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-09 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-09 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-09 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-10 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-10 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-10 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-11 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-11 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-11 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-11 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-12 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-12 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-12 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-12 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-13 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-13 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-13 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-13 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-14 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-14 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-14 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-15 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-15 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-15 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-15 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-16 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-16 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-16 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-16 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-17 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-17 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-17 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-17 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-18 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-18 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-18 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-18 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-19 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-19 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-19 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-19 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-20 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-20 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-20 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-20 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-21 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-21 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-21 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-21 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-22 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-22 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-22 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-22 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-23 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-23 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-23 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-23 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-24 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-24 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-24 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-24 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-25 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-25 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-25 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-25 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-26 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-26 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-26 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-26 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-27 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-27 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-27 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-27 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-27 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-28 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-28 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-28 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-28 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-28 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-28 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2024-12-29 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-29 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-29 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-29 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2024-12-30 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-30 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-30 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-30 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2024-12-31 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-31 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-31 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-31 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-01 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-01 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2025-01-01 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-02 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-02 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-02 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2025-01-02 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-03 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-03 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-03 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2025-01-03 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-03 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-04 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-04 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-04 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-04 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-04 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-05 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-05 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-05 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-05 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-05 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-06 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-06 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-06 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-06 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-06 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-07 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-07 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-07 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-07 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-08 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-08 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-08 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-08 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-09 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-09 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-09 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-10 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-10 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-10 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-11 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-11 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-11 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-12 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-12 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-12 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-13 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-13 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-13 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-14 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-14 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-14 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-15 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-15 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-15 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-16 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-16 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-16 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-17 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-17 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-17 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-18 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-18 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-18 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-18 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-19 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-19 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-19 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-19 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-20 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-20 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-20 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-21 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-21 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-21 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-22 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-22 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-22 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-22 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-22 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-23 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-23 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-23 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-23 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-23 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-24 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-24 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-24 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-24 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-25 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-25 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-25 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-25 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-26 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-26 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-26 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-26 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-27 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-27 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-27 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-27 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-28 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-28 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-28 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-28 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-29 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-29 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-29 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-30 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-30 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-30 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-01-30 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-30 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-01-31 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-31 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-01-31 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-01 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-02-01 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-01 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-02 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-02-02 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-02 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-03 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-02-03 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-03 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-04 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-04 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-04 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-05 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-05 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-05 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-06 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-06 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-06 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-07 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-07 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-07 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-08 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-08 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-08 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-09 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-09 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-09 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-10 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-10 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-10 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-10 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-11 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-11 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-11 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-11 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-12 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-12 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-12 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-12 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-13 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-13 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-13 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-13 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-14 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-14 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-14 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-14 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-15 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-15 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-15 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-15 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-16 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-16 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-16 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-16 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-17 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-17 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-17 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-17 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-18 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-18 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-18 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-18 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-19 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-19 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-19 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-19 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-19 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-20 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-20 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-20 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-20 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-21 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-21 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-21 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-21 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-22 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-22 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-22 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-22 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-23 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-23 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-23 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-23 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-24 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-24 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-24 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-24 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-25 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-25 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-25 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-25 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-26 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-02-26 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-26 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-26 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-27 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-02-27 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-27 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-27 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-28 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-02-28 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-28 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-28 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-03-01 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-03-01 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-01 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-03-01 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-03-01 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-03-02 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-03-02 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-02 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-02 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-03-03 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-03 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-03 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-03 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-03 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-04 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-04 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-04 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-04 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-04 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-05 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-05 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-05 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-05 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-05 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-06 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-06 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-06 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-06 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-06 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-07 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-07 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-07 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-07 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-07 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-08 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-08 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-08 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-08 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-08 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-09 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-09 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-09 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-09 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-09 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-10 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-10 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-10 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-10 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-10 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-11 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-11 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-11 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-11 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-11 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-12 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-12 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-12 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-12 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-12 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-13 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-13 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-13 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-13 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-13 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-14 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-14 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-14 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-14 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-15 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-15 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-15 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-15 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-15 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-16 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-16 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-16 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-16 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-16 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-16 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-17 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-17 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-17 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-17 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-17 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-17 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-18 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-18 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-18 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-18 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-18 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-19 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-19 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-19 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-19 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-19 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-20 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-20 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-20 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-20 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-20 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-21 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-21 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-21 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-21 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-21 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-22 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-22 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-22 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-22 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-22 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-23 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-23 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-23 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-23 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-23 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-23 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-24 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-24 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-24 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-24 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-24 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-25 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-25 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-25 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-25 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-25 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-26 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-26 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-26 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-26 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-26 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-27 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-27 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-27 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-27 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-27 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-28 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-28 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-28 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-28 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-28 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-29 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-29 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-29 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-29 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-29 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-29 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-29 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-03-30 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-30 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-30 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-03-30 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-30 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-30 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-03-31 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-31 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-03-31 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-31 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-31 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-04-01 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-01 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-01 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-04-01 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-01 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-04-02 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-02 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-02 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-02 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-02 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-04-03 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-03 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-03 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-03 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-03 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-04 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-04 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-04 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-04 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-04 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-05 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-05 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-05 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-05 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-05 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-06 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-06 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-06 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-06 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-06 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-07 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-07 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-07 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-07 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-07 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-08 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-08 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-08 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-08 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-08 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-09 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-09 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-09 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-09 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-09 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-10 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-10 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-10 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-10 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-10 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-11 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-11 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-11 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-11 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-11 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-12 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-12 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-12 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-12 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-12 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-13 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-13 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-13 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-13 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-13 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-14 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-14 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-14 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-14 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-14 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-15 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-15 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-15 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-15 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-15 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-16 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-16 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-16 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-16 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-16 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-17 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-17 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-17 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-17 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-17 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-18 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-18 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-18 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-18 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-18 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-19 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-19 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-19 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-19 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-19 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-19 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-20 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-20 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-20 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-20 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-20 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-21 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-21 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-21 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-21 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-21 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-22 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-22 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-22 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-22 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-22 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-23 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-23 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-23 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-23 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-23 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-24 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-24 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-24 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-24 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-24 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-25 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-25 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-25 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-25 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-25 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-26 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-26 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-26 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-26 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-26 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-27 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-27 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-27 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-27 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-27 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-28 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-28 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-28 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-28 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-04-29 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-29 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-04-29 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-29 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-04-30 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-30 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-04-30 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-30 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-05-01 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-05-01 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-01 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-02 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-02 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-05-02 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-02 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-03 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-03 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-03 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-03 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-04 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-04 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-04 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-04 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-05 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-05 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-05 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-05 | 2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421 | 11/1 | Completed
2025-05-06 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-06 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-06 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-06 | 2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421 | 11/1 | Completed
2025-05-07 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-07 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-07 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-07 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-08 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-08 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-08 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-08 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-08 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-09 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-09 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-09 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-09 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-10 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-10 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-10 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-10 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-10 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-10 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-11 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-11 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-11 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-11 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-11 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-11 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-12 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-12 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-12 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-12 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-12 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-12 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-13 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-13 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-13 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-13 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-13 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-13 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-14 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-14 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-14 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-14 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-14 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-14 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-15 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-15 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-15 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-15 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-15 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-15 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-16 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-16 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-16 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-16 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-16 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-16 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-17 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-17 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-17 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-17 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-17 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-18 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-18 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-18 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-18 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-18 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-19 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-19 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-19 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-19 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-19 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-20 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-20 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-20 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-20 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-20 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-21 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-21 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-21 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-21 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-21 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-22 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-22 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-22 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-22 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-22 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-23 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-23 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-23 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-23 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-24 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-24 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-24 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-24 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-25 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-25 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-25 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-26 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-26 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-26 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-27 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-27 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-27 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-28 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-28 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-28 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-29 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-29 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-29 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-05-30 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-30 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-30 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-05-31 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-31 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-31 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-06-01 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-01 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-01 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-06-02 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-02 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-02 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-06-03 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-03 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-03 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-04 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-04 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-04 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-05 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-05 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-05 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-05 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-06 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-06 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-06 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-06 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-06 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-07 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-07 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-07 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-07 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-08 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-08 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-08 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-08 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-09 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-09 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-09 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-09 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-10 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-10 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-10 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-10 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-11 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-11 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-11 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-11 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-12 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-12 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-12 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-13 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-13 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-13 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-14 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-14 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-14 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-15 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-15 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-15 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-16 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-16 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-16 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-17 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-17 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-17 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-18 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-18 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-18 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-19 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-19 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-19 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-20 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-20 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-20 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-21 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-21 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-21 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-22 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-22 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-22 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-23 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-23 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-23 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-24 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-24 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-24 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-24 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-24 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-25 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-25 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-25 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-25 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-25 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-25 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-26 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-26 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-26 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-26 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-26 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-27 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-27 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-27 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-27 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-27 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-28 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-28 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-28 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-28 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-28 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-29 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-29 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-29 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-29 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-29 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-06-30 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-30 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-30 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-30 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-30 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-07-01 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-01 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-01 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-01 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-01 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-07-02 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-02 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-02 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-02 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-02 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-07-03 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-03 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-03 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-03 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-03 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-04 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-04 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-04 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-04 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-04 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-04 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-05 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-05 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-05 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-05 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-05 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-06 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-06 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-06 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-06 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-06 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-07 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-07 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-07 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-07 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-07 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-08 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-08 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-08 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-08 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-09 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-09 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-09 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-09 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-10 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-10 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-10 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-10 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-11 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-11 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-11 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-11 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-12 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-12 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-12 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-12 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-12 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-13 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-13 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-13 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-13 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-13 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-13 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-14 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-14 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-14 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-14 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-14 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-14 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-14 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-15 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-15 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-15 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-15 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-15 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-15 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-15 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-15 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-16 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-16 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-16 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-16 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-16 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-16 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-16 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-17 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-17 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-17 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-17 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-17 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-17 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-17 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-18 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-18 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-18 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-18 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-18 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-18 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-18 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-19 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-19 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-19 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-19 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-19 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-19 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-19 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-20 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-20 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-20 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-20 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-20 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-20 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-20 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-21 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-21 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-21 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-21 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-21 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-21 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-21 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-22 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-22 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-22 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-22 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-22 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-22 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-22 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-23 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-23 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-23 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-23 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-23 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-23 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-23 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-24 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-24 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-24 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-24 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-24 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-24 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-24 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-25 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-25 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-25 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-25 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-25 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-25 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-25 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-26 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-26 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-26 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-26 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-26 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-26 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-26 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-27 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-27 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-27 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-27 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-27 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-27 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-27 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-28 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-28 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-28 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-28 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-28 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-28 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-28 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-29 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-29 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-29 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-29 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-29 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-29 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-29 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-30 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-07-30 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-30 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-30 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-30 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-07-30 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-30 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-31 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-07-31 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-31 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-31 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-07-31 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-31 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-08-01 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-01 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-01 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-08-01 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-08-01 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-08-01 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-02 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-02 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-02 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-08-02 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-08-02 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-08-02 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-03 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-03 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-03 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-08-03 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-03 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-04 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-04 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-04 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-08-04 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-04 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-05 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-05 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-05 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-05 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-05 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-06 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-06 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-06 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-06 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-06 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-07 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-07 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-07 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-07 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-07 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-08 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-08 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-08 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-08 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-08 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-08 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-09 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-09 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-09 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-09 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-09 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-09 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-10 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-10 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-10 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-10 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-10 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-10 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-11 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-11 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-11 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-11 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-11 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-11 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-12 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-12 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-12 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-12 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-12 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-12 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-13 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-13 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-13 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-13 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-13 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-13 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-14 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-14 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-14 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-14 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-14 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-14 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-15 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-15 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-15 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-15 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-15 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-16 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-16 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-16 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-16 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-16 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-16 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-17 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-17 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-17 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-17 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-17 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-17 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-18 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-18 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-18 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-18 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-18 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-18 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-19 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-19 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-19 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-19 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-19 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-19 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-20 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-20 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-20 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-20 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-20 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-20 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-21 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-21 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-21 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-21 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-21 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-21 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-22 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-22 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-22 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-22 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-22 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-22 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-23 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-23 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-23 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-23 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-23 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-23 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-23 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-24 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-24 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-24 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-24 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-24 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-24 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-24 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-25 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-25 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-25 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-25 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-25 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-25 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-25 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-26 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-26 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-26 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-26 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-26 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-26 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-26 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-27 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-27 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-27 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-27 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-27 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-27 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-27 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-28 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-28 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-28 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-28 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-28 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-28 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-28 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-29 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-29 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-29 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-29 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-29 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-29 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-29 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-30 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-30 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-08-30 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-30 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-30 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-30 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-31 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-31 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-08-31 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-08-31 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-31 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-08-31 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-09-01 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-01 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-01 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-01 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-01 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-01 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-02 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-02 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-02 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-02 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-02 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-02 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-03 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-03 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-03 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-03 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-03 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-03 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-04 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-04 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-04 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-04 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-04 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-05 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-05 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-05 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-05 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-05 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-05 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-06 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-06 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-06 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-06 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-06 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-06 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-07 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-07 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-07 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-07 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-07 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-07 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-08 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-08 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-08 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-08 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-08 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-08 | 2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421 | 4/7 | Completed
2025-09-09 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-09 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-09 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-09 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-09 | 2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421 | 4/7 | Completed
2025-09-10 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-10 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-10 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-10 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-10 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-11 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-11 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-11 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-11 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-12 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-12 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-12 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-12 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-13 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-13 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-13 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-13 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-13 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-14 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-14 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-14 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-14 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-14 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-15 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-15 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-15 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-15 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-16 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-16 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-16 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-16 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-17 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-17 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-17 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-18 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-18 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-18 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-19 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-19 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-19 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-20 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-20 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-20 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-21 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-21 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-21 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-21 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-22 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-22 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-22 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-22 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-23 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-23 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-23 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-23 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-24 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-24 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-24 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-24 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-25 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-25 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-25 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-25 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-26 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-26 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-26 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-27 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-27 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-27 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-28 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-28 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-28 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-29 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-29 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-29 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-30 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-30 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed

## RawData
Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name | Location No. | Status
2024-10-09 | 2024-10-27 | Gang 01 Sanjay | 27.96 | 1.4716 | TA418 | 34/1 | COMPLETED
2024-10-28 | 2024-11-05 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 33/12 | COMPLETED
2024-11-05 | 2024-11-13 | Gang 01 Sanjay | 27.96 | 3.1067 | TA418 | 35/06 | COMPLETED
2024-11-14 | 2024-11-19 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 34/3 | COMPLETED
2024-11-19 | 2024-11-24 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 35/4 | COMPLETED
2024-11-26 | 2024-12-01 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 40/1 | COMPLETED
2024-12-02 | 2024-12-06 | Gang 01 Sanjay | 27.96 | 5.592 | TA418 | 40/2 | COMPLETED
2024-12-03 | 2024-12-11 | Gang 02 Sanjay | 27.96 | 3.1067 | TA418 | 42/2 | COMPLETED
2024-12-06 | 2024-12-11 | Gang 01 Sanjay | 27.96 | 4.66 | TA418 | 41/3 | COMPLETED
2024-12-12 | 2024-12-18 | Gang 01 Sanjay | 29.12 | 4.16 | TA418 | 41/4 | COMPLETED
2024-12-12 | 2024-12-18 | Gang 02 Sanjay | 27.96 | 3.9943 | TA418 | 42/1 | COMPLETED
2024-12-19 | 2024-12-27 | Gang 01 Sanjay | 29.12 | 3.2356 | TA418 | 35/11 | COMPLETED
2024-12-19 | 2024-12-29 | Gang 02 Sanjay | 34.63 | 3.1482 | TA418 | 35/7 | COMPLETED
2024-12-29 | 2024-01-05 | Gang 01 Sanjay | 27.96 |  | TA418 | 33/10 | COMPLETED
2024-12-30 | 2024-01-07 | Gang 02 Sanjay | 27.96 |  | TA418 | 40/4 | COMPLETED
2024-01-07 | 2025-01-11 | Gang 01 Sanjay | 27.96 | 0.075364 | TA418 | 46/14 | COMPLETED
2024-01-09 | 2025-01-15 | Gang 02 Sanjay | 27.96 | 0.07496 | TA418 | 54/4 | COMPLETED
2025-01-13 | 2025-01-18 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 46/8 | COMPLETED
2025-01-16 | 2025-01-23 | Gang 02 Sanjay | 29 | 3.625 | TA418 | 55/1 | COMPLETED
2025-01-16 | 2025-01-23 | Gang 01 Sanjay | 28 | 3.5 | TA418 | 46/4 | COMPLETED
2025-01-24 | 2025-02-11 | Gang 02 Sanjay | 29 | 1.5263 | TA418 | 55/3 | COMPLETED
2025-01-24 | 2025-01-30 | Gang 01 Sanjay | 28 | 4 | TA418 | 34/2 | COMPLETED
2025-01-25 | 2025-02-02 | Gang 02 Sanjay | 28 | 3.1111 | TA418 | 55/2 | COMPLETED
2025-01-31 | 2025-02-05 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 35/8 | COMPLETED
2025-02-06 | 2025-02-11 | Gang 01 Sanjay | 33 | 5.5 | TA418 | 41/1 | COMPLETED
2025-02-12 | 2025-02-17 | Gang 01 Sanjay | 29 | 4.8333 | TA418 | 41/2 | COMPLETED
2025-02-12 | 2025-02-20 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 54/3 | COMPLETED
2025-02-21 | 2025-02-26 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 41/0 | COMPLETED
2025-02-26 | 2025-03-03 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 43/0 | COMPLETED
2025-03-03 | 2025-03-08 | Gang 01 Sanjay | 45 | 7.5 | TA418 | 46/0 | COMPLETED
2025-03-06 | 2025-03-11 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/9 | COMPLETED
2025-03-12 | 2025-03-17 | Gang 02 Sanjay | 45 | 7.5 | TA418 | 46/7 | COMPLETED
2025-03-18 | 2025-03-23 | Gang 02 Sanjay | 54 | 9 | TA418 | 45/0 | COMPLETED
2025-03-18 | 2025-03-28 | Gang 02 Sanjay | 52 | 4.7273 | TA418 | 45/1 | COMPLETED
2025-03-28 | 2025-04-01 | Gang 02 Sanjay | 28 | 5.6 | TA418 | 45/2 | COMPLETED
2025-04-02 | 2025-04-05 | Gang 02 Sanjay | 29 | 7.25 | TA418 | 40/3 | COMPLETED
2025-04-05 | 2025-04-10 | Gang 02 Sanjay | 47 | 7.8333 | TA418 | 42/0 | COMPLETED
2025-04-11 | 2025-04-21 | Gang 01 Sanjay | 54 | 4.9091 | TA418 | 33/5 | COMPLETED
2025-04-12 | 2025-04-18 | Gang 02 Sanjay | 29 | 4.1429 | TA418 | 55/4 | COMPLETED
2025-04-18 | 2025-04-26 | Gang 02 Sanjay | 45 | 5 | TA418 | 55/0 | COMPLETED
2025-04-22 | 2025-04-29 | Gang 01 Sanjay | 45 | 5.625 | TA418 | 34/0 | COMPLETED
2025-04-27 | 2025-05-03 | Gang 02 Sanjay | 34.63 | 4.9471 | TA418 | 46/15 | COMPLETED
2025-04-29 | 2025-05-07 | Gang 01 Sanjay | 29 | 3.2222 | TA418 | 37/1 | COMPLETED
2025-05-05 | 2025-05-10 | Gang 02 Sanjay | 28 | 4.6667 | TA418 | 46/2 | COMPLETED
2025-05-08 | 2025-05-17 | Gang 02 Sanjay | 45 | 4.5 | TA418 | 35/0 | COMPLETED
2025-05-11 | 2025-05-19 | Gang 01 Sanjay | 33 | 3.6667 | TA418 | 46/5 | COMPLETED
2025-05-11 | 2025-05-26 | Gang 02 Sanjay | 27 | 1.6875 | TA418 | 33/11 | COMPLETED
2025-05-22 | 2025-05-28 | Gang 01 Sanjay | 29 | 4.1429 | TA418 | 34/4 | COMPLETED
2025-05-30 | 2025-06-04 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 35/3 | COMPLETED
2025-05-29 | 2025-06-02 | Gang 01 Sanjay | 27 | 5.4 | TA418 | 40/5 | COMPLETED
2025-06-03 | 2025-06-08 | Gang 02 Sanjay | 27 | 4.5 | TA418 | 33/7 | COMPLETED
2025-06-09 | 2025-06-12 | Gang 02 Sanjay | 27 | 6.75 | TA418 | 33/8 | COMPLETED
2025-06-12 | 2025-06-17 | Gang 01 Sanjay | 27 | 4.5 | TA418 | 33/9 | COMPLETED
2025-06-14 | 2025-06-24 | Gang 02 Sanjay | 56 | 5.0909 | TA418 | 33/6 | COMPLETED
2025-06-19 | 2025-07-01 | Gang 01 Sanjay | 47 | 3.6154 | TA418 | 36/0 | COMPLETED
2025-07-03 | 2025-07-12 | Kec 01 Barkat Ali | 28 | 2.8 | TA418 | 38/2 | COMPLETED
2025-07-03 | 2025-07-21 | Gang 02 Sanjay | 54 | 2.8421 | TA418 | 40/0 | COMPLETED
2025-07-03 | 2025-07-14 | Kec 02 Barkat Ali | 47 | 3.9167 | TA418 | 37/0 | COMPLETED
2025-07-14 | 2025-07-20 | Kec 01 Barkat Ali | 28 | 4 | TA418 | 37/2 | COMPLETED
2025-07-15 | 2025-07-23 | Kec 02 Barkat Ali | 34.6 | 3.8444 | TA418 | 38/1 | COMPLETED
2025-07-21 | 2025-07-31 | Kec 02 Barkat Ali | 34.6 | 3.1455 | TA418 | 35/9 | COMPLETED
2025-07-22 | 2025-07-30 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 35/5 | COMPLETED
2025-07-21 | 2025-08-07 | Savitha | 29 | 1.6111 | TA418 | 35/1 | COMPLETED
2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | 41/5 | COMPLETED
2025-06-29 | 2025-08-07 | Kec 01 Barkat Ali | 29 | 0.725 | TA418 | 35/2 | COMPLETED
2025-08-06 | 2025-08-19 | Kec 02 Barkat Ali | 54 | 3.8571 | TA418 | 36/1 | COMPLETED
2025-08-07 | 2025-08-17 | Kec 01 Barkat Ali | 34.63 | 3.1482 | TA418 | 35/10 | COMPLETED
2025-08-07 | 2025-08-16 | Subhash | 51.6 | 5.16 | TA418 | 48A/0 | COMPLETED
2025-08-09 | 2025-08-22 | Savitha | 28 | 2 | TA418 | 46/13 | COMPLETED
2025-08-16 | 2025-09-01 | Subhash | 33 | 1.9412 | TA418 | 48/1 | COMPLETED
2025-08-18 | 2025-08-26 | Kec 01 Barkat Ali | 28 | 3.1111 | TA418 | 43/1 | COMPLETED
2025-08-19 | 2025-08-26 | Subhash | 51.6 | 6.45 | TA418 | 52/0 | COMPLETED
2025-08-22 | 2025-08-26 | Kec 02 Barkat Ali | 28 | 5.6 | TA418 | 46/3 | COMPLETED
2025-08-26 |  | Savitha | 28 |  | TA418 | 60/2 | 1st section completed- material and T&P stucked at location.ROW
2025-08-31 | 2025-09-10 | Kec 01 Barkat Ali | 35 | 3.1818 | TA418 | 33/3 | COMPLETED
2025-09-01 | 2025-09-12 | Kec 02 Barkat Ali | 63 | 5.25 | TA418 | 62/0 | COMPLETED
2025-09-03 | 2025-09-07 | Subhash | 27.9 | 5.58 | TA418 | 46/12 | COMPLETED
2025-09-05 |  | Savitha | 45 |  | TA418 | 56/0 | top CrossArm section work under progress.
2025-09-08 |  | Subhash | 33 |  | TA418 | 46/11 | (ROW)
2025-09-09 | 2025-09-13 | Subhash | 29 | 5.8 | TA418 | 48/2 | COMPLETED
2025-09-09 |  | M S Mdpl | 33.3 |  | TA418 | 45/3 | Middle Crossarm section work under progress.
2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | TA418 | 33/2 | COMPLETED
2025-09-14 | 2025-09-25 | Kec 02 Barkat Ali | 51.7 | 4.3083 | TA418 | 61/0 | COMPLETED
2025-09-16 | 2025-09-23 | Subhash | 60 | 7.5 | TA418 | 53/0 | COMPLETED
2025-09-22 |  | M S Tofit | 27 |  | TA418 | 33/1 | Bottom crossarm work under progress.
2025-09-25 |  | Subhash | 50 |  | TA418 | 44/0 | Middle section work under progress
2025-09-28 |  | Kec 02 Barkat Ali | 27 |  | TA418 | 54/1 | 1st section work under progress.
2025-09-29 |  | M S Mdpl | 60 |  | TA418 | 54/0 | Material shifting work under progress.
2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | COMPLETED
2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | COMPLETED
2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | COMPLETED
2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | COMPLETED
2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | COMPLETED
2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | COMPLETED
2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | COMPLETED
2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | COMPLETED
2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | COMPLETED
2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | COMPLETED
2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | COMPLETED
2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | COMPLETED
2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | COMPLETED
2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | COMPLETED
2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | COMPLETED
2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | COMPLETED
2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | COMPLETED
2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | COMPLETED
2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | COMPLETED
2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | COMPLETED
2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | COMPLETED
2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | COMPLETED
2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | COMPLETED
2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | COMPLETED
2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | COMPLETED
2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | COMPLETED
2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | COMPLETED
2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | COMPLETED
2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | COMPLETED
2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | COMPLETED
2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | COMPLETED
2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | COMPLETED
2024-09-01 | 2024-09-16 | Dewi Construction | 43.7758 | 2.736 | TA416 | 2/8 | Completed
2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | Completed
2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | Completed
2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | Completed
2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | Completed
2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | Completed
2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | Completed
2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | Completed
2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | Completed
2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | Completed
2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | Completed
2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | Completed
2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | Completed
2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | Completed
2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | Completed
2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | Completed
2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | Completed
2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | Completed
2024-11-14 | 2024-11-25 | Pinky Dewi | 46.0492 | 3.8374 | TA416 | 6/2 | Completed
2024-11-10 | 2024-11-25 | Horil Mahto | 46.0492 | 2.8781 | TA416 | 38/3 | Completed
2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | Completed
2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | Completed
2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | Completed
2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | Completed
2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | Completed
2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | Completed
2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | Completed
2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | Completed
2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | Completed
2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | Completed
2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | Completed
2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | Completed
2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | Completed
2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | Completed
2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | Completed
2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | Completed
2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | Completed
2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | Completed
2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | Completed
2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | Completed
2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | Completed
2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | Completed
2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | Completed
2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | Completed
2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | Completed
2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | Completed
2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | Completed
2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | Completed
2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | Completed
2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | Completed
2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | Completed
2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | Completed
2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | Completed
2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | Completed
2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | Completed
2025-01-08 | 2025-01-15 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/8 | Completed
2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | Completed
2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | Completed
2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | Completed
2025-01-10 | 2025-01-17 | Dewi Construction | 43.7758 | 5.472 | TA416 | 17/3 | Completed
2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | Completed
2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | Completed
2025-01-16 | 2025-01-22 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/7 | Completed
2025-01-18 | 2025-01-23 | Dewi Construction | 43.7758 | 7.296 | TA416 | 17/2 | Completed
2025-01-16 | 2025-01-24 | Amar Singh | 43.7758 | 4.864 | TA416 | 36/5 | Completed
2025-01-10 | 2025-01-31 | Rudra Construction | 46.0492 | 2.0931 | TA416 | 33/10 | Completed
2025-01-18 | 2025-01-27 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 19/9 | Completed
2025-01-18 | 2025-01-28 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 35/1 | Completed
2025-10-20 | 2025-01-25 | Asc Heights | 46.0492 |  | TA416 | 31/6 | Completed
2025-01-22 | 2025-01-25 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 12/4 | Completed
2025-01-23 | 2025-01-30 | Pankaj | 43.7758 | 5.472 | TA416 | 7/6 | Completed
2025-01-24 | 2025-01-29 | Dewi Construction | 46.0492 | 7.6749 | TA416 | 17/5 | Completed
2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | Completed
2025-01-26 | 2025-02-02 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/1 | Completed
2025-01-26 | 2025-02-01 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/5 | Completed
2025-01-30 | 2025-02-05 | Dewi Construction | 46.0492 | 6.5785 | TA416 | 17/7 | Completed
2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | Completed
2025-01-28 | 2025-02-06 | Reeta Bharti | 64.482 | 6.4482 | TA416 | 20/0 | Completed
2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | Completed
2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | Completed
2025-01-29 | 2025-02-10 | Horil Mahto | 73.426 | 5.6482 | TA416 | 35/0 | Completed
2025-01-31 | 2025-02-10 | Pankaj | 46.0492 | 4.1863 | TA416 | 7/5 | Completed
2025-02-02 |  | Rudra Construction | 46.0492 |  | TA416 | 33/11 | Completed
2025-02-06 |  | Dewi Construction | 64.482 |  | TA416 | 21/0 | Completed
2025-02-07 |  | Reeta Bharti | 43.7758 |  | TA416 | 20/2 | Completed
2025-02-08 |  | Amar Singh | 46.0492 |  | TA416 | 35/9 | Completed
2025-02-09 | 2025-02-15 | Pinky Dewi | 46.049 | 6.5784 | TA416 | 8/1 | Completed
2025-02-11 | 2025-02-18 | Pankaj | 43.7758 | 5.472 | TA416 | 7/4 | Completed
2025-02-11 | 2025-11-20 | Horil Mahto | 46.049 | 0.16272 | TA416 | 34/7 | Completed
2025-02-11 | 2025-11-20 | Asc Heights | 46.049 | 0.16272 | TA416 | 31/9 | Completed
2025-02-16 | 2025-02-21 | Amar Singh | 46.049 | 7.6748 | TA416 | 35/7 | Completed
2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | Completed
2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | Completed
2025-02-14 | 2025-02-20 | Dewi Construction | 46.049 | 6.5784 | TA416 | 33/6 | Completed
2025-02-14 | 2025-02-23 | Rudra Construction | 43.7758 | 4.3776 | TA416 | 33/9 | Completed
2025-02-20 | 2025-02-25 | Reeta Bharti | 42.375 | 7.0625 | TA416 | 20/4 | Completed
2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | Completed
2025-02-21 | 2025-02-25 | Dewi Construction | 46.049 | 9.2098 | TA416 | 33/7 | Completed
|  | Reeta Bharti |  |  | TA416 | 4/10 | Completed
|  | Dewi Construction |  |  | TA416 | 33/3 | Completed
|  | Pankaj |  |  | TA416 | 7/0 | Completed
|  | Pinky Dewi |  |  | TA416 | 8/0 | Completed
2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | Completed
2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | Completed
2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | Completed
2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | Completed
2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | Completed
2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | Completed
2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | Completed
2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | Completed
2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | Completed
2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | Completed
2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | Completed
2025-02-27 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.2988 | TA416 | 5/0 | Completed
2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | Completed
2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | Completed
2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | Completed
2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | Completed
2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | Completed
2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | Completed
2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | Completed
2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | Completed
2025-03-23 | 2025-03-26 | Pinky Dewi | 42.375 | 10.5938 | TA416 | 8B/1 | Completed
2025-03-22 | 2025-03-29 | Reeta Bharti | 64.482 | 8.0602 | TA416 | 6/0 | Completed
2025-03-20 | 2025-03-27 | Pankaj | 42.375 | 5.2969 | TA416 | 7/3 | Completed
2025-03-20 | 2025-03-30 | Horil Mahto | 42.375 | 3.8523 | TA416 | 35/2 | Completed
2025-03-24 | 2025-03-30 | Asc Heights | 42.375 | 6.0536 | TA416 | 31/10 | Completed
2025-03-23 | 2025-03-31 | Amar Singh | 42.375 | 4.7083 | TA416 | 35/8 | Completed
2025-03-22 | 2025-03-31 | Mk Infra | 46.0492 | 4.6049 | TA416 | 38/8 | Completed
2025-03-24 | 2025-03-31 | Ananya Traders | 46.0492 | 5.7561 | TA416 | 39/3 | Completed
2025-03-23 | 2025-03-31 | Pinky Dewi | 53.324 | 5.9249 | TA416 | 8B/5 | Completed
2025-03-24 | 2025-03-31 | Dewi Construction | 64.482 | 8.0602 | TA416 | 34/0 | Completed
2025-04-01 | 2025-04-11 | Gagan 2 | 75.8584 | 6.8962 | TA416 | 9/0 | Completed
2025-03-31 | 2025-04-11 | Anand Const | 46.0492 | 3.8374 | TA416 | 4/1 | Completed
2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | Completed
2025-03-31 | 2025-04-08 | Gagan | 42.375 | 4.7083 | TA416 | 20/11 | Completed
2025-04-01 | 2025-04-11 | Asc Heights |  |  | TA416 | 32/0 | Completed
2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | Completed
2025-04-01 | 2025-04-11 | Mk Infra | 46.0492 | 4.1863 | TA416 | 38/6 | Completed
2025-04-03 | 2025-04-10 | Dewi Construction | 42.375 | 5.2969 | TA416 | 34/4 | Completed
2025-04-08 | 2025-04-12 | Pinky Dewi 1 | 42.3742 | 8.4748 | TA416 | 8B/2 | Completed
2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | Completed
2025-04-01 | 2025-04-11 | Ananya Traders 1 | 46.0492 | 4.1863 | TA416 | 39/1 | Completed
2025-04-09 | 2025-04-14 | Gagan Enterprise 1 | 46.0492 | 7.6749 | TA416 | 20/10 | Completed
2025-04-01 | 2025-04-14 | Amar Singh | 64.4817 | 4.6058 | TA416 | 36/0 | Completed
2025-04-03 | 2025-04-17 | Ananya Traders 2 | 46.0492 | 3.0699 | TA416 | 52/6 | Completed
2025-04-12 | 2025-04-17 | Gagan 2 | 42.3742 | 7.0624 | TA416 | 10/1 | Completed
2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | Completed
2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | Completed
2025-04-12 | 2025-04-21 | Pinky Dewi | 42.3742 | 4.2374 | TA416 | 8B/4 | Completed
2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | Completed
2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | Completed
2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | Completed
2025-02-12 18:37 | 2025-04-22 | Amar Singh | 43.7758 | 0.63443 | TA416 | 36/6 | Completed
2025-04-12 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 4.8476 | TA416 | 20/1 | Completed
2025-04-12 | 2025-04-23 | Rudra Construction | 43.7758 | 3.648 | TA416 | 25/2 | Completed
2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | Completed
2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | Completed
2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | Completed
2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | Completed
2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | Completed
2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | Completed
2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | Completed
2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | Completed
2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | Completed
2025-04-23 | 2025-04-29 | M K Infra | 42.3742 | 6.0535 | TA416 | 38/9 | Completed
2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | Completed
2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | Completed
2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | Completed
2025-04-27 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/4 | Completed
2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | Completed
2025-05-02 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/3 | Completed
2025-05-01 | 2025-05-06 | Asc Heights | 43.7758 | 7.296 | TA416 | 30/3 | Completed
2025-05-02 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 9.2098 | TA416 | 19/10 | Completed
2025-04-27 | 2025-05-07 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 25/3 | Completed
2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | Completed
2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | Completed
2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | Completed
2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | Completed
2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | Completed
2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | Completed
2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | Completed
2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | Completed
2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | Completed
2025-05-13 | 2025-05-15 | Ananya Traders 2 | 42.3742 | 14.1247 | TA416 | 52/9 | Completed
2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | Completed
2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | Completed
2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | Completed
2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | Completed
2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | Completed
2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | Completed
2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | Completed
2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | Completed
2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | Completed
2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | Completed
2025-05-13 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 3.5312 | TA416 | 38/10 | Completed
2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | Completed
2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | Completed
2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.073 | 7.8073 | TA416 | 15/0 | Completed
2025-05-10 | 2025-05-25 | Rudra Construction | 42.3742 | 2.6484 | TA416 | 23/5 | Completed
2025-05-22 | 2025-05-30 | Reeta Bharti | 42.3742 | 4.7082 | TA416 | 0/2 | Completed
2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | Completed
2025-05-24 | 2025-05-28 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/4 | Completed
2025-05-24 | 2025-05-31 | Amar Singh | 42.3742 | 5.2968 | TA416 | 36/10 | Completed
2025-05-25 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 6.0535 | TA416 | 12/8 | Completed
2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | Completed
2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.049 | 7.6748 | TA416 | 38/5 | Completed
2025-05-28 | 2025-06-03 | Pinky Dewi | 55.339 | 7.9056 | TA416 | 23/1 | Completed
2025-05-25 | 2025-06-04 | Reeta Bharti | 42.374 | 3.8522 | TA416 | 0/3 | Completed
2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.374 | 7.0623 | TA416 | 56/5 | Completed
2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.229 | 8.1024 | TA416 | 51/0 | Completed
2025-06-03 | 2025-06-08 | Amar Singh | 46.049 | 7.6748 | TA416 | 33/5 | Completed
2025-06-04 | 2025-06-08 | Pinki Dewi | 43.776 | 8.7552 | TA416 | 23/2 | Completed
2025-06-05 | 2025-06-10 | Reeta Bharti | 42.374 | 7.0623 | TA416 | 0/1 | Completed
2025-06-08 | 2025-06-12 | Ananya Traders 2 | 43.776 | 8.7552 | TA416 | 50/1 | Completed
2025-06-02 | 2025-06-12 | Devine | 42.374 | 3.8522 | TA416 | 53A/5 | Completed
2025-06-09 | 2025-06-17 | Amar Singh | 43.776 | 4.864 | TA416 | 34/5 | Completed
2025-05-30 | 2025-06-17 | Amit Const | 46.049 | 2.4236 | TA416 | 53A/2 | Completed
2025-06-09 | 2025-06-19 | Pinki Dewi | 67.112 | 6.1011 | TA416 | 22/0 | Completed
2025-05-21 | 2025-06-21 | Asc Heights | 143.462 | 4.4832 | TA416 | 30/0 | Completed
2025-06-05 | 2025-06-23 | Reeta Bharti | 73.426 | 3.8645 | TA416 | 3/0 | Completed
2025-06-20 | 2025-06-26 | Pinki Dewi | 46.049 | 6.5784 | TA416 | 21/2 | Completed
2025-06-06 | 2025-06-26 | Mk Infra | 46.049 | 2.1928 | TA416 | 45/1 | Completed
2025-06-14 | 2025-06-28 | Ananya Traders 2 | 104.867 | 6.9911 | TA416 | 48/0 | Completed
2025-06-20 | 2025-06-28 | Amit Const | 42.374 | 4.7082 | TA416 | 53A/3 | Completed
1935-06-27 | 2025-06-29 | Pinki Dewi | 42.374 | 0.0012889 | TA416 | 21/1 | Completed
2025-06-03 | 2025-06-29 | Ananya Traders 1 | 161.355 | 5.9761 | TA416 | 40/0 | Completed
2025-06-24 | 2025-06-29 | Reeta Bharti | 42.374 | 7.0623 | TA416 | 12/7 | Completed
2025-05-28 | 2025-06-30 | Gagan | 188.378 | 5.5405 | TA416 | 14/0 | Completed
2025-06-22 | 2025-07-05 | Asc Heights | 46.049 | 3.2892 | TA416 | 28/1 | Completed
2025-07-02 | 2025-07-07 | Pinki Dewi | 46.049 | 7.6748 | TA416 | 21/3 | Completed
2025-07-02 | 2025-07-12 | Reeta Bharti | 55.339 | 5.0308 | TA416 | 25/1 | Completed
2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | Completed
2025-06-20 | 2025-07-22 | Amar Singh | 86.256 | 2.6138 | TA416 | 56/0 | Completed
2025-07-13 | 2025-07-31 | Reeta Bharti | 97.23 | 5.1174 | TA416 | 28/0 | Completed
2025-07-19 | 2025-08-08 | Ananya Traders 1 | 143.462 | 6.8315 | TA416 | 41/0 | Completed
2025-07-02 | 2025-08-11 | Gagan | 188.378 | 4.5946 | TA416 | 13/0 | Completed
2025-07-28 | 2025-08-17 | Punam Kumari | 46.049 | 2.1928 | TA416 | 53A/6 | Completed
2025-08-14 | 2025-08-26 | Kajal Const | 46.049 | 3.5422 | TA416 | 46/2 | Completed
2025-07-26 | 2025-08-27 | Kangresh 1 | 161.355 | 4.8895 | TA416 | 24/0 | Completed
2025-08-09 | 2025-08-30 | Radha Const | 78.073 | 3.5488 | TA416 | 1/0 | Completed
2025-08-04 | 2025-08-30 | Sainik Ent | 75.85 | 2.8093 | TA416 | 18/0 | Completed
2025-08-02 | 2025-08-30 | Kangresh 2 | 97.229 | 3.3527 | TA416 | 65/0 | Completed
2025-08-12 | 2025-09-02 | Gagan | 97.65 | 4.4386 | TA416 | 12/0 | Completed
2025-08-10 | 2025-09-07 | Ananya | 118.43 | 4.0838 | TA416 | 43/0 | Completed
2025-08-18 | 2025-09-04 | Punam Kumari | 55.339 | 3.0744 | TA416 | 54/1 | Completed
2025-09-08 |  | Ananya | 90.125 |  | TA416 | 47/0 | 3rd section wip
2025-08-18 |  | Mk Infra | 42.374 |  | TA416 | 48/1 | 1st section wip
2025-08-18 |  | Spotify Pvt Ltd 2 | 53.324 |  | TA416 | 53A/1 | 2nd section wip
2025-08-18 |  | Spotify Pvt Ltd 3 | 42.374 |  | TA416 | 56/8 | 3rd section wip
2025-08-31 |  | Sainik Ent | 87.01 |  | TA416 | 19/0 | 3rd section Completed
2025-08-31 |  | Kangresh 2 | 73.426 |  | TA416 | 64/0 | Bottom section wip
2025-08-31 |  | Radha Const | 89.7 |  | TA416 | 2/0 | Cage 1 wip
2025-08-24 | 2025-09-14 | Gouri Shankar | 97.65 | 4.4386 | TA416 | 11/0 | Completed
2025-09-04 |  | Gagan |  |  | TA416 | 23/0 | 1st section Completed
2025-08-16 | 2025-09-14 | Amit Const | 110.6 | 3.6867 | TA416 | 16/0 | Completed
2025-08-28 |  | Kangresh 1 | 161.355 |  | TA416 | 25/0 | 3rd section wip
2025-08-06 |  | Reeta Bharti | 161.355 |  | TA416 | 29/0 | Cage 2 Completed
2025-09-08 |  | Punam Kumari |  |  | TA416 | 52/0 | 3rd section wip
2025-09-11 |  | Maa Const |  |  | TA416 | 17/0 | leg joint Done
|  | Nan | 6152.1898 |  | TA505 |  | 130
2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-23 |  | Jhemon Mahato 2 | 85.264 |  | TA505 | 144A/0 | In-Progress
2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-26 |  | Paramanand 1 | 35.602 |  | TA505 | 160/2 | In-Progress
2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-26 |  | Pankaj Singh Mp | 36.16 |  | TA505 | 167/4 | In-Progress
2025-09-26 |  | Jagannaath Saw Mp | 55.451 |  | TA505 | 160/0 | In-Progress
2025-09-30 |  | Toshan Mahato | 36.1598 |  | TA505 | 148/1 | In-Progress
2025-09-30 |  | Deglal Mahato Mp | 36.16 |  | TA505 | 169/4 | In-Progress
2025-10-01 |  | Jyoti Const | 124.95 |  | TA505 | 112/0 | In-Progress
2025-10-01 |  | Shila Devi | 81.828 |  | TA505 | 128/0 | In-Progress
2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-10-02 |  | Pankaj Singh Mp | 36.1598 |  | TA505 | 167/2 | In-Progress
|  | Nan |  |  | TB401
|  | Nan |  |  | TB401
2023-09-13 | 2023-09-21 | Sobha Devi | 37.504 | 4.1671 | TB401 | 57/9 | Complete
2023-09-18 | 2023-09-25 | Sunny Const | 37.504 | 4.688 | TB401 | 58/12 | Complete
2023-09-21 | 2023-09-26 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/11 | Complete
|  | Nan |  |  | TB401
2023-09-25 | 2023-10-01 | Sunny Const | 37.504 | 5.3577 | TB401 | 58/14 | Complete
2023-09-26 | 2023-10-01 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/13 | Complete
2023-10-01 | 2023-10-06 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/10 | Complete
2023-10-01 | 2023-10-07 | Sunny Const | 37.504 | 5.3577 | TB401 | 58/9 | Complete
2023-10-03 | 2023-10-10 | Suraj Const | 37.504 | 4.688 | TB401 | 52/1 | Complete
2023-10-06 | 2023-10-11 | Sobha Devi | 38.847 | 6.4745 | TB401 | 57/12 | Complete
2023-10-07 | 2023-10-11 | Sunny Const | 37.504 | 7.5008 | TB401 | 58/8 | Complete
2023-09-25 | 2023-10-12 | Ganesh Kr Sinha | 37.504 | 2.0836 | TB401 | 58/1 | Complete
2023-10-10 | 2023-10-16 | Sobha Devi | 37.504 | 5.3577 | TB401 | 57/2 | Complete
2023-10-10 | 2023-10-15 | Suraj Const | 37.504 | 6.2507 | TB401 | 51/2 | Complete
2023-10-10 | 2023-10-17 | Sunny Const | 37.504 | 4.688 | TB401 | 58/16 | Complete
2023-10-15 | 2023-10-20 | Sobha Devi | 37.504 | 6.2507 | TB401 | 57/3 | Complete
2023-10-15 | 2023-10-21 | Suraj Const | 38.847 | 5.5496 | TB401 | 51/4 | Complete
2023-10-12 | 2023-10-22 | Ganesh Kr Sinha | 38.847 | 3.5315 | TB401 | 58/3 | Complete
2023-10-17 | 2023-10-23 | Sunny Const | 38.847 | 5.5496 | TB401 | 58/10 | Complete
2023-10-20 | 2023-10-26 | Sobha Devi | 37.504 | 5.3577 | TB401 | 57/4 | Complete
2023-10-20 | 2023-10-29 | Suraj Const | 37.504 | 3.7504 | TB401 | 51/5 | Complete
2023-10-26 | 2023-10-30 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/5 | Complete
2023-10-20 | 2023-10-31 | Ganesh Kr Sinha | 38.847 | 3.2372 | TB401 | 58/5 | Complete
2023-10-23 | 2023-10-31 | Sunny Const | 38.847 | 4.3163 | TB401 | 58/11 | Complete
|  | Nan |  |  | TB401
2023-10-30 | 2023-11-03 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/8 | Complete
2023-10-29 | 2023-11-04 | Suraj Const | 38.847 | 5.5496 | TB401 | 51/7 | Complete
2023-10-31 | 2023-11-07 | Sunny Const | 37.504 | 4.688 | TB401 | 59/6 | Complete
2023-11-03 | 2023-11-07 | Sobha Devi | 38.847 | 7.7694 | TB401 | 57/7 | Complete
2023-11-04 | 2023-11-09 | Suraj Const | 37.504 | 6.2507 | TB401 | 51/3 | Complete
2023-10-31 | 2023-11-11 | Ganesh Kr Sinha | 37.504 | 3.1253 | TB401 | 58/4 | Complete
2023-11-07 | 2023-11-13 | Sobha Devi | 38.847 | 5.5496 | TB401 | 57/1 | Complete
2023-11-07 | 2023-11-13 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/5 | Complete
2023-11-10 | 2023-11-14 | Suraj Const | 38.847 | 7.7694 | TB401 | 51/10 | Complete
2023-11-13 | 2023-11-16 | Sobha Devi | 38.847 | 9.7118 | TB401 | 56/9 | Complete
2023-11-13 | 2023-11-18 | Sunny Const | 37.504 | 6.2507 | TB401 | 59/3 | Complete
2023-11-15 | 2023-11-19 | Suraj Const | 38.847 | 7.7694 | TB401 | 52/2 | Complete
2023-11-15 | 2023-11-21 | Chinta Devi | 37.504 | 5.3577 | TB401 | 55/7 | Complete
2023-11-13 | 2023-11-21 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 58/6 | Complete
2023-11-16 | 2023-11-21 | Sobha Devi | 38.847 | 6.4745 | TB401 | 56/8 | Complete
2023-11-18 | 2023-11-24 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/2 | Complete
2023-11-19 | 2023-11-24 | Suraj Const | 38.847 | 6.4745 | TB401 | 52/5 | Complete
2023-11-22 | 2023-11-24 | Sobha Devi | 38.847 | 12.949 | TB401 | 56/7 | Complete
2023-11-22 | 2023-11-26 | Chinta Devi | 37.504 | 7.5008 | TB401 | 55/5 | Complete
2023-11-24 | 2023-11-29 | Sobha Devi | 37.504 | 6.2507 | TB401 | 56/3 | Complete
2023-11-24 | 2023-11-29 | Suraj Const | 38.847 | 6.4745 | TB401 | 53/3 | Complete
2023-11-24 | 2023-11-30 | Sunny Const | 37.504 | 5.3577 | TB401 | 59/1 | Complete
|  | Nan |  |  | TB401
2023-11-22 | 2023-12-01 | Ganesh Kr Sinha | 38.847 | 3.8847 | TB401 | 50/4 | Complete
2023-11-27 | 2023-12-02 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/4 | Complete
2023-11-29 | 2023-12-02 | Sobha Devi | 38.847 | 9.7118 | TB401 | 56/4 | Complete
2023-11-29 | 2023-12-03 | Suraj Const | 38.847 | 7.7694 | TB401 | 53/4 | Complete
2023-11-30 | 2023-12-06 | Sunny Const | 38.847 | 5.5496 | TB401 | 58/15 | Complete
2023-12-02 | 2023-12-06 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/2 | Complete
2023-12-02 | 2023-12-07 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/6 | Complete
2023-12-02 | 2023-12-09 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 48/1 | Complete
2023-12-03 | 2023-12-09 | Suraj Const | 38.847 | 5.5496 | TB401 | 55/1 | Complete
2023-12-07 | 2023-12-12 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/9 | Complete
2023-12-06 | 2023-12-13 | Sobha Devi | 57.597 | 7.1996 | TB401 | 57/6 | Complete
2023-12-06 | 2023-12-14 | Sunny Const | 37.504 | 4.1671 | TB401 | 61/2 | Complete
2023-12-09 | 2023-12-15 | Suraj Const | 38.847 | 5.5496 | TB401 | 55/2 | Complete
2023-12-09 | 2023-12-16 | Ganesh Kr Sinha | 38.847 | 4.8559 | TB401 | 48/2 | Complete
2023-12-12 | 2023-12-17 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/10 | Complete
2023-12-13 | 2023-12-19 | Sobha Devi | 57.597 | 8.2281 | TB401 | 57/0 | Complete
2023-12-16 | 2023-12-19 | Suraj Const | 37.504 | 9.376 | TB401 | 55/3 | Complete
2023-12-14 | 2023-12-20 | Sunny Const | 37.504 | 5.3577 | TB401 | 61/1 | Complete
2023-12-16 | 2023-12-22 | Ganesh Kr Sinha | 37.504 | 5.3577 | TB401 | 50/3 | Complete
2023-12-17 | 2023-12-22 | Chinta Devi | 38.847 | 6.4745 | TB401 | 55/11 | Complete
2023-12-20 | 2023-12-24 | Sobha Devi | 37.504 | 7.5008 | TB401 | 56/5 | Complete
2023-12-20 | 2023-12-24 | Suraj Const | 37.504 | 7.5008 | TB401 | 52/4 | Complete
2023-12-22 | 2023-12-28 | Chinta Devi | 38.847 | 5.5496 | TB401 | 55/8 | Complete
2023-12-24 | 2023-12-28 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/6 | Complete
2023-12-07 | 2023-12-29 | Sunny Const | 57.597 | 2.5042 | TB401 | 59/0 | Complete
2023-12-22 | 2023-12-29 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 47/3 | Complete
2023-12-24 | 2023-12-29 | Suraj Const | 38.847 | 6.4745 | TB401 | 51/9 | Complete
|  | Nan |  |  | TB401
2023-12-28 | 2024-01-05 | Sobha Devi | 57.597 | 6.3997 | TB401 | 56/0 | Complete
2023-12-28 | 2024-01-05 | Chinta Devi | 37.504 | 4.1671 | TB401 | 44/2 | Complete
2023-12-29 | 2024-01-06 | Suraj Const | 38.847 | 4.3163 | TB401 | 51/8 | Complete
2023-12-29 | 2024-01-07 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 47/2 | Complete
2023-12-29 | 2024-01-09 | Sunny Const | 57.597 | 4.7998 | TB401 | 58/7 | Complete
2024-01-05 | 2024-01-09 | Chinta Devi | 37.504 | 7.5008 | TB401 | 44/4 | Complete
2024-01-06 | 2024-01-11 | Suraj Const | 38.847 | 6.4745 | TB401 | 53/2 | Complete
2024-01-05 | 2024-01-12 | Sobha Devi | 38.847 | 4.8559 | TB401 | 41/11 | Complete
2024-01-09 | 2024-01-15 | Chinta Devi | 38.847 | 5.5496 | TB401 | 44/3 | Complete
2023-10-12 | 2024-01-16 | Sobha Devi | 38.847 | 0.40048 | TB401 | 41/10 | Complete
2024-01-07 | 2024-01-19 | Ganesh Kr Sinha | 57.597 | 4.4305 | TB401 | 48/0 | Complete
2024-01-12 | 2024-01-19 | Sunny Const | 37.504 | 4.688 | TB401 | 46/3 | Complete
2024-01-12 | 2024-01-19 | Suraj Const | 37.504 | 4.688 | TB401 | 51/6 | Complete
2024-01-16 | 2024-01-20 | Sobha Devi | 38.847 | 7.7694 | TB401 | 41/7 | Complete
2024-01-15 | 2024-01-22 | Chinta Devi | 47.148 | 5.8935 | TB401 | 43/4 | Complete
2024-01-22 | 2024-01-27 | Chinta Devi | 37.504 | 6.2507 | TB401 | 43/5 | Complete
2024-01-20 | 2024-01-28 | Sunny Const | 57.597 | 6.3997 | TB401 | 47/0 | Complete
2024-01-20 | 2024-01-28 | Ganesh Kr Sinha | 57.597 | 6.3997 | TB401 | 51/0 | Complete
2024-01-20 | 2024-01-28 | Suraj Const | 57.597 | 6.3997 | TB401 | 52/0 | Complete
2024-01-23 | 2024-01-28 | Sobha Devi | 47.148 | 7.858 | TB401 | 43/1 | Complete
2024-01-28 | 2024-01-31 | Sobha Devi | 37.504 | 9.376 | TB401 | 41/5 | Bottom complete
|  | Nan |  |  | TB401
2024-01-28 | 2024-02-01 | Chinta Devi | 37.504 | 7.5008 | TB401 | 44/1 | Complete
2024-01-28 | 2024-02-02 | Sunny Const | 37.504 | 6.2507 | TB401 | 46/2 | Complete
2024-01-28 | 2024-02-04 | Ganesh Kr Sinha | 37.504 | 4.688 | TB401 | 51/1 | Complete
2024-02-01 | 2024-02-05 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/4 | Complete
2024-02-04 | 2024-02-09 | Suraj Const | 37.504 | 6.2507 | TB401 | 53/1 | Complete
2024-02-07 | 2024-02-09 | Sobha Devi | 37.504 | 12.5013 | TB401 | 41/6 | Complete
2024-02-09 | 2024-02-13 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/8 | Complete
2024-02-13 | 2024-02-17 | Sobha Devi | 37.504 | 7.5008 | TB401 | 41/9 | Complete
2024-02-03 | 2024-02-09 | Tejal Construction | 38.847 | 5.5496 | TB401 | 29/8 | Complete
2024-02-10 | 2024-02-18 | Tejal Construction | 38.847 | 4.3163 | TB401 | 29/7 | Complete
2024-02-18 | 2024-02-24 | Tejal Construction | 37.504 | 5.3577 | TB401 | 29/5 | Complete
|  | Nan |  |  | TB401
2024-03-28 | 2024-04-04 | Sobha Devi | 66.381 | 8.2976 | TB401 | 55/0 | Complete
2024-04-08 | 2024-04-16 | Sunny Const | 66.381 | 7.3757 | TB401 | 58/0 | Complete
2024-04-12 | 2024-04-16 | Sobha Devi | 38.847 | 7.7694 | TB401 | 56/1 | Complete
2024-04-08 | 2024-04-18 | Ganesh Kr Sinha | 69.229 | 6.2935 | TB401 | 53/0 | Complete
|  | Nan |  |  | TB401
2024-04-26 | 2024-05-05 | Ganesh Kr Sinha | 37.504 | 3.7504 | TB401 | 52/3 | Complete
2024-05-05 | 2024-05-10 | Sunny Const | 37.504 | 6.2507 | TB401 | 58/2 | Complete
2024-05-10 | 2024-05-16 | Sunny Const | 37.504 | 5.3577 | TB401 | 65/4 | Complete
2024-05-16 | 2024-05-21 | Sunny Const | 37.504 | 6.2507 | TB401 | 65/3 | Complete
2024-05-16 | 2024-05-26 | Sunny Const | 37.504 | 3.4095 | TB401 | 65/5 | Complete
|  | Nan |  |  | TB401
2024-05-15 | 2024-06-08 | Departmental Gang | 45.413 | 1.8165 | TB401 | 29/6
2024-06-10 | 2024-06-24 | Departmental Gang | 38.847 | 2.5898 | TB401 | 29/9
|  | Nan |  |  | TB401
2024-06-25 | 2024-07-06 | Departmental Gang | 45.413 | 3.7844 | TB401 | 29/10
2024-07-07 | 2024-07-12 | Departmental Gang | 37.504 | 6.2507 | TB401 | 31/3
2024-07-13 | 2024-07-22 | Departmental Gang | 37.504 | 3.7504 | TB401 | 31/2
|  | Nan |  |  | TB401
2024-08-27 | 2024-08-30 | Sobha Devi | 37.504 | 9.376 | TB401 | 46/4 | Complete
2024-07-22 | 2024-08-01 | Departmental Gang | 45.413 | 4.1285 | TB401 | 32/5
2024-07-12 | 2024-08-04 | Sanjay Mahto | 47.148 | 1.9645 | TB401 | 31/4
2024-08-02 | 2024-08-09 | Yogendra Mahto | 45.413 | 5.6766 | TB401 | 32/6
2024-08-10 | 2024-08-20 | Yogendra Mahto | 37.504 | 3.4095 | TB401 | 32/2
|  | Nan |  |  | TB401
2024-08-25 | 2024-09-01 | Sunny Const | 37.504 | 4.688 | TB401 | 72/3 | Complete
2024-09-01 | 2024-09-06 | Sunny Const | 37.504 | 6.2507 | TB401 | 72/4 | Complete
2024-08-28 | 2024-09-06 | Chinta Devi | 37.504 | 3.7504 | TB401 | 71/5 | Complete
2024-09-01 | 2024-09-11 | Sunny Const | 37.504 | 3.4095 | TB401 | 72/5 | Complete
2024-09-09 | 2024-09-12 | Sobha Devi | 37.504 | 9.376 | TB401 | 47/1 | Complete
2024-09-11 | 2024-09-15 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/6 | Complete
2024-09-06 | 2024-09-16 | Chinta Devi | 57.597 | 5.2361 | TB401 | 72/0 | Complete
2024-09-12 | 2024-09-16 | Sobha Devi | 37.504 | 7.5008 | TB401 | 50/2 | Complete
2024-09-16 | 2024-09-20 | Sobha Devi | 37.504 | 7.5008 | TB401 | 50/1 | Complete
2024-09-16 | 2024-09-22 | Chinta Devi | 37.504 | 5.3577 | TB401 | 71/4 | Complete
2024-09-15 | 2024-09-25 | Sunny Const | 70.701 | 6.4274 | TB401 | 72/7 | Complete
2024-09-09 | 2024-09-26 | Jirwa Devi | 45.413 | 2.5229 | TB401 | 43/6 | Complete
2024-09-20 | 2024-09-26 | Sobha Devi | 69.229 | 9.8899 | TB401 | 50/0 | Complete
2024-09-22 | 2024-09-26 | Chinta Devi | 37.504 | 7.5008 | TB401 | 71/2 | Complete
2024-09-25 | 2024-09-29 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/2 | Complete
2024-08-28 | 2024-09-05 | Nirmal Mahto | 38.847 | 4.3163 | TB401 | 15/3 | Complete
2024-08-30 | 2024-09-06 | Deglal Mahto | 38.847 | 4.8559 | TB401 | 16/2 | Complete
2024-08-28 | 2024-09-08 | Jailal Ageria | 37.504 | 3.1253 | TB401 | 14/4 | Complete
2024-09-07 | 2024-09-11 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/3 | Complete
2024-09-07 | 2024-09-12 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 16/3 | Complete
2024-09-12 | 2024-09-16 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/4 | Complete
2024-09-12 | 2024-09-16 | Deglal Mahto | 38.847 | 7.7694 | TB401 | 16/4 | Complete
2024-09-06 | 2024-09-19 | Bina Devi | 47.148 | 3.3677 | TB401 | 10/19 | Complete
2024-09-16 | 2024-09-20 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/5 | Complete
2024-09-10 | 2024-09-20 | Jailal Ageria | 37.504 | 3.4095 | TB401 | 14/5 | Complete
2024-09-19 | 2024-09-21 | Nirmal Mahto | 47.148 | 15.716 | TB401 | 15/2 | Complete
2024-09-21 | 2024-09-25 | Jagdish Mahto | 38.847 | 7.7694 | TB401 | 10/6 | Complete
2024-09-10 | 2024-09-26 | Khublal Mahto | 38.847 | 2.2851 | TB401 | 10/14 | Complete
2024-09-22 | 2024-09-27 | Nirmal Mahto | 38.847 | 6.4745 | TB401 | 15/4 | Complete
|  | Nan |  |  | TB401
2024-09-26 | 2024-10-01 | Chinta Devi | 37.504 | 6.2507 | TB401 | 71/1 | Complete
2024-09-29 | 2024-10-03 | Sunny Const | 37.504 | 7.5008 | TB401 | 72/1 | Complete
2024-10-02 | 2024-10-05 | Chinta Devi | 38.847 | 9.7118 | TB401 | 68/1 | Complete
2024-09-27 | 2024-10-08 | Jirwa Devi | 38.847 | 3.2372 | TB401 | 43/3 | Complete
2024-10-05 | 2024-10-10 | Chinta Devi | 38.847 | 6.4745 | TB401 | 68/2 | Complete
2024-09-30 | 2024-10-10 | Sanjeev Kumar | 37.504 | 3.4095 | TB401 | 66/2 | Complete
2024-10-03 | 2024-10-17 | Sunny Const | 105.068 | 7.0045 | TB401 | 73/0 | Complete
2024-10-10 | 2024-10-19 | Chinta Devi | 70.701 | 7.0701 | TB401 | 67/1 | Complete
2024-10-08 | 2024-10-22 | Jirwa Devi | 47.148 | 3.1432 | TB401 | 43/2 | Complete
2024-10-18 | 2024-10-23 | Sunny Const | 37.504 | 6.2507 | TB401 | 71/3 | Complete
2024-10-23 | 2024-10-27 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/6 | Complete
2024-10-24 | 2024-10-28 | Chinta Devi | 37.504 | 7.5008 | TB401 | 68/3 | Complete
2024-10-23 | 2024-10-30 | Ganesh Kr Sinha | 47.148 | 5.8935 | TB401 | 40/11 | Complete
2024-10-27 | 2024-10-31 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/7 | Complete
2024-09-28 | 2024-10-03 | Deglal Mahto | 38.847 | 6.4745 | TB401 | 16/5 | Complete
2024-09-26 | 2024-10-04 | Yogendra Mahto | 37.504 | 4.1671 | TB401 | 10/21 | Complete
2024-09-30 | 2024-10-04 | Jagdish Mahto | 45.413 | 9.0826 | TB401 | 10/7 | Complete
2024-09-20 | 2024-10-06 | Bina Devi | 38.847 | 2.2851 | TB401 | 11/5 | Complete
2024-08-30 | 2024-10-09 | Parsuram Sai | 37.504 | 0.91473 | TB401 | 32/4 | Complete
2024-10-08 | 2024-10-11 | Jagdish Mahto | 38.847 | 9.7118 | TB401 | 10/9 | Complete
2024-09-19 | 2024-10-11 | Yogendra Mahto | 47.148 | 2.0499 | TB401 | 19/14 | Complete
2024-10-08 | 2024-10-15 | Rafikul Islam | 38.847 | 4.8559 | TB401 | 11/7 | Complete
2024-10-05 | 2024-10-16 | Jailal Ageria | 66.381 | 5.5317 | TB401 | 15/0 | Complete
2024-10-08 | 2024-10-17 | Rafikul Islam | 37.504 | 3.7504 | TB401 | 11/8 | Complete
2024-10-09 | 2024-10-18 | Deglal Mahto | 66.381 | 6.6381 | TB401 | 17/0 | Complete
2024-10-11 | 2024-10-19 | Bina Devi | 37.504 | 4.1671 | TB401 | 10/18 | Complete
2024-10-13 | 2024-10-28 | Yogendra Mahto | 67.873 | 4.2421 | TB401 | 32/0 | Complete
2024-10-13 | 2024-10-28 | Rafikul Islam | 38.847 | 2.4279 | TB401 | 11/9 | Complete
|  | Nan |  |  | TB401
2024-09-28 | 2024-11-01 | Chinta Devi | 38.847 | 1.1099 | TB401 | 68/5 | Complete
2024-11-01 | 2024-11-05 | Chinta Devi | 38.847 | 7.7694 | TB401 | 68/6 | Complete
2024-11-01 | 2024-11-05 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/5 | Complete
2024-11-05 | 2024-11-09 | Chinta Devi | 38.847 | 7.7694 | TB401 | 68/4 | Complete
2024-11-05 | 2024-11-09 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/4 | Complete
2024-10-30 | 2024-11-11 | Ganesh Kr Sinha | 67.873 | 5.221 | TB401 | 40/10 | Complete
2024-11-09 | 2024-11-13 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/3 | Complete
2024-10-29 | 2024-11-14 | Sanjeev Kumar | 38.847 | 2.2851 | TB401 | 66/4 | Complete
2024-11-13 | 2024-11-17 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/2 | Complete
2024-11-18 | 2024-11-22 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/1 | Complete
2024-11-22 | 2024-11-29 | Chinta Devi | 86.129 | 10.7661 | TB401 | 68/0 | Complete
2024-11-23 | 2024-11-30 | Sunny Const | 57.597 | 7.1996 | TB401 | 69/0 | Complete
2024-10-24 | 2024-11-01 | Jagdish Mahto | 37.504 | 4.1671 | TB401 | 10/8 | Complete
2024-10-27 | 2024-11-02 | Nirmal Mahto | 45.413 | 6.4876 | TB401 | 15/1 | Complete
2024-10-31 | 2024-11-03 | Deglal Mahto | 47.148 | 11.787 | TB401 | 15/9 | Complete
2024-10-27 | 2024-11-04 | Jailal Ageria | 38.847 | 4.3163 | TB401 | 14/2 | Complete
2024-11-02 | 2024-11-07 | Yogendra Mahto | 38.847 | 6.4745 | TB401 | 32/3 | Complete
2024-11-04 | 2024-11-09 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 15/6 | Complete
2024-10-20 | 2024-11-10 | Rafikul Islam | 38.847 | 1.7658 | TB401 | 11/6 | Complete
2024-11-06 | 2024-11-10 | Jagdish Mahto | 60.096 | 12.0192 | TB401 | 10/12 | Complete
2024-10-12 | 2024-11-12 | Parsuram Sai | 47.148 | 1.4734 | TB401 | 32/1 | Complete
2024-11-11 | 2024-11-17 | Deglal Mahto | 37.504 | 5.3577 | TB401 | 11/14 | Complete
2024-11-11 | 2024-11-17 | Jagdish Mahto | 38.847 | 5.5496 | TB401 | 10/10 | Complete
2024-11-10 | 2024-11-21 | Bina Devi | 57.597 | 4.7998 | TB401 | 16/0 | Complete
2024-11-18 | 2024-11-21 | Jagdish Mahto | 38.847 | 9.7118 | TB401 | 10/13 | Complete
2024-11-18 | 2024-11-23 | Deglal Mahto | 37.504 | 6.2507 | TB401 | 11/15 | Complete
2024-11-19 | 2024-11-25 | Jailal Ageria | 38.847 | 5.5496 | TB401 | 13/1 | Complete
2024-11-17 | 2024-11-28 | Nirmal Mahto | 47.148 | 3.929 | TB401 | 19/7 | Complete
2024-11-22 | 2024-11-29 | Jagdish Mahto | 37.504 | 4.688 | TB401 | 10/11 | Complete
|  | Nan |  |  | TB401
2024-12-01 | 2024-12-06 | Sunny Const | 37.504 | 6.2507 | TB401 | 69/9 | Complete
2024-12-01 | 2024-12-08 | Chinta Devi | 86.129 | 10.7661 | TB401 | 67/0 | Complete
2024-12-02 | 2024-12-08 | Sanjeev Kumar | 38.847 | 5.5496 | TB401 | 66/1 | Complete
2024-12-10 | 2024-12-15 | Sobha Devi | 47.148 | 7.858 | TB401 | 38/3 | Complete
2024-12-09 | 2024-12-17 | Ganesh Kr Sinha | 38.847 | 4.3163 | TB401 | 41/12 | Complete
2024-12-07 | 2024-12-17 | Sunny Const | 86.129 | 7.8299 | TB401 | 71/0 | Complete
2024-12-14 | 2024-12-18 | Chinta Devi | 37.504 | 7.5008 | TB401 | 65/6 | Complete
2024-12-11 | 2024-12-19 | Sanjeev Kumar | 37.504 | 4.1671 | TB401 | 58/13 | Complete
2024-12-15 | 2024-12-19 | Sobha Devi | 45.413 | 9.0826 | TB401 | 38/2 | Complete
2024-12-18 | 2024-12-22 | Sunny Const | 37.504 | 7.5008 | TB401 | 69/8 | Complete
2024-12-18 | 2024-12-22 | Chinta Devi | 37.504 | 7.5008 | TB401 | 65/7 | Complete
2024-12-20 | 2024-12-24 | Sobha Devi | 38.847 | 7.7694 | TB401 | 38/1 | Complete
2024-12-25 | 2024-12-28 | Sobha Devi | 37.504 | 9.376 | TB401 | 37/3 | Complete
2024-12-21 | 2024-12-28 | Jirwa Devi | 37.504 | 4.688 | TB401 | 41/2 | Complete
2024-12-22 | 2024-12-31 | Sunny Const | 86.129 | 8.6129 | TB401 | 70/0 | Complete
2024-12-19 | 2024-12-31 | Ganesh Kr Sinha | 81.945 | 6.3035 | TB401 | 42/0 | Complete
2024-12-22 | 2024-12-31 | Chinta Devi | 86.129 | 8.6129 | TB401 | 66/0 | Complete
2024-11-28 | 2024-12-20 | Yogendra Mahto | 89.909 | 3.9091 | TB401 | 31/0 | Complete
2024-12-07 | 2024-12-22 | Bina Devi | 37.504 | 2.344 | TB401 | 11/12 | Complete
2024-12-07 | 2024-12-24 | Jailal Ageria | 86.129 | 4.7849 | TB401 | 13/0 | Complete
2024-12-11 | 2024-12-24 | Jagdish Mahto | 67.873 | 4.8481 | TB401 | 10/20 | Complete
2024-12-17 | 2024-12-24 | Deglal Mahto | 37.504 | 4.688 | TB401 | 11/11 | Complete
2024-12-22 | 2024-12-30 | Bina Devi | 37.504 | 4.1671 | TB401 | 11/13 | Complete
|  | Nan |  |  | TB401
2024-12-29 | 2025-01-03 | Sobha Devi | 45.413 | 7.5688 | TB401 | 37/4 | Complete
2024-12-29 | 2025-01-07 | Jirwa Devi | 37.504 | 3.7504 | TB401 | 41/3 | Complete
2025-01-06 | 2025-01-10 | Sanjeev Kumar | 37.504 | 7.5008 | TB401 | 59/4 | Complete
2025-01-04 | 2025-01-10 | Sobha Devi | 67.873 | 9.6961 | TB401 | 37/2 | Complete
2025-01-10 | 2025-01-16 | Sobha Devi | 38.847 | 5.5496 | TB401 | 37/5 | Complete
2025-01-10 | 2025-01-17 | Jirwa Devi | 38.847 | 4.8559 | TB401 | 41/1 | Complete
2025-01-16 | 2025-01-20 | Sobha Devi | 45.413 | 9.0826 | TB401 | 37/6 | Complete
2025-01-20 | 2025-01-24 | Sobha Devi | 38.847 | 7.7694 | TB401 | 37/7 | Complete
2025-01-19 | 2025-01-28 | Om Construction | 45.413 | 4.5413 | TB401 | 39/1 | Complete
2025-01-25 | 2025-01-28 | Sobha Devi | 37.504 | 9.376 | TB401 | 37/8 | Complete
2025-01-18 | 2025-01-29 | Jirwa Devi | 57.597 | 4.7998 | TB401 | 41/0 | Complete
2025-01-10 | 2025-01-30 | Sunny Const | 70.701 | 3.3667 | TB401 | 40/2 | Complete
2024-12-25 | 2025-01-06 | Jagdish Mahto | 38.847 | 2.9882 | TB401 | 8/6 | Complete
|  | Nan |  |  | TB401
2025-01-29 | 2025-02-04 | Sobha Devi | 66.381 | 9.483 | TB401 | 38/0 | Complete
2025-01-29 | 2025-02-08 | Jirwa Devi | 37.504 | 3.4095 | TB401 | 40/12 | Complete
2025-01-31 | 2025-02-18 | Ganesh Kr Sinha | 70.701 | 3.7211 | TB401 | 43/0 | Complete
2025-02-07 | 2025-02-19 | Sanjeev Kumar | 69.229 | 5.3253 | TB401 | 60/0 | Complete
2025-02-15 | 2025-02-20 | Sunny Const | 38.847 | 6.4745 | TB401 | 40/6 | Complete
2025-02-09 | 2025-02-23 | Jirwa Devi | 69.229 | 4.6153 | TB401 | 49/0 | Complete
2025-02-21 | 2025-02-26 | Sunny Const | 38.847 | 6.4745 | TB401 | 40/7 | Complete
2025-02-19 | 2025-02-28 | Ganesh Kr Sinha | 57.597 | 5.7597 | TB401 | 44/0 | Complete
2025-02-21 | 2025-02-28 | Sobha Devi | 69.229 | 8.6536 | TB401 | 39/0 | Complete
|  | Nan |  |  | TB401
2025-02-20 | 2025-03-03 | Sanjeev Kumar | 67.873 | 5.6561 | TB401 | 61/0 | Complete
2025-02-27 | 2025-03-06 | Sunny Const | 66.381 | 8.2976 | TB401 | 40/0 | Complete
2025-03-01 | 2025-03-07 | Sobha Devi | 67.873 | 9.6961 | TB401 | 38/9 | Complete
2025-03-08 | 2025-03-11 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/8 | Complete
2025-03-08 | 2025-03-12 | Sunny Const | 37.504 | 7.5008 | TB401 | 40/1 | Complete
2025-03-13 | 2025-03-17 | Sobha Devi | 37.504 | 7.5008 | TB401 | 38/7 | Complete
2025-03-13 | 2025-03-20 | Sunny Const | 47.148 | 5.8935 | TB401 | 40/4 | Complete
2025-03-18 | 2025-03-21 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/6 | Complete
2025-03-22 | 2025-03-25 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/5 | Complete
2025-03-21 | 2025-03-28 | Sunny Const | 70.701 | 8.8376 | TB401 | 40/5 | Complete
2025-03-26 | 2025-03-29 | Sobha Devi | 37.504 | 9.376 | TB401 | 38/4 | Complete
2025-03-01 | 2025-03-09 | Bina Devi | 37.504 | 4.1671 | TB401 | 1A/1 | Complete
2025-03-10 | 2025-03-27 | Bina Devi | 45.413 | 2.5229 | TB401 | 1A/2 | Complete
|  | Nan |  |  | TB401
2025-04-06 | 2025-04-10 | Sobha Devi | 38.847 | 7.7694 | TB401 | 35/9 | Complete
2025-04-11 | 2025-04-14 | Sobha Devi | 37.504 | 9.376 | TB401 | 35/8 | Complete
2025-04-10 | 2025-04-15 | Chinta Devi | 38.847 | 6.4745 | TB401 | 63/5 | Complete
2025-04-15 | 2025-04-20 | Chinta Devi | 38.847 | 6.4745 | TB401 | 63/6 | Complete
2025-04-15 | 2025-04-20 | Sobha Devi | 38.847 | 6.4745 | TB401 | 35/7 | Complete
2025-04-15 | 2025-04-21 | Sunny Const | 45.413 | 6.4876 | TB401 | 63/1 | Complete
2025-04-21 | 2025-04-25 | Sunny Const | 37.504 | 7.5008 | TB401 | 63/2 | Complete
2025-04-21 | 2025-04-26 | Chinta Devi | 37.504 | 6.2507 | TB401 | 63/4 | Complete
2025-04-21 | 2025-04-26 | Sobha Devi | 47.148 | 7.858 | TB401 | 35/6 | Complete
2025-04-26 | 2025-04-30 | Sunny Const | 38.847 | 7.7694 | TB401 | 63/3 | Complete
2025-04-26 | 2025-04-30 | Sobha Devi | 37.504 | 7.5008 | TB401 | 35/5 | Complete
|  | Nan |  |  | TB401
2025-04-30 | 2025-05-06 | Satyam Manish | 45.413 | 6.4876 | TB401 | 44/5 | Complete
2025-04-30 | 2025-05-06 | Satyam Nitish | 38.847 | 5.5496 | TB401 | 39/3 | Complete
2025-04-30 | 2025-05-09 | Sunny Const | 66.381 | 6.6381 | TB401 | 62/0 | Complete
2025-05-07 | 2025-05-11 | Satyam Nitish | 37.504 | 7.5008 | TB401 | 39/2 | Complete
2025-04-29 | 2025-05-13 | Ganesh Kr Sinha | 45.413 | 3.0275 | TB401 | 34/4 | Complete
2025-04-28 | 2025-05-15 | Annaya Traders | 37.504 | 2.0836 | TB401 | 33/5 | Complete
2025-05-12 | 2025-05-17 | Satyam Nitish | 37.504 | 6.2507 | TB401 | 39/4 | Complete
2025-05-12 | 2025-05-19 | Sunny Const | 86.129 | 10.7661 | TB401 | 63/0 | Complete
2025-05-07 | 2025-05-23 | Satyam Manish | 143.601 | 8.4471 | TB401 | 45/0 | Complete
2025-05-12 | 2025-05-23 | Satyam Trivedi | 37.504 | 3.1253 | TB401 | 64/9 | Complete
2025-05-17 | 2025-05-24 | Satyam Nitish | 70.701 | 8.8376 | TB401 | 37/1 | Complete
2025-05-13 | 2025-05-25 | Satyam Mondal | 57.597 | 4.4305 | TB401 | 35/0 | Complete
2025-05-15 | 2025-05-27 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/6 | Complete
2025-05-24 | 2025-05-31 | Satyam Trivedi | 37.504 | 4.688 | TB401 | 64/8 | Complete
|  | Nan |  |  | TB401
2025-05-24 | 2025-06-03 | Satyam Manish | 45.413 | 4.1285 | TB401 | 46/1 | Complete
2025-05-30 | 2025-06-04 | Pankaj | 37.504 | 6.2507 | TB401 | 24/6 | Complete
2025-05-04 | 2025-06-05 | Bhairo Mahto Departmental | 38.847 | 1.1772 | TB401 | 1A/4 | Complete
2025-05-27 | 2025-06-06 | Satyam Mondal | 45.413 | 4.1285 | TB401 | 34/6 | Complete
2025-05-28 | 2025-06-06 | Jwala Singh 1 | 57.597 | 5.7597 | TB401 | 64/0 | Complete
2025-05-29 | 2025-06-08 | Satyam Vijay | 38.847 | 3.5315 | TB401 | 64/5 | Complete
2025-01-19 | 2025-06-09 | Satyam Trivedi | 38.847 | 0.27357 | TB401 | 66/3 | Complete
2025-06-08 | 2025-06-13 | Satyam Manish | 37.504 | 6.2507 | TB401 | 40/8 | Complete
2025-05-26 | 2025-06-15 | Satyam Nitish | 143.601 | 6.8381 | TB401 | 36/0 | Complete
2025-06-08 | 2025-06-15 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/1 | Complete
2025-06-07 | 2025-06-15 | Jwala Singh 1 | 45.413 | 5.0459 | TB401 | 64/1 | Complete
2025-05-30 | 2025-06-15 | Satyam Santosh | 37.504 | 2.2061 | TB401 | 64/3 | Complete
2025-05-16 | 2025-06-15 | Bhairo Mahto Departmental | 37.504 | 1.2098 | TB401 | 1A/3 | Complete
2025-06-16 | 2025-06-18 | Satyam Manish | 37.504 | 12.5013 | TB401 | 40/9 | Complete
2025-06-09 | 2025-06-18 | Jwala Singh 2 | 38.847 | 3.8847 | TB401 | 39/5 | Complete
2025-06-10 | 2025-06-19 | Satyam Trivedi | 60.096 | 6.0096 | TB401 | 65/0 | Complete
2025-05-30 | 2025-06-19 | Kewat Departmental | 37.504 | 1.7859 | TB401 | 1A/6 | Complete
2025-06-10 | 2025-06-22 | Satyam Vijay | 38.847 | 2.9882 | TB401 | 64/7 | Complete
2025-06-16 | 2025-06-23 | Satyam Mondal | 37.504 | 4.688 | TB401 | 35/2 | Complete
2025-05-20 | 2025-06-27 | Bhairo Mahto Departmental | 45.413 | 1.1644 | TB401 | 1A/5 | Complete
2025-06-18 | 2025-06-27 | Poonam | 38.847 | 3.8847 | TB401 | 24/5 | Complete
2025-06-24 | 2025-06-27 | Jwala Singh 3 | 38.847 | 9.7118 | TB401 | 8/9 | Complete
2025-06-23 | 2025-06-28 | Satyam Trivedi | 37.504 | 6.2507 | TB401 | 65/2 | Complete
2025-06-23 | 2025-06-28 | Jwala Singh 1 | 37.504 | 6.2507 | TB401 | 64/2 | Complete
2025-06-22 | 2025-06-28 | Jwala Singh 2 | 37.504 | 5.3577 | TB401 | 39/6 | Complete
2025-06-18 | 2025-06-30 | Satyam Manish | 143.601 | 11.0462 | TB401 | 46/0 | Complete
2025-06-17 | 2025-06-30 | Satyam Nitish | 143.601 | 10.2572 | TB401 | 37/0 | Complete
2025-06-25 | 2025-06-30 | Satyam Mondal | 37.504 | 6.2507 | TB401 | 35/3 | Complete
2025-06-10 | 2025-06-30 | Permanand | 38.847 | 1.8499 | TB401 | 40/3 | Complete
2025-06-27 | 2025-06-30 | Pusplata 1 | 45.413 | 11.3532 | TB401 | 25/11 | Complete
2025-06-26 | 2025-06-30 | Pusplata 4 | 38.847 | 7.7694 | TB401 | 25/5 | Complete
|  | Nan |  |  | TB401
2025-06-29 | 2025-07-02 | Poonam | 37.504 | 9.376 | TB401 | 24/4 | Complete
2025-06-30 | 2025-07-03 | Jwala Singh 2 | 37.504 | 9.376 | TB401 | 39/7 | Complete
2025-06-26 |  | Arawali Infra 1 | 37.504 |  | TB401 | 2/9 | Complete
2025-06-23 | 2025-07-04 | Priyanka Devi Sudheer | 45.413 | 3.7844 | TB401 | 15/7 | Complete
2025-06-27 | 2025-07-04 | Pusplata 5 | 38.847 | 4.8559 | TB401 | 21/2 | Complete
2025-06-30 | 2025-07-05 | Satyam Trivedi | 38.847 | 6.4745 | TB401 | 65/1 | Complete
2025-06-27 | 2025-07-05 | Pusplata 2 | 45.413 | 5.0459 | TB401 | 23/6 | Complete
2025-06-28 | 2025-07-05 | Pusplata 3 | 37.504 | 4.688 | TB401 | 24/2 | Complete
2025-07-01 | 2025-07-06 | Satyam Mondal | 38.847 | 6.4745 | TB401 | 35/4 | Complete
2025-06-24 | 2025-07-06 | Arawali Infra 2 | 86.129 | 6.6253 | TB401 | 12/0 | Complete
2025-07-02 | 2025-07-06 | Pusplata 4 | 38.847 | 7.7694 | TB401 | 25/6 | Complete
2025-07-02 | 2025-07-06 | Jwala Singh 3 | 38.847 | 7.7694 | TB401 | 8/10 | Complete
2025-06-09 | 2025-07-07 | Anil Kumar Departmental Kewat | 38.847 | 1.3396 | TB401 | 1A/7 | Complete
2025-07-04 | 2025-07-07 | Poonam | 37.504 | 9.376 | TB401 | 24/3 | Complete
2025-06-21 | 2025-07-08 | Satyam Manish 2 Santosh | 38.847 | 2.1582 | TB401 | 64/4 | Complete
2025-07-04 | 2025-07-08 | Satyam Nitish | 45.413 | 9.0826 | TB401 | 33/6 | Complete
2025-06-28 | 2025-07-08 | Pusplata 6 | 45.413 | 4.1285 | TB401 | 22/6 | Complete
2025-06-30 | 2025-07-08 | Gourishankar | 47.148 | 5.2387 | TB401 | 29/2 | Complete
2025-06-23 | 2025-07-09 | Vinay Const | 47.148 | 2.7734 | TB401 | 34/2 | Complete
2025-07-04 | 2025-07-09 | Satyam Manish | 60.096 | 10.016 | TB401 | 33/0 | Complete
2025-07-04 | 2025-07-09 | Pusplata 1 | 37.504 | 6.2507 | TB401 | 25/10 | Complete
2025-07-05 | 2025-07-10 | Arawali Infra 1 | 37.504 | 6.2507 | TB401 | 2/8 | Complete
2025-07-05 | 2025-07-11 | Pusplata 5 | 37.504 | 5.3577 | TB401 | 21/3 | Complete
2025-07-08 | 2025-07-11 | Poonam | 37.504 | 9.376 | TB401 | 21/6 | Complete
2025-07-05 | 2025-07-11 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401 | 15/5 | Complete
2025-07-04 | 2025-07-12 | Rahul Kumar | 37.504 | 4.1671 | TB401 | 28/9 | Complete
2025-07-07 | 2025-07-12 | Pusplata 4 | 47.148 | 7.858 | TB401 | 25/7 | Complete
2025-07-10 | 2025-07-13 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/3 | Complete
2025-07-09 | 2025-07-13 | Satyam Trivedi | 37.504 | 7.5008 | TB401 | 30/2 | Complete
2025-07-06 | 2025-07-13 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/7 | Complete
2025-07-03 | 2025-07-13 | Pusplata 7 | 38.847 | 3.5315 | TB401 | 22/3 | Complete
2025-07-06 | 2025-07-13 | Jwala Singh 2 | 57.597 | 7.1996 | TB401 | 28/0 | Complete
2025-07-09 | 2025-07-14 | Satyam Nitish | 47.148 | 7.858 | TB401 | 33/7 | Complete
2025-06-18 | 2025-07-14 | Anil Kumar Ramayan Departmental | 86.129 | 3.19 | TB401 | 1A/0 | Complete
2025-07-10 | 2025-07-15 | Pusplata 1 | 45.413 | 7.5688 | TB401 | 25/9 | Complete
2025-07-11 | 2025-07-15 | Jwala Singh 3 | 38.847 | 7.7694 | TB401 | 8/11 | Complete
2025-07-12 | 2025-07-16 | Poonam | 57.597 | 11.5194 | TB401 | 21/7 | Complete
2025-07-08 | 2025-07-16 | Arawali Infra 2 | 38.847 | 4.3163 | TB401 | 14/1 | Complete
2025-07-10 | 2025-07-17 | Gourishankar | 45.413 | 5.6766 | TB401 | 29/3 | Complete
2025-07-09 | 2025-07-17 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/7 | Complete
2025-07-15 | 2025-07-18 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/4 | Complete
2025-07-13 | 2025-07-18 | Pusplata 4 | 38.847 | 6.4745 | TB401 | 25/1 | Complete
2025-07-14 | 2025-07-19 | Jwala Singh 2 | 45.413 | 7.5688 | TB401 | 28/1 | Complete
2025-07-13 | 2025-07-19 | Priyanka Devi Sudheer | 37.504 | 5.3577 | TB401 | 15/8 | Complete
2025-07-11 | 2025-07-20 | Vinay Const | 38.847 | 3.8847 | TB401 | 34/1 | Complete
2025-07-12 | 2025-07-20 | Pusplata 5 | 47.148 | 5.2387 | TB401 | 21/4 | Complete
2025-07-14 | 2025-07-21 | Pusplata 2 | 47.148 | 5.8935 | TB401 | 23/8 | Complete
2025-07-17 | 2025-07-21 | Poonam | 37.504 | 7.5008 | TB401 | 21/8 | Complete
2025-07-14 | 2025-07-22 | Satyam Trivedi Nitish | 38.847 | 4.3163 | TB401 | 30/1 | Complete
2025-07-13 | 2025-07-22 | Rahul Kumar | 45.413 | 4.5413 | TB401 | 29/1 | Complete
2025-07-19 | 2025-07-22 | Pusplata 4 | 37.504 | 9.376 | TB401 | 25/3 | Complete
2025-07-14 | 2025-07-22 | Pusplata 7 | 38.847 | 4.3163 | TB401 | 22/4 | Complete
2025-07-10 | 2025-07-23 | Vinay Const 2 | 38.847 | 2.7748 | TB401 | 33/8 | Complete
2025-07-15 | 2025-07-23 | Satyam Nitish | 67.873 | 7.5414 | TB401 | 34/0 | Complete
2025-07-17 | 2025-07-23 | Pusplata 3 | 57.597 | 8.2281 | TB401 | 24/0 | Complete
2025-07-16 | 2025-07-23 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 26/0 | Complete
2025-07-18 | 2025-07-24 | Gourishankar | 38.847 | 5.5496 | TB401 | 29/4 | Complete
2025-07-18 | 2025-07-24 | Arawali Infra 2 | 66.381 | 9.483 | TB401 | 14/0 | Complete
2025-06-29 | 2025-07-24 | Anjani Enterprises | 45.413 | 1.7467 | TB401 | 11/4 | Complete
2025-07-19 | 2025-07-24 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/5 | Complete
2025-07-10 | 2025-07-26 | Satyam Mondal | 94.2225 | 5.5425 | TB401 | 34/5 | Complete
2025-07-22 | 2025-07-26 | Pusplata 2 | 38.847 | 7.7694 | TB401 | 23/10 | Complete
2025-07-24 | 2025-07-26 | Pusplata 4 | 37.504 | 12.5013 | TB401 | 23/3 | Complete
2025-07-18 | 2025-07-26 | Pusplata 6 | 45.413 | 5.0459 | TB401 | 22/9 | Complete
2025-07-12 | 2025-07-27 | Satyam Santosh | 38.847 | 2.4279 | TB401 | 26/2 | Complete
2025-07-23 | 2025-07-27 | Pusplata 7 | 38.847 | 7.7694 | TB401 | 22/5 | Complete
2025-07-22 | 2025-07-27 | Pusplata 5 | 38.847 | 6.4745 | TB401 | 21/5 | Complete
2025-07-22 | 2025-07-28 | Priyanka Devi Sudheer | 38.847 | 5.5496 | TB401 | 18/1 | Complete
2025-07-24 | 2025-07-29 | Rahul Kumar | 38.847 | 6.4745 | TB401 | 28/8 | Complete
2025-07-27 | 2025-07-30 | Pusplata 3 | 38.847 | 9.7118 | TB401 | 28/2 | Complete
2025-07-25 | 2025-07-30 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/4 | Complete
2025-07-10 | 2025-07-30 | Pusplata 3 Jwala | 47.148 | 2.2451 | TB401 | 25/8 | Complete
2025-07-25 | 2025-07-30 | Pusplata 1 | 38.847 | 6.4745 | TB401 | 26/1 | Complete
2025-07-24 | 2025-07-30 | Priyanka Devi Sudheer 2 | 38.847 | 5.5496 | TB401 | 17/4 | Complete
2025-07-16 | 2025-07-30 | Jwala Singh 3 | 129.11 | 8.6073 | TB401 | 10/0 | Complete
2025-07-24 | 2025-07-31 | Vinay Const | 47.184 | 5.898 | TB401 | 34/3 | Complete
2025-07-25 | 2025-07-31 | Gourishankar | 57.597 | 8.2281 | TB401 | 29/0 | Complete
2025-07-27 | 2025-07-31 | Pusplata 2 | 45.413 | 9.0826 | TB401 | 23/11 | Complete
2025-07-27 | 2025-07-31 | Pusplata 4 | 37.504 | 7.5008 | TB401 | 23/1 | Complete
2025-07-27 | 2025-07-31 | Pusplata 6 | 38.847 | 7.7694 | TB401 | 23/4 | Complete
2025-08-30 | 2025-07-31 | Priyanka Devi Sudheer | 38.847 |  | TB401 | 18/2 | Complete
2025-06-25 | 2025-07-31 | Anil Kumar Departmental Ramayan | 86.129 | 2.3278 | TB401 | 1/0 | Complete
2025-07-11 | 2025-07-31 | Usha Tower | 38.847 | 1.8499 | TB401 | 2/5 | Cross arm
2025-07-30 | 2025-07-31 | Satyam Vijay | 37.504 | 18.752 | TB401 | 27/3 | Complete
2025-07-28 | 2025-07-31 | Poonam | 37.504 | 9.376 | TB401 | 22/2 | Complete
|  | Nan |  |  | TB401
2025-07-31 | 2025-08-04 | Pusplata 3 | 37.504 | 7.5008 | TB401 | 28/3 | Complete
2025-08-01 | 2025-08-04 | Poonam | 37.504 | 9.376 | TB401 | 22/1 | Complete
2025-07-31 | 2025-08-05 | Jwala Singh 3 | 37.504 | 6.2507 | TB401 | 8/12 | Complete
2025-08-01 | 2025-08-05 | Pusplata 4 | 37.504 | 7.5008 | TB401 | 25/4 | Complete
2025-08-01 | 2025-08-06 | Pusplata Deepak | 37.504 | 6.2507 | TB401 | 23/5 | Complete
2025-08-04 | 2025-08-07 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/2 | Complete
2025-08-01 | 2025-08-08 | Pusplata 1 | 57.597 | 7.1996 | TB401 | 23/0 | Complete
2025-07-31 | 2025-08-09 | Rahul Kumar | 66.381 | 6.6381 | TB401 | 30/0 | Complete
2025-08-03 | 2025-08-09 | Gourishankar | 47.184 | 6.7406 | TB401 | 31/1 | Complete
2025-08-04 | 2025-08-09 | Priyanka Devi Sudheer | 37.504 | 6.2507 | TB401 | 16/6 | Complete
2025-08-04 | 2025-08-09 | Pusplata 6 | 37.504 | 6.2507 | TB401 | 23/2 | Complete
2025-08-05 | 2025-08-10 | Pusplata Santosh | 47.184 | 7.864 | TB401 | 28/4 | Complete
2025-08-06 | 2025-08-11 | Pusplata Ashok | 45.413 | 7.5688 | TB401 | 21/14 | Complete
2025-08-06 | 2025-08-11 | Satyam Vijay | 37.504 | 6.2507 | TB401 | 27/2 | Complete
2025-07-17 | 2025-08-12 | Bhairo Mahto Departmental Arawali | 100.96 | 3.7393 | TB401 | 4/0 | Complete
2025-08-09 | 2025-08-12 | Satyam Manish | 37.504 | 9.376 | TB401 | 33/1 | Complete
| 2025-08-13 | Satyam Santosh | 37.504 |  | TB401 | 26/3 | Complete
2025-08-05 | 2025-08-13 | Priyanka Devi 2 | 38.847 | 4.3163 | TB401 | 17/5 | Complete
2025-08-01 | 2025-08-14 | Pusplata Dharamveer | 47.184 | 3.3703 | TB401 | 21/12 | Complete
2025-08-27 | 2025-08-16 | Bhairo Mahto Departmental Bharo | 37.504 |  | TB401 | 4/1 | Complete
2025-08-04 | 2025-08-18 | Arawali Infra 2 | 38.847 | 2.5898 | TB401 | 16/1 | Complete
2025-08-16 | 2025-08-19 | Pusplata Deepak | 38.847 | 9.7118 | TB401 | 24/1 | Complete
2025-08-14 | 2025-08-19 | Priyanka Devi 2 | 38.847 | 6.4745 | TB401 | 18/8 | Complete
2025-08-14 | 2025-08-19 | Pusplata Ashok | 37.504 | 6.2507 | TB401 | 4/4 | Complete
2025-08-11 | 2025-08-22 | Priyanka Devi Sudheer | 57.597 | 4.7998 | TB401 | 18/0 | Complete
2025-08-13 | 2025-08-22 | Arawali | 45.413 | 4.5413 | TB401 | 2/7 | Complete
2025-08-19 | 2025-08-22 | Satyam Manish | 37.504 | 9.376 | TB401 | 32/7 | Complete
2025-08-17 | 2025-08-24 | Sital Singh | 37.504 | 4.688 | TB401 | 2/3 | Complete
2025-08-21 | 2025-08-24 | Pusplata Deepak | 37.504 | 9.376 | TB401 | 25/2 | Complete
2025-08-10 | 2025-08-25 | Pusplata Rajaram | 89.909 | 5.6193 | TB401 | 20/0 | Complete
2025-08-10 | 2025-08-25 | Pusplata Praful | 89.909 | 5.6193 | TB401 | 21/0 | Complete
2025-08-21 | 2025-08-25 | Priyanka Devi 2 | 37.504 | 7.5008 | TB401 | 18/9 | Complete
2025-08-14 | 2025-08-26 | Pusplata Ramchander | 81.494 | 6.2688 | TB401 | 22/0 | Complete
2025-08-12 | 2025-08-26 | Satyam Vijay | 70.701 | 4.7134 | TB401 | 27/1 | Complete
2025-08-23 | 2025-08-27 | Satyam Manish |  |  | TB401 | 32/8 | Complete
2025-08-14 | 2025-08-27 | Priyanka Devi | 66.381 | 4.7415 | TB401 | 2/0 | Complete
2025-04-24 | 2025-08-28 | Pusplata Ashok | 37.504 | 0.29531 | TB401 | 4/3 | Complete
2025-08-21 | 2025-08-28 | Jawala Singh | 37.504 | 4.688 | TB401 | 8/4 | Complete
2025-08-22 | 2025-08-29 | Usha Tower | 45.413 | 5.6766 | TB401 | 2/6 | Complete
2025-08-21 | 2025-08-30 | Sital Singh 2 | 38.847 | 3.8847 | TB401 | 2/4 | Complete
2025-08-24 | 2025-08-30 | Priyanka Devi Sudheer | 66.381 | 9.483 | TB401 | 19/0 | Complete
2025-08-25 | 2025-08-31 | Jawala Singh Suraj | 37.504 | 5.3577 | TB401 | 23/9 | Complete
2025-08-27 | 2025-08-31 | Satyam Vijay | 38.847 | 7.7694 | TB401 | 26/7 | Complete
2025-08-25 | 2025-08-31 | Sital Singh | 37.504 | 5.3577 | TB401 | 2/1 | Complete
|  | Nan |  |  | TB401
2025-08-25 | 2025-09-02 | Rahul Kumar | 47.184 | 5.2427 | TB401 | 28/5 | Complete
2025-08-27 | 2025-09-03 | Sanjeev Kumar | 37.504 | 4.688 | TB401 | 26/6 | Complete
2025-08-31 | 2025-09-05 | Usha Tower | 38.847 | 6.4745 | TB401 | 6/2 | Complete
2025-08-30 | 2025-09-08 | Priyanka Devi | 38.847 | 3.8847 | TB401 | 2/2 | Complete
2025-09-05 | 2025-09-09 | Rahul Kumar | 37.504 | 7.5008 | TB401 | 28/7 | Complete
2025-09-02 | 2025-09-10 | Bhairo Mahto | 38.847 | 4.3163 | TB401 | 8/2 | Complete
2025-09-05 | 2025-09-10 | Pusplata Pankaj | 37.504 | 6.2507 | TB401 | 14/3 | Complete
2025-09-06 | 2025-09-11 | Jwala Singh | 38.847 | 6.4745 | TB401 | 8/5 | Complete
2025-09-04 | 2025-09-13 | Pusplata Ashok | 70.701 | 7.0701 | TB401 | 6/0 | Complete
2025-09-05 | 2025-09-15 | Sanjeev Kumar | 47.184 | 4.2895 | TB401 | 26/5 | Complete
2025-09-02 | 2025-09-16 | Pusplata Deepak | 37.504 | 2.5003 | TB401 | 21/13 | Complete
2025-09-11 | 2025-09-20 | Sital Singh 1 | 38.847 | 3.8847 | TB401 | 10/17 | Complete
2025-09-15 | 2025-09-23 | Sital Singh 2 | 37.504 | 4.1671 | TB401 | 6/1 | Complete
2025-09-16 |  | Sanjeev Kumar | 47.184 |  | TB401 | 26/4 | Complete
2025-07-30 |  | Anjani Power | 38.847 |  | TB401 | 8/1 | 1st Section
2025-08-11 |  | Jwala Singh 3 Bhairo Mahto | 129.11 |  | TB401 | 9/0 | 2nd Section wip (ROW) work start with police proctution on date 27.-09.25
2025-09-26 |  | Sanjeev Kumar | 81.945 |  | TB401 | 27/0 | 1st Section
2025-09-08 |  | Priyanka Devi Santosh | 38.847 |  | TB401 | 18/4 | 1st Section (ROW since 10.09.25)
2025-09-21 | 2025-09-29 | Sital Singh 1 | 38.847 | 4.3163 | TB401 | 10/16 | Complete
|  | Sital Singh 1 |  |  | TB401 | 10/15 | Material Shifting
2025-09-23 |  | Priyanka Devi Subodh | 38.847 |  | TB401 | 10/1 | Bottom complete
|  | Bhairo Mahto | 57.597 |  | TB401 | 8/0 | Material Shifting
|  | Ganesh Sinha |  |  | TB401 | 28/6 | 1st Section
| 2025-09-19 | Dhaneshwar Mahto | 171.017 |  | TA325 | 101/0 | Completed.
| 2025-11-09 | Dhaneshwar Mahto | 156.901 |  | TA325 | 102/0
| 2025-08-13 | Dhaneshwar Mahto | 172.151 |  | TA325 | 104/0 | Completed
2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed.
2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed.
2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed.
2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed.
2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed.
2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed.
2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed.
2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed.
2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed.
2024-09-10 | 2024-09-27 | Dhaneshwar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed.
2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed.
2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed.
2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed.
2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed.
2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed.
2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed.
2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed.
2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325 | 119/2 | Completed
2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed.
2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed.
2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed.
2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed.
2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed.
2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed.
2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed.
2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed.
2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed.
2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed.
2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed.
2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed.
2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed.
2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed.
2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed.
2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed.
2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed.
2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed.
2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed.
2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325 | 133/4 | Completed
2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-13 | 2024-03-13 | Lalan Mahto | 37.73 | 37.73 | TA325 | 133A/1 | Completed
2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed.
2024-12-04 | 2024-12-20 | Dhaneshwar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed.
2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed.
2025-01-06 | 2025-01-11 | Surender Mahto | 44.728 | 7.4547 | TA325 | 135/1 | Completed.
2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed.
2024-12-27 | 2025-01-04 | Dhaneshwar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed.
2024-10-08 | 2024-11-03 | Dhaneshwar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed.
2024-11-05 | 2024-11-13 | Dhaneshwar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed.
2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2025-01-13 | 2025-01-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed.
2024-12-21 | 2024-12-26 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed.
2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed.
2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed.
2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed.
2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2025-02-03 | 2025-02-07 | Dhaneshwar Mahto | 39.459 | 7.8918 | TA325 | 137/5 | Completed.
2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed.
2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed.
2025-01-27 | 2025-01-29 | Dhaneshwar Mahto | 44.728 | 14.9093 | TA325 | 137A/1 | Completed.
2025-01-30 | 2025-02-02 | Dhaneshwar Mahto | 37.73 | 9.4325 | TA325 | 137A/2 | Completed.
2024-11-20 | 2024-11-28 | Dhaneshwar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed.
2024-11-29 | 2024-12-03 | Dhaneshwar Mahto | 36.045 | 7.209 | TA325 | 137A/4 | Completed.
2024-11-14 | 2024-11-20 | Dhaneshwar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed.
2025-01-20 | 2025-01-24 | Dhaneshwar Mahto | 46.623 | 9.3246 | TA325 | 137A/6 | Completed.
2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed.
2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed.
2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed.
2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed.
2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed.
2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325 | 139/2 | Completed.
2025-02-09 | 2025-02-14 | Dhaneshwar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed.
2025-02-16 | 2025-02-22 | Dhaneshwar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed.
2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed.
2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed.
2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed.
2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed.
2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed.
2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed.
2025-02-24 | 2025-03-02 | Dhaneshwar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed.
2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed.
2025-03-04 | 2025-03-17 | Dhaneshwar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed.
2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed.
2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed.
2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed.
2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed.
2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/2 | Completed
2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325 | 144/3 | Completed
2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/4 | Completed
2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed.
2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed.
2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed.
2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed.
2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed.
2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed.
2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed.
2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed.
2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed.
2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed.
2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed.
2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed.
2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed.
2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed.
2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed.
2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed.
2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed.
2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed.
2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed.
2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed.
2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed.
2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed.
2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325 | 148/5 | Completed.
2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed.
2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed.
2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed.
2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed.
2025-03-22 | 2025-03-31 | Dhaneshwar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed.
2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed.
2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325 | 150/2 | Completed.
2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed.
2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed.
2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed.
2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed.
2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed.
2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed.
2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed.
2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed.
2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325 | 152A/0 | Completed.
| 2025-08-08 | Nan | 141.874 |  | TA325 | 153/0 | Completed.
2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed.
2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed.
2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed.
2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed.
2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed.
2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed.
2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed.
2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed.
2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed.
2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed.
2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed.
2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed.
2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed.
2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed.
2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed.
2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed.
2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed.
2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed.
2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed.
2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed.
2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed.
2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed.
2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed.
2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed.
2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed.
2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed.
2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed.
2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed.
2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed.
2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed.
2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed.
2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed.
2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed.
2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed.
2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed.
2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed.
2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed.
2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed.
2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed.
2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed.
2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed.
2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed.
2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed.
2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed.
2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed.
2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed.
2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed.
2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed.
2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed.
2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed.
2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed.
2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed.
2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed.
| 2025-07-20 | Nan | 37.73 |  | TA325 | 175/2 | Completed.
2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed.
2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed.
2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed.
2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed.
2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed.
2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed.
2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed.
2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed.
2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed.
2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed.
2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed.
2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed.
2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed.
2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325 | 187/3 | Completed.
2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed.
2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed.
2025-04-05 | 2025-04-11 | Dhaneshwar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed.
2025-04-18 | 2025-05-06 | Dhaneshwar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed.
| 2025-08-26 | Modina India | 122.808 |  | TA325 | 191/0 | Completed.
2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed.
2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325 | 191/2 | Completed.
2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed.
2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed.
2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed.
2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed.
2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed.
2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed.
2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed.
2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed.
2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed.
2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed.
2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed.
2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed.
2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed.
2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed.
2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed.
2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed.
2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed.
2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed.
2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed.
2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed.
2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed.
2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed.
2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed.
2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed.
2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed.
2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed.
2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed.
2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed.
2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed.
2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed.
2025-05-13 | 2025-05-18 | Dhaneshwar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed.
2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed.
| 2025-10-05 | Modina India 3 Pgcil | 37.73 |  | TA325 | 229/3
| 2025-10-05 | Muni Bibi 2 | 37.73 |  | TA325 | 237/1
| 2025-10-15 | Rupesh | 89.146 |  | TA325 | 237/0
| 2025-10-08 | Dildar Electrical 2 Pgcil | 39.459 |  | TA325 | 237/6
2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed.
2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed.
2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed.
2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed.
2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed.
2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed.
2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed.
2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed.
2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed.
2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed.
2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed.
2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed.
2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed.
2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed.
2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed.
2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed.
2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed.
2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed.
2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed.
2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed.
2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed.
2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed.
2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed.
2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed.
2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed.
2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed.
2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed.
2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed.
2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed.
2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed.
2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed.
2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed.
2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed.
2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed.
2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed.
2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed.
2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed.
2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed.
2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed.
2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed.
2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed.
2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed.
2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed.
2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed.
2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed.
2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed.
2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed.
2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed.
2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed.
2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed.
2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed.
2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed.
2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed.
2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed.
2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325 | 271/1 | Completed.
2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed.
2035-03-04 | 2025-03-11 | Thanu Mahto | 36.045 |  | TA325 | 271/3 | Completed.
2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed.
2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed.
2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed.
2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed.
2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed.
2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed.
2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed.
2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed.
2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed.
2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed.
2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed.
2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed.
2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed.
2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325 | 272A/3 | Completed.
2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325 | 272A/4 | Completed.
2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed.
2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325 | 272A/6 | Completed.
2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325 | 272A/7 | Completed.
2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed.
2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325 | 273/2 | Completed.
2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed.
2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed.
|  | Nan | 20932.97 |  | TA325
|  | Nan |  |  | TA325
|  | Nan |  |  | TA325 |  | Completed Erection
|  | Nan | 40 |  | TA325 |  | 32
|  | Nan | 146 |  | TA325 |  | 129
|  | Nan | 40 |  | TA325 |  | 33
|  | Nan | 30 |  | TA325 |  | 28
|  | Nan | 11 |  | TA325 |  | 9
|  | Nan | 267 |  | TA325 |  | 231
|  | Nan | 25 |  | TA325
|  | Nan | 6 |  | TA325
|  | Nan | 8 |  | TA325
|  | Nan | 9 |  | TA325
|  | Nan | 6 |  | TA325
|  | Nan | 1 |  | TA325
|  | Nan | 55 |  | TA325
|  | Nan | 26 |  | TA325
|  | Nan | 3 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 7 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 3 |  | TA325
|  | Nan | 47 |  | TA325
|  | Nan | 16 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 3 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 6 |  | TA325
|  | Nan | 5 |  | TA325
|  | Nan | 2 |  | TA325
|  | Nan | 40 |  | TA325
|  | Nan | 19 |  | TA325
|  | Nan | 8 |  | TA325
|  | Nan | 11 |  | TA325
|  | Nan | 7 |  | TA325
|  | Nan | 7 |  | TA325
|  | Nan | 15 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 2 |  | TA325
|  | Nan | 73 |  | TA325
|  | Nan | 1 |  | TA325
|  | Nan | 1 |  | TA325
|  | Nan | 483 |  | TA325
|  | Nan |  |  | TA408
|  | Nan |  |  | TA408
|  | Nan |  |  | TA408
2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TA408 | 60/7 | Completed
2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TA408 | 59/13 | Completed
2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TA408 | 63/6 | Completed
2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/5 | Completed
2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TA408 | 59/14 | Completed
2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TA408 | 60/8 | Completed
2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TA408 | 63/7 | Completed
2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/6 | Completed
2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TA408 | 59/12 | Completed
2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TA408 | 63/8 | Completed
2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TA408 | 60/10 | Completed
2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TA408 | 62/5 | Completed
2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 59/7 | Completed
2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 59/10 | Completed
2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TA408 | 64/1 | Completed
2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TA408 | 60/11 | Completed
2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 62/4 | Completed
2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 59/9 | Completed
2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TA408 | 62/3 | Completed
2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TA408 | 59/8 | Completed
2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/4 | Completed
2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TA408 | 60/6 | Completed
2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 62/2 | Completed
2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/5 | Completed
2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/2 | Completed
2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 62/7 | Completed
2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TA408 | 59/16 | Completed
2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 65/4 | Completed
2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TA408 | 62/8 | Completed
2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 62/9 | Completed
2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 65/3 | Completed
2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TA408 | 60/5 | Completed
2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 62/10 | Completed
2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 65/5 | Completed
2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 61/6 | Completed
2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TA408 | 60/4 | Completed
2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/6 | Completed
2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TA408 | 64/6 | Completed
2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 61/7 | Completed
2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/7 | Completed
2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TA408 | 60/3 | Completed
2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 65/9 | Completed
2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TA408 | 64/8 | Completed
2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 65/11 | Completed
2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TA408 | 60/2 | Completed
2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TA408 | 63/5 | Completed
2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/9 | Completed
2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 67/1 | Completed
2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TA408 | 61/0 | Completed
2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TA408 | 63/4 | Completed
2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TA408 | 67/2 | Completed
2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TA408 | 63/3 | Completed
2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 64/10 | Completed
2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TA408 | 64/2 | Completed
2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TA408 | 61/2 | Completed
2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TA408 | 63/2 | Completed
2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TA408 | 60/1 | Completed
2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TA408 | 64/3 | Completed
2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TA408 | 65/0 | Completed
2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TA408 | 63/1 | Completed
2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TA408 | 61/1 | Completed
2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TA408 | 65/1 | Completed
2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TA408 | 62/11 | Completed
2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TA408 | 64/0 | Completed
2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 60/9 | Completed
2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TA408 | 61/3 | Completed
2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TA408 | 63/0 | Completed
2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TA408 | 61/4 | Completed
2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TA408 | 60/0 | Completed
2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TA408 | 61/10 | Completed
2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 61/5 | Completed
2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TA408 | 61/9 | Completed
2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TA408 | 59/15 | Completed
2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TA408 | 61/8 | Completed
2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TA408 | 55/3 | Completed
2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TA408 | 57/3 | Completed
2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TA408 | 55/4 | Completed
2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TA408 | 57/4 | Completed
2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TA408 | 62/1 | Completed
2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TA408 | 62/6 | Completed
2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TA408 | 57/6 | Completed
2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TA408 | 57/5 | Completed
2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TA408 | 10/18 | Completed
2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TA408 | 10/3 | Completed
2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 10/17 | Completed
2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TA408 | 62/0 | Completed
2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TA408 | 50/9 | Completed
2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TA408 | 16/3 | Completed
2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TA408 | 10/19 | Completed
2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TA408 | 52/5 | Completed
2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TA408 | 50/10 | Completed
2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/2 | Completed
2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TA408 | 10/20 | Completed
2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TA408 | 48/1 | Completed
2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TA408 | 15/1 | Completed
2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TA408 | 51/1 | Completed
2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/4 | Completed
2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TA408 | 10/6 | Completed
2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/6 | Completed
2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 57/7 | Completed
2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TA408 | 16/4 | Completed
2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TA408 | 14A/1 | Completed
2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TA408 | 51/2 | Completed
2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TA408 | 10/14 | Completed
2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TA408 | 11A/2 | Completed
2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TA408 | 50/0 | Completed
2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408 | 52/7 | Completed
2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TA408 | 10/9 | Completed
2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TA408 | 18/1 | Completed
2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TA408 | 10/21 | Completed
2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TA408 | 17/1 | Completed
2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TA408 | 50/1 | Completed
2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TA408 | 50/8 | Completed
2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TA408 | 10/4 | Completed
2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TA408 | 50/3 | Completed
2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TA408 | 17/2 | Completed
2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TA408 | 48/0 | Completed
2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 52/8 | Completed
2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TA408 | 73/2 | Completed
2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TA408 | 10/8 | Completed
2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/2 | Completed
2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 64/11 | Completed
2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TA408 | 16/2 | Completed
2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TA408 | 19/0 | Completed
2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TA408 | 59/11 | Completed
2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TA408 | 16/0 | Completed
2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TA408 | 17/3 | Completed
2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 73/1 | Completed
2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/4 | Completed
2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TA408 | 55/6 | Completed
2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TA408 | 11A/0 | Completed
2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TA408 | 59/3 | Completed
2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 50/7 | Completed
2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TA408 | 10/11 | Completed
2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TA408 | 11A/1 | Completed
2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TA408 | 16/5 | Completed
2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TA408 | 16/1 | Completed
2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TA408 | 59/4 | Completed
2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TA408 | 50/6 | Completed
2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TA408 | 55/5 | Completed
2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/9 | Completed
2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TA408 | 17/0 | Completed
2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 49/7 | Completed
2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 73/8 | Completed
2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TA408 | 11/5 | Completed
2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TA408 | 13/2 | Completed
2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TA408 | 43/9 | Completed
2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 49/6 | Completed
2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TA408 | 73/6 | Completed
2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TA408 | 47/10 | Completed
2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 49/4 | Completed
2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TA408 | 59/2 | Completed
2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TA408 | 52/10 | Completed
2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TA408 | 43/8 | Completed
2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TA408 | 49/5 | Completed
2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TA408 | 17/5 | Completed
2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TA408 | 11A/9 | Completed
2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 49/2 | Completed
2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TA408 | 72/3 | Completed
2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TA408 | 59/1 | Completed
2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TA408 | 52/9 | Completed
2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TA408 | 49/3 | Completed
2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TA408 | 11A/7 | Completed
2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TA408 | 11A/3 | Completed
2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 49/1 | Completed
2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TA408 | 10/12 | Completed
2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/3 | Completed
2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TA408 | 11A/6 | Completed
2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TA408 | 59/0 | Completed
2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/8 | Completed
2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TA408 | 11A/5 | Completed
2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TA408 | 65/7 | Completed
2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TA408 | 43/0 | Completed
2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TA408 | 73/0 | Completed
2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TA408 | 53/8 | Completed
2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TA408 | 74/0 | Completed
2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/4 | Completed
2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TA408 | 43/1 | Completed
2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TA408 | 43/7 | Completed
2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TA408 | 53/7 | Completed
2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 73/5 | Completed
2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TA408 | 73/7 | Completed
2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TA408 | 72/0 | Completed
2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TA408 | 43/6 | Completed
2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TA408 | 66/0 | Completed
2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TA408 | 53/6 | Completed
2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 72/1 | Completed
2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TA408 | 65/10 | Completed
2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TA408 | 72/2 | Completed
2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TA408 | 51/0 | Completed
2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TA408 | 1A/1 | Completed
2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TA408 | 71/8 | Completed
2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TA408 | 52/0 | Completed
2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TA408 | 49/0 | Completed
2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/7 | Completed
2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TA408 | 1A/2 | Completed
2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TA408 | 71/6 | Completed
2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TA408 | 50/5 | Completed
2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/5 | Completed
2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TA408 | 1A/3 | Completed
2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/4 | Completed
2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TA408 | 53/5 | Completed
2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TA408 | 71/3 | Completed
2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TA408 | 58/0 | Completed
2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 71/2 | Completed
2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TA408 | 70/3 | Completed
2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TA408 | 53/4 | Completed
2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 71/1 | Completed
2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TA408 | 53/3 | Completed
2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TA408 | 71/0 | Completed
2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TA408 | 70/5 | Completed
2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TA408 | 53/2 | Completed
2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 70/11 | Completed
2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TA408 | 47/9 | Completed
2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TA408 | 70/10 | Completed
2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TA408 | 47/8 | Completed
2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TA408 | 70/9 | Completed
2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TA408 | 53/1 | Completed
2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TA408 | 68/0 | Completed
2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TA408 | 53/0 | Completed
2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TA408 | 70/4 | Completed
2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TA408 | 67/0 | Completed
|  | Nan |  |  | TA408
2025-05-10 |  | Bhairo Mahto |  |  | TA408
2025-05-19 |  | Sonakshi Manish 2 |  |  | TA408
2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421 | 11/1 | Completed
2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
| 2025-07-12 | Subash | 33.38 |  | TA421 | 9/10 | Completed
2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
| 2025-07-13 | Naziruddin | 71.706 |  | TA421 | 14/0 | Completed
2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421 | 4/7 | Completed
2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-13 |  | Praveen | 36.37 |  | TA421 | 39/7 | 3rd Section under Progress
2025-09-21 |  | Yadhav | 37.931 |  | TA421 | 43/4 | 1st Section under Progress
2025-09-27 |  | Hassan | 36.37 |  | TA421 | 39/2 | Ground Assembling under Progress
2025-09-28 |  | Khatun | 31.99 |  | TA421 | 4/18 | Material Shifting Done
2025-10-01 |  | Subash |  |  | TA421 | 1/0 | Material Shifting under Progress
2025-10-01 |  | D K Verma |  |  | TA421 | 43/5 | Material Shifting Done

## Data Issues
Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name | Location No. | Status | Issues
2025-08-26 |  | Savitha | 28 |  | TA418 | 60/2 | 1st section completed- material and T&P stucked at location.ROW | Missing start/end date (not expanded)
2025-09-05 |  | Savitha | 45 |  | TA418 | 56/0 | top CrossArm section work under progress. | Missing start/end date (not expanded)
2025-09-08 |  | Subhash | 33 |  | TA418 | 46/11 | (ROW) | Missing start/end date (not expanded)
2025-09-09 |  | M S Mdpl | 33.3 |  | TA418 | 45/3 | Middle Crossarm section work under progress. | Missing start/end date (not expanded)
2025-09-22 |  | M S Tofit | 27 |  | TA418 | 33/1 | Bottom crossarm work under progress. | Missing start/end date (not expanded)
2025-09-25 |  | Subhash | 50 |  | TA418 | 44/0 | Middle section work under progress | Missing start/end date (not expanded)
2025-09-28 |  | Kec 02 Barkat Ali | 27 |  | TA418 | 54/1 | 1st section work under progress. | Missing start/end date (not expanded)
2025-09-29 |  | M S Mdpl | 60 |  | TA418 | 54/0 | Material shifting work under progress. | Missing start/end date (not expanded)
2024-12-29 | 2024-01-05 | Gang 01 Sanjay | 27.96 |  | TA418 | 33/10 | COMPLETED | Non-positive duration (Start > End or 0) (not expanded)
2024-12-30 | 2024-01-07 | Gang 02 Sanjay | 27.96 |  | TA418 | 40/4 | COMPLETED | Non-positive duration (Start > End or 0) (not expanded)
2025-07-24 | 2025-08-06 | Gang 02 Sanjay Kec 02 Barkat Ali | 29 | 2.0714 | TA418 | 41/5 | COMPLETED | Single-occurrence gang (not expanded)
2025-09-12 | 2025-09-22 | M S Tofit | 33.3 | 3.0273 | TA418 | 33/2 | COMPLETED | Single-occurrence gang (not expanded)
2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED | Single-occurrence gang (not expanded)
2025-02-02 |  | Rudra Construction | 46.0492 |  | TA416 | 33/11 | Completed | Missing start/end date (not expanded)
2025-02-06 |  | Dewi Construction | 64.482 |  | TA416 | 21/0 | Completed | Missing start/end date (not expanded)
2025-02-07 |  | Reeta Bharti | 43.7758 |  | TA416 | 20/2 | Completed | Missing start/end date (not expanded)
2025-02-08 |  | Amar Singh | 46.0492 |  | TA416 | 35/9 | Completed | Missing start/end date (not expanded)
|  | Reeta Bharti |  |  | TA416 | 4/10 | Completed | Missing start/end date (not expanded)
|  | Dewi Construction |  |  | TA416 | 33/3 | Completed | Missing start/end date (not expanded)
|  | Pankaj |  |  | TA416 | 7/0 | Completed | Missing start/end date (not expanded)
|  | Pinky Dewi |  |  | TA416 | 8/0 | Completed | Missing start/end date (not expanded)
2025-09-08 |  | Ananya | 90.125 |  | TA416 | 47/0 | 3rd section wip | Missing start/end date (not expanded)
2025-08-18 |  | Mk Infra | 42.374 |  | TA416 | 48/1 | 1st section wip | Missing start/end date (not expanded)
2025-08-18 |  | Spotify Pvt Ltd 2 | 53.324 |  | TA416 | 53A/1 | 2nd section wip | Missing start/end date (not expanded)
2025-08-18 |  | Spotify Pvt Ltd 3 | 42.374 |  | TA416 | 56/8 | 3rd section wip | Missing start/end date (not expanded)
2025-08-31 |  | Sainik Ent | 87.01 |  | TA416 | 19/0 | 3rd section Completed | Missing start/end date (not expanded)
2025-08-31 |  | Kangresh 2 | 73.426 |  | TA416 | 64/0 | Bottom section wip | Missing start/end date (not expanded)
2025-08-31 |  | Radha Const | 89.7 |  | TA416 | 2/0 | Cage 1 wip | Missing start/end date (not expanded)
2025-09-04 |  | Gagan |  |  | TA416 | 23/0 | 1st section Completed | Missing start/end date (not expanded)
2025-08-28 |  | Kangresh 1 | 161.355 |  | TA416 | 25/0 | 3rd section wip | Missing start/end date (not expanded)
2025-08-06 |  | Reeta Bharti | 161.355 |  | TA416 | 29/0 | Cage 2 Completed | Missing start/end date (not expanded)
2025-09-08 |  | Punam Kumari |  |  | TA416 | 52/0 | 3rd section wip | Missing start/end date (not expanded)
2025-09-11 |  | Maa Const |  |  | TA416 | 17/0 | leg joint Done | Missing start/end date (not expanded)
2025-10-20 | 2025-01-25 | Asc Heights | 46.0492 |  | TA416 | 31/6 | Completed | Non-positive duration (Start > End or 0) (not expanded)
1935-06-27 | 2025-06-29 | Pinki Dewi | 42.374 | 0.0012889 | TA416 | 21/1 | Completed | Start before 2021-01-01 (not expanded)
2025-03-24 | 2025-03-31 | Ananya Traders | 46.0492 | 5.7561 | TA416 | 39/3 | Completed | Single-occurrence gang (not expanded)
2025-03-31 | 2025-04-11 | Anand Const | 46.0492 | 3.8374 | TA416 | 4/1 | Completed | Single-occurrence gang (not expanded)
2025-04-08 | 2025-04-12 | Pinky Dewi 1 | 42.3742 | 8.4748 | TA416 | 8B/2 | Completed | Single-occurrence gang (not expanded)
2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | Completed | Single-occurrence gang (not expanded)
2025-06-02 | 2025-06-12 | Devine | 42.374 | 3.8522 | TA416 | 53A/5 | Completed | Single-occurrence gang (not expanded)
2025-08-14 | 2025-08-26 | Kajal Const | 46.049 | 3.5422 | TA416 | 46/2 | Completed | Single-occurrence gang (not expanded)
2025-07-26 | 2025-08-27 | Kangresh 1 | 161.355 | 4.8895 | TA416 | 24/0 | Completed | Single-occurrence gang (not expanded)
2025-08-09 | 2025-08-30 | Radha Const | 78.073 | 3.5488 | TA416 | 1/0 | Completed | Single-occurrence gang (not expanded)
2025-08-04 | 2025-08-30 | Sainik Ent | 75.85 | 2.8093 | TA416 | 18/0 | Completed | Single-occurrence gang (not expanded)
2025-08-02 | 2025-08-30 | Kangresh 2 | 97.229 | 3.3527 | TA416 | 65/0 | Completed | Single-occurrence gang (not expanded)
2025-08-10 | 2025-09-07 | Ananya | 118.43 | 4.0838 | TA416 | 43/0 | Completed | Single-occurrence gang (not expanded)
2025-08-24 | 2025-09-14 | Gouri Shankar | 97.65 | 4.4386 | TA416 | 11/0 | Completed | Single-occurrence gang (not expanded)
|  | Nan | 6152.1898 |  | TA505 |  | 130 | Missing start/end date (not expanded)
2025-09-23 |  | Jhemon Mahato 2 | 85.264 |  | TA505 | 144A/0 | In-Progress | Missing start/end date (not expanded)
2025-09-26 |  | Paramanand 1 | 35.602 |  | TA505 | 160/2 | In-Progress | Missing start/end date (not expanded)
2025-09-26 |  | Pankaj Singh Mp | 36.16 |  | TA505 | 167/4 | In-Progress | Missing start/end date (not expanded)
2025-09-26 |  | Jagannaath Saw Mp | 55.451 |  | TA505 | 160/0 | In-Progress | Missing start/end date (not expanded)
2025-09-30 |  | Toshan Mahato | 36.1598 |  | TA505 | 148/1 | In-Progress | Missing start/end date (not expanded)
2025-09-30 |  | Deglal Mahato Mp | 36.16 |  | TA505 | 169/4 | In-Progress | Missing start/end date (not expanded)
2025-10-01 |  | Jyoti Const | 124.95 |  | TA505 | 112/0 | In-Progress | Missing start/end date (not expanded)
2025-10-01 |  | Shila Devi | 81.828 |  | TA505 | 128/0 | In-Progress | Missing start/end date (not expanded)
2025-10-02 |  | Pankaj Singh Mp | 36.1598 |  | TA505 | 167/2 | In-Progress | Missing start/end date (not expanded)
|  | Nan | 6152.1898 |  | TA505 |  | 130 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed | Single-occurrence gang (not expanded)
2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed | Single-occurrence gang (not expanded)
2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed | Single-occurrence gang (not expanded)
2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed | Single-occurrence gang (not expanded)
2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed | Single-occurrence gang (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
2025-06-26 |  | Arawali Infra 1 | 37.504 |  | TB401 | 2/9 | Complete | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
| 2025-08-13 | Satyam Santosh | 37.504 |  | TB401 | 26/3 | Complete | Missing start/end date (not expanded)
|  | Nan |  |  | TB401 |  |  | Missing start/end date (not expanded)
2025-09-16 |  | Sanjeev Kumar | 47.184 |  | TB401 | 26/4 | Complete | Missing start/end date (not expanded)
2025-07-30 |  | Anjani Power | 38.847 |  | TB401 | 8/1 | 1st Section | Missing start/end date (not expanded)
2025-08-11 |  | Jwala Singh 3 Bhairo Mahto | 129.11 |  | TB401 | 9/0 | 2nd Section wip (ROW) work start with police proctution on date 27.-09.25 | Missing start/end date (not expanded)
2025-09-26 |  | Sanjeev Kumar | 81.945 |  | TB401 | 27/0 | 1st Section | Missing start/end date (not expanded)
2025-09-08 |  | Priyanka Devi Santosh | 38.847 |  | TB401 | 18/4 | 1st Section (ROW since 10.09.25) | Missing start/end date (not expanded)
|  | Sital Singh 1 |  |  | TB401 | 10/15 | Material Shifting | Missing start/end date (not expanded)
2025-09-23 |  | Priyanka Devi Subodh | 38.847 |  | TB401 | 10/1 | Bottom complete | Missing start/end date (not expanded)
|  | Bhairo Mahto | 57.597 |  | TB401 | 8/0 | Material Shifting | Missing start/end date (not expanded)
|  | Ganesh Sinha |  |  | TB401 | 28/6 | 1st Section | Missing start/end date (not expanded)
2025-08-30 | 2025-07-31 | Priyanka Devi Sudheer | 38.847 |  | TB401 | 18/2 | Complete | Non-positive duration (Start > End or 0) (not expanded)
2025-08-27 | 2025-08-16 | Bhairo Mahto Departmental Bharo | 37.504 |  | TB401 | 4/1 | Complete | Non-positive duration (Start > End or 0) (not expanded)
2024-07-12 | 2024-08-04 | Sanjay Mahto | 47.148 | 1.9645 | TB401 | 31/4 |  | Single-occurrence gang (not expanded)
2024-09-10 | 2024-09-26 | Khublal Mahto | 38.847 | 2.2851 | TB401 | 10/14 | Complete | Single-occurrence gang (not expanded)
2025-01-19 | 2025-01-28 | Om Construction | 45.413 | 4.5413 | TB401 | 39/1 | Complete | Single-occurrence gang (not expanded)
2025-04-28 | 2025-05-15 | Annaya Traders | 37.504 | 2.0836 | TB401 | 33/5 | Complete | Single-occurrence gang (not expanded)
2025-05-30 | 2025-06-04 | Pankaj | 37.504 | 6.2507 | TB401 | 24/6 | Complete | Single-occurrence gang (not expanded)
2025-05-30 | 2025-06-19 | Kewat Departmental | 37.504 | 1.7859 | TB401 | 1A/6 | Complete | Single-occurrence gang (not expanded)
2025-06-10 | 2025-06-30 | Permanand | 38.847 | 1.8499 | TB401 | 40/3 | Complete | Single-occurrence gang (not expanded)
2025-06-09 | 2025-07-07 | Anil Kumar Departmental Kewat | 38.847 | 1.3396 | TB401 | 1A/7 | Complete | Single-occurrence gang (not expanded)
2025-06-21 | 2025-07-08 | Satyam Manish 2 Santosh | 38.847 | 2.1582 | TB401 | 64/4 | Complete | Single-occurrence gang (not expanded)
2025-07-05 | 2025-07-10 | Arawali Infra 1 | 37.504 | 6.2507 | TB401 | 2/8 | Complete | Single-occurrence gang (not expanded)
2025-06-18 | 2025-07-14 | Anil Kumar Ramayan Departmental | 86.129 | 3.19 | TB401 | 1A/0 | Complete | Single-occurrence gang (not expanded)
2025-07-14 | 2025-07-22 | Satyam Trivedi Nitish | 38.847 | 4.3163 | TB401 | 30/1 | Complete | Single-occurrence gang (not expanded)
2025-07-10 | 2025-07-23 | Vinay Const 2 | 38.847 | 2.7748 | TB401 | 33/8 | Complete | Single-occurrence gang (not expanded)
2025-06-29 | 2025-07-24 | Anjani Enterprises | 45.413 | 1.7467 | TB401 | 11/4 | Complete | Single-occurrence gang (not expanded)
2025-07-10 | 2025-07-30 | Pusplata 3 Jwala | 47.148 | 2.2451 | TB401 | 25/8 | Complete | Single-occurrence gang (not expanded)
2025-07-24 | 2025-07-30 | Priyanka Devi Sudheer 2 | 38.847 | 5.5496 | TB401 | 17/4 | Complete | Single-occurrence gang (not expanded)
2025-06-25 | 2025-07-31 | Anil Kumar Departmental Ramayan | 86.129 | 2.3278 | TB401 | 1/0 | Complete | Single-occurrence gang (not expanded)
2025-08-05 | 2025-08-10 | Pusplata Santosh | 47.184 | 7.864 | TB401 | 28/4 | Complete | Single-occurrence gang (not expanded)
2025-07-17 | 2025-08-12 | Bhairo Mahto Departmental Arawali | 100.96 | 3.7393 | TB401 | 4/0 | Complete | Single-occurrence gang (not expanded)
2025-08-01 | 2025-08-14 | Pusplata Dharamveer | 47.184 | 3.3703 | TB401 | 21/12 | Complete | Single-occurrence gang (not expanded)
2025-08-13 | 2025-08-22 | Arawali | 45.413 | 4.5413 | TB401 | 2/7 | Complete | Single-occurrence gang (not expanded)
2025-08-10 | 2025-08-25 | Pusplata Rajaram | 89.909 | 5.6193 | TB401 | 20/0 | Complete | Single-occurrence gang (not expanded)
2025-08-10 | 2025-08-25 | Pusplata Praful | 89.909 | 5.6193 | TB401 | 21/0 | Complete | Single-occurrence gang (not expanded)
2025-08-14 | 2025-08-26 | Pusplata Ramchander | 81.494 | 6.2688 | TB401 | 22/0 | Complete | Single-occurrence gang (not expanded)
2025-08-21 | 2025-08-28 | Jawala Singh | 37.504 | 4.688 | TB401 | 8/4 | Complete | Single-occurrence gang (not expanded)
2025-08-25 | 2025-08-31 | Jawala Singh Suraj | 37.504 | 5.3577 | TB401 | 23/9 | Complete | Single-occurrence gang (not expanded)
2025-09-02 | 2025-09-10 | Bhairo Mahto | 38.847 | 4.3163 | TB401 | 8/2 | Complete | Single-occurrence gang (not expanded)
2025-09-05 | 2025-09-10 | Pusplata Pankaj | 37.504 | 6.2507 | TB401 | 14/3 | Complete | Single-occurrence gang (not expanded)
2025-09-06 | 2025-09-11 | Jwala Singh | 38.847 | 6.4745 | TB401 | 8/5 | Complete | Single-occurrence gang (not expanded)
| 2025-09-19 | Dhaneshwar Mahto | 171.017 |  | TA325 | 101/0 | Completed. | Missing start/end date (not expanded)
| 2025-11-09 | Dhaneshwar Mahto | 156.901 |  | TA325 | 102/0 |  | Missing start/end date (not expanded)
| 2025-08-13 | Dhaneshwar Mahto | 172.151 |  | TA325 | 104/0 | Completed | Missing start/end date (not expanded)
| 2025-08-08 | Nan | 141.874 |  | TA325 | 153/0 | Completed. | Missing start/end date (not expanded)
| 2025-07-20 | Nan | 37.73 |  | TA325 | 175/2 | Completed. | Missing start/end date (not expanded)
| 2025-08-26 | Modina India | 122.808 |  | TA325 | 191/0 | Completed. | Missing start/end date (not expanded)
| 2025-10-05 | Modina India 3 Pgcil | 37.73 |  | TA325 | 229/3 |  | Missing start/end date (not expanded)
| 2025-10-05 | Muni Bibi 2 | 37.73 |  | TA325 | 237/1 |  | Missing start/end date (not expanded)
| 2025-10-15 | Rupesh | 89.146 |  | TA325 | 237/0 |  | Missing start/end date (not expanded)
| 2025-10-08 | Dildar Electrical 2 Pgcil | 39.459 |  | TA325 | 237/6 |  | Missing start/end date (not expanded)
|  | Nan | 20932.97 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA325 |  | Completed Erection | Missing start/end date (not expanded)
|  | Nan | 40 |  | TA325 |  | 32 | Missing start/end date (not expanded)
|  | Nan | 146 |  | TA325 |  | 129 | Missing start/end date (not expanded)
|  | Nan | 40 |  | TA325 |  | 33 | Missing start/end date (not expanded)
|  | Nan | 30 |  | TA325 |  | 28 | Missing start/end date (not expanded)
|  | Nan | 11 |  | TA325 |  | 9 | Missing start/end date (not expanded)
|  | Nan | 267 |  | TA325 |  | 231 | Missing start/end date (not expanded)
|  | Nan | 25 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 6 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 8 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 9 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 6 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 1 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 55 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 26 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 3 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 7 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 3 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 47 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 16 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 3 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 6 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 5 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 2 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 40 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 19 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 8 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 11 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 7 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 7 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 15 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 2 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 73 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 1 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 1 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 483 |  | TA325 |  |  | Missing start/end date (not expanded)
2035-03-04 | 2025-03-11 | Thanu Mahto | 36.045 |  | TA325 | 271/3 | Completed. | Non-positive duration (Start > End or 0) (not expanded)
|  | Nan | 20932.97 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 267 |  | TA325 |  | 231 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 6 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 8 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 9 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 6 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 1 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 3 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 7 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 3 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 3 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 6 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 5 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 2 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 8 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 7 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 7 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 2 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 1 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 1 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 483 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
2025-01-06 | 2025-01-11 | Surender Mahto | 44.728 | 7.4547 | TA325 | 135/1 | Completed. | Single-occurrence gang (not expanded)
2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed. | Single-occurrence gang (not expanded)
2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed | Single-occurrence gang (not expanded)
|  | Nan |  |  | TA408 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA408 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA408 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA408 |  |  | Missing start/end date (not expanded)
2025-05-10 |  | Bhairo Mahto |  |  | TA408 |  |  | Missing start/end date (not expanded)
2025-05-19 |  | Sonakshi Manish 2 |  |  | TA408 |  |  | Missing start/end date (not expanded)
2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TA408 | 10/14 | Completed | Single-occurrence gang (not expanded)
2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TA408 | 67/0 | Completed | Single-occurrence gang (not expanded)
| 2025-07-12 | Subash | 33.38 |  | TA421 | 9/10 | Completed | Missing start/end date (not expanded)
| 2025-07-13 | Naziruddin | 71.706 |  | TA421 | 14/0 | Completed | Missing start/end date (not expanded)
2025-09-13 |  | Praveen | 36.37 |  | TA421 | 39/7 | 3rd Section under Progress | Missing start/end date (not expanded)
2025-09-21 |  | Yadhav | 37.931 |  | TA421 | 43/4 | 1st Section under Progress | Missing start/end date (not expanded)
2025-09-27 |  | Hassan | 36.37 |  | TA421 | 39/2 | Ground Assembling under Progress | Missing start/end date (not expanded)
2025-09-28 |  | Khatun | 31.99 |  | TA421 | 4/18 | Material Shifting Done | Missing start/end date (not expanded)
2025-10-01 |  | Subash |  |  | TA421 | 1/0 | Material Shifting under Progress | Missing start/end date (not expanded)
2025-10-01 |  | D K Verma |  |  | TA421 | 43/5 | Material Shifting Done | Missing start/end date (not expanded)
2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed | Single-occurrence gang (not expanded)
2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed | Single-occurrence gang (not expanded)
2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed | Single-occurrence gang (not expanded)
2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed | Single-occurrence gang (not expanded)

## Issues
file | issue | sheets
Micro Plan - TA-416 Sep'25.xlsx | Sheet 'Erection Compiled' not found | ['FDN-June25', 'Stub dispatch', 'Erection-Sep25', 'STG-Sep25']

## Diagnostics
file | project | sheet | detected_header_row | columns_detected
DPR TA-418 __ Dt.-29-09-25 (PGCIL) (1).xlsx | TA418 | Erection Compiled | 0 | sl no, location no, tower type, classification, starting date, tower weight, status, nan, nan, nan, completion date, gang name, gang strength, remark, nan, nan, 1.0, 2.0, 3.0, 4.0
DPR - TA - 413.xlsx | TA413 | Erection Compiled | 0 | sl no, location no, tower type, classification, starting date, tower weight, status, completion date, gang name, gang strength
DPR TA-416,14-09-25.xlsx | TA416 | Erection Compiled | 0 | sl no, location no, tower type, tower weight, starting date, completion date, status, gang name, gang strength, gang type(subcontractor/company), nan, tac welding, remark
DPR TA-505 06-10-2025.xlsx | TA505 | Erection Compiled | 3 | nan, sr. no, location no, tower type, tower weight, rev(inr), month of execution, gang name, status, starting date, completion date, no of compl. days, region, remarks if any
DPR TB401 Sterlite 765KV F3BTL 29.09.25.xlsx | TB401 | Erection Compiled | 3 | cum sl. no, month sl. no, location no, tower type, starting date, completion date, gang name, status, tower weight, nan, nan, nan, nan, nan, nan, nan, nan, nan, nan, nan
Latest TA-325-DPR-ANTL-30-09-2025.xlsx | TA325 | Erection Compiled | 0 | sl. no, location no, type, type of tower, starting date, revenue, tower weight, status, completion date, gang name
Micro Plan - TA-416 Sep'25.xlsx | TA416
TA 408.xlsx | TA408 | Erection Compiled | 3 | sl.no, month sl.no, location no, type of tower, starting date, completion date, gang name, status, tower weight, nan, nan, nan, nan, nan, nan, nan, nan, nan, nan, nan
TA 421 Latest BMTL-30-09-2025.xlsx | TA421 | Erection Compiled | 0 | sl no, location no, tower type, classification, starting date, tower weight, status, nan, nan, nan, completion date, gang name, gang strength, remark, tackwelding, tower tightening

## ProjectDetails
project_code | project_name | client_name | noa_start | loa_end | project_mgr | regional_mgr | planning_eng | pch | section_inch | supervisor | _source_file | Project Name
TA 418 | 765KV D/C HEXA AHMEDABAD - NAVSARI TL (PKG 02) | PGKTL | 2023-03-23 | 2024-12-22 | Mr. Sanjeev Garg | Mr. Nitin Bandale | Mr. Bikash Ranjan Pradhan | Mr. Sivaraman Natrajan | Prabin Patra, D N Prasad | Rupesh, Bijendra, Rahman, Sitaram, Churamani, J S Jha, Madhusudan, Ritlal, Somenath, Aflaudin, Akhtarul | DPR TA-418 __ Dt.-29-09-25 (PGCIL) (1).xlsx | TA418
TA 413 | 765kv D/C Bikaner II to Neemrana II TL-02 | PGCIL | 2024-03-12 | 2025-12-11 | Mr. Anil Kumar Sharma | Mr. Tushar Grover | Mr. Santosh Mishra | Mr. Sanjay Gupta | Surendra Kumar Patel, Kartik Jhorar, Shuvam Gupta, Govind Bhardwaj | Suraj Chaudhary, Rudra Prasad, Aman Kumar Singh, Manoj Gupta, Raju Mahto, Khublal Mahto, Sushil Kumar, Haridashn, Manoj Kumar chaudhary, Nabirul Islam, Sanjay Kumar, Rahul Ravidas, Narayan Mahto, Akbar Ali, Kamal Ravidas, Manirul Islam, Tarique Anwar, Raju Prasad, Abhay Ojha | DPR - TA - 413.xlsx | TA413
TA 416 | 765KV D/C HEXA AHMEDABAD - NAVSARI TL (PKG 02) | PGKTL | 2023-03-23 | 2024-12-22 | Mr. Sanjeev Garg | Mr. Nitin Bandale | Mr. Bikash Ranjan Pradhan | Mr. Sivaraman Natrajan | Prabin Patra, D N Prasad | Rupesh, Bijendra, Rahman, Sitaram, Churamani, J S Jha, Madhusudan, Ritlal, Somenath, Aflaudin, Akhtarul | DPR TA-416,14-09-25.xlsx | TA416
TA 505 | 765 Kv D/C Beawar-Mandsaur T/L | PBMTL | 2024-07-22 | 2026-06-21 | Mr. Sushil Kr Tiwari | Mr. Vijay Kute | Mr. Partha Pratim Pal | Mr. Arun Felbin | Mr.Deepak Anand, Mr.Bapan Mandal, Mr.Panneri Satish, Mr.Vinod Hankare | Nunuchand Mahto, Birkha Subba, Dilip Kumar, Teklal Mahato, Munid Meena, Mortuj Ali, Devdas Malik, Jayprakash Nishad, Kumar Singh, K. Sanjeevan, Mridul Baruah, Binda Shah, Prasanta Sahana, Lalit Sahoo, Sujit Roy, Ramprasad, Gourshankar, Vipin Mall, Aadesh | DPR TA-505 06-10-2025.xlsx | TA505
TB 401 | 765KV D/C HEXA AHMEDABAD - NAVSARI TL (PKG 02) | PGKTL | 2023-03-23 | 2024-12-22 | Mr. Sanjeev Garg | Mr. Nitin Bandale | Mr. Bikash Ranjan Pradhan | Mr. Sivaraman Natrajan | Prabin Patra, D N Prasad | Rupesh, Bijendra, Rahman, Sitaram, Churamani, J S Jha, Madhusudan, Ritlal, Somenath, Aflaudin, Akhtarul | DPR TB401 Sterlite 765KV F3BTL 29.09.25.xlsx | TB401
TA 325 | 765KV D/C HEXA AHMEDABAD - NAVSARI TL (PKG 02) | PGKTL | 2023-03-23 | 2024-12-22 | Mr. Sanjeev Garg | Mr. Nitin Bandale | Mr. Bikash Ranjan Pradhan | Mr. Sivaraman Natrajan | Prabin Patra, D N Prasad | Rupesh, Bijendra, Rahman, Sitaram, Churamani, J S Jha, Madhusudan, Ritlal, Somenath, Aflaudin, Akhtarul | Latest TA-325-DPR-ANTL-30-09-2025.xlsx | TA325
TA 408 | 765KV D/C HEXA AHMEDABAD - NAVSARI TL (PKG 02) | PGKTL | 2023-03-23 | 2024-12-22 | Mr. Sanjeev Garg | Mr. Nitin Bandale | Mr. Bikash Ranjan Pradhan | Mr. Sivaraman Natrajan | Prabin Patra, D N Prasad | Rupesh, Bijendra, Rahman, Sitaram, Churamani, J S Jha, Madhusudan, Ritlal, Somenath, Aflaudin, Akhtarul | TA 408.xlsx | TA408
TA 421 | 765KV D/C HEXA AHMEDABAD - NAVSARI TL (PKG 02) | PGKTL | 2023-03-23 | 2024-12-22 | Mr. Sanjeev Garg | Mr. Nitin Bandale | Mr. Bikash Ranjan Pradhan | Mr. Sivaraman Natrajan | Prabin Patra, D N Prasad | Rupesh, Bijendra, Rahman, Sitaram, Churamani, J S Jha, Madhusudan, Ritlal, Somenath, Aflaudin, Akhtarul | TA 421 Latest BMTL-30-09-2025.xlsx | TA421

## README_Assumptions
Notes
Assumptions & Cleaning Rules:
- Start date cutoff: rows with Start Date before 2021-01-01 are not expanded and logged in 'Data Issues'.
- Tower Weight range: only [10, 200] MT is considered valid for expansion; out-of-range rows go to 'Data Issues'.
- Missing or non-positive durations (Start/End missing or Start > End or 0) are logged to 'Data Issues' and not expanded.
- Gangs that performed erection only once (per Project+Gang) are not expanded and are logged in 'Data Issues'.
- Gang name normalization: remove special characters (digits kept), Title Case words, and insert a space before trailing digits (e.g., 'xyz4' → 'Xyz 4').
- Sheets:
• DailyExpanded : per-day expanded rows used by the dashboard
• RawData : per-erection rows (unexpanded), for traceability
• Data Issues : row-level data problems (reason in 'Issues' column)
• Issues : file-level problems (missing sheet/headers, read/open errors, etc.)
• Diagnostics : which sheet used, detected header row, and normalized header text
- Dashboard note: a 15-day productivity loss cap is used in downstream analytics.

## MicroPlanResponsibilities
project_key | project_name | entity_type | entity_name | location_no | revenue_planned | revenue_realised | tower_weight | tower_type | manpower | power_tools_issued | material_feeding | starting_date | completion_date | tack_welding | final_checking
ta416 | TA416 | Gang | Gagan Enterprise-1 | 12/0 | 861022 | 86102.2 | 97.704 | DB+18 | 30 |  | 2025-08-06 | 2025-08-06 | 2025-09-02 | 2025-09-03 | 2025-09-04
ta416 | TA416 | Gang | Reeta Bharti | 29/0 | 1610385.43 | 322077.086 | 161.355 | DD60+25 | 32 | No | 2025-08-10 | 2025-08-10 | 2025-09-10 | 2025-09-11 | 2025-09-12
ta416 | TA416 | Gang | Reeta Bharti | 27/0 | 875860 | 0 | 101.69 | DD60+3 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Gang | Kongres-1 | 25/0 | 1610385.43 | 0 | 161.355 | DD60+25 | 32 | No | 2025-08-30 | 2025-08-30 | 2025-09-21 | 2025-09-22 | 2025-09-23
ta416 | TA416 | Gang | Kongres-1 | 26/0 | 712728.77 | 142545.754 | 68.678 | DB+9 |  |  | 2025-09-22 | 2025-09-22 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Gang | Sainik Trader. | 19/0 | 789838 | 0 | 87.012 | DC+6 | 25 | No | 2025-09-01 | 2025-09-01 | 2025-09-13 | 2025-09-14 | 2025-09-15
ta416 | TA416 | Gang | Sainik Trader. | 37/0 | 1004656 | 0 | 110.696 | DC+18 |  |  | 2025-09-14 | 2025-09-14 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Gang | Gourishankar | 11/0 | 861022 | 0 | 97.704 | DB+18 | 45 | No | 2025-08-24 | 2025-08-24 | 2025-09-14 | 2025-09-15 | 2025-09-16
ta416 | TA416 | Gang | Gourishankar | 22A/0 | 974538 | 194907.6 | 110.575 | DB+25 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Gang | Mohika Con | 23/0 | 1492772 | 0 | 110.696 | DC+18 | 34 | No | 2025-08-30 | 2025-08-30 | 2025-09-21 | 2025-09-22 | 2025-09-23
ta416 | TA416 | Gang | Mohika Con | 46/0 | 568304 | 0 | 64.482 | DB+0 |  |  | 2025-09-22 | 2025-09-22 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Gang | Radha Construction | 2/0 | 827835 | 0 | 89.713 | DD45+3 | 33 | No | 2025-09-01 | 2025-09-01 | 2025-09-16 | 2025-09-17 | 2025-09-18
ta416 | TA416 | Gang | Radha Construction | 2/2 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-09-17 | 2025-09-17 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Gang | Ananya Trader | 43/0 | 1062230 | 0 | 118.43 | DD60+9 | 34 |  | 2025-08-16 | 2025-08-16 | 2025-09-05 | 2025-09-06 | 2025-09-07
ta416 | TA416 | Gang | Ananya Trader | 47/0 | 828626 | 165725.2 | 90.125 | DC+9 |  | No | 2025-09-06 | 2025-09-06 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Gang | Punam Kumari | 54/1 | 470947 | 0 | 55.339 | DA+9 | 33 | No | 2025-08-18 | 2025-08-18 | 2025-09-04 | 2025-09-05 | 2025-09-06
ta416 | TA416 | Gang | Punam Kumari | 52/0 | 828626 | 0 | 90.125 | DC+9 |  |  | 2025-09-05 | 2025-09-05 | 2025-09-14 | 2025-09-15 | 2025-09-16
ta416 | TA416 | Gang | Amit Choudhury | 16/0 | 974538 | 0 | 110.575 | DB+25 | 40 | No | 2025-08-18 | 2025-08-18 | 2025-09-11 | 2025-09-12 | 2025-09-13
ta416 | TA416 | Gang | Amit Choudhury | 17/0 | 669569.35 | 133913.87 | 75.897 | DB+6 |  |  | 2025-09-14 | 2025-09-15 | 2025-09-21 | 2025-09-22 | 2025-09-23
ta416 | TA416 | Gang | Amit Choudhury | 17/6 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-09-22 | 2025-09-22 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Gang | Kongres-2 | 64/0 | 666437 | 0 | 73.43 | DC+0 | 30 | No | 2025-09-01 | 2025-09-01 | 2025-09-12 | 2025-09-13 | 2025-09-14
ta416 | TA416 | Gang | Kongres-2 | 69A/0 | 837742 | 167548.4 | 97.229 | DD60+0 |  |  | 2025-09-13 | 2025-09-13 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Gang | MK Infra | 48/1 | 359483 | 0 | 42.374 | DA-3 | 16 | No | 2025-08-30 | 2025-08-30 | 2025-09-10 | 2025-09-11 | 2025-09-12
ta416 | TA416 | Gang | MK Infra | 49/0 | 828626 | 0 | 90.125 | DC+9 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Gang | Spotify-1 | 52/7 | 450628 | 0 | 53.324 | DA+6 | 20 | No | 2025-08-30 | 2025-08-30 | 2025-09-14 | 2025-09-15 | 2025-09-16
ta416 | TA416 | Gang | Spotify-1 | 53/0 | 666437 | 0 | 73.426 | DC+0 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Gang | Spotify-2 | 53A/1 | 450628 | 90125.6 | 53.324 | DA+6 | 20 | No | 2025-08-30 | 2025-08-30 | 2025-09-14 | 2025-09-15 | 2025-09-16
ta416 | TA416 | Gang | Spotify-2 | 55/0 | 666437 | 0 | 73.426 | DC+0 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Gang | Spotify-3 | 56/8 | 359483 | 0 | 42.374 | DA-3 | 24 | No | 2025-08-30 | 2025-08-30 | 2025-09-14 | 2025-09-15 | 2025-09-16
ta416 | TA416 | Gang | Spotify-3 | 56/7 | 450628 | 0 | 53.324 | DA+6 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Section Incharge | Prabin Patra | 12/0 | 861022 | 86102.2 | 97.704 | DB+18 | 30 |  | 2025-08-06 | 2025-08-06 | 2025-09-02 | 2025-09-03 | 2025-09-04
ta416 | TA416 | Section Incharge | Prabin Patra | 29/0 | 1610385.43 | 322077.086 | 161.355 | DD60+25 | 32 | No | 2025-08-10 | 2025-08-10 | 2025-09-10 | 2025-09-11 | 2025-09-12
ta416 | TA416 | Section Incharge | Prabin Patra | 27/0 | 875860 | 0 | 101.69 | DD60+3 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Section Incharge | Prabin Patra | 25/0 | 1610385.43 | 0 | 161.355 | DD60+25 | 32 | No | 2025-08-30 | 2025-08-30 | 2025-09-21 | 2025-09-22 | 2025-09-23
ta416 | TA416 | Section Incharge | Prabin Patra | 26/0 | 712728.77 | 142545.754 | 68.678 | DB+9 |  |  | 2025-09-22 | 2025-09-22 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Section Incharge | Prabin Patra | 19/0 | 789838 | 0 | 87.012 | DC+6 | 25 | No | 2025-09-01 | 2025-09-01 | 2025-09-13 | 2025-09-14 | 2025-09-15
ta416 | TA416 | Section Incharge | D N Prasad | 37/0 | 1004656 | 0 | 110.696 | DC+18 |  |  | 2025-09-14 | 2025-09-14 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Section Incharge | Prabin Patra | 11/0 | 861022 | 0 | 97.704 | DB+18 | 45 | No | 2025-08-24 | 2025-08-24 | 2025-09-14 | 2025-09-15 | 2025-09-16
ta416 | TA416 | Section Incharge | Prabin Patra | 22A/0 | 974538 | 194907.6 | 110.575 | DB+25 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Section Incharge | D N Prasad | 23/0 | 1492772 | 0 | 110.696 | DC+18 | 34 | No | 2025-08-30 | 2025-08-30 | 2025-09-21 | 2025-09-22 | 2025-09-23
ta416 | TA416 | Section Incharge | D N Prasad | 46/0 | 568304 | 0 | 64.482 | DB+0 |  |  | 2025-09-22 | 2025-09-22 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Section Incharge | Prabin Patra | 2/0 | 827835 | 0 | 89.713 | DD45+3 | 33 | No | 2025-09-01 | 2025-09-01 | 2025-09-16 | 2025-09-17 | 2025-09-18
ta416 | TA416 | Section Incharge | Prabin Patra | 2/2 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-09-17 | 2025-09-17 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Section Incharge | D N Prasad | 43/0 | 1062230 | 0 | 118.43 | DD60+9 | 34 |  | 2025-08-16 | 2025-08-16 | 2025-09-05 | 2025-09-06 | 2025-09-07
ta416 | TA416 | Section Incharge | D N Prasad | 47/0 | 828626 | 165725.2 | 90.125 | DC+9 |  | No | 2025-09-06 | 2025-09-06 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Section Incharge | D N Prasad | 54/1 | 470947 | 0 | 55.339 | DA+9 | 33 | No | 2025-08-18 | 2025-08-18 | 2025-09-04 | 2025-09-05 | 2025-09-06
ta416 | TA416 | Section Incharge | D N Prasad | 52/0 | 828626 | 0 | 90.125 | DC+9 |  |  | 2025-09-05 | 2025-09-05 | 2025-09-14 | 2025-09-15 | 2025-09-16
ta416 | TA416 | Section Incharge | Prabin Patra | 16/0 | 974538 | 0 | 110.575 | DB+25 | 40 | No | 2025-08-18 | 2025-08-18 | 2025-09-11 | 2025-09-12 | 2025-09-13
ta416 | TA416 | Section Incharge | Prabin Patra | 17/0 | 669569.35 | 133913.87 | 75.897 | DB+6 |  |  | 2025-09-14 | 2025-09-15 | 2025-09-21 | 2025-09-22 | 2025-09-23
ta416 | TA416 | Section Incharge | Prabin Patra | 17/6 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-09-22 | 2025-09-22 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Section Incharge | D N Prasad | 64/0 | 666437 | 0 | 73.43 | DC+0 | 30 | No | 2025-09-01 | 2025-09-01 | 2025-09-12 | 2025-09-13 | 2025-09-14
ta416 | TA416 | Section Incharge | D N Prasad | 69A/0 | 837742 | 167548.4 | 97.229 | DD60+0 |  |  | 2025-09-13 | 2025-09-13 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Section Incharge | D N Prasad | 48/1 | 359483 | 0 | 42.374 | DA-3 | 16 | No | 2025-08-30 | 2025-08-30 | 2025-09-10 | 2025-09-11 | 2025-09-12
ta416 | TA416 | Section Incharge | D N Prasad | 49/0 | 828626 | 0 | 90.125 | DC+9 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Section Incharge | D N Prasad | 52/7 | 450628 | 0 | 53.324 | DA+6 | 20 | No | 2025-08-30 | 2025-08-30 | 2025-09-14 | 2025-09-15 | 2025-09-16
ta416 | TA416 | Section Incharge | D N Prasad | 53/0 | 666437 | 0 | 73.426 | DC+0 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Section Incharge | D N Prasad | 53A/1 | 450628 | 90125.6 | 53.324 | DA+6 | 20 | No | 2025-08-30 | 2025-08-30 | 2025-09-14 | 2025-09-15 | 2025-09-16
ta416 | TA416 | Section Incharge | D N Prasad | 55/0 | 666437 | 0 | 73.426 | DC+0 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Section Incharge | D N Prasad | 56/8 | 359483 | 0 | 42.374 | DA-3 | 24 | No | 2025-08-30 | 2025-08-30 | 2025-09-14 | 2025-09-15 | 2025-09-16
ta416 | TA416 | Section Incharge | D N Prasad | 56/7 | 450628 | 0 | 53.324 | DA+6 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Supervisor | Bijendra | 12/0 | 861022 | 86102.2 | 97.704 | DB+18 | 30 |  | 2025-08-06 | 2025-08-06 | 2025-09-02 | 2025-09-03 | 2025-09-04
ta416 | TA416 | Supervisor | Rupesh | 29/0 | 1610385.43 | 322077.086 | 161.355 | DD60+25 | 32 | No | 2025-08-10 | 2025-08-10 | 2025-09-10 | 2025-09-11 | 2025-09-12
ta416 | TA416 | Supervisor | Rupesh | 27/0 | 875860 | 0 | 101.69 | DD60+3 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Supervisor | Bijendra | 25/0 | 1610385.43 | 0 | 161.355 | DD60+25 | 32 | No | 2025-08-30 | 2025-08-30 | 2025-09-21 | 2025-09-22 | 2025-09-23
ta416 | TA416 | Supervisor | Bijendra | 26/0 | 712728.77 | 142545.754 | 68.678 | DB+9 |  |  | 2025-09-22 | 2025-09-22 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Supervisor | Rahman | 19/0 | 789838 | 0 | 87.012 | DC+6 | 25 | No | 2025-09-01 | 2025-09-01 | 2025-09-13 | 2025-09-14 | 2025-09-15
ta416 | TA416 | Supervisor | Rahman | 37/0 | 1004656 | 0 | 110.696 | DC+18 |  |  | 2025-09-14 | 2025-09-14 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Supervisor | Sitaram | 11/0 | 861022 | 0 | 97.704 | DB+18 | 45 | No | 2025-08-24 | 2025-08-24 | 2025-09-14 | 2025-09-15 | 2025-09-16
ta416 | TA416 | Supervisor | Sitaram | 22A/0 | 974538 | 194907.6 | 110.575 | DB+25 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Supervisor | Bijendra | 23/0 | 1492772 | 0 | 110.696 | DC+18 | 34 | No | 2025-08-30 | 2025-08-30 | 2025-09-21 | 2025-09-22 | 2025-09-23
ta416 | TA416 | Supervisor | Bijendra | 46/0 | 568304 | 0 | 64.482 | DB+0 |  |  | 2025-09-22 | 2025-09-22 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Supervisor | Churamani | 2/0 | 827835 | 0 | 89.713 | DD45+3 | 33 | No | 2025-09-01 | 2025-09-01 | 2025-09-16 | 2025-09-17 | 2025-09-18
ta416 | TA416 | Supervisor | Churamani | 2/2 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-09-17 | 2025-09-17 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Supervisor | J S Jha | 43/0 | 1062230 | 0 | 118.43 | DD60+9 | 34 |  | 2025-08-16 | 2025-08-16 | 2025-09-05 | 2025-09-06 | 2025-09-07
ta416 | TA416 | Supervisor | J S Jha | 47/0 | 828626 | 165725.2 | 90.125 | DC+9 |  | No | 2025-09-06 | 2025-09-06 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Supervisor | Madhusudan | 54/1 | 470947 | 0 | 55.339 | DA+9 | 33 | No | 2025-08-18 | 2025-08-18 | 2025-09-04 | 2025-09-05 | 2025-09-06
ta416 | TA416 | Supervisor | Madhusudan | 52/0 | 828626 | 0 | 90.125 | DC+9 |  |  | 2025-09-05 | 2025-09-05 | 2025-09-14 | 2025-09-15 | 2025-09-16
ta416 | TA416 | Supervisor | Rahman | 16/0 | 974538 | 0 | 110.575 | DB+25 | 40 | No | 2025-08-18 | 2025-08-18 | 2025-09-11 | 2025-09-12 | 2025-09-13
ta416 | TA416 | Supervisor | Rahman | 17/0 | 669569.35 | 133913.87 | 75.897 | DB+6 |  |  | 2025-09-14 | 2025-09-15 | 2025-09-21 | 2025-09-22 | 2025-09-23
ta416 | TA416 | Supervisor | Rahman | 17/6 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-09-22 | 2025-09-22 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Supervisor | Ritlal | 64/0 | 666437 | 0 | 73.43 | DC+0 | 30 | No | 2025-09-01 | 2025-09-01 | 2025-09-12 | 2025-09-13 | 2025-09-14
ta416 | TA416 | Supervisor | Ritlal | 69A/0 | 837742 | 167548.4 | 97.229 | DD60+0 |  |  | 2025-09-13 | 2025-09-13 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Supervisor | Somenath | 48/1 | 359483 | 0 | 42.374 | DA-3 | 16 | No | 2025-08-30 | 2025-08-30 | 2025-09-10 | 2025-09-11 | 2025-09-12
ta416 | TA416 | Supervisor | Somenath | 49/0 | 828626 | 0 | 90.125 | DC+9 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Supervisor | Ritlal | 52/7 | 450628 | 0 | 53.324 | DA+6 | 20 | No | 2025-08-30 | 2025-08-30 | 2025-09-14 | 2025-09-15 | 2025-09-16
ta416 | TA416 | Supervisor | Ritlal | 53/0 | 666437 | 0 | 73.426 | DC+0 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Supervisor | Aflaudin | 53A/1 | 450628 | 90125.6 | 53.324 | DA+6 | 20 | No | 2025-08-30 | 2025-08-30 | 2025-09-14 | 2025-09-15 | 2025-09-16
ta416 | TA416 | Supervisor | Aflaudin | 55/0 | 666437 | 0 | 73.426 | DC+0 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-02
ta416 | TA416 | Supervisor | Akhtarul | 56/8 | 359483 | 0 | 42.374 | DA-3 | 24 | No | 2025-08-30 | 2025-08-30 | 2025-09-14 | 2025-09-15 | 2025-09-16
ta416 | TA416 | Supervisor | Aflaudin | 56/7 | 450628 | 0 | 53.324 | DA+6 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-02

## MicroPlanIndex
file_path | project_name | project_key | rows_cleaned | status | error
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Test\Micro Plan - TA-416 Sep'25.xlsx | TA416 | ta416 | 30 | ok