## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manger | Section Incharge | Engineer/Supervisor
TA 413 | 765kv D/C Bikaner II to Neemrana II TL-02 | PGCIL | 2024-03-12 | 2025-12-11 | Mr. Santosh Mishra | Mr. Sanjay Gupta | Mr. Tushar Grover | Mr. Anil Kumar Sharma | Surendra Kumar Patel | Suraj Chaudhary
[9 empty] | Kartik Jhorar | Rudra Prasad
[9 empty] | Shuvam Gupta | Aman Kumar Singh
[9 empty] | Govind Bhardwaj | Manoj Gupta
Raju Mahto
Khublal Mahto
Sushil Kumar
Haridashn
Manoj Kumar chaudhary
Nabirul Islam
Sanjay Kumar
Rahul Ravidas
Narayan Mahto
Akbar Ali
Kamal Ravidas
Manirul Islam
Tarique Anwar
Raju Prasad
Abhay Ojha

## Erection Compiled
SL No. | Location No. | Tower Type | Classification | Starting Date | Tower Weight | Status | Completion Date | Gang Name | Gang Strength
1 | 29A/2 | DA+6 | SANDY | 2024-09-12 | 43.8044 | COMPLETED | 2024-09-21 | Bhagwan construction
2 | 29/5 | DA+0 | SANDY | 2024-09-21 | 36.1598 | COMPLETED | 2024-09-27 | Bhagwan construction
3 | 29/3 | DA+0 | SANDY | 2024-09-28 | 36.1598 | COMPLETED | 2024-10-03 | Bhagwan construction
4 | 29/4 | DA+3 | SANDY | 2024-10-03 | 37.9311 | COMPLETED | 2024-10-08 | Bhagwan construction
5 | 29A/6 | DA+9 | SANDY | 2024-10-03 | 45.697 | COMPLETED | 2024-10-14 | Bhagwan construction
6 | 30/1 | DA+0 | SANDY | 2024-10-09 | 36.1598 | COMPLETED | 2024-10-17 | Bhagwan construction
7 | 29A/1 | DA+6 | SANDY | 2024-10-14 | 43.8044 | COMPLETED | 2024-10-25 | Bhagwan construction
8 | 34/8 | DA+0 | SANDY | 2024-11-12 | 36.1598 | COMPLETED | 2024-11-24 | Vasu dev singh-1
9 | 34/12 | DA+3 | SANDY | 2024-11-14 | 37.9311 | COMPLETED | 2024-11-25 | Vasu dev singh-2
10 | 34/4 | DA+6 | SANDY | 2024-11-25 | 43.8044 | COMPLETED | 2024-12-04 | Vasu dev singh-1
11 | 34/7 | DA+0 | SANDY | 2024-11-26 | 36.1598 | COMPLETED | 2024-12-12 | Vasu dev singh-2
12 | 34/3 | DA+1.5 | SANDY | 2024-12-05 | 37.1383 | COMPLETED | 2024-12-16 | Vasu dev singh-1
13 | 8/1 | DA-3 | SANDY | 2024-12-07 | 34.7898 | COMPLETED | 2024-12-16 | Punam Devi-2
14 | 34/9 | DA+1.5 | SANDY | 2024-12-13 | 37.1383 | COMPLETED | 2024-12-21 | Vasu dev singh-2
15 | 35/7 | DA+3 | SANDY | 2024-12-13 | 37.9311 | COMPLETED | 2024-12-22 | Punam Devi-2
16 | 7A/5 | DA+3 | SANDY | 2024-12-17 | 37.9311 | COMPLETED | 2024-12-24 | Punam Devi-2
17 | 36A/1 | DA+3 | SANDY | 2024-12-13 | 37.9311 | COMPLETED | 2024-12-25 | Punam Devi-3
18 | 7/1 | DA-3 | SANDY | 2024-12-15 | 34.7898 | COMPLETED | 2024-12-26 | Punam Devi-1
19 | 35/8 | DA+6 | SANDY | 2024-12-23 | 43.8044 | COMPLETED | 2024-12-28 | Punam Devi-2
20 | 34/5 | DA+9 | SANDY | 2024-12-17 | 45.697 | COMPLETED | 2024-12-29 | Vasu dev singh-1
21 | 34/10 | DA-3 | SANDY | 2024-12-22 | 34.7898 | COMPLETED | 2024-12-29 | Vasu dev singh-2
22 | 7A/4 | DA+3 | SANDY | 2024-12-24 | 37.9311 | COMPLETED | 2024-12-31 | Punam Devi-2
23 | 7/2 | DA+6 | SANDY | 2024-12-27 | 43.8044 | COMPLETED | 2025-01-03 | Punam Devi-1
24 | 35/11 | DA+3 | SANDY | 2024-12-24 | 37.9311 | COMPLETED | 2025-01-03 | Punam Devi-3
25 | 35/6 | DA+6 | SANDY | 2024-12-29 | 43.8044 | COMPLETED | 2025-01-05 | Punam Devi-2
26 | 34/11 | DA+1.5 | SANDY | 2024-12-30 | 37.1383 | COMPLETED | 2025-01-07 | Vasu dev singh-2
27 | 7A/3 | DA+3 | SANDY | 2025-01-01 | 37.9311 | COMPLETED | 2025-01-08 | Punam Devi-2
28 | 34/6 | DA+3 | SANDY | 2024-12-30 | 37.9311 | COMPLETED | 2025-01-09 | Vasu dev singh-1
29 | 8/5 | DA+9 | SANDY | 2025-01-04 | 45.697 | COMPLETED | 2025-01-09 | Punam Devi-1
30 | 36A/2 | DA+9 | SANDY | 2025-01-04 | 45.697 | COMPLETED | 2025-01-11 | Punam Devi-3
31 | 35/5 | DA+9 | SANDY | 2025-01-06 | 45.697 | COMPLETED | 2025-01-13 | Punam Devi-2
32 | 8/6 | DA+3 | SANDY | 2025-01-10 | 37.9311 | COMPLETED | 2025-01-15 | Punam Devi-1
33 | 7A/2 | DA+3 | SANDY | 2025-01-08 | 37.9311 | COMPLETED | 2025-01-16 | Punam Devi-2
34 | 35/1 | DA+6 | SANDY | 2025-01-07 | 43.8044 | COMPLETED | 2025-01-19 | Vasu dev singh-2
35 | 35/4 | DA+9 | SANDY | 2025-01-14 | 45.697 | COMPLETED | 2025-01-19 | Punam Devi-2
36 | 8/7 | DA+3 | SANDY | 2025-01-16 | 37.9311 | COMPLETED | 2025-01-20 | Punam Devi-1
37 | 34/2 | DA+9 | SANDY | 2025-01-10 | 45.697 | COMPLETED | 2025-01-21 | Vasu dev singh-1
38 | 37/4 | DA+9 | SANDY | 2025-01-11 | 45.697 | COMPLETED | 2025-01-22 | Punam Devi-3
39 | 7A/1 | DA+1.5 | SANDY | 2025-01-17 | 37.1383 | COMPLETED | 2025-01-22 | Punam Devi-2
40 | 35/9 | DA+1.5 | SANDY | 2025-01-17 | 37.1383 | COMPLETED | 2025-01-24 | Punam Devi-2
41 | 8/8 | DA+9 | SANDY | 2025-01-20 | 45.697 | COMPLETED | 2025-01-25 | Punam Devi-1
42 | 34/1 | DA+9 | SANDY | 2025-01-21 | 45.697 | COMPLETED | 2025-01-29 | Vasu dev singh-1
43 | 38/3 | DA+3 | SANDY | 2025-01-24 | 37.9311 | COMPLETED | 2025-01-29 | Punam Devi-2
44 | 8/9 | DA+3 | SANDY | 2025-01-25 | 37.9311 | COMPLETED | 2025-01-30 | Punam Devi-4
45 | 37/5 | DA+3 | SANDY | 2025-01-22 | 37.9311 | COMPLETED | 2025-01-30 | Punam Devi-3
46 | 7A/0 | DB1+6 | SANDY | 2025-01-22 | 65.0278 | COMPLETED | 2025-01-31 | Punam Devi-2
47 | 34/0 | DB1+6 | SANDY | 2025-01-17 | 65.0278 | COMPLETED | 2025-01-31 | Vasu dev singh-1
48 | 8/10 | DA+0 | SANDY | 2025-01-30 | 36.1598 | COMPLETED | 2025-02-03 | Punam Devi-4
49 | 38/6 | DA+6 | SANDY | 2025-01-29 | 43.8044 | COMPLETED | 2025-02-04 | Punam Devi-1
50 | 37A/2 | DA+1.5 | SANDY | 2025-01-29 | 37.1383 | COMPLETED | 2025-02-07 | Punam Devi-3
51 | 33/6 | DA+6 | SANDY | 2025-01-29 | 43.8044 | COMPLETED | 2025-02-08 | Vasu dev singh-2
52 | 8/2 | DA+6 | SANDY | 2025-02-03 | 43.8044 | COMPLETED | 2025-02-08 | Punam Devi-4
53 | 7/6 | DA-1.5 | SANDY | 2025-01-31 | 35.6018 | COMPLETED | 2025-02-10 | Punam Devi-2
54 | 38/4 | DA+1.5 | SANDY | 2025-02-05 | 37.1383 | COMPLETED | 2025-02-10 | Punam Devi-1
55 | 8/0 | DB1+0 | SANDY | 2025-02-09 | 55.4509 | COMPLETED | 2025-02-14 | Punam Devi-4
56 | 38/5 | DA+3 | SANDY | 2025-02-11 | 37.9311 | COMPLETED | 2025-02-15 | Punam Devi-1
57 | 37A/1 | DA+3 | SANDY | 2025-02-08 | 37.9311 | COMPLETED | 2025-02-16 | Punam Devi-3
58 | 33/5 | DA+0 | SANDY | 2025-01-31 | 36.1598 | COMPLETED | 2025-02-18 | Vasu dev singh-1
59 | 38/9 | DA+0 | SANDY | 2025-02-15 | 36.1598 | COMPLETED | 2025-02-18 | Punam Devi-1
60 | 7/5 | DA+6 | SANDY | 2025-02-11 | 43.8044 | COMPLETED | 2025-02-19 | Punam Devi-2
61 | 8/3 | DA+9 | SANDY | 2025-02-14 | 45.697 | COMPLETED | 2025-02-19 | Punam Devi-4
62 | 35/0 | DB2+0 | SANDY | 2025-02-09 | 59.5006 | COMPLETED | 2025-02-23 | Vasu dev singh-2
63 | 38/10 | DA+3 | SANDY | 2025-02-18 | 37.9311 | COMPLETED | 2025-02-24 | Punam Devi-1
64 | 8/4 | DA+6 | SANDY | 2025-02-20 | 43.8044 | COMPLETED | 2025-02-24 | Punam Devi-4
65 | 37A/3 | DA+3 | SANDY | 2025-02-16 | 37.9311 | COMPLETED | 2025-02-25 | Punam Devi-3
66 | 7/4 | DA+6 | SANDY | 2025-02-20 | 43.8044 | COMPLETED | 2025-02-27 | Punam Devi-2
67 | 9/1 | DA+3 | SANDY | 2025-02-24 | 37.9311 | COMPLETED | 2025-02-28 | Punam Devi-4
68 | 37A/5 | DA+3 | SANDY | 2025-02-24 | 37.9311 | COMPLETED | 2025-02-28 | Punam Devi-1
69 | 33/8 | DA+3 | SANDY | 2025-02-18 | 37.9311 | COMPLETED | 2025-03-04 | Vasu dev singh-1
70 | 9/3 | DA+0 | SANDY | 2025-03-01 | 36.1598 | COMPLETED | 2025-03-04 | Punam Devi-4
71 | 38/1 | DA+0 | SANDY | 2025-03-01 | 36.1598 | COMPLETED | 2025-03-06 | Punam Devi-1
72 | 37A/4 | DA+9 | SANDY | 2025-02-25 | 45.697 | COMPLETED | 2025-03-06 | Punam Devi-3
73 | 37A/6 | DA+3 | SANDY | 2025-02-24 | 37.9311 | COMPLETED | 2025-03-08 | Vasu dev singh-2
74 | 9/4 | DA+6 | SANDY | 2025-03-05 | 43.8044 | COMPLETED | 2025-03-09 | Punam Devi-4
75 | 37A/0 | DB1+0 | SANDY | 2025-02-28 | 55.4509 | COMPLETED | 2025-03-11 | Punam Devi-2
76 | 38/2 | DA+0 | SANDY | 2025-03-07 | 36.1598 | COMPLETED | 2025-03-11 | Punam Devi-1
77 | 39/7 | DA+3 | SANDY | 2025-03-07 | 37.9311 | COMPLETED | 2025-03-13 | Punam Devi-3
78 | 9/2 | DA+3 | SANDY | 2025-03-10 | 37.9311 | COMPLETED | 2025-03-13 | Punam Devi-4
79 | 15/2 | DA+3 | SANDY | 2025-03-14 | 37.9311 | COMPLETED | 2025-03-18 | Punam Devi-4
80 | 38/7 | DA+9 | SANDY | 2025-03-12 | 45.697 | COMPLETED | 2025-03-18 | Punam Devi-1
81 | 39/2 | DA+3 | SANDY | 2025-03-12 | 37.9311 | COMPLETED | 2025-03-19 | Punam Devi-2
82 | 39/5 | DA+1.5 | SANDY | 2025-03-14 | 37.1383 | COMPLETED | 2025-03-20 | Punam Devi-3
83 | 39/0 | DB2+0 | SANDY | 2025-03-09 | 59.5006 | COMPLETED | 2025-03-21 | Vasu dev singh-2
84 | 15/3 | DA+3 | SANDY | 2025-03-19 | 37.9311 | COMPLETED | 2025-03-22 | Punam Devi-4
85 | 38/8 | DA+1.5 | SANDY | 2025-03-19 | 37.1383 | COMPLETED | 2025-03-24 | Punam Devi-1
86 | 39/3 | DA+1.5 | SANDY | 2025-03-20 | 37.1383 | COMPLETED | 2025-03-25 | Punam Devi-2
87 | 39/4 | DA+3 | SANDY | 2025-03-21 | 37.9311 | COMPLETED | 2025-03-27 | Punam Devi-3
88 | 15/4 | DA+6 | SANDY | 2025-03-23 | 43.8044 | COMPLETED | 2025-03-27 | Punam Devi-4
89 | 39/1 | DA-1.5 | SANDY | 2025-03-22 | 35.6018 | COMPLETED | 2025-03-29 | Vasu dev singh-2
90 | 39/9 | DA+6 | SANDY | 2025-03-25 | 43.8044 | COMPLETED | 2025-03-30 | Punam Devi-1
91 | 40/2 | DA+6 | SANDY | 2025-03-26 | 43.8044 | COMPLETED | 2025-03-31 | Punam Devi-2
92 | 15/5 | DA+3 | SANDY | 2025-03-26 | 37.9311 | COMPLETED | 2025-03-31 | Punam Devi-4
93 | 39/8 | DA+1.5 | SANDY | 2024-03-26 | 37.1383 | COMPLETED | 2025-03-31 | Punam Devi-3
94 | 39/10 | DA+3 | SANDY | 2025-03-31 | 37.9311 | COMPLETED | 2025-04-05 | Punam Devi-3
95 | 15/6 | DA+9 | SANDY | 2025-03-31 | 45.697 | COMPLETED | 2025-04-06 | Punam Devi-4
96 | 39/11 | DA+6 | SANDY | 2025-03-30 | 43.8044 | COMPLETED | 2025-04-09 | Punam Devi-1
97 | 40/3 | DA+3 | SANDY | 2025-03-31 | 37.9311 | COMPLETED | 2025-04-09 | Punam Devi-2
98 | 38/0 | DB1+3 | SANDY | 2025-03-29 | 57.9632 | COMPLETED | 2025-04-11 | Vasu dev singh-2
99 | 40/5 | DA+9 | SANDY | 2025-04-05 | 45.697 | COMPLETED | 2025-04-14 | Punam Devi-3
100 | 40/4 | DA+6 | SANDY | 2025-04-09 | 43.8044 | COMPLETED | 2025-04-18 | Punam Devi-2
101 | 39/6 | DA+1.5 | SANDY | 2025-04-09 | 37.1383 | COMPLETED | 2025-04-18 | Punam Devi-1
102 | 40/6 | DA+9 | SANDY | 2025-04-14 | 45.697 | COMPLETED | 2025-04-22 | Punam Devi-3
103 | 36A/0 | DB1+9 | SANDY | 2025-04-18 | 66.7809 | COMPLETED | 2025-04-30 | Punam Devi-2
104 | 40/0 | DB1+6 | SANDY | 2025-04-18 | 65.0278 | COMPLETED | 2025-04-30 | Punam Devi-1
105 | 32/6 | DA+9 | SANDY | 2025-07-06 | 45.697 | COMPLETED | 2025-07-15 | Punam Kumari
106 | 32/1 | DA+6 | SANDY | 2025-07-05 | 43.8044 | COMPLETED | 2025-07-17 | Amit Kumar Singh
107 | 7/3 | DA+9 | SANDY | 2025-07-09 | 45.697 | COMPLETED | 2025-07-21 | Pritam Enterprises
108 | 32/5 | DA+9 | SANDY | 2025-07-16 | 45.697 | COMPLETED | 2025-07-25 | Punam Kumari
109 | 6/1 | DA+9 | SANDY | 2025-07-16 | 45.697 | COMPLETED | 2025-07-26 | Jwala Singh-1
110 | 32/2 | DA+9 | SANDY | 2025-07-18 | 45.697 | COMPLETED | 2025-07-26 | Amit Kumar Singh
111 | 7/0 | DB2+0 | SANDY | 2025-07-22 | 59.5006 | COMPLETED | 2025-07-31 | Pritam Enterprises
112 | 32/7 | DA+3 | SANDY | 2025-07-26 | 37.9311 | COMPLETED | 2025-07-31 | Punam Kumari
113 | 31/0 | DB1+0 | SANDY | 2025-07-16 | 55.4509 | COMPLETED | 2025-08-01 | SK Samiul -1
114 | 42/0 | DB2+0 | SANDY | 2025-07-21 | 59.5006 | COMPLETED | 2025-08-02 | Fouzi Ratto
115 | 8/11 | DA+9 | SANDY | 2025-07-15 | 45.697 | COMPLETED | 2025-08-03 | Jwala Singh-1
116 | 30/10 | DA+3 | SANDY | 2025-07-18 | 37.9311 | COMPLETED | 2025-08-03 | SK.Samiul -2
117 | 32/3 | DA+6 | SANDY | 2025-07-27 | 43.8044 | COMPLETED | 2025-08-05 | Amit Kumar Singh
118 | 42/1 | DA+3 | SANDY | 2025-08-02 | 37.9311 | COMPLETED | 2025-08-06 | Fouzi Ratto
119 | 40/1 | DA+9 | SANDY | 2025-07-06 | 45.697 | COMPLETED | 2025-08-07 | Bambole Traders
120 | 6/2 | DA+6 | SANDY | 2025-08-04 | 43.8044 | COMPLETED | 2025-08-08 | Jwala Singh-1
121 | 32A/0 | DB1+9 | SANDY | 2025-08-01 | 66.7809 | COMPLETED | 2025-08-09 | Punam Kumari
122 | 35/2 | DA+6 | SANDY | 2025-08-01 | 43.8044 | COMPLETED | 2025-08-09 | Jwala Singh-2
123 | 6/12 | DA+1.5 | SANDY | 2025-08-01 | 37.1383 | COMPLETED | 2025-08-09 | Pritam Enterprises-1
124 | 31/1 | DA+3 | SANDY | 2025-08-02 | 37.9311 | COMPLETED | 2025-08-10 | SK Samiul -1
125 | 31/2 | DA+1.5 | SANDY | 2025-08-04 | 37.1383 | COMPLETED | 2025-08-11 | SK.Samiul -2
126 | 42/2 | DA+9 | SANDY | 2025-08-07 | 45.697 | COMPLETED | 2025-08-11 | Fouzi Ratto
127 | 40/9 | DA+9 | SANDY | 2025-08-01 | 45.697 | COMPLETED | 2025-08-13 | Pinki Devi
128 | 6/5 | DA+9 | SANDY | 2025-08-02 | 45.697 | COMPLETED | 2025-08-13 | Pritam Enterprises-2
129 | 32/4 | DA+9 | SANDY | 2025-08-07 | 45.697 | COMPLETED | 2025-08-14 | Amit Kumar Singh
130 | 6/3 | DA+3 | SANDY | 2025-08-08 | 37.9311 | COMPLETED | 2025-08-14 | Jwala Singh-1
131 | 8A/0 | DB1+12 | SANDY | 2025-08-07 | 70.7883 | COMPLETED | 2025-08-14 | Punam Kumari-2
132 | 33/2 | DA+9 | SANDY | 2025-08-09 | 45.697 | COMPLETED | 2025-08-17 | Punam Kumari-1
133 | 6/10 | DA+1.5 | SANDY | 2025-08-09 | 37.1383 | COMPLETED | 2025-08-18 | Pritam Enterprises-1
134 | 9/5 | DA+3 | SANDY | 2025-08-15 | 37.9311 | COMPLETED | 2025-08-19 | Punam Kumari-2
135 | 42/3 | DB1+9 | SANDY | 2025-08-12 | 66.7809 | COMPLETED | 2025-08-19 | Fouzi Ratto
136 | 5/6 | DA+3 | SANDY | 2025-08-08 | 37.9311 | COMPLETED | 2025-08-20 | Pritam Enterprises-4
137 | 40/7 | DA+3 | SANDY | 2025-08-14 | 37.9311 | COMPLETED | 2025-08-20 | Pinki Devi
138 | 1/0 | DD60+0 | SANDY | 2025-08-07 | 83.1335 | COMPLETED | 2025-08-21 | Pritam Enterprises-3
139 | 6/0 | DB1+9 | SANDY | 2025-08-13 | 66.7809 | COMPLETED | 2025-08-21 | Jwala Singh-2
140 | 6/6 | DA-3 | SANDY | 2025-08-14 | 34.7898 | COMPLETED | 2025-08-21 | Pritam Enterprises-2
141 | 6/4 | DA+9 | SANDY | 2025-08-15 | 45.697 | COMPLETED | 2025-08-21 | Jwala Singh-1
142 | 30/9 | DA-3 | SANDY | 2025-08-12 | 34.7898 | COMPLETED | 2025-08-21 | SK.Samiul -2
143 | 31/3 | DA+3 | SANDY | 2025-08-12 | 37.9311 | COMPLETED | 2025-08-22 | SK Samiul -1
144 | 33/9 | DA+1.5 | SANDY | 2025-08-18 | 37.1383 | COMPLETED | 2025-08-22 | Punam Kumari-1
145 | 6/11 | DA-1.5 | SANDY | 2025-08-19 | 35.6018 | COMPLETED | 2025-08-25 | Pritam Enterprises-1
146 | 9/6 | DA+3 | SANDY | 2025-08-20 | 37.9311 | COMPLETED | 2025-08-25 | Punam Kumari-2
147 | 43/2 | DA+6 | SANDY | 2025-08-20 | 43.8044 | COMPLETED | 2025-08-25 | Fouzi Ratto
148 | 31/10 | DA+4.5 | SANDY | 2025-08-15 | 42.9218 | COMPLETED | 2025-08-25 | Amit Kumar Singh
149 | 2A/1 | DA+0 | SANDY | 2025-08-21 | 36.1598 | COMPLETED | 2025-08-27 | Pritam Enterprises-3
150 | 4A/4 | DA+6 | SANDY | 2025-08-18 | 43.8044 | COMPLETED | 2025-08-28 | Govind Mahto-1
151 | 5/5 | DA+6 | SANDY | 2025-08-20 | 43.8044 | COMPLETED | 2025-08-28 | Pritam Enterprises-4
152 | 6/7 | DA+1.5 | SANDY | 2025-08-22 | 37.1383 | COMPLETED | 2025-08-28 | Pritam Enterprises-2
153 | 5/10 | DA+9 | SANDY | 2025-08-22 | 45.697 | COMPLETED | 2025-08-28 | Jwala Singh-1
154 | 9/7 | DA+9 | SANDY | 2025-08-23 | 45.697 | COMPLETED | 2025-08-29 | Punam Kumari-2
155 | 33/7 | DA+6 | SANDY | 2025-08-23 | 43.8044 | COMPLETED | 2025-08-30 | Punam Kumari-1
156 | 31/4 | DA-1.5 | SANDY | 2025-08-22 | 35.6018 | COMPLETED | 2025-08-31 | SK.Samiul -2
157 | 5A/0 | DB1+12 | SANDY | 2025-08-22 | 70.7883 | COMPLETED | 2025-09-01 | Jwala Singh-2
158 | 32A/1 | DA+6 | SANDY | 2025-08-14 | 43.8044 | COMPLETED | 2025-09-02 | Amar Kumar Singh
159 | 6/9 | DA+6 | SANDY | 2025-08-23 | 43.8044 | COMPLETED | 2025-09-02 | Pritam Enterprises-2
160 | 2A/2 | DA+3 | SANDY | 2025-08-28 | 37.9311 | COMPLETED | 2025-09-02 | Pritam Enterprises-3
161 | 43/3 | DA-1.5 | SANDY | 2025-08-23 | 35.6018 | COMPLETED | 2025-09-02 | Fouzi Ratto
162 | 31/5 | DA+6 | SANDY | 2025-08-23 | 43.8044 | COMPLETED | 2025-09-03 | SK Samiul -1
163 | 31/9 | DA+1.5 | SANDY | 2025-08-23 | 37.1383 | COMPLETED | 2025-09-03 | Amit Kumar Singh
164 | 44/1 | DA+3 | SANDY | 2025-08-25 | 37.9311 | COMPLETED | 2025-09-03 | Ved Prakash
165 | 33/3 | DA+3 | SANDY | 2025-08-31 | 37.9311 | COMPLETED | 2025-09-04 | Punam Kumari-1
166 | 5/9 | DA+6 | SANDY | 2025-08-29 | 43.8044 | COMPLETED | 2025-09-05 | Jwala Singh-1
167 | 6/8 | DA+3 | SANDY | 2025-08-29 | 37.9311 | COMPLETED | 2025-09-06 | Pritam Enterprises-2
168 | 9/0 | DB1+12 | SANDY | 2025-08-30 | 70.7883 | COMPLETED | 2025-09-06 | Punam Kumari-2
169 | 4A/3 | DA+9 | SANDY | 2025-08-29 | 45.697 | COMPLETED | 2025-09-06 | Govind Mahto-1
170 | 43/4 | DA+0 | SANDY | 2025-09-03 | 36.1598 | COMPLETED | 2025-09-07 | Fouzi Ratto
171 | 5/4 | DA-1.5 | SANDY | 2025-08-29 | 35.6018 | COMPLETED | 2025-09-08 | Pritam Enterprises-4
172 | 2A/3 | DA+3 | SANDY | 2025-09-03 | 37.9311 | COMPLETED | 2025-09-08 | Pritam Enterprises-3
173 | 4A/5 | DA+9 | SANDY | 2025-08-25 | 45.697 | COMPLETED | 2025-09-08 | Govind Mahto-2
174 | 30/6 | DA+6 | SANDY | 2025-08-29 | 43.8044 | COMPLETED | 2025-09-08 | Punam Kumari-3
175 | 5/7 | DA+9 | SANDY | 2025-09-02 | 45.697 | COMPLETED | 2025-09-09 | Jwala Singh-2
176 | 44/2 | DA+3 | SANDY | 2025-09-04 | 37.9311 | COMPLETED | 2025-09-09 | Ved Prakash
177 | 33/4 | DA+3 | SANDY | 2025-09-05 | 37.9311 | COMPLETED | 2025-09-09 | Punam Kumari-1
178 | 33/1 | DA+9 | SANDY | 2025-08-25 | 45.697 | COMPLETED | 2025-09-10 | Bhairaw Mahto
179 | 3A/1 | DA+3 | SANDY | 2025-09-03 | 37.9311 | COMPLETED | 2025-09-11 | Pritam Enterprises-1
180 | 43/6 | DA+3 | SANDY | 2025-09-08 | 37.9311 | COMPLETED | 2025-09-11 | Fouzi Ratto
181 | 4/5 | DA+6 | SANDY | 2025-09-06 | 43.8044 | COMPLETED | 2025-09-12 | Jwala Singh-1
182 | 30/7 | DA-3 | SANDY | 2025-09-09 | 34.7898 | COMPLETED | 2025-09-13 | Punam Kumari-3
183 | 32/0 | DB2+0 | SANDY | 2025-09-04 | 59.5006 | COMPLETED | 2025-09-14 | Amit Kumar Singh
184 | 30/4 | DA+9 | SANDY | 2025-09-09 | 45.697 | COMPLETED | 2025-09-15 | Punam Kumari-4
185 | 18/0 | DB2+6 | SANDY | 2025-09-07 | 69.376 | COMPLETED | 2025-09-15 | Punam Kumari-2
186 | 2A/4 | DA+3 | SANDY | 2025-09-09 | 37.9311 | COMPLETED | 2025-09-15 | Pritam Enterprises-3
187 | 5/8 | DA+6 | SANDY | 2025-09-10 | 43.8044 | COMPLETED | 2025-09-15 | Jwala Singh-2
188 | 44/3 | DA+3 | SANDY | 2025-09-10 | 37.9311 | COMPLETED | 2025-09-15 | Ved Prakash
189 | 3A/5 | DA+3 | SANDY | 2025-09-07 | 37.9311 | COMPLETED | 2025-09-15 | Pritam Enterprises-2
190 | 4A/2 | DA+6 | SANDY | 2025-09-07 | 43.8044 | COMPLETED | 2025-09-16 | Govind Mahto-1
191 | 31/7 | DA+0 | SANDY | 2025-09-10 | 36.1598 | COMPLETED | 2025-09-16 | Punam Kumari-1
192 | 31/6 | DA+9 | SANDY | 2025-09-04 | 45.697 | COMPLETED | 2025-09-18 | SK Samiul -1
193 | 4A/6 | DA+9 | SANDY | 2025-09-09 | 45.697 | COMPLETED | 2025-09-18 | Govind Mahto-2
194 | 43/8 | DA+9 | SANDY | 2025-09-14 | 45.697 | COMPLETED | 2025-09-19 | Fouzi Ratto
195 | 44/4 | DA+0 | SANDY | 2025-09-16 | 36.1598 | COMPLETED | 2025-09-19 | Ved Prakash
196 | 3A/2 | DA+3 | SANDY | 2025-09-12 | 37.9311 | COMPLETED | 2025-09-19 | Pritam Enterprises-1
197 | 40A/0 | DB1+9 | SANDY | 2025-09-04 | 66.7809 | COMPLETED | 2025-09-20 | Kartik Mahto
198 | 33/0 | DB1+9 | SANDY | 2025-09-03 | 66.7809 | COMPLETED | 2025-09-20 | Amar Kumar Singh
199 | 18/1 | DA+3 | SANDY | 2025-09-16 | 37.9311 | COMPLETED | 2025-09-20 | Punam Kumari-2
200 | 31/8 | DA+0 | SANDY | 2025-09-15 | 36.1598 | COMPLETED | 2025-09-21 | Amit Kumar Singh
201 | 30/8 | DA+3 | SANDY | 2025-09-14 | 37.9311 | COMPLETED | 2025-09-22 | Punam Kumari-3
202 | 2A/5 | DA+3 | SANDY | 2025-09-16 | 37.9311 | COMPLETED | 2025-09-23 | Pritam Enterprises-3
203 | 44/5 | DA+0 | SANDY | 2025-09-20 | 36.1598 | COMPLETED | 2025-09-23 | Ved Prakash
204 | 3A/6 | DA+0 | SANDY | 2025-09-16 | 36.1598 | COMPLETED | 2025-09-24 | Pritam Enterprises-2
205 | 4A/0 | DB1+3 | SANDY | 2025-09-13 | 57.9632 | COMPLETED | 2025-09-24 | Jwala Singh-1
206 | 30/0 | DB1+0 | SANDY | 2025-09-11 | 55.4509 | COMPLETED | 2025-09-25 | Punam Kumari-4
207 | 5/1 | DA+6 | SANDY | 2025-09-13 | 43.8044 | COMPLETED | 2025-09-25 | Jwala Singh-2
208 | 4A/1 | DA+6 | SANDY | 2025-09-18 | 43.8044 | COMPLETED | 2025-09-25 | Govind Mahto-1
209 | 20/1 | DA-3 | SANDY | 2025-09-19 | 34.7898 | COMPLETED | 2025-09-25 | Punam Kumari-1
210 | 18/2 | DA+1.5 | SANDY | 2025-09-21 | 37.1383 | COMPLETED | 2025-09-25 | Punam Kumari-2
211 | 12/0 | DB1+9 | SANDY | 2025-09-11 | 66.7809 | COMPLETED | 2025-09-26 | Bhairaw Mahto
212 | 3A/3 | DA+0 | SANDY | 2025-09-20 | 36.1598 | COMPLETED | 2025-09-27 | Pritam Enterprises-1
213 | 43/7 | DA+0 | SANDY | 2025-09-24 | 36.1598 | COMPLETED | 2025-09-28 | Ved Prakash
214 | 44/0 | DB1+6 | SANDY | 2025-09-20 | 65.0278 | COMPLETED | 2025-09-29 | Fouzi Ratto
215 | 40/11 | DA+9 | SANDY | 2025-09-21 | 45.697 | COMPLETED | 2025-09-29 | Kartik Mahto
216 | 5/0 | DB1+6 | SANDY | 2025-09-19 | 65.0278 | COMPLETED | 2025-09-30 | Govind Mahto-2
217 | 20/2 | DA-3 | SANDY | 2025-09-26 | 34.7898 | COMPLETED | 2025-09-30 | Punam Kumari-1
218 | 18/3 | DA+6 | SANDY | 2025-09-26 | 43.8044 | COMPLETED | 2025-09-30 | Punam Kumari-2
219 | 2A/6 | DA+6 | SANDY | 2025-09-24 | 43.8044 | COMPLETED | 2025-09-30 | Pritam Enterprises-3
220 | 5/3 | DA+9 | SANDY | 2025-09-09 | 45.697 | COMPLETED | 2025-09-30 | Pritam Enterprises-4
221 | 5/2 | DA+9 | SANDY | 2025-09-26 | 45.697 | COMPLETED | 2025-09-30 | Jwala Singh-2