## Sept-25
ERECTION PRODUCTIVITY- TA-504 for the month of September-2025 | [44 empty] | DATE-14-09-2025
SL NO | SECTION INCHARGE | SUPERVISOR | Gang | Present Location |  |  | Next Towers |  |  | Start Date | End Date | No. of Days taken | Avg. Productivity per Day (MT) | Date wise Productivity | [29 empty] | Total Tonnage Completed | Remarks
|  |  |  | LOCATION NO | TYPE OF TOWER | WEIGHT IN MT | LOCATION NO | TYPE OF TOWER | WEIGHT IN MT |  |  |  |  | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30
1 | Khemchand | Teklal Mahto | Pinki Devi | 17/0 | DB2+0 | 59.5006 | 27/0 |  |  | 2025-08-25 | 2025-09-08 | 14 | 4.25 | 2025-09-01: 4; 2025-09-02: 4.2; 2025-09-03: 4.3; 2025-09-04: 5.1; 2025-09-05: 5.2; 2025-09-06: 2.2; 2025-09-07: 2.2; 2025-09-08: 3 | 30.2
2 | Khemchand | Nitesh Gupta | Ghanshyam Mahto | 23/2 | DA+0 | 36.1598 | 26/0 |  |  | 2025-08-26 | 2025-09-10 | 15 | 2.4107 | 2025-09-01: 2.2; 2025-09-02: 2.5; 2025-09-03: 2.7; 2025-09-04: 2; 2025-09-05: 2; 2025-09-06: 1.8; 2025-09-07: 2.5; 2025-09-08: 3.1 | 18.8
3 | Prasant Kumar | Teklal Mahto | Pinki Devi | 18/0 | DB1+9 | 66.7757 |  |  |  | 2025-09-09 | 2025-09-21 | 12 | 5.5646 | 2025-09-09: 3.2; 2025-09-10: 5.1; 2025-09-11: 5.5; 2025-09-12: 5.8; 2025-09-13: 5.8; 2025-09-14: 5.5; 2025-09-15: 5.9; 2025-09-16: 5.8; 2025-09-17: 6; 2025-09-18: 5.2; 2025-09-19: 5.9; 2025-09-20: 6; 2025-09-21: 1.1 | 66.8
4 | Prasant Kumar | Rahul Maharana | Neha Const. | 30/2 | DA+3 | 37.9311 |  |  |  | 2025-08-28 | 2025-09-17 | 20 | 1.8966 | 2025-09-01: 1; 2025-09-02: 1.5; 2025-09-03: 1.1; 2025-09-04: 1.3; 2025-09-05: 2.5; 2025-09-06: 1.6; 2025-09-07: 1.4; 2025-09-08: 3.2; 2025-09-09: 2.1; 2025-09-10: 2.5; 2025-09-11: 2.2; 2025-09-12: 2.3; 2025-09-13: 1.8; 2025-09-14: 1.1; 2025-09-15: 1; 2025-09-16: 1.2; 2025-09-17: 1.5 | 29.3
5 | Prasant Kumar | Akhtar | Sainik Traders | 11/0 | DB2+0 | 59.5006 |  |  |  | 2025-09-03 | 2025-09-22 | 19 | 3.1316 |  |  | 3.1316 | 3.1316 | 3.1316 | 3.1316 | 3.1316 | 3.1316 | 3.1316 | 3.1316 | 3.1316 | 3.1316 | 3.1316 | 3.1316 | 3.1316 | 3.1316 | 3.1316 | 3.1316 | 3.1316 | 3.1316 | 3.1316 | 3.1316 | [8 empty] | 62.6322
6 | Prasant Kumar | Ashutosh | Karam Const. | 13/1 | DA+0 | 36.1598 |  |  |  | 2025-08-28 | 2025-09-25 | 28 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | 1.2914 | [5 empty] | 32.2855
7 | Prasant Kumar | Teklal Mahto | Pinki Devi | 16/3 | DB1+6 | 65.0226 |  |  |  | 2025-09-21 | 2025-09-29 | 8 | 8.1278 | 2025-09-21: 8.1278; 2025-09-22: 8.1278; 2025-09-23: 8.1278; 2025-09-24: 8.1278; 2025-09-25: 8.1278; 2025-09-26: 8.1278; 2025-09-27: 8.1278; 2025-09-28: 8.1278; 2025-09-29: 8.1278 | 73.1504
8 | Prasant Kumar | Nitesh Gupta | Ghyansham Mahto | 24/1 | DB1+9 | 66.7757 |  |  |  | 2025-09-10 | 2025-09-26 | 16 | 4.1735 | 2025-09-10: 4.1735; 2025-09-11: 4.1735; 2025-09-12: 4.1735; 2025-09-13: 4.1735; 2025-09-14: 4.1735; 2025-09-15: 4.1735; 2025-09-16: 4.1735; 2025-09-17: 4.1735; 2025-09-18: 4.1735; 2025-09-19: 4.1735; 2025-09-20: 4.1735; 2025-09-21: 4.1735; 2025-09-22: 4.1735; 2025-09-23: 4.1735; 2025-09-24: 4.1735; 2025-09-25: 4.1735; 2025-09-26: 4.1735 | 70.9492
9 | Prasant Kumar | Rahul Maharana | Neha Const. | 29/2 | DA+0 | 36.1598 |  |  |  | 2025-09-18 | 2025-09-26 | 8 | 4.52 | 2025-09-18: 4.52; 2025-09-19: 4.52; 2025-09-20: 4.52; 2025-09-21: 4.52; 2025-09-22: 4.52; 2025-09-23: 4.52; 2025-09-24: 4.52; 2025-09-25: 4.52; 2025-09-26: 4.52 | 40.6797
| Prasant Kumar | [10 empty] | 0 | [31 empty] | 0
[6 empty] | 463.9856 | [7 empty] | 8.4914 | 9.4914 | 12.523 | 12.823 | 14.123 | 10.023 | 10.523 | 13.723 | 9.723 | 16.1965 | 16.2965 | 16.6965 | 16.1965 | 15.1965 | 15.4965 | 15.5965 | 16.0965 | 18.3165 | 19.0165 | 19.1165 | 22.3443 | 21.2443 | 18.1127 | 18.1127 | 18.1127 | 16.8213 | 8.1278 | 8.1278 | 8.1278 | 0 | 424.797

## Oct-25
Sl. No. | Gang Name | LOCATION NO | TYPE OF TOWER | WEIGHT IN MT | LOCATION NO | TYPE OF TOWER | WEIGHT IN MT | Starting Date | Ending Date | No of Days Taken | Productivity per Day | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30
1 | Sainik Traders | 12/0 | DB2+0 | 59.5006 |  |  |  | 2025-09-22 | 2025-10-08 | 17 | 3.5 | [30 empty] | 0
2 | Pinki Devi | 21/0 | DB2+6 | 69.376 |  |  |  | 2025-09-30 | 2025-10-09 | 10 | 6.9376 | [30 empty] | 0
3 | Karam Mahto | 30/4 | DA+3 | 37.9311 |  |  |  | 2025-09-26 | 2025-10-09 | 14 | 2.7094 | [30 empty] | 0
4 | Ghyansham Mahto | 24/0 | DB2+0 | 59.5 |  |  |  | 2025-09-27 | 2025-10-16 | 20 | 2.975 | [30 empty] | 0
5 | Pinki Devi | 27/1 | DA+3 | 37.93 |  |  |  | 2025-10-10 | 2025-10-16 | 7 | 5.4186 | [30 empty] | 0
6 | Karam Mahto | 30/5 | DA+0 | 36.1598 |  |  |  | 2025-10-10 | 2025-10-18 | 9 | 4.0178 | [30 empty] | 0
7 | Pinki Devi | 26/4 | DA-3 | 34.7898 |  |  |  | 2025-10-17 | 2025-10-24 | 8 | 4.3487 | [30 empty] | 0
[10 empty] | 0 | [31 empty] | 0
|  |  |  | 335.1872 | [5 empty] | 85 | 3.9434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0