## FDN
Project Code |  |  | TA-504
Sl | Location No | Tower type | Classification | Conc. Vol (CuM) | Reinf (MT)
1 | 25/1 | DA+0 | DFR | 30.22 | 1.45
2 | 25/2 | DA+0 | DFR | 30.22 | 1.45
3 | 26/2 | DA+3 | DFR | 34.29 | 1.8
4 | 32/1 | DA+6 | DFR | 34.29 | 1.8
5 | 31/1 | DA+6 | DFR | 34.29 | 1.8
6 | 9/0 | DD60+35 | DFR | 135.67 | 11.2
7 | 10/0 | DD60+35 | DFR | 135.67 | 11.2
8 | 13/2 | DA+0 | DFR | 30.22 | 1.45
9 | 14/1 | DA+0 | DFR | 30.22 | 1.45
10 | 10/4 | DA+3 | DFR | 34.29 | 1.8
11 | 11/6 | DA+0 | DFR | 30.22 | 1.45
|  |  |  | 464.87 | 32.15
Note: *With Subject to the Clearance of ROW Clearance & Statutory Clearance i) Hold from Gantry to 11/0 -> 32 loc, ii) Hold Lilo line->23 loc, iii)Forest location-> 3

## ERE
Project Code |  |  | TA-504
Sl No. | Location No | Tower type | Tower Weight (MT)
1 | 11/5 | DA+3 | 37.9311
2 | 13/0 | DB2+0 | 59.5006
3 | 22/0 | DD45+0 | 73.2445
4 | 26/9 | DA+0 | 36.1598
5 | 30/1 | DA+9 | 45.697
6 | 14/0 | DD45+0 | 73.2445
7 | 16/4 | DA+9 | 45.697
8 | 19/2 | DA+3 | 37.9311
9 | 23/0 | DC2+3 | 70.7447
10 | 26/0 | DC2+0 | 67.2617
11 | 26/7 | DA+0 | 36.1598
12 | 26/10 | DA+0 | 36.1598
13 | 27/0 | DC1+0 | 62.4437
14 | 28/0 | DC1+0 | 62.4437
15 | 30/0 | DC2+0 | 67.2617
16 | 30/3 | DA+9 | 45.697
17 | 31/0 | DD45+0 | 73.2445
18 | 31/2 | DB1+6 | 65.0226
19 | 32/0 | DB1+0 | 55.4509
20 | 32/2 | DB1+9 | 66.7757
21 | 33/0 | DC2+0 | 67.2617
1185.3332

## Micro Plan Dec-24 TA-504 (hidden)
Project Code |  |  | TA-504
Name of Line |  |  | 765KV D/C RISHABDEO MANDSAUR (PKG-E)
Activity |  |  | Foundation | Qty | [7 empty] | Foundation status of 765KV D/C RISHABDEO MANDSAUR (PKG-E) |  | Qty.
|  |  | Total | 176 | [7 empty] | Total location |  | 179
|  |  | Completed (Upto Nov-24) | 63 | [7 empty] | As per L2 (Till Dec'24) |  | 31
|  |  | Balance | 113 | [7 empty] | Actual executed till date |  | 63
[12 empty] | Target of Dec'24 |  | 26
Micro Plan for month |  |  | 2024-12-01 | 26 | Nos | 25000375.3651 |  | Rs. Cr. |  |  |  | Completed in Nov'24 |  | 36
Achievement for Month |  |  | Wk-1 | 0 | 0% | 0 |  | 0%
|  |  | Wk-2 | 0 | 0% | 0 |  | 0%
|  |  | Wk-3 | 0 | 0% | 0 |  | 0%
|  |  | Wk-4 | 0 | 0% | 0 |  | 0%
|  |  | Wk-5 | 0 | 0% | 0 |  | 0%
Actual for the Month |  |  | Total | 0 | 0 | 0 |  | 0
25000375.3651
Sl | Loc No. | Tower type | Classification | Conc. Vol (CuM) | Reinf (MT) | Sub-Cont |  | Work Plan | [9 empty] | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[7 empty] | Manpower (nos) | Excavation |  | Stub-setting |  | Concreting |  | Earthing | Backfilling | SITE ENG. | SITE SUPERVISOR |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[8 empty] | Start | End | Start | End | Start | End |  |  |  |  | Rs. | Date | [11 empty] | Rs. Lacs. | Rs. Lacs.
1 | 16/0 | DB2+0 | DFR | 76.03 | 3.3996 | Gang-1 | 15 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-03 | 2024-12-04 | 2024-12-05 | Mr. Khemchand | Mr. Anil Yadav & Mr. Rakesh Chotala | 1308130.6061 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1308130.6061
2 | 15/0 | DB1+0 | DFR | 63.24 | 2.72 |  |  | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10 | 2024-12-13 | 2024-12-14 | 2024-12-15 | Mr. Khemchand | Mr. Anil Yadav & Mr. Rakesh Chotala | 1085272.0332 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085272.0332
3 | 15/1 | DA+3 | DFR | 52.23 | 1.802 |  |  | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | Mr. Khemchand | Mr. Anil Yadav & Mr. Rakesh Chotala | 515483.346 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515483.346
4 | 19/0 | DD45+0 | DFR | 101.56 | 8.6688 |  |  | 2024-12-21 | 2024-12-22 | 2024-12-23 | 2024-12-25 | 2024-12-26 | 2024-12-30 | 2024-12-31 | 2025-01-01 | Mr. Khemchand | Mr. Anil Yadav & Mr. Rakesh Chotala | 1681855.5515 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1681855.5515
5 | 17/4 | DB1+9 | DFR | 63.78 | 2.6904 | Gang-2 | 15 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-12 | 2024-12-13 | 2024-12-14 | Mr. Khemchand | Mr. Anil Yadav & Mr. Rakesh Chotala | 1085272.0332 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085272.0332
6 | 17/5 | DA+9 | DFR | 52.23 | 1.802 |  |  | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-19 | 2024-12-20 | 2024-12-21 | Mr. Khemchand | Mr. Anil Yadav & Mr. Rakesh Chotala | 515483.346 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515483.346
7 | 17/6 | DA+3 | DFR | 52.23 | 1.802 |  |  | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | Mr. Khemchand | Mr. Anil Yadav & Mr. Rakesh Chotala | 515483.346 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515483.346
8 | 20/0 | DD45+6 | DFR | 103.79 | 9.0944 |  |  | 2024-12-22 | 2024-12-23 | 2024-12-24 | 2024-12-26 | 2024-12-27 | 2024-12-30 | 2024-12-31 | 2025-01-01 | Mr. Khemchand | Mr. Anil Yadav & Mr. Rakesh Chotala | 1781855.5515 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1781855.5515
9 | 21/0 | DB2+6 | DFR | 76.69 | 3.466 | Gang-3 | 15 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-11 | 2024-12-12 | 2024-12-13 | Mr. Khemchand | Mr. Anil Yadav & Mr. Rakesh Chotala | 1332876.522 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332876.522
10 | AP24 | DB2+0 | DFR | 76.03 | 3.3996 |  |  | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-18 | 2024-12-19 | 2024-12-20 | Mr. Khemchand | Mr. Anil Yadav & Mr. Rakesh Chotala | 1308130.6061 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1308130.6061
11 | 25/1 | DA+0 | DFR | 30.22 | 1.45 |  |  | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | Mr. Khemchand | Mr. Anil Yadav & Mr. Rakesh Chotala | 487106.102 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487106.102
12 | 25/2 | DA+0 | DFR | 30.22 | 1.45 |  |  | 2024-12-21 | 2024-12-22 | 2024-12-23 | 2024-12-25 | 2024-12-26 | 2024-12-29 | 2024-12-30 | 2024-12-31 | Mr. Khemchand | Mr. Anil Yadav & Mr. Rakesh Chotala | 487106.102 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487106.102
13 | 26/0 | DC2+0 | DFR | 101.79 | 4.5456 |  |  | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2024-12-30 | 2024-12-31 | 2025-01-01 | Mr. Khemchand | Mr. Anil Yadav & Mr. Rakesh Chotala | 1413793.5931 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1413793.5931
14 | 26/2 | DA+3 | DFR | 52.23 | 1.802 | Gang-4 | 15 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10 | Rajkumar | Mr. Ram shekar & Mulchand | 515483.346 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515483.346
15 | 26/10 | DA+0 | DFR | 30.22 | 1.45 |  |  | 2024-12-09 | 2024-12-10 | 2024-12-11 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | Rajkumar | Mr. Ram shekar & Mulchand | 487106.102 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487106.102
16 | 27/0 | DC1+0 | DFR | 82.67 | 3.8976 |  |  | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-18 | 2024-12-19 | 2024-12-22 | 2024-12-23 | 2024-12-24 | Rajkumar | Mr. Ram shekar & Mulchand | 1363793.5931 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1363793.5931
17 | 27/1 | DA+3 | DFR | 52.23 | 1.802 |  |  | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-27 | 2024-12-27 | 2024-12-28 | 2024-12-29 | 2024-12-30 | Rajkumar | Mr. Ram shekar & Mulchand | 515483.346 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515483.346
18 | 30/0 | DC2+0 | DFR | 101.79 | 4.5456 | Gang-5 | 15 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-08 | 2024-12-09 | 2024-12-12 | 2024-12-13 | 2024-12-14 | Rajkumar | Mr. Ram shekar & Mulchand | 1413793.5931 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1413793.5931
19 | 30/1 | DA+9 | DFR | 52.23 | 1.802 |  |  | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-19 | 2024-12-20 | 2024-12-21 | Rajkumar | Mr. Ram shekar & Mulchand | 515483.346 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515483.346
20 | 30/2 | DA+3 | DFR | 52.23 | 1.802 |  |  | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | Rajkumar | Mr. Ram shekar & Mulchand | 515483.346 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515483.346
21 | 30/3 | DA+9 | DFR | 52.23 | 1.802 |  |  | 2024-12-22 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2024-12-29 | Rajkumar | Mr. Ram shekar & Mulchand | 515483.346 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515483.346
22 | 30/4 | DA+3 | DFR | 52.23 | 1.802 |  |  | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2024-12-30 | 2024-12-31 | 2025-01-01 | Rajkumar | Mr. Ram shekar & Mulchand | 515483.346 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515483.346
23 | 30/5 | DA+0 | DFR | 30.22 | 1.45 | Gang-6 | 15 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10 | 2024-12-11 | Rajkumar | Mr. Ram shekar & Mulchand | 487106.102 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487106.102
24 | 31/0 | DD45+0 | DFR | 101.56 | 8.6688 |  |  | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-18 | 2024-12-19 | 2024-12-20 | Rajkumar | Mr. Ram shekar & Mulchand | 1681855.5515 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1681855.5515
25 | 31/1 | DA+6 | DFR | 52.23 | 1.802 |  |  | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | Rajkumar | Mr. Ram shekar & Mulchand | 515483.346 | [13 empty] | 515483.346
25 | 32/2 | DB1+9 | DFR | 63.78 | 2.6904 |  |  | 2024-12-21 | 2024-12-22 | 2024-12-23 | 2024-12-25 | 2024-12-26 | 2024-12-29 | 2024-12-30 | 2024-12-31 | Rajkumar | Mr. Ram shekar & Mulchand | 1085272.0332 | [13 empty] | 1085272.0332
26 | 33/0 | DC2+0 | DFR | 101.79 | 4.5456 |  |  | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-30 | 2024-12-31 | 2025-01-01 | Rajkumar | Mr. Ram shekar & Mulchand | 1355216.2296 | [13 empty] | 1355216.2296
[7 empty] | 90 | [10 empty] | 25000375.3651 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000375.3651
35
Note: i) Hold from Gantry to 13/40-> 49 loc, ii) Hold Lilo line->23 loc, iii)Forest location-> 5 loc, iv) Cross arm strengthening--> 6 loc, v)Hold due canal avoiding--> 3 loc , vi) RC location-> 3 loc, vii) Hold due to Opium crop (15/1), ROW location-5 loc, viii) AP-26 to AP 33 hold by SDM Pratapgarh-15 loc, Total hold location-110 loc, Completed-63 loc. Balance work front 6 loc ( 14/0, 15/0, 16/0, 19/0,20/0, 21/0)
Formulas:
End = +[Work Plan]+1
End = +[Stub-setting]+1
Stub-setting = 1+[End]
Concreting = 1+[End]
Qty. = [End]+1
Backfilling = +[Qty.]+1

## Micro Plan-Nov24 TA-504 (hidden)
Project Code |  |  | TA-504
Name of Line |  |  | 765KV D/C RISHABDEO MANDSAUR (PKG-E)
Activity |  |  | Foundation | Qty
|  |  | Total | 175
|  |  | Completed (Upto Oct-24) | 27
|  |  | Balance | 148
Micro Plan for month |  |  | 2024-11-01 | 40 | Nos | 27161598.38 |  | Rs. Cr.
Achievement for Month |  |  | Wk-1 | 0 | 0% | 0 |  | 0%
|  |  | Wk-2 | 0 | 0% | 0 |  | 0%
|  |  | Wk-3 | 0 | 0% | 0 |  | 0%
|  |  | Wk-4 | 0 | 0% | 0 |  | 0%
|  |  | Wk-5 | 0 | 0% | 0 |  | 0%
Actual for the Month |  |  | Total | 0 | 0 | 0 |  | 0
Sl | Loc No. | Tower type | Classification | Conc. Vol (CuM) | Reinf (MT) | Sub-Cont |  | Work Plan | [7 empty] | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[7 empty] | Manpower (nos) | Excavation |  | Stub-setting |  | Concreting |  | Earthing | Backfilling |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[8 empty] | Start | End | Start | End | Start | End |  |  | Rs. Lacs. | Date | [11 empty] | Rs. Lacs. | Rs. Lacs.
1 | 14/6 | DA+0 | DFR | 30.22 | 1.4496 | Tuliya Mama Const. |  | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-05 | 2024-11-06 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
2 | 14/5 | DA+3 | DFR | 30.22 | 1.4496 |  |  | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-07 | 2024-11-08 | 2024-11-10 | 2024-11-11 | 2024-11-12 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
3 | 14/4 | DA+0 | DFR | 30.22 | 1.4496 |  | 12 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-09 | 2024-11-10 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
4 | 14/7 | DA+3 | DFR | 34.29 | 1.802 |  |  | 2024-11-15 | 2024-11-16 | 2024-11-17 | 2024-11-19 | 2024-11-20 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
5 | 14/2 | DA+0 | DFR | 30.22 | 1.4496 |  |  | 2024-11-17 | 2024-11-18 | 2024-11-19 | 2024-11-21 | 2024-11-22 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
6 | 14/1 | DA+0 | DFR | 30.22 | 1.4496 |  |  | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-23 | 2024-11-24 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
7 | 15/4 | DA+3 | DFR | 34.29 | 1.802 | Bhagat Singh Anjana |  | 2024-11-01 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-09 | 2024-11-10 | 2024-11-11 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
8 | 15/3 | DA+0 | DFR | 30.22 | 1.4496 |  |  | 2024-11-04 | 2024-11-06 | 2024-11-07 | 2024-11-09 | 2024-11-10 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
9 | 15/2 | DA+3 | DFR | 34.29 | 1.802 |  | 12 | 2024-11-07 | 2024-11-09 | 2024-11-10 | 2024-11-12 | 2024-11-13 | 2024-11-16 | 2024-11-17 | 2024-11-18 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
10 | 15/5 | DA-3 | DFR | 30.22 | 1.4496 |  |  | 2024-11-16 | 2024-11-18 | 2024-11-19 | 2024-11-21 | 2024-11-22 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
11 | 15/6 | DA+3 | DFR | 34.29 | 1.802 |  |  | 2024-11-19 | 2024-11-21 | 2024-11-22 | 2024-11-24 | 2024-11-25 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
12 | 17/7 | DA+9 | DFR | 30.22 | 1.4496 | Siyaram Infra |  | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-05 | 2024-11-06 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
13 | 17/6 | DA+0 | DFR | 30.22 | 1.4496 |  |  | 2024-11-03 | 2024-11-05 | 2024-11-06 | 2024-11-08 | 2024-11-09 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
14 | 17/5 | DA+3 | DFR | 34.29 | 1.802 |  |  | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-10 | 2024-11-11 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
15 | 17/4 | DA+3 | DFR | 34.29 | 1.802 |  | Two Gang | 2024-11-16 | 2024-11-19 | 2024-11-20 | 2024-11-22 | 2024-11-23 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
16 | 17/3 | DA+3 | DFR | 34.29 | 1.802 |  | 25 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-24 | 2024-11-25 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
17 | 17/2 | DA+0 | DFR | 30.22 | 1.4496 |  |  | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-26 | 2024-11-27 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
18 | 17/1 | DA+3 | DFR | 34.29 | 1.802 |  |  | 2024-11-16 | 2024-11-19 | 2024-11-20 | 2024-11-22 | 2024-11-23 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
19 | 15/7 | DA+6 | DFR | 34.29 | 1.802 |  |  | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-24 | 2024-11-25 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
20 | 15/1 | DA+3 | DFR | 34.29 | 1.802 |  |  | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-26 | 2024-11-27 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
21 | 16/2 | DA-3 | DFR | 30.22 | 1.4496 | Shree Shyam |  | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
22 | 16/6 | DA-3 | DFR | 30.22 | 1.4496 |  |  | 2024-11-03 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-10 | 2024-11-11 | 2024-11-12 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
23 | 18/2 | DA+0 | DFR | 30.22 | 1.4496 |  | 18 | 2024-11-06 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-11 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
24 | 18/5 | DA+3 | DFR | 34.29 | 1.802 |  |  | 2024-11-16 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
25 | 19/1 | DA+3 | DFR | 34.29 | 1.802 |  |  | 2024-11-19 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
26 | 19/2 | DA+3 | DFR | 34.29 | 1.802 |  |  | 2024-11-22 | 2024-11-23 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
27 | 25/1 | DA+0 | DFR | 30.22 | 1.4496 | RST |  | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-05 | 2024-11-06 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
28 | 21/4 | DA+3 | DFR | 30.22 | 1.4496 |  |  | 2024-11-03 | 2024-11-05 | 2024-11-06 | 2024-11-08 | 2024-11-09 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
29 | 23/3 | DA+6 | DFR | 34.29 | 1.802 |  | Two Gang | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-10 | 2024-11-11 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
30 | 23/4 | DA-1.5 | DFR | 30.22 | 1.4496 |  | 30 | 2024-11-16 | 2024-11-19 | 2024-11-20 | 2024-11-22 | 2024-11-23 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
31 | 23/5 | DA+3 | DFR | 34.29 | 1.802 |  |  | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-24 | 2024-11-25 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
32 | 23/6 | DA-3 | DFR | 30.22 | 1.4496 |  |  | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-26 | 2024-11-27 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
33 | 23/7 | DA-3 | DFR | 30.22 | 1.4496 |  |  | 2024-11-16 | 2024-11-19 | 2024-11-20 | 2024-11-22 | 2024-11-23 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
34 | 21/1 | DA+0 | DFR | 30.22 | 1.4496 |  |  | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-24 | 2024-11-25 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
35 | 21/2 | DA+3 | DFR | 34.29 | 1.802 |  |  | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-26 | 2024-11-27 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
36 | 26/7 | DA+0 | DFR | 30.22 | 1.4496 | Vindhya Const. |  | 2024-11-01 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-09 | 2024-11-10 | 2024-11-11 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
37 | 25/2 | DA+0 | DFR | 30.22 | 1.4496 |  |  | 2024-11-04 | 2024-11-06 | 2024-11-07 | 2024-11-09 | 2024-11-10 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
38 | 26/2 | DA+3 | DFR | 34.29 | 1.802 |  | 12 | 2024-11-07 | 2024-11-09 | 2024-11-10 | 2024-11-12 | 2024-11-13 | 2024-11-16 | 2024-11-17 | 2024-11-18 | 728174.957 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728174.957
39 | 26/8 | DA+0 | DFR | 30.22 | 1.4496 |  |  | 2024-11-16 | 2024-11-18 | 2024-11-19 | 2024-11-21 | 2024-11-22 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
40 | 26/9 | DA+0 | DFR | 30.22 | 1.4496 |  |  | 2024-11-19 | 2024-11-21 | 2024-11-22 | 2024-11-24 | 2024-11-25 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 629904.962 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629904.962
|  |  |  | 1277.99 | 63.9748 |  | 109 | [8 empty] | 27161598.38 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27161598.38
[5 empty] | 13 | 40

## Sheet1 (hidden)
Sl | Activity | Quantity | CuM / MT | Revenue (Cr.)
1 | Foundation | 40 Nos. | Concrete 1290 (CuM) | 2.7162
2 | Erection | 0 Nos. | Tonnage 0 (MT) | 0
3 | Stringing | Km | -
Total 2.72 Cr.

## Stub dispatch (hidden)
Location | Project | Tower type | Structure | B LOT | Actual PRS Date | STEEL Wt (MT) | BNA Wt | Disp Bal | May'24 Disp Plan | Wk01 | WK02 | WK03 | WK04 | Jun'24 Disp Plan MT | July'24 Disp Plan | Remark
JPR | TA416 | DA | Stub - 28 Nos | TA416-00018 | 2024-04-11 | 26.8617 | 0.46323 | 26.8617 | 0 |  |  |  | 0 | 26.8617 | 0 | As on date 160 stub reieved.
JPR | TA416 | DA | Stub - 132 Nos | TA416-00026 | 2024-04-15 | 126.634 | 2.184 | 126.634 | [5 empty] | 126.634 | 0
Total |  |  | 160 | [10 empty] | 153.4957

## STG-July24 (hidden)
Project Code
Name of Line
Activity |  |  | Stringing | Qty
Total
Completed (Apr-24)
|  |  | Balance | 0
Micro Plan for month |  |  | 2024-05-01 |  | km | 0 | Rs. Cr
Achievement for Month |  |  | Wk-1 | 0 | #DIV/0! | 0 | #DIV/0!
|  |  | Wk-2 | 0 | #DIV/0! | 0 | #DIV/0!
|  |  | Wk-3 | 0 | #DIV/0! | 0 | #DIV/0!
|  |  | Wk-4 | 0 | #DIV/0! | 0 | #DIV/0!
|  |  | Wk-5 | 0 | #DIV/0! | 0 | #DIV/0!
|  |  | Total | 0 | #DIV/0! | 0 | #DIV/0!
Sl | Section | Section Length (km) | Manual/TSE | Sub-Cont | Work Plan |  |  |  |  | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[5 empty] | Matl feeding | Pay-Out |  | Final Sag |  |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[6 empty] | Start | End | Start | End | Rs. Cr. | Date | [11 empty] | Rs. Cr. | Rs. Cr.
1 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0