## Stringing - PKG-G
S.no | from_ap | to_ap | length_m | po_start_date | po_completion_date | month | fs_starting_date | fs_complete_date | month__2 | gang_name | project_code | line_name | project_name | project_display | project_scope_key | project | _source_file | source_sheet | method | method_inferred | method_inference_reason | erection_locations_for_method | number_of_tse | po
1 | 57/6 | 58/0 | 3.141 | 06.05.2024 | 10.05.24 | 2024-05-24 | 19.05.24 | 24.05.24 | 2024-05-24 | GPJ Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
2 | 57/0 | 57/6 | 2.344 | 16.05.24 | 24.05.24 | 2024-05-24 | 07.06.24 | 12.06.24 | 2024-06-24 | GPJ Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
3 | 56/0 | 57/0 | 4.127 | 04.06.24 | 12.06.24 | 2024-06-24 | 28.06.24 | 04.07.24 | 2024-07-24 | GPJ Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
4 | 55/0 | 56/0 | 4.9 | 25.06.24 | 04.07.24 | 2024-07-24 | 17.07.24 | 22.07.24 | 2024-07-24 | GPJ Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
5 | 53/0 | 55/0 | 2.013 | 16.07.24 | 22.07.24 | 2024-07-24 | 09.08.24 | 10.08.24 | 2024-08-24 | GPJ Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
6 | 52/0 | 53/0 | 2.364 | 19.08.24 | 22.08.24 | 2024-08-24 | 04.09.24 | 09.09.24 | 2024-09-24 | GPJ Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
7 | 51/0 | 52/0 | 4.403 | 01.09.24 | 08.09.24 | 2024-09-24 | 28.09.24 | 05.10.24 | 2024-10-24 | GPJ Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
8 | 50/0 | 51/0 | 1.971 | 26.9.24 | 02.10.24 | 2024-10-24 | 08.10.24 | 10.10.24 | 2024-10-24 | GPJ Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
9 | 72/7 | 73/0 | 0.49623 | 12.11.24 | 15.11.24 | 2024-11-24 | 27.11.24 | 29.11.24 | 2024-11-24 | MR Power | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
10 | 58/0 | 58/7 | 2.797 | 20.11.24 | 23.11.24 | 2024-11-24 | 01.12.245 | 05.12.24 | 2024-12-24 | Kddus Ali | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
11 | 72/0 | 72/7 | 2.589 | 18.11.24 | 23.11.24 | 2024-11-24 | 06.12.24 | 10.12.24 | 2024-12-24 | MR Power | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
12 | 67/1 | 68/0 | 0.42647 | 22.12.24 | 23.12.24 | 2024-12-24 | 23.12.24 | 25.12.25 | 2024-12-24 | Nasruddin | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
13 | 68/0 | 69/0 | 2.855 | 11.12.24 | 20.12.24 | 2024-12-24 | 01.01.25 | 05.01.25 | 2025-01-25 | Nasruddin | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
14 | 58/7 | 59/0 | 3.885 | 27.12.24 | 04.01.25 | 2025-01-25 | 07.01.25 | 09.01.25 | 2025-01-25 | MR Power | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
15 | 71/0 | 72/0 | 2.092 | 03.12.24 | 10.12.24 | 2024-12-24 | 16.01.25 | 19.01.25 | 2025-01-25 | MR Power | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
16 | 67/0 | 67/1 | 0.43755 | 21.12.24 | 22.12.24 | 2024-12-24 | 20.01.25 | 21.01.25 | 2025-01-25 | Nasruddin | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
17 | 69/0 | 70/0 | 3.881 | 30.12.24 | 05.01.25 | 2025-01-25 | 27.01.25 | 28.01.25 | 2025-01-25 | Nasruddin | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
18 | 41/0 | 42/0 | 4.981 | 13.02.25 | 20.02.25 | 2025-02-25 | 28.02.25 | 02.03.25 | 2025-03-25 | Nasruddin | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
19 | 59/0 | 60/0 | 2.581 | 20.01.25 | 25.01.25 | 2025-01-25 | 02.05.25 | 04.05.25 | 2025-05-25 | MR Power | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
20 | 42/0 | 43/0 | 0.489 | 04.05.25 | 11.05.25 | 2025-05-25 | 07.05.25 | 11.05.25 | 2025-05-25 | Indrajeet | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
21 | 49/0 | 50/0 | 0.241 | 15.05.25 | 17.05.25 | 2025-05-25 | 15.05.25 | 17.05.25 | 2025-05-25 | Indrajeet | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
22 | 48/0 | 49/0 | 1.162 | 14.05.25 | 17.05.25 | 2025-05-25 | 19.05.25 | 21.05.25 | 2025-05-25 | Indrajeet | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
23 | 47/0 | 48/0 | 1.274 | 19.05.25 | 21.05.25 | 2025-05-25 | 25.05.25 | 29.05.25 | 2025-05-25 | Indrajeet | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
24 | 37/2 | 38/0 | 2.71 | 24.05.25 | 30.05.25 | 2025-05-25 | 11.06.25 | 15.06.25 | 2025-06-25 | Indrajeet | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
25 | 43/0 | 44/0 | 2.856 | 05.05.25 | 10.05.25 | 2025-05-25 | 20.06.25 | 25.06.25 | 2025-06-25 | Indrajeet | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
26 | 61/0 | 62/0 | 1.028 | 27.06.25 | 29.6.25 | 2025-06-25 | 07.07.25 | 10.07.25 | Jul | GPJ Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
27 | 62/0 | 63/0 | 0.221 | 07.07.25 | 10.07.25 | Jul | 07.07.25 | 10.07.25 | Jul | GPJ Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
28 | 38/0 | 38/9 | 3.215 | 04.06.25 | 10.06.25 | 2025-06-25 | 07.07.25 | 13.7.25 | Jul | Indrajeet | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
29 | 40/10 | 41/0 | 1.073 | 02.07.25 | 05.07.25 | Jul | 24.07.25 | 28.07.25 | Jul | Indrajeet/Rahim | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
30 | 63/0 | 64/0 | 2.879 | 24.07.25 | 28.07.25 | Jul | 31.07.25 | 02.08.25 | Aug | GPJ Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
31 | 39/0 | 40/0 | 2.744 | 30.07.25 | 06.08.25 | Aug | 09.08.25 | 12.08.25 | Aug | Amir Sheikh | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
32 | 40/5 | 40/10 | 1.897 | 11.07.25 | 20.07.25 | Jul | 10.08.25 | 16.08.25 | Aug | Indrajeet/Rahim | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
33 | 38/9 | 39/0 | 0.544 | 04.07.25 | 11.07.25 | Jul | 19.08.25 | 23.08.25 | Aug | Indrajeet/Mohan/Amir Sheikh | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
34 | 40/0 | 40/2 | 0.652 | 28.07.25 | 01.08.25 | Aug | 23.08.25 | 31.08.25 | Aug | Rahim Khan | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
35 | 40/2 | 40/5 | 1.219 | 08.08.25 | 14.08.25 | Aug | 23.08.25 | 31.08.25 | Aug | Rahim Khan | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
36 | 66/0 | 67/0 | 2.028 | 04.09.25 | 10.09.25 | 2025-09-25 | 13.09.25 | 16.09.25 | sept | MC Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
37 | 35/0 | 36/0 | 3.604 | 07.09.25 | 14.09.25 | 2025-09-25 | 18.09.25 | 23.09.25 | sept | Amir Sheikh | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
38 | 46/0 | 47/0 | 1.728 | 22.06.25 | 27.06.25 | 2025-06-25 | 04.10.25 | 09.10.25 | 2025-10-25 | Indrajeet | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
39 | 31/0 | 32/0 | 1.678 | 18.09.25 | 24.09.25 | 2025-09-25 | 07.10.25 | 14.10.25 | 2025-10-25 | Krishna Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
40 | 44/0 | 45/0 | 2.459 | 13.06.25 | 18.06.25 | 2025-06-25 | 12.10.25 | 17.10.25 | 2025-10-25 | Indrajeet | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
41 | Gantry | 1/0 | 0.12293 | 08.10.25 | 17.10.25 | 2025-10-25 | 09.10.25 | 17.10.25 | 2025-10-25 | Devi Power | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
42 | 65/0 | 66/0 | 2.966 | 04.10.25 | 06.10.25 | 2025-10-25 | 13.10.25 | 18.10.25 | 2025-10-25 | MC Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
43 | 1/0 | 1A/0 | 0.1 | 04.10.25 | 06.10.25 | 2025-10-25 | 12.10.25 | 21.10.25 | 2025-10-25 | Devi Power | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
44 | 1A/0 | 2/0 | 3.187 | 10.10.25 | 17.10.25 | 2025-10-25 | 23.10.25 | 25.10.25 | 2025-10-25 | Devi Power | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
45 | 64/0 | 65/0 | 4.079 | 10.10.25 | 18.10.25 | 2025-10-25 | 23.10.25 | 26.10.25 | 2025-10-25 | MC Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
46 | 32/0 | 33/0 | 3.747 | 04.10.25 | 13.10.25 | 2025-10-25 | 23.10.25 | 29.10.25 | 2025-10-25 | Krishna Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
47 | 33/0 | 34/0 | 3.338 | 21.10.25 | 27.10.25 | 2025-10-25 | 23.10.25 | 29.10.25 | 2025-10-25 | Krishna Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
48 | 36/0 | 37/0 | 0.214 | 30.10.25 | 08.11.25 | 2025-11-25 | 30.10.25 | 08.11.25 | 2025-11-25 | Telegance Power | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
49 | 60/0 | 61/0 | 0.206 | 10.11.25 | 11.11.25 | 2025-11-25 | 10.11.25 | 11.11.25 | 2025-11-25 | Indrajeet | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
50 | 34/0 | 34/5 | 2.056 | 01.01.25 | 06.11.25 | 2025-11-25 | 14.11.25 | 18.11.25 | 2025-11-25 | Krishna Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
51 | 34/5 | 35/0 | 0.705 | 10.11.25 | 13.11.25 | 2025-11-25 | 14.11.25 | 19.11.25 | 2025-11-25 | Krishna Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
52 | 45/0 | 46/0 | 0.233 | 14.11.25 | 26.11.25 | 2025-11-25 | 14.11.25 | 26.11.25 | 2025-11-25 | Gopal Ji | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
53 | 37/0 | 37/1 | 0.371 | 29.11.25 | 30.11.25 | 2025-11-25 | 29.11.25 | 30.11.25 | 2025-11-25 | Indrajeet | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
54 | 37/1 | 37/2 | 0.468 | 29.11.25 | 30.11.25 | 2025-11-25 | 29.11.25 | 30.11.25 | 2025-11-25 | Indrajeet | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
55 | 25/0 | 26/0 | 4.965 | 13.11.25 | 24.11.25 | 2025-11-25 | 29.11.25 | 30.11.25 | 2025-11-25 | Krishna Const. -2 | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
56 | 2/0 | 3/0 | 3.818 | 30.10.25 | 05.11.25 | 2025-11-25 | 30.11.25 | 30.11.25 | 2025-11-25 | Devi Power | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
57 | 30/0 | 31/0 | 1.325 | 19.11.25 | 24.11.25 | 2025-11-25 | 30.11.25 | 30.11.25 | 2025-11-25 | Krishna Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
58 | 5/0 | 6/0 | 0.237 | 05.12.25 | 11.12.25 | 2025-12-25 | 05.12.25 | 11.12.25 | 2025-12-25 | Kunal Kumar | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
59 | 4/0 | 5/0 | 1.867 | 05.12.25 | 08.12.25 | 2025-12-25 | 09.12.25 | 12.12.25 | 2025-12-25 | Devi Power | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
60 | 15/0 | 16/0 | 4.141 | 03.12.25 | 10.12.25 | 2025-12-25 | 11.12.25 | 13.12.25 | 2025-12-25 | Nasir | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
61 | 29/0 | 30/0 | 4.45 | 01.12.25 | 08.12.25 | 2025-12-25 | 11.12.25 | 15.12.25 | 2025-12-25 | Krishna Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
62 | 16/0 | 17/0 | 2.818 | 14.12.25 | 17.12.25 | 2025-12-25 | 20.12.25 | 21.12.25 | 2025-12-25 | Nasir | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
63 | 24/0 | 25/0 | 2.69 | 01.12.25 | 08.12.25 | 2025-12-25 | 13.12.25 | 23.12.25 | 2025-12-25 | Krishna Const. -2 | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
64 | 6/0 | 7/0 | 1.175 | 17.12.25 | 18.12.25 | 2025-12-25 |  |  | 2025-12-25 | Devi Power | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
65 | 28/0 | 29/0 | 3.914 | 15.12.25 | 21.12.25 | 2025-12-25 | 23.12.25 |  | 2025-12-25 | Krishna Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
66 | 23/0 | 24/0 | 4.809 | 12.12.25 | 22.12.25 | 2025-12-25 | 25.12.25 |  | 2025-12-25 | Krishna Const. -2 | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
67 | 27/1 | 28/0 | 1.752 | 24.12.25 |  | 2025-12-25 |  |  | 2025-12-25 | Krishna Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
68 | 9/0 | 10/0 | 0.234 |  |  | 2025-12-25 |  |  | 2025-12-25 | Gopal Ji | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
69 | 17/0 | 18/0 | 2.508 |  |  | 2025-12-25 |  |  | 2025-12-25 | Nasir | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
70 | 10/12 | 10/20 | 3.208 |  |  | 2025-12-25 |  |  | 2025-12-25 | Deepak | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
71 | 70/0 | 71/0 | 0.258 |  |  | 2025-12-25 |  |  | 2025-12-25 | GPJ Const. | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
72 | 14/0 | 15/0 | 2.624 |  |  | 2025-12-25 |  |  | 2025-12-25 | Nasir | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
73 | 3/0 | 4/0 | 0.227 | 23.12.25 |  | 2025-12-25 | 23.12.25 |  | 2025-12-25 | Gopal Ji | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
74 | 22/0 | 23/0 | 4.035 |  |  | 2025-12-25 |  |  |  | Krishna Const. -2 | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[11 empty] | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[11 empty] | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[11 empty] | TB 401 | PKG-G | TB 401 - PKG-G | TB 401 - PKG-G | tb401pkgg | TB 401 - PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
| From | To | Section Length | Start Date | End Date |  | Start Date | End Date |  |  | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  | Section Length
1 | 60/0 | 61/0 | 4.877 | 2024-08-21 | 2024-08-28 |  | 2024-09-09 | 2024-09-16 |  | Kuddus ali | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 4.877
2 | 61/0 | 62/0 | 4.568 | 2024-09-06 | 2024-09-16 |  | 2024-09-26 | 2024-10-03 |  | Kuddus ali | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 4.568
3 | 62/0 | 63/0 | 4.863 | 2024-09-23 | 2024-10-02 |  | 2024-10-17 | 2024-10-22 |  | Kuddus ali | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 4.863
4 | 63/0 | 64/0 | 3.711 | 2024-10-14 | 2024-10-21 |  | 2024-10-31 | 2024-11-06 |  | Kuddus ali | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 3.711
5 | 64/0 | 65/0 | 4.918 | 2024-10-30 | 2024-11-05 |  | 2024-11-13 | 2024-11-16 |  | Kuddus ali | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 4.918
6 | 59/8 | 60/0 | 3.778 | 2024-12-22 | 2024-12-27 |  | 2025-01-04 | 2025-01-09 |  | Gopal Associate | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 3.778
7 | 59/0 | 59/8 | 3.337 | 2025-01-02 | 2025-01-08 |  | 2025-01-12 | 2025-01-15 |  | Gopal Associate | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 3.337
8 | 65/0 | 66/0 | 4.736 | 2025-02-03 | 2025-03-22 |  | 2025-03-10 | 2025-03-23 |  | MR Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 4.736
9 | 50/0 | 51/0 | 4.444 | 2025-03-12 | 2025-03-23 |  | 2025-03-17 | 2025-03-24 |  | Gopal Associate | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 4.444
10 | 49/0 | 50/0 | 3.227 | 2025-02-06 | 2025-02-19 |  | 2025-05-01 | 2025-05-05 |  | Gopal Associate | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 3.227
11 | 51/0 | 52/0 | 1.049 | 2025-04-02 | 2025-04-08 |  | 2025-04-04 | 2025-04-09 |  | Gopal Associate | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 1.049
12 | 73/0 | 74/0 | 3.788 | 2025-06-01 | 2025-06-21 |  | 2025-09-26 | 2025-09-30 |  | JPJ Construction/MC Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 3.788
13 | 72/0 | 73/0 | 1.628 | 2025-11-03 | 2025-11-08 |  | 2025-11-21 | 2025-11-25 |  | JPJ Construction/MC Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 1.628
14 | 2/0 | 3/0 | 3.823 | 2025-11-13 | 2025-11-18 |  | 2025-12-30 | 2026-01-14 |  | Devi Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 3.823
15 | 71/0 | 72/0 | 3.675 | 2025-11-20 | 2025-11-25 |  | 2025-11-28 | 2025-11-30 |  | MC Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 3.675
16 | 1A/0 | 2/0 | 3.426 | 2025-11-21 | 2025-11-28 |  | 2025-11-28 | 2025-11-30 |  | Devi Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 3.426
17 | 70/0 | 71/0 | 4.966 | 2025-12-08 | 2025-12-16 |  | 2025-12-12 | 2025-12-17 |  | MC Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 4.966
18 | 56/0 | 57/0 | 0.22 | 2025-11-20 | 2025-11-26 |  | 2025-11-20 | 2025-11-26 |  | Gopal Associate, Hotline | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | M | FALSE |  |  |  | 0.22
19 | 46/0 | 47/0 | 0.19908 | 2025-12-06 | 2025-12-11 |  | 2025-12-06 | 2025-12-11 |  | Gopal Associate, Hotline | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | M | FALSE |  |  |  | 0.19908
20 | 69/0 | 70/0 | 0.769 | 2025-12-18 | 2025-12-24 |  | 2025-12-21 | 2025-12-25 |  | MC Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 0.769
21 | 67/0 | 68/0 | 1.061 | 2025-12-26 | 2025-12-28 |  | 2026-01-06 | 2026-01-08 |  | MC Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 1.061
22 | 68/0 | 69/0 | 0.2 | 2025-12-29 | 2025-12-29 |  | 2025-12-29 | 2025-12-29 |  | MC Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | M | FALSE |  |  |  | 0.2
23 | 66/0 | 67/0 | 0.2078 | 2026-01-03 | 2026-01-03 |  | 2026-01-03 | 2026-01-03 |  | MC Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | M | FALSE |  |  |  | 0.2078
24 | 3/0 | 4/0 | 0.2265 | 2026-01-10 | 2026-01-16 |  | 2026-01-11 | 2026-01-16 |  | Gopal Associate, Hotline | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | M | FALSE |  |  |  | 0.2265
25 | 57/0 | 58/0 | 3.287 | 2026-01-19 | 2026-01-24 |  | 2026-01-29 | 2026-01-31 |  | MC Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 3.287
26 | 10/12 | 11/0 | 4.95 | 2026-01-14 | 2026-01-22 |  | 2026-02-05 | 2026-02-07 |  | Deepak Sarkar | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 4.95
27 | 47/0 | 48/0 | 4.477 | 2026-01-26 | 2026-01-31 |  | 2026-01-28 | 2026-01-31 |  | Krishna-1 | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 4.477
28 | 48/0 | 49/0 | 0.83 | 2026-01-17 | 2026-01-20 |  | 2026-01-20 | 2026-01-23 |  | Krishna-1 | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 0.83
29 | 58/0 | 59/0 | 0.2389 | 2026-01-28 | 2026-01-28 |  | 2026-01-28 | 2026-01-28 |  | MC Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | M | FALSE |  |  |  | 0.2389
30 | 45/0 | 46/0 | 0.70146 | 2026-02-07 | 2026-02-08 |  | 2026-02-10 | 2026-02-13 |  | Krishna-1 | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 0.70146
31 | 44/10 | 45/0 | 0.755 | 2026-02-09 | 2026-02-12 |  | 2026-02-17 | 2026-02-20 |  | Krishna-1 | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 0.755
32 | 7/0 | 8/0 | 0.211 | 2026-02-20 | 2026-02-26 |  | 2026-02-20 | 2026-02-26 |  | Gopal Associate, Hotline | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | M | FALSE |  |  |  | 0.211
33 | 55/0 | 56/0 | 3.34 | 2026-02-12 | 2026-03-25 |  | 2026-03-27 | 2026-03-31 |  | MC Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 3.34
34 | 44/8 | 44/10 | 0.795 | 2026-02-16 | 2026-02-19 |  | 2026-03-10 | 2026-03-13 |  | Krishna-1 | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 0.795
35 | 44/6 | 44/8 | 0.84 | 2026-03-20 | 2026-03-23 |  | 2026-03-28 | 2026-03-31 |  | Krishna-1 | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 0.84
36 | 1/0 | 1A/0 | 0.09 | 2026-03-24 | 2026-03-31 |  | 2026-03-24 | 2026-03-31 |  | Devi Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | M | FALSE |  |  |  | 0.09
37 | 44/0 | 44/6 | 2.312 | 2026-03-27 | 2026-03-31 |  | 2026-03-28 | 2026-03-31 |  | Krishna-1 | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 2.312
38 | Gty | 1/0 | 0.122 | 2026-03-27 | 2026-03-30 |  | 2026-03-27 | 2026-03-30 |  | Devi Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | M | FALSE |  |  |  | 0.122
39 | 10/0 | 10/12 | 4.894 | 2026-03-09 | 2026-03-15 |  | 2026-04-04 | 2026-04-08 |  | Deepak Sarkar | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 4.894
40 | 14/0 | 14A/0 | 0.381 | 2026-03-30 | 2026-04-06 |  | 2026-04-05 | 2026-04-06 |  | Nasiruddin | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | M | FALSE |  |  |  | 0.381
41 | 8/7 | 9/0 | 2.456 | 2026-03-30 | 2026-04-03 |  | 2026-04-06 | 2026-04-08 |  | Deepak Sarkar | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 2.456
42 | 9/0 | 10/0 | 0.233 | 2026-04-03 | 2026-04-09 |  | 2026-04-03 | 2026-04-10 |  | Gopal Associate, Hotline | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | M | FALSE |  |  |  | 0.233
43 | 54/0 | 55/0 | 2.411 | 2026-04-03 | 2026-04-09 |  | 2026-04-08 | 2026-04-11 |  | MC Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 2.411
44 | 8/0 | 8/7 | 2.861 | 2026-04-06 | 2026-04-09 |  | 2026-04-08 | 2026-04-11 |  | Devi Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 2.861
45 | 43/0 | 44/0 | 4.8527 | 2026-04-08 | 2026-04-15 |  | 2026-04-16 | 2026-04-18 |  | Krishna-1 | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 4.8527
46 | 6/0 | 7/0 | 1.14 | 2025-03-19 | 2026-04-15 |  | 2026-03-24 | 2026-04-30 |  | Deepak Sarkar / Nasiruddin | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 1.14
47 | 53/0 | 54/0 | 3.69 | 2025-04-18 | 2026-04-26 |  | 2026-04-30 | 2026-04-30 |  | MC Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 3.69
48 | 5/0 | 6/0 | 0.246 | 2026-04-24 | 2026-04-30 |  | 2026-04-24 | 2026-04-30 |  | Gopal Associate, Hotline | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | M | FALSE |  |  |  | 0.246
49 | 14A/0 | 15/0 | 1.192 | 2026-04-25 | 2026-05-04 |  | 2026-05-02 | 2026-05-04 |  | Nasiruddin | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 1.192
50 | 13/0 | 14/0 | 2.078 | 2026-03-30 | 2026-04-04 |  | 2026-05-12 | 2026-05-13 |  | Nasiruddin | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 2.078
51 | 52/0 | 53/0 | 4.534 | 2026-05-10 | 2026-05-16 |  | 2026-05-18 | 2026-05-22 |  | MC Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 4.534
52 | 11A/0 | 12/0 | 4.11 | 2026-05-18 | 2026-05-16 |  | 2026-05-27 | 2026-05-29 |  | Nasiruddin | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE |  |  |  | 4.11
53 | 12/0 | 13/0 | 0.2119 | 2026-05-26 | 2026-05-31 |  | 2026-05-26 | 2026-05-31 |  | Gopal Associate, Hotline | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | M | FALSE |  |  |  | 0.2119
54 | 4/0 | 5/0 | [7 empty] | Devi Power | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | TSE | FALSE
55 | [10 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
TOTAL |  |  | 125.9373 | [7 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  | 125.9373
[11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
|  |  | S. Len-P.O. | [7 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  | 0
|  |  | P/O-F/S | [7 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0 |  | 0
[11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
[11 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
|  |  | 88.4858 | [7 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0
|  |  | 37.4515 | [7 empty] | TB 408 |  | TB 408 | TB 408 | tb408 | TB 408 | TB 408 - DPR - 2026-06-01.xlsx | Stringing | tse | TRUE | SPAN_UNRESOLVED_TSE_FALLBACK | 0

## Diagnostics
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | DetectedHeaderRow | ColumnsDetected | NormalizedColumnsOk | PresentColumns | MissingColumns | AppliedMap | Rows | DailyRows | Status | FallbackNote | TemplateSheet | TemplateApplied | TemplateFallbackUsed | TemplateChanges | MethodInferenceRows
TB 401 - DPR - 2025-12-25.xlsx | TB401 | Stringing - PKG-G | Stringing - PKG-G | PKG-G | config | 4 | S.no, From AP, To AP, Span (M), P/O Starting Date, P/O Completion Date, month, F/S Starting Date, F/S/ Completion Date, month__2, Gang Name, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | FALSE | From AP, To AP, P/O Starting Date, P/O Completion Date, F/S Starting Date, F/S/ Completion Date, Length, Gang Name | Method, Section Readiness, P/O | From AP->from_ap, To AP->to_ap, Span (M)->length_m, P/O Starting Date->po_start_date, P/O Completion Date->po_completion_date, F/S Starting Date->fs_starting_date, F/S/ Completion Date->fs_complete_date, Gang Name->gang_name | 77 | 2164 | OK |  | TB 401 Stringing | TRUE | FALSE | C1:unnamed_col_1->S.no; C2:from->From AP; C3:to->To AP; C4:Length->Span (M); C5:start date->P/O Starting Date; C6:finish date->P/O Completion Date; C8:start date__2->F/S Starting Date; C9:finish date__2->F/S/ Completion Date; C11:unnamed_col_11->Gang Name | 77
TB 408 - DPR - 2026-06-01.xlsx | TB408 | Stringing | Stringing |  |  | 3 | S.no, From AP, To AP, Method, Gang Name, Span (M), P/O, P/O Starting Date, P/O Completion Date, Length, F/S Starting Date, F/S/ Completion Date, project_code, line_name, project_name, project_display, project_scope_key, project, _source_file, source_sheet | FALSE | From AP, To AP, Method, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Gang Name | Section Readiness | From AP->from_ap, To AP->to_ap, Method->method, Gang Name->gang_name, Span (M)->length_m, P/O->po, P/O Starting Date->po_start_date, P/O Completion Date->po_completion_date, Length->length_m, F/S Starting Date->fs_starting_date, F/S/ Completion Date->fs_complete_date | 65 | 1745 | OK |  | TB 408 Stringing | TRUE | FALSE | C1:sl no->S.no; C2:section->From AP; C3:unnamed_col_3->To AP; C4:type of sections->Method; C6:section length->Span (M); C7:paying out r sag->P/O; C8:unnamed_col_8->P/O Starting Date; C9:unnamed_col_9->P/O Completion Date; C10:final sag->Length; C11:unnamed_col_11->F/S Starting Date; C12:unnamed_col_12->F/S/ Completion Date | 11

## Data Issues
project_name | from_ap | to_ap | gang_name | method | status | po_start_date | po_completion_date | fs_starting_date | fs_complete_date | length_m | length_km | po_km | source_file | source_sheet | Issues
TB 401 - PKG-G | 58/0 | 58/7 | Kddus Ali | tse |  | 2024-11-20 | 2024-11-23 |  | 2024-12-05 | 2797 | 2.797 |  | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | Missing/Invalid F/S Start Date
TB 401 - PKG-G | 6/0 | 7/0 | Devi Power | tse |  | 2025-12-17 | 2025-12-18 |  |  | 1175 | 1.175 |  | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 401 - PKG-G | 28/0 | 29/0 | Krishna Const. | tse |  | 2025-12-15 | 2025-12-21 | 2025-12-23 |  | 3914 | 3.914 |  | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | Missing/Invalid F/S Complete Date
TB 401 - PKG-G | 23/0 | 24/0 | Krishna Const. -2 | tse |  | 2025-12-12 | 2025-12-22 | 2025-12-25 |  | 4809 | 4.809 |  | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | Missing/Invalid F/S Complete Date
TB 401 - PKG-G | 27/1 | 28/0 | Krishna Const. | tse |  | 2025-12-24 |  |  |  | 1752 | 1.752 |  | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 401 - PKG-G | 9/0 | 10/0 | Gopal Ji | tse | [5 empty] | 234 | 0.234 |  | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 401 - PKG-G | 17/0 | 18/0 | Nasir | tse | [5 empty] | 2508 | 2.508 |  | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 401 - PKG-G | 10/12 | 10/20 | Deepak | tse | [5 empty] | 3208 | 3.208 |  | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 401 - PKG-G | 70/0 | 71/0 | GPJ Const. | tse | [5 empty] | 258 | 0.258 |  | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 401 - PKG-G | 14/0 | 15/0 | Nasir | tse | [5 empty] | 2624 | 2.624 |  | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 401 - PKG-G | 3/0 | 4/0 | Gopal Ji | tse |  | 2025-12-23 |  | 2025-12-23 |  | 227 | 0.227 |  | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | Missing/Invalid PO Complete Date; Missing/Invalid F/S Complete Date
TB 401 - PKG-G | 22/0 | 23/0 | Krishna Const. -2 | tse | [5 empty] | 4035 | 4.035 |  | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 401 - PKG-G |  |  |  | tse | [8 empty] | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 401 - PKG-G |  |  |  | tse | [8 empty] | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 401 - PKG-G |  |  |  | tse | [8 empty] | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | From | To |  | tse | [8 empty] | TB 408 - DPR - 2026-06-01.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 | 11A/0 | 12/0 | Nasiruddin | TSE |  | 2026-05-18 | 2026-05-16 | 2026-05-27 | 2026-05-29 | 4110 | 4.11 |  | TB 408 - DPR - 2026-06-01.xlsx | Stringing | PO Start > PO Complete (non-positive duration)
TB 408 | 4/0 | 5/0 | Devi Power | TSE | [8 empty] | TB 408 - DPR - 2026-06-01.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-06-01.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [5 empty] | 125937.34 | 125.9373 |  | TB 408 - DPR - 2026-06-01.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-06-01.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-06-01.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-06-01.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-06-01.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-06-01.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [8 empty] | TB 408 - DPR - 2026-06-01.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [5 empty] | 88485.8 | 88.4858 |  | TB 408 - DPR - 2026-06-01.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date
TB 408 |  |  |  | tse | [5 empty] | 37451.54 | 37.4515 |  | TB 408 - DPR - 2026-06-01.xlsx | Stringing | Missing/Invalid PO Start Date; Missing/Invalid PO Complete Date; Missing/Invalid F/S Start Date; Missing/Invalid F/S Complete Date

## Issues
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | Issue | MissingColumns | Rows | DailyRows
TB 401 - DPR - 2025-12-25.xlsx | TB401 | Stringing - PKG-G | Stringing - PKG-G | PKG-G | config | MISSING_NONCRITICAL_COLUMNS | Method, Section Readiness | 77 | 0
TB 408 - DPR - 2026-06-01.xlsx | TB408 | Stringing | Stringing |  |  | MISSING_NONCRITICAL_COLUMNS | Section Readiness | 65 | 0

## README_Assumptions
Note | Rules
Compiled from DPR files: stringing sheet consolidation. | Preserve raw columns; diagnostics include column presence and date parsing; configured stringing sheets are processed independently with per-sheet line identity before concatenation; PO start to F/S complete inclusive for daily expansion.
Method fallback assumption | If Method is missing, infer using erection span depth: erection_locations<=2 => manual, >2 => tse, unresolved => tse fallback. Current inferred rows: 88.