## Notes
Item | Value
Cutoff | Complete Date >= 2025-04-01 for delivered tower/productivity summaries. Daily cross-check uses Work Date >= 2025-04-01.
Alias rule | Gagan group = gang names containing "gagan". Prakash group = gang names containing "prakash", "parkash", or "prakaash".
Deduplication | Dropped duplicate rows matching group, gang, project, location, start date, complete date, tower type, and tower weight. This removes duplicate Completed/COMPLETED rows.
Productivity | Aggregate Productivity MT/day = total tower weight / total inclusive tower-days. Avg Per-Tower Productivity MT/day = simple average of row-level productivity.
Micro-plan note | Mr. Satyaprakash appears in MicroPlanResponsibilities for TA 419 Oct-Nov 2025 but not as a completed-tower gang in RawData; kept in separate sheet.

## Group Summary
Contractor Group | Projects | Aliases Found | First Start Date | Last Complete Date | Towers Completed | Total Tower Weight MT | Avg Tower Weight MT | Total Tower Days | Aggregate Productivity MT/day | Avg Per-Tower Productivity MT/day
Gagan Enterprises | TA 416, TA 419, TA 602 | Gagan Enterprise 1, Gagan Enterprise 2, Gagan Enterprise 2 Kajol, Gagan Enterprises, M S Gagan Entp | 2025-03-31 | 2026-05-29 | 32 | 1694.857 | 52.964 | 412 | 4.114 | 6.191
Prakash | TA 413, TA 506 | Jai Prakash Mahto, Jay Prakash, Ved Prakash | 2025-08-25 | 2026-02-16 | 34 | 1622.163 | 47.711 | 299 | 5.425 | 5.436

## Project Summary
Contractor Group | Project Code | Project Name | Client | Aliases in Project | First Start Date | Last Complete Date | Towers Completed by Group | Total Tower Weight MT | Avg Tower Weight MT | Total Tower Days | Aggregate Productivity MT/day | Avg Per-Tower Productivity MT/day | Tower Types | Overall Project Towers Completed Apr25+ | Overall Project Avg Tower Weight MT Apr25+ | Daily Active Days | Daily Productivity Sum MT | Daily Avg MT/day Active
Gagan Enterprises | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | Gagan Enterprise 1, Gagan Enterprise 2, Gagan Enterprise 2 Kajol | 2025-03-31 | 2025-09-02 | 19 | 1279.858 | 67.361 | 209 | 6.124 | 6.943 | DA+3 (3), DA+6 (1), DA-3 (9), DB+18 (1), DB+6 (1), DB+9 (1), DC+3 (1), DD60+30 (2) | 170 | 68.472 | 147 | 1275.15 | 8.674
Gagan Enterprises | TA 419 | 765 KV D/C Sikar II - Narela TL02 | Power Grid Corporation of India | Gagan Enterprises | 2025-03-31 | 2025-05-10 | 4 | 197.888 | 49.472 | 45 | 4.398 | 4.483 | DA+0 (1), DA+6 (1), DA-3 (1), DD60+0 (1) | 153 | 54.472 | 40 | 195.305 | 4.883
Gagan Enterprises | TA 602 |  |  | M S Gagan Entp | 2026-01-16 | 2026-05-29 | 9 | 217.112 | 24.124 | 158 | 1.374 | 5.363 | A+0 (5), A+3 (1), A+6 (2), B2+3 (1) | 51 | 24.124 | 134 | 217.111 | 1.62
Prakash | TA 413 |  |  | Ved Prakash | 2025-08-25 | 2026-02-16 | 14 | 1029.906 | 73.565 | 174 | 5.919 | 6.213 | DA+0 (3), DA+3 (4), DB1+9 (2), DB2+3 (1), DD60+18 (1), DD60+35 (2), DD60+9 (1) | 210 | 49.259 | 173 | 1029.906 | 5.953
Prakash | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | Jai Prakash Mahto, Jay Prakash | 2025-09-09 | 2026-02-14 | 20 | 592.257 | 29.613 | 125 | 4.738 | 4.893 | DA+0 (2), DA+6 (2), DA+9 (1), DA-1.5 (1), DA-3 (1), DB1+6 (1), DB1+9 (1), DB2+6 (1), DC1+0 (3), DC1+6 (1), DC2+9 (1), DC2-3 (1), DD45+0 (1), DD45-3 (1), DD60+0 (1), DD60+9 (1) | 399 | 25.34 | 108 | 592.257 | 5.484

## Tower Type Detail
Contractor Group | Project Code | Tower Type | Tower Count | Total Weight MT | Avg Weight MT | Avg Productivity MT/day
Gagan Enterprises | TA 416 | DA+3 | 3 | 138.147 | 46.049 | 5.566
Gagan Enterprises | TA 416 | DA+6 | 1 | 53.324 | 53.324 | 7.618
Gagan Enterprises | TA 416 | DA-3 | 9 | 381.368 | 42.374 | 7.787
Gagan Enterprises | TA 416 | DB+18 | 1 | 97.653 | 97.653 | 4.439
Gagan Enterprises | TA 416 | DB+6 | 1 | 75.858 | 75.858 | 6.896
Gagan Enterprises | TA 416 | DB+9 | 1 | 78.678 | 78.678 | 6.556
Gagan Enterprises | TA 416 | DC+3 | 1 | 78.073 | 78.073 | 7.807
Gagan Enterprises | TA 416 | DD60+30 | 2 | 376.756 | 188.378 | 5.91
Gagan Enterprises | TA 419 | DA+0 | 1 | 36.16 | 36.16 | 2.583
Gagan Enterprises | TA 419 | DA+6 | 1 | 43.804 | 43.804 | 5.476
Gagan Enterprises | TA 419 | DA-3 | 1 | 34.79 | 34.79 | 3.479
Gagan Enterprises | TA 419 | DD60+0 | 1 | 83.134 | 83.134 | 6.395
Gagan Enterprises | TA 602 | A+0 | 5 | 120.618 | 24.124 | 4.542
Gagan Enterprises | TA 602 | A+3 | 1 | 24.124 | 24.124 | 8.041
Gagan Enterprises | TA 602 | A+6 | 2 | 48.247 | 24.124 | 5.744
Gagan Enterprises | TA 602 | B2+3 | 1 | 24.124 | 24.124 | 6.031
Prakash | TA 413 | DA+0 | 3 | 108.479 | 36.16 | 8.437
Prakash | TA 413 | DA+3 | 4 | 151.724 | 37.931 | 5.057
Prakash | TA 413 | DB1+9 | 2 | 133.562 | 66.781 | 4.452
Prakash | TA 413 | DB2+3 | 1 | 62.116 | 62.116 | 4.437
Prakash | TA 413 | DD60+18 | 1 | 124.95 | 124.95 | 6.942
Prakash | TA 413 | DD60+35 | 2 | 347.122 | 173.561 | 6.937
Prakash | TA 413 | DD60+9 | 1 | 101.953 | 101.953 | 7.282
Prakash | TA 506 | DA+0 | 2 | 33.933 | 16.967 | 4.242
Prakash | TA 506 | DA+6 | 2 | 42.194 | 21.097 | 3.516
Prakash | TA 506 | DA+9 | 1 | 22.488 | 22.488 | 4.498
Prakash | TA 506 | DA-1.5 | 1 | 16.452 | 16.452 | 5.484
Prakash | TA 506 | DA-3 | 1 | 15.858 | 15.858 | 3.964
Prakash | TA 506 | DB1+6 | 1 | 34.166 | 34.166 | 3.796
Prakash | TA 506 | DB1+9 | 1 | 36.585 | 36.585 | 7.317
Prakash | TA 506 | DB2+6 | 1 | 34.17 | 34.17 | 4.881
Prakash | TA 506 | DC1+0 | 3 | 89.334 | 29.778 | 5.038
Prakash | TA 506 | DC1+6 | 1 | 37.206 | 37.206 | 4.651
Prakash | TA 506 | DC2+9 | 1 | 39.622 | 39.622 | 3.962
Prakash | TA 506 | DC2-3 | 1 | 27.252 | 27.252 | 4.542
Prakash | TA 506 | DD45+0 | 1 | 35.845 | 35.845 | 5.974
Prakash | TA 506 | DD45-3 | 1 | 34.431 | 34.431 | 4.919
Prakash | TA 506 | DD60+0 | 1 | 39.597 | 39.597 | 6.599
Prakash | TA 506 | DD60+9 | 1 | 53.123 | 53.123 | 6.64

## Alias Project Detail
Contractor Group | Gang name | Project Code | Tower Count | Total Weight MT | Avg Weight MT | Aggregate Productivity MT/day | First Start Date | Last Complete Date
Gagan Enterprises | Gagan Enterprise 1 | TA 416 | 13 | 952.15 | 73.242 | 6.39 | 2025-03-31 | 2025-09-02
Gagan Enterprises | Gagan Enterprise 2 | TA 416 | 5 | 281.659 | 56.332 | 5.993 | 2025-04-01 | 2025-05-22
Gagan Enterprises | Gagan Enterprise 2 Kajol | TA 416 | 1 | 46.049 | 46.049 | 3.542 | 2025-08-14 | 2025-08-26
Gagan Enterprises | Gagan Enterprises | TA 419 | 4 | 197.888 | 49.472 | 4.398 | 2025-03-31 | 2025-05-10
Gagan Enterprises | M S Gagan Entp | TA 602 | 9 | 217.112 | 24.124 | 1.374 | 2026-01-16 | 2026-05-29
Prakash | Ved Prakash | TA 413 | 14 | 1029.906 | 73.565 | 5.919 | 2025-08-25 | 2026-02-16
Prakash | Jai Prakash Mahto | TA 506 | 17 | 492.467 | 28.969 | 4.735 | 2025-09-22 | 2026-02-14
Prakash | Jay Prakash | TA 506 | 3 | 99.79 | 33.263 | 4.752 | 2025-09-09 | 2025-09-30

## Aliases
Contractor Group | Rows Before Dedup | Completed Towers After Dedup | Aliases Found in Completed Tower Data
Gagan Enterprises | 32 | 32 | Gagan Enterprise 1, Gagan Enterprise 2, Gagan Enterprise 2 Kajol, Gagan Enterprises, M S Gagan Entp
Prakash | 53 | 34 | Jai Prakash Mahto, Jay Prakash, Ved Prakash

## Tower Records
Contractor Group | Gang name | Project Code | project_name | client_name | Location No. | Start Date | Complete Date | Tower Type | Tower Weight | Tower Days | Productivity MT/day | Status
Gagan Enterprises | Gagan Enterprise 1 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 20/11 | 2025-03-31 | 2025-04-08 | DA-3 | 42.374 | 9 | 4.708 | COMPLETED
Gagan Enterprises | Gagan Enterprise 2 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 9/0 | 2025-04-01 | 2025-04-11 | DB+6 | 75.858 | 11 | 6.896 | COMPLETED
Gagan Enterprises | Gagan Enterprise 1 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 20/10 | 2025-04-09 | 2025-04-15 | DA+3 | 46.049 | 7 | 6.578 | COMPLETED
Gagan Enterprises | Gagan Enterprise 2 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 10/1 | 2025-04-12 | 2025-04-16 | DA-3 | 42.374 | 5 | 8.475 | COMPLETED
Gagan Enterprises | Gagan Enterprise 1 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 20/1 | 2025-04-16 | 2025-04-22 | DA+6 | 53.324 | 7 | 7.618 | COMPLETED
Gagan Enterprises | Gagan Enterprise 1 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 19/12 | 2025-04-23 | 2025-04-26 | DA-3 | 42.374 | 4 | 10.594 | COMPLETED
Gagan Enterprises | Gagan Enterprise 2 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 10/0 | 2025-04-17 | 2025-04-28 | DB+9 | 78.678 | 12 | 6.556 | COMPLETED
Gagan Enterprises | Gagan Enterprise 1 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 19/11 | 2025-04-27 | 2025-04-30 | DA-3 | 42.374 | 4 | 10.594 | COMPLETED
Gagan Enterprises | Gagan Enterprise 1 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 19/10 | 2025-04-30 | 2025-05-06 | DA+3 | 46.049 | 7 | 6.578 | COMPLETED
Gagan Enterprises | Gagan Enterprise 1 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 19/8 | 2025-05-06 | 2025-05-09 | DA-3 | 42.374 | 4 | 10.594 | COMPLETED
Gagan Enterprises | Gagan Enterprise 2 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 12/1 | 2025-05-04 | 2025-05-10 | DA-3 | 42.374 | 7 | 6.053 | COMPLETED
Gagan Enterprises | Gagan Enterprise 1 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 17/8 | 2025-05-11 | 2025-05-15 | DA-3 | 42.374 | 5 | 8.475 | COMPLETED
Gagan Enterprises | Gagan Enterprise 2 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 12/6 | 2025-05-11 | 2025-05-22 | DA-3 | 42.374 | 12 | 3.531 | COMPLETED
Gagan Enterprises | Gagan Enterprise 1 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 15/0 | 2025-05-16 | 2025-05-25 | DC+3 | 78.073 | 10 | 7.807 | COMPLETED
Gagan Enterprises | Gagan Enterprise 1 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 12/8 | 2025-05-26 | 2025-05-31 | DA-3 | 42.374 | 6 | 7.062 | COMPLETED
Gagan Enterprises | Gagan Enterprise 1 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 14/0 | 2025-06-01 | 2025-06-30 | DD60+30 | 188.378 | 30 | 6.279 | COMPLETED
Gagan Enterprises | Gagan Enterprise 1 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 13/0 | 2025-07-09 | 2025-08-11 | DD60+30 | 188.378 | 34 | 5.541 | COMPLETED
Gagan Enterprises | Gagan Enterprise 2 Kajol | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 46/2 | 2025-08-14 | 2025-08-26 | DA+3 | 46.049 | 13 | 3.542 | COMPLETED
Gagan Enterprises | Gagan Enterprise 1 | TA 416 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 12/0 | 2025-08-12 | 2025-09-02 | DB+18 | 97.653 | 22 | 4.439 | COMPLETED
Gagan Enterprises | Gagan Enterprises | TA 419 | 765 KV D/C Sikar II - Narela TL02 | Power Grid Corporation of India | 30/1 | 2025-03-31 | 2025-04-13 | DA+0 | 36.16 | 14 | 2.583 | Completed
Gagan Enterprises | Gagan Enterprises | TA 419 | 765 KV D/C Sikar II - Narela TL02 | Power Grid Corporation of India | 28/1 | 2025-04-12 | 2025-04-21 | DA-3 | 34.79 | 10 | 3.479 | Completed
Gagan Enterprises | Gagan Enterprises | TA 419 | 765 KV D/C Sikar II - Narela TL02 | Power Grid Corporation of India | 31/1 | 2025-04-22 | 2025-04-29 | DA+6 | 43.804 | 8 | 5.476 | Completed
Gagan Enterprises | Gagan Enterprises | TA 419 | 765 KV D/C Sikar II - Narela TL02 | Power Grid Corporation of India | 31/0 | 2025-04-28 | 2025-05-10 | DD60+0 | 83.134 | 13 | 6.395 | Completed
Gagan Enterprises | M S Gagan Entp | TA 602 |  |  | 121/2 | 2026-04-28 | 2026-05-04 | A+6 | 24.124 | 7 | 3.446 | Completed
Gagan Enterprises | M S Gagan Entp | TA 602 |  |  | 121/1 | 2026-05-04 | 2026-05-08 | A+0 | 24.124 | 5 | 4.825 | Completed
Gagan Enterprises | M S Gagan Entp | TA 602 |  |  | 121/4 | 2026-05-08 | 2026-05-12 | A+0 | 24.124 | 5 | 4.825 | Completed
Gagan Enterprises | M S Gagan Entp | TA 602 |  |  | 121/7 | 2026-05-12 | 2026-05-16 | A+0 | 24.124 | 5 | 4.825 | Completed
Gagan Enterprises | M S Gagan Entp | TA 602 |  |  | 121/6 | 2026-01-16 | 2026-05-18 | A+0 | 24.124 | 123 | 0.196 | Completed
Gagan Enterprises | M S Gagan Entp | TA 602 |  |  | 121/5 | 2026-05-18 | 2026-05-20 | A+0 | 24.124 | 3 | 8.041 | Completed
Gagan Enterprises | M S Gagan Entp | TA 602 |  |  | 124/5 | 2026-05-21 | 2026-05-23 | A+6 | 24.124 | 3 | 8.041 | Completed
Gagan Enterprises | M S Gagan Entp | TA 602 |  |  | 125/1 | 2026-05-23 | 2026-05-25 | A+3 | 24.124 | 3 | 8.041 | Completed
Gagan Enterprises | M S Gagan Entp | TA 602 |  |  | 125/0 | 2026-05-26 | 2026-05-29 | B2+3 | 24.124 | 4 | 6.031 | Completed
Prakash | Ved Prakash | TA 413 |  |  | 44/1 | 2025-08-25 | 2025-09-03 | DA+3 | 37.931 | 10 | 3.793 | Completed
Prakash | Ved Prakash | TA 413 |  |  | 44/2 | 2025-09-04 | 2025-09-09 | DA+3 | 37.931 | 6 | 6.322 | Completed
Prakash | Ved Prakash | TA 413 |  |  | 44/3 | 2025-09-10 | 2025-09-15 | DA+3 | 37.931 | 6 | 6.322 | Completed
Prakash | Ved Prakash | TA 413 |  |  | 44/4 | 2025-09-16 | 2025-09-19 | DA+0 | 36.16 | 4 | 9.04 | Completed
Prakash | Ved Prakash | TA 413 |  |  | 44/5 | 2025-09-20 | 2025-09-23 | DA+0 | 36.16 | 4 | 9.04 | Completed
Prakash | Ved Prakash | TA 413 |  |  | 43/7 | 2025-09-24 | 2025-09-28 | DA+0 | 36.16 | 5 | 7.232 | Completed
Prakash | Ved Prakash | TA 413 |  |  | 45/0 | 2025-09-28 | 2025-10-09 | DB1+9 | 66.781 | 12 | 5.565 | Completed
Prakash | Ved Prakash | TA 413 |  |  | 26/0 | 2025-10-10 | 2025-11-07 | DD60+35 | 173.561 | 29 | 5.985 | Completed
Prakash | Ved Prakash | TA 413 |  |  | 27/0 | 2025-11-08 | 2025-11-29 | DD60+35 | 173.561 | 22 | 7.889 | Completed
Prakash | Ved Prakash | TA 413 |  |  | 14/0 | 2025-11-30 | 2025-12-17 | DD60+18 | 124.95 | 18 | 6.942 | Completed
Prakash | Ved Prakash | TA 413 |  |  | 13/0 | 2025-12-18 | 2025-12-31 | DD60+9 | 101.953 | 14 | 7.282 | Completed
Prakash | Ved Prakash | TA 413 |  |  | 13A/0 | 2026-01-01 | 2026-01-20 | DB1+9 | 66.781 | 20 | 3.339 | Completed
Prakash | Ved Prakash | TA 413 |  |  | 36/0 | 2026-01-22 | 2026-02-04 | DB2+3 | 62.116 | 14 | 4.437 | Completed
Prakash | Ved Prakash | TA 413 |  |  | 35/10 | 2026-02-07 | 2026-02-16 | DA+3 | 37.931 | 10 | 3.793 | Completed
Prakash | Jay Prakash | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 76A/1 | 2025-09-09 | 2025-09-17 | DB1+6 | 34.166 | 9 | 3.796 | Completed
Prakash | Jay Prakash | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 79/0 | 2025-09-20 | 2025-09-25 | DD45+0 | 35.845 | 6 | 5.974 | Completed
Prakash | Jay Prakash | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 66/0 | 2025-09-25 | 2025-09-30 | DC1+0 | 29.778 | 6 | 4.963 | Completed
Prakash | Jai Prakash Mahto | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 66/0 | 2025-09-22 | 2025-10-02 | DC1+0 | 29.778 | 11 | 2.707 | Completed
Prakash | Jai Prakash Mahto | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 67/0 | 2025-10-02 | 2025-10-09 | DC1+6 | 37.206 | 8 | 4.651 | Completed
Prakash | Jai Prakash Mahto | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 65A/0 | 2025-10-10 | 2025-10-16 | DB2+6 | 34.17 | 7 | 4.881 | Completed
Prakash | Jai Prakash Mahto | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 65/0 | 2025-10-20 | 2025-10-27 | DD60+9 | 53.123 | 8 | 6.64 | Completed
Prakash | Jai Prakash Mahto | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 64A/3 | 2025-10-26 | 2025-10-30 | DA+9 | 22.488 | 5 | 4.498 | Completed
Prakash | Jai Prakash Mahto | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 65A/3 | 2025-10-29 | 2025-11-01 | DC1+0 | 29.778 | 4 | 7.444 | Completed
Prakash | Jai Prakash Mahto | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 64A/2 | 2025-11-02 | 2025-11-05 | DA+0 | 16.967 | 4 | 4.242 | Completed
Prakash | Jai Prakash Mahto | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 64A/1 | 2025-11-04 | 2025-11-09 | DA+6 | 21.097 | 6 | 3.516 | Completed
Prakash | Jai Prakash Mahto | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 64/0 | 2025-11-13 | 2025-11-18 | DD60+0 | 39.597 | 6 | 6.599 | Completed
Prakash | Jai Prakash Mahto | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 64/1 | 2025-11-19 | 2025-11-22 | DA-3 | 15.858 | 4 | 3.964 | Completed
Prakash | Jai Prakash Mahto | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 65A/2 | 2025-11-24 | 2025-11-27 | DA+0 | 16.967 | 4 | 4.242 | Completed
Prakash | Jai Prakash Mahto | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 65A/1 | 2025-11-30 | 2025-12-02 | DA-1.5 | 16.452 | 3 | 5.484 | Completed
Prakash | Jai Prakash Mahto | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 139A/0 | 2025-12-22 | 2025-12-31 | DC2+9 | 39.622 | 10 | 3.962 | Completed
Prakash | Jai Prakash Mahto | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 140/1 | 2026-01-04 | 2026-01-09 | DA+6 | 21.097 | 6 | 3.516 | Completed
Prakash | Jai Prakash Mahto | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 140/0 | 2026-01-13 | 2026-01-18 | DC2-3 | 27.252 | 6 | 4.542 | Completed
Prakash | Jai Prakash Mahto | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 131/1 | 2026-01-27 | 2026-01-31 | DB1+9 | 36.585 | 5 | 7.317 | Completed
Prakash | Jai Prakash Mahto | TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 131/0 | 2026-02-08 | 2026-02-14 | DD45-3 | 34.431 | 7 | 4.919 | Completed

## Daily Crosscheck
Contractor Group | Project Code | Daily Active Days | Daily Productivity Sum MT | Daily Avg MT/day Active
Gagan Enterprises | TA 416 | 147 | 1275.15 | 8.674
Gagan Enterprises | TA 419 | 40 | 195.305 | 4.883
Gagan Enterprises | TA 602 | 134 | 217.111 | 1.62
Prakash | TA 413 | 173 | 1029.906 | 5.953
Prakash | TA 506 | 108 | 592.257 | 5.484

## MicroPlan Mentions
Contractor Group Candidate | entity_name | project_name | plan_month | Planned/Responsibility Rows | Rows With Completion Date | Total Planned Tower Weight MT | Avg Planned Tower Weight MT | Tower Types
Prakash | Mr. Satyaprakash | TA 419 | 2025-10-01 | 2 | 2 | 74.091 | 37.046 | DA+0 (1), DA+3 (1)
Prakash | Mr. Satyaprakash | TA 419 | 2025-11-01 | 37 | 37 | 2132.747 | 57.642 | 5DA+0 (6), 5DA+3 (2), 5DA+6 (2), 5DA+9 (1), 5DA-3 (4), 5DB1+6 (1), 5DD60+18 (1), 5DD60+9 (1), DA+0 (2), DA+1.5 (5), DA+3 (4), DA+6 (2), DA-1.5 (1), DC2+9 (1), DD60+0 (1), DD60+18 (2), DD60+30 (1)