## Focus_vs_Others
Month | Other projects avg DPR KM/month | Other projects total DPR KM strung | Other active projects | TB 401 DPR KM/month | TB 401 DPR KM strung | TB 401 reported KM strung | TB 401 reported TSE | TB 401 reported prod/TSE | TB 401 Future planned KM | TB 401 DPR KM/month rank | TB 401 DPR KM strung rank | TB 408 DPR KM/month | TB 408 DPR KM strung | TB 408 reported KM strung | TB 408 reported TSE | TB 408 reported prod/TSE | TB 408 Future planned KM | TB 408 DPR KM/month rank | TB 408 DPR KM strung rank
Apr-25 | 4.62 | 35.37 | 3 | 0.32 | 0 | 0 | 2 | 0 |  | 5 |  | 0.87 | 1.05 | 1 | 1 | 1 |  | 4 | 4
May-25 | 3.27 | 20.11 | 4 | 1.36 | 5.75 | 5.7 | 2 | 2.85 |  | 5 | 3 | 0.26 | 3.23 | 3.2 | 1 | 3.2 |  | 6 | 4
Jun-25 | 4.62 | 19.98 | 4 | 1.2 | 5.57 | 5.5 | 3 | 1.8333 |  | 5 | 2 | 0.44 | 0 | 0 |  |  |  | 6
Jul-25 | 5.05 | 26.27 | 3 | 1.06 | 5.54 | 5.5 | 3 | 1.8333 |  | 4 | 4 | 0.44 | 0 | 0 |  |  |  | 5
Aug-25 | 2.85 | 16.22 | 4 | 0.92 | 9.93 | 9.9 | 3 | 3.3 |  | 4 | 1 | 0.44 | 0 | 0 |  |  |  | 6
Sep-25 | 2.97 | 21.81 | 6 | 1.42 | 5.63 | 5.6 | 3 | 1.8667 |  | 6 | 2 | 0.44 | 3.79 |  |  |  |  | 8 | 5
Oct-25 | 4.01 | 45.87 | 6 | 2.68 | 23.4 | 24 | 4 | 6 |  | 5 | 1 | 0.19 | 0 | 1.6 |  |  |  | 8
Nov-25 | 5.41 | 42.5 | 6 | 2.52 | 14.36 | 3.4 | 3 | 1.1333 |  | 5 | 2 | 2.51 | 8.73 | 9 | 1 | 9 |  | 6 | 4
Dec-25 | 3.4 | 60.1 | 7 | 5.02 | 41.37 | 36 | 4 | 9 |  | 3 | 1 | 2.17 | 5.74 | 6 | 1 | 6 |  | 8 | 7
Jan-26 | 4.38 | 42.05 | 8 | 0 | 0 |  |  |  | 56.1 |  |  | 3.28 | 13.48 |  |  |  | 20 | 6 | 1
Feb-26 | 5.16 | 58 | 9 | 0 | 0 | [6 empty] | 1.28 | 6.41 |  |  |  | 35 | 9 | 4
Mar-26 | 4.74 | 60.94 | 9 | 0 | 0 | [6 empty] | 2.06 | 7.29 |  |  |  | 30 | 9 | 4

## 401_408_Detail
Project | Month Label | DPR KM/month | DPR KM strung | DPR active gangs | DPR daily rows | DPR compiled spans | Reported KM strung | Reported TSE available | Reported productivity per TSE | Reported/planned KM from Future | Future adjacent Converted Hexa/TSE context | Reported vs DPR KM variance | Reported productivity per TSE vs DPR KM/month
TB 401 | Apr-25 | 0.32 | 0 | 3 | 90 | 0 | 0 | 2 | 0 |  |  | 0 | -0.32
TB 401 | May-25 | 1.36 | 5.75 | 4 | 131 | 5 | 5.7 | 2 | 2.85 |  |  | -0.05 | 1.49
TB 401 | Jun-25 | 1.2 | 5.57 | 4 | 158 | 2 | 5.5 | 3 | 1.8333 |  |  | -0.07 | 0.63333
TB 401 | Jul-25 | 1.06 | 5.54 | 8 | 241 | 4 | 5.5 | 3 | 1.8333 |  |  | -0.04 | 0.77333
TB 401 | Aug-25 | 0.92 | 9.93 | 8 | 232 | 6 | 9.9 | 3 | 3.3 |  |  | -0.03 | 2.38
TB 401 | Sep-25 | 1.42 | 5.63 | 5 | 163 | 2 | 5.6 | 3 | 1.8667 |  |  | -0.03 | 0.44667
TB 401 | Oct-25 | 2.68 | 23.4 | 6 | 217 | 10 | 24 | 4 | 6 |  |  | 0.6 | 3.32
TB 401 | Nov-25 | 2.52 | 14.36 | 7 | 145 | 10 | 3.4 | 3 | 1.1333 |  |  | -10.96 | -1.3867
TB 401 | Dec-25 | 5.02 | 41.37 | 6 | 97 | 18 | 36 | 4 | 9 |  |  | -5.37 | 3.98
TB 401 | Jan-26 | 0 | 0 | 0 | 0 | 0 |  |  |  | 56.1 | 4
TB 401 | Feb-26 | 0 | 0 | 0 | 0 | 0
TB 401 | Mar-26 | 0 | 0 | 0 | 0 | 0
TB 408 | Apr-25 | 0.87 | 1.05 | 3 | 81 | 1 | 1 | 1 | 1 |  |  | -0.05 | 0.13
TB 408 | May-25 | 0.26 | 3.23 | 3 | 67 | 1 | 3.2 | 1 | 3.2 |  |  | -0.03 | 2.94
TB 408 | Jun-25 | 0.44 | 0 | 3 | 90 | 0 | 0 |  |  |  |  | 0
TB 408 | Jul-25 | 0.44 | 0 | 3 | 93 | 0 | 0 |  |  |  |  | 0
TB 408 | Aug-25 | 0.44 | 0 | 3 | 93 | 0 | 0 |  |  |  |  | 0
TB 408 | Sep-25 | 0.44 | 3.79 | 3 | 90 | 1
TB 408 | Oct-25 | 0.19 | 0 | 2 | 62 | 0 | 1.6 |  |  |  |  | 1.6
TB 408 | Nov-25 | 2.51 | 8.73 | 4 | 122 | 3 | 9 | 1 | 9 |  |  | 0.27 | 6.49
TB 408 | Dec-25 | 2.17 | 5.74 | 3 | 117 | 2 | 6 | 1 | 6 |  |  | 0.26 | 3.83
TB 408 | Jan-26 | 3.28 | 13.48 | 5 | 128 | 5 |  |  |  | 20 | 2
TB 408 | Feb-26 | 1.28 | 6.41 | 4 | 112 | 3 |  |  |  | 35 | 4
TB 408 | Mar-26 | 2.06 | 7.29 | 5 | 150 | 4 |  |  |  | 30 | 4

## All_Projects_Long
Project | Month Label | DPR KM/month | DPR KM strung | DPR active gangs | DPR daily rows | DPR compiled spans
TA 325 | Apr-25 | 3.42 | 19.66 | 11 | 173 | 12
TA 325 | May-25 | 2.22 | 8.9 | 5 | 83 | 5
TA 325 | Jun-25 | 3.05 | 4.79 | 2 | 30 | 2
TA 325 | Jul-25 | 0 | 0 | 0 | 0 | 0
TA 325 | Aug-25 | 0 | 0 | 0 | 0 | 0
TA 325 | Sep-25 | 1.88 | 0 | 1 | 15 | 0
TA 325 | Oct-25 | 2.36 | 3.56 | 4 | 73 | 4
TA 325 | Nov-25 | 4.7 | 18.19 | 10 | 108 | 11
TA 325 | Dec-25 | 3.96 | 18.92 | 9 | 138 | 12
TA 325 | Jan-26 | 2.56 | 2.28 | 2 | 13 | 2
TA 325 | Feb-26 | 0 | 0 | 0 | 0 | 0
TA 325 | Mar-26 | 0 | 0 | 0 | 0 | 0
TA 413 | Apr-25 | 7.54 | 11.46 | 0 | 38 | 3
TA 413 | May-25 | 0 | 0 | 0 | 0 | 0
TA 413 | Jun-25 | 0 | 0 | 0 | 0 | 0
TA 413 | Jul-25 | 0 | 0 | 0 | 0 | 0
TA 413 | Aug-25 | 3.52 | 0 | 0 | 5 | 0
TA 413 | Sep-25 | 4.26 | 5.13 | 0 | 32 | 2
TA 413 | Oct-25 | 7.42 | 4.46 | 0 | 18 | 1
TA 413 | Nov-25 | 14.7 | 4.9 | 0 | 10 | 1
TA 413 | Dec-25 | 5.73 | 7.1 | 0 | 38 | 2
TA 413 | Jan-26 | 3.54 | 6.39 | 0 | 73 | 3
TA 413 | Feb-26 | 4.44 | 4.12 | 0 | 65 | 2
TA 413 | Mar-26 | 6.27 | 13.99 | 0 | 36 | 4
TA 416 | Apr-25 | 0 | 0 | 0 | 0 | 0
TA 416 | May-25 | 6.08 | 8.07 | 2 | 46 | 3
TA 416 | Jun-25 | 3.81 | 8.24 | 1 | 55 | 2
TA 416 | Jul-25 | 7.79 | 7.01 | 2 | 27 | 2
TA 416 | Aug-25 | 5.32 | 8.33 | 2 | 47 | 3
TA 416 | Sep-25 | 4.19 | 3.61 | 3 | 72 | 1
TA 416 | Oct-25 | 5.73 | 17.69 | 3 | 73 | 5
TA 416 | Nov-25 | 4.04 | 9.81 | 3 | 87 | 2
TA 416 | Dec-25 | 2.17 | 7.69 | 3 | 70 | 3
TA 416 | Jan-26 | 3.09 | 7.58 | 3 | 79 | 3
TA 416 | Feb-26 | 2.36 | 8.73 | 4 | 79 | 6
TA 416 | Mar-26 | 6.15 | 7.79 | 2 | 38 | 3
TA 418 | Apr-25 | 0 | 0 | 0 | 0 | 0
TA 418 | May-25 | 0 | 0 | 0 | 0 | 0
TA 418 | Jun-25 | 0 | 0 | 0 | 0 | 0
TA 418 | Jul-25 | 0 | 0 | 0 | 0 | 0
TA 418 | Aug-25 | 0 | 0 | 0 | 0 | 0
TA 418 | Sep-25 | 1.58 | 0 | 1 | 6 | 0
TA 418 | Oct-25 | 1.11 | 1.11 | 2 | 44 | 1
TA 418 | Nov-25 | 2.46 | 0 | 2 | 59 | 0
TA 418 | Dec-25 | 2.86 | 8.94 | 2 | 56 | 3
TA 418 | Jan-26 | 6.66 | 4.96 | 1 | 13 | 2
TA 418 | Feb-26 | 10.32 | 2.02 | 2 | 6 | 1
TA 418 | Mar-26 | 2.35 | 3.41 | 2 | 43 | 3
TA 421 | Apr-25 | 2.89 | 4.25 | 1 | 38 | 2
TA 421 | May-25 | 2.56 | 1.66 | 1 | 36 | 1
TA 421 | Jun-25 | 4.14 | 2.69 | 1 | 45 | 1
TA 421 | Jul-25 | 2.33 | 5.94 | 1 | 13 | 2
TA 421 | Aug-25 | 0.66 | 0 | 1 | 10 | 0
TA 421 | Sep-25 | 4.49 | 5.22 | 2 | 48 | 2
TA 421 | Oct-25 | 4.71 | 11.93 | 2 | 62 | 4
TA 421 | Nov-25 | 5.55 | 4.9 | 2 | 35 | 1
TA 421 | Dec-25 | 5.91 | 12.96 | 2 | 61 | 4
TA 421 | Jan-26 | 9.35 | 12.09 | 2 | 33 | 4
TA 421 | Feb-26 | 7.75 | 5.75 | 2 | 44 | 2
TA 421 | Mar-26 | 6.59 | 16.52 | 3 | 64 | 6
TA 504 | Apr-25 | 0 | 0 | 0 | 0 | 0
TA 504 | May-25 | 0 | 0 | 0 | 0 | 0
TA 504 | Jun-25 | 0 | 0 | 0 | 0 | 0
TA 504 | Jul-25 | 0 | 0 | 0 | 0 | 0
TA 504 | Aug-25 | 0 | 0 | 0 | 0 | 0
TA 504 | Sep-25 | 0 | 0 | 0 | 0 | 0
TA 504 | Oct-25 | 0 | 0 | 0 | 0 | 0
TA 504 | Nov-25 | 0 | 0 | 0 | 0 | 0
TA 504 | Dec-25 | 0 | 0 | 0 | 0 | 0
TA 504 | Jan-26 | 0 | 0 | 0 | 0 | 0
TA 504 | Feb-26 | 5.17 | 8.44 | 1 | 49 | 4
TA 504 | Mar-26 | 8.81 | 0 | 1 | 7 | 0
TA 505 | Apr-25 | 0 | 0 | 0 | 0 | 0
TA 505 | May-25 | 0 | 0 | 0 | 0 | 0
TA 505 | Jun-25 | 0 | 0 | 0 | 0 | 0
TA 505 | Jul-25 | 0 | 0 | 0 | 0 | 0
TA 505 | Aug-25 | 0 | 0 | 0 | 0 | 0
TA 505 | Sep-25 | 0 | 0 | 0 | 0 | 0
TA 505 | Oct-25 | 0 | 0 | 0 | 0 | 0
TA 505 | Nov-25 | 0 | 0 | 0 | 0 | 0
TA 505 | Dec-25 | 0 | 0 | 0 | 0 | 0
TA 505 | Jan-26 | 5.21 | 0 | 1 | 5 | 0
TA 505 | Feb-26 | 4.49 | 5.67 | 1 | 33 | 2
TA 505 | Mar-26 | 3.41 | 6.49 | 2 | 61 | 4
TA 506 | Apr-25 | 0 | 0 | 0 | 0 | 0
TA 506 | May-25 | 0 | 0 | 0 | 0 | 0
TA 506 | Jun-25 | 0 | 0 | 0 | 0 | 0
TA 506 | Jul-25 | 0 | 0 | 0 | 0 | 0
TA 506 | Aug-25 | 0 | 0 | 0 | 0 | 0
TA 506 | Sep-25 | 0 | 0 | 0 | 0 | 0
TA 506 | Oct-25 | 0 | 0 | 0 | 0 | 0
TA 506 | Nov-25 | 0 | 0 | 0 | 0 | 0
TA 506 | Dec-25 | 0.81 | 0 | 1 | 26 | 0
TA 506 | Jan-26 | 3.7 | 8.75 | 2 | 92 | 5
TA 506 | Feb-26 | 8.46 | 17.97 | 2 | 52 | 6
TA 506 | Mar-26 | 5.17 | 1.21 | 1 | 13 | 1
TB 401 | Apr-25 | 0.32 | 0 | 3 | 90 | 0
TB 401 | May-25 | 1.36 | 5.75 | 4 | 131 | 5
TB 401 | Jun-25 | 1.2 | 5.57 | 4 | 158 | 2
TB 401 | Jul-25 | 1.06 | 5.54 | 8 | 241 | 4
TB 401 | Aug-25 | 0.92 | 9.93 | 8 | 232 | 6
TB 401 | Sep-25 | 1.42 | 5.63 | 5 | 163 | 2
TB 401 | Oct-25 | 2.68 | 23.4 | 6 | 217 | 10
TB 401 | Nov-25 | 2.52 | 14.36 | 7 | 145 | 10
TB 401 | Dec-25 | 5.02 | 41.37 | 6 | 97 | 18
TB 401 | Jan-26 | 0 | 0 | 0 | 0 | 0
TB 401 | Feb-26 | 0 | 0 | 0 | 0 | 0
TB 401 | Mar-26 | 0 | 0 | 0 | 0 | 0
TB 408 | Apr-25 | 0.87 | 1.05 | 3 | 81 | 1
TB 408 | May-25 | 0.26 | 3.23 | 3 | 67 | 1
TB 408 | Jun-25 | 0.44 | 0 | 3 | 90 | 0
TB 408 | Jul-25 | 0.44 | 0 | 3 | 93 | 0
TB 408 | Aug-25 | 0.44 | 0 | 3 | 93 | 0
TB 408 | Sep-25 | 0.44 | 3.79 | 3 | 90 | 1
TB 408 | Oct-25 | 0.19 | 0 | 2 | 62 | 0
TB 408 | Nov-25 | 2.51 | 8.73 | 4 | 122 | 3
TB 408 | Dec-25 | 2.17 | 5.74 | 3 | 117 | 2
TB 408 | Jan-26 | 3.28 | 13.48 | 5 | 128 | 5
TB 408 | Feb-26 | 1.28 | 6.41 | 4 | 112 | 3
TB 408 | Mar-26 | 2.06 | 7.29 | 5 | 150 | 4
TB 501 | Apr-25 | 0 | 0 | 0 | 0 | 0
TB 501 | May-25 | 2.22 | 1.48 | 1 | 20 | 2
TB 501 | Jun-25 | 7.49 | 4.26 | 2 | 18 | 3
TB 501 | Jul-25 | 5.04 | 13.32 | 3 | 83 | 7
TB 501 | Aug-25 | 1.92 | 7.89 | 2 | 142 | 4
TB 501 | Sep-25 | 1.41 | 7.85 | 1 | 128 | 13
TB 501 | Oct-25 | 2.74 | 7.12 | 1 | 75 | 11
TB 501 | Nov-25 | 1.03 | 4.7 | 1 | 141 | 7
TB 501 | Dec-25 | 2.33 | 4.49 | 1 | 56 | 7
TB 501 | Jan-26 | 0.9 | 0 | 2 | 9 | 0
TB 501 | Feb-26 | 0.92 | 3.33 | 3 | 117 | 12
TB 501 | Mar-26 | 1.42 | 7.23 | 4 | 147 | 28
TB 507 | Apr-25 | 0 | 0 | 0 | 0 | 0
TB 507 | May-25 | 0 | 0 | 0 | 0 | 0
TB 507 | Jun-25 | 0 | 0 | 0 | 0 | 0
TB 507 | Jul-25 | 0 | 0 | 0 | 0 | 0
TB 507 | Aug-25 | 0 | 0 | 0 | 0 | 0
TB 507 | Sep-25 | 0 | 0 | 0 | 0 | 0
TB 507 | Oct-25 | 0 | 0 | 0 | 0 | 0
TB 507 | Nov-25 | 0 | 0 | 0 | 0 | 0
TB 507 | Dec-25 | 0 | 0 | 0 | 0 | 0
TB 507 | Jan-26 | 0 | 0 | 0 | 0 | 0
TB 507 | Feb-26 | 2.52 | 1.97 | 1 | 48 | 1
TB 507 | Mar-26 | 2.49 | 4.3 | 1 | 64 | 2

## Wide_DPR_KM_month
Month | TA 325 | TA 413 | TA 416 | TA 418 | TA 421 | TA 504 | TA 505 | TA 506 | TB 401 | TB 408 | TB 501 | TB 507
Apr-25 | 3.42 | 7.54 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0.32 | 0.87 | 0 | 0
May-25 | 2.22 | 0 | 6.08 | 0 | 2.56 | 0 | 0 | 0 | 1.36 | 0.26 | 2.22 | 0
Jun-25 | 3.05 | 0 | 3.81 | 0 | 4.14 | 0 | 0 | 0 | 1.2 | 0.44 | 7.49 | 0
Jul-25 | 0 | 0 | 7.79 | 0 | 2.33 | 0 | 0 | 0 | 1.06 | 0.44 | 5.04 | 0
Aug-25 | 0 | 3.52 | 5.32 | 0 | 0.66 | 0 | 0 | 0 | 0.92 | 0.44 | 1.92 | 0
Sep-25 | 1.88 | 4.26 | 4.19 | 1.58 | 4.49 | 0 | 0 | 0 | 1.42 | 0.44 | 1.41 | 0
Oct-25 | 2.36 | 7.42 | 5.73 | 1.11 | 4.71 | 0 | 0 | 0 | 2.68 | 0.19 | 2.74 | 0
Nov-25 | 4.7 | 14.7 | 4.04 | 2.46 | 5.55 | 0 | 0 | 0 | 2.52 | 2.51 | 1.03 | 0
Dec-25 | 3.96 | 5.73 | 2.17 | 2.86 | 5.91 | 0 | 0 | 0.81 | 5.02 | 2.17 | 2.33 | 0
Jan-26 | 2.56 | 3.54 | 3.09 | 6.66 | 9.35 | 0 | 5.21 | 3.7 | 0 | 3.28 | 0.9 | 0
Feb-26 | 0 | 4.44 | 2.36 | 10.32 | 7.75 | 5.17 | 4.49 | 8.46 | 0 | 1.28 | 0.92 | 2.52
Mar-26 | 0 | 6.27 | 6.15 | 2.35 | 6.59 | 8.81 | 3.41 | 5.17 | 0 | 2.06 | 1.42 | 2.49

## Wide_DPR_KM_strung
Month | TA 325 | TA 413 | TA 416 | TA 418 | TA 421 | TA 504 | TA 505 | TA 506 | TB 401 | TB 408 | TB 501 | TB 507
Apr-25 | 19.66 | 11.46 | 0 | 0 | 4.25 | 0 | 0 | 0 | 0 | 1.05 | 0 | 0
May-25 | 8.9 | 0 | 8.07 | 0 | 1.66 | 0 | 0 | 0 | 5.75 | 3.23 | 1.48 | 0
Jun-25 | 4.79 | 0 | 8.24 | 0 | 2.69 | 0 | 0 | 0 | 5.57 | 0 | 4.26 | 0
Jul-25 | 0 | 0 | 7.01 | 0 | 5.94 | 0 | 0 | 0 | 5.54 | 0 | 13.32 | 0
Aug-25 | 0 | 0 | 8.33 | 0 | 0 | 0 | 0 | 0 | 9.93 | 0 | 7.89 | 0
Sep-25 | 0 | 5.13 | 3.61 | 0 | 5.22 | 0 | 0 | 0 | 5.63 | 3.79 | 7.85 | 0
Oct-25 | 3.56 | 4.46 | 17.69 | 1.11 | 11.93 | 0 | 0 | 0 | 23.4 | 0 | 7.12 | 0
Nov-25 | 18.19 | 4.9 | 9.81 | 0 | 4.9 | 0 | 0 | 0 | 14.36 | 8.73 | 4.7 | 0
Dec-25 | 18.92 | 7.1 | 7.69 | 8.94 | 12.96 | 0 | 0 | 0 | 41.37 | 5.74 | 4.49 | 0
Jan-26 | 2.28 | 6.39 | 7.58 | 4.96 | 12.09 | 0 | 0 | 8.75 | 0 | 13.48 | 0 | 0
Feb-26 | 0 | 4.12 | 8.73 | 2.02 | 5.75 | 8.44 | 5.67 | 17.97 | 0 | 6.41 | 3.33 | 1.97
Mar-26 | 0 | 13.99 | 7.79 | 3.41 | 16.52 | 0 | 6.49 | 1.21 | 0 | 7.29 | 7.23 | 4.3

## FY_Project_Rank
Project | Avg DPR KM/month across active months | FY DPR KM strung | Active productivity months | Active KM months | FY DPR daily rows | FY DPR compiled spans | FY KM strung rank | Avg KM/month rank
TB 401 | 1.83 | 111.55 | 9 | 8 | 1474 | 57 | 1 | 11
TA 416 | 4.61 | 94.55 | 11 | 11 | 673 | 33 | 2 | 4
TA 421 | 4.74 | 83.91 | 12 | 11 | 489 | 29 | 3 | 3
TA 325 | 3.02 | 76.3 | 8 | 7 | 633 | 48 | 4 | 8
TB 501 | 2.49 | 61.67 | 11 | 10 | 936 | 94 | 5 | 10
TA 413 | 6.38 | 57.55 | 9 | 8 | 315 | 18 | 6 | 2
TB 408 | 1.2 | 49.72 | 12 | 8 | 1205 | 20 | 7 | 12
TA 506 | 4.54 | 27.93 | 4 | 3 | 183 | 12 | 8 | 5
TA 418 | 3.91 | 20.44 | 7 | 5 | 227 | 10 | 9 | 7
TA 505 | 4.37 | 12.16 | 3 | 2 | 99 | 6 | 10 | 6
TA 504 | 6.99 | 8.44 | 2 | 1 | 56 | 4 | 11 | 1
TB 507 | 2.5 | 6.27 | 2 | 2 | 112 | 3 | 12 | 9

## External_Context
Project | Month Label | Reported KM strung | Reported TSE available | Reported productivity per TSE | Reported/planned KM from Future | Future adjacent Converted Hexa/TSE context
TB 401 | Apr-25 | 0 | 2 | 0
TB 401 | Aug-25 | 9.9 | 3 | 3.3
TB 401 | Dec-25 | 36 | 4 | 9
TB 401 | Feb-26
TB 401 | Jan-26 |  |  |  | 56.1 | 4
TB 401 | Jul-25 | 5.5 | 3 | 1.8333
TB 401 | Jun-25 | 5.5 | 3 | 1.8333
TB 401 | Mar-26
TB 401 | May-25 | 5.7 | 2 | 2.85
TB 401 | Nov-25 | 3.4 | 3 | 1.1333
TB 401 | Oct-25 | 24 | 4 | 6
TB 401 | Sep-25 | 5.6 | 3 | 1.8667
TB 408 | Apr-25 | 1 | 1 | 1
TB 408 | Aug-25 | 0
TB 408 | Dec-25 | 6 | 1 | 6
TB 408 | Feb-26 |  |  |  | 35 | 4
TB 408 | Jan-26 |  |  |  | 20 | 2
TB 408 | Jul-25 | 0
TB 408 | Jun-25 | 0
TB 408 | Mar-26 |  |  |  | 30 | 4
TB 408 | May-25 | 3.2 | 1 | 3.2
TB 408 | Nov-25 | 9 | 1 | 9
TB 408 | Oct-25 | 1.6

## Notes
Field | Definition
FY | 2025-04-01 to 2026-03-31
Scope | TSE only: method text containing TSE, case-insensitive
DPR KM/month | Mean daily_km for project-month * 30, matching export_stringing_summary.py
DPR KM strung | Completed TSE span length_km by F/S completion month; source month fallback only when F/S month blank
External context | Read from C:\Users\kaushikb\OneDrive - RPG Enterprises\Data - 05-01-26- R0.xlsx. Productvity gives Apr-Dec reported KM/TSE/prod per TSE. Future gives Jan-Mar plan/context, not treated as actual.