## RawData
project_code | project_display | project_scope_key | line_name | line_name_source | section_label | source_file | source_sheet | configured_sheet | template_sheet | report_date | header_row_number | source_row_number | stretch_identifier | from_ap | to_ap | length_m_raw | length_km | readiness_raw | final_check_raw | tack_welding_raw | balance_towers | readiness_state | remarks | readiness_source | source_tag | location_nos_raw | location_parse_status | location_parse_issue | required_location_count | matched_location_count | unmatched_location_count | required_locations | matched_locations | unmatched_locations
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 11 | Gantry - AP-1 |  |  | 150.014 | 0.15001 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 12 | AP-1 - AP-2A |  |  | 290.21 | 0.29021 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 13 | AP/2A - AP/3A |  |  | 2836.992 | 2.837 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 14 | AP3A/0-AP3B/0 |  |  | 2691.467 | 2.6915 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 15 | AP3B/0-AP4/0 |  |  | 1627.07 | 1.6271 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 16 | AP-4 - AP-4A/0 |  |  | 709.163 | 0.70916 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 17 | AP-4A/0 - AP-5 |  |  | 2681.611 | 2.6816 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 18 | AP-5 - AP-5A/0 |  |  | 4418.389 | 4.4184 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 19 | AP-5A/0 - AP-6 |  |  | 419.48 | 0.41948 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 20 | AP-6 - AP-7 |  |  | 4901.236 | 4.9012 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 21 | AP-7 - AP-7A/0 |  |  | 2699.284 | 2.6993 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 22 | AP-7A/0 - AP-8/0 |  |  | 2434.77 | 2.4348 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 23 | AP-8/0 - AP-8A/0 |  |  | 4455 | 4.455 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 24 | AP-8A/0 - AP-9/0 |  |  | 466.63 | 0.46663 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 25 | AP-9/0 - AP-10/0 |  |  | 4964.92 | 4.9649 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 26 | AP-10/0 - AP-11/0 |  |  | 1004.183 | 1.0042 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 27 | AP-11/0 - AP-12/0 |  |  | 242.89 | 0.24289 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 28 | AP-12/0 - AP-13/0 |  |  | 329.73 | 0.32973 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 29 | AP-13/0 - AP-13A/0 |  |  | 416.88 | 0.41688 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 30 | AP-13A/0 - AP-14/0 |  |  | 480.27 | 0.48027 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 31 | AP-14/0 - AP-15/0 |  |  | 223.82 | 0.22382 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 32 | AP-15/0 - AP-16/0 |  |  | 5019.34 | 5.0193 |  |  |  | 1 | NOT_READY | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 33 | AP-16/0 - AP-17/0 |  |  | 392.69 | 0.39269 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 34 | AP-17/0 - AP-18/0 |  |  | 398.4 | 0.3984 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 35 | AP-18/0 - AP-19/0 |  |  | 3030.029 | 3.03 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 36 | AP-19/0 - AP-20/0 |  |  | 279.36 | 0.27936 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 37 | AP-20/0 - AP-21/0 |  |  | 2550.167 | 2.5502 |  |  |  |  | UNKNOWN | WIP | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 38 | AP-21/0 - AP-22/0 |  |  | 2283.535 | 2.2835 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 39 | AP-22/0 - AP-23/0 |  |  | 259.05 | 0.25905 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 40 | AP-23/0 - AP-23A/0 |  |  | 440.46 | 0.44046 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 41 | AP-23A/0 - AP-24/0 |  |  | 496.69 | 0.49669 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 42 | AP-24/0 - AP-25/0 |  |  | 244.03 | 0.24403 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 43 | AP-25/0 - AP-26/0 |  |  | 237.43 | 0.23743 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 44 | AP-26/0 - AP-27/0 |  |  | 203.48 | 0.20348 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 45 | AP-27/0 - AP-28/0 |  |  | 2548.275 | 2.5483 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 46 | AP-28/0 - AP-29/0 |  |  | 211.21 | 0.21121 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 47 | AP-29/0 - AP-29A/0 |  |  | 2379.204 | 2.3792 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 48 | AP-29A/0 - AP-30/0 |  |  | 2669.008 | 2.669 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 49 | AP-30/0 - AP-31/0 |  |  | 4124.232 | 4.1242 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 50 | AP-31/0 - AP-32/0 |  |  | 4333.369 | 4.3334 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 51 | AP-32/0 - AP-32A/0 |  |  | 3283.51 | 3.2835 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 52 | AP-32A/0 - AP-33/0 |  |  | 840.439 | 0.84044 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 53 | AP-33/0 - AP-34/0 |  |  | 4049.763 | 4.0498 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 54 | AP-34/0 - AP-35/0 |  |  | 4898.588 | 4.8986 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 55 | AP-35/0 - AP-36/0 |  |  | 4916.293 | 4.9163 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 56 | AP-36/0 - AP-36A/0 |  |  | 454 | 0.454 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 57 | AP-36A/0 - AP 36B/0 |  |  | 826.7 | 0.8267 |  |  |  | 1 | NOT_READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 58 | AP-36B/0 N - AP-36C/0 N |  |  | 420.81 | 0.42081 |  |  |  | 1 | NOT_READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 59 | AP-36C/0 N - AP-37/0 N |  |  | 469.33 | 0.46933 |  |  |  | 1 | NOT_READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 60 | AP-37/0 N - AP-37A/0 |  |  | 2076.28 | 2.0763 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 61 | AP-37A/0 - AP-38/0 |  |  | 2583.589 | 2.5836 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 62 | AP-38/0 - AP-39/0 |  |  | 4163.677 | 4.1637 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 63 | AP-39/0 - AP-40/0 |  |  | 4716.811 | 4.7168 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 64 | AP-40/0 - AP-40A/0 |  |  | 4665.918 | 4.6659 |  |  |  |  | UNKNOWN | Completed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 65 | AP-40A/0 - AP-41/0 |  |  | 410.61 | 0.41061 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 66 | AP-41/0 - AP-42/0 |  |  | 823.782 | 0.82378 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 67 | AP-42/0 - AP-42/3 |  |  | 1258.998 | 1.259 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 68 | AP-42/3 - AP-43/0 |  |  | 424.891 | 0.42489 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 69 | AP-43/0 - AP-43/5 |  |  | 1851.866 | 1.8519 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 70 | AP-43/5-AP-44/0 |  |  | 1584.546 | 1.5845 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 71 | AP-44/0-AP45/0 |  |  | 2383.155 | 2.3832 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 72 | AP-45/0-AP-46/0 |  |  | 208.53 | 0.20853 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 73 |  |  |  | 117.8561 | 0.11786 |  |  |  | 4 | NOT_READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 74 | Type |  |  | Total Length (Km) | [5 empty] | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 75 | TSE |  |  | 109.2852 | 0.10929 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 413 | TA 413 | ta413 |  | filename |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | TA 413 Stretch | 2026-07-28 | 9 | 76 | Manual |  |  | 8.5709 | 0.0085709 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 18 | 0A/0 (CT) |  |  |  |  | Manual |  |  | 2 | NOT_READY | 447.34 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 19 | 0B/0 |  |  | 447.34 | 0.44734 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 20 | 0B/1 |  |  | 361.46 | 0.36146 | TSE |  |  | 4 | NOT_READY | 1594.82 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 21 | 0B/2 |  |  | 419.88 | 0.41988 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 22 | 0B/3 |  |  | 395.03 | 0.39503 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 23 | 0C/0 |  |  | 418.45 | 0.41845 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 24 | 0C/1 |  |  | 386.02 | 0.38602 | TSE |  |  | 2 | NOT_READY | 793.45 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 25 | 0D/0 |  |  | 407.43 | 0.40743 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 26 | 0D/1 |  |  | 419 | 0.419 | TSE |  |  | 5 | NOT_READY | 2099.0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 27 | 0D/2 |  |  | 409.1 | 0.4091 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 28 | 0D/3 |  |  | 430.69 | 0.43069 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 29 | 0D/4 |  |  | 406.16 | 0.40616 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 30 | 0D/5 |  |  | 434.05 | 0.43405 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 31 | 0E/0 |  |  | 449.69 | 0.44969 | Manual |  |  | 1 | NOT_READY | 449.69 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 32 | 0E/1 |  |  | 425.26 | 0.42526 | TSE |  |  | 3 | NOT_READY | 1238.46 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 33 | 0E/2 |  |  | 401.94 | 0.40194 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 34 | 0F/0 |  |  | 411.26 | 0.41126 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 35 | 0G/0 |  |  | 283.43 | 0.28343 | Manual |  |  | 1 | NOT_READY | 283.43 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 36 | 0G/1 |  |  | 433.48 | 0.43348 | TSE |  |  | 2 | NOT_READY | 799.95 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 37 | 0H/0 |  |  | 366.47 | 0.36647 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 38 | 1/0 |  |  | 245.33 | 0.24533 | Manual |  |  | 1 | NOT_READY | 245.33 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 39 | 2/0 |  |  | 199.37 | 0.19937 | Manual |  |  | 1 | NOT_READY | 199.37 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 40 | 3/0 |  |  | 263.38 | 0.26338 | Manual |  |  | 1 | NOT_READY | 263.38 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 41 | 3/1 |  |  | 382.35 | 0.38235 | TSE |  |  | 6 | NOT_READY | 2405.4800000000005 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 42 | 3/2 |  |  | 444.92 | 0.44492 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 43 | 3/3 |  |  | 389.86 | 0.38986 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 44 | 3/4 |  |  | 350.2 | 0.3502 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 45 | 3/5 |  |  | 444.89 | 0.44489 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 46 | 4/0 |  |  | 393.26 | 0.39326 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 47 | 4/1 |  |  | 396.81 | 0.39681 | TSE |  |  | 2 | NOT_READY | 775.24 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 48 | 5/0 |  |  | 378.43 | 0.37843 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 49 | 5/1 |  |  | 371.68 | 0.37168 | TSE |  |  | 5 | NOT_READY | 1991.87 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 50 | 5/2 |  |  | 379.91 | 0.37991 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 51 | 5/3 |  |  | 422.51 | 0.42251 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 52 | 5/4 |  |  | 417.45 | 0.41745 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 53 | 6/0 |  |  | 400.32 | 0.40032 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 54 | 6/1 |  |  | 376.76 | 0.37676 | TSE |  |  | 13 | NOT_READY | 4993.95 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 55 | 6/2 |  |  | 382.86 | 0.38286 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 56 | 6/3 |  |  | 440.1 | 0.4401 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 57 | 6/4 |  |  | 399.83 | 0.39983 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 58 | 6/5 |  |  | 405.28 | 0.40528 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 59 | 6/6 |  |  | 434.95 | 0.43495 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 60 | 6/7 |  |  | 390.04 | 0.39004 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 61 | 6/8 |  |  | 364.88 | 0.36488 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 62 | 6/9 |  |  | 324.16 | 0.32416 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 63 | 6/10 |  |  | 335.59 | 0.33559 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 64 | 6/11 |  |  | 358.72 | 0.35872 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 65 | 6/12 |  |  | 351.5 | 0.3515 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 66 | 7/0 |  |  | 429.28 | 0.42928 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 67 | 7/1 |  |  | 421.18 | 0.42118 | TSE |  |  | 2 | NOT_READY | 840.03 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 68 | 8/0 |  |  | 418.85 | 0.41885 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 69 | 9/0 |  |  | 339.15 | 0.33915 | Manual |  |  | 1 | NOT_READY | 339.15 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 70 | 10/0 |  |  | 473.56 | 0.47356 | Manual |  |  | 1 | NOT_READY | 473.56 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 71 | 11/0 |  |  | 264.19 | 0.26419 | Manual |  |  | 1 | NOT_READY | 264.19 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 72 | 11/1 |  |  | 378.01 | 0.37801 | Manual |  |  | 1 | NOT_READY | 378.01 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 73 | 11/2 |  |  | 484.94 | 0.48494 | Manual |  |  | 1 | NOT_READY | 484.94 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 74 | 11/3 |  |  | 400.04 | 0.40004 | TSE |  |  | 3 | NOT_READY | 1185.9099999999999 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 75 | 11/4 |  |  | 339.98 | 0.33998 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 76 | 12/0 |  |  | 445.89 | 0.44589 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 77 | 12/1 |  |  | 389.25 | 0.38925 | TSE |  |  | 3 | NOT_READY | 1141.1000000000001 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 78 | 12/2 |  |  | 369.91 | 0.36991 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 79 | 12A/0 |  |  | 381.94 | 0.38194 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 80 | 12A/1 |  |  | 417.05 | 0.41705 | TSE |  |  | 2 | NOT_READY | 840.3299999999999 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 81 | 13/0 |  |  | 423.28 | 0.42328 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 82 | 14/0 |  |  | 277.65 | 0.27765 | Manual |  |  | 1 | NOT_READY | 277.65 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 83 | 14/1 |  |  | 347 | 0.347 | TSE |  |  | 2 | NOT_READY | 700.36 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 84 | 15/0 |  |  | 353.36 | 0.35336 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 85 | 15A/0 |  |  | 282.44 | 0.28244 | Manual |  |  | 1 | NOT_READY | 282.44 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 86 | 16/0 |  |  | 247.43 | 0.24743 | Manual |  |  | 1 | NOT_READY | 247.43 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 87 | 17/0 |  |  | 364.22 | 0.36422 | Manual |  |  | 1 | NOT_READY | 364.22 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 88 | 17/1 |  |  | 332.67 | 0.33267 | TSE |  |  | 3 | NOT_READY | 1084.26 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 89 | 17/2 |  |  | 334.43 | 0.33443 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 90 | 18/0 |  |  | 417.16 | 0.41716 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 91 | 19/0 |  |  | 357.44 | 0.35744 | Manual |  |  | 1 | NOT_READY | 357.44 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 92 | 19/1 |  |  | 317.81 | 0.31781 | TSE |  |  | 6 | NOT_READY | 2321.07 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 93 | 19/2 |  |  | 380.3 | 0.3803 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 94 | 19/3 |  |  | 399 | 0.399 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 95 | 19/4 |  |  | 395.48 | 0.39548 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 96 | 19/5 |  |  | 400.26 | 0.40026 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 97 | 20/0 |  |  | 428.22 | 0.42822 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 98 | 20/1 |  |  | 382.37 | 0.38237 | TSE |  |  | 3 | NOT_READY | 1081.63 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 99 | 20/2 |  |  | 339.97 | 0.33997 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 100 | 20/3 |  |  | 359.29 | 0.35929 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 101 | 21/0 |  |  | 358.52 | 0.35852 | Manual |  |  | 1 | NOT_READY | 358.52 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 102 | 22/0 |  |  | 238.09 | 0.23809 | Manual |  |  | 1 | NOT_READY | 238.09 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 103 | 22/1 |  |  | 378.09 | 0.37809 | TSE |  |  | 4 | NOT_READY | 1531.84 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 104 | 22/2 |  |  | 410.18 | 0.41018 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 105 | 22/3 |  |  | 365.02 | 0.36502 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 106 | 23/0 |  |  | 378.55 | 0.37855 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 107 | 23/1 |  |  | 356.18 | 0.35618 | TSE |  |  | 4 | NOT_READY | 1521.5700000000002 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 108 | 23/2 |  |  | 345 | 0.345 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 109 | 23/3 |  |  | 414.54 | 0.41454 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 110 | 24/0 |  |  | 405.85 | 0.40585 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 111 | 24/1 |  |  | 369.22 | 0.36922 | TSE |  |  | 4 | NOT_READY | 1524.48 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 112 | 24/2 |  |  | 349.88 | 0.34988 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 113 | 24/3 |  |  | 395.34 | 0.39534 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 114 | 25/0 |  |  | 410.04 | 0.41004 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 115 | 26/0 |  |  | 221.32 | 0.22132 | Manual |  |  | 1 | NOT_READY | 221.32 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 116 | 26/1 |  |  | 473.23 | 0.47323 | TSE |  |  | 7 | NOT_READY | 2761.2799999999997 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 117 | 26/2 |  |  | 365.6 | 0.3656 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 118 | 26/3 |  |  | 390.02 | 0.39002 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 119 | 26/4 |  |  | 394.93 | 0.39493 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 120 | 26/5 |  |  | 365.42 | 0.36542 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 121 | 26/6 |  |  | 384.96 | 0.38496 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 122 | 27/0 |  |  | 387.12 | 0.38712 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 123 | 27/1 |  |  | 431.29 | 0.43129 | TSE |  |  | 4 | NOT_READY | 1507.3899999999999 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 124 | 27/2 |  |  | 386.54 | 0.38654 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 125 | 27/3 |  |  | 349.96 | 0.34996 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 126 | 28/0 |  |  | 339.6 | 0.3396 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 127 | 28/1 |  |  | 375.28 | 0.37528 | TSE |  |  | 2 | NOT_READY | 739.92 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 128 | 29/0 |  |  | 364.64 | 0.36464 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 129 | 30/0 |  |  | 207.12 | 0.20712 | Manual |  |  | 1 | NOT_READY | 207.12 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 130 | 30/1 |  |  | 382.05 | 0.38205 | TSE |  |  | 2 | NOT_READY | 785.64 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 131 | 31/0 |  |  | 403.59 | 0.40359 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 132 | 31/1 |  |  | 411.59 | 0.41159 | TSE |  |  | 3 | NOT_READY | 1169.33 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 133 | 31/2 |  |  | 422.37 | 0.42237 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 134 | 32/0 |  |  | 335.37 | 0.33537 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 135 | 33/0 |  |  | 269.5 | 0.2695 | Manual |  |  | 1 | NOT_READY | 269.5 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 136 | 33/1 |  |  | 358.26 | 0.35826 | TSE |  |  | 2 | NOT_READY | 708.89 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 137 | 34/0 |  |  | 350.63 | 0.35063 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 138 | 34/1 |  |  | 384.36 | 0.38436 | TSE |  |  | 2 | NOT_READY | 774.54 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 139 | 35/0 |  |  | 390.18 | 0.39018 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 140 | 36/0 |  |  | 246.98 | 0.24698 | Manual |  |  | 1 | NOT_READY | 246.98 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 141 | 36/1 |  |  | 397.66 | 0.39766 | TSE |  |  | 4 | NOT_READY | 1617.6399999999999 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 142 | 36/2 |  |  | 440.1 | 0.4401 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 143 | 36/3 |  |  | 347.03 | 0.34703 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 144 | 36/4 |  |  | 432.85 | 0.43285 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 145 | 36/5 |  |  | 444.68 | 0.44468 | TSE |  |  | 7 | NOT_READY | 2789.12 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 146 | 36/6 |  |  | 334.39 | 0.33439 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 147 | 36/7 |  |  | 390.9 | 0.3909 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 148 | 36/8 |  |  | 385.73 | 0.38573 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 149 | 36/9 |  |  | 409.46 | 0.40946 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 150 | 36/10 |  |  | 424.91 | 0.42491 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 151 | 37/0 |  |  | 399.05 | 0.39905 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 152 | 38/0 |  |  | 262.38 | 0.26238 | Manual |  |  | 1 | NOT_READY | 262.38 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 153 | 38/1 |  |  | 468.32 | 0.46832 | TSE |  |  | 12 | NOT_READY | 4946.999999999999 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 154 | 38/2 |  |  | 369.98 | 0.36998 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 155 | 38/3 |  |  | 400 | 0.4 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 156 | 38/4 |  |  | 420 | 0.42 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 157 | 38/5 |  |  | 417.07 | 0.41707 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 158 | 38/6 |  |  | 422.95 | 0.42295 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 159 | 38/7 |  |  | 415.02 | 0.41502 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 160 | 38/8 |  |  | 424.87 | 0.42487 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 161 | 38/9 |  |  | 400 | 0.4 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 162 | 38/10 |  |  | 364.92 | 0.36492 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 163 | 38/11 |  |  | 407.25 | 0.40725 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 164 | 39/0 |  |  | 436.62 | 0.43662 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 165 | 40/0 |  |  | 200.61 | 0.20061 | Manual |  |  | 1 | NOT_READY | 200.61 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 166 | 40/1 |  |  | 470.69 | 0.47069 | TSE |  |  | 10 | NOT_READY | 4067.6099999999997 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 167 | 40/2 |  |  | 367.4 | 0.3674 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 168 | 40/3 |  |  | 427.94 | 0.42794 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 169 | 40/4 |  |  | 416.92 | 0.41692 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 170 | 40/5 |  |  | 410.04 | 0.41004 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 171 | 40/6 |  |  | 414.91 | 0.41491 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 172 | 40/7 |  |  | 394.95 | 0.39495 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 173 | 40/8 |  |  | 379.33 | 0.37933 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 174 | 40/9 |  |  | 401.83 | 0.40183 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 175 | 41/0 |  |  | 383.6 | 0.3836 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 176 | 41/1 |  |  | 339.72 | 0.33972 | TSE |  |  | 9 | NOT_READY | 3468.86 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 177 | 41/2 |  |  | 346.64 | 0.34664 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 178 | 41/3 |  |  | 325.19 | 0.32519 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 179 | 41/4 |  |  | 415.04 | 0.41504 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 180 | 41/5 |  |  | 384.26 | 0.38426 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 181 | 41/6 |  |  | 405.89 | 0.40589 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 182 | 41/7 |  |  | 418.82 | 0.41882 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 183 | 41/8 |  |  | 380.82 | 0.38082 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 184 | 42/0 |  |  | 452.48 | 0.45248 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 185 | 43/0 |  |  | 219.42 | 0.21942 | Manual |  |  | 1 | NOT_READY | 219.42 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 186 | 43/1 |  |  | 482.34 | 0.48234 | TSE |  |  | 7 | NOT_READY | 2622.21 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 187 | 43/2 |  |  | 350.32 | 0.35032 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 188 | 43/3 |  |  | 364.91 | 0.36491 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 189 | 43/4 |  |  | 340.91 | 0.34091 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 190 | 43/5 |  |  | 359.3 | 0.3593 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 191 | 43/6 |  |  | 354.67 | 0.35467 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 192 | 44/0 |  |  | 369.76 | 0.36976 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 193 | 45/0 |  |  | 446.79 | 0.44679 | Manual |  |  | 1 | NOT_READY | 446.79 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 194 | 46/0 |  |  | 233.98 | 0.23398 | Manual |  |  | 1 | NOT_READY | 233.98 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 195 | 46/1 |  |  | 434.08 | 0.43408 | TSE |  |  | 5 | NOT_READY | 2072.0699999999997 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 196 | 46/2 |  |  | 396.74 | 0.39674 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 197 | 46/3 |  |  | 407.9 | 0.4079 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 198 | 46/4 |  |  | 416.91 | 0.41691 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 199 | 47/0 |  |  | 416.44 | 0.41644 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 200 | 48/0 |  |  | 349.44 | 0.34944 | Manual |  |  | 1 | NOT_READY | 349.44 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 201 | 48/1 |  |  | 347 | 0.347 | TSE |  |  | 2 | NOT_READY | 808.5899999999999 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 202 | 49/0 |  |  | 461.59 | 0.46159 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 203 | 50/0 |  |  | 207.14 | 0.20714 | Manual |  |  | 1 | NOT_READY | 207.14 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 204 | 50/1 |  |  | 482.87 | 0.48287 | Manual |  |  | 1 | NOT_READY | 482.87 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 205 | 51/0 |  |  | 370.42 | 0.37042 | Manual |  |  | 1 | NOT_READY | 370.42 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 206 | 52/0 |  |  | 252.5 | 0.2525 | Manual |  |  | 1 | NOT_READY | 252.5 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 207 | 52/1 |  |  | 313.4 | 0.3134 | TSE |  |  | 3 | NOT_READY | 1015.88 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 208 | 52/2 |  |  | 340 | 0.34 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 209 | 53/0 |  |  | 362.48 | 0.36248 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 210 | 54/0 |  |  | 219.62 | 0.21962 | Manual |  |  | 1 | NOT_READY | 219.62 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 211 | 54/1 |  |  | 372.57 | 0.37257 | TSE |  |  | 8 | NOT_READY | 3182.59 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 212 | 54/2 |  |  | 404.66 | 0.40466 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 213 | 54/3 |  |  | 379.94 | 0.37994 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 214 | 54/4 |  |  | 369.97 | 0.36997 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 215 | 54/5 |  |  | 409.97 | 0.40997 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 216 | 54/6 |  |  | 414.96 | 0.41496 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 217 | 54/7 |  |  | 369.9 | 0.3699 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 218 | 55/0 |  |  | 460.62 | 0.46062 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 219 | 55/1 |  |  | 374.27 | 0.37427 | TSE |  |  | 7 | NOT_READY | 2583.14 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 220 | 55/2 |  |  | 280.97 | 0.28097 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 221 | 55/3 |  |  | 309.68 | 0.30968 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 222 | 55/4 |  |  | 390.19 | 0.39019 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 223 | 55/5 |  |  | 395.08 | 0.39508 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 224 | 55/6 |  |  | 412.89 | 0.41289 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 225 | 56/0 |  |  | 420.06 | 0.42006 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 226 | 57/0 |  |  | 221.82 | 0.22182 | Manual |  |  | 1 | NOT_READY | 221.82 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 227 | 57/1 |  |  | 406.53 | 0.40653 | TSE |  |  | 2 | NOT_READY | 819.68 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 228 | 58/0 |  |  | 413.15 | 0.41315 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 229 | 59/0 |  |  | 294.64 | 0.29464 | Manual |  |  | 1 | NOT_READY | 294.64 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 230 | 59/1 |  |  | 287.37 | 0.28737 | TSE |  |  | 2 | NOT_READY | 620.1 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 231 | 60/0 |  |  | 332.73 | 0.33273 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 232 | 61/0 |  |  | 193.99 | 0.19399 | Manual |  |  | 1 | NOT_READY | 193.99 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 233 | 61/1 |  |  | 440.01 | 0.44001 | TSE |  |  | 2 | NOT_READY | 817.16 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 234 | 62/0 |  |  | 377.15 | 0.37715 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 235 | 62/1 |  |  | 430.22 | 0.43022 | TSE |  |  | 6 | NOT_READY | 2455.63 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 236 | 62/2 |  |  | 334.88 | 0.33488 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 237 | 62/3 |  |  | 470.73 | 0.47073 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 238 | 62/4 |  |  | 383.72 | 0.38372 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 239 | 62/5 |  |  | 410.24 | 0.41024 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 240 | 63/0 |  |  | 425.84 | 0.42584 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 241 | 63/1 |  |  | 371.1 | 0.3711 | TSE |  |  | 7 | NOT_READY | 2624.87 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 242 | 63/2 |  |  | 390.02 | 0.39002 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 243 | 63/3 |  |  | 380.95 | 0.38095 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 244 | 63/4 |  |  | 369.95 | 0.36995 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 245 | 63/5 |  |  | 346.43 | 0.34643 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 246 | 63/6 |  |  | 374.96 | 0.37496 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 247 | 63A/0 |  |  | 391.46 | 0.39146 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 248 | 63B/0 |  |  | 350.46 | 0.35046 | Manual |  |  | 1 | NOT_READY | 350.46 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 249 | 63B/1 |  |  | 354.99 | 0.35499 | TSE |  |  | 7 | NOT_READY | 2771.42 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 250 | 63B/2 |  |  | 428.99 | 0.42899 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 251 | 63B/3 |  |  | 405 | 0.405 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 252 | 63B/4 |  |  | 370 | 0.37 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 253 | 63B/5 |  |  | 375 | 0.375 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 254 | 63B/6 |  |  | 384.3 | 0.3843 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 255 | 64/0 |  |  | 453.14 | 0.45314 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 256 | 64/1 |  |  | 363.55 | 0.36355 | TSE |  |  | 2 | NOT_READY | 769.94 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 257 | 64/2 |  |  | 406.39 | 0.40639 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 258 | 64/3 |  |  | 471.65 | 0.47165 | TSE |  |  | 4 | NOT_READY | 1614.1399999999999 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 259 | 64/4 |  |  | 323 | 0.323 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 260 | 64/5 |  |  | 408.99 | 0.40899 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 261 | 64A/0 |  |  | 410.5 | 0.4105 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 262 | 65/0 |  |  | 454.37 | 0.45437 | Manual |  |  | 1 | NOT_READY | 454.37 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 263 | 65/1 |  |  | 361.81 | 0.36181 | TSE |  |  | 3 | NOT_READY | 1169.06 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 264 | 65/2 |  |  | 400 | 0.4 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 265 | 66/0 |  |  | 407.25 | 0.40725 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 266 | 66/1 |  |  | 294.34 | 0.29434 | TSE |  |  | 2 | NOT_READY | 775.69 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 267 | 67/0 |  |  | 481.35 | 0.48135 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 268 | 68/0 |  |  | 368.45 | 0.36845 | Manual |  |  | 1 | NOT_READY | 368.45 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 269 | 69/0 |  |  | 349.57 | 0.34957 | Manual |  |  | 1 | NOT_READY | 349.57 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 270 | 70/0 |  |  | 420.91 | 0.42091 | Manual |  |  | 1 | NOT_READY | 420.91 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 271 | 71/0 |  |  | 309.86 | 0.30986 | Manual |  |  | 1 | NOT_READY | 309.86 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 272 | 72/0 |  |  | 364.16 | 0.36416 | Manual |  |  | 1 | NOT_READY | 364.16 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 273 | 73/0 |  |  | 208.46 | 0.20846 | Manual |  |  | 1 | NOT_READY | 208.46 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 274 | 74/0 |  |  | 395.52 | 0.39552 | Manual |  |  | 1 | NOT_READY | 395.52 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 275 | 75/0 |  |  | 266.46 | 0.26646 | Manual |  |  | 1 | NOT_READY | 266.46 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 276 | 76/0 |  |  | 209.25 | 0.20925 | Manual |  |  | 1 | NOT_READY | 209.25 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 277 | 76/1 |  |  | 428.58 | 0.42858 | TSE |  |  | 4 | NOT_READY | 1639.09 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 278 | 76/2 |  |  | 400 | 0.4 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 279 | 76/3 |  |  | 414 | 0.414 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 280 | 77/0 |  |  | 396.51 | 0.39651 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 281 | 78/0 |  |  | 394.65 | 0.39465 | Manual |  |  | 1 | NOT_READY | 394.65 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 282 | 78/1 |  |  | 412.22 | 0.41222 | TSE |  |  | 5 | NOT_READY | 2033.85 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 283 | 78/2 |  |  | 418.33 | 0.41833 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 284 | 78/3 |  |  | 403.29 | 0.40329 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 285 | 78/4 |  |  | 400.19 | 0.40019 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 286 | 78A/0 |  |  | 399.82 | 0.39982 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 287 | 79/0 |  |  | 430.8 | 0.4308 | Manual |  |  | 1 | NOT_READY | 430.8 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 288 | 80/0 |  |  | 240.54 | 0.24054 | Manual |  |  | 1 | NOT_READY | 240.54 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 289 | 81/0 |  |  | 255.15 | 0.25515 | Manual |  |  | 1 | NOT_READY | 255.15 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 290 | 82/0 |  |  | 188.84 | 0.18884 | Manual |  |  | 1 | NOT_READY | 188.84 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 291 | 83/0 |  |  | 397.99 | 0.39799 | Manual |  |  | 1 | NOT_READY | 397.99 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 292 | 83/1 |  |  | 464.99 | 0.46499 | TSE |  |  | 10 | NOT_READY | 3875.28 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 293 | 83/2 |  |  | 365.09 | 0.36509 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 294 | 83/3 |  |  | 465 | 0.465 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 295 | 83/4 |  |  | 365 | 0.365 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 296 | 83/5 |  |  | 335.81 | 0.33581 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 297 | 83/6 |  |  | 353.97 | 0.35397 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 298 | 83/7 |  |  | 369.59 | 0.36959 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 299 | 83/8 |  |  | 370 | 0.37 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 300 | 83/9 |  |  | 388.72 | 0.38872 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 301 | 84/0 |  |  | 397.11 | 0.39711 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 302 | 84/1 |  |  | 322.91 | 0.32291 | TSE |  |  | 6 | NOT_READY | 2169.66 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 303 | 84/2 |  |  | 400.16 | 0.40016 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 304 | 84/3 |  |  | 364.97 | 0.36497 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 305 | 84/4 |  |  | 338.52 | 0.33852 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 306 | 84/5 |  |  | 357.84 | 0.35784 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 307 | 84A/0 |  |  | 385.26 | 0.38526 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 308 | 84A/1 |  |  | 408.32 | 0.40832 | TSE |  |  | 2 | NOT_READY | 670.06 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 309 | 85/0 |  |  | 261.74 | 0.26174 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 310 | 85A/0 |  |  | 289.67 | 0.28967 | Manual |  |  | 1 | NOT_READY | 289.67 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 311 | 85B/0 |  |  | 385.12 | 0.38512 |  |  |  |  | UNKNOWN | 385.12 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 312 | 86/0 |  |  | 348.96 | 0.34896 | Manual |  |  | 1 | NOT_READY | 348.96 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 313 | 86/1 |  |  | 372 | 0.372 | TSE |  |  | 3 | NOT_READY | 1032.8600000000001 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 314 | 86/2 |  |  | 335 | 0.335 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 315 | 86A/0 |  |  | 325.86 | 0.32586 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 316 | 86A/1 |  |  | 390 | 0.39 | TSE |  |  | 4 | NOT_READY | 1650.0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 317 | 86A/2 |  |  | 397 | 0.397 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 318 | 86A/3 |  |  | 426 | 0.426 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 319 | 86A/4 |  |  | 437 | 0.437 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 320 | 86A/5 |  |  | 394 | 0.394 | TSE |  |  | 2 | NOT_READY | 804.23 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 321 | 87/0 |  |  | 410.23 | 0.41023 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 322 | 87/1 |  |  | 362.99 | 0.36299 | TSE |  |  | 3 | NOT_READY | 1081.94 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 323 | 87/2 |  |  | 358.01 | 0.35801 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 324 | 88/0 |  |  | 360.94 | 0.36094 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 325 | 88/1 |  |  | 320.87 | 0.32087 | TSE |  |  | 3 | NOT_READY | 1071.87 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 326 | 88/2 |  |  | 353 | 0.353 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 327 | 89/0 |  |  | 398 | 0.398 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 328 | 90/0 |  |  | 324.41 | 0.32441 | Manual |  |  | 1 | NOT_READY | 324.41 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 329 | 90A/0 |  |  | 284.15 | 0.28415 | Manual |  |  | 1 | NOT_READY | 284.15 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 330 | 90A/1 |  |  | 318 | 0.318 | TSE |  |  | 2 | NOT_READY | 637.6700000000001 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 331 | 90B/0 |  |  | 319.67 | 0.31967 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 332 | 91/0 |  |  | 215.08 | 0.21508 | Manual |  |  | 1 | NOT_READY | 215.08 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 333 | 92/0 |  |  | 381.67 | 0.38167 | Manual |  |  | 1 | NOT_READY | 381.67 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 334 | 93/0 |  |  | 255.59 | 0.25559 | Manual |  |  | 1 | NOT_READY | 255.59 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 335 | 93A/0 |  |  | 351.25 | 0.35125 | Manual |  |  | 1 | NOT_READY | 351.25 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 336 | 93B/0 |  |  | 369.96 | 0.36996 | Manual |  |  | 1 | NOT_READY | 369.96 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 337 | 93C/0 |  |  | 260 | 0.26 | Manual |  |  | 1 | NOT_READY | 260.0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 338 | 94/0 |  |  | 166.6 | 0.1666 | Manual |  |  | 1 | NOT_READY | 166.6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 339 | 95/0 |  |  | 486.78 | 0.48678 | Manual |  |  | 1 | NOT_READY | 486.78 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 340 | 95A/0 |  |  | 179 | 0.179 | Manual |  |  | 1 | NOT_READY | 179.0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 341 | 96/0 |  |  | 153.59 | 0.15359 | Manual |  |  | 1 | NOT_READY | 153.59 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 342 | 96/1 |  |  | 367.88 | 0.36788 | Manual |  |  | 1 | NOT_READY | 367.88 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 343 | 96/2 |  |  | 421.45 | 0.42145 | TSE |  |  | 2 | NOT_READY | 814.9300000000001 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 344 | 97/0 |  |  | 393.48 | 0.39348 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 345 | 98/0 |  |  | 292.64 | 0.29264 | Manual |  |  | 1 | NOT_READY | 292.64 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 346 | 99/0 |  |  | 103.1 | 0.1031 | Manual |  |  | 1 | NOT_READY | 103.1 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 347 | 100/0 |  |  | 183.67 | 0.18367 | Manual |  |  | 1 | NOT_READY | 183.67 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 348 | 101/0 |  |  | 115.31 | 0.11531 | Manual |  |  | 1 | NOT_READY | 115.31 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 349 | GANTRY-2 |  |  | 78.28 | 0.07828 | Manual |  |  | 1 | NOT_READY | 78.28 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 350 | 100/0 |  |  |  | 0 | Manual |  |  | 1 | NOT_READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 419 | TA 419 | ta419 |  | filename |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | TA 419 Stretch | 2026-07-29 | 14 | 351 | GANTRY-1 |  |  | 147.68 | 0.14768 |  |  |  |  | UNKNOWN | 147.68 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 3 | [7 empty] | 23/0 |  | UNKNOWN | 3DB2+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 4 | [7 empty] | 23/1 |  | UNKNOWN | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 5 | [7 empty] | 23/2 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 6 | [7 empty] | 23/3 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 7 | [7 empty] | 23/4 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 8 | [7 empty] | 24/0 |  | UNKNOWN | 3DB1+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 9 | [7 empty] | 24/3 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 10 | [7 empty] | 24/5 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 11 | [7 empty] | 24/6 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 12 | [7 empty] | 24/7 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 13 | [7 empty] | 24/8 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 14 | [7 empty] | 25/0 |  | UNKNOWN | 3DB2+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 15 | [7 empty] | 25/1 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 16 | [7 empty] | 25/2 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 17 | [7 empty] | 25/4 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 18 | [7 empty] | 26/0 |  | UNKNOWN | 3DB2+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 19 | [7 empty] | 26/1 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 20 | [7 empty] | 26/2 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 21 | [7 empty] | 26/3 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 22 | [7 empty] | 26/4 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 23 | [7 empty] | 27/0 |  | UNKNOWN | 3DB1+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 24 | [7 empty] | 27/1 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 25 | [7 empty] | 27/2 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 26 | [7 empty] | 27/4 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 27 | [7 empty] | 27/5 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 28 | [7 empty] | 27/6 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 29 | [7 empty] | 27/7 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 30 | [7 empty] | 22/5 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 31 | [7 empty] | 27/8 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 32 | [7 empty] | 24/2 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 33 | [7 empty] | 24/4 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 34 | [7 empty] | 24/1 |  | UNKNOWN | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 35 | [7 empty] | 21/9 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 36 | [7 empty] | 22/0 |  | UNKNOWN | 3DB1+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 37 | [7 empty] | 22/1 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 38 | [7 empty] | 22/3 |  | UNKNOWN | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 39 | [7 empty] | 22/4 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 40 | [7 empty] | 22/2 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 41 | [7 empty] | 21/8 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 42 | [7 empty] | 21/7 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 43 | [7 empty] | 25/3 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 44 | [7 empty] | 29/1 |  | UNKNOWN | 3DA+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 45 | [7 empty] | 25/5 |  | UNKNOWN | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 46 | [7 empty] | 29/4 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 47 | [7 empty] | 29/2 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 48 | [7 empty] | 29/3 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 49 | [7 empty] | 29/5 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 50 | [7 empty] | 29/6 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 51 | [7 empty] | 29/7 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 52 | [7 empty] | 29/8 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 53 | [7 empty] | 30/1 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 54 | [7 empty] | 30/3 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 55 | [7 empty] | 30/4 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 56 | [7 empty] | 30/5 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 57 | [7 empty] | 29/0 |  | UNKNOWN | 3DC1+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 58 | [7 empty] | 31/1 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 59 | [7 empty] | 31/2 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 60 | [7 empty] | 31/4 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 61 | [7 empty] | 32/1 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 62 | [7 empty] | 32/3 |  | PARTIAL | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 63 | [7 empty] | 31/6 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 64 | [7 empty] | 31/5 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 65 | [7 empty] | 32/2 |  | PARTIAL | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 66 | [7 empty] | 32/0 |  | UNKNOWN | 3DC1+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 67 | [7 empty] | 33/0 |  | UNKNOWN | 3DD45+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 68 | [7 empty] | 31/3 |  | UNKNOWN | 3DA-3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 69 | [7 empty] | 31/0 |  | UNKNOWN | 3DB2+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 70 | [7 empty] | 29/9 |  | UNKNOWN | 3DB1+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 71 | [7 empty] | 30/0 |  | UNKNOWN | 3DC1+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 72 | [7 empty] | 30/2 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 73 | [7 empty] | 21/1 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 74 | [7 empty] | 21/2 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 75 | [7 empty] | 21/3 |  | UNKNOWN | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 76 | [7 empty] | 21/4 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 77 | [7 empty] | 21/5 |  | UNKNOWN | 3DA-3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 78 | [7 empty] | 21/6 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 79 | [7 empty] | 19/3 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 80 | [7 empty] | 19/1 |  | UNKNOWN | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 81 | [7 empty] | 19/2 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 82 | [7 empty] | 20A/0 |  | UNKNOWN | 3DB2+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 83 | [7 empty] | 20/0 |  | UNKNOWN | 3DB1+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 84 | [7 empty] | 13/10 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 85 | [7 empty] | 21/0 |  | UNKNOWN | 3DD45+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 86 | [7 empty] | 12/1 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 87 | [7 empty] | 12/2 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 88 | [7 empty] | 12/3 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 89 | [7 empty] | 12/4 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 90 | [7 empty] | 12/5 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 91 | [7 empty] | 12/6 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 92 | [7 empty] | 12/7 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 93 | [7 empty] | 12/8 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 94 | [7 empty] | 12/9 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 95 | [7 empty] | 12/10 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 96 | [7 empty] | 12/11 |  | UNKNOWN | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 97 | [7 empty] | 17/3 |  | UNKNOWN | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 98 | [7 empty] | 18/0 |  | UNKNOWN | 3DB2+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 99 | [7 empty] | 18/1 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 100 | [7 empty] | 18/2 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 101 | [7 empty] | 18/3 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 102 | [7 empty] | 12/0 |  | UNKNOWN | 3DB2+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 103 | [7 empty] | 13/0 |  | UNKNOWN | 3DB1+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 104 | [7 empty] | 10/5 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 105 | [7 empty] | 10/9 |  | UNKNOWN | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 106 | [7 empty] | 10/7 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 107 | [7 empty] | 10/8 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 108 | [7 empty] | 10/1 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 109 | [7 empty] | 10/3 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 110 | [7 empty] | 10/4 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 111 | [7 empty] | 11/0 |  | UNKNOWN | 3DC1+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 112 | [7 empty] | 19/0 |  | UNKNOWN | 3DD45+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 113 | [7 empty] | 10/2 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 114 | [7 empty] | 10/0 |  | UNKNOWN | 3DB2+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 115 | [7 empty] | 9/1 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 116 | [7 empty] | 9/2 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 117 | [7 empty] | 9/3 |  | UNKNOWN | 2DA+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 118 | [7 empty] | 9/4 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 119 | [7 empty] | 9/5 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 120 | [7 empty] | 9/6 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 121 | [7 empty] | 9/7 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 122 | [7 empty] | 9/8 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 123 | [7 empty] | 9/9 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 124 | [7 empty] | 9/10 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 125 | [7 empty] | 9/0 |  | UNKNOWN | 2DB1+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 126 | [7 empty] | 11/5 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 127 | [7 empty] | 11/6 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 128 | [7 empty] | 11/2 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 129 | [7 empty] | 11/7 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 130 | [7 empty] | 17/1 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 131 | [7 empty] | 16/2 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 132 | [7 empty] | 16/1 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 133 | [7 empty] | 16/4 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 134 | [7 empty] | 16/6 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 135 | [7 empty] | 16/10 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 136 | [7 empty] | 16/11 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 137 | [7 empty] | 16/8 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 138 | [7 empty] | 16/7 |  | UNKNOWN | 3DA-3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 139 | [7 empty] | 16/3 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 140 | [7 empty] | 16/5 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 141 | [7 empty] | 17/0 |  | UNKNOWN | 3DC1+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 142 | [7 empty] | 13/8 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 143 | [7 empty] | 13/9 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 144 | [7 empty] | 28/1 |  | UNKNOWN | 3DA+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 145 | [7 empty] | 27/3 |  | UNKNOWN | 3DCT+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 146 | [7 empty] | 27/9 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 147 | [7 empty] | 38/1 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 148 | [7 empty] | 38/0 |  | UNKNOWN | 3DC1+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 149 | [7 empty] | 38/2 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 150 | [7 empty] | 38/3 |  | PARTIAL | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 151 | [7 empty] | 38/4 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 152 | [7 empty] | 38/5 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 153 | [7 empty] | 38/6 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 154 | [7 empty] | 38/7 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 155 | [7 empty] | 28/0 |  | UNKNOWN | 3DC1+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 156 | [7 empty] | 37/1 |  | PARTIAL | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 157 | [7 empty] | 37/2 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 158 | [7 empty] | 37/3 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 159 | [7 empty] | 37/4 |  | PARTIAL | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 160 | [7 empty] | 37/5 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 161 | [7 empty] | 37/6 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 162 | [7 empty] | 4/8 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 163 | [7 empty] | 4/7 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 164 | [7 empty] | 4/23 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 165 | [7 empty] | 4/6 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 166 | [7 empty] | 37/0 |  | UNKNOWN | 3DB2+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 167 | [7 empty] | 39/0 |  | UNKNOWN | 3DC1+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 168 | [7 empty] | 39/1 |  | PARTIAL | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 169 | [7 empty] | 8/0 |  | UNKNOWN | 2DD60+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 170 | [7 empty] | 8/2 |  | UNKNOWN | 2DB1+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 171 | [7 empty] | 4/18 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 172 | [7 empty] | 4/21 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 173 | [7 empty] | 4/22 |  | UNKNOWN | 2DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 174 | [7 empty] | 4/5 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 175 | [7 empty] | 4/4 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 176 | [7 empty] | 4/3 |  | UNKNOWN | 2DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 177 | [7 empty] | 4/2 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 178 | [7 empty] | 2/0 |  | UNKNOWN | 2DB2+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 179 | [7 empty] | 1C/0 |  | UNKNOWN | 2DB1+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 180 | [7 empty] | 4/12 |  | UNKNOWN | 2DB1+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 181 | [7 empty] | 8/5 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 182 | [7 empty] | 8/6 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 183 | [7 empty] | 8/8 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 184 | [7 empty] | 8/10 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 185 | [7 empty] | 2/1 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 186 | [7 empty] | 2/2 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 187 | [7 empty] | 2/4 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 188 | [7 empty] | 10/6 |  | UNKNOWN | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 189 | [7 empty] | 1A/0 |  | UNKNOWN | 2DD45+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 190 | [7 empty] | 1B/0 |  | UNKNOWN | 2DB2+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 191 | [7 empty] | 1B/1 |  | UNKNOWN | 2DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 192 | [7 empty] | 1B/2 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 193 | [7 empty] | 1B/3 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 194 | [7 empty] | 2/3 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 195 | [7 empty] | 2/5 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 196 | [7 empty] | 3/0 |  | UNKNOWN | 2DB2+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 197 | [7 empty] | 3/3 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 198 | [7 empty] | 3/1 |  | UNKNOWN | 2DA+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 199 | [7 empty] | 4/1 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 200 | [7 empty] | 4/0 |  | UNKNOWN | 2DB2+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 201 | [7 empty] | 4/9 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 202 | [7 empty] | 4/10 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 203 | [7 empty] | 4/11 |  | UNKNOWN | 2DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 204 | [7 empty] | 4/17 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 205 | [7 empty] | 4/20 |  | UNKNOWN | 2DA+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 206 | [7 empty] | 5/0 |  | UNKNOWN | 2DD45+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 207 | [7 empty] | 6/0 |  | UNKNOWN | 2DD45+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 208 | [7 empty] | 4/15 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 209 | [7 empty] | 4/16 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 210 | [7 empty] | 6/1 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 211 | [7 empty] | 6/2 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 212 | [7 empty] | 6/3 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 213 | [7 empty] | 6/4 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 214 | [7 empty] | 6/5 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 215 | [7 empty] | 6/6 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 216 | [7 empty] | 8/1 |  | UNKNOWN | 2DB1+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 217 | [7 empty] | 8/3 |  | UNKNOWN | 2DB1+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 218 | [7 empty] | 8/4 |  | UNKNOWN | 2DB1+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 219 | [7 empty] | 8/11 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 220 | [7 empty] | 8/13 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 221 | [7 empty] | 8/14 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 222 | [7 empty] | 8/15 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 223 | [7 empty] | 11/3 |  | UNKNOWN | 3DA-3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 224 | [7 empty] | 11/4 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 225 | [7 empty] | 11/10 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 226 | [7 empty] | 11/11 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 227 | [7 empty] | 13/2 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 228 | [7 empty] | 13/3 |  | UNKNOWN | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 229 | [7 empty] | 13/5 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 230 | [7 empty] | 13/6 |  | UNKNOWN | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 231 | [7 empty] | 8/12 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 232 | [7 empty] | 11/1 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 233 | [7 empty] | 11/8 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 234 | [7 empty] | 39/2 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 235 | [7 empty] | 39/3 |  | PARTIAL | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 236 | [7 empty] | 39/4 |  | PARTIAL | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 237 | [7 empty] | 39/5 |  | PARTIAL | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 238 | [7 empty] | 39/6 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 239 | [7 empty] | 39/7 |  | PARTIAL | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 240 | [7 empty] | 39/8 |  | PARTIAL | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 241 | [7 empty] | 15/0 |  | UNKNOWN | 3DD45+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 242 | [7 empty] | 15/1 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 243 | [7 empty] | 15/2 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 244 | [7 empty] | 15/3 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 245 | [7 empty] | 15/4 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 246 | [7 empty] | 16/0 |  | UNKNOWN | 3DD45+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 247 | [7 empty] | 13/11 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 248 | [7 empty] | 14/0 |  | UNKNOWN | 3DC2+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 249 | [7 empty] | 13/7 |  | UNKNOWN | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 250 | [7 empty] | 6/7 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 251 | [7 empty] | 39/9 |  | PARTIAL | 3DA+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 252 | [7 empty] | 40/0 |  | UNKNOWN | 3DB2+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 253 | [7 empty] | 35/0 |  | UNKNOWN | 3DB1+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 254 | [7 empty] | 36/0 |  | UNKNOWN | 3DD60+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 255 | [7 empty] | 35/3 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 256 | [7 empty] | 35/4 |  | PARTIAL | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 257 | [7 empty] | 36/1 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 258 | [7 empty] | 36/2 |  | PARTIAL | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 259 | [7 empty] | 36/3 |  | PARTIAL | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 260 | [7 empty] | 36/4 |  | PARTIAL | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 261 | [7 empty] | 4/19 |  | UNKNOWN | 2DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 262 | [7 empty] | 4/14 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 263 | [7 empty] | 1/0 |  | UNKNOWN | 2DD60+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 264 | [7 empty] | 36/5 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 265 | [7 empty] | 36/7 |  | PARTIAL | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 266 | [7 empty] | 36/8 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 267 | [7 empty] | 8/9 |  | UNKNOWN | 2DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 268 | [7 empty] | 16/9 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 269 | [7 empty] | 17/2 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 270 | [7 empty] | 4/13 |  | UNKNOWN | 2DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 271 | [7 empty] | 7/0 |  | UNKNOWN | 2DD45+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 272 | [7 empty] | 11/9 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 273 | [7 empty] | 13/1 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 274 | [7 empty] | 35/1 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 275 | [7 empty] | 42/6 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 276 | [7 empty] | 13/4 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 277 | [7 empty] | 33/1 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 278 | [7 empty] | 43/2 |  | PARTIAL | 3DA-3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 279 | [7 empty] | 43/3 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 280 | [7 empty] | 43/4 |  | PARTIAL | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 281 | [7 empty] | 43A/0 |  | UNKNOWN | 3DD45+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 282 | [7 empty] | 43A/2 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 283 | [7 empty] | 33/2 |  | PARTIAL | 3DA-3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 284 | [7 empty] | 43/1 |  | PARTIAL | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 285 | [7 empty] | 42/0 |  | UNKNOWN | 3DB1+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 286 | [7 empty] | 43/0 |  | UNKNOWN | 3DB2+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 287 | [7 empty] | 43A/4 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 288 | [7 empty] | 43A/5 |  | UNKNOWN | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 289 | [7 empty] | 44/0 |  | UNKNOWN | 3DD45+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 290 | [7 empty] | 40/1 |  | PARTIAL | 3DA+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 291 | [7 empty] | 41/0 |  | UNKNOWN | 3DC1+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 292 | [7 empty] | 41/1 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 293 | [7 empty] | 42/8 |  | PARTIAL | 3DA+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 294 | [7 empty] | 42/9 |  | PARTIAL | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 295 | [7 empty] | 42/1 |  | PARTIAL | 3DA+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 296 | [7 empty] | 42/2 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 297 | [7 empty] | 42/3 |  | PARTIAL | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 298 | [7 empty] | 42/7 |  | PARTIAL | 3DA+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 299 | [7 empty] | 43/5 |  | PARTIAL | 3DA+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 300 | [7 empty] | 43A/1 |  | UNKNOWN | 3DB1+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 301 | [7 empty] | 43A/3 |  | UNKNOWN | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 302 | [7 empty] | 43B/0 |  | UNKNOWN | 3DB1+9 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 303 | [7 empty] | 34/0 |  | UNKNOWN | 3DC1+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 304 | [7 empty] | 34/1 |  | PARTIAL | 3DB1+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 305 | [7 empty] | 34/2 |  | PARTIAL | 3DB1+6 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 306 | [7 empty] | 35/2 |  | PARTIAL | 3DA+0 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 421 | TA 421 | ta421 |  | filename |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | TA 421 Tack Welding Stretch | 2026-07-11 | 2 | 307 | [7 empty] | 36/6 |  | PARTIAL | 3DA+3 | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 504 | TA 504 | ta504 |  | filename |  | TA 504 - DPR - 2026-07-27.xlsx | Stringing Compiled | Stringing | TA 504 Stretch | 2026-07-27 | 2 | 3 | Bhinder | 11/0 | 12/0 | 11/1, 11/2, 11/3, 11/4, 11/5, 11/6, 12/0 |  | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 504 | TA 504 | ta504 |  | filename |  | TA 504 - DPR - 2026-07-27.xlsx | Stringing Compiled | Stringing | TA 504 Stretch | 2026-07-27 | 2 | 4 | Bhinder | 12/0 | 13/0 | 12/1, 12/2, 12/3, 12/4, 12/5, 13/0 |  | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 504 | TA 504 | ta504 |  | filename |  | TA 504 - DPR - 2026-07-27.xlsx | Stringing Compiled | Stringing | TA 504 Stretch | 2026-07-27 | 2 | 5 | Bhinder | 15/0 | 16/0 | 15/1, 15/2, 15/3, 15/4, 15/5, 15/6, 15/7, 16/0 |  | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 504 | TA 504 | ta504 |  | filename |  | TA 504 - DPR - 2026-07-27.xlsx | Stringing Compiled | Stringing | TA 504 Stretch | 2026-07-27 | 2 | 6 | Bhinder | 16/0 | 16/3 | 16/1, 16/2, 16/3 |  | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 504 | TA 504 | ta504 |  | filename |  | TA 504 - DPR - 2026-07-27.xlsx | Stringing Compiled | Stringing | TA 504 Stretch | 2026-07-27 | 2 | 7 | Bhinder | 16/3 | 17/0 | 16/4, 16/5, 16/6, 17/0 |  | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 504 | TA 504 | ta504 |  | filename |  | TA 504 - DPR - 2026-07-27.xlsx | Stringing Compiled | Stringing | TA 504 Stretch | 2026-07-27 | 2 | 8 | Bhinder | 17/0 | 17/4 | 17/1, 17/2, 17/3, 17/4 |  | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 504 | TA 504 | ta504 |  | filename |  | TA 504 - DPR - 2026-07-27.xlsx | Stringing Compiled | Stringing | TA 504 Stretch | 2026-07-27 | 2 | 9 | Bhinder | 17/4 | 18/0 | 17/5, 17/6, 17/7, 17/8, 17/9, 18/0 |  | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 504 | TA 504 | ta504 |  | filename |  | TA 504 - DPR - 2026-07-27.xlsx | Stringing Compiled | Stringing | TA 504 Stretch | 2026-07-27 | 2 | 10 | Bhinder | 18/0 | 18/1 | 18/1, |  | Manual |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 504 | TA 504 | ta504 |  | filename |  | TA 504 - DPR - 2026-07-27.xlsx | Stringing Compiled | Stringing | TA 504 Stretch | 2026-07-27 | 2 | 11 | Bhinder | 18/1 | 19/0 | 18/2, 18/3, 18/4, 18/5, 18/6, 18/7, 18/8,19/0, |  | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 504 | TA 504 | ta504 |  | filename |  | TA 504 - DPR - 2026-07-27.xlsx | Stringing Compiled | Stringing | TA 504 Stretch | 2026-07-27 | 2 | 12 | Bhinder | 19/0 | 20/0 | 19/1, 19/2, 19/3, 20/0 |  | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 504 | TA 504 | ta504 |  | filename |  | TA 504 - DPR - 2026-07-27.xlsx | Stringing Compiled | Stringing | TA 504 Stretch | 2026-07-27 | 2 | 13 | Bhinder | 20/0 | 21/0 | 21/0 |  | Manual |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 5 | 100/0 To 101/0 | 100/0 | 101/0 | 419 | 0.419 | Manual |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 6 | 101/0 To 102/0 | 101/0 | 102/0 | 3470 | 3.47 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 7 | 102/0 To 103/0 | 102/0 | 103/0 | 461 | 0.461 | Manual |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 8 | 103/0 To 103/5A | 103/0 | 103/5A | 2200 | 2.2 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 9 | 103/5A To 103/6A | 103/5A | 103/6A | 567 | 0.567 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 10 | 103/6A To 104/0 | 103/6A | 104/0 | 1403 | 1.403 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 11 | 104/0 To 105/0 | 104/0 | 105/0 | 967 | 0.967 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 12 | 111/0 To 112/0 | 111/0 | 112/0 | 1954 | 1.954 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 13 | 113/0 To 114/0 | 113/0 | 114/0 | 2565 | 2.565 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 14 | 114/0 To 115/0 | 114/0 | 115/0 | 4304 | 4.304 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 15 | 110A/0 To 111/0 | 110A/0 | 111/0 | 1230 | 1.23 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 16 | 110/0 To 110A/0 | 110/0 | 110A/0 | 3512 | 3.512 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 17 | 112/0 To 113/0 | 112/0 | 113/0 | 226 | 0.226 | Hot Line |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 18 | 126/0 To 127/0 | 126/0 | 127/0 | 1957 | 1.957 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 19 | 127/0 To 128/0 | 127/0 | 128/0 | 1441 | 1.441 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 20 | 108/0 To 109/0 | 108/0 | 109/0 | 1668 | 1.668 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 21 | 109/0 To 110/0 | 109/0 | 110/0 | 1949 | 1.949 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 22 | 115/0 To 116/0 | 115/0 | 116/0 | 200 | 0.2 | Hot Line |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 23 | 105/0 To 106/0 | 105/0 | 106/0 | 755 | 0.755 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 24 | 106/0 To 108/0 | 106/0 | 108/0 | 212 | 0.212 | Manual |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 25 | 117/0 To 118/0 | 117/0 | 118/0 | 240 | 0.24 | Hot Line |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 26 | 147/0 To 147A/0 | 147/0 | 147A/0 | [6 empty] | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 27 | 147A/0 To148/0 | 147A/0 | 148/0 | [6 empty] | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 28 | 175/0 To 176/0 | 175/0 | 176/0 | 1675 | 1.675 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 29 | 176/0 To 177/0 | 176/0 | 177/0 | 1564 | 1.564 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 30 | 177/0 To 178/0 | 177/0 | 178/0 | 3272 | 3.272 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 31 | 116/0 To 117/0 | 116/0 | 117/0 | 1147 | 1.147 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 32 | 120/0 To 121/0 | 120/0 | 121/0 | 1593 | 1.593 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 33 | 119/0 To 120/0 | 119/0 | 120/0 | 193 | 0.193 | Hot Line |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 34 | 118/0 To 119/0 | 118/0 | 119/0 | 421 | 0.421 | Manual |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 35 | 99/0 - 100/0 | 99/0 | 100/0 | 3478 | 3.478 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 36 | 125/0 To126/0 | 125/0 | 126/0 | 742.55 | 0.74255 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 505 | TA 505 | ta505 |  | filename |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | TA 505 Stretch | 2026-07-22 | 4 | 37 | 155/0 To 156/0 | 155/0 | 156/0 | 2306.85 | 2.3068 | TSE |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 3 | Sirohi | 1/0 | 2/0 | 4424.083 | 4.4241 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 4 | Sirohi | 5/0 | 6/0 | 4949.33 | 4.9493 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 5 | Sirohi | 48/0 | 50/0 | 688.47 | 0.68847 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 6 | Sirohi | 50/0 | 51/0 | 1160.08 | 1.1601 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 7 | Sirohi | 2/0 | 2A/0 | 3318.603 | 3.3186 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 8 | Sirohi | 51/0 | 51A/0 | 1244.855 | 1.2449 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 9 | Sirohi | 51A/0 | 51C/0 | 1234.81 | 1.2348 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 10 | Sirohi | 51C/0 | 52/0 | 1968.185 | 1.9682 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 11 | Sirohi | 52/0 | 53/0 | 992.08 | 0.99208 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 12 | Sirohi | 4/0 | 5/0 | 2809.04 | 2.809 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 13 | Sirohi | 18/0 | 19/0 | 3934.01 | 3.934 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 14 | Sirohi | 68/0 | 68/1 | 504 | 0.504 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 15 | Sirohi | 67/0 | 68/0 | 176.73 | 0.17673 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 16 | Sirohi | 6/0 | 9/0 | 1210.68 | 1.2107 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 17 | Sirohi | 66/0 | 67/0 | 743.77 | 0.74377 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 18 | Sirohi | 10/0 | 11/0 | 1256.34 | 1.2563 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 19 | Sirohi | 11/0 | 11/3 | 1114 | 1.114 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 20 | Sirohi | 11/3 | 12/0 | 530.153 | 0.53015 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 21 | Sirohi | 65A/3 | 66/0 | 244.262 | 0.24426 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 22 | Udaipur | 213/0 | 214/0 | 2351.3 | 2.3513 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 23 | Sirohi | 17/0 | 18/0 | 2732.97 | 2.733 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 24 | Sirohi | 9/0 | 10/0 | 272.18 | 0.27218 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 25 | Gogunda | 139/0 | 139A/0 | 655.83 | 0.65583 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 26 | Gogunda | 139A/0 | 140/0 | 242.66 | 0.24266 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 27 | Udaipur | 212/0 | 213/0 | 2393.12 | 2.3931 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 28 | Sirohi | 12/0 | 13/0 | 3315.27 | 3.3153 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 29 | Sirohi | 65/0 | 65A/0 | 195.07 | 0.19507 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 30 | Sirohi | 65A/0 | 65A/3 | 919 | 0.919 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 31 | Sirohi | 15/0 | 16/0 | 1674.936 | 1.6749 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 32 | Sirohi | 64/0 | 64A/0 | 471.96 | 0.47196 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 33 | Udaipur | 211/0 | 212/0 | 3254.51 | 3.2545 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 34 | Sirohi | 63/0 | 64/0 | 778.97 | 0.77897 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 35 | Sirohi | 13/0 | 14/0 | 2454.45 | 2.4545 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 36 | Sirohi | 64A/0 | 65/0 | 1659.14 | 1.6591 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 37 | Sirohi | 38/0 | 39/0 | 762.52 | 0.76252 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 38 | Sirohi | 37/0 | 38/0 | 2040.002 | 2.04 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 39 | Sirohi | 14/0 | 15/0 | 280 | 0.28 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 40 | Sirohi | 61/0 | 62/0 | 795.22 | 0.79522 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 41 | Gogunda | 140/0 | 141/0 | 1152.71 | 1.1527 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 42 | Sirohi | 16/0 | 17/0 | 204.967 | 0.20497 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 43 | Gogunda | 141/0 | 142/0 | 720.38 | 0.72038 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 44 | Sirohi | 60/0 | 61/0 | 1279.5 | 1.2795 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 45 | Udaipur | 210/0 | 211/0 | 4052.317 | 4.0523 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 46 | Udaipur | 223/0 | 224/0 | 730.94 | 0.73094 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 47 | Gogunda | 138/0 | 139/0 | 777.08 | 0.77708 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 48 | Gogunda | 137/0 | 138/0 | 1056.753 | 1.0568 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 49 | Sirohi | 40/0 | 41/0 | 373.355 | 0.37335 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 50 | Sirohi | 39/0 | 40/0 | 392.674 | 0.39267 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 51 | Udaipur | 200/0 | 201/0 | 1587.001 | 1.587 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 52 | Udaipur | 187A/0 | 188/0 | 840 | 0.84 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 53 | Sirohi | 41/0 | 42/0 | 457.079 | 0.45708 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 54 | Udaipur | 199/0 | 200/0 | 2506.34 | 2.5063 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 55 | Udaipur | 187/0 | 187A/0 | 1204.128 | 1.2041 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 56 | Sirohi | 59/0 | 60/0 | 361.808 | 0.36181 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 506 | TA 506 | ta506 |  | filename |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | TA 506 Stretch | 2026-07-27 | 2 | 57 | Udaipur | 134/0 | 135/0 | 841.878 | 0.84188 | Ready |  |  |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 5 | 20/5 | [5 empty] | 2026-03-23 00:00:00 | 2026-03-23 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 6 | 20/6 | [5 empty] | 2026-03-23 00:00:00 | 2026-03-23 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 7 | 20/7 | [5 empty] | 2026-03-24 00:00:00 | 2026-03-24 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 8 | 20/4 | [5 empty] | 2026-03-24 00:00:00 | 2026-03-24 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 9 | 20/3 | [5 empty] | 2026-03-25 00:00:00 | 2026-03-25 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 10 | 20/2 | [5 empty] | 2026-03-25 00:00:00 | 2026-03-25 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 11 | 20/1 | [5 empty] | 2026-03-26 00:00:00 | 2026-03-26 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 12 | 20/0 | [5 empty] | 2026-03-27 00:00:00 | 2026-03-27 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 13 | 11/1 | [5 empty] | 2026-03-27 00:00:00 | 2026-03-27 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 14 | 11/2 | [5 empty] | 2026-03-28 00:00:00 | 2026-03-28 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 15 | 11/3 | [5 empty] | 2026-03-28 00:00:00 | 2026-03-28 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 16 | 11/4 | [5 empty] | 2026-03-29 00:00:00 | 2026-03-29 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 17 | 11/5 | [5 empty] | 2026-03-29 00:00:00 | 2026-03-29 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 18 | 19/3 | [5 empty] | 2026-03-30 00:00:00 | 2026-03-30 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 19 | 19/5 | [5 empty] | 2026-03-31 00:00:00 | 2026-03-31 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 20 | 18/2 | [5 empty] | 2026-03-31 00:00:00 | 2026-03-31 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 21 | 18/3 | [5 empty] | 2026-04-01 00:00:00 | 2026-04-01 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 22 | 18/4 | [5 empty] | 2026-04-01 00:00:00 | 2026-04-01 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 23 | 18/5 | [5 empty] | 2026-02-04 00:00:00 | 2026-02-04 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 24 | 19/2 | [5 empty] | 2026-02-04 00:00:00 | 2026-02-04 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 25 | 19/6 | [5 empty] | 2026-04-03 00:00:00 | 2026-04-03 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 26 | 19/7 | [5 empty] | 2026-04-04 00:00:00 | 2026-04-04 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 27 | 19/1 | [5 empty] | 2026-04-04 00:00:00 | 2026-04-04 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 28 | 19/4 | [5 empty] | 2026-04-05 00:00:00 | 2026-04-05 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 29 | 28/4 | [5 empty] | 2026-04-06 00:00:00 | 2026-04-06 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 30 | 28/6 | [5 empty] | 2026-04-06 00:00:00 | 2026-04-06 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 31 | 28/7 | [5 empty] | 2026-04-07 00:00:00 | 2026-04-07 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 32 | 29/5 | [5 empty] | 2026-04-08 00:00:00 | 2026-04-08 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 33 | 29/3 | [5 empty] | 2026-04-08 00:00:00 | 2026-04-08 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 34 | 11/6 | [5 empty] | 2026-04-09 00:00:00 | 2026-04-09 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 35 | 29/9 | [5 empty] | 2026-04-09 00:00:00 | 2026-04-09 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 36 | 29/15 | [5 empty] | 2026-04-11 00:00:00 | 2026-04-11 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 37 | 29/20 | [5 empty] | 2026-04-11 00:00:00 | 2026-04-11 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 38 | 7/1 | [5 empty] | 2026-04-13 00:00:00 | 2026-04-13 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 39 | 7/3 | [5 empty] | 2026-04-13 00:00:00 | 2026-04-13 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 40 | 7/4 | [5 empty] | 2026-04-14 00:00:00 | 2026-04-14 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 41 | 2/6 | [5 empty] | 2026-04-16 00:00:00 | 2026-04-16 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 42 | 7/5 | [5 empty] | 2026-04-18 00:00:00 | 2026-04-18 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 43 | 7/6 | [5 empty] | 2026-04-18 00:00:00 | 2026-04-18 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 44 | 7/7 | [5 empty] | 2026-04-19 00:00:00 | 2026-04-19 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 45 | 11/8 | [5 empty] | 2026-04-22 00:00:00 | 2026-04-22 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 46 | 12/2 | [5 empty] | 2026-04-22 00:00:00 | 2026-04-22 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 47 | 5/2 | [5 empty] | 2026-04-23 00:00:00 | 2026-04-23 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 48 | 5/3 | [5 empty] | 2026-04-23 00:00:00 | 2026-04-23 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 49 | 2/3 | [5 empty] | 2026-04-24 00:00:00 | 2026-04-24 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 50 | 5/4 | [5 empty] | 2026-04-25 00:00:00 | 2026-04-25 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 51 | 7/8 | [5 empty] | 2026-04-26 00:00:00 | 2026-04-26 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 52 | 3A/1 | [5 empty] | 2026-04-28 00:00:00 | 2026-04-28 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 53 | 3A/2 | [5 empty] | 2026-04-28 00:00:00 | 2026-04-28 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 54 | 3/6 | [5 empty] | 2026-04-29 00:00:00 | 2026-04-29 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 55 | 3/7 | [5 empty] | 2026-04-29 00:00:00 | 2026-04-29 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 56 | 3/4 | [5 empty] | 2026-04-30 00:00:00 | 2026-04-30 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 57 | 3/5 | [5 empty] | 2026-04-30 00:00:00 | 2026-04-30 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 58 | 3/3 | [5 empty] | 2026-05-02 00:00:00 | 2026-05-02 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 59 | 7/9 | [5 empty] | 2026-05-03 00:00:00 | 2026-05-03 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 60 | 7/10 | [5 empty] | 2026-05-03 00:00:00 | 2026-05-03 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 61 | 7/11 | [5 empty] | 2026-05-05 00:00:00 | 2026-05-05 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 62 | 35/1 | [5 empty] | 2026-05-05 00:00:00 | 2026-05-05 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 63 | 35/3 | [5 empty] | 2026-05-06 00:00:00 | 2026-05-06 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 64 | 35/4 | [5 empty] | 2026-05-06 00:00:00 | 2026-05-06 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 65 | 8/0 | [5 empty] | 2026-05-06 00:00:00 | 2026-05-06 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 66 | 8/1 | [5 empty] | 2026-05-07 00:00:00 | 2026-05-07 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 67 | 35/2 | [5 empty] | 2026-05-07 00:00:00 | 2026-05-07 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 68 | 35/5 | [5 empty] | 2026-05-08 00:00:00 | 2026-05-08 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 69 | 8/2 | [5 empty] | 2026-05-08 00:00:00 | 2026-05-08 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 70 | 29/11 | [5 empty] | 2026-05-09 00:00:00 | 2026-05-09 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 71 | 29/8 | [5 empty] | 2026-05-10 00:00:00 | 2026-05-10 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 72 | 29/10 | [5 empty] | 2026-05-10 00:00:00 | 2026-05-10 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 73 | 29/6 | [5 empty] | 2026-05-11 00:00:00 | 2026-05-11 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 74 | 33/4 | [5 empty] | 2026-05-11 00:00:00 | 2026-05-11 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 75 | 8/3 | [5 empty] | 2026-05-12 00:00:00 | 2026-05-12 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 76 | 29/1 | [5 empty] | 2026-05-12 00:00:00 | 2026-05-12 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 77 | 34/9 | [5 empty] | 2026-05-15 00:00:00 | 2026-05-15 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 78 | 33/3 | [5 empty] | 2026-05-16 00:00:00 | 2026-05-16 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 79 | 36/8 | [5 empty] | 2026-05-19 00:00:00 | 2026-05-19 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 80 | 36/7 | [5 empty] | 2026-05-20 00:00:00 | 2026-05-20 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 81 | 34/10 | [5 empty] | 2026-05-21 00:00:00 | 2026-05-21 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 82 | 36/6 | [5 empty] | 2026-05-22 00:00:00 | 2026-05-22 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 83 | 8/4 | [5 empty] | 2026-05-22 00:00:00 | 2026-05-22 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 84 | 6/8 | [5 empty] | 2026-06-04 00:00:00 | 2026-06-04 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 85 | 6/7 | [5 empty] | 2026-06-05 00:00:00 | 2026-06-05 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 86 | 6/9 | [5 empty] | 2026-06-05 00:00:00 | 2026-06-05 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 87 | 6/6 | [5 empty] | 2026-06-06 00:00:00 | 2026-06-06 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 88 | 7/0 | [5 empty] | 2026-06-07 00:00:00 | 2026-06-07 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 89 | 6/5 | [5 empty] | 2026-08-06 00:00:00 | 2026-08-06 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 90 | 6/4 | [5 empty] | 2026-08-06 00:00:00 | 2026-08-06 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 91 | 5/5 | [5 empty] | 2026-09-06 00:00:00 | 2026-09-06 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 92 | 5/6 | [5 empty] | 2026-09-06 00:00:00 | 2026-09-06 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 93 | 8/8 | [5 empty] | 2026-10-06 00:00:00 | 2026-10-06 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 94 | 8/6 | [5 empty] | 2026-10-06 00:00:00 | 2026-10-06 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 95 | 8/5 | [5 empty] | 2026-11-06 00:00:00 | 2026-11-06 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 96 | 6/10 | [5 empty] | 2026-11-06 00:00:00 | 2026-11-06 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 97 | 6/3 | [5 empty] | 2026-12-06 00:00:00 | 2026-12-06 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 98 | 23/3 | [5 empty] | 15/6/2026 | 15/6/2026 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 99 | 23/2 | [5 empty] | 16/6/2026 | 16/6/2026 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 100 | 6/2 | [5 empty] | 16/6/2026 | 16/6/2026 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 101 | 6/1 | [5 empty] | 17/6/2026 | 17/6/2026 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 102 | 5/8 | [5 empty] | 17/6/2026 | 17/6/2026 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 103 | 23/1 | [5 empty] | 18/6/2026 | 18/6/2026 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 104 | 28/1 | [5 empty] | 19/6/2026 | 19/6/2026 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 105 | 5/7 | [5 empty] | 2026-06-21 00:00:00 | 2026-06-21 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 106 | 41/1 | [5 empty] | 2026-06-21 00:00:00 | 2026-06-21 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 107 | 41/2 | [5 empty] | 2026-06-22 00:00:00 | 2026-06-22 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 108 | 41/4 | [5 empty] | 2026-06-22 00:00:00 | 2026-06-22 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 109 | 6/0 | [5 empty] | 2026-06-22 00:00:00 | 2026-06-22 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 110 | 41/5 | [5 empty] | 2026-06-23 00:00:00 | 2026-06-23 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 111 | 5/10 | [5 empty] | 2026-06-23 00:00:00 | 2026-06-23 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 112 | 28/0 | [5 empty] | 2026-06-27 00:00:00 | 2026-06-27 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 113 | 28/3 | [5 empty] | 2026-06-28 00:00:00 | 2026-06-28 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 114 | 5/11 | [5 empty] | 2026-06-30 00:00:00 | 2026-06-30 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 115 | 5/9 | [5 empty] | 2026-06-30 00:00:00 | 2026-06-30 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 116 | 8/7 | [5 empty] | 2026-07-02 00:00:00 | 2026-07-02 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 117 | 5/0 | [5 empty] | 2026-07-11 00:00:00 | 2026-07-11 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 118 | 28/2 | [5 empty] | 2026-07-12 00:00:00 | 2026-07-12 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 119 | 4/14 | [5 empty] | 2026-07-12 00:00:00 | 2026-07-12 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 120 | 4/13 | [5 empty] | 2026-07-13 00:00:00 | 2026-07-13 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 121 | 28/5 | [5 empty] | 2026-07-13 00:00:00 | 2026-07-13 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 122 | 4/11 | [5 empty] | 2026-07-14 00:00:00 | 2026-07-14 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 123 | 9/3 | [5 empty] | 2026-07-15 00:00:00 | 2026-07-15 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 124 | 9/4 | [5 empty] | 2026-07-16 00:00:00 | 2026-07-16 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 125 | 9/2 | [5 empty] | 2026-07-17 00:00:00 | 2026-07-17 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 126 | 9/0 | [5 empty] | 2026-07-18 00:00:00 | 2026-07-18 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 127 | 9/1 | [5 empty] | 2026-07-19 00:00:00 | 2026-07-19 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 128 | 4/9 | [5 empty] | 2026-07-20 00:00:00 | 2026-07-20 00:00:00 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 129 | 4/10 | [5 empty] | 21/7/2026 | 21/7/2026 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 130 | 4/7 | [5 empty] | 22/7/2026 | 22/7/2026 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 131 | 5/1 | [5 empty] | 23/07/2026 | 23/07/2026 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 512 | TA 512 | ta512 |  | filename |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | TA 512 Stretch | 2026-07-28 | 4 | 132 | 4/6 | [5 empty] | 25/07/2026 | 25/07/2026 |  | READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 4 | AP48 |  | AP49 | 3.3066 | 3.3066 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 5 | AP49 |  | AP50 | 4.5818 | 4.5818 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 6 | AP50 |  | AP51 | 1.519 | 1.519 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 7 | AP51 |  | AP52 | 4.3004 | 4.3004 | Y |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 8 | AP52 |  | AP53 | 1.9959 | 1.9959 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 9 | AP53 |  | AP54 | 2.7717 | 2.7717 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 10 | AP54 |  | AP55 | 0.23844 | 0.23844 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 11 | AP55 |  | AP56 | 1.4365 | 1.4365 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 12 | AP56 |  | AP57 | 5.2326 | 5.2326 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 13 | AP57 |  | AP58 | 0.21474 | 0.21474 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 14 | AP58 |  | AP59 | 1.5881 | 1.5881 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 15 | AP59 |  | AP60 | 2.3158 | 2.3158 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 16 | AP60 |  | AP61 | 3.8451 | 3.8451 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 17 | AP61 |  | AP62 | 0.24749 | 0.24749 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 18 | AP62 |  | AP63 | 1.82 | 1.82 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 19 | AP63 |  | AP64 | 1.6119 | 1.6119 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 20 | AP64 |  | AP65 | 0.43905 | 0.43905 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 21 | AP65 |  | AP66 | 1.3995 | 1.3995 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 22 | AP66 |  | AP67 | 0.88682 | 0.88682 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 23 | AP67 |  | AP68 | 1.8412 | 1.8412 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 24 | AP68 |  | AP69 | 1.1609 | 1.1609 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 25 | AP69 |  | AP70 | 1.2616 | 1.2616 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 26 | AP70 |  | AP71 | 1.967 | 1.967 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 27 | AP71 |  | AP72 | 0.24852 | 0.24852 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 28 | AP72 |  | AP73 | 0.82768 | 0.82768 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 29 | AP73 |  | AP74 | 1.2134 | 1.2134 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 30 | AP74 |  | AP75 | 0.25012 | 0.25012 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 31 | AP75 |  | AP76 | 1.6107 | 1.6107 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 32 | AP76 |  | AP77 | 0.19645 | 0.19645 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 33 | AP77 |  | AP78 | 4.2606 | 4.2606 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 34 | AP78 |  | AP79 | 1.5551 | 1.5551 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 35 | AP79 |  | AP80 | 1.5776 | 1.5776 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 36 | AP80 |  | AP81 | 2.4962 | 2.4962 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 37 | AP81 |  | AP82 | 1.6443 | 1.6443 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 38 | AP82 |  | AP83 | 1.2808 | 1.2808 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 39 | AP83 |  | AP84 | 1.1533 | 1.1533 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 40 | AP84 |  | AP85 | 2.7389 | 2.7389 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 41 | AP85 |  | AP86 | 1.8152 | 1.8152 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 42 | AP86 |  | AP87 | 0.75885 | 0.75885 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 43 | AP87 |  | AP88 | 0.46849 | 0.46849 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 44 | AP88 |  | AP89 | 0.292 | 0.292 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 45 | AP89 |  | AP90 | 0.7625 | 0.7625 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 46 | AP90 |  | AP91 | 2.4599 | 2.4599 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 47 | AP91 |  | AP92 | 1.1419 | 1.1419 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 48 | AP92 |  | AP93 | 1.2207 | 1.2207 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 49 | AP93 |  | AP94 | 1.7272 | 1.7272 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 50 | AP94 |  | AP95 | 1.7948 | 1.7948 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 51 | AP95 |  | AP96 | 0.26547 | 0.26547 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 52 | AP96 |  | AP97 | 3.6581 | 3.6581 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 53 | AP97 |  | AP98 | 1.9377 | 1.9377 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 54 | AP98 |  | AP99 | 2.328 | 2.328 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 55 | AP99 |  | AP100 | 4.9858 | 4.9858 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 56 | AP100 |  | AP101 | 3.6492 | 3.6492 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 57 | AP101 |  | AP102 | 3.924 | 3.924 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 58 | AP102 |  | AP103 | 2.7046 | 2.7046 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 59 | AP103 |  | AP104 | 1.5241 | 1.5241 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 60 | AP104 |  | AP105 | 4.6981 | 4.6981 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 61 | AP105 |  | AP106 | 1.5484 | 1.5484 |  |  |  |  | UNKNOWN | Row | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 62 | AP106 |  | AP107 | 0.26332 | 0.26332 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 63 | AP107 |  | AP108 | 0.78081 | 0.78081 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 64 | AP108 |  | AP109 | 1.1265 | 1.1265 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 65 | AP109 |  | AP110 | 0.19463 | 0.19463 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 66 | AP110 |  | AP111 | 0.20314 | 0.20314 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TA 601 | TA 601 | ta601 |  | filename |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | TA 601 Stretch | 2026-07-28 | 3 | 67 | Grand Total |  |  | 113.2692 | 113.2692 |  |  |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 6 | 59/13 | [5 empty] | 2024-02-20 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 7 | 59/14 | [5 empty] | 2024-02-22 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 8 | 62/5 | [5 empty] | 2024-02-27 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 9 | 63/6 | [5 empty] | 2024-02-28 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 10 | 63/8 | [5 empty] | 2024-03-02 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 11 | 62/3 | [5 empty] | 2024-02-03 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 12 | 62/4 | [5 empty] | 2024-03-04 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 13 | 59/12 | [5 empty] | 2024-03-05 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 14 | 59/10 | [5 empty] | 2024-03-06 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 15 | 59/9 | [5 empty] | 2024-03-07 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 16 | 60/7 | [5 empty] | 2024-03-09 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 17 | 62/2 | [5 empty] | 2024-03-10 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 18 | 62/7 | [5 empty] | 2024-03-11 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 19 | 64/1 | [5 empty] | 2024-03-12 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 20 | 59/7 | [5 empty] | 2024-03-12 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 21 | 64/4 | [5 empty] | 2024-03-13 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 22 | 60/11 | [5 empty] | 2024-03-15 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 23 | 62/8 | [5 empty] | 2024-03-15 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 24 | 65/2 | [5 empty] | 2024-03-16 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 25 | 60/6 | [5 empty] | 2024-03-16 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 26 | 65/4 | [5 empty] | 2024-03-17 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 27 | 64/5 | [5 empty] | 2024-03-18 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 28 | 62/9 | [5 empty] | 2024-03-19 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 29 | 60/8 | [5 empty] | 2024-03-19 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 30 | 62/10 | [5 empty] | 2024-03-21 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 31 | 65/3 | [5 empty] | 2024-03-22 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 32 | 59/6 | [5 empty] | 2024-03-22 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 33 | 60/10 | [5 empty] | 2024-03-24 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 34 | 61/6 | [5 empty] | 2024-03-28 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 35 | 65/5 | [5 empty] | 2024-03-29 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 36 | 64/6 | [5 empty] | 2024-04-01 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 37 | 61/7 | [5 empty] | 2024-04-03 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 38 | 65/6 | [5 empty] | 2024-04-04 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 39 | 64/7 | [5 empty] | 2024-04-06 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 40 | 63/7 | [5 empty] | 2024-04-22 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 41 | 64/9 | [5 empty] | 2024-04-24 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 42 | 61/0 | [5 empty] | 2024-04-25 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 43 | 65/9 | [5 empty] | 2024-04-27 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 44 | 65/11 | [5 empty] | 2024-04-28 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 45 | 67/2 | [5 empty] | 2024-04-29 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 46 | 61/2 | [5 empty] | 2024-04-30 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 47 | 64/10 | [5 empty] | 2024-05-05 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 48 | 67/1 | [5 empty] | 2024-05-07 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 49 | 64/8 | [5 empty] | 2024-05-09 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 50 | 65/1 | [5 empty] | 2024-05-10 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 51 | 65/0 | [5 empty] | 2024-05-10 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 52 | 61/1 | [5 empty] | 2024-05-10 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 53 | 60/9 | [5 empty] | 2024-05-11 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 54 | 63/4 | [5 empty] | 2024-05-14 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 55 | 63/3 | [5 empty] | 2024-05-15 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 56 | 63/5 | [5 empty] | 2024-05-16 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 57 | 61/3 | [5 empty] | 2024-05-17 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 58 | 62/11 | [5 empty] | 2024-05-19 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 59 | 61/4 | [5 empty] | 2024-05-23 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 60 | 61/5 | [5 empty] | 2024-05-25 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 61 | 64/2 | [5 empty] | 2024-06-03 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 62 | 64/3 | [5 empty] | 2024-06-06 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 63 | 64/0 | [5 empty] | 2024-06-06 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 64 | 61/10 | [5 empty] | 2024-06-07 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 65 | 61/8 | [5 empty] | 2024-06-08 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 66 | 63/2 | [5 empty] | 2024-06-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 67 | 61/9 | [5 empty] | 2024-06-09 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 68 | 63/1 | [5 empty] | 2024-06-09 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 69 | 59/5 | [5 empty] | 2024-06-10 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 70 | 63/0 | [5 empty] | 2024-06-11 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 71 | 60/5 | [5 empty] | 2024-06-11 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 72 | 60/4 | [5 empty] | 2024-06-13 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 73 | 60/3 | [5 empty] | 2024-06-23 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 74 | 60/2 | [5 empty] | 2024-06-25 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 75 | 60/1 | [5 empty] | 2024-06-30 00:00:00 | Done |  | READY | Ramagora | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 76 | 59/16 | [5 empty] | 2024-07-01 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 77 | 59/15 | [5 empty] | 2024-07-02 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 78 | 60/0 | [5 empty] | 2024-07-24 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 79 | 59/8 | [5 empty] | 2024-07-27 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 80 | 55/3 | [5 empty] | 2024-08-23 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 81 | 55/4 | [5 empty] | 2024-08-24 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 82 | 57/6 | [5 empty] | 2024-08-27 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 83 | 57/3 | [5 empty] | 2024-08-28 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 84 | 57/4 | [5 empty] | 2024-08-30 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 85 | 57/5 | [5 empty] | 2024-08-30 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 86 | 62/0 | [5 empty] | 2024-09-15 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 87 | 62/1 | [5 empty] | 2024-09-24 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 88 | 62/6 | [5 empty] | 2024-09-26 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 89 | 57/7 | [5 empty] | 2024-10-06 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 90 | 50/9 | [5 empty] | 2024-10-07 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 91 | 50/10 | [5 empty] | 2024-10-09 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 92 | 50/0 | [5 empty] | 2024-10-10 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 93 | 50/3 | [5 empty] | 2024-10-24 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 94 | 50/1 | [5 empty] | 2024-10-25 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 95 | 51/1 | [5 empty] | 2024-10-25 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 96 | 16/3 | [5 empty] | 2024-10-26 00:00:00 | Done |  | READY | R&A | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 97 | 50/2 | [5 empty] | 2024-10-28 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 98 | 64/11 | [5 empty] | 2024-10-29 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 99 | 15/1 | [5 empty] | 2024-10-29 00:00:00 | Done |  | READY | SB Enterprises | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 100 | 16/4 | [5 empty] | 2024-11-10 00:00:00 | Done |  | READY | SB Enterprises | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 101 | 59/11 | [5 empty] | 2024-11-11 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 102 | 18/1 | [5 empty] | 2024-11-12 00:00:00 | Done |  | READY | SB Enterprises | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 103 | 50/7 | [5 empty] | 2024-11-14 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 104 | 73/1 | [5 empty] | 2024-11-14 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 105 | 73/2 | [5 empty] | 2024-11-19 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 106 | 73/9 | [5 empty] | 2024-11-20 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 107 | 52/7 | [5 empty] | 2024-11-25 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 108 | 52/6 | [5 empty] | 2024-11-25 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 109 | 52/8 | [5 empty] | 2024-11-26 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 110 | 48/0 | [5 empty] | 2024-11-27 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 111 | 49/4 | [5 empty] | 2024-11-27 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 112 | 48/1 | [5 empty] | 2024-11-29 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 113 | 47/10 | [5 empty] | 2024-11-29 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 114 | 49/7 | [5 empty] | 2024-12-02 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 115 | 49/6 | [5 empty] | 2024-12-03 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 116 | 49/5 | [5 empty] | 2024-12-04 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 117 | 59/3 | [5 empty] | 2024-12-05 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 118 | 59/4 | [5 empty] | 2024-12-06 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 119 | 73/6 | [5 empty] | 2024-12-13 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 120 | 72/3 | [5 empty] | 2024-12-17 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 121 | 59/1 | [5 empty] | 2024-12-18 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 122 | 59/2 | [5 empty] | 2024-12-20 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 123 | 50/8 | [5 empty] | 2024-12-23 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 124 | 73/8 | [5 empty] | 2024-12-25 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 125 | 51/2 | [5 empty] | 2024-12-26 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 126 | 49/2 | [5 empty] | 2024-12-26 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 127 | 49/3 | [5 empty] | 2024-12-26 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 128 | 49/1 | [5 empty] | 2024-12-28 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 129 | 50/4 | [5 empty] | 2025-01-06 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 130 | 59/0 | [5 empty] | 2025-01-07 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 131 | 50/6 | [5 empty] | 2025-01-12 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 132 | 65/7 | [5 empty] | 2025-01-17 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 133 | 65/8 | [5 empty] | 2025-01-18 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 134 | 73/3 | [5 empty] | 2025-01-27 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 135 | 73/4 | [5 empty] | 2025-01-29 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 136 | 73/7 | [5 empty] | 2025-02-13 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 137 | 74/0 | [5 empty] | 2025-02-14 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 138 | 73/5 | [5 empty] | 2025-02-15 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 139 | 65/10 | [5 empty] | 2025-02-17 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 140 | 66/0 | [5 empty] | 2025-02-19 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 141 | 51/0 | [5 empty] | 2025-02-26 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 142 | 50/5 | [5 empty] | 2025-03-02 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 143 | 52/0 | [5 empty] | 2025-03-05 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 144 | 49/0 | [5 empty] | 2025-03-10 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 145 | 52/9 | [5 empty] | 2025-03-11 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 146 | 52/10 | [5 empty] | 2025-03-12 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 147 | 73/0 | [5 empty] | 2025-03-13 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 148 | 52/5 | [5 empty] | 2025-03-17 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 149 | 47/9 | [5 empty] | 2025-04-16 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 150 | 47/8 | [5 empty] | 2025-04-16 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 151 | 58/0 | [5 empty] | 2025-04-21 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 152 | 72/2 | [5 empty] | 2025-04-28 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 153 | 72/1 | [5 empty] | 2025-04-29 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 154 | 71/8 | [5 empty] | 2025-04-30 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 155 | 71/7 | [5 empty] | 2025-04-30 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 156 | 70/5 | [5 empty] | 2025-05-02 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 157 | 71/6 | [5 empty] | 2025-05-02 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 158 | 70/3 | [5 empty] | 2025-05-03 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 159 | 55/5 | [5 empty] | 2025-05-05 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 160 | 55/6 | [5 empty] | 2025-05-06 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 161 | 71/5 | [5 empty] | 2025-05-10 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 162 | 70/4 | [5 empty] | 2025-05-11 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 163 | 71/3 | [5 empty] | 2025-05-16 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 164 | 71/4 | [5 empty] | 2025-05-17 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 165 | 71/2 | [5 empty] | 2025-05-19 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 166 | 71/1 | [5 empty] | 2025-05-20 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 167 | 70/11 | [5 empty] | 2025-05-24 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 168 | 71/0 | [5 empty] | 2025-05-26 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 169 | 70/9 | [5 empty] | 2025-05-27 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 170 | 70/10 | [5 empty] | 2025-05-28 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 171 | 68/0 | [5 empty] | 2025-06-04 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 172 | 67/0 | [5 empty] | 2025-06-10 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 173 | 16/2 | [5 empty] | 2025-06-10 00:00:00 | Done |  | READY | Chanda Enterprises | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 174 | 17/0 | [5 empty] | 2025-06-10 00:00:00 | Done |  | READY | Chanda Enterprises | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 175 | 70/6 | [5 empty] | 2025-07-14 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 176 | 53/3 | [5 empty] | 2025-07-23 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 177 | 72/0 | [5 empty] | 2025-07-23 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 178 | 10/14 | [5 empty] | 2025-07-23 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 179 | 55/7 | [5 empty] | 2025-08-29 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 180 | 55/8 | [5 empty] | 2025-09-01 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 181 | 57/1 | [5 empty] | 2025-09-02 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 182 | 57/2 | [5 empty] | 2025-09-02 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 183 | 55/1 | [5 empty] | 2025-09-03 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 184 | 1A/0 | [5 empty] | 2025-09-02 00:00:00 | Done |  | READY | B.S. Infra | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 185 | 1A/1 | [5 empty] | 2025-09-03 00:00:00 | Done |  | READY | B.S. Infra | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 186 | 1A/3 | [5 empty] | 2025-09-04 00:00:00 | Done |  | READY | B.S. Infra | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 187 | 1A/4 | [5 empty] | 2025-09-05 00:00:00 | Done |  | READY | B.S. Infra | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 188 | 1A/5 | [5 empty] | 2025-09-06 00:00:00 | Done |  | READY | B.S. Infra | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 189 | 1A/6 | [5 empty] | 2025-09-07 00:00:00 | Done |  | READY | B.S. Infra | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 190 | 1A/8 | [5 empty] | 2025-09-08 00:00:00 | Done |  | READY | B.S. Infra | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 191 | 2/0 | [5 empty] | 2025-09-09 00:00:00 | Done |  | READY | B.S. Infra | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 192 | 54/3 | [5 empty] | 2025-09-24 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 193 | 70/8 | [5 empty] | 2025-10-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 194 | 70/7 | [5 empty] | 2025-10-14 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 195 | 54/4 | [5 empty] | 2025-10-15 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 196 | 54/5 | [5 empty] | 2025-10-16 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 197 | 44/11 | [5 empty] | 2025-10-17 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 198 | 45/1 | [5 empty] | 2025-10-18 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 199 | 2/1 | [5 empty] | 2025-10-19 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 200 | 2/2 | [5 empty] | 2025-10-22 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 201 | 2/3 | [5 empty] | 2025-10-23 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 202 | 10/3 | [5 empty] | 2025-10-25 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 203 | 10/4 | [5 empty] | 2025-10-26 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 204 | 10/6 | [5 empty] | 2025-10-27 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 205 | 10/12 | [5 empty] | 2025-10-28 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 206 | 11/5 | [5 empty] | 2025-10-29 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 207 | 11A/0 | [5 empty] | 2025-10-30 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 208 | 11A/9 | [5 empty] | 2025-10-31 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 209 | 52/4 | [5 empty] | 2025-11-07 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 210 | 52/1 | [5 empty] | 2025-11-07 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 211 | 52/2 | [5 empty] | 2025-11-07 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 212 | 38/4 | [5 empty] | 2025-11-12 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 213 | 39/1 | [5 empty] | 2025-11-14 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 214 | 40/0 | [5 empty] | 2025-11-15 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 215 | 30/1 | [5 empty] | 2025-11-16 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 216 | 29/4 | [5 empty] | 2025-11-17 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 217 | 30/2 | [5 empty] | 2025-11-18 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 218 | 30/3 | [5 empty] | 2025-11-18 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 219 | 30/5 | [5 empty] | 2025-11-19 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 220 | 31/1 | [5 empty] | 2025-11-19 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 221 | 31/2 | [5 empty] | 2025-11-19 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 222 | 32/1 | [5 empty] | 2025-11-19 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 223 | 28/2 | [5 empty] | 2025-11-26 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 224 | 28/0 | [5 empty] | 2025-11-27 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 225 | 27/3 | [5 empty] | 2025-11-27 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 226 | 27/2 | [5 empty] | 2025-11-27 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 227 | 70/0 | [5 empty] | 2025-11-30 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 228 | 38/3 | [5 empty] | 2025-12-04 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 229 | 28/5 | [5 empty] | 2025-12-07 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 230 | 33/0 | [5 empty] | 2025-12-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 231 | 33/1 | [5 empty] | 2025-12-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 232 | 34/1 | [5 empty] | 2025-12-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 233 | 34/3 | [5 empty] | 2025-12-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 234 | 35/0 | [5 empty] | 2025-12-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 235 | 35/1 | [5 empty] | 2025-12-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 236 | 35/2 | [5 empty] | 2025-12-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 237 | 38/0 | [5 empty] | 2025-12-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 238 | 39/0 | [5 empty] | 2025-12-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 239 | 41/0 | [5 empty] | 2025-12-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 240 | 42/0 | [5 empty] | 2025-12-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 241 | 42/3 | [5 empty] | 2025-12-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 242 | 42/4 | [5 empty] | 2025-12-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 243 | 42/5 | [5 empty] | 2025-12-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 244 | 53/2 | [5 empty] | 2025-12-09 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 245 | 54/2 | [5 empty] | 2025-12-10 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 246 | 69/0 | [5 empty] | 2025-12-11 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 247 | 69/1 | [5 empty] | 2025-12-12 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 248 | 70/1 | [5 empty] | 2025-12-13 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 249 | 70/2 | [5 empty] | 2025-12-14 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 250 | 2/5 | [5 empty] | 2025-12-15 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 251 | 2/6 | [5 empty] | 2025-12-16 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 252 | 2/8 | [5 empty] | 2025-12-17 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 253 | 8/10 | [5 empty] | 2025-12-18 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 254 | 16/5 | [5 empty] | 2025-12-19 00:00:00 | Done |  | READY | Vendor Name not confirmed by Section incharge | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 255 | 27/1 | [5 empty] | 2025-12-20 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 256 | 27/4 | [5 empty] | 2025-12-21 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 257 | 27/8 | [5 empty] | 2025-12-22 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 258 | 27/11 | [5 empty] | 2025-12-23 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 259 | 28/1 | [5 empty] | 2025-12-24 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 260 | 32/0 | [5 empty] | 2025-12-25 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 261 | 32/2 | [5 empty] | 2025-12-26 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 262 | 29/2 | [5 empty] | 2025-12-27 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 263 | 6/1 | [5 empty] | 2026-01-02 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 264 | 6/2 | [5 empty] | 2026-01-02 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 265 | 5/0 | [5 empty] | 2026-01-03 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 266 | 8/0 | [5 empty] | 2026-01-04 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 267 | 4/1 | [5 empty] | 2026-01-05 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 268 | 4/0 | [5 empty] | 2026-01-06 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 269 | 10/16 | [5 empty] | 2026-01-08 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 270 | 2/4 | [5 empty] | 2026-01-08 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 271 | 2/7 | [5 empty] | 2026-01-08 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 272 | 2/9 | [5 empty] | 2026-01-08 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 273 | 10/8 | [5 empty] | 2026-01-08 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 274 | 10/17 | [5 empty] | 2026-01-08 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 275 | 10/18 | [5 empty] | 2026-01-08 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 276 | 32/3 | [5 empty] | 2026-01-09 00:00:00 | Done |  | READY | The Shraddha Cooperative Multipurpose Society Limited | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 277 | 32/4 | [5 empty] | 2026-01-13 00:00:00 | Done |  | READY | The Shraddha Cooperative Multipurpose Society Limited | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 278 | 26/8 | [5 empty] | 2026-01-16 00:00:00 | Done |  | READY | The Shraddha Cooperative Multipurpose Society Limited | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 279 | 34/0 | [5 empty] | 2026-01-06 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 280 | 34/2 | [5 empty] | 2026-01-07 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 281 | 44/1 | [5 empty] | 2026-01-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 282 | 44/3 | [5 empty] | 2026-01-09 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 283 | 44/4 | [5 empty] | 2026-01-10 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 284 | 44/5 | [5 empty] | 2026-01-11 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 285 | 44/7 | [5 empty] | 2026-01-12 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 286 | 46/0 | [5 empty] | 2026-01-13 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 287 | 47/0 | [5 empty] | 2026-01-14 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 288 | 47/1 | [5 empty] | 2026-01-15 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 289 | 47/2 | [5 empty] | 2026-01-16 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 290 | 47/3 | [5 empty] | 2026-01-17 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 291 | 47/4 | [5 empty] | 2026-01-18 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 292 | 47/6 | [5 empty] | 2026-01-19 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 293 | 47/7 | [5 empty] | 2026-01-20 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 294 | 35/3 | [5 empty] | 2026-01-21 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 295 | 35/4 | [5 empty] | 2026-01-22 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 296 | 35/5 | [5 empty] | 2026-01-23 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 297 | 36/0 | [5 empty] | 2026-01-24 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 298 | 36/1 | [5 empty] | 2026-01-25 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 299 | 36/2 | [5 empty] | 2026-01-27 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 300 | 40/2 | [5 empty] | 2026-01-28 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 301 | 8/2 | [5 empty] | 2026-02-01 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 302 | 8/3 | [5 empty] | 2026-02-02 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 303 | 25/4 | [5 empty] | 2026-02-02 00:00:00 | Done |  | READY | The Shraddha Cooperative Multipurpose Society Limited | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 304 | 25/1 | [5 empty] | 2026-02-02 00:00:00 | Done |  | READY | The Shraddha Cooperative Multipurpose Society Limited | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 305 | 1/0 | [5 empty] | 2026-02-03 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 306 | 1A/2 | [5 empty] | 2026-02-03 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 307 | 1A/7 | [5 empty] | 2026-02-03 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 308 | 3/0 | [5 empty] | 2026-02-03 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 309 | 4/2 | [5 empty] | 2026-02-03 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 310 | 4/3 | [5 empty] | 2026-02-04 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 311 | 4/4 | [5 empty] | 2026-02-04 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 312 | 6/0 | [5 empty] | 2026-02-04 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 313 | 7/0 | [5 empty] | 2026-02-04 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 314 | 8/1 | [5 empty] | 2026-02-05 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 315 | 8/9 | [5 empty] | 2026-02-05 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 316 | 10/1 | [5 empty] | 2026-02-05 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 317 | 10/5 | [5 empty] | 2026-02-05 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 318 | 10/13 | [5 empty] | 2026-02-05 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 319 | 10/15 | [5 empty] | 2026-02-05 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 320 | 10/19 | [5 empty] | 2026-02-06 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 321 | 10/20 | [5 empty] | 2026-02-06 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 322 | 10/21 | [5 empty] | 2026-02-06 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 323 | 10/22 | [5 empty] | 2026-02-06 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 324 | 10/23 | [5 empty] | 2026-02-06 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 325 | 25/2 | [5 empty] | 2026-02-07 00:00:00 | Done |  | READY | The Shraddha Cooperative Multipurpose Society Limited | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 326 | 27/5 | [5 empty] | 2026-02-07 00:00:00 | Done |  | READY | The Shraddha Cooperative Multipurpose Society Limited | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 327 | 36/3 | [5 empty] | 2026-02-07 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 328 | 36/4 | [5 empty] | 2026-02-07 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 329 | 40/1 | [5 empty] | 2026-02-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 330 | 40/3 | [5 empty] | 2026-02-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 331 | 41/1 | [5 empty] | 2026-02-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 332 | 41/2 | [5 empty] | 2026-02-09 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 333 | 42/1 | [5 empty] | 2026-02-09 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 334 | 42/2 | [5 empty] | 2026-02-09 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 335 | 42/6 | [5 empty] | 2026-02-10 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 336 | 43/0 | [5 empty] | 2026-02-10 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 337 | 11/1 | [5 empty] | 2026-02-10 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 338 | 11/2 | [5 empty] | 2026-02-10 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 339 | 11A/8 | [5 empty] | 2026-02-10 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 340 | 12/0 | [5 empty] | 2026-02-10 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 341 | 17/4 | [5 empty] | 2026-02-10 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 342 | 18/0 | [5 empty] | 2026-02-11 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 343 | 20/2 | [5 empty] | 2026-02-11 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 344 | 20/3 | [5 empty] | 2026-02-11 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 345 | 21/4 | [5 empty] | 2026-02-11 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 346 | 21/5 | [5 empty] | 2026-02-11 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 347 | 22/13 | [5 empty] | 2026-02-11 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 348 | 43/1 | [5 empty] | 2026-02-11 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 349 | 43/2 | [5 empty] | 2026-02-11 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 350 | 43/3 | [5 empty] | 2026-02-11 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 351 | 43/4 | [5 empty] | 2026-02-12 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 352 | 43/5 | [5 empty] | 2026-02-12 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 353 | 43/6 | [5 empty] | 2026-02-12 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 354 | 43/7 | [5 empty] | 2026-02-13 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 355 | 44/0 | [5 empty] | 2026-02-13 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 356 | 44/2 | [5 empty] | 2026-02-14 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 357 | 44/6 | [5 empty] | 2026-02-14 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 358 | 8/4 | [5 empty] | 2026-02-20 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 359 | 8/5 | [5 empty] | 2026-02-20 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 360 | 10/7 | [5 empty] | 2026-02-20 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 361 | 10/9 | [5 empty] | 2026-02-21 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 362 | 10/10 | [5 empty] | 2026-02-21 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 363 | 10/11 | [5 empty] | 2026-02-22 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 364 | 11/0 | [5 empty] | 2026-02-22 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 365 | 16/1 | [5 empty] | 2026-02-22 00:00:00 | Done |  | READY | Chanda Enterprises | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 366 | 17/1 | [5 empty] | 2026-02-22 00:00:00 | Done |  | READY | Chanda Enterprises | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 367 | 27/6 | [5 empty] | 2026-02-22 00:00:00 | Done |  | READY | The Shraddha Cooperative Multipurpose Society Limited | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 368 | 27/7 | [5 empty] | 2026-02-22 00:00:00 | Done |  | READY | The Shraddha Cooperative Multipurpose Society Limited | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 369 | 27/12 | [5 empty] | 2026-02-15 00:00:00 | Done |  | READY | The Shraddha Cooperative Multipurpose Society Limited | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 370 | 28/6 | [5 empty] | 2026-02-16 00:00:00 | Done |  | READY | The Shraddha Cooperative Multipurpose Society Limited | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 371 | 28/7 | [5 empty] | 2026-02-16 00:00:00 | Done |  | READY | The Shraddha Cooperative Multipurpose Society Limited | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 372 | 29/0 | [5 empty] | 2026-02-17 00:00:00 | Done |  | READY | The Shraddha Cooperative Multipurpose Society Limited | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 373 | 44/9 | [5 empty] | 2026-02-18 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 374 | 45/0 | [5 empty] | 2026-02-18 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 375 | 53/0 | [5 empty] | 2026-02-19 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 376 | 53/1 | [5 empty] | 2026-02-19 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 377 | 53/4 | [5 empty] | 2026-02-20 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 378 | 53/5 | [5 empty] | 2026-02-20 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 379 | 53/6 | [5 empty] | 2026-02-21 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 380 | 53/7 | [5 empty] | 2026-02-21 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 381 | 54/0 | [5 empty] | 2026-02-22 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 382 | 8/12 | [5 empty] | 2026-03-01 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 383 | 44/8 | [5 empty] | 2026-03-02 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 384 | 44/10 | [5 empty] | 2026-03-04 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 385 | 52/3 | [5 empty] | 2026-03-05 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 386 | 54/1 | [5 empty] | 2026-03-06 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 387 | 55/0 | [5 empty] | 2026-03-07 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 388 | 55/2 | [5 empty] | 2026-03-08 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 389 | 56/0 | [5 empty] | 2026-03-09 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 390 | 57/0 | [5 empty] | 2026-03-09 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 391 | 13/0 | [5 empty] | 2026-03-30 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 392 | 13/2 | [5 empty] | 2026-04-01 00:00:00 | Done |  | READY | Yet to be confirm | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 393 | 11A/1 | [5 empty] | 2026-04-05 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 394 | 11A/2 | [5 empty] | 2026-04-04 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 395 | 11A/3 | [5 empty] | 2026-04-05 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 396 | 11A/4 | [5 empty] | 2026-04-06 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 397 | 11A/5 | [5 empty] | 2026-04-03 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 398 | 11A/6 | [5 empty] | 2026-04-03 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 399 | 11A/7 | [5 empty] | 2026-04-02 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 400 | 13/1 | [5 empty] | 2026-04-01 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 401 | 13/4 | [5 empty] | 2026-04-01 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 402 | 15/0 | [5 empty] | 2026-04-06 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 403 | 8/6 | [5 empty] | 2026-04-20 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 404 | 8/7 | [5 empty] | 2026-04-20 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 405 | 8/8 | [5 empty] | 2026-04-21 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 406 | 8/11 | [5 empty] | 2026-04-21 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 407 | 9/0 | [5 empty] | 2026-04-22 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 408 | 10/0 | [5 empty] | 2026-04-22 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 409 | 10/2 | [5 empty] | 2026-04-23 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 410 | 14/0 | [5 empty] | 2026-04-23 00:00:00 | Done |  | READY | Shiv Power | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 411 | 19/0 | [5 empty] | 2026-04-24 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 412 | 21/8 | [5 empty] | 2026-04-25 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 413 | 21/10 | [5 empty] | 2026-04-26 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 414 | 24/0 | [5 empty] | 2026-04-27 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 415 | 18/3 | [5 empty] | 2026-04-29 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 416 | 14A/2 | [5 empty] | 2026-04-30 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 417 | 14A/1 | [5 empty] | 2026-04-30 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 418 | 53/8 | [5 empty] | 2026-04-19 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 419 | 43/8 | [5 empty] | 2026-04-21 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 420 | 43/9 | [5 empty] | 2026-04-22 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 421 | 43/10 | [5 empty] | 2026-04-23 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 422 | 43/11 | [5 empty] | 2026-04-24 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 423 | 47/5 | [5 empty] | 2026-04-16 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 424 | 37/0 | [5 empty] | 2026-04-29 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 425 | 34/4 | [5 empty] | 2026-05-02 00:00:00 | Done |  | READY | Suraja Ram | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 426 | 19/2 | [5 empty] | 2026-05-05 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 427 | 18/4 | [5 empty] | 2026-05-05 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 428 | 21/2 | [5 empty] | 2026-05-05 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 429 | 27/9 | [5 empty] | 2026-05-09 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 430 | 28/3 | [5 empty] | 2026-05-10 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 431 | 28/4 | [5 empty] | 2026-05-13 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 432 | 27/10 | [5 empty] | 2026-05-13 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 433 | 29/3 | [5 empty] | 2026-05-14 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 434 | 28/8 | [5 empty] | 2026-05-15 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 435 | 29/1 | [5 empty] | 2026-05-17 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 436 | 16/0 | [5 empty] | 2026-05-18 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 437 | 26/0 | [5 empty] | 2026-05-20 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 438 | 31/0 | [5 empty] | 2026-05-21 00:00:00 | Done |  | READY | Jai Bagrangbali | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 408 | TB 408 | tb408 |  | filename |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | TB 408 Stretch | 2026-06-01 | 5 | 439 | 13/3 | [5 empty] | 2026-05-24 00:00:00 | Done |  | READY | Gang name not confimed | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 5 | 8/0 | [5 empty] | DB+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 6 | 8/4 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 7 | 8/3 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 8 | 9/4 | [5 empty] | DA+6 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 9 | 9/5 | [5 empty] | DB+6 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 10 | 8/2 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 11 | 9/3 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 12 | 9/0 | [5 empty] | DC+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 13 | 10/0 | [6 empty] | wip |  | NOT_READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 14 | 10/1 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 15 | 10/4 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 16 | 10/11 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 17 | 10/12 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 18 | 10/13 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 19 | 65/0 | [5 empty] | DD+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 20 | 65/1 | [5 empty] | DB+9 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 21 | 66/0 | [5 empty] | DD+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 22 | 72/0 | [5 empty] | DD+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 23 | 72/2 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 24 | 73/0 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 25 | 73/1 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 26 | 75/0 | [5 empty] | DC+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 27 | 75/1 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 28 | 75/2 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 29 | 75/3 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 30 | 75/4 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 31 | 75/5 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 32 | 75/6 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 33 | 75/7 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 34 | 76/0 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 35 | 76/1 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 36 | 77/0 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 37 | 77/1 | [8 empty] | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 38 | 77/2 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 39 | 77/3 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 40 | 77/4 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 41 | 77/5 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 42 | 79/0 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 43 | 79/1 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 44 | 79/2 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 45 | 78/0 | [5 empty] | DC+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 46 | 78/1 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 47 | 80/0 | [5 empty] | DB+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 48 | 80/1 | [5 empty] | DA+9 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 49 | 81/0 | [5 empty] | DB+9 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 50 | 81/1 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 51 | 81/2 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 52 | 81/3 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 53 | 81/4 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 54 | 81/5 | [5 empty] | DA+6 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 55 | 82/0 | [5 empty] | DB+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 56 | 82/1 | [5 empty] | DA+6 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 57 | 82/2 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 58 | 83/0 | [5 empty] | DC+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 59 | 83/1 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 60 | 84/0 | [5 empty] | DC+6 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 61 | 85/0 | [5 empty] | DC+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 62 | 85/1 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 63 | 86/0 | [5 empty] | DD+0 | ROW |  | NOT_READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 64 | 86/1 | [5 empty] | DA+6 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 65 | 86/2 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 66 | 89/1 | [5 empty] | DA+9 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 67 | 90/0 | [5 empty] | DC+0 | WIP |  | NOT_READY |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 68 | 90/1 | [5 empty] | DA+9 |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 69 | 91/0 | [6 empty] | Done |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 70 | 91/3 | [6 empty] | Done |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 71 | 92/0 | [6 empty] | Done |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 72 | 93/0 | [6 empty] | Done |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 73 | 95/0 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 74 | 98B/0 | [5 empty] | DD+0 |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 75 | 98A/1 | [5 empty] | DA+0 |  |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 76 | 109A/0 | [5 empty] | DB+6 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 77 | 110/0 | [5 empty] | DC+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 78 | 111/0 | [5 empty] | DB+9 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 79 | 112/0 | [5 empty] | DC+9 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 80 | 113/0 | [5 empty] | DD+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 81 | 113A/0 | [5 empty] | DC+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 82 | 114/0 | [5 empty] | DC+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 83 | 114/1 | [5 empty] | DA+9 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 84 | 115/0 | [5 empty] | DC+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 85 | 115/1 | [5 empty] | DB+9 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 86 | 116/0 | [5 empty] | DD+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 87 | 116/1 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 88 | 127/1 | [5 empty] | DA+9 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 89 | 128/0 | [5 empty] | DC+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 90 | 128/1 | [5 empty] | DA+6 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 91 | 129/0 | [5 empty] | DC+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 92 | 129/1 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 93 | 129/2 | [5 empty] | DA+9 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 94 | 130/0 | [5 empty] | DC+6 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 95 | 130/1 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 96 | 131/0 | [5 empty] | DD+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 97 | 131/1 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 98 | 131/2 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 99 | 132/0 | [6 empty] | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 100 | 132/1 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 101 | 132/2 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 102 | 132/3 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 103 | 132/4 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 104 | 133/0 | [5 empty] | DC+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 105 | 133/1 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 106 | 133/2 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 107 | 133/3 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 108 | 133/4 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 109 | 133/5 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 110 | 133/6 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 111 | 133/7 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 112 | 133/8 | [5 empty] | DA+6 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 113 | 134/0 | [5 empty] | DD+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 114 | 134A/0 | [5 empty] | DD+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 115 | 134A/1 | [5 empty] | DA+9 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 116 | 134A/2 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 117 | 134A/3 | [5 empty] | DA+6 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 118 | 134A/4 | [5 empty] | DA+9 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 119 | 135/0 | [5 empty] | DC+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 120 | 135/1 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 121 | 135/2 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 122 | 135/3 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 123 | 136/0 | [5 empty] | DD+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 124 | 137/0 | [5 empty] | DB+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 125 | 138/0 | [5 empty] | DB+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 126 | 138/1 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 127 | 138/2 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 128 | 138/3 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 129 | 139/0 | [5 empty] | DC+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 130 | 139/1 | [5 empty] | DA+9 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 131 | 140/0 | [5 empty] | DB+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 132 | 140/1 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 133 | 140/2 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 134 | 140/3 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 135 | 141/0 | [5 empty] | DC+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 136 | 141/1 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 137 | 141/2 | [5 empty] | DA+6 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 138 | 142/0 | [5 empty] | DC+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 139 | 143/0 | [5 empty] | DC+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 140 | 143/1 | [5 empty] | DA+6 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 141 | 143/2 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 142 | 143/3 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 143 | 143/4 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 144 | 143/5 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 145 | 143/6 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 146 | 143/7 | [5 empty] | DA+6 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 147 | 144/0 | [5 empty] | DD+6 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 148 | 145/0 | [5 empty] | DD+6 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 149 | 145/1 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 150 | 145/2 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 151 | 145/3 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 152 | 145/4 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 153 | 146/0 | [5 empty] | DC+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 154 | 146/1 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 155 | 146/2 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 156 | 147/0 | [5 empty] | DC+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 157 | 147/1 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 158 | 147/2 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 159 | 147/3 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 160 | 147/4 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 161 | 147/5 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 162 | 147/6 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 163 | 147/7 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 164 | 147/8 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 165 | 147/9 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 166 | 148/0 | [5 empty] | DB+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 167 | 148/1 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 168 | 148/2 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 169 | 148/3 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 170 | 148/4 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 171 | 148/5 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 172 | 148/6 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 173 | 148/7 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 174 | 149/0 | [5 empty] | DD+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 175 | 149A/0 | [5 empty] | DD+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 176 | 149B/0 | [5 empty] | DB+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 177 | 149B/1 | [5 empty] | DA+3 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 178 | 149B/2 | [5 empty] | DA+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 179 | 149B/3 | [5 empty] | DB+9 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 180 | 150/0 | [5 empty] | DD+9 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 181 | 151/0 | [5 empty] | DD+9 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 182 | 152/0 | [5 empty] | DD+18 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 183 | 153/0 | [5 empty] | DD+18 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 184 | 153A/0 | [5 empty] | DB+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 185 | 154/0 | [5 empty] | DD+0 | DONE |  | PARTIAL |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET
TB 507 | TB 507 - MAIN | tb507main | MAIN | config |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | TB 507 Stretch | 2026-07-26 | 4 | 187 | [7 empty] | 173 |  | UNKNOWN |  | LEGACY_STRETCH_SHEET | LEGACY_STRETCH_SHEET

## Summary
project_code | project_display | project_scope_key | line_name | line_name_source | report_date | source_files | source_sheets | total_count | ready_count | partial_count | not_ready_count | unknown_count | balance_count | total_km | ready_km | balance_km | readiness_pct | basis
TA 413 | TA 413 | ta413 |  | filename | 2026-07-28 | 1 | 1 | 66 | 0 | 0 | 5 | 61 | 66 | 118.0918 | 0 | 118.0918 | 0 | count_and_km
TA 419 | TA 419 | ta419 |  | filename | 2026-07-29 | 1 | 1 | 333 | 0 | 0 | 133 | 200 | 333 | 122.0225 | 0 | 122.0225 | 0 | count_and_km
TA 421 | TA 421 | ta421 |  | filename | 2026-07-11 | 1 | 1 | 305 | 0 | 55 | 0 | 250 | 305 | 0 | 0 | 0 | 0 | count_and_km
TA 504 | TA 504 | ta504 |  | filename | 2026-07-27 | 1 | 1 | 11 | 0 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | count_and_km
TA 505 | TA 505 | ta505 |  | filename | 2026-07-22 | 1 | 1 | 33 | 0 | 0 | 0 | 33 | 33 | 48.0924 | 0 | 48.0924 | 0 | count_and_km
TA 506 | TA 506 | ta506 |  | filename | 2026-07-27 | 1 | 1 | 55 | 55 | 0 | 0 | 0 | 0 | 78.2915 | 78.2915 | 0 | 100 | count_and_km
TA 512 | TA 512 | ta512 |  | filename | 2026-07-28 | 1 | 1 | 128 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | count_and_km
TA 601 | TA 601 | ta601 |  | filename | 2026-07-28 | 1 | 1 | 64 | 0 | 0 | 0 | 64 | 64 | 226.5384 | 0 | 226.5384 | 0 | count_and_km
TB 408 | TB 408 | tb408 |  | filename | 2026-06-01 | 1 | 1 | 434 | 434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | count_and_km
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | 2026-07-26 | 1 | 1 | 182 | 0 | 174 | 3 | 5 | 182 | 0 | 0 | 0 | 0 | count_and_km

## ManpowerAudit
project_code | project_display | project_scope_key | line_name | line_name_source | source_file | source_sheet | configured_sheet | header_row_number | manpower_fields | readiness_fields | readiness_column_present | signal_type | non_empty_count | sample_values | expected_manpower | expected_match | status | reason
TA 413 | TA 413 | ta413 |  | filename | TA 413 - DPR - 2026-07-28.xlsx | Stringing | Stringing | 3 |  |  | FALSE | ABSENT | 0 |  | no | TRUE | ABSENT
TA 414 | TA 414 | ta414 |  | filename | TA 414 - DPR - 2026-07-28.xlsx | Stringing Compiled | Stringing Compiled | 1 | gang strength | Section Readiness | TRUE | PRESENT_WITH_VALUES | 20 | 24; 49 | unknown | TRUE | PRESENT_WITH_VALUES
TA 416 | TA 416 | ta416 |  | filename | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | Stringing compiled | 2 | gang strength | Section Readiness | TRUE | PRESENT_WITH_VALUES | 4 | 40; 20; 36 | no | FALSE | PRESENT_WITH_VALUES
TA 418 | TA 418 | ta418 |  | filename | TA 418 - DPR - 2026-07-21.xlsx |  | Stringing Compiled |  |  |  | FALSE | READ_FAIL | 0 |  | yes | FALSE | READ_FAIL | NO_TARGET_SHEET
TA 419 | TA 419 | ta419 | [8 empty] | FALSE | NO_SHEET_CONFIG | 0 |  | unknown | TRUE | NO_SHEET_CONFIG | No daily stringing sheet configured for manpower audit.
TA 421 | TA 421 | ta421 |  | filename | TA 421 - DPR - 2026-07-11.xlsx | Stringing Compiled | Stringing Compiled | 2 | gang strength | Section Readiness | TRUE | PRESENT_WITH_VALUES | 60 | 35 | yes | TRUE | PRESENT_WITH_VALUES
TA 504 | TA 504 | ta504 |  | filename | TA 504 - DPR - 2026-07-27.xlsx | Stringing Compiled | Stringing | 1 | gang strength | Section Readiness | TRUE | PRESENT_WITH_VALUES | 11 | 40; 50 | yes | TRUE | PRESENT_WITH_VALUES
TA 505 | TA 505 | ta505 |  | filename | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | 3 | gang strength | Section Readiness | TRUE | PRESENT_WITH_VALUES | 25 | 30 | yes | TRUE | PRESENT_WITH_VALUES
TA 506 | TA 506 | ta506 |  | filename | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | 1 | gang strength | Section Readiness | TRUE | PRESENT_WITH_VALUES | 55 | 40; 39 | yes | TRUE | PRESENT_WITH_VALUES
TA 512 | TA 512 | ta512 | [8 empty] | FALSE | NO_SHEET_CONFIG | 0 |  | unknown | TRUE | NO_SHEET_CONFIG | No daily stringing sheet configured for manpower audit.
TA 601 | TA 601 | ta601 |  | filename | TA 601 - DPR - 2026-07-28.xlsx | Stringing Compiled | Stringing Compiled | 0 | R1C20:Gang Strength | R1C7:Section Readiness | TRUE | HEADER_ONLY | 0 |  | unknown | TRUE | HEADER_ONLY
TB 408 | TB 408 | tb408 |  | filename | TB 408 - DPR - 2026-06-01.xlsx | Stringing | Stringing | 3 |  |  | FALSE | ABSENT | 0 |  | no | TRUE | ABSENT
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | config | TB 501 - DPR - 2026-07-28.xlsx | Stringing-132KV | Stringing-132KV | 4 | R4C17:MP | R4C5:Stretch Readiness | TRUE | HEADER_ONLY | 0 |  | no | TRUE | HEADER_ONLY
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | config | TB 501 - DPR - 2026-07-28.xlsx | Stringing-220kV | Stringing-220kV | 4 | R4C16:MP | R4C5:Stretch Readiness | TRUE | HEADER_ONLY | 0 |  | no | TRUE | HEADER_ONLY
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Stringing Compiled | Stringing Compiled | 2 | manpower | Section Readiness | TRUE | PRESENT_WITH_VALUES | 14 | 15; 25; 40 | no | FALSE | PRESENT_WITH_VALUES

## Diagnostics
Workbook | Project | Category | Sheet | ConfiguredSheet | LineName | LineNameSource | TemplateSheet | TemplateApplied | TemplateChanges | FallbackNote | SectionsDetected | HeadersDetected | Rows | Status | Reason
TA 413 - DPR - 2026-07-28.xlsx | TA 413 | stretch | Stretch readiness | Stretch readiness |  | filename | TA 413 Stretch | TRUE | C2:Section->stretch_identifier; C3:Section Length (M)->length_m; C10:Balance__2->balance_towers; C12:Stringing Remarks->remarks | XML scrub fallback used for sheet 'Stretch readiness ' | 1 | 1 | 66 | OK
TA 413 - DPR - 2026-07-28.xlsx | TA 413 | manpower | Stringing | Stringing |  | filename |  | FALSE |  | XML scrub fallback used for sheet 'Stringing' | 0 | 1 | 46 | ABSENT
TA 414 - DPR - 2026-07-28.xlsx | TA 414 | manpower | Stringing Compiled | Stringing Compiled |  | filename |  | FALSE |  | XML scrub fallback used for sheet 'Stringing Compiled' | 0 | 1 | 172 | PRESENT_WITH_VALUES
TA 416 - DPR - 2026-07-16.xlsx | TA 416 | manpower | Stringing compiled | Stringing compiled |  | filename |  | FALSE |  |  | 0 | 1 | 79 | PRESENT_WITH_VALUES
TA 418 - DPR - 2026-07-21.xlsx | TA 418 | manpower |  | Stringing Compiled |  | filename |  | FALSE |  |  | 0 | 0 | 0 | READ_FAIL | NO_TARGET_SHEET
TA 419 - DPR - 2026-07-29.xlsx | TA 419 | stretch | Stringing Stretch Readiness | Stringing Stretch Readiness |  | filename | TA 419 Stretch | TRUE | C2:Loc. No.->stretch_identifier; C4:Span (in mtrs.)->length_m; C9:TSE/ Manual->readiness_raw; C11:Stringing Section->section_name; C13:Section Length->remarks; C16:No Of Towers->balance_towers | XML scrub fallback used for sheet 'Stringing Stretch Readiness' | 1 | 1 | 334 | OK
TA 421 - DPR - 2026-07-11.xlsx | TA 421 | stretch | Tack Welding | Tack Welding |  | filename | TA 421 Tack Welding Stretch | TRUE | C2:unnamed_col_2->stretch_identifier; C4:LOCATION NO.->tack_welding_raw; C5:TYPE OF TOWER->remarks |  | 1 | 1 | 305 | OK
TA 421 - DPR - 2026-07-11.xlsx | TA 421 | manpower | Stringing Compiled | Stringing Compiled |  | filename |  | FALSE |  |  | 0 | 1 | 76 | PRESENT_WITH_VALUES
TA 504 - DPR - 2026-07-27.xlsx | TA 504 | stretch | Stringing Compiled | Stringing |  | filename | TA 504 Stretch | TRUE | C2:Sec->stretch_identifier; C3:From AP->from_ap; C4:To AP->to_ap; C5:Location Nos.->length_m; C7:Method->readiness_raw; C23:Hindrance->remarks | XML scrub fallback used for sheet 'Stringing Compiled' | 1 | 1 | 11 | OK
TA 504 - DPR - 2026-07-27.xlsx | TA 504 | manpower | Stringing Compiled | Stringing |  | filename |  | FALSE |  | XML scrub fallback used for sheet 'Stringing Compiled'; Configured sheet 'Stringing' not found; used 'Stringing Compiled'. | 0 | 1 | 11 | PRESENT_WITH_VALUES
TA 505 - DPR - 2026-07-22.xlsx | TA 505 | stretch | Stringing Compiled | Stringing Compiled |  | filename | TA 505 Stretch | TRUE | C2:Sec->stretch_identifier; C3:From AP->from_ap; C4:To AP->to_ap; C5:Span (M)->length_m; C7:Method->readiness_raw; C23:Hindrance->remarks |  | 1 | 1 | 33 | OK
TA 505 - DPR - 2026-07-22.xlsx | TA 505 | manpower | Stringing Compiled | Stringing Compiled |  | filename |  | FALSE |  |  | 0 | 1 | 47 | PRESENT_WITH_VALUES
TA 506 - DPR - 2026-07-27.xlsx | TA 506 | stretch | Stringing | Stringing |  | filename | TA 506 Stretch | TRUE | C2:Sec->stretch_identifier; C3:From AP->from_ap; C4:To AP->to_ap; C5:Span (M)->length_m; C7:Section Readiness->readiness_raw | XML scrub fallback used for sheet 'Stringing' | 1 | 1 | 55 | OK
TA 506 - DPR - 2026-07-27.xlsx | TA 506 | manpower | Stringing | Stringing |  | filename |  | FALSE |  | XML scrub fallback used for sheet 'Stringing' | 0 | 1 | 229 | PRESENT_WITH_VALUES
TA 512 - DPR - 2026-07-28.xlsx | TA 512 | stretch | Tack Welding | Tack Welding |  | filename | TA 512 Stretch | TRUE | C3:Loc. No.->stretch_identifier; C5:Start->final_check_raw; C6:Complete->tack_welding_raw |  | 1 | 1 | 128 | OK
TA 601 - DPR - 2026-07-28.xlsx | TA 601 | stretch | STRG Stretch | STRG Stretch |  | filename | TA 601 Stretch | TRUE | C2:Section From->stretch_identifier; C3:Section TO->to_ap; C4:LENGTH (km)->length_m; C14:Stringing Status->remarks; C15:Streach Ready Y/N->readiness_raw |  | 1 | 1 | 64 | OK
TA 601 - DPR - 2026-07-28.xlsx | TA 601 | manpower | Stringing Compiled | Stringing Compiled |  | filename |  | FALSE |  |  | 0 | 1 | 0 | HEADER_ONLY
TB 408 - DPR - 2026-06-01.xlsx | TB 408 | stretch | Tackwelding | Tackwelding |  | filename | TB 408 Stretch | TRUE | C2:Loc. No.->stretch_identifier; C5:Completion Date->final_check_raw; C6:Name of the Contractor->remarks; C7:Tackwelding->tack_welding_raw |  | 1 | 1 | 434 | OK
TB 408 - DPR - 2026-06-01.xlsx | TB 408 | manpower | Stringing | Stringing |  | filename |  | FALSE |  |  | 0 | 1 | 65 | ABSENT
TB 501 - DPR - 2026-07-28.xlsx | TB 501 | manpower | Stringing-132KV | Stringing-132KV | 132kV | config |  | FALSE |  |  | 0 | 1 | 48 | HEADER_ONLY
TB 501 - DPR - 2026-07-28.xlsx | TB 501 | manpower | Stringing-220kV | Stringing-220kV | 220kV | config |  | FALSE |  |  | 0 | 1 | 226 | HEADER_ONLY
TB 507 [MAIN] - DPR - 2026-07-26.xlsx | TB 507 | stretch | Final Check In And Tack Welding | Final Check In And Tack Welding | MAIN | config | TB 507 Stretch | TRUE | C3:Loc No->stretch_identifier; C4:TOT->final_check_raw; C5:Final Checking->tack_welding_raw |  | 1 | 1 | 182 | OK
TB 507 [MAIN] - DPR - 2026-07-26.xlsx | TB 507 | manpower | Stringing Compiled | Stringing Compiled | MAIN | config |  | FALSE |  |  | 0 | 1 | 37 | PRESENT_WITH_VALUES
StringingCompiled.parquet; RawData.parquet |  | stretch_derived |  |  |  | derived |  | FALSE |  |  | 0 | 0 | 0 | NO_DERIVED_INPUT | Derived readiness inputs unavailable; legacy stretch readiness (if present) retained.

## Issues
Workbook | Project | Category | Sheet | ConfiguredSheet | LineName | LineNameSource | Issue | Reason
TA 418 - DPR - 2026-07-21.xlsx | TA 418 | stretch | Stringing Completed | Stringing Compiled |  | filename | MISSING_SOURCE | Configured stretch readiness sheet not found in selected workbook.
TA 418 - DPR - 2026-07-21.xlsx | TA 418 | manpower |  | Stringing Compiled |  | filename | READ_FAIL | NO_TARGET_SHEET
TB 507 - DPR - 2026-07-26.xlsx | TB 507 | stretch | Final Checking and Tack Welding | Final Check In And Tack Welding | MAIN | config | MISSING_SOURCE | Configured stretch readiness sheet not found in selected workbook.
TB 507 - DPR - 2026-07-26.xlsx | TB 507 | stretch |  |  |  | filename | MISSING_SOURCE | No dedicated stretch readiness sheet configured for this project line variant.

## Coverage
project_code | project_display | category | status | reason_code | reason | workbook | configured_sheet | resolved_sheet | rows | available_sheets
TA 413 | TA 413 | stretch | OK | OK |  | TA 413 - DPR - 2026-07-28.xlsx | Stretch readiness | Stretch readiness | 66 | TA413_PBNTL; WIP; Visual Chart; Stringing; Stretch readiness ; Erection; L2 Plan vs Actual; Survey summary; Detailed Survey ; Check Survey ; Earthing; Tack Welding; Final checking; Bird Guard ; Aviation Paint; Accessories; OPGW; Foundation; JUMPER Details; Crossing status; ROW Tracker; S-Curve FDN; S-Curve Erection; S-Curve Stringing; Supply Status; Hardware Supply; Tower Abstract sheet; Statutory Proposals; Tower Abstarct ; Location Summary; Foundation Daily Progress; Tower PRS abstract ; Stretch readiness (2); Area
TA 413 | TA 413 | manpower | ABSENT | ABSENT |  | TA 413 - DPR - 2026-07-28.xlsx | Stringing | Stringing | 46 | TA413_PBNTL; WIP; Visual Chart; Stringing; Stretch readiness ; Erection; L2 Plan vs Actual; Survey summary; Detailed Survey ; Check Survey ; Earthing; Tack Welding; Final checking; Bird Guard ; Aviation Paint; Accessories; OPGW; Foundation; JUMPER Details; Crossing status; ROW Tracker; S-Curve FDN; S-Curve Erection; S-Curve Stringing; Supply Status; Hardware Supply; Tower Abstract sheet; Statutory Proposals; Tower Abstarct ; Location Summary; Foundation Daily Progress; Tower PRS abstract ; Stretch readiness (2); Area
TA 414 | TA 414 | stretch | MISSING_SOURCE | MISSING_SOURCE | No dedicated stretch readiness sheet configured. | TA 414 - DPR - 2026-07-28.xlsx |  |  | 0
TA 414 | TA 414 | manpower | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES |  | TA 414 - DPR - 2026-07-28.xlsx | Stringing Compiled | Stringing Compiled | 172 | Project Details; 765KV TA 414 VNTL; VNTL - KEC; DPR Sheet; Sheet5; Sheet3; Sheet1; FDN; FDN Completed; Erection ; Erection Completed ; Erection Compiled; Stringing; Stringing Completed; Sheet6; Sheet4; Sheet7; Stringing Compiled; Visual chart; Pile Fdn; Crossing; Sheet2; Survey; Soil Inv.; Survey Anx
TA 416 | TA 416 | stretch | MISSING_SOURCE | MISSING_SOURCE | No dedicated stretch readiness sheet configured. | TA 416 - DPR - 2026-07-16.xlsx |  |  | 0
TA 416 | TA 416 | manpower | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES |  | TA 416 - DPR - 2026-07-16.xlsx | Stringing compiled | Stringing compiled | 79 | Project Details; MASTER SHEET; Erection Compiled ; Stringing compiled; Progress.; Visual chart.; PENDING FDN DETAILS; PENDING ERE DETAILS; TSE-MANUAL-LT-11KV-33KV Details; Crossing Details; TS; TS (2)
TA 418 | TA 418 | stretch | MISSING_SOURCE | MISSING_SOURCE | Configured stretch readiness sheet not found in selected workbook. | TA 418 - DPR - 2026-07-21.xlsx | Stringing Compiled |  | 0 | MASTER SHEET; Progress; Erection Completed; Stringing Completed; Visual Chart; ROW TRACKER; PENDING FDN DETAILS; TSE-MANUAL-LT-11KV-33KV Details; Crossing Details; Project Details; TS; TS (2)
TA 418 | TA 418 | manpower | READ_FAIL | READ_FAIL | NO_TARGET_SHEET | TA 418 - DPR - 2026-07-21.xlsx | Stringing Compiled |  | 0 | MASTER SHEET; Progress; Erection Completed; Stringing Completed; Visual Chart; ROW TRACKER; PENDING FDN DETAILS; TSE-MANUAL-LT-11KV-33KV Details; Crossing Details; Project Details; TS; TS (2)
TA 419 | TA 419 | stretch | OK | OK |  | TA 419 - DPR - 2026-07-29.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | 334 | DPR_TA419; Soil Inv; RATE; FDN; Updated Tower Schedule; Visual Chart; ERT; ERECTION COMPILED; Stringing Compiled; Stringing Stretch Readiness; Project details; Detailed Survey; Supply; dont change; TOWER ABSTRACT; Corridor LS; Foundation Daily Progresss; Erection Daily Progress; Statutory
TA 419 | TA 419 | manpower | NO_SHEET_CONFIG | NO_SHEET_CONFIG | No daily stringing sheet configured for manpower audit. | TA 419 - DPR - 2026-07-29.xlsx |  |  | 0
TA 421 | TA 421 | stretch | OK | OK |  | TA 421 - DPR - 2026-07-11.xlsx | Tack Welding | Tack Welding | 305 | Project Details; Master Sheet; ProGress Sheet ; Erection Compiled ; Stringing Compiled ; Erection Productivity ; Visual Chart ; Stubs and Towers ; SuPPLY ; X-ing Details ; Tack Welding ; Tower Accessories ; AL Bond ; Birdguard ; Tower Tightening ; Hardwares & Tower Accessories ; SwE
TA 421 | TA 421 | manpower | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES |  | TA 421 - DPR - 2026-07-11.xlsx | Stringing Compiled | Stringing Compiled | 76 | Project Details; Master Sheet; ProGress Sheet ; Erection Compiled ; Stringing Compiled ; Erection Productivity ; Visual Chart ; Stubs and Towers ; SuPPLY ; X-ing Details ; Tack Welding ; Tower Accessories ; AL Bond ; Birdguard ; Tower Tightening ; Hardwares & Tower Accessories ; SwE
TA 504 | TA 504 | stretch | OK | OK |  | TA 504 - DPR - 2026-07-27.xlsx | Stringing | Stringing Compiled | 11 | DPR_TA-504; Erection compiled; Tightening; Stringing Compiled; VC_MAIN; VC_LILO; Project Details; Location Summary
TA 504 | TA 504 | manpower | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES |  | TA 504 - DPR - 2026-07-27.xlsx | Stringing | Stringing Compiled | 11 | DPR_TA-504; Erection compiled; Tightening; Stringing Compiled; VC_MAIN; VC_LILO; Project Details; Location Summary
TA 505 | TA 505 | stretch | OK | OK |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | 33 | DPR-Summary; Sheet1; Project Details; Sheet5; Foundation; Balance Erc-RAJ; ERC ROW-MP; Erection Compiled; Stringing Compiled; Visual Chart; Erection Productivity; Earthing Status; Sheet4; Sheet3; Sheet2
TA 505 | TA 505 | manpower | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES |  | TA 505 - DPR - 2026-07-22.xlsx | Stringing Compiled | Stringing Compiled | 47 | DPR-Summary; Sheet1; Project Details; Sheet5; Foundation; Balance Erc-RAJ; ERC ROW-MP; Erection Compiled; Stringing Compiled; Visual Chart; Erection Productivity; Earthing Status; Sheet4; Sheet3; Sheet2
TA 506 | TA 506 | stretch | OK | OK |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | 55 | DPR_TA-506; VC; Erection compiled; Tightening; Stringing; Project Details; Location Summary
TA 506 | TA 506 | manpower | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES |  | TA 506 - DPR - 2026-07-27.xlsx | Stringing | Stringing | 229 | DPR_TA-506; VC; Erection compiled; Tightening; Stringing; Project Details; Location Summary
TA 512 | TA 512 | stretch | OK | OK |  | TA 512 - DPR - 2026-07-28.xlsx | Tack Welding | Tack Welding | 128 | Summary S; Supply Status; Summary E; DPR Sheet ; DS; CS; Hindrance Record; Earthing; Foundation; Erection Compiled; Tack Welding; Visual Chart; WIP; Stringing; Statuary clearance; OPGW; Accessories; Shield Wire Earthing; TS Gantry - AP47; Project Details; L3 Plan; Supply DPR ; Power line Crossings ; Hardware
TA 512 | TA 512 | manpower | NO_SHEET_CONFIG | NO_SHEET_CONFIG | No daily stringing sheet configured for manpower audit. | TA 512 - DPR - 2026-07-28.xlsx |  |  | 0
TA 601 | TA 601 | stretch | OK | OK |  | TA 601 - DPR - 2026-07-28.xlsx | STRG Stretch | STRG Stretch | 64 | Visual Chart ; Master Sheet; Progress Sheet ; SUPPLY; Erection Compiled; X-ing Details ; Visual Chart; Foundation & Erection; STRG Stretch ; Stringing Compiled
TA 601 | TA 601 | manpower | HEADER_ONLY | HEADER_ONLY |  | TA 601 - DPR - 2026-07-28.xlsx | Stringing Compiled | Stringing Compiled | 0 | Visual Chart ; Master Sheet; Progress Sheet ; SUPPLY; Erection Compiled; X-ing Details ; Visual Chart; Foundation & Erection; STRG Stretch ; Stringing Compiled
TB 408 | TB 408 | stretch | OK | OK |  | TB 408 - DPR - 2026-06-01.xlsx | Tackwelding | Tackwelding | 434 | Progress Summary; Project Details; X-ing Status; L2 Schedule vs Actual; Hindrance Register (Row); Page Chart; Survey; Foundation; Earthing; Erection Productivity; Crane Erection Productivity; Erection Compiled; Tackwelding; Stringing; Stringing associated works; Stringing Productivity; OPGW; Accessories details; Visual chart; Visual chart Edit; Benching F
TB 408 | TB 408 | manpower | ABSENT | ABSENT |  | TB 408 - DPR - 2026-06-01.xlsx | Stringing | Stringing | 65 | Progress Summary; Project Details; X-ing Status; L2 Schedule vs Actual; Hindrance Register (Row); Page Chart; Survey; Foundation; Earthing; Erection Productivity; Crane Erection Productivity; Erection Compiled; Tackwelding; Stringing; Stringing associated works; Stringing Productivity; OPGW; Accessories details; Visual chart; Visual chart Edit; Benching F
TB 501 | TB 501 | stretch | MISSING_SOURCE | MISSING_SOURCE | No dedicated stretch readiness sheet configured. | TB 501 - DPR - 2026-07-28.xlsx |  |  | 0
TB 501 | TB 501 - 132kV | manpower | HEADER_ONLY | HEADER_ONLY |  | TB 501 - DPR - 2026-07-28.xlsx | Stringing-132KV | Stringing-132KV | 48 | Detail Survey-220kV; Check Survey-220kV; Detail Survey-132kV; Check Survey-132kV; Summary; Statutory; Progress-132kV; Progress-220kV; Stringing-220kV; Stringing-132KV; VC-220kV; VC-132kV; Supply; Mail Body
TB 501 | TB 501 - 220kV | manpower | HEADER_ONLY | HEADER_ONLY |  | TB 501 - DPR - 2026-07-28.xlsx | Stringing-220kV | Stringing-220kV | 226 | Detail Survey-220kV; Check Survey-220kV; Detail Survey-132kV; Check Survey-132kV; Summary; Statutory; Progress-132kV; Progress-220kV; Stringing-220kV; Stringing-132KV; VC-220kV; VC-132kV; Supply; Mail Body
TB 507 | TB 507 - MAIN | stretch | MISSING_SOURCE | MISSING_SOURCE | Configured stretch readiness sheet not found in selected workbook. | TB 507 - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding |  | 0 | 765kV Summery; Check Survey Status; Check Survey; Sheet8; Sheet2; Sheet1; VC 51-96; VC; ROW; June; Check survey Loop out; Check survey Loop In; Royalty; Sheet14; Sheet7; Project Details; Foundation; Erection ; Completion date; Erection Compiled ; Earthing; Final Checking and Tack Welding; Stringing Compiled ; Soil Investigation; Sheet9; VC ; Sheet6; VC 51-121; Sheet5; Sheet3; Tower Schedule; Visual Chart; L2 Vs Actual Progress Chart (2); Sheet4
TB 507 | TB 507 - MAIN | stretch | OK | OK |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Final Check In And Tack Welding | Final Check In And Tack Welding | 182 | 400kV Summery; Project Details; Check Survey ; Check Survey Status; Check Survey; Sheet8; Sheet2; Statutory Clearence; Crossing Proposal; Sheet1; VC 51-96; VC; ROW; June; Royalty; Sheet14; Sheet7; Erection ; Completion date; Sheet12; Foundation; Erection Compiled ; Earthing; ROW TRACKER; Final Check In And Tack Welding; Sheet10; Sheet11; Stringing Compiled ; Soil Investigation; Sheet9; VC ; Sheet6; VC 51-121; Sheet5; Sheet3; Tower Schedule; Visual Chart 1; Visual Chart; L2 Vs Actual Progress Chart; L2 Vs Actual Progress Chart (2); Sheet4
TB 507 | TB 507 | stretch | MISSING_SOURCE | MISSING_SOURCE | No dedicated stretch readiness sheet configured for this project line variant. | TB 507 - DPR - 2026-07-26.xlsx |  |  | 0
TB 507 | TB 507 - MAIN | manpower | PRESENT_WITH_VALUES | PRESENT_WITH_VALUES |  | TB 507 [MAIN] - DPR - 2026-07-26.xlsx | Stringing Compiled | Stringing Compiled | 37 | 400kV Summery; Project Details; Check Survey ; Check Survey Status; Check Survey; Sheet8; Sheet2; Statutory Clearence; Crossing Proposal; Sheet1; VC 51-96; VC; ROW; June; Royalty; Sheet14; Sheet7; Erection ; Completion date; Sheet12; Foundation; Erection Compiled ; Earthing; ROW TRACKER; Final Check In And Tack Welding; Sheet10; Sheet11; Stringing Compiled ; Soil Investigation; Sheet9; VC ; Sheet6; VC 51-121; Sheet5; Sheet3; Tower Schedule; Visual Chart 1; Visual Chart; L2 Vs Actual Progress Chart; L2 Vs Actual Progress Chart (2); Sheet4