## RawData
project_code | project_display | project_scope_key | line_name | line_name_source | section_label | report_date | source_file | source_sheet | configured_sheet | template_sheet | stringing_resolution_policy | header_row_number | source_row_number | activity_raw | activity_norm | quantity_loa | quantity_estimated_or_total | quantity_primary | cumulative_last_month | plan_for_month | progress_for_month | today_progress | cumulative_progress | balance_progress | gangs_working | remarks
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 14 | Soil Investigation | soil_investigation |  | 31 | 31 | 16 | 0 |  |  | 17 | 14
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 15 | Foundation | foundation |  | 480 | 480 | 154 | 30 | 8 | 0 | 162 | 318 | 3.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 16 | Earthing | earthing |  | 480 | 480 | 96 | 30 | 10 | 1 | 106 | 374
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 17 | Tower Erection | tower_erection |  | 480 | 480 | 52 | 35 | 17 | 2 | 69 | 411 | 4.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 18 | Tack welding | tack_welding |  | 480 | 480 | 0 | 35 | 0 | 0 | 0 | 480 | 2.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 19 | Stringing(Km) | stringing |  | 184.986 | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 165 | 150.833 | 150.833 | 150.833 | 0 | 0 |  | 150.833 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 165 | 150.833 | 150.833 | 149.21 | 1.623 | 0 |  | 149.21 | 1.623 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 13 | Detailed Survey Profiling (Km) | detailed_survey | 165 | 150.833 | 150.833 | 147.635 | 3.198 | 0 |  | 147.635 | 3.198 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 15 | Check Survey (Km) | check_survey | 165 | 150.833 | 150.833 | 119.962 | 25.288 | 0 |  | 119.962 | 30.871 | 0.0 | U/P
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 16 | Approved check survey ( Km) | check_survey | 165 | 150.833 | 150.833 | 102.416 | 36.061 | 0 |  | 102.416 | 48.417 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 17 | Soil Investigation (Nos) | soil_investigation | 165 | 147 | 147 | 147 | 0 | 0 |  | 147 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 18 | Excavation (Nos) | excavation | 564 | 505 | 505 | 274 | 80 | 20 |  | 294 | 211 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 19 | Foundation (Nos) | foundation | 564 | 505 | 505 | 264 | 80 | 13 |  | 277 | 214 | 14.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 20 | Earthing (Nos) | earthing | 564 | 505 | 505 | 185 | 87 | 17 |  | 202 | 303 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 21 | Tower Erection (Nos) | tower_erection | 564 | 505 | 505 | 87 | 70 | 18 |  | 105 | 391 | 9.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 22 | Tack Welding (Nos) | tack_welding | 564 | 505 | 505 | 9 | 55 | 0 |  | 9 | 496 | 1.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 23 | Stringing (Km) | stringing | 165 | 150.833 | 150.833 | 0 | 12 | 0 |  | 0 | 147.643 | 1.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 24 | OPGW Stringing (Km) | opgw_stringing | 165 | 150.833 | 150.833 | 0 | 0 | 0 |  | 0 | 150.833 | 0.0

## Diagnostics
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | TemplateSheet | TemplateApplied | TemplateChanges | FallbackNote | SectionsDetected | HeadersDetected | Rows | FilenameDate | InternalDate | DateQuality | Status | Reason
TA 602 - DPR - 2026-06-15.xlsx | TA 602 | 800kV HVDC TA-602 | 800kV HVDC TA-602 |  | filename | TA 602 Status | TRUE | C1:Activity->activity_raw; C2:Final Estimated Quantity->quantity_estimated_or_total; C4:Cumulative Progress till Last Month(May'26)->cumulative_last_month; C6:Plan for the Month->plan_for_month; C7:Today's Progress->today_progress; C8:Progress till Date for the Month->progress_for_month; C10:Completed till Date->cumulative_progress; C11:Balance Work->balance_progress; C13:Gangs at Present->gangs_working | XML scrub fallback used for sheet '800kV HVDC TA-602' | 1 | 1 | 6 | 2026-06-15 | 2026-06-16 | MISMATCH | OK
TB 412 - DPR - 2026-06-14.xlsx | TB 412 | TB-412 SUMMARY | TB-412 SUMMARY |  | filename | TB 412 Status | TRUE | C2:Activity->activity_raw; C3:Total Quantity->quantity_loa; C4:unnamed_col_4->quantity_estimated_or_total; C5:Cumm. Progress up to Last Month (May'26)->cumulative_last_month; C7:Target of Month for (June'2026)->plan_for_month; C8:Comp This Month (June'2026)->progress_for_month; C9:Cumulative Progress->cumulative_progress; C11:Balance->balance_progress; C12:No of Gangs->gangs_working; C13:Remark->remarks |  | 1 | 1 | 13 | 2026-06-14 | 2026-06-14 | MATCH | OK

## Issues
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | Issue | Reason

## Coverage
project_code | project_display | status | reason_code | reason | workbook | configured_sheet | resolved_sheet | rows | filename_date | internal_date | date_quality | available_sheets
TA 602 | TA 602 | OK | OK |  | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | 6 | 2026-06-15 | 2026-06-16 | MISMATCH | Project Details; DPR Sheet; 800kV HVDC TA-602; PPT-Erection Part; PPT _Statutory; PPT Supply; Supply Status; FDN; FDN Completed; PGCIL - KEC; Survey details 11-06-2026; Erection ; Erection Completed ; Erection Compiled; Stringing; Stringing Completed; Stringing Compiled; TA-602Visual Chart ; Visual chart; Pile Fdn; Crossing; Survey; Soil Inv.; Survey Anx
TB 412 | TB 412 | OK | OK |  | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | 13 | 2026-06-14 | 2026-06-14 | MATCH | TB-412 SUMMARY; Summary-; Survey Status; Sheet3; DPR Sheet ; WIP; GANG Mapping MAY-26 ; Soil Investigation; Sheet1; Progress 400kV QM; VC 400 KV QM; Progress 220KV TM; VC 220 TM; VC 220 SZ; ROW; 220 SZ Status; CS-220kV TM ; DS-220 KV TM; DS 400kV LI; DS 400 kV LO; Survey Report; FDN; Earthing Pending; Erection; Earthing; Earthing Balance; Statutary ; Power line Crossings