## ProdDailyExpandedSingles
Work Date | Start Date | Complete Date | Gang name | Tower Weight | Tower Type | Productivity | Project Code | Line Name | Project Name | Project Display | Project Scope Key | Location No. | Status
2025-03-01 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-02 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-03 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-04 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-05 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-06 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-07 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-08 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-09 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-10 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-11 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-12 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-13 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-14 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-15 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-16 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-17 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-18 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-19 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-20 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-21 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-22 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-23 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-24 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-25 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-26 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-27 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-28 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-29 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-30 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-03-31 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-01 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-02 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-03 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-04 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-05 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-06 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-07 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-08 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-09 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-10 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-11 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-12 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-13 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-14 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-15 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-16 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-17 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-18 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-19 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-20 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-21 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-22 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-23 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-24 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-25 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-26 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-27 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-28 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-29 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-04-30 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-01 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-02 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-03 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-04 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-05 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-06 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-07 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-08 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-09 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-10 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-11 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-12 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-13 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-14 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-15 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-16 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-17 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-18 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-19 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-20 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-21 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-22 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-23 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-24 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-25 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-26 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-27 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-28 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-29 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-30 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-05-31 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-01 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-02 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-03 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-04 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-05 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-06 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-07 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-08 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-09 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-10 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-11 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-12 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-13 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-14 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-15 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-16 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-17 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-18 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-19 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-20 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-21 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-22 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-23 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-24 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-25 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-26 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-27 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-28 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-29 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-06-30 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-01 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-02 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-03 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-04 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-05 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-06 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-07 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-08 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-09 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-10 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-11 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-12 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-13 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-14 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-15 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-16 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-17 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-18 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-19 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-20 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-21 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-22 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-23 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-24 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-25 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-26 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-27 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-28 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-29 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-30 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-07-31 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-01 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-02 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-03 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-04 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-05 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-06 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-07 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-08 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-09 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-10 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-11 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-12 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-13 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-14 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-15 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-16 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-17 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-18 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-19 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-20 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-21 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-22 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-23 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-24 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-25 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-26 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-27 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-28 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-29 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-30 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-08-31 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-01 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-02 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-03 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-04 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-05 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-06 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-07 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-08 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-09 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-10 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-11 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-12 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-13 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-14 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-15 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-16 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-17 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-18 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-19 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-20 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-21 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-22 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-23 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-24 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-25 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-26 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-27 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-28 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-29 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-09-30 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-01 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-02 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-03 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-04 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-05 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-06 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-07 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-08 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-09 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-10 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-11 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-12 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-13 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-14 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-15 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-16 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-17 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-18 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-19 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-20 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-21 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-22 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-23 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-24 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-25 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-26 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-27 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-28 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-29 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-30 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-10-31 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-01 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-02 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-03 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-04 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-05 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-06 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-07 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-08 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-09 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-10 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-11 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-12 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-13 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-14 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-15 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-16 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-17 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-18 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-19 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-20 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-21 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-22 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-23 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-24 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-25 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-26 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-27 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-28 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-29 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-11-30 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-01 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-02 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-03 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-04 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-05 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-06 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-07 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-08 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-09 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-10 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-11 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-12 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-13 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-14 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-15 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-16 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-17 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-18 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-19 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-20 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-21 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-22 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-23 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-24 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-25 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-26 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-27 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-28 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-29 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-30 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2025-12-31 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-01 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-02 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-03 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-04 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-05 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-06 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-07 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-08 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-09 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-10 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-11 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-12 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-13 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-14 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-15 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-16 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-01-16 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-17 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-01-17 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-18 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-01-18 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-19 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-01-19 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-20 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-01-20 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-21 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-01-21 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-22 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-01-22 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-23 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-01-23 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-24 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-01-24 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-25 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-01-25 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-26 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-01-26 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-27 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-01-27 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-28 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-01-28 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-29 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-01-29 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-30 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-01-30 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-01-31 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-01-31 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-01 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-01 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-02 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-02 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-03 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-03 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-04 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-04 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-05 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-05 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-06 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-06 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-07 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-07 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-08 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-08 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-09 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-09 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-10 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-10 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-11 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-11 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-12 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-12 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-13 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-13 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-14 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-14 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-15 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-15 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-16 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-16 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-17 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-17 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-18 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-18 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-18 | 2026-02-18 | 2026-02-22 | M S Ratani Devi | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/2 | C
2026-02-19 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-19 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-19 | 2026-02-18 | 2026-02-22 | M S Ratani Devi | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/2 | C
2026-02-20 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-20 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-20 | 2026-02-18 | 2026-02-22 | M S Ratani Devi | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/2 | C
2026-02-21 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-21 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-21 | 2026-02-18 | 2026-02-22 | M S Ratani Devi | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/2 | C
2026-02-22 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-22 | 2026-02-22 | 2026-02-28 | M S Jwala | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 130/1 | C
2026-02-22 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-22 | 2026-02-18 | 2026-02-22 | M S Ratani Devi | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/2 | C
2026-02-23 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-23 | 2026-02-22 | 2026-02-28 | M S Jwala | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 130/1 | C
2026-02-23 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-24 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-24 | 2026-02-22 | 2026-02-28 | M S Jwala | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 130/1 | C
2026-02-24 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-25 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-25 | 2026-02-22 | 2026-02-28 | M S Jwala | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 130/1 | C
2026-02-25 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-25 | 2026-02-25 | 2026-02-28 | M S Ratani Devi | 22.9237 | A+0 | 5.7309 | TA 602 |  | TA 602 | TA 602 | ta602 | 122/2 | C
2026-02-26 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-26 | 2026-02-22 | 2026-02-28 | M S Jwala | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 130/1 | C
2026-02-26 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-26 | 2026-02-25 | 2026-02-28 | M S Ratani Devi | 22.9237 | A+0 | 5.7309 | TA 602 |  | TA 602 | TA 602 | ta602 | 122/2 | C
2026-02-27 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-27 | 2026-02-22 | 2026-02-28 | M S Jwala | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 130/1 | C
2026-02-27 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-27 | 2026-02-25 | 2026-02-28 | M S Ratani Devi | 22.9237 | A+0 | 5.7309 | TA 602 |  | TA 602 | TA 602 | ta602 | 122/2 | C
2026-02-28 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-02-28 | 2026-02-22 | 2026-02-28 | M S Jwala | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 130/1 | C
2026-02-28 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-02-28 | 2026-02-25 | 2026-02-28 | M S Ratani Devi | 22.9237 | A+0 | 5.7309 | TA 602 |  | TA 602 | TA 602 | ta602 | 122/2 | C
2026-03-01 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-01 | 2026-03-01 | 2026-03-10 | M S Jwala | 24.041 | A+3 | 2.4041 | TA 602 |  | TA 602 | TA 602 | ta602 | 129A/3 | C
2026-03-01 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-03-01 | 2026-03-01 | 2026-03-11 | M S Ratani Devi | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/9 | C
2026-03-02 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-02 | 2026-03-01 | 2026-03-10 | M S Jwala | 24.041 | A+3 | 2.4041 | TA 602 |  | TA 602 | TA 602 | ta602 | 129A/3 | C
2026-03-02 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-03-02 | 2026-03-01 | 2026-03-11 | M S Ratani Devi | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/9 | C
2026-03-03 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-03 | 2026-03-01 | 2026-03-10 | M S Jwala | 24.041 | A+3 | 2.4041 | TA 602 |  | TA 602 | TA 602 | ta602 | 129A/3 | C
2026-03-03 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-03-03 | 2026-03-01 | 2026-03-11 | M S Ratani Devi | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/9 | C
2026-03-03 | 2026-03-03 | 2026-03-07 | M S Ratani Devi | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/10 | C
2026-03-04 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-04 | 2026-03-01 | 2026-03-10 | M S Jwala | 24.041 | A+3 | 2.4041 | TA 602 |  | TA 602 | TA 602 | ta602 | 129A/3 | C
2026-03-04 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-03-04 | 2026-03-01 | 2026-03-11 | M S Ratani Devi | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/9 | C
2026-03-04 | 2026-03-03 | 2026-03-07 | M S Ratani Devi | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/10 | C
2026-03-05 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-05 | 2026-03-01 | 2026-03-10 | M S Jwala | 24.041 | A+3 | 2.4041 | TA 602 |  | TA 602 | TA 602 | ta602 | 129A/3 | C
2026-03-05 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-03-05 | 2026-03-01 | 2026-03-11 | M S Ratani Devi | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/9 | C
2026-03-05 | 2026-03-03 | 2026-03-07 | M S Ratani Devi | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/10 | C
2026-03-06 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-06 | 2026-03-01 | 2026-03-10 | M S Jwala | 24.041 | A+3 | 2.4041 | TA 602 |  | TA 602 | TA 602 | ta602 | 129A/3 | C
2026-03-06 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-03-06 | 2026-03-01 | 2026-03-11 | M S Ratani Devi | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/9 | C
2026-03-06 | 2026-03-03 | 2026-03-07 | M S Ratani Devi | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/10 | C
2026-03-07 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-07 | 2026-03-01 | 2026-03-10 | M S Jwala | 24.041 | A+3 | 2.4041 | TA 602 |  | TA 602 | TA 602 | ta602 | 129A/3 | C
2026-03-07 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-03-07 | 2026-03-01 | 2026-03-11 | M S Ratani Devi | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/9 | C
2026-03-07 | 2026-03-03 | 2026-03-07 | M S Ratani Devi | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/10 | C
2026-03-08 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-08 | 2026-03-01 | 2026-03-10 | M S Jwala | 24.041 | A+3 | 2.4041 | TA 602 |  | TA 602 | TA 602 | ta602 | 129A/3 | C
2026-03-08 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-03-08 | 2026-03-01 | 2026-03-11 | M S Ratani Devi | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/9 | C
2026-03-09 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-09 | 2026-03-01 | 2026-03-10 | M S Jwala | 24.041 | A+3 | 2.4041 | TA 602 |  | TA 602 | TA 602 | ta602 | 129A/3 | C
2026-03-09 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-03-09 | 2026-03-01 | 2026-03-11 | M S Ratani Devi | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/9 | C
2026-03-10 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-10 | 2026-03-01 | 2026-03-10 | M S Jwala | 24.041 | A+3 | 2.4041 | TA 602 |  | TA 602 | TA 602 | ta602 | 129A/3 | C
2026-03-10 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-03-10 | 2026-03-01 | 2026-03-11 | M S Ratani Devi | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/9 | C
2026-03-11 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-11 | 2026-03-11 | 2026-03-14 | M S Jwala | 26.7642 | A+6 | 6.691 | TA 602 |  | TA 602 | TA 602 | ta602 | 129A/4 | C
2026-03-11 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-03-11 | 2026-03-01 | 2026-03-11 | M S Ratani Devi | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/9 | C
2026-03-12 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-12 | 2026-03-11 | 2026-03-14 | M S Jwala | 26.7642 | A+6 | 6.691 | TA 602 |  | TA 602 | TA 602 | ta602 | 129A/4 | C
2026-03-12 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-03-13 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-13 | 2026-03-11 | 2026-03-14 | M S Jwala | 26.7642 | A+6 | 6.691 | TA 602 |  | TA 602 | TA 602 | ta602 | 129A/4 | C
2026-03-13 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-03-14 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-14 | 2026-03-11 | 2026-03-14 | M S Jwala | 26.7642 | A+6 | 6.691 | TA 602 |  | TA 602 | TA 602 | ta602 | 129A/4 | C
2026-03-14 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-03-15 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-15 | 2026-03-15 | 2026-03-19 | M S Jwala | 26.7642 | A+6 | 5.3528 | TA 602 |  | TA 602 | TA 602 | ta602 | 130/2 | C
2026-03-15 | 2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/5 | C
2026-03-15 | 2026-03-15 | 2026-03-19 | M S Ratani Devi | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/4 | C
2026-03-16 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-16 | 2026-03-15 | 2026-03-19 | M S Jwala | 26.7642 | A+6 | 5.3528 | TA 602 |  | TA 602 | TA 602 | ta602 | 130/2 | C
2026-03-16 | 2026-03-15 | 2026-03-19 | M S Ratani Devi | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/4 | C
2026-03-17 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-17 | 2026-03-15 | 2026-03-19 | M S Jwala | 26.7642 | A+6 | 5.3528 | TA 602 |  | TA 602 | TA 602 | ta602 | 130/2 | C
2026-03-17 | 2026-03-15 | 2026-03-19 | M S Ratani Devi | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/4 | C
2026-03-18 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-18 | 2026-03-15 | 2026-03-19 | M S Jwala | 26.7642 | A+6 | 5.3528 | TA 602 |  | TA 602 | TA 602 | ta602 | 130/2 | C
2026-03-18 | 2026-03-15 | 2026-03-19 | M S Ratani Devi | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/4 | C
2026-03-19 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-19 | 2026-03-15 | 2026-03-19 | M S Jwala | 26.7642 | A+6 | 5.3528 | TA 602 |  | TA 602 | TA 602 | ta602 | 130/2 | C
2026-03-19 | 2026-03-19 | 2026-03-22 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 130/3 | C
2026-03-19 | 2026-03-15 | 2026-03-19 | M S Ratani Devi | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/4 | C
2026-03-19 | 2026-03-19 | 2026-03-23 | M S Ratani Devi | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/3 | C
2026-03-20 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-20 | 2026-03-19 | 2026-03-22 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 130/3 | C
2026-03-20 | 2026-03-19 | 2026-03-23 | M S Ratani Devi | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/3 | C
2026-03-21 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-21 | 2026-03-19 | 2026-03-22 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 130/3 | C
2026-03-21 | 2026-03-19 | 2026-03-23 | M S Ratani Devi | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/3 | C
2026-03-22 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-22 | 2026-03-19 | 2026-03-22 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 130/3 | C
2026-03-22 | 2026-03-19 | 2026-03-23 | M S Ratani Devi | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/3 | C
2026-03-23 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-23 | 2026-03-23 | 2026-03-27 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/2 | C
2026-03-23 | 2026-03-19 | 2026-03-23 | M S Ratani Devi | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/3 | C
2026-03-23 | 2026-03-23 | 2026-03-28 | M S Ratani Devi | 26.7642 | A+6 | 4.4607 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/3 | C
2026-03-24 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-24 | 2026-03-23 | 2026-03-27 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/2 | C
2026-03-24 | 2026-03-23 | 2026-03-28 | M S Ratani Devi | 26.7642 | A+6 | 4.4607 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/3 | C
2026-03-25 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-25 | 2026-03-23 | 2026-03-27 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/2 | C
2026-03-25 | 2026-03-23 | 2026-03-28 | M S Ratani Devi | 26.7642 | A+6 | 4.4607 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/3 | C
2026-03-26 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-26 | 2026-03-23 | 2026-03-27 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/2 | C
2026-03-26 | 2026-03-23 | 2026-03-28 | M S Ratani Devi | 26.7642 | A+6 | 4.4607 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/3 | C
2026-03-27 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-27 | 2026-03-23 | 2026-03-27 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/2 | C
2026-03-27 | 2026-03-27 | 2026-03-30 | M S Jwala | 26.7642 | A+6 | 6.691 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/3 | C
2026-03-27 | 2026-03-23 | 2026-03-28 | M S Ratani Devi | 26.7642 | A+6 | 4.4607 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/3 | C
2026-03-28 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-28 | 2026-03-27 | 2026-03-30 | M S Jwala | 26.7642 | A+6 | 6.691 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/3 | C
2026-03-28 | 2026-03-23 | 2026-03-28 | M S Ratani Devi | 26.7642 | A+6 | 4.4607 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/3 | C
2026-03-28 | 2026-03-28 | 2026-04-02 | M S Ratani Devi | 24.041 | A+3 | 4.0068 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/4 | C
2026-03-29 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-29 | 2026-03-27 | 2026-03-30 | M S Jwala | 26.7642 | A+6 | 6.691 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/3 | C
2026-03-29 | 2026-03-28 | 2026-04-02 | M S Ratani Devi | 24.041 | A+3 | 4.0068 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/4 | C
2026-03-30 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-30 | 2026-03-27 | 2026-03-30 | M S Jwala | 26.7642 | A+6 | 6.691 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/3 | C
2026-03-30 | 2026-03-28 | 2026-04-02 | M S Ratani Devi | 24.041 | A+3 | 4.0068 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/4 | C
2026-03-31 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-03-31 | 2026-03-31 | 2026-04-03 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/4 | C
2026-03-31 | 2026-03-28 | 2026-04-02 | M S Ratani Devi | 24.041 | A+3 | 4.0068 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/4 | C
2026-04-01 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-01 | 2026-03-31 | 2026-04-03 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/4 | C
2026-04-01 | 2026-03-28 | 2026-04-02 | M S Ratani Devi | 24.041 | A+3 | 4.0068 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/4 | C
2026-04-02 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-02 | 2026-03-31 | 2026-04-03 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/4 | C
2026-04-02 | 2026-03-28 | 2026-04-02 | M S Ratani Devi | 24.041 | A+3 | 4.0068 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/4 | C
2026-04-03 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-03 | 2026-03-31 | 2026-04-03 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/4 | C
2026-04-04 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-04 | 2026-04-04 | 2026-04-07 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/8 | C
2026-04-05 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-05 | 2026-04-04 | 2026-04-07 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/8 | C
2026-04-06 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-06 | 2026-04-04 | 2026-04-07 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/8 | C
2026-04-07 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-07 | 2026-04-04 | 2026-04-07 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/8 | C
2026-04-07 | 2026-04-07 | 2026-04-11 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/9 | C
2026-04-08 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-08 | 2026-04-07 | 2026-04-11 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/9 | C
2026-04-09 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-09 | 2026-04-07 | 2026-04-11 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/9 | C
2026-04-10 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-10 | 2026-04-07 | 2026-04-11 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/9 | C
2026-04-11 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-11 | 2026-04-07 | 2026-04-11 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/9 | C
2026-04-12 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-12 | 2026-04-12 | 2026-04-15 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/7 | C
2026-04-13 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-13 | 2026-04-12 | 2026-04-15 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/7 | C
2026-04-14 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-14 | 2026-04-12 | 2026-04-15 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/7 | C
2026-04-15 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-15 | 2026-04-12 | 2026-04-15 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/7 | C
2026-04-15 | 2026-04-15 | 2026-04-19 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/5 | C
2026-04-16 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-16 | 2026-04-15 | 2026-04-19 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/5 | C
2026-04-17 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-17 | 2026-04-15 | 2026-04-19 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/5 | C
2026-04-18 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-18 | 2026-04-15 | 2026-04-19 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/5 | C
2026-04-19 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-19 | 2026-04-15 | 2026-04-19 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 134/5 | C
2026-04-19 | 2026-04-19 | 2026-04-23 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/2 | C
2026-04-20 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-20 | 2026-04-19 | 2026-04-23 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/2 | C
2026-04-21 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-21 | 2026-04-19 | 2026-04-23 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/2 | C
2026-04-22 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-22 | 2026-04-19 | 2026-04-23 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/2 | C
2026-04-23 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-23 | 2026-04-19 | 2026-04-23 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/2 | C
2026-04-24 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-24 | 2026-04-24 | 2026-04-28 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/1 | C
2026-04-25 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-25 | 2026-04-24 | 2026-04-28 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/1 | C
2026-04-26 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-26 | 2026-04-24 | 2026-04-28 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/1 | C
2026-04-27 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-27 | 2026-04-24 | 2026-04-28 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/1 | C
2026-04-28 | 2026-04-28 | 2026-05-04 | M S Amrendra Prasad | 24.041 | A+3 | 3.4344 | TA 602 |  | TA 602 | TA 602 | ta602 | 116/2 | C
2026-04-28 | 2026-04-28 | 2026-05-04 | M S Aravali Infrastructure | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 102/7 | C
2026-04-28 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-28 | 2026-04-28 | 2026-05-04 | M S Gagan Entp | 26.7642 | A+6 | 3.8235 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/2 | C
2026-04-28 | 2026-04-24 | 2026-04-28 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/1 | C
2026-04-28 | 2026-04-28 | 2026-05-02 | M S Jwala Singh | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/3 | C
2026-04-29 | 2026-04-28 | 2026-05-04 | M S Amrendra Prasad | 24.041 | A+3 | 3.4344 | TA 602 |  | TA 602 | TA 602 | ta602 | 116/2 | C
2026-04-29 | 2026-04-28 | 2026-05-04 | M S Aravali Infrastructure | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 102/7 | C
2026-04-29 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-29 | 2026-04-28 | 2026-05-04 | M S Gagan Entp | 26.7642 | A+6 | 3.8235 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/2 | C
2026-04-29 | 2026-04-28 | 2026-05-02 | M S Jwala Singh | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/3 | C
2026-04-30 | 2026-04-28 | 2026-05-04 | M S Amrendra Prasad | 24.041 | A+3 | 3.4344 | TA 602 |  | TA 602 | TA 602 | ta602 | 116/2 | C
2026-04-30 | 2026-04-28 | 2026-05-04 | M S Aravali Infrastructure | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 102/7 | C
2026-04-30 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-04-30 | 2026-04-28 | 2026-05-04 | M S Gagan Entp | 26.7642 | A+6 | 3.8235 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/2 | C
2026-04-30 | 2026-04-28 | 2026-05-02 | M S Jwala Singh | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/3 | C
2026-05-01 | 2026-04-28 | 2026-05-04 | M S Amrendra Prasad | 24.041 | A+3 | 3.4344 | TA 602 |  | TA 602 | TA 602 | ta602 | 116/2 | C
2026-05-01 | 2026-04-28 | 2026-05-04 | M S Aravali Infrastructure | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 102/7 | C
2026-05-01 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-01 | 2026-04-28 | 2026-05-04 | M S Gagan Entp | 26.7642 | A+6 | 3.8235 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/2 | C
2026-05-01 | 2026-04-28 | 2026-05-02 | M S Jwala Singh | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/3 | C
2026-05-02 | 2026-04-28 | 2026-05-04 | M S Amrendra Prasad | 24.041 | A+3 | 3.4344 | TA 602 |  | TA 602 | TA 602 | ta602 | 116/2 | C
2026-05-02 | 2026-04-28 | 2026-05-04 | M S Aravali Infrastructure | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 102/7 | C
2026-05-02 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-02 | 2026-04-28 | 2026-05-04 | M S Gagan Entp | 26.7642 | A+6 | 3.8235 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/2 | C
2026-05-02 | 2026-04-28 | 2026-05-02 | M S Jwala Singh | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/3 | C
2026-05-02 | 2026-05-02 | 2026-05-04 | M S Jwala Singh | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/4 | C
2026-05-03 | 2026-04-28 | 2026-05-04 | M S Amrendra Prasad | 24.041 | A+3 | 3.4344 | TA 602 |  | TA 602 | TA 602 | ta602 | 116/2 | C
2026-05-03 | 2026-04-28 | 2026-05-04 | M S Aravali Infrastructure | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 102/7 | C
2026-05-03 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-03 | 2026-04-28 | 2026-05-04 | M S Gagan Entp | 26.7642 | A+6 | 3.8235 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/2 | C
2026-05-03 | 2026-05-02 | 2026-05-04 | M S Jwala Singh | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/4 | C
2026-05-03 | 2026-05-03 | 2026-05-10 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/1 | C
2026-05-04 | 2026-04-28 | 2026-05-04 | M S Amrendra Prasad | 24.041 | A+3 | 3.4344 | TA 602 |  | TA 602 | TA 602 | ta602 | 116/2 | C
2026-05-04 | 2026-05-04 | 2026-05-09 | M S Amrendra Prasad | 24.041 | A+3 | 4.0068 | TA 602 |  | TA 602 | TA 602 | ta602 | 116/1 | C
2026-05-04 | 2026-04-28 | 2026-05-04 | M S Aravali Infrastructure | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 102/7 | C
2026-05-04 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-04 | 2026-04-28 | 2026-05-04 | M S Gagan Entp | 26.7642 | A+6 | 3.8235 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/2 | C
2026-05-04 | 2026-05-04 | 2026-05-08 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/1 | C
2026-05-04 | 2026-05-02 | 2026-05-04 | M S Jwala Singh | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/4 | C
2026-05-04 | 2026-05-04 | 2026-05-08 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/5 | C
2026-05-04 | 2026-05-03 | 2026-05-10 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/1 | C
2026-05-05 | 2026-05-04 | 2026-05-09 | M S Amrendra Prasad | 24.041 | A+3 | 4.0068 | TA 602 |  | TA 602 | TA 602 | ta602 | 116/1 | C
2026-05-05 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-05 | 2026-05-04 | 2026-05-08 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/1 | C
2026-05-05 | 2026-05-04 | 2026-05-08 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/5 | C
2026-05-05 | 2026-05-03 | 2026-05-10 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/1 | C
2026-05-06 | 2026-05-04 | 2026-05-09 | M S Amrendra Prasad | 24.041 | A+3 | 4.0068 | TA 602 |  | TA 602 | TA 602 | ta602 | 116/1 | C
2026-05-06 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-06 | 2026-05-04 | 2026-05-08 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/1 | C
2026-05-06 | 2026-05-04 | 2026-05-08 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/5 | C
2026-05-06 | 2026-05-03 | 2026-05-10 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/1 | C
2026-05-07 | 2026-05-04 | 2026-05-09 | M S Amrendra Prasad | 24.041 | A+3 | 4.0068 | TA 602 |  | TA 602 | TA 602 | ta602 | 116/1 | C
2026-05-07 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-07 | 2026-05-04 | 2026-05-08 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/1 | C
2026-05-07 | 2026-05-04 | 2026-05-08 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/5 | C
2026-05-07 | 2026-05-03 | 2026-05-10 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/1 | C
2026-05-08 | 2026-05-04 | 2026-05-09 | M S Amrendra Prasad | 24.041 | A+3 | 4.0068 | TA 602 |  | TA 602 | TA 602 | ta602 | 116/1 | C
2026-05-08 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-08 | 2026-05-04 | 2026-05-08 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/1 | C
2026-05-08 | 2026-05-08 | 2026-05-12 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/4 | C
2026-05-08 | 2026-05-04 | 2026-05-08 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/5 | C
2026-05-08 | 2026-05-08 | 2026-05-12 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 139/2 | C
2026-05-08 | 2026-05-03 | 2026-05-10 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/1 | C
2026-05-09 | 2026-05-04 | 2026-05-09 | M S Amrendra Prasad | 24.041 | A+3 | 4.0068 | TA 602 |  | TA 602 | TA 602 | ta602 | 116/1 | C
2026-05-09 | 2026-05-09 | 2026-05-14 | M S Amrendra Prasad | 22.9237 | A+0 | 3.8206 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/1 | C
2026-05-09 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-09 | 2026-05-08 | 2026-05-12 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/4 | C
2026-05-09 | 2026-05-08 | 2026-05-12 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 139/2 | C
2026-05-09 | 2026-05-09 | 2026-05-15 | M S Jwala Singh | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 139/5 | C
2026-05-09 | 2026-05-03 | 2026-05-10 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/1 | C
2026-05-10 | 2026-05-09 | 2026-05-14 | M S Amrendra Prasad | 22.9237 | A+0 | 3.8206 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/1 | C
2026-05-10 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-10 | 2026-05-08 | 2026-05-12 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/4 | C
2026-05-10 | 2026-05-08 | 2026-05-12 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 139/2 | C
2026-05-10 | 2026-05-09 | 2026-05-15 | M S Jwala Singh | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 139/5 | C
2026-05-10 | 2026-05-03 | 2026-05-10 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/1 | C
2026-05-10 | 2026-05-10 | 2026-05-16 | M S Mukesh Kumar Verma | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/2 | C
2026-05-11 | 2026-05-09 | 2026-05-14 | M S Amrendra Prasad | 22.9237 | A+0 | 3.8206 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/1 | C
2026-05-11 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-11 | 2026-05-08 | 2026-05-12 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/4 | C
2026-05-11 | 2026-05-08 | 2026-05-12 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 139/2 | C
2026-05-11 | 2026-05-09 | 2026-05-15 | M S Jwala Singh | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 139/5 | C
2026-05-11 | 2026-05-10 | 2026-05-16 | M S Mukesh Kumar Verma | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/2 | C
2026-05-12 | 2026-05-09 | 2026-05-14 | M S Amrendra Prasad | 22.9237 | A+0 | 3.8206 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/1 | C
2026-05-12 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-12 | 2026-05-08 | 2026-05-12 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/4 | C
2026-05-12 | 2026-05-12 | 2026-05-16 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/7 | C
2026-05-12 | 2026-05-08 | 2026-05-12 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 139/2 | C
2026-05-12 | 2026-05-09 | 2026-05-15 | M S Jwala Singh | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 139/5 | C
2026-05-12 | 2026-05-10 | 2026-05-16 | M S Mukesh Kumar Verma | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/2 | C
2026-05-13 | 2026-05-09 | 2026-05-14 | M S Amrendra Prasad | 22.9237 | A+0 | 3.8206 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/1 | C
2026-05-13 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-13 | 2026-05-12 | 2026-05-16 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/7 | C
2026-05-13 | 2026-05-09 | 2026-05-15 | M S Jwala Singh | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 139/5 | C
2026-05-13 | 2026-05-10 | 2026-05-16 | M S Mukesh Kumar Verma | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/2 | C
2026-05-14 | 2026-05-09 | 2026-05-14 | M S Amrendra Prasad | 22.9237 | A+0 | 3.8206 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/1 | C
2026-05-14 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-14 | 2026-05-12 | 2026-05-16 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/7 | C
2026-05-14 | 2026-05-09 | 2026-05-15 | M S Jwala Singh | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 139/5 | C
2026-05-14 | 2026-05-10 | 2026-05-16 | M S Mukesh Kumar Verma | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/2 | C
2026-05-15 | 2026-05-15 | 2026-05-18 | M S Amrendra Prasad | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/2 | C
2026-05-15 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-15 | 2026-05-12 | 2026-05-16 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/7 | C
2026-05-15 | 2026-05-09 | 2026-05-15 | M S Jwala Singh | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 139/5 | C
2026-05-15 | 2026-05-10 | 2026-05-16 | M S Mukesh Kumar Verma | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/2 | C
2026-05-16 | 2026-05-15 | 2026-05-18 | M S Amrendra Prasad | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/2 | C
2026-05-16 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-16 | 2026-05-12 | 2026-05-16 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/7 | C
2026-05-16 | 2026-05-16 | 2026-05-18 | M S Jwala Singh | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/8 | C
2026-05-16 | 2026-05-10 | 2026-05-16 | M S Mukesh Kumar Verma | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/2 | C
2026-05-17 | 2026-05-15 | 2026-05-18 | M S Amrendra Prasad | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/2 | C
2026-05-17 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-17 | 2026-05-16 | 2026-05-18 | M S Jwala Singh | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/8 | C
2026-05-17 | 2026-05-17 | 2026-05-21 | M S Mukesh Kumar Verma | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/5 | C
2026-05-18 | 2026-05-15 | 2026-05-18 | M S Amrendra Prasad | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/2 | C
2026-05-18 | 2026-05-18 | 2026-05-22 | M S Amrendra Prasad | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/3 | C
2026-05-18 | 2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/6 | C
2026-05-18 | 2026-05-18 | 2026-05-20 | M S Gagan Entp | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/5 | C
2026-05-18 | 2026-05-16 | 2026-05-18 | M S Jwala Singh | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | 136/8 | C
2026-05-18 | 2026-05-18 | 2026-05-21 | M S Jwala Singh | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 139/1 | C
2026-05-18 | 2026-05-17 | 2026-05-21 | M S Mukesh Kumar Verma | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/5 | C
2026-05-19 | 2026-05-18 | 2026-05-22 | M S Amrendra Prasad | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/3 | C
2026-05-19 | 2026-05-18 | 2026-05-20 | M S Gagan Entp | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/5 | C
2026-05-19 | 2026-05-18 | 2026-05-21 | M S Jwala Singh | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 139/1 | C
2026-05-19 | 2026-05-17 | 2026-05-21 | M S Mukesh Kumar Verma | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/5 | C
2026-05-20 | 2026-05-18 | 2026-05-22 | M S Amrendra Prasad | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/3 | C
2026-05-20 | 2026-05-18 | 2026-05-20 | M S Gagan Entp | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/5 | C
2026-05-20 | 2026-05-18 | 2026-05-21 | M S Jwala Singh | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 139/1 | C
2026-05-20 | 2026-05-17 | 2026-05-21 | M S Mukesh Kumar Verma | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/5 | C
2026-05-21 | 2026-05-18 | 2026-05-22 | M S Amrendra Prasad | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/3 | C
2026-05-21 | 2026-05-21 | 2026-05-23 | M S Gagan Entp | 26.7642 | A+6 | 8.9214 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/5 | C
2026-05-21 | 2026-05-18 | 2026-05-21 | M S Jwala Singh | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | 139/1 | C
2026-05-21 | 2026-05-17 | 2026-05-21 | M S Mukesh Kumar Verma | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/5 | C
2026-05-21 | 2026-05-21 | 2026-05-28 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/6 | C
2026-05-21 | 2026-05-21 | 2026-05-31 | M S Mukesh Kumar Verma | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/7 | C
2026-05-22 | 2026-05-18 | 2026-05-22 | M S Amrendra Prasad | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/3 | C
2026-05-22 | 2026-05-21 | 2026-05-23 | M S Gagan Entp | 26.7642 | A+6 | 8.9214 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/5 | C
2026-05-22 | 2026-05-21 | 2026-05-28 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/6 | C
2026-05-22 | 2026-05-21 | 2026-05-31 | M S Mukesh Kumar Verma | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/7 | C
2026-05-23 | 2026-05-23 | 2026-05-26 | M S Amrendra Prasad | 22.9237 | A+0 | 5.7309 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/4 | C
2026-05-23 | 2026-05-21 | 2026-05-23 | M S Gagan Entp | 26.7642 | A+6 | 8.9214 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/5 | C
2026-05-23 | 2026-05-23 | 2026-05-25 | M S Gagan Entp | 24.041 | A+3 | 8.0137 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/1 | C
2026-05-23 | 2026-05-21 | 2026-05-28 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/6 | C
2026-05-23 | 2026-05-21 | 2026-05-31 | M S Mukesh Kumar Verma | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/7 | C
2026-05-24 | 2026-05-23 | 2026-05-26 | M S Amrendra Prasad | 22.9237 | A+0 | 5.7309 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/4 | C
2026-05-24 | 2026-05-23 | 2026-05-25 | M S Gagan Entp | 24.041 | A+3 | 8.0137 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/1 | C
2026-05-24 | 2026-05-21 | 2026-05-28 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/6 | C
2026-05-24 | 2026-05-21 | 2026-05-31 | M S Mukesh Kumar Verma | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/7 | C
2026-05-25 | 2026-05-23 | 2026-05-26 | M S Amrendra Prasad | 22.9237 | A+0 | 5.7309 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/4 | C
2026-05-25 | 2026-05-23 | 2026-05-25 | M S Gagan Entp | 24.041 | A+3 | 8.0137 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/1 | C
2026-05-25 | 2026-05-21 | 2026-05-28 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/6 | C
2026-05-25 | 2026-05-21 | 2026-05-31 | M S Mukesh Kumar Verma | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/7 | C
2026-05-26 | 2026-05-23 | 2026-05-26 | M S Amrendra Prasad | 22.9237 | A+0 | 5.7309 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/4 | C
2026-05-26 | 2026-05-26 | 2026-05-29 | M S Gagan Entp | 31.6671 | B2+3 | 7.9168 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/0 | C
2026-05-26 | 2026-05-21 | 2026-05-28 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/6 | C
2026-05-26 | 2026-05-21 | 2026-05-31 | M S Mukesh Kumar Verma | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/7 | C
2026-05-27 | 2026-05-27 | 2026-06-01 | M S Amrendra Prasad | 26.7642 | A+6 | 4.4607 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/5 | C
2026-05-27 | 2026-05-26 | 2026-05-29 | M S Gagan Entp | 31.6671 | B2+3 | 7.9168 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/0 | C
2026-05-27 | 2026-05-21 | 2026-05-28 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/6 | C
2026-05-27 | 2026-05-21 | 2026-05-31 | M S Mukesh Kumar Verma | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/7 | C
2026-05-28 | 2026-05-27 | 2026-06-01 | M S Amrendra Prasad | 26.7642 | A+6 | 4.4607 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/5 | C
2026-05-28 | 2026-05-26 | 2026-05-29 | M S Gagan Entp | 31.6671 | B2+3 | 7.9168 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/0 | C
2026-05-28 | 2026-05-21 | 2026-05-28 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/6 | C
2026-05-28 | 2026-05-21 | 2026-05-31 | M S Mukesh Kumar Verma | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/7 | C
2026-05-29 | 2026-05-27 | 2026-06-01 | M S Amrendra Prasad | 26.7642 | A+6 | 4.4607 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/5 | C
2026-05-29 | 2026-05-26 | 2026-05-29 | M S Gagan Entp | 31.6671 | B2+3 | 7.9168 | TA 602 |  | TA 602 | TA 602 | ta602 | 125/0 | C
2026-05-29 | 2026-05-21 | 2026-05-31 | M S Mukesh Kumar Verma | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/7 | C
2026-05-30 | 2026-05-27 | 2026-06-01 | M S Amrendra Prasad | 26.7642 | A+6 | 4.4607 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/5 | C
2026-05-30 | 2026-05-30 | 2026-06-02 | M S Gagan Entp | 27.9651 | A+9 | 6.9913 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/3 | C
2026-05-30 | 2026-05-30 | 2026-06-03 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 127/3 | C
2026-05-30 | 2026-05-21 | 2026-05-31 | M S Mukesh Kumar Verma | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/7 | C
2026-05-31 | 2026-05-27 | 2026-06-01 | M S Amrendra Prasad | 26.7642 | A+6 | 4.4607 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/5 | C
2026-05-31 | 2026-05-30 | 2026-06-02 | M S Gagan Entp | 27.9651 | A+9 | 6.9913 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/3 | C
2026-05-31 | 2026-05-30 | 2026-06-03 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 127/3 | C
2026-05-31 | 2026-05-21 | 2026-05-31 | M S Mukesh Kumar Verma | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | 109/7 | C
2026-05-31 | 2026-05-31 | 2026-06-08 | M S Mukesh Kumar Verma | 27.9651 | A+9 | 3.1072 | TA 602 |  | TA 602 | TA 602 | ta602 | 108/1 | C
2026-06-01 | 2026-05-27 | 2026-06-01 | M S Amrendra Prasad | 26.7642 | A+6 | 4.4607 | TA 602 |  | TA 602 | TA 602 | ta602 | 111/5 | C
2026-06-01 | 2026-06-01 | 2026-06-07 | M S Amrendra Prasad | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 110/3 | C
2026-06-01 | 2026-05-30 | 2026-06-02 | M S Gagan Entp | 27.9651 | A+9 | 6.9913 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/3 | C
2026-06-01 | 2026-05-30 | 2026-06-03 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 127/3 | C
2026-06-01 | 2026-05-31 | 2026-06-08 | M S Mukesh Kumar Verma | 27.9651 | A+9 | 3.1072 | TA 602 |  | TA 602 | TA 602 | ta602 | 108/1 | C
2026-06-02 | 2026-06-01 | 2026-06-07 | M S Amrendra Prasad | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 110/3 | C
2026-06-02 | 2026-05-30 | 2026-06-02 | M S Gagan Entp | 27.9651 | A+9 | 6.9913 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/3 | C
2026-06-02 | 2026-06-02 | 2026-06-03 | M S Gagan Entp | 22.9237 | A+0 | 11.4619 | TA 602 |  | TA 602 | TA 602 | ta602 | 123/1 | C
2026-06-02 | 2026-05-30 | 2026-06-03 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 127/3 | C
2026-06-02 | 2026-05-31 | 2026-06-08 | M S Mukesh Kumar Verma | 27.9651 | A+9 | 3.1072 | TA 602 |  | TA 602 | TA 602 | ta602 | 108/1 | C
2026-06-03 | 2026-06-01 | 2026-06-07 | M S Amrendra Prasad | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 110/3 | C
2026-06-03 | 2026-06-02 | 2026-06-03 | M S Gagan Entp | 22.9237 | A+0 | 11.4619 | TA 602 |  | TA 602 | TA 602 | ta602 | 123/1 | C
2026-06-03 | 2026-06-03 | 2026-06-06 | M S Gagan Entp | 26.7642 | A+6 | 6.691 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/2 | C
2026-06-03 | 2026-05-30 | 2026-06-03 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 127/3 | C
2026-06-03 | 2026-06-03 | 2026-06-07 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 127/1 | C
2026-06-03 | 2026-05-31 | 2026-06-08 | M S Mukesh Kumar Verma | 27.9651 | A+9 | 3.1072 | TA 602 |  | TA 602 | TA 602 | ta602 | 108/1 | C
2026-06-04 | 2026-06-01 | 2026-06-07 | M S Amrendra Prasad | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 110/3 | C
2026-06-04 | 2026-06-03 | 2026-06-06 | M S Gagan Entp | 26.7642 | A+6 | 6.691 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/2 | C
2026-06-04 | 2026-06-03 | 2026-06-07 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 127/1 | C
2026-06-04 | 2026-05-31 | 2026-06-08 | M S Mukesh Kumar Verma | 27.9651 | A+9 | 3.1072 | TA 602 |  | TA 602 | TA 602 | ta602 | 108/1 | C
2026-06-05 | 2026-06-01 | 2026-06-07 | M S Amrendra Prasad | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 110/3 | C
2026-06-05 | 2026-06-03 | 2026-06-06 | M S Gagan Entp | 26.7642 | A+6 | 6.691 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/2 | C
2026-06-05 | 2026-06-03 | 2026-06-07 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 127/1 | C
2026-06-05 | 2026-05-31 | 2026-06-08 | M S Mukesh Kumar Verma | 27.9651 | A+9 | 3.1072 | TA 602 |  | TA 602 | TA 602 | ta602 | 108/1 | C
2026-06-06 | 2026-06-01 | 2026-06-07 | M S Amrendra Prasad | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 110/3 | C
2026-06-06 | 2026-06-03 | 2026-06-06 | M S Gagan Entp | 26.7642 | A+6 | 6.691 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/2 | C
2026-06-06 | 2026-06-06 | 2026-06-07 | M S Gagan Entp 2 | 24.041 | A+3 | 12.0205 | TA 602 |  | TA 602 | TA 602 | ta602 | 123/2
2026-06-06 | 2026-06-03 | 2026-06-07 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 127/1 | C
2026-06-06 | 2026-05-31 | 2026-06-08 | M S Mukesh Kumar Verma | 27.9651 | A+9 | 3.1072 | TA 602 |  | TA 602 | TA 602 | ta602 | 108/1 | C
2026-06-07 | 2026-06-01 | 2026-06-07 | M S Amrendra Prasad | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | 110/3 | C
2026-06-07 | 2026-06-06 | 2026-06-07 | M S Gagan Entp 2 | 24.041 | A+3 | 12.0205 | TA 602 |  | TA 602 | TA 602 | ta602 | 123/2
2026-06-07 | 2026-06-07 | 2026-06-11 | M S Gagan Entp 2 | 26.7642 | A+6 | 5.3528 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/1 | C
2026-06-07 | 2026-06-07 | 2026-06-14 | M S Gagan Entp 2 | 27.9651 | A+9 | 3.4956 | TA 602 |  | TA 602 | TA 602 | ta602 | 123/3 | C
2026-06-07 | 2026-06-03 | 2026-06-07 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | 127/1 | C
2026-06-07 | 2026-06-07 | 2026-06-11 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 127/2 | C
2026-06-07 | 2026-05-31 | 2026-06-08 | M S Mukesh Kumar Verma | 27.9651 | A+9 | 3.1072 | TA 602 |  | TA 602 | TA 602 | ta602 | 108/1 | C
2026-06-08 | 2026-06-08 | 2026-06-15 | M S Amrendra Prasad | 22.9237 | A+0 | 2.8655 | TA 602 |  | TA 602 | TA 602 | ta602 | 89/9 | C
2026-06-08 | 2026-06-07 | 2026-06-11 | M S Gagan Entp 2 | 26.7642 | A+6 | 5.3528 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/1 | C
2026-06-08 | 2026-06-07 | 2026-06-14 | M S Gagan Entp 2 | 27.9651 | A+9 | 3.4956 | TA 602 |  | TA 602 | TA 602 | ta602 | 123/3 | C
2026-06-08 | 2026-06-07 | 2026-06-11 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 127/2 | C
2026-06-08 | 2026-05-31 | 2026-06-08 | M S Mukesh Kumar Verma | 27.9651 | A+9 | 3.1072 | TA 602 |  | TA 602 | TA 602 | ta602 | 108/1 | C
2026-06-08 | 2026-06-08 | 2026-06-12 | M S Mukesh Kumar Verma | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 107/1 | C
2026-06-09 | 2026-06-08 | 2026-06-15 | M S Amrendra Prasad | 22.9237 | A+0 | 2.8655 | TA 602 |  | TA 602 | TA 602 | ta602 | 89/9 | C
2026-06-09 | 2026-06-07 | 2026-06-11 | M S Gagan Entp 2 | 26.7642 | A+6 | 5.3528 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/1 | C
2026-06-09 | 2026-06-07 | 2026-06-14 | M S Gagan Entp 2 | 27.9651 | A+9 | 3.4956 | TA 602 |  | TA 602 | TA 602 | ta602 | 123/3 | C
2026-06-09 | 2026-06-07 | 2026-06-11 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 127/2 | C
2026-06-09 | 2026-06-08 | 2026-06-12 | M S Mukesh Kumar Verma | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 107/1 | C
2026-06-10 | 2026-06-08 | 2026-06-15 | M S Amrendra Prasad | 22.9237 | A+0 | 2.8655 | TA 602 |  | TA 602 | TA 602 | ta602 | 89/9 | C
2026-06-10 | 2026-06-07 | 2026-06-11 | M S Gagan Entp 2 | 26.7642 | A+6 | 5.3528 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/1 | C
2026-06-10 | 2026-06-07 | 2026-06-14 | M S Gagan Entp 2 | 27.9651 | A+9 | 3.4956 | TA 602 |  | TA 602 | TA 602 | ta602 | 123/3 | C
2026-06-10 | 2026-06-10 | 2026-06-13 | M S Gagan Entp 3 | 30.2572 | B2+0 | 7.5643 | TA 602 |  | TA 602 | TA 602 | ta602 | 123/0 | C
2026-06-10 | 2026-06-07 | 2026-06-11 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 127/2 | C
2026-06-10 | 2026-06-08 | 2026-06-12 | M S Mukesh Kumar Verma | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 107/1 | C
2026-06-11 | 2026-06-08 | 2026-06-15 | M S Amrendra Prasad | 22.9237 | A+0 | 2.8655 | TA 602 |  | TA 602 | TA 602 | ta602 | 89/9 | C
2026-06-11 | 2026-06-07 | 2026-06-11 | M S Gagan Entp 2 | 26.7642 | A+6 | 5.3528 | TA 602 |  | TA 602 | TA 602 | ta602 | 124/1 | C
2026-06-11 | 2026-06-07 | 2026-06-14 | M S Gagan Entp 2 | 27.9651 | A+9 | 3.4956 | TA 602 |  | TA 602 | TA 602 | ta602 | 123/3 | C
2026-06-11 | 2026-06-10 | 2026-06-13 | M S Gagan Entp 3 | 30.2572 | B2+0 | 7.5643 | TA 602 |  | TA 602 | TA 602 | ta602 | 123/0 | C
2026-06-11 | 2026-06-07 | 2026-06-11 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 127/2 | C
2026-06-11 | 2026-06-08 | 2026-06-12 | M S Mukesh Kumar Verma | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 107/1 | C
2026-06-12 | 2026-06-08 | 2026-06-15 | M S Amrendra Prasad | 22.9237 | A+0 | 2.8655 | TA 602 |  | TA 602 | TA 602 | ta602 | 89/9 | C
2026-06-12 | 2026-06-07 | 2026-06-14 | M S Gagan Entp 2 | 27.9651 | A+9 | 3.4956 | TA 602 |  | TA 602 | TA 602 | ta602 | 123/3 | C
2026-06-12 | 2026-06-10 | 2026-06-13 | M S Gagan Entp 3 | 30.2572 | B2+0 | 7.5643 | TA 602 |  | TA 602 | TA 602 | ta602 | 123/0 | C
2026-06-12 | 2026-06-12 | 2026-06-14 | M S Jwala Singh | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/7 | C
2026-06-12 | 2026-06-08 | 2026-06-12 | M S Mukesh Kumar Verma | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | 107/1 | C
2026-06-13 | 2026-06-08 | 2026-06-15 | M S Amrendra Prasad | 22.9237 | A+0 | 2.8655 | TA 602 |  | TA 602 | TA 602 | ta602 | 89/9 | C
2026-06-13 | 2026-06-07 | 2026-06-14 | M S Gagan Entp 2 | 27.9651 | A+9 | 3.4956 | TA 602 |  | TA 602 | TA 602 | ta602 | 123/3 | C
2026-06-13 | 2026-06-13 | 2026-06-15 | M S Gagan Entp 2 | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/9 | C
2026-06-13 | 2026-06-10 | 2026-06-13 | M S Gagan Entp 3 | 30.2572 | B2+0 | 7.5643 | TA 602 |  | TA 602 | TA 602 | ta602 | 123/0 | C
2026-06-13 | 2026-06-12 | 2026-06-14 | M S Jwala Singh | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/7 | C
2026-06-14 | 2026-06-08 | 2026-06-15 | M S Amrendra Prasad | 22.9237 | A+0 | 2.8655 | TA 602 |  | TA 602 | TA 602 | ta602 | 89/9 | C
2026-06-14 | 2026-06-07 | 2026-06-14 | M S Gagan Entp 2 | 27.9651 | A+9 | 3.4956 | TA 602 |  | TA 602 | TA 602 | ta602 | 123/3 | C
2026-06-14 | 2026-06-13 | 2026-06-15 | M S Gagan Entp 2 | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/9 | C
2026-06-14 | 2026-06-12 | 2026-06-14 | M S Jwala Singh | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | 126/7 | C
2026-06-15 | 2026-06-08 | 2026-06-15 | M S Amrendra Prasad | 22.9237 | A+0 | 2.8655 | TA 602 |  | TA 602 | TA 602 | ta602 | 89/9 | C
2026-06-15 | 2026-06-13 | 2026-06-15 | M S Gagan Entp 2 | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | 121/9 | C

## RawData
Start Date | Complete Date | Gang name | Tower Weight | Tower Type | Productivity | Project Code | Line Name | Project Name | Project Display | Project Scope Key | Source File | Source Sheet | Location No. | Tower Tightening Raw | Tower Tightening | Status
2026-02-18 | 2026-02-22 | M S Ratani Devi | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 125/2 |  |  | C
2026-02-25 | 2026-02-28 | M S Ratani Devi | 22.9237 | A+0 | 5.7309 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 122/2 |  |  | C
2026-02-22 | 2026-02-28 | M S Jwala | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 130/1 |  |  | C
2026-03-03 | 2026-03-07 | M S Ratani Devi | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 126/10 |  |  | C
2026-03-01 | 2026-03-10 | M S Jwala | 24.041 | A+3 | 2.4041 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 129A/3 |  |  | C
2026-03-01 | 2026-03-11 | M S Ratani Devi | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 126/9 |  |  | C
2026-03-11 | 2026-03-14 | M S Jwala | 26.7642 | A+6 | 6.691 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 129A/4 |  |  | C
2025-03-01 | 2026-03-15 | M S Ratani Devi | 24.041 | A+3 | 0.063266 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 126/5 |  |  | C
2026-03-15 | 2026-03-19 | M S Ratani Devi | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 126/4 |  |  | C
2026-03-15 | 2026-03-19 | M S Jwala | 26.7642 | A+6 | 5.3528 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 130/2 |  |  | C
2026-03-19 | 2026-03-22 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 130/3 |  |  | C
2026-03-19 | 2026-03-23 | M S Ratani Devi | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 126/3 |  |  | C
2026-03-23 | 2026-03-27 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 134/2 |  |  | C
2026-03-23 | 2026-03-28 | M S Ratani Devi | 26.7642 | A+6 | 4.4607 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 125/3 |  |  | C
2026-03-27 | 2026-03-30 | M S Jwala | 26.7642 | A+6 | 6.691 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 134/3 |  |  | C
2026-03-28 | 2026-04-02 | M S Ratani Devi | 24.041 | A+3 | 4.0068 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 124/4 |  |  | C
2026-03-31 | 2026-04-03 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 134/4 |  |  | C
2026-04-04 | 2026-04-07 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 134/8 |  |  | C
2026-04-07 | 2026-04-11 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 134/9 |  |  | C
2026-04-12 | 2026-04-15 | M S Jwala | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 134/7 |  |  | C
2026-04-15 | 2026-04-19 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 134/5 |  |  | C
2026-04-19 | 2026-04-23 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 136/2 |  |  | C
2026-04-24 | 2026-04-28 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 136/1 |  |  | C
2026-04-28 | 2026-05-02 | M S Jwala Singh | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 136/3 |  |  | C
2026-04-28 | 2026-05-04 | M S Aravali Infrastructure | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 102/7 |  |  | C
2026-04-28 | 2026-05-04 | M S Amrendra Prasad | 24.041 | A+3 | 3.4344 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 116/2 |  |  | C
2026-04-28 | 2026-05-04 | M S Gagan Entp | 26.7642 | A+6 | 3.8235 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 121/2 |  |  | C
2026-05-02 | 2026-05-04 | M S Jwala Singh | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 136/4 |  |  | C
2026-05-04 | 2026-05-08 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 121/1 |  |  | C
2026-05-04 | 2026-05-08 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 136/5 |  |  | C
2026-05-04 | 2026-05-09 | M S Amrendra Prasad | 24.041 | A+3 | 4.0068 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 116/1 |  |  | C
2026-05-03 | 2026-05-10 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 109/1 |  |  | C
2026-05-08 | 2026-05-12 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 121/4 |  |  | C
2026-05-08 | 2026-05-12 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 139/2 |  |  | C
2026-05-09 | 2026-05-14 | M S Amrendra Prasad | 22.9237 | A+0 | 3.8206 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 111/1 |  |  | C
2026-05-09 | 2026-05-15 | M S Jwala Singh | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 139/5 |  |  | C
2026-05-10 | 2026-05-16 | M S Mukesh Kumar Verma | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 109/2 |  |  | C
2026-05-12 | 2026-05-16 | M S Gagan Entp | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 121/7 |  |  | C
2026-05-15 | 2026-05-18 | M S Amrendra Prasad | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 111/2 |  |  | C
2026-01-16 | 2026-05-18 | M S Gagan Entp | 22.9237 | A+0 | 0.18637 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 121/6 |  |  | C
2026-05-16 | 2026-05-18 | M S Jwala Singh | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 136/8 |  |  | C
2026-05-18 | 2026-05-20 | M S Gagan Entp | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 121/5 |  |  | C
2026-05-17 | 2026-05-21 | M S Mukesh Kumar Verma | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 109/5 |  |  | C
2026-05-18 | 2026-05-21 | M S Jwala Singh | 24.041 | A+3 | 6.0103 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 139/1 |  |  | C
2026-05-18 | 2026-05-22 | M S Amrendra Prasad | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 111/3 |  |  | C
2026-05-21 | 2026-05-23 | M S Gagan Entp | 26.7642 | A+6 | 8.9214 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 124/5 |  |  | C
2026-05-23 | 2026-05-25 | M S Gagan Entp | 24.041 | A+3 | 8.0137 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 125/1 |  |  | C
2026-05-23 | 2026-05-26 | M S Amrendra Prasad | 22.9237 | A+0 | 5.7309 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 111/4 |  |  | C
2026-05-21 | 2026-05-28 | M S Mukesh Kumar Verma | 24.041 | A+3 | 3.0051 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 109/6 |  |  | C
2026-05-26 | 2026-05-29 | M S Gagan Entp | 31.6671 | B2+3 | 7.9168 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 125/0 |  |  | C
2206-05-22 | 2026-05-29 | M S Jwala Singh | 42.1971 | C2+9 |  | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 136/0 |  |  | C
2026-05-21 | 2026-05-31 | M S Mukesh Kumar Verma | 24.041 | A+3 | 2.1855 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 109/7 |  |  | C
2026-05-27 | 2026-06-01 | M S Amrendra Prasad | 26.7642 | A+6 | 4.4607 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 111/5 |  |  | C
2026-05-30 | 2026-06-02 | M S Gagan Entp | 27.9651 | A+9 | 6.9913 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 124/3 |  |  | C
2026-06-02 | 2026-06-03 | M S Gagan Entp | 22.9237 | A+0 | 11.4619 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 123/1 |  |  | C
2026-05-30 | 2026-06-03 | M S Jwala | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 127/3 |  |  | C
2026-06-03 | 2026-06-06 | M S Gagan Entp | 26.7642 | A+6 | 6.691 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 124/2 |  |  | C
2026-06-01 | 2026-06-07 | M S Amrendra Prasad | 22.9237 | A+0 | 3.2748 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 110/3 |  |  | C
2026-06-03 | 2026-06-07 | M S Jwala | 24.041 | A+3 | 4.8082 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 127/1 |  |  | C
2026-06-06 | 2026-06-07 | M S Gagan Entp 2 | 24.041 | A+3 | 12.0205 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 123/2
2026-05-31 | 2026-06-08 | M S Mukesh Kumar Verma | 27.9651 | A+9 | 3.1072 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 108/1 |  |  | C
2026-06-07 | 2026-06-11 | M S Gagan Entp 2 | 26.7642 | A+6 | 5.3528 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 124/1 |  |  | C
2026-06-07 | 2026-06-11 | M S Jwala Singh | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 127/2 |  |  | C
2026-06-08 | 2026-06-12 | M S Mukesh Kumar Verma | 22.9237 | A+0 | 4.5847 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 107/1 |  |  | C
2026-06-10 | 2026-06-13 | M S Gagan Entp 3 | 30.2572 | B2+0 | 7.5643 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 123/0 |  |  | C
2026-06-07 | 2026-06-14 | M S Gagan Entp 2 | 27.9651 | A+9 | 3.4956 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 123/3 |  |  | C
2026-06-12 | 2026-06-14 | M S Jwala Singh | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 126/7 |  |  | C
2026-06-08 | 2026-06-15 | M S Amrendra Prasad | 22.9237 | A+0 | 2.8655 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 89/9 |  |  | C
2026-06-13 | 2026-06-15 | M S Gagan Entp 2 | 22.9237 | A+0 | 7.6412 | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 121/9 |  |  | C
2026-06-12 |  | M S Mukesh Kumar Verma | 24.041 | A+3 |  | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 107/4 |  |  | WIP
2026-05-14 |  | M S Jwala Singh | 30.2572 | B1+0 |  | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 127/0 |  |  | WIP
2026-06-15 |  | M S Amrendra Prasad | 22.9237 | A+0 |  | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 89/6 |  |  | WIP
2026-06-15 |  | M S Gagan Entp 2 | 36.1787 | C1+3 |  | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 116/0 |  |  | WIP

## Data Issues
Start Date | Complete Date | Gang name | Tower Weight | Tower Type | Productivity | Project Code | Line Name | Project Name | Project Display | Project Scope Key | Source File | Source Sheet | Location No. | Tower Tightening Raw | Tower Tightening | Status | Issues
2026-06-12 |  | M S Mukesh Kumar Verma | 24.041 | A+3 |  | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 107/4 |  |  | WIP | Missing start/end date (not expanded)
2026-05-14 |  | M S Jwala Singh | 30.2572 | B1+0 |  | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 127/0 |  |  | WIP | Missing start/end date (not expanded)
2026-06-15 |  | M S Amrendra Prasad | 22.9237 | A+0 |  | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 89/6 |  |  | WIP | Missing start/end date (not expanded)
2026-06-15 |  | M S Gagan Entp 2 | 36.1787 | C1+3 |  | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 116/0 |  |  | WIP | Missing start/end date (not expanded)
2206-05-22 | 2026-05-29 | M S Jwala Singh | 42.1971 | C2+9 |  | TA 602 |  | TA 602 | TA 602 | ta602 | TA 602 - DPR - 2026-06-15.xlsx | Erection | 136/0 |  |  | C | Non-positive duration (Start > End or 0) (not expanded)

## Issues
file | issue | sheet
TA 602 - DPR - 2026-06-15.xlsx | XML scrub fallback used for sheet 'Project Details'
TA 602 - DPR - 2026-06-15.xlsx | XML scrub fallback used for sheet 'Erection ' | Erection

## Diagnostics
file | project | sheet | line_name | line_name_source | detected_header_row | columns_detected | configured_sheet | template_mapping_sheet | template_mapping_applied | template_mapping_changes | tower_weight_assumed_mt | tower_weight_assumption_rows | date_repairs_applied
TA 602 - DPR - 2026-06-15.xlsx | TA 602 | Erection |  |  | 2 | sl no, location no, type of tower, nan, starting date, tower weight, status, completion date, gang name, manpower, hindarnce days, remarks, tackweldng status, tackwelding start date, tackwelding completion date, sub contractor name | Erection | TA 602 Erection | TRUE | C3:type of tower->tower type |  | 0 | 0

## README_Assumptions
Notes
Assumptions & Cleaning Rules:
- Start date cutoff: rows with Start Date before 2021-01-01 are not expanded and logged in 'Data Issues'.
- Completion date must be before 2026-06-16 (future completions go to 'Data Issues').
- Tower Weight range: only [0, 500] MT is considered valid for expansion; out-of-range rows go to 'Data Issues'.
- Missing or non-positive durations (Start/End missing or Start > End or 0) are logged to 'Data Issues' and not expanded.
- Ambiguous numeric dates (e.g., 1/12/2025) that initially parse as Start > End are retried with month-first before being marked invalid.
- Gang name normalization: remove special characters (digits kept), Title Case words, and insert a space before trailing digits (e.g., 'xyz4' â†’ 'Xyz 4').
- If 'Tower Weight' header is missing in a sheet, Tower Weight is assumed as 45 MT for all rows in that sheet (noted in 'Issues').
- If some Tower Weight values are present and some are blank in a sheet, blank rows are filled with the average of available in-range tower weights for that sheet (noted in 'Issues').
- If a sheet has no usable in-range Tower Weight values at all, blank rows fall back to 45 MT (noted in 'Issues').
- DPR_Config support: when multiple erection sheet names are configured for a project, each listed sheet is processed independently, assigned its own line identity, and then concatenated.
- DPR_Config template mapping: for projects with discipline-specific template check marked Yes, column-wise mapping from the discipline template tab is applied before required-field validation.
- DPR_Config section mapping: optional '<Project> Erection Sections' tabs can split a physical sheet by marker text, filter rows, derive line names from a column, and use section-specific template tabs.
- Sectioned rows with missing Tower Weight first use same-file historical averages for the same Line Name before falling back to the default assumption.
- Sheets:
â€¢ ProdDailyExpanded : per-day expanded rows used by the dashboard
â€¢ ProdDailyExpandedSingles : per-day expanded rows including single-occurrence gangs
â€¢ RawData : per-erection rows (unexpanded), for traceability
â€¢ Data Issues : row-level data problems (reason in 'Issues' column)
â€¢ Issues : file-level problems (missing sheet/headers, read/open errors, etc.)
â€¢ Diagnostics : which sheet used, detected header row, and normalized header text
- Dashboard note: a 15-day productivity loss cap is used in downstream analytics.