## RawData
project_code | project_display | project_scope_key | line_name | line_name_source | section_label | report_date | source_file | source_sheet | configured_sheet | template_sheet | stringing_resolution_policy | header_row_number | source_row_number | activity_raw | activity_norm | quantity_loa | quantity_estimated_or_total | quantity_primary | cumulative_last_month | plan_for_month | progress_for_month | today_progress | cumulative_progress | balance_progress | gangs_working | remarks
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 14 | Soil Investigation | soil_investigation |  | 31 | 31 | 16 | 0 |  |  | 17 | 14
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 15 | Foundation | foundation |  | 480 | 480 | 154 | 30 | 8 | 0 | 162 | 318 | 3.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 16 | Earthing | earthing |  | 480 | 480 | 96 | 30 | 10 | 1 | 106 | 374
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 17 | Tower Erection | tower_erection |  | 480 | 480 | 52 | 35 | 17 | 2 | 69 | 411 | 4.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 18 | Tack welding | tack_welding |  | 480 | 480 | 0 | 35 | 0 | 0 | 0 | 480 | 2.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 19 | Stringing(Km) | stringing |  | 184.986 | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0

## Diagnostics
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | TemplateSheet | TemplateApplied | TemplateChanges | FallbackNote | SectionsDetected | HeadersDetected | Rows | FilenameDate | InternalDate | DateQuality | Status | Reason
TA 602 - DPR - 2026-06-15.xlsx | TA 602 | 800kV HVDC TA-602 | 800kV HVDC TA-602 |  | filename | TA 602 Status | TRUE | C1:Activity->activity_raw; C2:Final Estimated Quantity->quantity_estimated_or_total; C4:Cumulative Progress till Last Month(May'26)->cumulative_last_month; C6:Plan for the Month->plan_for_month; C7:Today's Progress->today_progress; C8:Progress till Date for the Month->progress_for_month; C10:Completed till Date->cumulative_progress; C11:Balance Work->balance_progress; C13:Gangs at Present->gangs_working | XML scrub fallback used for sheet '800kV HVDC TA-602' | 1 | 1 | 6 | 2026-06-15 | 2026-06-16 | MISMATCH | OK

## Issues
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | Issue | Reason

## Coverage
project_code | project_display | status | reason_code | reason | workbook | configured_sheet | resolved_sheet | rows | filename_date | internal_date | date_quality | available_sheets
TA 602 | TA 602 | OK | OK |  | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | 6 | 2026-06-15 | 2026-06-16 | MISMATCH | Project Details; DPR Sheet; 800kV HVDC TA-602; PPT-Erection Part; PPT _Statutory; PPT Supply; Supply Status; FDN; FDN Completed; PGCIL - KEC; Survey details 11-06-2026; Erection ; Erection Completed ; Erection Compiled; Stringing; Stringing Completed; Stringing Compiled; TA-602Visual Chart ; Visual chart; Pile Fdn; Crossing; Survey; Soil Inv.; Survey Anx