## 765KV TA 414 VNTL (hidden)
| Project Code | TA 414 | Date |  | 2026-06-15 |  | President-T&D | Mr. Ganesh Srinivasan
| Project Name | 765KV D/C HEXA VATAMAN - NAVSARI TL (PKG 04) |  |  | NOA Start Date | 2024-03-12 | PCH | Mr. Arun Felbin
| Client Name | Powergrid Vataman Transmission Ltd |  |  | LOA End Date | 2025-12-11 | Regional Manager | Mr. Nitin Bandale
| Revised End Date | 2026-05-11 |  |  | Planning Engineer | Nishant Giri | Project Manger | Mr. Vivek Kumar Gupta
\
Check Survey
Activity | Unit | Final Est. Qty | L2 till Last Month | Submitted till Last Month | Approved till Last Month | Balance to Submit | Balance to Approve | L2 Submission Plan for Current Month | Progress For Month | Approved till Current Month | Remarks
Rout Alignment | km | 127.854 | 127.854 | 127.854 | 127.854 |  |  |  |  | 127.854 | Completed
Detailed Survey | km | 127.854 | 127.854 | 127.854 | 127.854 |  |  |  |  | 127.854 | Completed
Check Survey | km | 127.854 | 127.854 | 127.854 | 127.854 |  |  |  |  | 127.854 | Completed
Progress Status
Activity | Final Estimated Quantity | Cumulative L2 till Last Month (Jan'26) | Cumulative Progress till Last Month(Feb'26) | L2 for present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks
Soil Investigation | 28 |  | 0 | 0 | 0 |  |  | 0 | 28 | 0 |  |  | Completed.
Foundation | 351 |  | 266 | 0 | 45 | 0 | 0 | 0 | 266 | 85 | 0 | 0
Earthing | 351 |  | 236 | 0 | 45 | 1 | 7 | 0 | 243 | 108
Tower Erection | 351 |  | 123 | 0 | 100 |  | 5 | 0 | 128 | 223
Tack welding | 351 |  | 35 | 0 | 45 | 1 | 0 | 0 | 35 | 316 | 2 | 2
Stringing(Km) | 127.854 |  |  | 0 | 8.724 |  |  | 0 | 0 | 127.854

## 765KV ASOTL
| Project Code | TA 510 |  |  | Date | 2026-06-16 | President-T&D | Mr. Ganesh Srinivasan
| Project Name | 765KV D/C Ahmedabad to South Olpad TL-04 |  |  | NOA Start Date | 2024-11-26 | PCH | Mr. Arun Felbin
| Client Name | PGKTL |  |  | LOA End Date | 2026-10-25 | Regional Manager | Mr. Nitin Bendale
| Revised End Date |  |  |  | Planning Engineer | Mr.Jayant Vaishnav | Project Manger | Mr. Subash .S
Survey
Activity | Unit | Final Est. Qty | L2 till Last Month | Submitted till Last Month | Approved till Last Month | Balance to Submit | Balance to Approve | L2 Submission Plan for Current Month | Progress For Month | Approved till Current Month | Remarks
Rout Alignment | Km | 114.516 | 114.516 | 114.516 | 114.516 | 0 | 0 | 0 | 0 | 114.516 | Completed
Detailed Survey | Km | 114.516 | 114.516 | 114.315 | 107.492 | 0.201 | 7.024 | 0 | 0 | 107.492
Check Survey | Km | 114.516 | 114.516 | 97.677 | 90.949 | 23.567 | 23.567 | 0 | 0 | 93.542
Progress Status
Activity | Final Estimated Quantity | Cumulative L2 till Last Month (May'26) | Cumulative Progress till Last Month(May 26) | L2 for present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks
Soil Investigation | 30 | 0 | 30 | 0 | 0 |  |  | 24 | 30 | 0
Foundation | 299 | 16 | 85 | 0 | 47 |  | 7 | 293 | 92 | 207 | 3 | 5
Earthing | 299 | 16 | 78 | 8 | 47 | 1 | 7 | 293 | 85 | 214
Tower Erection | 299 | 30 | 40 | 8 | 30 |  | 5 | 270 | 45 | 254
Tack welding | 299 | 30 | 13 |  | 30 |  |  | 270 | 13 | 286
Stringing(Km) | 114.516 | 11 | 0 | 11 | 0 |  |  | 78 | 0 | 114.516

## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manager | Section Incharge | Supervisor
TA 510 | 765kV D/C Ahmedabad South Olpad TL04 | Powergrid South Olpad Transmission Limited | 2024-03-12 | 2025-12-11 | Mr.Jayant Vaishnav | Mr.Arun Felbin | Mr. Nitin Ashok Bendale | Mr. Subash.S | Mr.Sahil Khan | Mr.B Nagarajan
Mr.Praveen Singh Rathore
Mr.Vidhya Saker upadya
Mr.Mohan Kumar
Mr.Mohit Kumar Mahto
Mr.Dhananjay Kumar Srivastava
Mr.Ajay Mahato
Mr.Pramod Singh
Mr.Jitender Kumar

## AOTL - KEC
KEC INTERNATIONAL LIMITED | [11 empty] | 2026-06-16
Name of Client: |  | Powergrid South Olpad Transmission Limited
Name of Line: |  | TL-04 , 765 kV D/C Ahmedabad - South Olpad Transmission Line
NOA Ref. No.: |  | CC/T/W-TW/DOM/A10/23/12603/NOA-2/24-114169/01, Dt.26-11-24
Sr No. | Activity | Estimated Quantity | Cumm. Progress up to till last Month May'26) | Target as per L2 Schedule Cummulative (upto May'26) | L3 Plan for the month (May'26 ) | Today's Progress | Progress in this month | Cumm. Progress till date | Cumm. Balance | WIP | No of Gangs | Remark
1 | Route Alignment (Km) | 114.516 | 114.516 | 0 | 0 |  |  | 114.516 | 0
2 | Detailed Survey (Km) | 114.516 | 107.492 | 0 | 7.024 |  |  | 107.492 | 7.024
3 | Profiling (Km) | 114.516 | 107.587 | 0 | 6.929 |  |  | 107.587 | 6.929
4 | Check Survey (Km) | 114.516 | 93.542 | 0 | 20.974 |  |  | 93.542 | 20.974
5 | Soil Investigation (Nos.) | 30 | 30 | 0 | 0 |  |  | 30 | 0
6 | Excavation | 293 | 88 | 16 | 34 |  |  | 92 | 201
7 | Foundation (Nos.) | 293 | 85 | 16 | 42 |  | 7 | 92 | 201 | 3 | 5
8 | Earthing (Nos.) | 293 | 78 | 16 | 30 | 1 | 7 | 85 | 208
9 | Tower Erection (Nos) | 293 | 40 | 30 | 18 |  | 5 | 45 | 248
10 | Tack Welding | 293 | 13 | 30 | 18 |  |  | 13 | 280
11 | Stringing (Km) | 114.516 | 0 | 11 | 0 |  |  | 0 | 114.516
a) | Paying Out | 114.516 | 0 | 11 | 0 |  |  | 0 | 114.516
b) | Final Sag | 114.516 | 0 | 11 | 0 |  |  | 0 | 114.516
12 | OPGW (Km) | 114.516 | 0 | 20 | 0 |  |  | 0 | 114.516

## DPR Sheet
KEC INTERNATIONAL LIMITED
DAILY PROGRESS REPORT : SUBMISSION STATUS AS ON |  |  |  |  | 2026-06-16
Name of the Project: |  | TL-04 , 765 kV D/C Ahmedabad - South Olpad Transmission Line
Contract No. & Date : |  | CC/T/W-TW/DOM/A10/23/12603/NOA-2/24-114169/01, Dt.26-11-24
ROUTE ALIGNMENT PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
114.516 | 114.516 | 0 | 114.516 | 0
SOIL INVESTIGATION PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
30 | 30 | 0 | 30 | 0
DETAILED SURVEY PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
114.516 | 107.492 | 0 | 107.492 | 7.024
CHECK SURVEY PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
114.516 | 93.542 | 0 | 93.542 | 20.974
FOUNDATION PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
293 | 85 | 7 | 92 | 201
s
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
293 | 78 | 7 | 85 | 208
TOWER ERECTION PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
293 | 40 | 5 | 45 | 248
STRINGING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY(KM)
114.516 | 0 | 0 | 0 | 114.516
OPGW STRINGING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
114.516 | 0 | 0 | 0 | 114.516

## Sheet5 (hidden)
127/1
135/0
139/1
139/2
139/3
140/0
167/0
173/0
174/0
174/2
178/2
179/0
183/3
191/0
192/0
193/0
194/0
198/0
199/2
210/0
216/0
216/2
216/3
244/3
244/4
250/1
250A/0
255/0
256/1
211/0
162/0
199/0
127/1
128/0
135/0
139/1
139/2
139/3
140/0
141/0
149/0
162/0
167/0
173/0
174/0
174/2
178/2
179/0
183/3
191/0
192/0
193/0
194/0
198/0
199/2
210/0
216/0
216/2
216/3
241/1
244/0
244/3
244/4
250/1
250A/0
255/0
256/1
211/0
199/0

## Sheet3 (hidden)
A
127/2 | 127/2128/0135/0139/0139/2141/1141/2145/5145/6148/3161/0166/0175/1182/0183/0183/1183/3194/0214/3214/6217/4225/3244/0244/2250/2
128/0
135/0
139/0 | 127/2128/0135/0139/0139/2141/1141/2145/5145/6148/3161/0166/0175/1182/0183/0183/1183/3194/0214/3214/6217/4225/3244/0244/2250/2
139/2
141/1
141/2
145/5
145/6
148/3
161/0
166/0
175/1
182/0
183/0
183/1
183/3
194/0
214/3
214/6
217/4
225/3
244/0
244/2
250/2

## Sheet1 (hidden)
District | Till Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25
Bharuch | 14 | 9 | 14 | 4 | 1
Surat |  |  |  | 4 | 17 | 4
Navsari | 4 | 7 | 6 | 2

## Survey
|  |  | Date | 2026-06-16
TA-510 ¦ ASOTL PROJECT ¦ SURVEY STATUS ¦
Sl. No. | Particulars | UoM | Qty. | Remarks
1 | Total Line Length | Kms. | 114.315
2 | Detail Survey Submitted | Kms. | 114.315
3 | Balance to Submit | Kms. | 0 | AP171/0-175/0 GETCO- SS
4 | Detail Survey Approved | Kms. | 107.492
5 | Balance to Approve | Kms. | 16.839 | AP175-177 & 184-185
6 | Check Survey Submitted | Kms. | 97.677
7 | Check Survey Approved | Kms. | 93.542 |  | 4.135
8 | Balance to Approve | Kms. | 4.135
9 | Balanceto Submit due to Crossing Section | Kms. | 13.95

## Soil Inv.
ASOTL PROJECT - SOIL INVESTIGATION LOCATIONS
Sl. No. | Loc. No. | TOT | RC | Depth In Mtr | Status | Classification | Approval Letter Status | Remarks | Agency | PO
1 | AP118 | 5DD60+25 |  | 10 | Approved | Sandy Dry | 2025-05-25 |  | Geo Design | Done.
2 | 124/0 | 5DD60+9 |  | 20 | Approved | WET | 2026-05-31 | Instead of 127/0 | Geo Design | To be Done.
3 | 124/3 | 5DB1+0 |  | 20 | Approved | Sandy Dry/ WET | 2026-05-31 | New Location | Geo Design | To be Done.
4 | 124/7 | 5DB1+0 |  | 20 | Approved | Sandy Dry/ Normal Dry | 2026-05-31 | Instead of 130/0 | Geo Design | To be Done.
5 | 124/10 | 5DA+0 |  | 20 | Approved | Sandy Dry/ Normal Dry | 2026-05-31 | New Location | Geo Design | To be Done.
6 | AP127 |  |  | 10 | Approved | Sandy Dry | 2025-05-25 | Eliminated | Geo Design | Done.
| AP130 | [6 empty] | Eliminated | Geo Design
7 | AP131 | DD60+35(S) |  | 10 | Approved | WET | 2026-05-18 |  | Geo Design | Done.
8 | AP131/1 (Pile) | DD45+9 |  | 40 | Approved | Pile | 2026-03-11 |  | Geo Design | Done.
9 | AP131/2 (Pile) | DD60+55 |  | 40 | Approved | Pile | 2026-05-18 |  | Geo Design | Done.
10 | AP132 | DD60+55 |  | 10 | Approved | Sandy Dry |  |  | Geo Design | Done.
11 | AP139 | DD60+0 |  | 10 | Approved | Sandy Dry | 2025-05-25 |  | Geo Design | Done.
12 | AP142 | DB2+0 |  | 10 | Approved | Sandy Dry | 2025-05-25 |  | Geo Design | Done.
13 | AP146 | DD45+0 |  | 10 | Approved | Black Cotton | 2025-05-25 |  | Geo Design | Done.
14 | AP150 | DD60+6 |  | 10 | Approved | Normal dry/wet | 2025-05-25 |  | Geo Design | Done.
15 | AP155 | DB2+0 |  | 10 | Approved | Black Cotton | 2025-05-25 |  | Geo Design | Done.
16 | AP158 | DC1+3 |  | 10 | Approved | Black Cotton | 2025-05-25 |  | Geo Design | Done.
17 | AP162 | DD60+6 |  | 10 | Approved | Black Cotton | 2025-05-25 |  | Geo Design | Done.
18 | AP166 | DD60+6 |  | 10 | Approved | Black Cotton | 2025-05-25 |  | Geo Design | Done.
19 | AP174 |  |  | 10 | Approved | Black Cotton | 2025-05-25 |  | Geo Design | Done.
20 | AP176 |  |  | 10 | Approved | Black Cotton | 2025-05-25 |  | Geo Design | Done.
21 | AP180 | DD60+35(S) |  | 10 | Approval Awaiting from PGCIL |  |  |  | Bhoomi | To be Done.
22 | AP180/1(Pile) | DD45+35(S) |  | 40 | Approved | Pile | 2026-03-13 |  | Geo Design | Done.
23 | AP181 (Pile) | DD60+25(S) |  | 40 | Approved | Pile | 2026-03-14 |  | Geo Design | Done.
24 | AP182 (Pile) | DB2+6 |  | 40 | Approved | Pile | 2026-03-14 |  | Geo Design | Done.
25 | AP183 | DC1+9 |  | 10 | Approval Awaiting from PGCIL | Black Cotton |  |  | Geo Design | To be Done.
26 | AP184 | DD45+6 |  | 10 | Approval Awaiting from PGCIL | Sandy Dry/ WET |  |  | Geo Design | To be Done.
| AP185 | [6 empty] | Interchanged
27 | AP186 | DC1+0 |  | 10 | Approved | Black Cotton | 2026-03-18 | Instead of 185/0 | Geo Design | Done.
28 | AP187 | DB2+0 |  | 10 | Approved | Black Cotton | 2026-03-18 |  | Geo Design | Done.
29 | AP191 | DC1+0 |  | 10 | Approved | Black Cotton | 2026-03-18 |  | Geo Design | Done.
30 | AP192 | DB1+0 |  | 10 | Approved | Black Cotton | 2026-03-18 |  | Geo Design | Done.
[9 empty] | Geo Design | Done.

## Survey Anx
TL-04 , 765 kV D/C Ahmedabad - South Olpad Transmission Line
District | Section | Total | Detail Survey |  |  | Check Survey
|  |  | Completed | Submitted | Approved | Completed | Submitted | Approved
Anand | 117/0-119/0 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62
Anand | 119/0-124/0 | 1.572 | 1.572 | 1.572 | 1.572 | 1.572 | 1.572 | 1.572
Anand | 124/0-124/3 | 1.228 | 1.228 | 1.228 | 1.228 | 1.228 | 1.228 | 1.228
Anand | 124/3-131/0 | 3.994 | 3.994 | 3.994 | 3.994 | 3.994 | 3.994 | 3.994
Vadodara | 131/0-133/0 | 2.694 | 2.694 | 2.694 | 2.694 | 2.694 | 2.694 | 2.694
Vadodara | 133/0-135/0 | 1.555 | 1.555 | 1.555 | 1.555 | 1.555 | 1.555 | 1.555
Bharuch | 135/0-136/0 | 0.422 | 0.422 | 0.422 | 0.422 | 0.422 | 0.422 | 0.422
Bharuch | 136/0-139/5 | 3.881 | 3.881 | 3.881 | 3.881 | 3.881 | 3.881 | 3.881
Bharuch | 139/5-144/0 | 4.328 | 4.328 | 4.328 | 4.328 | 4.328 | 4.328 | 4.328
Bharuch | 144/0-146/0 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9
Bharuch | 146/0-148/1 | 3.526 | 3.526 | 3.526 | 3.526 | 3.526 | 3.526 | 3.526
Bharuch | 148/1-148/7 | 2.312 | 2.312 | 2.312 | 2.312 | 2.312 | 2.312 | 2.312
Bharuch | 148/7-153/0 | 4.704 | 4.704 | 4.704 | 4.704 | 4.704 | 4.704 | 4.704
Bharuch | 153/0-155/0 | 1.557 | 1.557 | 1.557 | 1.557 | 1.557 | 1.557 | 1.557
Bharuch | 155/0-155/5 | 1.947 | 1.947 | 1.947 | 1.947 | 1.947 | 1.947 | 1.947
Bharuch | 155/5-156/0 | 0.405 | 0.405 | 0.405 | 0.405 | 0.405 | 0.405 | 0.405
Bharuch | 156/0-160/1 | 8.356 | 8.356 | 8.356 | 8.356 | 8.356 | 8.356 | 8.356
Bharuch | 160/1-160/3 | 0.817 | 0.817 | 0.817 | 0.817 | 0.817 | 0.817 | 0.817
Bharuch | 160/3-162/0 | 5.219 | 5.219 | 5.219 | 5.219 | 5.219 | 5.219 | 5.219
Bharuch | 162/0-168/0 | 7.07 | 7.07 | 7.07 | 7.07 | 7.07 | 7.07 | 7.07
Bharuch | 168/0-171/0 | 2.693 | 2.693 | 2.693 | 2.693 | 2.693 | 2.693 | 2.693
Bharuch | 171/0-174A/0 | 1.429 | 1.429 | 1.429
Bharuch | 174A/0- 175/0 | 5.301 | 5.301 | 5.301 | 5.301
Bharuch | 175/0-177/0 | 3.992 | 3.992 | 3.992
Bharuch | 177/0-179/0 | 3.142 | 3.142 | 3.142 | 3.142 | 3.142 | 3.142 | 3.142
Bharuch | 179/0-183/0 | 2.477 | 2.477 | 2.477 | 2.477 | 2.477 | 2.477 | 2.477
Bharuch | 183/0-184/0 | 1.128 | 1.128 | 1.128 | 1.128 | 1.128 | 1.128 | 1.128
Bharuch | 184/0-185/0 | 5.916 | 5.916 | 5.916 | 4.514
Bharuch | 185/0-186/0 | 0.244 | 0.244 | 0.244 | 0.244 | 0.244 | 0.244 | 0.244
Bharuch | 186/0-189/0 | 6.597 | 6.597 | 6.597 | 6.597 | 6.597 | 6.597 | 6.597
Bharuch | 189/0-190/0 | 0.243 | 0.243 | 0.243 | 0.243 | 0.243 | 0.243 | 0.243
Bharuch | 190/0-192/1 | 5.061 | 5.061 | 5.061 | 5.061 | 5.061 | 5.061 | 5.061
Bharuch | 192/1-192/13 | 4.712 | 4.712 | 4.712 | 4.712 | 4.712 | 4.712 | 4.712
Bharuch | 192/13-194/0 | 2.794 | 2.794 | 2.794 | 2.794 | 2.794 | 2.794 | 2.794
Surat | 194/0-195/0 | 2.751 | 2.751 | 2.751 | 2.751 | 2.751 | 2.751 | 2.751
Surat | 195/0-Gantry | 6.728 | 6.728 | 6.728 | 6.728 | 6.728 | 6.728 | 2.593
|  | 114.315 | 114.315 | 114.315 | 107.492 | 97.677 | 97.677 | 93.542
6.823

## FDN
ASOTL Foundation | [12 empty] | 2026-06-16 | `
Sl. No. | Location No. | Tower Type | Classification | Concreting Volume in M3 | Starting Date | Todays Status | Cumulative Status | Completion Date | Remarks | Gang name | Earthing Status | Earthing Completion Date
1 | 155/3 | DA+0 | WPS | 39.126 | 2025-02-18 |  | Completed | 2025-02-25 |  | Arya Enterprises | Done | 2025-02-27
2 | 155/4 | DA+0 | WPS | 39.126 | 2025-02-18 |  | Completed | 2025-02-22 |  | B.K.Traders | Done | 2025-03-01
3 | 155/5 | DA+3 | WPS | 40.634 | 2025-02-23 |  | Completed | 2025-02-27 |  | B.K.Traders | Done | 2025-03-01
4 | 155/1 | DA+0 | WET | 63.346 | 2025-02-12 |  | Completed | 2025-02-17 |  | Arya Enterprises | Done | 2025-03-04
5 | 156/2 | DA+0 | WPS | 39.126 | 2025-03-26 |  | Completed | 2025-03-30 |  | Arya Enterprises | Done | 2025-04-03
6 | 156/1 | DA+3 | WET | 65.631 | 2025-03-05 |  | Completed | 2025-03-13 |  | Arya Enterprises | Done | 2025-03-15
7 | 156/0 | DB2+0 | WPS | 62.882 | 2025-03-05 |  | Completed | 2025-03-12 |  | B.K.Traders | Done | 2025-03-16
8 | 156/3 | DA+0 | WPS | 39.126 | 2025-03-13 |  | Completed | 2025-03-16 |  | B.K.Traders | Done | 2025-03-17
9 | 156/4 | DA+3 | WPS | 40.634 | 2025-03-21 |  | Completed | 2025-03-25 |  | Arya Enterprises | Done | 2025-03-28
10 | 139/5 | DA+0 | WPS | 39.126 | 2025-04-14 |  | Completed | 2025-04-21 |  | B.K.Traders | Done | 2025-04-23
11 | 139/4 | DA+0 | WPS | 39.126 | 2025-04-23 |  | Completed | 2025-04-28 |  | B.K.Traders | Done | 2025-05-02
12 | 139/1 | DA+0 | WPS | 39.126 | 2025-03-26 |  | Completed | 2025-04-16 |  | Om Infra | Done | 2025-05-06
13 | 138/1 | DA+0 | WPS | 39.126 | 2025-04-14 |  | Completed | 2025-04-29 |  | Om Infra | Done | 2025-05-06
14 | 137/0 | DD45+0 | WPS | 128.427 | 2025-04-14 |  | Completed | 2025-04-27 |  | Om Infra | Done | 2025-05-11
15 | 138/0 | DD60+0 | WPS | 178.19 | 2025-04-05 |  | Completed | 2025-04-21 |  | Om Infra | Done | 2025-05-11
16 | 136/0 | DD60+0 | WPS | 178.19 | 2025-04-25 |  | Completed | 2025-05-14 |  | Om Infra | Done | 2025-05-14
17 | 148/4 | DA+3 | WPS | 40.634 | 2025-05-13 |  | Completed | 2025-05-21 |  | B.K.Traders | Done | 2025-05-24
18 | 134/0 | DC2+0 | WPS | 92.292 | 2025-05-15 |  | Completed | 2025-05-25 |  | Om Infra | Done | 2025-05-26
19 | 144/0 | DB1+0 | WPS | 54.675 | 2025-06-01 |  | Completed | 2025-08-06 |  | Jyoti Construction | Done | 2025-06-08
20 | 143/1 | DA+3 | WPS | 40.634 | 2025-05-25 |  | Completed | 2025-06-02 |  | Jyoti Construction | Done | 2025-06-10
21 | 143/2 | DA+0 | WPS | 39.126 | 2025-05-30 |  | Completed | 2025-06-05 |  | Jyoti Construction | Done | 2025-06-10
22 | 141/0 | DB2+0 | WPS | 62.882 | 2025-07-23 |  | Completed | 2025-09-16 |  |  | Done | 2025-09-21
23 | 133/2 | DA+0 | WPS | 39.126 | 2025-08-31 |  | Completed | 2025-09-18 |  | B.K.Traders | Done | 2025-09-22
24 | 141/1 | DA+0 | WPS | 39.126 | 2025-09-21 |  | Completed | 2025-10-04 |  | Shakaldev | Done | 2025-10-08
25 | 138/2 | DA+0 | WPS | 39.126 | 2025-09-19 |  | Completed | 2025-10-05 |  | Vihan | Done | 2025-10-11
26 | 140/1 | DA+3 | WPS | 40.634 | 2025-09-24 |  | Completed | 2025-10-10 |  | Shakaldev | Done | 2025-09-21
27 | 148/5 | DA+0 | WET | 63.346 | 2025-05-03 |  | Completed | 2025-05-15 |  | B.K.Traders | Not Done
28 | 148/2 | DA+0 | WPS | 39.126 | 2025-05-15 |  | Completed | 2025-05-23 |  | B.K.Traders | Not Done
29 | 148/6 | DA+0 | WET | 63.346 | 2025-05-19 |  | Completed | 2025-05-31 |  | B.K.Traders | Not Done
30 | 148/7 | DA+0 | WPS | 39.126 | 2025-05-17 |  | Completed | 2025-05-28 |  | B.K.Traders | Not Done
31 | 145/0 | DB2+9 | WPS | 65.135 | 2025-09-25 |  | Completed | 2025-10-19 |  | Vihan | Done | 2025-11-08
32 | 139/2 | DA+3 | WPS | 40.634 | 2025-10-15 |  | Completed | 2025-10-24 |  | Shakaldev | Done | 2025-12-31
33 | 140/2 | DA+0 | WPS | 39.126 | 2025-09-10 |  | Completed | 2025-11-19 |  | Shakaldev | Done | 2025-11-26
34 | 135/0 | DB1+6 | WPS | 54.992 | 2025-11-11 |  | Completed | 2025-11-24 |  | B.K.Traders | Done | 2025-11-28
35 | 145/1 | DB1+9 | WPS | 54.992 | 2025-11-11 |  | Completed | 2025-11-24 |  | MD Hussain | Done | 2025-11-27
36 | 138/3 | DA-3 | WPS | 39.126 | 2025-11-18 |  | Completed | 2025-11-27 |  | Shakaldev | Done | 2025-11-28
37 | 192/11 | DA+3 | WET | 65.631 | 2025-11-15 |  | Completed | 2025-11-30 |  | Rudra | Done | 2025-12-22
38 | 141/2 | DA+6 | WPS | 40.634 | 2025-11-30 |  | Completed | 2025-12-07 |  | MD Hussain | Done | 2025-12-09
39 | 143/0 | DC2+0 | WPS | 92.292 | 2025-11-30 |  | Completed | 2025-12-09 |  | Shakaldev | Done | 2025-12-09
40 | 145/5 | DA+0 | WPS | 39.126 | 2025-11-15 |  | Completed | 2025-12-09 |  | Ambani | Done | 2025-12-14
41 | 148/3 | DA+0 | WET | 63.346 | 2025-11-27 |  | Completed | 2025-12-14 |  | Haji Enterprises | Done | 2025-12-13
42 | 192/13 | DA+0 | WET | 63.346 | 2025-12-01 |  | Completed | 2025-12-23 |  | Rudra | Done | 2025-12-25
43 | 145/3 | DA+0 | WET | 63.346 | 2025-12-01 |  | Completed | 2025-12-27 |  | Vihan | Done | 2025-12-28
44 | 146/1 | DA+0 | WET | 63.346 | 2025-12-10 |  | Completed | 2025-12-29 |  | MD Hussain | Done | 2025-12-28
45 | 146/3 | DA+0 | WET | 63.346 | 2025-12-21 |  | Completed | 2025-12-30 |  | Haji Enterprises | Done | 2025-12-30
46 | 140/0 | DD45+0 | WPS | 128.427 | 2025-12-16 |  | Completed | 2025-12-30 |  | Shakaldev | Done | 2026-01-01
47 | 145/4 | DA+0 | WET | 63.346 | 2025-12-10 |  | Completed | 2025-12-31 |  | Shakaldev | Done | 2026-01-01
48 | 192/10 | DA+0 | WET | 63.346 | 2025-12-21 |  | Completed | 2026-01-04 |  | Chandrakant Patel | Done | 2026-02-16
49 | 147/2 | DA-3 | WPS | 39.126 | 2026-01-01 |  | Completed | 2026-01-08 |  | MD Hussain | Done | 2026-01-09
50 | 146A/0 | DB2+0 | WET | 89.905 | 2025-12-15 |  | Completed | 2026-01-13 |  | Haji Enterprises | Done | 2026-01-13
51 | 186/1 | DA+0 | WET | 63.346 | 2026-01-05 |  | Completed | 2026-01-13 |  | Maa Bhavani | Done | 2026-01-09
52 | 192/7 | DB1+0 | WET | 79.944 | 2026-01-09 |  | Completed | 2026-01-21 |  | Chandrakant Patel | Done | 2026-01-23
53 | 192/12 | DA+6 | FS | 94.623 | 2026-01-16 |  | Completed | 2026-01-25 |  | Maa Bhavani | Done | 2026-01-27
54 | 147/1 | DA-3 | WET | 63.346 | 2026-01-08 |  | Completed | 2026-01-30 |  | Vihan | Done | 2026-02-02
55 | 142/0 | DB2+0 | WPS | 62.882 | 2026-01-27 |  | Completed | 2026-02-02 |  | Haji Enterprises | Done | 2025-02-02
56 | 146/0 | DD45+0 | WBC | 311.138 | 2026-01-06 |  | Completed | 2026-02-03 |  | MD Hussain | Done | 2026-02-04
57 | 194/1 | DA+6 | WET | 65.631 | 2026-02-01 |  | Completed | 2026-02-10 |  | Chandrakant Patel | Done | 2026-02-12
58 | 146A/1 | DA+0 | WET | 63.346 | 2026-02-02 |  | Completed | 2026-02-12 |  | Haji Enterprises | Done | 2026-02-13
59 | 148/1 | DA+0 | WET | 63.346 | 2026-02-03 |  | Completed | 2026-02-14 |  | ABS Construction | Done | 2026-02-14
60 | 148/0 | DC1+0 | WET | 117.033 | 2026-02-01 |  | Completed | 2026-02-27 |  | Vihan | Done | 2026-02-27
61 | 157B/0 | DD45+9 | WET | 192.374 | 2026-02-16 |  | Completed | 2026-03-11 |  | Haji Enterprises | Done | 2026-03-15
62 | 157A/0 | DC2+0 | WET | 134.785 | 2026-02-17 |  | Completed | 2026-03-22 |  | ABS Construction | Done | 2026-03-22
63 | 157/2 | DA+3 | WET | 65.631 | 2026-03-14 |  | Completed | 2026-03-23 |  | Haji Enterprises | Done | 2026-03-24
64 | 146/2 | DA+0 | WET | 63.346 | 2026-02-17 |  | Completed | 2026-03-31 |  | Haji Enterprises | Done | 2026-03-31
65 | 193/5 | DA+0 | WET | 63.346 | 2026-04-14 |  | Completed | 2026-04-20 |  | Chandrakant Patel | Done | 2026-05-18
66 | 192/8 | DA+0 | WET | 63.346 | 2026-04-29 |  | Completed | 2026-05-06 |  | BLG Infra | Done | 2026-05-08
67 | 192/9 | DA+3 | WET | 65.631 | 2026-04-02 |  | Completed | 2026-04-07 |  | BLG Infra | Done | 2026-04-07
68 | 139/0 | DD60+0 | WPS | 178.19 | 2026-04-01 |  | Completed | 2026-04-21 |  | Haji Enterprises | Done | 2026-04-22
69 | 139/3 | DA+3 | WPS | 40.634 | 2026-04-04 |  | Completed | 2026-04-13 |  | Haji Enterprises | Done | 2026-04-21
70 | 193/2 | DA+0 | WET | 63.346 | 2026-04-08 |  | Completed | 2026-04-13 |  | BLG Infra | Done | 2026-04-14
71 | 193/1 | DA+3 | WPS | 40.634 | 2026-04-12 |  | Completed | 2026-04-19 |  | BLG Infra | Done | 2026-04-19
72 | 193/4 | DA+3 | WPS | 40.634 | 2026-04-19 |  | Completed | 2026-04-29 |  | Chandrakant Patel | Done | 2026-05-29
73 | 193/0 | DC1+3 | WET | 120.461 | 2026-04-19 |  | Completed | 2026-04-28 |  | BLG Infra | Done | 2026-04-28
74 | 167/2 | DA+0 | WPS | 39.126 | 2026-05-07 |  | Completed | 2026-05-13 |  | BLG Infra | Done | 2026-05-15
75 | 157B/1 | DA+0 | WET | 63.346 | 2026-04-22 |  | Completed | 2026-05-16 |  | JDG Enterprises | Done | 2026-05-17
76 | 167/3 | DA+0 | WPS | 39.126 | 2026-05-11 |  | Completed | 2026-05-17 |  | BLG Infra | Done | 2026-05-18
77 | 133/0 | DC2+0 | WPS | 92.292 | 2026-05-09 |  | Completed | 2026-05-18 |  | Haji Enterprises | Done | 2026-05-17
78 | 167/4 | DA+3 | WPS | 40.634 | 2026-05-17 |  | Completed | 2026-05-20 |  | BLG Infra | Done | 2026-05-20
79 | 153/0 | DD60+0 | PS | 306.052 | 2026-04-04 |  | Completed | 2026-05-20 |  | Krishna Constrction | Done | 2026-05-08
80 | 133/1 | DA+3 | WPS | 40.634 | 2026-05-19 |  | Completed | 2026-05-23 |  | Haji Enterprises | Done | 2026-05-24
81 | 167/1 | DA+3 | WET | 65.631 | 2026-05-20 |  | Completed | 2026-05-26 |  | BLG Infra | Done | 2026-05-27
82 | 194/0 | DB1+0 | WET | 79.944 | 2026-04-30 |  | Completed | 2026-05-27 |  | Chandrakant Patel | Done | 2026-05-31
83 | 155/0 | DB2+0 | WBC | 127.51 | 2026-05-22 |  | Completed | 2026-05-31 |  | Haji Enterprises2 | Done | 2026-06-08
84 | 150/2 | DA+3 | WET | 65.631 | 2026-05-22 |  | Completed | 2026-05-31 |  | Vihan | Done | 2026-06-09
85 | 153/1 | DA+0 | WET | 63.346 | 2026-05-28 |  | Completed | 2026-05-31 |  | BLG Infra | Done | 2026-06-03
86 | 150/4 | DA+3 | WPS | 40.634 | 2026-05-28 |  | Completed | 2026-06-06 |  | Vihan | Done | 2026-06-08
87 | 155/2 | DA+3 | WPS | 40.634 | 2026-05-20 |  | Completed | 2026-06-06 |  | Haji Enterprises-1
88 | 154/0 | DC2+0 | PS | 168.913 | 2026-05-28 |  | Completed | 2026-06-10 |  | BLG Infra
89 | 150/3 | DA+3 | WPS | 40.634 | 2026-06-03 |  | Completed | 2026-06-11 |  | Vihan
90 | 154/1 | DC1+0 (TP) | WET | 117.033 | 2026-06-08 |  | Completed | 2026-06-14 |  | BLG Infra | Done | 2026-06-15
91 | 160/3 | DA+0 | WET | 63.346 | 2026-06-08 |  | Completed | 2026-06-14 |  | Haji Enterprises | Done | 2026-06-15
92 | 150/1 | DA+0 | WPS | 39.126 | 2026-06-08 |  | Completed | 2026-06-15 |  | Vihan | Done | 2026-06-16
93 | 148A/0 | DC2+0 | WET | 134.785 | 2026-06-12 | Excavation Wip |  |  |  | Vihan
94 | 154/2 | DA-3 | WET | 63.346 | 2026-06-15 | Excavation Wip |  |  |  | BLG Infra
95 | 160/2 | DA+0 | [7 empty] | Haji Enterprises
141/6
196/0
186/0
142/0
139/0
145/5
145/6
141/1

## Erection
AOTL Tower Erection | [14 empty] | 2026-06-16
Sl. No. | Location Number | Type of Tower | Starting Date | Tower Weight (MT) | Status | Completion Date | Gang Name | Tower Tightening | Manpower | Hindarnce Days | Remarks | Tackweldng Status | Tackwelding start date | Tackwelding Completion date | Sub Contractor name
1 | 141/1 | DA+0 | 2026-01-01 | 37.73 | Completed | 2026-01-07 | Dhaneshwar Mahato | Complete
2 | 139/2 | DA+3 | 2026-01-05 | 39.458 | Completed | 2026-01-12 | Lalan Mehta
3 | 141/0 | DB2+0 | 2026-01-08 | 54.418 | Completed | 2026-01-13 | Dhaneshwar Mahato | Complete
5 | 140/1 | DA+3 | 2026-01-14 | 39.458 | Completed | 2026-01-21 | Dhaneshwar Mahato | Complete
4 | 135/0 | DB1+6 | 2026-01-13 | 63.509 | Completed | 2026-01-25 | Lalan Mehta
7 | 145/4 | DA+0 | 2026-01-18 | 37.73 | Completed | 2026-01-28 | Lalan Mehta
6 | 143/1 | DA+3 | 2026-01-16 | 39.458 | Completed | 2026-01-29 | Hoque Construction |  |  |  |  | Completed | 2026-03-09 | 2026-03-09 | Asmina Power
8 | 145/0 | DB2+9 | 2026-01-22 | 65.757 | Completed | 2026-01-30 | Dhaneshwar Mahato | Complete |  |  |  | Completed | 2026-03-10 | 2026-03-10 | Asmina Power
9 | 145/5 | DA+0 | 2026-01-27 | 37.73 | Completed | 2026-01-31 | Lalan Mehta
11 | 134/0 | DC2+0 | 2026-02-01 | 64.254 | Completed | 2026-02-07 | Dhaneshwar Mahato | Complete
10 | 145/1 | DB1+9 | 2026-01-30 | 65.757 | Completed | 2026-02-11 | Hoque Construction
12 | 140/2 | DA+0 | 2026-02-08 | 37.73 | Completed | 2026-02-13 | Dhaneshwar Mahato | Complete
13 | 148/3 | DA+0 | 2026-02-13 | 37.73 | Completed | 2026-02-17 | Dhaneshwar Mahato | Complete |  |  |  | Completed | 2026-05-13 | 2026-05-13 | Asmina Power
14 | 143/0 | DC2+0 | 2026-02-12 | 64.254 | Completed | 2026-02-20 | Hoque Construction
15 | 148/2 | DA+0 | 2026-02-18 | 37.73 | Completed | 2026-02-22 | Dhaneshwar Mahato | Complete |  |  |  | Completed | 2026-05-13 | 2026-05-13 | Asmina Power
16 | 148/1 | DA+0 | 2026-02-23 | 37.73 | Completed | 2026-02-27 | Dhaneshwar Mahato | Complete |  |  |  | Completed | 2026-05-15 | 2026-05-15 | Asmina Power
17 | 192/13 | DA+0 | 2026-02-22 | 37.73 | Completed | 2026-02-28 | Hoque Construction
18 | 148/4 | DA+3 | 2026-02-27 | 39.458 | Completed | 2026-03-05 | Dhaneshwar Mahato | Complete |  |  |  | Completed | 2026-05-13 | 2026-05-13 | Asmina Power
19 | 192/11 | DA+3 | 2026-03-01 | 39.458 | Completed | 2026-03-09 | Hoque Construction
20 | 141/2 | DA+6 | 2026-03-08 | 44.727 | Completed | 2026-03-16 | Dhaneshwar Mahato | Complete
21 | 186/1 | DA+0 | 2026-03-10 | 37.73 | Completed | 2026-03-17 | Hoque Construction
22 | 140/0 | DD45+0 | 2026-03-16 | 72.234 | Completed | 2026-03-24 | Dhaneshwar Mahato | Complete
23 | 194/1 | DA+6 | 2026-03-17 | 44.727 | Completed | 2026-03-26 | Hoque Construction
24 | 146A/0 | DB2+0 | 2026-03-24 | 54.418 | Completed | 2026-03-30 | Dhaneshwar Mahato | Complete |  |  |  | Completed | 2026-05-19 | 2026-05-19 | Asmina Power
25 | 192/10 | DA+0 | 2026-03-26 | 37.73 | Completed | 2026-03-31 | Hoque Construction
26 | 146/0 | DD45+0 | 2026-04-02 | 72.234 | Completed | 2026-04-09 | Dhaneshwar Mahato | Complete |  |  |  | Completed | 2026-05-16 | 2026-05-16 | Asmina Power
27 | 146/1 | DA+0 | 2026-04-09 | 37.796 | Completed | 2026-04-15 | Dhaneshwar Mahato | Complete |  |  |  | Completed | 2026-05-17 | 2026-05-17 | Asmina Power
28 | 146/2 | DA+0 | 2026-04-15 | 37.796 | Completed | 2026-04-21 | Dhaneshwar Mahato | Complete |  |  |  | Completed | 2026-05-18 | 2026-05-18 | Asmina Power
29 | 146/3 | DA+0 | 2026-04-22 | 37.796 | Completed | 2026-04-29 | Dhaneshwar Mahato | Complete |  |  |  | Completed | 2026-05-18 | 2026-05-18 | Asmina Power
30 | 145/3 | DA+0 | 2026-04-30 | 37.796 | Completed | 2026-05-06 | Dhaneshwar Mahato | Complete |  |  |  | Completed | 2026-05-21 | 2026-05-21 | Asmina Power
31 | 148/5 | DA+0 | 2026-05-03 | 37.796 | Completed | 2026-05-07 | Gauri Shankar
32 | 146A/1 | DA+0 | 2026-05-07 | 37.796 | Completed | 2026-05-13 | Dhaneshwar Mahato | Complete |  |  |  | Completed | 2026-05-20 | 2026-05-20 | Asmina Power
33 | 148/6 | DA+0 | 2026-05-08 | 37.796 | Completed | 2026-05-12 | Gauri Shankar
34 | 148/7 | DA+0 | 2026-05-13 | 37.796 | Completed | 2026-05-17 | Gauri Shankar
35 | 147/1 | DA-3 | 2026-05-14 | 36.044 | Completed | 2026-05-18 | Dhaneshwar Mahato | Complete
36 | 139/3 | DA+3 | 2026-05-09 | 39.458 | Completed | 2026-05-21 | Hoque Construction
37 | 147/2 | DA-3 | 2026-05-18 | 36.044 | Completed | 2026-05-22 | Dhaneshwar Mahato | Complete
38 | 148/0 | DC1+0 | 2026-05-19 | 64.254 | Completed | 2026-05-25 | Gauri Shankar
39 | 142/0 | DB2+0 | 2026-05-23 | 54.418 | Completed | 2026-05-28 | Dhaneshwar Mahato
40 | 139/5 | DA+0 | 2026-05-22 | 37.796 | Completed | 2026-05-30 | Hoque Construction
41 | 136/0 | DD60+0 | 2026-05-28 | 80.255 | Completed | 2026-06-04 | Gauri Shankar
42 | 144/0 | DB1+0 | 2026-05-29 | 54.418 | Completed | 2026-06-04 | Dhaneshwar Mahato
43 | 139/1 | DA+0 | 2026-05-31 | 37.796 | Completed | 2026-06-08 | Hoque Construction
44 | 143/2 | DA+0 | 2026-06-05 | 37.796 | Completed | 2026-06-09 | Dhaneshwar Mahato |  | 33
45 | 138/0 | DD60+0 | 2026-06-05 | 80.255 | Tower Erection Completed | 2026-06-13 | Gauri Shankar |  | 30
46

## Visual chart 1
Visual Chart
Name of the Line : |  |  |  | TL04 765 kV D/C Ahmedabad - South Olpad Transmission Line
Client |  |  |  | Power Grid Corporation of India Limited | [26 empty] | FOUNDATION |  |  | TOWER ERECTION |  |  | STR P/O | STR F/S | OPGW STR
Agency |  |  |  | KEC International Limited | [26 empty] | TOTAL | COMP. | BAL. | TOTAL | COMP. | BAL.
[29 empty] | Date | 2026-06-16
PROGRESS AT A GLANCE : | [10 empty] | CROSSING PROPOSAL STATUS :
Sl. No. | Activity |  |  | UoM | Total Qty |  | Completed Till Date |  | Balance |  | Sl. No. | Type of Crossing |  | No. of X-ing | Apprd. | Bal
1 | Detailed Survey |  |  | Kms | 114.516 |  | 107.492 |  | 7.024 |  | 1 | PL X-ing
2 | Check Survey |  |  | Kms | 114.516 |  | 93.542 |  | 20.974 |  | 2 | 66 kV
3 | Soil Investigation |  |  | Nos. | 30 |  | 30 |  | 0 |  | 3 | 132 kV
4 | Foundation |  |  | Nos. | 293 |  | 92 |  | 201 |  | 4 | 220 kV
5 | Earthing |  |  | Nos. | 293 |  | 85 |  | 208 |  | 5 | 400 kV
6 | Erection |  |  | Nos. | 293 |  | 45 |  | 248 |  | 6 | 765 kV
7 | Tack Welding |  |  | Nos. | 293 |  | 13 |  | 280 |  | 7 | #VALUE!
8 | Stringing (P/O) |  |  | Kms | 114.516 |  | 0 |  | 114.516 |  | 8 | #VALUE!
9 | Stringing (F/S) |  |  | Kms | 114.516 |  | 0 |  | 114.516 |  | 9 | #VALUE!
10 | OPGW Stringing |  |  | Kms | 114.516 |  | 0 |  | 114.516 |  | 10 | #VALUE! | [27 empty] | FDN | ERC
[40 empty] | 92 | 45
| 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15
| 117/0 |  | 118/0 |  | 119/0 |  | 119/1 |  | 120/0 |  | 121/0 |  | 122/0 |  | 123/0 |  | 124/0 |  | 124/1 |  | 124/2 |  | 124/3 |  | 124/4 |  | 124/5 |  | 124/6
[13 empty] | Stub N/A |  | Stub N/A
| Stub N/A | 393.72 | Stub N/A | 225.97 | Stub N/A | 193.84 | Stub N/A | 401.38 | Stub N/A | 284.73 | Stub N/A | 238.17 |  | 164.96 |  | 343 | Stub N/A | 453 | Stub N/A | 369 | Stub N/A | 405 | Stub N/A | 416 | Stub N/A | 420 | Stub N/A | 364 | Stub N/A | 401
| 5DB2+3 |  | 5DD60+25 |  | 5DD60+25 |  | 5DB1+9 |  | CDDN+55 |  | CDDN+55 |  | CDDN+55 |  | CDDN+55 |  | 5DD45+9 |  | 5DA+0 |  | 5DA-3 |  | 5DB1+0 |  | 5DA+0 |  | 5DA+0 |  | 5DA+0
765KV ANTL Line
| 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30
| 124/7 |  | 124/8 |  | 124/9 |  | 124/10 |  | 124/11 |  | 124/12 |  | 131/0 |  | 131/1 |  | 131/2 |  | 132/0 |  | 132/1 |  | 133/0 |  | 133/1 |  | 133/2 |  | 134/0
[40 empty] | 4 | 1
| Stub N/A | 412 | Stub N/A | 405 | Stub N/A | 391 | Stub N/A | 397 | Stub N/A | 390 | Stub N/A | 397.5 | Stub N/A | 591 | Stub N/A | 534 | Stub N/A | 799 | Stub N/A | 321 | Stub N/A | 449 |  | 412.999 |  | 390 |  | 377.199 |  | 374.428
| 5DB1+0 |  | 5DA+0 |  | 5DA+0 |  | 5DA+0 |  | 5DA+0 |  | 5DA+9 |  | DD60+35(S) |  | DD45+9 |  | DD60+55 |  | DD60+55 |  | DB1+18 |  | DC2+0 |  | DA+3 |  | DA+0 |  | DC2+0
[7 empty] | Reserve Forest Approval Pending | [9 empty] | Mahi River
[31 empty] | 10 | 2 | 8 | 10 | 1 | 9
| 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45
| 135/0 |  | 136/0 |  | 137/0 |  | 138/0 |  | 138/1 |  | 138/2 |  | 138/3 |  | 139/0 |  | 139/1 |  | 139/2 |  | 139/3 |  | 139/4 |  | 139/5 |  | 140/0 |  | 140/1
[40 empty] | 15 | 9
|  | 421.994 |  | 232.608 |  | 216.641 |  | 355.998 |  | 384 |  | 362 |  | 307.028 |  | 379.002 |  | 412 |  | 429 |  | 408 |  | 395 |  | 380.686 |  | 410.997 |  | 413
| DB1+6 |  | DD60+0 |  | DD45+0 |  | DD60+0 |  | DA+0 |  | DA+0 |  | DA-3 |  | DD60+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DD45+0 |  | DA+3
[31 empty] | 10 | 10 | 0 | 10 | 10 | 0 | 1.273 | 1.273
| 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60
| 140/2 |  | 141/0 |  | 141/1 |  | 141/2 |  | 142/0 |  | 143/0 |  | 143/1 |  | 143/2 |  | 144/0 |  | 145/0 |  | 145/1 |  | 145/2 |  | 145/3 |  | 145/4 |  | 145/5
[23 empty] | ROW | [16 empty] | 14 | 14
|  | 386.816 |  | 324.004 |  | 416 |  | 404.53 |  | 374.076 |  | 423.003 |  | 420 |  | 375.064 |  | 417.215 |  | 498.001 |  | 448 |  | 394 |  | 383 |  | 379 |  | 380.837
| DA+0 |  | DB2+0 |  | DA+0 |  | DA+6 |  | DB2+0 |  | DC2+0 |  | DA+3 |  | DA+0 |  | DB1+0 |  | DB2+9 |  | DB1+9 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0
[31 empty] | 10 | 9 | 1 | 10 | 7 | 3 | 0.915 | 0.915
[31 empty] | 10 | 10 | 0 | 6 | 9 | -3
| 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70 |  | 71 |  | 72 |  | 73 |  | 74 |  | 75
| 146/0 |  | 146/1 |  | 146/2 |  | 146/3 |  | 146A/0 |  | 146A/1 |  | 147/0 |  | 147/1 |  | 147/2 |  | 148/0 |  | 148/1 |  | 148/2 |  | 148/3 |  | 148/4 |  | 148/5
[40 empty] | 14 | 14
|  | 366.003 |  | 376 |  | 368 |  | 373.965 |  | 373.005 |  | 362.45 |  | 323 |  | 299 |  | 350.381 |  | 333.997 |  | 394 |  | 363 |  | 413 |  | 376 |  | 388
| DD45+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA-3 |  | DD60+0 |  | DA-3 |  | DA-3 |  | DC1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0
| 76 |  | 77 |  | 78 |  | 79 |  | 80 |  | 81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90
| 148/6 |  | 148/7 |  | 148A/0 |  | 148B/0 |  | 149/0 |  | 150/0 |  | 150/1 |  | 150/2 |  | 150/3 |  | 150/4 |  | 150/5 |  | 151/0 |  | 152/0 |  | 152/1 |  | 153/0
[40 empty] | 7 | 2
|  | 378 |  | 342.706 |  | 259.342 |  | 268 |  | 276.41 |  | 438.126 |  | 399.671 |  | 438.276 |  | 400 |  | 440 |  | 375 |  | 298.193 |  | 348 |  | 422 |  | 242.877
[31 empty] | 10 | 7 | 3 | 10 | 5 | 5
| DA+0 |  | DA+0 |  | DC2+0 |  | DC1+0 |  | DD60+3 |  | DD60+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DD60+3 |  | DD60+6 |  | DA+9 |  | DD60+0
| 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100 |  | 101 |  | 102 |  | 103 |  | 104 |  | 105
| 153/1 |  | 154/0 |  | 154/1 |  | 154/2 |  | 155/0 |  | 155/1 |  | 155/2 |  | 155/3 |  | 155/4 |  | 155/5 |  | 156/0 |  | 156/1 |  | 156/2 |  | 156/3 |  | 156/4
[7 empty] | ROW | [32 empty] | 14 | 0 | 51 | 52 | 53 |  | 54 |  | 55 | 56 | 57 | 58 | 59 | 60
|  | 234.98 |  | 375.72 |  | 348 |  | 355.504 |  | 380.679 |  | 408 |  | 413 |  | 381 |  | 364 |  | 404.71 |  | 406.001 |  | 402 |  | 365 |  | 420 |  | 408.999 | [11 empty] | 127/4 | 127/5 | 128/0 |  | 129/0 |  | 129A/0 | 129A/1 | 129A/2 | 130/0 | 130/1 | 130/2
| DA+0 |  | DC2+0 |  | DC1+0 |  | DA-3 |  | DB2+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DB2+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3
TP
[42 empty] | WPS | WPS | WPS |  | WPS |  | WPS | WPS | WPS | WPS
| 106 |  | 107 |  | 108 |  | 109 |  | 110 |  | 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120
| 156/5 |  | 156/6 |  | 157/0 |  | 157/1 |  | 157/2 |  | 157/3 |  | 157A/0 |  | 157B/0 |  | 157B/1 |  | 158/0 |  | 158/1 |  | 158/2 |  | 159/0 |  | 159/1 |  | 159/2 | [12 empty] | DA+3 | DA+3 | DD60+6 |  | DD60+6 |  | DC1+0 | DA+0 | DA+3 | DB1+0 | DA+0 | DA+3
3-GAS PIPELINE
RLY X-ING (NOT IN USE)
[40 empty] | 4 | 0
| ROW | 388.001 | ROW | 348.628 | ROW | 424.14 |  | 412 |  | 406 |  | 370.192 |  | 378.534 |  | 408.004 |  | 405.551 |  | 405.999 |  | 386 |  | 408.363 |  | 380.997 |  | 426.001 |  | 394.475
| DA+0 |  | DA+0 |  | DB2+0 |  | DA+6 |  | DA+3 |  | DA+0 |  | DC2+0 |  | DD45+9 |  | DA+0 |  | DC1+3 |  | DA+0 |  | DA+0 |  | DD45+3 |  | DA+6 |  | DA+0
| 120 |  | 121 |  | 123 |  | 124 |  | 125 |  | 126 |  | 127 |  | 128 |  | 129 |  | 130 |  | 131 |  | 132 |  | 133 |  | 134 |  | 135
| 160/0 |  | 160/1 |  | 160/2 |  | 160/3 |  | 161/0 |  | 161/1 |  | 161A/0 |  | 161A/1 |  | 161A/2 |  | 161A/3 |  | 161A/4 |  | 161A/5 |  | 161A/6 |  | 161B/0 |  | 161C/0
[5 empty] | ROW | [34 empty] | 1 | 0
|  | 411.004 | ROW | 423 |  | 395 |  | 358.324 |  | 409.996 |  | 399.882 |  | 410.998 |  | 402 |  | 422 |  | 409 |  | 394 |  | 393 |  | 405.061 |  | 404.975 |  | 382.005
| DC2+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DD45+0 |  | DA+3 |  | DD45+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DC1+0 |  | DC2+3
| 136 |  | 137 |  | 138 |  | 139 |  | 140 |  | 141 |  | 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150
| 161C/1 |  | 162/0 |  | 163/0 |  | 163/1 |  | 163/2 |  | 163/3 |  | 163/4 |  | 164/0 |  | 164/1 |  | 165/0 |  | 165/1 |  | 165/2 |  | 166/0 |  | 167/0 |  | 167/1
|  | 428.053 |  | 155.725 |  | 387 |  | 344 |  | 384 |  | 391 |  | 426 |  | 328.995 |  | 428.039 |  | 314 |  | 365.78 |  | 407 | ROW | 276 | ROW | 410 |  | 418 | [9 empty] | 1 | 0
| DA+0 |  | DD60+6 |  | DD45+6 |  | DA-3 |  | DC1+0 |  | DA+0 |  | DA+0 |  | DB1+6 |  | DA+9 |  | DD45+0 |  | DA+0 |  | DA-3 |  | DD60+6 |  | DD60+3 |  | DA+3
[31 empty] | 10 | 7 | 3 | 4 | 6 | 5
[31 empty] | 10 | 3 | 7 | 9 |  | 5
| 151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137
| 167/2 |  | 167/3 |  | 167/4 |  | 167/5 |  | 167/6 |  | 168/0 |  | 169/0 |  | 170/0 |  | 170/1 |  | 170/2 |  | 170/3 |  | 170/4 |  | 171/0
[40 empty] | 3 | 0
|  | 383 |  | 409 |  | 420 |  | 414 |  | 406 |  | 403.139 |  | 381.59 |  | 357.996 |  | 365 |  | 378 |  | 370 |  | 437.534
| DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DD45+0 |  | DC2+3 |  | DD60+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+9
| 139 |  | 140 |  | 141 |  | 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150 |  | 151 |  | 152 |  | 153
| 177/0 |  | 178/0 |  | 178/1 |  | 178/2 |  | 178/3 |  | 178A/0 |  | 178A/1 |  | 178A/2 |  | 179/0 |  | 180/0 |  | 180/1 |  | 181/0 |  | 182/0 |  | 182/0 |  | 183/0
|  | 225.81 | ROW | 451 | ROW | 385 |  | 429 |  | 408 | ROW | 407 | ROW | 434 |  | 401 |  | 296 |  | 677 |  | 642 |  | 414 |  | 446 |  | 411 |  | 345
DA-3
| 154 |  | 155 |  | 156
| 183/1 |  | 183/2 |  | 184/0
|  | 345 |  | 372
| DC2+0 |  | DA+9 |  | DA+0
| 157 |  | 158 |  | 159 |  | 160 |  | 161 |  | 162 |  | 163 |  | 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170 |  | 171
| 185/0 |  | 186/0 |  | 186/1 |  | 186/2 |  | 186/3 |  | 186/4 |  | 186/5 |  | 186/6 |  | 187/0 |  | 187/1 |  | 187/2 |  | 187/3 |  | 187/4 |  | 187/5 |  | 187/6
| ROW | 244 | ROW | 390 |  | 377 |  | 382 |  | 390 |  | 364 |  | 390 |  | 395 | ROW | 413 |  | 422 |  | 306 |  | 357 |  | 390 |  | 430 |  | 399 | [9 empty] | 1 | 1
| DB2+0 |  | DC1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DB2+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3
| 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180 |  | 181 |  | 182 |  | 183 |  | 184 |  | 185 |  | 186
| 188/0 |  | 188/1 |  | 188/2 |  | 189/0 |  | 190/0 |  | 190/1 |  | 190/2 |  | 190/3 |  | 190/4 |  | 191/0 |  | 191/1 |  | 191/2 |  | 191/3 |  | 191/4 |  | 191/5
[40 empty] | 0 | 0
|  | 414 |  | 421 |  | 356 |  | 243 | ROW | 372 |  | 398 |  | 346 |  | 405 |  | 417 |  | 402 |  | 415 |  | 352 |  | 397 |  | 377 |  | 438
| DC2+0 |  | DA+3 |  | DA+0 |  | DC1+0 |  | DD45+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DC1+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0
| 187 |  | 188 |  | 189 |  | 190 |  | 191 |  | 192 |  | 193 |  | 194 |  | 196 |  | 197 |  | 198 |  | 199 |  | 200 |  | 201 |  | 202
| 191/6 |  | 192/0 |  | 192/1 |  | 192/2 |  | 192/3 |  | 192/4 |  | 192/5 |  | 192/6 |  | 192/7 |  | 192/8 |  | 192/9 |  | 192/10 |  | 192/11 |  | 192/12 |  | 192/13
|  | 363 | ROW | 380 |  | 346 |  | 390 | ROW | 405 |  | 421 |  | 391 | ROW | 394 |  | 382 |  | 384 |  | 406 |  | 352 |  | 453 |  | 388 |  | 395 | [9 empty] | 7 | 3
| DA+6 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DA+0
| 193/0 |  | 193/1 |  | 193/2 |  | 193/3 |  | 193/4 |  | 193/5 |  | 194/0 |  | 194/1 |  | 194/2 |  | 194/3 |  | 194/4 |  | 194/5 |  | 194/6 |  | 195/0 |  | 196/0
|  | 430 |  | 388 |  | 402 |  | 437 |  | 405 |  | 337 |  | 282 |  | 435 |  | 407 |  | 426 |  | 374 |  | 440 |  | 386 |  | 210 | [11 empty] | 7 | 1
| DC1+3 |  | DA+3 |  | DA+0 |  | DB1+3 |  | DA+3 |  | DA+0 |  | DB1+0 |  | DA+6 |  | DA+0 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+0 |  | DB2+0 |  | DB2+0
GAS PIPELINE

## Pile Foundation
ASOTL Pile
Sl. No. | Location No. | Tower Type | Classification | Concreting Volume in M3 | Starting Date | Todays Status | Cumulative Status | Completion Date | Remarks | Gang name | Earthing Status | Earthing Completion Date | Manpower
1 | 131/1 | DD45+9 | Pile |  | 2026-04-13 | work hampered due to forest dept. approval pending |  |  |  | Chowdhary Const. |  |  | 25

## Sheet6 (hidden)
Sr No. | Location | TOT | Start | End
1 | 117/1 | DA-3 | 2026-01-15 | 2026-01-21
2 | 119/1 | DA-3 | 2026-01-09 | 2026-01-15
3 | 120/0 | DD60+3 | 2026-01-21 | 2026-01-31
4 | 120/4 | DA+0 | 2025-12-28 | 2026-01-02
5 | 120/7 | DA+3 | 2025-12-28 | 2026-01-09
6 | 121/2 | DA+9 | 2025-12-30 | 2026-01-19
7 | 121/3 | DA+0 | 2026-01-19 | 2026-01-30
8 | 126/1 | DA+3 | 2025-12-30 | 2026-01-18
9 | 137/0 | DB2+3 | 2026-01-04 | 2026-01-12
10 | 137/1 | DA+6 | 2026-01-22 | 2026-01-31
11 | 137/2 | DA-3 | 2025-12-28 | 2026-01-04
12 | 138/0 | DC2+6 | 2026-01-12 | 2026-01-22
13 | 141/2 | DA+0 | 2026-01-02 | 2026-01-04
14 | 141/3 | DA+0 | 2026-01-04 | 2026-01-09
15 | 141/5 | DA-3 | 2026-01-09 | 2026-01-13
16 | 142/0 | DC1+9 | 2025-12-19 | 2026-01-29
17 | 143/0 | DD60+18 | 2026-01-13 | 2026-01-28
18 | 145/3 | DA-3 | 2026-01-15 | 2026-01-19
19 | 145/4 | DA+0 | 2026-01-09 | 2026-01-15
20 | 145/5 | DA+3 | 2025-12-28 | 2026-01-04
21 | 145/6 | DA+3 | 2026-01-04 | 2026-01-09
22 | 145/7 | DB1+0 | 2026-01-19 | 2026-01-25
23 | 148/1 | DA+3 | 2026-01-25 | 2026-01-31
24 | 148/3 | DA+6 | 2026-01-06 | 2026-01-21
25 | 148/4 | DA+3 | 2025-12-20 | 2026-01-06
26 | 148/5 | DB1+3 | 2026-01-21 | 2026-01-31
27 | 175/0 | DC2+6 | 2026-01-06 | 2026-01-15
28 | 175/1 | DB1+9 | 2025-12-28 | 2026-01-06
29 | 180/3 | DA+9 | 2025-12-29 | 2026-01-23
30 | 180/4 | DA-3 | 2025-12-30 | 2026-01-15
31 | 180/6 | DA+0 | 2026-01-06 | 2026-01-19
32 | 182/0 | DD45+0 | 2026-01-03 | 2026-01-29
33 | 183/0 | DD60+0 | 2026-01-11 | 2026-01-25
34 | 190/0 | DD60+9 | 2026-01-17 | 2026-01-30
35 | 197/2 | DA-3 | 2026-01-15 | 2026-01-21
36 | 199/0 | DD60+6 | 2026-01-21 | 2026-01-30
37 | 241/2 | DA+0 | 2026-01-14 | 2026-01-28
38 | 243/1 | DA+0 | 2025-12-29 | 2026-01-21
39 | 246/0 | DD45+9 | 2026-01-03 | 2026-01-31
40 | 248/1 | DB1+9 | 2025-12-26 | 2026-01-14
41 | 249/3 | DA+3 | 2025-12-24 | 2026-01-04
42 | 250/3 | DA+9 | 2025-12-23 | 2026-01-03
43 | 250A/1 | DA+6 | 2026-01-13 | 2026-01-23
44 | 250A/2 | DA+0 | 2026-01-04 | 2026-01-13
45 | 252/5 | DB1+9 | 2026-01-02 | 2026-01-19

## Sheet4 (hidden)
|  | 117/1 | 117/2 | 118/0 | 119/0 | 119/1 | 119/2 | 119/3 | 120/0 | 120/1 | 120/2 | 120/3 | 120/4 | 120/5 | 120/6 | 120/7 | 121/0 | 121/1 | 121/2 | 121/3 | 121/4 | 121/5 | 121/6 | 121/7 | 121/8 | 121/9 | 121/10 | 121/11 | 124/0 | 124/1 | 124/2 | 124/3 | 125/0 | 125/1 | 125/2 | 126/0 | 126/1 | 126/2 | 126/3 | 127/0 | 127/1 | 127/2 | 128/0 | 129/0 | 130/0 | 131/0 | 131/1 | 131/2 | 131/3 | 131/4 | 131/5 | 132/0 | 132/1 | 132/2 | 132/3 | 133/0 | 133/1 | 133/2 | 133/3 | 133/4 | 134/0 | 135/0 | 136/0 | 136/1 | 137/0 | 137/1 | 137/2 | 138/0 | 139/0 | 139/1 | 139/2 | 139/3 | 140/0 | 141/0 | 141/1 | 141/2 | 141/3 | 141/4 | 141/5 | 141/6 | 142/0 | 143/0 | 144/0 | 145/0 | 145/1 | 145/2 | 145/3 | 145/4 | 145/5 | 145/6 | 145/7 | 147/0 | 148/0 | 148/1 | 148/2 | 148/3 | 148/4 | 148/5 | 149/0 | 150/0 | 150/1 | 151/0 | 151A/0 | 152/0 | 153/0 | 153/1 | 153/2 | 153A/0 | 154/0 | 155/0 | 156/0 | 156/1 | 157/0 | 158/0 | 159/0 | 160/0 | 161/0 | 162/0 | 163/0 | 163/1 | 164/0 | 165/0 | 165/1 | 165/2 | 165/3 | 165/4 | 165/5 | 165/6 | 165/7 | 166/0 | 167/0 | 168/0 | 169/0 | 170/0 | 171/0 | 172/0 | 172/1 | 173/0 | 174/0 | 174/1 | 174/2 | 174/3 | 174/4 | 174/5 | 174/6 | 175/0 | 175/1 | 176/0 | 176/1 | 176/2 | 177/0 | 178/0 | 178/1 | 178/2 | 178/3 | 179/0 | 179/1 | 179/2 | 179/3 | 180/0 | 180/1 | 180/2 | 180/3 | 180/4 | 180/5 | 180/6 | 180/7 | 182/0 | 183/0 | 183/1 | 183/2 | 183/3 | 184/0 | 185/0 | 186/0 | 187/0 | 188/0 | 189/0 | 189/1 | 190/0 | 191/0 | 191/1 | 192/0 | 193/0 | 194/0 | 194/1 | 195/0 | 196/0 | 196/1 | 196/2 | 197/0 | 197/1 | 197/2 | 198/0 | 199/0 | 199/1 | 199/2 | 200/0 | 200/1 | 201/0 | 202/0 | 203/0 | 203/1 | 204/0 | 205/0 | 205/1 | 205/2 | 206/0 | 206/1 | 207/0 | 208/0 | 209/0 | 209/1 | 209/2 | 210/0 | 211/0 | 211/1 | 211/2 | 211/3 | 211/4 | 211/5 | 212/0 | 213/0 | 214/0 | 214/1 | 214/2 | 214/3 | 214/4 | 214/5 | 214/6 | 214/7 | 215/0 | 216/0 | 216/1 | 216/2 | 216/3 | 217/0 | 217/1 | 217/2 | 217/3 | 217/4 | 217/5 | 218/0 | 219/0 | 219/1 | 220/0 | 220/1 | 221/0 | 222/0 | 223/0 | 223/1 | 223/2 | 223/3 | 224/0 | 224/1 | 224/2 | 225/0 | 225/1 | 225/2 | 225/3 | 225/4 | 225/5 | 225/6 | 225/7 | 226/0 | 226/1 | 226/2 | 226/3 | 227/0 | 227/1 | 227/2 | 228/0 | 228/1 | 229/0 | 229/1 | 229A/0 | 229B/0 | 230/0 | 230/1 | 230A/0 | 231/0 | 232/0 | 232/1 | 232/2 | 232/3 | 232/4 | 233/0 | 234/0 | 235/0 | 235/1 | 235/2 | 235/3 | 235/4 | 236/0 | 237/0 | 238/0 | 239/0 | 239/1 | 240/0 | 240/1 | 241/0 | 241/1 | 241/2 | 241/3 | 241/4 | 242/0 | 243/0 | 243/1 | 243/2 | 243/3 | 244/0 | 244/1 | 244/2 | 244/3 | 244/4 | 244/5 | 244/6 | 245/0 | 245/1 | 246/0 | 247/0 | 248/0 | 248/1 | 248/2 | 249/0 | 249/1 | 249/2 | 249/3 | 250/0 | 250/1 | 250/2 | 250/3 | 250A/0 | 250A/1 | 250A/2 | 251/0 | 251/1 | 252/0 | 252/1 | 252/2 | 252/3 | 252/4 | 252/5 | 253/0 | 254/0 | 254/1 | 255/0 | 255/1 | 256/0 | 256/1 | 257/0 | 258/0
|  | DA-3 | DA+6 | DB2+0 | DD60+0 | DA-3 | DA-3 | DA+9 | DD60+3 | DA-3 | DA+0 | DA+6 | DA+0 | DA-3 | DA+0 | DA+3 | DB2+9 | DB1+25 | DA+9 | DA+0 | DA+0 | DA-3 | DA+0 | DB1+0 | DA+0 | DA+0 | DA+0 | DA+9 | DD45+3 | DA-3 | DA+0 | DA+0 | DC2+3 | DA+9 | DA+9 | DD45+3 | DA+3 | DA+0 | DA+0 | DB2+0 | DA-3 | DB1+9 | DD60+25 (2MRC) | DD45+25 (15.87MRC) | DD45+25 (11.9MRC) | DD60+9 (7MRC) | DA+3 | DA+0 | DA+3 | DA-3 | DA-3 | DB2+0 | DA-3 | DA-3 | DA-3 | DC1+0 | DA+0 | DB1+0 | DB1+0 | DA+3 | DD45+0 | DD60+3 | DD60+6 | DB1+9 | DB2+3 | DA+6 | DA-3 | DC2+6 | DD45+6 | DA+6 | DB2+0 | DB1+0 | DD60+25 | DD60+25 | DA+0 | DA+0 | DA+0 | DA-3 | DA-3 | DA+3 | DC1+9 | DD60+18 | DD60+18 | DD45+9 | DA+0 | DA+0 | DA-3 | DA+0 | DA+3 | DA+3 | DB1+0 | DD60+25 | DD60+25 | DA+3 | DA+0 | DA+6 | DA+3 | DB1+3 | DD60+25 | DD60+25 | DB1+0 | DD60+6 | DD60+18 | DD60+3 | DD60+3 | DA+3 | DA+0 | DD45+9 | DD60+9 | DD60+18 | DD45+18 | DB2+9 | DD60+41 | DD60+41 | DD60+9 (2MRC) | DC2+0 | DB1+3 | DD60+25 | DD60+30 | DB1+6 | DC2+6 | DB1+25 | DA+9 | DA+6 | DA+6 | DA-3 | DA-3 | DCT+0 | DA+0 | DD60+0 | DD60+9 | DD60+30 | DD60+25 | DD60+6 | DB1+18 | DD45+9 | DA+9 | DC2+18 | DD60+9 (2MRC) | DA+3 | DA+0 | DA+0 | DA+0 | DA+0 | DA+3 | DC2+6 | DB1+9 | DD45+0 | DA+0 | DA-3 | DD60+6 | DD60+6 | DA+0 | DA+0 | DA-3 | DB1+0 | DA+3 | DA+3 (A,B 1.5 RC) | DA+0 | DD45+0LE (3 Leg)+1.5LE (1 Leg) & (B1MRC & C0.5MRS) | DA+3 | DB1+3 | DA+9 | DA-3 | DA+3 | DA+0 | DA+0 | DD45+0 | DD60+0 | DA+0 | DA+0 | DA+3 | DB1+18 | DD45+25 | DC1+18 | DC1+0 | DD60+35 | DD60+35 | DA+9 | DD60+9 | DD60+9 | DB1+3 | DC2+9 | DD60+30 | DD60+30 | DB1+9 | DC1+18 | DB2+18 | DA+9 | DA+3 | DB1+0 | DA-3 | DA-3 | DD60+6 | DD60+6 | DA+3 | DA+6 | DC2+0 | DA+6 | DC1+9 | DC1+18 | DC1+18 | DB1+0 | DD60+25 (2MRC) | DD60+25 (3MRC) | DB2+9 | DA+9 | DC2+0 | DB1+6 | DD60+25 | DD45+35 | DD60+9 | DA+0 | DA-3 | DB2+9 (2MRC) | DB2+9 | DA-3 | DA+0 | DA+9 | DA-3 | DB1+9 | DD45+30 (2MRC) | DD60+35 | DD60+25 | DA+6 | DA-3 | DA-3 | DA-3 | DA+0 | DA+3 | DA+3 | DD60+3 | DD60+3 | DA+9 (2MRC) | DB1+18 (2MRC) | DA+9 | DC2+9 | DA+3 | DA+0 | DA+9 | DA+9 | DA+0 | DD60+3 | DD45+3 | DA+9 | DD45+0 | DA+6 | DD60+18 | DD60+25 | DC1+6 | DA+0 | DA+0 | DA-3 | DC1+0 | DA+3 | DB1+6 | DB2+0 | DA+9 | DA-3 | DA-3 | DA+3 | DA+0 | DA+0 | DA+6 | DB2+3 | DA+6 | DA+0 | DA+0 | DD45+0 | DA+6 | DA+3 | DD45+0 | DA+0 | DD45+0 | DA+9 | DB1+25 | DB2+25 | DC1+6 | DA+9 | DD45+0 | DB1+0 | DB1+0 | DA+0 | DA+0 | DA+0 | DA+3 | DC1+0 | DD60+18 | DD60+9 (2MRC) | DA+9 | DA+0 | DA+0 | DA+3 | DB2+18 | DB1+25 (2MRC) | DC1+25 | DD45+0 | DA+0 | DB2+0 | DA+3 | DD60+0 | DA+0 | DA+0 | DA+0 | DA+3 | DD60+3 | DD60+3 | DA+0 | DA+0 | DA+0 | DD45+0 | DA+0 | DA+0 | DA+3 | DA+3 | DA+0 | DA+3 | DD45+0 | DA+0 | DD45+9 | DD60+35 (2MRC) | DD60+35 (2MRC) | DB1+9 | DA+6 | DD60+3 | DA+9 | DA+3 | DA+3 | DD45+3 | DA+9 (1MRC) | DA+0 | DA+9 | DB1+3 (3MRC) | DA+6 | DA+0 | DD45+0 | DA+6 (1MRC) | DB2+0 | DA+0 | DA+3 | DA+6 | DA+0 | DB1+9 | DD45+35 (2MRC) | DD45+35 (2MRC) | DB1+9 | DD60+0 | DA+0 | DD60+0 | DA+9 | DC1+9 | DD60+0 (1.5MRC)
Loc No | Tower Type
118/0
117/1 | DA-3 | [5 empty] | 117/1
117/2 | DA+6 | [5 empty] | 117/2
118/0 | DB2+0 | [5 empty] | 118/0
119/0 | DD60+0 | [5 empty] | 119/0
119/1 | DA-3 | [5 empty] | 119/1
119/2 | DA-3 | [5 empty] | 119/2
119/3 | DA+9 | [5 empty] | 119/3
120/0 | DD60+3 | [5 empty] | 120/0
120/1 | DA-3 | [5 empty] | 120/1
120/2 | DA+0 | [5 empty] | 120/2
120/3 | DA+6 | [5 empty] | 120/3
120/4 | DA+0 | [6 empty] | 174/1
120/5 | DA-3 | [6 empty] | 174/2
120/6 | DA+0 | [6 empty] | 174/3
120/7 | DA+3 | [6 empty] | 174/4
121/0 | DB2+9 | [6 empty] | 174/5
121/1 | DB1+25 | [6 empty] | 174/6
121/10 | DA+0 | [6 empty] | 178/2
121/11 | DA+9 | [5 empty] | 121/11
121/2 | DA+9 | [6 empty] | 175/0
121/3 | DA+0 | [6 empty] | 175/1
121/4 | DA+0 | [6 empty] | 176/0
121/5 | DA-3 | [6 empty] | 176/1
121/6 | DA+0 | [6 empty] | 176/2
121/7 | DB1+0 | [6 empty] | 177/0
121/8 | DA+0 | [6 empty] | 178/0
121/9 | DA+0 | [6 empty] | 178/1
124/0 | DD45+3 | [6 empty] | 178/3
124/1 | DA-3 | [5 empty] | 124/1
124/2 | DA+0 | [5 empty] | 124/2
124/3 | DA+0 | [5 empty] | 124/3
125/0 | DC2+3 | [6 empty] | 180/1
125/1 | DA+9 | [6 empty] | 180/2
125/2 | DA+9 | [6 empty] | 180/3
126/0 | DD45+3 | [6 empty] | 180/4
126/1 | DA+3 | [6 empty] | 180/5
126/2 | DA+0 | [5 empty] | 126/2
126/3 | DA+0 | [6 empty] | 180/7
127/0 | DB2+0 | [5 empty] | 127/0
127/1 | DA-3 | [5 empty] | 127/1
127/2 | DB1+9 | [5 empty] | 127/2
128/0 | DD60+25 (2MRC) | [5 empty] | 128/0
129/0 | DD45+25 (15.87MRC) | [5 empty] | 129/0
130/0 | DD45+25 (11.9MRC) | [5 empty] | 130/0
131/0 | DD60+9 (7MRC) | [5 empty] | 131/0
131/1 | DA+3 | [5 empty] | 131/1
131/2 | DA+0 | [5 empty] | 131/2
131/3 | DA+3 | [5 empty] | 131/3
131/4 | DA-3 | [5 empty] | 131/4
131/5 | DA-3 | [5 empty] | 131/5
132/0 | DB2+0 | [5 empty] | 132/0
132/1 | DA-3 | [5 empty] | 132/1
132/2 | DA-3 | [5 empty] | 132/2
132/3 | DA-3 | [6 empty] | 186/0
133/0 | DC1+0 | [5 empty] | 133/0
133/1 | DA+0 | [5 empty] | 133/1
133/2 | DB1+0 | [5 empty] | 133/2
133/3 | DB1+0 | [5 empty] | 133/3
133/4 | DA+3 | [5 empty] | 133/4
134/0 | DD45+0 | [6 empty] | 191/0
135/0 | DD60+3 | [5 empty] | 135/0
136/0 | DD60+6 | [5 empty] | 136/0
136/1 | DB1+9 | [5 empty] | 136/1
137/0 | DB2+3 | [5 empty] | 137/0
137/1 | DA+6 | [5 empty] | 137/1
137/2 | DA-3 | [5 empty] | 137/2
138/0 | DC2+6 | [5 empty] | 138/0
139/0 | DD45+6 | [5 empty] | 139/0
139/1 | DA+6 | [5 empty] | 139/1
139/2 | DB2+0 | [5 empty] | 139/2
139/3 | DB1+0 | [5 empty] | 139/3
140/0 | DD60+25 | [5 empty] | 140/0
141/0 | DD60+25 | [5 empty] | 141/0
141/1 | DA+0 | [5 empty] | 141/1
141/2 | DA+0 | [5 empty] | 141/2
141/3 | DA+0 | [5 empty] | 141/3
141/4 | DA-3 | [5 empty] | 141/4
141/5 | DA-3 | [5 empty] | 141/5
141/6 | DA+3 | [5 empty] | 141/6
142/0 | DC1+9 | [5 empty] | 142/0
143/0 | DD60+18 | [6 empty] | 211/2
144/0 | DD60+18 | [5 empty] | 144/0
145/0 | DD45+9 | [5 empty] | 145/0
145/1 | DA+0 | [5 empty] | 145/1
145/2 | DA+0 | [6 empty] | 211/4
145/3 | DA-3 | [5 empty] | 145/3
145/4 | DA+0 | [5 empty] | 145/4
145/5 | DA+3 | [5 empty] | 145/5
145/6 | DA+3 | [5 empty] | 145/6
145/7 | DB1+0 | [5 empty] | 145/7
147/0 | DD60+25 | [5 empty] | 147/0
148/0 | DD60+25 | [5 empty] | 148/0
148/1 | DA+3 | [5 empty] | 148/1
148/2 | DA+0 | [5 empty] | 148/2
148/3 | DA+6 | [5 empty] | 148/3
148/4 | DA+3 | [5 empty] | 148/4
148/5 | DB1+3 | [5 empty] | 148/5
149/0 | DD60+25 | [5 empty] | 149/0
150/0 | DD60+25 | [5 empty] | 150/0
150/1 | DB1+0 | [5 empty] | 150/1
151/0 | DD60+6 | [5 empty] | 151/0
151A/0 | DD60+18 | [5 empty] | 151A/0
152/0 | DD60+3 | [5 empty] | 152/0
153/0 | DD60+3 | [5 empty] | 153/0
153/1 | DA+3 | [5 empty] | 153/1
153/2 | DA+0 | [5 empty] | 153/2
153A/0 | DD45+9 | [5 empty] | 153A/0
154/0 | DD60+9 | [5 empty] | 154/0
155/0 | DD60+18 | [5 empty] | 155/0
156/0 | DD45+18 | [5 empty] | 156/0
156/1 | DB2+9 | [5 empty] | 156/1
157/0 | DD60+41 | [6 empty] | 124/3
158/0 | DD60+41 | [5 empty] | 158/0
159/0 | DD60+9 (2MRC) | [5 empty] | 159/0
160/0 | DC2+0 | [5 empty] | 160/0
161/0 | DB1+3 | [5 empty] | 161/0
162/0 | DD60+25 | [5 empty] | 162/0
163/0 | DD60+30 | [5 empty] | 163/0
163/1 | DB1+6 | [5 empty] | 163/1
164/0 | DC2+6 | [5 empty] | 164/0
165/0 | DB1+25 | [5 empty] | 165/0
165/1 | DA+9 | [5 empty] | 165/1
165/2 | DA+6 | [5 empty] | 165/2
165/3 | DA+6 | [5 empty] | 165/3
165/4 | DA-3 | [6 empty] | 217/2
165/5 | DA-3 | [5 empty] | 165/5
165/6 | DCT+0 | [5 empty] | 165/6
165/7 | DA+0 | [5 empty] | 165/7
166/0 | DD60+0 | [5 empty] | 166/0
167/0 | DD60+9 | [5 empty] | 167/0
168/0 | DD60+30 | [5 empty] | 168/0
169/0 | DD60+25 | [5 empty] | 169/0
170/0 | DD60+6 | [5 empty] | 170/0
171/0 | DB1+18 | [5 empty] | 171/0
172/0 | DD45+9 | [6 empty] | 222/0
172/1 | DA+9 | [5 empty] | 172/1
173/0 | DC2+18 | [5 empty] | 173/0
174/0 | DD60+9 (2MRC) | [5 empty] | 174/0
174/1 | DA+3 | [5 empty] | 174/1
174/2 | DA+0 | [5 empty] | 174/2
174/3 | DA+0 | [5 empty] | 174/3
174/4 | DA+0 | [5 empty] | 174/4
174/5 | DA+0 | [5 empty] | 174/5
174/6 | DA+3 | [5 empty] | 174/6
175/0 | DC2+6 | [5 empty] | 175/0
175/1 | DB1+9 | [5 empty] | 175/1
176/0 | DD45+0 | [6 empty] | 225/3
176/1 | DA+0 | [6 empty] | 225/4
176/2 | DA-3 | [6 empty] | 226/3
177/0 | DD60+6 | [6 empty] | 227/0
178/0 | DD60+6 | [6 empty] | 227/1
178/1 | DA+0 | [6 empty] | 228/0
178/2 | DA+0 | [6 empty] | 228/1
178/3 | DA-3 | [6 empty] | 230/0
179/0 | DB1+0 | [6 empty] | 232/4
179/1 | DA+3 | [6 empty] | 233/0
179/2 | DA+3 (A,B 1.5 RC) | [5 empty] | 179/2
179/3 | DA+0 | [6 empty] | 235/0
180/0 | DD45+0LE (3 Leg)+1.5LE (1 Leg) & (B1MRC & C0.5MRS) | [5 empty] | 180/0
180/1 | DA+3 | [6 empty] | 235/1
180/2 | DB1+3 | [6 empty] | 235/2
180/3 | DA+9 | [6 empty] | 235/3
180/4 | DA-3 | [6 empty] | 236/0
180/5 | DA+3 | [6 empty] | 237/0
180/6 | DA+0 | [5 empty] | 180/6
180/7 | DA+0 | [5 empty] | 180/7
182/0 | DD45+0 | [5 empty] | 182/0
183/0 | DD60+0 | [5 empty] | 183/0
183/1 | DA+0 | [5 empty] | 183/1
183/2 | DA+0 | [5 empty] | 183/2
183/3 | DA+3 | [5 empty] | 183/3
184/0 | DB1+18 | [5 empty] | 184/0
185/0 | DD45+25 | [6 empty] | 243/0
186/0 | DC1+18 | [5 empty] | 186/0
187/0 | DC1+0 | [5 empty] | 187/0
188/0 | DD60+35 | [5 empty] | 188/0
189/0 | DD60+35 | [5 empty] | 189/0
189/1 | DA+9 | [5 empty] | 189/1
190/0 | DD60+9 | [5 empty] | 190/0
191/0 | DD60+9 | [5 empty] | 191/0
191/1 | DB1+3 | [5 empty] | 191/1
192/0 | DC2+9 | [5 empty] | 192/0
193/0 | DD60+30 | [5 empty] | 193/0
194/0 | DD60+30 | [5 empty] | 194/0
194/1 | DB1+9 | [5 empty] | 194/1
195/0 | DC1+18 | [5 empty] | 195/0
196/0 | DB2+18 | [5 empty] | 196/0
196/1 | DA+9 | [5 empty] | 196/1
196/2 | DA+3 | [5 empty] | 196/2
197/0 | DB1+0 | [5 empty] | 197/0
197/1 | DA-3 | [5 empty] | 197/1
197/2 | DA-3 | [5 empty] | 197/2
198/0 | DD60+6 | [5 empty] | 198/0
199/0 | DD60+6 | [5 empty] | 199/0
199/1 | DA+3 | [5 empty] | 199/1
199/2 | DA+6 | [5 empty] | 199/2
200/0 | DC2+0 | [6 empty] | 133/0
200/1 | DA+6 | [6 empty] | 133/1
201/0 | DC1+9 | [6 empty] | 133/2
202/0 | DC1+18 | [6 empty] | 133/4
203/0 | DC1+18 | [5 empty] | 203/0
203/1 | DB1+0 | [6 empty] | 136/0
204/0 | DD60+25 (2MRC) | [6 empty] | 136/1
205/0 | DD60+25 (3MRC) | [6 empty] | 137/0
205/1 | DB2+9 | [5 empty] | 205/1
205/2 | DA+9 | [5 empty] | 205/2
206/0 | DC2+0 | [6 empty] | 138/0
206/1 | DB1+6 | [5 empty] | 206/1
207/0 | DD60+25 | [5 empty] | 207/0
208/0 | DD45+35 | [5 empty] | 208/0
209/0 | DD60+9 | [5 empty] | 209/0
209/1 | DA+0 | [6 empty] | 140/0
209/2 | DA-3 | [5 empty] | 209/2
210/0 | DB2+9 (2MRC) | [6 empty] | 250/2
211/0 | DB2+9 | [5 empty] | 211/0
211/1 | DA-3 | [5 empty] | 211/1
211/2 | DA+0 | [5 empty] | 211/2
211/3 | DA+9 | [5 empty] | 211/3
211/4 | DA-3 | [5 empty] | 211/4
211/5 | DB1+9 | [5 empty] | 211/5
212/0 | DD45+30 (2MRC) | [5 empty] | 212/0
213/0 | DD60+35 | [5 empty] | 213/0
214/0 | DD60+25 | [5 empty] | 214/0
214/1 | DA+6 | [5 empty] | 214/1
214/2 | DA-3 | [5 empty] | 214/2
214/3 | DA-3 | [5 empty] | 214/3
214/4 | DA-3 | [5 empty] | 214/4
214/5 | DA+0 | [5 empty] | 214/5
214/6 | DA+3 | [5 empty] | 214/6
214/7 | DA+3 | [5 empty] | 214/7
215/0 | DD60+3 | [5 empty] | 215/0
216/0 | DD60+3 | [5 empty] | 216/0
216/1 | DA+9 (2MRC)
216/2 | DB1+18 (2MRC)
216/3 | DA+9
217/0 | DC2+9
217/1 | DA+3
217/2 | DA+0
217/3 | DA+9 | [5 empty] | 217/3
217/4 | DA+9 | [5 empty] | 217/4
217/5 | DA+0 | [5 empty] | 217/5
218/0 | DD60+3 | [6 empty] | 119/0
219/0 | DD45+3 | [5 empty] | 219/0
219/1 | DA+9 | [5 empty] | 219/1
220/0 | DD45+0 | [6 empty] | 120/7
220/1 | DA+6 | [6 empty] | 120/2
221/0 | DD60+18 | [6 empty] | 120/3
222/0 | DD60+25 | [6 empty] | 120/4
223/0 | DC1+6 | [5 empty] | 223/0
223/1 | DA+0 | [6 empty] | 120/6
223/2 | DA+0 | [6 empty] | 121/10
223/3 | DA-3 | [6 empty] | 119/1
224/0 | DC1+0 | [6 empty] | 121/4
224/1 | DA+3 | [6 empty] | 121/7
224/2 | DB1+6 | [6 empty] | 131/2
225/0 | DB2+0 | [6 empty] | 132/0
225/1 | DA+9 | [5 empty] | 225/1
225/2 | DA-3 | [5 empty] | 225/2
225/3 | DA-3 | [6 empty] | 141/1
225/4 | DA+3 | [5 empty] | 225/4
225/5 | DA+0 | [5 empty] | 225/5
225/6 | DA+0 | [6 empty] | 141/2
225/7 | DA+6 | [5 empty] | 225/7
226/0 | DB2+3 | [5 empty] | 226/0
226/1 | DA+6 | [5 empty] | 226/1
226/2 | DA+0 | [5 empty] | 226/2
226/3 | DA+0 | [5 empty] | 226/3
227/0 | DD45+0 | [5 empty] | 227/0
227/1 | DA+6 | [5 empty] | 227/1
227/2 | DA+3 | [5 empty] | 227/2
228/0 | DD45+0 | [6 empty] | 148/4
228/1 | DA+0 | [5 empty] | 228/1
229/0 | DD45+0 | [5 empty] | 229/0
229/1 | DA+9 | [5 empty] | 229/1
229A/0 | DB1+25 | [5 empty] | 229A/0
229B/0 | DB2+25 | [5 empty] | 229B/0
230/0 | DC1+6 | [5 empty] | 230/0
230/1 | DA+9 | [5 empty] | 230/1
230A/0 | DD45+0 | [5 empty] | 230A/0
231/0 | DB1+0 | [5 empty] | 231/0
232/0 | DB1+0 | [5 empty] | 232/0
232/1 | DA+0 | [5 empty] | 232/1
232/2 | DA+0 | [5 empty] | 232/2
232/3 | DA+0 | [5 empty] | 232/3
232/4 | DA+3 | [5 empty] | 232/4
233/0 | DC1+0 | [6 empty] | 141/3
234/0 | DD60+18 | [5 empty] | 234/0
235/0 | DD60+9 (2MRC) | [6 empty] | 137/0
235/1 | DA+9 | [5 empty] | 235/1
235/2 | DA+0 | [6 empty] | 145/6
235/3 | DA+0 | [5 empty] | 235/3
235/4 | DA+3 | [5 empty] | 235/4
236/0 | DB2+18 | [5 empty] | 236/0
237/0 | DB1+25 (2MRC) | [5 empty] | 237/0
238/0 | DC1+25 | [5 empty] | 238/0
239/0 | DD45+0 | [5 empty] | 239/0
239/1 | DA+0 | [5 empty] | 239/1
240/0 | DB2+0 | [5 empty] | 240/0
240/1 | DA+3 | [5 empty] | 240/1
241/0 | DD60+0 | [5 empty] | 241/0
241/1 | DA+0 | [5 empty] | 241/1
241/2 | DA+0 | [5 empty] | 241/2
241/3 | DA+0 | [5 empty] | 241/3
241/4 | DA+3 | [5 empty] | 241/4
242/0 | DD60+3 | [5 empty] | 242/0
243/0 | DD60+3 | [5 empty] | 243/0
243/1 | DA+0 | [5 empty] | 243/1
243/2 | DA+0 | [5 empty] | 243/2
243/3 | DA+0 | [5 empty] | 243/3
244/0 | DD45+0 | [5 empty] | 244/0
244/1 | DA+0 | [5 empty] | 244/1
244/2 | DA+0 | [5 empty] | 244/2
244/3 | DA+3 | [5 empty] | 244/3
244/4 | DA+3 | [6 empty] | 243/1
244/5 | DA+0 | [6 empty] | 197/2
244/6 | DA+3 | [5 empty] | 244/6
245/0 | DD45+0 | [5 empty] | 245/0
245/1 | DA+0 | [5 empty] | 245/1
246/0 | DD45+9 | [5 empty] | 246/0
247/0 | DD60+35 (2MRC) | [5 empty] | 247/0
248/0 | DD60+35 (2MRC) | [5 empty] | 248/0
248/1 | DB1+9 | [5 empty] | 248/1
248/2 | DA+6 | [5 empty] | 248/2
249/0 | DD60+3 | [5 empty] | 249/0
249/1 | DA+9 | [5 empty] | 249/1
249/2 | DA+3 | [5 empty] | 249/2
249/3 | DA+3 | [5 empty] | 249/3
250/0 | DD45+3 | [5 empty] | 250/0
250/1 | DA+9 (1MRC) | [5 empty] | 250/1
250/2 | DA+0 | [5 empty] | 250/2
250/3 | DA+9 | [6 empty] | 120/0
250A/0 | DB1+3 (3MRC) | [5 empty] | 250A/0
250A/1 | DA+6 | [5 empty] | 250A/1
250A/2 | DA+0 | [5 empty] | 250A/2
251/0 | DD45+0 | [5 empty] | 251/0
251/1 | DA+6 (1MRC) | [6 empty] | 160/0
252/0 | DB2+0 | [5 empty] | 252/0
252/1 | DA+0 | [5 empty] | 252/1
252/2 | DA+3 | [6 empty] | 244/2
252/3 | DA+6 | [6 empty] | 179/0
252/4 | DA+0 | [5 empty] | 252/4
252/5 | DB1+9 | [5 empty] | 252/5
253/0 | DD45+35 (2MRC) | [6 empty] | 161/0
254/0 | DD45+35 (2MRC) | [5 empty] | 254/0
254/1 | DB1+9 | [6 empty] | 180/2
255/0 | DD60+0 | [5 empty] | 255/0
255/1 | DA+0 | [5 empty] | 255/1
256/0 | DD60+0 | [5 empty] | 256/0
256/1 | DA+9 | [5 empty] | 256/1
257/0 | DC1+9 | [6 empty] | 214/2
258/0 | DD60+0 (1.5MRC) | [5 empty] | 258/0
241/2
241/0
118/0
120/3
121/5
120/2
121/4
121/2
183/1
119/0
121/3
120/5
120/0
244/6
145/4
249/1
119/2
119/3
121/6
249/0
249/2
120/6
126/3
137/2
121/1
121/7
145/3
120/7
244/5
250/0
121/8
252/3
136/1
145/2
250A/2
252/0
248/2
141/4
121/10
241/4
124/1
137/1
141/3
145/7
121/9
248/1
243/3
126/1
141/5
137/0
124/0
243/2
250/3
126/2
148/0
126/0
244/1
132/0
117/1
117/2
251/0
171/0
121/0
180/3
172/0
180/4
179/3
172/1
180/2
165/7
180/5
180/7
179/1
132/1
174/4
174/6
174/5
174/1
176/1
177/0
175/0
176/2
148/4
178/3
165/5
148/2
180/1
165/2
252/5
243/0
256/0
246/0
250A/1
131/2
241/3
178/0
120/1
224/1
119/1
224/2
225/0
120/4
223/3
221/0
224/0
138/0
223/1
220/1
222/0
185/0
220/0
141/6
223/2
219/1
223/0
218/0
144/0
196/0
142/0
225/1
125/1
187/0
136/0
214/2
225/4
148/5
215/0
186/0
194/1
176/0
214/5
214/7
143/0
214/4
184/0
244/2
145/5
225/3
139/0
183/0
148/3
217/4
250/2
214/3
127/2
214/6
183/2
249/3
182/0
225/2
141/1
161/0
243/1
189/1
145/6
175/1
217/3
141/2
217/2
166/0
180/6
191/1
199/1
257/0
165/6
254/1
216/1
127/0
190/0
148/1
196/1
197/0
170/0
173/0
252/2
174/0
197/2
196/2
252/1
241/1
128/0
183/3
179/0
216/2
149/0
141/0
167/0
210/0
127/1
139/1
192/0
178/2
244/0
255/0
211/3
216/3
162/0
199/2
211/1
230/0
245/0
132/3
191/0
160/0
125/2
199/0
235/3
245/1
178/1
194/0
133/0
174/3
227/0
250A/0
217/5
211/4
165/4
140/0
193/0
198/0
216/0
244/3
197/1
244/4
133/1
125/0
233/0
226/3
211/2
236/0
139/3
227/1
188/0
168/0
139/2
209/2
235/2
232/4
235/1
133/2
211/5
211/0
238/0
174/2
250/1
252/4
240/0
213/0
124/3
256/1
163/0
147/0
124/2
235/0
228/0
134/0
237/0
242/0
214/0
232/0
133/4
248/0
228/1
217/1
217/0
214/1
240/1
209/0
209/1
219/0
239/0
207/0
226/1
133/3
239/1
226/2
231/0
227/2
foundation
lfmlv
[8 empty] | 121/11 | DA+9
[8 empty] | 129/0 | DD45+25 (15.87MRC)
[8 empty] | 130/0 | DD45+25 (11.9MRC)
[8 empty] | 131/0 | DD60+9 (7MRC)
[8 empty] | 131/1 | DA+3
[8 empty] | 131/3 | DA+3
[8 empty] | 131/4 | DA-3
[8 empty] | 131/5 | DA-3
[8 empty] | 132/2 | DA-3
[8 empty] | 133/3 | DB1+0
[8 empty] | 135/0 | DD60+3
[8 empty] | 145/0 | DD45+9
[8 empty] | 145/1 | DA+0
[8 empty] | 150/0 | DD60+25
[8 empty] | 150/1 | DB1+0
[8 empty] | 151/0 | DD60+6
[8 empty] | 151A/0 | DD60+18
[8 empty] | 152/0 | DD60+3
[8 empty] | 153/0 | DD60+3
[8 empty] | 153/1 | DA+3
[8 empty] | 153/2 | DA+0
[8 empty] | 153A/0 | DD45+9
[8 empty] | 154/0 | DD60+9
[8 empty] | 155/0 | DD60+18
[8 empty] | 156/0 | DD45+18
[8 empty] | 156/1 | DB2+9
[8 empty] | 157/0 | DD60+41
[8 empty] | 158/0 | DD60+41
[8 empty] | 159/0 | DD60+9 (2MRC)
[8 empty] | 163/0 | DD60+30
[8 empty] | 163/1 | DB1+6
[8 empty] | 164/0 | DC2+6
[8 empty] | 165/0 | DB1+25
[8 empty] | 165/1 | DA+9
[8 empty] | 165/3 | DA+6
[8 empty] | 169/0 | DD60+25
[8 empty] | 179/2 | DA+3 (A,B 1.5 RC)
[8 empty] | 180/0 | DD45+0LE (3 Leg)+1.5LE (1 Leg) & (B1MRC & C0.5MRS)
[8 empty] | 189/0 | DD60+35
[8 empty] | 195/0 | DC1+18
[8 empty] | 200/0 | DC2+0
[8 empty] | 200/1 | DA+6
[8 empty] | 201/0 | DC1+9
[8 empty] | 202/0 | DC1+18
[8 empty] | 203/0 | DC1+18
[8 empty] | 203/1 | DB1+0
[8 empty] | 204/0 | DD60+25 (2MRC)
[8 empty] | 205/0 | DD60+25 (3MRC)
[8 empty] | 205/1 | DB2+9
[8 empty] | 205/2 | DA+9
[8 empty] | 206/0 | DC2+0
[8 empty] | 206/1 | DB1+6
[8 empty] | 207/0 | DD60+25
[8 empty] | 208/0 | DD45+35
[8 empty] | 209/0 | DD60+9
[8 empty] | 209/1 | DA+0
[8 empty] | 212/0 | DD45+30 (2MRC)
[8 empty] | 225/5 | DA+0
[8 empty] | 225/6 | DA+0
[8 empty] | 225/7 | DA+6
[8 empty] | 226/0 | DB2+3
[8 empty] | 226/1 | DA+6
[8 empty] | 226/2 | DA+0
[8 empty] | 227/2 | DA+3
[8 empty] | 229/0 | DD45+0
[8 empty] | 229/1 | DA+9
[8 empty] | 229A/0 | DB1+25
[8 empty] | 229B/0 | DB2+25
[8 empty] | 230/1 | DA+9
[8 empty] | 230A/0 | DD45+0
[8 empty] | 231/0 | DB1+0
[8 empty] | 232/0 | DB1+0
[8 empty] | 232/1 | DA+0
[8 empty] | 232/2 | DA+0
[8 empty] | 232/3 | DA+0
[8 empty] | 234/0 | DD60+18
[8 empty] | 235/4 | DA+3
[8 empty] | 239/0 | DD45+0
[8 empty] | 239/1 | DA+0
[8 empty] | 247/0 | DD60+35 (2MRC)
[8 empty] | 251/1 | DA+6 (1MRC)
[8 empty] | 253/0 | DD45+35 (2MRC)
[8 empty] | 254/0 | DD45+35 (2MRC)
[8 empty] | 255/1 | DA+0
[8 empty] | 258/0 | DD60+0 (1.5MRC)
129/0
[8 empty] | 129/0 | [6 empty] | 130/0
[8 empty] | 130/0 | [6 empty] | 133/3
[8 empty] | 133/3 | [6 empty] | 131/0
[8 empty] | 131/0 | [6 empty] | 131/1
[8 empty] | 131/1 | [6 empty] | 131/3
[8 empty] | 131/3 | [6 empty] | 131/4
[8 empty] | 131/4 | [6 empty] | 145/1
[8 empty] | 145/1 | [6 empty] | 145/0
[8 empty] | 145/0 | [6 empty] | 153/1
[8 empty] | 153/1 | [6 empty] | 121/11
[8 empty] | 121/11 | [6 empty] | 150/0
[8 empty] | 150/0 | [6 empty] | 150/1
[8 empty] | 150/1 | [6 empty] | 164/0
[8 empty] | 164/0 | [6 empty] | 163/1
[8 empty] | 163/1 | [6 empty] | 165/0
[8 empty] | 165/0 | [6 empty] | 165/1
[8 empty] | 165/1 | [6 empty] | 163/0
[8 empty] | 163/0 | [6 empty] | 165/3
[8 empty] | 165/3 | [6 empty] | 169/0
[8 empty] | 169/0 | [6 empty] | 150/1
[8 empty] | 150/1 | [6 empty] | 209/0
[8 empty] | 209/0 | [6 empty] | 208/0
[8 empty] | 208/0 | [6 empty] | 202/0
[8 empty] | 202/0 | [6 empty] | 212/0
[8 empty] | 212/0 | [6 empty] | 207/0
[8 empty] | 207/0 | [6 empty] | 209/1
[8 empty] | 209/1 | [6 empty] | 203/0
[8 empty] | 203/0 | [6 empty] | 200/0
[8 empty] | 200/0 | [6 empty] | 226/1
[8 empty] | 226/1 | [6 empty] | 225/7
[8 empty] | 225/7 | [6 empty] | 226/0
[8 empty] | 226/0 | [6 empty] | 226/2
[8 empty] | 226/2 | [6 empty] | 227/2
[8 empty] | 227/2 | [6 empty] | 229/0
[8 empty] | 229/0 | [6 empty] | 229A/0
[8 empty] | 229A/0 | [6 empty] | 239/0
[8 empty] | 239/0 | [6 empty] | 239/1
[8 empty] | 239/1 | [6 empty] | 234/0
[8 empty] | 234/0 | [6 empty] | 235/4
[8 empty] | 235/4 | [6 empty] | 232/3
[8 empty] | 232/3 | [6 empty] | 232/0
[8 empty] | 232/0 | [6 empty] | 231/0
[8 empty] | 231/0 | [6 empty] | 232/2
[8 empty] | 232/2 | [6 empty] | 232/1
232/1
dgg
121/11
129/0
130/0
131/0
131/1
131/3
131/4
[11 empty] | 131/5 |  |  |  |  | 131/5
[11 empty] | 132/2 |  |  |  |  | 132/2
[11 empty] | 133/3 |  |  |  |  | 135/0
[11 empty] | 135/0 |  |  |  |  | 150/0
[11 empty] | 145/0 |  |  |  |  | 151/0
[11 empty] | 145/1 |  |  |  |  | 151A/0
[11 empty] | 150/0 |  |  |  |  | 152/0
[11 empty] | 150/1 |  |  |  |  | 153/0
[11 empty] | 151/0 |  |  |  |  | 153/1
[11 empty] | 151A/0 |  |  |  |  | 153/2
[11 empty] | 152/0 |  |  |  |  | 153A/0
[11 empty] | 153/0 |  |  |  |  | 154/0
[11 empty] | 153/1 |  |  |  |  | 155/0
[11 empty] | 153/2 |  |  |  |  | 156/0
[11 empty] | 153A/0 |  |  |  |  | 156/1
[11 empty] | 154/0 |  |  |  |  | 157/0
[11 empty] | 155/0 |  |  |  |  | 158/0
[11 empty] | 156/0 |  |  |  |  | 159/0
[11 empty] | 156/1 |  |  |  |  | 179/2
[11 empty] | 157/0 |  |  |  |  | 180/0
[11 empty] | 158/0 |  |  |  |  | 189/0
[11 empty] | 159/0 |  |  |  |  | 195/0
[11 empty] | 163/0 |  |  |  |  | 203/1
[11 empty] | 163/1 |  |  |  |  | 204/0
[11 empty] | 164/0 |  |  |  |  | 205/0
[11 empty] | 165/0 |  |  |  |  | 205/1
[11 empty] | 165/1 |  |  |  |  | 205/2
[11 empty] | 165/3 |  |  |  |  | 225/5
[11 empty] | 169/0 |  |  |  |  | 225/6
[11 empty] | 179/2 |  |  |  |  | 229B/0
[11 empty] | 180/0 |  |  |  |  | 230/1
[11 empty] | 189/0 |  |  |  |  | 247/0
[11 empty] | 195/0 |  |  |  |  | 251/1
[11 empty] | 200/0 |  |  |  |  | 253/0
[11 empty] | 200/1 |  |  |  |  | 254/0
[11 empty] | 201/0 |  |  |  |  | 255/1
[11 empty] | 202/0 |  |  |  |  | 258/0
203/0
203/1
204/0
205/0
205/1
205/2
206/0
206/1
207/0
208/0
209/0
209/1
212/0
225/5
225/6
225/7
226/0
226/1
226/2
227/2
229/0
229/1
229A/0
229B/0
230/1
230A/0
231/0
232/0
232/1
232/2
232/3
234/0
235/4
239/0
239/1
247/0
251/1
253/0
254/0
255/1
258/0
129/0
130/0
133/3
131/0
131/1
131/3
131/4
145/0
145/1
121/11
164/0
163/1
165/0
165/1
163/0
165/3
169/0
150/1
212/0
206/1
206/0
209/0
208/0
202/0
207/0
200/0
200/1
201/0
209/1
203/0
200/0
226/1
225/7
226/0
226/2
227/2
229/0
229/1
229A/0
239/0
232/3
234/0
235/4
239/1
232/0
231/0
232/1
232/2
230A/0

## Sheet7 (hidden)
kfvnk
117/1
117/2
118/0
119/0
119/1
119/2
119/3
120/0
120/1
120/2
120/3
120/4
120/5
120/6
120/7
121/0
121/1
121/2
121/3
121/4
121/5
121/6
121/7
121/8
121/9
121/10
124/0
124/1
124/2
124/3
125/0
125/1
125/2
126/0
126/1
126/2
126/3
127/0
127/1
127/2
128/0
131/2
132/0
132/1
132/3
133/0
133/1
133/2
133/4
134/0
136/0
136/1
137/0
137/1
137/2
138/0
139/0
139/1
139/2
139/3
140/0
141/0
141/1
141/2
141/3
141/4
141/5
141/6
142/0
143/0
144/0
145/2
145/3
145/4
145/5
145/6
145/7
147/0
148/0
148/1
148/2
148/3
148/4
148/5
149/0
160/0
161/0
162/0
165/2
165/4
165/5
165/6
165/7
166/0
167/0
168/0
170/0
171/0
172/0
172/1
174/0
174/1
174/2
174/3
174/4
174/5
174/6
175/0
175/1
176/0
176/1
176/2
177/0
178/0
178/1
178/2
178/3
179/0
179/1
179/3
180/1
180/2
180/3
180/4
180/5
180/6
180/7
182/0
183/0
183/1
183/2
183/3
184/0
185/0
186/0
187/0
188/0
189/1
190/0
191/0
191/1
192/0
193/0
194/0
194/1
196/0
196/1
196/2
197/0
197/1
197/2
198/0
199/0
199/1
199/2
209/2
210/0
211/0
211/1
211/2
211/3
211/4
211/5
213/0
214/0
214/1
214/2
214/3
214/4
214/5
214/6
214/7
215/0
216/0
216/1
216/2
216/3
217/0
217/1
217/2
217/3
217/4
217/5
218/0
219/1
220/0
220/1
221/0
222/0
223/0
223/1
223/2
223/3
224/0
224/1
224/2
225/0
225/1
225/2
225/3
225/4
226/3
227/0
227/1
228/0
228/1
230/0
232/4
233/0
235/0
235/1
235/2
235/3
236/0
237/0
238/0
240/0
241/0
241/1
241/2
241/3
241/4
242/0
243/0
243/1
243/2
243/3
244/0
244/1
244/2
244/3
244/4
244/5
244/6
245/0
245/1
246/0
248/1
248/2
249/0
249/1
249/2
249/3
250/0
250/1
250/2
250/3
250A/0
250A/1
250A/2
251/0
252/0
252/1
252/2
252/3
252/4
252/5
254/1
255/0
256/0
256/1
257/0
117/2
118/0
119/0
119/2
119/3
120/7
120/2
120/3
120/4
120/5
120/6
121/10
119/1
121/4
121/7
131/2
132/0
136/1
137/2
141/1
141/2
141/6
145/5
148/2
148/4
175/1
176/0
179/1
141/3
137/0
180/5
145/6
187/0
241/0
241/4
243/0
243/2
244/1
244/5
141/5
249/3
250/3
145/4
175/0
180/4
250A/2
248/1
126/1
180/6
252/5
121/2
145/3
243/1
197/2
117/1
148/3
138/0
180/3
250A/1
183/0
145/7
143/0
241/2
142/0
182/0
190/0
199/0
121/3
120/0
148/5
148/1
137/1
246/0
252/2
248/2
244/2
179/0
197/1
252/1
180/2
174/6
139/1
250/2
214/2
141/4
189/1
177/0
241/3
121/5
198/0
245/1
214/4
180/7
178/1
141/0
183/2
252/0
139/0
176/2
196/0
251/0
197/0
214/5
126/0
220/1
176/1
191/0
148/0
196/2
121/6
136/0
194/1
178/2

## Stringing Compiled
Number of TSE
S.no | Sec | From AP | To AP | Span (M) | Method | Section Readiness | Insulator Hoisting | P/O Starting Date | P/O Completion Date | P/O | F/S Starting Date | F/S/ Completion Date | Jumpering | Spacering | Clipping | Length | Status | Gang Name | Gang Strength | Number of Fitters | Hindrance | Remarks
|  |  | Total | 0

## String
ASOTL Stringing
Sr. No. | Section | length | Manual/TSE | Engaged Date | Paying Out |  | Final Sag |  | P/O Completed | F/S Completed | Stringing Status As on Today | Cumulative Status | Sub Contractor name | Manpower | Hindarnce Days | Remarks
[5 empty] | Start Date | End Date | Start Date | End Date

## Crossing
TL-04 , 765 kV D/C Ahmedabad - South Olpad Transmission Line
Sl No | AP NO | Towe Type | AP No | Tower Type | Type of Crossings | Span Length | LINE OWNER | Line Name | Nos. | Work Portion | Status | Submitted to Client for Review | Proposal Submitted (Y/N) | Inspection Status (Y/N) | Remarks
1 | 118/0 | 5DD60+25 | 119/0 | DD60+25 | Powerline crossing | 225.97 | GETCO | 400 kV D/C Twin Chorniya/Pancham To Kosamba TL | 1 | Anand | Submitted | 2026-04-17 | Y |  | Approval Not Received from PGCIL
2 | 120/0 | CDDN+55 | 121/0 | CDDN+25 | Powerline crossing | 284.73 | PGCIL | 765 kV D/C Ahmedabad-Navsari | 1 | Anand | Submitted | 2026-04-17 | Y |  | Approval Not Received from PGCIL
3 | 122/0 | CDDN+55 | 123/0 | CDDN+25 | Powerline crossing | 164.96 | PGCIL | 765 kV D/C Vataman-Navsari | 1 | Anand | Submitted | 2026-04-17 | Y |  | Approval Not Received from PGCIL
4 | 145/1 | DB1+9 | 145/2 | DA+3 | Powerline crossing | 448 | GETCO | 66 kV D/C Gavasad-Sterling/Sarod | 1 | Bharuch | Submitted | 2025-07-21 | Y | Y | Approval Not Received from PGCIL
5 | 147/0 | DD60+0 | 147/1 | DA-3 | GAS PIPELINE | 323 | ONGC | GGS Jambusar-GGS Dabka | 1 | Bharuch | Submitted | 2025-08-18 | Y | Y | Approval Not Received from PGCIL
6 | 148A/0 | DC2+0 | 148B/0 | DC1+0 | GAS PIPELINE | 259.34 | GAIL | Dabka-Gandhar | 1 | Bharuch | Submitted | 2025-09-15 | Y | Y | Approval Not Received from PGCIL
7 | 148A/0 | DC2+0 | 148B/0 | DC1+0 | GAS PIPELINE | 259.34 | GSPL | Uchchhad-Jambusar | 1 | Bharuch | Submitted | 2025-09-15 | Y | Y | Approval Not Received from PGCIL
8 | 149/0 | DD60+6 | 150/0 | DD60+6 | Railway Crossing | 275.39 | IR WR | BG U/C electrified single Vishamitri-Jambusar | 1 | Bharuch | Submitted | 2025-09-30 | Y | Y | Approval Not Received from PGCIL
9 | 150/5 | DA+3 | 151/0 | DD60+3 | Powerline crossing | 375.54 | GETCO | 66 kV (H FRAME) Masar Road to Jambusar | 1 | Bharuch | Submitted | 2025-09-11 | Y | Y | Approval received on 25-04-2026
10 | 151/0 | DD60+3 | 152/0 | DD60+6 | NH | 297.52 | NHAI | Jambusar-Bharuch Section (NH 64) | 1 | Bharuch | Submitted | 2025-09-09 | Y | Y | Approval Not Received from PGCIL
11 | 151/0 | DD60+3 | 152/0 | DD60+6 | Railway Crossing | 297.52 | IR WR | BG U/C electrified single Bharuch-Jambusar | 1 | Bharuch | Submitted | 2025-09-30 | Y | Y | Approval Not Received from PGCIL
12 | 153/1 | DA+0 | 154/0 | DC2+0 | GAS PIPELINE | 234.98 | Reliance | Dahej-Vadodara | 1 | Bharuch | Submitted | 2025-04-03 | Y | Y | Approval Not Received from PGCIL
13 | 154/0 | DC2+0 | 154/1 | DA+0 | GAS PIPELINE | 375.72 | ONGC | GNAQ-Magnad | 1 | Bharuch | Submitted | 2025-04-04 | Y | Y | Approval Not Received from PGCIL
14 | 157A/0 | DC2+0 | 157B/0 | DD45+9 | GAS PIPELINE | 378.53 | ONGC | G763 Station to EPS253 Station | 1 | Bharuch | Submitted | 2025-09-13 | Y | Y | Approval Not Received from PGCIL
15 | 157A/0 | DC2+0 | 157B/0 | DD45+9 | Powerline crossing | 378.53 | GETCO | U/C 66 k/V D/C Amod-Muler | 1 | Bharuch | Submitted | 2025-09-02 | Y | Y | Approval Not Received from PGCIL
16 | 158/0 | DC1+3 | 158/1 | DA+0 | GAS PIPELINE | 406 | GAIL | Ankhi IP to CPF Gandhar 2 | 1 | Bharuch | Submitted | 2025-09-05 | Y | Y | Approval Not Received from PGCIL
17 | 159/1 | DA+6 | 159/2 | DA+0 | GAS PIPELINE | 426 | ONGC | Near EPS 253 Station | 19 | Bharuch | Submitted | 2025-08-08 | Y | Y | Approval Not Received from PGCIL
18 | 159/1 | DA+6 | 159/2 | DA+0 | GAS PIPELINE | 426 | IOCL | Dehaj-Koyali | 1 | Bharuch | Submitted | 2025-08-08 | Y | Y | Approval Not Received from PGCIL
19 | 161/0 | DD45+0 | 161/1 | DA+3 | GAS PIPELINE | 410 | IOCL | Amod-Hajira | 1 | Bharuch | Submitted | 2025-08-09 | Y | Y | Approval Not Received from PGCIL
20 | 161B/0 | DC1+0 | 161C/0 | DC2+3 | GAS PIPELINE | 404.98 | IHBL | Kandla-Gorakhpur | 1 | Bharuch | Submitted | 2025-08-08 | Y | Y | Approval Not Received from PGCIL
21 | 161C/0 | DC2+3 | 161C/1 | DA+0 | GAS PIPELINE | 382.01 | GAIL | CPU Gandhar-NTPC Tarminal (Jhanor) | 1 | Bharuch | Submitted | 2025-08-13 | Y | Y | Approval received on 25.04.2026
22 | 162/0 | DD60+6 | 163/0 | DD60+6 | Powerline crossing | 155.73 | GETCO | Kohsamba-Suva-Gavasad | 1 | Bharuch | Submitted | 2025-08-11 | Y | Y | Approval received on 25-04-2026
23 | 164/0 | DB2+6 | 164/1 | DA+9 | GAS PIPELINE | 329 | GAIL | CPU Gandhar DT-GNFC RT | 1 | Bharuch | Submitted | 2025-08-19 | Y | Y | Approval received on 25.04.2026
24 | 164/0 | DB2+6 | 164/1 | DA+9 | Powerline crossing | 329 | GETCO | Wagra-CPF ONGC | 1 | Bharuch | Submitted | 2025-08-20 | Y | Y | Approval received on 25-04-2026
25 | 164/1 | DA+9 | 165/0 | DD45+0 | Powerline crossing | 428.04 | GETCO | 66 kV (H FRAME) Wagra-Mular | 1 | Bharuch | Submitted | 2025-08-22 | Y | Y | Approval received on 25-04-2026
26 | 165/1 | DA+0 | 165/2 | DA-3 | Powerline crossing | 365.78 | GETCO | 66 kV (H FRAME) Wagra-Vensali | 1 | Bharuch | Submitted | 2025-08-25 | Y | Y | Approval received on 25-04-2026
27 | 166/0 | DD60+6 | 167/0 | DD60+3 | Railway Crossing | 276.3 | IR WR | BG Electrified Single Bharuch-Dahej | 1 | Bharuch | Submitted | 2025-09-30 | Y | Y | Approval Not Received from PGCIL
28 | 166/0 | DD60+6 | 167/0 | DD60+3 | Powerline Crossing | 276.3 | GETCO | 66 kV D/C Wagra-GAIL | 1 | Bharuch | Submitted | 2025-08-26 | Y | Y | Approval received on 25-04-2026
29 | 169/0 | DC2+3 | 170/0 | DD60+0 | GAS PIPELINE | 381.59 | IOCL | Amod-Hajira | 1 | Bharuch | Submitted | 2025-04-09 | Y | Y | Approval Not Received from PGCIL
30 | 170/2 | DA+0 | 170/3 | DA+0 | GAS PIPELINE | 378 | GAIL | Dahej-Vemar | 2 | Bharuch | Submitted | 2025-04-09 | Y | Y | Approval received on 25.04.2026
31 | 171/0 | DB2+9 | 172/0 | DC1+9 | Powerline crossing | 240.05 | GETCO | 220 kV D/C Haldarva-Dahej | 1 | Bharuch | Not Submitted |  |  |  | Details Survey Approval pending due to GETCO new substation in detail survey route
32 | 173/0 | DC2+9 | 174/0 | DB1+9 | Powerline crossing | 249 | GETCO | 220 kV D/C Haldarva-Suva/Dahej | 1 | Bharuch | Not Submitted |  |  |  | Details Survey Approval pending due to GETCO new substation in detail survey route
33 | 176/0 | DD60+0 | 176A/0 | DD60+0 | GAS PIPELINE | 172.61 | ONGC | CPU Gandhar-CPF Ankleshwar | 1 | Bharuch | Not Submitted |  |  |  | Awaited for details survey approval from PGCIL
34 | 177/0 | DD60+25 (2M RC) | 178/0 | DD60+25(2M RC) | Powerline crossing | 225.81 | Torrent Power | 400 kV D/C DGEN-Navsari | 1 | Bharuch | Submitted | 2026-05-08 | Y |  | Approval Not Received from PGCIL
35 | 177/0 | DD60+25 (2M RC) | 178/0 | DD60+25(2M RC) | GAS PIPELINE | 225.81 | IOCL | Amod-Hajira | 1 | Bharuch | Submitted | 2026-05-08 | Y |  | Approval Not Received from PGCIL
36 | 178/1 | DA+0 | 178/2 | DA+3 | GAS PIPELINE | 385 | GSPL | Amboli-Dahej | 1 | Bharuch | Submitted | 2026-05-11 | Y |  | Approval Not Received from PGCIL
37 | 178/2 | DA+3 | 178/3 | DA+3 | GAS PIPELINE | 429 | Reliance | Dahej-Hagothana | 1 | Bharuch | Not Submitted |  |  |  | U/P
38 | 178/2 | DA+3 | 178/3 | DA+3 | GAS PIPELINE | 429 | ONGC | IPCL Hajira-Dahej | 1 | Bharuch | Not Submitted |  |  |  | U/P
39 | 178/2 | DA+3 | 178/3 | DA+3 | GAS PIPELINE | 429 | GAIL | DUPL Dahej-Hajira | 1 | Bharuch | Not Submitted |  |  |  | U/P
40 | 184/10 | DA-3 | 184/11 | DA-3 | GAS PIPELINE | 360 | ONGC | ALLA BET- Ankleshwar | 1 | Bharuch | Not Submitted |  |  |  | Details Survey Approval pending due to KP Group new Solar in detail survey route
41 | 185/0 | DB2+0 | 186/0 | DC1+0 | NH | 244.02 | NHAI | Ankleshwar- Hansot (NH 64) | 1 | Bharuch | Submitted | 2025-07-21 | Y | Y | Approval Not Received from PGCIL
42 | 186/4 | DA+0 | 186/5 | DB1+0 | Powerline crossing | 364 | GETCO | 66 kV (H-Frame) Hansot-Ankleshwar | 1 | Bharuch | Submitted | 2025-07-16 | Y | Y | Approval received on 25-04-2026
43 | 186/5 | DB1+0 | 186/6 | DA+0 | Powerline crossing | 390 | GETCO | 66 kV (H-Frame) Panoli-Hansot | 1 | Bharuch | Submitted | 2025-07-16 | Y | Y | Approval received on 25-04-2026
44 | 189/0 | DC1+0 | 190/0 | DD45+0 | NH | 242.91 | NHAI | Hansot-Rayma (NH 64) | 1 | Bharuch | Submitted | 2025-07-21 | Y | Y | Approval Not Received from PGCIL
45 | 193/3 | DB1+3 | 193/4 | DA+3 | Powerline crossing | 437 | GETCO | 66 kV D/C Vadoli-Mindhi | 1 | Bharuch | Submitted | 2025-08-28 | Y | Y | Approval received on 25-04-2026
46 | 195/0 | DB2+0 | 196/0 | DB1+0 | NH | 210.48 | NHAI | Vadoli-Olpad | 1 | Surat | Submitted | 2026-06-09 | Y |  | Submitted today
47 | 197/0 | DD60+25 (3M RC) | 198/0 | DD60+25(3M RC) | Powerline crossing | 233.53 | ESSAR POWER | Hazira-Gandhar | 1 | Surat | Submitted | 2026-05-19 | Y |  | Approval Not Received from PGCIL

## Tree Enumeration
Sr.No. | Location Details | Length | Status
1 | AP145/0 to AP171/0 | 41.090 km | completed
2 | AP177/0 to AP184/0 | 6.747 km | completed
3 | AP177/0 to AP184/0 | 29.131 km | completed
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Sheet2 (hidden)
Hotline Stringing total KM : 17.112 Km
Sl NO | Description | Dec'25 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | June'25
1 | Hotline Stringing | 2.4446 | 2.4446 | 2.4446 | 2.4446 | 2.4446 | 2.4446 | 2.4446