## Notes
Item | Value
Mail HTML | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Productivity Summaries\Daily_DPR_Mail_2026-07-30.html
Ground workbook | C:\Users\kaushikb\Downloads\Jul'26.xlsx
Ground sheet | Worker for TL
Generated on | 2026-07-31 11:01:21
Interpretation | Delta = Ground - Mail; positive means mail is lower than ground.

## Comprehensive Comparison
project_key | activity | unit | coverage | mail_project | ground_project | mail_pch | ground_pch | ground_pe | ground_client | mail_plan | ground_plan | plan_delta_ground_minus_mail | plan_status | mail_actual | ground_actual | actual_delta_ground_minus_mail | actual_status | ground_wip | ground_total_scope | ground_completed_upto_prev_month | ground_balance_start_month | latest_dpr_date | latest_dpr_file
TA 413 | erection | Nos. | Both | TA 413 | 765 KV D/C Bikaner Complex PART-A line | Mr. NK Gupta | Mr. N K Gupta | Santosh Kumar - 9370318069 | PGCIL | 3 | 3 | 0 | Matched | 0 |  |  | Missing actual | 1 | 306 | 303 | 3 | 2026-07-29 | TA 413 - DPR - 2026-07-29.xlsx
TA 413 | stringing | KM | Both | TA 413 | 765 KV D/C Bikaner Complex PART-A line | Mr. NK Gupta | Mr. N K Gupta | Santosh Kumar - 9370318069 | PGCIL | 20 | 20 | 0 | Matched | 11.29 | 14 | 2.71 | Mail lower than ground | 7.16 | 118 | 87 | 31 | 2026-07-29 | TA 413 - DPR - 2026-07-29.xlsx
TA 414 | erection | Nos. | Both | TA 414 | 765kV D/C Vataman - Navsari line | Mr. Arun Felbin | Mr. Arun Felbin | Pawan Shrivastava - 9525760939 | PGCIL | 30 | 40 | 10 | Mail lower than ground | 12 | 11 | -1 | Mail higher than ground | 4 | 352 | 267 | 85 | 2026-07-30 | TA 414 - DPR - 2026-07-30.xlsx
TA 414 | stringing | KM | Both | TA 414 | 765kV D/C Vataman - Navsari line | Mr. Arun Felbin | Mr. Arun Felbin | Pawan Shrivastava - 9525760939 | PGCIL | 15 | 18 | 3 | Mail lower than ground | 2.92 | 2.921 | 0.001 | Matched | 1.148 | 128 | 25 | 103 | 2026-07-30 | TA 414 - DPR - 2026-07-30.xlsx
TA 416 | stringing | KM | Mail only | TA 416 | [5 empty] | 4 |  |  | Missing plan | 0.68 |  |  | Missing actual |  |  |  |  | 2026-07-16 | TA 416 - DPR - 2026-07-16.xlsx
TA 418 | stringing | KM | Both | TA 418 | 765 KV D/C Kopal - Raichor |  | Mr. Arun Felbin | S Ajith Jayasurya - 9788911010 | PGCIL | 10.98 | 11 | 0.02 | Mail lower than ground | 7.43 | 6 | -1.43 | Mail higher than ground | 0.417 | 48 | 37 | 11 | 2026-07-21 | TA 418 - DPR - 2026-07-21.xlsx
TA 419 | erection | Nos. | Both | TA 419 | 765 KV D/C Sikar - Narela Line |  | Mr. N K Gupta | Suraj Chaudhary - 7439328228 | PGCIL | 40 | 40 | 0 | Matched | 18 | 20 | 2 | Mail lower than ground | 10 | 331 | 222 | 109 | 2026-07-30 | TA 419 - DPR - 2026-07-30.xlsx
TA 419 | stringing | KM | Both | TA 419 | 765 KV D/C Sikar - Narela Line |  | Mr. N K Gupta | Suraj Chaudhary - 7439328228 | PGCIL | 19.5 | 20 | 0.5 | Mail lower than ground | 6.24 | 5.15 | -1.09 | Mail higher than ground | 7.76 | 122 | 2 | 120 | 2026-07-30 | TA 419 - DPR - 2026-07-30.xlsx
TA 504 | erection | Nos. | Both | TA 504 | 765 KV D/C Rishabhdeo - Mansour Tr, Line | Mr. Nabajit Baruah | Mr. Nabajit Barwa | Abir Kumar Das - 8583937594 / 9830806660 | PGCIL | 6 | 2 | -4 | Mail higher than ground | 4 | 4 | 0 | Matched | 1 | 186 | 125 | 61 | 2026-07-28 | TA 504 - DPR - 2026-07-28.xlsx
TA 505 | erection | Nos. | Both | TA 505 | 765KV D/C Mandsour - Beawar Tr, Line |  | Mr. Nabajit Barwa | Partha Pratim Pal - 8017746581 | PGCIL | 6 | 6 | 0 | Matched | 2 | 2 | 0 | Matched | 1 | 379 | 364 | 15 | 2026-07-29 | TA 505 - DPR - 2026-07-29.xlsx
TA 505 | stringing | KM | Both | TA 505 | 765KV D/C Mandsour - Beawar Tr, Line | Mr. Nabajit Baruah | Mr. Nabajit Barwa | Partha Pratim Pal - 8017746581 | PGCIL | 21.33 | 40 | 18.67 | Mail lower than ground | 14.56 | 18 | 3.44 | Mail lower than ground | 4.221 | 139 | 28 | 111 | 2026-07-29 | TA 505 - DPR - 2026-07-29.xlsx
TA 506 | erection | Nos. | Both | TA 506 | 400 KV D/C Sirohi - Chittorgarh Tr, Line |  | Mr. Nabajit Barwa | Abir Kumar Das - 8583937594 / 9830806660 | PGCIL | 20 | 20 | 0 | Matched | 13 | 13 | 0 | Matched | 4 | 602 | 422 | 180 | 2026-07-28 | TA 506 - DPR - 2026-07-28.xlsx
TA 506 | stringing | KM | Both | TA 506 | 400 KV D/C Sirohi - Chittorgarh Tr, Line |  | Mr. Nabajit Barwa | Abir Kumar Das - 8583937594 / 9830806660 | PGCIL | 27 | 27 | 0 | Matched | 11.93 | 12 | 0.07 | Mail lower than ground | 10 | 223 | 66 | 157 | 2026-07-28 | TA 506 - DPR - 2026-07-28.xlsx
TA 509 | erection | Nos. | Both | TA 509 | 765 KV D/C Mandsour - Kurawar Tr, Line |  | Mr. Nabajit Barwa | shubayu Das - 8240796656 | PGCIL | 15 | 30 | 15 | Mail lower than ground | 7 | 6 | -1 | Mail higher than ground | 2 | 309 | 223 | 86 | 2026-07-29 | TA 509 - DPR - 2026-07-29.xlsx
TA 509 | stringing | KM | Both | TA 509 | 765 KV D/C Mandsour - Kurawar Tr, Line |  | Mr. Nabajit Barwa | shubayu Das - 8240796656 | PGCIL | 12 | 19.17 | 7.17 | Mail lower than ground | 5.91 | 5.909 | -0.001 | Matched | 1.582 | 120 | 4 | 116 | 2026-07-29 | TA 509 - DPR - 2026-07-29.xlsx
TA 510 | erection | Nos. | Both | TA 510 | 765 KV D/C Ahmedabad - South Olpad line |  | Mr. Arun Felbin | Jayant 7727996705 | PGCIL | 285 | 15 | -270 | Mail higher than ground | 2 | 2 | 0 | Matched | 1 | 299 | 45 | 254 | 2026-07-30 | TA 510 - DPR - 2026-07-30.xlsx
TA 510 | stringing | KM | Both | TA 510 | 765 KV D/C Ahmedabad - South Olpad line |  | Mr. Arun Felbin | Jayant 7727996705 | PGCIL | 95 | 0 | -95 | Mail higher than ground | 0 |  |  | Missing actual |  | 111 | 0 | 111 | 2026-07-30 | TA 510 - DPR - 2026-07-30.xlsx
TA 512 | erection | Nos. | Both | TA 512 | 765 KV D/C Bikaner - Shivani line |  | Mr. N K Gupta | Saurabh Katiyar - 8447468911 | PGCIL | 20 | 30 | 10 | Mail lower than ground | 28 | 25 | -3 | Mail higher than ground | 11 | 319 | 237 | 82 | 2026-07-30 | TA 512 - DPR - 2026-07-30.xlsx
TA 512 | stringing | KM | Ground only |  | 765 KV D/C Bikaner - Shivani line |  | Mr. N K Gupta | Saurabh Katiyar - 8447468911 | PGCIL |  | 23 |  | Missing plan |  |  |  | Missing actual | 5.5 | 124.568 |  | 124.568 | 2026-07-30 | TA 512 - DPR - 2026-07-30.xlsx
TA 513 | erection | Nos. | Ground only |  | TA513 Shivani- Patratu |  | Mr. Hitesh Bahri | Harshit Kumar - 7055470402 | PGCIL |  | 16 |  | Missing plan |  |  |  | Missing actual |  | 619 | 35 | 584 | 2026-07-28 | TA 513 - DPR - 2026-07-28.xlsx
TA 513 | stringing | KM | Ground only |  | TA513 Shivani- Patratu |  | Mr. Hitesh Bahri | Harshit Kumar - 7055470402 | PGCIL |  | 0 |  | Missing plan |  |  |  | Missing actual |  | 230.39 | 0 | 230.39 | 2026-07-28 | TA 513 - DPR - 2026-07-28.xlsx
TA 601 | erection | Nos. | Both | TA 601 | Kurnool - Bidhar part 2 |  | Mr. Arun Felbin | Siddhesh bhoyar - 7020337487 | PGCIL | 25 | 25 | 0 | Matched | 29 | 28 | -1 | Mail higher than ground | 6 | 292 | 87 | 205 | 2026-07-30 | TA 601 - DPR - 2026-07-30.xlsx
TA 601 | stringing | KM | Ground only |  | Kurnool - Bidhar part 2 |  | Mr. Arun Felbin | Siddhesh bhoyar - 7020337487 | PGCIL |  | 0 |  | Missing plan |  |  |  | Missing actual |  | 113.27 |  | 113.27 | 2026-07-30 | TA 601 - DPR - 2026-07-30.xlsx
TA 602 | erection | Nos. | Both | TA 602 | HVDC KPS2 - Nagpur TL06 |  | Mr. Arun Felbin | Rishi Shukla - 8299744206 | PGCIL | 20 | 30 | 10 | Mail lower than ground | 11 | 11 | 0 | Matched | 1 | 478 | 93 | 385 | 2026-07-29 | TA 602 - DPR - 2026-07-29.xlsx
TA 602 | stringing | KM | Ground only |  | HVDC KPS2 - Nagpur TL06 |  | Mr. Arun Felbin | Rishi Shukla - 8299744206 | PGCIL |  | 0 |  | Missing plan |  |  |  | Missing actual |  | 186 | 0 | 186 | 2026-07-29 | TA 602 - DPR - 2026-07-29.xlsx
TB 408 | erection | Nos. | Both | TB 408 | 765 KV D/C Sterlite (Pkg F) |  | Mr. N K Gupta | Raghav Ranjan - 7717770750 | Sterlite | 1 | 1 | 0 | Matched | 1 | 1 | 0 | Matched |  | 485 | 484 | 1 | 2026-07-30 | TB 408 - DPR - 2026-07-30.xlsx
TB 408 | stringing | KM | Both | TB 408 | 765 KV D/C Sterlite (Pkg F) |  | Mr. N K Gupta | Raghav Ranjan - 7717770750 | Sterlite | 43.46 | 30 | -13.46 | Mail higher than ground | 18.1 | 18 | -0.1 | Mail higher than ground | 11.5 | 173 | 129 | 44 | 2026-07-30 | TB 408 - DPR - 2026-07-30.xlsx
TB 412 | erection | Nos. | Both | TB 412 | Chappra TL |  | Mr. N K Gupta | Uttam Rai - 7080157757 | Resonia | 45 | 45 | 0 | Matched | 32 | 35 | 3 | Mail lower than ground | 6 | 505 | 138 | 367 | 2026-07-30 | TB 412 - DPR - 2026-07-30.xlsx
TB 412 | stringing | KM | Both | TB 412 | Chappra TL |  | Mr. N K Gupta | Uttam Rai - 7080157757 | Resonia | 6.2 | 20 | 13.8 | Mail lower than ground | 2.2 | 2.4 | 0.2 | Mail lower than ground | 0.378 | 151 | 3.2 | 147.8 | 2026-07-30 | TB 412 - DPR - 2026-07-30.xlsx
TB 501 | erection | Nos. | Mail only | TB 501 | [5 empty] | 5 |  |  | Missing plan | 1 |  |  | Missing actual |  |  |  |  | 2026-07-30 | TB 501 - DPR - 2026-07-30.xlsx
TB 501 | stringing | KM | Mail only | TB 501 | [5 empty] | 5.81 |  |  | Missing plan | 3.57 |  |  | Missing actual |  |  |  |  | 2026-07-30 | TB 501 - DPR - 2026-07-30.xlsx
TB 507 | erection | Nos. | Both | TB 507 | 400/765 KV TB507 |  | Mr. N K Gupta | Amartya Sarkar - 7575003302 | Apparva | 55 | 55 | 0 | Matched | 27 | 24 | -3 | Mail higher than ground | 7 | 556 | 237 | 319 | 2026-07-29 | TB 507 - DPR - 2026-07-29.xlsx
TB 507 | stringing | KM | Both | TB 507 | 400/765 KV TB507 |  | Mr. N K Gupta | Amartya Sarkar - 7575003302 | Apparva | 21.08 | 21 | -0.08 | Mail higher than ground | 5.25 | 5.6 | 0.35 | Mail lower than ground | 3.087 | 203.981 | 25 | 178.981 | 2026-07-29 | TB 507 - DPR - 2026-07-29.xlsx
TB 605 | erection | Nos. | Both | TB 605 | Jallander - Sambha Line |  | Mr. Hitesh Bahri | Aditya Narasimha Kumar - 9550759853 | Indigrid | 41 | 35 | -6 | Mail higher than ground | 23 | 21 | -2 | Mail higher than ground | 13 | 523 | 248 | 275 | 2026-07-30 | TB 605 - DPR - 2026-07-30.xlsx
TB 605 | stringing | KM | Both | TB 605 | Jallander - Sambha Line |  | Mr. Hitesh Bahri | Aditya Narasimha Kumar - 9550759853 | Indigrid | 9.6 | 15 | 5.4 | Mail lower than ground | 3.24 | 3 | -0.24 | Mail higher than ground | 5 | 176 | 1 | 174 | 2026-07-30 | TB 605 - DPR - 2026-07-30.xlsx
TB 608 | erection | Nos. | Both | TB 608 | Alipurdur - Bornagar - Assam |  | Mr. N K Gupta | Nilashis Neogi - 9614739494 | Resonia | 20 | 12 | -8 | Mail higher than ground | 13 | 13 | 0 | Matched | 5 | 316 | 43 | 273 | 2026-07-26 | TB 608 - DPR - 2026-07-26.xlsm
TB 609 | erection | Nos. | Ground only |  | Kutch - Jamnagar Line |  | Mr. Arun Felbin | Argho roy - 9163687007 | RIL |  | 3 |  | Missing plan |  | 1 |  | Missing actual | 1 | 195 | 2 | 193
TB 609 | stringing | KM | Ground only |  | Kutch - Jamnagar Line |  | Mr. Arun Felbin | Argho roy - 9163687007 | RIL |  | 0 |  | Missing plan |  |  |  | Missing actual |  | 74 |  | 74
TB 610 | erection | Nos. | Ground only |  | HVDC Badla - Fathpur |  | Mr. Hitesh Bahri | Sayan Sadhukhan - 7449601054 | Adani |  |  |  | Missing plan |  | 1 |  | Missing actual | 3 | 500 |  | 500
TB 611 | erection | Nos. | Ground only |  | Morena PS (South of Sabalgarh) - Karera (near Datia) 765kV D/C line |  | Mr. Nabajit Barwa | Shyam Biswas - 8670984234 | Indigrid |  | 0 |  | Missing plan |  |  |  | Missing actual |  | 225 |  | 225
TB 611 | stringing | KM | Ground only |  | Morena PS (South of Sabalgarh) - Karera (near Datia) 765kV D/C line |  | Mr. Nabajit Barwa | Shyam Biswas - 8670984234 | Indigrid |  | 0 |  | Missing plan |  |  |  | Missing actual |  | 86 |  | 86

## Activity Totals
activity | mail_plan_total | ground_plan_total | plan_delta_total | mail_actual_total | ground_actual_total | actual_delta_total
erection | 637 | 408 | -243 | 223 | 218 | -6
stringing | 310.96 | 264.17 | -59.98 | 93.32 | 92.98 | 3.91

## Coverage Summary
activity | coverage | row_count
erection | Mail only | 1
erection | Ground only | 4
erection | Both | 16
stringing | Mail only | 2
stringing | Ground only | 6
stringing | Both | 12

## Project Rollup
project_key | activities_in_mail | activities_in_ground | mail_plan_total | ground_plan_total | plan_delta_total | mail_actual_total | ground_actual_total | actual_delta_total | latest_dpr_date
TA 413 | 2 | 2 | 23 | 23 | 0 | 11.29 | 14 | 2.71 | 2026-07-29
TA 414 | 2 | 2 | 45 | 58 | 13 | 14.92 | 13.921 | -0.999 | 2026-07-30
TA 416 | 1 | 0 | 4 | 0 | 0 | 0.68 | 0 | 0 | 2026-07-16
TA 418 | 1 | 1 | 10.98 | 11 | 0.02 | 7.43 | 6 | -1.43 | 2026-07-21
TA 419 | 2 | 2 | 59.5 | 60 | 0.5 | 24.24 | 25.15 | 0.91 | 2026-07-30
TA 504 | 1 | 1 | 6 | 2 | -4 | 4 | 4 | 0 | 2026-07-28
TA 505 | 2 | 2 | 27.33 | 46 | 18.67 | 16.56 | 20 | 3.44 | 2026-07-29
TA 506 | 2 | 2 | 47 | 47 | 0 | 24.93 | 25 | 0.07 | 2026-07-28
TA 509 | 2 | 2 | 27 | 49.17 | 22.17 | 12.91 | 11.909 | -1.001 | 2026-07-29
TA 510 | 2 | 2 | 380 | 15 | -365 | 2 | 2 | 0 | 2026-07-30
TA 512 | 1 | 2 | 20 | 53 | 10 | 28 | 25 | -3 | 2026-07-30
TA 513 | 0 | 2 | 0 | 16 | 0 | 0 | 0 | 0 | 2026-07-28
TA 601 | 1 | 2 | 25 | 25 | 0 | 29 | 28 | -1 | 2026-07-30
TA 602 | 1 | 2 | 20 | 30 | 10 | 11 | 11 | 0 | 2026-07-29
TB 408 | 2 | 2 | 44.46 | 31 | -13.46 | 19.1 | 19 | -0.1 | 2026-07-30
TB 412 | 2 | 2 | 51.2 | 65 | 13.8 | 34.2 | 37.4 | 3.2 | 2026-07-30
TB 501 | 2 | 0 | 10.81 | 0 | 0 | 4.57 | 0 | 0 | 2026-07-30
TB 507 | 2 | 2 | 76.08 | 76 | -0.08 | 32.25 | 29.6 | -2.65 | 2026-07-29
TB 605 | 2 | 2 | 50.6 | 50 | -0.6 | 26.24 | 24 | -2.24 | 2026-07-30
TB 608 | 1 | 1 | 20 | 12 | -8 | 13 | 13 | 0 | 2026-07-26
TB 609 | 0 | 2 | 0 | 3 | 0 | 0 | 1 | 0
TB 610 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
TB 611 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0

## Mail Only
project_key | activity | unit | coverage | mail_project | ground_project | mail_pch | ground_pch | ground_pe | ground_client | mail_plan | ground_plan | plan_delta_ground_minus_mail | plan_status | mail_actual | ground_actual | actual_delta_ground_minus_mail | actual_status | ground_wip | ground_total_scope | ground_completed_upto_prev_month | ground_balance_start_month | latest_dpr_date | latest_dpr_file
TA 416 | stringing | KM | Mail only | TA 416 | [5 empty] | 4 |  |  | Missing plan | 0.68 |  |  | Missing actual |  |  |  |  | 2026-07-16 | TA 416 - DPR - 2026-07-16.xlsx
TB 501 | erection | Nos. | Mail only | TB 501 | [5 empty] | 5 |  |  | Missing plan | 1 |  |  | Missing actual |  |  |  |  | 2026-07-30 | TB 501 - DPR - 2026-07-30.xlsx
TB 501 | stringing | KM | Mail only | TB 501 | [5 empty] | 5.81 |  |  | Missing plan | 3.57 |  |  | Missing actual |  |  |  |  | 2026-07-30 | TB 501 - DPR - 2026-07-30.xlsx

## Ground Only
project_key | activity | unit | coverage | mail_project | ground_project | mail_pch | ground_pch | ground_pe | ground_client | mail_plan | ground_plan | plan_delta_ground_minus_mail | plan_status | mail_actual | ground_actual | actual_delta_ground_minus_mail | actual_status | ground_wip | ground_total_scope | ground_completed_upto_prev_month | ground_balance_start_month | latest_dpr_date | latest_dpr_file
TA 512 | stringing | KM | Ground only |  | 765 KV D/C Bikaner - Shivani line |  | Mr. N K Gupta | Saurabh Katiyar - 8447468911 | PGCIL |  | 23 |  | Missing plan |  |  |  | Missing actual | 5.5 | 124.568 |  | 124.568 | 2026-07-30 | TA 512 - DPR - 2026-07-30.xlsx
TA 513 | erection | Nos. | Ground only |  | TA513 Shivani- Patratu |  | Mr. Hitesh Bahri | Harshit Kumar - 7055470402 | PGCIL |  | 16 |  | Missing plan |  |  |  | Missing actual |  | 619 | 35 | 584 | 2026-07-28 | TA 513 - DPR - 2026-07-28.xlsx
TA 513 | stringing | KM | Ground only |  | TA513 Shivani- Patratu |  | Mr. Hitesh Bahri | Harshit Kumar - 7055470402 | PGCIL |  | 0 |  | Missing plan |  |  |  | Missing actual |  | 230.39 | 0 | 230.39 | 2026-07-28 | TA 513 - DPR - 2026-07-28.xlsx
TA 601 | stringing | KM | Ground only |  | Kurnool - Bidhar part 2 |  | Mr. Arun Felbin | Siddhesh bhoyar - 7020337487 | PGCIL |  | 0 |  | Missing plan |  |  |  | Missing actual |  | 113.27 |  | 113.27 | 2026-07-30 | TA 601 - DPR - 2026-07-30.xlsx
TA 602 | stringing | KM | Ground only |  | HVDC KPS2 - Nagpur TL06 |  | Mr. Arun Felbin | Rishi Shukla - 8299744206 | PGCIL |  | 0 |  | Missing plan |  |  |  | Missing actual |  | 186 | 0 | 186 | 2026-07-29 | TA 602 - DPR - 2026-07-29.xlsx
TB 609 | erection | Nos. | Ground only |  | Kutch - Jamnagar Line |  | Mr. Arun Felbin | Argho roy - 9163687007 | RIL |  | 3 |  | Missing plan |  | 1 |  | Missing actual | 1 | 195 | 2 | 193
TB 609 | stringing | KM | Ground only |  | Kutch - Jamnagar Line |  | Mr. Arun Felbin | Argho roy - 9163687007 | RIL |  | 0 |  | Missing plan |  |  |  | Missing actual |  | 74 |  | 74
TB 610 | erection | Nos. | Ground only |  | HVDC Badla - Fathpur |  | Mr. Hitesh Bahri | Sayan Sadhukhan - 7449601054 | Adani |  |  |  | Missing plan |  | 1 |  | Missing actual | 3 | 500 |  | 500
TB 611 | erection | Nos. | Ground only |  | Morena PS (South of Sabalgarh) - Karera (near Datia) 765kV D/C line |  | Mr. Nabajit Barwa | Shyam Biswas - 8670984234 | Indigrid |  | 0 |  | Missing plan |  |  |  | Missing actual |  | 225 |  | 225
TB 611 | stringing | KM | Ground only |  | Morena PS (South of Sabalgarh) - Karera (near Datia) 765kV D/C line |  | Mr. Nabajit Barwa | Shyam Biswas - 8670984234 | Indigrid |  | 0 |  | Missing plan |  |  |  | Missing actual |  | 86 |  | 86

## Plan Deltas
project_key | activity | unit | coverage | mail_project | ground_project | mail_pch | ground_pch | ground_pe | ground_client | mail_plan | ground_plan | plan_delta_ground_minus_mail | plan_status | mail_actual | ground_actual | actual_delta_ground_minus_mail | actual_status | ground_wip | ground_total_scope | ground_completed_upto_prev_month | ground_balance_start_month | latest_dpr_date | latest_dpr_file
TA 510 | erection | Nos. | Both | TA 510 | 765 KV D/C Ahmedabad - South Olpad line |  | Mr. Arun Felbin | Jayant 7727996705 | PGCIL | 285 | 15 | -270 | Mail higher than ground | 2 | 2 | 0 | Matched | 1 | 299 | 45 | 254 | 2026-07-30 | TA 510 - DPR - 2026-07-30.xlsx
TA 510 | stringing | KM | Both | TA 510 | 765 KV D/C Ahmedabad - South Olpad line |  | Mr. Arun Felbin | Jayant 7727996705 | PGCIL | 95 | 0 | -95 | Mail higher than ground | 0 |  |  | Missing actual |  | 111 | 0 | 111 | 2026-07-30 | TA 510 - DPR - 2026-07-30.xlsx
TA 505 | stringing | KM | Both | TA 505 | 765KV D/C Mandsour - Beawar Tr, Line | Mr. Nabajit Baruah | Mr. Nabajit Barwa | Partha Pratim Pal - 8017746581 | PGCIL | 21.33 | 40 | 18.67 | Mail lower than ground | 14.56 | 18 | 3.44 | Mail lower than ground | 4.221 | 139 | 28 | 111 | 2026-07-29 | TA 505 - DPR - 2026-07-29.xlsx
TA 509 | erection | Nos. | Both | TA 509 | 765 KV D/C Mandsour - Kurawar Tr, Line |  | Mr. Nabajit Barwa | shubayu Das - 8240796656 | PGCIL | 15 | 30 | 15 | Mail lower than ground | 7 | 6 | -1 | Mail higher than ground | 2 | 309 | 223 | 86 | 2026-07-29 | TA 509 - DPR - 2026-07-29.xlsx
TB 412 | stringing | KM | Both | TB 412 | Chappra TL |  | Mr. N K Gupta | Uttam Rai - 7080157757 | Resonia | 6.2 | 20 | 13.8 | Mail lower than ground | 2.2 | 2.4 | 0.2 | Mail lower than ground | 0.378 | 151 | 3.2 | 147.8 | 2026-07-30 | TB 412 - DPR - 2026-07-30.xlsx
TB 408 | stringing | KM | Both | TB 408 | 765 KV D/C Sterlite (Pkg F) |  | Mr. N K Gupta | Raghav Ranjan - 7717770750 | Sterlite | 43.46 | 30 | -13.46 | Mail higher than ground | 18.1 | 18 | -0.1 | Mail higher than ground | 11.5 | 173 | 129 | 44 | 2026-07-30 | TB 408 - DPR - 2026-07-30.xlsx
TA 512 | erection | Nos. | Both | TA 512 | 765 KV D/C Bikaner - Shivani line |  | Mr. N K Gupta | Saurabh Katiyar - 8447468911 | PGCIL | 20 | 30 | 10 | Mail lower than ground | 28 | 25 | -3 | Mail higher than ground | 11 | 319 | 237 | 82 | 2026-07-30 | TA 512 - DPR - 2026-07-30.xlsx
TA 602 | erection | Nos. | Both | TA 602 | HVDC KPS2 - Nagpur TL06 |  | Mr. Arun Felbin | Rishi Shukla - 8299744206 | PGCIL | 20 | 30 | 10 | Mail lower than ground | 11 | 11 | 0 | Matched | 1 | 478 | 93 | 385 | 2026-07-29 | TA 602 - DPR - 2026-07-29.xlsx
TA 414 | erection | Nos. | Both | TA 414 | 765kV D/C Vataman - Navsari line | Mr. Arun Felbin | Mr. Arun Felbin | Pawan Shrivastava - 9525760939 | PGCIL | 30 | 40 | 10 | Mail lower than ground | 12 | 11 | -1 | Mail higher than ground | 4 | 352 | 267 | 85 | 2026-07-30 | TA 414 - DPR - 2026-07-30.xlsx
TB 608 | erection | Nos. | Both | TB 608 | Alipurdur - Bornagar - Assam |  | Mr. N K Gupta | Nilashis Neogi - 9614739494 | Resonia | 20 | 12 | -8 | Mail higher than ground | 13 | 13 | 0 | Matched | 5 | 316 | 43 | 273 | 2026-07-26 | TB 608 - DPR - 2026-07-26.xlsm
TA 509 | stringing | KM | Both | TA 509 | 765 KV D/C Mandsour - Kurawar Tr, Line |  | Mr. Nabajit Barwa | shubayu Das - 8240796656 | PGCIL | 12 | 19.17 | 7.17 | Mail lower than ground | 5.91 | 5.909 | -0.001 | Matched | 1.582 | 120 | 4 | 116 | 2026-07-29 | TA 509 - DPR - 2026-07-29.xlsx
TB 605 | erection | Nos. | Both | TB 605 | Jallander - Sambha Line |  | Mr. Hitesh Bahri | Aditya Narasimha Kumar - 9550759853 | Indigrid | 41 | 35 | -6 | Mail higher than ground | 23 | 21 | -2 | Mail higher than ground | 13 | 523 | 248 | 275 | 2026-07-30 | TB 605 - DPR - 2026-07-30.xlsx
TB 605 | stringing | KM | Both | TB 605 | Jallander - Sambha Line |  | Mr. Hitesh Bahri | Aditya Narasimha Kumar - 9550759853 | Indigrid | 9.6 | 15 | 5.4 | Mail lower than ground | 3.24 | 3 | -0.24 | Mail higher than ground | 5 | 176 | 1 | 174 | 2026-07-30 | TB 605 - DPR - 2026-07-30.xlsx
TA 504 | erection | Nos. | Both | TA 504 | 765 KV D/C Rishabhdeo - Mansour Tr, Line | Mr. Nabajit Baruah | Mr. Nabajit Barwa | Abir Kumar Das - 8583937594 / 9830806660 | PGCIL | 6 | 2 | -4 | Mail higher than ground | 4 | 4 | 0 | Matched | 1 | 186 | 125 | 61 | 2026-07-28 | TA 504 - DPR - 2026-07-28.xlsx
TA 414 | stringing | KM | Both | TA 414 | 765kV D/C Vataman - Navsari line | Mr. Arun Felbin | Mr. Arun Felbin | Pawan Shrivastava - 9525760939 | PGCIL | 15 | 18 | 3 | Mail lower than ground | 2.92 | 2.921 | 0.001 | Matched | 1.148 | 128 | 25 | 103 | 2026-07-30 | TA 414 - DPR - 2026-07-30.xlsx
TA 419 | stringing | KM | Both | TA 419 | 765 KV D/C Sikar - Narela Line |  | Mr. N K Gupta | Suraj Chaudhary - 7439328228 | PGCIL | 19.5 | 20 | 0.5 | Mail lower than ground | 6.24 | 5.15 | -1.09 | Mail higher than ground | 7.76 | 122 | 2 | 120 | 2026-07-30 | TA 419 - DPR - 2026-07-30.xlsx
TB 507 | stringing | KM | Both | TB 507 | 400/765 KV TB507 |  | Mr. N K Gupta | Amartya Sarkar - 7575003302 | Apparva | 21.08 | 21 | -0.08 | Mail higher than ground | 5.25 | 5.6 | 0.35 | Mail lower than ground | 3.087 | 203.981 | 25 | 178.981 | 2026-07-29 | TB 507 - DPR - 2026-07-29.xlsx
TA 418 | stringing | KM | Both | TA 418 | 765 KV D/C Kopal - Raichor |  | Mr. Arun Felbin | S Ajith Jayasurya - 9788911010 | PGCIL | 10.98 | 11 | 0.02 | Mail lower than ground | 7.43 | 6 | -1.43 | Mail higher than ground | 0.417 | 48 | 37 | 11 | 2026-07-21 | TA 418 - DPR - 2026-07-21.xlsx
TA 413 | stringing | KM | Both | TA 413 | 765 KV D/C Bikaner Complex PART-A line | Mr. NK Gupta | Mr. N K Gupta | Santosh Kumar - 9370318069 | PGCIL | 20 | 20 | 0 | Matched | 11.29 | 14 | 2.71 | Mail lower than ground | 7.16 | 118 | 87 | 31 | 2026-07-29 | TA 413 - DPR - 2026-07-29.xlsx
TA 413 | erection | Nos. | Both | TA 413 | 765 KV D/C Bikaner Complex PART-A line | Mr. NK Gupta | Mr. N K Gupta | Santosh Kumar - 9370318069 | PGCIL | 3 | 3 | 0 | Matched | 0 |  |  | Missing actual | 1 | 306 | 303 | 3 | 2026-07-29 | TA 413 - DPR - 2026-07-29.xlsx
TA 506 | stringing | KM | Both | TA 506 | 400 KV D/C Sirohi - Chittorgarh Tr, Line |  | Mr. Nabajit Barwa | Abir Kumar Das - 8583937594 / 9830806660 | PGCIL | 27 | 27 | 0 | Matched | 11.93 | 12 | 0.07 | Mail lower than ground | 10 | 223 | 66 | 157 | 2026-07-28 | TA 506 - DPR - 2026-07-28.xlsx
TA 506 | erection | Nos. | Both | TA 506 | 400 KV D/C Sirohi - Chittorgarh Tr, Line |  | Mr. Nabajit Barwa | Abir Kumar Das - 8583937594 / 9830806660 | PGCIL | 20 | 20 | 0 | Matched | 13 | 13 | 0 | Matched | 4 | 602 | 422 | 180 | 2026-07-28 | TA 506 - DPR - 2026-07-28.xlsx
TA 505 | erection | Nos. | Both | TA 505 | 765KV D/C Mandsour - Beawar Tr, Line |  | Mr. Nabajit Barwa | Partha Pratim Pal - 8017746581 | PGCIL | 6 | 6 | 0 | Matched | 2 | 2 | 0 | Matched | 1 | 379 | 364 | 15 | 2026-07-29 | TA 505 - DPR - 2026-07-29.xlsx
TA 419 | erection | Nos. | Both | TA 419 | 765 KV D/C Sikar - Narela Line |  | Mr. N K Gupta | Suraj Chaudhary - 7439328228 | PGCIL | 40 | 40 | 0 | Matched | 18 | 20 | 2 | Mail lower than ground | 10 | 331 | 222 | 109 | 2026-07-30 | TA 419 - DPR - 2026-07-30.xlsx
TB 408 | erection | Nos. | Both | TB 408 | 765 KV D/C Sterlite (Pkg F) |  | Mr. N K Gupta | Raghav Ranjan - 7717770750 | Sterlite | 1 | 1 | 0 | Matched | 1 | 1 | 0 | Matched |  | 485 | 484 | 1 | 2026-07-30 | TB 408 - DPR - 2026-07-30.xlsx
TA 601 | erection | Nos. | Both | TA 601 | Kurnool - Bidhar part 2 |  | Mr. Arun Felbin | Siddhesh bhoyar - 7020337487 | PGCIL | 25 | 25 | 0 | Matched | 29 | 28 | -1 | Mail higher than ground | 6 | 292 | 87 | 205 | 2026-07-30 | TA 601 - DPR - 2026-07-30.xlsx
TB 507 | erection | Nos. | Both | TB 507 | 400/765 KV TB507 |  | Mr. N K Gupta | Amartya Sarkar - 7575003302 | Apparva | 55 | 55 | 0 | Matched | 27 | 24 | -3 | Mail higher than ground | 7 | 556 | 237 | 319 | 2026-07-29 | TB 507 - DPR - 2026-07-29.xlsx
TB 412 | erection | Nos. | Both | TB 412 | Chappra TL |  | Mr. N K Gupta | Uttam Rai - 7080157757 | Resonia | 45 | 45 | 0 | Matched | 32 | 35 | 3 | Mail lower than ground | 6 | 505 | 138 | 367 | 2026-07-30 | TB 412 - DPR - 2026-07-30.xlsx

## Actual Deltas
project_key | activity | unit | coverage | mail_project | ground_project | mail_pch | ground_pch | ground_pe | ground_client | mail_plan | ground_plan | plan_delta_ground_minus_mail | plan_status | mail_actual | ground_actual | actual_delta_ground_minus_mail | actual_status | ground_wip | ground_total_scope | ground_completed_upto_prev_month | ground_balance_start_month | latest_dpr_date | latest_dpr_file
TA 505 | stringing | KM | Both | TA 505 | 765KV D/C Mandsour - Beawar Tr, Line | Mr. Nabajit Baruah | Mr. Nabajit Barwa | Partha Pratim Pal - 8017746581 | PGCIL | 21.33 | 40 | 18.67 | Mail lower than ground | 14.56 | 18 | 3.44 | Mail lower than ground | 4.221 | 139 | 28 | 111 | 2026-07-29 | TA 505 - DPR - 2026-07-29.xlsx
TA 512 | erection | Nos. | Both | TA 512 | 765 KV D/C Bikaner - Shivani line |  | Mr. N K Gupta | Saurabh Katiyar - 8447468911 | PGCIL | 20 | 30 | 10 | Mail lower than ground | 28 | 25 | -3 | Mail higher than ground | 11 | 319 | 237 | 82 | 2026-07-30 | TA 512 - DPR - 2026-07-30.xlsx
TB 412 | erection | Nos. | Both | TB 412 | Chappra TL |  | Mr. N K Gupta | Uttam Rai - 7080157757 | Resonia | 45 | 45 | 0 | Matched | 32 | 35 | 3 | Mail lower than ground | 6 | 505 | 138 | 367 | 2026-07-30 | TB 412 - DPR - 2026-07-30.xlsx
TB 507 | erection | Nos. | Both | TB 507 | 400/765 KV TB507 |  | Mr. N K Gupta | Amartya Sarkar - 7575003302 | Apparva | 55 | 55 | 0 | Matched | 27 | 24 | -3 | Mail higher than ground | 7 | 556 | 237 | 319 | 2026-07-29 | TB 507 - DPR - 2026-07-29.xlsx
TA 413 | stringing | KM | Both | TA 413 | 765 KV D/C Bikaner Complex PART-A line | Mr. NK Gupta | Mr. N K Gupta | Santosh Kumar - 9370318069 | PGCIL | 20 | 20 | 0 | Matched | 11.29 | 14 | 2.71 | Mail lower than ground | 7.16 | 118 | 87 | 31 | 2026-07-29 | TA 413 - DPR - 2026-07-29.xlsx
TA 419 | erection | Nos. | Both | TA 419 | 765 KV D/C Sikar - Narela Line |  | Mr. N K Gupta | Suraj Chaudhary - 7439328228 | PGCIL | 40 | 40 | 0 | Matched | 18 | 20 | 2 | Mail lower than ground | 10 | 331 | 222 | 109 | 2026-07-30 | TA 419 - DPR - 2026-07-30.xlsx
TB 605 | erection | Nos. | Both | TB 605 | Jallander - Sambha Line |  | Mr. Hitesh Bahri | Aditya Narasimha Kumar - 9550759853 | Indigrid | 41 | 35 | -6 | Mail higher than ground | 23 | 21 | -2 | Mail higher than ground | 13 | 523 | 248 | 275 | 2026-07-30 | TB 605 - DPR - 2026-07-30.xlsx
TA 418 | stringing | KM | Both | TA 418 | 765 KV D/C Kopal - Raichor |  | Mr. Arun Felbin | S Ajith Jayasurya - 9788911010 | PGCIL | 10.98 | 11 | 0.02 | Mail lower than ground | 7.43 | 6 | -1.43 | Mail higher than ground | 0.417 | 48 | 37 | 11 | 2026-07-21 | TA 418 - DPR - 2026-07-21.xlsx
TA 419 | stringing | KM | Both | TA 419 | 765 KV D/C Sikar - Narela Line |  | Mr. N K Gupta | Suraj Chaudhary - 7439328228 | PGCIL | 19.5 | 20 | 0.5 | Mail lower than ground | 6.24 | 5.15 | -1.09 | Mail higher than ground | 7.76 | 122 | 2 | 120 | 2026-07-30 | TA 419 - DPR - 2026-07-30.xlsx
TA 414 | erection | Nos. | Both | TA 414 | 765kV D/C Vataman - Navsari line | Mr. Arun Felbin | Mr. Arun Felbin | Pawan Shrivastava - 9525760939 | PGCIL | 30 | 40 | 10 | Mail lower than ground | 12 | 11 | -1 | Mail higher than ground | 4 | 352 | 267 | 85 | 2026-07-30 | TA 414 - DPR - 2026-07-30.xlsx
TA 601 | erection | Nos. | Both | TA 601 | Kurnool - Bidhar part 2 |  | Mr. Arun Felbin | Siddhesh bhoyar - 7020337487 | PGCIL | 25 | 25 | 0 | Matched | 29 | 28 | -1 | Mail higher than ground | 6 | 292 | 87 | 205 | 2026-07-30 | TA 601 - DPR - 2026-07-30.xlsx
TA 509 | erection | Nos. | Both | TA 509 | 765 KV D/C Mandsour - Kurawar Tr, Line |  | Mr. Nabajit Barwa | shubayu Das - 8240796656 | PGCIL | 15 | 30 | 15 | Mail lower than ground | 7 | 6 | -1 | Mail higher than ground | 2 | 309 | 223 | 86 | 2026-07-29 | TA 509 - DPR - 2026-07-29.xlsx
TB 507 | stringing | KM | Both | TB 507 | 400/765 KV TB507 |  | Mr. N K Gupta | Amartya Sarkar - 7575003302 | Apparva | 21.08 | 21 | -0.08 | Mail higher than ground | 5.25 | 5.6 | 0.35 | Mail lower than ground | 3.087 | 203.981 | 25 | 178.981 | 2026-07-29 | TB 507 - DPR - 2026-07-29.xlsx
TB 605 | stringing | KM | Both | TB 605 | Jallander - Sambha Line |  | Mr. Hitesh Bahri | Aditya Narasimha Kumar - 9550759853 | Indigrid | 9.6 | 15 | 5.4 | Mail lower than ground | 3.24 | 3 | -0.24 | Mail higher than ground | 5 | 176 | 1 | 174 | 2026-07-30 | TB 605 - DPR - 2026-07-30.xlsx
TB 412 | stringing | KM | Both | TB 412 | Chappra TL |  | Mr. N K Gupta | Uttam Rai - 7080157757 | Resonia | 6.2 | 20 | 13.8 | Mail lower than ground | 2.2 | 2.4 | 0.2 | Mail lower than ground | 0.378 | 151 | 3.2 | 147.8 | 2026-07-30 | TB 412 - DPR - 2026-07-30.xlsx
TB 408 | stringing | KM | Both | TB 408 | 765 KV D/C Sterlite (Pkg F) |  | Mr. N K Gupta | Raghav Ranjan - 7717770750 | Sterlite | 43.46 | 30 | -13.46 | Mail higher than ground | 18.1 | 18 | -0.1 | Mail higher than ground | 11.5 | 173 | 129 | 44 | 2026-07-30 | TB 408 - DPR - 2026-07-30.xlsx
TA 506 | stringing | KM | Both | TA 506 | 400 KV D/C Sirohi - Chittorgarh Tr, Line |  | Mr. Nabajit Barwa | Abir Kumar Das - 8583937594 / 9830806660 | PGCIL | 27 | 27 | 0 | Matched | 11.93 | 12 | 0.07 | Mail lower than ground | 10 | 223 | 66 | 157 | 2026-07-28 | TA 506 - DPR - 2026-07-28.xlsx
TA 509 | stringing | KM | Both | TA 509 | 765 KV D/C Mandsour - Kurawar Tr, Line |  | Mr. Nabajit Barwa | shubayu Das - 8240796656 | PGCIL | 12 | 19.17 | 7.17 | Mail lower than ground | 5.91 | 5.909 | -0.001 | Matched | 1.582 | 120 | 4 | 116 | 2026-07-29 | TA 509 - DPR - 2026-07-29.xlsx
TA 414 | stringing | KM | Both | TA 414 | 765kV D/C Vataman - Navsari line | Mr. Arun Felbin | Mr. Arun Felbin | Pawan Shrivastava - 9525760939 | PGCIL | 15 | 18 | 3 | Mail lower than ground | 2.92 | 2.921 | 0.001 | Matched | 1.148 | 128 | 25 | 103 | 2026-07-30 | TA 414 - DPR - 2026-07-30.xlsx
TA 506 | erection | Nos. | Both | TA 506 | 400 KV D/C Sirohi - Chittorgarh Tr, Line |  | Mr. Nabajit Barwa | Abir Kumar Das - 8583937594 / 9830806660 | PGCIL | 20 | 20 | 0 | Matched | 13 | 13 | 0 | Matched | 4 | 602 | 422 | 180 | 2026-07-28 | TA 506 - DPR - 2026-07-28.xlsx
TA 504 | erection | Nos. | Both | TA 504 | 765 KV D/C Rishabhdeo - Mansour Tr, Line | Mr. Nabajit Baruah | Mr. Nabajit Barwa | Abir Kumar Das - 8583937594 / 9830806660 | PGCIL | 6 | 2 | -4 | Mail higher than ground | 4 | 4 | 0 | Matched | 1 | 186 | 125 | 61 | 2026-07-28 | TA 504 - DPR - 2026-07-28.xlsx
TA 505 | erection | Nos. | Both | TA 505 | 765KV D/C Mandsour - Beawar Tr, Line |  | Mr. Nabajit Barwa | Partha Pratim Pal - 8017746581 | PGCIL | 6 | 6 | 0 | Matched | 2 | 2 | 0 | Matched | 1 | 379 | 364 | 15 | 2026-07-29 | TA 505 - DPR - 2026-07-29.xlsx
TB 408 | erection | Nos. | Both | TB 408 | 765 KV D/C Sterlite (Pkg F) |  | Mr. N K Gupta | Raghav Ranjan - 7717770750 | Sterlite | 1 | 1 | 0 | Matched | 1 | 1 | 0 | Matched |  | 485 | 484 | 1 | 2026-07-30 | TB 408 - DPR - 2026-07-30.xlsx
TA 602 | erection | Nos. | Both | TA 602 | HVDC KPS2 - Nagpur TL06 |  | Mr. Arun Felbin | Rishi Shukla - 8299744206 | PGCIL | 20 | 30 | 10 | Mail lower than ground | 11 | 11 | 0 | Matched | 1 | 478 | 93 | 385 | 2026-07-29 | TA 602 - DPR - 2026-07-29.xlsx
TA 510 | erection | Nos. | Both | TA 510 | 765 KV D/C Ahmedabad - South Olpad line |  | Mr. Arun Felbin | Jayant 7727996705 | PGCIL | 285 | 15 | -270 | Mail higher than ground | 2 | 2 | 0 | Matched | 1 | 299 | 45 | 254 | 2026-07-30 | TA 510 - DPR - 2026-07-30.xlsx
TB 608 | erection | Nos. | Both | TB 608 | Alipurdur - Bornagar - Assam |  | Mr. N K Gupta | Nilashis Neogi - 9614739494 | Resonia | 20 | 12 | -8 | Mail higher than ground | 13 | 13 | 0 | Matched | 5 | 316 | 43 | 273 | 2026-07-26 | TB 608 - DPR - 2026-07-26.xlsm