## Progress Summary
#VALUE! | Project Code - | TB-408 | Date | 2026-07-29 |  | Head - T&D | Rajinder Gupta |  | Head T&D-North | N. K. Gupta | Regional Manager | Rajnish Pandey |  |  | Shortcut for previous of Full description
| Client Name- | Resonia Limited (Formally Sterlite Power Transmission Limited) |  |  |  | Project Manager | Virendra Gupta |  |  |  | Planning Engineer | Raghav Ranjan |  |  | Link for go through
| Project Name- | 765KV D/C Fatehgarh III- Beawar Transmission Line, PKG F |  |  |  | Effective Date | 2023-12-06 |  | End Date | 28-02-2026 (TE awaited) | LOA Value | Rs 283.08 Cr Supply -Rs 209.88 Cr., Service.-Rs 73.20 Cr |  |  | X-ing Status'!A1
Sr. No. | Activity | As per latest Estimate | Cumm. Progress up to last Month (incl. Tata) | Opening Balance (This Month, excl. Tata) | Plan for this Month | Today Progress | MTD | WIP | Cumulative Progress | Balance | Gangs at present | Remarks | Support Required | % Completion | L2 Schedule'!A1
1 | Check Survey (Kms) | 191.392 | 191.393 | -0.001 | -0.001 |  |  |  | 191.393 | -0.001 | - |  |  | 100.0005 | Hindrance Register (Row)'!A1
2 | Foundation (Nos.) | 485 | 485 | 0 | 0 |  |  |  | 485 | 0 | - |  |  | 100 | Survey!A1
3 | Earthing (Nos.) | 485 | 485 | 0 | 0 |  |  |  | 485 | 0 | - |  |  | 100 | Foundation!A1
4 | Tower Erection (Nos) | 485 | 484 | 1 | 1 |  | 1 |  | 485 | 0 | - |  |  | 100 | Earthing!A1
5 | Tack Welding (Nos) | 485 | 441 | 44 | 44 |  | 23 | 1 | 464 | 21 | 1 |  |  | 95.6701 | Erection!A1
6 | Paying Out (Kms) | 191.392 | 152.748 | 38.644 | 38.674 |  | 15.62 | 9.1426 | 168.368 | 23.024 | 4 | AP17-18:- WIP. AP25-26:- WIP. AP28-29:- WIP. AP31-32:- WIP. | Tata Scope:- 23.288 [19.1 Kms from AP32-42 & 4.17 Kms AP18-20] | 87.9702 | Tackwelding!A1
7 | Final Sag (Kms) | 191.392 | 147.9275 | 43.4645 | 43.4645 |  | 18.0969 | 2.3362 | 166.0244 | 25.3676 |  | AP16-17:- WIP. |  | 86.7458 | Stringing!A1
8 | OPGW (Kms) | 191.392 | 119.054 | 72.338 | 40 |  | 39.244 | 2.8104 | 158.298 | 33.094 | 3 |  |  | 82.7088 | Stringing associated works'!A1
OPGW!A1
Workfront Status | [14 empty] | Visual chart'!A1
Page Chart'!A1
A. Foundation (in Nos) | [14 empty] | Benching F'!A1
Balance on 1st of this month | Progress MTD | WIP | Clear/Yet to attempt | ROW | Remarks
0 | 0 | 0 | 0 | 0
B. Erection (in Nos)
Balance on 1st of this month | Progress MTD | WIP | Clear/Yet to attempt | ROW | Linked With Fnd | Remarks
1 | 1 | 0 | 0 | 0 | 0
C. Stringing (in Kms)
STR P/Out Bal. on starting of this month | Progress MTD | WIP | TATA (Additional) | ROW | Readiness awaited due to Erec. | Shutdown Required 33 kV & above
38.644 | 15.62 | 9.1426 | 4.115 | 9.7201 | 0 | 0
0.0463

## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manger | Section Incharge | Supervisor
TB408 | 765 KV Beawer Transmission Line, PKG F | Resonia Limited | 2023-12-06 | 2025-10-30 | Mr. Raghav Ranjan | Mr. N. K. Gupta | Mr. Rajnish Pandey | Mr. Virendra Gupta | Mr. Dev Saran Swarakar | Mr. Ganesh Singh
[9 empty] | Mr. Rajeev Kumar | Mr. Umesh Prashad
[9 empty] | Mr. Vivek Shukla | Mr. Rajesh Paul
[9 empty] | Mr. Ram Tirath Singh | Mr. Aslam Ansari
[9 empty] | Mr. Jitendra Saini | Mr. Lal Babu Patel
[9 empty] | Mr. Dhiraj Adhikari | Mr. V Challe Durai
[9 empty] | Mr. Mohammad Tabrej | Mr. Vimal Chandra
Mr. Soumitra Knor
Mr. R N Yadav
Mr. Ramji Tanti
Mr. Mahesh Dhaka
Mr. Pradeep Kumar
Mr. Dineshwar Mahto
Mr. Niraj Kumar
Mr. Milan
Mr. Sonkaran Patel
Mr. Rakesh Pramanik
Mr. Jyoti Kumar
Mr. Baleswar Mahto
Mr. Sunder Lal
Mr. Nirmal Mahto
Mr. Jainath Mahto
Mr. Acche Lal
Mr. Ajay Malakar
Mr. Dhananjay Kumar
Mr. Pradeep Kumar
Mr. Gautam Kumar
Mr. Vikash Kumar

## X-ing Status
Progress Summary'!A1
Details of Crossing in 765KV D/C Fatehgarh-III to Beawar Transmission Line, Package F
Sr. No. | Name of Crossing | From | To | Span in Mtrs | Foundation Status | Erection Status | Stringing Status
Power Line Crossing – 9 nos
1 | 400 KV S/C Jaisalmer-Barmer Line | 3/0 | 4/0 | 226.52 | AP3:- Completed AP4:- Completed | AP3:- Completed AP4:- Completed | Completed
2 | 220 KV D/C Barmer-Akal Line | 5/0 | 6/0 | 246.019 | AP5:- Completed AP6:- Completed | AP5:- Completed AP6:- Completed | Completed
3 | 132 KV S/C Sheo-Jaisalmer Line | 7/0 | 8/0 | 210.755 | AP7:- Completed AP8:- Completed | AP7:- Completed AP8:- Completed | Completed
4 | 400 KV D/C Barmer-Jaisalmer-2 Line | 9/0 | 10/0 | 233.076 | AP9:- Completed AP10:- Completed | AP9:- Completed AP10:- Completed | Completed
5 | 132 KV S/C Sheo-Undoo Line | 12/0 | 13/0 | 211.914 | AP12:- Completed AP13:- Completed | AP12:- Completed AP13:- Completed | Completed
6 | 132 KV S/C Undoo-Baytoo Line | 23/0 | 24/0 | 222.155 | AP23:- Completed AP24:- Completed | AP23:- Completed AP24:- Completed | Completed
7 | 400 KV D/C Mandor-JSW Transmission Line | 46/0 | 47/0 | 197.7 | AP46:- Completed AP47:- Completed | AP46:- Completed AP47:- Completed | Completed
8 | 400 KV D/C Line | 56/0 | 57/0 | 179.9 | AP56:- Completed AP57:- Completed | AP56:- Completed AP57:- Completed | Completed
9 | 220 KV D/C Balotra-Boranada Transmission Line | 66/0 | 67/0 | 207.8 | AP66:- Completed AP67:- Completed | AP66:- Completed AP67:- Completed | Completed
NH Crossings-3 Nos | NH Crossing
1 | NH - 68 (Barmer - Jaisalmer) | 5/0 | 6/0 | 246.019 | AP5:- Completed AP6:- Completed | AP5:- Completed AP6:- Completed | Completed
2 | Expressway (Amritsar-Jamnagar) | 58/0 | 59/0 | 238.9 | AP58:- Completed AP59:- Completed | AP58:- Completed AP59:- Completed | Completed
3 | NH | 68/0 | 69/0 | 200.9 | AP68:- Completed AP69:- Completed | AP68:- Completed AP69:- Completed | Completed
Gas Pipe Line-1 Nos | NH Crossing
1 | Gas Pipe Lines | 65/7 | 65/8 | 394.3 | AP65/7:- Completed AP65/8:- Completed | AP65/7:- Completed AP65/8:- Completed | Completed

## L2 Schedule vs Actual
Progress Summary'!A1 | L2 Schedule vs Actual
Line Name: Part F, 765KV D/C Fatehgarh- Beawar Transmission Line
LOI Date: 11-Sep-2023
Effective Date: 06-Dec-2023
| Schedule Completion as per LOA: 05-March-2025 | [5 empty] | Time Extension Extended till- 28.02.2026 (Further Extension applied till 30th July 2026)
| Scope & Discription |  |  |  |  | Before L2 | L2-Approved | [15 empty] | Extension of time (Approved) -1 | [6 empty] | Extension of time (Approved) -2 |  |  |  | Extension of time-3 (Proposed) |  |  |  |  | Remarks
| Sr. No. | Description | Scope of Work | UOM | Qty. | 2023-10-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01
[6 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
| 1 | Release of Sag Template Curve & Tower Spotting Data | Sterlite
| 2 | Approval of repeated tower design & its BOMS | Sterlite
| 3 | Approval of repeated foundation design/drawings | Sterlite
| 4 | Supply
| i) | Manufacturing of Stubs with Earthing material(incl. B&N) | KEC
| A. | Inspection of stub | Sterlite | Nos. | 482 | 1: 40; 2: 100; 3: 100; 5: 100; 6: 65; 8: 77
| B. | Dispatch of stub | KEC | Nos. | 482 | 1: 40; 2: 100; 3: 100; 4: 0; 5: 100; 6: 65; 7: 0; 8: 77; 9: 0; 10: 0; 11: 0; 12: 0; 13: 0
| C. | Receipt of stubs at site | KEC | Nos. | 482 | 1: 40; 2: 100; 3: 100; 4: 0; 5: 100; 6: 65; 7: 0; 8: 77; 9: 0; 10: 0; 11: 0; 12: 0; 13: 0
|  | MFC submitted on |  |  |  | 1: 192; 2: 73; 3: 73
|  | MFC received on |  |  |  | 1: 192; 2: 73; 4: 73; 7: 144
|  | Actual |  |  |  | 1: 40; 2: 120; 3: 0; 4: 10; 6: 152; 7: 39; 8: 5; 11: 27
| ii) | Manufacturing of Tower (incl B&N) | KEC
| A. | Inspection of tower | Sterlite | Nos. | 482 | 1: 50; 2: 60; 3: 60; 4: 60; 5: 60; 6: 65; 7: 66; 8: 31; 9: 30
| B. | Dispatch of tower | KEC | Nos. | 482 | 2: 50; 3: 60; 4: 60; 5: 60; 6: 60; 7: 65; 8: 66; 9: 31; 10: 30; 11: 0; 12: 0; 13: 0
| C. | Receipt of complete towers at site | KEC | Nos. | 482 | 2: 50; 3: 60; 4: 60; 5: 60; 6: 60; 7: 65; 8: 66; 9: 31; 10: 30; 11: 0; 12: 0; 13: 0
|  | MFC submitted on |  |  |  | 1: 97; 2: 128; 6: 65; 7: 192
|  | MFC received on |  |  |  | 1: 97; 2: 128; 7: 257
|  | Actual |  |  |  | 2: 50; 3: 60; 4: 45; 5: 74; 6: 9; 7: 99; 10: 54; 12: 10
| iii) | Supply of following Tower accessories
| A. | Danger Plate | KEC | % | 100 | 9: 100%
| B. | Number Plate | KEC | % | 100 | 9: 100%
| C. | Phase Plate (Set of three) | KEC | % | 100 | 9: 100%
| D. | Circuit Plate (Set of Two) | KEC | & | 100 | 9: 100%
| E. | Anti-Climbing Device | KEC | % | 100 | 9: 100%
| F. | Bird Guard (Set of Three) | KEC | % | 100 | 9: 100%
| iv) | Other's Supply
| A. | Span Marker | KEC | % | 100 | 9: 100%
| B. | Aviation Light | KEC | % | 100 | 9: 100%
| v) | OSM
| A. | Supply of AL59 Zebra Conductor & associated Acessories | Sterlite | % | 100 | 4: 25%; 7: 25%; 9: 25%; 11: 25%
| B. | Supply of Insulator & associated Hardwere | Sterlite | % | 100 | 4: 25%; 7: 25%; 9: 25%; 11: 25%
| C. | Supply of Earth Wire & associated Hardwere | Sterlite | % | 100 | 1: 0; 2: 0; 4: 25%; 5: 0; 7: 25%; 8: 0; 9: 25%; 11: 25%
| D. | Supply of OPGW & associated Hardwere | Sterlite | % | 100 | 1: 0; 2: 0; 6: 25%; 9: 25%; 11: 25%; 12: 25%
| 5 | Erection | [36 empty] | 0
| A. | Establishment of Site Office | [36 empty] | 0
| B. | Route Alignment(Date of Start) | Sterlite | Kms | 191 | [33 empty] | 0
| C. | Detail Survey | Sterlite | Kms | 191 | 1: 90; 2: 71; 3: 30 | 191
|  | Actual |  |  |  | 1: 191 | 191
| D. | Check Survey | KEC | Kms | 191 | 1: 20; 2: 65; 3: 65; 4: 41 | 191
|  | Actual date of submission |  |  |  | 1: 128.337; 2: 2.238; 3: 28.252; 7: 10.313; 8: 5.601; 9: 3.788; 10: 3.65; 12: 2.747; 13: 4.966 | 189.892
|  | Actual date of approval |  |  |  | 1: 86.508; 2: 44.067; 3: 14.03; 6: 12.488; 8: 15.914; 9: 3.788; 12: 3.57; 13: 9.446 | 189.811
| E. | Soil Investigation Location approval | Sterlite | Loc | 193 | 1: 193 | 193
|  | Actual |  |  |  | 2: 24 | 24
| F. | Soil Investigation Location at Site | KEC | Loc | 193 | 1: 40; 2: 40; 3: 60; 4: 53 | 193
|  | Actual |  |  |  | 4: 24 | 24
| G. | Foundation | [36 empty] | 0
| G.1 | Foundation(Incl.Earthing) | KEC | Nos | 482 | 1: 20; 2: 40; 3: 45; 4: 45; 5: 45; 6: 40; 7: 30; 8: 35; 9: 35; 10: 35; 11: 45; 12: 45; 13: 22 | 482
|  | Actual |  |  |  | 1 | 22 | 46 | 36 | 16 | 7 | 15 | 9 | 14 | 26 | 38 | 26 | 9 | 31 | 47 | 27 | 17 | 13 | 13 | 19 | 22 | 8 | 9 | 7 | 3 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 485
|  | Cummulative |  |  |  | 1 | 23 | 69 | 105 | 121 | 128 | 143 | 152 | 166 | 192 | 230 | 256 | 265 | 296 | 343 | 370 | 387 | 400 | 413 | 432 | 454 | 462 | 471 | 478 | 481 | 481 | 481 | 484 | 485 | 485 | 485 | 485 | 485 | 10709
| G.2. | Earthing |  |  |  | 0 | 5 | 35 | 58 | 20 | 10 | 11 | 9 | 10 | 19 | 45 | 20 | 2 | 25 | 37 | 53 | 22 | 12 | 15 | 17 | 19 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451
|  | Cummulative |  |  |  | 0 | 5 | 40 | 98 | 118 | 128 | 139 | 148 | 158 | 177 | 222 | 242 | 244 | 269 | 306 | 359 | 381 | 393 | 408 | 425 | 444 | 449 | 451 | 451 | 451 | 451 | 451 | 451 | 451 | 451 | 451 | 451 | 451 | 10114
| H. | Erection | [36 empty] | 0
| H.1 | Erection of towers (Incl. Tack welding & painting of tower) | KEC | Nos | 482 | 3: 25; 4: 30; 5: 45; 6: 45; 7: 35; 8: 35; 9: 35; 10: 35; 11: 50; 12: 50; 13: 50; 14: 47 | 482
|  | Actual | [6 empty] | 22 | 20 | 19 | 14 | 3 | 2 | 3 | 16 | 30 | 30 | 11 | 16 | 14 | 13 | 7 | 2 | 6 | 23 | 52 | 47 | 25 | 33 | 40 | 11 | 6 | 10 | 3 | 7 | 0 | 0 | 485
|  | Tonnage | MT | [5 empty] | 879.6247 | 782.8797 | 787.2406 | 641.6864 | 112.5131 | 77.6952 | 116.5428 | 652.8044 | 1312.5266 | 1233.2503 | 484.4793 | 739.5367 | 654.4012 | 567.0935 | 358.0625 | 120.3422 | 231.7424 | 981.9642 | 2382.2999 | 2430.3868 | 1309.1609 | 1672.8395 | 1833.481 | 489.2682 | 262.2796 | 608.9285 | 131.445 | 357.8034 | 0 | 0 | 22212.2786
|  | Cummulative | [6 empty] | 22 | 42 | 61 | 75 | 78 | 80 | 83 | 99 | 129 | 159 | 170 | 186 | 200 | 213 | 220 | 222 | 228 | 251 | 303 | 350 | 375 | 408 | 448 | 459 | 465 | 475 | 478 | 485 | 485 | 485 | 7734
| I. | Stringing | [36 empty] | 0
| I.1 | Stringing Conductor & Earthwire | KEC | Kms | 191 | 5: 5; 6: 12; 7: 12; 8: 12; 9: 18; 10: 25; 11: 25; 12: 25; 13: 25; 14: 20; 15: 12 | 191
|  | Actual | [8 empty] | 0 | 0 | 0 | 0 | 0 | 4.877 | 9.431 | 8.629 | 0 | 7.115 | 0 | 9.18 | 1.049 | 3.227 | 0 | 0 | 0 | 3.788 | 0 | 8.949 | 6.1341 | 14.1512 | 6.6175 | 7.477 | 23.1647 | 12.1259 | 2.8942 | 18.0972 | 146.9067
|  | Cummulative | [8 empty] | 0 | 0 | 0 | 0 | 0 | 4.877 | 14.308 | 22.937 | 22.937 | 30.052 | 30.052 | 39.232 | 40.281 | 43.508 | 43.508 | 43.508 | 43.508 | 47.296 | 47.296 | 56.245 | 62.3791 | 76.5303 | 83.1477 | 90.6247 | 113.7894 | 125.9153 | 128.8095 | 146.9067 | 1357.6479
| I.2 | OPGW Stringing | KEC | Kms | 191 | 8: 5; 9: 15; 10: 20; 11: 25; 12: 35; 13: 45; 14: 30; 15: 16 | 191
|  | Actual | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.423 | 8.629 | 0 | 0 | 0 | 5.493 | 4.058 | 0 | 0 | 0 | 14.057 | 10.6128 | 17.003 | 0 | 0 | 7.21 | 11.4506 | 30.8848 | 130.8212
|  | Cummulative | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.423 | 30.052 | 30.052 | 30.052 | 30.052 | 35.545 | 39.603 | 39.603 | 39.603 | 39.603 | 53.66 | 64.2728 | 81.2758 | 81.2758 | 81.2758 | 88.4858 | 99.9364 | 130.8212 | 1016.5916
| J. | Fixing Of Tower Accessories, aviation painting & installation of span marker | KEC | % | 100 | 13: 30%; 14: 30%; 15: 40% | 1
| K. | Checking, Testing & Commissioning/Ready for Commissioning | KEC | Kms. | 191 | 14: 50%; 15: 50% | 1
REMARKS
Represents L2 Schedule. | bar: 0 to 13
Provisional Tower Quantities are 482 Nos.

## Hindrance Register (Row)
Progress Summary'!A1
HINDRANCE REGISTER (Note:- Day to day hindrance are captured on other sheet and intimate to resonia via DPR on Summary Sheet)
1 | Name of the Substation/TL/Project | 765 KV Fatehgarh-3 Beawer Transmission Line Part-F |  |  |  | 2. Name of Work |  | Transmission & Power Distribution
3 | Name of the Executing Agency | KEC International Limited |  |  |  | 3. LOA No. & Date |  | LOI/EPC/FBTL/PART-F/KEC/01 Dated 11.09.2023
Sr. No. | Activity | Total | Open | Close |  |  |  | Progress Summary'!A1
1 | Survey | 20 | 0 | 20
2 | Foundation | 210 | 0 | 210
3 | Erection | 87 | 0 | 87
4 | Stringing | 35 | 4 | 31
5 | Others | 3 | 0 | 3
Total |  | 355 | 4 | 351
Check Survey
S.No | Nature of Hindrance | Loc/Sec. | Affected Activity | Affected Gang Name | Date of 1st attempt | Date of removal (Last attempt) | Period of hindrance | Remarks
1 | Check survey not done due to frequent obstruction by land owner from 38/0 to 39/0. | 38-39 | Survey |  | 2023-12-06 | 2024-10-10 | 310 | Refer KEC letter dated 02-01-24. Reattempted on 09-01-24 but still in ROW. 3rd time attempted on dated 10.07.24 informed to you via mail regarding ROW.
2 | Check survey not done due to frequent obstruction by land owner from 39/0 to 40/0. | 39-40 | Survey |  | 2023-12-06 | 2024-10-10 | 310 | Refer KEC letter dated 02-01-24. Reattempted on 09-01-24 but still in ROW. 3rd time attempted on dated 10.07.24 informed to you via mail regarding ROW.
3 | Check survey is on hold from Gantry to 2/0 due to Non-Finalization of Gantry. | Gty-2 | Survey |  | 2023-12-06 | 2024-07-15 | 223 | Refer KEC letter dated 02-01-24.
4 | Check survey not done due to frequent obstruction by land owner from 10/12 to 11A. | 10/12-11A | Survey |  | 2023-12-06 | 2024-01-16 | 42 | Refer KEC letter dated 02-01-24.
5 | Check survey not done due to ROW from AP 20-AP 21. | 20-21 | Survey |  | 2023-12-06 | 2025-06-23 | 566 | Refer KEC letter dated 02-01-24. SPTL mail dated 20/5/24 having subject Optimization from GTY to AP74 (Part- F). Clearance for check survey received on 17.10.24. however survey team along with machinery idled at this section since 18th. Section is still in ROW. on dated 19.10.2024.
6 | Delay in approval of check survey report from Ap 21 to AP 25. | 21-25 | Survey |  | 2023-12-06 | 2023-12-14 | 9
7 | Delay in approval of check survey report from Ap 14 to AP 20. | 14-20 | Survey |  | 2023-12-06 | 2023-12-14 | 9
8 | ROW in check survey works. | 47-48 | Survey |  | 2023-12-12 | 2023-12-14 | 3
9 | ROW in check survey works. | 70-71 | Survey |  | 2023-12-15 | 2024-12-10 | 362
10 | ROW in check survey works. | 71-72 | Survey |  | 2023-12-15 | 2024-02-09 | 57
11 | ROW in check survey works. | 72-73 | Survey |  | 2023-12-15 | 2024-02-09 | 57
12 | ROW in check survey works. | 73-74 | Survey |  | 2023-12-15 | 2024-07-14 | 213
13 | Delay in approval of check survey report from Ap 32 to AP 37. | 32-37 | Survey |  | 2023-12-21 | 2023-12-29 | 9
14 | Delay in approval of check survey From AP 2-10/12 | 2-10/12 | Survey |  | 2023-12-26 | 2024-01-25 | 31 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
15 | Delay in approval of check survey From AP 11A-14. | 11A-14 | Survey |  | 2023-12-26 | 2024-01-25 | 31 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
16 | Location no 11/5 are on Hold due to ROW during check survey, Centre peg not done for verification of benching and others. | 11/5 | Survey |  | 2024-01-17 | 2024-05-20 | 125 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
17 | Location no 11A/0 are on Hold due to ROW during check survey, Centre peg not done for verification of benching and others. | 11A/0 | Survey |  | 2024-01-17 | 2024-05-20 | 125 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
18 | ROW in check survey works. | 40-41 | Survey |  | 2024-01-27 | 2024-04-08 | 73
19 | ROW in check survey works. | 41-42 | Survey |  | 2024-01-27 | 2024-04-08 | 73
20 | ROW in check survey works. | 42-43 | Survey |  | 2024-01-27 | 2024-04-08 | 73
Foundation
S.No | Nature of Hindrance | Loc/Sec. | Affected Activity | Affected Gang Name | Date of occurrence | Date of removal | Period of hindrance | Remarks
1 | ROW due to obstruction by land owner at Loc No 37/2. Post Excavation work was stopped by Land owners. After that cleared on 07/12/2023. | 37/2 | Foundation | Nagana Rai | 2023-12-06 | 2023-12-07 | 2
2 | ROW encountered in Excavation works. | 62/6 | Foundation |  | 2023-12-14 | 2023-12-15 | 2
3 | ROW due to obstruction by land owner at Loc No 26/2. | 26/2 | Foundation | A.B. Construction | 2023-12-16 | 2023-12-17 | 2 | Refer Mail dated 16/12/2023.
4 | Our Whole team of one gang along with its machinery are completely idle at location no 26/2 | 26/2 | Foundation | A.B. Construction | 2023-12-16 | 2023-12-17 | 2 | Idled Resources (Highly Skilled manpower-1, Skilled:- 2, Semi Skilled:- 3, Unskilled:- 4, JCB with operator:- 1, Azax flori with operator:- 1, Tracktor with operator:- 1, Tanker with Operator:- 1, Bolero/Camper with Diesel:- 1)
5 | ROW at Location No 27/11. | 27/11 | Foundation | Nagana Rai | 2023-12-06 | 2024-02-12 | 69 | Email dated 18/1/24 regarding Frequent obstruction by landowners. Your email dated 12.02.24 regarding workfront
6 | ROW at location no 28/1 due to frequent interupption by land owner of PKG F. | 28/1 | Foundation | N.R. Enterprises | 2023-12-26 | 2025-06-11 | 534 | Reference Email dated 26/12/2023.
7 | Gang is idled for full day. During idling attempted 5 nos locations to start the work. But all are found in ROW. |  | Foundation | N.R. Enterprises | 2023-12-26 | 2023-12-29 | 4 | Reference Email dated 26/12/2023. Idled Resources (Highly Skilled manpower-1, Skilled:- 2, Semi Skilled:- 3, Unskilled:- 5, JCB with operator:- 1, Azax flori with operator:- 1, Tracktor with operator:- 1, Tanker with Operator:- 1, Bolero/Camper with Diesel:- 1)
8 | ROW in Foundation work in sawan Moolraj village at Loc No 28/2 | 28/2 | Foundation |  | 2023-12-26 | 2024-01-27 | 33 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
9 | ROW in Foundation work in sawan Moolraj village at Loc No 28/3 | 28/3 | Foundation |  | 2023-12-26 | 2025-02-03 | 406 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
10 | ROW in Foundation work in sawan Moolraj village at Loc No 28/4 | 28/4 | Foundation |  | 2023-12-26 | 2025-02-03 | 406 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
11 | ROW in Foundation work in sawan Moolraj village at Loc No 28/5 | 28/5 | Foundation |  | 2023-12-26 | 2025-01-22 | 394 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
12 | ROW in Foundation work in sawan Moolraj village at Loc No 28/6 | 28/6 | Foundation |  | 2023-12-26 | 2024-01-16 | 22 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
13 | ROW in Foundation work in sawan Moolraj village at Loc No 28/7 | 28/7 | Foundation |  | 2023-12-26 | 2025-01-30 | 402 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
14 | ROW in Foundation work in sawan Moolraj village at Loc No 28/8 | 28/8 | Foundation |  | 2023-12-26 | 2025-01-25 | 397 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
15 | ROW in Foundation work in sawan Moolraj village at Loc No 29/0 | 29/0 | Foundation |  | 2023-12-26 | 2025-01-11 | 383 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
16 | ROW in Foundation work in sawan Moolraj village at Loc No 29/1 | 29/1 | Foundation |  | 2023-12-26 | 2025-02-22 | 425 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
17 | ROW in Foundation work in sawan Moolraj village at Loc No 29/2 | 29/2 | Foundation |  | 2023-12-26 | 2025-03-01 | 432 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
18 | ROW in Foundation work in sawan Moolraj village at Loc No 29/3 | 29/3 | Foundation |  | 2023-12-26 | 2025-03-02 | 433 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
19 | ROW in Foundation work in sawan Moolraj village at Loc No 29/4 | 29/4 | Foundation |  | 2023-12-26 | 2025-02-20 | 423 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
20 | ROW in Foundation work in sawan Moolraj village at Loc No 30/0 | 30/0 | Foundation |  | 2023-12-26 | 2025-02-13 | 416 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
21 | ROW in Foundation work in sawan Moolraj village at Loc No 30/1 | 30/1 | Foundation |  | 2023-12-26 | 2025-02-15 | 418 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
22 | ROW in Foundation work in sawan Moolraj village at Loc No 30/2 | 30/2 | Foundation |  | 2023-12-26 | 2025-02-28 | 431 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
23 | ROW in Foundation work in sawan Moolraj village at Loc No 30/3 | 30/3 | Foundation |  | 2023-12-26 | 2025-02-25 | 428 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
24 | ROW in Foundation work in sawan Moolraj village at Loc No 30/4 | 30/4 | Foundation |  | 2023-12-26 | 2025-05-21 | 513 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
25 | ROW in Foundation work in sawan Moolraj village at Loc No 30/5 | 30/5 | Foundation |  | 2023-12-26 | 2025-05-30 | 522 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
26 | ROW in Foundation work in sawan Moolraj village at Loc No 30/6 | 30/6 | Foundation |  | 2023-12-26 | 2025-06-10 | 533 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
27 | ROW in Foundation work in sawan Moolraj village at Loc No 31/0 | 31/0 | Foundation |  | 2023-12-26 | 2025-06-23 | 546 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
28 | ROW in Foundation work in sawan Moolraj village at Loc No 31/1 | 31/1 | Foundation |  | 2023-12-26 | 2025-03-05 | 436 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
29 | ROW in Foundation work in sawan Moolraj village at Loc No 31/2 | 31/2 | Foundation |  | 2023-12-26 | 2025-03-02 | 433 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
30 | ROW in Foundation work in sawan Moolraj village at Loc No 32/0 | 32/0 | Foundation |  | 2023-12-26 | 2025-02-26 | 429 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
31 | ROW encountered while pit marking. | 59/15 | Foundation |  | 2024-01-11 | 2024-01-15 | 5
32 | ROW encountered while pit marking. | 59/16 | Foundation |  | 2024-01-11 | 2024-01-15 | 5
33 | ROW encountered while pit marking. | 60/3 | Foundation |  | 2024-01-11 | 2024-01-13 | 3
34 | ROW encountered while pit marking. | 60/4 | Foundation |  | 2024-01-11 | 2024-01-13 | 3
35 | ROW encountered while pit marking. | 60/11 | Foundation |  | 2024-01-13 | 2024-01-19 | 7
36 | Shifting of 11 KV Line in Location No 26/4 as 11 KV Line pass through centre of the Pit D. | 26/4 | Foundation |  | 2024-01-20 | 2024-01-23 | 4 | Email dated 20/01/2024 regarding shifting of 11 KV Line. On dated 23/1/24, FDN location 5 Mtr shifted towards 26/3 for execution of Foundation works.
37 | Excavation work stopped at 28/2 after completion of 3 Pit excavation works due to ROW. | 28/2 | Foundation | A.B. Construction | 2024-01-28 | 2024-02-12 | 16 | D.P.R. Dated 28-01-24. 10 Nos Manpower are idled due to this hindrances (confirmed by D.P.R. Dated 29.01.2024), Your email dated 12.02.24 regarding workfront
38 | ROW encountered during excavation . | 64/10 | Foundation |  | 2024-02-01 | 2024-02-07 | 7
39 | Excavation work could not done at 27/5 after completion of 3 Pit excavation works due to ROW. | 27/5 | Foundation | Majisa Construction | 2024-02-02 | 2024-03-05 | 33 | DPR dated 03.02.24. Email dated 22.02.24 Sterlite's Part G & F 765KV Fategarh -III Beawar TL
40 | Excavation work could not done at 27/6 due to ROW. | 27/6 | Foundation | Majisa Construction | 2024-02-08 | 2024-05-07 | 90
41 | Excavation work could not done at 27/7 due to ROW. | 27/7 | Foundation | Majisa Construction | 2024-02-08 | 2025-05-18 | 466
42 | Excavation work could not done at 32/1 due to ROW. | 32/1 | Foundation |  | 2024-02-08 | 2025-02-28 | 387
43 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 32/2 | Foundation |  | 2024-02-08 | 2025-02-07 | 366
44 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 32/3 | Foundation |  | 2024-02-08 | 2025-02-03 | 362
45 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 32/4 | Foundation |  | 2024-02-08 | 2025-02-03 | 362
46 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 33/0 | Foundation |  | 2024-02-08 | 2025-02-12 | 371
47 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 33/1 | Foundation |  | 2024-02-08 | 2025-01-31 | 359
48 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 34/0 | Foundation |  | 2024-02-08 | 2025-01-27 | 355
49 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 34/1 | Foundation |  | 2024-02-08 | 2025-01-05 | 333
50 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 34/2 | Foundation |  | 2024-02-08 | 2025-01-16 | 344
51 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 34/3 | Foundation |  | 2024-02-08 | 2024-02-14 | 7 | Email dated 14.01.2024 regarding KEC - Sterlite's Part G & F 765KV Fategarh -III Beawar TL
52 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 34/4 | Foundation |  | 2024-02-08 | 2025-02-15 | 374
53 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/0 | Foundation |  | 2024-02-08 | 2025-01-02 | 330
54 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/1 | Foundation |  | 2024-02-08 | 2025-03-20 | 407
55 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/2 | Foundation |  | 2024-02-08 | 2025-01-03 | 331
56 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/3 | Foundation |  | 2024-02-08 | 2025-01-30 | 358 | Your email dated 12.02.24 regarding workfront. This locations is reattempted on 28.01.2024 after verbal communication by SPTL by the location found in ROW. Again SPTL claimed that ROW cleared on 30.01.25.
57 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/4 | Foundation |  | 2024-02-08 | 2024-02-12 | 5 | Your email dated 12.02.24 regarding workfront
58 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/5 | Foundation |  | 2024-02-08 | 2025-01-27 | 355
59 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 36/0 | Foundation |  | 2024-02-08 | 2024-02-12 | 5 | Your email dated 12.02.24 regarding workfront
60 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 36/2 | Foundation |  | 2024-02-08 | 2025-05-31 | 479
61 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 36/3 | Foundation |  | 2024-02-08 | 2025-05-31 | 479
62 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 36/4 | Foundation |  | 2024-02-08 | 2025-05-31 | 479
63 | ROW in Excavation as Landowner not allowing for pit marking. | 26/7 | Foundation | Mehai Construction | 2024-02-19 | 2024-12-30 | 316 | DPR of 19.02.24. Email dated Sterlite's Part G & F 765KV Fategarh -III Beawar TL.
64 | ROW in Pit marking as Landowner not allowing for pit marking. | 26/8 | Foundation | Mehai Construction | 2024-02-19 | 2025-10-28 | 618 | DPR of 19.02.24. Email dated Sterlite's Part G & F 765KV Fategarh -III Beawar TL. Cleared on 28.10.2025.
65 | ROW in Pit marking by Landowner. Further nearby location 22/0 excavation not done due to ROW. Excavator machine is standing idle. He committed to increase the gang strength but due to non-availability of clear work front they have planned to reduce the strength if locations not allocated timely. | 22/0 | Foundation |  | 2024-02-18 | 2025-11-07 | 629 | DPR of 19.02.24. Email dated Sterlite's Part G & F 765KV Fategarh -III Beawar TL. Email dated 25.02.24 regarding Workfront Delays and Local Villager Interruptions in PKG G & PKG F. further, Clearances for this locations is received on 20.08.2025 at nearby 04:00 PM under police protection, However on dated 23.08.2025 the locations again falls under ROW when landowners creating issues. Cleared on dated 04.10.2025 with the help of police administration. Excavation WIP in 2nd pit. from 10.10.2025.Further from 11.10.2025 Locs is in ROW. and then cleared on 13.10.2025. against Excavation started in all Pit started from 11.10.2025. further Slow progress due to ROCK encountered. No work done due to ROW from 15.10.2025 Machinery idled. 2nos Poklain idle since 15.10.2025. ROW Cleared on 07.11.2025
66 | ROW encountered during excavation . | 61/10 | Foundation |  | 2024-02-19 | 2024-02-29 | 11
67 | ROW encountered during excavation . | 61/4 | Foundation |  | 2024-02-19 | 2024-02-29 | 11
68 | ROW encountered while pit marking. | 62/0 | Foundation |  | 2024-02-19 | 2024-02-29 | 11
69 | Pit marking not done due to cultivated land and SPTL not allowing for further pit marking. | 21/9 | Foundation |  | 2024-02-22 | 2025-05-13 | 447 | D.P.R. Dated 22.02.24
70 | Gang was shifted after completion of location no 23/1 (G) on dated 22.02.24 but due to non-availability of nearby Workfront gang is shifted at 22/5 after one day idling at 22/5. on a progress front he have not worked any productivity till today after 23rd Feb. his time is lapsed on shifting of gang and machinery. |  | Foundation | A.B. Construction | 2024-02-25 | 2024-02-26 | 2 | Email dated 25.02.24 regarding Workfront Delays and Local Villager Interruptions in PKG G & PKG F
71 | Due to interruptions by landowners works are stopped. and gang is completely idle along with machinery. (this team have ability to execute the works in two locations at a time). | 26/6 | Foundation | Mehai Contruction | 2024-02-25 | 2024-02-26 | 2 | Email dated 25.02.24 regarding Workfront Delays and Local Villager Interruptions in PKG G & PKG F
72 | Gang idled due to clear workfront not available after completion of 26/6. | 26/6 | Foundation | Mehai Construction | 2024-03-01 | 2024-03-04 | 4 | Email dated 02/03/24 regarding Survey & Foundation update (Workfront Delay/Interruptions updates in PKG G & PKG F
73 | 22/1:- Completed today. Machinery idled due to Nearby locations not available. Further Gang left the site due to workfront not available. | 22/1 | Foundation | Swarup Enterprises | 2024-03-02 | 2024-03-03 | 2 | Email dated 02/03/24 regarding Survey & Foundation update (Workfront Delay/Interruptions updates in PKG G & PKG F
74 | ROW encountered while pit marking. | 53/6 | Foundation |  | 2024-03-06 | 2024-05-24 | 80
75 | ROW encountered while pit marking. | 53/7 | Foundation |  | 2024-03-06 | 2024-04-04 | 30
76 | ROW encountered while pit marking. | 53/8 | Foundation |  | 2024-03-06 | 2024-04-04 | 30
77 | ROW encountered while pit marking. | 54/0 | Foundation |  | 2024-03-06 | 2024-05-24 | 80
78 | ROW encountered while pit marking. | 54/1 | Foundation |  | 2024-03-06 | 2024-05-24 | 80
79 | ROW encountered while pit marking. | 54/2 | Foundation |  | 2024-03-06 | 2024-05-24 | 80
80 | SPTL representatives not aggreed to start pit marking along with Excavation against clear workfront shared on may'10 at loc no 8/8 (F) | 8/8 | Foundation | Mateshwari Construction/HS Engineering | 2024-05-17 | 2026-02-08 | 633 | Gang idled from 14.11.2024 to 16.11.2024 after 2nd attampt. After idling SPTL allocate other locations.
81 | Works stopped due to ROW by landowners at location No 10/13. | 10/13 | Foundation | Mateshwari Construction | 2024-05-04 | 2024-05-04 | 1
82 | Works stopped due to ROW by landowners at location No 10/12. | 10/12 | Foundation | Mateshwari Construction | 2024-05-14 | 2024-06-16 | 34 | Reference daily progress report.
83 | Works not started due to ROW. | 10/9 | Foundation | Jai Bhawani | 2024-07-04 | 2024-08-07 | 35
84 | Works not started due to ROW. | 10/10 | Foundation | Jai Bhawani | 2024-07-04 | 2025-10-02 | 456
85 | Works not started due to ROW. | 10/21 | Foundation | Jai Bhawani | 2024-07-04 | 2024-07-07 | 4
86 | Works not started due to ROW. | 14A/2 | Foundation | Majisa Construction | 2024-07-04 | 2024-09-07 | 66
87 | Works not started due to ROW. | 15/0 | Foundation | Majisa Construction | 2024-07-04 | 2024-07-07 | 4
88 | No work-done due to Continuous rain at location | 10/3 | Foundation | Jai Bhawani | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
89 | No work-done due to Continuous rain at location | 10/4 | Foundation | Jai Bhawani | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
90 | No work-done due to Continuous rain at location | 11A/7 | Foundation | Punia Construction | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
91 | No work-done due to Continuous rain at location | 16/3 | Foundation | Majisa Construction | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
92 | No work-done due to Continuous rain at location | 18/2 | Foundation | Vibe infra | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
93 | No work-done due to Continuous rain at location | 17/3 | Foundation | J.P. Infra | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
94 | No work-done due to Continuous rain at location | 43/9 | Foundation | N.R. Enterprises | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
95 | Works stopped due to ROW at loc no 16/1. | 16/1 | Foundation | Om Enterprise | 2024-08-24 | 2024-08-25 | 2 | DPR email on regular basis.
96 | Works stopped due to ROW at loc no 43/7 | 43/7 | Foundation | N.R. Enterprises | 2024-08-27 | 2024-08-30 | 4 | DPR email on regular basis.
97 | Full day ROW. 9 nos manpower alongwith JCB (JCB idled since last 6 days). ROW cleared after 2nd half on dated 29.09.2024 | 19/3 | Foundation | Vibe infra | 2024-09-28 | 2024-09-29 | 2 | DPR email on regular basis.
98 | ROW encountered while pit marking. | 65/7 | Foundation |  | 2024-10-10 | 2024-11-11 | 33
99 | ROW encountered while pit marking. | 65/8 | Foundation |  | 2024-10-10 | 2024-11-11 | 33
100 | ROW encountered while pit marking. | 65/10 | Foundation |  | 2024-10-10 | 2025-01-22 | 105
101 | ROW encountered while pit marking. | 68/0 | Foundation |  | 2024-10-10 | 2025-01-13 | 96
102 | ROW encountered while pit marking. | 55/0 | Foundation |  | 2024-10-10 | 2025-01-13 | 96
103 | ROW encountered while pit marking. | 55/1 | Foundation |  | 2024-10-10 | 2025-01-13 | 96
104 | ROW encountered while pit marking. | 55/2 | Foundation |  | 2024-10-10 | 2025-01-13 | 96
105 | ROW encountered while pit marking. | 71/1 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
106 | ROW encountered while pit marking. | 71/2 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
107 | ROW encountered while pit marking. | 71/3 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
108 | ROW encountered while pit marking. | 71/4 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
109 | ROW encountered while pit marking. | 71/5 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
110 | ROW encountered while pit marking. | 71/8 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
111 | ROW encountered while pit marking. | 72/0 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
112 | ROW encountered while pit marking. | 72/1 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
113 | Machinery stucked at location due to ROW, idled (machinery alongwith Gang) till 3 PM on dated 15.10.24. ROW resolved at 03:00 PM. | 22/12 | Foundation | RBM | 2024-10-14 | 2024-10-15 | 2 | DPR email on regular basis.
114 | Full day ROW from 13/3 G & 12/0 F. | 13/3, 12/0 | Foundation | Punia Construction | 2024-10-24 | 2024-10-25 | 2 | DPR email on regular basis.
115 | work could not started due to ROW. | 13/4 | Foundation |  | 2024-11-01 | 2025-11-11 | 376 | DPR email on regular basis. During execution post excavation ROW encountered from 14.07.2025 to till date, Thus earlier cleared date is revised. No work done due to ROW post Excavation, ROW since 14.07.25 to 13.10.2025. Row Cleared on 13.10.2025 by late evening. Further when the gang shifted at location, The location is stiil in ROW. Chandrapal Gang is idle from 14.10.2025 to 29.10.2025. They have arranged all the constrcution materials but due to non clearance, Gang demobilized from site. Cleared on dated 11.11.25 with the support of police admin.
116 | work could not started due to ROW. | 14A/0 | Foundation |  | 2024-11-01 | 2025-06-15 | 227 | DPR email on regular basis.
117 | Excavation can't be started due to ROW. | 22/9 | Foundation |  | 2024-11-17 | 2024-12-01 | 15 | DPR email on regular basis.
118 | Excavation can't be started due to ROW in approach road. | 22/4 | Foundation | J.P. Infra | 2024-11-18 | 2024-11-20 | 3 | DPR email on regular basis.
119 | Excavation can't be started due to ROW. | 6/1 & 6/2 | Foundation | H.s Engineering | 2024-11-18 | 2024-11-20 | 3 | DPR email on regular basis.
120 | Works Stopped due to ROW. | 22/10 | Foundation | RBM | 2024-12-09 | 2025-09-10 | 276 | DPR email on regular basis. ROW issues in approach road is resloved on dated 10.09.2025. Post clearance received for work was received on 21.07.2025 during attempeted locs falls under ROW in approach. and approach was cleared on 10.09.2025.
121 | No work done due to ROW by local persons. Gang Idle till 19.12.2024. Further nex location allaocted 8/9 in PKG G. | 6/2 | Foundation | HS Engineering | 2024-12-11 | 2024-12-19 | 9 | DPR email on regular basis.
122 | Works Stopped due to ROW. | 35/4 | Foundation | Parsuram Sahi | 2024-12-30 | 2024-12-30 | 1 | DPR email on regular basis.
123 | Work can't started due to ROW. | 1/0 | Foundation |  | 2024-12-02 | 2025-02-23 | 84 | Informed to SPTL by mail Communications
124 | Work can't started due to ROW. | 1A/0 | Foundation |  | 2024-12-02 | 2025-01-12 | 42 | Informed to SPTL by mail Communications
125 | Work can't started due to ROW. | 1A/1 | Foundation |  | 2024-12-02 | 2025-01-13 | 43 | Informed to SPTL by mail Communications
126 | Work can't started due to ROW. | 1A/2 | Foundation |  | 2024-12-02 | 2025-01-21 | 51 | Informed to SPTL by mail Communications
127 | Work can't started due to ROW. | 1A/3 | Foundation |  | 2024-12-02 | 2025-01-16 | 46 | Informed to SPTL by mail Communications
128 | Work can't started due to ROW. | 1A/4 | Foundation |  | 2024-12-02 | 2025-01-15 | 45 | Informed to SPTL by mail Communications. This locations is reattmpetd in 28.01.25 after pit marking the locations is found under ROW.
129 | Work can't started due to ROW. | 1A/5 | Foundation |  | 2024-12-02 | 2025-01-22 | 52 | Informed to SPTL by mail Communications
130 | Work can't started due to ROW. | 1A/6 | Foundation |  | 2024-12-02 | 2025-01-21 | 51 | Informed to SPTL by mail Communications
131 | Work can't started due to ROW. | 1A/7 | Foundation |  | 2024-12-02 | 2025-02-26 | 87 | Informed to SPTL by mail Communications
132 | Work can't started due to ROW. | 1A/8 | Foundation |  | 2024-12-02 | 2025-05-02 | 152 | Informed to SPTL by mail Communications
133 | Work can't started due to ROW. | 2/0 | Foundation |  | 2024-12-02 | 2025-01-14 | 44 | Informed to SPTL by mail Communications
134 | Work can't started due to ROW. | 2/1 | Foundation |  | 2024-12-03 | 2025-03-12 | 100 | Informed to SPTL by mail Communications
135 | Work can't started due to ROW. | 2/7 | Foundation |  | 2024-12-03 | 2025-06-05 | 185 | Informed to SPTL by mail Communications, Initially ROW resolved on 30th May 2025, Further during execution, ROW encountered on datedx 04.06.2025
136 | Work can't started due to ROW. | 2/8 | Foundation |  | 2024-12-03 | 2025-02-04 | 64 | Informed to SPTL by mail Communications
137 | Work can't started due to ROW. | 2/9 | Foundation |  | 2024-12-03 | 2025-06-03 | 183 | Informed to SPTL by mail Communications. Work stopped after casting of 2 pit.
138 | Work can't started due to ROW. | 3/0 | Foundation |  | 2024-12-03 | 2025-04-12 | 131 | Informed to SPTL by mail Communications
139 | Work can't started due to ROW. | 4/0 | Foundation |  | 2024-12-18 | 2025-02-18 | 63 | Informed to SPTL by mail Communications
140 | Work can't started due to ROW. | 4/1 | Foundation |  | 2024-12-18 | 2025-04-28 | 132 | Informed to SPTL by mail Communications
141 | Work can't started due to ROW. | 4/2 | Foundation |  | 2024-12-18 | 2025-06-23 | 188 | Informed to SPTL by mail Communications
142 | Work can't started due to ROW. | 4/3 | Foundation |  | 2024-12-18 | 2025-05-13 | 147 | Informed to SPTL by mail Communications
143 | Work can't started due to ROW. | 4/4 | Foundation |  | 2024-12-18 | 2025-06-25 | 190 | Informed to SPTL by mail Communications
144 | Work can't started due to ROW. | 5/0 | Foundation |  | 2024-12-18 | 2025-08-17 | 243 | Informed to SPTL by mail Communications
145 | Work can't started due to ROW. | 6/0 | Foundation |  | 2024-12-18 | 2025-07-26 | 221 | Informed to SPTL by mail Communications
146 | Work can't started due to ROW. | 7/0 | Foundation |  | 2024-12-18 | 2025-09-12 | 269 | Informed to SPTL by mail Communications
147 | Work can't started due to ROW. | 8/0 | Foundation |  | 2024-12-07 | 2025-07-09 | 215 | Informed to SPTL by mail Communications
148 | Work can't started due to ROW. | 8/1 | Foundation |  | 2024-12-07 | 2025-07-06 | 212 | Informed to SPTL by mail Communications
149 | Work can't started due to ROW. | 8/2 | Foundation |  | 2024-12-07 | 2025-06-15 | 191 | Informed to SPTL by mail Communications. Dated 17.05.2025 location is attempted with police protection but all the locations are in ROW.
150 | Work can't started due to ROW. | 8/3 | Foundation |  | 2024-12-07 | 2025-10-09 | 307 | Informed to SPTL by mail Communications. Dated 17.05.2025 location is attempted with police protection but all the locations are in ROW.
151 | Work can't started due to ROW. | 8/4 | Foundation |  | 2024-12-07 | 2025-07-22 | 228 | Informed to SPTL by mail Communications. Dated 17.05.2025 location is attempted with police protection but all the locations are in ROW.
152 | Work can't started due to ROW. | 8/5 | Foundation |  | 2024-12-07 | 2025-06-19 | 195 | Informed to SPTL by mail Communications. Dated 17.05.2025 location is attempted with police protection but all the locations are in ROW.
153 | Work can't started due to ROW. | 8/6 | Foundation |  | 2024-12-07 | 2026-02-15 | 436 | Informed to SPTL by mail Communications. Dated 17.05.2025 location is attempted with police protection but all the locations are in ROW.
154 | Work can't started due to ROW. | 8/11 | Foundation |  | 2024-12-07 | 2025-05-12 | 157 | Informed to SPTL by mail Communications
155 | Work can't started due to ROW. | 8/12 | Foundation |  | 2024-12-07 | 2025-05-12 | 157 | Informed to SPTL by mail Communications
156 | Work can't started due to ROW. | 9/0 | Foundation |  | 2024-12-07 | 2025-07-06 | 212 | Informed to SPTL by mail Communications
157 | Work can't started due to ROW. | 10/0 | Foundation |  | 2024-12-07 | 2025-05-14 | 159 | Informed to SPTL by mail Communications
158 | Work can't started due to ROW. | 10/1 | Foundation |  | 2024-12-07 | 2025-05-16 | 161 | Informed to SPTL by mail Communications
159 | Work can't started due to ROW. | 10/2 | Foundation |  | 2024-12-07 | 2026-01-31 | 421 | Informed to SPTL by mail Communications.
160 | Work can't started due to ROW. | 10/7 | Foundation |  | 2024-12-07 | 2025-07-13 | 219 | Informed to SPTL by mail Communications. '10/7 (No work done due to ROW, ROW since 20.07.25)
161 | Work can't started due to ROW. | 10/15 | Foundation |  | 2024-12-07 | 2025-09-14 | 282 | Informed to SPTL by mail Communications
162 | Work can't started due to ROW. | 10/16 | Foundation |  | 2024-12-07 | 2025-09-06 | 274 | Informed to SPTL by mail Communications
163 | Work can't started due to ROW. | 10/22 | Foundation |  | 2024-12-07 | 2025-12-06 | 365 | Informed to SPTL by mail Communications. During work progress got interupputed on dated 05.12.2025. informed via DPR and respective whatsapp group.
164 | Work can't started due to ROW. | 10/23 | Foundation |  | 2024-12-07 | 2025-09-29 | 297 | Informed to SPTL by mail Communications
165 | Work can't started due to ROW. | 11/0 | Foundation |  | 2024-12-07 | 2025-09-06 | 274 | Informed to SPTL by mail Communications
166 | Work can't started due to ROW. | 11/1 | Foundation |  | 2024-12-07 | 2025-08-02 | 239 | Informed to SPTL by mail Communications
167 | Work can't started due to ROW. | 11/2 | Foundation |  | 2024-12-07 | 2025-08-16 | 253 | Informed to SPTL by mail Communications
168 | Work can't started due to ROW. | 11/3 | Foundation |  | 2024-12-07 | 2025-09-15 | 283 | Informed to SPTL by mail Communications
169 | Work can't started due to ROW. | 11/4 | Foundation |  | 2024-12-07 | 2025-06-06 | 182 | Informed to SPTL by mail Communications
170 | Work can't started due to ROW. | 19/4 | Foundation |  | 2024-12-07 | 2025-10-04 | 302 | Informed to SPTL by mail Communications. Cleared on dated 04.10.2025 with the help of police administration.
171 | Work can't started due to ROW. | 19/5 | Foundation |  | 2024-12-07 | 2025-06-01 | 177 | Informed to SPTL by mail Communications
172 | Work can't started due to ROW. | 20/0 | Foundation |  | 2024-12-17 | 2025-07-04 | 200 | Informed to SPTL by mail Communications
173 | Work can't started due to ROW. | 20/1 | Foundation |  | 2024-12-17 | 2025-09-04 | 262 | Informed to SPTL by mail Communications, clearances for this locations is received on 20.08.2025 at nearby 04:00 PM under police protection, However on dated 23.08.2025 the locations again falls under ROW when landowners creating issues. Location resolved on 04.09.2025.
174 | Work can't started due to ROW. | 20/2 | Foundation |  | 2024-12-17 | 2025-07-20 | 216 | Informed to SPTL by mail Communications
175 | Work can't started due to ROW. | 20/3 | Foundation |  | 2024-12-17 | 2025-07-23 | 219 | Informed to SPTL by mail Communications
176 | Work can't started due to ROW. | 21/0 | Foundation |  | 2024-12-17 | 2025-07-21 | 217 | Informed to SPTL by mail Communications
177 | Work can't started due to ROW. | 21/1 | Foundation |  | 2024-12-17 | 2026-03-13 | 452 | Informed to SPTL by mail Communications. All the activity of 2 leg is completed on 01.11.2025, Further last pit not done due to ROW. Last pit marking attended dated 13.03.2026 with Police administration support.
178 | Work can't started due to ROW. | 21/2 | Foundation |  | 2024-12-17 | 2025-07-25 | 221 | Informed to SPTL by mail Communications, ROW in approach road when location attempted at 22.06.2025. ROW in approach Road, ROW since 28.06.2025. Final ROW cleared on 25.07.2025.
179 | Work can't started due to ROW. | 21/3 | Foundation |  | 2024-12-17 | 2025-06-21 | 187 | Informed to SPTL by mail Communications. Reattempted on 23.05.2025 but the locations still persist in ROW.
180 | Work can't started due to ROW. | 21/4 | Foundation |  | 2024-12-17 | 2025-06-10 | 176 | Informed to SPTL by mail Communications
181 | Work can't started due to ROW. | 21/5 | Foundation |  | 2024-12-17 | 2025-05-29 | 164 | Informed to SPTL by mail Communications, tried on 07.05.25 also after pit marking location is in ROW then Excavation started on loc no 21/7.
182 | Work can't started due to ROW. | 21/6 | Foundation |  | 2024-12-17 | 2025-10-26 | 314 | Informed to SPTL by mail Communications. Cleared on dated 04.10.2025 with the help of police administration. Excavation in all Pit started from 11.10.2025. further Slow progress due to ROCK encountered. No work done due to ROW from 15.10.2025 Machinery idled. 2nos Poklain idle since 15.10.2025. Finally cleared on 26.10.2025.
183 | Work can't started due to ROW. | 21/7 | Foundation |  | 2024-12-17 | 2025-05-07 | 142 | Informed to SPTL by mail Communications
184 | Work can't started due to ROW. | 21/8 | Foundation |  | 2024-12-17 | 2025-10-03 | 291 | Informed to SPTL by mail Communications. clearances for this locations is received on 20.08.2025 at nearby 04:00 PM under police protection, However on dated 23.08.2025 the locations again falls under ROW when landowners creating issues. Cleared in presence of police administrator on dated 03.10.2025.
185 | Work can't started due to ROW. | 23/0 | Foundation |  | 2024-12-17 | 2025-07-30 | 226 | Informed to SPTL by mail Communications
186 | Work can't started due to ROW. | 24/0 | Foundation |  | 2024-12-13 | 2025-07-20 | 220 | Informed to SPTL by mail Communications
187 | Work can't started due to ROW. | 26/0 | Foundation |  | 2024-12-13 | 2025-07-11 | 211 | Informed to SPTL by mail Communications
188 | Work can't started due to ROW. | 26/1 | Foundation |  | 2024-12-13 | 2025-08-01 | 232 | Informed to SPTL by mail Communications
189 | Work can't started due to ROW. | 27/0 | Foundation |  | 2024-12-13 | 2025-05-06 | 145 | Informed to SPTL by mail Communications
190 | Work can't started due to ROW. | 27/1 | Foundation |  | 2024-12-13 | 2025-05-02 | 141 | Informed to SPTL by mail Communications
191 | Work can't started due to ROW. | 27/2 | Foundation |  | 2024-12-13 | 2025-04-16 | 125 | Informed to SPTL by mail Communications
192 | Work can't started due to ROW. | 27/3 | Foundation |  | 2024-12-13 | 2025-04-11 | 120 | Informed to SPTL by mail Communications
193 | Work can't started due to ROW. | 27/4 | Foundation |  | 2024-12-13 | 2025-05-12 | 151 | Informed to SPTL by mail Communications
194 | Work can't started due to ROW. | 37/0 | Foundation |  | 2024-12-13 | 2025-06-23 | 193 | Informed to SPTL by mail Communications
195 | Work can't started due to ROW. | 37/1 | Foundation |  | 2024-12-13 | 2025-06-28 | 198 | Informed to SPTL by mail Communications
196 | Work can't started due to ROW. | 37/3 | Foundation |  | 2024-12-13 | 2025-04-18 | 127 | Informed to SPTL by mail Communications
197 | Work can't started due to ROW. | 38/0 | Foundation |  | 2024-12-13 | 2025-04-15 | 124 | Informed to SPTL by mail Communications
198 | Work can't started due to ROW. | 38/1 | Foundation |  | 2024-12-13 | 2025-04-21 | 130 | Informed to SPTL by mail Communications
199 | Work can't started due to ROW. | 38/2 | Foundation |  | 2024-12-15 | 2025-04-16 | 123 | Informed to SPTL by mail Communications
200 | Work can't started due to ROW. | 38/3 | Foundation |  | 2024-12-15 | 2025-05-12 | 149 | Informed to SPTL by mail Communications
201 | Work can't started due to ROW. | 38/4 | Foundation |  | 2024-12-15 | 2025-04-05 | 112 | Informed to SPTL by mail Communications
202 | Work can't started due to ROW. | 39/0 | Foundation |  | 2024-12-15 | 2025-04-11 | 118 | Informed to SPTL by mail Communications
203 | Work can't started due to ROW. | 39/1 | Foundation |  | 2024-12-15 | 2025-04-28 | 135 | Informed to SPTL by mail Communications. Reattempted on 25.06.2025.
204 | Work can't started due to ROW. | 40/0 | Foundation |  | 2024-12-15 | 2025-04-28 | 135 | Informed to SPTL by mail Communications. Work started on 26.04.2025 further during excavation works are stopped the land owners.
205 | Work can't started due to ROW. | 40/1 | Foundation |  | 2024-12-15 | 2025-05-02 | 139 | Informed to SPTL by mail Communications
206 | Work can't started due to ROW. | 40/3 | Foundation |  | 2024-12-15 | 2025-05-18 | 155 | Informed to SPTL by mail Communications
207 | Work can't started due to ROW. | 41/0 | Foundation |  | 2024-12-15 | 2025-04-20 | 127 | Informed to SPTL by mail Communications
208 | Work can't started due to ROW. | 41/1 | Foundation |  | 2024-12-15 | 2025-05-21 | 158 | Informed to SPTL by mail Communications
209 | Work can't started due to ROW. | 42/4 | Foundation |  | 2024-12-15 | 2025-05-16 | 153 | Informed to SPTL by mail Communications
210 | Work can't started due to ROW. | 43/10 | Foundation |  | 2024-12-15 | 2025-02-16 | 64 | Informed to SPTL by mail Communications
Erection
S.No | Nature of Hindrance | Loc/Sec. | Affected Activity | Affected Gang Name | Date of occurrence | Date of removal | Period of hindrance | Remarks
0 | Gang idle due to ROW at 10/19 | 10/19 | Erection | Yogender Mahto | 2024-09-10 | 2024-09-12 | 3 | DPR email on regular basis.
0 | Rafikul Islam:- 11A/0 WIP. No work due to ROW. | 11A/0 | Erection | Rafikul Islam | 2024-10-24 | 2024-10-25 | 2 | DPR email on regular basis.
0 | Jailal ageria:- 16/0 WIP. No work due to ROW. | 16/0 | Erection | Jailal Ageria | 2024-10-24 | 2024-10-25 | 2 | DPR email on regular basis.
0 | Nirmal Mahto:- 16/2 WIP. No work due to ROW. | 16/2 | Erection | Nirmal Mahto | 2024-10-24 | 2024-10-25 | 2 | DPR email on regular basis.
0 | work could not started due to ROW. | 14A/2 | Erection |  | 2024-11-01 | 2025-12-31 | 426 | DPR email on regular basis.
0 | work could not started due to ROW. | 15/0 | Erection |  | 2024-11-01 | 2026-03-24 | 509 | DPR email on regular basis.
0 | work could not started due to ROW. | 17/4 | Erection |  | 2024-11-02 | 2025-04-12 | 162 | DPR email on regular basis.
0 | work could not started due to ROW. | 17/5 | Erection | Bina Devi | 2024-11-02 | 2024-11-23 | 22 | DPR email on regular basis. Gang reattempted on dated 22.11.24 after allocating by SPTL, but ROW is still not resolved. And gang is being idle.
0 | work could not started due to ROW. | 18/0 | Erection |  | 2024-11-02 | 2025-08-16 | 288 | DPR email on regular basis.
0 | 13/1 WIP. No work due to ROW. | 13/1 | Erection | Jailal Ageria | 2024-11-26 | 2025-12-12 | 382 | DPR email on regular basis.
0 | Works Stopped due to ROW. | 13/0 | Erection | Jailal Agerai | 2024-12-30 | 2026-02-23 | 421 | DPR email on regular basis. Work stopped after completion of 1st Section. Works started on 25.02.2026 when attended Locs in ROW after 1st half.
0 | Works Stopped due to ROW. | 11A/5 | Erection | Deglal Mahto | 2024-12-30 | 2024-12-31 | 2 | DPR email on regular basis.
0 | Work can't started due to ROW. | 10/5 | Erection |  | 2025-01-01 | 2025-12-23 | 357 | Informed to SPTL by mail Communications
0 | Work can't started due to ROW. | 11A/4 | Erection |  | 2025-01-01 | 2026-03-13 | 437 | Informed to SPTL by mail Communications, Gang idle after shifting of tower parts at many days post that locations was cleared.
0 | Work can't started due to ROW. | 11A/8 | Erection |  | 2025-01-01 | 2025-12-05 | 339 | Informed to SPTL by mail Communications
0 | Work can't started due to ROW. | 12/0 | Erection |  | 2025-01-01 | 2025-07-20 | 201 | Informed to SPTL by mail Communications
0 | Work can't started due to ROW. | 13/3 | Erection |  | 2025-01-01 | 2025-12-16 | 350 | Informed to SPTL by mail Communications
0 | Work can't started due to ROW. | 14/0 | Erection |  | 2025-01-01 | 2025-12-16 | 350 | Informed to SPTL by mail Communications
0 | Work can't started due to ROW. | 18/3 | Erection |  | 2025-01-01 | 2025-07-14 | 195 | Informed to SPTL by mail Communications
0 | Work can't started due to ROW. | 19/1 | Erection |  | 2025-01-01 | 2025-12-28 | 362 | Informed to SPTL by mail Communications
0 | Work can't started due to ROW. | 19/2 | Erection |  | 2025-01-01 | 2025-10-20 | 293 | Informed to SPTL by mail Communications
0 | Work can't started due to ROW. | 1A/5 | Erection | Kewat | 2025-07-24 | 2025-07-25 | 2 | No work done due to ROW. Earlier work is going on Cage. Cleared on 25.07.2025 (Today).
0 | Work can't started due to ROW. | 11/4 | Erection | Anjali Enterprises | 2025-07-25 | 2025-10-20 | 88 | Informed to SPTL by mail Communications, additional mail having subject Frequent obstruction (ROW) in Both the Package (G & F) dated 25.07.2025 sent by partho pal. Gang idle 21 manpower incl truck and T&P.
0 | Work can't started due to ROW. | 27/6 | Erection | Pusplata_Rajaram | 2025-08-06 | 2025-12-02 | 119 | Please refer daily progress report. Email dated 07.08.2025 having subject delay in unloading of tower parts
0 | Work can't started due to ROW. | 19/4 | Erection |  | 2025-11-01 | 2025-12-18 | 48 | Location cleared on 18.12.25 after idling of 5 hours of truck.
0 | Work can't started due to ROW. | 8/7 | Erection |  | 2025-08-12 | 2026-02-24 | 197 | Please refer daily progress report.
0 | Work can't started due to ROW. | 8/11 | Erection |  | 2025-08-12 | 2026-02-18 | 191 | Please refer daily progress report.
0 | Work can't started due to ROW. | 27/10 | Erection | Pusplata_Ramchandra | 2025-08-29 | 2025-12-26 | 120 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/11 | Erection |  | 2025-08-30 | 2025-12-26 | 119 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/12 | Erection |  | 2025-08-30 | 2026-04-23 | 237 | Please refer daily progress report. Cleared on 23.04.2026.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/13 | Erection |  | 2025-08-30 | 2026-01-02 | 126 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 23/0 | Erection |  | 2025-08-30 | 2026-04-21 | 235 | Please refer daily progress report. Cleared on 23.04.2026 based on the clearance over whatsapp.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 25/0 | Erection |  | 2025-08-30 | 2026-01-21 | 145 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 25/1 | Erection |  | 2025-08-30 | 2026-01-12 | 136 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 25/2 | Erection |  | 2025-08-30 | 2026-01-03 | 127 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 26/1 | Erection |  | 2025-08-30 | 2025-09-06 | 8 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 26/4 | Erection |  | 2025-08-30 | 2026-01-29 | 153 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 26/5 | Erection |  | 2025-08-30 | 2025-11-20 | 83 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 26/6 | Erection |  | 2025-08-30 | 2026-01-09 | 133 | Please refer daily progress report. Police support taken on 14.11.25 but the locations remains on under hindrance. After that we again attempted on 03.12 and again ROW encountered on 06.12.25. again attempted today in presence of police administration on dated 17.12.25 and the locations is still unreolved. Cleared on 09.01.2026 with thehelp of police admin.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 26/7 | Erection |  | 2025-08-30 | 2025-12-06 | 99 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 27/5 | Erection |  | 2025-08-30 | 2025-11-06 | 69 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 27/7 | Erection |  | 2025-08-30 | 2025-12-11 | 104 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 27/8 | Erection |  | 2025-08-30 | 2025-11-18 | 81 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 27/9 | Erection |  | 2025-08-30 | 2025-12-14 | 107 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 27/12 | Erection |  | 2025-08-30 | 2025-11-26 | 89 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 28/1 | Erection |  | 2025-08-30 | 2025-11-10 | 73 | Please refer daily progress report. Cleared on 10.11.25.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 28/3 | Erection |  | 2025-08-30 | 2025-12-20 | 113 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 28/4 | Erection |  | 2025-08-30 | 2025-12-20 | 113 | Please refer daily progress report. Clearance received via MS teams Call jointly with BCG team.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 28/6 | Erection |  | 2025-08-30 | 2025-12-28 | 121 | Please refer daily progress report. Allocated this location for works on 12.09.2025. while attending location in in ROW.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 28/7 | Erection |  | 2025-08-30 | 2025-12-10 | 103 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 28/8 | Erection |  | 2025-08-30 | 2025-12-20 | 113 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 29/2 | Erection |  | 2025-08-30 | 2025-11-09 | 72 | Please refer daily progress report. Cleared on 09.11.25 post idling of truck nearby 4 hours.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 29/3 | Erection |  | 2025-08-30 | 2025-09-15 | 17 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 29/4 | Erection |  | 2025-08-30 | 2025-10-12 | 44 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 30/0 | Erection |  | 2025-08-30 | 2025-11-13 | 76 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 30/2 | Erection |  | 2025-08-30 | 2025-09-30 | 32 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 30/4 | Erection |  | 2025-08-30 | 2025-12-23 | 116 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 31/0 | Erection |  | 2025-08-30 | 2025-12-16 | 109 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 32/0 | Erection |  | 2025-08-30 | 2025-11-06 | 69 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 32/2 | Erection |  | 2025-08-30 | 2025-11-06 | 69 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 32/3 | Erection |  | 2025-08-30 | 2025-10-30 | 62 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 32/4 | Erection |  | 2025-08-30 | 2024-11-06 | -296 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 33/0 | Erection |  | 2025-08-30 | 2025-10-22 | 54 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 9/0 | Erection |  | 2025-08-30 | 2025-12-01 | 94 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 10/0 | Erection |  | 2025-08-30 | 2026-03-01 | 184 | Please refer daily progress report.
0 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 20/0 | Erection |  | 2025-08-30 | 2025-09-19 | 21 | Please refer daily progress report.
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 20/1 | Erection |  | 2025-09-13 | 2026-05-17 | 247 | Please refer daily progress report. ROW after material shifting but due to this material unloaded at 21/2. Further Resonia email dated 01.05.2026 having subject 765kV Fatehgrah III to Beawar_BTL_KEC Section (Daily working plan for Erection & Stringing). Location cleared with the support of police administration.
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 21/2 | Erection |  | 2025-09-13 | 2026-03-28 | 197 | Please refer daily progress report. Cleared on 28.03.2026.
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 21/5 | Erection |  | 2025-09-13 | 2025-09-19 | 7 | Please refer daily progress report.
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 21/7 | Erection |  | 2025-09-13 | 2026-04-23 | 223 | Please refer daily progress report. Cleared on 16.04.2026. When material unloading on 17.04.2026. Location is still under ROW.
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 21/9 | Erection |  | 2025-09-13 | 2026-03-19 | 188 | Please refer daily progress report. ROW resolved on 28.01.2025 with police protection. Prior to that there is 2 more incident in which we have shifted the materials at site and due to ROW material return back to store. Again clearance received on 19.03.2026.
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 21/10 | Erection |  | 2025-09-13 | 2026-04-10 | 210 | Please refer daily progress report. Material shifted on 29.09.25 but due to ROW locations falls in ROW. Then the gang moved in PKG G. Police protection availed on 17.12. but not resolved. Cleared on 10.04.2026
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/1 | Erection |  | 2025-09-13 | 2026-04-10 | 210 | Please refer daily progress report. Cleared on 10.04.2026
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/2 | Erection |  | 2025-09-13 | 2025-12-21 | 100 | Please refer daily progress report.
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/3 | Erection |  | 2025-09-13 | 2026-01-02 | 112 | Please refer daily progress report.
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/4 | Erection |  | 2025-09-13 | 2026-05-11 | 241 | Please refer daily progress report. Resonia email dated 11.05.2026 having subject 765kV Fatehgrah III to Beawar_BTL_KEC Section (Daily working plan for Erection & Stringing)
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/5 | Erection |  | 2025-09-13 | 2025-12-25 | 104 | Please refer daily progress report.
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/6 | Erection |  | 2025-09-13 | 2025-12-21 | 100 | Please refer daily progress report.
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/7 | Erection |  | 2025-09-13 | 2025-12-15 | 94 | Please refer daily progress report.
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/8 | Erection |  | 2025-09-13 | 2026-02-16 | 157 | Please refer daily progress report.
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/9 | Erection |  | 2025-09-13 | 2026-03-19 | 188 | Please refer daily progress report.
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 38/3 | Erection | Jwala Singh | 2025-10-13 | 2025-11-06 | 25 | Please refer daily progress report. X-arm WIP. No work due to ROW as per instruction by resonia Ltd. Further the gang shifted at next location 39/0 F.
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 19/3 | Erection |  | 2025-12-01 | 2025-12-23 | 23 | Please refer daily progress report.
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 21/6 | Erection |  | 2025-12-01 | 2026-05-07 | 158 | Please refer daily progress report. Resonia email dated 01.05.2026 having subject 765kV Fatehgrah III to Beawar_BTL_KEC Section (Daily working plan for Erection & Stringing), Cleared on 7.5.26 at 04:30 P.M with the admin support.
1 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 21/8 | Erection |  | 2025-12-01 | 2026-08-31 | 274 | Please refer daily progress report. Resonia email dated 01.05.2026 having subject 765kV Fatehgrah III to Beawar_BTL_KEC Section (Daily working plan for Erection & Stringing)
2 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/0 | Erection |  | 2025-12-01 | 2026-07-13 | 225 | Please refer daily progress report. Resonia email dated 01.05.2026 having subject 765kV Fatehgrah III to Beawar_BTL_KEC Section (Daily working plan for Erection & Stringing). Location cleared with the support of police administration. Tower parts return at store post shifting at site. The locations still under ROW. after mutliple holts and manhandling at locations while working the locations completed on 13th July 2026.
2 | Location can't be allocated for further works, and gang is idled at nearby locations, Thus considered in ROW. | 22/10 | Erection |  | 2025-12-01 | 2026-03-08 |  | Please refer daily progress report.
Others
S.No | Nature of Hindrance | Loc/Sec. | Affected Activity | Affected Gang Name | Date of occurrence | Date of removal | Period of hindrance | Remarks
1 | Delay in finalization of locations for Soil investigation |  | Others |  | 2023-12-06 | 2024-02-24 | 81 | 24 Locations SPT Confirmed on 24th Feb 2024.
2 | Delay in approval of L2 Schedule. |  | Others |  | 2023-12-06 | 2024-01-23 | 49 | Approval reference email dated 23.01.24.
3 | New tower optimization and shifting was proposed by SPTL on dated 18th March 2024. Final confirmation for omit of optimization is received on 15.05.2024. |  | Others |  | 2024-03-18 | 2024-05-15 | 59 | Email dated 15/5/24.
Stringing
S.No | Nature of Hindrance | Loc/Sec. | Affected Activity | Affected Gang Name | Date of occurrence | Date of removal | Period of hindrance | Remarks
0 | Insulator hoisting not done due to ROW at location no 72/1. | 72/1 | Stringing | JPJ construction | 2025-05-24 | 2025-05-26 | 3
0 | This Months Idling- JPJ Construction was idled 43 manpower with T&P's from 27.05.2025 to 31.05.2025 due to 33 KV shut down not availed on time in AP73-74 (3.788 Kms). | AP72-73 | Stringing | JPJ construction | 2025-05-27 | 2025-06-17 | 22 | Infomed to resonia via daily progress report.
0 | Delay occurred due to the removal of the insulator from the previously completed hoisting, and the subsequent re-hoisting of the platina roller. As a result, a total of 6 days were lost. This was done based on clear instruction of resonia. | AP71-AP72 | Stringing | MC Construction | 2025-10-25 | 2025-10-31 | 7 | Infomed to resonia via email dated 01.11.2025 having subject Plan for the month of Nov-2025 [PKG F]
0 | ROW at location no 71/0. due to this drum was unloded at alternate places. | AP70-71 | Stringing | MC Construction | 2025-11-12 | 2025-11-13 | 2 | informed via daily progress report. Cleared on dated 13.11.2025.
0 | Progress hampered due to ROW in 1st half in AP70-71. | AP70-71 | Stringing | MC Construction | 2025-12-03 | 2025-12-09 | 7 | informed via daily progress report. Cleared on dated 13.11.2025. Email dated 08.12.2025
0 | 33 KV Shutdown not received for Final Sag in AP2-3 | AP2-3 | Stringing | Devi Power | 2025-11-18 | 2026-01-12 | 56 | Informed via daily progress report. and email Dated 23.12.25, 24.12.25 & 27.12.25 further email having subject ROW & Order Issues Impacting Progress – Immediate Intervention Required [PKG G & F]
0 | Insulator hoisting not done due to ROW at location no 72/1. | 72/1 | Stringing | Deepak | 2025-01-10 | 2025-11-03 | 298 | informed via daily progress report. and email having subject ROW & Order Issues Impacting Progress – Immediate Intervention Required [PKG G & F] dated 10/1/26.
0 | Clipping not done due to ROW. | 70/8 & 70/9 | Stringing | MC Construction | 2026-01-01 | 2026-03-31 | 90 | Informed to you via daily progress report.
0 | Final Sag not done due to ROW in backstay at 10/12 | 10/12-10/20 | Stringing | Deepak | 2026-01-23 | 2026-02-04 | 13 | Informed to you via daily progress report.
0 | Paying out not done due to unavailability of Platina in AP55-56 | 55/0-56/0 | Stringing | MC Construction | 2026-02-01 | 2026-03-26 | 54 | Informed to you via daily progress report. From 19.02.25 based on resonia instructions, No works will be done and gangs shifted in Package G for rectification. No works will be done until readiness of PKG G.
8 | Stringing not started due to ROW. | AP43-44 | Stringing |  | 2026-02-23 | 2026-04-06 | 43 | Informed to you via daily progress report. ROW for insulator hoisting 43/1, 43/2, 43/3 ,43/9 & 43/11. Due to non clearance of Section Gang idle.
9 | Stringing not started due to ROW. | AP44-44/6 | Stringing |  | 2026-02-23 | 2026-03-24 | 30 | Informed to you via daily progress report.
10 | F/Sag not started due to ROW. | AP44/6-44/8 | Stringing | Krishna-1 | 2026-02-23 | 2026-03-20 | 26 | Informed to you via daily progress report.
11 | Paying out not started due to ROW in AP10/0-10/12 | AP10-10/12 | Stringing | Deepak | 2026-03-10 | 2026-03-12 | 3 | Informed to you via daily progress report.
12 | 33 KV Shutdown not received for Final Sag in AP2-3 | AP6-7 | Stringing | Deepak | 2026-03-21 | 2026-04-14 | 25 | Shutdown received on 15.04.2026 from 11:00 PM to EOD. This section was completed in 2 days shutdown only. F/Sag not started due to ROW at 5/0 for back stay as AP5-6 Hotline X-ings is going on. And AP5 is in ROW.
13 | R/Sag not started due to ROW. | AP13-14 | Stringing | Nasir | 2026-03-28 | 2026-04-02 | 6 | Informed to you via daily progress report. Works started on 30th March after 4 phase Paying out works stopped due to ROW in 13/2 (Gang idled).
14 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 4/0-5/0 | Stringing |  | 2025-11-18 | 2025-07-18 | -122 | 33 kV adani shut down required. Refer Resonia email dated 04.05.2026 having subject 765kV Fatehgrah III to Beawar_BTL_KEC Section (Daily working plan for Erection & Stringing), Shutdown received on 18.07.2026
15 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 5/0-6/0 | Stringing |  | 2025-12-08 | 2026-04-22 | 136 | Insulator hoisting started on 2/3/26. Hotline shutdown granted on 13.04.2026 onwards. Due to ROW at 5/0, Location no 5/0 clear on 22.04.2026 for further work.
16 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 11/0-11A/0 | Stringing |  | 2026-01-01 | 2026-06-17 | 168 | Section under ROW as confirmed by resonia via email dated 04.05.26 having subject 765kV Fatehgrah III to Beawar_BTL_KEC Section (Daily working plan for Erection & Stringing)
17 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 11A/0-12/0 | Stringing |  | 2026-03-17 | 2026-05-18 | 63 | Insulator hoisting started on 2/3/26 in a haphazard manner. Not started on dated 10.04.2026 due to Infravision Not started for platina paying out. Infra team started platina paying out on dated 11.04.2026. Due to ROW @ 11A/0 no works is started on dated 13.04.2025. Section under ROW as confirmed by resonia via email dated 04.05.26 having subject 765kV Fatehgrah III to Beawar_BTL_KEC Section (Daily working plan for Erection & Stringing). Cleared on 18.05.2026. Confirmed via mail dated 17.08.2026.
18 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 15/0-16/0 | Stringing |  | 2026-03-30 | 2026-07-10 | 103 | Insulator hoisting done in AP15 on 21/4/26 however the section is still under ROW till Finish date mentioned. Section under ROW as confirmed by resonia via email dated 04.05.26 having subject 765kV Fatehgrah III to Beawar_BTL_KEC Section (Daily working plan for Erection & Stringing), 16/0 is still under row when attended on 09.05.26
19 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 16/0-17/0 | Stringing |  | 2024-11-15 | 2026-07-10 | 603 | Section under ROW at 16/0, 16/5 as confirmed by resonia via email dated 05.05.26 having subject 765kV Fatehgrah III to Beawar_BTL_KEC Section (Daily working plan for Erection & Stringing), Insulator hoisting completed Paying out not stared due to ROW.
20 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 17/0-18/0 | Stringing |  | 2025-08-20 |  | Awaited | Section under ROW as confirmed by resonia via email dated 05.05.26 having subject 765kV Fatehgrah III to Beawar_BTL_KEC Section (Daily working plan for Erection & Stringing)
21 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 18/0-19/0 | Stringing |  | 2025-01-26 | 2026-07-26 | 547 | Section under ROW as confirmed by resonia via email dated 05.05.26 having subject 765kV Fatehgrah III to Beawar_BTL_KEC Section (Daily working plan for Erection & Stringing), on dated 26th July the section was allocated to tata projects Limited.
22 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 19/0-20/0 | Stringing |  | 2026-01-08 | 2026-07-26 | 200 | Section under ROW as confirmed by resonia via email dated 05.05.26 having subject 765kV Fatehgrah III to Beawar_BTL_KEC Section (Daily working plan for Erection & Stringing), on dated 26th July the section was allocated to tata projects Limited.
23 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 24/0-25/0 | Stringing |  | 2026-02-01 | 2026-06-22 | 142
24 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 25/0-26/0 | Stringing |  | 2026-02-01 |  | Awaited
25 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 26/0-27/0 | Stringing |  | 2026-02-08 |  | Awaited
26 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 44/8-44/10 | Stringing |  | 2025-10-01 | 2026-02-14 | 137
27 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 52/0-53/0 | Stringing |  | 2025-10-01 | 2026-04-30 | 212
28 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 53/0-54/0 | Stringing |  | 2025-03-29 | 2026-04-15 | 383 | Insulator hoisting started on 7/4/26 in a haphazard way. Not started insulator hoisting on dated 10.04.2026 due to Infravision Not started for platina paying out. ROW in 53/8 revisited on 11.04.2028 for Insulator hoisting. ROW @ 53/8 is cleared on 14.04.2026 in which Final Checking is in WIP. Platina paying out started on 14.04.2025 however upong completion of 4 phase from AP53/0-53/4, Drone got breakdown. 53/8 Hoisting done on 15.04.2026.
29 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 54/0-55/0 | Stringing |  | 2025-10-01 | 2026-04-03 | 185
30 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 22/8-23/0 | Stringing |  | 2026-05-14 | 2026-06-29 | 47
31 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 23/0-24/0 | Stringing |  | 2026-05-14 | 2026-06-07 | 25
32 | Section Ready for Stringing but the same is not yet started due to section not allocated for further works. | 20/0-21/0 | Stringing |  | 2026-05-25 |  | Awaited
Formulas:
Period of hindrance = +IF([Date of removal (Last attempt)]="","Awaited",DAYS([Date of removal (Last attempt)],[Date of 1st attempt])+1)

## Page Chart
Progress Summary'!A1 | [12 empty] | Village wise dashboard
Location Wise Status | [7 empty] | Post Stringing work |  |  |  |  | Foundation | [5 empty] | Erection | [6 empty] | Stringing (Paying out)
Sr. No. | Loc No. | TOT | Village Name | Span | FDN | ERE | Str (P/Out) | Hoisting | Clipp. | Spac. | Jump. | Remarks (if any) | Village wise breakups | Total | Comp. | WIP | Clear | ROW | Total | Comp. | WIP | Clear | ROW | Yet to attempt | Balance | Scope | C | WIP | Clear | ROW | P/X | Dep. | TPL
1 | 1/0 | DD60+0 | Mandai | 122 | DRY | E | C | C |  | C | C |  | Village (49 No's) | 485 | 485 | 0 | 0 | 0 | 485 | 485 | 0 | 0 | 0 | 0 | 0 | 191.3926 | 146.0751 | 12.3199 | 0 | 9.7201 | 0 | 0 | 23.2775
2 | 1A/0 | DD60+0 | Mandai | 90 | DRY | E | C | C |  | C | C |  | Mandai | 16 | 16 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 5.6287 | 5.6287 | 0 | 0 | 0 | 0 | 0 | 0
3 | 1A/1 | DA+6 | Mandai | 277.7 | DFR | E | C | C | C | C |  |  | Harwa | 22 | 22 | 0 | 0 | 0 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 7.9501 | 7.9501 | 0 | 0 | 0 | 0 | 0 | 0
4 | 1A/2 | DA+0 | Mandai | 386 | DRY | E | C | C | C | C |  |  | Chak Goonga | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 3.1303 | 3.1303 | 0 | 0 | 0 | 0 | 0 | 0
5 | 1A/3 | DA+0 | Mandai | 443.6 | DRY | E | C | C | C | C |  |  | Goonga | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 2.0524 | 2.0524 | 0 | 0 | 0 | 0 | 0 | 0
6 | 1A/4 | DA+3 | Mandai | 333.4 | DFR | E | C | C | C | C |  |  | Pusar | 14 | 14 | 0 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 5.7155 | 5.7155 | 0 | 0 | 0 | 0 | 0 | 0
7 | 1A/5 | DA+0 | Mandai | 431.9 | DRY | E | C | C | C | C |  |  | Bisoo Khurd | 13 | 13 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 5.1285 | 5.1285 | 0 | 0 | 0 | 0 | 0 | 0
8 | 1A/6 | DA+0 | Mandai | 348.7 | Sandy | E | C | C | C | C |  |  | Bhiyad | 38 | 38 | 0 | 0 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 15.0319 | 10.3109 | 2.451 | 0 | 0 | 0 | 0 | 2.27
9 | 1A/7 | DA+3 | Mandai | 395.7 | Sandy | E | C | C | C | C |  |  | Kashmir | 29 | 29 | 0 | 0 | 0 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 11.512 | 0.3892 | 3.1771 | 0 | 6.0558 | 0 | 0 | 1.8899
10 | 1A/8 | DA+0 | Mandai | 415 | Sandy | E | C | C | C | C |  |  | Rateu | 35 | 35 | 0 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 13.7801 | 7.766 | 2.3498 | 0 | 3.6643 | 0 | 0 | 0
11 | 2/0 | DC1+0 | Mandai | 394.3 | DRY | E | C | C |  | C | C |  | Sawau Moolraj | 23 | 23 | 0 | 0 | 0 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 9.072 | 4.73 | 4.342 | 0 | 0 | 0 | 0 | 0
12 | 2/1 | DA+3 | Mandai | 405.3 | Sandy | E | C | C | C | C |  |  | Neemba Ki Dhani | 23 | 23 | 0 | 0 | 0 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 9.1431 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1431
13 | 2/2 | DA+3 | Mandai | 338.5 | Sandy | E | C | C | C | C |  | 33 KV SHUTDOWN, GANG IDLING SINCE 11.09.2025. | Danpura | 13 | 13 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 5.2985 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2985
14 | 2/3 | DA+3 | Mandai | 406 | Sandy | E | C | C | C | C |  |  | Rampura Kharda | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0.4017 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4017
15 | 2/4 | DA+3 | Mandai | 429 | Sandy | E | C | C | C | C |  |  | Manpura Kharda | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.7771 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7771
16 | 2/5 | DA+3 | Mandai | 411.6 | Sandy | E | C | C | C | C |  |  | Kharda Charnan | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 3.4972 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4972
17 | 2/6 | DA+3 | Harwa | 425.7 | Sandy | E | C | C | C | C |  |  | Beniwalon Ki Dhani | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 2.4504 | 2.4504 | 0 | 0 | 0 | 0 | 0 | 0
18 | 2/7 | DA+3 | Harwa | 408.2 | Sandy | E | C | C | C | C |  |  | Pareu | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 1.5736 | 1.5736 | 0 | 0 | 0 | 0 | 0 | 0
19 | 2/8 | DA+0 | Harwa | 354.6 | Sandy | E | C | C | C | C |  |  | Mahadeo Ka Mandir | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 2.656 | 2.656 | 0 | 0 | 0 | 0 | 0 | 0
20 | 2/9 | DA+0 | Harwa | 308.7 | DRY | E | C | C | C | C |  |  | Chimoniyon Ki Dhani | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 3.1701 | 3.1701 | 0 | 0 | 0 | 0 | 0 | 0
21 | 3/0 | DD60+6 | Harwa | 336 | DRY | E | C | C |  | C | C |  | Godaron Ki Dhani | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 3.4586 | 3.4586 | 0 | 0 | 0 | 0 | 0 | 0
22 | 4/0 | DD60+6 | Harwa | 226.5 | DRY | E | C | C |  | C | C |  | Daukiyon Ki Dhani | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 1.6246 | 1.6246 | 0 | 0 | 0 | 0 | 0 | 0
23 | 4/1 | DA+0 | Harwa | 343 | DRY | E | C | C | C | C |  |  | Nehru Nagar | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 2.4092 | 2.4092 | 0 | 0 | 0 | 0 | 0 | 0
24 | 4/2 | DA+0 | Harwa | 358.4 | DRY | E | C | C | C | C |  |  | Nematpura | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 2.9564 | 2.9564 | 0 | 0 | 0 | 0 | 0 | 0
25 | 4/3 | DA+0 | Harwa | 381 | DRY | E | C | C | C | C |  |  | Gangapura | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 1.6321 | 1.6321 | 0 | 0 | 0 | 0 | 0 | 0
26 | 4/4 | DA+0 | Harwa | 367.6 | DRY | E | C | C | C | C |  |  | Barnama Charnan | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 2.5541 | 2.5541 | 0 | 0 | 0 | 0 | 0 | 0
27 | 5/0 | DB1+9 | Harwa | 423.1 | DRY | E | C | C |  | C | C |  | Khanora | 13 | 13 | 0 | 0 | 0 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 5.3755 | 5.3755 | 0 | 0 | 0 | 0 | 0 | 0
28 | 6/0 | DB2+9 | Harwa | 246 | DRY | E | C | C |  | C | C | attempeted on 10.07.2025 | Sathuni Purohitan | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 1.2327 | 1.2327 | 0 | 0 | 0 | 0 | 0 | 0
29 | 6/1 | DA+0 | Harwa | 429.9 | DFR | E | C | C | C | C |  |  | Sathuni Charnan | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 3.2034 | 3.2034 | 0 | 0 | 0 | 0 | 0 | 0
30 | 6/2 | DA+0 | Harwa | 362.4 | DFR | E | C | C | C | C |  |  | Simarkhiya | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 1.2299 | 1.2299 | 0 | 0 | 0 | 0 | 0 | 0
31 | 7/0 | DB1+0 | Harwa | 347.9 | DRY | E | C | C |  | C | C |  | Bagawas | 11 | 11 | 0 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 4.011 | 4.011 | 0 | 0 | 0 | 0 | 0 | 0
32 | 8/0 | DB1+0 | Harwa | 210.8 | DRY | E | C | C |  | C | C |  | Mohanpura | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 2.4074 | 2.4074 | 0 | 0 | 0 | 0 | 0 | 0
33 | 8/1 | DA+3 | Harwa | 409.2 | DRY | E | C | C | C | C |  |  | Meghawas | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 1.9041 | 1.9041 | 0 | 0 | 0 | 0 | 0 | 0
34 | 8/2 | DA+3 | Harwa | 413.6 | DRY | E | C | C | C | C |  |  | Sagaranari | 10 | 10 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 4.1779 | 4.1779 | 0 | 0 | 0 | 0 | 0 | 0
35 | 8/3 | DA+0 | Harwa | 393.2 | DRY | E | C | C | C | C |  |  | Nagana | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 2.5271 | 2.5271 | 0 | 0 | 0 | 0 | 0 | 0
36 | 8/4 | DA+3 | Harwa | 416.5 | DRY | E | C | C | C | C |  |  | Deoriya | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 3.6251 | 3.6251 | 0 | 0 | 0 | 0 | 0 | 0
37 | 8/5 | DA+3 | Harwa | 394.6 | DRY | E | C | C | C | C |  |  | Bakati | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 3.7283 | 3.7283 | 0 | 0 | 0 | 0 | 0 | 0
38 | 8/6 | DA+3 | Harwa | 393.2 | DRY | E | C | C | C | C |  |  | Gwalnada | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 3.6749 | 3.6749 | 0 | 0 | 0 | 0 | 0 | 0
39 | 8/7 | DB1+0 | Chak Goonga | 441.1 | DRY | E | C | C |  | C | C |  | Godawas Kalan | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 3.681 | 3.681 | 0 | 0 | 0 | 0 | 0 | 0
40 | 8/8 | DA+6 | Chak Goonga | 414.4 | DRY | E | C | C | C | C |  |  | Doli Kalan | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0.3861 | 0.3861 | 0 | 0 | 0 | 0 | 0 | 0
41 | 8/9 | DA+3 | Chak Goonga | 395.863 | DFR | E | C | C | C | C |  |  | Modathali | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 2.0474 | 2.0474 | 0 | 0 | 0 | 0 | 0 | 0
42 | 8/10 | DA+3 | Chak Goonga | 413.404 | DFR | E | C | C | C | C |  |  | Piprali | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 1.2276 | 1.2276 | 0 | 0 | 0 | 0 | 0 | 0
43 | 8/11 | DA+0 | Chak Goonga | 402.6 | DRY | E | C | C | C | C |  |  | Rabariyawas | 11 | 11 | 0 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 4.5078 | 4.5078 | 0 | 0 | 0 | 0 | 0 | 0
44 | 8/12 | DA+0 | Chak Goonga | 372.1 | DRY | E | C | C | C | C |  |  | Loonawas Charna | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 1.5661 | 1.5661 | 0 | 0 | 0 | 0 | 0 | 0
45 | 9/0 | DD60+18 | Chak Goonga | 457.7 | DRY | E | C | C |  | C | C |  | Loonawas Khurd | 12 | 12 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 4.2541 | 4.2541 | 0 | 0 | 0 | 0 | 0 | 0
46 | 10/0 | DD60+25 | Chak Goonga | 233.1 | DFR | E | C | C |  | C | C |  | Borapadakhamar | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.769 | 0.769 | 0 | 0 | 0 | 0 | 0 | 0
47 | 10/1 | DA+0 | Goonga | 443.7 | DRY | E | C | C | C | C |  |  | Katarda | 12 | 12 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 4.9329 | 4.9329 | 0 | 0 | 0 | 0 | 0 | 0
48 | 10/2 | DA+0 | Goonga | 383.2 | DFR | E | C | C | C | C |  |  | Karni Nagar | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.8202 | 0.8202 | 0 | 0 | 0 | 0 | 0 | 0
49 | 10/3 | DA+0 | Goonga | 398.6 | DFR | E | C | C | C | C |  |  | Basni Jhoonthan | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 3.7108 | 3.7108 | 0 | 0 | 0 | 0 | 0 | 0
50 | 10/4 | DA+3 | Goonga | 410.7 | DFR | E | C | C | C | C |  |  | Sardargarh | 10 | 10 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 3.7882 | 3.7882 | 0 | 0 | 0 | 0 | 0 | 0
51 | 10/5 | DA+3 | Goonga | 416.2 | DRY | E | C | C | C | C
52 | 10/6 | DA+0 | Pusar | 403.4 | DFR | E | C | C | C | C
53 | 10/7 | DA+3 | Pusar | 373.845 | DRY | E | C | C | C | C
54 | 10/8 | DA+3 | Pusar | 411.823 | DFR | E | C | C | C | C
55 | 10/9 | DA+0 | Pusar | 414.2 | DRY | E | C | C | C | C
56 | 10/10 | DA+3 | Pusar | 402.3 | Sandy | E | C | C | C | C
57 | 10/11 | DA+3 | Pusar | 430.3 | DRY | E | C | C | C | C
58 | 10/12 | DB1+0 | Pusar | 406.2 | DRY | E | C | C |  | C | C
59 | 10/13 | DA+3 | Pusar | 405.3 | DRY | E | C | C | C | C
60 | 10/14 | DA+3 | Pusar | 427.1 | DRY | E | C | C | C | C
61 | 10/15 | DA+3 | Pusar | 400 | DRY | E | C | C | C | C
62 | 10/16 | DA+3 | Pusar | 412.8 | DRY | E | C | C | C | C
63 | 10/17 | DA+3 | Pusar | 387.8 | DFR | E | C | C | C | C
64 | 10/18 | DA+3 | Pusar | 436.7 | DFR | E | C | C | C | C
65 | 10/19 | DA+0 | Pusar | 403.7 | DRY | E | C | C | C | C
66 | 10/20 | DA+3 | Bisoo Khurd | 409.5 | DFR | E | C | C | C | C
67 | 10/21 | DA+3 | Bisoo Khurd | 418.6 | DFR | E | C | C | C | C
68 | 10/22 | DA+0 | Bisoo Khurd | 410.3 | Sandy | E | C | C | C | C
69 | 10/23 | DA+0 | Bisoo Khurd | 384 | Sandy | E | C | C | C | C
70 | 11/0 | DB1+0 | Bisoo Khurd | 450.8 | Sandy | E | C | C |  | C | C
71 | 11/1 | DA+0 | Bisoo Khurd | 384.2 | Sandy | E | C | C | C | C
72 | 11/2 | DA+0 | Bisoo Khurd | 338.6 | Sandy | E | C | C | C | C
73 | 11/3 | DA+0 | Bisoo Khurd | 370.7 | Sandy | E | C | C | C | C
74 | 11/4 | DA+0 | Bisoo Khurd | 434.1 | Sandy | E | C | C | C | C
75 | 11/5 | DA+0 | Bisoo Khurd | 368.1 | DFR | E | C | C | C | C
76 | 11A/0 | DB1+0 | Bisoo Khurd | 342.3 | DRY | E | C | C |  | C | C
77 | 11A/1 | DA+3 | Bisoo Khurd | 405.1 | DRY | E | C | C | C | C
78 | 11A/2 | DA+0 | Bisoo Khurd | 412.2 | DRY | E | C | C | C | C
79 | 11A/3 | DA+3 | Bhiyad | 412.2 | DRY | E | C | C | C | C
80 | 11A/4 | DA+3 | Bhiyad | 422.1 | DRY | E | C | C | C | C
81 | 11A/5 | DA+3 | Bhiyad | 418.3 | DRY | E | C | C | C | C
82 | 11A/6 | DA+6 | Bhiyad | 384.3 | DRY | E | C | C | C | C
83 | 11A/7 | DA+9 | Bhiyad | 434.2 | Sandy | E | C | C | C | C
84 | 11A/8 | DA+6 | Bhiyad | 390.1 | Sandy | E | C | C | C | C
85 | 11A/9 | DA+3 | Bhiyad | 426.3 | DRY | E | C | C | C | C
86 | 12/0 | DD60+0 | Bhiyad | 405.9 | DRY | E | C | C |  | C | C
87 | 13/0 | DD60+3 | Bhiyad | 211.9 | DRY | E | C | C |  | C | C
88 | 13/1 | DA+9 | Bhiyad | 464.3 | DRY | E | C | C | C | C
89 | 13/2 | DA+3 | Bhiyad | 373.7 | DRY | E | C | C | C | C
90 | 13/3 | DA+3 | Bhiyad | 419.7 | Sandy | E | C | C | C | C
91 | 13/4 | DA+3 | Bhiyad | 420.3 | DRY | E | C | C | C | C
92 | 14/0 | DC2+0 | Bhiyad | 400 | Sandy | E | C | C |  | C | C
93 | 14A/0 | DC1+0 | Bhiyad | 381.4 | DRY | E | C | C |  | C | C
94 | 14A/1 | DA+3 | Bhiyad | 412.765 | DRY | E | C | C | C | C
95 | 14A/2 | DA+0 | Bhiyad | 396.029 | DRY | E | C | C | C | C
96 | 15/0 | DC1+0 | Bhiyad | 383.3 | DRY | E | C | C |  | C | C
97 | 15/1 | DA+3 | Bhiyad | 404.6 | DRY | E | C | C | C | C
98 | 16/0 | DC1+0 | Bhiyad | 413.3 | DRY | E | C | C |  | C | C
99 | 16/1 | DA+0 | Bhiyad | 354.283 | DRY | E | C | C | C | C
100 | 16/2 | DA+0 | Bhiyad | 424.28 | DRY | E | C | C | C | C
101 | 16/3 | DA+3 | Bhiyad | 340.3 | DRY | E | C | C | C | C
102 | 16/4 | DA+0 | Bhiyad | 394.7 | DRY | E | C | C | C | C
103 | 16/5 | DA+3 | Bhiyad | 435.863 | DRY | E | C | C | C | C
104 | 17/0 | DB2+3 | Bhiyad | 386.8 | DRY | E | C | C
105 | 17/1 | DA+3 | Bhiyad | 393.7 | DRY | E | WIP
106 | 17/2 | DA+6 | Bhiyad | 415.9 | DRY | E | WIP
107 | 17/3 | DA+0 | Bhiyad | 422.8 | DRY | E | WIP
108 | 17/4 | DA+3 | Bhiyad | 409.9 | DRY | E | WIP
109 | 17/5 | DA+3 | Bhiyad | 425.3 | DRY | E | WIP
110 | 18/0 | DC2+0 | Bhiyad | 383.4 | DRY | E | WIP | C
111 | 18/1 | DA+0 | Bhiyad | 372.8 | DRY | E | TPL
112 | 18/2 | DA+0 | Bhiyad | 379.8 | DRY | E | TPL
113 | 18/3 | DA+0 | Bhiyad | 371 | DRY | E | TPL
114 | 18/4 | DA+0 | Bhiyad | 398.7 | DRY | E | TPL
115 | 19/0 | DC2+0 | Bhiyad | 380.8 | DRY | E | TPL
116 | 19/1 | DA+0 | Bhiyad | 366.9 | DRY | E | TPL
117 | 19/2 | DA+0 | Kashmir | 372.5 | DRY | E | TPL
118 | 19/3 | DA+0 | Kashmir | 376.5 | DRY | E | TPL
119 | 19/4 | DA+0 | Kashmir | 384.3 | DRY | E | TPL
120 | 19/5 | DA+0 | Kashmir | 375.4 | DRY | E | TPL
121 | 20/0 | DB2+0 | Kashmir | 381.2 | Sandy | E | TPL
122 | 20/1 | DA+0 | Kashmir | 386.8 | Sandy | E | ROW
123 | 20/2 | DA+0 | Kashmir | 387 | DRY | E | ROW
124 | 20/3 | DA+0 | Kashmir | 348.5 | DRY | E | ROW
125 | 21/0 | DB2+0 | Kashmir | 355 | DRY | E | ROW
126 | 21/1 | DA+6 | Kashmir | 414.9 | DRY | E | ROW
127 | 21/2 | DA+0 | Kashmir | 407.2 | Sandy | E | ROW
128 | 21/3 | DA+6 | Kashmir | 432.2 | Sandy | E | ROW
129 | 21/4 | DA+3 | Kashmir | 401.9 | Sandy | E | ROW
130 | 21/5 | DA+6 | Kashmir | 434.2 | DFR | E | ROW
131 | 21/6 | DA+3 | Kashmir | 405.5 | DRY | E | ROW
132 | 21/7 | DA+3 | Kashmir | 426 | DFR | E | ROW
133 | 21/8 | DA+6 | Kashmir | 406.9 | DRY | E | ROW
134 | 21/9 | DA+3 | Kashmir | 433.3 | DFR | E | ROW
135 | 21/10 | DA+6 | Kashmir | 372.9 | DRY | E | ROW
136 | 22/0 | DB2+3 | Kashmir | 443.5 | DRY | E | ROW
137 | 22/1 | DA+9 | Kashmir | 456.3 | Sandy | E | WIP
138 | 22/2 | DA+6 | Kashmir | 379.2 | Sandy | E | WIP
139 | 22/3 | DA+9 | Kashmir | 382.6 | Sandy | E | WIP
140 | 22/4 | DA+9 | Kashmir | 435.6 | Sandy | E | WIP
141 | 22/5 | DA+9 | Kashmir | 402.1 | DRY | E | WIP
142 | 22/6 | DA+0 | Kashmir | 417.3 | Sandy | E | WIP
143 | 22/7 | DA+0 | Kashmir | 347.7 | Sandy | E | WIP
144 | 22/8 | DB1+0 | Kashmir | 356.3 | Sandy | E | WIP
145 | 22/9 | DA+6 | Kashmir | 389.2 | Sandy | E | C
146 | 22/10 | DA+6 | Rateu | 343.8 | Sandy | E | C
147 | 22/11 | DA+6 | Rateu | 395.5 | Sandy | E | C
148 | 22/12 | DA+3 | Rateu | 408 | Sandy | E | C
149 | 22/13 | DA+6 | Rateu | 318 | Sandy | E | C
150 | 23/0 | DD45+3 | Rateu | 447.3 | DRY | E | C
151 | 24/0 | DD45+3 | Rateu | 222.2 | DRY | E | C
152 | 25/0 | DC1+6 | Rateu | 433.9 | DRY | E | C
153 | 25/1 | DA+3 | Rateu | 422.3 | DRY | E | WIP
154 | 25/2 | DA+0 | Rateu | 370.7 | DRY | E | WIP
155 | 25/3 | DA+0 | Rateu | 345.7 | Sandy | E | WIP
156 | 25/4 | DA+0 | Rateu | 391.1 | Sandy | E | WIP
157 | 26/0 | DB1+0 | Rateu | 440.4 | DFR | E | WIP
158 | 26/1 | DA+0 | Rateu | 391.4 | DRY | E | ROW
159 | 26/2 | DA+3 | Rateu | 406.5 | DFR | E | ROW
160 | 26/3 | DA+0 | Rateu | 418 | DRY | E | ROW
161 | 26/4 | DA+6 | Rateu | 422.6 | Sandy | E | ROW |  |  |  |  | 11 KV LINE SHIFTING
162 | 26/5 | DA+6 | Rateu | 410 | Sandy | E | ROW
163 | 26/6 | DA+6 | Rateu | 363.4 | Sandy | E | ROW
164 | 26/7 | DA+0 | Rateu | 421.9 | DFR | E | ROW
165 | 26/8 | DA+6 | Rateu | 416.7 | DFR | E | ROW
166 | 27/0 | DC1+0 | Rateu | 413.8 | DFR | E | ROW
167 | 27/1 | DA+3 | Rateu | 399.8 | DFR | E | C
168 | 27/2 | DA+3 | Rateu | 425.2 | DFR | E | C
169 | 27/3 | DA+3 | Rateu | 398.6 | DFR | E | C
170 | 27/4 | DA+3 | Rateu | 430.7 | DFR | E | C
171 | 27/5 | DA+0 | Rateu | 410 | DRY | E | C
172 | 27/6 | DA+0 | Rateu | 402.6 | Sandy | E | C
173 | 27/7 | DB1+0 | Rateu | 343.5 | DFR | E | C
174 | 27/8 | DA+0 | Rateu | 392 | DFR | E | C
175 | 27/9 | DA+0 | Rateu | 381.1 | DFR | E | C
176 | 27/10 | DA+3 | Rateu | 366.3 | DFR | E | C
177 | 27/11 | DA+3 | Rateu | 420.1 | DRY | E | C
178 | 27/12 | DA+3 | Rateu | 420.8 | Sandy | E | C
179 | 28/0 | DB2+0 | Rateu | 406.6 | DFR | E | C
180 | 28/1 | DA+0 | Rateu | 379.6 | DRY | E | WIP
181 | 28/2 | DA+0 | Sawau Moolraj | 385 | DFR | E | WIP
182 | 28/3 | DA+0 | Sawau Moolraj | 369 | DFR | E | WIP
183 | 28/4 | DA+0 | Sawau Moolraj | 409 | Sandy | E | WIP
184 | 28/5 | DA+9 | Sawau Moolraj | 422 | Sandy | E | WIP
185 | 28/6 | DA+6 | Sawau Moolraj | 370 | Sandy | E | WIP
186 | 28/7 | DA+3 | Sawau Moolraj | 464 | Sandy | E | WIP
187 | 28/8 | DA+3 | Sawau Moolraj | 375 | Sandy | E | WIP
188 | 29/0 | DB1+0 | Sawau Moolraj | 465.5 | DRY | E | WIP
189 | 29/1 | DA+3 | Sawau Moolraj | 365.6 | DRY | E | C
190 | 29/2 | DA+3 | Sawau Moolraj | 424 | DRY | E | C
191 | 29/3 | DA+0 | Sawau Moolraj | 399 | Sandy | E | C
192 | 29/4 | DA+6 | Sawau Moolraj | 440 | DRY | E | C
193 | 30/0 | DC1+0 | Sawau Moolraj | 382.1 | DRY | E | C
194 | 30/1 | DA+0 | Sawau Moolraj | 388.9 | Sandy | E | C
195 | 30/2 | DA+0 | Sawau Moolraj | 445 | Sandy | E | C
196 | 30/3 | DA+3 | Sawau Moolraj | 395 | Sandy | E | C
197 | 30/4 | DA+3 | Sawau Moolraj | 387 | DRY | E | C
198 | 30/5 | DA+3 | Sawau Moolraj | 442 | DRY | E | C
199 | 30/6 | DA+0 | Sawau Moolraj | 314 | DRY | E | C
200 | 31/0 | DB2+0 | Sawau Moolraj | 347.4 | Sandy | E | C
201 | 31/1 | DA+0 | Sawau Moolraj | 383.6 | DRY | E | WIP
202 | 31/2 | DA+0 | Sawau Moolraj | 366 | DRY | E | WIP
203 | 32/0 | DC1+0 | Sawau Moolraj | 332.9 | DRY | E | WIP
204 | 32/1 | DA+3 | Neemba Ki Dhani | 402.7 | Sandy | E | TPL
205 | 32/2 | DA+3 | Neemba Ki Dhani | 428.8 | DRY | E | TPL
206 | 32/3 | DA+0 | Neemba Ki Dhani | 410.9 | Sandy | E | TPL
207 | 32/4 | DA+0 | Neemba Ki Dhani | 381.1 | Sandy | E | TPL
208 | 33/0 | DC1+0 | Neemba Ki Dhani | 451.5 | DRY | E | TPL
209 | 33/1 | DA+0 | Neemba Ki Dhani | 379.6 | DRY | E | TPL
210 | 34/0 | DB2+0 | Neemba Ki Dhani | 292.5 | DRY | E | TPL
211 | 34/1 | DA+9 | Neemba Ki Dhani | 432.6 | Sandy | E | TPL
212 | 34/2 | DA+6 | Neemba Ki Dhani | 407.5 | Sandy | E | TPL
213 | 34/3 | DA+0 | Neemba Ki Dhani | 377 | Sandy | E | TPL
214 | 34/4 | DA+0 | Neemba Ki Dhani | 451.6 | Sandy | E | TPL
215 | 35/0 | DB2+6 | Neemba Ki Dhani | 379.3 | Sandy | E | TPL
216 | 35/1 | DA+9 | Neemba Ki Dhani | 265.6 | Sandy | E | TPL
217 | 35/2 | DB1+0 | Neemba Ki Dhani | 492.4 | Sandy | E | TPL
218 | 35/3 | DB1+6 | Neemba Ki Dhani | 522.2 | Sandy | E | TPL
219 | 35/4 | DA+0 | Neemba Ki Dhani | 418.9 | DRY | E | TPL
220 | 35/5 | DA+0 | Neemba Ki Dhani | 421.7 | Sandy | E | TPL
221 | 36/0 | DB2+0 | Neemba Ki Dhani | 342.7 | Sandy | E | TPL
222 | 36/1 | DA+3 | Neemba Ki Dhani | 386.4 | Sandy | E | TPL
223 | 36/2 | DA+0 | Neemba Ki Dhani | 309.4 | Sandy | E | TPL
224 | 36/3 | DA+0 | Neemba Ki Dhani | 357.8 | Sandy | E | TPL
225 | 36/4 | DA+6 | Neemba Ki Dhani | 480.4 | Sandy | E | TPL
226 | 37/0 | DB2+0 | Neemba Ki Dhani | 350.5 | Sandy | E | TPL
227 | 37/1 | DA+9 | Danpura | 443.3 | Sandy | E | TPL
228 | 37/2 | DA+3 | Danpura | 356.7 | Sandy | E | TPL
229 | 37/3 | DA+0 | Danpura | 339.9 | Sandy | E | TPL
230 | 38/0 | DB2+6 | Danpura | 500.3 | Sandy | E | TPL
231 | 38/1 | DA+0 | Danpura | 421.4 | Sandy | E | TPL
232 | 38/2 | DA+6 | Danpura | 419 | Sandy | E | TPL
233 | 38/3 | DA+9 | Danpura | 420.3 | Sandy | E | TPL |  |  |  |  | ROW, 4 -X arm balance, Left the location based on instruction by resonia Ltd.
234 | 38/4 | DA+9 | Danpura | 414.9 | Sandy | E | TPL
235 | 39/0 | DB2+6 | Danpura | 425.5 | Sandy | E | TPL
236 | 39/1 | DA+0 | Danpura | 412.638 | Sandy | E | TPL
237 | 40/0 | DC2+0 | Danpura | 322.61 | Sandy | E | TPL
238 | 40/1 | DA+6 | Danpura | 396.2 | Sandy | E | TPL
239 | 40/2 | DA+3 | Danpura | 425.8 | Sandy | E | TPL
240 | 40/3 | DA+3 | Rampura Kharda | 401.7 | Sandy | E | TPL
241 | 41/0 | DC1+6 | Manpura Kharda | 436.3 | Sandy | E | TPL
242 | 41/1 | DB1+9 | Manpura Kharda | 340.8 | Sandy | E | TPL
243 | 41/2 | DA+0 | Kharda Charnan | 447.8 | Sandy | E | TPL
244 | 42/0 | DC1+0 | Kharda Charnan | 382.3 | Sandy | E | TPL
245 | 42/1 | DA+6 | Kharda Charnan | 384.7 | Sandy | E | TPL
246 | 42/2 | DA+6 | Kharda Charnan | 407.4 | Sandy | E | TPL
247 | 42/3 | DA+0 | Kharda Charnan | 414.2 | Sandy | E | TPL
248 | 42/4 | DA+0 | Kharda Charnan | 256.4 | Sandy | E | TPL
249 | 42/5 | DA+9 | Kharda Charnan | 403.8 | Sandy | E | TPL
250 | 42/6 | DA+0 | Kharda Charnan | 396.7 | Sandy | E | TPL
251 | 43/0 | DB1+0 | Kharda Charnan | 403.9 | Sandy | E | TPL | C
252 | 43/1 | DA+3 | Beniwalon Ki Dhani | 346 | Sandy | E | C | C | C | C
253 | 43/2 | DA+0 | Beniwalon Ki Dhani | 475.8 | Sandy | E | C | C | C | C
254 | 43/3 | DA+0 | Beniwalon Ki Dhani | 363.7 | DRY | E | C | C | C | C
255 | 43/4 | DA+3 | Beniwalon Ki Dhani | 431.8 | Sandy | E | C | C | C | C
256 | 43/5 | DA+3 | Beniwalon Ki Dhani | 405.3 | DRY | E | C | C | C | C
257 | 43/6 | DA+3 | Beniwalon Ki Dhani | 427.8 | Sandy | E | C | C | C | C
258 | 43/7 | DA+3 | Pareu | 389.8 | Sandy | E | C | C | C | C
259 | 43/8 | DA+9 | Pareu | 449.5 | Sandy | E | C | C | C | C
260 | 43/9 | DA+9 | Pareu | 388 | Sandy | E | C | C | C | C
261 | 43/10 | DA+3 | Pareu | 346.3 | Sandy | E | C | C | C | C
262 | 43/11 | DA+3 | Mahadeo Ka Mandir | 444.8 | Sandy | E | C | C | C | C
263 | 44/0 | DB1+3 | Mahadeo Ka Mandir | 383.9 | Sandy | E | C | C |  | C | C
264 | 44/1 | DA+0 | Mahadeo Ka Mandir | 384.3 | Sandy | E | C | C | C | C
265 | 44/2 | DA+0 | Mahadeo Ka Mandir | 359 | Sandy | E | C | C | C | C
266 | 44/3 | DA+0 | Mahadeo Ka Mandir | 334 | Sandy | E | C | C | C | C
267 | 44/4 | DA+9 | Mahadeo Ka Mandir | 395 | Sandy | E | C | C | C | C
268 | 44/5 | DA+9 | Mahadeo Ka Mandir | 355 | Sandy | E | C | C | C | C
269 | 44/6 | DB1+3 | Chimoniyon Ki Dhani | 485 | Sandy | E | C | C |  | C | C
270 | 44/7 | DA+9 | Chimoniyon Ki Dhani | 473 | Sandy | E | C | C | C | C
271 | 44/8 | DCT+0 | Chimoniyon Ki Dhani | 367 | Sandy | E | C | C |  | C | C
272 | 44/9 | DA+9 | Chimoniyon Ki Dhani | 430 | Sandy | E | C | C | C | C
273 | 44/10 | DB1+9 | Chimoniyon Ki Dhani | 365 | Sandy | E | C | C |  | C | C
274 | 44/11 | DA+0 | Chimoniyon Ki Dhani | 428 | Sandy | E | C | C | C | C
275 | 45/0 | DC2+0 | Chimoniyon Ki Dhani | 327.2 | Sandy | E | C | C |  | C | C
276 | 45/1 | DA+9 | Chimoniyon Ki Dhani | 294.92 | Sandy | E | C | C | C | C
277 | 46/0 | DD60+25 | Godaron Ki Dhani | 406.54 | Sandy | E | C | C |  | C | C
278 | 47/0 | DD60+25 | Godaron Ki Dhani | 199.08 | Sandy | E | C | C |  | C | C
279 | 47/1 | DA+3 | Godaron Ki Dhani | 441.2 | Sandy | E | C | C | C | C
280 | 47/2 | DA+9 | Godaron Ki Dhani | 365.93 | Sandy | E | C | C | C | C
281 | 47/3 | DA+9 | Godaron Ki Dhani | 417.4 | Sandy | E | C | C | C | C
282 | 47/4 | DA+3 | Godaron Ki Dhani | 358.4 | Sandy | E | C | C | C | C
283 | 47/5 | DA+0 | Godaron Ki Dhani | 461.2 | Sandy | E | C | C | C | C
284 | 47/6 | DA+3 | Godaron Ki Dhani | 377.3 | Sandy | E | C | C | C | C
285 | 47/7 | DA+3 | Godaron Ki Dhani | 431.5 | Sandy | E | C | C | C | C
286 | 47/8 | DA+0 | Daukiyon Ki Dhani | 398.8 | Sandy | E | C | C | C | C
287 | 47/9 | DA+3 | Daukiyon Ki Dhani | 405.9 | Sandy | E | C | C | C | C
288 | 47/10 | DA+6 | Daukiyon Ki Dhani | 433.7 | Sandy | E | C | C | C | C
289 | 48/0 | DC2+0 | Daukiyon Ki Dhani | 386.2 | Sandy | E | C | C |  | C | C
290 | 48/1 | DA+9 | Nehru Nagar | 428.9 | Sandy | E | C | C | C | C
291 | 49/0 | DD45+0 | Nehru Nagar | 402.9 | Sandy | E | C | C |  | C | C
292 | 49/1 | DA+0 | Nehru Nagar | 379.1 | Sandy | E | C | C | C | C
293 | 49/2 | DA+3 | Nehru Nagar | 386.6 | Sandy | E | C | C | C | C
294 | 49/3 | DA+3 | Nehru Nagar | 390 | Sandy | E | C | C | C | C
295 | 49/4 | DA+3 | Nehru Nagar | 421.7 | Sandy | E | C | C | C | C
296 | 49/5 | DA+3 | Nematpura | 396.6 | Sandy | E | C | C | C | C
297 | 49/6 | DA+0 | Nematpura | 412.8 | Sandy | E | C | C | C | C
298 | 49/7 | DA+0 | Nematpura | 340.2 | Sandy | E | C | C | C | C
299 | 50/0 | DB2+0 | Nematpura | 500.2 | Sandy | E | C | C |  | C | C
300 | 50/1 | DA+6 | Nematpura | 469.1 | Sandy | E | C | C | C | C
301 | 50/2 | DA+9 | Nematpura | 367.1 | Sandy | E | C | C | C | C
302 | 50/3 | DA+6 | Nematpura | 470.4 | Sandy | E | C | C | C | C
303 | 50/4 | DA+9 | Gangapura | 354.8 | Sandy | E | C | C | C | C
304 | 50/5 | DA+9 | Gangapura | 442.1 | Sandy | E | C | C | C | C
305 | 50/6 | DA+9 | Gangapura | 364.4 | Sandy | E | C | C | C | C
306 | 50/7 | DA+0 | Gangapura | 470.8 | Sandy | E | C | C | C | C
307 | 50/8 | DA+9 | Barnama Charnan | 345 | Sandy | E | C | C | C | C
308 | 50/9 | DA+0 | Barnama Charnan | 364.4 | Sandy | E | C | C | C | C
309 | 50/10 | DA+0 | Barnama Charnan | 394.6 | Sandy | E | C | C | C | C
310 | 51/0 | DC2+0 | Barnama Charnan | 401.4 | Sandy | E | C | C |  | C | C
311 | 51/1 | DA+0 | Barnama Charnan | 356.6 | Sandy | E | C | C | C | C
312 | 51/2 | DA+0 | Barnama Charnan | 307.1 | Sandy | E | C | C | C | C
313 | 52/0 | DC2+0 | Barnama Charnan | 385 | Sandy | E | C | C |  | C | C
314 | 52/1 | DA+6 | Khanora | 402 | Sandy | E | C | C | C | C
315 | 52/2 | DA+6 | Khanora | 402.6 | Sandy | E | C | C | C | C
316 | 52/3 | DA+9 | Khanora | 437 | Sandy | E | C | C | C | C
317 | 52/4 | DA+9 | Khanora | 393.8 | Sandy | E | C | C | C | C
318 | 52/5 | DA+9 | Khanora | 447 | Sandy | E | C | C | C | C
319 | 52/6 | DA+6 | Khanora | 373 | Sandy | E | C | C | C | C
320 | 52/7 | DA+3 | Khanora | 406.8 | Sandy | E | C | C | C | C
321 | 52/8 | DA+6 | Khanora | 433 | Sandy | E | C | C | C | C
322 | 52/9 | DA+3 | Khanora | 399.7 | Sandy | E | C | C | C | C
323 | 52/10 | DA+9 | Khanora | 384.1 | Sandy | E | C | C | C | C
324 | 53/0 | DB2+9 | Khanora | 455.9 | Sandy | E | C | C |  | C | C
325 | 53/1 | DA+9 | Khanora | 433.2 | Sandy | E | C | C | C | C
326 | 53/2 | DA+0 | Khanora | 407.4 | Sandy | E | C | C | C | C
327 | 53/3 | DA+6 | Sathuni Purohitan | 394.5 | Sandy | E | C | C | C | C
328 | 53/4 | DA+0 | Sathuni Purohitan | 410.1 | Sandy | E | C | C | C | C
329 | 53/5 | DA+3 | Sathuni Purohitan | 428.1 | Sandy | E | C | C | C | C
330 | 53/6 | DA+6 | Sathuni Charnan | 406.6 | Sandy | E | C | C | C | C
331 | 53/7 | DA+3 | Sathuni Charnan | 411.3 | Sandy | E | C | C | C | C
332 | 53/8 | DA+3 | Sathuni Charnan | 427.8 | Sandy | E | C | C | C | C
333 | 54/0 | DB1+6 | Sathuni Charnan | 371.3 | Sandy | E | C | C |  | C | C
334 | 54/1 | DA+3 | Sathuni Charnan | 365.1 | Sandy | E | C | C | C | C
335 | 54/2 | DA+3 | Sathuni Charnan | 381 | Sandy | E | C | C | C | C
336 | 54/3 | DA+6 | Sathuni Charnan | 417 | Sandy | E | C | C | C | C
337 | 54/4 | DA+9 | Sathuni Charnan | 423.3 | Sandy | E | C | C | C | C
338 | 54/5 | DA+9 | Simarkhiya | 401 | Sandy | E | C | C | C | C
339 | 55/0 | DB1+6 | Simarkhiya | 424 | Sandy | E | C | C |  | C | C
340 | 55/1 | DA+0 | Simarkhiya | 404.9 | WFR | E | C | C | C | C
341 | 55/2 | DA+0 | Bagawas | 343.1 | WFR | E | C | C | C | C
342 | 55/3 | DA+0 | Bagawas | 357.7 | Sandy | E | C | C | C | C
343 | 55/4 | DA+0 | Bagawas | 365.2 | Sandy | E | C | C | C | C
344 | 55/5 | DA+0 | Bagawas | 350.1 | Sandy | E | C | C | C | C
345 | 55/6 | DA+0 | Bagawas | 357.7 | Sandy | E | C | C | C | C
346 | 55/7 | DA+0 | Bagawas | 337.8 | Sandy | E | C | C | C | C
347 | 55/8 | DA+6 | Bagawas | 341.22 | Sandy | E | C | C | C | C
348 | 56/0 | DD60+25 | Bagawas | 460.49 | Sandy | E | C | C |  | C | C
349 | 57/0 | DD60+25 | Bagawas | 219.76 | Sandy | E | C | C |  | C | C
350 | 57/1 | DA+0 | Bagawas | 461.1 | Sandy | E | C | C | C | C
351 | 57/2 | DA+3 | Mohanpura | 355.5 | DRY | E | C | C | C | C
352 | 57/3 | DA+0 | Mohanpura | 405.4 | DRY | E | C | C | C | C
353 | 57/4 | DA+0 | Mohanpura | 418.2 | Sandy | E | C | C | C | C
354 | 57/5 | DA+3 | Bagawas | 416.8 | Sandy | E | C | C | C | C
355 | 57/6 | DA+3 | Mohanpura | 395 | Sandy | E | C | C | C | C
356 | 57/7 | DA+3 | Meghawas | 401.8 | DFR | E | C | C | C | C
357 | 58/0 | DC1+3 | Meghawas | 433.9 | DFR | E | C | C |  | C | C
358 | 59/0 | DC2+0 | Meghawas | 238.9 | DRY | E | C | C |  | C | c
359 | 59/1 | DA+3 | Meghawas | 411.3 | DRY | E | C | C | C | C
360 | 59/2 | DA+3 | Meghawas | 418.2 | DFR | E | C | C | C | C
361 | 59/3 | DA+3 | Mohanpura | 412.3 | DFR | E | C | C | C | C
362 | 59/4 | DA+3 | Mohanpura | 421 | DFR | E | C | C | C | C
363 | 59/5 | DA+3 | Sagaranari | 419.7 | DFR | E | C | C | C | C
364 | 59/6 | DA+3 | Sagaranari | 419.1 | DFR | E | C | C | C | C
365 | 59/7 | DA+3 | Sagaranari | 408.8 | DRY | E | C | C | C | C
366 | 59/8 | DB1+3 | Sagaranari | 426.9 | DRY | E | C | C |  | C | C
367 | 59/9 | DA+3 | Sagaranari | 434.7 | DRY | E | C | C | C | C
368 | 59/10 | DA+0 | Sagaranari | 400.8 | DRY | E | C | C | C | C
369 | 59/11 | DA+6 | Sagaranari | 436.3 | DFR | E | C | C | C | C
370 | 59/12 | DA+6 | Sagaranari | 393.1 | DFR | E | C | C | C | C
371 | 59/13 | DA+3 | Sagaranari | 447.4 | DRY | E | C | C | C | C
372 | 59/14 | DA+6 | Sagaranari | 391.1 | DRY | E | C | C | C | C
373 | 59/15 | DA+6 | Nagana | 448.6 | DRY | E | C | C | C | C
374 | 59/16 | DA+9 | Nagana | 388 | Dry | E | C | C | C | C
375 | 60/0 | DC1+0 | Nagana | 438 | DRY | E | C | C |  | C | C
376 | 60/1 | DA+6 | Nagana | 413.8 | DRY | E | C | C | C | C
377 | 60/2 | DA+3 | Nagana | 424.2 | DFR | E | C | C | C | C
378 | 60/3 | DA+3 | Nagana | 414.5 | DFR | E | C | C | C | C
379 | 60/4 | DA+3 | Deoriya | 425.6 | DFR | E | C | C | C | C
380 | 60/5 | DA+3 | Deoriya | 412.3 | DRY | E | C | C | C | C
381 | 60/6 | DA+0 | Deoriya | 374.1 | DRY | E | C | C | C | C
382 | 60/7 | DA+3 | Deoriya | 410.1 | DRY | E | C | C | C | C
383 | 60/8 | DA+0 | Deoriya | 400.4 | DRY | E | C | C | C | C
384 | 60/9 | DA+3 | Deoriya | 409.2 | DRY | E | C | C | C | C
385 | 60/10 | DA+0 | Deoriya | 401 | DFR | E | C | C | C | C
386 | 60/11 | DA+3 | Deoriya | 394.5 | DRY | E | C | C | C | C
387 | 61/0 | DB2+0 | Deoriya | 397.9 | DRY | E | C | C |  | C | C
388 | 61/1 | DA+6 | Bakati | 405.7 | DFR | E | C | C | C | C
389 | 61/2 | DA+6 | Bakati | 433.2 | DFR | E | C | C | C | C
390 | 61/3 | DA+6 | Bakati | 400.9 | DRY | E | C | C | C | C
391 | 61/4 | DA+3 | Bakati | 427 | DRY | E | C | C | C | C
392 | 61/5 | DA+3 | Bakati | 413.9 | DRY | E | C | C | C | C
393 | 61/6 | DA+3 | Bakati | 426.4 | DRY | E | C | C | C | C
394 | 61/7 | DA+9 | Bakati | 411.5 | Dry | E | C | C | C | C
395 | 61/8 | DA+6 | Bakati | 376.3 | DRY | E | C | C | C | C
396 | 61/9 | DA+0 | Bakati | 433.4 | Dry | E | C | C | C | C
397 | 61/10 | DA+9 | Gwalnada | 405.6 | DRY | E | C | C | C | C
398 | 62/0 | DB2+0 | Gwalnada | 434.3 | DRY | E | C | C |  | C | C
399 | 62/1 | DA+3 | Gwalnada | 418 | Sandy | E | C | C | C | C
400 | 62/2 | DA+3 | Gwalnada | 386 | DRY | E | C | C | C | C
401 | 62/3 | DA+0 | Gwalnada | 400 | DRY | E | C | C | C | C
402 | 62/4 | DA+3 | Gwalnada | 401 | DRY | E | C | C | C | C
403 | 62/5 | DA+0 | Gwalnada | 403 | DRY | E | C | C | C | C
404 | 62/6 | DA+3 | Gwalnada | 404 | DRY | E | C | C | C | C
405 | 62/7 | DA+3 | Gwalnada | 423 | DRY | E | C | C | C | C
406 | 62/8 | DA+0 | Godawas Kalan | 409 | DFR | E | C | C | C | C
407 | 62/9 | DA+3 | Godawas Kalan | 409 | DFR | E | C | C | C | C
408 | 62/10 | DA+0 | Godawas Kalan | 411 | DFR | E | C | C | C | C
409 | 62/11 | DA+3 | Godawas Kalan | 413 | DRY | E | C | C | C | C
410 | 63/0 | DC1+0 | Doli Kalan | 386.1 | DFR | E | C | C |  | C | C
411 | 63/1 | DA+3 | Godawas Kalan | 400 | DFR | E | C | C | C | C
412 | 63/2 | DA+0 | Godawas Kalan | 416 | DFR | E | C | C | C | C
413 | 63/3 | DA+3 | Godawas Kalan | 411 | DFR | E | C | C | C | C
414 | 63/4 | DA+0 | Godawas Kalan | 399 | DRY | E | C | C | C | C
415 | 63/5 | DA+3 | Godawas Kalan | 413 | DFR | E | C | C | C | C
416 | 63/6 | DA+3 | Modathali | 426 | DRY | E | C | C | C | C
417 | 63/7 | DA+3 | Modathali | 413 | DRY | E | C | C | C | C
418 | 63/8 | DA+3 | Modathali | 425 | DRY | E | C | C | C | C
419 | 64/0 | DB2+0 | Modathali | 408.3 | DRY | E | C | C |  | C | C
420 | 64/1 | DA+0 | Modathali | 375.1 | DRY | E | C | C | C | C
421 | 64/2 | DA+3 | Piprali | 408.7 | DRY | E | C | C | C | C
422 | 64/3 | DA+0 | Piprali | 410.7 | DRY | E | C | C | C | C
423 | 64/4 | DA+3 | Piprali | 408.2 | DRY | E | C | C | C | C
424 | 64/5 | DA+3 | Rabariyawas | 426.2 | DRY | E | C | C | C | C
425 | 64/6 | DA+0 | Rabariyawas | 407.7 | DRY | E | C | C | C | C
426 | 64/7 | DA+3 | Rabariyawas | 401.6 | DRY | E | C | C | C | C
427 | 64/8 | DA+3 | Rabariyawas | 425.5 | DRY | E | C | C | C | C
428 | 64/9 | DA+3 | Rabariyawas | 414.4 | DRY | E | C | C | C | C
429 | 64/10 | DA+3 | Rabariyawas | 410.6 | DRY | E | C | C | C | C
430 | 64/11 | DA+3 | Rabariyawas | 428.4 | DRY | E | C | C | C | C
431 | 65/0 | DB1+0 | Rabariyawas | 400.6 | DRY | E | C | C |  | C | C
432 | 65/1 | DA+0 | Rabariyawas | 395.4 | DRY | E | C | C | C | C
433 | 65/2 | DA+0 | Rabariyawas | 393.7 | DRY | E | C | C | C | C
434 | 65/3 | DA+3 | Rabariyawas | 403.7 | DRY | E | C | C | C | C
435 | 65/4 | DA+0 | Loonawas Charna | 402.9 | DRY | E | C | C | C | C
436 | 65/5 | DA+0 | Loonawas Charna | 376.4 | DRY | E | C | C | C | C
437 | 65/6 | DA+0 | Loonawas Charna | 389.2 | DRY | E | C | C | C | C
438 | 65/7 | DA+0 | Loonawas Charna | 397.6 | DRY | E | C | C | C | C
439 | 65/8 | DA+0 | Loonawas Khurd | 394.3 | DRY | E | C | C | C | C
440 | 65/9 | DA+0 | Loonawas Khurd | 389 | DRY | E | C | C | C | C
441 | 65/10 | DA+0 | Loonawas Khurd | 379.1 | DRY | E | C | C | C | C
442 | 65/11 | DA+0 | Loonawas Khurd | 387.6 | DRY | E | C | C | C | C
443 | 66/0 | DC2+6 | Loonawas Khurd | 426.9 | DRY | E | C | C |  | C | C
444 | 67/0 | DC1+9 | Loonawas Khurd | 207.8 | DRY | E | C | C |  | C | C
445 | 67/1 | DA+0 | Loonawas Khurd | 347.1 | DRY | E | C | C | C | C
446 | 67/2 | DA+0 | Loonawas Khurd | 344.9 | DRY | E | C | C | C | C
447 | 68/0 | DD45+0 | Loonawas Khurd | 369.2 | DRY | E | C | C |  | C | C
448 | 69/0 | DB2+0 | Loonawas Khurd | 200.9 | DFR | E | C | C |  | C | C
449 | 69/1 | DA+3 | Borapadakhamar | 374.1 | DRY | E | C | C | C | C
450 | 70/0 | DC1+0 | Borapadakhamar | 394.9 | DRY | E | C | C |  | C | C
451 | 70/1 | DA+3 | Loonawas Khurd | 388.4 | DRY | E | C | C | C | C
452 | 70/2 | DA+3 | Loonawas Khurd | 418.9 | DRY | E | C | C | C | C
453 | 70/3 | DA+3 | Katarda | 418.6 | DRY | E | C | C | C | C
454 | 70/4 | DA+3 | Katarda | 414 | DRY | E | C | C | C | C
455 | 70/5 | DA+3 | Katarda | 419.6 | DRY | E | C | C | C | C
456 | 70/6 | DA+3 | Katarda | 420.3 | DRY | E | C | C | C | C
457 | 70/7 | DA+3 | Katarda | 419.6 | DRY | E | C | C | C | C
458 | 70/8 | DA+3 | Katarda | 418.2 | DRY | E | C | C | C | C
459 | 70/9 | DA+3 | Karni Nagar | 414.1 | DRY | E | C | C | C | C
460 | 70/10 | DA+3 | Karni Nagar | 406.1 | DRY | E | C | C | C | C
461 | 70/11 | DA+3 | Katarda | 408.6 | DRY | E | C | C | C | C
462 | 71/0 | DB2+3 | Katarda | 420.4 | DRY | E | C | C |  | C | C
463 | 71/1 | DA+3 | Katarda | 398.6 | DRY | E | C | C | C | C
464 | 71/2 | DA+3 | Katarda | 414.3 | DRY | E | C | C | C | C
465 | 71/3 | DA+6 | Katarda | 413 | DRY | E | C | C | C | C
466 | 71/4 | DA+3 | Katarda | 367.7 | DRY | E | C | C | C | C
467 | 71/5 | DA+3 | Basni Jhoonthan | 429.4 | DRY | E | C | C | C | C
468 | 71/6 | DA+0 | Basni Jhoonthan | 408 | DRY | E | C | C | C | C
469 | 71/7 | DA+3 | Basni Jhoonthan | 404.9 | DRY | E | C | C | C | C
470 | 71/8 | DA+3 | Basni Jhoonthan | 431.6 | DRY | E | C | C | C | C
471 | 72/0 | DB2+3 | Basni Jhoonthan | 408.4 | DRY | E | C | C |  | C | C
472 | 72/1 | DA+3 | Basni Jhoonthan | 435.3 | DRY | E | C | C | C | C
473 | 72/2 | DA+0 | Basni Jhoonthan | 403.9 | DRY | E | C | C | C | C
474 | 72/3 | DA+3 | Basni Jhoonthan | 389.2 | DRY | E | C | C | C | C
475 | 73/0 | DB2+0 | Basni Jhoonthan | 400.1 | DRY | E | C | C |  | C | C
476 | 73/1 | DA+0 | Sardargarh | 383.3 | DRY | E | C | C | C | C
477 | 73/2 | DA+0 | Sardargarh | 379 | DRY | E | C | C | C | C
478 | 73/3 | DA+0 | Sardargarh | 381.2 | DRY | E | C | C | C | C
479 | 73/4 | DA+0 | Sardargarh | 384.7 | DRY | E | C | C | C | C
480 | 73/5 | DA+0 | Sardargarh | 368.8 | DRY | E | C | C | C | C
481 | 73/6 | DA+0 | Sardargarh | 365.5 | DRY | E | C | C | C | C
482 | 73/7 | DA+0 | Sardargarh | 392.4 | DRY | E | C | C | C | C
483 | 73/8 | DA+3 | Sardargarh | 374.9 | DRY | E | C | C | C | C
484 | 73/9 | DA+0 | Sardargarh | 379.5 | DRY | E | C | C | C | C
485 | 74/0 | DB2+0 | Sardargarh | 378.9 | Sandy | E | C | C |  | C
[9 empty] | 397 | 485 | 88
[9 empty] | 281 | 337 | 55
[9 empty] | 116 | 148 | 33
[9 empty] | 0 | 0 | 0

## Survey
Progress Summary'!A1 | KEC International Limited
Survey status at TB-408
Section | Sl. No | Section |  | Section Length (in Mtrs) | Detail Survey received Date | Check Survey | [5 empty] | Total | Susp. | Tens.
|  | From | To |  |  | Status | Date of Submission | Further Modification date | Approved Date | Remarks | Remarks
1 | 1 | Gty | 1/0 | 122 | 2023-10-14 | Approved | 2024-09-20 |  | 2024-11-08 | Clearances received on 15.07.2024 |  | 1 | 0 | 1
1 | 2 | 1/0 | 1A/0 | 90 | 2023-10-14 | Approved | 2024-09-20 |  | 2024-11-08 | Clearances received on 15.07.2024 |  | 1 | 0 | 1
1 | 3 | 1/0 | 2/0 | 3438.766 | 2023-10-14 | Approved | 2024-09-20 |  | 2024-11-08 | Clearances received on 15.07.2024 |  | 1 | 0 | 1
1 | 4 | 2/0 | 3/0 | 3823.508 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 10 | 9 | 1
1 | 5 | 3/0 | 4/0 | 226.52 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 1 | 0 | 1
1 | 6 | 4/0 | 5/0 | 1873.545 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 5 | 4 | 1
1 | 7 | 5/0 | 6/0 | 246.019 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 1 | 0 | 1
1 | 8 | 6/0 | 7/0 | 1140.147 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 3 | 2 | 1
1 | 9 | 7/0 | 8/0 | 210.755 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 1 | 0 | 1
1 | 10 | 8/0 | 8/7 | 2861.372 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 7 | 6 | 1
1 | 11 | 8/7 | 9/0 | 2456.044 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 6 | 5 | 1
1 | 12 | 9/0 | 10/0 | 233.076 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 1 | 0 | 1
1 | 13 | 10/0 | 10/12 | 4894.437 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 12 | 11 | 1
1 | 14 | 10/12 | 11/0 | 4844.45 | 2023-10-14 | Approved | 2024-02-22 |  | 2024-05-20 | ROW Cleared on 16/01/23. approved on 20.05.2024 having subject Optimization from GTY to AP74 (Part- F) |  | 12 | 11 | 1
1 | 15 | 11/0 | 11A/0 | 2339.993 | 2023-10-14 | Approved | 2024-02-22 |  | 2024-05-20 | Location no 11/5, 11A/0 are on Hold due to ROW during check survey, Centre peg not done for verification of benching and others. approved on 20.05.2024 having subject Optimization from GTY to AP74 (Part- F) |  | 6 | 5 | 1
1 | 16 | 11A/0 | 12/0 | 4110.631 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 10 | 9 | 1
1 | 17 | 12/0 | 13/0 | 211.914 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 1 | 0 | 1
1 | 18 | 13/0 | 14/0 | 2077.901 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 5 | 4 | 1
1 | 19 | 14/0 | 14A/0 | 381.413 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 1 | 0 | 1
1 | 20 | 14A/0 | 15/0 | 1192.131 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 3 | 2 | 1
1 | 21 | 15/0 | 16/0 | 817.914 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 2 | 1 | 1
1 | 22 | 16/0 | 17/0 | 2336.157 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 6 | 5 | 1
1 | 23 | 17/0 | 18/0 | 2451.083 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 6 | 5 | 1
1 | 24 | 18/0 | 19/0 | 1903.166 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 5 | 4 | 1
1 | 25 | 19/0 | 20/0 | 2256.723 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 6 | 5 | 1
1 | 26 | 20/0 | 21/0 | 1477.254 | 2023-10-14 | Approved | 2025-07-03 |  | 2025-07-12 | ROW Cleared on 23/6/2025, Check survey completed on the same day. |  | 4 | 3 | 1
1 | 27 | 21/0 | 22/0 | 4578.525 | 2023-10-14 | Approved | 2023-11-21 | 2023-12-05 | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 11 | 10 | 1
1 | 28 | 22/0 | 22/8 | 3184.049 | 2023-10-14 | Approved | 2023-11-21 | 2023-12-05 | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 8 | 7 | 1
1 | 29 | 22/8 | 23/0 | 2294.809 | 2023-10-14 | Approved | 2023-11-21 | 2023-12-05 | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 6 | 5 | 1
1 | 30 | 23/0 | 24/0 | 222.155 | 2023-10-14 | Approved | 2023-11-21 | 2023-12-05 | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 1 | 0 | 1
1 | 31 | 24/0 | 25/0 | 433.889 | 2023-10-14 | Approved | 2023-11-21 | 2023-12-05 | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 1 | 0 | 1
1 | 32 | 25/0 | 26/0 | 1970.278 | 2023-10-14 | Approved | 2023-11-06 |  | 2023-11-22 |  |  | 5 | 4 | 1
1 | 33 | 26/0 | 27/0 | 3664.173 | 2023-10-14 | Approved | 2023-11-06 |  | 2023-11-22 |  |  | 9 | 8 | 1
1 | 34 | 27/0 | 27/7 | 2810.22 | 2023-10-14 | Approved | 2023-11-06 |  | 2023-11-22 |  |  | 7 | 6 | 1
1 | 35 | 27/7 | 28/0 | 2386.877 | 2023-10-14 | Approved | 2023-11-06 |  | 2023-11-22 |  |  | 6 | 5 | 1
1 | 36 | 28/0 | 29/0 | 3639.092 | 2023-10-14 | Approved | 2023-11-10 | 2023-12-07 | 2023-11-22 | Modifications due to shifting. |  | 9 | 8 | 1
1 | 37 | 29/0 | 30/0 | 2010.644 | 2023-10-14 | Approved | 2023-11-10 | 2023-12-07 | 2023-11-22 | Modifications due to shifting. |  | 5 | 4 | 1
1 | 38 | 30/0 | 31/0 | 2719.335 | 2023-10-14 | Approved | 2023-11-10 | 2023-12-07 | 2023-11-22 | Modifications due to shifting. |  | 7 | 6 | 1
1 | 39 | 31/0 | 32/0 | 1082.475 | 2023-10-14 | Approved | 2023-11-10 | 2023-12-07 | 2023-11-22 | ROW from 21.12.2023 to 29.12.2023 |  | 3 | 2 | 1
1 | 40 | 32/0 | 33/0 | 2074.99 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | ROW from 21.12.2023 to 29.12.2023 |  | 5 | 4 | 1
1 | 41 | 33/0 | 34/0 | 672.091 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | ROW from 21.12.2023 to 29.12.2023 |  | 2 | 1 | 1
1 | 42 | 34/0 | 35/0 | 2048.196 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 5 | 4 | 1
1 | 43 | 35/0 | 35/2 | 775.496 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 2 | 1 | 1
1 | 44 | 35/2 | 35/3 | 504.678 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 1 | 0 | 1
1 | 45 | 35/3 | 36/0 | 1180.197 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 3 | 2 | 1
1 | 46 | 36/0 | 37/0 | 1883.954 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 5 | 4 | 1
1 | 47 | 37/0 | 37/3 | 1138.536 | 2023-10-14 | Approved | 2024-02-25 |  | 2024-12-11 | Resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 3 | 2 | 1
1 | 48 | 37/3 | 38/0 | 594.059 | 2023-10-14 | Approved | 2024-02-25 |  | 2024-12-11 | Resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 1 | 0 | 1
1 | 49 | 38/0 | 39/0 | 2063.067 | 2023-10-14 | Approved | 2024-11-30 |  | 2024-12-11 | ROW from 06.12.2023 to 10.10.2024 |  | 5 | 4 | 1
1 | 50 | 39/0 | 40/0 | 684.371 | 2023-10-14 | Approved | 2024-11-30 |  | 2024-12-11 | ROW from 06.12.2023 to 10.10.2024 |  | 2 | 1 | 1
1 | 51 | 40/0 | 40/3 | 1183.8 |  | Approved | 2024-06-23 |  | 2024-07-03 | ROW Since 27/1/24 |  | 3 | 2 | 1
1 | 52 | 40/3 | 41/0 | 478.3 |  | Approved | 2024-06-23 |  | 2024-07-03 | ROW Since 27/1/24 |  | 1 | 0 | 1
1 | 53 | 41/0 | 41/1 | 312.3 |  | Approved | 2024-06-23 |  | 2024-07-03 | ROW Since 27/1/24 |  | 1 | 0 | 1
1 | 54 | 41/1 | 42/0 | 818.5 |  | Approved | 2024-06-23 |  | 2024-07-03 | ROW Since 27/1/24 |  | 2 | 1 | 1
1 | 55 | 42/0 | 43/0 | 2607.2 |  | Approved | 2024-06-23 |  | 2024-07-03 | ROW Since 27/1/24 |  | 7 | 6 | 1
1 | 56 | 43/0 | 44/0 | 4912.9 |  | Approved | 2024-06-23 |  | 2024-07-03 |  |  | 12 | 11 | 1
2 | 57 | 44/0 | 44/3 | 1258.6 |  | Approved | 2024-07-06 |  | 2024-07-24 |  |  | 3 | 2 | 1
2 | 58 | 44/3 | 44/8 | 1995.5 |  | Approved | 2024-07-06 |  | 2024-07-24 |  |  | 5 | 4 | 1
2 | 59 | 44/8 | 45/0 | 1448.6 |  | Approved | 2024-07-06 |  | 2024-07-24 |  |  | 4 | 3 | 1
2 | 60 | 45/0 | 46/0 | 701.4 |  | Approved | 2024-07-06 |  | 2024-07-24 |  |  | 2 | 1 | 1
2 | 61 | 46/0 | 47/0 | 197.7 |  | Approved | 2024-07-06 |  | 2024-07-24 |  |  | 1 | 0 | 1
2 | 62 | 47/0 | 48/0 | 4479.5 |  | Approved | 2024-02-06 |  | 2024-02-29 |  |  | 11 | 10 | 1
2 | 63 | 48/0 | 49/0 | 809.9 |  | Approved | 2024-02-06 |  | 2024-02-29 |  |  | 2 | 1 | 1
2 | 64 | 49/0 | 50/0 | 3248.6 |  | Approved | 2024-02-06 |  | 2024-02-29 |  |  | 8 | 7 | 1
2 | 65 | 50/0 | 51/0 | 4444.1 |  | Approved | 2024-02-06 |  | 2024-02-29 |  |  | 11 | 10 | 1
2 | 66 | 51/0 | 52/0 | 1048.7 |  | Approved | 2024-02-06 |  | 2024-02-29 |  |  | 3 | 2 | 1
2 | 67 | 52/0 | 53/0 | 4534.9 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 11 | 10 | 1
2 | 68 | 53/0 | 54/0 | 3690.3 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 9 | 8 | 1
2 | 69 | 54/0 | 55/0 | 2411.4 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 6 | 5 | 1
2 | 70 | 55/0 | 56/0 | 3338.2 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 9 | 8 | 1
2 | 71 | 56/0 | 57/0 | 179.9 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 1 | 0 | 1
2 | 72 | 57/0 | 58/0 | 3307.7 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 8 | 7 | 1
2 | 73 | 58/0 | 59/0 | 238.9 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 1 | 0 | 1
2 | 74 | 59/0 | 59/8 | 3337.3 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 8 | 7 | 1
2 | 75 | 59/8 | 60/0 | 3778 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 9 | 8 | 1
2 | 76 | 60/0 | 61/0 | 4877.6 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 12 | 11 | 1
2 | 77 | 61/0 | 62/0 | 4568.1 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 11 | 10 | 1
2 | 78 | 62/0 | 63/0 | 4866.9 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 12 | 11 | 1
2 | 79 | 63/0 | 64/0 | 3664 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 9 | 8 | 1
2 | 80 | 64/0 | 65/0 | 4967.6 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 12 | 11 | 1
2 | 81 | 65/0 | 66/0 | 4735.8 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 12 | 11 | 1
2 | 82 | 66/0 | 67/0 | 207.8 |  | Approved | 2024-01-24 |  | 2024-01-31 |  |  | 1 | 0 | 1
2 | 83 | 67/0 | 68/0 | 1061.2 |  | Approved | 2024-01-24 |  | 2024-01-31 |  |  | 3 | 2 | 1
2 | 84 | 68/0 | 69/0 | 200.9 |  | Approved | 2024-01-24 |  | 2024-01-31 |  |  | 1 | 0 | 1
2 | 85 | 69/0 | 70/0 | 769 |  | Approved | 2024-01-24 |  | 2024-01-31 |  |  | 2 | 1 | 1
2 | 86 | 70/0 | 71/0 | 4966.8 |  | Approved | 2024-12-02 |  | 2024-12-10 | ROW Since 20/1/24. |  | 12 | 11 | 1
2 | 87 | 71/0 | 72/0 | 3676 |  | Approved | 2024-02-22 |  | 2024-05-20 |  |  | 9 | 8 | 1
2 | 88 | 72/0 | 73/0 | 1628.5 |  | Approved | 2024-02-22 |  | 2024-05-20 |  |  | 4 | 3 | 1
2 | 89 | 73/0 | 74/0 | 3788.2 |  | Approved | 2024-08-20 |  | 2024-08-27 | Approved. |  | 10 | 9 | 1
| Total (Part-1 & Part-2) |  |  | 191373.675 | [7 empty] | 477 | 388 | 89

## Foundation
Progress Summary'!A1
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line
List of Completed Foundations
Sr. No. | Completion Months | Loc. No. | Tower Type | Soil Classification | Date of Pit marking Till oct-24/ After Oct casting start date | Fdn Comp. Date | Vendor's Name | KEC Section In-Charge
0 | 2023-10-01 | 36/1 | DA+3 | Sandy | 2023-09-28 | 2023-10-04 | Nagana Ray and company | Kuntal Debnath
0 | 2023-12-01 | 61/3 | DA+6 | DRY | 2023-12-13 | 2023-12-14 | Manoj Sharma | R T Singh
0 | 2023-12-01 | 27/12 | DA+3 | Sandy | 2023-12-06 | 2023-12-18 | Nagana Ray And Company | Ajay Yadav
0 | 2023-12-01 | 62/6 | DA+3 | DRY | 2023-12-16 | 2023-12-18 | Shakti Construction | Rakesh Pathak
0 | 2023-12-01 | 59/14 | DA+6 | DRY | 2023-12-17 | 2023-12-18 | Manoj Sharma | R T Singh
0 | 2023-12-01 | 62/7 | DA+3 | DRY | 2023-12-19 | 2023-12-21 | Shakti Construction | Rakesh Pathak
0 | 2023-12-01 | 59/13 | DA+3 | DRY | 2023-12-21 | 2023-12-21 | Manoj Sharma | R T Singh
0 | 2023-12-01 | 27/10 | DA+3 | DFR | 2023-12-19 | 2023-12-24 | Nagana Ray And Company | Jeetu Sachan
0 | 2023-12-01 | 63/8 | DA+3 | DRY | 2023-12-22 | 2023-12-24 | Mahadev Eng | Rakesh Pathak
0 | 2023-12-01 | 59/10 | DA+0 | DRY | 2023-12-23 | 2023-12-24 | Manoj Sharma | R T Singh
0 | 2023-12-01 | 62/5 | DA+0 | DRY | 2023-12-22 | 2023-12-25 | Shakti Construction | Rakesh Pathak
0 | 2023-12-01 | 59/9 | DA+3 | DRY | 2023-12-25 | 2023-12-26 | Manoj Sharma | R T Singh
0 | 2023-12-01 | 60/9 | DA+3 | DRY | 2023-12-26 | 2023-12-27 | Imran | Sumit
0 | 2023-12-01 | 62/4 | DA+3 | DRY | 2023-12-26 | 2023-12-28 | Shakti Construction | Rakesh Pathak
0 | 2023-12-01 | 59/8 | DB1+3 | DRY | 2023-12-27 | 2023-12-28 | Manoj Sharma | Sumit
0 | 2023-12-01 | 26/2 | DA+3 | DFR | 2023-12-22 | 2023-12-29 | A.B. Construction | Jeetu Sachan
0 | 2023-12-01 | 59/6 | DA+3 | DFR | 2023-12-27 | 2023-12-29 | Om Const | Rakesh Pathak
0 | 2023-12-01 | 63/6 | DA+3 | DRY | 2023-12-27 | 2023-12-29 | Mahadev Eng | Rakesh Pathak
0 | 2023-12-01 | 60/8 | DA+0 | DRY | 2023-12-26 | 2023-12-29 | Imran | Sumit
0 | 2023-12-01 | 27/9 | DA+0 | DFR | 2023-12-25 | 2023-12-30 | Nagana Ray And Company | Jeetu Sachan
0 | 2023-12-01 | 59/7 | DA+3 | DRY | 2023-12-29 | 2023-12-30 | Manoj Sharma | R T Singh
0 | 2023-12-01 | 59/5 | DA+3 | DFR | 2023-12-25 | 2023-12-31 | Om Const | R T Singh
0 | 2023-12-01 | 62/3 | DA+0 | DRY | 2023-12-30 | 2023-12-31 | Shakti Construction | Rakesh Pathak
0 | 2024-01-01 | 59/12 | DA+6 | DFR | 2024-01-04 | 2024-01-05 | Manoj Sharma | R T Singh
0 | 2024-01-01 | 60/7 | DA+3 | DRY | 2024-01-01 | 2024-01-05 | Imran | R T Singh
0 | 2024-01-01 | 62/2 | DA+3 | DRY | 2024-01-02 | 2024-01-05 | Shakti Construction | Rakesh Pathak
0 | 2024-01-01 | 59/3 | DA+3 | DFR | 2024-01-03 | 2024-01-05 | Om Const | R T Singh
0 | 2024-01-01 | 64/0 | DB2+0 | DRY | 2024-01-04 | 2024-01-08 | Mahadev Eng | Rakesh Pathak
0 | 2024-01-01 | 57/3 | DA+0 | DRY | 2024-01-06 | 2024-01-08 | Om Const | R T Singh
0 | 2024-01-01 | 60/5 | DA+3 | DRY | 2024-01-08 | 2024-01-09 | Manoj Sharma | R T Singh
0 | 2024-01-01 | 62/11 | DA+3 | DRY | 2024-01-09 | 2024-01-10 | Shakti Construction | Rakesh Pathak
0 | 2024-01-01 | 65/2 | DA+0 | DRY | 2024-01-08 | 2024-01-10 | Veerteja Enterprises | Rakesh Pathak
0 | 2024-01-01 | 65/11 | DA+0 | DRY | 2024-01-09 | 2024-01-10 | Bhati Const. | Rakesh Pathak
0 | 2024-01-01 | 60/6 | DA+0 | DRY | 2024-01-10 | 2024-01-11 | Manoj Sharma | R T Singh
0 | 2024-01-01 | 57/2 | DA+3 | DRY | 2024-01-09 | 2024-01-11 | Om Const | R T Singh
0 | 2024-01-01 | 62/10 | DA+0 | DFR | 2024-01-11 | 2024-01-13 | Shakti Construction | Rakesh Pathak
0 | 2024-01-01 | 65/9 | DA+0 | DRY | 2024-01-11 | 2024-01-13 | Bhati Const. | Rakesh Pathak
0 | 2024-01-01 | 57/4 | DA+0 | Sandy | 2024-01-12 | 2024-01-14 | Om Const | R T Singh
0 | 2024-01-01 | 64/4 | DA+3 | DRY | 2024-01-13 | 2024-01-14 | Mahadev Eng | Rakesh Pathak
0 | 2024-01-01 | 65/3 | DA+3 | DRY | 2024-01-13 | 2024-01-15 | Veerteja Enterprises | Rakesh Pathak
0 | 2024-01-01 | 55/3 | DA+0 | Sandy | 2024-01-09 | 2024-01-15 | Imran | R T Singh
0 | 2024-01-01 | 60/10 | DA+0 | DFR | 2024-01-14 | 2024-01-15 | Manoj Sharma | R T Singh
0 | 2024-01-01 | 62/8 | DA+0 | DFR | 2024-01-15 | 2024-01-16 | Shakti Construction | Rakesh Pathak
0 | 2024-01-01 | 55/4 | DA+0 | Sandy | 2024-01-12 | 2024-01-17 | Imran | R T Singh
0 | 2024-01-01 | 57/5 | DA+3 | Sandy | 2024-01-14 | 2024-01-17 | Om Const | R T Singh
0 | 2024-01-01 | 26/3 | DA+0 | DRY | 2024-01-12 | 2024-01-18 | A.B. Construction | Jeetu Sachan
0 | 2024-01-01 | 64/1 | DA+0 | DRY | 2024-01-10 | 2024-01-18 | Mahadev Eng | Rakesh Pathak
0 | 2024-01-01 | 64/5 | DA+3 | DRY | 2024-01-16 | 2024-01-18 | Mahadev Eng | Rakesh Pathak
0 | 2024-01-01 | 65/6 | DA+0 | DRY | 2024-01-16 | 2024-01-18 | Bhati Const. | Rakesh Pathak
0 | 2024-01-01 | 61/0 | DB2+0 | DRY | 2024-01-17 | 2024-01-19 | Manoj Sharma | R T Singh
0 | 2024-01-01 | 62/9 | DA+3 | DFR | 2024-01-18 | 2024-01-19 | Shakti Construction | Rakesh Pathak
0 | 2024-01-01 | 65/5 | DA+0 | DRY | 2024-01-20 | 2024-01-21 | Bhati Const. | Rakesh Pathak
0 | 2024-01-01 | 64/2 | DA+3 | DRY | 2024-01-20 | 2024-01-21 | Mahadev Eng | Rakesh Pathak
0 | 2024-01-01 | 57/6 | DA+3 | Sandy | 2024-01-18 | 2024-01-21 | Om Const | R T Singh
0 | 2024-01-01 | 63/1 | DA+3 | DFR | 2024-01-21 | 2024-01-23 | Shakti Construction | Rakesh Pathak
0 | 2024-01-01 | 64/9 | DA+3 | DRY | 2024-01-22 | 2024-01-24 | Veerteja Enterprises | Rakesh Pathak
0 | 2024-01-01 | 60/11 | DA+3 | DRY | 2024-01-23 | 2024-01-24 | Manoj Sharma | R T Singh
0 | 2024-01-01 | 65/4 | DA+0 | DRY | 2024-01-23 | 2024-01-24 | Bhati Const. | Rakesh Pathak
0 | 2024-01-01 | 63/7 | DA+3 | DRY | 2024-01-24 | 2024-01-25 | Mahadev Eng | Rakesh Pathak
0 | 2024-01-01 | 55/5 | DA+0 | Sandy | 2024-01-17 | 2024-01-25 | Imran | R T Singh
0 | 2024-01-01 | 55/6 | DA+0 | Sandy | 2024-01-20 | 2024-01-25 | Imran | R T Singh
0 | 2024-01-01 | 63/2 | DA+0 | DFR | 2024-01-24 | 2024-01-25 | Shakti Construction | Rakesh Pathak
0 | 2024-01-01 | 27/8 | DA+0 | DFR | 2024-01-14 | 2024-01-27 | Nagana Ray And Company | Jeetu Sachan
0 | 2024-01-01 | 61/1 | DA+6 | DFR | 2024-01-27 | 2024-01-28 | Manoj Sharma | R T Singh
0 | 2024-01-01 | 55/7 | DA+0 | Sandy | 2024-01-27 | 2024-01-29 | Imran | R T Singh
0 | 2024-01-01 | 64/3 | DA+0 | DRY | 2024-01-29 | 2024-01-30 | Mahadev Eng | Rakesh Pathak
0 | 2024-01-01 | 63/3 | DA+3 | DFR | 2024-01-29 | 2024-01-30 | Shakti Construction | Rakesh Pathak
0 | 2024-01-01 | 64/8 | DA+3 | DRY | 2024-01-29 | 2024-01-31 | Veerteja Enterprises | Rakesh Pathak
0 | 2024-01-01 | 61/2 | DA+6 | DFR | 2024-01-30 | 2024-01-31 | Manoj Sharma | R T Singh
0 | 2024-02-01 | 64/7 | DA+3 | DRY | 2024-02-01 | 2024-02-02 | Mahadev Eng | Rakesh Pathak
0 | 2024-02-01 | 52/5 | DA+9 | Sandy | 2024-01-31 | 2024-02-02 | Imran | R T Singh
0 | 2024-02-01 | 63/4 | DA+0 | DRY | 2024-02-01 | 2024-02-02 | Shakti Construction | Rakesh Pathak
0 | 2024-02-01 | 26/4 | DA+6 | Sandy | 2024-01-27 | 2024-02-04 | Mehai Construction | Jeetu Sachan
0 | 2024-02-01 | 67/2 | DA+0 | DRY | 2024-02-03 | 2024-02-04 | Bhati Const. | Rakesh Pathak
0 | 2024-02-01 | 52/6 | DA+6 | Sandy | 2024-02-03 | 2024-02-06 | Imran | R T Singh
0 | 2024-02-01 | 64/6 | DA+0 | DRY | 2024-02-03 | 2024-02-07 | Mahadev Eng | Rakesh Pathak
0 | 2024-02-01 | 63/5 | DA+3 | DFR | 2024-02-06 | 2024-02-07 | Shakti Construction | Rakesh Pathak
0 | 2024-02-01 | 59/15 | DA+6 | DRY | 2024-02-05 | 2024-02-07 | Om Const | R T Singh
0 | 2024-02-01 | 61/5 | DA+3 | DRY | 2024-02-07 | 2024-02-09 | Manoj Sharma | R T Singh
0 | 2024-02-01 | 67/1 | DA+0 | DRY | 2024-02-07 | 2024-02-09 | Bhati Const. | Rakesh Pathak
0 | 2024-02-01 | 64/10 | DA+3 | DRY | 2024-02-08 | 2024-02-10 | Veerteja Enterprises | Rakesh Pathak
0 | 2024-02-01 | 61/6 | DA+3 | DRY | 2024-02-09 | 2024-02-11 | Manoj Sharma | R T Singh
0 | 2024-02-01 | 52/7 | DA+3 | Sandy | 2024-02-07 | 2024-02-12 | Imran | R T Singh
0 | 2024-02-01 | 59/16 | DA+9 | Dry | 2024-02-11 | 2024-02-12 | Om Const | R T Singh
0 | 2024-02-01 | 63/0 | DC1+0 | DFR | 2024-02-09 | 2024-02-13 | Shakti Construction | Rakesh Pathak
0 | 2024-02-01 | 52/8 | DA+6 | Sandy | 2024-02-09 | 2024-02-13 | Imran | R T Singh
0 | 2024-02-01 | 61/7 | DA+9 | Dry | 2024-02-11 | 2024-02-13 | Manoj Sharma | R T Singh
0 | 2024-02-01 | 26/5 | DA+6 | Sandy | 2024-02-05 | 2024-02-16 | Mehai Construction | Jeetu Sachan
0 | 2024-02-01 | 61/9 | DA+0 | Dry | 2024-02-14 | 2024-02-16 | Manoj Sharma | R T Singh
0 | 2024-02-01 | 60/1 | DA+6 | DRY | 2024-02-14 | 2024-02-16 | Om Const | R T Singh
0 | 2024-02-01 | 28/0 | DB2+0 | DFR | 2024-02-05 | 2024-02-17 | A.B. Construction | Jeetu Sachan
0 | 2024-02-01 | 52/10 | DA+9 | Sandy | 2024-02-14 | 2024-02-17 | Imran | R T Singh
0 | 2024-02-01 | 27/11 | DA+3 | DRY | 2024-02-10 | 2024-02-18 | A.B. Construction | Jeetu Sachan
0 | 2024-02-01 | 49/2 | DA+3 | Sandy | 2024-02-14 | 2024-02-18 | Veerteja Enterprises | R T Singh
0 | 2024-02-01 | 52/9 | DA+3 | Sandy | 2024-02-17 | 2024-02-19 | Imran | R T Singh
0 | 2024-02-01 | 61/8 | DA+6 | DRY | 2024-02-17 | 2024-02-20 | Manoj Sharma | R T Singh
0 | 2024-02-01 | 62/1 | DA+3 | Sandy | 2024-02-17 | 2024-02-21 | Shakti Construction | Rakesh Pathak
0 | 2024-02-01 | 53/5 | DA+3 | Sandy | 2024-02-21 | 2024-02-22 | Imran | R T Singh
0 | 2024-02-01 | 64/11 | DA+3 | DRY | 2024-02-23 | 2024-02-24 | Bhati Const. | Rakesh Pathak
0 | 2024-02-01 | 60/2 | DA+3 | DFR | 2024-02-20 | 2024-02-24 | Om Const | R T Singh
0 | 2024-02-01 | 21/10 | DA+6 | DRY | 2024-02-19 | 2024-02-25 | Swarup Enterprises | Jeetu Sachan
0 | 2024-02-01 | 60/3 | DA+3 | DFR | 2024-02-25 | 2024-02-28 | Manoj Sharma | R T Singh
0 | 2024-02-01 | 26/6 | DA+6 | Sandy | 2024-02-20 | 2024-02-29 | Mehai Construction | Jeetu Sachan
0 | 2024-02-01 | 65/0 | DB1+0 | DRY | 2024-02-28 | 2024-02-29 | Bhati Const. | Rakesh Pathak
0 | 2024-02-01 | 60/4 | DA+3 | DFR | 2024-02-27 | 2024-02-29 | Manoj Sharma | R T Singh
0 | 2024-03-01 | 22/1 | DA+9 | Sandy | 2024-02-26 | 2024-03-02 | Swarup Enterprises | Jeetu Sachan
0 | 2024-03-01 | 61/10 | DA+9 | DRY | 2024-02-03 | 2024-03-04 | Manoj Sharma | R T Singh
0 | 2024-03-01 | 65/1 | DA+0 | DRY | 2024-03-03 | 2024-03-05 | Bhati Const. | Rakesh Pathak
0 | 2024-03-01 | 22/6 | DA+0 | Sandy | 2024-03-01 | 2024-03-09 | A.B. Construction | Jeetu Sachan
0 | 2024-03-01 | 62/0 | DB2+0 | DRY | 2024-03-06 | 2024-03-10 | Manoj Sharma | R T Singh
0 | 2024-03-01 | 61/4 | DA+3 | DRY | 2024-03-13 | 2024-03-14 | Manoj Sharma | R T Singh
0 | 2024-03-01 | 49/3 | DA+3 | Sandy | 2024-03-13 | 2024-03-15 | Veerteja Enterprises | R T Singh
0 | 2024-03-01 | 27/5 | DA+0 | DRY | 2024-01-31 | 2024-03-17 | Majisa Construction | Jeetu Sachan
0 | 2024-03-01 | 49/6 | DA+0 | Sandy | 2024-03-14 | 2024-03-17 | Shakti Construction | R T Singh
0 | 2024-03-01 | 60/0 | DC1+0 | DRY | 2024-03-15 | 2024-03-19 | Manoj Sharma | R T Singh
0 | 2024-03-01 | 49/4 | DA+3 | Sandy | 2024-03-15 | 2024-03-19 | Veerteja Enterprises | R T Singh
0 | 2024-03-01 | 49/5 | DA+3 | Sandy | 2024-03-18 | 2024-03-20 | Shakti Construction | R T Singh
0 | 2024-03-01 | 47/10 | DA+6 | Sandy | 2024-03-18 | 2024-03-20 | Bhati Const. | R T Singh
0 | 2024-03-01 | 47/9 | DA+3 | Sandy | 2024-03-21 | 2024-03-23 | Bhati Const. | R T Singh
0 | 2024-03-01 | 47/8 | DA+0 | Sandy | 2024-03-26 | 2024-03-29 | Bhati Const.
0 | 2024-03-01 | 47/7 | DA+3 | Sandy | 2024-03-30 | 2024-03-31 | Bhati Const.
0 | 2024-04-01 | 50/9 | DA+0 | Sandy | 2024-03-22 | 2024-04-01 | Shakti Construction | R T Singh
0 | 2024-04-01 | 48/0 | DC2+0 | Sandy | 2024-04-03 | 2024-04-07 | Bhati Const. | R T Singh
0 | 2024-04-01 | 50/10 | DA+0 | Sandy | 2024-04-03 | 2024-04-08 | Shakti Construction | R T Singh
0 | 2024-04-01 | 51/1 | DA+0 | Sandy | 2024-04-08 | 2024-04-13 | Shakti Construction
0 | 2024-04-01 | 48/1 | DA+9 | Sandy | 2024-04-08 | 2024-04-15 | Veerteja Enterprises | R T Singh
0 | 2024-04-01 | 50/8 | DA+9 | Sandy | 2024-04-14 | 2024-04-19 | Shakti Construction | R T Singh
0 | 2024-04-01 | 49/1 | DA+0 | Sandy | 2024-04-17 | 2024-04-20 | Veerteja Enterprises | R T Singh
0 | 2024-05-01 | 49/0 | DD45+0 | Sandy | 2024-04-22 | 2024-05-03 | Veerteja Enterprises | R T Singh
0 | 2024-05-01 | 43/6 | DA+3 | Sandy | 2024-05-02 | 2024-05-08 | Bande Bharat Group | Kuntal Debnath
0 | 2024-05-01 | 8/7 | DB1+0 | DRY | 2024-05-05 | 2024-05-10 | Mateshwari Const. | Abhijit Dutta
0 | 2024-05-01 | 50/7 | DA+0 | Sandy | 2024-05-05 | 2024-05-10 | Veerteja Enterprises | R T Singh
0 | 2024-05-01 | 8/10 | DA+3 | DFR | 2024-05-14 | 2024-05-18 | Mateshwari Const. | Abhijit Dutta
0 | 2024-05-01 | 50/1 | DA+6 | Sandy | 2024-05-14 | 2024-05-18 | Veerteja Enterprises | R T Singh
0 | 2024-05-01 | 47/6 | DA+3 | Sandy | 2024-05-15 | 2024-05-18 | Bhati Const. | R T Singh
0 | 2024-05-01 | 52/3 | DA+9 | Sandy | 2024-05-14 | 2024-05-25 | Sb Mehar Const. | R T Singh
0 | 2024-05-01 | 47/2 | DA+9 | Sandy | 2024-05-23 | 2024-05-26 | Bhati Const. | R T Singh
0 | 2024-05-01 | 10/14 | DA+3 | DRY | 2024-05-19 | 2024-05-27 | Mateshwari Const. | Abhijit Dutta
0 | 2024-05-01 | 10/19 | DA+0 | DRY | 2024-05-18 | 2024-05-28 | Jai Bhawani Construction | Abhijit Dutta
0 | 2024-05-01 | 50/4 | DA+9 | Sandy | 2024-05-20 | 2024-05-28 | Veerteja Enterprises | R T Singh
0 | 2024-05-01 | 51/2 | DA+0 | Sandy | 2024-05-25 | 2024-05-31 | Sb Mehar Const. | R T Singh
0 | 2024-05-01 | 47/5 | DA+0 | Sandy | 2024-05-29 | 2024-05-31 | Bhati Const. | R T Singh
0 | 2024-05-01 | 50/2 | DA+9 | Sandy | 2024-05-26 | 2024-05-31 | Veerteja Enterprises | R T Singh
0 | 2024-06-01 | 10/11 | DA+3 | DRY | 2024-05-29 | 2024-06-02 | Mateshwari Const. | Abhijit Dutta
0 | 2024-06-01 | 10/18 | DA+3 | DFR | 2024-05-29 | 2024-06-05 | Jai Bhawani Construction | Abhijit Dutta
0 | 2024-06-01 | 10/13 | DA+3 | DRY | 2024-05-30 | 2024-06-06 | Mateshwari Const. | Abhijit Dutta
0 | 2024-06-01 | 47/3 | DA+9 | Sandy | 2024-06-03 | 2024-06-08 | Bhati Const. | R T Singh
0 | 2024-06-01 | 51/0 | DC2+0 | Sandy | 2024-06-03 | 2024-06-10 | Sb Mehar Const. | R T Singh
0 | 2024-06-01 | 10/17 | DA+3 | DFR | 2024-06-03 | 2024-06-15 | Jai Bhawani Construction | Abhijit Dutta
0 | 2024-06-01 | 53/7 | DA+3 | Sandy | 2024-06-12 | 2024-06-15 | Bhati Const. | R T Singh
0 | 2024-06-01 | 10/8 | DA+3 | DFR | 2024-06-08 | 2024-06-19 | Mateshwari Const. | Abhijit Dutta
0 | 2024-06-01 | 10/12 | DB1+0 | DRY | 2024-06-10 | 2024-06-27 | Mateshwari Const. | Abhijit Dutta
0 | 2024-07-01 | 15/1 | DA+3 | DRY | 2024-06-29 | 2024-07-06 | Om Enterprise | Jeetu Sachan
0 | 2024-07-01 | 10/20 | DA+3 | DFR | 2024-06-20 | 2024-07-07 | Jai Bhawani Construction | Abhijit Dutta
0 | 2024-07-01 | 11A/5 | DA+3 | DRY | 2024-07-04 | 2024-07-12 | Punia Construction | Abhijit Dutta
0 | 2024-07-01 | 10/21 | DA+3 | DFR | 2024-06-28 | 2024-07-14 | Jai Bhawani Construction | Abhijit Dutta
0 | 2024-07-01 | 18/1 | DA+0 | DRY | 2024-07-07 | 2024-07-14 | J.P. Infra | Abhijit Dutta
0 | 2024-07-01 | 15/0 | DC1+0 | DRY | 2024-07-07 | 2024-07-15 | Om Enterprise | Jeetu Sachan
0 | 2024-07-01 | 14A/1 | DA+3 | DRY | 2024-07-14 | 2024-07-22 | Majisa Construction | Jeetu Sachan
0 | 2024-07-01 | 50/0 | DB2+0 | Sandy | 2024-07-10 | 2024-07-22 | Veerteja Enterprises | R T Singh
0 | 2024-07-01 | 11A/6 | DA+6 | DRY | 2024-07-10 | 2024-07-26 | Punia Construction | Bipin Kumar
0 | 2024-07-01 | 10/6 | DA+0 | DFR | 2024-07-16 | 2024-07-26 | Jai Bhawani Construction | Bipin Kumar
0 | 2024-07-01 | 16/0 | DC1+0 | DRY | 2024-07-03 | 2024-07-26 | Majisa Construction | Jeetu Sachan
0 | 2024-07-01 | 58/0 | DC1+3 | DFR | 2024-07-23 | 2024-07-29 | Bhati Const. | R T Singh
0 | 2024-07-01 | 18/0 | DC2+0 | DRY | 2024-07-20 | 2024-07-31 | J.P. Infra | Jeetu Sachan
0 | 2024-07-01 | 11/5 | DA+0 | DFR | 2024-07-18 | 2024-07-31 | Mci | Bipin Kumar
0 | 2024-08-01 | 10/3 | DA+0 | DFR | 2024-07-22 | 2024-08-03 | Jai Bhawani Construction | Bipin Kumar
0 | 2024-08-01 | 11A/7 | DA+9 | Sandy | 2024-07-27 | 2024-08-07 | Punia Construction | Bipin Kumar
0 | 2024-08-01 | 18/2 | DA+0 | DRY | 2024-07-30 | 2024-08-09 | Vibe Infra | Jeetu Sachan
0 | 2024-08-01 | 17/3 | DA+0 | DRY | 2024-07-30 | 2024-08-10 | J.P. Infra | Jeetu Sachan
0 | 2024-08-01 | 57/7 | DA+3 | DFR | 2024-08-07 | 2024-08-10 | Bhati Const. | R T Singh
0 | 2024-08-01 | 16/3 | DA+3 | DRY | 2024-08-03 | 2024-08-12 | Majisa Construction | Jeetu Sachan
0 | 2024-08-01 | 43/9 | DA+9 | Sandy | 2024-08-07 | 2024-08-13 | N.R. Enterprises | Kuntal Debnath
0 | 2024-08-01 | 17/5 | DA+3 | DRY | 2024-08-07 | 2024-08-14 | J.P. Infra | Jeetu Sachan
0 | 2024-08-01 | 11A/2 | DA+0 | DRY | 2024-08-12 | 2024-08-16 | R.K. Construction | Bipin Kumar
0 | 2024-08-01 | 16/4 | DA+0 | DRY | 2024-08-10 | 2024-08-18 | Om Enterprise | Jeetu Sachan
0 | 2024-08-01 | 18/3 | DA+0 | DRY | 2024-08-10 | 2024-08-18 | Vibe Infra | Jeetu Sachan
0 | 2024-08-01 | 17/4 | DA+3 | DRY | 2024-08-15 | 2024-08-19 | J.P. Infra | Jeetu Sachan
0 | 2024-08-01 | 10/9 | DA+0 | DRY | 2024-08-12 | 2024-08-19 | A.B. Construction | Bipin Kumar
0 | 2024-08-01 | 11A/8 | DA+6 | Sandy | 2024-08-07 | 2024-08-20 | Punia Construction | Bipin Kumar
0 | 2024-08-01 | 11A/9 | DA+3 | DRY | 2024-08-16 | 2024-08-22 | Punia Construction | Bipin Kumar
0 | 2024-08-01 | 43/8 | DA+9 | Sandy | 2024-08-14 | 2024-08-22 | N.R. Enterprises | Kuntal Debnath
0 | 2024-08-01 | 18/4 | DA+0 | DRY | 2024-08-13 | 2024-08-23 | Vibe Infra | Jeetu Sachan
0 | 2024-08-01 | 59/2 | DA+3 | DFR | 2024-08-19 | 2024-08-23 | Bhati Const. | R T Singh
0 | 2024-08-01 | 16/2 | DA+0 | DRY | 2024-08-14 | 2024-08-24 | Om Enterprise | Jeetu Sachan
0 | 2024-08-01 | 11A/0 | DB1+0 | DRY | 2024-08-12 | 2024-08-25 | Mci | Abhijit Dutta
0 | 2024-08-01 | 50/6 | DA+9 | Sandy | 2024-08-14 | 2024-08-28 | Kalpana Const. | R T Singh
0 | 2024-08-01 | 53/8 | DA+3 | Sandy | 2024-08-26 | 2024-08-29 | Bhati Const. | R T Singh
0 | 2024-08-01 | 17/1 | DA+3 | DRY | 2024-08-24 | 2024-08-30 | J.P. Infra | Jeetu Sachan
0 | 2024-08-01 | 43/7 | DA+3 | Sandy | 2024-08-24 | 2024-08-30 | N.R. Enterprises | Kuntal Debnath
0 | 2024-08-01 | 16/5 | DA+3 | DRY | 2024-08-28 | 2024-08-31 | Majisa Construction | Jeetu Sachan
0 | 2024-08-01 | 19/0 | DC2+0 | DRY | 2024-08-22 | 2024-08-31 | Vibe Infra | Jeetu Sachan
0 | 2024-09-01 | 11A/1 | DA+3 | DRY | 2024-08-22 | 2024-09-01 | Mci | Abhijit Dutta
0 | 2024-09-01 | 19/1 | DA+0 | DRY | 2024-08-29 | 2024-09-03 | Vibe Infra | Jeetu Sachan
0 | 2024-09-01 | 17/2 | DA+6 | DRY | 2024-08-27 | 2024-09-03 | J.P. Infra | Jeetu Sachan
0 | 2024-09-01 | 13/2 | DA+3 | DRY | 2024-08-28 | 2024-09-03 | Punia Construction | Abhijit Dutta
0 | 2024-09-01 | 43/5 | DA+3 | DRY | 2024-08-25 | 2024-09-05 | N.R. Enterprises | Kuntal Debnath
0 | 2024-09-01 | 53/6 | DA+6 | Sandy | 2024-08-30 | 2024-09-05 | Bhati Const. | R T Singh
0 | 2024-09-01 | 16/1 | DA+0 | DRY | 2024-08-27 | 2024-09-06 | Sidhi Vinayak | Jeetu Sachan
0 | 2024-09-01 | 11A/4 | DA+3 | DRY | 2024-09-02 | 2024-09-07 | Punia Construction | Jeetu Sachan
0 | 2024-09-01 | 54/1 | DA+3 | Sandy | 2024-09-05 | 2024-09-09 | Bhati Const. | R T Singh
0 | 2024-09-01 | 50/3 | DA+6 | Sandy | 2024-09-01 | 2024-09-10 | Kalpana Const. | R T Singh
0 | 2024-09-01 | 73/0 | DB2+0 | DRY | 2024-09-09 | 2024-09-10 | Shree Shyam Const.
0 | 2024-09-01 | 73/9 | DA+0 | DRY | 2024-09-08 | 2024-09-11 | Shakti Construction
0 | 2024-09-01 | 73/2 | DA+0 | DRY | 2024-09-12 | 2024-09-13 | Shree Shyam Const.
0 | 2024-09-01 | 25/0 | DC1+6 | DRY | 2024-09-05 | 2024-09-14 | J.P. Infra | Jeetu Sachan
0 | 2024-09-01 | 54/2 | DA+3 | Sandy | 2024-09-11 | 2024-09-14 | Bhati Const. | R T Singh
0 | 2024-09-01 | 14A/2 | DA+0 | DRY | 2024-09-08 | 2024-09-16 | Sidhi Vinayak | Jeetu Sachan
0 | 2024-09-01 | 10/4 | DA+3 | DFR | 2024-08-27 | 2024-09-16 | A.B. Construction | Abhijit Dutta
0 | 2024-09-01 | 73/1 | DA+0 | DRY | 2024-09-15 | 2024-09-16 | Shree Shyam Const. | Sk Sil
0 | 2024-09-01 | 14/0 | DC2+0 | Sandy | 2024-09-05 | 2024-09-18 | Om Enterprise | Jeetu Sachan
0 | 2024-09-01 | 11A/3 | DA+3 | DRY | 2024-09-05 | 2024-09-19 | R.K. Construction | Abhijit Dutta
0 | 2024-09-01 | 73/6 | DA+0 | DRY | 2024-09-18 | 2024-09-19 | Shree Shyam Const. | Sk Sil
0 | 2024-09-01 | 42/3 | DA+0 | Sandy | 2024-09-05 | 2024-09-20 | Mahadev Construction | Kuntal Debnath
0 | 2024-09-01 | 69/1 | DA+3 | DRY | 2024-09-19 | 2024-09-20 | Bhati Const. | Sk Sil
0 | 2024-09-01 | 25/4 | DA+0 | Sandy | 2024-09-13 | 2024-09-23 | J.P. Infra | Jeetu Sachan
0 | 2024-09-01 | 73/5 | DA+0 | DRY | 2024-09-22 | 2024-09-23 | Shree Shyam Const.
0 | 2024-09-01 | 43/4 | DA+3 | Sandy | 2024-09-10 | 2024-09-25 | N.R. Enterprises | Kuntal Debnath
0 | 2024-09-01 | 13/1 | DA+9 | DRY | 2024-09-19 | 2024-09-25 | Punia Construction | Abhijit Dutta
1 | 2024-09-01 | 40/2 | DA+3 | Sandy | 2024-09-19 | 2024-09-25 | D.R. Construction | Kuntal Debnath
1 | 2024-09-01 | 73/8 | DA+3 | DRY | 2024-09-23 | 2024-09-25 | Shakti Construction
1 | 2024-09-01 | 59/1 | DA+3 | DRY | 2024-09-20 | 2024-09-25 | Bhati Const. | R T Singh
1 | 2024-09-01 | 19/2 | DA+0 | DRY | 2024-09-20 | 2024-09-26 | Vibe Infra | Jeetu Sachan
1 | 2024-09-01 | 72/2 | DA+0 | DRY | 2024-09-25 | 2024-09-26 | Shree Shyam Const.
1 | 2024-09-01 | 17/0 | DB2+3 | DRY | 2024-09-19 | 2024-09-27 | Om Enterprise | Jeetu Sachan
1 | 2024-09-01 | 66/0 | DC2+6 | DRY | 2024-09-23 | 2024-09-27 | Bhati Const. | Sk Sil
1 | 2024-09-01 | 59/11 | DA+6 | DFR | 2024-09-25 | 2024-09-27 | Mahadev Eng | R T Singh
1 | 2024-09-01 | 19/3 | DA+0 | DRY | 2024-09-28 | 2024-09-30 | Vibe Infra | Jeetu Sachan
1 | 2024-09-01 | 43/3 | DA+0 | DRY | 2024-09-15 | 2024-09-30 | Parsuram Sai | Kuntal Debnath
1 | 2024-09-01 | 73/3 | DA+0 | DRY | 2024-09-25 | 2024-09-30 | Awadh Const.
1 | 2024-10-01 | 73/7 | DA+0 | DRY | 2024-09-29 | 2024-10-01 | Shakti Construction
1 | 2024-10-01 | 59/0 | DC2+0 | DRY | 2024-09-29 | 2024-10-04 | Bhati Const. | R T Singh
1 | 2024-10-01 | 67/0 | DC1+9 | DRY | 2024-10-04 | 2024-10-05 | Bhati Const.
1 | 2024-10-01 | 42/5 | DA+9 | Sandy | 2024-09-23 | 2024-10-07 | Mahadev Construction | Kuntal Debnath
1 | 2024-10-01 | 43/0 | DB1+0 | Sandy | 2024-09-28 | 2024-10-07 | N.R. Enterprises | Kuntal Debnath
1 | 2024-10-01 | 25/3 | DA+0 | Sandy | 2024-09-15 | 2024-10-08 | J.P. Infra | Bipin Kumar
1 | 2024-10-01 | 69/0 | DB2+0 | DFR | 2024-09-28 | 2024-10-09 | Bhati Const. | Sk Sil
1 | 2024-10-01 | 73/4 | DA+0 | DRY | 2024-10-08 | 2024-10-09 | Shree Shyam Const. | Sk Sil
1 | 2024-10-01 | 22/13 | DA+6 | Sandy | 2024-09-25 | 2024-10-10 | Rbm | Bipin Kumar
1 | 2024-10-01 | 74/0 | DB2+0 | Sandy | 2024-10-07 | 2024-10-10 | Shakti Construction | Sk Sil
1 | 2024-10-01 | 25/1 | DA+3 | DRY | 2024-09-28 | 2024-10-12 | J.P. Infra | Bipin Kumar
1 | 2024-10-01 | 43/2 | DA+0 | Sandy | 2024-09-28 | 2024-10-12 | Parsuram Sai | Kuntal Debnath
1 | 2024-10-01 | 72/3 | DA+3 | DRY | 2024-10-14 | 2024-10-15 | Shree Shyam Const. | Sk Sil
1 | 2024-10-01 | 43/11 | DA+3 | Sandy | 2024-09-25 | 2024-10-18 | Jitendra Enterprises | Kuntal Debnath
1 | 2024-10-01 | 13/0 | DD60+3 | DRY | 2024-10-04 | 2024-10-18 | R.K. Construction | Jeetu Sachan
1 | 2024-10-01 | 71/7 | DA+3 | DRY | 2024-10-17 | 2024-10-18 | Shree Shyam Const. | Sk Sil
1 | 2024-10-01 | 59/4 | DA+3 | DFR | 2024-10-14 | 2024-10-19 | Bhati Const. | R T Singh
1 | 2024-10-01 | 22/12 | DA+3 | Sandy | 2024-10-11 | 2024-10-21 | Rbm | Bipin Kumar
1 | 2024-10-01 | 42/1 | DA+6 | Sandy | 2024-10-10 | 2024-10-21 | N.R. Enterprises | Kuntal Debnath
1 | 2024-10-01 | 71/6 | DA+0 | DRY | 2024-10-20 | 2024-10-21 | Shree Shyam Const. | Sk Sil
1 | 2024-10-01 | 49/7 | DA+0 | Sandy | 2024-09-12 | 2024-10-21 | Kalpana Const. | R T Singh
1 | 2024-10-01 | 25/2 | DA+0 | DRY | 2024-10-12 | 2024-10-22 | J.P. Infra | Bipin Kumar
1 | 2024-10-01 | 13/3 | DA+3 | Sandy | 2024-09-28 | 2024-10-25 | Punia Construction | Ashutosh Singh
1 | 2024-10-01 | 22/7 | DA+0 | Sandy | 2024-10-24 | 2024-10-27 | Rbm | Bipin Kumar
1 | 2024-10-01 | 22/3 | DA+9 | Sandy | 2024-10-24 | 2024-10-27 | J.P. Infra | Bipin Kumar
1 | 2024-10-01 | 43/1 | DA+3 | Sandy | 2024-10-16 | 2024-10-30 | Parsuram Sai | Kuntal Debnath
2 | 2024-11-01 | 42/6 | DA+0 | Sandy | 2024-10-22 | 2024-11-07 | D.R. Construction | Kuntal Debnath
2 | 2024-11-01 | 2/4 | DA+3 | Sandy | 2024-11-12 | 2024-11-16 | Laxmi Enterprises | Ashutosh Kumar
3 | 2024-11-01 | 42/2 | DA+6 | Sandy | 2024-11-08 | 2024-11-17 | D.R. Construction | Kuntal Debnath
3 | 2024-11-01 | 22/8 | DB1+0 | Sandy | 2024-11-06 | 2024-11-19 | Rbm | Bipin Kumar
3 | 2024-11-01 | 22/2 | DA+6 | Sandy | 2024-11-11 | 2024-11-20 | J.P. Infra | Bipin Kumar
3 | 2024-11-01 | 54/0 | DB1+6 | Sandy | 2024-11-15 | 2024-11-21 | Bhati Const. | R T Singh
3 | 2024-11-01 | 65/8 | DA+0 | DRY | 2024-11-27 | 2024-11-28 | Bhati Const. | Sk Sil
4 | 2024-11-01 | 42/0 | DC1+0 | Sandy | 2024-11-20 | 2024-11-30 | D.R. Construction | Kuntal Debnath
4 | 2024-11-01 | 65/7 | DA+0 | DRY | 2024-11-29 | 2024-11-30 | Bhati Const. | Sk Sil
4 | 2024-12-01 | 2/3 | DA+3 | Sandy | 2024-11-29 | 2024-12-03 | Laxmi Enterprise | Karan Singh
4 | 2024-12-01 | 22/4 | DA+9 | Sandy | 2024-12-01 | 2024-12-05 | Jp Infra | Bipin Singh
4 | 2024-12-01 | 6/1 | DA+0 | DFR | 2024-12-01 | 2024-12-10 | H.S. Engineering | Jitendra Yadav
4 | 2024-12-01 | 12/0 | DD60+0 | DRY | 2024-12-07 | 2024-12-14 | Vibe Infra Power | Jitendra Yadav
4 | 2024-12-01 | 22/5 | DA+9 | DRY | 2024-12-09 | 2024-12-14 | S.D. Infra | Bipin Singh
5 | 2024-12-01 | 41/2 | DA+0 | Sandy | 2024-10-26 | 2024-12-15 | D.R. Construction | Kuntal Debnath
5 | 2024-12-01 | 2/5 | DA+3 | Sandy | 2024-12-10 | 2024-12-15 | Sri Nagana Ray Enterprise | Jitendra Yadav
5 | 2024-12-01 | 22/9 | DA+6 | Sandy | 2024-12-13 | 2024-12-16 | Rbm | Bipin Singh
5 | 2024-12-01 | 70/8 | DA+3 | DRY | 2024-12-16 | 2024-12-17 | Tantray Construction | Sk Sil
5 | 2024-12-01 | 72/1 | DA+3 | DRY | 2024-12-16 | 2024-12-18 | Meer Const | Sk Sil
5 | 2024-12-01 | 70/7 | DA+3 | DRY | 2024-12-17 | 2024-12-19 | Tantray Construction | Sk Sil
5 | 2024-12-01 | 71/8 | DA+3 | DRY | 2024-12-19 | 2024-12-20 | Meer Const | Sk Sil
5 | 2024-12-01 | 52/1 | DA+6 | Sandy | 2024-12-17 | 2024-12-20 | Tantray Construction
5 | 2024-12-01 | 70/9 | DA+3 | DRY | 2024-12-20 | 2024-12-21 | Tantray Construction | Sk Sil
5 | 2024-12-01 | 6/2 | DA+0 | DFR | 2024-12-18 | 2024-12-23 | Hs Engineering | Jitendra Yadav
5 | 2024-12-01 | 72/0 | DB2+3 | DRY | 2024-12-22 | 2024-12-23 | Meer Const | Sk Sil
5 | 2024-12-01 | 70/6 | DA+3 | DRY | 2024-12-22 | 2024-12-23 | Tantray Construction | Sk Sil
5 | 2024-12-01 | 2/6 | DA+3 | Sandy | 2024-12-12 | 2024-12-24 | Sri Nagana Ray Enterprise | Jitendra Yadav
5 | 2024-12-01 | 71/4 | DA+3 | DRY | 2024-12-24 | 2024-12-25 | Meer Const | Sk Sil
5 | 2024-12-01 | 52/2 | DA+6 | Sandy | 2024-12-24 | 2024-12-25 | Tantray Construction | R T Singh
5 | 2024-12-01 | 70/10 | DA+3 | DRY | 2024-12-24 | 2024-12-25 | Tantray Construction
5 | 2024-12-01 | 2/2 | DA+3 | Sandy | 2024-12-17 | 2024-12-27 | Laxmi Enterprises | Jitendra Yadav
5 | 2024-12-01 | 71/5 | DA+3 | DRY | 2024-12-26 | 2024-12-27 | Meer Const | Sk Sil
5 | 2024-12-01 | 70/11 | DA+3 | DRY | 2024-12-26 | 2024-12-27 | Tantray Construction | Sk Sil
5 | 2024-12-01 | 53/2 | DA+0 | Sandy | 2024-12-25 | 2024-12-29 | Meer Const | R T Singh
5 | 2024-12-01 | 36/0 | DB2+0 | Sandy | 2024-12-21 | 2024-12-30 | Parsuram Sahi | Kuntal Debnath
5 | 2024-12-01 | 71/3 | DA+6 | DRY | 2024-12-29 | 2024-12-30 | Meer Const | Sk Sil
5 | 2024-12-01 | 52/4 | DA+9 | Sandy | 2024-12-27 | 2024-12-30 | Tantray Construction | R T Singh
5 | 2024-12-01 | 10/5 | DA+3 | DRY | 2024-12-25 | 2024-12-31 | Jsr Infrastructure | Jitendra Yadav
5 | 2024-12-01 | 35/4 | DA+0 | DRY | 2024-12-25 | 2024-12-31 | Parsuram Sahi | Kuntal Debnath
5 | 2024-12-01 | 71/0 | DB2+3 | DRY | 2024-12-29 | 2024-12-31 | Tantray Construction | Sk Sil
5 | 2025-01-01 | 22/11 | DA+6 | Sandy | 2024-12-23 | 2025-01-04 | Rbm | Bipin Singh
5 | 2025-01-01 | 71/2 | DA+3 | DRY | 2024-12-31 | 2025-01-04 | Meer Const | Sk Sil
5 | 2025-01-01 | 71/1 | DA+3 | DRY | 2025-01-04 | 2025-01-06 | Meer Const | Sk Sil
5 | 2025-01-01 | 54/3 | DA+6 | Sandy | 2025-01-02 | 2025-01-06 | Tantray Construction | R T Singh
5 | 2025-01-01 | 44/1 | DA+0 | Sandy | 2025-01-02 | 2025-01-06 | Tantray Construction | R T Singh
5 | 2025-01-01 | 44/2 | DA+0 | Sandy | 2025-01-04 | 2025-01-07 | Tantray Construction | R T Singh
5 | 2025-01-01 | 8/9 | DA+3 | DFR | 2025-01-02 | 2025-01-08 | Jsr Infrastructure | Sumit Kumar
5 | 2025-01-01 | 53/1 | DA+9 | Sandy | 2024-12-29 | 2025-01-08 | Meer Const | R T Singh
5 | 2025-01-01 | 70/3 | DA+3 | DRY | 2025-01-07 | 2025-01-09 | Meer Const | Sk Sil
5 | 2025-01-01 | 54/4 | DA+9 | Sandy | 2025-01-06 | 2025-01-09 | Tantray Construction | R T Singh
5 | 2025-01-01 | 45/0 | DC2+0 | Sandy | 2025-01-06 | 2025-01-09 | Nadeem | R T Singh
5 | 2025-01-01 | 44/11 | DA+0 | Sandy | 2025-01-07 | 2025-01-09 | Nadeem | R T Singh
5 | 2025-01-01 | 53/0 | DB2+9 | Sandy | 2025-01-06 | 2025-01-12 | Meer Const | R T Singh
5 | 2025-01-01 | 44/10 | DB1+9 | Sandy | 2025-01-11 | 2025-01-12 | Nadeem | R T Singh
5 | 2025-01-01 | 44/4 | DA+9 | Sandy | 2025-01-08 | 2025-01-12 | Tantray Construction | R T Singh
5 | 2025-01-01 | 70/4 | DA+3 | DRY | 2025-01-12 | 2025-01-13 | Meer Const | Sk Sil
5 | 2025-01-01 | 34/1 | DA+9 | Sandy | 2025-01-08 | 2025-01-14 | Ymk Construction | Kuntal Debnath
5 | 2025-01-01 | 70/5 | DA+3 | DRY | 2025-01-13 | 2025-01-15 | Meer Const | Sk Sil
5 | 2025-01-01 | 53/3 | DA+6 | Sandy | 2025-01-11 | 2025-01-15 | Meer Const | R T Singh
5 | 2025-01-01 | 35/2 | DB1+0 | Sandy | 2025-01-08 | 2025-01-16 | Parsuram Sahi | Kuntal Debnath
5 | 2025-01-01 | 68/0 | DD45+0 | DRY | 2025-01-13 | 2025-01-17 | Bhati Const.
5 | 2025-01-01 | 1A/1 | DA+6 | DFR | 2025-01-11 | 2025-01-18 | Jsr Infrastructure | Sumit Kumar
5 | 2025-01-01 | 53/4 | DA+0 | Sandy | 2025-01-14 | 2025-01-18 | Meer Const | R T Singh
5 | 2025-01-01 | 52/0 | DC2+0 | Sandy | 2025-01-11 | 2025-01-18 | Tantray Construction | R T Singh
5 | 2025-01-01 | 44/5 | DA+9 | Sandy | 2025-01-13 | 2025-01-19 | Tantray Construction | R T Singh
5 | 2025-01-01 | 2/0 | DC1+0 | DRY | 2025-01-04 | 2025-01-20 | Laxmi Enterprises | Sumit Kumar
5 | 2025-01-01 | 44/9 | DA+9 | Sandy | 2025-01-15 | 2025-01-20 | Iqbal | R T Singh
5 | 2025-01-01 | 70/1 | DA+3 | DRY | 2025-01-17 | 2025-01-21 | Meer Const | Sk Sil
5 | 2025-01-01 | 70/2 | DA+3 | DRY | 2025-01-20 | 2025-01-21 | Bhati Const. | Sk Sil
5 | 2025-01-01 | 44/6 | DB1+3 | Sandy | 2025-01-19 | 2025-01-21 | Tantray Construction | R T Singh
5 | 2025-01-01 | 55/2 | DA+0 | WFR | 2025-01-18 | 2025-01-22 | Meer Const | R T Singh
5 | 2025-01-01 | 47/4 | DA+3 | Sandy | 2025-01-19 | 2025-01-23 | Tantray Construction | R T Singh
5 | 2025-01-01 | 50/5 | DA+9 | Sandy | 2025-01-16 | 2025-01-23 | Om Const | R T Singh
5 | 2025-01-01 | 1A/4 | DA+3 | DFR | 2025-01-20 | 2025-01-25 | Naganaray Enterprise | Sumit
5 | 2025-01-01 | 28/6 | DA+6 | Sandy | 2025-01-19 | 2025-01-25 | Vishwakarma Construction | Bipin Kumar
5 | 2025-01-01 | 70/0 | DC1+0 | DRY | 2025-01-20 | 2025-01-25 | Meer Const
5 | 2025-01-01 | 44/7 | DA+9 | Sandy | 2025-01-23 | 2025-01-25 | Iqbal | R T Singh
5 | 2025-01-01 | 34/2 | DA+6 | Sandy | 2025-01-20 | 2025-01-27 | Ymk Construction | Kuntal Debnath
5 | 2025-01-01 | 65/10 | DA+0 | DRY | 2025-01-24 | 2025-01-27 | Bhati Const. | Sk Sil
5 | 2025-01-01 | 57/1 | DA+0 | Sandy | 2025-01-24 | 2025-01-27 | Meer Const | R T Singh
5 | 2025-01-01 | 28/5 | DA+9 | Sandy | 2025-01-22 | 2025-01-28 | Vishwakarma Construction | Bipin Kumar
5 | 2025-01-01 | 35/0 | DB2+6 | Sandy | 2025-01-18 | 2025-01-28 | Parsuram Sahi | Kuntal Debnath
5 | 2025-01-01 | 44/3 | DA+0 | Sandy | 2025-01-24 | 2025-01-28 | Tantray Construction | R T Singh
5 | 2025-01-01 | 1A/3 | DA+0 | DRY | 2025-01-21 | 2025-01-29 | Jsr Infrastructure | Sumit
5 | 2025-01-01 | 55/8 | DA+6 | Sandy | 2025-01-28 | 2025-01-30 | Meer Const | R T Singh
5 | 2025-01-01 | 1A/2 | DA+0 | DRY | 2025-01-26 | 2025-01-31 | Jsr Infrastructure | Sumit
5 | 2025-01-01 | 44/8 | DCT+0 | Sandy | 2025-01-27 | 2025-01-31 | Iqbal | R T Singh
5 | 2025-02-01 | 34/0 | DB2+0 | DRY | 2025-01-25 | 2025-02-01 | Ymk Construction | Kuntal Debnath
5 | 2025-02-01 | 28/8 | DA+3 | Sandy | 2025-01-25 | 2025-02-01 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-02-01 | 47/1 | DA+3 | Sandy | 2025-01-25 | 2025-02-01 | Tantray Construction | R T Singh
5 | 2025-02-01 | 1A/5 | DA+0 | DRY | 2025-01-27 | 2025-02-02 | Jsr Infrastructure | Sumit
5 | 2025-02-01 | 28/7 | DA+3 | Sandy | 2025-01-28 | 2025-02-04 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-02-01 | 33/1 | DA+0 | DRY | 2025-02-01 | 2025-02-07 | Ymk Construction | Kuntal Debnath
5 | 2025-02-01 | 28/4 | DA+0 | Sandy | 2025-02-02 | 2025-02-07 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-02-01 | 1A/6 | DA+0 | Sandy | 2025-01-31 | 2025-02-07 | Jsr Infrastructure | Sumit
5 | 2025-02-01 | 35/3 | DB1+6 | Sandy | 2025-02-01 | 2025-02-09 | Parsuram Sahi | Kuntal Debnath
5 | 2025-02-01 | 45/1 | DA+9 | Sandy | 2025-02-01 | 2025-02-09 | Tantray Construction | R T Singh
5 | 2025-02-01 | 54/5 | DA+9 | Sandy | 2025-02-06 | 2025-02-10 | Meer Const | R T Singh
5 | 2025-02-01 | 32/3 | DA+0 | Sandy | 2025-02-05 | 2025-02-11 | Ymk Construction | Kuntal Debnath
5 | 2025-02-01 | 28/3 | DA+0 | DFR | 2025-02-04 | 2025-02-11 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-02-01 | 32/4 | DA+0 | Sandy | 2025-02-09 | 2025-02-13 | Ymk Construction | Kuntal Debnath
5 | 2025-02-01 | 28/2 | DA+0 | DFR | 2025-02-09 | 2025-02-13 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-02-01 | 32/2 | DA+3 | DRY | 2025-02-09 | 2025-02-13 | Ymk Construction | Kuntal Debnath
5 | 2025-02-01 | 29/0 | DB1+0 | DRY | 2025-02-12 | 2025-02-16 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-02-01 | 55/0 | DB1+6 | Sandy | 2025-02-11 | 2025-02-16 | Meer Const | R T Singh
5 | 2025-02-01 | 44/0 | DB1+3 | Sandy | 2025-02-10 | 2025-02-16 | Om Const | R T Singh
5 | 2025-02-01 | 30/0 | DC1+0 | DRY | 2025-02-15 | 2025-02-20 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-02-01 | 33/0 | DC1+0 | DRY | 2025-02-14 | 2025-02-20 | Ymk Construction | Kuntal Debnath
5 | 2025-02-01 | 1A/0 | DD60+0 | DRY | 2025-02-06 | 2025-02-20 | Jsr Infrastructure | Sumit
5 | 2025-02-01 | 30/1 | DA+0 | Sandy | 2025-02-17 | 2025-02-22 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-02-01 | 43/10 | DA+3 | Sandy | 2025-02-18 | 2025-02-23 | Om Const | R T Singh
5 | 2025-02-01 | 29/4 | DA+6 | DRY | 2025-02-22 | 2025-02-25 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-02-01 | 29/1 | DA+3 | DRY | 2025-02-24 | 2025-02-28 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-02-01 | 55/1 | DA+0 | WFR | 2025-02-21 | 2025-02-28 | Bhati | R T Singh
5 | 2025-03-01 | 35/5 | DA+0 | Sandy | 2025-02-10 | 2025-03-02 | Parsuram Sahi | Kuntal Debnath
5 | 2025-03-01 | 32/1 | DA+3 | Sandy | 2025-02-28 | 2025-03-02 | Ymk | Kuntal Debnath
5 | 2025-03-01 | 30/3 | DA+3 | Sandy | 2025-02-28 | 2025-03-03 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-03-01 | 30/2 | DA+0 | Sandy | 2025-03-01 | 2025-03-06 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-03-01 | 1/0 | DD60+0 | DRY | 2025-02-25 | 2025-03-07 | Jsr Infrastructure | Sumit
5 | 2025-03-01 | 32/0 | DC1+0 | DRY | 2025-03-01 | 2025-03-07 | Ymk | Kuntal Debnath
5 | 2025-03-01 | 29/2 | DA+3 | DRY | 2025-03-03 | 2025-03-08 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-03-01 | 1A/7 | DA+3 | Sandy | 2025-03-01 | 2025-03-08 | Jsr Infrastructure | Sumit
5 | 2025-03-01 | 29/3 | DA+0 | Sandy | 2025-03-05 | 2025-03-10 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-03-01 | 31/2 | DA+0 | DRY | 2025-03-05 | 2025-03-10 | Ymk | Kuntal Debnath
5 | 2025-03-01 | 31/1 | DA+0 | DRY | 2025-03-08 | 2025-03-12 | Ymk | Kuntal Debnath
5 | 2025-03-01 | 2/1 | DA+3 | Sandy | 2025-03-14 | 2025-03-20 | Jsr Infrastructure | Sumit
5 | 2025-03-01 | 34/3 | DA+0 | Sandy | 2025-03-19 | 2025-03-25 | Ymk | Kuntal Debnath
5 | 2025-03-01 | 26/7 | DA+0 | DFR | 2025-03-20 | 2025-03-26 | Jsr Infrastructure | Bipin Kumar
5 | 2025-03-01 | 37/3 | DA+0 | Sandy | 2025-03-22 | 2025-03-30 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-03-01 | 34/4 | DA+0 | Sandy | 2025-03-21 | 2025-03-31 | Ymk | Kuntal Debnath
5 | 2025-03-01 | 57/0 | DD60+25 | Sandy | 2025-03-22 | 2025-03-31 | Bhati | R T Singh
5 | 2025-04-01 | 35/1 | DA+9 | Sandy | 2025-03-31 | 2025-04-06 | Ymk | Kuntal Debnath
5 | 2025-04-01 | 46/0 | DD60+25 | Sandy | 2025-03-25 | 2025-04-09 | Om Const | R T Singh
5 | 2025-04-01 | 38/4 | DA+9 | Sandy | 2025-04-07 | 2025-04-11 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-04-01 | 56/0 | DD60+25 | Sandy | 2025-04-02 | 2025-04-12 | Bhati | R T Singh
5 | 2025-04-01 | 39/0 | DB2+6 | Sandy | 2025-04-12 | 2025-04-15 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-04-01 | 27/3 | DA+3 | DFR | 2025-04-12 | 2025-04-17 | YMK | Kuntal Debnath
5 | 2025-04-01 | 47/0 | DD60+25 | Sandy | 2025-04-05 | 2025-04-17 | Om Const | R T Singh
5 | 2025-04-01 | 4/0 | DD60+6 | DRY | 2025-04-13 | 2025-04-19 | Jsr Infrastructure | Sumit
5 | 2025-04-01 | 38/2 | DA+6 | Sandy | 2025-04-18 | 2025-04-22 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-04-01 | 27/2 | DA+3 | DFR | 2025-04-17 | 2025-04-23 | YMK | Kuntal Debnath
5 | 2025-04-01 | 38/1 | DA+0 | Sandy | 2025-04-21 | 2025-04-23 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-04-01 | 38/0 | DB2+6 | Sandy | 2025-04-24 | 2025-04-26 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-04-01 | 39/1 | DA+0 | Sandy | 2025-04-27 | 2025-04-29 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-05-01 | 40/0 | DC2+0 | Sandy | 2025-04-30 | 2025-05-05 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-05-01 | 40/1 | DA+6 | Sandy | 2025-05-02 | 2025-05-10 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-05-01 | 27/6 | DA+0 | Sandy | 2025-05-07 | 2025-05-12 | YMK | Kuntal Debnath
5 | 2025-05-01 | 1A/8 | DA+0 | Sandy | 2025-04-29 | 2025-05-16 | Jsr Infrastructure | Sumit
5 | 2025-05-01 | 27/4 | DA+3 | DFR | 2025-05-12 | 2025-05-18 | YMK | Kuntal Debnath
5 | 2025-05-01 | 38/3 | DA+9 | Sandy | 2025-05-12 | 2025-05-19 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-05-01 | 42/4 | DA+0 | Sandy | 2025-05-16 | 2025-05-20 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-05-01 | 40/3 | DA+3 | Sandy | 2025-05-18 | 2025-05-24 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-05-01 | 21/9 | DA+3 | DFR | 2025-05-13 | 2025-05-26 | M.R. Choudhary | Vivek Shukla
5 | 2025-05-01 | 27/7 | DB1+0 | DFR | 2025-05-18 | 2025-05-27 | YMK | Kuntal Debnath
5 | 2025-05-01 | 4/3 | DA+0 | DRY | 2025-05-13 | 2025-05-28 | Nyce Service & Security | Sumit
5 | 2025-05-01 | 2/8 | DA+0 | Sandy | 2025-05-26 | 2025-05-30 | Jsr Infrastructure | Sumit
5 | 2025-05-01 | 8/11 | DA+0 | DRY | 2025-05-12 | 2025-05-30 | Bhati Construction | Sumit
5 | 2025-06-01 | 41/1 | DB1+9 | Sandy | 2025-05-21 | 2025-06-02 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-06-01 | 30/4 | DA+3 | DRY | 2025-05-21 | 2025-06-03 | Rabbit bright technology pvt. Ltd. | Kuntal Debnath
5 | 2025-06-01 | 21/7 | DA+3 | DFR | 2025-05-07 | 2025-06-06 | M.R. Choudhary | Vivek Shukla
5 | 2025-06-01 | 19/5 | DA+0 | DRY | 2025-06-01 | 2025-06-06 | Shree Ram Construction | Vivek Shukla
5 | 2025-06-01 | 41/0 | DC1+6 | Sandy | 2025-06-01 | 2025-06-08 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-06-01 | 27/1 | DA+3 | DFR | 2025-05-02 | 2025-06-11 | YMK | Kuntal Debnath
5 | 2025-06-01 | 30/5 | DA+3 | DRY | 2025-05-30 | 2025-06-12 | Rabbit bright technology pvt. Ltd. | Kuntal Debnath
5 | 2025-06-01 | 2/7 | DA+3 | Sandy | 2025-05-30 | 2025-06-13 | Jsr Infrastructure | Sumit
5 | 2025-06-01 | 11/4 | DA+0 | Sandy | 2025-06-08 | 2025-06-13 | BR & Sons | Sumit
5 | 2025-06-01 | 36/2 | DA+0 | Sandy | 2025-06-10 | 2025-06-13 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-06-01 | 36/3 | DA+0 | Sandy | 2025-06-10 | 2025-06-15 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-06-01 | 10/0 | DD60+25 | DFR | 2025-05-14 | 2025-06-18 | Bhati Construction | Sumit
5 | 2025-06-01 | 4/1 | DA+0 | DRY | 2025-04-26 | 2025-06-19 | Jsr Infrastructure | Sumit
5 | 2025-06-01 | 21/5 | DA+6 | DFR | 2025-05-29 | 2025-06-21 | M.R. Choudhary | Vivek Shukla
5 | 2025-06-01 | 36/4 | DA+6 | Sandy | 2025-06-13 | 2025-06-23 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-06-01 | 30/6 | DA+0 | DRY | 2025-06-20 | 2025-06-25 | YMK | Kuntal Debnath
5 | 2025-06-01 | 2/9 | DA+0 | DRY | 2025-06-08 | 2025-06-25 | Jsr Infrastructure | Sumit
5 | 2025-06-01 | 37/0 | DB2+0 | Sandy | 2025-06-23 | 2025-06-28 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-06-01 | 21/4 | DA+3 | Sandy | 2025-06-11 | 2025-06-30 | M.R. Choudhary | Vivek Shukla
5 | 2025-07-01 | 31/0 | DB2+0 | Sandy | 2025-06-24 | 2025-07-01 | YMK | Kuntal Debnath
5 | 2025-07-01 | 4/2 | DA+0 | DRY | 2025-06-23 | 2025-07-01 | Nyce Services | Sumit
5 | 2025-07-01 | 3/0 | DD60+6 | DRY | 2025-05-02 | 2025-07-02 | Jsr Infrastructure | Sumit
5 | 2025-07-01 | 4/4 | DA+0 | DRY | 2025-06-27 | 2025-07-02 | Nice Security & Services | Sumit
5 | 2025-07-01 | 21/3 | DA+6 | Sandy | 2025-06-21 | 2025-07-05 | M.R. Choudhary | Vivek Shukla
5 | 2025-07-01 | 8/12 | DA+0 | DRY | 2025-05-12 | 2025-07-06 | Jsr Infrastructure | Sumit
5 | 2025-07-01 | 8/2 | DA+3 | DRY | 2025-06-17 | 2025-07-08 | Dhakad Enterprises | Sumit
5 | 2025-07-01 | 37/1 | DA+9 | Sandy | 2025-06-28 | 2025-07-09 | Vishwakarma Construction | Kuntal Debnath
5 | 2025-07-01 | 8/1 | DA+3 | DRY | 2025-07-08 | 2025-07-12 | Dhakad Enterprises | Sumit
5 | 2025-07-01 | 20/0 | DB2+0 | Sandy | 2025-07-05 | 2025-07-12 | Vishwakarma Construction | Vivek Shukla
5 | 2025-07-01 | 27/0 | DC1+0 | DFR | 2025-07-05 | 2025-07-13 | YMK | Kuntal Debnath
5 | 2025-07-01 | 37/2 | DA+3 | Sandy | 2025-07-07 | 2025-07-13 | Vishwakarma Construction | Vivek Shukla
5 | 2025-07-01 | 9/0 | DD60+18 | DRY | 2025-07-08 | 2025-07-16 | Jsr Infrastructure | Sumit
5 | 2025-07-01 | 8/5 | DA+3 | DRY | 2025-06-20 | 2025-07-22 | Yash Infra | Sumit
5 | 2025-07-01 | 20/2 | DA+0 | DRY | 2025-07-20 | 2025-07-23 | Vishwakarma Construction | Vivek Shukla
5 | 2025-07-01 | 21/0 | DB2+0 | DRY | 2025-07-21 | 2025-07-26 | Vishwakarma Construction | Vivek Shukla
5 | 2025-07-01 | 26/0 | DB1+0 | DFR | 2025-07-11 | 2025-07-26 | YMK | Shymal Sil
5 | 2025-07-01 | 20/3 | DA+0 | DRY | 2025-07-24 | 2025-07-27 | Vishwakarma Construction | Vivek Shukla
5 | 2025-07-01 | 21/2 | DA+0 | Sandy | 2025-06-22 | 2025-07-29 | Vishwakarma Construction | Vivek Shukla
5 | 2025-07-01 | 8/0 | DB1+0 | DRY | 2025-07-10 | 2025-07-30 | Dhakad Enterprises | Sumit
5 | 2025-07-01 | 8/4 | DA+3 | DRY | 2025-07-23 | 2025-07-31 | Jsr Infrastructure | Sumit
5 | 2025-07-01 | 24/0 | DD45+3 | DRY | 2025-07-20 | 2025-07-31 | YMK | Shymal Sil
5 | 2025-08-01 | 14A/0 | DC1+0 | DRY | 2025-06-17 | 2025-08-02 | BR & Sons | Vivek Shukla
5 | 2025-08-01 | 23/0 | DD45+3 | DRY | 2025-07-31 | 2025-08-06 | YMK | Shymal Sil
5 | 2025-08-01 | 10/1 | DA+0 | DRY | 2025-07-16 | 2025-08-09 | Jsr Infrastructure | Sumit
5 | 2025-08-01 | 11/1 | DA+0 | Sandy | 2025-08-02 | 2025-08-10 | Om Construction_Chandrapal | Sumit
5 | 2025-08-01 | 26/1 | DA+0 | DRY | 2025-08-06 | 2025-08-13 | YMK | Shymal Sil
5 | 2025-08-01 | 11/2 | DA+0 | Sandy | 2025-08-16 | 2025-08-20 | Om Construction_Chandrapal | Sumit
5 | 2025-08-01 | 28/1 | DA+0 | DRY | 2025-06-12 | 2025-08-27 | YMK | Shymal Sil
5 | 2025-08-01 | 10/7 | DA+3 | DRY | 2025-07-14 | 2025-08-28 | Jsr Infrastructure | Sumit
5 | 2025-09-01 | 20/1 | DA+0 | Sandy | 2025-08-21 | 2025-09-05 | Vishwakarma Construction | Vivek Shukla
5 | 2025-09-01 | 6/0 | DB2+9 | DRY | 2025-08-28 | 2025-09-08 | Dhakad Enterprises | Sumit
5 | 2025-09-01 | 5/0 | DB1+9 | DRY | 2025-08-18 | 2025-09-12 | Dhakad Enterprises | Sumit
5 | 2025-09-01 | 10/16 | DA+3 | DRY | 2025-09-06 | 2025-09-13 | Jsr Infrastructure | Sumit
5 | 2025-09-01 | 11/0 | DB1+0 | Sandy | 2025-09-06 | 2025-09-15 | Om Construction_Chandrapal | Sumit
5 | 2025-09-01 | 22/10 | DA+6 | Sandy | 2025-07-21 | 2025-09-14 | Vishwakarma Construction | Vivek Shukla
5 | 2025-09-01 | 10/15 | DA+3 | DRY | 2025-09-15 | 2025-09-16 | Jsr Infrastructure | Sumit
5 | 2025-09-01 | 11/3 | DA+0 | Sandy | 2025-09-15 | 2025-09-22 | Om Construction_Chandrapal | Sumit
5 | 2025-09-01 | 7/0 | DB1+0 | DRY | 2025-09-19 | 2025-09-30 | Dhakad Enterprises | Sumit
5 | 2025-10-01 | 10/10 | DA+3 | Sandy | 2025-10-02 | 2025-10-04 | Jsr Infrastructure | Sumit
5 | 2025-10-01 | 10/23 | DA+0 | Sandy | 2025-09-29 | 2025-10-06 | Om Construction_Chandrapal | Sumit
5 | 2025-10-01 | 21/8 | DA+6 | DRY | 2025-10-03 | 2025-10-11 | Vishwakarma Construction | Vivek Shukla
5 | 2025-10-01 | 10/22 | DA+0 | Sandy | 2025-10-06 | 2025-10-12 | Om Construction_Chandrapal | Sumit
5 | 2025-10-01 | 8/3 | DA+0 | DRY | 2025-10-10 | 2025-10-14 | Jsr Infrastructure | Sumit
5 | 2025-10-01 | 19/4 | DA+0 | DRY | 2025-10-13 | 2025-10-14 | Vishwakarma Construction | Vivek Shukla
5 | 2025-10-01 | 21/6 | DA+3 | DRY | 2025-10-11 | 2025-10-28 | Vishwakarma Construction | Vivek Shukla
5 | 2025-11-01 | 26/8 | DA+6 | DFR | 2025-10-28 | 2025-11-04 | Vishwakarma Construction | Vivek Shukla
5 | 2025-11-01 | 22/0 | DB2+3 | DRY | 2025-10-10 | 2025-11-09 | Vishwakarma Construction | Vivek Shukla
5 | 2025-11-01 | 13/4 | DA+3 | DRY | 2025-06-11 | 2025-11-14 | Vishwakarma Construction | Vivek Shukla
5 | 2026-02-01 | 10/2 | DA+0 | DFR | 2026-02-02 | 2026-02-10 | Jsr Infrastructure | Swarankar
5 | 2026-02-01 | 8/8 | DA+6 | DRY | 2026-02-09 | 2026-02-13 | Jsr Infrastructure | Swarankar
5 | 2026-02-01 | 8/6 | DA+3 | DRY | 2026-02-16 | 2026-02-20 | Jsr Infrastructure | Swarankar
5 | 2026-03-01 | 21/1 | DA+6 | DRY | 2025-10-31 | 2026-03-15 | Vishwakarma Construction | Vivek Shukla

## Earthing (hidden)
Progress Summary'!A1
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line
List of Completed Earthing
Earthing
SL No. | FDN No. | Location No. | Tower Type | Classification | Type of Earthing | End Date | Gang Name | Earthing Completion Month
1 | 2023-10-01 | 36/1 | DA+3 | Sandy | Pipe | 2023-12-30 | Nagana Ray and company | 2023-12-01
2 | 2023-12-01 | 61/3 | DA+6 | DRY | Pipe | 2023-12-18 | Manoj Sharma | 2023-12-01
3 | 2023-12-01 | 27/12 | DA+3 | Sandy | Pipe | 2024-02-26 | Nagana Ray And Company | 2024-02-01
4 | 2023-12-01 | 62/6 | DA+3 | DRY | Pipe | 2024-01-07 | Shakti Construction | 2024-01-01
5 | 2023-12-01 | 59/14 | DA+6 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01 |  | 3.2 | 2nd Section WIP.
6 | 2023-12-01 | 62/7 | DA+3 | DRY | Pipe | 2024-01-09 | Shakti Construction | 2024-01-01
7 | 2023-12-01 | 59/13 | DA+3 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01 | T&P Shifting WIP
8 | 2023-12-01 | 27/10 | DA+3 | DFR | CP | 2023-12-30 | Nagana Ray And Company | 2023-12-01 |  | 2.5
9 | 2023-12-01 | 63/8 | DA+3 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
10 | 2023-12-01 | 59/10 | DA+0 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01
11 | 2023-12-01 | 62/5 | DA+0 | DRY | Pipe | 2024-01-07 | Shakti Construction | 2024-01-01
12 | 2023-12-01 | 59/9 | DA+3 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01
13 | 2023-12-01 | 60/9 | DA+3 | DRY | Pipe | 2024-01-06 | Imran | 2024-01-01
14 | 2023-12-01 | 62/4 | DA+3 | DRY | Pipe | 2023-12-31 | Shakti Construction | 2023-12-01
15 | 2023-12-01 | 59/8 | DB1+3 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01
16 | 2023-12-01 | 26/2 | DA+3 | DFR | CP | 2025-06-23 | A.B. Construction | 2025-06-01
17 | 2023-12-01 | 59/6 | DA+3 | DFR | CP | 2024-01-05 | Om Const | 2024-01-01
18 | 2023-12-01 | 63/6 | DA+3 | DRY | Pipe | 2024-01-12 | Mahadev Eng | 2024-01-01
19 | 2023-12-01 | 60/8 | DA+0 | DRY | Pipe | 2024-01-06 | Imran | 2024-01-01
20 | 2023-12-01 | 27/9 | DA+0 | DFR | CP | 2023-12-30 | Nagana Ray And Company | 2023-12-01
21 | 2023-12-01 | 59/7 | DA+3 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01
22 | 2023-12-01 | 59/5 | DA+3 | DFR | CP | 2024-01-05 | Om Const | 2024-01-01
23 | 2023-12-01 | 62/3 | DA+0 | DRY | Pipe | 2024-01-07 | Shakti Construction | 2024-01-01
24 | 2024-01-01 | 59/12 | DA+6 | DFR | CP | 2024-01-16 | Manoj Sharma | 2024-01-01
25 | 2024-01-01 | 60/7 | DA+3 | DRY | Pipe | 2024-01-06 | Imran | 2024-01-01
26 | 2024-01-01 | 62/2 | DA+3 | DRY | Pipe | 2024-01-07 | Shakti Construction | 2024-01-01
27 | 2024-01-01 | 59/3 | DA+3 | DFR | CP | 2024-02-22 | Om Const | 2024-02-01
28 | 2024-01-01 | 64/0 | DB2+0 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
29 | 2024-01-01 | 57/3 | DA+0 | DRY | Pipe | 2024-02-22 | Om Const | 2024-02-01
30 | 2024-01-01 | 60/5 | DA+3 | DRY | Pipe | 2024-01-16 | Manoj Sharma | 2024-01-01
31 | 2024-01-01 | 62/11 | DA+3 | DRY | Pipe | 2024-01-28 | Shakti Construction | 2024-01-01
32 | 2024-01-01 | 65/2 | DA+0 | DRY | Pipe | 2024-01-12 | Veerteja Enterprises | 2024-01-01
33 | 2024-01-01 | 65/11 | DA+0 | DRY | Pipe | 2024-01-15 | Bhati Const. | 2024-01-01
34 | 2024-01-01 | 60/6 | DA+0 | DRY | Pipe | 2024-01-16 | Manoj Sharma | 2024-01-01
35 | 2024-01-01 | 57/2 | DA+3 | DRY | Pipe | 2024-02-14 | Om Const | 2024-02-01
36 | 2024-01-01 | 62/10 | DA+0 | DFR | CP | 2024-02-22 | Shakti Construction | 2024-02-01
37 | 2024-01-01 | 65/9 | DA+0 | DRY | Pipe | 2024-01-15 | Bhati Const. | 2024-01-01
38 | 2024-01-01 | 57/4 | DA+0 | Sandy | Pipe | 2024-02-14 | Om Const | 2024-02-01
39 | 2024-01-01 | 64/4 | DA+3 | DRY | Pipe | 2024-01-19 | Mahadev Eng | 2024-01-01
40 | 2024-01-01 | 65/3 | DA+3 | DRY | Pipe | 2024-01-20 | Veerteja Enterprises | 2024-01-01
41 | 2024-01-01 | 55/3 | DA+0 | Sandy | Pipe | 2024-02-02 | Imran | 2024-02-01
42 | 2024-01-01 | 60/10 | DA+0 | DFR | CP | 2024-02-02 | Manoj Sharma | 2024-02-01
43 | 2024-01-01 | 62/8 | DA+0 | DFR | CP | 2024-02-21 | Shakti Construction | 2024-02-01
44 | 2024-01-01 | 55/4 | DA+0 | Sandy | Pipe | 2024-01-17 | Imran | 2024-01-01
45 | 2024-01-01 | 57/5 | DA+3 | Sandy | Pipe | 2024-02-14 | Om Const | 2024-02-01
46 | 2024-01-01 | 26/3 | DA+0 | DRY | Pipe | 2025-06-23 | A.B. Construction | 2025-06-01
47 | 2024-01-01 | 64/1 | DA+0 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
48 | 2024-01-01 | 64/5 | DA+3 | DRY | Pipe | 2024-01-25 | Mahadev Eng | 2024-01-01
49 | 2024-01-01 | 65/6 | DA+0 | DRY | Pipe | 2024-02-09 | Bhati Const. | 2024-02-01
50 | 2024-01-01 | 61/0 | DB2+0 | DRY | Pipe | 2024-02-02 | Manoj Sharma | 2024-02-01
51 | 2024-01-01 | 62/9 | DA+3 | DFR | CP | 2024-02-21 | Shakti Construction | 2024-02-01
52 | 2024-01-01 | 65/5 | DA+0 | DRY | Pipe | 2024-02-09 | Bhati Const. | 2024-02-01
53 | 2024-01-01 | 64/2 | DA+3 | DRY | Pipe | 2024-01-25 | Mahadev Eng | 2024-01-01
54 | 2024-01-01 | 57/6 | DA+3 | Sandy | Pipe | 2024-02-22 | Om Const | 2024-02-01
55 | 2024-01-01 | 63/1 | DA+3 | DFR | CP | 2024-01-27 | Shakti Construction | 2024-01-01
56 | 2024-01-01 | 64/9 | DA+3 | DRY | Pipe | 2024-02-20 | Veerteja Enterprises | 2024-02-01
57 | 2024-01-01 | 60/11 | DA+3 | DRY | Pipe | 2024-02-02 | Manoj Sharma | 2024-02-01
58 | 2024-01-01 | 65/4 | DA+0 | DRY | Pipe | 2024-01-25 | Bhati Const. | 2024-01-01
59 | 2024-01-01 | 63/7 | DA+3 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
60 | 2024-01-01 | 55/5 | DA+0 | Sandy | Pipe | 2024-01-29 | Imran | 2024-01-01
61 | 2024-01-01 | 55/6 | DA+0 | Sandy | Pipe | 2024-01-29 | Imran | 2024-01-01
62 | 2024-01-01 | 63/2 | DA+0 | DFR | CP | 2024-01-27 | Shakti Construction | 2024-01-01
63 | 2024-01-01 | 27/8 | DA+0 | DFR | CP | 2024-01-31 | Nagana Ray And Company | 2024-01-01
64 | 2024-01-01 | 61/1 | DA+6 | DFR | CP | 2024-02-02 | Manoj Sharma | 2024-02-01
65 | 2024-01-01 | 55/7 | DA+0 | Sandy | Pipe | 2024-02-02 | Imran | 2024-02-01
66 | 2024-01-01 | 64/3 | DA+0 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
67 | 2024-01-01 | 63/3 | DA+3 | DFR | Pipe | 2024-02-22 | Shakti Construction | 2024-02-01
68 | 2024-01-01 | 64/8 | DA+3 | DRY | Pipe | 2024-02-01 | Veerteja Enterprises | 2024-02-01
69 | 2024-01-01 | 61/2 | DA+6 | DFR | CP | 2024-02-02 | Manoj Sharma | 2024-02-01
70 | 2024-02-01 | 64/7 | DA+3 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
71 | 2024-02-01 | 52/5 | DA+9 | Sandy | Pipe | 2024-02-05 | Imran | 2024-02-01
72 | 2024-02-01 | 63/4 | DA+0 | DRY | Pipe | 2024-02-14 | Shakti Construction | 2024-02-01
73 | 2024-02-01 | 26/4 | DA+6 | Sandy | Pipe | 2024-02-17 | Mehai Construction | 2024-02-01
74 | 2024-02-01 | 67/2 | DA+0 | DRY | Pipe | 2024-02-09 | Bhati Const. | 2024-02-01
75 | 2024-02-01 | 52/6 | DA+6 | Sandy | Pipe | 2024-02-08 | Imran | 2024-02-01
76 | 2024-02-01 | 64/6 | DA+0 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
77 | 2024-02-01 | 63/5 | DA+3 | DFR | CP | 2024-02-15 | Shakti Construction | 2024-02-01
78 | 2024-02-01 | 59/15 | DA+6 | DRY | Pipe | 2024-02-26 | Om Const | 2024-02-01
79 | 2024-02-01 | 61/5 | DA+3 | DRY | Pipe | 2024-02-22 | Manoj Sharma | 2024-02-01
80 | 2024-02-01 | 67/1 | DA+0 | DRY | Pipe | 2024-02-13 | Bhati Const. | 2024-02-01
81 | 2024-02-01 | 64/10 | DA+3 | DRY | Pipe | 2024-02-11 | Veerteja Enterprises | 2024-02-01
82 | 2024-02-01 | 61/6 | DA+3 | DRY | Pipe | 2024-02-22 | Manoj Sharma | 2024-02-01
83 | 2024-02-01 | 52/7 | DA+3 | Sandy | Pipe | 2024-02-13 | Imran | 2024-02-01
84 | 2024-02-01 | 59/16 | DA+9 | Dry | Pipe | 2024-02-26 | Om Const | 2024-02-01
85 | 2024-02-01 | 63/0 | DC1+0 | DFR | CP | 2024-02-15 | Shakti Construction | 2024-02-01
86 | 2024-02-01 | 52/8 | DA+6 | Sandy | Pipe | 2024-02-22 | Imran | 2024-02-01
87 | 2024-02-01 | 61/7 | DA+9 | Dry | Pipe | 2024-02-22 | Manoj Sharma | 2024-02-01
88 | 2024-02-01 | 26/5 | DA+6 | Sandy | Pipe | 2024-02-18 | Mehai Construction | 2024-02-01
89 | 2024-02-01 | 61/9 | DA+0 | Dry | Pipe | 2024-02-22 | Manoj Sharma | 2024-02-01
90 | 2024-02-01 | 60/1 | DA+6 | DRY | Pipe | 2024-02-23 | Om Const | 2024-02-01
91 | 2024-02-01 | 28/0 | DB2+0 | DFR | CP | 2024-02-18 | A.B. Construction | 2024-02-01
92 | 2024-02-01 | 52/10 | DA+9 | Sandy | Pipe | 2024-02-17 | Imran | 2024-02-01
93 | 2024-02-01 | 27/11 | DA+3 | DRY | Pipe | 2024-02-19 | A.B. Construction | 2024-02-01
94 | 2024-02-01 | 49/2 | DA+3 | Sandy | Pipe | 2024-03-08 | Veerteja Enterprises | 2024-03-01
95 | 2024-02-01 | 52/9 | DA+3 | Sandy | Pipe | 2024-02-22 | Imran | 2024-02-01
96 | 2024-02-01 | 61/8 | DA+6 | DRY | Pipe | 2024-02-22 | Manoj Sharma | 2024-02-01
97 | 2024-02-01 | 62/1 | DA+3 | Sandy | Pipe | 2024-02-22 | Shakti Construction | 2024-02-01
98 | 2024-02-01 | 53/5 | DA+3 | Sandy | Pipe | 2024-02-25 | Imran | 2024-02-01
99 | 2024-02-01 | 64/11 | DA+3 | DRY | Pipe | 2024-03-06 | Bhati Const. | 2024-03-01
100 | 2024-02-01 | 60/2 | DA+3 | DFR | CP | 2024-02-26 | Om Const | 2024-02-01
101 | 2024-02-01 | 21/10 | DA+6 | DRY | Pipe | 2024-03-03 | Swarup Enterprises | 2024-03-01
102 | 2024-02-01 | 60/3 | DA+3 | DFR | CP | 2024-03-01 | Manoj Sharma | 2024-03-01
103 | 2024-02-01 | 26/6 | DA+6 | Sandy | Pipe | 2024-03-05 | Mehai Construction | 2024-03-01
104 | 2024-02-01 | 65/0 | DB1+0 | DRY | Pipe | 2024-03-06 | Bhati Const. | 2024-03-01
105 | 2024-02-01 | 60/4 | DA+3 | DFR | CP | 2024-03-01 | Manoj Sharma | 2024-03-01
106 | 2024-03-01 | 22/1 | DA+9 | Sandy | Pipe | 2024-03-03 | Swarup Enterprises | 2024-03-01
107 | 2024-03-01 | 61/10 | DA+9 | DRY | Pipe | 2024-03-12 | Manoj Sharma | 2024-03-01
108 | 2024-03-01 | 65/1 | DA+0 | DRY | Pipe | 2024-03-07 | Bhati Const. | 2024-03-01
109 | 2024-03-01 | 22/6 | DA+0 | Sandy | Pipe | 2024-03-23 | A.B. Construction | 2024-03-01
110 | 2024-03-01 | 62/0 | DB2+0 | DRY | Pipe | 2024-03-12 | Manoj Sharma | 2024-03-01
111 | 2024-03-01 | 61/4 | DA+3 | DRY | Pipe | 2024-03-22 | Manoj Sharma | 2024-03-01
112 | 2024-03-01 | 49/3 | DA+3 | Sandy | Pipe | 2024-03-21 | Veerteja Enterprises | 2024-03-01
113 | 2024-03-01 | 27/5 | DA+0 | DRY | Pipe | 2024-03-18 | Majisa Construction | 2024-03-01
114 | 2024-03-01 | 49/6 | DA+0 | Sandy | Pipe | 2024-04-20 | Shakti Construction | 2024-04-01
115 | 2024-03-01 | 60/0 | DC1+0 | DRY | Pipe | 2024-03-19 | Manoj Sharma | 2024-03-01
116 | 2024-03-01 | 49/4 | DA+3 | Sandy | Pipe | 2024-04-22 | Veerteja Enterprises | 2024-04-01
117 | 2024-03-01 | 49/5 | DA+3 | Sandy | Pipe | 2024-03-21 | Shakti Construction | 2024-03-01
118 | 2024-03-01 | 47/10 | DA+6 | Sandy | Pipe | 2024-03-29 | Bhati Const. | 2024-03-01
119 | 2024-03-01 | 47/9 | DA+3 | Sandy | Pipe | 2024-03-29 | Bhati Const. | 2024-03-01
120 | 2024-03-01 | 47/8 | DA+0 | Sandy | Pipe | 2024-03-29 | Bhati Const. | 2024-03-01
121 | 2024-03-01 | 47/7 | DA+3 | Sandy | Pipe | 2024-04-02 | Bhati Const. | 2024-04-01
122 | 2024-04-01 | 50/9 | DA+0 | Sandy | Pipe | 2024-04-19 | Shakti Construction | 2024-04-01
123 | 2024-04-01 | 48/0 | DC2+0 | Sandy | Pipe | 2024-04-07 | Bhati Const. | 2024-04-01
124 | 2024-04-01 | 50/10 | DA+0 | Sandy | Pipe | 2024-04-19 | Shakti Construction | 2024-04-01
125 | 2024-04-01 | 51/1 | DA+0 | Sandy | Pipe | 2024-04-19 | Shakti Construction | 2024-04-01
126 | 2024-04-01 | 48/1 | DA+9 | Sandy | Pipe | 2024-04-16 | Veerteja Enterprises | 2024-04-01
127 | 2024-04-01 | 50/8 | DA+9 | Sandy | Pipe | 2024-04-20 | Shakti Construction | 2024-04-01
128 | 2024-04-01 | 49/1 | DA+0 | Sandy | Pipe | 2024-04-22 | Veerteja Enterprises | 2024-04-01
129 | 2024-05-01 | 49/0 | DD45+0 | Sandy | Pipe | 2024-05-03 | Veerteja Enterprises | 2024-05-01
130 | 2024-05-01 | 43/6 | DA+3 | Sandy | Pipe | 2024-05-09 | Bande Bharat Group | 2024-05-01
131 | 2024-05-01 | 8/7 | DB1+0 | DRY | Pipe | 2024-05-23 | Mateshwari Const. | 2024-05-01
132 | 2024-05-01 | 50/7 | DA+0 | Sandy | Pipe | 2024-05-31 | Veerteja Enterprises | 2024-05-01
133 | 2024-05-01 | 8/10 | DA+3 | DFR | CP | 2024-05-31 | Mateshwari Const. | 2024-05-01
134 | 2024-05-01 | 50/1 | DA+6 | Sandy | Pipe | 2024-05-31 | Veerteja Enterprises | 2024-05-01
135 | 2024-05-01 | 47/6 | DA+3 | Sandy | Pipe | 2024-06-08 | Bhati Const. | 2024-06-01
136 | 2024-05-01 | 52/3 | DA+9 | Sandy | Pipe | 2024-05-23 | Sb Mehar Const. | 2024-05-01
137 | 2024-05-01 | 47/2 | DA+9 | Sandy | Pipe | 2024-05-28 | Bhati Const. | 2024-05-01
138 | 2024-05-01 | 10/14 | DA+3 | DRY | Pipe | 2024-05-31 | Mateshwari Const. | 2024-05-01
139 | 2024-05-01 | 10/19 | DA+0 | DRY | Pipe | 2024-05-31 | Jai Bhawani Construction | 2024-05-01
140 | 2024-05-01 | 50/4 | DA+9 | Sandy | Pipe | 2024-02-03 | Veerteja Enterprises | 2024-02-01
141 | 2024-05-01 | 51/2 | DA+0 | Sandy | Pipe | 2024-05-31 | Sb Mehar Const. | 2024-05-01
142 | 2024-05-01 | 47/5 | DA+0 | Sandy | Pipe | 2024-06-08 | Bhati Const. | 2024-06-01
143 | 2024-05-01 | 50/2 | DA+9 | Sandy | Pipe | 2024-02-04 | Veerteja Enterprises | 2024-02-01
144 | 2024-06-01 | 10/11 | DA+3 | DRY | Pipe | 2024-06-18 | Mateshwari Const. | 2024-06-01
145 | 2024-06-01 | 10/18 | DA+3 | DFR | CP | 2024-06-30 | Jai Bhawani Construction | 2024-06-01
146 | 2024-06-01 | 10/13 | DA+3 | DRY | Pipe | 2024-06-19 | Mateshwari Const. | 2024-06-01
147 | 2024-06-01 | 47/3 | DA+9 | Sandy | Pipe | 2024-06-08 | Bhati Const. | 2024-06-01
148 | 2024-06-01 | 51/0 | DC2+0 | Sandy | Pipe | 2024-06-11 | Sb Mehar Const. | 2024-06-01
149 | 2024-06-01 | 10/17 | DA+3 | DFR | CP | 2024-06-18 | Jai Bhawani Construction | 2024-06-01
150 | 2024-06-01 | 53/7 | DA+3 | Sandy | Pipe | 2024-07-02 | Bhati Const. | 2024-07-01
151 | 2024-06-01 | 10/8 | DA+3 | DFR | CP | 2024-06-20 | Mateshwari Const. | 2024-06-01
152 | 2024-06-01 | 10/12 | DB1+0 | DRY | Pipe | 2024-07-10 | Mateshwari Const. | 2024-07-01
153 | 2024-07-01 | 15/1 | DA+3 | DRY | Pipe | 2024-07-13 | Om Enterprise | 2024-07-01
154 | 2024-07-01 | 10/20 | DA+3 | DFR | CP | 2024-07-13 | Jai Bhawani Construction | 2024-07-01
155 | 2024-07-01 | 11A/5 | DA+3 | DRY | Pipe | 2024-08-26 | Punia Construction | 2024-08-01
156 | 2024-07-01 | 10/21 | DA+3 | DFR | CP | 2024-08-26 | Jai Bhawani Construction | 2024-08-01
157 | 2024-07-01 | 18/1 | DA+0 | DRY | Pipe | 2024-07-18 | J.P. Infra | 2024-07-01
158 | 2024-07-01 | 15/0 | DC1+0 | DRY | Pipe | 2024-07-16 | Om Enterprise | 2024-07-01
159 | 2024-07-01 | 14A/1 | DA+3 | DRY | Pipe | 2024-07-22 | Majisa Construction | 2024-07-01
160 | 2024-07-01 | 50/0 | DB2+0 | Sandy | Pipe | 2024-08-03 | Veerteja Enterprises | 2024-08-01
161 | 2024-07-01 | 11A/6 | DA+6 | DRY | Pipe | 2024-08-26 | Punia Construction | 2024-08-01
162 | 2024-07-01 | 10/6 | DA+0 | DFR | CP | 2024-09-01 | Jai Bhawani Construction | 2024-09-01
163 | 2024-07-01 | 16/0 | DC1+0 | DRY | Pipe | 2024-07-22 | Majisa Construction | 2024-07-01
164 | 2024-07-01 | 58/0 | DC1+3 | DFR | CP | 2024-07-30 | Bhati Const. | 2024-07-01
165 | 2024-07-01 | 18/0 | DC2+0 | DRY | Pipe | 2024-07-31 | J.P. Infra | 2024-07-01
166 | 2024-07-01 | 11/5 | DA+0 | DFR | CP | 2024-08-26 | Mci | 2024-08-01
167 | 2024-08-01 | 10/3 | DA+0 | DFR | CP | 2024-08-07 | Jai Bhawani Construction | 2024-08-01
168 | 2024-08-01 | 11A/7 | DA+9 | Sandy | Pipe | 2024-09-08 | Punia Construction | 2024-09-01
169 | 2024-08-01 | 18/2 | DA+0 | DRY | Pipe | 2024-09-07 | Vibe Infra | 2024-09-01
170 | 2024-08-01 | 17/3 | DA+0 | DRY | Pipe | 2024-09-07 | J.P. Infra | 2024-09-01
171 | 2024-08-01 | 57/7 | DA+3 | DFR | CP | 2024-08-12 | Bhati Const. | 2024-08-01
172 | 2024-08-01 | 16/3 | DA+3 | DRY | Pipe | 2024-09-07 | Majisa Construction | 2024-09-01
173 | 2024-08-01 | 43/9 | DA+9 | Sandy | Pipe | 2024-08-27 | N.R. Enterprises | 2024-08-01
174 | 2024-08-01 | 17/5 | DA+3 | DRY | Pipe | 2024-09-07 | J.P. Infra | 2024-09-01
175 | 2024-08-01 | 11A/2 | DA+0 | DRY | Pipe | 2024-08-18 | R.K. Construction | 2024-08-01
176 | 2024-08-01 | 16/4 | DA+0 | DRY | Pipe | 2024-08-24 | Om Enterprise | 2024-08-01
177 | 2024-08-01 | 18/3 | DA+0 | DRY | Pipe | 2024-09-07 | Vibe Infra | 2024-09-01
178 | 2024-08-01 | 17/4 | DA+3 | DRY | Pipe | 2024-09-05 | J.P. Infra | 2024-09-01
179 | 2024-08-01 | 10/9 | DA+0 | DRY | Pipe | 2024-08-31 | A.B. Construction | 2024-08-01
180 | 2024-08-01 | 11A/8 | DA+6 | Sandy | Pipe | 2024-09-08 | Punia Construction | 2024-09-01
181 | 2024-08-01 | 11A/9 | DA+3 | DRY | Pipe | 2024-09-08 | Punia Construction | 2024-09-01
182 | 2024-08-01 | 43/8 | DA+9 | Sandy | Pipe | 2024-08-27 | N.R. Enterprises | 2024-08-01
183 | 2024-08-01 | 18/4 | DA+0 | DRY | Pipe | 2024-09-03 | Vibe Infra | 2024-09-01
184 | 2024-08-01 | 59/2 | DA+3 | DFR | CP | 2024-08-23 | Bhati Const. | 2024-08-01
185 | 2024-08-01 | 16/2 | DA+0 | DRY | Pipe | 2024-08-31 | Om Enterprise | 2024-08-01
186 | 2024-08-01 | 11A/0 | DB1+0 | DRY | Pipe | 2024-08-26 | Mci | 2024-08-01
187 | 2024-08-01 | 50/6 | DA+9 | Sandy | Pipe | 2024-09-29 | Kalpana Const. | 2024-09-01
188 | 2024-08-01 | 53/8 | DA+3 | Sandy | Pipe | 2024-09-03 | Bhati Const. | 2024-09-01
189 | 2024-08-01 | 17/1 | DA+3 | DRY | Pipe | 2024-08-30 | J.P. Infra | 2024-08-01
190 | 2024-08-01 | 43/7 | DA+3 | Sandy | Pipe | 2024-08-30 | N.R. Enterprises | 2024-08-01
191 | 2024-08-01 | 16/5 | DA+3 | DRY | Pipe | 2024-08-31 | Majisa Construction | 2024-08-01
192 | 2024-08-01 | 19/0 | DC2+0 | DRY | Pipe | 2024-08-31 | Vibe Infra | 2024-08-01
193 | 2024-09-01 | 11A/1 | DA+3 | DRY | Pipe | 2024-09-01 | Mci | 2024-09-01
194 | 2024-09-01 | 19/1 | DA+0 | DRY | Pipe | 2024-09-04 | Vibe Infra | 2024-09-01
195 | 2024-09-01 | 17/2 | DA+6 | DRY | Pipe | 2024-09-04 | J.P. Infra | 2024-09-01
196 | 2024-09-01 | 13/2 | DA+3 | DRY | Pipe | 2024-09-30 | Punia Construction | 2024-09-01
197 | 2024-09-01 | 43/5 | DA+3 | DRY | Pipe | 2024-09-06 | N.R. Enterprises | 2024-09-01
198 | 2024-09-01 | 53/6 | DA+6 | Sandy | Pipe | 2024-09-13 | Bhati Const. | 2024-09-01
199 | 2024-09-01 | 16/1 | DA+0 | DRY | Pipe | 2024-09-10 | Sidhi Vinayak | 2024-09-01
200 | 2024-09-01 | 11A/4 | DA+3 | DRY | Pipe | 2024-09-30 | Punia Construction | 2024-09-01
201 | 2024-09-01 | 54/1 | DA+3 | Sandy | Pipe | 2024-09-14 | Bhati Const. | 2024-09-01
202 | 2024-09-01 | 50/3 | DA+6 | Sandy | Pipe | 2024-09-29 | Kalpana Const. | 2024-09-01
203 | 2024-09-01 | 73/0 | DB2+0 | DRY | Pipe | 2024-09-15 | Shree Shyam Const. | 2024-09-01
204 | 2024-09-01 | 73/9 | DA+0 | DRY | Pipe | 2024-09-19 | Shakti Construction | 2024-09-01
205 | 2024-09-01 | 73/2 | DA+0 | DRY | Pipe | 2024-09-16 | Shree Shyam Const. | 2024-09-01
206 | 2024-09-01 | 25/0 | DC1+6 | DRY | Pipe | 2024-09-26 | J.P. Infra | 2024-09-01
207 | 2024-09-01 | 54/2 | DA+3 | Sandy | Pipe | 2024-09-14 | Bhati Const. | 2024-09-01
208 | 2024-09-01 | 14A/2 | DA+0 | DRY | Pipe | 2024-09-30 | Sidhi Vinayak | 2024-09-01
209 | 2024-09-01 | 10/4 | DA+3 | DFR | CP | 2024-09-30 | A.B. Construction | 2024-09-01
210 | 2024-09-01 | 73/1 | DA+0 | DRY | Pipe | 2024-09-19 | Shree Shyam Const. | 2024-09-01
211 | 2024-09-01 | 14/0 | DC2+0 | Sandy | Pipe | 2024-09-26 | Om Enterprise | 2024-09-01
212 | 2024-09-01 | 11A/3 | DA+3 | DRY | Pipe | 2024-09-23 | R.K. Construction | 2024-09-01
213 | 2024-09-01 | 73/6 | DA+0 | DRY | Pipe | 2024-09-22 | Shree Shyam Const. | 2024-09-01
214 | 2024-09-01 | 42/3 | DA+0 | Sandy | Pipe | 2024-09-22 | Mahadev Construction | 2024-09-01
215 | 2024-09-01 | 69/1 | DA+3 | DRY | Pipe | 2024-09-27 | Bhati Const. | 2024-09-01
216 | 2024-09-01 | 25/4 | DA+0 | Sandy | Pipe | 2024-09-30 | J.P. Infra | 2024-09-01
217 | 2024-09-01 | 73/5 | DA+0 | DRY | Pipe | 2024-10-07 | Shree Shyam Const. | 2024-10-01
218 | 2024-09-01 | 43/4 | DA+3 | Sandy | Pipe | 2024-09-30 | N.R. Enterprises | 2024-09-01
219 | 2024-09-01 | 13/1 | DA+9 | DRY | Pipe | 2024-09-30 | Punia Construction | 2024-09-01
220 | 2024-09-01 | 40/2 | DA+3 | Sandy | Pipe | 2024-09-30 | D.R. Construction | 2024-09-01
221 | 2024-09-01 | 73/8 | DA+3 | DRY | Pipe | 2024-10-07 | Shakti Construction | 2024-10-01
222 | 2024-09-01 | 59/1 | DA+3 | DRY | Pipe | 2024-10-01 | Bhati Const. | 2024-10-01
223 | 2024-09-01 | 19/2 | DA+0 | DRY | Pipe | 2024-09-30 | Vibe Infra | 2024-09-01
224 | 2024-09-01 | 72/2 | DA+0 | DRY | Pipe | 2024-10-07 | Shree Shyam Const. | 2024-10-01
225 | 2024-09-01 | 17/0 | DB2+3 | DRY | Pipe | 2024-09-30 | Om Enterprise | 2024-09-01
226 | 2024-09-01 | 66/0 | DC2+6 | DRY | Pipe | 2024-09-27 | Bhati Const. | 2024-09-01
227 | 2024-09-01 | 59/11 | DA+6 | DFR | CP | 2024-09-28 | Mahadev Eng | 2024-09-01
228 | 2024-09-01 | 19/3 | DA+0 | DRY | Pipe | 2024-10-14 | Vibe Infra | 2024-10-01
229 | 2024-09-01 | 43/3 | DA+0 | DRY | Pipe | 2024-09-30 | Parsuram Sai | 2024-09-01
230 | 2024-09-01 | 73/3 | DA+0 | DRY | Pipe | 2024-10-07 | Awadh Const. | 2024-10-01
231 | 2024-10-01 | 73/7 | DA+0 | DRY | Pipe | 2024-10-07 | Shakti Construction | 2024-10-01
232 | 2024-10-01 | 59/0 | DC2+0 | DRY | Pipe | 2024-10-05 | Bhati Const. | 2024-10-01
233 | 2024-10-01 | 67/0 | DC1+9 | DRY | Pipe | 2024-10-10 | Bhati Const. | 2024-10-01
234 | 2024-10-01 | 42/5 | DA+9 | Sandy | Pipe | 2024-10-28 | Mahadev Construction | 2024-10-01
235 | 2024-10-01 | 43/0 | DB1+0 | Sandy | Pipe | 2024-10-09 | N.R. Enterprises | 2024-10-01
236 | 2024-10-01 | 25/3 | DA+0 | Sandy | Pipe | 2024-10-08 | J.P. Infra | 2024-10-01
237 | 2024-10-01 | 69/0 | DB2+0 | DFR | CP | 2024-10-16 | Bhati Const. | 2024-10-01
238 | 2024-10-01 | 73/4 | DA+0 | DRY | Pipe | 2024-10-10 | Shree Shyam Const. | 2024-10-01
239 | 2024-10-01 | 22/13 | DA+6 | Sandy | Pipe | 2024-12-09 | Rbm | 2024-12-01
240 | 2024-10-01 | 74/0 | DB2+0 | Sandy | Pipe | 2024-10-16 | Shakti Construction | 2024-10-01
241 | 2024-10-01 | 25/1 | DA+3 | DRY | Pipe | 2024-12-17 | J.P. Infra | 2024-12-01
242 | 2024-10-01 | 43/2 | DA+0 | Sandy | Pipe | 2024-12-21 | Parsuram Sai | 2024-12-01
243 | 2024-10-01 | 72/3 | DA+3 | DRY | Pipe | 2024-10-18 | Shree Shyam Const. | 2024-10-01
244 | 2024-10-01 | 43/11 | DA+3 | Sandy | Pipe | 2024-12-17 | Jitendra Enterprises | 2024-12-01
245 | 2024-10-01 | 13/0 | DD60+3 | DRY | Pipe | 2025-01-12 | R.K. Construction | 2025-01-01
246 | 2024-10-01 | 71/7 | DA+3 | DRY | Pipe | 2024-10-22 | Shree Shyam Const. | 2024-10-01
247 | 2024-10-01 | 59/4 | DA+3 | DFR | CP | 2024-10-23 | Bhati Const. | 2024-10-01
248 | 2024-10-01 | 22/12 | DA+3 | Sandy | Pipe | 2024-12-09 | Rbm | 2024-12-01
249 | 2024-10-01 | 42/1 | DA+6 | Sandy | Pipe | 2024-12-18 | N.R. Enterprises | 2024-12-01
250 | 2024-10-01 | 71/6 | DA+0 | DRY | Pipe | 2024-10-22 | Shree Shyam Const. | 2024-10-01
251 | 2024-10-01 | 49/7 | DA+0 | Sandy | Pipe | 2024-10-23 | Kalpana Const. | 2024-10-01
252 | 2024-10-01 | 25/2 | DA+0 | DRY | Pipe | 2024-12-17 | J.P. Infra | 2024-12-01
252 | 2024-10-01 | 13/3 | DA+3 | Sandy | Pipe |  | Punia Construction
253 | 2024-10-01 | 22/7 | DA+0 | Sandy | Pipe | 2024-12-09 | Rbm | 2024-12-01
254 | 2024-10-01 | 22/3 | DA+9 | Sandy | Pipe | 2024-12-09 | J.P. Infra | 2024-12-01
255 | 2024-10-01 | 43/1 | DA+3 | Sandy | Pipe | 2024-12-21 | Parsuram Sai | 2024-12-01
256 | 2024-11-01 | 42/6 | DA+0 | Sandy | Pipe | 2024-12-04 | D.R. Construction | 2024-12-01
257 | 2024-11-01 | 2/4 | DA+3 | Sandy | Pipe | 2024-11-17 | Laxmi Enterprises | 2024-11-01
258 | 2024-11-01 | 42/2 | DA+6 | Sandy | Pipe | 2024-12-01 | D.R. Construction | 2024-12-01
259 | 2024-11-01 | 22/8 | DB1+0 | Sandy | Pipe | 2024-12-09 | Rbm | 2024-12-01
260 | 2024-11-01 | 22/2 | DA+6 | Sandy | Pipe | 2024-12-09 | J.P. Infra | 2024-12-01
261 | 2024-11-01 | 54/0 | DB1+6 | Sandy | Pipe | 2024-11-21 | Bhati Const. | 2024-11-01
262 | 2024-11-01 | 65/8 | DA+0 | DRY | Pipe | 2024-12-06 | Bhati Const. | 2024-12-01
263 | 2024-11-01 | 42/0 | DC1+0 | Sandy | Pipe | 2024-12-04 | D.R. Construction | 2024-12-01
264 | 2024-11-01 | 65/7 | DA+0 | DRY | Pipe | 2024-12-06 | Bhati Const. | 2024-12-01
265 | 2024-12-01 | 2/3 | DA+3 | Sandy | Pipe | 2024-12-13 | Laxmi Enterprise | 2024-12-01
266 | 2024-12-01 | 22/4 | DA+9 | Sandy | Pipe | 2024-12-09 | Jp Infra | 2024-12-01
267 | 2024-12-01 | 6/1 | DA+0 | DFR | CP | 2024-12-19 | H.S. Engineering | 2024-12-01
268 | 2024-12-01 | 12/0 | DD60+0 | DRY | Pipe | 2025-01-04 | Vibe Infra Power | 2025-01-01
269 | 2024-12-01 | 22/5 | DA+9 | DRY | Pipe | 2024-12-21 | S.D. Infra | 2024-12-01
270 | 2024-12-01 | 41/2 | DA+0 | Sandy | Pipe | 2024-12-16 | D.R. Construction | 2024-12-01
271 | 2024-12-01 | 2/5 | DA+3 | Sandy | Pipe | 2024-12-28 | Sri Nagana Ray Enterprise | 2024-12-01
272 | 2024-12-01 | 22/9 | DA+6 | Sandy | Pipe | 2025-01-06 | Rbm | 2025-01-01
273 | 2024-12-01 | 70/8 | DA+3 | DRY | Pipe | 2025-02-01 | Tantray Construction | 2025-02-01
274 | 2024-12-01 | 72/1 | DA+3 | DRY | Pipe | 2025-02-01 | Meer Const | 2025-02-01
275 | 2024-12-01 | 70/7 | DA+3 | DRY | Pipe | 2025-02-01 | Tantray Construction | 2025-02-01
276 | 2024-12-01 | 71/8 | DA+3 | DRY | Pipe | 2025-02-01 | Meer Const | 2025-02-01
277 | 2024-12-01 | 52/1 | DA+6 | Sandy | Pipe | 2025-02-17 | Tantray Construction | 2025-02-01
278 | 2024-12-01 | 70/9 | DA+3 | DRY | Pipe | 2025-02-01 | Tantray Construction | 2025-02-01
279 | 2024-12-01 | 6/2 | DA+0 | DFR | CP | 2025-01-05 | Hs Engineering | 2025-01-01
280 | 2024-12-01 | 72/0 | DB2+3 | DRY | Pipe | 2025-01-28 | Meer Const | 2025-01-01
281 | 2024-12-01 | 70/6 | DA+3 | DRY | Pipe | 2025-01-27 | Tantray Construction | 2025-01-01
282 | 2024-12-01 | 2/6 | DA+3 | Sandy | Pipe | 2025-01-06 | Sri Nagana Ray Enterprise | 2025-01-01
283 | 2024-12-01 | 71/4 | DA+3 | DRY | Pipe | 2025-01-28 | Meer Const | 2025-01-01
284 | 2024-12-01 | 52/2 | DA+6 | Sandy | Pipe | 2025-02-17 | Tantray Construction | 2025-02-01
285 | 2024-12-01 | 70/10 | DA+3 | DRY | Pipe | 2025-02-01 | Tantray Construction | 2025-02-01
286 | 2024-12-01 | 2/2 | DA+3 | Sandy | Pipe | 2025-01-06 | Laxmi Enterprises | 2025-01-01
287 | 2024-12-01 | 71/5 | DA+3 | DRY | Pipe | 2025-02-01 | Meer Const | 2025-02-01
288 | 2024-12-01 | 70/11 | DA+3 | DRY | Pipe | 2025-03-29 | Tantray Construction | 2025-03-01
289 | 2024-12-01 | 53/2 | DA+0 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
290 | 2024-12-01 | 36/0 | DB2+0 | Sandy | Pipe | 2024-12-30 | Parsuram Sahi | 2024-12-01
291 | 2024-12-01 | 71/3 | DA+6 | DRY | Pipe | 2025-01-28 | Meer Const | 2025-01-01
292 | 2024-12-01 | 52/4 | DA+9 | Sandy | Pipe | 2025-02-17 | Tantray Construction | 2025-02-01
293 | 2024-12-01 | 10/5 | DA+3 | DRY | Pipe | 2024-12-20 | Jsr Infrastructure | 2024-12-01
294 | 2024-12-01 | 35/4 | DA+0 | DRY | Pipe | 2025-01-03 | Parsuram Sahi | 2025-01-01
295 | 2024-12-01 | 71/0 | DB2+3 | DRY | Pipe | 2025-01-27 | Tantray Construction | 2025-01-01
296 | 2025-01-01 | 22/11 | DA+6 | Sandy | Pipe | 2025-01-07 | Rbm | 2025-01-01
297 | 2025-01-01 | 71/2 | DA+3 | DRY | Pipe | 2025-01-27 | Meer Const | 2025-01-01
298 | 2025-01-01 | 71/1 | DA+3 | DRY | Pipe | 2025-01-27 | Meer Const | 2025-01-01
299 | 2025-01-01 | 54/3 | DA+6 | Sandy | Pipe | 2025-01-07 | Tantray Construction | 2025-01-01
300 | 2025-01-01 | 44/1 | DA+0 | Sandy | Pipe | 2025-03-16 | Tantray Construction | 2025-03-01
301 | 2025-01-01 | 44/2 | DA+0 | Sandy | Pipe | 2025-03-16 | Tantray Construction | 2025-03-01
302 | 2025-01-01 | 8/9 | DA+3 | DFR | CP | 2025-01-09 | Jsr Infrastructure | 2025-01-01
303 | 2025-01-01 | 53/1 | DA+9 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
304 | 2025-01-01 | 70/3 | DA+3 | DRY | Pipe | 2025-01-25 | Meer Const | 2025-01-01
305 | 2025-01-01 | 54/4 | DA+9 | Sandy | Pipe | 2025-01-10 | Tantray Construction | 2025-01-01
306 | 2025-01-01 | 45/0 | DC2+0 | Sandy | Pipe | 2025-02-26 | Nadeem | 2025-02-01
307 | 2025-01-01 | 44/11 | DA+0 | Sandy | Pipe | 2025-02-27 | Nadeem | 2025-02-01
308 | 2025-01-01 | 53/0 | DB2+9 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
309 | 2025-01-01 | 44/10 | DB1+9 | Sandy | Pipe | 2025-02-27 | Nadeem | 2025-02-01
310 | 2025-01-01 | 44/4 | DA+9 | Sandy | Pipe | 2025-02-28 | Tantray Construction | 2025-02-01
311 | 2025-01-01 | 70/4 | DA+3 | DRY | Pipe | 2025-01-25 | Meer Const | 2025-01-01
312 | 2025-01-01 | 34/1 | DA+9 | Sandy | Pipe | 2025-01-16 | Ymk Construction | 2025-01-01
313 | 2025-01-01 | 70/5 | DA+3 | DRY | Pipe | 2025-01-27 | Meer Const | 2025-01-01
314 | 2025-01-01 | 53/3 | DA+6 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
315 | 2025-01-01 | 35/2 | DB1+0 | Sandy | Pipe | 2025-01-19 | Parsuram Sahi | 2025-01-01
316 | 2025-01-01 | 68/0 | DD45+0 | DRY | Pipe | 2025-02-19 | Bhati Const. | 2025-02-01
317 | 2025-01-01 | 1A/1 | DA+6 | DFR | CP | 2025-01-21 | Jsr Infrastructure | 2025-01-01
318 | 2025-01-01 | 53/4 | DA+0 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
319 | 2025-01-01 | 52/0 | DC2+0 | Sandy | Pipe | 2025-02-17 | Tantray Construction | 2025-02-01
320 | 2025-01-01 | 44/5 | DA+9 | Sandy | Pipe | 2025-02-28 | Tantray Construction | 2025-02-01
321 | 2025-01-01 | 2/0 | DC1+0 | DRY | Pipe | 2025-01-21 | Laxmi Enterprises | 2025-01-01
322 | 2025-01-01 | 44/9 | DA+9 | Sandy | Pipe | 2025-02-27 | Iqbal | 2025-02-01
323 | 2025-01-01 | 70/1 | DA+3 | DRY | Pipe | 2025-01-25 | Meer Const | 2025-01-01
324 | 2025-01-01 | 70/2 | DA+3 | DRY | Pipe | 2025-02-19 | Bhati Const. | 2025-02-01
325 | 2025-01-01 | 44/6 | DB1+3 | Sandy | Pipe | 2025-02-28 | Tantray Construction | 2025-02-01
326 | 2025-01-01 | 55/2 | DA+0 | WFR | Pipe | 2025-02-07 | Meer Const | 2025-02-01
327 | 2025-01-01 | 47/4 | DA+3 | Sandy | Pipe | 2025-01-29 | Tantray Construction | 2025-01-01
328 | 2025-01-01 | 50/5 | DA+9 | Sandy | Pipe | 2025-01-23 | Om Const | 2025-01-01
329 | 2025-01-01 | 1A/4 | DA+3 | DFR | CP | 2025-01-28 | Naganaray Enterprise | 2025-01-01
330 | 2025-01-01 | 28/6 | DA+6 | Sandy | Pipe | 2025-01-29 | Vishwakarma Construction | 2025-01-01
331 | 2025-01-01 | 70/0 | DC1+0 | DRY | Pipe | 2025-01-25 | Meer Const | 2025-01-01
332 | 2025-01-01 | 44/7 | DA+9 | Sandy | Pipe | 2025-02-18 | Iqbal | 2025-02-01
333 | 2025-01-01 | 34/2 | DA+6 | Sandy | Pipe | 2025-01-27 | Ymk Construction | 2025-01-01
334 | 2025-01-01 | 65/10 | DA+0 | DRY | Pipe | 2025-02-19 | Bhati Const. | 2025-02-01
335 | 2025-01-01 | 57/1 | DA+0 | Sandy | Pipe | 2025-01-29 | Meer Const | 2025-01-01
336 | 2025-01-01 | 28/5 | DA+9 | Sandy | Pipe | 2025-01-31 | Vishwakarma Construction | 2025-01-01
337 | 2025-01-01 | 35/0 | DB2+6 | Sandy | Pipe | 2025-01-29 | Parsuram Sahi | 2025-01-01
338 | 2025-01-01 | 44/3 | DA+0 | Sandy | Pipe | 2025-02-18 | Tantray Construction | 2025-02-01
339 | 2025-01-01 | 1A/3 | DA+0 | DRY | Pipe | 2025-01-31 | Jsr Infrastructure | 2025-01-01
340 | 2025-01-01 | 55/8 | DA+6 | Sandy | Pipe | 2025-02-03 | Meer Const | 2025-02-01
341 | 2025-01-01 | 1A/2 | DA+0 | DRY | Pipe | 2025-02-03 | Jsr Infrastructure | 2025-02-01
342 | 2025-01-01 | 44/8 | DCT+0 | Sandy | Pipe | 2025-02-28 | Iqbal | 2025-02-01
343 | 2025-02-01 | 34/0 | DB2+0 | DRY | Pipe | 2025-02-04 | Ymk Construction | 2025-02-01
344 | 2025-02-01 | 28/8 | DA+3 | Sandy | Pipe | 2025-02-04 | Vishwakarma Construction | 2025-02-01
345 | 2025-02-01 | 47/1 | DA+3 | Sandy | Pipe | 2025-01-29 | Tantray Construction | 2025-01-01
346 | 2025-02-01 | 1A/5 | DA+0 | DRY | Pipe | 2025-02-05 | Jsr Infrastructure | 2025-02-01
347 | 2025-02-01 | 28/7 | DA+3 | Sandy | Pipe | 2025-02-07 | Vishwakarma Construction | 2025-02-01
348 | 2025-02-01 | 33/1 | DA+0 | DRY | Pipe | 2025-02-10 | Ymk Construction | 2025-02-01
349 | 2025-02-01 | 28/4 | DA+0 | Sandy | Pipe | 2025-02-10 | Vishwakarma Construction | 2025-02-01
350 | 2025-02-01 | 1A/6 | DA+0 | Sandy | Pipe | 2025-02-10 | Jsr Infrastructure | 2025-02-01
351 | 2025-02-01 | 35/3 | DB1+6 | Sandy | Pipe | 2025-02-13 | Parsuram Sahi | 2025-02-01
352 | 2025-02-01 | 45/1 | DA+9 | Sandy | Pipe | 2025-02-26 | Tantray Construction | 2025-02-01
353 | 2025-02-01 | 54/5 | DA+9 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
354 | 2025-02-01 | 32/3 | DA+0 | Sandy | Pipe | 2025-02-14 | Ymk Construction | 2025-02-01
355 | 2025-02-01 | 28/3 | DA+0 | DFR | CP | 2025-02-14 | Vishwakarma Construction | 2025-02-01
356 | 2025-02-01 | 32/4 | DA+0 | Sandy | Pipe | 2025-02-16 | Ymk Construction | 2025-02-01
357 | 2025-02-01 | 28/2 | DA+0 | DFR | CP | 2025-02-16 | Vishwakarma Construction | 2025-02-01
358 | 2025-02-01 | 32/2 | DA+3 | DRY | Pipe | 2025-03-04 | Ymk Construction | 2025-03-01
359 | 2025-02-01 | 29/0 | DB1+0 | DRY | Pipe | 2025-02-20 | Vishwakarma Construction | 2025-02-01
360 | 2025-02-01 | 55/0 | DB1+6 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
361 | 2025-02-01 | 44/0 | DB1+3 | Sandy | Pipe | 2025-03-16 | Om Const | 2025-03-01
362 | 2025-02-01 | 30/0 | DC1+0 | DRY | Pipe | 2025-02-23 | Vishwakarma Construction | 2025-02-01
363 | 2025-02-01 | 33/0 | DC1+0 | DRY | Pipe | 2025-02-24 | Ymk Construction | 2025-02-01
364 | 2025-02-01 | 1A/0 | DD60+0 | DRY | Pipe | 2025-02-24 | Jsr Infrastructure | 2025-02-01
365 | 2025-02-01 | 30/1 | DA+0 | Sandy | Pipe | 2025-02-25 | Vishwakarma Construction | 2025-02-01
366 | 2025-02-01 | 43/10 | DA+3 | Sandy | Pipe | 2025-03-16 | Om Const | 2025-03-01
367 | 2025-02-01 | 29/4 | DA+6 | DRY | Pipe | 2025-03-01 | Vishwakarma Construction | 2025-03-01
368 | 2025-02-01 | 29/1 | DA+3 | DRY | Pipe | 2025-03-03 | Vishwakarma Construction | 2025-03-01
369 | 2025-02-01 | 55/1 | DA+0 | WFR | Pipe | 2025-03-02 | Bhati | 2025-03-01
370 | 2025-03-01 | 35/5 | DA+0 | Sandy | Pipe | 2025-03-06 | Parsuram Sahi | 2025-03-01
371 | 2025-03-01 | 32/1 | DA+3 | Sandy | Pipe | 2025-03-06 | Ymk | 2025-03-01
372 | 2025-03-01 | 30/3 | DA+3 | Sandy | Pipe | 2025-03-06 | Vishwakarma Construction | 2025-03-01
373 | 2025-03-01 | 30/2 | DA+0 | Sandy | Pipe | 2025-03-10 | Vishwakarma Construction | 2025-03-01
374 | 2025-03-01 | 1/0 | DD60+0 | DRY | Pipe | 2025-02-24 | Jsr Infrastructure | 2025-02-01
375 | 2025-03-01 | 32/0 | DC1+0 | DRY | Pipe | 2025-03-11 | Ymk | 2025-03-01
376 | 2025-03-01 | 29/2 | DA+3 | DRY | Pipe | 2025-03-12 | Vishwakarma Construction | 2025-03-01
377 | 2025-03-01 | 1A/7 | DA+3 | Sandy | Pipe | 2025-03-11 | Jsr Infrastructure | 2025-03-01
378 | 2025-03-01 | 29/3 | DA+0 | Sandy | Pipe | 2025-03-14 | Vishwakarma Construction | 2025-03-01
379 | 2025-03-01 | 31/2 | DA+0 | DRY | Pipe | 2025-03-14 | Ymk | 2025-03-01
380 | 2025-03-01 | 31/1 | DA+0 | DRY | Pipe | 2025-03-15 | Ymk | 2025-03-01
381 | 2025-03-01 | 2/1 | DA+3 | Sandy | Pipe | 2025-03-21 | Jsr Infrastructure | 2025-03-01
382 | 2025-03-01 | 34/3 | DA+0 | Sandy | Pipe | 2025-03-28 | Ymk | 2025-03-01
383 | 2025-03-01 | 26/7 | DA+0 | DFR | CP | 2025-03-28 | Jsr Infrastructure | 2025-03-01
384 | 2025-03-01 | 37/3 | DA+0 | Sandy | Pipe | 2025-04-03 | Vishwakarma Construction | 2025-04-01
385 | 2025-03-01 | 34/4 | DA+0 | Sandy | Pipe | 2025-04-04 | Ymk | 2025-04-01
386 | 2025-03-01 | 57/0 | DD60+25 | Sandy | Pipe | 2025-04-07 | Bhati | 2025-04-01
387 | 2025-04-01 | 35/1 | DA+9 | Sandy | Pipe | 2025-04-06 | Ymk | 2025-04-01
388 | 2025-04-01 | 46/0 | DD60+25 | Sandy | Pipe | 2025-04-10 | Om Const | 2025-04-01
389 | 2025-04-01 | 38/4 | DA+9 | Sandy | Pipe | 2025-04-15 | Vishwakarma Construction | 2025-04-01
390 | 2025-04-01 | 56/0 | DD60+25 | Sandy | Pipe | 2025-04-11 | Bhati | 2025-04-01
391 | 2025-04-01 | 39/0 | DB2+6 | Sandy | Pipe | 2025-04-15 | Vishwakarma Construction | 2025-04-01
392 | 2025-04-01 | 27/3 | DA+3 | DFR | CP | 2025-05-17 | YMK | 2025-05-01
393 | 2025-04-01 | 47/0 | DD60+25 | Sandy | Pipe | 2025-04-17 | Om Const | 2025-04-01
394 | 2025-04-01 | 4/0 | DD60+6 | DRY | Pipe | 2025-05-05 | Jsr Infrastructure | 2025-05-01
395 | 2025-04-01 | 38/2 | DA+6 | Sandy | Pipe | 2025-04-23 | Vishwakarma Construction | 2025-04-01
396 | 2025-04-01 | 27/2 | DA+3 | DFR | CP | 2025-05-19 | YMK | 2025-05-01
397 | 2025-04-01 | 38/1 | DA+0 | Sandy | Pipe | 2025-04-25 | Vishwakarma Construction | 2025-04-01
398 | 2025-04-01 | 38/0 | DB2+6 | Sandy | Pipe | 2025-04-28 | Vishwakarma Construction | 2025-04-01
399 | 2025-04-01 | 39/1 | DA+0 | Sandy | Pipe | 2025-05-01 | Vishwakarma Construction | 2025-05-01
400 | 2025-05-01 | 40/0 | DC2+0 | Sandy | Pipe | 2025-05-18 | Vishwakarma Construction | 2025-05-01
401 | 2025-05-01 | 40/1 | DA+6 | Sandy | Pipe | 2025-05-10 | Vishwakarma Construction | 2025-05-01
402 | 2025-05-01 | 27/6 | DA+0 | Sandy | Pipe | 2025-05-20 | YMK | 2025-05-01
403 | 2025-05-01 | 1A/8 | DA+0 | Sandy | Pipe | 2025-05-17 | Jsr Infrastructure | 2025-05-01
404 | 2025-05-01 | 27/4 | DA+3 | DFR | CP | 2025-05-20 | YMK | 2025-05-01
405 | 2025-05-01 | 38/3 | DA+9 | Sandy | Pipe | 2025-05-20 | Vishwakarma Construction | 2025-05-01
406 | 2025-05-01 | 42/4 | DA+0 | Sandy | Pipe | 2025-05-21 | Vishwakarma Construction | 2025-05-01
407 | 2025-05-01 | 40/3 | DA+3 | Sandy | Pipe | 2025-05-25 | Vishwakarma Construction | 2025-05-01
408 | 2025-05-01 | 21/9 | DA+3 | DFR | CP | 2025-05-27 | M.R. Choudhary | 2025-05-01
409 | 2025-05-01 | 27/7 | DB1+0 | DFR | CP | 2025-05-31 | YMK | 2025-05-01
410 | 2025-05-01 | 4/3 | DA+0 | DRY | Pipe | 2025-05-30 | Nyce Service & Security | 2025-05-01
411 | 2025-05-01 | 2/8 | DA+0 | Sandy | Pipe | 2025-06-04 | Jsr Infrastructure | 2025-06-01
412 | 2025-05-01 | 8/11 | DA+0 | DRY | Pipe | 2025-06-18 | Bhati Construction | 2025-06-01
413 | 2025-06-01 | 41/1 | DB1+9 | Sandy | Pipe | 2025-06-02 | Vishwakarma Construction | 2025-06-01
414 | 2025-06-01 | 30/4 | DA+3 | DRY | Pipe | 2025-06-08 | Rabbit bright technology pvt. Ltd. | 2025-06-01
415 | 2025-06-01 | 21/7 | DA+3 | DFR | CP | 2025-06-08 | M.R. Choudhary | 2025-06-01
416 | 2025-06-01 | 19/5 | DA+0 | DRY | Pipe | 2025-06-08 | Shree Ram Construction | 2025-06-01
417 | 2025-06-01 | 41/0 | DC1+6 | Sandy | Pipe | 2025-06-11 | Vishwakarma Construction | 2025-06-01
418 | 2025-06-01 | 27/1 | DA+3 | DFR | CP | 2025-07-12 | YMK | 2025-06-01
419 | 2025-06-01 | 30/5 | DA+3 | DRY | Pipe | 2025-06-17 | Rabbit bright technology pvt. Ltd. | 2025-06-01
420 | 2025-06-01 | 2/7 | DA+3 | Sandy | Pipe | 2025-06-14 | Jsr Infrastructure | 2025-06-01
421 | 2025-06-01 | 11/4 | DA+0 | Sandy | Pipe | 2025-06-15 | BR & Sons | 2025-06-01
422 | 2025-06-01 | 36/2 | DA+0 | Sandy | Pipe | 2025-06-16 | Vishwakarma Construction | 2025-06-01
423 | 2025-06-01 | 36/3 | DA+0 | Sandy | Pipe | 2025-06-15 | Vishwakarma Construction | 2025-06-01
424 | 2025-06-01 | 10/0 | DD60+25 | DFR | CP | 2025-06-18 | Bhati Construction | 2025-06-01
425 | 2025-06-01 | 4/1 | DA+0 | DRY | Pipe | 2025-07-04 | Jsr Infrastructure | 2025-07-01
426 | 2025-06-01 | 21/5 | DA+6 | DFR | CP | 2025-07-24 | M.R. Choudhary | 2025-07-01
427 | 2025-06-01 | 36/4 | DA+6 | Sandy | Pipe | 2025-06-23 | Vishwakarma Construction | 2025-06-01
428 | 2025-06-01 | 30/6 | DA+0 | DRY | Pipe | 2025-07-02 | YMK | 2025-07-01
429 | 2025-06-01 | 2/9 | DA+0 | DRY | Pipe | 2025-07-04 | Jsr Infrastructure | 2025-07-01
430 | 2025-06-01 | 37/0 | DB2+0 | Sandy | Pipe | 2025-07-03 | Vishwakarma Construction | 2025-07-01
431 | 2025-06-01 | 21/4 | DA+3 | Sandy | Pipe | 2025-07-24 | M.R. Choudhary | 2025-07-01
432 | 2025-07-01 | 31/0 | DB2+0 | Sandy | Pipe | 2025-07-03 | YMK | 2025-07-01
433 | 2025-07-01 | 4/2 | DA+0 | DRY | Pipe | 2025-07-04 | Nyce Services | 2025-07-01
434 | 2025-07-01 | 3/0 | DD60+6 | DRY | Pipe | 2025-07-12 | Jsr Infrastructure | 2025-07-01
435 | 2025-07-01 | 4/4 | DA+0 | DRY | Pipe | 2025-07-12 | Nice Security & Services | 2025-07-01
436 | 2025-07-01 | 21/3 | DA+6 | Sandy | Pipe | 2025-07-24 | M.R. Choudhary | 2025-07-01
436 | 2025-07-01 | 8/12 | DA+0 | DRY | Pipe |  | Jsr Infrastructure
436 | 2025-07-01 | 8/2 | DA+3 | DRY | Pipe |  | Dhakad Enterprises
437 | 2025-07-01 | 37/1 | DA+9 | Sandy | Pipe | 2025-07-18 | Vishwakarma Construction | 2025-07-01
437 | 2025-07-01 | 8/1 | DA+3 | DRY | Pipe |  | Dhakad Enterprises
438 | 2025-07-01 | 20/0 | DB2+0 | Sandy | Pipe | 2025-07-24 | Vishwakarma Construction | 2025-07-01
438 | 2025-07-01 | 27/0 | DC1+0 | DFR | CP |  | YMK
439 | 2025-07-01 | 37/2 | DA+3 | Sandy | Pipe | 2025-07-18 | Vishwakarma Construction | 2025-07-01
440 | 2025-07-01 | 9/0 | DD60+18 | DRY | Pipe | 2025-07-22 | Jsr Infrastructure | 2025-07-01
441 | 2025-07-01 | 8/5 | DA+3 | DRY | Pipe | 2025-07-29 | Yash Infra | 2025-07-01
442 | 2025-07-01 | 20/2 | DA+0 | DRY | Pipe | 2025-07-24 | Vishwakarma Construction | 2025-07-01
442 | 2025-07-01 | 21/0 | DB2+0 | DRY | Pipe |  | Vishwakarma Construction
443 | 2025-07-01 | 26/0 | DB1+0 | DFR | CP | 2025-07-27 | YMK | 2025-07-01
443 | 2025-07-01 | 20/3 | DA+0 | DRY | Pipe |  | Vishwakarma Construction
443 | 2025-07-01 | 21/2 | DA+0 | Sandy | Pipe |  | Vishwakarma Construction
444 | 2025-07-01 | 8/0 | DB1+0 | DRY | Pipe | 2025-07-31 | Dhakad Enterprises | 2025-07-01
444 | 2025-07-01 | 8/4 | DA+3 | DRY | Pipe |  | Jsr Infrastructure
445 | 2025-07-01 | 24/0 | DD45+3 | DRY | Pipe | 2025-08-05 | YMK | 2025-08-01
445 | 2025-08-01 | 14A/0 | DC1+0 | DRY | Pipe |  | BR & Sons
446 | 2025-08-01 | 23/0 | DD45+3 | DRY | Pipe | 2025-08-07 | YMK | 2025-08-01
447 | 2025-08-01 | 10/1 | DA+0 | DRY | Pipe | 2025-08-24 | Jsr Infrastructure | 2025-08-01
447 | 2025-08-01 | 11/1 | DA+0 | Sandy | Pipe |  | Om Construction_Chandrapal
448 | 2025-08-01 | 26/1 | DA+0 | DRY | Pipe | 2025-08-20 | YMK | 2025-08-01
448 | 2025-08-01 | 11/2 | DA+0 | Sandy | Pipe |  | Om Construction_Chandrapal
449 | 2025-08-01 | 28/1 | DA+0 | DRY | Pipe | 2025-08-29 | YMK | 2025-08-01
449 | 2025-08-01 | 10/7 | DA+3 | DRY | Pipe |  | Jsr Infrastructure
449 | 2025-09-01 | 20/1 | DA+0 | Sandy | Pipe |  | Vishwakarma Construction
449 | 2025-09-01 | 6/0 | DB2+9 | DRY | Pipe |  | Dhakad Enterprises
449 | 2025-09-01 | 5/0 | DB1+9 | DRY | Pipe |  | Dhakad Enterprises
450 | 2025-09-01 | 10/16 | DA+3 | DRY | Pipe | 2025-09-20 | Jsr Infrastructure | 2025-09-01
450 | 2025-09-01 | 11/0 | DB1+0 | Sandy | Pipe |  | Om Construction_Chandrapal
450 | 2025-09-01 | 22/10 | DA+6 | Sandy | Pipe |  | Vishwakarma Construction
451 | 2025-09-01 | 10/15 | DA+3 | DRY | Pipe | 2025-09-20 | Jsr Infrastructure | 2025-09-01
451 | 2025-09-01 | 11/3 | DA+0 | Sandy | Pipe |  | Om Construction_Chandrapal
451 | 2025-09-01 | 7/0 | DB1+0 | DRY | Pipe |  | Dhakad Enterprises
451 | 2025-10-01 | 10/10 | DA+3 | Sandy | Pipe |  | Jsr Infrastructure
451 | 2025-10-01 | 10/23 | DA+0 | Sandy | Pipe |  | Om Construction_Chandrapal
451 | 2025-10-01 | 21/8 | DA+6 | DRY | Pipe |  | Vishwakarma Construction
451 | 2025-10-01 | 10/22 | DA+0 | Sandy | Pipe |  | Om Construction_Chandrapal
451 | 2025-10-01 | 8/3 | DA+0 | DRY | Pipe |  | Jsr Infrastructure
451 | 2025-10-01 | 19/4 | DA+0 | DRY | Pipe |  | Vishwakarma Construction
451 | 2025-10-01 | 21/6 | DA+3 | DRY | Pipe |  | Vishwakarma Construction
451 | 2025-11-01 | 26/8 | DA+6 | DFR | CP |  | Vishwakarma Construction
451 | 2025-11-01 | 22/0 | DB2+3 | DRY | Pipe |  | Vishwakarma Construction
451 | 2025-11-01 | 13/4 | DA+3 | DRY | Pipe |  | Vishwakarma Construction
451 | 2026-02-01 | 10/2 | DA+0 | DFR | CP |  | Jsr Infrastructure
451 | 2026-02-01 | 8/8 | DA+6 | DRY | Pipe |  | Jsr Infrastructure
451 | 2026-02-01 | 8/6 | DA+3 | DRY | Pipe |  | Jsr Infrastructure
451 | 2026-03-01 | 21/1 | DA+6 | DRY | Pipe |  | Vishwakarma Construction
451 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!

## Erection Productivity (hidden)
Sr no | Item | Unit | Total | Comp Qty | Bal Qty | Aug'25 |  |  | Remarks
|  |  | Qty | 31.08.25 | 01.08.25 | Plan | WIP | Actual
1 | Erection | Nos | 485 | 303 | 182 | 87 | 18 | 6
2 | Stringing | KM | 191.3 | 43.51 | 147.79 | 0 | 0 | 0
[44 empty] | 0 | [11 empty] | 0
Gang Wise Output
Sr. No. | Sub-Contractor Name | WIP |  |  | Start Date | Comp Date | Output -01.08.25 | Output -02.08.25 | Output -03.08.25 | Output -04.08.25 | Output -05.08.25 | Output -06.08.25 | Output -07.08.25 | Output -08.08.25 | Output -09.08.25 | Output -10.08.25 | Output -11.08.25 | Output -12.08.25 | Output -13.08.25 | Output -14.08.25 | Output -15.08.25 | Output -16.08.25 | Output -17.08.25 | Output -18.08.25 | Output -19.08.25 | Output -20.08.25 | Output -21.08.25 | Output -22.08.25 | Output -23.08.25 | Output -24.08.25 | Output -25.08.25 | Output -26.08.25 | Output -27.08.25 | Output -28.08.25 | Output -29.08.25 | Output -30.08.25 | Output -31.08.25 | Output -01.09.25 | Output -02.09.25 | Output -03.09.25 | Output -04.09.25 | Output -05.09.25 | Output -06.09.25 | Output -07.09.25 | Output -08.09.25 | Output -09.09.25 | Output -10.09.25 | Output -11.09.25 | Output -12.09.25 | Output -13.09.25 | Output -14.09.25 | Output -15.09.25 | Output -16.09.25 | Output -17.09.25 | Output -18.09.25 | Output -19.09.25 | Output -20.09.25 | Output -21.09.25 | Output -22.09.25 | Output -23.09.25 | Output -24.09.25 | Output -25.09.25 | Output -26.09.25 | Output -27.09.25 | Output -28.09.25 | Output -29.09.25 | Output -30.09.25 | Output -31.09.25 | Cumulative Till dated | Status
|  | Loc. No. | Type of Tower | Tower Weight
1 | Arawali-2 | 12/0 | DD60+0 | 0 | 2025-07-25 | 2025-08-02 | 3.8 | 4.1 | [60 empty] | 7.9 | Completed
2 | Vinay Gupta | 44/7 | DA+9 | 0 | 2025-07-26 | 2025-07-03 | 4.8 | 4.3 | 5.1 | [59 empty] | 14.2 | Completed
3 | Manish (Pawan) | 44/0 | DB1+3 | 0 | 2025-07-29 | 2025-08-03 | 8.4 | 7.8 | 8.4 | [59 empty] | 24.6 | Completed
4 | Jwala Singh | 29/1 | DA+3 | 0 | 2025-07-30 | 2025-08-04 | 7.2 | 7.1 | 6.8 | 8.8 | [58 empty] | 29.9 | Completed
5 | Vinay Gupta | 47/7 | DA+3 | 0 | 2025-07-26 | 2025-08-05 | 3.6 | 3.2 | 3.7 | 3.9 | 4.1 | [57 empty] | 18.5 | Completed
6 | Priyanka Devi | 19/5 | DA+0 | 0 | 2025-08-01 | 2025-08-05 | 7.2 | 8.2 | 8.2 | 6.2 | 7.7 | [57 empty] | 37.5 | Completed
7 | Sintu_Pawan (Satyam Enterprises) | 44/10 | DB1+9 | 0 | 2025-07-28 | 2025-08-06 | 7.9 | 8.2 | 8.3 | 8.1 | 8.6 | [57 empty] | 41.1 | Completed
8 | Pusplata (Kailash) | 30/3 | DA+3 | 0 | 2025-08-01 | 2025-08-06 | 6.2 | 6.2 | 7.2 | 6.9 | 6.5 | 5.8 | [56 empty] | 38.8 | Completed
9 | Bhairo Mahto | 4/1 | DA+0 | 0 | 2025-07-25 | 2025-08-09 | 2.9 | 2.7 | 3.2 | 3.5 | 3.8 | 3.1 | 2.9 | 2.8 | 2.7 | [53 empty] | 27.6 | Completed
10 | Pusplata (Praful) | 25/3 | DA+0 | 0 | 2025-07-31 | 2025-08-09 | 3.3 | 3.8 | 3.2 | 3.8 | 4.2 | 4.5 | 4.1 | 3.8 | 4.1 | [53 empty] | 34.8 | Completed
11 | Nitish (Pawan) | 44/5 | DA+9 | 0 | 2025-08-04 | 2025-08-09 |  |  |  | 5.2 | 8.2 | 8.9 | 9.1 | 8.7 | 7.1 | [53 empty] | 47.2 | Completed
12 | Jwala Singh | 8/12 | DA+0 | 0 | 2025-08-04 | 2025-08-09 |  |  |  | 5.2 | 6.3 | 6.2 | 6.8 | 6.9 | 6.1 | [53 empty] | 37.5 | Completed
13 | Jwala Singh | 29/0 | DB1+0 | 0 | 2025-07-30 | 2025-08-12 | 2.8 | 5.1 | 5.2 | 4.5 | 4.6 | 4.3 | 5.1 | 4.3 | 4.8 | 5.4 | 4.9 | 6.6 | [50 empty] | 57.6 | Completed
14 | Priyanka Devi | 2/0 | DC1+0 | 0 | 2025-07-29 | 2025-08-13 | 3.3 | 3.6 | 3.8 | 4.9 | 5.1 | 5.2 | 5.3 | 5.7 | 5.5 | 5.9 | 6.2 | 5.6 | 6.3 | [49 empty] | 66.4 | Completed
15 | Shobha Devi | 55/8 | DA+6 | 0 | 2025-08-07 | 2025-08-13 | [6 empty] | 5.7 | 6.9 | 6.2 | 6.8 | 6.1 | 7.2 | 6.2 | [49 empty] | 45.1 | Completed
16 | Vinay Gupta | 47/2 | DA+9 | 0 | 2025-08-04 | 2025-08-16 |  |  |  | 3.1 | 3.4 | 4.9 | 2.1 | 3.2 | 3.8 | 4.1 | 4.1 | 4.7 | 4.9 | 4.1 |  | 4.7 | [46 empty] | 47.1 | Completed
17 | Satyam Enterprises | 44/6 | DB1+3 | 0 | 2025-08-09 | 2025-08-16 | [8 empty] | 6.8 | 9.3 | 9.7 | 8.1 | 8.3 | 8.2 |  | 9.7 | [46 empty] | 60.1 | Completed
18 | Sheetal Singh | 2/3 | DA+3 | 0 | 2025-08-04 | 2025-08-17 |  |  |  | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | 2.7714 | [45 empty] | 38.8 | Completed
19 | Sintu_Pawan (Satyam Enterprises) | 45/0 | DC2+0 | 0 | 2025-08-06 | 2025-08-17 | [5 empty] | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | [45 empty] | 66.381 | Completed
20 | Pusplata (Kailash) | 30/5 | DA+3 | 0 | 2025-08-06 | 2025-08-17 | [5 empty] | 3.2333 | 3.2333 | 3.2333 | 3.2333 | 3.2333 | 3.2333 | 3.2333 | 3.2333 | 3.2333 | 3.2333 | 3.2333 | 3.2333 | [45 empty] | 38.8 | Completed
21 | Pusplata (Ramchandra) | 27/4 | DA+3 | 0 | 2025-08-09 | 2025-08-17 | [8 empty] | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | [45 empty] | 38.8 | Completed
22 | Rahul Kumar | 40/3 | DA+3 | 0 | 2025-08-10 | 2025-08-17 | [9 empty] | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | [45 empty] | 38.8 | Completed
23 | Sobha Devi | 55/7 | DA+0 | 0 | 2025-08-13 | 2025-08-17 | [12 empty] | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | [45 empty] | 37.5 | Completed
24 | Satyam-Manish | 43/11 | DA+3 | 0 | 2025-08-12 | 2025-08-18 | [11 empty] | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | [44 empty] | 38.8 | Completed
25 | Pusplata_Pankaj | 17/4 | DA+3 | 0 | 2025-08-13 | 2025-08-18 | [12 empty] | 6.4667 | 6.4667 | 6.4667 | 6.4667 | 6.4667 | 6.4667 | [44 empty] | 38.8 | Completed
26 | Usha Tower | 2/5 | DA+3 | 0 | 2025-08-04 | 2025-08-19 |  |  |  | 2.2 | 2.5 | 2.5 | 2.8 | 2.9 | 2.1 | 2.7 | 3.1 | 1.9 | 2.4 | 2.7 |  | 2.9 | 2.1 | 2.3 | 2.7 | [43 empty] | 37.8 | Completed
27 | Jwala Singh | 28/5 | DA+9 | 0 | 2025-08-12 | 2025-08-19 | [11 empty] | 6.9 | 6.4 | 7.1 |  | 6.9 | 6.2 | 6.7 | 6.9 | [43 empty] | 47.1 | Completed
28 | Bhairo Mahto | 1/0 | DD60+0 | 0 | 2025-07-07 | 2025-08-20 | 2.9 | 3.1 | 2.8 | 2.2 | 2.5 | 2.5 | 2.8 | 2.9 | 2.1 | 2.7 | 3.1 | 1.9 | 2.4 | 2.7 |  | 2.9 | 2.1 | 2.3 | 2.7 | 2.9 | [42 empty] | 49.5 | Completed
29 | Gauri Shankar | 41/1 | DB1+9 | 0 | 2025-08-10 | 2025-08-10 | [9 empty] | 4.5 | 6.7 | 7.2 | 7.6 | 7.9 |  | 7.1 | 6.9 | 7.5 | 7.2 | 8.1 | [42 empty] | 70.7 | Completed
30 | Bhairo Mahto | 4/2 | DA+0 | 0 | 2025-07-30 | 2025-07-30 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | 1.5627 | [40 empty] | 34.379 | Completed
31 | Vinay Gupta | 47/4 | DA+3 | 0 | 2025-08-06 | 2025-08-06 | [5 empty] | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | 2.2824 | [40 empty] | 38.8 | Completed
32 | Satyam Enterprises | 44/9 | DA+9 | 0 | Sandy | 2025-08-17 | [16 empty] | 5.898 | 5.898 | 5.898 | 5.898 | 5.898 | 5.898 | 5.898 | 5.898 | [38 empty] | 47.184 | Completed
33 | Pusplata (Kailash) | 30/6 | DA+0 | 0 | DRY | 2025-08-17 | [16 empty] | 7.5009 | 7.5009 | 7.5009 | 7.5009 | 7.5009 | [41 empty] | 37.5044 | Completed
34 | Jwala Singh | 28/2 | DA+0 | 0 | DFR | 2025-08-19 | [18 empty] | 5.3578 | 5.3578 | 5.3578 | 5.3578 | 5.3578 | 5.3578 | 5.3578 | [37 empty] | 37.5044 | Completed
35 | Vinay Construction | 47/3 | DA+9 | 0 | Sandy | 2025-08-17 | [16 empty] | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | 3.6295 | [33 empty] | 47.184 | Completed
36 | Rahul Kumar | 40/2 | DA+3 | 0 | Sandy | 2025-08-18 | [17 empty] | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | [38 empty] | 38.8 | Completed
37 | Pusplata | 18/0 | DC2+0 | 0 | DRY | 2025-08-18 | [17 empty] | 8.2976 | 8.2976 | 8.2976 | 8.2976 | 8.2976 | 8.2976 | 8.2976 | 8.2976 | [37 empty] | 66.381 | Completed
38 | Pusplata (Dharamveer) | 27/1 | DA+3 | 0 | DFR | 2025-08-16 | [15 empty] | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | [39 empty] | 38.8 | Completed
39 | Jirwa Devi | 52/3 | DA+9 | 0 | Sandy | 2025-08-17 | [16 empty] | 3.3703 | 3.3703 | 3.3703 | 3.3703 | 3.3703 | 3.3703 | 3.3703 | [39 empty] | 23.592 | Completed
40 | Sunny Construction | 55/1 | DA+0 | 0 | WFR | 2025-08-17 | [16 empty] | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | [38 empty] | 37.5044 | Completed
41 | Chinta Devi | 44/11 | DA+0 | 0 | Sandy | 2025-08-19 | [18 empty] | 5.3578 | 5.3578 | 5.3578 | 5.3578 | 5.3578 | 5.3578 | 5.3578 | [37 empty] | 37.5044 | Completed
42 | Pusplata (Ashok) | 4/4 | DA+0 | 0 | DRY | 2025-08-20 | [19 empty] | 6.2507 | 6.2507 | 6.2507 | 6.2507 | 6.2507 | 6.2507 | [37 empty] | 37.5044 | Completed
43 | Sobha Devi | 57/2 | DA+3 | 0 | DRY | 2025-08-21 | [20 empty] | 7.76 | 7.76 | 7.76 | 7.76 | 7.76 | [37 empty] | 38.8 | Completed
44 | 45895 | 31/1 | DA+0 | 0 | DRY | 2025-08-22 | [21 empty] | 7.5009 | 7.5009 | 7.5009 | 7.5009 | 7.5009 | [36 empty] | 37.5044 | Completed
45 | 45898 | 57/1 | DA+0 | 0 | Sandy | 2025-08-21 | [20 empty] | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | [33 empty] | 37.5044 | Completed
46 | 45899 | 30/1 | DA+0 | 0 | Sandy | 2025-08-25 | [24 empty] | 6.2507 | 6.2507 | 6.2507 | 6.2507 | 6.2507 | 6.2507 | [32 empty] | 37.5044 | Completed
47 | 45899 | 43/10 | DA+3 | 0 | Sandy | 2025-08-25 | [24 empty] | 6.4667 | 6.4667 | 6.4667 | 6.4667 | 6.4667 | 6.4667 | [32 empty] | 38.8 | Completed
48 | 45899 | 36/2 | DA+0 | 0 | Sandy | 2025-08-22 | [21 empty] | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | [32 empty] | 37.5044 | Completed
49 | 45900 | 8/1 | DA+3 | 0 | DRY | 2025-08-23 | [22 empty] | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | 4.3111 | [31 empty] | 38.8 | Completed
50 | 45900 | 54/5 | DA+9 | 0 | Sandy | 2025-08-17 | [16 empty] | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | 3.1456 | [31 empty] | 47.184 | Completed
51 | 45900 | 4/3 | DA+0 | 0 | DRY | 2025-08-29 | [28 empty] | 12.5015 | 12.5015 | 12.5015 | [31 empty] | 37.5044 | Completed
52 | 45900 | 45/1 | DA+9 | 0 | Sandy | 2025-08-25 | [24 empty] | 6.7406 | 6.7406 | 6.7406 | 6.7406 | 6.7406 | 6.7406 | 6.7406 | [31 empty] | 47.184 | Completed
1 | 45903 | 14A/0 | DC1+0 | 0 | DRY | 2025-08-26 | [25 empty] | 7.3757 | 7.3757 | 7.3757 | 7.3757 | 7.3757 | 7.3757 | 7.3757 | 7.3757 | 7.3757 | [28 empty] | 66.381 | Completed
2 | 45903 | 20/3 | DA+0 | 0 | DRY | 2025-08-26 | [25 empty] | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | [28 empty] | 37.5044 | Completed
3 | 45902 | 31/2 | DA+0 | 0 | DRY | 2025-08-26 | [25 empty] | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | [29 empty] | 37.5044 | Completed
4 | 45903 | 27/0 | DC1+0 | 0 | DFR | 2025-08-23 | [22 empty] | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | 5.5317 | [28 empty] | 66.381 | Completed
5 | 45903 | 43/5 | DA+3 | 0 | DRY | 2025-08-29 | [28 empty] | 9.1 | 10.1 | 9.1 |  |  | 10.5 | [28 empty] | 38.8 | Completed
6 | 45904 | 8/4 | DA+3 | 0 | DRY | 2025-08-29 | [28 empty] | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | 5.5429 | [27 empty] | 38.8 | Completed
7 | 45905 | 21/0 | DB2+0 | 0 | DRY | 2025-09-02 | [32 empty] | 14.3993 | 14.3993 | 14.3993 | 14.3993 | [26 empty] | 57.5972 | Completed
8 | 45906 | 36/3 | DA+0 | 0 | Sandy | 2025-08-30 | [31 empty] | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | 4.688 | [23 empty] | 37.5044 | Completed
9 | 45906 | 47/6 | DA+3 | 0 | Sandy | 2025-08-22 | [21 empty] | 3.5 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 3.15 | 2.3 | [25 empty] | 38.85 | Completed
10 | 45906 | 54/4 | DA+9 | 0 | Sandy | 2025-09-01 | [31 empty] | 7.8641 | 7.8641 | 7.8641 | 7.8641 | 7.8641 | 7.8641 | [25 empty] | 47.1844 | Completed
11 | 45906 | 26/0 | DB1+0 | 0 | DFR | 2025-08-26 | [25 empty] | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | [25 empty] | 57.5972 | Completed
12 | 45907 | 47/1 | DA+3 | 0 | Sandy | 2025-09-01 | [31 empty] | 5.5497 | 5.5497 | 5.5497 | 5.5497 | 5.5497 | 5.5497 | 5.5497 | [24 empty] | 38.8476 | Completed
13 | 45907 | 20/2 | DA+0 | 0 | DRY | 2025-09-02 | [32 empty] | 6.2507 | 6.2507 | 6.2507 | 6.2507 | 6.2507 | 6.2507 | [24 empty] | 37.5044 | Completed
14 | 45907 | 24/0 | DD45+3 | 0 | DRY | 2025-08-26 | [25 empty] | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | 6.9161 | [24 empty] | 89.9096 | Completed
15 | 45909 | 2/4 | DA+3 | 0 | Sandy | 2025-08-24 | [23 empty] | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | [22 empty] | 38.8476 | Completed
16 | 45909 | 2/6 | DA+3 | 0 | Sandy | 2025-08-24 | [23 empty] | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | 2.2852 | [22 empty] | 38.8476 | Completed
17 | 45910 | 32/1 | DA+3 | 0 | Sandy | 2025-09-03 | [33 empty] | 4.856 | 4.856 | 4.856 | 4.856 | 4.856 | 4.856 | 4.856 | 4.856 | [21 empty] | 38.8476 | Completed
18 | 45910 | 52/4 | DA+9 | 0 | Sandy | 2025-09-01 | [31 empty] | 4.7184 | 4.7184 | 4.7184 | 4.7184 | 4.7184 | 4.7184 | 4.7184 | 4.7184 | 4.7184 | 4.7184 | [21 empty] | 47.1844 | Completed
19 | 45911 | 34/3 | DA+0 | 0 | Sandy | 2025-09-03 | [33 empty] | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | 4.1672 | [20 empty] | 37.5044 | Completed
20 | 45912 | 21/4 | DA+3 | 0 | Sandy | 2025-09-09 | [39 empty] | 9.7119 | 9.7119 | 9.7119 | 9.7119 | [19 empty] | 38.8476 | Completed
21 | 45912 | 28/0 | DB2+0 | 0 | DFR | 2025-09-03 | [33 empty] | 4.3 | 3.6 | 2.9 | 4.1 | 1.2 | 1.1 | 10.1 | 10.3 | 9.9 | 10.1 | [19 empty] | 57.6 | Completed
22 | 45912 | 6/2 | DA+0 | 0 | DFR | 2025-09-05 | [37 empty] | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | 6.25 | [19 empty] | 37.5 | Completed
23 | 45912 | 54/3 | DA+6 | 0 | Sandy | 2025-09-07 | [37 empty] | 7.5688 | 7.5688 | 7.5688 | 7.5688 | 7.5688 | 7.5688 | [19 empty] | 45.413 | Completed
24 | 45913 | 2/1 | DA+3 | 0 | Sandy | 2025-09-03 | [33 empty] | 3.5316 | 3.5316 | 3.5316 | 3.5316 | 3.5316 | 3.5316 | 3.5316 | 3.5316 | 3.5316 | 3.5316 | 3.5316 | [18 empty] | 38.8476 | Completed
25 | 45914 | 56/0 | DD60+25 | 0 | Sandy | 2025-08-30 | [29 empty] | 8.9 | 8.9 | 8.9 | 8.9 | 8.9 | 8.2 | 8.9 | 9.2 | 10.4 | 10.6 | 10.6 | 10.6 | 10.6 | 10.6 | 8.9 | [18 empty] | 143.1 | Completed
26 | 45916 | 26/1 | DA+0 | 0 | DRY | 2025-09-07 | [38 empty] | 1.2 | 1.3 | 1.5 | 1.3 | 1.1 | 2.1 | 9 | 10.1 | 9.9 | [15 empty] | 37.5 | Completed
27 | 45920 | 52/2 | DA+6 | 0 | Sandy | 2025-09-10 | [40 empty] | 5.7 | 6.2 |  |  | 4.1285 | 4.1285 | 4.1285 | 4.1285 | 4.5985 | 6.2 | 6.2 | [11 empty] | 45.4123 | Completed
28 | 45918 | 54/1 | DA+3 | 0 | Sandy | 2025-09-13 | [42 empty] | 6.47 |  | 6.4746 | 6.4746 | 6.4746 | 6.4746 | 6.4746 | [13 empty] | 38.843 | Completed
29 | 45925 | 47/0 | DD60+25 | 0 | Sandy | 2025-09-09 | [39 empty] | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | 8.4176 | [6 empty] | 143.1 | Completed
30 | 45916 | 36/4 | DA+6 | 0 | Sandy | 2025-09-07 | [37 empty] | 3.9 | 4.9 | 4.6 | 4.2 | 5.1 | 5.2 | 5.6 | 4.5413 | 4.5413 | 2.8313 | [15 empty] | 45.4139 | Completed
31 | 45929 | 47/5 | DA+0 | 0 | Sandy | 2025-09-07 | [37 empty] | 2.9 | 3.9 | [16 empty] | 6.35 | 5.1 | 6.4176 | 6.4176 | 6.4176 |  |  | 37.5029 | Completed
32 | 45926 | 27/11 | DA+3 | 0 | DRY | 2025-08-29 | [17 empty] | 4.3 | [10 empty] | 4.6 | 5.1 | 4.5 | 6.6 | 5.2 | [16 empty] | 4.5 | [6 empty] | 4 | [5 empty] | 38.8 | Completed
33 | 45916 | 36/1 | DA+3 | 0 | Sandy | 2025-08-29 | [31 empty] | 3.2 | 3.2 | 3.2 |  | 3.2 | 3.2 | 3.2 | 4.1 | 4.3 | 3.9 | 5.1 | 4.8 | 4.2 | 2.0446 | 2.0446 | 2.0446 | [15 empty] | 51.7338 | Completed
34 | 45922 | 2/2 | DA+3 | 0 | Sandy | 2025-09-09 | [39 empty] | 2.1 | 2.9 | 3.1 | 3.5 | 3.3 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 2.7748 | 1.7448 | [9 empty] | 38.8435 | Completed
35 | 45922 | 43/3 | DA+0 | 0 | DRY | 2025-09-09 | [39 empty] | 2.1 | 2.9 | 3.1 | 3.5 | 3.3 | 2.6789 | 2.6789 | 2.1 | 2.1 | 2.1 | 2.6789 | 2.6789 | 2.6789 | 2.9 | [9 empty] | 37.4944 | Completed
36 | 45930 | 21/3 | DA+6 | 0 | Sandy | 2025-09-10 | [39 empty] | 2.6 | 2.8 |  |  |  | 2.1625 | 2.1625 | 2.1625 | 2.1625 | 2.1625 | 2.1625 | 2.1625 | 2.1625 | 2.1625 | 2.1625 | 2.1625 |  | 3.02 | 3.61 | 3.1 | 3.4 | 3.1 |  | 45.4178 | Completed
37 | 45918 | 8/5 | DA+3 | 0 | DRY | 2025-09-12 | [42 empty] | 2.9 | 4.1 | 6.5 | 6.7 | 6.4 | 6.7 | 5.5497 | [13 empty] | 38.8497 | Completed
38 | 45923 | 8/2 | DA+3 | 0 | DRY | 2025-09-12 | [42 empty] | 2.6 | 3.1 | 3.2373 | 3.2373 | 3.2373 | 3.2373 | 3.2373 | 3.2373 | 3.2373 | 3.2373 | 3.2373 | 4.0073 | [8 empty] | 38.843 | Completed
39 | 45922 | 21/5 | DA+6 | 0 | DFR | 2025-09-19 | [49 empty] | 11.3533 | 11.3533 | 11.3533 | 11.3533 | [9 empty] | 45.413 | Completed
40 | 45922 | 54/2 | DA+3 | 0 | Sandy | 2025-09-19 | [49 empty] | 9.7119 | 9.7119 | 9.7119 | 9.7119 | [9 empty] | 38.8476 | Completed
41 | 45923 | 29/3 | DA+0 | 0 | Sandy | 2025-09-10 | [40 empty] | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 |  |  |  | 2.5 | [8 empty] | 37.5 | Completed
42 | 45927 | 36/0 | DB2+0 | 0 | Sandy | 2025-09-16 | [46 empty] | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 |  |  |  |  | 57.5972 | Completed
43 | 45927 | 37/0 | DB2+0 | 0 | Sandy | 2025-09-16 | [46 empty] | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 | 4.7998 |  |  |  |  | 57.5972 | Completed
44 | 45929 | 20/0 | DB2+0 | 0 | Sandy | 2025-09-20 | [50 empty] | 5.76 | 5.76 | 5.76 | 5.76 | 5.76 | 5.76 | 5.76 | 5.76 | 5.76 | 5.76 |  |  | 57.6 | Completed
45 | 45929 | 57/0 | DD60+25 | 0 | Sandy | 2025-09-15 | [45 empty] | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 | 9.5735 |  |  | 143.6019 | Completed
46 | 45930 | 52/1 | DA+6 | 0 | Sandy | 2025-09-20 | [50 empty] | 4.1285 | 4.1285 | 4.1285 | 4.1285 | 4.1285 | 4.1285 | 4.1285 | 4.1285 | 4.1285 | 4.1285 | 4.1285 |  | 45.413 | Completed
47 | 45930 | 54/0 | DB1+6 | 0 | Sandy | 2025-09-22 | [52 empty] | 7.5415 | 7.5415 | 7.5415 | 7.5415 | 7.5415 | 7.5415 | 7.5415 | 7.5415 | 7.5415 |  | 67.8737 | Completed
48 | Shobha Devi | 40/0 | DC2+0 | 66.3811 | 2025-09-29 | WIP | [60 empty] | 3.2 |  | 3.2 | WIP
49 | Vinay Construction/ Chinta Devi | 46/0 | DD60+25 | 143.6019 | 2025-09-29 | WIP | [60 empty] | 2.9 |  | 2.9 | WIP
50 | Nirmal Mahto | 35/5 | DA+0 | 37.5 | 2025-09-27 | WIP | [57 empty] | 1.8 | 2.1 | 2.3 | 2.3 |  | 8.5 | WIP
51 | Vivek Ganju | 42/6 | DA+0 | 37.5 | 2025-09-22 | WIP | [52 empty] | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 |  | 26.1 | WIP
52 | Sheetal Singh-1 | 6/1 | DA+0 | 37.5 | 2025-09-25 | WIP | [55 empty] | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 |  | 30.6 | WIP
53 | Priyanka Devi (Sontosh) | 21/10 | DA+6 | 45.413 | 2025-09-29 | WIP | [60 empty] | 1.8 |  | 1.8 | WIP
Total |  |  |  | 367.896 |  |  | 65.8627 | 68.9627 | 67.4627 | 72.8341 | 71.8341 | 63.2815 | 62.0815 | 63.4815 | 70.9927 | 65.9427 | 68.4427 | 80.1855 | 88.5522 | 76.7522 | 44.0522 | 83.1022 | 94.4345 | 85.8774 | 80.9834 | 78.7341 | 79.6613 | 87.3284 | 92.1263 | 88.4763 | 91.8053 | 86.7282 | 79.2273 | 79.2273 | 110.9717 | 113.575 | 95.0904 | 87.4119 | 106.6619 | 124.1286 | 91.954 | 90.4611 | 76.7118 | 80.6668 | 66.1503 | 91.4918 | 97.5215 | 87.5471 | 89.75 | 50.0492 | 55.4602 | 66.3336 | 73.1443 | 58.6684 | 57.988 | 73.7093 | 75.5978 | 69.3978 | 79.0304 | 56.5904 | 50.0831 | 59.3706 | 56.723 | 56.4306 | 46.6211 | 47.1211 | 32.97 | 0 | 4613.816
Formulas:
Aug'25 = +VLOOKUP([Unit],'Erection Compiled'!$C189:G309,4,FALSE)
Note on AM66: Raghav Ranjan: No work done due to ROW at 47/5.
Note on AN66: Raghav Ranjan: No work done due to ROW at 47/5.
Note on AO82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to ROW
Note on AP82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to ROW
Note on AQ82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to ROW
Note on AR82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to ROW
Note on AS82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to ROW
Note on AT82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to ROW
Note on AT87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gang idle due to ROW
Note on AU87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gang idle due to ROW
Note on AV87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gang idle due to ROW
Note on AW87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gang idle due to ROW
Note on AX87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gang idle due to ROW
Note on AY87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gang idle due to ROW
Note on AU92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gang idle due to ROW
Note on AV92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gang idle due to ROW
Note on AW92: Raghav Ranjan: No work done due to less manpower
Note on AX92: Raghav Ranjan: No work done due to less manpower
Note on AY92: Raghav Ranjan: No work done due to less manpower
Note on AZ92: Raghav Ranjan: No work done due to less manpower
Note on BA92: Raghav Ranjan: No work done due to less manpower
Note on BB92: Raghav Ranjan: No work done due to less manpower
Note on BC92: Raghav Ranjan: No work done due to less manpower
Note on BD92: Raghav Ranjan: No work done due to less manpower
Note on BE92: Raghav Ranjan: No work done due to less manpower
Note on BF92: Raghav Ranjan: No work done due to less manpower
Note on BG92: Raghav Ranjan: No work done due to less manpower
Note on BH92: Raghav Ranjan: No work done due to less manpower
Note on BI92: Raghav Ranjan: No work done due to less manpower
Note on BJ92: Raghav Ranjan: No work done due to less manpower
Note on AO93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AP93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AQ93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AR93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AS93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AT93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AU93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AV93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AW93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AX93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AY93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AZ93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BA93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BB93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BC93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BD93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to ROW
Note on BF93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BG93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BH93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BI93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BJ93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on BK93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to shutdown of 33 KV
Note on AP94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done.
Note on AW97: Raghav Ranjan: No work done due to less manpower
Note on AX97: Raghav Ranjan: No work done due to less manpower
Note on AY97: Raghav Ranjan: No work done due to less manpower
Note on BK97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No work done due to ROW

## Crane Erection Productivity (hidden)
Sr No | Locs | TOT | Crane Using | [5 empty] | Manual Erection
|  |  | Start Date | Complete Date | No of Days | Weight in MT | Gang | Manpower | Start Date | Complete Date | No of Days | Weight in MT | Manpower | Gangs
1 | 1A/4 | DA+3 | 2025-05-10 | 2025-05-14 | 5 | 14.78 | Bhairo Mahto (Departmental) | 42 | 2025-06-04 | 2025-06-11 | 8 | 24.0676 | 30 | Bhairo Mahto (Departmental) | 38.8476
2 | 1A/6 | DA+0 | 2025-05-28 | 2025-05-31 | 4 | 14.875 | Bhairo Mahto (Departmental) | 42 | 2025-06-12 | 2025-06-20 | 9 | 22.6294 | 30 | Bhairo Mahto (Departmental) | 37.5044
3 | 1A/7 | DA+3 | 2025-06-05 | 2025-06-08 | 4 | 14.78 | Anil Kumar | 42 | 2025-06-23 | 2025-06-30 | 8 | 24.068 | 30 | Kewat (Departmental) | 38.848
4 | 1A/8 | DA+0 | 2025-06-12 | 2025-06-16 | 5 | 14.875 | Anil Kumar | 42 | 2025-07-09 | 2025-07-15 | 7 | 22.625 | 20 | Kewat (Departmental) | 37.5
5 | 1A/0 | DD60+0 | 2025-07-01 | 2025-07-07 | 7 | 41.773 | Bhairo Mahto (Departmental) |  | 2025-07-23 | 2025-07-29 | 7 | 44.3563 | 28 | Priyanka Devi (Subodh) | 86.1293
6 | 1/0 | DD60+0 | 2025-07-07 | 2025-07-11 | 5 | 41.773 | Bhairo Mahto (Departmental) |  | 2025-08-02 | 2025-08-20 | 19 | 44.3563 | 28 | Kewat (Departmental) | 86.1293
7 | 1A/5 | DA+0 | 2025-07-10 |  |  | 14.875 | Bhairo Mahto (Departmental) | 38 | 2025-07-16 | 2025-07-26 | 11 | 22.625 | 20 | Kewat (Departmental) | 37.5
8 | 4/1 | DA+0 | 2025-07-25 | 2025-07-29 | 5 | 14.875 | Bhairo Mahto (Departmental) |  | 2025-08-06 | 2025-08-09 | 4 | 22.625 | 30 | Bhairo Mahto (Departmental) | 37.5
9 | 4/2 | DA+0 | 2025-07-30
Total Weight/Days |  |  |  |  | 35 | 172.606 |  |  |  |  | 73 | 227.3525
Total Average Weight/Days | [5 empty] | 4.9316 | [5 empty] | 3.1144
113.7
59.224
Formulas:
No of Days = +DAYS([Complete Date],[Crane Using])+1

## Erection Compiled
Progress Summary'!A1 | [7 empty] | Total As per LOA | 22212.28
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line | [7 empty] | Total Executed | 22212.2786
List of Completed Erection | [7 empty] | Balance | 0.001404
SL No. | Month Sl.No. | Location No. | Tower Type | Classification | Starting Date | Completion Date | Gang Name | Gang Strength | Tower Weight | Status
1 | 2024-02-01 | 60/7 | DA+3 | DRY | 2024-01-28 | 2024-02-04 | Suraj const |  | 38.8476 |  | 7 | DA+0 | 37.5044
2 | 2024-02-01 | 59/13 | DA+3 | DRY | 2024-02-01 | 2024-02-07 | Chinta Devi |  | 38.8476 |  | 6 | DA+3 | 38.8476
3 | 2024-02-01 | 63/6 | DA+3 | DRY | 2024-02-03 | 2024-02-10 | Sunny Const. |  | 38.8476 |  | 7 | DA+6 | 45.413
4 | 2024-02-01 | 59/5 | DA+3 | DFR | 2024-02-05 | 2024-02-11 | Ganesh Const |  | 38.8476 |  | 6 | DA+9 | 47.1844 | 2nd Section WIP.
5 | 2024-02-01 | 59/14 | DA+6 | DRY | 2024-02-08 | 2024-02-13 | Chinta Devi |  | 45.413 |  | 5 | DB1+0 | 57.5972
6 | 2024-02-01 | 60/8 | DA+0 | DRY | 2024-02-09 | 2024-02-15 | Suraj const |  | 37.5044 |  | 6 | DB1+3 | 60.0968
7 | 2024-02-01 | 63/7 | DA+3 | DRY | 2024-02-11 | 2024-02-15 | Sunny Const. |  | 38.8476 |  | 4 | DB1+6 | 67.8737
8 | 2024-02-01 | 59/6 | DA+3 | DFR | 2024-02-12 | 2024-02-18 | Ganesh Const |  | 38.8476 |  | 6 | DB1+9 | 70.7017
9 | 2024-02-01 | 59/12 | DA+6 | DFR | 2024-02-13 | 2024-02-20 | Chinta Devi |  | 45.413 |  | 7 | DB2+0 | 57.5972
10 | 2024-02-01 | 63/8 | DA+3 | DRY | 2024-02-15 | 2024-02-20 | Sunny Const. |  | 38.8476 |  | 5 | DB2+3 | 60.0968
11 | 2024-02-01 | 60/10 | DA+0 | DFR | 2024-02-15 | 2024-02-21 | Suraj const |  | 37.5044 |  | 6 | DB2+6 | 67.8737
12 | 2024-02-01 | 62/5 | DA+0 | DRY | 2024-02-17 | 2024-02-22 | Sobha Devi |  | 37.5044 |  | 5 | DB2+9 | 70.7017
13 | 2024-02-01 | 59/7 | DA+3 | DRY | 2024-02-18 | 2024-02-24 | Ganesh Const |  | 38.8476 |  | 6 | DC1+0 | 66.3811
14 | 2024-02-01 | 59/10 | DA+0 | DRY | 2024-02-20 | 2024-02-24 | Chinta Devi |  | 37.5044 |  | 4 | DCT+0 | 94.2199
15 | 2024-02-01 | 64/1 | DA+0 | DRY | 2024-02-20 | 2024-02-24 | Sunny Const. |  | 37.5044 |  | 4 | DC1+3 | 69.2287
16 | 2024-02-01 | 60/11 | DA+3 | DRY | 2024-02-21 | 2024-02-26 | Suraj const |  | 38.8476 |  | 5 | DC1+6 | 78.132
17 | 2024-02-01 | 62/4 | DA+3 | DRY | 2024-02-22 | 2024-02-26 | Sobha Devi |  | 38.8476 |  | 4 | DC1+9 | 81.4946
18 | 2024-02-01 | 59/9 | DA+3 | DRY | 2024-02-24 | 2024-02-28 | Chinta Devi |  | 38.8476 |  | 4 | DC2+0 | 66.3811
19 | 2024-02-01 | 62/3 | DA+0 | DRY | 2024-02-26 | 2024-02-28 | Sobha Devi |  | 37.5044 |  | 2 | DC2+3 | 69.2287
20 | 2024-02-01 | 59/8 | DB1+3 | DRY | 2024-02-24 | 2024-02-29 | Ganesh Const |  | 60.0968 |  | 5 | DC2+6 | 78.132
21 | 2024-02-01 | 64/4 | DA+3 | DRY | 2024-02-24 | 2024-02-29 | Sunny Const. |  | 38.8476 |  | 5 | DC2+9 | 81.4946
22 | 2024-02-01 | 60/6 | DA+0 | DRY | 2024-02-26 | 2024-02-29 | Suraj const |  | 37.5044 |  | 3 | DD45+0 | 86.1293
23 | 2024-03-01 | 62/2 | DA+3 | DRY | 2024-02-29 | 2024-03-03 | Sobha Devi |  | 38.8476 |  | 3 | DD45+3 | 89.9096
24 | 2024-03-01 | 64/5 | DA+3 | DRY | 2024-02-29 | 2024-03-04 | Sunny Const. |  | 38.8476 |  | 4 | DD60+0 | 86.1293
25 | 2024-03-01 | 65/2 | DA+0 | DRY | 2024-02-29 | 2024-03-06 | Chinta Devi |  | 37.5044 |  | 6 | DD60+3 | 89.9096
26 | 2024-03-01 | 62/7 | DA+3 | DRY | 2024-03-04 | 2024-03-07 | Sobha Devi |  | 38.8476 |  | 3 | DD60+6 | 100.968
27 | 2024-03-01 | 59/16 | DA+9 | Dry | 2024-02-29 | 2024-03-11 | Ganesh Const. |  | 47.1844 |  | 11 | DD60+9 | 105.0682
28 | 2024-03-01 | 65/4 | DA+0 | DRY | 2024-03-06 | 2024-03-11 | Chinta Devi |  | 37.5044 |  | 5 | DD60+18 | 129.111
29 | 2024-03-01 | 62/8 | DA+0 | DFR | 2024-03-07 | 2024-03-11 | Sobha Devi |  | 37.5044 |  | 4 | DD60+25 | 143.6019
30 | 2024-03-01 | 62/9 | DA+3 | DFR | 2024-03-11 | 2024-03-15 | Sobha Devi |  | 38.8476 |  | 4
31 | 2024-03-01 | 65/3 | DA+3 | DRY | 2024-03-11 | 2024-03-16 | Chinta Devi |  | 38.8476 |  | 5
32 | 2024-03-01 | 60/5 | DA+3 | DRY | 2024-03-11 | 2024-03-17 | Ganesh Const. |  | 38.8476 |  | 6
33 | 2024-03-01 | 62/10 | DA+0 | DFR | 2024-03-15 | 2024-03-18 | Sobha Devi |  | 37.5044 |  | 3
34 | 2024-03-01 | 65/5 | DA+0 | DRY | 2024-03-16 | 2024-03-20 | Chinta Devi |  | 37.5044 |  | 4
35 | 2024-03-01 | 61/6 | DA+3 | DRY | 2024-03-18 | 2024-03-22 | Sobha Devi |  | 38.8476 |  | 4
36 | 2024-03-01 | 60/4 | DA+3 | DFR | 2024-03-18 | 2024-03-23 | Ganesh Const. |  | 38.8476 |  | 5
37 | 2024-03-01 | 65/6 | DA+0 | DRY | 2024-03-20 | 2024-03-26 | Chinta Devi |  | 37.5044 |  | 6
38 | 2024-03-01 | 64/6 | DA+0 | DRY | 2024-03-21 | 2024-03-26 | Sunny Const. |  | 37.5044 |  | 5
39 | 2024-03-01 | 61/7 | DA+9 | Dry | 2024-03-22 | 2024-03-28 | Sobha Devi |  | 47.1844 |  | 6
40 | 2024-03-01 | 64/7 | DA+3 | DRY | 2024-03-26 | 2024-03-30 | Sunny Const. |  | 38.8476 |  | 4
41 | 2024-03-01 | 60/3 | DA+3 | DFR | 2024-03-23 | 2024-03-31 | Ganesh Const. |  | 38.8476 |  | 8
42 | 2024-03-01 | 65/9 | DA+0 | DRY | 2024-03-26 | 2024-03-31 | Chinta Devi |  | 37.5044 |  | 5
43 | 2024-04-01 | 64/8 | DA+3 | DRY | 2024-03-30 | 2024-04-03 | Sunny Const. |  | 38.8476 |  | 4
44 | 2024-04-01 | 65/11 | DA+0 | DRY | 2024-03-31 | 2024-04-04 | Chinta Devi |  | 37.5044 |  | 4
45 | 2024-04-01 | 60/2 | DA+3 | DFR | 2024-03-31 | 2024-04-07 | Ganesh Const. |  | 38.8476 |  | 7
46 | 2024-04-01 | 63/5 | DA+3 | DFR | 2024-04-01 | 2024-04-07 | Suraj Const |  | 38.8476 |  | 6
47 | 2024-04-01 | 64/9 | DA+3 | DRY | 2024-04-03 | 2024-04-08 | Sunny Const. |  | 38.8476 |  | 5
48 | 2024-04-01 | 67/1 | DA+0 | DRY | 2024-04-06 | 2024-04-10 | Chinta Devi |  | 37.5044 |  | 4
49 | 2024-04-01 | 61/0 | DB2+0 | DRY | 2024-04-06 | 2024-04-11 | Sobha Devi |  | 57.5972 |  | 5
50 | 2024-04-01 | 63/4 | DA+0 | DRY | 2024-04-07 | 2024-04-13 | Suraj Const |  | 37.5044 |  | 6
51 | 2024-04-01 | 67/2 | DA+0 | DRY | 2024-04-10 | 2024-04-15 | Chinta Devi |  | 37.5044 |  | 5
52 | 2024-04-01 | 63/3 | DA+3 | DFR | 2024-04-13 | 2024-04-17 | Suraj Const |  | 38.8476 |  | 4
53 | 2024-04-01 | 64/10 | DA+3 | DRY | 2024-04-15 | 2024-04-20 | Chinta Devi |  | 38.8476 |  | 5
54 | 2024-04-01 | 64/2 | DA+3 | DRY | 2024-04-16 | 2024-04-21 | Sunny Const. |  | 38.8476 |  | 5
55 | 2024-04-01 | 61/2 | DA+6 | DFR | 2024-04-16 | 2024-04-22 | Sobha Devi |  | 45.413 |  | 6
56 | 2024-04-01 | 63/2 | DA+0 | DFR | 2024-04-17 | 2024-04-22 | Suraj const |  | 37.5044 |  | 5
57 | 2024-04-01 | 60/1 | DA+6 | DRY | 2024-04-18 | 2024-04-25 | Ganesh Const. |  | 45.413 |  | 7
58 | 2024-04-01 | 64/3 | DA+0 | DRY | 2024-04-21 | 2024-04-26 | Sunny Const. |  | 37.5044 |  | 5
59 | 2024-04-01 | 65/0 | DB1+0 | DRY | 2024-04-21 | 2024-04-27 | Chinta Devi |  | 57.5972 |  | 6
60 | 2024-04-01 | 63/1 | DA+3 | DFR | 2024-04-22 | 2024-04-27 | Suraj const |  | 38.8476 |  | 5
61 | 2024-04-01 | 61/1 | DA+6 | DFR | 2024-04-22 | 2024-04-29 | Sobha Devi |  | 45.413 |  | 7
62 | 2024-05-01 | 65/1 | DA+0 | DRY | 2024-04-27 | 2024-05-03 | Chinta Devi |  | 37.5044 |  | 6
63 | 2024-05-01 | 62/11 | DA+3 | DRY | 2024-04-27 | 2024-05-03 | Suraj const |  | 38.8476 |  | 6
64 | 2024-05-01 | 64/0 | DB2+0 | DRY | 2024-04-27 | 2024-05-05 | Sunny Const. |  | 57.5972 |  | 8
65 | 2024-05-01 | 60/9 | DA+3 | DRY | 2024-04-29 | 2024-05-05 | Sobha Devi |  | 38.8476 |  | 6
66 | 2024-05-01 | 61/3 | DA+6 | DRY | 2024-05-05 | 2024-05-11 | Sobha Devi |  | 45.413 |  | 6
67 | 2024-05-01 | 63/0 | DC1+0 | DFR | 2024-05-03 | 2024-05-12 | Suraj const |  | 66.3811 |  | 9
68 | 2024-05-01 | 61/4 | DA+3 | DRY | 2024-05-11 | 2024-05-16 | Sobha Devi |  | 38.8476 |  | 5
69 | 2024-05-01 | 60/0 | DC1+0 | DRY | 2024-05-05 | 2024-05-18 | Ganesh |  | 66.3811 |  | 13
70 | 2024-05-01 | 61/10 | DA+9 | DRY | 2024-05-12 | 2024-05-19 | Suraj const |  | 47.1844 |  | 7
71 | 2024-05-01 | 61/5 | DA+3 | DRY | 2024-05-16 | 2024-05-22 | Sobha Devi |  | 38.8476 |  | 6
72 | 2024-05-01 | 61/9 | DA+0 | Dry | 2024-05-19 | 2024-05-23 | Suraj const |  | 37.5044 |  | 4
73 | 2024-05-01 | 59/15 | DA+6 | DRY | 2024-05-18 | 2024-05-30 | Ganesh |  | 45.413 |  | 12
74 | 2024-05-01 | 61/8 | DA+6 | DRY | 2024-05-23 | 2024-05-30 | Suraj const |  | 45.413 |  | 7
75 | 2024-05-01 | 55/3 | DA+0 | Sandy | 2024-05-12 | 2024-05-31 | Mansukh lal |  | 37.5044 |  | 19
76 | 2024-06-01 | 57/3 | DA+0 | DRY | 2024-05-29 | 2024-06-11 | Bhuvneshwar |  | 37.5044 |  | 13
77 | 2024-06-01 | 55/4 | DA+0 | Sandy | 2024-06-01 | 2024-06-19 | Mansukh lal |  | 37.5044 |  | 18
78 | 2024-06-01 | 57/4 | DA+0 | Sandy | 2024-06-12 | 2024-06-27 | Bhuvneshwar |  | 37.5044 |  | 15
79 | 2024-07-01 | 62/1 | DA+3 | Sandy | 2024-07-04 | 2024-07-12 | Bhuvneshwar |  | 38.8476 |  | 8
80 | 2024-07-01 | 62/6 | DA+3 | DRY | 2024-07-15 | 2024-07-26 | Bhuvneshwar |  | 38.8476 |  | 11
81 | 2024-08-01 | 57/6 | DA+3 | Sandy | 2024-08-13 | 2024-08-20 | Sobha devi |  | 38.8476 |  | 7
82 | 2024-08-01 | 57/5 | DA+3 | Sandy | 2024-08-20 | 2024-08-26 | Sobha devi |  | 38.8476 |  | 6
83 | 2024-08-01 | 10/18 | DA+3 | DFR | 2024-08-23 | 2024-08-30 | Yogendra Mahto |  | 38.8476 |  | 7
84 | 2024-09-01 | 10/3 | DA+0 | DFR | 2024-08-28 | 2024-09-06 | Jagdish Mahto |  | 37.5044 |  | 9
85 | 2024-09-01 | 10/17 | DA+3 | DFR | 2024-08-30 | 2024-09-08 | Yogendra Mahto |  | 38.8476 |  | 9
86 | 2024-09-01 | 62/0 | DB2+0 | DRY | 2024-08-31 | 2024-09-08 | Sobha devi |  | 57.5972 |  | 8
87 | 2024-09-01 | 50/9 | DA+0 | Sandy | 2024-08-28 | 2024-09-09 | Uma const |  | 37.5044 |  | 12
88 | 2024-09-01 | 16/3 | DA+3 | DRY | 2024-09-06 | 2024-09-13 | Nirmal Mahto |  | 38.8476 |  | 7
89 | 2024-09-01 | 10/19 | DA+0 | DRY | 2024-09-09 | 2024-09-18 | Yogendra Mahto |  | 37.5044 |  | 9
90 | 2024-09-01 | 52/5 | DA+9 | Sandy | 2024-08-27 | 2024-09-19 | Ganesh Sinha |  | 47.1844 |  | 23
91 | 2024-09-01 | 50/10 | DA+0 | Sandy | 2024-09-10 | 2024-09-19 | Uma const |  | 37.5044 |  | 9
92 | 2024-09-01 | 18/2 | DA+0 | DRY | 2024-09-18 | 2024-09-22 | Deglal Mahto |  | 37.5044 |  | 4
93 | 2024-09-01 | 10/20 | DA+3 | DFR | 2024-09-19 | 2024-09-25 | Yogendra Mahto |  | 38.8476 |  | 6
94 | 2024-09-01 | 48/1 | DA+9 | Sandy | 2024-09-08 | 2024-09-25 | Kaushalya const |  | 47.1844 |  | 17
95 | 2024-09-01 | 15/1 | DA+3 | DRY | 2024-09-21 | 2024-09-26 | Jailal Ageria |  | 38.8476 |  | 5
96 | 2024-09-01 | 51/1 | DA+0 | Sandy | 2024-09-19 | 2024-09-26 | Uma const |  | 37.5044 |  | 7
97 | 2024-09-01 | 18/4 | DA+0 | DRY | 2024-09-23 | 2024-09-27 | Deglal Mahto |  | 37.5044 |  | 4
98 | 2024-09-01 | 10/6 | DA+0 | DFR | 2024-09-25 | 2024-09-29 | Jagdish Mahto |  | 37.5044 |  | 4
99 | 2024-09-01 | 52/6 | DA+6 | Sandy | 2024-09-19 | 2024-09-30 | Ganesh Sinha |  | 45.413 |  | 11
100 | 2024-10-01 | 57/7 | DA+3 | DFR | 2024-09-27 | 2024-10-01 | Sobha devi |  | 38.8476 |  | 4
101 | 2024-10-01 | 16/4 | DA+0 | DRY | 2024-09-28 | 2024-10-03 | Nirmal Mahto |  | 37.5044 |  | 5
102 | 2024-10-01 | 14A/1 | DA+3 | DRY | 2024-09-28 | 2024-10-03 | Jailal Ageria |  | 38.8476 |  | 5
103 | 2024-10-01 | 51/2 | DA+0 | Sandy | 2024-09-26 | 2024-10-04 | Uma const |  | 37.5044 |  | 8
104 | 2024-10-01 | 10/14 | DA+3 | DRY | 2024-09-27 | 2024-10-06 | Khublal Mahto |  | 38.8476 |  | 9
105 | 2024-10-01 | 11A/2 | DA+0 | DRY | 2024-09-27 | 2024-10-07 | Rafikul Islam |  | 37.5044 |  | 10
106 | 2024-10-01 | 50/0 | DB2+0 | Sandy | 2024-10-02 | 2024-10-07 | Sobha devi |  | 57.5972 |  | 5
107 | 2024-10-01 | 52/7 | DA+3 | Sandy | 2024-10-01 | 2024-10-07 | Ganesh Sinha |  | 38.8476 |  | 6
108 | 2024-10-01 | 10/9 | DA+0 | DRY | 2024-10-05 | 2024-10-08 | Jagdish Mahto |  | 37.5044 |  | 3
109 | 2024-10-01 | 18/1 | DA+0 | DRY | 2024-10-04 | 2024-10-08 | Deglal Mahto |  | 37.5044 |  | 4
110 | 2024-10-01 | 10/21 | DA+3 | DFR | 2024-10-07 | 2024-10-10 | Bina Devi |  | 38.8476 |  | 3
111 | 2024-10-01 | 17/1 | DA+3 | DRY | 2024-10-05 | 2024-10-10 | Nirmal Mahto |  | 38.8476 |  | 5
112 | 2024-10-01 | 50/1 | DA+6 | Sandy | 2024-10-07 | 2024-10-15 | Sobha Devi |  | 45.413 |  | 8
113 | 2024-10-01 | 50/8 | DA+9 | Sandy | 2024-10-07 | 2024-10-16 | Uma const |  | 47.1844 |  | 9
114 | 2024-10-01 | 10/4 | DA+3 | DFR | 2024-10-12 | 2024-10-17 | Jagdish Mahto |  | 38.8476 |  | 5
115 | 2024-10-01 | 50/3 | DA+6 | Sandy | 2024-10-13 | 2024-10-18 | Sobha Devi |  | 45.413 |  | 5
116 | 2024-10-01 | 17/2 | DA+6 | DRY | 2024-10-11 | 2024-10-19 | Nirmal Mahto |  | 45.413 |  | 8
117 | 2024-10-01 | 48/0 | DC2+0 | Sandy | 2024-09-28 | 2024-10-19 | Kaushalya const |  | 66.3811 |  | 21
118 | 2024-10-01 | 52/8 | DA+6 | Sandy | 2024-10-08 | 2024-10-19 | Ganesh Sinha |  | 45.413 |  | 11
119 | 2024-10-01 | 73/2 | DA+0 | DRY | 2024-10-10 | 2024-10-20 | Sanjeev Kumar |  | 37.5044 |  | 10
120 | 2024-10-01 | 10/8 | DA+3 | DFR | 2024-10-19 | 2024-10-22 | Jagdish Mahto |  | 38.8476 |  | 3
121 | 2024-10-01 | 50/2 | DA+9 | Sandy | 2024-10-18 | 2024-10-24 | Sobha Devi |  | 47.1844 |  | 6
122 | 2024-10-01 | 64/11 | DA+3 | DRY | 2024-10-20 | 2024-10-24 | Chinta devi |  | 38.8476 |  | 4
123 | 2024-10-01 | 16/2 | DA+0 | DRY | 2024-10-20 | 2024-10-26 | Nirmal Mahto |  | 37.5044 |  | 6
124 | 2024-10-01 | 19/0 | DC2+0 | DRY | 2024-10-19 | 2024-10-26 | Deglal Mahto |  | 66.3811 |  | 7
125 | 2024-10-01 | 59/11 | DA+6 | DFR | 2024-10-17 | 2024-10-26 | Uma const |  | 45.413 |  | 9
126 | 2024-10-01 | 16/0 | DC1+0 | DRY | 2024-10-18 | 2024-10-27 | Jailal Ageria |  | 66.3811 |  | 9
127 | 2024-10-01 | 17/3 | DA+0 | DRY | 2024-10-21 | 2024-10-27 | Bina Devi |  | 37.5044 |  | 6
128 | 2024-10-01 | 73/1 | DA+0 | DRY | 2024-10-21 | 2024-10-29 | Sanjeev Kumar |  | 37.5044 |  | 8
129 | 2024-10-01 | 50/4 | DA+9 | Sandy | 2024-10-24 | 2024-10-30 | Sobha Devi |  | 47.1844 |  | 6
130 | 2024-11-01 | 55/6 | DA+0 | Sandy | 2024-10-23 | 2024-11-01 | Jirwa Devi |  | 37.5044 |  | 9
131 | 2024-11-01 | 11A/0 | DB1+0 | DRY | 2024-10-16 | 2024-11-02 | Rafikul Islam |  | 57.5972 |  | 17
132 | 2024-11-01 | 59/3 | DA+3 | DFR | 2024-10-27 | 2024-11-02 | Uma const |  | 38.8476 |  | 6
133 | 2024-11-01 | 50/7 | DA+0 | Sandy | 2024-11-01 | 2024-11-04 | Sobha Devi |  | 37.5044 |  | 3
134 | 2024-11-01 | 10/11 | DA+3 | DRY | 2024-11-02 | 2024-11-05 | Jagdish Mahto |  | 38.8476 |  | 3
135 | 2024-11-01 | 11A/1 | DA+3 | DRY | 2024-10-18 | 2024-11-08 | Rafikul Islam |  | 38.8476 |  | 21
136 | 2024-11-01 | 16/5 | DA+3 | DRY | 2024-11-03 | 2024-11-09 | Bina Devi |  | 38.8476 |  | 6
137 | 2024-11-01 | 16/1 | DA+0 | DRY | 2024-11-05 | 2024-11-09 | Jailal Ageria |  | 37.5044 |  | 4
138 | 2024-11-01 | 59/4 | DA+3 | DFR | 2024-11-01 | 2024-11-09 | Uma const |  | 38.8476 |  | 8
139 | 2024-11-01 | 50/6 | DA+9 | Sandy | 2024-11-04 | 2024-11-10 | Sobha Devi |  | 47.1844 |  | 6
140 | 2024-11-01 | 55/5 | DA+0 | Sandy | 2024-11-01 | 2024-11-12 | Jirwa Devi |  | 37.5044 |  | 11
141 | 2024-11-01 | 73/9 | DA+0 | DRY | 2024-11-09 | 2024-11-13 | Chinta devi |  | 37.5044 |  | 4
142 | 2024-11-01 | 17/0 | DB2+3 | DRY | 2024-11-04 | 2024-11-14 | Nirmal Mahto |  | 60.0968 |  | 10
143 | 2024-11-01 | 49/7 | DA+0 | Sandy | 2024-11-11 | 2024-11-14 | Sobha Devi |  | 37.5044 |  | 3
144 | 2024-11-01 | 73/8 | DA+3 | DRY | 2024-11-13 | 2024-11-17 | Chinta devi |  | 38.8476 |  | 4
145 | 2024-11-01 | 11/5 | DA+0 | DFR | 2024-11-10 | 2024-11-18 | Rafikul Islam |  | 37.5044 |  | 8
146 | 2024-11-01 | 13/2 | DA+3 | DRY | 2024-11-11 | 2024-11-18 | Jailal Ageria |  | 38.8476 |  | 7
147 | 2024-11-01 | 43/9 | DA+9 | Sandy | 2024-11-07 | 2024-11-18 | Yogendra Mahto |  | 47.1844 |  | 11
148 | 2024-11-01 | 49/6 | DA+0 | Sandy | 2024-11-15 | 2024-11-18 | Sobha Devi |  | 37.5044 |  | 3
149 | 2024-11-01 | 73/6 | DA+0 | DRY | 2024-11-17 | 2024-11-20 | Chinta devi |  | 37.5044 |  | 3
150 | 2024-11-01 | 47/10 | DA+6 | Sandy | 2024-11-02 | 2024-11-22 | Kaushalya const |  | 45.413 |  | 20
151 | 2024-11-01 | 49/4 | DA+3 | Sandy | 2024-11-18 | 2024-11-22 | Sobha Devi |  | 38.8476 |  | 4
152 | 2024-11-01 | 59/2 | DA+3 | DFR | 2024-11-12 | 2024-11-24 | Jirwa Devi |  | 38.8476 |  | 12
153 | 2024-11-01 | 52/10 | DA+9 | Sandy | 2024-11-13 | 2024-11-25 | Ganesh Sinha |  | 47.1844 |  | 12
154 | 2024-11-01 | 43/8 | DA+9 | Sandy | 2024-11-19 | 2024-11-27 | Yogendra Mahto |  | 47.1844 |  | 8
155 | 2024-11-01 | 49/5 | DA+3 | Sandy | 2024-11-23 | 2024-11-27 | Sobha Devi |  | 38.8476 |  | 4
156 | 2024-11-01 | 17/5 | DA+3 | DRY | 2024-11-22 | 2024-11-30 | Bina Devi |  | 38.8476 |  | 8
157 | 2024-11-01 | 11A/9 | DA+3 | DRY | 2024-11-24 | 2024-11-30 | Deglal Mahto |  | 38.8476 |  | 6
158 | 2024-11-01 | 49/2 | DA+3 | Sandy | 2024-11-27 | 2024-11-30 | Sobha Devi |  | 38.8476 |  | 3
159 | 2024-11-01 | 72/3 | DA+3 | DRY | 2024-11-24 | 2024-11-30 | Sanjeev Kumar |  | 38.8476 |  | 6
160 | 2024-12-01 | 59/1 | DA+3 | DRY | 2024-11-25 | 2024-12-03 | Jirwa Devi |  | 38.8476 |  | 8
161 | 2024-12-01 | 52/9 | DA+3 | Sandy | 2024-11-26 | 2024-12-05 | Ganesh Sinha |  | 38.8476 |  | 9
162 | 2024-12-01 | 49/3 | DA+3 | Sandy | 2024-12-02 | 2024-12-05 | Sobha Devi |  | 38.8476 |  | 3
163 | 2024-12-01 | 11A/7 | DA+9 | Sandy | 2024-11-28 | 2024-12-06 | Jailal Ageria |  | 47.1844 |  | 8
164 | 2024-12-01 | 11A/3 | DA+3 | DRY | 2024-12-01 | 2024-12-07 | Deglal Mahto |  | 38.8476 |  | 6
165 | 2024-12-01 | 49/1 | DA+0 | Sandy | 2024-12-06 | 2024-12-09 | Sobha Devi |  | 37.5044 |  | 3
166 | 2024-12-01 | 10/12 | DB1+0 | DRY | 2024-11-30 | 2024-12-11 | Jagdish Mahto |  | 57.5972 |  | 11
167 | 2024-12-01 | 73/3 | DA+0 | DRY | 2024-12-09 | 2024-12-13 | Chinta devi |  | 37.5044 |  | 4
168 | 2024-12-01 | 11A/6 | DA+6 | DRY | 2024-12-09 | 2024-12-16 | Deglal Mahto |  | 45.413 |  | 7
169 | 2024-12-01 | 59/0 | DC2+0 | DRY | 2024-12-03 | 2024-12-16 | Jirwa Devi |  | 66.3811 |  | 13
170 | 2024-12-01 | 65/8 | DA+0 | DRY | 2024-12-20 | 2024-12-27 | Sanjeev Kumar |  | 37.5044 |  | 7
171 | 2025-01-01 | 11A/5 | DA+3 | DRY | 2024-12-25 | 2025-01-04 | Deglal Mahto |  | 38.8476 |  | 10
172 | 2025-01-01 | 65/7 | DA+0 | DRY | 2024-12-28 | 2025-01-04 | Sanjeev Kumar |  | 37.5044 |  | 7
173 | 2025-01-01 | 43/0 | DB1+0 | Sandy | 2024-12-25 | 2025-01-07 | Yogendra Mahto |  | 57.5972 |  | 13
174 | 2025-01-01 | 73/0 | DB2+0 | DRY | 2025-01-03 | 2025-01-09 | Chinta devi |  | 57.5972 |  | 6
175 | 2025-01-01 | 53/8 | DA+3 | Sandy | 2025-01-04 | 2025-01-09 | Ganesh Sinha |  | 38.8476 |  | 5
176 | 2025-01-01 | 74/0 | DB2+0 | Sandy | 2025-01-05 | 2025-01-13 | Sunny Const |  | 57.5972 |  | 8
177 | 2025-01-01 | 73/4 | DA+0 | DRY | 2025-01-10 | 2025-01-14 | Chinta devi |  | 37.5044 |  | 4
178 | 2025-01-01 | 43/1 | DA+3 | Sandy | 2025-01-08 | 2025-01-17 | Yogendra Mahto |  | 38.8476 |  | 9
179 | 2025-01-01 | 43/7 | DA+3 | Sandy | 2025-01-11 | 2025-01-18 | Bina Devi |  | 38.8476 |  | 7
180 | 2025-01-01 | 53/7 | DA+3 | Sandy | 2025-01-10 | 2025-01-18 | Ganesh Sinha |  | 38.8476 |  | 8
181 | 2025-01-01 | 73/5 | DA+0 | DRY | 2025-01-15 | 2025-01-19 | Chinta devi |  | 37.5044 |  | 4
182 | 2025-01-01 | 73/7 | DA+0 | DRY | 2025-01-14 | 2025-01-19 | Sunny Const |  | 37.5044 |  | 5
183 | 2025-01-01 | 72/0 | DB2+3 | DRY | 2025-01-21 | 2025-01-27 | Chinta Devi |  | 60.0968 |  | 6
184 | 2025-01-01 | 43/6 | DA+3 | Sandy | 2025-01-19 | 2025-01-29 | Bina Devi |  | 38.8476 |  | 10
185 | 2025-01-01 | 66/0 | DC2+6 | DRY | 2025-01-11 | 2025-01-29 | Sanjeev Kumar |  | 78.132 |  | 18
186 | 2025-01-01 | 53/6 | DA+6 | Sandy | 2025-01-19 | 2025-01-30 | Ganesh Sinha |  | 45.413 |  | 11
187 | 2025-02-01 | 72/1 | DA+3 | DRY | 2025-01-28 | 2025-02-02 | Chinta Devi |  | 38.8476 |  | 5
188 | 2025-02-01 | 65/10 | DA+0 | DRY | 2025-01-29 | 2025-02-06 | Sanjeev Kumar |  | 37.5044 |  | 8
189 | 2025-02-01 | 72/2 | DA+0 | DRY | 2025-02-02 | 2025-02-06 | Chinta Devi |  | 37.5044 |  | 4
190 | 2025-02-01 | 51/0 | DC2+0 | Sandy | 2025-01-31 | 2025-02-07 | Sunny Const. |  | 66.3811 |  | 7
191 | 2025-02-01 | 1A/1 | DA+6 | DFR | 2025-01-31 | 2025-02-10 | Bina Devi |  | 45.413 |  | 10
192 | 2025-02-01 | 71/8 | DA+3 | DRY | 2025-02-07 | 2025-02-10 | Chinta Devi |  | 38.8476 |  | 3
193 | 2025-02-01 | 52/0 | DC2+0 | Sandy | 2025-02-08 | 2025-02-14 | Sunny Const. |  | 66.3811 |  | 6
194 | 2025-02-01 | 49/0 | DD45+0 | Sandy | 2025-02-05 | 2025-02-14 | Sobha Devi |  | 86.1293 |  | 9
195 | 2025-02-01 | 71/7 | DA+3 | DRY | 2025-02-11 | 2025-02-15 | Chinta Devi |  | 38.8476 |  | 4
196 | 2025-02-01 | 1A/2 | DA+0 | DRY | 2025-02-11 | 2025-02-18 | Bina Devi |  | 37.5044 |  | 7
197 | 2025-02-01 | 71/6 | DA+0 | DRY | 2025-02-16 | 2025-02-19 | Chinta Devi |  | 37.5044 |  | 3
198 | 2025-02-01 | 50/5 | DA+9 | Sandy | 2025-02-15 | 2025-02-20 | Sobha Devi |  | 47.1844 |  | 5
199 | 2025-02-01 | 71/5 | DA+3 | DRY | 2025-02-20 | 2025-02-24 | Chinta Devi |  | 38.8476 |  | 4
200 | 2025-02-01 | 1A/3 | DA+0 | DRY | 2025-02-19 | 2025-02-28 | Bina Devi |  | 37.5044 |  | 9
201 | 2025-03-01 | 71/4 | DA+3 | DRY | 2025-02-25 | 2025-03-01 | Chinta Devi |  | 38.8476 |  | 4
202 | 2025-03-01 | 53/5 | DA+3 | Sandy | 2025-03-01 | 2025-03-07 | Ganesh Sinha |  | 38.8476 |  | 6
203 | 2025-03-01 | 71/3 | DA+6 | DRY | 2025-03-02 | 2025-03-07 | Chinta Devi |  | 45.413 |  | 5
204 | 2025-03-01 | 58/0 | DC1+3 | DFR | 2025-02-26 | 2025-03-10 | Jirwa Devi |  | 69.2287 |  | 12
205 | 2025-03-01 | 71/2 | DA+3 | DRY | 2025-03-08 | 2025-03-12 | Chinta Devi |  | 38.8476 |  | 4
206 | 2025-03-01 | 70/3 | DA+3 | DRY | 2025-03-08 | 2025-03-16 | Sanjeev kumar |  | 38.8476 |  | 8
207 | 2025-03-01 | 53/4 | DA+0 | Sandy | 2025-03-09 | 2025-03-17 | Ganesh Sinha |  | 37.5044 |  | 8
208 | 2025-03-01 | 71/1 | DA+3 | DRY | 2025-03-13 | 2025-03-18 | Chinta Devi |  | 38.8476 |  | 5
209 | 2025-03-01 | 53/3 | DA+6 | Sandy | 2025-03-18 | 2025-03-25 | Ganesh Sinha |  | 45.413 |  | 7
210 | 2025-03-01 | 71/0 | DB2+3 | DRY | 2025-03-19 | 2025-03-25 | Chinta Devi |  | 60.0968 |  | 6
211 | 2025-03-01 | 70/5 | DA+3 | DRY | 2025-03-20 | 2025-03-29 | Sanjeev kumar |  | 38.8476 |  | 9
212 | 2025-03-01 | 53/2 | DA+0 | Sandy | 2025-03-26 | 2025-03-31 | Ganesh Sinha |  | 37.5044 |  | 5
213 | 2025-03-01 | 70/11 | DA+3 | DRY | 2025-03-26 | 2025-03-31 | Chinta Devi |  | 38.8476 |  | 5
214 | 2025-04-01 | 47/9 | DA+3 | Sandy | 2025-03-31 | 2025-04-02 | Sobha Devi |  | 38.8476 |  | 2
215 | 2025-04-01 | 70/10 | DA+3 | DRY | 2025-03-31 | 2025-04-04 | Chinta Devi |  | 38.8476 |  | 4
216 | 2025-04-01 | 47/8 | DA+0 | Sandy | 2025-04-03 | 2025-04-06 | Sobha Devi |  | 37.5044 |  | 3
217 | 2025-04-01 | 70/9 | DA+3 | DRY | 2025-04-06 | 2025-04-09 | Chinta Devi |  | 38.8476 |  | 3
218 | 2025-04-01 | 53/1 | DA+9 | Sandy | 2025-04-02 | 2025-04-11 | Ganesh Sinha |  | 47.1844 |  | 9
219 | 2025-04-01 | 68/0 | DD45+0 | DRY | 2025-03-13 | 2025-04-14 | Sunny Const. |  | 86.1293 |  | 32
220 | 2025-04-01 | 53/0 | DB2+9 | Sandy | 2025-04-12 | 2025-04-28 | Ganesh Sinha |  | 70.7017 |  | 16
221 | 2025-05-01 | 70/4 | DA+3 | DRY | 2025-04-27 | 2025-05-02 | Chinta devi |  | 38.8476 |  | 5
222 | 2025-05-01 | 67/0 | DC1+9 | DRY | 2025-05-20 | 2025-05-29 | Sunny Construction |  | 81.4946 |  | 9
223 | 2025-06-01 | 1A/4 | DA+3 | DFR | 2025-05-10 | 2025-06-11 | Bhairo Mahto |  | 38.8476 | Crane erection+Derrick Pole | 32
224 | 2025-06-01 | 1A/6 | DA+0 | Sandy | 2025-06-11 | 2025-06-20 | Bhairo Mahto |  | 37.5044 | Crane erection+Derrick Pole | 9
225 | 2025-06-01 | 70/7 | DA+3 | DRY | 2025-06-17 | 2025-06-22 | Jwala Singh |  | 38.8476 | Derrick | 5
226 | 2025-06-01 | 70/6 | DA+3 | DRY | 2025-05-19 | 2025-06-28 | Satyam Enterprises (Santosh) |  | 38.8476 | Derrick | 40
227 | 2025-06-01 | 1A/7 | DA+3 | Sandy | 2025-06-04 | 2025-06-30 | Anil Kumar+Kewat |  | 38.8476 | Crane erection+Derrick Pole | 26
228 | 2025-06-01 | 70/2 | DA+3 | DRY | 2025-06-22 | 2025-06-30 | Satyam Enterprises (Vijay) |  | 38.8476 | Derrick | 8
229 | 2025-07-01 | 8/9 | DA+3 | DFR | 2025-06-27 | 2025-07-01 | Jwala Singh |  | 38.8476 | Derrick | 4
230 | 2025-07-01 | 69/1 | DA+3 | DRY | 2025-06-28 | 2025-07-03 | Jwala Singh (Suraj Kumar) |  | 38.8476 | Derrick | 5
231 | 2025-07-01 | 70/1 | DA+3 | DRY | 2025-07-01 | 2025-07-08 | Satyam Enterprises (Vijay) |  | 38.8476 | Derrick | 7
232 | 2025-07-01 | 8/10 | DA+3 | DFR | 2025-07-07 | 2025-07-19 | Jwala Singh |  | 38.8476 | Derrick | 12
233 | 2025-07-01 | 70/0 | DC1+0 | DRY | 2025-07-03 | 2025-07-14 | Jwala Singh (Suraj Kumar) |  | 66.3811 | Derrick | 11
234 | 2025-07-01 | 70/8 | DA+3 | DRY | 2025-07-08 | 2025-07-14 | Satyam Enterprises (Vijay) |  | 38.8476 | Derrick | 6
235 | 2025-07-01 | 1A/8 | DA+0 | Sandy | 2025-06-11 | 2025-07-15 | Anil Kumar+Kewat |  | 37.5044 | Crane erection+Derrick Pole | 34
236 | 2025-07-01 | 2/8 | DA+0 | Sandy | 2025-07-11 | 2025-07-16 | Arawali-2 |  | 37.5044 | Derrick | 5
237 | 2025-07-01 | 69/0 | DB2+0 | DFR | 2025-07-14 | 2025-07-21 | Jwala Singh (Suraj Kumar) |  | 57.5972 | Derrick | 7
238 | 2025-07-01 | 44/3 | DA+0 | Sandy | 2025-07-19 | 2025-07-22 | Satyam Enterprises |  | 37.5044 | Derrick | 3
239 | 2025-07-01 | 2/9 | DA+0 | DRY | 2025-07-16 | 2025-07-23 | Arawali-2 |  | 37.5044 | Derrick | 7
240 | 2025-07-01 | 18/3 | DA+0 | DRY | 2025-07-14 | 2025-07-23 | Priyanka Devi-2 |  | 37.5044 | Derrick | 9
241 | 2025-07-01 | 26/2 | DA+3 | DFR | 2025-07-21 | 2025-07-24 | Hazarilal Yadav-Poonam Kumari |  | 38.8476 | Derrick | 3
242 | 2025-07-01 | 1A/5 | DA+0 | DRY | 2025-07-10 | 2025-07-26 | Bhairo Mahto+Kewat |  | 37.5044 | Derrick | 16
243 | 2025-07-01 | 44/2 | DA+0 | Sandy | 2025-07-23 | 2025-07-26 | Satyam Enterprises |  | 37.5044 | Derrick | 3
244 | 2025-07-01 | 26/3 | DA+0 | DRY | 2025-07-25 | 2025-07-28 | Hazarilal Yadav-Poonam Kumari |  | 37.5044 | Derrick | 3
245 | 2025-07-01 | 44/4 | DA+9 | Sandy | 2025-07-23 | 2025-07-28 | Satyam Enterprises |  | 47.1844 | Derrick | 5
246 | 2025-07-01 | 44/1 | DA+0 | Sandy | 2025-07-26 | 2025-07-29 | Satyam Enterprises |  | 37.5044 | Derrick | 3
247 | 2025-07-01 | 1A/0 | DD60+0 | DRY | 2025-07-01 | 2025-07-29 | Bhairo Mahto+Priyanka Devi (Subodh) |  | 86.1293 | Crane erection+Derrick | 28
248 | 2025-07-01 | 2/7 | DA+3 | Sandy | 2025-07-23 | 2025-07-30 | Arawali-2 |  | 38.8476 | Derrick | 7
249 | 2025-07-01 | 25/4 | DA+0 | Sandy | 2025-07-27 | 2025-07-31 | Pusplata (Praful) |  | 37.5044 | Derrick | 4
250 | 2025-07-01 | 27/2 | DA+3 | DFR | 2025-07-21 | 2025-07-31 | Dharmendra-Munnilal (Pusplata) |  | 38.8476 | Derrick | 10
251 | 2025-07-01 | 27/3 | DA+3 | DFR | 2025-07-27 | 2025-07-31 | Pusplata (Kailash) |  | 38.8476 | Derrick | 4
252 | 2025-08-01 | 44/0 | DB1+3 | Sandy | 2025-07-29 | 2025-08-03 | Satyam Enterprises |  | 60.0968 | Derrick | 5
253 | 2025-08-01 | 12/0 | DD60+0 | DRY | 2025-07-25 | 2025-08-02 | Arawali-1 |  | 86.1293 | Derrick | 8
254 | 2025-08-01 | 29/1 | DA+3 | DRY | 2025-07-30 | 2025-08-04 | Jwala Singh |  | 38.8476 | Derrick | 5
255 | 2025-08-01 | 44/7 | DA+9 | Sandy | 2025-07-28 | 2025-08-03 | Satyam Enterprises |  | 47.1844 | Derrick | 6
256 | 2025-08-01 | 47/7 | DA+3 | Sandy | 2025-07-26 | 2025-08-05 | Vinay Construction |  | 38.8476 | Derrick | 10
257 | 2025-08-01 | 19/5 | DA+0 | DRY | 2025-08-01 | 2025-08-05 | Priyanka Devi |  | 37.5044 | Derrick | 4
258 | 2025-08-01 | 30/3 | DA+3 | Sandy | 2025-08-01 | 2025-08-06 | Pusplata (Kailash) |  | 38.8476 | Derrick | 5
259 | 2025-08-01 | 44/10 | DB1+9 | Sandy | 2025-07-28 | 2025-08-06 | Satyam Enterprises |  | 70.7017 | Derrick | 9
260 | 2025-08-01 | 25/3 | DA+0 | Sandy | 2025-07-31 | 2025-08-09 | Pusplata (Praful) |  | 37.5044 | Derrick | 9
261 | 2025-08-01 | 44/5 | DA+9 | Sandy | 2025-08-04 | 2025-08-09 | Satyam Enterprises |  | 47.1844 | Derrick | 5
262 | 2025-08-01 | 4/1 | DA+0 | DRY | 2025-07-25 | 2025-08-09 | Bhairo Mahto |  | 37.5044 | Derrick | 15
263 | 2025-08-01 | 8/12 | DA+0 | DRY | 2025-08-04 | 2025-08-09 | Jwala Singh |  | 37.5044 | Derrick | 5
264 | 2025-08-01 | 29/0 | DB1+0 | DRY | 2025-07-30 | 2025-08-12 | Jwala Singh |  | 57.5972 | Derrick | 13
265 | 2025-08-01 | 55/8 | DA+6 | Sandy | 2025-08-07 | 2025-08-13 | Shobha Devi |  | 45.413 | Derrick | 6
266 | 2025-08-01 | 2/0 | DC1+0 | DRY | 2025-07-29 | 2025-08-13 | Priyanka Devi (Subodh) |  | 66.3811 | Derrick | 15
267 | 2025-08-01 | 44/6 | DB1+3 | Sandy | 2025-08-09 | 2025-08-16 | Satyam Enterprises |  | 60.0968 | Derrick | 7
268 | 2025-08-01 | 47/2 | DA+9 | Sandy | 2025-08-04 | 2025-08-16 | Vinay Construction |  | 47.1844 | Derrick | 12
269 | 2025-08-01 | 40/3 | DA+3 | Sandy | 2025-08-10 | 2025-08-17 | Rahul Kumar |  | 38.8476 | Derrick | 7
270 | 2025-08-01 | 45/0 | DC2+0 | Sandy | 2025-08-06 | 2025-08-17 | Sintu_Pawan (Satyam Enterprises) |  | 66.3811 | Derrick | 11
271 | 2025-08-01 | 55/7 | DA+0 | Sandy | 2025-08-13 | 2025-08-17 | Shobha Devi |  | 37.5044 | Derrick | 4
272 | 2025-08-01 | 2/3 | DA+3 | Sandy | 2025-08-04 | 2025-08-17 | Sheetal Singh |  | 38.8476 | Derrick | 13
273 | 2025-08-01 | 30/5 | DA+3 | DRY | 2025-08-06 | 2025-08-17 | Pusplata (Kailash) |  | 38.8476 | Derrick | 11
274 | 2025-08-01 | 27/4 | DA+3 | DFR | 2025-08-09 | 2025-08-17 | Pusplata (Ramchandra) |  | 38.8476 | Derrick | 8
275 | 2025-08-01 | 43/11 | DA+3 | Sandy | 2025-08-12 | 2025-08-18 | Satyam-Manish |  | 38.8476 | Derrick | 6
276 | 2025-08-01 | 17/4 | DA+3 | DRY | 2025-08-13 | 2025-08-18 | Pusplata_Pankaj |  | 38.8476 | Derrick | 5
277 | 2025-08-01 | 28/5 | DA+9 | Sandy | 2025-08-12 | 2025-08-19 | Jwala Singh |  | 47.1844 | Derrick | 7
278 | 2025-08-01 | 2/5 | DA+3 | Sandy | 2025-08-04 | 2025-08-19 | Usha Tower |  | 38.8476 | Derrick | 15
279 | 2025-08-01 | 1/0 | DD60+0 | DRY | 2025-07-07 | 2025-08-20 | Bhairo Mahto+Kewat |  | 86.1293 | Derrick | 44
280 | 2025-08-01 | 41/1 | DB1+9 | Sandy | 2025-08-10 | 2025-08-21 | Gauri Shankar |  | 70.7017 | Derrick | 11
281 | 2025-08-01 | 30/6 | DA+0 | DRY | 2025-08-17 | 2025-08-21 | Pusplata (Kailash) |  | 37.5044 | Derrick | 4
282 | 2025-08-01 | 4/2 | DA+0 | DRY | 2025-07-30 | 2025-08-22 | Bhairo Mahto |  | 37.5044 | Derrick | 23
283 | 2025-08-01 | 47/4 | DA+3 | Sandy | 2025-08-06 | 2025-08-22 | Vinay Construction |  | 38.8476 | Derrick | 16
284 | 2025-08-01 | 27/1 | DA+3 | DFR | 2025-08-16 | 2025-08-23 | Pusplata (Dharamveer) |  | 38.8476 | Derrick | 7
285 | 2025-08-01 | 44/9 | DA+9 | Sandy | 2025-08-17 | 2025-08-24 | Satyam Enterprises |  | 47.1844 | Derrick | 7
286 | 2025-08-01 | 55/1 | DA+0 | WFR | 2025-08-17 | 2025-08-24 | Sunny Construction |  | 37.5044 | Derrick | 7
287 | 2025-08-01 | 40/2 | DA+3 | Sandy | 2025-08-18 | 2025-08-24 | Rahul Kumar |  | 38.8476 | Derrick | 6
288 | 2025-08-01 | 28/2 | DA+0 | DFR | 2025-08-19 | 2025-08-25 | Jwala Singh |  | 37.5044 | Derrick | 6
289 | 2025-08-01 | 18/0 | DC2+0 | DRY | 2025-08-18 | 2025-08-25 | Pusplata |  | 66.3811 | Derrick | 7
290 | 2025-08-01 | 4/4 | DA+0 | DRY | 2025-08-20 | 2025-08-25 | Pusplata (Ashok) |  | 37.5044 | Derrick | 5
291 | 2025-08-01 | 57/2 | DA+3 | DRY | 2025-08-21 | 2025-08-25 | Sobha Devi |  | 38.8476 | Derrick | 4
292 | 2025-08-01 | 44/11 | DA+0 | Sandy | 2025-08-19 | 2025-08-25 | Chinta Devi |  | 37.5044 | Derrick | 6
293 | 2025-08-01 | 31/1 | DA+0 | DRY | 2025-08-22 | 2025-08-26 | Pusplata (Kailash) |  | 37.5044 | Derrick | 4
294 | 2025-08-01 | 47/3 | DA+9 | Sandy | 2025-08-17 | 2025-08-29 | Vinay Construction |  | 47.1844 | Derrick | 12
295 | 2025-08-01 | 57/1 | DA+0 | Sandy | 2025-08-21 | 2025-08-29 | Sobha Devi |  | 37.5044 | Derrick | 8
296 | 2025-08-01 | 30/1 | DA+0 | Sandy | 2025-08-25 | 2025-08-30 | Pusplata (Deepak) |  | 37.5044 | Derrick | 5
297 | 2025-08-01 | 43/10 | DA+3 | Sandy | 2025-08-25 | 2025-08-30 | Satyam Enterprises (Pawan) |  | 38.8476 | Derrick | 5
298 | 2025-08-01 | 36/2 | DA+0 | Sandy | 2025-08-22 | 2025-08-30 | Ganesh Sinha |  | 37.5044 | Derrick | 8
299 | 2025-08-01 | 52/3 | DA+9 | Sandy | 2025-08-17 | 2025-08-30 | Jirwa Devi |  | 47.1844 | Derrick | 13
300 | 2025-08-01 | 8/1 | DA+3 | DRY | 2025-08-23 | 2025-08-31 | Bhairo Mahto |  | 38.8476 | Derrick | 8
301 | 2025-08-01 | 54/5 | DA+9 | Sandy | 2025-08-17 | 2025-08-31 | Sunny Construction |  | 47.1844 | Derrick | 14
302 | 2025-08-01 | 4/3 | DA+0 | DRY | 2025-08-29 | 2025-08-31 | Pusplata (Ashok) |  | 37.5044 | Derrick | 2
303 | 2025-08-01 | 45/1 | DA+9 | Sandy | 2025-08-25 | 2025-08-31 | Chinta Devi |  | 47.1844 | Derrick | 6
304 | 2025-09-01 | 14A/0 | DC1+0 | DRY | 2025-08-26 | 2025-09-03 | Pusplata (Santosh/Pankaj Singh) |  | 66.3811 | Derrick | 8
305 | 2025-09-01 | 20/3 | DA+0 | DRY | 2025-08-26 | 2025-09-03 | Priyanka Devi (Santosh) |  | 37.5044 | Derrick | 8
306 | 2025-09-01 | 31/2 | DA+0 | DRY | 2025-08-26 | 2025-09-02 | Pusplata (Kailash) |  | 37.5044 | Derrick | 7
307 | 2025-09-01 | 27/0 | DC1+0 | DFR | 2025-08-23 | 2025-09-03 | Pusplata (Dharamveer) |  | 66.3811 | Derrick | 11
308 | 2025-09-01 | 43/5 | DA+3 | DRY | 2025-08-29 | 2025-09-03 | Satyam Enterprises (Manish) |  | 38.8476 | Derrick | 5
309 | 2025-09-01 | 8/4 | DA+3 | DRY | 2025-08-29 | 2025-09-04 | Jwala Singh |  | 38.8476 | Derrick | 6
310 | 2025-09-01 | 21/0 | DB2+0 | DRY | 2025-09-02 | 2025-09-05 | Sudheer-2 (Priyanka Devi) |  | 57.5972 | Derrick | 3
311 | 2025-09-01 | 36/3 | DA+0 | Sandy | 2025-08-30 | 2025-09-06 | Ganesh Sinha |  | 37.5044 | Derrick | 7
312 | 2025-09-01 | 47/6 | DA+3 | Sandy | 2025-08-22 | 2025-09-06 | Vinay Construction |  | 38.8476 | Derrick | 15
313 | 2025-09-01 | 54/4 | DA+9 | Sandy | 2025-09-01 | 2025-09-06 | Sunny Construction |  | 47.1844 | Derrick | 5
314 | 2025-09-01 | 26/0 | DB1+0 | DFR | 2025-08-26 | 2025-09-06 | Pusplata (rajaram) |  | 57.5972 | Derrick | 11
315 | 2025-09-01 | 47/1 | DA+3 | Sandy | 2025-09-01 | 2025-09-07 | Chinta Devi |  | 38.8476 | Derrick | 6
316 | 2025-09-01 | 20/2 | DA+0 | DRY | 2025-09-02 | 2025-09-07 | Priyanka Devi (Sudheer) |  | 37.5044 | Derrick | 5
317 | 2025-09-01 | 24/0 | DD45+3 | DRY | 2025-08-26 | 2025-09-07 | Pusplata (Praphul) |  | 89.9096 | Derrick | 12
318 | 2025-09-01 | 2/4 | DA+3 | Sandy | 2025-08-24 | 2025-09-09 | Sheetal Singh-2 |  | 38.8476 | Derrick | 16
319 | 2025-09-01 | 2/6 | DA+3 | Sandy | 2025-08-24 | 2025-09-09 | Anvi Construction |  | 38.8476 | Derrick | 16
320 | 2025-09-01 | 32/1 | DA+3 | Sandy | 2025-09-03 | 2025-09-10 | Pusplata (Kailash) |  | 38.8476 | Derrick | 7
321 | 2025-09-01 | 52/4 | DA+9 | Sandy | 2025-09-01 | 2025-09-10 | Jirwa Devi |  | 47.1844 | Derrick | 9
322 | 2025-09-01 | 34/3 | DA+0 | Sandy | 2025-09-03 | 2025-09-11 | Satyam Enterprises (Vijay) |  | 37.5044 | Derrick | 8
323 | 2025-09-01 | 21/4 | DA+3 | Sandy | 2025-09-09 | 2025-09-12 | Priyanka Devi (Sudheer) |  | 38.8476 | Derrick | 3
324 | 2025-09-01 | 28/0 | DB2+0 | DFR | 2025-09-03 | 2025-09-12 | Jwala Singh-1 |  | 57.5972 | Derrick | 9
325 | 2025-09-01 | 6/2 | DA+0 | DFR | 2025-09-05 | 2025-09-12 | Usha Tower |  | 37.5044 | Derrick | 7
326 | 2025-09-01 | 54/3 | DA+6 | Sandy | 2025-09-07 | 2025-09-12 | Sunny Construction |  | 45.413 | Derrick | 5
327 | 2025-09-01 | 2/1 | DA+3 | Sandy | 2025-09-03 | 2025-09-13 | Sheetal Singh-1 |  | 38.8476 | Derrick | 10
328 | 2025-09-01 | 56/0 | DD60+25 | Sandy | 2025-08-30 | 2025-09-14 | Shobha Devi |  | 143.6019 | Derrick+Crane | 15
329 | 2025-09-01 | 26/1 | DA+0 | DRY | 2025-09-07 | 2025-09-16 | Pusplata (rajaram) |  | 37.5044 | Derrick | 9
330 | 2025-09-01 | 36/1 | DA+3 | Sandy | 2025-08-29 | 2025-09-16 | Nirmal Mahto |  | 38.8476 | Derrick | 18
331 | 2025-09-01 | 36/4 | DA+6 | Sandy | 2025-09-07 | 2025-09-16 | Ganesh Sinha |  | 45.413 | Derrick | 9
332 | 2025-09-01 | 54/1 | DA+3 | Sandy | 2025-09-13 | 2025-09-18 | Sunny Construction |  | 38.8476 | Derrick | 5
333 | 2025-09-01 | 8/5 | DA+3 | DRY | 2025-09-12 | 2025-09-18 | Jwala Singh-2 |  | 38.8476 | Derrick | 6
334 | 2025-09-01 | 52/2 | DA+6 | Sandy | 2025-09-10 | 2025-09-20 | Jirwa Devi |  | 45.413 | Derrick | 10
335 | 2025-09-01 | 2/2 | DA+3 | Sandy | 2025-09-09 | 2025-09-22 | Priyanka Devi (Subodh) |  | 38.8476 | Derrick | 13
336 | 2025-09-01 | 21/5 | DA+6 | DFR | 2025-09-19 | 2025-09-22 | Priyanka Devi (Sudheer) |  | 45.413 | Derrick | 3
337 | 2025-09-01 | 54/2 | DA+3 | Sandy | 2025-09-19 | 2025-09-22 | Sunny Construction |  | 38.8476 | Derrick | 3
338 | 2025-09-01 | 43/3 | DA+0 | DRY | 2025-09-09 | 2025-09-22 | Vivek Ganju |  | 37.5044 | Derrick | 13
339 | 2025-09-01 | 29/3 | DA+0 | Sandy | 2025-09-10 | 2025-09-23 | Jwala Singh-1 |  | 37.5044 | Derrick | 13
340 | 2025-09-01 | 8/2 | DA+3 | DRY | 2025-09-12 | 2025-09-23 | Bhairo Mahto |  | 38.8476 | Derrick | 11
341 | 2025-09-01 | 47/0 | DD60+25 | Sandy | 2025-09-09 | 2025-09-25 | Chinta Devi |  | 143.6019 | Derrick+Crane | 16
342 | 2025-09-01 | 27/11 | DA+3 | DRY | 2025-08-29 | 2025-09-26 | Pusplata (Ramchandra) |  | 38.8476 | Derrick | 28
343 | 2025-09-01 | 36/0 | DB2+0 | Sandy | 2025-09-16 | 2025-09-27 | Nirmal Mahto |  | 57.5972 | Derrick | 11
344 | 2025-09-01 | 37/0 | DB2+0 | Sandy | 2025-09-16 | 2025-09-27 | Ganesh Sinha |  | 57.5972 | Derrick | 11
345 | 2025-09-01 | 20/0 | DB2+0 | Sandy | 2025-09-20 | 2025-09-29 | Priyanka Devi (Sontosh) |  | 57.5972 | Derrick | 9
346 | 2025-09-01 | 47/5 | DA+0 | Sandy | 2025-09-07 | 2025-09-29 | Vinay Construction/ Chinta Devi |  | 37.5044 | Derrick | 22
347 | 2025-09-01 | 57/0 | DD60+25 | Sandy | 2025-09-15 | 2025-09-29 | Shobha Devi |  | 143.6019 | Derrick+Crane | 14
348 | 2025-09-01 | 52/1 | DA+6 | Sandy | 2025-09-20 | 2025-09-30 | Jirwa Devi |  | 45.413 | Derrick | 10
349 | 2025-09-01 | 54/0 | DB1+6 | Sandy | 2025-09-22 | 2025-09-30 | Sunny Construction |  | 67.8737 | Derrick | 8
350 | 2025-09-01 | 21/3 | DA+6 | Sandy | 2025-09-10 | 2025-09-30 | Shri Shyam Construction |  | 45.413 | Derrick | 20
351 | 2025-10-01 | 6/1 | DA+0 | DFR | 2025-09-25 | 2025-10-03 | Sheetal Singh-1 |  | 37.5044 | Derrick | 8
352 | 2025-10-01 | 35/5 | DA+0 | Sandy | 2025-09-27 | 2025-10-06 | Nirmal Mahto |  | 37.5044 | Derrick | 9
353 | 2025-10-01 | 42/6 | DA+0 | Sandy | 2025-09-22 | 2025-10-07 | Vivek Ganju |  | 37.5044 | Derrick | 15
354 | 2025-10-01 | 40/0 | DC2+0 | Sandy | 2025-09-29 | 2025-10-08 | Shobha Devi |  | 66.3811 | Derrick | 9
355 | 2025-10-01 | 10/1 | DA+0 | DRY | 2025-10-03 | 2025-10-10 | Priyanka Devi (Subodh) |  | 37.5044 | Derrick | 7
356 | 2025-10-01 | 55/0 | DB1+6 | Sandy | 2025-09-30 | 2025-10-11 | Sunny Construction |  | 67.8737 | Derrick | 11
357 | 2025-10-01 | 30/2 | DA+0 | Sandy | 2025-09-30 | 2025-10-12 | Jirwa Devi |  | 37.5044 | Derrick | 12
358 | 2025-10-01 | 35/4 | DA+0 | DRY | 2025-10-07 | 2025-10-13 | Nirmal Mahto |  | 37.5044 | Derrick | 6
359 | 2025-10-01 | 55/2 | DA+0 | WFR | 2025-10-12 | 2025-10-14 | Sunny Construction |  | 37.5044 | Derrick | 2
360 | 2025-10-01 | 37/1 | DA+9 | Sandy | 2025-10-10 | 2025-10-17 | Ganesh Sinha |  | 47.1844 | Derrick | 7
361 | 2025-10-01 | 39/0 | DB2+6 | Sandy | 2025-10-14 | 2025-10-18 | Shobha Devi |  | 67.8737 | Derrick | 4
362 | 2025-10-01 | 46/0 | DD60+25 | Sandy | 2025-09-29 | 2025-10-18 | Chinta Devi |  | 143.6019 | Derrick | 19
363 | 2025-10-01 | 35/2 | DB1+0 | Sandy | 2025-10-14 | 2025-10-22 | Nirmal Mahto |  | 57.5972 | Derrick | 8
364 | 2025-10-01 | 39/1 | DA+0 | Sandy | 2025-10-18 | 2025-10-22 | Shobha Devi |  | 37.5044 | Derrick | 4
365 | 2025-10-01 | 29/4 | DA+6 | DRY | 2025-10-13 | 2025-10-23 | Jirwa Devi |  | 45.413 | Derrick | 10
366 | 2025-10-01 | 37/2 | DA+3 | Sandy | 2025-10-18 | 2025-10-24 | Ganesh Sinha |  | 38.8476 | Derrick | 6
367 | 2025-10-01 | 11/4 | DA+0 | Sandy | 2025-10-17 | 2025-10-24 | Devi Construction |  | 37.5044 | Derrick | 7
368 | 2025-10-01 | 35/0 | DB2+6 | Sandy | 2025-10-16 | 2025-10-26 | Sanjeev Kumar |  | 67.8737 | Derrick | 10
369 | 2025-10-01 | 38/4 | DA+9 | Sandy | 2025-10-22 | 2025-10-26 | Shobha Devi |  | 47.1844 | Derrick | 4
370 | 2025-10-01 | 41/2 | DA+0 | Sandy | 2025-10-10 | 2025-10-27 | Vinay Construction |  | 37.5044 | Derrick | 17
371 | 2025-10-01 | 37/3 | DA+0 | Sandy | 2025-10-25 | 2025-10-30 | Ganesh Sinha |  | 37.5044 | Derrick | 5
372 | 2025-10-01 | 35/1 | DA+9 | Sandy | 2025-10-22 | 2025-10-31 | Nirmal Mahto |  | 47.1844 | Derrick | 9
373 | 2025-10-01 | 19/2 | DA+0 | DRY | 2025-10-20 | 2025-10-31 | Shri Shyam Construction |  | 37.5044 | Derrick | 11
374 | 2025-10-01 | 44/8 | DCT+0 | Sandy | 2025-10-18 | 2025-10-31 | Chinta Devi |  | 94.2199 | Derrick | 13
375 | 2025-10-01 | 38/0 | DB2+6 | Sandy | 2025-10-27 | 2025-10-31 | Shobha Devi |  | 67.8737 | Derrick | 4
376 | 2025-11-01 | 34/4 | DA+0 | Sandy | 2025-10-27 | 2025-11-04 | Sanjeev Kumar |  | 37.5044 | Derrick | 8
377 | 2025-11-01 | 40/1 | DA+6 | Sandy | 2025-11-01 | 2025-11-06 | Shobha Devi |  | 45.413 | Derrick | 5
378 | 2025-11-01 | 38/3 | DA+9 | Sandy | 2025-10-09 | 2025-11-07 | Shobha Devi |  | 47.1844 | Derrick | 29
379 | 2025-11-01 | 34/1 | DA+9 | Sandy | 2025-10-31 | 2025-11-07 | Nirmal Mahto |  | 47.1844 | Derrick | 7
380 | 2025-11-01 | 32/3 | DA+0 | Sandy | 2025-10-31 | 2025-11-07 | Ganesh Sinha |  | 37.5044 | Derrick | 7
381 | 2025-11-01 | 4/0 | DD60+6 | DRY | 2025-10-25 | 2025-11-08 | Devi Construction |  | 100.968 | Derrick | 14
382 | 2025-11-01 | 33/0 | DC1+0 | DRY | 2025-10-22 | 2025-11-08 | Santosh Singh |  | 66.3811 | Derrick | 17
383 | 2025-11-01 | 42/0 | DC1+0 | Sandy | 2025-10-27 | 2025-11-09 | Chinta Devi |  | 66.3811 | Derrick | 13
384 | 2025-11-01 | 42/2 | DA+6 | Sandy | 2025-10-27 | 2025-11-09 | Vinay Construction |  | 45.413 | Derrick | 13
385 | 2025-11-01 | 3/0 | DD60+6 | DRY | 2025-10-07 | 2025-11-10 | Panva Devi |  | 100.968 | Derrick | 34
386 | 2025-11-01 | 33/1 | DA+0 | DRY | 2025-11-05 | 2025-11-11 | Sanjeev Kumar |  | 37.5044 | Derrick | 6
387 | 2025-11-01 | 32/2 | DA+3 | DRY | 2025-11-08 | 2025-11-13 | Ganesh Sinha |  | 38.8476 | Derrick | 5
388 | 2025-11-01 | 29/2 | DA+3 | DRY | 2025-11-10 | 2025-11-13 | Chinta Devi |  | 38.8476 | Derrick | 3
389 | 2025-11-01 | 42/4 | DA+0 | Sandy | 2025-11-08 | 2025-11-14 | Shobha Devi |  | 37.5044 | Derrick | 6
390 | 2025-11-01 | 5/0 | DB1+9 | DRY | 2025-10-29 | 2025-11-16 | Kamlesh Kumar |  | 70.7017 | Derrick | 18
391 | 2025-11-01 | 42/3 | DA+0 | Sandy | 2025-11-15 | 2025-11-17 | Sobha Devi |  | 37.5044 | Derrick | 2
392 | 2025-11-01 | 28/1 | DA+0 | DRY | 2025-11-10 | 2025-11-17 | Chinta Devi |  | 37.5044 | Derrick | 7
393 | 2025-11-01 | 8/0 | DB1+0 | DRY | 2025-11-09 | 2025-11-18 | Devi Construction |  | 57.5972 | Derrick | 9
394 | 2025-11-01 | 32/4 | DA+0 | Sandy | 2025-11-11 | 2025-11-18 | Santosh Singh |  | 37.5044 | Derrick | 7
395 | 2025-11-01 | 32/0 | DC1+0 | DRY | 2025-11-08 | 2025-11-18 | Jirwa Devi |  | 66.3811 | Derrick | 10
396 | 2025-11-01 | 34/2 | DA+6 | Sandy | 2025-11-11 | 2025-11-21 | Sanjeev Kumar |  | 45.413 | Derrick | 10
397 | 2025-11-01 | 42/1 | DA+6 | Sandy | 2025-11-10 | 2025-11-21 | Vinay Construction |  | 45.413 | Derrick | 11
398 | 2025-11-01 | 38/2 | DA+6 | Sandy | 2025-11-18 | 2025-11-22 | Shobha Devi |  | 45.413 | Derrick | 4
399 | 2025-11-01 | 27/8 | DA+0 | DFR | 2025-11-18 | 2025-11-26 | Jirwa Devi |  | 37.5044 | Derrick | 8
400 | 2025-11-01 | 30/0 | DC1+0 | DRY | 2025-11-14 | 2025-11-26 | Ganesh Sinha |  | 66.3811 | Derrick | 12
401 | 2025-11-01 | 26/5 | DA+6 | Sandy | 2025-11-21 | 2025-11-27 | Chinta Devi |  | 45.413 | Derrick | 6
402 | 2025-11-01 | 8/3 | DA+0 | DRY | 2025-11-10 | 2025-11-27 | Priyanka Devi |  | 37.5044 | Derrick | 17
403 | 2025-11-01 | 7/0 | DB1+0 | DRY | 2025-11-19 | 2025-11-28 | Devi Construction |  | 57.5972 | Derrick | 9
404 | 2025-11-01 | 27/5 | DA+0 | DRY | 2025-11-08 | 2025-11-30 | Dular chand Patel |  | 37.5044 | Derrick | 22
405 | 2025-11-01 | 41/0 | DC1+6 | Sandy | 2025-11-23 | 2025-11-30 | Shobha Devi |  | 78.132 | Derrick | 7
406 | 2025-11-01 | 43/2 | DA+0 | Sandy | 2025-11-22 | 2025-11-30 | Vinay Construction |  | 37.5044 | Derrick | 8
407 | 2025-11-01 | 10/16 | DA+3 | DRY | 2025-11-17 | 2025-11-30 | Kamlesh Kumar |  | 38.8476 | Derrick | 13
408 | 2025-11-01 | 26/8 | DA+6 | DFR | 2025-11-26 | 2025-11-30 | Ganesh Sinha |  | 45.413 | Derrick | 4
409 | 2025-12-01 | 27/12 | DA+3 | Sandy | 2025-11-27 | 2025-12-04 | Jirwa Devi |  | 38.8476 | Derrick | 7
410 | 2025-12-01 | 34/0 | DB2+0 | DRY | 2025-11-22 | 2025-12-05 | Sanjeev Kumar |  | 57.5972 | Derrick | 13
411 | 2025-12-01 | 42/5 | DA+9 | Sandy | 2025-12-03 | 2025-12-06 | Shobha Devi |  | 47.1844 | Derrick | 3
412 | 2025-12-01 | 10/7 | DA+3 | DRY | 2025-11-28 | 2025-12-06 | Priyanka Devi |  | 38.8476 | Derrick | 8
413 | 2025-12-01 | 6/0 | DB2+9 | DRY | 2025-11-23 | 2025-12-07 | Panva Devi |  | 70.7017 | Derrick | 14
414 | 2025-12-01 | 43/4 | DA+3 | Sandy | 2025-12-03 | 2025-12-10 | Vinay Construction |  | 38.8476 | Derrick | 7
415 | 2025-12-01 | 10/22 | DA+0 | Sandy | 2025-10-04 | 2025-12-10 | Vedanta Construction |  | 37.5044 | Derrick | 67
416 | 2025-12-01 | 26/7 | DA+0 | DFR | 2025-12-07 | 2025-12-11 | Chinta Devi |  | 37.5044 | Derrick | 4
417 | 2025-12-01 | 38/1 | DA+0 | Sandy | 2025-12-07 | 2025-12-12 | Shobha Devi |  | 37.5044 | Derrick | 5
418 | 2025-12-01 | 11/1 | DA+0 | Sandy | 2025-12-05 | 2025-12-12 | Nirmal Mahto |  | 37.5044 | Derrick | 7
419 | 2025-12-01 | 10/10 | DA+3 | Sandy | 2025-12-07 | 2025-12-14 | Priyanka Devi |  | 38.8476 | Derrick | 7
420 | 2025-12-01 | 10/15 | DA+3 | DRY | 2025-12-03 | 2025-12-14 | Kamlesh Kumar |  | 38.8476 | Derrick | 11
421 | 2025-12-01 | 11A/8 | DA+6 | Sandy | 2025-12-05 | 2025-12-16 | Sheetal Singh |  | 45.413 | Derrick | 11
422 | 2025-12-01 | 10/23 | DA+0 | Sandy | 2025-12-11 | 2025-12-17 | Vedanta Construction |  | 37.5044 | Derrick | 6
423 | 2025-12-01 | 11/2 | DA+0 | Sandy | 2025-12-12 | 2025-12-18 | Nirmal Mahto |  | 37.5044 | Derrick | 6
424 | 2025-12-01 | 13/1 | DA+9 | DRY | 2025-12-13 | 2025-12-18 | Santosh Singh / Laxmi |  | 47.1844 | Derrick | 5
425 | 2025-12-01 | 27/9 | DA+0 | DFR | 2025-12-13 | 2025-12-19 | Ganesh Sinha |  | 37.5044 | Derrick | 6
426 | 2025-12-01 | 35/3 | DB1+6 | Sandy | 2025-12-13 | 2025-12-19 | Shobha Devi |  | 67.8737 | Derrick | 6
427 | 2025-12-01 | 27/7 | DB1+0 | DFR | 2025-12-12 | 2025-12-20 | Chinta Devi |  | 57.5972 | Derrick | 8
428 | 2025-12-01 | 28/7 | DA+3 | Sandy | 2025-12-10 | 2025-12-20 | Panva Devi |  | 38.8476 | Derrick | 10
429 | 2025-12-01 | 31/0 | DB2+0 | Sandy | 2025-12-16 | 2025-12-20 | Jirwa Devi |  | 57.5972 | Derrick | 4
430 | 2025-12-01 | 22/7 | DA+0 | Sandy | 2025-12-16 | 2025-12-21 | Sunny Construction |  | 37.5044 | Derrick | 5
431 | 2025-12-01 | 9/0 | DD60+18 | DRY | 2025-12-02 | 2025-12-22 | Devi Construction |  | 129.111 | Derrick | 20
432 | 2025-12-01 | 13/3 | DA+3 | Sandy | 2025-12-16 | 2025-12-23 | Vivek Ganju |  | 38.8476 | Derrick | 7
433 | 2025-12-01 | 19/4 | DA+0 | DRY | 2025-12-19 | 2025-12-24 | Vedanta Construction |  | 37.5044 | Derrick | 5
434 | 2025-12-01 | 28/3 | DA+0 | DFR | 2025-12-21 | 2025-12-24 | Chinta Devi |  | 37.5044 | Derrick | 3
435 | 2025-12-01 | 11/3 | DA+0 | Sandy | 2025-12-18 | 2025-12-25 | Nirmal Mahto |  | 37.5044 | Derrick | 7
436 | 2025-12-01 | 22/6 | DA+0 | Sandy | 2025-12-21 | 2025-12-26 | Sunny Construction |  | 37.5044 | Derrick | 5
437 | 2025-12-01 | 28/4 | DA+0 | Sandy | 2025-12-21 | 2025-12-27 | Ganesh Sinha |  | 37.5044 | Derrick | 6
438 | 2025-12-01 | 10/13 | DA+3 | DRY | 2025-12-15 | 2025-12-27 | Kamlesh Kumar |  | 38.8476 | Derrick | 12
439 | 2025-12-01 | 28/8 | DA+3 | Sandy | 2025-12-21 | 2025-12-28 | Panva Devi |  | 38.8476 | Derrick | 7
440 | 2025-12-01 | 13/4 | DA+3 | DRY | 2025-12-24 | 2025-12-30 | Vivek Ganju |  | 38.8476 | Derrick | 6
441 | 2025-12-01 | 19/3 | DA+0 | DRY | 2025-12-25 | 2025-12-30 | Vedanta Construction |  | 37.5044 | Derrick | 5
442 | 2025-12-01 | 30/4 | DA+3 | DRY | 2025-12-26 | 2025-12-30 | Chinta Devi |  | 38.8476 | Derrick | 4
443 | 2025-12-01 | 10/5 | DA+3 | DRY | 2025-12-25 | 2025-12-31 | Devi Construction |  | 38.8476 | Derrick | 6
444 | 2025-12-01 | 14/0 | DC2+0 | Sandy | 2025-12-17 | 2025-12-31 | Sheetal Singh |  | 66.3811 | Derrick | 14
445 | 2025-12-01 | 22/2 | DA+6 | Sandy | 2025-12-23 | 2025-12-31 | Vinay Gupta |  | 45.413 | Derrick | 8
446 | 2025-12-01 | 22/11 | DA+6 | Sandy | 2025-12-27 | 2025-12-31 | Shobha Devi |  | 45.413 | Derrick | 4
447 | 2025-12-01 | 22/5 | DA+9 | DRY | 2025-12-27 | 2025-12-31 | Sunny Construction |  | 47.1844 | Derrick | 4
448 | 2025-12-01 | 11/0 | DB1+0 | Sandy | 2025-11-25 | 2025-12-31 | Nirmal Mahto |  | 57.5972 | Derrick | 36
449 | 2026-01-01 | 27/6 | DA+0 | Sandy | 2025-12-04 | 2026-01-05 | Dular chand Patel |  | 37.5044 | Derrick | 32
450 | 2026-01-01 | 19/1 | DA+0 | DRY | 2025-12-31 | 2026-01-07 | Vedanta Construction |  | 37.5044 | Derrick | 7
451 | 2026-01-01 | 27/10 | DA+3 | DFR | 2025-12-28 | 2026-01-07 | Ganesh Sinha |  | 38.8476 | Derrick | 10
452 | 2026-01-01 | 28/6 | DA+6 | Sandy | 2025-12-29 | 2026-01-08 | Jirwa Devi |  | 45.413 | Derrick | 10
453 | 2026-01-01 | 22/3 | DA+9 | Sandy | 2026-01-03 | 2026-01-09 | Sunny Construction |  | 47.1844 | Derrick | 6
454 | 2026-01-01 | 22/13 | DA+6 | Sandy | 2026-01-03 | 2026-01-09 | Shobha Devi |  | 45.413 | Derrick | 6
455 | 2026-01-01 | 26/6 | DA+6 | Sandy | 2025-12-03 | 2026-01-11 | Chinta Devi |  | 45.413 | Derrick | 39
456 | 2026-01-01 | 25/2 | DA+0 | DRY | 2026-01-06 | 2026-01-13 | Chinta Devi |  | 37.5044 | Derrick | 7
457 | 2026-01-01 | 14A/2 | DA+0 | DRY | 2026-01-03 | 2026-01-14 | Sheetal Singh |  | 37.5044 | Derrick | 11
458 | 2026-01-01 | 25/1 | DA+3 | DRY | 2026-01-14 | 2026-01-18 | Chinta Devi |  | 38.8476 | Derrick | 4
459 | 2026-01-01 | 25/0 | DC1+6 | DRY | 2026-01-22 | 2026-01-30 | Chinta Devi |  | 78.132 | Derrick | 8
460 | 2026-02-01 | 26/4 | DA+6 | Sandy | 2026-01-30 | 2026-02-06 | Chinta Devi |  | 45.413 | Derrick | 7
461 | 2026-02-01 | 10/2 | DA+0 | DFR | 2026-02-16 | 2026-02-19 | Sunny Construction |  | 37.5044 | Derrick | 3
462 | 2026-02-01 | 8/8 | DA+6 | DRY | 2026-02-17 | 2026-02-22 | Shobha Devi |  | 45.413 | Derrick | 5
463 | 2026-02-01 | 8/11 | DA+0 | DRY | 2026-02-19 | 2026-02-24 | Sunny Construction |  | 37.5044 | Derrick | 5
464 | 2026-02-01 | 8/6 | DA+3 | DRY | 2026-02-17 | 2026-02-27 | Shobha Devi |  | 38.8476 | Derrick | 10
465 | 2026-02-01 | 22/8 | DB1+0 | Sandy | 2026-02-16 | 2026-02-28 | Sheetal Singh |  | 57.5972 | Derrick | 12
466 | 2026-03-01 | 13/0 | DD60+3 | DRY | 2026-02-25 | 2026-03-05 | Chinta Devi |  | 89.9096 | Derrick | 8
467 | 2026-03-01 | 8/7 | DB1+0 | DRY | 2026-02-25 | 2026-03-07 | Sunny Construction |  | 57.5972 | Derrick | 10
468 | 2026-03-01 | 11A/4 | DA+3 | DRY | 2026-02-25 | 2026-03-16 | Chinta Devi |  | 38.8476 | Derrick | 19
469 | 2026-03-01 | 22/10 | DA+6 | Sandy | 2026-03-11 | 2026-03-16 | Sunny Construction |  | 45.413 | Derrick | 5
470 | 2026-03-01 | 10/0 | DD60+25 | DFR | 2026-03-02 | 2026-03-25 | Shobha Devi |  | 143.6019 | Derrick | 23
471 | 2026-03-01 | 21/9 | DA+3 | DFR | 2026-03-18 | 2026-03-26 | Chinta Devi |  | 38.8476 | Derrick | 8
472 | 2026-03-01 | 22/9 | DA+6 | Sandy | 2026-03-18 | 2026-03-27 | Sunny Construction |  | 45.413 | Derrick | 9
473 | 2026-03-01 | 21/2 | DA+0 | Sandy | 2026-03-28 | 2026-03-31 | Sunny Construction |  | 37.5044 | Derrick | 3
474 | 2026-03-01 | 21/8 | DA+6 | DRY | 2026-03-26 | 2026-03-31 | Chinta Devi |  | 45.413 | Derrick | 5
475 | 2026-03-01 | 15/0 | DC1+0 | DRY | 2026-03-26 | 2026-03-31 | Shobha Devi |  | 66.3811 | Derrick | 5
476 | 2026-04-01 | 21/10 | DA+6 | DRY | 2026-04-10 | 2026-04-20 | Sunny Construction |  | 45.413 | Derrick | 10
477 | 2026-04-01 | 22/1 | DA+9 | Sandy | 2026-04-11 | 2026-04-20 | Chinta Devi |  | 47.1844 | Derrick | 9
478 | 2026-04-01 | 21/7 | DA+3 | DFR | 2026-04-16 | 2026-04-27 | Shobha Devi |  | 38.8476 | Derrick | 11
479 | 2026-05-01 | 22/12 | DA+3 | Sandy | 2026-04-23 | 2026-05-04 | Sunny Construction |  | 38.8476 | Derrick | 11
480 | 2026-05-01 | 23/0 | DD45+3 | DRY | 2026-04-22 | 2026-05-10 | Chinta Devi |  | 89.9096 | Derrick | 18
481 | 2026-05-01 | 21/6 | DA+3 | DRY | 2026-05-08 | 2026-05-15 | Sunny Construction |  | 38.8476 | Derrick | 7
482 | 2026-05-01 | 21/1 | DA+6 | DRY | 2026-05-09 | 2026-05-16 | Shobha Devi |  | 45.413 | Derrick | 7
483 | 2026-05-01 | 20/1 | DA+0 | Sandy | 2026-05-17 | 2026-05-22 | Shobha Devi |  | 37.5044 | Derrick | 5
484 | 2026-05-01 | 22/4 | DA+9 | Sandy | 2026-05-12 | 2026-05-24 | Chinta Devi |  | 47.1844 | Derrick | 12
485 | 2026-05-01 | 22/0 | DB2+3 | DRY | 2026-06-28 | 2026-07-13 | Mukkhi Lal Singh |  | 60.0968 | Derrick | 15

## Tackwelding
Progress Summary'!A1
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line
List of Tackwelding Progress
Sl.No. | Loc. No. | Type of Tower | Start Date | Completion Date | Name of the Contractor | Tackwelding | Painting
1 | 59/13 | DA+3 | 2024-02-20 | 2024-02-20 | Suraja Ram | Done | Done
2 | 59/14 | DA+6 | 2024-02-22 | 2024-02-22 | Suraja Ram | Done | Done
3 | 62/5 | DA+0 | 2024-02-27 | 2024-02-27 | Suraja Ram | Done | Done
4 | 63/6 | DA+3 | 2024-02-28 | 2024-02-28 | Suraja Ram | Done | Done
5 | 63/8 | DA+3 | 2024-03-01 | 2024-03-02 | Suraja Ram | Done | Done
6 | 62/3 | DA+0 | 2024-02-03 | 2024-02-03 | Suraja Ram | Done | Done
7 | 62/4 | DA+3 | 2024-03-04 | 2024-03-04 | Suraja Ram | Done | Done
8 | 59/12 | DA+6 | 2024-03-05 | 2024-03-05 | Suraja Ram | Done | Done
9 | 59/10 | DA+0 | 2024-03-06 | 2024-03-06 | Suraja Ram | Done | Done
10 | 59/9 | DA+3 | 2024-03-07 | 2024-03-07 | Suraja Ram | Done | Done
11 | 60/7 | DA+3 | 2024-03-09 | 2024-03-09 | Suraja Ram | Done | Done
12 | 62/2 | DA+3 | 2024-03-10 | 2024-03-10 | Suraja Ram | Done | Done
13 | 62/7 | DA+3 | 2024-03-11 | 2024-03-11 | Suraja Ram | Done | Done
14 | 64/1 | DA+0 | 2024-03-12 | 2024-03-12 | Suraja Ram | Done | Done
15 | 59/7 | DA+3 | 2024-03-12 | 2024-03-12 | Ramagora | Done | Done
16 | 64/4 | DA+3 | 2024-03-13 | 2024-03-13 | Suraja Ram | Done | Done
17 | 60/11 | DA+3 | 2024-03-15 | 2024-03-15 | Ramagora | Done | Done
18 | 62/8 | DA+0 | 2024-03-15 | 2024-03-15 | Suraja Ram | Done | Done
19 | 65/2 | DA+0 | 2024-03-16 | 2024-03-16 | Suraja Ram | Done | Done
20 | 60/6 | DA+0 | 2024-03-16 | 2024-03-16 | Ramagora | Done | Done
21 | 65/4 | DA+0 | 2024-03-17 | 2024-03-17 | Suraja Ram | Done | Done
22 | 64/5 | DA+3 | 2024-03-18 | 2024-03-18 | Suraja Ram | Done | Done
23 | 62/9 | DA+3 | 2024-03-19 | 2024-03-19 | Suraja Ram | Done | Done
24 | 60/8 | DA+0 | 2024-03-19 | 2024-03-19 | Ramagora | Done | Done
25 | 62/10 | DA+0 | 2024-03-21 | 2024-03-21 | Suraja Ram | Done | Done
26 | 65/3 | DA+3 | 2024-03-22 | 2024-03-22 | Suraja Ram | Done | Done
27 | 59/6 | DA+3 | 2024-03-22 | 2024-03-22 | Ramagora | Done | Done
28 | 60/10 | DA+0 | 2024-03-24 | 2024-03-24 | Suraja Ram | Done | Done
29 | 61/6 | DA+3 | 2024-03-28 | 2024-03-28 | Suraja Ram | Done | Done
30 | 65/5 | DA+0 | 2024-03-29 | 2024-03-29 | Suraja Ram | Done | Done
31 | 64/6 | DA+0 | 2024-04-01 | 2024-04-01 | Suraja Ram | Done | Done
32 | 61/7 | DA+9 | 2024-04-03 | 2024-04-03 | Suraja Ram | Done | Done
33 | 65/6 | DA+0 | 2024-04-04 | 2024-04-04 | Suraja Ram | Done | Done
34 | 64/7 | DA+3 | 2024-04-06 | 2024-04-06 | Suraja Ram | Done | Done
35 | 63/7 | DA+3 | 2024-04-21 | 2024-04-22 | Suraja Ram | Done | Done
36 | 64/9 | DA+3 | 2024-04-24 | 2024-04-24 | Suraja Ram | Done | Done
37 | 61/0 | DB2+0 | 2024-04-25 | 2024-04-25 | Ramagora | Done | Done
38 | 65/9 | DA+0 | 2024-04-27 | 2024-04-27 | Suraja Ram | Done | Done
39 | 65/11 | DA+0 | 2024-04-28 | 2024-04-28 | Suraja Ram | Done | Done
40 | 67/2 | DA+0 | 2024-04-29 | 2024-04-29 | Suraja Ram | Done | Done
41 | 61/2 | DA+6 | 2024-04-29 | 2024-04-30 | Ramagora | Done | Done
42 | 64/10 | DA+3 | 2024-05-05 | 2024-05-05 | Suraja Ram | Done | Done
43 | 67/1 | DA+0 | 2024-05-07 | 2024-05-07 | Suraja Ram | Done | Done
44 | 64/8 | DA+3 | 2024-05-09 | 2024-05-09 | Suraja Ram | Done | Done
45 | 65/1 | DA+0 | 2024-05-10 | 2024-05-10 | Suraja Ram | Done | Done
46 | 65/0 | DB1+0 | 2024-05-10 | 2024-05-10 | Suraja Ram | Done | Done
47 | 61/1 | DA+6 | 2024-05-10 | 2024-05-10 | Ramagora | Done | Done
48 | 60/9 | DA+3 | 2024-05-11 | 2024-05-11 | Ramagora | Done | Done
49 | 63/4 | DA+0 | 2024-05-14 | 2024-05-14 | Suraja Ram | Done | Done
50 | 63/3 | DA+3 | 2024-05-15 | 2024-05-15 | Suraja Ram | Done | Done
51 | 63/5 | DA+3 | 2024-05-16 | 2024-05-16 | Suraja Ram | Done | Done
52 | 61/3 | DA+6 | 2024-05-17 | 2024-05-17 | Ramagora | Done | Done
53 | 62/11 | DA+3 | 2024-05-19 | 2024-05-19 | Suraja Ram | Done | Done
54 | 61/4 | DA+3 | 2024-05-23 | 2024-05-23 | Suraja Ram | Done | Done
55 | 61/5 | DA+3 | 2024-05-25 | 2024-05-25 | Suraja Ram | Done | Done
56 | 64/2 | DA+3 | 2024-06-03 | 2024-06-03 | Suraja Ram | Done | Done
57 | 64/3 | DA+0 | 2024-06-06 | 2024-06-06 | Suraja Ram | Done | Done
58 | 64/0 | DB2+0 | 2024-06-06 | 2024-06-06 | Suraja Ram | Done | Done
59 | 61/10 | DA+9 | 2024-06-07 | 2024-06-07 | Suraja Ram | Done | Done
60 | 61/8 | DA+6 | 2024-06-08 | 2024-06-08 | Ramagora | Done | Done
61 | 63/2 | DA+0 | 2024-06-08 | 2024-06-08 | Suraja Ram | Done | Done
62 | 61/9 | DA+0 | 2024-06-09 | 2024-06-09 | Ramagora | Done | Done
63 | 63/1 | DA+3 | 2024-06-09 | 2024-06-09 | Suraja Ram | Done | Done
64 | 59/5 | DA+3 | 2024-06-10 | 2024-06-10 | Ramagora | Done | Done
65 | 63/0 | DC1+0 | 2024-06-10 | 2024-06-11 | Suraja Ram | Done | Done
66 | 60/5 | DA+3 | 2024-06-11 | 2024-06-11 | Ramagora | Done | Done
67 | 60/4 | DA+3 | 2024-06-13 | 2024-06-13 | Ramagora | Done | Done
68 | 60/3 | DA+3 | 2024-06-23 | 2024-06-23 | Ramagora | Done | Done
69 | 60/2 | DA+3 | 2024-06-25 | 2024-06-25 | Ramagora | Done | Done
70 | 60/1 | DA+6 | 2024-06-30 | 2024-06-30 | Ramagora | Done | Done
71 | 59/16 | DA+9 | 2024-07-01 | 2024-07-01 | Suraja Ram | Done | Done
72 | 59/15 | DA+6 | 2024-07-02 | 2024-07-02 | Suraja Ram | Done | Done
73 | 60/0 | DC1+0 | 2024-07-24 | 2024-07-24 | Suraja Ram | Done | Done
74 | 59/8 | DB1+3 | 2024-07-27 | 2024-07-27 | Suraja Ram | Done | Done
75 | 55/3 | DA+0 | 2024-08-23 | 2024-08-23 | Suraja Ram | Done | Done
76 | 55/4 | DA+0 | 2024-08-24 | 2024-08-24 | Suraja Ram | Done | Done
77 | 57/6 | DA+3 | 2024-08-27 | 2024-08-27 | Suraja Ram | Done | Done
78 | 57/3 | DA+0 | 2024-08-28 | 2024-08-28 | Suraja Ram | Done | Done
79 | 57/4 | DA+0 | 2024-08-30 | 2024-08-30 | Suraja Ram | Done | Done
80 | 57/5 | DA+3 | 2024-08-30 | 2024-08-30 | Suraja Ram | Done | Done
81 | 62/0 | DB2+0 | 2024-09-15 | 2024-09-15 | Suraja Ram | Done | Done
82 | 62/1 | DA+3 | 2024-09-23 | 2024-09-24 | Suraja Ram | Done | Done
83 | 62/6 | DA+3 | 2024-09-25 | 2024-09-26 | Suraja Ram | Done | Done
84 | 57/7 | DA+3 | 2024-10-05 | 2024-10-06 | Suraja Ram | Done | Done
85 | 50/9 | DA+0 | 2024-10-06 | 2024-10-07 | Suraja Ram | Done | Done
86 | 50/10 | DA+0 | 2024-10-09 | 2024-10-09 | Suraja Ram | Done | Done
87 | 50/0 | DB2+0 | 2024-10-10 | 2024-10-10 | Suraja Ram | Done | Done
88 | 50/3 | DA+6 | 2024-10-24 | 2024-10-24 | Suraja Ram | Done | Done
89 | 50/1 | DA+6 | 2024-10-25 | 2024-10-25 | Suraja Ram | Done | Done
90 | 51/1 | DA+0 | 2024-10-25 | 2024-10-25 | Suraja Ram | Done | Done
91 | 16/3 | DA+3 | 2024-10-26 | 2024-10-26 | R&A | Done
92 | 50/2 | DA+9 | 2024-10-28 | 2024-10-28 | Suraja Ram | Done | Done
93 | 64/11 | DA+3 | 2024-10-29 | 2024-10-29 | Suraja Ram | Done | Done
94 | 15/1 | DA+3 | 2024-10-26 | 2024-10-29 | SB Enterprises | Done
95 | 16/4 | DA+0 | 2024-11-10 | 2024-11-10 | SB Enterprises | Done
96 | 59/11 | DA+6 | 2024-11-11 | 2024-11-11 | Suraja Ram | Done | Done
97 | 18/1 | DA+0 | 2024-11-12 | 2024-11-12 | SB Enterprises | Done
98 | 50/7 | DA+0 | 2024-11-14 | 2024-11-14 | Suraja Ram | Done | Done
99 | 73/1 | DA+0 | 2024-11-14 | 2024-11-14 | Suraja Ram | Done | Done
100 | 73/2 | DA+0 | 2024-11-19 | 2024-11-19 | Suraja Ram | Done | Done
101 | 73/9 | DA+0 | 2024-11-20 | 2024-11-20 | Suraja Ram | Done | Done
102 | 52/7 | DA+3 | 2024-11-25 | 2024-11-25 | Suraja Ram | Done | Done
103 | 52/6 | DA+6 | 2024-11-25 | 2024-11-25 | Suraja Ram | Done | Done
104 | 52/8 | DA+6 | 2024-11-26 | 2024-11-26 | Suraja Ram | Done | Done
105 | 48/0 | DC2+0 | 2024-11-27 | 2024-11-27 | Suraja Ram | Done | Done
106 | 49/4 | DA+3 | 2024-11-27 | 2024-11-27 | Suraja Ram | Done | Done
107 | 48/1 | DA+9 | 2024-11-29 | 2024-11-29 | Suraja Ram | Done | Done
108 | 47/10 | DA+6 | 2024-11-29 | 2024-11-29 | Suraja Ram | Done | Done
109 | 49/7 | DA+0 | 2024-12-02 | 2024-12-02 | Suraja Ram | Done | Done
110 | 49/6 | DA+0 | 2024-12-03 | 2024-12-03 | Suraja Ram | Done | Done
111 | 49/5 | DA+3 | 2024-12-04 | 2024-12-04 | Suraja Ram | Done | Done
112 | 59/3 | DA+3 | 2024-12-05 | 2024-12-05 | Suraja Ram | Done | Done
113 | 59/4 | DA+3 | 2024-12-06 | 2024-12-06 | Suraja Ram | Done | Done
114 | 73/6 | DA+0 | 2024-12-13 | 2024-12-13 | Suraja Ram | Done | Done
115 | 72/3 | DA+3 | 2024-12-17 | 2024-12-17 | Suraja Ram | Done | Done
116 | 59/1 | DA+3 | 2024-12-18 | 2024-12-18 | Suraja Ram | Done | Done
117 | 59/2 | DA+3 | 2024-12-20 | 2024-12-20 | Suraja Ram | Done | Done
118 | 50/8 | DA+9 | 2024-12-23 | 2024-12-23 | Suraja Ram | Done | Done
119 | 73/8 | DA+3 | 2024-12-25 | 2024-12-25 | Suraja Ram | Done | Done
120 | 51/2 | DA+0 | 2024-12-26 | 2024-12-26 | Suraja Ram | Done | Done
121 | 49/2 | DA+3 | 2024-12-26 | 2024-12-26 | Suraja Ram | Done | Done
122 | 49/3 | DA+3 | 2024-12-26 | 2024-12-26 | Suraja Ram | Done | Done
123 | 49/1 | DA+0 | 2024-12-28 | 2024-12-28 | Suraja Ram | Done | Done
124 | 50/4 | DA+9 | 2025-01-06 | 2025-01-06 | Suraja Ram | Done | Done
125 | 59/0 | DC2+0 | 2025-01-07 | 2025-01-07 | Suraja Ram | Done | Done
126 | 50/6 | DA+9 | 2025-01-12 | 2025-01-12 | Suraja Ram | Done | Done
127 | 65/7 | DA+0 | 2025-01-17 | 2025-01-17 | Suraja Ram | Done | Done
128 | 65/8 | DA+0 | 2025-01-18 | 2025-01-18 | Suraja Ram | Done | Done
129 | 73/3 | DA+0 | 2025-01-27 | 2025-01-27 | Suraja Ram | Done | Done
130 | 73/4 | DA+0 | 2025-01-28 | 2025-01-29 | Suraja Ram | Done | Done
131 | 73/7 | DA+0 | 2025-02-13 | 2025-02-13 | Suraja Ram | Done | Done
132 | 74/0 | DB2+0 | 2025-02-14 | 2025-02-14 | Suraja Ram | Done | Done
133 | 73/5 | DA+0 | 2025-02-15 | 2025-02-15 | Suraja Ram | Done | Done
134 | 65/10 | DA+0 | 2025-02-17 | 2025-02-17 | Suraja Ram | Done | Done
135 | 66/0 | DC2+6 | 2025-02-19 | 2025-02-19 | Suraja Ram | Done | Done
136 | 51/0 | DC2+0 | 2025-02-26 | 2025-02-26 | Suraja Ram | Done | Done
137 | 50/5 | DA+9 | 2025-03-02 | 2025-03-02 | Suraja Ram | Done | Done
138 | 52/0 | DC2+0 | 2025-03-05 | 2025-03-05 | Suraja Ram | Done | Done
139 | 49/0 | DD45+0 | 2025-03-10 | 2025-03-10 | Suraja Ram | Done | Done
140 | 52/9 | DA+3 | 2025-03-11 | 2025-03-11 | Suraja Ram | Done | Done
141 | 52/10 | DA+9 | 2025-03-12 | 2025-03-12 | Suraja Ram | Done | Done
142 | 73/0 | DB2+0 | 2025-03-13 | 2025-03-13 | Suraja Ram | Done | Done
143 | 52/5 | DA+9 | 2025-03-17 | 2025-03-17 | Suraja Ram | Done | Done
144 | 47/9 | DA+3 | 2025-04-16 | 2025-04-16 | Suraja Ram | Done
145 | 47/8 | DA+0 | 2025-04-16 | 2025-04-16 | Suraja Ram | Done
146 | 58/0 | DC1+3 | 2025-04-21 | 2025-04-21 | Suraja Ram | Done
147 | 72/2 | DA+0 | 2025-04-28 | 2025-04-28 | Suraja Ram | Done | Done
148 | 72/1 | DA+3 | 2025-04-29 | 2025-04-29 | Suraja Ram | Done | Done
149 | 71/8 | DA+3 | 2025-04-30 | 2025-04-30 | Suraja Ram | Done | Done
150 | 71/7 | DA+3 | 2025-04-30 | 2025-04-30 | Suraja Ram | Done | Done
151 | 70/5 | DA+3 | 2025-05-02 | 2025-05-02 | Suraja Ram | Done | Done
152 | 71/6 | DA+0 | 2025-05-02 | 2025-05-02 | Suraja Ram | Done | Done
153 | 70/3 | DA+3 | 2025-05-03 | 2025-05-03 | Suraja Ram | Done | Done
154 | 55/5 | DA+0 | 2025-05-05 | 2025-05-05 | Suraja Ram | Done | Done
155 | 55/6 | DA+0 | 2025-05-06 | 2025-05-06 | Suraja Ram | Done | Done
156 | 71/5 | DA+3 | 2025-05-10 | 2025-05-10 | Suraja Ram | Done | Done
157 | 70/4 | DA+3 | 2025-05-11 | 2025-05-11 | Suraja Ram | Done | Done
158 | 71/3 | DA+6 | 2025-05-16 | 2025-05-16 | Suraja Ram | Done | Done
159 | 71/4 | DA+3 | 2025-05-17 | 2025-05-17 | Suraja Ram | Done | Done
160 | 71/2 | DA+3 | 2025-05-19 | 2025-05-19 | Suraja Ram | Done | Done
161 | 71/1 | DA+3 | 2025-05-20 | 2025-05-20 | Suraja Ram | Done | Done
162 | 70/11 | DA+3 | 2025-05-24 | 2025-05-24 | Suraja Ram | Done | Done
163 | 71/0 | DB2+3 | 2025-05-26 | 2025-05-26 | Suraja Ram | Done | Done
164 | 70/9 | DA+3 | 2025-05-27 | 2025-05-27 | Suraja Ram | Done | Done
165 | 70/10 | DA+3 | 2025-05-28 | 2025-05-28 | Suraja Ram | Done | Done
166 | 68/0 | DD45+0 | 2025-06-04 | 2025-06-04 | Suraja Ram | Done | Done
167 | 67/0 | DC1+9 | 2025-06-10 | 2025-06-10 | Suraja Ram | Done | Done
168 | 16/2 | DA+0 | 2025-06-10 | 2025-06-10 | Chanda Enterprises | Done
169 | 17/0 | DB2+3 | 2025-06-10 | 2025-06-10 | Chanda Enterprises | Done
170 | 70/6 | DA+3 | 2025-07-13 | 2025-07-14 | Suraja Ram | Done
171 | 53/3 | DA+6 | 2025-07-23 | 2025-07-23 | Suraja Ram | Done
172 | 72/0 | DB2+3 | 2025-07-23 | 2025-07-23 | Suraja Ram | Done | Done
173 | 10/14 | DA+3 | 2025-07-23 | 2025-07-23 | Shiv Power | Done | Done
174 | 55/7 | DA+0 | 2025-08-29 | 2025-08-29 | Suraja Ram | Done | Done
175 | 55/8 | DA+6 | 2025-09-01 | 2025-09-01 | Suraja Ram | Done | Done
176 | 57/1 | DA+0 | 2025-09-02 | 2025-09-02 | Suraja Ram | Done
177 | 57/2 | DA+3 | 2025-09-02 | 2025-09-02 | Suraja Ram | Done
178 | 55/1 | DA+0 | 2025-09-03 | 2025-09-03 | Suraja Ram | Done | Done
179 | 1A/0 | DD60+0 | 2025-09-02 | 2025-09-02 | B.S. Infra | Done | Done
180 | 1A/1 | DA+6 | 2025-09-03 | 2025-09-03 | B.S. Infra | Done | Done
181 | 1A/3 | DA+0 | 2025-09-04 | 2025-09-04 | B.S. Infra | Done | Done
182 | 1A/4 | DA+3 | 2025-09-05 | 2025-09-05 | B.S. Infra | Done | Done
183 | 1A/5 | DA+0 | 2025-09-06 | 2025-09-06 | B.S. Infra | Done | Done
184 | 1A/6 | DA+0 | 2025-09-07 | 2025-09-07 | B.S. Infra | Done | Done
185 | 1A/8 | DA+0 | 2025-09-08 | 2025-09-08 | B.S. Infra | Done | Done
186 | 2/0 | DC1+0 | 2025-09-09 | 2025-09-09 | B.S. Infra | Done | Done
187 | 54/3 | DA+6 | 2025-09-24 | 2025-09-24 | Suraja Ram | Done
188 | 70/8 | DA+3 | 2025-10-08 | 2025-10-08 | Suraja Ram | Done | Done
189 | 70/7 | DA+3 | 2025-10-14 | 2025-10-14 | Suraja Ram | Done | Done
190 | 54/4 | DA+9 | 2025-10-15 | 2025-10-15 | Suraja Ram | Done | Done
191 | 54/5 | DA+9 | 2025-10-16 | 2025-10-16 | Suraja Ram | Done | Done
192 | 44/11 | DA+0 | 2025-10-17 | 2025-10-17 | Suraja Ram | Done | Done
193 | 45/1 | DA+9 | 2025-10-18 | 2025-10-18 | Suraja Ram | Done | Done
194 | 2/1 | DA+3 | 2025-10-19 | 2025-10-19 | Shiv Power | Done | Done
195 | 2/2 | DA+3 | 2025-10-22 | 2025-10-22 | Shiv Power | Done | Done
196 | 2/3 | DA+3 | 2025-10-23 | 2025-10-23 | Shiv Power | Done | Done
197 | 10/3 | DA+0 | 2025-10-25 | 2025-10-25 | Shiv Power | Done | Done
198 | 10/4 | DA+3 | 2025-10-26 | 2025-10-26 | Shiv Power | Done | Done
199 | 10/6 | DA+0 | 2025-10-27 | 2025-10-27 | Shiv Power | Done | Done
200 | 10/12 | DB1+0 | 2025-10-28 | 2025-10-28 | Shiv Power | Done | Done
201 | 11/5 | DA+0 | 2025-10-29 | 2025-10-29 | Shiv Power | Done | Done
202 | 11A/0 | DB1+0 | 2025-10-30 | 2025-10-30 | Shiv Power | Done
203 | 11A/9 | DA+3 | 2025-10-31 | 2025-10-31 | Shiv Power | Done | Done
204 | 52/4 | DA+9 | 2025-11-07 | 2025-11-07 | Suraja Ram | Done
205 | 52/1 | DA+6 | 2025-11-07 | 2025-11-07 | Suraja Ram | Done
206 | 52/2 | DA+6 | 2025-11-07 | 2025-11-07 | Suraja Ram | Done
207 | 38/4 | DA+9 | 2025-11-12 | 2025-11-12 | Suraja Ram | Done
208 | 39/1 | DA+0 | 2025-11-14 | 2025-11-14 | Suraja Ram | Done
209 | 40/0 | DC2+0 | 2025-11-15 | 2025-11-15 | Suraja Ram | Done | Done
210 | 30/1 | DA+0 | 2025-11-16 | 2025-11-16 | Jai Bagrangbali | Done | Done
211 | 29/4 | DA+6 | 2025-11-17 | 2025-11-17 | Jai Bagrangbali | Done | Done
212 | 30/2 | DA+0 | 2025-11-18 | 2025-11-18 | Jai Bagrangbali | Done | Done
213 | 30/3 | DA+3 | 2025-11-18 | 2025-11-18 | Jai Bagrangbali | Done | Done
214 | 30/5 | DA+3 | 2025-11-19 | 2025-11-19 | Jai Bagrangbali | Done | Done
215 | 31/1 | DA+0 | 2025-11-19 | 2025-11-19 | Jai Bagrangbali | Done | Done
216 | 31/2 | DA+0 | 2025-11-19 | 2025-11-19 | Jai Bagrangbali | Done | Done
217 | 32/1 | DA+3 | 2025-11-19 | 2025-11-19 | Jai Bagrangbali | Done | Done
218 | 28/2 | DA+0 | 2025-11-26 | 2025-11-26 | Jai Bagrangbali | Done | Done
219 | 28/0 | DB2+0 | 2025-11-27 | 2025-11-27 | Jai Bagrangbali | Done | Done
220 | 27/3 | DA+3 | 2025-11-27 | 2025-11-27 | Jai Bagrangbali | Done | Done
221 | 27/2 | DA+3 | 2025-11-27 | 2025-11-27 | Jai Bagrangbali | Done | Done
222 | 70/0 | DC1+0 | 2025-11-30 | 2025-11-30 | Suraja Ram | Done | Done
223 | 38/3 | DA+9 | 2025-12-04 | 2025-12-04 | Suraja Ram | Done | Done
224 | 28/5 | DA+9 | 2025-12-07 | 2025-12-07 | Jai Bagrangbali | Done | Done
225 | 33/0 | DC1+0 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
226 | 33/1 | DA+0 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
227 | 34/1 | DA+9 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
228 | 34/3 | DA+0 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
229 | 35/0 | DB2+6 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
230 | 35/1 | DA+9 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
231 | 35/2 | DB1+0 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
232 | 38/0 | DB2+6 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
233 | 39/0 | DB2+6 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
234 | 41/0 | DC1+6 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
235 | 42/0 | DC1+0 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
236 | 42/3 | DA+0 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
237 | 42/4 | DA+0 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
238 | 42/5 | DA+9 | 2025-12-08 | 2025-12-08 | Suraja Ram | Done | Done
239 | 53/2 | DA+0 | 2025-12-09 | 2025-12-09 | Suraja Ram | Done | Done
240 | 54/2 | DA+3 | 2025-12-10 | 2025-12-10 | Suraja Ram | Done | Done
241 | 69/0 | DB2+0 | 2025-12-11 | 2025-12-11 | Suraja Ram | Done | Done
242 | 69/1 | DA+3 | 2025-12-12 | 2025-12-12 | Suraja Ram | Done | Done
243 | 70/1 | DA+3 | 2025-12-13 | 2025-12-13 | Suraja Ram | Done | Done
244 | 70/2 | DA+3 | 2025-12-14 | 2025-12-14 | Suraja Ram | Done | Done
245 | 2/5 | DA+3 | 2025-12-15 | 2025-12-15 | Shiv Power | Done | Done
246 | 2/6 | DA+3 | 2025-12-16 | 2025-12-16 | Shiv Power | Done | Done
247 | 2/8 | DA+0 | 2025-12-17 | 2025-12-17 | Shiv Power | Done | Done
248 | 8/10 | DA+3 | 2025-12-18 | 2025-12-18 | Jai Bagrangbali | Done | Done
249 | 16/5 | DA+3 | 2025-12-19 | 2025-12-19 | Vendor Name not confirmed by Section incharge | Done | Done | incomplete
250 | 27/1 | DA+3 | 2025-12-20 | 2025-12-20 | Jai Bagrangbali | Done | Done
251 | 27/4 | DA+3 | 2025-12-21 | 2025-12-21 | Jai Bagrangbali | Done | Done
252 | 27/8 | DA+0 | 2025-12-22 | 2025-12-22 | Jai Bagrangbali | Done | Done
253 | 27/11 | DA+3 | 2025-12-23 | 2025-12-23 | Jai Bagrangbali | Done | Done
254 | 28/1 | DA+0 | 2025-12-24 | 2025-12-24 | Jai Bagrangbali | Done | Done
255 | 32/0 | DC1+0 | 2025-12-25 | 2025-12-25 | Jai Bagrangbali | Done | Done
256 | 32/2 | DA+3 | 2025-12-26 | 2025-12-26 | Jai Bagrangbali | Done | Done
257 | 29/2 | DA+3 | 2025-12-27 | 2025-12-27 | Jai Bagrangbali | Done | Done
258 | 6/1 | DA+0 | 2026-01-02 | 2026-01-02 | Jai Bagrangbali | Done | Done
259 | 6/2 | DA+0 | 2026-01-02 | 2026-01-02 | Jai Bagrangbali | Done | Done
260 | 5/0 | DB1+9 | 2026-01-03 | 2026-01-03 | Jai Bagrangbali | Done | Done
261 | 8/0 | DB1+0 | 2026-01-04 | 2026-01-04 | Jai Bagrangbali | Done | Done
262 | 4/1 | DA+0 | 2026-01-05 | 2026-01-05 | Jai Bagrangbali | Done | Done
263 | 4/0 | DD60+6 | 2026-01-06 | 2026-01-06 | Jai Bagrangbali | Done | Done
264 | 10/16 | DA+3 | 2026-01-08 | 2026-01-08 | Jai Bagrangbali | Done | Done
265 | 2/4 | DA+3 | 2026-01-08 | 2026-01-08 | Shiv Power | Done | Done
266 | 2/7 | DA+3 | 2026-01-08 | 2026-01-08 | Shiv Power | Done
267 | 2/9 | DA+0 | 2026-01-08 | 2026-01-08 | Shiv Power | Done | Done
268 | 10/8 | DA+3 | 2026-01-08 | 2026-01-08 | Shiv Power | Done
269 | 10/17 | DA+3 | 2026-01-08 | 2026-01-08 | Jai Bagrangbali | Done | Done
270 | 10/18 | DA+3 | 2026-01-08 | 2026-01-08 | Jai Bagrangbali | Done | Done
271 | 32/3 | DA+0 | 2026-01-09 | 2026-01-09 | The Shraddha Cooperative Multipurpose Society Limited | Done
272 | 32/4 | DA+0 | 2026-01-13 | 2026-01-13 | The Shraddha Cooperative Multipurpose Society Limited | Done
273 | 26/8 | DA+6 | 2026-01-16 | 2026-01-16 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
274 | 34/0 | DB2+0 | 2026-01-06 | 2026-01-06 | Suraja Ram | Done | Done
275 | 34/2 | DA+6 | 2026-01-07 | 2026-01-07 | Suraja Ram | Done | Done
276 | 44/1 | DA+0 | 2026-01-08 | 2026-01-08 | Suraja Ram | Done | Done
277 | 44/3 | DA+0 | 2026-01-09 | 2026-01-09 | Suraja Ram | Done | Done
278 | 44/4 | DA+9 | 2026-01-10 | 2026-01-10 | Suraja Ram | Done | Done
279 | 44/5 | DA+9 | 2026-01-11 | 2026-01-11 | Suraja Ram | Done | Done
280 | 44/7 | DA+9 | 2026-01-12 | 2026-01-12 | Suraja Ram | Done | Done
281 | 46/0 | DD60+25 | 2026-01-13 | 2026-01-13 | Suraja Ram | Done | Done
282 | 47/0 | DD60+25 | 2026-01-14 | 2026-01-14 | Suraja Ram | Done | Done
283 | 47/1 | DA+3 | 2026-01-15 | 2026-01-15 | Suraja Ram | Done | Done
284 | 47/2 | DA+9 | 2026-01-16 | 2026-01-16 | Suraja Ram | Done | Done
285 | 47/3 | DA+9 | 2026-01-17 | 2026-01-17 | Suraja Ram | Done | Done
286 | 47/4 | DA+3 | 2026-01-18 | 2026-01-18 | Suraja Ram | Done | Done
287 | 47/6 | DA+3 | 2026-01-19 | 2026-01-19 | Suraja Ram | Done | Done
288 | 47/7 | DA+3 | 2026-01-20 | 2026-01-20 | Suraja Ram | Done | Done
289 | 35/3 | DB1+6 | 2026-01-21 | 2026-01-21 | Suraja Ram | Done | Done
290 | 35/4 | DA+0 | 2026-01-22 | 2026-01-22 | Suraja Ram | Done | Done
291 | 35/5 | DA+0 | 2026-01-23 | 2026-01-23 | Suraja Ram | Done | Done
292 | 36/0 | DB2+0 | 2026-01-24 | 2026-01-24 | Suraja Ram | Done | Done
293 | 36/1 | DA+3 | 2026-01-25 | 2026-01-25 | Suraja Ram | Done | Done
294 | 36/2 | DA+0 | 2026-01-27 | 2026-01-27 | Suraja Ram | Done | Done
295 | 40/2 | DA+3 | 2026-01-28 | 2026-01-28 | Suraja Ram | Done | Done
296 | 8/2 | DA+3 | 2026-02-01 | 2026-02-01 | Jai Bagrangbali | Done | Done
297 | 8/3 | DA+0 | 2026-02-02 | 2026-02-02 | Jai Bagrangbali | Done | Done
298 | 25/4 | DA+0 | 2026-02-02 | 2026-02-02 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
299 | 25/1 | DA+3 | 2026-02-02 | 2026-02-02 | The Shraddha Cooperative Multipurpose Society Limited | Done
300 | 1/0 | DD60+0 | 2026-02-03 | 2026-02-03 | Jai Bagrangbali | Done | Done
301 | 1A/2 | DA+0 | 2026-02-03 | 2026-02-03 | Shiv Power | Done | Done
302 | 1A/7 | DA+3 | 2026-02-03 | 2026-02-03 | Shiv Power | Done | Done
303 | 3/0 | DD60+6 | 2026-02-03 | 2026-02-03 | Jai Bagrangbali | Done | Done
304 | 4/2 | DA+0 | 2026-02-03 | 2026-02-03 | Jai Bagrangbali | Done | Done
305 | 4/3 | DA+0 | 2026-02-04 | 2026-02-04 | Jai Bagrangbali | Done | Done
306 | 4/4 | DA+0 | 2026-02-04 | 2026-02-04 | Jai Bagrangbali | Done | Done
307 | 6/0 | DB2+9 | 2026-02-04 | 2026-02-04 | Jai Bagrangbali | Done | Done
308 | 7/0 | DB1+0 | 2026-02-04 | 2026-02-04 | Jai Bagrangbali | Done | Done
309 | 8/1 | DA+3 | 2026-02-05 | 2026-02-05 | Jai Bagrangbali | Done | Done
310 | 8/9 | DA+3 | 2026-02-05 | 2026-02-05 | Shiv Power | Done | Done
311 | 10/1 | DA+0 | 2026-02-05 | 2026-02-05 | Jai Bagrangbali | Done | Done
312 | 10/5 | DA+3 | 2026-02-05 | 2026-02-05 | Jai Bagrangbali | Done | Done
313 | 10/13 | DA+3 | 2026-02-05 | 2026-02-05 | Jai Bagrangbali | Done | Done
314 | 10/15 | DA+3 | 2026-02-05 | 2026-02-05 | Jai Bagrangbali | Done | Done
315 | 10/19 | DA+0 | 2026-02-06 | 2026-02-06 | Jai Bagrangbali | Done | Done
316 | 10/20 | DA+3 | 2026-02-06 | 2026-02-06 | Jai Bagrangbali | Done | Done
317 | 10/21 | DA+3 | 2026-02-06 | 2026-02-06 | Jai Bagrangbali | Done | Done
318 | 10/22 | DA+0 | 2026-02-06 | 2026-02-06 | Jai Bagrangbali | Done | Done
319 | 10/23 | DA+0 | 2026-02-06 | 2026-02-06 | Jai Bagrangbali | Done | Done
320 | 25/2 | DA+0 | 2026-02-07 | 2026-02-07 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
321 | 27/5 | DA+0 | 2026-02-07 | 2026-02-07 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
322 | 36/3 | DA+0 | 2026-02-07 | 2026-02-07 | Suraja Ram | Done | Done
323 | 36/4 | DA+6 | 2026-02-07 | 2026-02-07 | Suraja Ram | Done | Done
324 | 40/1 | DA+6 | 2026-02-08 | 2026-02-08 | Suraja Ram | Done | Done
325 | 40/3 | DA+3 | 2026-02-08 | 2026-02-08 | Suraja Ram | Done | Done
326 | 41/1 | DB1+9 | 2026-02-08 | 2026-02-08 | Suraja Ram | Done | Done
327 | 41/2 | DA+0 | 2026-02-09 | 2026-02-09 | Suraja Ram | Done | Done
328 | 42/1 | DA+6 | 2026-02-09 | 2026-02-09 | Suraja Ram | Done | Done
329 | 42/2 | DA+6 | 2026-02-09 | 2026-02-09 | Suraja Ram | Done | Done
330 | 42/6 | DA+0 | 2026-02-10 | 2026-02-10 | Suraja Ram | Done | Done
331 | 43/0 | DB1+0 | 2026-02-10 | 2026-02-10 | Suraja Ram | Done | Done
332 | 11/1 | DA+0 | 2026-02-10 | 2026-02-10 | Shiv Power | Done | Done
333 | 11/2 | DA+0 | 2026-02-10 | 2026-02-10 | Shiv Power | Done | Done
334 | 11A/8 | DA+6 | 2026-02-10 | 2026-02-10 | Shiv Power | Done | Done
335 | 12/0 | DD60+0 | 2026-02-10 | 2026-02-10 | Shiv Power | Done | Done
336 | 17/4 | DA+3 | 2026-02-10 | 2026-02-10 | Shiv Power | Done | Done
337 | 18/0 | DC2+0 | 2026-02-11 | 2026-02-11 | Shiv Power | Done | Done
338 | 20/2 | DA+0 | 2026-02-11 | 2026-02-11 | Shiv Power | Done | Done
339 | 20/3 | DA+0 | 2026-02-11 | 2026-02-11 | Shiv Power | Done | Done
340 | 21/4 | DA+3 | 2026-02-11 | 2026-02-11 | Shiv Power | Done | Done
341 | 21/5 | DA+6 | 2026-02-11 | 2026-02-11 | Shiv Power | Done | Done
342 | 22/13 | DA+6 | 2026-02-11 | 2026-02-11 | Shiv Power | Done | Done
343 | 43/1 | DA+3 | 2026-02-11 | 2026-02-11 | Suraja Ram | Done | Done
344 | 43/2 | DA+0 | 2026-02-11 | 2026-02-11 | Suraja Ram | Done | Done
345 | 43/3 | DA+0 | 2026-02-11 | 2026-02-11 | Suraja Ram | Done | Done
346 | 43/4 | DA+3 | 2026-02-12 | 2026-02-12 | Suraja Ram | Done | Done
347 | 43/5 | DA+3 | 2026-02-12 | 2026-02-12 | Suraja Ram | Done | Done
348 | 43/6 | DA+3 | 2026-02-12 | 2026-02-12 | Suraja Ram | Done | Done
349 | 43/7 | DA+3 | 2026-02-13 | 2026-02-13 | Suraja Ram | Done | Done
350 | 44/0 | DB1+3 | 2026-02-13 | 2026-02-13 | Suraja Ram | Done | Done
351 | 44/2 | DA+0 | 2026-02-14 | 2026-02-14 | Suraja Ram | Done | Done
352 | 44/6 | DB1+3 | 2026-02-14 | 2026-02-14 | Suraja Ram | Done | Done
353 | 8/4 | DA+3 | 2026-02-20 | 2026-02-20 | Jai Bagrangbali | Done | Done
354 | 8/5 | DA+3 | 2026-02-20 | 2026-02-20 | Jai Bagrangbali | Done | Done
355 | 10/7 | DA+3 | 2026-02-20 | 2026-02-20 | Jai Bagrangbali | Done | Done
356 | 10/9 | DA+0 | 2026-02-21 | 2026-02-21 | Jai Bagrangbali | Done | Done
357 | 10/10 | DA+3 | 2026-02-21 | 2026-02-21 | Jai Bagrangbali | Done | Done
358 | 10/11 | DA+3 | 2026-02-22 | 2026-02-22 | Jai Bagrangbali | Done | Done
359 | 11/0 | DB1+0 | 2026-02-22 | 2026-02-22 | Shiv Power | Done | Done
360 | 16/1 | DA+0 | 2026-02-22 | 2026-02-22 | Chanda Enterprises | Done | Done
361 | 17/1 | DA+3 | 2026-02-22 | 2026-02-22 | Chanda Enterprises | Done | Done
362 | 27/6 | DA+0 | 2026-02-22 | 2026-02-22 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
363 | 27/7 | DB1+0 | 2026-02-22 | 2026-02-22 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
364 | 27/12 | DA+3 | 2026-02-15 | 2026-02-15 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
365 | 28/6 | DA+6 | 2026-02-16 | 2026-02-16 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
366 | 28/7 | DA+3 | 2026-02-16 | 2026-02-16 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
367 | 29/0 | DB1+0 | 2026-02-17 | 2026-02-17 | The Shraddha Cooperative Multipurpose Society Limited | Done | Done
368 | 44/9 | DA+9 | 2026-02-18 | 2026-02-18 | Suraja Ram | Done | Done
369 | 45/0 | DC2+0 | 2026-02-18 | 2026-02-18 | Suraja Ram | Done | Done
370 | 53/0 | DB2+9 | 2026-02-19 | 2026-02-19 | Suraja Ram | Done | Done
371 | 53/1 | DA+9 | 2026-02-19 | 2026-02-19 | Suraja Ram | Done | Done
372 | 53/4 | DA+0 | 2026-02-20 | 2026-02-20 | Suraja Ram | Done | Done
373 | 53/5 | DA+3 | 2026-02-20 | 2026-02-20 | Suraja Ram | Done | Done
374 | 53/6 | DA+6 | 2026-02-21 | 2026-02-21 | Suraja Ram | Done | Done
375 | 53/7 | DA+3 | 2026-02-21 | 2026-02-21 | Suraja Ram | Done | Done
376 | 54/0 | DB1+6 | 2026-02-22 | 2026-02-22 | Suraja Ram | Done | Done
377 | 8/12 | DA+0 | 2026-03-01 | 2026-03-01 | Jai Bagrangbali | Done | Done
378 | 44/8 | DCT+0 | 2026-03-02 | 2026-03-02 | Suraja Ram | Done | Done
379 | 44/10 | DB1+9 | 2026-03-04 | 2026-03-04 | Suraja Ram | Done | Done
380 | 52/3 | DA+9 | 2026-03-05 | 2026-03-05 | Suraja Ram | Done | Done
381 | 54/1 | DA+3 | 2026-03-06 | 2026-03-06 | Suraja Ram | Done | Done
382 | 55/0 | DB1+6 | 2026-03-07 | 2026-03-07 | Suraja Ram | Done | Done
383 | 55/2 | DA+0 | 2026-03-08 | 2026-03-08 | Suraja Ram | Done | Done
384 | 56/0 | DD60+25 | 2026-03-09 | 2026-03-09 | Suraja Ram | Done | Done
385 | 57/0 | DD60+25 | 2026-03-09 | 2026-03-09 | Suraja Ram | Done | Done
386 | 13/0 | DD60+3 | 2026-03-30 | 2026-03-30 | Jai Bagrangbali | Done
387 | 13/2 | DA+3 | 2026-04-01 | 2026-04-01 | Yet to be confirm | Done
388 | 11A/1 | DA+3 | 2026-04-05 | 2026-04-05 | Jai Bagrangbali | Done
389 | 11A/2 | DA+0 | 2026-04-04 | 2026-04-04 | Jai Bagrangbali | Done
390 | 11A/3 | DA+3 | 2026-04-05 | 2026-04-05 | Jai Bagrangbali | Done
391 | 11A/4 | DA+3 | 2026-04-06 | 2026-04-06 | Jai Bagrangbali | Done
392 | 11A/5 | DA+3 | 2026-04-03 | 2026-04-03 | Jai Bagrangbali | Done
393 | 11A/6 | DA+6 | 2026-04-03 | 2026-04-03 | Jai Bagrangbali | Done
394 | 11A/7 | DA+9 | 2026-04-02 | 2026-04-02 | Jai Bagrangbali | Done
395 | 13/1 | DA+9 | 2026-04-01 | 2026-04-01 | Jai Bagrangbali | Done
396 | 13/4 | DA+3 | 2026-04-01 | 2026-04-01 | Jai Bagrangbali | Done
397 | 15/0 | DC1+0 | 2026-04-06 | 2026-04-06 | Jai Bagrangbali | Done
398 | 8/6 | DA+3 | 2026-04-20 | 2026-04-20 | Jai Bagrangbali | Done | Done
399 | 8/7 | DB1+0 | 2026-04-20 | 2026-04-20 | Jai Bagrangbali | Done | Done
400 | 8/8 | DA+6 | 2026-04-21 | 2026-04-21 | Jai Bagrangbali | Done | Done
401 | 8/11 | DA+0 | 2026-04-21 | 2026-04-21 | Jai Bagrangbali | Done | Done
402 | 9/0 | DD60+18 | 2026-04-22 | 2026-04-22 | Jai Bagrangbali | Done | Done
403 | 10/0 | DD60+25 | 2026-04-22 | 2026-04-22 | Jai Bagrangbali | Done | Done
404 | 10/2 | DA+0 | 2026-04-23 | 2026-04-23 | Jai Bagrangbali | Done | Done
405 | 14/0 | DC2+0 | 2026-04-23 | 2026-04-23 | Shiv Power | Done
406 | 19/0 | DC2+0 | 2026-04-24 | 2026-04-24 | Jai Bagrangbali | Done | Done
407 | 21/8 | DA+6 | 2026-04-25 | 2026-04-25 | Jai Bagrangbali | Done | Done
408 | 21/10 | DA+6 | 2026-04-26 | 2026-04-26 | Jai Bagrangbali | Done | Done
409 | 24/0 | DD45+3 | 2026-04-27 | 2026-04-27 | Jai Bagrangbali | Done | Done
410 | 18/3 | DA+0 | 2026-04-29 | 2026-04-29 | Jai Bagrangbali | Done | Done
411 | 14A/2 | DA+0 | 2026-04-30 | 2026-04-30 | Jai Bagrangbali | Done | Done
412 | 14A/1 | DA+3 | 2026-04-30 | 2026-04-30 | Jai Bagrangbali | Done | Done
413 | 53/8 | DA+3 | 2026-04-19 | 2026-04-19 | Suraja Ram | Done | Done
414 | 43/8 | DA+9 | 2026-04-21 | 2026-04-21 | Suraja Ram | Done | Done
415 | 43/9 | DA+9 | 2026-04-22 | 2026-04-22 | Suraja Ram | Done | Done
416 | 43/10 | DA+3 | 2026-04-23 | 2026-04-23 | Suraja Ram | Done | Done
417 | 43/11 | DA+3 | 2026-04-24 | 2026-04-24 | Suraja Ram | Done | Done
418 | 47/5 | DA+0 | 2026-04-16 | 2026-04-16 | Suraja Ram | Done | Done
419 | 37/0 | DB2+0 | 2026-04-29 | 2026-04-29 | Suraja Ram | Done | Done
420 | 34/4 | DA+0 | 2026-05-02 | 2026-05-02 | Suraja Ram | Done | Done
421 | 19/2 | DA+0 | 2026-05-05 | 2026-05-05 | Jai Bagrangbali | Done | Done
422 | 18/4 | DA+0 | 2026-05-05 | 2026-05-05 | Jai Bagrangbali | Done | Done
423 | 21/2 | DA+0 | 2026-05-05 | 2026-05-05 | Jai Bagrangbali | Done | Done
424 | 27/9 | DA+0 | 2026-05-09 | 2026-05-09 | Jai Bagrangbali | Done | Done
425 | 28/3 | DA+0 | 2026-05-10 | 2026-05-10 | Jai Bagrangbali | Done | Done
426 | 28/4 | DA+0 | 2026-05-13 | 2026-05-13 | Jai Bagrangbali | Done | Done
427 | 27/10 | DA+3 | 2026-05-13 | 2026-05-13 | Jai Bagrangbali | Done | Done
428 | 29/3 | DA+0 | 2026-05-14 | 2026-05-14 | Jai Bagrangbali | Done | Done
429 | 28/8 | DA+3 | 2026-05-15 | 2026-05-15 | Jai Bagrangbali | Done | Done
430 | 29/1 | DA+3 | 2026-05-17 | 2026-05-17 | Jai Bagrangbali | Done | Done
431 | 16/0 | DC1+0 | 2026-05-18 | 2026-05-18 | Jai Bagrangbali | Done | Done
432 | 26/0 | DB1+0 | 2026-05-20 | 2026-05-20 | Jai Bagrangbali | Done | Done
433 | 31/0 | DB2+0 | 2026-05-21 | 2026-05-21 | Jai Bagrangbali | Done | Done
434 | 13/3 | DA+3 | 2026-05-24 | 2026-05-24 | Gang name not confimed | Done
435 | 22/4 | DA+9 | 2026-05-31 | 2026-05-31 | Jai Bagrangbali | Done | Done
436 | 20/1 | DA+0 | 2026-06-02 | 2026-06-02 | Jai Bagrangbali | Done | Done
437 | 21/6 | DA+3 | 2026-06-02 | 2026-06-02 | Jai Bagrangbali | Done | Done
438 | 21/7 | DA+3 | 2026-06-02 | 2026-06-02 | Jai Bagrangbali | Done | Done
439 | 27/0 | DC1+0 | 2026-06-02 | 2026-06-02 | Jai Bagrangbali | Done | Done
440 | 30/0 | DC1+0 | 2026-06-03 | 2026-06-03 | Jai Bagrangbali | Done | Done
441 | 23/0 | DD45+3 | 2026-06-07 | 2026-06-07 | Jai Bagrangbali | Done | Done
442 | 25/0 | DC1+6 | 2026-07-03 | 2026-07-03 | Jai Bagrangbali | Done | Done
443 | 30/4 | DA+3 | 2026-07-04 | 2026-07-04 | Jai Bagrangbali | Done | Done
444 | 30/6 | DA+0 | 2026-07-05 | 2026-07-05 | Jai Bagrangbali | Done | Done
445 | 37/1 | DA+9 | 2026-07-06 | 2026-07-06 | Suraja Ram (to be Confirm) | Done | Done
446 | 37/2 | DA+3 | 2026-07-07 | 2026-07-07 | Suraja Ram (to be Confirm) | Done | Done
447 | 37/3 | DA+0 | 2026-07-08 | 2026-07-08 | Suraja Ram (to be Confirm) | Done | Done
448 | 38/1 | DA+0 | 2026-07-09 | 2026-07-09 | Jai Bagrangbali | Done | Done
449 | 38/2 | DA+6 | 2026-07-10 | 2026-07-10 | Jai Bagrangbali | Done | Done
450 | 21/3 | DA+6 | 2026-07-10 | 2026-07-10 | Jai Bagrangbali | Done | Done
451 | 22/9 | DA+6 | 2026-07-11 | 2026-07-11 | Jai Bagrangbali | Done | Done
452 | 22/10 | DA+6 | 2026-07-11 | 2026-07-11 | Jai Bagrangbali | Done | Done
453 | 11/4 | DA+0 | 2026-07-12 | 2026-07-12 | Jai Bagrangbali | Done | Done
454 | 11/3 | DA+0 | 2026-07-12 | 2026-07-12 | Jai Bagrangbali | Done | Done
455 | 22/8 | DB1+0 | 2026-07-13 | 2026-07-13 | Jai Bagrangbali | Done | Done
456 | 22/12 | DA+3 | 2026-07-13 | 2026-07-13 | Jai Bagrangbali | Done | Done
457 | 25/3 | DA+0 | 2026-07-16 | 2026-07-16 | Gang name not confimed | Done | Done
458 | 26/1 | DA+0 | 2026-07-17 | 2026-07-17 | Gang name not confimed | Done | Done
459 | 26/2 | DA+3 | 2026-07-18 | 2026-07-18 | Gang name not confimed | Done | Done
460 | 26/3 | DA+0 | 2026-07-19 | 2026-07-19 | Gang name not confimed | Done | Done
461 | 26/4 | DA+6 | 2026-07-20 | 2026-07-20 | Gang name not confimed | Done | Done
462 | 26/5 | DA+6 | 2026-07-21 | 2026-07-21 | Gang name not confimed | Done | Done
463 | 26/6 | DA+6 | 2026-07-22 | 2026-07-22 | Gang name not confimed | Done | Done
464 | 26/7 | DA+0 | 2026-07-23 | 2026-07-23 | Gang name not confimed | Done | Done
11/3
11/4
13/3
14A/0
17/2
17/3
17/5
18/2
19/1
19/3
19/4
19/5
20/0
20/1
21/0
21/1
21/3
21/6
21/7
21/9
22/0
22/1
22/2
22/3
22/4
22/5
22/6
22/7
22/8
22/9
22/10
22/11
22/12

## Stringing
Progress Summary'!A1 | [14 empty] | 166
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line
Stringing
SL. No. | Section |  | Type of Sections | Gang Name | Section Length | Paying Out/R-Sag |  |  | Final Sag
| From | To |  |  |  | Section Length | Start Date | End Date | Section Length | Start Date | End Date | Remarks | Completion Month
1 | 60/0 | 61/0 | TSE | Kuddus ali | 4.877 | 4.877 | 2024-08-21 | 2024-08-28 | 4.877 | 2024-09-09 | 2024-09-16 | Final sag completed | 2024-09-01
2 | 61/0 | 62/0 | TSE | Kuddus ali | 4.568 | 4.568 | 2024-09-06 | 2024-09-16 | 4.568 | 2024-09-26 | 2024-10-03 | Final sag completed | 2024-10-01
3 | 62/0 | 63/0 | TSE | Kuddus ali | 4.863 | 4.863 | 2024-09-23 | 2024-10-02 | 4.863 | 2024-10-17 | 2024-10-22 | Final sag completed | 2024-10-01
4 | 63/0 | 64/0 | TSE | Kuddus ali | 3.711 | 3.711 | 2024-10-14 | 2024-10-21 | 3.711 | 2024-10-31 | 2024-11-06 | Final sag completed | 2024-11-01
5 | 64/0 | 65/0 | TSE | Kuddus ali | 4.918 | 4.918 | 2024-10-30 | 2024-11-05 | 4.918 | 2024-11-13 | 2024-11-16 | Final sag completed | 2024-11-01
6 | 59/8 | 60/0 | TSE | Gopal Associate | 3.778 | 3.778 | 2024-12-22 | 2024-12-27 | 3.778 | 2025-01-04 | 2025-01-09 | Final sag completed | 2025-01-01
7 | 59/0 | 59/8 | TSE | Gopal Associate | 3.337 | 3.337 | 2025-01-02 | 2025-01-08 | 3.337 | 2025-01-12 | 2025-01-15 | Final sag completed | 2025-01-01
8 | 65/0 | 66/0 | TSE | MR Power | 4.736 | 4.736 | 2025-02-03 | 2025-03-22 | 4.736 | 2025-03-10 | 2025-03-23 | Final sag completed | 2025-03-01
9 | 50/0 | 51/0 | TSE | Gopal Associate | 4.444 | 4.444 | 2025-03-12 | 2025-03-23 | 4.444 | 2025-03-17 | 2025-03-24 | Final sag completed | 2025-03-01
10 | 49/0 | 50/0 | TSE | Gopal Associate | 3.227 | 3.227 | 2025-02-06 | 2025-02-19 | 3.227 | 2025-05-01 | 2025-05-05 | Final sag completed | 2025-05-01
11 | 51/0 | 52/0 | TSE | Gopal Associate | 1.049 | 1.049 | 2025-04-02 | 2025-04-08 | 1.049 | 2025-04-04 | 2025-04-09 | Final sag completed | 2025-04-01
12 | 73/0 | 74/0 | TSE | JPJ Construction/MC Power | 3.788 | 3.788 | 2025-06-01 | 2025-06-21 | 3.788 | 2025-09-26 | 2025-09-30 | Final sag completed | 2025-09-01
13 | 72/0 | 73/0 | TSE | JPJ Construction/MC Power | 1.628 | 1.628 | 2025-11-03 | 2025-11-08 | 1.628 | 2025-11-21 | 2025-11-25 | Final sag completed. | 2025-11-01
14 | 2/0 | 3/0 | TSE | Devi Power | 3.823 | 3.823 | 2025-11-13 | 2025-11-18 | 3.823 | 2025-12-30 | 2026-01-14 | Final sag completed. | 2026-01-01
15 | 71/0 | 72/0 | TSE | MC Power | 3.675 | 3.675 | 2025-11-20 | 2025-11-25 | 3.675 | 2025-11-28 | 2025-11-30 | Final sag completed. | 2025-11-01
16 | 1A/0 | 2/0 | TSE | Devi Power | 3.426 | 3.426 | 2025-11-21 | 2025-11-28 | 3.426 | 2025-11-28 | 2025-11-30 | Final sag completed. | 2025-11-01
17 | 70/0 | 71/0 | TSE | MC Power | 4.966 | 4.966 | 2025-12-08 | 2025-12-16 | 4.966 | 2025-12-12 | 2025-12-17 | Final sag completed. | 2025-12-01
18 | 56/0 | 57/0 | M | Gopal Associate, Hotline | 0.22 | 0.22 | 2025-11-20 | 2025-11-26 | 0.22 | 2025-11-20 | 2025-11-26 | Final sag completed. | 2025-11-01
19 | 46/0 | 47/0 | M | Gopal Associate, Hotline | 0.19908 | 0.19908 | 2025-12-06 | 2025-12-11 | 0.19908 | 2025-12-06 | 2025-12-11 | Final sag completed. | 2025-12-01
20 | 69/0 | 70/0 | TSE | MC Power | 0.769 | 0.769 | 2025-12-18 | 2025-12-24 | 0.769 | 2025-12-21 | 2025-12-25 | Final sag completed. | 2025-12-01
21 | 67/0 | 68/0 | TSE | MC Power | 1.061 | 1.061 | 2025-12-26 | 2025-12-28 | 1.061 | 2026-01-06 | 2026-01-08 | Final sag completed. | 2026-01-01
22 | 68/0 | 69/0 | M | MC Power | 0.2 | 0.2 | 2025-12-29 | 2025-12-29 | 0.2 | 2025-12-29 | 2025-12-29 | Final sag completed. | 2025-12-01
23 | 66/0 | 67/0 | M | MC Power | 0.2078 | 0.2078 | 2026-01-03 | 2026-01-03 | 0.2078 | 2026-01-03 | 2026-01-03 | Final sag completed. | 2026-01-01
24 | 3/0 | 4/0 | M | Gopal Associate, Hotline | 0.2265 | 0.2265 | 2026-01-10 | 2026-01-16 | 0.2265 | 2026-01-11 | 2026-01-16 | Final sag completed. | 2026-01-01
25 | 57/0 | 58/0 | TSE | MC Power | 3.287 | 3.287 | 2026-01-19 | 2026-01-24 | 3.287 | 2026-01-29 | 2026-01-31 | Final sag completed. | 2026-01-01
26 | 10/12 | 11/0 | TSE | Deepak Sarkar | 4.95 | 4.95 | 2026-01-14 | 2026-01-22 | 4.95 | 2026-02-05 | 2026-02-07 | Final sag completed. | 2026-02-01
27 | 47/0 | 48/0 | TSE | Krishna-1 | 4.477 | 4.477 | 2026-01-26 | 2026-01-31 | 4.477 | 2026-01-28 | 2026-01-31 | Final sag completed. | 2026-01-01
28 | 48/0 | 49/0 | TSE | Krishna-1 | 0.83 | 0.83 | 2026-01-17 | 2026-01-20 | 0.83 | 2026-01-20 | 2026-01-23 | Final sag completed. | 2026-01-01
29 | 58/0 | 59/0 | M | MC Power | 0.2389 | 0.2389 | 2026-01-28 | 2026-01-28 | 0.2389 | 2026-01-28 | 2026-01-28 | Final sag completed. | 2026-01-01
30 | 45/0 | 46/0 | TSE | Krishna-1 | 0.70146 | 0.70146 | 2026-02-07 | 2026-02-08 | 0.70146 | 2026-02-10 | 2026-02-13 | Final sag completed. | 2026-02-01
31 | 44/10 | 45/0 | TSE | Krishna-1 | 0.755 | 0.755 | 2026-02-09 | 2026-02-12 | 0.755 | 2026-02-17 | 2026-02-20 | Final sag completed. | 2026-02-01
32 | 7/0 | 8/0 | M | Gopal Associate, Hotline | 0.211 | 0.211 | 2026-02-20 | 2026-02-26 | 0.211 | 2026-02-20 | 2026-02-26 | Final sag completed. | 2026-02-01
33 | 55/0 | 56/0 | TSE | MC Power | 3.318 | 3.318 | 2026-02-12 | 2026-03-25 | 3.318 | 2026-03-27 | 2026-03-31 | Final sag completed. | 2026-03-01
34 | 44/8 | 44/10 | TSE | Krishna-1 | 0.795 | 0.795 | 2026-02-16 | 2026-02-19 | 0.795 | 2026-03-10 | 2026-03-13 | Final sag completed. | 2026-03-01
35 | 44/6 | 44/8 | TSE | Krishna-1 | 0.84 | 0.84 | 2026-03-20 | 2026-03-23 | 0.84 | 2026-03-28 | 2026-03-31 | Final sag completed. | 2026-03-01
36 | 1/0 | 1A/0 | M | Devi Power | 0.09 | 0.09 | 2026-03-24 | 2026-03-31 | 0.09 | 2026-03-24 | 2026-03-31 | Final sag completed. | 2026-03-01
37 | 44/0 | 44/6 | TSE | Krishna-1 | 2.312 | 2.312 | 2026-03-27 | 2026-03-31 | 2.312 | 2026-03-28 | 2026-03-31 | Final Sag completed. | 2026-03-01
38 | Gty | 1/0 | M | Devi Power | 0.122 | 0.122 | 2026-03-27 | 2026-03-30 | 0.122 | 2026-03-27 | 2026-03-30 | Final Sag completed. | 2026-03-01
39 | 10/0 | 10/12 | TSE | Deepak Sarkar | 4.894 | 4.894 | 2026-03-09 | 2026-03-15 | 4.894 | 2026-04-04 | 2026-04-08 | Final Sag completed. | 2026-04-01
40 | 14/0 | 14A/0 | M | Nasiruddin | 0.381 | 0.381 | 2026-03-30 | 2026-04-06 | 0.381 | 2026-04-05 | 2026-04-06 | Final Sag completed. | 2026-04-01
41 | 8/7 | 9/0 | TSE | Deepak Sarkar | 2.456 | 2.456 | 2026-03-30 | 2026-04-03 | 2.456 | 2026-04-06 | 2026-04-08 | Final Sag completed. | 2026-04-01
42 | 9/0 | 10/0 | M | Gopal Associate, Hotline | 0.233 | 0.233 | 2026-04-03 | 2026-04-09 | 0.233 | 2026-04-03 | 2026-04-10 | Final Sag completed. | 2026-04-01
43 | 54/0 | 55/0 | TSE | MC Power | 2.411 | 2.411 | 2026-04-03 | 2026-04-09 | 2.411 | 2026-04-08 | 2026-04-11 | Final Sag completed. | 2026-04-01
44 | 8/0 | 8/7 | TSE | Devi Power | 2.861 | 2.861 | 2026-04-06 | 2026-04-09 | 2.861 | 2026-04-08 | 2026-04-11 | Final Sag completed. | 2026-04-01
45 | 43/0 | 44/0 | TSE | Krishna-1 | 4.8527 | 4.8527 | 2026-04-08 | 2026-04-15 | 4.8527 | 2026-04-16 | 2026-04-18 | Final Sag completed. | 2026-04-01 | 18
46 | 6/0 | 7/0 | TSE | Deepak Sarkar / Nasiruddin | 1.14 | 1.14 | 2025-03-19 | 2026-04-15 | 1.14 | 2026-03-24 | 2026-04-30 | Final Sag completed. | 2026-04-01
47 | 53/0 | 54/0 | TSE | MC Power | 3.69 | 3.69 | 2025-04-18 | 2026-04-26 | 3.69 | 2026-04-30 | 2026-04-30 | Final Sag completed. | 2026-04-01 | 28
48 | 5/0 | 6/0 | M | Gopal Associate, Hotline | 0.246 | 0.246 | 2026-04-24 | 2026-04-30 | 0.246 | 2026-04-24 | 2026-04-30 | Final Sag completed. | 2026-04-01
49 | 14A/0 | 15/0 | TSE | Nasiruddin | 1.192 | 1.192 | 2026-04-25 | 2026-05-04 | 1.192 | 2026-05-02 | 2026-05-04 | Final Sag completed. | 2026-05-01
50 | 13/0 | 14/0 | TSE | Nasiruddin | 2.078 | 2.078 | 2026-03-30 | 2026-04-04 | 2.078 | 2026-05-12 | 2026-05-13 | Final Sag completed. | 2026-05-01
51 | 52/0 | 53/0 | TSE | MC Power | 4.534 | 4.534 | 2026-05-10 | 2026-05-16 | 4.534 | 2026-05-18 | 2026-05-22 | Final Sag completed. | 2026-05-01
52 | 11A/0 | 12/0 | TSE | Nasiruddin | 4.11 | 4.11 | 2026-05-18 | 2026-05-16 | 4.11 | 2026-05-27 | 2026-05-29 | Final Sag completed. | 2026-05-01
53 | 12/0 | 13/0 | M | Gopal Associate, Hotline | 0.2119 | 0.2119 | 2026-05-26 | 2026-05-31 | 0.2119 | 2026-05-26 | 2026-05-31 | Final Sag completed. | 2026-05-01
54 | 23/0 | 24/0 | M | Gopal Associate, Hotline | 0.2222 | 0.2222 | 2026-06-09 | 2026-06-16 | 0.2222 | 2026-06-09 | 2026-06-16 | Final Sag completed. | 2026-06-01
55 | 24/0 | 25/0 | M | MC Power | 0.434 | 0.434 | 2026-06-21 | 2026-06-26 | 0.434 | 2026-06-21 | 2026-06-26 | Final Sag completed. | 2026-06-01
56 | 11/0 | 11A/0 | TSE | Nasiruddin | 2.238 | 2.238 | 2026-06-17 | 2026-06-22 | 2.238 | 2026-06-23 | 2026-06-26 | Final Sag completed. | 2026-06-01
57 | 27/0 | 27/7 | TSE | Mohammad Construction / Furkhan | 2.8104 | 2.8104 | 2026-06-22 | 2026-06-29 | 2.8104 | 2026-07-01 | 2026-07-05 | Final Sag Completed. | 2026-07-01
58 | 22/8 | 23/0 | TSE | MC Power | 2.3018 | 2.3018 | 2026-06-30 | 2026-07-04 | 2.3018 | 2026-07-05 | 2026-07-09 | Final Sag Completed. | 2026-07-01
59 | 29/0 | 30/0 | TSE | Jamera Bibi | 2.0107 | 2.0107 | 2026-06-23 | 2026-06-29 | 2.0107 | 2026-07-02 | 2026-07-06 | Final Sag Completed. | 2026-07-01
60 | 15/0 | 16/0 | TSE | Nasiruddin | 0.8179 | 0.8179 | 2026-07-04 | 2026-07-06 | 0.8179 | 2026-07-11 | 2026-07-15 | Final Sag completed. | 2026-07-01
61 | 4/0 | 5/0 | TSE | Nasiruddin | 1.8731 | 1.8731 | 2026-07-17 | 2026-07-19 | 1.8731 | 2026-07-20 | 2026-07-21 | Final Sag completed. | 2026-07-01
63 | 27/7 | 28/0 | TSE | Mohammad Construction / Furkhan | 2.3869 | 2.3869 | 2026-07-11 | 2026-07-16 | 2.3869 | 2026-07-20 | 2026-07-23 | Final Sag Completed. | 2026-07-01
64 | 22/0 | 22/8 | TSE | MC Power | 3.1771 | 3.1771 | 2026-08-21 | 2026-07-26 | 3.1771 | 2026-07-23 | 2026-07-27 | Final Sag Completed. | 2026-07-01 | 47
65 | 30/0 | 31/0 | TSE | Jamera Bibi | 2.7193 | 2.7193 | 2026-07-11 | 2026-07-22 | 2.7193 | 2026-07-26 | 2026-07-28 | Final Sag Completed. | 2026-07-01 | 38
66 | 31/0 | 32/0 | TSE | Jamera Bibi | 1.0825 |  | Platina P/out |  |  |  |  | Insulator hoisting Completed.
67 | 16/0 | 17/0 | TSE | Nasiruddin | 2.3362 | 2.3362 | 2026-07-11 | 2026-07-15 |  | 2026-07-28 |  | 2 phase Final Sag done.
68 | 28/0 | 29/0 | TSE | Mohammad Construction / Furkhan | 3.6391 |  | 2026-07-27 |  |  |  |  | 2nd phase R/Sag Completed. |  | 53
69 | 17/0 | 18/0 | TSE | Nasiruddin | 2.451 |  | 2026-07-27 |  |  | 2026-07-29 |  | 2 phase Final Sag done.
70 | 25/0 | 26/0 | TSE | MC Power | 1.97 | [6 empty] | Insulator hoisting 25/4.
TOTAL |  |  |  |  | 158.3855 | 149.2429 |  |  | 146.9067
144.182
[5 empty] | S. Len-P.O. | 9.1426 |  |  | 168.105
[5 empty] | P/O-F/S | 2.3362 |  |  | 21.1983
9.7195
1 | 20/0 | 21/0 | TSE | Gang Not Allocated | 1.48
2 | 21/0 | 22/0 | TSE | Gang Not Allocated | 4.58
4 | 26/0 | 27/0 | TSE | Gang Not Allocated | 3.66 | [6 empty] | Insulator hoisting WIP.
1 | 32/0 | 33/0 | TSE | Tata Projects Limited | 2.075 | 2.075 |  |  | 2.075 |  |  | Completed
2 | 33/0 | 34/0 | TSE | Tata Projects Limited | 0.672 | 0.672 |  |  | 0.672 |  |  | Completed
3 | 34/0 | 35/0 | TSE | Tata Projects Limited | 2.048 | 2.048 |  |  | 2.048 |  |  | Completed
4 | 35/0 | 35/2 | TSE | Tata Projects Limited | 0.758 | 0.758 |  |  | 0.758 |  |  | Completed
5 | 35/2 | 35/3 | M | Tata Projects Limited | 0.522 | 0.522 |  |  | 0.522 |  |  | Completed
6 | 35/3 | 36/0 | TSE | Tata Projects Limited | 1.183 | 1.183 |  |  | 1.183 |  |  | Completed
7 | 36/0 | 37/0 | TSE | Tata Projects Limited | 1.8845 | 1.8845 |  |  | 1.8845 |  |  | Completed
8 | 37/0 | 38/0 | TSE | Tata Projects Limited | 1.64 | 1.64 |  |  | 1.64 |  |  | Completed
9 | 38/0 | 39/0 | TSE | Tata Projects Limited | 2.101 | 2.101 |  |  | 2.101 |  |  | Completed
10 | 39/0 | 40/0 | TSE | Tata Projects Limited | 0.735 | 0.735 |  |  | 0.735 |  |  | Completed
11 | 40/0 | 41/0 | TSE | Tata Projects Limited | 1.66 | 1.66 |  |  | 1.66 |  |  | Completed
12 | 41/0 | 42/0 | TSE | Tata Projects Limited | 1.1709 | 1.1709 |  |  | 1.1709 |  |  | Completed
13 | 42/0 | 43/0 | TSE | Tata Projects Limited | 2.667 | 2.667 |  |  | 2.667 |  |  | Completed
14 | 18/0 | 19/0 | TSE | Tata Projects Limited | 1.91 | [6 empty] | WIP
15 | 19/0 | 20/0 | TSE | Tata Projects Limited | 2.26
[5 empty] | 23.2864 | 19.1164 |  |  | 19.1164
Formulas:
Start Date = [End Date]-6

## Stringing associated works
Progress Summary'!A1 | [10 empty] | Sterlite+Apar | Sterlite | Deccan | Deccan | Moosedorfer | Moosedorfer | Moosedorfer | Moosedorfer | Moosedorfer | Moosedorfer | Moosedorfer | Moosedorfer | Moosedorfer | Moosedorfer | Moosedorfer | Moosedorfer | Moosedorfer | Moosedorfer | Moosedorfer
LINE MATERIAL, PACKAGE-F
As per details shared on dated 10.03.2025 | [12 empty] | CLR Insulators |  | Hardware Fittings (Set) |  |  |  | Conductor Accessories for AL59 Zebra |  |  |  |  | Earthwire Accessories | [5 empty] | Remarks
Sl No | Twr No. | Tower Type | A | B | C | D | Deviation Angle (DMS) | Span (m) |  | Section Length (m) | Conductor (Mtr.) | Earthwire (Mtr.) | 210 KN Insulator Rod for 765KV(2*2975 or 1*5950)mm lenth | 160 KN Insulator Rod for 765KV(2*2975 or 1*5950)mm lenth | 4x210KN Quad Tension for 765KV | 2x160KN Double Suspension Insulator string | 160KN Single "I" Pilot string | Single tension Insulator string | MSCJ | Repair Sleeve | Hexa Spacer Damper for 765KV AL59 Zebra | Rigid Spacer for 765KV AL59 Zebra | T - Connector | Tension Clamp | Suspension Clamp | Flexible Copper bond | MSCJ | Repair Sleeve | VD
| GANTRY | GTY |  |  |  |  | 00°00'00" | [5 empty] | 24 | 6 | 6 | [8 empty] | 3 |  |  |  |  | 6
[8 empty] | 121.998 | 125 |  | 4500 | 375 | [8 empty] | 12
1 | 1/0 | DE |  |  |  |  | 11°14'51"LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 3 |  | 3 |  |  | 4
[8 empty] | 89.999 | 90 |  | 3240 | 90 | [8 empty] | 6
2 | 1A/0 | DD60+0 |  |  |  |  | 52°22'23.88"LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 277.726 | 280 |  | 10080 | 280 | [8 empty] | 30
3 | 1A/1 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 386.044 | 390 |  | 14040 | 390 | [8 empty] | 42
4 | 1A/2 | DA+0 | 0 | 1 | 1 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 443.632 | 445 |  | 16020 | 445 | [8 empty] | 48
5 | 1A/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 333.393 | 335 |  | 12060 | 335 | [8 empty] | 36
6 | 1A/4 | DA+3 | 0 | 0 | 1 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 431.848 | 435 |  | 15660 | 435 | [8 empty] | 42
7 | 1A/5 | DA+0 | 1 | 1 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 348.735 | 350 |  | 12600 | 350 | [8 empty] | 36
8 | 1A/6 | DA+0 | 1 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 395.693 | 400 |  | 14400 | 400 | [8 empty] | 42
9 | 1A/7 | DA+3 | 0 | 1 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 414.953 | 415 |  | 14940 | 415 | [8 empty] | 42
10 | 1A/8 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 394.306 | 395 |  | 14220 | 395 | [8 empty] | 42
11 | 2/0 | DC1+0 |  |  |  |  | 16° 05' 50.64" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 405.342 | 410 |  | 14760 | 410 | [8 empty] | 42
12 | 2/1 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 338.507 | 340 |  | 12240 | 340 | [8 empty] | 36
13 | 2/2 | DA+3 | 0 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 406.023 | 410 |  | 14760 | 410 | [8 empty] | 42
14 | 2/3 | DA+3 | 1 | 0 | 1 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 428.949 | 430 |  | 15480 | 430 | [8 empty] | 42
15 | 2/4 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 411.548 | 415 |  | 14940 | 415 | [8 empty] | 42
16 | 2/5 | DA+3 | 0 | 0 | 1 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 425.741 | 430 |  | 15480 | 430 | [8 empty] | 42
17 | 2/6 | DA+3 | 0 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 408.176 | 410 |  | 14760 | 410 | [8 empty] | 42
18 | 2/7 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 354.581 | 355 |  | 12780 | 355 | [8 empty] | 36
19 | 2/8 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 308.656 | 310 |  | 11160 | 310 | [8 empty] | 30
20 | 2/9 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 335.979 | 340 |  | 12240 | 340 | [8 empty] | 36
21 | 3/0 | DD60+6 |  |  |  |  | 01° 29' 56.04" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 226.52 | 230 |  | 8280 | 230 | [8 empty] | 24
22 | 4/0 | DD60+6 |  |  |  |  | 07° 48' 05.04" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 343.373 | 345 |  | 12420 | 345 | [8 empty] | 36
23 | 4/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 358.444 | 360 |  | 12960 | 360 | [8 empty] | 36
24 | 4/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 381.012 | 385 |  | 13860 | 385 | [8 empty] | 42
25 | 4/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 367.624 | 370 |  | 13320 | 370 | [8 empty] | 36
26 | 4/4 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 423.091 | 425 |  | 15300 | 425 | [8 empty] | 42
27 | 5/0 | DB1+9,5RC | 5 | 5 | 5 | 5 | 05° 43' 49.08" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 246.019 | 250 |  | 9000 | 250 | [8 empty] | 24
28 | 6/0 | DB2+9,5RC | 5 | 5 | 5 | 5 | 10° 20' 7.44" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 429.917 | 430 |  | 15480 | 430 | [8 empty] | 42
29 | 6/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 362.365 | 365 |  | 13140 | 365 | [8 empty] | 36
30 | 6/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 347.864 | 350 |  | 12600 | 350 | [8 empty] | 36
31 | 7/0 | DB1+0 | 2 | 3 | 3 | 2 | 04° 51' 39.96" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 210.755 | 215 |  | 7740 | 215 | [8 empty] | 24
32 | 8/0 | DB1+0 |  |  |  |  | 01° 26' 19.32" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 409.202 | 410 |  | 14760 | 410 | [8 empty] | 42
33 | 8/1 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 413.633 | 415 |  | 14940 | 415 | [8 empty] | 42
34 | 8/2 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 393.241 | 395 |  | 14220 | 395 | [8 empty] | 42
35 | 8/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 416.473 | 420 |  | 15120 | 420 | [8 empty] | 42
36 | 8/4 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 394.562 | 395 |  | 14220 | 395 | [8 empty] | 42
37 | 8/5 | DA+3 | 0 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 393.204 | 395 |  | 14220 | 395 | [8 empty] | 42
38 | 8/6 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 441.058 | 445 |  | 16020 | 445 | [8 empty] | 48
39 | 8/7 | DB1+0 |  |  |  |  | 00° 00' 00" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 419.392 | 420 |  | 15120 | 420 | [8 empty] | 42
40 | 8/8 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 390.864 | 395 |  | 14220 | 395 | [8 empty] | 42
41 | 8/9 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 413.404 | 415 |  | 14940 | 415 | [8 empty] | 42
42 | 8/10 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 402.636 | 405 |  | 14580 | 405 | [8 empty] | 42
43 | 8/11 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 372.046 | 375 |  | 13500 | 375 | [8 empty] | 42
44 | 8/12 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 457.703 | 460 |  | 16560 | 460 | [8 empty] | 48
45 | 9/0 | DD60+18 |  |  |  |  | 20° 13' 33.24" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 233.076 | 235 |  | 8460 | 235 | [8 empty] | 24
46 | 10/0 | DD60+25 |  |  |  |  | 33° 37' 51.96" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 443.71 | 445 |  | 16020 | 445 | [8 empty] | 48
47 | 10/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 383.235 | 385 |  | 13860 | 385 | [8 empty] | 42
48 | 10/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 398.553 | 400 |  | 14400 | 400 | [8 empty] | 42
49 | 10/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 410.719 | 415 |  | 14940 | 415 | [8 empty] | 42
50 | 10/4 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 416.15 | 420 |  | 15120 | 420 | [8 empty] | 42
51 | 10/5 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 403.399 | 405 |  | 14580 | 405 | [8 empty] | 42
52 | 10/6 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 373.846 | 375 |  | 13500 | 375 | [8 empty] | 42
53 | 10/7 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 411.824 | 415 |  | 14940 | 415 | [8 empty] | 42
54 | 10/8 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 414.2 | 415 |  | 14940 | 415 | [8 empty] | 42
55 | 10/9 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 402.294 | 405 |  | 14580 | 405 | [8 empty] | 42
56 | 10/10 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 430.283 | 435 |  | 15660 | 435 | [8 empty] | 42
57 | 10/11 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 406.223 | 410 |  | 14760 | 410 | [8 empty] | 42
58 | 10/12 | DB1+0 |  |  |  |  | 00° 00' 00" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 405.251 | 410 |  | 14760 | 410 | [8 empty] | 42
59 | 10/13 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 427.084 | 430 |  | 15480 | 430 | [8 empty] | 42
60 | 10/14 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 400.036 | 405 |  | 14580 | 405 | [8 empty] | 42
61 | 10/15 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 412.79 | 415 |  | 14940 | 415 | [8 empty] | 42
62 | 10/16 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 387.758 | 390 |  | 14040 | 390 | [8 empty] | 42
63 | 10/17 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 436.732 | 440 |  | 15840 | 440 | [8 empty] | 42
64 | 10/18 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 403.689 | 405 |  | 14580 | 405 | [8 empty] | 42
65 | 10/19 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 409.528 | 410 |  | 14760 | 410 | [8 empty] | 42
66 | 10/20 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 418.56 | 420 |  | 15120 | 420 | [8 empty] | 42
67 | 10/21 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 410.253 | 415 |  | 14940 | 415 | [8 empty] | 42
68 | 10/22 | DA+0 | 1 | 3 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 383.968 | 385 |  | 13860 | 385 | [8 empty] | 42
69 | 10/23 | DA+0 | 0 | 2 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 450.808 | 455 |  | 16380 | 455 | [8 empty] | 48
70 | 11/0 | DB1+0 | 1 | 4 | 0 | 3 | [6 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 384.218 | 385 |  | 13860 | 385 | [8 empty] | 42
71 | 11/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 338.549 | 340 |  | 12240 | 340 | [8 empty] | 36
72 | 11/2 | DA+0 | 2 | 1 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 370.74 | 375 |  | 13500 | 375 | [8 empty] | 36
73 | 11/3 | DA+0 | 0 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 434.099 | 435 |  | 15660 | 435 | [8 empty] | 42
74 | 11/4 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 368.102 | 370 |  | 13320 | 370 | [8 empty] | 36
75 | 11/5 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 342.28 | 345 |  | 12420 | 345 | [8 empty] | 36
76 | 11A/0 | DB1+0 |  |  |  |  | 01° 00' 23.04" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 405.114 | 410 |  | 14760 | 410 | [8 empty] | 42
77 | 11A/1 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 412.146 | 415 |  | 14940 | 415 | [8 empty] | 42
78 | 11A/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 412.223 | 415 |  | 14940 | 415 | [8 empty] | 42
79 | 11A/3 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 422.072 | 425 |  | 15300 | 425 | [8 empty] | 42
80 | 11A/4 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 418.268 | 420 |  | 15120 | 420 | [8 empty] | 42
81 | 11A/5 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 384.308 | 385 |  | 13860 | 385 | [8 empty] | 42
82 | 11A/6 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 434.199 | 435 |  | 15660 | 435 | [8 empty] | 42
83 | 11A/7 | DA+9 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 390.121 | 395 |  | 14220 | 395 | [8 empty] | 42
84 | 11A/8 | DA+6 | 0 | 2 | 4 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 426.314 | 430 |  | 15480 | 430 | [8 empty] | 42
85 | 11A/9 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 405.867 | 410 |  | 14760 | 410 | [8 empty] | 42
86 | 12/0 | DD60+0 |  |  |  |  | 52° 09' 12.24" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 211.914 | 215 |  | 7740 | 215 | [8 empty] | 24
87 | 13/0 | DD60+3 |  |  |  |  | 50° 55' 18.84" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 464.251 | 465 |  | 16740 | 465 | [8 empty] | 48
88 | 13/1 | DA+9 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 373.688 | 375 |  | 13500 | 375 | [8 empty] | 42
89 | 13/2 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 419.672 | 420 |  | 15120 | 420 | [8 empty] | 42
90 | 13/3 | DA+3 | 0 | 0 | 2 | 4 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 420.252 | 425 |  | 15300 | 425 | [8 empty] | 42
91 | 13/4 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 400.037 | 405 |  | 14580 | 405 | [8 empty] | 42
92 | 14/0 | DC2+0 |  |  |  |  | 23° 35' 02.76" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 381.413 | 385 |  | 13860 | 385 | [8 empty] | 42
93 | 14A/0 | DC1+0 |  |  |  |  | 17° 04' 19.92" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 412.766 | 415 |  | 14940 | 415 | [8 empty] | 42
94 | 14A/1 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 396.03 | 400 |  | 14400 | 400 | [8 empty] | 42
95 | 14A/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 383.335 | 385 |  | 13860 | 385 | [8 empty] | 42
96 | 15/0 | DC1+0 |  |  |  |  | 19° 19' 46.92" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 404.587 | 405 |  | 14580 | 405 | [8 empty] | 42
97 | 15/1 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 413.327 | 415 |  | 14940 | 415 | [8 empty] | 42
98 | 16/0 | DC1+0 |  |  |  |  | 18° 26' 35.88" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 354.282 | 355 |  | 12780 | 355 | [8 empty] | 36
99 | 16/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 424.282 | 425 |  | 15300 | 425 | [8 empty] | 42
100 | 16/2 | DA+0 | 1 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 340.311 | 345 |  | 12420 | 345 | [8 empty] | 36
101 | 16/3 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 404.648 | 405 |  | 14580 | 405 | [8 empty] | 42
102 | 16/4 | DA+0 | 0 | 1 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 425.863 | 430 |  | 15480 | 430 | [8 empty] | 42
103 | 16/5 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 386.772 | 390 |  | 14040 | 390 | [8 empty] | 42
104 | 17/0 | DB2+3 | 0 | 0 | 0 | 1 | 12° 43' 17.04" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 393.724 | 395 |  | 14220 | 395 | [8 empty] | 42
105 | 17/1 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 415.886 | 420 |  | 15120 | 420 | [8 empty] | 42
106 | 17/2 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 422.815 | 425 |  | 15300 | 425 | [8 empty] | 42
107 | 17/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 409.889 | 410 |  | 14760 | 410 | [8 empty] | 42
108 | 17/4 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 425.336 | 430 |  | 15480 | 430 | [8 empty] | 42
109 | 17/5 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 383.432 | 385 |  | 13860 | 385 | [8 empty] | 42
110 | 18/0 | DC2+0 |  |  |  |  | 24° 50' 58.2" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 372.844 | 375 |  | 13500 | 375 | [8 empty] | 42
111 | 18/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 379.803 | 380 |  | 13680 | 380 | [8 empty] | 42
112 | 18/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 370.997 | 375 |  | 13500 | 375 | [8 empty] | 42
113 | 18/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 398.701 | 400 |  | 14400 | 400 | [8 empty] | 42
114 | 18/4 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 380.821 | 385 |  | 13860 | 385 | [8 empty] | 42
115 | 19/0 | DC2+0 |  |  |  |  | 28° 14' 9.24" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 366.875 | 370 |  | 13320 | 370 | [8 empty] | 36
116 | 19/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 372.501 | 375 |  | 13500 | 375 | [8 empty] | 42
117 | 19/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 376.459 | 380 |  | 13680 | 380 | [8 empty] | 42
118 | 19/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 384.284 | 385 |  | 13860 | 385 | [8 empty] | 42
119 | 19/4 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 375.36 | 380 |  | 13680 | 380 | [8 empty] | 42
120 | 19/5 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 381.243 | 385 |  | 13860 | 385 | [8 empty] | 42
121 | 20/0 | DB2+0 |  |  |  |  | 12° 15' 49.68" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 386.781 | 390 |  | 14040 | 390 | [8 empty] | 42
122 | 20/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 387.041 | 390 |  | 14040 | 390 | [8 empty] | 42
123 | 20/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 348.466 | 350 |  | 12600 | 350 | [8 empty] | 36
124 | 20/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 354.966 | 355 |  | 12780 | 355 | [8 empty] | 36
125 | 21/0 | DB2+0 |  |  |  |  | 14° 55' 19.2" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 414.903 | 415 |  | 14940 | 415 | [8 empty] | 42
126 | 21/1 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 407.236 | 410 |  | 14760 | 410 | [8 empty] | 42
127 | 21/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 432.227 | 435 |  | 15660 | 435 | [8 empty] | 42
128 | 21/3 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 401.871 | 405 |  | 14580 | 405 | [8 empty] | 42
129 | 21/4 | DA+3 | 0 | 1 | 2 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 434.179 | 435 |  | 15660 | 435 | [8 empty] | 42
130 | 21/5 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 405.501 | 410 |  | 14760 | 410 | [8 empty] | 42
131 | 21/6 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 426.014 | 430 |  | 15480 | 430 | [8 empty] | 42
132 | 21/7 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 406.905 | 410 |  | 14760 | 410 | [8 empty] | 42
133 | 21/8 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 433.253 | 435 |  | 15660 | 435 | [8 empty] | 42
134 | 21/9 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 372.897 | 375 |  | 13500 | 375 | [8 empty] | 42
135 | 21/10 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 443.539 | 445 |  | 16020 | 445 | [8 empty] | 48
136 | 22/0 | DB2+3 |  |  |  |  | 09° 09' 25.92" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 456.348 | 460 |  | 16560 | 460 | [8 empty] | 48
137 | 22/1 | DA+9 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 379.199 | 380 |  | 13680 | 380 | [8 empty] | 42
138 | 22/2 | DA+6 | 0 | 0 | 0 | 2 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 382.622 | 385 |  | 13860 | 385 | [8 empty] | 42
139 | 22/3 | DA+9 | 0 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 435.556 | 440 |  | 15840 | 440 | [8 empty] | 42
140 | 22/4 | DA+9 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 402.063 | 405 |  | 14580 | 405 | [8 empty] | 42
141 | 22/5 | DA+9,2RC | 2 | 2 | 2 | 2 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 417.315 | 420 |  | 15120 | 420 | [8 empty] | 42
142 | 22/6 | DA+0 | 0 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 347.702 | 350 |  | 12600 | 350 | [8 empty] | 36
143 | 22/7 | DA+0 | 0 | 1 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 356.245 | 360 |  | 12960 | 360 | [8 empty] | 36
144 | 22/8 | DB1+0 | 0 | 2 | 1 | 1 | 00° 00' 00" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 389.193 | 390 |  | 14040 | 390 | [8 empty] | 42
145 | 22/9 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 343.775 | 345 |  | 12420 | 345 | [8 empty] | 36
146 | 22/10 | DA+6 | 1 | 2 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 395.488 | 400 |  | 14400 | 400 | [8 empty] | 42
147 | 22/11 | DA+6 | 0 | 2 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 408.032 | 410 |  | 14760 | 410 | [8 empty] | 42
148 | 22/12 | DA+3 | 1 | 2 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 318.002 | 320 |  | 11520 | 320 | [8 empty] | 36
149 | 22/13 | DA+6 | 0 | 0 | 1 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 447.32 | 450 |  | 16200 | 450 | [8 empty] | 48
150 | 23/0 | DD45+3 | 2 | 2 | 2 | 2 | 34° 59' 23.64" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 222.155 | 225 |  | 8100 | 225 | [8 empty] | 24
151 | 24/0 | DD45+3 | 2 | 2 | 2 | 2 | 32° 40' 24.96" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 433.889 | 435 |  | 15660 | 435 | [8 empty] | 42
152 | 25/0 | DC1+6 |  |  |  |  | 15° 53' 08.16" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 422.332 | 425 |  | 15300 | 425 | [8 empty] | 42
153 | 25/1 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 370.741 | 375 |  | 13500 | 375 | [8 empty] | 36
154 | 25/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 345.675 | 350 |  | 12600 | 350 | [8 empty] | 36
155 | 25/3 | DA+0 | 1 | 2 | 0 | 2 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 391.123 | 395 |  | 14220 | 395 | [8 empty] | 42
156 | 25/4 | DA+0 | 1 | 1 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 440.407 | 445 |  | 16020 | 445 | [8 empty] | 42
157 | 26/0 | DB1+0 |  |  |  |  | 00° 51' 11.52" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 391.364 | 395 |  | 14220 | 395 | [8 empty] | 42
158 | 26/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 406.47 | 410 |  | 14760 | 410 | [8 empty] | 42
159 | 26/2 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 418.022 | 420 |  | 15120 | 420 | [8 empty] | 42
160 | 26/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 422.596 | 425 |  | 15300 | 425 | [8 empty] | 42
161 | 26/4 | DA+6 | 1 | 0 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 409.977 | 410 |  | 14760 | 410 | [8 empty] | 42
162 | 26/5 | DA+6 | 1 | 1 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 363.382 | 365 |  | 13140 | 365 | [8 empty] | 36
163 | 26/6 | DA+6 | 0 | 1 | 1 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 421.855 | 425 |  | 15300 | 425 | [8 empty] | 42
164 | 26/7 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 416.722 | 420 |  | 15120 | 420 | [8 empty] | 42
165 | 26/8 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 413.786 | 415 |  | 14940 | 415 | [8 empty] | 42
166 | 27/0 | DC1+0 |  |  |  |  | 19° 33' 38.16" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 399.755 | 400 |  | 14400 | 400 | [8 empty] | 42
167 | 27/1 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 425.179 | 430 |  | 15480 | 430 | [8 empty] | 42
168 | 27/2 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 398.561 | 400 |  | 14400 | 400 | [8 empty] | 42
169 | 27/3 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 430.665 | 435 |  | 15660 | 435 | [8 empty] | 42
170 | 27/4 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 410.013 | 415 |  | 14940 | 415 | [8 empty] | 42
171 | 27/5 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 402.548 | 405 |  | 14580 | 405 | [8 empty] | 42
172 | 27/6 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 343.499 | 345 |  | 12420 | 345 | [8 empty] | 36
173 | 27/7 | DB1+0 |  |  |  |  | 00° 00' 00" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 392.004 | 395 |  | 14220 | 395 | [8 empty] | 42
174 | 27/8 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 381.088 | 385 |  | 13860 | 385 | [8 empty] | 42
175 | 27/9 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 366.278 | 370 |  | 13320 | 370 | [8 empty] | 36
176 | 27/10 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 420.087 | 425 |  | 15300 | 425 | [8 empty] | 42
177 | 27/11 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 420.787 | 425 |  | 15300 | 425 | [8 empty] | 42
178 | 27/12 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 406.635 | 410 |  | 14760 | 410 | [8 empty] | 42
179 | 28/0 | DB2+0 |  |  |  |  | 12° 53' 28.32" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 379.637 | 380 |  | 13680 | 380 | [8 empty] | 42
180 | 28/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 385 | 385 |  | 13860 | 385 | [8 empty] | 42
181 | 28/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 369 | 370 |  | 13320 | 370 | [8 empty] | 36
182 | 28/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 409 | 410 |  | 14760 | 410 | [8 empty] | 42
183 | 28/4 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 422 | 425 |  | 15300 | 425 | [8 empty] | 42
184 | 28/5 | DA+9 | 0 | 2 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 370 | 370 |  | 13320 | 370 | [8 empty] | 36
185 | 28/6 | DA+6 | 1 | 4 | 3 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 464 | 465 |  | 16740 | 465 | [8 empty] | 48
186 | 28/7 | DA+3 | 1 | 3 | 2 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 375 | 375 |  | 13500 | 375 | [8 empty] | 42
187 | 28/8 | DA+3 | 0 | 0 | 5 | 3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 465.455 | 470 |  | 16920 | 470 | [8 empty] | 48
188 | 29/0 | DB1+0 |  |  |  |  | 06° 14' 21.84" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 365.545 | 370 |  | 13320 | 370 | [8 empty] | 36
189 | 29/1 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 424 | 425 |  | 15300 | 425 | [8 empty] | 42
190 | 29/2 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 399 | 400 |  | 14400 | 400 | [8 empty] | 42
191 | 29/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 440 | 440 |  | 15840 | 440 | [8 empty] | 42
192 | 29/4 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 382.099 | 385 |  | 13860 | 385 | [8 empty] | 42
193 | 30/0 | DC1+0 |  |  |  |  | 16° 15' 6.12" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 388.901 | 390 |  | 14040 | 390 | [8 empty] | 42
194 | 30/1 | DA+0 | 2 | 0 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 445 | 445 |  | 16020 | 445 | [8 empty] | 48
195 | 30/2 | DA+0 | 1 | 2 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 395 | 395 |  | 14220 | 395 | [8 empty] | 42
196 | 30/3 | DA+3 | 1 | 2 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 377 | 380 |  | 13680 | 380 | [8 empty] | 42
197 | 30/4 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 444 | 445 |  | 16020 | 445 | [8 empty] | 48
198 | 30/5 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 322 | 325 |  | 11700 | 325 | [8 empty] | 36
199 | 30/6 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 347.434 | 350 |  | 12600 | 350 | [8 empty] | 36
200 | 31/0 | DB2+0 |  |  |  |  | 14° 44' 46.32" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 383.566 | 385 |  | 13860 | 385 | [8 empty] | 42
201 | 31/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 366 | 370 |  | 13320 | 370 | [8 empty] | 36
202 | 31/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 332.909 | 335 |  | 12060 | 335 | [8 empty] | 36
203 | 32/0 | DC1+0 |  |  |  |  | 21° 35' 19.68" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 402.684 | 405 |  | 14580 | 405 | [8 empty] | 42
204 | 32/1 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 428.809 | 430 |  | 15480 | 430 | [8 empty] | 42
205 | 32/2 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 410.89 | 415 |  | 14940 | 415 | [8 empty] | 42
206 | 32/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 381.106 | 385 |  | 13860 | 385 | [8 empty] | 42
207 | 32/4 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 451.501 | 455 |  | 16380 | 455 | [8 empty] | 48
208 | 33/0 | DC1+0 | 1 | 0 | 0 | 0 | 20° 0' 49.32" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 379.558 | 380 |  | 13680 | 380 | [8 empty] | 42
209 | 33/1 | DA+0 | 0 | 1 | 1 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 292.533 | 295 |  | 10620 | 295 | [8 empty] | 30
210 | 34/0 | DB2+0 |  |  |  |  | 9° 34' 3.36" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 432.636 | 435 |  | 15660 | 435 | [8 empty] | 42
211 | 34/1 | DA+9 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 407.467 | 410 |  | 14760 | 410 | [8 empty] | 42
212 | 34/2 | DA+6 | 0 | 0 | 0 | 2 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 377.043 | 380 |  | 13680 | 380 | [8 empty] | 42
213 | 34/3 | DA+0 | 0 | 3 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 451.576 | 455 |  | 16380 | 455 | [8 empty] | 48
214 | 34/4 | DA+0 | 0 | 3 | 1 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 379.275 | 380 |  | 13680 | 380 | [8 empty] | 42
215 | 35/0 | DB2+6 | 2 | 0 | 0 | 0 | 13° 13' 27.12" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 265.554 | 270 |  | 9720 | 270 | [8 empty] | 30
216 | 35/1 | DA+9 | 2 | 0 | 0 | 2 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 492.404 | 495 |  | 17820 | 495 | [8 empty] | 54
217 | 35/2 | DB1+0 | 1 | 1 | 0 | 0 | [6 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 522.221 | 525 |  | 18900 | 525 | [8 empty] | 54
218 | 35/3 | DB1+6 | 1 | 0 | 0 | 0 | [6 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 418.925 | 420 |  | 15120 | 420 | [8 empty] | 42
219 | 35/4 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 421.684 | 425 |  | 15300 | 425 | [8 empty] | 42
220 | 35/5 | DA+0 | 0 | 0 | 4 | 4 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 342.697 | 345 |  | 12420 | 345 | [8 empty] | 36
221 | 36/0 | DB2+0 |  |  |  |  | 14° 55' 10.2" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 386.433 | 390 |  | 14040 | 390 | [8 empty] | 42
222 | 36/1 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 309.428 | 310 |  | 11160 | 310 | [8 empty] | 30
223 | 36/2 | DA+0 | 1 | 1 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 357.809 | 360 |  | 12960 | 360 | [8 empty] | 36
224 | 36/3 | DA+0 | 0 | 2 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 480.439 | 485 |  | 17460 | 485 | [8 empty] | 48
225 | 36/4 | DA+6 | 2 | 3 | 0 | 5 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 350.468 | 355 |  | 12780 | 355 | [8 empty] | 36
226 | 37/0 | DB2+0 | 0 | 0 | 0 | 1 | 14° 56' 10.32" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 443.286 | 445 |  | 16020 | 445 | [8 empty] | 48
227 | 37/1 | DA+9 | 2 | 2 | 2 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 356.665 | 360 |  | 12960 | 360 | [8 empty] | 36
228 | 37/2 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 339.878 | 340 |  | 12240 | 340 | [8 empty] | 36
229 | 37/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 500.279 | 505 |  | 18180 | 505 | [8 empty] | 54
230 | 38/0 | DB2+6 |  |  |  |  | 9° 11' 45.24" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 421.442 | 425 |  | 15300 | 425 | [8 empty] | 42
231 | 38/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 419.024 | 420 |  | 15120 | 420 | [8 empty] | 42
232 | 38/2 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 420.329 | 425 |  | 15300 | 425 | [8 empty] | 42
233 | 38/3 | DA+9 | 2 | 2 | 2 | 2 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 414.895 | 415 |  | 14940 | 415 | [8 empty] | 42
234 | 38/4 | DA+9 | 1 | 1 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 425.489 | 430 |  | 15480 | 430 | [8 empty] | 42
235 | 39/0 | DB2+6 |  |  |  |  | 14° 1' 20.28" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 412.639 | 415 |  | 14940 | 415 | [8 empty] | 42
236 | 39/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 322.554 | 325 |  | 11700 | 325 | [8 empty] | 36
237 | 40/0 | DC2+0 | 1 | 1 | 0 | 0 | 21° 42' 13.68" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 396.201 | 400 |  | 14400 | 400 | [8 empty] | 42
238 | 40/1 | DA+6 | 1 | 2 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 425.809 | 430 |  | 15480 | 430 | [8 empty] | 42
239 | 40/2 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 401.688 | 405 |  | 14580 | 405 | [8 empty] | 42
240 | 40/3 | DA+3 | 1 | 2 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 436.302 | 440 |  | 15840 | 440 | [8 empty] | 42
241 | 41/0 | DC1+6 | 3 | 1 | 0 | 1 | 16° 54' 46" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 340.766 | 345 |  | 12420 | 345 | [8 empty] | 36
242 | 41/1 | DB1+9 | 4 | 5 | 6 | 6 | [6 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 447.822 | 450 |  | 16200 | 450 | [8 empty] | 48
243 | 41/2 | DA+0 | 0 | 0 | 1 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 382.33 | 385 |  | 13860 | 385 | [8 empty] | 42
244 | 42/0 | DC1+0 | 1 | 0 | 0 | 2 | 17° 31' 50" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 384.711 | 385 |  | 13860 | 385 | [8 empty] | 42
245 | 42/1 | DA+6 | 1 | 0 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 407.363 | 410 |  | 14760 | 410 | [8 empty] | 42
246 | 42/2 | DA+6 | 0 | 0 | 1 | 3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 414.174 | 415 |  | 14940 | 415 | [8 empty] | 42
247 | 42/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 256.36 | 260 |  | 9360 | 260 | [8 empty] | 30
248 | 42/4 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 403.84 | 405 |  | 14580 | 405 | [8 empty] | 42
249 | 42/5 | DA+9 | 0 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 396.724 | 400 |  | 14400 | 400 | [8 empty] | 42
250 | 42/6 | DA+0 | 2 | 1 | 0 | 2 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 403.932 | 405 |  | 14580 | 405 | [8 empty] | 42
251 | 43/0 | DB1+0 |  |  |  |  | 01° 56' 25" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 345.988 | 350 |  | 12600 | 350 | [8 empty] | 36
252 | 43/1 | DA+3 | 0 | 0 | 3 | 3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 475.789 | 480 |  | 17280 | 480 | [8 empty] | 48
253 | 43/2 | DA+0 | 1 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 363.648 | 365 |  | 13140 | 365 | [8 empty] | 36
254 | 43/3 | DA+0 | 0 | 1 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 431.843 | 435 |  | 15660 | 435 | [8 empty] | 42
255 | 43/4 | DA+3 | 1 | 1 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 405.305 | 410 |  | 14760 | 410 | [8 empty] | 42
256 | 43/5 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 427.816 | 430 |  | 15480 | 430 | [8 empty] | 42
257 | 43/6 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 389.757 | 390 |  | 14040 | 390 | [8 empty] | 42
258 | 43/7 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 449.543 | 450 |  | 16200 | 450 | [8 empty] | 48
259 | 43/8 | DA+9 | 1 | 0 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 387.977 | 390 |  | 14040 | 390 | [8 empty] | 42
260 | 43/9 | DA+9 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 346.332 | 350 |  | 12600 | 350 | [8 empty] | 36
261 | 43/10 | DA+3 | 3 | 3 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 444.843 | 445 |  | 16020 | 445 | [8 empty] | 48
262 | 43/11 | DA+3 | 2 | 3 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 383.925 | 385 |  | 13860 | 385 | [8 empty] | 42
263 | 44/0 | DB1+3 | 0 | 1 | 1 | 0 | 6° 14' 24.0" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 384.293 | 385 |  | 13860 | 385 | [8 empty] | 42
264 | 44/1 | DA+0 | 0 | 0 | 1 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 359 | 360 |  | 12960 | 360 | [8 empty] | 36
265 | 44/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 333.999 | 335 |  | 12060 | 335 | [8 empty] | 36
266 | 44/3 | DA+0 | 2 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 395 | 395 |  | 14220 | 395 | [8 empty] | 42
267 | 44/4 | DA+9 | 4 | 3 | 3 | 3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 355.001 | 360 |  | 12960 | 360 | [8 empty] | 36
268 | 44/5 | DA+9 | 1 | 3 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 484.999 | 485 |  | 17460 | 485 | [8 empty] | 48
269 | 44/6 | DB1+3 | 1 | 0 | 0 | 1 | 0° 0' 0" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 473.001 | 475 |  | 17100 | 475 | [8 empty] | 48
270 | 44/7 | DA+9 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 367 | 370 |  | 13320 | 370 | [8 empty] | 36
271 | 44/8 | DCT1+0 | 1 | 2 | 0 | 1 | 0° 0' 0" | [5 empty] | 56 | 8 | 12 |  | 8 | 4 |  |  |  | 30 | 72 | 2 |  | 2 |  |  | 4
[8 empty] | 430 | 430 |  | 15480 | 430 | [8 empty] | 42
272 | 44/9 | DA+9 | 4 | 0 | 2 | 6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 365 | 365 |  | 13140 | 365 | [8 empty] | 36
273 | 44/10 | DB1+9 | 0 | 1 | 0 | 0 | 0° 0' 0" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 428 | 430 |  | 15480 | 430 | [8 empty] | 42
274 | 44/11 | DA+0 | 0 | 1 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 327.231 | 330 |  | 11880 | 330 | [8 empty] | 36
275 | 45/0 | DC2+0 | 0 | 1 | 0 | 0 | 24° 55' 38.28" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 294.921 | 295 |  | 10620 | 295 | [8 empty] | 30
276 | 45/1 | DA+9 | 0 | 0 | 6 | 6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 406.542 | 410 |  | 14760 | 410 | [8 empty] | 42
277 | 46/0 | DD60+25 | 0 | 6 | 6 | 2 | 28° 47' 23" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 199.082 | 200 |  | 7200 | 200 | [8 empty] | 18
278 | 47/0 | DD60+25 | 5 | 5 | 5 | 5 | 47° 00' 03" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 441.182 | 445 |  | 16020 | 445 | [8 empty] | 48
279 | 47/1 | DA+3 | 2 | 0 | 2 | 5 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 365.945 | 370 |  | 13320 | 370 | [8 empty] | 36
280 | 47/2 | DA+9 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 417.366 | 420 |  | 15120 | 420 | [8 empty] | 42
281 | 47/3 | DA+9 | 1 | 2 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 358.36 | 360 |  | 12960 | 360 | [8 empty] | 36
282 | 47/4 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 461.195 | 465 |  | 16740 | 465 | [8 empty] | 48
283 | 47/5 | DA+0 | 0 | 1 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 377.282 | 380 |  | 13680 | 380 | [8 empty] | 42
284 | 47/6 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 431.516 | 435 |  | 15660 | 435 | [8 empty] | 42
285 | 47/7 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 398.835 | 400 |  | 14400 | 400 | [8 empty] | 42
286 | 47/8 | DA+0 | 1 | 0 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 405.865 | 410 |  | 14760 | 410 | [8 empty] | 42
287 | 47/9 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 433.704 | 435 |  | 15660 | 435 | [8 empty] | 42
288 | 47/10 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 386.154 | 390 |  | 14040 | 390 | [8 empty] | 42
289 | 48/0 | DC2+0 |  |  |  |  | 29°14'33.0" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 428.901 | 430 |  | 15480 | 430 | [8 empty] | 42
290 | 48/1 | DA+9 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 402.922 | 405 |  | 14580 | 405 | [8 empty] | 42
291 | 49/0 | DD45+0 |  |  |  |  | 33° 51' 14.4" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 379.1 | 380 |  | 13680 | 380 | [8 empty] | 42
292 | 49/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 386.636 | 390 |  | 14040 | 390 | [8 empty] | 42
293 | 49/2 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 390.002 | 395 |  | 14220 | 395 | [8 empty] | 42
294 | 49/3 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 421.729 | 425 |  | 15300 | 425 | [8 empty] | 42
295 | 49/4 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 396.643 | 400 |  | 14400 | 400 | [8 empty] | 42
296 | 49/5 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 412.789 | 415 |  | 14940 | 415 | [8 empty] | 42
297 | 49/6 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 340.206 | 345 |  | 12420 | 345 | [8 empty] | 36
298 | 49/7 | DA+0 | 0 | 3 | 2 | 2 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 500.231 | 505 |  | 18180 | 505 | [8 empty] | 54
299 | 50/0 | DB2+0 | 0 | 0 | 0 | 1 | 8° 23' 20.04" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 469.069 | 470 |  | 16920 | 470 | [8 empty] | 48
300 | 50/1 | DA+6 | 1 | 0 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 367.133 | 370 |  | 13320 | 370 | [8 empty] | 36
301 | 50/2 | DA+9 | 2 | 2 | 2 | 2 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 470.387 | 475 |  | 17100 | 475 | [8 empty] | 48
302 | 50/3 | DA+6 | 0 | 0 | 1 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 354.811 | 355 |  | 12780 | 355 | [8 empty] | 36
303 | 50/4 | DA+9 | 3 | 3 | 4 | 3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 442.053 | 445 |  | 16020 | 445 | [8 empty] | 48
304 | 50/5 | DA+9 | 4 | 3 | 4 | 3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 364.426 | 365 |  | 13140 | 365 | [8 empty] | 36
305 | 50/6 | DA+9 | 3 | 4 | 3 | 3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 470.777 | 475 |  | 17100 | 475 | [8 empty] | 48
306 | 50/7 | DA+0 | 0 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 345.004 | 350 |  | 12600 | 350 | [8 empty] | 36
307 | 50/8 | DA+9 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 364.406 | 365 |  | 13140 | 365 | [8 empty] | 36
308 | 50/9 | DA+0 | 0 | 0 | 1 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 394.591 | 395 |  | 14220 | 395 | [8 empty] | 42
309 | 50/10 | DA+0 | 0 | 0 | 1 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 401.397 | 405 |  | 14580 | 405 | [8 empty] | 42
310 | 51/0 | DC2+0 |  |  |  |  | 25° 51' 48.24" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 356.579 | 360 |  | 12960 | 360 | [8 empty] | 36
311 | 51/1 | DA+0 | 0 | 0 | 1 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 307.101 | 310 |  | 11160 | 310 | [8 empty] | 30
312 | 51/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 384.965 | 385 |  | 13860 | 385 | [8 empty] | 42
313 | 52/0 | DC2+0 | 0 | 0 | 3 | 3 | 22° 21' 21.96" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 402.021 | 405 |  | 14580 | 405 | [8 empty] | 42
314 | 52/1 | DA+6 | 0 | 4 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 402.64 | 405 |  | 14580 | 405 | [8 empty] | 42
315 | 52/2 | DA+6 | 0 | 0 | 0 | 3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 436.956 | 440 |  | 15840 | 440 | [8 empty] | 42
316 | 52/3 | DA+9 | 4 | 3 | 3 | 3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 393.809 | 395 |  | 14220 | 395 | [8 empty] | 42
317 | 52/4 | DA+9 | 2 | 2 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 447.029 | 450 |  | 16200 | 450 | [8 empty] | 48
318 | 52/5 | DA+9 | 0 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 373.001 | 375 |  | 13500 | 375 | [8 empty] | 42
319 | 52/6 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 406.819 | 410 |  | 14760 | 410 | [8 empty] | 42
320 | 52/7 | DA+3 | 0 | 3 | 1 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 433.034 | 435 |  | 15660 | 435 | [8 empty] | 42
321 | 52/8 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 399.703 | 400 |  | 14400 | 400 | [8 empty] | 42
322 | 52/9 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 384.142 | 385 |  | 13860 | 385 | [8 empty] | 42
323 | 52/10 | DA+9 | 1 | 2 | 1 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 455.857 | 460 |  | 16560 | 460 | [8 empty] | 48
324 | 53/0 | DB2+9 | 4 | 4 | 4 | 4 | 6° 57' 38.88" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 433.242 | 435 |  | 15660 | 435 | [8 empty] | 42
325 | 53/1 | DA+9 | 4 | 4 | 4 | 4 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 407.406 | 410 |  | 14760 | 410 | [8 empty] | 42
326 | 53/2 | DA+0 | 0 | 0 | 0 | 2 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 394.498 | 395 |  | 14220 | 395 | [8 empty] | 42
327 | 53/3 | DA+6 | 0 | 4 | 1 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 410.082 | 415 |  | 14940 | 415 | [8 empty] | 42
328 | 53/4 | DA+0 | 0 | 2 | 1 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 428.073 | 430 |  | 15480 | 430 | [8 empty] | 42
329 | 53/5 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 406.604 | 410 |  | 14760 | 410 | [8 empty] | 42
330 | 53/6 | DA+6 | 1 | 1 | 3 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 411.298 | 415 |  | 14940 | 415 | [8 empty] | 42
331 | 53/7 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 427.748 | 430 |  | 15480 | 430 | [8 empty] | 42
332 | 53/8 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 371.307 | 375 |  | 13500 | 375 | [8 empty] | 42
333 | 54/0 | DB1+6 |  |  |  |  | 6° 44' 37.68" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 365.051 | 370 |  | 13320 | 370 | [8 empty] | 36
334 | 54/1 | DA+3 | 1 | 1 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 380.985 | 385 |  | 13860 | 385 | [8 empty] | 42
335 | 54/2 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 417.041 | 420 |  | 15120 | 420 | [8 empty] | 42
336 | 54/3 | DA+6 | 0 | 2 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 423.34 | 425 |  | 15300 | 425 | [8 empty] | 42
337 | 54/4 | DA+9 | 1 | 2 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 400.981 | 405 |  | 14580 | 405 | [8 empty] | 42
338 | 54/5 | DA+9 | 1 | 3 | 3 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 424.016 | 425 |  | 15300 | 425 | [8 empty] | 42
339 | 55/0 | DB1+6 | 0 | 1 | 1 | 0 | 2° 29' 53.88" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 404.939 | 405 |  | 14580 | 405 | [8 empty] | 42
340 | 55/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 343.124 | 345 |  | 12420 | 345 | [8 empty] | 36
341 | 55/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 357.687 | 360 |  | 12960 | 360 | [8 empty] | 36
342 | 55/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 365.158 | 370 |  | 13320 | 370 | [8 empty] | 36
343 | 55/4 | DA+0 | 0 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 350.096 | 355 |  | 12780 | 355 | [8 empty] | 36
344 | 55/5 | DA+0 | 0 | 0 | 1 | 3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 357.682 | 360 |  | 12960 | 360 | [8 empty] | 36
345 | 55/6 | DA+0 | 0 | 0 | 1 | 2 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 337.791 | 340 |  | 12240 | 340 | [8 empty] | 36
346 | 55/7 | DA+0 | 0 | 0 | 1 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 341.218 | 345 |  | 12420 | 345 | [8 empty] | 36
347 | 55/8 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 460.489 | 465 |  | 16740 | 465 | [8 empty] | 48
348 | 56/0 | DD60+25 | 3 | 3 | 0 | 2 | 5° 23' 07" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 219.763 | 220 |  | 7920 | 220 | [8 empty] | 24
349 | 57/0 | DD60+25 | 0 | 1 | 1 | 0 | 0° 16' 10" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 461.115 | 465 |  | 16740 | 465 | [8 empty] | 48
350 | 57/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 355.491 | 360 |  | 12960 | 360 | [8 empty] | 36
351 | 57/2 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 405.387 | 410 |  | 14760 | 410 | [8 empty] | 42
352 | 57/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 418.151 | 420 |  | 15120 | 420 | [8 empty] | 42
353 | 57/4 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 416.747 | 420 |  | 15120 | 420 | [8 empty] | 42
354 | 57/5 | DA+3 | 0 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 394.972 | 395 |  | 14220 | 395 | [8 empty] | 42
355 | 57/6 | DA+3 | 0 | 1 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 401.782 | 405 |  | 14580 | 405 | [8 empty] | 42
356 | 57/7 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 433.932 | 435 |  | 15660 | 435 | [8 empty] | 42
357 | 58/0 | DC1+3 |  |  |  |  | 19° 22' 13.08" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 238.897 | 240 |  | 8640 | 240 | [8 empty] | 24
358 | 59/0 | DC2+0 |  |  |  |  | 27° 51' 8.64" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 411.335 | 415 |  | 14940 | 415 | [8 empty] | 42
359 | 59/1 | DA+3 | 0 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 418.204 | 420 |  | 15120 | 420 | [8 empty] | 42
360 | 59/2 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 412.314 | 415 |  | 14940 | 415 | [8 empty] | 42
361 | 59/3 | DA+3 | 0 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 420.969 | 425 |  | 15300 | 425 | [8 empty] | 42
362 | 59/4 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 419.66 | 420 |  | 15120 | 420 | [8 empty] | 42
363 | 59/5 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 419.111 | 420 |  | 15120 | 420 | [8 empty] | 42
364 | 59/6 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 408.809 | 410 |  | 14760 | 410 | [8 empty] | 42
365 | 59/7 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 426.933 | 430 |  | 15480 | 430 | [8 empty] | 42
366 | 59/8 | DB1+3 |  |  |  |  | 0° 0' 0" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 434.725 | 435 |  | 15660 | 435 | [8 empty] | 42
367 | 59/9 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 400.826 | 405 |  | 14580 | 405 | [8 empty] | 42
368 | 59/10 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 436.297 | 440 |  | 15840 | 440 | [8 empty] | 42
369 | 59/11 | DA+6 | 0 | 0 | 2 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 393.114 | 395 |  | 14220 | 395 | [8 empty] | 42
370 | 59/12 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 447.361 | 450 |  | 16200 | 450 | [8 empty] | 48
371 | 59/13 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 391.112 | 395 |  | 14220 | 395 | [8 empty] | 42
372 | 59/14 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 448.593 | 450 |  | 16200 | 450 | [8 empty] | 48
373 | 59/15 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 388 | 390 |  | 14040 | 390 | [8 empty] | 42
374 | 59/16 | DA+9 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 437.955 | 440 |  | 15840 | 440 | [8 empty] | 42
375 | 60/0 | DC1+0 |  |  |  |  | 20° 22' 38.64" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 413.81 | 415 |  | 14940 | 415 | [8 empty] | 42
376 | 60/1 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 424.2 | 425 |  | 15300 | 425 | [8 empty] | 42
377 | 60/2 | DA+3 | 2 | 2 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 414.521 | 415 |  | 14940 | 415 | [8 empty] | 42
378 | 60/3 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 425.581 | 430 |  | 15480 | 430 | [8 empty] | 42
379 | 60/4 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 412.27 | 415 |  | 14940 | 415 | [8 empty] | 42
380 | 60/5 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 374.127 | 375 |  | 13500 | 375 | [8 empty] | 42
381 | 60/6 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 410.05 | 415 |  | 14940 | 415 | [8 empty] | 42
382 | 60/7 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 400.355 | 405 |  | 14580 | 405 | [8 empty] | 42
383 | 60/8 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 409.166 | 410 |  | 14760 | 410 | [8 empty] | 42
384 | 60/9 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 400.967 | 405 |  | 14580 | 405 | [8 empty] | 42
385 | 60/10 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 394.536 | 395 |  | 14220 | 395 | [8 empty] | 42
386 | 60/11 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 397.858 | 400 |  | 14400 | 400 | [8 empty] | 42
387 | 61/0 | DB2+0 |  |  |  |  | 13° 28' 15.24" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 405.656 | 410 |  | 14760 | 410 | [8 empty] | 42
388 | 61/1 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 433.158 | 435 |  | 15660 | 435 | [8 empty] | 42
389 | 61/2 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 400.923 | 405 |  | 14580 | 405 | [8 empty] | 42
390 | 61/3 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 427.004 | 430 |  | 15480 | 430 | [8 empty] | 42
391 | 61/4 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 413.927 | 415 |  | 14940 | 415 | [8 empty] | 42
392 | 61/5 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 426.392 | 430 |  | 15480 | 430 | [8 empty] | 42
393 | 61/6 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 411.448 | 415 |  | 14940 | 415 | [8 empty] | 42
394 | 61/7 | DA+9 | 0 | 0 | 0 | 1 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 376.246 | 380 |  | 13680 | 380 | [8 empty] | 42
395 | 61/8 | DA+6 | 1 | 2 | 1 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 433.371 | 435 |  | 15660 | 435 | [8 empty] | 42
396 | 61/9 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 405.615 | 410 |  | 14760 | 410 | [8 empty] | 42
397 | 61/10 | DA+9 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 434.245 | 435 |  | 15660 | 435 | [8 empty] | 42
398 | 62/0 | DB2+0 |  |  |  |  | 7° 27' 29.88" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 418.001 | 420 |  | 15120 | 420 | [8 empty] | 42
399 | 62/1 | DA+3 | 0 | 0 | 1 | 2 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 386.002 | 390 |  | 14040 | 390 | [8 empty] | 42
400 | 62/2 | DA+3 | 0 | 1 | 0 | 0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 399.999 | 400 |  | 14400 | 400 | [8 empty] | 42
401 | 62/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 400.999 | 405 |  | 14580 | 405 | [8 empty] | 42
402 | 62/4 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 403 | 405 |  | 14580 | 405 | [8 empty] | 42
403 | 62/5 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 404.001 | 405 |  | 14580 | 405 | [8 empty] | 42
404 | 62/6 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 423 | 425 |  | 15300 | 425 | [8 empty] | 42
405 | 62/7 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 408.999 | 410 |  | 14760 | 410 | [8 empty] | 42
406 | 62/8 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 409 | 410 |  | 14760 | 410 | [8 empty] | 42
407 | 62/9 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 411.001 | 415 |  | 14940 | 415 | [8 empty] | 42
408 | 62/10 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 412.998 | 415 |  | 14940 | 415 | [8 empty] | 42
409 | 62/11 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 386.106 | 390 |  | 14040 | 390 | [8 empty] | 42
410 | 63/0 | DC1+0 |  |  |  |  | 18° 26' 28.68" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 400 | 400 |  | 14400 | 400 | [8 empty] | 42
411 | 63/1 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 416.001 | 420 |  | 15120 | 420 | [8 empty] | 42
412 | 63/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 410.999 | 415 |  | 14940 | 415 | [8 empty] | 42
413 | 63/3 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 398.999 | 400 |  | 14400 | 400 | [8 empty] | 42
414 | 63/4 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 413.002 | 415 |  | 14940 | 415 | [8 empty] | 42
415 | 63/5 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 426 | 430 |  | 15480 | 430 | [8 empty] | 42
416 | 63/6 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 412.998 | 415 |  | 14940 | 415 | [8 empty] | 42
417 | 63/7 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 425.001 | 430 |  | 15480 | 430 | [8 empty] | 42
418 | 63/8 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 408.342 | 410 |  | 14760 | 410 | [8 empty] | 42
419 | 64/0 | DB2+0 |  |  |  |  | 13° 49' 10.2" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 375.075 | 380 |  | 13680 | 380 | [8 empty] | 42
420 | 64/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 408.721 | 410 |  | 14760 | 410 | [8 empty] | 42
421 | 64/2 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 410.741 | 415 |  | 14940 | 415 | [8 empty] | 42
422 | 64/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 408.233 | 410 |  | 14760 | 410 | [8 empty] | 42
423 | 64/4 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 426.149 | 430 |  | 15480 | 430 | [8 empty] | 42
424 | 64/5 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 407.715 | 410 |  | 14760 | 410 | [8 empty] | 42
425 | 64/6 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 401.624 | 405 |  | 14580 | 405 | [8 empty] | 42
426 | 64/7 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 425.512 | 430 |  | 15480 | 430 | [8 empty] | 42
427 | 64/8 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 414.346 | 415 |  | 14940 | 415 | [8 empty] | 42
428 | 64/9 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 410.63 | 415 |  | 14940 | 415 | [8 empty] | 42
429 | 64/10 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 428.424 | 430 |  | 15480 | 430 | [8 empty] | 42
430 | 64/11 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 400.562 | 405 |  | 14580 | 405 | [8 empty] | 42
431 | 65/0 | DB1+0 |  |  |  |  | 2° 32' 0.6" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 395.375 | 400 |  | 14400 | 400 | [8 empty] | 42
432 | 65/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 393.737 | 395 |  | 14220 | 395 | [8 empty] | 42
433 | 65/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 403.694 | 405 |  | 14580 | 405 | [8 empty] | 42
434 | 65/3 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 402.93 | 405 |  | 14580 | 405 | [8 empty] | 42
435 | 65/4 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 376.376 | 380 |  | 13680 | 380 | [8 empty] | 42
436 | 65/5 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 389.191 | 390 |  | 14040 | 390 | [8 empty] | 42
437 | 65/6 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 397.579 | 400 |  | 14400 | 400 | [8 empty] | 42
438 | 65/7 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 394.265 | 395 |  | 14220 | 395 | [8 empty] | 42
439 | 65/8 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 388.953 | 390 |  | 14040 | 390 | [8 empty] | 42
440 | 65/9 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 379.103 | 380 |  | 13680 | 380 | [8 empty] | 42
441 | 65/10 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 387.628 | 390 |  | 14040 | 390 | [8 empty] | 42
442 | 65/11 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 426.927 | 430 |  | 15480 | 430 | [8 empty] | 42
443 | 66/0 | DC2+6 |  |  |  |  | 22° 23' 34.44" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 207.839 | 210 |  | 7560 | 210 | [8 empty] | 24
444 | 67/0 | DC1+9 |  |  |  |  | 17° 55' 44.04" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 347.141 | 350 |  | 12600 | 350 | [8 empty] | 36
445 | 67/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 344.931 | 345 |  | 12420 | 345 | [8 empty] | 36
446 | 67/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 369.226 | 370 |  | 13320 | 370 | [8 empty] | 36
447 | 68/0 | DD45+0 |  |  |  |  | 42° 20' 12.84" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 200.889 | 205 |  | 7380 | 205 | [8 empty] | 18
448 | 69/0 | DB2+0 |  |  |  |  | 12° 32' 12.12" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 374.132 | 375 |  | 13500 | 375 | [8 empty] | 42
449 | 69/1 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 394.886 | 395 |  | 14220 | 395 | [8 empty] | 42
450 | 70/0 | DC1+0 |  |  |  |  | 19° 34' 30.72" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 388.385 | 390 |  | 14040 | 390 | [8 empty] | 42
451 | 70/1 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 418.865 | 420 |  | 15120 | 420 | [8 empty] | 42
452 | 70/2 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 418.601 | 420 |  | 15120 | 420 | [8 empty] | 42
453 | 70/3 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 413.987 | 415 |  | 14940 | 415 | [8 empty] | 42
454 | 70/4 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 419.583 | 420 |  | 15120 | 420 | [8 empty] | 42
455 | 70/5 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 420.331 | 425 |  | 15300 | 425 | [8 empty] | 42
456 | 70/6 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 419.632 | 420 |  | 15120 | 420 | [8 empty] | 42
457 | 70/7 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 418.147 | 420 |  | 15120 | 420 | [8 empty] | 42
458 | 70/8 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 414.142 | 415 |  | 14940 | 415 | [8 empty] | 42
459 | 70/9 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 406.073 | 410 |  | 14760 | 410 | [8 empty] | 42
460 | 70/10 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 408.566 | 410 |  | 14760 | 410 | [8 empty] | 42
461 | 70/11 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 420.444 | 425 |  | 15300 | 425 | [8 empty] | 42
462 | 71/0 | DB2+3 |  |  |  |  | 9° 37' 5.52" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 398.637 | 400 |  | 14400 | 400 | [8 empty] | 42
463 | 71/1 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 414.33 | 415 |  | 14940 | 415 | [8 empty] | 42
464 | 71/2 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 413.012 | 415 |  | 14940 | 415 | [8 empty] | 42
465 | 71/3 | DA+6 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 367.658 | 370 |  | 13320 | 370 | [8 empty] | 36
466 | 71/4 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 429.409 | 430 |  | 15480 | 430 | [8 empty] | 42
467 | 71/5 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 408.031 | 410 |  | 14760 | 410 | [8 empty] | 42
468 | 71/6 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 404.849 | 405 |  | 14580 | 405 | [8 empty] | 42
469 | 71/7 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 431.601 | 435 |  | 15660 | 435 | [8 empty] | 42
470 | 71/8 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 408.371 | 410 |  | 14760 | 410 | [8 empty] | 42
471 | 72/0 | DB2+3 |  |  |  |  | 10° 39' 52.92" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 435.269 | 440 |  | 15840 | 440 | [8 empty] | 42
472 | 72/1 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 403.852 | 405 |  | 14580 | 405 | [8 empty] | 42
473 | 72/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 389.167 | 390 |  | 14040 | 390 | [8 empty] | 42
474 | 72/3 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 400.085 | 405 |  | 14580 | 405 | [8 empty] | 42
475 | 73/0 | DB2+0 |  |  |  |  | 13° 10' 26.4" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
[8 empty] | 383.337 | 385 |  | 13860 | 385 | [8 empty] | 42
476 | 73/1 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 378.99 | 380 |  | 13680 | 380 | [8 empty] | 42
477 | 73/2 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 381.209 | 385 |  | 13860 | 385 | [8 empty] | 42
478 | 73/3 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 384.657 | 385 |  | 13860 | 385 | [8 empty] | 42
479 | 73/4 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 368.816 | 370 |  | 13320 | 370 | [8 empty] | 36
480 | 73/5 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 365.477 | 370 |  | 13320 | 370 | [8 empty] | 36
481 | 73/6 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 392.386 | 395 |  | 14220 | 395 | [8 empty] | 42
482 | 73/7 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 374.923 | 375 |  | 13500 | 375 | [8 empty] | 42
483 | 73/8 | DA+3 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 379.526 | 380 |  | 13680 | 380 | [8 empty] | 42
484 | 73/9 | DA+0 | [11 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
[8 empty] | 378.903 | 380 |  | 13680 | 380 | [8 empty] | 42
485 | 74/0 | DB2+0 |  |  |  |  | 9° 59' 12.84" RT | [5 empty] | 24 |  | 6 | [6 empty] | 30 |  | 1 |  | 1 |  |  | 2
Total | [7 empty] | 191391.82 |  |  | 6932340 | 192815 | 4232 | 4874 | 1056 | 2382 | 104 | 4 | 0 | 0 | 19806 | 2640 | 72 | 179 | 397 | 573 | 0 | 0 | 1150
Receipt at Mandli | [14 empty] | 1002 | 2394 | 164 | 4 | 3827 | 1276 | 15372 | 1401 | 72 | 83 | 399 | 399 | 100 | 32 | 1130
Receipt at Phalsund mail dated 28.03.26 | [10 empty] | 7525990 |  |  |  | 102 | 24 |  |  | 200 | 76 | 5124 | 1246 | 5 | 102 | 258 | 179 | 74 | 69 | 70
Total Till 21.01.2026 | [10 empty] | 7525990 | 0 | 0 | 0 | 1104 | 2418 | 164 | 4 | 4027 | 1352 | 20496 | 2647 | 77 | 185 | 657 | 578 | 174 | 101 | 1200
Balance | [10 empty] | -593650 | 192815 | 4232 | 4874 | -48 | -36 | -60 | 0 | -4027 | -1352 | -690 | -7 | -5 | -6 | -260 | -5 | -174 | -101 | -50
41
42

## Stringing Productivity (hidden)
765KV D/C Fatehgarh III- Beawar Transmission Line, PKG F, Stringing Status | [39 empty] | Dated | 2026-07-29
Sr. No. | Sub-Contractor Name | Completed in April |  |  | Insulator Hoisting | [30 empty] | Output Upto Yesterdays (Kms) in May | Cumulative Output till today(Kms) | Start Date | Comp Date | Status | Total Manpower
|  | From | To | Span | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31
0

## OPGW
Progress Summary'!A1
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line
OPGW
SL. No. | Section |  | Gang Name | Section Length | Paying out |  |  |  | Final Sag |  |  |  | Completion Month | Splicing | Splicing done by | Remarks
| From | To |  |  | Section Length | Start Date | End Date | Remarks | Section Length | Start Date | End Date | Remarks |  |  |  | Remarks
1 | 59/0 | 59/8 | Congent Technology | 3.337 | 3.337 | 2025-02-10 | 2025-02-11 |  | 3.337 | 2025-02-10 | 2025-02-11 | Final sag completed | 2025-02-01 | 2025-03-05 | Revant Sharma
2 | 59/8 | 60/0 | Congent Technology | 3.778 | 3.778 | 2025-02-12 | 2025-02-13 |  | 3.778 | 2025-02-12 | 2025-02-13 | Final sag completed | 2025-02-01 | 2025-02-26 | Revant Sharma
3 | 60/0 | 61/0 | Congent Technology | 4.877 | 4.877 | 2025-02-15 | 2025-02-16 |  | 4.877 | 2025-02-15 | 2025-02-16 | Final sag completed | 2025-02-01
4 | 61/0 | 62/0 | Congent Technology | 4.568 | 4.568 | 2025-02-19 | 2025-02-19 |  | 4.568 | 2025-02-19 | 2025-02-19 | Final sag completed | 2025-02-01 | 2025-02-27 | Revant Sharma
5 | 62/0 | 63/0 | Congent Technology | 4.863 | 4.863 | 2025-02-23 | 2025-02-24 |  | 4.863 | 2025-02-23 | 2025-02-24 | Final sag completed | 2025-02-01
6 | 63/0 | 64/0 | Congent Technology | 3.711 | 3.711 | 2025-03-01 | 2025-03-02 |  | 3.711 | 2025-03-01 | 2025-03-02 | Final sag completed | 2025-03-01
7 | 64/0 | 65/0 | Congent Technology | 4.918 | 4.918 | 2025-03-03 | 2025-03-03 |  | 4.918 | 2025-03-03 | 2025-03-03 | Final sag completed | 2025-03-01
8 | 51/0 | 52/0 | Congent Technology | 1.049 | 1.049 | 2025-07-23 | 2025-07-24 |  | 1.049 | 2025-07-23 | 2025-07-24 | Final sag completed | 2025-07-01
9 | 50/0 | 51/0 | Congent Technology | 4.444 | 4.444 | 2025-07-26 | 2025-07-26 |  | 4.444 | 2025-07-26 | 2025-07-26 | Final sag completed | 2025-07-01
10 | 48/0 | 49/0 | Congent Technology | 0.831 | 0.831 | 2025-08-02 | 2025-08-05 |  | 0.831 | 2025-08-02 | 2025-08-05 | Final sag completed | 2025-08-01
11 | 49/0 | 50/0 | Congent Technology | 3.227 | 3.227 | 2025-08-10 | 2025-08-14 |  | 3.227 | 2025-08-10 | 2025-08-14 | Final sag completed | 2025-08-01
12 | 70/0 | 71/0 | Congent Technology | 4.966 | 4.966 | 2025-12-17 | 2025-12-17 |  | 4.966 | 2025-12-17 | 2025-12-18 | Final sag completed | 2025-12-01
13 | 71/0 | 72/0 | Congent Technology | 3.675 | 3.675 | 2025-12-20 | 2025-12-20 |  | 3.675 | 2025-12-21 | 2025-12-21 | Final sag completed | 2025-12-01
14 | 72/0 | 73/0 | Congent Technology | 1.628 | 1.628 | 2025-12-23 | 2025-12-23 |  | 1.628 | 2025-12-24 | 2025-12-24 | Final sag completed | 2025-12-01
15 | 73/0 | 74/0 | Congent Technology | 3.788 | 3.788 | 2025-12-24 | 2025-12-24 |  | 3.788 | 2025-12-24 | 2025-12-24 | Final sag completed | 2025-12-01
16 | 65/0 | 66/0 | Congent Technology | 4.7358 | 4.7358 | 2026-01-04 | 2026-01-04 |  | 4.7358 | 2026-01-04 | 2026-01-04 | Final sag completed | 2026-01-01
17 | 66/0 | 70/0 | Congent Technology | 2.239 | 2.239 | 2026-01-05 | 2026-01-05 |  | 2.239 | 2026-01-07 | 2026-01-07 | Final sag completed | 2026-01-01
18 | Gty | 2/0 | Jai Bagrangbali | 3.638 | 3.638 | 2026-01-07 | 2026-01-07 |  | 3.638 | 2026-01-18 | 2026-01-19 | Final sag completed | 2026-01-01
19 | 47/0 | 48/0 | Congent Technology | 4.477 | 4.477 | 2026-02-05 | 2026-02-05 |  | 4.477 | 2026-02-05 | 2026-02-05 | Final sag completed | 2026-02-01
20 | 2/0 | 4/0 | Jai Bagrangbali | 4.05 | 4.05 | 2026-02-06 | 2026-02-06 |  | 4.05 | 2026-02-06 | 2026-02-06 | Final sag completed | 2026-02-01
21 | 57/0 | 59/0 | Congent Technology | 3.526 | 3.526 | 2026-02-07 | 2026-02-07 |  | 3.526 | 2026-02-07 | 2026-02-07 | Final sag completed | 2026-02-01
22 | 10/12 | 11/0 | Congent Technology | 4.95 | 4.95 | 2026-02-09 | 2026-02-09 |  | 4.95 | 2026-02-09 | 2026-02-09 | Final sag completed | 2026-02-01
23 | 55/0 | 57/0 | Congent Technology | 3.52 | 3.52 | 2026-05-07 | 2026-05-07 |  | 3.52 | 2026-05-07 | 2026-05-07 | Final sag completed | 2026-05-01
24 | 53/0 | 54/0 | Congent Technology | 3.69 | 3.69 | 2026-05-11 | 2026-05-11 |  | 3.69 | 2026-05-12 | 2026-05-12 | Final sag completed | 2026-05-01
25 | 10/0 | 10/12 | Congent Technology | 4.89 | 4.89 | 2026-06-19 | 2026-06-23 |  | 4.89 | 2026-06-23 | 2026-06-23 | Final sag completed | 2026-06-01
26 | 11/0 | 11A/0 | Congent Technology | 2.238 | 2.238 | 2026-06-25 | 2026-06-26 |  | 2.238 | 2026-06-25 | 2026-06-26 | Final sag completed | 2026-06-01
27 | 11A/0 | 13/0 | Congent Technology | 4.3226 | 4.3226 | 2026-06-28 | 2026-06-29 |  | 4.3226 | 2026-06-28 | 2026-06-29 | Final sag completed | 2026-06-01
28 | 8/7 | 10/0 | Congent Technology | 2.6892 | 2.6892 | 2026-07-01 | 2026-07-01 |  | 2.6892 | 2026-07-01 | 2026-07-01 | Final sag completed | 2026-07-01
29 | 8/0 | 8/7 | Congent Technology | 2.8614 | 2.8614 | 2026-07-04 | 2026-07-04 |  | 2.8614 | 2026-07-04 | 2026-07-04 | Final sag completed | 2026-07-01
30 | 54/0 | 55/0 | Congent Technology | 2.41 | 2.41 | 2026-07-10 | 2026-07-10 |  | 2.41 | 2026-07-10 | 2026-07-10 | Final sag completed | 2026-07-01
31 | 52/0 | 53/0 | Congent Technology | 4.53 | 4.53 | 2026-07-13 | 2026-07-13 |  | 4.53 | 2026-07-13 | 2026-07-13 | Final sag completed | 2026-07-01
32 | 43/0 | 44/0 | Congent Technology-1 | 4.8527 | 4.8527 | 2026-07-24 | 2026-07-24 |  | 4.8527 | 2026-07-24 | 2026-07-24 | Final sag completed | 2026-07-01
33 | 4/0 | 8/0 | Congent Technology-2 | 3.4705 | 3.4705 | 2026-07-23 | 2026-07-23 |  | 3.4705 | 2026-07-23 | 2026-07-23 | Final sag completed | 2026-07-01
34 | 44/0 | 44/8 | Congent Technology-1 | 3.1523 | 3.1523 | 2026-07-26 | 2026-07-26 |  | 3.1523 | 2026-07-26 | 2026-07-26 | Final sag completed | 2026-07-01
35 | 13/0 | 16/0 | Congent Technology-2 | 4.4694 | 4.4694 | 2026-07-27 | 2026-07-27 |  | 4.4694 | 2026-07-27 | 2026-07-27 | Final sag completed | 2026-07-01 |  |  | 14A/2-ROW
36 | 44/8 | 47/0 | Congent Technology-1 | 2.4493 | 2.4493 | 2026-07-28 | 2026-07-28 |  | 2.4493 | 2026-07-28 | 2026-07-28 | Final sag completed | 2026-07-01
37 | 27/0 | 27/7 | Congent Technology-1 | 2.8104 |  | Platina paying ouut WIP.
TOTAL |  |  |  | 133.6316 | 130.8212 |  |  |  | 130.8212
[5 empty] | 19.114 |  |  |  | 19.114
[5 empty] | 149.9352 |  |  |  | 149.9352
|  |  |  | WIP=P/O-F/S | 2.8104
[9 empty] | 172.275 | 55.195
[9 empty] | 41.4538 | 28.59
1 | 36/0 | 38/0 | Completed by Tata | 3.5247 | 3.5247 |  |  |  | 3.5247 |  |  | Final sag completed by TPL
2 | 38/0 | 41/1 | Completed by Tata | 4.8371 | 4.8371 |  |  |  | 4.8371 |  |  | Final sag completed by TPL
Formulas:
Start Date = [Start Date]
End Date = [End Date]

## Accessories details
Owner : M/S Resonai Limited | [41 empty] | Tower Type | Tower Wt. Above Middle Cross Arm | Total Tower | Total Wt. | Colour Specifications
Project : Fatehgarh-3-Beawar 765kV D/C Transmission Line (Hexa AL59 Zebra Conductor) Part-F | [41 empty] | DA | 4.903 | 147 | 720.741 | White & Orange, Berger BR SYN ENL IS2932
Line Name : 765kV DC Fatehgarh3-Beawar TL | [41 empty] | DB | 7.366 | 12 | 88.392
Contractor : - Kec International Limited | [41 empty] | DC | 8.319 | 7 | 58.233
Accessories & Aviation painting details | [41 empty] | DD | 9.255 | 7 | 64.785
|  |  |  | 485 | 485 | Installation of Phase Plate, Sets of Six | [5 empty] | 485 | 96 |  | Installation of Circuit, Sets of two |  |  | 485 | 73 |  | 485 | 73 |  | 397 | 108 |  | 144 | 141 |  | 88 | 88 |  | 10033 |  | 5000 |  | 0 | 51 | 51 |  | 785.222
|  |  |  | Danger Plate | Number Plate | Phase Plate | [8 empty] | Circuit |  |  | Circuit Plate |  |  | Anti Climbing Device |  |  | Bird Guard |  |  | Aviation requirements
Sl. No | Loc. No. | Tower Type | Span |  |  | Circuit - 1 Left Side when Face is towards Beawer |  |  | Circuit - 2 Right Side when Face is towards Beawer |  |  | Total Required | Completion Date | Gang Name | Circuit - I Left Side when Face is towards Beawer | Circuit - II Right Side when Face is towards Beawer | Set's:- CKT I + CKT II | Total Required | Completion Date | Gang Name | Total Required | Completion Date | Gang Name | Total Required | Completion Date | Gang Name | Span Markers |  |  | Obstruction Light |  |  | Bird Flight Divertors (Non LED) |  |  |  |  | Painting Normal Towers | [8 empty] | TOT | Ext | Concetanate
[27 empty] | Total Required | Completion Date | Gang Name | Total Required | Completion Date | Gang Name | E/W |  | Date | Gang Name | OPGW | Total Required | Completion Date | Gang Name | Weight of Painting portion
|  |  | m | Set of one | Set of one | Top | Middle | Bottom | Top | Middle | Bottom | Set of Six | [5 empty] | Set of two |  |  | Set of one |  |  | Set of Six |  |  | Sets of 1 |  |  | 1 medium intensity + 2 low intensity, Sets of 1 |  |  | In Nos
| GANTRY | GTY
|  |  | 122 | [29 empty] | 11 | TRUE
1 | 1/0 | DD60+0 |  | 1 | 0001 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DD | 0 | DD+0
|  |  | 90 | [29 empty] | 8 | TRUE
2 | 1A/0 | DD60+0 |  | 1 | 0002 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DD | 0 | DD+0
|  |  | 277.7 | [29 empty] | 27 | FALSE | 2025-03-01 | Jai Bagrangbali
3 | 1A/1 | DA+6 |  | 1 | 0003 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 386 | [29 empty] | 38 | FALSE | 2025-03-01 | Jai Bagrangbali
4 | 1A/2 | DA+0 |  | 1 | 0004 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 443.6 | [29 empty] | 43 | FALSE | 2025-03-01 | Jai Bagrangbali
5 | 1A/3 | DA+0 |  | 1 | 0005 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 333.4 | [29 empty] | 32 | FALSE | 2025-03-01 | Jai Bagrangbali
6 | 1A/4 | DA+3 |  | 1 | 0006 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 431.9 | [29 empty] | 42 | FALSE | 2025-03-01 | Jai Bagrangbali
7 | 1A/5 | DA+0 |  | 1 | 0007 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 348.7 | [29 empty] | 34 | FALSE | 2025-03-01 | Jai Bagrangbali
8 | 1A/6 | DA+0 |  | 1 | 0008 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 395.7 | [29 empty] | 39 | FALSE | 2025-03-01 | Jai Bagrangbali
9 | 1A/7 | DA+3 |  | 1 | 0009 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 415 | [29 empty] | 41 | FALSE | 2025-03-01 | Jai Bagrangbali
10 | 1A/8 | DA+0 |  | 1 | 0010 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 394.3 | [29 empty] | 38 | FALSE | 2025-03-01 | Jai Bagrangbali
11 | 2/0 | DC1+0 |  | 1 | 0011 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 405.3 | [29 empty] | 40 | FALSE | 2025-03-01 | Jai Bagrangbali
12 | 2/1 | DA+3 |  | 1 | 0012 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 338.5 | [29 empty] | 33 | FALSE | 2025-03-01 | Jai Bagrangbali
13 | 2/2 | DA+3 |  | 1 | 0013 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 406 | [29 empty] | 40 | FALSE | 2026-03-02 | Jai Bagrangbali
14 | 2/3 | DA+3 |  | 1 | 0014 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 429 | [29 empty] | 42 | FALSE | 2026-03-02 | Jai Bagrangbali
15 | 2/4 | DA+3 |  | 1 | 0015 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 411.6 | [29 empty] | 40 | FALSE | 2026-03-02 | Jai Bagrangbali
16 | 2/5 | DA+3 |  | 1 | 0016 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 425.7 | [29 empty] | 42 | FALSE | 2026-03-02 | Jai Bagrangbali
17 | 2/6 | DA+3 |  | 1 | 0017 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 408.2 | [29 empty] | 40 | FALSE | 2026-03-02 | Jai Bagrangbali
18 | 2/7 | DA+3 |  | 1 | 0018 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 354.6 | [29 empty] | 34 | FALSE | 2026-03-02 | Jai Bagrangbali
19 | 2/8 | DA+0 |  | 1 | 0019 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 308.7 | [29 empty] | 30 | FALSE | 2026-03-02 | Jai Bagrangbali
20 | 2/9 | DA+0 |  | 1 | 0020 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 336 | [29 empty] | 33 | FALSE | 2026-03-02 | Jai Bagrangbali
21 | 3/0 | DD60+6 |  | 1 | 0021 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DD | 6 | DD+6
|  |  | 226.5 | [29 empty] | 22 | FALSE | 2026-03-02 | Jai Bagrangbali
22 | 4/0 | DD60+6 |  | 1 | 0022 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DD | 6 | DD+6
|  |  | 343 | [29 empty] | 33 | TRUE
23 | 4/1 | DA+0 |  | 1 | 0023 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 358.4 | [29 empty] | 35 | TRUE
24 | 4/2 | DA+0 |  | 1 | 0024 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 381 | [29 empty] | 37 | TRUE
25 | 4/3 | DA+0 |  | 1 | 0025 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 367.6 | [29 empty] | 36 | TRUE
26 | 4/4 | DA+0 |  | 1 | 0026 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 423.1 | [29 empty] | 41 | TRUE
27 | 5/0 | DB1+9 |  | 1 | 0027 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 9 | DB+9
|  |  | 246 | [29 empty] | 24 | FALSE | 2026-05-07 | Om Construction
28 | 6/0 | DB2+9 |  | 1 | 0028 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 9 | DB+9
|  |  | 429.9 | [29 empty] | 42 | FALSE | 2026-05-07 | Om Construction
29 | 6/1 | DA+0 |  | 1 | 0029 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 362.4 | [29 empty] | 35 | FALSE | 2026-05-07 | Om Construction
30 | 6/2 | DA+0 |  | 1 | 0030 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 347.9 | [29 empty] | 34 | FALSE | 2026-05-07 | Om Construction
31 | 7/0 | DB1+0 |  | 1 | 0031 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 210.8 | [29 empty] | 20 | FALSE | 2026-05-07 | Om Construction
32 | 8/0 | DB1+0 |  | 1 | 0032 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 409.2 | [29 empty] | 40 | FALSE | 2026-05-07 | Om Construction
33 | 8/1 | DA+3 |  | 1 | 0033 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 413.6 | [29 empty] | 40 | FALSE | 2026-05-07 | Om Construction
34 | 8/2 | DA+3 |  | 1 | 0034 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 393.2 | [29 empty] | 38 | FALSE | 2026-05-07 | Om Construction
35 | 8/3 | DA+0 |  | 1 | 0035 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 416.5 | [29 empty] | 41 | FALSE | 2026-05-07 | Om Construction
36 | 8/4 | DA+3 |  | 1 | 0036 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 394.6 | [29 empty] | 38 | FALSE | 2026-05-07 | Om Construction
37 | 8/5 | DA+3 |  | 1 | 0037 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 393.2 | [29 empty] | 38 | FALSE | 2026-05-07 | Om Construction
38 | 8/6 | DA+3 |  | 1 | 0038 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 441.1 | [29 empty] | 43 | FALSE | 2026-05-07 | Om Construction
39 | 8/7 | DB1+0 |  | 1 | 0039 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 414.4 | [29 empty] | 40 | FALSE | 2026-05-07 | Om Construction
40 | 8/8 | DA+6 |  | 1 | 0040 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 395.863 | [29 empty] | 39 | FALSE | 2026-05-08 | Om Construction
41 | 8/9 | DA+3 |  | 1 | 0041 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 413.404 | [29 empty] | 40 | FALSE | 2026-05-08 | Om Construction
42 | 8/10 | DA+3 |  | 1 | 0042 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 402.6 | [29 empty] | 39 | FALSE | 2026-05-08 | Om Construction
43 | 8/11 | DA+0 |  | 1 | 0043 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 372.1 | [29 empty] | 36 | FALSE | 2026-05-08 | Om Construction
44 | 8/12 | DA+0 |  | 1 | 0044 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 457.7 | [23 empty] | 1 | 2026-05-10 | Om Construction |  |  |  | 45 | FALSE | 2026-05-08 | Om Construction
45 | 9/0 | DD60+18 |  | 1 | 0045 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [8 empty] | 1 | 2026-05-20 | Om Construction | [5 empty] | 1 | 2026-05-24 | Om Construction | 37.298 | [5 empty] | DD | 18 | DD+18
|  |  | 233.1 | [23 empty] | 1 | 2026-05-10 | Om Construction |  |  |  | 22 | FALSE | 2026-05-08 | Om Construction
46 | 10/0 | DD60+25 |  | 1 | 0046 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [8 empty] | 1 | 2026-05-20 | Om Construction | [5 empty] | 1 | 2026-05-26 | Om Construction | 46.074 | [5 empty] | DD | 25 | DD+25
|  |  | 443.7 | [23 empty] | 1 | 2026-05-10 | Om Construction |  |  |  | 43 | FALSE | 2026-05-08 | Om Construction
47 | 10/1 | DA+0 |  | 1 | 0047 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 383.2 | [29 empty] | 37 | FALSE | 2026-05-08 | Om Construction
48 | 10/2 | DA+0 |  | 1 | 0048 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 398.6 | [29 empty] | 39 | FALSE | 2026-05-08 | Om Construction
49 | 10/3 | DA+0 |  | 1 | 0049 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 410.7 | [29 empty] | 40 | FALSE | 2026-05-08 | Om Construction
50 | 10/4 | DA+3 |  | 1 | 0050 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 416.2 | [29 empty] | 41 | FALSE | 2026-05-08 | Om Construction
51 | 10/5 | DA+3 |  | 1 | 0051 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 403.4 | [29 empty] | 39 | FALSE | 2026-05-08 | Om Construction
52 | 10/6 | DA+0 |  | 1 | 0052 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 373.845 | [29 empty] | 36 | FALSE | 2026-05-08 | Om Construction
53 | 10/7 | DA+3 |  | 1 | 0053 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 411.823 | [29 empty] | 40 | FALSE | 2026-05-08 | Om Construction
54 | 10/8 | DA+3 |  | 1 | 0054 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 414.2 | [29 empty] | 40 | FALSE | 2026-05-08 | Om Construction
55 | 10/9 | DA+0 |  | 1 | 0055 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 402.3 | [29 empty] | 39 | FALSE | 2026-05-08 | Om Construction
56 | 10/10 | DA+3 |  | 1 | 0056 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 430.3 | [29 empty] | 42 | FALSE | 2026-05-08 | Om Construction
57 | 10/11 | DA+3 |  | 1 | 0057 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 406.2 | [29 empty] | 40 | FALSE | 2026-05-08 | Om Construction
58 | 10/12 | DB1+0 |  | 1 | 0058 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 405.3 | [29 empty] | 40 | FALSE | 2025-03-01 | Shiv Power
59 | 10/13 | DA+3 |  | 1 | 0059 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 427.1 | [29 empty] | 42 | FALSE | 2025-03-01 | Shiv Power
60 | 10/14 | DA+3 |  | 1 | 0060 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 400 | [29 empty] | 39 | FALSE | 2025-03-01 | Shiv Power
61 | 10/15 | DA+3 |  | 1 | 0061 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 412.8 | [29 empty] | 40 | FALSE | 2025-03-01 | Shiv Power
62 | 10/16 | DA+3 |  | 1 | 0062 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 387.8 | [29 empty] | 38 | FALSE | 2025-03-01 | Shiv Power
63 | 10/17 | DA+3 |  | 1 | 0063 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 436.7 | [29 empty] | 43 | FALSE | 2025-03-01 | Shiv Power
64 | 10/18 | DA+3 |  | 1 | 0064 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 403.7 | [29 empty] | 39 | FALSE | 2025-03-02 | Shiv Power
65 | 10/19 | DA+0 |  | 1 | 0065 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 409.5 | [29 empty] | 40 | FALSE | 2025-03-02 | Shiv Power
66 | 10/20 | DA+3 |  | 1 | 0066 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 418.6 | [29 empty] | 41 | FALSE | 2025-03-02 | Shiv Power
67 | 10/21 | DA+3 |  | 1 | 0067 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 410.3 | [29 empty] | 40 | FALSE | 2025-03-02 | Shiv Power
68 | 10/22 | DA+0 |  | 1 | 0068 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 384 | [29 empty] | 37 | FALSE | 2025-03-02 | Shiv Power
69 | 10/23 | DA+0 |  | 1 | 0069 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 450.8 | [29 empty] | 44 | FALSE | 2025-03-02 | Shiv Power
70 | 11/0 | DB1+0 |  | 1 | 0070 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 384.2 | [29 empty] | 37 | FALSE | 2026-07-01 | Om Construction
71 | 11/1 | DA+0 |  | 1 | 0071 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 338.6 | [29 empty] | 33 | FALSE | 2026-07-01 | Om Construction
72 | 11/2 | DA+0 |  | 1 | 0072 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 370.7 | [29 empty] | 36 | FALSE | 2026-07-01 | Om Construction
73 | 11/3 | DA+0 |  | 1 | 0073 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 434.1 | [29 empty] | 42 | FALSE | 2026-07-01 | Om Construction
74 | 11/4 | DA+0 |  | 1 | 0074 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 368.1 | [29 empty] | 36 | FALSE | 2026-07-01 | Om Construction
75 | 11/5 | DA+0 |  | 1 | 0075 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 342.3 | [29 empty] | 33 | FALSE | 2026-07-01 | Om Construction
76 | 11A/0 | DB1+0 |  | 1 | 0076 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 405.1 | [29 empty] | 40 | FALSE | 2026-07-01 | Om Construction
77 | 11A/1 | DA+3 |  | 1 | 0077 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 412.2 | [29 empty] | 40 | FALSE | 2026-07-01 | Om Construction
78 | 11A/2 | DA+0 |  | 1 | 0078 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 412.2 | [29 empty] | 40 | FALSE | 2026-07-01 | Om Construction
79 | 11A/3 | DA+3 |  | 1 | 0079 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 422.1 | [29 empty] | 41 | FALSE | 2026-07-01 | Om Construction
80 | 11A/4 | DA+3 |  | 1 | 0080 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 418.3 | [29 empty] | 41 | FALSE | 2026-07-01 | Om Construction
81 | 11A/5 | DA+3 |  | 1 | 0081 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 384.3 | [29 empty] | 37 | FALSE | 2026-07-01 | Om Construction
82 | 11A/6 | DA+6 |  | 1 | 0082 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 434.2 | [29 empty] | 42 | FALSE | 2026-07-01 | Om Construction
83 | 11A/7 | DA+9 |  | 1 | 0083 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 390.1 | [29 empty] | 38 | FALSE | 2026-07-01 | Om Construction
84 | 11A/8 | DA+6 |  | 1 | 0084 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 426.3 | [29 empty] | 42 | FALSE | 2026-07-01 | Om Construction
85 | 11A/9 | DA+3 |  | 1 | 0085 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 405.9 | [29 empty] | 40 | FALSE | 2026-07-01 | Om Construction
86 | 12/0 | DD60+0 |  | 1 | 0086 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DD | 0 | DD+0
|  |  | 211.9 | [29 empty] | 20 | FALSE | 2026-07-01 | Om Construction
87 | 13/0 | DD60+3 |  | 1 | 0087 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DD | 3 | DD+3
|  |  | 464.3 | [29 empty] | 45 | FALSE | 2026-07-02 | Om Construction
88 | 13/1 | DA+9 |  | 1 | 0088 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 373.7 | [29 empty] | 36 | FALSE | 2026-07-02 | Om Construction
89 | 13/2 | DA+3 |  | 1 | 0089 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 419.7 | [29 empty] | 41 | FALSE | 2026-07-02 | Om Construction
90 | 13/3 | DA+3 |  | 1 | 0090 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 420.3 | [29 empty] | 41 | FALSE | 2026-07-02 | Om Construction
91 | 13/4 | DA+3 |  | 1 | 0091 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 400 | [29 empty] | 39 | FALSE | 2026-07-02 | Om Construction
92 | 14/0 | DC2+0 |  | 1 | 0092 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 381.4 | [29 empty] | 37 | FALSE | 2026-07-02 | Om Construction
93 | 14A/0 | DC1+0 |  | 1 | 0093 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 412.765 | [29 empty] | 40 | FALSE | 2026-07-02 | Om Construction
94 | 14A/1 | DA+3 |  | 1 | 0094 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 396.029 | [29 empty] | 39 | FALSE | 2026-07-02 | Om Construction
95 | 14A/2 | DA+0 |  | 1 | 0095 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 383.3 | [29 empty] | 37 | FALSE | 2026-07-02 | Om Construction
96 | 15/0 | DC1+0 |  | 1 | 0096 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 404.6 | [29 empty] | 39 | TRUE
97 | 15/1 | DA+3 |  | 1 | 0097 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 413.3 | [29 empty] | 40 | TRUE
98 | 16/0 | DC1+0 |  | 1 | 0098 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 354.283 | [29 empty] | 34 | TRUE
99 | 16/1 | DA+0 |  | 1 | 0099 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 424.28 | [29 empty] | 41 | TRUE
100 | 16/2 | DA+0 |  | 1 | 0100 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 340.3 | [29 empty] | 33 | TRUE
101 | 16/3 | DA+3 |  | 1 | 0101 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 394.7 | [29 empty] | 38 | TRUE
102 | 16/4 | DA+0 |  | 1 | 0102 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 435.863 | [29 empty] | 43 | TRUE
103 | 16/5 | DA+3 |  | 1 | 0103 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 386.8 | [29 empty] | 38 | TRUE
104 | 17/0 | DB2+3 |  | 1 | 0104 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 3 | DB+3
|  |  | 393.7 | [29 empty] | 38 | TRUE
105 | 17/1 | DA+3 |  | 1 | 0105 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 415.9 | [29 empty] | 41 | TRUE
106 | 17/2 | DA+6 |  | 1 | 0106 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 422.8 | [29 empty] | 41 | TRUE
107 | 17/3 | DA+0 |  | 1 | 0107 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 409.9 | [29 empty] | 40 | TRUE
108 | 17/4 | DA+3 |  | 1 | 0108 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 425.3 | [29 empty] | 42 | TRUE
109 | 17/5 | DA+3 |  | 1 | 0109 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 383.4 | [29 empty] | 37 | TRUE
110 | 18/0 | DC2+0 |  | 1 | 0110 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 372.8 | [29 empty] | 36 | TRUE
111 | 18/1 | DA+0 |  | 1 | 0111 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 379.8 | [29 empty] | 37 | TRUE
112 | 18/2 | DA+0 |  | 1 | 0112 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 371 | [29 empty] | 36 | TRUE
113 | 18/3 | DA+0 |  | 1 | 0113 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 398.7 | [29 empty] | 39 | TRUE
114 | 18/4 | DA+0 |  | 1 | 0114 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 380.8 | [29 empty] | 37 | TRUE
115 | 19/0 | DC2+0 |  | 1 | 0115 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 366.9 | [29 empty] | 36 | TRUE
116 | 19/1 | DA+0 |  | 1 | 0116 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 372.5 | [29 empty] | 36 | TRUE
117 | 19/2 | DA+0 |  | 1 | 0117 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 376.5 | [29 empty] | 37 | TRUE
118 | 19/3 | DA+0 |  | 1 | 0118 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 384.3 | [29 empty] | 37 | TRUE
119 | 19/4 | DA+0 |  | 1 | 0119 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 375.4 | [29 empty] | 37 | TRUE
120 | 19/5 | DA+0 |  | 1 | 0120 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 381.2 | [29 empty] | 37 | TRUE
121 | 20/0 | DB2+0 |  | 1 | 0121 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 386.8 | [29 empty] | 38 | TRUE
122 | 20/1 | DA+0 |  | 1 | 0122 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 387 | [29 empty] | 38 | TRUE
123 | 20/2 | DA+0 |  | 1 | 0123 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 348.5 | [29 empty] | 34 | TRUE
124 | 20/3 | DA+0 |  | 1 | 0124 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 355 | [29 empty] | 35 | TRUE
125 | 21/0 | DB2+0 |  | 1 | 0125 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 414.9 | [29 empty] | 40 | TRUE
126 | 21/1 | DA+6 |  | 1 | 0126 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 407.2 | [29 empty] | 40 | TRUE
127 | 21/2 | DA+0 |  | 1 | 0127 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 432.2 | [29 empty] | 42 | TRUE
128 | 21/3 | DA+6 |  | 1 | 0128 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 401.9 | [29 empty] | 39 | TRUE
129 | 21/4 | DA+3 |  | 1 | 0129 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 434.2 | [29 empty] | 42 | TRUE
130 | 21/5 | DA+6 |  | 1 | 0130 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 405.5 | [29 empty] | 40 | TRUE
131 | 21/6 | DA+3 |  | 1 | 0131 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 426 | [29 empty] | 42 | TRUE
132 | 21/7 | DA+3 |  | 1 | 0132 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 406.9 | [29 empty] | 40 | TRUE
133 | 21/8 | DA+6 |  | 1 | 0133 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 433.3 | [29 empty] | 42 | TRUE
134 | 21/9 | DA+3 |  | 1 | 0134 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 372.9 | [29 empty] | 36 | TRUE
135 | 21/10 | DA+6 |  | 1 | 0135 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 443.5 | [29 empty] | 43 | TRUE
136 | 22/0 | DB2+3 |  | 1 | 0136 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 3 | DB+3
|  |  | 456.3 | [29 empty] | 45 | TRUE
137 | 22/1 | DA+9 |  | 1 | 0137 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-27 | MC Power | [20 empty] | DA | 9 | DA+9
|  |  | 379.2 | [29 empty] | 37 | TRUE
138 | 22/2 | DA+6 |  | 1 | 0138 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 382.6 | [29 empty] | 37 | TRUE
139 | 22/3 | DA+9 |  | 1 | 0139 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 435.6 | [29 empty] | 43 | TRUE
140 | 22/4 | DA+9 |  | 1 | 0140 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 402.1 | [29 empty] | 39 | TRUE
141 | 22/5 | DA+9 |  | 1 | 0141 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 417.3 | [29 empty] | 41 | TRUE
142 | 22/6 | DA+0 |  | 1 | 0142 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 347.7 | [29 empty] | 34 | TRUE
143 | 22/7 | DA+0 |  | 1 | 0143 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 356.3 | [29 empty] | 35 | TRUE
144 | 22/8 | DB1+0 |  | 1 | 0144 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 389.2 | [29 empty] | 38 | TRUE
145 | 22/9 | DA+6 |  | 1 | 0145 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 343.8 | [29 empty] | 33 | TRUE
146 | 22/10 | DA+6 |  | 1 | 0146 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-27 | Final Checking Gang | [20 empty] | DA | 6 | DA+6
|  |  | 395.5 | [29 empty] | 39 | TRUE
147 | 22/11 | DA+6 |  | 1 | 0147 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-27 | Final Checking Gang | [20 empty] | DA | 6 | DA+6
|  |  | 408 | [29 empty] | 40 | TRUE
148 | 22/12 | DA+3 |  | 1 | 0148 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-27 | Final Checking Gang | [20 empty] | DA | 3 | DA+3
|  |  | 318 | [29 empty] | 31 | TRUE
149 | 22/13 | DA+6 |  | 1 | 0149 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-27 | Final Checking Gang | [20 empty] | DA | 6 | DA+6
|  |  | 447.3 | [29 empty] | 44 | TRUE
150 | 23/0 | DD45+3 |  | 1 | 0150 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DD | 3 | DD+3
|  |  | 222.2 | [29 empty] | 21 | TRUE
151 | 24/0 | DD45+3 |  | 1 | 0151 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DD | 3 | DD+3
|  |  | 433.9 | [29 empty] | 42 | TRUE
152 | 25/0 | DC1+6 |  | 1 | 0152 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 6 | DC+6
|  |  | 422.3 | [29 empty] | 41 | TRUE
153 | 25/1 | DA+3 |  | 1 | 0153 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 370.7 | [29 empty] | 36 | TRUE
154 | 25/2 | DA+0 |  | 1 | 0154 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 345.7 | [29 empty] | 34 | TRUE
155 | 25/3 | DA+0 |  | 1 | 0155 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 391.1 | [29 empty] | 38 | TRUE
156 | 25/4 | DA+0 |  | 1 | 0156 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 440.4 | [29 empty] | 43 | TRUE
157 | 26/0 | DB1+0 |  | 1 | 0157 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 391.4 | [29 empty] | 38 | TRUE
158 | 26/1 | DA+0 |  | 1 | 0158 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 406.5 | [29 empty] | 40 | TRUE
159 | 26/2 | DA+3 |  | 1 | 0159 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 418 | [29 empty] | 41 | TRUE
160 | 26/3 | DA+0 |  | 1 | 0160 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 422.6 | [29 empty] | 41 | TRUE
161 | 26/4 | DA+6 |  | 1 | 0161 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 410 | [29 empty] | 40 | TRUE
162 | 26/5 | DA+6 |  | 1 | 0162 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 363.4 | [29 empty] | 35 | TRUE
163 | 26/6 | DA+6 |  | 1 | 0163 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 421.9 | [29 empty] | 41 | TRUE
164 | 26/7 | DA+0 |  | 1 | 0164 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 416.7 | [29 empty] | 41 | TRUE
165 | 26/8 | DA+6 |  | 1 | 0165 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 413.8 | [29 empty] | 40 | TRUE
166 | 27/0 | DC1+0 |  | 1 | 0166 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 399.8 | [29 empty] | 39 | TRUE
167 | 27/1 | DA+3 |  | 1 | 0167 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-26 | Final Checking Gang | [20 empty] | DA | 3 | DA+3
|  |  | 425.2 | [29 empty] | 42 | TRUE
168 | 27/2 | DA+3 |  | 1 | 0168 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-26 | Final Checking Gang | [20 empty] | DA | 3 | DA+3
|  |  | 398.6 | [29 empty] | 39 | TRUE
169 | 27/3 | DA+3 |  | 1 | 0169 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-26 | Final Checking Gang | [20 empty] | DA | 3 | DA+3
|  |  | 430.7 | [29 empty] | 42 | TRUE
170 | 27/4 | DA+3 |  | 1 | 0170 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-26 | Final Checking Gang | [20 empty] | DA | 3 | DA+3
|  |  | 410 | [29 empty] | 40 | TRUE
171 | 27/5 | DA+0 |  | 1 | 0171 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-26 | Final Checking Gang | [20 empty] | DA | 0 | DA+0
|  |  | 402.6 | [29 empty] | 39 | TRUE
172 | 27/6 | DA+0 |  | 1 | 0172 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-26 | Final Checking Gang | [20 empty] | DA | 0 | DA+0
|  |  | 343.5 | [29 empty] | 33 | TRUE
173 | 27/7 | DB1+0 |  | 1 | 0173 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 392 | [29 empty] | 38 | TRUE
174 | 27/8 | DA+0 |  | 1 | 0174 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-26 | Final Checking Gang | [20 empty] | DA | 0 | DA+0
|  |  | 381.1 | [29 empty] | 37 | TRUE
175 | 27/9 | DA+0 |  | 1 | 0175 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-26 | Final Checking Gang | [20 empty] | DA | 0 | DA+0
|  |  | 366.3 | [29 empty] | 36 | TRUE
176 | 27/10 | DA+3 |  | 1 | 0176 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-26 | Final Checking Gang | [20 empty] | DA | 3 | DA+3
|  |  | 420.1 | [29 empty] | 41 | TRUE
177 | 27/11 | DA+3 |  | 1 | 0177 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-26 | Final Checking Gang | [20 empty] | DA | 3 | DA+3
|  |  | 420.8 | [29 empty] | 41 | TRUE
178 | 27/12 | DA+3 |  | 1 | 0178 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-26 | Final Checking Gang | [20 empty] | DA | 3 | DA+3
|  |  | 406.6 | [29 empty] | 40 | TRUE
179 | 28/0 | DB2+0 |  | 1 | 0179 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 379.6 | [29 empty] | 37 | TRUE
180 | 28/1 | DA+0 |  | 1 | 0180 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 385 | [29 empty] | 38 | TRUE
181 | 28/2 | DA+0 |  | 1 | 0181 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 369 | [29 empty] | 36 | TRUE
182 | 28/3 | DA+0 |  | 1 | 0182 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 409 | [29 empty] | 40 | TRUE
183 | 28/4 | DA+0 |  | 1 | 0183 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 422 | [29 empty] | 41 | TRUE
184 | 28/5 | DA+9 |  | 1 | 0184 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 370 | [29 empty] | 36 | TRUE
185 | 28/6 | DA+6 |  | 1 | 0185 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 464 | [29 empty] | 45 | TRUE
186 | 28/7 | DA+3 |  | 1 | 0186 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 375 | [29 empty] | 37 | TRUE
187 | 28/8 | DA+3 |  | 1 | 0187 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 465.5 | [29 empty] | 46 | TRUE
188 | 29/0 | DB1+0 |  | 1 | 0188 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 365.6 | [29 empty] | 36 | TRUE
189 | 29/1 | DA+3 |  | 1 | 0189 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-25 | Final Checking Gang | [20 empty] | DA | 3 | DA+3
|  |  | 424 | [29 empty] | 41 | TRUE
190 | 29/2 | DA+3 |  | 1 | 0190 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-25 | Final Checking Gang | [20 empty] | DA | 3 | DA+3
|  |  | 399 | [29 empty] | 39 | TRUE
191 | 29/3 | DA+0 |  | 1 | 0191 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-25 | Final Checking Gang | [20 empty] | DA | 0 | DA+0
|  |  | 440 | [29 empty] | 43 | TRUE
192 | 29/4 | DA+6 |  | 1 | 0192 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-25 | Final Checking Gang | [20 empty] | DA | 6 | DA+6
|  |  | 382.1 | [29 empty] | 37 | TRUE
193 | 30/0 | DC1+0 |  | 1 | 0193 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 388.9 | [29 empty] | 38 | TRUE
194 | 30/1 | DA+0 |  | 1 | 0194 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 445 | [29 empty] | 44 | TRUE
195 | 30/2 | DA+0 |  | 1 | 0195 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 395 | [29 empty] | 39 | TRUE
196 | 30/3 | DA+3 |  | 1 | 0196 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 387 | [29 empty] | 38 | TRUE
197 | 30/4 | DA+3 |  | 1 | 0197 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 442 | [29 empty] | 43 | TRUE
198 | 30/5 | DA+3 |  | 1 | 0198 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 314 | [29 empty] | 30 | TRUE
199 | 30/6 | DA+0 |  | 1 | 0199 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 347.4 | [29 empty] | 34 | TRUE
200 | 31/0 | DB2+0 |  | 1 | 0200 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 383.6 | [29 empty] | 37 | TRUE
201 | 31/1 | DA+0 |  | 1 | 0201 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 366 | [29 empty] | 36 | TRUE
202 | 31/2 | DA+0 |  | 1 | 0202 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 332.9 | [29 empty] | 32 | TRUE
203 | 32/0 | DC1+0 |  | 1 | 0203 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 402.7 | [29 empty] | 39 | FALSE | 2026-05-06 | Om Construction
204 | 32/1 | DA+3 |  | 1 | 0204 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 428.8 | [29 empty] | 42 | FALSE | 2026-05-06 | Om Construction
205 | 32/2 | DA+3 |  | 1 | 0205 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 410.9 | [29 empty] | 40 | FALSE | 2026-05-06 | Om Construction
206 | 32/3 | DA+0 |  | 1 | 0206 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 381.1 | [29 empty] | 37 | FALSE | 2026-05-06 | Om Construction
207 | 32/4 | DA+0 |  | 1 | 0207 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 451.5 | [29 empty] | 44 | FALSE | 2026-05-06 | Om Construction
208 | 33/0 | DC1+0 |  | 1 | 0208 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 379.6 | [29 empty] | 37 | FALSE | 2026-05-06 | Om Construction
209 | 33/1 | DA+0 |  | 1 | 0209 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 292.5 | [29 empty] | 28 | FALSE | 2026-05-06 | Om Construction
210 | 34/0 | DB2+0 |  | 1 | 0210 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 432.6 | [29 empty] | 42 | FALSE | 2026-05-06 | Om Construction
211 | 34/1 | DA+9 |  | 1 | 0211 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 407.5 | [29 empty] | 40 | FALSE | 2026-05-06 | Om Construction
212 | 34/2 | DA+6 |  | 1 | 0212 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 377 | [29 empty] | 37 | FALSE | 2026-05-06 | Om Construction
213 | 34/3 | DA+0 |  | 1 | 0213 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 10.07.2026 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 451.6 | [29 empty] | 44 | FALSE | 2026-05-06 | Om Construction
214 | 34/4 | DA+0 |  | 1 | 0214 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 10.07.2026 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 379.3 | [29 empty] | 37 | FALSE | 2026-05-06 | Om Construction
215 | 35/0 | DB2+6 |  | 1 | 0215 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 6 | DB+6
|  |  | 265.6 | [29 empty] | 26 | FALSE | 2026-05-06 | Om Construction
216 | 35/1 | DA+9 |  | 1 | 0216 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 10.07.2026 | Company Gang | [20 empty] | DA | 9 | DA+9
|  |  | 492.4 | [29 empty] | 48 | FALSE | 2026-05-06 | Om Construction
217 | 35/2 | DB1+0 |  | 1 | 0217 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 522.2 | [29 empty] | 51 | FALSE | 2026-05-06 | Om Construction
218 | 35/3 | DB1+6 |  | 1 | 0218 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 6 | DB+6
|  |  | 418.9 | [29 empty] | 41 | FALSE | 2026-07-04 | Om Construction
219 | 35/4 | DA+0 |  | 1 | 0219 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 10.07.2026 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 421.7 | [29 empty] | 41 | FALSE | 2026-07-04 | Om Construction
220 | 35/5 | DA+0 |  | 1 | 0220 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 10.07.2026 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 342.7 | [29 empty] | 33 | FALSE | 2026-07-04 | Om Construction
221 | 36/0 | DB2+0 |  | 1 | 0221 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 386.4 | [29 empty] | 38 | FALSE | 2026-07-04 | Om Construction
222 | 36/1 | DA+0 |  | 1 | 0222 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 10.07.2026 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 309.4 | [29 empty] | 30 | FALSE | 2026-07-04 | Om Construction
223 | 36/2 | DA+0 |  | 1 | 0223 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 10.07.2026 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 357.8 | [29 empty] | 35 | FALSE | 2026-07-04 | Om Construction
224 | 36/3 | DA+0 |  | 1 | 0224 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 10.07.2026 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 480.4 | [29 empty] | 47 | FALSE | 2026-07-04 | Om Construction
225 | 36/4 | DA+6 |  | 1 | 0225 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 10.07.2026 | Company Gang | [20 empty] | DA | 6 | DA+6
|  |  | 350.5 | [29 empty] | 34 | FALSE | 2026-07-04 | Om Construction
226 | 37/0 | DB2+0 |  | 1 | 0226 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 443.3 | [29 empty] | 43 | TRUE
227 | 37/1 | DA+9 |  | 1 | 0227 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-24 | Final Checking Gang | [20 empty] | DA | 9 | DA+9
|  |  | 356.7 | [29 empty] | 35 | TRUE
228 | 37/2 | DA+3 |  | 1 | 0228 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-24 | Final Checking Gang | [20 empty] | DA | 3 | DA+3
|  |  | 339.9 | [29 empty] | 33 | TRUE
229 | 37/3 | DA+0 |  | 1 | 0229 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-24 | Final Checking Gang | [20 empty] | DA | 0 | DA+0
|  |  | 500.3 | [29 empty] | 49 | TRUE
230 | 38/0 | DB2+6 |  | 1 | 0230 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 6 | DB+6
|  |  | 421.4 | [29 empty] | 41 | TRUE
231 | 38/1 | DA+0 |  | 1 | 0231 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 419 | [29 empty] | 41 | TRUE
232 | 38/2 | DA+6 |  | 1 | 0232 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 420.3 | [29 empty] | 41 | TRUE
233 | 38/3 | DA+9 |  | 1 | 0233 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 414.9 | [29 empty] | 40 | TRUE
234 | 38/4 | DA+9 |  | 1 | 0234 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 425.5 | [29 empty] | 42 | TRUE
235 | 39/0 | DB2+6 |  | 1 | 0235 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 6 | DB+6
|  |  | 412.638 | [29 empty] | 40 | TRUE
236 | 39/1 | DA+0 |  | 1 | 0236 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 322.61 | [29 empty] | 31 | TRUE
237 | 40/0 | DC2+0 |  | 1 | 0237 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 396.2 | [29 empty] | 39 | TRUE
238 | 40/1 | DA+6 |  | 1 | 0238 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 425.8 | [29 empty] | 42 | TRUE
239 | 40/2 | DA+3 |  | 1 | 0239 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 401.7 | [29 empty] | 39 | TRUE
240 | 40/3 | DA+3 |  | 1 | 0240 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 436.3 | [29 empty] | 43 | TRUE
241 | 41/0 | DC1+6 |  | 1 | 0241 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 6 | DC+6
|  |  | 340.8 | [29 empty] | 33 | TRUE
242 | 41/1 | DB1+9 |  | 1 | 0242 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 9 | DB+9
|  |  | 447.8 | [29 empty] | 44 | TRUE
243 | 41/2 | DA+0 |  | 1 | 0243 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 09.07.2026 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 382.3 | [29 empty] | 37 | TRUE
244 | 42/0 | DC1+0 |  | 1 | 0244 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 384.7 | [29 empty] | 37 | FALSE | 2026-07-03 | Om Construction
245 | 42/1 | DA+6 |  | 1 | 0245 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 09.07.2026 | Company Gang | [20 empty] | DA | 6 | DA+6
|  |  | 407.4 | [29 empty] | 40 | FALSE | 2026-07-03 | Om Construction
246 | 42/2 | DA+6 |  | 1 | 0246 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 09.07.2026 | Company Gang | [20 empty] | DA | 6 | DA+6
|  |  | 414.2 | [29 empty] | 40 | FALSE | 2026-07-03 | Om Construction
247 | 42/3 | DA+0 |  | 1 | 0247 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 09.07.2026 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 256.4 | [29 empty] | 25 | FALSE | 2026-07-03 | Om Construction
248 | 42/4 | DA+0 |  | 1 | 0248 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 403.8 | [29 empty] | 39 | FALSE | 2026-07-03 | Om Construction
249 | 42/5 | DA+9 |  | 1 | 0249 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 09.07.2026 | Company Gang | [20 empty] | DA | 9 | DA+9
|  |  | 396.7 | [29 empty] | 39 | FALSE | 2026-07-03 | Om Construction
250 | 42/6 | DA+0 |  | 1 | 0250 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 403.9 | [29 empty] | 39 | FALSE | 2026-07-03 | Om Construction
251 | 43/0 | DB1+0 |  | 1 | 0251 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 346 | [29 empty] | 34 | FALSE | 2026-07-03 | Om Construction
252 | 43/1 | DA+3 |  | 1 | 0252 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 475.8 | [29 empty] | 47 | FALSE | 2026-07-03 | Om Construction
253 | 43/2 | DA+0 |  | 1 | 0253 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 363.7 | [29 empty] | 35 | FALSE | 2026-07-03 | Om Construction
254 | 43/3 | DA+0 |  | 1 | 0254 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 431.8 | [29 empty] | 42 | FALSE | 2026-07-03 | Om Construction
255 | 43/4 | DA+3 |  | 1 | 0255 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 405.3 | [29 empty] | 40 | FALSE | 2026-07-03 | Om Construction
256 | 43/5 | DA+3 |  | 1 | 0256 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 427.8 | [29 empty] | 42 | FALSE | 2026-07-03 | Om Construction
257 | 43/6 | DA+3 |  | 1 | 0257 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 389.8 | [29 empty] | 38 | FALSE | 2026-07-03 | Om Construction
258 | 43/7 | DA+3 |  | 1 | 0258 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 449.5 | [29 empty] | 44 | FALSE | 2026-07-03 | Om Construction
259 | 43/8 | DA+9 |  | 1 | 0259 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 388 | [29 empty] | 38 | FALSE | 2026-07-03 | Om Construction
260 | 43/9 | DA+9 |  | 1 | 0260 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 346.3 | [29 empty] | 34 | FALSE | 2026-07-03 | Om Construction
261 | 43/10 | DA+3 |  | 1 | 0261 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 444.8 | [29 empty] | 43 | FALSE | 2026-07-03 | Om Construction
262 | 43/11 | DA+3 |  | 1 | 0262 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 383.9 | [29 empty] | 37 | FALSE | 2026-07-03 | Om Construction
263 | 44/0 | DB1+3 |  | 1 | 0263 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 3 | DB+3
|  |  | 384.3 | [30 empty] | TRUE
264 | 44/1 | DA+0 |  | 1 | 0264 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 359 | [30 empty] | TRUE
265 | 44/2 | DA+0 |  | 1 | 0265 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 334 | [30 empty] | TRUE
266 | 44/3 | DA+0 |  | 1 | 0266 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 395 | [30 empty] | TRUE
267 | 44/4 | DA+9 |  | 1 | 0267 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 355 | [30 empty] | TRUE
268 | 44/5 | DA+9 |  | 1 | 0268 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 485 | [30 empty] | TRUE
269 | 44/6 | DB1+3 |  | 1 | 0269 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 3 | DB+3
|  |  | 473 | [30 empty] | TRUE
270 | 44/7 | DA+9 |  | 1 | 0270 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 367 | [30 empty] | TRUE
271 | 44/8 | DCT+0 |  | 1 | 0271 | R | B | Y | R | B | Y | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 430 | [30 empty] | TRUE
272 | 44/9 | DA+9 |  | 1 | 0272 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 365 | [30 empty] | TRUE
273 | 44/10 | DB1+9 |  | 1 | 0273 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 9 | DB+9
|  |  | 428 | [30 empty] | TRUE
274 | 44/11 | DA+0 |  | 1 | 0274 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-25 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 327.2 | [30 empty] | TRUE
275 | 45/0 | DC2+0 |  | 1 | 0275 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 294.92 | [30 empty] | TRUE
276 | 45/1 | DA+9 |  | 1 | 0276 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-25 | Company Gang | [20 empty] | DA | 9 | DA+9
|  |  | 406.54 | [23 empty] | 1 | 2026-06-30 | Om Construction |  |  |  |  | TRUE
277 | 46/0 | DD60+25 |  | 1 | 0277 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [8 empty] | 1 | 2026-03-27 | Om Construction | [5 empty] | 1 | 2026-04-05 | Om Construction | 46.074 | [5 empty] | DD | 25 | DD+25
|  |  | 199.08 | [23 empty] | 1 | 2026-06-30 | Om Construction |  |  |  |  | TRUE
278 | 47/0 | DD60+25 |  | 1 | 0278 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [8 empty] | 1 | 2026-03-27 | Om Construction | [5 empty] | 1 | 2026-04-06 | Om Construction | 46.074 | [5 empty] | DD | 25 | DD+25
|  |  | 441.2 | [23 empty] | 1 | 2026-06-30 | Om Construction |  |  |  |  | TRUE
279 | 47/1 | DA+3 |  | 1 | 0279 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-25 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 365.93 | [30 empty] | TRUE
280 | 47/2 | DA+9 |  | 1 | 0280 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-25 | Company Gang | [20 empty] | DA | 9 | DA+9
|  |  | 417.4 | [30 empty] | TRUE
281 | 47/3 | DA+9 |  | 1 | 0281 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-25 | Company Gang | [20 empty] | DA | 9 | DA+9
|  |  | 358.4 | [30 empty] | TRUE
282 | 47/4 | DA+3 |  | 1 | 0282 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-25 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 461.2 | [30 empty] | TRUE
283 | 47/5 | DA+0 |  | 1 | 0283 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-23 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 377.3 | [30 empty] | TRUE
284 | 47/6 | DA+3 |  | 1 | 0284 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-06-30 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 431.5 | [30 empty] | TRUE
285 | 47/7 | DA+3 |  | 1 | 0285 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-06-30 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 398.8 | [30 empty] | TRUE
286 | 47/8 | DA+0 |  | 1 | 0286 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-23 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 405.9 | [30 empty] | TRUE
287 | 47/9 | DA+3 |  | 1 | 0287 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-23 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 433.7 | [30 empty] | TRUE
288 | 47/10 | DA+6 |  | 1 | 0288 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-23 | Company Gang | [20 empty] | DA | 6 | DA+6
|  |  | 386.2 | [30 empty] | TRUE
289 | 48/0 | DC2+0 |  | 1 | 0289 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 428.9 | [30 empty] | TRUE
290 | 48/1 | DA+9 |  | 1 | 0290 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-26 | Company Gang | [20 empty] | DA | 9 | DA+9
|  |  | 402.9 | [30 empty] | TRUE
291 | 49/0 | DD45+0 |  | 1 | 0291 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DD | 0 | DD+0
|  |  | 379.1 | [30 empty] | TRUE
292 | 49/1 | DA+0 |  | 1 | 0292 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-26 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 386.6 | [30 empty] | TRUE
293 | 49/2 | DA+3 |  | 1 | 0293 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-26 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 390 | [30 empty] | TRUE
294 | 49/3 | DA+3 |  | 1 | 0294 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-26 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 421.7 | [30 empty] | TRUE
295 | 49/4 | DA+3 |  | 1 | 0295 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-26 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 396.6 | [30 empty] | TRUE
296 | 49/5 | DA+3 |  | 1 | 0296 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-26 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 412.8 | [30 empty] | TRUE
297 | 49/6 | DA+0 |  | 1 | 0297 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-26 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 340.2 | [30 empty] | TRUE
298 | 49/7 | DA+0 |  | 1 | 0298 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-26 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 500.2 | [30 empty] | TRUE
299 | 50/0 | DB2+0 |  | 1 | 0299 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 0 | DB+0
|  |  | 469.1 | [30 empty] | TRUE
300 | 50/1 | DA+6 |  | 1 | 0300 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-29 | Company Gang | [20 empty] | DA | 6 | DA+6
|  |  | 367.1 | [30 empty] | TRUE
301 | 50/2 | DA+9 |  | 1 | 0301 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-29 | Company Gang | [20 empty] | DA | 9 | DA+9
|  |  | 470.4 | [30 empty] | TRUE
302 | 50/3 | DA+6 |  | 1 | 0302 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-29 | Company Gang | [20 empty] | DA | 6 | DA+6
|  |  | 354.8 | [30 empty] | TRUE
303 | 50/4 | DA+9 |  | 1 | 0303 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-29 | Company Gang | [20 empty] | DA | 9 | DA+9
|  |  | 442.1 | [30 empty] | TRUE
304 | 50/5 | DA+9 |  | 1 | 0304 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-29 | Company Gang | [20 empty] | DA | 9 | DA+9
|  |  | 364.4 | [30 empty] | TRUE
305 | 50/6 | DA+9 |  | 1 | 0305 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 470.8 | [30 empty] | TRUE
306 | 50/7 | DA+0 |  | 1 | 0306 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-30 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 345 | [30 empty] | TRUE
307 | 50/8 | DA+9 |  | 1 | 0307 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-30 | Company Gang | [20 empty] | DA | 9 | DA+9
|  |  | 364.4 | [30 empty] | TRUE
308 | 50/9 | DA+0 |  | 1 | 0308 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-30 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 394.6 | [30 empty] | TRUE
309 | 50/10 | DA+0 |  | 1 | 0309 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-25 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 401.4 | [30 empty] | TRUE
310 | 51/0 | DC2+0 |  | 1 | 0310 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 356.6 | [30 empty] | TRUE
311 | 51/1 | DA+0 |  | 1 | 0311 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-25 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 307.1 | [30 empty] | TRUE
312 | 51/2 | DA+0 |  | 1 | 0312 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-25 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 385 | [30 empty] | TRUE
313 | 52/0 | DC2+0 |  | 1 | 0313 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 0 | DC+0
|  |  | 402 | [30 empty] | TRUE
314 | 52/1 | DA+6 |  | 1 | 0314 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 402.6 | [30 empty] | TRUE
315 | 52/2 | DA+6 |  | 1 | 0315 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 437 | [30 empty] | TRUE
316 | 52/3 | DA+9 |  | 1 | 0316 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 393.8 | [30 empty] | TRUE
317 | 52/4 | DA+9 |  | 1 | 0317 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 447 | [30 empty] | TRUE
318 | 52/5 | DA+9 |  | 1 | 0318 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 373 | [30 empty] | TRUE
319 | 52/6 | DA+6 |  | 1 | 0319 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 406.8 | [30 empty] | TRUE
320 | 52/7 | DA+3 |  | 1 | 0320 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 433 | [30 empty] | TRUE
321 | 52/8 | DA+6 |  | 1 | 0321 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 399.7 | [30 empty] | TRUE
322 | 52/9 | DA+3 |  | 1 | 0322 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 384.1 | [30 empty] | TRUE
323 | 52/10 | DA+9 |  | 1 | 0323 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 455.9 | [30 empty] | TRUE
324 | 53/0 | DB2+9 |  | 1 | 0324 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 9 | DB+9
|  |  | 433.2 | [30 empty] | TRUE
325 | 53/1 | DA+9 |  | 1 | 0325 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 407.4 | [30 empty] | TRUE
326 | 53/2 | DA+0 |  | 1 | 0326 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 394.5 | [30 empty] | TRUE
327 | 53/3 | DA+6 |  | 1 | 0327 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 410.1 | [30 empty] | TRUE
328 | 53/4 | DA+0 |  | 1 | 0328 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 428.1 | [30 empty] | TRUE
329 | 53/5 | DA+3 |  | 1 | 0329 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 406.6 | [30 empty] | TRUE
330 | 53/6 | DA+6 |  | 1 | 0330 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 411.3 | [30 empty] | TRUE
331 | 53/7 | DA+3 |  | 1 | 0331 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 427.8 | [30 empty] | TRUE
332 | 53/8 | DA+3 |  | 1 | 0332 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 371.3 | [30 empty] | TRUE
333 | 54/0 | DB1+6 |  | 1 | 0333 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 6 | DB+6
|  |  | 365.1 | [30 empty] | TRUE
334 | 54/1 | DA+3 |  | 1 | 0334 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 381 | [30 empty] | TRUE
335 | 54/2 | DA+3 |  | 1 | 0335 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 417 | [30 empty] | TRUE
336 | 54/3 | DA+6 |  | 1 | 0336 | Y | R | B | Y | R | B | 1 | 11.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 423.3 | [30 empty] | TRUE
337 | 54/4 | DA+9 |  | 1 | 0337 | Y | R | B | Y | R | B | 1 | 11.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 401 | [30 empty] | TRUE
338 | 54/5 | DA+9 |  | 1 | 0338 | Y | R | B | Y | R | B | 1 | 10.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 424 | [30 empty] | TRUE
339 | 55/0 | DB1+6 |  | 1 | 0339 | Y | R | B | Y | R | B | 1 | 10.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 | [25 empty] | DB | 6 | DB+6
|  |  | 404.9 | [30 empty] | TRUE
340 | 55/1 | DA+0 |  | 1 | 0340 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 343.1 | [30 empty] | TRUE
341 | 55/2 | DA+0 |  | 1 | 0341 | Y | R | B | Y | R | B | 1 | 10.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 357.7 | [30 empty] | TRUE
342 | 55/3 | DA+0 |  | 1 | 0342 | Y | R | B | Y | R | B | 1 | 09.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 365.2 | [30 empty] | TRUE
343 | 55/4 | DA+0 |  | 1 | 0343 | Y | R | B | Y | R | B | 1 | 09.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 350.1 | [30 empty] | TRUE
344 | 55/5 | DA+0 |  | 1 | 0344 | Y | R | B | Y | R | B | 1 | 09.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 357.7 | [24 empty] | 2026-06-30 | Om Construction |  |  |  |  | TRUE
345 | 55/6 | DA+0 |  | 1 | 0345 | Y | R | B | Y | R | B | 1 | 09.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 337.8 | [24 empty] | 2026-06-30 | Om Construction |  |  |  |  | TRUE
346 | 55/7 | DA+0 |  | 1 | 0346 | Y | R | B | Y | R | B | 1 | 09.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 341.22 | [24 empty] | 2026-06-30 | Om Construction |  |  |  |  | TRUE
347 | 55/8 | DA+6 |  | 1 | 0347 | Y | R | B | Y | R | B | 1 | 07.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 460.49 | [23 empty] | 1 | 2026-06-30 | Om Construction |  |  |  |  | TRUE
348 | 56/0 | DD60+25 |  | 1 | 0348 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [8 empty] | 1 | 2026-03-28 | Om Construction | [5 empty] | 1 | 2026-04-03 | Om Construction | 46.074 | [5 empty] | DD | 25 | DD+25
|  |  | 219.76 | [23 empty] | 1 | 2026-06-30 | Om Construction |  |  |  |  | TRUE
349 | 57/0 | DD60+25 |  | 1 | 0349 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [8 empty] | 1 | 2026-03-28 | Om Construction | [5 empty] | 1 | 2026-04-04 | Om Construction | 46.074 | [5 empty] | DD | 25 | DD+25
|  |  | 461.1 | [23 empty] | 1 | 2026-06-30 | Om Construction |  |  |  |  | TRUE
350 | 57/1 | DA+0 |  | 1 | 0350 | Y | R | B | Y | R | B | 1 | 07.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 355.5 | [23 empty] | 1 | 2026-06-30 | Om Construction |  |  |  |  | TRUE
351 | 57/2 | DA+3 |  | 1 | 0351 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 405.4 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
352 | 57/3 | DA+0 |  | 1 | 0352 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 418.2 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
353 | 57/4 | DA+0 |  | 1 | 0353 | Y | R | B | Y | R | B | 1 | 07.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 416.8 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
354 | 57/5 | DA+3 |  | 1 | 0354 | Y | R | B | Y | R | B | 1 | 06.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 395 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
355 | 57/6 | DA+3 |  | 1 | 0355 | Y | R | B | Y | R | B | 1 | 06.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 401.8 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
356 | 57/7 | DA+3 |  | 1 | 0356 | Y | R | B | Y | R | B | 1 | 06.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 433.9 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
357 | 58/0 | DC1+3 |  | 1 | 0357 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [25 empty] | DC | 3 | DC+3
|  |  | 238.9 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
358 | 59/0 | DC2+0 |  | 1 | 0358 | Y | R | B | Y | R | B | 1 | 08.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 08.06.26 | Shri Balaji Const. | 1 | 08.06.26 | Shri Balaji Const. | [23 empty] | DC | 0 | DC+0
|  |  | 411.3 | [23 empty] | 1 | [6 empty] | TRUE
359 | 59/1 | DA+3 |  | 1 | 0359 | Y | R | B | Y | R | B | 1 | 08.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 08.06.26 | Shri Balaji Const. | 1 | 08.06.26 | Shri Balaji Const. | 1 | 2026-06-12 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 418.2 | [23 empty] | 1 | [6 empty] | TRUE
360 | 59/2 | DA+3 |  | 1 | 0360 | Y | R | B | Y | R | B | 1 | 08.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 08.06.26 | Shri Balaji Const. | 1 | 08.06.26 | Shri Balaji Const. | 1 | 2026-06-12 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 412.3 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
361 | 59/3 | DA+3 |  | 1 | 0361 | Y | R | B | Y | R | B | 1 | 08.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 08.06.26 | Shri Balaji Const. | 1 | 08.06.26 | Shri Balaji Const. | 1 | 2026-06-12 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 421 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
362 | 59/4 | DA+3 |  | 1 | 0362 | Y | R | B | Y | R | B | 1 | 08.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 08.06.26 | Shri Balaji Const. | 1 | 08.06.26 | Shri Balaji Const. | 1 | 2026-06-12 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 419.7 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
363 | 59/5 | DA+3 |  | 1 | 0363 | Y | R | B | Y | R | B | 1 | 08.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 08.06.26 | Shri Balaji Const. | 1 | 08.06.26 | Shri Balaji Const. | 1 | 2026-06-12 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 419.1 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
364 | 59/6 | DA+3 |  | 1 | 0364 | Y | R | B | Y | R | B | 1 | 08.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 08.06.26 | Shri Balaji Const. | 1 | 08.06.26 | Shri Balaji Const. | 1 | 2026-06-13 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 408.8 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
365 | 59/7 | DA+3 |  | 1 | 0365 | Y | R | B | Y | R | B | 1 | 10.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 10.06.26 | Shri Balaji Const. | 1 | 10.06.26 | Shri Balaji Const. | 1 | 2026-06-13 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 426.9 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
366 | 59/8 | DB1+3 |  | 1 | 0366 | Y | R | B | Y | R | B | 1 | 10.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 10.06.26 | Shri Balaji Const. | 1 | 10.06.26 | Shri Balaji Const. | [23 empty] | DB | 3 | DB+3
|  |  | 434.7 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
367 | 59/9 | DA+3 |  | 1 | 0367 | Y | R | B | Y | R | B | 1 | 10.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 10.06.26 | Shri Balaji Const. | 1 | 10.06.26 | Shri Balaji Const. | 1 | 2026-06-13 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 400.8 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
368 | 59/10 | DA+0 |  | 1 | 0368 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-06-13 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 436.3 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
369 | 59/11 | DA+6 |  | 1 | 0369 | Y | R | B | Y | R | B | 1 | 10.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 10.06.26 | Shri Balaji Const. | 1 | 10.06.26 | Shri Balaji Const. | 1 | 2026-06-13 | Company Gang | [20 empty] | DA | 6 | DA+6
|  |  | 393.1 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
370 | 59/12 | DA+6 |  | 1 | 0370 | Y | R | B | Y | R | B | 1 | 10.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 10.06.26 | Shri Balaji Const. | 1 | 10.06.26 | Shri Balaji Const. | 1 | 2026-06-14 | Company Gang | [20 empty] | DA | 6 | DA+6
|  |  | 447.4 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
371 | 59/13 | DA+3 |  | 1 | 0371 | Y | R | B | Y | R | B | 1 | 11.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 11.06.26 | Shri Balaji Const. | 1 | 11.06.26 | Shri Balaji Const. | 1 | 2026-06-14 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 391.1 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
372 | 59/14 | DA+6 |  | 1 | 0372 | Y | R | B | Y | R | B | 1 | 11.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 11.06.26 | Shri Balaji Const. | 1 | 11.06.26 | Shri Balaji Const. | 1 | 2026-06-14 | Company Gang | [20 empty] | DA | 6 | DA+6
|  |  | 448.6 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
373 | 59/15 | DA+6 |  | 1 | 0373 | Y | R | B | Y | R | B | 1 | 11.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 11.06.26 | Shri Balaji Const. | 1 | 11.06.26 | Shri Balaji Const. | 1 | 2026-06-14 | Company Gang | [20 empty] | DA | 6 | DA+6
|  |  | 388 | [23 empty] | 1 | [6 empty] | TRUE
374 | 59/16 | DA+9 |  | 1 | 0374 | Y | R | B | Y | R | B | 1 | 11.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 11.06.26 | Shri Balaji Const. | 1 | 11.06.26 | Shri Balaji Const. | 1 | 2026-06-14 | Company Gang | [20 empty] | DA | 9 | DA+9
|  |  | 438 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
375 | 60/0 | DC1+0 |  | 1 | 0375 | Y | R | B | Y | R | B | 1 | 11.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 11.06.26 | Shri Balaji Const. | 1 | 11.06.26 | Shri Balaji Const. | [23 empty] | DC | 0 | DC+0
|  |  | 413.8 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
376 | 60/1 | DA+6 |  | 1 | 0376 | Y | R | B | Y | R | B | 1 | 11.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 11.06.26 | Shri Balaji Const. | 1 | 11.06.26 | Shri Balaji Const. | 1 | 2026-06-14 | Company Gang | [20 empty] | DA | 6 | DA+6
|  |  | 424.2 | [23 empty] | 1 | 2026-03-18 | Om Construction |  |  |  |  | TRUE
377 | 60/2 | DA+3 |  | 1 | 0377 | Y | R | B | Y | R | B | 1 | 24.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 24.06.26 | Shri Balaji Const. | 1 | 24.06.26 | Shri Balaji Const. | 1 | 2026-06-15 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 414.5 | [23 empty] | 1 | 2026-03-31 | Om Construction |  |  |  |  | TRUE
378 | 60/3 | DA+3 |  | 1 | 0378 | Y | R | B | Y | R | B | 1 | 24.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 24.06.26 | Shri Balaji Const. | 1 | 24.06.26 | Shri Balaji Const. | 1 | 2026-06-15 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 425.6 | [23 empty] | 1 | 2026-03-31 | Om Construction |  |  |  |  | TRUE
379 | 60/4 | DA+3 |  | 1 | 0379 | Y | R | B | Y | R | B | 1 | 24.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 24.06.26 | Shri Balaji Const. | 1 | 24.06.26 | Shri Balaji Const. | 1 | 2026-06-15 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 412.3 | [23 empty] | 1 | 2026-03-31 | Om Construction |  |  |  |  | TRUE
380 | 60/5 | DA+3 |  | 1 | 0380 | Y | R | B | Y | R | B | 1 | 24.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 24.06.26 | Shri Balaji Const. | 1 | 24.06.26 | Shri Balaji Const. | 1 | 2026-06-15 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 374.1 | [23 empty] | 1 | 2026-03-31 | Om Construction |  |  |  |  | TRUE
381 | 60/6 | DA+0 |  | 1 | 0381 | Y | R | B | Y | R | B | 1 | 25.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 25.06.26 | Shri Balaji Const. | 1 | 25.06.26 | Shri Balaji Const. | 1 | 2026-06-15 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 410.1 | [23 empty] | 1 | 2026-03-31 | Om Construction |  |  |  |  | TRUE
382 | 60/7 | DA+3 |  | 1 | 0382 | Y | R | B | Y | R | B | 1 | 25.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 25.06.26 | Shri Balaji Const. | 1 | 25.06.26 | Shri Balaji Const. | 1 | 2026-06-16 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 400.4 | [23 empty] | 1 | 2026-03-31 | Om Construction |  |  |  |  | TRUE
383 | 60/8 | DA+0 |  | 1 | 0383 | Y | R | B | Y | R | B | 1 | 25.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 25.06.26 | Shri Balaji Const. | 1 | 25.06.26 | Shri Balaji Const. | 1 | 2026-06-16 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 409.2 | [23 empty] | 1 | 2026-03-31 | Om Construction |  |  |  |  | TRUE
384 | 60/9 | DA+3 |  | 1 | 0384 | Y | R | B | Y | R | B | 1 | 25.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 25.06.26 | Shri Balaji Const. | 1 | 25.06.26 | Shri Balaji Const. | 1 | 2026-06-16 | Company Gang | [20 empty] | DA | 3 | DA+3
|  |  | 401 | [23 empty] | 1 | 2026-03-31 | Om Construction |  |  |  |  | TRUE
385 | 60/10 | DA+0 |  | 1 | 0385 | Y | R | B | Y | R | B | 1 | 25.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 25.06.26 | Shri Balaji Const. | 1 | 25.06.26 | Shri Balaji Const. | 1 | 2026-06-16 | Company Gang | [20 empty] | DA | 0 | DA+0
|  |  | 394.5 | [23 empty] | 1 | 2026-03-31 | Om Construction |  |  |  |  | TRUE
386 | 60/11 | DA+3 |  | 1 | 0386 | Y | R | B | Y | R | B | 1 | 25.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 25.06.26 | Shri Balaji Const. | 1 | 25.06.26 | Shri Balaji Const. | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 397.9 | [23 empty] | 1 | 2026-03-31 | Om Construction |  |  |  |  | TRUE
387 | 61/0 | DB2+0 |  | 1 | 0387 | Y | R | B | Y | R | B | 1 | 26.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 26.06.26 | Shri Balaji Const. | 1 | 26.06.26 | Shri Balaji Const. | [23 empty] | DB | 0 | DB+0
|  |  | 405.7 | [23 empty] | 1 | 2026-03-31 | Om Construction |  |  |  |  | TRUE
388 | 61/1 | DA+6 |  | 1 | 0388 | Y | R | B | Y | R | B | 1 | 26.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 26.06.26 | Shri Balaji Const. | 1 | 26.06.26 | Shri Balaji Const. | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 433.2 | [23 empty] | 1 | 2026-03-31 | Om Construction |  |  |  |  | TRUE
389 | 61/2 | DA+6 |  | 1 | 0389 | Y | R | B | Y | R | B | 1 | 26.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 26.06.26 | Shri Balaji Const. | 1 | 26.06.26 | Shri Balaji Const. | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 400.9 | [23 empty] | 1 | 2026-03-31 | Om Construction |  |  |  |  | TRUE
390 | 61/3 | DA+6 |  | 1 | 0390 | Y | R | B | Y | R | B | 1 | 26.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 26.06.26 | Shri Balaji Const. | 1 | 26.06.26 | Shri Balaji Const. | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 427 | [23 empty] | 1 | 2026-03-31 | Om Construction |  |  |  |  | TRUE
391 | 61/4 | DA+3 |  | 1 | 0391 | Y | R | B | Y | R | B | 1 | 26.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 26.06.26 | Shri Balaji Const. | 1 | 26.06.26 | Shri Balaji Const. | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 413.9 | [23 empty] | 1 | 2026-06-22 | Om Construction |  |  |  |  | TRUE
392 | 61/5 | DA+3 |  | 1 | 0392 | Y | R | B | Y | R | B | 1 | 27.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 27.06.26 | Shri Balaji Const. | 1 | 27.06.26 | Shri Balaji Const. | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 426.4 | [23 empty] | 1 | 2026-06-22 | Om Construction |  |  |  |  | TRUE
393 | 61/6 | DA+3 |  | 1 | 0393 | Y | R | B | Y | R | B | 1 | 27.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 27.06.26 | Shri Balaji Const. | 1 | 27.06.26 | Shri Balaji Const. | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 411.5 | [23 empty] | 1 | 2026-06-22 | Om Construction |  |  |  |  | TRUE
394 | 61/7 | DA+9 |  | 1 | 0394 | Y | R | B | Y | R | B | 1 | 27.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 27.06.26 | Shri Balaji Const. | 1 | 27.06.26 | Shri Balaji Const. | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 376.3 | [23 empty] | 1 | 2026-06-22 | Om Construction |  |  |  |  | TRUE
395 | 61/8 | DA+6 |  | 1 | 0395 | Y | R | B | Y | R | B | 1 | 27.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 27.06.26 | Shri Balaji Const. | 1 | 27.06.26 | Shri Balaji Const. | 1 | [22 empty] | DA | 6 | DA+6
|  |  | 433.4 | [23 empty] | 1 | 2026-06-22 | Om Construction |  |  |  |  | TRUE
396 | 61/9 | DA+0 |  | 1 | 0396 | Y | R | B | Y | R | B | 1 | 27.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 27.06.26 | Shri Balaji Const. | 1 | 27.06.26 | Shri Balaji Const. | 1 | [22 empty] | DA | 0 | DA+0
|  |  | 405.6 | [23 empty] | 1 | 2026-06-22 | Om Construction |  |  |  |  | TRUE
397 | 61/10 | DA+9 |  | 1 | 0397 | Y | R | B | Y | R | B | 1 | 27.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 27.06.26 | Shri Balaji Const. | 1 | 27.06.26 | Shri Balaji Const. | 1 | [22 empty] | DA | 9 | DA+9
|  |  | 434.3 | [23 empty] | 1 | 2026-06-22 | Om Construction |  |  |  |  | TRUE
398 | 62/0 | DB2+0 |  | 1 | 0398 | Y | R | B | Y | R | B | 1 | 28.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 28.06.26 | Shri Balaji Const. | 1 | 28.06.26 | Shri Balaji Const. | [23 empty] | DB | 0 | DB+0
|  |  | 418 | [23 empty] | 1 | 2026-06-22 | Om Construction |  |  |  |  | TRUE
399 | 62/1 | DA+3 |  | 1 | 0399 | Y | R | B | Y | R | B | 1 | 28.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 28.06.26 | Shri Balaji Const. | 1 | 28.06.26 | Shri Balaji Const. | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 386 | [23 empty] | 1 | 2026-06-22 | Om Construction |  |  |  |  | TRUE
400 | 62/2 | DA+3 |  | 1 | 0400 | Y | R | B | Y | R | B | 1 | 28.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 28.06.26 | Shri Balaji Const. | 1 | 28.06.26 | Shri Balaji Const. | 1 | [22 empty] | DA | 3 | DA+3
|  |  | 400 | [23 empty] | 1 | 2026-06-22 | Om Construction |  |  |  |  | TRUE
401 | 62/3 | DA+0 |  | 1 | 0401 | Y | R | B | Y | R | B | 1 | 28.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 28.06.26 | Shri Balaji Const. | 1 | 28.06.26 | Shri Balaji Const. | 1 | [6 empty] | 2026-07-04 | Om Construction | [14 empty] | DA | 0 | DA+0
|  |  | 401 | [23 empty] | 1 | 2026-06-22 | Om Construction |  |  |  |  | TRUE
402 | 62/4 | DA+3 |  | 1 | 0402 | Y | R | B | Y | R | B | 1 | 28.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 28.06.26 | Shri Balaji Const. | 1 | 28.06.26 | Shri Balaji Const. | 1 | [6 empty] | 2026-07-04 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 403 | [23 empty] | 1 | 2026-06-22 | Om Construction |  |  |  |  | TRUE
403 | 62/5 | DA+0 |  | 1 | 0403 | Y | R | B | Y | R | B | 1 | 28.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 28.06.26 | Shri Balaji Const. | 1 | 28.06.26 | Shri Balaji Const. | 1 | [6 empty] | 2026-07-04 | Om Construction | [14 empty] | DA | 0 | DA+0
|  |  | 404 | [23 empty] | 1 | 2026-06-22 | Om Construction |  |  |  |  | TRUE
404 | 62/6 | DA+3 |  | 1 | 0404 | Y | R | B | Y | R | B | 1 | 29.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 29.06.26 | Shri Balaji Const. | 1 | 29.06.26 | Shri Balaji Const. | 1 | [5 empty] | 1 | 2026-06-28 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 423 | [23 empty] | 1 | 2026-06-22 | Om Construction |  |  |  |  | TRUE
405 | 62/7 | DA+3 |  | 1 | 0405 | Y | R | B | Y | R | B | 1 | 29.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 29.06.26 | Shri Balaji Const. | 1 | 29.06.26 | Shri Balaji Const. | 1 | [5 empty] | 1 | 2026-06-28 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 409 | [23 empty] | 1 | 2026-06-22 | Om Construction |  |  |  |  | TRUE
406 | 62/8 | DA+0 |  | 1 | 0406 | Y | R | B | Y | R | B | 1 | 29.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 29.06.26 | Shri Balaji Const. | 1 | 29.06.26 | Shri Balaji Const. | 1 | [5 empty] | 1 | 2026-06-28 | Om Construction | [14 empty] | DA | 0 | DA+0
|  |  | 409 | [23 empty] | 1 | 2026-06-23 | Om Construction |  |  |  |  | TRUE
407 | 62/9 | DA+3 |  | 1 | 0407 | Y | R | B | Y | R | B | 1 | 29.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 29.06.26 | Shri Balaji Const. | 1 | 29.06.26 | Shri Balaji Const. | 1 | [5 empty] | 1 | 2026-06-28 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 411 | [23 empty] | 1 | 2026-06-23 | Om Construction |  |  |  |  | TRUE
408 | 62/10 | DA+0 |  | 1 | 0408 | Y | R | B | Y | R | B | 1 | 29.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 29.06.26 | Shri Balaji Const. | 1 | 29.06.26 | Shri Balaji Const. | 1 | [5 empty] | 1 | 2026-06-28 | Om Construction | [14 empty] | DA | 0 | DA+0
|  |  | 413 | [23 empty] | 1 | 2026-06-23 | Om Construction |  |  |  |  | TRUE
409 | 62/11 | DA+3 |  | 1 | 0409 | Y | R | B | Y | R | B | 1 | 30.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 30.06.26 | Shri Balaji Const. | 1 | 30.06.26 | Shri Balaji Const. | 1 | [5 empty] | 1 | 2026-06-28 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 386.1 | [23 empty] | 1 | 2026-06-23 | Om Construction |  |  |  |  | TRUE
410 | 63/0 | DC1+0 |  | 1 | 0410 | Y | R | B | Y | R | B | 1 | 30.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 30.06.26 | Shri Balaji Const. | 1 | 30.06.26 | Shri Balaji Const. | [6 empty] | 1 | 2026-06-27 | Om Construction | [14 empty] | DC | 0 | DC+0
|  |  | 400 | [23 empty] | 1 | 2026-06-23 | Om Construction |  |  |  |  | TRUE
411 | 63/1 | DA+3 |  | 1 | 0411 | Y | R | B | Y | R | B | 1 | 30.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 30.06.26 | Shri Balaji Const. | 1 | 30.06.26 | Shri Balaji Const. | 1 | [5 empty] | 1 | 2026-06-27 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 416 | [23 empty] | 1 | 2026-06-23 | Om Construction |  |  |  |  | TRUE
412 | 63/2 | DA+0 |  | 1 | 0412 | Y | R | B | Y | R | B | 1 | 30.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 30.06.26 | Shri Balaji Const. | 1 | 30.06.26 | Shri Balaji Const. | 1 | [5 empty] | 1 | 2026-06-27 | Om Construction | [14 empty] | DA | 0 | DA+0
|  |  | 411 | [23 empty] | 1 | 2026-06-23 | Om Construction |  |  |  |  | TRUE
413 | 63/3 | DA+3 |  | 1 | 0413 | Y | R | B | Y | R | B | 1 | 30.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 30.06.26 | Shri Balaji Const. | 1 | 30.06.26 | Shri Balaji Const. | 1 | [5 empty] | 1 | 2026-06-27 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 399 | [23 empty] | 1 | 2026-06-23 | Om Construction |  |  |  |  | TRUE
414 | 63/4 | DA+0 |  | 1 | 0414 | Y | R | B | Y | R | B | 1 | 30.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 30.06.26 | Shri Balaji Const. | 1 | 30.06.26 | Shri Balaji Const. | 1 | [5 empty] | 1 | 2026-06-27 | Om Construction | [14 empty] | DA | 0 | DA+0
|  |  | 413 | [23 empty] | 1 | 2026-06-23 | Om Construction |  |  |  |  | TRUE
415 | 63/5 | DA+3 |  | 1 | 0415 | Y | R | B | Y | R | B | 1 | 30.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 30.06.26 | Shri Balaji Const. | 1 | 30.06.26 | Shri Balaji Const. | 1 | [5 empty] | 1 | 2026-06-27 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 426 | [23 empty] | 1 | 2026-06-23 | Om Construction |  |  |  |  | TRUE
416 | 63/6 | DA+3 |  | 1 | 0416 | Y | R | B | Y | R | B | 1 | 01.07.26 | Shri Balaji Const. | I | II | 1 | 1 | 01.07.26 | Shri Balaji Const. | 1 | 01.07.26 | Shri Balaji Const. | 1 | [5 empty] | 1 | 2026-06-27 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 413 | [23 empty] | 1 | 2026-06-23 | Om Construction |  |  |  |  | TRUE
417 | 63/7 | DA+3 |  | 1 | 0417 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-06-27 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 425 | [23 empty] | 1 | 2026-06-23 | Om Construction |  |  |  |  | TRUE
418 | 63/8 | DA+3 |  | 1 | 0418 | Y | R | B | Y | R | B | 1 | 01.07.26 | Shri Balaji Const. | I | II | 1 | 1 | 01.07.26 | Shri Balaji Const. | 1 | 01.07.26 | Shri Balaji Const. | 1 | [5 empty] | 1 | 2026-06-27 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 408.3 | [23 empty] | 1 | 2026-06-23 | Om Construction |  |  |  |  | TRUE
419 | 64/0 | DB2+0 |  | 1 | 0419 | Y | R | B | Y | R | B | 1 | 01.07.26 | Shri Balaji Const. | I | II | 1 | 1 | 01.07.26 | Shri Balaji Const. | 1 | 01.07.26 | Shri Balaji Const. | [6 empty] | 1 | 2026-06-26 | Om Construction | [14 empty] | DB | 0 | DB+0
|  |  | 375.1 | [23 empty] | 1 | 2026-06-23 | Om Construction |  |  |  |  | TRUE
420 | 64/1 | DA+0 |  | 1 | 0420 | Y | R | B | Y | R | B | 1 | 01.07.26 | Shri Balaji Const. | I | II | 1 | 1 | 01.07.26 | Shri Balaji Const. | 1 | 01.07.26 | Shri Balaji Const. | 1 | [5 empty] | 1 | 2026-06-26 | Om Construction | [14 empty] | DA | 0 | DA+0
|  |  | 408.7 | [23 empty] | 1 | 2026-06-23 | Om Construction |  |  |  |  | TRUE
421 | 64/2 | DA+3 |  | 1 | 0421 | Y | R | B | Y | R | B | 1 | 01.07.26 | Shri Balaji Const. | I | II | 1 | 1 | 01.07.26 | Shri Balaji Const. | 1 | 01.07.26 | Shri Balaji Const. | 1 | [5 empty] | 1 | 2026-06-26 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 410.7 | [23 empty] | 1 | 2026-06-23 | Om Construction |  |  |  |  | TRUE
422 | 64/3 | DA+0 |  | 1 | 0422 | Y | R | B | Y | R | B | 1 | 01.07.26 | Shri Balaji Const. | I | II | 1 | 1 | 01.07.26 | Shri Balaji Const. | 1 | 01.07.26 | Shri Balaji Const. | 1 | 2026-03-12 | Company Gang |  |  |  | 1 | 2026-06-26 | Om Construction | [14 empty] | DA | 0 | DA+0
|  |  | 408.2 | [23 empty] | 1 | 2026-06-24 | Om Construction |  |  |  |  | TRUE
423 | 64/4 | DA+3 |  | 1 | 0423 | Y | R | B | Y | R | B | 1 | 02.07.26 | Shri Balaji Const. | I | II | 1 | 1 | 02.07.26 | Shri Balaji Const. | 1 | 02.07.26 | Shri Balaji Const. | 1 | 2026-03-12 | Company Gang |  |  |  | 1 | 2026-06-25 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 426.2 | [23 empty] | 1 | 2026-06-24 | Om Construction |  |  |  |  | TRUE
424 | 64/5 | DA+3 |  | 1 | 0424 | Y | R | B | Y | R | B | 1 | 02.07.26 | Shri Balaji Const. | I | II | 1 | 1 | 02.07.26 | Shri Balaji Const. | 1 | 02.07.26 | Shri Balaji Const. | 1 | 2026-03-12 | Company Gang |  |  |  | 1 | 2026-06-25 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 407.7 | [23 empty] | 1 | 2026-06-24 | Om Construction |  |  |  |  | TRUE
425 | 64/6 | DA+0 |  | 1 | 0425 | Y | R | B | Y | R | B | 1 | 02.07.26 | Shri Balaji Const. | I | II | 1 | 1 | 02.07.26 | Shri Balaji Const. | 1 | 02.07.26 | Shri Balaji Const. | 1 | 2026-03-12 | Company Gang |  |  |  | 1 | 2026-06-25 | Om Construction | [14 empty] | DA | 0 | DA+0
|  |  | 401.6 | [23 empty] | 1 | 2026-06-24 | Om Construction |  |  |  |  | TRUE
426 | 64/7 | DA+3 |  | 1 | 0426 | Y | R | B | Y | R | B | 1 | 03.07.26 | Shri Balaji Const. | I | II | 1 | 1 | 03.07.26 | Shri Balaji Const. | 1 | 03.07.26 | Shri Balaji Const. | 1 | 2026-03-12 | Company Gang |  |  |  | 1 | 2026-06-25 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 425.5 | [23 empty] | 1 | 2026-06-24 | Om Construction |  |  |  |  | TRUE
427 | 64/8 | DA+3 |  | 1 | 0427 | Y | R | B | Y | R | B | 1 | 03.07.26 | Shri Balaji Const. | I | II | 1 | 1 | 03.07.26 | Shri Balaji Const. | 1 | 03.07.26 | Shri Balaji Const. | 1 | 2026-03-12 | Company Gang |  |  |  | 1 | 2026-06-25 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 414.4 | [23 empty] | 1 | 2026-06-24 | Om Construction |  |  |  |  | TRUE
428 | 64/9 | DA+3 |  | 1 | 0428 | Y | R | B | Y | R | B | 1 | 03.07.26 | Shri Balaji Const. | I | II | 1 | 1 | 03.07.26 | Shri Balaji Const. | 1 | 03.07.26 | Shri Balaji Const. | 1 | 2026-07-23 | Final Checking Gang |  |  |  | 1 | 2026-06-25 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 410.6 | [23 empty] | 1 | 2026-06-24 | Om Construction |  |  |  |  | TRUE
429 | 64/10 | DA+3 |  | 1 | 0429 | Y | R | B | Y | R | B | 1 | 03.07.26 | Shri Balaji Const. | I | II | 1 | 1 | 03.07.26 | Shri Balaji Const. | 1 | 03.07.26 | Shri Balaji Const. | 1 | 2026-07-23 | Final Checking Gang |  |  |  | 1 | 2026-06-25 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 428.4 | [23 empty] | 1 | 2026-06-24 | Om Construction |  |  |  |  | TRUE
430 | 64/11 | DA+3 |  | 1 | 0430 | Y | R | B | Y | R | B | 1 | 03.07.26 | Shri Balaji Const. | I | II | 1 | 1 | 03.07.26 | Shri Balaji Const. | 1 | 03.07.26 | Shri Balaji Const. | 1 | 2026-07-23 | Final Checking Gang |  |  |  | 1 | 2026-06-25 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 400.6 | [23 empty] | 1 | 2026-06-24 | Om Construction |  |  |  |  | TRUE
431 | 65/0 | DB1+0 |  | 1 | 0431 | Y | R | B | Y | R | B | 1 | 03.07.26 | Shri Balaji Const. | I | II | 1 | 1 | 03.07.26 | Shri Balaji Const. | 1 | 03.07.26 | Shri Balaji Const. | [6 empty] | 1 | 2026-06-24 | Om Construction | [14 empty] | DB | 0 | DB+0
|  |  | 395.4 | [23 empty] | 1 | 2026-06-24 | Om Construction |  |  |  |  | TRUE
432 | 65/1 | DA+0 |  | 1 | 0432 | Y | R | B | Y | R | B | 1 | 04.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-23 | Final Checking Gang |  |  |  | 1 | 2026-06-24 | Om Construction | [14 empty] | DA | 0 | DA+0
|  |  | 393.7 | [23 empty] | 1 | 2026-06-24 | Om Construction |  |  |  |  | TRUE
433 | 65/2 | DA+0 |  | 1 | 0433 | Y | R | B | Y | R | B | 1 | 04.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-23 | Final Checking Gang |  |  |  | 1 | 2026-06-24 | Om Construction | [14 empty] | DA | 0 | DA+0
|  |  | 403.7 | [23 empty] | 1 | 2026-06-24 | Om Construction |  |  |  |  | TRUE
434 | 65/3 | DA+3 |  | 1 | 0434 | Y | R | B | Y | R | B | 1 | 04.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-23 | Final Checking Gang |  |  |  | 1 | 2026-03-22 | Om Construction | [14 empty] | DA | 3 | DA+3
|  |  | 402.9 | [23 empty] | 1 | 2026-06-24 | Om Construction |  |  |  |  | TRUE
435 | 65/4 | DA+0 |  | 1 | 0435 | Y | R | B | Y | R | B | 1 | 04.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-07-23 | Final Checking Gang |  |  |  | 1 | 2026-03-22 | Om Construction | [14 empty] | DA | 0 | DA+0
|  |  | 376.4 | [23 empty] | 1 | 2026-06-24 | Om Construction |  |  |  |  | TRUE
436 | 65/5 | DA+0 |  | 1 | 0436 | Y | R | B | Y | R | B | 1 | 04.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-22 | Om Construction | [14 empty] | DA | 0 | DA+0
|  |  | 389.2 | [23 empty] | 1 | 2026-06-24 | Om Construction |  |  |  |  | TRUE
437 | 65/6 | DA+0 |  | 1 | 0437 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-22 | Om Construction | [14 empty] | DA | 0 | DA+0
|  |  | 397.6 | [23 empty] | 1 | 2026-06-24 | Om Construction |  |  |  |  | TRUE
438 | 65/7 | DA+0 |  | 1 | 0438 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-22 | Om Construction | [14 empty] | DA | 0 | DA+0
|  |  | 394.3 | [23 empty] | 1 | [6 empty] | TRUE
439 | 65/8 | DA+0 |  | 1 | 0439 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | [16 empty] | DA | 0 | DA+0
|  |  | 389 | [23 empty] | 1 | [6 empty] | TRUE
440 | 65/9 | DA+0 |  | 1 | 0440 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-22 | Om Construction | [14 empty] | DA | 0 | DA+0
|  |  | 379.1 | [23 empty] | 1 | [6 empty] | TRUE
441 | 65/10 | DA+0 |  | 1 | 0441 | Y | R | B | Y | R | B | 1 | 05.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-22 | Om Construction | [5 empty] | 1 | 2026-03-23 | Om Construction | 10.016 | [5 empty] | DA | 0 | DA+0
|  |  | 387.6 | [23 empty] | 1 | 2026-03-23 | Om Construction |  |  |  |  | TRUE
442 | 65/11 | DA+0 |  | 1 | 0442 | Y | R | B | Y | R | B | 1 | 05.07.26 | Shri Balaji Const. | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-23 | Om Construction | [5 empty] | 1 | 2026-03-23 | Om Construction | 10.016 | [5 empty] | DA | 0 | DA+0
|  |  | 426.9 | [23 empty] | 1 | 2026-03-23 | Om Construction |  |  |  |  | TRUE
443 | 66/0 | DC2+6 |  | 1 | 0443 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [8 empty] | 1 | 2026-03-23 | Om Construction | [5 empty] | 1 | 2026-05-27 | Om Construction | 17.076 | [5 empty] | DC | 6 | DC+6
|  |  | 207.8 | [23 empty] | 1 | 2026-03-23 | Om Construction |  |  |  |  | TRUE
444 | 67/0 | DC1+9 |  | 1 | 0444 | Y | R | B | Y | R | B | 1 | 07.06.26 | Shri Balaji Const. | I | II | 1 | 1 | 07.06.26 | Shri Balaji Const. | 1 | 07.06.26 | Shri Balaji Const. | [6 empty] | 1 | 2026-03-23 | Om Construction | [5 empty] | 1 | 2026-03-23 | Om Construction | 20.436 | [5 empty] | DC | 9 | DC+9
|  |  | 347.1 | [23 empty] | 1 | 2026-03-23 | Om Construction |  |  |  |  | TRUE
445 | 67/1 | DA+0 |  | 1 | 0445 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-23 | Om Construction | [5 empty] | 1 | 2026-03-23 | Om Construction | 10.016 | [5 empty] | DA | 0 | DA+0
|  |  | 344.9 | [23 empty] | 1 | 2026-03-23 | Om Construction |  |  |  |  | TRUE
446 | 67/2 | DA+0 |  | 1 | 0446 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-23 | Om Construction | [5 empty] | 1 | 2026-03-24 | Om Construction | 10.016 | [5 empty] | DA | 0 | DA+0
|  |  | 369.2 | [23 empty] | 1 | 2026-03-23 | Om Construction |  |  |  |  | TRUE
447 | 68/0 | DD45+0 |  | 1 | 0447 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [8 empty] | 1 | 2026-03-23 | Om Construction | [5 empty] | 1 | 2026-03-24 | Om Construction | 15.885 | [5 empty] | DD | 0 | DD+0
|  |  | 200.9 | [23 empty] | 1 | 2026-03-23 | Om Construction |  |  |  |  | TRUE
448 | 69/0 | DB2+0 |  | 1 | 0448 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [8 empty] | 1 | 2026-03-23 | Om Construction | [5 empty] | 1 | 2026-04-02 | Om Construction | 11.441 | [5 empty] | DB | 0 | DB+0
|  |  | 374.1 | [23 empty] | 1 | 2026-03-23 | Om Construction |  |  |  |  | TRUE
449 | 69/1 | DA+3 |  | 1 | 0449 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-23 | Om Construction | [5 empty] | 1 | 2026-03-24 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 394.9 | [23 empty] | 1 | 2026-03-23 | Om Construction |  |  |  |  | TRUE
450 | 70/0 | DC1+0 |  | 1 | 0450 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [8 empty] | 1 | [7 empty] | 1 | 2026-05-28 | Om Construction | 13.124 | [5 empty] | DC | 0 | DC+0
|  |  | 388.4 | [23 empty] | 1 | 2026-03-23 | Om Construction |  |  |  |  | TRUE
451 | 70/1 | DA+3 |  | 1 | 0451 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-23 | Om Construction | [5 empty] | 1 | 2026-03-24 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 418.9 | [23 empty] | 1 | 2026-03-23 | Om Construction |  |  |  |  | TRUE
452 | 70/2 | DA+3 |  | 1 | 0452 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-24 | Om Construction | [5 empty] | 1 | 2026-03-25 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 418.6 | [23 empty] | 1 | 2026-03-23 | Om Construction |  |  |  |  | TRUE
453 | 70/3 | DA+3 |  | 1 | 0453 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-24 | Om Construction | [5 empty] | 1 | 2026-03-25 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 414 | [23 empty] | 1 | 2026-03-23 | Om Construction |  |  |  |  | TRUE
454 | 70/4 | DA+3 |  | 1 | 0454 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-24 | Om Construction | [5 empty] | 1 | 2026-03-25 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 419.6 | [23 empty] | 1 | 2026-03-24 | Om Construction |  |  |  |  | TRUE
455 | 70/5 | DA+3 |  | 1 | 0455 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-24 | Om Construction | [5 empty] | 1 | 2026-03-25 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 420.3 | [23 empty] | 1 | 2026-03-24 | Om Construction |  |  |  |  | TRUE
456 | 70/6 | DA+3 |  | 1 | 0456 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-24 | Om Construction | [5 empty] | 1 | 2026-03-26 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 419.6 | [23 empty] | 1 | 2026-03-24 | Om Construction |  |  |  |  | TRUE
457 | 70/7 | DA+3 |  | 1 | 0457 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-24 | Om Construction | [5 empty] | 1 | 2026-03-26 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 418.2 | [23 empty] | 1 | 2026-03-24 | Om Construction |  |  |  |  | TRUE
458 | 70/8 | DA+3 |  | 1 | 0458 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-11 | Company Gang |  |  |  | 1 | 2026-03-24 | Om Construction | [5 empty] | 1 | 2026-03-26 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 414.1 | [23 empty] | 1 | 2026-03-24 | Om Construction |  |  |  |  | TRUE
459 | 70/9 | DA+3 |  | 1 | 0459 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | 2026-03-11 | Company Gang |  |  |  | 1 | 2026-03-24 | Om Construction | [5 empty] | 1 | 2026-03-26 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 406.1 | [23 empty] | 1 | 2026-03-24 | Om Construction |  |  |  |  | TRUE
460 | 70/10 | DA+3 |  | 1 | 0460 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-24 | Om Construction | [5 empty] | 1 | 2026-03-26 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 408.6 | [23 empty] | 1 | 2026-03-24 | Om Construction |  |  |  |  | TRUE
461 | 70/11 | DA+3 |  | 1 | 0461 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-24 | Om Construction | [5 empty] | 1 | 2026-03-27 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 420.4 | [23 empty] | 1 | 2026-03-24 | Om Construction |  |  |  |  | TRUE
462 | 71/0 | DB2+3 |  | 1 | 0462 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [8 empty] | 1 | 2026-03-24 | Om Construction | [5 empty] | 1 | 2026-03-27 | Om Construction | 13.403 | [5 empty] | DB | 3 | DB+3
|  |  | 398.6 | [23 empty] | 1 | 2026-03-24 | Om Construction |  |  |  |  | TRUE
463 | 71/1 | DA+3 |  | 1 | 0463 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-25 | Om Construction | [5 empty] | 1 | 2026-03-27 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 414.3 | [23 empty] | 1 | 2026-03-24 | Om Construction |  |  |  |  | TRUE
464 | 71/2 | DA+3 |  | 1 | 0464 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-25 | Om Construction | [5 empty] | 1 | 2026-03-27 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 413 | [23 empty] | 1 | 2026-06-20 | Om Construction |  |  |  |  | TRUE
465 | 71/3 | DA+6 |  | 1 | 0465 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-25 | Om Construction | [5 empty] | 1 | 2026-03-28 | Om Construction | 12.506 | [5 empty] | DA | 6 | DA+6
|  |  | 367.7 | [23 empty] | 1 | 2026-06-20 | Om Construction |  |  |  |  | TRUE
466 | 71/4 | DA+3 |  | 1 | 0466 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-25 | Om Construction | [5 empty] | 1 | 2026-03-28 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 429.4 | [23 empty] | 1 | 2026-06-20 | Om Construction |  |  |  |  | TRUE
467 | 71/5 | DA+3 |  | 1 | 0467 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-25 | Om Construction | [5 empty] | 1 | 2026-03-29 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 408 | [23 empty] | 1 | 2026-06-20 | Om Construction |  |  |  |  | TRUE
468 | 71/6 | DA+0 |  | 1 | 0468 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-25 | Om Construction | [5 empty] | 1 | 2026-03-29 | Om Construction | 10.016 | [5 empty] | DA | 0 | DA+0
|  |  | 404.9 | [23 empty] | 1 | 2026-06-20 | Om Construction |  |  |  |  | TRUE
469 | 71/7 | DA+3 |  | 1 | 0469 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-25 | Om Construction | [5 empty] | 1 | 2026-03-29 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 431.6 | [23 empty] | 1 | 2026-06-20 | Om Construction |  |  |  |  | TRUE
470 | 71/8 | DA+3 |  | 1 | 0470 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-25 | Om Construction | [5 empty] | 1 | 2026-03-30 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 408.4 | [23 empty] | 1 | 2026-06-20 | Om Construction |  |  |  |  | TRUE
471 | 72/0 | DB2+3 |  | 1 | 0471 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [8 empty] | 1 | 2026-03-25 | Om Construction | [5 empty] | 1 | 2026-03-30 | Om Construction | 13.403 | [5 empty] | DB | 3 | DB+3
|  |  | 435.3 | [23 empty] | 1 | 2026-06-20 | Om Construction |  |  |  |  | TRUE
472 | 72/1 | DA+3 |  | 1 | 0472 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-28 | Om Construction | [5 empty] | 1 | 2026-03-30 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 403.9 | [23 empty] | 1 | 2026-06-20 | Om Construction |  |  |  |  | TRUE
473 | 72/2 | DA+0 |  | 1 | 0473 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-28 | Om Construction | [5 empty] | 1 | 2026-03-30 | Om Construction | 10.016 | [5 empty] | DA | 0 | DA+0
|  |  | 389.2 | [23 empty] | 1 | 2026-06-20 | Om Construction |  |  |  |  | TRUE
474 | 72/3 | DA+3 |  | 1 | 0474 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-03-28 | Om Construction | [5 empty] | 1 | 2026-03-30 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 400.1 | [23 empty] | 1 | 2026-06-20 | Om Construction |  |  |  |  | TRUE
475 | 73/0 | DB2+0 |  | 1 | 0475 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [8 empty] | 1 | 2026-03-28 | Om Construction | [5 empty] | 1 | 2026-03-31 | Om Construction | 11.441 | [5 empty] | DB | 0 | DB+0
|  |  | 383.3 | [23 empty] | 1 | 2026-06-20 | Om Construction |  |  |  |  | TRUE
476 | 73/1 | DA+0 |  | 1 | 0476 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-06-29 | Om Construction | [5 empty] | 1 | 2026-03-31 | Om Construction | 10.016 | [5 empty] | DA | 0 | DA+0
|  |  | 379 | [23 empty] | 1 | 2026-06-21 | Om Construction |  |  |  |  | TRUE
477 | 73/2 | DA+0 |  | 1 | 0477 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-06-29 | Om Construction | [5 empty] | 1 | 2026-03-31 | Om Construction | 10.016 | [5 empty] | DA | 0 | DA+0
|  |  | 381.2 | [23 empty] | 1 | 2026-06-21 | Om Construction |  |  |  |  | TRUE
478 | 73/3 | DA+0 |  | 1 | 0478 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-06-29 | Om Construction | [5 empty] | 1 | 2026-03-31 | Om Construction | 10.016 | [5 empty] | DA | 0 | DA+0
|  |  | 384.7 | [23 empty] | 1 | 2026-06-21 | Om Construction |  |  |  |  | TRUE
479 | 73/4 | DA+0 |  | 1 | 0479 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-06-29 | Om Construction | [5 empty] | 1 | 2026-03-31 | Om Construction | 10.016 | [5 empty] | DA | 0 | DA+0
|  |  | 368.8 | [23 empty] | 1 | 2026-06-21 | Om Construction |  |  |  |  | TRUE
480 | 73/5 | DA+0 |  | 1 | 0480 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-06-29 | Om Construction | [5 empty] | 1 | 2026-04-01 | Om Construction | 10.016 | [5 empty] | DA | 0 | DA+0
|  |  | 365.5 | [23 empty] | 1 | 2026-06-21 | Om Construction |  |  |  |  | TRUE
481 | 73/6 | DA+0 |  | 1 | 0481 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-06-29 | Om Construction | [5 empty] | 1 | 2026-04-01 | Om Construction | 10.016 | [5 empty] | DA | 0 | DA+0
|  |  | 392.4 | [23 empty] | 1 | 2026-06-21 | Om Construction |  |  |  |  | TRUE
482 | 73/7 | DA+0 |  | 1 | 0482 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-06-29 | Om Construction | [5 empty] | 1 | 2026-04-01 | Om Construction | 10.016 | [5 empty] | DA | 0 | DA+0
|  |  | 374.9 | [23 empty] | 1 | 2026-06-21 | Om Construction |  |  |  |  | TRUE
483 | 73/8 | DA+3 |  | 1 | 0483 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-06-29 | Om Construction | [5 empty] | 1 | 2026-04-01 | Om Construction | 11.294 | [5 empty] | DA | 3 | DA+3
|  |  | 379.5 | [23 empty] | 1 | 2026-06-21 | Om Construction |  |  |  |  | TRUE
484 | 73/9 | DA+0 |  | 1 | 0484 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 |  |  | 1 | [5 empty] | 1 | 2026-06-29 | Om Construction | [5 empty] | 1 | 2026-04-01 | Om Construction | 10.016 | [5 empty] | DA | 0 | DA+0
|  |  | 378.9 | [23 empty] | 1 | 2026-06-21 | Om Construction |  |  |  |  | TRUE
485 | 74/0 | DB2+0 |  | 1 | 0485 | Y | R | B | Y | R | B | 1 |  |  | I | II | 1 | 1 |  |  | 1 | [8 empty] | 1 | [7 empty] | 1 | 2026-04-02 | Om Construction | 11.441 | [5 empty] | DB | 0 | DB+0
Total Required |  |  |  | 485 | 485 | [6 empty] | 485 | [5 empty] | 485 |  |  | 485 |  |  | 397 |  |  | 144 |  |  | 88 |  |  | 10033 |  |  |  | 0 | 51 |  |  | 785.222
65/3
65/4
65/5
65/6
65/7
65/9
65/10
65/11
66/0
67/1
67/2
68/0
69/0
69/1
70/1
70/2
70/3
70/4
70/5
70/6
70/7
70/8
70/9
70/10
70/11
71/0
71/1
71/2
71/3
71/4
71/5
71/6
71/7
71/8
72/0
46/0
47/0
56/0
57/0
72/1
72/2
72/3
73/0
9/0
10/0
65/2
65/1
65/0
64/4
64/5
64/6
64/7
64/8
64/9
64/10
64/11
64/0
64/1
64/2
64/3
63/0
63/1
63/2
63/3
63/4
63/5
63/6
63/7
63/8
62/6
62/7
62/8
62/9
62/10
62/11
67/0
73/1
73/2
73/3
73/4
73/5
73/6
73/7
73/8
73/9

## Visual chart
Progress Summary'!A1
| Project Name :- Beawar 765 KV D/C Line, (TB-408 PKG-F) | [15 empty] | Progress Legends
| Progress Status as on dated | [5 empty] | 2026-07-29
| Sr. No. |  | Description |  |  |  | UOM |  | Total qty |  | Completed |  |  | Balance |  | WIP |  |  |  |  | Stringing WIP | [22 empty] | Identification for auto fill linked with Summary of visual chart
| 1 |  | Foundation |  |  |  | Nos |  | 485 |  | 485 |  |  | 0 |  | 0 |  |  |  |  | Erection U/P
| 2 |  | Earthing |  |  |  | Nos |  | 485 |  | 485 |  |  | 0 |  | 0 |  |  |  |  | Tackwelding U/P | [30 empty] | E
| 3 |  | Tower Erection |  |  |  | Nos |  | 485 |  | 485 |  |  | 0 |  | 3 |  |  |  |  | Foundation U/P
| 4 |  | Tack-Welding |  |  |  | Nos |  | 485 |  | 464 |  |  | 21 |  | 0 |  |  |  |  | Earthing U/P
| 5 |  | Rough Sag |  |  |  | KM |  | 191.36 |  | 158.0358 |  |  | 33.3242 |  | 11 | [27 empty] | Sandy | Dry | DFR
| 6 |  | Final Sag |  |  |  | KM |  | 191.36 |  | 158.0358 |  |  | 33.3242 |  | 1 | [34 empty] | C
| Legends & Quantity | [19 empty] | Final Sag Completed
[14 empty] | NH | [6 empty] | Pay out Completed
|  |  | B Type Towers | [6 empty] | Forest |  |  |  | 3 No's/1 No's | [6 empty] | Erection Completed
|  |  | C & D type towers | [17 empty] | Welding Completed
|  | 132/220 KV Line |  |  |  | 400 KV |  |  | Gas Pipe Line | [9 empty] | DFR |  | FDN Completed | [22 empty] | FOUNDATION | [6 empty] | EARTHING | ERECTION | Welding | P/O | FS | Total Section Length | P/0 WIP | Paying out Completed | Final Sag Completed
|  | 3 No's/2 No's |  |  |  | 4 No's |  |  | 1 No's | [9 empty] | C |  | Earthing Completed | [22 empty] | SANDY | DRY | DFR | WFR | FS | Total FDN | FDN WIP | C | E | Done | PO | FS |  | . | .. | ,
[19 empty] | LE |  | Leg Exten. A,B,C,D | [22 empty] | 200 | 223 | 60 | 2 | 0 | 485 | 0 | 485 | 485 | 464 | 0 | 0 | 191392.643 | 6343.9 | 0 | 138917.769
| 0 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21
| Gty |  | 1/0 |  | 1A/0 |  | 1A/1 |  | 1A/2 |  | 1A/3 |  | 1A/4 |  | 1A/5 |  | 1A/6 |  | 1A/7 |  | 1A/8 |  | 2/0 |  | 2/1 |  | 2/2 |  | 2/3 |  | 2/4 |  | 2/5 |  | 2/6 |  | 2/7 |  | 2/8 |  | 2/9 |  | 3/0
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 7461.9
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
|  | 122 | DRY | 90 | DRY | 277.7 | DFR | 386 | DRY | 443.6 | DRY | 333.4 | DFR | 431.9 | DRY | 348.7 | Sandy | 395.7 | Sandy | 415 | Sandy | 394.3 | DRY | 405.3 | Sandy | 338.5 | Sandy | 406 | Sandy | 429 | Sandy | 411.6 | Sandy | 425.7 | Sandy | 408.2 | Sandy | 354.6 | Sandy | 308.7 | DRY | 336 | DRY | 11 | 8 | 2 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 7461.9
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
|  |  | DD60+0 |  | DD60+0 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DC1+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DD60+6
|  |  | ,,, |  | ,,, |  | ,,, |  | ,1,1, |  | ,,, |  | ,,1, |  | 1,1,, |  | 1,,,1 |  | ,1,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,1 |  | 1,,1,1 |  | ,,, |  | ,,1,1 |  | ,,,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42
|  |  | 4/0 |  | 4/1 |  | 4/2 |  | 4/3 |  | 4/4 |  | 5/0 |  | 6/0 |  | 6/1 |  | 6/2 |  | 7/0 |  | 8/0 |  | 8/1 |  | 8/2 |  | 8/3 |  | 8/4 |  | 8/5 |  | 8/6 |  | 8/7 |  | 8/8 |  | 8/9 |  | 8/10
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 7781.667
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 226.5 | DRY | 343 | DRY | 358.4 | DRY | 381 | DRY | 367.6 | DRY | 423.1 | DRY | 246 | DRY | 429.9 | DFR | 362.4 | DFR | 347.9 | DRY | 210.8 | DRY | 409.2 | DRY | 413.6 | DRY | 393.2 | DRY | 416.5 | DRY | 394.6 | DRY | 393.2 | DRY | 441.1 | DRY | 414.4 | DRY | 395.863 | DFR | 413.404 | DFR | 0 | 17 | 4 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 7781.667
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DD60+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+9 |  | DB2+9 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DB1+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+6 |  | DA+3 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 5,5,5,5 |  | 5,5,5,5 |  | ,,, |  | ,,, |  | 2,3,3,2 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60 |  | 61 |  | 62 |  | 63
|  |  | 8/11 |  | 8/12 |  | 9/0 |  | 10/0 |  | 10/1 |  | 10/2 |  | 10/3 |  | 10/4 |  | 10/5 |  | 10/6 |  | 10/7 |  | 10/8 |  | 10/9 |  | 10/10 |  | 10/11 |  | 10/12 |  | 10/13 |  | 10/14 |  | 10/15 |  | 10/16 |  | 10/17
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8392.968
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 402.6 | DRY | 372.1 | DRY | 457.7 | DRY | 233.1 | DFR | 443.7 | DRY | 383.2 | DFR | 398.6 | DFR | 410.7 | DFR | 416.2 | DRY | 403.4 | DFR | 373.845 | DRY | 411.823 | DFR | 414.2 | DRY | 402.3 | Sandy | 430.3 | DRY | 406.2 | DRY | 405.3 | DRY | 427.1 | DRY | 400 | DRY | 412.8 | DRY | 387.8 | DFR | 1 | 13 | 7 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8392.968
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+0 |  | DA+0 |  | DD60+18 |  | DD60+25 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70 |  | 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80 |  | 81 |  | 82 |  | 83 |  | 84
|  |  | 10/18 |  | 10/19 |  | 10/20 |  | 10/21 |  | 10/22 |  | 10/23 |  | 11/0 |  | 11/1 |  | 11/2 |  | 11/3 |  | 11/4 |  | 11/5 |  | 11A/0 |  | 11A/1 |  | 11A/2 |  | 11A/3 |  | 11A/4 |  | 11A/5 |  | 11A/6 |  | 11A/7 |  | 11A/8
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8430.1
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 436.7 | DFR | 403.7 | DRY | 409.5 | DFR | 418.6 | DFR | 410.3 | Sandy | 384 | Sandy | 450.8 | Sandy | 384.2 | Sandy | 338.6 | Sandy | 370.7 | Sandy | 434.1 | Sandy | 368.1 | DFR | 342.3 | DRY | 405.1 | DRY | 412.2 | DRY | 412.2 | DRY | 422.1 | DRY | 418.3 | DRY | 384.3 | DRY | 434.2 | Sandy | 390.1 | Sandy | 9 | 8 | 4 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8430.1
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+9 |  | DA+6
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 1,3,, |  | ,2,, |  | 1,4,,3 |  | ,,, |  | 2,1,, |  | ,,,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,2,4,1
REM
|  |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90 |  | 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100 |  | 101 |  | 102 |  | 103 |  | 104 |  | 105
|  |  | 11A/9 |  | 12/0 |  | 13/0 |  | 13/1 |  | 13/2 |  | 13/3 |  | 13/4 |  | 14/0 |  | 14A/0 |  | 14A/1 |  | 14A/2 |  | 15/0 |  | 15/1 |  | 16/0 |  | 16/1 |  | 16/2 |  | 16/3 |  | 16/4 |  | 16/5 |  | 17/0 |  | 17/1
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [13 empty] | . | [14 empty] | 393.7 | 0 | 5513.494
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  |  |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 426.3 | DRY | 405.9 | DRY | 211.9 | DRY | 464.3 | DRY | 373.7 | DRY | 419.7 | Sandy | 420.3 | DRY | 400 | Sandy | 381.4 | DRY | 412.765 | DRY | 396.029 | DRY | 383.3 | DRY | 404.6 | DRY | 413.3 | DRY | 354.283 | DRY | 424.28 | DRY | 340.3 | DRY | 394.7 | DRY | 435.863 | DRY | 386.8 | DRY | 393.7 | DRY | 2 | 19 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 20 |  |  | 8243.42
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DD60+0 |  | DD60+3 |  | DA+9 |  | DA+3 |  | DA+3 |  | DA+3 |  | DC2+0 |  | DC1+0 |  | DA+3 |  | DA+0 |  | DC1+0 |  | DA+3 |  | DC1+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB2+3 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,2,4 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 1,,,1 |  | ,,, |  | ,1,, |  | ,,, |  | ,,,1 |  | ,,,
REM
|  |  | 106 |  | 107 |  | 108 |  | 109 |  | 110 |  | 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120 |  | 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126
|  |  | 17/2 |  | 17/3 |  | 17/4 |  | 17/5 |  | 18/0 |  | 18/1 |  | 18/2 |  | 18/3 |  | 18/4 |  | 19/0 |  | 19/1 |  | 19/2 |  | 19/3 |  | 19/4 |  | 19/5 |  | 20/0 |  | 20/1 |  | 20/2 |  | 20/3 |  | 21/0 |  | 21/1
|  | . |  | . |  | . |  | . |  | . | [46 empty] | 2057.3 | 0 | 0
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD | [5 empty] | Done |  |  |  | Done |  | Done |  |  |  | Done |  | Done |  | Done |  |  |  | Done | [9 empty] | Done |  | Done |  | Done
| FDN | 415.9 | DRY | 422.8 | DRY | 409.9 | DRY | 425.3 | DRY | 383.4 | DRY | 372.8 | DRY | 379.8 | DRY | 371 | DRY | 398.7 | DRY | 380.8 | DRY | 366.9 | DRY | 372.5 | DRY | 376.5 | DRY | 384.3 | DRY | 375.4 | DRY | 381.2 | Sandy | 386.8 | Sandy | 387 | DRY | 348.5 | DRY | 355 | DRY | 414.9 | DRY | 2 | 19 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 10 |  |  | 8109.4
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+3 |  | DC2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+6
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 127 |  | 128 |  | 129 |  | 130 |  | 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140 |  | 141 |  | 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147
|  |  | 21/2 |  | 21/3 |  | 21/4 |  | 21/5 |  | 21/6 |  | 21/7 |  | 21/8 |  | 21/9 |  | 21/10 |  | 22/0 |  | 22/1 |  | 22/2 |  | 22/3 |  | 22/4 |  | 22/5 |  | 22/6 |  | 22/7 |  | 22/8 |  | 22/9 |  | 22/10 |  | 22/11
[38 empty] | , |  | , |  | , | [14 empty] | 0 | 0 | 1128.5
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  |  |  | Done | [9 empty] | Done | [7 empty] | Done |  | Done |  | Done
| FDN | 407.2 | Sandy | 432.2 | Sandy | 401.9 | Sandy | 434.2 | DFR | 405.5 | DRY | 426 | DFR | 406.9 | DRY | 433.3 | DFR | 372.9 | DRY | 443.5 | DRY | 456.3 | Sandy | 379.2 | Sandy | 382.6 | Sandy | 435.6 | Sandy | 402.1 | DRY | 417.3 | Sandy | 347.7 | Sandy | 356.3 | Sandy | 389.2 | Sandy | 343.8 | Sandy | 395.5 | Sandy | 13 | 5 | 3 | 0 | 0 | 21 | 0 | 21 | 21 | 12 |  |  | 8469.2
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+6 |  | DB2+3 |  | DA+9 |  | DA+6 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+6 |  | DA+6 |  | DA+6
| LE |  | ,,, |  | ,,, |  | ,1,2,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,2 |  | ,,,1 |  | ,,, |  | 2,2,2,2 |  | ,,,1 |  | ,1,,1 |  | ,2,1,1 |  | ,,, |  | 1,2,, |  | ,2,,
REM
|  |  | 148 |  | 149 |  | 150 |  | 151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160 |  | 161 |  | 162 |  | 163 |  | 164 |  | 165 |  | 166 |  | 167 |  | 168
|  |  | 22/12 |  | 22/13 |  | 23/0 |  | 24/0 |  | 25/0 |  | 25/1 |  | 25/2 |  | 25/3 |  | 25/4 |  | 26/0 |  | 26/1 |  | 26/2 |  | 26/3 |  | 26/4 |  | 26/5 |  | 26/6 |  | 26/7 |  | 26/8 |  | 27/0 |  | 27/1 |  | 27/2
|  | , |  | , |  | , |  | , |  | , | [29 empty] | . |  | . | [14 empty] | 825 | 0 | 1829.4
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 408 | Sandy | 318 | Sandy | 447.3 | DRY | 222.2 | DRY | 433.9 | DRY | 422.3 | DRY | 370.7 | DRY | 345.7 | Sandy | 391.1 | Sandy | 440.4 | DFR | 391.4 | DRY | 406.5 | DFR | 418 | DRY | 422.6 | Sandy | 410 | Sandy | 363.4 | Sandy | 421.9 | DFR | 416.7 | DFR | 413.8 | DFR | 399.8 | DFR | 425.2 | DFR | 7 | 7 | 7 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8288.9
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+6 |  | DD45+3 |  | DD45+3 |  | DC1+6 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+6 |  | DA+6 |  | DA+0 |  | DA+6 |  | DC1+0 |  | DA+3 |  | DA+3
| LE |  | 1,2,, |  | ,,1, |  | 2,2,2,2 |  | 2,2,2,2 |  | ,,, |  | ,,, |  | ,,, |  | 1,2,,2 |  | 1,1,,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 1,,, |  | 1,1,, |  | ,1,1, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 169 |  | 170 |  | 171 |  | 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180 |  | 181 |  | 182 |  | 183 |  | 184 |  | 185 |  | 186 |  | 187 |  | 188 |  | 189
|  |  | 27/3 |  | 27/4 |  | 27/5 |  | 27/6 |  | 27/7 |  | 27/8 |  | 27/9 |  | 27/10 |  | 27/11 |  | 27/12 |  | 28/0 |  | 28/1 |  | 28/2 |  | 28/3 |  | 28/4 |  | 28/5 |  | 28/6 |  | 28/7 |  | 28/8 |  | 29/0 |  | 29/1
|  | . |  | . |  | . |  | . |  | . |  | , |  | , |  | , |  | , |  | , |  | , | [34 empty] | 1985.4 | 0 | 2386.9
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 398.6 | DFR | 430.7 | DFR | 410 | DRY | 402.6 | Sandy | 343.5 | DFR | 392 | DFR | 381.1 | DFR | 366.3 | DFR | 420.1 | DRY | 420.8 | Sandy | 406.6 | DFR | 379.6 | DRY | 385 | DFR | 369 | DFR | 409 | Sandy | 422 | Sandy | 370 | Sandy | 464 | Sandy | 375 | Sandy | 465.5 | DRY | 365.6 | DRY | 7 | 5 | 9 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8377
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+9 |  | DA+6 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,2,, |  | 1,4,3, |  | 1,3,2, |  | ,,5,3 |  | ,,, |  | ,,,
REM
|  |  | 190 |  | 191 |  | 192 |  | 193 |  | 194 |  | 195 |  | 196 |  | 197 |  | 198 |  | 199 |  | 200 |  | 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207 |  | 208 |  | 209 |  | 210
|  |  | 29/2 |  | 29/3 |  | 29/4 |  | 30/0 |  | 30/1 |  | 30/2 |  | 30/3 |  | 30/4 |  | 30/5 |  | 30/6 |  | 31/0 |  | 31/1 |  | 31/2 |  | 32/0 |  | 32/1 |  | 32/2 |  | 32/3 |  | 32/4 |  | 33/0 |  | 33/1 |  | 34/0
[10 empty] | , |  | , |  | , |  | , |  | , |  | , |  | , |  | . |  | . |  | . | [28 empty] | 1082.5 | 0 | 2719.3
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 424 | DRY | 399 | Sandy | 440 | DRY | 382.1 | DRY | 388.9 | Sandy | 445 | Sandy | 395 | Sandy | 387 | DRY | 442 | DRY | 314 | DRY | 347.4 | Sandy | 383.6 | DRY | 366 | DRY | 332.9 | DRY | 402.7 | Sandy | 428.8 | DRY | 410.9 | Sandy | 381.1 | Sandy | 451.5 | DRY | 379.6 | DRY | 292.5 | DRY | 8 | 13 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8194
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+0 |  | DA+6 |  | DC1+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DC1+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DC1+0 |  | DA+0 |  | DB2+0
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 2,,, |  | 1,2,, |  | 1,2,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 1,,, |  | ,1,1, |  | ,,,
REM
|  |  | 211 |  | 212 |  | 213 |  | 214 |  | 215 |  | 216 |  | 217 |  | 218 |  | 219 |  | 220 |  | 221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229 |  | 230 |  | 231
|  |  | 34/1 |  | 34/2 |  | 34/3 |  | 34/4 |  | 35/0 |  | 35/1 |  | 35/2 |  | 35/3 |  | 35/4 |  | 35/5 |  | 36/0 |  | 36/1 |  | 36/2 |  | 36/3 |  | 36/4 |  | 37/0 |  | 37/1 |  | 37/2 |  | 37/3 |  | 38/0 |  | 38/1
[57 empty] | 0 | 0 | 0
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 432.6 | Sandy | 407.5 | Sandy | 377 | Sandy | 451.6 | Sandy | 379.3 | Sandy | 265.6 | Sandy | 492.4 | Sandy | 522.2 | Sandy | 418.9 | DRY | 421.7 | Sandy | 342.7 | Sandy | 386.4 | Sandy | 309.4 | Sandy | 357.8 | Sandy | 480.4 | Sandy | 350.5 | Sandy | 443.3 | Sandy | 356.7 | Sandy | 339.9 | Sandy | 500.3 | Sandy | 421.4 | Sandy | 20 | 1 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8457.6
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+9 |  | DA+6 |  | DA+0 |  | DA+0 |  | DB2+6 |  | DA+9 |  | DB1+0 |  | DB1+6 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+6 |  | DB2+0 |  | DA+9 |  | DA+3 |  | DA+0 |  | DB2+6 |  | DA+0
| LE |  | ,,, |  | ,,,2 |  | ,3,, |  | ,3,1, |  | 2,,, |  | 2,,,2 |  | 1,1,, |  | 1,,, |  | ,,, |  | ,,4,4 |  | ,,, |  | ,,, |  | 1,1,, |  | ,2,, |  | 2,3,,5 |  | ,,,1 |  | 2,2,2,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 232 |  | 233 |  | 234 |  | 235 |  | 236 |  | 237 |  | 238 |  | 239 |  | 240 |  | 241 |  | 242 |  | 243 |  | 244 |  | 245 |  | 246 |  | 247 |  | 248 |  | 249 |  | 250 |  | 251 |  | 252
|  |  | 38/2 |  | 38/3 |  | 38/4 |  | 39/0 |  | 39/1 |  | 40/0 |  | 40/1 |  | 40/2 |  | 40/3 |  | 41/0 |  | 41/1 |  | 41/2 |  | 42/0 |  | 42/1 |  | 42/2 |  | 42/3 |  | 42/4 |  | 42/5 |  | 42/6 |  | 43/0 |  | 43/1
[42 empty] | , | [14 empty] | 0 | 0 | 346
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 419 | Sandy | 420.3 | Sandy | 414.9 | Sandy | 425.5 | Sandy | 412.638 | Sandy | 322.61 | Sandy | 396.2 | Sandy | 425.8 | Sandy | 401.7 | Sandy | 436.3 | Sandy | 340.8 | Sandy | 447.8 | Sandy | 382.3 | Sandy | 384.7 | Sandy | 407.4 | Sandy | 414.2 | Sandy | 256.4 | Sandy | 403.8 | Sandy | 396.7 | Sandy | 403.9 | Sandy | 346 | Sandy | 21 | 0 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8258.948
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+6 |  | DA+9 |  | DA+9 |  | DB2+6 |  | DA+0 |  | DC2+0 |  | DA+6 |  | DA+3 |  | DA+3 |  | DC1+6 |  | DB1+9 |  | DA+0 |  | DC1+0 |  | DA+6 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+9 |  | DA+0 |  | DB1+0 |  | DA+3
| LE |  | ,,, |  | 2,2,2,2 |  | 1,1,,1 |  | ,,, |  | ,,, |  | 1,1,, |  | 1,2,, |  | ,,, |  | 1,2,, |  | 3,1,,1 |  | 4,5,6,6 |  | ,,1,1 |  | 1,,,2 |  | 1,,, |  | ,,1,3 |  | ,,, |  | ,,, |  | ,,,1 |  | 2,1,,2 |  | ,,, |  | ,,3,3
REM
|  |  | 253 |  | 254 |  | 255 |  | 256 |  | 257 |  | 258 |  | 259 |  | 260 |  | 261 |  | 262 |  | 263 |  | 264 |  | 265 |  | 266 |  | 267 |  | 268 |  | 269 |  | 270 |  | 271 |  | 272 |  | 273
|  |  | 43/2 |  | 43/3 |  | 43/4 |  | 43/5 |  | 43/6 |  | 43/7 |  | 43/8 |  | 43/9 |  | 43/10 |  | 43/11 |  | 44/0 |  | 44/1 |  | 44/2 |  | 44/3 |  | 44/4 |  | 44/5 |  | 44/6 |  | 44/7 |  | 44/8 |  | 44/9 |  | 44/10
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8454
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
|  |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
|  | 475.8 | Sandy | 363.7 | DRY | 431.8 | Sandy | 405.3 | DRY | 427.8 | Sandy | 389.8 | Sandy | 449.5 | Sandy | 388 | Sandy | 346.3 | Sandy | 444.8 | Sandy | 383.9 | Sandy | 384.3 | Sandy | 359 | Sandy | 334 | Sandy | 395 | Sandy | 355 | Sandy | 485 | Sandy | 473 | Sandy | 367 | Sandy | 430 | Sandy | 365 | Sandy | 19 | 2 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8454
|  |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
|  |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DB1+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+9 |  | DA+9 |  | DB1+3 |  | DA+9 |  | DCT+0 |  | DA+9 |  | DB1+9
|  |  | 1,,,1 |  | ,1,, |  | 1,1,, |  | ,,, |  | ,,, |  | ,,, |  | 1,,, |  | ,,, |  | 3,3,, |  | 2,3,,1 |  | 0,1,1,0 |  | 0,0,1,0 |  | 0,0,0,0 |  | 2,0,0,1 |  | 4,3,3,3 |  | 1,3,0,0 |  | 1,0,0,1 |  | 0,0,0,0 |  | 1,2,0,1 |  | 4,0,2,6 |  | 0,1,0,0
REM
|  |  | 274 |  | 275 |  | 276 |  | 277 |  | 278 |  | 279 |  | 280 |  | 281 |  | 282 |  | 283 |  | 284 |  | 285 |  | 286 |  | 287 |  | 288 |  | 289 |  | 290 |  | 291 |  | 292 |  | 293 |  | 294
|  |  | 44/11 |  | 45/0 |  | 45/1 |  | 46/0 |  | 47/0 |  | 47/1 |  | 47/2 |  | 47/3 |  | 47/4 |  | 47/5 |  | 47/6 |  | 47/7 |  | 47/8 |  | 47/9 |  | 47/10 |  | 48/0 |  | 48/1 |  | 49/0 |  | 49/1 |  | 49/2 |  | 49/3
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8120.77
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 428 | Sandy | 327.2 | Sandy | 294.92 | Sandy | 406.54 | Sandy | 199.08 | Sandy | 441.2 | Sandy | 365.93 | Sandy | 417.4 | Sandy | 358.4 | Sandy | 461.2 | Sandy | 377.3 | Sandy | 431.5 | Sandy | 398.8 | Sandy | 405.9 | Sandy | 433.7 | Sandy | 386.2 | Sandy | 428.9 | Sandy | 402.9 | Sandy | 379.1 | Sandy | 386.6 | Sandy | 390 | Sandy | 21 | 0 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8120.77
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+0 |  | DC2+0 |  | DA+9 |  | DD60+25 |  | DD60+25 |  | DA+3 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DC2+0 |  | DA+9 |  | DD45+0 |  | DA+0 |  | DA+3 |  | DA+3
| LE |  | 0,1,0,0 |  | 0,1,0,0 |  | 0,0,6,6 |  | 0,6,6,2 |  | 5,5,5,5 |  | 2,0,2,5 |  | 0,0,0,0 |  | 1,2,0,0 |  | ,,, |  | 0,1,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 1,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0
REM
|  |  | 295 |  | 296 |  | 297 |  | 298 |  | 299 |  | 300 |  | 301 |  | 302 |  | 303 |  | 304 |  | 305 |  | 306 |  | 307 |  | 308 |  | 309 |  | 310 |  | 311 |  | 312 |  | 313 |  | 314 |  | 315
|  |  | 49/4 |  | 49/5 |  | 49/6 |  | 49/7 |  | 50/0 |  | 50/1 |  | 50/2 |  | 50/3 |  | 50/4 |  | 50/5 |  | 50/6 |  | 50/7 |  | 50/8 |  | 50/9 |  | 50/10 |  | 51/0 |  | 51/1 |  | 51/2 |  | 52/0 |  | 52/1 |  | 52/2
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8368.9
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 421.7 | Sandy | 396.6 | Sandy | 412.8 | Sandy | 340.2 | Sandy | 500.2 | Sandy | 469.1 | Sandy | 367.1 | Sandy | 470.4 | Sandy | 354.8 | Sandy | 442.1 | Sandy | 364.4 | Sandy | 470.8 | Sandy | 345 | Sandy | 364.4 | Sandy | 394.6 | Sandy | 401.4 | Sandy | 356.6 | Sandy | 307.1 | Sandy | 385 | Sandy | 402 | Sandy | 402.6 | Sandy | 21 | 0 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8368.9
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+6 |  | DA+9 |  | DA+6 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+0 |  | DA+9 |  | DA+0 |  | DA+0 |  | DC2+0 |  | DA+0 |  | DA+0 |  | DC2+0 |  | DA+6 |  | DA+6
| LE |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,3,2,2 |  | 0,0,0,1 |  | 1,0,0,0 |  | 2,2,2,2 |  | 0,0,1,0 |  | 3,3,4,3 |  | 4,3,4,3 |  | 3,4,3,3 |  | 0,0,0,1 |  | 0,0,0,0 |  | 0,0,1,0 |  | 0,0,1,0 |  | 0,0,0,0 |  | 0,0,1,0 |  | 0,0,0,0 |  | 0,0,3,3 |  | 0,4,0,0 |  | 0,0,0,3
REM
|  |  | 316 |  | 317 |  | 318 |  | 319 |  | 320 |  | 321 |  | 322 |  | 323 |  | 324 |  | 325 |  | 326 |  | 327 |  | 328 |  | 329 |  | 330 |  | 331 |  | 332 |  | 333 |  | 334 |  | 335 |  | 336
|  |  | 52/3 |  | 52/4 |  | 52/5 |  | 52/6 |  | 52/7 |  | 52/8 |  | 52/9 |  | 52/10 |  | 53/0 |  | 53/1 |  | 53/2 |  | 53/3 |  | 53/4 |  | 53/5 |  | 53/6 |  | 53/7 |  | 53/8 |  | 54/0 |  | 54/1 |  | 54/2 |  | 54/3
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8583.7
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 437 | Sandy | 393.8 | Sandy | 447 | Sandy | 373 | Sandy | 406.8 | Sandy | 433 | Sandy | 399.7 | Sandy | 384.1 | Sandy | 455.9 | Sandy | 433.2 | Sandy | 407.4 | Sandy | 394.5 | Sandy | 410.1 | Sandy | 428.1 | Sandy | 406.6 | Sandy | 411.3 | Sandy | 427.8 | Sandy | 371.3 | Sandy | 365.1 | Sandy | 381 | Sandy | 417 | Sandy | 21 | 0 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8583.7
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+9 |  | DB2+9 |  | DA+9 |  | DA+0 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+3 |  | DB1+6 |  | DA+3 |  | DA+3 |  | DA+6
| LE |  | 4,3,3,3 |  | 2,2,0,0 |  | 0,0,0,1 |  | 0,0,0,0 |  | 0,3,1,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 1,2,1,1 |  | 4,4,4,4 |  | 4,4,4,4 |  | 0,0,0,2 |  | 0,4,1,0 |  | 0,2,1,0 |  | 0,0,0,0 |  | 1,1,3,1 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 1,1,0,0 |  | 0,0,0,0 |  | 0,2,0,0
REM
|  |  | 337 |  | 338 |  | 339 |  | 340 |  | 341 |  | 342 |  | 343 |  | 344 |  | 345 |  | 346 |  | 347 |  | 348 |  | 349 |  | 350 |  | 351 |  | 352 |  | 353 |  | 354 |  | 355 |  | 356 |  | 357
|  |  | 54/4 |  | 54/5 |  | 55/0 |  | 55/1 |  | 55/2 |  | 55/3 |  | 55/4 |  | 55/5 |  | 55/6 |  | 55/7 |  | 55/8 |  | 56/0 |  | 57/0 |  | 57/1 |  | 57/2 |  | 57/3 |  | 57/4 |  | 57/5 |  | 57/6 |  | 57/7 |  | 58/0
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8073.97
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 423.3 | Sandy | 401 | Sandy | 424 | Sandy | 404.9 | WFR | 343.1 | WFR | 357.7 | Sandy | 365.2 | Sandy | 350.1 | Sandy | 357.7 | Sandy | 337.8 | Sandy | 341.22 | Sandy | 460.49 | Sandy | 219.76 | Sandy | 461.1 | Sandy | 355.5 | DRY | 405.4 | DRY | 418.2 | Sandy | 416.8 | Sandy | 395 | Sandy | 401.8 | DFR | 433.9 | DFR | 15 | 2 | 2 | 2 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8073.97
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+9 |  | DA+9 |  | DB1+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DD60+25 |  | DD60+25 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DC1+3
| LE |  | 1,2,0,0 |  | 1,3,3,1 |  | 0,1,1,0 |  | ,,, |  | ,,, |  | ,,, |  | 0,0,0,1 |  | 0,0,1,3 |  | 0,0,1,2 |  | 0,0,1,0 |  | 0,0,0,0 |  | 3,3,0,2 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,1 |  | 0,1,0,0 |  | ,,, |  | 0,0,0,0
REM
|  |  | 358 |  | 359 |  | 360 |  | 361 |  | 362 |  | 363 |  | 364 |  | 365 |  | 366 |  | 367 |  | 368 |  | 369 |  | 370 |  | 371 |  | 372 |  | 373 |  | 374 |  | 375 |  | 376 |  | 377 |  | 378
|  |  | 59/0 |  | 59/1 |  | 59/2 |  | 59/3 |  | 59/4 |  | 59/5 |  | 59/6 |  | 59/7 |  | 59/8 |  | 59/9 |  | 59/10 |  | 59/11 |  | 59/12 |  | 59/13 |  | 59/14 |  | 59/15 |  | 59/16 |  | 60/0 |  | 60/1 |  | 60/2 |  | 60/3
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8606.7
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 238.9 | DRY | 411.3 | DRY | 418.2 | DFR | 412.3 | DFR | 421 | DFR | 419.7 | DFR | 419.1 | DFR | 408.8 | DRY | 426.9 | DRY | 434.7 | DRY | 400.8 | DRY | 436.3 | DFR | 393.1 | DFR | 447.4 | DRY | 391.1 | DRY | 448.6 | DRY | 388 | Dry | 438 | DRY | 413.8 | DRY | 424.2 | DFR | 414.5 | DFR | 0 | 12 | 9 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8606.7
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DC2+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB1+3 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+6 |  | DA+9 |  | DC1+0 |  | DA+6 |  | DA+3 |  | DA+3
| LE |  | 0,0,0,0 |  | 0,0,0,1 |  | 0,0,0,0 |  | 0,0,0,1 |  | ,,, |  | ,,, |  | ,,, |  | 0,0,0,0 |  | ,,, |  | ,,, |  | ,,, |  | 0,0,2,0 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 2,2,0,0 |  | ,,,
REM
|  |  | 379 |  | 380 |  | 381 |  | 382 |  | 383 |  | 384 |  | 385 |  | 386 |  | 387 |  | 388 |  | 389 |  | 390 |  | 391 |  | 392 |  | 393 |  | 394 |  | 395 |  | 396 |  | 397 |  | 398 |  | 399
|  |  | 60/4 |  | 60/5 |  | 60/6 |  | 60/7 |  | 60/8 |  | 60/9 |  | 60/10 |  | 60/11 |  | 61/0 |  | 61/1 |  | 61/2 |  | 61/3 |  | 61/4 |  | 61/5 |  | 61/6 |  | 61/7 |  | 61/8 |  | 61/9 |  | 61/10 |  | 62/0 |  | 62/1
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8611.3
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 425.6 | DFR | 412.3 | DRY | 374.1 | DRY | 410.1 | DRY | 400.4 | DRY | 409.2 | DRY | 401 | DFR | 394.5 | DRY | 397.9 | DRY | 405.7 | DFR | 433.2 | DFR | 400.9 | DRY | 427 | DRY | 413.9 | DRY | 426.4 | DRY | 411.5 | Dry | 376.3 | DRY | 433.4 | Dry | 405.6 | DRY | 434.3 | DRY | 418 | Sandy | 1 | 16 | 4 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8611.3
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB2+0 |  | DA+6 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+9 |  | DA+6 |  | DA+0 |  | DA+9 |  | DB2+0 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 0,0,0,0 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 0,0,0,1 |  | 1,2,1,0 |  | ,,, |  | ,,, |  | 0,0,0,0 |  | 0,0,1,2
REM
|  |  | 400 |  | 401 |  | 402 |  | 403 |  | 404 |  | 405 |  | 406 |  | 407 |  | 408 |  | 409 |  | 410 |  | 411 |  | 412 |  | 413 |  | 414 |  | 415 |  | 416 |  | 417 |  | 418 |  | 419 |  | 420
|  |  | 62/2 |  | 62/3 |  | 62/4 |  | 62/5 |  | 62/6 |  | 62/7 |  | 62/8 |  | 62/9 |  | 62/10 |  | 62/11 |  | 63/0 |  | 63/1 |  | 63/2 |  | 63/3 |  | 63/4 |  | 63/5 |  | 63/6 |  | 63/7 |  | 63/8 |  | 64/0 |  | 64/1
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8531.5
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 386 | DRY | 400 | DRY | 401 | DRY | 403 | DRY | 404 | DRY | 423 | DRY | 409 | DFR | 409 | DFR | 411 | DFR | 413 | DRY | 386.1 | DFR | 400 | DFR | 416 | DFR | 411 | DFR | 399 | DRY | 413 | DFR | 426 | DRY | 413 | DRY | 425 | DRY | 408.3 | DRY | 375.1 | DRY | 0 | 13 | 8 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8531.5
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DC1+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB2+0 |  | DA+0
| LE |  | 0,1,0,0 |  | ,,, |  | ,,, |  | 0,0,0,0 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 0,0,0,0 |  | ,,, |  | ,,, |  | 0,0,0,0 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 421 |  | 422 |  | 423 |  | 424 |  | 425 |  | 426 |  | 427 |  | 428 |  | 429 |  | 430 |  | 431 |  | 432 |  | 433 |  | 434 |  | 435 |  | 436 |  | 437 |  | 438 |  | 439 |  | 440 |  | 441
|  |  | 64/2 |  | 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | 64/7 |  | 64/8 |  | 64/9 |  | 64/10 |  | 64/11 |  | 65/0 |  | 65/1 |  | 65/2 |  | 65/3 |  | 65/4 |  | 65/5 |  | 65/6 |  | 65/7 |  | 65/8 |  | 65/9 |  | 65/10
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8463.9
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 408.7 | DRY | 410.7 | DRY | 408.2 | DRY | 426.2 | DRY | 407.7 | DRY | 401.6 | DRY | 425.5 | DRY | 414.4 | DRY | 410.6 | DRY | 428.4 | DRY | 400.6 | DRY | 395.4 | DRY | 393.7 | DRY | 403.7 | DRY | 402.9 | DRY | 376.4 | DRY | 389.2 | DRY | 397.6 | DRY | 394.3 | DRY | 389 | DRY | 379.1 | DRY | 0 | 21 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8463.9
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 442 |  | 443 |  | 444 |  | 445 |  | 446 |  | 447 |  | 448 |  | 449 |  | 450 |  | 451 |  | 452 |  | 453 |  | 454 |  | 455 |  | 456 |  | 457 |  | 458 |  | 459 |  | 460 |  | 461 |  | 462
|  |  | 65/11 |  | 66/0 |  | 67/0 |  | 67/1 |  | 67/2 |  | 68/0 |  | 69/0 |  | 69/1 |  | 70/0 |  | 70/1 |  | 70/2 |  | 70/3 |  | 70/4 |  | 70/5 |  | 70/6 |  | 70/7 |  | 70/8 |  | 70/9 |  | 70/10 |  | 70/11 |  | 71/0
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8020.2
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 387.6 | DRY | 426.9 | DRY | 207.8 | DRY | 347.1 | DRY | 344.9 | DRY | 369.2 | DRY | 200.9 | DFR | 374.1 | DRY | 394.9 | DRY | 388.4 | DRY | 418.9 | DRY | 418.6 | DRY | 414 | DRY | 419.6 | DRY | 420.3 | DRY | 419.6 | DRY | 418.2 | DRY | 414.1 | DRY | 406.1 | DRY | 408.6 | DRY | 420.4 | DRY | 0 | 20 | 1 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8020.2
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+0 |  | DC2+6 |  | DC1+9 |  | DA+0 |  | DA+0 |  | DD45+0 |  | DB2+0 |  | DA+3 |  | DC1+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB2+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 463 |  | 464 |  | 465 |  | 466 |  | 467 |  | 468 |  | 469 |  | 470 |  | 471 |  | 472 |  | 473 |  | 474 |  | 475 |  | 476 |  | 477 |  | 478 |  | 479 |  | 480 |  | 481 |  | 482 |  | 483
|  |  | 71/1 |  | 71/2 |  | 71/3 |  | 71/4 |  | 71/5 |  | 71/6 |  | 71/7 |  | 71/8 |  | 72/0 |  | 72/1 |  | 72/2 |  | 72/3 |  | 73/0 |  | 73/1 |  | 73/2 |  | 73/3 |  | 73/4 |  | 73/5 |  | 73/6 |  | 73/7 |  | 73/8
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8334.2
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 398.6 | DRY | 414.3 | DRY | 413 | DRY | 367.7 | DRY | 429.4 | DRY | 408 | DRY | 404.9 | DRY | 431.6 | DRY | 408.4 | DRY | 435.3 | DRY | 403.9 | DRY | 389.2 | DRY | 400.1 | DRY | 383.3 | DRY | 379 | DRY | 381.2 | DRY | 384.7 | DRY | 368.8 | DRY | 365.5 | DRY | 392.4 | DRY | 374.9 | DRY | 0 | 21 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8334.2
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DB2+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 484 |  | 485
|  |  | 73/9 |  | 74/0
|  | , |  | , | [52 empty] | 0 | 0 | 758.4
| ERE |  | E |  | E
| WELD |  | Done |  | Done
| FDN | 379.5 | DRY | 378.9 | Sandy |  |  |  | Towards Beawar S/S | [34 empty] | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 2 |  |  | 758.4
| EAR |  | C |  | C
| TOT |  | DA+0 |  | DB2+0
| LE |  | ,,, |  | ,,,
REM
Progress overview (Tower wise breakups)
| TOT |  | Total Qty. in No's |  | Wight of individual towers in MT | Progress breakups dashboard | [15 empty] | Notepad:- |  |  | PKG F
[6 empty] | FDN |  | ERE | [12 empty] | JMC Status
[6 empty] | Comp. | Balance | Comp. | Erected Weight (MT) |  | Balance | Balance to erect (MT) | [8 empty] | Description |  |  | Total Completed | Total Approved | Balance | CTQ approved | CTQ approval awaited | CTQ not initiated
| DA+0 |  | 150 |  | 37.5044 | 150 | 0 | 150 | 5625.6558 |  | 0 | 0 | [8 empty] | Foundation |  |  | 485
| DA+3 |  | 161 |  | 38.8476 | 161 | 0 | 161 | 6254.4646 |  | 0 | 0 | [8 empty] | Erection |  |  | 485
| DA+6 |  | 48 |  | 45.413 | 48 | 0 | 48 | 2179.8253 |  | 0 | 0
| DA+9 |  | 38 |  | 47.1844 | 38 | 0 | 38 | 1793.0053 |  | 0 | 0
| DB1+0 |  | 13 |  | 57.5972 | 13 | 0 | 13 | 748.7641 |  | 0 | 0
| DB1+3 |  | 3 |  | 60.0968 | 3 | 0 | 3 | 180.2903 |  | 0 | 0
| DB1+6 |  | 3 |  | 67.8737 | 3 | 0 | 3 | 203.621 |  | 0 | 0
| DB1+9 |  | 3 |  | 70.7017 | 3 | 0 | 3 | 212.1051 |  | 0 | 0
| DB2+0 |  | 14 |  | 57.5972 | 14 | 0 | 14 | 806.3614 |  | 0 | 0
| DB2+3 |  | 4 |  | 60.0968 | 4 | 0 | 4 | 240.3871 |  | 0 | 0
| DB2+6 |  | 3 |  | 67.8737 | 3 | 0 | 3 | 203.621 |  | 0 | 0
| DB2+9 |  | 2 |  | 70.7017 | 2 | 0 | 2 | 141.4034 |  | 0 | 0
| DC1+0 |  | 12 |  | 66.3811 | 12 | 0 | 12 | 796.5733 |  | 0 | 0
| DCT+0 |  | 1 |  | 94.2199 | 1 | 0 | 1 | 94.2199 |  | 0 | 0
| DC1+3 |  | 1 |  | 69.2287 | 1 | 0 | 1 | 69.2287 |  | 0 | 0
| DC1+6 |  | 2 |  | 78.132 | 2 | 0 | 2 | 156.2641 |  | 0 | 0
| DC1+9 |  | 1 |  | 81.4946 | 1 | 0 | 1 | 81.4946 |  | 0 | 0
| DC2+0 |  | 9 |  | 66.3811 | 9 | 0 | 9 | 597.43 |  | 0 | 0
| DC2+3 |  | 0 |  | 69.2287 | 0 | 0 | 0 | 0 |  | 0 | 0
| DC2+6 |  | 1 |  | 78.132 | 1 | 0 | 1 | 78.132 |  | 0 | 0
| DC2+9 |  | 0 |  | 81.4946 | 0 | 0 | 0 | 0 |  | 0 | 0
| DD45+0 |  | 2 |  | 86.1293 | 2 | 0 | 2 | 172.2586 |  | 0 | 0
| DD45+3 |  | 2 |  | 89.9096 | 2 | 0 | 2 | 179.8193 |  | 0 | 0
| DD60+0 |  | 3 |  | 86.1293 | 3 | 0 | 3 | 258.3878 |  | 0 | 0
| DD60+3 |  | 1 |  | 89.9096 | 1 | 0 | 1 | 89.9096 |  | 0 | 0
| DD60+6 |  | 2 |  | 100.968 | 2 | 0 | 2 | 201.936 |  | 0 | 0
| DD60+9 |  | 0 |  | 105.0682 | 0 | 0 | 0 | 0 |  | 0 | 0
| DD60+18 |  | 1 |  | 129.111 | 1 | 0 | 1 | 129.111 |  | 0 | 0
| DD60+25 |  | 5 |  | 143.6019 | 5 | 0 | 5 | 718.0094 |  | 0 | 0
| Total |  | 485 |  |  | 485 | 0 | 485 | 22212.2786 |  | 0 | 0
Global Footprint in 110+ countries*
*Includes EPC and Supply
TATA PORTION
TATA PORTION
TATA PORTION

## Visual chart Edit
Progress Summary'!A1
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Data taken from Pramanand mail dated 12/12/24.
Sr. No. | PKG G
| Loc No | TOT | A | B | C | D | CONCATANATE (A,B,C,D) | Span length | Remarks | FDN | Erection | Tackwelding
0 | Gty
1 | 1/0 | DD60+0 |  |  |  |  | ,,, | 122 |  | DRY | E | Done
2 | 1A/0 | DD60+0 |  |  |  |  | ,,, | 90 | As per approved 0,0,0,1 | DRY | E | Done
3 | 1A/1 | DA+6 |  |  |  |  | ,,, | 277.7 |  | DFR | E | Done
4 | 1A/2 | DA+0 |  | 1 | 1 |  | ,1,1, | 386 |  | DRY | E | Done
5 | 1A/3 | DA+0 |  |  |  |  | ,,, | 443.6 |  | DRY | E | Done
6 | 1A/4 | DA+3 |  |  | 1 |  | ,,1, | 333.4 |  | DFR | E | Done
7 | 1A/5 | DA+0 | 1 | 1 |  |  | 1,1,, | 431.9 |  | DRY | E | Done
8 | 1A/6 | DA+0 | 1 |  |  | 1 | 1,,,1 | 348.7 |  | Sandy | E | Done
9 | 1A/7 | DA+3 |  | 1 |  |  | ,1,, | 395.7 |  | Sandy | E | Done
10 | 1A/8 | DA+0 |  |  |  |  | ,,, | 415 |  | Sandy | E | Done
11 | 2/0 | DC1+0 |  |  |  |  | ,,, | 394.3 |  | DRY | E | Done
12 | 2/1 | DA+3 |  |  |  |  | ,,, | 405.3 |  | Sandy | E | Done
13 | 2/2 | DA+3 |  |  |  | 1 | ,,,1 | 338.5 |  | Sandy | E | Done
14 | 2/3 | DA+3 | 1 |  | 1 | 1 | 1,,1,1 | 406 |  | Sandy | E | Done
15 | 2/4 | DA+3 |  |  |  |  | ,,, | 429 |  | Sandy | E | Done
16 | 2/5 | DA+3 |  |  | 1 | 1 | ,,1,1 | 411.6 |  | Sandy | E | Done
17 | 2/6 | DA+3 |  |  |  | 1 | ,,,1 | 425.7 |  | Sandy | E | Done
18 | 2/7 | DA+3 |  |  |  |  | ,,, | 408.2 |  | Sandy | E | Done
19 | 2/8 | DA+0 |  |  |  |  | ,,, | 354.6 |  | Sandy | E | Done
20 | 2/9 | DA+0 |  |  |  |  | ,,, | 308.7 |  | DRY | E | Done
21 | 3/0 | DD60+6 |  |  |  |  | ,,, | 336 |  | DRY | E | Done
22 | 4/0 | DD60+6 |  |  |  |  | ,,, | 226.5 |  | DRY | E | Done
23 | 4/1 | DA+0 |  |  |  |  | ,,, | 343 |  | DRY | E | Done
24 | 4/2 | DA+0 |  |  |  |  | ,,, | 358.4 |  | DRY | E | Done
25 | 4/3 | DA+0 |  |  |  |  | ,,, | 381 |  | DRY | E | Done
26 | 4/4 | DA+0 |  |  |  |  | ,,, | 367.6 |  | DRY | E | Done
27 | 5/0 | DB1+9 | 5 | 5 | 5 | 5 | 5,5,5,5 | 423.1 |  | DRY | E | Done
28 | 6/0 | DB2+9 | 5 | 5 | 5 | 5 | 5,5,5,5 | 246 |  | DRY | E | Done
29 | 6/1 | DA+0 |  |  |  |  | ,,, | 429.9 |  | DFR | E | Done
30 | 6/2 | DA+0 |  |  |  |  | ,,, | 362.4 |  | DFR | E | Done
31 | 7/0 | DB1+0 | 2 | 3 | 3 | 2 | 2,3,3,2 | 347.9 |  | DRY | E | Done
32 | 8/0 | DB1+0 |  |  |  |  | ,,, | 210.8 |  | DRY | E | Done
33 | 8/1 | DA+3 |  |  |  |  | ,,, | 409.2 |  | DRY | E | Done
34 | 8/2 | DA+3 |  |  |  |  | ,,, | 413.6 |  | DRY | E | Done
35 | 8/3 | DA+0 |  |  |  |  | ,,, | 393.2 |  | DRY | E | Done
36 | 8/4 | DA+3 |  |  |  |  | ,,, | 416.5 |  | DRY | E | Done
37 | 8/5 | DA+3 |  |  |  | 1 | ,,,1 | 394.6 |  | DRY | E | Done
38 | 8/6 | DA+3 |  |  |  |  | ,,, | 393.2 |  | DRY | E | Done
39 | 8/7 | DB1+0 |  |  |  |  | ,,, | 441.1 |  | DRY | E | Done
40 | 8/8 | DA+6 |  |  |  |  | ,,, | 414.4 |  | DRY | E | Done
41 | 8/9 | DA+3 |  |  |  |  | ,,, | 395.863 |  | DFR | E | Done
42 | 8/10 | DA+3 |  |  |  |  | ,,, | 413.404 |  | DFR | E | Done
43 | 8/11 | DA+0 |  |  |  |  | ,,, | 402.6 |  | DRY | E | Done
44 | 8/12 | DA+0 |  |  |  |  | ,,, | 372.1 |  | DRY | E | Done
45 | 9/0 | DD60+18 |  |  |  |  | ,,, | 457.7 |  | DRY | E | Done
46 | 10/0 | DD60+25 |  |  |  |  | ,,, | 233.1 |  | DFR | E | Done
47 | 10/1 | DA+0 |  |  |  |  | ,,, | 443.7 |  | DRY | E | Done
48 | 10/2 | DA+0 |  |  |  |  | ,,, | 383.2 |  | DFR | E | Done
49 | 10/3 | DA+0 |  |  |  |  | ,,, | 398.6 |  | DFR | E | Done
50 | 10/4 | DA+3 |  |  |  |  | ,,, | 410.7 |  | DFR | E | Done
51 | 10/5 | DA+3 |  |  |  |  | ,,, | 416.2 |  | DRY | E | Done
52 | 10/6 | DA+0 |  |  |  |  | ,,, | 403.4 |  | DFR | E | Done
53 | 10/7 | DA+3 |  |  |  |  | ,,, | 373.845 |  | DRY | E | Done
54 | 10/8 | DA+3 |  |  |  |  | ,,, | 411.823 |  | DFR | E | Done
55 | 10/9 | DA+0 |  |  |  |  | ,,, | 414.2 |  | DRY | E | Done
56 | 10/10 | DA+3 |  |  |  |  | ,,, | 402.3 |  | Sandy | E | Done
57 | 10/11 | DA+3 |  |  |  |  | ,,, | 430.3 |  | DRY | E | Done
58 | 10/12 | DB1+0 |  |  |  |  | ,,, | 406.2 |  | DRY | E | Done
59 | 10/13 | DA+3 |  |  |  |  | ,,, | 405.3 |  | DRY | E | Done
60 | 10/14 | DA+3 |  |  |  |  | ,,, | 427.1 |  | DRY | E | Done
61 | 10/15 | DA+3 |  |  |  |  | ,,, | 400 |  | DRY | E | Done
62 | 10/16 | DA+3 |  |  |  |  | ,,, | 412.8 |  | DRY | E | Done
63 | 10/17 | DA+3 |  |  |  |  | ,,, | 387.8 |  | DFR | E | Done
64 | 10/18 | DA+3 |  |  |  |  | ,,, | 436.7 |  | DFR | E | Done
65 | 10/19 | DA+0 |  |  |  |  | ,,, | 403.7 |  | DRY | E | Done
66 | 10/20 | DA+3 |  |  |  |  | ,,, | 409.5 |  | DFR | E | Done
67 | 10/21 | DA+3 |  |  |  |  | ,,, | 418.6 |  | DFR | E | Done
68 | 10/22 | DA+0 | 1 | 3 |  |  | 1,3,, | 410.3 |  | Sandy | E | Done
69 | 10/23 | DA+0 |  | 2 |  |  | ,2,, | 384 |  | Sandy | E | Done
70 | 11/0 | DB1+0 | 1 | 4 |  | 3 | 1,4,,3 | 450.8 |  | Sandy | E | Done
71 | 11/1 | DA+0 |  |  |  |  | ,,, | 384.2 |  | Sandy | E | Done
72 | 11/2 | DA+0 | 2 | 1 |  |  | 2,1,, | 338.6 |  | Sandy | E | Done
73 | 11/3 | DA+0 |  |  |  | 1 | ,,,1 | 370.7 |  | Sandy | E | Done
74 | 11/4 | DA+0 |  |  |  |  | ,,, | 434.1 |  | Sandy | E | Done
75 | 11/5 | DA+0 |  |  |  |  | ,,, | 368.1 |  | DFR | E | Done
76 | 11A/0 | DB1+0 |  |  |  |  | ,,, | 342.3 |  | DRY | E | Done
77 | 11A/1 | DA+3 |  |  |  |  | ,,, | 405.1 |  | DRY | E | Done
78 | 11A/2 | DA+0 |  |  |  |  | ,,, | 412.2 |  | DRY | E | Done
79 | 11A/3 | DA+3 |  |  |  |  | ,,, | 412.2 |  | DRY | E | Done
80 | 11A/4 | DA+3 |  |  |  |  | ,,, | 422.1 |  | DRY | E | Done
81 | 11A/5 | DA+3 |  |  |  |  | ,,, | 418.3 |  | DRY | E | Done
82 | 11A/6 | DA+6 |  |  |  |  | ,,, | 384.3 |  | DRY | E | Done
83 | 11A/7 | DA+9 |  |  |  |  | ,,, | 434.2 |  | Sandy | E | Done
84 | 11A/8 | DA+6 |  | 2 | 4 | 1 | ,2,4,1 | 390.1 |  | Sandy | E | Done
85 | 11A/9 | DA+3 |  |  |  |  | ,,, | 426.3 |  | DRY | E | Done
86 | 12/0 | DD60+0 |  |  |  |  | ,,, | 405.9 |  | DRY | E | Done
87 | 13/0 | DD60+3 |  |  |  |  | ,,, | 211.9 |  | DRY | E | Done
88 | 13/1 | DA+9 |  |  |  |  | ,,, | 464.3 |  | DRY | E | Done
89 | 13/2 | DA+3 |  |  |  |  | ,,, | 373.7 |  | DRY | E | Done
90 | 13/3 | DA+3 |  |  | 2 | 4 | ,,2,4 | 419.7 |  | Sandy | E | Done
91 | 13/4 | DA+3 |  |  |  |  | ,,, | 420.3 |  | DRY | E | Done
92 | 14/0 | DC2+0 |  |  |  |  | ,,, | 400 |  | Sandy | E | Done
93 | 14A/0 | DC1+0 |  |  |  |  | ,,, | 381.4 |  | DRY | E
94 | 14A/1 | DA+3 |  |  |  |  | ,,, | 412.765 |  | DRY | E | Done
95 | 14A/2 | DA+0 |  |  |  |  | ,,, | 396.029 |  | DRY | E | Done
96 | 15/0 | DC1+0 |  |  |  |  | ,,, | 383.3 |  | DRY | E | Done
97 | 15/1 | DA+3 |  |  |  |  | ,,, | 404.6 |  | DRY | E | Done
98 | 16/0 | DC1+0 |  |  |  |  | ,,, | 413.3 |  | DRY | E | Done
99 | 16/1 | DA+0 |  |  |  |  | ,,, | 354.283 |  | DRY | E | Done
100 | 16/2 | DA+0 | 1 |  |  | 1 | 1,,,1 | 424.28 |  | DRY | E | Done
101 | 16/3 | DA+3 |  |  |  |  | ,,, | 340.3 |  | DRY | E | Done
102 | 16/4 | DA+0 |  | 1 |  |  | ,1,, | 394.7 |  | DRY | E | Done
103 | 16/5 | DA+3 |  |  |  |  | ,,, | 435.863 |  | DRY | E | Done
104 | 17/0 | DB2+3 |  |  |  | 1 | ,,,1 | 386.8 |  | DRY | E | Done
105 | 17/1 | DA+3 |  |  |  |  | ,,, | 393.7 |  | DRY | E | Done
106 | 17/2 | DA+6 |  |  |  |  | ,,, | 415.9 |  | DRY | E
107 | 17/3 | DA+0 |  |  |  |  | ,,, | 422.8 |  | DRY | E
108 | 17/4 | DA+3 |  |  |  |  | ,,, | 409.9 |  | DRY | E | Done
109 | 17/5 | DA+3 |  |  |  |  | ,,, | 425.3 |  | DRY | E
110 | 18/0 | DC2+0 |  |  |  |  | ,,, | 383.4 |  | DRY | E | Done
111 | 18/1 | DA+0 |  |  |  |  | ,,, | 372.8 |  | DRY | E | Done
112 | 18/2 | DA+0 |  |  |  |  | ,,, | 379.8 |  | DRY | E
113 | 18/3 | DA+0 |  |  |  |  | ,,, | 371 |  | DRY | E | Done
114 | 18/4 | DA+0 |  |  |  |  | ,,, | 398.7 |  | DRY | E | Done
115 | 19/0 | DC2+0 |  |  |  |  | ,,, | 380.8 |  | DRY | E | Done
116 | 19/1 | DA+0 |  |  |  |  | ,,, | 366.9 |  | DRY | E
117 | 19/2 | DA+0 |  |  |  |  | ,,, | 372.5 |  | DRY | E | Done
118 | 19/3 | DA+0 |  |  |  |  | ,,, | 376.5 |  | DRY | E
119 | 19/4 | DA+0 |  |  |  |  | ,,, | 384.3 |  | DRY | E
120 | 19/5 | DA+0 |  |  |  |  | ,,, | 375.4 |  | DRY | E
121 | 20/0 | DB2+0 |  |  |  |  | ,,, | 381.2 |  | Sandy | E
122 | 20/1 | DA+0 |  |  |  |  | ,,, | 386.8 |  | Sandy | E | Done
123 | 20/2 | DA+0 |  |  |  |  | ,,, | 387 |  | DRY | E | Done
124 | 20/3 | DA+0 |  |  |  |  | ,,, | 348.5 |  | DRY | E | Done
125 | 21/0 | DB2+0 |  |  |  |  | ,,, | 355 |  | DRY | E
126 | 21/1 | DA+6 |  |  |  |  | ,,, | 414.9 |  | DRY | E
127 | 21/2 | DA+0 |  |  |  |  | ,,, | 407.2 |  | Sandy | E | Done
128 | 21/3 | DA+6 |  |  |  |  | ,,, | 432.2 |  | Sandy | E | Done
129 | 21/4 | DA+3 |  | 1 | 2 | 1 | ,1,2,1 | 401.9 |  | Sandy | E | Done
130 | 21/5 | DA+6 |  |  |  |  | ,,, | 434.2 |  | DFR | E | Done
131 | 21/6 | DA+3 |  |  |  |  | ,,, | 405.5 |  | DRY | E | Done
132 | 21/7 | DA+3 |  |  |  |  | ,,, | 426 |  | DFR | E | Done
133 | 21/8 | DA+6 |  |  |  |  | ,,, | 406.9 |  | DRY | E | Done
134 | 21/9 | DA+3 |  |  |  |  | ,,, | 433.3 |  | DFR | E
135 | 21/10 | DA+6 |  |  |  |  | ,,, | 372.9 |  | DRY | E | Done
136 | 22/0 | DB2+3 |  |  |  |  | ,,, | 443.5 |  | DRY | E
137 | 22/1 | DA+9 |  |  |  |  | ,,, | 456.3 |  | Sandy | E
138 | 22/2 | DA+6 |  |  |  | 2 | ,,,2 | 379.2 |  | Sandy | E
139 | 22/3 | DA+9 |  |  |  | 1 | ,,,1 | 382.6 |  | Sandy | E
140 | 22/4 | DA+9 |  |  |  |  | ,,, | 435.6 |  | Sandy | E | Done
141 | 22/5 | DA+9 | 2 | 2 | 2 | 2 | 2,2,2,2 | 402.1 |  | DRY | E
142 | 22/6 | DA+0 |  |  |  | 1 | ,,,1 | 417.3 |  | Sandy | E
143 | 22/7 | DA+0 |  | 1 |  | 1 | ,1,,1 | 347.7 |  | Sandy | E
144 | 22/8 | DB1+0 |  | 2 | 1 | 1 | ,2,1,1 | 356.3 |  | Sandy | E | Done
145 | 22/9 | DA+6 |  |  |  |  | ,,, | 389.2 |  | Sandy | E | Done
146 | 22/10 | DA+6 | 1 | 2 |  |  | 1,2,, | 343.8 |  | Sandy | E | Done
147 | 22/11 | DA+6 |  | 2 |  |  | ,2,, | 395.5 |  | Sandy | E
148 | 22/12 | DA+3 | 1 | 2 |  |  | 1,2,, | 408 |  | Sandy | E | Done
149 | 22/13 | DA+6 |  |  | 1 |  | ,,1, | 318 |  | Sandy | E | Done
150 | 23/0 | DD45+3 | 2 | 2 | 2 | 2 | 2,2,2,2 | 447.3 |  | DRY | E | Done
151 | 24/0 | DD45+3 | 2 | 2 | 2 | 2 | 2,2,2,2 | 222.2 |  | DRY | E | Done
152 | 25/0 | DC1+6 |  |  |  |  | ,,, | 433.9 |  | DRY | E | Done
153 | 25/1 | DA+3 |  |  |  |  | ,,, | 422.3 |  | DRY | E | Done
154 | 25/2 | DA+0 |  |  |  |  | ,,, | 370.7 |  | DRY | E | Done
155 | 25/3 | DA+0 | 1 | 2 |  | 2 | 1,2,,2 | 345.7 |  | Sandy | E | Done
156 | 25/4 | DA+0 | 1 | 1 |  | 1 | 1,1,,1 | 391.1 |  | Sandy | E | Done
157 | 26/0 | DB1+0 |  |  |  |  | ,,, | 440.4 |  | DFR | E | Done
158 | 26/1 | DA+0 |  |  |  |  | ,,, | 391.4 |  | DRY | E | Done
159 | 26/2 | DA+3 |  |  |  |  | ,,, | 406.5 |  | DFR | E | Done
160 | 26/3 | DA+0 |  |  |  |  | ,,, | 418 |  | DRY | E | Done
161 | 26/4 | DA+6 | 1 |  |  |  | 1,,, | 422.6 |  | Sandy | E | Done
162 | 26/5 | DA+6 | 1 | 1 |  |  | 1,1,, | 410 |  | Sandy | E | Done
163 | 26/6 | DA+6 |  | 1 | 1 |  | ,1,1, | 363.4 |  | Sandy | E | Done
164 | 26/7 | DA+0 |  |  |  |  | ,,, | 421.9 |  | DFR | E | Done
165 | 26/8 | DA+6 |  |  |  |  | ,,, | 416.7 |  | DFR | E | Done
166 | 27/0 | DC1+0 |  |  |  |  | ,,, | 413.8 |  | DFR | E | Done
167 | 27/1 | DA+3 |  |  |  |  | ,,, | 399.8 |  | DFR | E | Done
168 | 27/2 | DA+3 |  |  |  |  | ,,, | 425.2 |  | DFR | E | Done
169 | 27/3 | DA+3 |  |  |  |  | ,,, | 398.6 |  | DFR | E | Done
170 | 27/4 | DA+3 |  |  |  |  | ,,, | 430.7 |  | DFR | E | Done
171 | 27/5 | DA+0 |  |  |  |  | ,,, | 410 |  | DRY | E | Done
172 | 27/6 | DA+0 |  |  |  |  | ,,, | 402.6 |  | Sandy | E | Done
173 | 27/7 | DB1+0 |  |  |  |  | ,,, | 343.5 |  | DFR | E | Done
174 | 27/8 | DA+0 |  |  |  |  | ,,, | 392 |  | DFR | E | Done
175 | 27/9 | DA+0 |  |  |  |  | ,,, | 381.1 |  | DFR | E | Done
176 | 27/10 | DA+3 |  |  |  |  | ,,, | 366.3 |  | DFR | E | Done
177 | 27/11 | DA+3 |  |  |  |  | ,,, | 420.1 |  | DRY | E | Done
178 | 27/12 | DA+3 |  |  |  |  | ,,, | 420.8 |  | Sandy | E | Done
179 | 28/0 | DB2+0 |  |  |  |  | ,,, | 406.6 |  | DFR | E | Done
180 | 28/1 | DA+0 |  |  |  |  | ,,, | 379.6 |  | DRY | E | Done
181 | 28/2 | DA+0 |  |  |  |  | ,,, | 385 |  | DFR | E | Done
182 | 28/3 | DA+0 |  |  |  |  | ,,, | 369 |  | DFR | E | Done
183 | 28/4 | DA+0 |  |  |  |  | ,,, | 409 |  | Sandy | E | Done
184 | 28/5 | DA+9 |  | 2 |  |  | ,2,, | 422 |  | Sandy | E | Done
185 | 28/6 | DA+6 | 1 | 4 | 3 |  | 1,4,3, | 370 |  | Sandy | E | Done
186 | 28/7 | DA+3 | 1 | 3 | 2 |  | 1,3,2, | 464 |  | Sandy | E | Done
187 | 28/8 | DA+3 |  |  | 5 | 3 | ,,5,3 | 375 |  | Sandy | E | Done
188 | 29/0 | DB1+0 |  |  |  |  | ,,, | 465.5 |  | DRY | E | Done
189 | 29/1 | DA+3 |  |  |  |  | ,,, | 365.6 |  | DRY | E | Done
190 | 29/2 | DA+3 |  |  |  |  | ,,, | 424 |  | DRY | E | Done
191 | 29/3 | DA+0 |  |  |  |  | ,,, | 399 |  | Sandy | E | Done
192 | 29/4 | DA+6 |  |  |  |  | ,,, | 440 |  | DRY | E | Done
193 | 30/0 | DC1+0 |  |  |  |  | ,,, | 382.1 |  | DRY | E | Done
194 | 30/1 | DA+0 | 2 |  |  |  | 2,,, | 388.9 |  | Sandy | E | Done
195 | 30/2 | DA+0 | 1 | 2 |  |  | 1,2,, | 445 |  | Sandy | E | Done
196 | 30/3 | DA+3 | 1 | 2 |  |  | 1,2,, | 395 |  | Sandy | E | Done
197 | 30/4 | DA+3 |  |  |  |  | ,,, | 387 |  | DRY | E | Done
198 | 30/5 | DA+3 |  |  |  |  | ,,, | 442 |  | DRY | E | Done
199 | 30/6 | DA+0 |  |  |  |  | ,,, | 314 |  | DRY | E | Done
200 | 31/0 | DB2+0 |  |  |  |  | ,,, | 347.4 |  | Sandy | E | Done
201 | 31/1 | DA+0 |  |  |  |  | ,,, | 383.6 |  | DRY | E | Done
202 | 31/2 | DA+0 |  |  |  |  | ,,, | 366 |  | DRY | E | Done
203 | 32/0 | DC1+0 |  |  |  |  | ,,, | 332.9 |  | DRY | E | Done
204 | 32/1 | DA+3 |  |  |  |  | ,,, | 402.7 |  | Sandy | E | Done
205 | 32/2 | DA+3 |  |  |  |  | ,,, | 428.8 |  | DRY | E | Done
206 | 32/3 | DA+0 |  |  |  |  | ,,, | 410.9 |  | Sandy | E | Done
207 | 32/4 | DA+0 |  |  |  |  | ,,, | 381.1 |  | Sandy | E | Done
208 | 33/0 | DC1+0 | 1 |  |  |  | 1,,, | 451.5 |  | DRY | E | Done
209 | 33/1 | DA+0 |  | 1 | 1 |  | ,1,1, | 379.6 |  | DRY | E | Done
210 | 34/0 | DB2+0 |  |  |  |  | ,,, | 292.5 |  | DRY | E | Done
211 | 34/1 | DA+9 |  |  |  |  | ,,, | 432.6 |  | Sandy | E | Done
212 | 34/2 | DA+6 |  |  |  | 2 | ,,,2 | 407.5 |  | Sandy | E | Done
213 | 34/3 | DA+0 |  | 3 |  |  | ,3,, | 377 |  | Sandy | E | Done
214 | 34/4 | DA+0 |  | 3 | 1 |  | ,3,1, | 451.6 |  | Sandy | E | Done
215 | 35/0 | DB2+6 | 2 |  |  |  | 2,,, | 379.3 |  | Sandy | E | Done
216 | 35/1 | DA+9 | 2 |  |  | 2 | 2,,,2 | 265.6 |  | Sandy | E | Done
217 | 35/2 | DB1+0 | 1 | 1 |  |  | 1,1,, | 492.4 |  | Sandy | E | Done
218 | 35/3 | DB1+6 | 1 |  |  |  | 1,,, | 522.2 |  | Sandy | E | Done
219 | 35/4 | DA+0 |  |  |  |  | ,,, | 418.9 |  | DRY | E | Done
220 | 35/5 | DA+0 |  |  | 4 | 4 | ,,4,4 | 421.7 |  | Sandy | E | Done
221 | 36/0 | DB2+0 |  |  |  |  | ,,, | 342.7 |  | Sandy | E | Done
222 | 36/1 | DA+3 |  |  |  |  | ,,, | 386.4 |  | Sandy | E | Done
223 | 36/2 | DA+0 | 1 | 1 |  |  | 1,1,, | 309.4 |  | Sandy | E | Done
224 | 36/3 | DA+0 |  | 2 |  |  | ,2,, | 357.8 |  | Sandy | E | Done
225 | 36/4 | DA+6 | 2 | 3 |  | 5 | 2,3,,5 | 480.4 |  | Sandy | E | Done
226 | 37/0 | DB2+0 |  |  |  | 1 | ,,,1 | 350.5 |  | Sandy | E | Done
227 | 37/1 | DA+9 | 2 | 2 | 2 | 1 | 2,2,2,1 | 443.3 |  | Sandy | E | Done
228 | 37/2 | DA+3 |  |  |  |  | ,,, | 356.7 |  | Sandy | E | Done
229 | 37/3 | DA+0 |  |  |  |  | ,,, | 339.9 |  | Sandy | E | Done
230 | 38/0 | DB2+6 |  |  |  |  | ,,, | 500.3 |  | Sandy | E | Done
231 | 38/1 | DA+0 |  |  |  |  | ,,, | 421.4 |  | Sandy | E | Done
232 | 38/2 | DA+6 |  |  |  |  | ,,, | 419 |  | Sandy | E | Done
233 | 38/3 | DA+9 | 2 | 2 | 2 | 2 | 2,2,2,2 | 420.3 |  | Sandy | E | Done
234 | 38/4 | DA+9 | 1 | 1 |  | 1 | 1,1,,1 | 414.9 |  | Sandy | E | Done
235 | 39/0 | DB2+6 |  |  |  |  | ,,, | 425.5 |  | Sandy | E | Done
236 | 39/1 | DA+0 |  |  |  |  | ,,, | 412.638 |  | Sandy | E | Done
237 | 40/0 | DC2+0 | 1 | 1 |  |  | 1,1,, | 322.61 |  | Sandy | E | Done
238 | 40/1 | DA+6 | 1 | 2 |  |  | 1,2,, | 396.2 |  | Sandy | E | Done
239 | 40/2 | DA+3 |  |  |  |  | ,,, | 425.8 |  | Sandy | E | Done
240 | 40/3 | DA+3 | 1 | 2 |  |  | 1,2,, | 401.7 |  | Sandy | E | Done
241 | 41/0 | DC1+6 | 3 | 1 |  | 1 | 3,1,,1 | 436.3 |  | Sandy | E | Done
242 | 41/1 | DB1+9 | 4 | 5 | 6 | 6 | 4,5,6,6 | 340.8 |  | Sandy | E | Done
243 | 41/2 | DA+0 |  |  | 1 | 1 | ,,1,1 | 447.8 |  | Sandy | E | Done
244 | 42/0 | DC1+0 | 1 |  |  | 2 | 1,,,2 | 382.3 |  | Sandy | E | Done
245 | 42/1 | DA+6 | 1 |  |  |  | 1,,, | 384.7 |  | Sandy | E | Done
246 | 42/2 | DA+6 |  |  | 1 | 3 | ,,1,3 | 407.4 |  | Sandy | E | Done
247 | 42/3 | DA+0 |  |  |  |  | ,,, | 414.2 |  | Sandy | E | Done
248 | 42/4 | DA+0 |  |  |  |  | ,,, | 256.4 |  | Sandy | E | Done
249 | 42/5 | DA+9 |  |  |  | 1 | ,,,1 | 403.8 |  | Sandy | E | Done
250 | 42/6 | DA+0 | 2 | 1 |  | 2 | 2,1,,2 | 396.7 |  | Sandy | E | Done
251 | 43/0 | DB1+0 |  |  |  |  | ,,, | 403.9 |  | Sandy | E | Done
252 | 43/1 | DA+3 |  |  | 3 | 3 | ,,3,3 | 346 |  | Sandy | E | Done
253 | 43/2 | DA+0 | 1 |  |  | 1 | 1,,,1 | 475.8 |  | Sandy | E | Done
254 | 43/3 | DA+0 |  | 1 |  |  | ,1,, | 363.7 |  | DRY | E | Done
255 | 43/4 | DA+3 | 1 | 1 |  |  | 1,1,, | 431.8 |  | Sandy | E | Done
256 | 43/5 | DA+3 |  |  |  |  | ,,, | 405.3 |  | DRY | E | Done
257 | 43/6 | DA+3 |  |  |  |  | ,,, | 427.8 |  | Sandy | E | Done
258 | 43/7 | DA+3 |  |  |  |  | ,,, | 389.8 |  | Sandy | E | Done
259 | 43/8 | DA+9 | 1 |  |  |  | 1,,, | 449.5 |  | Sandy | E | Done
260 | 43/9 | DA+9 |  |  |  |  | ,,, | 388 |  | Sandy | E | Done
261 | 43/10 | DA+3 | 3 | 3 |  |  | 3,3,, | 346.3 |  | Sandy | E | Done
262 | 43/11 | DA+3 | 2 | 3 |  | 1 | 2,3,,1 | 444.8 |  | Sandy | E | Done
263 | 44/0 | DB1+3 | 0 | 1 | 1 | 0 | 0,1,1,0 | 383.9 |  | Sandy | E | Done
264 | 44/1 | DA+0 | 0 | 0 | 1 | 0 | 0,0,1,0 | 384.3 |  | Sandy | E | Done
265 | 44/2 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 359 |  | Sandy | E | Done
266 | 44/3 | DA+0 | 2 | 0 | 0 | 1 | 2,0,0,1 | 334 |  | Sandy | E | Done
267 | 44/4 | DA+9 | 4 | 3 | 3 | 3 | 4,3,3,3 | 395 |  | Sandy | E | Done
268 | 44/5 | DA+9 | 1 | 3 | 0 | 0 | 1,3,0,0 | 355 |  | Sandy | E | Done
269 | 44/6 | DB1+3 | 1 | 0 | 0 | 1 | 1,0,0,1 | 485 |  | Sandy | E | Done
270 | 44/7 | DA+9 | 0 | 0 | 0 | 0 | 0,0,0,0 | 473 |  | Sandy | E | Done
271 | 44/8 | DCT+0 | 1 | 2 | 0 | 1 | 1,2,0,1 | 367 |  | Sandy | E | Done
272 | 44/9 | DA+9 | 4 | 0 | 2 | 6 | 4,0,2,6 | 430 |  | Sandy | E | Done
273 | 44/10 | DB1+9 | 0 | 1 | 0 | 0 | 0,1,0,0 | 365 |  | Sandy | E | Done
274 | 44/11 | DA+0 | 0 | 1 | 0 | 0 | 0,1,0,0 | 428 |  | Sandy | E | Done
275 | 45/0 | DC2+0 | 0 | 1 | 0 | 0 | 0,1,0,0 | 327.2 |  | Sandy | E | Done
276 | 45/1 | DA+9 | 0 | 0 | 6 | 6 | 0,0,6,6 | 294.92 |  | Sandy | E | Done
277 | 46/0 | DD60+25 | 0 | 6 | 6 | 2 | 0,6,6,2 | 406.54 |  | Sandy | E | Done
278 | 47/0 | DD60+25 | 5 | 5 | 5 | 5 | 5,5,5,5 | 199.08 |  | Sandy | E | Done
279 | 47/1 | DA+3 | 2 | 0 | 2 | 5 | 2,0,2,5 | 441.2 |  | Sandy | E | Done
280 | 47/2 | DA+9 | 0 | 0 | 0 | 0 | 0,0,0,0 | 365.93 |  | Sandy | E | Done
281 | 47/3 | DA+9 | 1 | 2 | 0 | 0 | 1,2,0,0 | 417.4 |  | Sandy | E | Done
282 | 47/4 | DA+3 |  |  |  |  | ,,, | 358.4 |  | Sandy | E | Done
283 | 47/5 | DA+0 | 0 | 1 | 0 | 0 | 0,1,0,0 | 461.2 |  | Sandy | E | Done
284 | 47/6 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 377.3 |  | Sandy | E | Done
285 | 47/7 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 431.5 |  | Sandy | E | Done
286 | 47/8 | DA+0 | 1 | 0 | 0 | 0 | 1,0,0,0 | 398.8 |  | Sandy | E | Done
287 | 47/9 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 405.9 |  | Sandy | E | Done
288 | 47/10 | DA+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 433.7 |  | Sandy | E | Done
289 | 48/0 | DC2+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 386.2 |  | Sandy | E | Done
290 | 48/1 | DA+9 | 0 | 0 | 0 | 0 | 0,0,0,0 | 428.9 |  | Sandy | E | Done
291 | 49/0 | DD45+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 402.9 |  | Sandy | E | Done
292 | 49/1 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 379.1 |  | Sandy | E | Done
293 | 49/2 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 386.6 |  | Sandy | E | Done
294 | 49/3 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 390 |  | Sandy | E | Done
295 | 49/4 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 421.7 |  | Sandy | E | Done
296 | 49/5 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 396.6 |  | Sandy | E | Done
297 | 49/6 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 412.8 |  | Sandy | E | Done
298 | 49/7 | DA+0 | 0 | 3 | 2 | 2 | 0,3,2,2 | 340.2 |  | Sandy | E | Done
299 | 50/0 | DB2+0 | 0 | 0 | 0 | 1 | 0,0,0,1 | 500.2 |  | Sandy | E | Done
300 | 50/1 | DA+6 | 1 | 0 | 0 | 0 | 1,0,0,0 | 469.1 |  | Sandy | E | Done
301 | 50/2 | DA+9 | 2 | 2 | 2 | 2 | 2,2,2,2 | 367.1 |  | Sandy | E | Done
302 | 50/3 | DA+6 | 0 | 0 | 1 | 0 | 0,0,1,0 | 470.4 |  | Sandy | E | Done
303 | 50/4 | DA+9 | 3 | 3 | 4 | 3 | 3,3,4,3 | 354.8 |  | Sandy | E | Done
304 | 50/5 | DA+9 | 4 | 3 | 4 | 3 | 4,3,4,3 | 442.1 |  | Sandy | E | Done
305 | 50/6 | DA+9 | 3 | 4 | 3 | 3 | 3,4,3,3 | 364.4 |  | Sandy | E | Done
306 | 50/7 | DA+0 | 0 | 0 | 0 | 1 | 0,0,0,1 | 470.8 |  | Sandy | E | Done
307 | 50/8 | DA+9 | 0 | 0 | 0 | 0 | 0,0,0,0 | 345 |  | Sandy | E | Done
308 | 50/9 | DA+0 | 0 | 0 | 1 | 0 | 0,0,1,0 | 364.4 |  | Sandy | E | Done
309 | 50/10 | DA+0 | 0 | 0 | 1 | 0 | 0,0,1,0 | 394.6 |  | Sandy | E | Done
310 | 51/0 | DC2+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 401.4 |  | Sandy | E | Done
311 | 51/1 | DA+0 | 0 | 0 | 1 | 0 | 0,0,1,0 | 356.6 |  | Sandy | E | Done
312 | 51/2 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 307.1 |  | Sandy | E | Done
313 | 52/0 | DC2+0 | 0 | 0 | 3 | 3 | 0,0,3,3 | 385 |  | Sandy | E | Done
314 | 52/1 | DA+6 | 0 | 4 | 0 | 0 | 0,4,0,0 | 402 |  | Sandy | E | Done
315 | 52/2 | DA+6 | 0 | 0 | 0 | 3 | 0,0,0,3 | 402.6 |  | Sandy | E | Done
316 | 52/3 | DA+9 | 4 | 3 | 3 | 3 | 4,3,3,3 | 437 |  | Sandy | E | Done
317 | 52/4 | DA+9 | 2 | 2 | 0 | 0 | 2,2,0,0 | 393.8 |  | Sandy | E | Done
318 | 52/5 | DA+9 | 0 | 0 | 0 | 1 | 0,0,0,1 | 447 |  | Sandy | E | Done
319 | 52/6 | DA+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 373 |  | Sandy | E | Done
320 | 52/7 | DA+3 | 0 | 3 | 1 | 0 | 0,3,1,0 | 406.8 |  | Sandy | E | Done
321 | 52/8 | DA+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 433 |  | Sandy | E | Done
322 | 52/9 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 399.7 |  | Sandy | E | Done
323 | 52/10 | DA+9 | 1 | 2 | 1 | 1 | 1,2,1,1 | 384.1 |  | Sandy | E | Done
324 | 53/0 | DB2+9 | 4 | 4 | 4 | 4 | 4,4,4,4 | 455.9 |  | Sandy | E | Done
325 | 53/1 | DA+9 | 4 | 4 | 4 | 4 | 4,4,4,4 | 433.2 |  | Sandy | E | Done
326 | 53/2 | DA+0 | 0 | 0 | 0 | 2 | 0,0,0,2 | 407.4 |  | Sandy | E | Done
327 | 53/3 | DA+6 | 0 | 4 | 1 | 0 | 0,4,1,0 | 394.5 |  | Sandy | E | Done
328 | 53/4 | DA+0 | 0 | 2 | 1 | 0 | 0,2,1,0 | 410.1 |  | Sandy | E | Done
329 | 53/5 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 428.1 |  | Sandy | E | Done
330 | 53/6 | DA+6 | 1 | 1 | 3 | 1 | 1,1,3,1 | 406.6 |  | Sandy | E | Done
331 | 53/7 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 411.3 |  | Sandy | E | Done
332 | 53/8 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 427.8 |  | Sandy | E | Done
333 | 54/0 | DB1+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 371.3 |  | Sandy | E | Done
334 | 54/1 | DA+3 | 1 | 1 | 0 | 0 | 1,1,0,0 | 365.1 |  | Sandy | E | Done
335 | 54/2 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 381 |  | Sandy | E | Done
336 | 54/3 | DA+6 | 0 | 2 | 0 | 0 | 0,2,0,0 | 417 |  | Sandy | E | Done
337 | 54/4 | DA+9 | 1 | 2 | 0 | 0 | 1,2,0,0 | 423.3 |  | Sandy | E | Done
338 | 54/5 | DA+9 | 1 | 3 | 3 | 1 | 1,3,3,1 | 401 |  | Sandy | E | Done
339 | 55/0 | DB1+6 | 0 | 1 | 1 | 0 | 0,1,1,0 | 424 |  | Sandy | E | Done
340 | 55/1 | DA+0 |  |  |  |  | ,,, | 404.9 |  | WFR | E | Done
341 | 55/2 | DA+0 |  |  |  |  | ,,, | 343.1 |  | WFR | E | Done
342 | 55/3 | DA+0 |  |  |  |  | ,,, | 357.7 |  | Sandy | E | Done
343 | 55/4 | DA+0 | 0 | 0 | 0 | 1 | 0,0,0,1 | 365.2 |  | Sandy | E | Done
344 | 55/5 | DA+0 | 0 | 0 | 1 | 3 | 0,0,1,3 | 350.1 |  | Sandy | E | Done
345 | 55/6 | DA+0 | 0 | 0 | 1 | 2 | 0,0,1,2 | 357.7 |  | Sandy | E | Done
346 | 55/7 | DA+0 | 0 | 0 | 1 | 0 | 0,0,1,0 | 337.8 |  | Sandy | E | Done
347 | 55/8 | DA+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 341.22 |  | Sandy | E | Done
348 | 56/0 | DD60+25 | 3 | 3 | 0 | 2 | 3,3,0,2 | 460.49 |  | Sandy | E | Done
349 | 57/0 | DD60+25 | 0 | 0 | 0 | 0 | 0,0,0,0 | 219.76 |  | Sandy | E | Done
350 | 57/1 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 461.1 |  | Sandy | E | Done
351 | 57/2 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 355.5 |  | DRY | E | Done
352 | 57/3 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 405.4 |  | DRY | E | Done
353 | 57/4 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 418.2 |  | Sandy | E | Done
354 | 57/5 | DA+3 | 0 | 0 | 0 | 1 | 0,0,0,1 | 416.8 |  | Sandy | E | Done
355 | 57/6 | DA+3 | 0 | 1 | 0 | 0 | 0,1,0,0 | 395 |  | Sandy | E | Done
356 | 57/7 | DA+3 |  |  |  |  | ,,, | 401.8 |  | DFR | E | Done
357 | 58/0 | DC1+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 433.9 |  | DFR | E | Done
358 | 59/0 | DC2+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 238.9 |  | DRY | E | Done
359 | 59/1 | DA+3 | 0 | 0 | 0 | 1 | 0,0,0,1 | 411.3 |  | DRY | E | Done
360 | 59/2 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 418.2 |  | DFR | E | Done
361 | 59/3 | DA+3 | 0 | 0 | 0 | 1 | 0,0,0,1 | 412.3 |  | DFR | E | Done
362 | 59/4 | DA+3 |  |  |  |  | ,,, | 421 |  | DFR | E | Done
363 | 59/5 | DA+3 |  |  |  |  | ,,, | 419.7 |  | DFR | E | Done
364 | 59/6 | DA+3 |  |  |  |  | ,,, | 419.1 |  | DFR | E | Done
365 | 59/7 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 408.8 |  | DRY | E | Done
366 | 59/8 | DB1+3 |  |  |  |  | ,,, | 426.9 |  | DRY | E | Done
367 | 59/9 | DA+3 |  |  |  |  | ,,, | 434.7 |  | DRY | E | Done
368 | 59/10 | DA+0 |  |  |  |  | ,,, | 400.8 |  | DRY | E | Done
369 | 59/11 | DA+6 | 0 | 0 | 2 | 0 | 0,0,2,0 | 436.3 |  | DFR | E | Done
370 | 59/12 | DA+6 |  |  |  |  | ,,, | 393.1 |  | DFR | E | Done
371 | 59/13 | DA+3 |  |  |  |  | ,,, | 447.4 |  | DRY | E | Done
372 | 59/14 | DA+6 |  |  |  |  | ,,, | 391.1 |  | DRY | E | Done
373 | 59/15 | DA+6 |  |  |  |  | ,,, | 448.6 |  | DRY | E | Done
374 | 59/16 | DA+9 |  |  |  |  | ,,, | 388 |  | Dry | E | Done
375 | 60/0 | DC1+0 |  |  |  |  | ,,, | 438 |  | DRY | E | Done
376 | 60/1 | DA+6 |  |  |  |  | ,,, | 413.8 |  | DRY | E | Done
377 | 60/2 | DA+3 | 2 | 2 | 0 | 0 | 2,2,0,0 | 424.2 |  | DFR | E | Done
378 | 60/3 | DA+3 |  |  |  |  | ,,, | 414.5 |  | DFR | E | Done
379 | 60/4 | DA+3 |  |  |  |  | ,,, | 425.6 |  | DFR | E | Done
380 | 60/5 | DA+3 |  |  |  |  | ,,, | 412.3 |  | DRY | E | Done
381 | 60/6 | DA+0 |  |  |  |  | ,,, | 374.1 |  | DRY | E | Done
382 | 60/7 | DA+3 |  |  |  |  | ,,, | 410.1 |  | DRY | E | Done
383 | 60/8 | DA+0 |  |  |  |  | ,,, | 400.4 |  | DRY | E | Done
384 | 60/9 | DA+3 |  |  |  |  | ,,, | 409.2 |  | DRY | E | Done
385 | 60/10 | DA+0 |  |  |  |  | ,,, | 401 |  | DFR | E | Done
386 | 60/11 | DA+3 |  |  |  |  | ,,, | 394.5 |  | DRY | E | Done
387 | 61/0 | DB2+0 |  |  |  |  | ,,, | 397.9 |  | DRY | E | Done
388 | 61/1 | DA+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 405.7 |  | DFR | E | Done
389 | 61/2 | DA+6 |  |  |  |  | ,,, | 433.2 |  | DFR | E | Done
390 | 61/3 | DA+6 |  |  |  |  | ,,, | 400.9 |  | DRY | E | Done
391 | 61/4 | DA+3 |  |  |  |  | ,,, | 427 |  | DRY | E | Done
392 | 61/5 | DA+3 |  |  |  |  | ,,, | 413.9 |  | DRY | E | Done
393 | 61/6 | DA+3 |  |  |  |  | ,,, | 426.4 |  | DRY | E | Done
394 | 61/7 | DA+9 | 0 | 0 | 0 | 1 | 0,0,0,1 | 411.5 |  | Dry | E | Done
395 | 61/8 | DA+6 | 1 | 2 | 1 | 0 | 1,2,1,0 | 376.3 |  | DRY | E | Done
396 | 61/9 | DA+0 |  |  |  |  | ,,, | 433.4 |  | Dry | E | Done
397 | 61/10 | DA+9 |  |  |  |  | ,,, | 405.6 |  | DRY | E | Done
398 | 62/0 | DB2+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 434.3 |  | DRY | E | Done
399 | 62/1 | DA+3 | 0 | 0 | 1 | 2 | 0,0,1,2 | 418 |  | Sandy | E | Done
400 | 62/2 | DA+3 | 0 | 1 | 0 | 0 | 0,1,0,0 | 386 |  | DRY | E | Done
401 | 62/3 | DA+0 |  |  |  |  | ,,, | 400 |  | DRY | E | Done
402 | 62/4 | DA+3 |  |  |  |  | ,,, | 401 |  | DRY | E | Done
403 | 62/5 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 403 |  | DRY | E | Done
404 | 62/6 | DA+3 |  |  |  |  | ,,, | 404 |  | DRY | E | Done
405 | 62/7 | DA+3 |  |  |  |  | ,,, | 423 |  | DRY | E | Done
406 | 62/8 | DA+0 |  |  |  |  | ,,, | 409 |  | DFR | E | Done
407 | 62/9 | DA+3 |  |  |  |  | ,,, | 409 |  | DFR | E | Done
408 | 62/10 | DA+0 |  |  |  |  | ,,, | 411 |  | DFR | E | Done
409 | 62/11 | DA+3 |  |  |  |  | ,,, | 413 |  | DRY | E | Done
410 | 63/0 | DC1+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 386.1 |  | DFR | E | Done
411 | 63/1 | DA+3 |  |  |  |  | ,,, | 400 |  | DFR | E | Done
412 | 63/2 | DA+0 |  |  |  |  | ,,, | 416 |  | DFR | E | Done
413 | 63/3 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 411 |  | DFR | E | Done
414 | 63/4 | DA+0 |  |  |  |  | ,,, | 399 |  | DRY | E | Done
415 | 63/5 | DA+3 |  |  |  |  | ,,, | 413 |  | DFR | E | Done
416 | 63/6 | DA+3 |  |  |  |  | ,,, | 426 |  | DRY | E | Done
417 | 63/7 | DA+3 |  |  |  |  | ,,, | 413 |  | DRY | E | Done
418 | 63/8 | DA+3 |  |  |  |  | ,,, | 425 |  | DRY | E | Done
419 | 64/0 | DB2+0 |  |  |  |  | ,,, | 408.3 |  | DRY | E | Done
420 | 64/1 | DA+0 |  |  |  |  | ,,, | 375.1 |  | DRY | E | Done
421 | 64/2 | DA+3 |  |  |  |  | ,,, | 408.7 |  | DRY | E | Done
422 | 64/3 | DA+0 |  |  |  |  | ,,, | 410.7 |  | DRY | E | Done
423 | 64/4 | DA+3 |  |  |  |  | ,,, | 408.2 |  | DRY | E | Done
424 | 64/5 | DA+3 |  |  |  |  | ,,, | 426.2 |  | DRY | E | Done
425 | 64/6 | DA+0 |  |  |  |  | ,,, | 407.7 |  | DRY | E | Done
426 | 64/7 | DA+3 |  |  |  |  | ,,, | 401.6 |  | DRY | E | Done
427 | 64/8 | DA+3 |  |  |  |  | ,,, | 425.5 |  | DRY | E | Done
428 | 64/9 | DA+3 |  |  |  |  | ,,, | 414.4 |  | DRY | E | Done
429 | 64/10 | DA+3 |  |  |  |  | ,,, | 410.6 |  | DRY | E | Done
430 | 64/11 | DA+3 |  |  |  |  | ,,, | 428.4 |  | DRY | E | Done
431 | 65/0 | DB1+0 |  |  |  |  | ,,, | 400.6 |  | DRY | E | Done
432 | 65/1 | DA+0 |  |  |  |  | ,,, | 395.4 |  | DRY | E | Done
433 | 65/2 | DA+0 |  |  |  |  | ,,, | 393.7 |  | DRY | E | Done
434 | 65/3 | DA+3 |  |  |  |  | ,,, | 403.7 |  | DRY | E | Done
435 | 65/4 | DA+0 |  |  |  |  | ,,, | 402.9 |  | DRY | E | Done
436 | 65/5 | DA+0 |  |  |  |  | ,,, | 376.4 |  | DRY | E | Done
437 | 65/6 | DA+0 |  |  |  |  | ,,, | 389.2 |  | DRY | E | Done
438 | 65/7 | DA+0 |  |  |  |  | ,,, | 397.6 |  | DRY | E | Done
439 | 65/8 | DA+0 |  |  |  |  | ,,, | 394.3 |  | DRY | E | Done
440 | 65/9 | DA+0 |  |  |  |  | ,,, | 389 |  | DRY | E | Done
441 | 65/10 | DA+0 |  |  |  |  | ,,, | 379.1 |  | DRY | E | Done
442 | 65/11 | DA+0 |  |  |  |  | ,,, | 387.6 |  | DRY | E | Done
443 | 66/0 | DC2+6 |  |  |  |  | ,,, | 426.9 |  | DRY | E | Done
444 | 67/0 | DC1+9 |  |  |  |  | ,,, | 207.8 |  | DRY | E | Done
445 | 67/1 | DA+0 |  |  |  |  | ,,, | 347.1 |  | DRY | E | Done
446 | 67/2 | DA+0 |  |  |  |  | ,,, | 344.9 |  | DRY | E | Done
447 | 68/0 | DD45+0 |  |  |  |  | ,,, | 369.2 |  | DRY | E | Done
448 | 69/0 | DB2+0 |  |  |  |  | ,,, | 200.9 |  | DFR | E | Done
449 | 69/1 | DA+3 |  |  |  |  | ,,, | 374.1 |  | DRY | E | Done
450 | 70/0 | DC1+0 |  |  |  |  | ,,, | 394.9 |  | DRY | E | Done
451 | 70/1 | DA+3 |  |  |  |  | ,,, | 388.4 |  | DRY | E | Done
452 | 70/2 | DA+3 |  |  |  |  | ,,, | 418.9 |  | DRY | E | Done
453 | 70/3 | DA+3 |  |  |  |  | ,,, | 418.6 |  | DRY | E | Done
454 | 70/4 | DA+3 |  |  |  |  | ,,, | 414 |  | DRY | E | Done
455 | 70/5 | DA+3 |  |  |  |  | ,,, | 419.6 |  | DRY | E | Done
456 | 70/6 | DA+3 |  |  |  |  | ,,, | 420.3 |  | DRY | E | Done
457 | 70/7 | DA+3 |  |  |  |  | ,,, | 419.6 |  | DRY | E | Done
458 | 70/8 | DA+3 |  |  |  |  | ,,, | 418.2 |  | DRY | E | Done
459 | 70/9 | DA+3 |  |  |  |  | ,,, | 414.1 |  | DRY | E | Done
460 | 70/10 | DA+3 |  |  |  |  | ,,, | 406.1 |  | DRY | E | Done
461 | 70/11 | DA+3 |  |  |  |  | ,,, | 408.6 |  | DRY | E | Done
462 | 71/0 | DB2+3 |  |  |  |  | ,,, | 420.4 |  | DRY | E | Done
463 | 71/1 | DA+3 |  |  |  |  | ,,, | 398.6 |  | DRY | E | Done
464 | 71/2 | DA+3 |  |  |  |  | ,,, | 414.3 |  | DRY | E | Done
465 | 71/3 | DA+6 |  |  |  |  | ,,, | 413 |  | DRY | E | Done
466 | 71/4 | DA+3 |  |  |  |  | ,,, | 367.7 |  | DRY | E | Done
467 | 71/5 | DA+3 |  |  |  |  | ,,, | 429.4 |  | DRY | E | Done
468 | 71/6 | DA+0 |  |  |  |  | ,,, | 408 |  | DRY | E | Done
469 | 71/7 | DA+3 |  |  |  |  | ,,, | 404.9 |  | DRY | E | Done
470 | 71/8 | DA+3 |  |  |  |  | ,,, | 431.6 |  | DRY | E | Done
471 | 72/0 | DB2+3 |  |  |  |  | ,,, | 408.4 |  | DRY | E | Done
472 | 72/1 | DA+3 |  |  |  |  | ,,, | 435.3 |  | DRY | E | Done
473 | 72/2 | DA+0 |  |  |  |  | ,,, | 403.9 |  | DRY | E | Done
474 | 72/3 | DA+3 |  |  |  |  | ,,, | 389.2 |  | DRY | E | Done
475 | 73/0 | DB2+0 |  |  |  |  | ,,, | 400.1 |  | DRY | E | Done
476 | 73/1 | DA+0 |  |  |  |  | ,,, | 383.3 |  | DRY | E | Done
477 | 73/2 | DA+0 |  |  |  |  | ,,, | 379 |  | DRY | E | Done
478 | 73/3 | DA+0 |  |  |  |  | ,,, | 381.2 |  | DRY | E | Done
479 | 73/4 | DA+0 |  |  |  |  | ,,, | 384.7 |  | DRY | E | Done
480 | 73/5 | DA+0 |  |  |  |  | ,,, | 368.8 |  | DRY | E | Done
481 | 73/6 | DA+0 |  |  |  |  | ,,, | 365.5 |  | DRY | E | Done
482 | 73/7 | DA+0 |  |  |  |  | ,,, | 392.4 |  | DRY | E | Done
483 | 73/8 | DA+3 |  |  |  |  | ,,, | 374.9 |  | DRY | E | Done
484 | 73/9 | DA+0 |  |  |  |  | ,,, | 379.5 |  | DRY | E | Done
485 | 74/0 | DB2+0 |  |  |  |  | ,,, | 378.9 |  | Sandy | E | Done
Note on F112: Raghav Ranjan: in approved survey 1 mrc in pit C & D. but actual no any RC casted
Note on G372: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AS PER APPROVED CHECK SURVEY, 1 M RC IN PIT A BUT SAME WAS REVISED (PIT d IN PLACE OF PIT A) AS PER INSTRUCTION BY SACHCHIDANAND ON DATED 28.08.24

## Benching F
Progress Summary'!A1 | [7 empty] | Total | 35308.5487 | 22312.4407 | 24183.155
[8 empty] | No of Locs | 215 | 175 | 170 | 45
RC, Benching & Revetment Locations
Sr. No. | Loc No. | Tower Type | CP Position Up/Down | Raised Chimney | Chimney Extension |  |  |  | Submitted Benching Volume (Cum) | Approved Benching Volume (Cum) during check survey | Approved Benching Volume (Cum) after execution
[5 empty] | A | B | C | D | Cutting | Cutting | Approved Benching volume in JMC | Soil Type
1 | 1A/0 | DD60+0 |  | 280.663 |  |  |  | 1 | 396.753 | 396.753 | 396.75 | DRY
2 | 1A/2 | DA+0 |  | 289.355 |  | 1 | 1 |  | 135.475 | 126.578 | 126.578 | DRY
3 | 1A/4 | DA+3 |  | 279.611 |  |  | 1 |  | 96.198 | 84.47 | 96.198 | DFR
4 | 1A/5 | DA+0 |  | 283.369 | 1 | 1 |  |  | 90.818 | 90.818
5 | 1A/6 | DA+0 |  | 285.088 | 1 |  |  | 1 | 115.601 | 95.447
6 | 1A/7 | DA+3 |  | 279.351 |  | 1 |  |  | 16.618 | 15.102 | 16.618 | Sandy
7 | 2/2 | DA+3 |  | 286.123 |  |  |  | 1 | 32.393 | 32.393 | 32.393 | Sandy
8 | 2/3 | DA+3 |  | 291.649 | 1 |  | 1 | 1 | 6.352 | 6.352 | 6.352 | Sandy
9 | 2/5 | DA+3 | -0.3 | 295.847 |  |  | 1 | 1 | 37.105 | 37.105 | 37.105 | Sandy
10 | 2/6 | DA+3 |  | 295.748 |  |  |  | 1 | 183.868 | 183.868
11 | 5/0 | DB1+9 |  | 276.367 | 5 | 5 | 5 | 5
12 | 6/0 | DB2+9 |  | 278.864 | 5 | 5 | 5 | 5
13 | 6/2 | DA+0 |  | 285.435 |  |  |  |  | 62.716 | 62.716
14 | 7/0 | DB1+0 |  | 285.258 | 2 | 3 | 3 | 2 | 38.395 | 38.395 | 38.395 | Sandy
15 | 8/1 | DA+3 |  | 277.532 |  |  |  |  | 95.017 | 95.017 | 95.017 | Dry
16 | 8/5 | DA+3 |  | 278.292 |  |  |  | 1 | 36.524 | 36.524 | 36.524 | Dry
17 | 8/11 | DA+0 | 0.1 | 258.784
18 | 10/18 | DA+3 | 0.2 | 263.543
19 | 10/22 | DA+0 | -0.3 | 267.946 | 1 |  |  | 3
20 | 10/23 | DA+0 | -0.3 | 274.896 |  | 2
21 | 11/0 | DB1+0 | -0.3 | 267.684 | 1 | 4 |  | 3
22 | 11/2 | DA+0 |  | 260.632 | 2 | 1
23 | 11/3 | DA+0 | -0.3 | 244.31 |  |  |  | 1
24 | 11A/8 | DA+6 |  | 276.713 |  | 2 | 4 | 1 | 21.332 | 21.332 | 21.331 | Sandy
25 | 13/3 | DA+3 |  | 259.023 |  |  | 2 | 4 | 263.579 | 263.579 | 263.579 | DRY
26 | 15/1 | DA+3 | 0.1 | 257.553
27 | 16/2 | DA+0 |  | 231.584 | 1 |  |  | 1 | 103.375 | 103.375 | 103.375 | DRY
28 | 16/4 | DA+0 |  | 230.932 |  | 1 |  |  | 111.857 | 111.857 | 111.857 | DRY
29 | 17/0 | DB2+3 |  | 231.525 |  |  |  | 1 | 203.454 | 203.454 | 203.454 | DRY
30 | 21/4 | DA+3 | -0.17 | 219.398 |  | 1 | 2 | 1 | 32.563 | 32.563 | 32.563 | Sandy
31 | 22/2 | DA+6 |  | 221.472 |  |  |  | 2 | 150.696 | 150.696 | 198.696 | Sandy
32 | 22/3 | DA+9 | -0.37 | 229.546 |  |  |  | 1 | 156.167 | 156.167 | 156.167 | Sandy
33 | 22/5 | DA+9 |  | 237.504 | 2 | 2 | 2 | 2
34 | 22/6 | DA+0 |  | 228.106 |  |  |  | 1 | 134.906 | 134.906 | 134.906 | Sandy
35 | 22/7 | DA+0 |  | 230.791 |  | 1 |  | 1 | 163.818 | 163.818 | 163.818 | DRY
36 | 22/8 | DB1+0 | -0.25 | 238.053 |  | 2 | 1 | 1 | 42.317 | 42.317 | 42.317 | Sandy
37 | 22/10 | DA+6 |  | 226.251 | 1 | 2 |  |  | 141.305 | 141.305
38 | 22/11 | DA+6 | -0.2 | 219.64 |  | 2 |  |  | 115.216 | 115.216
39 | 22/12 | DA+3 | -0.2 | 219.348 | 1 | 2 |  |  | 273.42 | 273.42 | 322.43 | Sandy
40 | 22/13 | DA+6 | -0.2 | 228.631 |  |  | 1 |  | 156.896 | 156.896 | 156.896 | Sandy
41 | 23/0 | DD45+3 |  | 234.317 | 2 | 2 | 2 | 2
42 | 24/0 | DD45+3 |  | 216.73 | 2 | 2 | 2 | 2
43 | 25/3 | DA+0 | -0.12 | 218.505 | 1 | 2 |  | 2 | 66.405 | 66.405 | 66.405 | Sandy
44 | 25/4 | DA+0 | -0.15 | 214.763 | 1 | 1 |  | 1 | 28.422 | 28.422 | 28.422 | Sandy
45 | 26/4 | DA+6 |  | 213.407 | 1 |  |  |  | 120.137 | 120.137 | 120.137 | Sandy
46 | 26/5 | DA+6 |  | 221.414 | 1 | 1 |  |  | 81.488 | 81.488 | 81.488 | Sandy
47 | 26/6 | DA+6 | 0.6 | 211.524 |  | 1 | 1 |  | 254.213 | 254.213 | 254.213 | Sandy
48 | 28/5 | DA+9 | -0.18 | 214.138 |  | 2 |  |  | 281.983 | 281.983 | 359.86 | Sandy
49 | 28/6 | DA+6 |  | 215.881 | 1 | 4 | 3 |  | 148.097 | 148.097 | 148.097 | Sandy
50 | 28/7 | DA+3 | +0.40 | 205.536 | 1 | 3 | 2 |  | 51.177 | 51.177 | 51.177 | Sandy
51 | 28/8 | DA+3 | +0.20 | 210.955 |  |  | 5 | 3 | 89.36 | 89.36 | 172.933 | Sandy
52 | 30/1 | DA+0 | +0.29 | 207.56 | 2 |  |  |  | 25.504 | 25.504 | 25.504 | Sandy
53 | 30/2 | DA+0 |  | 202.695 | 1 | 2 |  |  | 263.44 | 263.44 | 263.44 | Sandy
54 | 30/3 | DA+3 |  | 197.067 | 1 | 2 |  |  | 59.056 | 59.056 | 59.056 | Sandy
55 | 30/5 | DA+3 | [8 empty] | 478.121 | Dry
56 | 31/0 | DB2+0 | -0.7 | 209.344 |  |  |  |  | 120.033 | 120.033
57 | 33/0 | DC1+0 | -0.25 | 227.212 | 1 |  |  |  | 119.762 | 119.762 | 182.96 | Sandy
58 | 33/1 | DA+0 | -0.5 | 241.549 |  | 1 | 1 |  | 182.96 | 182.96 | 182.96 | Dry
59 | 34/0 | DB2+0 |  | 229.094 |  |  |  |  | 55.9616 | 55.9616
60 | 34/2 | DA+6 |  | 234.416 |  |  |  | 2 | 172.507 | 172.507
61 | 34/3 | DA+0 |  | 222.158 |  | 3 |  |  | 232.822 | 232.822
62 | 34/4 | DA+0 |  | 191.038 |  | 3 | 1 |  | 113.6503 | 113.6503
63 | 35/0 | DB2+6 |  | 190.847 | 2 |  |  |  | 163.1337 | 163.1337 | 163.134 | Sandy
64 | 35/1 | DA+9 |  | 184.479 | 2 |  |  | 2 | 355.4292 | 355.4292 | 284.41 | Sandy
65 | 35/2 | DB1+0 |  | 196.532 | 1 | 1 |  |  | 44.5475 | 44.5475
66 | 35/3 | DB1+6 | +1.0 | 211.007 | 1 |  |  |  | 50.2817 | 50.2817 | 50.28 | Sandy
67 | 35/5 | DA+0 |  | 192.578 |  |  | 4 | 4 | 625.888 | 625.888
68 | 36/2 | DA+0 |  | 185.467 | 1 | 1 |  |  | 83.5731 | 83.5731 | 64.595 | Sandy
69 | 36/3 | DA+0 |  | 196.493 |  | 2 |  |  | 102.3249 | 102.3249 | 88.813 | Sandy
70 | 36/4 | DA+6 |  | 216.948 | 2 | 3 |  | 5 | 138.429 | 138.429 | 93.659 | Sandy
71 | 37/0 | DB2+0 |  | 232.205 |  |  |  | 1 | 162.7886 | 162.7886 | 159.767 | Sandy
72 | 37/1 | DA+9 | +1.0 | 223.469 | 2 | 2 | 2 | 1 | 94.895 | 94.895 | 22.5 | Sandy
73 | 37/2 | DA+3 |  | 217.775 |  |  |  |  | 172.4831 | 172.4831 | 132.116 | Sandy
74 | 37/3 | DA+0 | +1.0 | 218.259 |  |  |  |  | 283.6687 | 283.6687 | 283.669 | Sandy
75 | 38/0 | DB2+6 |  | 183.041 |  |  |  |  | 63.3033 | 63.3033
76 | 38/3 | DA+9 | +1.0 | 195.915 | 2 | 2 | 2 | 2 | 15.318 | 15.318 | 15.318 | Sandy
77 | 38/4 | DA+9 | +1.0 | 188.108 | 1 | 1 |  | 1 | 128.046 | 128.046 | 128.046 | Sandy
78 | 40/0 | DC1+0 |  | 189.11 | 1 | 1 |  |  | 91.75 | 83.997 | 83.997 | Sandy
79 | 40/1 | DA+6 |  | 189.83 | 1 | 2 |  |  | 153.267 | 51.543 | 51.543 | Sandy
80 | 40/2 | DA+3 |  | 192.04 |  |  |  |  | 48.633 | 34.461 | 34.4 | Sandy
81 | 40/3 | DA+3 |  | 200.906 | 1 | 2 |  |  | 233.433 | 139.125 | 139.125 | Sandy
82 | 41/0 | DC1+6 |  | 220.24 | 3 | 1 |  | 1 | 249.833 | 139.683 | 139.683 | Sandy
83 | 41/1 | DB1+9 |  | 193.1 | 4 | 5 | 6 | 6 | 120.747 | 45.165 | 918.667 | Sandy
84 | 41/2 | DA+0 |  | 187.77 |  |  | 1 | 1 | 1170.806 | 1139.792 | 1875.83 | Sandy
85 | 42/0 | DC1+0 |  | 189.212 | 1 |  |  | 2 | 339.457 | 328.874 | 329.325 | Sandy
86 | 42/1 | DA+6 |  | 200.55 | 1 |  |  |  | 127.8 | 83.2 | 78.56 | Sandy
87 | 42/2 | DA+6 |  | 189.49 |  |  | 1 | 3 | 91.933 | 56.323 | 39.17 | Sandy
88 | 42/3 | DA+0 |  | 184.13 |  |  |  |  | 9.463 | 3.72 | 3.72 | Sandy
89 | 42/4 | DA+0 |  | 184.34 |  |  |  |  | 136.417 | 99.463
90 | 42/5 | DA+9 |  | 188.05 |  |  |  | 1 | 106.4 | 49.975 | 18.096 | Dry
91 | 42/6 | DA+0 |  | 214.42 | 2 | 1 |  | 2 | 144.417 | 85.947 | 80.2 | Sandy
92 | 43/0 | DB1+0 |  | 210.52 |  |  |  |  | 68.726 | 53.162 | 33.44 | Sandy
93 | 43/1 | DA+3 |  | 203.87 |  |  | 3 | 3 | 199.917 | 73.957 | 73.84 | Sandy
94 | 43/2 | DA+0 |  | 185.92 | 1 |  |  | 1 | 189.737 | 89.999 | 66.4 | Sandy
95 | 43/3 | DA+0 |  | 187.1 |  | 1 |  |  | 275.117 | 183.088
96 | 43/4 | DA+3 |  | 191.67 | 1 | 1 |  |  | 108.9 | 38.999 | 102.72 | Sandy
97 | 43/5 | DA+3 |  | 184 |  |  |  |  | 35.95 | 18.096 | 18.096 | Sandy
98 | 43/6 | DA+3 |  | 185.22 |  |  |  |  | 17.8 | 7.552 | 7.552 | Sandy
99 | 43/7 | DA+3 | +0.20 | 184.11 |  |  |  |  | 46.75 | 26.32 | 26.08 | Sandy
100 | 43/8 | DA+9 |  | 192.68 | 1 |  |  |  | 120.65 | 100.624 | 104 | Sandy
101 | 43/9 | DA+9 |  | 201.66 |  |  |  |  | 61.583 | 42.336 | 24.16 | Sandy
102 | 43/10 | DA+3 |  | 219.93 | 3 | 3 |  |  | 70.8 | 24.393 | 24.393 | Sandy
103 | 43/11 | DA+3 |  | 216.7 | 2 | 3 |  | 1 | 125.717 | 24.813 | 213.4 | Sandy
104 | 44/0 | DB1+3 |  | 198.375 |  | 1 | 1 |  | 227.336 | 145.45
105 | 44/1 | DA+0 |  |  | 0 | 0 | 1 | 0 | 516.62 |  | 134.696 | Sandy
106 | 44/2 | DA+0 |  |  | 0 | 0 | 0 | 0 | 145.7 |  | 97.248 | Sandy
107 | 44/3 | DA+0 |  |  | 2 | 0 | 0 | 1 | 35.453 |  | 5.64 | Sandy
108 | 44/4 | DA+9 | 3.3 | 3 | 4 | 3 | 3 | 3 | 62.367 |  | 10.487 | Sandy
109 | 44/5 | DA+9 |  |  | 1 | 3 | 0 | 0 | 476.6 |  | 623.445 | Sandy
110 | 44/6 | DB1+3 |  |  | 1 | 0 | 0 | 1 | 263.667 |  | 197.423 | Sandy
111 | 44/7 | DA+9 |  |  | 0 | 0 | 0 | 0 | 107.267 |  | 73.68 | Sandy
112 | 44/8 | DC1+0 |  |  | 1 | 2 | 0 | 1 | 114.075 |  | 79.401 | Sandy
113 | 44/9 | DA+9 | 3 |  | 4 | 0 | 2 | 6 | 218.923 |  | 101.028 | Sandy
114 | 44/10 | DA+9 |  |  | 0 | 1 | 0 | 0 | 68.233 |  | 16.058 | Sandy
115 | 44/11 | DA+0 |  |  | 0 | 1 | 0 | 0 | 148.233 |  | 67.987 | Sandy
116 | 45/0 | DC2+0 |  |  | 0 | 1 | 0 | 0 | 104.47 |  | 47.558 | Sandy
117 | 45/1 | DA+0 |  |  | 0 | 0 | 1 | 2 | 329.483
118 | 46/0 | DD60+18 | 3 |  | 0 | 4 | 4 | 0 | 773.08 |  | 428.908 | Sandy
119 | 47/0 | DD60+18 |  | 2 | 3 | 2 | 2 | 2 | 333.585 |  | 262.43 | Sandy
120 | 47/1 | DA+6 |  | 1 | 1 | 1 | 2 | 2 | 334.445 | 183.244 | 653.343 | Sandy
121 | 47/2 | DA+9 |  |  | 0 | 0 | 0 | 0 | 35.008 | 14.894 | 14.894 | Sandy
122 | 47/3 | DA+9 |  |  | 1 | 2 | 0 | 0 | 351.248 | 198.462 | 198.051 | Sandy
123 | 47/4 | DA+3
124 | 47/5 | DA+0 |  |  | 0 | 1 | 0 | 0 | 151.406 | 50.19 | 50.19 | Sandy
125 | 47/6 | DA+3 |  |  | 0 | 0 | 0 | 0 | 214.683 | 105.461 | 105.295 | Sandy
126 | 47/7 | DA+3 |  |  | 0 | 0 | 0 | 0 | 146.833 | 85.356 | 83.13 | Sandy
127 | 47/8 | DA+0 |  |  | 1 | 0 | 0 | 0 | 186.171 | 58.541 | 57.389 | Sandy
128 | 47/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 36.917 | 21.243 | 21.243 | Sandy
129 | 47/10 | DA+6 |  |  | 0 | 0 | 0 | 0 | 105.1 | 44.208 | 44.128 | Sandy
130 | 48/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 271.371 | 121.376 | 121.152 | Sandy
131 | 48/1 | DA+9 |  |  | 0 | 0 | 0 | 0 | 83.933 | 43.92 | 42.432 | Sandy
132 | 49/1 | DA+0 |  |  | 0 | 0 | 0 | 0 | 28.5 | 20.37 | 20.37 | Sandy
133 | 49/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 237.2 | 152.093 | 151.986 | Sandy
134 | 49/3 | DA+3 |  |  | 0 | 0 | 0 | 0 | 130.95 | 59.392 | 59.168 | Sandy
135 | 49/4 | DA+3 |  |  | 0 | 0 | 0 | 0 | 52.95 | 27.468 | 27.342 | Sandy
136 | 49/5 | DA+3 | 0.1 |  | 0 | 0 | 0 | 0 | 68.133 | 33.446 | 33.173 | Sandy
137 | 49/6 | DA+0 | 0.1 |  | 0 | 0 | 0 | 0 | 29.783 | 10.948 | 10.948 | Sandy
138 | 49/7 | DA+3 |  |  | 0 | 3 | 2 | 2 | 190.733 | 89.935 | 92.01 | Sandy
139 | 50/0 | DB2+0 |  |  | 0 | 0 | 0 | 1 | 29.469 | 6.775 | 6.775 | Sandy
140 | 50/1 | DA+6 |  |  | 1 | 0 | 0 | 0 | 258.417 | 126.731 | 126.619 | Sandy
141 | 50/2 | DA+9 |  | 2 | 2 | 2 | 2 | 2 | 109.183 | 50.596 | 50.428 | Sandy
142 | 50/3 | DA+6 |  |  | 0 | 0 | 1 | 0 | 82.817 | 40.792 | 40.792 | Sandy
143 | 50/4 | DA+9 |  | 3 | 3 | 3 | 4 | 3 | 90.133 | 31.88 | 31.61 | Sandy
144 | 50/5 | DA+9 |  | 3 | 4 | 3 | 4 | 3 | 82.717 | 13.972 | 13.972 | Sandy
145 | 50/6 | DA+9 |  | 3 | 3 | 4 | 3 | 3 | 266.417 | 133.278 | 133.022 | Sandy
146 | 50/7 | DA+0 |  |  | 0 | 0 | 0 | 1 | 58.15 | 20.044 | 20.044 | Sandy
147 | 50/8 | DA+9 |  |  | 0 | 0 | 0 | 0 | 379.65 | 287.607 | 287.114 | Sandy
148 | 50/9 | DA+0 |  |  | 0 | 0 | 1 | 0 | 551.811 | 283.026
149 | 50/10 | DA+0 |  |  | 0 | 0 | 1 | 0 | 304.834 | 114.598 | 114.31 | Sandy
150 | 51/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 119.229 | 103.624 | 103.59 | Sandy
151 | 51/1 | DA+0 |  |  | 0 | 0 | 1 | 0 | 74.897 | 10.113 | 10.113 | Sandy
152 | 51/2 | DA+0 | -1 |  | 0 | 0 | 0 | 0 | 73.95 | 12.784 | 12.784 | Sandy
153 | 52/0 | DC2+0 |  |  | 0 | 0 | 3 | 3 | 474.917 | 226.626 | 226.483 | Sandy
154 | 52/1 | DA+6 |  |  | 0 | 4 | 0 | 0 | 95.517 | 20.215 | 20.215 | Sandy
155 | 52/2 | DA+6 |  |  | 0 | 0 | 0 | 3 | 74.467 | 56.535 | 56.468 | Sandy
156 | 52/3 | DA+9 |  | 3 | 4 | 3 | 3 | 3 | 54.25 | 21.459 | 21.459 | Sandy
157 | 52/4 | DA+9 |  |  | 2 | 2 | 0 | 0 | 35.517 | 14.371 | 14.371 | Sandy
158 | 52/5 | DA+9 |  |  | 0 | 0 | 0 | 1 | 269.167 | 177.797 | 177.045 | Sandy
159 | 52/6 | DA+6 |  |  | 0 | 0 | 0 | 0 | 343.483 | 239.936 | 236.824 | Sandy
160 | 52/7 | DA+3 |  |  | 0 | 3 | 1 | 0 | 464.317 | 306.372 | 305.292 | Sandy
161 | 52/8 | DA+6 |  |  | 0 | 0 | 0 | 0 | 644.717 | 582.599 | 579.567 | Sandy
162 | 52/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 192.433 | 139.028 | 139.116 | Sandy
163 | 52/10 | DA+9 |  | 1 | 1 | 2 | 1 | 1 | 270.567 | 123.839 | 122.335 | Sandy
164 | 53/0 | DB2+9 |  | 4 | 4 | 4 | 4 | 4 | 102.651 | 342.89 | 342.823 | Sandy
165 | 53/1 | DA+9 |  | 4 | 4 | 4 | 4 | 4 | 511.767 | 302.874 | 302.554 | Sandy
166 | 53/2 | DA+0 |  |  | 0 | 0 | 0 | 2 | 121.063 | 38.768 | 38.755 | Sandy
167 | 53/3 | DA+9 |  |  | 0 | 4 | 1 | 0 | 454.927 | 204.813 | 204.743 | Sandy
168 | 53/4 | DA+0 |  |  | 0 | 2 | 1 | 0 | 686.16 | 280.645 | 280.485 | Sandy
169 | 53/5 | DA+3 |  |  | 0 | 0 | 0 | 0 | 104.9 | 76.75 | 76.51 | Sandy
170 | 53/6 | DA+6 |  |  | 1 | 1 | 3 | 1 | 111.483 | 14.573 | 14.573 | Sandy
171 | 53/7 | DA+0 |  |  | 0 | 0 | 0 | 0 | 245.537 | 112.464 | 112.304 | Sandy
172 | 53/8 | DA+9 |  | 0 | 0 | 0 | 0 | 0 | 326.55 | 334.123 | 333.951 | Sandy
173 | 54/0 | DB1+6 |  |  | 0 | 0 | 0 | 0 | 400.8 | 293.967 | 293.9 | Sandy
174 | 54/1 | DA+9 |  |  | 1 | 1 | 0 | 0 | 74.4 | 17.753 | 17.753 | Sandy
175 | 54/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 105.35 | 63.16 | 63.14 | Sandy
176 | 54/3 | DA+6 |  |  | 0 | 2 | 0 | 0 | 106.517 | 71.292 | 71.275 | Sandy
177 | 54/4 | DA+9 |  | 0 | 1 | 2 | 0 | 0 | 264 | 131.156 | 283.706 | Sandy
178 | 54/5 | DA+9 |  | 1 | 1 | 3 | 3 | 1 | 210.2 | 91.403 | 91.345 | Sandy
179 | 55/0 | DB1+6 |  |  | 0 | 1 | 1 | 0 | 375.874 | 244.465 | 244.015 | Sandy
180 | 55/4 | DA+0 |  |  | 0 | 0 | 0 | 1 | 248.177 | 98.757 | 96.581 | Sandy
181 | 55/5 | DA+0 |  |  | 0 | 0 | 1 | 3 | 674.16 | 250.709 | 249.909 | Sandy
182 | 55/6 | DA+0 |  |  | 0 | 0 | 1 | 2 | 100.954 | 24.027 | 24.027 | Sandy
183 | 55/7 | DA+0 |  |  | 0 | 0 | 1 | 0 | 551.126 | 317.518 | 316.72 | Sandy
184 | 55/8 | DA+9 |  |  | 0 | 0 | 1 | 0 | 480.283 | 241.51 | 136.288 | Sandy
185 | 56/0 | DD60+9 |  | 4 | 4 | 6 | 4 | 4 | 454.562 | 387.425
186 | 57/0 | DD60+9 |  | 0 | 0 | 1 | 1 | 0 | 715.032 | 562.651 | 742.695 | Sandy
187 | 57/1 | DA+3 |  |  | 0 | 0 | 0 | 0 | 38.65 | 24.155
188 | 57/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 64.033 | 20.988 | 20.988 | All Kind of Soil
189 | 57/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 91.063 | 39.024 | 39.024 | All Kind of Soil
190 | 57/4 | DA+0 |  |  | 0 | 0 | 0 | 0 | 165.446 | 77.472 | 77.408 | sandy
191 | 57/5 | DA+3 |  |  | 0 | 0 | 0 | 1 | 114.817 | 54.629 | 53.905 | sandy
192 | 57/6 | DA+3 |  |  | 0 | 1 | 0 | 0 | 118.95 | 69.342 | 68.908 | All Kind of Soil
193 | 58/0 | DC1+3 |  |  | 0 | 0 | 0 | 0 | 16.509
194 | 59/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 97.629 | 97.629 | 97.594 | All Kind of Soil
195 | 59/1 | DA+3 |  |  | 0 | 0 | 0 | 1 | 30.167
196 | 59/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 74.35 | 57.328 | 57.216 | All Kind of Soil
197 | 59/3 | DA+3 |  |  | 0 | 0 | 0 | 1 | 29.783
198 | 59/7 | DA+3 |  |  | 0 | 0 | 0 | 0 | 88.917 | 67.301 | 67.237 | All Kind of Soil
199 | 59/8 | DB1+3 |  |  | 0 | 0 | 0 | 0 | 30.926
200 | 59/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 51.683
201 | 59/11 | DA+6 |  |  | 0 | 0 | 2 | 0 | 609.4 | 443.002 | 442.55 | FR
202 | 59/12 | DA+6 |  |  | 0 | 0 | 0 | 0 | 69.983
203 | 60/2 | DA+3 |  |  | 2 | 2 | 0 | 0 | 150.115 | 67.99 | 67.248 | All Kind of Soil
204 | 61/1 | DA+6 |  |  | 0 | 0 | 0 | 0 | 130.228 | 98.667 | 98.627 | All Kind of Soil
205 | 61/7 | DA+9 |  |  | 0 | 0 | 0 | 1 | 237.78 | 155.449 | 154.809 | All Kind of Soil
206 | 61/8 | DA+6 |  |  | 1 | 2 | 1 | 0 | 139.242 | 18.852 | 18.852 | All Kind of Soil
207 | 62/0 | DB2+0 |  |  | 0 | 0 | 0 | 0 | 50.997 | 36.79 | 36.29 | All Kind of Soil
208 | 62/1 | DA+3 |  |  | 0 | 0 | 1 | 2 | 200.388 | 135.911 | 135.895 | sandy
209 | 62/2 | DA+3 |  |  | 0 | 1 | 0 | 0 | 22.433
210 | 62/4 | DA+3 |  |  | 0 | 0 | 0 | 0 | 27.142
211 | 62/5 | DA+0 |  |  | 0 | 0 | 0 | 0 | 109.341 | 45.234 | 45.234 | All Kind of Soil
212 | 62/6 | DA+3 |  |  | 0 | 0 | 0 | 0 | 23.573
213 | 63/0 | DC1+0 |  |  | 0 | 0 | 0 | 0 | 199.633 | 199.633 | 199.333 | All Kind of Soil
214 | 63/3 | DA+3 |  |  | 0 | 0 | 0 | 0 | 173.683 | 140.624 | 140.608 | All Kind of Soil
215 | 63/5 | DA+3 |  |  | 0 | 0 | 0 | 0 | 31.908