## Summary
TSE
stage | avg_productivity_km_month | total_km | active_days | spans | gangs | projects | start_date | end_date
Overall | 0 | 0 | 0 | 0 | 0 | 0
P/O | 0 | 0 | 0 | 0 | 0 | 0
F/S | 0 | 0 | 0 | 0 | 0 | 0
Overall
stage | avg_productivity_km_month | total_km | active_days | spans | gangs | projects | start_date | end_date
Overall | 0 | 0 | 0 | 0 | 0 | 0
P/O | 0 | 0 | 0 | 0 | 0 | 0
F/S | 0 | 0 | 0 | 0 | 0 | 0

## Gang_Productivity
TSE
Overall

## PO_FS_Gap
TSE
Overall
project_name | from_ap | to_ap | gang_name | po_completion_date | fs_starting_date | gap_days | negative_gap_flag | source_file
TA 325 | 201/1 | 202/0 | Modina India 2 | 2026-01-04 | 2025-12-29 | -6 | TRUE
TA 325 | 202/0 | 203/0 | Teklal Saw / Muslehuddin | 2026-01-04 | 2025-12-30 | -5 | TRUE
TA 325 | 154/1 | 155/0 | Munni Bibi 2 | 2026-01-05 | 2025-12-30 | -6 | TRUE
TA 325 | 159/0 | 159/2 | Enamul Haque | 2026-01-05 | 2026-01-03 | -2 | TRUE
TA 325 | 173/0 | 174/0 | Dharmendra 2 | 2026-01-05 | 2025-12-31 | -5 | TRUE
TA 325 | 174/0 | 174/1 | Alam Construction | 2026-01-06 | 2026-01-03 | -3 | TRUE
TA 325 | 174/1 | 175/0 | Alam Construction | 2026-01-06 | 2026-01-03 | -3 | TRUE
TA 325 | 206/0 | 208/0 | Ramavat Electricals 2 | 2026-01-09 | 2025-12-18 | -22 | TRUE
TA 325 | 216/0 | 217/0 | Ramavat Electricals 1 | 2026-01-09 | 2026-01-01 | -8 | TRUE
TA 325 | 185/0 | 186/0 | Alam Construction | 2026-01-09 | 2026-01-09 | 0 | FALSE
TA 325 | 186/0 | 187/0 | Dharmendra 2 | 2026-01-11 | 2026-01-10 | -1 | TRUE
TA 325 | 215/0 | 215/1 | Ramavat Electricals 1&2 | 2026-01-14 | 2026-01-13 | -1 | TRUE
TA 325 | 215/1 | 216/0 | Kudus Ali | 2026-01-14 | 2026-01-13 | -1 | TRUE
TA 325 | 166/0 | 167/0 | Muni bibi / Enamul / Alam / Rafikul | 2026-01-17 | 2026-01-17 | 0 | FALSE
TA 413 | 3B/0 | 4/0 | Rahim Khan | 2026-01-17 | 2026-01-24 | 7 | FALSE
TA 413 | 33/0 | 34/0 | SK Infratech | 2026-01-13 | 2026-01-21 | 8 | FALSE
TA 413 | 32A/0 | 33/0 | SK Infratech | 2026-01-19 | 2026-01-31 | 12 | FALSE
TA 413 | 32/0 | 32A/0 | SK Infratech | 2026-01-30 | 2026-01-31 | 1 | FALSE
TA 416 - compliled | AP23/0 | AP24/0 | Jahangir(Company) | 2026-01-15 | 2026-01-16 | 1 | FALSE
TA 416 - compliled | AP40/0 | AP41/0 | Babloo Haque/Anarul-2 | 2026-01-16 | 2026-01-16 | 0 | FALSE
TA 416 - compliled | AP16/0 | AP17/0 | Ramawat-Hot line | 2026-01-10 | 2026-01-11 | 1 | FALSE
TA 416 - compliled | AP2/0 | AP3/0 | ANARUL ISLAM | 2026-01-22 | 2026-01-23 | 1 | FALSE
TA 416 - compliled | AP26/0 | AP27/0 | AE Solution(Company) | 2026-01-15 | 2026-01-16 | 1 | FALSE
TA 416 - compliled | AP25/0 | AP26/0 | Bhola prasad(Company)+Sing Bahini | 2026-01-31 | 2026-01-27 | -4 | TRUE
TA 416 - compliled | AP42/0 | AP43/0 | Babloo Haque/Anarul-2 | 2026-01-27 | 2026-01-27 | 0 | FALSE
TA 418 | 33/5 | 33/6 | Ramawat | 2026-01-30 | 2026-01-26 | -4 | TRUE
TA 418 | 33/6 | 34/0 | SUFIYAN / Haque | 2026-01-27 | 2026-01-26 | -1 | TRUE
TA 421 | 8/4 | 9/0 | Nasiruddin | 2026-01-06 | 2026-01-06 | 0 | FALSE
TA 421 | 6/0 | 7/0 | Nasiruddin | 2026-01-15 | 2026-01-18 | 3 | FALSE
TA 421 | 8/3 | 8/4 | Ramavath Electricals | 2026-01-28 | 2026-01-28 | 0 | FALSE
TA 421 | 27/0 | 27/3 | M R Constructions | 2026-01-12 | 2026-01-22 | 10 | FALSE
TA 421 | 27/3 | 28/0 | M R Constructions | 2026-01-28 | 2026-01-22 | -6 | TRUE
TA 505 | 100/0 | 101/0 | Alimuddin | 2026-01-25 | 2026-02-05 | 11 | FALSE
TA 506 | 1/0 | 2/0 | National Construction | 2026-01-22 | 2026-01-26 | 4 | FALSE
TA 506 | 5/0 | 6/0 | National Construction | 2026-01-27 | 2026-01-27 | 0 | FALSE
TA 506 | 51/0 | 51A/0 | Jahangir Alam | 2026-01-20 | 2026-01-27 | 7 | FALSE
TA 506 | 51A/0 | 51C/0 | Jahangir Alam | 2026-01-26 | 2026-01-27 | 1 | FALSE
TB 408 | 66/0 | 67/0 | MC Power | 2026-01-03 |  |  | FALSE
TB 408 | 3/0 | 4/0 | Gopal Associate, Hotline | 2026-01-16 |  |  | FALSE
TB 408 | 57/0 | 58/0 | MC Power | 2026-01-24 |  |  | FALSE
TB 408 | 10/12 | 11/0 | Deepak Sarkar | 2026-01-22 |  |  | FALSE
TB 408 | 47/0 | 48/0 | Krishna-1 | 2026-01-31 |  |  | FALSE
TB 408 | 48/0 | 49/0 | Krishna-1 | 2026-01-20 |  |  | FALSE
TB 408 | 58/0 | 59/0 | MC Power | 2026-01-28 |  |  | FALSE

## PO_FS_Gap_Summary
TSE
count | avg_gap_days | median_gap_days | min_gap_days | max_gap_days
0 | 0 | 0 | 0 | 0
Overall
count | avg_gap_days | median_gap_days | min_gap_days | max_gap_days
37 | 1.84 | 0 | 0 | 12

## Erection_PO_Gap
TSE
Overall

## Erection_PO_Gap_Summary
TSE
count | avg_gap_days | median_gap_days | min_gap_days | max_gap_days
0 | 0 | 0 | 0 | 0
Overall
count | avg_gap_days | median_gap_days | min_gap_days | max_gap_days
0 | 0 | 0 | 0 | 0

## Stringing Summary Overall
TSE
Scope (TSE): (empty)
Overall Avg Productivity (KM/month) | TSE Avg Productivity (KM/month) | Total KM | Spans | Gangs | Projects
0 | 0 | 0 | 0 | 0 | 0
Scope (TSE): (empty)
PCH | Overall Avg Productivity (KM/month) | TSE Avg Productivity (KM/month) | Total KM | Spans | Gangs | Projects
Scope (TSE): (empty)
PCH | Project | Overall Avg Productivity (KM/month) | TSE Avg Productivity (KM/month) | Total KM | Spans | Gangs
Mr Arun Felbin | TA 414 | 0 | 0 | 0 | 0 | 0
Mr Arun Felbin | TA 416 | 0 | 0 | 0 | 0 | 0
Mr Sanjay Kumar Gupta | TA 512 | 0 | 0 | 0 | 0 | 0
Mr. Arun Felbin | TA 325 | 0 | 0 | 0 | 0 | 0
Mr. Arun Felbin | TA 418 | 0 | 0 | 0 | 0 | 0
Mr. Arun Felbin | TA509 | 0 | 0 | 0 | 0 | 0
Mr. Arun Felbin | TA601 | 0 | 0 | 0 | 0 | 0
Mr. Dheeraj Vashishth | TA513 | 0 | 0 | 0 | 0 | 0
Mr. Dheeraj Vashishth | TB605 | 0 | 0 | 0 | 0 | 0
Mr. Nabajit Baruah | TA 504 | 0 | 0 | 0 | 0 | 0
Mr. Nabajit Baruah | TA 505 | 0 | 0 | 0 | 0 | 0
Mr. Nabajit Baruah | TA 506 | 0 | 0 | 0 | 0 | 0
Mr. Nabajit Baruah | TB501 | 0 | 0 | 0 | 0 | 0
Mr. Sanjay Gupta | TA 413 | 0 | 0 | 0 | 0 | 0
Mr. Sanjay Gupta | TA-419 | 0 | 0 | 0 | 0 | 0
Mr. Sanjay Kumar Gupta | TB401 | 0 | 0 | 0 | 0 | 0
Mr. Sanjay Kumar Gupta | TB408 | 0 | 0 | 0 | 0 | 0
Mr.Arun Felbin | TA 421 | 0 | 0 | 0 | 0 | 0
Sanjay Kr Gupta | TB 507 | 0 | 0 | 0 | 0 | 0
Unassigned | TA 310 | 0 | 0 | 0 | 0 | 0
Overall
Scope: (empty)
Overall Avg Productivity (KM/month) | TSE Avg Productivity (KM/month) | Total KM | Spans | Gangs | Projects
0 | 0 | 0 | 0 | 0 | 0
Scope: (empty)
PCH | Overall Avg Productivity (KM/month) | TSE Avg Productivity (KM/month) | Total KM | Spans | Gangs | Projects
Scope: (empty)
PCH | Project | Overall Avg Productivity (KM/month) | TSE Avg Productivity (KM/month) | Total KM | Spans | Gangs
Mr Arun Felbin | TA 414 | 0 | 0 | 0 | 0 | 0
Mr Arun Felbin | TA 416 | 0 | 0 | 0 | 0 | 0
Mr Sanjay Kumar Gupta | TA 512 | 0 | 0 | 0 | 0 | 0
Mr. Arun Felbin | TA 325 | 0 | 0 | 0 | 0 | 0
Mr. Arun Felbin | TA 418 | 0 | 0 | 0 | 0 | 0
Mr. Arun Felbin | TA509 | 0 | 0 | 0 | 0 | 0
Mr. Arun Felbin | TA601 | 0 | 0 | 0 | 0 | 0
Mr. Dheeraj Vashishth | TA513 | 0 | 0 | 0 | 0 | 0
Mr. Dheeraj Vashishth | TB605 | 0 | 0 | 0 | 0 | 0
Mr. Nabajit Baruah | TA 504 | 0 | 0 | 0 | 0 | 0
Mr. Nabajit Baruah | TA 505 | 0 | 0 | 0 | 0 | 0
Mr. Nabajit Baruah | TA 506 | 0 | 0 | 0 | 0 | 0
Mr. Nabajit Baruah | TB501 | 0 | 0 | 0 | 0 | 0
Mr. Sanjay Gupta | TA 413 | 0 | 0 | 0 | 0 | 0
Mr. Sanjay Gupta | TA-419 | 0 | 0 | 0 | 0 | 0
Mr. Sanjay Kumar Gupta | TB401 | 0 | 0 | 0 | 0 | 0
Mr. Sanjay Kumar Gupta | TB408 | 0 | 0 | 0 | 0 | 0
Mr.Arun Felbin | TA 421 | 0 | 0 | 0 | 0 | 0
Sanjay Kr Gupta | TB 507 | 0 | 0 | 0 | 0 | 0
Unassigned | TA 310 | 0 | 0 | 0 | 0 | 0

## Stringing Summary Monthly
TSE
Scope (TSE): (empty)
Overall
Avg Productivity (KM/month) | No. of Gangs | KM Strung
0 | 0 | 0
Scope (TSE): (empty)
PCH | Overall
| Avg Productivity (KM/month) | No. of Gangs | KM Strung
Mr. Arun Felbin | 0 | 0 | 0
Mr. Nabajit Baruah | 0 | 0 | 0
Mr. Sanjay Gupta | 0 | 0 | 0
Mr.Arun Felbin | 0 | 0 | 0
Unassigned | 0 | 0 | 0
Scope (TSE): (empty)
PCH | Project | Overall
|  | Avg Productivity (KM/month) | No. of Gangs | KM Strung
Mr Arun Felbin | TA 414 | 0 | 0 | 0
Mr Arun Felbin | TA 416 | 0 | 0 | 0
Mr Sanjay Kumar Gupta | TA 512 | 0 | 0 | 0
Mr. Arun Felbin | TA 325 | 0 | 0 | 0
Mr. Arun Felbin | TA 418 | 0 | 0 | 0
Mr. Arun Felbin | TA509 | 0 | 0 | 0
Mr. Arun Felbin | TA601 | 0 | 0 | 0
Mr. Dheeraj Vashishth | TA513 | 0 | 0 | 0
Mr. Dheeraj Vashishth | TB605 | 0 | 0 | 0
Mr. Nabajit Baruah | TA 504 | 0 | 0 | 0
Mr. Nabajit Baruah | TA 505 | 0 | 0 | 0
Mr. Nabajit Baruah | TA 506 | 0 | 0 | 0
Mr. Nabajit Baruah | TB501 | 0 | 0 | 0
Mr. Sanjay Gupta | TA 413 | 0 | 0 | 0
Mr. Sanjay Gupta | TA-419 | 0 | 0 | 0
Mr. Sanjay Kumar Gupta | TB401 | 0 | 0 | 0
Mr. Sanjay Kumar Gupta | TB408 | 0 | 0 | 0
Mr.Arun Felbin | TA 421 | 0 | 0 | 0
Sanjay Kr Gupta | TB 507 | 0 | 0 | 0
Unassigned | TA 310 | 0 | 0 | 0
Unassigned | TA 416 - compliled | 0 | 0 | 0
Unassigned | TB 507 - MAIN | 0 | 0 | 0
TSE - Month-wise Project Table (Vertical)
Month: No Data
Project | Productivity | Total Stringing
Overall
Scope: (empty)
Overall
Avg Productivity (KM/month) | No. of Gangs | KM Strung
0 | 0 | 0
Scope: (empty)
PCH | Overall
| Avg Productivity (KM/month) | No. of Gangs | KM Strung
Mr Arun Felbin | 0 | 0 | 0
Mr. Arun Felbin | 0 | 0 | 0
Mr. Nabajit Baruah | 0 | 0 | 0
Mr. Sanjay Gupta | 0 | 0 | 0
Mr. Sanjay Kumar Gupta | 0 | 0 | 0
Mr.Arun Felbin | 0 | 0 | 0
Sanjay Kr Gupta | 0 | 0 | 0
Unassigned | 0 | 0 | 0
Scope: (empty)
PCH | Project | Overall
|  | Avg Productivity (KM/month) | No. of Gangs | KM Strung
Mr Arun Felbin | TA 414 | 0 | 0 | 0
Mr Arun Felbin | TA 416 | 0 | 0 | 0
Mr Sanjay Kumar Gupta | TA 512 | 0 | 0 | 0
Mr. Arun Felbin | TA 325 | 0 | 0 | 0
Mr. Arun Felbin | TA 418 | 0 | 0 | 0
Mr. Arun Felbin | TA509 | 0 | 0 | 0
Mr. Arun Felbin | TA601 | 0 | 0 | 0
Mr. Dheeraj Vashishth | TA513 | 0 | 0 | 0
Mr. Dheeraj Vashishth | TB605 | 0 | 0 | 0
Mr. Nabajit Baruah | TA 504 | 0 | 0 | 0
Mr. Nabajit Baruah | TA 505 | 0 | 0 | 0
Mr. Nabajit Baruah | TA 506 | 0 | 0 | 0
Mr. Nabajit Baruah | TB501 | 0 | 0 | 0
Mr. Sanjay Gupta | TA 413 | 0 | 0 | 0
Mr. Sanjay Gupta | TA-419 | 0 | 0 | 0
Mr. Sanjay Kumar Gupta | TB401 | 0 | 0 | 0
Mr. Sanjay Kumar Gupta | TB408 | 0 | 0 | 0
Mr.Arun Felbin | TA 421 | 0 | 0 | 0
Sanjay Kr Gupta | TB 507 | 0 | 0 | 0
Unassigned | TA 310 | 0 | 0 | 0
Unassigned | TA 416 - compliled | 0 | 0 | 0
Unassigned | TA 419 - Stretch Readiness | 0 | 0 | 0
Unassigned | TB 401 - PKG-G | 0 | 0 | 0
Unassigned | TB 507 - MAIN | 0 | 0 | 0
Overall - Month-wise Project Table (Vertical)
Month: No Data
Project | Productivity | Total Stringing

## Review_Format
PCH | Project | Overall Avg Productivity (KM/month) | TSE Avg Productivity (KM/month) | Total KM | Spans
Mr Arun Felbin | TA 414 | 0 | 0 | 0 | 0
Mr Arun Felbin | TA 416 | 0 | 0 | 0 | 0
Mr Sanjay Kumar Gupta | TA 512 | 0 | 0 | 0 | 0
Mr. Arun Felbin | TA 325 | 0 | 0 | 0 | 0
Mr. Arun Felbin | TA 418 | 0 | 0 | 0 | 0
Mr. Arun Felbin | TA509 | 0 | 0 | 0 | 0
Mr. Arun Felbin | TA601 | 0 | 0 | 0 | 0
Mr. Dheeraj Vashishth | TA513 | 0 | 0 | 0 | 0
Mr. Dheeraj Vashishth | TB605 | 0 | 0 | 0 | 0
Mr. Nabajit Baruah | TA 504 | 0 | 0 | 0 | 0
Mr. Nabajit Baruah | TA 505 | 0 | 0 | 0 | 0
Mr. Nabajit Baruah | TA 506 | 0 | 0 | 0 | 0
Mr. Nabajit Baruah | TB501 | 0 | 0 | 0 | 0
Mr. Sanjay Gupta | TA 413 | 0 | 0 | 0 | 0
Mr. Sanjay Gupta | TA-419 | 0 | 0 | 0 | 0
Mr. Sanjay Kumar Gupta | TB401 | 0 | 0 | 0 | 0
Mr. Sanjay Kumar Gupta | TB408 | 0 | 0 | 0 | 0
Mr.Arun Felbin | TA 421 | 0 | 0 | 0 | 0
Sanjay Kr Gupta | TB 507 | 0 | 0 | 0 | 0
Unassigned | TA 310 | 0 | 0 | 0 | 0
Overall |  | Total |  | 0 | 0
PCH | Project | Overall Avg Productivity (KM/month) | TSE Avg Productivity (KM/month) | Total KM | Spans
Mr Arun Felbin | TA 414 | 0 | 0 | 0 | 0
Mr Arun Felbin | TA 416 | 0 | 0 | 0 | 0
Mr Arun Felbin |  | Total |  | 0 | 0
PCH | Project | Overall Avg Productivity (KM/month) | TSE Avg Productivity (KM/month) | Total KM | Spans
Mr Sanjay Kumar Gupta | TA 512 | 0 | 0 | 0 | 0
Mr Sanjay Kumar Gupta |  | Total |  | 0 | 0
PCH | Project | Overall Avg Productivity (KM/month) | TSE Avg Productivity (KM/month) | Total KM | Spans
Mr. Arun Felbin | TA 325 | 0 | 0 | 0 | 0
Mr. Arun Felbin | TA 418 | 0 | 0 | 0 | 0
Mr. Arun Felbin | TA509 | 0 | 0 | 0 | 0
Mr. Arun Felbin | TA601 | 0 | 0 | 0 | 0
Mr. Arun Felbin |  | Total |  | 0 | 0
PCH | Project | Overall Avg Productivity (KM/month) | TSE Avg Productivity (KM/month) | Total KM | Spans
Mr. Dheeraj Vashishth | TA513 | 0 | 0 | 0 | 0
Mr. Dheeraj Vashishth | TB605 | 0 | 0 | 0 | 0
Mr. Dheeraj Vashishth |  | Total |  | 0 | 0
PCH | Project | Overall Avg Productivity (KM/month) | TSE Avg Productivity (KM/month) | Total KM | Spans
Mr. Nabajit Baruah | TA 504 | 0 | 0 | 0 | 0
Mr. Nabajit Baruah | TA 505 | 0 | 0 | 0 | 0
Mr. Nabajit Baruah | TA 506 | 0 | 0 | 0 | 0
Mr. Nabajit Baruah | TB501 | 0 | 0 | 0 | 0
Mr. Nabajit Baruah |  | Total |  | 0 | 0
PCH | Project | Overall Avg Productivity (KM/month) | TSE Avg Productivity (KM/month) | Total KM | Spans
Mr. Sanjay Gupta | TA 413 | 0 | 0 | 0 | 0
Mr. Sanjay Gupta | TA-419 | 0 | 0 | 0 | 0
Mr. Sanjay Gupta |  | Total |  | 0 | 0
PCH | Project | Overall Avg Productivity (KM/month) | TSE Avg Productivity (KM/month) | Total KM | Spans
Mr. Sanjay Kumar Gupta | TB401 | 0 | 0 | 0 | 0
Mr. Sanjay Kumar Gupta | TB408 | 0 | 0 | 0 | 0
Mr. Sanjay Kumar Gupta |  | Total |  | 0 | 0
PCH | Project | Overall Avg Productivity (KM/month) | TSE Avg Productivity (KM/month) | Total KM | Spans
Mr.Arun Felbin | TA 421 | 0 | 0 | 0 | 0
Mr.Arun Felbin |  | Total |  | 0 | 0
PCH | Project | Overall Avg Productivity (KM/month) | TSE Avg Productivity (KM/month) | Total KM | Spans
Sanjay Kr Gupta | TB 507 | 0 | 0 | 0 | 0
Sanjay Kr Gupta |  | Total |  | 0 | 0
PCH | Project | Overall Avg Productivity (KM/month) | TSE Avg Productivity (KM/month) | Total KM | Spans
Unassigned | TA 310 | 0 | 0 | 0 | 0
Unassigned |  | Total |  | 0 | 0

## README
Assumption | Details
Productivity units | Avg productivity is reported per month as mean(daily_km) * 30. Total_km is the sum of daily_km.
Overall / P/O / F/S daily rows | Overall uses PO start to FS complete. P/O uses PO start to PO completion with PO length as primary metric (fallback to span length). F/S uses FS start to FS complete with span length.
PO-FS gap | gap_days = fs_starting_date - po_completion_date. Negative gaps are flagged in Data_Issues and retained in PO_FS_Gap; summary stats clamp negatives to 0. Missing dates are excluded from stats.
Erection-PO gap | gap_days = po_start_date - last erection completion date within the span (inclusive). Negative gaps are flagged and clamped to 0. Missing dates or unmatched spans are logged in Data_Issues.
Location parsing | From/To AP values strip a leading 'AP' (case-insensitive) with optional separators. Parsed as main number + optional letters + optional '/sub'. Order key = main*1,000,000 + letter_rank*1,000 + sub.
Gantry spans | From/To AP values containing 'gantry' or 'gty' are treated as line ends. If To_AP is gantry, the span runs from From_AP to the max location for that project; if From_AP is gantry, the span runs from the min location to To_AP. Both ends marked gantry are flagged as data issues.
Length units | Span lengths are auto-detected per source_file (fallback per project): if p90 <= 50 and max <= 100, values are treated as KM; otherwise meters. KM values are converted to meters for length_m and used directly for length_km.
Span matching | Span ranges are inclusive of From and To locations. If From/To order is reversed, the range is normalized.
Project matching | Projects are matched using a compact key (lowercase, alphanumeric only).
Date filters | PO-FS gaps are filtered by PO completion date; Erection-PO gaps are filtered by PO start date; daily outputs are filtered by the daily date column.
Date parsing | Stringing dates support mixed formats. Values like DD.MM.YY or DD/MM/YYYY are parsed day-first; Excel serials are supported.
Method split | Method is read from the stringing daily data (method/method_norm). Rows without method are logged in Data_Issues. Summary groups into TSE, Manual, and Other.
Pareto analysis | Pareto buckets use gang-level avg_km_month (mean daily_km * 30). KM % Delivered is based on sum(length_km) from compiled rows for gangs in each bucket; counts and percentages reflect unique gangs per bucket.
Monthly totals | Review_Format monthly tables use sum(length_km) grouped by F/S completion month and count unique gangs per month.

## Coverage_Issues
PCH | Project | Project Code | Status | Reason | Compiled Rows | Daily Rows | Workbook | Configured Sheet | Resolved Sheet | Fallback Used
Mr. Arun Felbin | TA 601 | TA 601 | READ_FAIL | TEMPLATE_CONFIG_ERROR: Stringing Template Check is Yes but no mapping tab matching project 'TA 601' was found. | 0 | 0 | TA 601 - DPR - 2026-03-10.xlsx | Stringing Compiled |  | FALSE
Unassigned | TB 501 - Stringing 132kV | TB 501 | NO_TARGET_SHEET | Configured sheet name not found in workbook. | 0 | 0 | TB 501 - DPR - 2026-03-10.xlsx | Stringing-132KV; Stringing-220kV |  | FALSE
Mr. Sanjay Kumar Gupta | TB 408 | TB 408 | MISSING_REQUIRED_COLUMNS | Missing headers: Method, Section Readiness, F/S Starting Date, F/S/ Completion Date | 44 | 0 | TB 408 - DPR - 2026-03-10.xlsx | Stringing | Stringing | FALSE
Unassigned | TA 419 - Stretch Readiness | TA 419 | MISSING_REQUIRED_COLUMNS | Missing headers: From AP, To AP, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Gang Name | 426 | 0 | TA 419 - DPR - 2026-03-10.xlsx | Stringing Stretch Readiness | Stringing Stretch Readiness | FALSE
Unassigned | TB 401 - PKG-G | TB 401 | MISSING_REQUIRED_COLUMNS | Missing headers: From AP, To AP, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Gang Name | 92 | 0 | TB 401 - DPR - 2026-03-10.xlsx | Stringing - PKG-G | Stringing - PKG-G | FALSE
Mr Arun Felbin | TA 414 | TA 414 | NO_DAILY | No valid PO-start to FS-complete ranges expanded to daily rows. | 3 | 0 | TA 414 - DPR - 2026-03-06.xlsx | Stringing Compiled | Stringing Compiled | FALSE
Mr Sanjay Kumar Gupta | TA 512 | TA 512 | SKIPPED_NO_STRINGING_CONFIG | Project has blank Stringing Sheet Names in DPR_Config. | 0 | 0 | TA 512 - DPR - 2026-03-10.xlsx |  |  | FALSE
Mr. Arun Felbin | TA 509 | TA 509 | SKIPPED_NO_STRINGING_CONFIG | Project has blank Stringing Sheet Names in DPR_Config. | 0 | 0 | TA 509 - DPR - 2026-01-17.xlsx |  |  | FALSE
Mr. Dheeraj Vashishth | TA 513 | TA 513 | SKIPPED_NO_STRINGING_CONFIG | Project has blank Stringing Sheet Names in DPR_Config. | 0 | 0 | TA 513 - DPR - 2026-01-08.xlsx |  |  | FALSE
Mr. Dheeraj Vashishth | TB 605 | TB 605 | SKIPPED_NO_STRINGING_CONFIG | Project has blank Stringing Sheet Names in DPR_Config. | 0 | 0 | TB 605 - DPR - 2026-03-09.xlsx |  |  | FALSE
Unassigned | TA 310 | TA 310 | SKIPPED_NO_STRINGING_CONFIG | Project has blank Stringing Sheet Names in DPR_Config. | 0 | 0 | TA 310 - DPR - 2026-01-12.xlsx |  |  | FALSE
Unassigned | TB 507 - MAIN | TB 507 | OK | No valid PO-start to FS-complete ranges expanded to daily rows. | 9 | 23 | TB 507 - DPR - 2026-03-08.xlsx; TB 507 [MAIN] - DPR - 2026-03-08.xlsx | Stringing Compiled | Stringing Compiled | FALSE
Mr. Arun Felbin | TA 325 | TA 325 | OK |  | 232 | 3463 | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | Stringing Compiled | FALSE
Mr. Arun Felbin | TA 418 | TA 418 | OK |  | 43 | 224 | TA 418 - DPR - 2026-03-11.xlsx | Stringing Compiled | Stringing Compiled | FALSE
Mr. Nabajit Baruah | TA 504 | TA 504 | OK |  | 228 | 59 | TA 504 - DPR - 2026-03-09.xlsx | Stringing | Stringing | FALSE
Mr. Nabajit Baruah | TA 505 | TA 505 | OK |  | 230 | 67 | TA 505 - DPR - 2026-03-10.xlsx | Stringing Compiled | Stringing Compiled | FALSE
Mr. Nabajit Baruah | TA 506 | TA 506 | OK |  | 228 | 170 | TA 506 - DPR - 2026-03-09.xlsx | Stringing | Stringing | FALSE
Mr. Sanjay Gupta | TA 413 | TA 413 | OK |  | 61 | 292 | TA 413 - DPR - 2026-02-24.xlsx | Stringing Compiled | Stringing Compiled | FALSE
Mr.Arun Felbin | TA 421 | TA 421 | OK |  | 76 | 573 | TA 421 - DPR - 2026-03-05.xlsx | Stringing Compiled | Stringing Compiled | FALSE
Unassigned | TA 416 - compliled | TA 416 | OK |  | 78 | 728 | TA 416 - DPR - 2026-03-09.xlsx | Stringing compliled | Stringing compliled | FALSE

## Data_Issues
issue_type | project | from_ap | to_ap | po_start_date | po_completion_date | fs_starting_date | fs_complete_date | details
PO_FS_NEGATIVE_GAP | TA 325 | 201/1 | 202/0 |  | 2026-01-04 | 2025-12-29 |  | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 202/0 | 203/0 |  | 2026-01-04 | 2025-12-30 |  | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 154/1 | 155/0 |  | 2026-01-05 | 2025-12-30 |  | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 159/0 | 159/2 |  | 2026-01-05 | 2026-01-03 |  | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 173/0 | 174/0 |  | 2026-01-05 | 2025-12-31 |  | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 174/0 | 174/1 |  | 2026-01-06 | 2026-01-03 |  | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 174/1 | 175/0 |  | 2026-01-06 | 2026-01-03 |  | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 206/0 | 208/0 |  | 2026-01-09 | 2025-12-18 |  | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 216/0 | 217/0 |  | 2026-01-09 | 2026-01-01 |  | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 186/0 | 187/0 |  | 2026-01-11 | 2026-01-10 |  | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 215/0 | 215/1 |  | 2026-01-14 | 2026-01-13 |  | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 215/1 | 216/0 |  | 2026-01-14 | 2026-01-13 |  | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 416 - compliled | AP25/0 | AP26/0 |  | 2026-01-31 | 2026-01-27 |  | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 418 | 33/5 | 33/6 |  | 2026-01-30 | 2026-01-26 |  | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 418 | 33/6 | 34/0 |  | 2026-01-27 | 2026-01-26 |  | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 421 | 27/3 | 28/0 |  | 2026-01-28 | 2026-01-22 |  | FS start is before PO completion