## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manger | Section Incharge | Supervisor
TA 408 | 765KV D/C HEXA AHMEDABAD - NAVSARI TL (PKG 02) | PGKTL | 2023-03-23 | 2024-12-22 | Mr. Bikash Ranjan Pradhan | Mr. Sivaraman Natrajan | Mr. Nitin Bandale | Mr. Sanjeev Garg | Prabin Patra | Rupesh
[9 empty] | D N Prasad | Bijendra
Rahman
Sitaram
Churamani
J S Jha
Madhusudan
Ritlal
Somenath
Aflaudin
Akhtarul

## Progress Summary
#VALUE! | Project Code - | TB-408 | Date | 2025-10-06 |  | Head - T&D | Rajinder Gupta |  | Head T&D-North | Sanjay K. Gupta | Regional Manager | Sandeep Singh Kumar |  | Shortcut for previous of Full description
| Client Name- | Resonia Limited (Formally Sterlite Power Transmission Limited) |  |  |  | Project Manager | Rajesh Yadav |  |  |  | Planning Engineer | Raghav Ranjan |  | Link for go through
| Project Name- | 765KV D/C Fatehgarh III- Beawar Transmission Line, PKG F |  |  |  | Effective Date | 2023-12-06 |  | End Date | Dec-25 (TE Applied) | LOA Value | Rs 283.08 Cr Supply -Rs 209.88 Cr., Service.-Rs 73.20 Cr |  | X-ing Status'!A1
Sr. No. | Activity | As per latest Estimate | Cumm. Progress up to last Month | Balance on Starting of this Month | Plan for this Month | Today Progress | MTD | WIP | Cumulative Progress | Balance | Gangs at present | Remarks | Support Required | L2 Schedule'!A1
1 | Check Survey (Km) | 191.373 | 189.893 | 1.48 | 1.48 |  |  |  | 189.893 | 1.48 | - |  | ROW-1.48 Kms (AP20-21) | Hindrance Register (Row)'!A1
2 | Foundation (Nos.) | 485 | 413 | 72 | 14 | 1 | 2 | 13 | 415 | 70 | 6 | WIP- 2/7, 3/0, 4/1, 8/12, 10/0, 10/1, 19/5, 21/5, 21/7, 27/0, 27/1, 30/5, 41/0. |  | Survey!A1
3 | Earthing (Nos.) | 485 | 407 | 78 | 14 |  | 2 |  | 409 | 76 | 6 |  |  | Foundation!A1
4 | Tower Erection (Nos) | 485 | 222 | 263 | 5 |  |  | 2 | 222 | 263 | 1 | WIP-1A/4, 70/6 |  | Earthing!A1
5 | Tack Welding (Nos) | 485 | 165 | 320 | 14 |  |  |  | 165 | 320 | 2 |  |  | Erection!A1
6 | Paying Out (Kms) | 191.373 | 43.508 | 147.865 | 3.788 |  |  | 3.788 | 43.508 | 147.865 | 1 | AP73-AP74- 1 phase R/Sag completed. Gang idle due to shut down initially 26th to 31st May further 02nd June to till date. | Required shutdown of 33 KV Line on earliest basis. | Tackwelding!A1
7 | Final Sag (Kms) | 191.373 | 43.508 | 147.865 | 3.788 |  |  | 0 | 43.508 | 147.865 | - |  |  | Stringing!A1
8 | OPGW (Kms) | 191.373 | 30.052 | 161.321 | 0 |  |  | 0 | 30.052 | 161.321 | - |  |  | Stringing associated works'!A1
OPGW!A1
Workfront Status | [13 empty] | Visual chart'!A1
Page Chart'!A1
A. Foundation | [13 empty] | Benching F'!A1
Balance on 1st of this month | Progress MTD | WIP | Clear/Yet to attempt | ROW | Remarks
72 | 2 | 13 | 12 | 45
B. Erection
Balance on 1st of this month | Progress MTD | WIP | Clear/Yet to attempt | ROW | Linked With Fnd | Remarks
263 | 0 | 2 | 174 | 15 | 72
C. Stringing
STR P/Out Bal. on starting of this month | Progress MTD | WIP | Clear/Yet to attempt | ROW | Readiness awaited due to Erec. | Remarks
147.865 | 0 | 3.788

## X-ing Status
Progress Summary'!A1
Details of Crossing in 765KV D/C Fatehgarh-III to Beawar Transmission Line
Sr. No. | Name of Crossing | From | To | Span in Mtrs | Submission Date | Appr. Date | Foundation Status | Erection Status | Stringing Status | Remarks
Power Line Crossing – 9 nos
1 | 400 KV S/C Jaisalmer-Barmer Line | 3/0 | 4/0 | 226.52 | 2024-02-15 |  | AP3:- WIP AP4:- Completed
2 | 220 KV D/C Barmer-Akal Line | 5/0 | 6/0 | 246.019 | 2024-02-15 |  | AP5:- Balance AP6:- Balance
3 | 132 KV S/C Sheo-Jaisalmer Line | 7/0 | 8/0 | 210.755 | 2024-02-15 |  | AP7:- Balance AP8:- Balance
4 | 400 KV D/C Barmer-Jaisalmer-2 Line | 9/0 | 10/0 | 233.076 | 2024-02-15 |  | AP9:- Balance AP10:- Balance
5 | 132 KV S/C Sheo-Undoo Line | 12/0 | 13/0 | 211.914 | 2024-02-15 |  | AP12:- Completed AP13:- Completed | AP12:- Balance AP13:- Balance
6 | 132 KV S/C Undoo-Baytoo Line | 23/0 | 24/0 | 222.155 | 2024-01-16 | 2024-06-27 | AP23:- Balance AP24:- Balance
7 | 400 KV D/C Mandor-JSW Transmission Line | 46/0 | 47/0 | 197.7 |  |  | AP46:- Completed AP47:- Completed | AP46:- Balance AP47:-
8 | 400 KV D/C Line | 56/0 | 57/0 | 179.9 |  |  | AP56:- Completed AP57:- Completed | AP56:- Balance AP57:- Balance
9 | 220 KV D/C Balotra-Boranada Transmission Line | 66/0 | 67/0 | 207.8 | 2024-03-08 | 2024-07-18 | AP66:- Completed AP67:- Completed | AP66:- Completed AP67:- Balance
NH Crossings-3 Nos | NH Crossing
1 | NH - 68 (Barmer - Jaisalmer) | 5/0 | 6/0 | 246.019 | 2024-02-15 |  | AP5:- Balance AP6:- Balance
2 | Expressway (Amritsar-Jamnagar) | 58/0 | 59/0 | 238.9 | 2024-03-08 | 2024-06-01 | AP58:- Completed AP59:- Completed | AP58:- Completed AP59:- Completed | Balance
3 | NH | 68/0 | 69/0 | 200.9 | 2024-03-08 | 2024-06-26 | AP68:- Completed AP69:- Completed | AP68:- Balance AP69:- Balance
Gas Pipe Line-1 Nos | NH Crossing
1 | Gas Pipe Lines | 65/7 | 65/8 | 394.3 |  |  | AP65/7:- Completed AP65/8:- Completed | AP65/7:- Completed AP65/8:- Completed | Completed

## L2 Schedule
Progress Summary'!A1 | L2 Schedule vs Actual
Line Name: Part F, 765KV D/C Fatehgarh- Beawar Transmission Line
LOI Date: 11-Sep-2023
Effective Date: 06-Dec-2023
Schedule Completion as per LOA: 05-March-2025
| Scope & Discription |  |  |  |  | Before L2 | Approved | [15 empty] | Extension of time (Proposed) -1 | [8 empty] | Remarks
| Sr. No. | Description | Scope of Work | UOM | Qty. | 2023-10-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
[6 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
| 1 | Release of Sag Template Curve & Tower Spotting Data | Sterlite
| 2 | Approval of repeated tower design & its BOMS | Sterlite
| 3 | Approval of repeated foundation design/drawings | Sterlite
| 4 | Supply
| i) | Manufacturing of Stubs with Earthing material(incl. B&N) | KEC
| A. | Inspection of stub | Sterlite | Nos. | 482 | 1: 40; 2: 100; 3: 100; 5: 100; 6: 65; 8: 77
| B. | Dispatch of stub | KEC | Nos. | 482 | 1: 40; 2: 100; 3: 100; 4: 0; 5: 100; 6: 65; 7: 0; 8: 77; 9: 0; 10: 0; 11: 0; 12: 0; 13: 0
| C. | Receipt of stubs at site | KEC | Nos. | 482 | 1: 40; 2: 100; 3: 100; 4: 0; 5: 100; 6: 65; 7: 0; 8: 77; 9: 0; 10: 0; 11: 0; 12: 0; 13: 0
|  | MFC submitted on |  |  |  | 1: 192; 2: 73; 3: 73
|  | MFC received on |  |  |  | 1: 192; 2: 73; 4: 73; 7: 144
|  | Actual |  |  |  | 1: 40; 2: 120; 3: 0; 4: 10; 6: 152; 7: 39; 8: 5; 11: 27
| ii) | Manufacturing of Tower (incl B&N) | KEC
| A. | Inspection of tower | Sterlite | Nos. | 482 | 1: 50; 2: 60; 3: 60; 4: 60; 5: 60; 6: 65; 7: 66; 8: 31; 9: 30
| B. | Dispatch of tower | KEC | Nos. | 482 | 2: 50; 3: 60; 4: 60; 5: 60; 6: 60; 7: 65; 8: 66; 9: 31; 10: 30; 11: 0; 12: 0; 13: 0
| C. | Receipt of complete towers at site | KEC | Nos. | 482 | 2: 50; 3: 60; 4: 60; 5: 60; 6: 60; 7: 65; 8: 66; 9: 31; 10: 30; 11: 0; 12: 0; 13: 0
|  | MFC submitted on |  |  |  | 1: 97; 2: 128; 6: 65; 7: 192
|  | MFC received on |  |  |  | 1: 97; 2: 128; 7: 257
|  | Actual |  |  |  | 2: 50; 3: 60; 4: 45; 5: 74; 6: 9; 7: 99; 10: 54; 12: 10
| iii) | Supply of following Tower accessories
| A. | Danger Plate | KEC | % | 100 | 9: 100%
| B. | Number Plate | KEC | % | 100 | 9: 100%
| C. | Phase Plate (Set of three) | KEC | % | 100 | 9: 100%
| D. | Circuit Plate (Set of Two) | KEC | & | 100 | 9: 100%
| E. | Anti-Climbing Device | KEC | % | 100 | 9: 100%
| F. | Bird Guard (Set of Three) | KEC | % | 100 | 9: 100%
| iv) | Other's Supply
| A. | Span Marker | KEC | % | 100 | 9: 100%
| B. | Aviation Light | KEC | % | 100 | 9: 100%
| v) | OSM
| A. | Supply of AL59 Zebra Conductor & associated Acessories | Sterlite | % | 100 | 4: 25%; 7: 25%; 9: 25%; 11: 25%
| B. | Supply of Insulator & associated Hardwere | Sterlite | % | 100 | 4: 25%; 7: 25%; 9: 25%; 11: 25%
| C. | Supply of Earth Wire & associated Hardwere | Sterlite | % | 100 | 1: 0; 2: 0; 4: 25%; 5: 0; 7: 25%; 8: 0; 9: 25%; 11: 25%
| D. | Supply of OPGW & associated Hardwere | Sterlite | % | 100 | 1: 0; 2: 0; 6: 25%; 9: 25%; 11: 25%; 12: 25%
| 5 | Erection
| A. | Establishment of Site Office
| B. | Route Alignment(Date of Start) | Sterlite | Kms | 191
| C. | Detail Survey | Sterlite | Kms | 191 | 1: 90; 2: 71; 3: 30
|  | Actual |  |  |  | 1: 191
| D. | Check Survey | KEC | Kms | 191 | 1: 20; 2: 65; 3: 65; 4: 41
|  | Actual date of submission |  |  |  | 1: 128.337; 2: 2.238; 3: 28.252; 7: 10.313; 8: 5.601; 9: 3.788; 10: 3.65; 12: 2.747; 13: 4.966
|  | Actual date of approval |  |  |  | 1: 86.508; 2: 44.067; 3: 14.03; 6: 12.488; 8: 15.914; 9: 3.788; 12: 3.57; 13: 9.446
| E. | Soil Investigation Location approval | Sterlite | Loc | 193 | 1: 193
|  | Actual |  |  |  | 2: 24
| F. | Soil Investigation Location at Site | KEC | Loc | 193 | 1: 40; 2: 40; 3: 60; 4: 53
|  | Actual |  |  |  | 4: 24
| G. | Foundation
| G.1 | Foundation(Incl.Earthing) | KEC | Nos | 482 | 1: 20; 2: 40; 3: 45; 4: 45; 5: 45; 6: 40; 7: 30; 8: 35; 9: 35; 10: 35; 11: 45; 12: 45; 13: 22
|  | Actual |  |  |  | 1 | 22 | 46 | 36 | 16 | 7 | 15 | 9 | 14 | 26 | 38 | 26 | 9 | 31 | 47 | 27 | 17 | 13 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cummulative |  |  |  | 1 | 23 | 69 | 105 | 121 | 128 | 143 | 152 | 166 | 192 | 230 | 256 | 265 | 296 | 343 | 370 | 387 | 400 | 413 | 415 | 415 | 415 | 415 | 415 | 415 | 415
| G.2. | Earthing |  |  |  | 0 | 5 | 35 | 58 | 20 | 10 | 11 | 9 | 10 | 19 | 45 | 20 | 2 | 25 | 37 | 53 | 22 | 12 | 15 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cummulative |  |  |  | 0 | 5 | 40 | 98 | 118 | 128 | 139 | 148 | 158 | 177 | 222 | 242 | 244 | 269 | 306 | 359 | 381 | 393 | 408 | 409 | 409 | 409 | 409 | 409 | 409 | 409
| H. | Erection
| H.1 | Erection of towers (Incl. Tack welding & painting of tower) | KEC | Nos | 482 | 3: 25; 4: 30; 5: 45; 6: 45; 7: 35; 8: 35; 9: 35; 10: 35; 11: 50; 12: 50; 13: 50; 14: 47
|  | Actual | [6 empty] | 22 | 20 | 19 | 14 | 3 | 2 | 3 | 16 | 30 | 30 | 11 | 16 | 14 | 13 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cummulative | [6 empty] | 22 | 42 | 61 | 75 | 78 | 80 | 83 | 99 | 129 | 159 | 170 | 186 | 200 | 213 | 220 | 222 | 222 | 222 | 222 | 222 | 222 | 222 | 222
| I. | Stringing
| I.1 | Stringing Conductor & Earthwire | KEC | Kms | 191 | 5: 5; 6: 12; 7: 12; 8: 12; 9: 18; 10: 25; 11: 25; 12: 25; 13: 25; 14: 20; 15: 12
|  | Actual | [8 empty] | 0 | 0 | 0 | 0 | 0 | 4.877 | 9.431 | 8.629 | 0 | 7.115 | 0 | 9.18 | 1.049 | 3.227 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cummulative | [8 empty] | 0 | 0 | 0 | 0 | 0 | 4.877 | 14.308 | 22.937 | 22.937 | 30.052 | 30.052 | 39.232 | 40.281 | 43.508 | 43.508 | 43.508 | 43.508 | 43.508 | 43.508 | 43.508 | 43.508
| I.2 | OPGW Stringing | KEC | Kms | 191 | 8: 5; 9: 15; 10: 20; 11: 25; 12: 35; 13: 45; 14: 30; 15: 16
|  | Actual | [11 empty] | 0 | 0 | 3.337 | 8.655 | 9.431 | 0 | 8.629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cummulative | [11 empty] | 0 | 0 | 3.337 | 11.992 | 21.423 | 21.423 | 30.052 | 30.052 | 30.052 | 30.052 | 30.052 | 30.052 | 30.052 | 30.052 | 30.052 | 30.052 | 30.052 | 30.052
| J. | Fixing Of Tower Accessories, aviation painting & installation of span marker | KEC | % | 100 | 13: 30%; 14: 30%; 15: 40%
| K. | Checking, Testing & Commissioning/Ready for Commissioning | KEC | Kms. | 191 | 14: 50%; 15: 50%
REMARKS
1 | Provisional Tower Quantities are 482 Nos.

## Hindrance Register (Row)
Progress Summary'!A1
HINDRANCE REGISTER
1 | Name of the Substation/TL/Project | 765 KV Fatehgarh-3 Beawer Transmission Line Part-F |  |  |  | 2. Name of Work |  | Transmission & Power Distribution
3 | Name of the Executing Agency | KEC International Limited |  |  |  | 3. LOA No. & Date |  | LOI/EPC/FBTL/PART-F/KEC/01 Dated 11.09.2023
Sr. No. | Activity | Total | Open | Close |  |  |  |  | Progress Summary'!A1
1 | Survey | 20 | 1 | 19
2 | Foundation | 210 | 57 | 153
3 | Erection | 21 | 15 | 6
4 | Stringing | 1 | 0 | 1
5 | Others | 3 | 1 | 2
Total |  | 255 | 74 | 181
Check Survey
S.No | Nature of Hindrance | Loc/Sec. | Affected Activity | Affected Gang Name | Date of 1st attempt | Date of removal (Last attempt) | Period of hindrance | Remarks
1 | Check survey not done due to frequent obstruction by land owner from 38/0 to 39/0. | 38-39 | Survey |  | 2023-12-06 | 2024-10-10 | 310 | Refer KEC letter dated 02-01-24. Reattempted on 09-01-24 but still in ROW. 3rd time attempted on dated 10.07.24 informed to you via mail regarding ROW.
2 | Check survey not done due to frequent obstruction by land owner from 39/0 to 40/0. | 39-40 | Survey |  | 2023-12-06 | 2024-10-10 | 310 | Refer KEC letter dated 02-01-24. Reattempted on 09-01-24 but still in ROW. 3rd time attempted on dated 10.07.24 informed to you via mail regarding ROW.
3 | Check survey is on hold from Gantry to 2/0 due to Non-Finalization of Gantry. | Gty-2 | Survey |  | 2023-12-06 | 2024-07-15 | 223 | Refer KEC letter dated 02-01-24.
4 | Check survey not done due to frequent obstruction by land owner from 10/12 to 11A. | 10/12-11A | Survey |  | 2023-12-06 | 2024-01-16 | 42 | Refer KEC letter dated 02-01-24.
5 | Check survey not done due to ROW from AP 20-AP 21. | 20-21 | Survey |  | 2023-12-06 |  | Awaited | Refer KEC letter dated 02-01-24. SPTL mail dated 20/5/24 having subject Optimization from GTY to AP74 (Part- F). Clearance for check survey received on 17.10.24. however survey team along with machinery idled at this section since 18th. Section is still in ROW. on dated 19.10.2024.
6 | Delay in approval of check survey report from Ap 21 to AP 25. | 21-25 | Survey |  | 2023-12-06 | 2023-12-14 | 9
7 | Delay in approval of check survey report from Ap 14 to AP 20. | 14-20 | Survey |  | 2023-12-06 | 2023-12-14 | 9
8 | ROW in check survey works. | 47-48 | Survey |  | 2023-12-12 | 2023-12-14 | 3
9 | ROW in check survey works. | 70-71 | Survey |  | 2023-12-15 | 2024-12-10 | 362
10 | ROW in check survey works. | 71-72 | Survey |  | 2023-12-15 | 2024-02-09 | 57
11 | ROW in check survey works. | 72-73 | Survey |  | 2023-12-15 | 2024-02-09 | 57
12 | ROW in check survey works. | 73-74 | Survey |  | 2023-12-15 | 2024-07-14 | 213
13 | Delay in approval of check survey report from Ap 32 to AP 37. | 32-37 | Survey |  | 2023-12-21 | 2023-12-29 | 9
14 | Delay in approval of check survey From AP 2-10/12 | 2-10/12 | Survey |  | 2023-12-26 | 2024-01-25 | 31 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
15 | Delay in approval of check survey From AP 11A-14. | 11A-14 | Survey |  | 2023-12-26 | 2024-01-25 | 31 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
16 | Location no 11/5 are on Hold due to ROW during check survey, Centre peg not done for verification of benching and others. | 11/5 | Survey |  | 2024-01-17 | 2024-05-20 | 125 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
17 | Location no 11A/0 are on Hold due to ROW during check survey, Centre peg not done for verification of benching and others. | 11A/0 | Survey |  | 2024-01-17 | 2024-05-20 | 125 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
18 | ROW in check survey works. | 40-41 | Survey |  | 2024-01-27 | 2024-04-08 | 73
19 | ROW in check survey works. | 41-42 | Survey |  | 2024-01-27 | 2024-04-08 | 73
20 | ROW in check survey works. | 42-43 | Survey |  | 2024-01-27 | 2024-04-08 | 73
Foundation
S.No | Nature of Hindrance | Loc/Sec. | Affected Activity | Affected Gang Name | Date of occurrence | Date of removal | Period of hindrance | Remarks
1 | ROW due to obstruction by land owner at Loc No 37/2. Post Excavation work was stopped by Land owners. After that cleared on 07/12/2023. | 37/2 | Foundation | Nagana Rai | 2023-12-06 | 2023-12-07 | 2
2 | ROW encountered in Excavation works. | 62/6 | Foundation |  | 2023-12-14 | 2023-12-15 | 2
3 | ROW due to obstruction by land owner at Loc No 26/2. | 26/2 | Foundation | A.B. Construction | 2023-12-16 | 2023-12-17 | 2 | Refer Mail dated 16/12/2023.
4 | Our Whole team of one gang along with its machinery are completely idle at location no 26/2 | 26/2 | Foundation | A.B. Construction | 2023-12-16 | 2023-12-17 | 2 | Idled Resources (Highly Skilled manpower-1, Skilled:- 2, Semi Skilled:- 3, Unskilled:- 4, JCB with operator:- 1, Azax flori with operator:- 1, Tracktor with operator:- 1, Tanker with Operator:- 1, Bolero/Camper with Diesel:- 1)
5 | ROW at Location No 27/11. | 27/11 | Foundation | Nagana Rai | 2023-12-06 | 2024-02-12 | 69 | Email dated 18/1/24 regarding Frequent obstruction by landowners. Your email dated 12.02.24 regarding workfront
6 | ROW at location no 28/1 due to frequent interupption by land owner of PKG F. | 28/1 | Foundation | N.R. Enterprises | 2023-12-26 |  | Awaited | Reference Email dated 26/12/2023.
7 | Gang is idled for full day. During idling attempted 5 nos locations to start the work. But all are found in ROW. |  | Foundation | N.R. Enterprises | 2023-12-26 | 2023-12-29 | 4 | Reference Email dated 26/12/2023. Idled Resources (Highly Skilled manpower-1, Skilled:- 2, Semi Skilled:- 3, Unskilled:- 5, JCB with operator:- 1, Azax flori with operator:- 1, Tracktor with operator:- 1, Tanker with Operator:- 1, Bolero/Camper with Diesel:- 1)
8 | ROW in Foundation work in sawan Moolraj village at Loc No 28/2 | 28/2 | Foundation |  | 2023-12-26 | 2024-01-27 | 33 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
9 | ROW in Foundation work in sawan Moolraj village at Loc No 28/3 | 28/3 | Foundation |  | 2023-12-26 | 2025-02-03 | 406 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
10 | ROW in Foundation work in sawan Moolraj village at Loc No 28/4 | 28/4 | Foundation |  | 2023-12-26 | 2025-02-03 | 406 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
11 | ROW in Foundation work in sawan Moolraj village at Loc No 28/5 | 28/5 | Foundation |  | 2023-12-26 | 2025-01-22 | 394 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
12 | ROW in Foundation work in sawan Moolraj village at Loc No 28/6 | 28/6 | Foundation |  | 2023-12-26 | 2024-01-16 | 22 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
13 | ROW in Foundation work in sawan Moolraj village at Loc No 28/7 | 28/7 | Foundation |  | 2023-12-26 | 2025-01-30 | 402 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
14 | ROW in Foundation work in sawan Moolraj village at Loc No 28/8 | 28/8 | Foundation |  | 2023-12-26 | 2025-01-25 | 397 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
15 | ROW in Foundation work in sawan Moolraj village at Loc No 29/0 | 29/0 | Foundation |  | 2023-12-26 | 2025-01-11 | 383 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
16 | ROW in Foundation work in sawan Moolraj village at Loc No 29/1 | 29/1 | Foundation |  | 2023-12-26 | 2025-02-22 | 425 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
17 | ROW in Foundation work in sawan Moolraj village at Loc No 29/2 | 29/2 | Foundation |  | 2023-12-26 | 2025-03-01 | 432 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
18 | ROW in Foundation work in sawan Moolraj village at Loc No 29/3 | 29/3 | Foundation |  | 2023-12-26 | 2025-03-02 | 433 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
19 | ROW in Foundation work in sawan Moolraj village at Loc No 29/4 | 29/4 | Foundation |  | 2023-12-26 | 2025-02-20 | 423 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
20 | ROW in Foundation work in sawan Moolraj village at Loc No 30/0 | 30/0 | Foundation |  | 2023-12-26 | 2025-02-13 | 416 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
21 | ROW in Foundation work in sawan Moolraj village at Loc No 30/1 | 30/1 | Foundation |  | 2023-12-26 | 2025-02-15 | 418 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
22 | ROW in Foundation work in sawan Moolraj village at Loc No 30/2 | 30/2 | Foundation |  | 2023-12-26 | 2025-02-28 | 431 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
23 | ROW in Foundation work in sawan Moolraj village at Loc No 30/3 | 30/3 | Foundation |  | 2023-12-26 | 2025-02-25 | 428 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
24 | ROW in Foundation work in sawan Moolraj village at Loc No 30/4 | 30/4 | Foundation |  | 2023-12-26 | 2025-05-21 | 513 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
25 | ROW in Foundation work in sawan Moolraj village at Loc No 30/5 | 30/5 | Foundation |  | 2023-12-26 | 2025-05-30 | 522 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
26 | ROW in Foundation work in sawan Moolraj village at Loc No 30/6 | 30/6 | Foundation |  | 2023-12-26 |  | Awaited | Email dated 18/1/24 regarding Frequent obstruction by landowners.
27 | ROW in Foundation work in sawan Moolraj village at Loc No 31/0 | 31/0 | Foundation |  | 2023-12-26 |  | Awaited | Email dated 18/1/24 regarding Frequent obstruction by landowners.
28 | ROW in Foundation work in sawan Moolraj village at Loc No 31/1 | 31/1 | Foundation |  | 2023-12-26 | 2025-03-05 | 436 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
29 | ROW in Foundation work in sawan Moolraj village at Loc No 31/2 | 31/2 | Foundation |  | 2023-12-26 | 2025-03-02 | 433 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
30 | ROW in Foundation work in sawan Moolraj village at Loc No 32/0 | 32/0 | Foundation |  | 2023-12-26 | 2025-02-26 | 429 | Email dated 18/1/24 regarding Frequent obstruction by landowners.
31 | ROW encountered while pit marking. | 59/15 | Foundation |  | 2024-01-11 | 2024-01-15 | 5
32 | ROW encountered while pit marking. | 59/16 | Foundation |  | 2024-01-11 | 2024-01-15 | 5
33 | ROW encountered while pit marking. | 60/3 | Foundation |  | 2024-01-11 | 2024-01-13 | 3
34 | ROW encountered while pit marking. | 60/4 | Foundation |  | 2024-01-11 | 2024-01-13 | 3
35 | ROW encountered while pit marking. | 60/11 | Foundation |  | 2024-01-13 | 2024-01-19 | 7
36 | Shifting of 11 KV Line in Location No 26/4 as 11 KV Line pass through centre of the Pit D. | 26/4 | Foundation |  | 2024-01-20 | 2024-01-23 | 4 | Email dated 20/01/2024 regarding shifting of 11 KV Line. On dated 23/1/24, FDN location 5 Mtr shifted towards 26/3 for execution of Foundation works.
37 | Excavation work stopped at 28/2 after completion of 3 Pit excavation works due to ROW. | 28/2 | Foundation | A.B. Construction | 2024-01-28 | 2024-02-12 | 16 | D.P.R. Dated 28-01-24. 10 Nos Manpower are idled due to this hindrances (confirmed by D.P.R. Dated 29.01.2024), Your email dated 12.02.24 regarding workfront
38 | ROW encountered during excavation . | 64/10 | Foundation |  | 2024-02-01 | 2024-02-07 | 7
39 | Excavation work could not done at 27/5 after completion of 3 Pit excavation works due to ROW. | 27/5 | Foundation | Majisa Construction | 2024-02-02 | 2024-03-05 | 33 | DPR dated 03.02.24. Email dated 22.02.24 Sterlite's Part G & F 765KV Fategarh -III Beawar TL
40 | Excavation work could not done at 27/6 due to ROW. | 27/6 | Foundation | Majisa Construction | 2024-02-08 | 2024-05-07 | 90
41 | Excavation work could not done at 27/7 due to ROW. | 27/7 | Foundation | Majisa Construction | 2024-02-08 | 2025-05-18 | 466
42 | Excavation work could not done at 32/1 due to ROW. | 32/1 | Foundation |  | 2024-02-08 | 2025-02-28 | 387
43 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 32/2 | Foundation |  | 2024-02-08 | 2025-02-07 | 366
44 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 32/3 | Foundation |  | 2024-02-08 | 2025-02-03 | 362
45 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 32/4 | Foundation |  | 2024-02-08 | 2025-02-03 | 362
46 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 33/0 | Foundation |  | 2024-02-08 | 2025-02-12 | 371
47 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 33/1 | Foundation |  | 2024-02-08 | 2025-01-31 | 359
48 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 34/0 | Foundation |  | 2024-02-08 | 2025-01-27 | 355
49 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 34/1 | Foundation |  | 2024-02-08 | 2025-01-05 | 333
50 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 34/2 | Foundation |  | 2024-02-08 | 2025-01-16 | 344
51 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 34/3 | Foundation |  | 2024-02-08 | 2024-02-14 | 7 | Email dated 14.01.2024 regarding KEC - Sterlite's Part G & F 765KV Fategarh -III Beawar TL
52 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 34/4 | Foundation |  | 2024-02-08 | 2025-02-15 | 374
53 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/0 | Foundation |  | 2024-02-08 | 2025-01-02 | 330
54 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/1 | Foundation |  | 2024-02-08 | 2025-03-20 | 407
55 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/2 | Foundation |  | 2024-02-08 | 2025-01-03 | 331
56 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/3 | Foundation |  | 2024-02-08 | 2025-01-30 | 358 | Your email dated 12.02.24 regarding workfront. This locations is reattempted on 28.01.2024 after verbal communication by SPTL by the location found in ROW. Again SPTL claimed that ROW cleared on 30.01.25.
57 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/4 | Foundation |  | 2024-02-08 | 2024-02-12 | 5 | Your email dated 12.02.24 regarding workfront
58 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 35/5 | Foundation |  | 2024-02-08 | 2025-01-27 | 355
59 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 36/0 | Foundation |  | 2024-02-08 | 2024-02-12 | 5 | Your email dated 12.02.24 regarding workfront
60 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 36/2 | Foundation |  | 2024-02-08 |  | Awaited
61 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 36/3 | Foundation |  | 2024-02-08 |  | Awaited
62 | Row in foundation work due to Obstruction by land owner in Nimba ki Dhani Village. | 36/4 | Foundation |  | 2024-02-08 |  | Awaited
63 | ROW in Excavation as Landowner not allowing for pit marking. | 26/7 | Foundation | Mehai Construction | 2024-02-19 | 2024-12-30 | 316 | DPR of 19.02.24. Email dated Sterlite's Part G & F 765KV Fategarh -III Beawar TL.
64 | ROW in Pit marking as Landowner not allowing for pit marking. | 26/8 | Foundation | Mehai Construction | 2024-02-19 |  | Awaited | DPR of 19.02.24. Email dated Sterlite's Part G & F 765KV Fategarh -III Beawar TL.
65 | ROW in Pit marking by Landowner. Further nearby location 22/0 excavation not done due to ROW. Excavator machine is standing idle. He committed to increase the gang strength but due to non-availability of clear work front they have planned to reduce the strength if locations not allocated timely. | 22/0 | Foundation |  | 2024-02-18 |  | Awaited | DPR of 19.02.24. Email dated Sterlite's Part G & F 765KV Fategarh -III Beawar TL. Email dated 25.02.24 regarding Workfront Delays and Local Villager Interruptions in PKG G & PKG F
66 | ROW encountered during excavation . | 61/10 | Foundation |  | 2024-02-19 | 2024-02-29 | 11
67 | ROW encountered during excavation . | 61/4 | Foundation |  | 2024-02-19 | 2024-02-29 | 11
68 | ROW encountered while pit marking. | 62/0 | Foundation |  | 2024-02-19 | 2024-02-29 | 11
69 | Pit marking not done due to cultivated land and SPTL not allowing for further pit marking. | 21/9 | Foundation |  | 2024-02-22 | 2025-05-13 | 447 | D.P.R. Dated 22.02.24
70 | Gang was shifted after completion of location no 23/1 (G) on dated 22.02.24 but due to non-availability of nearby Workfront gang is shifted at 22/5 after one day idling at 22/5. on a progress front he have not worked any productivity till today after 23rd Feb. his time is lapsed on shifting of gang and machinery. |  | Foundation | A.B. Construction | 2024-02-25 | 2024-02-26 | 2 | Email dated 25.02.24 regarding Workfront Delays and Local Villager Interruptions in PKG G & PKG F
71 | Due to interruptions by landowners works are stopped. and gang is completely idle along with machinery. (this team have ability to execute the works in two locations at a time). | 26/6 | Foundation | Mehai Contruction | 2024-02-25 | 2024-02-26 | 2 | Email dated 25.02.24 regarding Workfront Delays and Local Villager Interruptions in PKG G & PKG F
72 | Gang idled due to clear workfront not available after completion of 26/6. | 26/6 | Foundation | Mehai Construction | 2024-03-01 | 2024-03-04 | 4 | Email dated 02/03/24 regarding Survey & Foundation update (Workfront Delay/Interruptions updates in PKG G & PKG F
73 | 22/1:- Completed today. Machinery idled due to Nearby locations not available. Further Gang left the site due to workfront not available. | 22/1 | Foundation | Swarup Enterprises | 2024-03-02 | 2024-03-03 | 2 | Email dated 02/03/24 regarding Survey & Foundation update (Workfront Delay/Interruptions updates in PKG G & PKG F
74 | ROW encountered while pit marking. | 53/6 | Foundation |  | 2024-03-06 | 2024-05-24 | 80
75 | ROW encountered while pit marking. | 53/7 | Foundation |  | 2024-03-06 | 2024-04-04 | 30
76 | ROW encountered while pit marking. | 53/8 | Foundation |  | 2024-03-06 | 2024-04-04 | 30
77 | ROW encountered while pit marking. | 54/0 | Foundation |  | 2024-03-06 | 2024-05-24 | 80
78 | ROW encountered while pit marking. | 54/1 | Foundation |  | 2024-03-06 | 2024-05-24 | 80
79 | ROW encountered while pit marking. | 54/2 | Foundation |  | 2024-03-06 | 2024-05-24 | 80
80 | SPTL representatives not aggreed to start pit marking along with Excavation against clear workfront shared on may'10 at loc no 8/8 (F) | 8/8 | Foundation | Mateshwari Construction/HS Engineering | 2024-05-17 |  | Awaited | Gang idled from 14.11.2024 to 16.11.2024 afetr 2nd attampt. After idling SPTL allocate other locations.
81 | Works stopped due to ROW by landowners at location No 10/13. | 10/13 | Foundation | Mateshwari Construction | 2024-05-04 | 2024-05-04 | 1
82 | Works stopped due to ROW by landowners at location No 10/12. | 10/12 | Foundation | Mateshwari Construction | 2024-05-14 | 2024-06-16 | 34 | Reference daily progress report.
83 | Works not started due to ROW. | 10/9 | Foundation | Jai Bhawani | 2024-07-04 | 2024-08-07 | 35
84 | Works not started due to ROW. | 10/10 | Foundation | Jai Bhawani | 2024-07-04 |  | Awaited
85 | Works not started due to ROW. | 10/21 | Foundation | Jai Bhawani | 2024-07-04 | 2024-07-07 | 4
86 | Works not started due to ROW. | 14A/2 | Foundation | Majisa Construction | 2024-07-04 | 2024-09-07 | 66
87 | Works not started due to ROW. | 15/0 | Foundation | Majisa Construction | 2024-07-04 | 2024-07-07 | 4
88 | No work-done due to Continuous rain at location | 10/3 | Foundation | Jai Bhawani | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
89 | No work-done due to Continuous rain at location | 10/4 | Foundation | Jai Bhawani | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
90 | No work-done due to Continuous rain at location | 11A/7 | Foundation | Punia Construction | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
91 | No work-done due to Continuous rain at location | 16/3 | Foundation | Majisa Construction | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
92 | No work-done due to Continuous rain at location | 18/2 | Foundation | Vibe infra | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
93 | No work-done due to Continuous rain at location | 17/3 | Foundation | J.P. Infra | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
94 | No work-done due to Continuous rain at location | 43/9 | Foundation | N.R. Enterprises | 2024-08-04 | 2024-08-06 | 3 | DPR email on regular basis.
95 | Works stopped due to ROW at loc no 16/1. | 16/1 | Foundation | Om Enterprise | 2024-08-24 | 2024-08-25 | 2 | DPR email on regular basis.
96 | Works stopped due to ROW at loc no 43/7 | 43/7 | Foundation | N.R. Enterprises | 2024-08-27 | 2024-08-30 | 4 | DPR email on regular basis.
97 | Full day ROW. 9 nos manpower alongwith JCB (JCB idled since last 6 days). ROW cleared after 2nd half on dated 29.09.2024 | 19/3 | Foundation | Vibe infra | 2024-09-28 | 2024-09-29 | 2 | DPR email on regular basis.
98 | ROW encountered while pit marking. | 65/7 | Foundation |  | 2024-10-10 | 2024-11-11 | 33
99 | ROW encountered while pit marking. | 65/8 | Foundation |  | 2024-10-10 | 2024-11-11 | 33
100 | ROW encountered while pit marking. | 65/10 | Foundation |  | 2024-10-10 | 2025-01-22 | 105
101 | ROW encountered while pit marking. | 68/0 | Foundation |  | 2024-10-10 | 2025-01-13 | 96
102 | ROW encountered while pit marking. | 55/0 | Foundation |  | 2024-10-10 | 2025-01-13 | 96
103 | ROW encountered while pit marking. | 55/1 | Foundation |  | 2024-10-10 | 2025-01-13 | 96
104 | ROW encountered while pit marking. | 55/2 | Foundation |  | 2024-10-10 | 2025-01-13 | 96
105 | ROW encountered while pit marking. | 71/1 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
106 | ROW encountered while pit marking. | 71/2 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
107 | ROW encountered while pit marking. | 71/3 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
108 | ROW encountered while pit marking. | 71/4 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
109 | ROW encountered while pit marking. | 71/5 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
110 | ROW encountered while pit marking. | 71/8 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
111 | ROW encountered while pit marking. | 72/0 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
112 | ROW encountered while pit marking. | 72/1 | Foundation |  | 2024-10-10 | 2024-12-15 | 67
113 | Machinery stucked at location due to ROW, idled (machinery alongwith Gang) till 3 PM on dated 15.10.24. ROW resolved at 03:00 PM. | 22/12 | Foundation | RBM | 2024-10-14 | 2024-10-15 | 2 | DPR email on regular basis.
114 | Full day ROW from 13/3 G & 12/0 F. | 13/3, 12/0 | Foundation | Punia Construction | 2024-10-24 | 2024-10-25 | 2 | DPR email on regular basis.
115 | work could not started due to ROW. | 13/4 | Foundation |  | 2024-11-01 |  | Awaited | DPR email on regular basis.
116 | work could not started due to ROW. | 14A/0 | Foundation |  | 2024-11-01 |  | Awaited | DPR email on regular basis.
117 | Excavation can't be started due to ROW. | 22/9 | Foundation |  | 2024-11-17 | 2024-12-01 | 15 | DPR email on regular basis.
118 | Excavation can't be started due to ROW in approach road. | 22/4 | Foundation | J.P. Infra | 2024-11-18 | 2024-11-20 | 3 | DPR email on regular basis.
119 | Excavation can't be started due to ROW. | 6/1 & 6/2 | Foundation | H.s Engineering | 2024-11-18 | 2024-11-20 | 3 | DPR email on regular basis.
120 | Works Stopped due to ROW. | 22/10 | Foundation | RBM | 2024-12-09 |  | Awaited | DPR email on regular basis.
121 | No work done due to ROW by local persons. Gang Idle till 19.12.2024. Further nex location allaocted 8/9 in PKG G. | 6/2 | Foundation | HS Engineering | 2024-12-11 | 2024-12-19 | 9 | DPR email on regular basis.
122 | Works Stopped due to ROW. | 35/4 | Foundation | Parsuram Sahi | 2024-12-30 | 2024-12-30 | 1 | DPR email on regular basis.
123 | Work can't started due to ROW. | 1/0 | Foundation |  | 2024-12-02 | 2025-02-23 | 84 | Informed to SPTL by mail Communications
124 | Work can't started due to ROW. | 1A/0 | Foundation |  | 2024-12-02 | 2025-01-12 | 42 | Informed to SPTL by mail Communications
125 | Work can't started due to ROW. | 1A/1 | Foundation |  | 2024-12-02 | 2025-01-13 | 43 | Informed to SPTL by mail Communications
126 | Work can't started due to ROW. | 1A/2 | Foundation |  | 2024-12-02 | 2025-01-21 | 51 | Informed to SPTL by mail Communications
127 | Work can't started due to ROW. | 1A/3 | Foundation |  | 2024-12-02 | 2025-01-16 | 46 | Informed to SPTL by mail Communications
128 | Work can't started due to ROW. | 1A/4 | Foundation |  | 2024-12-02 | 2025-01-15 | 45 | Informed to SPTL by mail Communications. This locations is reattmpetd in 28.01.25 after pit marking the locations is found under ROW.
129 | Work can't started due to ROW. | 1A/5 | Foundation |  | 2024-12-02 | 2025-01-22 | 52 | Informed to SPTL by mail Communications
130 | Work can't started due to ROW. | 1A/6 | Foundation |  | 2024-12-02 | 2025-01-21 | 51 | Informed to SPTL by mail Communications
131 | Work can't started due to ROW. | 1A/7 | Foundation |  | 2024-12-02 | 2025-02-26 | 87 | Informed to SPTL by mail Communications
132 | Work can't started due to ROW. | 1A/8 | Foundation |  | 2024-12-02 | 2025-05-02 | 152 | Informed to SPTL by mail Communications
133 | Work can't started due to ROW. | 2/0 | Foundation |  | 2024-12-02 | 2025-01-14 | 44 | Informed to SPTL by mail Communications
134 | Work can't started due to ROW. | 2/1 | Foundation |  | 2024-12-03 | 2025-03-12 | 100 | Informed to SPTL by mail Communications
135 | Work can't started due to ROW. | 2/7 | Foundation |  | 2024-12-03 | 2025-05-30 | 179 | Informed to SPTL by mail Communications
136 | Work can't started due to ROW. | 2/8 | Foundation |  | 2024-12-03 | 2025-02-04 | 64 | Informed to SPTL by mail Communications
137 | Work can't started due to ROW. | 2/9 | Foundation |  | 2024-12-03 | 2025-09-27 | 299 | Informed to SPTL by mail Communications
138 | Work can't started due to ROW. | 3/0 | Foundation |  | 2024-12-03 | 2025-04-12 | 131 | Informed to SPTL by mail Communications
139 | Work can't started due to ROW. | 4/0 | Foundation |  | 2024-12-18 | 2025-02-18 | 63 | Informed to SPTL by mail Communications
140 | Work can't started due to ROW. | 4/1 | Foundation |  | 2024-12-18 | 2025-04-28 | 132 | Informed to SPTL by mail Communications
141 | Work can't started due to ROW. | 4/2 | Foundation |  | 2024-12-18 |  | Awaited | Informed to SPTL by mail Communications
142 | Work can't started due to ROW. | 4/3 | Foundation |  | 2024-12-18 | 2025-05-13 | 147 | Informed to SPTL by mail Communications
143 | Work can't started due to ROW. | 4/4 | Foundation |  | 2024-12-18 |  | Awaited | Informed to SPTL by mail Communications
144 | Work can't started due to ROW. | 5/0 | Foundation |  | 2024-12-18 |  | Awaited | Informed to SPTL by mail Communications
145 | Work can't started due to ROW. | 6/0 | Foundation |  | 2024-12-18 |  | Awaited | Informed to SPTL by mail Communications
146 | Work can't started due to ROW. | 7/0 | Foundation |  | 2024-12-18 |  | Awaited | Informed to SPTL by mail Communications
147 | Work can't started due to ROW. | 8/0 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications
148 | Work can't started due to ROW. | 8/1 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications
149 | Work can't started due to ROW. | 8/2 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications. Dated 17.05.2025 location is attempted with police protection but all the locations are in ROW.
150 | Work can't started due to ROW. | 8/3 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications. Dated 17.05.2025 location is attempted with police protection but all the locations are in ROW.
151 | Work can't started due to ROW. | 8/4 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications. Dated 17.05.2025 location is attempted with police protection but all the locations are in ROW.
152 | Work can't started due to ROW. | 8/5 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications. Dated 17.05.2025 location is attempted with police protection but all the locations are in ROW.
153 | Work can't started due to ROW. | 8/6 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications. Dated 17.05.2025 location is attempted with police protection but all the locations are in ROW.
154 | Work can't started due to ROW. | 8/11 | Foundation |  | 2024-12-07 | 2025-05-12 | 157 | Informed to SPTL by mail Communications
155 | Work can't started due to ROW. | 8/12 | Foundation |  | 2024-12-07 | 2025-05-12 | 157 | Informed to SPTL by mail Communications
156 | Work can't started due to ROW. | 9/0 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications
157 | Work can't started due to ROW. | 10/0 | Foundation |  | 2024-12-07 | 2025-05-14 | 159 | Informed to SPTL by mail Communications
158 | Work can't started due to ROW. | 10/1 | Foundation |  | 2024-12-07 | 2025-05-16 | 161 | Informed to SPTL by mail Communications
159 | Work can't started due to ROW. | 10/2 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications
160 | Work can't started due to ROW. | 10/7 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications
161 | Work can't started due to ROW. | 10/15 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications
162 | Work can't started due to ROW. | 10/16 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications
163 | Work can't started due to ROW. | 10/22 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications
164 | Work can't started due to ROW. | 10/23 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications
165 | Work can't started due to ROW. | 11/0 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications
166 | Work can't started due to ROW. | 11/1 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications
167 | Work can't started due to ROW. | 11/2 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications
168 | Work can't started due to ROW. | 11/3 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications
169 | Work can't started due to ROW. | 11/4 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications
170 | Work can't started due to ROW. | 19/4 | Foundation |  | 2024-12-07 |  | Awaited | Informed to SPTL by mail Communications
171 | Work can't started due to ROW. | 19/5 | Foundation |  | 2024-12-07 | 2025-06-01 | 177 | Informed to SPTL by mail Communications
172 | Work can't started due to ROW. | 20/0 | Foundation |  | 2024-12-17 |  | Awaited | Informed to SPTL by mail Communications
173 | Work can't started due to ROW. | 20/1 | Foundation |  | 2024-12-17 |  | Awaited | Informed to SPTL by mail Communications
174 | Work can't started due to ROW. | 20/2 | Foundation |  | 2024-12-17 |  | Awaited | Informed to SPTL by mail Communications
175 | Work can't started due to ROW. | 20/3 | Foundation |  | 2024-12-17 |  | Awaited | Informed to SPTL by mail Communications
176 | Work can't started due to ROW. | 21/0 | Foundation |  | 2024-12-17 |  | Awaited | Informed to SPTL by mail Communications
177 | Work can't started due to ROW. | 21/1 | Foundation |  | 2024-12-17 |  | Awaited | Informed to SPTL by mail Communications
178 | Work can't started due to ROW. | 21/2 | Foundation |  | 2024-12-17 |  | Awaited | Informed to SPTL by mail Communications
179 | Work can't started due to ROW. | 21/3 | Foundation |  | 2024-12-17 |  | Awaited | Informed to SPTL by mail Communications. Reattempted on 23.05.2025 but the locations still persist in ROW.
180 | Work can't started due to ROW. | 21/4 | Foundation |  | 2024-12-17 |  | Awaited | Informed to SPTL by mail Communications
181 | Work can't started due to ROW. | 21/5 | Foundation |  | 2024-12-17 | 2025-05-29 | 164 | Informed to SPTL by mail Communications, tried on 07.05.25 also after pit marking location is in ROW then Excavation started on loc no 21/7.
182 | Work can't started due to ROW. | 21/6 | Foundation |  | 2024-12-17 |  | Awaited | Informed to SPTL by mail Communications
183 | Work can't started due to ROW. | 21/7 | Foundation |  | 2024-12-17 | 2025-05-07 | 142 | Informed to SPTL by mail Communications
184 | Work can't started due to ROW. | 21/8 | Foundation |  | 2024-12-17 |  | Awaited | Informed to SPTL by mail Communications
185 | Work can't started due to ROW. | 23/0 | Foundation |  | 2024-12-17 |  | Awaited | Informed to SPTL by mail Communications
186 | Work can't started due to ROW. | 24/0 | Foundation |  | 2024-12-13 |  | Awaited | Informed to SPTL by mail Communications
187 | Work can't started due to ROW. | 26/0 | Foundation |  | 2024-12-13 |  | Awaited | Informed to SPTL by mail Communications
188 | Work can't started due to ROW. | 26/1 | Foundation |  | 2024-12-13 |  | Awaited | Informed to SPTL by mail Communications
189 | Work can't started due to ROW. | 27/0 | Foundation |  | 2024-12-13 | 2025-05-06 | 145 | Informed to SPTL by mail Communications
190 | Work can't started due to ROW. | 27/1 | Foundation |  | 2024-12-13 | 2025-05-02 | 141 | Informed to SPTL by mail Communications
191 | Work can't started due to ROW. | 27/2 | Foundation |  | 2024-12-13 | 2025-04-16 | 125 | Informed to SPTL by mail Communications
192 | Work can't started due to ROW. | 27/3 | Foundation |  | 2024-12-13 | 2025-04-11 | 120 | Informed to SPTL by mail Communications
193 | Work can't started due to ROW. | 27/4 | Foundation |  | 2024-12-13 | 2025-05-12 | 151 | Informed to SPTL by mail Communications
194 | Work can't started due to ROW. | 37/0 | Foundation |  | 2024-12-13 |  | Awaited | Informed to SPTL by mail Communications
195 | Work can't started due to ROW. | 37/1 | Foundation |  | 2024-12-13 |  | Awaited | Informed to SPTL by mail Communications
196 | Work can't started due to ROW. | 37/3 | Foundation |  | 2024-12-13 |  | Awaited | Informed to SPTL by mail Communications
197 | Work can't started due to ROW. | 38/0 | Foundation |  | 2024-12-13 |  | Awaited | Informed to SPTL by mail Communications
198 | Work can't started due to ROW. | 38/1 | Foundation |  | 2024-12-13 | 2025-04-21 | 130 | Informed to SPTL by mail Communications
199 | Work can't started due to ROW. | 38/2 | Foundation |  | 2024-12-15 | 2025-04-16 | 123 | Informed to SPTL by mail Communications
200 | Work can't started due to ROW. | 38/3 | Foundation |  | 2024-12-15 | 2025-05-12 | 149 | Informed to SPTL by mail Communications
201 | Work can't started due to ROW. | 38/4 | Foundation |  | 2024-12-15 | 2025-04-05 | 112 | Informed to SPTL by mail Communications
202 | Work can't started due to ROW. | 39/0 | Foundation |  | 2024-12-15 | 2025-04-11 | 118 | Informed to SPTL by mail Communications
203 | Work can't started due to ROW. | 39/1 | Foundation |  | 2024-12-15 | 2025-04-28 | 135 | Informed to SPTL by mail Communications. Reattempted on 25.06.2025.
204 | Work can't started due to ROW. | 40/0 | Foundation |  | 2024-12-15 | 2025-04-28 | 135 | Informed to SPTL by mail Communications. Work started on 26.04.2025 further during excavation works are stopped the land owners.
205 | Work can't started due to ROW. | 40/1 | Foundation |  | 2024-12-15 | 2025-05-02 | 139 | Informed to SPTL by mail Communications
206 | Work can't started due to ROW. | 40/3 | Foundation |  | 2024-12-15 | 2025-05-18 | 155 | Informed to SPTL by mail Communications
207 | Work can't started due to ROW. | 41/0 | Foundation |  | 2024-12-15 | 2025-04-20 | 127 | Informed to SPTL by mail Communications
208 | Work can't started due to ROW. | 41/1 | Foundation |  | 2024-12-15 | 2025-05-21 | 158 | Informed to SPTL by mail Communications
209 | Work can't started due to ROW. | 42/4 | Foundation |  | 2024-12-15 | 2025-05-16 | 153 | Informed to SPTL by mail Communications
210 | Work can't started due to ROW. | 43/10 | Foundation |  | 2024-12-15 | 2025-02-16 | 64 | Informed to SPTL by mail Communications
Erection
S.No | Nature of Hindrance | Loc/Sec. | Affected Activity | Affected Gang Name | Date of occurrence | Date of removal | Period of hindrance | Remarks
1 | Gang idle due to ROW at 10/19 | 10/19 | Erection | Yogender Mahto | 2024-09-10 | 2024-09-12 | 3 | DPR email on regular basis.
2 | Rafikul Islam:- 11A/0 WIP. No work due to ROW. | 11A/0 | Erection | Rafikul Islam | 2024-10-24 | 2024-10-25 | 2 | DPR email on regular basis.
3 | Jailal ageria:- 16/0 WIP. No work due to ROW. | 16/0 | Erection | Jailal Ageria | 2024-10-24 | 2024-10-25 | 2 | DPR email on regular basis.
4 | Nirmal Mahto:- 16/2 WIP. No work due to ROW. | 16/2 | Erection | Nirmal Mahto | 2024-10-24 | 2024-10-25 | 2 | DPR email on regular basis.
5 | work could not started due to ROW. | 14A/2 | Erection |  | 2024-11-01 |  | Awaited | DPR email on regular basis.
6 | work could not started due to ROW. | 15/0 | Erection |  | 2024-11-01 |  | Awaited | DPR email on regular basis.
7 | work could not started due to ROW. | 17/4 | Erection |  | 2024-11-02 |  | Awaited | DPR email on regular basis.
8 | work could not started due to ROW. | 17/5 | Erection | Bina Devi | 2024-11-02 | 2024-11-23 | 22 | DPR email on regular basis. Gang reattempted on dated 22.11.24 after allocating by SPTL, but ROW is still not resolved. And gang is being idle.
9 | work could not started due to ROW. | 18/0 | Erection |  | 2024-11-02 |  | Awaited | DPR email on regular basis.
10 | 13/1 WIP. No work due to ROW. | 13/1 | Erection | Jailal Ageria | 2024-11-26 |  | Awaited | DPR email on regular basis.
11 | Works Stopped due to ROW. | 13/0 | Erection | Jailal Agerai | 2024-12-30 |  | Awaited | DPR email on regular basis.
12 | Works Stopped due to ROW. | 11A/5 | Erection | Deglal Mahto | 2024-12-30 | 2024-12-31 | 2 | DPR email on regular basis.
13 | Work can't started due to ROW. | 10/5 | Erection |  | 2025-01-01 |  | Awaited | Informed to SPTL by mail Communications
14 | Work can't started due to ROW. | 11A/4 | Erection |  | 2025-01-01 |  | Awaited | Informed to SPTL by mail Communications
15 | Work can't started due to ROW. | 11A/8 | Erection |  | 2025-01-01 |  | Awaited | Informed to SPTL by mail Communications
16 | Work can't started due to ROW. | 12/0 | Erection |  | 2025-01-01 |  | Awaited | Informed to SPTL by mail Communications
17 | Work can't started due to ROW. | 13/3 | Erection |  | 2025-01-01 |  | Awaited | Informed to SPTL by mail Communications
18 | Work can't started due to ROW. | 14/0 | Erection |  | 2025-01-01 |  | Awaited | Informed to SPTL by mail Communications
19 | Work can't started due to ROW. | 18/3 | Erection |  | 2025-01-01 |  | Awaited | Informed to SPTL by mail Communications
20 | Work can't started due to ROW. | 19/1 | Erection |  | 2025-01-01 |  | Awaited | Informed to SPTL by mail Communications
21 | Work can't started due to ROW. | 19/2 | Erection |  | 2025-01-01 |  | Awaited | Informed to SPTL by mail Communications
Others
S.No | Nature of Hindrance | Loc/Sec. | Affected Activity | Affected Gang Name | Date of occurrence | Date of removal | Period of hindrance | Remarks
1 | Delay in finalization of locations for Soil investigation |  | Others |  | 2023-12-06 |  | Awaited | 24 Locations SPT Confirmed on 24th Feb 2024.
2 | Delay in approval of L2 Schedule. |  | Others |  | 2023-12-06 | 2024-01-23 | 49 | Approval reference email dated 23.01.24.
3 | New tower optimization and shifting was proposed by SPTL on dated 18th March 2024. Final confirmation for omit of optimization is received on 15.05.2024. |  | Others |  | 2024-03-18 | 2024-05-15 | 59 | Email dated 15/5/24.
Stringing
S.No | Nature of Hindrance | Loc/Sec. | Affected Activity | Affected Gang Name | Date of occurrence | Date of removal | Period of hindrance | Remarks
1 | Insulator hoisting not done due to ROW at location no 72/1. | 72/1 | Stringing |  | 2025-05-24 | 2025-05-26 | 3
Formulas:
Period of hindrance = +IF([Date of removal (Last attempt)]="","Awaited",DAYS([Date of removal (Last attempt)],[Date of 1st attempt])+1)

## Page Chart
Progress Summary'!A1 | [8 empty] | Village wise dashboard
Location Wise Status | [8 empty] | Foundation | [5 empty] | Erection
Sr. No. | Loc No. | TOT | Village Name | Span | FDN | ERE | Str |  | Village wise breakups | Total | Comp. | WIP | Clear | ROW | Total | Comp. | WIP | Clear | ROW | Yet to attempt | Balance
1 | 1/0 | DD60+0 | Mandai | 122 | DRY |  |  |  | Total Number of Village (49 No's) | 485 | 415 | 13 | 12 | 45 | 485 | 222 | 2 | 0 | 15 | 246 | 263
2 | 1A/0 | DD60+0 | Mandai | 90 | DRY |  |  |  | Mandai | 16 | 16 | 0 | 0 | 0 | 16 | 3 | 1 | 0 | 0 | 12 | 13
3 | 1A/1 | DA+6 | Mandai | 277.7 | DFR | E |  |  | Harwa | 22 | 6 | 3 | 5 | 8 | 22 | 0 | 0 | 0 | 0 | 22 | 22
4 | 1A/2 | DA+0 | Mandai | 386 | DRY | E |  |  | Chak Goonga | 8 | 4 | 2 | 0 | 2 | 8 | 0 | 0 | 0 | 0 | 8 | 8
5 | 1A/3 | DA+0 | Mandai | 443.6 | DRY | E |  |  | Goonga | 5 | 3 | 1 | 0 | 1 | 5 | 2 | 0 | 0 | 1 | 2 | 3
6 | 1A/4 | DA+3 | Mandai | 333.4 | DFR | WIP |  |  | Pusar | 14 | 10 | 0 | 0 | 4 | 14 | 9 | 0 | 0 | 0 | 5 | 5
7 | 1A/5 | DA+0 | Mandai | 431.9 | DRY |  |  |  | Bisoo Khurd | 13 | 6 | 0 | 0 | 7 | 13 | 6 | 0 | 0 | 0 | 7 | 7
8 | 1A/6 | DA+0 | Mandai | 348.7 | Sandy |  |  |  | Bhiyad | 38 | 36 | 0 | 0 | 2 | 38 | 23 | 0 | 0 | 13 | 2 | 15
9 | 1A/7 | DA+3 | Mandai | 395.7 | Sandy |  |  |  | Kashmir | 29 | 13 | 3 | 0 | 13 | 29 | 0 | 0 | 0 | 1 | 28 | 29
10 | 1A/8 | DA+0 | Mandai | 415 | Sandy |  |  |  | Rateu | 35 | 26 | 2 | 2 | 5 | 35 | 0 | 0 | 0 | 0 | 35 | 35
11 | 2/0 | DC1+0 | Mandai | 394.3 | DRY |  |  |  | Sawau Moolraj | 23 | 20 | 1 | 0 | 2 | 23 | 0 | 0 | 0 | 0 | 23 | 23
12 | 2/1 | DA+3 | Mandai | 405.3 | Sandy |  |  |  | Neemba Ki Dhani | 23 | 19 | 0 | 4 | 0 | 23 | 0 | 0 | 0 | 0 | 23 | 23
13 | 2/2 | DA+3 | Mandai | 338.5 | Sandy |  |  |  | Danpura | 13 | 11 | 0 | 1 | 1 | 13 | 0 | 0 | 0 | 0 | 13 | 13
14 | 2/3 | DA+3 | Mandai | 406 | Sandy |  |  |  | Rampura Kharda | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1
15 | 2/4 | DA+3 | Mandai | 429 | Sandy |  |  |  | Manpura Kharda | 2 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 2
16 | 2/5 | DA+3 | Mandai | 411.6 | Sandy |  |  |  | Kharda Charnan | 9 | 9 | 0 | 0 | 0 | 9 | 1 | 0 | 0 | 0 | 8 | 8
17 | 2/6 | DA+3 | Harwa | 425.7 | Sandy |  |  |  | Beniwalon Ki Dhani | 6 | 6 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 4 | 4
18 | 2/7 | DA+3 | Harwa | 408.2 | WIP |  |  |  | Pareu | 4 | 4 | 0 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 1 | 1
19 | 2/8 | DA+0 | Harwa | 354.6 | Sandy |  |  |  | Mahadeo Ka Mandir | 7 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 7 | 7
20 | 2/9 | DA+0 | Harwa | 308.7 | Clear |  |  |  | Chimoniyon Ki Dhani | 8 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 8 | 8
21 | 3/0 | DD60+6 | Harwa | 336 | WIP |  |  |  | Godaron Ki Dhani | 9 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 9
22 | 4/0 | DD60+6 | Harwa | 226.5 | DRY |  |  |  | Daukiyon Ki Dhani | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
23 | 4/1 | DA+0 | Harwa | 343.4 | WIP |  |  |  | Nehru Nagar | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
24 | 4/2 | DA+0 | Harwa | 358.4 | Clear |  |  |  | Nematpura | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0
25 | 4/3 | DA+0 | Harwa | 381 | DRY |  |  |  | Gangapura | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
26 | 4/4 | DA+0 | Harwa | 367.6 | ROW |  |  |  | Barnama Charnan | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0
27 | 5/0 | DB1+9 | Harwa | 423.1 | Clear |  |  |  | Khanora | 13 | 13 | 0 | 0 | 0 | 13 | 9 | 0 | 0 | 0 | 4 | 4
28 | 6/0 | DB2+9 | Harwa | 246 | Clear |  |  |  | Sathuni Purohitan | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
29 | 6/1 | DA+0 | Harwa | 429.9 | DFR |  |  |  | Sathuni Charnan | 8 | 8 | 0 | 0 | 0 | 8 | 3 | 0 | 0 | 0 | 5 | 5
30 | 6/2 | DA+0 | Harwa | 362.4 | DFR |  |  |  | Simarkhiya | 3 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 3
31 | 7/0 | DB1+0 | Harwa | 347.9 | ROW |  |  |  | Bagawas | 11 | 11 | 0 | 0 | 0 | 11 | 5 | 0 | 0 | 0 | 6 | 6
32 | 8/0 | DB1+0 | Harwa | 210.8 | Clear |  |  |  | Mohanpura | 6 | 6 | 0 | 0 | 0 | 6 | 5 | 0 | 0 | 0 | 1 | 1
33 | 8/1 | DA+3 | Harwa | 409.2 | ROW |  |  |  | Meghawas | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
34 | 8/2 | DA+3 | Harwa | 413.6 | ROW |  |  |  | Sagaranari | 10 | 10 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0
35 | 8/3 | DA+0 | Harwa | 393.2 | ROW |  |  |  | Nagana | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
36 | 8/4 | DA+3 | Harwa | 416.5 | ROW |  |  |  | Deoriya | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0
37 | 8/5 | DA+3 | Harwa | 394.6 | ROW |  |  |  | Bakati | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0
38 | 8/6 | DA+3 | Harwa | 393.2 | ROW |  |  |  | Gwalnada | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0
39 | 8/7 | DB1+0 | Chak Goonga | 441.1 | DRY |  |  |  | Godawas Kalan | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0
40 | 8/8 | DA+6 | Chak Goonga | 414.4 | ROW |  |  |  | Doli Kalan | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
41 | 8/9 | DA+3 | Chak Goonga | 395.9 | DFR |  |  |  | Modathali | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0
42 | 8/10 | DA+3 | Chak Goonga | 413.4 | DFR |  |  |  | Piprali | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
43 | 8/11 | DA+0 | Chak Goonga | 402.6 | DRY |  |  |  | Rabariyawas | 11 | 11 | 0 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0
44 | 8/12 | DA+0 | Chak Goonga | 372.1 | WIP |  |  |  | Loonawas Charna | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
45 | 9/0 | DD60+18 | Chak Goonga | 457.7 | ROW |  |  |  | Loonawas Khurd | 12 | 12 | 0 | 0 | 0 | 12 | 9 | 0 | 0 | 0 | 3 | 3
46 | 10/0 | DD60+25 | Chak Goonga | 233.1 | WIP |  |  |  | Borapadakhamar | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 2
47 | 10/1 | DA+0 | Goonga | 443.7 | WIP |  |  |  | Katarda | 12 | 12 | 0 | 0 | 0 | 12 | 9 | 1 | 0 | 0 | 2 | 3
48 | 10/2 | DA+0 | Goonga | 383.2 | ROW |  |  |  | Karni Nagar | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
49 | 10/3 | DA+0 | Goonga | 398.6 | DFR | E |  |  | Basni Jhoonthan | 9 | 9 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0
50 | 10/4 | DA+3 | Goonga | 410.7 | DFR | E |  |  | Sardargarh | 10 | 10 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0
51 | 10/5 | DA+3 | Goonga | 416.2 | DRY | ROW
52 | 10/6 | DA+0 | Pusar | 403.4 | DFR | E
53 | 10/7 | DA+3 | Pusar | 373.9 | ROW
54 | 10/8 | DA+3 | Pusar | 411.8 | DFR | E
55 | 10/9 | DA+0 | Pusar | 414.2 | DRY | E
56 | 10/10 | DA+3 | Pusar | 402.3 | ROW
57 | 10/11 | DA+3 | Pusar | 430.3 | DRY | E
58 | 10/12 | DB1+0 | Pusar | 406.2 | DRY | E
59 | 10/13 | DA+3 | Pusar | 405.251 | DRY
60 | 10/14 | DA+3 | Pusar | 427.085 | DRY | E
61 | 10/15 | DA+3 | Pusar | 400.035 | ROW
62 | 10/16 | DA+3 | Pusar | 412.79 | ROW
63 | 10/17 | DA+3 | Pusar | 387.758 | DFR | E
64 | 10/18 | DA+3 | Pusar | 436.732 | DFR | E
65 | 10/19 | DA+0 | Pusar | 403.689 | DRY | E
66 | 10/20 | DA+3 | Bisoo Khurd | 409.528 | DFR | E
67 | 10/21 | DA+3 | Bisoo Khurd | 419.56 | DFR | E
68 | 10/22 | DA+0 | Bisoo Khurd | 369.467 | ROW
69 | 10/23 | DA+0 | Bisoo Khurd | 403.73 | ROW
70 | 11/0 | DB1+0 | Bisoo Khurd | 368.825 | ROW
71 | 11/1 | DA+0 | Bisoo Khurd | 385.289 | ROW
72 | 11/2 | DA+0 | Bisoo Khurd | 409.446 | ROW
73 | 11/3 | DA+0 | Bisoo Khurd | 385.819 | ROW
74 | 11/4 | DA+0 | Bisoo Khurd | 449.057 | ROW
75 | 11/5 | DA+0 | Bisoo Khurd | 368.102 | DFR | E
76 | 11A/0 | DB1+0 | Bisoo Khurd | 342.28 | DRY | E
77 | 11A/1 | DA+3 | Bisoo Khurd | 405.1 | DRY | E
78 | 11A/2 | DA+0 | Bisoo Khurd | 412.2 | DRY | E
79 | 11A/3 | DA+3 | Bhiyad | 412.2 | DRY | E
80 | 11A/4 | DA+3 | Bhiyad | 422.1 | DRY | ROW
81 | 11A/5 | DA+3 | Bhiyad | 418.3 | DRY | E
82 | 11A/6 | DA+6 | Bhiyad | 384.3 | DRY | E
83 | 11A/7 | DA+9 | Bhiyad | 434.2 | Sandy | E
84 | 11A/8 | DA+6 | Bhiyad | 390.1 | Sandy | ROW
85 | 11A/9 | DA+3 | Bhiyad | 426.3 | DRY | E
86 | 12/0 | DD60+0 | Bhiyad | 405.9 | DRY | ROW
87 | 13/0 | DD60+3 | Bhiyad | 211.9 | DRY | ROW
88 | 13/1 | DA+9 | Bhiyad | 464.3 | DRY | ROW
89 | 13/2 | DA+3 | Bhiyad | 373.7 | DRY | E
90 | 13/3 | DA+3 | Bhiyad | 419.7 | Sandy | ROW
91 | 13/4 | DA+3 | Bhiyad | 420.3 | ROW
92 | 14/0 | DC2+0 | Bhiyad | 400 | Sandy | ROW
93 | 14A/0 | DC1+0 | Bhiyad | 381.4 | ROW
94 | 14A/1 | DA+3 | Bhiyad | 407.8 | DRY | E
95 | 14A/2 | DA+0 | Bhiyad | 401 | DRY | ROW
96 | 15/0 | DC1+0 | Bhiyad | 383.3 | DRY | ROW
97 | 15/1 | DA+3 | Bhiyad | 404.6 | DRY | E
98 | 16/0 | DC1+0 | Bhiyad | 413.3 | DRY | E
99 | 16/1 | DA+0 | Bhiyad | 364.3 | DRY | E
100 | 16/2 | DA+0 | Bhiyad | 414.3 | DRY | E
101 | 16/3 | DA+3 | Bhiyad | 340.3 | DRY | E
102 | 16/4 | DA+0 | Bhiyad | 394.7 | DRY | E
103 | 16/5 | DA+3 | Bhiyad | 425.9 | DRY | E
104 | 17/0 | DB2+3 | Bhiyad | 396.8 | DRY | E
105 | 17/1 | DA+3 | Bhiyad | 393.7 | DRY | E
106 | 17/2 | DA+6 | Bhiyad | 415.9 | DRY | E
107 | 17/3 | DA+0 | Bhiyad | 422.8 | DRY | E
108 | 17/4 | DA+3 | Bhiyad | 409.9 | DRY | ROW
109 | 17/5 | DA+3 | Bhiyad | 425.3 | DRY | E
110 | 18/0 | DC2+0 | Bhiyad | 383.4 | DRY | ROW
111 | 18/1 | DA+0 | Bhiyad | 372.8 | DRY | E
112 | 18/2 | DA+0 | Bhiyad | 379.8 | DRY | E
113 | 18/3 | DA+0 | Bhiyad | 371 | DRY | ROW
114 | 18/4 | DA+0 | Bhiyad | 398.7 | DRY | E
115 | 19/0 | DC2+0 | Bhiyad | 380.8 | DRY | E
116 | 19/1 | DA+0 | Bhiyad | 366.9 | DRY | ROW
117 | 19/2 | DA+0 | Kashmir | 372.5 | DRY | ROW
118 | 19/3 | DA+0 | Kashmir | 376.5 | DRY
119 | 19/4 | DA+0 | Kashmir | 384.3 | ROW
120 | 19/5 | DA+0 | Kashmir | 375.4 | WIP
121 | 20/0 | DB2+0 | Kashmir | 381.2 | ROW
122 | 20/1 | DA+0 | Kashmir | 386.782 | ROW
123 | 20/2 | DA+0 | Kashmir | 387.041 | ROW
124 | 20/3 | DA+0 | Kashmir | 348.466 | ROW
125 | 21/0 | DB2+0 | Kashmir | 354.965 | ROW
126 | 21/1 | DA+6 | Kashmir | 414.9 | ROW
127 | 21/2 | DA+0 | Kashmir | 407.2 | ROW
128 | 21/3 | DA+6 | Kashmir | 432.2 | ROW
129 | 21/4 | DA+3 | Kashmir | 401.9 | ROW
130 | 21/5 | DA+6 | Kashmir | 434.2 | WIP |  |  | Reattempted on 07.05.25
131 | 21/6 | DA+3 | Kashmir | 405.5 | ROW
132 | 21/7 | DA+3 | Kashmir | 426 | WIP
133 | 21/8 | DA+6 | Kashmir | 406.9 | ROW
134 | 21/9 | DA+3 | Kashmir | 433.3 | DFR
135 | 21/10 | DA+6 | Kashmir | 372.9 | DRY
136 | 22/0 | DB2+3 | Kashmir | 443.5 | ROW
137 | 22/1 | DA+9 | Kashmir | 456.4 | Sandy
138 | 22/2 | DA+6 | Kashmir | 379.2 | Sandy
139 | 22/3 | DA+9 | Kashmir | 382.6 | Sandy
140 | 22/4 | DA+9 | Kashmir | 435.6 | Sandy
141 | 22/5 | DA+9 | Kashmir | 402.1 | DRY
142 | 22/6 | DA+0 | Kashmir | 417.3 | Sandy
143 | 22/7 | DA+0 | Kashmir | 347.7 | Sandy
144 | 22/8 | DB1+0 | Kashmir | 356.3 | Sandy
145 | 22/9 | DA+6 | Kashmir | 389.2 | Sandy
146 | 22/10 | DA+6 | Rateu | 343.8 | ROW
147 | 22/11 | DA+6 | Rateu | 395.5 | Sandy
148 | 22/12 | DA+3 | Rateu | 408 | Sandy
149 | 22/13 | DA+6 | Rateu | 318 | Sandy
150 | 23/0 | DD45+3 | Rateu | 447.3 | Clear
151 | 24/0 | DD45+3 | Rateu | 222.2 | ROW
152 | 25/0 | DC1+6 | Rateu | 433.9 | DRY
153 | 25/1 | DA+3 | Rateu | 422.3 | DRY
154 | 25/2 | DA+0 | Rateu | 370.7 | DRY
155 | 25/3 | DA+0 | Rateu | 345.7 | Sandy
156 | 25/4 | DA+0 | Rateu | 391.1 | Sandy
157 | 26/0 | DB1+0 | Rateu | 440.4 | ROW
158 | 26/1 | DA+0 | Rateu | 391.4 | ROW
159 | 26/2 | DA+3 | Rateu | 406.5 | DFR
160 | 26/3 | DA+0 | Rateu | 418 | DRY
161 | 26/4 | DA+6 | Rateu | 422.6 | Sandy
162 | 26/5 | DA+6 | Rateu | 410 | Sandy
163 | 26/6 | DA+6 | Rateu | 363.4 | Sandy
164 | 26/7 | DA+0 | Rateu | 421.9 | DFR
165 | 26/8 | DA+6 | Rateu | 416.7 | Clear
166 | 27/0 | DC1+0 | Rateu | 413.8 | WIP
167 | 27/1 | DA+3 | Rateu | 399.8 | WIP
168 | 27/2 | DA+3 | Rateu | 425.2 | DFR
169 | 27/3 | DA+3 | Rateu | 398.6 | DFR
170 | 27/4 | DA+3 | Rateu | 430.7 | DFR
171 | 27/5 | DA+0 | Rateu | 410 | DRY
172 | 27/6 | DA+0 | Rateu | 402.6 | Sandy
173 | 27/7 | DB1+0 | Rateu | 343.5 | DFR
174 | 27/8 | DA+0 | Rateu | 392 | DFR
175 | 27/9 | DA+0 | Rateu | 381.1 | DFR
176 | 27/10 | DA+3 | Rateu | 366.3 | DFR
177 | 27/11 | DA+3 | Rateu | 420.1 | DRY
178 | 27/12 | DA+3 | Rateu | 420.8 | Sandy
179 | 28/0 | DB2+0 | Rateu | 406.6 | DFR
180 | 28/1 | DA+0 | Rateu | 379.6 | ROW
181 | 28/2 | DA+0 | Sawau Moolraj | 385 | DFR
182 | 28/3 | DA+0 | Sawau Moolraj | 369 | DFR
183 | 28/4 | DA+0 | Sawau Moolraj | 409 | Sandy
184 | 28/5 | DA+9 | Sawau Moolraj | 422 | Sandy
185 | 28/6 | DA+6 | Sawau Moolraj | 370 | Sandy
186 | 28/7 | DA+3 | Sawau Moolraj | 464 | Sandy
187 | 28/8 | DA+3 | Sawau Moolraj | 375 | Sandy
188 | 29/0 | DB1+0 | Sawau Moolraj | 465.5 | DRY
189 | 29/1 | DA+3 | Sawau Moolraj | 365.6 | DRY
190 | 29/2 | DA+3 | Sawau Moolraj | 424 | DRY
191 | 29/3 | DA+0 | Sawau Moolraj | 399 | Sandy
192 | 29/4 | DA+6 | Sawau Moolraj | 440 | DRY
193 | 30/0 | DC1+0 | Sawau Moolraj | 382.1 | DRY
194 | 30/1 | DA+0 | Sawau Moolraj | 388.9 | Sandy
195 | 30/2 | DA+0 | Sawau Moolraj | 445 | Sandy
196 | 30/3 | DA+3 | Sawau Moolraj | 395 | Sandy
197 | 30/4 | DA+3 | Sawau Moolraj | 387 | DRY
198 | 30/5 | DA+3 | Sawau Moolraj | 442 | WIP
199 | 30/6 | DA+0 | Sawau Moolraj | 314 | ROW
200 | 31/0 | DB2+0 | Sawau Moolraj | 347.4 | ROW
201 | 31/1 | DA+0 | Sawau Moolraj | 383.6 | DRY
202 | 31/2 | DA+0 | Sawau Moolraj | 366 | DRY
203 | 32/0 | DC1+0 | Sawau Moolraj | 332.9 | DRY
204 | 32/1 | DA+3 | Neemba Ki Dhani | 402.7 | Sandy
205 | 32/2 | DA+3 | Neemba Ki Dhani | 428.8 | DRY
206 | 32/3 | DA+0 | Neemba Ki Dhani | 410.9 | Sandy
207 | 32/4 | DA+0 | Neemba Ki Dhani | 381.1 | Sandy
208 | 33/0 | DC1+0 | Neemba Ki Dhani | 451.5 | DRY
209 | 33/1 | DA+0 | Neemba Ki Dhani | 379.6 | DRY
210 | 34/0 | DB2+0 | Neemba Ki Dhani | 292.5 | DRY
211 | 34/1 | DA+9 | Neemba Ki Dhani | 432.6 | Sandy
212 | 34/2 | DA+6 | Neemba Ki Dhani | 407.5 | Sandy
213 | 34/3 | DA+0 | Neemba Ki Dhani | 377 | Sandy
214 | 34/4 | DA+0 | Neemba Ki Dhani | 451.6 | Sandy
215 | 35/0 | DB2+6 | Neemba Ki Dhani | 379.3 | Sandy
216 | 35/1 | DA+9 | Neemba Ki Dhani | 265.6 | Sandy
217 | 35/2 | DB1+0 | Neemba Ki Dhani | 492.4 | Sandy
218 | 35/3 | DB1+6 | Neemba Ki Dhani | 522.2 | Sandy
219 | 35/4 | DA+0 | Neemba Ki Dhani | 418.9 | DRY
220 | 35/5 | DA+0 | Neemba Ki Dhani | 421.7 | Sandy
221 | 36/0 | DB2+0 | Neemba Ki Dhani | 342.7 | Sandy
222 | 36/1 | DA+0 | Neemba Ki Dhani | 386.4 | Sandy
223 | 36/2 | DA+0 | Neemba Ki Dhani | 309.4 | Clear
224 | 36/3 | DA+0 | Neemba Ki Dhani | 357.8 | Clear
225 | 36/4 | DA+6 | Neemba Ki Dhani | 480.4 | Clear
226 | 37/0 | DB2+0 | Neemba Ki Dhani | 350.5 | Clear
227 | 37/1 | DA+9 | Danpura | 443.3 | ROW
228 | 37/2 | DA+3 | Danpura | 356.7 | Clear
229 | 37/3 | DA+0 | Danpura | 339.9 | Sandy
230 | 38/0 | DB2+6 | Danpura | 500.3 | Sandy
231 | 38/1 | DA+0 | Danpura | 421.4 | Sandy
232 | 38/2 | DA+6 | Danpura | 419 | Sandy
233 | 38/3 | DA+9 | Danpura | 420.3 | Sandy
234 | 38/4 | DA+9 | Danpura | 414.9 | Sandy
235 | 39/0 | DB2+6 | Danpura | 425.5 | Sandy
236 | 39/1 | DA+0 | Danpura | 412.6 | Sandy
237 | 40/0 | DC2+0 | Danpura | 322.6 | Sandy
238 | 40/1 | DA+6 | Danpura | 396.2 | Sandy
239 | 40/2 | DA+3 | Danpura | 425.8 | Sandy
240 | 40/3 | DA+3 | Rampura Kharda | 401.7 | Sandy
241 | 41/0 | DC1+6 | Manpura Kharda | 436.3 | WIP
242 | 41/1 | DB1+9 | Manpura Kharda | 340.8 | Sandy
243 | 41/2 | DA+0 | Kharda Charnan | 447.8 | Sandy
244 | 42/0 | DC1+0 | Kharda Charnan | 382.3 | Sandy
245 | 42/1 | DA+6 | Kharda Charnan | 384.7 | Sandy
246 | 42/2 | DA+6 | Kharda Charnan | 407.4 | Sandy
247 | 42/3 | DA+0 | Kharda Charnan | 414.2 | Sandy
248 | 42/4 | DA+0 | Kharda Charnan | 256.4 | Sandy
249 | 42/5 | DA+9 | Kharda Charnan | 403.8 | Sandy
250 | 42/6 | DA+0 | Kharda Charnan | 396.7 | Sandy
251 | 43/0 | DB1+0 | Kharda Charnan | 403.9 | Sandy | E
252 | 43/1 | DA+3 | Beniwalon Ki Dhani | 346 | Sandy | E
253 | 43/2 | DA+0 | Beniwalon Ki Dhani | 475.8 | Sandy
254 | 43/3 | DA+0 | Beniwalon Ki Dhani | 363.7 | DRY
255 | 43/4 | DA+3 | Beniwalon Ki Dhani | 431.8 | Sandy
256 | 43/5 | DA+3 | Beniwalon Ki Dhani | 405.3 | DRY
257 | 43/6 | DA+3 | Beniwalon Ki Dhani | 427.8 | Sandy | E
258 | 43/7 | DA+3 | Pareu | 389.8 | Sandy | E
259 | 43/8 | DA+9 | Pareu | 449.5 | Sandy | E
260 | 43/9 | DA+9 | Pareu | 388 | Sandy | E
261 | 43/10 | DA+3 | Pareu | 346.3 | Sandy
262 | 43/11 | DA+3 | Mahadeo Ka Mandir | 444.8 | Sandy
263 | 44/0 | DB1+3 | Mahadeo Ka Mandir | 384.3 | Sandy
264 | 44/1 | DA+0 | Mahadeo Ka Mandir | 384.3 | Sandy
265 | 44/2 | DA+0 | Mahadeo Ka Mandir | 359 | Sandy
266 | 44/3 | DA+0 | Mahadeo Ka Mandir | 334 | Sandy
267 | 44/4 | DA+9 | Mahadeo Ka Mandir | 395 | Sandy
268 | 44/5 | DA+9 | Mahadeo Ka Mandir | 355 | Sandy
269 | 44/6 | DB1+3 | Chimoniyon Ki Dhani | 485 | Sandy
270 | 44/7 | DA+9 | Chimoniyon Ki Dhani | 473 | Sandy
271 | 44/8 | DCT+0 | Chimoniyon Ki Dhani | 367 | Sandy
272 | 44/9 | DA+9 | Chimoniyon Ki Dhani | 430 | Sandy
273 | 44/10 | DB1+9 | Chimoniyon Ki Dhani | 365 | Sandy
274 | 44/11 | DA+0 | Chimoniyon Ki Dhani | 428 | Sandy
275 | 45/0 | DC2+0 | Chimoniyon Ki Dhani | 327.2 | Sandy
276 | 45/1 | DA+9 | Chimoniyon Ki Dhani | 294.92 | Sandy
277 | 46/0 | DD60+25 | Godaron Ki Dhani | 406.54 | Sandy
278 | 47/0 | DD60+25 | Godaron Ki Dhani | 199.08 | Sandy
279 | 47/1 | DA+3 | Godaron Ki Dhani | 441.2 | Sandy
280 | 47/2 | DA+9 | Godaron Ki Dhani | 365.93 | Sandy
281 | 47/3 | DA+9 | Godaron Ki Dhani | 417.4 | Sandy
282 | 47/4 | DA+3 | Godaron Ki Dhani | 358.4 | Sandy
283 | 47/5 | DA+0 | Godaron Ki Dhani | 461.2 | Sandy
284 | 47/6 | DA+3 | Godaron Ki Dhani | 377.3 | Sandy
285 | 47/7 | DA+3 | Godaron Ki Dhani | 431.5 | Sandy
286 | 47/8 | DA+0 | Daukiyon Ki Dhani | 398.8 | Sandy | E
287 | 47/9 | DA+3 | Daukiyon Ki Dhani | 405.9 | Sandy | E
288 | 47/10 | DA+6 | Daukiyon Ki Dhani | 433.7 | Sandy | E
289 | 48/0 | DC2+0 | Daukiyon Ki Dhani | 386.2 | Sandy | E
290 | 48/1 | DA+9 | Nehru Nagar | 428.9 | Sandy | E
291 | 49/0 | DD45+0 | Nehru Nagar | 402.9 | Sandy | E
292 | 49/1 | DA+0 | Nehru Nagar | 379.1 | Sandy | E
293 | 49/2 | DA+3 | Nehru Nagar | 386.6 | Sandy | E
294 | 49/3 | DA+3 | Nehru Nagar | 390 | Sandy | E
295 | 49/4 | DA+3 | Nehru Nagar | 421.7 | Sandy | E
296 | 49/5 | DA+3 | Nematpura | 396.6 | Sandy | E
297 | 49/6 | DA+0 | Nematpura | 412.8 | Sandy | E
298 | 49/7 | DA+0 | Nematpura | 340.2 | Sandy | E
299 | 50/0 | DB2+0 | Nematpura | 500.2 | Sandy | E | C
300 | 50/1 | DA+6 | Nematpura | 469.1 | Sandy | E | C
301 | 50/2 | DA+9 | Nematpura | 367.1 | Sandy | E | C
302 | 50/3 | DA+6 | Nematpura | 470.4 | Sandy | E | C
303 | 50/4 | DA+9 | Gangapura | 354.8 | Sandy | E | C
304 | 50/5 | DA+9 | Gangapura | 442.1 | Sandy | E | C
305 | 50/6 | DA+9 | Gangapura | 364.4 | Sandy | E | C
306 | 50/7 | DA+0 | Gangapura | 470.8 | Sandy | E | C
307 | 50/8 | DA+9 | Barnama Charnan | 345 | Sandy | E | C
308 | 50/9 | DA+0 | Barnama Charnan | 364.4 | Sandy | E | C
309 | 50/10 | DA+0 | Barnama Charnan | 394.6 | Sandy | E | C
310 | 51/0 | DC2+0 | Barnama Charnan | 401.4 | Sandy | E | C
311 | 51/1 | DA+0 | Barnama Charnan | 356.6 | Sandy | E | C
312 | 51/2 | DA+0 | Barnama Charnan | 307.1 | Sandy | E | C
313 | 52/0 | DC2+0 | Barnama Charnan | 385 | Sandy | E | C
314 | 52/1 | DA+6 | Khanora | 402 | Sandy
315 | 52/2 | DA+6 | Khanora | 402.6 | Sandy
316 | 52/3 | DA+9 | Khanora | 437 | Sandy
317 | 52/4 | DA+9 | Khanora | 393.8 | Sandy
318 | 52/5 | DA+9 | Khanora | 447 | Sandy | E
319 | 52/6 | DA+6 | Khanora | 373 | Sandy | E
320 | 52/7 | DA+3 | Khanora | 406.8 | Sandy | E
321 | 52/8 | DA+6 | Khanora | 433 | Sandy | E
322 | 52/9 | DA+3 | Khanora | 399.7 | Sandy | E
323 | 52/10 | DA+9 | Khanora | 384.1 | Sandy | E
324 | 53/0 | DB2+9 | Khanora | 455.9 | Sandy | E
325 | 53/1 | DA+9 | Khanora | 433.2 | Sandy | E
326 | 53/2 | DA+0 | Khanora | 407.4 | Sandy | E
327 | 53/3 | DA+6 | Sathuni Purohitan | 394.5 | Sandy | E
328 | 53/4 | DA+0 | Sathuni Purohitan | 410.1 | Sandy | E
329 | 53/5 | DA+3 | Sathuni Purohitan | 428.1 | Sandy | E
330 | 53/6 | DA+6 | Sathuni Charnan | 406.6 | Sandy | E
331 | 53/7 | DA+3 | Sathuni Charnan | 411.3 | Sandy | E
332 | 53/8 | DA+3 | Sathuni Charnan | 427.8 | Sandy | E
333 | 54/0 | DB1+6 | Sathuni Charnan | 371.3 | Sandy
334 | 54/1 | DA+3 | Sathuni Charnan | 365.1 | Sandy
335 | 54/2 | DA+3 | Sathuni Charnan | 381 | Sandy
336 | 54/3 | DA+6 | Sathuni Charnan | 417 | Sandy
337 | 54/4 | DA+9 | Sathuni Charnan | 423.3 | Sandy
338 | 54/5 | DA+9 | Simarkhiya | 401 | Sandy
339 | 55/0 | DB1+6 | Simarkhiya | 424 | Sandy
340 | 55/1 | DA+0 | Simarkhiya | 404.9 | WFR
341 | 55/2 | DA+0 | Bagawas | 343.1 | WFR
342 | 55/3 | DA+0 | Bagawas | 357.7 | Sandy | E
343 | 55/4 | DA+0 | Bagawas | 365.2 | Sandy | E
344 | 55/5 | DA+0 | Bagawas | 350.1 | Sandy | E
345 | 55/6 | DA+0 | Bagawas | 357.7 | Sandy | E
346 | 55/7 | DA+0 | Bagawas | 337.8 | Sandy
347 | 55/8 | DA+6 | Bagawas | 341.22 | Sandy
348 | 56/0 | DD60+25 | Bagawas | 460.49 | Sandy
349 | 57/0 | DD60+25 | Bagawas | 219.76 | Sandy
350 | 57/1 | DA+0 | Bagawas | 461.11 | Sandy
351 | 57/2 | DA+3 | Mohanpura | 355.5 | DRY
352 | 57/3 | DA+0 | Mohanpura | 405.4 | DRY | E
353 | 57/4 | DA+0 | Mohanpura | 418.2 | Sandy | E
354 | 57/5 | DA+3 | Bagawas | 416.8 | Sandy | E
355 | 57/6 | DA+3 | Mohanpura | 395 | Sandy | E
356 | 57/7 | DA+3 | Meghawas | 401.8 | DFR | E
357 | 58/0 | DC1+3 | Meghawas | 433.9 | DFR | E | C
358 | 59/0 | DC2+0 | Meghawas | 238.897 | DRY | E | C
359 | 59/1 | DA+3 | Meghawas | 411.3 | DRY | E | C
360 | 59/2 | DA+3 | Meghawas | 418.204 | DFR | E | C
361 | 59/3 | DA+3 | Mohanpura | 412.3 | DFR | E | C
362 | 59/4 | DA+3 | Mohanpura | 421 | DFR | E | C
363 | 59/5 | DA+3 | Sagaranari | 419.7 | DFR | E | C
364 | 59/6 | DA+3 | Sagaranari | 419.1 | DFR | E | C
365 | 59/7 | DA+3 | Sagaranari | 408.8 | DRY | E | C
366 | 59/8 | DB1+3 | Sagaranari | 426.9 | DRY | E | C
367 | 59/9 | DA+3 | Sagaranari | 434.7 | DRY | E | C
368 | 59/10 | DA+0 | Sagaranari | 400.8 | DRY | E | C
369 | 59/11 | DA+6 | Sagaranari | 436.3 | DFR | E | C
370 | 59/12 | DA+6 | Sagaranari | 393.1 | DFR | E | C
371 | 59/13 | DA+3 | Sagaranari | 447.4 | DRY | E | C
372 | 59/14 | DA+6 | Sagaranari | 391.1 | DRY | E | C
373 | 59/15 | DA+6 | Nagana | 448.6 | DRY | E | C
374 | 59/16 | DA+9 | Nagana | 388 | Dry | E | C
375 | 60/0 | DC1+0 | Nagana | 438 | DRY | E | C
376 | 60/1 | DA+6 | Nagana | 413.8 | DRY | E | C
377 | 60/2 | DA+3 | Nagana | 424.2 | DFR | E | C
378 | 60/3 | DA+3 | Nagana | 414.5 | DFR | E | C
379 | 60/4 | DA+3 | Deoriya | 425.6 | DFR | E | C
380 | 60/5 | DA+3 | Deoriya | 412.3 | DRY | E | C
381 | 60/6 | DA+0 | Deoriya | 374.1 | DRY | E | C
382 | 60/7 | DA+3 | Deoriya | 410.1 | DRY | E | C
383 | 60/8 | DA+0 | Deoriya | 400.4 | DRY | E | C
384 | 60/9 | DA+3 | Deoriya | 409.2 | DRY | E | C
385 | 60/10 | DA+0 | Deoriya | 401 | DFR | E | C
386 | 60/11 | DA+3 | Deoriya | 394.5 | DRY | E | C
387 | 61/0 | DB2+0 | Deoriya | 397.9 | DRY | E | C
388 | 61/1 | DA+6 | Bakati | 405.7 | DFR | E | C
389 | 61/2 | DA+6 | Bakati | 433.2 | DFR | E | C
390 | 61/3 | DA+6 | Bakati | 400.9 | DRY | E | C
391 | 61/4 | DA+3 | Bakati | 427 | DRY | E | C
392 | 61/5 | DA+3 | Bakati | 413.9 | DRY | E | C
393 | 61/6 | DA+3 | Bakati | 426.4 | DRY | E | C
394 | 61/7 | DA+9 | Bakati | 411.5 | Dry | E | C
395 | 61/8 | DA+6 | Bakati | 376.3 | DRY | E | C
396 | 61/9 | DA+0 | Bakati | 433.4 | Dry | E | C
397 | 61/10 | DA+9 | Gwalnada | 405.6 | DRY | E | C
398 | 62/0 | DB2+0 | Gwalnada | 434.3 | DRY | E | C
399 | 62/1 | DA+3 | Gwalnada | 418 | Sandy | E | C
400 | 62/2 | DA+3 | Gwalnada | 386 | DRY | E | C
401 | 62/3 | DA+0 | Gwalnada | 400 | DRY | E | C
402 | 62/4 | DA+3 | Gwalnada | 401 | DRY | E | C
403 | 62/5 | DA+0 | Gwalnada | 403 | DRY | E | C
404 | 62/6 | DA+3 | Gwalnada | 404 | DRY | E | C
405 | 62/7 | DA+3 | Gwalnada | 423 | DRY | E | C
406 | 62/8 | DA+0 | Godawas Kalan | 409 | DFR | E | C
407 | 62/9 | DA+3 | Godawas Kalan | 409 | DFR | E | C
408 | 62/10 | DA+0 | Godawas Kalan | 411 | DFR | E | C
409 | 62/11 | DA+3 | Godawas Kalan | 413 | DRY | E | C
410 | 63/0 | DC1+0 | Doli Kalan | 386.1 | DFR | E | C
411 | 63/1 | DA+3 | Godawas Kalan | 400 | DFR | E | C
412 | 63/2 | DA+0 | Godawas Kalan | 416 | DFR | E | C
413 | 63/3 | DA+3 | Godawas Kalan | 411 | DFR | E | C
414 | 63/4 | DA+0 | Godawas Kalan | 399 | DRY | E | C
415 | 63/5 | DA+3 | Godawas Kalan | 413 | DFR | E | C
416 | 63/6 | DA+3 | Modathali | 426 | DRY | E | C
417 | 63/7 | DA+3 | Modathali | 413 | DRY | E | C
418 | 63/8 | DA+3 | Modathali | 425 | DRY | E | C
419 | 64/0 | DB2+0 | Modathali | 408.3 | DRY | E | C
420 | 64/1 | DA+0 | Modathali | 375.1 | DRY | E | C
421 | 64/2 | DA+3 | Piprali | 408.7 | DRY | E | C
422 | 64/3 | DA+0 | Piprali | 410.7 | DRY | E | C
423 | 64/4 | DA+3 | Piprali | 408.2 | DRY | E | C
424 | 64/5 | DA+3 | Rabariyawas | 426.2 | DRY | E | C
425 | 64/6 | DA+0 | Rabariyawas | 407.7 | DRY | E | C
426 | 64/7 | DA+3 | Rabariyawas | 401.6 | DRY | E | C
427 | 64/8 | DA+3 | Rabariyawas | 425.5 | DRY | E | C
428 | 64/9 | DA+3 | Rabariyawas | 414.4 | DRY | E | C
429 | 64/10 | DA+3 | Rabariyawas | 410.6 | DRY | E | C
430 | 64/11 | DA+3 | Rabariyawas | 428.4 | DRY | E | C
431 | 65/0 | DB1+0 | Rabariyawas | 400.6 | DRY | E | C
432 | 65/1 | DA+0 | Rabariyawas | 395.4 | DRY | E | C
433 | 65/2 | DA+0 | Rabariyawas | 393.7 | DRY | E | C
434 | 65/3 | DA+3 | Rabariyawas | 403.7 | DRY | E | C
435 | 65/4 | DA+0 | Loonawas Charna | 402.9 | DRY | E | C
436 | 65/5 | DA+0 | Loonawas Charna | 376.4 | DRY | E | C
437 | 65/6 | DA+0 | Loonawas Charna | 389.2 | DRY | E | C
438 | 65/7 | DA+0 | Loonawas Charna | 397.6 | DRY | E | C
439 | 65/8 | DA+0 | Loonawas Khurd | 394.3 | DRY | E | C
440 | 65/9 | DA+0 | Loonawas Khurd | 389 | DRY | E | C
441 | 65/10 | DA+0 | Loonawas Khurd | 379.1 | DRY | E | C
442 | 65/11 | DA+0 | Loonawas Khurd | 387.6 | DRY | E | C
443 | 66/0 | DC2+6 | Loonawas Khurd | 426.9 | DRY | E | C
444 | 67/0 | DC1+9 | Loonawas Khurd | 207.8 | DRY | E
445 | 67/1 | DA+0 | Loonawas Khurd | 347.1 | DRY | E
446 | 67/2 | DA+0 | Loonawas Khurd | 344.9 | DRY | E
447 | 68/0 | DD45+0 | Loonawas Khurd | 369.2 | DRY | E
448 | 69/0 | DB2+0 | Loonawas Khurd | 200.9 | DFR
449 | 69/1 | DA+3 | Borapadakhamar | 374.1 | DRY
450 | 70/0 | DC1+0 | Borapadakhamar | 394.9 | DRY
451 | 70/1 | DA+3 | Loonawas Khurd | 388.4 | DRY
452 | 70/2 | DA+3 | Loonawas Khurd | 418.9 | DRY
453 | 70/3 | DA+3 | Katarda | 418.6 | DRY | E
454 | 70/4 | DA+3 | Katarda | 414 | DRY | E
455 | 70/5 | DA+3 | Katarda | 419.6 | DRY | E
456 | 70/6 | DA+3 | Katarda | 420.3 | DRY | WIP
457 | 70/7 | DA+3 | Katarda | 419.6 | DRY
458 | 70/8 | DA+3 | Katarda | 418.2 | DRY
459 | 70/9 | DA+3 | Karni Nagar | 414.1 | DRY | E
460 | 70/10 | DA+3 | Karni Nagar | 406.1 | DRY | E
461 | 70/11 | DA+3 | Katarda | 408.6 | DRY | E
462 | 71/0 | DB2+3 | Katarda | 420.4 | DRY | E
463 | 71/1 | DA+3 | Katarda | 398.6 | DRY | E
464 | 71/2 | DA+3 | Katarda | 414.3 | DRY | E
465 | 71/3 | DA+6 | Katarda | 413 | DRY | E
466 | 71/4 | DA+3 | Katarda | 367.7 | DRY | E
467 | 71/5 | DA+3 | Basni Jhoonthan | 429.4 | DRY | E
468 | 71/6 | DA+0 | Basni Jhoonthan | 408 | DRY | E
469 | 71/7 | DA+3 | Basni Jhoonthan | 404.9 | DRY | E
470 | 71/8 | DA+3 | Basni Jhoonthan | 431.6 | DRY | E
471 | 72/0 | DB2+3 | Basni Jhoonthan | 408.4 | DRY | E
472 | 72/1 | DA+3 | Basni Jhoonthan | 435.3 | DRY | E | ROW
473 | 72/2 | DA+0 | Basni Jhoonthan | 403.9 | DRY | E
474 | 72/3 | DA+3 | Basni Jhoonthan | 389.2 | DRY | E
475 | 73/0 | DB2+0 | Basni Jhoonthan | 400.1 | DRY | E
476 | 73/1 | DA+0 | Sardargarh | 383.3 | DRY | E
477 | 73/2 | DA+0 | Sardargarh | 379 | DRY | E
478 | 73/3 | DA+0 | Sardargarh | 381.2 | DRY | E
479 | 73/4 | DA+0 | Sardargarh | 384.7 | DRY | E
480 | 73/5 | DA+0 | Sardargarh | 368.8 | DRY | E
481 | 73/6 | DA+0 | Sardargarh | 365.5 | DRY | E
482 | 73/7 | DA+0 | Sardargarh | 392.4 | DRY | E
483 | 73/8 | DA+3 | Sardargarh | 374.9 | DRY | E
484 | 73/9 | DA+0 | Sardargarh | 379.5 | DRY | E
485 | 74/0 | DB2+0 | Sardargarh | 378.9 | Sandy | E

## Survey
Progress Summary'!A1 | KEC International Limited
[6 empty] | Particulars | Section-1 | Section-2 | Remarks
[6 empty] | Hold | 0 | 0
[6 empty] | Under Submission | 0 | 0
[6 empty] | ROW | 1.4773 | 0 | AP20-AP21
[6 empty] | Approved | 101.4688 | 88.4276
[6 empty] | Under approval | 0 | 0
[6 empty] | Check survey balance | 0 | 0
[6 empty] | Re-submission | 0 | 0
[6 empty] | Total | 102.9461 | 88.4276
Survey status at TB-408
Section | Sl. No | Section |  | Section Length (in Mtrs) | Detail Survey received Date | Check Survey | [5 empty] | Total | Susp. | Tens.
|  | From | To |  |  | Status | Date of Submission | Further Modification date | Approved Date | Remarks | Remarks
1 | 1 | Gty | 1/0 | 122 | 2023-10-14 | Approved | 2024-09-20 |  | 2024-11-08 | Clearances received on 15.07.2024 |  | 1 | 0 | 1
1 | 2 | 1/0 | 1A/0 | 90 | 2023-10-14 | Approved | 2024-09-20 |  | 2024-11-08 | Clearances received on 15.07.2024 |  | 1 | 0 | 1
1 | 3 | 1/0 | 2/0 | 3438.766 | 2023-10-14 | Approved | 2024-09-20 |  | 2024-11-08 | Clearances received on 15.07.2024 |  | 9 | 8 | 1
1 | 4 | 2/0 | 3/0 | 3823.508 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 10 | 9 | 1
1 | 5 | 3/0 | 4/0 | 226.52 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 1 | 0 | 1
1 | 3 | 4/0 | 5/0 | 1873.545 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 5 | 4 | 1
1 | 7 | 5/0 | 6/0 | 246.019 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 1 | 0 | 1
1 | 8 | 6/0 | 7/0 | 1140.147 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 3 | 2 | 1
1 | 9 | 7/0 | 8/0 | 210.755 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 1 | 0 | 1
1 | 4 | 8/0 | 8/7 | 2861.372 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 7 | 6 | 1
1 | 11 | 8/7 | 9/0 | 2456.044 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 6 | 5 | 1
1 | 12 | 9/0 | 10/0 | 233.076 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 1 | 0 | 1
1 | 13 | 10/0 | 10/12 | 4894.437 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 12 | 11 | 1
1 | 5 | 10/12 | 11/0 | 4844.45 | 2023-10-14 | Approved | 2024-02-22 |  | 2024-05-20 | ROW Cleared on 16/01/23. approved on 20.05.2024 having subject Optimization from GTY to AP74 (Part- F) |  | 12 | 11 | 1
1 | 15 | 11/0 | 11A/0 | 2339.993 | 2023-10-14 | Approved | 2024-02-22 |  | 2024-05-20 | Location no 11/5, 11A/0 are on Hold due to ROW during check survey, Centre peg not done for verification of benching and others. approved on 20.05.2024 having subject Optimization from GTY to AP74 (Part- F) |  | 6 | 5 | 1
1 | 16 | 11A/0 | 12/0 | 4110.631 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 10 | 9 | 1
1 | 17 | 12/0 | 13/0 | 211.914 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 1 | 0 | 1
1 | 6 | 13/0 | 14/0 | 2077.901 | 2023-10-14 | Approved | 2023-12-30 |  | 2024-01-25 | ROW from 26.12.2023 to 25.01.2024 |  | 5 | 4 | 1
1 | 19 | 14/0 | 14A/0 | 381.413 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 1 | 0 | 1
1 | 20 | 14A/0 | 15/0 | 1192.131 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 3 | 2 | 1
1 | 21 | 15/0 | 16/0 | 817.914 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 2 | 1 | 1
1 | 7 | 16/0 | 17/0 | 2336.157 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 6 | 5 | 1
1 | 23 | 17/0 | 18/0 | 2451.083 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 6 | 5 | 1
1 | 24 | 18/0 | 19/0 | 1903.166 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 5 | 4 | 1
1 | 25 | 19/0 | 20/0 | 2256.723 | 2023-10-14 | Approved | 2023-12-05 |  | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 6 | 5 | 1
1 | 8 | 20/0 | 21/0 | 1477.254 | 2023-10-14 | ROW | Not submitted due to ROW |  |  |  |  | 4 | 3 | 1
1 | 27 | 21/0 | 22/0 | 4578.525 | 2023-10-14 | Approved | 2023-11-21 | 2023-12-05 | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 11 | 10 | 1
1 | 28 | 22/0 | 22/8 | 3184.049 | 2023-10-14 | Approved | 2023-11-21 | 2023-12-05 | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 8 | 7 | 1
1 | 29 | 22/8 | 23/0 | 2294.809 | 2023-10-14 | Approved | 2023-11-21 | 2023-12-05 | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 6 | 5 | 1
1 | 9 | 23/0 | 24/0 | 222.155 | 2023-10-14 | Approved | 2023-11-21 | 2023-12-05 | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 1 | 0 | 1
1 | 31 | 24/0 | 25/0 | 433.889 | 2023-10-14 | Approved | 2023-11-21 | 2023-12-05 | 2023-12-14 | ROW from 06.12.2023 to 14.12.2023 |  | 1 | 0 | 1
1 | 32 | 25/0 | 26/0 | 1970.278 | 2023-10-14 | Approved | 2023-11-06 |  | 2023-11-22 |  |  | 5 | 4 | 1
1 | 33 | 26/0 | 27/0 | 3664.173 | 2023-10-14 | Approved | 2023-11-06 |  | 2023-11-22 |  |  | 9 | 8 | 1
1 | 10 | 27/0 | 27/7 | 2810.22 | 2023-10-14 | Approved | 2023-11-06 |  | 2023-11-22 |  |  | 7 | 6 | 1
1 | 35 | 27/7 | 28/0 | 2386.877 | 2023-10-14 | Approved | 2023-11-06 |  | 2023-11-22 |  |  | 6 | 5 | 1
1 | 36 | 28/0 | 29/0 | 3639.092 | 2023-10-14 | Approved | 2023-11-10 | 2023-12-07 | 2023-11-22 | Modifications due to shifting. | Benching approval awaited | 9 | 8 | 1
1 | 37 | 29/0 | 30/0 | 2010.644 | 2023-10-14 | Approved | 2023-11-10 | 2023-12-07 | 2023-11-22 | Modifications due to shifting. | Benching approval awaited | 5 | 4 | 1
1 | 11 | 30/0 | 31/0 | 2719.335 | 2023-10-14 | Approved | 2023-11-10 | 2023-12-07 | 2023-11-22 | Modifications due to shifting. | Benching approval awaited | 7 | 6 | 1
1 | 39 | 31/0 | 32/0 | 1082.475 | 2023-10-14 | Approved | 2023-11-10 | 2023-12-07 | 2023-11-22 | ROW from 21.12.2023 to 29.12.2023 | Benching approval awaited | 3 | 2 | 1
1 | 40 | 32/0 | 33/0 | 2074.99 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | ROW from 21.12.2023 to 29.12.2023 |  | 5 | 4 | 1
1 | 41 | 33/0 | 34/0 | 672.091 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | ROW from 21.12.2023 to 29.12.2023 |  | 2 | 1 | 1
1 | 12 | 34/0 | 35/0 | 2048.196 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 5 | 4 | 1
1 | 43 | 35/0 | 35/2 | 775.496 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 2 | 1 | 1
1 | 44 | 35/2 | 35/3 | 504.678 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 1 | 0 | 1
1 | 45 | 35/3 | 36/0 | 1180.197 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 3 | 2 | 1
1 | 13 | 36/0 | 37/0 | 1883.954 | 2023-10-14 | Approved | 2023-12-21 | 2024-02-25 | 29-12-2023/06/09/2024 | resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 5 | 4 | 1
1 | 47 | 37/0 | 37/3 | 1138.536 | 2023-10-14 | Approved | 2024-02-25 |  | 2024-12-11 | Resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 3 | 2 | 1
1 | 48 | 37/3 | 38/0 | 594.059 | 2023-10-14 | Approved | 2024-02-25 |  | 2024-12-11 | Resurvey to be done in AP36 to AP40. Confirmed on 20.5.24 |  | 1 | 0 | 1
1 | 49 | 38/0 | 39/0 | 2063.067 | 2023-10-14 | Approved | 2024-11-30 |  | 2024-12-11 | ROW from 06.12.2023 to 10.10.2024 |  | 5 | 4 | 1
1 | 14 | 39/0 | 40/0 | 684.371 | 2023-10-14 | Approved | 2024-11-30 |  | 2024-12-11 | ROW from 06.12.2023 to 10.10.2024 |  | 2 | 1 | 1
1 | 51 | 40/0 | 40/3 | 1183.8 |  | Approved | 2024-06-23 |  | 2024-07-03 | ROW Since 27/1/24 |  | 3 | 2 | 1
1 | 52 | 40/3 | 41/0 | 478.3 |  | Approved | 2024-06-23 |  | 2024-07-03 | ROW Since 27/1/24 |  | 1 | 0 | 1
1 | 53 | 41/0 | 41/1 | 312.3 |  | Approved | 2024-06-23 |  | 2024-07-03 | ROW Since 27/1/24 |  | 1 | 0 | 1
1 | 15 | 41/1 | 42/0 | 818.5 |  | Approved | 2024-06-23 |  | 2024-07-03 | ROW Since 27/1/24 |  | 2 | 1 | 1
1 | 55 | 42/0 | 43/0 | 2607.2 |  | Approved | 2024-06-23 |  | 2024-07-03 | ROW Since 27/1/24 |  | 7 | 6 | 1
1 | 56 | 43/0 | 44/0 | 4912.9 |  | Approved | 2024-06-23 |  | 2024-07-03 |  |  | 12 | 11 | 1
2 | 57 | 44/0 | 44/3 | 1258.6 |  | Approved | 2024-07-06 |  | 2024-07-24 |  |  | 3 | 2 | 1
2 | 16 | 44/3 | 44/8 | 1995.5 |  | Approved | 2024-07-06 |  | 2024-07-24 |  |  | 5 | 4 | 1
2 | 59 | 44/8 | 45/0 | 1448.6 |  | Approved | 2024-07-06 |  | 2024-07-24 |  |  | 4 | 3 | 1
2 | 60 | 45/0 | 46/0 | 701.4 |  | Approved | 2024-07-06 |  | 2024-07-24 |  |  | 2 | 1 | 1
2 | 61 | 46/0 | 47/0 | 197.7 |  | Approved | 2024-07-06 |  | 2024-07-24 |  |  | 1 | 0 | 1
2 | 17 | 47/0 | 48/0 | 4479.5 |  | Approved | 2024-02-06 |  | 2024-02-29 |  |  | 11 | 10 | 1
2 | 63 | 48/0 | 49/0 | 809.9 |  | Approved | 2024-02-06 |  | 2024-02-29 |  |  | 2 | 1 | 1
2 | 64 | 49/0 | 50/0 | 3248.6 |  | Approved | 2024-02-06 |  | 2024-02-29 |  |  | 8 | 7 | 1
2 | 65 | 50/0 | 51/0 | 4444.1 |  | Approved | 2024-02-06 |  | 2024-02-29 |  |  | 11 | 10 | 1
2 | 18 | 51/0 | 52/0 | 1048.7 |  | Approved | 2024-02-06 |  | 2024-02-29 |  |  | 3 | 2 | 1
2 | 67 | 52/0 | 53/0 | 4534.9 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 11 | 10 | 1
2 | 68 | 53/0 | 54/0 | 3690.3 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 9 | 8 | 1
2 | 69 | 54/0 | 55/0 | 2411.4 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 6 | 5 | 1
2 | 19 | 55/0 | 56/0 | 3338.2 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 9 | 8 | 1
2 | 71 | 56/0 | 57/0 | 179.9 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 1 | 0 | 1
2 | 72 | 57/0 | 58/0 | 3307.7 |  | Approved | 2023-12-30 |  | 2024-01-09 |  |  | 8 | 7 | 1
2 | 73 | 58/0 | 59/0 | 238.9 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 1 | 0 | 1
2 | 20 | 59/0 | 59/8 | 3337.3 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 8 | 7 | 1
2 | 75 | 59/8 | 60/0 | 3778 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 9 | 8 | 1
2 | 76 | 60/0 | 61/0 | 4877.6 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 12 | 11 | 1
2 | 77 | 61/0 | 62/0 | 4568.1 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 11 | 10 | 1
2 | 21 | 62/0 | 63/0 | 4866.9 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 12 | 11 | 1
2 | 79 | 63/0 | 64/0 | 3664 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 9 | 8 | 1
2 | 80 | 64/0 | 65/0 | 4967.6 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 12 | 11 | 1
2 | 81 | 65/0 | 66/0 | 4735.8 |  | Approved | 2023-12-17 |  | 2023-12-22 |  |  | 12 | 11 | 1
2 | 22 | 66/0 | 67/0 | 207.8 |  | Approved | 2024-01-24 |  | 2024-01-31 |  |  | 1 | 0 | 1
2 | 83 | 67/0 | 68/0 | 1061.2 |  | Approved | 2024-01-24 |  | 2024-01-31 |  |  | 3 | 2 | 1
2 | 84 | 68/0 | 69/0 | 200.9 |  | Approved | 2024-01-24 |  | 2024-01-31 |  |  | 1 | 0 | 1
2 | 85 | 69/0 | 70/0 | 769 |  | Approved | 2024-01-24 |  | 2024-01-31 |  |  | 2 | 1 | 1
2 | 23 | 70/0 | 71/0 | 4966.8 |  | Approved | 2024-12-02 |  | 2024-12-10 | ROW Since 20/1/24. |  | 12 | 11 | 1
2 | 87 | 71/0 | 72/0 | 3676 |  | Approved | 2024-02-22 |  | 2024-05-20 |  |  | 9 | 8 | 1
2 | 88 | 72/0 | 73/0 | 1628.5 |  | Approved | 2024-02-22 |  | 2024-05-20 |  |  | 4 | 3 | 1
2 | 89 | 73/0 | 74/0 | 3788.2 |  | Approved | 2024-08-20 |  | 2024-08-27 | Approved. |  | 10 | 9 | 1
| Total (Part-1 & Part-2) |  |  | 191373.675 | [7 empty] | 485 | 396 | 89

## Foundation
Progress Summary'!A1
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line
List of Completed Foundations
Sr. No. | Completion Months | Loc. No. | Tower Type | Soil Classification | Date of Pit marking Till oct/ after Oct casting start date | Fdn Comp. Date | Vendor's Name | KEC Section In-Charge
1 | 2023-10-01 | 36/1 | DA+0 | Sandy | 2023-09-28 | 2023-10-04 | Nagana Ray and company | Kuntal Debnath
2 | 2023-12-01 | 61/3 | DA+6 | DRY | 2023-12-13 | 2023-12-14 | Manoj Sharma | R T Singh
3 | 2023-12-01 | 27/12 | DA+3 | Sandy | 2023-12-06 | 2023-12-18 | Nagana Ray And Company | Ajay Yadav
4 | 2023-12-01 | 62/6 | DA+3 | DRY | 2023-12-16 | 2023-12-18 | Shakti Construction | Rakesh Pathak
5 | 2023-12-01 | 59/14 | DA+6 | DRY | 2023-12-17 | 2023-12-18 | Manoj Sharma | R T Singh
6 | 2023-12-01 | 62/7 | DA+3 | DRY | 2023-12-19 | 2023-12-21 | Shakti Construction | Rakesh Pathak
7 | 2023-12-01 | 59/13 | DA+3 | DRY | 2023-12-21 | 2023-12-21 | Manoj Sharma | R T Singh
8 | 2023-12-01 | 27/10 | DA+3 | DFR | 2023-12-19 | 2023-12-24 | Nagana Ray And Company | Jeetu Sachan
9 | 2023-12-01 | 63/8 | DA+3 | DRY | 2023-12-22 | 2023-12-24 | Mahadev Eng | Rakesh Pathak
10 | 2023-12-01 | 59/10 | DA+0 | DRY | 2023-12-23 | 2023-12-24 | Manoj Sharma | R T Singh
11 | 2023-12-01 | 62/5 | DA+0 | DRY | 2023-12-22 | 2023-12-25 | Shakti Construction | Rakesh Pathak
12 | 2023-12-01 | 59/9 | DA+3 | DRY | 2023-12-25 | 2023-12-26 | Manoj Sharma | R T Singh
13 | 2023-12-01 | 60/9 | DA+3 | DRY | 2023-12-26 | 2023-12-27 | Imran | Sumit
14 | 2023-12-01 | 62/4 | DA+3 | DRY | 2023-12-26 | 2023-12-28 | Shakti Construction | Rakesh Pathak
15 | 2023-12-01 | 59/8 | DB1+3 | DRY | 2023-12-27 | 2023-12-28 | Manoj Sharma | Sumit
16 | 2023-12-01 | 26/2 | DA+3 | DFR | 2023-12-22 | 2023-12-29 | A.B. Construction | Jeetu Sachan
17 | 2023-12-01 | 59/6 | DA+3 | DFR | 2023-12-27 | 2023-12-29 | Om Const | Rakesh Pathak
18 | 2023-12-01 | 63/6 | DA+3 | DRY | 2023-12-27 | 2023-12-29 | Mahadev Eng | Rakesh Pathak
19 | 2023-12-01 | 60/8 | DA+0 | DRY | 2023-12-26 | 2023-12-29 | Imran | Sumit
20 | 2023-12-01 | 27/9 | DA+0 | DFR | 2023-12-25 | 2023-12-30 | Nagana Ray And Company | Jeetu Sachan
21 | 2023-12-01 | 59/7 | DA+3 | DRY | 2023-12-29 | 2023-12-30 | Manoj Sharma | R T Singh
22 | 2023-12-01 | 59/5 | DA+3 | DFR | 2023-12-25 | 2023-12-31 | Om Const | R T Singh
23 | 2023-12-01 | 62/3 | DA+0 | DRY | 2023-12-30 | 2023-12-31 | Shakti Construction | Rakesh Pathak
24 | 2024-01-01 | 59/12 | DA+6 | DFR | 2024-01-04 | 2024-01-05 | Manoj Sharma | R T Singh
25 | 2024-01-01 | 60/7 | DA+3 | DRY | 2024-01-01 | 2024-01-05 | Imran | R T Singh
26 | 2024-01-01 | 62/2 | DA+3 | DRY | 2024-01-02 | 2024-01-05 | Shakti Construction | Rakesh Pathak
27 | 2024-01-01 | 59/3 | DA+3 | DFR | 2024-01-03 | 2024-01-05 | Om Const | R T Singh
28 | 2024-01-01 | 64/0 | DB2+0 | DRY | 2024-01-04 | 2024-01-08 | Mahadev Eng | Rakesh Pathak
29 | 2024-01-01 | 57/3 | DA+0 | DRY | 2024-01-06 | 2024-01-08 | Om Const | R T Singh
30 | 2024-01-01 | 60/5 | DA+3 | DRY | 2024-01-08 | 2024-01-09 | Manoj Sharma | R T Singh
31 | 2024-01-01 | 62/11 | DA+3 | DRY | 2024-01-09 | 2024-01-10 | Shakti Construction | Rakesh Pathak
32 | 2024-01-01 | 65/2 | DA+0 | DRY | 2024-01-08 | 2024-01-10 | Veerteja Enterprises | Rakesh Pathak
33 | 2024-01-01 | 65/11 | DA+0 | DRY | 2024-01-09 | 2024-01-10 | Bhati Const. | Rakesh Pathak
34 | 2024-01-01 | 60/6 | DA+0 | DRY | 2024-01-10 | 2024-01-11 | Manoj Sharma | R T Singh
35 | 2024-01-01 | 57/2 | DA+3 | DRY | 2024-01-09 | 2024-01-11 | Om Const | R T Singh
36 | 2024-01-01 | 62/10 | DA+0 | DFR | 2024-01-11 | 2024-01-13 | Shakti Construction | Rakesh Pathak
37 | 2024-01-01 | 65/9 | DA+0 | DRY | 2024-01-11 | 2024-01-13 | Bhati Const. | Rakesh Pathak
38 | 2024-01-01 | 57/4 | DA+0 | Sandy | 2024-01-12 | 2024-01-14 | Om Const | R T Singh
39 | 2024-01-01 | 64/4 | DA+3 | DRY | 2024-01-13 | 2024-01-14 | Mahadev Eng | Rakesh Pathak
40 | 2024-01-01 | 65/3 | DA+3 | DRY | 2024-01-13 | 2024-01-15 | Veerteja Enterprises | Rakesh Pathak
41 | 2024-01-01 | 55/3 | DA+0 | Sandy | 2024-01-09 | 2024-01-15 | Imran | R T Singh
42 | 2024-01-01 | 60/10 | DA+0 | DFR | 2024-01-14 | 2024-01-15 | Manoj Sharma | R T Singh
43 | 2024-01-01 | 62/8 | DA+0 | DFR | 2024-01-15 | 2024-01-16 | Shakti Construction | Rakesh Pathak
44 | 2024-01-01 | 55/4 | DA+0 | Sandy | 2024-01-12 | 2024-01-17 | Imran | R T Singh
45 | 2024-01-01 | 57/5 | DA+3 | Sandy | 2024-01-14 | 2024-01-17 | Om Const | R T Singh
46 | 2024-01-01 | 26/3 | DA+0 | DRY | 2024-01-12 | 2024-01-18 | A.B. Construction | Jeetu Sachan
47 | 2024-01-01 | 64/1 | DA+0 | DRY | 2024-01-10 | 2024-01-18 | Mahadev Eng | Rakesh Pathak
48 | 2024-01-01 | 64/5 | DA+3 | DRY | 2024-01-16 | 2024-01-18 | Mahadev Eng | Rakesh Pathak
49 | 2024-01-01 | 65/6 | DA+0 | DRY | 2024-01-16 | 2024-01-18 | Bhati Const. | Rakesh Pathak
50 | 2024-01-01 | 61/0 | DB2+0 | DRY | 2024-01-17 | 2024-01-19 | Manoj Sharma | R T Singh
51 | 2024-01-01 | 62/9 | DA+3 | DFR | 2024-01-18 | 2024-01-19 | Shakti Construction | Rakesh Pathak
52 | 2024-01-01 | 65/5 | DA+0 | DRY | 2024-01-20 | 2024-01-21 | Bhati Const. | Rakesh Pathak
53 | 2024-01-01 | 64/2 | DA+3 | DRY | 2024-01-20 | 2024-01-21 | Mahadev Eng | Rakesh Pathak
54 | 2024-01-01 | 57/6 | DA+3 | Sandy | 2024-01-18 | 2024-01-21 | Om Const | R T Singh
55 | 2024-01-01 | 63/1 | DA+3 | DFR | 2024-01-21 | 2024-01-23 | Shakti Construction | Rakesh Pathak
56 | 2024-01-01 | 64/9 | DA+3 | DRY | 2024-01-22 | 2024-01-24 | Veerteja Enterprises | Rakesh Pathak
57 | 2024-01-01 | 60/11 | DA+3 | DRY | 2024-01-23 | 2024-01-24 | Manoj Sharma | R T Singh
58 | 2024-01-01 | 65/4 | DA+0 | DRY | 2024-01-23 | 2024-01-24 | Bhati Const. | Rakesh Pathak
59 | 2024-01-01 | 63/7 | DA+3 | DRY | 2024-01-24 | 2024-01-25 | Mahadev Eng | Rakesh Pathak
60 | 2024-01-01 | 55/5 | DA+0 | Sandy | 2024-01-17 | 2024-01-25 | Imran | R T Singh
61 | 2024-01-01 | 55/6 | DA+0 | Sandy | 2024-01-20 | 2024-01-25 | Imran | R T Singh
62 | 2024-01-01 | 63/2 | DA+0 | DFR | 2024-01-24 | 2024-01-25 | Shakti Construction | Rakesh Pathak
63 | 2024-01-01 | 27/8 | DA+0 | DFR | 2024-01-14 | 2024-01-27 | Nagana Ray And Company | Jeetu Sachan
64 | 2024-01-01 | 61/1 | DA+6 | DFR | 2024-01-27 | 2024-01-28 | Manoj Sharma | R T Singh
65 | 2024-01-01 | 55/7 | DA+0 | Sandy | 2024-01-27 | 2024-01-29 | Imran | R T Singh
66 | 2024-01-01 | 64/3 | DA+0 | DRY | 2024-01-29 | 2024-01-30 | Mahadev Eng | Rakesh Pathak
67 | 2024-01-01 | 63/3 | DA+3 | DFR | 2024-01-29 | 2024-01-30 | Shakti Construction | Rakesh Pathak
68 | 2024-01-01 | 64/8 | DA+3 | DRY | 2024-01-29 | 2024-01-31 | Veerteja Enterprises | Rakesh Pathak
69 | 2024-01-01 | 61/2 | DA+6 | DFR | 2024-01-30 | 2024-01-31 | Manoj Sharma | R T Singh
70 | 2024-02-01 | 64/7 | DA+3 | DRY | 2024-02-01 | 2024-02-02 | Mahadev Eng | Rakesh Pathak
71 | 2024-02-01 | 52/5 | DA+9 | Sandy | 2024-01-31 | 2024-02-02 | Imran | R T Singh
72 | 2024-02-01 | 63/4 | DA+0 | DRY | 2024-02-01 | 2024-02-02 | Shakti Construction | Rakesh Pathak
73 | 2024-02-01 | 26/4 | DA+6 | Sandy | 2024-01-27 | 2024-02-04 | Mehai Construction | Jeetu Sachan
74 | 2024-02-01 | 67/2 | DA+0 | DRY | 2024-02-03 | 2024-02-04 | Bhati Const. | Rakesh Pathak
75 | 2024-02-01 | 52/6 | DA+6 | Sandy | 2024-02-03 | 2024-02-06 | Imran | R T Singh
76 | 2024-02-01 | 64/6 | DA+0 | DRY | 2024-02-03 | 2024-02-07 | Mahadev Eng | Rakesh Pathak
77 | 2024-02-01 | 63/5 | DA+3 | DFR | 2024-02-06 | 2024-02-07 | Shakti Construction | Rakesh Pathak
78 | 2024-02-01 | 59/15 | DA+6 | DRY | 2024-02-05 | 2024-02-07 | Om Const | R T Singh
79 | 2024-02-01 | 61/5 | DA+3 | DRY | 2024-02-07 | 2024-02-09 | Manoj Sharma | R T Singh
80 | 2024-02-01 | 67/1 | DA+0 | DRY | 2024-02-07 | 2024-02-09 | Bhati Const. | Rakesh Pathak
81 | 2024-02-01 | 64/10 | DA+3 | DRY | 2024-02-08 | 2024-02-10 | Veerteja Enterprises | Rakesh Pathak
82 | 2024-02-01 | 61/6 | DA+3 | DRY | 2024-02-09 | 2024-02-11 | Manoj Sharma | R T Singh
83 | 2024-02-01 | 52/7 | DA+3 | Sandy | 2024-02-07 | 2024-02-12 | Imran | R T Singh
84 | 2024-02-01 | 59/16 | DA+9 | Dry | 2024-02-11 | 2024-02-12 | Om Const | R T Singh
85 | 2024-02-01 | 63/0 | DC1+0 | DFR | 2024-02-09 | 2024-02-13 | Shakti Construction | Rakesh Pathak
86 | 2024-02-01 | 52/8 | DA+6 | Sandy | 2024-02-09 | 2024-02-13 | Imran | R T Singh
87 | 2024-02-01 | 61/7 | DA+9 | Dry | 2024-02-11 | 2024-02-13 | Manoj Sharma | R T Singh
88 | 2024-02-01 | 26/5 | DA+6 | Sandy | 2024-02-05 | 2024-02-16 | Mehai Construction | Jeetu Sachan
89 | 2024-02-01 | 61/9 | DA+0 | Dry | 2024-02-14 | 2024-02-16 | Manoj Sharma | R T Singh
90 | 2024-02-01 | 60/1 | DA+6 | DRY | 2024-02-14 | 2024-02-16 | Om Const | R T Singh
91 | 2024-02-01 | 28/0 | DB2+0 | DFR | 2014-02-05 | 2024-02-17 | A.B. Construction | Jeetu Sachan
92 | 2024-02-01 | 52/10 | DA+9 | Sandy | 2024-02-14 | 2024-02-17 | Imran | R T Singh
93 | 2024-02-01 | 27/11 | DA+3 | DRY | 2024-02-10 | 2024-02-18 | A.B. Construction | Jeetu Sachan
94 | 2024-02-01 | 49/2 | DA+3 | Sandy | 2024-02-14 | 2024-02-18 | Veerteja Enterprises | R T Singh
95 | 2024-02-01 | 52/9 | DA+3 | Sandy | 2024-02-17 | 2024-02-19 | Imran | R T Singh
96 | 2024-02-01 | 61/8 | DA+6 | DRY | 2024-02-17 | 2024-02-20 | Manoj Sharma | R T Singh
97 | 2024-02-01 | 62/1 | DA+3 | Sandy | 2024-02-17 | 2024-02-21 | Shakti Construction | Rakesh Pathak
98 | 2024-02-01 | 53/5 | DA+3 | Sandy | 2024-02-21 | 2024-02-22 | Imran | R T Singh
99 | 2024-02-01 | 64/11 | DA+3 | DRY | 2024-02-23 | 2024-02-24 | Bhati Const. | Rakesh Pathak
100 | 2024-02-01 | 60/2 | DA+3 | DFR | 2024-02-20 | 2024-02-24 | Om Const | R T Singh
101 | 2024-02-01 | 21/10 | DA+6 | DRY | 2024-02-19 | 2024-02-25 | Swarup Enterprises | Jeetu Sachan
102 | 2024-02-01 | 60/3 | DA+3 | DFR | 2024-02-25 | 2024-02-28 | Manoj Sharma | R T Singh
103 | 2024-02-01 | 26/6 | DA+6 | Sandy | 2024-02-20 | 2024-02-29 | Mehai Construction | Jeetu Sachan
104 | 2024-02-01 | 65/0 | DB1+0 | DRY | 2024-02-28 | 2024-02-29 | Bhati Const. | Rakesh Pathak
105 | 2024-02-01 | 60/4 | DA+3 | DFR | 2024-02-27 | 2024-02-29 | Manoj Sharma | R T Singh
106 | 2024-03-01 | 22/1 | DA+9 | Sandy | 2024-02-26 | 2024-03-02 | Swarup Enterprises | Jeetu Sachan
107 | 2024-03-01 | 61/10 | DA+9 | DRY | 2024-02-03 | 2024-03-04 | Manoj Sharma | R T Singh
108 | 2024-03-01 | 65/1 | DA+0 | DRY | 2024-03-03 | 2024-03-05 | Bhati Const. | Rakesh Pathak
109 | 2024-03-01 | 22/6 | DA+0 | Sandy | 2024-03-01 | 2024-03-09 | A.B. Construction | Jeetu Sachan
110 | 2024-03-01 | 62/0 | DB2+0 | DRY | 2024-03-06 | 2024-03-10 | Manoj Sharma | R T Singh
111 | 2024-03-01 | 61/4 | DA+3 | DRY | 2024-03-13 | 2024-03-14 | Manoj Sharma | R T Singh
112 | 2024-03-01 | 49/3 | DA+3 | Sandy | 2024-03-13 | 2024-03-15 | Veerteja Enterprises | R T Singh
113 | 2024-03-01 | 27/5 | DA+0 | DRY | 2024-01-31 | 2024-03-17 | Majisa Construction | Jeetu Sachan
114 | 2024-03-01 | 49/6 | DA+0 | Sandy | 2024-03-14 | 2024-03-17 | Shakti Construction | R T Singh
115 | 2024-03-01 | 60/0 | DC1+0 | DRY | 2024-03-15 | 2024-03-19 | Manoj Sharma | R T Singh
116 | 2024-03-01 | 49/4 | DA+3 | Sandy | 2024-03-15 | 2024-03-19 | Veerteja Enterprises | R T Singh
117 | 2024-03-01 | 49/5 | DA+3 | Sandy | 2024-03-18 | 2024-03-20 | Shakti Construction | R T Singh
118 | 2024-03-01 | 47/10 | DA+6 | Sandy | 2024-03-18 | 2024-03-20 | Bhati Const. | R T Singh
119 | 2024-03-01 | 47/9 | DA+3 | Sandy | 2024-03-21 | 2024-03-23 | Bhati Const. | R T Singh
120 | 2024-03-01 | 47/8 | DA+0 | Sandy | 2024-03-26 | 2024-03-29 | Bhati Const.
121 | 2024-03-01 | 47/7 | DA+3 | Sandy | 2024-03-30 | 2024-03-31 | Bhati Const.
122 | 2024-04-01 | 50/9 | DA+0 | Sandy | 2024-03-22 | 2024-04-01 | Shakti Construction | R T Singh
123 | 2024-04-01 | 48/0 | DC2+0 | Sandy | 2024-04-03 | 2024-04-07 | Bhati Const. | R T Singh
124 | 2024-04-01 | 50/10 | DA+0 | Sandy | 2024-04-03 | 2024-04-08 | Shakti Construction | R T Singh
125 | 2024-04-01 | 51/1 | DA+0 | Sandy | 2024-04-08 | 2024-04-13 | Shakti Construction
126 | 2024-04-01 | 48/1 | DA+9 | Sandy | 2024-04-08 | 2024-04-15 | Veerteja Enterprises | R T Singh
127 | 2024-04-01 | 50/8 | DA+9 | Sandy | 2024-04-14 | 2024-04-19 | Shakti Construction | R T Singh
128 | 2024-04-01 | 49/1 | DA+0 | Sandy | 17-04-214 | 2024-04-20 | Veerteja Enterprises | R T Singh
129 | 2024-05-01 | 49/0 | DD45+0 | Sandy | 2024-04-22 | 2024-05-03 | Veerteja Enterprises | R T Singh
130 | 2024-05-01 | 43/6 | DA+3 | Sandy | 2024-05-02 | 2024-05-08 | Bande Bharat Group | Kuntal Debnath
131 | 2024-05-01 | 8/7 | DB1+0 | DRY | 2024-05-05 | 2024-05-10 | Mateshwari Const. | Abhijit Dutta
132 | 2024-05-01 | 50/7 | DA+0 | Sandy | 2024-05-05 | 2024-05-10 | Veerteja Enterprises | R T Singh
133 | 2024-05-01 | 8/10 | DA+3 | DFR | 2024-05-14 | 2024-05-18 | Mateshwari Const. | Abhijit Dutta
134 | 2024-05-01 | 50/1 | DA+6 | Sandy | 2024-05-14 | 2024-05-18 | Veerteja Enterprises | R T Singh
135 | 2024-05-01 | 47/6 | DA+3 | Sandy | 2024-05-15 | 2024-05-18 | Bhati Const. | R T Singh
136 | 2024-05-01 | 52/3 | DA+9 | Sandy | 2024-05-14 | 2024-05-25 | Sb Mehar Const. | R T Singh
137 | 2024-05-01 | 47/2 | DA+9 | Sandy | 2024-05-23 | 2024-05-26 | Bhati Const. | R T Singh
138 | 2024-05-01 | 10/14 | DA+3 | DRY | 2024-05-19 | 2024-05-27 | Mateshwari Const. | Abhijit Dutta
139 | 2024-05-01 | 10/19 | DA+0 | DRY | 2024-05-18 | 2024-05-28 | Jai Bhawani Construction | Abhijit Dutta
140 | 2024-05-01 | 50/4 | DA+9 | Sandy | 2024-05-20 | 2024-05-28 | Veerteja Enterprises | R T Singh
141 | 2024-05-01 | 51/2 | DA+0 | Sandy | 2024-05-25 | 2024-05-31 | Sb Mehar Const. | R T Singh
142 | 2024-05-01 | 47/5 | DA+0 | Sandy | 2024-05-29 | 2024-05-31 | Bhati Const. | R T Singh
143 | 2024-05-01 | 50/2 | DA+9 | Sandy | 2024-05-26 | 2024-05-31 | Veerteja Enterprises | R T Singh
144 | 2024-06-01 | 10/11 | DA+3 | DRY | 2024-05-29 | 2024-06-02 | Mateshwari Const. | Abhijit Dutta
145 | 2024-06-01 | 10/18 | DA+3 | DFR | 2024-05-29 | 2024-06-05 | Jai Bhawani Construction | Abhijit Dutta
146 | 2024-06-01 | 10/13 | DA+3 | DRY | 2024-05-30 | 2024-06-06 | Mateshwari Const. | Abhijit Dutta
147 | 2024-06-01 | 47/3 | DA+9 | Sandy | 2024-06-03 | 2024-06-08 | Bhati Const. | R T Singh
148 | 2024-06-01 | 51/0 | DC2+0 | Sandy | 2024-06-03 | 2024-06-10 | Sb Mehar Const. | R T Singh
149 | 2024-06-01 | 10/17 | DA+3 | DFR | 2024-06-03 | 2024-06-15 | Jai Bhawani Construction | Abhijit Dutta
150 | 2024-06-01 | 53/7 | DA+3 | Sandy | 2024-06-12 | 2024-06-15 | Bhati Const. | R T Singh
151 | 2024-06-01 | 10/8 | DA+3 | DFR | 2024-06-08 | 2024-06-19 | Mateshwari Const. | Abhijit Dutta
152 | 2024-06-01 | 10/12 | DB1+0 | DRY | 2024-06-10 | 2024-06-27 | Mateshwari Const. | Abhijit Dutta
153 | 2024-07-01 | 15/1 | DA+3 | DRY | 2024-06-29 | 2024-07-06 | Om Enterprise | Jeetu Sachan
154 | 2024-07-01 | 10/20 | DA+3 | DFR | 2024-06-20 | 2024-07-07 | Jai Bhawani Construction | Abhijit Dutta
155 | 2024-07-01 | 11A/5 | DA+3 | DRY | 2024-07-04 | 2024-07-12 | Punia Construction | Abhijit Dutta
156 | 2024-07-01 | 10/21 | DA+3 | DFR | 2024-06-28 | 2024-07-14 | Jai Bhawani Construction | Abhijit Dutta
157 | 2024-07-01 | 18/1 | DA+0 | DRY | 2024-07-07 | 2024-07-14 | J.P. Infra | Abhijit Dutta
158 | 2024-07-01 | 15/0 | DC1+0 | DRY | 2024-07-07 | 2024-07-15 | Om Enterprise | Jeetu Sachan
159 | 2024-07-01 | 14A/1 | DA+3 | DRY | 2024-07-14 | 2024-07-22 | Majisa Construction | Jeetu Sachan
160 | 2024-07-01 | 50/0 | DB2+0 | Sandy | 2024-07-10 | 2024-07-22 | Veerteja Enterprises | R T Singh
161 | 2024-07-01 | 11A/6 | DA+6 | DRY | 2024-07-10 | 2024-07-26 | Punia Construction | Bipin Kumar
162 | 2024-07-01 | 10/6 | DA+0 | DFR | 2024-07-16 | 2024-07-26 | Jai Bhawani Construction | Bipin Kumar
163 | 2024-07-01 | 16/0 | DC1+0 | DRY | 2024-07-03 | 2024-07-26 | Majisa Construction | Jeetu Sachan
164 | 2024-07-01 | 58/0 | DC1+3 | DFR | 2024-07-23 | 2024-07-29 | Bhati Const. | R T Singh
165 | 2024-07-01 | 18/0 | DC2+0 | DRY | 2024-07-20 | 2024-07-31 | J.P. Infra | Jeetu Sachan
166 | 2024-07-01 | 11/5 | DA+0 | DFR | 2024-07-18 | 2024-07-31 | Mci | Bipin Kumar
167 | 2024-08-01 | 10/3 | DA+0 | DFR | 2024-07-22 | 2024-08-03 | Jai Bhawani Construction | Bipin Kumar
168 | 2024-08-01 | 11A/7 | DA+9 | Sandy | 2024-07-27 | 2024-08-07 | Punia Construction | Bipin Kumar
169 | 2024-08-01 | 18/2 | DA+0 | DRY | 2024-07-30 | 2024-08-09 | Vibe Infra | Jeetu Sachan
170 | 2024-08-01 | 17/3 | DA+0 | DRY | 2024-07-30 | 2024-08-10 | J.P. Infra | Jeetu Sachan
171 | 2024-08-01 | 57/7 | DA+3 | DFR | 2024-08-07 | 2024-08-10 | Bhati Const. | R T Singh
172 | 2024-08-01 | 16/3 | DA+3 | DRY | 2024-08-03 | 2024-08-12 | Majisa Construction | Jeetu Sachan
173 | 2024-08-01 | 43/9 | DA+9 | Sandy | 2024-08-07 | 2024-08-13 | N.R. Enterprises | Kuntal Debnath
174 | 2024-08-01 | 17/5 | DA+3 | DRY | 2024-08-07 | 2024-08-14 | J.P. Infra | Jeetu Sachan
175 | 2024-08-01 | 11A/2 | DA+0 | DRY | 2024-08-12 | 2024-08-16 | R.K. Construction | Bipin Kumar
176 | 2024-08-01 | 16/4 | DA+0 | DRY | 2024-08-10 | 2024-08-18 | Om Enterprise | Jeetu Sachan
177 | 2024-08-01 | 18/3 | DA+0 | DRY | 2024-08-10 | 2024-08-18 | Vibe Infra | Jeetu Sachan
178 | 2024-08-01 | 17/4 | DA+3 | DRY | 2024-08-15 | 2024-08-19 | J.P. Infra | Jeetu Sachan
179 | 2024-08-01 | 10/9 | DA+0 | DRY | 2024-08-12 | 2024-08-19 | A.B. Construction | Bipin Kumar
180 | 2024-08-01 | 11A/8 | DA+6 | Sandy | 2024-08-07 | 2024-08-20 | Punia Construction | Bipin Kumar
181 | 2024-08-01 | 11A/9 | DA+3 | DRY | 2024-08-16 | 2024-08-22 | Punia Construction | Bipin Kumar
182 | 2024-08-01 | 43/8 | DA+9 | Sandy | 2024-08-14 | 2024-08-22 | N.R. Enterprises | Kuntal Debnath
183 | 2024-08-01 | 18/4 | DA+0 | DRY | 2024-08-13 | 2024-08-23 | Vibe Infra | Jeetu Sachan
184 | 2024-08-01 | 59/2 | DA+3 | DFR | 2024-08-19 | 2024-08-23 | Bhati Const. | R T Singh
185 | 2024-08-01 | 16/2 | DA+0 | DRY | 2024-08-14 | 2024-08-24 | Om Enterprise | Jeetu Sachan
186 | 2024-08-01 | 11A/0 | DB1+0 | DRY | 2024-08-12 | 2024-08-25 | Mci | Abhijit Dutta
187 | 2024-08-01 | 50/6 | DA+9 | Sandy | 2024-08-14 | 2024-08-28 | Kalpana Const. | R T Singh
188 | 2024-08-01 | 53/8 | DA+3 | Sandy | 2024-08-26 | 2024-08-29 | Bhati Const. | R T Singh
189 | 2024-08-01 | 17/1 | DA+3 | DRY | 2024-08-24 | 2024-08-30 | J.P. Infra | Jeetu Sachan
190 | 2024-08-01 | 43/7 | DA+3 | Sandy | 2024-08-24 | 2024-08-30 | N.R. Enterprises | Kuntal Debnath
191 | 2024-08-01 | 16/5 | DA+3 | DRY | 2024-08-28 | 2024-08-31 | Majisa Construction | Jeetu Sachan
192 | 2024-08-01 | 19/0 | DC2+0 | DRY | 2024-08-22 | 2024-08-31 | Vibe Infra | Jeetu Sachan
193 | 2024-09-01 | 11A/1 | DA+3 | DRY | 2024-08-22 | 2024-09-01 | Mci | Abhijit Dutta
194 | 2024-09-01 | 19/1 | DA+0 | DRY | 2024-08-29 | 2024-09-03 | Vibe Infra | Jeetu Sachan
195 | 2024-09-01 | 17/2 | DA+6 | DRY | 2024-08-27 | 2024-09-03 | J.P. Infra | Jeetu Sachan
196 | 2024-09-01 | 13/2 | DA+3 | DRY | 2024-08-28 | 2024-09-03 | Punia Construction | Abhijit Dutta
197 | 2024-09-01 | 43/5 | DA+3 | DRY | 2024-08-25 | 2024-09-05 | N.R. Enterprises | Kuntal Debnath
198 | 2024-09-01 | 53/6 | DA+6 | Sandy | 2024-08-30 | 2024-09-05 | Bhati Const. | R T Singh
199 | 2024-09-01 | 16/1 | DA+0 | DRY | 2024-08-27 | 2024-09-06 | Sidhi Vinayak | Jeetu Sachan
200 | 2024-09-01 | 11A/4 | DA+3 | DRY | 2024-09-02 | 2024-09-07 | Punia Construction | Jeetu Sachan
201 | 2024-09-01 | 54/1 | DA+3 | Sandy | 2024-09-05 | 2024-09-09 | Bhati Const. | R T Singh
202 | 2024-09-01 | 50/3 | DA+6 | Sandy | 2024-09-01 | 2024-09-10 | Kalpana Const. | R T Singh
203 | 2024-09-01 | 73/0 | DB2+0 | DRY | 2024-09-09 | 2024-09-10 | Shree Shyam Const.
204 | 2024-09-01 | 73/9 | DA+0 | DRY | 2024-09-08 | 2024-09-11 | Shakti Construction
205 | 2024-09-01 | 73/2 | DA+0 | DRY | 2024-09-12 | 2024-09-13 | Shree Shyam Const.
206 | 2024-09-01 | 25/0 | DC1+6 | DRY | 2024-09-05 | 2024-09-14 | J.P. Infra | Jeetu Sachan
207 | 2024-09-01 | 54/2 | DA+3 | Sandy | 2024-09-11 | 2024-09-14 | Bhati Const. | R T Singh
208 | 2024-09-01 | 14A/2 | DA+0 | DRY | 2024-09-08 | 2024-09-16 | Sidhi Vinayak | Jeetu Sachan
209 | 2024-09-01 | 10/4 | DA+3 | DFR | 2024-08-27 | 2024-09-16 | A.B. Construction | Abhijit Dutta
210 | 2024-09-01 | 73/1 | DA+0 | DRY | 2024-09-15 | 2024-09-16 | Shree Shyam Const. | Sk Sil
211 | 2024-09-01 | 14/0 | DC2+0 | Sandy | 2024-09-05 | 2024-09-18 | Om Enterprise | Jeetu Sachan
212 | 2024-09-01 | 11A/3 | DA+3 | DRY | 2024-09-05 | 2024-09-19 | R.K. Construction | Abhijit Dutta
213 | 2024-09-01 | 73/6 | DA+0 | DRY | 2024-09-18 | 2024-09-19 | Shree Shyam Const. | Sk Sil
214 | 2024-09-01 | 42/3 | DA+0 | Sandy | 2024-09-05 | 2024-09-20 | Mahadev Construction | Kuntal Debnath
215 | 2024-09-01 | 69/1 | DA+3 | DRY | 2024-09-19 | 2024-09-20 | Bhati Const. | Sk Sil
216 | 2024-09-01 | 25/4 | DA+0 | Sandy | 2024-09-13 | 2024-09-23 | J.P. Infra | Jeetu Sachan
217 | 2024-09-01 | 73/5 | DA+0 | DRY | 2024-09-22 | 2024-09-23 | Shree Shyam Const.
218 | 2024-09-01 | 43/4 | DA+3 | Sandy | 2024-09-10 | 2024-09-25 | N.R. Enterprises | Kuntal Debnath
219 | 2024-09-01 | 13/1 | DA+9 | DRY | 2024-09-19 | 2024-09-25 | Punia Construction | Abhijit Dutta
220 | 2024-09-01 | 40/2 | DA+3 | Sandy | 2024-09-19 | 2024-09-25 | D.R. Construction | Kuntal Debnath
221 | 2024-09-01 | 73/8 | DA+3 | DRY | 2024-09-23 | 2024-09-25 | Shakti Construction
222 | 2024-09-01 | 59/1 | DA+3 | DRY | 2024-09-20 | 2024-09-25 | Bhati Const. | R T Singh
223 | 2024-09-01 | 19/2 | DA+0 | DRY | 2024-09-20 | 2024-09-26 | Vibe Infra | Jeetu Sachan
224 | 2024-09-01 | 72/2 | DA+0 | DRY | 2024-09-25 | 2024-09-26 | Shree Shyam Const.
225 | 2024-09-01 | 17/0 | DB2+3 | DRY | 2024-09-19 | 2024-09-27 | Om Enterprise | Jeetu Sachan
226 | 2024-09-01 | 66/0 | DC2+6 | DRY | 2024-09-23 | 2024-09-27 | Bhati Const. | Sk Sil
227 | 2024-09-01 | 59/11 | DA+6 | DFR | 2024-09-25 | 2024-09-27 | Mahadev Eng | R T Singh
228 | 2024-09-01 | 19/3 | DA+0 | DRY | 2024-09-28 | 2024-09-30 | Vibe Infra | Jeetu Sachan
229 | 2024-09-01 | 43/3 | DA+0 | DRY | 2024-09-15 | 2024-09-30 | Parsuram Sai | Kuntal Debnath
230 | 2024-09-01 | 73/3 | DA+0 | DRY | 2024-09-25 | 2024-09-30 | Awadh Const.
231 | 2024-10-01 | 73/7 | DA+0 | DRY | 2024-09-29 | 2024-10-01 | Shakti Construction
232 | 2024-10-01 | 59/0 | DC2+0 | DRY | 2024-09-29 | 2024-10-04 | Bhati Const. | R T Singh
233 | 2024-10-01 | 67/0 | DC1+9 | DRY | 2024-10-04 | 2024-10-05 | Bhati Const.
234 | 2024-10-01 | 42/5 | DA+9 | Sandy | 2024-09-23 | 2024-10-07 | Mahadev Construction | Kuntal Debnath
235 | 2024-10-01 | 43/0 | DB1+0 | Sandy | 2024-09-28 | 2024-10-07 | N.R. Enterprises | Kuntal Debnath
236 | 2024-10-01 | 25/3 | DA+0 | Sandy | 2024-09-15 | 2024-10-08 | J.P. Infra | Bipin Kumar
237 | 2024-10-01 | 69/0 | DB2+0 | DFR | 2024-09-28 | 2024-10-09 | Bhati Const. | Sk Sil
238 | 2024-10-01 | 73/4 | DA+0 | DRY | 2024-10-08 | 2024-10-09 | Shree Shyam Const. | Sk Sil
239 | 2024-10-01 | 22/13 | DA+6 | Sandy | 2024-09-25 | 2024-10-10 | Rbm | Bipin Kumar
240 | 2024-10-01 | 74/0 | DB2+0 | Sandy | 2024-10-07 | 2024-10-10 | Shakti Construction | Sk Sil
241 | 2024-10-01 | 25/1 | DA+3 | DRY | 2024-09-28 | 2024-10-12 | J.P. Infra | Bipin Kumar
242 | 2024-10-01 | 43/2 | DA+0 | Sandy | 2024-09-28 | 2024-10-12 | Parsuram Sai | Kuntal Debnath
243 | 2024-10-01 | 72/3 | DA+3 | DRY | 2024-10-14 | 2024-10-15 | Shree Shyam Const. | Sk Sil
244 | 2024-10-01 | 43/11 | DA+3 | Sandy | 2024-09-25 | 2024-10-18 | Jitendra Enterprises | Kuntal Debnath
245 | 2024-10-01 | 13/0 | DD60+3 | DRY | 2024-10-04 | 2024-10-18 | R.K. Construction | Jeetu Sachan
246 | 2024-10-01 | 71/7 | DA+3 | DRY | 2024-10-17 | 2024-10-18 | Shree Shyam Const. | Sk Sil
247 | 2024-10-01 | 59/4 | DA+3 | DFR | 2024-10-14 | 2024-10-19 | Bhati Const. | R T Singh
248 | 2024-10-01 | 22/12 | DA+3 | Sandy | 2024-10-11 | 2024-10-21 | Rbm | Bipin Kumar
249 | 2024-10-01 | 42/1 | DA+6 | Sandy | 2024-10-10 | 2024-10-21 | N.R. Enterprises | Kuntal Debnath
250 | 2024-10-01 | 71/6 | DA+0 | DRY | 2024-10-20 | 2024-10-21 | Shree Shyam Const. | Sk Sil
251 | 2024-10-01 | 49/7 | DA+0 | Sandy | 2024-09-12 | 2024-10-21 | Kalpana Const. | R T Singh
252 | 2024-10-01 | 25/2 | DA+0 | DRY | 2024-10-12 | 2024-10-22 | J.P. Infra | Bipin Kumar
253 | 2024-10-01 | 13/3 | DA+3 | Sandy | 2024-09-28 | 2024-10-25 | Punia Construction | Ashutosh Singh
254 | 2024-10-01 | 22/7 | DA+0 | Sandy | 2024-10-24 | 2024-10-27 | Rbm | Bipin Kumar
255 | 2024-10-01 | 22/3 | DA+9 | Sandy | 2024-10-24 | 2024-10-27 | J.P. Infra | Bipin Kumar
256 | 2024-10-01 | 43/1 | DA+3 | Sandy | 2024-10-16 | 2024-10-30 | Parsuram Sai | Kuntal Debnath
257 | 2024-11-01 | 42/6 | DA+0 | Sandy | 2024-10-22 | 2024-11-07 | D.R. Construction | Kuntal Debnath
258 | 2024-11-01 | 2/4 | DA+3 | Sandy | 2024-11-12 | 2024-11-16 | Laxmi Enterprises | Ashutosh Kumar
259 | 2024-11-01 | 42/2 | DA+6 | Sandy | 2024-11-08 | 2024-11-17 | D.R. Construction | Kuntal Debnath
260 | 2024-11-01 | 22/8 | DB1+0 | Sandy | 2024-11-06 | 2024-11-19 | Rbm | Bipin Kumar
261 | 2024-11-01 | 22/2 | DA+6 | Sandy | 2024-11-11 | 2024-11-20 | J.P. Infra | Bipin Kumar
262 | 2024-11-01 | 54/0 | DB1+6 | Sandy |  | 2024-11-21 | Bhati Const. | R T Singh
263 | 2024-11-01 | 65/8 | DA+0 | DRY | 2024-11-27 | 2024-11-28 | Bhati Const. | Sk Sil
264 | 2024-11-01 | 42/0 | DC1+0 | Sandy | 2024-11-20 | 2024-11-30 | D.R. Construction | Kuntal Debnath
265 | 2024-11-01 | 65/7 | DA+0 | DRY | 2024-11-29 | 2024-11-30 | Bhati Const. | Sk Sil
266 | 2024-12-01 | 2/3 | DA+3 | Sandy | 2024-11-29 | 2024-12-03 | Laxmi Enterprise | Karan Singh
267 | 2024-12-01 | 22/4 | DA+9 | Sandy | 2024-12-01 | 2024-12-05 | Jp Infra | Bipin Singh
268 | 2024-12-01 | 6/1 | DA+0 | DFR | 2024-12-01 | 2024-12-10 | H.S. Engineering | Jitendra Yadav
269 | 2024-12-01 | 12/0 | DD60+0 | DRY | 2024-12-07 | 2024-12-14 | Vibe Infra Power | Jitendra Yadav
270 | 2024-12-01 | 22/5 | DA+9 | DRY | 2024-12-09 | 2024-12-14 | S.D. Infra | Bipin Singh
271 | 2024-12-01 | 41/2 | DA+0 | Sandy | 2024-10-26 | 2024-12-15 | D.R. Construction | Kuntal Debnath
272 | 2024-12-01 | 2/5 | DA+3 | Sandy | 2024-12-10 | 2024-12-15 | Sri Nagana Ray Enterprise | Jitendra Yadav
273 | 2024-12-01 | 22/9 | DA+6 | Sandy | 2024-12-13 | 2024-12-16 | Rbm | Bipin Singh
274 | 2024-12-01 | 70/8 | DA+3 | DRY | 2024-12-16 | 2024-12-17 | Tantray Construction | Sk Sil
275 | 2024-12-01 | 72/1 | DA+3 | DRY | 2024-12-16 | 2024-12-18 | Meer Const | Sk Sil
276 | 2024-12-01 | 70/7 | DA+3 | DRY | 2024-12-17 | 2024-12-19 | Tantray Construction | Sk Sil
277 | 2024-12-01 | 71/8 | DA+3 | DRY | 2024-12-19 | 2024-12-20 | Meer Const | Sk Sil
278 | 2024-12-01 | 52/1 | DA+6 | Sandy | 2024-12-17 | 2024-12-20 | Tantray Construction
279 | 2024-12-01 | 70/9 | DA+3 | DRY | 2024-12-20 | 2024-12-21 | Tantray Construction | Sk Sil
280 | 2024-12-01 | 6/2 | DA+0 | DFR | 2024-12-18 | 2024-12-23 | Hs Engineering | Jitendra Yadav
281 | 2024-12-01 | 72/0 | DB2+3 | DRY | 2024-12-22 | 2024-12-23 | Meer Const | Sk Sil
282 | 2024-12-01 | 70/6 | DA+3 | DRY | 2024-12-22 | 2024-12-23 | Tantray Construction | Sk Sil
283 | 2024-12-01 | 2/6 | DA+3 | Sandy | 2024-12-12 | 2024-12-24 | Sri Nagana Ray Enterprise | Jitendra Yadav
284 | 2024-12-01 | 71/4 | DA+3 | DRY | 2024-12-24 | 2024-12-25 | Meer Const | Sk Sil
285 | 2024-12-01 | 52/2 | DA+6 | Sandy | 2024-12-24 | 2024-12-25 | Tantray Construction | R T Singh
286 | 2024-12-01 | 70/10 | DA+3 | DRY | 2024-12-24 | 2024-12-25 | Tantray Construction
287 | 2024-12-01 | 2/2 | DA+3 | Sandy | 2024-12-17 | 2024-12-27 | Laxmi Enterprises | Jitendra Yadav
288 | 2024-12-01 | 71/5 | DA+3 | DRY | 2024-12-26 | 2024-12-27 | Meer Const | Sk Sil
289 | 2024-12-01 | 70/11 | DA+3 | DRY | 2024-12-26 | 2024-12-27 | Tantray Construction | Sk Sil
290 | 2024-12-01 | 53/2 | DA+0 | Sandy | 2024-12-25 | 2024-12-29 | Meer Const | R T Singh
291 | 2024-12-01 | 36/0 | DB2+0 | Sandy | 2024-12-21 | 2024-12-30 | Parsuram Sahi | Kuntal Debnath
292 | 2024-12-01 | 71/3 | DA+6 | DRY | 2024-12-29 | 2024-12-30 | Meer Const | Sk Sil
293 | 2024-12-01 | 52/4 | DA+9 | Sandy | 2024-12-27 | 2024-12-30 | Tantray Construction | R T Singh
294 | 2024-12-01 | 10/5 | DA+3 | DRY | 2024-12-25 | 2024-12-31 | Jsr Infrastructure | Jitendra Yadav
295 | 2024-12-01 | 35/4 | DA+0 | DRY | 2024-12-25 | 2024-12-31 | Parsuram Sahi | Kuntal Debnath
296 | 2024-12-01 | 71/0 | DB2+3 | DRY | 2024-12-29 | 2024-12-31 | Tantray Construction | Sk Sil
297 | 2025-01-01 | 22/11 | DA+6 | Sandy | 2024-12-23 | 2025-01-04 | Rbm | Bipin Singh
298 | 2025-01-01 | 71/2 | DA+3 | DRY | 2024-12-31 | 2025-01-04 | Meer Const | Sk Sil
299 | 2025-01-01 | 71/1 | DA+3 | DRY | 2025-01-04 | 2025-01-06 | Meer Const | Sk Sil
300 | 2025-01-01 | 54/3 | DA+6 | Sandy | 2025-01-02 | 2025-01-06 | Tantray Construction | R T Singh
301 | 2025-01-01 | 44/1 | DA+0 | Sandy | 2025-01-02 | 2025-01-06 | Tantray Construction | R T Singh
302 | 2025-01-01 | 44/2 | DA+0 | Sandy | 2025-01-04 | 2025-01-07 | Tantray Construction | R T Singh
303 | 2025-01-01 | 8/9 | DA+3 | DFR | 2025-01-02 | 2025-01-08 | Jsr Infrastructure | Sumit Kumar
304 | 2025-01-01 | 53/1 | DA+9 | Sandy | 2024-12-29 | 2025-01-08 | Meer Const | R T Singh
305 | 2025-01-01 | 70/3 | DA+3 | DRY | 2025-01-07 | 2025-01-09 | Meer Const | Sk Sil
306 | 2025-01-01 | 54/4 | DA+9 | Sandy | 2025-01-06 | 2025-01-09 | Tantray Construction | R T Singh
307 | 2025-01-01 | 45/0 | DC2+0 | Sandy | 2025-01-06 | 2025-01-09 | Nadeem | R T Singh
308 | 2025-01-01 | 44/11 | DA+0 | Sandy | 2025-01-07 | 2025-01-09 | Nadeem | R T Singh
309 | 2025-01-01 | 53/0 | DB2+9 | Sandy | 2025-01-06 | 2025-01-12 | Meer Const | R T Singh
310 | 2025-01-01 | 44/10 | DB1+9 | Sandy | 2025-01-11 | 2025-01-12 | Nadeem | R T Singh
311 | 2025-01-01 | 44/4 | DA+9 | Sandy | 2025-01-08 | 2025-01-12 | Tantray Construction | R T Singh
312 | 2025-01-01 | 70/4 | DA+3 | DRY | 2025-01-12 | 2025-01-13 | Meer Const | Sk Sil
313 | 2025-01-01 | 34/1 | DA+9 | Sandy | 2025-01-08 | 2025-01-14 | Ymk Construction | Kuntal Debnath
314 | 2025-01-01 | 70/5 | DA+3 | DRY | 2025-01-13 | 2025-01-15 | Meer Const | Sk Sil
315 | 2025-01-01 | 53/3 | DA+6 | Sandy | 2025-01-11 | 2025-01-15 | Meer Const | R T Singh
316 | 2025-01-01 | 35/2 | DB1+0 | Sandy | 2025-01-08 | 2025-01-16 | Parsuram Sahi | Kuntal Debnath
317 | 2025-01-01 | 68/0 | DD45+0 | DRY | 2025-01-13 | 2025-01-17 | Bhati Const.
318 | 2025-01-01 | 1A/1 | DA+6 | DFR | 2025-01-11 | 2025-01-18 | Jsr Infrastructure | Sumit Kumar
319 | 2025-01-01 | 53/4 | DA+0 | Sandy | 2025-01-14 | 2025-01-18 | Meer Const | R T Singh
320 | 2025-01-01 | 52/0 | DC2+0 | Sandy | 2025-01-11 | 2025-01-18 | Tantray Construction | R T Singh
321 | 2025-01-01 | 44/5 | DA+9 | Sandy | 2025-01-13 | 2025-01-19 | Tantray Construction | R T Singh
322 | 2025-01-01 | 2/0 | DC1+0 | DRY | 2025-01-04 | 2025-01-20 | Laxmi Enterprises | Sumit Kumar
323 | 2025-01-01 | 44/9 | DA+9 | Sandy | 2025-01-15 | 2025-01-20 | Iqbal | R T Singh
324 | 2025-01-01 | 70/1 | DA+3 | DRY | 2025-01-17 | 2025-01-21 | Meer Const | Sk Sil
325 | 2025-01-01 | 70/2 | DA+3 | DRY | 2025-01-20 | 2025-01-21 | Bhati Const. | Sk Sil
326 | 2025-01-01 | 44/6 | DB1+3 | Sandy | 2025-01-19 | 2025-01-21 | Tantray Construction | R T Singh
327 | 2025-01-01 | 55/2 | DA+0 | WFR | 2025-01-18 | 2025-01-22 | Meer Const | R T Singh
328 | 2025-01-01 | 47/4 | DA+3 | Sandy | 2025-01-19 | 2025-01-23 | Tantray Construction | R T Singh
329 | 2025-01-01 | 50/5 | DA+9 | Sandy | 2025-01-16 | 2025-01-23 | Om Const | R T Singh
330 | 2025-01-01 | 1A/4 | DA+3 | DFR | 2025-01-20 | 2025-01-25 | Naganaray Enterprise | Sumit
331 | 2025-01-01 | 28/6 | DA+6 | Sandy | 2025-01-19 | 2025-01-25 | Vishwakarma Construction | Bipin Kumar
332 | 2025-01-01 | 70/0 | DC1+0 | DRY | 2025-01-20 | 2025-01-25 | Meer Const
333 | 2025-01-01 | 44/7 | DA+9 | Sandy | 2025-01-23 | 2025-01-25 | Iqbal | R T Singh
334 | 2025-01-01 | 34/2 | DA+6 | Sandy | 2025-01-20 | 2025-01-27 | Ymk Construction | Kuntal Debnath
335 | 2025-01-01 | 65/10 | DA+0 | DRY | 2025-01-24 | 2025-01-27 | Bhati Const. | Sk Sil
336 | 2025-01-01 | 57/1 | DA+0 | Sandy | 2025-01-24 | 2025-01-27 | Meer Const | R T Singh
337 | 2025-01-01 | 28/5 | DA+9 | Sandy | 2025-01-22 | 2025-01-28 | Vishwakarma Construction | Bipin Kumar
338 | 2025-01-01 | 35/0 | DB2+6 | Sandy | 2025-01-18 | 2025-01-28 | Parsuram Sahi | Kuntal Debnath
339 | 2025-01-01 | 44/3 | DA+0 | Sandy | 2025-01-24 | 2025-01-28 | Tantray Construction | R T Singh
340 | 2025-01-01 | 1A/3 | DA+0 | DRY | 2025-01-21 | 2025-01-29 | Jsr Infrastructure | Sumit
341 | 2025-01-01 | 55/8 | DA+6 | Sandy | 2025-01-28 | 2025-01-30 | Meer Const | R T Singh
342 | 2025-01-01 | 1A/2 | DA+0 | DRY | 2025-01-26 | 2025-01-31 | Jsr Infrastructure | Sumit
343 | 2025-01-01 | 44/8 | DCT+0 | Sandy | 2025-01-27 | 2025-01-31 | Iqbal | R T Singh
344 | 2025-02-01 | 34/0 | DB2+0 | DRY | 2025-01-25 | 2025-02-01 | Ymk Construction | Kuntal Debnath
345 | 2025-02-01 | 28/8 | DA+3 | Sandy | 2025-01-25 | 2025-02-01 | Vishwakarma Construction | Kuntal Debnath
346 | 2025-02-01 | 47/1 | DA+3 | Sandy | 2025-01-25 | 2025-02-01 | Tantray Construction | R T Singh
347 | 2025-02-01 | 1A/5 | DA+0 | DRY | 2025-01-27 | 2025-02-02 | Jsr Infrastructure | Sumit
348 | 2025-02-01 | 28/7 | DA+3 | Sandy | 2025-01-28 | 2025-02-04 | Vishwakarma Construction | Kuntal Debnath
349 | 2025-02-01 | 33/1 | DA+0 | DRY | 2025-02-01 | 2025-02-07 | Ymk Construction | Kuntal Debnath
350 | 2025-02-01 | 28/4 | DA+0 | Sandy | 2025-02-02 | 2025-02-07 | Vishwakarma Construction | Kuntal Debnath
351 | 2025-02-01 | 1A/6 | DA+0 | Sandy | 2025-01-31 | 2025-02-07 | Jsr Infrastructure | Sumit
352 | 2025-02-01 | 35/3 | DB1+6 | Sandy | 2025-02-01 | 2025-02-09 | Parsuram Sahi | Kuntal Debnath
353 | 2025-02-01 | 45/1 | DA+9 | Sandy | 2025-02-01 | 2025-02-09 | Tantray Construction | R T Singh
354 | 2025-02-01 | 54/5 | DA+9 | Sandy | 2025-02-06 | 2025-02-10 | Meer Const | R T Singh
355 | 2025-02-01 | 32/3 | DA+0 | Sandy | 2025-02-05 | 2025-02-11 | Ymk Construction | Kuntal Debnath
356 | 2025-02-01 | 28/3 | DA+0 | DFR | 2025-02-04 | 2025-02-11 | Vishwakarma Construction | Kuntal Debnath
357 | 2025-02-01 | 32/4 | DA+0 | Sandy | 2025-02-09 | 2025-02-13 | Ymk Construction | Kuntal Debnath
358 | 2025-02-01 | 28/2 | DA+0 | DFR | 2025-02-09 | 2025-02-13 | Vishwakarma Construction | Kuntal Debnath
359 | 2025-02-01 | 32/2 | DA+3 | DRY | 2025-02-09 | 2025-02-13 | Ymk Construction | Kuntal Debnath
360 | 2025-02-01 | 29/0 | DB1+0 | DRY | 2025-02-12 | 2025-02-16 | Vishwakarma Construction | Kuntal Debnath
361 | 2025-02-01 | 55/0 | DB1+6 | Sandy | 2025-02-11 | 2025-02-16 | Meer Const | R T Singh
362 | 2025-02-01 | 44/0 | DB1+3 | Sandy | 2025-02-10 | 2025-02-16 | Om Const | R T Singh
363 | 2025-02-01 | 30/0 | DC1+0 | DRY | 2025-02-15 | 2025-02-20 | Vishwakarma Construction | Kuntal Debnath
364 | 2025-02-01 | 33/0 | DC1+0 | DRY | 2025-02-14 | 2025-02-20 | Ymk Construction | Kuntal Debnath
365 | 2025-02-01 | 1A/0 | DD60+0 | DRY | 2025-02-06 | 2025-02-20 | Jsr Infrastructure | Sumit
366 | 2025-02-01 | 30/1 | DA+0 | Sandy | 2025-02-17 | 2025-02-22 | Vishwakarma Construction | Kuntal Debnath
367 | 2025-02-01 | 43/10 | DA+3 | Sandy | 2025-02-18 | 2025-02-23 | Om Const | R T Singh
368 | 2025-02-01 | 29/4 | DA+6 | DRY | 2025-02-22 | 2025-02-25 | Vishwakarma Construction | Kuntal Debnath
369 | 2025-02-01 | 29/1 | DA+3 | DRY | 2025-02-24 | 2025-02-28 | Vishwakarma Construction | Kuntal Debnath
370 | 2025-02-01 | 55/1 | DA+0 | WFR | 2025-02-21 | 2025-02-28 | Bhati | R T Singh
371 | 2025-03-01 | 35/5 | DA+0 | Sandy | 2025-02-10 | 2025-03-02 | Parsuram Sahi | Kuntal Debnath
372 | 2025-03-01 | 32/1 | DA+3 | Sandy | 2025-02-28 | 2025-03-02 | Ymk | Kuntal Debnath
373 | 2025-03-01 | 30/3 | DA+3 | Sandy | 2025-02-28 | 2025-03-03 | Vishwakarma Construction | Kuntal Debnath
374 | 2025-03-01 | 30/2 | DA+0 | Sandy | 2025-03-01 | 2025-03-06 | Vishwakarma Construction | Kuntal Debnath
375 | 2025-03-01 | 1/0 | DD60+0 | DRY | 2025-02-25 | 2025-03-07 | Jsr | Sumit
376 | 2025-03-01 | 32/0 | DC1+0 | DRY | 2025-03-01 | 2025-03-07 | Ymk | Kuntal Debnath
377 | 2025-03-01 | 29/2 | DA+3 | DRY | 2025-03-03 | 2025-03-08 | Vishwakarma Construction | Kuntal Debnath
378 | 2025-03-01 | 1A/7 | DA+3 | Sandy | 2025-03-01 | 2025-03-08 | Jsr | Sumit
379 | 2025-03-01 | 29/3 | DA+0 | Sandy | 2025-03-05 | 2025-03-10 | Vishwakarma Construction | Kuntal Debnath
380 | 2025-03-01 | 31/2 | DA+0 | DRY | 2025-03-05 | 2025-03-10 | Ymk | Kuntal Debnath
381 | 2025-03-01 | 31/1 | DA+0 | DRY | 2025-03-08 | 2025-03-12 | Ymk | Kuntal Debnath
382 | 2025-03-01 | 2/1 | DA+3 | Sandy | 2025-03-14 | 2025-03-20 | Jsr | Sumit
383 | 2025-03-01 | 34/3 | DA+0 | Sandy | 2025-03-19 | 2025-03-25 | Ymk | Kuntal Debnath
384 | 2025-03-01 | 26/7 | DA+0 | DFR | 2025-03-20 | 2025-03-26 | Jsr | Bipin Kumar
385 | 2025-03-01 | 37/3 | DA+0 | Sandy | 2025-04-22 | 2025-03-30 | Vishwakarma Construction | Kuntal Debnath
386 | 2025-03-01 | 34/4 | DA+0 | Sandy | 2025-04-21 | 2025-03-31 | Ymk | Kuntal Debnath
387 | 2025-03-01 | 57/0 | DD60+25 | Sandy | 2025-03-22 | 2025-03-31 | Bhati | R T Singh
388 | 2025-04-01 | 35/1 | DA+9 | Sandy | 2025-03-31 | 2025-04-06 | Ymk | Kuntal Debnath
389 | 2025-04-01 | 46/0 | DD60+25 | Sandy | 2025-03-25 | 2025-04-09 | Om Const | R T Singh
390 | 2025-04-01 | 38/4 | DA+9 | Sandy | 2025-04-07 | 2025-04-11 | Vishwakarma Construction | Kuntal Debnath
391 | 2025-04-01 | 56/0 | DD60+25 | Sandy | 2025-04-02 | 2025-04-12 | Bhati | R T Singh
392 | 2025-04-01 | 39/0 | DB2+6 | Sandy | 2025-04-12 | 2025-04-15 | Vishwakarma Construction | Kuntal Debnath
393 | 2025-04-01 | 27/3 | DA+3 | DFR | 2025-04-12 | 2025-04-17 | YMK | Kuntal Debnath
394 | 2025-04-01 | 47/0 | DD60+25 | Sandy | 2025-04-05 | 2025-04-17 | Om Const | R T Singh
395 | 2025-04-01 | 4/0 | DD60+6 | DRY | 2025-04-13 | 2025-04-19 | Jsr | Sumit
396 | 2025-04-01 | 38/2 | DA+6 | Sandy | 2025-04-18 | 2025-04-22 | Vishwakarma Construction | Kuntal Debnath
397 | 2025-04-01 | 27/2 | DA+3 | DFR | 2025-04-17 | 2025-04-23 | YMK | Kuntal Debnath
398 | 2025-04-01 | 38/1 | DA+0 | Sandy | 2025-04-21 | 2025-04-23 | Vishwakarma Construction | Kuntal Debnath
399 | 2025-04-01 | 38/0 | DB2+6 | Sandy | 2025-04-24 | 2025-04-26 | Vishwakarma Construction | Kuntal Debnath
400 | 2025-04-01 | 39/1 | DA+0 | Sandy | 2025-04-27 | 2025-04-29 | Vishwakarma Construction | Kuntal Debnath
401 | 2025-05-01 | 40/0 | DC2+0 | Sandy | 2025-04-30 | 2025-05-05 | Vishwakarma Construction | Kuntal Debnath
402 | 2025-05-01 | 40/1 | DA+6 | Sandy | 2025-05-02 | 2025-05-10 | Vishwakarma Construction | Kuntal Debnath
403 | 2025-05-01 | 27/6 | DA+0 | Sandy | 2025-05-07 | 2025-05-12 | YMK | Kuntal Debnath
404 | 2025-05-01 | 1A/8 | DA+0 | Sandy | 2025-05-29 | 2025-05-16 | Jsr | Sumit
405 | 2025-05-01 | 27/4 | DA+3 | DFR | 2025-05-12 | 2025-05-18 | YMK | Kuntal Debnath
406 | 2025-05-01 | 38/3 | DA+9 | Sandy | 2025-05-12 | 2025-05-19 | Vishwakarma Construction | Kuntal Debnath
407 | 2025-05-01 | 42/4 | DA+0 | Sandy | 2024-05-16 | 2024-05-20 | Vishwakarma Construction | Kuntal Debnath
408 | 2025-05-01 | 40/3 | DA+3 | Sandy | 2025-05-18 | 2025-05-24 | Vishwakarma Construction | Kuntal Debnath
409 | 2025-05-01 | 21/9 | DA+3 | DFR | 2025-05-13 | 2025-05-26 | M.R. Choudhary | Vivek Shukla
410 | 2025-05-01 | 27/7 | DB1+0 | DFR | 2025-05-18 | 2025-05-27 | YMK | Kuntal Debnath
411 | 2025-05-01 | 4/3 | DA+0 | DRY | 2025-05-13 | 2025-05-28 | Nyce Service & Security | Sumit
412 | 2025-05-01 | 2/8 | DA+0 | Sandy | 2025-05-26 | 2025-05-30 | Jsr | Sumit
413 | 2025-05-01 | 8/11 | DA+0 | DRY | 2025-05-12 | 2025-05-30 | Bhati Construction | Sumit
414 | 2025-06-01 | 41/1 | DB1+9 | Sandy | 2025-05-21 | 2025-06-02 | Vishwakarma Construction | Kuntal Debnath
415 | 2025-06-01 | 30/4 | DA+3 | DRY | 2025-05-21 | 2025-06-03 | Rabbit bright technology pvt. Ltd. | Kuntal Debnath
|  | Loc no | TOT | FDN Status | Classification | Start Date | Gang Name | Section Incharge | Foundation Status | Materials Status
|  | 3/0 | DD60+6 | WIP | DRY | 2025-05-02 | Jsr | Sumit |  | Only Stub balance to supply.
|  | 4/1 | DA+0 | WIP |  | 2025-04-26 | Jsr | Sumit |  | Indent received, material to be supplied by 18th.
|  | 2/7 | DA+3 | WIP |  | 2025-05-30 | Jsr | Sumit
|  | 8/12 | DA+0 | WIP |  | 2025-05-12 | Bhati Construction | Sumit |  | Indent received, material required by 16th.
|  | 27/0 | DC1+0 | WIP |  | 2025-05-05 | YMK | Kuntal Debnath |  | Indent received, will be confirmed in 2 days advance.
|  | 27/1 | DA+3 | WIP |  | 2025-05-02 | YMK | Kuntal Debnath |  | All materials received at site.
|  | 21/7 | DA+3 | WIP |  | 2025-05-07 | M.R. Choudhary | Kuntal Debnath |  | Indent received, Materials will be required by 14.5
|  | 21/5 | DA+6 | WIP |  | 2025-05-29 | M.R. Choudhary | Kuntal Debnath
|  | 41/0 | DC1+6 | WIP |  | 2025-06-01 | Vishwakarma Construction | Kuntal Debnath
|  | 19/5 | DA+0 | WIP |  | 2025-06-01 | Shree Ram Construction | Vivek Shukla
|  | 10/0 | DD60+25 | WIP |  | 2025-05-14 | Bhati Construction | Sumit |  | Indent awaited.
|  | 10/1 | DA+0 | WIP |  | 2025-05-16 | Bhati Construction | Sumit
|  | 30/5 | DA+3 | WIP |  | 2025-05-30 | Rabbit bright technology pvt. Ltd. | Kuntal Debnath

## Earthing
Progress Summary'!A1
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line
List of Completed Earthing
Earthing
SL No. | FDN No. | Location No. | Tower Type | Classification | Type of Earthing | End Date | Gang Name | Earthing Completion Month
1 | 2023-10-01 | 36/1 | DA+0 | Sandy | Pipe | 2023-12-30 | Nagana Ray and company | 2023-12-01
2 | 2023-12-01 | 61/3 | DA+6 | DRY | Pipe | 2023-12-18 | Manoj Sharma | 2023-12-01
3 | 2023-12-01 | 27/12 | DA+3 | Sandy | Pipe | 2024-02-26 | Nagana Ray And Company | 2024-02-01
4 | 2023-12-01 | 62/6 | DA+3 | DRY | Pipe | 2024-01-07 | Shakti Construction | 2024-01-01
5 | 2023-12-01 | 59/14 | DA+6 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01
6 | 2023-12-01 | 62/7 | DA+3 | DRY | Pipe | 2024-01-09 | Shakti Construction | 2024-01-01
7 | 2023-12-01 | 59/13 | DA+3 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01
8 | 2023-12-01 | 27/10 | DA+3 | DFR | CP | 2023-12-30 | Nagana Ray And Company | 2023-12-01
9 | 2023-12-01 | 63/8 | DA+3 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
10 | 2023-12-01 | 59/10 | DA+0 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01
11 | 2023-12-01 | 62/5 | DA+0 | DRY | Pipe | 2024-01-07 | Shakti Construction | 2024-01-01
12 | 2023-12-01 | 59/9 | DA+3 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01
13 | 2023-12-01 | 60/9 | DA+3 | DRY | Pipe | 2024-01-06 | Imran | 2024-01-01
14 | 2023-12-01 | 62/4 | DA+3 | DRY | Pipe | 2023-12-31 | Shakti Construction | 2023-12-01
15 | 2023-12-01 | 59/8 | DB1+3 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01
15 | 2023-12-01 | 26/2 | DA+3 | DFR | CP |  | A.B. Construction
16 | 2023-12-01 | 59/6 | DA+3 | DFR | CP | 2024-01-05 | Om Const | 2024-01-01
17 | 2023-12-01 | 63/6 | DA+3 | DRY | Pipe | 2024-01-12 | Mahadev Eng | 2024-01-01
18 | 2023-12-01 | 60/8 | DA+0 | DRY | Pipe | 2024-01-06 | Imran | 2024-01-01
19 | 2023-12-01 | 27/9 | DA+0 | DFR | CP | 2023-12-30 | Nagana Ray And Company | 2023-12-01
20 | 2023-12-01 | 59/7 | DA+3 | DRY | Pipe | 2024-01-03 | Manoj Sharma | 2024-01-01
21 | 2023-12-01 | 59/5 | DA+3 | DFR | CP | 2024-01-05 | Om Const | 2024-01-01
22 | 2023-12-01 | 62/3 | DA+0 | DRY | Pipe | 2024-01-07 | Shakti Construction | 2024-01-01
23 | 2024-01-01 | 59/12 | DA+6 | DFR | CP | 2024-01-16 | Manoj Sharma | 2024-01-01
24 | 2024-01-01 | 60/7 | DA+3 | DRY | Pipe | 2024-01-06 | Imran | 2024-01-01
25 | 2024-01-01 | 62/2 | DA+3 | DRY | Pipe | 2024-01-07 | Shakti Construction | 2024-01-01
26 | 2024-01-01 | 59/3 | DA+3 | DFR | CP | 2024-02-22 | Om Const | 2024-02-01
27 | 2024-01-01 | 64/0 | DB2+0 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
28 | 2024-01-01 | 57/3 | DA+0 | DRY | Pipe | 2024-02-22 | Om Const | 2024-02-01
29 | 2024-01-01 | 60/5 | DA+3 | DRY | Pipe | 2024-01-16 | Manoj Sharma | 2024-01-01
30 | 2024-01-01 | 62/11 | DA+3 | DRY | Pipe | 2024-01-28 | Shakti Construction | 2024-01-01
31 | 2024-01-01 | 65/2 | DA+0 | DRY | Pipe | 2024-01-12 | Veerteja Enterprises | 2024-01-01
32 | 2024-01-01 | 65/11 | DA+0 | DRY | Pipe | 2024-01-15 | Bhati Const. | 2024-01-01
33 | 2024-01-01 | 60/6 | DA+0 | DRY | Pipe | 2024-01-16 | Manoj Sharma | 2024-01-01
34 | 2024-01-01 | 57/2 | DA+3 | DRY | Pipe | 2024-02-14 | Om Const | 2024-02-01
35 | 2024-01-01 | 62/10 | DA+0 | DFR | CP | 2024-02-22 | Shakti Construction | 2024-02-01
36 | 2024-01-01 | 65/9 | DA+0 | DRY | Pipe | 2024-01-15 | Bhati Const. | 2024-01-01
37 | 2024-01-01 | 57/4 | DA+0 | Sandy | Pipe | 2024-02-14 | Om Const | 2024-02-01
38 | 2024-01-01 | 64/4 | DA+3 | DRY | Pipe | 2024-01-19 | Mahadev Eng | 2024-01-01
39 | 2024-01-01 | 65/3 | DA+3 | DRY | Pipe | 2024-01-20 | Veerteja Enterprises | 2024-01-01
40 | 2024-01-01 | 55/3 | DA+0 | Sandy | Pipe | 2024-02-02 | Imran | 2024-02-01
41 | 2024-01-01 | 60/10 | DA+0 | DFR | CP | 2024-02-02 | Manoj Sharma | 2024-02-01
42 | 2024-01-01 | 62/8 | DA+0 | DFR | CP | 2024-02-21 | Shakti Construction | 2024-02-01
43 | 2024-01-01 | 55/4 | DA+0 | Sandy | Pipe | 2024-01-17 | Imran | 2024-01-01
44 | 2024-01-01 | 57/5 | DA+3 | Sandy | Pipe | 2024-02-14 | Om Const | 2024-02-01
44 | 2024-01-01 | 26/3 | DA+0 | DRY | Pipe |  | A.B. Construction
45 | 2024-01-01 | 64/1 | DA+0 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
46 | 2024-01-01 | 64/5 | DA+3 | DRY | Pipe | 2024-01-25 | Mahadev Eng | 2024-01-01
47 | 2024-01-01 | 65/6 | DA+0 | DRY | Pipe | 2024-02-09 | Bhati Const. | 2024-02-01
48 | 2024-01-01 | 61/0 | DB2+0 | DRY | Pipe | 2024-02-02 | Manoj Sharma | 2024-02-01
49 | 2024-01-01 | 62/9 | DA+3 | DFR | CP | 2024-02-21 | Shakti Construction | 2024-02-01
50 | 2024-01-01 | 65/5 | DA+0 | DRY | Pipe | 2024-02-09 | Bhati Const. | 2024-02-01
51 | 2024-01-01 | 64/2 | DA+3 | DRY | Pipe | 2024-01-25 | Mahadev Eng | 2024-01-01
52 | 2024-01-01 | 57/6 | DA+3 | Sandy | Pipe | 2024-02-22 | Om Const | 2024-02-01
53 | 2024-01-01 | 63/1 | DA+3 | DFR | CP | 2024-01-27 | Shakti Construction | 2024-01-01
54 | 2024-01-01 | 64/9 | DA+3 | DRY | Pipe | 2024-02-20 | Veerteja Enterprises | 2024-02-01
55 | 2024-01-01 | 60/11 | DA+3 | DRY | Pipe | 2024-02-02 | Manoj Sharma | 2024-02-01
56 | 2024-01-01 | 65/4 | DA+0 | DRY | Pipe | 2024-01-25 | Bhati Const. | 2024-01-01
57 | 2024-01-01 | 63/7 | DA+3 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
58 | 2024-01-01 | 55/5 | DA+0 | Sandy | Pipe | 2024-01-29 | Imran | 2024-01-01
59 | 2024-01-01 | 55/6 | DA+0 | Sandy | Pipe | 2024-01-29 | Imran | 2024-01-01
60 | 2024-01-01 | 63/2 | DA+0 | DFR | CP | 2024-01-27 | Shakti Construction | 2024-01-01
61 | 2024-01-01 | 27/8 | DA+0 | DFR | CP | 2024-01-31 | Nagana Ray And Company | 2024-01-01
62 | 2024-01-01 | 61/1 | DA+6 | DFR | CP | 2024-02-02 | Manoj Sharma | 2024-02-01
63 | 2024-01-01 | 55/7 | DA+0 | Sandy | Pipe | 2024-02-02 | Imran | 2024-02-01
64 | 2024-01-01 | 64/3 | DA+0 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
65 | 2024-01-01 | 63/3 | DA+3 | DFR | Pipe | 2024-02-22 | Shakti Construction | 2024-02-01
66 | 2024-01-01 | 64/8 | DA+3 | DRY | Pipe | 2024-02-01 | Veerteja Enterprises | 2024-02-01
67 | 2024-01-01 | 61/2 | DA+6 | DFR | CP | 2024-02-02 | Manoj Sharma | 2024-02-01
68 | 2024-02-01 | 64/7 | DA+3 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
69 | 2024-02-01 | 52/5 | DA+9 | Sandy | Pipe | 2024-02-05 | Imran | 2024-02-01
70 | 2024-02-01 | 63/4 | DA+0 | DRY | Pipe | 2024-02-14 | Shakti Construction | 2024-02-01
71 | 2024-02-01 | 26/4 | DA+6 | Sandy | Pipe | 2024-02-17 | Mehai Construction | 2024-02-01
72 | 2024-02-01 | 67/2 | DA+0 | DRY | Pipe | 2024-02-09 | Bhati Const. | 2024-02-01
73 | 2024-02-01 | 52/6 | DA+6 | Sandy | Pipe | 2024-02-08 | Imran | 2024-02-01
74 | 2024-02-01 | 64/6 | DA+0 | DRY | Pipe | 2024-02-14 | Mahadev Eng | 2024-02-01
75 | 2024-02-01 | 63/5 | DA+3 | DFR | CP | 2024-02-15 | Shakti Construction | 2024-02-01
76 | 2024-02-01 | 59/15 | DA+6 | DRY | Pipe | 2024-02-26 | Om Const | 2024-02-01
77 | 2024-02-01 | 61/5 | DA+3 | DRY | Pipe | 2024-02-22 | Manoj Sharma | 2024-02-01
78 | 2024-02-01 | 67/1 | DA+0 | DRY | Pipe | 2024-02-13 | Bhati Const. | 2024-02-01
79 | 2024-02-01 | 64/10 | DA+3 | DRY | Pipe | 2024-02-11 | Veerteja Enterprises | 2024-02-01
80 | 2024-02-01 | 61/6 | DA+3 | DRY | Pipe | 2024-02-22 | Manoj Sharma | 2024-02-01
81 | 2024-02-01 | 52/7 | DA+3 | Sandy | Pipe | 2024-02-13 | Imran | 2024-02-01
82 | 2024-02-01 | 59/16 | DA+9 | Dry | Pipe | 2024-02-26 | Om Const | 2024-02-01
83 | 2024-02-01 | 63/0 | DC1+0 | DFR | CP | 2024-02-15 | Shakti Construction | 2024-02-01
84 | 2024-02-01 | 52/8 | DA+6 | Sandy | Pipe | 2024-02-22 | Imran | 2024-02-01
85 | 2024-02-01 | 61/7 | DA+9 | Dry | Pipe | 2024-02-22 | Manoj Sharma | 2024-02-01
86 | 2024-02-01 | 26/5 | DA+6 | Sandy | Pipe | 2024-02-18 | Mehai Construction | 2024-02-01
87 | 2024-02-01 | 61/9 | DA+0 | Dry | Pipe | 2024-02-22 | Manoj Sharma | 2024-02-01
88 | 2024-02-01 | 60/1 | DA+6 | DRY | Pipe | 2024-02-23 | Om Const | 2024-02-01
89 | 2024-02-01 | 28/0 | DB2+0 | DFR | CP | 2024-02-18 | A.B. Construction | 2024-02-01
90 | 2024-02-01 | 52/10 | DA+9 | Sandy | Pipe | 2024-02-17 | Imran | 2024-02-01
91 | 2024-02-01 | 27/11 | DA+3 | DRY | Pipe | 2024-02-19 | A.B. Construction | 2024-02-01
92 | 2024-02-01 | 49/2 | DA+3 | Sandy | Pipe | 2024-03-08 | Veerteja Enterprises | 2024-03-01
93 | 2024-02-01 | 52/9 | DA+3 | Sandy | Pipe | 2024-02-22 | Imran | 2024-02-01
94 | 2024-02-01 | 61/8 | DA+6 | DRY | Pipe | 2024-02-22 | Manoj Sharma | 2024-02-01
95 | 2024-02-01 | 62/1 | DA+3 | Sandy | Pipe | 2024-02-22 | Shakti Construction | 2024-02-01
96 | 2024-02-01 | 53/5 | DA+3 | Sandy | Pipe | 2024-02-25 | Imran | 2024-02-01
97 | 2024-02-01 | 64/11 | DA+3 | DRY | Pipe | 2024-03-06 | Bhati Const. | 2024-03-01
98 | 2024-02-01 | 60/2 | DA+3 | DFR | CP | 2024-02-26 | Om Const | 2024-02-01
99 | 2024-02-01 | 21/10 | DA+6 | DRY | Pipe | 2024-03-03 | Swarup Enterprises | 2024-03-01
100 | 2024-02-01 | 60/3 | DA+3 | DFR | CP | 2024-03-01 | Manoj Sharma | 2024-03-01
101 | 2024-02-01 | 26/6 | DA+6 | Sandy | Pipe | 2024-03-05 | Mehai Construction | 2024-03-01
102 | 2024-02-01 | 65/0 | DB1+0 | DRY | Pipe | 2024-03-06 | Bhati Const. | 2024-03-01
103 | 2024-02-01 | 60/4 | DA+3 | DFR | CP | 2024-03-01 | Manoj Sharma | 2024-03-01
104 | 2024-03-01 | 22/1 | DA+9 | Sandy | Pipe | 2024-03-03 | Swarup Enterprises | 2024-03-01
105 | 2024-03-01 | 61/10 | DA+9 | DRY | Pipe | 2024-03-12 | Manoj Sharma | 2024-03-01
106 | 2024-03-01 | 65/1 | DA+0 | DRY | Pipe | 2024-03-07 | Bhati Const. | 2024-03-01
107 | 2024-03-01 | 22/6 | DA+0 | Sandy | Pipe | 2024-03-23 | A.B. Construction | 2024-03-01
108 | 2024-03-01 | 62/0 | DB2+0 | DRY | Pipe | 2024-03-12 | Manoj Sharma | 2024-03-01
109 | 2024-03-01 | 61/4 | DA+3 | DRY | Pipe | 2024-03-22 | Manoj Sharma | 2024-03-01
110 | 2024-03-01 | 49/3 | DA+3 | Sandy | Pipe | 2024-03-21 | Veerteja Enterprises | 2024-03-01
111 | 2024-03-01 | 27/5 | DA+0 | DRY | Pipe | 2024-03-18 | Majisa Construction | 2024-03-01
112 | 2024-03-01 | 49/6 | DA+0 | Sandy | Pipe | 2024-04-20 | Shakti Construction | 2024-04-01
113 | 2024-03-01 | 60/0 | DC1+0 | DRY | Pipe | 2024-03-19 | Manoj Sharma | 2024-03-01
114 | 2024-03-01 | 49/4 | DA+3 | Sandy | Pipe | 2024-04-22 | Veerteja Enterprises | 2024-04-01
115 | 2024-03-01 | 49/5 | DA+3 | Sandy | Pipe | 2024-03-21 | Shakti Construction | 2024-03-01
116 | 2024-03-01 | 47/10 | DA+6 | Sandy | Pipe | 2024-03-29 | Bhati Const. | 2024-03-01
117 | 2024-03-01 | 47/9 | DA+3 | Sandy | Pipe | 2024-03-29 | Bhati Const. | 2024-03-01
118 | 2024-03-01 | 47/8 | DA+0 | Sandy | Pipe | 2024-03-29 | Bhati Const. | 2024-03-01
119 | 2024-03-01 | 47/7 | DA+3 | Sandy | Pipe | 2024-04-02 | Bhati Const. | 2024-04-01
120 | 2024-04-01 | 50/9 | DA+0 | Sandy | Pipe | 2024-04-19 | Shakti Construction | 2024-04-01
121 | 2024-04-01 | 48/0 | DC2+0 | Sandy | Pipe | 2024-04-07 | Bhati Const. | 2024-04-01
122 | 2024-04-01 | 50/10 | DA+0 | Sandy | Pipe | 2024-04-19 | Shakti Construction | 2024-04-01
123 | 2024-04-01 | 51/1 | DA+0 | Sandy | Pipe | 2024-04-19 | Shakti Construction | 2024-04-01
124 | 2024-04-01 | 48/1 | DA+9 | Sandy | Pipe | 2024-04-16 | Veerteja Enterprises | 2024-04-01
125 | 2024-04-01 | 50/8 | DA+9 | Sandy | Pipe | 2024-04-20 | Shakti Construction | 2024-04-01
126 | 2024-04-01 | 49/1 | DA+0 | Sandy | Pipe | 2024-04-22 | Veerteja Enterprises | 2024-04-01
127 | 2024-05-01 | 49/0 | DD45+0 | Sandy | Pipe | 2024-05-03 | Veerteja Enterprises | 2024-05-01
128 | 2024-05-01 | 43/6 | DA+3 | Sandy | Pipe | 2024-05-09 | Bande Bharat Group | 2024-05-01
129 | 2024-05-01 | 8/7 | DB1+0 | DRY | Pipe | 2024-05-23 | Mateshwari Const. | 2024-05-01
130 | 2024-05-01 | 50/7 | DA+0 | Sandy | Pipe | 2024-05-31 | Veerteja Enterprises | 2024-05-01
131 | 2024-05-01 | 8/10 | DA+3 | DFR | CP | 2024-05-31 | Mateshwari Const. | 2024-05-01
132 | 2024-05-01 | 50/1 | DA+6 | Sandy | Pipe | 2024-05-31 | Veerteja Enterprises | 2024-05-01
133 | 2024-05-01 | 47/6 | DA+3 | Sandy | Pipe | 2024-06-08 | Bhati Const. | 2024-06-01
134 | 2024-05-01 | 52/3 | DA+9 | Sandy | Pipe | 2024-05-23 | Sb Mehar Const. | 2024-05-01
135 | 2024-05-01 | 47/2 | DA+9 | Sandy | Pipe | 2024-05-28 | Bhati Const. | 2024-05-01
136 | 2024-05-01 | 10/14 | DA+3 | DRY | Pipe | 2024-05-31 | Mateshwari Const. | 2024-05-01
137 | 2024-05-01 | 10/19 | DA+0 | DRY | Pipe | 2024-05-31 | Jai Bhawani Construction | 2024-05-01
138 | 2024-05-01 | 50/4 | DA+9 | Sandy | Pipe | 2024-02-03 | Veerteja Enterprises | 2024-02-01
139 | 2024-05-01 | 51/2 | DA+0 | Sandy | Pipe | 2024-05-31 | Sb Mehar Const. | 2024-05-01
140 | 2024-05-01 | 47/5 | DA+0 | Sandy | Pipe | 2024-06-08 | Bhati Const. | 2024-06-01
141 | 2024-05-01 | 50/2 | DA+9 | Sandy | Pipe | 2024-02-04 | Veerteja Enterprises | 2024-02-01
142 | 2024-06-01 | 10/11 | DA+3 | DRY | Pipe | 2024-06-18 | Mateshwari Const. | 2024-06-01
143 | 2024-06-01 | 10/18 | DA+3 | DFR | CP | 2024-06-30 | Jai Bhawani Construction | 2024-06-01
144 | 2024-06-01 | 10/13 | DA+3 | DRY | Pipe | 2024-06-19 | Mateshwari Const. | 2024-06-01
145 | 2024-06-01 | 47/3 | DA+9 | Sandy | Pipe | 2024-06-08 | Bhati Const. | 2024-06-01
146 | 2024-06-01 | 51/0 | DC2+0 | Sandy | Pipe | 2024-06-11 | Sb Mehar Const. | 2024-06-01
147 | 2024-06-01 | 10/17 | DA+3 | DFR | CP | 2024-06-18 | Jai Bhawani Construction | 2024-06-01
148 | 2024-06-01 | 53/7 | DA+3 | Sandy | Pipe | 2024-07-02 | Bhati Const. | 2024-07-01
149 | 2024-06-01 | 10/8 | DA+3 | DFR | CP | 2024-06-20 | Mateshwari Const. | 2024-06-01
150 | 2024-06-01 | 10/12 | DB1+0 | DRY | Pipe | 2024-07-10 | Mateshwari Const. | 2024-07-01
151 | 2024-07-01 | 15/1 | DA+3 | DRY | Pipe | 2024-07-13 | Om Enterprise | 2024-07-01
152 | 2024-07-01 | 10/20 | DA+3 | DFR | CP | 2024-07-13 | Jai Bhawani Construction | 2024-07-01
153 | 2024-07-01 | 11A/5 | DA+3 | DRY | Pipe | 2024-08-26 | Punia Construction | 2024-08-01
154 | 2024-07-01 | 10/21 | DA+3 | DFR | CP | 2024-08-26 | Jai Bhawani Construction | 2024-08-01
155 | 2024-07-01 | 18/1 | DA+0 | DRY | Pipe | 2024-07-18 | J.P. Infra | 2024-07-01
156 | 2024-07-01 | 15/0 | DC1+0 | DRY | Pipe | 2024-07-16 | Om Enterprise | 2024-07-01
157 | 2024-07-01 | 14A/1 | DA+3 | DRY | Pipe | 2024-07-22 | Majisa Construction | 2024-07-01
158 | 2024-07-01 | 50/0 | DB2+0 | Sandy | Pipe | 2024-08-03 | Veerteja Enterprises | 2024-08-01
159 | 2024-07-01 | 11A/6 | DA+6 | DRY | Pipe | 2024-08-26 | Punia Construction | 2024-08-01
160 | 2024-07-01 | 10/6 | DA+0 | DFR | CP | 2024-09-01 | Jai Bhawani Construction | 2024-09-01
161 | 2024-07-01 | 16/0 | DC1+0 | DRY | Pipe | 2024-07-22 | Majisa Construction | 2024-07-01
162 | 2024-07-01 | 58/0 | DC1+3 | DFR | CP | 2024-07-30 | Bhati Const. | 2024-07-01
163 | 2024-07-01 | 18/0 | DC2+0 | DRY | Pipe | 2024-07-31 | J.P. Infra | 2024-07-01
164 | 2024-07-01 | 11/5 | DA+0 | DFR | CP | 2024-08-26 | Mci | 2024-08-01
165 | 2024-08-01 | 10/3 | DA+0 | DFR | CP | 2024-08-07 | Jai Bhawani Construction | 2024-08-01
166 | 2024-08-01 | 11A/7 | DA+9 | Sandy | Pipe | 2024-09-08 | Punia Construction | 2024-09-01
167 | 2024-08-01 | 18/2 | DA+0 | DRY | Pipe | 2024-09-07 | Vibe Infra | 2024-09-01
168 | 2024-08-01 | 17/3 | DA+0 | DRY | Pipe | 2024-09-07 | J.P. Infra | 2024-09-01
169 | 2024-08-01 | 57/7 | DA+3 | DFR | CP | 2024-08-12 | Bhati Const. | 2024-08-01
170 | 2024-08-01 | 16/3 | DA+3 | DRY | Pipe | 2024-09-07 | Majisa Construction | 2024-09-01
171 | 2024-08-01 | 43/9 | DA+9 | Sandy | Pipe | 2024-08-27 | N.R. Enterprises | 2024-08-01
172 | 2024-08-01 | 17/5 | DA+3 | DRY | Pipe | 2024-09-07 | J.P. Infra | 2024-09-01
173 | 2024-08-01 | 11A/2 | DA+0 | DRY | Pipe | 2024-08-18 | R.K. Construction | 2024-08-01
174 | 2024-08-01 | 16/4 | DA+0 | DRY | Pipe | 2024-08-24 | Om Enterprise | 2024-08-01
175 | 2024-08-01 | 18/3 | DA+0 | DRY | Pipe | 2024-09-07 | Vibe Infra | 2024-09-01
176 | 2024-08-01 | 17/4 | DA+3 | DRY | Pipe | 2024-09-05 | J.P. Infra | 2024-09-01
177 | 2024-08-01 | 10/9 | DA+0 | DRY | Pipe | 2024-08-31 | A.B. Construction | 2024-08-01
178 | 2024-08-01 | 11A/8 | DA+6 | Sandy | Pipe | 2024-09-08 | Punia Construction | 2024-09-01
179 | 2024-08-01 | 11A/9 | DA+3 | DRY | Pipe | 2024-09-08 | Punia Construction | 2024-09-01
180 | 2024-08-01 | 43/8 | DA+9 | Sandy | Pipe | 2024-08-27 | N.R. Enterprises | 2024-08-01
181 | 2024-08-01 | 18/4 | DA+0 | DRY | Pipe | 2024-09-03 | Vibe Infra | 2024-09-01
182 | 2024-08-01 | 59/2 | DA+3 | DFR | CP | 2024-08-23 | Bhati Const. | 2024-08-01
183 | 2024-08-01 | 16/2 | DA+0 | DRY | Pipe | 2024-08-31 | Om Enterprise | 2024-08-01
184 | 2024-08-01 | 11A/0 | DB1+0 | DRY | Pipe | 2024-08-26 | Mci | 2024-08-01
185 | 2024-08-01 | 50/6 | DA+9 | Sandy | Pipe | 2024-09-29 | Kalpana Const. | 2024-09-01
186 | 2024-08-01 | 53/8 | DA+3 | Sandy | Pipe | 2024-09-03 | Bhati Const. | 2024-09-01
187 | 2024-08-01 | 17/1 | DA+3 | DRY | Pipe | 2024-08-30 | J.P. Infra | 2024-08-01
188 | 2024-08-01 | 43/7 | DA+3 | Sandy | Pipe | 2024-08-30 | N.R. Enterprises | 2024-08-01
189 | 2024-08-01 | 16/5 | DA+3 | DRY | Pipe | 2024-08-31 | Majisa Construction | 2024-08-01
190 | 2024-08-01 | 19/0 | DC2+0 | DRY | Pipe | 2024-08-31 | Vibe Infra | 2024-08-01
191 | 2024-09-01 | 11A/1 | DA+3 | DRY | Pipe | 2024-09-01 | Mci | 2024-09-01
192 | 2024-09-01 | 19/1 | DA+0 | DRY | Pipe | 2024-09-04 | Vibe Infra | 2024-09-01
193 | 2024-09-01 | 17/2 | DA+6 | DRY | Pipe | 2024-09-04 | J.P. Infra | 2024-09-01
194 | 2024-09-01 | 13/2 | DA+3 | DRY | Pipe | 2024-09-30 | Punia Construction | 2024-09-01
195 | 2024-09-01 | 43/5 | DA+3 | DRY | Pipe | 2024-09-06 | N.R. Enterprises | 2024-09-01
196 | 2024-09-01 | 53/6 | DA+6 | Sandy | Pipe | 2024-09-13 | Bhati Const. | 2024-09-01
197 | 2024-09-01 | 16/1 | DA+0 | DRY | Pipe | 2024-09-10 | Sidhi Vinayak | 2024-09-01
198 | 2024-09-01 | 11A/4 | DA+3 | DRY | Pipe | 2024-09-30 | Punia Construction | 2024-09-01
199 | 2024-09-01 | 54/1 | DA+3 | Sandy | Pipe | 2024-09-14 | Bhati Const. | 2024-09-01
200 | 2024-09-01 | 50/3 | DA+6 | Sandy | Pipe | 2024-09-29 | Kalpana Const. | 2024-09-01
201 | 2024-09-01 | 73/0 | DB2+0 | DRY | Pipe | 2024-09-15 | Shree Shyam Const. | 2024-09-01
202 | 2024-09-01 | 73/9 | DA+0 | DRY | Pipe | 2024-09-19 | Shakti Construction | 2024-09-01
203 | 2024-09-01 | 73/2 | DA+0 | DRY | Pipe | 2024-09-16 | Shree Shyam Const. | 2024-09-01
204 | 2024-09-01 | 25/0 | DC1+6 | DRY | Pipe | 2024-09-26 | J.P. Infra | 2024-09-01
205 | 2024-09-01 | 54/2 | DA+3 | Sandy | Pipe | 2024-09-14 | Bhati Const. | 2024-09-01
206 | 2024-09-01 | 14A/2 | DA+0 | DRY | Pipe | 2024-09-30 | Sidhi Vinayak | 2024-09-01
207 | 2024-09-01 | 10/4 | DA+3 | DFR | CP | 2024-09-30 | A.B. Construction | 2024-09-01
208 | 2024-09-01 | 73/1 | DA+0 | DRY | Pipe | 2024-09-19 | Shree Shyam Const. | 2024-09-01
209 | 2024-09-01 | 14/0 | DC2+0 | Sandy | Pipe | 2024-09-26 | Om Enterprise | 2024-09-01
210 | 2024-09-01 | 11A/3 | DA+3 | DRY | Pipe | 2024-09-23 | R.K. Construction | 2024-09-01
211 | 2024-09-01 | 73/6 | DA+0 | DRY | Pipe | 2024-09-22 | Shree Shyam Const. | 2024-09-01
212 | 2024-09-01 | 42/3 | DA+0 | Sandy | Pipe | 2024-09-22 | Mahadev Construction | 2024-09-01
213 | 2024-09-01 | 69/1 | DA+3 | DRY | Pipe | 2024-09-27 | Bhati Const. | 2024-09-01
214 | 2024-09-01 | 25/4 | DA+0 | Sandy | Pipe | 2024-09-30 | J.P. Infra | 2024-09-01
215 | 2024-09-01 | 73/5 | DA+0 | DRY | Pipe | 2024-10-07 | Shree Shyam Const. | 2024-10-01
216 | 2024-09-01 | 43/4 | DA+3 | Sandy | Pipe | 2024-09-30 | N.R. Enterprises | 2024-09-01
217 | 2024-09-01 | 13/1 | DA+9 | DRY | Pipe | 2024-09-30 | Punia Construction | 2024-09-01
218 | 2024-09-01 | 40/2 | DA+3 | Sandy | Pipe | 2024-09-30 | D.R. Construction | 2024-09-01
219 | 2024-09-01 | 73/8 | DA+3 | DRY | Pipe | 2024-10-07 | Shakti Construction | 2024-10-01
220 | 2024-09-01 | 59/1 | DA+3 | DRY | Pipe | 2024-10-01 | Bhati Const. | 2024-10-01
221 | 2024-09-01 | 19/2 | DA+0 | DRY | Pipe | 2024-09-30 | Vibe Infra | 2024-09-01
222 | 2024-09-01 | 72/2 | DA+0 | DRY | Pipe | 2024-10-07 | Shree Shyam Const. | 2024-10-01
223 | 2024-09-01 | 17/0 | DB2+3 | DRY | Pipe | 2024-09-30 | Om Enterprise | 2024-09-01
224 | 2024-09-01 | 66/0 | DC2+6 | DRY | Pipe | 2024-09-27 | Bhati Const. | 2024-09-01
225 | 2024-09-01 | 59/11 | DA+6 | DFR | CP | 2024-09-28 | Mahadev Eng | 2024-09-01
226 | 2024-09-01 | 19/3 | DA+0 | DRY | Pipe | 2024-10-14 | Vibe Infra | 2024-10-01
227 | 2024-09-01 | 43/3 | DA+0 | DRY | Pipe | 2024-09-30 | Parsuram Sai | 2024-09-01
228 | 2024-09-01 | 73/3 | DA+0 | DRY | Pipe | 2024-10-07 | Awadh Const. | 2024-10-01
229 | 2024-10-01 | 73/7 | DA+0 | DRY | Pipe | 2024-10-07 | Shakti Construction | 2024-10-01
230 | 2024-10-01 | 59/0 | DC2+0 | DRY | Pipe | 2024-10-05 | Bhati Const. | 2024-10-01
231 | 2024-10-01 | 67/0 | DC1+9 | DRY | Pipe | 2024-10-10 | Bhati Const. | 2024-10-01
232 | 2024-10-01 | 42/5 | DA+9 | Sandy | Pipe | 2024-10-28 | Mahadev Construction | 2024-10-01
233 | 2024-10-01 | 43/0 | DB1+0 | Sandy | Pipe | 2024-10-09 | N.R. Enterprises | 2024-10-01
234 | 2024-10-01 | 25/3 | DA+0 | Sandy | Pipe | 2024-10-08 | J.P. Infra | 2024-10-01
235 | 2024-10-01 | 69/0 | DB2+0 | DFR | CP | 2024-10-16 | Bhati Const. | 2024-10-01
236 | 2024-10-01 | 73/4 | DA+0 | DRY | Pipe | 2024-10-10 | Shree Shyam Const. | 2024-10-01
237 | 2024-10-01 | 22/13 | DA+6 | Sandy | Pipe | 2024-12-09 | Rbm | 2024-12-01
238 | 2024-10-01 | 74/0 | DB2+0 | Sandy | Pipe | 2024-10-16 | Shakti Construction | 2024-10-01
239 | 2024-10-01 | 25/1 | DA+3 | DRY | Pipe | 2024-12-17 | J.P. Infra | 2024-12-01
240 | 2024-10-01 | 43/2 | DA+0 | Sandy | Pipe | 2024-12-21 | Parsuram Sai | 2024-12-01
241 | 2024-10-01 | 72/3 | DA+3 | DRY | Pipe | 2024-10-18 | Shree Shyam Const. | 2024-10-01
242 | 2024-10-01 | 43/11 | DA+3 | Sandy | Pipe | 2024-12-17 | Jitendra Enterprises | 2024-12-01
243 | 2024-10-01 | 13/0 | DD60+3 | DRY | Pipe | 2025-01-12 | R.K. Construction | 2025-01-01
244 | 2024-10-01 | 71/7 | DA+3 | DRY | Pipe | 2024-10-22 | Shree Shyam Const. | 2024-10-01
245 | 2024-10-01 | 59/4 | DA+3 | DFR | CP | 2024-10-23 | Bhati Const. | 2024-10-01
246 | 2024-10-01 | 22/12 | DA+3 | Sandy | Pipe | 2024-12-09 | Rbm | 2024-12-01
247 | 2024-10-01 | 42/1 | DA+6 | Sandy | Pipe | 2024-12-18 | N.R. Enterprises | 2024-12-01
248 | 2024-10-01 | 71/6 | DA+0 | DRY | Pipe | 2024-10-22 | Shree Shyam Const. | 2024-10-01
249 | 2024-10-01 | 49/7 | DA+0 | Sandy | Pipe | 2024-10-23 | Kalpana Const. | 2024-10-01
250 | 2024-10-01 | 25/2 | DA+0 | DRY | Pipe | 2024-12-17 | J.P. Infra | 2024-12-01
250 | 2024-10-01 | 13/3 | DA+3 | Sandy | Pipe |  | Punia Construction
251 | 2024-10-01 | 22/7 | DA+0 | Sandy | Pipe | 2024-12-09 | Rbm | 2024-12-01
252 | 2024-10-01 | 22/3 | DA+9 | Sandy | Pipe | 2024-12-09 | J.P. Infra | 2024-12-01
253 | 2024-10-01 | 43/1 | DA+3 | Sandy | Pipe | 2024-12-21 | Parsuram Sai | 2024-12-01
254 | 2024-11-01 | 42/6 | DA+0 | Sandy | Pipe | 2024-12-04 | D.R. Construction | 2024-12-01
255 | 2024-11-01 | 2/4 | DA+3 | Sandy | Pipe | 2024-11-17 | Laxmi Enterprises | 2024-11-01
256 | 2024-11-01 | 42/2 | DA+6 | Sandy | Pipe | 2024-12-01 | D.R. Construction | 2024-12-01
257 | 2024-11-01 | 22/8 | DB1+0 | Sandy | Pipe | 2024-12-09 | Rbm | 2024-12-01
258 | 2024-11-01 | 22/2 | DA+6 | Sandy | Pipe | 2024-12-09 | J.P. Infra | 2024-12-01
259 | 2024-11-01 | 54/0 | DB1+6 | Sandy | Pipe | 2024-11-21 | Bhati Const. | 2024-11-01
260 | 2024-11-01 | 65/8 | DA+0 | DRY | Pipe | 2024-12-06 | Bhati Const. | 2024-12-01
261 | 2024-11-01 | 42/0 | DC1+0 | Sandy | Pipe | 2024-12-04 | D.R. Construction | 2024-12-01
262 | 2024-11-01 | 65/7 | DA+0 | DRY | Pipe | 2024-12-06 | Bhati Const. | 2024-12-01
263 | 2024-12-01 | 2/3 | DA+3 | Sandy | Pipe | 2024-12-13 | Laxmi Enterprise | 2024-12-01
264 | 2024-12-01 | 22/4 | DA+9 | Sandy | Pipe | 2024-12-09 | Jp Infra | 2024-12-01
265 | 2024-12-01 | 6/1 | DA+0 | DFR | CP | 2024-12-19 | H.S. Engineering | 2024-12-01
266 | 2024-12-01 | 12/0 | DD60+0 | DRY | Pipe | 2025-01-04 | Vibe Infra Power | 2025-01-01
267 | 2024-12-01 | 22/5 | DA+9 | DRY | Pipe | 2024-12-21 | S.D. Infra | 2024-12-01
268 | 2024-12-01 | 41/2 | DA+0 | Sandy | Pipe | 2024-12-16 | D.R. Construction | 2024-12-01
269 | 2024-12-01 | 2/5 | DA+3 | Sandy | Pipe | 2024-12-28 | Sri Nagana Ray Enterprise | 2024-12-01
270 | 2024-12-01 | 22/9 | DA+6 | Sandy | Pipe | 2025-01-06 | Rbm | 2025-01-01
271 | 2024-12-01 | 70/8 | DA+3 | DRY | Pipe | 2025-02-01 | Tantray Construction | 2025-02-01
272 | 2024-12-01 | 72/1 | DA+3 | DRY | Pipe | 2025-02-01 | Meer Const | 2025-02-01
273 | 2024-12-01 | 70/7 | DA+3 | DRY | Pipe | 2025-02-01 | Tantray Construction | 2025-02-01
274 | 2024-12-01 | 71/8 | DA+3 | DRY | Pipe | 2025-02-01 | Meer Const | 2025-02-01
275 | 2024-12-01 | 52/1 | DA+6 | Sandy | Pipe | 2025-02-17 | Tantray Construction | 2025-02-01
276 | 2024-12-01 | 70/9 | DA+3 | DRY | Pipe | 2025-02-01 | Tantray Construction | 2025-02-01
277 | 2024-12-01 | 6/2 | DA+0 | DFR | CP | 2025-01-05 | Hs Engineering | 2025-01-01
278 | 2024-12-01 | 72/0 | DB2+3 | DRY | Pipe | 2025-01-28 | Meer Const | 2025-01-01
279 | 2024-12-01 | 70/6 | DA+3 | DRY | Pipe | 2025-01-27 | Tantray Construction | 2025-01-01
280 | 2024-12-01 | 2/6 | DA+3 | Sandy | Pipe | 2025-01-06 | Sri Nagana Ray Enterprise | 2025-01-01
281 | 2024-12-01 | 71/4 | DA+3 | DRY | Pipe | 2025-01-28 | Meer Const | 2025-01-01
282 | 2024-12-01 | 52/2 | DA+6 | Sandy | Pipe | 2025-02-17 | Tantray Construction | 2025-02-01
283 | 2024-12-01 | 70/10 | DA+3 | DRY | Pipe | 2025-02-01 | Tantray Construction | 2025-02-01
284 | 2024-12-01 | 2/2 | DA+3 | Sandy | Pipe | 2025-01-06 | Laxmi Enterprises | 2025-01-01
285 | 2024-12-01 | 71/5 | DA+3 | DRY | Pipe | 2025-02-01 | Meer Const | 2025-02-01
286 | 2024-12-01 | 70/11 | DA+3 | DRY | Pipe | 2025-03-29 | Tantray Construction | 2025-03-01
287 | 2024-12-01 | 53/2 | DA+0 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
288 | 2024-12-01 | 36/0 | DB2+0 | Sandy | Pipe | 2024-12-30 | Parsuram Sahi | 2024-12-01
289 | 2024-12-01 | 71/3 | DA+6 | DRY | Pipe | 2025-01-28 | Meer Const | 2025-01-01
290 | 2024-12-01 | 52/4 | DA+9 | Sandy | Pipe | 2025-02-17 | Tantray Construction | 2025-02-01
291 | 2024-12-01 | 10/5 | DA+3 | DRY | Pipe | 2024-12-20 | Jsr Infrastructure | 2024-12-01
292 | 2024-12-01 | 35/4 | DA+0 | DRY | Pipe | 2025-01-03 | Parsuram Sahi | 2025-01-01
293 | 2024-12-01 | 71/0 | DB2+3 | DRY | Pipe | 2025-01-27 | Tantray Construction | 2025-01-01
294 | 2025-01-01 | 22/11 | DA+6 | Sandy | Pipe | 2025-01-07 | Rbm | 2025-01-01
295 | 2025-01-01 | 71/2 | DA+3 | DRY | Pipe | 2025-01-27 | Meer Const | 2025-01-01
296 | 2025-01-01 | 71/1 | DA+3 | DRY | Pipe | 2025-01-27 | Meer Const | 2025-01-01
297 | 2025-01-01 | 54/3 | DA+6 | Sandy | Pipe | 2025-01-07 | Tantray Construction | 2025-01-01
298 | 2025-01-01 | 44/1 | DA+0 | Sandy | Pipe | 2025-03-16 | Tantray Construction | 2025-03-01
299 | 2025-01-01 | 44/2 | DA+0 | Sandy | Pipe | 2025-03-16 | Tantray Construction | 2025-03-01
300 | 2025-01-01 | 8/9 | DA+3 | DFR | CP | 2025-01-09 | Jsr Infrastructure | 2025-01-01
301 | 2025-01-01 | 53/1 | DA+9 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
302 | 2025-01-01 | 70/3 | DA+3 | DRY | Pipe | 2025-01-25 | Meer Const | 2025-01-01
303 | 2025-01-01 | 54/4 | DA+9 | Sandy | Pipe | 2025-01-10 | Tantray Construction | 2025-01-01
304 | 2025-01-01 | 45/0 | DC2+0 | Sandy | Pipe | 2025-02-26 | Nadeem | 2025-02-01
305 | 2025-01-01 | 44/11 | DA+0 | Sandy | Pipe | 2025-02-27 | Nadeem | 2025-02-01
306 | 2025-01-01 | 53/0 | DB2+9 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
307 | 2025-01-01 | 44/10 | DB1+9 | Sandy | Pipe | 2025-02-27 | Nadeem | 2025-02-01
308 | 2025-01-01 | 44/4 | DA+9 | Sandy | Pipe | 2025-02-28 | Tantray Construction | 2025-02-01
309 | 2025-01-01 | 70/4 | DA+3 | DRY | Pipe | 2025-01-25 | Meer Const | 2025-01-01
310 | 2025-01-01 | 34/1 | DA+9 | Sandy | Pipe | 2025-01-16 | Ymk Construction | 2025-01-01
311 | 2025-01-01 | 70/5 | DA+3 | DRY | Pipe | 2025-01-27 | Meer Const | 2025-01-01
312 | 2025-01-01 | 53/3 | DA+6 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
313 | 2025-01-01 | 35/2 | DB1+0 | Sandy | Pipe | 2025-01-19 | Parsuram Sahi | 2025-01-01
314 | 2025-01-01 | 68/0 | DD45+0 | DRY | Pipe | 2025-02-19 | Bhati Const. | 2025-02-01
315 | 2025-01-01 | 1A/1 | DA+6 | DFR | CP | 2025-01-21 | Jsr Infrastructure | 2025-01-01
316 | 2025-01-01 | 53/4 | DA+0 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
317 | 2025-01-01 | 52/0 | DC2+0 | Sandy | Pipe | 2025-02-17 | Tantray Construction | 2025-02-01
318 | 2025-01-01 | 44/5 | DA+9 | Sandy | Pipe | 2025-02-28 | Tantray Construction | 2025-02-01
319 | 2025-01-01 | 2/0 | DC1+0 | DRY | Pipe | 2025-01-21 | Laxmi Enterprises | 2025-01-01
320 | 2025-01-01 | 44/9 | DA+9 | Sandy | Pipe | 2025-02-27 | Iqbal | 2025-02-01
321 | 2025-01-01 | 70/1 | DA+3 | DRY | Pipe | 2025-01-25 | Meer Const | 2025-01-01
322 | 2025-01-01 | 70/2 | DA+3 | DRY | Pipe | 2025-02-19 | Bhati Const. | 2025-02-01
323 | 2025-01-01 | 44/6 | DB1+3 | Sandy | Pipe | 2025-02-28 | Tantray Construction | 2025-02-01
324 | 2025-01-01 | 55/2 | DA+0 | WFR | Pipe | 2025-02-07 | Meer Const | 2025-02-01
325 | 2025-01-01 | 47/4 | DA+3 | Sandy | Pipe | 2025-01-29 | Tantray Construction | 2025-01-01
326 | 2025-01-01 | 50/5 | DA+9 | Sandy | Pipe | 2025-01-23 | Om Const | 2025-01-01
327 | 2025-01-01 | 1A/4 | DA+3 | DFR | CP | 2025-01-28 | Naganaray Enterprise | 2025-01-01
328 | 2025-01-01 | 28/6 | DA+6 | Sandy | Pipe | 2025-01-29 | Vishwakarma Construction | 2025-01-01
329 | 2025-01-01 | 70/0 | DC1+0 | DRY | Pipe | 2025-01-25 | Meer Const | 2025-01-01
330 | 2025-01-01 | 44/7 | DA+9 | Sandy | Pipe | 2025-02-18 | Iqbal | 2025-02-01
331 | 2025-01-01 | 34/2 | DA+6 | Sandy | Pipe | 2025-01-27 | Ymk Construction | 2025-01-01
332 | 2025-01-01 | 65/10 | DA+0 | DRY | Pipe | 2025-02-19 | Bhati Const. | 2025-02-01
333 | 2025-01-01 | 57/1 | DA+0 | Sandy | Pipe | 2025-01-29 | Meer Const | 2025-01-01
334 | 2025-01-01 | 28/5 | DA+9 | Sandy | Pipe | 2025-01-31 | Vishwakarma Construction | 2025-01-01
335 | 2025-01-01 | 35/0 | DB2+6 | Sandy | Pipe | 2025-01-29 | Parsuram Sahi | 2025-01-01
336 | 2025-01-01 | 44/3 | DA+0 | Sandy | Pipe | 2025-02-18 | Tantray Construction | 2025-02-01
337 | 2025-01-01 | 1A/3 | DA+0 | DRY | Pipe | 2025-01-31 | Jsr Infrastructure | 2025-01-01
338 | 2025-01-01 | 55/8 | DA+6 | Sandy | Pipe | 2025-02-03 | Meer Const | 2025-02-01
339 | 2025-01-01 | 1A/2 | DA+0 | DRY | Pipe | 2025-02-03 | Jsr Infrastructure | 2025-02-01
340 | 2025-01-01 | 44/8 | DCT+0 | Sandy | Pipe | 2025-02-28 | Iqbal | 2025-02-01
341 | 2025-02-01 | 34/0 | DB2+0 | DRY | Pipe | 2025-02-04 | Ymk Construction | 2025-02-01
342 | 2025-02-01 | 28/8 | DA+3 | Sandy | Pipe | 2025-02-04 | Vishwakarma Construction | 2025-02-01
343 | 2025-02-01 | 47/1 | DA+3 | Sandy | Pipe | 2025-01-29 | Tantray Construction | 2025-01-01
344 | 2025-02-01 | 1A/5 | DA+0 | DRY | Pipe | 2025-02-05 | Jsr Infrastructure | 2025-02-01
345 | 2025-02-01 | 28/7 | DA+3 | Sandy | Pipe | 2025-02-07 | Vishwakarma Construction | 2025-02-01
346 | 2025-02-01 | 33/1 | DA+0 | DRY | Pipe | 2025-02-10 | Ymk Construction | 2025-02-01
347 | 2025-02-01 | 28/4 | DA+0 | Sandy | Pipe | 2025-02-10 | Vishwakarma Construction | 2025-02-01
348 | 2025-02-01 | 1A/6 | DA+0 | Sandy | Pipe | 2025-02-10 | Jsr Infrastructure | 2025-02-01
349 | 2025-02-01 | 35/3 | DB1+6 | Sandy | Pipe | 2025-02-13 | Parsuram Sahi | 2025-02-01
350 | 2025-02-01 | 45/1 | DA+9 | Sandy | Pipe | 2025-02-26 | Tantray Construction | 2025-02-01
351 | 2025-02-01 | 54/5 | DA+9 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
352 | 2025-02-01 | 32/3 | DA+0 | Sandy | Pipe | 2025-02-14 | Ymk Construction | 2025-02-01
353 | 2025-02-01 | 28/3 | DA+0 | DFR | CP | 2025-02-14 | Vishwakarma Construction | 2025-02-01
354 | 2025-02-01 | 32/4 | DA+0 | Sandy | Pipe | 2025-02-16 | Ymk Construction | 2025-02-01
355 | 2025-02-01 | 28/2 | DA+0 | DFR | CP | 2025-02-16 | Vishwakarma Construction | 2025-02-01
356 | 2025-02-01 | 32/2 | DA+3 | DRY | Pipe | 2025-03-04 | Ymk Construction | 2025-03-01
357 | 2025-02-01 | 29/0 | DB1+0 | DRY | Pipe | 2025-02-20 | Vishwakarma Construction | 2025-02-01
358 | 2025-02-01 | 55/0 | DB1+6 | Sandy | Pipe | 2025-02-23 | Meer Const | 2025-02-01
359 | 2025-02-01 | 44/0 | DB1+3 | Sandy | Pipe | 2025-03-16 | Om Const | 2025-03-01
360 | 2025-02-01 | 30/0 | DC1+0 | DRY | Pipe | 2025-02-23 | Vishwakarma Construction | 2025-02-01
361 | 2025-02-01 | 33/0 | DC1+0 | DRY | Pipe | 2025-02-24 | Ymk Construction | 2025-02-01
362 | 2025-02-01 | 1A/0 | DD60+0 | DRY | Pipe | 2025-02-24 | Jsr Infrastructure | 2025-02-01
363 | 2025-02-01 | 30/1 | DA+0 | Sandy | Pipe | 2025-02-25 | Vishwakarma Construction | 2025-02-01
364 | 2025-02-01 | 43/10 | DA+3 | Sandy | Pipe | 2025-03-16 | Om Const | 2025-03-01
365 | 2025-02-01 | 29/4 | DA+6 | DRY | Pipe | 2025-03-01 | Vishwakarma Construction | 2025-03-01
366 | 2025-02-01 | 29/1 | DA+3 | DRY | Pipe | 2025-03-03 | Vishwakarma Construction | 2025-03-01
367 | 2025-02-01 | 55/1 | DA+0 | WFR | Pipe | 2025-03-02 | Bhati | 2025-03-01
368 | 2025-03-01 | 35/5 | DA+0 | Sandy | Pipe | 2025-03-06 | Parsuram Sahi | 2025-03-01
369 | 2025-03-01 | 32/1 | DA+3 | Sandy | Pipe | 2025-03-06 | Ymk | 2025-03-01
370 | 2025-03-01 | 30/3 | DA+3 | Sandy | Pipe | 2025-03-06 | Vishwakarma Construction | 2025-03-01
371 | 2025-03-01 | 30/2 | DA+0 | Sandy | Pipe | 2025-03-10 | Vishwakarma Construction | 2025-03-01
372 | 2025-03-01 | 1/0 | DD60+0 | DRY | Pipe | 2025-02-24 | Jsr | 2025-02-01
373 | 2025-03-01 | 32/0 | DC1+0 | DRY | Pipe | 2025-03-11 | Ymk | 2025-03-01
374 | 2025-03-01 | 29/2 | DA+3 | DRY | Pipe | 2025-03-12 | Vishwakarma Construction | 2025-03-01
375 | 2025-03-01 | 1A/7 | DA+3 | Sandy | Pipe | 2025-03-11 | Jsr | 2025-03-01
376 | 2025-03-01 | 29/3 | DA+0 | Sandy | Pipe | 2025-03-14 | Vishwakarma Construction | 2025-03-01
377 | 2025-03-01 | 31/2 | DA+0 | DRY | Pipe | 2025-03-14 | Ymk | 2025-03-01
378 | 2025-03-01 | 31/1 | DA+0 | DRY | Pipe | 2025-03-15 | Ymk | 2025-03-01
379 | 2025-03-01 | 2/1 | DA+3 | Sandy | Pipe | 2025-03-21 | Jsr | 2025-03-01
380 | 2025-03-01 | 34/3 | DA+0 | Sandy | Pipe | 2025-03-28 | Ymk | 2025-03-01
381 | 2025-03-01 | 26/7 | DA+0 | DFR | CP | 2025-03-28 | Jsr | 2025-03-01
382 | 2025-03-01 | 37/3 | DA+0 | Sandy | Pipe | 2025-04-03 | Vishwakarma Construction | 2025-04-01
383 | 2025-03-01 | 34/4 | DA+0 | Sandy | Pipe | 2025-04-04 | Ymk | 2025-04-01
384 | 2025-03-01 | 57/0 | DD60+25 | Sandy | Pipe | 2025-04-07 | Bhati | 2025-04-01
385 | 2025-04-01 | 35/1 | DA+9 | Sandy | Pipe | 2025-04-06 | Ymk | 2025-04-01
386 | 2025-04-01 | 46/0 | DD60+25 | Sandy | Pipe | 2025-04-10 | Om Const | 2025-04-01
387 | 2025-04-01 | 38/4 | DA+9 | Sandy | Pipe | 2025-04-15 | Vishwakarma Construction | 2025-04-01
388 | 2025-04-01 | 56/0 | DD60+25 | Sandy | Pipe | 2025-04-11 | Bhati | 2025-04-01
389 | 2025-04-01 | 39/0 | DB2+6 | Sandy | Pipe | 2025-04-15 | Vishwakarma Construction | 2025-04-01
390 | 2025-04-01 | 27/3 | DA+3 | DFR | CP | 2025-05-17 | YMK | 2025-05-01
391 | 2025-04-01 | 47/0 | DD60+25 | Sandy | Pipe | 2025-04-17 | Om Const | 2025-04-01
392 | 2025-04-01 | 4/0 | DD60+6 | DRY | Pipe | 2025-05-05 | Jsr | 2025-05-01
393 | 2025-04-01 | 38/2 | DA+6 | Sandy | Pipe | 2025-04-23 | Vishwakarma Construction | 2025-04-01
394 | 2025-04-01 | 27/2 | DA+3 | DFR | CP | 2025-05-19 | YMK | 2025-05-01
395 | 2025-04-01 | 38/1 | DA+0 | Sandy | Pipe | 2025-04-25 | Vishwakarma Construction | 2025-04-01
396 | 2025-04-01 | 38/0 | DB2+6 | Sandy | Pipe | 2025-04-28 | Vishwakarma Construction | 2025-04-01
397 | 2025-04-01 | 39/1 | DA+0 | Sandy | Pipe | 2025-05-01 | Vishwakarma Construction | 2025-05-01
398 | 2025-05-01 | 40/0 | DC2+0 | Sandy | Pipe | 2025-05-18 | Vishwakarma Construction | 2025-05-01
399 | 2025-05-01 | 40/1 | DA+6 | Sandy | Pipe | 2025-05-10 | Vishwakarma Construction | 2025-05-01
400 | 2025-05-01 | 27/6 | DA+0 | Sandy | Pipe | 2025-05-20 | YMK | 2025-05-01
401 | 2025-05-01 | 1A/8 | DA+0 | Sandy | Pipe | 2025-05-17 | Jsr | 2025-05-01
402 | 2025-05-01 | 27/4 | DA+3 | DFR | CP | 2025-05-20 | YMK | 2025-05-01
403 | 2025-05-01 | 38/3 | DA+9 | Sandy | Pipe | 2025-05-20 | Vishwakarma Construction | 2025-05-01
404 | 2025-05-01 | 42/4 | DA+0 | Sandy | Pipe | 2025-05-21 | Vishwakarma Construction | 2025-05-01
405 | 2025-05-01 | 40/3 | DA+3 | Sandy | Pipe | 2025-05-25 | Vishwakarma Construction | 2025-05-01
406 | 2025-05-01 | 21/9 | DA+3 | DFR | CP | 2025-05-27 | M.R. Choudhary | 2025-05-01
407 | 2025-05-01 | 27/7 | DB1+0 | DFR | CP | 2025-05-31 | YMK | 2025-05-01
408 | 2025-05-01 | 4/3 | DA+0 | DRY | Pipe | 2025-05-30 | Nyce Service & Security | 2025-05-01
408 | 2025-05-01 | 2/8 | DA+0 | Sandy | Pipe |  | Jsr
408 | 2025-05-01 | 8/11 | DA+0 | DRY | Pipe |  | Bhati Construction
409 | 2025-06-01 | 41/1 | DB1+9 | Sandy | Pipe | 2025-06-02 | Vishwakarma Construction | 2025-06-01
409 | 2025-06-01 | 30/4 | DA+3 | DRY | Pipe |  | Rabbit bright technology pvt. Ltd.
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | Loc no | TOT | FDN Status | Pipe |  | Gang Name
409 | 0 | 3/0 | DD60+6 | WIP | Pipe |  | Jsr
409 | 0 | 4/1 | DA+0 | WIP | Pipe |  | Jsr
409 | 0 | 2/7 | DA+3 | WIP | Pipe |  | #REF!
409 | 0 | 8/12 | DA+0 | WIP | Pipe |  | Jsr
409 | 0 | 27/0 | DC1+0 | WIP | Pipe |  | Bhati Construction
409 | 0 | 27/1 | DA+3 | WIP | Pipe |  | YMK
409 | 0 | 21/7 | DA+3 | WIP | Pipe |  | YMK
409 | 0 | 21/5 | DA+6 | WIP | Pipe |  | M.R. Choudhary
409 | 0 | 41/0 | DC1+6 | WIP | Pipe |  | M.R. Choudhary
409 | 0 | 19/5 | DA+0 | WIP | Pipe |  | Vishwakarma Construction
409 | 0 | 0 | 0 | 0 |  |  | Shree Ram Construction
409 | 0 | 10/0 | DD60+25 | WIP | Pipe |  | 0
409 | 0 | 10/1 | DA+0 | WIP | Pipe |  | Bhati Construction
409 | 0 | 0 | 0 | 0 |  |  | Bhati Construction
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 30/5 | DA+3 | WIP | Pipe |  | 0
409 | 0 | 0 | 0 | 0 |  |  | Rabbit bright technology pvt. Ltd.
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0
409 | 0 | 0 | 0 | 0 |  |  | 0

## Erection Productivity
Sr no | Item | Unit | Total | Comp Qty | Bal Qty | June'25 |  |  | Remarks
|  |  | Qty | 31.05.25 | 01.06.25 | Plan | WIP | Actual
1 | Erection | Nos | 485 | 222 | 263 | 5 | 2 | 0
2 | Stringing | KM | 191.3 | 43.51 | 147.79 | 3.7 | 5.416 | 0
Gang Wise Output- May'25
Sr. No. | Sub-Contractor Name | WIP |  |  | Start Date | Comp Date | Output -01.06.25 | Output -02.06.25 | Output -03.06.25 | Output -04.06.25 | Output -05.06.25 | Output -06.06.25 | Output -07.06.25 | Output -08.06.25 | Output -09.06.25 | Output -10.06.25 | Output -11.06.25 | Output -12.06.25 | Output -13.06.25 | Output -14.06.25 | Output -15.06.25 | Output -16.06.25 | Output -17.06.25 | Output -18.06.25 | Output -19.06.25 | Output -20.06.25 | Output -21.06.25 | Output -22.06.25 | Output -23.06.25 | Output -24.06.25 | Output -25.06.25 | Output -26.06.25 | Output -27.06.25 | Output -28.06.25 | Output -29.06.25 | Output -30.06.25 | Cumulative Till dated | Status | Manpower
|  | Loc. No. | Type of Tower | Tower Weight | [34 empty] | Plan | Actual | Shotfall
1 | Sonakshi (Manish-2) | 70/6 | DA+3 | 38.848 | 2025-05-19 |  | 0 | 0 | [29 empty] | 1st Section WIP. | 22 | 17 | -5
2
3
4
5
6
7
8
Total |  |  |  | 38.848 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 22 | 17 | -5
Note on AC10: Raghav Ranjan: No work done due to all fitters left the site.
Note on AD10: Raghav Ranjan: No work done due to all fitters left the site.
Note on AE10: Raghav Ranjan: No work done due to all fitters left the site.
Note on AF10: Raghav Ranjan: No work done due to all fitters left the site.
Note on AG10: Raghav Ranjan: No work done due to all fitters left the site.
Note on AH10: Raghav Ranjan: No work done due to all fitters left the site.
Note on AI10: Raghav Ranjan: No work done due to all fitters left the site.
Note on AJ10: Raghav Ranjan: No work done due to all fitters left the site.

## Erection Compiled
Progress Summary'!A1 | [6 empty] | Total As per LOA | 22399.3752
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line | [6 empty] | Total Executed | 9520.6792
List of Completed Erection | [6 empty] | Balance | 12878.6959
Sl.No. | Month Sl.No. | Location No. | Type of tower | Starting Date | Completion Date | Gang Name | Status | Tower Weight
1 | 2024-02-01 | 60/7 | DA+3 | 2024-01-28 | 2024-02-04 | Suraj const | Completed | 38.8476 |  |  | DA+0 | 37.5044
2 | 2024-02-01 | 59/13 | DA+3 | 2024-02-01 | 2024-02-07 | Chinta Devi | Completed | 38.8476 |  |  | DA+3 | 38.8476
3 | 2024-02-01 | 63/6 | DA+3 | 2024-02-03 | 2024-02-10 | Sunny Const. | Completed | 38.8476 |  |  | DA+6 | 45.413
4 | 2024-02-01 | 59/5 | DA+3 | 2024-02-05 | 2024-02-11 | Ganesh Const | Completed | 38.8476 |  |  | DA+9 | 47.1844
5 | 2024-02-01 | 59/14 | DA+6 | 2024-02-08 | 2024-02-13 | Chinta Devi | Completed | 45.413 |  |  | DB1+0 | 57.5972
6 | 2024-02-01 | 60/8 | DA+0 | 2024-02-09 | 2024-02-15 | Suraj const | Completed | 37.5044 |  |  | DB1+3 | 60.0968
7 | 2024-02-01 | 63/7 | DA+3 | 2024-02-11 | 2024-02-15 | Sunny Const. | Completed | 38.8476 |  |  | DB1+6 | 67.8737
8 | 2024-02-01 | 59/6 | DA+3 | 2024-02-12 | 2024-02-18 | Ganesh Const | Completed | 38.8476 |  |  | DB1+9 | 70.7017
9 | 2024-02-01 | 59/12 | DA+6 | 2024-02-13 | 2024-02-20 | Chinta Devi | Completed | 45.413 |  |  | DB2+0 | 57.5972
10 | 2024-02-01 | 63/8 | DA+3 | 2024-02-15 | 2024-02-20 | Sunny Const. | Completed | 38.8476 |  |  | DB2+3 | 60.0968
11 | 2024-02-01 | 60/10 | DA+0 | 2024-02-15 | 2024-02-21 | Suraj const | Completed | 37.5044 |  |  | DB2+6 | 67.8737
12 | 2024-02-01 | 62/5 | DA+0 | 2024-02-17 | 2024-02-22 | Sobha Devi | Completed | 37.5044 |  |  | DB2+9 | 70.7017
13 | 2024-02-01 | 59/7 | DA+3 | 2024-02-18 | 2024-02-24 | Ganesh Const | Completed | 38.8476 |  |  | DC1+0 | 66.3811
14 | 2024-02-01 | 59/10 | DA+0 | 2024-02-20 | 2024-02-24 | Chinta Devi | Completed | 37.5044 |  |  | DCT+0 | 94.2199
15 | 2024-02-01 | 64/1 | DA+0 | 2024-02-20 | 2024-02-24 | Sunny Const. | Completed | 37.5044 |  |  | DC1+3 | 69.2287
16 | 2024-02-01 | 60/11 | DA+3 | 2024-02-21 | 2024-02-26 | Suraj const | Completed | 38.8476 |  |  | DC1+6 | 78.132
17 | 2024-02-01 | 62/4 | DA+3 | 2024-02-22 | 2024-02-26 | Sobha Devi | Completed | 38.8476 |  |  | DC1+9 | 81.4946
18 | 2024-02-01 | 59/9 | DA+3 | 2024-02-24 | 2024-02-28 | Chinta Devi | Completed | 38.8476 |  |  | DC2+0 | 66.3811
19 | 2024-02-01 | 62/3 | DA+0 | 2024-02-26 | 2024-02-28 | Sobha Devi | Completed | 37.5044 |  |  | DC2+3 | 69.2287
20 | 2024-02-01 | 59/8 | DB1+3 | 2024-02-24 | 2024-02-29 | Ganesh Const | Completed | 60.0968 |  |  | DC2+6 | 78.132
21 | 2024-02-01 | 64/4 | DA+3 | 2024-02-24 | 2024-02-29 | Sunny Const. | Completed | 38.8476 |  |  | DC2+9 | 81.4946
22 | 2024-02-01 | 60/6 | DA+0 | 2024-02-26 | 2024-02-29 | Suraj const | Completed | 37.5044 |  |  | DD45+0 | 86.1293
23 | 2024-03-01 | 62/2 | DA+3 | 2024-02-29 | 2024-03-03 | Sobha Devi | Completed | 38.8476 |  |  | DD45+3 | 89.9096
24 | 2024-03-01 | 64/5 | DA+3 | 2024-02-29 | 2024-03-04 | Sunny Const. | Completed | 38.8476 |  |  | DD60+0 | 86.1293
25 | 2024-03-01 | 65/2 | DA+0 | 2024-02-29 | 2024-03-06 | Chinta Devi | Completed | 37.5044 |  |  | DD60+3 | 89.9096
26 | 2024-03-01 | 62/7 | DA+3 | 2024-03-04 | 2024-03-07 | Sobha Devi | Completed | 38.8476 |  |  | DD60+6 | 100.968
27 | 2024-03-01 | 59/16 | DA+9 | 2024-02-29 | 2024-03-11 | Ganesh Const. | Completed | 47.1844 |  |  | DD60+9 | 105.0682
28 | 2024-03-01 | 65/4 | DA+0 | 2024-03-06 | 2024-03-11 | Chinta Devi | Completed | 37.5044 |  |  | DD60+18 | 129.111
29 | 2024-03-01 | 62/8 | DA+0 | 2024-03-07 | 2024-03-11 | Sobha Devi | Completed | 37.5044 |  |  | DD+25 | 143.6019
30 | 2024-03-01 | 62/9 | DA+3 | 2024-03-11 | 2024-03-15 | Sobha Devi | Completed | 38.8476
31 | 2024-03-01 | 65/3 | DA+3 | 2024-03-11 | 2024-03-16 | Chinta Devi | Completed | 38.8476
32 | 2024-03-01 | 60/5 | DA+3 | 2024-03-11 | 2024-03-17 | Ganesh Const. | Completed | 38.8476
33 | 2024-03-01 | 62/10 | DA+0 | 2024-03-15 | 2024-03-18 | Sobha Devi | Completed | 37.5044
34 | 2024-03-01 | 65/5 | DA+0 | 2024-03-16 | 2024-03-20 | Chinta Devi | Completed | 37.5044
35 | 2024-03-01 | 61/6 | DA+3 | 2024-03-18 | 2024-03-22 | Sobha Devi | Completed | 38.8476
36 | 2024-03-01 | 60/4 | DA+3 | 2024-03-18 | 2024-03-23 | Ganesh Const. | Completed | 38.8476
37 | 2024-03-01 | 65/6 | DA+0 | 2024-03-20 | 2024-03-26 | Chinta Devi | Completed | 37.5044
38 | 2024-03-01 | 64/6 | DA+0 | 2024-03-21 | 2024-03-26 | Sunny Const. | Completed | 37.5044
39 | 2024-03-01 | 61/7 | DA+9 | 2024-03-22 | 2024-03-28 | Sobha Devi | Completed | 47.1844
40 | 2024-03-01 | 64/7 | DA+3 | 2024-03-26 | 2024-03-30 | Sunny Const. | Completed | 38.8476
41 | 2024-03-01 | 60/3 | DA+3 | 2024-03-23 | 2024-03-31 | Ganesh Const. | Completed | 38.8476
42 | 2024-03-01 | 65/9 | DA+0 | 2024-03-26 | 2024-03-31 | Chinta Devi | Completed | 37.5044
43 | 2024-04-01 | 64/8 | DA+3 | 2024-03-30 | 2024-04-03 | Sunny Const. | Completed | 38.8476
44 | 2024-04-01 | 65/11 | DA+0 | 2024-03-31 | 2024-04-04 | Chinta Devi | Completed | 37.5044
45 | 2024-04-01 | 60/2 | DA+3 | 2024-03-31 | 2024-04-07 | Ganesh Const. | Completed | 38.8476
46 | 2024-04-01 | 63/5 | DA+3 | 2024-04-01 | 2024-04-07 | Suraj Const | Completed | 38.8476
47 | 2024-04-01 | 64/9 | DA+3 | 2024-04-03 | 2024-04-08 | Sunny Const. | Completed | 38.8476
48 | 2024-04-01 | 67/1 | DA+0 | 2024-04-06 | 2024-04-10 | Chinta Devi | Completed | 37.5044
49 | 2024-04-01 | 61/0 | DB2+0 | 2024-04-06 | 2024-04-11 | Sobha Devi | Completed | 57.5972
50 | 2024-04-01 | 63/4 | DA+0 | 2024-04-07 | 2024-04-13 | Suraj Const | Completed | 37.5044
51 | 2024-04-01 | 67/2 | DA+0 | 2024-04-10 | 2024-04-15 | Chinta Devi | Completed | 37.5044
52 | 2024-04-01 | 63/3 | DA+3 | 2024-04-13 | 2024-04-17 | Suraj Const | Completed | 38.8476
53 | 2024-04-01 | 64/10 | DA+3 | 2024-04-15 | 2024-04-20 | Chinta Devi | Completed | 38.8476
54 | 2024-04-01 | 64/2 | DA+3 | 2024-04-16 | 2024-04-21 | Sunny Const. | Completed | 38.8476
55 | 2024-04-01 | 61/2 | DA+6 | 2024-04-16 | 2024-04-22 | Sobha Devi | Completed | 45.413
56 | 2024-04-01 | 63/2 | DA+0 | 2024-04-17 | 2024-04-22 | Suraj const | Completed | 37.5044
57 | 2024-04-01 | 60/1 | DA+6 | 2024-04-18 | 2024-04-25 | Ganesh Const. | Completed | 45.413
58 | 2024-04-01 | 64/3 | DA+0 | 2024-04-21 | 2024-04-26 | Sunny Const. | Completed | 37.5044
59 | 2024-04-01 | 65/0 | DB1+0 | 2024-04-21 | 2024-04-27 | Chinta Devi | Completed | 57.5972
60 | 2024-04-01 | 63/1 | DA+3 | 2024-04-22 | 2024-04-27 | Suraj const | Completed | 38.8476
61 | 2024-04-01 | 61/1 | DA+6 | 2024-04-22 | 2024-04-29 | Sobha Devi | Completed | 45.413
62 | 2024-05-01 | 65/1 | DA+0 | 2024-04-27 | 2024-05-03 | Chinta Devi | Completed | 37.5044
63 | 2024-05-01 | 62/11 | DA+3 | 2024-04-27 | 2024-05-03 | Suraj const | Completed | 38.8476
64 | 2024-05-01 | 64/0 | DB2+0 | 2024-04-27 | 2024-05-05 | Sunny Const. | Completed | 57.5972
65 | 2024-05-01 | 60/9 | DA+3 | 2024-04-29 | 2024-05-05 | Sobha Devi | Completed | 38.8476
66 | 2024-05-01 | 61/3 | DA+6 | 2024-05-05 | 2024-05-11 | Sobha Devi | Completed | 45.413
67 | 2024-05-01 | 63/0 | DC1+0 | 2024-05-03 | 2024-05-12 | Suraj const | Completed | 66.3811
68 | 2024-05-01 | 61/4 | DA+3 | 2024-05-11 | 2024-05-16 | Sobha Devi | Completed | 38.8476
69 | 2024-05-01 | 60/0 | DC1+0 | 2024-05-05 | 2024-05-18 | Ganesh | Completed | 66.3811
70 | 2024-05-01 | 61/10 | DA+9 | 2024-05-12 | 2024-05-19 | Suraj const | Completed | 47.1844
71 | 2024-05-01 | 61/5 | DA+3 | 2024-05-16 | 2024-05-22 | Sobha Devi | Completed | 38.8476
72 | 2024-05-01 | 61/9 | DA+0 | 2024-05-19 | 2024-05-23 | Suraj const | Completed | 37.5044
73 | 2024-05-01 | 59/15 | DA+6 | 2024-05-18 | 2024-05-30 | Ganesh | Completed | 45.413
74 | 2024-05-01 | 61/8 | DA+6 | 2024-05-23 | 2024-05-30 | Suraj const | Completed | 45.413
75 | 2024-05-01 | 55/3 | DA+0 | 2024-05-12 | 2024-05-31 | Mansukh lal | Completed | 37.5044
76 | 2024-06-01 | 57/3 | DA+0 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | Completed | 37.5044
77 | 2024-06-01 | 55/4 | DA+0 | 2024-06-01 | 2024-06-19 | Mansukh lal | Completed | 37.5044
78 | 2024-06-01 | 57/4 | DA+0 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | Completed | 37.5044
79 | 2024-07-01 | 62/1 | DA+3 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | Completed | 38.8476
80 | 2024-07-01 | 62/6 | DA+3 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | Completed | 38.8476
81 | 2024-08-01 | 57/6 | DA+3 | 2024-08-13 | 2024-08-20 | Sobha devi | Completed | 38.8476
82 | 2024-08-01 | 57/5 | DA+3 | 2024-08-20 | 2024-08-26 | Sobha devi | Completed | 38.8476
83 | 2024-08-01 | 10/18 | DA+3 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | Completed | 38.8476
84 | 2024-09-01 | 10/3 | DA+0 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | Completed | 37.5044
85 | 2024-09-01 | 10/17 | DA+3 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | Completed | 38.8476
86 | 2024-09-01 | 62/0 | DB2+0 | 2024-08-31 | 2024-09-08 | Sobha devi | Completed | 57.5972
87 | 2024-09-01 | 50/9 | DA+0 | 2024-08-28 | 2024-09-09 | Uma const | Completed | 37.5044
88 | 2024-09-01 | 16/3 | DA+3 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | Completed | 38.8476
89 | 2024-09-01 | 10/19 | DA+0 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | Completed | 37.5044
90 | 2024-09-01 | 52/5 | DA+9 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | Completed | 47.1844
91 | 2024-09-01 | 50/10 | DA+0 | 2024-09-10 | 2024-09-19 | Uma const | Completed | 37.5044
92 | 2024-09-01 | 18/2 | DA+0 | 2024-09-18 | 2024-09-22 | Deglal Mahto | Completed | 37.5044
93 | 2024-09-01 | 10/20 | DA+3 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | Completed | 38.8476
94 | 2024-09-01 | 48/1 | DA+9 | 2024-09-08 | 2024-09-25 | Kaushalya const | Completed | 47.1844
95 | 2024-09-01 | 15/1 | DA+3 | 2024-09-21 | 2024-09-26 | Jailal Ageria | Completed | 38.8476
96 | 2024-09-01 | 51/1 | DA+0 | 2024-09-19 | 2024-09-26 | Uma const | Completed | 37.5044
97 | 2024-09-01 | 18/4 | DA+0 | 2024-09-23 | 2024-09-27 | Deglal Mahto | Completed | 37.5044
98 | 2024-09-01 | 10/6 | DA+0 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | Completed | 37.5044
99 | 2024-09-01 | 52/6 | DA+6 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | Completed | 45.413
100 | 2024-10-01 | 57/7 | DA+3 | 2024-09-27 | 2024-10-01 | Sobha devi | Completed | 38.8476
101 | 2024-10-01 | 16/4 | DA+0 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | Completed | 37.5044
102 | 2024-10-01 | 14A/1 | DA+3 | 2024-09-28 | 2024-10-03 | Jailal Ageria | Completed | 38.8476
103 | 2024-10-01 | 51/2 | DA+0 | 2024-09-26 | 2024-10-04 | Uma const | Completed | 37.5044
104 | 2024-10-01 | 10/14 | DA+3 | 2024-09-27 | 2024-10-06 | Khublal Mahto | Completed | 38.8476
105 | 2024-10-01 | 11A/2 | DA+0 | 2024-09-27 | 2024-10-07 | Rafikul Islam | Completed | 37.5044
106 | 2024-10-01 | 50/0 | DB2+0 | 2024-10-02 | 2024-10-07 | Sobha devi | Completed | 57.5972
107 | 2024-10-01 | 52/7 | DA+3 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | Completed | 38.8476
108 | 2024-10-01 | 10/9 | DA+0 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | Completed | 37.5044
109 | 2024-10-01 | 18/1 | DA+0 | 2024-10-04 | 2024-10-08 | Deglal Mahto | Completed | 37.5044
110 | 2024-10-01 | 10/21 | DA+3 | 2024-10-07 | 2024-10-10 | Bina Devi | Completed | 38.8476
111 | 2024-10-01 | 17/1 | DA+3 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | Completed | 38.8476
112 | 2024-10-01 | 50/1 | DA+6 | 2024-10-07 | 2024-10-15 | Sobha Devi | Completed | 45.413
113 | 2024-10-01 | 50/8 | DA+9 | 2024-10-07 | 2024-10-16 | Uma const | Completed | 47.1844
114 | 2024-10-01 | 10/4 | DA+3 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | Completed | 38.8476
115 | 2024-10-01 | 50/3 | DA+6 | 2024-10-13 | 2024-10-18 | Sobha Devi | Completed | 45.413
116 | 2024-10-01 | 17/2 | DA+6 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | Completed | 45.413
117 | 2024-10-01 | 48/0 | DC2+0 | 2024-09-28 | 2024-10-19 | Kaushalya const | Completed | 66.3811
118 | 2024-10-01 | 52/8 | DA+6 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | Completed | 45.413
119 | 2024-10-01 | 73/2 | DA+0 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | Completed | 37.5044
120 | 2024-10-01 | 10/8 | DA+3 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | Completed | 38.8476
121 | 2024-10-01 | 50/2 | DA+9 | 2024-10-18 | 2024-10-24 | Sobha Devi | Completed | 47.1844
122 | 2024-10-01 | 64/11 | DA+3 | 2024-10-20 | 2024-10-24 | Chinta devi | Completed | 38.8476
123 | 2024-10-01 | 16/2 | DA+0 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | Completed | 37.5044
124 | 2024-10-01 | 19/0 | DC2+0 | 2024-10-19 | 2024-10-26 | Deglal Mahto | Completed | 66.3811
125 | 2024-10-01 | 59/11 | DA+6 | 2024-10-17 | 2024-10-26 | Uma const | Completed | 45.413
126 | 2024-10-01 | 16/0 | DC1+0 | 2024-10-18 | 2024-10-27 | Jailal Ageria | Completed | 66.3811
127 | 2024-10-01 | 17/3 | DA+0 | 2024-10-21 | 2024-10-27 | Bina Devi | Completed | 37.5044
128 | 2024-10-01 | 73/1 | DA+0 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | Completed | 37.5044
129 | 2024-10-01 | 50/4 | DA+9 | 2024-10-24 | 2024-10-30 | Sobha Devi | Completed | 47.1844
130 | 2024-11-01 | 55/6 | DA+0 | 2024-10-23 | 2024-11-01 | Jirwa Devi | Completed | 37.5044
131 | 2024-11-01 | 11A/0 | DB1+0 | 2024-10-16 | 2024-11-02 | Rafikul Islam | Completed | 57.5972
132 | 2024-11-01 | 59/3 | DA+3 | 2024-10-27 | 2024-11-02 | Uma const | Completed | 38.8476
133 | 2024-11-01 | 50/7 | DA+0 | 2024-11-01 | 2024-11-04 | Sobha Devi | Completed | 37.5044
134 | 2024-11-01 | 10/11 | DA+3 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | Completed | 38.8476
135 | 2024-11-01 | 11A/1 | DA+3 | 2024-10-18 | 2024-11-08 | Rafikul Islam | Completed | 38.8476
136 | 2024-11-01 | 16/5 | DA+3 | 2024-11-03 | 2024-11-09 | Bina Devi | Completed | 38.8476
137 | 2024-11-01 | 16/1 | DA+0 | 2024-11-05 | 2024-11-09 | Jailal Ageria | Completed | 37.5044
138 | 2024-11-01 | 59/4 | DA+3 | 2024-11-01 | 2024-11-09 | Uma const | Completed | 38.8476
139 | 2024-11-01 | 50/6 | DA+9 | 2024-11-04 | 2024-11-10 | Sobha Devi | Completed | 47.1844
140 | 2024-11-01 | 55/5 | DA+0 | 2024-11-01 | 2024-11-12 | Jirwa Devi | Completed | 37.5044
141 | 2024-11-01 | 73/9 | DA+0 | 2024-11-09 | 2024-11-13 | Chinta devi | Completed | 37.5044
142 | 2024-11-01 | 17/0 | DB2+3 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | Completed | 60.0968
143 | 2024-11-01 | 49/7 | DA+0 | 2024-11-11 | 2024-11-14 | Sobha Devi | Completed | 37.5044
144 | 2024-11-01 | 73/8 | DA+3 | 2024-11-13 | 2024-11-17 | Chinta devi | Completed | 38.8476
145 | 2024-11-01 | 11/5 | DA+0 | 2024-11-10 | 2024-11-18 | Rafikul Islam | Completed | 37.5044
146 | 2024-11-01 | 13/2 | DA+3 | 2024-11-11 | 2024-11-18 | Jailal Ageria | Completed | 38.8476
147 | 2024-11-01 | 43/9 | DA+9 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | Completed | 47.1844
148 | 2024-11-01 | 49/6 | DA+0 | 2024-11-15 | 2024-11-18 | Sobha Devi | Completed | 37.5044
149 | 2024-11-01 | 73/6 | DA+0 | 2024-11-17 | 2024-11-20 | Chinta devi | Completed | 37.5044
150 | 2024-11-01 | 47/10 | DA+6 | 2024-11-02 | 2024-11-22 | Kaushalya const | Completed | 45.413
151 | 2024-11-01 | 49/4 | DA+3 | 2024-11-18 | 2024-11-22 | Sobha Devi | Completed | 38.8476
152 | 2024-11-01 | 59/2 | DA+3 | 2024-11-12 | 2024-11-24 | Jirwa Devi | Completed | 38.8476
153 | 2024-11-01 | 52/10 | DA+9 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | Completed | 47.1844
154 | 2024-11-01 | 43/8 | DA+9 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | Completed | 47.1844
155 | 2024-11-01 | 49/5 | DA+3 | 2024-11-23 | 2024-11-27 | Sobha Devi | Completed | 38.8476
156 | 2024-11-01 | 17/5 | DA+3 | 2024-11-22 | 2024-11-30 | Bina Devi | Completed | 38.8476
157 | 2024-11-01 | 11A/9 | DA+3 | 2024-11-24 | 2024-11-30 | Deglal Mahto | Completed | 38.8476
158 | 2024-11-01 | 49/2 | DA+3 | 2024-11-27 | 2024-11-30 | Sobha Devi | Completed | 38.8476
159 | 2024-11-01 | 72/3 | DA+3 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | Completed | 38.8476
160 | 2024-12-01 | 59/1 | DA+3 | 2024-11-25 | 2024-12-03 | Jirwa Devi | Completed | 38.8476
161 | 2024-12-01 | 52/9 | DA+3 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | Completed | 38.8476
162 | 2024-12-01 | 49/3 | DA+3 | 2024-12-02 | 2024-12-05 | Sobha Devi | Completed | 38.8476
163 | 2024-12-01 | 11A/7 | DA+9 | 2024-11-28 | 2024-12-06 | Jailal Ageria | Completed | 47.1844
164 | 2024-12-01 | 11A/3 | DA+3 | 2024-12-01 | 2024-12-07 | Deglal Mahto | Completed | 38.8476
165 | 2024-12-01 | 49/1 | DA+0 | 2024-12-06 | 2024-12-09 | Sobha Devi | Completed | 37.5044
166 | 2024-12-01 | 10/12 | DB1+0 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | Completed | 57.5972
167 | 2024-12-01 | 73/3 | DA+0 | 2024-12-09 | 2024-12-13 | Chinta devi | Completed | 37.5044
168 | 2024-12-01 | 11A/6 | DA+6 | 2024-12-09 | 2024-12-16 | Deglal Mahto | Completed | 45.413
169 | 2024-12-01 | 59/0 | DC2+0 | 2024-12-03 | 2024-12-16 | Jirwa Devi | Completed | 66.3811
170 | 2024-12-01 | 65/8 | DA+0 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | Completed | 37.5044
171 | 2025-01-01 | 11A/5 | DA+3 | 2024-12-25 | 2025-01-04 | Deglal Mahto | Completed | 38.8476
172 | 2025-01-01 | 65/7 | DA+0 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | Completed | 37.5044
173 | 2025-01-01 | 43/0 | DB1+0 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | Completed | 57.5972
174 | 2025-01-01 | 73/0 | DB2+0 | 2025-01-03 | 2025-01-09 | Chinta devi | Completed | 57.5972
175 | 2025-01-01 | 53/8 | DA+3 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | Completed | 38.8476
176 | 2025-01-01 | 74/0 | DB2+0 | 2025-01-05 | 2025-01-13 | Sunny Const | Completed | 57.5972
177 | 2025-01-01 | 73/4 | DA+0 | 2025-01-10 | 2025-01-14 | Chinta devi | Completed | 37.5044
178 | 2025-01-01 | 43/1 | DA+3 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | Completed | 38.8476
179 | 2025-01-01 | 43/7 | DA+3 | 2025-01-11 | 2025-01-18 | Bina Devi | Completed | 38.8476
180 | 2025-01-01 | 53/7 | DA+3 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | Completed | 38.8476
181 | 2025-01-01 | 73/5 | DA+0 | 2025-01-15 | 2025-01-19 | Chinta devi | Completed | 37.5044
182 | 2025-01-01 | 73/7 | DA+0 | 2025-01-14 | 2025-01-19 | Sunny Const | Completed | 37.5044
183 | 2025-01-01 | 72/0 | DB2+3 | 2025-01-21 | 2025-01-27 | Chinta Devi | Completed | 60.0968
184 | 2025-01-01 | 43/6 | DA+3 | 2025-01-19 | 2025-01-29 | Bina Devi | Completed | 38.8476
185 | 2025-01-01 | 66/0 | DC2+6 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | Completed | 78.132
186 | 2025-01-01 | 53/6 | DA+6 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | Completed | 45.413
187 | 2025-02-01 | 72/1 | DA+3 | 2025-01-28 | 2025-02-02 | Chinta Devi | Completed | 38.8476
188 | 2025-02-01 | 65/10 | DA+0 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | Completed | 37.5044
189 | 2025-02-01 | 72/2 | DA+0 | 2025-02-02 | 2025-02-06 | Chinta Devi | Completed | 37.5044
190 | 2025-02-01 | 51/0 | DC2+0 | 2025-01-31 | 2025-02-07 | Sunny Const. | Completed | 66.3811
191 | 2025-02-01 | 1A/1 | DA+6 | 2025-01-31 | 2025-02-10 | Bina Devi | Completed | 45.413
192 | 2025-02-01 | 71/8 | DA+3 | 2025-02-07 | 2025-02-10 | Chinta Devi | Completed | 38.8476
193 | 2025-02-01 | 52/0 | DC2+0 | 2025-02-08 | 2025-02-14 | Sunny Const. | Completed | 66.3811
194 | 2025-02-01 | 49/0 | DD45+0 | 2025-02-05 | 2025-02-14 | Sobha Devi | Completed | 86.1293
195 | 2025-02-01 | 71/7 | DA+3 | 2025-02-11 | 2025-02-15 | Chinta Devi | Completed | 38.8476
196 | 2025-02-01 | 1A/2 | DA+0 | 2025-02-11 | 2025-02-18 | Bina Devi | Completed | 37.5044
197 | 2025-02-01 | 71/6 | DA+0 | 2025-02-16 | 2025-02-19 | Chinta Devi | Completed | 37.5044
198 | 2025-02-01 | 50/5 | DA+9 | 2025-02-15 | 2025-02-20 | Sobha Devi | Completed | 47.1844
199 | 2025-02-01 | 71/5 | DA+3 | 2025-02-20 | 2025-02-24 | Chinta Devi | Completed | 38.8476
200 | 2025-02-01 | 1A/3 | DA+0 | 2025-02-19 | 2025-02-28 | Bina Devi | Completed | 37.5044
201 | 2025-03-01 | 71/4 | DA+3 | 2025-02-25 | 2025-03-01 | Chinta Devi | Completed | 38.8476
202 | 2025-03-01 | 53/5 | DA+3 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | Completed | 38.8476
203 | 2025-03-01 | 71/3 | DA+6 | 2025-03-02 | 2025-03-07 | Chinta Devi | Completed | 45.413
204 | 2025-03-01 | 58/0 | DC1+3 | 2025-02-26 | 2025-03-10 | Jirwa Devi | Completed | 69.2287
205 | 2025-03-01 | 71/2 | DA+3 | 2025-03-08 | 2025-03-12 | Chinta Devi | Completed | 38.8476
206 | 2025-03-01 | 70/3 | DA+3 | 2025-03-08 | 2025-03-16 | Sanjeev kumar | Completed | 38.8476
207 | 2025-03-01 | 53/4 | DA+0 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | Completed | 37.5044
208 | 2025-03-01 | 71/1 | DA+3 | 2025-03-13 | 2025-03-18 | Chinta Devi | Completed | 38.8476
209 | 2025-03-01 | 53/3 | DA+6 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | Completed | 45.413
210 | 2025-03-01 | 71/0 | DB2+3 | 2025-03-19 | 2025-03-25 | Chinta Devi | Completed | 60.0968
211 | 2025-03-01 | 70/5 | DA+3 | 2025-03-20 | 2025-03-29 | Sanjeev kumar | Completed | 38.8476
212 | 2025-03-01 | 53/2 | DA+0 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | Completed | 37.5044
213 | 2025-03-01 | 70/11 | DA+3 | 2025-03-26 | 2025-03-31 | Chinta Devi | Completed | 38.8476
214 | 2025-04-01 | 47/9 | DA+3 | 2025-03-31 | 2025-04-02 | Sobha Devi | Completed | 38.8476
215 | 2025-04-01 | 70/10 | DA+3 | 2025-03-31 | 2025-04-04 | Chinta Devi | Completed | 38.8476
216 | 2025-04-01 | 47/8 | DA+0 | 2025-04-03 | 2025-04-06 | Sobha Devi | Completed | 37.5044
217 | 2025-04-01 | 70/9 | DA+3 | 2025-04-06 | 2025-04-09 | Chinta Devi | Completed | 38.8476
218 | 2025-04-01 | 53/1 | DA+9 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | Completed | 47.1844
219 | 2025-04-01 | 68/0 | DD45+0 | 2025-03-13 | 2025-04-14 | Sunny Const. | Completed | 86.1293
220 | 2025-04-01 | 53/0 | DB2+9 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | Completed | 70.7017
221 | 2025-05-01 | 70/4 | DA+3 | 2025-04-27 | 2025-05-02 | Chinta devi | Completed | 38.8476
222 | 2025-05-01 | 67/0 | DC1+9 | 2025-05-20 | 2025-05-29 | Sunny Construction | Completed | 81.4946
|  |  | 1A/4 | 2025-05-10 | WIP | Bhairo Mahto |  |  | Crane erection
|  |  | 70/6 | 2025-05-19 |  | Sonakshi (Manish-2) |  |  | 1st Section WIP. | 17 Manpower

## Tackwelding
Progress Summary'!A1
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line
List of Tackwelding Progress
Sl.No. | Loc. No. | Type of Tower | Start Date | Completion Date | Name of the Contractor | Tackwelding | Painting
1 | 59/13 | DA+3 | 2024-02-20 | 2024-02-20 | Suraja Ram | Done | Done
2 | 59/14 | DA+6 | 2024-02-22 | 2024-02-22 | Suraja Ram | Done | Done
3 | 62/5 | DA+0 | 2024-02-27 | 2024-02-27 | Suraja Ram | Done | Done
4 | 63/6 | DA+3 | 2024-02-28 | 2024-02-28 | Suraja Ram | Done | Done
5 | 63/8 | DA+3 | 2024-03-01 | 2024-03-02 | Suraja Ram | Done | Done
6 | 62/3 | DA+0 | 2024-02-03 | 2024-02-03 | Suraja Ram | Done | Done
7 | 62/4 | DA+3 | 2024-03-04 | 2024-03-04 | Suraja Ram | Done | Done
8 | 59/12 | DA+6 | 2024-03-05 | 2024-03-05 | Suraja Ram | Done | Done
9 | 59/10 | DA+0 | 2024-03-06 | 2024-03-06 | Suraja Ram | Done | Done
10 | 59/9 | DA+3 | 2024-03-07 | 2024-03-07 | Suraja Ram | Done | Done
11 | 60/7 | DA+3 | 2024-03-09 | 2024-03-09 | Suraja Ram | Done | Done
12 | 62/2 | DA+3 | 2024-03-10 | 2024-03-10 | Suraja Ram | Done | Done
13 | 62/7 | DA+3 | 2024-03-11 | 2024-03-11 | Suraja Ram | Done | Done
14 | 64/1 | DA+0 | 2024-03-12 | 2024-03-12 | Suraja Ram | Done | Done
15 | 59/7 | DA+3 | 2024-03-12 | 2024-03-12 | Ramagora | Done | Done
16 | 64/4 | DA+3 | 2024-03-13 | 2024-03-13 | Suraja Ram | Done | Done
17 | 60/11 | DA+3 | 2024-03-15 | 2024-03-15 | Ramagora | Done | Done
18 | 62/8 | DA+0 | 2024-03-15 | 2024-03-15 | Suraja Ram | Done | Done
19 | 65/2 | DA+0 | 2024-03-16 | 2024-03-16 | Suraja Ram | Done | Done
20 | 60/6 | DA+0 | 2024-03-16 | 2024-03-16 | Ramagora | Done | Done
21 | 65/4 | DA+0 | 2024-03-17 | 2024-03-17 | Suraja Ram | Done | Done
22 | 64/5 | DA+3 | 2024-03-18 | 2024-03-18 | Suraja Ram | Done | Done
23 | 62/9 | DA+3 | 2024-03-19 | 2024-03-19 | Suraja Ram | Done | Done
24 | 60/8 | DA+0 | 2024-03-19 | 2024-03-19 | Ramagora | Done | Done
25 | 62/10 | DA+0 | 2024-03-21 | 2024-03-21 | Suraja Ram | Done | Done
26 | 65/3 | DA+3 | 2024-03-22 | 2024-03-22 | Suraja Ram | Done | Done
27 | 59/6 | DA+3 | 2024-03-22 | 2024-03-22 | Ramagora | Done | Done
28 | 60/10 | DA+0 | 2024-03-24 | 2024-03-24 | Suraja Ram | Done | Done
29 | 61/6 | DA+3 | 2024-03-28 | 2024-03-28 | Suraja Ram | Done | Done
30 | 65/5 | DA+0 | 2024-03-29 | 2024-03-29 | Suraja Ram | Done | Done
31 | 64/6 | DA+0 | 2024-04-01 | 2024-04-01 | Suraja Ram | Done | Done
32 | 61/7 | DA+9 | 2024-04-03 | 2024-04-03 | Suraja Ram | Done | Done
33 | 65/6 | DA+0 | 2024-04-04 | 2024-04-04 | Suraja Ram | Done | Done
34 | 64/7 | DA+3 | 2024-04-06 | 2024-04-06 | Suraja Ram | Done | Done
35 | 63/7 | DA+3 | 2024-04-21 | 2024-04-22 | Suraja Ram | Done | Done
36 | 64/9 | DA+3 | 2024-04-24 | 2024-04-24 | Suraja Ram | Done | Done
37 | 61/0 | DB2+0 | 2024-04-25 | 2024-04-25 | Ramagora | Done | Done
38 | 65/9 | DA+0 | 2024-04-27 | 2024-04-27 | Suraja Ram | Done | Done
39 | 65/11 | DA+0 | 2024-04-28 | 2024-04-28 | Suraja Ram | Done | Done
40 | 67/2 | DA+0 | 2024-04-29 | 2024-04-29 | Suraja Ram | Done | Done
41 | 61/2 | DA+6 | 2024-04-29 | 2024-04-30 | Ramagora | Done | Done
42 | 64/10 | DA+3 | 2024-05-05 | 2024-05-05 | Suraja Ram | Done | Done
43 | 67/1 | DA+0 | 2024-05-07 | 2024-05-07 | Suraja Ram | Done | Done
44 | 64/8 | DA+3 | 2024-05-09 | 2024-05-09 | Suraja Ram | Done | Done
45 | 65/1 | DA+0 | 2024-05-10 | 2024-05-10 | Suraja Ram | Done | Done
46 | 65/0 | DB1+0 | 2024-05-10 | 2024-05-10 | Suraja Ram | Done | Done
47 | 61/1 | DA+6 | 2024-05-10 | 2024-05-10 | Ramagora | Done | Done
48 | 60/9 | DA+3 | 2024-05-11 | 2024-05-11 | Ramagora | Done | Done
49 | 63/4 | DA+0 | 2024-05-14 | 2024-05-14 | Suraja Ram | Done | Done
50 | 63/3 | DA+3 | 2024-05-15 | 2024-05-15 | Suraja Ram | Done | Done
51 | 63/5 | DA+3 | 2024-05-16 | 2024-05-16 | Suraja Ram | Done | Done
52 | 61/3 | DA+6 | 2024-05-17 | 2024-05-17 | Ramagora | Done | Done
53 | 62/11 | DA+3 | 2024-05-19 | 2024-05-19 | Suraja Ram | Done | Done
54 | 61/4 | DA+3 | 2024-05-23 | 2024-05-23 | Suraja Ram | Done | Done
55 | 61/5 | DA+3 | 2024-05-25 | 2024-05-25 | Suraja Ram | Done | Done
56 | 64/2 | DA+3 | 2024-06-03 | 2024-06-03 | Suraja Ram | Done | Done
57 | 64/3 | DA+0 | 2024-06-06 | 2024-06-06 | Suraja Ram | Done | Done
58 | 64/0 | DB2+0 | 2024-06-06 | 2024-06-06 | Suraja Ram | Done | Done
59 | 61/10 | DA+9 | 2024-06-07 | 2024-06-07 | Suraja Ram | Done | Done
60 | 61/8 | DA+6 | 2024-06-08 | 2024-06-08 | Ramagora | Done | Done
61 | 63/2 | DA+0 | 2024-06-08 | 2024-06-08 | Suraja Ram | Done | Done
62 | 61/9 | DA+0 | 2024-06-09 | 2024-06-09 | Ramagora | Done | Done
63 | 63/1 | DA+3 | 2024-06-09 | 2024-06-09 | Suraja Ram | Done | Done
64 | 59/5 | DA+3 | 2024-06-10 | 2024-06-10 | Ramagora | Done | Done
65 | 63/0 | DC1+0 | 2024-06-10 | 2024-06-11 | Suraja Ram | Done | Done
66 | 60/5 | DA+3 | 2024-06-11 | 2024-06-11 | Ramagora | Done | Done
67 | 60/4 | DA+3 | 2024-06-13 | 2024-06-13 | Ramagora | Done | Done
68 | 60/3 | DA+3 | 2024-06-23 | 2024-06-23 | Ramagora | Done | Done
69 | 60/2 | DA+3 | 2024-06-25 | 2024-06-25 | Ramagora | Done | Done
70 | 60/1 | DA+6 | 2024-06-30 | 2024-06-30 | Ramagora | Done | Done
71 | 59/16 | DA+9 | 2024-07-01 | 2024-07-01 | Suraja Ram | Done | Done
72 | 59/15 | DA+6 | 2024-07-02 | 2024-07-02 | Suraja Ram | Done | Done
73 | 60/0 | DC1+0 | 2024-07-24 | 2024-07-24 | Suraja Ram | Done | Done
74 | 59/8 | DB1+3 | 2024-07-27 | 2024-07-27 | Suraja Ram | Done | Done
75 | 55/3 | DA+0 | 2024-08-23 | 2024-08-23 | Suraja Ram | Done | Done
76 | 55/4 | DA+0 | 2024-08-24 | 2024-08-24 | Suraja Ram | Done | Done
77 | 57/6 | DA+3 | 2024-08-27 | 2024-08-27 | Suraja Ram | Done | Done
78 | 57/3 | DA+0 | 2024-08-28 | 2024-08-28 | Suraja Ram | Done | Done
79 | 57/4 | DA+0 | 2024-08-30 | 2024-08-30 | Suraja Ram | Done | Done
80 | 57/5 | DA+3 | 2024-08-30 | 2024-08-30 | Suraja Ram | Done | Done
81 | 62/0 | DB2+0 | 2024-09-15 | 2024-09-15 | Suraja Ram | Done | Done
82 | 62/1 | DA+3 | 2024-09-23 | 2024-09-24 | Suraja Ram | Done | Done
83 | 62/6 | DA+3 | 2024-09-25 | 2024-09-26 | Suraja Ram | Done | Done
84 | 57/7 | DA+3 | 2024-10-05 | 2024-10-06 | Suraja Ram | Done | Done
85 | 50/9 | DA+0 | 2024-10-06 | 2024-10-07 | Suraja Ram | Done | Done
86 | 50/10 | DA+0 | 2024-10-09 | 2024-10-09 | Suraja Ram | Done | Done
87 | 50/0 | DB2+0 | 2024-10-10 | 2024-10-10 | Suraja Ram | Done | Done
88 | 50/3 | DA+6 | 2024-10-24 | 2024-10-24 | Suraja Ram | Done | Done
89 | 50/1 | DA+6 | 2024-10-25 | 2024-10-25 | Suraja Ram | Done | Done
90 | 51/1 | DA+0 | 2024-10-25 | 2024-10-25 | Suraja Ram | Done | Done
91 | 16/3 | DA+3 | 2024-10-26 | 2024-10-26 | R&A | Done
92 | 50/2 | DA+9 | 2024-10-28 | 2024-10-28 | Suraja Ram | Done | Done
93 | 64/11 | DA+3 | 2024-10-29 | 2024-10-29 | Suraja Ram | Done | Done
94 | 15/1 | DA+3 | 2024-10-26 | 2024-10-29 | SB Enterprises | Done
95 | 16/4 | DA+0 | 2024-11-10 | 2024-11-10 | SB Enterprises | Done
96 | 59/11 | DA+6 | 2024-11-11 | 2024-11-11 | Suraja Ram | Done | Done
97 | 18/1 | DA+0 | 2024-11-12 | 2024-11-12 | SB Enterprises | Done
98 | 50/7 | DA+0 | 2024-11-14 | 2024-11-14 | Suraja Ram | Done | Done
99 | 73/1 | DA+0 | 2024-11-14 | 2024-11-14 | Suraja Ram | Done | Done
100 | 73/2 | DA+0 | 2024-11-19 | 2024-11-19 | Suraja Ram | Done | Done
101 | 73/9 | DA+0 | 2024-11-20 | 2024-11-20 | Suraja Ram | Done | Done
102 | 52/7 | DA+3 | 2024-11-25 | 2024-11-25 | Suraja Ram | Done | Done
103 | 52/6 | DA+6 | 2024-11-25 | 2024-11-25 | Suraja Ram | Done | Done
104 | 52/8 | DA+6 | 2024-11-26 | 2024-11-26 | Suraja Ram | Done | Done
105 | 48/0 | DC2+0 | 2024-11-27 | 2024-11-27 | Suraja Ram | Done | Done
106 | 49/4 | DA+3 | 2024-11-27 | 2024-11-27 | Suraja Ram | Done | Done
107 | 48/1 | DA+9 | 2024-11-29 | 2024-11-29 | Suraja Ram | Done | Done
108 | 47/10 | DA+6 | 2024-11-29 | 2024-11-29 | Suraja Ram | Done | Done
109 | 49/7 | DA+0 | 2024-12-02 | 2024-12-02 | Suraja Ram | Done | Done
110 | 49/6 | DA+0 | 2024-12-03 | 2024-12-03 | Suraja Ram | Done | Done
111 | 49/5 | DA+3 | 2024-12-04 | 2024-12-04 | Suraja Ram | Done | Done
112 | 59/3 | DA+3 | 2024-12-05 | 2024-12-05 | Suraja Ram | Done | Done
113 | 59/4 | DA+3 | 2024-12-06 | 2024-12-06 | Suraja Ram | Done | Done
114 | 73/6 | DA+0 | 2024-12-13 | 2024-12-13 | Suraja Ram | Done | Done
115 | 72/3 | DA+3 | 2024-12-17 | 2024-12-17 | Suraja Ram | Done | Done
116 | 59/1 | DA+3 | 2024-12-18 | 2024-12-18 | Suraja Ram | Done | Done
117 | 59/2 | DA+3 | 2024-12-20 | 2024-12-20 | Suraja Ram | Done | Done
118 | 50/8 | DA+9 | 2024-12-23 | 2024-12-23 | Suraja Ram | Done | Done
119 | 73/8 | DA+3 | 2024-12-25 | 2024-12-25 | Suraja Ram | Done | Done
120 | 51/2 | DA+0 | 2024-12-26 | 2024-12-26 | Suraja Ram | Done | Done
121 | 49/2 | DA+3 | 2024-12-26 | 2024-12-26 | Suraja Ram | Done | Done
122 | 49/3 | DA+3 | 2024-12-26 | 2024-12-26 | Suraja Ram | Done | Done
123 | 49/1 | DA+0 | 2024-12-28 | 2024-12-28 | Suraja Ram | Done | Done
124 | 50/4 | DA+9 | 2025-01-06 | 2025-01-06 | Suraja Ram | Done | Done
125 | 59/0 | DC2+0 | 2025-01-07 | 2025-01-07 | Suraja Ram | Done | Done
126 | 50/6 | DA+9 | 2025-01-12 | 2025-01-12 | Suraja Ram | Done | Done
127 | 65/7 | DA+0 | 2025-01-17 | 2025-01-17 | Suraja Ram | Done | Done
128 | 65/8 | DA+0 | 2025-01-18 | 2025-01-18 | Suraja Ram | Done | Done
129 | 73/3 | DA+0 | 2025-01-27 | 2025-01-27 | Suraja Ram | Done | Done
130 | 73/4 | DA+0 | 2025-01-28 | 2025-01-29 | Suraja Ram | Done | Done
131 | 73/7 | DA+0 | 2025-02-13 | 2025-02-13 | Suraja Ram | Done | Done
132 | 74/0 | DB2+0 | 2025-02-14 | 2025-02-14 | Suraja Ram | Done | Done
133 | 73/5 | DA+0 | 2025-02-15 | 2025-02-15 | Suraja Ram | Done | Done
134 | 65/10 | DA+0 | 2025-02-17 | 2025-02-17 | Suraja Ram | Done | Done
135 | 66/0 | DC2+6 | 2025-02-19 | 2025-02-19 | Suraja Ram | Done | Done
136 | 51/0 | DC2+0 | 2025-02-26 | 2025-02-26 | Suraja Ram | Done | Done
137 | 50/5 | DA+9 | 2025-03-02 | 2025-03-02 | Suraja Ram | Done | Done
138 | 52/0 | DC2+0 | 2025-03-05 | 2025-03-05 | Suraja Ram | Done | Done
139 | 49/0 | DD45+0 | 2025-03-10 | 2025-03-10 | Suraja Ram | Done | Done
140 | 52/9 | DA+3 | 2025-03-11 | 2025-03-11 | Suraja Ram | Done | Done
141 | 52/10 | DA+9 | 2025-03-12 | 2025-03-12 | Suraja Ram | Done | Done
142 | 73/0 | DB2+0 | 2025-03-13 | 2025-03-13 | Suraja Ram | Done | Done
143 | 52/5 | DA+9 | 2025-03-17 | 2025-03-17 | Suraja Ram | Done | Done
144 | 47/9 | DA+3 | 2025-04-16 | 2025-04-16 | Suraja Ram | Done
145 | 47/8 | DA+0 | 2025-04-16 | 2025-04-16 | Suraja Ram | Done
146 | 58/0 | DC1+3 | 2025-04-21 | 2025-04-21 | Suraja Ram | Done
147 | 72/2 | DA+0 | 2025-04-28 | 2025-04-28 | Suraja Ram | Done | Done
148 | 72/1 | DA+3 | 2025-04-29 | 2025-04-29 | Suraja Ram | Done | Done
149 | 71/8 | DA+3 | 2025-04-30 | 2025-04-30 | Suraja Ram | Done | Done
150 | 71/7 | DA+3 | 2025-04-30 | 2025-04-30 | Suraja Ram | Done | Done
151 | 70/5 | DA+3 | 2025-05-02 | 2025-05-02 | Suraja Ram | Done | Done
152 | 71/6 | DA+0 | 2025-05-02 | 2025-05-02 | Suraja Ram | Done | Done
153 | 70/3 | DA+3 | 2025-05-03 | 2025-05-03 | Suraja Ram | Done | Done
154 | 55/5 | DA+0 | 2025-05-05 | 2025-05-05 | Suraja Ram | Done | Done
155 | 55/6 | DA+0 | 2025-05-06 | 2025-05-06 | Suraja Ram | Done | Done
156 | 71/5 | DA+3 | 2025-05-10 | 2025-05-10 | Suraja Ram | Done | Done
157 | 70/4 | DA+3 | 2025-05-11 | 2025-05-11 | Suraja Ram | Done | Done
158 | 71/3 | DA+6 | 2025-05-16 | 2025-05-16 | Suraja Ram | Done | Done
159 | 71/4 | DA+3 | 2025-05-17 | 2025-05-17 | Suraja Ram | Done | Done
160 | 71/2 | DA+3 | 2025-05-19 | 2025-05-19 | Suraja Ram | Done | Done
161 | 71/1 | DA+3 | 2025-05-20 | 2025-05-20 | Suraja Ram | Done | Done
162 | 70/11 | DA+3 | 2025-05-24 | 2025-05-24 | Suraja Ram | Done | Done
163 | 71/0 | DB2+3 | 2025-05-26 | 2025-05-26 | Suraja Ram | Done | Done
164 | 70/9 | DA+3 | 2025-05-27 | 2025-05-27 | Suraja Ram | Done | Done
165 | 70/10 | DA+3 | 2025-05-28 | 2025-05-28 | Suraja Ram | Done | Done

## Stringing Productivity
765KV D/C Fatehgarh III- Beawar Transmission Line, PKG F, Stringing Status | [22 empty] | Dated | 2025-10-06
Sr. No. | Sub-Contractor Name | Completed in April |  |  | Insulator Hoisting | [13 empty] | Output Upto Yesterdays (Kms) in May | Cumulative Output till today(Kms) | Start Date | Comp Date | Status | Total Manpower
|  | From | To | Span | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14
1 | JPJ Construction | AP73 | AP74 | 3.788 | 1 Phase paying out & R/Sag done. | No work done due to Shutdown. Gang Idle. | No work done due to Shutdown. Gang Idle. | [13 empty] | 2025-06-01 |  | 1 phase R/Sag done. Further works stopped due to shut down of 33 KV line not availed. | 43
2 | JPJ Construction | AP72 | AP73 | 1.628 | [18 empty] | Further work stopped due to ROW in loc no 72/1.
|  |  |  | 5.416 | [19 empty] | #REF!

## Stringing
Progress Summary'!A1
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line
STRINGING
SL. No. | Section |  | Type of Sections | Gang Name | Section Length | Insulator Hoisting |  | Paying Out |  |  |  | Final Sag
| From | To |  |  |  | Start Date | End Date | Section Length | Start Date | End Date | Remarks | Section Length | Start Date | End Date | Remarks | Completion Month
1 | 60/0 | 61/0 | TSE | Kuddus ali | 4.877 |  |  | 4.877 | 2024-08-21 | 2024-08-28 |  | 4.877 | 2024-09-09 | 2024-09-16 | Final sag completed | 2024-09-01
2 | 61/0 | 62/0 | TSE | Kuddus ali | 4.568 |  |  | 4.568 | 2024-09-06 | 2024-09-16 |  | 4.568 | 2024-09-26 | 2024-10-03 | Final sag completed | 2024-10-01
3 | 62/0 | 63/0 | TSE | Kuddus ali | 4.863 |  |  | 4.863 | 2024-09-23 | 2024-10-02 |  | 4.863 | 2024-10-17 | 2024-10-22 | Final sag completed | 2024-10-01
4 | 63/0 | 64/0 | TSE | Kuddus ali | 3.711 |  |  | 3.711 | 2024-10-14 | 2024-10-21 |  | 3.711 | 2024-10-31 | 2024-11-06 | Final sag completed | 2024-11-01
5 | 64/0 | 65/0 | TSE | Kuddus ali | 4.918 |  |  | 4.918 | 2024-10-30 | 2024-11-05 |  | 4.918 | 2024-11-13 | 2024-11-16 | Final sag completed | 2024-11-01
6 | 59/8 | 60/0 | TSE | Gopal Associate | 3.778 |  |  | 3.778 | 2024-12-22 | 2024-12-27 |  | 3.778 | 2025-01-04 | 2025-01-09 | Final sag completed | 2025-01-01
7 | 59/0 | 59/8 | TSE | Gopal Associate | 3.337 |  |  | 3.337 | 2025-01-02 | 2025-01-08 |  | 3.337 | 2025-01-12 | 2025-01-15 | Final sag completed | 2025-01-01
8 | 65/0 | 66/0 | TSE | MR Power | 4.736 |  |  | 4.736 | 2025-02-03 | 2025-03-22 |  | 4.736 | 2025-03-10 | 2025-03-23 | Final sag completed | 2025-03-01
9 | 50/0 | 51/0 | TSE | Gopal Associate | 4.444 |  |  | 4.444 | 2025-03-12 | 2025-03-23 |  | 4.444 | 2025-03-17 | 2025-03-24 | Final sag completed | 2025-03-01
10 | 49/0 | 50/0 | TSE | Gopal Associate | 3.227 |  |  | 3.227 | 2025-02-06 | 2025-02-19 |  | 3.227 | 2025-05-01 | 2025-05-05 | Conductor Final sag completed. | 2025-05-01
11 | 51/0 | 52/0 | TSE | Gopal Associate | 1.049 |  |  | 1.049 | 2025-04-02 | 2025-04-08 |  | 1.049 | 2025-04-04 | 2025-04-09 | Final sag completed | 2025-04-01
11 | 73/0 | 74/0 | TSE | JPJ Construction | 3.788 | 2025-05-17 | 2025-05-23 |  | 2025-06-01 | [5 empty] | Insulator hositing completed.
12 | 72/0 | 730 | TSE | JPJ Construction | 1.628 | 2025-05-24 | [8 empty] | Insulator hositing WIP.
TOTAL |  |  |  |  | 48.924 |  |  | 43.508 |  |  |  | 43.508

## Stringing associated works (hidden)
Progress Summary'!A1
LINE MATERIAL
As per details shared on dated 10.03.2025 | [8 empty] | CLR Insulators |  | Hardware Fittings (Set) |  |  |  | Conductor Accessories for AL59 Zebra |  |  |  |  | Earthwire Accessories | [5 empty] | Remarks | Progress
Sl No | Twr No. | Tower Type | Deviation Angle (DMS) | Span (m) |  | Section Length (m) | Conductor (Mtr.) | Earthwire (Mtr.) | 210 KN Insulator Rod for 765KV(2*2975 or 1*5950)mm lenth | 160 KN Insulator Rod for 765KV(2*2975 or 1*5950)mm lenth | 4x210KN Quad Tension for 765KV | 2x160KNDouble Suspension Insulator string | 160KN Single "I" Pilot string | Single tension Insulator string | MSCJ | Repair Sleeve | Hexa Spacer Damper for 765KV AL59 Zebra | Rigid Spacer for 765KV AL59 Zebra | T - Connector | Tension Clamp | Suspension Clamp | Flexible Copper bond | MSCJ | Repair Sleeve | VD |  | Jumper | Spacer | Clipping | Earthwire Clipping
| GANTRY | GTY | 00°00'00" | [5 empty] | 48 | 12 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 1 |  |  | 4
|  |  |  | 121.9985 | 125 |  | 4500 | 125 | [8 empty] | 12
1 | 1/0 | DE | 11°14'51"LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 89.9994 | 90 |  | 3240 | 90 | [8 empty] | 12
2 | 1A/0 | DD60+0 | 52°22'23.88"LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 277.7254 | 280 |  | 10080 | 280 | [8 empty] | 30
3 | 1A/1 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 386.0439 | 390 |  | 14040 | 390 | [8 empty] | 36
4 | 1A/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 443.6322 | 445 |  | 16020 | 445 | [8 empty] | 42
5 | 1A/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 333.3931 | 335 |  | 12060 | 335 | [8 empty] | 36
6 | 1A/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 431.8482 | 435 |  | 15660 | 435 | [8 empty] | 42
7 | 1A/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 348.7352 | 350 |  | 12600 | 350 | [8 empty] | 36
8 | 1A/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 395.6926 | 400 |  | 14400 | 400 | [8 empty] | 42
9 | 1A/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 414.9531 | 415 |  | 14940 | 415 | [8 empty] | 42
10 | 1A/8 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 394.3057 | 395 |  | 14220 | 395 | [8 empty] | 42
11 | 2/0 | DC1+0 | 16° 05' 50.64" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 405.3424 | 410 |  | 14760 | 410 | [8 empty] | 42
12 | 2/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 338.5077 | 340 |  | 12240 | 340 | [8 empty] | 36
13 | 2/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.023 | 410 |  | 14760 | 410 | [8 empty] | 42
14 | 2/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 428.9489 | 430 |  | 15480 | 430 | [8 empty] | 42
15 | 2/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 411.548 | 415 |  | 14940 | 415 | [8 empty] | 42
16 | 2/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 425.7409 | 430 |  | 15480 | 430 | [8 empty] | 42
17 | 2/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.1755 | 410 |  | 14760 | 410 | [8 empty] | 42
18 | 2/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 354.5811 | 355 |  | 12780 | 355 | [8 empty] | 36
19 | 2/8 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 308.6564 | 310 |  | 11160 | 310 | [8 empty] | 30
20 | 2/9 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 335.9782 | 340 |  | 12240 | 340 | [8 empty] | 36
21 | 3/0 | DD60+6 | 01° 29' 56.04" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 226.5199 | 230 |  | 8280 | 230 | [8 empty] | 24
22 | 4/0 | DD60+6 | 07° 48' 05.04" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 343.3742 | 345 |  | 12420 | 345 | [8 empty] | 36
23 | 4/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 358.4439 | 360 |  | 12960 | 360 | [8 empty] | 36
24 | 4/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 381.0116 | 385 |  | 13860 | 385 | [8 empty] | 36
25 | 4/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 367.6241 | 370 |  | 13320 | 370 | [8 empty] | 36
26 | 4/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 423.0902 | 425 |  | 15300 | 425 | [8 empty] | 42
27 | 5/0 | DB1+9,5RC | 05° 43' 49.08" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 246.0191 | 250 |  | 9000 | 250 | [8 empty] | 24
28 | 6/0 | DB2+9,5RC | 10° 20' 7.44" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 429.9181 | 430 |  | 15480 | 430 | [8 empty] | 42
29 | 6/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 362.365 | 365 |  | 13140 | 365 | [8 empty] | 36
30 | 6/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 347.8637 | 350 |  | 12600 | 350 | [8 empty] | 36
31 | 7/0 | DB1+0 | 04° 51' 39.96" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 210.754 | 215 |  | 7740 | 215 | [8 empty] | 24
32 | 8/0 | DB1+0 | 01° 26' 19.32" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 409.2022 | 410 |  | 14760 | 410 | [8 empty] | 42
33 | 8/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 413.633 | 415 |  | 14940 | 415 | [8 empty] | 42
34 | 8/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 393.2406 | 395 |  | 14220 | 395 | [8 empty] | 42
35 | 8/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 416.4734 | 420 |  | 15120 | 420 | [8 empty] | 42
36 | 8/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 394.5618 | 395 |  | 14220 | 395 | [8 empty] | 42
37 | 8/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 393.2039 | 395 |  | 14220 | 395 | [8 empty] | 42
38 | 8/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 441.0581 | 445 |  | 16020 | 445 | [8 empty] | 42
39 | 8/7 | DB1+0 | 00° 00' 00" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 414.3921 | 415 |  | 14940 | 415 | [8 empty] | 42
40 | 8/8 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 395.8638 | 400 |  | 14400 | 400 | [8 empty] | 42
41 | 8/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 413.4043 | 415 |  | 14940 | 415 | [8 empty] | 42
42 | 8/10 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 402.6362 | 405 |  | 14580 | 405 | [8 empty] | 42
43 | 8/11 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 372.0453 | 375 |  | 13500 | 375 | [8 empty] | 36
44 | 8/12 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 457.7028 | 460 |  | 16560 | 460 | [8 empty] | 48
45 | 9/0 | DD60+18 | 20° 13' 33.24" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 233.0763 | 235 |  | 8460 | 235 | [8 empty] | 24
46 | 10/0 | DD60+25 | 33° 37' 51.96" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 443.7105 | 445 |  | 16020 | 445 | [8 empty] | 42
47 | 10/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 383.2352 | 385 |  | 13860 | 385 | [8 empty] | 36
48 | 10/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 398.553 | 400 |  | 14400 | 400 | [8 empty] | 42
49 | 10/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 410.7191 | 415 |  | 14940 | 415 | [8 empty] | 42
50 | 10/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 416.15 | 420 |  | 15120 | 420 | [8 empty] | 42
51 | 10/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 403.3984 | 405 |  | 14580 | 405 | [8 empty] | 42
52 | 10/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 373.8459 | 375 |  | 13500 | 375 | [8 empty] | 36
53 | 10/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 411.824 | 415 |  | 14940 | 415 | [8 empty] | 42
54 | 10/8 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 414.2003 | 415 |  | 14940 | 415 | [8 empty] | 42
55 | 10/9 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 402.2937 | 405 |  | 14580 | 405 | [8 empty] | 42
56 | 10/10 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 430.283 | 435 |  | 15660 | 435 | [8 empty] | 42
57 | 10/11 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.2235 | 410 |  | 14760 | 410 | [8 empty] | 42
58 | 10/12 | DB1+0 | 00° 00' 00" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 405.2508 | 410 |  | 14760 | 410 | [8 empty] | 42
59 | 10/13 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 427.0841 | 430 |  | 15480 | 430 | [8 empty] | 42
60 | 10/14 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400.0355 | 405 |  | 14580 | 405 | [8 empty] | 42
61 | 10/15 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 412.7903 | 415 |  | 14940 | 415 | [8 empty] | 42
62 | 10/16 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 387.7578 | 390 |  | 14040 | 390 | [8 empty] | 36
63 | 10/17 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 436.7319 | 440 |  | 15840 | 440 | [8 empty] | 42
64 | 10/18 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 403.6899 | 405 |  | 14580 | 405 | [8 empty] | 42
65 | 10/19 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 409.5279 | 410 |  | 14760 | 410 | [8 empty] | 42
66 | 10/20 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 419.5597 | 420 |  | 15120 | 420 | [8 empty] | 42
67 | 10/21 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 409.2531 | 410 |  | 14760 | 410 | [8 empty] | 42
68 | 10/22 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 383.9681 | 385 |  | 13860 | 385 | [8 empty] | 36
69 | 10/23 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 450.8072 | 455 |  | 16380 | 455 | [8 empty] | 42
70 | 11/0 | DB1+0 | [6 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 384.2188 | 385 |  | 13860 | 385 | [8 empty] | 36
71 | 11/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 338.5488 | 340 |  | 12240 | 340 | [8 empty] | 36
72 | 11/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 370.7399 | 375 |  | 13500 | 375 | [8 empty] | 36
73 | 11/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 434.0995 | 435 |  | 15660 | 435 | [8 empty] | 42
74 | 11/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 368.1012 | 370 |  | 13320 | 370 | [8 empty] | 36
75 | 11/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 342.2792 | 345 |  | 12420 | 345 | [8 empty] | 36
76 | 11A/0 | DB1+0 | 01° 00' 23.04" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 405.1155 | 410 |  | 14760 | 410 | [8 empty] | 42
77 | 11A/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 412.1456 | 415 |  | 14940 | 415 | [8 empty] | 42
78 | 11A/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 412.2235 | 415 |  | 14940 | 415 | [8 empty] | 42
79 | 11A/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 422.0714 | 425 |  | 15300 | 425 | [8 empty] | 42
80 | 11A/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 418.2682 | 420 |  | 15120 | 420 | [8 empty] | 42
81 | 11A/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 384.3076 | 385 |  | 13860 | 385 | [8 empty] | 36
82 | 11A/6 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 434.1992 | 435 |  | 15660 | 435 | [8 empty] | 42
83 | 11A/7 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 390.1215 | 395 |  | 14220 | 395 | [8 empty] | 42
84 | 11A/8 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 426.3141 | 430 |  | 15480 | 430 | [8 empty] | 42
85 | 11A/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 405.8662 | 410 |  | 14760 | 410 | [8 empty] | 42
86 | 12/0 | DD60+0 | 52° 09' 12.24" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 211.9149 | 215 |  | 7740 | 215 | [8 empty] | 24
87 | 13/0 | DD60+3 | 50° 55' 18.84" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 464.251 | 465 |  | 16740 | 465 | [8 empty] | 48
88 | 13/1 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 373.6874 | 375 |  | 13500 | 375 | [8 empty] | 36
89 | 13/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 419.6725 | 420 |  | 15120 | 420 | [8 empty] | 42
90 | 13/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 420.2521 | 425 |  | 15300 | 425 | [8 empty] | 42
91 | 13/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400.0369 | 405 |  | 14580 | 405 | [8 empty] | 42
92 | 14/0 | DC2+0 | 23° 35' 02.76" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 381.4133 | 385 |  | 13860 | 385 | [8 empty] | 36
93 | 14A/0 | DC1+0 | 17° 04' 19.92" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 412.7659 | 415 |  | 14940 | 415 | [8 empty] | 42
94 | 14A/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 396.0298 | 400 |  | 14400 | 400 | [8 empty] | 42
95 | 14A/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 383.3345 | 385 |  | 13860 | 385 | [8 empty] | 36
96 | 15/0 | DC1+0 | 19° 19' 46.92" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 404.5871 | 405 |  | 14580 | 405 | [8 empty] | 42
97 | 15/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 413.3265 | 415 |  | 14940 | 415 | [8 empty] | 42
98 | 16/0 | DC1+0 | 18° 26' 35.88" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 354.2839 | 355 |  | 12780 | 355 | [8 empty] | 36
99 | 16/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 424.2808 | 425 |  | 15300 | 425 | [8 empty] | 42
100 | 16/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 340.3112 | 345 |  | 12420 | 345 | [8 empty] | 36
101 | 16/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 394.648 | 395 |  | 14220 | 395 | [8 empty] | 42
102 | 16/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 435.8632 | 440 |  | 15840 | 440 | [8 empty] | 42
103 | 16/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 386.7712 | 390 |  | 14040 | 390 | [8 empty] | 36
104 | 17/0 | DB2+3 | 12° 43' 17.04" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 393.7242 | 395 |  | 14220 | 395 | [8 empty] | 42
105 | 17/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 415.8861 | 420 |  | 15120 | 420 | [8 empty] | 42
106 | 17/2 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 422.8149 | 425 |  | 15300 | 425 | [8 empty] | 42
107 | 17/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 409.8892 | 410 |  | 14760 | 410 | [8 empty] | 42
108 | 17/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 425.3357 | 430 |  | 15480 | 430 | [8 empty] | 42
109 | 17/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 383.4318 | 385 |  | 13860 | 385 | [8 empty] | 36
110 | 18/0 | DC2+0 | 24° 50' 58.2" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 372.8444 | 375 |  | 13500 | 375 | [8 empty] | 36
111 | 18/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 379.8034 | 380 |  | 13680 | 380 | [8 empty] | 36
112 | 18/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 370.9967 | 375 |  | 13500 | 375 | [8 empty] | 36
113 | 18/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 398.7009 | 400 |  | 14400 | 400 | [8 empty] | 42
114 | 18/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 380.8207 | 385 |  | 13860 | 385 | [8 empty] | 36
115 | 19/0 | DC2+0 | 28° 14' 9.24" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 366.8761 | 370 |  | 13320 | 370 | [8 empty] | 36
116 | 19/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 372.5001 | 375 |  | 13500 | 375 | [8 empty] | 36
117 | 19/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 376.4596 | 380 |  | 13680 | 380 | [8 empty] | 36
118 | 19/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 384.2838 | 385 |  | 13860 | 385 | [8 empty] | 36
119 | 19/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 375.36 | 380 |  | 13680 | 380 | [8 empty] | 36
120 | 19/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 381.2426 | 385 |  | 13860 | 385 | [8 empty] | 36
121 | 20/0 | DB2+0 | 12° 15' 49.68" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 386.781 | 390 |  | 14040 | 390 | [8 empty] | 36
122 | 20/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 387.0413 | 390 |  | 14040 | 390 | [8 empty] | 36
123 | 20/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 348.4661 | 350 |  | 12600 | 350 | [8 empty] | 36
124 | 20/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 354.9658 | 355 |  | 12780 | 355 | [8 empty] | 36
125 | 21/0 | DB2+0 | 14° 55' 19.2" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 414.9035 | 415 |  | 14940 | 415 | [8 empty] | 42
126 | 21/1 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 407.2354 | 410 |  | 14760 | 410 | [8 empty] | 42
127 | 21/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 432.227 | 435 |  | 15660 | 435 | [8 empty] | 42
128 | 21/3 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 401.8715 | 405 |  | 14580 | 405 | [8 empty] | 42
129 | 21/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 434.1793 | 435 |  | 15660 | 435 | [8 empty] | 42
130 | 21/5 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 405.5004 | 410 |  | 14760 | 410 | [8 empty] | 42
131 | 21/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 426.0147 | 430 |  | 15480 | 430 | [8 empty] | 42
132 | 21/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.9044 | 410 |  | 14760 | 410 | [8 empty] | 42
133 | 21/8 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 433.2535 | 435 |  | 15660 | 435 | [8 empty] | 42
134 | 21/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 372.8965 | 375 |  | 13500 | 375 | [8 empty] | 36
135 | 21/10 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 443.5385 | 445 |  | 16020 | 445 | [8 empty] | 42
136 | 22/0 | DB2+3 | 09° 09' 25.92" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 456.3484 | 460 |  | 16560 | 460 | [8 empty] | 48
137 | 22/1 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 379.1989 | 380 |  | 13680 | 380 | [8 empty] | 36
138 | 22/2 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 382.6221 | 385 |  | 13860 | 385 | [8 empty] | 36
139 | 22/3 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 435.556 | 440 |  | 15840 | 440 | [8 empty] | 42
140 | 22/4 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 402.063 | 405 |  | 14580 | 405 | [8 empty] | 42
141 | 22/5 | DA+9,2RC | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 417.315 | 420 |  | 15120 | 420 | [8 empty] | 42
142 | 22/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 347.7023 | 350 |  | 12600 | 350 | [8 empty] | 36
143 | 22/7 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 356.2447 | 360 |  | 12960 | 360 | [8 empty] | 36
144 | 22/8 | DB1+0 | 00° 00' 00" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 389.1929 | 390 |  | 14040 | 390 | [8 empty] | 36
145 | 22/9 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 343.7755 | 345 |  | 12420 | 345 | [8 empty] | 36
146 | 22/10 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 395.4872 | 400 |  | 14400 | 400 | [8 empty] | 42
147 | 22/11 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.0325 | 410 |  | 14760 | 410 | [8 empty] | 42
148 | 22/12 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 318.0022 | 320 |  | 11520 | 320 | [8 empty] | 30
149 | 22/13 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 447.3191 | 450 |  | 16200 | 450 | [8 empty] | 42
150 | 23/0 | DD45+3 | 34° 59' 23.64" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 222.1547 | 225 |  | 8100 | 225 | [8 empty] | 24
151 | 24/0 | DD45+3 | 32° 40' 24.96" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 433.8892 | 435 |  | 15660 | 435 | [8 empty] | 42
152 | 25/0 | DC1+6 | 15° 53' 08.16" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 422.3316 | 425 |  | 15300 | 425 | [8 empty] | 42
153 | 25/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 370.741 | 375 |  | 13500 | 375 | [8 empty] | 36
154 | 25/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 345.6754 | 350 |  | 12600 | 350 | [8 empty] | 36
155 | 25/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 391.1224 | 395 |  | 14220 | 395 | [8 empty] | 42
156 | 25/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 440.4075 | 445 |  | 16020 | 445 | [8 empty] | 42
157 | 26/0 | DB1+0 | 00° 51' 11.52" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 391.3642 | 395 |  | 14220 | 395 | [8 empty] | 42
158 | 26/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.4695 | 410 |  | 14760 | 410 | [8 empty] | 42
159 | 26/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 418.0221 | 420 |  | 15120 | 420 | [8 empty] | 42
160 | 26/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 422.5967 | 425 |  | 15300 | 425 | [8 empty] | 42
161 | 26/4 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 409.9767 | 410 |  | 14760 | 410 | [8 empty] | 42
162 | 26/5 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 363.3821 | 365 |  | 13140 | 365 | [8 empty] | 36
163 | 26/6 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 421.855 | 425 |  | 15300 | 425 | [8 empty] | 42
164 | 26/7 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 416.722 | 420 |  | 15120 | 420 | [8 empty] | 42
165 | 26/8 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 413.7851 | 415 |  | 14940 | 415 | [8 empty] | 42
166 | 27/0 | DC1+0 | 19° 33' 38.16" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 399.7558 | 400 |  | 14400 | 400 | [8 empty] | 42
167 | 27/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 425.1788 | 430 |  | 15480 | 430 | [8 empty] | 42
168 | 27/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 398.5615 | 400 |  | 14400 | 400 | [8 empty] | 42
169 | 27/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 430.6651 | 435 |  | 15660 | 435 | [8 empty] | 42
170 | 27/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 410.0124 | 415 |  | 14940 | 415 | [8 empty] | 42
171 | 27/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 402.5479 | 405 |  | 14580 | 405 | [8 empty] | 42
172 | 27/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 343.4996 | 345 |  | 12420 | 345 | [8 empty] | 36
173 | 27/7 | DB1+0 | 00° 00' 00" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 392.0031 | 395 |  | 14220 | 395 | [8 empty] | 42
174 | 27/8 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 381.088 | 385 |  | 13860 | 385 | [8 empty] | 36
175 | 27/9 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 366.2781 | 370 |  | 13320 | 370 | [8 empty] | 36
176 | 27/10 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 420.0871 | 425 |  | 15300 | 425 | [8 empty] | 42
177 | 27/11 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 420.7871 | 425 |  | 15300 | 425 | [8 empty] | 42
178 | 27/12 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.6348 | 410 |  | 14760 | 410 | [8 empty] | 42
179 | 28/0 | DB2+0 | 12° 53' 28.32" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 379.638 | 380 |  | 13680 | 380 | [8 empty] | 36
180 | 28/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 384.9995 | 385 |  | 13860 | 385 | [8 empty] | 36
181 | 28/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 369.0001 | 370 |  | 13320 | 370 | [8 empty] | 36
182 | 28/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.9999 | 410 |  | 14760 | 410 | [8 empty] | 42
183 | 28/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 422.0003 | 425 |  | 15300 | 425 | [8 empty] | 42
184 | 28/5 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 369.9993 | 370 |  | 13320 | 370 | [8 empty] | 36
185 | 28/6 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 463.9999 | 465 |  | 16740 | 465 | [8 empty] | 48
186 | 28/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 374.9999 | 375 |  | 13500 | 375 | [8 empty] | 36
187 | 28/8 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 465.4553 | 470 |  | 16920 | 470 | [8 empty] | 48
188 | 29/0 | DB1+0 | 06° 14' 21.84" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 365.5457 | 370 |  | 13320 | 370 | [8 empty] | 36
189 | 29/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 423.9992 | 425 |  | 15300 | 425 | [8 empty] | 42
190 | 29/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 398.9997 | 400 |  | 14400 | 400 | [8 empty] | 42
191 | 29/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 440.0007 | 445 |  | 16020 | 445 | [8 empty] | 42
192 | 29/4 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 382.099 | 385 |  | 13860 | 385 | [8 empty] | 36
193 | 30/0 | DC1+0 | 16° 15' 6.12" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 388.9012 | 390 |  | 14040 | 390 | [8 empty] | 36
194 | 30/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 444.9998 | 445 |  | 16020 | 445 | [8 empty] | 42
195 | 30/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 395.0004 | 400 |  | 14400 | 400 | [8 empty] | 42
196 | 30/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 386.999 | 390 |  | 14040 | 390 | [8 empty] | 36
197 | 30/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 442.0002 | 445 |  | 16020 | 445 | [8 empty] | 42
198 | 30/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 314 | 315 |  | 11340 | 315 | [8 empty] | 30
199 | 30/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 347.4341 | 350 |  | 12600 | 350 | [8 empty] | 36
200 | 31/0 | DB2+0 | 14° 44' 46.32" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 383.566 | 385 |  | 13860 | 385 | [8 empty] | 36
201 | 31/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 366.0003 | 370 |  | 13320 | 370 | [8 empty] | 36
202 | 31/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 332.9086 | 335 |  | 12060 | 335 | [8 empty] | 36
203 | 32/0 | DC1+0 | 21° 35' 19.68" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 402.6848 | 405 |  | 14580 | 405 | [8 empty] | 42
204 | 32/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 428.8084 | 430 |  | 15480 | 430 | [8 empty] | 42
205 | 32/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 410.8899 | 415 |  | 14940 | 415 | [8 empty] | 42
206 | 32/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 381.1058 | 385 |  | 13860 | 385 | [8 empty] | 36
207 | 32/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 451.5009 | 455 |  | 16380 | 455 | [8 empty] | 42
208 | 33/0 | DC1+0 | 20° 0' 49.32" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 379.5592 | 380 |  | 13680 | 380 | [8 empty] | 36
209 | 33/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 292.5322 | 295 |  | 10620 | 295 | [8 empty] | 30
210 | 34/0 | DB2+0 | 9° 34' 3.36" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 432.6365 | 435 |  | 15660 | 435 | [8 empty] | 42
211 | 34/1 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 407.4668 | 410 |  | 14760 | 410 | [8 empty] | 42
212 | 34/2 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 377.043 | 380 |  | 13680 | 380 | [8 empty] | 36
213 | 34/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 451.5759 | 455 |  | 16380 | 455 | [8 empty] | 42
214 | 34/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 379.2746 | 380 |  | 13680 | 380 | [8 empty] | 36
215 | 35/0 | DB2+6 | 13° 13' 27.12" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 265.5549 | 270 |  | 9720 | 270 | [8 empty] | 30
216 | 35/1 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 492.4032 | 495 |  | 17820 | 495 | [8 empty] | 48
217 | 35/2 | DB1+0 | [6 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 522.2211 | 525 |  | 18900 | 525 | [8 empty] | 48
218 | 35/3 | DB1+6 | [6 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 418.9247 | 420 |  | 15120 | 420 | [8 empty] | 42
219 | 35/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 421.6842 | 425 |  | 15300 | 425 | [8 empty] | 42
220 | 35/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 342.6969 | 345 |  | 12420 | 345 | [8 empty] | 36
221 | 36/0 | DB2+0 | 14° 55' 10.2" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 386.4336 | 390 |  | 14040 | 390 | [8 empty] | 36
222 | 36/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 309.4281 | 310 |  | 11160 | 310 | [8 empty] | 30
223 | 36/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 357.809 | 360 |  | 12960 | 360 | [8 empty] | 36
224 | 36/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 480.4387 | 485 |  | 17460 | 485 | [8 empty] | 48
225 | 36/4 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 350.467 | 355 |  | 12780 | 355 | [8 empty] | 36
226 | 37/0 | DB2+0 | 14° 56' 10.32" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 443.2869 | 445 |  | 16020 | 445 | [8 empty] | 42
227 | 37/1 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 356.6649 | 360 |  | 12960 | 360 | [8 empty] | 36
228 | 37/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 339.8786 | 340 |  | 12240 | 340 | [8 empty] | 36
229 | 37/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 500.2774 | 505 |  | 18180 | 505 | [8 empty] | 48
230 | 38/0 | DB2+6 | 9° 11' 45.24" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 421.4432 | 425 |  | 15300 | 425 | [8 empty] | 42
231 | 38/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 419.0234 | 420 |  | 15120 | 420 | [8 empty] | 42
232 | 38/2 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 420.3291 | 425 |  | 15300 | 425 | [8 empty] | 42
233 | 38/3 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 414.8948 | 415 |  | 14940 | 415 | [8 empty] | 42
234 | 38/4 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 425.4898 | 430 |  | 15480 | 430 | [8 empty] | 42
235 | 39/0 | DB2+6 | 14° 1' 20.28" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 412.6384 | 415 |  | 14940 | 415 | [8 empty] | 42
236 | 39/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 322.6107 | 325 |  | 11700 | 325 | [8 empty] | 30
237 | 40/0 | DC2+0 | 21° 42' 13.68" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 396.2 | 400 |  | 14400 | 400 | [8 empty] | 42
238 | 40/1 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 425.8095 | 430 |  | 15480 | 430 | [8 empty] | 42
239 | 40/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 401.6882 | 405 |  | 14580 | 405 | [8 empty] | 42
240 | 40/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 436.3011 | 440 |  | 15840 | 440 | [8 empty] | 42
241 | 41/0 | DC1+6 | 16° 54' 46" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 340.7661 | 345 |  | 12420 | 345 | [8 empty] | 36
242 | 41/1 | DB1+9 | [6 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 447.8224 | 450 |  | 16200 | 450 | [8 empty] | 42
243 | 41/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 382.33 | 385 |  | 13860 | 385 | [8 empty] | 36
244 | 42/0 | DC1+0 | 17° 31' 50" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 384.711 | 385 |  | 13860 | 385 | [8 empty] | 36
245 | 42/1 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 407.3629 | 410 |  | 14760 | 410 | [8 empty] | 42
246 | 42/2 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 414.1741 | 415 |  | 14940 | 415 | [8 empty] | 42
247 | 42/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 256.3606 | 260 |  | 9360 | 260 | [8 empty] | 24
248 | 42/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 403.8393 | 405 |  | 14580 | 405 | [8 empty] | 42
249 | 42/5 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 396.7237 | 400 |  | 14400 | 400 | [8 empty] | 42
250 | 42/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 403.9326 | 405 |  | 14580 | 405 | [8 empty] | 42
251 | 43/0 | DB1+0 | 01° 56' 25" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 345.9876 | 350 |  | 12600 | 350 | [8 empty] | 36
252 | 43/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 475.7889 | 480 |  | 17280 | 480 | [8 empty] | 48
253 | 43/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 363.6483 | 365 |  | 13140 | 365 | [8 empty] | 36
254 | 43/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 431.8433 | 435 |  | 15660 | 435 | [8 empty] | 42
255 | 43/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 405.3048 | 410 |  | 14760 | 410 | [8 empty] | 42
256 | 43/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 427.8159 | 430 |  | 15480 | 430 | [8 empty] | 42
257 | 43/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 389.7576 | 390 |  | 14040 | 390 | [8 empty] | 36
258 | 43/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 449.5431 | 450 |  | 16200 | 450 | [8 empty] | 42
259 | 43/8 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 387.9766 | 390 |  | 14040 | 390 | [8 empty] | 36
260 | 43/9 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 346.3318 | 350 |  | 12600 | 350 | [8 empty] | 36
261 | 43/10 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 444.8433 | 445 |  | 16020 | 445 | [8 empty] | 42
262 | 43/11 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 383.9246 | 385 |  | 13860 | 385 | [8 empty] | 36
263 | 44/0 | DB1+3 | 6° 14' 24.0" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 384.3 | 385 |  | 13860 | 385 | [8 empty] | 36
264 | 44/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 359 | 360 |  | 12960 | 360 | [8 empty] | 36
265 | 44/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 334 | 335 |  | 12060 | 335 | [8 empty] | 36
266 | 44/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 395 | 395 |  | 14220 | 395 | [8 empty] | 42
267 | 44/4 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 355 | 355 |  | 12780 | 355 | [8 empty] | 36
268 | 44/5 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 485 | 485 |  | 17460 | 485 | [8 empty] | 48
269 | 44/6 | DB1+3 | 0° 0' 0" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 473 | 475 |  | 17100 | 475 | [8 empty] | 48
270 | 44/7 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 367 | 370 |  | 13320 | 370 | [8 empty] | 36
271 | 44/8 | DCT1+0 | 0° 0' 0" | [5 empty] | 48 | 4 | 12 |  | 4 | 4 |  |  |  | 30 | 72 | 2 |  | 2 |  |  | 4
|  |  |  | 430 | 430 |  | 15480 | 430 | [8 empty] | 42
272 | 44/9 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 365 | 365 |  | 13140 | 365 | [8 empty] | 36
273 | 44/10 | DB1+9 | 0° 0' 0" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 428 | 430 |  | 15480 | 430 | [8 empty] | 42
274 | 44/11 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 327.2 | 330 |  | 11880 | 330 | [8 empty] | 30
275 | 45/0 | DC2+0 | 24° 55' 38.28" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 354.9 | 355 |  | 12780 | 355 | [8 empty] | 36
276 | 45/1 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.43 | 410 |  | 14760 | 410 | [8 empty] | 42
277 | 46/0 | DD60+25 | 28° 47' 23" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 199.08 | 200 |  | 7200 | 200 | [8 empty] | 18
278 | 47/0 | DD60+25 | 47° 00' 03" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 441.2 | 445 |  | 16020 | 445 | [8 empty] | 42
279 | 47/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 395.9 | 400 |  | 14400 | 400 | [8 empty] | 42
280 | 47/2 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 417.4 | 420 |  | 15120 | 420 | [8 empty] | 42
281 | 47/3 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 358.4 | 360 |  | 12960 | 360 | [8 empty] | 36
282 | 47/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 461.2 | 465 |  | 16740 | 465 | [8 empty] | 48
283 | 47/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 377.3 | 380 |  | 13680 | 380 | [8 empty] | 36
284 | 47/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 431.5 | 435 |  | 15660 | 435 | [8 empty] | 42
285 | 47/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 398.8 | 400 |  | 14400 | 400 | [8 empty] | 42
286 | 47/8 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 405.9 | 410 |  | 14760 | 410 | [8 empty] | 42
287 | 47/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 433.7 | 435 |  | 15660 | 435 | [8 empty] | 42
288 | 47/10 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 386.2 | 390 |  | 14040 | 390 | [8 empty] | 36
289 | 48/0 | DC2+0 | 29°14'33.0" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 428.9 | 430 |  | 15480 | 430 | [8 empty] | 42
290 | 48/1 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 402.9 | 405 |  | 14580 | 405 | [8 empty] | 42
291 | 49/0 | DD45+0 | 33° 51' 14.4" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 379.1 | 380 |  | 13680 | 380 | [8 empty] | 36
292 | 49/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 386.6 | 390 |  | 14040 | 390 | [8 empty] | 36
293 | 49/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 390 | 390 |  | 14040 | 390 | [8 empty] | 36
294 | 49/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 421.7 | 425 |  | 15300 | 425 | [8 empty] | 42
295 | 49/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 396.6 | 400 |  | 14400 | 400 | [8 empty] | 42
296 | 49/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 412.8 | 415 |  | 14940 | 415 | [8 empty] | 42
297 | 49/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 340.2 | 345 |  | 12420 | 345 | [8 empty] | 36
298 | 49/7 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 500.2 | 505 |  | 18180 | 505 | [8 empty] | 48
299 | 50/0 | DB2+0 | 8° 23' 20.04" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 469.1 | 470 |  | 16920 | 470 | [8 empty] | 48
300 | 50/1 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 367.1 | 370 |  | 13320 | 370 | [8 empty] | 36
301 | 50/2 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 470.4 | 475 |  | 17100 | 475 | [8 empty] | 48
302 | 50/3 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 354.8 | 355 |  | 12780 | 355 | [8 empty] | 36
303 | 50/4 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 442.1 | 445 |  | 16020 | 445 | [8 empty] | 42
304 | 50/5 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 364.4 | 365 |  | 13140 | 365 | [8 empty] | 36
305 | 50/6 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 470.8 | 475 |  | 17100 | 475 | [8 empty] | 48
306 | 50/7 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 345 | 345 |  | 12420 | 345 | [8 empty] | 36
307 | 50/8 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 364.4 | 365 |  | 13140 | 365 | [8 empty] | 36
308 | 50/9 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 394.6 | 395 |  | 14220 | 395 | [8 empty] | 42
309 | 50/10 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 401.4 | 405 |  | 14580 | 405 | [8 empty] | 42
310 | 51/0 | DC2+0 | 25° 51' 48.24" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 356.6 | 360 |  | 12960 | 360 | [8 empty] | 36
311 | 51/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 307.1 | 310 |  | 11160 | 310 | [8 empty] | 30
312 | 51/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 385 | 385 |  | 13860 | 385 | [8 empty] | 36
313 | 52/0 | DC2+0 | 22° 21' 21.96" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 402 | 405 |  | 14580 | 405 | [8 empty] | 42
314 | 52/1 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 402.6 | 405 |  | 14580 | 405 | [8 empty] | 42
315 | 52/2 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 437 | 440 |  | 15840 | 440 | [8 empty] | 42
316 | 52/3 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 393.8 | 395 |  | 14220 | 395 | [8 empty] | 42
317 | 52/4 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 447 | 450 |  | 16200 | 450 | [8 empty] | 42
318 | 52/5 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 373 | 375 |  | 13500 | 375 | [8 empty] | 36
319 | 52/6 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.8 | 410 |  | 14760 | 410 | [8 empty] | 42
320 | 52/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 433 | 435 |  | 15660 | 435 | [8 empty] | 42
321 | 52/8 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 399.7 | 400 |  | 14400 | 400 | [8 empty] | 42
322 | 52/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 384.1 | 385 |  | 13860 | 385 | [8 empty] | 36
323 | 52/10 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 455.9 | 460 |  | 16560 | 460 | [8 empty] | 48
324 | 53/0 | DB2+9 | 6° 57' 38.88" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 433.2 | 435 |  | 15660 | 435 | [8 empty] | 42
325 | 53/1 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 407.4 | 410 |  | 14760 | 410 | [8 empty] | 42
326 | 53/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 394.5 | 395 |  | 14220 | 395 | [8 empty] | 42
327 | 53/3 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 410.1 | 415 |  | 14940 | 415 | [8 empty] | 42
328 | 53/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 428.1 | 430 |  | 15480 | 430 | [8 empty] | 42
329 | 53/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.6 | 410 |  | 14760 | 410 | [8 empty] | 42
330 | 53/6 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 411.3 | 415 |  | 14940 | 415 | [8 empty] | 42
331 | 53/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 427.8 | 430 |  | 15480 | 430 | [8 empty] | 42
332 | 53/8 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 371.3 | 375 |  | 13500 | 375 | [8 empty] | 36
333 | 54/0 | DB1+6 | 6° 44' 37.68" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 365.1 | 370 |  | 13320 | 370 | [8 empty] | 36
334 | 54/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 381 | 385 |  | 13860 | 385 | [8 empty] | 36
335 | 54/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 417 | 420 |  | 15120 | 420 | [8 empty] | 42
336 | 54/3 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 423.3 | 425 |  | 15300 | 425 | [8 empty] | 42
337 | 54/4 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 401 | 405 |  | 14580 | 405 | [8 empty] | 42
338 | 54/5 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 424 | 425 |  | 15300 | 425 | [8 empty] | 42
339 | 55/0 | DB1+6 | 2° 29' 53.88" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 404.9 | 405 |  | 14580 | 405 | [8 empty] | 42
340 | 55/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 343.1 | 345 |  | 12420 | 345 | [8 empty] | 36
341 | 55/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 357.7 | 360 |  | 12960 | 360 | [8 empty] | 36
342 | 55/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 365.2 | 370 |  | 13320 | 370 | [8 empty] | 36
343 | 55/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 350.1 | 355 |  | 12780 | 355 | [8 empty] | 36
344 | 55/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 357.7 | 360 |  | 12960 | 360 | [8 empty] | 36
345 | 55/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 337.8 | 340 |  | 12240 | 340 | [8 empty] | 36
346 | 55/7 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 422.8 | 425 |  | 15300 | 425 | [8 empty] | 42
347 | 55/8 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 460.49 | 465 |  | 16740 | 465 | [8 empty] | 48
348 | 56/0 | DD60+25 | 5° 23' 07" LT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 219.76 | 220 |  | 7920 | 220 | [8 empty] | 24
349 | 57/0 | DD60+25 | 0° 16' 10" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 461.11 | 465 |  | 16740 | 465 | [8 empty] | 48
350 | 57/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 432.3 | 435 |  | 15660 | 435 | [8 empty] | 42
351 | 57/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 405.4 | 410 |  | 14760 | 410 | [8 empty] | 42
352 | 57/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 418.2 | 420 |  | 15120 | 420 | [8 empty] | 42
353 | 57/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 416.8 | 420 |  | 15120 | 420 | [8 empty] | 42
354 | 57/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 395 | 395 |  | 14220 | 395 | [8 empty] | 42
355 | 57/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 401.8 | 405 |  | 14580 | 405 | [8 empty] | 42
356 | 57/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 433.9 | 435 |  | 15660 | 435 | [8 empty] | 42
357 | 58/0 | DC1+3 | 19° 22' 13.08" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 238.897 | 240 |  | 8640 | 240 | [8 empty] | 24
358 | 59/0 | DC2+0 | 27° 51' 8.64" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 411.3 | 415 |  | 14940 | 415 | [8 empty] | 42
359 | 59/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 418.204 | 420 |  | 15120 | 420 | [8 empty] | 42
360 | 59/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 412.3 | 415 |  | 14940 | 415 | [8 empty] | 42
361 | 59/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 421 | 425 |  | 15300 | 425 | [8 empty] | 42
362 | 59/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 419.7 | 420 |  | 15120 | 420 | [8 empty] | 42
363 | 59/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 419.1 | 420 |  | 15120 | 420 | [8 empty] | 42
364 | 59/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.8 | 410 |  | 14760 | 410 | [8 empty] | 42
365 | 59/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 426.9 | 430 |  | 15480 | 430 | [8 empty] | 42
366 | 59/8 | DB1+3 | 0° 0' 0" | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 434.7 | 435 |  | 15660 | 435 | [8 empty] | 42
367 | 59/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400.8 | 405 |  | 14580 | 405 | [8 empty] | 42
368 | 59/10 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 436.3 | 440 |  | 15840 | 440 | [8 empty] | 42
369 | 59/11 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 393.1 | 395 |  | 14220 | 395 | [8 empty] | 42
370 | 59/12 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 447.4 | 450 |  | 16200 | 450 | [8 empty] | 42
371 | 59/13 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 391.1 | 395 |  | 14220 | 395 | [8 empty] | 42
372 | 59/14 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 448.6 | 450 |  | 16200 | 450 | [8 empty] | 42
373 | 59/15 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 388 | 390 |  | 14040 | 390 | [8 empty] | 36
374 | 59/16 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 438 | 440 |  | 15840 | 440 | [8 empty] | 42
375 | 60/0 | DC1+0 | 20° 22' 38.64" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 413.8 | 415 |  | 14940 | 415 | [8 empty] | 42
376 | 60/1 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 424.2 | 425 |  | 15300 | 425 | [8 empty] | 42
377 | 60/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 414.5 | 415 |  | 14940 | 415 | [8 empty] | 42
378 | 60/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 425.6 | 430 |  | 15480 | 430 | [8 empty] | 42
379 | 60/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 412.3 | 415 |  | 14940 | 415 | [8 empty] | 42
380 | 60/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 374.1 | 375 |  | 13500 | 375 | [8 empty] | 36
381 | 60/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 410.1 | 415 |  | 14940 | 415 | [8 empty] | 42
382 | 60/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400.4 | 405 |  | 14580 | 405 | [8 empty] | 42
383 | 60/8 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 409.2 | 410 |  | 14760 | 410 | [8 empty] | 42
384 | 60/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 401 | 405 |  | 14580 | 405 | [8 empty] | 42
385 | 60/10 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 394.5 | 395 |  | 14220 | 395 | [8 empty] | 42
386 | 60/11 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 397.9 | 400 |  | 14400 | 400 | [8 empty] | 42
387 | 61/0 | DB2+0 | 13° 28' 15.24" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4 |  | kuddus Ali-23.10.2024
|  |  |  | 405.7 | 410 |  | 14760 | 410 | [8 empty] | 42
388 | 61/1 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 433.2 | 435 |  | 15660 | 435 | [8 empty] | 42
389 | 61/2 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400.9 | 405 |  | 14580 | 405 | [8 empty] | 42
390 | 61/3 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 427 | 430 |  | 15480 | 430 | [8 empty] | 42
391 | 61/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 413.9 | 415 |  | 14940 | 415 | [8 empty] | 42
392 | 61/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 426.4 | 430 |  | 15480 | 430 | [8 empty] | 42
393 | 61/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 411.5 | 415 |  | 14940 | 415 | [8 empty] | 42
394 | 61/7 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 376.3 | 380 |  | 13680 | 380 | [8 empty] | 36
395 | 61/8 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 433.4 | 435 |  | 15660 | 435 | [8 empty] | 42
396 | 61/9 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 405.6 | 410 |  | 14760 | 410 | [8 empty] | 42
397 | 61/10 | DA+9 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 434.3 | 435 |  | 15660 | 435 | [8 empty] | 42
398 | 62/0 | DB2+0 | 7° 27' 29.88" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4 |  | Kuddus Ali- 11.11.2024
|  |  |  | 418 | 420 |  | 15120 | 420 | [8 empty] | 42
399 | 62/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 386 | 390 |  | 14040 | 390 | [8 empty] | 36
400 | 62/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400 | 400 |  | 14400 | 400 | [8 empty] | 42
401 | 62/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 401 | 405 |  | 14580 | 405 | [8 empty] | 42
402 | 62/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 403 | 405 |  | 14580 | 405 | [8 empty] | 42
403 | 62/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 404 | 405 |  | 14580 | 405 | [8 empty] | 42
404 | 62/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 423 | 425 |  | 15300 | 425 | [8 empty] | 42
405 | 62/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 409 | 410 |  | 14760 | 410 | [8 empty] | 42
406 | 62/8 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 409 | 410 |  | 14760 | 410 | [8 empty] | 42
407 | 62/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 411 | 415 |  | 14940 | 415 | [8 empty] | 42
408 | 62/10 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 413 | 415 |  | 14940 | 415 | [8 empty] | 42
409 | 62/11 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 386.1 | 390 |  | 14040 | 390 | [8 empty] | 36
410 | 63/0 | DC1+0 | 18° 26' 28.68" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 400 | 400 |  | 14400 | 400 | [8 empty] | 42
411 | 63/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 416 | 420 |  | 15120 | 420 | [8 empty] | 42
412 | 63/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 411 | 415 |  | 14940 | 415 | [8 empty] | 42
413 | 63/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 399 | 400 |  | 14400 | 400 | [8 empty] | 42
414 | 63/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 413 | 415 |  | 14940 | 415 | [8 empty] | 42
415 | 63/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 426 | 430 |  | 15480 | 430 | [8 empty] | 42
416 | 63/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 413 | 415 |  | 14940 | 415 | [8 empty] | 42
417 | 63/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 425 | 425 |  | 15300 | 425 | [8 empty] | 42
418 | 63/8 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.3 | 410 |  | 14760 | 410 | [8 empty] | 42
419 | 64/0 | DB2+0 | 13° 49' 10.2" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 375.1 | 380 |  | 13680 | 380 | [8 empty] | 36
420 | 64/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.7 | 410 |  | 14760 | 410 | [8 empty] | 42
421 | 64/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 410.7 | 415 |  | 14940 | 415 | [8 empty] | 42
422 | 64/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.2 | 410 |  | 14760 | 410 | [8 empty] | 42
423 | 64/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 426.2 | 430 |  | 15480 | 430 | [8 empty] | 42
424 | 64/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 407.7 | 410 |  | 14760 | 410 | [8 empty] | 42
425 | 64/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 401.6 | 405 |  | 14580 | 405 | [8 empty] | 42
426 | 64/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 425.5 | 430 |  | 15480 | 430 | [8 empty] | 42
427 | 64/8 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 414.4 | 415 |  | 14940 | 415 | [8 empty] | 42
428 | 64/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 410.6 | 415 |  | 14940 | 415 | [8 empty] | 42
429 | 64/10 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 428.4 | 430 |  | 15480 | 430 | [8 empty] | 42
430 | 64/11 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400.6 | 405 |  | 14580 | 405 | [8 empty] | 42
431 | 65/0 | DB1+0 | 2° 32' 0.6" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 395.4 | 400 |  | 14400 | 400 | [8 empty] | 42
432 | 65/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 393.7 | 395 |  | 14220 | 395 | [8 empty] | 42
433 | 65/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 403.7 | 405 |  | 14580 | 405 | [8 empty] | 42
434 | 65/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 402.9 | 405 |  | 14580 | 405 | [8 empty] | 42
435 | 65/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 376.4 | 380 |  | 13680 | 380 | [8 empty] | 36
436 | 65/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 389.2 | 390 |  | 14040 | 390 | [8 empty] | 36
437 | 65/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 397.6 | 400 |  | 14400 | 400 | [8 empty] | 42
438 | 65/7 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 394.3 | 395 |  | 14220 | 395 | [8 empty] | 42
439 | 65/8 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 389 | 390 |  | 14040 | 390 | [8 empty] | 36
440 | 65/9 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 379.1 | 380 |  | 13680 | 380 | [8 empty] | 36
441 | 65/10 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 387.6 | 390 |  | 14040 | 390 | [8 empty] | 36
442 | 65/11 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 426.9 | 430 |  | 15480 | 430 | [8 empty] | 42
443 | 66/0 | DC2+6 | 22° 23' 34.44" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 207.8 | 210 |  | 7560 | 210 | [8 empty] | 18
444 | 67/0 | DC1+9 | 17° 55' 44.04" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 347.1 | 350 |  | 12600 | 350 | [8 empty] | 36
445 | 67/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 344.9 | 345 |  | 12420 | 345 | [8 empty] | 36
446 | 67/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 369.2 | 370 |  | 13320 | 370 | [8 empty] | 36
447 | 68/0 | DD45+0 | 42° 20' 12.84" RT | [5 empty] | 48 | 6 | 12 |  | 6 |  |  |  |  | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 200.9 | 205 |  | 7380 | 205 | [8 empty] | 18
448 | 69/0 | DB2+0 | 12° 32' 12.12" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 374.1 | 375 |  | 13500 | 375 | [8 empty] | 36
449 | 69/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 394.9 | 395 |  | 14220 | 395 | [8 empty] | 42
450 | 70/0 | DC1+0 | 19° 34' 30.72" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 388.4 | 390 |  | 14040 | 390 | [8 empty] | 36
451 | 70/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 418.9 | 420 |  | 15120 | 420 | [8 empty] | 42
452 | 70/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 418.6 | 420 |  | 15120 | 420 | [8 empty] | 42
453 | 70/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 414 | 415 |  | 14940 | 415 | [8 empty] | 42
454 | 70/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 419.6 | 420 |  | 15120 | 420 | [8 empty] | 42
455 | 70/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 420.3 | 425 |  | 15300 | 425 | [8 empty] | 42
456 | 70/6 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 419.6 | 420 |  | 15120 | 420 | [8 empty] | 42
457 | 70/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 418.2 | 420 |  | 15120 | 420 | [8 empty] | 42
458 | 70/8 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 414.1 | 415 |  | 14940 | 415 | [8 empty] | 42
459 | 70/9 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 406.1 | 410 |  | 14760 | 410 | [8 empty] | 42
460 | 70/10 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.6 | 410 |  | 14760 | 410 | [8 empty] | 42
461 | 70/11 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 420.4 | 425 |  | 15300 | 425 | [8 empty] | 42
462 | 71/0 | DB2+3 | 9° 37' 5.52" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 398.6 | 400 |  | 14400 | 400 | [8 empty] | 42
463 | 71/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 414.3 | 415 |  | 14940 | 415 | [8 empty] | 42
464 | 71/2 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 413 | 415 |  | 14940 | 415 | [8 empty] | 42
465 | 71/3 | DA+6 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 367.7 | 370 |  | 13320 | 370 | [8 empty] | 36
466 | 71/4 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 429.4 | 430 |  | 15480 | 430 | [8 empty] | 42
467 | 71/5 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408 | 410 |  | 14760 | 410 | [8 empty] | 42
468 | 71/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 404.9 | 405 |  | 14580 | 405 | [8 empty] | 42
469 | 71/7 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 431.6 | 435 |  | 15660 | 435 | [8 empty] | 42
470 | 71/8 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 408.4 | 410 |  | 14760 | 410 | [8 empty] | 42
471 | 72/0 | DB2+3 | 10° 39' 52.92" LT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 435.3 | 440 |  | 15840 | 440 | [8 empty] | 42
472 | 72/1 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 403.9 | 405 |  | 14580 | 405 | [8 empty] | 42
473 | 72/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 389.2 | 390 |  | 14040 | 390 | [8 empty] | 36
474 | 72/3 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 400.1 | 405 |  | 14580 | 405 | [8 empty] | 42
475 | 73/0 | DB2+0 | 13° 10' 26.4" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
|  |  |  | 383.3 | 385 |  | 13860 | 385 | [8 empty] | 36
476 | 73/1 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 379 | 380 |  | 13680 | 380 | [8 empty] | 36
477 | 73/2 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 381.2 | 385 |  | 13860 | 385 | [8 empty] | 36
478 | 73/3 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 384.7 | 385 |  | 13860 | 385 | [8 empty] | 36
479 | 73/4 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 368.8 | 370 |  | 13320 | 370 | [8 empty] | 36
480 | 73/5 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 365.5 | 370 |  | 13320 | 370 | [8 empty] | 36
481 | 73/6 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 392.4 | 395 |  | 14220 | 395 | [8 empty] | 42
482 | 73/7 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 374.9 | 375 |  | 13500 | 375 | [8 empty] | 36
483 | 73/8 | DA+3 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 379.5 | 380 |  | 13680 | 380 | [8 empty] | 36
484 | 73/9 | DA+0 | [7 empty] | 12 |  | 6 | [8 empty] | 1 | 1 |  |  | 2
|  |  |  | 378.9 | 380 |  | 13680 | 380 | [8 empty] | 36
485 | 74/0 | DB2+0 | 9° 59' 12.84" RT | [5 empty] | 48 |  | 12 | [6 empty] | 30 |  | 2 |  | 2 |  |  | 4
Total |  |  |  | 191640.534 |  |  | 6940620 | 192795 | 4272 | 4876 | 1068 | 2382 | 106 | 4 | 0 | 0 | 19188 | 2670 | 72 | 178 | 397 | 574 | 0 | 0 | 1150 | 0
Wastage (0.75%) | [6 empty] | 52054.65 | 1445.9625
Total required | [6 empty] | 6992674.65 | 194240.9625

## OPGW
Progress Summary'!A1
Name of Project : 765KV D/C Fatehgarh- Beawar Transmission Line
OPGW
SL. No. | Section |  | Gang Name | Section Length | Paying out |  |  |  | Final Sag |  |  |  | Completion Month | Splicing | Splicing done by
| From | To |  |  | Section Length | Start Date | End Date | Remarks | Section Length | Start Date | End Date | Remarks
1 | 59/0 | 59/8 | Congent Technology | 3.337 | 3.337 | 10.02.25 | 11.02.25 |  | 3.337 | 2024-09-09 | 2024-09-16 | Final sag completed | 2024-09-01 | 2025-03-05 | Revant Sharma
2 | 59/8 | 60/0 | Congent Technology | 3.778 | 3.778 | 12.02.25 | 13.02.25 |  | 3.778 | 2024-09-26 | 2024-10-03 | Final sag completed | 2024-10-01 | 2025-02-26 | Revant Sharma
3 | 60/0 | 61/0 | Congent Technology | 4.877 | 4.877 | 15.02.25 | 16.02.25 |  | 4.877 | 2024-10-17 | 2024-10-22 | Final sag completed | 2024-10-01
4 | 61/0 | 62/0 | Congent Technology | 4.568 | 4.568 | 19.02.25 | 19.02.25 |  | 4.568 | 2024-10-31 | 2024-11-06 | Final sag completed | 2024-11-01 | 2025-02-27 | Revant Sharma
5 | 62/0 | 63/0 | Congent Technology | 4.863 | 4.863 | 23.02.25 | 24.02.25 |  | 4.863 | 2024-11-13 | 2024-11-16 | Final sag completed | 2024-11-01
6 | 63/0 | 64/0 | Congent Technology | 3.711 | 3.711 | 01.03.25 | 02.03.25 |  | 3.711 | 2025-01-04 | 2025-01-09 | Final sag completed | 2025-01-01
7 | 64/0 | 65/0 | Congent Technology | 4.918 | 4.918 | 03.03.25 | 03.03.25 |  | 4.918 | 2025-01-12 | 2025-01-15 | Final sag completed | 2025-01-01
TOTAL |  |  |  | 30.052 |  |  |  |  | 30.052

## Visual chart
Progress Summary'!A1
| Project Name :- Beawar 765 KV D/C Line, (TB-408 PKG-F) | [15 empty] | Progress Legends
| Progress Status as on dated | [5 empty] | 2025-10-06
| Sr. No. |  | Description |  |  |  | UOM |  | Total qty |  | Completed |  |  | Balance |  | WIP |  |  |  |  | Stringing WIP | [22 empty] | Identification for auto fill linked with Summary of visual chart
| 1 |  | Foundation |  |  |  | Nos |  | 485 |  | 415 |  |  | 70 |  | 13 |  |  |  |  | Erection U/P
| 2 |  | Earthing |  |  |  | Nos |  | 485 |  | 409 |  |  | 76 |  | 0 |  |  |  |  | Tackwelding U/P | [30 empty] | E
| 3 |  | Tower Erection |  |  |  | Nos |  | 485 |  | 222 |  |  | 263 |  | 2 |  |  |  |  | Foundation U/P
| 4 |  | Tack-Welding |  |  |  | Nos |  | 485 |  | 165 |  |  | 320 | [6 empty] | Earthing U/P
| 5 |  | Rough Sag |  |  |  | KM |  | 193.36 |  | 43.509 |  |  | 149.851 |  | 0 | [27 empty] | Sandy | Dry | DFR
| 6 |  | Final Sag |  |  |  | KM |  | 193.36 |  | 43.509 |  |  | 149.851 |  | 0 | [34 empty] | C
| Legends & Quantity | [19 empty] | Final Sag Completed
[14 empty] | NH | [6 empty] | Paying out Completed
|  |  | B Type Towers | [6 empty] | Forest |  |  |  | 3 No's/1 No's | [6 empty] | Erection Completed
|  |  | C & D type towers | [17 empty] | Welding Completed
|  | 132/220 KV Line |  |  |  | 400 KV |  |  | Gas Pipe Line | [9 empty] | DFR |  | FDN Completed | [22 empty] | FOUNDATION | [6 empty] | EARTHING | ERECTION | Welding | P/O | FS | Total Section Length | P/0 WIP | Paying out Completed | Final Sag Completed
|  | 3 No's/2 No's |  |  |  | 4 No's |  |  | 1 No's | [9 empty] | C |  | Earthing Completed | [22 empty] | SANDY | DRY | DFR | WFR | FS | Total FDN | FDN WIP | C | E | Done | PO | FS |  | . | .. | ,
[19 empty] | LE |  | Leg Extension A,B,C,D | [22 empty] | 177 | 184 | 52 | 2 | 0 | 415 | 13 | 409 | 222 | 165 | 0 | 0 | 191393.448 | 0 | 0 | 43509.004
| 0 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21
| Gty |  | 1/0 |  | 1A/0 |  | 1A/1 |  | 1A/2 |  | 1A/3 |  | 1A/4 |  | 1A/5 |  | 1A/6 |  | 1A/7 |  | 1A/8 |  | 2/0 |  | 2/1 |  | 2/2 |  | 2/3 |  | 2/4 |  | 2/5 |  | 2/6 |  | 2/7 |  | 2/8 |  | 2/9 |  | 3/0
[57 empty] | 0 | 0 | 0
| ERE | [5 empty] | E |  | E |  | E
WELD
|  | 122 | DRY | 90 | DRY | 277.7 | DFR | 386 | DRY | 443.6 | DRY | 333.4 | DFR | 431.9 | DRY | 348.7 | Sandy | 395.7 | Sandy | 415 | Sandy | 394.3 | DRY | 405.3 | Sandy | 338.5 | Sandy | 406 | Sandy | 429 | Sandy | 411.6 | Sandy | 425.7 | Sandy | 408.2 | WIP | 354.6 | Sandy | 308.7 |  | 336 | WIP | 10 | 6 | 2 | 0 | 0 | 18 | 2 | 17 | 3 | 0 |  |  | 7461.9
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
|  |  | DD60+0 |  | DD60+0 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DC1+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DD60+6
|  |  | ,,, |  | ,,, |  | ,,, |  | ,1,1, |  | ,,, |  | ,,1, |  | 1,1,, |  | 1,,,1 |  | ,1,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,1 |  | 1,,1,1 |  | ,,, |  | ,,1,1 |  | ,,,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42
|  |  | 4/0 |  | 4/1 |  | 4/2 |  | 4/3 |  | 4/4 |  | 5/0 |  | 6/0 |  | 6/1 |  | 6/2 |  | 7/0 |  | 8/0 |  | 8/1 |  | 8/2 |  | 8/3 |  | 8/4 |  | 8/5 |  | 8/6 |  | 8/7 |  | 8/8 |  | 8/9 |  | 8/10
[57 empty] | 0 | 0 | 0
ERE
WELD
| FDN | 226.5 | DRY | 343.4 | WIP | 358.4 |  | 381 | DRY | 367.6 |  | 423.1 |  | 246 |  | 429.9 | DFR | 362.4 | DFR | 347.9 |  | 210.8 |  | 409.2 |  | 413.6 |  | 393.2 |  | 416.5 |  | 394.6 |  | 393.2 |  | 441.1 | DRY | 414.4 |  | 395.9 | DFR | 413.4 | DFR | 0 | 3 | 4 | 0 | 0 | 7 | 1 | 7 | 0 | 0 |  |  | 7782.1
| EAR |  | C | [5 empty] | C | [7 empty] | C |  | C | [17 empty] | C |  |  |  | C |  | C
| TOT |  | DD60+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+9 |  | DB2+9 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DB1+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+6 |  | DA+3 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 5,5,5,5 |  | 5,5,5,5 |  | ,,, |  | ,,, |  | 2,3,3,2 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60 |  | 61 |  | 62 |  | 63
|  |  | 8/11 |  | 8/12 |  | 9/0 |  | 10/0 |  | 10/1 |  | 10/2 |  | 10/3 |  | 10/4 |  | 10/5 |  | 10/6 |  | 10/7 |  | 10/8 |  | 10/9 |  | 10/10 |  | 10/11 |  | 10/12 |  | 10/13 |  | 10/14 |  | 10/15 |  | 10/16 |  | 10/17
[57 empty] | 0 | 0 | 0
| ERE | [13 empty] | E |  | E |  |  |  | E |  |  |  | E |  | E |  |  |  | E |  | E |  |  |  | E | [5 empty] | E
WELD
| FDN | 402.6 | DRY | 372.1 | WIP | 457.7 |  | 233.1 | WIP | 443.7 | WIP | 383.2 |  | 398.6 | DFR | 410.7 | DFR | 416.2 | DRY | 403.4 | DFR | 373.9 |  | 411.8 | DFR | 414.2 | DRY | 402.3 |  | 430.3 | DRY | 406.2 | DRY | 405.251 | DRY | 427.085 | DRY | 400.035 |  | 412.79 |  | 387.758 | DFR | 0 | 7 | 5 | 0 | 0 | 12 | 3 | 11 | 9 | 0 |  |  | 8392.919
| EAR | [13 empty] | C |  | C |  | C |  | C |  |  |  | C |  | C |  |  |  | C |  | C |  | C |  | C | [5 empty] | C
| TOT |  | DA+0 |  | DA+0 |  | DD60+18 |  | DD60+25 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70 |  | 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80 |  | 81 |  | 82 |  | 83 |  | 84
|  |  | 10/18 |  | 10/19 |  | 10/20 |  | 10/21 |  | 10/22 |  | 10/23 |  | 11/0 |  | 11/1 |  | 11/2 |  | 11/3 |  | 11/4 |  | 11/5 |  | 11A/0 |  | 11A/1 |  | 11A/2 |  | 11A/3 |  | 11A/4 |  | 11A/5 |  | 11A/6 |  | 11A/7 |  | 11A/8
[57 empty] | 0 | 0 | 0
| ERE |  | E |  | E |  | E |  | E | [15 empty] | E |  | E |  | E |  | E |  | E |  |  |  | E |  | E |  | E
WELD
| FDN | 436.732 | DFR | 403.689 | DRY | 409.528 | DFR | 419.56 | DFR | 369.467 |  | 403.73 |  | 368.825 |  | 385.289 |  | 409.446 |  | 385.819 |  | 449.057 |  | 368.102 | DFR | 342.28 | DRY | 405.1 | DRY | 412.2 | DRY | 412.2 | DRY | 422.1 | DRY | 418.3 | DRY | 384.3 | DRY | 434.2 | Sandy | 390.1 | Sandy | 2 | 8 | 4 | 0 | 0 | 14 | 0 | 14 | 12 | 0 |  |  | 8430.024
| EAR |  | C |  | C |  | C |  | C | [15 empty] | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+9 |  | DA+6
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 1,3,, |  | ,2,, |  | 1,4,,3 |  | ,,, |  | 2,1,, |  | ,,,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,2,4,1
REM
|  |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90 |  | 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100 |  | 101 |  | 102 |  | 103 |  | 104 |  | 105
|  |  | 11A/9 |  | 12/0 |  | 13/0 |  | 13/1 |  | 13/2 |  | 13/3 |  | 13/4 |  | 14/0 |  | 14A/0 |  | 14A/1 |  | 14A/2 |  | 15/0 |  | 15/1 |  | 16/0 |  | 16/1 |  | 16/2 |  | 16/3 |  | 16/4 |  | 16/5 |  | 17/0 |  | 17/1
[57 empty] | 0 | 0 | 0
| ERE |  | E | [7 empty] | E | [9 empty] | E | [5 empty] | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD | [25 empty] | Done | [7 empty] | Done |  | Done
| FDN | 426.3 | DRY | 405.9 | DRY | 211.9 | DRY | 464.3 | DRY | 373.7 | DRY | 419.7 | Sandy | 420.3 |  | 400 | Sandy | 381.4 |  | 407.8 | DRY | 401 | DRY | 383.3 | DRY | 404.6 | DRY | 413.3 | DRY | 364.3 | DRY | 414.3 | DRY | 340.3 | DRY | 394.7 | DRY | 425.9 | DRY | 396.8 | DRY | 393.7 | DRY | 2 | 17 | 0 | 0 | 0 | 19 | 0 | 18 | 12 | 3 |  |  | 8243.5
| EAR |  | C |  | C |  | C |  | C |  | C | [5 empty] | C |  |  |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DD60+0 |  | DD60+3 |  | DA+9 |  | DA+3 |  | DA+3 |  | DA+3 |  | DC2+0 |  | DC1+0 |  | DA+3 |  | DA+0 |  | DC1+0 |  | DA+3 |  | DC1+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB2+3 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,2,4 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 1,,,1 |  | ,,, |  | ,1,, |  | ,,, |  | ,,,1 |  | ,,,
REM
|  |  | 106 |  | 107 |  | 108 |  | 109 |  | 110 |  | 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120 |  | 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126
|  |  | 17/2 |  | 17/3 |  | 17/4 |  | 17/5 |  | 18/0 |  | 18/1 |  | 18/2 |  | 18/3 |  | 18/4 |  | 19/0 |  | 19/1 |  | 19/2 |  | 19/3 |  | 19/4 |  | 19/5 |  | 20/0 |  | 20/1 |  | 20/2 |  | 20/3 |  | 21/0 |  | 21/1
[57 empty] | 0 | 0 | 0
| ERE |  | E |  | E |  |  |  | E |  |  |  | E |  | E |  |  |  | E |  | E
| WELD | [11 empty] | Done
| FDN | 415.9 | DRY | 422.8 | DRY | 409.9 | DRY | 425.3 | DRY | 383.4 | DRY | 372.8 | DRY | 379.8 | DRY | 371 | DRY | 398.7 | DRY | 380.8 | DRY | 366.9 | DRY | 372.5 | DRY | 376.5 | DRY | 384.3 |  | 375.4 | WIP | 381.2 |  | 386.782 |  | 387.041 |  | 348.466 |  | 354.965 |  | 414.9 |  | 0 | 13 | 0 | 0 | 0 | 13 | 1 | 13 | 7 | 1 |  |  | 8109.354
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+3 |  | DC2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+6
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 127 |  | 128 |  | 129 |  | 130 |  | 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140 |  | 141 |  | 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147
|  |  | 21/2 |  | 21/3 |  | 21/4 |  | 21/5 |  | 21/6 |  | 21/7 |  | 21/8 |  | 21/9 |  | 21/10 |  | 22/0 |  | 22/1 |  | 22/2 |  | 22/3 |  | 22/4 |  | 22/5 |  | 22/6 |  | 22/7 |  | 22/8 |  | 22/9 |  | 22/10 |  | 22/11
[57 empty] | 0 | 0 | 0
ERE
WELD
| FDN | 407.2 |  | 432.2 |  | 401.9 |  | 434.2 | WIP | 405.5 |  | 426 | WIP | 406.9 |  | 433.3 | DFR | 372.9 | DRY | 443.5 |  | 456.4 | Sandy | 379.2 | Sandy | 382.6 | Sandy | 435.6 | Sandy | 402.1 | DRY | 417.3 | Sandy | 347.7 | Sandy | 356.3 | Sandy | 389.2 | Sandy | 343.8 |  | 395.5 | Sandy | 9 | 2 | 1 | 0 | 0 | 12 | 2 | 12 | 0 | 0 |  |  | 8469.3
| EAR | [15 empty] | C |  | C |  |  |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  |  |  | C
| TOT |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+6 |  | DB2+3 |  | DA+9 |  | DA+6 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+6 |  | DA+6 |  | DA+6
| LE |  | ,,, |  | ,,, |  | ,1,2,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,2 |  | ,,,1 |  | ,,, |  | 2,2,2,2 |  | ,,,1 |  | ,1,,1 |  | ,2,1,1 |  | ,,, |  | 1,2,, |  | ,2,,
REM
|  |  | 148 |  | 149 |  | 150 |  | 151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160 |  | 161 |  | 162 |  | 163 |  | 164 |  | 165 |  | 166 |  | 167 |  | 168
|  |  | 22/12 |  | 22/13 |  | 23/0 |  | 24/0 |  | 25/0 |  | 25/1 |  | 25/2 |  | 25/3 |  | 25/4 |  | 26/0 |  | 26/1 |  | 26/2 |  | 26/3 |  | 26/4 |  | 26/5 |  | 26/6 |  | 26/7 |  | 26/8 |  | 27/0 |  | 27/1 |  | 27/2
[57 empty] | 0 | 0 | 0
ERE
WELD
| FDN | 408 | Sandy | 318 | Sandy | 447.3 |  | 222.2 |  | 433.9 | DRY | 422.3 | DRY | 370.7 | DRY | 345.7 | Sandy | 391.1 | Sandy | 440.4 |  | 391.4 |  | 406.5 | DFR | 418 | DRY | 422.6 | Sandy | 410 | Sandy | 363.4 | Sandy | 421.9 | DFR | 416.7 |  | 413.8 | WIP | 399.8 | WIP | 425.2 | DFR | 7 | 4 | 3 | 0 | 0 | 14 | 2 | 12 | 0 | 0 |  |  | 8288.9
| EAR |  | C |  | C | [5 empty] | C |  | C |  | C |  | C |  | C | [9 empty] | C |  | C |  | C |  | C | [7 empty] | C
| TOT |  | DA+3 |  | DA+6 |  | DD45+3 |  | DD45+3 |  | DC1+6 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+6 |  | DA+6 |  | DA+0 |  | DA+6 |  | DC1+0 |  | DA+3 |  | DA+3
| LE |  | 1,2,, |  | ,,1, |  | 2,2,2,2 |  | 2,2,2,2 |  | ,,, |  | ,,, |  | ,,, |  | 1,2,,2 |  | 1,1,,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 1,,, |  | 1,1,, |  | ,1,1, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 169 |  | 170 |  | 171 |  | 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180 |  | 181 |  | 182 |  | 183 |  | 184 |  | 185 |  | 186 |  | 187 |  | 188 |  | 189
|  |  | 27/3 |  | 27/4 |  | 27/5 |  | 27/6 |  | 27/7 |  | 27/8 |  | 27/9 |  | 27/10 |  | 27/11 |  | 27/12 |  | 28/0 |  | 28/1 |  | 28/2 |  | 28/3 |  | 28/4 |  | 28/5 |  | 28/6 |  | 28/7 |  | 28/8 |  | 29/0 |  | 29/1
[57 empty] | 0 | 0 | 0
ERE
WELD
| FDN | 398.6 | DFR | 430.7 | DFR | 410 | DRY | 402.6 | Sandy | 343.5 | DFR | 392 | DFR | 381.1 | DFR | 366.3 | DFR | 420.1 | DRY | 420.8 | Sandy | 406.6 | DFR | 379.6 |  | 385 | DFR | 369 | DFR | 409 | Sandy | 422 | Sandy | 370 | Sandy | 464 | Sandy | 375 | Sandy | 465.5 | DRY | 365.6 | DRY | 7 | 4 | 9 | 0 | 0 | 20 | 0 | 20 | 0 | 0 |  |  | 8377
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  |  |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+9 |  | DA+6 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,2,, |  | 1,4,3, |  | 1,3,2, |  | ,,5,3 |  | ,,, |  | ,,,
REM
|  |  | 190 |  | 191 |  | 192 |  | 193 |  | 194 |  | 195 |  | 196 |  | 197 |  | 198 |  | 199 |  | 200 |  | 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207 |  | 208 |  | 209 |  | 210
|  |  | 29/2 |  | 29/3 |  | 29/4 |  | 30/0 |  | 30/1 |  | 30/2 |  | 30/3 |  | 30/4 |  | 30/5 |  | 30/6 |  | 31/0 |  | 31/1 |  | 31/2 |  | 32/0 |  | 32/1 |  | 32/2 |  | 32/3 |  | 32/4 |  | 33/0 |  | 33/1 |  | 34/0
[57 empty] | 0 | 0 | 0
ERE
WELD
| FDN | 424 | DRY | 399 | Sandy | 440 | DRY | 382.1 | DRY | 388.9 | Sandy | 445 | Sandy | 395 | Sandy | 387 | DRY | 442 | WIP | 314 |  | 347.4 |  | 383.6 | DRY | 366 | DRY | 332.9 | DRY | 402.7 | Sandy | 428.8 | DRY | 410.9 | Sandy | 381.1 | Sandy | 451.5 | DRY | 379.6 | DRY | 292.5 | DRY | 7 | 11 | 0 | 0 | 0 | 18 | 1 | 17 | 0 | 0 |  |  | 8194
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C | [9 empty] | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+0 |  | DA+6 |  | DC1+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DC1+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DC1+0 |  | DA+0 |  | DB2+0
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 2,,, |  | 1,2,, |  | 1,2,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 1,,, |  | ,1,1, |  | ,,,
REM
|  |  | 211 |  | 212 |  | 213 |  | 214 |  | 215 |  | 216 |  | 217 |  | 218 |  | 219 |  | 220 |  | 221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229 |  | 230 |  | 231
|  |  | 34/1 |  | 34/2 |  | 34/3 |  | 34/4 |  | 35/0 |  | 35/1 |  | 35/2 |  | 35/3 |  | 35/4 |  | 35/5 |  | 36/0 |  | 36/1 |  | 36/2 |  | 36/3 |  | 36/4 |  | 37/0 |  | 37/1 |  | 37/2 |  | 37/3 |  | 38/0 |  | 38/1
[57 empty] | 0 | 0 | 0
ERE
WELD
| FDN | 432.6 | Sandy | 407.5 | Sandy | 377 | Sandy | 451.6 | Sandy | 379.3 | Sandy | 265.6 | Sandy | 492.4 | Sandy | 522.2 | Sandy | 418.9 | DRY | 421.7 | Sandy | 342.7 | Sandy | 386.4 | Sandy | 309.4 |  | 357.8 |  | 480.4 |  | 350.5 |  | 443.3 |  | 356.7 |  | 339.9 | Sandy | 500.3 | Sandy | 421.4 | Sandy | 14 | 1 | 0 | 0 | 0 | 15 | 0 | 15 | 0 | 0 |  |  | 8457.6
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C | [13 empty] | C |  | C |  | C
| TOT |  | DA+9 |  | DA+6 |  | DA+0 |  | DA+0 |  | DB2+6 |  | DA+9 |  | DB1+0 |  | DB1+6 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DB2+0 |  | DA+9 |  | DA+3 |  | DA+0 |  | DB2+6 |  | DA+0
| LE |  | ,,, |  | ,,,2 |  | ,3,, |  | ,3,1, |  | 2,,, |  | 2,,,2 |  | 1,1,, |  | 1,,, |  | ,,, |  | ,,4,4 |  | ,,, |  | ,,, |  | 1,1,, |  | ,2,, |  | 2,3,,5 |  | ,,,1 |  | 2,2,2,1 |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 232 |  | 233 |  | 234 |  | 235 |  | 236 |  | 237 |  | 238 |  | 239 |  | 240 |  | 241 |  | 242 |  | 243 |  | 244 |  | 245 |  | 246 |  | 247 |  | 248 |  | 249 |  | 250 |  | 251 |  | 252
|  |  | 38/2 |  | 38/3 |  | 38/4 |  | 39/0 |  | 39/1 |  | 40/0 |  | 40/1 |  | 40/2 |  | 40/3 |  | 41/0 |  | 41/1 |  | 41/2 |  | 42/0 |  | 42/1 |  | 42/2 |  | 42/3 |  | 42/4 |  | 42/5 |  | 42/6 |  | 43/0 |  | 43/1
[57 empty] | 0 | 0 | 0
| ERE | [39 empty] | E |  | E
WELD
| FDN | 419 | Sandy | 420.3 | Sandy | 414.9 | Sandy | 425.5 | Sandy | 412.6 | Sandy | 322.6 | Sandy | 396.2 | Sandy | 425.8 | Sandy | 401.7 | Sandy | 436.3 | WIP | 340.8 | Sandy | 447.8 | Sandy | 382.3 | Sandy | 384.7 | Sandy | 407.4 | Sandy | 414.2 | Sandy | 256.4 | Sandy | 403.8 | Sandy | 396.7 | Sandy | 403.9 | Sandy | 346 | Sandy | 20 | 0 | 0 | 0 | 0 | 20 | 1 | 20 | 2 | 0 |  |  | 8258.9
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  |  |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+6 |  | DA+9 |  | DA+9 |  | DB2+6 |  | DA+0 |  | DC2+0 |  | DA+6 |  | DA+3 |  | DA+3 |  | DC1+6 |  | DB1+9 |  | DA+0 |  | DC1+0 |  | DA+6 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+9 |  | DA+0 |  | DB1+0 |  | DA+3
| LE |  | ,,, |  | 2,2,2,2 |  | 1,1,,1 |  | ,,, |  | ,,, |  | 1,1,, |  | 1,2,, |  | ,,, |  | 1,2,, |  | 3,1,,1 |  | 4,5,6,6 |  | ,,1,1 |  | 1,,,2 |  | 1,,, |  | ,,1,3 |  | ,,, |  | ,,, |  | ,,,1 |  | 2,1,,2 |  | ,,, |  | ,,3,3
REM
|  |  | 253 |  | 254 |  | 255 |  | 256 |  | 257 |  | 258 |  | 259 |  | 260 |  | 261 |  | 262 |  | 263 |  | 264 |  | 265 |  | 266 |  | 267 |  | 268 |  | 269 |  | 270 |  | 271 |  | 272 |  | 273
|  |  | 43/2 |  | 43/3 |  | 43/4 |  | 43/5 |  | 43/6 |  | 43/7 |  | 43/8 |  | 43/9 |  | 43/10 |  | 43/11 |  | 44/0 |  | 44/1 |  | 44/2 |  | 44/3 |  | 44/4 |  | 44/5 |  | 44/6 |  | 44/7 |  | 44/8 |  | 44/9 |  | 44/10
[57 empty] | 0 | 0 | 0
| ERE | [9 empty] | E |  | E |  | E |  | E
|  | 475.8 | Sandy | 363.7 | DRY | 431.8 | Sandy | 405.3 | DRY | 427.8 | Sandy | 389.8 | Sandy | 449.5 | Sandy | 388 | Sandy | 346.3 | Sandy | 444.8 | Sandy | 384.3 | Sandy | 384.3 | Sandy | 359 | Sandy | 334 | Sandy | 395 | Sandy | 355 | Sandy | 485 | Sandy | 473 | Sandy | 367 | Sandy | 430 | Sandy | 365 | Sandy | 19 | 2 | 0 | 0 | 0 | 21 | 0 | 21 | 4 | 0 |  |  | 8454.4
|  |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
|  |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DB1+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+9 |  | DA+9 |  | DB1+3 |  | DA+9 |  | DCT+0 |  | DA+9 |  | DB1+9
|  |  | 1,,,1 |  | ,1,, |  | 1,1,, |  | ,,, |  | ,,, |  | ,,, |  | 1,,, |  | ,,, |  | 3,3,, |  | 2,3,,1 |  | 0,1,1,0 |  | 0,0,1,0 |  | 0,0,0,0 |  | 2,0,0,1 |  | 4,3,3,3 |  | 1,3,0,0 |  | 1,0,0,1 |  | 0,0,0,0 |  | 1,2,0,1 |  | 4,0,2,6 |  | 0,1,0,0
REM
|  |  | 274 |  | 275 |  | 276 |  | 277 |  | 278 |  | 279 |  | 280 |  | 281 |  | 282 |  | 283 |  | 284 |  | 285 |  | 286 |  | 287 |  | 288 |  | 289 |  | 290 |  | 291 |  | 292 |  | 293 |  | 294
|  |  | 44/11 |  | 45/0 |  | 45/1 |  | 46/0 |  | 47/0 |  | 47/1 |  | 47/2 |  | 47/3 |  | 47/4 |  | 47/5 |  | 47/6 |  | 47/7 |  | 47/8 |  | 47/9 |  | 47/10 |  | 48/0 |  | 48/1 |  | 49/0 |  | 49/1 |  | 49/2 |  | 49/3
[38 empty] | , |  | , |  | , | [14 empty] | 0 | 0 | 1155.7
| ERE | [25 empty] | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD | [25 empty] | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 428 | Sandy | 327.2 | Sandy | 294.92 | Sandy | 406.54 | Sandy | 199.08 | Sandy | 441.2 | Sandy | 365.93 | Sandy | 417.4 | Sandy | 358.4 | Sandy | 461.2 | Sandy | 377.3 | Sandy | 431.5 | Sandy | 398.8 | Sandy | 405.9 | Sandy | 433.7 | Sandy | 386.2 | Sandy | 428.9 | Sandy | 402.9 | Sandy | 379.1 | Sandy | 386.6 | Sandy | 390 | Sandy | 21 | 0 | 0 | 0 | 0 | 21 | 0 | 21 | 9 | 9 |  |  | 8120.77
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+0 |  | DC2+0 |  | DA+9 |  | DD60+25 |  | DD60+25 |  | DA+3 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DC2+0 |  | DA+9 |  | DD45+0 |  | DA+0 |  | DA+3 |  | DA+3
| LE |  | 0,1,0,0 |  | 0,1,0,0 |  | 0,0,6,6 |  | 0,6,6,2 |  | 5,5,5,5 |  | 2,0,2,5 |  | 0,0,0,0 |  | 1,2,0,0 |  | ,,, |  | 0,1,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 1,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0
REM
|  |  | 295 |  | 296 |  | 297 |  | 298 |  | 299 |  | 300 |  | 301 |  | 302 |  | 303 |  | 304 |  | 305 |  | 306 |  | 307 |  | 308 |  | 309 |  | 310 |  | 311 |  | 312 |  | 313 |  | 314 |  | 315
|  |  | 49/4 |  | 49/5 |  | 49/6 |  | 49/7 |  | 50/0 |  | 50/1 |  | 50/2 |  | 50/3 |  | 50/4 |  | 50/5 |  | 50/6 |  | 50/7 |  | 50/8 |  | 50/9 |  | 50/10 |  | 51/0 |  | 51/1 |  | 51/2 |  | 52/0 |  | 52/1 |  | 52/2
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [18 empty] | 0 | 0 | 7564.3
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 421.7 | Sandy | 396.6 | Sandy | 412.8 | Sandy | 340.2 | Sandy | 500.2 | Sandy | 469.1 | Sandy | 367.1 | Sandy | 470.4 | Sandy | 354.8 | Sandy | 442.1 | Sandy | 364.4 | Sandy | 470.8 | Sandy | 345 | Sandy | 364.4 | Sandy | 394.6 | Sandy | 401.4 | Sandy | 356.6 | Sandy | 307.1 | Sandy | 385 | Sandy | 402 | Sandy | 402.6 | Sandy | 21 | 0 | 0 | 0 | 0 | 21 | 0 | 21 | 19 | 19 |  |  | 8368.9
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+6 |  | DA+9 |  | DA+6 |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+0 |  | DA+9 |  | DA+0 |  | DA+0 |  | DC2+0 |  | DA+0 |  | DA+0 |  | DC2+0 |  | DA+6 |  | DA+6
| LE |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,3,2,2 |  | 0,0,0,1 |  | 1,0,0,0 |  | 2,2,2,2 |  | 0,0,1,0 |  | 3,3,4,3 |  | 4,3,4,3 |  | 3,4,3,3 |  | 0,0,0,1 |  | 0,0,0,0 |  | 0,0,1,0 |  | 0,0,1,0 |  | 0,0,0,0 |  | 0,0,1,0 |  | 0,0,0,0 |  | 0,0,3,3 |  | 0,4,0,0 |  | 0,0,0,3
REM
|  |  | 316 |  | 317 |  | 318 |  | 319 |  | 320 |  | 321 |  | 322 |  | 323 |  | 324 |  | 325 |  | 326 |  | 327 |  | 328 |  | 329 |  | 330 |  | 331 |  | 332 |  | 333 |  | 334 |  | 335 |  | 336
|  |  | 52/3 |  | 52/4 |  | 52/5 |  | 52/6 |  | 52/7 |  | 52/8 |  | 52/9 |  | 52/10 |  | 53/0 |  | 53/1 |  | 53/2 |  | 53/3 |  | 53/4 |  | 53/5 |  | 53/6 |  | 53/7 |  | 53/8 |  | 54/0 |  | 54/1 |  | 54/2 |  | 54/3
[57 empty] | 0 | 0 | 0
| ERE | [5 empty] | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD | [5 empty] | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 437 | Sandy | 393.8 | Sandy | 447 | Sandy | 373 | Sandy | 406.8 | Sandy | 433 | Sandy | 399.7 | Sandy | 384.1 | Sandy | 455.9 | Sandy | 433.2 | Sandy | 407.4 | Sandy | 394.5 | Sandy | 410.1 | Sandy | 428.1 | Sandy | 406.6 | Sandy | 411.3 | Sandy | 427.8 | Sandy | 371.3 | Sandy | 365.1 | Sandy | 381 | Sandy | 417 | Sandy | 21 | 0 | 0 | 0 | 0 | 21 | 0 | 21 | 15 | 6 |  |  | 8583.7
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+9 |  | DA+9 |  | DA+9 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+9 |  | DB2+9 |  | DA+9 |  | DA+0 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+3 |  | DB1+6 |  | DA+3 |  | DA+3 |  | DA+6
| LE |  | 4,3,3,3 |  | 2,2,0,0 |  | 0,0,0,1 |  | 0,0,0,0 |  | 0,3,1,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 1,2,1,1 |  | 4,4,4,4 |  | 4,4,4,4 |  | 0,0,0,2 |  | 0,4,1,0 |  | 0,2,1,0 |  | 0,0,0,0 |  | 1,1,3,1 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 1,1,0,0 |  | 0,0,0,0 |  | 0,2,0,0
REM
|  |  | 337 |  | 338 |  | 339 |  | 340 |  | 341 |  | 342 |  | 343 |  | 344 |  | 345 |  | 346 |  | 347 |  | 348 |  | 349 |  | 350 |  | 351 |  | 352 |  | 353 |  | 354 |  | 355 |  | 356 |  | 357
|  |  | 54/4 |  | 54/5 |  | 55/0 |  | 55/1 |  | 55/2 |  | 55/3 |  | 55/4 |  | 55/5 |  | 55/6 |  | 55/7 |  | 55/8 |  | 56/0 |  | 57/0 |  | 57/1 |  | 57/2 |  | 57/3 |  | 57/4 |  | 57/5 |  | 57/6 |  | 57/7 |  | 58/0
[57 empty] | 0 | 0 | 0
| ERE | [11 empty] | E |  | E |  | E |  | E | [13 empty] | E |  | E |  | E |  | E |  | E |  | E
| WELD | [11 empty] | Done |  | Done |  | Done |  | Done | [13 empty] | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 423.3 | Sandy | 401 | Sandy | 424 | Sandy | 404.9 | WFR | 343.1 | WFR | 357.7 | Sandy | 365.2 | Sandy | 350.1 | Sandy | 357.7 | Sandy | 337.8 | Sandy | 341.22 | Sandy | 460.49 | Sandy | 219.76 | Sandy | 461.11 | Sandy | 355.5 | DRY | 405.4 | DRY | 418.2 | Sandy | 416.8 | Sandy | 395 | Sandy | 401.8 | DFR | 433.9 | DFR | 15 | 2 | 2 | 2 | 0 | 21 | 0 | 21 | 10 | 10 |  |  | 8073.98
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+9 |  | DA+9 |  | DB1+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DD60+25 |  | DD60+25 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DC1+3
| LE |  | 1,2,0,0 |  | 1,3,3,1 |  | 0,1,1,0 |  | ,,, |  | ,,, |  | ,,, |  | 0,0,0,1 |  | 0,0,1,3 |  | 0,0,1,2 |  | 0,0,1,0 |  | 0,0,0,0 |  | 3,3,0,2 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,0 |  | 0,0,0,1 |  | 0,1,0,0 |  | ,,, |  | 0,0,0,0
REM
|  |  | 358 |  | 359 |  | 360 |  | 361 |  | 362 |  | 363 |  | 364 |  | 365 |  | 366 |  | 367 |  | 368 |  | 369 |  | 370 |  | 371 |  | 372 |  | 373 |  | 374 |  | 375 |  | 376 |  | 377 |  | 378
|  |  | 59/0 |  | 59/1 |  | 59/2 |  | 59/3 |  | 59/4 |  | 59/5 |  | 59/6 |  | 59/7 |  | 59/8 |  | 59/9 |  | 59/10 |  | 59/11 |  | 59/12 |  | 59/13 |  | 59/14 |  | 59/15 |  | 59/16 |  | 60/0 |  | 60/1 |  | 60/2 |  | 60/3
|  |  |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8367.804
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 238.897 | DRY | 411.3 | DRY | 418.204 | DFR | 412.3 | DFR | 421 | DFR | 419.7 | DFR | 419.1 | DFR | 408.8 | DRY | 426.9 | DRY | 434.7 | DRY | 400.8 | DRY | 436.3 | DFR | 393.1 | DFR | 447.4 | DRY | 391.1 | DRY | 448.6 | DRY | 388 | Dry | 438 | DRY | 413.8 | DRY | 424.2 | DFR | 414.5 | DFR | 0 | 12 | 9 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8606.701
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DC2+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB1+3 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+6 |  | DA+9 |  | DC1+0 |  | DA+6 |  | DA+3 |  | DA+3
| LE |  | 0,0,0,0 |  | 0,0,0,1 |  | 0,0,0,0 |  | 0,0,0,1 |  | ,,, |  | ,,, |  | ,,, |  | 0,0,0,0 |  | ,,, |  | ,,, |  | ,,, |  | 0,0,2,0 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 2,2,0,0 |  | ,,,
REM
|  |  | 379 |  | 380 |  | 381 |  | 382 |  | 383 |  | 384 |  | 385 |  | 386 |  | 387 |  | 388 |  | 389 |  | 390 |  | 391 |  | 392 |  | 393 |  | 394 |  | 395 |  | 396 |  | 397 |  | 398 |  | 399
|  |  | 60/4 |  | 60/5 |  | 60/6 |  | 60/7 |  | 60/8 |  | 60/9 |  | 60/10 |  | 60/11 |  | 61/0 |  | 61/1 |  | 61/2 |  | 61/3 |  | 61/4 |  | 61/5 |  | 61/6 |  | 61/7 |  | 61/8 |  | 61/9 |  | 61/10 |  | 62/0 |  | 62/1
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8611.3
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 425.6 | DFR | 412.3 | DRY | 374.1 | DRY | 410.1 | DRY | 400.4 | DRY | 409.2 | DRY | 401 | DFR | 394.5 | DRY | 397.9 | DRY | 405.7 | DFR | 433.2 | DFR | 400.9 | DRY | 427 | DRY | 413.9 | DRY | 426.4 | DRY | 411.5 | Dry | 376.3 | DRY | 433.4 | Dry | 405.6 | DRY | 434.3 | DRY | 418 | Sandy | 1 | 16 | 4 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8611.3
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB2+0 |  | DA+6 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+9 |  | DA+6 |  | DA+0 |  | DA+9 |  | DB2+0 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 0,0,0,0 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 0,0,0,1 |  | 1,2,1,0 |  | ,,, |  | ,,, |  | 0,0,0,0 |  | 0,0,1,2
REM
|  |  | 400 |  | 401 |  | 402 |  | 403 |  | 404 |  | 405 |  | 406 |  | 407 |  | 408 |  | 409 |  | 410 |  | 411 |  | 412 |  | 413 |  | 414 |  | 415 |  | 416 |  | 417 |  | 418 |  | 419 |  | 420
|  |  | 62/2 |  | 62/3 |  | 62/4 |  | 62/5 |  | 62/6 |  | 62/7 |  | 62/8 |  | 62/9 |  | 62/10 |  | 62/11 |  | 63/0 |  | 63/1 |  | 63/2 |  | 63/3 |  | 63/4 |  | 63/5 |  | 63/6 |  | 63/7 |  | 63/8 |  | 64/0 |  | 64/1
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8531.5
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 386 | DRY | 400 | DRY | 401 | DRY | 403 | DRY | 404 | DRY | 423 | DRY | 409 | DFR | 409 | DFR | 411 | DFR | 413 | DRY | 386.1 | DFR | 400 | DFR | 416 | DFR | 411 | DFR | 399 | DRY | 413 | DFR | 426 | DRY | 413 | DRY | 425 | DRY | 408.3 | DRY | 375.1 | DRY | 0 | 13 | 8 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8531.5
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DC1+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB2+0 |  | DA+0
| LE |  | 0,1,0,0 |  | ,,, |  | ,,, |  | 0,0,0,0 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | 0,0,0,0 |  | ,,, |  | ,,, |  | 0,0,0,0 |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 421 |  | 422 |  | 423 |  | 424 |  | 425 |  | 426 |  | 427 |  | 428 |  | 429 |  | 430 |  | 431 |  | 432 |  | 433 |  | 434 |  | 435 |  | 436 |  | 437 |  | 438 |  | 439 |  | 440 |  | 441
|  |  | 64/2 |  | 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | 64/7 |  | 64/8 |  | 64/9 |  | 64/10 |  | 64/11 |  | 65/0 |  | 65/1 |  | 65/2 |  | 65/3 |  | 65/4 |  | 65/5 |  | 65/6 |  | 65/7 |  | 65/8 |  | 65/9 |  | 65/10
|  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , |  | , | [14 empty] | 0 | 0 | 8463.9
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 408.7 | DRY | 410.7 | DRY | 408.2 | DRY | 426.2 | DRY | 407.7 | DRY | 401.6 | DRY | 425.5 | DRY | 414.4 | DRY | 410.6 | DRY | 428.4 | DRY | 400.6 | DRY | 395.4 | DRY | 393.7 | DRY | 403.7 | DRY | 402.9 | DRY | 376.4 | DRY | 389.2 | DRY | 397.6 | DRY | 394.3 | DRY | 389 | DRY | 379.1 | DRY | 0 | 21 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 21 |  |  | 8463.9
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 442 |  | 443 |  | 444 |  | 445 |  | 446 |  | 447 |  | 448 |  | 449 |  | 450 |  | 451 |  | 452 |  | 453 |  | 454 |  | 455 |  | 456 |  | 457 |  | 458 |  | 459 |  | 460 |  | 461 |  | 462
|  |  | 65/11 |  | 66/0 |  | 67/0 |  | 67/1 |  | 67/2 |  | 68/0 |  | 69/0 |  | 69/1 |  | 70/0 |  | 70/1 |  | 70/2 |  | 70/3 |  | 70/4 |  | 70/5 |  | 70/6 |  | 70/7 |  | 70/8 |  | 70/9 |  | 70/10 |  | 70/11 |  | 71/0
|  | , |  | , | [52 empty] | 0 | 0 | 814.5
| ERE |  | E |  | E |  | E |  | E |  | E |  | E | [11 empty] | E |  | E |  | E | [7 empty] | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  |  |  | Done |  | Done | [13 empty] | Done |  | Done |  | Done | [7 empty] | Done |  | Done |  | Done |  | Done
| FDN | 387.6 | DRY | 426.9 | DRY | 207.8 | DRY | 347.1 | DRY | 344.9 | DRY | 369.2 | DRY | 200.9 | DFR | 374.1 | DRY | 394.9 | DRY | 388.4 | DRY | 418.9 | DRY | 418.6 | DRY | 414 | DRY | 419.6 | DRY | 420.3 | DRY | 419.6 | DRY | 418.2 | DRY | 414.1 | DRY | 406.1 | DRY | 408.6 | DRY | 420.4 | DRY | 0 | 20 | 1 | 0 | 0 | 21 | 0 | 21 | 13 | 11 |  |  | 8020.2
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+0 |  | DC2+6 |  | DC1+9 |  | DA+0 |  | DA+0 |  | DD45+0 |  | DB2+0 |  | DA+3 |  | DC1+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB2+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 463 |  | 464 |  | 465 |  | 466 |  | 467 |  | 468 |  | 469 |  | 470 |  | 471 |  | 472 |  | 473 |  | 474 |  | 475 |  | 476 |  | 477 |  | 478 |  | 479 |  | 480 |  | 481 |  | 482 |  | 483
|  |  | 71/1 |  | 71/2 |  | 71/3 |  | 71/4 |  | 71/5 |  | 71/6 |  | 71/7 |  | 71/8 |  | 72/0 |  | 72/1 |  | 72/2 |  | 72/3 |  | 73/0 |  | 73/1 |  | 73/2 |  | 73/3 |  | 73/4 |  | 73/5 |  | 73/6 |  | 73/7 |  | 73/8
[57 empty] | 0 | 0 | 0
| ERE |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E |  | E
| WELD |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  |  |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done |  | Done
| FDN | 398.6 | DRY | 414.3 | DRY | 413 | DRY | 367.7 | DRY | 429.4 | DRY | 408 | DRY | 404.9 | DRY | 431.6 | DRY | 408.4 | DRY | 435.3 | DRY | 403.9 | DRY | 389.2 | DRY | 400.1 | DRY | 383.3 | DRY | 379 | DRY | 381.2 | DRY | 384.7 | DRY | 368.8 | DRY | 365.5 | DRY | 392.4 | DRY | 374.9 | DRY | 0 | 21 | 0 | 0 | 0 | 21 | 0 | 21 | 21 | 20 |  |  | 8334.2
| EAR |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C |  | C
| TOT |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DB2+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3
| LE |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,, |  | ,,,
REM
|  |  | 484 |  | 485
|  |  | 73/9 |  | 74/0
[57 empty] | 0 | 0 | 0
| ERE |  | E |  | E
| WELD |  | Done |  | Done
| FDN | 379.5 | DRY | 378.9 | Sandy |  |  |  | Towards Beawar S/S | [34 empty] | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 2 |  |  | 758.4
| EAR |  | C |  | C
| TOT |  | DA+0 |  | DB2+0
| LE |  | ,,, |  | ,,,
REM
Progress overview (Tower wise breakups)
| TOT |  | Total Qty. in No's |  | Wight of individual towers in MT | Progress breakups dashboard | [15 empty] | Notepad:- |  |  | PKG F
[6 empty] | FDN |  | ERE | [12 empty] | JMC Status
[6 empty] | Comp. | Balance | Comp. | Erected Weight (MT) |  | Balance | Balance to erect (MT) | [8 empty] | Description |  |  | Total Completed | Total Approved | Balance | CTQ approved | CTQ approval awaited | CTQ not initiated
| DA+0 |  | 151 |  | 37.504 | 126 | 25 | 68 | 2550.272 |  | 83 | 3112.832 | [8 empty] | Foundation |  |  | 415
| DA+3 |  | 160 |  | 38.847 | 143 | 17 | 91 | 3535.077 |  | 69 | 2680.443 | [8 empty] | Erection |  |  | 222
| DA+6 |  | 48 |  | 45.413 | 40 | 8 | 20 | 908.26 |  | 28 | 1271.564
| DA+9 |  | 38 |  | 45.413 | 37 | 1 | 15 | 681.195 |  | 23 | 1044.499
| DB1+0 |  | 13 |  | 57.597 | 9 | 4 | 4 | 230.388 |  | 9 | 518.373
| DB1+3 |  | 3 |  | 60.096 | 3 | 0 | 1 | 60.096 |  | 2 | 120.192
| DB1+6 |  | 3 |  | 67.873 | 3 | 0 | 0 | 0 |  | 3 | 203.619
| DB1+9 |  | 3 |  | 70.701 | 2 | 1 | 0 | 0 |  | 3 | 212.103
| DB2+0 |  | 14 |  | 57.597 | 10 | 4 | 6 | 345.582 |  | 8 | 460.776
| DB2+3 |  | 4 |  | 60.096 | 3 | 1 | 3 | 180.288 |  | 1 | 60.096
| DB2+6 |  | 3 |  | 67.873 | 3 | 0 | 0 | 0 |  | 3 | 203.619
| DB2+9 |  | 2 |  | 70.701 | 1 | 1 | 1 | 70.701 |  | 1 | 70.701
| DC1+0 |  | 12 |  | 66.381 | 10 | 2 | 3 | 199.143 |  | 9 | 597.429
| DCT+0 |  | 1 |  | 94.219 | 1 | 0 | 0 | 0 |  | 1 | 94.219
| DC1+3 |  | 1 |  | 69.228 | 1 | 0 | 1 | 69.228 |  | 0 | 0
| DC1+6 |  | 2 |  | 78.253 | 1 | 1 | 0 | 0 |  | 2 | 156.506
| DC1+9 |  | 1 |  | 81.613 | 1 | 0 | 1 | 81.613 |  | 0 | 0
| DC2+0 |  | 9 |  | 66.381 | 9 | 0 | 5 | 331.905 |  | 4 | 265.524
| DC2+3 |  | 0 |  | 69.228 | 0 | 0 | 0 | 0 |  | 0 | 0
| DC2+6 |  | 1 |  | 78.253 | 1 | 0 | 1 | 78.253 |  | 0 | 0
| DC2+9 |  | 0 |  | 81.613 | 0 | 0 | 0 | 0 |  | 0 | 0
| DD45+0 |  | 2 |  | 86.129 | 2 | 0 | 2 | 172.258 |  | 0 | 0
| DD45+3 |  | 2 |  | 89.909 | 0 | 2 | 0 | 0 |  | 2 | 179.818
| DD60+0 |  | 3 |  | 86.129 | 3 | 0 | 0 | 0 |  | 3 | 258.387
| DD60+3 |  | 1 |  | 89.909 | 1 | 0 | 0 | 0 |  | 1 | 89.909
| DD60+6 |  | 2 |  | 100.968 | 1 | 1 | 0 | 0 |  | 2 | 201.936
| DD60+9 |  | 0 |  | 105.068 | 0 | 0 | 0 | 0 |  | 0 | 0
| DD60+18 |  | 1 |  | 129.11 | 0 | 1 | 0 | 0 |  | 1 | 129.11
| DD60+25 |  | 5 |  | 143.601 | 4 | 1 | 0 | 0 |  | 5 | 718.005
| Total |  | 485 |  |  | 415 | 70 | 222 | 9494.259 |  | 263 | 12649.66
Survey under ROW
Global Footprint in 110+ countries*
*Includes EPC and Supply

## Visual chart Edit
Progress Summary'!A1
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Data taken from Pramanand mail dated 12/12/24.
Sr. No. | PKG G
| Loc No | TOT | A | B | C | D | CONCATANATE (A,B,C,D) | Span length | Remarks | FDN | Erection | Tackwelding
0 | Gty
1 | 1/0 | DD60+0 |  |  |  |  | ,,, | 122 |  | DRY
2 | 1A/0 | DD60+0 |  |  |  |  | ,,, | 90 | As per approved 0,0,0,1 | DRY
3 | 1A/1 | DA+6 |  |  |  |  | ,,, | 277.7 |  | DFR | E
4 | 1A/2 | DA+0 |  | 1 | 1 |  | ,1,1, | 386 |  | DRY | E
5 | 1A/3 | DA+0 |  |  |  |  | ,,, | 443.6 |  | DRY | E
6 | 1A/4 | DA+3 |  |  | 1 |  | ,,1, | 333.4 |  | DFR
7 | 1A/5 | DA+0 | 1 | 1 |  |  | 1,1,, | 431.9 |  | DRY
8 | 1A/6 | DA+0 | 1 |  |  | 1 | 1,,,1 | 348.7 |  | Sandy
9 | 1A/7 | DA+3 |  | 1 |  |  | ,1,, | 395.7 |  | Sandy
10 | 1A/8 | DA+0 |  |  |  |  | ,,, | 415 |  | Sandy
11 | 2/0 | DC1+0 |  |  |  |  | ,,, | 394.3 |  | DRY
12 | 2/1 | DA+3 |  |  |  |  | ,,, | 405.3 |  | Sandy
13 | 2/2 | DA+3 |  |  |  | 1 | ,,,1 | 338.5 |  | Sandy
14 | 2/3 | DA+3 | 1 |  | 1 | 1 | 1,,1,1 | 406 |  | Sandy
15 | 2/4 | DA+3 |  |  |  |  | ,,, | 429 |  | Sandy
16 | 2/5 | DA+3 |  |  | 1 | 1 | ,,1,1 | 411.6 |  | Sandy
17 | 2/6 | DA+3 |  |  |  | 1 | ,,,1 | 425.7 |  | Sandy
18 | 2/7 | DA+3 |  |  |  |  | ,,, | 408.2 |  | WIP
19 | 2/8 | DA+0 |  |  |  |  | ,,, | 354.6 |  | Sandy
20 | 2/9 | DA+0 |  |  |  |  | ,,, | 308.7
21 | 3/0 | DD60+6 |  |  |  |  | ,,, | 336 |  | WIP
22 | 4/0 | DD60+6 |  |  |  |  | ,,, | 226.5 |  | DRY
23 | 4/1 | DA+0 |  |  |  |  | ,,, | 343.4 |  | WIP
24 | 4/2 | DA+0 |  |  |  |  | ,,, | 358.4
25 | 4/3 | DA+0 |  |  |  |  | ,,, | 381 |  | DRY
26 | 4/4 | DA+0 |  |  |  |  | ,,, | 367.6
27 | 5/0 | DB1+9 | 5 | 5 | 5 | 5 | 5,5,5,5 | 423.1
28 | 6/0 | DB2+9 | 5 | 5 | 5 | 5 | 5,5,5,5 | 246
29 | 6/1 | DA+0 |  |  |  |  | ,,, | 429.9 |  | DFR
30 | 6/2 | DA+0 |  |  |  |  | ,,, | 362.4 |  | DFR
31 | 7/0 | DB1+0 | 2 | 3 | 3 | 2 | 2,3,3,2 | 347.9
32 | 8/0 | DB1+0 |  |  |  |  | ,,, | 210.8
33 | 8/1 | DA+3 |  |  |  |  | ,,, | 409.2
34 | 8/2 | DA+3 |  |  |  |  | ,,, | 413.6
35 | 8/3 | DA+0 |  |  |  |  | ,,, | 393.2
36 | 8/4 | DA+3 |  |  |  |  | ,,, | 416.5
37 | 8/5 | DA+3 |  |  |  | 1 | ,,,1 | 394.6
38 | 8/6 | DA+3 |  |  |  |  | ,,, | 393.2
39 | 8/7 | DB1+0 |  |  |  |  | ,,, | 441.1 |  | DRY
40 | 8/8 | DA+6 |  |  |  |  | ,,, | 414.4
41 | 8/9 | DA+3 |  |  |  |  | ,,, | 395.9 |  | DFR
42 | 8/10 | DA+3 |  |  |  |  | ,,, | 413.4 |  | DFR
43 | 8/11 | DA+0 |  |  |  |  | ,,, | 402.6 |  | DRY
44 | 8/12 | DA+0 |  |  |  |  | ,,, | 372.1 |  | WIP
45 | 9/0 | DD60+18 |  |  |  |  | ,,, | 457.7
46 | 10/0 | DD60+25 |  |  |  |  | ,,, | 233.1 |  | WIP
47 | 10/1 | DA+0 |  |  |  |  | ,,, | 443.7 |  | WIP
48 | 10/2 | DA+0 |  |  |  |  | ,,, | 383.2
49 | 10/3 | DA+0 |  |  |  |  | ,,, | 398.6 |  | DFR | E
50 | 10/4 | DA+3 |  |  |  |  | ,,, | 410.7 |  | DFR | E
51 | 10/5 | DA+3 |  |  |  |  | ,,, | 416.2 |  | DRY
52 | 10/6 | DA+0 |  |  |  |  | ,,, | 403.4 |  | DFR | E
53 | 10/7 | DA+3 |  |  |  |  | ,,, | 373.9
54 | 10/8 | DA+3 |  |  |  |  | ,,, | 411.8 |  | DFR | E
55 | 10/9 | DA+0 |  |  |  |  | ,,, | 414.2 |  | DRY | E
56 | 10/10 | DA+3 |  |  |  |  | ,,, | 402.3
57 | 10/11 | DA+3 |  |  |  |  | ,,, | 430.3 |  | DRY | E
58 | 10/12 | DB1+0 |  |  |  |  | ,,, | 406.2 |  | DRY | E
59 | 10/13 | DA+3 |  |  |  |  | ,,, | 405.251 |  | DRY
60 | 10/14 | DA+3 |  |  |  |  | ,,, | 427.085 |  | DRY | E
61 | 10/15 | DA+3 |  |  |  |  | ,,, | 400.035
62 | 10/16 | DA+3 |  |  |  |  | ,,, | 412.79
63 | 10/17 | DA+3 |  |  |  |  | ,,, | 387.758 |  | DFR | E
64 | 10/18 | DA+3 |  |  |  |  | ,,, | 436.732 |  | DFR | E
65 | 10/19 | DA+0 |  |  |  |  | ,,, | 403.689 |  | DRY | E
66 | 10/20 | DA+3 |  |  |  |  | ,,, | 409.528 |  | DFR | E
67 | 10/21 | DA+3 |  |  |  |  | ,,, | 419.56 |  | DFR | E
68 | 10/22 | DA+0 | 1 | 3 |  |  | 1,3,, | 369.467
69 | 10/23 | DA+0 |  | 2 |  |  | ,2,, | 403.73
70 | 11/0 | DB1+0 | 1 | 4 |  | 3 | 1,4,,3 | 368.825
71 | 11/1 | DA+0 |  |  |  |  | ,,, | 385.289
72 | 11/2 | DA+0 | 2 | 1 |  |  | 2,1,, | 409.446
73 | 11/3 | DA+0 |  |  |  | 1 | ,,,1 | 385.819
74 | 11/4 | DA+0 |  |  |  |  | ,,, | 449.057
75 | 11/5 | DA+0 |  |  |  |  | ,,, | 368.102 |  | DFR | E
76 | 11A/0 | DB1+0 |  |  |  |  | ,,, | 342.28 |  | DRY | E
77 | 11A/1 | DA+3 |  |  |  |  | ,,, | 405.1 |  | DRY | E
78 | 11A/2 | DA+0 |  |  |  |  | ,,, | 412.2 |  | DRY | E
79 | 11A/3 | DA+3 |  |  |  |  | ,,, | 412.2 |  | DRY | E
80 | 11A/4 | DA+3 |  |  |  |  | ,,, | 422.1 |  | DRY
81 | 11A/5 | DA+3 |  |  |  |  | ,,, | 418.3 |  | DRY | E
82 | 11A/6 | DA+6 |  |  |  |  | ,,, | 384.3 |  | DRY | E
83 | 11A/7 | DA+9 |  |  |  |  | ,,, | 434.2 |  | Sandy | E
84 | 11A/8 | DA+6 |  | 2 | 4 | 1 | ,2,4,1 | 390.1 |  | Sandy
85 | 11A/9 | DA+3 |  |  |  |  | ,,, | 426.3 |  | DRY | E
86 | 12/0 | DD60+0 |  |  |  |  | ,,, | 405.9 |  | DRY
87 | 13/0 | DD60+3 |  |  |  |  | ,,, | 211.9 |  | DRY
88 | 13/1 | DA+9 |  |  |  |  | ,,, | 464.3 |  | DRY
89 | 13/2 | DA+3 |  |  |  |  | ,,, | 373.7 |  | DRY | E
90 | 13/3 | DA+3 |  |  | 2 | 4 | ,,2,4 | 419.7 |  | Sandy
91 | 13/4 | DA+3 |  |  |  |  | ,,, | 420.3
92 | 14/0 | DC2+0 |  |  |  |  | ,,, | 400 |  | Sandy
93 | 14A/0 | DC1+0 |  |  |  |  | ,,, | 381.4
94 | 14A/1 | DA+3 |  |  |  |  | ,,, | 407.8 |  | DRY | E
95 | 14A/2 | DA+0 |  |  |  |  | ,,, | 401 |  | DRY
96 | 15/0 | DC1+0 |  |  |  |  | ,,, | 383.3 |  | DRY
97 | 15/1 | DA+3 |  |  |  |  | ,,, | 404.6 |  | DRY | E | Done
98 | 16/0 | DC1+0 |  |  |  |  | ,,, | 413.3 |  | DRY | E
99 | 16/1 | DA+0 |  |  |  |  | ,,, | 364.3 |  | DRY | E
100 | 16/2 | DA+0 | 1 |  |  | 1 | 1,,,1 | 414.3 |  | DRY | E
101 | 16/3 | DA+3 |  |  |  |  | ,,, | 340.3 |  | DRY | E | Done
102 | 16/4 | DA+0 |  | 1 |  |  | ,1,, | 394.7 |  | DRY | E | Done
103 | 16/5 | DA+3 |  |  |  |  | ,,, | 425.9 |  | DRY | E
104 | 17/0 | DB2+3 |  |  |  | 1 | ,,,1 | 396.8 |  | DRY | E
105 | 17/1 | DA+3 |  |  |  |  | ,,, | 393.7 |  | DRY | E
106 | 17/2 | DA+6 |  |  |  |  | ,,, | 415.9 |  | DRY | E
107 | 17/3 | DA+0 |  |  |  |  | ,,, | 422.8 |  | DRY | E
108 | 17/4 | DA+3 |  |  |  |  | ,,, | 409.9 |  | DRY
109 | 17/5 | DA+3 |  |  |  |  | ,,, | 425.3 |  | DRY | E
110 | 18/0 | DC2+0 |  |  |  |  | ,,, | 383.4 |  | DRY
111 | 18/1 | DA+0 |  |  |  |  | ,,, | 372.8 |  | DRY | E | Done
112 | 18/2 | DA+0 |  |  |  |  | ,,, | 379.8 |  | DRY | E
113 | 18/3 | DA+0 |  |  |  |  | ,,, | 371 |  | DRY
114 | 18/4 | DA+0 |  |  |  |  | ,,, | 398.7 |  | DRY | E
115 | 19/0 | DC2+0 |  |  |  |  | ,,, | 380.8 |  | DRY | E
116 | 19/1 | DA+0 |  |  |  |  | ,,, | 366.9 |  | DRY
117 | 19/2 | DA+0 |  |  |  |  | ,,, | 372.5 |  | DRY
118 | 19/3 | DA+0 |  |  |  |  | ,,, | 376.5 |  | DRY
119 | 19/4 | DA+0 |  |  |  |  | ,,, | 384.3
120 | 19/5 | DA+0 |  |  |  |  | ,,, | 375.4 |  | WIP
121 | 20/0 | DB2+0 |  |  |  |  | ,,, | 381.2
122 | 20/1 | DA+0 |  |  |  |  | ,,, | 386.782
123 | 20/2 | DA+0 |  |  |  |  | ,,, | 387.041
124 | 20/3 | DA+0 |  |  |  |  | ,,, | 348.466
125 | 21/0 | DB2+0 |  |  |  |  | ,,, | 354.965
126 | 21/1 | DA+6 |  |  |  |  | ,,, | 414.9
127 | 21/2 | DA+0 |  |  |  |  | ,,, | 407.2
128 | 21/3 | DA+6 |  |  |  |  | ,,, | 432.2
129 | 21/4 | DA+3 |  | 1 | 2 | 1 | ,1,2,1 | 401.9
130 | 21/5 | DA+6 |  |  |  |  | ,,, | 434.2 |  | WIP
131 | 21/6 | DA+3 |  |  |  |  | ,,, | 405.5
132 | 21/7 | DA+3 |  |  |  |  | ,,, | 426 |  | WIP
133 | 21/8 | DA+6 |  |  |  |  | ,,, | 406.9
134 | 21/9 | DA+3 |  |  |  |  | ,,, | 433.3 |  | DFR
135 | 21/10 | DA+6 |  |  |  |  | ,,, | 372.9 |  | DRY
136 | 22/0 | DB2+3 |  |  |  |  | ,,, | 443.5
137 | 22/1 | DA+9 |  |  |  |  | ,,, | 456.4 |  | Sandy
138 | 22/2 | DA+6 |  |  |  | 2 | ,,,2 | 379.2 |  | Sandy
139 | 22/3 | DA+9 |  |  |  | 1 | ,,,1 | 382.6 |  | Sandy
140 | 22/4 | DA+9 |  |  |  |  | ,,, | 435.6 |  | Sandy
141 | 22/5 | DA+9 | 2 | 2 | 2 | 2 | 2,2,2,2 | 402.1 |  | DRY
142 | 22/6 | DA+0 |  |  |  | 1 | ,,,1 | 417.3 |  | Sandy
143 | 22/7 | DA+0 |  | 1 |  | 1 | ,1,,1 | 347.7 |  | Sandy
144 | 22/8 | DB1+0 |  | 2 | 1 | 1 | ,2,1,1 | 356.3 |  | Sandy
145 | 22/9 | DA+6 |  |  |  |  | ,,, | 389.2 |  | Sandy
146 | 22/10 | DA+6 | 1 | 2 |  |  | 1,2,, | 343.8
147 | 22/11 | DA+6 |  | 2 |  |  | ,2,, | 395.5 |  | Sandy
148 | 22/12 | DA+3 | 1 | 2 |  |  | 1,2,, | 408 |  | Sandy
149 | 22/13 | DA+6 |  |  | 1 |  | ,,1, | 318 |  | Sandy
150 | 23/0 | DD45+3 | 2 | 2 | 2 | 2 | 2,2,2,2 | 447.3
151 | 24/0 | DD45+3 | 2 | 2 | 2 | 2 | 2,2,2,2 | 222.2
152 | 25/0 | DC1+6 |  |  |  |  | ,,, | 433.9 |  | DRY
153 | 25/1 | DA+3 |  |  |  |  | ,,, | 422.3 |  | DRY
154 | 25/2 | DA+0 |  |  |  |  | ,,, | 370.7 |  | DRY
155 | 25/3 | DA+0 | 1 | 2 |  | 2 | 1,2,,2 | 345.7 |  | Sandy
156 | 25/4 | DA+0 | 1 | 1 |  | 1 | 1,1,,1 | 391.1 |  | Sandy
157 | 26/0 | DB1+0 |  |  |  |  | ,,, | 440.4
158 | 26/1 | DA+0 |  |  |  |  | ,,, | 391.4
159 | 26/2 | DA+3 |  |  |  |  | ,,, | 406.5 |  | DFR
160 | 26/3 | DA+0 |  |  |  |  | ,,, | 418 |  | DRY
161 | 26/4 | DA+6 | 1 |  |  |  | 1,,, | 422.6 |  | Sandy
162 | 26/5 | DA+6 | 1 | 1 |  |  | 1,1,, | 410 |  | Sandy
163 | 26/6 | DA+6 |  | 1 | 1 |  | ,1,1, | 363.4 |  | Sandy
164 | 26/7 | DA+0 |  |  |  |  | ,,, | 421.9 |  | DFR
165 | 26/8 | DA+6 |  |  |  |  | ,,, | 416.7
166 | 27/0 | DC1+0 |  |  |  |  | ,,, | 413.8 |  | WIP
167 | 27/1 | DA+3 |  |  |  |  | ,,, | 399.8 |  | WIP
168 | 27/2 | DA+3 |  |  |  |  | ,,, | 425.2 |  | DFR
169 | 27/3 | DA+3 |  |  |  |  | ,,, | 398.6 |  | DFR
170 | 27/4 | DA+3 |  |  |  |  | ,,, | 430.7 |  | DFR
171 | 27/5 | DA+0 |  |  |  |  | ,,, | 410 |  | DRY
172 | 27/6 | DA+0 |  |  |  |  | ,,, | 402.6 |  | Sandy
173 | 27/7 | DB1+0 |  |  |  |  | ,,, | 343.5 |  | DFR
174 | 27/8 | DA+0 |  |  |  |  | ,,, | 392 |  | DFR
175 | 27/9 | DA+0 |  |  |  |  | ,,, | 381.1 |  | DFR
176 | 27/10 | DA+3 |  |  |  |  | ,,, | 366.3 |  | DFR
177 | 27/11 | DA+3 |  |  |  |  | ,,, | 420.1 |  | DRY
178 | 27/12 | DA+3 |  |  |  |  | ,,, | 420.8 |  | Sandy
179 | 28/0 | DB2+0 |  |  |  |  | ,,, | 406.6 |  | DFR
180 | 28/1 | DA+0 |  |  |  |  | ,,, | 379.6
181 | 28/2 | DA+0 |  |  |  |  | ,,, | 385 |  | DFR
182 | 28/3 | DA+0 |  |  |  |  | ,,, | 369 |  | DFR
183 | 28/4 | DA+0 |  |  |  |  | ,,, | 409 |  | Sandy
184 | 28/5 | DA+9 |  | 2 |  |  | ,2,, | 422 |  | Sandy
185 | 28/6 | DA+6 | 1 | 4 | 3 |  | 1,4,3, | 370 |  | Sandy
186 | 28/7 | DA+3 | 1 | 3 | 2 |  | 1,3,2, | 464 |  | Sandy
187 | 28/8 | DA+3 |  |  | 5 | 3 | ,,5,3 | 375 |  | Sandy
188 | 29/0 | DB1+0 |  |  |  |  | ,,, | 465.5 |  | DRY
189 | 29/1 | DA+3 |  |  |  |  | ,,, | 365.6 |  | DRY
190 | 29/2 | DA+3 |  |  |  |  | ,,, | 424 |  | DRY
191 | 29/3 | DA+0 |  |  |  |  | ,,, | 399 |  | Sandy
192 | 29/4 | DA+6 |  |  |  |  | ,,, | 440 |  | DRY
193 | 30/0 | DC1+0 |  |  |  |  | ,,, | 382.1 |  | DRY
194 | 30/1 | DA+0 | 2 |  |  |  | 2,,, | 388.9 |  | Sandy
195 | 30/2 | DA+0 | 1 | 2 |  |  | 1,2,, | 445 |  | Sandy
196 | 30/3 | DA+3 | 1 | 2 |  |  | 1,2,, | 395 |  | Sandy
197 | 30/4 | DA+3 |  |  |  |  | ,,, | 387 |  | DRY
198 | 30/5 | DA+3 |  |  |  |  | ,,, | 442 |  | WIP
199 | 30/6 | DA+0 |  |  |  |  | ,,, | 314
200 | 31/0 | DB2+0 |  |  |  |  | ,,, | 347.4
201 | 31/1 | DA+0 |  |  |  |  | ,,, | 383.6 |  | DRY
202 | 31/2 | DA+0 |  |  |  |  | ,,, | 366 |  | DRY
203 | 32/0 | DC1+0 |  |  |  |  | ,,, | 332.9 |  | DRY
204 | 32/1 | DA+3 |  |  |  |  | ,,, | 402.7 |  | Sandy
205 | 32/2 | DA+3 |  |  |  |  | ,,, | 428.8 |  | DRY
206 | 32/3 | DA+0 |  |  |  |  | ,,, | 410.9 |  | Sandy
207 | 32/4 | DA+0 |  |  |  |  | ,,, | 381.1 |  | Sandy
208 | 33/0 | DC1+0 | 1 |  |  |  | 1,,, | 451.5 |  | DRY
209 | 33/1 | DA+0 |  | 1 | 1 |  | ,1,1, | 379.6 |  | DRY
210 | 34/0 | DB2+0 |  |  |  |  | ,,, | 292.5 |  | DRY
211 | 34/1 | DA+9 |  |  |  |  | ,,, | 432.6 |  | Sandy
212 | 34/2 | DA+6 |  |  |  | 2 | ,,,2 | 407.5 |  | Sandy
213 | 34/3 | DA+0 |  | 3 |  |  | ,3,, | 377 |  | Sandy
214 | 34/4 | DA+0 |  | 3 | 1 |  | ,3,1, | 451.6 |  | Sandy
215 | 35/0 | DB2+6 | 2 |  |  |  | 2,,, | 379.3 |  | Sandy
216 | 35/1 | DA+9 | 2 |  |  | 2 | 2,,,2 | 265.6 |  | Sandy
217 | 35/2 | DB1+0 | 1 | 1 |  |  | 1,1,, | 492.4 |  | Sandy
218 | 35/3 | DB1+6 | 1 |  |  |  | 1,,, | 522.2 |  | Sandy
219 | 35/4 | DA+0 |  |  |  |  | ,,, | 418.9 |  | DRY
220 | 35/5 | DA+0 |  |  | 4 | 4 | ,,4,4 | 421.7 |  | Sandy
221 | 36/0 | DB2+0 |  |  |  |  | ,,, | 342.7 |  | Sandy
222 | 36/1 | DA+0 |  |  |  |  | ,,, | 386.4 |  | Sandy
223 | 36/2 | DA+0 | 1 | 1 |  |  | 1,1,, | 309.4
224 | 36/3 | DA+0 |  | 2 |  |  | ,2,, | 357.8
225 | 36/4 | DA+6 | 2 | 3 |  | 5 | 2,3,,5 | 480.4
226 | 37/0 | DB2+0 |  |  |  | 1 | ,,,1 | 350.5
227 | 37/1 | DA+9 | 2 | 2 | 2 | 1 | 2,2,2,1 | 443.3
228 | 37/2 | DA+3 |  |  |  |  | ,,, | 356.7
229 | 37/3 | DA+0 |  |  |  |  | ,,, | 339.9 |  | Sandy
230 | 38/0 | DB2+6 |  |  |  |  | ,,, | 500.3 |  | Sandy
231 | 38/1 | DA+0 |  |  |  |  | ,,, | 421.4 |  | Sandy
232 | 38/2 | DA+6 |  |  |  |  | ,,, | 419 |  | Sandy
233 | 38/3 | DA+9 | 2 | 2 | 2 | 2 | 2,2,2,2 | 420.3 |  | Sandy
234 | 38/4 | DA+9 | 1 | 1 |  | 1 | 1,1,,1 | 414.9 |  | Sandy
235 | 39/0 | DB2+6 |  |  |  |  | ,,, | 425.5 |  | Sandy
236 | 39/1 | DA+0 |  |  |  |  | ,,, | 412.6 |  | Sandy
237 | 40/0 | DC2+0 | 1 | 1 |  |  | 1,1,, | 322.6 |  | Sandy
238 | 40/1 | DA+6 | 1 | 2 |  |  | 1,2,, | 396.2 |  | Sandy
239 | 40/2 | DA+3 |  |  |  |  | ,,, | 425.8 |  | Sandy
240 | 40/3 | DA+3 | 1 | 2 |  |  | 1,2,, | 401.7 |  | Sandy
241 | 41/0 | DC1+6 | 3 | 1 |  | 1 | 3,1,,1 | 436.3 |  | WIP
242 | 41/1 | DB1+9 | 4 | 5 | 6 | 6 | 4,5,6,6 | 340.8 |  | Sandy
243 | 41/2 | DA+0 |  |  | 1 | 1 | ,,1,1 | 447.8 |  | Sandy
244 | 42/0 | DC1+0 | 1 |  |  | 2 | 1,,,2 | 382.3 |  | Sandy
245 | 42/1 | DA+6 | 1 |  |  |  | 1,,, | 384.7 |  | Sandy
246 | 42/2 | DA+6 |  |  | 1 | 3 | ,,1,3 | 407.4 |  | Sandy
247 | 42/3 | DA+0 |  |  |  |  | ,,, | 414.2 |  | Sandy
248 | 42/4 | DA+0 |  |  |  |  | ,,, | 256.4 |  | Sandy
249 | 42/5 | DA+9 |  |  |  | 1 | ,,,1 | 403.8 |  | Sandy
250 | 42/6 | DA+0 | 2 | 1 |  | 2 | 2,1,,2 | 396.7 |  | Sandy
251 | 43/0 | DB1+0 |  |  |  |  | ,,, | 403.9 |  | Sandy | E
252 | 43/1 | DA+3 |  |  | 3 | 3 | ,,3,3 | 346 |  | Sandy | E
253 | 43/2 | DA+0 | 1 |  |  | 1 | 1,,,1 | 475.8 |  | Sandy
254 | 43/3 | DA+0 |  | 1 |  |  | ,1,, | 363.7 |  | DRY
255 | 43/4 | DA+3 | 1 | 1 |  |  | 1,1,, | 431.8 |  | Sandy
256 | 43/5 | DA+3 |  |  |  |  | ,,, | 405.3 |  | DRY
257 | 43/6 | DA+3 |  |  |  |  | ,,, | 427.8 |  | Sandy | E
258 | 43/7 | DA+3 |  |  |  |  | ,,, | 389.8 |  | Sandy | E
259 | 43/8 | DA+9 | 1 |  |  |  | 1,,, | 449.5 |  | Sandy | E
260 | 43/9 | DA+9 |  |  |  |  | ,,, | 388 |  | Sandy | E
261 | 43/10 | DA+3 | 3 | 3 |  |  | 3,3,, | 346.3 |  | Sandy
262 | 43/11 | DA+3 | 2 | 3 |  | 1 | 2,3,,1 | 444.8 |  | Sandy
263 | 44/0 | DB1+3 | 0 | 1 | 1 | 0 | 0,1,1,0 | 384.3 |  | Sandy
264 | 44/1 | DA+0 | 0 | 0 | 1 | 0 | 0,0,1,0 | 384.3 |  | Sandy
265 | 44/2 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 359 |  | Sandy
266 | 44/3 | DA+0 | 2 | 0 | 0 | 1 | 2,0,0,1 | 334 |  | Sandy
267 | 44/4 | DA+9 | 4 | 3 | 3 | 3 | 4,3,3,3 | 395 |  | Sandy
268 | 44/5 | DA+9 | 1 | 3 | 0 | 0 | 1,3,0,0 | 355 |  | Sandy
269 | 44/6 | DB1+3 | 1 | 0 | 0 | 1 | 1,0,0,1 | 485 |  | Sandy
270 | 44/7 | DA+9 | 0 | 0 | 0 | 0 | 0,0,0,0 | 473 |  | Sandy
271 | 44/8 | DCT+0 | 1 | 2 | 0 | 1 | 1,2,0,1 | 367 |  | Sandy
272 | 44/9 | DA+9 | 4 | 0 | 2 | 6 | 4,0,2,6 | 430 |  | Sandy
273 | 44/10 | DB1+9 | 0 | 1 | 0 | 0 | 0,1,0,0 | 365 |  | Sandy
274 | 44/11 | DA+0 | 0 | 1 | 0 | 0 | 0,1,0,0 | 428 |  | Sandy
275 | 45/0 | DC2+0 | 0 | 1 | 0 | 0 | 0,1,0,0 | 327.2 |  | Sandy
276 | 45/1 | DA+9 | 0 | 0 | 6 | 6 | 0,0,6,6 | 294.92 |  | Sandy
277 | 46/0 | DD60+25 | 0 | 6 | 6 | 2 | 0,6,6,2 | 406.54 |  | Sandy
278 | 47/0 | DD60+25 | 5 | 5 | 5 | 5 | 5,5,5,5 | 199.08 |  | Sandy
279 | 47/1 | DA+3 | 2 | 0 | 2 | 5 | 2,0,2,5 | 441.2 |  | Sandy
280 | 47/2 | DA+9 | 0 | 0 | 0 | 0 | 0,0,0,0 | 365.93 |  | Sandy
281 | 47/3 | DA+9 | 1 | 2 | 0 | 0 | 1,2,0,0 | 417.4 |  | Sandy
282 | 47/4 | DA+3 |  |  |  |  | ,,, | 358.4 |  | Sandy
283 | 47/5 | DA+0 | 0 | 1 | 0 | 0 | 0,1,0,0 | 461.2 |  | Sandy
284 | 47/6 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 377.3 |  | Sandy
285 | 47/7 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 431.5 |  | Sandy
286 | 47/8 | DA+0 | 1 | 0 | 0 | 0 | 1,0,0,0 | 398.8 |  | Sandy | E | Done
287 | 47/9 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 405.9 |  | Sandy | E | Done
288 | 47/10 | DA+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 433.7 |  | Sandy | E | Done
289 | 48/0 | DC2+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 386.2 |  | Sandy | E | Done
290 | 48/1 | DA+9 | 0 | 0 | 0 | 0 | 0,0,0,0 | 428.9 |  | Sandy | E | Done
291 | 49/0 | DD45+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 402.9 |  | Sandy | E | Done
292 | 49/1 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 379.1 |  | Sandy | E | Done
293 | 49/2 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 386.6 |  | Sandy | E | Done
294 | 49/3 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 390 |  | Sandy | E | Done
295 | 49/4 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 421.7 |  | Sandy | E | Done
296 | 49/5 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 396.6 |  | Sandy | E | Done
297 | 49/6 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 412.8 |  | Sandy | E | Done
298 | 49/7 | DA+0 | 0 | 3 | 2 | 2 | 0,3,2,2 | 340.2 |  | Sandy | E | Done
299 | 50/0 | DB2+0 | 0 | 0 | 0 | 1 | 0,0,0,1 | 500.2 |  | Sandy | E | Done
300 | 50/1 | DA+6 | 1 | 0 | 0 | 0 | 1,0,0,0 | 469.1 |  | Sandy | E | Done
301 | 50/2 | DA+9 | 2 | 2 | 2 | 2 | 2,2,2,2 | 367.1 |  | Sandy | E | Done
302 | 50/3 | DA+6 | 0 | 0 | 1 | 0 | 0,0,1,0 | 470.4 |  | Sandy | E | Done
303 | 50/4 | DA+9 | 3 | 3 | 4 | 3 | 3,3,4,3 | 354.8 |  | Sandy | E | Done
304 | 50/5 | DA+9 | 4 | 3 | 4 | 3 | 4,3,4,3 | 442.1 |  | Sandy | E | Done
305 | 50/6 | DA+9 | 3 | 4 | 3 | 3 | 3,4,3,3 | 364.4 |  | Sandy | E | Done
306 | 50/7 | DA+0 | 0 | 0 | 0 | 1 | 0,0,0,1 | 470.8 |  | Sandy | E | Done
307 | 50/8 | DA+9 | 0 | 0 | 0 | 0 | 0,0,0,0 | 345 |  | Sandy | E | Done
308 | 50/9 | DA+0 | 0 | 0 | 1 | 0 | 0,0,1,0 | 364.4 |  | Sandy | E | Done
309 | 50/10 | DA+0 | 0 | 0 | 1 | 0 | 0,0,1,0 | 394.6 |  | Sandy | E | Done
310 | 51/0 | DC2+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 401.4 |  | Sandy | E | Done
311 | 51/1 | DA+0 | 0 | 0 | 1 | 0 | 0,0,1,0 | 356.6 |  | Sandy | E | Done
312 | 51/2 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 307.1 |  | Sandy | E | Done
313 | 52/0 | DC2+0 | 0 | 0 | 3 | 3 | 0,0,3,3 | 385 |  | Sandy | E | Done
314 | 52/1 | DA+6 | 0 | 4 | 0 | 0 | 0,4,0,0 | 402 |  | Sandy
315 | 52/2 | DA+6 | 0 | 0 | 0 | 3 | 0,0,0,3 | 402.6 |  | Sandy
316 | 52/3 | DA+9 | 4 | 3 | 3 | 3 | 4,3,3,3 | 437 |  | Sandy
317 | 52/4 | DA+9 | 2 | 2 | 0 | 0 | 2,2,0,0 | 393.8 |  | Sandy
318 | 52/5 | DA+9 | 0 | 0 | 0 | 1 | 0,0,0,1 | 447 |  | Sandy | E | Done
319 | 52/6 | DA+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 373 |  | Sandy | E | Done
320 | 52/7 | DA+3 | 0 | 3 | 1 | 0 | 0,3,1,0 | 406.8 |  | Sandy | E | Done
321 | 52/8 | DA+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 433 |  | Sandy | E | Done
322 | 52/9 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 399.7 |  | Sandy | E | Done
323 | 52/10 | DA+9 | 1 | 2 | 1 | 1 | 1,2,1,1 | 384.1 |  | Sandy | E | Done
324 | 53/0 | DB2+9 | 4 | 4 | 4 | 4 | 4,4,4,4 | 455.9 |  | Sandy | E
325 | 53/1 | DA+9 | 4 | 4 | 4 | 4 | 4,4,4,4 | 433.2 |  | Sandy | E
326 | 53/2 | DA+0 | 0 | 0 | 0 | 2 | 0,0,0,2 | 407.4 |  | Sandy | E
327 | 53/3 | DA+6 | 0 | 4 | 1 | 0 | 0,4,1,0 | 394.5 |  | Sandy | E
328 | 53/4 | DA+0 | 0 | 2 | 1 | 0 | 0,2,1,0 | 410.1 |  | Sandy | E
329 | 53/5 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 428.1 |  | Sandy | E
330 | 53/6 | DA+6 | 1 | 1 | 3 | 1 | 1,1,3,1 | 406.6 |  | Sandy | E
331 | 53/7 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 411.3 |  | Sandy | E
332 | 53/8 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 427.8 |  | Sandy | E
333 | 54/0 | DB1+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 371.3 |  | Sandy
334 | 54/1 | DA+3 | 1 | 1 | 0 | 0 | 1,1,0,0 | 365.1 |  | Sandy
335 | 54/2 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 381 |  | Sandy
336 | 54/3 | DA+6 | 0 | 2 | 0 | 0 | 0,2,0,0 | 417 |  | Sandy
337 | 54/4 | DA+9 | 1 | 2 | 0 | 0 | 1,2,0,0 | 423.3 |  | Sandy
338 | 54/5 | DA+9 | 1 | 3 | 3 | 1 | 1,3,3,1 | 401 |  | Sandy
339 | 55/0 | DB1+6 | 0 | 1 | 1 | 0 | 0,1,1,0 | 424 |  | Sandy
340 | 55/1 | DA+0 |  |  |  |  | ,,, | 404.9 |  | WFR
341 | 55/2 | DA+0 |  |  |  |  | ,,, | 343.1 |  | WFR
342 | 55/3 | DA+0 |  |  |  |  | ,,, | 357.7 |  | Sandy | E | Done
343 | 55/4 | DA+0 | 0 | 0 | 0 | 1 | 0,0,0,1 | 365.2 |  | Sandy | E | Done
344 | 55/5 | DA+0 | 0 | 0 | 1 | 3 | 0,0,1,3 | 350.1 |  | Sandy | E | Done
345 | 55/6 | DA+0 | 0 | 0 | 1 | 2 | 0,0,1,2 | 357.7 |  | Sandy | E | Done
346 | 55/7 | DA+0 | 0 | 0 | 1 | 0 | 0,0,1,0 | 337.8 |  | Sandy
347 | 55/8 | DA+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 341.22 |  | Sandy
348 | 56/0 | DD60+25 | 3 | 3 | 0 | 2 | 3,3,0,2 | 460.49 |  | Sandy
349 | 57/0 | DD60+25 | 0 | 0 | 0 | 0 | 0,0,0,0 | 219.76 |  | Sandy
350 | 57/1 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 461.11 |  | Sandy
351 | 57/2 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 355.5 |  | DRY
352 | 57/3 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 405.4 |  | DRY | E | Done
353 | 57/4 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 418.2 |  | Sandy | E | Done
354 | 57/5 | DA+3 | 0 | 0 | 0 | 1 | 0,0,0,1 | 416.8 |  | Sandy | E | Done
355 | 57/6 | DA+3 | 0 | 1 | 0 | 0 | 0,1,0,0 | 395 |  | Sandy | E | Done
356 | 57/7 | DA+3 |  |  |  |  | ,,, | 401.8 |  | DFR | E | Done
357 | 58/0 | DC1+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 433.9 |  | DFR | E | Done
358 | 59/0 | DC2+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 238.897 |  | DRY | E | Done
359 | 59/1 | DA+3 | 0 | 0 | 0 | 1 | 0,0,0,1 | 411.3 |  | DRY | E | Done
360 | 59/2 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 418.204 |  | DFR | E | Done
361 | 59/3 | DA+3 | 0 | 0 | 0 | 1 | 0,0,0,1 | 412.3 |  | DFR | E | Done
362 | 59/4 | DA+3 |  |  |  |  | ,,, | 421 |  | DFR | E | Done
363 | 59/5 | DA+3 |  |  |  |  | ,,, | 419.7 |  | DFR | E | Done
364 | 59/6 | DA+3 |  |  |  |  | ,,, | 419.1 |  | DFR | E | Done
365 | 59/7 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 408.8 |  | DRY | E | Done
366 | 59/8 | DB1+3 |  |  |  |  | ,,, | 426.9 |  | DRY | E | Done
367 | 59/9 | DA+3 |  |  |  |  | ,,, | 434.7 |  | DRY | E | Done
368 | 59/10 | DA+0 |  |  |  |  | ,,, | 400.8 |  | DRY | E | Done
369 | 59/11 | DA+6 | 0 | 0 | 2 | 0 | 0,0,2,0 | 436.3 |  | DFR | E | Done
370 | 59/12 | DA+6 |  |  |  |  | ,,, | 393.1 |  | DFR | E | Done
371 | 59/13 | DA+3 |  |  |  |  | ,,, | 447.4 |  | DRY | E | Done
372 | 59/14 | DA+6 |  |  |  |  | ,,, | 391.1 |  | DRY | E | Done
373 | 59/15 | DA+6 |  |  |  |  | ,,, | 448.6 |  | DRY | E | Done
374 | 59/16 | DA+9 |  |  |  |  | ,,, | 388 |  | Dry | E | Done
375 | 60/0 | DC1+0 |  |  |  |  | ,,, | 438 |  | DRY | E | Done
376 | 60/1 | DA+6 |  |  |  |  | ,,, | 413.8 |  | DRY | E | Done
377 | 60/2 | DA+3 | 2 | 2 | 0 | 0 | 2,2,0,0 | 424.2 |  | DFR | E | Done
378 | 60/3 | DA+3 |  |  |  |  | ,,, | 414.5 |  | DFR | E | Done
379 | 60/4 | DA+3 |  |  |  |  | ,,, | 425.6 |  | DFR | E | Done
380 | 60/5 | DA+3 |  |  |  |  | ,,, | 412.3 |  | DRY | E | Done
381 | 60/6 | DA+0 |  |  |  |  | ,,, | 374.1 |  | DRY | E | Done
382 | 60/7 | DA+3 |  |  |  |  | ,,, | 410.1 |  | DRY | E | Done
383 | 60/8 | DA+0 |  |  |  |  | ,,, | 400.4 |  | DRY | E | Done
384 | 60/9 | DA+3 |  |  |  |  | ,,, | 409.2 |  | DRY | E | Done
385 | 60/10 | DA+0 |  |  |  |  | ,,, | 401 |  | DFR | E | Done
386 | 60/11 | DA+3 |  |  |  |  | ,,, | 394.5 |  | DRY | E | Done
387 | 61/0 | DB2+0 |  |  |  |  | ,,, | 397.9 |  | DRY | E | Done
388 | 61/1 | DA+6 | 0 | 0 | 0 | 0 | 0,0,0,0 | 405.7 |  | DFR | E | Done
389 | 61/2 | DA+6 |  |  |  |  | ,,, | 433.2 |  | DFR | E | Done
390 | 61/3 | DA+6 |  |  |  |  | ,,, | 400.9 |  | DRY | E | Done
391 | 61/4 | DA+3 |  |  |  |  | ,,, | 427 |  | DRY | E | Done
392 | 61/5 | DA+3 |  |  |  |  | ,,, | 413.9 |  | DRY | E | Done
393 | 61/6 | DA+3 |  |  |  |  | ,,, | 426.4 |  | DRY | E | Done
394 | 61/7 | DA+9 | 0 | 0 | 0 | 1 | 0,0,0,1 | 411.5 |  | Dry | E | Done
395 | 61/8 | DA+6 | 1 | 2 | 1 | 0 | 1,2,1,0 | 376.3 |  | DRY | E | Done
396 | 61/9 | DA+0 |  |  |  |  | ,,, | 433.4 |  | Dry | E | Done
397 | 61/10 | DA+9 |  |  |  |  | ,,, | 405.6 |  | DRY | E | Done
398 | 62/0 | DB2+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 434.3 |  | DRY | E | Done
399 | 62/1 | DA+3 | 0 | 0 | 1 | 2 | 0,0,1,2 | 418 |  | Sandy | E | Done
400 | 62/2 | DA+3 | 0 | 1 | 0 | 0 | 0,1,0,0 | 386 |  | DRY | E | Done
401 | 62/3 | DA+0 |  |  |  |  | ,,, | 400 |  | DRY | E | Done
402 | 62/4 | DA+3 |  |  |  |  | ,,, | 401 |  | DRY | E | Done
403 | 62/5 | DA+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 403 |  | DRY | E | Done
404 | 62/6 | DA+3 |  |  |  |  | ,,, | 404 |  | DRY | E | Done
405 | 62/7 | DA+3 |  |  |  |  | ,,, | 423 |  | DRY | E | Done
406 | 62/8 | DA+0 |  |  |  |  | ,,, | 409 |  | DFR | E | Done
407 | 62/9 | DA+3 |  |  |  |  | ,,, | 409 |  | DFR | E | Done
408 | 62/10 | DA+0 |  |  |  |  | ,,, | 411 |  | DFR | E | Done
409 | 62/11 | DA+3 |  |  |  |  | ,,, | 413 |  | DRY | E | Done
410 | 63/0 | DC1+0 | 0 | 0 | 0 | 0 | 0,0,0,0 | 386.1 |  | DFR | E | Done
411 | 63/1 | DA+3 |  |  |  |  | ,,, | 400 |  | DFR | E | Done
412 | 63/2 | DA+0 |  |  |  |  | ,,, | 416 |  | DFR | E | Done
413 | 63/3 | DA+3 | 0 | 0 | 0 | 0 | 0,0,0,0 | 411 |  | DFR | E | Done
414 | 63/4 | DA+0 |  |  |  |  | ,,, | 399 |  | DRY | E | Done
415 | 63/5 | DA+3 |  |  |  |  | ,,, | 413 |  | DFR | E | Done
416 | 63/6 | DA+3 |  |  |  |  | ,,, | 426 |  | DRY | E | Done
417 | 63/7 | DA+3 |  |  |  |  | ,,, | 413 |  | DRY | E | Done
418 | 63/8 | DA+3 |  |  |  |  | ,,, | 425 |  | DRY | E | Done
419 | 64/0 | DB2+0 |  |  |  |  | ,,, | 408.3 |  | DRY | E | Done
420 | 64/1 | DA+0 |  |  |  |  | ,,, | 375.1 |  | DRY | E | Done
421 | 64/2 | DA+3 |  |  |  |  | ,,, | 408.7 |  | DRY | E | Done
422 | 64/3 | DA+0 |  |  |  |  | ,,, | 410.7 |  | DRY | E | Done
423 | 64/4 | DA+3 |  |  |  |  | ,,, | 408.2 |  | DRY | E | Done
424 | 64/5 | DA+3 |  |  |  |  | ,,, | 426.2 |  | DRY | E | Done
425 | 64/6 | DA+0 |  |  |  |  | ,,, | 407.7 |  | DRY | E | Done
426 | 64/7 | DA+3 |  |  |  |  | ,,, | 401.6 |  | DRY | E | Done
427 | 64/8 | DA+3 |  |  |  |  | ,,, | 425.5 |  | DRY | E | Done
428 | 64/9 | DA+3 |  |  |  |  | ,,, | 414.4 |  | DRY | E | Done
429 | 64/10 | DA+3 |  |  |  |  | ,,, | 410.6 |  | DRY | E | Done
430 | 64/11 | DA+3 |  |  |  |  | ,,, | 428.4 |  | DRY | E | Done
431 | 65/0 | DB1+0 |  |  |  |  | ,,, | 400.6 |  | DRY | E | Done
432 | 65/1 | DA+0 |  |  |  |  | ,,, | 395.4 |  | DRY | E | Done
433 | 65/2 | DA+0 |  |  |  |  | ,,, | 393.7 |  | DRY | E | Done
434 | 65/3 | DA+3 |  |  |  |  | ,,, | 403.7 |  | DRY | E | Done
435 | 65/4 | DA+0 |  |  |  |  | ,,, | 402.9 |  | DRY | E | Done
436 | 65/5 | DA+0 |  |  |  |  | ,,, | 376.4 |  | DRY | E | Done
437 | 65/6 | DA+0 |  |  |  |  | ,,, | 389.2 |  | DRY | E | Done
438 | 65/7 | DA+0 |  |  |  |  | ,,, | 397.6 |  | DRY | E | Done
439 | 65/8 | DA+0 |  |  |  |  | ,,, | 394.3 |  | DRY | E | Done
440 | 65/9 | DA+0 |  |  |  |  | ,,, | 389 |  | DRY | E | Done
441 | 65/10 | DA+0 |  |  |  |  | ,,, | 379.1 |  | DRY | E | Done
442 | 65/11 | DA+0 |  |  |  |  | ,,, | 387.6 |  | DRY | E | Done
443 | 66/0 | DC2+6 |  |  |  |  | ,,, | 426.9 |  | DRY | E | Done
444 | 67/0 | DC1+9 |  |  |  |  | ,,, | 207.8 |  | DRY | E
445 | 67/1 | DA+0 |  |  |  |  | ,,, | 347.1 |  | DRY | E | Done
446 | 67/2 | DA+0 |  |  |  |  | ,,, | 344.9 |  | DRY | E | Done
447 | 68/0 | DD45+0 |  |  |  |  | ,,, | 369.2 |  | DRY | E
448 | 69/0 | DB2+0 |  |  |  |  | ,,, | 200.9 |  | DFR
449 | 69/1 | DA+3 |  |  |  |  | ,,, | 374.1 |  | DRY
450 | 70/0 | DC1+0 |  |  |  |  | ,,, | 394.9 |  | DRY
451 | 70/1 | DA+3 |  |  |  |  | ,,, | 388.4 |  | DRY
452 | 70/2 | DA+3 |  |  |  |  | ,,, | 418.9 |  | DRY
453 | 70/3 | DA+3 |  |  |  |  | ,,, | 418.6 |  | DRY | E | Done
454 | 70/4 | DA+3 |  |  |  |  | ,,, | 414 |  | DRY | E | Done
455 | 70/5 | DA+3 |  |  |  |  | ,,, | 419.6 |  | DRY | E | Done
456 | 70/6 | DA+3 |  |  |  |  | ,,, | 420.3 |  | DRY
457 | 70/7 | DA+3 |  |  |  |  | ,,, | 419.6 |  | DRY
458 | 70/8 | DA+3 |  |  |  |  | ,,, | 418.2 |  | DRY
459 | 70/9 | DA+3 |  |  |  |  | ,,, | 414.1 |  | DRY | E | Done
460 | 70/10 | DA+3 |  |  |  |  | ,,, | 406.1 |  | DRY | E | Done
461 | 70/11 | DA+3 |  |  |  |  | ,,, | 408.6 |  | DRY | E | Done
462 | 71/0 | DB2+3 |  |  |  |  | ,,, | 420.4 |  | DRY | E | Done
463 | 71/1 | DA+3 |  |  |  |  | ,,, | 398.6 |  | DRY | E | Done
464 | 71/2 | DA+3 |  |  |  |  | ,,, | 414.3 |  | DRY | E | Done
465 | 71/3 | DA+6 |  |  |  |  | ,,, | 413 |  | DRY | E | Done
466 | 71/4 | DA+3 |  |  |  |  | ,,, | 367.7 |  | DRY | E | Done
467 | 71/5 | DA+3 |  |  |  |  | ,,, | 429.4 |  | DRY | E | Done
468 | 71/6 | DA+0 |  |  |  |  | ,,, | 408 |  | DRY | E | Done
469 | 71/7 | DA+3 |  |  |  |  | ,,, | 404.9 |  | DRY | E | Done
470 | 71/8 | DA+3 |  |  |  |  | ,,, | 431.6 |  | DRY | E | Done
471 | 72/0 | DB2+3 |  |  |  |  | ,,, | 408.4 |  | DRY | E
472 | 72/1 | DA+3 |  |  |  |  | ,,, | 435.3 |  | DRY | E | Done
473 | 72/2 | DA+0 |  |  |  |  | ,,, | 403.9 |  | DRY | E | Done
474 | 72/3 | DA+3 |  |  |  |  | ,,, | 389.2 |  | DRY | E | Done
475 | 73/0 | DB2+0 |  |  |  |  | ,,, | 400.1 |  | DRY | E | Done
476 | 73/1 | DA+0 |  |  |  |  | ,,, | 383.3 |  | DRY | E | Done
477 | 73/2 | DA+0 |  |  |  |  | ,,, | 379 |  | DRY | E | Done
478 | 73/3 | DA+0 |  |  |  |  | ,,, | 381.2 |  | DRY | E | Done
479 | 73/4 | DA+0 |  |  |  |  | ,,, | 384.7 |  | DRY | E | Done
480 | 73/5 | DA+0 |  |  |  |  | ,,, | 368.8 |  | DRY | E | Done
481 | 73/6 | DA+0 |  |  |  |  | ,,, | 365.5 |  | DRY | E | Done
482 | 73/7 | DA+0 |  |  |  |  | ,,, | 392.4 |  | DRY | E | Done
483 | 73/8 | DA+3 |  |  |  |  | ,,, | 374.9 |  | DRY | E | Done
484 | 73/9 | DA+0 |  |  |  |  | ,,, | 379.5 |  | DRY | E | Done
485 | 74/0 | DB2+0 |  |  |  |  | ,,, | 378.9 |  | Sandy | E | Done
Note on F112: Raghav Ranjan: in approved survey 1 mrc in pit C & D. but actual no any RC casted
Note on G372: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AS PER APPROVED CHECK SURVEY, 1 M RC IN PIT A BUT SAME WAS REVISED (PIT d IN PLACE OF PIT A) AS PER INSTRUCTION BY SACHCHIDANAND ON DATED 28.08.24

## Benching F
Progress Summary'!A1 | [7 empty] | Total | 35308.5487 |  | 22312.4407 |  | 9429.231
RC, Benching & Revetment Locations
Sl No. | Loc No. | Tower Type | CP Position Up/Down | Raised Chimney | Chimney Extension |  |  |  | Submitted Benching Volume (Cum) |  | Approved Benching Volume (Cum) during check survey |  | Approved Benching Volume (Cum) after execution
[5 empty] | A | B | C | D | Cutting | Filling | Cutting | Filling
1 | 1A/0 | DD60+0 |  | 280.663 |  |  |  | 1 | 396.753 |  | 396.753 |  | 396.75 | DRY
2 | 1A/2 | DA+0 |  | 289.355 |  | 1 | 1 |  | 135.475 |  | 126.578
3 | 1A/4 | DA+3 |  | 279.611 |  |  | 1 |  | 96.198 |  | 84.47
4 | 1A/5 | DA+0 |  | 283.369 | 1 | 1 |  |  | 90.818 |  | 90.818
5 | 1A/6 | DA+0 |  | 285.088 | 1 |  |  | 1 | 115.601 |  | 95.447
6 | 1A/7 | DA+3 |  | 279.351 |  | 1 |  |  | 16.618 |  | 15.102
7 | 2/2 | DA+3 |  | 286.123 |  |  |  | 1 | 32.393 |  | 32.393
8 | 2/3 | DA+3 |  | 291.649 | 1 |  | 1 | 1 | 6.352 |  | 6.352
9 | 2/5 | DA+3 | -0.3 | 295.847 |  |  | 1 | 1 | 37.105 |  | 37.105
10 | 2/6 | DA+3 |  | 295.748 |  |  |  | 1 | 183.868 |  | 183.868
11 | 5/0 | DB1+9 |  | 276.367 | 5 | 5 | 5 | 5
12 | 6/0 | DB2+9 |  | 278.864 | 5 | 5 | 5 | 5
13 | 6/2 | DA+0 |  | 285.435 |  |  |  |  | 62.716 |  | 62.716
14 | 7/0 | DB1+0 |  | 285.258 | 2 | 3 | 3 | 2 | 38.395 |  | 38.395
15 | 8/1 | DA+3 |  | 277.532 |  |  |  |  | 95.017 |  | 95.017
16 | 8/5 | DA+3 |  | 278.292 |  |  |  | 1 | 36.524 |  | 36.524
17 | 8/11 | DA+0 | +0.10 | 258.784
18 | 10/18 | DA+3 | +0.20 | 263.543
19 | 10/22 | DA+0 | -0.30 | 267.946 | 1 |  |  | 3
20 | 10/23 | DA+0 | -0.30 | 274.896 |  | 2
21 | 11/0 | DB1+0 | -0.30 | 267.684 | 1 | 4 |  | 3
22 | 11/2 | DA+0 |  | 260.632 | 2 | 1
23 | 11/3 | DA+0 | -0.30 | 244.31 |  |  |  | 1
24 | 11A/8 | DA+6 |  | 276.713 |  | 2 | 4 | 1 | 21.332 |  | 21.332 |  | 21.331 | Sandy
25 | 13/3 | DA+3 |  | 259.023 |  |  | 2 | 4 | 263.579 |  | 263.579 |  | 263.579 | DRY
26 | 15/1 | DA+3 | +0.10 | 257.553
27 | 16/2 | DA+0 |  | 231.584 | 1 |  |  | 1 | 103.375 |  | 103.375 |  | 103.375 | DRY
28 | 16/4 | DA+0 |  | 230.932 |  | 1 |  |  | 111.857 |  | 111.857 |  | 111.857 | DRY
29 | 17/0 | DB2+3 |  | 231.525 |  |  |  | 1 | 203.454 |  | 203.454 |  | 203.454 | DRY
30 | 21/4 | DA+3 | -0.17 | 219.398 |  | 1 | 2 | 1 | 32.563 |  | 32.563
31 | 22/2 | DA+6 |  | 221.472 |  |  |  | 2 | 150.696 |  | 150.696 |  | 198.696 | Sandy
32 | 22/3 | DA+9 | -0.37 | 229.546 |  |  |  | 1 | 156.167 |  | 156.167 |  | 156.167 | Sandy
33 | 22/5 | DA+9 |  | 237.504 | 2 | 2 | 2 | 2
34 | 22/6 | DA+0 |  | 228.106 |  |  |  | 1 | 134.906 |  | 134.906 |  | 134.906 | Sandy
35 | 22/7 | DA+0 |  | 230.791 |  | 1 |  | 1 | 163.818 |  | 163.818 |  | 163.818 | DRY
36 | 22/8 | DB1+0 | -0.25 | 238.053 |  | 2 | 1 | 1 | 42.317 |  | 42.317 |  | 42.317 | Sandy
37 | 22/10 | DA+6 |  | 226.251 | 1 | 2 |  |  | 141.305 |  | 141.305
38 | 22/11 | DA+6 | -0.2 | 219.64 |  | 2 |  |  | 115.216 |  | 115.216
39 | 22/12 | DA+3 | -0.2 | 219.348 | 1 | 2 |  |  | 273.42 |  | 273.42 |  | 322.43 | Sandy
40 | 22/13 | DA+6 | -0.2 | 228.631 |  |  | 1 |  | 156.896 |  | 156.896 |  | 156.896 | Sandy
41 | 23/0 | DD45+3 |  | 234.317 | 2 | 2 | 2 | 2
42 | 24/0 | DD45+3 |  | 216.73 | 2 | 2 | 2 | 2
43 | 25/3 | DA+0 | -0.12 | 218.505 | 1 | 2 |  | 2 | 66.405 |  | 66.405 |  | 66.405 | Sandy
44 | 25/4 | DA+0 | -0.15 | 214.763 | 1 | 1 |  | 1 | 28.422 |  | 28.422 |  | 28.422 | Sandy
45 | 26/4 | DA+6 |  | 213.407 | 1 |  |  |  | 120.137 |  | 120.137 |  | 120.137 | Sandy
46 | 26/5 | DA+6 |  | 221.414 | 1 | 1 |  |  | 81.488 |  | 81.488 |  | 81.488 | Sandy
47 | 26/6 | DA+6 | 0.6 | 211.524 |  | 1 | 1 |  | 254.213 |  | 254.213 |  | 254.213 | Sandy
48 | 28/5 | DA+9 | -0.18 | 214.138 |  | 2 |  |  | 281.983 |  | 281.983 |  | 359.86 | Sandy
49 | 28/6 | DA+6 |  | 215.881 | 1 | 4 | 3 |  | 148.097 |  | 148.097 |  | 148.097 | Sandy
50 | 28/7 | DA+3 | +0.40 | 205.536 | 1 | 3 | 2 |  | 51.177 |  | 51.177 |  | 51.177 | Sandy
51 | 28/8 | DA+3 | +0.20 | 210.955 |  |  | 5 | 3 | 89.36 |  | 89.36 |  | 172.933 | Sandy
52 | 30/1 | DA+0 | +0.29 | 207.56 | 2 |  |  |  | 25.504 |  | 25.504 |  | 25.504 | Sandy
53 | 30/2 | DA+0 |  | 202.695 | 1 | 2 |  |  | 263.44 |  | 263.44 |  | 263.44 | Sandy
54 | 30/3 | DA+3 |  | 197.067 | 1 | 2 |  |  | 59.056 |  | 59.056 |  | 59.056 | Sandy
55 | 31/0 | DB2+0 | -0.7 | 209.344 |  |  |  |  | 120.033 |  | 120.033
56 | 33/0 | DC1+0 | -0.25 | 227.212 | 1 |  |  |  | 119.762 |  | 119.762
57 | 33/1 | DA+0 | -0.5 | 241.549 |  | 1 | 1 |  | 182.96 |  | 182.96
58 | 34/0 | DB2+0 |  | 229.094 |  |  |  |  | 55.9616 |  | 55.9616
59 | 34/2 | DA+6 |  | 234.416 |  |  |  | 2 | 172.507 |  | 172.507
60 | 34/3 | DA+0 |  | 222.158 |  | 3 |  |  | 232.822 |  | 232.822
61 | 34/4 | DA+0 |  | 191.038 |  | 3 | 1 |  | 113.6503 |  | 113.6503
62 | 35/0 | DB2+6 |  | 190.847 | 2 |  |  |  | 163.1337 |  | 163.1337
63 | 35/1 | DA+9 |  | 184.479 | 2 |  |  | 2 | 355.4292 |  | 355.4292
64 | 35/2 | DB1+0 |  | 196.532 | 1 | 1 |  |  | 44.5475 |  | 44.5475
65 | 35/3 | DB1+6 | +1.0 | 211.007 | 1 |  |  |  | 50.2817 |  | 50.2817
66 | 35/5 | DA+0 |  | 192.578 |  |  | 4 | 4 | 625.888 |  | 625.888
67 | 36/2 | DA+0 |  | 185.467 | 1 | 1 |  |  | 83.5731 |  | 83.5731
68 | 36/3 | DA+0 |  | 196.493 |  | 2 |  |  | 102.3249 |  | 102.3249
69 | 36/4 | DA+6 |  | 216.948 | 2 | 3 |  | 5 | 138.429 |  | 138.429
70 | 37/0 | DB2+0 |  | 232.205 |  |  |  | 1 | 162.7886 |  | 162.7886
71 | 37/1 | DA+9 | +1.0 | 223.469 | 2 | 2 | 2 | 1 | 94.895 |  | 94.895
72 | 37/2 | DA+3 |  | 217.775 |  |  |  |  | 172.4831 |  | 172.4831
73 | 37/3 | DA+0 | +1.0 | 218.259 |  |  |  |  | 283.6687 |  | 283.6687
74 | 38/0 | DB2+6 |  | 183.041 |  |  |  |  | 63.3033 |  | 63.3033
75 | 38/3 | DA+9 | +1.0 | 195.915 | 2 | 2 | 2 | 2 | 15.318 |  | 15.318
76 | 38/4 | DA+9 | +1.0 | 188.108 | 1 | 1 |  | 1 | 128.046 |  | 128.046
77 | 40/0 | DC1+0 |  | 189.11 | 1 | 1 |  |  | 91.75 |  | 83.997
78 | 40/1 | DA+6 |  | 189.83 | 1 | 2 |  |  | 153.267 |  | 51.543
79 | 40/2 | DA+3 |  | 192.04 |  |  |  |  | 48.633 |  | 34.461 |  | 34.4 | Sandy
80 | 40/3 | DA+3 |  | 200.906 | 1 | 2 |  |  | 233.433 |  | 139.125
81 | 41/0 | DC1+6 |  | 220.24 | 3 | 1 |  | 1 | 249.833 |  | 139.683
82 | 41/1 | DB1+9 |  | 193.1 | 4 | 5 | 6 | 6 | 120.747 |  | 45.165
83 | 41/2 | DA+0 |  | 187.77 |  |  | 1 | 1 | 1170.806 |  | 1139.792 |  | 1875.83 | Sandy
84 | 42/0 | DC1+0 |  | 189.212 | 1 |  |  | 2 | 339.457 |  | 328.874 |  | 329.325 | Sandy
85 | 42/1 | DA+6 |  | 200.55 | 1 |  |  |  | 127.8 |  | 83.2 |  | 78.56 | Sandy
86 | 42/2 | DA+6 |  | 189.49 |  |  | 1 | 3 | 91.933 |  | 56.323 |  | 39.17 | Sandy
87 | 42/3 | DA+0 |  | 184.13 |  |  |  |  | 9.463 |  | 3.72
88 | 42/4 | DA+0 |  | 184.34 |  |  |  |  | 136.417 |  | 99.463
89 | 42/5 | DA+9 |  | 188.05 |  |  |  | 1 | 106.4 |  | 49.975
90 | 42/6 | DA+0 |  | 214.42 | 2 | 1 |  | 2 | 144.417 |  | 85.947 |  | 80.2 | Sandy
91 | 43/0 | DB1+0 |  | 210.52 |  |  |  |  | 68.726 |  | 53.162 |  | 33.44 | Sandy
92 | 43/1 | DA+3 |  | 203.87 |  |  | 3 | 3 | 199.917 |  | 73.957 |  | 73.84 | Sandy
93 | 43/2 | DA+0 |  | 185.92 | 1 |  |  | 1 | 189.737 |  | 89.999 |  | 66.4 | Sandy
94 | 43/3 | DA+0 |  | 187.1 |  | 1 |  |  | 275.117 |  | 183.088
95 | 43/4 | DA+3 |  | 191.67 | 1 | 1 |  |  | 108.9 |  | 38.999 |  | 102.72 | Sandy
96 | 43/5 | DA+3 |  | 184 |  |  |  |  | 35.95 |  | 18.096
97 | 43/6 | DA+3 |  | 185.22 |  |  |  |  | 17.8 |  | 7.552
98 | 43/7 | DA+3 | +0.20 | 184.11 |  |  |  |  | 46.75 |  | 26.32 |  | 26.08 | Sandy
99 | 43/8 | DA+9 |  | 192.68 | 1 |  |  |  | 120.65 |  | 100.624 |  | 104 | Sandy
100 | 43/9 | DA+9 |  | 201.66 |  |  |  |  | 61.583 |  | 42.336 |  | 24.16 | Sandy
101 | 43/10 | DA+3 |  | 219.93 | 3 | 3 |  |  | 70.8 |  | 24.393
102 | 43/11 | DA+3 |  | 216.7 | 2 | 3 |  | 1 | 125.717 |  | 24.813 |  | 213.4 | Sandy
103 | 44/0 | DB1+3 |  | 198.375 |  | 1 | 1 |  | 227.336 |  | 145.45
104 | 44/1 | DA+0 |  |  | 0 | 0 | 1 | 0 | 516.62
105 | 44/2 | DA+0 |  |  | 0 | 0 | 0 | 0 | 145.7
106 | 44/3 | DA+0 |  |  | 2 | 0 | 0 | 1 | 35.453
107 | 44/4 | DA+9 | 3.3 | 3 | 4 | 3 | 3 | 3 | 62.367
108 | 44/5 | DA+9 |  |  | 1 | 3 | 0 | 0 | 476.6
109 | 44/6 | DB1+3 |  |  | 1 | 0 | 0 | 1 | 263.667
110 | 44/7 | DA+9 |  |  | 0 | 0 | 0 | 0 | 107.267
111 | 44/8 | DC1+0 |  |  | 1 | 2 | 0 | 1 | 114.075
112 | 44/9 | DA+9 | 3 |  | 4 | 0 | 2 | 6 | 218.923
113 | 44/10 | DA+9 |  |  | 0 | 1 | 0 | 0 | 68.233
114 | 44/11 | DA+0 |  |  | 0 | 1 | 0 | 0 | 148.233
115 | 45/0 | DC2+0 |  |  | 0 | 1 | 0 | 0 | 104.47
116 | 45/1 | DA+0 |  |  | 0 | 0 | 1 | 2 | 329.483
117 | 46/0 | DD60+18 | 3 |  | 0 | 4 | 4 | 0 | 773.08
118 | 47/0 | DD60+18 |  | 2 | 3 | 2 | 2 | 2 | 333.585
119 | 47/1 | DA+6 |  | 1 | 1 | 1 | 2 | 2 | 334.445 |  | 183.244
120 | 47/2 | DA+9 |  |  | 0 | 0 | 0 | 0 | 35.008 |  | 14.894
121 | 47/3 | DA+9 |  |  | 1 | 2 | 0 | 0 | 351.248 |  | 198.462
122 | 47/4 | DA+3
123 | 47/5 | DA+0 |  |  | 0 | 1 | 0 | 0 | 151.406 |  | 50.19
124 | 47/6 | DA+3 |  |  | 0 | 0 | 0 | 0 | 214.683 |  | 105.461
125 | 47/7 | DA+3 |  |  | 0 | 0 | 0 | 0 | 146.833 |  | 85.356 |  | 83.13 | Sandy
126 | 47/8 | DA+0 |  |  | 1 | 0 | 0 | 0 | 186.171 |  | 58.541 |  | 57.389 | Sandy
127 | 47/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 36.917 |  | 21.243 |  | 21.243 | Sandy
128 | 47/10 | DA+6 |  |  | 0 | 0 | 0 | 0 | 105.1 |  | 44.208 |  | 44.128 | Sandy
129 | 48/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 271.371 |  | 121.376
130 | 48/1 | DA+9 |  |  | 0 | 0 | 0 | 0 | 83.933 |  | 43.92 |  | 42.432 | Sandy
131 | 49/1 | DA+0 |  |  | 0 | 0 | 0 | 0 | 28.5 |  | 20.37 |  | 20.37 | Sandy
132 | 49/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 237.2 |  | 152.093 |  | 151.986 | Sandy
133 | 49/3 | DA+3 |  |  | 0 | 0 | 0 | 0 | 130.95 |  | 59.392 |  | 59.168 | Sandy
134 | 49/4 | DA+3 |  |  | 0 | 0 | 0 | 0 | 52.95 |  | 27.468 |  | 27.342 | Sandy
135 | 49/5 | DA+3 | 0.1 |  | 0 | 0 | 0 | 0 | 68.133 |  | 33.446 |  | 33.173 | Sandy
136 | 49/6 | DA+0 | 0.1 |  | 0 | 0 | 0 | 0 | 29.783 |  | 10.948 |  | 10.948 | Sandy
137 | 49/7 | DA+3 |  |  | 0 | 3 | 2 | 2 | 190.733 |  | 89.935
138 | 50/0 | DB2+0 |  |  | 0 | 0 | 0 | 1 | 29.469 |  | 6.775
139 | 50/1 | DA+6 |  |  | 1 | 0 | 0 | 0 | 258.417 |  | 126.731 |  | 126.619 | Sandy
140 | 50/2 | DA+9 |  | 2 | 2 | 2 | 2 | 2 | 109.183 |  | 50.596
141 | 50/3 | DA+6 |  |  | 0 | 0 | 1 | 0 | 82.817 |  | 40.792
142 | 50/4 | DA+9 |  | 3 | 3 | 3 | 4 | 3 | 90.133 |  | 31.88
143 | 50/5 | DA+9 |  | 3 | 4 | 3 | 4 | 3 | 82.717 |  | 13.972
144 | 50/6 | DA+9 |  | 3 | 3 | 4 | 3 | 3 | 266.417 |  | 133.278
145 | 50/7 | DA+0 |  |  | 0 | 0 | 0 | 1 | 58.15 |  | 20.044 |  | 20.044 | Sandy
146 | 50/8 | DA+9 |  |  | 0 | 0 | 0 | 0 | 379.65 |  | 287.607
147 | 50/9 | DA+0 |  |  | 0 | 0 | 1 | 0 | 551.811 |  | 283.026
148 | 50/10 | DA+0 |  |  | 0 | 0 | 1 | 0 | 304.834 |  | 114.598
149 | 51/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 119.229 |  | 103.624
150 | 51/1 | DA+0 |  |  | 0 | 0 | 1 | 0 | 74.897 |  | 10.113
151 | 51/2 | DA+0 | -1 |  | 0 | 0 | 0 | 0 | 73.95 |  | 12.784
152 | 52/0 | DC2+0 |  |  | 0 | 0 | 3 | 3 | 474.917 |  | 226.626
153 | 52/1 | DA+6 |  |  | 0 | 4 | 0 | 0 | 95.517 |  | 20.215
154 | 52/2 | DA+6 |  |  | 0 | 0 | 0 | 3 | 74.467 |  | 56.535
155 | 52/3 | DA+9 |  | 3 | 4 | 3 | 3 | 3 | 54.25 |  | 21.459
156 | 52/4 | DA+9 |  |  | 2 | 2 | 0 | 0 | 35.517 |  | 14.371
157 | 52/5 | DA+9 |  |  | 0 | 0 | 0 | 1 | 269.167 |  | 177.797
158 | 52/6 | DA+6 |  |  | 0 | 0 | 0 | 0 | 343.483 |  | 239.936
159 | 52/7 | DA+3 |  |  | 0 | 3 | 1 | 0 | 464.317 |  | 306.372
160 | 52/8 | DA+6 |  |  | 0 | 0 | 0 | 0 | 644.717 |  | 582.599
161 | 52/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 192.433 |  | 139.028
162 | 52/10 | DA+9 |  | 1 | 1 | 2 | 1 | 1 | 270.567 |  | 123.839
163 | 53/0 | DB2+9 |  | 4 | 4 | 4 | 4 | 4 | 102.651 |  | 342.89
164 | 53/1 | DA+9 |  | 4 | 4 | 4 | 4 | 4 | 511.767 |  | 302.874
165 | 53/2 | DA+0 |  |  | 0 | 0 | 0 | 2 | 121.063 |  | 38.768
166 | 53/3 | DA+9 |  |  | 0 | 4 | 1 | 0 | 454.927 |  | 204.813
167 | 53/4 | DA+0 |  |  | 0 | 2 | 1 | 0 | 686.16 |  | 280.645
168 | 53/5 | DA+3 |  |  | 0 | 0 | 0 | 0 | 104.9 |  | 76.75 |  | 76.51 | sandy
169 | 53/6 | DA+6 |  |  | 1 | 1 | 3 | 1 | 111.483 |  | 14.573
170 | 53/7 | DA+0 |  |  | 0 | 0 | 0 | 0 | 245.537 |  | 112.464
171 | 53/8 | DA+9 |  | 0 | 0 | 0 | 0 | 0 | 326.55 |  | 334.123
172 | 54/0 | DB1+6 |  |  | 0 | 0 | 0 | 0 | 400.8 |  | 293.967
173 | 54/1 | DA+9 |  |  | 1 | 1 | 0 | 0 | 74.4 |  | 17.753
174 | 54/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 105.35 |  | 63.16
175 | 54/3 | DA+6 |  |  | 0 | 2 | 0 | 0 | 106.517 |  | 71.292
176 | 54/4 | DA+9 |  | 0 | 1 | 2 | 0 | 0 | 264 |  | 131.156
177 | 54/5 | DA+9 |  | 1 | 1 | 3 | 3 | 1 | 210.2 |  | 91.403
178 | 55/0 | DB1+6 |  |  | 0 | 1 | 1 | 0 | 375.874 |  | 244.465
179 | 55/4 | DA+0 |  |  | 0 | 0 | 0 | 1 | 248.177 |  | 98.757
180 | 55/5 | DA+0 |  |  | 0 | 0 | 1 | 3 | 674.16 |  | 250.709
181 | 55/6 | DA+0 |  |  | 0 | 0 | 1 | 2 | 100.954 |  | 24.027
182 | 55/7 | DA+0 |  |  | 0 | 0 | 1 | 0 | 551.126 |  | 317.518
183 | 55/8 | DA+9 |  |  | 0 | 0 | 1 | 0 | 480.283 |  | 241.51
184 | 56/0 | DD60+9 |  | 4 | 4 | 6 | 4 | 4 | 454.562 |  | 387.425
185 | 57/0 | DD60+9 |  | 0 | 0 | 1 | 1 | 0 | 715.032 |  | 562.651
186 | 57/1 | DA+3 |  |  | 0 | 0 | 0 | 0 | 38.65 |  | 24.155
187 | 57/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 64.033 |  | 20.988 |  | 20.988 | All Kind of Soil
188 | 57/3 | DA+0 |  |  | 0 | 0 | 0 | 0 | 91.063 |  | 39.024 |  | 39.024 | All Kind of Soil
189 | 57/4 | DA+0 |  |  | 0 | 0 | 0 | 0 | 165.446 |  | 77.472 |  | 77.408 | sandy
190 | 57/5 | DA+3 |  |  | 0 | 0 | 0 | 1 | 114.817 |  | 54.629 |  | 53.905 | sandy
191 | 57/6 | DA+3 |  |  | 0 | 1 | 0 | 0 | 118.95 |  | 69.342 |  | 68.908 | All Kind of Soil
192 | 58/0 | DC1+3 |  |  | 0 | 0 | 0 | 0 | 16.509
193 | 59/0 | DC2+0 |  |  | 0 | 0 | 0 | 0 | 97.629 |  | 97.629
194 | 59/1 | DA+3 |  |  | 0 | 0 | 0 | 1 | 30.167
195 | 59/2 | DA+3 |  |  | 0 | 0 | 0 | 0 | 74.35 |  | 57.328
196 | 59/3 | DA+3 |  |  | 0 | 0 | 0 | 1 | 29.783
197 | 59/7 | DA+3 |  |  | 0 | 0 | 0 | 0 | 88.917 |  | 67.301 |  | 67.237 | All Kind of Soil
198 | 59/8 | DB1+3 |  |  | 0 | 0 | 0 | 0 | 30.926
199 | 59/9 | DA+3 |  |  | 0 | 0 | 0 | 0 | 51.683
200 | 59/11 | DA+6 |  |  | 0 | 0 | 2 | 0 | 609.4 |  | 443.002 |  | 442.55 | FR
201 | 59/12 | DA+6 |  |  | 0 | 0 | 0 | 0 | 69.983
202 | 60/2 | DA+3 |  |  | 2 | 2 | 0 | 0 | 150.115 |  | 67.99 |  | 67.248 | All Kind of Soil
203 | 61/1 | DA+6 |  |  | 0 | 0 | 0 | 0 | 130.228 |  | 98.667 |  | 98.627 | All Kind of Soil
204 | 61/7 | DA+9 |  |  | 0 | 0 | 0 | 1 | 237.78 |  | 155.449 |  | 154.809 | All Kind of Soil
205 | 61/8 | DA+6 |  |  | 1 | 2 | 1 | 0 | 139.242 |  | 18.852 |  | 18.852 | All Kind of Soil
206 | 62/0 | DB2+0 |  |  | 0 | 0 | 0 | 0 | 50.997 |  | 36.79 |  | 36.29 | All Kind of Soil
207 | 62/1 | DA+3 |  |  | 0 | 0 | 1 | 2 | 200.388 |  | 135.911 |  | 135.895 | sandy
208 | 62/2 | DA+3 |  |  | 0 | 1 | 0 | 0 | 22.433
209 | 62/4 | DA+3 |  |  | 0 | 0 | 0 | 0 | 27.142
210 | 62/5 | DA+0 |  |  | 0 | 0 | 0 | 0 | 109.341 |  | 45.234 |  | 45.234 | All Kind of Soil
211 | 62/6 | DA+3 |  |  | 0 | 0 | 0 | 0 | 23.573
212 | 63/0 | DC1+0 |  |  | 0 | 0 | 0 | 0 | 199.633 |  | 199.633 |  | 199.333 | All Kind of Soil
213 | 63/3 | DA+3 |  |  | 0 | 0 | 0 | 0 | 173.683 |  | 140.624 |  | 140.608 | All Kind of Soil
214 | 63/5 | DA+3 |  |  | 0 | 0 | 0 | 0 | 31.908

## Incharge
Sr. No. | From - To | Section Incharge | Email ID | Contact Number
1 | Gty-AP12 | Sumit Singh | kumars7@kecrpg.com | 7082518194
2 | AP12-AP27 | Vivek Shukla | shuklavk@kecrpg.com | 9451783340
3 | AP27-AP44 | Kuntal Debnath | debnathk@kecrpg.com | 8617007718
4 | AP44-AP57 | Ram Tirath Singh | singhrt@kecrpg.com | 9450069921
5 | AP57-AP74 | Shyamal Kumar Sil | silsk@kecrpg.com | 9598777205