## Erection Summary
Scope: 2026-01-01 to 2026-01-31 ¦ Projects: 16 ¦ Erections: 127 ¦ Gangs: 83
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | Avg Tower Weight Overall
3.71 | 3.83 | 4.38 | 3.66 | 0 | 3.89 | 5626.63 | 127 | 44.3
Scope: 2026-01-01 to 2026-01-31 ¦ Projects: 16 ¦ Erections: 127 ¦ Gangs: 83
PCH | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | 3.51 | 3.71 | 4.52 | 0 | 0 | 3.43 | 2181.8 | 54 | 40.4
Mr. Arun Felbin | 4.03 | 4.11 | 4.51 | 0 | 0 | 4.34 | 3367.19 | 69 | 48.8
Mr. Dheeraj Vashishth | 1.84 | 1.86 | 3.05 | 3.66 | 0 | 2.17 | 77.64 | 4 | 19.41
[6 empty] | Total | 5626.63 | 127
Scope: 2026-01-01 to 2026-01-31 ¦ Projects: 16 ¦ Erections: 127 ¦ Gangs: 83
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | TA413 | 5.22 | 4.97 | 0 | 0 | 0 | 5.12 | 78.59 | 2 | 39.3
Mr. Sanjay Kumar Gupta | TA419 | 3.07 | 3.75 | 4.03 | 0 | 0 | 3.29 | 668.01 | 12 | 55.67
Mr. Sanjay Kumar Gupta | TA512 | 3.38 | 3.44 | 4.09 | 0 | 0 | 3.57 | 998.25 | 24 | 41.59
Mr. Sanjay Kumar Gupta | TB408 | 4.22 | 4.29 | 7.77 | 0 | 0 | 4.51 | 298.62 | 7 | 42.66
Mr. Sanjay Kumar Gupta | TB507 | 1.65 | 2.08 | 2.21 | 0 | 0 | 1.99 | 138.33 | 9 | 15.37
Mr. Arun Felbin | TA325 | 3.69 | 3.67 | 0 | 0 | 0 | 3.68 | 280.48 | 2 | 140.24
Mr. Arun Felbin | TA414 | 2.17 | 2.17 | 4 | 0 | 0 | 2.79 | 331.65 | 8 | 41.46
Mr. Arun Felbin | TA416 | 3.03 | 3.21 | 3.17 | 0 | 0 | 3.11 | 647.95 | 6 | 107.99
Mr. Arun Felbin | TA418 | 3.82 | 4.32 | 5.46 | 0 | 0 | 4.36 | 283 | 7 | 40.43
Mr. Arun Felbin | TA421 | 7.66 | 6.8 | 0 | 0 | 0 | 7.34 | 268.4 | 6 | 44.73
Mr. Arun Felbin | TA504 | 0 | 4.5 | 4.5 | 0 | 0 | 4.5 | 36 | 1 | 36
Mr. Arun Felbin | TA505 | 5.65 | 5.23 | 5.27 | 0 | 0 | 5.41 | 1233.4 | 26 | 47.44
Mr. Arun Felbin | TA506 | 4.6 | 4.67 | 4.65 | 0 | 0 | 4.65 | 192 | 8 | 24
Mr. Arun Felbin | TA601 | 2.8 | 2.44 | 0 | 0 | 0 | 2.76 | 73.15 | 2 | 36.57
Mr. Arun Felbin | TB501 | 2.82 | 0 | 0 | 0 | 0 | 2.82 | 21.16 | 3 | 7.06
Mr. Dheeraj Vashishth | TB605 | 1.84 | 1.86 | 3.05 | 3.66 | 0 | 2.17 | 77.64 | 4 | 19.41
[7 empty] | Total | 5626.63 | 127

## Review_Format
Scope: 2026-01-01 to 2026-01-31 ¦ Projects: 16 ¦ Erections: 127 ¦ Gangs: 83
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
PCH: Mr. Sanjay Kumar Gupta
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
Mr. Sanjay Kumar Gupta | TA413 | 5.22 | 4.97 | 0 | 0 | 0 | 5.12 | 78.59 | 2
Mr. Sanjay Kumar Gupta | TA419 | 3.07 | 3.75 | 4.03 | 0 | 0 | 3.29 | 668.01 | 12
Mr. Sanjay Kumar Gupta | TA512 | 3.38 | 3.44 | 4.09 | 0 | 0 | 3.57 | 998.25 | 24
Mr. Sanjay Kumar Gupta | TB408 | 4.22 | 4.29 | 7.77 | 0 | 0 | 4.51 | 298.62 | 7
Mr. Sanjay Kumar Gupta | TB507 | 1.65 | 2.08 | 2.21 | 0 | 0 | 1.99 | 138.33 | 9
[7 empty] | Total | 2181.8 | 54
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
PCH: Mr. Arun Felbin
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
Mr. Arun Felbin | TA325 | 3.69 | 3.67 | 0 | 0 | 0 | 3.68 | 280.48 | 2
Mr. Arun Felbin | TA414 | 2.17 | 2.17 | 4 | 0 | 0 | 2.79 | 331.65 | 8
Mr. Arun Felbin | TA416 | 3.03 | 3.21 | 3.17 | 0 | 0 | 3.11 | 647.95 | 6
Mr. Arun Felbin | TA418 | 3.82 | 4.32 | 5.46 | 0 | 0 | 4.36 | 283 | 7
Mr. Arun Felbin | TA421 | 7.66 | 6.8 | 0 | 0 | 0 | 7.34 | 268.4 | 6
Mr. Arun Felbin | TA504 | 0 | 4.5 | 4.5 | 0 | 0 | 4.5 | 36 | 1
Mr. Arun Felbin | TA505 | 5.65 | 5.23 | 5.27 | 0 | 0 | 5.41 | 1233.4 | 26
Mr. Arun Felbin | TA506 | 4.6 | 4.67 | 4.65 | 0 | 0 | 4.65 | 192 | 8
Mr. Arun Felbin | TA601 | 2.8 | 2.44 | 0 | 0 | 0 | 2.76 | 73.15 | 2
Mr. Arun Felbin | TB501 | 2.82 | 0 | 0 | 0 | 0 | 2.82 | 21.16 | 3
[7 empty] | Total | 3367.19 | 69
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
PCH: Mr. Dheeraj Vashishth
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
Mr. Dheeraj Vashishth | TB605 | 1.84 | 1.86 | 3.05 | 3.66 | 0 | 2.17 | 77.64 | 4
[7 empty] | Total | 77.64 | 4
Erection productivity | Jan'26
PCH: Mr. Sanjay Kumar Gupta
Erection productivity | Jan'26
Weight/day (Avg) | 3.43
No of Gangs engaged (Avg) | 36
Erection productivity | Jan'26
PCH: Mr. Arun Felbin
Erection productivity | Jan'26
Weight/day (Avg) | 4.34
No of Gangs engaged (Avg) | 46
Erection productivity | Jan'26
PCH: Mr. Dheeraj Vashishth
Erection productivity | Jan'26
Weight/day (Avg) | 2.17
No of Gangs engaged (Avg) | 2

## Gang Level Productivity
Scope: 2026-01-01 to 2026-01-31 ¦ Projects: 16 ¦ Erections: 127 ¦ Gangs: 83
PCH | Project | Gang Name | Avg Productivity (MTD) | Avg Productivity (Overall) | Total MT (MTD) | Total No. of Erections (MTD) | Avg Tower Weight Overall | Idle Counted (days) | Number of Idle Intervals
Mr. Sanjay Kumar Gupta | TA413 | Jwala Singh 1 | 5.12 | 4.11 | 78.59 | 2 | 39.3 | 1 | 1
Mr. Sanjay Kumar Gupta | TA419 | Amit Yadav | 2.35 | 1.72 | 42.37 | 1 | 42.37 | 0 | 0
Mr. Sanjay Kumar Gupta | TA419 | Dhruv Enterprises | 0.3 | 0.7 | 43.78 | 1 | 43.78 | 0 | 0
Mr. Sanjay Kumar Gupta | TA419 | Ganesh 1 | 4.24 | 4.24 | 42.37 | 1 | 42.37 | 0 | 0
Mr. Sanjay Kumar Gupta | TA419 | Ganesh 2 | 1.33 | 1.44 | 89.82 | 2 | 44.91 | 0 | 0
Mr. Sanjay Kumar Gupta | TA419 | Infinidea 2 | 0.69 | 0.19 | 37.93 | 1 | 37.93 | 0 | 0
Mr. Sanjay Kumar Gupta | TA419 | Jwala Singh | 5.75 | 3.13 | 86.26 | 1 | 86.26 | 0 | 0
Mr. Sanjay Kumar Gupta | TA419 | Madhu Sah | 4.03 | 0.84 | 124.95 | 1 | 124.95 | 0 | 0
Mr. Sanjay Kumar Gupta | TA419 | Mukhilal | 2.9 | 2.9 | 34.79 | 1 | 34.79 | 0 | 0
Mr. Sanjay Kumar Gupta | TA419 | Raju Kumar | 3.54 | 1.36 | 46.05 | 1 | 46.05 | 0 | 0
Mr. Sanjay Kumar Gupta | TA419 | Rohit | 4.22 | 0.75 | 75.91 | 1 | 75.91 | 0 | 0
Mr. Sanjay Kumar Gupta | TA419 | Satyam Trading | 3.65 | 0.48 | 43.78 | 1 | 43.78 | 0 | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Company Gang | 1.06 | 1.94 | 135.42 | 3 | 45.14 | 0 | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Govind Mahto 2 | 2.92 | 3.28 | 93.38 | 2 | 46.69 | 0 | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Jwala Singh | 4.63 | 5.18 | 118.17 | 2 | 59.09 | 0 | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Jwala Singh 2 | 4.74 | 5.03 | 37.93 | 1 | 37.93 | 0 | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Karni Construction 1 | 2.51 | 2.44 | 80.49 | 2 | 40.24 | 0 | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Karni Construction 2 | 2.96 | 3.02 | 78.59 | 2 | 39.3 | 0 | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Kartik Mahto | 6.58 | 7.04 | 182.57 | 5 | 36.51 | 0 | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Mohika Costruction | 2.11 | 2.11 | 18.97 | 1 | 18.97 | 0 | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Punam Kumari 3 | 3.62 | 3.88 | 36.16 | 1 | 36.16 | 0 | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Punam Kumari 4 | 4.77 | 4.89 | 66.78 | 1 | 66.78 | 0 | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Raju Kumar | 4.14 | 4.14 | 78.59 | 2 | 39.3 | 0 | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Sani Construction | 5.09 | 5.09 | 35.6 | 1 | 35.6 | 0 | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Shobha Debi | 7.12 | 7.12 | 35.6 | 1 | 35.6 | 0 | 0
Mr. Sanjay Kumar Gupta | TB408 | Chinta Devi | 3.21 | 6.34 | 84.26 | 2 | 42.13 | 2 | 1
Mr. Sanjay Kumar Gupta | TB408 | Ganesh Sinha | 3.53 | 4.53 | 38.85 | 1 | 38.85 | 0 | 0
Mr. Sanjay Kumar Gupta | TB408 | Jirwa Devi | 4.13 | 4.18 | 45.41 | 1 | 45.41 | 0 | 0
Mr. Sanjay Kumar Gupta | TB408 | Shobha Devi | 6.49 | 7.3 | 45.41 | 1 | 45.41 | 0 | 0
Mr. Sanjay Kumar Gupta | TB408 | Sunny Construction | 6.74 | 6.59 | 47.18 | 1 | 47.18 | 0 | 0
Mr. Sanjay Kumar Gupta | TB408 | Vedanta Construction | 4.69 | 1.97 | 37.5 | 1 | 37.5 | 0 | 0
Mr. Sanjay Kumar Gupta | TB507 | Gokul Sarkar | 1.62 | 2.62 | 14.57 | 1 | 14.57 | 0 | 0
Mr. Sanjay Kumar Gupta | TB507 | Namechand Mahto | 0.49 | 0.59 | 22.29 | 2 | 11.14 | 0 | 0
Mr. Sanjay Kumar Gupta | TB507 | Prayag Saw | 3.24 | 3.46 | 48.66 | 3 | 16.22 | 1 | 1
Mr. Sanjay Kumar Gupta | TB507 | Rajesh Mahto | 2.43 | 0.63 | 14.57 | 1 | 14.57 | 0 | 0
Mr. Sanjay Kumar Gupta | TB507 | Vinay Construction | 3.82 | 3.22 | 38.23 | 2 | 19.11 | 1 | 1
Mr. Arun Felbin | TA325 | Dildar Electricals 1 Pgcil Prayag Mahto Nasirudin 2 | 3.73 | 3.73 | 156.83 | 1 | 156.83 | 0 | 0
Mr. Arun Felbin | TA325 | Modina India 3 Pgcil Dildar Electricals 3 Pgcil Nasirudin Md Akhtar | 3.64 | 3.64 | 123.65 | 1 | 123.65 | 0 | 0
Mr. Arun Felbin | TA414 | Anannya Traders | 7.55 | 7.55 | 37.73 | 1 | 37.73 | 0 | 0
Mr. Arun Felbin | TA414 | Anjum Construction | 1.45 | 2.38 | 34.7 | 1 | 34.7 | 0 | 0
Mr. Arun Felbin | TA414 | Modina India 1 | 2.22 | 2.22 | 37.73 | 1 | 37.73 | 0 | 0
Mr. Arun Felbin | TA414 | Modina India 2 | 2.14 | 2.14 | 45.04 | 1 | 45.04 | 0 | 0
Mr. Arun Felbin | TA414 | Modina India 3 | 1.9 | 1.9 | 38.04 | 1 | 38.04 | 0 | 0
Mr. Arun Felbin | TA414 | Sakila Khatun | 5.39 | 6.69 | 37.73 | 1 | 37.73 | 0 | 0
Mr. Arun Felbin | TA414 | Sk Samiul Sima Khatun | 3.15 | 3.25 | 62.95 | 1 | 62.95 | 0 | 0
Mr. Arun Felbin | TA414 | Subhash | 5.39 | 5.55 | 37.73 | 1 | 37.73 | 0 | 0
Mr. Arun Felbin | TA416 | Amit Choudhry | 2.99 | 2.99 | 143.46 | 1 | 143.46 | 0 | 0
Mr. Arun Felbin | TA416 | Mahon Mahto | 3.69 | 4.28 | 188.38 | 1 | 188.38 | 0 | 0
Mr. Arun Felbin | TA416 | Pankaj Kumar | 4.42 | 4.56 | 97.23 | 1 | 97.23 | 0 | 0
Mr. Arun Felbin | TA416 | Pinky Dewi | 2.39 | 6.08 | 64.48 | 1 | 64.48 | 0 | 0
Mr. Arun Felbin | TA416 | Punam Kumari 1 | 1.41 | 2.02 | 43.78 | 1 | 43.78 | 0 | 0
Mr. Arun Felbin | TA416 | Punam Kumari 3 | 3.25 | 3.88 | 110.63 | 1 | 110.63 | 0 | 0
Mr. Arun Felbin | TA418 | Kec 02 Barkat Ali | 2.77 | 2.76 | 54 | 2 | 27 | 0 | 0
Mr. Arun Felbin | TA418 | M S Mdpl | 5.34 | 3.16 | 100 | 2 | 50 | 0 | 0
Mr. Arun Felbin | TA418 | M S Tofit | 4.65 | 4.53 | 129 | 3 | 43 | 0 | 0
Mr. Arun Felbin | TA421 | D K Verma | 4.72 | 5.94 | 37.72 | 1 | 37.72 | 0 | 0
Mr. Arun Felbin | TA421 | Gauri Shankar Mahto | 6.73 | 6.67 | 93.51 | 2 | 46.76 | 0 | 0
Mr. Arun Felbin | TA421 | Khatun | 8.35 | 7.24 | 33.38 | 1 | 33.38 | 0 | 0
Mr. Arun Felbin | TA421 | Subash | 8.36 | 7.46 | 103.79 | 2 | 51.9 | 2 | 1
Mr. Arun Felbin | TA504 | Sainik Traders | 4.5 | 0.52 | 36 | 1 | 36 | 0 | 0
Mr. Arun Felbin | TA505 | Crane Erc Team Mp | 4.21 | 3.04 | 37.93 | 1 | 37.93 | 0 | 0
Mr. Arun Felbin | TA505 | Deglal Mahato | 4.94 | 6.36 | 168.12 | 3 | 56.04 | 0 | 0
Mr. Arun Felbin | TA505 | Deglal Mahato Mp | 4.95 | 4.79 | 114.75 | 3 | 38.25 | 0 | 0
Mr. Arun Felbin | TA505 | Gokul Sarkar Mp | 7.27 | 4.74 | 72.72 | 2 | 36.36 | 0 | 0
Mr. Arun Felbin | TA505 | Gokul Sarkar Mp 2 | 4.81 | 4.41 | 108.88 | 3 | 36.29 | 0 | 0
Mr. Arun Felbin | TA505 | Jagannaath Saw Mp | 4.1 | 4.76 | 78.59 | 2 | 39.3 | 0 | 0
Mr. Arun Felbin | TA505 | Jhemon Mahato 1 | 5.17 | 5.66 | 109.4 | 2 | 54.7 | 0 | 0
Mr. Arun Felbin | TA505 | Jwala Singh | 8.1 | 3.13 | 145.75 | 2 | 72.88 | 0 | 0
Mr. Arun Felbin | TA505 | Jwala Singh 2 | 4.71 | 5.81 | 108.88 | 3 | 36.29 | 0 | 0
Mr. Arun Felbin | TA505 | Jyoti Const | 5.45 | 3.91 | 113.24 | 2 | 56.62 | 0 | 0
Mr. Arun Felbin | TA505 | Prayag Shah Mp | 2.92 | 3.34 | 37.93 | 1 | 37.93 | 0 | 0
Mr. Arun Felbin | TA505 | Shila Devi | 8.07 | 6 | 137.19 | 2 | 68.59 | 0 | 0
Mr. Arun Felbin | TA506 | Ab Const | 4.5 | 0.57 | 27 | 1 | 27 | 0 | 0
Mr. Arun Felbin | TA506 | Ab Const 2 | 3.6 | 3.6 | 18 | 1 | 18 | 0 | 0
Mr. Arun Felbin | TA506 | Ab Construction | 5 | 5 | 25 | 1 | 25 | 0 | 0
Mr. Arun Felbin | TA506 | Horil Mahto | 5.5 | 1.21 | 22 | 1 | 22 | 0 | 0
Mr. Arun Felbin | TA506 | Jai Prakash Mahto | 4.5 | 0.64 | 27 | 1 | 27 | 0 | 0
Mr. Arun Felbin | TA506 | Khemlal Mahto | 4.54 | 0.43 | 57 | 2 | 28.5 | 13 | 1
Mr. Arun Felbin | TA506 | Mukkhilal 2 | 4 | 4 | 16 | 1 | 16 | 0 | 0
Mr. Arun Felbin | TA601 | Nasiruddin | 4.06 | 5.22 | 36.57 | 1 | 36.57 | 0 | 0
Mr. Arun Felbin | TA601 | Uma Devi | 2.44 | 2.44 | 36.57 | 1 | 36.57 | 0 | 0
Mr. Arun Felbin | TB501 | Suman | 2.82 | 1.32 | 21.16 | 3 | 7.06 | 0 | 0
Mr. Dheeraj Vashishth | TB605 | Anbi Construction | 1.73 | 1.67 | 36.64 | 2 | 18.32 | 1 | 1
Mr. Dheeraj Vashishth | TB605 | Raj Labour Suppliers | 2.68 | 2.62 | 41 | 2 | 20.5 | 9 | 1

## Idle Intervals
Scope: 2026-01-01 to 2026-01-31 ¦ Projects: 16 ¦ Erections: 127 ¦ Gangs: 83
Gang | Interval Start | Interval End | Raw Gap (days) | Idle Counted (days)
Anbi Construction | 06-01-2026 | 06-01-2026 | 1 | 1
Chinta Devi | 12-01-2026 | 13-01-2026 | 2 | 2
Jwala Singh 1 | 04-01-2026 | 04-01-2026 | 1 | 1
Khemlal Mahto | 02-01-2026 | 14-01-2026 | 13 | 13
Prayag Saw | 12-01-2026 | 12-01-2026 | 1 | 1
Raj Labour Suppliers | 09-01-2026 | 17-01-2026 | 9 | 9
Subash | 05-01-2026 | 06-01-2026 | 2 | 2
Vinay Construction | 11-01-2026 | 11-01-2026 | 1 | 1

## Project Gang Rankings
Scope: 2026-01-01 to 2026-01-31 ¦ Projects: 16 ¦ Erections: 127 ¦ Gangs: 83
Top 3 Gangs
PCH | Project | Gang Name | Avg Productivity (MTD) | Avg Productivity (Overall) | Total MT (MTD) | Total No. of Erections (MTD) | Avg Tower Weight Overall | Idle Counted (days) | Number of Idle Intervals
Mr. Sanjay Kumar Gupta | TA512 | M S Kartik Mahto | 6.58 | 7.04 | 182.57 | 5 | 36.51 | 0 | 0
Bottom 3 Gangs
PCH | Project | Gang Name | Avg Productivity (MTD) | Avg Productivity (Overall) | Total MT (MTD) | Total No. of Erections (MTD) | Avg Tower Weight Overall | Idle Counted (days) | Number of Idle Intervals
Mr. Sanjay Kumar Gupta | TA512 | M S Kartik Mahto | 6.58 | 7.04 | 182.57 | 5 | 36.51 | 0 | 0

## Idle Days Buckets
Overall Idle Days Buckets | [13 empty] | MTD Idle Days Buckets
Erections >=1 | [13 empty] | Erections >=1
Scope: 2023-09-13 to 2026-01-22 ¦ Projects: 18 ¦ Erections: 3677 ¦ Gangs: 456 | [13 empty] | Scope: 2026-01-01 to 2026-01-31 ¦ Projects: 16 ¦ Erections: 127 ¦ Gangs: 83
Metric | 0-1 | 1-2 | 2-3 | 3-4 | 4-5 | 5-6 | 6-7 | 7-8 | 8-9 | 9-10 | 10-11 | 11-12 | >12 | Metric | 0-1 | 1-2 | 2-3 | 3-4 | 4-5 | 5-6 | 6-7 | 7-8 | 8-9 | 9-10 | 10-11 | 11-12 | >12
Days per idle window (severity) | 0.99 | 0.89 | 1.58 | 1.62 | 1.46 | 1.43 | 1.16 | 1.28 | 1.47 | 0 | 1 | 0 | 0 | Days per idle window (severity) | 0 | 0.14 | 0.56 | 0.31 | 0.54 | 0.11 | 0 | 0 | 0.67 | 0 | 0 | 0 | 0
Avg Idle Days (Magnitude) | 2.07 | 1.91 | 6.67 | 4.49 | 4.9 | 5.04 | 6.28 | 6.26 | 5.25 | 0 | 1 | 0 | 0 | Avg Idle Days (Magnitude) | 0 | 0.14 | 0.56 | 0.31 | 0.54 | 0.11 | 0 | 0 | 0.67 | 0 | 0 | 0 | 0
Idle windows per gang (Frequency) | 0.37 | 0.7 | 1.8 | 1.56 | 1.67 | 2.04 | 2.66 | 2.32 | 2.5 | 0 | 1 | 0 | 0 | Idle windows per gang (Frequency) | 0 | 0.14 | 0.06 | 0.23 | 0.04 | 0.11 | 0 | 0 | 0.33 | 0 | 0 | 0 | 0
Gang Count | 60 | 53 | 75 | 89 | 70 | 50 | 32 | 19 | 4 | 2 | 1 | 0 | 1 | Gang Count | 3 | 7 | 16 | 13 | 24 | 9 | 4 | 4 | 3 | 0 | 0 | 0 | 0
Weight Erected (MT) - Daily Prod | 9965.31 | 11248.3 | 15376.96 | 28644.25 | 27106.52 | 23363.11 | 28103.94 | 13093.72 | 1449.96 | 162.48 | 83.03 | 0 | 57.6 | Weight Erected (MT) - Daily Prod | 15.75 | 176.14 | 577.39 | 514.52 | 1191.21 | 501.3 | 337.89 | 366.56 | 262.57 | 0 | 0 | 0 | 0
Weight Erected (MT) - Tower Weight | 9965.31 | 11228.53 | 15376.97 | 28644.25 | 27106.51 | 23363.11 | 28103.94 | 13093.72 | 1449.96 | 162.48 | 83.03 | 0 | 57.6 | Weight Erected (MT) - Tower Weight | 104 | 392.97 | 844.53 | 996.43 | 1708.28 | 559.29 | 368.67 | 378.06 | 274.36 | 0 | 0 | 0 | 0
Erections >=2 | [13 empty] | Erections >=2
Scope: 2023-09-13 to 2026-01-22 ¦ Projects: 18 ¦ Erections: 3677 ¦ Gangs: 456 | [13 empty] | Scope: 2026-01-01 to 2026-01-31 ¦ Projects: 16 ¦ Erections: 127 ¦ Gangs: 83
Metric | 0-1 | 1-2 | 2-3 | 3-4 | 4-5 | 5-6 | 6-7 | 7-8 | 8-9 | 9-10 | 10-11 | 11-12 | >12 | Metric | 0-1 | 1-2 | 2-3 | 3-4 | 4-5 | 5-6 | 6-7 | 7-8 | 8-9 | 9-10 | 10-11 | 11-12 | >12
Days per idle window (severity) | 1.65 | 1.31 | 2.88 | 2.05 | 1.83 | 1.7 | 1.49 | 2.21 | 1.96 | 0 | 1 | 0 | 0 | Days per idle window (severity) | 0 | 0.33 | 1.5 | 1.33 | 1.44 | 0.25 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Avg Idle Days (Magnitude) | 3.44 | 2.81 | 12.2 | 5.71 | 6.12 | 6 | 8.04 | 10.82 | 7 | 0 | 1 | 0 | 0 | Avg Idle Days (Magnitude) | 0 | 0.33 | 1.5 | 1.33 | 1.44 | 0.25 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Idle windows per gang (Frequency) | 0.61 | 1.03 | 3.29 | 1.99 | 2.09 | 2.43 | 3.4 | 4 | 3.33 | 0 | 1 | 0 | 0 | Idle windows per gang (Frequency) | 0 | 0.33 | 0.17 | 1 | 0.11 | 0.25 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0
Gang Count | 36 | 36 | 41 | 70 | 56 | 42 | 25 | 11 | 3 | 1 | 1 | 0 | 0 | Gang Count | 1 | 3 | 6 | 3 | 9 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0
Weight Erected (MT) - Daily Prod | 8972.69 | 10501.24 | 13646.37 | 27349.23 | 26417.1 | 22985.84 | 27696.48 | 12642.36 | 1383.58 | 76.35 | 83.03 | 0 | 0 | Weight Erected (MT) - Daily Prod | 11.69 | 87.09 | 283.72 | 138.23 | 706.74 | 343.24 | 245.3 | 293.23 | 229.19 | 0 | 0 | 0 | 0
Weight Erected (MT) - Tower Weight | 8972.69 | 10481.47 | 13646.38 | 27349.23 | 26417.09 | 22985.84 | 27696.48 | 12642.36 | 1383.58 | 76.35 | 83.03 | 0 | 0 | Weight Erected (MT) - Tower Weight | 22.29 | 261.88 | 368.62 | 171.15 | 961.98 | 401.23 | 276.08 | 304.73 | 240.98 | 0 | 0 | 0 | 0
Erections >=3 | [13 empty] | Erections >=3
Scope: 2023-09-13 to 2026-01-22 ¦ Projects: 18 ¦ Erections: 3677 ¦ Gangs: 456 | [13 empty] | Scope: 2026-01-01 to 2026-01-31 ¦ Projects: 16 ¦ Erections: 127 ¦ Gangs: 83
Metric | 0-1 | 1-2 | 2-3 | 3-4 | 4-5 | 5-6 | 6-7 | 7-8 | 8-9 | 9-10 | 10-11 | 11-12 | >12 | Metric | 0-1 | 1-2 | 2-3 | 3-4 | 4-5 | 5-6 | 6-7 | 7-8 | 8-9 | 9-10 | 10-11 | 11-12 | >12
Days per idle window (severity) | 2.09 | 1.51 | 3.34 | 1.84 | 1.9 | 1.81 | 1.69 | 2.21 | 1.96 | 0 | 0 | 0 | 0 | Days per idle window (severity) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Avg Idle Days (Magnitude) | 4.48 | 3.75 | 16.07 | 6.08 | 6.81 | 6.44 | 9.14 | 10.82 | 7 | 0 | 0 | 0 | 0 | Avg Idle Days (Magnitude) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Idle windows per gang (Frequency) | 0.78 | 1.33 | 4.4 | 2.24 | 2.32 | 2.59 | 3.86 | 4 | 3.33 | 0 | 0 | 0 | 0 | Idle windows per gang (Frequency) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gang Count | 27 | 24 | 30 | 59 | 47 | 39 | 22 | 11 | 3 | 0 | 0 | 0 | 0 | Gang Count | 0 | 1 | 1 | 1 | 5 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Weight Erected (MT) - Daily Prod | 8299.37 | 9738.63 | 12432.14 | 26290.08 | 25489.64 | 22479.75 | 27335.44 | 12642.36 | 1383.58 | 0 | 0 | 0 | 0 | Weight Erected (MT) - Daily Prod | 0 | 35.91 | 19.72 | 48.66 | 471.52 | 0 | 164.49 | 220.51 | 0 | 0 | 0 | 0 | 0
Weight Erected (MT) - Tower Weight | 8299.37 | 9718.86 | 12432.14 | 26290.08 | 25489.63 | 22479.75 | 27335.44 | 12642.36 | 1383.58 | 0 | 0 | 0 | 0 | Weight Erected (MT) - Tower Weight | 0 | 135.41 | 21.16 | 48.66 | 629.63 | 0 | 182.57 | 232.01 | 0 | 0 | 0 | 0 | 0
Idle Days Audit (Erections >=3) | [13 empty] | Idle Days Audit (Erections >=3)
Scope: 2023-09-13 to 2026-01-22 ¦ Projects: 18 ¦ Erections: 3677 ¦ Gangs: 456 | [13 empty] | Scope: 2026-01-01 to 2026-01-31 ¦ Projects: 16 ¦ Erections: 127 ¦ Gangs: 83
Gang Name | Productivity (MT/day) | Bucket | Idle Days | Idle Intervals | Idle Days per Interval | Towers Erected | Daily Prod Sum (MT) | Tower Weight Sum (MT) | Project Codes |  |  |  |  | Gang Name | Productivity (MT/day) | Bucket | Idle Days | Idle Intervals | Idle Days per Interval | Towers Erected | Daily Prod Sum (MT) | Tower Weight Sum (MT) | Project Codes
Ab Const | 0.57 | 0-1 | 7 | 2 | 3.5 | 8 | 195 | 195 | TA506 |  |  |  |  | M S Company Gang | 1.06 | 1-2 | 0 | 0 | 0 | 3 | 35.91 | 135.41 | TA512
Bhairo Mahato | 0.6 | 0-1 | 0 | 0 | 0 | 3 | 319.85 | 319.85 | TA419 |  |  |  |  | Suman | 2.82 | 2-3 | 0 | 0 | 0 | 3 | 19.72 | 21.16 | TB501
Binod Mahto | 0.99 | 0-1 | 4 | 1 | 4 | 5 | 146 | 146 | TA506 |  |  |  |  | Prayag Saw | 3.24 | 3-4 | 1 | 1 | 1 | 3 | 48.66 | 48.66 | TB507
Ghyansham Mahto | 0.48 | 0-1 | 1 | 1 | 1 | 5 | 292 | 292 | TA504 |  |  |  |  | Deglal Mahato | 4.94 | 4-5 | 0 | 0 | 0 | 3 | 98.71 | 168.12 | TA505
Govind Mahto | 0.29 | 0-1 | 1 | 1 | 1 | 10 | 272 | 272 | TA506 |  |  |  |  | Deglal Mahato Mp | 4.95 | 4-5 | 0 | 0 | 0 | 3 | 94.09 | 114.75 | TA505
Gulab Mahto | 0.46 | 0-1 | 0 | 0 | 0 | 8 | 151 | 151 | TA506 |  |  |  |  | Gokul Sarkar Mp 2 | 4.81 | 4-5 | 0 | 0 | 0 | 3 | 96.24 | 108.88 | TA505
Infinidea | 0.58 | 0-1 | 0 | 0 | 0 | 4 | 204.53 | 204.53 | TA419 |  |  |  |  | Jwala Singh 2 | 4.71 | 4-5 | 0 | 0 | 0 | 3 | 84.77 | 108.88 | TA505
Jai Prakash Mahto | 0.64 | 0-1 | 29 | 5 | 5.8 | 11 | 324 | 324 | TA506 |  |  |  |  | M S Tofit | 4.65 | 4-5 | 0 | 0 | 0 | 3 | 97.71 | 129 | TA418
Karam Mahto | 0.43 | 0-1 | 0 | 0 | 0 | 3 | 108 | 108 | TA504 |  |  |  |  | M S Kartik Mahto | 6.58 | 6-7 | 0 | 0 | 0 | 5 | 164.49 | 182.57 | TA512
Karni Const 1 | 0.32 | 0-1 | 0 | 0 | 0 | 10 | 214 | 214 | TA506 |  |  |  |  | Jwala Singh | 7.11 | 7-8 | 0 | 0 | 0 | 3 | 220.51 | 232.01 | TA419, TA505
Karni Const 2 | 0.48 | 0-1 | 25 | 4 | 6.25 | 9 | 267 | 267 | TA506
Karni Const 3 | 0.42 | 0-1 | 0 | 0 | 0 | 11 | 285 | 285 | TA506
Karni Const 4 | 0.33 | 0-1 | 0 | 0 | 0 | 8 | 254 | 254 | TA506
Karni Const 5 | 0.96 | 0-1 | 12 | 1 | 12 | 5 | 147 | 147 | TA506
Karni Const 6 | 0.34 | 0-1 | 2 | 1 | 2 | 4 | 87 | 87 | TA506
Khemlal Mahto | 0.43 | 0-1 | 25 | 2 | 12.5 | 11 | 280 | 280 | TA506
Madhu Sah | 0.84 | 0-1 | 0 | 0 | 0 | 34 | 1546.67 | 1546.67 | TA419
Mohan Mahto | 0.38 | 0-1 | 0 | 0 | 0 | 4 | 125 | 125 | TA506
Namechand Mahto | 0.59 | 0-1 | 0 | 0 | 0 | 16 | 269.34 | 269.34 | TB507
Pankaj 2 | 0.8 | 0-1 | 0 | 0 | 0 | 24 | 912 | 912 | TA504, TA506
Prem Kumar | 0.47 | 0-1 | 2 | 1 | 2 | 4 | 156 | 156 | TA506
Rajesh Mahto | 0.63 | 0-1 | 0 | 0 | 0 | 4 | 57.11 | 57.11 | TB507
Rohit | 0.75 | 0-1 | 0 | 0 | 0 | 4 | 224.93 | 224.93 | TA419
Sainik Traders | 0.52 | 0-1 | 13 | 2 | 6.5 | 11 | 479 | 479 | TA504
Sakhila Khatun | 0.99 | 0-1 | 0 | 0 | 0 | 3 | 168.88 | 168.88 | TA414
Satyam Trading | 0.48 | 0-1 | 0 | 0 | 0 | 5 | 195.06 | 195.06 | TA419
Shri Karni Construction | 0.66 | 0-1 | 0 | 0 | 0 | 29 | 619 | 619 | TA506
Ahmed Construction | 1.54 | 1-2 | 3 | 1 | 3 | 8 | 101.95 | 101.95 | TB507
Ajay Kumar 1 | 1.14 | 1-2 | 0 | 0 | 0 | 3 | 41.02 | 41.02 | TB507
Ayansh Const | 1.32 | 1-2 | 0 | 0 | 0 | 3 | 34.29 | 34.29 | TB507
Bhairo Mahto Departmental | 1.18 | 1-2 | 0 | 0 | 0 | 3 | 121.76 | 121.76 | TB401
Bhoi Enterprises | 1.99 | 1-2 | 2 | 1 | 2 | 19 | 253.31 | 253.31 | TB507
Ganesh | 1.85 | 1-2 | 0 | 0 | 0 | 4 | 209.51 | 209.51 | TA419, TB408
Ganesh 2 | 1.44 | 1-2 | 0 | 0 | 0 | 3 | 132.2 | 132.2 | TA419
Gang 01 Sanjay | 1.63 | 1-2 | 16 | 5 | 3.2 | 30 | 968.84 | 968.84 | TA418
Gang 02 Sanjay | 1.55 | 1-2 | 14 | 6 | 2.33 | 26 | 915.1 | 915.1 | TA418
Horil Mahto | 1.21 | 1-2 | 10 | 3 | 3.33 | 29 | 1142.95 | 1142.95 | TA416, TA506
Lakhan Singh | 1.64 | 1-2 | 0 | 0 | 0 | 3 | 14.73 | 14.73 | TB501
M S Company Gang | 1.94 | 1-2 | 4 | 2 | 2 | 6 | 240.8 | 221.03 | TA512
M S Sakkurddin | 1.33 | 1-2 | 0 | 0 | 0 | 3 | 118.5 | 118.5 | TA414
Pankaj | 1.43 | 1-2 | 4 | 3 | 1.33 | 52 | 2006.41 | 2006.41 | TA416, TA504, TA506, TB401
Paramanand 1 | 1.82 | 1-2 | 0 | 0 | 0 | 9 | 357.37 | 357.37 | TA505
Punam Devi 3 | 1.26 | 1-2 | 0 | 0 | 0 | 16 | 643.35 | 643.35 | TA413
Pusplata Ashok | 1.68 | 1-2 | 3 | 1 | 3 | 6 | 266.13 | 266.13 | TB401, TB408
Rabiul Hauq | 1.86 | 1-2 | 4 | 1 | 4 | 10 | 52.21 | 52.21 | TB501
Radha Enterprises | 1.34 | 1-2 | 0 | 0 | 0 | 22 | 1279.36 | 1279.36 | TA419
Raju Kumar | 1.36 | 1-2 | 0 | 0 | 0 | 3 | 191.51 | 191.51 | TA419
Satyam Trivedi | 1.52 | 1-2 | 7 | 3 | 2.33 | 7 | 287.81 | 287.81 | TB401
Savitha | 1.67 | 1-2 | 14 | 3 | 4.67 | 3 | 102 | 102 | TA418
Suman | 1.32 | 1-2 | 8 | 2 | 4 | 9 | 70 | 70 | TB501
Vedanta Construction | 1.97 | 1-2 | 1 | 1 | 1 | 5 | 187.52 | 187.52 | TB408
Bhairo Mahto | 2.37 | 2-3 | 2 | 2 | 1 | 7 | 267.9 | 267.9 | TB401, TB408
Bhuvneshwar | 2.99 | 2-3 | 8 | 3 | 2.67 | 4 | 152.7 | 152.7 | TB408
Dipak | 2.8 | 2-3 | 6 | 4 | 1.5 | 31 | 483.64 | 483.64 | TB507
Dudhnath Kumar | 2.51 | 2-3 | 55 | 18 | 3.06 | 51 | 346.53 | 346.53 | TB501
Ghanshyam Mahto | 2.52 | 2-3 | 34 | 8 | 4.25 | 14 | 689.52 | 689.52 | TA325
Gokul Sarkar | 2.62 | 2-3 | 0 | 0 | 0 | 22 | 364.82 | 364.82 | TB507
Intizer Infratech | 2.63 | 2-3 | 0 | 0 | 0 | 3 | 113.19 | 113.19 | TA325
Kaushalya Const | 2.61 | 2-3 | 15 | 3 | 5 | 3 | 158.98 | 158.98 | TB408
Kec 01 Barkat Ali | 2.17 | 2-3 | 4 | 1 | 4 | 7 | 210.63 | 210.63 | TA418
Kec 02 Barkat Ali | 2.76 | 2-3 | 11 | 6 | 1.83 | 18 | 622.9 | 622.9 | TA418
M K Infra | 2.45 | 2-3 | 8 | 1 | 8 | 5 | 222.9 | 222.9 | TA416
Mithun Kumar | 2.1 | 2-3 | 29 | 8 | 3.62 | 17 | 908.76 | 908.76 | TA325
Modina India | 2.38 | 2-3 | 18 | 6 | 3 | 16 | 790.55 | 790.55 | TA325
Modina India 2 Pgcil | 2.31 | 2-3 | 18 | 3 | 6 | 3 | 131.61 | 131.61 | TA325
Nan | 2.51 | 2-3 | 0 | 0 | 0 | 5 | 350.7 | 350.7 | TA325
Poornam Kumari | 2.18 | 2-3 | 4 | 1 | 4 | 3 | 139.47 | 139.47 | TA419
Praveen | 2.26 | 2-3 | 34 | 10 | 3.4 | 23 | 936.22 | 936.22 | TA421
Pritam Enterprises 4 | 2.82 | 2-3 | 8 | 2 | 4 | 6 | 262.62 | 262.62 | TA413
Punam Kumari 1 | 2.02 | 2-3 | 0 | 0 | 0 | 26 | 1336.49 | 1336.49 | TA413, TA416, TA419, TA504
Punam Kumari 2 | 2.68 | 2-3 | 0 | 0 | 0 | 21 | 1122.37 | 1122.37 | TA413, TA416, TA419, TA504
Radha Enterprises 1 | 2.15 | 2-3 | 20 | 3 | 6.67 | 11 | 545.07 | 545.07 | TA419
Rafikul Islam | 2.81 | 2-3 | 0 | 0 | 0 | 8 | 325.5 | 325.5 | TB401, TB408
Raj Labour Suppliers | 2.62 | 2-3 | 21 | 3 | 7 | 5 | 97.08 | 97.08 | TB605
Rames Kumar M | 2.8 | 2-3 | 29 | 3 | 9.67 | 8 | 53.16 | 53.16 | TB501
Ramesh Kumar | 2.54 | 2-3 | 88 | 29 | 3.03 | 95 | 632.21 | 632.21 | TB501
Ramesh Kumar M | 2.14 | 2-3 | 6 | 3 | 2 | 5 | 25.68 | 25.68 | TB501
Rupesh | 2.1 | 2-3 | 16 | 3 | 5.33 | 4 | 371.25 | 371.25 | TA325
Saidur Rahaman | 2.19 | 2-3 | 3 | 1 | 3 | 3 | 19.73 | 19.73 | TB501
Senahul | 2.76 | 2-3 | 33 | 8 | 4.12 | 11 | 663.26 | 663.26 | TA325
Shree Ganesh Sital Enterprice | 2.22 | 2-3 | 12 | 3 | 4 | 14 | 86.7 | 86.7 | TB501
Ajay Kumar | 3.82 | 3-4 | 6 | 4 | 1.5 | 11 | 644.96 | 644.96 | TA325, TB507
Aloriva Global | 3.37 | 3-4 | 6 | 2 | 3 | 3 | 161.58 | 161.58 | TA416
Amar Kumar Singh | 3.33 | 3-4 | 3 | 1 | 3 | 4 | 223.06 | 223.06 | TA413
Amit Choudhury | 3.93 | 3-4 | 0 | 0 | 0 | 5 | 416.64 | 416.64 | TA416
Anarul Haque | 3.81 | 3-4 | 3 | 2 | 1.5 | 3 | 247.89 | 247.89 | TA325
Anil Construction | 3.84 | 3-4 | 1 | 1 | 1 | 18 | 411.02 | 411.02 | TA513
Ashok | 3.44 | 3-4 | 8 | 2 | 4 | 4 | 165.33 | 165.33 | TA421
Barkat Ali | 3 | 3-4 | 16 | 6 | 2.67 | 16 | 731.12 | 731.12 | TA325
Bina Devi | 3.86 | 3-4 | 25 | 7 | 3.57 | 17 | 691.22 | 691.22 | TB401, TB408
Crane Erc Team Mp | 3.04 | 3-4 | 0 | 0 | 0 | 8 | 313.42 | 313.42 | TA505
Daulat Mahto | 3.74 | 3-4 | 31 | 12 | 2.58 | 13 | 594.05 | 594.05 | TA325
Departmental Gang | 3.17 | 3-4 | 1 | 1 | 1 | 6 | 250.09 | 250.09 | TB401
Dk Verma | 3.11 | 3-4 | 17 | 6 | 2.83 | 21 | 1534.65 | 1534.65 | TA325
Eagle Enterprises | 3.83 | 3-4 | 0 | 0 | 0 | 3 | 114.75 | 114.75 | TA505
Eagle Enterprises Paramand | 3.31 | 3-4 | 2 | 1 | 2 | 8 | 308.08 | 308.08 | TA505
Hassan 2 | 3.81 | 3-4 | 0 | 0 | 0 | 3 | 141.08 | 141.08 | TA421
J Lngh O 2 | 3.16 | 3-4 | 0 | 0 | 0 | 5 | 186.53 | 186.53 | TA421
Jhemon Mahato 2 | 3.61 | 3-4 | 0 | 0 | 0 | 9 | 444.32 | 444.32 | TA505
Jwala Singh | 3.13 | 3-4 | 0 | 0 | 0 | 85 | 3840.31 | 3840.31 | TA325, TA419, TA505, TB401, TB408
Jyoti Const | 3.91 | 3-4 | 0 | 0 | 0 | 11 | 597.95 | 597.95 | TA505
Kamlesh Kumar | 3.23 | 3-4 | 2 | 1 | 2 | 4 | 187.24 | 187.24 | TB408
M S Govind Mahto 2 | 3.28 | 3-4 | 0 | 0 | 0 | 3 | 131.31 | 131.31 | TA512
M S Kavya Enterprises | 3.59 | 3-4 | 15 | 4 | 3.75 | 13 | 502.74 | 502.74 | TA512
M S Mdpl | 3.16 | 3-4 | 2 | 2 | 1 | 10 | 451.3 | 451.3 | TA418
M S Punam Kumari 3 | 3.88 | 3-4 | 1 | 1 | 1 | 5 | 193.76 | 193.76 | TA512
Maa Const | 3.45 | 3-4 | 1 | 1 | 1 | 7 | 276 | 276 | TA421
Mjr | 3.8 | 3-4 | 25 | 9 | 2.78 | 13 | 710.38 | 710.38 | TA325
Modina India 3 Pgcil | 3.76 | 3-4 | 14 | 4 | 3.5 | 4 | 157.92 | 157.92 | TA325
Pc 2 | 3.54 | 3-4 | 0 | 0 | 0 | 3 | 279.55 | 279.55 | TA325
Poonam Kumari | 3.46 | 3-4 | 0 | 0 | 0 | 16 | 733.05 | 733.05 | TA325, TA419
Prayag Mahto | 3.19 | 3-4 | 16 | 2 | 8 | 3 | 223.2 | 223.2 | TA325
Prayag Saw | 3.46 | 3-4 | 8 | 4 | 2 | 7 | 114.33 | 114.33 | TB507
Prayag Saw 1 | 3.38 | 3-4 | 0 | 0 | 0 | 14 | 216.25 | 216.25 | TB507
Prayag Saw 2 | 3.21 | 3-4 | 4 | 2 | 2 | 22 | 340.35 | 340.35 | TB507
Prayag Shah Mp | 3.34 | 3-4 | 1 | 1 | 1 | 6 | 247.07 | 247.07 | TA505
Pritam Enterprises | 3.27 | 3-4 | 0 | 0 | 0 | 16 | 287.38 | 287.38 | TA413, TB507
Pritam Enterprises 1 | 3.37 | 3-4 | 12 | 4 | 3 | 9 | 390.73 | 390.73 | TA413
Pritam Enterprises 2 | 3.42 | 3-4 | 4 | 1 | 4 | 12 | 546.44 | 546.44 | TA413
Priyanka Devi Subodh | 3.71 | 3-4 | 0 | 0 | 0 | 4 | 181.58 | 181.58 | TB401, TB408
Punam Kumari | 3.84 | 3-4 | 2 | 1 | 2 | 9 | 490.89 | 490.89 | TA413, TA416, TA419
Punam Kumari 3 | 3.88 | 3-4 | 0 | 0 | 0 | 5 | 337.85 | 337.85 | TA413, TA416
Rahim Khan | 3.22 | 3-4 | 10 | 5 | 2 | 13 | 588.7 | 588.7 | TA325
S K Janarul Sheikh | 3.52 | 3-4 | 5 | 2 | 2.5 | 3 | 109.11 | 109.11 | TA421
Sainik Trader | 3.33 | 3-4 | 1 | 1 | 1 | 3 | 236.3 | 236.3 | TA416
Sheetal Singh | 3.67 | 3-4 | 0 | 0 | 0 | 3 | 150.64 | 150.64 | TB408
Sk Samiul 1 | 3.5 | 3-4 | 7 | 3 | 2.33 | 7 | 321.96 | 321.96 | TA413
Sk Samiul 2 | 3.23 | 3-4 | 0 | 0 | 0 | 4 | 145.46 | 145.46 | TA413
Sk Samuil | 3.18 | 3-4 | 11 | 4 | 2.75 | 23 | 937.56 | 937.56 | TA325
Sukhriddin | 3.14 | 3-4 | 33 | 12 | 2.75 | 16 | 869.03 | 869.03 | TA325
Sukruddin | 3.97 | 3-4 | 6 | 1 | 6 | 4 | 380.67 | 380.67 | TA325
Sulen Sarkar | 3.64 | 3-4 | 16 | 3 | 5.33 | 7 | 276.46 | 276.46 | TA325
Thanu Mahto | 3.48 | 3-4 | 15 | 6 | 2.5 | 14 | 668.09 | 668.09 | TA325
Toshan Mahato | 3.77 | 3-4 | 0 | 0 | 0 | 7 | 460.06 | 460.06 | TA505
Usha Tower | 3.38 | 3-4 | 6 | 3 | 2 | 5 | 199.46 | 199.46 | TB401, TB408
Vasu Dev Singh 1 | 3.34 | 3-4 | 0 | 0 | 0 | 10 | 431.24 | 431.24 | TA413
Vasu Dev Singh 2 | 3.67 | 3-4 | 9 | 1 | 9 | 12 | 521.26 | 521.26 | TA413
Vinay Const | 3.81 | 3-4 | 4 | 2 | 2 | 3 | 133.22 | 133.22 | TB401
Vinay Construction | 3.22 | 3-4 | 3 | 2 | 1.5 | 12 | 453.82 | 453.82 | TB408, TB507
Vivek Ganju | 3.61 | 3-4 | 7 | 5 | 1.4 | 10 | 389.67 | 389.67 | TB401, TB408
Amit Const | 4.85 | 4-5 | 1 | 1 | 1 | 3 | 145.42 | 145.42 | TA416
Amit Kumar Singh | 4.38 | 4-5 | 1 | 1 | 1 | 8 | 354.72 | 354.72 | TA413
Bhagwan Construction | 4.51 | 4-5 | 0 | 0 | 0 | 7 | 279.72 | 279.72 | TA413
Bhairaw Mahto | 4.31 | 4-5 | 7 | 1 | 7 | 5 | 318.65 | 318.65 | TA413
Deglal Mahato Mp | 4.79 | 4-5 | 0 | 0 | 0 | 16 | 632.74 | 632.74 | TA505
Gagan Enterprises | 4.66 | 4-5 | 8 | 1 | 8 | 3 | 163.1 | 163.1 | TA419
Ganesh Kr Sinha | 4.34 | 4-5 | 9 | 3 | 3 | 23 | 1088.25 | 1088.25 | TB401
Ganesh Sinha | 4.53 | 4-5 | 16 | 5 | 3.2 | 30 | 1313.9 | 1313.9 | TB401, TB408
Gokul Rajwanshi | 4.61 | 4-5 | 6 | 4 | 1.5 | 23 | 940.12 | 940.12 | TA505
Gokul Sarkar 1 | 4.15 | 4-5 | 5 | 1 | 5 | 3 | 120.23 | 120.23 | TA325
Gokul Sarkar Mp | 4.74 | 4-5 | 2 | 2 | 1 | 7 | 251.18 | 251.18 | TA505
Gokul Sarkar Mp 2 | 4.41 | 4-5 | 0 | 0 | 0 | 6 | 215.99 | 215.99 | TA505
Govind Mahto 1 | 4.48 | 4-5 | 11 | 4 | 2.75 | 12 | 515.57 | 515.57 | TA413
Govind Mahto 2 | 4.93 | 4-5 | 4 | 1 | 4 | 9 | 522.54 | 522.54 | TA413
Hassan | 4.22 | 4-5 | 9 | 4 | 2.25 | 18 | 890.28 | 890.28 | TA421
Jagannaath Saw Mp | 4.76 | 4-5 | 0 | 0 | 0 | 14 | 623.66 | 623.66 | TA505
Jay Prakash | 4.76 | 4-5 | 2 | 1 | 2 | 3 | 100 | 100 | TA506
Jirwa Devi | 4.18 | 4-5 | 22 | 7 | 3.14 | 28 | 1317.03 | 1317.03 | TB401, TB408
Jwala Singh 1 | 4.11 | 4-5 | 15 | 4 | 3.75 | 25 | 1098.14 | 1098.14 | TA413, TB401, TB408
Kartik Mahto | 4.31 | 4-5 | 0 | 0 | 0 | 5 | 241.46 | 241.46 | TA413
Khatan | 4.93 | 4-5 | 8 | 3 | 2.67 | 17 | 621.41 | 621.41 | TA421
Khemlal | 4.56 | 4-5 | 0 | 0 | 0 | 4 | 82 | 82 | TA506
Kongres Kumar 1 | 4.56 | 4-5 | 0 | 0 | 0 | 3 | 365.08 | 365.08 | TA416
M S Punam Kumari | 4.77 | 4-5 | 0 | 0 | 0 | 15 | 577.73 | 577.73 | TA512
M S Punam Kumari 4 | 4.89 | 4-5 | 5 | 2 | 2.5 | 4 | 186.01 | 186.01 | TA512
M S Tofit | 4.53 | 4-5 | 10 | 4 | 2.5 | 13 | 575.3 | 575.3 | TA418
Maa Construction | 4.01 | 4-5 | 15 | 8 | 1.88 | 12 | 750.69 | 750.69 | TA325, TA416
Mahon Mahto | 4.28 | 4-5 | 0 | 0 | 0 | 4 | 552.06 | 552.06 | TA416
Naziruddin | 4.86 | 4-5 | 0 | 0 | 0 | 11 | 461.81 | 461.81 | TA421
Pankaj Kumar | 4.56 | 4-5 | 0 | 0 | 0 | 6 | 615.75 | 615.75 | TA416
Panva Devi | 4.19 | 4-5 | 2 | 1 | 2 | 5 | 339.27 | 339.27 | TB401, TB408
Pinki Devi | 4.47 | 4-5 | 14 | 3 | 4.67 | 10 | 469.69 | 469.69 | TA413, TA419, TA504
Priyanka Devi | 4.01 | 4-5 | 10 | 2 | 5 | 6 | 256.59 | 256.59 | TB401, TB408
Punam Kumari 4 | 4.7 | 4-5 | 0 | 0 | 0 | 5 | 220.81 | 220.81 | TA413, TA419
Pusplata 7 | 4.66 | 4-5 | 0 | 0 | 0 | 3 | 116.54 | 116.54 | TB401
Pusplata Dharamveer | 4.48 | 4-5 | 1 | 1 | 1 | 3 | 152.41 | 152.41 | TB401, TB408
Pusplata Rajaram | 4.87 | 4-5 | 0 | 0 | 0 | 3 | 185.01 | 185.01 | TB401, TB408
Rahul Kumar | 4.35 | 4-5 | 68 | 19 | 3.58 | 47 | 2773.91 | 2773.91 | TA325, TA414, TB401, TB408
Reeta Bharti | 4.93 | 4-5 | 12 | 5 | 2.4 | 29 | 1648.09 | 1648.09 | TA416
Rudra Construction | 4.08 | 4-5 | 16 | 5 | 3.2 | 7 | 314.12 | 314.12 | TA416
Sanjeev Kumar | 4.38 | 4-5 | 21 | 7 | 3 | 25 | 1168.76 | 1168.76 | TB401, TB408
Satyam Enterprises Vijay | 4.67 | 4-5 | 0 | 0 | 0 | 4 | 154.05 | 154.05 | TB408
Satyam Vijay | 4.88 | 4-5 | 7 | 3 | 2.33 | 9 | 376.1 | 376.1 | TB401
Sital Singh | 4.57 | 4-5 | 0 | 0 | 0 | 3 | 132.61 | 132.6 | TB401
Sital Singh 1 | 4.63 | 4-5 | 0 | 0 | 0 | 5 | 231.74 | 231.74 | TB401
Uma Const | 4.21 | 4-5 | 2 | 1 | 2 | 8 | 320.31 | 320.31 | TB408
Yogendra Mahto | 4.03 | 4-5 | 11 | 5 | 2.2 | 15 | 709.09 | 709.09 | TB401, TB408
Amar Singh | 5.14 | 5-6 | 17 | 8 | 2.12 | 25 | 1171.91 | 1171.91 | TA416
Anita Devi | 5.33 | 5-6 | 4 | 2 | 2 | 3 | 298.41 | 298.41 | TA325
Arawali 2 | 5.18 | 5-6 | 0 | 0 | 0 | 3 | 113.86 | 113.86 | TB408
Arawali Infra 2 | 5.23 | 5-6 | 12 | 4 | 3 | 4 | 230.2 | 230.2 | TB401
Asc Heights | 5.45 | 5-6 | 8 | 4 | 2 | 20 | 1040.7 | 1040.7 | TA416
D K Verma | 5.94 | 5-6 | 17 | 6 | 2.83 | 22 | 956.69 | 956.69 | TA421
Devi Construction | 5.93 | 5-6 | 5 | 3 | 1.67 | 7 | 468.81 | 468.81 | TB401, TB408
Fouzi Ratto | 5.04 | 5-6 | 2 | 1 | 2 | 12 | 669.87 | 669.87 | TA413
Gagan Enterprise 2 | 5.99 | 5-6 | 5 | 2 | 2.5 | 5 | 281.66 | 281.66 | TA416
Ganesh Const | 5.51 | 5-6 | 10 | 1 | 10 | 10 | 424.63 | 424.63 | TB408
Gokul Sarkar 2 | 5.66 | 5-6 | 7 | 4 | 1.75 | 4 | 266.18 | 266.18 | TA325
Horil | 5.28 | 5-6 | 0 | 0 | 0 | 4 | 95 | 95 | TA506
J Lngh O 1 | 5.84 | 5-6 | 1 | 1 | 1 | 6 | 251.1 | 251.1 | TA421
Jailal Ageria | 5.07 | 5-6 | 7 | 6 | 1.17 | 12 | 572.82 | 572.82 | TB401, TB408
Jaman Mahto 1 Ratna Devi | 5.12 | 5-6 | 5 | 2 | 2.5 | 4 | 394.41 | 394.41 | TA325
Jhemon Mahato 1 | 5.66 | 5-6 | 0 | 0 | 0 | 6 | 396.26 | 396.26 | TA505
Jwala Singh 2 | 5.81 | 5-6 | 28 | 7 | 4 | 41 | 1753.28 | 1753.28 | TA413, TA505, TB401, TB408
M S Govind Mahto | 5.91 | 5-6 | 0 | 0 | 0 | 4 | 165.36 | 165.36 | TA512
M S Jwala Singh | 5.18 | 5-6 | 3 | 3 | 1 | 18 | 786.62 | 786.62 | TA512
M S Jwala Singh 2 | 5.03 | 5-6 | 0 | 0 | 0 | 7 | 266.85 | 266.85 | TA512
Md Akhtar | 5.19 | 5-6 | 8 | 2 | 4 | 4 | 409.72 | 409.72 | TA325
Mukesh | 5.28 | 5-6 | 1 | 1 | 1 | 10 | 617.89 | 617.89 | TA325
Nasiruddin | 5.22 | 5-6 | 1 | 1 | 1 | 3 | 109.72 | 109.72 | TA601
Nirmal Mahto | 5.1 | 5-6 | 11 | 5 | 2.2 | 24 | 1061.82 | 1061.82 | TB401, TB408
Pankaj Singh Mp | 5.36 | 5-6 | 0 | 0 | 0 | 13 | 519.88 | 519.88 | TA505
Pritam Enterprises 3 | 5.22 | 5-6 | 0 | 0 | 0 | 9 | 428.06 | 428.06 | TA413
Priyanka Devi 2 | 5.09 | 5-6 | 13 | 3 | 4.33 | 4 | 152.7 | 152.7 | TB401, TB408
Priyanka Devi Sudheer | 5.48 | 5-6 | 41 | 13 | 3.15 | 13 | 559.06 | 559.06 | TB401, TB408
Punam Devi 1 | 5.83 | 5-6 | 3 | 1 | 3 | 20 | 821.67 | 821.67 | TA413
Punam Devi 2 | 5.03 | 5-6 | 0 | 0 | 0 | 24 | 1026.73 | 1026.73 | TA413
Pusplata 5 | 5.41 | 5-6 | 1 | 1 | 1 | 4 | 162.38 | 162.38 | TB401
Pusplata 6 | 5.31 | 5-6 | 3 | 1 | 3 | 5 | 212.59 | 212.59 | TB401
Pusplata Deepak | 5.4 | 5-6 | 12 | 4 | 3 | 5 | 188.86 | 188.86 | TB401, TB408
Pusplata Kailash | 5.47 | 5-6 | 0 | 0 | 0 | 7 | 267.9 | 267.9 | TB408
Pusplata Praful | 5.32 | 5-6 | 0 | 0 | 0 | 3 | 164.92 | 164.92 | TB401, TB408
Satyam Mondal | 5.05 | 5-6 | 6 | 4 | 1.5 | 7 | 348.59 | 348.59 | TB401
Subhash | 5.55 | 5-6 | 10 | 6 | 1.67 | 13 | 837.66 | 837.66 | TA325, TA414, TA418
Sunny Const | 5.74 | 5-6 | 10 | 5 | 2 | 84 | 3869.78 | 3869.78 | TB401, TB408
Tejal Construction | 5.01 | 5-6 | 0 | 0 | 0 | 3 | 115.2 | 115.2 | TB401
Ananya Traders 1 | 6.03 | 6-7 | 12 | 6 | 2 | 14 | 1036.91 | 1036.91 | TA416
Ananya Traders 2 | 6.77 | 6-7 | 1 | 1 | 1 | 11 | 595.89 | 595.89 | TA416
Chinta Devi | 6.34 | 6-7 | 15 | 10 | 1.5 | 93 | 4213.81 | 4213.81 | TB401, TB408
Deglal Mahato | 6.36 | 6-7 | 0 | 0 | 0 | 16 | 947.24 | 947.24 | TA505
Deglal Mahto | 6.22 | 6-7 | 7 | 4 | 1.75 | 18 | 758.48 | 758.48 | TB401, TB408
Dewi Construction Girendra | 6.64 | 6-7 | 9 | 5 | 1.8 | 40 | 1858.04 | 1858.04 | TA416
Dhaneswar Mahto | 6.96 | 6-7 | 46 | 14 | 3.29 | 22 | 1433.16 | 1433.16 | TA325
Gagan Enterprise 1 | 6.39 | 6-7 | 9 | 2 | 4.5 | 13 | 952.15 | 952.15 | TA416
Gauri Shankar Mahto | 6.67 | 6-7 | 13 | 2 | 6.5 | 4 | 233.34 | 233.34 | TA421
Gourishankar | 6.26 | 6-7 | 54 | 19 | 2.84 | 38 | 2440.69 | 2440.69 | TA325, TB401
J Lngh | 6.41 | 6-7 | 1 | 1 | 1 | 7 | 262.86 | 262.86 | TA421
Jagdish Mahto | 6.31 | 6-7 | 2 | 2 | 1 | 20 | 845.82 | 845.82 | TB401, TB408
Jwala Singh Suraj Kumar | 6.26 | 6-7 | 0 | 0 | 0 | 3 | 162.83 | 162.83 | TB408
Lalan Mahto | 6.36 | 6-7 | 2 | 2 | 1 | 17 | 762.97 | 762.97 | TA325
Pinky Dewi | 6.08 | 6-7 | 11 | 5 | 2.2 | 37 | 1921.83 | 1921.83 | TA416
Pusplata 2 | 6.4 | 6-7 | 0 | 0 | 0 | 5 | 224.04 | 224.04 | TB401
Sakila Khatun | 6.69 | 6-7 | 5 | 2 | 2.5 | 4 | 374.7 | 374.7 | TA325, TA414
Shila Devi | 6 | 6-7 | 1 | 1 | 1 | 14 | 840.24 | 840.24 | TA505
Sobha Devi | 6.58 | 6-7 | 11 | 8 | 1.38 | 105 | 4487.37 | 4487.37 | TB401, TB408
Sunny Construction | 6.59 | 6-7 | 2 | 1 | 2 | 14 | 679.11 | 679.11 | TB408
Suraj Const | 6.03 | 6-7 | 0 | 0 | 0 | 36 | 1440.88 | 1440.88 | TB401, TB408
Ved Prakash | 6.64 | 6-7 | 0 | 0 | 0 | 11 | 863.08 | 863.08 | TA413
Jwala | 7.68 | 7-8 | 21 | 12 | 1.75 | 22 | 1229.32 | 1229.32 | TA325
Khatun | 7.24 | 7-8 | 34 | 12 | 2.83 | 68 | 2997.93 | 2997.93 | TA421
M S Kartik Mahto | 7.04 | 7-8 | 0 | 0 | 0 | 21 | 837.88 | 837.88 | TA512
Poonam | 7.19 | 7-8 | 8 | 3 | 2.67 | 9 | 366.88 | 366.88 | TB401
Punam Devi 4 | 7.87 | 7-8 | 0 | 0 | 0 | 15 | 621.97 | 621.97 | TA413
Pusplata 1 | 7.43 | 7-8 | 5 | 3 | 1.67 | 6 | 282.37 | 282.37 | TB401
Pusplata 3 | 7.14 | 7-8 | 14 | 2 | 7 | 4 | 171.45 | 171.45 | TB401
Satyam Enterprises | 7.81 | 7-8 | 0 | 0 | 0 | 10 | 492.15 | 492.15 | TB408
Satyam Nitish | 7.81 | 7-8 | 5 | 3 | 1.67 | 9 | 632.23 | 632.23 | TB401
Shobha Devi | 7.3 | 7-8 | 26 | 5 | 5.2 | 19 | 1153.97 | 1153.97 | TB408
Subash | 7.46 | 7-8 | 6 | 4 | 1.5 | 97 | 3856.21 | 3856.21 | TA421
Jwala Singh 3 | 8.09 | 8-9 | 8 | 3 | 2.67 | 5 | 283.16 | 283.16 | TB401
Pusplata 4 | 8.04 | 8-9 | 2 | 2 | 1 | 8 | 313.74 | 313.74 | TB401
Satyam Manish | 8.28 | 8-9 | 11 | 5 | 2.2 | 14 | 786.68 | 786.68 | TB401, TB408

## Monthly Gang Buckets
Monthly Gang Production Buckets (All Data)
Scope: 2023-09-13 to 2026-01-22 ¦ Projects: 18 ¦ Erections: 3677 ¦ Gangs: 456
Bucket | Gang-Months | Sum of Tower Weight (MT)
<80 | 1285 | 36793.21
80-100 | 136 | 11958.31
100-120 | 133 | 14780.01
120-140 | 113 | 14315.19
140-160 | 97 | 14163.49
160-180 | 77 | 13085.15
180-200 | 58 | 10351.22
200-220 | 54 | 11491.96
220-240 | 40 | 9393.1
240-260 | 35 | 8929.44
>=260 | 44 | 13374.18
Gang Name | Month | Monthly Production (MT) | Monthly Tower Weight (MT) | Project Codes | Towers Erected | Bucket
A B Const Birendra Panday | 2025-09 | 17 | 17 | TA506 | 1 | <80
Aamir Khan | 2025-11 | 52.53 | 37.73 | TA325 | 1 | <80
Aamir Khan | 2025-12 | 24.66 | 39.46 | TA325 | 1 | <80
Ab Const | 2025-05 | 4.97 | 0 |  | 0 | <80
Ab Const | 2025-06 | 11.66 | 0 |  | 0 | <80
Ab Const | 2025-07 | 14.78 | 0 |  | 0 | <80
Ab Const | 2025-08 | 10.05 | 22 | TA506 | 1 | <80
Ab Const | 2025-09 | 12.83 | 0 |  | 0 | <80
Ab Const | 2025-10 | 55.17 | 39 | TA506 | 2 | <80
Ab Const | 2025-11 | 58.54 | 107 | TA506 | 4 | <80
Ab Const | 2025-12 | 22.5 | 0 |  | 0 | <80
Ab Const | 2026-01 | 4.5 | 27 | TA506 | 1 | <80
Ab Const 2 | 2025-12 | 14.4 | 0 |  | 0 | <80
Ab Const 2 | 2026-01 | 3.6 | 18 | TA506 | 1 | <80
Ab Construction | 2026-01 | 25 | 25 | TA506 | 1 | <80
Ahmed Construction | 2025-07 | 11.14 | 11.14 | TB507 | 1 | <80
Ahmed Construction | 2025-08 | 56.55 | 53.98 | TB507 | 4 | <80
Ahmed Construction | 2025-09 | 34.26 | 36.83 | TB507 | 3 | <80
Ajay Kumar | 2024-07 | 95.95 | 80.41 | TA325 | 1 | 80-100
Ajay Kumar | 2024-08 | 31.08 | 46.62 | TA325 | 1 | <80
Ajay Kumar | 2024-09 | 103.71 | 72.24 | TA325 | 1 | 100-120
Ajay Kumar | 2024-10 | 165.84 | 179.64 | TA325 | 2 | 160-180
Ajay Kumar | 2024-11 | 157.35 | 160.68 | TA325 | 2 | 140-160
Ajay Kumar | 2024-12 | 25.11 | 39.46 | TA325 | 1 | <80
Ajay Kumar | 2025-01 | 7.84 | 0 |  | 0 | <80
Ajay Kumar | 2025-02 | 28.21 | 36.04 | TA325 | 1 | <80
Ajay Kumar | 2025-08 | 11.14 | 11.14 | TB507 | 1 | <80
Ajay Kumar | 2025-09 | 4.68 | 0 |  | 0 | <80
Ajay Kumar | 2025-10 | 14.05 | 18.73 | TB507 | 1 | <80
Ajay Kumar 1 | 2025-09 | 41.02 | 41.02 | TB507 | 3 | <80
Ajay Kumar 2 | 2025-09 | 21.9 | 12 | TB507 | 1 | <80
Ajay Kumar 2 | 2025-10 | 1.24 | 11.14 | TB507 | 1 | <80
Ali Uslam | 2025-12 | 36.57 | 36.57 | TA601 | 1 | <80
Alo Reeva | 2025-05 | 2.58 | 0 |  | 0 | <80
Alo Reeva | 2025-06 | 3.87 | 0 |  | 0 | <80
Alo Reeva | 2025-07 | 4 | 0 |  | 0 | <80
Alo Reeva | 2025-08 | 4 | 0 |  | 0 | <80
Alo Reeva | 2025-09 | 1.55 | 16 | TA506 | 1 | <80
Aloriva Global | 2025-11 | 108.26 | 108.26 | TA416 | 2 | 100-120
Aloriva Global | 2025-12 | 53.32 | 53.32 | TA416 | 1 | <80
Amar Kumar Singh | 2025-08 | 39.42 | 0 |  | 0 | <80
Amar Kumar Singh | 2025-09 | 100.24 | 110.58 | TA413 | 2 | 100-120
Amar Kumar Singh | 2025-10 | 83.4 | 112.48 | TA413 | 2 | 80-100
Amar Singh | 2024-11 | 47.96 | 43.78 | TA416 | 1 | <80
Amar Singh | 2024-12 | 152.17 | 134.47 | TA416 | 3 | 140-160
Amar Singh | 2025-01 | 157.76 | 179.65 | TA416 | 4 | 140-160
Amar Singh | 2025-02 | 198.07 | 179.65 | TA416 | 4 | 180-200
Amar Singh | 2025-03 | 70 | 88.42 | TA416 | 2 | <80
Amar Singh | 2025-04 | 168.69 | 156.58 | TA416 | 3 | 160-180
Amar Singh | 2025-05 | 201.17 | 213.27 | TA416 | 5 | 200-220
Amar Singh | 2025-06 | 100.18 | 89.82 | TA416 | 2 | 100-120
Amar Singh | 2025-07 | 75.91 | 86.26 | TA416 | 1 | <80
Amit Choudhry | 2025-12 | 92.65 | 0 |  | 0 | 80-100
Amit Choudhry | 2026-01 | 50.81 | 143.46 | TA416 | 1 | <80
Amit Choudhury | 2025-08 | 59 | 0 |  | 0 | <80
Amit Choudhury | 2025-09 | 121.63 | 153 | TA416 | 2 | 120-140
Amit Choudhury | 2025-10 | 111.39 | 64.48 | TA416 | 1 | 100-120
Amit Choudhury | 2025-11 | 124.62 | 199.16 | TA416 | 2 | 120-140
Amit Const | 2025-05 | 53.32 | 53.32 | TA416 | 1 | <80
Amit Const | 2025-06 | 92.1 | 92.1 | TA416 | 2 | 80-100
Amit Kumar Singh | 2025-07 | 111.4 | 89.5 | TA413 | 2 | 100-120
Amit Kumar Singh | 2025-08 | 138.37 | 132.42 | TA413 | 3 | 120-140
Amit Kumar Singh | 2025-09 | 104.95 | 132.8 | TA413 | 3 | 100-120
Amit Yadav | 2025-11 | 16.42 | 0 |  | 0 | <80
Amit Yadav | 2025-12 | 53.26 | 43.78 | TA419 | 1 | <80
Amit Yadav | 2026-01 | 16.48 | 42.37 | TA419 | 1 | <80
Anand Construction | 2025-03 | 3.84 | 0 |  | 0 | <80
Anand Construction | 2025-04 | 97.55 | 101.39 | TA416 | 2 | 80-100
Anannya Traders | 2026-01 | 37.73 | 37.73 | TA414 | 1 | <80
Ananya Trader | 2025-09 | 94.54 | 42.37 | TA416 | 1 | 80-100
Ananya Trader | 2025-10 | 91.29 | 143.46 | TA416 | 1 | 80-100
Ananya Traders 1 | 2025-03 | 46.05 | 46.05 | TA416 | 1 | <80
Ananya Traders 1 | 2025-04 | 168.25 | 152.91 | TA416 | 3 | 160-180
Ananya Traders 1 | 2025-05 | 192.2 | 176.85 | TA416 | 4 | 180-200
Ananya Traders 1 | 2025-06 | 176.7 | 207.4 | TA416 | 2 | 160-180
Ananya Traders 1 | 2025-07 | 187.77 | 101.69 | TA416 | 1 | 180-200
Ananya Traders 1 | 2025-08 | 150.44 | 143.46 | TA416 | 1 | 140-160
Ananya Traders 1 | 2025-09 | 115.5 | 208.56 | TA416 | 2 | 100-120
Ananya Traders 2 | 2025-04 | 136.85 | 130.8 | TA416 | 3 | 120-140
Ananya Traders 2 | 2025-05 | 253.68 | 219.22 | TA416 | 5 | 240-260
Ananya Traders 2 | 2025-06 | 205.36 | 245.87 | TA416 | 3 | 200-220
Anarul Haque | 2025-02 | 21.99 | 0 |  | 0 | <80
Anarul Haque | 2025-03 | 105.1 | 72.24 | TA325 | 1 | 100-120
Anarul Haque | 2025-04 | 120.81 | 175.65 | TA325 | 2 | 120-140
Anbi Construction | 2025-12 | 10.69 | 0 |  | 0 | <80
Anbi Construction | 2026-01 | 25.95 | 36.64 | TB605 | 2 | <80
Anil Construction | 2025-09 | 41.65 | 34.6 | TA513 | 2 | <80
Anil Construction | 2025-10 | 143.95 | 146.48 | TA513 | 6 | 140-160
Anil Construction | 2025-11 | 135.66 | 122.2 | TA513 | 6 | 120-140
Anil Construction | 2025-12 | 89.76 | 107.75 | TA513 | 4 | 80-100
Anil Kumar | 2025-09 | 51.58 | 0 |  | 0 | <80
Anil Kumar | 2025-10 | 48.79 | 100.38 | TA505 | 2 | <80
Anil Kumar Departmental Kewat | 2025-06 | 29.47 | 0 |  | 0 | <80
Anil Kumar Departmental Kewat | 2025-07 | 9.38 | 38.85 | TB401 | 1 | <80
Anil Kumar Departmental Ramayan | 2025-06 | 13.97 | 0 |  | 0 | <80
Anil Kumar Departmental Ramayan | 2025-07 | 72.16 | 86.13 | TB401 | 1 | <80
Anil Kumar Kewat | 2025-06 | 60.28 | 38.85 | TB408 | 1 | <80
Anil Kumar Kewat | 2025-07 | 16.07 | 37.5 | TB408 | 1 | <80
Anil Kumar Ramayan Departmental | 2025-06 | 41.47 | 0 |  | 0 | <80
Anil Kumar Ramayan Departmental | 2025-07 | 44.66 | 86.13 | TB401 | 1 | <80
Anil Kumar Rudra Const | 2025-08 | 37.93 | 37.93 | TA505 | 1 | <80
Anita Devi | 2025-10 | 150.52 | 72.24 | TA325 | 1 | 140-160
Anita Devi | 2025-11 | 128.98 | 84.3 | TA325 | 1 | 120-140
Anita Devi | 2025-12 | 18.92 | 141.87 | TA325 | 1 | <80
Anjani Enterprises | 2025-06 | 3.49 | 0 |  | 0 | <80
Anjani Enterprises | 2025-07 | 41.92 | 45.41 | TB401 | 1 | <80
Anjani Power Priyanka Devi Sudheer | 2025-07 | 0.85 | 0 |  | 0 | <80
Anjani Power Priyanka Devi Sudheer | 2025-08 | 13.23 | 0 |  | 0 | <80
Anjani Power Priyanka Devi Sudheer | 2025-09 | 12.81 | 0 |  | 0 | <80
Anjani Power Priyanka Devi Sudheer | 2025-10 | 11.95 | 38.85 | TB401 | 1 | <80
Anjum | 2025-10 | 23.6 | 0 |  | 0 | <80
Anjum | 2025-11 | 70.81 | 94.41 | TA325 | 1 | <80
Anjum Construction | 2025-11 | 3.24 | 0 |  | 0 | <80
Anjum Construction | 2025-12 | 85.4 | 84.3 | TA414 | 1 | 80-100
Anjum Construction | 2026-01 | 30.36 | 34.7 | TA414 | 1 | <80
Annaya Traders | 2025-04 | 6.25 | 0 |  | 0 | <80
Annaya Traders | 2025-05 | 31.25 | 37.5 | TB401 | 1 | <80
Anvi Construction | 2025-08 | 18.28 | 0 |  | 0 | <80
Anvi Construction | 2025-09 | 20.57 | 38.85 | TB408 | 1 | <80
Arawali | 2025-08 | 45.41 | 45.41 | TB401 | 1 | <80
Arawali 1 | 2025-07 | 66.99 | 0 |  | 0 | <80
Arawali 1 | 2025-08 | 19.14 | 86.13 | TB408 | 1 | <80
Arawali 2 | 2025-07 | 113.86 | 113.86 | TB408 | 3 | 100-120
Arawali Infra 1 | 2025-07 | 37.5 | 37.5 | TB401 | 1 | <80
Arawali Infra 2 | 2025-06 | 46.38 | 0 |  | 0 | <80
Arawali Infra 2 | 2025-07 | 144.98 | 191.36 | TB401 | 3 | 140-160
Arawali Infra 2 | 2025-08 | 38.85 | 38.85 | TB401 | 1 | <80
Asc Heights | 2024-12 | 33.49 | 0 |  | 0 | <80
Asc Heights | 2025-01 | 178.81 | 178.25 | TA416 | 4 | 160-180
Asc Heights | 2025-02 | 164.03 | 198.08 | TA416 | 4 | 160-180
Asc Heights | 2025-03 | 174.57 | 174.57 | TA416 | 4 | 160-180
Asc Heights | 2025-04 | 178.01 | 171.76 | TA416 | 3 | 160-180
Asc Heights | 2025-05 | 158.14 | 128.52 | TA416 | 3 | 140-160
Asc Heights | 2025-06 | 134.46 | 143.46 | TA416 | 1 | 120-140
Asc Heights | 2025-07 | 19.19 | 46.05 | TA416 | 1 | <80
Ashok | 2024-10 | 72.74 | 72.74 | TA421 | 2 | <80
Ashok | 2024-11 | 92.59 | 92.59 | TA421 | 2 | 80-100
Ashok Kumar | 2024-09 | 36.37 | 36.37 | TA421 | 1 | <80
Ashokkumar | 2024-10 | 13.64 | 0 |  | 0 | <80
Ashokkumar | 2024-11 | 22.73 | 36.37 | TA421 | 1 | <80
Ayansh Const | 2025-08 | 4.28 | 0 |  | 0 | <80
Ayansh Const | 2025-09 | 30 | 34.29 | TB507 | 3 | <80
Balaji Tour Travels 2 | 2025-12 | 12 | 12 | TB507 | 1 | <80
Bambole Traders | 2025-07 | 36 | 0 |  | 0 | <80
Bambole Traders | 2025-08 | 9.69 | 45.7 | TA413 | 1 | <80
Barkat Ali | 2024-09 | 36.04 | 36.04 | TA325 | 1 | <80
Barkat Ali | 2024-11 | 24.85 | 0 |  | 0 | <80
Barkat Ali | 2024-12 | 84.14 | 99.55 | TA325 | 2 | 80-100
Barkat Ali | 2025-01 | 193.44 | 132.14 | TA325 | 2 | 180-200
Barkat Ali | 2025-02 | 55.76 | 113.18 | TA325 | 2 | <80
Barkat Ali | 2025-03 | 103.5 | 73.78 | TA325 | 2 | 100-120
Barkat Ali | 2025-04 | 163.72 | 200.96 | TA325 | 5 | 160-180
Barkat Ali | 2025-05 | 69.66 | 75.46 | TA325 | 2 | <80
Barkat Ali Mithun Kumar Vntl | 2025-07 | 3.73 | 0 |  | 0 | <80
Barkat Ali Mithun Kumar Vntl | 2025-08 | 12.85 | 0 |  | 0 | <80
Barkat Ali Mithun Kumar Vntl | 2025-09 | 12.44 | 0 |  | 0 | <80
Barkat Ali Mithun Kumar Vntl | 2025-10 | 8.71 | 37.73 | TA325 | 1 | <80
Bhagwan Construction | 2024-09 | 98.04 | 79.96 | TA413 | 2 | 80-100
Bhagwan Construction | 2024-10 | 181.67 | 199.75 | TA413 | 5 | 180-200
Bhairaw Mahto | 2025-08 | 18.82 | 0 |  | 0 | <80
Bhairaw Mahto | 2025-09 | 112.23 | 112.48 | TA413 | 2 | 100-120
Bhairaw Mahto | 2025-10 | 113.52 | 109.29 | TA413 | 2 | 100-120
Bhairaw Mahto | 2025-11 | 74.08 | 96.88 | TA413 | 1 | <80
Bhairo Mahato | 2025-03 | 5.35 | 0 |  | 0 | <80
Bhairo Mahato | 2025-04 | 8.03 | 0 |  | 0 | <80
Bhairo Mahato | 2025-05 | 23.38 | 0 |  | 0 | <80
Bhairo Mahato | 2025-06 | 29.58 | 0 |  | 0 | <80
Bhairo Mahato | 2025-07 | 30.57 | 0 |  | 0 | <80
Bhairo Mahato | 2025-08 | 30.57 | 0 |  | 0 | <80
Bhairo Mahato | 2025-09 | 29.58 | 0 |  | 0 | <80
Bhairo Mahato | 2025-10 | 30.57 | 0 |  | 0 | <80
Bhairo Mahato | 2025-11 | 29.58 | 0 |  | 0 | <80
Bhairo Mahato | 2025-12 | 102.62 | 319.85 | TA419 | 3 | 100-120
Bhairo Mahto | 2025-05 | 25.9 | 0 |  | 0 | <80
Bhairo Mahto | 2025-06 | 50.45 | 76.35 | TB408 | 2 | <80
Bhairo Mahto | 2025-07 | 19.53 | 0 |  | 0 | <80
Bhairo Mahto | 2025-08 | 94.32 | 113.86 | TB408 | 3 | 80-100
Bhairo Mahto | 2025-09 | 77.69 | 77.69 | TB401, TB408 | 2 | <80
Bhairo Mahto Departmental | 2025-05 | 66.29 | 0 |  | 0 | <80
Bhairo Mahto Departmental | 2025-06 | 55.47 | 121.76 | TB401 | 3 | <80
Bhairo Mahto Departmental Arawali | 2025-07 | 56.09 | 0 |  | 0 | <80
Bhairo Mahto Departmental Arawali | 2025-08 | 44.87 | 100.96 | TB401 | 1 | <80
Bhairo Mahto Kewat | 2025-07 | 85.35 | 37.5 | TB408 | 1 | 80-100
Bhairo Mahto Kewat | 2025-08 | 38.28 | 86.13 | TB408 | 1 | <80
Bhairo Mahto Priyanka Devi Subodh | 2025-07 | 86.13 | 86.13 | TB408 | 1 | 80-100
Bhoi Enterprises | 2025-08 | 2.23 | 0 |  | 0 | <80
Bhoi Enterprises | 2025-09 | 35.24 | 34.29 | TB507 | 3 | <80
Bhoi Enterprises | 2025-10 | 73.81 | 76.99 | TB507 | 6 | <80
Bhoi Enterprises | 2025-11 | 85.19 | 76.58 | TB507 | 6 | 80-100
Bhoi Enterprises | 2025-12 | 56.84 | 65.45 | TB507 | 4 | <80
Bhuvneshwar | 2024-05 | 8.04 | 0 |  | 0 | <80
Bhuvneshwar | 2024-06 | 66.97 | 75.01 | TB408 | 2 | <80
Bhuvneshwar | 2024-07 | 77.7 | 77.7 | TB408 | 2 | <80
Bina Devi | 2024-09 | 72.32 | 47.18 | TB401 | 1 | <80
Bina Devi | 2024-10 | 127.57 | 152.7 | TB401, TB408 | 4 | 120-140
Bina Devi | 2024-11 | 135.29 | 135.29 | TB401, TB408 | 3 | 120-140
Bina Devi | 2024-12 | 75.01 | 75.01 | TB401 | 2 | <80
Bina Devi | 2025-01 | 81.82 | 77.7 | TB408 | 2 | 80-100
Bina Devi | 2025-02 | 116.29 | 120.42 | TB408 | 3 | 100-120
Bina Devi | 2025-03 | 82.92 | 82.92 | TB401 | 2 | 80-100
Binod Mahto | 2025-04 | 4.54 | 0 |  | 0 | <80
Binod Mahto | 2025-05 | 7.41 | 0 |  | 0 | <80
Binod Mahto | 2025-06 | 7.17 | 0 |  | 0 | <80
Binod Mahto | 2025-07 | 2.87 | 22 | TA506 | 1 | <80
Binod Mahto | 2025-10 | 51.29 | 22 | TA506 | 1 | <80
Binod Mahto | 2025-11 | 50.71 | 80 | TA506 | 2 | <80
Binod Mahto | 2025-12 | 22 | 22 | TA506 | 1 | <80
Chahanur Bibi | 2024-08 | 2.9 | 0 |  | 0 | <80
Chahanur Bibi | 2024-09 | 29.02 | 0 |  | 0 | <80
Chahanur Bibi | 2024-10 | 5.8 | 37.73 | TA325 | 1 | <80
Chinta Devi | 2023-11 | 100.91 | 75.01 | TB401 | 2 | 100-120
Chinta Devi | 2023-12 | 223.85 | 233.08 | TB401 | 6 | 220-240
Chinta Devi | 2024-01 | 211.88 | 198.54 | TB401 | 5 | 200-220
Chinta Devi | 2024-02 | 218.88 | 243.53 | TB401, TB408 | 6 | 200-220
Chinta Devi | 2024-03 | 228.51 | 226.37 | TB408 | 6 | 220-240
Chinta Devi | 2024-04 | 222.89 | 208.96 | TB408 | 5 | 220-240
Chinta Devi | 2024-05 | 16.07 | 37.5 | TB408 | 1 | <80
Chinta Devi | 2024-08 | 15 | 0 |  | 0 | <80
Chinta Devi | 2024-09 | 189.69 | 170.11 | TB401 | 4 | 180-200
Chinta Devi | 2024-10 | 265.4 | 262.25 | TB401, TB408 | 6 | >=260
Chinta Devi | 2024-11 | 278.79 | 316.53 | TB401, TB408 | 7 | >=260
Chinta Devi | 2024-12 | 284.77 | 284.77 | TB401, TB408 | 5 | >=260
Chinta Devi | 2025-01 | 218.6 | 192.7 | TB408 | 4 | 200-220
Chinta Devi | 2025-02 | 235.58 | 230.4 | TB408 | 6 | 220-240
Chinta Devi | 2025-03 | 237.59 | 260.9 | TB408 | 6 | 220-240
Chinta Devi | 2025-04 | 211.02 | 192.89 | TB401, TB408 | 5 | 200-220
Chinta Devi | 2025-05 | 12.95 | 38.85 | TB408 | 1 | <80
Chinta Devi | 2025-08 | 84.69 | 84.69 | TB408 | 2 | 80-100
Chinta Devi | 2025-09 | 196.81 | 182.45 | TB408 | 2 | 180-200
Chinta Devi | 2025-10 | 247.17 | 237.82 | TB408 | 2 | 240-260
Chinta Devi | 2025-11 | 257.04 | 280.74 | TB401, TB408 | 6 | 240-260
Chinta Devi | 2025-12 | 204.38 | 171.45 | TB408 | 4 | 200-220
Chinta Devi | 2026-01 | 51.34 | 84.26 | TB408 | 2 | <80
Chitra Construction | 2025-04 | 2.87 | 0 |  | 0 | <80
Chitra Construction | 2025-05 | 4.68 | 0 |  | 0 | <80
Chitra Construction | 2025-06 | 4.53 | 0 |  | 0 | <80
Chitra Construction | 2025-07 | 4.68 | 0 |  | 0 | <80
Chitra Construction | 2025-08 | 4.68 | 0 |  | 0 | <80
Chitra Construction | 2025-09 | 4.53 | 0 |  | 0 | <80
Chitra Construction | 2025-10 | 4.68 | 0 |  | 0 | <80
Chitra Construction | 2025-11 | 42.26 | 37.73 | TA325 | 1 | <80
Chitra Construction | 2025-12 | 2.87 | 38.04 | TA414 | 1 | <80
Crane Erc Team Mp | 2025-10 | 14.14 | 0 |  | 0 | <80
Crane Erc Team Mp | 2025-11 | 102.01 | 107.11 | TA505 | 3 | 100-120
Crane Erc Team Mp | 2025-12 | 163.56 | 168.38 | TA505 | 4 | 160-180
Crane Erc Team Mp | 2026-01 | 33.72 | 37.93 | TA505 | 1 | <80
D K Verma | 2025-07 | 88.51 | 75.86 | TA421 | 2 | 80-100
D K Verma | 2025-08 | 149.56 | 162.21 | TA421 | 4 | 140-160
D K Verma | 2025-09 | 182.59 | 182.59 | TA421 | 4 | 180-200
D K Verma | 2025-10 | 182.41 | 153.96 | TA421 | 4 | 180-200
D K Verma | 2025-11 | 185.05 | 213.5 | TA421 | 5 | 180-200
D K Verma | 2025-12 | 154.43 | 130.85 | TA421 | 2 | 140-160
D K Verma | 2026-01 | 14.14 | 37.72 | TA421 | 1 | <80
Daulat Mahto | 2024-11 | 70.81 | 0 |  | 0 | <80
Daulat Mahto | 2024-12 | 75.05 | 132.14 | TA325 | 2 | <80
Daulat Mahto | 2025-01 | 118.48 | 120.19 | TA325 | 3 | 100-120
Daulat Mahto | 2025-02 | 135.11 | 136.34 | TA325 | 3 | 120-140
Daulat Mahto | 2025-03 | 102.45 | 113.23 | TA325 | 3 | 100-120
Daulat Mahto | 2025-04 | 55.87 | 37.73 | TA325 | 1 | <80
Daulat Mahto | 2025-05 | 36.28 | 54.42 | TA325 | 1 | <80
Deglal Mahato | 2025-08 | 33.63 | 0 |  | 0 | <80
Deglal Mahato | 2025-09 | 209.89 | 188.14 | TA505 | 3 | 200-220
Deglal Mahato | 2025-10 | 241.01 | 296.39 | TA505 | 4 | 240-260
Deglal Mahato | 2025-11 | 150.01 | 121.56 | TA505 | 3 | 140-160
Deglal Mahato | 2025-12 | 213.99 | 173.03 | TA505 | 3 | 200-220
Deglal Mahato | 2026-01 | 98.71 | 168.12 | TA505 | 3 | 80-100
Deglal Mahato Mp | 2025-09 | 76.34 | 72.32 | TA505 | 2 | <80
Deglal Mahato Mp | 2025-10 | 145.15 | 144.08 | TA505 | 4 | 140-160
Deglal Mahato Mp | 2025-11 | 154.12 | 144.08 | TA505 | 4 | 140-160
Deglal Mahato Mp | 2025-12 | 163.04 | 157.5 | TA505 | 3 | 160-180
Deglal Mahato Mp | 2026-01 | 94.09 | 114.75 | TA505 | 3 | 80-100
Deglal Mahto | 2024-08 | 9.71 | 0 |  | 0 | <80
Deglal Mahto | 2024-09 | 199.92 | 190.21 | TB401, TB408 | 5 | 180-200
Deglal Mahto | 2024-10 | 201.49 | 209.11 | TB401, TB408 | 4 | 200-220
Deglal Mahto | 2024-11 | 186.75 | 198.54 | TB401, TB408 | 5 | 180-200
Deglal Mahto | 2024-12 | 146.49 | 121.76 | TB401, TB408 | 3 | 140-160
Deglal Mahto | 2025-01 | 14.13 | 38.85 | TB408 | 1 | <80
Departmental Gang | 2024-05 | 30.88 | 0 |  | 0 | <80
Departmental Gang | 2024-06 | 76.09 | 84.26 | TB401 | 2 | <80
Departmental Gang | 2024-07 | 139 | 120.42 | TB401 | 3 | 120-140
Departmental Gang | 2024-08 | 4.13 | 45.41 | TB401 | 1 | <80
Devi Construction | 2025-10 | 131.81 | 84.69 | TB401, TB408 | 2 | 120-140
Devi Construction | 2025-11 | 169.04 | 216.16 | TB408 | 3 | 160-180
Devi Construction | 2025-12 | 167.96 | 167.96 | TB408 | 2 | 160-180
Devine | 2025-06 | 42.37 | 42.37 | TA416 | 1 | <80
Dewi Construction Girendra | 2024-09 | 87.55 | 87.55 | TA416 | 2 | 80-100
Dewi Construction Girendra | 2024-10 | 222.02 | 222.02 | TA416 | 5 | 220-240
Dewi Construction Girendra | 2024-11 | 239.08 | 226.57 | TA416 | 5 | 220-240
Dewi Construction Girendra | 2024-12 | 204.97 | 217.48 | TA416 | 5 | 200-220
Dewi Construction Girendra | 2025-01 | 192.81 | 179.65 | TA416 | 4 | 180-200
Dewi Construction Girendra | 2025-02 | 217.1 | 202.63 | TA416 | 4 | 200-220
Dewi Construction Girendra | 2025-03 | 256.07 | 283.7 | TA416 | 6 | 240-260
Dewi Construction Girendra | 2025-04 | 193.85 | 175.43 | TA416 | 3 | 180-200
Dewi Construction Girendra | 2025-05 | 216.33 | 220.62 | TA416 | 5 | 200-220
Dewi Construction Girendra | 2025-06 | 28.25 | 42.37 | TA416 | 1 | <80
Dhaneshwar | 2025-06 | 98.74 | 0 |  | 0 | 80-100
Dhaneshwar | 2025-07 | 127.86 | 0 |  | 0 | 120-140
Dhaneshwar | 2025-08 | 85.74 | 173.13 | TA325 | 1 | 80-100
Dhaneshwar | 2025-09 | 33.91 | 173.13 | TA325 | 1 | <80
Dhaneshwar Mahto Modina India 4 Prayag Rupesh Kumar | 2025-10 | 29.12 | 0 |  | 0 | <80
Dhaneshwar Mahto Modina India 4 Prayag Rupesh Kumar | 2025-11 | 67.21 | 0 |  | 0 | <80
Dhaneshwar Mahto Modina India 4 Prayag Rupesh Kumar | 2025-12 | 60.49 | 156.83 | TA325 | 1 | <80
Dhaneswar Mahto | 2024-09 | 112.42 | 112.42 | TA325 | 1 | 100-120
Dhaneswar Mahto | 2024-10 | 67.07 | 0 |  | 0 | <80
Dhaneswar Mahto | 2024-11 | 169.33 | 221.98 | TA325 | 4 | 160-180
Dhaneswar Mahto | 2024-12 | 204.66 | 183.38 | TA325 | 3 | 200-220
Dhaneswar Mahto | 2025-01 | 176.5 | 193.34 | TA325 | 4 | 160-180
Dhaneswar Mahto | 2025-02 | 256.09 | 223.35 | TA325 | 4 | 240-260
Dhaneswar Mahto | 2025-03 | 248.82 | 300.41 | TA325 | 3 | 240-260
Dhaneswar Mahto | 2025-04 | 121.76 | 37.73 | TA325 | 1 | 120-140
Dhaneswar Mahto | 2025-05 | 76.51 | 160.54 | TA325 | 2 | <80
Dharmendra Munnilal Pusplata | 2025-07 | 38.85 | 38.85 | TB408 | 1 | <80
Dhruv Enterprises | 2025-08 | 6.08 | 0 |  | 0 | <80
Dhruv Enterprises | 2025-09 | 9.12 | 0 |  | 0 | <80
Dhruv Enterprises | 2025-10 | 9.42 | 0 |  | 0 | <80
Dhruv Enterprises | 2025-11 | 57.95 | 0 |  | 0 | <80
Dhruv Enterprises | 2025-12 | 33.84 | 73.24 | TA419 | 1 | <80
Dhruv Enterprises | 2026-01 | 0.61 | 43.78 | TA419 | 1 | <80
Dildar Electrical 2 4 Pgcil | 2025-10 | 9.7 | 0 |  | 0 | <80
Dildar Electrical 2 4 Pgcil | 2025-11 | 97.01 | 0 |  | 0 | 80-100
Dildar Electrical 2 4 Pgcil | 2025-12 | 22.63 | 129.34 | TA325 | 1 | <80
Dildar Electrical 2 Pgcil | 2025-10 | 39.46 | 39.46 | TA325 | 1 | <80
Dildar Electrical 3 | 2025-10 | 37.73 | 37.73 | TA325 | 1 | <80
Dildar Electricals | 2025-03 | 3.13 | 0 |  | 0 | <80
Dildar Electricals | 2025-04 | 5.22 | 0 |  | 0 | <80
Dildar Electricals | 2025-05 | 5.4 | 0 |  | 0 | <80
Dildar Electricals | 2025-06 | 5.22 | 0 |  | 0 | <80
Dildar Electricals | 2025-07 | 5.4 | 0 |  | 0 | <80
Dildar Electricals | 2025-08 | 5.4 | 0 |  | 0 | <80
Dildar Electricals | 2025-09 | 5.22 | 0 |  | 0 | <80
Dildar Electricals | 2025-10 | 1.04 | 36.04 | TA325 | 1 | <80
Dildar Electricals 1 Pgcil | 2025-10 | 39.46 | 39.46 | TA325 | 1 | <80
Dildar Electricals 1 Pgcil | 2025-11 | 37.73 | 37.73 | TA325 | 1 | <80
Dildar Electricals 1 Pgcil Prayag Mahto Nasirudin 2 | 2025-11 | 3.73 | 0 |  | 0 | <80
Dildar Electricals 1 Pgcil Prayag Mahto Nasirudin 2 | 2025-12 | 115.75 | 0 |  | 0 | 100-120
Dildar Electricals 1 Pgcil Prayag Mahto Nasirudin 2 | 2026-01 | 37.34 | 156.83 | TA325 | 1 | <80
Dipak | 2025-06 | 19.2 | 12 | TB507 | 1 | <80
Dipak | 2025-07 | 97.35 | 104.55 | TB507 | 9 | 80-100
Dipak | 2025-08 | 95.73 | 95.73 | TB507 | 6 | 80-100
Dipak | 2025-09 | 83.95 | 81.27 | TB507 | 6 | 80-100
Dipak | 2025-10 | 95.85 | 83.05 | TB507 | 4 | 80-100
Dipak | 2025-11 | 74.71 | 85.37 | TB507 | 4 | <80
Dipak | 2025-12 | 16.86 | 21.67 | TB507 | 1 | <80
Dk Verma | 2024-09 | 13.54 | 0 |  | 0 | <80
Dk Verma | 2024-10 | 101.47 | 72.24 | TA325 | 1 | 100-120
Dk Verma | 2024-11 | 44.25 | 0 |  | 0 | <80
Dk Verma | 2024-12 | 126.39 | 181.29 | TA325 | 3 | 120-140
Dk Verma | 2025-01 | 214.29 | 228.28 | TA325 | 3 | 200-220
Dk Verma | 2025-02 | 176.65 | 131.61 | TA325 | 3 | 160-180
Dk Verma | 2025-03 | 203.49 | 197.58 | TA325 | 3 | 200-220
Dk Verma | 2025-04 | 147.86 | 190.14 | TA325 | 2 | 140-160
Dk Verma | 2025-05 | 156.44 | 127.03 | TA325 | 2 | 140-160
Dk Verma | 2025-06 | 141.96 | 112.42 | TA325 | 1 | 140-160
Dk Verma | 2025-07 | 32.77 | 80.41 | TA325 | 1 | <80
Dk Verma | 2025-08 | 19.37 | 0 |  | 0 | <80
Dk Verma | 2025-09 | 18.75 | 0 |  | 0 | <80
Dk Verma | 2025-10 | 19.37 | 0 |  | 0 | <80
Dk Verma | 2025-11 | 103.04 | 84.3 | TA325 | 1 | 100-120
Dk Verma | 2025-12 | 15 | 129.34 | TA325 | 1 | <80
Dudhnath | 2025-08 | 6.91 | 6.91 | TB501 | 1 | <80
Dudhnath Kumar | 2025-02 | 42.12 | 42.12 | TB501 | 8 | <80
Dudhnath Kumar | 2025-03 | 70.27 | 70.27 | TB501 | 12 | <80
Dudhnath Kumar | 2025-04 | 67.84 | 67.84 | TB501 | 10 | <80
Dudhnath Kumar | 2025-05 | 11.99 | 11.99 | TB501 | 1 | <80
Dudhnath Kumar | 2025-06 | 87.45 | 87.45 | TB501 | 12 | 80-100
Dudhnath Kumar | 2025-07 | 50.8 | 50.8 | TB501 | 6 | <80
Dudhnath Kumar | 2025-08 | 16.06 | 16.06 | TB501 | 2 | <80
Dular Chand Patel | 2025-11 | 37.5 | 37.5 | TB408 | 1 | <80
Eagle Enterprises | 2025-03 | 79.96 | 79.96 | TA505 | 2 | <80
Eagle Enterprises | 2025-04 | 34.79 | 34.79 | TA505 | 1 | <80
Eagle Enterprises Paramand | 2025-04 | 104.46 | 70.39 | TA505 | 2 | 100-120
Eagle Enterprises Paramand | 2025-05 | 109.1 | 119.67 | TA505 | 3 | 100-120
Eagle Enterprises Paramand | 2025-06 | 62.26 | 72.32 | TA505 | 2 | <80
Eagle Enterprises Paramand | 2025-07 | 32.26 | 45.7 | TA505 | 1 | <80
Enjamul Haque | 2025-10 | 30.29 | 0 |  | 0 | <80
Enjamul Haque | 2025-11 | 41.94 | 72.24 | TA325 | 1 | <80
Fatima | 2025-09 | 21 | 21 | TA506 | 1 | <80
Fatima 1 | 2025-06 | 3.86 | 0 |  | 0 | <80
Fatima 1 | 2025-07 | 5.44 | 0 |  | 0 | <80
Fatima 1 | 2025-08 | 5.44 | 0 |  | 0 | <80
Fatima 1 | 2025-09 | 5.26 | 0 |  | 0 | <80
Fatima 1 | 2025-10 | 5.44 | 0 |  | 0 | <80
Fatima 1 | 2025-11 | 1.58 | 27 | TA506 | 1 | <80
Fouzi Ratto | 2025-07 | 50.35 | 0 |  | 0 | <80
Fouzi Ratto | 2025-08 | 232.5 | 253.71 | TA413 | 5 | 220-240
Fouzi Ratto | 2025-09 | 196.73 | 220.42 | TA413 | 5 | 180-200
Fouzi Ratto | 2025-10 | 118.51 | 70.79 | TA413 | 1 | 100-120
Fouzi Ratto | 2025-11 | 71.78 | 124.95 | TA413 | 1 | <80
Gagan Enterprise 1 | 2025-03 | 4.71 | 0 |  | 0 | <80
Gagan Enterprise 1 | 2025-04 | 228.37 | 226.5 | TA416 | 5 | 220-240
Gagan Enterprise 1 | 2025-05 | 244.67 | 251.25 | TA416 | 5 | 240-260
Gagan Enterprise 1 | 2025-06 | 188.38 | 188.38 | TA416 | 1 | 180-200
Gagan Enterprise 1 | 2025-07 | 127.43 | 0 |  | 0 | 120-140
Gagan Enterprise 1 | 2025-08 | 149.72 | 188.38 | TA416 | 1 | 140-160
Gagan Enterprise 1 | 2025-09 | 8.88 | 97.65 | TA416 | 1 | <80
Gagan Enterprise 2 | 2025-04 | 196.91 | 196.91 | TA416 | 3 | 180-200
Gagan Enterprise 2 | 2025-05 | 84.75 | 84.75 | TA416 | 2 | 80-100
Gagan Enterprise 2 Kajol | 2025-08 | 46.05 | 46.05 | TA416 | 1 | <80
Gagan Enterprises | 2025-03 | 2.58 | 0 |  | 0 | <80
Gagan Enterprises | 2025-04 | 96.57 | 79.96 | TA419 | 2 | 80-100
Gagan Enterprises | 2025-05 | 63.95 | 83.13 | TA419 | 1 | <80
Ganesg Sinha | 2025-12 | 45.41 | 45.41 | TB401 | 1 | <80
Ganesh | 2024-05 | 111.79 | 111.79 | TB408 | 2 | 100-120
Ganesh | 2025-10 | 14.96 | 0 |  | 0 | <80
Ganesh | 2025-11 | 29.5 | 0 |  | 0 | <80
Ganesh | 2025-12 | 53.26 | 97.71 | TA419 | 2 | <80
Ganesh 1 | 2025-12 | 25.42 | 0 |  | 0 | <80
Ganesh 1 | 2026-01 | 16.95 | 42.37 | TA419 | 1 | <80
Ganesh 2 | 2025-11 | 11.51 | 0 |  | 0 | <80
Ganesh 2 | 2025-12 | 95.46 | 42.37 | TA419 | 1 | 80-100
Ganesh 2 | 2026-01 | 25.23 | 89.82 | TA419 | 2 | <80
Ganesh Const | 2024-02 | 180.57 | 176.64 | TB408 | 4 | 180-200
Ganesh Const | 2024-03 | 164.65 | 163.73 | TB408 | 4 | 160-180
Ganesh Const | 2024-04 | 79.4 | 84.26 | TB408 | 2 | <80
Ganesh Kr Sinha | 2023-09 | 12.5 | 0 |  | 0 | <80
Ganesh Kr Sinha | 2023-10 | 105.82 | 115.2 | TB401 | 3 | 100-120
Ganesh Kr Sinha | 2023-11 | 108.19 | 76.35 | TB401 | 2 | 100-120
Ganesh Kr Sinha | 2023-12 | 166.49 | 190.21 | TB401 | 5 | 160-180
Ganesh Kr Sinha | 2024-01 | 160.2 | 152.7 | TB401 | 3 | 160-180
Ganesh Kr Sinha | 2024-02 | 18.75 | 37.5 | TB401 | 1 | <80
Ganesh Kr Sinha | 2024-04 | 87.98 | 69.23 | TB401 | 1 | 80-100
Ganesh Kr Sinha | 2024-05 | 18.75 | 37.5 | TB401 | 1 | <80
Ganesh Kr Sinha | 2024-10 | 57.63 | 47.18 | TB401 | 1 | <80
Ganesh Kr Sinha | 2024-11 | 57.43 | 67.87 | TB401 | 1 | <80
Ganesh Kr Sinha | 2024-12 | 120.79 | 120.79 | TB401 | 2 | 120-140
Ganesh Kr Sinha | 2025-01 | 3.72 | 0 |  | 0 | <80
Ganesh Kr Sinha | 2025-02 | 124.58 | 128.3 | TB401 | 2 | 120-140
Ganesh Kr Sinha | 2025-04 | 6.06 | 0 |  | 0 | <80
Ganesh Kr Sinha | 2025-05 | 39.36 | 45.41 | TB401 | 1 | <80
Ganesh Sinha | 2024-08 | 9.83 | 0 |  | 0 | <80
Ganesh Sinha | 2024-09 | 82.77 | 92.6 | TB408 | 2 | 80-100
Ganesh Sinha | 2024-10 | 84.26 | 84.26 | TB408 | 2 | 80-100
Ganesh Sinha | 2024-11 | 66.61 | 47.18 | TB408 | 1 | <80
Ganesh Sinha | 2024-12 | 19.42 | 38.85 | TB408 | 1 | <80
Ganesh Sinha | 2025-01 | 123.11 | 123.11 | TB408 | 3 | 120-140
Ganesh Sinha | 2025-03 | 159.27 | 159.27 | TB408 | 4 | 140-160
Ganesh Sinha | 2025-04 | 117.89 | 117.89 | TB408 | 2 | 100-120
Ganesh Sinha | 2025-08 | 46.88 | 37.5 | TB408 | 1 | <80
Ganesh Sinha | 2025-09 | 139.72 | 140.51 | TB408 | 3 | 120-140
Ganesh Sinha | 2025-10 | 166.83 | 170.72 | TB401, TB408 | 4 | 160-180
Ganesh Sinha | 2025-11 | 183.46 | 188.15 | TB408 | 4 | 180-200
Ganesh Sinha | 2025-12 | 89.14 | 75.01 | TB408 | 2 | 80-100
Ganesh Sinha | 2026-01 | 24.72 | 38.85 | TB408 | 1 | <80
Gang 01 Sanjay | 2024-01 | 1.88 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-02 | 2.19 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-03 | 2.34 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-04 | 2.26 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-05 | 2.34 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-06 | 2.26 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-07 | 2.34 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-08 | 2.34 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-09 | 2.26 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-10 | 42.72 | 27.96 | TA418 | 1 | <80
Gang 01 Sanjay | 2024-11 | 124.97 | 111.84 | TA418 | 4 | 120-140
Gang 01 Sanjay | 2024-12 | 131.64 | 142.12 | TA418 | 5 | 120-140
Gang 01 Sanjay | 2025-01 | 108.14 | 140.92 | TA418 | 5 | 100-120
Gang 01 Sanjay | 2025-02 | 182.67 | 165 | TA418 | 5 | 180-200
Gang 01 Sanjay | 2025-03 | 67.5 | 90 | TA418 | 2 | <80
Gang 01 Sanjay | 2025-04 | 105.44 | 99 | TA418 | 2 | 100-120
Gang 01 Sanjay | 2025-05 | 100.76 | 91 | TA418 | 3 | 100-120
Gang 01 Sanjay | 2025-06 | 81.18 | 54 | TA418 | 2 | 80-100
Gang 01 Sanjay | 2025-07 | 3.62 | 47 | TA418 | 1 | <80
Gang 02 Sanjay | 2024-01 | 1.72 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-02 | 2.17 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-03 | 2.32 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-04 | 2.25 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-05 | 2.32 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-06 | 2.25 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-07 | 2.32 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-08 | 2.32 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-09 | 2.25 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-10 | 2.32 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-11 | 2.25 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-12 | 99.09 | 90.55 | TA418 | 3 | 80-100
Gang 02 Sanjay | 2025-01 | 85.86 | 84.92 | TA418 | 3 | 80-100
Gang 02 Sanjay | 2025-02 | 23.01 | 57 | TA418 | 2 | <80
Gang 02 Sanjay | 2025-03 | 201.4 | 179 | TA418 | 4 | 200-220
Gang 02 Sanjay | 2025-04 | 175.39 | 178 | TA418 | 5 | 160-180
Gang 02 Sanjay | 2025-05 | 123.84 | 134.63 | TA418 | 4 | 120-140
Gang 02 Sanjay | 2025-06 | 128 | 137 | TA418 | 4 | 120-140
Gang 02 Sanjay | 2025-07 | 54 | 54 | TA418 | 1 | <80
Gang 02 Sanjay Kec 02 Barkat Ali | 2025-07 | 16.57 | 0 |  | 0 | <80
Gang 02 Sanjay Kec 02 Barkat Ali | 2025-08 | 12.43 | 29 | TA418 | 1 | <80
Gauri Shankar | 2025-08 | 70.7 | 70.7 | TB408 | 1 | <80
Gauri Shankar Mahto | 2025-11 | 33.97 | 0 |  | 0 | <80
Gauri Shankar Mahto | 2025-12 | 118.56 | 139.83 | TA421 | 2 | 100-120
Gauri Shankar Mahto | 2026-01 | 80.81 | 93.51 | TA421 | 2 | 80-100
Ghanshyam Mahto | 2023-09 | 2.36 | 0 |  | 0 | <80
Ghanshyam Mahto | 2023-10 | 73.1 | 75.46 | TA325 | 2 | <80
Ghanshyam Mahto | 2023-11 | 110.29 | 75.46 | TA325 | 2 | 100-120
Ghanshyam Mahto | 2023-12 | 40.63 | 75.46 | TA325 | 2 | <80
Ghanshyam Mahto | 2024-07 | 18.87 | 0 |  | 0 | <80
Ghanshyam Mahto | 2024-08 | 24.01 | 37.73 | TA325 | 1 | <80
Ghanshyam Mahto | 2024-09 | 68.12 | 64.25 | TA325 | 1 | <80
Ghanshyam Mahto | 2024-10 | 45.9 | 36.04 | TA325 | 1 | <80
Ghanshyam Mahto | 2024-11 | 40.63 | 37.73 | TA325 | 1 | <80
Ghanshyam Mahto | 2024-12 | 80.76 | 97.93 | TA325 | 1 | 80-100
Ghanshyam Mahto | 2025-01 | 109.59 | 64.25 | TA325 | 1 | 100-120
Ghanshyam Mahto | 2025-02 | 75.27 | 125.19 | TA325 | 2 | <80
Ghyansham Mahto | 2025-03 | 8.82 | 0 |  | 0 | <80
Ghyansham Mahto | 2025-04 | 12.79 | 0 |  | 0 | <80
Ghyansham Mahto | 2025-05 | 13.22 | 0 |  | 0 | <80
Ghyansham Mahto | 2025-06 | 12.79 | 0 |  | 0 | <80
Ghyansham Mahto | 2025-07 | 13.22 | 0 |  | 0 | <80
Ghyansham Mahto | 2025-08 | 18.02 | 0 |  | 0 | <80
Ghyansham Mahto | 2025-09 | 48.79 | 0 |  | 0 | <80
Ghyansham Mahto | 2025-10 | 68.42 | 96 | TA504 | 2 | <80
Ghyansham Mahto | 2025-11 | 9.03 | 73 | TA504 | 1 | <80
Ghyansham Mahto | 2025-12 | 86.91 | 123 | TA504 | 2 | 80-100
Gokul 1 | 2025-10 | 46.62 | 46.62 | TA325 | 1 | <80
Gokul Rajwanshi | 2025-03 | 39.66 | 34.79 | TA505 | 1 | <80
Gokul Rajwanshi | 2025-04 | 113.03 | 117.9 | TA505 | 3 | 100-120
Gokul Rajwanshi | 2025-05 | 186.11 | 186.11 | TA505 | 5 | 180-200
Gokul Rajwanshi | 2025-06 | 149.54 | 149.54 | TA505 | 4 | 140-160
Gokul Rajwanshi | 2025-07 | 152.13 | 152.13 | TA505 | 4 | 140-160
Gokul Rajwanshi | 2025-08 | 153.76 | 108.04 | TA505 | 2 | 140-160
Gokul Rajwanshi | 2025-09 | 145.89 | 191.61 | TA505 | 4 | 140-160
Gokul Sarkar | 2025-08 | 15.92 | 11.14 | TB507 | 1 | <80
Gokul Sarkar | 2025-09 | 76.88 | 78.87 | TB507 | 7 | <80
Gokul Sarkar | 2025-10 | 98.63 | 87.4 | TB507 | 6 | 80-100
Gokul Sarkar | 2025-11 | 90.3 | 96 | TB507 | 4 | 80-100
Gokul Sarkar | 2025-12 | 68.53 | 76.84 | TB507 | 3 | <80
Gokul Sarkar | 2026-01 | 14.57 | 14.57 | TB507 | 1 | <80
Gokul Sarkar 1 | 2025-10 | 36.04 | 36.04 | TA325 | 1 | <80
Gokul Sarkar 1 | 2025-11 | 84.19 | 84.19 | TA325 | 2 | 80-100
Gokul Sarkar 2 | 2025-10 | 122.62 | 122.62 | TA325 | 2 | 120-140
Gokul Sarkar 2 | 2025-11 | 143.56 | 143.56 | TA325 | 2 | 140-160
Gokul Sarkar Mp | 2025-09 | 34.79 | 34.79 | TA505 | 1 | <80
Gokul Sarkar Mp | 2025-12 | 143.67 | 143.67 | TA505 | 4 | 140-160
Gokul Sarkar Mp | 2026-01 | 72.72 | 72.72 | TA505 | 2 | <80
Gokul Sarkar Mp 2 | 2025-12 | 119.75 | 107.11 | TA505 | 3 | 100-120
Gokul Sarkar Mp 2 | 2026-01 | 96.24 | 108.88 | TA505 | 3 | 80-100
Gouri Shankar | 2025-08 | 35.51 | 0 |  | 0 | <80
Gouri Shankar | 2025-09 | 140.82 | 176.33 | TA416 | 2 | 140-160
Gourishankar | 2024-06 | 148.46 | 118.86 | TA325 | 2 | 140-160
Gourishankar | 2024-07 | 136.72 | 156.42 | TA325 | 3 | 120-140
Gourishankar | 2024-08 | 108.79 | 118.67 | TA325 | 2 | 100-120
Gourishankar | 2024-09 | 108.28 | 108.28 | TA325 | 2 | 100-120
Gourishankar | 2024-10 | 212.93 | 212.93 | TA325 | 3 | 200-220
Gourishankar | 2024-11 | 123.1 | 56.86 | TA325 | 1 | 120-140
Gourishankar | 2024-12 | 227.68 | 238.64 | TA325 | 3 | 220-240
Gourishankar | 2025-01 | 182.9 | 192.83 | TA325 | 2 | 180-200
Gourishankar | 2025-02 | 217.98 | 221.18 | TA325 | 4 | 200-220
Gourishankar | 2025-03 | 228.88 | 271.03 | TA325 | 4 | 220-240
Gourishankar | 2025-04 | 237.22 | 174.82 | TA325 | 2 | 220-240
Gourishankar | 2025-05 | 176.99 | 207.28 | TA325 | 3 | 160-180
Gourishankar | 2025-06 | 99.79 | 126.66 | TA325 | 2 | 80-100
Gourishankar | 2025-07 | 183.8 | 189.04 | TB401 | 4 | 180-200
Gourishankar | 2025-08 | 47.18 | 47.18 | TB401 | 1 | <80
Govind Mahto | 2025-02 | 2.43 | 0 |  | 0 | <80
Govind Mahto | 2025-03 | 6.65 | 0 |  | 0 | <80
Govind Mahto | 2025-04 | 12.3 | 0 |  | 0 | <80
Govind Mahto | 2025-05 | 14.64 | 0 |  | 0 | <80
Govind Mahto | 2025-06 | 18.97 | 0 |  | 0 | <80
Govind Mahto | 2025-07 | 22.08 | 0 |  | 0 | <80
Govind Mahto | 2025-08 | 22.08 | 0 |  | 0 | <80
Govind Mahto | 2025-09 | 59.37 | 38 | TA506 | 2 | <80
Govind Mahto | 2025-10 | 60.75 | 81 | TA506 | 3 | <80
Govind Mahto | 2025-11 | 31.61 | 58 | TA506 | 2 | <80
Govind Mahto | 2025-12 | 21.11 | 95 | TA506 | 3 | <80
Govind Mahto 1 | 2025-08 | 59.04 | 43.8 | TA413 | 1 | <80
Govind Mahto 1 | 2025-09 | 137.11 | 133.3 | TA413 | 3 | 120-140
Govind Mahto 1 | 2025-10 | 146.15 | 154.58 | TA413 | 4 | 140-160
Govind Mahto 1 | 2025-11 | 137.11 | 147.72 | TA413 | 3 | 120-140
Govind Mahto 1 | 2025-12 | 36.16 | 36.16 | TA413 | 1 | <80
Govind Mahto 2 | 2025-08 | 21.33 | 0 |  | 0 | <80
Govind Mahto 2 | 2025-09 | 135.1 | 156.42 | TA413 | 3 | 120-140
Govind Mahto 2 | 2025-10 | 143.37 | 137.05 | TA413 | 1 | 140-160
Govind Mahto 2 | 2025-11 | 167.82 | 149.11 | TA413 | 3 | 160-180
Govind Mahto 2 | 2025-12 | 54.93 | 79.96 | TA413 | 2 | <80
Gowrishankar | 2025-11 | 37.93 | 37.93 | TA421 | 1 | <80
Gulab Mahto | 2025-01 | 3.12 | 0 |  | 0 | <80
Gulab Mahto | 2025-02 | 4.17 | 0 |  | 0 | <80
Gulab Mahto | 2025-03 | 4.61 | 0 |  | 0 | <80
Gulab Mahto | 2025-04 | 4.46 | 0 |  | 0 | <80
Gulab Mahto | 2025-05 | 7.39 | 18 | TA506 | 1 | <80
Gulab Mahto | 2025-06 | 8.23 | 0 |  | 0 | <80
Gulab Mahto | 2025-07 | 7.59 | 17 | TA506 | 1 | <80
Gulab Mahto | 2025-08 | 6.75 | 0 |  | 0 | <80
Gulab Mahto | 2025-09 | 6.53 | 0 |  | 0 | <80
Gulab Mahto | 2025-10 | 95.75 | 89 | TA506 | 5 | 80-100
Gulab Mahto | 2025-11 | 2.4 | 27 | TA506 | 1 | <80
Harsh Vivek | 2025-11 | 8.67 | 8.67 | TB501 | 2 | <80
Hassan | 2025-05 | 74.3 | 74.3 | TA421 | 2 | <80
Hassan | 2025-06 | 154.25 | 132.43 | TA421 | 3 | 140-160
Hassan | 2025-07 | 131.78 | 99.53 | TA421 | 2 | 120-140
Hassan | 2025-08 | 143.17 | 184.44 | TA421 | 3 | 140-160
Hassan | 2025-09 | 148.82 | 150.44 | TA421 | 3 | 140-160
Hassan | 2025-10 | 93.88 | 74.3 | TA421 | 2 | 80-100
Hassan | 2025-11 | 144.07 | 174.84 | TA421 | 3 | 140-160
Hassan 2 | 2025-06 | 22.13 | 0 |  | 0 | <80
Hassan 2 | 2025-07 | 118.96 | 141.08 | TA421 | 3 | 100-120
Hazarilal Yadav Poonam Kumari | 2025-07 | 76.35 | 76.35 | TB408 | 2 | <80
Horel Mahto | 2025-08 | 5.76 | 0 |  | 0 | <80
Horel Mahto | 2025-09 | 8.64 | 0 |  | 0 | <80
Horel Mahto | 2025-10 | 8.93 | 0 |  | 0 | <80
Horel Mahto | 2025-11 | 8.64 | 0 |  | 0 | <80
Horel Mahto | 2025-12 | 69.03 | 101 | TA504 | 2 | <80
Horil | 2025-09 | 95 | 95 | TA506 | 4 | 80-100
Horil Mahto | 2024-09 | 41.04 | 0 |  | 0 | <80
Horil Mahto | 2024-10 | 138.61 | 179.65 | TA416 | 4 | 120-140
Horil Mahto | 2024-11 | 103.04 | 92.1 | TA416 | 2 | 100-120
Horil Mahto | 2024-12 | 124.93 | 135.87 | TA416 | 3 | 120-140
Horil Mahto | 2025-01 | 107.83 | 92.1 | TA416 | 2 | 100-120
Horil Mahto | 2025-02 | 159.71 | 163.25 | TA416 | 3 | 140-160
Horil Mahto | 2025-03 | 137.45 | 129.93 | TA416 | 3 | 120-140
Horil Mahto | 2025-04 | 58.03 | 46.05 | TA416 | 1 | <80
Horil Mahto | 2025-05 | 12.38 | 0 |  | 0 | <80
Horil Mahto | 2025-06 | 6.96 | 32 | TA506 | 1 | <80
Horil Mahto | 2025-07 | 9.23 | 0 |  | 0 | <80
Horil Mahto | 2025-08 | 14.85 | 0 |  | 0 | <80
Horil Mahto | 2025-09 | 28.85 | 0 |  | 0 | <80
Horil Mahto | 2025-10 | 92.97 | 90 | TA506 | 4 | 80-100
Horil Mahto | 2025-11 | 80.95 | 105 | TA506 | 3 | 80-100
Horil Mahto | 2025-12 | 4.11 | 55 | TA506 | 2 | <80
Horil Mahto | 2026-01 | 22 | 22 | TA506 | 1 | <80
Imadul Haque | 2025-10 | 57.89 | 0 |  | 0 | <80
Imadul Haque | 2025-11 | 22.51 | 80.41 | TA325 | 1 | <80
Imadul Haque Enjamul Haque | 2025-11 | 56.86 | 56.86 | TA325 | 1 | <80
Infinedea 1 | 2025-04 | 2.73 | 0 |  | 0 | <80
Infinedea 1 | 2025-05 | 4.45 | 0 |  | 0 | <80
Infinedea 1 | 2025-06 | 4.3 | 0 |  | 0 | <80
Infinedea 1 | 2025-07 | 4.45 | 0 |  | 0 | <80
Infinedea 1 | 2025-08 | 4.45 | 0 |  | 0 | <80
Infinedea 1 | 2025-09 | 4.3 | 0 |  | 0 | <80
Infinedea 1 | 2025-10 | 4.45 | 0 |  | 0 | <80
Infinedea 1 | 2025-11 | 4.3 | 0 |  | 0 | <80
Infinedea 1 | 2025-12 | 2.73 | 36.16 | TA419 | 1 | <80
Infinidea | 2025-01 | 5.39 | 0 |  | 0 | <80
Infinidea | 2025-02 | 6.29 | 0 |  | 0 | <80
Infinidea | 2025-03 | 6.96 | 0 |  | 0 | <80
Infinidea | 2025-04 | 6.74 | 0 |  | 0 | <80
Infinidea | 2025-05 | 6.96 | 0 |  | 0 | <80
Infinidea | 2025-06 | 6.74 | 0 |  | 0 | <80
Infinidea | 2025-07 | 9.74 | 0 |  | 0 | <80
Infinidea | 2025-08 | 71.8 | 36.16 | TA419 | 1 | <80
Infinidea | 2025-09 | 24.6 | 95.89 | TA419 | 2 | <80
Infinidea | 2025-10 | 51.06 | 0 |  | 0 | <80
Infinidea | 2025-11 | 8.24 | 72.47 | TA419 | 1 | <80
Infinidea 2 | 2025-01 | 2.23 | 0 |  | 0 | <80
Infinidea 2 | 2025-02 | 3.12 | 0 |  | 0 | <80
Infinidea 2 | 2025-03 | 3.46 | 0 |  | 0 | <80
Infinidea 2 | 2025-04 | 3.35 | 0 |  | 0 | <80
Infinidea 2 | 2025-05 | 3.46 | 0 |  | 0 | <80
Infinidea 2 | 2025-06 | 3.35 | 0 |  | 0 | <80
Infinidea 2 | 2025-07 | 3.46 | 0 |  | 0 | <80
Infinidea 2 | 2025-08 | 3.46 | 0 |  | 0 | <80
Infinidea 2 | 2025-09 | 3.35 | 0 |  | 0 | <80
Infinidea 2 | 2025-10 | 3.46 | 0 |  | 0 | <80
Infinidea 2 | 2025-11 | 16.45 | 0 |  | 0 | <80
Infinidea 2 | 2025-12 | 22.49 | 37.14 | TA419 | 1 | <80
Infinidea 2 | 2026-01 | 3.45 | 37.93 | TA419 | 1 | <80
Intizer Infratech | 2024-05 | 78.89 | 75.46 | TA325 | 2 | <80
Intizer Infratech | 2024-06 | 34.3 | 37.73 | TA325 | 1 | <80
J Lngh | 2025-02 | 101.27 | 79.45 | TA421 | 2 | 100-120
J Lngh | 2025-03 | 161.59 | 183.41 | TA421 | 5 | 160-180
J Lngh O 1 | 2025-03 | 51.96 | 36.37 | TA421 | 1 | <80
J Lngh O 1 | 2025-04 | 162.77 | 178.36 | TA421 | 4 | 160-180
J Lngh O 1 | 2025-05 | 36.37 | 36.37 | TA421 | 1 | <80
J Lngh O 2 | 2025-03 | 48.32 | 37.93 | TA421 | 1 | <80
J Lngh O 2 | 2025-04 | 138.21 | 148.6 | TA421 | 4 | 120-140
Jagannaath Saw Mp | 2025-09 | 54.24 | 37.93 | TA505 | 1 | <80
Jagannaath Saw Mp | 2025-10 | 126.87 | 91.61 | TA505 | 2 | 120-140
Jagannaath Saw Mp | 2025-11 | 199.4 | 221.76 | TA505 | 4 | 180-200
Jagannaath Saw Mp | 2025-12 | 169.42 | 193.76 | TA505 | 5 | 160-180
Jagannaath Saw Mp | 2026-01 | 73.73 | 78.59 | TA505 | 2 | <80
Jagdish Mahto | 2024-08 | 15 | 0 |  | 0 | <80
Jagdish Mahto | 2024-09 | 224.48 | 230.4 | TB401, TB408 | 6 | 220-240
Jagdish Mahto | 2024-10 | 223.71 | 199.46 | TB401, TB408 | 5 | 220-240
Jagdish Mahto | 2024-11 | 223.11 | 251.65 | TB401, TB408 | 6 | 220-240
Jagdish Mahto | 2024-12 | 141.59 | 125.47 | TB401, TB408 | 2 | 140-160
Jagdish Mahto | 2025-01 | 17.93 | 38.85 | TB401 | 1 | <80
Jai Prakash Mahto | 2025-02 | 6.7 | 0 |  | 0 | <80
Jai Prakash Mahto | 2025-03 | 11.24 | 0 |  | 0 | <80
Jai Prakash Mahto | 2025-04 | 13.61 | 0 |  | 0 | <80
Jai Prakash Mahto | 2025-05 | 11.69 | 17 | TA506 | 1 | <80
Jai Prakash Mahto | 2025-06 | 9.3 | 0 |  | 0 | <80
Jai Prakash Mahto | 2025-07 | 9.61 | 0 |  | 0 | <80
Jai Prakash Mahto | 2025-08 | 9.61 | 0 |  | 0 | <80
Jai Prakash Mahto | 2025-09 | 3.24 | 58 | TA506 | 2 | <80
Jai Prakash Mahto | 2025-10 | 109 | 109 | TA506 | 3 | 100-120
Jai Prakash Mahto | 2025-11 | 73 | 73 | TA506 | 3 | <80
Jai Prakash Mahto | 2025-12 | 40 | 40 | TA506 | 1 | <80
Jai Prakash Mahto | 2026-01 | 27 | 27 | TA506 | 1 | <80
Jailal Ageria | 2024-08 | 12.5 | 0 |  | 0 | <80
Jailal Ageria | 2024-09 | 120.78 | 113.86 | TB401, TB408 | 3 | 120-140
Jailal Ageria | 2024-10 | 173.77 | 171.61 | TB401, TB408 | 3 | 160-180
Jailal Ageria | 2024-11 | 148.19 | 154.05 | TB401, TB408 | 4 | 140-160
Jailal Ageria | 2024-12 | 117.59 | 133.31 | TB401, TB408 | 2 | 100-120
Jaman Mahto 1 Ratna Devi | 2025-10 | 143.59 | 77.72 | TA325 | 1 | 140-160
Jaman Mahto 1 Ratna Devi | 2025-11 | 167.12 | 141.87 | TA325 | 1 | 160-180
Jaman Mahto 1 Ratna Devi | 2025-12 | 83.7 | 174.82 | TA325 | 2 | 80-100
Javir Hossen | 2025-10 | 57.79 | 0 |  | 0 | <80
Javir Hossen | 2025-11 | 22.61 | 80.41 | TA325 | 1 | <80
Javir Hossen Enjamul Haque | 2025-11 | 68.59 | 0 |  | 0 | <80
Javir Hossen Enjamul Haque | 2025-12 | 6.86 | 75.45 | TA325 | 1 | <80
Jawala Singh | 2025-08 | 37.5 | 37.5 | TB401 | 1 | <80
Jawala Singh Suraj | 2025-08 | 45.41 | 45.41 | TB401 | 1 | <80
Jay Prakash | 2025-09 | 100 | 100 | TA506 | 3 | 100-120
Jhemon Mahato 1 | 2025-08 | 36.62 | 0 |  | 0 | <80
Jhemon Mahato 1 | 2025-09 | 153.06 | 189.68 | TA505 | 3 | 140-160
Jhemon Mahato 1 | 2025-12 | 103.27 | 97.17 | TA505 | 1 | 100-120
Jhemon Mahato 1 | 2026-01 | 103.3 | 109.4 | TA505 | 2 | 100-120
Jhemon Mahato 2 | 2025-08 | 14.75 | 0 |  | 0 | <80
Jhemon Mahato 2 | 2025-09 | 97.23 | 74.09 | TA505 | 2 | 80-100
Jhemon Mahato 2 | 2025-10 | 135.53 | 123.2 | TA505 | 2 | 120-140
Jhemon Mahato 2 | 2025-11 | 121.52 | 171.75 | TA505 | 4 | 120-140
Jhemon Mahato 2 | 2025-12 | 75.28 | 75.28 | TA505 | 1 | <80
Jirwa Devi | 2024-09 | 58.36 | 45.41 | TB401 | 1 | <80
Jirwa Devi | 2024-10 | 106.84 | 86.03 | TB401 | 2 | 100-120
Jirwa Devi | 2024-11 | 106 | 113.86 | TB408 | 3 | 100-120
Jirwa Devi | 2024-12 | 128.09 | 142.73 | TB401, TB408 | 3 | 120-140
Jirwa Devi | 2025-01 | 132.93 | 133.95 | TB401 | 3 | 120-140
Jirwa Devi | 2025-02 | 112.48 | 106.73 | TB401 | 2 | 100-120
Jirwa Devi | 2025-03 | 53.25 | 69.23 | TB408 | 1 | <80
Jirwa Devi | 2025-08 | 47.18 | 47.18 | TB408 | 1 | <80
Jirwa Devi | 2025-09 | 140.9 | 138.01 | TB408 | 3 | 140-160
Jirwa Devi | 2025-10 | 120.88 | 82.92 | TB408 | 2 | 120-140
Jirwa Devi | 2025-11 | 148.84 | 170.27 | TB401, TB408 | 3 | 140-160
Jirwa Devi | 2025-12 | 128.25 | 135.29 | TB401, TB408 | 3 | 120-140
Jirwa Devi | 2026-01 | 33.03 | 45.41 | TB408 | 1 | <80
Jwala | 2024-11 | 55.88 | 37.73 | TA325 | 1 | <80
Jwala | 2024-12 | 186.49 | 195.65 | TA325 | 3 | 180-200
Jwala | 2025-01 | 245.99 | 242.4 | TA325 | 3 | 240-260
Jwala | 2025-02 | 171.87 | 184.44 | TA325 | 4 | 160-180
Jwala | 2025-03 | 254.25 | 185.32 | TA325 | 5 | 240-260
Jwala | 2025-04 | 176.56 | 245.48 | TA325 | 4 | 160-180
Jwala | 2025-05 | 138.29 | 138.29 | TA325 | 2 | 120-140
Jwala Singh | 2025-01 | 167.88 | 165.36 | TA505 | 4 | 160-180
Jwala Singh | 2025-02 | 261.63 | 258.28 | TA505 | 7 | >=260
Jwala Singh | 2025-03 | 311.65 | 293.48 | TA505 | 8 | >=260
Jwala Singh | 2025-04 | 279.46 | 283.8 | TA505 | 8 | >=260
Jwala Singh | 2025-05 | 237.36 | 229.48 | TA505 | 6 | 220-240
Jwala Singh | 2025-06 | 290.33 | 257.87 | TA505, TB408 | 6 | >=260
Jwala Singh | 2025-07 | 220.95 | 221.87 | TA505, TB408 | 5 | 220-240
Jwala Singh | 2025-08 | 437.14 | 375.02 | TA505, TB408 | 7 | >=260
Jwala Singh | 2025-09 | 243.78 | 289.69 | TA505, TB401, TB408 | 5 | 240-260
Jwala Singh | 2025-10 | 439.85 | 350.8 | TA325, TA419, TA505 | 5 | >=260
Jwala Singh | 2025-11 | 345.86 | 428.6 | TA325, TA419, TA505 | 9 | >=260
Jwala Singh | 2025-12 | 383.92 | 454.05 | TA419, TA505 | 12 | >=260
Jwala Singh | 2026-01 | 220.51 | 232.01 | TA419, TA505 | 3 | 220-240
Jwala Singh 01 | 2025-05 | 72.74 | 72.74 | TA421 | 2 | <80
Jwala Singh 1 | 2025-05 | 23.04 | 0 |  | 0 | <80
Jwala Singh 1 | 2025-06 | 117.48 | 140.51 | TB401 | 3 | 100-120
Jwala Singh 1 | 2025-07 | 84.54 | 45.7 | TA413 | 1 | 80-100
Jwala Singh 1 | 2025-08 | 196.41 | 218.83 | TA413 | 5 | 180-200
Jwala Singh 1 | 2025-09 | 248.3 | 240.67 | TA413, TB408 | 5 | 240-260
Jwala Singh 1 | 2025-10 | 116.98 | 110.09 | TA413 | 2 | 100-120
Jwala Singh 1 | 2025-11 | 127.63 | 147.62 | TA413 | 4 | 120-140
Jwala Singh 1 | 2025-12 | 132.55 | 116.12 | TA413 | 3 | 120-140
Jwala Singh 1 | 2026-01 | 51.22 | 78.59 | TA413 | 2 | <80
Jwala Singh 2 | 2025-03 | 9.48 | 0 |  | 0 | <80
Jwala Singh 2 | 2025-04 | 206.05 | 191.43 | TA505 | 5 | 200-220
Jwala Singh 2 | 2025-05 | 254.36 | 278.47 | TA505 | 7 | 240-260
Jwala Singh 2 | 2025-06 | 211.27 | 201.89 | TA505, TB401 | 5 | 200-220
Jwala Singh 2 | 2025-07 | 131.14 | 140.51 | TB401 | 3 | 120-140
Jwala Singh 2 | 2025-08 | 174.94 | 110.58 | TA413 | 2 | 160-180
Jwala Singh 2 | 2025-09 | 224.28 | 288.64 | TA413, TB408 | 6 | 220-240
Jwala Singh 2 | 2025-10 | 122.33 | 117.34 | TA413 | 3 | 120-140
Jwala Singh 2 | 2025-11 | 144.21 | 135.28 | TA413 | 3 | 140-160
Jwala Singh 2 | 2025-12 | 190.45 | 180.27 | TA413, TA505 | 4 | 180-200
Jwala Singh 2 | 2026-01 | 84.77 | 108.88 | TA505 | 3 | 80-100
Jwala Singh 3 | 2025-06 | 38.85 | 38.85 | TB401 | 1 | <80
Jwala Singh 3 | 2025-07 | 213.05 | 206.8 | TB401 | 3 | 200-220
Jwala Singh 3 | 2025-08 | 31.25 | 37.5 | TB401 | 1 | <80
Jwala Singh 3 Bhairo Mahto | 2025-08 | 35.68 | 0 |  | 0 | <80
Jwala Singh 3 Bhairo Mahto | 2025-09 | 50.96 | 0 |  | 0 | <80
Jwala Singh 3 Bhairo Mahto | 2025-10 | 42.47 | 129.11 | TB401 | 1 | <80
Jwala Singh Suraj Kumar | 2025-06 | 19.42 | 0 |  | 0 | <80
Jwala Singh Suraj Kumar | 2025-07 | 143.4 | 162.83 | TB408 | 3 | 140-160
Jyoti Const | 2025-08 | 39.58 | 0 |  | 0 | <80
Jyoti Const | 2025-09 | 120.55 | 160.13 | TA505 | 3 | 120-140
Jyoti Const | 2025-10 | 136.8 | 124.95 | TA505 | 1 | 120-140
Jyoti Const | 2025-11 | 87.96 | 81.74 | TA505 | 2 | 80-100
Jyoti Const | 2025-12 | 120.48 | 117.9 | TA505 | 3 | 120-140
Jyoti Const | 2026-01 | 92.58 | 113.24 | TA505 | 2 | 80-100
Kamlesh | 2025-10 | 70.7 | 70.7 | TB401 | 1 | <80
Kamlesh Kumar | 2025-10 | 11.16 | 0 |  | 0 | <80
Kamlesh Kumar | 2025-11 | 98.39 | 109.55 | TB408 | 2 | 80-100
Kamlesh Kumar | 2025-12 | 77.7 | 77.7 | TB408 | 2 | <80
Kamruddin | 2025-08 | 12.06 | 0 |  | 0 | <80
Kamruddin | 2025-09 | 60.31 | 0 |  | 0 | <80
Kamruddin | 2025-10 | 8.04 | 80.41 | TA325 | 1 | <80
Karam Mahto | 2025-04 | 3.35 | 0 |  | 0 | <80
Karam Mahto | 2025-05 | 5.19 | 0 |  | 0 | <80
Karam Mahto | 2025-06 | 5.02 | 0 |  | 0 | <80
Karam Mahto | 2025-07 | 5.19 | 0 |  | 0 | <80
Karam Mahto | 2025-08 | 10.16 | 0 |  | 0 | <80
Karam Mahto | 2025-09 | 36.06 | 36 | TA504 | 1 | <80
Karam Mahto | 2025-10 | 41.19 | 36 | TA504 | 1 | <80
Karam Mahto | 2025-11 | 1.84 | 36 | TA504 | 1 | <80
Karni Const 1 | 2025-01 | 9.56 | 0 |  | 0 | <80
Karni Const 1 | 2025-02 | 14.87 | 0 |  | 0 | <80
Karni Const 1 | 2025-03 | 12.64 | 16 | TA506 | 1 | <80
Karni Const 1 | 2025-04 | 10.19 | 16 | TA506 | 1 | <80
Karni Const 1 | 2025-05 | 10.25 | 0 |  | 0 | <80
Karni Const 1 | 2025-06 | 9.92 | 0 |  | 0 | <80
Karni Const 1 | 2025-07 | 6.37 | 17 | TA506 | 1 | <80
Karni Const 1 | 2025-08 | 8.59 | 0 |  | 0 | <80
Karni Const 1 | 2025-09 | 10.19 | 0 |  | 0 | <80
Karni Const 1 | 2025-10 | 26.53 | 16 | TA506 | 1 | <80
Karni Const 1 | 2025-11 | 69.1 | 115 | TA506 | 4 | <80
Karni Const 1 | 2025-12 | 25.78 | 34 | TA506 | 2 | <80
Karni Const 2 | 2025-01 | 6.6 | 0 |  | 0 | <80
Karni Const 2 | 2025-02 | 8.4 | 0 |  | 0 | <80
Karni Const 2 | 2025-03 | 7.69 | 18 | TA506 | 1 | <80
Karni Const 2 | 2025-04 | 10.81 | 0 |  | 0 | <80
Karni Const 2 | 2025-05 | 15.89 | 0 |  | 0 | <80
Karni Const 2 | 2025-06 | 16.92 | 0 |  | 0 | <80
Karni Const 2 | 2025-07 | 13.38 | 18 | TA506 | 1 | <80
Karni Const 2 | 2025-08 | 11.42 | 0 |  | 0 | <80
Karni Const 2 | 2025-09 | 8.44 | 18 | TA506 | 1 | <80
Karni Const 2 | 2025-10 | 50.46 | 96 | TA506 | 2 | <80
Karni Const 2 | 2025-11 | 64.32 | 43 | TA506 | 2 | <80
Karni Const 2 | 2025-12 | 52.68 | 74 | TA506 | 2 | <80
Karni Const 3 | 2025-01 | 3.07 | 0 |  | 0 | <80
Karni Const 3 | 2025-02 | 4.29 | 0 |  | 0 | <80
Karni Const 3 | 2025-03 | 4.75 | 0 |  | 0 | <80
Karni Const 3 | 2025-04 | 10.78 | 0 |  | 0 | <80
Karni Const 3 | 2025-05 | 17.47 | 0 |  | 0 | <80
Karni Const 3 | 2025-06 | 18.15 | 0 |  | 0 | <80
Karni Const 3 | 2025-07 | 18.76 | 0 |  | 0 | <80
Karni Const 3 | 2025-08 | 12.58 | 38 | TA506 | 1 | <80
Karni Const 3 | 2025-09 | 8.88 | 0 |  | 0 | <80
Karni Const 3 | 2025-10 | 110.75 | 154 | TA506 | 6 | 100-120
Karni Const 3 | 2025-11 | 70.43 | 72 | TA506 | 3 | <80
Karni Const 3 | 2025-12 | 5.09 | 21 | TA506 | 1 | <80
Karni Const 4 | 2025-02 | 2.19 | 0 |  | 0 | <80
Karni Const 4 | 2025-03 | 3.58 | 0 |  | 0 | <80
Karni Const 4 | 2025-04 | 3.46 | 0 |  | 0 | <80
Karni Const 4 | 2025-05 | 8.27 | 0 |  | 0 | <80
Karni Const 4 | 2025-06 | 10.16 | 0 |  | 0 | <80
Karni Const 4 | 2025-07 | 12.78 | 0 |  | 0 | <80
Karni Const 4 | 2025-08 | 26.81 | 21 | TA506 | 1 | <80
Karni Const 4 | 2025-09 | 32.14 | 0 |  | 0 | <80
Karni Const 4 | 2025-10 | 74.2 | 67 | TA506 | 2 | <80
Karni Const 4 | 2025-11 | 71.74 | 49 | TA506 | 2 | <80
Karni Const 4 | 2025-12 | 8.67 | 117 | TA506 | 3 | <80
Karni Const 5 | 2025-07 | 6.67 | 0 |  | 0 | <80
Karni Const 5 | 2025-08 | 9.84 | 0 |  | 0 | <80
Karni Const 5 | 2025-09 | 9.52 | 0 |  | 0 | <80
Karni Const 5 | 2025-10 | 100.84 | 91 | TA506 | 3 | 100-120
Karni Const 5 | 2025-11 | 20.13 | 56 | TA506 | 2 | <80
Karni Const 6 | 2025-01 | 2.32 | 0 |  | 0 | <80
Karni Const 6 | 2025-02 | 2.95 | 0 |  | 0 | <80
Karni Const 6 | 2025-03 | 3.26 | 0 |  | 0 | <80
Karni Const 6 | 2025-04 | 3.16 | 0 |  | 0 | <80
Karni Const 6 | 2025-05 | 3.26 | 0 |  | 0 | <80
Karni Const 6 | 2025-06 | 1.05 | 16 | TA506 | 1 | <80
Karni Const 6 | 2025-07 | 3.78 | 0 |  | 0 | <80
Karni Const 6 | 2025-08 | 5.33 | 0 |  | 0 | <80
Karni Const 6 | 2025-09 | 5.16 | 0 |  | 0 | <80
Karni Const 6 | 2025-10 | 1.72 | 16 | TA506 | 1 | <80
Karni Const 6 | 2025-11 | 55 | 55 | TA506 | 2 | <80
Kartik Mahto | 2025-09 | 116.27 | 112.48 | TA413 | 2 | 100-120
Kartik Mahto | 2025-10 | 125.19 | 128.98 | TA413 | 3 | 120-140
Kaushalya Const | 2024-09 | 56.24 | 47.18 | TB408 | 1 | <80
Kaushalya Const | 2024-10 | 57.33 | 66.38 | TB408 | 1 | <80
Kaushalya Const | 2024-11 | 45.41 | 45.41 | TB408 | 1 | <80
Kec 01 Barkat Ali | 2025-06 | 1.45 | 0 |  | 0 | <80
Kec 01 Barkat Ali | 2025-07 | 106.48 | 84 | TA418 | 3 | 100-120
Kec 01 Barkat Ali | 2025-08 | 70.89 | 91.63 | TA418 | 3 | <80
Kec 01 Barkat Ali | 2025-09 | 31.82 | 35 | TA418 | 1 | <80
Kec 02 Barkat Ali | 2025-07 | 116.2 | 116.2 | TA418 | 3 | 100-120
Kec 02 Barkat Ali | 2025-08 | 85.17 | 82 | TA418 | 2 | 80-100
Kec 02 Barkat Ali | 2025-09 | 140.67 | 114.7 | TA418 | 2 | 140-160
Kec 02 Barkat Ali | 2025-10 | 63.19 | 83 | TA418 | 3 | <80
Kec 02 Barkat Ali | 2025-11 | 98.07 | 85 | TA418 | 3 | 80-100
Kec 02 Barkat Ali | 2025-12 | 78.06 | 88 | TA418 | 3 | <80
Kec 02 Barkat Ali | 2026-01 | 41.54 | 54 | TA418 | 2 | <80
Kewat Departmental | 2025-05 | 3.57 | 0 |  | 0 | <80
Kewat Departmental | 2025-06 | 33.93 | 37.5 | TB401 | 1 | <80
Khatan | 2024-07 | 95.47 | 72.74 | TA421 | 2 | 80-100
Khatan | 2024-08 | 214.89 | 218.22 | TA421 | 6 | 200-220
Khatan | 2024-09 | 177 | 181.85 | TA421 | 5 | 160-180
Khatan | 2024-10 | 134.05 | 148.6 | TA421 | 4 | 120-140
Khatun | 2024-10 | 68.24 | 37.93 | TA421 | 1 | <80
Khatun | 2024-11 | 242.78 | 273.09 | TA421 | 6 | 240-260
Khatun | 2024-12 | 223.47 | 191.86 | TA421 | 5 | 220-240
Khatun | 2025-01 | 175.04 | 184.97 | TA421 | 5 | 160-180
Khatun | 2025-02 | 191.74 | 184.97 | TA421 | 5 | 180-200
Khatun | 2025-03 | 271.81 | 265.8 | TA421 | 6 | >=260
Khatun | 2025-04 | 316.35 | 331.85 | TA421 | 6 | >=260
Khatun | 2025-05 | 219.06 | 238.03 | TA421 | 4 | 200-220
Khatun | 2025-07 | 186.38 | 161.34 | TA421 | 5 | 180-200
Khatun | 2025-08 | 205.3 | 230.33 | TA421 | 6 | 200-220
Khatun | 2025-09 | 142.07 | 128.36 | TA421 | 2 | 140-160
Khatun | 2025-10 | 194.96 | 184.42 | TA421 | 5 | 180-200
Khatun | 2025-11 | 244.75 | 224.81 | TA421 | 5 | 240-260
Khatun | 2025-12 | 282.6 | 326.78 | TA421 | 6 | >=260
Khatun | 2026-01 | 33.38 | 33.38 | TA421 | 1 | <80
Khemlal | 2025-09 | 82 | 82 | TA506 | 4 | 80-100
Khemlal Mahto | 2025-02 | 6.34 | 0 |  | 0 | <80
Khemlal Mahto | 2025-03 | 11.24 | 0 |  | 0 | <80
Khemlal Mahto | 2025-04 | 10.88 | 0 |  | 0 | <80
Khemlal Mahto | 2025-05 | 10.22 | 17 | TA506 | 1 | <80
Khemlal Mahto | 2025-06 | 8.72 | 0 |  | 0 | <80
Khemlal Mahto | 2025-07 | 9.01 | 0 |  | 0 | <80
Khemlal Mahto | 2025-08 | 13.36 | 0 |  | 0 | <80
Khemlal Mahto | 2025-09 | 11.95 | 37 | TA506 | 1 | <80
Khemlal Mahto | 2025-10 | 48.59 | 40 | TA506 | 2 | <80
Khemlal Mahto | 2025-11 | 64.87 | 77 | TA506 | 3 | <80
Khemlal Mahto | 2025-12 | 62.12 | 52 | TA506 | 2 | <80
Khemlal Mahto | 2026-01 | 22.71 | 57 | TA506 | 2 | <80
Khublal Mahto | 2024-09 | 54.39 | 38.85 | TB401 | 1 | <80
Khublal Mahto | 2024-10 | 23.31 | 38.85 | TB408 | 1 | <80
Kongres Kumar 1 | 2025-07 | 29.34 | 0 |  | 0 | <80
Kongres Kumar 1 | 2025-08 | 151.58 | 161.36 | TA416 | 1 | 140-160
Kongres Kumar 1 | 2025-09 | 162.98 | 161.36 | TA416 | 1 | 160-180
Kongres Kumar 1 | 2025-10 | 21.19 | 42.37 | TA416 | 1 | <80
Kongres Kumar 2 | 2025-08 | 100.42 | 97.23 | TA416 | 1 | 100-120
Kongres Kumar 2 | 2025-09 | 70.23 | 73.43 | TA416 | 1 | <80
Kuduas Ali 2 | 2025-11 | 76.71 | 0 |  | 0 | <80
Kuduas Ali 2 | 2025-12 | 8.52 | 85.23 | TA325 | 1 | <80
Lakhan Singh | 2024-12 | 14.73 | 14.73 | TB501 | 3 | <80
Lalan Mahto | 2024-02 | 148.74 | 129.88 | TA325 | 3 | 140-160
Lalan Mahto | 2024-03 | 148.74 | 167.61 | TA325 | 4 | 140-160
Lalan Mahto | 2024-04 | 146.71 | 146.71 | TA325 | 3 | 140-160
Lalan Mahto | 2024-05 | 215.36 | 208.8 | TA325 | 5 | 200-220
Lalan Mahto | 2024-06 | 103.4 | 109.97 | TA325 | 2 | 100-120
Laxmi | 2025-11 | 37.5 | 37.5 | TB401 | 1 | <80
Laxmi | 2025-12 | 38.85 | 38.85 | TB401 | 1 | <80
M K Infra | 2025-03 | 46.05 | 46.05 | TA416 | 1 | <80
M K Infra | 2025-04 | 96.9 | 88.42 | TA416 | 2 | 80-100
M K Infra | 2025-05 | 32.84 | 0 |  | 0 | <80
M K Infra | 2025-06 | 47.11 | 88.42 | TA416 | 2 | <80
M S Company Gang | 2025-11 | 61.58 | 30.49 | TA512 | 1 | <80
M S Company Gang | 2025-12 | 143.31 | 55.13 | TA512 | 2 | 140-160
M S Company Gang | 2026-01 | 35.91 | 135.42 | TA512 | 3 | <80
M S Gauri Shankar | 2024-03 | 0.66 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-04 | 3.99 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-05 | 4.12 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-06 | 3.99 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-07 | 4.12 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-08 | 4.12 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-09 | 3.99 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-10 | 4.12 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-11 | 3.99 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-12 | 4.12 | 0 |  | 0 | <80
M S Gauri Shankar | 2025-01 | 0.53 | 37.73 | TA414 | 1 | <80
M S Govind Mahto | 2025-12 | 165.36 | 165.36 | TA512 | 4 | 160-180
M S Govind Mahto 2 | 2025-12 | 43.62 | 37.93 | TA512 | 1 | <80
M S Govind Mahto 2 | 2026-01 | 87.69 | 93.38 | TA512 | 2 | 80-100
M S Israul Hoque | 2025-02 | 7.33 | 0 |  | 0 | <80
M S Israul Hoque | 2025-03 | 11.36 | 0 |  | 0 | <80
M S Israul Hoque | 2025-04 | 10.99 | 0 |  | 0 | <80
M S Israul Hoque | 2025-05 | 11.36 | 0 |  | 0 | <80
M S Israul Hoque | 2025-06 | 10.99 | 0 |  | 0 | <80
M S Israul Hoque | 2025-07 | 11.36 | 0 |  | 0 | <80
M S Israul Hoque | 2025-08 | 11.36 | 0 |  | 0 | <80
M S Israul Hoque | 2025-09 | 5.5 | 80.24 | TA414 | 1 | <80
M S Jwala Singh | 2025-08 | 66.19 | 36.16 | TA512 | 1 | <80
M S Jwala Singh | 2025-09 | 192.04 | 203.29 | TA512 | 5 | 180-200
M S Jwala Singh | 2025-10 | 141.57 | 154.87 | TA512 | 3 | 140-160
M S Jwala Singh | 2025-11 | 161.54 | 167.01 | TA512 | 4 | 160-180
M S Jwala Singh | 2025-12 | 165.09 | 107.11 | TA512 | 3 | 160-180
M S Jwala Singh | 2026-01 | 60.19 | 118.17 | TA512 | 2 | <80
M S Jwala Singh 2 | 2025-11 | 66.04 | 45.7 | TA512 | 1 | <80
M S Jwala Singh 2 | 2025-12 | 167.62 | 183.23 | TA512 | 5 | 160-180
M S Jwala Singh 2 | 2026-01 | 33.19 | 37.93 | TA512 | 1 | <80
M S Karni Construction 1 | 2025-12 | 27.83 | 0 |  | 0 | <80
M S Karni Construction 1 | 2026-01 | 52.65 | 80.49 | TA512 | 2 | <80
M S Karni Construction 2 | 2025-12 | 31.29 | 0 |  | 0 | <80
M S Karni Construction 2 | 2026-01 | 47.31 | 78.59 | TA512 | 2 | <80
M S Kartik Mahto | 2025-10 | 141.24 | 141.24 | TA512 | 3 | 140-160
M S Kartik Mahto | 2025-11 | 284.78 | 270.18 | TA512 | 7 | >=260
M S Kartik Mahto | 2025-12 | 247.37 | 243.9 | TA512 | 6 | 240-260
M S Kartik Mahto | 2026-01 | 164.49 | 182.57 | TA512 | 5 | 160-180
M S Kavya Enterprises | 2025-07 | 18.04 | 0 |  | 0 | <80
M S Kavya Enterprises | 2025-08 | 122.46 | 117.9 | TA512 | 3 | 120-140
M S Kavya Enterprises | 2025-09 | 151.86 | 152.28 | TA512 | 4 | 140-160
M S Kavya Enterprises | 2025-10 | 83.23 | 93.38 | TA512 | 2 | 80-100
M S Kavya Enterprises | 2025-11 | 95.2 | 107.22 | TA512 | 3 | 80-100
M S Kavya Enterprises | 2025-12 | 31.95 | 31.96 | TA512 | 1 | <80
M S Mdpl | 2025-09 | 39.62 | 33.3 | TA418 | 1 | <80
M S Mdpl | 2025-10 | 85.33 | 60 | TA418 | 1 | 80-100
M S Mdpl | 2025-11 | 85.36 | 117 | TA418 | 2 | 80-100
M S Mdpl | 2025-12 | 144.86 | 141 | TA418 | 4 | 140-160
M S Mdpl | 2026-01 | 96.14 | 100 | TA418 | 2 | 80-100
M S Mgr | 2025-05 | 3.4 | 0 |  | 0 | <80
M S Mgr | 2025-06 | 51.01 | 54.41 | TA414 | 1 | <80
M S Mohika Costruction | 2026-01 | 18.97 | 18.97 | TA512 | 1 | <80
M S Punam Kumari | 2025-08 | 141.63 | 75.86 | TA512 | 2 | 140-160
M S Punam Kumari | 2025-09 | 283.39 | 302.24 | TA512 | 8 | >=260
M S Punam Kumari | 2025-10 | 152.71 | 199.63 | TA512 | 5 | 140-160
M S Punam Kumari 3 | 2025-11 | 31.03 | 0 |  | 0 | <80
M S Punam Kumari 3 | 2025-12 | 130.18 | 157.6 | TA512 | 4 | 120-140
M S Punam Kumari 3 | 2026-01 | 32.54 | 36.16 | TA512 | 1 | <80
M S Punam Kumari 4 | 2025-12 | 128.77 | 119.23 | TA512 | 3 | 120-140
M S Punam Kumari 4 | 2026-01 | 57.24 | 66.78 | TA512 | 1 | <80
M S Rahul | 2025-02 | 5.75 | 0 |  | 0 | <80
M S Rahul | 2025-03 | 7.75 | 0 |  | 0 | <80
M S Rahul | 2025-04 | 7.5 | 0 |  | 0 | <80
M S Rahul | 2025-05 | 7.75 | 0 |  | 0 | <80
M S Rahul | 2025-06 | 45.23 | 37.73 | TA414 | 1 | <80
M S Rahul | 2025-07 | 1.5 | 37.73 | TA414 | 1 | <80
M S Raju Kumar | 2026-01 | 78.59 | 78.59 | TA512 | 2 | <80
M S Sakkurddin | 2025-07 | 22.76 | 0 |  | 0 | <80
M S Sakkurddin | 2025-08 | 79.17 | 80.77 | TA414 | 2 | <80
M S Sakkurddin | 2025-09 | 16.56 | 37.73 | TA414 | 1 | <80
M S Sani Construction | 2026-01 | 35.6 | 35.6 | TA512 | 1 | <80
M S Shobha Debi | 2026-01 | 35.6 | 35.6 | TA512 | 1 | <80
M S Tofit | 2025-09 | 60.3 | 60.3 | TA418 | 2 | <80
M S Tofit | 2025-10 | 121.91 | 60 | TA418 | 1 | 120-140
M S Tofit | 2025-11 | 107.59 | 163 | TA418 | 3 | 100-120
M S Tofit | 2025-12 | 187.79 | 163 | TA418 | 4 | 180-200
M S Tofit | 2026-01 | 97.71 | 129 | TA418 | 3 | 80-100
Maa Const | 2024-09 | 37.93 | 37.93 | TA421 | 1 | <80
Maa Const | 2024-10 | 74.3 | 74.3 | TA421 | 2 | <80
Maa Const | 2024-11 | 163.77 | 163.77 | TA421 | 4 | 160-180
Maa Construction | 2024-11 | 61.73 | 0 |  | 0 | <80
Maa Construction | 2024-12 | 97.2 | 129.34 | TA325 | 1 | 80-100
Maa Construction | 2025-01 | 170.04 | 199.64 | TA325 | 4 | 160-180
Maa Construction | 2025-02 | 92.15 | 92.15 | TA325 | 2 | 80-100
Maa Construction | 2025-03 | 113.92 | 75.46 | TA325 | 2 | 100-120
Maa Construction | 2025-04 | 41.95 | 80.41 | TA325 | 1 | <80
Maa Construction | 2025-09 | 75.86 | 75.86 | TA416 | 1 | <80
Maa Construction | 2025-10 | 97.83 | 97.83 | TA416 | 1 | 80-100
Madhu Sah | 2024-06 | 8.45 | 0 |  | 0 | <80
Madhu Sah | 2024-07 | 11.04 | 0 |  | 0 | <80
Madhu Sah | 2024-08 | 11.04 | 0 |  | 0 | <80
Madhu Sah | 2024-09 | 10.69 | 0 |  | 0 | <80
Madhu Sah | 2024-10 | 11.04 | 0 |  | 0 | <80
Madhu Sah | 2024-11 | 59.85 | 35.6 | TA419 | 1 | <80
Madhu Sah | 2024-12 | 140.24 | 183.95 | TA419 | 5 | 140-160
Madhu Sah | 2025-01 | 147.43 | 114.75 | TA419 | 3 | 140-160
Madhu Sah | 2025-02 | 184.36 | 172.7 | TA419 | 4 | 180-200
Madhu Sah | 2025-03 | 49.98 | 37.14 | TA419 | 1 | <80
Madhu Sah | 2025-04 | 125.9 | 95.66 | TA419 | 2 | 120-140
Madhu Sah | 2025-05 | 92.56 | 75.07 | TA419 | 2 | 80-100
Madhu Sah | 2025-06 | 40.54 | 0 |  | 0 | <80
Madhu Sah | 2025-07 | 107.15 | 119.29 | TA419 | 2 | 100-120
Madhu Sah | 2025-08 | 106.24 | 142.64 | TA419 | 3 | 100-120
Madhu Sah | 2025-09 | 106.15 | 142.64 | TA419 | 2 | 100-120
Madhu Sah | 2025-10 | 58.53 | 79.41 | TA419 | 2 | <80
Madhu Sah | 2025-11 | 112.23 | 111.41 | TA419 | 3 | 100-120
Madhu Sah | 2025-12 | 94.73 | 111.46 | TA419 | 3 | 80-100
Madhu Sah | 2026-01 | 68.52 | 124.95 | TA419 | 1 | <80
Mahon Mahto | 2025-09 | 22.16 | 0 |  | 0 | <80
Mahon Mahto | 2025-10 | 192.58 | 78.07 | TA416 | 1 | 180-200
Mahon Mahto | 2025-11 | 152.63 | 285.61 | TA416 | 2 | 140-160
Mahon Mahto | 2025-12 | 114.5 | 0 |  | 0 | 100-120
Mahon Mahto | 2026-01 | 70.18 | 188.38 | TA416 | 1 | <80
Manirul Islam Khatun | 2024-09 | 25.98 | 0 |  | 0 | <80
Manirul Islam Khatun | 2024-10 | 10.39 | 36.37 | TA421 | 1 | <80
Mansukh Lal | 2024-05 | 37.5 | 37.5 | TB408 | 1 | <80
Mansukh Lal | 2024-06 | 37.5 | 37.5 | TB408 | 1 | <80
Md Akhtar | 2025-09 | 44.72 | 0 |  | 0 | <80
Md Akhtar | 2025-10 | 177.23 | 138.51 | TA325 | 2 | 160-180
Md Akhtar | 2025-11 | 150.43 | 129.34 | TA325 | 1 | 140-160
Md Akhtar | 2025-12 | 37.34 | 141.87 | TA325 | 1 | <80
Md Emdadul Hoque | 2025-12 | 38.04 | 38.04 | TA414 | 1 | <80
Mithun Kumar | 2024-09 | 11.18 | 0 |  | 0 | <80
Mithun Kumar | 2024-10 | 33.55 | 44.73 | TA325 | 1 | <80
Mithun Kumar | 2024-11 | 36.04 | 36.04 | TA325 | 1 | <80
Mithun Kumar | 2024-12 | 59.36 | 37.73 | TA325 | 1 | <80
Mithun Kumar | 2025-01 | 101.2 | 111.51 | TA325 | 3 | 100-120
Mithun Kumar | 2025-02 | 100.19 | 111.51 | TA325 | 3 | 100-120
Mithun Kumar | 2025-03 | 37.73 | 37.73 | TA325 | 1 | <80
Mithun Kumar | 2025-04 | 208.12 | 146.71 | TA325 | 3 | 200-220
Mithun Kumar | 2025-05 | 141.42 | 176.68 | TA325 | 2 | 140-160
Mithun Kumar | 2025-06 | 19.61 | 0 |  | 0 | <80
Mithun Kumar | 2025-07 | 20.27 | 0 |  | 0 | <80
Mithun Kumar | 2025-08 | 20.27 | 0 |  | 0 | <80
Mithun Kumar | 2025-09 | 19.61 | 0 |  | 0 | <80
Mithun Kumar | 2025-10 | 20.27 | 0 |  | 0 | <80
Mithun Kumar | 2025-11 | 79.94 | 206.13 | TA325 | 2 | <80
Mjr | 2024-12 | 100.23 | 46.62 | TA325 | 1 | 100-120
Mjr | 2025-01 | 103.99 | 157.6 | TA325 | 3 | 100-120
Mjr | 2025-02 | 115.45 | 115.45 | TA325 | 2 | 100-120
Mjr | 2025-03 | 132.32 | 101.24 | TA325 | 2 | 120-140
Mjr | 2025-04 | 144.27 | 110.88 | TA325 | 2 | 140-160
Mjr | 2025-05 | 114.12 | 178.59 | TA325 | 3 | 100-120
Modina India | 2024-11 | 32.44 | 0 |  | 0 | <80
Modina India | 2024-12 | 117.98 | 120.23 | TA325 | 3 | 100-120
Modina India | 2025-01 | 150.38 | 150.92 | TA325 | 4 | 140-160
Modina India | 2025-02 | 95.14 | 114.92 | TA325 | 3 | 80-100
Modina India | 2025-03 | 79.92 | 82.24 | TA325 | 1 | <80
Modina India | 2025-04 | 94.48 | 82.46 | TA325 | 2 | 80-100
Modina India | 2025-05 | 25.16 | 44.73 | TA325 | 1 | <80
Modina India | 2025-06 | 41.41 | 0 |  | 0 | <80
Modina India | 2025-07 | 44.27 | 0 |  | 0 | <80
Modina India | 2025-08 | 84.08 | 122.81 | TA325 | 1 | 80-100
Modina India | 2025-09 | 25.28 | 72.24 | TA325 | 1 | <80
Modina India 1 | 2025-12 | 4.44 | 0 |  | 0 | <80
Modina India 1 | 2026-01 | 33.29 | 37.73 | TA414 | 1 | <80
Modina India 1 4 Pgcil | 2025-10 | 72.09 | 72.09 | TA325 | 2 | <80
Modina India 1 Pgcil | 2025-11 | 54.32 | 0 |  | 0 | <80
Modina India 1 Pgcil | 2025-12 | 47.53 | 101.85 | TA325 | 1 | <80
Modina India 2 | 2025-12 | 4.29 | 0 |  | 0 | <80
Modina India 2 | 2026-01 | 40.75 | 45.04 | TA414 | 1 | <80
Modina India 2 Pgcil | 2025-09 | 17.61 | 0 |  | 0 | <80
Modina India 2 Pgcil | 2025-10 | 36.81 | 54.42 | TA325 | 1 | <80
Modina India 2 Pgcil | 2025-11 | 65.87 | 39.46 | TA325 | 1 | <80
Modina India 2 Pgcil | 2025-12 | 11.32 | 37.73 | TA325 | 1 | <80
Modina India 3 | 2025-12 | 3.8 | 0 |  | 0 | <80
Modina India 3 | 2026-01 | 34.24 | 38.04 | TA414 | 1 | <80
Modina India 3 Pgcil | 2025-10 | 75.46 | 75.46 | TA325 | 2 | <80
Modina India 3 Pgcil | 2025-11 | 82.46 | 82.46 | TA325 | 2 | 80-100
Modina India 3 Pgcil Dildar Electricals 3 Pgcil Nasirudin Md Akhtar | 2025-12 | 72.73 | 0 |  | 0 | <80
Modina India 3 Pgcil Dildar Electricals 3 Pgcil Nasirudin Md Akhtar | 2026-01 | 50.91 | 123.65 | TA325 | 1 | <80
Mohan Mahto | 2025-01 | 3.11 | 0 |  | 0 | <80
Mohan Mahto | 2025-02 | 3.78 | 0 |  | 0 | <80
Mohan Mahto | 2025-03 | 4.19 | 0 |  | 0 | <80
Mohan Mahto | 2025-04 | 4.05 | 0 |  | 0 | <80
Mohan Mahto | 2025-05 | 4.19 | 0 |  | 0 | <80
Mohan Mahto | 2025-06 | 4.05 | 0 |  | 0 | <80
Mohan Mahto | 2025-07 | 4.19 | 0 |  | 0 | <80
Mohan Mahto | 2025-08 | 29.86 | 0 |  | 0 | <80
Mohan Mahto | 2025-09 | 66.38 | 88 | TA506 | 3 | <80
Mohan Mahto | 2025-10 | 1.22 | 37 | TA506 | 1 | <80
Mukesh | 2024-10 | 129.59 | 100.3 | TA325 | 2 | 120-140
Mukesh | 2024-11 | 181.97 | 160.35 | TA325 | 3 | 180-200
Mukesh | 2024-12 | 219.65 | 210.75 | TA325 | 3 | 200-220
Mukesh | 2025-01 | 86.68 | 146.49 | TA325 | 2 | 80-100
Mukhilal | 2025-12 | 11.6 | 0 |  | 0 | <80
Mukhilal | 2026-01 | 23.19 | 34.79 | TA419 | 1 | <80
Mukhilal 1 | 2025-11 | 22.28 | 0 |  | 0 | <80
Mukhilal 1 | 2025-12 | 14.86 | 37.14 | TA419 | 1 | <80
Mukhilal 2 | 2025-03 | 9.65 | 0 |  | 0 | <80
Mukhilal 2 | 2025-04 | 14.48 | 0 |  | 0 | <80
Mukhilal 2 | 2025-05 | 14.96 | 0 |  | 0 | <80
Mukhilal 2 | 2025-06 | 14.48 | 0 |  | 0 | <80
Mukhilal 2 | 2025-07 | 14.96 | 0 |  | 0 | <80
Mukhilal 2 | 2025-08 | 14.96 | 0 |  | 0 | <80
Mukhilal 2 | 2025-09 | 14.48 | 0 |  | 0 | <80
Mukhilal 2 | 2025-10 | 14.96 | 0 |  | 0 | <80
Mukhilal 2 | 2025-11 | 14.48 | 0 |  | 0 | <80
Mukhilal 2 | 2025-12 | 12.55 | 139.97 | TA419 | 1 | <80
Mukkhilal 2 | 2026-01 | 16 | 16 | TA506 | 1 | <80
Muni Bibi 1 | 2025-10 | 44.73 | 44.73 | TA325 | 1 | <80
Muni Bibi 1 | 2025-11 | 61.36 | 0 |  | 0 | <80
Muni Bibi 1 | 2025-12 | 33.04 | 94.41 | TA325 | 1 | <80
Muni Bibi 1 2 | 2025-10 | 39.69 | 0 |  | 0 | <80
Muni Bibi 1 2 | 2025-11 | 23.82 | 63.51 | TA325 | 1 | <80
Muni Bibi 2 | 2025-10 | 37.73 | 37.73 | TA325 | 1 | <80
Muni Bibi 2 | 2025-11 | 84.45 | 0 |  | 0 | 80-100
Muni Bibi 2 | 2025-12 | 4.69 | 89.15 | TA325 | 1 | <80
Munna Singh | 2025-04 | 7.78 | 5.48 | TB501 | 1 | <80
Munna Singh | 2025-05 | 4.61 | 6.91 | TB501 | 1 | <80
Namechand Mahto | 2025-01 | 0.54 | 0 |  | 0 | <80
Namechand Mahto | 2025-02 | 0.84 | 0 |  | 0 | <80
Namechand Mahto | 2025-03 | 0.93 | 0 |  | 0 | <80
Namechand Mahto | 2025-04 | 0.9 | 0 |  | 0 | <80
Namechand Mahto | 2025-05 | 0.93 | 0 |  | 0 | <80
Namechand Mahto | 2025-06 | 0.9 | 0 |  | 0 | <80
Namechand Mahto | 2025-07 | 0.93 | 0 |  | 0 | <80
Namechand Mahto | 2025-08 | 0.93 | 0 |  | 0 | <80
Namechand Mahto | 2025-09 | 0.9 | 0 |  | 0 | <80
Namechand Mahto | 2025-10 | 30.81 | 29.87 | TB507 | 2 | <80
Namechand Mahto | 2025-11 | 99.24 | 98.34 | TB507 | 6 | 80-100
Namechand Mahto | 2025-12 | 119.78 | 118.84 | TB507 | 6 | 100-120
Namechand Mahto | 2026-01 | 11.69 | 22.29 | TB507 | 2 | <80
Nan | 2025-06 | 61.52 | 0 |  | 0 | <80
Nan | 2025-07 | 97.64 | 37.73 | TA325 | 1 | 80-100
Nan | 2025-08 | 20.67 | 142.1 | TA325 | 1 | <80
Nan | 2025-09 | 107.91 | 0 |  | 0 | 100-120
Nan | 2025-10 | 62.96 | 170.87 | TA325 | 3 | <80
Nasiruddin | 2025-12 | 101.59 | 73.15 | TA601 | 2 | 100-120
Nasiruddin | 2026-01 | 8.13 | 36.57 | TA601 | 1 | <80
Nasirudin | 2025-10 | 74.63 | 74.63 | TA325 | 1 | <80
Nasirudin 2 | 2025-10 | 110.05 | 80.41 | TA325 | 1 | 100-120
Nasirudin 2 | 2025-11 | 33.87 | 63.51 | TA325 | 1 | <80
Naziruddin | 2025-06 | 48.49 | 0 |  | 0 | <80
Naziruddin | 2025-07 | 180.78 | 213.27 | TA421 | 4 | 180-200
Naziruddin | 2025-08 | 136.58 | 148.4 | TA421 | 4 | 120-140
Naziruddin | 2025-09 | 95.97 | 100.14 | TA421 | 3 | 80-100
Neha Const | 2025-08 | 7.24 | 0 |  | 0 | <80
Neha Const | 2025-09 | 66.76 | 74 | TA504 | 2 | <80
Niranjan Singh | 2025-11 | 43.78 | 43.78 | TA416 | 1 | <80
Nirmal Mahto | 2024-08 | 17.27 | 0 |  | 0 | <80
Nirmal Mahto | 2024-09 | 165.21 | 163.73 | TB401, TB408 | 4 | 160-180
Nirmal Mahto | 2024-10 | 172.96 | 159.27 | TB408 | 4 | 160-180
Nirmal Mahto | 2024-11 | 120.26 | 152.69 | TB401, TB408 | 3 | 120-140
Nirmal Mahto | 2025-08 | 6.13 | 0 |  | 0 | <80
Nirmal Mahto | 2025-09 | 105.31 | 96.44 | TB408 | 2 | 100-120
Nirmal Mahto | 2025-10 | 170.69 | 179.79 | TB408 | 4 | 160-180
Nirmal Mahto | 2025-11 | 166.25 | 151.97 | TB401, TB408 | 3 | 160-180
Nirmal Mahto | 2025-12 | 137.74 | 157.93 | TB401, TB408 | 4 | 120-140
Om Construction | 2025-01 | 45.41 | 45.41 | TB401 | 1 | <80
Pankaj | 2024-11 | 74.83 | 46.05 | TA416 | 1 | <80
Pankaj | 2024-12 | 274.67 | 297.7 | TA416, TA504 | 7 | >=260
Pankaj | 2025-01 | 377.52 | 337.65 | TA416, TA504 | 8 | >=260
Pankaj | 2025-02 | 322.86 | 321.6 | TA416, TA504 | 8 | >=260
Pankaj | 2025-03 | 303.64 | 270.91 | TA416, TA504 | 6 | >=260
Pankaj | 2025-04 | 143.61 | 156 | TA504 | 4 | 140-160
Pankaj | 2025-05 | 167.08 | 76 | TA504 | 2 | 160-180
Pankaj | 2025-06 | 81.28 | 119.5 | TA504, TB401 | 3 | 80-100
Pankaj | 2025-07 | 52.57 | 94 | TA504, TA506 | 3 | <80
Pankaj | 2025-08 | 46.51 | 36 | TA504 | 1 | <80
Pankaj | 2025-09 | 26.76 | 38 | TA504 | 1 | <80
Pankaj | 2025-10 | 15.81 | 36 | TA504 | 1 | <80
Pankaj | 2025-11 | 46.1 | 78 | TA504, TA506 | 3 | <80
Pankaj | 2025-12 | 73.17 | 99 | TA506 | 4 | <80
Pankaj 1 | 2025-04 | 4.4 | 0 |  | 0 | <80
Pankaj 1 | 2025-05 | 6.2 | 0 |  | 0 | <80
Pankaj 1 | 2025-06 | 6 | 0 |  | 0 | <80
Pankaj 1 | 2025-07 | 6.2 | 0 |  | 0 | <80
Pankaj 1 | 2025-08 | 6.2 | 0 |  | 0 | <80
Pankaj 1 | 2025-09 | 24 | 18 | TA506 | 1 | <80
Pankaj 1 | 2025-10 | 6.2 | 0 |  | 0 | <80
Pankaj 1 | 2025-11 | 1.8 | 43 | TA506 | 1 | <80
Pankaj 2 | 2025-01 | 92.44 | 72 | TA504 | 2 | 80-100
Pankaj 2 | 2025-02 | 143.42 | 112 | TA504 | 3 | 140-160
Pankaj 2 | 2025-03 | 187.26 | 152 | TA504 | 4 | 180-200
Pankaj 2 | 2025-04 | 157.36 | 166 | TA504 | 4 | 140-160
Pankaj 2 | 2025-05 | 81.02 | 118 | TA504 | 3 | 80-100
Pankaj 2 | 2025-06 | 92.09 | 35 | TA504 | 1 | 80-100
Pankaj 2 | 2025-07 | 49.14 | 36 | TA504 | 1 | <80
Pankaj 2 | 2025-08 | 35.92 | 35 | TA504 | 1 | <80
Pankaj 2 | 2025-09 | 57.91 | 68 | TA506 | 2 | <80
Pankaj 2 | 2025-10 | 8.42 | 80 | TA504 | 2 | <80
Pankaj 2 | 2025-11 | 6.2 | 0 |  | 0 | <80
Pankaj 2 | 2025-12 | 0.83 | 38 | TA504 | 1 | <80
Pankaj Const | 2025-03 | 2.68 | 0 |  | 0 | <80
Pankaj Const | 2025-04 | 3.66 | 0 |  | 0 | <80
Pankaj Const | 2025-05 | 3.78 | 0 |  | 0 | <80
Pankaj Const | 2025-06 | 3.66 | 0 |  | 0 | <80
Pankaj Const | 2025-07 | 3.78 | 0 |  | 0 | <80
Pankaj Const | 2025-08 | 3.78 | 0 |  | 0 | <80
Pankaj Const | 2025-09 | 3.66 | 0 |  | 0 | <80
Pankaj Const | 2025-10 | 3.78 | 0 |  | 0 | <80
Pankaj Const | 2025-11 | 1.22 | 30 | TA506 | 1 | <80
Pankaj Kumar | 2025-09 | 22.71 | 0 |  | 0 | <80
Pankaj Kumar | 2025-10 | 223.97 | 221.39 | TA416 | 2 | 220-240
Pankaj Kumar | 2025-11 | 154.77 | 75.86 | TA416 | 1 | 140-160
Pankaj Kumar | 2025-12 | 170.11 | 221.27 | TA416 | 2 | 160-180
Pankaj Kumar | 2026-01 | 44.19 | 97.23 | TA416 | 1 | <80
Pankaj Singh Mp | 2025-09 | 64.92 | 34.79 | TA505 | 1 | <80
Pankaj Singh Mp | 2025-10 | 157.9 | 163.93 | TA505 | 4 | 140-160
Pankaj Singh Mp | 2025-11 | 166.13 | 181.2 | TA505 | 5 | 160-180
Pankaj Singh Mp | 2025-12 | 130.92 | 139.96 | TA505 | 3 | 120-140
Panva Devi | 2025-10 | 72.12 | 0 |  | 0 | <80
Panva Devi | 2025-11 | 156.46 | 190.88 | TB401, TB408 | 2 | 140-160
Panva Devi | 2025-12 | 110.69 | 148.4 | TB408 | 3 | 100-120
Pappu Kumar | 2025-11 | 10.23 | 0 |  | 0 | <80
Pappu Kumar | 2025-12 | 10.77 | 21 | TA506 | 1 | <80
Paramanand | 2025-04 | 19.14 | 0 |  | 0 | <80
Paramanand | 2025-05 | 17.02 | 36.16 | TA505 | 1 | <80
Paramanand 1 | 2025-05 | 55.44 | 36.16 | TA505 | 1 | <80
Paramanand 1 | 2025-06 | 32.28 | 36.16 | TA505 | 1 | <80
Paramanand 1 | 2025-07 | 20.76 | 36.16 | TA505 | 1 | <80
Paramanand 1 | 2025-08 | 13.12 | 0 |  | 0 | <80
Paramanand 1 | 2025-09 | 73.48 | 71.76 | TA505 | 2 | <80
Paramanand 1 | 2025-10 | 97.78 | 71.2 | TA505 | 2 | 80-100
Paramanand 1 | 2025-11 | 49.05 | 62.12 | TA505 | 1 | <80
Paramanand 1 | 2025-12 | 15.46 | 43.8 | TA505 | 1 | <80
Paramanand 2 | 2025-05 | 41.78 | 36.16 | TA505 | 1 | <80
Paramanand 2 | 2025-06 | 32.31 | 37.93 | TA505 | 1 | <80
Parsuram Sai | 2024-08 | 1.83 | 0 |  | 0 | <80
Parsuram Sai | 2024-09 | 27.44 | 0 |  | 0 | <80
Parsuram Sai | 2024-10 | 37.72 | 37.5 | TB401 | 1 | <80
Parsuram Sai | 2024-11 | 17.69 | 47.18 | TB401 | 1 | <80
Pc 2 | 2025-11 | 163.23 | 46.62 | TA325 | 1 | 160-180
Pc 2 | 2025-12 | 116.32 | 232.93 | TA325 | 2 | 100-120
Pc 3 Prabhat Kumar Ranjan | 2025-11 | 57.57 | 0 |  | 0 | <80
Pc 3 Prabhat Kumar Ranjan | 2025-12 | 24.67 | 82.24 | TA325 | 1 | <80
Pc Construction | 2025-11 | 97.93 | 97.93 | TA325 | 1 | 80-100
Pc Construction 1 | 2025-11 | 26.74 | 0 |  | 0 | <80
Pc Construction 1 | 2025-12 | 185.21 | 211.95 | TA325 | 2 | 180-200
Permanand | 2025-06 | 38.85 | 38.85 | TB401 | 1 | <80
Pinki Devi | 2025-01 | 53.16 | 37.93 | TA419 | 1 | <80
Pinki Devi | 2025-02 | 117.06 | 105.2 | TA419 | 2 | 100-120
Pinki Devi | 2025-03 | 10.84 | 37.93 | TA419 | 1 | <80
Pinki Devi | 2025-08 | 83.63 | 83.63 | TA413 | 2 | 80-100
Pinki Devi | 2025-09 | 132 | 132 | TA504 | 2 | 120-140
Pinki Devi | 2025-10 | 73 | 73 | TA504 | 2 | <80
Pinky Dewi | 2024-11 | 63.32 | 46.05 | TA416 | 1 | <80
Pinky Dewi | 2024-12 | 231.07 | 222.02 | TA416 | 5 | 220-240
Pinky Dewi | 2025-01 | 198.18 | 184.2 | TA416 | 4 | 180-200
Pinky Dewi | 2025-02 | 206.11 | 246.4 | TA416 | 5 | 200-220
Pinky Dewi | 2025-03 | 253.93 | 237.19 | TA416 | 5 | 240-260
Pinky Dewi | 2025-04 | 222.23 | 238.98 | TA416 | 4 | 220-240
Pinky Dewi | 2025-05 | 213.6 | 181.98 | TA416 | 3 | 200-220
Pinky Dewi | 2025-06 | 223.03 | 254.65 | TA416 | 5 | 220-240
Pinky Dewi | 2025-07 | 46.05 | 46.05 | TA416 | 1 | <80
Pinky Dewi | 2025-11 | 133.52 | 43.78 | TA416 | 1 | 120-140
Pinky Dewi | 2025-12 | 90.19 | 156.05 | TA416 | 2 | 80-100
Pinky Dewi | 2026-01 | 40.6 | 64.48 | TA416 | 1 | <80
Poonam | 2025-06 | 57.6 | 38.85 | TB401 | 1 | <80
Poonam | 2025-07 | 226.36 | 245.12 | TB401 | 6 | 220-240
Poonam | 2025-08 | 37.5 | 37.5 | TB401 | 1 | <80
Poonam | 2025-11 | 20.64 | 0 |  | 0 | <80
Poonam | 2025-12 | 24.77 | 45.41 | TB401 | 1 | <80
Poonam Kumari | 2024-01 | 183.07 | 157.92 | TA325 | 4 | 180-200
Poonam Kumari | 2024-02 | 205.34 | 205.34 | TA325 | 5 | 200-220
Poonam Kumari | 2024-03 | 41.45 | 37.73 | TA325 | 1 | <80
Poonam Kumari | 2024-04 | 10.59 | 39.46 | TA325 | 1 | <80
Poonam Kumari | 2025-01 | 3.71 | 0 |  | 0 | <80
Poonam Kumari | 2025-02 | 167.06 | 104.4 | TA419 | 2 | 160-180
Poonam Kumari | 2025-03 | 66.37 | 132.75 | TA419 | 2 | <80
Poonam Kumari | 2025-04 | 16.64 | 0 |  | 0 | <80
Poonam Kumari | 2025-05 | 38.82 | 55.45 | TA419 | 1 | <80
Poonam Kumari 2 | 2025-10 | 43.8 | 43.8 | TA419 | 1 | <80
Poornam Kumari | 2025-03 | 48.93 | 0 |  | 0 | <80
Poornam Kumari | 2025-04 | 90.54 | 139.46 | TA419 | 3 | 80-100
Pramod Kumar | 2025-04 | 2.91 | 0 |  | 0 | <80
Pramod Kumar | 2025-05 | 4.75 | 0 |  | 0 | <80
Pramod Kumar | 2025-06 | 4.6 | 0 |  | 0 | <80
Pramod Kumar | 2025-07 | 4.75 | 0 |  | 0 | <80
Pramod Kumar | 2025-08 | 4.75 | 0 |  | 0 | <80
Pramod Kumar | 2025-09 | 4.6 | 0 |  | 0 | <80
Pramod Kumar | 2025-10 | 4.75 | 0 |  | 0 | <80
Pramod Kumar | 2025-11 | 4.6 | 0 |  | 0 | <80
Pramod Kumar | 2025-12 | 1.99 | 37.73 | TA414 | 1 | <80
Praveen | 2024-10 | 48.63 | 37.93 | TA421 | 1 | <80
Praveen | 2024-11 | 55.7 | 36.37 | TA421 | 1 | <80
Praveen | 2024-12 | 45.83 | 75.86 | TA421 | 2 | <80
Praveen | 2025-01 | 78.8 | 72.74 | TA421 | 2 | <80
Praveen | 2025-02 | 105.21 | 79.45 | TA421 | 2 | 100-120
Praveen | 2025-03 | 102.19 | 122.53 | TA421 | 3 | 100-120
Praveen | 2025-04 | 86.34 | 86.16 | TA421 | 2 | 80-100
Praveen | 2025-05 | 79.17 | 37.93 | TA421 | 1 | <80
Praveen | 2025-06 | 77.97 | 97.48 | TA421 | 2 | <80
Praveen | 2025-07 | 53.51 | 54.66 | TA421 | 1 | <80
Praveen | 2025-08 | 31.14 | 34.95 | TA421 | 1 | <80
Praveen | 2025-09 | 36.22 | 37.93 | TA421 | 1 | <80
Praveen | 2025-10 | 52.71 | 79.45 | TA421 | 2 | <80
Praveen | 2025-11 | 45.11 | 37.93 | TA421 | 1 | <80
Praveen | 2025-12 | 37.67 | 44.85 | TA421 | 1 | <80
Prayag Mahto | 2025-09 | 47.63 | 0 |  | 0 | <80
Prayag Mahto | 2025-10 | 61.2 | 99.55 | TA325 | 2 | <80
Prayag Mahto | 2025-11 | 92.74 | 0 |  | 0 | 80-100
Prayag Mahto | 2025-12 | 21.64 | 123.65 | TA325 | 1 | <80
Prayag Saw | 2025-12 | 65.67 | 65.67 | TB507 | 4 | <80
Prayag Saw | 2026-01 | 48.66 | 48.66 | TB507 | 3 | <80
Prayag Saw 1 | 2025-09 | 59.97 | 59.97 | TB507 | 5 | <80
Prayag Saw 1 | 2025-10 | 127.38 | 116.14 | TB507 | 7 | 120-140
Prayag Saw 1 | 2025-11 | 28.9 | 40.14 | TB507 | 2 | <80
Prayag Saw 2 | 2025-09 | 70.52 | 70.52 | TB507 | 5 | <80
Prayag Saw 2 | 2025-10 | 106.53 | 99.25 | TB507 | 6 | 100-120
Prayag Saw 2 | 2025-11 | 119.91 | 127.19 | TB507 | 8 | 100-120
Prayag Saw 2 | 2025-12 | 43.39 | 43.39 | TB507 | 3 | <80
Prayag Shah Mp | 2025-11 | 102.03 | 102.03 | TA505 | 2 | 100-120
Prayag Shah Mp | 2025-12 | 107.11 | 107.11 | TA505 | 3 | 100-120
Prayag Shah Mp | 2026-01 | 37.93 | 37.93 | TA505 | 1 | <80
Prem Kumar | 2025-03 | 2.57 | 0 |  | 0 | <80
Prem Kumar | 2025-04 | 3.86 | 0 |  | 0 | <80
Prem Kumar | 2025-05 | 3.99 | 0 |  | 0 | <80
Prem Kumar | 2025-06 | 3.86 | 0 |  | 0 | <80
Prem Kumar | 2025-07 | 3.99 | 0 |  | 0 | <80
Prem Kumar | 2025-08 | 3.99 | 0 |  | 0 | <80
Prem Kumar | 2025-09 | 3.86 | 0 |  | 0 | <80
Prem Kumar | 2025-10 | 74.07 | 40 | TA506 | 1 | <80
Prem Kumar | 2025-11 | 26.78 | 53 | TA506 | 1 | <80
Prem Kumar | 2025-12 | 29.06 | 63 | TA506 | 2 | <80
Pritam Enterprises | 2025-07 | 105.2 | 105.2 | TA413 | 2 | 100-120
Pritam Enterprises | 2025-09 | 15 | 12 | TB507 | 1 | <80
Pritam Enterprises | 2025-10 | 124.47 | 127.47 | TB507 | 10 | 120-140
Pritam Enterprises | 2025-11 | 42.72 | 42.72 | TB507 | 3 | <80
Pritam Enterprises 1 | 2025-08 | 109.88 | 109.88 | TA413 | 3 | 100-120
Pritam Enterprises 1 | 2025-09 | 112.02 | 112.02 | TA413 | 3 | 100-120
Pritam Enterprises 1 | 2025-10 | 102.96 | 102.96 | TA413 | 2 | 100-120
Pritam Enterprises 1 | 2025-11 | 26 | 0 |  | 0 | <80
Pritam Enterprises 1 | 2025-12 | 39.87 | 65.87 | TA413 | 1 | <80
Pritam Enterprises 2 | 2025-08 | 166.11 | 117.62 | TA413 | 3 | 160-180
Pritam Enterprises 2 | 2025-09 | 129.6 | 155.83 | TA413 | 4 | 120-140
Pritam Enterprises 2 | 2025-10 | 76.97 | 66.78 | TA413 | 1 | <80
Pritam Enterprises 2 | 2025-11 | 58.93 | 87.61 | TA413 | 2 | <80
Pritam Enterprises 2 | 2025-12 | 114.83 | 118.6 | TA413 | 2 | 100-120
Pritam Enterprises 3 | 2025-08 | 144.58 | 119.29 | TA413 | 2 | 140-160
Pritam Enterprises 3 | 2025-09 | 170.24 | 195.53 | TA413 | 5 | 160-180
Pritam Enterprises 3 | 2025-10 | 113.24 | 113.24 | TA413 | 2 | 100-120
Pritam Enterprises 4 | 2025-08 | 91.44 | 81.74 | TA413 | 2 | 80-100
Pritam Enterprises 4 | 2025-09 | 71.59 | 81.3 | TA413 | 2 | <80
Pritam Enterprises 4 | 2025-10 | 71.73 | 62.44 | TA413 | 1 | <80
Pritam Enterprises 4 | 2025-11 | 27.85 | 37.14 | TA413 | 1 | <80
Priyanka Devi | 2025-08 | 111.39 | 103.89 | TB401, TB408 | 2 | 100-120
Priyanka Devi | 2025-09 | 30 | 37.5 | TB401 | 1 | <80
Priyanka Devi | 2025-11 | 50.45 | 37.5 | TB408 | 1 | <80
Priyanka Devi | 2025-12 | 64.75 | 77.7 | TB408 | 2 | <80
Priyanka Devi 2 | 2025-07 | 37.5 | 37.5 | TB408 | 1 | <80
Priyanka Devi 2 | 2025-08 | 115.2 | 115.2 | TB401 | 3 | 100-120
Priyanka Devi Santosh | 2025-08 | 25 | 0 |  | 0 | <80
Priyanka Devi Santosh | 2025-09 | 39.58 | 37.5 | TB408 | 1 | <80
Priyanka Devi Santosh | 2025-10 | 11.77 | 38.85 | TB401 | 1 | <80
Priyanka Devi Sontosh | 2025-09 | 57.6 | 57.6 | TB408 | 1 | <80
Priyanka Devi Subodh | 2025-07 | 12.45 | 0 |  | 0 | <80
Priyanka Devi Subodh | 2025-08 | 53.93 | 66.38 | TB408 | 1 | <80
Priyanka Devi Subodh | 2025-09 | 67.1 | 38.85 | TB408 | 1 | <80
Priyanka Devi Subodh | 2025-10 | 48.1 | 76.35 | TB401, TB408 | 2 | <80
Priyanka Devi Sudheer | 2025-06 | 30.28 | 0 |  | 0 | <80
Priyanka Devi Sudheer | 2025-07 | 130.34 | 160.61 | TB401 | 4 | 120-140
Priyanka Devi Sudheer | 2025-08 | 161.48 | 161.48 | TB401 | 3 | 160-180
Priyanka Devi Sudheer | 2025-09 | 129.53 | 121.77 | TB408 | 3 | 120-140
Priyanka Devi Sudheer | 2025-10 | 71.57 | 76.35 | TB401 | 2 | <80
Priyanka Devi Sudheer | 2025-11 | 35.86 | 38.85 | TB401 | 1 | <80
Priyanka Devi Sudheer 2 | 2025-07 | 38.85 | 38.85 | TB401 | 1 | <80
Punam Devi 1 | 2024-12 | 62.17 | 34.79 | TA413 | 1 | <80
Punam Devi 1 | 2025-01 | 202.46 | 211.06 | TA413 | 5 | 200-220
Punam Devi 1 | 2025-02 | 212.12 | 230.9 | TA413 | 6 | 200-220
Punam Devi 1 | 2025-03 | 206.92 | 198.96 | TA413 | 5 | 200-220
Punam Devi 1 | 2025-04 | 138.01 | 145.97 | TA413 | 3 | 120-140
Punam Devi 2 | 2024-12 | 208.81 | 192.39 | TA413 | 5 | 200-220
Punam Devi 2 | 2025-01 | 375.11 | 388.3 | TA413 | 9 | >=260
Punam Devi 2 | 2025-02 | 124.59 | 123.21 | TA413 | 3 | 120-140
Punam Devi 2 | 2025-03 | 173.5 | 174.32 | TA413 | 4 | 160-180
Punam Devi 2 | 2025-04 | 144.72 | 148.52 | TA413 | 3 | 140-160
Punam Devi 3 | 2024-03 | 0.6 | 0 |  | 0 | <80
Punam Devi 3 | 2024-04 | 3 | 0 |  | 0 | <80
Punam Devi 3 | 2024-05 | 3.1 | 0 |  | 0 | <80
Punam Devi 3 | 2024-06 | 3 | 0 |  | 0 | <80
Punam Devi 3 | 2024-07 | 3.1 | 0 |  | 0 | <80
Punam Devi 3 | 2024-08 | 3.1 | 0 |  | 0 | <80
Punam Devi 3 | 2024-09 | 3 | 0 |  | 0 | <80
Punam Devi 3 | 2024-10 | 3.1 | 0 |  | 0 | <80
Punam Devi 3 | 2024-11 | 3 | 0 |  | 0 | <80
Punam Devi 3 | 2024-12 | 68.62 | 37.93 | TA413 | 1 | <80
Punam Devi 3 | 2025-01 | 153.91 | 167.26 | TA413 | 4 | 140-160
Punam Devi 3 | 2025-02 | 122.94 | 113 | TA413 | 3 | 120-140
Punam Devi 3 | 2025-03 | 149.84 | 195.83 | TA413 | 5 | 140-160
Punam Devi 3 | 2025-04 | 123 | 129.32 | TA413 | 3 | 120-140
Punam Devi 4 | 2025-01 | 52.4 | 37.93 | TA413 | 1 | <80
Punam Devi 4 | 2025-02 | 248.38 | 262.85 | TA413 | 6 | 240-260
Punam Devi 4 | 2025-03 | 282.02 | 275.49 | TA413 | 7 | >=260
Punam Devi 4 | 2025-04 | 39.17 | 45.7 | TA413 | 1 | <80
Punam Kumari | 2024-11 | 19.72 | 0 |  | 0 | <80
Punam Kumari | 2024-12 | 16.44 | 36.16 | TA419 | 1 | <80
Punam Kumari | 2025-07 | 139.79 | 129.32 | TA413 | 3 | 120-140
Punam Kumari | 2025-08 | 145.41 | 112.83 | TA413, TA416 | 2 | 140-160
Punam Kumari | 2025-09 | 133.4 | 145.46 | TA416 | 2 | 120-140
Punam Kumari | 2025-10 | 36.14 | 67.11 | TA416 | 1 | <80
Punam Kumari 1 | 2025-05 | 5.53 | 0 |  | 0 | <80
Punam Kumari 1 | 2025-06 | 8.29 | 0 |  | 0 | <80
Punam Kumari 1 | 2025-07 | 8.57 | 0 |  | 0 | <80
Punam Kumari 1 | 2025-08 | 142.8 | 126.64 | TA413 | 3 | 140-160
Punam Kumari 1 | 2025-09 | 228.51 | 181.6 | TA413 | 5 | 220-240
Punam Kumari 1 | 2025-10 | 384.89 | 320.9 | TA413, TA416 | 4 | >=260
Punam Kumari 1 | 2025-11 | 327.72 | 323.03 | TA413, TA416, TA419 | 6 | >=260
Punam Kumari 1 | 2025-12 | 220.29 | 340.54 | TA416, TA419, TA504 | 7 | 220-240
Punam Kumari 1 | 2026-01 | 9.88 | 43.78 | TA416 | 1 | <80
Punam Kumari 2 | 2025-04 | 2.97 | 0 |  | 0 | <80
Punam Kumari 2 | 2025-05 | 4.84 | 0 |  | 0 | <80
Punam Kumari 2 | 2025-06 | 4.68 | 0 |  | 0 | <80
Punam Kumari 2 | 2025-07 | 4.84 | 0 |  | 0 | <80
Punam Kumari 2 | 2025-08 | 214.88 | 192.35 | TA413 | 4 | 200-220
Punam Kumari 2 | 2025-09 | 246.02 | 259.04 | TA413 | 5 | 240-260
Punam Kumari 2 | 2025-10 | 277.42 | 196.16 | TA413, TA416 | 5 | >=260
Punam Kumari 2 | 2025-11 | 117.3 | 189.05 | TA416, TA419 | 3 | 100-120
Punam Kumari 2 | 2025-12 | 249.41 | 285.78 | TA419, TA504 | 4 | 240-260
Punam Kumari 3 | 2025-08 | 11.95 | 0 |  | 0 | <80
Punam Kumari 3 | 2025-09 | 104.58 | 116.52 | TA413 | 3 | 100-120
Punam Kumari 3 | 2025-11 | 55.35 | 0 |  | 0 | <80
Punam Kumari 3 | 2025-12 | 110.66 | 110.7 | TA416 | 1 | 100-120
Punam Kumari 3 | 2026-01 | 55.31 | 110.63 | TA416 | 1 | <80
Punam Kumari 4 | 2025-09 | 125.48 | 101.15 | TA413 | 2 | 120-140
Punam Kumari 4 | 2025-10 | 57.4 | 81.74 | TA413 | 2 | <80
Punam Kumari 4 | 2025-12 | 37.93 | 37.93 | TA419 | 1 | <80
Pusplata | 2025-08 | 66.38 | 66.38 | TB408 | 1 | <80
Pusplata 1 | 2025-06 | 45.41 | 45.41 | TB401 | 1 | <80
Pusplata 1 | 2025-07 | 179.36 | 179.36 | TB401 | 4 | 160-180
Pusplata 1 | 2025-08 | 57.6 | 57.6 | TB401 | 1 | <80
Pusplata 2 | 2025-06 | 20.18 | 0 |  | 0 | <80
Pusplata 2 | 2025-07 | 203.86 | 224.04 | TB401 | 5 | 200-220
Pusplata 3 | 2025-06 | 14.06 | 0 |  | 0 | <80
Pusplata 3 | 2025-07 | 127.38 | 133.95 | TB401 | 3 | 120-140
Pusplata 3 | 2025-08 | 30 | 37.5 | TB401 | 1 | <80
Pusplata 3 Jwala | 2025-07 | 47.18 | 47.18 | TB401 | 1 | <80
Pusplata 4 | 2025-06 | 38.85 | 38.85 | TB401 | 1 | <80
Pusplata 4 | 2025-07 | 237.39 | 237.39 | TB401 | 6 | 220-240
Pusplata 4 | 2025-08 | 37.5 | 37.5 | TB401 | 1 | <80
Pusplata 5 | 2025-06 | 19.42 | 0 |  | 0 | <80
Pusplata 5 | 2025-07 | 142.96 | 162.38 | TB401 | 4 | 140-160
Pusplata 6 | 2025-06 | 12.39 | 0 |  | 0 | <80
Pusplata 6 | 2025-07 | 162.7 | 175.09 | TB401 | 4 | 160-180
Pusplata 6 | 2025-08 | 37.5 | 37.5 | TB401 | 1 | <80
Pusplata 7 | 2025-07 | 116.54 | 116.54 | TB401 | 3 | 100-120
Pusplata Ashok | 2025-04 | 2.07 | 0 |  | 0 | <80
Pusplata Ashok | 2025-05 | 9.15 | 0 |  | 0 | <80
Pusplata Ashok | 2025-06 | 8.86 | 0 |  | 0 | <80
Pusplata Ashok | 2025-07 | 9.15 | 0 |  | 0 | <80
Pusplata Ashok | 2025-08 | 166.19 | 195.43 | TB401, TB408 | 5 | 160-180
Pusplata Ashok | 2025-09 | 70.7 | 70.7 | TB401 | 1 | <80
Pusplata Deepak | 2025-08 | 151.36 | 151.36 | TB401, TB408 | 4 | 140-160
Pusplata Deepak | 2025-09 | 37.5 | 37.5 | TB401 | 1 | <80
Pusplata Dharamveer | 2025-08 | 135.82 | 86.03 | TB401, TB408 | 2 | 120-140
Pusplata Dharamveer | 2025-09 | 16.6 | 66.38 | TB408 | 1 | <80
Pusplata Kailash | 2025-07 | 38.85 | 38.85 | TB408 | 1 | <80
Pusplata Kailash | 2025-08 | 180.83 | 152.7 | TB408 | 4 | 180-200
Pusplata Kailash | 2025-09 | 48.22 | 76.35 | TB408 | 2 | <80
Pusplata Pankaj | 2025-08 | 38.85 | 38.85 | TB408 | 1 | <80
Pusplata Pankaj | 2025-09 | 37.5 | 37.5 | TB401 | 1 | <80
Pusplata Praful | 2025-07 | 41.25 | 37.5 | TB408 | 1 | <80
Pusplata Praful | 2025-08 | 123.66 | 127.41 | TB401, TB408 | 2 | 120-140
Pusplata Praphul | 2025-08 | 41.5 | 0 |  | 0 | <80
Pusplata Praphul | 2025-09 | 48.41 | 89.91 | TB408 | 1 | <80
Pusplata Rajaram | 2025-08 | 118.71 | 89.91 | TB401 | 1 | 100-120
Pusplata Rajaram | 2025-09 | 66.3 | 95.1 | TB408 | 2 | <80
Pusplata Ramchander | 2025-08 | 81.49 | 81.49 | TB401 | 1 | 80-100
Pusplata Ramchandra | 2025-08 | 42.87 | 38.85 | TB408 | 1 | <80
Pusplata Ramchandra | 2025-09 | 34.83 | 38.85 | TB408 | 1 | <80
Pusplata Santosh | 2025-08 | 47.18 | 47.18 | TB401 | 1 | <80
Pusplata Santosh Pankaj Singh | 2025-08 | 44.25 | 0 |  | 0 | <80
Pusplata Santosh Pankaj Singh | 2025-09 | 22.13 | 66.38 | TB408 | 1 | <80
Rabiul Hauq | 2025-02 | 28.07 | 26.53 | TB501 | 5 | <80
Rabiul Hauq | 2025-03 | 24.14 | 25.68 | TB501 | 5 | <80
Radha Construction | 2025-08 | 78.07 | 78.07 | TA416 | 1 | <80
Radha Construction | 2025-09 | 89.72 | 89.72 | TA416 | 1 | 80-100
Radha Enterprises | 2024-04 | 5.62 | 0 |  | 0 | <80
Radha Enterprises | 2024-05 | 9.17 | 0 |  | 0 | <80
Radha Enterprises | 2024-06 | 8.88 | 0 |  | 0 | <80
Radha Enterprises | 2024-07 | 9.17 | 0 |  | 0 | <80
Radha Enterprises | 2024-08 | 9.17 | 0 |  | 0 | <80
Radha Enterprises | 2024-09 | 16.15 | 0 |  | 0 | <80
Radha Enterprises | 2024-10 | 21.04 | 0 |  | 0 | <80
Radha Enterprises | 2024-11 | 72.55 | 34.79 | TA419 | 1 | <80
Radha Enterprises | 2024-12 | 201.22 | 318.18 | TA419 | 8 | 200-220
Radha Enterprises | 2025-01 | 174.15 | 117.34 | TA419 | 3 | 160-180
Radha Enterprises | 2025-02 | 92.65 | 149.46 | TA419 | 2 | 80-100
Radha Enterprises | 2025-04 | 61.87 | 37.14 | TA419 | 1 | <80
Radha Enterprises | 2025-05 | 139.74 | 137.05 | TA419 | 1 | 120-140
Radha Enterprises | 2025-06 | 15.24 | 0 |  | 0 | <80
Radha Enterprises | 2025-07 | 83.61 | 55.45 | TA419 | 1 | 80-100
Radha Enterprises | 2025-08 | 156.63 | 189.97 | TA419 | 2 | 140-160
Radha Enterprises | 2025-09 | 171.34 | 102.94 | TA419 | 2 | 160-180
Radha Enterprises | 2025-10 | 31.15 | 137.05 | TA419 | 1 | <80
Radha Enterprises 1 | 2025-02 | 45.7 | 45.7 | TA419 | 1 | <80
Radha Enterprises 1 | 2025-03 | 57.92 | 36.16 | TA419 | 1 | <80
Radha Enterprises 1 | 2025-04 | 85.61 | 107.36 | TA419 | 3 | 80-100
Radha Enterprises 1 | 2025-05 | 88.71 | 0 |  | 0 | 80-100
Radha Enterprises 1 | 2025-06 | 102.91 | 153.21 | TA419 | 3 | 100-120
Radha Enterprises 1 | 2025-07 | 88.8 | 67.26 | TA419 | 1 | 80-100
Radha Enterprises 1 | 2025-08 | 38.87 | 35.6 | TA419 | 1 | <80
Radha Enterprises 1 | 2025-09 | 22.85 | 0 |  | 0 | <80
Radha Enterprises 1 | 2025-10 | 13.71 | 99.78 | TA419 | 1 | <80
Radha Enterprises 2 | 2025-02 | 7.69 | 0 |  | 0 | <80
Radha Enterprises 2 | 2025-03 | 59.57 | 67.26 | TA419 | 1 | <80
Radhika Enterprises | 2025-02 | 2.97 | 0 |  | 0 | <80
Radhika Enterprises | 2025-03 | 4.6 | 0 |  | 0 | <80
Radhika Enterprises | 2025-04 | 4.45 | 0 |  | 0 | <80
Radhika Enterprises | 2025-05 | 4.6 | 0 |  | 0 | <80
Radhika Enterprises | 2025-06 | 4.45 | 0 |  | 0 | <80
Radhika Enterprises | 2025-07 | 4.6 | 0 |  | 0 | <80
Radhika Enterprises | 2025-08 | 1.34 | 27 | TA506 | 1 | <80
Rafikul Islam | 2024-09 | 13.64 | 0 |  | 0 | <80
Rafikul Islam | 2024-10 | 236.17 | 152.7 | TB401, TB408 | 4 | 220-240
Rafikul Islam | 2024-11 | 75.69 | 172.8 | TB401, TB408 | 4 | <80
Rahim Khan | 2024-11 | 8.93 | 0 |  | 0 | <80
Rahim Khan | 2024-12 | 74.08 | 75.46 | TA325 | 2 | <80
Rahim Khan | 2025-01 | 85.96 | 75.46 | TA325 | 2 | 80-100
Rahim Khan | 2025-02 | 19.69 | 37.73 | TA325 | 1 | <80
Rahim Khan | 2025-03 | 157.13 | 132.14 | TA325 | 2 | 140-160
Rahim Khan | 2025-04 | 169.15 | 194.13 | TA325 | 4 | 160-180
Rahim Khan | 2025-05 | 73.78 | 73.78 | TA325 | 2 | <80
Rahim Khan 1 | 2025-05 | 39.46 | 39.46 | TA325 | 1 | <80
Rahul Kumar | 2024-05 | 114.92 | 114.92 | TA325 | 3 | 100-120
Rahul Kumar | 2024-06 | 157.21 | 150.92 | TA325 | 4 | 140-160
Rahul Kumar | 2024-07 | 171.16 | 177.45 | TA325 | 4 | 160-180
Rahul Kumar | 2024-08 | 192.41 | 192.41 | TA325 | 3 | 180-200
Rahul Kumar | 2024-09 | 121.74 | 64.25 | TA325 | 1 | 120-140
Rahul Kumar | 2024-10 | 108.38 | 129.34 | TA325 | 1 | 100-120
Rahul Kumar | 2024-11 | 191.7 | 164.15 | TA325 | 3 | 180-200
Rahul Kumar | 2024-12 | 91.39 | 151.88 | TA325 | 2 | 80-100
Rahul Kumar | 2025-01 | 128.5 | 103.71 | TA325 | 2 | 120-140
Rahul Kumar | 2025-02 | 184.44 | 141.87 | TA325 | 1 | 180-200
Rahul Kumar | 2025-03 | 191.28 | 262.22 | TA325 | 3 | 180-200
Rahul Kumar | 2025-04 | 182.89 | 170.87 | TA325 | 3 | 180-200
Rahul Kumar | 2025-05 | 88.28 | 100.3 | TA325 | 2 | 80-100
Rahul Kumar | 2025-07 | 128.4 | 121.76 | TB401 | 3 | 120-140
Rahul Kumar | 2025-08 | 182.77 | 144.08 | TB401, TB408 | 3 | 180-200
Rahul Kumar | 2025-09 | 60.95 | 84.69 | TB401 | 2 | <80
Rahul Kumar | 2025-10 | 185.9 | 162.65 | TA325 | 2 | 180-200
Rahul Kumar | 2025-11 | 152.18 | 39.46 | TA325 | 1 | 140-160
Rahul Kumar | 2025-12 | 139.4 | 296.97 | TA325, TA414 | 4 | 120-140
Raj Labour Suppliers | 2025-11 | 10.47 | 0 |  | 0 | <80
Raj Labour Suppliers | 2025-12 | 51.8 | 56.08 | TB605 | 3 | <80
Raj Labour Suppliers | 2026-01 | 34.81 | 41 | TB605 | 2 | <80
Rajesh Kumar | 2025-05 | 4.97 | 0 |  | 0 | <80
Rajesh Kumar | 2025-06 | 7.46 | 0 |  | 0 | <80
Rajesh Kumar | 2025-07 | 7.71 | 0 |  | 0 | <80
Rajesh Kumar | 2025-08 | 7.71 | 0 |  | 0 | <80
Rajesh Kumar | 2025-09 | 7.46 | 0 |  | 0 | <80
Rajesh Kumar | 2025-10 | 7.71 | 0 |  | 0 | <80
Rajesh Kumar | 2025-11 | 2.98 | 46 | TA504 | 1 | <80
Rajesh Mahto | 2025-10 | 2.4 | 0 |  | 0 | <80
Rajesh Mahto | 2025-11 | 5.14 | 0 |  | 0 | <80
Rajesh Mahto | 2025-12 | 37.42 | 42.54 | TB507 | 3 | <80
Rajesh Mahto | 2026-01 | 12.14 | 14.57 | TB507 | 1 | <80
Raju Kumar | 2025-09 | 15.57 | 0 |  | 0 | <80
Raju Kumar | 2025-10 | 25.4 | 0 |  | 0 | <80
Raju Kumar | 2025-11 | 55.32 | 0 |  | 0 | <80
Raju Kumar | 2025-12 | 70.43 | 145.46 | TA419 | 2 | <80
Raju Kumar | 2026-01 | 24.8 | 46.05 | TA419 | 1 | <80
Rames Kumar M | 2025-05 | 17.18 | 17.18 | TB501 | 2 | <80
Rames Kumar M | 2025-10 | 24.45 | 24.45 | TB501 | 4 | <80
Rames Kumar M | 2025-11 | 11.53 | 11.53 | TB501 | 2 | <80
Ramesh | 2025-11 | 8.01 | 5.48 | TB501 | 1 | <80
Ramesh | 2025-12 | 3.8 | 6.33 | TB501 | 1 | <80
Ramesh Kumar | 2024-12 | 10.1 | 10.1 | TB501 | 2 | <80
Ramesh Kumar | 2025-01 | 84.1 | 80.45 | TB501 | 15 | 80-100
Ramesh Kumar | 2025-02 | 100.22 | 100.22 | TB501 | 17 | 100-120
Ramesh Kumar | 2025-03 | 95.14 | 97.25 | TB501 | 16 | 80-100
Ramesh Kumar | 2025-04 | 65.4 | 66.94 | TB501 | 9 | <80
Ramesh Kumar | 2025-05 | 49.45 | 49.45 | TB501 | 8 | <80
Ramesh Kumar | 2025-06 | 66.97 | 66.97 | TB501 | 6 | <80
Ramesh Kumar | 2025-07 | 55.29 | 55.29 | TB501 | 7 | <80
Ramesh Kumar | 2025-10 | 6.2 | 6.2 | TB501 | 1 | <80
Ramesh Kumar | 2025-11 | 64.99 | 64.99 | TB501 | 10 | <80
Ramesh Kumar | 2025-12 | 34.36 | 34.36 | TB501 | 4 | <80
Ramesh Kumar M | 2025-05 | 25.68 | 25.68 | TB501 | 5 | <80
Ramjivan | 2024-08 | 17.29 | 0 |  | 0 | <80
Ramjivan | 2024-09 | 71.16 | 37.73 | TA325 | 1 | <80
Ramjivan | 2024-10 | 78.62 | 129.34 | TA325 | 1 | <80
Ranjan Kumar | 2025-11 | 36.04 | 36.04 | TA325 | 1 | <80
Ranjan Kumar | 2025-12 | 37.73 | 37.73 | TA414 | 1 | <80
Reeta Bharti | 2024-11 | 62.47 | 46.05 | TA416 | 1 | <80
Reeta Bharti | 2024-12 | 171.88 | 173.7 | TA416 | 4 | 160-180
Reeta Bharti | 2025-01 | 147.07 | 135.87 | TA416 | 3 | 140-160
Reeta Bharti | 2025-02 | 168.61 | 194.41 | TA416 | 4 | 160-180
Reeta Bharti | 2025-03 | 240.52 | 221.06 | TA416 | 4 | 240-260
Reeta Bharti | 2025-04 | 110.58 | 130.03 | TA416 | 2 | 100-120
Reeta Bharti | 2025-05 | 157.76 | 130.8 | TA416 | 3 | 140-160
Reeta Bharti | 2025-06 | 173.58 | 200.55 | TA416 | 4 | 160-180
Reeta Bharti | 2025-07 | 152.57 | 152.57 | TA416 | 2 | 140-160
Reeta Bharti | 2025-08 | 87.4 | 0 |  | 0 | 80-100
Reeta Bharti | 2025-09 | 117.54 | 161.36 | TA416 | 1 | 100-120
Reeta Bharti | 2025-10 | 58.11 | 101.69 | TA416 | 1 | <80
Rejaul | 2024-09 | 20.96 | 0 |  | 0 | <80
Rejaul | 2024-10 | 16.77 | 37.73 | TA325 | 1 | <80
Rohit | 2025-04 | 4.05 | 0 |  | 0 | <80
Rohit | 2025-05 | 6.61 | 0 |  | 0 | <80
Rohit | 2025-06 | 6.4 | 0 |  | 0 | <80
Rohit | 2025-07 | 6.61 | 0 |  | 0 | <80
Rohit | 2025-08 | 6.61 | 0 |  | 0 | <80
Rohit | 2025-09 | 6.4 | 0 |  | 0 | <80
Rohit | 2025-10 | 6.61 | 0 |  | 0 | <80
Rohit | 2025-11 | 51.3 | 0 |  | 0 | <80
Rohit | 2025-12 | 71.29 | 149.02 | TA419 | 3 | <80
Rohit | 2026-01 | 59.04 | 75.91 | TA419 | 1 | <80
Rudra Construction | 2025-01 | 46.05 | 46.05 | TA416 | 1 | <80
Rudra Construction | 2025-02 | 89.82 | 89.82 | TA416 | 2 | 80-100
Rudra Construction | 2025-03 | 46.05 | 46.05 | TA416 | 1 | <80
Rudra Construction | 2025-04 | 49.53 | 43.78 | TA416 | 1 | <80
Rudra Construction | 2025-05 | 82.67 | 88.42 | TA416 | 2 | 80-100
Rupesh | 2025-03 | 41.53 | 0 |  | 0 | <80
Rupesh | 2025-04 | 67.45 | 108.98 | TA325 | 2 | <80
Rupesh | 2025-05 | 11.26 | 0 |  | 0 | <80
Rupesh | 2025-06 | 42.23 | 0 |  | 0 | <80
Rupesh | 2025-07 | 43.63 | 0 |  | 0 | <80
Rupesh | 2025-08 | 43.63 | 0 |  | 0 | <80
Rupesh | 2025-09 | 32.37 | 173.13 | TA325 | 1 | <80
Rupesh | 2025-10 | 79.92 | 0 |  | 0 | <80
Rupesh | 2025-11 | 9.22 | 89.15 | TA325 | 1 | <80
S K Janarul | 2024-08 | 19.25 | 0 |  | 0 | <80
S K Janarul | 2024-09 | 17.12 | 36.37 | TA421 | 1 | <80
S K Janarul Sheikh | 2024-09 | 59.1 | 36.37 | TA421 | 1 | <80
S K Janarul Sheikh | 2024-10 | 50.01 | 72.74 | TA421 | 2 | <80
Saidur Rahaman | 2025-01 | 6.05 | 6.05 | TB501 | 1 | <80
Saidur Rahaman | 2025-02 | 13.68 | 13.68 | TB501 | 2 | <80
Sainik Trader | 2025-08 | 79.34 | 75.86 | TA416 | 1 | <80
Sainik Trader | 2025-09 | 102.85 | 87.01 | TA416 | 1 | 100-120
Sainik Trader | 2025-10 | 54.1 | 73.43 | TA416 | 1 | <80
Sainik Traders | 2025-01 | 3.96 | 0 |  | 0 | <80
Sainik Traders | 2025-02 | 4.62 | 0 |  | 0 | <80
Sainik Traders | 2025-03 | 17.09 | 0 |  | 0 | <80
Sainik Traders | 2025-04 | 21.19 | 0 |  | 0 | <80
Sainik Traders | 2025-05 | 21.89 | 0 |  | 0 | <80
Sainik Traders | 2025-06 | 25.07 | 0 |  | 0 | <80
Sainik Traders | 2025-07 | 100.23 | 72 | TA504 | 2 | 100-120
Sainik Traders | 2025-08 | 63.26 | 74 | TA504 | 2 | <80
Sainik Traders | 2025-09 | 19.94 | 60 | TA504 | 1 | <80
Sainik Traders | 2025-10 | 13.71 | 0 |  | 0 | <80
Sainik Traders | 2025-11 | 46.18 | 96 | TA504 | 2 | <80
Sainik Traders | 2025-12 | 105.86 | 141 | TA504 | 3 | 100-120
Sainik Traders | 2026-01 | 36 | 36 | TA504 | 1 | <80
Sakhila Khatun | 2025-08 | 6.19 | 0 |  | 0 | <80
Sakhila Khatun | 2025-09 | 9.28 | 0 |  | 0 | <80
Sakhila Khatun | 2025-10 | 9.59 | 0 |  | 0 | <80
Sakhila Khatun | 2025-11 | 39.26 | 0 |  | 0 | <80
Sakhila Khatun | 2025-12 | 104.57 | 168.88 | TA414 | 3 | 100-120
Sakila Khatun | 2025-10 | 127.44 | 65.76 | TA325 | 1 | 120-140
Sakila Khatun | 2025-11 | 209.53 | 271.22 | TA325 | 2 | 200-220
Sakila Khatun | 2026-01 | 37.73 | 37.73 | TA414 | 1 | <80
Sanjay Mahto | 2024-07 | 39.32 | 0 |  | 0 | <80
Sanjay Mahto | 2024-08 | 7.86 | 47.18 | TB401 | 1 | <80
Sanjeet | 2025-04 | 4.17 | 0 |  | 0 | <80
Sanjeet | 2025-05 | 6.8 | 0 |  | 0 | <80
Sanjeet | 2025-06 | 6.58 | 0 |  | 0 | <80
Sanjeet | 2025-07 | 6.8 | 0 |  | 0 | <80
Sanjeet | 2025-08 | 6.8 | 0 |  | 0 | <80
Sanjeet | 2025-09 | 6.58 | 0 |  | 0 | <80
Sanjeet | 2025-10 | 6.8 | 0 |  | 0 | <80
Sanjeet | 2025-11 | 6.58 | 0 |  | 0 | <80
Sanjeet | 2025-12 | 2.19 | 53.32 | TA419 | 1 | <80
Sanjeev Kumar | 2024-09 | 3.41 | 0 |  | 0 | <80
Sanjeev Kumar | 2024-10 | 115.96 | 112.51 | TB401, TB408 | 3 | 100-120
Sanjeev Kumar | 2024-11 | 70.84 | 77.69 | TB401, TB408 | 2 | <80
Sanjeev Kumar | 2024-12 | 132.61 | 113.86 | TB401, TB408 | 3 | 120-140
Sanjeev Kumar | 2025-01 | 146.89 | 153.14 | TB401, TB408 | 3 | 140-160
Sanjeev Kumar | 2025-02 | 145.14 | 106.73 | TB401, TB408 | 2 | 140-160
Sanjeev Kumar | 2025-03 | 94.66 | 145.57 | TB401, TB408 | 3 | 80-100
Sanjeev Kumar | 2025-08 | 23.44 | 0 |  | 0 | <80
Sanjeev Kumar | 2025-09 | 128.81 | 131.87 | TB401 | 3 | 120-140
Sanjeev Kumar | 2025-10 | 149.83 | 149.37 | TB401, TB408 | 2 | 140-160
Sanjeev Kumar | 2025-11 | 136.61 | 120.42 | TB408 | 3 | 120-140
Sanjeev Kumar | 2025-12 | 20.57 | 57.6 | TB408 | 1 | <80
Santosh Singh | 2025-10 | 36.88 | 0 |  | 0 | <80
Santosh Singh | 2025-11 | 67.01 | 103.89 | TB408 | 2 | <80
Santosh Singh Laxmi | 2025-12 | 47.18 | 47.18 | TB408 | 1 | <80
Satish Kumar | 2025-10 | 74.83 | 65.76 | TA325 | 1 | <80
Satish Kumar | 2025-11 | 54.44 | 63.51 | TA325 | 1 | <80
Satyam Enterprises | 2025-07 | 244.99 | 159.7 | TB408 | 4 | 240-260
Satyam Enterprises | 2025-08 | 247.16 | 332.45 | TB408 | 6 | 240-260
Satyam Enterprises Manish | 2025-08 | 19.42 | 0 |  | 0 | <80
Satyam Enterprises Manish | 2025-09 | 19.42 | 38.85 | TB408 | 1 | <80
Satyam Enterprises Pawan | 2025-08 | 38.85 | 38.85 | TB408 | 1 | <80
Satyam Enterprises Santosh | 2025-05 | 12.32 | 0 |  | 0 | <80
Satyam Enterprises Santosh | 2025-06 | 26.53 | 38.85 | TB408 | 1 | <80
Satyam Enterprises Vijay | 2025-06 | 38.85 | 38.85 | TB408 | 1 | <80
Satyam Enterprises Vijay | 2025-07 | 77.7 | 77.7 | TB408 | 2 | <80
Satyam Enterprises Vijay | 2025-09 | 37.5 | 37.5 | TB408 | 1 | <80
Satyam Manish | 2025-04 | 6.49 | 0 |  | 0 | <80
Satyam Manish | 2025-05 | 215.55 | 189.01 | TB401 | 2 | 200-220
Satyam Manish | 2025-06 | 230.99 | 264.02 | TB401 | 4 | 220-240
Satyam Manish | 2025-07 | 135.1 | 135.1 | TB401 | 3 | 120-140
Satyam Manish | 2025-08 | 198.54 | 198.54 | TB401, TB408 | 5 | 180-200
Satyam Manish 2 Santosh | 2025-06 | 21.58 | 0 |  | 0 | <80
Satyam Manish 2 Santosh | 2025-07 | 17.27 | 38.85 | TB401 | 1 | <80
Satyam Mondal | 2025-05 | 78.24 | 57.6 | TB401 | 1 | <80
Satyam Mondal | 2025-06 | 137.28 | 157.92 | TB401 | 4 | 120-140
Satyam Mondal | 2025-07 | 133.07 | 133.07 | TB401 | 2 | 120-140
Satyam Nitish | 2025-04 | 5.55 | 0 |  | 0 | <80
Satyam Nitish | 2025-05 | 220.04 | 184.56 | TB401 | 4 | 220-240
Satyam Nitish | 2025-06 | 246.17 | 287.2 | TB401 | 2 | 240-260
Satyam Nitish | 2025-07 | 160.47 | 160.47 | TB401 | 3 | 160-180
Satyam Santosh | 2025-05 | 4.41 | 0 |  | 0 | <80
Satyam Santosh | 2025-06 | 33.09 | 37.5 | TB401 | 1 | <80
Satyam Santosh | 2025-07 | 38.85 | 38.85 | TB401 | 1 | <80
Satyam Trading | 2025-03 | 2.53 | 0 |  | 0 | <80
Satyam Trading | 2025-04 | 3.8 | 0 |  | 0 | <80
Satyam Trading | 2025-05 | 3.92 | 0 |  | 0 | <80
Satyam Trading | 2025-06 | 3.8 | 0 |  | 0 | <80
Satyam Trading | 2025-07 | 3.92 | 0 |  | 0 | <80
Satyam Trading | 2025-08 | 3.92 | 0 |  | 0 | <80
Satyam Trading | 2025-09 | 10.61 | 0 |  | 0 | <80
Satyam Trading | 2025-10 | 15.04 | 0 |  | 0 | <80
Satyam Trading | 2025-11 | 58.33 | 43.78 | TA419 | 1 | <80
Satyam Trading | 2025-12 | 56.36 | 107.51 | TA419 | 3 | <80
Satyam Trading | 2026-01 | 32.83 | 43.78 | TA419 | 1 | <80
Satyam Trivedi | 2025-01 | 3.56 | 0 |  | 0 | <80
Satyam Trivedi | 2025-02 | 7.66 | 0 |  | 0 | <80
Satyam Trivedi | 2025-03 | 8.48 | 0 |  | 0 | <80
Satyam Trivedi | 2025-04 | 8.21 | 0 |  | 0 | <80
Satyam Trivedi | 2025-05 | 83.49 | 75.01 | TB401 | 2 | 80-100
Satyam Trivedi | 2025-06 | 106.54 | 136.45 | TB401 | 3 | 100-120
Satyam Trivedi | 2025-07 | 69.88 | 76.35 | TB401 | 2 | <80
Satyam Trivedi Nitish | 2025-07 | 38.85 | 38.85 | TB401 | 1 | <80
Satyam Vijay | 2025-05 | 49.44 | 38.85 | TB401 | 1 | <80
Satyam Vijay | 2025-06 | 67.1 | 77.69 | TB401 | 2 | <80
Satyam Vijay | 2025-07 | 112.51 | 112.51 | TB401 | 3 | 100-120
Satyam Vijay | 2025-08 | 147.05 | 147.05 | TB401 | 3 | 140-160
Savitha | 2025-07 | 17.72 | 0 |  | 0 | <80
Savitha | 2025-08 | 39.28 | 57 | TA418 | 2 | <80
Savitha | 2025-09 | 40.34 | 0 |  | 0 | <80
Savitha | 2025-10 | 4.66 | 45 | TA418 | 1 | <80
Senahul | 2024-09 | 54.37 | 39.46 | TA325 | 1 | <80
Senahul | 2024-10 | 24.55 | 39.46 | TA325 | 1 | <80
Senahul | 2024-11 | 67.91 | 54.42 | TA325 | 1 | <80
Senahul | 2024-12 | 150.17 | 150.06 | TA325 | 2 | 140-160
Senahul | 2025-01 | 104.32 | 117.93 | TA325 | 2 | 100-120
Senahul | 2025-02 | 88.17 | 64.25 | TA325 | 1 | 80-100
Senahul | 2025-03 | 53.8 | 77.72 | TA325 | 1 | <80
Senahul | 2025-04 | 89.1 | 82.24 | TA325 | 1 | 80-100
Senahul | 2025-05 | 30.87 | 37.73 | TA325 | 1 | <80
Senahul Modina India 3 | 2025-05 | 5.08 | 0 |  | 0 | <80
Senahul Modina India 3 | 2025-06 | 8.03 | 0 |  | 0 | <80
Senahul Modina India 3 | 2025-07 | 8.3 | 0 |  | 0 | <80
Senahul Modina India 3 | 2025-08 | 8.3 | 0 |  | 0 | <80
Senahul Modina India 3 | 2025-09 | 8.03 | 37.73 | TA325 | 1 | <80
Senaul | 2025-09 | 25.82 | 0 |  | 0 | <80
Senaul | 2025-10 | 11.91 | 37.73 | TA325 | 1 | <80
Shakila Khatun | 2025-08 | 8 | 0 |  | 0 | <80
Shakila Khatun | 2025-09 | 75.03 | 83.03 | TA421 | 2 | <80
Sheetal Singh | 2025-08 | 38.85 | 38.85 | TB408 | 1 | <80
Sheetal Singh | 2025-12 | 111.79 | 111.79 | TB408 | 2 | 100-120
Sheetal Singh 1 | 2025-09 | 63.85 | 38.85 | TB408 | 1 | <80
Sheetal Singh 1 | 2025-10 | 12.5 | 37.5 | TB408 | 1 | <80
Sheetal Singh 2 | 2025-08 | 18.28 | 0 |  | 0 | <80
Sheetal Singh 2 | 2025-09 | 20.57 | 38.85 | TB408 | 1 | <80
Shila Devi | 2025-08 | 154 | 132.75 | TA505 | 2 | 140-160
Shila Devi | 2025-09 | 162.88 | 184.13 | TA505 | 3 | 160-180
Shila Devi | 2025-10 | 81.83 | 81.83 | TA505 | 1 | 80-100
Shila Devi | 2025-11 | 86.71 | 71.76 | TA505 | 2 | 80-100
Shila Devi | 2025-12 | 217.64 | 232.59 | TA505 | 4 | 200-220
Shila Devi | 2026-01 | 137.19 | 137.19 | TA505 | 2 | 120-140
Shobha Devi | 2025-08 | 100.87 | 82.92 | TB408 | 2 | 100-120
Shobha Devi | 2025-09 | 282.53 | 287.2 | TB408 | 2 | >=260
Shobha Devi | 2025-10 | 309.72 | 286.82 | TB408 | 5 | >=260
Shobha Devi | 2025-11 | 217.47 | 253.65 | TB408 | 5 | 200-220
Shobha Devi | 2025-12 | 197.98 | 197.98 | TB408 | 4 | 180-200
Shobha Devi | 2026-01 | 45.41 | 45.41 | TB408 | 1 | <80
Shree Ganesh Sital Enterprice | 2025-01 | 3.08 | 0 |  | 0 | <80
Shree Ganesh Sital Enterprice | 2025-02 | 39.25 | 39.85 | TB501 | 7 | <80
Shree Ganesh Sital Enterprice | 2025-03 | 44.36 | 46.85 | TB501 | 7 | <80
Shree Karni Entp | 2025-05 | 6.05 | 6.05 | TB501 | 1 | <80
Shri Karni Construction | 2025-01 | 3.23 | 0 |  | 0 | <80
Shri Karni Construction | 2025-02 | 6.76 | 0 |  | 0 | <80
Shri Karni Construction | 2025-03 | 8.74 | 0 |  | 0 | <80
Shri Karni Construction | 2025-04 | 12.21 | 0 |  | 0 | <80
Shri Karni Construction | 2025-05 | 10.94 | 17 | TA506 | 1 | <80
Shri Karni Construction | 2025-06 | 11.94 | 0 |  | 0 | <80
Shri Karni Construction | 2025-07 | 16.64 | 0 |  | 0 | <80
Shri Karni Construction | 2025-08 | 17.74 | 21 | TA506 | 1 | <80
Shri Karni Construction | 2025-09 | 510.4 | 502 | TA506 | 24 | >=260
Shri Karni Construction | 2025-10 | 12.51 | 0 |  | 0 | <80
Shri Karni Construction | 2025-11 | 6.6 | 36 | TA506 | 2 | <80
Shri Karni Construction | 2025-12 | 1.27 | 43 | TA506 | 1 | <80
Shri Shyam | 2025-11 | 45.41 | 45.41 | TB401 | 1 | <80
Shri Shyam Construction | 2025-09 | 45.41 | 45.41 | TB408 | 1 | <80
Shri Shyam Construction | 2025-10 | 37.5 | 37.5 | TB408 | 1 | <80
Shyam Construction | 2025-10 | 38.85 | 38.85 | TB401 | 1 | <80
Sintu Pawan Satyam Enterprises | 2025-08 | 66.38 | 66.38 | TB408 | 1 | <80
Sital Singh | 2025-08 | 75.01 | 75.01 | TB401 | 2 | <80
Sital Singh | 2025-11 | 41.14 | 0 |  | 0 | <80
Sital Singh | 2025-12 | 16.46 | 57.6 | TB401 | 1 | <80
Sital Singh 1 | 2025-09 | 80.93 | 77.69 | TB401 | 2 | 80-100
Sital Singh 1 | 2025-10 | 150.8 | 154.04 | TB401 | 3 | 140-160
Sital Singh 2 | 2025-08 | 38.85 | 38.85 | TB401 | 1 | <80
Sital Singh 2 | 2025-09 | 37.5 | 37.5 | TB401 | 1 | <80
Sk Samirul | 2025-06 | 3.78 | 0 |  | 0 | <80
Sk Samirul | 2025-07 | 6.17 | 0 |  | 0 | <80
Sk Samirul | 2025-08 | 6.17 | 0 |  | 0 | <80
Sk Samirul | 2025-09 | 5.97 | 0 |  | 0 | <80
Sk Samirul | 2025-10 | 6.17 | 0 |  | 0 | <80
Sk Samirul | 2025-11 | 5.97 | 0 |  | 0 | <80
Sk Samirul | 2025-12 | 3.78 | 38.04 | TA414 | 1 | <80
Sk Samiul 1 | 2025-07 | 52.19 | 0 |  | 0 | <80
Sk Samiul 1 | 2025-08 | 111.98 | 131.31 | TA413 | 3 | 100-120
Sk Samiul 1 | 2025-09 | 85.73 | 89.5 | TA413 | 2 | 80-100
Sk Samiul 1 | 2025-10 | 72.07 | 101.15 | TA413 | 2 | <80
Sk Samiul 2 | 2025-07 | 31.24 | 0 |  | 0 | <80
Sk Samiul 2 | 2025-08 | 114.22 | 145.46 | TA413 | 4 | 100-120
Sk Samiul Dildar Electricals 1 | 2025-11 | 90.6 | 0 |  | 0 | 80-100
Sk Samiul Dildar Electricals 1 | 2025-12 | 8.24 | 98.84 | TA325 | 1 | <80
Sk Samiul Sima Khatun | 2025-12 | 56.62 | 37.73 | TA414 | 1 | <80
Sk Samiul Sima Khatun | 2026-01 | 44.06 | 62.95 | TA414 | 1 | <80
Sk Samuil | 2024-09 | 5.61 | 0 |  | 0 | <80
Sk Samuil | 2024-10 | 24.83 | 0 |  | 0 | <80
Sk Samuil | 2024-11 | 75.25 | 75.5 | TA325 | 2 | <80
Sk Samuil | 2024-12 | 124.27 | 141.73 | TA325 | 3 | 120-140
Sk Samuil | 2025-01 | 58.96 | 39.46 | TA325 | 1 | <80
Sk Samuil | 2025-02 | 194.2 | 226.43 | TA325 | 6 | 180-200
Sk Samuil | 2025-03 | 202.4 | 159.65 | TA325 | 4 | 200-220
Sk Samuil | 2025-04 | 177.67 | 212.34 | TA325 | 5 | 160-180
Sk Samuil | 2025-05 | 74.37 | 82.46 | TA325 | 2 | <80
Sobha Devi | 2023-09 | 106.26 | 75.01 | TB401 | 2 | 100-120
Sobha Devi | 2023-10 | 257.51 | 265.21 | TB401 | 7 | 240-260
Sobha Devi | 2023-11 | 286.49 | 270.59 | TB401 | 7 | >=260
Sobha Devi | 2023-12 | 287.83 | 269.24 | TB401 | 6 | >=260
Sobha Devi | 2024-01 | 200.79 | 258.83 | TB401 | 6 | 200-220
Sobha Devi | 2024-02 | 273.58 | 263.87 | TB401, TB408 | 7 | >=260
Sobha Devi | 2024-03 | 301.06 | 277.58 | TB408 | 7 | >=260
Sobha Devi | 2024-04 | 231.56 | 253.65 | TB401, TB408 | 5 | 220-240
Sobha Devi | 2024-05 | 150.86 | 161.96 | TB408 | 4 | 140-160
Sobha Devi | 2024-08 | 121.6 | 115.2 | TB401, TB408 | 3 | 120-140
Sobha Devi | 2024-09 | 264.02 | 239.34 | TB401, TB408 | 5 | >=260
Sobha Devi | 2024-10 | 250.56 | 281.64 | TB408 | 6 | 240-260
Sobha Devi | 2024-11 | 276.24 | 276.24 | TB408 | 7 | >=260
Sobha Devi | 2024-12 | 268.01 | 245.3 | TB401, TB408 | 6 | >=260
Sobha Devi | 2025-01 | 279.64 | 273.9 | TB401 | 6 | >=260
Sobha Devi | 2025-02 | 240.47 | 268.92 | TB401, TB408 | 4 | 240-260
Sobha Devi | 2025-03 | 268.34 | 255.39 | TB401 | 6 | >=260
Sobha Devi | 2025-04 | 263.29 | 276.24 | TB401, TB408 | 7 | >=260
Sobha Devi | 2025-08 | 76.35 | 76.35 | TB408 | 2 | <80
Sobha Devi | 2025-11 | 82.92 | 82.92 | TB401, TB408 | 2 | 80-100
Spotyfy | 2025-09 | 26.66 | 0 |  | 0 | <80
Spotyfy | 2025-10 | 26.66 | 53.32 | TA416 | 1 | <80
Spotyfy 3 | 2025-08 | 15.61 | 0 |  | 0 | <80
Spotyfy 3 | 2025-09 | 26.76 | 42.37 | TA416 | 1 | <80
Srikarni | 2025-06 | 3.18 | 0 |  | 0 | <80
Srikarni | 2025-07 | 7.96 | 11.14 | TB507 | 1 | <80
Srvan Kumar | 2025-12 | 37.73 | 37.73 | TA414 | 1 | <80
Subash | 2024-10 | 72.16 | 37.93 | TA421 | 1 | <80
Subash | 2024-11 | 223.59 | 231.84 | TA421 | 5 | 220-240
Subash | 2024-12 | 310.82 | 294.08 | TA421 | 8 | >=260
Subash | 2025-01 | 249.39 | 277.56 | TA421 | 7 | 240-260
Subash | 2025-02 | 232.34 | 234.76 | TA421 | 6 | 220-240
Subash | 2025-03 | 329.71 | 319.08 | TA421 | 8 | >=260
Subash | 2025-04 | 307.67 | 330.43 | TA421 | 8 | >=260
Subash | 2025-05 | 290.3 | 267.54 | TA421 | 7 | >=260
Subash | 2025-06 | 248.69 | 253.98 | TA421 | 5 | 240-260
Subash | 2025-07 | 236.25 | 253.72 | TA421 | 7 | 220-240
Subash | 2025-08 | 202.38 | 202.38 | TA421 | 5 | 200-220
Subash | 2025-09 | 228.1 | 228.1 | TA421 | 7 | 220-240
Subash | 2025-10 | 181.05 | 175.72 | TA421 | 4 | 180-200
Subash | 2025-11 | 262.97 | 260.76 | TA421 | 7 | >=260
Subash | 2025-12 | 388.78 | 384.54 | TA421 | 10 | >=260
Subash | 2026-01 | 92 | 103.79 | TA421 | 2 | 80-100
Subhash | 2025-08 | 134.26 | 103.2 | TA418 | 2 | 120-140
Subhash | 2025-09 | 184.61 | 149.9 | TA418 | 4 | 180-200
Subhash | 2025-10 | 149.12 | 198.83 | TA325, TA418 | 3 | 140-160
Subhash | 2025-11 | 203.58 | 206.13 | TA325 | 2 | 200-220
Subhash | 2025-12 | 128.36 | 141.87 | TA325 | 1 | 120-140
Subhash | 2026-01 | 37.73 | 37.73 | TA414 | 1 | <80
Subhash Kumar | 2025-08 | 5.22 | 0 |  | 0 | <80
Subhash Kumar | 2025-09 | 7.83 | 0 |  | 0 | <80
Subhash Kumar | 2025-10 | 8.1 | 0 |  | 0 | <80
Subhash Kumar | 2025-11 | 7.83 | 0 |  | 0 | <80
Subhash Kumar | 2025-12 | 7.05 | 36.04 | TA414 | 1 | <80
Sudheer 2 Priyanka Devi | 2025-09 | 57.6 | 57.6 | TB408 | 1 | <80
Sukhriddin | 2024-07 | 48.21 | 37.73 | TA325 | 1 | <80
Sukhriddin | 2024-08 | 64.92 | 37.73 | TA325 | 1 | <80
Sukhriddin | 2024-09 | 73.34 | 92.15 | TA325 | 2 | <80
Sukhriddin | 2024-10 | 78.55 | 92.15 | TA325 | 2 | <80
Sukhriddin | 2024-11 | 83.85 | 82.46 | TA325 | 2 | 80-100
Sukhriddin | 2024-12 | 82.41 | 75.46 | TA325 | 2 | 80-100
Sukhriddin | 2025-01 | 78.54 | 92.15 | TA325 | 2 | <80
Sukhriddin | 2025-02 | 51.03 | 37.73 | TA325 | 1 | <80
Sukhriddin | 2025-03 | 128.57 | 141.87 | TA325 | 1 | 120-140
Sukhriddin | 2025-04 | 141.87 | 141.87 | TA325 | 1 | 140-160
Sukhriddin | 2025-05 | 37.73 | 37.73 | TA325 | 1 | <80
Sukhrridin | 2025-09 | 25.23 | 0 |  | 0 | <80
Sukhrridin | 2025-10 | 48.54 | 73.78 | TA325 | 2 | <80
Sukruddin | 2025-10 | 69.84 | 37.73 | TA325 | 1 | <80
Sukruddin | 2025-11 | 170.75 | 170.17 | TA325 | 2 | 160-180
Sukruddin | 2025-12 | 140.08 | 172.77 | TA325 | 1 | 140-160
Sulen Sarkar | 2025-02 | 19.73 | 0 |  | 0 | <80
Sulen Sarkar | 2025-03 | 96.92 | 116.65 | TA325 | 3 | 80-100
Sulen Sarkar | 2025-04 | 122.08 | 122.08 | TA325 | 3 | 120-140
Sulen Sarkar | 2025-05 | 37.73 | 37.73 | TA325 | 1 | <80
Suman | 2025-08 | 8.41 | 8.41 | TB501 | 1 | <80
Suman | 2025-11 | 5 | 0 |  | 0 | <80
Suman | 2025-12 | 36.87 | 40.42 | TB501 | 5 | <80
Suman | 2026-01 | 19.72 | 21.16 | TB501 | 3 | <80
Sunny Const | 2023-09 | 69.65 | 37.5 | TB401 | 1 | <80
Sunny Const | 2023-10 | 200.25 | 227.71 | TB401 | 6 | 200-220
Sunny Const | 2023-11 | 188.38 | 187.52 | TB401 | 5 | 180-200
Sunny Const | 2023-12 | 180.3 | 171.45 | TB401 | 4 | 180-200
Sunny Const | 2024-01 | 163.3 | 152.7 | TB401 | 3 | 160-180
Sunny Const | 2024-02 | 213.17 | 230.4 | TB401, TB408 | 6 | 200-220
Sunny Const | 2024-03 | 122.97 | 115.2 | TB408 | 3 | 120-140
Sunny Const | 2024-04 | 230.49 | 220.43 | TB401, TB408 | 5 | 220-240
Sunny Const | 2024-05 | 182.01 | 207.61 | TB401, TB408 | 5 | 180-200
Sunny Const | 2024-08 | 32.82 | 0 |  | 0 | <80
Sunny Const | 2024-09 | 240.41 | 258.22 | TB401 | 6 | 240-260
Sunny Const | 2024-10 | 240.08 | 255.08 | TB401 | 5 | 240-260
Sunny Const | 2024-11 | 245.12 | 245.12 | TB401 | 6 | 240-260
Sunny Const | 2024-12 | 247.27 | 247.27 | TB401 | 4 | 240-260
Sunny Const | 2025-01 | 174.1 | 165.8 | TB401, TB408 | 3 | 160-180
Sunny Const | 2025-02 | 218.75 | 210.46 | TB401, TB408 | 4 | 200-220
Sunny Const | 2025-03 | 254.76 | 221.77 | TB401 | 4 | 240-260
Sunny Const | 2025-04 | 164.94 | 207.89 | TB401, TB408 | 4 | 160-180
Sunny Const | 2025-05 | 145.87 | 152.51 | TB401 | 2 | 140-160
Sunny Const | 2025-10 | 102.22 | 86.03 | TB401 | 2 | 100-120
Sunny Const | 2025-11 | 176.56 | 192.75 | TB401 | 4 | 160-180
Sunny Const | 2025-12 | 76.35 | 76.35 | TB401 | 2 | <80
Sunny Construction | 2025-05 | 81.49 | 81.49 | TB408 | 1 | 80-100
Sunny Construction | 2025-08 | 84.69 | 84.69 | TB408 | 2 | 80-100
Sunny Construction | 2025-09 | 243.82 | 238.17 | TB408 | 5 | 240-260
Sunny Construction | 2025-10 | 99.72 | 105.38 | TB408 | 2 | 80-100
Sunny Construction | 2025-12 | 122.19 | 122.19 | TB408 | 3 | 120-140
Sunny Construction | 2026-01 | 47.18 | 47.18 | TB408 | 1 | <80
Suraj Const | 2023-10 | 168.01 | 151.36 | TB401 | 4 | 160-180
Suraj Const | 2023-11 | 230.63 | 231.74 | TB401 | 6 | 220-240
Suraj Const | 2023-12 | 227.81 | 230.4 | TB401 | 6 | 220-240
Suraj Const | 2024-01 | 179.27 | 172.8 | TB401 | 4 | 160-180
Suraj Const | 2024-02 | 208.29 | 227.71 | TB401, TB408 | 6 | 200-220
Suraj Const | 2024-04 | 213.75 | 191.55 | TB408 | 5 | 200-220
Suraj Const | 2024-05 | 213.13 | 235.33 | TB408 | 5 | 200-220
Surender Mahto | 2025-01 | 44.73 | 44.73 | TA325 | 1 | <80
Tajirul | 2025-01 | 28.18 | 0 |  | 0 | <80
Tajirul | 2025-02 | 45.34 | 39.46 | TA325 | 1 | <80
Tajirul | 2025-03 | 12.55 | 46.62 | TA325 | 1 | <80
Tejal | 2025-03 | 2.67 | 0 |  | 0 | <80
Tejal | 2025-04 | 3.48 | 0 |  | 0 | <80
Tejal | 2025-05 | 3.59 | 0 |  | 0 | <80
Tejal | 2025-06 | 3.48 | 0 |  | 0 | <80
Tejal | 2025-07 | 3.59 | 0 |  | 0 | <80
Tejal | 2025-08 | 3.59 | 0 |  | 0 | <80
Tejal | 2025-09 | 20.48 | 17 | TA506 | 1 | <80
Tejal | 2025-10 | 3.59 | 0 |  | 0 | <80
Tejal | 2025-11 | 3.48 | 0 |  | 0 | <80
Tejal | 2025-12 | 1.04 | 32 | TA506 | 1 | <80
Tejal Const | 2025-08 | 10 | 0 |  | 0 | <80
Tejal Const | 2025-09 | 13.64 | 0 |  | 0 | <80
Tejal Const | 2025-10 | 6.36 | 30 | TA506 | 1 | <80
Tejal Construction | 2024-02 | 115.2 | 115.2 | TB401 | 3 | 100-120
Tejal Mahto | 2025-02 | 5.95 | 0 |  | 0 | <80
Tejal Mahto | 2025-03 | 10.25 | 0 |  | 0 | <80
Tejal Mahto | 2025-04 | 9.92 | 0 |  | 0 | <80
Tejal Mahto | 2025-05 | 10.25 | 0 |  | 0 | <80
Tejal Mahto | 2025-06 | 6.42 | 40 | TA506 | 1 | <80
Tejal Mahto | 2025-07 | 4.54 | 0 |  | 0 | <80
Tejal Mahto | 2025-08 | 4.54 | 0 |  | 0 | <80
Tejal Mahto | 2025-09 | 4.39 | 0 |  | 0 | <80
Tejal Mahto | 2025-10 | 1.76 | 18 | TA506 | 1 | <80
Teklal Mahto | 2025-10 | 64.02 | 37.73 | TA325 | 1 | <80
Teklal Mahto | 2025-11 | 37.97 | 64.25 | TA325 | 1 | <80
Thanu Mahto | 2024-09 | 1.78 | 0 |  | 0 | <80
Thanu Mahto | 2024-10 | 61.04 | 56.86 | TA325 | 1 | <80
Thanu Mahto | 2024-11 | 75.31 | 37.73 | TA325 | 1 | <80
Thanu Mahto | 2024-12 | 105.73 | 149.26 | TA325 | 2 | 100-120
Thanu Mahto | 2025-01 | 121.15 | 90.46 | TA325 | 2 | 120-140
Thanu Mahto | 2025-02 | 135.98 | 141.44 | TA325 | 3 | 120-140
Thanu Mahto | 2025-03 | 82.9 | 108.13 | TA325 | 3 | 80-100
Thanu Mahto | 2025-04 | 39.46 | 39.46 | TA325 | 1 | <80
Thanu Mahto | 2025-05 | 14.91 | 0 |  | 0 | <80
Thanu Mahto | 2025-06 | 29.82 | 44.73 | TA325 | 1 | <80
Toshan Mahato | 2025-09 | 84.08 | 81.3 | TA505 | 2 | 80-100
Toshan Mahato | 2025-10 | 115.61 | 91.61 | TA505 | 2 | 100-120
Toshan Mahato | 2025-11 | 124.42 | 65.03 | TA505 | 1 | 120-140
Toshan Mahato | 2025-12 | 135.95 | 222.12 | TA505 | 2 | 120-140
Uma Const | 2024-08 | 11.54 | 0 |  | 0 | <80
Uma Const | 2024-09 | 121.81 | 112.51 | TB408 | 3 | 120-140
Uma Const | 2024-10 | 137.01 | 130.1 | TB408 | 3 | 120-140
Uma Const | 2024-11 | 49.95 | 77.7 | TB408 | 2 | <80
Uma Devi | 2025-12 | 17.07 | 0 |  | 0 | <80
Uma Devi | 2026-01 | 19.51 | 36.57 | TA601 | 1 | <80
Usha Tower | 2025-07 | 38.85 | 38.85 | TB401 | 1 | <80
Usha Tower | 2025-08 | 90.74 | 84.26 | TB401, TB408 | 2 | 80-100
Usha Tower | 2025-09 | 69.88 | 76.35 | TB401, TB408 | 2 | <80
Vasu Dev Singh 1 | 2024-11 | 62.44 | 36.16 | TA413 | 1 | <80
Vasu Dev Singh 1 | 2024-12 | 107.25 | 126.64 | TA413 | 3 | 100-120
Vasu Dev Singh 1 | 2025-01 | 189.36 | 194.35 | TA413 | 4 | 180-200
Vasu Dev Singh 1 | 2025-02 | 62.07 | 36.16 | TA413 | 1 | <80
Vasu Dev Singh 1 | 2025-03 | 10.11 | 37.93 | TA413 | 1 | <80
Vasu Dev Singh 2 | 2024-11 | 48.57 | 37.93 | TA413 | 1 | <80
Vasu Dev Singh 2 | 2024-12 | 105.71 | 108.09 | TA413 | 3 | 100-120
Vasu Dev Singh 2 | 2025-01 | 84.64 | 80.94 | TA413 | 2 | 80-100
Vasu Dev Singh 2 | 2025-02 | 105.95 | 103.3 | TA413 | 2 | 100-120
Vasu Dev Singh 2 | 2025-03 | 130.87 | 133.03 | TA413 | 3 | 120-140
Vasu Dev Singh 2 | 2025-04 | 45.54 | 57.96 | TA413 | 1 | <80
Ved Prakash | 2025-08 | 26.55 | 0 |  | 0 | <80
Ved Prakash | 2025-09 | 212.42 | 222.27 | TA413 | 6 | 200-220
Ved Prakash | 2025-10 | 181.75 | 66.78 | TA413 | 1 | 180-200
Ved Prakash | 2025-11 | 222.4 | 347.12 | TA413 | 2 | 220-240
Ved Prakash | 2025-12 | 219.96 | 226.9 | TA413 | 2 | 200-220
Vedanta Const | 2025-11 | 75.31 | 47.18 | TB401 | 1 | <80
Vedanta Const | 2025-12 | 9.38 | 37.5 | TB401 | 1 | <80
Vedanta Construction | 2025-10 | 15.44 | 0 |  | 0 | <80
Vedanta Construction | 2025-11 | 16.55 | 0 |  | 0 | <80
Vedanta Construction | 2025-12 | 122.72 | 150.02 | TB408 | 4 | 120-140
Vedanta Construction | 2026-01 | 32.82 | 37.5 | TB408 | 1 | <80
Vinay Const | 2025-06 | 22.2 | 0 |  | 0 | <80
Vinay Const | 2025-07 | 111.01 | 133.22 | TB401 | 3 | 100-120
Vinay Const 2 | 2025-07 | 38.85 | 38.85 | TB401 | 1 | <80
Vinay Construction | 2025-07 | 21.19 | 0 |  | 0 | <80
Vinay Construction | 2025-08 | 175.15 | 172.06 | TB408 | 4 | 160-180
Vinay Construction | 2025-09 | 14.57 | 38.85 | TB408 | 1 | <80
Vinay Construction | 2025-10 | 53.72 | 37.5 | TB408 | 1 | <80
Vinay Construction | 2025-11 | 112.11 | 128.33 | TB408 | 3 | 100-120
Vinay Construction | 2025-12 | 38.85 | 38.85 | TB408 | 1 | <80
Vinay Construction | 2026-01 | 38.23 | 38.23 | TB507 | 2 | <80
Vinay Construction Chinta Devi | 2025-09 | 37.5 | 37.5 | TB408 | 1 | <80
Vinay Gupta | 2025-12 | 45.41 | 45.41 | TB408 | 1 | <80
Vinod | 2025-07 | 3.34 | 0 |  | 0 | <80
Vinod | 2025-08 | 4.5 | 0 |  | 0 | <80
Vinod | 2025-09 | 47.35 | 43 | TA506 | 1 | <80
Vinod | 2025-10 | 4.5 | 0 |  | 0 | <80
Vinod | 2025-11 | 1.31 | 18 | TA506 | 1 | <80
Vivek Ganju | 2025-09 | 58.6 | 37.5 | TB408 | 1 | <80
Vivek Ganju | 2025-10 | 81.24 | 82.92 | TB401, TB408 | 2 | 80-100
Vivek Ganju | 2025-11 | 111.18 | 116.54 | TB401 | 3 | 100-120
Vivek Ganju | 2025-12 | 138.64 | 152.7 | TB401, TB408 | 4 | 120-140
Yadhav D K Verma | 2025-09 | 23.71 | 0 |  | 0 | <80
Yadhav D K Verma | 2025-10 | 14.22 | 37.93 | TA421 | 1 | <80
Yogendra Mahto | 2024-08 | 129.53 | 121.76 | TB401, TB408 | 3 | 120-140
Yogendra Mahto | 2024-09 | 152.88 | 115.2 | TB408 | 3 | 140-160
Yogendra Mahto | 2024-10 | 107.11 | 152.56 | TB401 | 3 | 100-120
Yogendra Mahto | 2024-11 | 144.94 | 133.22 | TB401, TB408 | 3 | 140-160
Yogendra Mahto | 2024-12 | 106.98 | 89.91 | TB401 | 1 | 100-120
Yogendra Mahto | 2025-01 | 67.65 | 96.44 | TB408 | 2 | <80
Zainab Fatima | 2025-09 | 10.62 | 0 |  | 0 | <80
Zainab Fatima | 2025-10 | 16.47 | 0 |  | 0 | <80
Zainab Fatima | 2025-11 | 6.91 | 34 | TA506 | 1 | <80
Zakir Hussain | 2025-06 | 3.73 | 0 |  | 0 | <80
Zakir Hussain | 2025-07 | 6.09 | 0 |  | 0 | <80
Zakir Hussain | 2025-08 | 6.09 | 0 |  | 0 | <80
Zakir Hussain | 2025-09 | 5.9 | 0 |  | 0 | <80
Zakir Hussain | 2025-10 | 6.09 | 0 |  | 0 | <80
Zakir Hussain | 2025-11 | 5.9 | 0 |  | 0 | <80
Zakir Hussain | 2025-12 | 3.93 | 37.73 | TA414 | 1 | <80

## PCH Mr. Sanjay Kumar Gupta
Scope: 2026-01-01 to 2026-01-31 ¦ Projects: 16 ¦ Erections: 127 ¦ Gangs: 83
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
Mr. Sanjay Kumar Gupta | TA413 | 5.22 | 4.97 | 0 | 0 | 0 | 5.12 | 78.59 | 2
Mr. Sanjay Kumar Gupta | TA419 | 3.07 | 3.75 | 4.03 | 0 | 0 | 3.29 | 668.01 | 12
Mr. Sanjay Kumar Gupta | TA512 | 3.38 | 3.44 | 4.09 | 0 | 0 | 3.57 | 998.25 | 24
Mr. Sanjay Kumar Gupta | TB408 | 4.22 | 4.29 | 7.77 | 0 | 0 | 4.51 | 298.62 | 7
Mr. Sanjay Kumar Gupta | TB507 | 1.65 | 2.08 | 2.21 | 0 | 0 | 1.99 | 138.33 | 9
[7 empty] | Total | 2181.8 | 54
Erection productivity | Jan'26
PCH Overall
Erection productivity | Jan'26
Weight/day (Avg) | 3.43
No of Gangs engaged (Avg) | 36
Erection productivity | Jan'26
Project: TA413
Erection productivity | Jan'26
Weight/day (Avg) | 5.12
No of Gangs engaged (Avg) | 1
Erection productivity | Jan'26
Project: TA419
Erection productivity | Jan'26
Weight/day (Avg) | 3.29
No of Gangs engaged (Avg) | 11
Erection productivity | Jan'26
Project: TA512
Erection productivity | Jan'26
Weight/day (Avg) | 3.57
No of Gangs engaged (Avg) | 13
Erection productivity | Jan'26
Project: TB408
Erection productivity | Jan'26
Weight/day (Avg) | 4.51
No of Gangs engaged (Avg) | 6
Erection productivity | Jan'26
Project: TB507
Erection productivity | Jan'26
Weight/day (Avg) | 1.99
No of Gangs engaged (Avg) | 5

## PCH Mr. Arun Felbin
Scope: 2026-01-01 to 2026-01-31 ¦ Projects: 16 ¦ Erections: 127 ¦ Gangs: 83
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
Mr. Arun Felbin | TA325 | 3.69 | 3.67 | 0 | 0 | 0 | 3.68 | 280.48 | 2
Mr. Arun Felbin | TA414 | 2.17 | 2.17 | 4 | 0 | 0 | 2.79 | 331.65 | 8
Mr. Arun Felbin | TA416 | 3.03 | 3.21 | 3.17 | 0 | 0 | 3.11 | 647.95 | 6
Mr. Arun Felbin | TA418 | 3.82 | 4.32 | 5.46 | 0 | 0 | 4.36 | 283 | 7
Mr. Arun Felbin | TA421 | 7.66 | 6.8 | 0 | 0 | 0 | 7.34 | 268.4 | 6
Mr. Arun Felbin | TA504 | 0 | 4.5 | 4.5 | 0 | 0 | 4.5 | 36 | 1
Mr. Arun Felbin | TA505 | 5.65 | 5.23 | 5.27 | 0 | 0 | 5.41 | 1233.4 | 26
Mr. Arun Felbin | TA506 | 4.6 | 4.67 | 4.65 | 0 | 0 | 4.65 | 192 | 8
Mr. Arun Felbin | TA601 | 2.8 | 2.44 | 0 | 0 | 0 | 2.76 | 73.15 | 2
Mr. Arun Felbin | TB501 | 2.82 | 0 | 0 | 0 | 0 | 2.82 | 21.16 | 3
[7 empty] | Total | 3367.19 | 69
Erection productivity | Jan'26
PCH Overall
Erection productivity | Jan'26
Weight/day (Avg) | 4.34
No of Gangs engaged (Avg) | 46
Erection productivity | Jan'26
Project: TA325
Erection productivity | Jan'26
Weight/day (Avg) | 3.68
No of Gangs engaged (Avg) | 2
Erection productivity | Jan'26
Project: TA414
Erection productivity | Jan'26
Weight/day (Avg) | 2.79
No of Gangs engaged (Avg) | 8
Erection productivity | Jan'26
Project: TA416
Erection productivity | Jan'26
Weight/day (Avg) | 3.11
No of Gangs engaged (Avg) | 6
Erection productivity | Jan'26
Project: TA418
Erection productivity | Jan'26
Weight/day (Avg) | 4.36
No of Gangs engaged (Avg) | 3
Erection productivity | Jan'26
Project: TA421
Erection productivity | Jan'26
Weight/day (Avg) | 7.34
No of Gangs engaged (Avg) | 4
Erection productivity | Jan'26
Project: TA504
Erection productivity | Jan'26
Weight/day (Avg) | 4.5
No of Gangs engaged (Avg) | 1
Erection productivity | Jan'26
Project: TA505
Erection productivity | Jan'26
Weight/day (Avg) | 5.41
No of Gangs engaged (Avg) | 12
Erection productivity | Jan'26
Project: TA506
Erection productivity | Jan'26
Weight/day (Avg) | 4.65
No of Gangs engaged (Avg) | 7
Erection productivity | Jan'26
Project: TA601
Erection productivity | Jan'26
Weight/day (Avg) | 2.76
No of Gangs engaged (Avg) | 2
Erection productivity | Jan'26
Project: TB501
Erection productivity | Jan'26
Weight/day (Avg) | 2.82
No of Gangs engaged (Avg) | 1

## PCH Mr. Dheeraj Vashishth
Scope: 2026-01-01 to 2026-01-31 ¦ Projects: 16 ¦ Erections: 127 ¦ Gangs: 83
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
Mr. Dheeraj Vashishth | TB605 | 1.84 | 1.86 | 3.05 | 3.66 | 0 | 2.17 | 77.64 | 4
[7 empty] | Total | 77.64 | 4
Erection productivity | Jan'26
PCH Overall
Erection productivity | Jan'26
Weight/day (Avg) | 2.17
No of Gangs engaged (Avg) | 2
Erection productivity | Jan'26
Project: TB605
Erection productivity | Jan'26
Weight/day (Avg) | 2.17
No of Gangs engaged (Avg) | 2