## MonthlySummary
Month | Erections Completed | Total Tower Weight (MT) | Avg Tower Weight (MT) | Avg Productivity (MT/day) | Active Gangs | Top 3 Gangs (Avg Productivity)
Nov 2024 | 2 | 70.39 | 35.2 | 4.71 | Madhu Sah, Radha Enterprises | Radha Enterprises (4.97), Madhu Sah (4.45)
Dec 2024 | 14 | 538.29 | 38.45 | 5.32 | Madhu Sah, Punam Kumari, Radha Enterprises | Radha Enterprises (5.87), Madhu Sah (5.16), Punam Kumari (1.64)
Jan 2025 | 13 | 490.13 | 37.7 | 5.24 | Madhu Sah, Pinki Devi, Radha Enterprises | Radha Enterprises (5.70), Madhu Sah (4.85), Pinki Devi (4.43)
Feb 2025 | 17 | 862 | 50.71 | 4.87 | Madhu Sah, Pinki Devi, Poonam Kumari, Radha Enterprises, Radha Enterprises 1, Radha Enterprises 2 | Madhu Sah (5.63), Radha Enterprises (5.03), Poonam Kumari (4.76)
Mar 2025 | 8 | 422.41 | 52.8 | 3.92 | Madhu Sah, Pinki Devi, Poonam Kumari, Radha Enterprises, Radha Enterprises 1, Radha Enterprises 2 | Radha Enterprises 1 (5.29), Madhu Sah (4.64), Radha Enterprises (4.31)
Apr 2025 | 16 | 639.42 | 39.96 | 4.22 | Gagan Enterprises, Madhu Sah, Poornam Kumari, Radha Enterprises, Radha Enterprises 1 | Radha Enterprises (6.19), Radha Enterprises 1 (4.77), Poornam Kumari (4.14)
May 2025 | 5 | 350.7 | 70.14 | 5.84 | Gagan Enterprises, Madhu Sah, Poonam Kumari, Radha Enterprises | Radha Enterprises (6.53), Gagan Enterprises (6.39), Poonam Kumari (5.55)
Jun 2025 | 4 | 188 | 47 | 4.83 | Radha Enterprises 1 | Radha Enterprises 1 (4.83)
Jul 2025 | 5 | 307.03 | 61.41 | 5.82 | Madhu Sah, Radha Enterprises, Radha Enterprises 1 | Radha Enterprises (6.93), Radha Enterprises 1 (6.05), Madhu Sah (5.03)
Aug 2025 | 8 | 442.3 | 55.29 | 5.48 | Infinidea, Madhu Sah, Radha Enterprises, Radha Enterprises 1 | Radha Enterprises (6.93), Madhu Sah (5.10), Radha Enterprises 1 (5.09)
Sep 2025 | 6 | 341.46 | 56.91 | 3.65 | Infinidea, Madhu Sah, Radha Enterprises | Radha Enterprises (6.76), Madhu Sah (3.19), Infinidea (1.01)
Oct 2025 | 8 | 501.73 | 62.72 | 5.16 | Jwala Singh, Madhu Sah, Poonam Kumari, Poonam Kumari 2, Radha Enterprises, Radha Enterprises 1 | Radha Enterprises 1 (7.68), Radha Enterprises (6.23), Madhu Sah (5.28)
Nov 2025 | 14 | 690.5 | 49.32 | 4.47 | Infinidea, Infinidea 2, Jwala Singh, Madhu Sah, Punam Kumari 1, Punam Kumari 2, Satyam Trading | Madhu Sah (5.21), Jwala Singh (5.18), Satyam Trading (4.77)
Dec 2025 | 30 | 1613.6 | 53.79 | 4.31 | Amit Yadav, Bhairo Mahato, Dhruv Enterprises, Ganesh, Ganesh 2, Infinedea 1, Infinidea 2, Jwala Singh, Madhu Sah, Mukhilal 1, Mukhilal 2, Punam Kumari 1, Punam Kumari 2, Punam Kumari 4, Raju Kumar, Rohit, Sanjeet, Satyam Trading | Jwala Singh (6.52), Punam Kumari 1 (6.14), Mukhilal 2 (5.83)

## MonthlyDetails
Completion Month | Completion Date | Location No. | Project Name | Tower Type | Tower Weight (MT) | Gang Name | Status | Starting Date | Productivity (MT/day) | Source
Nov 2024 | 2024-11-27 | 20/1 | TA419 | DA-3 | 34.79 | Radha Enterprises | Completed | 2024-11-21 | 4.97 | ErectionCompiled_Output.xlsx
Nov 2024 | 2024-11-28 | 6/8 | TA419 | DA-1.5 | 35.6 | Madhu Sah | Completed | 2024-11-21 | 4.45 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-03 | 20/2 | TA419 | DA-3 | 34.79 | Radha Enterprises | Completed | 2024-11-28 | 5.8 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-05 | 6/11 | TA419 | DA+0 | 36.16 | Madhu Sah | Completed | 2024-11-28 | 4.52 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-08 | 22/2 | TA419 | DA-1.5 | 35.6 | Radha Enterprises | Completed | 2024-12-04 | 7.12 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-10 | 19/2 | TA419 | DA+0 | 36.16 | Punam Kumari | Completed | 2024-11-19 | 1.64 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-11 | 6/3 | TA419 | DA+1.5 | 37.14 | Madhu Sah | Completed | 2024-12-06 | 6.19 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-13 | 22/3 | TA419 | DA-1.5 | 35.6 | Radha Enterprises | Completed | 2024-12-09 | 7.12 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-17 | 23/1 | TA419 | DA-3 | 34.79 | Radha Enterprises | Completed | 2024-12-14 | 8.7 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-17 | 6/2 | TA419 | DA+3 | 37.93 | Madhu Sah | Completed | 2024-12-12 | 6.32 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-23 | 0B/2 | TA419 | DA+3 | 37.93 | Radha Enterprises | Completed | 2024-12-04 | 1.9 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-23 | 23/2 | TA419 | DA+0 | 36.16 | Radha Enterprises | Completed | 2024-12-18 | 6.03 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-23 | 6/10 | TA419 | DA-3 | 34.79 | Madhu Sah | Completed | 2024-12-17 | 4.97 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-31 | 0D/1 | TA419 | DA+6 | 43.8 | Radha Enterprises | Completed | 2024-12-22 | 4.38 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-31 | 23/0 | TA419 | DB2+0 | 59.5 | Radha Enterprises | Completed | 2024-12-22 | 5.95 | ErectionCompiled_Output.xlsx
Dec 2024 | 2024-12-31 | 6/12 | TA419 | DA+3 | 37.93 | Madhu Sah | Completed | 2024-12-22 | 3.79 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-09 | 24/1 | TA419 | DA-3 | 34.79 | Radha Enterprises | Completed | 2025-01-03 | 4.97 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-10 | 0E/2 | TA419 | DA+3 | 37.93 | Radha Enterprises | Completed | 2025-01-04 | 5.42 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-13 | 6/9 | TA419 | DA-3 | 34.79 | Madhu Sah | Completed | 2024-01-06 | 0.09 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-16 | 6/1 | TA419 | DA+0 | 36.16 | Madhu Sah | Completed | 2025-01-11 | 6.03 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-17 | 19/4 | TA419 | DA+0 | 36.16 | Radha Enterprises | Completed | 2025-01-11 | 5.17 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-18 | 0E/1 | TA419 | DA+3 | 37.93 | Radha Enterprises | Completed | 2025-01-11 | 4.74 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-19 | 0D/2 | TA419 | DA+1.5 | 37.14 | Pinki Devi | Completed | 2025-01-12 | 4.64 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-21 | 6/5 | TA419 | DA+6 | 43.8 | Madhu Sah | Completed | 2025-01-17 | 8.76 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-22 | 19/3 | TA419 | DA+3 | 37.93 | Radha Enterprises | Completed | 2025-01-18 | 7.59 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-27 | 0B/3 | TA419 | DA+6 | 43.8 | Radha Enterprises | Completed | 2025-01-19 | 4.87 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-27 | 19/1 | TA419 | DA-1.5 | 35.6 | Radha Enterprises | Completed | 2025-01-23 | 7.12 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-27 | 6/4 | TA419 | DA+0 | 36.16 | Madhu Sah | Completed | 2025-01-20 | 4.52 | ErectionCompiled_Output.xlsx
Jan 2025 | 2025-01-28 | 0C/1 | TA419 | DA+3 | 37.93 | Pinki Devi | Completed | 2025-01-20 | 4.21 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-01 | 6/7 | TA419 | DA+0 | 36.16 | Madhu Sah | Completed | 2025-01-27 | 6.03 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-05 | 19/0 | TA419 | DC1+0 | 62.44 | Radha Enterprises | Completed | 2025-01-27 | 6.24 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-08 | 0D/3 | TA419 | DA+9 | 45.7 | Pinki Devi | Completed | 2025-01-28 | 3.81 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-09 | 17/2 | TA419 | DA+1.5 | 37.14 | Poonam Kumari | Completed | 2025-01-31 | 3.71 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-11 | 6/0 | TA419 | DC1+0 | 62.44 | Madhu Sah | Completed | 2025-02-02 | 6.24 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-12 | 0A/0 (CT) | TA419 | DD60+3 | 87.02 | Radha Enterprises | Completed | 2025-01-27 | 5.12 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-12 | 19/5 | TA419 | DA+1.5 | 37.14 | Radha Enterprises | Completed | 2025-02-03 | 3.71 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-14 | 17/1 | TA419 | DA-3 | 34.79 | Poonam Kumari | Completed | 2025-02-08 | 4.97 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-15 | 0D/4 | TA419 | DA+0 | 36.16 | Pinki Devi | Completed | 2025-02-08 | 4.52 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-18 | 5/4 | TA419 | DA+6 | 43.8 | Madhu Sah | completed | 2025-02-09 | 4.38 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-20 | 20/0 | TA419 | DC1+3 | 65.87 | Radha Enterprises 1 | completed | 2025-02-07 | 4.71 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-24 | 6/6 | TA419 | DA+0 | 36.16 | Madhu Sah | Completed | 2025-02-18 | 5.17 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-25 | 0D/0 | TA419 | DB2+0 | 59.5 | Pinki Devi | Completed | 2025-02-13 | 4.58 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-25 | 18/0 | TA419 | DC2+0 | 67.26 | Poonam Kumari | Completed | 2025-02-14 | 5.61 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-27 | 0D/5 | TA419 | DB1+9 | 66.78 | Radha Enterprises 2 | Completed | 2025-02-07 | 3.18 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-28 | 22/1 | TA419 | DA+9 | 45.7 | Radha Enterprises 1 | Completed | 2025-02-19 | 4.57 | ErectionCompiled_Output.xlsx
Feb 2025 | 2025-02-28 | 5/3 | TA419 | DA+3 | 37.93 | Madhu Sah | Completed | 2025-02-23 | 6.32 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-04 | 0B/1 | TA419 | DA+3 | 37.93 | Pinki Devi | Completed | 2025-02-19 | 2.71 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-07 | 17/0 | TA419 | DB2+0 | 59.5 | Poonam Kumari | Completed | 2025-02-22 | 4.25 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-08 | 7/1 | TA419 | DA+1.5 | 37.14 | Madhu Sah | Completed | 2025-03-01 | 4.64 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-12 | 23/3 | TA419 | DA+3 | 37.93 | Radha Enterprises 1 | Completed | 2025-03-06 | 5.42 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-24 | 24/0 | TA419 | DD45+0 | 73.24 | Radha Enterprises | Completed | 2025-03-08 | 4.31 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-26 | 15A/0 | TA419 | DD45+0 | 73.24 | Poonam Kumari | Completed | 2025-03-02 | 2.93 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-28 | 26/1 | TA419 | DA+0 | 36.16 | Radha Enterprises 1 | Completed | 2025-03-22 | 5.17 | ErectionCompiled_Output.xlsx
Mar 2025 | 2025-03-31 | 0F/0 | TA419 | DC2+0 | 67.26 | Radha Enterprises 2 | Completed | 2025-02-25 | 1.92 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-05 | 12/1 | TA419 | DA+0 | 36.16 | Poornam Kumari | Completed | 2025-03-26 | 3.29 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-05 | 24/3 | TA419 | DA-1.5 | 35.6 | Radha Enterprises 1 | Completed | 2025-03-27 | 3.56 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-08 | 26/5 | TA419 | DA-1.5 | 35.6 | Radha Enterprises 1 | Completed | 2025-03-31 | 3.96 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-11 | 5/2 | TA419 | DA+0 | 36.16 | Madhu Sah | Completed | 2025-03-24 | 1.9 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-13 | 26/6 | TA419 | DA+0 | 36.16 | Radha Enterprises 1 | Completed | 2025-04-08 | 6.03 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-13 | 30/1 | TA419 | DA+0 | 36.16 | Gagan Enterprises | Completed | 2025-03-31 | 2.58 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-14 | 11/4 | TA419 | DA+6 | 43.8 | Poornam Kumari | Completed | 2025-04-03 | 3.65 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-17 | 5/1 | TA419 | DA-3 | 34.79 | Madhu Sah | Completed | 2025-04-07 | 3.16 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-18 | 26/3 | TA419 | DA+0 | 36.16 | Radha Enterprises 1 | Completed | 2025-04-12 | 5.17 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-19 | 11/3 | TA419 | DA+3 | 37.93 | Poornam Kumari | Completed | 2025-04-11 | 4.21 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-21 | 28/1 | TA419 | DA-3 | 34.79 | Gagan Enterprises | Completed | 2025-04-12 | 3.48 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-23 | 26/4 | TA419 | DA+0 | 36.16 | Radha Enterprises 1 | Completed | 2025-04-17 | 5.17 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-27 | 5/0 | TA419 | DB2+0 | 59.5 | Madhu Sah | Completed | 2025-04-14 | 4.25 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-28 | 24/2 | TA419 | DA+1.5 | 37.14 | Radha Enterprises | Completed | 2025-04-23 | 6.19 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-29 | 12/0 | TA419 | DB2+0 | 59.5 | Poornam Kumari | Completed | 2025-04-19 | 5.41 | ErectionCompiled_Output.xlsx
Apr 2025 | 2025-04-29 | 31/1 | TA419 | DA+6 | 43.8 | Gagan Enterprises | Completed | 2025-04-22 | 5.48 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-04 | 4/1 | TA419 | DA+3 | 37.93 | Madhu Sah | Completed | 2025-04-28 | 5.42 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-07 | 12A/0 | TA419 | DB1+0 | 55.45 | Poonam Kumari | Completed | 2025-04-28 | 5.55 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-10 | 31/0 | TA419 | DD60+0 | 83.13 | Gagan Enterprises | Completed | 2025-04-28 | 6.39 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-11 | 3/5 | TA419 | DA+1.5 | 37.14 | Madhu Sah | Completed | 2025-05-05 | 5.31 | ErectionCompiled_Output.xlsx
May 2025 | 2025-05-19 | 22/0 | TA419 | DD60+25 | 137.05 | Radha Enterprises | completed | 2025-04-29 | 6.53 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-03 | 27/0 | TA419 | DD45+0 | 73.24 | Radha Enterprises 1 | Completed | 2025-05-19 | 4.58 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-13 | 27/1 | TA419 | DA+6 | 43.8 | Radha Enterprises 1 | Completed | 2025-06-05 | 4.87 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-20 | 27/2 | TA419 | DA-3 | 34.79 | Radha Enterprises 1 | Completed | 2025-06-12 | 3.87 | ErectionCompiled_Output.xlsx
Jun 2025 | 2025-06-26 | 27/3 | TA419 | DA+0 | 36.16 | Radha Enterprises 1 | Completed | 2025-06-21 | 6.03 | ErectionCompiled_Output.xlsx
Jul 2025 | 2025-07-08 | 28/0 | TA419 | DC2+0 | 67.26 | Radha Enterprises 1 | Completed | 2025-06-27 | 5.61 | ErectionCompiled_Output.xlsx
Jul 2025 | 2025-07-17 | 34/0 | TA419 | DD60+0 | 83.13 | Madhu Sah | Completed | 2025-07-01 | 4.89 | ErectionCompiled_Output.xlsx
Jul 2025 | 2025-07-18 | 29/0 | TA419 | DB1+6 | 65.02 | Radha Enterprises 1 | Completed | 2025-07-09 | 6.5 | ErectionCompiled_Output.xlsx
Jul 2025 | 2025-07-24 | 34/1 | TA419 | DA+0 | 36.16 | Madhu Sah | Completed | 2025-07-18 | 5.17 | ErectionCompiled_Output.xlsx
Jul 2025 | 2025-07-26 | 20/3 | TA419 | DB1+0 | 55.45 | Radha Enterprises | Completed | 2025-07-19 | 6.93 | ErectionCompiled_Output.xlsx
Aug 2025 | 2025-08-01 | 36/1 | TA419 | DA+3 | 37.93 | Madhu Sah | Completed | 2025-07-26 | 5.42 | ErectionCompiled_Output.xlsx
Aug 2025 | 2025-08-03 | 26/2 | TA419 | DA-1.5 | 35.6 | Radha Enterprises 1 | Completed | 2025-07-28 | 5.09 | ErectionCompiled_Output.xlsx
Aug 2025 | 2025-08-07 | 36/2 | TA419 | DA+3 | 37.93 | Madhu Sah | Completed | 2025-08-02 | 6.32 | ErectionCompiled_Output.xlsx
Aug 2025 | 2025-08-13 | 11/1 | TA419 | DB1+6 | 65.02 | Radha Enterprises | Completed | 2025-08-04 | 6.5 | ErectionCompiled_Output.xlsx
Aug 2025 | 2025-08-19 | 3/1 | TA419 | DA+3 | 37.93 | Madhu Sah | Completed | 2025-08-12 | 4.74 | ErectionCompiled_Output.xlsx
Aug 2025 | 2025-08-27 | 0G/1 | TA419 | DA+0 | 36.16 | Infinidea | Completed | 2025-08-20 | 4.52 | ErectionCompiled_Output.xlsx
Aug 2025 | 2025-08-30 | 10/0 | TA419 | DD60+18 | 124.95 | Radha Enterprises | Completed | 2025-08-14 | 7.35 | ErectionCompiled_Output.xlsx
Aug 2025 | 2025-08-31 | 0G/0 | TA419 | DB1+9 | 66.78 | Madhu Sah | Completed | 2025-08-15 | 3.93 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-07 | 11/2 | TA419 | DB1+9 | 66.78 | Radha Enterprises | Completed | 2025-08-31 | 8.35 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-07 | 3/2 | TA419 | DA+3 | 37.93 | Infinidea | Completed | 2025-07-29 | 0.93 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-13 | 12/2 | TA419 | DA+0 | 36.16 | Radha Enterprises | Completed | 2025-09-07 | 5.17 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-15 | 0H/0 | TA419 | DD60+0 | 83.13 | Madhu Sah | Completed | 2025-08-01 | 1.81 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-22 | 1/0 | TA419 | DB1+3 | 57.96 | Infinidea | Completed | 2025-08-01 | 1.09 | ErectionCompiled_Output.xlsx
Sep 2025 | 2025-09-27 | 4/0 | TA419 | DB2+0 | 59.5 | Madhu Sah | Completed | 2025-09-15 | 4.58 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-05 | 21/0 | TA419 | DD60+25 | 137.05 | Radha Enterprises | Completed | 2025-09-14 | 6.23 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-05 | 3/4 | TA419 | DA+6 | 43.8 | Madhu Sah | Completed | 2025-09-28 | 5.48 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-12 | 3/3 | TA419 | DA-1.5 | 35.6 | Madhu Sah | Completed | 2025-10-06 | 5.09 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-18 | 26/0 | TA419 | DC2+18 | 99.78 | Radha Enterprises 1 | Completed | 2025-10-06 | 7.68 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-23 | 36/7 | TA419 | DA+0 | 36.16 | Jwala Singh | Completed | 2025-10-16 | 4.52 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-26 | 16/0 | TA419 | DB2+6 | 69.38 | Poonam Kumari | Completed | 2025-10-12 | 4.63 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-27 | 31/2 | TA419 | DA+6 | 43.8 | Poonam Kumari 2 | Completed | 2025-10-14 | 3.13 | ErectionCompiled_Output.xlsx
Oct 2025 | 2025-10-30 | 36/6 | TA419 | DA+0 | 36.16 | Jwala Singh | Completed | 2025-10-23 | 4.52 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-05 | 0B/0 | TA419 | DC1+6 | 72.47 | Infinidea | Completed | 2025-09-23 | 1.65 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-08 | 36/8 | TA419 | DA+0 | 36.16 | Jwala Singh | Completed | 2025-11-01 | 4.52 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-12 | 30/0 | TA419 | DD45+0 | 73.24 | Punam Kumari 2 | Completed | 2025-10-26 | 4.07 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-13 | 35/0 | TA419 | DD45+3 | 77.08 | Punam Kumari 1 | Completed | 2025-10-27 | 4.28 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-14 | 41/5 | TA419 | DA+1.5 | 37.14 | Jwala Singh | Completed | 2025-11-08 | 5.31 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-16 | 40/5 | TA419 | DA+1.5 | 37.14 | Madhu Sah | Completed | 2025-11-08 | 4.13 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-23 | 40/6 | TA419 | DA+1.5 | 37.14 | Madhu Sah | Completed | 2025-11-17 | 5.31 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-23 | 41/4 | TA419 | DA+6 | 43.8 | Jwala Singh | Completed | 2025-11-15 | 4.87 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-25 | 38/7 | TA419 | DA+3 | 37.93 | Infinidea 2 | Completed | 2025-11-12 | 2.71 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-25 | 46/2 | TA419 | DA+3 | 46.05 | Satyam Trading | Completed | 2025-11-12 | 3.29 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-29 | 40/4 | TA419 | DA+1.5 | 37.14 | Madhu Sah | Completed | 2025-11-24 | 6.19 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-29 | 41/3 | TA419 | DA+0 | 36.16 | Jwala Singh | Completed | 2025-11-24 | 6.03 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-30 | 36/0 | TA419 | DC1+9 | 75.27 | Punam Kumari 1 | Completed | 2025-11-12 | 3.96 | ErectionCompiled_Output.xlsx
Nov 2025 | 2025-11-30 | 46/1 | TA419 | DA+0 | 43.78 | Satyam Trading | Completed | 2025-11-24 | 6.25 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-02 | 46/3 | TA419 | DA+0 | 43.78 | Sanjeet | Completed | 2025-11-12 | 2.08 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-03 | 62/1 | TA419 | DA+6 | 53.32 | Rohit | Completed | 2025-11-15 | 2.81 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-04 | 41/7 | TA419 | DA+0 | 36.16 | Jwala Singh | Completed | 2025-11-29 | 6.03 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-05 | 40/3 | TA419 | DA+3 | 37.93 | Madhu Sah | Completed | 2025-11-29 | 5.42 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-08 | 0C/0 | TA419 | DD45+0 | 73.24 | Dhruv Enterprises | Completed | 2025-11-15 | 3.05 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-08 | 43/5 | TA419 | DA+1.5 | 37.14 | Mukhilal 1 | Completed | 2025-11-19 | 1.86 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-08 | 83/1 | TA419 | DA+9 | 55.34 | Raju Kumar | Completed | 2025-11-21 | 3.07 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-10 | 38/5 | TA419 | DA+3 | 37.93 | Punam Kumari 2 | Completed | 2025-12-04 | 5.42 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-10 | 38/6 | TA419 | DA+1.5 | 37.14 | Infinidea 2 | Completed | 2025-12-01 | 3.71 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-10 | 40/2 | TA419 | DA+3 | 37.93 | Madhu Sah | Completed | 2025-12-05 | 6.32 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-10 | 41/8 | TA419 | DA+0 | 36.16 | Jwala Singh | Completed | 2025-12-05 | 6.03 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-10 | 46/4 | TA419 | DA+6 | 53.32 | Sanjeet | Completed | 2025-12-04 | 7.62 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-10 | 62/4 | TA419 | DA-3 | 42.37 | Ganesh | Completed | 2025-11-29 | 3.53 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-11 | 43/6 | TA419 | DA-3 | 34.79 | Satyam Trading | Completed | 2025-12-03 | 3.87 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-16 | 38/11 | TA419 | DA+0 | 36.16 | Punam Kumari 1 | Completed | 2025-12-10 | 5.17 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-16 | 41/1 | TA419 | DA-3 | 34.79 | Jwala Singh | Completed | 2025-12-10 | 4.97 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-17 | 43/4 | TA419 | DA-3 | 34.79 | Satyam Trading | Completed | 2025-12-09 | 3.87 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-17 | 62/2 | TA419 | DA+6 | 53.32 | Rohit | Completed | 2025-12-04 | 3.81 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-18 | 38/0 | TA419 | DD60+25 | 137.05 | Punam Kumari 2 | Completed | 2025-11-12 | 3.7 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-18 | 40/7 | TA419 | DA-1.5 | 35.6 | Madhu Sah | Completed | 2025-12-10 | 3.96 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-19 | 38/10 | TA419 | DA+0 | 36.16 | Infinedea 1 | Completed | 2025-12-04 | 2.26 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-20 | 11/0 | TA419 | DD60+30 | 160.94 | Bhairo Mahato | Completed | 2025-11-05 | 3.5 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-20 | 40/9 | TA419 | DA+0 | 36.16 | Jwala Singh | Completed | 2025-12-17 | 9.04 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-20 | 83/7 | TA419 | DA+0 | 43.78 | Amit Yadav | Completed | 2025-11-19 | 1.37 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-21 | 12A/1 | TA419 | DA+6 | 37.93 | Punam Kumari 4 | Completed | 2025-12-12 | 3.79 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-21 | 38/9 | TA419 | DA-1.5 | 35.6 | Punam Kumari 1 | Completed | 2025-12-17 | 7.12 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-24 | 0E/0 | TA419 | DD45+3 | 77.08 | Bhairo Mahato | Completed | 2025-12-03 | 3.5 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-24 | 62/5 | TA419 | DA+9 | 55.34 | Ganesh | Completed | 2025-12-10 | 3.69 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-26 | 43/0 | TA419 | DD60+18 | 139.97 | Mukhilal 2 | Completed | 2025-12-03 | 5.83 | ErectionCompiled_Output.xlsx
Dec 2025 | 2025-12-26 | 84/4 | TA419 | DA-3 | 42.37 | Ganesh 2 | Completed | 2025-12-13 | 3.03 | ErectionCompiled_Output.xlsx

## SelectionContext
Project Code | Project Names | Dataset Path | Range Start | Range End | Months Covered | Total Completions
TA419 | TA419 | C:\Users\kaushikb\Documents\Work\Git\Office-work-\Parquets\Erection\ErectionCompiled_Output.xlsx | 2024-11-27 | 2025-12-26 | 14 | 150