## Foundation
Project Code |  |  | TA-418
Name of Line |  |  | 765KV D/C KOPPAL II(PS) - RAICHUR TL (Part-1)
Activity |  |  | Foundation | Qty
|  |  | Total | 127
|  |  | Completed (Nov-25) | 120
|  |  | Balance | 7
Micro Plan for month |  |  | 2025-12-01 | 7 | Nos | 53.62 | Rs. Lakhs
Achievement for Month |  |  | Wk-1 | 0 | 0% | 0 | 0%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
Actual for the Month |  |  | Total | 0 | 0 | 0 | 0
Sl | Loc No. | Tower type | Classification | Conc. Vol (CuM) | Reinf (MT) | Sub-Cont | Work Plan | [7 empty] | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[7 empty] | Excavation |  | Stub-setting |  | Concreting |  | Earthing | Backfilling |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[7 empty] | Start | End | Start | End | Start | End |  |  | Rs. Lacs. | Date | [11 empty] | Rs. Lacs. | Rs. Lacs.
1 | 48A/2 | 1DA-1.5 | DFR | 11.42 | 0.62 | Gang- 01 | 2025-12-02 | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-04 | 2025-12-08 | 2025-12-10 | 2025-12-09 | 2.86 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2.86
2 | 59/1 | 1DA-3 | DFR | 11.42 | 0.62 | Gang- 01 | 2025-12-07 | 2025-12-09 | 2025-12-10 | 2025-12-10 | 2025-12-11 | 2025-12-15 | 2025-12-17 | 2025-12-16 | 2.86 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.86
3 | 60/3 | 1DA+0 | DFR | 11.42 | 0.62 | Gang- 01 | 2025-12-14 | 2025-12-16 | 2025-12-17 | 2025-12-17 | 2025-12-18 | 2025-12-22 | 2025-12-24 | 2025-12-23 | 2.86 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.86
4 | 63/0 | 1DD60+0 | DFR | 72.19 | 3.42 | Gang- 01 | 2025-12-21 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-24 | 2025-12-29 | 2025-12-31 | 2025-12-30 | 14.15 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.15
5 | AP49 | 1DC1+3 | DFR | 28.1 | 1.46 | Gang-02 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-04 | 2025-12-05 | 2025-12-10 | 2025-12-12 | 2025-12-11 | 8.33 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.33
6 | AP57 | 1DC1+6 | DFR | 28.1 | 1.46 | Gang-02 | 2025-12-09 | 2025-12-11 | 2025-12-12 | 2025-12-12 | 2025-12-13 | 2025-12-18 | 2025-12-20 | 2025-12-19 | 8.33 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.33
7 | AP38 | 1DD60+6 | DFR | 72.19 | 3.49 | Gang-02 | 2025-12-17 | 2025-12-19 | 2025-12-20 | 2025-12-20 | 2025-12-21 | 2025-12-27 | 2025-12-29 | 2025-12-28 | 14.23 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.23
0
|  |  |  | 234.84 | 11.69 | [9 empty] | 53.62 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.62
[13 empty] | STUB Setting- |  | 0.4
[13 empty] | Earthing- |  | 1.2
[13 empty] | Total Reve |  | 55.22
Formulas:
End = [Work Plan]+1
End = [Stub-setting]
Stub-setting = [End]
Stub-setting = [End]+1
Concreting = [End]+1
Earthing = [End]+2
Backfilling = [End]+1
Work Plan = [End, row above]-1

## Stub dispatch (hidden)
Location | Project | Tower type | Structure | B LOT | Actual PRS Date | STEEL Wt (MT) | BNA Wt | Disp Bal | May'24 Disp Plan | Wk01 | WK02 | WK03 | WK04 | Jun'24 Disp Plan MT | July'24 Disp Plan | Remark
JPR | TA416 | DA | Stub - 28 Nos | TA416-00018 | 2024-04-11 | 26.8617 | 0.46323 | 26.8617 | 0 |  |  |  | 0 | 26.8617 | 0 | As on date 160 stub reieved.
JPR | TA416 | DA | Stub - 132 Nos | TA416-00026 | 2024-04-15 | 126.634 | 2.184 | 126.634 | [5 empty] | 126.634 | 0
Total |  |  | 160 | [10 empty] | 153.4957

## Erection
Project Code |  |  | TA-418
Name of Line |  |  | 765KV D/C KOPPAL II(PS) - RAICHUR TL (Part-1)
Activity |  |  | Erection | Qty
|  |  | Total | 127
|  |  | Completed (Nov-25) | 97
|  |  | Balance | 30
Micro Plan for month |  |  | 2025-12-01 | 16 | Nos | 62.63 | Rs. Lakhs
Achievement for Month |  |  | Wk-1 | 0 | 0% | 0 | 0%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
|  |  | Total | 0 | 0% | 0 | 0%
Sl | Loc No. | Tower type | Tonnage (MT) | Sub-Cont | Work Plan |  |  |  |  | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[5 empty] | Matl feeding | Erection |  | Tack-welding | Final checking |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[6 empty] | Start | End |  |  | Rs. Lacs. | Date | [11 empty] | Rs. Cr. | Rs. Cr.
1 | 47/0 | DC1+0 | 51.673 | GANG - 01 | 2025-12-02 | 2025-12-04 | 2025-12-11 |  |  | 5.62 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.62
2 | 46/1 | DA-3 | 26.846 |  | 2025-12-10 | 2025-12-12 | 2025-12-17 |  |  | 2.95 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95
3 | 51/0 | DB1-3 | 43.621 |  | 2025-12-16 | 2025-12-18 | 2025-12-24 |  |  | 4.72 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.72
4 | 52/1 | DA+3 | 29.122 |  | 2025-12-23 | 2025-12-25 | 2025-12-30 |  |  | 3.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6
5 | 60/0 | DC2+0 | 51.673 | GANG - 02 | 2025-11-30 | 2025-12-01 | 2025-12-08 |  |  | 5.62 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.62
6 | 43/3 | DA-3 | 26.846 |  | 2025-12-07 | 2025-12-09 | 2025-12-13 |  |  | 2.95 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95
7 | 48A/1 | DA+9 | 34.63 |  | 2025-12-12 | 2025-12-14 | 2025-12-19 |  |  | 3.89 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.89
8 | 48A/2 | DA-1.5 | 27.601 |  | 2025-12-18 | 2025-12-20 | 2025-12-25 |  |  | 3.04 | [13 empty] | 3.04
9 | 52/2 | DA-3 | 26.846 |  | 2025-12-24 | 2025-12-26 | 2026-01-01 |  |  | 2.95 | [13 empty] | 2.95
10 | 44/1 | DA+0 | 27.963 | GANG - 03 | 2025-11-26 | 2025-11-28 | 2025-12-03 |  |  | 3.08 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.08
11 | 46/11 | DA-1.5 | 27.601 |  | 2025-12-02 | 2025-12-04 | 2025-12-09 |  |  | 3.04 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04
12 | 49/0 | DC1+3 | 53.871 |  | 2025-12-08 | 2025-12-10 | 2025-12-17 |  |  | 6.57 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.57
13 | 50/0 | DC1+0 | 51.673 |  | 2025-12-16 | 2025-12-18 | 2025-12-25 |  |  | 5.62 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.62
14 | 54/2 | DA-3 | 26.846 |  | 2025-12-24 | 2025-12-26 | 2026-01-01 |  |  | 2.95 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95
15 | 55/5 | DA+0 | 27.963 | GANG - 04 | 2025-12-15 | 2025-12-17 | 2025-12-24 |  |  | 3.08 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.08
16 | 55/6 | DA-3 | 26.846 |  | 2025-12-23 | 2025-12-25 | 2025-12-31 |  |  | 2.95 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95
|  |  | 561.621 | [6 empty] | 62.63 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.63
Formulas:
Erection = [Work Plan]+2
End = [Erection]+7
Work Plan = [End, row above]-1

## Stringing
Project Code |  |  | TA-418
Name of Line |  |  | 765KV D/C KOPPAL II(PS) - RAICHUR TL (Part-1)
Activity |  |  | Stringing | Qty |  |  |  |  | Rate | 10.942
|  |  | Total | 47.84
|  |  | Completed (Nov-25) | 10.52
|  |  | Balance | 37.32
Micro Plan for month |  |  | 2025-12-01 | 9.75 | km | 106.6849 | Rs. Lakhs
Achievement for Month |  |  | Wk-1 | 0 | 0% | 0 | 0%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
|  |  | Total | 0 | 0% | 0 | 0%
Sl | Section | Section Length (km) | Manual/TSE | Sub-Cont | Work Plan |  |  |  |  | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[5 empty] | Matl feeding | Pay-Out |  | Final Sag |  |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[6 empty] | Start | End | Start | End | Rs. Cr. | Date | [11 empty] | Rs. Cr. | Rs. Cr.
1 | 40/0 - 41/0 | 2.426 | TSE | GANG - 01 | 2025-12-03 | 2025-12-04 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 26.5454 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.5454
2 | 33/6 - 34/0 | 2.537 | TSE |  | 2025-12-10 | 2025-12-11 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 27.76 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.76
3 | 33/0 - 33/5 | 2.015 | TSE |  | 2025-12-17 | 2025-12-18 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 22.0482 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.0482
4 | 43/0 - 44/0 | 1.445 | TSE |  | 2025-12-24 | 2025-12-25 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 15.8112 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.8112
5 | 44/0 - 45/0 | 0.697 | TSE |  | 2025-12-29 | 2025-12-30 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 7.6266 | [13 empty] | 7.6266
6 | 33/5 - 33/6 | 0.38 | MANUAL | GANG - 01 | 2025-12-12 | 2025-12-13 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 4.158 | [13 empty] | 4.158
7 | 32/0 - 33/0 | 0.25 | MANUAL |  | 2025-12-22 | 2025-12-24 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2.7355 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7355
6 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 9.75 | [7 empty] | 106.6849 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106.6849
Formulas:
Pay-Out = [Work Plan]+1
End = [Pay-Out]+3
Final Sag = [End]+1
Work Plan = [Rate, row above]+1
Work Plan = [Rate, row above]