## FDN-June25 (hidden)
Project Code |  |  | TA-416
Name of Line |  |  | NEEMRANA-II-BAREILLY (PG) 765KV D/C LINE,WZ-5 (Part-III)
Activity |  |  | Foundation | Qty
|  |  | Total | 302
|  |  | Completed (May-25) | 301
|  |  | Balance | 1
Micro Plan for month |  |  | 2025-06-01 | 1 | Nos | 4925228.89 | Rs. Cr.
Achievement for Month |  |  | Wk-1 | 1 | 100% | 4925228.89 | 100%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
Actual for the Month |  |  | Total | 1 | 1 | 4925228.89 | 1
Sl | Loc No. | Tower type | Classification | Conc. Vol (CuM) | Reinf (MT) | Sub-Cont | Work Plan | [7 empty] | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[7 empty] | Excavation |  | Stub-setting |  | Concreting |  | Earthing | Backfilling |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[7 empty] | Start | End | Start | End | Start | End |  |  | Rs. Lacs. | Date | [11 empty] | Rs. Lacs. | Rs. Lacs.
1 | 38/0 | DC2+18 | FS | 261.196 | 15.029 | AVI | 2025-05-21 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 4925228.89 | 2025-06-03 | 1 |  |  |  |  | 1 | 4925228.89 | 0 | 0 | 0 | 0 | 4925228.89 | 0
2 | [21 empty] | 0 |  |  |  |  | 0 | 0 | 0
3 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 261.196 | 15.029 | [9 empty] | 4925228.89 |  | 1 | 0 | 0 | 0 | 0 | 1 | 4925228.89 | 0 | 0 | 0 | 0 | 4925228.89 | 0
[13 empty] | STUB Setting-1 |  | 7224.33
[13 empty] | Earthing-1 |  | 7782.57
[13 empty] | Total Reve |  | 4940235.79

## Stub dispatch (hidden)
Location | Project | Tower type | Structure | B LOT | Actual PRS Date | STEEL Wt (MT) | BNA Wt | Disp Bal | May'24 Disp Plan | Wk01 | WK02 | WK03 | WK04 | Jun'24 Disp Plan MT | July'24 Disp Plan | Remark
JPR | TA416 | DA | Stub - 28 Nos | TA416-00018 | 2024-04-11 | 26.8617 | 0.46323 | 26.8617 | 0 |  |  |  | 0 | 26.8617 | 0 | As on date 160 stub reieved.
JPR | TA416 | DA | Stub - 132 Nos | TA416-00026 | 2024-04-15 | 126.634 | 2.184 | 126.634 | [5 empty] | 126.634 | 0
Total |  |  | 160 | [10 empty] | 153.4957

## Erection-Nov25
Sl | Location No. | Tower type | Tower Weight | Gang Name | Manpower | Section Incharge | Supervisor | Power Tools Issued (YES/NO) | Material Feeding | Starting Date | Completion Date | Tack-welding | Final checking | Revenue Planned | Revenue Realised
1 | 2A/2 | DA+6 | 21.0969 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 283394.8726
2 | 11/0 | DD45+0 | 35.8452 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 481508.8
3 | 30/0 | DD60+3 | 41.8329 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 561941.0367
4 | 46/0 | DD60+9 | 53.1226 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 713596.356
5 | 47/1 | DB1+9 | 36.5854 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 491451.0468
6 | 63/1 | DA+6 | 21.0969 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 283394.8726
7 | 65A/1 | DA-1.5 | 16.4524 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 221005.7071
8 | 76A/0 | DC1+3 | 31.8647 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 428038.2061
9 | 113/0 | DB2+9 | 36.5854 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 491451.0468
10 | 119/0 | DB2+9 | 36.5854 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 491451.0468
11 | 128/0 | DB1+6 | 34.1664 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 458957.6676
12 | 135/1 | DA+9 | 22.4884 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 302086.3279
13 | 172/1 | DA-1.5 | 16.4524 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 221005.7071
14 | 212/0 | DB2+3 | 28.3681 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 381068.0559
15 | 227/2 | DD60+0 | 39.5967 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 531902.4039
16 | 1/0 | DD60+0 | 39.5967 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 531902.4039
17 | 4/1 | DA+3 | 18.1188 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 243390.0553
18 | 13/4 | DA+9 | 22.4884 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 302086.3279
19 | 17/0 | DC1+18 | 53.2386 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 715154.6646
20 | 18/0 | DD45+0 | 35.8452 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 481508.8
21 | 31/0 | DD45+6 | 46.4686 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 624212.9859
22 | 35A/0 | DB2-3 | 24.7001 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 331796.2955
23 | 36/0 | DC1-3 | 27.2498 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 366046.8186
24 | 40/0 | DD45+0 | 35.8452 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 481508.8
25 | 42/1 | DA+0 | 16.9667 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 227914.0035
26 | 44/0 | DC2+3 | 31.8647 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 428038.2061
27 | 44/1 | DA+0 | 16.9667 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 227914.0035
28 | 47/2 | DA+9 | 22.4884 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 302086.3279
29 | 51B/0 | DB2-1.5 | 25.0049 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 335890.6471
30 | 52/0 | DC1-1.5 | 28.3001 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 380154.6388
31 | 54/0 | DC2+18 | 53.2386 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 715154.6646
32 | 61/0 | DC1-3 | 27.2498 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 366046.8186
33 | 64A/0 | DC1-3 | 27.2498 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 366046.8186
34 | 68/1 | DB1+0 | 27.0921 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 363928.8375
35 | 72/0 | DD60+0 | 39.5967 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 531902.4039
36 | 76D/0 | DC1+6 | 37.2057 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 499784.7189
37 | 80/0 | DD45+0 | 35.8452 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 481508.8
38 | 206/2 | DA+9 | 22.4884 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 302086.3279
39 | 207/0 | DD45+6 | 46.4686 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 624212.9859
40 | 207/1 | DA+3 | 18.1188 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 243390.0553
41 | 207/3 | DA+0 | 16.9667 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 227914.0035
42 | 210/0 | DB1+0 | 27.0921 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 363928.8375
43 | 210/3 | DA+3 | 18.1188 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 243390.0553
44 | 210/4 | DA+6 | 21.0969 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 283394.8726
45 | 210/5 | DA+6 | 21.0969 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 283394.8726
46 | 210/6 | DA+0 | 16.9667 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 227914.0035
47 | 210/8 | DA+6 | 21.0969 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 283394.8726
48 | 211/1 | DA+0 | 16.9667 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 227914.0035
49 | 212/1 | DA+6 | 21.0969 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 283394.8726
50 | 215/0 | DB1+6 | 34.1664 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 458957.6676

## Stringing- Nov25
Name of the line : 400 KV Sirohi - Chittorgarh
Powergrid Sirohi Transmission Limited (Power Grid Corporation of India)
Executing Agency:- KEC International Limited
Datewise Stringing planning for the month of December 2025
Micro Plan - Stringing
Sr no | Section Name | Section Length Miter | Tower Erection Status | Tower in section | Insulator Hoisting | Paying Out Start | Paying Out Completed | Final sag complete | Gang Name
1 | AP5-AP6 | 4932.33 | Completed | 12
2 | AP2-AP2A | 3291.6 | Completed | 10
3
4
5
6
7
Total length (KM) |  | 8.2239 |  | 22

## STG-Sep25 (hidden)
Project Code
Name of Line
Activity |  |  | Stringing | Qty |  |  |  |  | Rate @Kms | 905812
|  |  | Total | 115
|  |  | Completed (Aug-25) | 32.6
|  |  | Balance | 82.4
Micro Plan for month |  |  | 2025-09-01 | 23.985 | km | 21725900.82 | Rs. Cr
Achievement for Month |  |  | Wk-1 | 0 | 0% | 0 | 0%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
|  |  | Total | 0 | 0% | 0 | 0%
Sl | Section | Section Length (km) | Manual/TSE | Sub-Cont | Work Plan |  |  |  |  | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[5 empty] | Matl feeding | Pay-Out |  | Final Sag |  |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[6 empty] | Start | End | Start | End | Rs. Cr. | Date | [11 empty] | Rs. Cr. | Rs. Cr.
1 | 14/0-15/0 | 3.611 | TSE | Anarul | 2025-08-30 | 2025-09-01 | 2025-09-08 | 2025-09-09 | 2025-09-12 | 3270887.132 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3270887.132
2 | 12/0-13/0 | 3.92 | TSE |  | 2025-09-13 | 2025-09-14 | 2025-09-19 | 2025-09-20 | 2025-09-22 | 3550783.04 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3550783.04
3 | 3/0-4/0 | 0.28 | Manual-1 |  | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 253627.36 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253627.36
4 | 11/0-12/0 | 0.313 | Manual-1 |  | 2025-09-27 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 283519.156 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283519.156
5 | 13/0-14/0 | 0.319 | Manual-1 |  | 2025-09-15 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 288954.028 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288954.028
6 | 20/0-21/0 | 4.958 | TSE | Pankaj | 2025-09-03 | 2025-09-04 | 2025-09-09 | 2025-09-10 | 2025-09-13 | 4491015.896 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4491015.896
7 | 21/0-22/0 | 1.606 | TSE |  | 2025-09-14 | 2025-09-15 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 1454734.072 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1454734.072
8 | 18/0-19/0 | 0.323 | Manual-1 |  | 2025-09-20 | 2025-09-21 | 2025-09-26 | 2025-09-27 | 2025-09-30 | 292577.276 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292577.276
9 | 36/0-37/0 | 4.947 | TSE |  | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-07 | 2025-09-10 | 4481051.964 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4481051.964
10 | 30/0-31/0 | 2.75 | TSE |  | 2025-09-11 | 2025-09-12 | 2025-09-17 | 2025-09-18 | 2025-09-21 | 2490983 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2490983
11 | 29/0-30/0 | 0.27 | TSE |  | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-22 | 2025-09-22 | 244569.24 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244569.24
12 | 28/0-29/0 | 0.688 | Manual-2 |  | 2025-09-27 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 623198.656 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623198.656
13 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 23.985 | [7 empty] | 21725900.82 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21725900.82