## FDN-June25 (hidden)
Project Code |  |  | TA-416
Name of Line |  |  | NEEMRANA-II-BAREILLY (PG) 765KV D/C LINE,WZ-5 (Part-III)
Activity |  |  | Foundation | Qty
|  |  | Total | 302
|  |  | Completed (May-25) | 301
|  |  | Balance | 1
Micro Plan for month |  |  | 2025-06-01 | 1 | Nos | 4925228.89 | Rs. Cr.
Achievement for Month |  |  | Wk-1 | 1 | 100% | 4925228.89 | 100%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
Actual for the Month |  |  | Total | 1 | 1 | 4925228.89 | 1
Sl | Loc No. | Tower type | Classification | Conc. Vol (CuM) | Reinf (MT) | Sub-Cont | Work Plan | [7 empty] | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[7 empty] | Excavation |  | Stub-setting |  | Concreting |  | Earthing | Backfilling |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[7 empty] | Start | End | Start | End | Start | End |  |  | Rs. Lacs. | Date | [11 empty] | Rs. Lacs. | Rs. Lacs.
1 | 38/0 | DC2+18 | FS | 261.196 | 15.029 | AVI | 2025-05-21 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 4925228.89 | 2025-06-03 | 1 |  |  |  |  | 1 | 4925228.89 | 0 | 0 | 0 | 0 | 4925228.89 | 0
2 | [21 empty] | 0 |  |  |  |  | 0 | 0 | 0
3 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 261.196 | 15.029 | [9 empty] | 4925228.89 |  | 1 | 0 | 0 | 0 | 0 | 1 | 4925228.89 | 0 | 0 | 0 | 0 | 4925228.89 | 0
[13 empty] | STUB Setting-1 |  | 7224.33
[13 empty] | Earthing-1 |  | 7782.57
[13 empty] | Total Reve |  | 4940235.79

## Stub dispatch (hidden)
Location | Project | Tower type | Structure | B LOT | Actual PRS Date | STEEL Wt (MT) | BNA Wt | Disp Bal | May'24 Disp Plan | Wk01 | WK02 | WK03 | WK04 | Jun'24 Disp Plan MT | July'24 Disp Plan | Remark
JPR | TA416 | DA | Stub - 28 Nos | TA416-00018 | 2024-04-11 | 26.8617 | 0.46323 | 26.8617 | 0 |  |  |  | 0 | 26.8617 | 0 | As on date 160 stub reieved.
JPR | TA416 | DA | Stub - 132 Nos | TA416-00026 | 2024-04-15 | 126.634 | 2.184 | 126.634 | [5 empty] | 126.634 | 0
Total |  |  | 160 | [10 empty] | 153.4957

## Erection-Oct25
Sl | Location No. | Tower type | Tower Weight | Gang Name | Manpower | Section Incharge | Supervisor | Power Tools Issued (YES/NO) | Material Feeding | Starting Date | Completion Date | Tack-welding | Final checking | Revenue Planned | Revenue Realised
1 | 102/0 | DD45+35 | 156.8261 | Dhaneshwar Mahto | 45 |  | Mohit | Yes | Yes | 2025-10-19 | 2025-11-18 | 2025-11-21 | 2025-11-20 | 1182783
2 | 154/1 | DD45+25 | 122.8048 | Prayag Mahto | 53 | Milan Mal | Khemlal Mahto | Yes | Yes | 2025-10-29 | 2025-11-15 | 2025-11-18 | 2025-11-17 | 934927
3 | 159/2 | DCT+0 | 101.852 | Modina India-1&4 (PGCIL) | 55 | Milan Mal | Abu Alam | Yes | Yes | 2025-11-04 | 2025-11-19 | 2025-11-22 | 2025-11-21 | 470077
4 | 160/0 | DD60+18 | 129.341 | Dildar Electrical-2 & 3 PGCIL | 58 | Milan Mal | Jaylal Mahto | Yes | Yes | 2025-10-29 | 2025-11-15 | 2025-11-18 | 2025-11-17 | 1003256
5 | 165/4 | DD45+9 | 89.1428 | New Gang 4 |  | Milan Mal | Jaggarnath | Yes | Yes | 2025-11-08 | 2025-11-22 | 2025-11-25 | 2025-11-24 | 680590
6 | 165/5 | DD45+9 | 89.1428 | New Gang 5 |  | Milan Mal | Jaggarnath | Yes | Yes | 2025-11-08 | 2025-11-22 | 2025-11-25 | 2025-11-24 | 680590
7 | 166/0 | DD60+6 | 94.4077 | Aamir Khan | 19 | Milan Mal | Jaggarnath | Yes | Yes | 2025-11-05 | 2025-11-23 | 2025-11-26 | 2025-11-25 | 719574
8 | 167/0 | DD60+6 | 94.4077 | Anjum |  | Milan Mal | Gaurishankar | Yes | Yes | 2025-11-08 | 2025-11-23 | 2025-11-26 | 2025-11-25 | 719574
9 | 167/1 | DD60+0 | 80.408 | Sakila Khatun |  | Milan Mal | Baleshwar | Yes | Yes | 2025-11-12 | 2025-11-27 | 2025-11-30 | 2025-11-29 | 604881
10 | 172/1 | DA+3 | 39.4589 | Gokul Sarkar-1 |  | Milan Mal | Birkha Subba | Yes | Yes | 2025-11-12 | 2025-11-19 | 2025-11-22 | 2025-11-21 | 297143
11 | 173/0 | DD60+25 | 142.1014 | Muni Bibi- 1 & 2 |  | Milan Mal | Abbu alam | Yes | Yes | 2025-11-06 | 2025-11-28 | 2025-12-01 | 2025-11-30 | 1099828
12 | 174/0 | DD60+18 | 129.341 | Muni Bibi 1 |  | Milan Mal | Abbu alam | Yes | Yes | 2025-11-07 | 2025-11-27 | 2025-11-30 | 2025-11-29 | 1003256
13 | 175/1 | DA+0 | 37.7305 | Imadul Haque |  | Milan Mal | Vikash Sharma | Yes | Yes | 2025-11-06 | 2025-11-13 | 2025-11-16 | 2025-11-15 | 286911
14 | 182A/0 | DD45+6 | 85.2305 | Dildar Electricals-1 (PGCIL) |  | Milan Mal | Janki Mahto | Yes | Yes | 2025-11-08 | 2025-11-22 | 2025-11-25 | 2025-11-24 | 650023
15 | 183/0 | DD60+25 | 142.1014 | Anita Devi | 47 | Milan Mal | Janki Mahto | Yes | Yes | 2025-11-04 | 2025-11-24 | 2025-11-27 | 2025-11-26 | 1099828
16 | 184/0 | DD60+25 | 142.1014 | Jaman Mahto-1 (Ratna Devi) | 37 | Milan Mal | Mukesh Kumar | Yes | Yes | 2025-10-19 | 2025-11-14 | 2025-11-17 | 2025-11-16 | 1099828
17 | 184/1 | DB1+6 | 63.509 | Satish Kumar | 17 | Milan Mal | Aman Yadav | Yes | Yes | 2025-10-29 | 2025-11-08 | 2025-11-11 | 2025-11-10 | 480757
18 | 185/0 | DC2+0 | 64.2536 | Mithun Kumar | 45 | Milan Mal | Nunuchand | Yes | Yes | 2025-11-03 | 2025-11-11 | 2025-11-14 | 2025-11-13 | 470077
19 | 186/0 | DD60+35 | 173.1266 | New Gang 3 |  | Milan Mal | Nunuchand | Yes | Yes | 2025-11-09 | 2025-12-05 | 2025-12-08 | 2025-12-07 | 1294023
20 | 187/0 | DD60+25 | 142.1014 | Rupesh | 28 | Milan Mal | Pankaj Kumar Mahto | Yes | Yes | 2025-11-04 | 2025-11-14 | 2025-11-17 | 2025-11-16 | 1099828
21 | 200/0 | DB2+18 | 82.2388 | New Gang 2 |  | Milan Mal | Aman Yadav | Yes | Yes | 2025-11-09 | 2025-11-22 | 2025-11-25 | 2025-11-24 | 670636
22 | 201/0 | DC2+18 | 97.9334 | Satish Kumar |  | Milan Mal | Aman Yadav | Yes | Yes | 2025-11-09 | 2025-11-24 | 2025-11-27 | 2025-11-26 | 780122
23 | 201/1 | DD60+9 | 98.8356 | SK Samiul | 20 | Milan Mal | Aman Yadav | Yes | Yes | 2025-11-04 | 2025-11-22 | 2025-11-25 | 2025-11-24 | 753337
24 | 202/0 | DD60+55 | 226.737 | Nasirudin | 32 | Milan Mal | Ruplal Mahto | Yes | Yes | 2025-10-18 | 2025-11-20 | 2025-11-23 | 2025-11-22 | 1878263
25 | 203/1 | DD60+6 | 94.4077 | Anjum | 28 | Bibhu Kalyan Das | Gaurishankar | Yes | Yes | 2025-10-26 | 2025-11-07 | 2025-11-10 | 2025-11-09 | 719574
26 | 208/0 | DD60+25 | 142.1014 | Javir Hossen |  | Bibhu Kalyan Das | Dularchand Mahto | Yes | Yes | 2025-11-06 | 2025-11-26 | 2025-11-29 | 2025-11-28 | 1099828
27 | 209/1 | DA+3 | 39.4589 | Rahul Kumar | 18 | Bibhu Kalyan Das | Ravi Kumar | Yes | Yes | 2025-10-29 | 2025-11-06 | 2025-11-09 | 2025-11-08 | 297143
28 | 211/0 | DB1+9 | 65.7565 | Jwala Singh | 25 | Bibhu Kalyan Das | Abshik | Yes | Yes | 2025-10-23 | 2025-11-05 | 2025-11-08 | 2025-11-07 | 503365
29 | 211/2 | DA+0 | 37.7305 | Dildar Electrical-2 & 3 PGCIL |  | Bibhu Kalyan Das | Jaylal Mahto | Yes | Yes | 2025-11-16 | 2025-11-23 | 2025-11-26 | 2025-11-25 | 286911
30 | 211A/0 | DB2+0 | 54.4178 | Jwala Singh |  | Bibhu Kalyan Das | Abshik | Yes | Yes | 2025-11-06 | 2025-11-14 | 2025-11-17 | 2025-11-16 | 403998
31 | 211A/1 | DA-3 | 36.0448 | Nasirudin 2 |  | Bibhu Kalyan Das | Govind Mahto | Yes | Yes | 2025-11-08 | 2025-11-15 | 2025-11-18 | 2025-11-17 | 273608.9283
32 | 211A/2 | DA+0 | 37.7305 | Chitra Construction | 20 | Bibhu Kalyan Das | Govind Mahto | Yes | Yes | 2025-11-04 | 2025-11-12 | 2025-11-15 | 2025-11-14 | 286911
33 | 212/0 | DD45+3 | 75.4524 | Jaman Mahto-1 (Ratna Devi) |  | Bibhu Kalyan Das | Mukesh Kumar | Yes | Yes | 2025-11-15 | 2025-11-27 | 2025-11-30 | 2025-11-29 | 573550
34 | 213/0 | DD60+3 | 84.2993 | Teklal Mahto |  | Bibhu Kalyan Das | Kalicharan | Yes | Yes | 2025-11-08 | 2025-11-22 | 2025-11-25 | 2025-11-24 | 635073
35 | 213/1 | DA+0 | 37.7305 | Mithun Kumar |  | Bibhu Kalyan Das | Nunuchand | Yes | Yes | 2025-11-12 | 2025-11-19 | 2025-11-22 | 2025-11-21 | 286911
36 | 214/0 | DD45+0 | 72.2342 | Enjamul Haque | 18 | Bibhu Kalyan Das | Amit Shrivastav | Yes | Yes | 2025-10-19 | 2025-11-07 | 2025-11-10 | 2025-11-09 | 546238
37 | 214/1 | DA+6 | 44.7282 | Modina India-3 (PGCIL) |  | Bibhu Kalyan Das | Dhiraj Mahto | Yes | Yes | 2025-11-10 | 2025-11-17 | 2025-11-20 | 2025-11-19 | 342192
38 | 215/1 | DA+9 | 46.6235 | Chitra Construction |  | Bibhu Kalyan Das |  | Yes | Yes | 2025-11-13 | 2025-11-20 | 2025-11-23 | 2025-11-22 | 357181
39 | 216/0 | DB2+25 | 91.0829 | Rahul Kumar |  | Bibhu Kalyan Das | Ravi Kumar | Yes | Yes | 2025-11-07 | 2025-11-22 | 2025-11-25 | 2025-11-24 | 676263.874
40 | 217/0 | DD45+25 | 122.8048 | Enjamul Haque |  | Bibhu Kalyan Das | Amit Shrivastav | Yes | Yes | 2025-11-08 | 2025-11-28 | 2025-12-01 | 2025-11-30 | 994153
41 | 217A/0 | DB1+3 | 56.8632 | Rupesh |  | Bibhu Kalyan Das | Pankaj Kumar Mahto | Yes | Yes | 2025-11-15 | 2025-11-24 | 2025-11-27 | 2025-11-26 | 424198
42 | 218/0 | DD60+0 | 80.408 | Imadul Haque | 24 | Gurveet Singh | Vikash Sharma | Yes | Yes | 2025-10-14 | 2025-11-05 | 2025-11-08 | 2025-11-07 | 604881
43 | 218/1 | DA+3 | 39.4589 | Modina India-2 (PGCIL) | 30 | Gurveet Singh | Vikash Bishnoi | Yes | Yes | 2025-11-04 | 2025-11-11 | 2025-11-14 | 2025-11-13 | 297143
44 | 219/0 | DC2+18 | 97.9334 | Raj Labour | 27 | Gurveet Singh | Pankaj Kumar Mahto | Yes | Yes | 2025-11-04 | 2025-11-22 | 2025-11-25 | 2025-11-24 | 780122
45 | 220/0 | DD45+9 | 89.1428 | Gokul Sarkar-2 | 29 | Gurveet Singh | Birkha Subba | Yes | Yes | 2025-11-03 | 2025-11-18 | 2025-11-21 | 2025-11-20 | 680590
46 | 220/1 | DA+3 | 39.4589 | Gokul Sarkar-1 | 27 | Gurveet Singh | Birkha Subba | Yes | Yes | 2025-11-04 | 2025-11-11 | 2025-11-14 | 2025-11-13 | 297143
47 | 221/0 | DD60+18 | 129.341 | MD Akhtar |  | Gurveet Singh | Rewatlal Mahto | Yes | Yes | 2025-11-08 | 2025-11-27 | 2025-11-30 | 2025-11-29 | 1003256
48 | 222/0 | DD60+25 | 142.1014 | New Gang 1 |  | Gurveet Singh | Rewatlal Mahto | Yes | Yes | 2025-11-09 | 2025-11-30 | 2025-12-03 | 2025-12-02 | 1099828
49 | 223/0 | DC1+0 | 64.2536 | Teklal Mahto | 24 | Gurveet Singh | Kalicharan | Yes | Yes | 2025-10-23 | 2025-11-07 | 2025-11-10 | 2025-11-09 | 470077
50 | 223/2 | DA+0 | 37.7305 | Modina India-2 (PGCIL) |  | Gurveet Singh | Vikash Bishnoi | Yes | Yes | 2025-11-12 | 2025-11-19 | 2025-11-22 | 2025-11-21 | 286911
51 | 223/3 | DA+0 | 37.7305 | Dildar Electricals-1 (PGCIL) | 30 | Gurveet Singh | Vikash Bishnoi | Yes | Yes | 2025-11-04 | 2025-11-11 | 2025-11-14 | 2025-11-13 | 286911
52 | 226/0 | DC2+0 | 64.2536 | Subhash | 26 | Gurveet Singh | Yugal Kishor | Yes | Yes | 2025-10-29 | 2025-11-08 | 2025-11-11 | 2025-11-10 | 470077
53 | 227/0 | DB1+6 | 63.509 | Muni Bibi- 1 & 2 | 56 | Gurveet Singh | Abbu alam | Yes | Yes | 2025-10-22 | 2025-11-05 | 2025-11-08 | 2025-11-07 | 480757
54 | 228/0 | DD60+25 | 142.1014 | Sukruddin |  | Gurveet Singh | Lal Mohan | Yes | Yes | 2025-11-07 | 2025-11-29 | 2025-12-02 | 2025-12-01 | 1099828
55 | 229/0 | DD60+18 | 129.341 | MD Akhtar | 36 | Gurveet Singh | Rewatlal Mahto | Yes | Yes | 2025-10-12 | 2025-11-07 | 2025-11-10 | 2025-11-09 | 1003256
56 | 229/1 | DB1+6 | 63.509 | Nasirudin 2 | 28 | Gurveet Singh | Govind Mahto | Yes | Yes | 2025-10-25 | 2025-11-07 | 2025-11-10 | 2025-11-09 | 480757
57 | 229/2 | DA+6 | 44.7282 | Modina India-3 (PGCIL) | 30 | Gurveet Singh | Dhiraj Mahto | Yes | Yes | 2025-11-02 | 2025-11-09 | 2025-11-12 | 2025-11-11 | 342192
58 | 230/0 | DD60+0 | 80.408 | Javir Hossen | 24 | Gurveet Singh | Dularchand Mahto | Yes | Yes | 2025-10-09 | 2025-11-05 | 2025-11-08 | 2025-11-07 | 604881
59 | 239/0 | DD60+25 | 142.1014 | Subhash |  | Gurveet Singh | Yugal Kishor | Yes | Yes | 2025-11-09 | 2025-11-29 | 2025-12-02 | 2025-12-01 | 1099828
60 | 240/0 | DD60+25 | 142.1014 | Sakila Khatun | 37 | Gurveet Singh | Baleshwar | Yes | Yes | 2025-10-22 | 2025-11-11 | 2025-11-14 | 2025-11-13 | 1099828
61 | 245/0 | DD45+0 | 72.2342 | Sukruddin | 32 | Gurveet Singh | Lal Mohan | Yes | Yes | 2025-10-24 | 2025-11-06 | 2025-11-09 | 2025-11-08 | 546238
Formulas:
Tack-welding = +[Final checking]+1
Final checking = +[Completion Date]+2

## STG-Sep25 (hidden)
Project Code
Name of Line
Activity |  |  | Stringing | Qty |  |  |  |  | Rate @Kms | 905812
|  |  | Total | 115
|  |  | Completed (Aug-25) | 32.6
|  |  | Balance | 82.4
Micro Plan for month |  |  | 2025-09-01 | 23.985 | km | 21725900.82 | Rs. Cr
Achievement for Month |  |  | Wk-1 | 0 | 0% | 0 | 0%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
|  |  | Total | 0 | 0% | 0 | 0%
Sl | Section | Section Length (km) | Manual/TSE | Sub-Cont | Work Plan |  |  |  |  | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[5 empty] | Matl feeding | Pay-Out |  | Final Sag |  |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[6 empty] | Start | End | Start | End | Rs. Cr. | Date | [11 empty] | Rs. Cr. | Rs. Cr.
1 | 14/0-15/0 | 3.611 | TSE | Anarul | 2025-08-30 | 2025-09-01 | 2025-09-08 | 2025-09-09 | 2025-09-12 | 3270887.132 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3270887.132
2 | 12/0-13/0 | 3.92 | TSE |  | 2025-09-13 | 2025-09-14 | 2025-09-19 | 2025-09-20 | 2025-09-22 | 3550783.04 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3550783.04
3 | 3/0-4/0 | 0.28 | Manual-1 |  | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 253627.36 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253627.36
4 | 11/0-12/0 | 0.313 | Manual-1 |  | 2025-09-27 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 283519.156 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283519.156
5 | 13/0-14/0 | 0.319 | Manual-1 |  | 2025-09-15 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 288954.028 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288954.028
6 | 20/0-21/0 | 4.958 | TSE | Pankaj | 2025-09-03 | 2025-09-04 | 2025-09-09 | 2025-09-10 | 2025-09-13 | 4491015.896 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4491015.896
7 | 21/0-22/0 | 1.606 | TSE |  | 2025-09-14 | 2025-09-15 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 1454734.072 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1454734.072
8 | 18/0-19/0 | 0.323 | Manual-1 |  | 2025-09-20 | 2025-09-21 | 2025-09-26 | 2025-09-27 | 2025-09-30 | 292577.276 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292577.276
9 | 36/0-37/0 | 4.947 | TSE |  | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-07 | 2025-09-10 | 4481051.964 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4481051.964
10 | 30/0-31/0 | 2.75 | TSE |  | 2025-09-11 | 2025-09-12 | 2025-09-17 | 2025-09-18 | 2025-09-21 | 2490983 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2490983
11 | 29/0-30/0 | 0.27 | TSE |  | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-22 | 2025-09-22 | 244569.24 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244569.24
12 | 28/0-29/0 | 0.688 | Manual-2 |  | 2025-09-27 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 623198.656 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623198.656
13 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 23.985 | [7 empty] | 21725900.82 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21725900.82