## FDN-June25 (hidden)
Project Code |  |  | TA-416
Name of Line |  |  | NEEMRANA-II-BAREILLY (PG) 765KV D/C LINE,WZ-5 (Part-III)
Activity |  |  | Foundation | Qty
|  |  | Total | 302
|  |  | Completed (May-25) | 301
|  |  | Balance | 1
Micro Plan for month |  |  | 2025-06-01 | 1 | Nos | 4925228.89 | Rs. Cr.
Achievement for Month |  |  | Wk-1 | 1 | 100% | 4925228.89 | 100%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
Actual for the Month |  |  | Total | 1 | 1 | 4925228.89 | 1
Sl | Loc No. | Tower type | Classification | Conc. Vol (CuM) | Reinf (MT) | Sub-Cont | Work Plan | [7 empty] | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[7 empty] | Excavation |  | Stub-setting |  | Concreting |  | Earthing | Backfilling |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[7 empty] | Start | End | Start | End | Start | End |  |  | Rs. Lacs. | Date | [11 empty] | Rs. Lacs. | Rs. Lacs.
1 | 38/0 | DC2+18 | FS | 261.196 | 15.029 | AVI | 2025-05-21 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 4925228.89 | 2025-06-03 | 1 |  |  |  |  | 1 | 4925228.89 | 0 | 0 | 0 | 0 | 4925228.89 | 0
2 | [21 empty] | 0 |  |  |  |  | 0 | 0 | 0
3 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 261.196 | 15.029 | [9 empty] | 4925228.89 |  | 1 | 0 | 0 | 0 | 0 | 1 | 4925228.89 | 0 | 0 | 0 | 0 | 4925228.89 | 0
[13 empty] | STUB Setting-1 |  | 7224.33
[13 empty] | Earthing-1 |  | 7782.57
[13 empty] | Total Reve |  | 4940235.79

## Stub dispatch (hidden)
Location | Project | Tower type | Structure | B LOT | Actual PRS Date | STEEL Wt (MT) | BNA Wt | Disp Bal | May'24 Disp Plan | Wk01 | WK02 | WK03 | WK04 | Jun'24 Disp Plan MT | July'24 Disp Plan | Remark
JPR | TA416 | DA | Stub - 28 Nos | TA416-00018 | 2024-04-11 | 26.8617 | 0.46323 | 26.8617 | 0 |  |  |  | 0 | 26.8617 | 0 | As on date 160 stub reieved.
JPR | TA416 | DA | Stub - 132 Nos | TA416-00026 | 2024-04-15 | 126.634 | 2.184 | 126.634 | [5 empty] | 126.634 | 0
Total |  |  | 160 | [10 empty] | 153.4957

## Erection-Nov25
Sl | Location No. | Tower type | Tower Weight | Gang Name | Manpower | Section Incharge | Supervisor | Power Tools Issued (YES/NO) | Material Feeding | Starting Date | Completion Date | Tack-welding | Final checking | Revenue Planned | Revenue Realised
1 | 1/8 | DA+1.5 | 17.6337 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 236872.9816
2 | 1/9 | DA+1.5 | 17.6337 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 236872.9816
3 | 12/2 | DA+1.5 | 17.6337 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 236872.9816
4 | 12/8 | DA-3 | 15.8578 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 213017.3707
5 | 15/0 | DD45+3 | 38.1379 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 512306.1286
6 | 16/0 | DB2+6 | 34.1664 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 458957.6676
7 | 28/0 | DD45+9 | 48.342 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 649377.9651
8 | 37/0 | DD45+9 | 48.342 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 649377.9651
9 | 42/2 | DA-3 | 15.8578 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 213017.3707
10 | 52/1 | DA-1.5 | 16.4524 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 221005.7071
11 | 62/0 | DD60+9 | 53.1226 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 713596.356
12 | 65A/3 | DC1+0 | 29.7779 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 400006.7322
13 | 110/0 | DC2+3 | 31.8647 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 428038.2061
14 | 167A/0 | DD45+3 | 38.1379 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 512306.1286
15 | 197/2 | DA+3 | 18.1188 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 243390.0553
16 | 211/1 | DA+0 | 16.9667 |  |  | Abhishek Kumar | Sunil Kumar | [6 empty] | 227914.0035
17 | 220/5 | DA-1.5 | 16.4524 |  |  | Abhishek Kumar | Sunil Kumar | [6 empty] | 221005.7071
18 | 2/0 | DB2+0 | 27.0921 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 363928.8375
19 | 2A/1 | DA-3 | 15.8578 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 213017.3707
20 | 13/4 | DA+9 | 22.4884 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 302086.3279
21 | 13/5 | DA+3 | 18.1188 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 243390.0553
22 | 34/2 | DA+1.5 | 17.6337 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 236872.9816
23 | 35A/0 | DB2-3 | 24.7001 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 331796.2955
24 | 36/0 | DC1-3 | 27.2498 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 366046.8186
25 | 36/1 | DA+9 | 22.4884 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 302086.3279
26 | 36/2 | DA+6 | 21.0969 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 283394.8726
27 | 40/0 | DD45+0 | 35.8452 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 481508.8
28 | 42/1 | DA+0 | 16.9667 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 227914.0035
29 | 44/0 | DC2+3 | 31.8647 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 428038.2061
30 | 44/1 | DA+0 | 16.9667 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 227914.0035
31 | 44A/0 | DC2+3 | 31.8647 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 428038.2061
32 | 44A/1 | DA-1.5 | 16.4524 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 221005.7071
33 | 44A/2 | DA+0 | 16.9667 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 227914.0035
34 | 45/0 | DD45+0 | 35.8452 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 481508.8
35 | 46/0 | DD60+9 | 53.1226 |  |  | Dharmendra Pandey | Bipattaran Dolui | [6 empty] | 713596.356
36 | 94/0 | DD45+6 | 46.4686 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 624212.9859
37 | 94/1 | DA+9 | 22.4884 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 302086.3279
38 | 94/2 | DA+9 | 22.4884 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 302086.3279
39 | 94/3 | DA+9 | 22.4884 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 302086.3279
40 | 95/0 | DC2+9 | 39.6224 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 532248.3306
41 | 95/1 | DA+3 | 18.1188 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 243390.0553
42 | 95A/0 | DB1+9 | 36.5854 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 491451.0468
43 | 97/0 | DB2+1.5 | 27.86 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 374243.689
44 | 107/1 | DA+3 | 18.1188 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 243390.0553
45 | 111/0 | DC1+0 | 29.7779 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 400006.7322
46 | 114/1 | DB1+6 | 34.1664 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 458957.6676
47 | 166/1 | DB1+6 | 34.1664 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 458957.6676
48 | 167A/1 | DC1+0 | 29.7779 |  |  | Rajkumar Tomar | Sahadev Gope | [6 empty] | 400006.7322
49 | 181/3 | DA+6 | 21.0969 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 283394.8726
50 | 182/0 | DD60+0 | 39.5967 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 531902.4039
51 | 182/6 | DA+3 | 18.1188 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 243390.0553
52 | 184/1 | DA+3 | 18.1188 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 243390.0553
53 | 193/0 | DB2+6 | 34.1664 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 458957.6676
54 | 195/0 | DB1+0 | 27.0921 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 363928.8375
55 | 199/1 | DA+6 | 21.0969 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 283394.8726
56 | 199/3 | DA+3 | 18.1188 |  |  | Abhishek Kumar | Bhola Karmakat | [6 empty] | 243390.0553
57 | 211/4 | DA+6 | 21.0969 |  |  | Abhishek Kumar | Sunil Kumar | [6 empty] | 283394.8726
58 | 211/5 | DA+6 | 21.0969 |  |  | Abhishek Kumar | Sunil Kumar | [6 empty] | 283394.8726
59 | 211/6 | DA+6 | 21.0969 |  |  | Abhishek Kumar | Sunil Kumar | [6 empty] | 283394.8726
60 | 212/0 | DB2+3 | 28.3681 |  |  | Abhishek Kumar | Sunil Kumar | [6 empty] | 381068.0559
61 | 212/1 | DA+6 | 21.0969 |  |  | Abhishek Kumar | Sunil Kumar | [6 empty] | 283394.8726
62 | 215/0 | DB1+6 | 34.1664 |  |  | Abhishek Kumar | Sunil Kumar | [6 empty] | 458957.6676
63 | 220/8 | DA+3 | 18.1188 |  |  | Abhishek Kumar | Sunil Kumar | [6 empty] | 243390.0553
64 | 221/0 | DB2+9 | 36.5854 |  |  | Abhishek Kumar | Sunil Kumar | [6 empty] | 491451.0468
65 | 17/0 | DC1+18 | 53.2386 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 715154.6646
66 | 17/1 | DA+0 | 16.9667 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 227914.0035
67 | 18/0 | DD45+0 | 35.8452 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 481508.8
68 | 25/2 | DA+1.5 | 17.6337 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 236872.9816
69 | 26/0 | DD45+0 | 35.8452 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 481508.8
70 | 30/0 | DD60+3 | 41.8329 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 561941.0367
71 | 31/0 | DD45+6 | 46.4686 |  |  | Dharmendra Pandey | Anil Kumar | [6 empty] | 624212.9859

## STG-Sep25 (hidden)
Project Code
Name of Line
Activity |  |  | Stringing | Qty |  |  |  |  | Rate @Kms | 905812
|  |  | Total | 115
|  |  | Completed (Aug-25) | 32.6
|  |  | Balance | 82.4
Micro Plan for month |  |  | 2025-09-01 | 23.985 | km | 21725900.82 | Rs. Cr
Achievement for Month |  |  | Wk-1 | 0 | 0% | 0 | 0%
|  |  | Wk-2 | 0 | 0% | 0 | 0%
|  |  | Wk-3 | 0 | 0% | 0 | 0%
|  |  | Wk-4 | 0 | 0% | 0 | 0%
|  |  | Wk-5 | 0 | 0% | 0 | 0%
|  |  | Total | 0 | 0% | 0 | 0%
Sl | Section | Section Length (km) | Manual/TSE | Sub-Cont | Work Plan |  |  |  |  | Revenue | Actual Completion | Physical Completion | [5 empty] | Revenue Achievement | [5 empty] | Shortfall
[5 empty] | Matl feeding | Pay-Out |  | Final Sag |  |  |  | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total | Wk-1 | Wk-2 | Wk-3 | Wk-4 | Wk-5 | Total
[6 empty] | Start | End | Start | End | Rs. Cr. | Date | [11 empty] | Rs. Cr. | Rs. Cr.
1 | 14/0-15/0 | 3.611 | TSE | Anarul | 2025-08-30 | 2025-09-01 | 2025-09-08 | 2025-09-09 | 2025-09-12 | 3270887.132 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3270887.132
2 | 12/0-13/0 | 3.92 | TSE |  | 2025-09-13 | 2025-09-14 | 2025-09-19 | 2025-09-20 | 2025-09-22 | 3550783.04 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3550783.04
3 | 3/0-4/0 | 0.28 | Manual-1 |  | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 253627.36 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253627.36
4 | 11/0-12/0 | 0.313 | Manual-1 |  | 2025-09-27 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 283519.156 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283519.156
5 | 13/0-14/0 | 0.319 | Manual-1 |  | 2025-09-15 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 288954.028 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288954.028
6 | 20/0-21/0 | 4.958 | TSE | Pankaj | 2025-09-03 | 2025-09-04 | 2025-09-09 | 2025-09-10 | 2025-09-13 | 4491015.896 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4491015.896
7 | 21/0-22/0 | 1.606 | TSE |  | 2025-09-14 | 2025-09-15 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 1454734.072 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1454734.072
8 | 18/0-19/0 | 0.323 | Manual-1 |  | 2025-09-20 | 2025-09-21 | 2025-09-26 | 2025-09-27 | 2025-09-30 | 292577.276 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292577.276
9 | 36/0-37/0 | 4.947 | TSE |  | 2025-08-30 | 2025-08-31 | 2025-09-06 | 2025-09-07 | 2025-09-10 | 4481051.964 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4481051.964
10 | 30/0-31/0 | 2.75 | TSE |  | 2025-09-11 | 2025-09-12 | 2025-09-17 | 2025-09-18 | 2025-09-21 | 2490983 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2490983
11 | 29/0-30/0 | 0.27 | TSE |  | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-22 | 2025-09-22 | 244569.24 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244569.24
12 | 28/0-29/0 | 0.688 | Manual-2 |  | 2025-09-27 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 623198.656 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623198.656
13 | [9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 23.985 | [7 empty] | 21725900.82 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21725900.82