## Summary
Project -TA513-Powergrid Bikaner IV Transmission Limited | [13 empty] | 2026-06-28
LOA DT Completion Schedule DT 21.12.2026 Project Value 666 Cr(S-530,F&I-12Cr.,C-124 Cr.) | 2025-01-21 |  |  | Project Period (Months):- |  | 23 |  | P.Completion | 2026-12-22 |  | No. of Days Delayed:- | 177 |  |  | F&I | 12
Progress Summary -Power Grid Bikaner IV Transmission limited | [13 empty] | 2026-06-26
Activity | BOQ Qty | Final Estimated Qty | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks
Detailed Survey | 222.93 | 230.36 | 222.93 | 230.36 | 0 | 0 | 0 | 0 | 78.73 | 230.36 | 0 | 0 | 0
Check Survey | 222.93 | 230.36 | 222.93 | 230.36 | 0 | 0 | 0 | 0 | 222.93 | 230.36 | 0 | 0 | 0 | 13km check Survey Approval Awaited
Foundation | 597 | 619 | 547 | 89 | 28 | 35 | 0 | 11 | 575 | 100 | 519 | 0 | 1 | SP Line -46/1
Earthing | 597 | 619 | 547 | 17 | 28 | 0 | 0 | 0 | 575 | 17 | 602 | 0 | 0
Tower Erection | 597 | 619 | 465 | 31 | 35 | 16 | 0 | 4 | 500 | 35 | 584 | 0 | 0
Tack welding | 597 | 619 | 465 | 0 | 35 | 0 | 0 | 0 | 500 | 0 | 619 | 0 | 0
Stringing | 222.93 | 230.56 | 140 | 0 | 13 | 0 | 0 | 0 | 153 | 0 | 230.56 | 0 | 0
OPGW | 222.93 | 230.56 | 50 | 0 | 35 | 0 | 0 | 0 | 85 | 0 | 230.56 | 0 | 0
Line Wise Progress
400 kV Siwani-Fatehabad Transmission Limited
Activity | BOQ Qty | Final Estimated Qty | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks
Detailed Survey | 78.73 | 82.8 | 78.73 | 82.8 | 0 | 0 |  |  | 78.73 | 82.8 | 0
Check Survey | 78.73 | 82.8 | 78.73 | 82.8 | 0 | 0 |  |  | 78.73 | 82.8 | 0 |  |  | Gantry to AP3-Approval Awaited , Submitted on date 24.12.2025
Foundation | 210 | 220 | 197 | 25 | 8 | 10 |  | 1 | 205 | 26 | 194 | 0 | 0
Earthing | 210 | 220 | 197 | 10 | 8 | 0 |  |  | 205 | 10 | 210
Tower Erection | 210 | 220 | 155 | 7 | 20 | 5 |  |  | 175 | 7 | 213 | 0 | 0
Tack welding | 210 | 220 | 155 | 0 | 20 | 0 |  |  | 175 | 0 | 220
Stringing | 78.73 | 83 | 40 | 0 | 8 | 0 |  |  | 48 | 0 | 83
OPGW | 78.73 | 83 | 15 | 0 | 15 | 0 |  |  | 30 | 0 | 83
400 kV Siwani-Patran Transmission Limited
Activity | BOQ Qty | Final Estimated Qty | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks
Detailed Survey | 144.2 | 147.56 | 144.2 | 147.56 | 0 | 0 |  |  | 0 | 147.56 | 0
Check Survey | 144.2 | 147.56 | 144.2 | 147.56 | 0 | 0 |  |  | 144.2 | 147.56 | 0 |  |  | Gantry to AP3-Approval Awaited , Submitted on date 06.02.2026
Foundation | 387 | 399 | 350 | 64 | 20 | 25 |  | 10 | 370 | 74 | 325 |  | 1 | Gang shifting to Loc-46/1
Earthing | 387 | 399 | 350 | 7 | 20 | 0 |  |  | 370 | 7 | 392
Tower Erection | 387 | 399 | 310 | 24 | 15 | 11 |  | 4 | 325 | 28 | 371 | 0 | 0
Tack welding | 387 | 399 | 310 | 0 | 15 | 0 |  |  | 325 | 0 | 399
Stringing | 144.2 | 147.56 | 100 | 0 | 5 | 0 |  |  | 105 | 0 | 147.56
OPGW | 144.2 | 147.56 | 35 | 0 | 20 | 0 |  |  | 55 | 0 | 147.56

## LS Physical
M/S KEC International Limited
400 KV D/C Siwani To Fatehabad & Siwani-Patran TL
Tower Base Measurement | [9 empty] | 30
S.NO | Line | Date of Measurement | Location | Type of Tower | District | Tehsil | Village | KEC representatives | PGCIL Representatives | Remarks
1 | SP Line | 19.06.2026 | 37/1 | 5DA+0 | Hisar | Hisar | Landhari sukh nambran | Mr.Debashish Sarkar | Mr.Jai Shankar | Compl
2 | SP Line | 19.06.2026 | 39/0 | 5DC2+9 | Hisar | Hisar | Landhari sukh nambran | Mr.Debashish Sarkar | Mr.Jai Shankar | Compl
3 | SP Line | 20.06.2026 | 36/1 | 5DA+3 | Hisar | Hisar | Landhari sukh nambran | Mr.Ujjjwal Ghosh | Mr.Jai Shankar | Compl
4 | SP Line | 20.06.2026 | 36/4 | 5DA-3 | Hisar | Hisar | Landhari sukh nambran | Mr.Ujjjwal Ghosh | Mr.Jai Shankar | Compl
5 | SP Line | 20.06.2026 | 36/5 | 5DA+6 | Hisar | Hisar | Landhari sukh nambran | Mr.Ujjjwal Ghosh | Mr.Jai Shankar | Compl
6 | SP Line | 22.06.2026 | 39/1 | 5DA+3 | Hisar | Hisar | Nangthala | Mr.Ujjjwal Ghosh |  | Marking done
7 | SP Line | 22.06.2026 | 39/2 | 5DA+3 | Hisar | Hisar | Nangthala | Mr.Ujjjwal Ghosh |  | Marking done
8 | SP Line | 23.06.2026 | 45/0 | 5DD60+0 | Hisar | Hisar | Nangthala | Mr.Ujjjwal Ghosh | Mr.Jai Shankar | Compl
9 | SP Line | 23.06.2026 | 45/1 | 5DA+6 | Hisar | Hisar | Nangthala | Mr.Ujjjwal Ghosh | Mr.Jai Shankar | Compl
10 | SP Line | 26.06.2026 | 44/2 | 5DA+6 | Hisar | Hisar | Nangthala | Mr.Ujjjwal Ghosh | Mr.Jai Shankar | Compl
10 | SP Line |  | 42/0 | 5DC2+6 | Hisar | Hisar | Nangthala | Mr.Ujjjwal Ghosh | Mr.Jai Shankar | Compl
11 | SP Line |  | 43/0 | 5DC1+0 | Hisar | Hisar | Nangthala | Mr.Ujjjwal Ghosh | Mr.Jai Shankar | Compl
12 | SP Line |  | 44/1 | 5DA+0 | Hisar | Hisar | Nangthala | Mr.Ujjjwal Ghosh | Mr.Jai Shankar | Compl
13 | SP Line |  | 47/0 | 5DC1+3 | Hisar | Hisar | Nangthala | Mr.Ujjjwal Ghosh | Mr.Jai Shankar | Compl
14 | SP Line |  | 51/3 | 5DA+0 | Fatehabad | Bhuna | Nehla | Mr.Sushil kushwaha | Mr.Rahul | Compl
15 | SP Line |  | 51/4 | 5DA+6 | Fatehabad | Bhuna | Nehla | Mr.Sushil kushwaha | Mr.Rahul | Compl
16 | SP Line |  | 51/5 | 5DA+6 | Fatehabad | Bhuna | Nehla | Mr.Sushil kushwaha | Mr.Rahul | Compl
17 | SP Line |  | 52/0 | 5DB1+3 | Fatehabad | Bhuna | Nehla | Mr.Sushil kushwaha | Mr.Rahul | Compl
18 | SP Line |  | 52/1 | 5DA+0 | Fatehabad | Bhuna | Nehla | Mr.Sushil kushwaha | Mr.Rahul | Compl
19 | SP Line |  | 52/2 | 5DA+0 | Fatehabad | Bhuna | Nehla | Mr.Sushil kushwaha | Mr.Rahul | Compl
20 | SP Line |  | 52/3 | 5DA+0 | Fatehabad | Bhuna | Nehla | Mr.Sushil kushwaha | Mr.Rahul | Compl
21 | SP Line |  | 52/4 | 5DA+0 | Fatehabad | Bhuna | Nehla | Mr.Sushil kushwaha | Mr.Rahul | Compl
22 | SP Line |  | 52/5 | 5DA+0 | Fatehabad | Bhuna | Nehla | Mr.Sushil kushwaha | Mr.Rahul | Compl
23 | SP Line |  | 54/1 | 5DA+0 | Fatehabad | Bhuna | Nehla | Mr.Sushil kushwaha | Mr.Rahul | Compl
24 | SP Line |  | 54/2 | 5DA+0 | Fatehabad | Bhuna | Nehla | Mr.Sushil kushwaha | Mr.Rahul | Compl
25 | SP Line |  | 54/3 | 5DA+3 | Fatehabad | Bhuna | Nehla | Mr.Sushil kushwaha | Mr.Rahul | Compl
26 | SP Line |  | 56/3 | 5DA+3 | Hisar | Uklana | Pabra | Mr.Piyush | Mr.Chaman | Compl
27 | SP Line |  | 56/0 | 5DB1+6 | Hisar | Uklana | Pabra | Mr.Piyush | Mr.Chaman | Compl
28 | SP Line |  | 54/7 | 5DA+6 | Hisar | Uklana | Pabra | Mr.Piyush | Mr.Chaman | Compl
29 | SP Line |  | 54/8 | 5DA+3 | Hisar | Uklana | Pabra | Mr.Piyush | Mr.Chaman | Compl

## T.Marking (hidden)
Client-Powergrid Bikaner IV Tranmission Limited |  |  |  |  | Line | Line Length | Compl | ROW
Project-Siwani-Patran TL & Siwani-Fatehabad TL |  |  |  |  | SP | 147.586 | 103.806 | 43.78
Tree Marking Details |  |  |  |  | SF | 82.798 | 61.252 | 21.546
400 Kv Siwani-Patran TL |  |  |  |  | 400 Kv Siwani-fatehabad TL
S.NO | Section |  | Section Length (KM) | Status | S.NO | Section |  | Section Length (KM) | Status
| From | To |  |  |  | From | To
1 | S.Gantry | AP-5 | 13.157 | The farmer has refused to allow the commencement of work due to ROW | 1 | S.Gantry | AP-3 | 6.528 | The farmer has refused to allow the commencement of work due to ROW
2 | AP-5 | AP-7 | 2.616 | Completed | 2 | AP-3 | 5/1 | 7.398 | Completed
3 | AP-7 | 19/3 | 19.915 | The farmer has refused to allow the commencement of work due to ROW | 3 | 5/1 | 9/0 | 13.009 | The farmer has refused to allow the commencement of work due to ROW
4 | 19/3 | 26/0 | 9.563 | Completed | 4 | 9/1 | 14/0 | 6.018 | Completed
5 | AP26 | AP29 | 3.335 | The farmer has refused to allow the commencement of work due to ROW | 5 | 14/0 | 15/3 | 2.009 | The farmer has refused to allow the commencement of work due to ROW
6 | AP29 | 36/1 | 10.027 | Completed | 6 | 15/3 | F.Gantry | 47.836 | Completed
7 | 36/1 | 36/3 | 0.805 | The farmer has refused to allow the commencement of work due to ROW
8 | 36/3 | AP43 | 4.742 | Completed
9 | AP43 | AP50 | 7.294 | Completed
10 | AP50 | 106/1 | 65.96 | Completed
11 | 106/1 | 115/0 | 6.568 | The farmer has refused to allow the commencement of work due to ROW
12 | AP115 | AP120 | 3.604 | Completed
Total |  |  | 147.586 |  | Total |  |  | 82.798

## ERT (hidden)
Client-Powergrid Bikaner IV Tranmission Limited
Project-Siwani-Patran TL & Siwani-Fatehabad TL
Soil Resistivity Details
Soil Resitivity-Siwani-Fatehabad TL | [5 empty] | Soil Resitivity-Siwani-Patran TL
S.No | Approx. Distance (3Kms) | Chainage in Kms | Instrument Reading (R) (Ohm) | S.R. Value (P=2πARX1) (ohm-m) | Remarks | S.No | Approx. Distance (3Kms) | Chainage in Kms | Instrument Reading (R) (Ohm) | S.R. Value (P=2πARX1) (ohm-m) | Remarks
1 | AP1A/0 | 0.2 | 0.075 | 23.5714 | Completed | 1 | GANTY SS SIWANI | 0
2 | AP1B/0 | 1.219 | 0.185 | 58.1429 | Completed | 2 | 1C/0 | 1.349 | 0.0655 | 20.5857 | Completed
3 | 2C/0 | 4.009 | 0.14 | 44 | Completed | 3 | 2A/0 | 4.337 | 0.01 | 3.1429 | Completed
4 | 3/0 | 6.527 | 0.13 | 40.8571 | Completed | 4 | 2D/0 | 6.47 | 0.11 | 34.5714 | Completed
5 | 3/7 | 9.307 | 0.135 | 42.4286 | Completed | 5 | 3/6 | 9.248 | 0.1 | 31.4286 | Completed
6 | 4/3 | 12.112 | 0.0515 | 16.1857 | Completed | 6 | 4/2 | 11.961 | 0.0115 | 3.6143 | Completed
7 | 5/3 | 14.727 | 0.0535 | 16.8143 | Completed | 7 | 5/4 | 14.556 | 0.0275 | 8.6429 | Completed
8 | 6/2 | 17.447 | 0.08 | 25.1429 | Completed | 8 | 8/2 | 17.254 | 0.0295 | 9.2714 | Completed
9 | 6/9 | 20.296 | 0.27 | 84.8571 | Completed | 9 | 10/0 | 20.09 | 0.0195 | 6.1286 | Completed
10 | 8/0 | 22.988 | 0.18 | 56.5714 | Completed | 10 | 11/4 | 22.888 | 0.016 | 5.0286 | Completed
11 | 8/7 | 25.684 | 0.015 | 4.7143 | Completed | 11 | 12/6 | 25.8 | 0.0125 | 3.9286 | Completed
12 | 10/0 | 28.106 | 0.0315 | 9.9 | Completed | 12 | 14/5 | 28.484 | 0.025 | 7.8571 | Completed
13 | 12/0 | 30.53 | 0.018 | 5.6571 | Completed | 13 | 15B/0 | 30.069 | 0.008 | 2.5143 | Completed
14 | 14/0 | 32.951 | 0.0185 | 5.8143 | Completed | 14 | 17/0 | 32.905 | 0.0085 | 2.6714 | Completed
15 | 16/1 | 35.759 | 0.011 | 3.4571 | Completed | 15 | 19/3 | 35.682 | 0.0095 | 2.9857 | Completed
16 | 16/8 | 38.586 | 0.0295 | 9.2714 | Completed | 16 | 21/4 | 38.642 | 0.02 | 6.2857 | Completed
17 | 17/6 | 41.292 | 0.116 | 36.4571 | Completed | 17 | 23/2 | 41.289 | 0.017 | 5.3429 | Completed
18 | 19/0 | 43.996 | 0.0215 | 6.7571 | Completed | 18 | 25/0 | 43.654 | 0.0155 | 4.8714 | Completed
19 | 21/0 | 45.533 | 0.017 | 5.3429 | Completed | 19 | 27/0 | 46.409 | 0.01 | 3.1429 | Completed
20 | 23/0 | 47.146 | 0.004 | 1.2571 | Completed | 20 | 29/0 | 48.579 | 0.01 | 3.1429 | Completed
21 | 24/0 | 49.935 | 0.012 | 3.7714 | Completed | 21 | 30/0 | 50.999 | 0.0115 | 3.6143 | Completed
22 | 25/0 | 51.934 | 0.008 | 2.5143 | Completed | 22 | 30/6 | 53.345 | 0.024 | 7.5429 | Completed
23 | 28/0 | 54.595 | 0.021 | 6.6 | Completed | 23 | 32/0 | 55.289 | 0.016 | 5.0286 | Completed
24 | 30/0 | 55.586 | 0.03 | 9.4286 | Completed | 24 | 33/0 | 57.277 | 0.019 | 5.9714 | Completed
25 | 32/0 | 57.799 | 0.135 | 42.4286 | Completed | 25 | 36/0 | 58.179 | 0.021 | 6.6 | Completed
26 | 33/0 | 59.807 | 0.022 | 6.9143 | Completed | 26 | 36/4 | 59.754 | 0.0155 | 4.8714 | Completed
27 | 36/0 | 62.571 | 0.0035 | 1.1 | Completed | 27 | 37/1 | 60.989 | 0.0165 | 5.1857 | Completed
28 | 39/0 | 64.426 | 0.0105 | 3.3 | Completed | 28 | 41/0 | 62.728 | 0.0215 | 6.7571 | Completed
29 | 40A/0 | 66.382 | 0.0115 | 3.6143 | Completed | 29 | 45/0 | 65.529 | 0.022 | 6.9143 | Completed
30 | 42/0 | 68.373 | 0.014 | 4.4 | Completed | 30 | 47/2 | 68.345 | 0.0305 | 9.5857 | Completed
31 | 46/0 | 70.247 | 0.0265 | 8.3286 | Completed | 31 | 49/0 | 71.08 | 0.0405 | 12.7286 | Completed
32 | 48/0 | 72.585 | 0.0235 | 7.3857 | Completed | 32 | 51/0 | 72.896 | 0.0565 | 17.7571 | Completed
33 | 50/0 | 74.927 | 0.0275 | 8.6429 | Completed | 33 | 52/0 | 75.271 | 0.0155 | 4.8714 | Completed
34 | 50A/1 | 76.106 | 0.029 | 9.1143 | Completed | 34 | 53/0 | 77.571 | 0.014 | 4.4 | Completed
35 | 54/0 | 77.199 | 0.014 | 4.4 | Completed | 35 | 54/7 | 80.515 | 0.0155 | 4.8714 | Completed
36 | 58/0 | 80.089 | 0.032 | 10.0571 | Completed | 36 | 55/5 | 82.907 | 0.0305 | 9.5857 | Completed
37 | 63/0 | 82.957 | 0.2275 | 71.5 | Completed | 37 | 56/0 | 84.533 | 0.036 | 11.3143 | Completed
[6 empty] | 38 | 57/0 | 86.532 | 0.05 | 15.7143 | Completed
[6 empty] | 39 | 59/0 | 88.534 | 0.083 | 26.0857 | Completed
[6 empty] | 40 | 63/0 | 90.965 | 0.053 | 16.6571 | Completed
[6 empty] | 41 | 65/0 | 93.888 | 0.074 | 23.2571 | Completed
[6 empty] | 42 | 68/0 | 96.586 | 0.132 | 41.4857 | Completed
[6 empty] | 43 | 70/0 | 99.611 | 0.074 | 23.2571 | Completed
|  |  |  | 74 |  | 44 | 73/0 | 100.894 | 0.078 | 24.5143 | Completed
[6 empty] | 45 | 74/7 | 104.041 | 0.1925 | 60.5 | Completed
[6 empty] | 46 | 76/0 | 105.301 | 0.255 | 80.1429 | Completed
[6 empty] | 47 | 78/0 | 107.679 | 0.237 | 74.4857 | Completed
[6 empty] | 48 | 80/0 | 110.449 | 0.4255 | 133.7286 | Completed
[6 empty] | 49 | 84/0 | 111.682 | 0.677 | 212.7714 | Completed
[6 empty] | 50 | 87/0 | 113.838 | 0.2315 | 72.7571 | Completed
[6 empty] | 51 | 91/0 | 115.068 | 0.483 | 151.8 | Completed
[6 empty] | 52 | 92/6 | 117.682 | 0.405 | 127.2857 | Completed
[6 empty] | 53 | 94/0 | 120.421 | 0.64 | 201.1429 | Completed
[6 empty] | 54 | 94/7 | 123.231 | 0.271 | 85.1714 | Completed
[6 empty] | 55 | 96/0 | 125.138 | 0.217 | 68.2 | Completed
[6 empty] | 56 | 98/4 | 127.582 | 0.038 | 11.9429 | Completed
[6 empty] | 57 | 100/0 | 129.536 | 0.5525 | 173.6429 | Completed
[6 empty] | 58 | 102/0 | 132.526 | 0.19 | 59.7143 | Completed
[6 empty] | 59 | 105/0 | 134.478 | 0.227 | 71.3429 | Completed
[6 empty] | 60 | 106/1 | 137.255 | 0.785 | 246.7143 | Completed
[6 empty] | 61 | 108/0 | 140.041 | 0.565 | 177.5714 | Completed
[6 empty] | 62 | 112/0 | 142.074 | 0.48 | 150.8571 | Completed
[6 empty] | 63 | 116/0 | 144.881 | 0.905 | 284.4286 | Completed
[6 empty] | 64 | 120/0 | 147.428 | 0.641 | 201.4571 | Completed

## VC SF
Visual Chart | [34 empty] | 2026-06-26
Progress | [5 empty] | WXMIDNC | [20 empty] | LEGEND
Foundation |  |  | Nos. | 26 / 220 |  | 220 |  |  |  |  | TL03: Siwani– Fatehabad (PG) 400 kV TL | [15 empty] | Crossings |  |  |  |  | Status
Earthing |  |  | Nos. | 10 / 220 |  | 220 |  |  |  |  | Client: Powergrid Bikaner IV Transmission limited | [15 empty] | #VALUE! | Powerline Crossing |  |  |  |  | In Progress
Erection |  |  | Nos. | 7 / 220 |  | 220 |  |  |  |  | Executing Agency:M/s KEC International Limited | [15 empty] | #VALUE! | Rail Crossing |  |  |  |  | Completed
Tack Welding |  |  | Nos. | 0/220 |  | 220 | [20 empty] | #VALUE! | Road Crossing |  |  |  |  | Right of Way
Stringing Paying Out |  |  | Km. | 0 / 82.801 |  | 82.801 | [21 empty] | Gas Pipe line |  |  |  |  | Earthing Compl
Stringing Final sag |  |  | Km. | 0 / 82.801 |  | 82.801
[33 empty] | Row Length | Cum Length | Fdns Comp | TE Comp | STG Comp | Earthing
Siwani-Gantry |  | 151.994 |  | 410 |  | 429.494 |  | 228.257 |  | 230.92 |  | 373.098 |  | 343 |  | 414 |  | 397 |  | 350.278 |  | 338 |  | 343.261 |  | 152.793 |  | 445 |  | 383 |  |  | 4990.095 | 4990.095 | 0 | 0
|  |  | 1/0 |  | 1/1 |  | 1A/0 | NH | 1B/0 | Rly Xing | 2/0 |  | 2A/0 |  | 2A/1 |  | 2A/2 |  | 2A/3 |  | 2B/0 |  | 2B/1 |  | 2C/0 | 132KV | 2D/0 |  | 2D/1 |  | 2D/2
|  |  | DD60+0 |  | DA+6 |  | DD60+0 |  | DD60+6 |  | DD60+3 |  | DC1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+3 |  | DD60+6 | S/C | DD60+6 |  | DA+0 |  | DA+6
368.645 |  | 349.87 |  | 415 |  | 404.484 |  | 325 |  | 386 |  | 434 |  | 392 |  | 404 |  | 398 |  | 441 |  | 385 |  | 434 |  | 402 |  | 391.079 |  | 392 |  |  | 6322.078 | 11312.173 | 0 | 0
| 2D/3 |  | 2D/4 |  | 2D/5 |  | 3/0 |  | 3/1 |  | 3/2 |  | 3/3 |  | 3/4 |  | 3/5 |  | 3/6 |  | 3/7 |  | 3/8 |  | 3/9 |  | 3/10 |  | 4/0 |  | 4/1
| DA+6 |  | DA+0 |  | DA+6 |  | DB1+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+9 |  | DA+3 |  | DA+0 |  | DA+6 |  | DB2+3 |  | DA+3
400 |  | 401 |  | 386 |  | 322 |  | 301 |  | 374.546 |  | 430 |  | 401 |  | 401 |  | 439 |  | 362 |  | 397 |  | 337 |  | 344.26 |  | 409 |  | 432 |  |  | 6136.806 | 17448.979 | 0 | 0
| 4/2 |  | 4/3 |  | 4/4 |  | 4/5 |  | 4/6 |  | 5/0 |  | 5/1 |  | 5/2 |  | 5/3 |  | 5/4 |  | 5/5 |  | 5/6 |  | 5/7 |  | 6/0 |  | 6/1 |  | 6/2
| DA+6 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC2+0 |  | DA+9 |  | DA+0 |  | DA+3 |  | DA+6 |  | DA+9 |  | DA-3 |  | DA-3 |  | DB1+0 |  | DA+6 |  | DA+0
393 |  | 451 |  | 387 |  | 382 |  | 414 |  | 385 |  | 437 |  | 376 |  | 316.217 |  | 384 |  | 387 |  | 389 |  | 424 |  | 416.069 |  | 364 |  | 337 |  |  | 6242.286 | 23691.265 | 0 | 0
| 6/3 |  | 6/4 |  | 6/5 |  | 6/6 |  | 6/7 |  | 6/8 |  | 6/9 |  | 6/10 |  | 7/0 |  | 7/1 |  | 7/2 |  | 7/3 |  | 7/4 |  | 8/0 |  | 8/1 |  | 8/2
| DA+6 |  | DA+0 |  | DA+9 |  | DA+0 |  | DA+0 |  | DA+9 |  | DA+3 |  | DA+0 |  | DB1+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+6 |  | DB2+0 |  | DA+0 |  | DA+0
434 |  | 401 |  | 372 |  | 368 |  | 420 |  | 411 |  | 423 |  | 416.365 |  | 402 |  | 388 |  | 382.444 |  | 405 |  | 416 |  | 407 |  | 385.937 |  | 398 |  |  | 6429.746 | 30121.011 | 0 | 0
| 8/3 |  | 8/4 |  | 8/5 |  | 8/6 |  | 8/7 |  | 8/8 |  | 8/9 |  | 9/0 |  | 9/1 |  | 9/2 |  | 10/0 |  | 10/1 |  | 10/2 |  | 10/3 |  | 11/0 |  | 11/1
| DA+6 |  | DA+3 |  | DA-3 |  | DA+0 |  | DA+6 |  | DA+0 |  | DA+3 |  | DC2+0 |  | DA+3 |  | DA+0 |  | DD45+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DC2+0 |  | DA+3
412.384 |  | 411 |  | 432 |  | 369 |  | 425 |  | 384.259 |  | 400.558 |  | 413 |  | 388.988 |  | 433 |  | 408 |  | 367 |  | 391.859 |  | 406 |  | 402 |  | 409 |  |  | 6453.048 | 36574.059 | 0 | 0
| 12/0 |  | 12/1 |  | 12/2 |  | 12/3 |  | 12/4 |  | 13/0 |  | 14/0 |  | 14/1 |  | 15/0 |  | 15/1 |  | 15/2 |  | 15/3 |  | 16/0 |  | 16/1 |  | 16/2 |  | 16/3
| DC2+3 |  | DA+9 |  | DA+0 |  | DA+0 |  | DA+6 |  | DC1+3 |  | DC1+0 |  | DA+3 |  | DC2+0 |  | DA+9 |  | DA+0 |  | DA-3 |  | DC2+3 |  | DA+6 |  | DA+0 |  | DA+3
432 |  | 401 |  | 424 |  | 392 |  | 367 |  | 362.955 |  | 346 |  | 384 |  | 406 |  | 419 |  | 381 |  | 408 |  | 398 |  | 405.185 |  | 396 |  | 386 |  |  | 6308.14 | 42882.199 | 1 | 0
DRY
| 16/4 |  | 16/5 |  | 16/6 |  | 16/7 |  | 16/8 |  | 17/0 |  | 17/1 |  | 17/2 |  | 17/3 |  | 17/4 |  | 17/5 |  | 17/6 |  | 17/7 |  | 18/0 |  | 18/1 |  | 18/2
| DA+3 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB1+0 |  | DA+0 |  | DA+0
373 |  | 363 |  | 383.043 |  | 425 |  | 388 |  | 351.545 |  | 373.161 |  | 344.001 |  | 317 |  | 322 |  | 380.273 |  | 250.503 |  | 394 |  | 383 |  | 412 |  | 396 |  |  | 5855.526 | 48737.725 | 3 | 0
|  |  | Sandy |  | WET | [23 empty] | Wet
| 18/3 |  | 18/4 |  | 19/0 |  | 19/1 |  | 19/2 |  | 20/0 |  | 21/0 |  | 21/1 |  | 21/2 |  | 21/3 |  | 22/0 | Rly Xing | 23/0 |  | 23/1 |  | 23/2 |  | 23/3 |  | 23/4
| DA-1.5 |  | DA-1.5 |  | DC2+3 |  | DA+3 |  | DA-3 |  | DC2+0 |  | DB2+0 |  | DA+0 |  | DA-3 |  | DA-3 |  | DD60+9 |  | DD60+6 |  | DA-3 |  | DA+3 |  | DA+0 |  | DA+0
Ready for stringing
[13 empty] | A |  | A |  | A |  | A |  | A |  |  |  | A |  | A
435 |  | 409 |  | 359.991 |  | 394 |  | 393 |  | 406 |  | 403 |  | 403.728 |  | 403.001 |  | 397 |  | 374.01 |  | 388 |  | 436 |  | 381.286 |  | 281.969 |  | 386 |  |  | 6250.985 | 54988.71 | 15 | 7 |  | 9
| WET |  | WET |  | WPS |  | WET |  | WET |  | Sandy |  | Sandy |  | Sandy |  | WET |  | WET |  | Sandy |  |  |  | WET |  | Sandy |  | DRY |  | DRY
| 23/5 |  | 23/6 |  | 24/0 |  | 24/1 |  | 24/2 |  | 24/3 |  | 24/4 |  | 25/0 |  | 25/1 |  | 25/2 |  | 26/0 |  | 26/1 |  | 26/2 |  | 27/0 |  | 28/0 |  | 28/1
| DA+6 |  | DA-1.5 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+1.5 |  | DB2+0 |  | DA+1.5 |  | DA+0 |  | DC1+0 |  | DA+0 |  | DA+6 |  | DC1+0 |  | DC1-3 |  | DA+9
349.422 |  | 245.99 |  | 365 |  | 327 |  | 383.791 |  | 342 |  | 388 |  | 408.02 |  | 431.035 |  | 342.651 |  | 420 |  | 398 |  | 416.489 |  | 385 |  | 416.149 |  | 387 |  |  | 6005.547 | 60994.257 | 5 | 0 |  | 1
|  |  | WPS |  |  |  | WET |  |  |  | WET |  | WET | [7 empty] | WET
| 29/0 | 132KV | 30/0 |  | 30/1 |  | 30/2 |  | 31/0 |  | 31/1 |  | 31/2 |  | 32/0 |  | 32A/0 |  | 32B/0 |  | 32B/1 |  | 32B/2 |  | 33/0 |  | 33/1 |  | 34/0 |  | 34/1
| DB2+18 | S/C | DC1+6 |  | DA+0 |  | DA+0 |  | DD45+0 |  | DA+0 |  | DA+0 |  | DB2+3 |  | DB2+3 |  | DB2+0 |  | DA+3 |  | DA+3 |  | DB1+3 |  | DA+6 |  | DC1+0 |  | DA+6
427.589 |  | 398 |  | 377 |  | 373.455 |  | 369.768 |  | 383 |  | 376.896 |  | 344 |  | 381.526 |  | 394 |  | 399.055 |  | 402.9996 |  | 400.0001 |  | 360.4864 |  | 401.4504 |  | 410.6506 |  |  | 6199.8761 | 67194.1331 | 1 | 0
PS
| 35/0 |  | 35/1 |  | 35/2 |  | 36/0 |  | 37/0 |  | 37/1 |  | 38/0 |  | 38/1 |  | 39/0 |  | 39/1 |  | 40/0 |  | 40/1 |  | 40/2 |  | 40A/0 |  | 40A/1 |  | 41/0
| DD45+0 |  | DA+1.5 |  | DA+6 |  | DC1+0 |  | DC2+0 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DB1+0 |  | DA+1.5 |  | DB2+0 |  | DA+3 |  | DA+0 |  | DB1+0 |  | 5DA+6 |  | 5DC2+6
405 |  | 373.934 |  | 245.502 |  | 403.981 |  | 389 |  | 411.536 |  | 423.721 |  | 401 |  | 400.231 |  | 423 |  | 377 |  | 402 |  | 334.932 |  | 375 |  | 402 |  | 438.46 |  |  | 6206.297 | 73400.4301 | 0 | 0
| 41/1 |  | 42/0 | NH | 43/0 |  | 44/0 |  | 44/1 |  | 45/0 |  | 46/0 |  | 46/1 |  | 47/0 |  | 47/1 |  | 47/2 |  | 47/3 |  | 48/0 |  | 48/1 |  | 48/2 |  | 49/0
| 5DA+9 |  | 5DD45+0 |  | 5DD60+3 |  | 5DB2+3 |  | 5DA+3 |  | 5DC2+9 |  | 5DD45+9 |  | 5DA+9 |  | 5DD45+3 |  | 5DA+6 |  | 5DA+6 |  | 5DA+6 |  | 5DB2+0 |  | 5DA+9 |  | 5DA+9 |  | 5DC2+9
376 |  | 403 |  | 347.805 |  | 426.041 |  | 343.959 |  | 409.991 |  | 190.397 |  | 240 |  | 378.145 |  | 285.332 |  | 400 |  | 400 |  | 307.494 |  | 345.001 |  | 260 |  | 327.263 |  |  | 5440.428 | 78840.8581 | 1 | 0
DRY
| 49/1 |  | 49/2 |  | 50/0 |  | 50A/0 |  | 50A/1 |  | 51/0 | 220kv | 52/0 |  | 52/1 |  | 53/0 | 132kv | 54/0 |  | 54/1 |  | 54/2 |  | 55/0 |  | 55/1 |  | 55/2 |  | 56/0
| 5DA+3 |  | 5DA+9 |  | 5DD45+3 |  | 5DB1+9 |  | 5DA+0 |  | 5DD45+18 | D/C | 5DD45+18 |  | 5DB1+0 |  | 5DD45+18 | D/C | 5DD60+9 |  | 5DA+6 |  | 5DA+3 |  | 5DB2+6 |  | 5DA-3 |  | 5DA-3 |  | 5DD45-3
266 |  | 232.295 |  | 351.696 |  | 399.415 |  | 370 |  | 431.59 |  | 250 |  | 301.869 |  | 397.473 |  | 225.946 |  | 243.859 |  | 247.73 |  | 141.997 |  | 100.475 | [6 empty] | 3960.345 | 82801.2031 | 0 | 0
| 56/1 |  | 57/0 |  | 58/0 |  | 59/0 |  | 59/1 |  | 60/0 |  | 60/1 |  | 61/0 |  | 61/1 |  | 61A/0 |  | 62/0 |  | 63/0 |  | 64/0 |  | Fatehabad Gantry
| 5DA+0 |  | 5DB2-1.5 |  | 5DC2+3 |  | 5DB2+3 |  | 5DA+9 |  | 5DD45+3 |  | 5DA+3 |  | 5DC1+6 |  | 5DA+6 |  | 5DB1-3 |  | 5DD45+3 | NH | 5DC2+0 |  | 5DD60+0
[32 empty] | Total | 82801.2031 | 82801.2031 | 26 | 7 | 0 | 10

## VC SP
Visual Chart | [34 empty] | 2026-06-26
Progress | [5 empty] | WXMIDNC | [20 empty] | LEGEND
Foundation |  |  | Nos. | 74 / 399 |  | 399 |  |  |  |  | TL03: Siwani– Patran (Indi Grid) 400 kV TL | [15 empty] | Crossings |  |  |  |  | Status
Earthing |  |  | Nos. | 8 / 399 |  | 399 |  |  |  |  | Client: Powergrid Bikaner IV Transmission limited | [15 empty] | #VALUE! | Powerline Crossing |  |  |  |  | In Progress
Erection |  |  | Nos. | 28 / 399 |  | 399 |  |  |  |  | Executing Agency:M/s KEC International Limited | [15 empty] | #VALUE! | Rail Crossing |  |  |  |  | Completed
Tack Welding |  |  | Nos. | 0/220 |  | 399 | [20 empty] | #VALUE! | Road Crossing |  |  |  |  | Right of Way
Stringing Paying Out |  |  | Km. | 0 / 147.56 |  | 147.56 | [21 empty] | Oil/Gas Pipe line |  |  |  |  | Earthing
Stringing Final sag |  |  | Km. | / 147.56 |  | 147.56
[33 empty] | Row Length | Cum Length | Fdns Comp | TE Comp | STG Comp | Earthing
Siwani-Gantry |  | 100.36 |  | 268.44 |  | 161.36 |  | 400 |  | 419.03 |  | 418 |  | 386.78 |  | 319.22 |  | 390.8 |  | 438 |  | 406 |  | 436.42 |  | 193.59 |  | 205.24 |  | 356 |  |  | 4899.24 | 4899.24 | 0 | 0
|  |  | 1/0 |  | 1A/0 |  | 1B/0 |  | 1B/1 |  | 1C/0 |  | 1C/1 |  | 1C/2 |  | 1C/3 |  | 1D/0 |  | 1D/1 |  | 1D/2 |  | 2/0 | NH Xing | 2A/0 | Rly Xing | 2B/0 |  | 2B/1
|  |  | DD60+0 |  | DD60+25 |  | DD60+25 |  | DA+9 |  | DC1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC2+6 |  | DA+3 |  | DA+9 |  | DD60+3 |  | DD60+6 |  | DD60+9 |  | DA+0
300 |  | 318 |  | 375 |  | 371.02 |  | 204.05 |  | 377.97 |  | 420.897 |  | 393 |  | 393 |  | 383 |  | 391 |  | 429 |  | 389 |  | 413 |  | 365 |  | 438 |  |  | 5960.937 | 10860.177 | 3 | 0
[21 empty] | sandy |  | sandy | [7 empty] | sandy
| 2B/2 |  | 2B/3 |  | 2B/3 |  | 2C/0 | 132KV | 2D/0 |  | 3/0 |  | 3/1 |  | 3/2 |  | 3/3 |  | 3/4 |  | 3/5 |  | 3/6 |  | 3/7 |  | 3/8 |  | 3/9 |  | 3/10
| DA+0 |  | DA+0 |  | DA+0 |  | DD45+9 | S/C | DD60+9 |  | DA+0 |  | DA+1.5 |  | DA+3 |  | DA-3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA-3 |  | DA+0 |  | DA+3
132 KV RVNL
393.115 |  | 356 |  | 359 |  | 410 |  | 361 |  | 418.331 |  | 424 |  | 318.001 |  | 319.999 |  | 344 |  | 411 |  | 393.887 |  | 405.25 |  | 350 |  | 370.747 |  | 376 |  |  | 6010.33 | 16870.507 | 0 | 0
| 4/0 |  | 4/1 |  | 4/2 |  | 4/3 |  | 4/4 |  | 5/0 |  | 5/1 |  | 5/2 |  | 5/3 |  | 5/4 |  | 5/5 |  | 5/6 |  | 7/0 |  | 7/1 |  | 8/0 |  | 8/1
| DB2+0 |  | DA-3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+6 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DB2+0 |  | DA+3 |  | DB1+0 |  | DA+6
391 |  | 401 |  | 402 |  | 442 |  | 387.599 |  | 414 |  | 418 |  | 371.223 |  | 407 |  | 377 |  | 405.674 |  | 368 |  | 427 |  | 401 |  | 413 |  | 403.193 |  |  | 6428.689 | 23299.196 | 0 | 0
| 8/2 |  | 8/3 |  | 8/4 |  | 8/5 |  | 9/0 |  | 9/1 |  | 9/2 |  | 10/0 |  | 10/1 |  | 10/2 |  | 11/0 |  | 11/1 |  | 11/2 |  | 11/3 |  | 11/4 |  | 12/0
| DA+3 |  | DA+3 |  | DA+9 |  | DA+6 |  | DC2+3 |  | DA+0 |  | DA+3 |  | DC1+3 |  | DA+6 |  | DA+0 |  | DB1+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB2+0
433.474 |  | 338.526 |  | 418 |  | 412 |  | 425 |  | 361 |  | 402.251 |  | 403.51 |  | 418 |  | 403 |  | 415 |  | 385 |  | 378 |  | 370.903 |  | 370 |  | 435.958 |  |  | 6369.622 | 29668.818 | 3 | 0
[19 empty] | Sandy |  | DRY |  | Sandy
| 12/1 |  | 12/2 |  | 12/3 |  | 12/4 |  | 12/5 |  | 12/6 |  | 13/0 |  | 14/0 |  | 14/1 |  | 14/2 |  | 14/3 |  | 14/4 |  | 14/5 |  | 15/0 |  | 15/1 |  | 15A/0
| DA+6 |  | DA+6 |  | DA+0 |  | DA+6 |  | DA+6 |  | DA+0 |  | DB2+9 |  | DC1+3 |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DC2+6
407.011 |  | 415 |  | 395.995 |  | 404.005 |  | 395 |  | 423.118 |  | 376 |  | 427.627 |  | 417 |  | 382 |  | 366 |  | 446.464 |  | 408 |  | 407 |  | 350 |  | 376.934 |  |  | 6397.154 | 36065.972 | 1 | 0
DRY
| 15B/0 |  | 15B/1 |  | 15B/2 |  | 15B/3 |  | 15B/4 |  | 16/0 |  | 16/1 |  | 17/0 |  | 17/1 |  | 17/2 |  | 17/3 |  | 19/0 |  | 19/1 |  | 19/2 |  | 19/3 |  | 20/0
| DC1+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DC2+0 |  | DA+0 |  | DC2+6 |  | DA+0 |  | DA+0 |  | DA+6 |  | DC2+9 |  | DA+0 |  | DA+3 |  | DA+3 |  | DC2-3
355 |  | 383 |  | 330.223 |  | 377 |  | 382 |  | 380 |  | 376 |  | 390 |  | 397 |  | 380 |  | 398 |  | 362.442 |  | 348 |  | 372 |  | 422 |  | 420 |  |  | 6072.665 | 42138.637 | 6 | 0
[17 empty] | PS |  | Wet | [5 empty] | Wet |  | Wet |  | Wet |  | Wet
| 20/1 |  | 20/2 |  | 21/0 |  | 21/1 |  | 21/2 |  | 21/3 |  | 21/4 |  | 21/5 |  | 21/6 |  | 21/7 |  | 21/8 |  | 23/0 |  | 23/1 |  | 23/2 |  | 23/3 |  | 23/4
| DA+0 |  | DA+3 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DB1-3 |  | DA-1.5 |  | DA+0 |  | DA+6 |  | DA+0
| 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120 |  | 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126 |  | 127
[27 empty] | A |  | A |  | A
358.141 |  | 466 |  | 320 |  | 378.053 |  | 411 |  | 378 |  | 401 |  | 400.805 |  | 350 |  | 384 |  | 430.959 |  | 201.147 |  | 420 |  | 398.239 |  | 385.761 |  | 374 |  |  | 6057.105 | 48195.742 | 4 | 3 |  | 3
[17 empty] | WPS | [9 empty] | sandy |  | sandy |  | Wet
| 24/0 |  | 24/1 |  | 24/2 |  | 25/0 |  | 25/1 |  | 25/2 |  | 25/3 |  | 26/0 |  | 26/1 |  | 26/2 |  | 27/0 | Rly Xing | 28/0 |  | 28/1 |  | 28/2 |  | 28/3 |  | 28/4
| DB2+3 |  | DA+9 |  | DA+3 |  | DB2+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DD60+6 |  | DD60+6 |  | DA+0 |  | DA+3 |  | DA+6 |  | DA+3
| 128 |  | 129 |  | 130 |  | 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140 |  | 141 |  | 142 |  | 143
| A |  | A |  | A |  | A |  | A |  | A |  | A
390.364 |  | 377 |  | 419 |  | 420 |  | 414 |  | 419 |  | 371.669 |  | 412 |  | 377 |  | 354 |  | 386 |  | 410 |  | 406 |  | 425 |  | 400.252 |  | 338 |  |  | 6319.285 | 54515.027 | 10 | 7 |  | 5
| DRY |  | Sandy |  | Wet |  | Wet |  | Sandy |  | Wet |  | DRY |  | Wet |  | Wet |  | Wet
| 29/0 |  | 29/1 |  | 29/2 |  | 29/3 |  | 29/4 |  | 29/5 |  | 30/0 |  | 30/1 |  | 30/2 |  | 30/3 |  | 30/4 |  | 30/5 |  | 30/6 |  | 30/7 |  | 31/0 |  | 31/1
| DC1+0 |  | DA+0 |  | DA+9 |  | DA+3 |  | DA+6 |  | DA+0 |  | DB2+0 |  | DA+3 |  | DA+3 |  | DA-3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DB1+3 |  | DA+0
| 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150 |  | 151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159
402 |  | 379.885 |  | 360 |  | 431 |  | 384 |  | 411 |  | 401.511 |  | 246.67 |  | 474 |  | 181.733 |  | 427 |  | 411 |  | 394 |  | 343 |  | 347 |  | 417.552 |  |  | 6011.351 | 60526.378 | 2 | 0
[25 empty] | DRY |  | DRY
| 31/2 |  | 32/0 |  | 32/1 |  | 32/2 |  | 32/3 |  | 32/4 |  | 33/0 | NH | 34/0 |  | 35/0 | 132KV | 36/0 |  | 36/1 |  | 36/2 |  | 36/3 |  | 36/4 |  | 36/5 |  | 37/0
| DA+3 |  | DB2+3 |  | DA+0 |  | DA+6 |  | DA+0 |  | DA+3 |  | DD60+0 |  | DD60+3 |  | DB1+9 | D/C | 5DB1+9 |  | 5DA+3 |  | 5DA+6 |  | 5DA+0 |  | 5DA-3 |  | 5DA+6 |  | 5DD45+3
| 160 |  | 161 |  | 162 |  | 163 |  | 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170 |  | 171 |  | 172 |  | 173 |  | 174 |  | 175
379 |  | 386.391 |  | 250.289 |  | 356 |  | 403 |  | 434.661 |  | 261.78 |  | 386.604 |  | 409 |  | 367.192 |  | 309.944 |  | 356 |  | 362 |  | 348.24 |  | 397 |  | 381 |  |  | 5788.101 | 66314.479 | 0 | 0
| 37/1 |  | 38/0 | 132KV | 39/0 |  | 39/1 |  | 39/2 |  | 40/0 | 220 KV | 41/0 |  | 42/0 |  | 42/1 |  | 43/0 |  | 44/0 |  | 44/1 |  | 44/2 |  | 45/0 |  | 45/1 |  | 45/2
| 5DA+0 |  | 5DD45+18 | S/C | 5DC2+9 |  | 5DA+3 |  | 5DA+3 |  | 5DC1+18 | D/C | 5DB2+25 |  | 5DC2+6 |  | 5DA+6 |  | 5DC1+0 |  | 5DD45+0 |  | 5DA+0 |  | 5DA+6 |  | 5DD60+0 |  | 5DA+6 |  | 5DA+9
| 176 |  | 177 |  | 178 |  | 179 |  | 180 |  | 181 |  | 182 |  | 183 |  | 184 |  | 185 |  | 186 |  | 187 |  | 188 |  | 189 |  | 190 |  | 191
408.451 |  | 429 |  | 360.902 |  | 433 |  | 407 |  | 370 |  | 375 |  | 420 |  | 400 |  | 418.466 |  | 297 |  | 453.982 |  | 215.992 |  | 442 |  | 390.998 |  | 387.002 |  |  | 6208.793 | 72523.272 | 0 | 0
| 46/0 |  | 46/1 |  | 47/0 |  | 47/1 |  |  |  | 47/3 |  | 47/4 |  | 47/5 |  | 47/6 |  | 48/0 |  | 48/1 |  | 49/0 | 400 KV | 50/0 |  | 50/1 |  | 50/2 |  | 50/3
| 5DD45+6 |  | 5DA+6 |  | 5DC1+3 |  | 5DA+9 |  | 5DA+0 |  | 5DA+0 |  | 5DA+3 |  | 5DA+6 |  | 5DA+6 |  | 5DB1+3 |  | 5DA+0 |  | 5DD60+30 | D/C | 5DD60+30 |  | 5DA+0 |  | 5DA+6 |  | 5DA+6
| 192 |  | 193 |  | 194 |  | 195 |  | 196 |  | 197 |  | 198 |  | 199 |  | 200 |  | 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207
[5 empty] | A |  |  |  | A |  | a | [5 empty] | a |  | A |  | A
385.376 |  | 409 |  | 385 |  | 366 |  | 398 |  | 436 |  | 380.514 |  | 383 |  | 362.419 |  | 378.581 |  | 361 |  | 372 |  | 443.274 |  | 186.799 |  | 423 |  | 358 |  |  | 6027.963 | 78551.235 | 14 | 6
| WPS |  | WPS |  | DRY |  | WPS |  | DRY |  | DRY |  | WPS |  | WPS |  | WPS |  | WPS |  | DRY |  | WET | [5 empty] | Wet |  | Wet
| 51/0 |  | 51/1 |  | 51/2 |  | 51/3 |  | 51/4 |  | 51/5 |  | 52/0 |  | 52/1 |  | 52/2 |  | 52/3 |  | 52/4 |  | 52/5 |  | 53/0 | 220 Kv | 54/0 |  | 54/1 |  | 54/2
| 5DB2+6 |  | 5DA+3 |  | 5DA+3 |  | 5DA+0 |  | 5DA+6 |  | 5DA+6 |  | 5DB1+3 |  | 5DA+0 |  | 5DA+0 |  | 5DA+0 |  | 5DA+0 |  | 5DA+0 |  | 5DC2+18 | D/C | 5DD45+25 |  | 5DA+0 |  | 5DA+0
| 208 |  | 209 |  | 210 |  | 211 |  | 212 |  | 213 |  | 214 |  | 215 |  | 216 |  | 217 |  | 218 |  | 219 |  | 220 |  | 221 |  | 222 |  | 223
| A |  |  |  | A |  | A |  | A |  | A |  |  |  | A | [7 empty] | A |  | A | [5 empty] | A
389 |  | 427 |  | 395 |  | 373 |  | 392 |  | 398 |  | 391.642 |  | 410 |  | 430 |  | 392 |  | 371.098 |  | 404.9 |  | 402 |  | 410 |  | 408.712 |  | 420 |  |  | 6414.352 | 84965.587 | 15 | 9
| Wet |  |  |  | WET |  | WET |  | Wet |  | PS |  | DRY |  | PS |  | WET |  | WET |  | WET |  | DRY |  | DRY |  | WET |  | DRY |  | DRY
| 54/3 |  | 54/4 |  | 54/5 |  | 54/6 |  | 54/7 |  | 54/8 |  | 55/0 |  | 55/1 |  | 55/2 |  | 55/3 |  | 55/4 |  | 55/5 |  | 55/6 |  | 55/7 |  | 56/0 |  | 56/1
| 5DA+3 |  | 5DA+6 |  | 5DA+0 |  | 5DA+0 |  | 5DA+6 |  | 5DA+3 |  | 5DB2+3 |  | 5DA+9 |  | 5DA+3 |  | 5DA+0 |  | 5DA+3 |  | 5DA+6 |  | 5DA+3 |  | 5DA+9 |  | 5DB1+6 |  | 5DA+3
| 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229 |  | 230 |  | 231 |  | 232 |  | 233 |  | 234 |  | 235 |  | 236 |  | 237 |  | 238 |  | 239
| A |  | a |  | a
414 |  | 399 |  | 402 |  | 363.51 |  | 200.601 |  | 430 |  | 363 |  | 308 |  | 347 |  | 353.269 |  | 269.791 |  | 263.175 |  | 392 |  | 438 |  | 369.977 |  | 310 |  |  | 5623.323 | 90588.91 | 7 | 3
| DRY |  | DRY |  | DRY | [17 empty] | WPS |  | WPS |  | WPS |  |  |  | WPS
| 56/2 |  | 56/3 |  | 56/4 |  | 57/0 | 400KV | 58/0 |  | 58/1 |  | 58/2 |  | 58/3 |  | 58/4 |  | 59/0 | 220KV | 60/0 | 132KV | 61/0 |  | 61/1 |  | 61/2 |  | 62/0 |  | 62/1
| 5DA+6 |  | 5DA+3 |  | 5DA+9 |  | 5DD60+18 | D/C | 5DD60+18 |  | 5DA+6 |  | 5DA+0 |  | 5DA-3 |  | 5DA+0 |  | 5DB1+9 | S/C | 5DB2+18 | S/C | 5DB1+3 |  | 5DA+6 |  | 5DA+9 |  | 5DB2+0 |  | 5DA+3
| 240 |  | 241 |  | 242 |  | 243 |  | 244 |  | 245 |  | 246 |  | 247 |  | 248 |  | 249 |  | 250 |  | 251 |  | 252 |  | 253 |  | 254 |  | 255
388.611 |  | 203.306 |  | 397 |  | 409 |  | 361 |  | 373 |  | 400 |  | 403 |  | 376.543 |  | 383 |  | 374 |  | 403.154 |  | 400 |  | 366.748 |  | 407 |  | 364.182 |  |  | 6009.544 | 96598.454 | 6 | 0
[5 empty] | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS
| 63/0 | 400KV | 64/0 |  | 64/1 |  | 64/2 |  | 64/3 |  | 64/4 |  | 64/5 |  | 64/6 |  | 65/0 |  | 65/1 |  | 65/2 |  | 66/0 |  | 66/1 |  | 67/0 |  | 67/1 |  | 68/0
| 5DD60+18 | D/C | 5DD60+18 |  | 5DA+6 |  | 5DA+0 |  | 5DA+0 |  | 5DA+3 |  | 5DA+3 |  | 5DA+3 |  | 5DC1+0 |  | 5DA+3 |  | 5DA+6 |  | 5DD45+0 |  | 5DA+6 |  | 5DB2+3 |  | 5DA+9 |  | 5DB2+0
| 256 |  | 257 |  | 258 |  | 259 |  | 260 |  | 261 |  | 262 |  | 263 |  | 264 |  | 265 |  | 266 |  | 267 |  | 268 |  | 269 |  | 270 |  | 271
347 |  | 380.094 |  | 388 |  | 371 |  | 364 |  | 336 |  | 418 |  | 420.93 |  | 217.862 |  | 373.793 |  | 336 |  | 355.56 |  | 169 |  | 81 |  | 80.799 |  | 382 |  |  | 5021.038 | 101619.492 | 0 | 0
| 68/1 |  | 69/0 |  | 69/1 |  | 69/2 |  | 69/3 |  | 69/4 |  | 69/5 |  | 70/0 | Rly Xing | 71/0 |  | 72/0 |  | 72/1 |  | 73/0 |  | 73/1 | 765 KV | 73/2 |  | 74/0 |  | 74/1
| 5DA+6 |  | 5DB1+3 |  | 5DA+0 |  | 5DA+0 |  | 5DA+0 |  | 5DA+9 |  | 5DA+6 |  | 5DD60+6 |  | 5DD60+6 |  | 5DC1+3 |  | 5DA+0 |  | 5DD60+0 |  | DDH | S/C | DDH |  | 5DD60+0 |  | 5DA+9
| 272 |  | 273 |  | 274 |  | 275 |  | 276 |  | 277 |  | 278 |  | 279 |  | 280 |  | 281 |  | 282 |  | 283 |  | 284 |  | 285 |  | 286 |  | 287
420 |  | 404 |  | 433 |  | 389 |  | 430 |  | 357 |  | 369 |  | 294 |  | 377.328 |  | 219.542 |  | 390 |  | 408.749 |  | 413 |  | 396 |  | 355 |  | 416.158 |  |  | 6071.777 | 107691.269 | 3 | 0
[11 empty] | WPS |  | WPS |  | WPS
| 74/2 |  | 74/3 |  | 74/4 |  | 74/5 |  | 74/6 |  | 74/7 |  | 74/8 |  | 74/9 |  | 75/0 | 132 KV | 76/0 |  | 76/1 |  | 77/0 |  | 77/1 |  | 77/2 |  | 77/3 |  | 78/0
| 5DA+0 |  | 5DA+6 |  | 5DA+6 |  | 5DA+6 |  | 5DA+6 |  | 5DA+3 |  | 5DA+0 |  | 5DA+0 |  | 5DB1+18 | D/C | 5DB2+18 |  | 5DA+0 |  | 5DC1+9 |  | 5DA+9 |  | 5DA+3 |  | 5DA+3 |  | 5DB2+6
| 288 |  | 289 |  | 290 |  | 291 |  | 292 |  | 293 |  | 294 |  | 295 |  | 296 |  | 297 |  | 298 |  | 299 |  | 300 |  | 301 |  | 302 |  | 303
386 |  | 417.906 |  | 407 |  | 405 |  | 404.002 |  | 409.998 |  | 340.345 |  | 246.238 |  | 383.094 |  | 220.922 |  | 382.481 |  | 251.097 |  | 405.559 |  | 394 |  | 341 |  | 345 |  |  | 5739.642 | 113430.911 | 0 | 0
| 78/1 |  | 79/0 |  | 79/1 |  | 79/2 |  | 79/3 |  | 79/4 |  | 80/0 | NH Xing | 81/0 |  | 82/0 | 132KV | 83/0 |  | 84/0 | 220KV | 85/0 |  | 86/0 |  | 86/1 |  | 86/2 |  | 86/3
| 5DA+9 |  | 5DB2+9 |  | 5DA+3 |  | 5DA+3 |  | 5DA+3 |  | 5DA+6 |  | 5DC2+0 |  | 5DC1+3 |  | 5DB2+9(1 M RC) |  | 5DB1+18 |  | 5DC1+18 |  | 5DD60+18 |  | 5DC1+3 |  | 5DA+3 |  | 5DA+3 |  | 5DA+3
| 304 |  | 305 |  | 306 |  | 307 |  | 308 |  | 309 |  | 310 |  | 311 |  | 312 |  | 313 |  | 314 |  | 315 |  | 316 |  | 317 |  | 318 |  | 319
419.431 |  | 247.386 |  | 240.467 |  | 400.069 |  | 342.102 |  | 228.107 |  | 379 |  | 407 |  | 433 |  | 375 |  | 409 |  | 383 |  | 383 |  | 400.558 |  | 417.979 |  | 366 |  |  | 5831.099 | 119262.01 | 0 | 0
| 87/0 | Rly Xing | 88/0 | 132KV | 89/0 |  | 90/0 |  | 91/0 | 132KV | 92/0 |  | 92/1 |  | 92/2 |  | 92/3 |  | 92/4 |  | 92/5 |  | 92/6 |  | 92/7 |  | 92A/0 |  | 93/0 |  | 93/1
| 5DD60+9 |  | 5DD60+9 |  | 5DB2+9 |  | 5DB2+0 |  | 5DB2+18 |  | 5DD45+9 |  | 5DA+6 |  | 5DA+9 |  | 5DA+3 |  | 5DA+3 |  | 5DA+3 |  | 5DA+0 |  | 5DA+9 |  | 5DB2+9 |  | 5DC2+6 |  | 5DA+0
| 320 |  | 321 |  | 322 |  | 323 |  | 324 |  | 325 |  | 326 |  | 327 |  | 328 |  | 329 |  | 330 |  | 331 |  | 332 |  | 333 |  | 334 |  | 335
394 |  | 391 |  | 385.773 |  | 380 |  | 403 |  | 375 |  | 413 |  | 418 |  | 410 |  | 411 |  | 413 |  | 379 |  | 401.332 |  | 395 |  | 318.988 |  | 226.508 |  |  | 6114.601 | 125376.611 | 0 | 0
| 93/2 |  | 93/3 |  | 94/0 |  | 94/1 |  | 94/2 |  | 94/3 |  | 94/4 |  | 94/5 |  | 94/6 |  | 94/7 |  | 94/8 |  | 94/9 |  | 95/0 |  | 95/1 |  | 96/0 | 66KV | 97/0
| 5DA+6 |  | 5DA+0 |  | 5DB1+6 |  | 5DA+6 |  | 5DA+0 |  | 5DA+6 |  | 5DA+6 |  | 5DA+3 |  | 5DA+6 |  | 5DA+9 |  | 5DA+0 |  | 5DA+9 |  | 5DB1+6 |  | 5DA+6 |  | 5DC2+6 |  | 5DB2+6
| 336 |  | 337 |  | 338 |  | 339 |  | 340 |  | 341 |  | 342 |  | 343 |  | 344 |  | 345 |  | 346 |  | 347 |  | 348 |  | 349 |  | 350 |  | 351
376 |  | 382.573 |  | 402 |  | 338 |  | 337 |  | 383 |  | 384 |  | 388 |  | 389.649 |  | 409 |  | 382.024 |  | 379 |  | 272 |  | 327 |  | 295 |  | 390 |  |  | 5834.246 | 131210.857 | 0 | 0
| 97/1 |  | 98/0 |  | 98/1 |  | 98/2 |  | 98/3 |  | 98/4 |  | 98/5 |  | 98/6 |  | 99/0 |  | 99/1 |  | 100/0 |  | 100/1 |  | 100/2 |  | 100/3 |  | 100/4 |  | 100/5
| 5DA+3 |  | 5DB2+9 |  | 5DA+6 |  | 5DA-3 |  | 5DA+0 |  | 5DA+3 |  | 5DA+6 |  | 5DA+6 |  | 5DC1+6 |  | 5DA+3 |  | 5DB1+0 |  | 5DA+3 |  | 5DA+0 |  | 5DA-3 |  | 5DA+3 |  | 5DA+9
| 352 |  | 353 |  | 354 |  | 355 |  | 356 |  | 357 |  | 358 |  | 359 |  | 360 |  | 361 |  | 362 |  | 363 |  | 364 |  | 365 |  | 366 |  | 367
412 |  | 356 |  | 336.413 |  | 223.24 |  | 378 |  | 416.359 |  | 403 |  | 413.905 |  | 340.961 |  | 346 |  | 383 |  | 434 |  | 400 |  | 407 |  | 425.597 |  | 381 |  |  | 6056.475 | 137267.332 | 0 | 0
| 100/6 |  | 100/7 |  | 101/0 | 66KV | 102/0 |  | 102/1 |  | 103/0 |  | 103/1 |  | 104/0 |  | 105/0 |  | 105/1 |  | 105/2 |  | 105/3 |  | 105/4 |  | 105/5 |  | 106/0 |  | 106/1
| 5DA+6 |  | 5DA+0 |  | 5DB1+6 |  | 5DB1+6 |  | 5DA+3 |  | 5DB1+6 |  | 5DA+9 |  | 5DB2+6 |  | 5DB2+0 |  | 5DA+0 |  | 5DA+6 |  | 5DA+6 |  | 5DA+6 |  | 5DA+9 |  | 5DB2+9 |  | 5DA+3
| 368 |  | 369 |  | 370 |  | 371 |  | 372 |  | 373 |  | 374 |  | 375 |  | 376 |  | 377 |  | 378 |  | 379 |  | 380 |  | 381 |  | 382 |  | 383
357 |  | 367 |  | 276 |  | 332 |  | 320 |  | 367 |  | 416.111 |  | 350.472 |  | 199.194 |  | 433 |  | 341 |  | 331.662 |  | 245.356 |  | 243 |  | 240.23 |  | 212.64 |  |  | 5031.665 | 142298.997 | 0 | 0
| 106/2 |  | 106/3 |  | 106/4 |  | 106/5 |  | 106/6 |  | 106/7 |  | 107/0 |  | 108/0 | 400KV | 109/0 |  | 109/1 |  | 109/2 |  | 110/0 | 2 66 KV | 111/0 |  | 111/1 |  | 112/0 | NH Xing | 113/0
| 5DA+0 |  | 5DA+0 |  | 5DA+0 |  | 5DA-3 |  | 5DA+0 |  | 5DA+6 |  | 5DC2+6 |  | 5DD60+25 |  | 5DD60+18 |  | 5DA+6 |  | 5DA+0 |  | 5DB2+9 |  | 5DD45+3 |  | 5DA+3 |  | 5DD45+0 |  | 5DB2+0
| 384 |  | 385 |  | 386 |  | 387 |  | 388 |  | 389 |  | 390 |  | 391 |  | 392 |  | 393 |  | 394 |  | 395 |  | 396 |  | 397 |  | 398 |  | 399
329 |  | 432.99 |  | 431.324 |  | 343.224 |  | 322 |  | 360 |  | 375.37 |  | 249.27 |  | 410 |  | 401.896 |  | 353 |  | 337 |  | 255 |  | 340.043 |  | 185.849 |  | 113.34 |  |  | 5239.306 | 147538.303 | 0 | 0
| 113/1 |  | 114/0 |  | 114/1 |  | 115/0 |  | 115/1 |  | 115/2 |  | 116/0 | NH Xing | 117/0 |  | 117/1 |  | 118/0 |  | 118/1 |  | 118/2 |  | 118/3 |  | 119/0 |  | 120/0 | 400KV | 121/0
| 5DA+6 |  | 5DC2+9 |  | 5DA+6 |  | 5DB2+0 |  | 5DA+6 |  | 5DA+0 |  | 5DC1+3 |  | 5DD45+0 |  | 5DA+9 |  | 5DB1+6 |  | 5DA+0 |  | 5DA+0 |  | 5DA+0 |  | 5DD60+9 |  | 5DD60+25 |  | 5DD60+18(1.5M RC)
[32 empty] | Total: | 147.5383 | 147.5383 | 74 | 28 | 0 | 8
62.66
Patran Gantry

## LS (hidden)
Client-Powergrid Bikaner IV Tranmission Limited
Project-Siwani-Patran TL & Siwani-Fatehabad TL
Land Schedule Data
Land Schedule Verified
| State | District | Tehsil | Line Length (Km) | Total Locations | Corridor Data Submitted (Km) | Verified from Patwari | Sketch Prepared | Balance Sketch
Siwani-Patran | Haryana | Bhiwani | Siwani | 22.072 | 60 | 22.072 | 59 | 39 | 21
|  | Hisar | Balsamand | 4.048 | 10 | 4.048 | 10 | 10 | 0
|  |  | Hisar | 41.98 | 110 | 41.98 | 110 | 106 | 4
|  |  | Uklana | 10.358 | 27 | 10.358 | 27 | 27 | 0
|  |  | Adampur | 4.39 | 11 | 4.39 | 11 | 11 | 0
|  | Fatehabad | Bhuna | 5.664 | 15 | 5.66 | 15 | 15 | 0
|  |  | Tohana | 25.551 | 72 | 25.55 | 71 | 70 | 2
|  | Jind | Narwana | 2.804 | 8 | 2.804 | 6 | 8 | 0
| Punjab | Sangrur | Moonak | 5.101 | 13 | 5.101 | 13 | 13 | 0
|  |  | Khanauri | 12.832 | 35 | 12.832 | 35 | 35 | 0
|  | Patiala | Patran | 12.761 | 38 | 12.76 | 38 | 37 | 1
|  | Total |  | 147.561 | 399 | 147.555 | 395 | 371 | 28
Siwani To Fatehabad | Haryana | Bhiwani | Siwani | 21.374 | 57 | 21.37 | 57 | 38 | 19
|  | Hisar | Balsamand | 15.976 | 40 | 15.98 | 40 | 40 | 0
|  |  | Hisar | 9.17 | 24 | 9.17 | 24 | 24 | 0
|  |  | Adampur | 18.287 | 48 | 18.28 | 48 | 48 | 0
|  | Fatehabad | Fatehabad | 17.981 | 51 | 17.98 | 51 | 49 | 2
|  | Total |  | 82.8 | 220 | 82.8 | 220 | 199 | 21
G Total |  |  |  | 230.361 | 619 | 230.355 | 615 | 570 | 49

## Survey
KEC International Limited | [7 empty] | KEC International Limited
400 KV D/C Siwani To Fatehabad | [7 empty] | 400 KV D/C Siwani To Patran
Detailed Survey | [7 empty] | Detailed Survey
Sl.No. | SPAN |  | Section Length (Km) | Submitted For Approval | Approved Date | Approved Status | Remarks | Sl.No. | SPAN |  | Section Length (Km) | Submitted For Approval | PGCIL Letter Date | PGCIL Aprroval Mail Date | Approved Status
| From Section | To Section | [6 empty] | From Section | To Section
1 | 3/0 | 14/0 | 26.427 | 24.05.2025 | 26.05.2025 | Approved |  | 1 | 3/0 | 5/0 | 6.312 | 15.05.2025 | 17.05.2025 |  | Approved
2 | 14/0 | 24/0 | 16.986 | 03.04.2025 | 01.05.2025 | Approved |  | 2 | 14/0 | 29/0 | 22.093 | 10.04.2025 | 17.05.2025 |  | Approved
3 | 24/0 | 30/0 | 5.64 | 07.03.2025 | 05.4.2025 | Approved |  | 3 | 29/0 | 33/0 | 8.699 | 10.04.2025 | 17.05.2025 |  | Approved
4 | 30/0 | 32/0 | 2.21 | 28.03.2025 | 05.04.2025 | Approved |  | 4 | 35/0 | 58/0 | 28.735 | 15.05.2025 | 15.05.2025 |  | Approved
5 | 32/0 | 33/0 | 2.01 | 28.03.2025 | 05.04.2025 | Approved |  | 5 | 58/0 | 101/0 | 45.55 | 18.05.2025 | 19.05.2025 | 29.05.2025 | Approved
6 | 33/0 | 40/0 | 5.412 | 28.03.2025 | 05.04.2025 | Approved |  | 6 | 101/0 | Gantry | 15.283 | 20.05.2025 | 11.06.2025 |  | Approved
7 | 40/0 | Gantry | 17.582 | 12.04.2025 02.06.2025 | 09.06.2025 | Approved |  | 7 | 33/0 | 35/0 | 0.721 | 10.04.2025 |  |  | Approved
8 | Gantry | AP-3 | 6.528 | 29.10.2025 | 11.12.2025 | Approved |  | 8 | AP5 | AP14 | 13.34 | 17.07.2025 | 2025-07-22 |  | Approved
[8 empty] | 9 | Gantry | AP-3 | 6.853 | 18.11.2025, 09.01.2025 |  |  | Approved
Approved Total Qty |  |  | 82.795 |  |  |  |  | Approved Total Qty |  |  | 147.586
400 KV D/C Siwani To Fatehabad | [7 empty] | 400 KV D/C Siwani To Patran
Check Survey | [7 empty] | Check survey
Sl.No. | SPAN |  | Section Length (Km) | Submitted For Approval | Approval Date | Status | Remarks | Sl.No. | SPAN |  | Section Length (Km) | Submitted For Approval | PGCIL Letter Date | PGCIL Aprroval Mail Date | Approval Date
| From Section | To Section | [6 empty] | From Section | To Section
1 | 3/0 | 14/0 | 26.427 | 4.06.2025 | 3.06.2025 | Approved |  | 1 | 3/0 | 5/0 | 6.312 | 17.05.2025 | 17.05.2025 |  | Approved
2 | 14/0 | 18/0 | 9.145 | 2.06.2025 | 3.06.2025 | Approved |  | 2 | 14/0 | 29/0 | 22.093 | 14.05.2025 | 15.05.2025 |  | Approved
3 | 18/0 | 23/0 | 5.0525 | 12.04.2025 | 13.04.2025 | Approved |  | 3 | 29/0 | 33/0 | 8.699 | 19.04.2025 | 01.05.2025 |  | Approved
4 | 23/0 | 24/0 | 2.789 | 05.04.2025 | 07.04.2025 | Approved |  | 4 | 35/0 | 58/0 | 28.735 | 15.05.2025 | 15.05.2025 |  | Approved
5 | 24/0 | 30/0 | 5.64 | 07.03.2025 | 04.04.2025 | Approved |  | 5 | 87/0 | 101/0 | 45.55 | 06.06.2025 |  |  | Approved
6 | 30/0 | 32/0 | 2.21 | 28.03.2025 | 05.04.2025 | Approved |  | 6 | 58/0 | 87/0 |  | 08.06.2025 |  |  | Approved
7 | 33/0 | 40/0 | 5.41 | 28.03.2025 | 05.04.2025 | Approved |  | 7 | 101/0 | 119/0 | 15.286 | 17.07.2025 | 26.07.2025 |  | Approved
8 | 32/0 | 33/0 | 2.01 | 28.03.2025 | 05.04.2025 | Approved |  | 8 | AP5 | AP14 | 13.34 | 05.08.2025 |  |  | Approved
9 | 41/0 | Gantry | 15.6 | 12.06.2025 | 04.07.2025 | Approved |  | 9 | AP32 | AP33 | 0.72 | 05.08.2025 |  |  | Approved
10 | 40/0 | 41/0 | 1.98 | 16.07.2025 | 18.07.2025 | Approved |  | 10 | Gantry | AP-3 | 6.85 | 06.02.2026 |  |  | Approval Pending
11 | Gantry | AP-3 | 6.528 | 24.12.2025 |  | Approval Pending
Approved Total Qty |  |  | 76.2635 |  |  |  |  | Approved Total Qty |  |  | 140.735
400 KV D/C Siwani To Fatehabad
Land Schedule
Sl.No. | SPAN |  | Submitted For Approval |  |  | Status | Remarks
| From Section | To Section |  |  | Approval Date
1 | 18/0 | 40/0 | 17.05.2025 |  |  | 53
2 | 14/0 | 17/0 | 29.05.2025 |  |  | 16
3 | 3/0 | 7/0 | 06.06.2025 |  |  | 38
4 | 7/0 | 14/0 | 10.06.2025 |  |  | 29

## FDN S-P
KEC International Limited | [10 empty] | WET | WP |  | SANDY | PS | DRY
400 KV D/C (Quad) Siwani-Patran TL | [10 empty] | 3 |  |  |  | 1 | 9
Details of Foundation
CUMM. SR.NO | MONTH SR.NO. | Location No. | Type of Tower | Type of Classification | Starting Date | Completion Date | Remarks | Village | Tehsil
1 | 1 | 30/3 | DA-3 | WET | 21.04.2025 | 22.04.2025 | Template | Durjanpur | Hisar
2 | 2 | 30/1 | DA+3 | WET | 22.04.2025 | 25.04.2025 | Template | Durjanpur | Hisar | S.NO | Tower | Type | Windzone | Classification( Excecuted Locations)
3 | 3 | 30/2 | DA+3 | WET | 24.04.2025 | 28.04.2025 | Template | Durjanpur | Hisar |  |  |  |  | WET | WP | SANDY | PS | DRY | Total
2025-05-01 | [9 empty] | 1 | DA | -3M TO 0M | 4 | 13 | 1 | 4 | 2 |  | 20 | 8
4 | 1 | 29/5 | DA+0 | WET | 29.04.2025 | 01.05.2025 | Template | Kaijlan | Adampur | 2 | DA | +1.5M To 9M | 4 | 11 |  | 9 |  | 1 | 21 | 4
5 | 2 | 29/2 | DA+9 | WET | 1.05.2025 | 03.05.2025 | Template | Inchha kharkheri | Adampur | 3 | DB | -3M TO 0M | 4 |  | 1 |  |  | 3 | 4
6 | 3 | 29/4 | DA+6 | Sandy | 02.05.2025 | 04.05.2025 | Template | Inchha kharkheri | Adampur | 4 | DC | -3M TO 0M | 4 |  |  |  |  | 4 | 4
7 | 4 | 29/1 | DA+0 | Sandy | 03.05.2025 | 06.05.2025 | Prop | Inchha kharkheri | Adampur | 5 | DC | +1.5M To 9M | 4 | 1 |  |  |  |  | 1
8 | 5 | 29/3 | DA+3 | WET | 03.05.2025 | 05.05.2025 | Template | Inchha kharkheri | Adampur | 6 | 5DA | -3M TO 0M | 5 | 2 | 1 |  | 1 | 3 | 7
9 | 6 | 28/4 | DA+3 | WET | 07.05.2025 | 09.05.2025 | Prop | Neoli khurd | Adampur | 7 | 5DA | +1.5M To 9M | 5 | 3 |  |  | 1 | 9 | 13
10 | 7 | 28/3 | DA+6 | Sandy | 07.05.2025 | 09.05.2025 | Prop | Neoli khurd | Adampur | 8 | 5DB | +1.5M To 9M | 5 |  |  |  |  | 1 | 1
11 | 8 | 28/2 | DA+3 | Sandy | 09.05.2025 | 11.05.2025 | Template | Neoli khurd | Adampur | Total |  |  |  | 30 | 3 | 13 | 4 | 21 | 71
12 | 9 | 3/5 | DA+3 | Sandy | 16.05.2025 | 20.05.2025 | Prop | Gaindwas | Siwani
13 | 10 | 3/6 | DA+0 | Sandy | 20.05.2025 | 24.05.2025 | Prop | Gaindwas | Siwani
14 | 11 | 3/10 | DA+3 | Sandy | 24.05.2025 | 27.05.2025 | Prop | Siwani | Siwani
2025-06-01
15 | 1 | 21/7 | DA+3 | WET | 30.05.2025 | 02.06.2025 | Template | Shahpur | Hisar
16 | 2 | 21/6 | DA+0 | PS | 30.05.2025 | 05.06.2025 | Prop | Hindwan | Hisar
17 | 3 | 23/1 | DA-1.5 | WET | 03.06.2025 | 07.06.2025 | Prop | Shahpur | Hisar
18 | 4 | 23/3 | DA+6 | WET | 05.06.2025 | 09.06.2025 | Prop | Shahpur | Hisar
19 | 5 | 23/2 | DA+0 | WET | 07.06.2025 | 11.06.2025 | Prop | Shahpur | Hisar
20 | 6 | 23/4 | DA+0 | WET | 11.06.2025 | 15.06.2025 | Prop | Shahpur | Hisar
21 | 7 | 56/1 | 5DA+3 | Dry | 21.06.2025 | 28.06.2025 | Prop | Pabra | Uklana
2025-07-01
22 | 1 | 14/4 | DA+3 | Sandy | 20.06.2025 | 01.07.2025 | Prop | Panihari Chak | Hisar
23 | 2 | 26/1 | DA+0 | Wet Paddy | 28.06.2025 | 03.07.2025 | Prop | Mattarsham | Hisar
24 | 3 | 56/2 | 5DA+6 | DRY | 02.07.2025 | 05.07.2025 | Prop | Pabra | Uklana
25 | 4 | 14/3 | DA+3 | Sandy | 02.07.2025 | 07.07.2025 | Prop | Panihari Chak | Hisar
26 | 5 | 56/4 | 5DA+9 | Dry | 05.07.2025 | 10.07.2025 | Prop | Chamar khera | Uklana
27 | 6 | 14/2 | DA+6 | Sandy | 07.07.2025 | 2025-07-13 | Prop | Chaudhriwas | Hisar
28 | 7 | 56/0 | 5DB1+6 | Dry | 12.07.2026 | 2025-07-15 | Prop | Pabra | Uklana
29 | 8 | 55/5 | 5DA+6 | Dry | 2025-07-16 | 20.07.2025 | Prop | Pabra | Uklana
30 | 9 | 15B/4 | DA+6 | Dry | 15.07.2025 | 21.07.2025 | Prop | Rawalwas kalan | Balsamand
31 | 10 | 55/0 | 5DB2+3 | Dry | 20-07.2025 | 24.07.2025 | Prop | Pabra | Uklana
32 | 11 | 55/6 | 5DA+3 | Dry | 2025-07-24 | 28.07.2025 | Prop | Pabra | Uklana
Aug'25
33 | 1 | 54/6 | 5DA+0 | Wet | 21.07.2025 | 9.08.2025 | Prop | Pabra | Uklana
34 | 2 | 36/3 | 5DA+0 | Dry | 2025-07-26 | 20.08.2025 | Prop | Landhari sukh nambran | Hisar
35 | 3 | 56/3 | 5DA+3 | Dry | 2025-08-19 | 24.08.2025 | Prop | Pabra | Uklana
Sept'25
36 | 1 | 36/4 | 5DA-3 | Dry | 21.08.2025 | 01.09.2025 | Prop | Landhari sukh nambran | Hisar
37 | 2 | 30/0 | DB2+0 | Dry | 10.09.2025 | 19.09.2025 | Prop | Kaijlan | Adampur
38 | 3 | 29/0 | DC1+0 | DRY | 19.08.2025 | 24.09.2025 | Prop | Inchha kharkheri | Adampur
Nov'25
39 | 1 | 54/3 | 5DA+3 | WET | 24.10.2025 | 11.11.2025 | Prop | Bhuna | Uklana
40 | 2 | 54/7 | 5DA+6 | WET | 14.11.2025 | 23.11.2025 | Prop | Pabra | Uklana
41 |  | 55/3 |  | WET | 03.11.2025
Dec'25
41 | 1 | 51/4 | 5DA+6 | DRY | 30.11.2025 | 05.12.2025 | Prop | Nehla | Bhuna
42 | 2 | 51/2 | 5DA+3 | DRY | 06.12.2025 | 09.12.2025 | Prop | Pabra | Uklana
43 | 3 | 54/5 | 5DA+0 | WET | 21.08.2025 | 15.12.2025 | Prop | Pabra | Uklana
44 | 4 | 52/4 | 5DA+0 | DRY | 14.12.2025 | 18.12.2025 | Prop | Nehla | Bhuna
45 | 5 | 51/5 | 5DA+6 | DRY | 19.12.2025 | 23.12.2025 | Prop | Nehla | Bhuna
Feb'26
46 | 1 | 54/8 | 5DA+3 | PS | 24.01.2026 | 2026-02-15 | Prop | Pabra | Uklana
47 | 2 | 52/3 | 5DA+0 | Wet Paddy | 2026-02-17 | 2026-02-25 | Prop | Nehla | Bhuna
March'26
48 | 1 | 55/1 | 5DA+9 | PS | 2026-02-27 | 2026-03-07 | Prop | Pabra | Uklana
April'26
49 | 1 | 55/2 | 5DA+3 | WET | 2026-03-28 | 2026-04-11 | Prop | Pabra | Uklana
May'26
50 | 1 | 52/2 | 5DA+0 | Wet Paddy | 2026-04-22 | 2026-05-03 | Prop | Nehla | Bhuna
51 | 2 | 55/4 | 5DA+3 | WET | 2026-04-27 | 2026-05-04 | Prop | Nehla | Bhuna
52 | 3 | 52/0 | 5DB1+3 | Wet Paddy | 2026-04-24 | 2026-05-05 | Prop | Nehla | Bhuna
53 | 4 | 52/1 | 5DA+0 | Wet Paddy | 2026-05-04 | 2026-05-10 | Prop | Nehla | Bhuna
54 | 5 | 52/5 | 5DA+0 | Wet | 2025-05-05 | 2026-05-11 | Prop | Nehla | Bhuna
55 | 6 | 55/3 | 5DA+0 | Wet | 2025-05-06 | 2026-05-15 | Prop | Pabra | Uklana
56 | 7 | 64/2 | 5DA+0 | Wet Paddy | 2025-05-11 | 2026-05-16 | Prop | Saniana | Tohana
57 | 8 | 64/5 | 5DA+3 | Wet Paddy | 2025-05-11 | 2026-05-19 | Prop | Saniana | Tohana
58 | 9 | 55/7 | 5DA+9 | Wet | 2025-05-11 | 2025-05-20 | Prop | Pabra | Uklana
59 | 10 | 64/3 | 5DA+0 | Wet Paddy | 2026-05-19 | 2026-05-21 | Prop | Saniana | Tohana
60 | 11 | 51/3 | 5DA+0 | Wet Paddy | 2026-05-20 | 2026-05-23 | Prop | Nehla | Bhuna
61 | 12 | 64/4 | 5DA+3 | Wet Paddy | 2026-05-21 | 2026-05-25 | Prop | Saniana | Tohana
62 | 13 | 64/6 | 5DA+3 | Wet Paddy | 2026-05-24 | 2026-05-29 | Prop | Saniana | Tohana
63 | 14 | 74/9 | 5DA+0 | Wet Paddy | 2026-05-19 | 2026-05-30 | Prop | Laloda | Tohaana
64 | 15 | 61/2 | 5DA+9 | Wet Paddy | 2026-05-23 | 2026-05-30 | Prop | Saniana | Tohana
June'26
65 | 1 | 64/1 | 5DA+6 | Wet Paddy | 2026-05-26 | 2026-06-01 | Prop | Saniana | Tohana
66 | 2 | 54/1 | 5DA+0 | Wet | 2026-05-23 | 2026-06-07 | Prop | Nehla | Bhuna
67 | 3 | 74/8 | 5DA+0 | Wet Paddy | 2026-06-01 | 2026-06-07 | Prop | Laloda | Tohaana
68 | 4 | 62/1 | 5DA+9 | Wet Paddy | 2026-06-02 | 2026-06-09 | Prop | Saniana | Tohana
69 | 5 | 61/0 | 5DB1+3 | Wet Paddy | 2026-06-06 | 2026-06-14 | Prop | Saniana | Tohana
70 | 6 | 74/7 | 5DA+3 | Wet Paddy | 2026-06-07 | 2026-06-14 | Prop | Laloda | Tohaana
71 | 7 | 51/1 | 5DA+3 | Wet Paddy | 2026-06-07 | 2026-06-17 | Prop | Kanoh | Uklana
72 | 8 | 61/1 | 5DA+6 | Wet Paddy | 2026-06-13 | 2026-06-18 | Prop | Saniana | Tohana
73 | 9 | 51/0 | 5DB2+6 | Wet Paddy | 2026-06-18 | 2026-06-25 | Prop | Kanoh | Uklana
74 | 10 | 54/2 | 5DA+0 | Wet | 2026-06-04 | 27-6-2026 | Prop | Nehla | Bhuna
75 |  | 62/0 | 5DB2+0 | Wet Paddy | 2026-05-30 |  | Prop | Saniana | Tohana | [11 empty] | ROW-06-06-2026
76 |  | 58/2 | 5DA+0 | Wet Paddy | 2026-06-19 |  | Prop | Chamar khera | Uklana | [11 empty] | ROW

## FDN S-F
KEC International Limited
400 KV D/C (Quad) Siwani-Fatehabad TL
Details of Foundations
CUMM. SR.NO | MONTH SR.NO. | Location No. | Type of Tower | Type of Classification | Starting Date | Completion Date | Remarks | Village | Tehsil
1 | 1 | 25/1 | DA+1.5 | WET | 22.03.2025 | 28.03.2025 | Prop | Kaijlan | Adampur
2025-04-01
2 | 1 | 25/2 | DA+0 | WET | 25.03.2025 | 01.04.2025 | Prop | Ashrawan | Adampur
3 | 2 | 24/2 | DA+0 | WET | 30.03.2025 | 04.04.2025 | Prop | Mallapur | Adampur
4 | 3 | 24/1 | DA+0 | WET | 02.04.2025 | 07.04.2025 | Prop | Mallapur | Adampur
5 | 4 | 26/2 | DA+6 | WET | 04.04.2025 | 12.04.2025 | Prop | Ashrawan | Adampur
6 | 5 | 30/2 | DA-3 | WET | 09.04.2025 | 12.04.2025 | Prop | Kaliravan | Adampur
7 | 6 | 23/6 | DA-1.5 | WET | 12.04.2025 | 14.04.2025 | Prop | Mallapur | Adampur
8 | 7 | 23/5 | DA+6 | WET | 14.04.2025 | 16.04.2025 | Prop | Mallapur | Adampur
9 | 8 | 31/1 | DA+0 | WET | 14.04.2025 | 17.04.2025 | Prop | Kaliravan | Adampur
10 | 9 | 37/1 | DA+0 | PS | 17.04.2025 | 24.04.2025 | Prop | Khasa mahajan | Adampur
11 | 10 | 31/2 | DA+0 | WET | 23.04.2025 | 30.04.2025 | Prop | Kaliravan | Adampur
12 | 11 | 24/3 | DA+0 | Sandy | 26.04.2025 | 29.04.2025 | Prop | Kaijlan | Adampur
2025-05-01
13 | 1 | 24/4 | DA+1.5 | Sandy | 16.05.2025 | 17.05.2025 | Template | Kaijlan | Adampur
14 | 2 | 23/3 | DA+0 | WET | 21.05.2025 | 24.05.2025 | Template | Neoli Khurd | Adampur
15 | 3 | 32B/1 | DA+3 | WET | 25.05.2025 | 28.05.2025 | Template | Kaliravan | Adampur
2025-06-01
16 | 1 | 18/4 | DA-1.5 | Sandy | 20.06.2025 | 28.06.2025 | Template | Mattarsham | Hisar
Sept'25
17 | 1 | 27/0 | DC1+0 | DRY | 10.09.2025 | 14.09.2025 | Prop | Ashrawan | Adampur
18 | 2 | 26/0 | DC1+0 | DRY | 13.09.2025 | 18.09.2025 | Prop | Ashrawan | Adampur
19 | 3 | 25/0 | DB2+0 | DRY | 15.09.2025 | 20.09.2025 | Prop | Kaijlan | Adampur
20 | 4 | 24/0 | DB1+0 | WET Paddy | 19.09.2025 | 24.09.2025 | Prop | Mallapur | Adampur
2025-10-01
21 | 1 | 19/0 | DC2+3 | Wet | 25.09.2025 | 01.10.2025 | Prop | Mattarsham | Hisar
22 | 2 | 28/0 | DC1-3 | Dry | 30.09.2025 | 05.10.2025 | Prop | Ashrawan | Adampur
23 | 3 | 18/0 | DB1+0 | DRY | 04.10.2025 | 06.10.2025 | Prop | Mattarsham | Hisar
2025-05-01
24 | 1 | 30/0 | DC1+6 | WET Paddy | 04.05.2026 | 17.05.2026 | Prop | Ashrawan | Adampur
25 | 2 | 28/1 | DA+9 | DRY | 17.05.2026 | 22.05.2026 | Prop | Ashrawan | Adampur
2025-06-01
26 | 1 | 55/1 | 5DA-3 | DRY | 28.05.2026 | 09.06.2026 | Prop | Dhangar | Fatehabad

## Total Supply
SUPPLY STATUS SUMMARY (Siwani-Patran TL & Siwani-Fatehabad TL
Sl. No. | Description | UOM | Latest Estimate |  | Final LE | L2 Sch till March''26 | Receipt Material |  |  | Reciept Qty | Balance to reciept | Remarks
|  |  | SF | SP |  |  | SF | SP(Haryana) | SP(Punjab)
I | SUPPLY
1 | Stubs | Sets | 220 | 399 | 619 | 597 | 191 | 284 | 56 | 531 | 88
| Wind zone -04 -Stub | Sets | 173 | 152 | 325 |  | 155 | 127 |  | 282 | 43 | Supply Underprogress
| Wind Zone -05-Stub | Sets | 47 | 247 | 294 |  | 36 | 157 | 56 | 249 | 45
2 | Towers | Nos | 220 | 399 | 619 | 490 | 176 | 246 | 61 | 483 | 136
| Wind zone -04 -Tower | Sets | 173 | 152 | 325 |  | 148 | 124 | 0 | 272 | 53
| Wind Zone -05-Tower | Sets | 47 | 247 | 294 |  | 28 | 122 | 61 | 211 | 83
3 | Conductor | KM | 1908 | 3495 | 5403 | 3800 | 1908 | 2749.124 | 744.749 | 5401.873 | 1.127
4 | Conductor Accessories H/W | % | 100% | 100% | 100% | 70% | 85% | 85% |  | 85% | 15%
5 | Earthwire | KM | 80 | 150 | 230 | 161 | 56 | 105 |  | 161 | 69
6 | Earthwire Acessories for 7/3.66mm | % | 100% | 100% | 100% | 70% | 85% | 85% |  | 85% | 15%
7 | Insulator (120 KN) | Nos | 1776 | 3242 | 5018 | 3996 | 600 | 1300 |  | 1900 | 3118 | Supply U/P
8 | Insulator (160 KN) | Nos | 3648 | 6624 | 10272 | 8000 | 2400 | 4500 |  | 6900 | 3372
9 | OPGW drums | KM | 83 | 151.78 | 234.78 | 117.89 | 0 | 0 |  | 0 | 234.78
10 | OPGW H/W fittings | % | 100% | 100% | 100% | 50 | 0 | 0 |  | 0 | 100%
I | SUPPLY
1 i) | Stubs | Nos
1 | Tower type "DA" | Sets | 124 | 111 | 235 | 597 | 114 | 96 |  | 210 | 25
2 | Tower type "DB1 & DB2" upto 9 Mtr | Sets | 19 | 17 | 36 |  | 18 | 17 |  | 35 | 1
3 | Tower type "DB1+18M | Sets | 1 | 0 | 1 |  | 1 |  |  | 1 | 0
5 | Tower type "DC1& DC2" upto 9 Mtr | Sets | 18 | 12 | 30 |  | 17 | 10 |  | 27 | 3
7 | Tower type "DC2+18M" | Sets | 0 | 0 | 0 |  |  |  |  | 0 | 0
8 | Tower type "DD45" upto 9 Mtr | Sets | 3 | 1 | 4 |  | 4 | 2 |  | 6 | -2
9 | Tower type "DD60" upto 9 Mtr | Sets | 8 | 9 | 17 |  | 2 | 3 |  | 5 | 12
10 | Tower type "DD60" for +18 & +25M Extn | Sets |  | 2 | 2 |  |  |  |  | 0 | 2
11 | Tower type "DD60" for +30 & +35M Extn | Sets |  | 0 | 0 |  |  |  |  | 0 | 0
0
12 | Tower type "5DA" | Sets | 20 | 158 | 178 |  | 20 | 110 | 40 | 170 | 8 | 48
13 | Tower type "5DB1 & 5DB2" upto 9 Mtr | Sets | 8 | 32 | 40 |  | 7 | 23 | 9 | 39 | 1
14 | Tower type "5DB1+18M & 25M | Sets | 0 | 6 | 6 |  |  |  |  | 0 | 6
16 | Tower type "5DC1& 5DC2" upto 9 Mtr | Sets | 6 | 16 | 22 |  | 5 | 10 | 5 | 20 | 2
18 | Tower type "5DC2+18M" | Sets | 0 | 3 | 3 |  |  |  |  | 0 | 3
19 | Tower type "5DD45" upto 9 Mtr | Sets | 7 | 8 | 15 |  | 1 | 4 | 2 | 7 | 8
| Tower type "5DD45" FOR 18 Mtr | Sets | 3 | 2 | 5 |  |  |  |  | 0 | 5
20 | Tower type "5DD60" upto 9 Mtr | Sets | 3 | 8 | 11 |  | 3 | 10 |  | 13 | -2
21 | Tower type "5DD60" for +18 & +25M Extn | Sets | 0 | 8 | 8 |  |  |  |  | 0 | 8
22 | Tower type "DD60" for +30 & +35M Extn | Sets | 0 | 2 | 2 |  |  |  |  | 0 | 2
23 | DDH | Sets |  | 2 | 2 |  |  |  |  | 0 | 2
[10 empty] | 0 | 0
24 | Tower type "5DD60+18"(1.5 M RC) | Sets |  | 1 | 1 |  |  |  |  | 0 | 1
25 | Tower type "5DB2+9"(2 M RC) | Sets |  | 1 | 1 |  |  |  |  | 0 | 1
|  |  | 220 | 399 | 619 |  | 192 | 285 | 56 | 533 | 86
2 i) | Towers
1 | DA
| DA Basic | SET | 124 | 111 | 235 |  | 114 | 96 |  | 210 | 25
i | DA-1.5 | SET | 3 | 1 | 4 |  | 3 | 1 |  | 4 | 0
ii | DA-3 | SET | 8 | 4 | 12 |  | 8 | 4 |  | 12 | 0
| DA+0 Tower | [5 empty] | 47 | 38 |  | 85
iii | DA+0 Extenstion | SET | 82 | 67 | 149 |  | 26 | 17 |  | 43 | 106
iv | DA+1.5 | SET | 4 | 1 | 5 |  | 4 | 0 |  | 4 | 1
v | DA+3 | SET | 27 | 38 | 65 |  | 26 | 36 |  | 62 | 3
vi | DA+6 | SET | 22 | 15 | 37 |  | 18 | 14 |  | 32 | 5
vii | DA+9 | SET | 8 | 5 | 13 |  | 8 | 3 |  | 11 | 2
DB1 & DB2
| Basic | SET | 20 | 17 | 37 |  | 16 | 16 |  | 32 | 5
i | DB-1.5 | SET | 0 | 0 | 0 |  |  |  |  | 0 | 0
ii | DB-3 | SET | 0 | 1 | 1 |  |  |  |  | 0 | 1
iii | DB+0 | SET | 16 | 12 | 28 |  | 12 | 11 |  | 23 | 5
| DB+0 Extension | [6 empty] | 1 |  | 1
iv | DB+3 | SET | 4 | 4 | 8 |  | 4 | 4 |  | 8 | 0
v | DB+6 | SET | 0 | 0 | 0 |  |  |  |  | 0 | 0
vi | DB+9 | SET | 0 | 2 | 2 |  |  | 1 |  | 1 | 1
vii | DB+18 | SET | 1 | 0 | 1 |  |  |  |  | 0 | 1
DC1 & DC2
| Basic | SET | 18 | 12 | 30 |  | 14 | 9 |  | 23 | 7
i | DC-1.5 | SET |  |  | 0 |  |  |  |  | 0 | 0
ii | DC-3 | SET | 1 | 1 | 2 |  |  |  |  | 0 | 2
iii | DC+0 | SET | 13 | 8 | 21 |  | 10 | 3 |  | 13 | 8
| DC+0 Extension | SET |  |  |  |  | 0 | 4 |  | 4
iv | DC+3 | SET | 4 | 3 | 7 |  | 4 | 2 |  | 6 | 1
v | DC+6 | SET | 1 | 3 | 4 |  |  | 2 |  | 2 | 2
vi | DC+9 | SET | 0 | 2 | 2 |  |  | 2 |  | 2 | 0
vii | DC+18 | SET | 0 | 0 | 0 |  |  |  |  | 0 | 0
DD45
i | Basic | SET | 3 | 1 | 4 |  | 3 | 0 |  | 3 | 1
ii | DD45+0 | SET | 3 | 1 | 4 |  | 3 |  |  | 3 | 1
| DD45+0 extension | SET |  |  |  |  | 0 | 0 |  | 0
iii | DD45+3 | SET |  |  | 0 |  |  |  |  | 0 | 0
iv | DD45+6 | SET |  |  | 0 |  |  |  |  | 0 | 0
v | DD45+9 | SET |  | 1 | 1 |  |  |  |  | 0 | 1
DD60
| Basic | SET | 8 | 11 | 19 |  | 1 | 3 |  | 4 | 15
i | DD60+0 | SET | 7 | 9 | 16 |  | 1 | 1 |  | 2 | 14
| DD60+0 Extension | [5 empty] | 0 | 1 |  | 1
ii | DD60+3 | SET | 1 | 2 | 3 |  |  | 1 |  | 1 | 2
iii | DD60+6 | SET | 4 | 3 | 7 |  |  | 1 |  | 1 | 6
iv | DD60+9 | SET | 1 | 2 | 3 |  |  |  |  | 0 | 3
v | DD60+18 | SET |  | 0 | 0 |  |  |  |  | 0 | 0
vi | DD60+25 | SET |  | 2 | 2 |  |  |  |  | 0 | 2
vii | DD60+35 | SET |  |  | 0 |  |  |  |  | 0 | 0
|  |  | 173 | 152 | 325 | 0 | 148 | 124 | 0 | 272 | 53
1 | 5DA
| 5DA Basic | SET | 20 | 158 | 178 |  | 19 | 103 | 48 | 170 | 8
i | 5DA-1.5 | SET | 0 | 0 | 0 |  |  |  |  | 0 | 0
ii | 5DA-3 | SET | 2 | 5 | 7 |  | 0 | 0 |  | 0 | 7
iii | 5DA+0 | SET | 14 | 114 | 128 |  | 2 | 31 | 18 | 51 | 77
| 5DA+0 Extension | SET |  |  |  |  | 13 | 45 | 20 | 78
v | 5DA+3 | SET | 4 | 39 | 43 |  | 4 | 27 | 10 | 41 | 2
vi | 5DA+6 | SET | 6 | 47 | 53 |  | 6 | 33 | 13 | 52 | 1
vii | 5DA+9 | SET | 6 | 19 | 25 |  | 7 | 12 | 7 | 26 | -1
| 5DB1 & 5DB2 | [9 empty] | 0
| Basic | SET | 8 | 39 | 47 |  | 2 | 9 | 8 | 19 | 28
i | 5DB-1.5 | SET | 1 | 0 | 1 |  |  |  |  | 0 | 1
ii | 5DB-3 | SET | 1 | 0 | 1 |  |  |  |  | 0 | 1
iii | 5DB+0 | SET | 4 | 33 | 37 |  | 1 | 6 | 4 | 11 | 26
| 5DB+0 Extension | [5 empty] | 1 | 3 | 4 | 8
iv | 5DB+3 | SET | 2 | 6 | 8 |  |  |  |  | 0 | 8
v | 5DB+6 | SET | 1 | 11 | 12 |  |  |  |  | 0 | 12
vi | 5DB+9 | SET | 1 | 9 | 10 |  | 1 | 3 | 4 | 8 | 2
vii | 5DB+18 | SET | 0 | 5 | 5 |  |  |  |  | 0 | 5
VIII | 5DB+25 | SET |  | 1 | 1 |  |  |  |  | 0 | 1
| 5DC1 & 5DC2 | [9 empty] | 0
| Basic | SET | 6 | 19 | 25 |  | 6 | 10 | 5 | 21 | 4
iii | 5DC+0 | SET | 5 | 14 | 19 |  | 1 | 3 | 0 | 4 | 15
| 5DC+0 Extension | [5 empty] | 4 | 3 | 5 | 12
iv | 5DC+3 | SET | 1 | 5 | 6 |  | 1 | 4 |  | 5 | 1
v | 5DC+6 | SET | 2 | 5 | 7 |  | 2 | 1 | 4 | 7 | 0
vi | 5DC+9 | SET | 2 | 3 | 5 |  | 2 | 2 | 1 | 5 | 0
vii | 5DC+18 | SET | 0 | 3 | 3 |  |  |  |  | 0 | 3
| 5DD45 | [9 empty] | 0
i | 5Basic | SET | 10 | 10 | 20 |  |  |  |  | 0 | 20
| 5DD45-3 | SET | 1 |  | 1 |  |  |  |  | 0 | 1
ii | 5DD45+0 | SET | 5 | 8 | 13 |  |  |  |  | 0 | 13
iii | 5DD45+3 | SET | 4 | 2 | 6 |  |  |  |  | 0 | 6
iv | 5DD45+6 | SET | 0 | 1 | 1 |  |  |  |  | 0 | 1
v | 5DD45+9 | SET | 1 | 1 | 2 |  |  |  |  | 0 | 2
Vi | 5DD45+18 | SET | 3 | 1 | 4 |  |  |  |  | 0 | 4
viii | 5DD45+25 | SET |  | 1 | 1 |  |  |  |  | 0 | 1
| 5DD60 | [9 empty] | 0
| Basic | SET | 3 | 19 | 22 |  | 1 |  |  | 1 | 21
i | DD60+0 | SET | 2 | 19 | 21 |  | 1 |  |  | 1 | 20
ii | DD60+3 | SET | 1 |  | 1 |  |  |  |  | 0 | 1
iii | DD60+6 | SET |  | 2 | 2 |  |  |  |  | 0 | 2
iv | DD60+9 | SET | 1 | 3 | 4 |  | 1 |  |  | 1 | 3
v | DD60+18 | SET |  | 7 | 7 |  |  |  |  | 0 | 7
vi | DD60+25 | SET |  | 2 | 2 |  |  |  |  | 0 | 2
v | DD60+30 | SET |  | 2 | 2 |  |  |  |  | 0 | 2
vi | DD60+35 | SET |  |  | 0 |  |  |  |  | 0 | 0
| DDH | SET |  | 2 | 2 | [5 empty] | 2
|  |  | 47 | 247 | 294 |  | 28 | 122 | 61 | 211 | 83
3 | Tower accessories
i | Danger plate | Nos
ii | Number plate | Nos
iii | Phase Plate (Set of Three) | Sets
iv | Circuite Plate (Set of Two) | Nos
v | Anticlimbing Device | Nos
vi | Bird Guard (Set of Three) | Nos
IV | Supply of H/W Fittings
1 | Supply of Hardware fitting (ACSR Moose Conductor)
a) | Double ISuspension String | EA | 810 | 1500 | 2310 |  | 689 | 939 | 336 | 1964 | 346
b) | Single ISuspension String (Pilot) | EA | 156 | 234 | 390 |  | 55 | 28 | 54 | 137 | 253
c) | Quad Tension String | EA | 912 | 1656 | 2568 |  | 775 | 1036 | 372 | 2183 | 385
d) | SingleTension String | EA |  | 8 | 8 |  |  | 7 | 0 | 7 | 1
2 | Supply of Hardware Fitting accessories | [6 empty] | 0 |  | 0 | 0
a) | MID SPAN COMPRESSION JOINT FOR AL59 Moose CONDUCTOR | EA | 999 | 1831 | 2830 |  | 849 | 1256 | 300 | 2405 | 425
b) | REPAIR SLEEVE FOR AL59 Moose CONDUCTOR | EA | 333 | 610 | 943 |  | 283 | 509 | 10 | 802 | 141
c) | PREFORMED RETAINING ROD TYPE SPACER DAMPER SUITABLE FOR Quad AL59 Moose CONDUCTOR | EA | 8820 | 16254 | 25074 |  | 7497 | 10366 | 3450 | 21313 | 3761
d) | RIGID SPACER for jumper AL59 Moose CONDUCTOR | EA | 1350 | 2466 | 3816 |  | 1148 | 1376 | 720 | 3244 | 572
e) | T-CONNECTOR-400KV AC WITH AL59 Moose CONDUCTOR | EA |  | 64 | 64 |  |  | 54 |  | 54 | 10
3 | Supply of E/W cable & Fittings | [6 empty] | 0 |  | 0 | 0
a) | 7/3.66 G.S. EARTHWIRE | Km | 80 | 150 | 230 |  |  | 0 | 0 | 0 | 230
b) | Mid Span Compression Joint -7/3.66mmEarth Wire | Nos | 44 | 80 | 124 | 204 | 37 | 58 | 10 | 105 | 19
c) | FLEXIBLE AL BOND-7/3.66MM E/W | Nos | 287 | 526 | 813 |  | 244 | 437 | 10 | 691 | 122
d) | Vibration damper -7/3.66mm Earth Wire | Nos | 574 | 1052 | 1626 |  | 488 | 662 | 232 | 1382 | 244
e) | Suspension clamp assembly -7/3.66mmEarth Wire | Nos | 135 | 250 | 385 |  | 115 | 157 | 56 | 328 | 57
f) | Tension clamp assembly-7/3.66mm EarthWire | Nos | 150 | 274 | 424 |  | 128 | 173 | 60 | 361 | 63
4 | Supply of OPGW cabe & Fittings
a) | 24 FIBRE (DWSM) OPGW FIBRE OPTIC CABLE | Km | 83 | 151.78 | 234.78 |  |  |  |  | 0
b) | Suspension clamp assembly for 24 fibreOPGW | Nos | 130 | 245 | 375 |  |  |  |  | 0
c) | TENSION FITTINGS ASSEMBLY ON SUSPENSIONTOWER FOR 24F OPGW INCLUDINGALLACCESSORIES AT JOINT BOX (SPLICING)LOCATION | Sets | 5 | 5 | 10 |  |  |  |  | 0
d) | TENSION FITTINGS ASSEMBLY FOR 24F OPGWINCLUDING ALL ACCESSORIES FORJOINT BOX(SPLICING) LOCATION | Sets | 11 | 25 | 36 |  |  |  |  | 0
e) | TENSION ASSEMBLY - DOUBLE TENSION PASSTHROUGH ASSEMBLY FOR 24 FIBEROPGW | Sets | 63 | 110 | 173 |  |  |  |  | 0
f) | TENSION ASSEMBLY - DEAD END FOR 24 FIBEROPGW | Sets | 2 | 2 | 4 |  |  |  |  | 0
g) | Vibration Damper for 24 fibre OPGW | Nos | 986 | 1792 | 2778 |  |  |  |  | 0
h) | Down Lead clamp Assembly for 24 fibreOPGW | Nos | 840 | 1447 | 2287 |  |  |  |  | 0
i) | Joint Box for 24 fibre OPGW | Nos | 18 | 31 | 49 |  |  |  |  | 0
j) | Insulation Sleeve for Conductor |  |  | 320 | 320 |  |  |  |  | 0

## Ere S-F
KEC International Limited
400 KV D/C (Quad) Siwani-Fatehabad TL
Details of Tower Erection
CUMM. SR.NO | MONTH SR.NO. | Loc. No. | Type of Tower | Start | Complete | Remarks
2025-09-01
1 | 1 | 25/2 | DA+0 | 17.09.2025 | 22.09.2025 | Compl
2 | 2 | 25/1 | DA+1.5 | 23.09.2025 | 29.09.2025 | Compl
2025-10-01
3 | 1 | 24/4 | DA+1.5 | 29.09.2025 | 03.10.2025 | Compl
4 | 2 | 26/2 | DA+6 | 03.10.2025 | 09.10.2025 | Compl
5 | 3 | 25/0 | DB2+0 | 10.10.2025 | 14.10.2025 | Compl
6 | 4 | 26/0 | DC1+0 | 14.10.2025 | 19.10.2025 | Compl
7 | 5 | 27/0 | DC1+0 | 19.10.2025 | 25.10.2025 | Compl

## Ere S-P
KEC International Limited
400 KV D/C (Quad) Siwani-Patran TL
Details of Tower Erection
CUMM. SR.NO | MONTH SR.NO. | Loc. No. | Type of Tower | Start | Complete | Remarks
2025-10-01
1 | 1 | 28/3 | DA+6 | 25.10.2025 | 31.10.2025 | Compl
2025-11-01
2 | 1 | 28/2 | DA+3 | 31.10.2025 | 03.11.2025 | Compl
3 | 2 | 29/4 | DA+6 | 03.11.2025 | 06.11.2025 | Compl
4 | 3 | 28/4 | DA+3 | 06.11.2025 | 10.11.2025 | Compl
5 | 4 | 29/5 | DA+0 | 11.11.2025 | 14.11.2025 | Compl
6 | 5 | 29/3 | DA+3 | 15.11.2025 | 18.11.2025 | Compl
7 | 6 | 29/0 | DC1+0 | 19.11.2025 | 26.11.2025 | Compl
2025-12-01
8 | 1 | 29/2 | DA+9 | 27.11.2025 | 01.12.2025 | Compl
9 | 2 | 29/1 | DA+0 | 03.12.2025 | 07.12.2025 | Compl
10 | 3 | 30/0 | DB2+0 | 08.12.2025 | 14.12.2025 | Compl
11 | 4 | 55/5 | 5DA+6 | 15.12.2025 | 24.12.2025 | Compl
2026-01-01
12 | 1 | 55/6 | 5DA+3 | 16.01.2026 | 2026-01-22 | Compl
13 | 2 | 56/2 | 5DA+3 | 23.01.2026 | 2026-01-29 | Compl
2026-02-01
14 | 1 | 54/6 | 5DA+0 | 2026-01-29 | 03.02.2026 | Compl
2026-03-01
15 | 1 | 54/3 | 5DA+3 | 01.03.2026 | 07.03.2026 | Compl
16 | 2 | 56/1 | 5DA+3 | 08.03.2026 | 11.03.2026 | Compl
17 | 3 | 54/5 | 5DA+0 | 12.03.2026 | 16.03.2026 | Compl
18 | 4 | 54/7 | 5DA+6 | 16.03.2026 | 20.03.2026 | Compl
19 | 5 | 55/1 | 5DA+9 | 20.03.2026 | 24.03.2026 | Compl
20 | 6 | 54/8 | 5DA+3 | 24.03.2026 | 31.03.2026 | Compl
2026-04-01
21 | 1 | 52/4 | 5DA+0 | 01.04.2026 | 07.04.2026 | Compl
2026-05-01
22 | 1 | 51/2 | 5DA+3 | 10.05.2025 | 18.05.2026 | Compl
23 | 2 | 51/4 | 5DA+6 | 18.05.2026 | 23.05.2026 | Compl
24 | 3 | 51/5 | 5DA+6 | 23.05.2026 | 31.05.2026 | Compl
2026-06-01
25 | 1 | 52/3 | 5DA+0 | 31.05.2026 | 04.06.2026 | Compl
26 | 2 | 56/4 | 5DA+9 | 04.06.2026 | 12.06.2026 | Compl
27 | 3 | 56/3 | 5DA+3 | 12.06.2026 | 17.06.2026 | Compl
28 | 4 | 52/2 | 5DA+0 | 17.06.2026 | 22.06.2026 | Compl

## T.Abstract
Siwani-Fatehabad TL |  |  |  | Siwani-Patran TL |  |  |  | Total | [5 empty] | WZ-04-Drawing Availability | [5 empty] | WZ-05-Drawing Availability
TOT | Tower qty | TOT | Tower qty | TOT | Tower qty | TOT | Tower qty | TOT | Tower qty | TOT | Tower qty |  | Foundation | Stub | BOM | Tower | BOM | Prop | Template | Foundation | Stub | BOM | Tower | BOM | Prop | Template
DA+0 | 52 | 5DA+0 | 2 | DA+0 | 47 | 5DA+0 | 48 | DA+0 | 99 | 5DA+0 | 50 |  | A | A | A | A | A | A | A | A | A | A | A | A | A | A
DA+1.5 | 4 | 5DA+1.5 | 0 | DA+1.5 | 1 | 5DA+1.5 | 0 | DA+1.5 | 5 | 5DA+1.5 | 0 |  | A | A | A | A | A | A | A | A | 0 | 0 | 0 | 0 | 0 | 0
DA+3 | 27 | 5DA+3 | 4 | DA+3 | 38 | 5DA+3 | 39 | DA+3 | 65 | 5DA+3 | 43 |  | A | A | A | A | A | A | A | A | A | A | A | A | A | A
DA+4.5 | 0 | 5DA+4.5 | 0 | DA+4.5 | 0 | 5DA+4.5 | 0 | DA+4.5 | 0 | 5DA+4.5 | 0 |  | A | A | A | A | A | A | A | A | 0 | 0 | 0 | 0 | 0 | 0
DA+6 | 22 | 5DA+6 | 6 | DA+6 | 15 | 5DA+6 | 47 | DA+6 | 37 | 5DA+6 | 53 |  | A | A | A | A | A | A | A | A | A | A | A | A | A | A
DA+9 | 8 | 5DA+9 | 6 | DA+9 | 5 | 5DA+9 | 19 | DA+9 | 13 | 5DA+9 | 25 |  | A | A | A | A | A | A | A | A | A | A | A | A | A | A
DA-1.5 | 3 | 5DA-1.5 | 0 | DA-1.5 | 1 | 5DA-1.5 | 0 | DA-1.5 | 4 | 5DA-1.5 | 0 |  | A | A | A | A | A | A | A | A | 0 | 0 | 0 | 0 | 0 | 0
DA-3 | 8 | 5DA-3 | 2 | DA-3 | 4 | 5DA-3 | 5 | DA-3 | 12 | 5DA-3 | 7 |  | A | A | A | A | A | A | A | A | A | A | NA | NA | A | A
DB1+0 | 7 | 5DB1+0 | 1 | DB1+0 | 2 | 5DB1+0 | 1 | DB1+0 | 9 | 5DB1+0 | 2 |  | A | A | A | A | A | A | NA | A | A | A | NA | NA | A | A
DB1+3 | 1 | 5DB1+3 | 0 | DB1+3 | 2 | 5DB1+3 | 4 | DB1+3 | 3 | 5DB1+3 | 4 |  | A | A | A | A | A | A | NA | A | A | A | NA | NA | A | A
DB1+6 | 0 | 5DB1+6 | 0 | DB1+6 | 0 | 5DB1+6 | 7 | DB1+6 | 0 | 5DB1+6 | 7 |  | A | A | A | A | A | A | NA | A | A | A | NA | NA | A | A
DB1+9 | 0 | 5DB1+9 | 1 | DB1+9 | 1 | 5DB1+9 | 2 | DB1+9 | 1 | 5DB1+9 | 3 |  | A | A | A | A | A | A | NA | A | A | A | NA | NA | A | A
DB1+18 | 0 | 5DB1+18 | 0 | DB1+18 | 0 | 5DB1+18 | 2 | DB1+18 | 0 | 5DB1+18 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA
DB1-3 | 0 | 5DB1-3 | 1 | DB1-3 | 1 | 5DB1-3 | 0 | DB1-3 | 1 | 5DB1-3 | 1 |  | A | A | A | A | NA | A | NA | A | A | A | NA | NA | A | A
DB2+0 | 8 | 5DB2+0 | 1 | DB2+0 | 8 | 5DB2+0 | 6 | DB2+0 | 16 | 5DB2+0 | 7 |  | A | A | A | A | A | A | NA | A | A | A | NA | NA | A | A
DB2+3 | 3 | 5DB2+3 | 2 | DB2+3 | 2 | 5DB2+3 | 2 | DB2+3 | 5 | 5DB2+3 | 4 |  | A | A | A | A | A | A | NA | A | A | A | NA | NA | A | A
DB2+6 | 0 | 5DB2+6 | 1 | DB2+6 | 0 | 5DB2+6 | 4 | DB2+6 | 0 | 5DB2+6 | 5 |  | A | A | A | A | A | A | NA | A | A | A | NA | NA | A | A
DB2+9 | 0 | 5DB2+9 | 0 | DB2+9 | 1 | 5DB2+9 | 6 | DB2+9 | 1 | 5DB2+9 | 6 |  | A | A | A | A | A | A | NA | A | A | A | NA | NA | A | A
1 |  |  |  | 1 |  | 5DB2+9(1 M RC) | 1 | 1 | 0 | 5DB2+9(1 M RC) | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | A
DB2+18 | 1 | 5DB2+18 | 0 | DB2+18 | 0 | 5DB2+18 | 3 | DB2+18 | 1 | 5DB2+18 | 3 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
DB2+25 | 0 | 5DB2+25 | 0 | DB2+25 | 0 | 5DB2+25 | 1 | DB2+25 | 0 | 5DB2+25 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA
DB2-1.5 | 0 | 5DB2-1.5 | 1 | DB2-1.5 | 0 | 5DB2-1.5 | 0 | DB2-1.5 | 0 | 5DB2-1.5 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A | A | A | NA | NA | A | A
DC1+0 | 6 | 5DC1+0 | 0 | DC1+0 | 2 | 5DC1+0 | 2 | DC1+0 | 8 | 5DC1+0 | 2 |  | A | A | A | A | A | A | A | A | A | A | NA | NA | A | A
DC1+3 | 1 | 5DC1+3 | 0 | DC1+3 | 2 | 5DC1+3 | 5 | DC1+3 | 3 | 5DC1+3 | 5 |  | A | A | A | A | A | A | A | A | A | A | NA | NA | A | A
DC1+6 | 1 | 5DC1+6 | 1 | DC1+6 | 0 | 5DC1+6 | 1 | DC1+6 | 1 | 5DC1+6 | 2 |  | A | A | A | A | A | A | A | A | A | A | NA | NA | A | A
DC1+9 | 0 | 5DC1+9 | 0 | DC1+9 | 1 | 5DC1+9 | 1 | DC1+9 | 1 | 5DC1+9 | 1 |  | A | A | A | A | A | A | A | A | A | A | NA | NA | A | A
DC1+18 | 0 | 5DC1+18 | 0 | DC1+18 | 0 | 5DC1+18 | 2 | DC1+18 | 0 | 5DC1+18 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA
DC1-3 | 1 | 5DC1-3 | 0 | DC1-3 | 0 | 5DC1-3 | 0 | DC1-3 | 1 | 5DC1-3 | 0 |  | A | A | A | A | A | A | A | A | A | 0 | 0 | 0 | 0 | 0
DC2+0 | 6 | 5DC2+0 | 1 | DC2+0 | 1 | 5DC2+0 | 1 | DC2+0 | 7 | 5DC2+0 | 2 |  | A | A | A | A | A | A | A | A | A | A | NA | NA | A | A
DC2+3 | 3 | 5DC2+3 | 1 | DC2+3 | 1 | 5DC2+3 | 0 | DC2+3 | 4 | 5DC2+3 | 1 |  | A | A | A | A | A | A | A | A | A | A | NA | NA | A | A
DC2+6 | 0 | 5DC2+6 | 1 | DC2+6 | 3 | 5DC2+6 | 4 | DC2+6 | 3 | 5DC2+6 | 5 |  | A | A | A | A | A | A | A | A | A | A | NA | NA | A | A
DC2+9 | 0 | 5DC2+9 | 2 | DC2+9 | 1 | 5DC2+9 | 2 | DC2+9 | 1 | 5DC2+9 | 4 |  | A | A | A | A | A | A | A | A | A | A | NA | NA | A | A
DC2-3 | 0 | 5DC2-3 | 0 | DC2-3 | 1 | 5DC2-3 | 0 | DC2-3 | 1 | 5DC2-3 | 0 |  | A | A | A | A | A | A | A | A | A | A | 0 | 0 | A | A
0 | [5 empty] | 5DC2+18 | 1 |  |  | 5DC2+18 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A | NA | NA | NA | NA | NA | NA
DD45+0 | 3 | 5DD45+0 | 1 | DD45+0 | 0 | 5DD45+0 | 4 | DD45+0 | 3 | 5DD45+0 | 5 |  | A | A | A | A | A | A | A | A | NA | NA | NA | NA | NA | NA
DD45+3 | 0 | 5DD45+3 | 4 | DD45+3 | 0 | 5DD45+3 | 2 | DD45+3 | 0 | 5DD45+3 | 6 |  | 0 | A | A | A | A | A | 0 | A | NA | NA | NA | NA | NA | NA
DD45+6 | 0 | 5DD45+6 | 0 | DD45+6 | 0 | 5DD45+6 | 1 | DD45+6 | 0 | 5DD45+6 | 1 |  | 0 | A | A | A | A | A | 0 | A | NA | NA | NA | NA | NA | NA
DD45+9 | 0 | 5DD45+9 | 1 | DD45+9 | 1 | 5DD45+9 | 1 | DD45+9 | 1 | 5DD45+9 | 2 |  | A | A | A | A | A | A | A | A | NA | NA | NA | NA | NA | NA
DD45+18 | 0 | 5DD45+18 | 3 | DD45+18 | 0 | 5DD45+18 | 1 | DD45+18 | 0 | 5DD45+18 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA
DD45+25 | 0 | 5DD45+25 | 0 | DD45+25 | 0 | 5DD45+25 | 1 | DD45+25 | 0 | 5DD45+25 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA
DD45-3 | 0 | 5DD45-3 | 1 | DD45-3 | 0 | 5DD45-3 | 0 | DD45-3 | 0 | 5DD45-3 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A | NA | NA | NA | NA | NA | NA
DD60+0 | 2 | 5DD60+0 | 1 | DD60+0 | 2 | 5DD60+0 | 3 | DD60+0 | 4 | 5DD60+0 | 4 |  | A | A | A | A | A | A | A | A | A | A | A | A | A | A
DD60+3 | 1 | 5DD60+3 | 1 | DD60+3 | 2 | 5DD60+3 | 0 | DD60+3 | 3 | 5DD60+3 | 1 |  | A | A | A | A | A | A | A | A | A | A | NA | NA | A | A
DD60+6 | 4 | 5DD60+6 | 0 | DD60+6 | 3 | 5DD60+6 | 2 | DD60+6 | 7 | 5DD60+6 | 2 |  | A | A | A | A | A | A | A | A | A | A | NA | NA | A | A
DD60+9 | 1 | 5DD60+9 | 1 | DD60+9 | 2 | 5DD60+9 | 3 | DD60+9 | 3 | 5DD60+9 | 4 |  | A | A | A | A | A | A | A | A | A | A | NA | A | A | A
DD60+18 | 0 | 5DD60+18 | 0 | DD60+18 | 0 | 5DD60+18 | 6 | DD60+18 | 0 | 5DD60+18 | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A | NA | NA | NA | NA | NA | NA
0 | [5 empty] | 5DD60+18(1.5M RC) | 1 | 0 |  | 5DD60+18(1.5M RC) | 1 | Not Approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA
DD60+25 | 0 | 5DD60+25 | 0 | DD60+25 | 2 | 5DD60+25 | 2 | DD60+25 | 2 | 5DD60+25 | 2 |  | NA | A | NA | A | A | NA | NA | A | NA | NA | NA | NA | NA | NA
DD60+30 | 0 | 5DD60+30 | 0 | DD60+30 | 0 | 5DD60+30 | 2 | DD60+30 | 0 | 5DD60+30 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA
0 |  |  |  | 0 |  | DDH | 2 | 0 | 0 | DDH | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA
| 173 |  | 47 |  | 152 |  | 247 |  | 325 |  | 294 | 619
| 220 |  |  |  | 399

## Earthing S-P (hidden)
KEC International Limited
400 KV D/C (Quad) Siwani-Patran TL
Details of Earthing
TFR
CUMM. SR.NO | MONTH SR.NO. | Loc. No. | Type of Tower | Type of Classification | Start | Complete | Type of Earthing | Before Earthing Value | After Earthing Value | Remarks
1 | 1 | 29/1 | DA+0 | Sandy | 2025-08-11 | 2025-08-11 | Pipe type | 1.33 | 0.99
2 | 2 | 28/2 | DA+3 | Sandy | 2025-08-11 | 2025-08-11 | Pipe type | 1.31 | 0.78
3 | 3 | 28/3 | DA+6 | Sandy | 2025-08-11 | 2025-08-11 | Pipe type | 4.07 | 3.44
4 | 4 | 28/4 | DA+3 | WET | 2025-08-11 | 2025-08-11 | Pipe type | 3.35 | 1.79
5 | 5 | 29/4 | DA+6 | Sandy | 2025-08-14 | 2025-08-14 | Pipe type | 1.38 | 0.9
6 | 6 | 29/5 | DA+0 | WET | 2025-08-14 | 2025-08-14 | Pipe type | 1.4 | 1.09
7 | 7 | 30/1 | DA+3 | WET | 2025-08-14 | 2025-08-14 | Pipe type | 1.01 | 0.89
8 | 8 | 29/3 | DA+3 | WET | 2025-08-14 | 2025-08-14 | Pipe type | 1.3 | 1.27

## Crossing status
Crossing Status
Sl. | Line | Description | From | Stub Availability | To | Stub Availability | Name of Crossing | Owner | Approval status | Status |  |  | Remarks
No | [9 empty] | FDN | ERE | STR
Power Line Crossing–26 nos
1 | SP | PL | 2C |  | 2D |  | 132 KV S/C HISAR-RAJGARH TL | HVPNL | In Progress
2 | SP | PL | 35/0(DB1+9) | Yes | 36/0(5DB1+9) | Yes | 132 KV D/C HISAR-FATEHABAD TL HVPNL | HVPNL | Approved |  |  |  | NOC Received on date : 24.12.2025
3 | SP | PL | 38/0(5DD45+18) | No | 39/0(5DC2+9) | Yes | 132 KV S/C KIROR-ADAMPUR TL HVPNL | HVPNL | Approved |  |  |  | NOC Received on date : 24.12.2025
4 | SP | PL | 40/0(5DC1+18) | No | 41/0(5DB2+25) | No | 220 kV D/C MAYAR - FATEHABAD TL HVPNL | HVPNL | Approved |  |  |  | NOC Received on date : 02.04.2026
5 | SP | PL | 49/0(5DD60+30) | No | 50/0(5DD60+30) | No | 400 KV D/C KHEDAR-FATEHABAD TL HVPNL | HVPNL | Approved |  |  |  | NOC Received on date 08.06.2026
6 | SP | PL | 53/0(5DC2+18) | NO | 54/0(5DD45+25) | No | 220 KV D/C KIRMARA-BHUNA TL HVPNL | HVPNL | Approved |  |  |  | NOC Received on date : 23.12.2025
7 | SP | PL | 57/0(5DD60+18) | No | 58/0(5DD60+18) | No | 400 KV D/C MOGA-HISAR TL | PGCIL | In Progress
8 | SP | PL | 59/0(5DB1+9) | YES | 60/0(5DB2+18) | No | 220kV S/C BHUNA NARWANA TL | HVPNL | Approved |  |  |  | NOC Received on date : 24.12.2025
9 | SP | PL | 60/0(5DB2+9) | No | 61/0(5DB1+9) | Yes | 132kV S/C BHUDDHA KHEDA -BHUNA TL | HVPNL | Approved |  |  |  | NOC Received on date : 24.12.2025
10 | SP | PL | 63/0(5DD60+18) | No | 64/0((5DD60+18)) | No | 400kV D/C PGCIL MOGA-BHIWADI TL | PGCIL | In Progress
11 | SP | PL | 73/1(DDH) | No | 73/2(DDH) | No | 765kV S/C line BHIWANI - MOGA TL | PGCIL | In Progress
12 | SP | PL | 75/0(5DB1+18) | No | 76/0(5DB+18) | No | 132 KV D/C SAMANA-CHANDER KHURD TL | HVPNL | Approved |  |  |  | NOC Received on date : 23.12.2025
13 | SP | PL | 82/0(5DB+9)1M | No | 83/0(5DB1+18) | No | 132kV D/C SAMANA-TOHANA TL | HVPNL | Approved |  |  |  | NOC Received on date : 23.12.2025
14 | SP | PL | 84/0(5DC1+18) | No | 85/0(5DD60+18) | No | 220kV D/C HISAR- SANGAPUR TL | BBMB | Approved
15 | SP | PL | 88/0(5DD60+9) | Yes | 89/0(5DB2+9) | Yes | 132kV D/C TOHANA DAMTAL SAHIB TL | HVPNL | Approved |  |  |  | NOC Received on date : 23.12.2025
16 | SP | PL | 91/0(5DB2+18) | No | 92/0(5DD45+9) | No | 132kV S/C NARWANA -TOHANA TL | HVPNL | Approved |  |  |  | NOC Received on date : 23.12.2025
17 | SP | PL | 96/0(5DC2+6) | Yes | 97/0(5DB2+6) | Yes | 66kV S/C MANDVI - KARODA PSTCL line | PSTCL | Approved |  |  |  | NOC Received on date : 11.12.2025
18 | SP | PL | 101/0(5DB1+6) | Yes | 102/0(5DB1+6) | Yes | 66kV D/C BANGA-BANARASI PSTCL line | PSTCL | Approved |  |  |  | NOC Received on date : 11.12.2025
19 | SP | PL | 108/0(5DD60+25) | No | 109/0(5DD60+25) | No | 400 KV DC PATRAN-Kaithal TL | PGCIL | In Progress
20 | SP | PL | 110/0(5DB2+9) | YES | 111/0(5DD45+3) | No | 66kV S/C PATRAN-SHERGARH PSTCL line | PSTCL | Approved |  |  |  | NOC Received on date : 11.12.2025
21 | SP | PL | 110/0(5DB2+9) | YES | 111/0(5DD45+3) | No | Circuit 1-66kV D/C PATRAN TO KHANOURI PSTCL line Circuit 2 -66K/C PATRAN TO SHUTRANA PSTCL Line | PSTCL | Approved |  |  |  | NOC Received on date : 11.12.2025
22 | SP | PL | 120/0(5DD60+25) | No | 121/0(5DD60+18) | No | 400 KV D/C PATIALA -PATRAN TL | PGCIL | In Progress
23 | SF | PL | 51/0(5DD45+18) | No | 52/0(5DD45+18) | No | 220 KV D/C HISAR -FATEHABAD TL | HVPNL | Approved |  |  |  | NOC Received on date : 16.01.2025
24 | SF | PL | 53/0(5DD45+18) | No | 54/0(5DD60+9) | Yes | 132 KV D/C TL HISAR-FATEHABAD TL | HVPNL | Approved |  |  |  | NOC Received on date : 24.12.2025
25 | SF | PL | 29/0(DB2+18) | Yes | 30/0(DC1+6) | Yes | 132 KV S/C KIRORI-Adampur TL HVPNL | HVPNL | Approved | 30/0-compl |  |  | NOC Received on date : 24.12.2025
26 | SF | PL | 2C |  | 2D |  | 132 KV S/C HISAR-RAJGARH TL | RVPNL | In Progress
NH Crossing-08 nos
1 | SP | NH | 2/0 |  | 2A/0 |  | NH529( HISAR -RAJGARH ) | NHAI | In Progress
2 | SP | NH | 33/0(DD60+0 | No | 34/0(DD60+3) | No | NH-9 (SIRSA -ROHTAK ) | NHAI | Approved
3 | SP | NH | 112/0(5DD45+0) | No | 113/0(DB2+0) | Yes | NH-52 (PATRAN-HISAR) | NHAI | Approved |  |  |  | NOC Received on date 09.05.2026
4 | SP | NH | 116/0(5DC+3) | Yes | 117/0(5DD45+3 | No | DELHI -AMRITSAR NE5 EXPRESS WAY | NHAI | Approved |  |  |  | NOC Received on date 30.03.2026
5 | SP | NH | 80/0(5DC2+0) | Yes | 81/0(5DC1+3) | Yes | NH-148B Moonak -Surewala | NHAI | Approved |  |  |  | NOC Received on date 28.11.2025
6 | SF | NH | 42/0(5DD45+0) | No | 43/0(6DD60+3) | Yes | NH-9 (SIRSA-ROHTAK ) | NHAI | Approved
7 | SF | NH | 62/0(5DD45+5) | No | 63/0(5DC2+0) | No | NH-9 (SIRSA-ROHTAK ) | NHAI | Approved
8 | SF | NH | 1A |  | 1B |  | NH52( SIWANI -RAJGARH ) | NHAI | In Progress
SH Crossing-3 nos
1 | SP | SH | 61/2 |  | 62/0 |  | SH-02 Fatehabad To okhlana | PWD | Approved |  |  |  | NOC Received on date 28.11.2025
2 | SP | SH | 44/0 |  | 44/1 |  | SH-10 (BARWALA-AGROHA ROAD | PWD | Approved |  |  |  | NOC Received on date 06.08.2025
3 | SF | SH | 32A/0 |  | 32B/0 |  | SH10 (BARWALA-ADAMPUR ) | PWD | Approved |  |  |  | NOC Received on date 11.08.2025
Railway Crossing-06 nos
1 | SP | RL | 2A |  | 2B |  | (Sadulpur -Siwani) Single Electrified Railway track | Northern Railway | In Progress
2 | SP | RL | 27/0 |  | 28/0 |  | ( Hisar-Bhatinda ) Single Electrified Track | North Western Railway | In Progress
3 | SP | RL | 70/0 |  | 71/0 |  | (Bhatinda-Hansi) Single Electrified Railway Track | Northern Railway | In Progress
4 | SP | RL | 87/0 |  | 88/0 |  | (Tohana-Narwana) Double Track Electrified | Northern Railway | In Progress
5 | SF | RL | 22/0(DD60+9) | Yes | 23/0(DD60+9) | Yes | (Hisar-Bhatinda ) Single Electrified Track | North Western Railway | Approved |  |  |  | NOC Received on date 13.06.2026
6 | SF | RL | 1B |  | 2/0 |  | (Sadulpur -Siwani) Single Electrified Railway track | North Western Railway | In Progress
Pipe lIne-03
1 | SP | Pipe line | 15A/0 |  | 15B/0 |  | ROHTAK -PANIPAT PIPELINE | GSPL | In Progress
2 | SP | Pipe line | 55/1 | Yes | 55/2 | Yes | HPCL (RAMANMANDI-BAHADURGARH ) PIPE LINE | HPCL | Approved | 55/1-Compl 55/2-Compl | 55/1-Compl |  | Approved on Date 02-04-2026
3 | SF | Pipe line | 10/2 |  | 10/3 |  | GSPL INDIA GASNET LIMITED 18''HIGH PRESSURE LPG PIPE LINE & OFC ROHTAK - PANIPAT | GSPL | In Progress
3/3
3/4
3/5
3/6
3/7
3/8
3/9

## Earthing S-F (hidden)
KEC International Limited
400 KV D/C (Quad) Siwani-Fatehabad TL
Details of Earthing
TFR
CUMM. SR.NO | MONTH SR.NO. | Loc. No. | Type of Tower | Type of Classification | Type of Earthing | Start | Complete | Before Earthing Value | After Earthing Value | Remarks
1 | 1 | 24/2 | DA+0 | WET | Pipe Type | 2025-08-05 | 2025-08-05 | 1.56 | 1.39
2 | 2 | 24/3 | DA+0 | Sandy | Pipe Type | 2025-08-04 | 2025-08-04 | 2.73 | 2.4
3 | 3 | 24/4 | DA+1.5 | Sandy | Pipe Type | 2025-08-05 | 2025-08-05 | 0.94 | 0.85
4 | 4 | 25/1 | DA+1.5 | WET | Pipe Type | 2025-08-06 | 2025-08-06 | 1.76 | 1.68
5 | 5 | 25/2 | DA+0 | WET | Pipe Type | 2025-08-06 | 2025-08-06 | 2.24 | 2.01
6 | 6 | 23/6 | DA-1.5 | WET | Pipe Type | 2025-08-07 | 2025-08-07 | 2.79 | 2.57
7 | 7 | 23/5 | DA+6 | WET | Pipe Type | 2025-08-07 | 2025-08-07 | 2.13 | 1.97
8 | 8 | 24/1 | DA+0 | WET | Pipe Type | 2025-08-07 | 2025-08-07 | 1.77 | 1.68
9 | 9 | 26/2 | DA+6 | WET | Pipe Type | 2025-08-08 | 2025-08-08 | 3.14 | 2.44
10 | 10 | 31/1 | DA+0 | WET | Pipe Type | 2025-08-08 | 2025-08-08 | 1.84 | 1.58
Formulas:
Complete = [Start]

## Proposal .
Client : PowerGrid Bikaner IV Transmission Limited.
KEC International Limited
Name of Line: 400 KV D/C Siwani To Fatehabad + 400 KV D/C Siwani To Patran TL
Summary of crossing Details
Sl.No | Crossing | Line | Total Nos | Proposal Submitted | Balance Submission' | NOC Received | Remarks
1 | PL | Siwani-Patran | 22 | 22 | 0 | 16 | [17 empty] | LINE | PL Crossing(Nos) |  | Submitted | Crossing Authority
|  | Siwani-Fatehabad | 4 | 4 | 0 | 3 | [8 empty] | Description | Total Crossing |  |  | Submitted |  |  | Balance To Submit | Concern Authority |  | SP | SF
2 | NH | Siwani-Patran | 5 | 5 | 0 | 4 |  |  |  |  | Description | Crossing |  | Authority |  | SF | SP | Total | SF | SP | Total |  |  | 132KV | 8 | 3 | 9 | HVPNL
|  | Siwani-Fatehabad | 3 | 3 | 0 | 2 | [5 empty] | SF | SP |  | 66 kv | 0 | 4 | 4 | 0 | 4 | 4 | 0 | PSTCL | 220KV | 4 | 1 | 5 | HVPNL
3 | SH | Siwani-Patran | 2 | 2 | 0 | 2 |  |  |  |  | 66 KV |  | 4 | PSTCL | 132 kv | 3 | 8 | 11 | 2 | 7 | 9 | 2 | HVPNL | 400KV | 5 | 0 | 3 | HVPNL, 4 No's PGCIL
|  | Siwani-Fatehabad | 1 | 1 | 0 | 1 |  |  |  |  | 132 KV | 3 | 8 | HVPNL | 220 kv | 1 | 4 | 5 | 1 | 4 | 5 | 0 | HVPNL | 66KV | 4 | 0 | 4 | PSTCL
4 | RL | Siwani-Patran | 4 | 4 | 0 | 1 |  |  |  |  | 220 KV | 1 | 4 | 4 Nos HVPNL , 1 Nos BBMB | 400 kv | 0 | 5 | 5 | 0 | 3 | 3 | 2 | 4 PGCIL ,1 HVPNL | 765KV | 1 | 0 | 0 | PGCIL
|  | Siwani-Fatehabad | 2 | 2 | 0 | 0 |  |  |  |  | 400 KV |  | 5 | 1 HVPNL , 4 PGCIL | 765KV | 0 | 1 | 1 | 0 | 0 | 0 | 1 | PGCIL |  | 22 | 4 | 21
5 | Canal | Siwani-Patran | 32 | 32 | 0 | 0 |  |  |  |  | 765 KV |  | 1 | PGCIL |  | 4 | 22 | 26 | 3 | 18 | 21 | 5
|  | Siwani-Fatehabad | 16 | 16 | 0 | 0 | [5 empty] | 4 | 22
6 | Gas pipe line | Siwani-Patran | 2 | 2 | 0 | 1
|  | Siwani-Fatehabad | 1 | 1 | 0 | 0
7 | PTCC | Siwani-Patran | 1 | 1 | 0 | 0 | Submit to PGCIL on date 10.05.2026
|  | Siwani-Fatehabad | 1 | 1 | 0 | 0
8 | Civil Aviation | Siwani-Patran | 1 | 1 | 0 | 0 | Online Portal uploading Under progress
|  | Siwani-Fatehabad | 1 | 1 | 0 | 0 | Upload on Portal on date 25-05-2026
9 | Defence Aviation | Siwani-Patran | 1 |  | 1 | 0
|  | Siwani-Fatehabad | 1 |  | 1
Total |  |  | 100 | 98 | 2 | 30
Sl.No | Line Name | Type of crossing | Description of Crossing |  |  |  |  | Crossing Authority | KEC Letter | Status
|  |  | Loc from | Type of Tower | Loc To | Type of Tower | Details
1 | Siwani-Patran | PL Xing | 2C | DD45+9 | 2D | DD60+9 | 132 KV S/C HISAR-RAJGARH TL | RVPNL |  | Proposal Submit to PGCIL on date 16.01.2026
2 | Siwani-Patran | PL Xing | 35/0 | DB1+9 | 36/0 | 5DB1+9 | 132 KV D/C HISAR-FATEHABAD TL HVPNL | HVPNL | 113 ,176 | Submit to PGCIL on date : 26-07-2025 Site Visit Done on Date : 21.08.2025 File Returm : Extra Clearance Required Proposal Resubmit on date 29.11.2025 ,as HVPNL requested the profile of their existing line span NOC received on 24.12.2025
3 | Siwani-Patran | PL Xing | 38/0 | 5DD45+18 | 39/0 | 5DC2+9 | 132 KV S/C KIROR-ADAMPUR TL HVPNL | HVPNL | 113 ,181 | Submit to PGCIL on date : 26-07-2025 Site Visit Done on Date : 21.08.2025 Presently file with Executive Engineer Revisit done on date : 16.10.2025 The proposal resubmitted on 03.12.2025, as HVPNL requested the profile of their existing line span,, NOC received on 24.12.2025
4 | Siwani-Patran | PL Xing | 40/0 | 5DB2+9 | 41/0 | 5DB2+18 | 220 kV D/C MAYAR - FATEHABAD TL HVPNL | HVPNL | 113 , 181 | Submit to PGCIL on date : 26-07-2025 Site Visit Done on Date : 21.08.2025 On date-19.09.2025 , File send to SE office from AE The proposal resubmitted on 04.12.2025, as HVPNL requested the profile of their existing line span NOC Received on date 02.04.2026
5 | Siwani-Patran | PL Xing | 49/0 | 5DD60+25 | 50/0 | 5DD60+25 | 400 KV D/C KHEDAR-FATEHABAD TL HVPNL | HVPNL | 126 | Submit to PGCIL on date : 30-08-2025 Proposal Resubmit on date 29.11.2025 ,as HVPNL requested the profile of their existing line span Proposal resubmit with compliance on dated 05.01.2025. Again Compliance Submit on date 27.01.2026 NOC Recievedon date 08.06.2026
6 | Siwani-Patran | PL Xing | 53/0 | 5DC1+18 | 54/0 | 5DD45+25 | 220 KV D/C KIRMARA-BHUNA TL HVPNL | HVPNL | 119 , 179 | Submit to PGCIL on date : 31-07-2025 Hard Copy Submit on Date : 13-08-2025 Site visit done on date : 02.09.2025 After Proposal verification on date 05.09.2025 , Letter send to SE From AE Proposal Re- Submit on date-04.12.2025 (Submit with Compliance) , NOC received on 23.12.2025
7 | Siwani-Patran | PL Xing | 57/0 | 5DD60+25 | 58/0 | 5DD60+25 | 400 KV D/C MOGA-HISAR TL | PGCIL | 119 | Submit to PGCIL on date : 31-07-2025 Hard Copy Submit on Date : 13-08-2025 Site Visit done on date : 07.10.2025 Proposal compliance -Diamond Crossing arrangement submitted to PGCIL on date 30.12.2025 Re-Site visit done on date 26-05-2026
8 | Siwani-Patran | PL Xing | 59/0 | 5DB1+9 | 60/0 | 5DB1+18 | 220kV S/C BHUNA NARWANA TL | HVPNL | 117 | Submit to PGCIL on date : 26-07-2025 Hard Copy Submitted on Date-13-08-2025 File Return : Extra Clearance Required as per HVPNL Revisit done on date : 16.10.2025 Proposal Resubmit on date 29.11.2025 ,as HVPNL requested the profile of their existing line span,, NOC received on 24.12.2025
9 | Siwani-Patran | PL Xing | 60/0 | 5DB1+18 | 61/0 | 5DB1+3 | 132kV S/C BHUDDHA KHEDA -BHUNA TL | HVPNL | 117 | Submit to PGCIL on date : 31-07-2025 Hard Copy Submit on Date : 13-08-2025 Site visit done on date : 02.09.2025 On date : 05.09.2025 , Proposal after verification sent to SE From AE Proposal Resubmit on date 29.11.2025 ,as HVPNL requested the profile of their existing line span,, NOC received on 24.12.2025
10 | Siwani-Patran | PL Xing | 63/0 | 5DD60+25 | 64/0 | 5DD60+25 | 400kV D/C PGCIL MOGA-BHIWADI TL | PGCIL | 117 | Submit to PGCIL on date : 26-07-2025 Hard Copy Submitted on Date-13-08-2025 Site Visit done on date : 07.10.2025 Proposal compliance -Diamond Crossing arrangement submitted to PGCIL on date 30.12.2025 Re-Site visit done on date 26-05-2026
11 | Siwani-Patran | PL Xing | 73/1 | DDH | 73/2 | DDH | 765kV S/C line BHIWANI - MOGA TL | PGCIL | 147 | Submit to PGCIL on date 09.10.2025 Compliance Submit on date 03.01.2025
12 | Siwani-Patran | PL Xing | 75/0 | 5DB1+18 | 76/0 | 5DB2+18 | 132 KV D/C SAMANA-CHANDER KHURD TL | HVPNL | 119 , 179 | Submit to PGCIL on date : 31-07-2025 Hard Copy Submit on Date : 13-08-2025 Site visit done on date : 02.09.2025 On date : 05.09.2025 , Proposal after verification sent to SE From AE Proposal Re- Submit on date-04.12.2025 (Submit with Compliance) ,, NOC recieved on 23.12.2025
13 | Siwani-Patran | PL Xing | 82/0 | 5DB2+9 | 83/0 | 5DB1+18 | 132kV D/C SAMANA-TOHANA TL | HVPNL | 119 , 179 | Submit to PGCIL on date : 31-07-2025 Hard Copy Submit on Date : 13-08-2025 Site visit done on date : 02.09.2025 On date : 05.09.2025 , Proposal after verification sent to SE From AE Observation by HVPNL regarding rasing Height of conductor Proposal Re- Submit on date-04.12.2025 (Submit with Compliance) ,, NOC recieved on 23.12.2025
14 | Siwani-Patran | PL Xing | 84/0 | 5DC1+18 | 85/0 | 5DD60+18 | 220kV D/C HISAR- SANGAPUR TL | BBMB | 119 | Submit to PGCIL on date : 31-07-2025 Hard Copy Submit on Date : 13-08-2025 Submit to concern authority on date 08.10.2025 Joint inspection done on date 29.10.2025 Proposal Submit to BBMB office on date 28.11.2025 NOC Received on date 30.12.2025
15 | Siwani-Patran | PL Xing | 88/0 | 5DD60+9 | 89/0 | 5DB2+9 | 132kV D/C TOHANA DAMTAL SAHIB TL | HVPNL | 119 , 179 | Submit to PGCIL on date : 31-07-2025 Hard Copy Submit on Date : 13-08-2025 File Return : Extra clearance required as per HVPNL Proposal Re- Submit on date-04.12.2025 (Submit with Compliance) ,, NOC recieved on 23.12.2025
16 | Siwani-Patran | PL Xing | 91/0 | 5DB1+18 | 92/0 | 5DD45+9 | 132kV S/C NARWANA -TOHANA TL | HVPNL | 119 , 179 | Submit to PGCIL on date : 31-07-2025 Hard Copy Submit on Date : 13-08-2025 Proposal Re- Submit on date-04.12.2025 (Submit with Compliance) ,, NOC recieved on 23.12.2025
17 | Siwani-Patran | PL Xing | 96/0 | 5DC2+6 | 97/0 | 5DB2+6 | 66kV S/C MANDVI - KARODA PSTCL line | PSTCL | 119164 | Submit to PGCIL on date : 31-07-2025 Hard Copy Submit on Date : 13-08-2025 Submit to concern authority -13.10.2025 Site visit done on date : 28.10.2025 Compliance Submit on date : 31.10.2025 Proposal are with SE PSTCL, NOC Received On date =10.12.2025
18 | Siwani-Patran | PL Xing | 101/0 | 5DB1+6 | 102/0 | 5DB1+6 | 66kV D/C BANGA-BANARASI PSTCL line | PSTCL | 164 | Submit to PGCIL on date : 11.08.2025 Submit to Concern authority-13.10.2025 Compliance submit on date 31.10.2025 Proposal are with SE PSTCL,NOC Received On date =10.12.2025
19 | Siwani-Patran | PL Xing | 108/0 | 5DD60+25 | 109/0 | 5DD60+30 | 400 KV DC PATRAN-Kaithal TL | PGCIL | 151 | Submit to PGCIL on date : 11.08.2025 Proposal compliance -Diamond Crossing arrangement submitted to PGCIL on date 30.12.2025
20 | Siwani-Patran | PL Xing | 110/0 | 5DB2+9 | 111/0 | 5DD45+3 | 66kV S/C PATRAN-SHERGARH PSTCL line | PSTCL | 164 | Submit to PGCIL on date : 11.08.2025 Submit to Concern authority-13.10.2025 Compliance submit on date 31.10.2025 Proposal are with SE PSTCL,NOC Received On date =10.12.2025
21 | Siwani-Patran | PL Xing | 110/0 | 5DB2+9 | 111/0 | 5DD45+3 | Circuit 1-66kV D/C PATRAN TO KHANOURI PSTCL line Circuit 2 -66K/C PATRAN TO SHUTRANA PSTCL Line | PSTCL | 164 | Submit to PGCIL on date : 11.08.2025 Submit to Concern authority-13.10.2025 Compliance submit on date 31.10.2025 Proposal are with SE PSTCL,NOC Received On date =10.12.2025
22 | Siwani-Patran | PL Xing | 120/0 | 5DD60+25 | 121/0 | 5DD60+18 | 400 KV D/C PATIALA -PATRAN TL | PGCIL | 152 | Submit to PGCIL on date : 17.10.2025 Diamond Proposal demand Diamond Proposal (Preparation U/P)
23 | Siwani-Fatehabad | PL Xing | 51/0 | 5DD45+18 | 52/0 | 5DD45+9 | 220 KV D/C HISAR -FATEHABAD TL | HVPNL | 180 | Submit by mail on date : 23-07-2025. Hard Copy submit on date-26-07-2025 Site Visit done on date -21.08.2025 On date-19.09.2025 , File send to SE office from AE The proposal resubmitted on 04.12.2025, as HVPNL requested the profile of their existing line span Proposal submit to SE Hisar on 29.12.2025 which forwarded to SE Panchkula on 31.12.2025 NOC Recieved on date 16.01.2026
24 | Siwani-Fatehabad | PL Xing | 53/0 | 5DD45+18 | 54/0 | 5DD60+9 | 132 KV D/C TL HISAR-FATEHABAD TL | HVPNL | 180 | Submit by mail on date : 23-07-2025. Hard Copy submit on date-26-07-2025 Site Visit done on date -21.08.2025 On date-19.09.2025 , File send to SE office from AE The proposal resubmitted on 04.12.2025, as HVPNL requested the profile of their existing line span NOC Recieved
25 | Siwani-Fatehabad | PL Xing | 29/0 | DB2+18 | 30/0 | DC1+6 | 132 KV S/C KIRORI-Adampur TL HVPNL | HVPNL | 180 | Submit by mail on date : 23-07-2025. Hard Copy submit on date-26-07-2025 Site Visit done on date -21.08.2025 On date-19.09.2025 , File send to SE office from AE The proposal resubmitted on 04.12.2025, as HVPNL requested the profile of their existing line span,, NOC received on 24.12.2025
26 | Siwani-Fatehabad | PL Xing | 2C | DD60+6 | 2D | DD60+6 | 132 KV S/C HISAR-RAJGARH TL | RVPNL | 180 | The proposal submitted on 04.12.2025
Road Crossing
1 | Siwani-Patran | Highway Xing | 2/0 | DD60 | 2A/0 | DD60 | NH529( HISAR -RAJGARH ) | NHAI |  | Proposal submit to PGCIL on date 29.01.2026
2 | Siwani-Patran | Highway Xing | 33/0 | DD60+0 | 34/0 | DD60+3 | NH-9 (SIRSA -ROHTAK ) | NHAI | 99A | Submit to PGCIL On date : 10.07.2025 Submitted to Concern authority on date : 23-07-2025 Site Visit done 20.08.2025 On Dated:11.09.2025 , ProposaL return as there is some point need to be compliances Compliance Submit on date 30.09.2025 File send To RO Chandigarh NOC Recieved
3 | Siwani-Patran | Highway Xing | 112/0 | 5DD45+0 | 113/0 | 5DB2+0 | NH-52 (PATRAN-HISAR) | NHAI | 99 | Submitted To PGCIL on dated : 09.07.2025 Site Visit done on 26.08.2025 Proposal is with PIU Chandigarh, Demand Letter in the form of BG is received from PIU Chd. E Ofc Note initiated on 30.12.2025 NOC Received on date-09.05.2026] NOC Received
4 | Siwani-Patran | Highway Xing | 116/0 | 5DC1+0 | 117/0 | 5DD45+0 | DELHI -AMRITSAR NE5 EXPRESS WAY | NHAI | 99 | Submitted To PGCIL on dated : 09.07.2025 Site visit done on date : 18.09.2025 File is with PIU Bhiwani Invitation of Public Comment Issued-31.12.2025 NOC Received on date 30.03.2026
5 | Siwani-Patran | Highway Xing | 80/0 | 5DC2+0 | 81/0 | 5DC1+3 | NH-148B Moonak -Surewala | NHAI | 99 | Submitted To PGCIL on dated : 09.07.2025 NOC Received on date : 28.11.2025
6 | Siwani-Fatehabad | Highway Xing | 42/0 | 5DD45+0 | 43/0 | 5DD60+3 | NH-9 (SIRSA-ROHTAK ) | NHAI |  | Submitted To PGCIL ON Dated : 08.07.2025 Site Visit done on date : 01.08.2025 Presently case at RO, Chandigarh On Dated:11.09.2025 , ProposaL return as there is some point need to be compliances Compliance Submit on date 30.09.2025 File send to RO Chandigarh NOC Recieved
7 | Siwani-Fatehabad | Highway Xing | 62/0 | 5DD45+3 | 63/0 | 5DC2+0 | NH-9 (SIRSA-ROHTAK ) | NHAI |  | Submitted To PGCIL ON Dated : 08.07.2025 Site Visit done on date : 01.08.2025 Presently case at RO, Chandigarh On Dated:11.09.2025 , ProposaL return as there is some point need to be compliances Compliance Submit on date 30.09.2025 File send to RO Chandigarh
8 | Siwani-Fatehabad | Highway Xing | 1A | DD60 | 1B | DD60 | NH52( SIWANI -RAJGARH ) | NHAI |  | Proposal Submit to PGCIL on date 08.12.2025 Submit on portal on date 12.01.2026
10 | Siwani-Patran | SH Xing | 61/2 | 5DD45+0 | 62/0 | 5DD60+0 | SH-02 Fatehabad To okhlana | PWD | 95 | Submitted to PGCIL on dated 28.06.2025 NOC Received on date : 28.11.2025
11 | Siwani-Patran | SH Xing | 44/0 | 5DD45+0 | 44/1 | 5DA+0 | SH-10 (BARWALA-AGROHA ROAD | PWD |  | Submitted to PGCIL on dated 21.06.2025 NOC Received on Date : 06.08.2025
14 | Siwani-Fatehabad | SH Xing | 32A/0 | DB2+3 | 32B/0 | DB2+0 | SH10 (BARWALA-ADAMPUR ) | PWD |  | Submitted to PGCIL on dated : 21.06.2025 NOC Received on Date: 11.08.2025
Utlility Crossing
1 | Siwani-Patran | Gas Pipe line | 15A/0 | DC2+6 | 15B/0 | DC1+9 | ROHTAK -PANIPAT PIPELINE | GSPL | 136 | Submitted on date 10.09.2025 Site visit done on date 13.10.2025 Letter submitted to GSPL on 02.01.2026 for consideration of processing fee, BG Submmission for further issuance of NOC. (Insurance shall be submitted later on start of work)
2 | Siwani-Patran | Gas Pipe line | 55/1 | 5DA+9 | 55/2 | 5DA+3 | HPCL (RAMANMANDI-BAHADURGARH ) PIPE LINE | HPCL | 136 | Submitted on date 15.10.2025. NOC Received on Date 02.04.2026
3 | Siwani-Fatehabad | Gas Pipe line | 10/2 | DA+0 | 10/3 | DA+3 | GSPL INDIA GASNET LIMITED 18''HIGH PRESSURE LPG PIPE LINE & OFC ROHTAK - PANIPAT | GSPL | 136 | Submitted on date 10.09.2025 Site visit done on date 13.10.2025 Letter submitted to GSPL on 02.01.2026 for consideration of NOC. (processing fee, BG Submmission has proposed yet. (Insurance shall be submit later on start of work
Railway Crossing
1 | Siwani-Patran | RL Xing | 70/0 | 5DD60+6 | 71/0 | 5DD60+6 | (Bhatinda-Hansi) Single Electrified Railway Track | Northern Railway | 168 | Submit on Date-11.08.2025 Hard copy submitted to PGCIL after document verification by PGCIL on date 31.10.2025 Submit on online Portal on date 31.10.2025 Site Visit done on date 11.11.2025 File wiith Div.Electrical engineer(G).
2 | Siwani-Patran | RL Xing | 2/0 | DD60 | 2B | DD60 | (Sadulpur -Siwani) Single Electrified Railway track | North Western Railway |  | Proposal submit to PGCIL on date 16.01.2026 Site Visit done on date : 17.04.2026
3 | Siwani-Patran | RL Xing | 27/0 | DD60+6 | 28/0 | DD60+6 | ( Hisar-Bhatinda ) Single Electrified Track | North Western Railway | By Mail | Submit on Date-08.08.2025(ROW)
4 | Siwani-Patran | RL Xing | 87/0 | 5DD60+9 | 88/0 | 5DD60+9 | (Tohana-Narwana) Double Track Electrified | Northern Railway | 168 | Submit on Date-11.08.2025 Hard copy submitted to PGCIL after document verification by PGCIL on date 31.10.2025 Submit on online Portal on date 31.10.2025, Joint Visit done on 13.11.2025, File submit to Delhi officeon date 03.01.2025
5 | Siwani-Fatehabad | RL Xing | 22/0 | DD60+9 | 23/0 | DD60+6 | (Hisar-Bhatinda ) Single Electrified Track | North Western Railway | By Mail | Submit on Date-06.08.2025 Online Submit on Portal on Date : 12-08-2025 Online Submit Observation 13-08-2025 Compliance Submitted by KEC. site visit done on date : 17.11.2025 File sign by ADEN And to be submitted to Bikaner Office On date 22.12.2025 Compliance submit By KEC in bikaner Railway office. NOC Recieved on date 12-06-2026
6 | Siwani-Fatehabad | RL Xing | 1B | DD60 | 2/0 | DD60 | (Sadulpur -Siwani) Single Electrified Railway track | North Western Railway | By Mail | Submit by mail on date :: 10.11.2025 Proposal Submit online on date 05.01.2025 Proposal resubmit on date 05.02.2025 for compliance. Revised SLD submit on date 25.02.2025 Query raised by railway regarding the correction of name on date 24.04.2026 . Same Compliance by KEC on date 25.04.2026
CANAL
1 | Siwani-Patran | Canal | 7/1 | DA+3 | 8/0 | DB1+0 | Devsar Fedder | Irrigation Dept. | 120 | Submit on 11.08.2025 , Demand Draft Submitted .
2 | Siwani-Patran | Canal | 8/5 | DA+6 | 9/0 | DC2+3 | Devsar Fedder | Irrigation Dept. | 120
3 | Siwani-Patran | Canal | 10/1 | DA+6 | 10/2 | DA+0 | Devsar Fedder | Irrigation Dept. | 120
4 | Siwani-Patran | Canal | 11/0 | DB1+3 | 12/0 | DB2+0 | Gawar Minor | Irrigation Dept. | 120
5 | Siwani-Patran | Canal | 15B/1 | DA+0 | 15B/2 | DA+3 | Rawalvas Minor | Irrigation Dept. | 120
6 | Siwani-Patran | Canal | 17/3 | DA+3 | 19/0 | DC2+9 | Sarsana canal | Irrigation Dept. | 120
7 | Siwani-Patran | Canal | 21/4 | DA+0 | 21/5 | DA+3 | Chodhari minor | Irrigation Dept. | 120
8 | Siwani-Patran | Canal | 23/0 | DB1-3 | 23/1 | DA-1.5 | Kabir Minor | Irrigation Dept. | 120
9 | Siwani-Patran | Canal | 24/0 | DB2+3 | 24/1 | DA+9 | HisarDistributory | Irrigation Dept. | 120
10 | Siwani-Patran | Canal | 26/0 | DB2+0 | 26/1 | DA+0 | Rana minor | Irrigation Dept. | 120
11 | Siwani-Patran | Canal | 29/1 | DA+0 | 29/2 | DA+9 | Nyoli minor | Irrigation Dept. | 120
12 | Siwani-Patran | Canal | 46/0 | 5DD45+6 | 46/1 | 5DA+6 | Pabra minor canal | Irrigation Dept. | 120
13 | Siwani-Patran | Canal | 47/0 | 5DC1+3 | 47/1 | 5DA+9 | Kuleri minor canal | Irrigation Dept. | 120
14 | Siwani-Patran | Canal | 50/1 | 5DA+0 | 50/2 | 5DA+6 | Pabra Distributory canal | Irrigation Dept. | 120
15 | Siwani-Patran | Canal | 51/1 | 5DA+3 | 51/2 | 5DA+3 | Pabra Distributory Branch | Irrigation Dept. | 120
16 | Siwani-Patran | Canal | 58/3 | 5DA-3 | 58/4 | 5DA+0 | Gorakhpur distributory | Irrigation Dept. | 120
17 | Siwani-Patran | Canal | 61/0 | 5DB1+3 | 61/1 | 5DA+6 | Fatehabad Branch | Irrigation Dept. | 120
18 | Siwani-Patran | Canal | 61/0 | 5DB1+3 | 61/1 | 5DA+6 | Sidmukh nahar | Irrigation Dept. | 120
19 | Siwani-Patran | Canal | 65/2 | 5DA+6 | 66/0 | 5DD45+0 | Perthala Distributory canal | Irrigation Dept. | 120
20 | Siwani-Patran | Canal | 68/1 | 5DA+6 | 69/0 | 5DB1+3 | Perthala Distributory canal | Irrigation Dept. | 120
21 | Siwani-Patran | Canal | 69/4 | 5DA+9 | 69/5 | 5DA+6 | Sidmukh nahar | Irrigation Dept. | 120
22 | Siwani-Patran | Canal | 69/4 | 5DA+9 | 69/5 | 5DA+6 | Fatehabad Branch | Irrigation Dept. | 120
23 | Siwani-Patran | Canal | 70/0 | 5DD60+6 | 70/1 | #N/A | Gajuwala Minor | Irrigation Dept. | 120
24 | Siwani-Patran | Canal | 74/5 | 5DA+6 | 74/6 | 5DA+6 | Chitian minor | Irrigation Dept. | 120
25 | Siwani-Patran | Canal | 78/0 | 5DB2+6 | 78/1 | 5DA+9 | Gajuwala Minor | Irrigation Dept. | 120
26 | Siwani-Patran | Canal | 85/0 | 5DD60+18 | 86/0 | 5DC1+3 | Saman Distributory | Irrigation Dept. | 120
27 | Siwani-Patran | Canal | 87/0 | 5DD60+9 | 88/0 | 5DD60+9 | New link channel | Irrigation Dept. | 120
28 | Siwani-Patran | Canal | 92/4 | 5DA+3 | 92/5 | 5DA+3 | Kalwan fedder | Irrigation Dept. | 120
29 | Siwani-Patran | Canal | 92A/0 | 5DB2+9 | 93/0 | 5DC2+6 | Bhakar canal main branch | Irrigation Dept. | 120
30 | Siwani-Patran | Canal | 97/1 | 5DA+3 | 98/0 | 5DB2+9 | Dhanauri Distty | Irrigation Dept. | 120
31 | Siwani-Patran | Canal | 106/4 | 5DA+0 | 106/5 | 5DA-3 | Karam garh Minor | Irrigation Dept. | 120
32 | Siwani-Patran | Canal | 115/0 | 5DB2+0 | 115/1 | 5DA+6 | Karam garh link | Irrigation Dept. | 120
1 | Siwani-Fatehabad | Canal | 3/10 | DA+6 | 4/0 | DB2+3 | Pratamal minor | Irrigation Dept. | 119
2 | Siwani-Fatehabad | Canal | 4/2 | DA+6 | 4/3 | DA+3 | Devsar Fedder | Irrigation Dept. | 119
3 | Siwani-Fatehabad | Canal | 6/10 | DA+0 | 7/0 | DB1+0 | Gawar Minor | Irrigation Dept. | 119
4 | Siwani-Fatehabad | Canal | 14/1 | DA+3 | 15/0 | DC2+0 | Sarsana minor | Irrigation Dept. | 119
5 | Siwani-Fatehabad | Canal | 16/7 | DA+0 | 16/8 | DA+0 | Chodhari minor | Irrigation Dept. | 119
6 | Siwani-Fatehabad | Canal | 18/0 | DB1+0 | 18/1 | DA+0 | Kabir Minor | Irrigation Dept. | 119
7 | Siwani-Fatehabad | Canal | 18/4 | DA-1.5 | 19/0 | DC2+3 | Hisar Distri canal / Hisar Drain | Irrigation Dept. | 119
8 | Siwani-Fatehabad | Canal | 21/0 | DB2+0 | 21/1 | DA+0 | Rana minor | Irrigation Dept. | 119
9 | Siwani-Fatehabad | Canal | 30/0 | DC1+6 | 30/1 | DA+0 | Jakhod Distributary canal | Irrigation Dept. | 119
10 | Siwani-Fatehabad | Canal | 34/1 | DA+6 | 35/0 | DD45+0 | Sidhhmukh Fedder Canal | Irrigation Dept. | 119
11 | Siwani-Fatehabad | Canal | 34/1 | DA+6 | 35/0 | DD45+0 | Kishan garh Sub Branch (Canal ) | Irrigation Dept. | 119
12 | Siwani-Fatehabad | Canal | 39/1 | DA+1.5 | 40/0 | DB2+0 | Khairam pur Distributary Canal | Irrigation Dept. | 119
13 | Siwani-Fatehabad | Canal | 45/0 | 5DC2+9 | 46/0 | 5DD45+9 | Branch Canal | Irrigation Dept. | 119
14 | Siwani-Fatehabad | Canal | 49/1 | 5DA+3 | 49/2 | 5DA+9 | Canal (Gorakh pur River ) | Irrigation Dept. | 119
15 | Siwani-Fatehabad | Canal | 61/0 | 5DC1+6 | 61/1 | 5DA+6 | Fatehabad Branch | Irrigation Dept. | 119
16 | Siwani-Fatehabad | Canal | 63/0 | 5DC2+0 | Dead End |  | Fatehabad Branch | Irrigation Dept. | 119
Avaition
S.NO | Line Name | Authority | Nearest Airport | Nearest Location To Airport | Distance from Airport | Remarks
1 | Siwani-Patran | AAI | Hisar | AP30 | 10.538 KM | 16/0,16/1,17/0,17/1,17/2,17/3,19/0,19/1,19/2,19/3,20/0,20/1,20/2,21/0,21/1,21/2,21/3,21/4,21/5,21/6,21/7,21/8,23/0,23/1,23/2,23/3,23/4,24/0,24/1,24/2,25/0,25/1,25/2,25/3,26/0,26/1,26/2,27/0,28/0,28/1,28/2,28/3,28/4,29/0,29/1,29/2,29/3,29/4,29/5,30/0,30/1,30/2,30/3,30/4,30/5,30/6,30/7,31/0,31/1,31/2,32/0,32/1,32/2,32/3,32/4,33/0,AP34/0,AP35/0,36/0,36/1,36/2,36/3,36/4,36/5,37/0,37/1,38/0,39/0,39/1,39/2,40/0,41/0,42/0,42/1,43/0,44/0,44/1,44/2,45/0,45/1,45/2,46/0,46/1,47/0,47/1,47/2,47/3,47/4,47/5,47/6,48/0
2 | Siwani-Fatehabad | AAI | Hisar | AP23 | 13.4 km | 13/0 ,14/0,14/1,15/0,15/1,15/2,15/3,16/0,16/1,16/2,16/3,16/4,16/5 ,16/6,16/7,16/8,17/0,17/1,17/2,17/3,17/4,17/5,17/6,17/7,18/0,18/1,18/2,18/3,18/4,19/0,19/1,19/3,20/0,21/0,21/1,21/2,21/3,22/0,23/0,23/1,23/2,23/3,23/4,23/5,23/6,24/0,24/1,24/2,24/3,24/4,25/0'25/1,25/2,26/0,26/1,26/2,27/0,28/0,28/1,29/0,30/0,30/1,30/2,31/0,31/1,31/2,32/0,32A/0,32B/0
Forest Proposal Status
Range |  | Block | Siwani-Fatehabad |  | Siwani-Patran
|  |  | Loc NO | Area | Loc NO | Area
Hisar Range |  | Gangwa | AP7-AP8 | 0.028
Hisar Range |  | Gangwa | AP9-AP10 | 0.069 | AP12-14/5 | 0.1012
Adampur/Balsamad Range |  | Adampur | AP11-AP24 | 1.141 | AP15-AP29 | 1.334
Adampur Range |  | Agroha | AP24-AP40 | 0.584 | AP30-AP37 | 0.29
Adampur Range |  | Agroha |  |  | AP36-AP47 | 0.225
Hisar Range |  | Uklana |  |  | AP55-AP56 | 0.055
Adampur Range |  | Pabra |  |  | AP47-AP56 | 0.451
Fatehabad |  |  |  | 0.771 |  | 1.465
Jind | [5 empty] | 0.483
Sangrur | [5 empty] | 0.405
Patiala | [5 empty] | 0.092
Bhiwani |  |  |  | 0.929 |  | 1.4
Total (JVR Compl) |  |  |  | 3.494 |  | 6.3012
Forest Proposal
S.NO | Line | Name of Forest Division' | Total Area (in HA) | Remarks
1 | Siwani-fatehabad TL | Bhiwani | 2.001 | Submit online on Parvesh Portal on date :06.11.2025. After compliance it is again sumbit on portal on date 17.11.2025. Again Compliance Submitted on date 04.01.2025. Site Visit Compl for all district Proposal upload on portal after correction. 10. Case is accepted by DFO Bhiwani on 17.02.2026 and Currently case with Sectratry office
2 |  | Hisar | 1.919
3 |  | Fatehabad | 1.026
|  | Total Area | 4.946
1 | Siwani-Patran TL | Bhiwani | 3.3902 | Proposal Submitted on Portal on date : 06.12.2025. Site Visit compl for all district ,5. Case is accepted by Jind, Fatehabad and Bhiwani DFOs on 28.01.2026, 11.02.2026 and 19.02.2026 respectively. Currently case is with Hisar DFO. Case Return , Compliance Submitted.Currently case with RO officer
2 |  | Hisar | 3.0642
3 |  | Fatehabad | 1.7546
4 |  | Jind | 0.501
5 |  | Patiala | 0.092 | Proposal Submitted on Portal on date : 09.12.2025.8. Case is accepted by Patiala DFO on 16.02.2026. and Currently case with Nodal officer
6 |  | Sangrur | 0.405
|  | Total Area | 9.207

## ROW S-F
ROW Status(Siwani-Fatehabad TL) | [12 empty] | 2026-06-29
S.No | Loc. No. | Tower/Type | Activity | Date of Approach | Date of Resolution | Duration of ROW (Days) | Nature of hindrance | Status of Resolution | Name of Farmer | Father Name | Mobile no. | Vill. Name | Tehsil
1 | 19/1 | DA+3 | Foundation | 2025-04-27 |  | 429 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh Ramkumar | Sh. Tularam | 9416927655/8199991624 | Mattrasham | Hisar | 1
2 | 19/2 | DA-3 | Foundation | 2025-04-27 |  | 429 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh.Amardeep | Sh. Omprakash | 7206313374/9466052316 | Mattrasham | Hisar | 1
3 | 21/1 | DA+0 | Foundation | 2025-04-27 | 2025-07-01 | 429 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh.Bhup Singh Nain |  | 9467874974 | Mattrasham | Hisar | 1
4 | 21/2 | DA-3 | Foundation | 2025-04-27 |  | 429 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh.Sube Singh Nain(Pappu) |  | 9416123004 | Mattrasham | Hisar | 1
5 | 21/3 | DA-3 | Foundation | 2025-04-27 |  | 429 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh.Rajbir Singh Nain |  | 7015457214 | Mattrasham | Hisar | 1
6 | 23/2 | DA+3 | Foundation | 2025-04-04 |  | 452 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Suresh mund | Ramchandra | 9812365010 | Neoli Khurd | Adampur | 1
7 | 23/3 | DA+0 | Foundation | 2025-04-05 | 2025-05-21 | 46 | Demanding Compensation before work & Market Rate of Land | resolved | Satendra Jaat | Adhwari | 9812100060 | neoli Khurd | Adampur
8 | 23/4 | DA+0 | Foundation | 2025-04-12 |  | 444 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh.Maan Singh & Sh. Suresh Saran | Sh.Bhaum Singh / Mangat Ram |  | Neoli Khurd | Adampur | 1
9 | 24/4 | DA+1.5 | Foundation | 2025-03-01 | 2025-05-16 | 76 | Demanding Compensation before work & Market Rate of Land | resolved | Kajila Panchayat & Subbaram |  | Subbaram (9466873306) | Kajila | Adampur
10 | 26/1 | DA+0 | Foundation | 2025-03-22 |  | 465 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Santlal & Makhan lal |  | 9813959071 & 9728201541 | Asrawa | Asrawa | 1
11 | 32B/1 | DA+3 | Foundation | 2025-04-29 | 2025-05-25 | 26 | Demanding Compensation before work & Market Rate of Land | resolved | Sh. Balwant Singh | Sh. Ganga Visan | 8572072491/9518465559 | Kalirawan | Adampur
12 | 32B/2 | DA+3 | Foundation | 2025-04-29 |  | 427 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Smt. Indrawati Jhajhariya |  | 9999593555/9549558888 | Kalirawan | Adampur | 1
13 | 33/1 | DA+6 | Foundation | 2025-04-15 |  | 441 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh.Sandeep | Sh. Ramswaroop | 9813263383 | Kalirawan | Adampur | 1
14 | 34/1 | DA+6 | Foundation | 2025-04-13 |  | 443 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh.Satpal Singh | Sh.Bhoop Singh Godara | 9992738883/9671933543 | Kalirawan | Adampur | 1
15 | 35/1 | DA+1.5 | Foundation | 2025-04-14 |  | 442 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh.Baljeet Chahar | Sh. Badri chahar | 9812346450 | Khasamahajan | Adampur | 1
16 | 35/2 | DA+6 | Foundation | 2025-04-15 |  | 441 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh.Baljeet Singh | Sh. Chatar Singh | 8053573208/9812238045 | Khasamahajan | Adampur | 1
17 | 38/1 | DA+0 | Foundation | 2025-04-13 |  | 443 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh.Yuglal | Sh.Brijlal | 8057700029/9991463529 | Khasamahajan | Adampur | 1
18 | 39/1 | DA+1.5 | Foundation | 2025-04-13 |  | 443 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh.Dharam Chand | Sh.Ratan Singh | 9350342508 | Khasamahajan | Adampur | 1
19 | 18/1 | DA+0 | Foundation | 2025-06-16 |  | 379 | Deny to accept intimation notice | Pending | Mr.Satpal | Sh.Ramji lal | 949925762 | Mattrasham | Hisar | 1
20 | 18/2 | DA+0 | Foundation | 2025-06-16 |  | 379 | Deny to accept intimation notice | Pending | Seetaram & Subhash Chandra | Sh.Amar Singh Sh. Omprakash | 9466150116 | Mattrasham | Hisar | 1
21 | 18/3 | DA-1.5 | Foundation | 2025-06-16 |  | 379 | Deny to accept intimation notice | Pending | Raghuvvir Singh |  |  | Mattrasham | Hisar | 1
22 | 18/4 | DA-1.5 | Foundation | 2025-06-16 | 2025-06-18 | 2 | Deny to accept intimation notice | resolved | Mahavir ji C & D pit. |  | 8901254602 | Mattrasham | Hisar
23 | 3/8 | DA+3 | Foundation | 2025-06-18 |  | 377 |  | Pending | Pursaram |  |  |  |  | 1
24 | 3/9 | DA+0 | Foundation | 2025-06-18 |  | 377 |  | Pending | Satish |  |  |  |  | 1
25 | 3/10 | DA+6 | Foundation | 2025-06-18 |  | 377 |  | Pending | Wazir Singh |  | 8449631111 |  |  | 1
26 | 24/0 | DB1+0 | Foundation | 2025-06-27 | 2025-07-05 | 8 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | resolved | Subhash Punia | Tek chand | 9467252125 | Mallapur | Hisar | 1
27 | 19/0 | DC2+3 | Foundation | 2025-07-04 | 2025-09-19 | 77 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | resolved | Rishipal | Bheemsingh | 9466329508 | Mattarsham | Hisar
28 | 25/0 | DB2+0 | Foundation | 2025-06-27 |  | 368 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | resolved | Subhash Uff Pandu | Ramshwaroop bishnoi | 8569911929 | Kaulan | Adampur
27 | 8/6 | DA+0 | Foundation | 2025-07-16 |  | 349 | Work when kissan union agree | Pending | Mohanlal , satbir ,swube singh | Alisherji | 9991620086 | Gorchhi | Balsamand | 1
28 | 8/5 | DA-3 | Foundation | 2025-07-16 |  | 349 | Work when kissan union agree | Pending | Raj kumar | Guru datta | 9873407664 | Choudhriwas | Balsamand | 1
29 | 8/7 | DA+6 | Foundation | 2025-07-16 |  | 349 | Work when kissan union agree | Pending | Sushil ji | Juglal | 8168868724 | Gorchhi | Balsamand | 1
30 | 8/8 | DA+0 | Foundation | 2025-07-16 |  | 349 | Work when kissan union agree | Pending | Jila singh | Jagat | 7015458662 | Gorchhi | Balsamand | 1
31 | 8/9 | DA+3 | Foundation | 2025-07-16 |  | 349 | Work when kissan union agree | Pending | Manga lal , Hawa Singh , Azad |  | 9992093998 9729969033 9992510816 | Gorchhi | Balsamand | 1
32 | 8/1 | DA+0 | Foundation | 2025-07-16 |  | 349 | Work when kissan union agree | Pending | Banwari | Lal singh | 9812813090 | Gawar | Balsamand | 1
33 | 8/2 | DA+0 | Foundation | 2025-07-16 |  | 349 | Work when kissan union agree | Pending | Bharat Singh | Kurda Ram | 9812021238 | Gawar | Balsamand | 1
34 | 8/3 | DA+6 | Foundation | 2025-07-16 |  | 349 | Work when kissan union agree | Pending | Jaipal Singh | Suba Singh | 9813290041 | Gawar | Balsamand | 1
35 | 8/4 | DA+3 | Foundation | 2025-07-16 |  | 349 | Work when kissan union agree | Pending | Manga Ram | Banwari Lal | 7056344159 | Choudhriwas | Hisar | 1
36 | 39/0 | DB1+0 | Foundation | 2025-08-05 |  | 329 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh.Dharam Chand | Sh.Ratan Singh | 9350342508 | Khasamahajan | Adampur | 1
37 | 38/0 | DB2+0 | Foundation | 2025-08-05 |  | 329 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh Maniram ji | Sh.Bhuna Ramji | 9896510459 | Khasamahajan | Adampur | 1
38 | 36/0 | DC1+0 | Foundation | 2025-08-05 |  | 329 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh Dalbir Singh | Sh.Balbir Singh | 9812482899 | Khasamahajan | Adampur | 1
39 | 35/0 | DD45+0 | Foundation | 2025-07-12 |  | 353 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh.Satbir Singh/ Babru bhai | Sh.Shyu Chand | 9992227830/9416335913 | Khasamahajan | Adampur | 1
40 | 34/0 | DC1+0 | Foundation | 2025-07-12 |  | 353 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh. Chotu ram | Sh.Surja | 9416940566 | Kalirawan | Adampur | 1
41 | 33/0 | DB1+3 | Foundation | 2025-07-12 |  | 353 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh.Ram Swaroop | Sh.Shankar | 9813263383 | Kalirawan | Adampur | 1
42 | 32B/0 | DB2+0 | Foundation | 2025-08-04 |  | 330 | Demand Route Diversion | Pending | Sh.Sitaram/Radhashyam | Sh.begraj | 981271879 9992477310 | Kalirawan | Adampur | 1
43 | 32/0 | DB2+3 | Foundation | 2025-08-04 |  | 330 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh.Rampal, Vijendra,Premsingh | Sh.HawaSingh | 7206377038 9992434213 | Kalirawan | Adampur | 1
44 | 31/0 | DD45+0 | Foundation | 2025-08-04 |  | 330 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sh.Sultan Singh Jatt(B&C Pit) Ramesh(A&d Pit) | S/0 Gyani Ram S/0 Ram Niwas | 8059332245 9812472983 | Kalirawan | Adampur | 1
45 | 18/0 | DB1+0 | Foundation | 2025-08-05 |  | 329 | Demanding Compensation before work & Market Rate of Land | resolved | Sh.Satyabir Singh | Sh.Ramji Lal | 9416646066 | Mattrasham | Hisar
46 | 17/7 | DA+3 | Foundation | 2025-08-05 |  | 329 | Take decision after kisan union agree to work | Pending | Sh.Rajendra Singh Mahendra Singh | S/0 Nihal Singh | Deny | Mattrasham | Hisar | 1
47 | 17/6 | DA+0 | Foundation | 2025-08-05 |  | 329 | Take decision after kisan union agree to work | Pending | Sh.Subhash Sh. Gulab | S/0 Amarsigh | 9466004012 9468092870 | Mattrasham | Hisar | 1
48 | 17/0 | DB2+0 | Foundation | 2025-08-06 |  | 328 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Suraj Bhan , Ram Nivas | Sher Singh | 9467969511 9729459405 | Kirtan | Balsamand | 1
49 | 17/1 | DA+0 | Foundation | 2025-08-06 |  | 328 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sandeep Neela | Chabila Chandagi | 8295280252 9416431351 | Kirtan | Balsamand | 1
50 | 17/4 | DA+0 | Foundation | 2025-08-06 |  | 328 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Krishna(Pit c) Rajpal (Pit A&b) Mailal (Pit D) | Ishwar Singh Atma Ram & Shiv karan | 9728017189 9467545407 9728754617 | Kirtan | Balsamand | 1
51 | 17/3 | DA+3 | Foundation | 2025-08-06 |  | 328 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Chanra Devi Rohtas Mahendra | Ishwar Singh. Jay Singh Nathuram | 8059969948 9466401002 9728017189 | Kirtan | Balsamand | 1
52 | 17/5 | DA+3 | Foundation | 2025-08-06 |  | 328 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Jai Veer Shivkumar | TulaRAM bhururam | 9992814592 | Kirtan | Balsamand | 1
53 | 59/1 | 5DA+9 | Foundation | 2025-08-07 |  | 327 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Anil Kumar | Chotu Ram | 9992256029 | Dhangar | Fatehabad | 1
54 | 59/0 | 5DB2+3 | Foundation | 2025-08-07 |  | 327 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Shri Mari Sheela Devi(Pit A& b) Raj Bala(Pit C & d) | Ram Narayan Shrawan Kumar | 9416851119 9896929429 | Dhangar | Fatehabad | 1
55 | 60/0 | 5DD45+3 | Foundation | 2025-08-07 | 2025-08-07 | 0 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Hawa Singh(Pit B &c) Pawan Kumar(Pit A & d) | Ram swaroop | 9068113793 9068433134 | Dhangar | Fatehabad | 1
56 | 58/0 | 5DC2+3 | Foundation | 2025-08-10 |  | 324 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Shri Mati Ratan Dev | W/O Nathuram | 9817477344 | Dhangar | Fatehabad | 1
58 | 55/2 | 5DA-3 | Foundation | 2025-08-10 |  | 324 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sushil Kumar | Mohanlal | 9518428745 | Dhangar | Fatehabad | 1
59 | 55/1 | 5DA-3 | Foundation | 2025-08-10 | 2026-05-23 | 286 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | resolved | Rambai | W/O Rajaram | 9416490076 | Dhangar | Fatehabad | 1
60 | 55/0 | 5DB2+6 | Foundation | 2025-08-10 |  | 324 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Dungarmal | Mokh Ram | 9813661170 | Dhangar | Fatehabad | 1
61 | 54/2 | 5DA+3 | Foundation | 2025-08-10 |  | 324 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Darshan (Pit A& B) Bhup Singh (Pit C & D) | Ugrasen Khyali | 8570078111 9467900108 | Dhangar | Fatehabad | 1
62 | 54/0 | 5DD60+9 | Foundation | 2025-08-11 |  | 323 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Shyo Chand | Duni Chand | 9518428745 | Dhangar | Fatehabad | 1
63 | 41/1 | 5DA+9 | Foundation | 2025-08-12 | 2025-08-12 | 0 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Krishna kumar Sarwan Kumar | Naki ram | 9996429321, 9992633847 | Khara kheri | Fatehabad | 1
64 | 57/0 | 5DB2-1.5 | Foundation | 2025-08-07 |  | 327 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Shiv kumar(A&C&D Pit) Lakhmi Chand (Pit B) | Ompraskash lilu ram | 9991268029 7056028459 | Dhangar | Fatehabad | 1
65 | 27/0 | DC1+0 | Foundation | 2025-08-10 | 2025-08-10 | 0 | Resolved | resolved | Ishwar Inder | Devkaran | 9812713661 9416107885 | Asrawa | Adampur
66 | 40/0 | DB2+0 | Foundation | 2025-08-20 |  | 314 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Sunil | om prakash | 9068100029 | Khara kheri | Fatehabad
67 | 40/1 | DA+3 | Foundation | 2025-08-20 |  | 314 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Pala ram(Pi C & D) Pravendra(PitA&B) | Ram lal Ramphal | 9467534421 9813898958 | Khara kheri | Fatehabad
68 | 40/2 | DA+0 | Foundation | 2025-08-20 |  | 314 | Demanding Compensation before work & (MRC is not fixed by PGCIL) | Pending | Jagdish , Banwari , palaram | Ramchandran | 9812972821 | Khara kheri | Fatehabad

## ROW S-P
ROW Status (Siwani-Patran TL) | [12 empty] | #REF!
S.No | Loc. No. | Tower/Type | Activity | Date of 1st Approach | Date of Resolution | Duration of ROW (Days) | Nature of hindrance | Status of Resolution | Name of Farmer | Father Name | Mobile no. | Vill. Name | Tehsil
1 | 30/4 | DA+3 | Foundation | 2025-04-18 |  | #REF! | Demanding Tower Shifting & Before Compensation | Pending | Sh.Janakraj | Sh. Mulchand | 9255500551/8168456965 | Durjanpur | Hisar
2 | 30/5 | DA+0 | Foundation | 2025-04-15 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Sh.Suresh / Sh.Mela Ram | Sh.Kisanlal/Sh.Nandram | 8307632460/9812843445 | Chikanwas | Hisar
3 | 30/6 | DA+3 | Foundation | 2025-04-16 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Sh. Amit Kumar |  | 9992828789 | Durjanpur | Hisar
4 | 30/7 | DA+3 | Foundation | 2025-04-25 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Sh.Kuldeep Beniwal | Sh.Jaibeer Singh | 9416251922 | Chikanwas | Hisar
5 | 31/1 | DA+0 | Foundation | 2025-05-03 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Kashabil Das | Sh.Ram Karan | 9992718781 | Chikanwas | Hisar
6 | 31/2 | DA+3 | Foundation | 2025-05-03 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Mahavir(Vinod Son) | Sh.Bagdawat | 9992915495 | Chikanwas | Hisar
7 | 32/1 | DA+0 | Foundation | 2025-05-03 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Ugrasen | Sh Rajendra | 9034731474 | Chikanwas | Hisar
8 | 32/2 | DA+6 | Foundation | 2025-05-03 | 2025-06-14 | 42 | Pending,Demanding Compensation before work | Resolved | Vinay/ Krishan | Sh.Mahendra/Gurudayal Singh | 8221836828/9416509790 | Chikanwas | Hisar
9 | 32/4 | DA+3 | Foundation | 2025-05-03 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending
10 | 19/3 | DA+3 | Foundation | 2025-05-08 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Naresh kumar/Balwant | /Chandrabhan | 9813928820/9813416920 | Rawalwas Khurd | Hisar
11 | 19/1 | DA+0 | Foundation | 2025-05-08 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Sandeep | Sh.Mehtab Singh | 9996738888/7988884133 | Dhiranwas | Balsamand
12 | 19/2 | DA+3 | Foundation | 2025-05-08 |  | #REF! | Due to Hold 19/3 | Pending | Dhiranwas Panchayat(Rambeer Fauji) |  | 9467705022 | Dhiranwas | Balsamand
13 | 20/1 | DA+0 | Foundation | 2025-05-09 |  | #REF! | Due to Hold 19/4 | Pending | Rajmal/Vedh ram | Sh Phool Singh/Kheta ram | 8529472005/9729122489 | Rawalwas Khurd | Hisar
14 | 20/2 | DA+3 | Foundation | 2025-05-09 |  | #REF! | Due to Hold 19/4 | Pending | Veer singh( Ajit Mitharwal) | Sh. Dharampal | 8059662625/9466006507 | Rawalwas Khurd | Hisar
15 | 3/2 | DA+3 | Foundation | 2025-05-10 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Satyabhan |  | 9813629404 | Lilas | Siwani
16 | 3/3 | DA-3 | Foundation | 2025-05-10 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Mayaram | Sh. Banwari | 9992896751,9813965291 | Lilas | Siwani
17 | 3/4 | DA+0 | Foundation | 2025-05-10 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Bhup Singh | Sh.Mahavir Singh | 8053744663 | Gaindawas | Siwani
18 | 3/5 | DA+3 | Foundation | 2025-05-10 | 2025-05-20 | 10 | Pending,Demanding Compensation before work | Resolved | Mahipal Siwach | Sh. Chanduram | 9813560174 | Gaindawas | Siwani
19 | 3/6 | DA+0 | Foundation | 2025-05-10 | 2025-05-20 | 10 | Pending,Demanding Compensation before work | Resolved | Shyochand | Sh. Buddharam | 8860712578 | Gaindawas | Siwani
20 | 3/7 | DA+0 | Foundation | 2025-05-10 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Jai singh | Sh. Laal Chand | 9416695580 | Siwani | Siwani
21 | 3/8 | DA-3 | Foundation | 2025-05-10 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Jai singh/ | Sh. Laal Chand/ | 9416695580 | Siwani | Siwani
22 | 3/9 | DA+0 | Foundation | 2025-05-10 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Krishan Singh | SH.Pratap Singh | 9813960139 | Azad Nagar | Siwani
23 | 3/10 | DA+3 | Foundation | 2025-05-10 | 2025-05-24 | 14 | After Casting Owner not allowed to shift the material | Resolved | Rajvir Singh | Sh. Hait Ram | 9813491027 | Lilas | Siwani
24 | 4/1 | DA-3 | Foundation | 2025-05-10 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Shiv Kumar/Rajender/Devinder |  | 7863000029/9255170101/9466612021 | Siwani | Siwani
25 | 4/2 | DA+0 | Foundation | 2025-05-15 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Krishna | Sh.Hari Singh | 9991352250 | Siwani | Siwani
26 | 4/3 | DA+3 | Foundation | 2025-05-15 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Suresh (Chairman) |  | 9813199428 | Siwani | Siwani
27 | 4/4 | DA+3 | Foundation | 2025-05-15 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Pradeep Dhiwan/Ashok | /Sh. Ram singh | 9416357463 | Siwani | Siwani
28 | 21/2 | DA+0 | Foundation | 2025-05-28 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Jayneer/Anup | Guljari | 9812177150 | Hindwaan | Hisar
29 | 21/3 | DA+0 | Foundation | 2025-05-10 | 2025-06-15 | 36 | First Complete 19/3 then do | Resolved | Randhit Singh | Sh. Charan Singh | 9050520065 | Hindwaan | Hisar
30 | 21/4 | DA+0 | Foundation | 2025-05-09 |  | #REF! |  | Pending | Rohtash | Sh. Shyochand | 9416768356 | Hindwaan | Hisar
31 | 21/5 | DA+3 | Foundation | 2025-05-28 |  | #REF! | First Complete 19/3 then do | Pending | Sandeep | Sh.Maniram | 9468158973 | Hindwaan | Hisar
32 | 21/6 | DA+0 | Foundation | 2025-05-28 | 2025-05-29 | 1 |  | Resolved | Dharam Singh, Rajpal+Rampat | Sh.Hari Singh | 9896486455 | Hindwaan | Hisar
33 | 21/7 | DA+3 | Foundation | 2025-05-28 | 2025-05-29 | 1 |  | Resolved | Ram Singh | SH.Rann Singh/Mann Singh | 7400073005 | Shahpur | Hisar
34 | 21/8 | DA+0 | Foundation | 2025-05-28 |  | #REF! | First Complete 19/3 then do | Pending | Dileep Singh | Sh.Bhagwanaram | 7988191556 | Shahpur | Hisar
35 | 23/1 | DA-1.5 | Foundation | 2025-05-29 | 2025-05-30 | 1 |  | Resolved | khaniya | Sh. Sukhlal | 9992364989 | Shahpur | Hisar
36 | 23/2 | DA+0 | Foundation | 2025-05-29 | 2025-06-07 | 9 |  | Resolved | Krishan | Sh. Purkha | 9813380493 | Shahpur | Hisar
37 | 23/3 | DA+6 | Foundation | 2025-05-29 | 2025-05-30 | 1 |  | Resolved | Jaidev Singh | Sh.Manaka Singh | 9466329684 | Shahpur | Hisar
38 | 23/4 | DA+0 | Foundation | 2025-05-30 | 2025-06-11 | 12 | Pending,Demanding Compensation before work | Resolved | Krishnan Beniwal | Sh. Pratap Beniwal | 8221868848 | Shahpur | Hisar
39 | 24/1 | DA+9 | Foundation | 2025-05-30 | 2025-06-15 | 16 | Pending,Demanding Compensation before work | Resolved | Randhir | sh.shriramji lal/ sh.Kurrada | 9467153826 | Shahpur | Hisar
40 | 24/2 | DA+3 | Foundation | 2025-05-30 |  | #REF! |  | Pending | Ishwar Singh | Sh.Bachan Singh | 9050120046 | Shahpur | Hisar
41 | 25/1 | DA+3 | Foundation | 2025-05-30 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Omprakash | Sh.Ramjlal | 9416886203 | Mattrashyam | Hisar
42 | 25/2 | DA+0 | Foundation | 2025-05-30 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Vimla Devi(Sandeep) | Sh.Parsaram | 7404513083 | Mattrashyam | Hisar
43 | 25/3 | DA+3 | Foundation | 2025-05-30 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Balram | Sh. Parma Singh | 7015847366 | Mattrashyam | Hisar
44 | 26/1 | DA+0 | Foundation | 2025-05-30 | 2025-06-27 | 28 |  | Resolved | Satyabhan/Anoop Sarpanch | Sh.Sh.Laljiram/Mattershyam Panchayaat | 9466681480 | Mattrashyam | Hisar
45 | 26/2 | DA+0 | Foundation | 2025-05-30 |  | #REF! | Pending,Demanding Compensation before work | Pending | Prem Kumar | Sh.Balveer | 8569987304 | Mattrashyam | Hisar
46 | 23/0 | DB1-3 | Foundation | 2025-06-02 | 2025-06-07 | 5 | ROW Clear (2+2 legs) | Resolved | Ranveer Singh/Mahaveer Singh | Sh. Beerbalram | 8607467212/9354198016 | Shahpur | Hisar
47 | 24/0 | DB2+3 | Foundation | 2025-06-09 | 2025-06-10 | 1 | ROW Clear (04 legs) | Resolved | Ramesh kumar/Rajesh Kumar | Sh. Late Liluram | 9992416681/9468046166 | Shahpur | Hisar
48 | 32/3 | DA+0 | Foundation | 2025-06-11 |  | #REF! | Demanding Route Diversion | Pending | Mr. Trilok | Sh.Roshan lal | 9896343715 | Chikanwas | Hisar
49 | 36/4 | 5DA-3 | Foundation | 2025-06-11 | 2025-06-12 | 1 | ROW Clear (04 legs) | Resolved | Sarjeet | Sh. Baghirat | 9416217808 | Landhari | Hisar
50 | 30/0 | DB2+0 | Foundation | 2025-06-11 | 2025-06-12 | 1 | ROW Clear (04 legs) | Resolved | Omprakash | Sh. Sohanlal | 9992519590 | Kajila | Adampur
51 | 21/1 | DA+0 | Foundation | 2025-06-18 |  | #REF! |  | Pending | Satbir Singh | Amar Singh | 9991566543 | Nathwala | Hisar
52 | 56/3 | 5DA+3 | Foundation | 2025-06-21 |  |  | Row after Excavation | Resolved | Raj Meher |  | 9992058288 | Chahal dhani | Uklana
53 | 19/0 | DC2+9 | Foundation | 2025-06-21 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Jagat singh | Sh. Darbari | 9992362130 | Dhiranwas | Hisar
54 | 56/2 | 5DA+6 | Foundation | 2025-06-19 | 2025-07-01 | 12 | Pending,Demanding Compensation before work | Resolved | Dalveer Singh |  | 8059531363 | Khairi | Hisar
55 | 43/0 | 5DC1+0 | Foundation | 2025-06-23 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Anil Bhadu |  | 9991120101 | Nagathala | Hisar
56 | 31/0 | DB1+3 | Foundation | 2025-06-22 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Gurmesh Kumar | Sh. Kashbildas | 9992170766 | Chiknawas | Hisar
57 | 32/0 | DB2+3 | Foundation | 2025-06-22 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Ashwani Kumar | Sh.Rajendra | 9416435662 | Chiknawas | Hisar
58 | 21/0 | DB2+0 | Foundation | 2025-06-21 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Suhbeer | Sh.Dharam Pal` | 9813243069 | Nathwana | Hisar
59 | 42/1 | 5DA+6 | Foundation | 2025-06-24 |  | #REF! | Demand Tower shifting | Pending | Mukesh Bhadu | Surendra bhadu | 9671116129 | Nangthala | Hisar
60 | 25/0 | DB2+0 | Foundation | 2025-06-28 |  | #REF! | Demand Tower shifting | Pending | Jay Bhojvan | Ratan Lal | 9466248791 | Mattrashyam | Hisar
62 | 36/3 | 5DA+0 | Foundation | 2025-06-12 | 2025-06-12 | 0 | ROW Clear 04 legs | Resolved | Palaram | Sh.Moman ram | 9306104243 | Landhari | Hisar
63 | 36/5 | 5DA+6 | Foundation | 2025-06-12 |  | #REF! | Demanding Compensation before work | Pending | Shantanu Johar | Sh. Vedpal Johar | 9202902929 | Landhari | Hisar
64 | 36/2 | 5DA+6 | Foundation | 2025-06-12 |  | #REF! | ROW 04 legs | Pending | Ramswarup Johar | Sh.Sohanlal Johar | 9812007050 | Landhari | Hisar
65 | 37/0 | 5DD45+3 | Foundation | 2025-06-13 | 2025-06-13 | 0 | ROW Clear 04 legs | Resolved | Ajeet Dhaka/ Sunder Singh | Late Sh. Tarachand | 9466532520/9255594508 | Thaska | Hisar
66 | 29/0 | DC1+0 | Foundation | 2025-06-20 | 2025-06-21 | 1 | ROW Clear 04 legs | Resolved | Jagdish Chander | Sh.Lalchand | 9466006521/9466638429 | Ichhakhedi | Adampur
67 | 44/1 | 5DA+0 | Foundation | 2025-06-23 | 2025-06-24 | 1 | ROW Clear of 02 legs (02 Pending) | Resolved | Subhash Mehla/Kuljeet Singh | Sh.Lalchand Mehla/Sh.Besant Singh | 9728535858/8950001281 | Nangthala | Hisar
68 | 45/2 | 5DA+9 | Foundation | 2025-06-24 |  | #REF! | ROW After Excavation ,Farmer demand MRC Should be final before work before work | Pending | Sunil Sharma(Pawan& Navneet) | Sh.Khajanchand Sharma | 9467025567/7404303889 | Nangthala | Hisar
69 | 46/0 | 5DD45+6 | Foundation | 2025-06-24 | 2025-06-24 | 0 | ROW Clear 04 legs | Resolved | Mangeram | SH.Rai singh | 9050036963 | Nangthala | Hisar
70 | 44/0 | 5DD45+0 | Foundation | 2025-06-23 |  | #REF! | Demanding tower shifting due to Land Road | Pending | Mangiram | Sh.Navrang | 9813193558 | Nangthala | Hisar
71 | 45/1 | 5DA+6 | Foundation | 2025-06-24 |  | #REF! | Demanding Compensation before work | Pending | Parmanand/ Rajkumar | Sh.Ramkrishan | 9467846880/8901255905 | Nangthala | Hisar
72 | 44/2 | 5DA+6 | Foundation | 2025-06-23 |  | #REF! | ROW Clear 04 legs( Notice not issue- telephonic) | Pending | Saddanand | Sh.Jamunudas | 7988475604/8295752701 | Nangthala | Hisar
73 | 14/1 | DA+0 | Foundation | 2025-06-16 |  | #REF! | Demanding tower shifting due to Land Road | Pending | Daya Kisan | Sh.Ramchandra | 8053026266/9813256941 | Panihar Chak | Hisar
74 | 15/0 | DB2+0 | Foundation | 2025-07-11 |  | #REF! | Demanding tower shifting due to Land Road | Pending | Randava | Sh.Faden Singh | 9729770703 | Panihar Chak | Hisar
75 | 15/1 | DA+0 | Foundation | 2025-07-11 |  | #REF! | Demanding tower shifting due to Land Road | Pending | Jaikisan/Gyan Kaswa | /Kunwar Singh | 8059460510/9813145633 | Panihar Chak | Hisar
76 | 15B/1 | DA+0 | Foundation | 2025-07-11 |  | #REF! | Demanding tower shifting due to Land Road | Pending | Balwan | Sh.Lakhiram | 7015912919/9416216093 | Panihar Chak | Hisar
77 | 15B/2 | DA+3 | Foundation | 2025-07-13 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Deepak | Sh.Sadhuram | 9812450855 | Panihar Chak | Hisar
78 | 15B/3 | DA+0 | Foundation | 2025-06-21 |  | #REF! | Demanding tower shifting due to Land Road | Pending | Ramkrishan,Roshan | Sh.Mahendra singh | 9991944744/9996102327 | Panihar Chak | Hisar
79 | 17/0 | DC2+6 | Foundation | 2025-07-14 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Krishan Kumar | Sh.Chhajuram | 9416419188 | Dhiranwas | Balsamand
80 | 17/1 | DA+0 | Foundation | 2025-07-14 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Umed, Dalbeer | Sh.Kheturam | 9991705037 | Dhiranwas | Balsamand
81 | 17/2 | DA+0 | Foundation | 2025-07-14 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Satbeer | Sh.Lal singh | 9467018161 | Dhiranwas | Balsamand
82 | 17/3 | DA+6 | Foundation | 2025-07-14 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Sant Kumar | Sh.Pratap | 9215600717 | Dhiranwas | Balsamand
83 | 16/1 | DA+0 | Foundation | 2025-07-14 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Shobachand | Sh.Bhaliram | 9996640566 | Rawalwaskalan | Balsamand
84 | 14/5 | DA+0 | Foundation | 2025-07-14 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Anil Kumar | 0 | 9306708872 | Panihar Chak | Hisar
85 | 50/0 | 5DD60+30 | Foundation | 2025-08-07 |  | #REF! | Row not Clear & Hold due to Xing | Pending | Manoj | Sh. Iswar Singh | 9813428960,9050450156 | Kirmara | Hisar
86 | 46/1 | 5DA+6 | Foundation | 2025-08-06 |  | #REF! | ROW Clear but due to wet land work possible after 5-6 days ROW After Excavation ,Farmer demand MRC Should be final before work before work | Pending | Anoop Sharma | Sh. Krishan kumar | 9992108706, 8570823994 | Nangthala | Hisar
87 | 47/0 | 5DC1+3 | Foundation | 2025-08-06 | 2025-08-06 | 0 | ROW Clear but work not possible due to Paddy& Cotton Field. | Resolved | Ramswaroop (Virendra)/Liluram & Rakesh | Sh. Shankar/Sh. Ramkumar | 9996647602/9355338112,9813263017 | Nangthala | Hisar
88 | 47/3 | 5DA+0 | Foundation | 2025-08-06 | 2025-08-06 | 0 | ROW Clear but work not possible due to Paddy Field. | Resolved | Joginder/Ramesh | Sh.Ramchandra | 9050169485,9728383736 | Sandol | Hisar
89 | 47/2 | 5DA+0 | Foundation | 2025-08-06 | 2025-08-06 | 0 | ROW Cleared | Resolved | Doonger Singh | Sh.Sujan Singh | 9659697000,9813126777 | Sandol(Kanoh) | Hisar
90 | 48/1 | 5DA+0 | Foundation | 2025-08-07 | 2025-08-07 | 0 | Row Cleared But Paddy field & Hold due to Xing Also | Resolved | Manoj Kumar | Sh.Iswar Singh | 9813428960,9050450156 | Kirmara | Hisar
91 | 48/0 | 5DB1+3 | Foundation | 2025-08-07 | 2025-08-07 | 0 | ROW Clear but work not possible due to Paddy Field. | Resolved | Ramesh kumar | Sh.Balwant | 9996371626 | Kirmara | Hisar
92 | 47/6 | 5DA+6 | Foundation | 2025-08-07 | 2025-08-07 | 0 | ROW Clear but work not possible due to Paddy Field. | Resolved | Akashya Kumar | Sh.Krishan Kumar | 9813383278,7082130778 | Kirmara | Hisar
93 | 47/1 | 5DA+9 | Foundation | 2025-08-06 |  | #REF! | Intimation Accepted but Denied to work | Pending | Anup/Vinod | Sh.Rishilal/Sh.Ramveer singh | 9068870402,9671733547 | Nangthala | Hisar
94 | 47/5 | 5DA+6 | Foundation | 2025-08-07 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Mahendra singh,Harpal Singh/ Smt Poonam | Sh.Badalu Singh/ Naveen Kumar | 7082431607,9812924850/9813552924 | Kirmara | Hisar
95 | 49/0 | 5DD60+30 | Foundation | 2025-08-07 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Dharmpal | Sh.Dayaram | 9466052983 | Kirmara | Hisar
96 | 13/0 | DB2+9 | Foundation | 45882 |  | #REF! | Intimitation Not Accepted | Pending | Hansraj | Surjaram | 9467250649 | Chaudhariwas | Hisar
97 | 45/2 | 5DA+9 | Foundation | 2025-09-29 |  | #REF! | After Excavation , Farmer demand MRC Finalization and stopped the work | Pending
98 | 46/1 | 5DA+6 | Foundation | 2025-09-29 |  | #REF! | After Excavation , Farmer demand MRC Finalization and stopped the work | Pending
97 | 114/1 | 5DA+6 | Foundation | 2025-09-20 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Jasveer singh | Gurmukh singh | 9278268566 | Duttal | Patran
98 | 109/0 | 5DD60+30 | Foundation | 2025-09-25 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Param jit | Charate singh |  | Molvi wala | Patran
99 | 111/0 | 5DD45+3 | Foundation | 2025-09-27 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Gurbhajan singh | kartar singh | 9914721366 | Paind | Patran
100 | 111/1 | 5DA+3 | Foundation | 2025-09-27 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Dilip singh | Teja singh | 9914721366 | Sutrana | Patran
101 | 115/1 | 5DA+6 | Foundation | 2025-09-27 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Baldev singh | pala singh |  | Duttal | Patran
102 | 114/0 | 5DC2+9 | Foundation | 2025-09-29 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Gurpreet singh | Pyara singh | 9463054418 | Duttal | Patran
103 | 117/0 | 5DD45+0 | Foundation | 2025-09-29 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Satpal singh | Maluk singh |  | Duttal | Patran
104 | 113/0 | 5DB2+0 | Foundation | 2025-09-29 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | aswaran singh | Joginder singh |  | Duttal | Patran
105 | 113/1 | 5DA+6 | Foundation | 2025-09-29 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Daljeet singh | Gurmej Singh |  | Duttal | Patran
106 | 118/1 | 5DA+0 | Foundation | 2025-09-29 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Iqbal singh | Bhan singh | 9478686001 | Duttal | Patran
107 | 115/2 | 5DA+0 | Foundation | 2025-09-29 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Gurdev singh | Nirmal singh |  | Duttal | Patran
108 | 120/0 | 5DD60+25 | Foundation | 2025-09-30 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Darshan singh | Shingar Singh |  | Daroli | Patran
109 | 119/0 | 5DD60+9 | Foundation | 2025-09-30 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Gurdeep singh | Nihal Singh |  | Daroli | Patran
110 | 106/0 | 5DB2+9 | Foundation | 2025-10-06 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Jasveer singh | Baaj singh | 9915643334 | Noorpur | Patran
111 | 105/5 | 5DA+9 | Foundation | 2025-10-06 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Gurpreet singh | Pipal singh | 9915643334 | Noorpur | Patran
112 | 106/0 | 5DB2+9 | Foundation | 2025-10-06 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Baldeev Singh | Kashmir singh | 9855152930 | Noorpur | Patran
113 | 109/1 | 5DA+6 | Foundation | 2025-09-25 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Gurpreet singh | Wirsa Singh |  | Taind | Patran
114 | 105/2 | 5DA+6 | Foundation | 2025-10-06 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Daljinder singh | Jaswant singh | 9855601841 | Khaing | Patran
115 | 116/0 | 5DC1+3 | Foundation | 2025-10-06 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Bagicha singh0 | Bahal singh | 8146528652 | Daital | Patran
116 | 118/2 | 5DA+0 | Foundation | 2025-10-06 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Harbhajan singh | Hardev singh | 9464250552 | Banwala | Patran
117 | 121/0 | 5DD60+18 | Foundation | 2025-10-06 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Palwinder Singh | Swan singh | 9464250552 | Deoli | Patran
118 | 118/0 | 5DB1+6 | Foundation | 2025-10-09 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Baljit kaur | W/O sncha singh | 9463074557 | Daital | Patran
119 | 105/3 | 5DA+6 | Foundation | 2025-10-10 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Fguru charan singh | Amrek singh | 8264197699 | Hastipur(Hotipura) | Patran
120 | 105/4 | 5DA+6 | Foundation | 2025-10-10 |  | #REF! | Pending,Demanding Compensation before work (MRC is not fixed by PGCIL) | Pending | Robin singh | Balwinder singh | 9017458545 | Khang(Gullar) | Patran

## TS SP
KEC INTERNATIONAL LIMITED
Transmission Line Package TL03 for (a) Siwani– Fatehabad (PG) 400kV D/c line (Quad); (b) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) associated with “Transmission System for evacuation of power from Rajasthan REZ Ph-IV (Part 3: 6 GW) (Bikaner Complex) : Part A” through Tariff Based Competitive Bidding
Package TL03 for (b)400 KV DC Quad Siwani to Patran Transmission Line
TOWER SCHEDULE - S.Gantry to PATRAN GANTRY WZ-4 & WZ-5
Client :POWERGRID BIKANER IV TRANSMISSION LIMITED (A 100% WHOLLY OWNED SUBSIDIARY OF POWER GRID) | [24 empty] | DT :30.07.2020
Sl.No | AP NO. | TOWER NO. | TYPE OF TOWER | HT of Tower (Mtr) | SPAN (Mtr) | CUMULATIVE SPAN | R.L (Mtr) | DEVIATION ANGLE (Deg) | Sum of Adjacent Spans | WIND SPAN (Mtr) | WEIGHT SPAN IN Mtr (Cold) |  |  | WEIGHT SPAN IN Mtr (Hot) |  |  | LONGITUDE (E) | LATITUDE (N) | UTM Coordinates |  | CROSSING DETAILS | VILLAGE | TEHSIL | Remarks | DISTRICT
[11 empty] | Left | Right | Total | Left | Right | Total |  |  | Easting (m) | Northing (m)
1 |  | Shiwani Gantry | Gantry | 22.8 |  | 0 | 215.65 |  | 100.363 | 50.1815 | 0 | 16 | 16 | 0 | 18 | 18 | 75d33'0.794"E | 28d47'34.369"N | 553698.378 | 3185163.056 |  | Jhumpa kalan
100.363
2 | AP1/0 | 1/0 | DD60+0 | 47.97 |  | 100.363 | 215.05 | 3° 47' 9"LT | 368.807 | 184.4035 | 89 | -39 | 50 | 87 | 34 | 121 | 75d33'0.814"E | 28d47'37.63"N | 553698.451 | 3185263.419 |  | Jhumpa kalan
[5 empty] | 268.444 | [15 empty] | Proposed 400KV D/C TL
3 | AP1A/0 | 1A/0 | DD60+25 | 72.97 |  | 368.807 | 214.2 | 1° 33' 45"RT | 429.802 | 214.901 | 309 | 80 | 389 | 237 | 81 | 318 | 75d33'0.213"E | 28d47'46.336"N | 553680.921 | 3185531.29 |  | Jhumpa kalan
161.358
4 | AP1B/0 | 1B/0 | DD60+25 | 72.97 |  | 530.165 | 214.25 | 53° 11' 58"RT | 561.358 | 280.679 | 82 | 303 | 385 | 81 | 271 | 352 | 75d33'0.014"E | 28d47'51.576"N | 553674.778 | 3185692.531 |  | Jhumpa kalan
400
5 |  | 1B/1 | DA+9 | 57.15 |  | 930.165 | 212.647 |  | 819.03 | 409.515 | 100 | 263 | 363 | 131 | 246 | 377 | 75d33'11.527"E | 28d47'59.706"N | 553985.714 | 3185944.163 |  | Jhumpa kalan
[5 empty] | 419.03 | [15 empty] | CART TRACK
6 | AP1C/0 | 1C/0 | DC1+0 | 47.07 |  | 1349.195 | 212.287 | 18° 32' 4"LT | 837.03 | 418.515 | 157 | 167 | 324 | 174 | 182 | 356 | 75d33'23.588"E | 28d48'8.222"N | 554311.443 | 3186207.767 |  | Jhumpa kalan
[5 empty] | 418 | [15 empty] | CART TRACK
7 |  | 1C/1 | DA+0 | 48.15 |  | 1767.195 | 219.44 |  | 804.784 | 402.392 | 252 | 200 | 452 | 237 | 198 | 435 | 75d33'31.93"E | 28d48'19.645"N | 554535.932 | 3186560.37 |  | Jhumpa kalan
[5 empty] | 386.784 | [15 empty] | METAL ROAD
8 |  | 1C/2 | DA+0 | 48.15 |  | 2153.979 | 218.365 |  | 706 | 353 | 187 | 167 | 354 | 190 | 165 | 355 | 75d33'39.65"E | 28d48'30.214"N | 554743.655 | 3186886.641 |  | Budhsheli
319.216
9 |  | 1C/3 | DA+0 | 48.15 |  | 2473.195 | 217.385 |  | 710.016 | 355.008 | 153 | 194 | 347 | 155 | 195 | 350 | 75d33'46.022"E | 28d48'38.937"N | 554915.092 | 3187155.915 |  | Budhsheli
[5 empty] | 390.8 | [15 empty] | CART TRACK
10 | AP1D/0 | 1D/0 | DC2+6 | 53.07 |  | 2863.995 | 212.06 | 24° 58' 40"LT | 828.8 | 414.4 | 197 | 233 | 430 | 197 | 229 | 426 | 75d33'53.822"E | 28d48'49.617"N | 555124.972 | 3187485.573 |  | Budhsheli
438
11 |  | 1D/1 | DA+3 | 51.15 |  | 3301.995 | 211.904 |  | 844 | 422 | 206 | 167 | 373 | 210 | 178 | 388 | 75d33'56.009"E | 28d49'3.718"N | 555182.183 | 3187919.82 |  | Budhsheli
[5 empty] | 406 | [15 empty] | RAW ROAD/TAR ROAD
12 |  | 1D/2 | DA+9 | 57.15 |  | 3707.995 | 212.696 |  | 842.419 | 421.2095 | 240 | 233 | 473 | 229 | 229 | 458 | 75d33'58.037"E | 28d49'16.788"N | 555235.214 | 3188322.342 |  | Budhsheli
436.419
13 | AP2/0 | 2/0 | DD60+3 | 50.97 |  | 4144.414 | 215.22 | 35° 42' 56"LT | 630.011 | 315.0055 | 204 | 108 | 312 | 208 | 101 | 309 | 75d34'0.216"E | 28d49'30.839"N | 555292.219 | 3188755.022 |  | Budhsheli
[5 empty] | 193.592 | [15 empty] | NHI=52/LT LINE
14 | AP2A/0 | 2A/0 | DD60+6 | 53.97 |  | 4338.006 | 211.45 | 14° 43' 54"LT | 398.832 | 199.416 | 85 | 69 | 154 | 92 | 89 | 181 | 75d33'56.869"E | 28d49'36.396"N | 555200.707 | 3188925.619 |  | Budhsheli
[5 empty] | 205.24 | [15 empty] | RAILWAY TRACK
15 | AP2B/0 | 2B/0 | DD60+9 | 56.97 |  | 4543.246 | 210.85 | 50° 45' 36"RT | 561.24 | 280.62 | 137 | 213 | 350 | 116 | 199 | 315 | 75d33'51.737"E | 28d49'41.299"N | 555060.886 | 3189075.864 |  | Budhsheli
356
16 |  | 2B/1 | DA+0 | 48.15 |  | 4899.246 | 215.316 |  | 656 | 328 | 144 | 140 | 284 | 158 | 144 | 302 | 75d33'53.585"E | 28d49'52.752"N | 555109.312 | 3189428.555 |  | Budhsheli
300
17 |  | 2B/2 | DA+0 | 48.15 |  | 5199.246 | 216.523 |  | 618 | 309 | 160 | 134 | 294 | 156 | 144 | 300 | 75d33'55.143"E | 28d50'2.403"N | 555150.121 | 3189725.766 |  | Lilas
318
18 |  | 2B/3 | DA+0 | 48.15 |  | 5517.246 | 219.754 |  | 693 | 346.5 | 184 | 234 | 418 | 174 | 216 | 390 | 75d33'56.795"E | 28d50'12.633"N | 555193.378 | 3190040.811 |  | Lilas
375
19 |  | 2B/3 | DA+0 | 48.15 |  | 5892.246 | 212.655 |  | 746.016 | 373.008 | 142 | 102 | 244 | 160 | 135 | 295 | 75d33'58.743"E | 28d50'24.696"N | 555244.388 | 3190412.325 |  | Lilas
[5 empty] | 371.016 | [15 empty] | RAW ROAD
20 | AP2C/0 | 2C/0 | DD45+9 | 56.97 |  | 6263.262 | 215.979 | 43° 5' 29"LT | 575.062 | 287.531 | 270 | 104 | 374 | 237 | 103 | 340 | 75d34'0.67"E | 28d50'36.632"N | 555294.857 | 3190779.892 |  | Lilas
[5 empty] | 204.046 | [15 empty] | 132 KV SC TL
21 | AP2D/0 | 2D/0 | DD60+9 | 56.97 |  | 6467.308 | 215.868 | 54° 29' 6"RT | 582.018 | 291.009 | 100 | 279 | 379 | 102 | 249 | 351 | 75d33'56.351"E | 28d50'42.063"N | 555177.025 | 3190946.477 |  | Lilas
[5 empty] | 377.972 | [15 empty] | TAR ROAD/LT LINE/RAW ROAD
22 | AP3/0 | 3/0 | DA+0 | 48.15 |  | 6845.28 | 210.75 | 1° 19' 17"RT | 788.972 | 394.486 | 100 | 217 | 317 | 130 | 214 | 344 | 75d34'1.003"E | 28d50'53.641"N | 555301.4 | 3191303.4 |  | Lilas
[5 empty] | 411 | [15 empty] | CART TRACK
23 |  | 3/1 | DA+1.5 | 49.65 |  | 7256.28 | 207.25 |  | 804 | 402 | 194 | 187 | 381 | 199 | 190 | 389 | 75d34'6.392"E | 28d51'6.124"N | 555445.558 | 3191688.289 |  | Gaindwas
[5 empty] | 393 | [15 empty] | CART TRACK
24 |  | 3/2 | DA+3 | 51.15 |  | 7649.28 | 207.424 |  | 786 | 393 | 198 | 235 | 433 | 198 | 222 | 420 | 75°34'11.543"E | 28°51'18.058"N | 555583.363 | 3192056.223 |  | Gaindwas
[5 empty] | 393 | [15 empty] | CART TRACK
25 |  | 3/3 | DA-3 | 45.15 |  | 8042.28 | 207.019 |  | 776 | 388 | 159 | 152 | 311 | 172 | 166 | 338 | 75°34'16.696"E | 28°51'29.995"N | 555721.208 | 3192424.256 |  | Gaindwas
383
26 |  | 3/4 | DA+0 | 48.15 |  | 8425.28 | 210.576 |  | 774 | 387 | 231 | 168 | 399 | 219 | 177 | 396 | 75°34'21.718"E | 28°51'41.628"N | 555855.545 | 3192782.923 |  | Gaindwas
391
27 |  | 3/5 | DA+3 | 51.15 |  | 8816.28 | 212.323 |  | 820 | 410 | 224 | 240 | 464 | 215 | 232 | 447 | 75°34'26.845"E | 28°51'53.504"N | 555992.689 | 3193149.083 |  | Gaindwas
[5 empty] | 429 | [15 empty] | CART TRACK | [6 empty] | 19900
28 |  | 3/6 | DA+0 | 48.15 |  | 9245.28 | 210.672 |  | 818 | 409 | 190 | 213 | 403 | 198 | 207 | 405 | 75°34'32.471"E | 28°52'6.534"N | 556143.16 | 3193550.828 |  | Gaindwas
389
29 |  | 3/7 | DA+0 | 48.15 |  | 9634.28 | 207.688 |  | 802 | 401 | 177 | 197 | 374 | 183 | 200 | 383 | 75°34'37.573"E | 28°52'18.349"N | 556279.602 | 3193915.114 |  | Gaindwas
413
30 |  | 3/8 | DA-3 | 45.15 |  | 10047.28 | 212.49 |  | 778 | 389 | 217 | 184 | 401 | 214 | 184 | 398 | 75°34'42.99"E | 28°52'30.893"N | 556424.462 | 3194301.876 |  | Gaindwas
365
31 |  | 3/9 | DA+0 | 48.15 |  | 10412.28 | 209.264 |  | 803 | 401.5 | 181 | 236 | 417 | 182 | 231 | 413 | 75°34'47.778"E | 28°52'41.979"N | 556552.486 | 3194643.687 |  | Gaindwas
[5 empty] | 438 | [15 empty] | PH HT-3.7M/CART TRACK/
32 |  | 3/10 | DA+3 | 51.15 |  | 10850.28 | 203.185 |  | 831.115 | 415.5575 | 203 | 219 | 422 | 209 | 212 | 421 | 75°34'53.523"E | 28°52'55.282"N | 556706.115 | 3195053.86 |  | Siwani
[5 empty] | 393.115 | [15 empty] | CART TRACK
33 | AP4/0 | 4/0 | DB2+0 | 46.87 |  | 11243.395 | 202.981 | 11° 7' 1"LT | 749.115 | 374.5575 | 174 | 191 | 365 | 182 | 187 | 369 | 75°34'58.68"E | 28°53'7.222"N | 556844 | 3195422 |  | Siwani
[5 empty] | 356 | [15 empty] | BRICK ROAD
34 |  | 4/1 | DA-3 | 45.15 |  | 11599.395 | 203.459 |  | 715 | 357.5 | 166 | 163 | 329 | 170 | 169 | 339 | 75°35'0.894"E | 28°53'18.624"N | 556902.244 | 3195773.203 |  | Siwani
[5 empty] | 359 | [15 empty] | CART TRACK
35 |  | 4/2 | DA+0 | 48.15 |  | 11958.395 | 202.933 |  | 769 | 384.5 | 196 | 179 | 375 | 190 | 189 | 379 | 75°35'3.127"E | 28°53'30.122"N | 556960.978 | 3196127.366 |  | Siwani
410
36 |  | 4/3 | DA+3 | 51.15 |  | 12368.395 | 204.526 |  | 771 | 385.5 | 232 | 165 | 397 | 223 | 171 | 394 | 75°35'5.678"E | 28°53'43.253"N | 557028.057 | 3196531.841 |  | Siwani
[5 empty] | 361 | [15 empty] | 11 KV LINE /CART TRACK
37 |  | 4/4 | DA+3 | 51.15 |  | 12729.395 | 206.977 |  | 779.331 | 389.6655 | 197 | 252 | 449 | 191 | 238 | 429 | 75°35'7.923"E | 28°53'54.816"N | 557087.119 | 3196887.977 |  | Siwani
[5 empty] | 418.331 | [15 empty] | TEMPLE HT-.7M
38 | AP5/0 | 5/0 | DB1+0 | 46.87 |  | 13147.726 | 203.012 | 1° 8' 55"LT | 842.331 | 421.1655 | 167 | 174 | 341 | 182 | 188 | 370 | 75°35'10.526"E | 28°54'8.214"N | 557155.56 | 3197300.672 |  | Siwani
[5 empty] | 424 | [15 empty] | METAL ROAD/SOLAR PANEL HT-3M/CART TRACK
39 |  | 5/1 | DA+6 | 54.15 |  | 13571.726 | 203.334 |  | 742.001 | 371.0005 | 251 | 183 | 434 | 238 | 174 | 412 | 75°35'12.854"E | 28°54'21.838"N | 557216.531 | 3197720.265 |  | Siwani
[5 empty] | 318.001 | [15 empty] | CART TRACK/PH HT-3.7M/11 KV LINE /NALI
40 |  | 5/2 | DA+3 | 51.15 |  | 13889.727 | 203.161 |  | 638 | 319 | 136 | 189 | 325 | 144 | 179 | 323 | 75°35'14.6"E | 28°54'32.056"N | 557262.26 | 3198034.961 |  | Siwani
[5 empty] | 319.999 | [15 empty] | METAL ROAD/11 KV LINE /PH HT-3.7M/NALI/11 KV LINE /CART TRACK
41 |  | 5/3 | DA+0 | 48.15 |  | 14209.726 | 202.307 |  | 663.999 | 331.9995 | 132 | 177 | 309 | 142 | 176 | 318 | 75°35'16.357"E | 28°54'42.338"N | 557308.276 | 3198351.634 |  | Dhani Ramjas
[5 empty] | 344 | [15 empty] | LT LINE /PH HT-3.7M/CART TRACK/NALI
42 |  | 5/4 | DA+0 | 48.15 |  | 14553.726 | 201.571 |  | 755 | 377.5 | 167 | 189 | 356 | 169 | 195 | 364 | 75°35'18.246"E | 28°54'53.391"N | 557357.743 | 3198692.059 |  | Dhani Ramjas
[5 empty] | 411 | [15 empty] | PH HT-3.7M/11 KV LINE/BORE
43 |  | 5/5 | DA+3 | 51.15 |  | 14964.726 | 201.57 |  | 804.887 | 402.4435 | 223 | 196 | 419 | 217 | 197 | 414 | 75°35'20.503"E | 28°55'6.597"N | 557416.845 | 3199098.788 |  | Siwani
[5 empty] | 393.887 | [15 empty] | CART TRACK/NALI/PH HT-3.7M/CART TRACK/11 KV LINE/METAL ROAD
44 |  | 5/6 | DA+3 | 51.15 |  | 15358.613 | 201.826 | 0° 34' 16"RT | 799.137 | 399.5685 | 199 | 221 | 420 | 198 | 215 | 413 | 75°35'22.667"E | 28°55'19.253"N | 557473.486 | 3199488.581 |  | Siwani
[5 empty] | 405.25 | [15 empty] | 11 KV LINE
45 | AP7/0 | 7/0 | DB2+0 | 46.87 |  | 15763.863 | 202.28 | 11° 27' 14"LT | 755.25 | 377.625 | 184 | 150 | 334 | 191 | 159 | 350 | 75°35'25.04"E | 28°55'32.254"N | 557535.756 | 3199889.018 |  | Dhani Ramjas
[5 empty] | 350 | [15 empty] | CART TRACK/NALI
46 |  | 7/1 | DA+3 | 51.15 |  | 16113.863 | 202.402 |  | 720.747 | 360.3735 | 201 | 197 | 398 | 191 | 193 | 384 | 75°35'24.515"E | 28°55'43.617"N | 557519.788 | 3200238.654 |  | Dhani Ramjas
[5 empty] | 370.747 | [15 empty] | 11 KV LINE/NALI/11 KV LINE /CANAL/CART TRACK
47 | AP8/0 | 8/0 | DB1+0 | 46.87 |  | 16484.61 | 204.281 | 2° 47' 8"LT | 746.747 | 373.3735 | 174 | 149 | 323 | 179 | 162 | 341 | 75°35'23.958"E | 28°55'55.653"N | 557502.873 | 3200609.014 |  | Dhani Ramjas
[5 empty] | 376 | [15 empty] | LT LINE /METAL ROAD/NALI/LT LINE /CART TRACK/NALI
48 |  | 8/1 | DA+6 | 54.15 |  | 16860.61 | 204.012 |  | 767 | 383.5 | 227 | 217 | 444 | 215 | 211 | 426 | 75°35'22.72"E | 28°56'7.822"N | 557467.485 | 3200983.345 |  | Dhani Ramjas
[5 empty] | 391 | [15 empty] | CART TRACK/11 KV LINE/NALI
49 |  | 8/2 | DA+3 | 51.15 |  | 17251.61 | 203.348 |  | 792 | 396 | 174 | 142 | 316 | 182 | 162 | 344 | 75°35'21.432"E | 28°56'20.476"N | 557430.686 | 3201372.609 |  | Dhani Ramjas
401
50 |  | 8/3 | DA+3 | 51.15 |  | 17652.61 | 213.589 |  | 803 | 401.5 | 260 | 213 | 473 | 241 | 210 | 451 | 75°35'20.112"E | 28°56'33.453"N | 557392.946 | 3201771.83 |  | Dhani Ramjas
[5 empty] | 402 | [15 empty] | SOLAR PANEL HT-3M
51 |  | 8/4 | DA+9 | 57.15 |  | 18054.61 | 205.511 |  | 844 | 422 | 189 | 244 | 433 | 194 | 237 | 431 | 75°35'18.788"E | 28°56'46.463"N | 557355.111 | 3202172.045 |  | Badwa
[5 empty] | 442 | [15 empty] | CART TRACK/PH HT-3.7M/11 KV LINE/POND/PH HT-3.7M
52 |  | 8/5 | DA+6 | 54.15 |  | 18496.61 | 204.197 |  | 829.599 | 414.7995 | 199 | 216 | 415 | 207 | 209 | 416 | 75°35'17.332"E | 28°57'0.768"N | 557313.512 | 3202612.083 |  | Badwa
[5 empty] | 387.599 | [15 empty] | 11 KV LINE/CANAL/CART TRACK/BORE/PH HT-3.7M
53 | AP9/0 | 9/0 | DC2+3 | 50.07 |  | 18884.209 | 203.961 | 23° 36' 23"RT | 801.599 | 400.7995 | 172 | 222 | 394 | 180 | 217 | 397 | 75°35'16.055"E | 28°57'13.312"N | 557277.033 | 3202997.962 |  | Badwa
[5 empty] | 414 | [15 empty] | NALA/LT LINE /PH HT-3.7M/NALI
54 |  | 9/1 | DA+0 | 48.15 |  | 19298.209 | 203.964 |  | 832 | 416 | 193 | 194 | 387 | 198 | 199 | 397 | 75°35'20.906"E | 28°57'26.069"N | 557406.38 | 3203391.237 |  | Badwa
418
55 |  | 9/2 | DA+3 | 51.15 |  | 19716.209 | 203.796 |  | 789.223 | 394.6115 | 225 | 190 | 415 | 220 | 189 | 409 | 75°35'25.804"E | 28°57'38.949"N | 557536.976 | 3203788.312 |  | Badwa
[5 empty] | 371.223 | [15 empty] | 33 KV LINE/METAL ROAD/11 KV LINE/HUT/CART TRACK END/11 KV LINE
56 | AP10/0 | 10/0 | DC1+3 | 50.07 |  | 20087.432 | 203.598 | 20° 7' 41"LT | 778.223 | 389.1115 | 182 | 181 | 363 | 183 | 189 | 372 | 75°35'30.154"E | 28°57'50.389"N | 557652.958 | 3204140.952 |  | Badwa
[5 empty] | 407 | [15 empty] | CART TRACK/11 KV LINE/NALI/SOLAR PANEL HT-3M
57 |  | 10/1 | DA+6 | 54.15 |  | 20494.432 | 204.142 |  | 784 | 392 | 226 | 224 | 450 | 219 | 212 | 431 | 75°35'29.724"E | 28°58'3.608"N | 557639.306 | 3204547.723 |  | Badwa
[5 empty] | 377 | [15 empty] | SOLAR PANEL HT-3M/CART TRACK/CANAL/BRIDGE/LT LINE/METAL ROAD/PH HT-3.7M
58 |  | 10/2 | DA+0 | 48.15 |  | 20871.432 | 204.467 |  | 782.674 | 391.337 | 154 | 189 | 343 | 166 | 194 | 360 | 75°35'29.327"E | 28°58'15.852"N | 557626.66 | 3204924.511 |  | Badwa
[5 empty] | 405.674 | [15 empty] | CART TRACK
59 | AP11/0 | 11/0 | DB1+3 | 49.87 |  | 21277.106 | 204.475 | 2° 10' 57"LT | 773.674 | 386.837 | 217 | 180 | 397 | 213 | 182 | 395 | 75°35'28.899"E | 28°58'29.028"N | 557613.052 | 3205329.956 |  | Badwa
[5 empty] | 368 | [15 empty] | LT LINE /CART TRACK
60 |  | 11/1 | DA+3 | 51.15 |  | 21645.106 | 204.526 |  | 795 | 397.5 | 188 | 212 | 400 | 187 | 213 | 400 | 75°35'27.993"E | 28°58'40.959"N | 557586.71 | 3205697.012 |  | Badwa
[5 empty] | 427 | [15 empty] | CART TRACK/NALA/CART TRACK
61 |  | 11/2 | DA+3 | 51.15 |  | 22072.106 | 204.826 |  | 828 | 414 | 215 | 203 | 418 | 215 | 202 | 417 | 75°35'26.943"E | 28°58'54.802"N | 557556.145 | 3206122.917 |  | Badwa
[5 empty] | 401 | [15 empty] | CART TRACK
62 |  | 11/3 | DA+3 | 51.15 |  | 22473.106 | 204.481 |  | 814 | 407 | 199 | 208 | 407 | 200 | 208 | 408 | 75°35'25.956"E | 28°59'7.803"N | 557527.442 | 3206522.888 |  | Chaudhariwas | Hisar |  | Hisar
[5 empty] | 413 | [15 empty] | BRICK ROAD/METAL ROAD
63 |  | 11/4 | DA+3 | 51.15 |  | 22886.106 | 204.243 |  | 816.193 | 408.0965 | 205 | 222 | 427 | 206 | 216 | 422 | 75°35'24.939"E | 28°59'21.192"N | 557497.879 | 3206934.829 |  | Chaudhariwas
[5 empty] | 403.193 | [15 empty] | NALI/PH HT-3.7M/NALI
64 | AP12/0 | 12/0 | DB2+0 | 46.87 |  | 23289.299 | 204.279 | 10° 58' 26"RT | 836.667 | 418.3335 | 181 | 186 | 367 | 188 | 197 | 385 | 75°35'23.947"E | 28°59'34.264"N | 557469.018 | 3207336.987 |  | Chaudhariwas
[5 empty] | 433.474 | [15 empty] | LT LINE
65 |  | 12/1 | DA+6 | 54.15 |  | 23722.773 | 203.482 |  | 772 | 386 | 248 | 166 | 414 | 238 | 167 | 405 | 75°35'25.942"E | 28°59'48.238"N | 557520.862 | 3207767.35 |  | Chaudhariwas
[5 empty] | 338.526 | [15 empty] | CART TRACK/NALI/BORE/CART TRACK/PH HT-3.7M
66 |  | 12/2 | DA+6 | 54.15 |  | 24061.299 | 203.956 |  | 756.526 | 378.263 | 173 | 247 | 420 | 172 | 235 | 407 | 75°35'27.501"E | 28°59'59.152"N | 557561.35 | 3208103.446 |  | Chaudhariwas
[5 empty] | 418 | [15 empty] | 11 KV LINE/BRICK ROAD/POND/NALI
67 |  | 12/3 | DA+0 | 48.15 |  | 24479.299 | 203.193 |  | 830 | 415 | 172 | 172 | 344 | 185 | 184 | 369 | 75°35'29.425"E | 29°0'12.628"N | 557611.343 | 3208518.445 |  | Chaudhariwas
[5 empty] | 412 | [15 empty] | LT CABLE LINE/METAL ROAD/11 KV LINE/CART TRACK
68 |  | 12/4 | DA+6 | 54.15 |  | 24891.299 | 203.222 |  | 837 | 418.5 | 240 | 212 | 452 | 229 | 213 | 442 | 75°35'31.322"E | 29°0'25.911"N | 557660.618 | 3208927.488 |  | Chaudhariwas
[5 empty] | 425 | [15 empty] | 11KV LINE/NALI/PH
69 |  | 12/5 | DA+6 | 54.15 |  | 25316.299 | 203.301 |  | 786 | 393 | 213 | 213 | 426 | 213 | 202 | 415 | 75°35'33.279"E | 29°0'39.612"N | 557711.449 | 3209349.437 |  | Chaudhariwas
[5 empty] | 361 | [15 empty] | 11 KV LINE/METAL ROAD/LT LINE
70 |  | 12/6 | DA+0 | 48.15 |  | 25677.299 | 204.309 |  | 763.251 | 381.6255 | 149 | 149 | 298 | 160 | 167 | 327 | 75°35'34.942"E | 29°0'51.25"N | 557754.624 | 3209707.846 |  | Chaudhariwas
[5 empty] | 402.251 | [15 empty] | SOLAR PANEL HT-3M
71 | AP13/0 | 13/0 | DB2+9 | 55.87 |  | 26079.55 | 205.062 | 11° 32' 58"RT | 805.761 | 402.8805 | 254 | 235 | 489 | 237 | 225 | 462 | 75°35'36.794"E | 29°1'4.219"N | 557802.734 | 3210107.21 |  | Chaudhariwas
[5 empty] | 403.51 | [15 empty] | NALA/11KV LINE/NALA/LT LINE/METAL ROAD
72 | AP14/0 | 14/0 | DC1+3 | 50.07 |  | 26483.06 | 205.067 | 18° 40' 17"LT | 821.51 | 410.755 | 169 | 164 | 333 | 180 | 180 | 360 | 75°35'41.578"E | 29°1'16.637"N | 557930.225 | 3210490.05 |  | Chaudhariwas
418
73 |  | 14/1 | DA+0 | 48.15 |  | 26901.06 | 216.812 |  | 821 | 410.5 | 272 | 215 | 487 | 248 | 214 | 462 | 75°35'41.587"E | 29°1'29.569"N | 557928.379 | 3210908.0479 |  | Chaudhariwas
[5 empty] | 403 | [15 empty] | CART TRACK
74 |  | 14/2 | DA+6 | 54.15 |  | 27304.06 | 210.185 |  | 838 | 419 | 208 | 215 | 423 | 210 | 213 | 423 | 75°35'41.597"E | 29°1'43.313"N | 557926.6 | 3211311.042 |  | Chaudhariwas
415
75 |  | 14/3 | DA+3 | 51.15 |  | 27719.06 | 211.93 |  | 800 | 400 | 201 | 198 | 399 | 203 | 196 | 399 | 75°35'41.607"E | 29°1'56.797"N | 557924.767 | 3211726.038 |  | Panihari Chak
[5 empty] | 385 | [15 empty] | LT END/POND/PH HT-4M
76 |  | 14/4 | DA+3 | 51.15 |  | 28104.06 | 211.087 |  | 763 | 381.5 | 188 | 217 | 405 | 190 | 208 | 398 | 75°35'41.615"E | 29°2'9.306"N | 557923.067 | 3212111.034 |  | Panihari Chak
[5 empty] | 378 | [15 empty] | METAL ROAD/LT LINE CABLE
77 |  | 14/5 | DA+0 | 48.15 |  | 28482.06 | 209.647 |  | 748.903 | 374.4515 | 162 | 196 | 358 | 171 | 193 | 364 | 75°35'41.624"E | 29°2'21.588"N | 557921.398 | 3212489.031 |  | Panihari Chak
[5 empty] | 370.903 | [15 empty] | POND/SOLAR PANEL HT-3M/11 KV LINE
78 | AP15/0 | 15/0 | DB2+0 | 46.87 |  | 28852.963 | 208.61 | 12° 12' 0"RT | 740.903 | 370.4515 | 175 | 193 | 368 | 179 | 191 | 370 | 75°35'41.633"E | 29°2'33.64"N | 557919.76 | 3212859.93 |  | Panihari Chak
[5 empty] | 370 | [15 empty] | BRICK ROAD
79 |  | 15/1 | DA+0 | 48.15 |  | 29222.963 | 206.669 |  | 805.958 | 402.979 | 177 | 196 | 373 | 180 | 204 | 384 | 75°35'44.532"E | 29°2'45.389"N | 557996.353 | 3213221.916 |  | Panihari Chak
[5 empty] | 435.958 | [15 empty] | 11 KV LINE /BRICK ROAD
80 | AP15A/0 | 15A/0 | DC2+6 | 53.07 |  | 29658.921 | 205.305 | 25° 32' 47"LT | 842.969 | 421.4845 | 240 | 189 | 429 | 234 | 194 | 428 | 75°35'47.949"E | 29°2'59.232"N | 558086.6 | 3213648.43 |  | Panihari Chak
[5 empty] | 407.011 | [15 empty] | ROHTAK -PANIPAT PIPELINE/METAL ROAD/11 KV LINE/NALI/CART TRACK
81 | AP15B/0 | 15B/0 | DC1+9 | 56.07 |  | 30065.932 | 205.38 | 21° 4' 8"RT | 822.011 | 411.0055 | 218 | 254 | 472 | 215 | 240 | 455 | 75°35'44.484"E | 29°3'12.101"N | 557990.9 | 3214044.03 |  | Panihari Chak
[5 empty] | 415 | [15 empty] | CART TRACK
82 |  | 15B/1 | DA+0 | 48.15 |  | 30480.932 | 205.565 |  | 810.995 | 405.4975 | 162 | 181 | 343 | 177 | 187 | 364 | 75°35'46.556"E | 29°3'25.462"N | 558049.5802 | 3214455.508 |  | Panihari Chak
[5 empty] | 395.995 | [15 empty] | METAL ROAD/NALA/CART TRACK/NALI
83 |  | 15B/2 | DA+3 | 51.15 |  | 30876.927 | 205.602 |  | 800 | 400 | 216 | 221 | 437 | 210 | 215 | 425 | 75°35'48.533"E | 29°3'38.211"N | 558105.4057 | 3214846.9681 |  | Panihari Chak
[5 empty] | 404.005 | [15 empty] | PH HT-4M/NALI
84 |  | 15B/3 | DA+0 | 48.15 |  | 31280.932 | 205.294 |  | 799.005 | 399.5025 | 184 | 163 | 347 | 190 | 175 | 365 | 75°35'50.55"E | 29°3'51.217"N | 558155.0817 | 3215248.073 |  | Panihari Chak
[5 empty] | 395 | [17 empty] | Balsamand
85 |  | 15B/4 | DA+6 | 54.15 |  | 31675.932 | 205.248 |  | 818.118 | 409.059 | 232 | 247 | 479 | 221 | 236 | 457 | 75°35'52.523"E | 29°4'3.934"N | 558203.5646 | 3215639.544 |  | Rawalwas kalan
[5 empty] | 423.118 | [15 empty] | NALI/CART TRACK
86 | AP16/0 | 16/0 | DC2+0 | 47.07 |  | 32099.05 | 205.167 | 27° 27' 50"RT | 799.118 | 399.559 | 177 | 184 | 361 | 189 | 186 | 375 | 75°35'54.636"E | 29°4'17.556"N | 558255.211 | 3216059.894 |  | Rawalwas kalan
[5 empty] | 376 | [15 empty] | 11 KV LINE/CART TRACK/CART TRACK/METAL ROAD/SAMADHI HT .5M/NALI
87 |  | 16/1 | DA+0 | 48.15 |  | 32475.05 | 205.413 |  | 803.627 | 401.8135 | 192 | 184 | 376 | 191 | 194 | 385 | 75°36'2.657"E | 29°4'27.536"N | 558470.519 | 3216368.145 |  | Rawalwas kalan
[5 empty] | 427.627 | [15 empty] | LT LINE/NALI/LTTPOINT/CART TRACK
88 | AP17/0 | 17/0 | DC2+6 | 53.07 |  | 32902.677 | 205.377 | 23° 50' 3"LT | 844.627 | 422.3135 | 244 | 237 | 481 | 235 | 228 | 463 | 75°36'11.78"E | 29°4'38.886"N | 558715.39 | 3216718.72 |  | Dhiranwas
[5 empty] | 417 | [15 empty] | LT LINE/BRICK ROAD/CART TRACK
89 |  | 17/1 | DA+0 | 48.15 |  | 33319.677 | 205.903 |  | 799 | 399.5 | 181 | 192 | 373 | 190 | 192 | 382 | 75°36'14.827"E | 29°4'52.168"N | 558795.669 | 3217127.92 |  | Dhiranwas
[5 empty] | 382 | [15 empty] | CART TRACK
90 |  | 17/2 | DA+0 | 48.15 |  | 33701.677 | 205.748 |  | 748 | 374 | 190 | 165 | 355 | 191 | 171 | 362 | 75°36'17.618"E | 29°5'4.335"N | 558869.209 | 3217502.774 |  | Dhiranwas
[5 empty] | 366 | [15 empty] | NALI/LT LINE/BORE/CART TRACK/NALI
91 |  | 17/3 | DA+6 | 51.15 |  | 34067.677 | 205.66 |  | 812.464 | 406.232 | 201 | 194 | 395 | 196 | 204 | 400 | 75°36'20.293"E | 29°5'15.993"N | 558939.669 | 3217861.928 |  | Dhiranwas
[5 empty] | 446.464 | [15 empty] | 11 KV LINE/PH HT-4M/LT LINE /METAL ROAD/11 KV LINE /CANAL/NALI
92 | AP19/0 | 19/0 | DC2+9 | 56.07 |  | 34514.141 | 205.824 | 28° 47' 34"LT | 854.464 | 427.232 | 253 | 254 | 507 | 244 | 237 | 481 | 75°36'23.556"E | 29°5'30.213"N | 559025.62 | 3218300.04 |  | Dhiranwas
[5 empty] | 408 | [15 empty] | BRICK ROAD
93 |  | 19/1 | DA+0 | 48.15 |  | 34922.141 | 205.824 |  | 815 | 407.5 | 155 | 186 | 341 | 172 | 193 | 365 | 75°36'19.042"E | 29°5'42.863"N | 558901.621 | 3218688.741 |  | Dhiranwas
[5 empty] | 407 | [15 empty] | 11 KV LINE/METAL ROAD/33 KV LINE
94 |  | 19/2 | DA+3 | 51.15 |  | 35329.141 | 205.861 |  | 757 | 378.5 | 221 | 177 | 398 | 216 | 177 | 393 | 75°36'14.54"E | 29°5'55.482"N | 558777.925 | 3219076.488 |  | Dhiranwas
[5 empty] | 350 | [15 empty] | 11 KV LINE/METAL ROAD/11 KV LINE/CART TRACK |  | Hisar
95 |  | 19/3 | DA+3 | 51.15 |  | 35679.141 | 205.596 |  | 726.934 | 363.467 | 173 | 227 | 400 | 174 | 214 | 388 | 75°36'10.668"E | 29°6'6.334"N | 558671.553 | 3219409.933 |  | Rawalwas Khurd
[5 empty] | 376.934 | [15 empty] | NALA/CART TRACK/LT LINE/NALA
96 | AP20/0 | 20/0 | DC2-3 | 44.07 |  | 36056.075 | 205.792 | 25° 18' 60"RT | 731.934 | 365.967 | 150 | 157 | 307 | 164 | 165 | 329 | 75°36'6.498"E | 29°6'18.021"N | 558556.995 | 3219769.037 |  | Rawalwas Khurd
[5 empty] | 355 | [15 empty] | CART TRACK/NALA
97 |  | 20/1 | DA+0 | 48.15 |  | 36411.075 | 205.465 |  | 738 | 369 | 199 | 174 | 373 | 191 | 181 | 372 | 75°36'8.307"E | 29°6'29.445"N | 558604.09 | 3220120.899 |  | Rawalwas Khurd
[5 empty] | 383 | [15 empty] | CART TRACK/NALA
98 |  | 20/2 | DA+3 | 51.15 |  | 36794.075 | 205.307 |  | 713.223 | 356.6115 | 210 | 195 | 405 | 203 | 184 | 387 | 75°36'10.258"E | 29°6'41.771"N | 558654.899 | 3220500.514 |  | Rawalwas Khurd
[5 empty] | 330.223 | [15 empty] | CART TRACK/11KV LIN3/METAL ROAD/11KV LINE
99 | AP21/0 | 21/0 | DB2+0 | 46.87 |  | 37124.298 | 204.867 | 2° 26' 40"LT | 707.223 | 353.6115 | 136 | 182 | 318 | 147 | 185 | 332 | 75°36'11.941"E | 29°6'52.398"N | 558698.707 | 3220827.818 |  | Nathuwana
[5 empty] | 377 | [15 empty] | NALA
100 |  | 21/1 | DA+0 | 48.15 |  | 37501.298 | 205.275 |  | 759 | 379.5 | 195 | 192 | 387 | 193 | 192 | 385 | 75°36'13.272"E | 29°7'4.592"N | 558732.737 | 3221203.279 |  | Nathuwana
382
101 |  | 21/2 | DA+0 | 48.15 |  | 37883.298 | 205.224 |  | 762 | 381 | 191 | 189 | 380 | 191 | 189 | 380 | 75°36'14.62"E | 29°7'16.947"N | 558767.218 | 3221583.72 |  | Hindwan
[5 empty] | 380 | [15 empty] | NALA
102 |  | 21/3 | DA+0 | 48.15 |  | 38263.298 | 205.478 |  | 756 | 378 | 192 | 186 | 378 | 192 | 187 | 379 | 75°36'15.961"E | 29°7'29.237"N | 558801.519 | 3221962.169 |  | Hindwan
[5 empty] | 376 | [15 empty] | NALA/BRICK ROAD
103 |  | 21/4 | DA+0 | 48.15 |  | 38639.298 | 205.823 |  | 766 | 383 | 190 | 174 | 364 | 190 | 182 | 372 | 75°36'17.288"E | 29°7'41.399"N | 558835.458 | 3222336.634 |  | Hindwan
[5 empty] | 390 | [15 empty] | CART TRACK/11KV LINE/CART TRACK/CANAL
104 |  | 21/5 | DA+3 | 51.15 |  | 39029.298 | 206.34 |  | 787 | 393.5 | 216 | 219 | 435 | 209 | 212 | 421 | 75°36'18.665"E | 29°7'54.012"N | 558870.662 | 3222725.042 |  | Hindwan
[5 empty] | 397 | [15 empty] | CART TRACK
105 |  | 21/6 | DA+0 | 48.15 |  | 39426.298 | 206 |  | 777 | 388.5 | 179 | 170 | 349 | 186 | 178 | 364 | 75°36'20.066"E | 29°8'6.853"N | 558906.497 | 3223120.421 |  | Hindwan
[5 empty] | 380 | [15 empty] | NALA/CART TRACK
106 |  | 21/7 | DA+3 | 51.15 |  | 39806.298 | 206.217 |  | 778 | 389 | 210 | 215 | 425 | 203 | 210 | 413 | 75°36'21.407"E | 29°8'19.143"N | 558940.798 | 3223498.87 |  | Shahpur
[5 empty] | 398 | [15 empty] | NALI/BRICK ROAD/NALI
107 |  | 21/8 | DA+0 | 48.15 |  | 40204.298 | 206.603 |  | 760.442 | 380.221 | 184 | 208 | 392 | 190 | 199 | 389 | 75°36'22.813"E | 29°8'32.016"N | 558976.723 | 3223895.245 |  | Shahpur
[5 empty] | 362.442 | [15 empty] | BORE/NALI
108 | AP23/0 | 23/0 | DB1-3 | 43.87 |  | 40566.74 | 206.06 | 4° 5' 16"LT | 710.442 | 355.221 | 154 | 160 | 314 | 164 | 165 | 329 | 75°36'24.092"E | 29°8'43.738"N | 559009.439 | 3224256.207 |  | Shahpur
[5 empty] | 348 | [15 empty] | CART TRACK/11KV LINE/CART TRACK/CANAL/BORE
109 |  | 23/1 | DA-1.5 | 46.65 |  | 40914.74 | 205.989 |  | 720 | 360 | 188 | 176 | 364 | 183 | 180 | 363 | 75°36'24.404"E | 29°8'55.042"N | 559016.065 | 3224604.144 |  | Shahpur
[5 empty] | 372 | [15 empty] | PUMP HOUSE/NALI/CART TRACK
110 |  | 23/2 | DA+0 | 48.15 |  | 41286.74 | 206.031 |  | 794 | 397 | 196 | 182 | 378 | 193 | 193 | 386 | 75°36'24.737"E | 29°9'7.125"N | 559023.148 | 3224976.076 |  | Shahpur
[5 empty] | 422 | [15 empty] | PUMP HOUSE
111 |  | 23/3 | DA+6 | 54.15 |  | 41708.74 | 205.313 |  | 842 | 421 | 241 | 247 | 488 | 231 | 234 | 465 | 75°36'25.115"E | 29°9'20.833"N | 559031.184 | 3225398 |  | Shahpur
[5 empty] | 420 | [15 empty] | 11KV LINE/BRICK ROAD/11KV LINE
112 |  | 23/4 | DA+0 | 48.15 |  | 42128.74 | 204.796 |  | 778.141 | 389.0705 | 174 | 164 | 338 | 187 | 169 | 356 | 75°36'25.491"E | 29°9'34.475"N | 559039.181 | 3225817.924 |  | Shahpur
[5 empty] | 358.141 | [15 empty] | 11KV LINE/BRICK ROAD
113 | AP24/0 | 24/0 | DB2+3 | 49.87 |  | 42486.881 | 204.74 | 11° 24' 18"LT | 824.141 | 412.0705 | 195 | 204 | 399 | 189 | 214 | 403 | 75°36'25.812"E | 29°9'46.108"N | 559046 | 3226176 |  | Shahpur
[5 empty] | 466 | [15 empty] | CART TRACK/NALI/11KV LINE/NALA
114 |  | 24/1 | DA+9 | 57.15 |  | 42952.881 | 203.977 |  | 786 | 393 | 263 | 204 | 467 | 253 | 189 | 442 | 75°36'22.811"E | 29°10'1.018"N | 558962.567 | 3226634.47 |  | Shahpur
[5 empty] | 320 | [15 empty] | BORE/PUMP HOUSE/LT LINE/LT LINE
115 |  | 24/2 | DA+3 | 51.15 |  | 43272.881 | 203.95 |  | 698.053 | 349.0265 | 116 | 215 | 331 | 131 | 207 | 338 | 75°36'20.75"E | 29°10'11.257"N | 558905.274 | 3226949.3 |  | Shahpur
[5 empty] | 378.053 | [15 empty] | 11 KV LINE/METAL ROAD/11 KV LINE/PUMP HOUSE/LT LINE/PUMP HOUSE
116 | AP25/0 | 25/0 | DB2+0 | 46.87 |  | 43650.934 | 203.364 | 9° 10' 0"RT | 789.053 | 394.5265 | 164 | 182 | 346 | 172 | 191 | 363 | 75°36'18.316"E | 29°10'23.353"N | 558837.587 | 3227321.244 |  | Mattarsham
[5 empty] | 411 | [15 empty] | BRICK ROAD/CART TRACK/LT LINE
117 |  | 25/1 | DA+3 | 51.15 |  | 44061.934 | 203.877 |  | 789 | 394.5 | 229 | 204 | 433 | 222 | 199 | 421 | 75°36'18.089"E | 29°10'36.705"N | 558829.359 | 3227732.162 |  | Mattarsham
[5 empty] | 378 | [15 empty] | 11 KV LINE/METAL ROAD/BORE/PUMP HOUSE
118 |  | 25/2 | DA+0 | 48.15 |  | 44439.934 | 204.494 |  | 779 | 389.5 | 175 | 174 | 349 | 180 | 183 | 363 | 75°36'17.881"E | 29°10'48.986"N | 558821.791 | 3228110.086 |  | Mattarsham
[5 empty] | 401 | [15 empty] | NALI/CART TRACK/
119 |  | 25/3 | DA+3 | 51.15 |  | 44840.934 | 206.088 |  | 801.805 | 400.9025 | 227 | 222 | 449 | 219 | 215 | 434 | 75°36'17.66"E | 29°11'2.013"N | 558813.763 | 3228511.005 |  | Mattarsham
[5 empty] | 400.805 | [15 empty] | CART TRACK
120 | AP26/0 | 26/0 | DB2+0 | 46.87 |  | 45241.739 | 206.093 | 14° 6' 28"RT | 750.805 | 375.4025 | 180 | 171 | 351 | 187 | 172 | 359 | 75°36'17.44"E | 29°11'15.034"N | 558805.739 | 3228911.73 |  | Mattarsham
[5 empty] | 350 | [15 empty] | METAL ROAD/CART TRACK/CANAL
121 |  | 26/1 | DA+0 | 48.15 |  | 45591.739 | 206.151 |  | 734 | 367 | 180 | 194 | 374 | 178 | 194 | 372 | 75°36'20.411"E | 29°11'26.103"N | 558884.238 | 3229252.813 |  | Mattarsham
[5 empty] | 384 | [15 empty] | NALI/CART TRACK
122 |  | 26/2 | DA+0 | 48.15 |  | 45975.739 | 205.791 |  | 814.959 | 407.4795 | 190 | 181 | 371 | 191 | 193 | 384 | 75°36'23.672"E | 29°11'38.247"N | 558970.362 | 3229627.031 |  | Mattarsham
[5 empty] | 430.959 | [15 empty] | NALI
123 | AP27/0 | 27/0 | DD60+6 | 53.97 |  | 46406.698 | 205.726 | 8° 36' 52"RT | 632.106 | 316.053 | 251 | 103 | 354 | 239 | 102 | 341 | 75°36'27.331"E | 29°11'51.877"N | 559067.018 | 3230047.011 |  | Neoli kalan
[5 empty] | 201.147 | [15 empty] | RAILWAY BOUNDARY/RAILWAY TRACK/RAILWAY BOUNDARY/METAL ROAD/NALI
124 | AP28/0 | 28/0 | DD60+6 | 53.97 |  | 46607.845 | 205.596 | 23° 21' 48"RT | 621.147 | 310.5735 | 99 | 246 | 345 | 100 | 234 | 334 | 75°36'30.106"E | 29°11'57.942"N | 559140.984 | 3230234.065 |  | Neoli kalan
420
125 |  | 28/1 | DA+0 | 48.15 |  | 47027.845 | 205.7 |  | 818.239 | 409.1195 | 175 | 183 | 358 | 187 | 189 | 376 | 75°36'41.149"E | 29°12'7.551"N | 559437.649 | 3230531.37 |  | Neoli kalan
[5 empty] | 398.239 | [15 empty] | 11 KV LINE/NALI
126 | AP28/2 | 28/2 | DA+3 | 51.15 |  | 47426.084 | 205.55 | 1° 35' 43"LT | 784 | 392 | 216 | 190 | 406 | 211 | 191 | 402 | 75°36'51.62"E | 29°12'16.663"N | 559718.943 | 3230813.27 |  | Neoli kalan
[5 empty] | 385.761 | [15 empty] | METAL ROAD/NALI
127 |  | 28/3 | DA+6 | 51.15 |  | 47811.845 | 206.029 |  | 759.761 | 379.8805 | 196 | 188 | 384 | 195 | 188 | 383 | 75°37'1.48"E | 29°12'25.733"N | 559983.715 | 3231093.818 |  | Neoli kalan
[5 empty] | 374 | [15 empty] | 11 KV LINE
128 |  | 28/4 | DA+3 | 51.15 |  | 48185.845 | 205.94 |  | 764.364 | 382.182 | 187 | 215 | 402 | 187 | 209 | 396 | 75°37'11.039"E | 29°12'34.526"N | 560240.415 | 3231365.813 |  | Neoli kalan
[5 empty] | 390.364 | [15 empty] | BRICK ROAD/CART TRACK/CART TRACK |  | Adampur
129 | AP29/0 | 29/0 | DC1+0 | 47.07 |  | 48576.209 | 205.99 | 21° 7' 53"LT | 767.364 | 383.682 | 175 | 183 | 358 | 182 | 185 | 367 | 75°37'21.018"E | 29°12'43.704"N | 560508.347 | 3231649.709 |  | Inchha kharkheri
[5 empty] | 377 | [15 empty] | LT LINE
130 |  | 29/1 | DA+0 | 48.15 |  | 48953.209 | 206.531 |  | 796 | 398 | 194 | 163 | 357 | 193 | 179 | 372 | 75°37'26.364"E | 29°12'55.019"N | 560650.863 | 3231998.733 |  | Inchha kharkheri
[5 empty] | 419 | [15 empty] | CART TRACK/11 KV LINE/CART TRACK/LT LINE/NALA/NALI
131 |  | 29/2 | DA+9 | 57.15 |  | 49372.209 | 206.071 |  | 839 | 419.5 | 257 | 243 | 500 | 242 | 233 | 475 | 75°37'32.307"E | 29°13'7.595"N | 560809.257 | 3232386.641 |  | Inchha kharkheri
[5 empty] | 420 | [15 empty] | BRICK ROAD
132 |  | 29/3 | DA+3 | 51.15 |  | 49792.209 | 206.079 |  | 834 | 417 | 177 | 191 | 368 | 189 | 197 | 386 | 75°37'38.265"E | 29°13'20.201"N | 560968.03 | 3232775.474 |  | Inchha kharkheri
[5 empty] | 414 | [15 empty] | CART TRACK/NALI/BRICK ROAD/11KV LINE
133 |  | 29/4 | DA+6 | 54.15 |  | 50206.209 | 206.027 |  | 833 | 416.5 | 224 | 244 | 468 | 219 | 233 | 452 | 75°37'44.137"E | 29°13'32.627"N | 561124.533 | 3233158.753 |  | Inchha kharkheri
[5 empty] | 419 | [15 empty] | CART TRACK/NALI
134 |  | 29/5 | DA+0 | 48.15 |  | 50625.209 | 205.819 |  | 790.669 | 395.3345 | 176 | 185 | 361 | 187 | 186 | 373 | 75°37'50.081"E | 29°13'45.203"N | 561282.927 | 3233546.661 |  | Kaijlan | Hisar
[5 empty] | 371.669 | [15 empty] | CART TRACK/PUMP HOUSE
135 | AP30/0 | 30/0 | DB2+0 | 46.87 |  | 50996.878 | 206.604 | 7° 0' 22"LT | 784.669 | 392.3345 | 192 | 190 | 382 | 190 | 196 | 386 | 75°37'55.354"E | 29°13'56.358"N | 561423.429 | 3233890.75 |  | Kaijlan
[5 empty] | 412 | [15 empty] | Nala, Cart track, Solar panel
136 |  | 30/1 | DA+3 | 51.15 |  | 51408.878 | 206.495 |  | 789 | 394.5 | 222 | 189 | 411 | 217 | 189 | 406 | 75°37'59.437"E | 29°14'9.256"N | 561531.5 | 3234288.323 |  | Durjanpur
[5 empty] | 377 | [15 empty] | 11kV lines, Metal road
137 |  | 30/2 | DA+3 | 51.15 |  | 51785.878 | 206.462 |  | 731 | 365.5 | 189 | 224 | 413 | 189 | 208 | 397 | 75°38'3.173"E | 29°14'21.059"N | 561630.39 | 3234652.122 |  | Durjanpur
[5 empty] | 354 | [15 empty] | Nala
138 |  | 30/3 | DA-3 | 45.15 |  | 52139.878 | 205.339 |  | 740 | 370 | 130 | 161 | 291 | 146 | 172 | 318 | 75°38'6.681"E | 29°14'32.141"N | 561723.248 | 3234993.726 |  | Durjanpur
[5 empty] | 386 | [15 empty] | 11kV lines, Cart track, Nala
139 |  | 30/4 | DA+3 | 51.15 |  | 52525.878 | 204.693 |  | 796 | 398 | 226 | 215 | 441 | 215 | 212 | 427 | 75°38'10.507"E | 29°14'44.225"N | 561824.499 | 3235366.21 |  | Durjanpur
[5 empty] | 410 | [15 empty] | Metal road, Nala
140 |  | 30/5 | DA+0 | 48.15 |  | 52935.878 | 206.028 |  | 816 | 408 | 196 | 185 | 381 | 199 | 191 | 390 | 75°38'14.571"E | 29°14'57.061"N | 561932.045 | 3235761.854 |  | Durjanpur
[5 empty] | 406 | [15 empty] | Cart track, Solar panel
141 |  | 30/6 | DA+3 | 51.15 |  | 53341.878 | 206.286 |  | 831 | 415.5 | 222 | 209 | 431 | 216 | 211 | 427 | 75°38'18.596"E | 29°15'9.771"N | 562038.542 | 3236153.637 |  | Durjanpur
[5 empty] | 425 | [15 empty] | Pump house
142 |  | 30/7 | DA+3 | 51.15 |  | 53766.878 | 207.01 |  | 825.252 | 412.626 | 217 | 202 | 419 | 216 | 202 | 418 | 75°38'22.809"E | 29°15'23.076"N | 562150.024 | 3236563.756 |  | Durjanpur
[5 empty] | 400.252 | [15 empty] | 11kV line, Nala
143 | AP31/0 | 31/0 | DB1+3 | 49.87 |  | 54167.13 | 206.645 | 5° 47' 32"LT | 738.252 | 369.126 | 199 | 189 | 388 | 200 | 182 | 382 | 75°38'26.777"E | 29°15'35.607"N | 562255.013 | 3236949.992 |  | Durjanpur
[5 empty] | 338 | [15 empty] | 11kV line, Nala
144 |  | 31/1 | DA+0 | 48.15 |  | 54505.13 | 206.877 |  | 740 | 370 | 149 | 182 | 331 | 157 | 190 | 347 | 75°38'28.893"E | 29°15'46.43"N | 562310.305 | 3237283.439 |  | Chickenwas
[5 empty] | 402 | [15 empty] | Pump house, Cart track
145 |  | 31/2 | DA+3 | 51.15 |  | 54907.13 | 207.07 |  | 781.885 | 390.9425 | 220 | 191 | 411 | 214 | 191 | 405 | 75°38'31.41"E | 29°15'59.304"N | 562376.066 | 3237680.024 |  | Chickenwas
[5 empty] | 379.885 | [15 empty] | Brick road, Cart track, LT line
146 | AP32/0 | 32/0 | DB2+3 | 49.87 |  | 55287.015 | 206.877 | 7° 20' 3"RT | 739.885 | 369.9425 | 190 | 199 | 389 | 190 | 193 | 383 | 75°38'33.789"E | 29°16'11.469"N | 562438.209 | 3238054.792 |  | Chickenwas
[5 empty] | 360 | [15 empty] | 11kV line
147 |  | 32/1 | DA+0 | 48.15 |  | 55647.015 | 207.005 |  | 791 | 395.5 | 161 | 183 | 344 | 168 | 195 | 363 | 75°38'37.704"E | 29°16'22.651"N | 562541.954 | 3238399.519 |  | Chickenwas
[5 empty] | 431 | [15 empty] | Cart track, Nala
148 |  | 32/2 | DA+6 | 54.15 |  | 56078.015 | 207.032 |  | 815 | 407.5 | 248 | 224 | 472 | 238 | 214 | 452 | 75°38'42.39"E | 29°16'36.038"N | 562666.161 | 3238812.234 |  | Chickenwas
[5 empty] | 384 | [15 empty] | 11kV lines, LT lines, Metal road
149 |  | 32/3 | DA+0 | 48.15 |  | 56462.015 | 207.808 |  | 795 | 397.5 | 161 | 192 | 353 | 171 | 197 | 368 | 75°38'46.567"E | 29°16'47.965"N | 562776.822 | 3239179.943 |  | Chickenwas
[5 empty] | 411 | [15 empty] | Nala, Cart track
150 |  | 32/4 | DA+3 | 51.15 |  | 56873.015 | 207.311 |  | 812.511 | 406.2555 | 220 | 217 | 437 | 216 | 212 | 428 | 75°38'51.037"E | 29°17'0.73"N | 562895.265 | 3239573.507 |  | Chickenwas
[5 empty] | 401.511 | [15 empty] | Brick road, Cart track
151 | AP33/0 | 33/0 | DD60+0 | 47.97 |  | 57274.526 | 207.554 | 55° 33' 18"RT | 648.181 | 324.0905 | 186 | 93 | 279 | 191 | 109 | 300 | 75°38'55.404"E | 29°17'13.201"N | 563010.973 | 3239957.984 |  | Chickenwas
[5 empty] | 246.67 | [15 empty] | NH-9, NH boundary, 11kV lines
152 | AP34/0 | 34/0 | DD60+3 | 49.87 |  | 57521.196 | 207.347 | 7° 4' 54"LT | 720.67 | 360.335 | 154 | 212 | 366 | 138 | 219 | 357 | 75°39'4.128"E | 29°17'15.595"N | 563245.971 | 3240032.963 |  | Chickenwas
474
153 | AP35/0 | 35/0 | DB1+9 | 55.87 |  | 57995.196 | 207.436 | 0° 12' 58"RT | 181.733 | 90.8665 | 263 | 84 | 347 | 257 | 89 | 346 | 75°39'20.123"E | 29°17'21.965"N | 563676.429 | 3240231.412 | WZ-4 | Chickenwas
[5 empty] | 181.733 | [15 empty] | 132 kV D/C TL HVPNL
154 | AP36/0 | 36/0 | 5DB1+9 | 56.35 |  | 58176.929 | 207.378 | 4° 25' 0"RT | 608.733 | 304.3665 | 97 | 240 | 337 | 93 | 233 | 326 | 75°39'26.266"E | 29°17'24.386"N | 563841.754 | 3240306.875 | WZ-5 | Chickenwas
[5 empty] | 427 | [15 empty] | Metal road, 11kV line
155 |  | 36/1 | 5DA+3 | 51.72 |  | 58603.929 | 206.716 |  | 838 | 419 | 188 | 187 | 375 | 196 | 193 | 389 | 75°39'41.157"E | 29°17'29.085"N | 564242.702 | 3240453.742 |  | Landhari sukh nambran
[5 empty] | 411 | [15 empty] | Nala, Cart track
156 |  | 36/2 | 5DA+6 | 54.72 |  | 59014.929 | 207.838 |  | 805 | 402.5 | 224 | 223 | 447 | 220 | 217 | 437 | 75°39'55.49"E | 29°17'33.607"N | 564628.626 | 3240595.105 |  | Landhari sukh nambran
[5 empty] | 394 | [15 empty] | Nala
157 |  | 36/3 | 5DA+0 | 48.72 |  | 59408.929 | 208.27 |  | 737 | 368.5 | 171 | 190 | 361 | 179 | 185 | 364 | 75°40'9.231"E | 29°17'37.941"N | 564998.587 | 3240730.622 |  | Landhari sukh nambran
[5 empty] | 343 | [15 empty] | Nala, Guava garden, Pond,Cart track
158 |  | 36/4 | 5DA-3 | 45.72 |  | 59751.929 | 207.911 |  | 690 | 345 | 154 | 128 | 282 | 159 | 141 | 300 | 75°40'21.193"E | 29°17'41.714"N | 565320.66 | 3240848.597 |  | Landhari sukh nambran
347
159 |  | 36/5 | 5DA+6 | 54.72 |  | 60098.929 | 207.56 |  | 764.552 | 382.276 | 220 | 219 | 439 | 208 | 217 | 425 | 75°40'33.295"E | 29°17'45.531"N | 565646.489 | 3240967.948 |  | Landhari sukh nambran
[5 empty] | 417.552 | [15 empty] | Metal road, Nala, 11kV line
160 | AP37/0 | 37/0 | 5DD45+3 | 51.45 |  | 60516.481 | 207.94 | 41° 21' 41"LT | 796.552 | 398.276 | 199 | 208 | 407 | 202 | 203 | 405 | 75°40'47.858"E | 29°17'50.123"N | 566038.565 | 3241111.565 |  | Thaska
[5 empty] | 379 | [15 empty] | Meta road, Cart track
161 |  | 37/1 | 5DA+0 | 48.72 |  | 60895.481 | 207.809 |  | 765.391 | 382.6955 | 172 | 138 | 310 | 177 | 154 | 331 | 75°40'54.638"E | 29°18'0.908"N | 566219.529 | 3241444.571 |  | Landhari sukh nambran
[5 empty] | 386.391 | [15 empty] | Cart track
162 | AP38/0 | 38/0 | 5DD45+18 | 66.45 |  | 61281.872 | 207.663 | 37° 56' 47"LT | 636.68 | 318.34 | 249 | 131 | 380 | 233 | 128 | 361 | 75°41'1.55"E | 29°18'11.903"N | 566404.022 | 3241784.071 |  | Nangthala
[5 empty] | 250.289 | [15 empty] | 132 kV SC KIR-ADP TL HVPNL
163 | AP39/0 | 39/0 | 5DC2+9 | 56.55 |  | 61532.161 | 208.022 | 26° 10' 18"RT | 606.289 | 303.1445 | 120 | 213 | 333 | 123 | 204 | 327 | 75°41'0.084"E | 29°18'19.933"N | 566363.033 | 3242030.981 |  | Landhari sukh nambran
356
164 |  | 39/1 | 5DA+3 | 51.72 |  | 61888.161 | 208.651 |  | 759 | 379.5 | 144 | 201 | 345 | 153 | 202 | 355 | 75°41'3.96"E | 29°18'30.99"N | 566465.607 | 3242371.883 |  | Nangthala
[5 empty] | 403 | [15 empty] | Nala, LT line, Brick road
165 |  | 39/2 | 5DA+3 | 51.72 |  | 62291.161 | 208.778 |  | 837.661 | 418.8305 | 202 | 198 | 400 | 203 | 203 | 406 | 75°41'8.348"E | 29°18'43.506"N | 566581.724 | 3242757.793 |  | Nangthala
434.661
166 | AP40/0 | 40/0 | 5DC1+18 | 65.55 |  | 62725.822 | 208.388 | 14° 59' 29"RT | 696.441 | 348.2205 | 238 | 52 | 290 | 233 | 91 | 324 | 75°41'13.081"E | 29°18'57.005"N | 566706.963 | 3243174.02 |  | Nangthala
[5 empty] | 261.78 | [15 empty] | 220 kV DCHISAR(MAYAR) - FATEHABAD TL HVPNL, Cart track, 11kV line
167 | AP41/0 | 41/0 | 5DB2+25 | 72.35 |  | 62987.602 | 207.656 | 10° 43' 15"LT | 648.384 | 324.192 | 210 | 248 | 458 | 171 | 233 | 404 | 75°41'18.235"E | 29°19'4.212"N | 566844.667 | 3243396.655 |  | Nangthala
[5 empty] | 386.604 | [15 empty] | 11kV lines, Metal road
168 | AP42/0 | 42/0 | 5DC2+6 | 53.55 |  | 63374.206 | 208.337 | 29° 27' 5"RT | 795.604 | 397.802 | 139 | 199 | 338 | 155 | 201 | 356 | 75°41'23.454"E | 29°19'15.91"N | 566983.32 | 3243757.54 |  | Nangthala
[5 empty] | 409 | [15 empty] | LT line, Cart track
169 |  | 42/1 | 5DA+6 | 54.72 |  | 63783.206 | 209.055 |  | 776.192 | 388.096 | 211 | 219 | 430 | 209 | 210 | 419 | 75°41'35.206"E | 29°19'24.308"N | 567298.771 | 3244017.87 |  | Nangthala
[5 empty] | 367.192 | [15 empty] | 11kV line, Cart track
170 | AP43/0 | 43/0 | 5DC1+0 | 47.55 |  | 64150.398 | 208.649 | 20° 29' 32"LT | 677.136 | 338.568 | 149 | 150 | 299 | 159 | 152 | 311 | 75°41'45.757"E | 29°19'31.846"N | 567581.976 | 3244251.59 |  | Nangthala
309.944
171 | AP44/0 | 44/0 | 5DD45+0 | 48.45 |  | 64460.342 | 208.372 | 31° 11' 54"LT | 665.944 | 332.972 | 160 | 176 | 336 | 158 | 177 | 335 | 75°41'51.558"E | 29°19'40.539"N | 567736.836 | 3244520.074 |  | Nangthala
[5 empty] | 356 | [15 empty] | 11kV lines, Metal road, Solar panel, 33kV lines, NH-10
172 |  | 44/1 | 5DA+0 | 48.72 |  | 64816.342 | 209.185 |  | 718 | 359 | 181 | 144 | 325 | 180 | 157 | 337 | 75°41'51.355"E | 29°19'52.104"N | 567729.242 | 3244875.993 |  | Nangthala
[5 empty] | 362 | [15 empty] | Brick road, 11kV line
173 |  | 44/2 | 5DA+6 | 54.72 |  | 65178.342 | 209.49 |  | 710.24 | 355.12 | 218 | 209 | 427 | 206 | 197 | 403 | 75°41'51.149"E | 29°20'3.864"N | 567721.521 | 3245237.911 |  | Nangthala
[5 empty] | 348.24 | [15 empty] | Pump house, LT lines, Metal road, 11kV lines
174 | AP45/0 | 45/0 | 5DD60+0 | 48.45 |  | 65526.582 | 209.511 | 46° 42' 2"RT | 745.24 | 372.62 | 140 | 174 | 314 | 152 | 181 | 333 | 75°41'50.95"E | 29°20'15.177"N | 567714.093 | 3245586.071 |  | Nangthala
[5 empty] | 397 | [15 empty] | Nala
175 |  | 45/1 | 5DA+6 | 54.72 |  | 65923.582 | 209.426 |  | 778 | 389 | 225 | 176 | 401 | 218 | 180 | 398 | 75°42'1.508"E | 29°20'24.166"N | 567997.149 | 3245864.439 |  | Nangthala
381
176 |  | 45/2 | 5DA+9 | 57.72 |  | 66304.582 | 209.57 |  | 789.451 | 394.7255 | 206 | 215 | 421 | 202 | 213 | 415 | 75°42'11.64"E | 29°20'32.793"N | 568268.796 | 3246131.587 |  | Nangthala
[5 empty] | 408.451 | [15 empty] | 11kV lines, LT line, Metal road, Cart track
177 | AP46/0 | 46/0 | 5DD45+6 | 54.45 |  | 66713.033 | 209.838 | 36° 9' 44"LT | 837.451 | 418.7255 | 194 | 215 | 409 | 197 | 216 | 413 | 75°42'22.503"E | 29°20'42.041"N | 568560.016 | 3246417.984 |  | Nangthala
[5 empty] | 429 | [15 empty] | 11kV line, Cart track, Canal, Pump house, Bore, Nala, LT line
178 |  | 46/1 | 5DA+6 | 54.72 |  | 67142.033 | 210.101 |  | 789.902 | 394.951 | 214 | 199 | 413 | 215 | 195 | 410 | 75°42'25.173"E | 29°20'55.781"N | 568629.464 | 3246841.325 |  | Nangthala
[5 empty] | 360.902 | [15 empty] | 11kV line, Cart track, Bore
179 | AP47/0 | 47/0 | 5DC1+3 | 50.55 |  | 67502.935 | 209.908 | 21° 54' 38"RT | 793.902 | 396.951 | 162 | 188 | 350 | 167 | 196 | 363 | 75°42'27.42"E | 29°21'7.341"N | 568687.888 | 3247197.467 |  | Nangthala
[5 empty] | 433 | [15 empty] | SOLAR PANEL HT-4M/LT LINE/NALI/BORE/NALI/CART TRACK/CART TRACK/CANAL/PH HT-4.2M
180 |  | 47/1 | 5DA+9 | 57.72 |  | 67935.935 | 210.461 |  | 840 | 420 | 246 | 243 | 489 | 239 | 234 | 473 | 75°42'35.828"E | 29°21'19.326"N | 568912.367 | 3247567.735 |  | Nangthala
407
181 |  | 47/2 | 5DA+0 | 48.72 |  | 68342.935 | 210.483 |  | 777 | 388.5 | 165 | 187 | 352 | 175 | 187 | 362 | 75°42'43.731"E | 29°21'30.592"N | 569123.368 | 3247915.769 |  | Sandol
[5 empty] | 370 | [15 empty] | CART TRACK
182 |  | 47/3 | 5DA+0 | 48.72 |  | 68712.935 | 210.155 |  | 745 | 372.5 | 184 | 173 | 357 | 184 | 177 | 361 | 75°42'50.917"E | 29°21'40.833"N | 569315.186 | 3248232.164 |  | Sandol
[5 empty] | 375 | [15 empty] | METAL ROAD/SOLAR PANEL HT-4M/CART TRACK
183 |  | 47/4 | 5DA+3 | 51.72 |  | 69087.935 | 210.291 |  | 795 | 397.5 | 203 | 198 | 401 | 199 | 202 | 401 | 75°42'58.2"E | 29°21'51.213"N | 569509.596 | 3248552.834 |  | Sandol
[5 empty] | 420 | [15 empty] | SOLAR PANEL HT-4M/NALI/PH HT-4.2M/BORE/NALI
184 |  | 47/5 | 5DA+6 | 54.72 |  | 69507.935 | 210.162 |  | 820 | 410 | 223 | 202 | 425 | 220 | 202 | 422 | 75°43'6.358"E | 29°22'2.838"N | 569727.336 | 3248911.985 |  | Kirmara
[5 empty] | 400 | [15 empty] | 11 KV LINE /NALI/BORE/
185 |  | 47/6 | 5DA+6 | 54.72 |  | 69907.935 | 209.715 |  | 818.466 | 409.233 | 198 | 226 | 424 | 199 | 222 | 421 | 75°43'14.128"E | 29°22'13.909"N | 569934.707 | 3249254.034 |  | Kirmara
[5 empty] | 418.466 | [15 empty] | BORE/BRICK ROAD/BORE/CART TRACK/HUT HT-2.3M
186 | AP48/0 | 48/0 | 5DB1+3 | 50.35 |  | 70326.401 | 209.587 | 4° 34' 39"RT | 715.466 | 357.733 | 193 | 160 | 353 | 198 | 157 | 355 | 75°43'22.256"E | 29°22'25.492"N | 570151.652 | 3249611.873 |  | Kirmara
[5 empty] | 297 | [15 empty] | CART TRACK/NALI
187 |  | 48/1 | 5DA+0 | 48.72 |  | 70623.401 | 210.099 |  | 750.982 | 375.491 | 138 | 118 | 256 | 141 | 147 | 288 | 75°43'28.757"E | 29°22'33.282"N | 570325.402 | 3249852.746 |  | Kirmara
453.982
188 | AP49/0 | 49/0 | 5DD60+30 | 78.45 |  | 71077.383 | 210.055 | 20° 14' 3"LT | 669.974 | 334.987 | 338 | 126 | 464 | 309 | 116 | 425 | 75°43'38.693"E | 29°22'45.191"N | 570590.99 | 3250220.935 | RC=2M | Kirmara
[5 empty] | 215.992 | [15 empty] | 400 KV DC KDR-FTP TL HVPN
189 | AP50/0 | 50/0 | 5DD60+30 | 78.45 |  | 71293.375 | 210.617 | 24° 32' 20"RT | 652.992 | 326.496 | 90 | 321 | 411 | 101 | 295 | 396 | 75°43'40.892"E | 29°22'51.939"N | 570648.966 | 3250429.001 |  | Kirmara
[5 empty] | 442 | [15 empty] | BRICK ROAD/11 KV LINE /METAL ROAD/11 KV LINE/HUT HT-2.3M/NALI/CART TRACK
190 |  | 50/1 | 5DA+0 | 48.72 |  | 71735.375 | 211.553 |  | 827.998 | 413.999 | 101 | 164 | 265 | 133 | 172 | 305 | 75°43'51.51"E | 29°23'2.86"N | 570933.72 | 3250767.05 |  | Kirmara
[5 empty] | 390.998 | [15 empty] | BORE/CANALBORE/CART TRACK/11 KV LINE
191 |  | 50/2 | 5DA+6 | 54.72 |  | 72126.373 | 211.694 |  | 778 | 389 | 224 | 194 | 418 | 217 | 194 | 411 | 75°44'0.827"E | 29°23'12.405"N | 571182.399 | 3251062.27 |  | Kirmara
[5 empty] | 387.002 | [15 empty] | CART TRACK/11 KV LINE/SOLAR PANEL HT-4M/PH HT-4.2M
192 |  | 50/3 | 5DA+6 | 54.72 |  | 72513.375 | 211.674 |  | 772.378 | 386.189 | 194 | 194 | 388 | 194 | 194 | 388 | 75°44'10.145"E | 29°23'21.97"N | 571431.723 | 3251358.257 |  | Kirmara
[5 empty] | 385.376 | [15 empty] | SOLAR PANEL HT-4M/NALI/11 KV LINE /BRICK ROAD/METAL ROAD |  | Uklana
193 | AP51/0 | 51/0 | 5DB2+6 | 53.35 |  | 72898.751 | 212.095 | 10° 35' 5"LT | 794.376 | 397.188 | 192 | 216 | 408 | 192 | 214 | 406 | 75°44'19.425"E | 29°23'31.495"N | 571680 | 3251653 |  | Kanoh
[5 empty] | 409 | [15 empty] | BORE/NALI/CART TRACK
194 |  | 51/1 | 5DA+3 | 51.72 |  | 73307.751 | 211.891 |  | 794 | 397 | 194 | 191 | 385 | 197 | 191 | 388 | 75°44'26.986"E | 29°23'43.016"N | 571881.552 | 3252008.89 |  | Kanoh
[5 empty] | 385 | [15 empty] | HUT HT-2.3M/CART TRACK/CANAL
195 |  | 51/2 | 5DA+3 | 51.72 |  | 73692.751 | 212.378 |  | 751 | 375.5 | 195 | 195 | 390 | 195 | 192 | 387 | 75°44'34.104"E | 29°23'53.861"N | 572071.277 | 3252343.897 |  | Kanoh
[5 empty] | 366 | [15 empty] | BORE/PH HT-4M/NALI
196 |  | 51/3 | 5DA+0 | 48.72 |  | 74058.751 | 212.97 |  | 764 | 382 | 171 | 176 | 347 | 175 | 183 | 358 | 75°44'40.871"E | 29°24'4.17"N | 572251.639 | 3252662.37 |  | Nehla | Bhuna |  | Fatehabad
[5 empty] | 398 | [15 empty] | CART TRACK/11 KV LINE
197 |  | 51/4 | 5DA+6 | 54.72 |  | 74456.751 | 212.021 |  | 834 | 417 | 223 | 220 | 443 | 217 | 220 | 437 | 75°44'48.23"E | 29°24'15.381"N | 572447.771 | 3253008.689 |  | Nehla
[5 empty] | 436 | [15 empty] | CART TRACK/SOLAR PANEL HT-4M/NALI/METAL ROAD/BORE/SOLAR PANEL HT-4M
198 |  | 51/5 | 5DA+6 | 54.72 |  | 74892.751 | 211.661 |  | 816.514 | 408.257 | 217 | 206 | 423 | 218 | 202 | 420 | 75°44'56.292"E | 29°24'27.662"N | 572662.628 | 3253388.073 |  | Nehla
[5 empty] | 380.514 | [15 empty] | TEMPLE HT-2M/METAL ROAD/11 KV LINE
199 | AP52/0 | 52/0 | 5DB1+3 | 50.35 |  | 75273.265 | 212.078 | 6° 52' 47"RT | 763.514 | 381.757 | 175 | 204 | 379 | 179 | 201 | 380 | 75°45'3.329"E | 29°24'38.38"N | 572850.143 | 3253719.176 |  | Nehla
[5 empty] | 383 | [15 empty] | CART TRACK/BRICK ROAD/CART TRACK
200 |  | 52/1 | 5DA+0 | 48.72 |  | 75656.265 | 211.953 |  | 745.419 | 372.7095 | 180 | 181 | 361 | 184 | 182 | 366 | 75°45'11.837"E | 29°24'48.347"N | 573074.8492 | 3254029.3143 |  | Nehla
[5 empty] | 362.419 | [15 empty] | NALI/BORE/BRICK ROAD/PIPAL TREE HT-12M
201 |  | 52/2 | 5DA+0 | 48.72 |  | 76018.684 | 212.003 | 0°42'21"RT | 741 | 370.5 | 182 | 193 | 375 | 182 | 192 | 374 | 75°45'19.888"E | 29°24'57.779"N | 573287.528 | 3254322.8508 |  | Nehla
[5 empty] | 378.581 | [15 empty] | TEMPLE HT-1.5M/
202 |  | 52/3 | 5DA+0 | 48.72 |  | 76397.265 | 211.409 |  | 739.581 | 369.7905 | 187 | 183 | 370 | 188 | 183 | 371 | 75°45'28.299"E | 29°25'7.631"N | 573513.4056 | 3254626.6573 |  | Nehla
[5 empty] | 361 | [15 empty] | BORE/CART TRACK/NALI/CART TRACK/SOLAR PANEL HT-4M
203 |  | 52/4 | 5DA+0 | 48.72 |  | 76758.265 | 210.941 |  | 733 | 366.5 | 178 | 185 | 363 | 179 | 186 | 365 | 75°45'36.319"E | 29°25'17.025"N | 573728.7954 | 3254916.3574 |  | Nehla
372
204 |  | 52/5 | 5DA+0 | 48.72 |  | 77130.265 | 211.129 |  | 815.274 | 407.637 | 187 | 149 | 336 | 187 | 170 | 357 | 75°45'44.585"E | 29°25'26.705"N | 573950.7485 | 3255214.8853 |  | Nehla
[5 empty] | 443.274 | [15 empty] | CART TRACK/NALI/METAL ROAD/CART TRACK/LT NEW POL
205 | AP53/0 | 53/0 | 5DC1+18 | 65.55 |  | 77573.539 | 210.798 | 18° 17' 30"RT | 630.073 | 315.0365 | 296 | 67 | 363 | 275 | 84 | 359 | 75°45'54.434"E | 29°25'38.24"N | 574215.295 | 3255570.56 |  | Nehla
[5 empty] | 186.799 | [15 empty] | NALI/CART TRACK/220 KV D/C KIRORI-BHUNA TL HVPN
206 | AP54/0 | 54/0 | 5DD45+25 | 73.45 |  | 77760.338 | 211.646 | 30° 0' 31"LT | 609.799 | 304.8995 | 120 | 291 | 411 | 103 | 270 | 373 | 75°46'0.118"E | 29°25'41.715"N | 574367.74 | 3255678.515 |  | Nehla
[5 empty] | 423 | [15 empty] | 11 KV LINE/
207 |  | 54/1 | 5DA+0 | 48.72 |  | 78183.338 | 211.95 |  | 781 | 390.5 | 133 | 179 | 312 | 155 | 179 | 334 | 75°46'6.769"E | 29°25'54.164"N | 574544.411 | 3256062.854 |  | Nehla
[5 empty] | 358 | [15 empty] | NALI/BORE/SOLAR PANEL HT-4M
208 |  | 54/2 | 5DA+0 | 48.72 |  | 78541.338 | 212.095 |  | 747 | 373.5 | 180 | 180 | 360 | 180 | 184 | 364 | 75°46'12.398"E | 29°26'4.7"N | 574693.934 | 3256388.134 |  | Nehla
[5 empty] | 389 | [15 empty] | NALI/CART TRACK
209 |  | 54/3 | 5DA+3 | 51.72 |  | 78930.338 | 212.289 |  | 816 | 408 | 210 | 202 | 412 | 206 | 205 | 411 | 75°46'18.514"E | 29°26'16.148"N | 574856.404 | 3256741.58 |  | Nehla
[5 empty] | 427 | [15 empty] | NALI/CART TRACK/NALI
210 |  | 54/4 | 5DA+6 | 54.72 |  | 79357.338 | 212.13 |  | 822 | 411 | 226 | 226 | 452 | 223 | 219 | 442 | 75°46'25.229"E | 29°26'28.714"N | 575034.746 | 3257129.553 |  | Nehla
[5 empty] | 395 | [15 empty] | CART TRACK
211 |  | 54/5 | 5DA+0 | 48.72 |  | 79752.338 | 212.088 |  | 768 | 384 | 170 | 186 | 356 | 178 | 186 | 364 | 75°46'31.441"E | 29°26'40.338"N | 575199.722 | 3257488.451 |  | Pabra | Uklana |  | Hisar
373
212 |  | 54/6 | 5DA+0 | 48.72 |  | 80125.338 | 212.302 |  | 765 | 382.5 | 188 | 169 | 357 | 188 | 177 | 365 | 75°46'37.307"E | 29°26'51.315"N | 575355.51 | 3257827.36 |  | Pabra
[5 empty] | 392 | [15 empty] | METAL ROAD/BORE/PH HT-4M
213 |  | 54/7 | 5DA+6 | 54.72 |  | 80517.338 | 212.137 |  | 790 | 395 | 224 | 211 | 435 | 217 | 208 | 425 | 75°46'43.473"E | 29°27'2.851"N | 575519.234 | 3258183.532 |  | Pabra
[5 empty] | 398 | [15 empty] | LT LINE /CART TRACK
214 |  | 54/8 | 5DA+3 | 51.72 |  | 80915.338 | 212.655 |  | 789.642 | 394.821 | 188 | 200 | 388 | 191 | 199 | 390 | 75°46'49.733"E | 29°27'14.564"N | 575685.463 | 3258545.156 |  | Pabra
[5 empty] | 391.642 | [15 empty] | CART TRACK/NALI/SOLAR PANEL HT-4M
215 | AP55/0 | 55/0 | 5DB2+3 | 50.35 |  | 81306.98 | 212.535 | 9° 2' 14"LT | 801.642 | 400.821 | 192 | 175 | 367 | 194 | 183 | 377 | 75°46'55.894"E | 29°27'26.089"N | 575849.037 | 3258901.003 |  | Pabra
[5 empty] | 410 | [15 empty] | CART TRACK/11 KV LINE/METAL ROAD/CART TRACK/PH HT-4M/NALI
216 |  | 55/1 | 5DA+9 | 57.72 |  | 81716.98 | 212.768 |  | 840 | 420 | 236 | 238 | 474 | 228 | 233 | 461 | 75°47'0.098"E | 29°27'38.891"N | 575959.638 | 3259295.803 |  | Pabra
[5 empty] | 430 | [15 empty] | NALI/HPCL (RAMANMANDI-BAHADURGARH ) PIPE LINE/SOLAR PANEL HT-4M/CART TRACK
217 |  | 55/2 | 5DA+3 | 51.72 |  | 82146.98 | 213.272 |  | 822 | 411 | 193 | 208 | 401 | 199 | 205 | 404 | 75°47'4.508"E | 29°27'52.318"N | 576075.634 | 3259709.862 |  | Pabra
[5 empty] | 392 | [15 empty] | SOLAR PANEL HT-4M/BRICK ROAD/NALI
218 |  | 55/3 | 5DA+0 | 48.72 |  | 82538.98 | 213.819 |  | 763.098 | 381.549 | 185 | 173 | 358 | 188 | 177 | 365 | 75°47'8.528"E | 29°28'4.558"N | 576181.38 | 3260087.33 |  | Pabra
[5 empty] | 371.098 | [15 empty] | BORE/PH HT-4M/SOLAR PANEL HT-4M/CART TRACK
219 |  | 55/4 | 5DA+3 | 51.72 |  | 82910.078 | 213.387 |  | 767 | 383.5 | 198 | 184 | 382 | 195 | 188 | 383 | 75°47'12.334"E | 29°28'16.145"N | 576281.487 | 3260444.671 |  | Pabra
[5 empty] | 404.9 | [15 empty] | BORE/SOLAR PANEL HT-4M/BORE
220 |  | 55/5 | 5DA+6 | 54.72 |  | 83314.978 | 213.499 |  | 806.902 | 403.451 | 212 | 217 | 429 | 209 | 215 | 424 | 75°47'16.395"E | 29°28'28.507"N | 576390.6347 | 3260834.7409 |  | Pabra
[5 empty] | 402 | [15 empty] | METAL ROAD/NALI
221 |  | 55/6 | 5DA+3 | 51.72 |  | 83716.978 | 213.967 |  | 821 | 410.5 | 195 | 179 | 374 | 198 | 186 | 384 | 75°47'20.611"E | 29°28'41.34"N | 576499.155 | 3261221.659 |  | Pabra
[5 empty] | 410 | [15 empty] | BORE/SOLAR PANEL HT-4M
222 |  | 55/7 | 5DA+9 | 57.72 |  | 84126.978 | 214.036 |  | 818.712 | 409.356 | 232 | 223 | 455 | 226 | 219 | 445 | 75°47'24.817"E | 29°28'54.142"N | 576609.756 | 3261616.46 |  | Pabra
[5 empty] | 408.712 | [15 empty] | NALI/11 KV LINE/METAL ROAD/BORE/11 KV LINE
223 | AP56/0 | 56/0 | 5DB1+6 | 53.35 |  | 84535.69 | 213.557 | 1° 59' 22"LT | 828.712 | 414.356 | 186 | 218 | 404 | 192 | 217 | 409 | 75°47'29.011"E | 29°29'6.904"N | 576720.01 | 3262010.02 |  | Pabra
420
224 |  | 56/1 | 5DA+3 | 51.72 |  | 84955.69 | 214.012 |  | 834 | 417 | 203 | 197 | 400 | 205 | 200 | 405 | 75°47'32.797"E | 29°29'20.141"N | 576819.2 | 3262418.139 |  | Pabra
[5 empty] | 414 | [15 empty] | BORE/CART TRACK
225 |  | 56/2 | 5DA+6 | 54.72 |  | 85369.69 | 213.38 |  | 813 | 406.5 | 218 | 212 | 430 | 215 | 209 | 424 | 75°47'36.529"E | 29°29'33.189"N | 576916.974 | 3262820.428 |  | Pabra
[5 empty] | 399 | [15 empty] | NALI/PH HT-4M/BRICK ROAD
226 |  | 56/3 | 5DA+3 | 51.72 |  | 85768.69 | 213.734 |  | 801 | 400.5 | 188 | 171 | 359 | 191 | 179 | 370 | 75°47'40.127"E | 29°29'45.764"N | 577011.204 | 3263208.141 |  | Pabra
[5 empty] | 402 | [15 empty] | CART TRACK/11 KV LINE /NALI/SOLAR PANEL HT-4M
227 |  | 56/4 | 5DA+9 | 57.72 |  | 86170.69 | 214.506 |  | 765.51 | 382.755 | 232 | 101 | 333 | 224 | 122 | 346 | 75°47'43.752"E | 29°29'58.433"N | 577106.144 | 3263598.77 |  | Chamar khera
[5 empty] | 363.51 | [15 empty] | CART TRACK/BORE/11 KV LINE
228 | AP57/0 | 57/0 | 5DD60+18 | 66.45 |  | 86534.2 | 214.606 | 39° 15' 3"RT | 564.111 | 282.0555 | 264 | 73 | 337 | 243 | 89 | 332 | 75°47'47.03"E | 29°30'9.89"N | 577191.993 | 3263951.997 |  | Chamar khera
[5 empty] | 200.601 | [15 empty] | 400 KV DC MGA-HISAR (I) TL PGCIL
229 | AP58/0 | 58/0 | 5DD60+18 | 66.45 |  | 86734.801 | 214.641 | 37° 31' 19"LT | 630 | 315 | 128 | 315 | 443 | 112 | 283 | 395 | 75°47'53.004"E | 29°30'13.784"N | 577352.013 | 3264072.97 |  | Chamar khera
[5 empty] | 430 | [15 empty] | Cart track
230 |  | 58/1 | 5DA+6 | 54.72 |  | 87164.801 | 215.092 |  | 793 | 396.5 | 116 | 212 | 328 | 149 | 202 | 351 | 75°47'57.347"E | 29°30'27.228"N | 577466.125 | 3264487.552 |  | Chamar khera
[5 empty] | 363 | [15 empty] | 11kV lines, Metal road, Nala
231 |  | 58/2 | 5DA+0 | 48.72 |  | 87527.801 | 215.751 |  | 671 | 335.5 | 152 | 174 | 326 | 162 | 168 | 330 | 75°48'1.015"E | 29°30'38.577"N | 577562.456 | 3264837.537 |  | Chamar khera
308
232 |  | 58/3 | 5DA-3 | 45.72 |  | 87835.801 | 215.716 |  | 655 | 327.5 | 134 | 158 | 292 | 141 | 163 | 304 | 75°48'4.126"E | 29°30'48.206"N | 577644.192 | 3265134.494 |  | Chamar khera
[5 empty] | 347 | [15 empty] | Pump house, Cart track
233 |  | 58/4 | 5DA+0 | 48.72 |  | 88182.801 | 215.455 |  | 700.269 | 350.1345 | 190 | 131 | 321 | 185 | 146 | 331 | 75°48'7.632"E | 29°30'59.054"N | 577736.278 | 3265469.052 |  | Chamar khera
353.269
234 | AP59/0 | 59/0 | 5DB1+9 | 56.35 |  | 88536.07 | 215.056 | 1° 30' 23"LT | 623.06 | 311.53 | 222 | 51 | 273 | 208 | 92 | 300 | 75°48'11.202"E | 29°31'10.099"N | 577830.027 | 3265809.654 |  | Chamar khera
[5 empty] | 269.791 | [15 empty] | 220kV line, 11kV line, Cart track
235 | AP60/0 | 60/0 | 5DB1+18 | 65.35 |  | 88805.861 | 215.189 | 6° 38' 6"RT | 532.966 | 266.483 | 219 | 268 | 487 | 178 | 201 | 379 | 75°48'13.674"E | 29°31'18.593"N | 577894.76 | 3266071.564 |  | Saniana | Tohana |  | Fatehabad
[5 empty] | 263.175 | [15 empty] | 132kv line, Metal road, Brick road, cart track
236 | AP61/0 | 61/0 | 5DB1+3 | 50.35 |  | 89069.036 | 215.842 | 3° 54' 29"LT | 655.175 | 327.5875 | -4 | 179 | 175 | 63 | 183 | 246 | 75°48'17.163"E | 29°31'26.58"N | 577987.002 | 3266318.044 |  | Saniana
[5 empty] | 392 | [15 empty] | 11kV lines, cart track, canal
237 |  | 61/1 | 5DA+6 | 54.72 |  | 89461.036 | 216.04 |  | 830 | 415 | 214 | 205 | 419 | 210 | 209 | 419 | 75°48'21.422"E | 29°31'38.758"N | 578099.056 | 3266693.687 |  | Saniana
[5 empty] | 438 | [15 empty] | Cart track, Pump house
238 |  | 61/2 | 5DA+9 | 57.72 |  | 89899.036 | 216.493 |  | 807.977 | 403.9885 | 234 | 232 | 466 | 231 | 221 | 452 | 75°48'26.182"E | 29°31'52.366"N | 578224.259 | 3267113.411 |  | Saniana
[5 empty] | 369.977 | [15 empty] | 11kV line, SH-2
239 | AP62/0 | 62/0 | 5DB2+0 | 47.35 |  | 90269.013 | 216.533 | 7° 1' 9"RT | 679.977 | 339.9885 | 138 | 87 | 225 | 151 | 111 | 262 | 75°48'30.202"E | 29°32'3.86"N | 578330.017 | 3267467.951 |  | Saniana
[5 empty] | 310 | [15 empty] | 11kV line, LT line, Metal road, Brick road, Nala
240 |  | 62/1 | 5DA+9 | 57.72 |  | 90579.013 | 216.817 |  | 698.611 | 349.3055 | 224 | 102 | 326 | 200 | 135 | 335 | 75°48'34.892"E | 29°32'13.059"N | 578454.269 | 3267751.961 |  | Saniana
[5 empty] | 388.611 | [15 empty] | Pump house, Nala
241 | AP63/0 | 63/0 | 5DD60+18 | 66.45 |  | 90967.624 | 217.294 | 34° 25' 54"RT | 591.917 | 295.9585 | 287 | 100 | 387 | 256 | 101 | 357 | 75°48'40.771"E | 29°32'24.59"N | 578610.029 | 3268107.99 |  | Saniana
[5 empty] | 203.306 | [15 empty] | 400kV line, Nala
242 | AP64/0 | 64/0 | 5DD60+18 | 66.45 |  | 91170.93 | 217.399 | 18° 41' 42"LT | 600.306 | 300.153 | 103 | 287 | 390 | 102 | 263 | 365 | 75°48'47.208"E | 29°32'28.045"N | 578782.556 | 3268215.543 |  | Saniana
[5 empty] | 397 | [15 empty] | Nala, Cart track
243 |  | 64/1 | 5DA+6 | 54.72 |  | 91567.93 | 218.187 |  | 806 | 403 | 111 | 238 | 349 | 136 | 229 | 365 | 75°48'56.643"E | 29°32'37.959"N | 579034.359 | 3268522.47 |  | Saniana
[5 empty] | 409 | [15 empty] | 11kV line, LT line, Metal road, Cart track
244 |  | 64/2 | 5DA+0 | 48.72 |  | 91976.93 | 216.889 |  | 770 | 385 | 172 | 178 | 350 | 181 | 179 | 360 | 75°49'6.364"E | 29°32'48.173"N | 579293.774 | 3268838.674 |  | Saniana
[5 empty] | 361 | [15 empty] | Cart track
245 |  | 64/3 | 5DA+0 | 48.72 |  | 92337.93 | 217.402 |  | 734 | 367 | 183 | 173 | 356 | 183 | 177 | 360 | 75°49'14.945"E | 29°32'57.187"N | 579522.744 | 3269117.768 |  | Saniana
[5 empty] | 373 | [15 empty] | LT line
246 |  | 64/4 | 5DA+3 | 51.72 |  | 92710.93 | 217.247 |  | 773 | 386.5 | 201 | 197 | 398 | 197 | 198 | 395 | 75°49'23.811"E | 29°33'6.501"N | 579759.325 | 3269406.14 |  | Saniana
[5 empty] | 400 | [15 empty] | Cart track
247 |  | 64/5 | 5DA+3 | 51.72 |  | 93110.93 | 217.944 |  | 803 | 401.5 | 204 | 201 | 405 | 203 | 202 | 405 | 75°49'33.319"E | 29°33'16.489"N | 580013.031 | 3269715.386 |  | Saniana
[5 empty] | 403 | [15 empty] | Brick road, Solar panel
248 |  | 64/6 | 5DA+3 | 51.72 |  | 93513.93 | 218.059 |  | 779.543 | 389.7715 | 202 | 207 | 409 | 203 | 202 | 405 | 75°49'42.9"E | 29°33'26.552"N | 580268.641 | 3270026.952 |  | Saniana
376.543
249 | AP65/0 | 65/0 | 5DC1+0 | 47.55 |  | 93890.473 | 217.821 | 20° 17' 54"LT | 759.543 | 379.7715 | 170 | 172 | 342 | 175 | 178 | 353 | 75°49'51.852"E | 29°33'35.954"N | 580507.469 | 3270318.063 |  | Bosti
[5 empty] | 383 | [15 empty] | 11kV line
250 |  | 65/1 | 5DA+3 | 51.72 |  | 94273.473 | 218.309 |  | 757 | 378.5 | 211 | 169 | 380 | 206 | 175 | 381 | 75°49'56.597"E | 29°33'47.685"N | 580632.587 | 3270680.05 |  | Parta
[5 empty] | 374 | [15 empty] | LT line, Cart track
251 |  | 65/2 | 5DA+6 | 54.72 |  | 94647.473 | 218.934 |  | 777.154 | 388.577 | 206 | 231 | 437 | 201 | 223 | 424 | 75°50'1.232"E | 29°33'59.14"N | 580754.765 | 3271033.53 |  | Parta
[5 empty] | 403.154 | [15 empty] | 11kV line,Metal road, Cart track, Canal
252 | AP66/0 | 66/0 | 5DD45+0 | 48.45 |  | 95050.627 | 218.297 | 31° 0' 55"RT | 803.154 | 401.577 | 173 | 172 | 345 | 182 | 180 | 362 | 75°50'6.228"E | 29°34'11.488"N | 580886.467 | 3271414.565 |  | Parta
[5 empty] | 400 | [15 empty] | 11kV line, Metal road, Nala
253 |  | 66/1 | 5DA+6 | 54.72 |  | 95450.627 | 218.77 |  | 766.748 | 383.374 | 229 | 207 | 436 | 221 | 201 | 422 | 75°50'17.698"E | 29°34'19.755"N | 581193.256 | 3271671.237 |  | Parta
[5 empty] | 366.748 | [15 empty] | 11kV line, Cart track, Solar panel, Bore, Pump house
254 | AP67/0 | 67/0 | 5DB2+3 | 50.35 |  | 95817.375 | 217.89 | 9° 49' 9"LT | 773.748 | 386.874 | 160 | 172 | 332 | 167 | 181 | 348 | 75°50'28.215"E | 29°34'27.334"N | 581474.541 | 3271906.573 |  | Parta
[5 empty] | 407 | [15 empty] | 11kV line, Solar panel
255 |  | 67/1 | 5DA+9 | 57.72 |  | 96224.375 | 218.058 |  | 771.182 | 385.591 | 236 | 232 | 468 | 227 | 218 | 445 | 75°50'38.075"E | 29°34'37.362"N | 581737.586 | 3272217.147 |  | Parta
[5 empty] | 364.182 | [15 empty] | 11kV lines, LT line, Brick road, Cart track, Bore, Pump house, Nala
256 | AP68/0 | 68/0 | 5DB2+0 | 47.35 |  | 96588.557 | 218.177 | 11° 27' 3"RT | 711.182 | 355.591 | 133 | 134 | 267 | 147 | 147 | 294 | 75°50'46.898"E | 29°34'46.334"N | 581972.958 | 3272495.048 |  | Parta
[5 empty] | 347 | [15 empty] | 33kV line, 11kV lines, Metal road, Nala,
257 |  | 68/1 | 5DA+6 | 54.72 |  | 96935.557 | 218.304 |  | 727.094 | 363.547 | 214 | 210 | 424 | 201 | 204 | 405 | 75°50'57.079"E | 29°34'53.254"N | 582245.328 | 3272710.044 |  | Parta
[5 empty] | 380.094 | [15 empty] | 11kV line, Cart track, Nala, Pump house
258 | AP69/0 | 69/0 | 5DB1+3 | 50.35 |  | 97315.651 | 218.326 | 6° 41' 51"LT | 768.094 | 384.047 | 171 | 204 | 375 | 177 | 201 | 378 | 75°51'8.232"E | 29°35'0.834"N | 582543.675 | 3272945.545 |  | Pirthla
388
259 |  | 69/1 | 5DA+0 | 48.72 |  | 97703.651 | 218.67 |  | 759 | 379.5 | 185 | 182 | 367 | 188 | 183 | 371 | 75°51'18.507"E | 29°35'9.679"N | 582818.112 | 3273219.823 |  | Pirthla
[5 empty] | 371 | [15 empty] | Cart track
260 |  | 69/2 | 5DA+0 | 48.72 |  | 98074.651 | 219.505 |  | 735 | 367.5 | 190 | 182 | 372 | 189 | 182 | 371 | 75°51'28.333"E | 29°35'18.136"N | 583080.524 | 3273482.084 |  | Pirthla
[5 empty] | 364 | [15 empty] | Nala, Pump house
261 |  | 69/3 | 5DA+0 | 48.72 |  | 98438.651 | 219.559 |  | 700 | 350 | 183 | 121 | 304 | 183 | 135 | 318 | 75°51'37.973"E | 29°35'26.433"N | 583337.985 | 3273739.397 |  | Pirthla
[5 empty] | 336 | [15 empty] | 11kV lins, Nala, Brick road, Solar panel
262 |  | 69/4 | 5DA+9 | 57.72 |  | 98774.651 | 218.939 |  | 754 | 377 | 215 | 223 | 438 | 202 | 220 | 422 | 75°51'46.873"E | 29°35'34.092"N | 583575.641 | 3273976.916 |  | Pirthla
[5 empty] | 418 | [15 empty] | Cart track, Canal, Nala, LT lines, Metal road
263 |  | 69/5 | 5DA+6 | 54.72 |  | 99192.651 | 218.861 |  | 838.93 | 419.465 | 196 | 210 | 406 | 200 | 211 | 411 | 75°51'57.944"E | 29°35'43.62"N | 583871.297 | 3274272.402 |  | Pirthla
420.93
264 | AP70/0 | 70/0 | 5DD60+6 | 54.45 |  | 99613.581 | 218.695 | 37° 55' 5"RT | 638.792 | 319.396 | 212 | 112 | 324 | 212 | 111 | 323 | 75°52'9.094"E | 29°35'53.215"N | 584169.025 | 3274569.958 |  | Pirthla
[5 empty] | 217.862 | [15 empty] | Railway track, cart track, Nala
265 | AP71/0 | 71/0 | 5DD60+6 | 54.45 |  | 99831.443 | 218.412 | 57° 22' 30"LT | 591.655 | 295.8275 | 105 | 208 | 313 | 108 | 202 | 310 | 75°52'17.139"E | 29°35'54.032"N | 584385.233 | 3274596.756 |  | Pirthla
[5 empty] | 373.793 | [15 empty] | 11kV line, LT line, Metal road, Nala
266 | AP72/0 | 72/0 | 5DC1+3 | 50.55 |  | 100205.236 | 218.343 | 17° 1' 37"LT | 709.793 | 354.8965 | 166 | 185 | 351 | 173 | 179 | 352 | 75°52'23.228"E | 29°36'4.948"N | 584546.505 | 3274933.969 |  | Pirthla
[5 empty] | 336 | [15 empty] | 11kV lines
267 |  | 72/1 | 5DA+0 | 48.72 |  | 100541.236 | 218.345 |  | 691.56 | 345.78 | 152 | 176 | 328 | 158 | 177 | 335 | 75°52'25.174"E | 29°36'15.731"N | 584596.357 | 3275266.25 |  | Pirthla |  |  |  | 47605.358
355.56
268 | AP73/0 | 73/0 | 5DD60+0 | 48.45 |  | 100896.796 | 218.329 | 30° 18' 22"RT | 524.56 | 262.28 | 180 | 166 | 346 | 180 | 152 | 332 | 75°52'27.234"E | 29°36'27.141"N | 584649.112 | 3275617.875 |  | Nagla
169
269 |  | 73/1 | DDH | 25.86 |  | 101065.796 | 218.504 |  | 250 | 125 | 6 | 40 | 46 | 20 | 41 | 61 | 75°52'31.211"E | 29°36'31.391"N | 584755.096 | 3275749.512 |  | Nagla
[5 empty] | 81 | [15 empty] | 765kV line, Nala
270 |  | 73/2 | DDH | 25.86 |  | 101146.796 | 218.786 |  | 161.799 | 80.8995 | 42 | -187 | -145 | 42 | -58 | -16 | 75°52'33.117"E | 29°36'33.428"N | 584805.894 | 3275812.604 |  | Nagla
80.799
271 | AP74/0 | 74/0 | 5DD60+0 | 48.45 |  | 101227.595 | 218.528 | 12° 40' 21"LT | 462.799 | 231.3995 | 271 | 143 | 414 | 142 | 157 | 299 | 75°52'35.019"E | 29°36'35.461"N | 584856.565 | 3275875.54 |  | Nagla
[5 empty] | 382 | [15 empty] | 11kV line, LT line, Brick road, Cart track, Pump House
272 |  | 74/1 | 5DA+9 | 57.72 |  | 101609.595 | 218.735 |  | 802 | 401 | 240 | 247 | 487 | 227 | 238 | 465 | 75°52'41.378"E | 29°36'46.557"N | 585025.017 | 3276218.393 |  | Nagla
420
273 |  | 74/2 | 5DA+0 | 48.72 |  | 102029.595 | 219.431 |  | 824 | 412 | 174 | 175 | 349 | 184 | 183 | 367 | 75°52'48.37"E | 29°36'58.758"N | 585210.225 | 3276595.351 |  | Nagla
[5 empty] | 404 | [15 empty] | 11kV lines, Metal road, Nala
274 |  | 74/3 | 5DA+6 | 54.72 |  | 102433.595 | 219.466 |  | 837 | 418.5 | 230 | 217 | 447 | 223 | 217 | 440 | 75°52'55.096"E | 29°37'10.493"N | 585388.378 | 3276957.95 |  | Nagla
[5 empty] | 433 | [15 empty] | 11kV lines, Cart track, Water tank, Pipal tree,
275 |  | 74/4 | 5DA+6 | 54.72 |  | 102866.595 | 219.499 |  | 822 | 411 | 217 | 195 | 412 | 218 | 195 | 413 | 75°53'2.306"E | 29°37'23.071"N | 585579.319 | 3277346.576 |  | Nagla
[5 empty] | 389 | [15 empty] | 11kV lines, LT lines, Pump house
276 |  | 74/5 | 5DA+6 | 54.72 |  | 103255.595 | 219.412 |  | 819 | 409.5 | 194 | 215 | 409 | 195 | 215 | 410 | 75°53'8.783"E | 29°37'34.371"N | 585750.858 | 3277695.711 |  | Nagla
[5 empty] | 430 | [15 empty] | LT lines, Cart track, Nala
277 |  | 74/6 | 5DA+6 | 54.72 |  | 103685.595 | 219.607 |  | 787 | 393.5 | 216 | 195 | 411 | 217 | 191 | 408 | 75°53'15.943"E | 29°37'46.861"N | 585940.476 | 3278081.645 |  | Laloda
[5 empty] | 357 | [15 empty] | 11kV lines, Metal road
278 |  | 74/7 | 5DA+3 | 51.72 |  | 104042.595 | 219.494 |  | 726 | 363 | 163 | 201 | 364 | 167 | 197 | 364 | 75°53'21.889"E | 29°37'57.231"N | 586097.903 | 3278402.06 |  | Laloda
369
279 |  | 74/8 | 5DA+0 | 48.72 |  | 104411.595 | 219.303 |  | 663 | 331.5 | 169 | 146 | 315 | 173 | 146 | 319 | 75°53'28.034"E | 29°38'7.95"N | 586260.622 | 3278733.245 |  | Laloda
[5 empty] | 294 | [15 empty] | 11kV line, Cart track, Metal road
280 |  | 74/9 | 5DA+0 | 48.72 |  | 104705.595 | 219.534 |  | 671.328 | 335.664 | 149 | 105 | 254 | 148 | 128 | 276 | 75°53'32.931"E | 29°38'16.49"N | 586390.268 | 3278997.116 |  | Laloda
[5 empty] | 377.328 | [15 empty] | 11kV line, Brick road, Pump house
281 | AP75/0 | 75/0 | 5DB1+18 | 65.35 |  | 105082.923 | 219.362 | 2° 48' 47"RT | 596.87 | 298.435 | 274 | 110 | 384 | 251 | 110 | 361 | 75°53'39.216"E | 29°38'27.45"N | 586556.66 | 3279335.776 |  | Laloda
[5 empty] | 219.542 | [15 empty] | 132kV line
282 | AP76/0 | 76/0 | 5DB2+18 | 65.35 |  | 105302.465 | 219.338 | 9° 32' 9"RT | 609.542 | 304.771 | 110 | 269 | 379 | 110 | 250 | 360 | 75°53'43.226"E | 29°38'33.662"N | 586663.026 | 3279527.831 |  | Laloda
[5 empty] | 390 | [15 empty] | 11kV line, Guava Garden
283 |  | 76/1 | 5DA+0 | 48.72 |  | 105692.465 | 220.832 |  | 798.749 | 399.3745 | 122 | 170 | 292 | 142 | 179 | 321 | 75°53'52.346"E | 29°38'43.515"N | 586905.885 | 3279832.986 |  | Laloda
[5 empty] | 408.749 | [15 empty] | 11kV line, Brick road, Nala
284 | AP77/0 | 77/0 | 5DC1+9 | 56.55 |  | 106101.214 | 220.169 | 19° 51' 24"LT | 821.749 | 410.8745 | 240 | 204 | 444 | 231 | 205 | 436 | 75°54'1.905"E | 29°38'53.84"N | 587160.42 | 3280152.81 |  | Bidhai Khera
[5 empty] | 413 | [15 empty] | 33kV line, 11kV line, Guava Garden, Pump house, Cart track
285 |  | 77/1 | 5DA+9 | 57.72 |  | 106514.214 | 220.397 |  | 809 | 404.5 | 210 | 224 | 434 | 210 | 218 | 428 | 75°54'6.932"E | 29°39'6.519"N | 587292.547 | 3280544.104 |  | Bidhai Khera
[5 empty] | 396 | [15 empty] | Metal road, Cart track, Brick road
286 |  | 77/2 | 5DA+3 | 51.72 |  | 106910.214 | 220.777 |  | 751 | 375.5 | 172 | 178 | 350 | 180 | 178 | 358 | 75°54'11.753"E | 29°39'18.675"N | 587419.236 | 3280919.292 |  | Bidhai Khera
[5 empty] | 355 | [15 empty] | 11kV line, LT line, Brick road, Nala
287 |  | 77/3 | 5DA+3 | 51.72 |  | 107265.214 | 220.691 |  | 771.158 | 385.579 | 177 | 199 | 376 | 178 | 202 | 380 | 75°54'16.074"E | 29°39'29.573"N | 587532.808 | 3281255.635 |  | Bidhai Khera
[5 empty] | 416.158 | [15 empty] | LT line
288 | AP78/0 | 78/0 | 5DB2+6 | 53.35 |  | 107681.372 | 220.654 | 14° 52' 42"RT | 802.158 | 401.079 | 219 | 173 | 392 | 216 | 178 | 394 | 75°54'21.141"E | 29°39'42.348"N | 587665.946 | 3281649.922 |  | Loha Khera
[5 empty] | 386 | [15 empty] | 11kV lines, Metal road, Cart track, Nala
289 |  | 78/1 | 5DA+9 | 57.72 |  | 108067.372 | 221.426 |  | 803.906 | 401.953 | 214 | 212 | 426 | 209 | 212 | 421 | 75°54'29.167"E | 29°39'52.746"N | 587879.199 | 3281971.666 |  | Loha Khera
[5 empty] | 417.906 | [15 empty] | 11kv line, Nala, Bore, Pump house
290 | AP79/0 | 79/0 | 5DB2+9 | 56.35 |  | 108485.278 | 221.437 | 12° 18' 31"LT | 824.906 | 412.453 | 206 | 229 | 435 | 208 | 223 | 431 | 75°54'37.857"E | 29°40'4.003"N | 588110.079 | 3282320.005 |  | Loha Khera
[5 empty] | 407 | [15 empty] | LT line, Cart track
291 |  | 79/1 | 5DA+3 | 51.72 |  | 108892.278 | 221.132 |  | 812 | 406 | 179 | 204 | 383 | 186 | 204 | 390 | 75°54'43.45"E | 29°40'16.29"N | 588257.446 | 3282699.389 |  | Loha Khera
[5 empty] | 405 | [15 empty] | 11KkV line, Metal road, Nala
292 |  | 79/2 | 5DA+3 | 51.72 |  | 109297.278 | 220.948 |  | 809.002 | 404.501 | 202 | 203 | 405 | 203 | 203 | 406 | 75°54'49.016"E | 29°40'28.517"N | 588404.089 | 3283076.908 |  | Loha Khera
[5 empty] | 404.002 | [15 empty] | Cart track
293 |  | 79/3 | 5DA+3 | 51.72 |  | 109701.28 | 220.756 |  | 814 | 407 | 202 | 194 | 396 | 202 | 198 | 400 | 75°54'54.568"E | 29°40'40.713"N | 588550.371 | 3283453.497 |  | Loha Khera
[5 empty] | 409.998 | [15 empty] | Cart track, Nala
294 |  | 79/4 | 5DA+6 | 54.72 |  | 110111.278 | 220.226 |  | 750.343 | 375.1715 | 216 | 211 | 427 | 214 | 200 | 414 | 75°55'0.204"E | 29°40'53.09"N | 588698.823 | 3283835.675 |  | Loha Khera
[5 empty] | 340.345 | [15 empty] | LT line, Cart track
295 | AP80/0 | 80/0 | 5DC2+0 | 47.55 |  | 110451.623 | 219.187 | 28° 21' 51"RT | 586.583 | 293.2915 | 130 | 78 | 208 | 141 | 102 | 243 | 75°55'4.882"E | 29°41'3.365"N | 588822.056 | 3284152.927 |  | Tohana
[5 empty] | 246.238 | [15 empty] | 11kV lines, NH-148B, Cart track
296 | AP81/0 | 81/0 | 5DC1+3 | 50.55 |  | 110697.861 | 220.581 | 18° 41' 7"RT | 629.332 | 314.666 | 169 | 163 | 332 | 145 | 172 | 317 | 75°55'11.905"E | 29°41'8.502"N | 589009.554 | 3284312.544 |  | Tohana
383.094
297 | AP82/0 | 82/0 | 5DB2+9 | 57.35 |  | 111080.955 | 220.508 | 7° 35' 11"RT | 604.016 | 302.008 | 221 | 2 | 223 | 213 | 63 | 276 | 75°55'25.188"E | 29°41'13.015"N | 589365.444 | 3284454.331 | RC 1Mtr | Kamalwala
[5 empty] | 220.922 | [15 empty] | 132kV line,11kV line, Nala
298 | AP83/0 | 83/0 | 5DB1+18 | 65.35 |  | 111301.877 | 220.535 | 4° 18' 27"RT | 603.403 | 301.7015 | 219 | 190 | 409 | 158 | 191 | 349 | 75°55'33.174"E | 29°41'14.713"N | 589579.676 | 3284508.285 |  | Kamalwala
[5 empty] | 382.481 | [15 empty] | 11kV line, Metal road, Cart track
299 | AP84/0 | 84/0 | 5DC1+18 | 65.55 |  | 111684.358 | 220.712 | 18° 17' 47"LT | 633.578 | 316.789 | 193 | 116 | 309 | 193 | 121 | 314 | 75°55'47.215"E | 29°41'16.735"N | 589956.543 | 3284573.574 |  | Kamalwala
[5 empty] | 251.097 | [15 empty] | 220kV line, Cart track
300 | AP85/0 | 85/0 | 5DD60+18 | 66.45 |  | 111935.455 | 220.738 | 14° 23' 16"LT | 656.656 | 328.328 | 135 | 272 | 407 | 130 | 255 | 385 | 75°55'55.49"E | 29°41'20.523"N | 590177.991 | 3284691.939 |  | Kamalwala
[5 empty] | 405.559 | [15 empty] | 11kV line, Cart track, Nala
301 | AP86/0 | 86/0 | 5DC1+3 | 50.55 |  | 112341.014 | 221.087 | 15° 11' 4"LT | 799.559 | 399.7795 | 135 | 195 | 330 | 152 | 196 | 348 | 75°56'6.695"E | 29°41'29.347"N | 590476.941 | 3284965.995 |  | Kamalwala
[5 empty] | 394 | [15 empty] | LT line, Cart track
302 |  | 86/1 | 5DA+3 | 51.72 |  | 112735.014 | 221.137 |  | 735 | 367.5 | 200 | 169 | 369 | 200 | 170 | 370 | 75°56'14.629"E | 29°41'40.11"N | 590687.494 | 3285299.017 |  | Kamalwala
[5 empty] | 341 | [15 empty] | 11kV lines, Metal road, Cart track
303 |  | 86/2 | 5DA+3 | 51.72 |  | 113076.014 | 221.471 |  | 686 | 343 | 173 | 172 | 345 | 172 | 173 | 345 | 75°56'21.496"E | 29°41'49.425"N | 590869.724 | 3285587.241 |  | Kamalwala
[5 empty] | 345 | [15 empty] | 11kV line, Cart track, Pump house
304 |  | 86/3 | 5DA+3 | 51.72 |  | 113421.014 | 221.529 |  | 764.431 | 382.2155 | 173 | 181 | 354 | 173 | 190 | 363 | 75°56'28.445"E | 29°41'58.85"N | 591054.091 | 3285878.846 |  | Kamalwala
[5 empty] | 419.431 | [15 empty] | LT line, Cart track, Pump house
305 | AP87/0 | 87/0 | 5DD60+9 | 57.45 |  | 113840.445 | 221.425 | 4° 21' 5"LT | 666.817 | 333.4085 | 239 | 118 | 357 | 231 | 121 | 352 | 75°56'36.892"E | 29°42'10.307"N | 591278.234 | 3286233.363 |  | Balianwala
[5 empty] | 247.386 | [15 empty] | Railway track, Cart track, Nala
306 | AP88/0 | 88/0 | 5DD60+9 | 57.45 |  | 114087.831 | 221.999 | 3° 39' 58"LT | 487.853 | 243.9265 | 130 | 130 | 260 | 127 | 125 | 252 | 75°56'41.274"E | 29°42'17.375"N | 591394.19 | 3286451.89 |  | Balianwala/Kalwan
[5 empty] | 240.467 | [15 empty] | 132kV line |  | Narwana |  | Jind
307 | AP89/0 | 89/0 | 5DB2+9 | 56.35 |  | 114328.298 | 222.148 | 8° 18' 53"LT | 640.536 | 320.268 | 110 | 243 | 353 | 116 | 233 | 349 | 75°56'45.021"E | 29°42'24.469"N | 591493.09 | 3286671.077 |  | Kalwan
[5 empty] | 400.069 | [15 empty] | 11kV lines, LT line, MDR-111
308 | AP90/0 | 90/0 | 5DB2+0 | 47.35 |  | 114728.367 | 221.679 | 13° 3' 21"LT | 742.171 | 371.0855 | 157 | 49 | 206 | 169 | 96 | 265 | 75°56'49.234"E | 29°42'36.935"N | 591603.169 | 3287055.704 |  | Kalwan
342.102
309 | AP91/0 | 91/0 | 5DB1+18 | 65.35 |  | 115070.469 | 222.149 | 6° 17' 59"LT | 570.209 | 285.1045 | 294 | 201 | 495 | 248 | 153 | 401 | 75°56'49.986"E | 29°42'48.029"N | 591620.567 | 3287397.363 |  | Kalwan
[5 empty] | 228.107 | [15 empty] | 132kV line, 11kV line
310 | AP92/0 | 92/0 | 5DD45+9 | 57.45 |  | 115298.576 | 222.519 | 30° 13' 17"RT | 607.107 | 303.5535 | 28 | 205 | 233 | 75 | 201 | 276 | 75°56'49.554"E | 29°42'55.43"N | 591607.1 | 3287625.072 |  | Kalwan
[5 empty] | 379 | [15 empty] | 11kV lines, Cart track, Nala
311 |  | 92/1 | 5DA+6 | 54.72 |  | 115677.576 | 222.766 |  | 786 | 393 | 175 | 192 | 367 | 179 | 196 | 375 | 75°56'56.025"E | 29°43'6.371"N | 591778.0008 | 3287963.3459 |  | Kalwan
[5 empty] | 407 | [15 empty] | 11kV line, LT line, Cart track, Pump house
312 |  | 92/2 | 5DA+9 | 57.72 |  | 116084.576 | 222.396 |  | 840 | 420 | 216 | 245 | 461 | 213 | 238 | 451 | 75°57'2.974"E | 29°43'18.119"N | 591961.5887 | 3288326.7319 |  | Kalwan
[5 empty] | 433 | [15 empty] | Cart track
313 |  | 92/3 | 5DA+3 | 51.72 |  | 116517.576 | 221.852 |  | 808 | 404 | 189 | 189 | 378 | 197 | 189 | 386 | 75°57'10.368"E | 29°43'30.618"N | 592157.3678 | 3288714.2489 |  | Kalwan
[5 empty] | 375 | [15 empty] | Cart track, Nala
314 |  | 92/4 | 5DA+3 | 51.72 |  | 116892.576 | 221.596 |  | 784 | 392 | 187 | 204 | 391 | 187 | 205 | 392 | 75°57'16.741"E | 29°43'41.456"N | 592325.892 | 3289047.808 |  | Kalwan
[5 empty] | 409 | [15 empty] | 11kV line
315 |  | 92/5 | 5DA+3 | 54.72 |  | 117301.576 | 221.743 |  | 792 | 396 | 206 | 201 | 407 | 206 | 199 | 405 | 75°57'23.718"E | 29°43'53.266"N | 592510.324 | 3289412.864 |  | Hari Garh Gehlan
[5 empty] | 383 | [15 empty] | 11kV lines, Cart track, Pump house
316 |  | 92/6 | 5DA+0 | 48.72 |  | 117684.576 | 222.812 |  | 766 | 383 | 183 | 148 | 331 | 185 | 160 | 345 | 75°57'30.252"E | 29°44'4.324"N | 592683.033 | 3289754.713 |  | Hari Garh Gehlan
[5 empty] | 383 | [15 empty] | 11kV lines, Pump house
317 |  | 92/7 | 5DA+9 | 57.72 |  | 118067.576 | 222.907 |  | 783.558 | 391.779 | 235 | 206 | 441 | 224 | 205 | 429 | 75°57'36.787"E | 29°44'15.383"N | 592855.741 | 3290096.562 |  | Hari Garh Gehlan
[5 empty] | 400.558 | [15 empty] | 11kV line, Cart track, Pump house
318 | AP92A/0 | 92A/0 | 5DB2+9 | 56.35 |  | 118468.134 | 222.495 | 13° 56' 45"LT | 818.537 | 409.2685 | 196 | 223 | 419 | 197 | 220 | 417 | 75°57'43.621"E | 29°44'26.948"N | 593036.367 | 3290454.082 |  | Hari Garh Gehlan
[5 empty] | 417.979 | [15 empty] | 11kV lines, Canal, Metal road, Cart track
319 | AP93/0 | 93/0 | 5DC2+6 | 53.55 |  | 118886.113 | 222.06 | 24° 20' 39"RT | 783.979 | 391.9895 | 196 | 212 | 408 | 200 | 204 | 404 | 75°57'47.21"E | 29°44'40.161"N | 593129.381 | 3290861.58 |  | Hari Garh Gehlan
[5 empty] | 366 | [15 empty] | 11kV line, Cart track
320 |  | 93/1 | 5DA+0 | 48.72 |  | 119252.113 | 222.06 |  | 760 | 380 | 155 | 169 | 324 | 163 | 177 | 340 | 75°57'55.538"E | 29°44'49.571"N | 593350.674 | 3291153.103 |  | Hari Garh Gehlan
[5 empty] | 394 | [15 empty] | 11kV line, Cart track, Pump house
321 |  | 93/2 | 5DA+6 | 54.72 |  | 119646.113 | 221.963 |  | 785 | 392.5 | 226 | 224 | 450 | 218 | 216 | 434 | 75°58'4.504"E | 29°44'59.701"N | 593588.896 | 3291466.928 |  | Hari Garh Gehlan
[5 empty] | 391 | [15 empty] | 11kV lines, Cart track, Pump house
322 |  | 93/3 | 5DA+0 | 48.72 |  | 120037.113 | 222.158 |  | 776.773 | 388.3865 | 168 | 163 | 331 | 176 | 172 | 348 | 75°58'13.403"E | 29°45'9.753"N | 593825.305 | 3291778.363 |  | Khokhhar
[5 empty] | 385.773 | [15 empty] | 11kV lines, LT line, Metal road
323 | AP94/0 | 94/0 | 5DB1+6 | 53.35 |  | 120422.886 | 222.977 | 1° 20' 15"RT | 765.773 | 382.8865 | 223 | 190 | 413 | 215 | 190 | 405 | 75°58'22.183"E | 29°45'19.671"N | 594058.553 | 3292085.635 |  | Fatheghar
[5 empty] | 380 | [15 empty] | 11kV lines, LT line, Metal road
324 |  | 94/1 | 5DA+6 | 54.72 |  | 120802.886 | 222.325 |  | 783 | 391.5 | 191 | 228 | 419 | 191 | 221 | 412 | 75°58'31.091"E | 29°45'29.262"N | 594295.313 | 3292382.863 |  | Fatheghar
[5 empty] | 403 | [15 empty] | 11kV line, Cart track
325 |  | 94/2 | 5DA+0 | 48.72 |  | 121205.886 | 222.593 |  | 778 | 389 | 176 | 159 | 335 | 183 | 167 | 350 | 75°58'40.538"E | 29°45'39.433"N | 594546.403 | 3292698.082 |  | Fatheghar
[5 empty] | 375 | [15 empty] | Cart track
326 |  | 94/3 | 5DA+6 | 54.72 |  | 121580.886 | 222.625 |  | 788 | 394 | 217 | 205 | 422 | 210 | 206 | 416 | 75°58'49.33"E | 29°45'48.897"N | 594780.048 | 3292991.4 |  | Fatheghar
[5 empty] | 413 | [15 empty] | LT line, Metal road, Pump house
327 |  | 94/4 | 5DA+6 | 54.72 |  | 121993.886 | 223.052 |  | 831 | 415.5 | 209 | 222 | 431 | 209 | 219 | 428 | 75°58'59.013"E | 29°45'59.32"N | 595037.368 | 3293314.44 |  | Fatheghar
[5 empty] | 418 | [15 empty] | Cart track, Pump house
328 |  | 94/5 | 5DA+3 | 51.72 |  | 122411.886 | 223.194 |  | 828 | 414 | 197 | 192 | 389 | 201 | 196 | 397 | 75°59'8.814"E | 29°46'9.868"N | 595297.804 | 3293641.391 |  | Ramgarh Gujjaran
[5 empty] | 410 | [15 empty] | Cart track
329 |  | 94/6 | 5DA+6 | 54.72 |  | 122821.886 | 223.321 |  | 821 | 410.5 | 219 | 192 | 411 | 216 | 196 | 412 | 75°59'18.428"E | 29°46'20.215"N | 595553.255 | 3293962.085 |  | Ramgarh Gujjaran
[5 empty] | 411 | [15 empty] | 11kV lines, LT line, Metal road, Cart track, Pump house
330 |  | 94/7 | 5DA+9 | 57.72 |  | 123232.886 | 223.522 |  | 824 | 412 | 220 | 247 | 467 | 217 | 237 | 454 | 75°59'28.066"E | 29°46'30.587"N | 595809.33 | 3294283.561 |  | Ramgarh Gujjaran
[5 empty] | 413 | [15 empty] | Cart track
331 |  | 94/8 | 5DA+0 | 48.72 |  | 123645.886 | 223.395 |  | 792 | 396 | 167 | 147 | 314 | 178 | 158 | 336 | 75°59'37.751"E | 29°46'41.009"N | 596066.65 | 3294606.602 |  | Ramgarh Gujjaran
[5 empty] | 379 | [15 empty] | 11kV line, Pump house
332 |  | 94/9 | 5DA+9 | 57.72 |  | 124024.886 | 223.462 |  | 780.332 | 390.166 | 233 | 217 | 450 | 222 | 213 | 435 | 75°59'46.64"E | 29°46'50.573"N | 596302.787 | 3294903.048 |  | Mandavi B
[5 empty] | 401.332 | [15 empty] | 11kV lines, Metal road, Cart track, Pump house
333 | AP95/0 | 95/0 | 5DB1+6 | 53.35 |  | 124426.218 | 223.569 | 3° 9' 49"LT | 796.332 | 398.166 | 185 | 190 | 375 | 189 | 193 | 382 | 75°59'56.053"E | 29°47'0.7"N | 596552.838 | 3295216.962 |  | Mandavi B
[5 empty] | 395 | [15 empty] | 11kV lines, Brick road
334 |  | 95/1 | 5DA+6 | 54.72 |  | 124821.218 | 224.268 |  | 713.988 | 356.994 | 205 | 162 | 367 | 203 | 162 | 365 | 76°0'4.673"E | 29°47'11.098"N | 596781.517 | 3295539.034 |  | Mandavi B
[5 empty] | 318.988 | [15 empty] | 11kV lines
335 | AP96/0 | 96/0 | 5DC2+6 | 53.55 |  | 125140.206 | 224.362 | 22° 36' 3"LT | 545.496 | 272.748 | 157 | 116 | 273 | 158 | 115 | 273 | 76°0'11.634"E | 29°47'19.495"N | 596966.191 | 3295799.129 |  | Mandavi B
[5 empty] | 226.508 | [15 empty] | 66kV line, 11kV line
336 | AP97/0 | 97/0 | 5DB2+6 | 53.35 |  | 125366.714 | 224.293 | 11° 41' 10"RT | 602.508 | 301.254 | 110 | 201 | 311 | 112 | 197 | 309 | 76°0'13.571"E | 29°47'26.656"N | 597016.277 | 3296020.03 |  | Mandavi B
[5 empty] | 376 | [15 empty] | 11kV lines
337 |  | 97/1 | 5DA+3 | 51.72 |  | 125742.714 | 224.222 |  | 758.573 | 379.2865 | 176 | 162 | 338 | 180 | 171 | 351 | 76°0'19.481"E | 29°47'37.73"N | 597171.969 | 3296362.281 |  | Mandavi B
[5 empty] | 382.573 | [15 empty] | 11kV lines, Metal road, Cart track, Nala
338 | AP98/0 | 98/0 | 5DB2+9 | 53.35 |  | 126125.287 | 224.798 | 13° 14' 28"RT | 784.573 | 392.2865 | 221 | 211 | 432 | 213 | 208 | 421 | 76°0'25.494"E | 29°47'48.998"N | 597330.383 | 3296710.516 |  | Mandavi B
[5 empty] | 402 | [15 empty] | 11kV lines
339 |  | 98/1 | 5DA+6 | 51.72 |  | 126527.287 | 225.16 |  | 740 | 370 | 192 | 223 | 415 | 195 | 207 | 402 | 76°0'34.754"E | 29°47'59.26"N | 597576.229 | 3297028.578 |  | Mandavi B
338
340 |  | 98/2 | 5DA-3 | 45.72 |  | 126865.287 | 224.946 |  | 675 | 337.5 | 116 | 152 | 268 | 132 | 157 | 289 | 76°0'42.54"E | 29°48'7.888"N | 597782.935 | 3297296.004 |  | Mandavi B
[5 empty] | 337 | [15 empty] | Cart track
341 |  | 98/3 | 5DA+0 | 48.72 |  | 127202.287 | 224.774 |  | 720 | 360 | 185 | 177 | 362 | 180 | 182 | 362 | 76°0'50.304"E | 29°48'16.491"N | 597989.03 | 3297562.638 |  | Mandavi B
383
342 |  | 98/4 | 5DA+3 | 51.72 |  | 127585.287 | 224.713 |  | 767 | 383.5 | 207 | 180 | 387 | 203 | 184 | 387 | 76°0'59.128"E | 29°48'26.268"N | 598223.257 | 3297865.668 |  | Mandavi B
[5 empty] | 384 | [15 empty] | 11kV line, Cart track
343 |  | 98/5 | 5DA+6 | 54.72 |  | 127969.287 | 224.181 |  | 772 | 386 | 205 | 195 | 400 | 201 | 195 | 396 | 76°1'7.975"E | 29°48'36.07"N | 598458.095 | 3298169.489 |  | Andana
[5 empty] | 388 | [15 empty] | 11kV line
344 |  | 98/6 | 5DA+6 | 54.72 |  | 128357.287 | 224.124 |  | 777.649 | 388.8245 | 194 | 199 | 393 | 194 | 198 | 392 | 76°1'16.915"E | 29°48'45.974"N | 598695.379 | 3298476.475 |  | Andana
[5 empty] | 389.649 | [15 empty] | 11kV line, cart track
345 | AP99/0 | 99/0 | 5DC1+6 | 53.55 |  | 128746.936 | 223.772 | 15° 33' 44"LT | 798.649 | 399.3245 | 191 | 225 | 416 | 192 | 220 | 412 | 76°1'25.894"E | 29°48'55.92"N | 598933.672 | 3298784.765 |  | Andana
[5 empty] | 409 | [15 empty] | Cart track, Metal road
346 |  | 99/1 | 5DA+3 | 50.22 |  | 129155.936 | 223.401 |  | 791.024 | 395.512 | 185 | 206 | 391 | 191 | 203 | 394 | 76°1'31.761"E | 29°49'8.181"N | 599087.813 | 3299163.607 |  | Shahpur
[5 empty] | 382.024 | [15 empty] | 11kV line
347 | AP100/0 | 100/0 | 5DB1+0 | 47.35 |  | 129537.96 | 222.511 | 0° 42' 29"LT | 761.024 | 380.512 | 177 | 170 | 347 | 181 | 177 | 358 | 76°1'37.242"E | 29°49'19.634"N | 599231.787 | 3299517.463 |  | Shahpur
[5 empty] | 379 | [15 empty] | 11kV line, Cart track
348 |  | 100/1 | 5DA+3 | 51.72 |  | 129916.96 | 222.289 |  | 651 | 325.5 | 209 | 156 | 365 | 203 | 149 | 352 | 76°1'42.519"E | 29°49'31.055"N | 599370.272 | 3299870.256 |  | Shahpur
272
349 |  | 100/2 | 5DA+0 | 48.72 |  | 130188.96 | 222.779 |  | 599 | 299.5 | 116 | 183 | 299 | 123 | 176 | 299 | 76°1'46.306"E | 29°49'39.25"N | 599469.66 | 3300123.448 |  | Shahpur
[5 empty] | 327 | [15 empty] | Ghagger river, Cart track, 11kV line
350 |  | 100/3 | 5DA-3 | 45.72 |  | 130515.96 | 222.868 |  | 622 | 311 | 145 | 107 | 252 | 152 | 122 | 274 | 76°1'50.859"E | 29°49'49.104"N | 599589.145 | 3300427.836 |  | Andana
[5 empty] | 295 | [15 empty] | 11kV lines, Cart track
351 |  | 100/4 | 5DA+3 | 51.72 |  | 130810.96 | 222.454 |  | 685 | 342.5 | 188 | 164 | 352 | 174 | 175 | 349 | 76°1'54.966"E | 29°49'57.992"N | 599696.937 | 3300702.437 |  | Andana
[5 empty] | 390 | [15 empty] | Cart track, Metal road
352 |  | 100/5 | 5DA+9 | 57.72 |  | 131200.96 | 222.242 |  | 802 | 401 | 227 | 221 | 448 | 216 | 216 | 432 | 76°2'0.397"E | 29°50'9.744"N | 599839.442 | 3301065.47 |  | Nawan Gaon
[5 empty] | 412 | [15 empty] | 11kV lines, Cart track, Pump house
353 |  | 100/6 | 5DA+6 | 54.72 |  | 131612.96 | 222.468 |  | 768 | 384 | 192 | 215 | 407 | 197 | 202 | 399 | 76°2'6.135"E | 29°50'22.158"N | 599989.985 | 3301448.981 |  | Nawan Gaon
[5 empty] | 356 | [15 empty] | 11kV line, LT line
354 |  | 100/7 | 5DA+0 | 48.72 |  | 131968.96 | 222.357 |  | 692.413 | 346.2065 | 141 | 136 | 277 | 155 | 147 | 302 | 76°2'11.093"E | 29°50'32.884"N | 600120.067 | 3301780.364 |  | Nawan Gaon
336.413
355 | AP101/0 | 101/0 | 5DB1+6 | 53.35 |  | 132305.373 | 222.183 | 6° 4' 53"LT | 223.24 | 111.62 | 201 | 107 | 308 | 190 | 110 | 300 | 76°2'15.778"E | 29°50'43.021"N | 600242.991 | 3302093.515 |  | Nawan Gaon
[5 empty] | 223.24 | [15 empty] | 66 KV DC TL PSPCL
356 | AP102/0 | 102/0 | 5DB1+6 | 53.35 |  | 132528.613 | 222.551 | 0° 2' 33"LT | 601.24 | 300.62 | 116 | 201 | 317 | 114 | 198 | 312 | 76°2'18.052"E | 29°50'49.997"N | 600302.088 | 3302308.791 |  | Nawan Gaon
[5 empty] | 378 | [15 empty] | 11 KV LINE/METAL ROAD/LT LINE/PUMP HOUSE/CART TRACK/11KV LINE
357 |  | 102/1 | 5DA+3 | 51.72 |  | 132906.613 | 222.51 |  | 794.359 | 397.1795 | 178 | 198 | 376 | 181 | 201 | 382 | 76°2'21.894"E | 29°51'1.811"N | 600401.883 | 3302673.379 |  | Nawan Gaon
416.359
358 | AP103/0 | 103/0 | 5DB1+6 | 53.35 |  | 133322.972 | 222.689 | 3° 28' 33"LT | 819.359 | 409.6795 | 219 | 183 | 402 | 217 | 188 | 405 | 76°2'26.125"E | 29°51'14.823"N | 600511.806 | 3303074.966 |  | Jaswant Pur Hotipur
[5 empty] | 403 | [15 empty] | PUMP HOUSE/11 KV LINE/PUMP HOUSE/LT LINE
359 |  | 103/1 | 5DA+9 | 57.72 |  | 133725.972 | 223.315 |  | 816.905 | 408.4525 | 221 | 225 | 446 | 217 | 221 | 438 | 76°2'29.338"E | 29°51'27.612"N | 600594.44 | 3303469.403 |  | Jaswant Pur Hotipur
[5 empty] | 413.905 | [15 empty] | LT LINE/PUMP HOUSE/METAL ROAD/11KV LINE/CART TRACK/11KV LINE/LT LINE
360 | AP104/0 | 104/0 | 5DB2+6 | 53.35 |  | 134139.877 | 222.832 | 13° 51' 39"RT | 754.866 | 377.433 | 190 | 205 | 395 | 194 | 192 | 386 | 76°2'32.637"E | 29°51'40.747"N | 600679.31 | 3303874.514 |  | Jaswant Pur Hotipur
[5 empty] | 340.961 | [15 empty] | 11KV LINE/METAL ROAD/11KV LINE
361 | AP105/0 | 105/0 | 5DB2+0 | 47.35 |  | 134480.838 | 223.632 | 12° 29' 43"RT | 686.961 | 343.4805 | 136 | 168 | 304 | 150 | 170 | 320 | 76°2'38.25"E | 29°51'50.684"N | 600827.134 | 3304181.764 |  | Jaswant Pur Hotipur
[5 empty] | 346 | [15 empty] | LT LINE/CART TRACK/NALA/METAL ROAD
362 |  | 105/1 | 5DA+0 | 48.72 |  | 134826.838 | 223.948 |  | 729 | 364.5 | 179 | 161 | 340 | 177 | 169 | 346 | 76°2'46.315"E | 29°51'59.455"N | 601041.048 | 3304453.714 |  | Jaswant Pur Hotipur
[5 empty] | 383 | [15 empty] | CART TRACK END/11KV LINE/LT LINE
363 |  | 105/2 | 5DA+6 | 54.72 |  | 135209.838 | 224.489 |  | 817 | 408.5 | 223 | 217 | 440 | 215 | 218 | 433 | 76°2'55.242"E | 29°52'9.163"N | 601277.838 | 3304754.746 |  | Khang
[5 empty] | 434 | [15 empty] | 11KV LINE
364 |  | 105/3 | 5DA+6 | 54.72 |  | 135643.838 | 224.562 |  | 834 | 417 | 218 | 201 | 419 | 218 | 201 | 419 | 76°3'5.359"E | 29°52'20.164"N | 601546.157 | 3305095.862 |  | Gulhar
[5 empty] | 400 | [15 empty] | CART TRACK/11KV LINE/CART TRACK
365 |  | 105/4 | 5DA+6 | 54.72 |  | 136043.838 | 224.388 |  | 807 | 403.5 | 200 | 188 | 388 | 200 | 193 | 393 | 76°3'14.684"E | 29°52'30.304"N | 601793.457 | 3305410.255 |  | Gulhar
[5 empty] | 407 | [15 empty] | CART TRACK/11KV LINE/11KV LINE/CART TRACK/CART TRACK
366 |  | 105/5 | 5DA+9 | 57.72 |  | 136450.838 | 224.973 |  | 832.597 | 416.2985 | 220 | 218 | 438 | 216 | 217 | 433 | 76°3'24.172"E | 29°52'40.62"N | 602045.084 | 3305730.15 |  | Noorpur
[5 empty] | 425.597 | [15 empty] | METAL ROAD/11KV LINE/LT LINE
367 | AP106/0 | 106/0 | 5DB2+9 | 56.35 |  | 136876.435 | 224.462 | 10° 46' 18"LT | 806.597 | 403.2985 | 208 | 218 | 426 | 210 | 209 | 419 | 76°3'34.095"E | 29°52'51.407"N | 602308.209 | 3306064.662 |  | Noorpur
[5 empty] | 381 | [15 empty] | 11KV LINE/CART TRACK
368 |  | 106/1 | 5DA+3 | 51.72 |  | 137257.435 | 224.768 |  | 738 | 369 | 163 | 196 | 359 | 173 | 190 | 363 | 76°3'40.75"E | 29°53'2.341"N | 602483.644 | 3306402.868 |  | Khang
[5 empty] | 357 | [15 empty] | 11KV LINE/CART TRACK
369 |  | 106/2 | 5DA+0 | 48.72 |  | 137614.435 | 224.832 |  | 724 | 362 | 161 | 181 | 342 | 168 | 182 | 350 | 76°3'46.987"E | 29°53'12.586"N | 602648.027 | 3306719.771 |  | Molviwala
[5 empty] | 367 | [15 empty] | 11KV LINE/CART TRACK
370 |  | 106/3 | 5DA+0 | 48.72 |  | 137981.435 | 225.36 |  | 643 | 321.5 | 187 | 132 | 319 | 186 | 134 | 320 | 76°3'53.399"E | 29°53'23.117"N | 602817.016 | 3307045.55 |  | Molviwala
[5 empty] | 276 | [15 empty] | METAL ROAD/PUMP HOUSE/11KV LINE
371 |  | 106/4 | 5DA+0 | 48.72 |  | 138257.435 | 226.181 |  | 608 | 304 | 144 | 188 | 332 | 142 | 181 | 323 | 76°3'58.221"E | 29°53'31.038"N | 602944.102 | 3307290.55 |  | Molviwala
[5 empty] | 332 | [15 empty] | NALA/CART TRACK
372 |  | 106/5 | 5DA-3 | 45.72 |  | 138589.435 | 225.746 |  | 652 | 326 | 144 | 140 | 284 | 152 | 147 | 299 | 76°4'4.022"E | 29°53'40.565"N | 603096.974 | 3307585.26 |  | Molviwala
[5 empty] | 320 | [15 empty] | PUMP HOUSE /11KV LINE/CART TRACK/11KV LINE
373 |  | 106/6 | 5DA+0 | 48.72 |  | 138909.435 | 225.828 |  | 687 | 343.5 | 180 | 149 | 329 | 174 | 161 | 335 | 76°4'9.614"E | 29°53'49.747"N | 603244.321 | 3307869.318 |  | Molviwala
[5 empty] | 367 | [15 empty] | NALA
374 |  | 106/7 | 5DA+6 | 54.72 |  | 139276.435 | 225.964 |  | 783.111 | 391.5555 | 219 | 211 | 430 | 207 | 210 | 417 | 76°4'16.027"E | 29°54'0.279"N | 603413.309 | 3308195.097 |  | Molviwala
[5 empty] | 416.111 | [15 empty] | PUMP HOUSE/4 NOS. 11 KV LINE/CART TRACK
375 | AP107/0 | 107/0 | 5DC2+6 | 53.55 |  | 139692.546 | 226.035 | 23° 41' 2"RT | 766.583 | 383.2915 | 206 | 18 | 224 | 207 | 75 | 282 | 76°4'23.299"E | 29°54'12.219"N | 603604.911 | 3308564.471 |  | Molviwala
[5 empty] | 350.472 | [15 empty] | 11KV LINE/METAL ROAD/LT LINE/CART TRACK
376 | AP108/0 | 108/0 | 5DD60+30 | 78.45 |  | 140043.018 | 226.488 | 42° 55' 20"RT | 549.666 | 274.833 | 334 | 95 | 429 | 277 | 98 | 375 | 76°4'33.545"E | 29°54'19.285"N | 603877.665 | 3308784.552 |  | Molviwala
[5 empty] | 199.194 | [15 empty] | 400 KV DC PTR-KTL TL PGCIL
377 | AP109/0 | 109/0 | 5DD60+30 | 78.45 |  | 140242.212 | 226.791 | 35° 10' 35"LT | 632.194 | 316.097 | 104 | 330 | 434 | 101 | 296 | 397 | 76°4'40.949"E | 29°54'18.771"N | 604076.368 | 3308770.578 |  | Molviwala
[5 empty] | 433 | [15 empty] | CART TRACK
378 |  | 109/1 | 5DA+6 | 54.72 |  | 140675.212 | 226.213 |  | 774 | 387 | 104 | 200 | 304 | 139 | 191 | 330 | 76°4'54.843"E | 29°54'25.934"N | 604446.922 | 3308994.585 |  | Paind
[5 empty] | 341 | [15 empty] | 11KV LINE/BRICK ROAD/LT LINE/BRICK ROAD/PUMP HOUSE
379 |  | 109/2 | 5DA+0 | 48.72 |  | 141016.212 | 227.133 |  | 672.662 | 336.331 | 142 | 115 | 257 | 151 | 131 | 282 | 76°5'5.786"E | 29°54'31.575"N | 604738.744 | 3309170.996 |  | Paind
[5 empty] | 331.662 | [15 empty] | BRICK ROAD/11KV LINE
380 | AP110/0 | 110/0 | 5DB2+9 | 56.35 |  | 141347.874 | 227.475 | 14° 39' 60"LT | 577.018 | 288.509 | 217 | 172 | 389 | 202 | 146 | 348 | 76°5'16.429"E | 29°54'37.062"N | 605022.574 | 3309342.577 |  | Paind
[5 empty] | 245.356 | [15 empty] | 2 NOS. 66 KV SC LINE PSEB/11KV LINE
381 | AP111/0 | 111/0 | 5DD45+3 | 51.45 |  | 141593.23 | 227.658 | 34°35'50"LT | 488.356 | 244.178 | 73 | 124 | 197 | 99 | 123 | 222 | 76°5'22.867"E | 29°54'42.725"N | 605193.565 | 3309518.536 |  | shutrana
[5 empty] | 243 | [15 empty] | 3 NOS. 11KV LINE/
382 |  | 111/1 | 5DA+3 | 51.72 |  | 141836.23 | 227.814 |  | 483.23 | 241.615 | 119 | 147 | 266 | 120 | 133 | 253 | 76°5'24.178"E | 29°54'50.535"N | 605234.02 | 3309758.15 |  | shutrana
240.23
383 | AP112/0 | 112/0 | 5DD45+0 | 48.45 |  | 142076.46 | 227.897 | 31°35'22"RT | 452.87 | 226.435 | 93 | 116 | 209 | 108 | 110 | 218 | 76°5'25.494"E | 29°54'58.365"N | 605274.007 | 3309995.025 |  | shutrana
[5 empty] | 212.64 | [15 empty] | 11KV LINE/NH52/11KV LINE
384 | AP113/0 | 113/0 | 5DB2+0 | 50.35 |  | 142289.1 | 228.274 | 9° 48' 37"RT | 541.64 | 270.82 | 97 | 127 | 224 | 103 | 138 | 241 | 76°5'30.956"E | 29°55'3.721"N | 605413.989 | 3310155.084 |  | Duttal
[5 empty] | 329 | [15 empty] | 11KV LINE NEED TO BE SHIFTED/11KV LINE /CART TRACK/PUMP HOUSE
385 |  | 113/1 | 5DA+6 | 51.72 |  | 142618.1 | 228.146 |  | 761.99 | 380.995 | 203 | 207 | 410 | 192 | 210 | 402 | 76°5'40.869"E | 29°55'10.607"N | 605665.053 | 3310367.705 |  | Duttal
[5 empty] | 432.99 | [15 empty] | CART TRACK/11 KV LINE /CART TRACK
386 | AP114/0 | 114/0 | 5DC2+9 | 56.55 |  | 143051.09 | 228.007 | 25° 53' 54"LT | 864.31 | 432.155 | 227 | 229 | 456 | 224 | 226 | 450 | 76°5'53.169"E | 29°55'19.15"N | 605995.474 | 3310647.533 |  | Duttal
[5 empty] | 431.324 | [15 empty] | 11 KV LINE /PUMP HOUSE/11 KV LINE /CART TRACK
387 |  | 114/1 | 5DA+6 | 54.72 |  | 143482.414 | 227.41 |  | 774.549 | 387.2745 | 203 | 208 | 411 | 207 | 198 | 405 | 76°6'0.103"E | 29°55'31.792"N | 606177.682 | 3311038.481 |  | Duttal
[5 empty] | 343.224 | [15 empty] | CART TRACK/2 NOS. BRICK ROAD/11KV LINE
388 | AP115/0 | 115/0 | 5DB2+0 | 47.35 |  | 143825.638 | 227.37 | 9° 46' 28"RT | 665.225 | 332.6125 | 136 | 112 | 248 | 146 | 130 | 276 | 76°6'5.622"E | 29°55'41.853"N | 606322.674 | 3311349.577 |  | Duttal
[5 empty] | 322 | [15 empty] | 33KV LINE/LT LINE/NALA/CART TRACK
389 |  | 115/1 | 5DA+6 | 54.72 |  | 144147.638 | 227.951 |  | 682 | 341 | 210 | 219 | 429 | 193 | 205 | 398 | 76°6'12.563"E | 29°55'50.388"N | 606506.8016 | 3311613.7372 |  | Duttal
[5 empty] | 360 | [15 empty] | 11KV LINE/CART TRACK/11KV LINE/NALI/11KV LINE/METAL ROAD/CART TRACK/11KV LINE
390 |  | 115/2 | 5DA+0 | 48.72 |  | 144507.638 | 227.57 |  | 727.366 | 363.683 | 142 | 169 | 311 | 156 | 175 | 331 | 76°6'20.324"E | 29°55'59.93"N | 606712.6585 | 3311909.0714 |  | Duttal
[5 empty] | 375.37 | [15 empty] | 11KV LINE/PUMP HOUSE/CART TRACK
391 | AP116/0 | 116/0 | 5DC1+3 | 50.55 |  | 144883.008 | 227.587 | 14° 59' 32"RT | 624.641 | 312.3205 | 199 | 148 | 347 | 194 | 138 | 332 | 76°6'28.245"E | 29°56'9.668"N | 606927.0835 | 3312216.6981 |  | Duttal
[5 empty] | 249.27 | [15 empty] | EXPRESSWAY
392 | AP117/0 | 117/0 | 5DD45+0 | 48.45 |  | 145132.278 | 227.71 | 39° 48' 46"LT | 667.275 | 333.6375 | 109 | 166 | 275 | 119 | 176 | 295 | 76°6'35.629"E | 29°56'15.005"N | 607117.383 | 3312377.861 |  | Duttal
[5 empty] | 410 | [15 empty] | 11KV LINE/CART TRACK
393 |  | 117/1 | 5DA+9 | 57.72 |  | 145542.278 | 228.201 |  | 811.896 | 405.948 | 245 | 219 | 464 | 235 | 215 | 450 | 76°6'38.415"E | 29°56'28.101"N | 607188.173 | 3312781.703 |  | Duttal
[5 empty] | 401.896 | [15 empty] | METAL ROAD/11K V LINE/LT LINE/BRICK ROAD/PUMP HOSE
394 | AP118/0 | 118/0 | 5DB1+6 | 53.35 |  | 145944.174 | 227.945 | 6° 9' 58"LT | 754.896 | 377.448 | 184 | 208 | 392 | 189 | 196 | 385 | 76°6'41.146"E | 29°56'40.938"N | 607257.564 | 3313177.564 |  | Duttal
[5 empty] | 353 | [15 empty] | METAL ROAD/LT LINE/11KV LINE/
395 |  | 118/1 | 5DA+0 | 48.72 |  | 146297.174 | 228.39 |  | 690 | 345 | 145 | 169 | 314 | 158 | 169 | 327 | 76°6'42.14"E | 29°56'52.372"N | 607280.813 | 3313529.798 |  | Duttal
[5 empty] | 337 | [15 empty] | 11KV LINE/PUMP HOUSE/CART TRACK
396 |  | 118/2 | 5DA+0 | 48.72 |  | 146634.174 | 228.315 |  | 592 | 296 | 168 | 129 | 297 | 169 | 128 | 297 | 76°6'43.089"E | 29°57'3.288"N | 607303.009 | 3313866.066 |  | Bishanpur Alias banwala
[5 empty] | 255 | [15 empty] | 11KV LINE/METAL ROAD
397 |  | 118/3 | 5DA+0 | 48.72 |  | 146889.174 | 228.201 |  | 595.043 | 297.5215 | 127 | 104 | 231 | 127 | 131 | 258 | 76°6'43.808"E | 29°57'11.548"N | 607319.804 | 3314120.512 |  | Bishanpur Alias banwala
[5 empty] | 340.043 | [15 empty] | CART TRACK/LT LINE
398 | AP119/0 | 119/0 | 5DD60+9 | 57.45 |  | 147229.217 | 228.553 | 57° 4' 0"LT | 525.892 | 262.946 | 236 | -147 | 89 | 210 | 3 | 213 | 76°6'44.766"E | 29°57'22.562"N | 607342.2 | 3314459.817 |  | Daroli
[5 empty] | 185.849 | [15 empty] | CART TRACK
399 | AP120/0 | 120/0 | 5DD60+25 | 73.45 |  | 147415.066 | 228.41 | 25° 25' 48"LT | 299.189 | 149.5945 | 333 | 205 | 538 | 184 | 94 | 278 | 76°6'39.248"E | 29°57'26.218"N | 607193.21 | 3314570.91 |  | Daroli
[5 empty] | 113.34 | [15 empty] | LT LINE/400 KV DC PTL-PTR TL PGCIL/SS BOUNDARY
400 | AP121/0 | 121/0 | 5DD60+18 | 66.45 |  | 147528.406 | 228.482 | 12° 15' 32"LT | 175.996 | 87.998 | -92 | 112 | 20 | 19 | 107 | 126 | 76°6'35.11"E | 29°57'26.973"N | 607082.059 | 3314593.079 | RC=1.5M | Daroli
[5 empty] | 62.656 | [23 empty] | 52.9359
401 |  | Patran Gantry | Gantry | 22.8 |  | 147591.062 | 228.626 |  | 62.656 | 31.328 | -35 | 0 | -35 | -29 | 0 | -29 | 76°6'32.773"E | 29°57'26.958"N | 607019.412 | 3314592.008 |  | Daroli | [6 empty] | 47.6054
|  |  |  | Total | 147.5911 | KM | [19 empty] | 47049.826 | 147591.062 | 147.5911 | 47.0498
147.5911
For Kec International Limited | [10 empty] | M/s, Powergrid Bikaner IV Transmission Limited
Surveyed By |  |  |  | Checked By |  |  |  | submitted by |  |  | Checked By | [6 empty] | Recommended By |  |  | Approved By

## TS SF
KEC INTERNATIONAL LIMITED
Transmission Line Package TL03 for (a) Siwani– Fatehabad (PG) 400kV D/c line (Quad); (b) Siwani – Patran (Indi Grid) 400 kV D/c line (Quad) associated with “Transmission System for evacuation of power from Rajasthan REZ Ph-IV (Part 3: 6 GW) (Bikaner Complex) : Part A” through Tariff Based Competitive Bidding
Package TL03 for (a) Siwani– Fatehabad (PG) 400kV D/C Transmission Line
TOWER SCHEDULE - SIWANI GANTRY to FATEHABAD GANTRY (WZ-4 & WZ-5)
Client : POWERGRID BIKANER IV TRANSMISSION LIMITED (A 100% WHOLLY OWNED SUBSIDIARY OF POWER GRID) | [34 empty] | DT.
Sl.No | AP NO. | TOWER NO. | TYPE OF TOWER | HT of Tower (Mtr) | SPAN (Mtr) | SECTION LENGTH (Mtr) | CUMULATIVE SPAN | LEG EXTENSION |  |  |  | RAISED CHIMNEY | BENCHING VOLUME (Cum) | REVETMENT VOLUME (Cum) | R.L (Mtr) | DEVIATION ANGLE (Deg) | Sum of Adjacent Spans | WIND SPAN (Mtr) | WEIGHT SPAN IN Mtr (Cold) |  |  | WEIGHT SPAN IN Mtr (Hot) |  |  | LONGITUDE (E) | LATITUDE (N) | UTM Coordinates |  | CROSSING DETAILS | NAME OF VILLAGE | NAME OF TEHSIL | NAME OF POLICE STATION | VILLAGE NAME | TEHSIL/CIRCLE | Remarks
[8 empty] | A | B | C | D | [7 empty] | Left | Right | Total | Left | Right | Total |  |  | Easting (m) | Y Northing (m)
1 |  | Shiwani Gantry | S/S GANTRY | 29.9 |  |  | 0 | [7 empty] | 215.049 |  | 151.994 | 75.997 | 0 | 42 | 42 | 0 | 45 | 45 | 75º 32' 54.538" E | 28º 47' 32.703" N | 553529.005 | 3185111.006 |  |  |  |  | Jhumpa Kalan |  | No count
151.994
2 | AP1/0 | 1/0 | DD60+0 | 47.97 |  | 151.994 | 151.994 | [7 empty] | 214.7 | 7° 37' 35"RT | 561.994 | 280.997 | 112 | 183 | 295 | 110 | 190 | 300 | 75º 32' 54.563" E | 28º 47' 37.642" N | 553529 | 3185263 |  |  |  |  | Jhumpa Kalan
[5 empty] | 410 | [23 empty] | Raw Road 2nos
3 |  | 1/1 | DA+6 | 54.15 |  |  | 561.994 | [7 empty] | 213.287 |  | 839.494 | 419.747 | 227 | 248 | 475 | 221 | 238 | 459 | 75º 32' 56.64" E | 28º 47' 50.807" N | 553583.4 | 3185669.375 |  |  |  |  | Jhumpa Kalan
429.494
4 | AP1A/0 | 1A/0 | DD60+0 | 47.97 |  | 839.494 | 991.488 | [7 empty] | 212.35 | 54° 8' 46"LT | 657.751 | 328.8755 | 182 | -19 | 163 | 192 | 56 | 248 | 75º 32' 58.814" E | 28º 48' 4.662" N | 553640.386 | 3186095.072 |  |  |  |  | Jhumpa Kalan
[5 empty] | 228.257 | [23 empty] | 11KV,NH-52
5 | AP1B/0 | 1B/0 | DD60+6 | 53.97 |  | 228.257 | 1219.745 | [7 empty] | 217.18 | 10° 52' 60"LT | 459.177 | 229.5885 | 248 | 164 | 412 | 172 | 137 | 309 | 75º 32' 52.731" E | 28º 48' 9.79" N | 553474.755 | 3186252.132 |  |  |  |  | Jhumpa Kalan
[5 empty] | 230.92 | [23 empty] | RAILWAY LINE
6 | AP2/0 | 2/0 | DD60+3 | 50.97 |  | 230.92 | 1450.665 | [7 empty] | 216.15 | 54° 25' 27"RT | 604.018 | 302.009 | 67 | 222 | 289 | 94 | 209 | 303 | 75º 32' 45.575" E | 28º 48' 13.861" N | 553280.206 | 3186376.529 |  |  |  |  | Jhumpa Kalan
[5 empty] | 373.098 | [23 empty] | Cart Track
7 | AP2A/0 | 2A/0 | DC1+0 | 47.07 |  | 373.098 | 1823.763 | [7 empty] | 214.558 | 20° 23' 46"RT | 716.098 | 358.049 | 152 | 141 | 293 | 165 | 152 | 317 | 75º 32' 44.922" E | 28º 48' 25.971" N | 553260.806 | 3186749.122 |  |  |  |  | Jhumpa Kalan
[5 empty] | 343 | [23 empty] | Cart Track, Water pipe line
8 |  | 2A/1 | DA+0 | 48.15 |  |  | 2166.763 | [7 empty] | 218.554 |  | 757 | 378.5 | 202 | 246 | 448 | 191 | 233 | 424 | 75º 32' 48.765" E | 28º 48' 36.589" N | 553363.465 | 3187076.399 |  |  |  |  | Jhumpa Kalan
[5 empty] | 414 | [23 empty] | Cart Track
9 |  | 2A/2 | DA+0 | 48.15 |  |  | 2580.763 | [7 empty] | 211.698 |  | 811 | 405.5 | 168 | 178 | 346 | 182 | 185 | 367 | 75º 32' 53.404" E | 28º 48' 49.406" N | 553487.375 | 3187471.421 |  |  |  |  | Jhumpa Kalan
397
10 |  | 2A/3 | DA+0 | 48.15 |  |  | 2977.763 | [7 empty] | 215.259 |  | 747.278 | 373.639 | 220 | 213 | 433 | 213 | 200 | 413 | 75º 32' 57.852" E | 28º 49' 1.697" N | 553606.196 | 3187850.222 |  |  |  |  | Jhumpa Kalan
350.278
11 | AP2B/0 | 2B/0 | DB2+0 | 46.87 |  | 1504.278 | 3328.041 | [7 empty] | 210.23 | 14° 48' 37"LT | 688.278 | 344.139 | 137 | 147 | 284 | 151 | 156 | 307 | 75º 33' 1.777" E | 28º 49' 12.541" N | 553711.034 | 3188184.443 |  |  |  |  | Jhumpa Kalan
[5 empty] | 338 | [23 empty] | LT Line 2nos
12 |  | 2B/1 | DA+3 | 51.15 |  |  | 3666.041 | [7 empty] | 209.718 |  | 681.261 | 340.6305 | 192 | 150 | 342 | 183 | 159 | 342 | 75º 33' 2.401" E | 28º 49' 23.51" N | 553726.397 | 3188522.094 |  |  |  |  | Jhumpa Kalan
[5 empty] | 343.261 | [23 empty] | Metal Road
13 | AP2C/0 | 2C/0 | DD60+6 | 53.97 |  | 681.261 | 4009.302 | [7 empty] | 209.28 | 49° 11' 44"LT | 496.054 | 248.027 | 193 | 72 | 265 | 185 | 75 | 260 | 75º 33' 3.036" E | 28º 49' 34.649" N | 553742 | 3188865 |  |  |  |  | Jhumpa Kalan
[5 empty] | 152.793 | [23 empty] | 132KV S/C line (Hisar-Rajgarh)
14 | AP2D/0 | 2D/0 | DD60+6 | 53.97 |  | 152.793 | 4162.095 | [7 empty] | 209.501 | 54° 36' 16"RT | 597.793 | 298.8965 | 81 | 238 | 319 | 78 | 234 | 312 | 75º 32' 58.958" E | 28º 49' 38.078" N | 553631.002 | 3188970.001 |  |  |  |  | Jhumpa Kalan
[5 empty] | 445 | [23 empty] | Well, Solar Plate
15 |  | 2D/1 | DA+0 | 48.15 |  |  | 4607.095 | [7 empty] | 213.044 |  | 828 | 414 | 208 | 171 | 379 | 213 | 178 | 391 | 75º 33' 1.323" E | 28º 49' 52.387" N | 553693.042 | 3189410.655 |  |  |  |  | Jhumpa Kalan
[5 empty] | 383 | [23 empty] | Cart Track
16 |  | 2D/2 | DA+6 | 54.15 |  |  | 4990.095 | [7 empty] | 210.5 |  | 751.645 | 375.8225 | 213 | 175 | 388 | 206 | 179 | 385 | 75º 33' 3.358" E | 28º 50' 4.702" N | 553746.439 | 3189789.915 |  |  |  |  | Lilas
[5 empty] | 368.645 | [23 empty] | Solar plate, Nala, Bore well
17 |  | 2D/3 | DA+6 | 54.15 |  |  | 5358.74 | [7 empty] | 211.971 |  | 718.515 | 359.2575 | 194 | 216 | 410 | 191 | 202 | 393 | 75º 33' 5.317" E | 28º 50' 16.555" N | 553797.834 | 3190154.959 |  |  |  |  | Lilas
349.87
18 | AP2D/4 | 2D/4 | DA+0 | 48.15 |  |  | 5708.61 | [7 empty] | 211.84 | 0° 51' 45"RT | 764.87 | 382.435 | 134 | 146 | 280 | 148 | 167 | 315 | 75º 33' 7.176" E | 28º 50' 27.805" N | 553846.612 | 3190501.412 |  |  |  |  | Lilas
[5 empty] | 415 | [23 empty] | Cart Track
19 |  | 2D/5 | DA+6 | 54.15 |  |  | 6123.61 | [7 empty] | 216.904 |  | 819.484 | 409.742 | 270 | 286 | 556 | 249 | 258 | 507 | 75º 33' 9.61" E | 28º 50' 41.118" N | 553910.649 | 3190911.442 |  |  |  |  | Lilas
[5 empty] | 404.484 | [23 empty] | Metal Road, 11kv Line
20 | AP3/0 | 3/0 | DB1+0 | 46.87 |  | 2365.999 | 6528.094 | [7 empty] | 209.057 | 1° 55' 54"RT | 729.483 | 364.7415 | 119 | 141 | 260 | 148 | 148 | 296 | 75º 33' 11.982" E | 28º 50' 54.094" N | 553973.063 | 3191311.081 |  |  |  |  | Lilas
325
21 |  | 3/1 | DA+0 | 48.15 |  |  | 6853.094 | [7 empty] | 211.492 |  | 711 | 355.5 | 176 | 180 | 356 | 172 | 185 | 357 | 75°33'14.286"E | 28°51'4.458"N | 554034.008 | 3191630.316 |  |  |  |  | Lilas
[5 empty] | 386 | [23 empty] | Cart track
22 |  | 3/2 | DA+3 | 51.15 |  |  | 7239.094 | [7 empty] | 210.684 |  | 820 | 410 | 206 | 244 | 450 | 202 | 236 | 438 | 75°33'17.023"E | 28°51'16.766"N | 554106.391 | 3192009.468 |  |  |  |  | Lilas
[5 empty] | 434 | [23 empty] | Cart track
23 |  | 3/3 | DA+0 | 48.15 |  |  | 7673.094 | [7 empty] | 208.692 |  | 826 | 413 | 191 | 186 | 377 | 200 | 189 | 389 | 75°33'20.1"E | 28°51'30.606"N | 554187.776 | 3192435.769 |  |  |  |  | Lilas
[5 empty] | 392 | [23 empty] | Cart track
24 |  | 3/4 | DA+3 | 51.15 |  |  | 8065.094 | [7 empty] | 207.482 |  | 796 | 398 | 207 | 208 | 415 | 204 | 206 | 410 | 75°33'22.88"E | 28°51'43.105"N | 554261.285 | 3192820.815 |  |  |  |  | Siwani
[5 empty] | 404 | [23 empty] | Cart track
25 |  | 3/5 | DA+3 | 51.15 |  |  | 8469.094 | [7 empty] | 206.484 |  | 802 | 401 | 197 | 157 | 354 | 199 | 172 | 371 | 75°33'25.745"E | 28°51'55.988"N | 554337.043 | 3193217.648 |  |  |  |  | Siwani
398
26 |  | 3/6 | DA+6 | 54.15 |  |  | 8867.094 | [7 empty] | 210.697 |  | 839 | 419.5 | 241 | 221 | 462 | 228 | 221 | 449 | 75°33'28.568"E | 28°52'8.679"N | 554411.677 | 3193608.588 |  |  |  |  | Siwani
[5 empty] | 441 | [23 empty] | Cart track
27 |  | 3/7 | DA+9 | 57.15 |  |  | 9308.094 | [7 empty] | 207.653 |  | 826 | 413 | 221 | 234 | 455 | 221 | 221 | 442 | 75°33'31.696"E | 28°52'22.742"N | 554494.375 | 3194041.765 |  |  |  |  | Siwani
385
28 |  | 3/8 | DA+3 | 51.15 |  |  | 9693.094 | [7 empty] | 206.739 |  | 819 | 409.5 | 151 | 229 | 380 | 165 | 226 | 391 | 75°33'34.427"E | 28°52'35.018"N | 554566.571 | 3194419.935 |  |  |  |  | Siwani
[5 empty] | 434 | [23 empty] | Cart track
29 |  | 3/9 | DA+0 | 48.15 |  |  | 10127.094 | [7 empty] | 207.556 |  | 836 | 418 | 206 | 128 | 334 | 210 | 153 | 363 | 75°33'37.505"E | 28°52'48.857"N | 554647.955 | 3194846.236 |  |  |  |  | Siwani
402
30 |  | 3/10 | DA+6 | 54.15 |  |  | 10529.094 | [7 empty] | 214.257 |  | 793.079 | 396.5395 | 275 | 273 | 548 | 251 | 248 | 499 | 75°33'40.357"E | 28°53'1.676"N | 554723.339 | 3195241.105 |  |  |  |  | Siwani
[5 empty] | 391.079 | [23 empty] | 11kV line, Cart track
31 | AP4/0 | 4/0 | DB2+3 | 49.87 |  | 4392.079 | 10920.173 | [7 empty] | 204.85 | 13° 1' 47"RT | 783.079 | 391.5395 | 119 | 201 | 320 | 145 | 200 | 345 | 75°33'43.132"E | 28°53'14.147"N | 554796.675 | 3195625.246 |  |  |  |  | Devsar 2
[5 empty] | 392 | [23 empty] | 11kV lines
32 |  | 4/1 | DA+3 | 51.15 |  |  | 11312.173 | [7 empty] | 203.404 |  | 792 | 396 | 191 | 190 | 381 | 193 | 194 | 387 | 75°33'49.044"E | 28°53'25.773"N | 554955.102 | 3195983.805 |  |  |  |  | Devsar 2
[5 empty] | 400 | [23 empty] | 11kV lines, Metal road, Cart track, Pump house
33 |  | 4/2 | DA+6 | 54.15 |  |  | 11712.173 | [7 empty] | 202.162 |  | 801 | 400.5 | 211 | 218 | 429 | 207 | 212 | 419 | 75°33'55.077"E | 28°53'37.636"N | 555116.763 | 3196349.682 |  |  |  |  | Kikral
[5 empty] | 401 | [23 empty] | 11kV lines, Cart track, Canal, Pump house
34 |  | 4/3 | DA+3 | 51.15 |  |  | 12113.173 | [7 empty] | 202.233 |  | 787 | 393.5 | 183 | 212 | 395 | 190 | 206 | 396 | 75°34'1.125"E | 28°53'49.529"N | 555278.828 | 3196716.474 |  |  |  |  | Kikral
[5 empty] | 386 | [23 empty] | Solar panel, Nala, Cart track
35 |  | 4/4 | DA+0 | 48.15 |  |  | 12499.173 | [7 empty] | 202.139 |  | 708 | 354 | 174 | 155 | 329 | 181 | 158 | 339 | 75°34'6.948"E | 28°54'0.976"N | 555434.83 | 3197069.545 |  |  |  |  | Kikral
[5 empty] | 322 | [23 empty] | Cart track, 11kV line
36 |  | 4/5 | DA+0 | 48.15 |  |  | 12821.173 | [7 empty] | 202.933 |  | 623 | 311.5 | 167 | 152 | 319 | 165 | 152 | 317 | 75°34'11.805"E | 28°54'10.526"N | 555564.967 | 3197364.076 |  |  |  |  | Kikral
301
37 |  | 4/6 | DA+0 | 48.15 |  |  | 13122.173 | [7 empty] | 202.694 |  | 675.546 | 337.773 | 149 | 189 | 338 | 150 | 189 | 339 | 75°34'16.346"E | 28°54'19.453"N | 555686.617 | 3197639.398 |  |  |  |  | Kikral
[5 empty] | 374.546 | [23 empty] | Pump house, Bore
38 | AP5/0 | 5/0 | DC2+0 | 47.07 |  | 2576.546 | 13496.719 | [7 empty] | 202.891 | 28° 2' 29"LT | 804.546 | 402.273 | 186 | 164 | 350 | 187 | 182 | 369 | 75°34'21.997"E | 28°54'30.561"N | 555837.99 | 3197981.992 |  |  |  |  | Kikral
[5 empty] | 430 | [23 empty] | 11kV lines, Cart track, Metal road
39 |  | 5/1 | DA+9 | 57.15 |  |  | 13926.719 | [7 empty] | 202.893 |  | 831 | 415.5 | 266 | 258 | 524 | 249 | 239 | 488 | 75°34'20.909"E | 28°54'44.5"N | 555806.472 | 3198410.835 |  |  |  |  | Kikral
[5 empty] | 401 | [23 empty] | Cart track
40 |  | 5/2 | DA+0 | 48.15 |  |  | 14327.719 | [7 empty] | 202.062 |  | 802 | 401 | 144 | 189 | 333 | 163 | 194 | 357 | 75°34'19.895"E | 28°54'57.499"N | 555777.079 | 3198810.757 |  |  |  |  | Kikral
[5 empty] | 401 | [23 empty] | Cart track, Bore
41 |  | 5/3 | DA+3 | 51.15 |  |  | 14728.719 | [7 empty] | 201.022 |  | 840 | 420 | 212 | 174 | 386 | 209 | 190 | 399 | 75°34'18.881"E | 28°55'10.498"N | 555747.687 | 3199210.678 |  |  |  |  | Kikral
[5 empty] | 439 | [23 empty] | 11kV line, Solar panel, Cart track, Metal road, Pump house, Pond, Canal
42 |  | 5/4 | DA+6 | 54.15 |  |  | 15167.719 | [7 empty] | 206.627 |  | 801 | 400.5 | 266 | 161 | 427 | 250 | 168 | 418 | 75°34'17.771"E | 28°55'24.729"N | 555715.509 | 3199648.497 |  |  |  |  | Dhani Ramjas
[5 empty] | 362 | [23 empty] | 11kV lines, LT line, Metal road
43 |  | 5/5 | DA+9 | 57.15 |  |  | 15529.719 | [7 empty] | 206.72 |  | 759 | 379.5 | 201 | 293 | 494 | 195 | 261 | 456 | 75°34'16.855"E | 28°55'36.463"N | 555688.975 | 3200009.523 |  |  |  |  | Dhani Ramjas
[5 empty] | 397 | [23 empty] | Nala, Pump house
44 |  | 5/6 | DA-3 | 45.15 |  |  | 15926.719 | [7 empty] | 202.649 |  | 734 | 367 | 104 | 166 | 270 | 137 | 167 | 304 | 75°34'15.851"E | 28°55'49.333"N | 555659.876 | 3200405.455 |  |  |  |  | Dhani Ramjas
[5 empty] | 337 | [23 empty] | Metal road, Nala
45 |  | 5/7 | DA-3 | 45.15 |  |  | 16263.719 | [7 empty] | 202.964 |  | 681.26 | 340.63 | 171 | 154 | 325 | 170 | 161 | 331 | 75°34'14.998"E | 28°56'0.257"N | 555635.175 | 3200741.549 |  |  |  |  | Dhani Ramjas
[5 empty] | 344.26 | [23 empty] | Solar panel, Nala
46 | AP6/0 | 6/0 | DB1+0 | 46.87 |  | 3111.26 | 16607.979 | [7 empty] | 203.236 | 4° 11' 46"RT | 753.26 | 376.63 | 190 | 168 | 358 | 184 | 181 | 365 | 75°34'14.127"E | 28°56'11.417"N | 555609.941 | 3201084.883 |  |  |  |  | Dhani Ramjas
409
47 |  | 6/1 | DA+6 | 54.15 |  |  | 17016.979 | [7 empty] | 203.061 |  | 841 | 420.5 | 241 | 214 | 455 | 230 | 215 | 445 | 75°34'14.198"E | 28°56'24.706"N | 555609.889 | 3201493.883 |  |  |  |  | Dhani Ramjas
[5 empty] | 432 | [23 empty] | Cart track
48 |  | 6/2 | DA+0 | 48.15 |  |  | 17448.979 | [7 empty] | 209.489 |  | 825 | 412.5 | 219 | 164 | 383 | 218 | 175 | 393 | 75°34'14.273"E | 28°56'38.743"N | 555609.834 | 3201925.883 |  |  |  |  | Dhani Ramjas
393
49 |  | 6/3 | DA+6 | 54.15 |  |  | 17841.979 | [7 empty] | 209.076 |  | 844 | 422 | 230 | 218 | 448 | 219 | 221 | 440 | 75°34'14.341"E | 28°56'51.512"N | 555609.784 | 3202318.883 |  |  |  |  | Badwa
451
50 |  | 6/4 | DA+0 | 48.15 |  |  | 18292.979 | [7 empty] | 216.668 |  | 838 | 419 | 234 | 157 | 391 | 232 | 170 | 402 | 75°34'14.419"E | 28°57'6.166"N | 555609.727 | 3202769.883 |  |  |  |  | Badwa
387
51 |  | 6/5 | DA+9 | 57.15 |  |  | 18679.979 | [7 empty] | 213.748 |  | 769 | 384.5 | 230 | 281 | 511 | 218 | 252 | 470 | 75°34'14.487"E | 28°57'18.74"N | 555609.678 | 3203156.883 |  |  |  |  | Badwa
[5 empty] | 382 | [23 empty] | 33kV line, 11kV line, Metal road, Cart track
52 |  | 6/6 | DA+0 | 48.15 |  |  | 19061.979 | [7 empty] | 207.958 |  | 796 | 398 | 102 | 151 | 253 | 132 | 170 | 302 | 75°34'14.553"E | 28°57'31.152"N | 555609.63 | 3203538.883 |  |  |  |  | Badwa
[5 empty] | 414 | [23 empty] | Cart track
53 |  | 6/7 | DA+0 | 48.15 |  |  | 19475.979 | [7 empty] | 218.122 |  | 799 | 399.5 | 264 | 208 | 472 | 246 | 203 | 449 | 75°34'14.625"E | 28°57'44.604"N | 555609.577 | 3203952.883 |  |  |  |  | Badwa
[5 empty] | 385 | [23 empty] | Cart track
54 |  | 6/8 | DA+9 | 57.15 |  |  | 19860.979 | [7 empty] | 206.621 |  | 822 | 411 | 178 | 233 | 411 | 183 | 229 | 412 | 75°34'14.692"E | 28°57'57.113"N | 555609.528 | 3204337.883 |  |  |  |  | Badwa
[5 empty] | 437 | [23 empty] | Cart track
55 |  | 6/9 | DA+3 | 51.15 |  |  | 20297.979 | [7 empty] | 209.92 |  | 813 | 406.5 | 205 | 250 | 455 | 210 | 230 | 440 | 75°34'14.767"E | 28°58'11.313"N | 555609.473 | 3204774.883 |  |  |  |  | Badwa
[5 empty] | 376 | [23 empty] | LT line, Cart track
56 |  | 6/10 | DA+0 | 48.15 |  |  | 20673.979 | [7 empty] | 202.816 |  | 692.217 | 346.1085 | 126 | 118 | 244 | 147 | 131 | 278 | 75°34'14.833"E | 28°58'23.53"N | 555609.425 | 3205150.883 |  |  |  |  | Badwa
[5 empty] | 316.217 | [23 empty] | 11kV ;ine, Metal road, Nala, Bore
57 | AP7/0 | 7/0 | DB1+0 | 46.87 |  | 4382.217 | 20990.196 | [7 empty] | 208.979 | 6° 20' 14"RT | 700.217 | 350.1085 | 199 | 178 | 377 | 186 | 183 | 369 | 75°34'14.888"E | 28°58'33.804"N | 555609.385 | 3205467.1 |  |  |  |  | Badwa
384
58 |  | 7/1 | DA+3 | 51.15 |  |  | 21374.196 | [7 empty] | 207.752 |  | 771 | 385.5 | 207 | 141 | 348 | 202 | 159 | 361 | 75°34'16.52"E | 28°58'46.198"N | 555651.722 | 3205848.759 |  |  |  |  | Badwa
[5 empty] | 387 | [23 empty] | Cart track
59 |  | 7/2 | DA+0 | 48.15 |  |  | 21761.196 | [7 empty] | 219.536 |  | 776 | 388 | 246 | 160 | 406 | 229 | 172 | 401 | 75°34'18.165"E | 28°58'58.689"N | 555694.39 | 3206233.4 |  |  |  |  | Gawar | Balsamand
[5 empty] | 389 | [23 empty] | Brick road, Cart track
60 |  | 7/3 | DA+6 | 54.15 |  |  | 22150.196 | [7 empty] | 219.3 |  | 813 | 406.5 | 229 | 264 | 493 | 218 | 247 | 465 | 75°34'19.819"E | 28°59'11.245"N | 555737.279 | 3206620.028 |  |  |  |  | Gawar
424
61 |  | 7/4 | DA+6 | 54.15 |  |  | 22574.196 | [7 empty] | 209.789 |  | 840.069 | 420.0345 | 160 | 252 | 412 | 178 | 238 | 416 | 75°34'21.622"E | 28°59'24.93"N | 555784.026 | 3207041.443 |  |  |  |  | Gawar
[5 empty] | 416.069 | [23 empty] | 11kV lines, Metal road, Cart track
62 | AP8/0 | 8/0 | DB2+0 | 46.87 |  | 2000.069 | 22990.265 | [7 empty] | 208.511 | 10° 28' 15"LT | 780.069 | 390.0345 | 164 | 209 | 373 | 179 | 200 | 379 | 75°34'23.392"E | 28°59'38.359"N | 555829.899 | 3207454.976 |  |  |  |  | Gawar
364
63 |  | 8/1 | DA+0 | 48.15 |  |  | 23354.265 | [7 empty] | 203.73 |  | 701 | 350.5 | 156 | 177 | 333 | 165 | 175 | 340 | 75°34'22.485"E | 28°59'50.16"N | 555803.616 | 3207818.026 |  |  |  |  | Gawar
[5 empty] | 337 | [23 empty] | 11kV line, Cart track, Nala
64 |  | 8/2 | DA+0 | 48.15 |  |  | 23691.265 | [7 empty] | 202.459 |  | 771 | 385.5 | 160 | 181 | 341 | 163 | 193 | 356 | 75°34'21.646"E | 29°0'1.085"N | 555779.282 | 3208154.146 |  |  |  |  | Gawar
[5 empty] | 434 | [23 empty] | Solar panel, Cart track, Nala, Bore
65 |  | 8/3 | DA+6 | 54.15 |  |  | 24125.265 | [7 empty] | 203.318 |  | 835 | 417.5 | 254 | 215 | 469 | 242 | 210 | 452 | 75°34'20.566"E | 29°0'15.154"N | 555747.944 | 3208587.013 |  |  |  |  | Gawar | Hisar
401
66 |  | 8/4 | DA+3 | 51.15 |  |  | 24526.265 | [7 empty] | 203.925 |  | 773 | 386.5 | 187 | 223 | 410 | 192 | 211 | 403 | 75°34'19.567"E | 29°0'28.154"N | 555718.99 | 3208986.967 |  |  |  |  | Chaudhariwas
372
67 |  | 8/5 | DA-3 | 45.15 |  |  | 24898.265 | [7 empty] | 204.054 |  | 740 | 370 | 150 | 165 | 315 | 162 | 172 | 334 | 75°34'18.641"E | 29°0'40.214"N | 555692.129 | 3209357.996 |  |  |  |  | Gorchhi
[5 empty] | 368 | [23 empty] | Cart track
68 |  | 8/6 | DA+0 | 48.15 |  |  | 25266.265 | [7 empty] | 204.047 |  | 788 | 394 | 203 | 179 | 382 | 197 | 190 | 387 | 75°34'17.724"E | 29°0'52.144"N | 555665.557 | 3209725.035 |  |  |  |  | Gorchhi | Balsamand
[5 empty] | 420 | [23 empty] | Cart track, Metal road
69 |  | 8/7 | DA+6 | 54.15 |  |  | 25686.265 | [7 empty] | 203.652 |  | 831 | 415.5 | 241 | 235 | 476 | 231 | 225 | 456 | 75°34'16.678"E | 29°1'5.759"N | 555635.23 | 3210143.939 |  |  |  |  | Gorchhi
[5 empty] | 411 | [23 empty] | Cart track, Bore
70 |  | 8/8 | DA+0 | 48.15 |  |  | 26097.265 | [7 empty] | 204.541 |  | 834 | 417 | 177 | 176 | 353 | 187 | 188 | 375 | 75°34'15.654"E | 29°1'19.083"N | 555605.553 | 3210553.866 |  |  |  |  | Gorchhi
[5 empty] | 423 | [23 empty] | Cart track, Nala, Pump house, Bore
71 |  | 8/9 | DA+3 | 51.15 |  |  | 26520.265 | [7 empty] | 208.059 |  | 839.365 | 419.6825 | 248 | 253 | 501 | 236 | 238 | 474 | 75°34'14.6"E | 29°1'32.796"N | 555575.009 | 3210975.762 |  |  |  |  | Gorchhi
[5 empty] | 416.365 | [23 empty] | Cart track
72 | AP9/0 | 9/0 | DC2+0 | 47.07 |  | 3946.365 | 26936.63 | [7 empty] | 203.533 | 29° 23' 56"RT | 818.365 | 409.1825 | 164 | 179 | 343 | 180 | 187 | 367 | 75°34'13.563"E | 29°1'46.294"N | 555544.945 | 3211391.04 |  |  |  |  | Gorchhi
[5 empty] | 402 | [23 empty] | Metal road
73 |  | 9/1 | DA+3 | 51.15 |  |  | 27338.63 | [7 empty] | 204.004 |  | 790 | 395 | 224 | 206 | 430 | 216 | 202 | 418 | 75°34'19.97"E | 29°1'58.08"N | 555716.478 | 3211754.606 |  |  |  |  | Gorchhi
[5 empty] | 388 | [23 empty] | Nala, Metal road
74 |  | 9/2 | DA+0 | 48.15 |  |  | 27726.63 | [7 empty] | 205.024 |  | 770.444 | 385.222 | 182 | 188 | 370 | 187 | 189 | 376 | 75°34'26.154"E | 29°2'9.455"N | 555882.037 | 3212105.511 |  |  |  |  | Gorchhi
[5 empty] | 382.444 | [23 empty] | LT line, Cart track
75 | AP10/0 | 10/0 | DD45+0 | 47.97 |  | 1172.444 | 28109.074 | [7 empty] | 205.122 | 32° 24' 39"LT | 787.444 | 393.722 | 195 | 191 | 386 | 194 | 195 | 389 | 75°34'32.249"E | 29°2'20.668"N | 556045.225 | 3212451.391 |  |  |  |  | Gorchhi
[5 empty] | 405 | [23 empty] | Cart track, Pump house
76 |  | 10/1 | DA+3 | 51.15 |  |  | 28514.074 | [7 empty] | 204.609 |  | 821 | 410.5 | 214 | 225 | 439 | 211 | 220 | 431 | 75°34'30.457"E | 29°2'33.732"N | 555994.797 | 3212853.239 |  |  |  |  | Gorchhi
[5 empty] | 416 | [23 empty] | Cart track
77 |  | 10/2 | DA+0 | 48.15 |  |  | 28930.074 | [7 empty] | 204.558 |  | 823 | 411.5 | 191 | 185 | 376 | 197 | 192 | 389 | 75°34'28.617"E | 29°2'47.152"N | 555943 | 3213266.002 |  |  |  |  | Gorchhi
[5 empty] | 407 | [23 empty] | 11kV line, Gas pipeline, Nala
78 |  | 10/3 | DA+3 | 51.15 |  |  | 29337.074 | [7 empty] | 204.854 |  | 792.937 | 396.4685 | 222 | 214 | 436 | 217 | 207 | 424 | 75°34'26.815"E | 29°3'0.281"N | 555892.323 | 3213669.835 |  |  |  |  | Gorchhi
[5 empty] | 385.937 | [23 empty] | Cart track, Nala
79 | AP11/0 | 11/0 | DC2+0 | 47.07 |  | 1613.937 | 29723.011 | [7 empty] | 204.839 | 28° 0' 48"LT | 783.937 | 391.9685 | 173 | 179 | 352 | 180 | 186 | 366 | 75°34'25.107"E | 29°3'12.731"N | 555844.269 | 3214052.768 |  |  |  |  | Rawalwas Kalan
[5 empty] | 398 | [23 empty] | Nala
80 |  | 11/1 | DA+3 | 51.15 |  |  | 30121.011 | [7 empty] | 204.982 |  | 810.384 | 405.192 | 220 | 213 | 433 | 213 | 211 | 424 | 75°34'16.689"E | 29°3'23.338"N | 555615.043 | 3214378.129 |  |  |  |  | Rawalwas Kalan
[5 empty] | 412.384 | [23 empty] | Metal road, Cart track, Nala
81 | AP12/0 | 12/0 | DC2+3 | 50.07 |  | 810.384 | 30533.395 | [7 empty] | 204.219 | 28° 4' 23"RT | 823.384 | 411.692 | 200 | 171 | 371 | 202 | 183 | 385 | 75°34'7.966"E | 29°3'34.329"N | 555377.533 | 3214715.248 |  |  |  |  | Rawalwas Kalan
[5 empty] | 411 | [23 empty] | 11kV lines, Cart track
82 |  | 12/1 | DA+9 | 57.15 |  |  | 30944.395 | [7 empty] | 204.041 |  | 843 | 421.5 | 241 | 263 | 504 | 230 | 249 | 479 | 75°34'6.162"E | 29°3'47.589"N | 555326.784 | 3215123.103 |  |  |  |  | Rawalwas Kalan
[5 empty] | 432 | [23 empty] | 11kV line, Metal road, Pump house
83 |  | 12/2 | DA+0 | 48.15 |  |  | 31376.395 | [7 empty] | 204.176 |  | 801 | 400.5 | 169 | 183 | 352 | 185 | 184 | 369 | 75°34'4.266"E | 29°4'1.526"N | 555273.442 | 3215551.797 |  |  |  |  | Rawalwas Kalan
[5 empty] | 369 | [23 empty] | Cart track
84 |  | 12/3 | DA+0 | 48.15 |  |  | 31745.395 | [7 empty] | 204.372 |  | 794 | 397 | 186 | 179 | 365 | 186 | 190 | 376 | 75°34'2.646"E | 29°4'13.431"N | 555227.879 | 3215917.973 |  |  |  |  | Rawalwas Kalan
[5 empty] | 425 | [23 empty] | Cart track, Nala
85 |  | 12/4 | DA+6 | 54.15 |  |  | 32170.395 | [7 empty] | 204.707 |  | 809.259 | 404.6295 | 247 | 211 | 458 | 236 | 205 | 441 | 75°34'0.78"E | 29°4'27.143"N | 555175.401 | 3216339.721 |  |  |  |  | Rawalwas Kalan
[5 empty] | 384.259 | [23 empty] | LT line, Brick road
86 | AP13/0 | 13/0 | DC1+3 | 50.07 |  | 2021.259 | 32554.654 | [7 empty] | 205.025 | 15° 59' 4"LT | 784.817 | 392.4085 | 174 | 216 | 390 | 180 | 211 | 391 | 75°33'59.093"E | 29°4'39.54"N | 555127.954 | 3216721.039 |  |  |  |  | Rawalwas Kalan
[5 empty] | 400.558 | [23 empty] | 33kV line, 11kV lines, MDR 107
87 | AP14/0 | 14/0 | DC1+0 | 47.07 |  | 400.56 | 32955.212 | [7 empty] | 205.317 | 21° 21' 47"RT | 813.558 | 406.779 | 185 | 188 | 373 | 190 | 195 | 385 | 75°33'53.351"E | 29°4'51.537"N | 554970.946 | 3217089.543 |  |  |  |  | Rawalwas Kalan
[5 empty] | 413 | [23 empty] | 11kV line
88 |  | 14/1 | DA+3 | 51.15 |  |  | 33368.212 | [7 empty] | 205.229 |  | 801.988 | 400.994 | 223 | 210 | 433 | 218 | 206 | 424 | 75°33'52.967"E | 29°5'4.952"N | 554958.59 | 3217502.358 |  |  |  |  | Rawalwas Kalan
[5 empty] | 388.988 | [23 empty] | Cart track, Canal, Pump house
89 | AP15/0 | 15/0 | DC2+0 | 47.07 |  | 801.988 | 33757.2 | [7 empty] | 205.502 | 27° 14' 32"RT | 821.988 | 410.994 | 179 | 169 | 348 | 185 | 186 | 371 | 75°33'52.606"E | 29°5'17.587"N | 554946.953 | 3217891.172 |  |  |  |  | Rawalwas Kalan
[5 empty] | 433 | [23 empty] | 11kV lines, LT line, Pump house, Nala, Metal road
90 |  | 15/1 | DA+9 | 57.15 |  |  | 34190.2 | [7 empty] | 205.442 |  | 841 | 420.5 | 264 | 259 | 523 | 249 | 241 | 490 | 75°33'59.578"E | 29°5'30.253"N | 555133.555 | 3218281.901 |  |  |  |  | Rawalwas Kalan
[5 empty] | 408 | [23 empty] | Cart track, Bore, LT line
91 |  | 15/2 | DA+0 | 48.15 |  |  | 34598.2 | [7 empty] | 204.854 |  | 775 | 387.5 | 150 | 196 | 346 | 168 | 192 | 360 | 75°34'6.148"E | 29°5'42.188"N | 555309.383 | 3218650.07 |  |  |  |  | Rawalwas Kalan
[5 empty] | 367 | [23 empty] | Well
92 |  | 15/3 | DA-3 | 45.15 |  |  | 34965.2 | [7 empty] | 205.946 |  | 758.859 | 379.4295 | 172 | 165 | 337 | 176 | 175 | 351 | 75°34'12.058"E | 29°5'52.924"N | 555467.543 | 3218981.241 |  |  |  |  | Rawalwas Khurd | Hisar
[5 empty] | 391.859 | [23 empty] | Cart track
93 | AP16/0 | 16/0 | DC2+3 | 50.07 |  | 1599.859 | 35357.059 | [7 empty] | 205.183 | 25° 32' 54"LT | 797.859 | 398.9295 | 228 | 189 | 417 | 217 | 194 | 411 | 75°34'18.369"E | 29°6'4.386"N | 555636.415 | 3219334.845 |  |  |  |  | Rawalwas Khurd
[5 empty] | 406 | [23 empty] | Metal road, 11kV line
94 |  | 16/1 | DA+6 | 54.15 |  |  | 35763.059 | [7 empty] | 204.796 |  | 808 | 404 | 218 | 232 | 450 | 213 | 222 | 435 | 75°34'18.436"E | 29°6'17.578"N | 555636.271 | 3219740.845 |  |  |  |  | Rawalwas Khurd
[5 empty] | 402 | [23 empty] | 11kV line
95 |  | 16/2 | DA+0 | 48.15 |  |  | 36165.059 | [7 empty] | 205.403 |  | 811 | 405.5 | 170 | 191 | 361 | 181 | 196 | 377 | 75°34'18.503"E | 29°6'30.639"N | 555636.129 | 3220142.845 |  |  |  |  | Rawalwas Khurd
409
96 |  | 16/3 | DA+3 | 51.15 |  |  | 36574.059 | [7 empty] | 204.805 |  | 841 | 420.5 | 218 | 212 | 430 | 214 | 214 | 428 | 75°34'18.571"E | 29°6'43.928"N | 555635.983 | 3220551.845 |  |  |  |  | Rawalwas Khurd
[5 empty] | 432 | [23 empty] | Cart track
97 |  | 16/4 | DA+3 | 51.15 |  |  | 37006.059 | [7 empty] | 205.582 |  | 833 | 416.5 | 220 | 186 | 406 | 219 | 191 | 410 | 75°34'18.643"E | 29°6'57.964"N | 555635.83 | 3220983.845 |  |  |  |  | Siswala | Balsamand
[5 empty] | 401 | [23 empty] | 11kV line
98 |  | 16/5 | DA+6 | 54.15 |  |  | 37407.059 | [7 empty] | 205.138 |  | 825 | 412.5 | 216 | 243 | 459 | 211 | 233 | 444 | 75°34'18.71"E | 29°7'10.993"N | 555635.688 | 3221384.845 |  |  |  |  | Siswala
[5 empty] | 424 | [23 empty] | 11kV line, Brick road, Pump house
99 |  | 16/6 | DA+0 | 48.15 |  |  | 37831.059 | [7 empty] | 205.58 |  | 816 | 408 | 182 | 195 | 377 | 192 | 196 | 388 | 75°34'18.781"E | 29°7'24.77"N | 555635.538 | 3221808.845 |  |  |  |  | Siswala
[5 empty] | 392 | [23 empty] | Cart track
100 |  | 16/7 | DA+0 | 48.15 |  |  | 38223.059 | [7 empty] | 205.82 |  | 759 | 379.5 | 198 | 183 | 381 | 197 | 183 | 380 | 75°34'18.846"E | 29°7'37.506"N | 555635.399 | 3222200.845 |  |  |  |  | Siswala
[5 empty] | 367 | [23 empty] | Cart track, Canal, 11kV line
101 |  | 16/8 | DA+0 | 48.15 |  |  | 38590.059 | [7 empty] | 205.962 |  | 729.955 | 364.9775 | 185 | 181 | 366 | 185 | 182 | 367 | 75°34'18.907"E | 29°7'49.431"N | 555635.269 | 3222567.845 |  |  |  |  | Siswala
[5 empty] | 362.955 | [23 empty] | 11kV line
102 | AP17/0 | 17/0 | DB2+0 | 46.87 |  | 3595.955 | 38953.014 | [7 empty] | 205.921 | 10° 35' 46"RT | 708.955 | 354.4775 | 182 | 173 | 355 | 182 | 174 | 356 | 75°34'18.968"E | 29°8'1.224"N | 555635.14 | 3222930.8 |  |  |  |  | Siswala
[5 empty] | 346 | [23 empty] | 11kV line, Cart track
103 |  | 17/1 | DA+0 | 48.15 |  |  | 39299.014 | [7 empty] | 205.974 |  | 730 | 365 | 173 | 192 | 365 | 173 | 193 | 366 | 75°34'21.379"E | 29°8'12.265"N | 555698.643 | 3223270.923 |  |  |  |  | Mattarsham | Hisar
[5 empty] | 384 | [23 empty] | Bore, Nala, Cart track
104 |  | 17/2 | DA+0 | 48.15 |  |  | 39683.014 | [7 empty] | 205.974 |  | 790 | 395 | 192 | 186 | 378 | 193 | 192 | 385 | 75°34'24.055"E | 29°8'24.518"N | 555769.12 | 3223648.4 |  |  |  |  | Kirtan | Balsamand
[5 empty] | 406 | [23 empty] | Solar panel, Pond, Pump house, Cart track
105 |  | 17/3 | DA+3 | 51.15 |  |  | 40089.014 | [7 empty] | 205.903 |  | 825 | 412.5 | 220 | 222 | 442 | 215 | 218 | 433 | 75°34'26.885"E | 29°8'37.474"N | 555843.634 | 3224047.503 |  |  |  |  | Kirtan
[5 empty] | 419 | [23 empty] | Cart track, 11kV line
106 |  | 17/4 | DA+0 | 48.15 |  |  | 40508.014 | [7 empty] | 206.652 |  | 800 | 400 | 197 | 180 | 377 | 202 | 184 | 386 | 75°34'29.806"E | 29°8'50.844"N | 555920.535 | 3224459.386 |  |  |  |  | Kirtan
[5 empty] | 381 | [23 empty] | Nala
107 |  | 17/5 | DA+3 | 51.15 |  |  | 40889.014 | [7 empty] | 205.48 |  | 789 | 394.5 | 202 | 221 | 423 | 198 | 216 | 414 | 75°34'32.462"E | 29°9'3.002"N | 555990.462 | 3224833.914 |  |  |  |  | Kirtan
[5 empty] | 408 | [23 empty] | Nala
108 |  | 17/6 | DA+0 | 48.15 |  |  | 41297.014 | [7 empty] | 205.472 |  | 806 | 403 | 187 | 172 | 359 | 193 | 181 | 374 | 75°34'35.306"E | 29°9'16.021"N | 556065.343 | 3225234.983 |  |  |  |  | Mattarsham | Hisar
[5 empty] | 398 | [23 empty] | Pump house, Cart track
109 |  | 17/7 | DA+3 | 51.15 |  |  | 41695.014 | [7 empty] | 207.166 |  | 803.185 | 401.5925 | 227 | 225 | 452 | 218 | 218 | 436 | 75°34'38.081"E | 29°9'28.721"N | 556138.39 | 3225626.223 |  |  |  |  | Mattarsham
[5 empty] | 405.185 | [23 empty] | Cart track
110 | AP18/0 | 18/0 | DB1+0 | 46.87 |  | 3147.185 | 42100.199 | [7 empty] | 206.26 | 3° 55' 26"LT | 801.185 | 400.5925 | 181 | 201 | 382 | 189 | 201 | 390 | 75°34'40.906"E | 29°9'41.65"N | 556212.755 | 3226024.525 |  |  |  |  | Mattarsham
[5 empty] | 396 | [23 empty] | Cart track, Canal, Nala, Solar panel, Pump house, Bore
111 |  | 18/1 | DA+0 | 48.15 |  |  | 42496.199 | [7 empty] | 205.821 |  | 782 | 391 | 195 | 194 | 389 | 197 | 194 | 391 | 75°34'42.676"E | 29°9'54.423"N | 556258.625 | 3226417.859 |  |  |  |  | Mattarsham
[5 empty] | 386 | [23 empty] | Cart track, Nala
112 |  | 18/2 | DA+0 | 48.15 |  |  | 42882.199 | [7 empty] | 205.664 |  | 759 | 379.5 | 192 | 196 | 388 | 193 | 193 | 386 | 75°34'44.401"E | 29°10'6.873"N | 556303.337 | 3226801.261 |  |  |  |  | Mattarsham
[5 empty] | 373 | [23 empty] | Solar Panel, Nala, Cart track
113 |  | 18/3 | DA-1.5 | 46.65 |  |  | 43255.199 | [7 empty] | 205.709 |  | 736 | 368 | 177 | 189 | 366 | 181 | 187 | 368 | 75°34'46.068"E | 29°10'18.904"N | 556346.544 | 3227171.75 |  |  |  |  | Mattarsham
[5 empty] | 363 | [23 empty] | 11kV line
114 |  | 18/4 | DA-1.5 | 46.65 |  |  | 43618.199 | [7 empty] | 204.601 |  | 746.043 | 373.0215 | 174 | 166 | 340 | 177 | 175 | 352 | 75°34'47.69"E | 29°10'30.612"N | 556388.591 | 3227532.306 |  |  |  |  | Mattarsham
[5 empty] | 383.043 | [23 empty] | Cart track, Canal, Solar panel, Pump house, Bore, 11kV line, LT line
115 | AP19/0 | 19/0 | DC2+3 | 50.07 |  | 1901.043 | 44001.242 | [7 empty] | 204.275 | 23° 0' 27"RT | 808.043 | 404.0215 | 218 | 205 | 423 | 209 | 208 | 417 | 75°34'49.402"E | 29°10'42.966"N | 556432.961 | 3227912.771 |  |  |  |  | Mattarsham
[5 empty] | 425 | [23 empty] | 11kV lines, Cart track, Metal road
116 |  | 19/1 | DA+3 | 51.15 |  |  | 44426.242 | [7 empty] | 205.851 |  | 813 | 406.5 | 221 | 231 | 452 | 219 | 219 | 438 | 75°34'57.256"E | 29°10'54.932"N | 556643.269 | 3228282.089 |  |  |  |  | Mattarsham
[5 empty] | 388 | [23 empty] | Nala
117 |  | 19/2 | DA-3 | 45.15 |  |  | 44814.242 | [7 empty] | 205.711 |  | 739.545 | 369.7725 | 157 | 153 | 310 | 170 | 161 | 331 | 75°35'4.427"E | 29°11'5.856"N | 556835.267 | 3228619.254 |  |  |  |  | Mattarsham
351.545
118 | AP20/0 | 20/0 | DC2+0 | 47.07 |  | 1164.545 | 45165.787 | [7 empty] | 206.013 | 23° 22' 34"LT | 724.706 | 362.353 | 198 | 189 | 387 | 191 | 188 | 379 | 75°35'10.924"E | 29°11'15.753"N | 557009.226 | 3228924.741 |  |  |  |  | Mattarsham
[5 empty] | 373.161 | [23 empty] | Metal road, Nala
119 | AP21/0 | 21/0 | DB2+0 | 46.87 |  | 373.16 | 45538.948 | [7 empty] | 205.703 | 12° 26' 36"RT | 717.162 | 358.581 | 185 | 177 | 362 | 186 | 175 | 361 | 75°35'12.505"E | 29°11'27.798"N | 557050.066 | 3229295.66 |  |  |  |  | Mattarsham
[5 empty] | 344.001 | [23 empty] | Cart track, 11kV line, Nala, LT line
120 |  | 21/1 | DA+0 | 48.15 |  |  | 45882.949 | [7 empty] | 205.159 |  | 661.001 | 330.5005 | 168 | 177 | 345 | 170 | 170 | 340 | 75°35'16.655"E | 29°11'38.365"N | 557160.507 | 3229621.45 |  |  |  |  | Mattarsham
317
121 |  | 21/2 | DA-3 | 45.15 |  |  | 46199.949 | [7 empty] | 205.721 |  | 639 | 319.5 | 140 | 161 | 301 | 148 | 161 | 309 | 75°35'20.479"E | 29°11'48.103"N | 557262.28 | 3229921.669 |  |  |  |  | Mattarsham
[5 empty] | 322 | [23 empty] | Metal road
122 |  | 21/3 | DA-3 | 45.15 |  |  | 46521.949 | [7 empty] | 205.728 |  | 702.273 | 351.1365 | 161 | 113 | 274 | 161 | 144 | 305 | 75°35'24.364"E | 29°11'57.994"N | 557365.658 | 3230226.623 |  |  |  |  | Mattarsham
[5 empty] | 380.273 | [23 empty] | Cart track, Nala
123 | AP22/0 | 22/0 | DD60+9 | 56.97 |  | 1363.274 | 46902.222 | [7 empty] | 205.696 | 1° 46' 15"RT | 630.776 | 315.388 | 268 | 157 | 425 | 237 | 141 | 378 | 75°35'28.952"E | 29°12'9.676"N | 557487.745 | 3230586.765 |  |  |  |  | Neoli Khurd | Adampur
[5 empty] | 250.503 | [23 empty] | Railway track, Cart track, Railway boundary, Metal road
124 | AP23/0 | 23/0 | DD60+6 | 53.97 |  | 250.5 | 47152.725 | [7 empty] | 205.746 | 15° 5' 38"LT | 644.503 | 322.2515 | 93 | 248 | 341 | 110 | 231 | 341 | 75°35'32.244"E | 29°12'17.285"N | 557575.462 | 3230821.408 |  |  |  |  | Neoli Khurd
394
125 |  | 23/1 | DA-3 | 45.15 |  |  | 47546.725 | [7 empty] | 206.257 |  | 777 | 388.5 | 147 | 153 | 300 | 164 | 166 | 330 | 75°35'33.691"E | 29°12'30.023"N | 557612.564 | 3231213.657 |  |  |  |  | Neoli Khurd
[5 empty] | 383 | [23 empty] | Pump house
126 |  | 23/2 | DA+3 | 51.15 |  |  | 47929.725 | [7 empty] | 206.613 |  | 795 | 397.5 | 230 | 223 | 453 | 218 | 218 | 436 | 75°35'35.098"E | 29°12'42.406"N | 557648.63 | 3231594.955 |  |  |  |  | Neoli Khurd
[5 empty] | 412 | [23 empty] | Cart track, Nala, Pump house
127 |  | 23/3 | DA+0 | 48.15 |  |  | 48341.725 | [7 empty] | 206.651 |  | 808 | 404 | 190 | 198 | 388 | 195 | 199 | 394 | 75°35'36.612"E | 29°12'55.726"N | 557687.427 | 3232005.125 |  |  |  |  | Neoli Khurd
396
128 |  | 23/4 | DA+0 | 48.15 |  |  | 48737.725 | [7 empty] | 206.661 |  | 831 | 415.5 | 198 | 186 | 384 | 199 | 197 | 396 | 75°35'38.067"E | 29°13'8.529"N | 557724.718 | 3232399.365 |  |  |  |  | Mallapur
[5 empty] | 435 | [23 empty] | Metal road, Nala
129 |  | 23/5 | DA+6 | 54.15 |  |  | 49172.725 | [7 empty] | 206.674 |  | 844 | 422 | 250 | 254 | 504 | 240 | 238 | 478 | 75°35'39.665"E | 29°13'22.593"N | 557765.681 | 3232832.432 |  |  |  |  | Mallapur
[5 empty] | 409 | [23 empty] | 11kV line, LT line, Nala, Pump house
130 |  | 23/6 | DA-1.5 | 46.65 |  |  | 49581.725 | [7 empty] | 205.428 |  | 768.991 | 384.4955 | 155 | 176 | 331 | 172 | 178 | 350 | 75°35'41.168"E | 29°13'35.817"N | 557804.195 | 3233239.615 |  |  |  |  | Mallapur
359.991
131 | AP24/0 | 24/0 | DB1+0 | 46.87 |  | 2788.991 | 49941.716 | [7 empty] | 204.414 | 5° 35' 15"LT | 753.991 | 376.9955 | 184 | 197 | 381 | 183 | 198 | 381 | 75°35'42.491"E | 29°13'47.455"N | 557838.095 | 3233598.006 |  |  |  |  | Mallapur
[5 empty] | 394 | [23 empty] | Metal Road
132 |  | 24/1 | DA+0 | 48.15 |  |  | 50335.716 | [7 empty] | 204.461 |  | 787 | 393.5 | 197 | 187 | 384 | 197 | 190 | 387 | 75°35'42.518"E | 29°14'0.257"N | 557836.83 | 3233992.004 |  |  |  |  | Mallapur
[5 empty] | 393 | [23 empty] | Cart Track
133 |  | 24/2 | DA+0 | 48.15 |  |  | 50728.716 | [7 empty] | 206.18 |  | 799 | 399.5 | 207 | 191 | 398 | 204 | 195 | 399 | 75°35'42.545"E | 29°14'13.026"N | 557835.568 | 3234385.002 |  |  |  |  | Mallapur
406
134 |  | 24/3 | DA+0 | 48.15 |  |  | 51134.716 | [7 empty] | 208.366 |  | 809 | 404.5 | 216 | 205 | 421 | 212 | 204 | 416 | 75°35'42.574"E | 29°14'26.217"N | 557834.264 | 3234791 |  |  |  |  | Kaijlan
[5 empty] | 403 | [23 empty] | Cart Track
135 |  | 24/4 | DA+1.5 | 49.65 |  |  | 51537.716 | [7 empty] | 206.261 |  | 806.728 | 403.364 | 198 | 210 | 408 | 200 | 208 | 408 | 75°35'42.601"E | 29°14'39.311"N | 557832.97 | 3235193.998 |  |  |  |  | Kaijlan
[5 empty] | 403.728 | [23 empty] | Cart Track/HUT HT-4M
136 | AP25/0 | 25/0 | DB2+0 | 46.87 |  | 1999.728 | 51941.444 | [7 empty] | 206.298 | 9° 57' 24"RT | 806.729 | 403.3645 | 194 | 189 | 383 | 197 | 194 | 391 | 75°35'42.629"E | 29°14'52.428"N | 557831.674 | 3235597.724 |  |  |  |  | Kaijlan
[5 empty] | 403.001 | [23 empty] | Cart Track/NALI
137 |  | 25/1 | DA+1.5 | 49.65 |  |  | 52344.445 | [7 empty] | 207.049 |  | 800.001 | 400.0005 | 214 | 214 | 428 | 210 | 209 | 419 | 75°35'45.238"E | 29°15'5.321"N | 557900.079 | 3235994.877 |  |  |  |  | Kaijlan
[5 empty] | 397 | [23 empty] | Cart Track
138 |  | 25/2 | DA+0 | 48.15 |  |  | 52741.445 | [7 empty] | 205.943 |  | 771.01 | 385.505 | 183 | 184 | 367 | 189 | 185 | 374 | 75°35'47.809"E | 29°15'18.021"N | 557967.466 | 3236386.116 |  |  |  |  | Ashrawan
[5 empty] | 374.01 | [23 empty] | LT LINE
139 | AP26/0 | 26/0 | DC1+0 | 47.07 |  | 1174.011 | 53115.455 | [7 empty] | 206.344 | 17° 43' 23"LT | 762.01 | 381.005 | 190 | 188 | 378 | 189 | 191 | 380 | 75°35'50.23"E | 29°15'29.986"N | 558030.95 | 3236754.699 |  |  |  |  | Ashrawan
[5 empty] | 388 | [23 empty] | NALI
140 |  | 26/1 | DA+0 | 48.15 |  |  | 53503.455 | [7 empty] | 207.403 |  | 824 | 412 | 200 | 186 | 386 | 198 | 197 | 395 | 75°35'48.314"E | 29°15'42.48"N | 557977.284 | 3237138.97 |  |  |  |  | Ashrawan
[5 empty] | 436 | [23 empty] | CART TRACK/NALI
141 |  | 26/2 | DA+6 | 54.15 |  |  | 53939.455 | [7 empty] | 207.446 |  | 817.286 | 408.643 | 250 | 228 | 478 | 240 | 216 | 456 | 75°35'46.161"E | 29°15'56.52"N | 557916.978 | 3237570.779 |  |  |  |  | Ashrawan
[5 empty] | 381.286 | [23 empty] | CART TRACK/11 KV LINE/11 KV LINE
142 | AP27/0 | 27/0 | DC1+0 | 47.07 |  | 1205.286 | 54320.741 | [7 empty] | 207.198 | 16° 3' 58"RT | 663.255 | 331.6275 | 154 | 171 | 325 | 166 | 157 | 323 | 75°35'44.278"E | 29°16'8.798"N | 557864.24 | 3237948.4 |  |  |  |  | Ashrawan
281.969
143 | AP28/0 | 28/0 | DC1-3 | 44.07 |  | 281.97 | 54602.71 | [7 empty] | 207.016 | 17° 19' 57"LT | 667.969 | 333.9845 | 112 | 121 | 233 | 126 | 148 | 274 | 75°35'45.806"E | 29°16'17.861"N | 557904.047 | 3238227.545 |  |  |  |  | Ashrawan
[5 empty] | 386 | [23 empty] | LT LINE /PH HT-4.3M/NALI/11KV LINE/CART TRACK/11KV LINE/CART TRACK
144 |  | 28/1 | DA+9 | 57.15 |  |  | 54988.71 | [7 empty] | 206.828 |  | 735.422 | 367.711 | 266 | 112 | 378 | 239 | 136 | 375 | 75°35'43.587"E | 29°16'30.25"N | 557842.222 | 3238608.562 |  |  |  |  | Ashrawan
[5 empty] | 349.422 | [23 empty] | NALI
145 | AP29/0 | 29/0 | DB2+18 | 64.87 |  | 735.422 | 55338.132 | [7 empty] | 206.941 | 12° 59' 54"LT | 595.412 | 297.706 | 238 | 257 | 495 | 215 | 185 | 400 | 75°35'41.578"E | 29°16'41.466"N | 557786.256 | 3238953.473 |  |  |  |  | Ashrawan
[5 empty] | 245.99 | [23 empty] | 11 KV LINE/132 KV SC KIRORI-BARWALA TL HVPNL/132 KV SC KIRORI-BARWALA TL HVPNL/CART TRACK/11 KV LINE
146 | AP30/0 | 30/0 | DC1+6 | 53.07 |  | 245.99 | 55584.122 | [7 empty] | 206.936 | 21° 39' 35"LT | 610.99 | 305.495 | -11 | 220 | 209 | 61 | 206 | 267 | 75°35'38.174"E | 29°16'48.88"N | 557693.252 | 3239181.204 |  |  |  |  | Ashrawan
[5 empty] | 365 | [23 empty] | 11 KV LINE/CART TRACK/CANAL/NALA/PH HT-4.3M
147 |  | 30/1 | DA+0 | 48.15 |  |  | 55949.122 | [7 empty] | 207.432 |  | 692 | 346 | 149 | 166 | 315 | 162 | 165 | 327 | 75°35'28.848"E | 29°16'57.47"N | 557440.278 | 3239444.318 |  |  |  |  | Ashrawan
[5 empty] | 327 | [23 empty] | CART TRACK/PH HT-4.3M
148 |  | 30/2 | DA+0 | 48.15 |  |  | 56276.122 | [7 empty] | 207.138 |  | 710.791 | 355.3955 | 162 | 192 | 354 | 163 | 192 | 355 | 75°35'20.493"E | 29°17'5.167"N | 557213.641 | 3239680.039 |  |  |  |  | Kaliravan
[5 empty] | 383.791 | [23 empty] | NALA
149 | AP31/0 | 31/0 | DD45+0 | 47.97 |  | 1075.791 | 56659.913 | [7 empty] | 206.768 | 39° 21' 6"RT | 725.791 | 362.8955 | 193 | 175 | 368 | 193 | 174 | 367 | 75°35'10.686"E | 29°17'14.198"N | 556947.643 | 3239956.699 |  |  |  |  | Kaliravan
[5 empty] | 342 | [23 empty] | CART TRACK/11 KV LINE
150 |  | 31/1 | DA+0 | 48.15 |  |  | 57001.913 | [7 empty] | 206.714 |  | 730 | 365 | 170 | 193 | 363 | 171 | 194 | 365 | 75°35'9.749"E | 29°17'25.28"N | 556920.675 | 3240297.634 |  |  |  |  | Kaliravan
[5 empty] | 388 | [23 empty] | PH HT-4.3M/CART TRACK
151 |  | 31/2 | DA+0 | 48.15 |  |  | 57389.913 | [7 empty] | 206.834 |  | 796.02 | 398.01 | 195 | 189 | 384 | 195 | 195 | 390 | 75°35'8.687"E | 29°17'37.852"N | 556890.08 | 3240684.426 |  |  |  |  | Kaliravan
[5 empty] | 408.02 | [23 empty] | NALI/BORE/SOLAR/CART TRACK
152 | AP32/0 | 32/0 | DB2+3 | 49.87 |  | 1138.02 | 57797.933 | [7 empty] | 206.392 | 12° 54' 20"LT | 839.055 | 419.5275 | 220 | 216 | 436 | 214 | 216 | 430 | 75°35'7.57"E | 29°17'51.072"N | 556857.906 | 3241091.175 |  |  |  |  | Kaliravan
[5 empty] | 431.035 | [23 empty] | METAL ROAD/LT LINE/11 KV LINE
153 | AP32A/0 | 32A/0 | DB2+3 | 49.87 |  | 431.04 | 58228.968 | [7 empty] | 206.611 | 11° 3' 8"LT | 773.686 | 386.843 | 217 | 191 | 408 | 217 | 184 | 401 | 75°35'2.862"E | 29°18'4.455"N | 556728.826 | 3241502.429 |  |  |  |  | Kaliravan
[5 empty] | 342.651 | [23 empty] | 33 KV LINE/11 KV LINE/SH-10/33 KV LINE
154 | AP32B/0 | 32B/0 | DB2+0 | 46.87 |  | 342.65 | 58571.619 | [7 empty] | 206.842 | 14° 5' 52"RT | 762.651 | 381.3255 | 152 | 193 | 345 | 160 | 199 | 359 | 75°34'56.861"E | 29°18'14.267"N | 556565.445 | 3241803.62 |  |  |  |  | Kaliravan
[5 empty] | 420 | [23 empty] | PLOT
155 |  | 32B/1 | DA+3 | 51.15 |  |  | 58991.619 | [7 empty] | 207.124 |  | 818 | 409 | 227 | 201 | 428 | 222 | 201 | 423 | 75°34'53.07"E | 29°18'27.503"N | 556461.138 | 3242210.462 |  |  |  |  | Kaliravan
[5 empty] | 398 | [23 empty] | METAL ROAD/
156 |  | 32B/2 | DA+3 | 51.15 |  |  | 59389.619 | [7 empty] | 206.867 |  | 814.489 | 407.2445 | 198 | 209 | 407 | 199 | 209 | 408 | 75°34'49.476"E | 29°18'40.045"N | 556362.295 | 3242595.992 |  |  |  |  | Kaliravan
[5 empty] | 416.489 | [23 empty] | NALI/BORE/LT LINE/NALI
157 | AP33/0 | 33/0 | DB1+3 | 49.87 |  | 1234.489 | 59806.108 | [7 empty] | 206.669 | 0° 3' 53"LT | 801.489 | 400.7445 | 208 | 173 | 381 | 208 | 180 | 388 | 75°34'45.716"E | 29°18'53.169"N | 556258.86 | 3242999.433 |  |  |  |  | Kaliravan
[5 empty] | 385 | [23 empty] | LT LINE /11 KV LINE /NALI/PH HT-4M/CART TRACK/BORE/SOLAR/
158 |  | 33/1 | DA+6 | 54.15 |  |  | 60191.108 | [7 empty] | 207.012 |  | 801.149 | 400.5745 | 212 | 243 | 455 | 206 | 232 | 438 | 75°34'42.224"E | 29°19'5.298"N | 556162.824 | 3243372.263 |  |  |  |  | Kaliravan
[5 empty] | 416.149 | [23 empty] | NALI/LT LINE
159 | AP34/0 | 34/0 | DC1+0 | 47.07 |  | 801.149 | 60607.257 | [7 empty] | 206.701 | 19° 48' 6"LT | 803.149 | 401.5745 | 174 | 158 | 332 | 186 | 170 | 356 | 75°34'38.45"E | 29°19'18.408"N | 556059.019 | 3243775.257 |  |  |  |  | Kaliravan
[5 empty] | 387 | [23 empty] | NALI/CART TRACK/SOLAR
160 |  | 34/1 | DA+6 | 54.15 |  |  | 60994.257 | [7 empty] | 206.885 |  | 814.589 | 407.2945 | 230 | 235 | 465 | 218 | 228 | 446 | 75°34'30.434"E | 29°19'28.837"N | 555841.234 | 3244095.161 |  |  |  |  | Kaliravan
[5 empty] | 427.589 | [23 empty] | BORE/33 KV LINE /CART TRACK/CANAL/CART TRACK/CANAL
161 | AP35/0 | 35/0 | DD45+0 | 47.97 |  | 814.589 | 61421.846 | [7 empty] | 208.951 | 32° 10' 18"RT | 825.589 | 412.7945 | 194 | 197 | 391 | 201 | 198 | 399 | 75°34'21.576"E | 29°19'40.359"N | 555600.607 | 3244448.617 |  |  |  |  | khasa Mahajan
[5 empty] | 398 | [23 empty] | 11 KV LINE/CART TRACK/BORE/SOLAR/WELL/SOLAR/BORE/SOLAR
162 |  | 35/1 | DA+1.5 | 49.65 |  |  | 61819.846 | [7 empty] | 207.909 |  | 775 | 387.5 | 201 | 162 | 363 | 201 | 172 | 373 | 75°34'21.114"E | 29°19'53.284"N | 555586.199 | 3244846.356 |  |  |  |  | khasa Mahajan
[5 empty] | 377 | [23 empty] | LT LINE /CART TRACK/11 KV LINE /NALI/BORE
163 |  | 35/2 | DA+6 | 54.15 |  |  | 62196.846 | [7 empty] | 207.686 |  | 750.455 | 375.2275 | 215 | 228 | 443 | 206 | 214 | 420 | 75°34'20.677"E | 29°20'5.527"N | 555572.552 | 3245223.109 |  |  |  |  | khasa Mahajan
[5 empty] | 373.455 | [23 empty] | NALI/11 KV LINE /METAL ROAD/LT LINE/NALI/BORE/SOLAR
164 | AP36/0 | 36/0 | DC1+0 | 47.07 |  | 1148.455 | 62570.301 | [7 empty] | 207.104 | 20° 33' 35"LT | 743.223 | 371.6115 | 146 | 184 | 330 | 161 | 185 | 346 | 75°34'20.243"E | 29°20'17.655"N | 555559.033 | 3245596.319 |  |  |  |  | khasa Mahajan
[5 empty] | 369.768 | [23 empty] | SOLAR/NALI
165 | AP37/0 | 37/0 | DC2+0 | 47.07 |  | 369.77 | 62940.069 | [7 empty] | 207.202 | 27° 50' 36"RT | 752.768 | 376.384 | 186 | 189 | 375 | 186 | 191 | 377 | 75°34'15.028"E | 29°20'28.766"N | 555416.728 | 3245937.607 |  |  |  |  | khasa Mahajan
[5 empty] | 383 | [23 empty] | NALI
166 |  | 37/1 | DA+0 | 48.15 |  |  | 63323.069 | [7 empty] | 207.677 |  | 759.896 | 379.948 | 194 | 189 | 383 | 194 | 189 | 383 | 75°34'16.387"E | 29°20'41.153"N | 555451.499 | 3246319.025 |  |  |  |  | khasa Mahajan
[5 empty] | 376.896 | [23 empty] | NALI
167 | AP38/0 | 38/0 | DB2+0 | 46.87 |  | 759.896 | 63699.965 | [7 empty] | 207.594 | 12° 43' 59"LT | 720.896 | 360.448 | 189 | 176 | 365 | 189 | 175 | 364 | 75°34'17.724"E | 29°20'53.342"N | 555485.715 | 3246694.365 |  |  |  |  | khasa Mahajan
[5 empty] | 344 | [23 empty] | CART TRACK/NALI
168 |  | 38/1 | DA+0 | 48.15 |  |  | 64043.965 | [7 empty] | 207.147 |  | 725.526 | 362.763 | 168 | 192 | 360 | 170 | 192 | 362 | 75°34'16.115"E | 29°21'4.429"N | 555440.67 | 3247035.403 |  |  |  |  | khasa Mahajan
[5 empty] | 381.526 | [23 empty] | NALI/11 KV LINE /CART TRACK
169 | AP39/0 | 39/0 | DB1+0 | 46.87 |  | 725.526 | 64425.491 | [7 empty] | 206.97 | 5° 40' 51"LT | 775.526 | 387.763 | 190 | 186 | 376 | 191 | 190 | 381 | 75°34'14.331"E | 29°21'16.727"N | 555390.711 | 3247413.644 |  |  |  |  | khasa Mahajan
[5 empty] | 394 | [23 empty] | NALI/TEMP.BOUNDARY WALL HT.7M/NALI/CART TRACK/NALI
170 |  | 39/1 | DA+1.5 | 49.65 |  |  | 64819.491 | [7 empty] | 207.511 |  | 793.055 | 396.5275 | 209 | 203 | 412 | 205 | 203 | 408 | 75°34'11.062"E | 29°21'29.203"N | 555300.708 | 3247797.226 |  |  |  |  | khasa Mahajan
[5 empty] | 399.055 | [23 empty] | BORE/NALI/CANAL/CART TRACK
171 | AP40/0 | 40/0 | DB2+0 | 46.87 |  | 793.055 | 65218.546 | [7 empty] | 208.29 | 12°8'51"RT | 802.0546 | 401.0273 | 192 | 185 | 377 | 195 | 191 | 386 | 75°34'7.751"E | 29°21'41.84"N | 555209.55 | 3248185.73 |  |  |  |  | Khara kheri | Fatehabad
[5 empty] | 402.9996 | [23 empty] | Nala, Solar
172 |  | 40/1 | DA+3 | 51.15 |  |  | 65621.5456 | [7 empty] | 207.586 |  | 802.9997 | 401.4999 | 219 | 218 | 437 | 213 | 212 | 425 | 75°34'7.726"E | 29°21'54.934"N | 555202.113 | 3248588.661 |  |  |  |  | Khara kheri
400.0001
173 |  | 40/2 | DA+0 | 48.15 |  |  | 66021.5457 | [7 empty] | 207.5 |  | 760.4865 | 380.2433 | 182 | 184 | 366 | 189 | 184 | 373 | 75°34'7.701"E | 29°22'7.93"N | 555194.732 | 3248988.593 |  |  |  |  | Khara kheri
[5 empty] | 360.4864 | [23 empty] | 11kV line, Nala
174 | AP40A/0 | 40A/0 | DB1+0 | 46.87 |  | 1163.4861 | 66382.0321 | [7 empty] | 207.842 | 3°54'21"LT | 761.9367 | 380.9684 | 180 | 169 | 349 | 181 | 177 | 358 | 75°34'7.679"E | 29°22'19.756"N | 555188.079 | 3249349.018 | WZ-5 start from Excluding AP40A to Fatehabad Gantry |  |  |  | Khara kheri
[5 empty] | 401.4504 | [23 empty] | Cart track, Pump house, Nala
175 |  | 40A/1 | 5DA+6 | 54.72 |  |  | 66783.4825 | [7 empty] | 207.513 | 0°58'20"LT | 812.101 | 406.0505 | 231 | 208 | 439 | 223 | 208 | 431 | 75°34'6.087"E | 29°22'32.645"N | 555153.346 | 3249748.963 |  |  |  |  | Khara kheri
[5 empty] | 410.6506 | [23 empty] | 11kV line, LT line, Metal road, Cart track
176 | AP41/0 | 41/0 | 5DC2+6 | 53.55 |  | 812.101 | 67194.1331 | [7 empty] | 207.5 | 21°23'15"RT | 815.6506 | 407.8253 | 204 | 178 | 382 | 205 | 185 | 390 | 75°34'4.447"E | 29°22'45.916"N | 555110.88 | 3250157.412 |  |  |  |  | Khara kheri
[5 empty] | 405 | [23 empty] | Nala, Cart track, 11kV line
177 |  | 41/1 | 5DA+9 | 57.72 |  |  | 67599.1331 | [7 empty] | 209.385 |  | 778.934 | 389.467 | 228 | 235 | 463 | 221 | 222 | 443 | 75°34'8.521"E | 29°22'58.582"N | 555218.784 | 3250547.773 |  |  |  |  | Khara kheri
[5 empty] | 373.934 | [23 empty] | Nala, Cart track
178 | AP42/0 | 42/0 | 5DD45+0 | 48.45 |  | 778.934 | 67973.0671 | [7 empty] | 208.46 | 42° 21' 48"RT | 619.436 | 309.718 | 140 | 91 | 231 | 153 | 108 | 261 | 75°34'12.282"E | 29°23'10.276"N | 555318.412 | 3250908.191 |  |  |  |  | Khara kheri
[5 empty] | 245.502 | [23 empty] | 11kV lines, Nala, NH-9
179 | AP43/0 | 43/0 | 5DD60+3 | 51.45 |  | 245.5 | 68218.5691 | [7 empty] | 208.519 | 49° 36' 47"LT | 649.483 | 324.7415 | 155 | 208 | 363 | 138 | 207 | 345 | 75°34'20.014"E | 29°23'14.492"N | 555526.189 | 3251038.958 |  |  |  |  | Khara kheri
[5 empty] | 403.981 | [23 empty] | Cart track
180 | AP44/0 | 44/0 | 5DB2+3 | 50.35 |  | 403.98 | 68622.5501 | [7 empty] | 208.307 | 13° 32' 37"LT | 792.981 | 396.4905 | 196 | 182 | 378 | 198 | 186 | 384 | 75°34'22.225"E | 29°23'27.474"N | 555583.823 | 3251438.807 |  |  |  |  | Khara kheri
[5 empty] | 389 | [23 empty] | Nala, Cart track
181 |  | 44/1 | 5DA+3 | 51.72 |  |  | 69011.5501 | [7 empty] | 210.321 |  | 800.536 | 400.268 | 207 | 181 | 388 | 205 | 188 | 393 | 75°34'20.951"E | 29°23'40.063"N | 555547.609 | 3251826.118 |  |  |  |  | Khara kheri
[5 empty] | 411.536 | [23 empty] | Orange garden, Nala, Cart track
182 | AP45/0 | 45/0 | 5DC2+9 | 56.55 |  | 800.536 | 69423.0861 | [7 empty] | 210.45 | 23° 58' 18"LT | 835.257 | 417.6285 | 231 | 212 | 443 | 225 | 212 | 437 | 75°34'19.605"E | 29°23'53.382"N | 555509.298 | 3252235.866 |  |  |  |  | Badopal
[5 empty] | 423.721 | [23 empty] | 11kV line, LT line, Cart track, Brick road, Nala
183 | AP46/0 | 46/0 | 5DD45+9 | 57.45 |  | 423.72 | 69846.8071 | [7 empty] | 209.642 | 32° 12' 39"LT | 824.721 | 412.3605 | 213 | 204 | 417 | 213 | 203 | 416 | 75°34'11.975"E | 29°24'5.419"N | 555301.85 | 3252605.332 |  |  |  |  | Badopal
[5 empty] | 401 | [23 empty] | 11kV lines
184 |  | 46/1 | 5DA+9 | 57.72 |  |  | 70247.8071 | [7 empty] | 209.35 |  | 801.231 | 400.6155 | 198 | 206 | 404 | 199 | 205 | 404 | 75°33'58.931"E | 29°24'11.686"N | 554949.364 | 3252796.524 |  |  |  |  | Badopal
[5 empty] | 400.231 | [23 empty] | Solar panel
185 | AP47/0 | 47/0 | 5DD45+3 | 51.45 |  | 801.231 | 70648.0381 | [7 empty] | 213.748 | 42° 12' 11"RT | 823.231 | 411.6155 | 195 | 205 | 400 | 197 | 207 | 404 | 75°33'45.911"E | 29°24'17.942"N | 554597.554 | 3252987.35 |  |  |  |  | Badopal
[5 empty] | 423 | [23 empty] | Brick road, LT line
186 |  | 47/1 | 5DA+6 | 54.72 |  |  | 71071.0381 | [7 empty] | 212.828 |  | 800 | 400 | 220 | 212 | 432 | 218 | 206 | 424 | 75°33'40.79"E | 29°24'30.933"N | 554457.6 | 3253386.526 |  |  |  |  | Badopal
[5 empty] | 377 | [23 empty] | 11kV line, Brick road, Nala
187 |  | 47/2 | 5DA+6 | 54.72 |  |  | 71448.0381 | [7 empty] | 208.16 |  | 779 | 389.5 | 166 | 202 | 368 | 172 | 202 | 374 | 75°33'36.224"E | 29°24'42.511"N | 554332.865 | 3253742.294 |  |  |  |  | Badopal
[5 empty] | 402 | [23 empty] | LT lines
188 |  | 47/3 | 5DA+6 | 54.72 |  |  | 71850.0381 | [7 empty] | 207.94 |  | 736.932 | 368.466 | 200 | 204 | 404 | 201 | 194 | 395 | 75°33'31.356"E | 29°24'54.857"N | 554199.859 | 3254121.653 |  |  |  |  | Badopal
[5 empty] | 334.932 | [23 empty] | 11kV line, LT line, Cart track, Metal road, Nala
189 | AP48/0 | 48/0 | 5DB2+0 | 47.35 |  | 1536.932 | 72184.9701 | [7 empty] | 208.126 | 7° 6' 24"LT | 709.932 | 354.966 | 131 | 138 | 269 | 142 | 151 | 293 | 75°33'27.3"E | 29°25'5.143"N | 554089.043 | 3254437.721 |  |  |  |  | Badopal
[5 empty] | 375 | [23 empty] | 11kV lines, Cart track, Metal road, Nala
190 |  | 48/1 | 5DA+9 | 57.72 |  |  | 72559.9701 | [7 empty] | 208.897 |  | 777 | 388.5 | 237 | 200 | 437 | 225 | 201 | 426 | 75°33'21.166"E | 29°25'16.08"N | 553922.143 | 3254773.532 |  |  |  |  | Badopal
402
191 |  | 48/2 | 5DA+9 | 57.72 |  |  | 72961.9701 | [7 empty] | 209.134 |  | 840.46 | 420.23 | 202 | 220 | 422 | 203 | 220 | 423 | 75°33'14.59"E | 29°25'27.803"N | 553743.225 | 3255133.522 |  |  |  |  | Badopal
[5 empty] | 438.46 | [23 empty] | 11kV lines, LT lines, Metal road, Brick road
192 | AP49/0 | 49/0 | 5DC2+9 | 56.55 |  | 1215.46 | 73400.4301 | [7 empty] | 209.64 | 25° 28' 34"LT | 814.46 | 407.23 | 220 | 213 | 433 | 220 | 206 | 426 | 75°33'7.417"E | 29°25'40.59"N | 553548.081 | 3255526.162 |  |  |  |  | Badopal
[5 empty] | 376 | [23 empty] | 11kV line, LT line, Solar panel
193 |  | 49/1 | 5DA+3 | 51.72 |  |  | 73776.4301 | [7 empty] | 210.28 |  | 779 | 389.5 | 163 | 174 | 337 | 171 | 183 | 354 | 75°32'56.475"E | 29°25'48.173"N | 553252.178 | 3255758.148 |  |  |  |  | Badopal
[5 empty] | 403 | [23 empty] | Cart track, Canal, Nala, 11kV line, Brick road
194 |  | 49/2 | 5DA+9 | 57.72 |  |  | 74179.4301 | [7 empty] | 209.943 |  | 750.805 | 375.4025 | 229 | 210 | 439 | 221 | 199 | 420 | 75°32'44.748"E | 29°25'56.3"N | 552935.027 | 3256006.793 |  |  |  |  | Badopal
[5 empty] | 347.805 | [23 empty] | Pump house, 11kV lines, Metal road,
195 | AP50/0 | 50/0 | 5DD45+3 | 51.45 |  | 1126.805 | 74527.2351 | [7 empty] | 209.21 | 25° 43' 31"RT | 773.846 | 386.923 | 139 | 193 | 332 | 150 | 198 | 348 | 75°32'34.626"E | 29°26'3.313"N | 552661.313 | 3256221.383 |  |  |  |  | Badopal
[5 empty] | 426.041 | [23 empty] | Brick road, Cart track, LT line
196 | AP50A/0 | 50A/0 | 5DB1+9 | 56.35 |  | 426.04 | 74953.2761 | [7 empty] | 209.53 | 4° 54' 4"RT | 770 | 385 | 234 | 220 | 454 | 230 | 207 | 437 | 75°32'27.716"E | 29°26'15.764"N | 552473.358 | 3256603.723 |  |  |  |  | Badopal
[5 empty] | 343.959 | [23 empty] | Cart track
197 |  | 50A/1 | 5DA+0 | 48.72 |  |  | 75297.2351 | [7 empty] | 209.21 |  | 753.95 | 376.975 | 124 | 123 | 247 | 139 | 147 | 286 | 75°32'23.138"E | 29°26'26.196"N | 552348.542 | 3256924.236 |  |  |  |  | Badopal
[5 empty] | 409.991 | [23 empty] | Brick road, Cart track, Nala
198 | AP51/0 | 51/0 | 5DD45+18 | 66.45 |  | 753.95 | 75707.2261 | [7 empty] | 208.49 | 34° 27' 52"RT | 600.388 | 300.194 | 289 | 211 | 500 | 265 | 140 | 405 | 75°32'17.681"E | 29°26'38.631"N | 552199.765 | 3257306.281 |  |  |  |  | Badopal
[5 empty] | 190.397 | [23 empty] | 220kV OHTL, 11kV line
199 | AP52/0 | 52/0 | 5DD45+9 | 57.45 |  | 190.4 | 75897.6231 |  |  |  |  | 1 |  |  | 208.616 | 35° 52' 18"LT | 430.397 | 215.1985 | -20 | 133 | 113 | 51 | 128 | 179 | 75°32'19.325"E | 29°26'44.647"N | 552243.201 | 3257491.657 | RC=1M |  |  |  | Badopal
240
200 |  | 52/1 | 5DA+9 | 57.72 |  |  | 76137.6231 | [7 empty] | 208.662 |  | 618.145 | 309.0725 | 107 | 131 | 238 | 112 | 154 | 266 | 75°32'15.928"E | 29°26'51.856"N | 552150.643 | 3257713.091 |  |  |  |  | Badopal
378.145
201 | AP53/0 | 53/0 | 5DD45+18 | 66.45 |  | 618.145 | 76515.7681 | [7 empty] | 208.905 | 36° 48' 6"RT | 663.477 | 331.7385 | 248 | 220 | 468 | 225 | 185 | 410 | 75°32'10.574"E | 29°27'3.213"N | 552004.809 | 3258061.984 |  |  |  |  | Dhangar
[5 empty] | 285.332 | [23 empty] | 132 KV DC TL HVPNL
202 | AP54/0 | 54/0 | 5DD60+9 | 57.45 |  | 285.33 | 76801.1001 | [7 empty] | 208.772 | 42° 25' 37"LT | 685.332 | 342.666 | 65 | 214 | 279 | 101 | 210 | 311 | 75°32'13.204"E | 29°27'12.193"N | 552074.403 | 3258338.699 |  |  |  |  | Dhangar
[5 empty] | 400 | [23 empty] | LT line
203 |  | 54/1 | 5DA+6 | 54.72 |  |  | 77201.1001 | [7 empty] | 209.317 |  | 800 | 400 | 186 | 214 | 400 | 191 | 210 | 401 | 75°32'6.223"E | 29°27'23.663"N | 551884.708 | 3258690.858 |  |  |  |  | Dhangar
[5 empty] | 400 | [23 empty] | Brick road, Cart track
204 |  | 54/2 | 5DA+3 | 51.72 |  |  | 77601.1001 | [7 empty] | 209.502 |  | 707.494 | 353.747 | 187 | 143 | 330 | 191 | 147 | 338 | 75°31'59.24"E | 29°27'35.133"N | 551695.012 | 3259043.016 |  |  |  |  | Dhangar
[5 empty] | 307.494 | [23 empty] | 33kV line, Solar Panel
205 | AP55/0 | 55/0 | 5DB2+6 | 53.35 |  | 1107.494 | 77908.5941 | [7 empty] | 208.906 | 13° 49' 25"RT | 652.495 | 326.2475 | 165 | 229 | 394 | 162 | 206 | 368 | 75°31'53.872"E | 29°27'43.95"N | 551549.187 | 3259313.733 |  |  |  |  | Dhangar
[5 empty] | 345.001 | [23 empty] | Solar panel, Cart track, 11kV line
206 |  | 55/1 | 5DA-3 | 45.72 |  |  | 78253.5951 | [7 empty] | 208.871 |  | 605.001 | 302.5005 | 117 | 127 | 244 | 140 | 129 | 269 | 75°31'50.725"E | 29°27'54.815"N | 551462.886 | 3259647.766 |  |  |  |  | Dhangar
[5 empty] | 260 | [23 empty] | Metal road, 11kV line
207 |  | 55/2 | 5DA-3 | 45.72 |  |  | 78513.5951 | [7 empty] | 209.184 |  | 587.263 | 293.6315 | 133 | 160 | 293 | 132 | 162 | 294 | 75°31'48.353"E | 29°28'3.004"N | 551397.847 | 3259899.5 |  |  |  |  | Dhangar
[5 empty] | 327.263 | [23 empty] | Brick road
208 | AP56/0 | 56/0 | 5DD45-3 | 45.45 |  | 932.264 | 78840.8581 | [7 empty] | 209.247 | 31° 29' 44"LT | 593.263 | 296.6315 | 167 | 108 | 275 | 166 | 121 | 287 | 75°31'45.367"E | 29°28'13.311"N | 551315.983 | 3260216.358 |  |  |  |  | Dhangar
[5 empty] | 266 | [23 empty] | 11kV line, Cart track
209 |  | 56/1 | 5DA+0 | 48.72 |  |  | 79106.8581 | [7 empty] | 209.273 |  | 498.295 | 249.1475 | 158 | 145 | 303 | 145 | 130 | 275 | 75°31'38.296"E | 29°28'19.344"N | 551124.698 | 3260401.198 |  |  |  |  | Dhangar
232.295
210 | AP57/0 | 57/0 | 5DB2-1.5 | 45.85 |  | 498.295 | 79339.1531 | [7 empty] | 208.831 | 8° 56' 5"RT | 583.991 | 291.9955 | 87 | 149 | 236 | 102 | 159 | 261 | 75°31'32.12"E | 29°28'24.613"N | 550957.65 | 3260562.617 |  |  |  |  | Dhangar
[5 empty] | 351.696 | [23 empty] | Metal road, LT line, Cart track
211 | AP58/0 | 58/0 | 5DC2+3 | 50.55 |  | 351.7 | 79690.8491 | [7 empty] | 208.554 | 23° 14' 37"LT | 751.111 | 375.5555 | 203 | 202 | 405 | 194 | 201 | 395 | 75°31'24.3"E | 29°28'33.764"N | 550745.764 | 3260843.321 |  |  |  |  | Dhangar
[5 empty] | 399.415 | [23 empty] | 11kV line, LT line, Cart track
212 | AP59/0 | 59/0 | 5DB2+3 | 50.35 |  | 399.42 | 80090.2641 | [7 empty] | 208.441 | 12° 28' 21"RT | 769.415 | 384.7075 | 199 | 151 | 350 | 199 | 160 | 359 | 75°31'11.451"E | 29°28'40.246"N | 550398.853 | 3261041.273 |  |  |  |  | Dhangar
[5 empty] | 370 | [23 empty] | Metal road, LT line, Cart track
213 |  | 59/1 | 5DA+9 | 57.72 |  |  | 80460.2641 | [7 empty] | 208.888 |  | 801.59 | 400.795 | 220 | 240 | 460 | 211 | 234 | 445 | 75°31'1.312"E | 29°28'48.358"N | 550124.678 | 3261289.724 |  |  |  |  | Dhangar
431.59
214 | AP60/0 | 60/0 | 5DD45+3 | 51.45 |  | 801.59 | 80891.8541 | [7 empty] | 208.851 | 34° 7' 17"LT | 681.59 | 340.795 | 193 | 129 | 322 | 199 | 127 | 326 | 75°30'49.484"E | 29°28'57.82"N | 549804.864 | 3261579.533 |  |  |  |  | Dhangar
[5 empty] | 250 | [23 empty] | Metal road, LT line, Cart track
215 |  | 60/1 | 5DA+3 | 51.72 |  |  | 81141.8541 | [7 empty] | 208.818 |  | 551.869 | 275.9345 | 121 | 121 | 242 | 123 | 135 | 258 | 75°30'40.298"E | 29°28'58.994"N | 549557.334 | 3261614.589 |  |  |  |  | Dhangar
[5 empty] | 301.869 | [23 empty] | 11kV lines
216 | AP61/0 | 61/0 | 5DC1+6 | 53.55 |  | 551.869 | 81443.7231 | [7 empty] | 210.035 | 18° 7' 21"RT | 699.342 | 349.671 | 181 | 201 | 382 | 167 | 200 | 367 | 75°30'29.206"E | 29°29'0.412"N | 549258.448 | 3261656.919 |  |  |  |  | Dhangar
[5 empty] | 397.473 | [23 empty] | 11kV line, Cart track, Canal
217 |  | 61/1 | 5DA+6 | 54.72 |  |  | 81841.1961 | [7 empty] | 209.251 |  | 623.419 | 311.7095 | 197 | 209 | 406 | 198 | 173 | 371 | 75°30'15.989"E | 29°29'6.16"N | 548901.761 | 3261832.302 |  |  |  |  | (Matana)Basti Bhawan
225.946
218 | AP61A/0 | 61A/0 | 5DB1-3 | 44.35 |  | 623.419 | 82067.1421 | [7 empty] | 209.25 | 6° 35' 19"RT | 469.805 | 234.9025 | 17 | 48 | 65 | 53 | 87 | 140 | 75°30'8.476"E | 29°29'9.428"N | 548699 | 3261932 |  |  |  |  | (Matana)Basti Bhawan
243.859
219 | AP62/0 | 62/0 | 5DD45+3 | 51.45 |  | 243.86 | 82311.0011 | [7 empty] | 209.16 | 35° 25' 24"LT | 491.589 | 245.7945 | 196 | 164 | 360 | 157 | 143 | 300 | 75°30'0.883"E | 29°29'13.745"N | 548493.955 | 3262064 |  |  |  |  | (Matana)Basti Bhawan
[5 empty] | 247.73 | [23 empty] | NH-9, 11kV line
220 | AP63/0 | 63/0 | 5DC2+0 | 47.55 |  | 247.73 | 82558.7311 | [7 empty] | 209.13 | 28° 15' 16"LT | 389.727 | 194.8635 | 83 | 37 | 120 | 104 | 61 | 165 | 75°29'51.691"E | 29°29'13.408"N | 548246.49 | 3262052.54 |  |  |  |  | (Matana)Basti Bhawan
[5 empty] | 141.997 | [23 empty] | Cart track, Canal, LT line
221 | AP64/0 | 64/0 | 5DD60+0 | 48.45 |  | 142 | 82700.7281 | [7 empty] | 209.846 | 14° 25' 59"LT | 242.472 | 121.236 | 105 | 204 | 309 | 81 | 140 | 221 | 75°29'47.155"E | 29°29'11.055"N | 548124.655 | 3261979.606 |  |  |  |  | (Matana)Basti Bhawan
[5 empty] | 100.475 | [23 empty] | LT line, SS gantry
222 |  | FATEHABAD GANTRY | Gantry | 22.8 |  | 100.48 | 82801.2031 | [7 empty] | 210.528 |  | 183.2762 | 91.6381 | -101 | 0 | -101 | -37 | 0 | -37 | 75°29'44.521"E | 29°29'8.743"N | 548054.03 | 3261908.14 | [6 empty] | No count
|  |  |  | Length= | 82.8012 | KM
For KEC International Ltd | [18 empty] | M/s, Powergrid Bikaner IV Transmission Limited
Surveyed By |  |  |  | Checked By | [7 empty] | Submitted By |  |  | Submitted By |  |  |  | Checked By | [5 empty] | Recommended By |  |  |  | Approved By
| TOWER QUENTATY WZ-4 |  |  |  | TOWER QUENTATY WZ-5
| TOWER TYPE |  | QUENTATY |  | TOWER TYPE | [9 empty] | QUENTATY
| DA-3 | ₌ | 8 |  | 5DA-3 |  | ₌ | [7 empty] | 2
| DA-1.5 | ₌ | 3 |  | 5DA+0 |  | ₌ | [7 empty] | 2
| DA+0 | ₌ | 52 |  | 5DA+3 |  | ₌ | [7 empty] | 4
| DA+1.5 | ₌ | 4 |  | 5DA+6 |  | ₌ | [7 empty] | 6
| DA+3 | ₌ | 27 |  | 5DA+9 |  | ₌ | [7 empty] | 7
| DA+6 | ₌ | 22 |  | 5DB1-3 |  | ₌ | [7 empty] | 1
| DA+9 | ₌ | 8 |  | 5DB1+9 |  | ₌ | [7 empty] | 1
| DB1+0 | ₌ | 5 |  | 5DB2-1.5 |  | ₌ | [7 empty] | 1
| DB1+3 | ₌ | 1 |  | 5DB2+0 |  | ₌ | [7 empty] | 1
| DB1+9 |  | 0 |  | 5DB2+3 |  | ₌ | [7 empty] | 2
| DB2+0 | ₌ | 10 |  | 5DB2+6 |  | ₌ | [7 empty] | 1
| DB2+3 | ₌ | 3 |  | 5DC1+6 |  | ₌ | [7 empty] | 1
| DB2+18 | ₌ | 1 |  | 5DC2+0 |  | ₌ | [7 empty] | 1
| DC1-3 | ₌ | 1 |  | 5DC2+3 |  | ₌ | [7 empty] | 1
| DC1+0 | ₌ | 6 |  | 5DC2+6 |  | ₌ | [7 empty] | 1
| DC1+3 | ₌ | 1 |  | 5DC2+9 |  | ₌ | [7 empty] | 2
| DC1+6 | ₌ | 1 |  | 5DD45+0 |  | ₌ | [7 empty] | 1
| DC2+0 | ₌ | 6 |  | 5DD45+3 |  | ₌ | [7 empty] | 5
| DC2+3 | ₌ | 3 |  | 5DD45+9 |  | ₌ | [7 empty] | 2
| DD45+0 | ₌ | 3 |  | 5DD45+18 |  | ₌ | [7 empty] | 2
| DD60+0 |  | 2 |  | 5DD60+0 |  | ₌ | [7 empty] | 1
| DD602+3 |  | 1 |  | 5DD60+3 |  | ₌ | [7 empty] | 1
| DD60+6 | ₌ | 4 |  | 5DD60+9 |  | ₌ | [7 empty] | 1
| DD60+9 | ₌ | 1 |  | TOTAL |  | ₌ | [7 empty] | 47
| TOTAL | ₌ | 173
| Tower Type |  | Tower Qty
| DA TYPE |  | 145
| DB1 TYPE |  | 8
| DB2 TYPE |  | 19
| DC1 TYPE |  | 10
| DC2 TYPE |  | 14
| DD45 TYPE |  | 13
| DD60 TYPE |  | 11
| Total |  | 220
NOTE: - SIWANI GANTRY AND FATEHABAD GANTRY NOT INCLUDED THIS TOWER QTY.

## Forest (hidden)
Sl.No | Activity |  |  | Line | Total Nos | Proposal Submitted | Approval/NOC Obtained | Remarks
1 | POWERLINE CROSSINGS |  |  | Siwani-Fatehabad TL | 4
|  |  |  | Siwani-Patran TL | 21
2 | NATIONAL HIGHWAY CROSSINGS |  |  | Siwani-Fatehabad TL | 3
|  |  |  | Siwani-Patran TL | 3
3 | RAILWAY CROSSING |  |  | Siwani-Fatehabad TL | 2
|  |  |  | Siwani-Patran TL | 4
4 | OIL Pipeline |  |  | Siwani-Fatehabad TL | 0
|  |  |  | Siwani-Patran TL | 2
4 | FOREST CLEARANCE |  |  | Siwani-Fatehabad TL | 8.312
|  |  |  | Siwani-Patran TL | 13.119
Total |  |  |  |  | 39 | 0 | 0
Line Description | State | District | Total Forest(Ha) | Forest(Ha) | Status As on Dated
KEC/TA-513/PGCIL/029 Dated 20.03.2025
Siwani To Fatehabad | Haryana | Bhiwani | 8.312
|  | Hisar |  | 3.363
|  | Fatehabad |  | 4.949
Siwani To Patran | Haryana | Jind | 13.119 | 0.324
|  | Hisar |  | 6.221
|  | Fatehabad |  | 4.346
|  | Bhiwani |  | 2.228
Siwani To Fatehabad TL | State | District | Section | Wind - Zone | Length | PL Xing | NH Xing | Railway Xng | SH | Forest visit done on dated-17.06.2025
| Haryana | Bhiwani | Gantry to AP-7 | 4 | 21.1581 | 1 | 1 | 1
|  | Hisar | AP-7 to AP-38 | 4 | 42.7098 | 1 |  | 1 | 1
|  | Fatehabad | AP38-AP41 | 4 | 3.4954
|  | Fatehabad | AP 41 to AP-64/Gantry | 5 | 15.6071 | 2 | 2
|  | Total |  |  | 82.9704
[6 empty] | 4 | 3 | 2 | 1
Siwani To Patran | State | District | Section | Wind - Zone | Length | PL Xing | NH Xing | Railway Xng | SH
| Haryana | Bhiwani | Gantry To AP12 | 4 | 23.428 | 1 | 1 | 1 | 1
|  | Hisar | AP12 To AP35 | 4 | 34.687 |  | 1 | 1 | 1
|  | Hisar | AP35 To AP62 | 5 | 32.2688 | 8 |  |  | 3
|  | Fatehabad | AP62 To AP87 | 5 | 23.8188 | 5 |  | 1 | 1
|  | Jind | AP87 To AP92 | 5 | 1.5897 | 2 |  | 1 | 1
| Punjab | Sanrur | AP92 To AP121,Gantry | 5 | 31.8919 | 6 | 2
[5 empty] | 147.6843 | 22 | 4 | 4 | 7