## Completion Plan (hidden)
Construction Plan-TA-602
PARTICULARS |  | Unit | Final | Till 30 June’26 | Bal | June |  |  | Jun’26 | July'26 | Aug'26 | Sept'26 | Oct'26 | Nov'26 | Dec'26 | Jan'27 | Feb'27 | Mar'27 | Apri'27 | Q2-27 | Q3-27 | Q4-27 | Q1-28 | Q2-28 | Remarks
|  |  | Qty |  | 1st July | Plan | Act | WIP
TOWER Fdn | Fdn | Nos | 494 | 169 | 325 | 30 | 15 | 0 |  | 20 | 40 | 40 | 40 | 40 | 33 | 33 | 30 | 34 | [6 empty] | 494
| Gangs | Nos |  |  |  | 6 | 6 | - |  | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
TOWER ERECTION | Location | Nos | 494 | 73 | 421 | 40 | 8 | 3 |  | 25 | 35 | 40 | 40 | 40 | 40 | 40 | 35 | 35 | 35 | 48 |  |  |  |  | 494
| Volume | MT
| Gang | No |  | 2 |  | 8 | 4 | 4 |  | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 8 | 10
STRINGING | Stringing - P/O | KMs | 186 | - | - | - | - | - | - | - | - | - |  | 5 | 12 | 18 | 18 | 18 | 20 | 20 | 20 | 20 | 18 | 17 | 186
| Stringing F/S | Kms | 186 | - | - | - | - | - | - | - | - | - |  | 5 | 12 | 18 | 18 | 18 | 20 | 20 | 20 | 20 | 18 | 17 | 186
| Gang | No |  | - | - | - | - | - | - | - | - | - |  | 2 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
OPGW | Stringing | KMs | 186 | - | - | - | - | - | - | - | - | - |  | 5 | 12 | 18 | 18 | 18 | 20 | 20 | 20 | 20 | 18 | 17 | 186
| Gang | No |  | - | - | - | - | - | - | - | - | - |  | 2 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5

## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manager | Section Incharge | Employee Name | Designation
TA-602 | Name of Line: Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line | Powergrid West Central Transmission Ltd. | 2025-05-13 | 2028-11-12 | Mr. Rishi Shukla | Mr Arun Felbin R | Mr. Vijay Govindrao Kute | Mr. Minarul Alam | Mr. Ajaya Kumar | Mr. Vishnu R Nair | Sr. Engineer
[10 empty] | Mr. Tapash Das | Sr. Surveyour
[10 empty] | Mr. Rakesh Debnath | Survey Officer
[10 empty] | Mr. Monnesh C.K. | Syrvey Assist.
[10 empty] | Mr. Deep kumar Das | Sr. Supervisor
[10 empty] | Mr. Soumen Khan | Survey Officer
[10 empty] | Mr. Khokan Mandal | Assit. Surveyour
[9 empty] | Mr. Tanmay Nayak | Mr. Madhu Saran Prashad | Supervisor
[10 empty] | Jaynta Ghosh | Supervisor
[10 empty] | Uttam das | Supervisor
[10 empty] | Md. Wahiddujaman Biswash | Officer Project
[10 empty] | Mijanur Rahaman | Officer Project
[10 empty] | Saddam Hossain | Officer Project
[10 empty] | Sanjit Singh | Erection Supervisor
[10 empty] | Hulash mahato | Erection Supervisor
[10 empty] | Bhim mahato | Erection Supervisor
[10 empty] | M Ganesan | Assistant Officer - project

## PGCIL - KEC
TA-602 KEC INTERNATIONAL LIMITED | [11 empty] | 2026-06-27
Powergrid West Central Transmission Ltd.
Name of Line: Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line
NOA No.: CC/T/W-TW/DOM/A06/24/04774/NOA-2/25-105721/01&02 Dt:13-05-2025
Sr No. | Activity | Estimated Quantity | Cumm. Progress up to till last Month (May'26) | Target as per L2 Schedule Cummulative (upto May'26) | L3 Plan for the month (May'26 ) | Today's Progress | Progress in this month | Cumm. Progress till date | Cumm. Balance | WIP | No of Gangs | Remark
1 | Route Alignment (Km) | 185.149 | 185.149 | 185.149 | 0 |  |  | 185.149 | 0
2 | Detailed Survey (Km) | 184.986 | 178.3635 | 184.986 | 6.6225 |  | 11.83 | 178.3635 | 6.6225
3 | Profiling (Km) | 184.986 | 184.986 | 184.986 | 0 |  |  | 184.986 | 0
4 | Check Survey (Km) | 184.986 | 136.139 | 184.986 | 48.847 |  | 30.3921 | 166.5311 | 18.4549
5 | Soil Investigation (Nos.) | 31 | 17 |  |  |  |  | 17 | 14
6 | Excavation | 480 | 154 | 167 | 30 |  | 12 | 166 | 314 | 2
7 | Foundation (Nos.) | 480 | 154 | 167 | 30 |  | 11 | 165 | 315 | 4 | 3 | ROW"67/3"(10/06/2026)
8 | Earthing (Nos.) | 480 | 96 | 167 | 30 |  | 10 | 106 | 374
9 | Tower Erection (Nos) | 480 | 52 | 102 | 35 |  | 25 | 77 | 403 | 3 | 4
10 | Tack Welding | 480 | 0 | 102 | 35 |  | 0 | 0 | 480 | 0 | 0
11 | Stringing (Km) | 184.986 | 0 | 10 | 0 |  | 0 | 0 | 184.986 | 0 | 0
a) | Paying Out | 184.986 | 0 | 10 | 0 |  | 0 | 0 | 184.986
b) | Final Sag | 184.986 | 0 | 10 | 0 |  | 0 | 0 | 184.986
12 | OPGW (Km) | 184.986 | 0 | 0 | 0 |  |  | 0 | 184.986

## PPT-Erection Part (hidden)
LOA DT -13-May-2026 Completion Schedule 12-Nov-2028 Project Value-613.31Cr
Sl No | PARTICULARS |  | Unit | Total | Comp Till 31-May’26 | Balance Till 01-Jun’26 | June’26 |  |  | July’26 | Aug’26 | Support / Issue
|  |  |  | Qty |  |  | Plan | Actual | WIP | Plan | Plan
1 | Survey | Details | KMs | 185.149 | 166.531 | 18.455 | 18.455 |  | 8.123 | - | -
|  | Check | Kms | 185.149 | 136.139 | 48.847 | 48.847 |  | 30.392
2 | FOUNDATION | Location | Nos | 480 | 154 | 326 | 30 | 4 | 5 | 20 | 40
|  | Gang | No |  |  |  | 6 | 5 | 5 | 5 | 6
|  | Earthing | No | 480 | 96 | 384 | 40 | 4 | - | 20 | 30
3 | TOWER ERECTION | Location | Nos | 480 | 52 | 428 | 35 | 4 | 5 | 25 | 35
|  | Volume | MT | 13208 | 1321 | 11887 | 840 | 104 | 120 | 625 | 840
|  | Gang | No |  |  |  | 5 | 5 | 5 | 5 | 5
|  | Tack Welding | No | 480 |  | 480
4 | STRINGING | Stringing - P/O | KMs | 185.1 |  | 185.1
|  | Stringing Final Sag | Kms | 185.1 |  | 185.1
|  | TSE - Section | No | 166.083 |  | 166.083
|  | Manual - Section | No | 19.017 |  | 19.017
|  | Gang | No
5 | OPGW | Stringing | KMs | 185.1 |  | 185.1
| STRINGING | Gang | No
6 | Revenue |  | CR. | 100.47 | 10 | 10

## CMD-1 (hidden)
Activity | UoM | As Per LOA (Qty) | Revised | As per L2 | Completed | Balance | Front Availability |  | Gangs Available |  | Plan |  |  | Plan | Plan | Remarks
|  |  | (Qty) | (June'26) | (as on 30.06.26) | (Up to 01.06.26) |  |  |  |  | 2026-07-01 |  |  | 2026-07-01 | 2026-08-01
[11 empty] | Plan |  | Act
Check Survey | Km | 186 | 185 | 185 | 178.36 | 6.64 | - |  | - |  | 48.85 |  | 42.22 | 6.622 | - | Narmada River Approval WIP(6.622 Kms)
Foundation | No | 494 | 480 | 177 | 169 | 311 | 1 |  | 3 |  | 35 |  | 15 | 20 | 30
Erection | No | 494 | 480 | 112 | 77 | 403 | 7 |  | 4 |  | 40 |  | 25 | 25 | 35
Stringing | Km | 186 | 185 | 15 | - | 185 | - |  | - |  | - |  | - | - | - | -
OPGW Stringing | Km | 186 | 185 | - | - | - | - |  | - |  | - |  | - | - | - | L2 Schedule from Oct’26
Supply Status:
Item | UoM | As Per LOA (Qty) | Revised | As per L2 | Actual Supplied | Balance | Plan for June'26 | Plan for July'26 |  | Plan for Aug'26 |  | Remarks
|  |  | (Qty) | (July'26)
Stub | Nos | 494 | 480 | 410 | 282 | 198 | 77
Tower | Nos | 494 | 480 | 330 | 193 | 287 | 45 | 48
Conductor | Km | 3030 | 3030 | 2121 | 1209.512 | 1820.488 | 70 |  |  | 500
Earthwire | Km | 192 | 192 | 135 | 77 | 115 |  |  |  | 60
160KN CLR | Nos | 1202 | 1202 | 842 | - | 1202 | - | - |  | - |  | Insulator being delayed due to delay in Design/Type Testing Stage Cat-II
210KN CLR | Nos | 1438 | 1438 | 1006 | - | 1438 | - | - |  | - |  | Insulator being delayed due to delay in Design/Type Testing Stage Cat-II
410 KN CLR | Nos | 10142 | 10142 | 7100 | - | 10142 | [5 empty] | Insulator being delayed due to delay in Design/Type Testing Stage Cat-II
HW Fittings | % | 100 | 100 | 70 | - | 100
Front Availability Status
Activity | UoM | Mar’26 |  |  | April’26 |  |  | May’26
|  | Front | Completed | Gang | Front | Completed | Gang | Front | Completed | Gang
Foundation | No | 10 | 5 | 3 | 25 | 22 | 2 | 25 | 22 | 4
Tower Erection | No | 15 | 12 | 2 | 12 | 8 | 2 | 20 | 18 | 4
Stringing | Km | - | - | - | - | - | - | - | - | -

## CMD-2 (hidden)
No. of month from NOA |  | UoM | Qty. | Upto June-26 | July-26 | 2026-08-01 | 2026-09-01 | Oct-26 | 2026-11-01 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-28 | May-28 | June-27
Activity
Foundation | As per L2 | Nos | 494 | 177 | 5 | 5 | 5 | 15 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 10
| Completion Plan | Nos | 494 | 184 | 25 | 25 | 40 | 40 | 40 | 40 | 36 | 36 | 28
| Front Required from POWERGRID | Nos | 494 | 184 | 22 | 25 | 40 | 40 | 40 | 40 | 36 | 36 | 28
| Gangs Planned | Nos |  |  | 6 | 8 | 8 | 8 | 8 | 10 | 10 | 10 | 10
| Stubs Supply as per L2 | Nos | 515 | 290 | 120 |  |  | 105
| Stub Supply Actual | Nos | 515 | 282
Erection | As per L2 | Nos | 494 | 77 | 8 | 8 | 8 | 15 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 10
| Completion Plan | Nos | 494 | 77 | 25 | 35 | 36 | 40 | 40 | 40 | 40 | 35 | 35 | 35 | 30 | 18
| Front Required from POWERGRID | Nos | 494 | 77 | 25 | 35 | 36 | 40 | 40 | 40 | 40 | 35 | 35 | 35 | 30 | 18
| Gangs Planned | Nos |  |  | 6 | 8 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 8
| Tower Supply as per L2 | Nos | 515 | 230 | 100 |  |  |  | 100 |  |  |  | 85
| Tower Supply Actual | Nos | 515 | 192
Stringing | As per L2 | Kms | 186.3 | 15 | 1 | 1 | 1 | 6 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10
| Completion Plan | Kms | 186.3 | [7 empty] | 5 | 12 | 18 | 18 | 18 | 5
| Front Required from POWERGRID | Kms | 186.3 | [7 empty] | 5 | 12 | 18 | 18 | 18 | 5
| Gangs Planned | TSE (Nos) | 186.3 | [7 empty] | 5 | 12 | 18 | 18 | 18 | 5
Manual (Nos)
| Conductor Supply as per L2 | Nos | 3030 | 1212 | 909 |  |  |  |  | 606
| Conductor Supply Actual | Nos | 3030 | 1209.519
| Insulator Supply as per L2 | Nos | 12782 | 5113 | 3835 |  |  |  |  | 2556
| Insulator Supply Actual | Nos | 12782 | - | - | - | - | - | - | - | - | - | - | - | - | -
| Hardware Supply as per L2 | % | 100% | 40% | 30% |  |  | 30% |  | 20%
| Hardware Supply Actual | % | 100% | - | - | - | - | - | - | - | - | - | - | - | - | -

## PPT _Statutory (hidden)
Statuary Clearances :
Sl No | Name Statuary Clearances | Total | Submitted | Approved | Balance to Submit | Balance to Approve | Status of submitted Proposals
1 | Railway X-ing | 2 | 0 | 0 | 2 | 2 | • AP50–AP51: Foundation drawing awaited (D60+6, D60+9) • 111A–111B: Railway crossing – details awaited
2 | Powerline X-ing | 12 | 12 | 0 | 0 | 12 | 11 No's Location Site Visit done.
3 | NH X-ing | 4 | 4 | 0 | 0 | 4 | Two No's Site Visit Done( AP 118 to AP119 & AP133 to AP34).
4 | River X-ing | 1 | 1 | 0 | 1 | 0 | Awaitiing/Dependency @ Approval of Detail Survey & Soil Investigation Testing Underprocess.
5 | Civil Aviation Proposal | 1 | 0 | 0 | 1 | 1 | Under Process
6 | Defence Aviation | 1 | 0 | 0 | 1 | 1 | Under Process
7 | PTCC Proposal | 1 | 0 | 0 | 1 | 1
8 | Pipe line X-ings | 1 | 1 | 0 | 0 | 1

## PPT Supply (hidden)
Supply & BOI Details
SL No. | Type of Tower | UOM | BOQ Qty | Final line Qty (Amended) | Received as on dated | Balance to be supply | Remark
1 | Stubs | Nos | 494 | U/P | 282 | 212
2 | Towers | Nos | 494 | U/P | 193 | 301
3 | Conductor | Km | 3030.64 | U/P | 1209.519 | 1821.121
4 | Insulators | Nos | 12782 | U/P | 0 | 12782
5 | Earthwire | Km | 192.165 | U/P | 77 | 115.165
6 | HW for Cond & EW | % | 100 | U/P | 0% | 100 | 25% Material under dispatch
7 | OPGW Cable | Km | 199 | U/P | 0 | 199
8 | OPGW Accessories | % | 100 | U/P | 0 | 100

## Supply Status (hidden)
Supply & BOI Details
SL No. | Type of Tower | UOM | BOQ Qty | DSL | PRS Released | Balance to Release | Remark's
1 | Stubs | Nos | 494 | 410 | 351 | 59 | DSL UPTO-July
2 | Towers | Nos | 494 | 330 | 286 | 44 | DSL UPTO-July
3 | Conductor | Km | 3030.64 | 2121 | 2200 | -79 | DSL UPTO-July
4 | Insulators | Nos | 12782 | 8948 | 8948 | 0 | DSL UPTO-July
5 | Earthwire | Km | 192.165 | 135 | 188 | -53 | DSL UPTO-July
6 | HW for Cond & EW | % | 100 | 25% | 70% | -45% | DSL UPTO-July
7 | OPGW Cable | Km | 199 | 100 | 0 | 100 | DSL UPTO-July
8 | OPGW Accessories | % | 100 | 50% | 70% | -20% | DSL UPTO-June

## 800kV HVDC TA-602
| Project Code | TA-602 | Date | 2026-06-27 |  |  | President-T&D | Mr. Ganesh Srinivasan
| Project Name | Name of Line: Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line |  |  | NOA Start Date | 2025-05-13 | PCH | Mr. Arun Felbin
| Client Name | Powergrid West Central Transmission Ltd. |  |  | LOA End Date | 2028-11-12 | Regional Manager | Mr. Vijay Govindrao Kute
[5 empty] | Planning Engineer | Mr. Rishi Shukla | Project Manger | Mr. Minarul Alam
\
Check Survey
Activity | Unit | Final Est. Qty | L2 till Last Month | Submitted till Last Month | Approved till Last Month | Balance to Submit | Balance to Approve | L2 Submission Plan for Current Month | Progress For Month | Approved till Current Month | Remarks
Rout Alignment | km | 185.149 | 185.149 | 185.149 | 185.149 | 0 | 0 | - |  | 185.149
Detailed Survey | km | 184.986 | 184.986 | 184.986 | 166.531 | 0 | 18.455 | - | 11.8325 | 178.3635
Check Survey | km | 184.986 | 184.986 | 166.531 | 136.139 | 18.455 | 48.847 | - |  | 136.139
Progress Status
Activity | Final Estimated Quantity | Cumulative L2 till Last Month (May'26) | Cumulative Progress till Last Month(May'26) | L2 for present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks
Soil Investigation | 31 |  | 16 | 0 | 0 |  |  | 0 | 17 | 14 | 1
Foundation | 480 | 167 | 154 | 10 | 30 | 0 | 11 | 177 | 165 | 315 | 4 | 3
Earthing | 480 | 167 | 96 | 10 | 30 | 0 | 10 | 177 | 106 | 374
Tower Erection | 480 | 102 | 52 | 10 | 35 | 2 | 25 | 112 | 77 | 403 | 3 | 4
Tack welding | 480 | 102 | 0 | 10 | 35 | 0 | 0 | 112 | 0 | 480 | 2 | 2
Stringing(Km) | 184.986 | 10 | 0 | 5 | 0 |  | 0 | 15 | 0 | 184.986 | 0 | 0

## DPR Sheet
KEC INTERNATIONAL LIMITED
DAILY PROGRESS REPORT : SUBMISSION STATUS AS ON |  |  |  |  | 2026-06-27
Name of the Project: |  | ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6
Contract No. & Date : |  | CC/T/W/-TW/DOM/A06/24/04774/CA-1/25-105721,01&02 Dt.13.05.25
ROUTE ALIGNMENT PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
184.986 | 185.149 | 0 | 185.149 | 0
SOIL INVESTIGATION PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
31 | 17 | 0 | 17 | 14
DETAILED SURVEY PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
184.986 | 178.3635 | 11.83 | 178.3635 | 6.6225
CHECK SURVEY PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
184.986 | 136.139 | 30.3921 | 166.5311 | 18.4549
FOUNDATION PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
480 | 154 | 11 | 165 | 315
EARTHING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
480 | 96 | 10 | 106 | 374
TOWER ERECTION PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
480 | 52 | 25 | 77 | 403
STRINGING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY(KM)
184.986 | 0 | 0 | 0 | 184.986
OPGW STRINGING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
184.986 | 0 | 0 | 0 | 184.986

## Survey details 11-06-2026
Survey Status | [10 empty] | Date: 10-06-2026 | 2026-03-11
Project Name & Code |  |  | TA-602
Sl No | Section | Kms | Detailed Survey |  |  |  |  | Check Survey
|  |  | Completed | Submitted | Approved | Remarks | Surveyor | Completed | Submitted | Approved | Remarks | Surveyor
1 | AP0 to AP16 | 11.8325 | 11.8325 | 11.8325 | 11.8325 | Due to Brick -kiln Hold B/W Section AP13 to AP14(3.710) Submitted 26-05-2026 |  | 11.8325 | 11.8325 |  | Approved
3 | AP16 to AP29 | 7.454 | 7.454 | 7.454 | 7.454 | Approved | Mr. Hemanta/Mr. Tapas Das | 30.3921 | 30.3921 | 30.3921 | Approved
4 | AP29 to AP35 | 4.653 | 4.6525 | 4.6525 | 4.6525 | Approved | Mr. Hemanta/Mr. Tapas Das
5 | AP35 to AP 40 | 6.557 | 6.557 | 6.557 | 6.557 | Approved | Mr. Hemanta/Mr. Tapas Das
6 | AP 40 to AP 51 | 11.729 | 11.7286 | 11.7286 | 11.7286 | Approved | Mr. Hemanta/Mr. Tapas Das | [5 empty] | #REF!
10 |  |  |  | 0 | 0
11 | AP0 to AP23 |  |  | 0 | 0 | Route Diversion due to Newly under constrction house (Alternate Route Submitted) | Hemanta Malik/Tapas Das/Rakesh Debnath | 0 |  | 0
12 | AP33 to AP38A |  |  | 0 | 0 |  | Hemanta Malik/Tapas Das/Rakesh Debnath | 0 |  | 0
13 | AP38 to AP51 |  |  | 0 | 0 |  | Hemanta Malik/Tapas Das/Rakesh Debnath | 0 |  | 0
7 | AP51 to AP62 | 8.344 | 8.345 | 8.345 | 8.345 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 8.345 | 8.345 | 8.345 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
8 | AP62 to AP 64 | 3.615 | 3.615 | 3.615 | 3.615 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 3.615 | 3.615 | 3.615 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
9 | AP64 to AP71 | 9.709 | 9.71 | 9.71 | 9.71 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 9.71 | 9.71 | 9.71 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
13 | AP71 to AP75 | 3.714 | 3.787 | 3.787 | 3.787 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 3.787 | 3.787 | 3.787 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
14 | AP75 to AP76 | 1.238 | 1.178 | 1.178 | 1.178 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 1.178 | 1.178 | 1.178 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
15 | AP76 to AP83 | 7.242 | 7.241 | 7.241 | 7.241 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 7.241 | 7.241 | 7.241 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
16 | AP83 to AP92 | 22.602 | 22.602 | 22.602 | 22.602 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 22.602 | 22.602 | 22.602 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
17 | AP92 to AP94 | 4.351 | 4.351 | 4.351 | 4.351 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 4.351 | 4.351 | 4.351 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
18 | AP94 to AP99 | 6.622 | 6.622 | 6.622 |  | Narmada River Crossing | Hemanta Malik/Tapas Das | 0 | 0 | 0
19 | AP 99 to AP 106 | 11.413 | 11.413 | 11.413 | 11.413 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 11.413 | 11.413 | 11.413 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
20 | AP106 to AP110 | 10.77 | 10.77 | 10.77 | 10.77 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 10.77 | 10.77 | 10.77 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
21 | AP110 to AP118 | 10.198 | 10.198 | 10.198 | 10.198 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 10.198 | 10.198 | 10.198 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
22 | AP118 to AP 123 | 6.502 | 6.5023 | 6.5023 | 6.5023 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 6.5023 | 6.5023 | 6.5023 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
23 | AP123 to AP126 | 6.516 | 6.516 | 6.516 | 6.516 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 6.516 | 6.516 | 6.516 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
24 | AP126 to Ap127 | 4.34 | 4.34 | 4.34 | 4.34 | Approved | Hemanta Malik/Rakesh Debnath | 4.34 | 4.34 | 4.34 | Approved | Hemanta Malik/Rakesh Debnath
25 | AP127 to AP129A | 4.836 | 4.836 | 4.836 | 4.836 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 4.836 | 4.836 | 4.836 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
26 | AP129A to AP130 | 4.41 | 4.41 | 4.41 | 4.41 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 4.41 | 4.41 | 4.41 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
27 | AP130 to AP134 | 4.122 | 4.122 | 4.122 | 4.122 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 4.122 | 4.122 | 4.122 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
28 | AP134 to AP141 | 12.203 | 12.203 | 12.203 | 12.203 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 12.203 | 12.203 | 12.203 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
|  | 184.9725 | 184.9859 | 184.9859 | 178.3639 |  |  | 178.3639 | 178.3639 | 166.5314

## FDN
±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (Part- 6) Foundation
Sl. No. | Location No. | Tower Type | Classification | Concreting Volume in M3 | Starting Date | Todays Status | Pit A | Pit B | Pit C | Pit D | Cummulative Status | Completion Date | Remarks | Gang name | Earthing Status | Earthing Completion Date
1 | 125/2 | A+3 | DFR |  | 2025-09-02 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-09-15 |  | Balaji Enterprises |  |  | 11
2 | 125/3 | A+6 | DFR |  | 2025-09-09 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-10-03 |  | Balaji Enterprises |  |  | 11
3 | 123/1 | A+0 | WFR |  | 2025-10-01 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-10-07 |  | R.K . Enterprises | C | 2025-10-10 | 11
4 | 124/1 | A+6 | WET Paddy |  | 2025-09-21 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-10-08 |  | Balaji Enterprises | C | 2025-11-21 | 11
5 | 124/2 | A+6 | WFR |  | 2025-09-07 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-10-15 |  | Jai Shri Ram Enterprises | C | 2025-10-20 | 11
6 | 121/7 | A+0 | WFR |  | 2025-09-24 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-10-16 |  | Pawan enterprises | C | 2025-11-07 | 11
7 | 121/2 | A+6 | DFR |  | 2025-10-08 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-10-19 |  | Balaji Enterprises | C | 2025-10-20 | 11
8 | 123/3 | A+9 | DFR |  | 2025-10-08 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-10-19 |  | R.K . Enterprises | C | 2025-10-22 | 11
9 | 122/2 | A+0 | WFR |  | 2025-10-10 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-10-25 |  | Jai Shri Ram Enterprises | C | 2025-11-02 | 11
10 | 126/5 | A+3 | DFR |  | 2025-10-11 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-10-28 |  | Rajiya Infra. | C | 2025-11-03 | 11
11 | 116/1 | A+3 | DFR |  | 2025-10-12 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-01 |  | B.L Construction | C | 2025-11-04 | 11
12 | 126/4 | A+0 | DFR |  | 2025-10-12 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-01 |  | Rajiya Infra. | C | 2025-11-07 | 11
13 | 116/2 | A+3 | DFR |  | 2025-10-12 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-03 |  | B.L Construction | C | 2025-11-08 | 11
14 | 124/3 | A+9 | WFR |  | 2025-09-10 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-04 |  | Jai Shri Ram Enterprises |  |  | 11
15 | 123/4 | A+0 | WET |  | 2025-09-30 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-06 |  | Shri Balaji Construction | C | 2025-11-08 | 11
16 | 126/3 | A+3 | DFR |  | 2025-10-30 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-06 |  | Rajiya Infra. | C | 2025-11-13 | 11
17 | 130/1 | A+0 | DFR |  | 2025-10-27 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-08 |  | R.K . Enterprises | C | 2025-12-04 | 11
18 | 111/1 | A+0 | DFR |  | 2025-10-31 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-09 |  | B.L Construction |  |  | 11
19 | 126/9 | A+3 | DFR |  | 2025-10-11 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-11 |  | Rajiya Infra. | C | 2025-11-24 | 11
20 | 123/2 | A+0 | WFR |  | 2025-10-28 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-13 |  | Jai Shri Ram Enterprises | C | 2025-11-20 | 11
21 | 111/2 | A+3 | DFR |  | 2025-11-08 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-14 |  | B.L Construction | C | 2025-11-24 | 11
22 | 126/10 | A+0 | DFR |  | 2025-10-10 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-14 |  | Rajiya Infra. | C | 2025-11-25 | 11
23 | 121/6 | A+0 | DFR |  | 2025-11-07 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-15 |  | Pawan enterprises |  |  | 11
24 | 121/1 | A+0 | DFR |  | 2025-11-07 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-16 |  | Shri Balaji Construction | C | 2025-11-19 | 11
25 | 111/3 | A+0 | WFR |  | 2025-11-07 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-19 |  | B.L Construction | C | 2025-11-26 | 11
26 | 130/3 | A+3 | WFR |  | 2025-11-09 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-19 |  | R.K . Enterprises | C | 2025-11-26 | 11
27 | 103/2 | A+0 | WET PADDY |  | 2025-11-09 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-20 |  | MUKESH MEHTA | C | 2025-11-23 | 11
28 | 124/4 | A+3 | WFR |  | 2025-11-08 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-21 |  | Jai Shri Ram Enterprises | C | 2025-11-23 | 11
29 | 126/2 | A+9 | WFR |  | 2025-11-13 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-21 |  | Rajiya Infra. | C | 2025-11-23 | 11
30 | 121/4 | A+0 | DFR |  | 2025-11-16 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-22 |  | Pawan enterprises | C | 2025-11-25 | 11
31 | 111/4 | A+0 | DFR |  | 2025-11-14 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-23 |  | B.L Construction | C | 2025-11-25 | 11
32 | 103/3 | A+3 | WET PADDY |  | 2025-11-07 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-24 |  | MUKESH MEHTA | C | 2025-11-26 | 11
33 | 134/2 | A+3 | WFR |  | 2025-11-15 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-24 |  | R.K . Enterprises |  |  | 11
34 | 103/1 | A+6 | WET PADDY |  | 2025-11-23 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-28 |  | MUKESH MEHTA | C | 2025-12-02 | 11
35 | 111/5 | A+6 | DFR |  | 2025-11-20 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-28 |  | B.L Construction | C | 2025-11-30 | 11
36 | 134/3 | A+6 | WFR |  | 2025-11-24 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-28 |  | R.K . Enterprises |  |  | 11
37 | 102/7 | A+0 | WET PADDY |  | 2025-11-07 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-30 |  | Rajiya Infra. | C | 2025-12-09 | 11
38 | 110/2 | A+0 | DFR |  | 2025-11-23 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-30 |  | Shri Balaji Construction | C | 2025-12-05 | 11
39 | 121/5 | A+0 | DFR |  | 2025-11-23 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-30 |  | Pawan enterprises |  |  | 11
40 | 134/5 | A+0 | DFR |  | 2025-11-23 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-11-30 |  | Jai Shri Ram Enterprises |  |  | 11
41 | 110/1 | A+7.5 | DFR |  | 2025-11-28 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-03 |  | B.L Construction | C | 2025-12-05 | 10
42 | 134/4 | A+3 | DFR |  | 2025-11-20 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-03 |  | R.K . Enterprises |  |  | 10
43 | 99/1 | A+3 | WET PADDY |  | 2025-11-24 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-06 |  | Dhanraj construction | C | 2025-12-09 | 10
44 | 109/1 | A+3 | WET PADDY |  | 2025-11-30 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-06 |  | MUKESH MEHTA | C | 2025-12-07 | 10
45 | 134/6 | A+3 | DFR |  | 2025-11-25 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-06 |  | Jai Shri Ram Enterprises |  |  | 10
46 | 102/9 | A+3 | WET PADDY |  | 2025-11-21 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-07 |  | Rajiya Infra. | C | 2025-12-09 | 10
47 | 109/10 | A-3 | DFR |  | 2025-12-03 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-07 |  | B.L Construction |  |  | 10
48 | 134/9 | A+0 | WET PADDY |  | 2025-12-01 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-07 |  | R.K . Enterprises | C | 2025-12-08 | 10
49 | 134/7 | A+3 | DFR |  | 2025-12-01 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-08 |  | Jai Shri Ram Enterprises |  |  | 10
50 | 136/2 | A+3 | WET Paddy |  | 2025-12-01 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-10 |  | R.K . Enterprises | C | 2025-12-21 | 10
51 | 110/3 | A+0 | DFR |  | 2025-11-29 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-11 |  | Shri Balaji Construction | C | 2025-12-13 | 10
52 | 109/2 | A+0 | WET PADDY |  | 2025-12-07 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-12 |  | MUKESH MEHTA | C | 2025-12-28 | 10
53 | 109/11 | A+3 | DFR |  | 2025-12-04 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-12 |  | B.L Construction |  |  | 10
54 | 136/7 | A+0 | WET PADDY |  | 2025-12-06 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-12 |  | R.K . Enterprises | C | 2025-12-20 | 10
55 | 99/2 | A+3 | WET PADDY |  | 2025-12-07 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-13 |  | Dhanraj construction | C | 2025-12-20 | 10
56 | 102/8 | A+0 | WET PADDY |  | 2025-12-07 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-15 |  | Rajiya Infra. | C | 2025-12-21 | 10
57 | 108/7 | A-3 | WET PADDY |  | 2025-12-10 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-16 |  | MUKESH MEHTA | C | 2025-12-27 | 10
58 | 136/8 | A+0 | WET PADDY |  | 2025-12-07 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-16 |  | R.K . Enterprises | C | 2025-12-21 | 10
59 | 134/8 | A+3 | WFR |  | 2025-11-26 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-17 | Drawing Approval Done | Jai Shri Ram Enterprises |  |  | 10
60 | 136/5 | A+0 | WET PADDY |  | 2025-12-13 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-17 |  | R.K . Enterprises | C | 2025-12-20 | 10
61 | 110/4 | A+0 | DFR |  | 2025-12-10 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-19 |  | Shri Balaji Construction |  |  | 10
62 | 136/9 | A+0 | WET PADDY |  | 2025-12-14 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-19 |  | R.K . Enterprises | C | 2025-12-21 | 10
63 | 109/7 | A+3 | DFR |  | 2025-12-11 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-20 |  | B.L Construction |  |  | 10
64 | 108/5 | A-3 | WET PADDY |  | 2025-12-12 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-22 |  | MUKESH MEHTA | C | 2025-12-24 | 10
65 | 136/6 | A+0 | WET Paddy |  | 2025-12-07 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-22 |  | R.K . Enterprises | C | 2025-12-23 | 10
66 | 89/9 | A+0 | WFR |  | 2025-12-22 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-24 |  | Shree Khatushyam | C | 2025-12-27 | 10
67 | 109/9 | A+3 | DFR |  | 2025-12-22 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-24 |  | B.L Construction |  |  | 10
68 | 139/3 | A+3 | DFR |  | 2025-12-22 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-24 |  | Jai Shri Ram Enterprises |  |  | 10
69 | 107/2 | A-3 | WFR |  | 2025-12-22 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-26 |  | Rajiya Infra. |  |  | 10
70 | 108/6 | A-3 | WET PADDY |  | 2025-12-22 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-26 |  | MUKESH MEHTA | C | 2025-12-27 | 10
71 | 109/6 | A+3 | DFR |  | 2025-12-22 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-27 |  | B.L Construction |  |  | 10
72 | 130/2 | A+6 | DFR |  | 2025-11-06 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-27 |  | R.K . Enterprises | C | 2025-12-29 | 10
73 | 89/8 | A+0 | DFR |  | 2025-12-22 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-28 |  | Afflux Construction | C | 2025-12-30 | 10
74 | 136/1 | A+0 | WET PADDY |  | 2025-12-25 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-29 |  | R.K . Enterprises | C | 2025-12-30 | 10
75 | 89/7 | A+0 | DFR |  | 2025-12-24 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-30 |  | Shree Khatushyam | C | 2026-01-03 | 10
76 | 109/5 | A+3 | DFR |  | 2025-12-22 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-30 |  | B.L Construction |  |  | 10
77 | 139/2 | A+0 | DFR |  | 2025-12-25 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2025-12-30 |  | Jai Shri Ram Enterprises |  |  | 10
78 | 107/1 | A+0 | WFR |  | 2025-12-23 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-03 |  | Rajiya Infra. |  |  | 10
79 | 89/6 | A+0 | DFR |  | 2025-12-28 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-04 |  | Afflux Construction | C | 2026-01-08 | 11
80 | 129A/1 | A-3 | DFR |  | 2026-01-04 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-07 |  | R.K . Enterprises |  |  | 11
81 | 139/5 | A+0 | DFR |  | 2025-12-31 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-09 |  | Jai Shri Ram Enterprises |  |  | 10
82 | 89/5 | A+3 | DFR |  | 2026-01-02 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-10 |  | Shree Khatushyam | C | 2026-01-12 | 11
83 | 108/4 | A+3 | WFR |  | 2025-12-18 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-11 |  | B.L Construction |  |  | 10
84 | 129A/5 | A+9 | DFR |  | 2026-01-04 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-11 |  | R.K . Enterprises |  |  | 11
85 | 108/1 | A+9 | DFR |  | 2026-01-11 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-17 |  | B.L Construction | C | 2026-01-19 | 11
86 | 76/2 | A+6 | DFR |  | 2026-01-14 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-20 |  | Afflux Construction | C | 2026-01-24 | 11
87 | 136/4 | A+0 | WET PADDY |  | 2026-01-16 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-20 |  | R.K . Enterprises | C | 2026-01-21 | 10
88 | 77/1 | A-3 | DFR |  | 2026-01-18 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-24 |  | Shree Khatushyam | C | 2026-02-02 | 11
89 | 107/4 | A+3 | DFR |  | 2026-01-16 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-25 |  | B.L Construction |  |  | 10
90 | 76/1 | A+6 | DFR |  | 2026-01-14 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-27 |  | Afflux Construction | C | 2026-02-04 | 11
91 | 129A/7 | A+1.5 | DFR |  | 2026-01-14 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-27 |  | R.K . Enterprises |  |  | 10
92 | 139/6 | A+0 | DFR |  | 2026-01-11 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-28 |  | Jai Shri Ram Enterprises |  |  | 10
93 | 127/7 | A-3 | DFR |  | 2026-01-19 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-30 |  | B.L Construction | C | 2026-02-02 | 10
94 | 129A/2 | A+7.5 | DFR |  | 2026-01-23 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-30 |  | R.K . Enterprises | C | 2026-02-02 | 10
95 | 76/6 | A+1.5 | DFR |  | 2026-01-20 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-31 |  | Shree Khatushyam |  |  | 11
96 | 129A/4 | A+6 | DFR |  | 2026-01-23 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-31 |  | R.K . Enterprises | C | 2026-02-03 | 10
97 | 136/3 | A+3 | DFR |  | 2026-01-27 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-01-31 |  | Jai Shri Ram Enterprises |  |  | 10
98 | 82/2 | A+7.5 | WFR |  | 2026-01-27 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-02-02 |  | Afflux Construction | C | 2026-02-04 | 10
99 | 127/4 | A+3 | WFR |  | 2026-01-20 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-02-03 |  | B.L Construction | C | 2026-04-17 | 10
100 | 129A/10 | A+1.5 | DFR |  | 2026-01-30 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-02-05 |  | R.K . Enterprises |  |  | 11
101 | 82/3 | A+9 | WET |  | 2026-01-31 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-02-08 |  | Afflux Construction | C | 2026-02-09 | 11
102 | 127/1 | A+3 | DFR |  | 2026-01-30 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-02-09 |  | B.L Construction | C | 2026-02-10 | 11
103 | 129A/3 | A+3 | DFR |  | 2026-02-07 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-02-11 |  | R.K . Enterprises | C | 2026-02-13 | 11
104 | 70/3 | A-3 | DFR |  | 2026-02-06 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-02-13 |  | Afflux Construction | C | 2026-02-19 | 11
105 | 127/2 | A+0 | DFR |  | 2026-02-06 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-02-13 |  | B.L Construction | C | 2026-02-14 | 11
106 | 129A/6 | A+9 | WFR |  | 2026-01-11 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-02-16 |  | R.K . Enterprises | C | 2026-02-17 | 10
107 | 121/10 | A+9 | DFR |  | 2026-02-11 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-02-17 |  | B.L Construction | C | 2026-02-27 | 11
108 | 70/1 | A+4.5 | DFR |  | 2026-02-06 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-02-23 |  | Afflux Construction | C | 2026-02-24 | 11
109 | 125/1 | A+3 | WFR |  | 2026-02-17 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-02-28 |  | B.L Construction |  |  | 10
110 | 126/7 | A+0 | DFR |  | 2026-02-17 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-03-03 |  | B.L Construction | C | 2026-03-10 | 11
111 | 70/2 | A+9 | WFR |  | 2026-02-13 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-03-07 |  | Afflux Constrcutoin | C | 2026-03-08 | 10
112 | 124/5 | A+6 | DFR |  | 2026-02-08 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-03-14 |  | B.L Construction |  |  | 10
113 | 76/5 | A+9 | DFR |  | 2026-03-12 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-03-21 |  | Afflux Constrcutoin | C | 2026-03-23 | 11
114 | 88/2 | A+0 | DFR |  | 2026-02-23 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-03-30 |  | Afflux Constrcutoin | C | 2026-04-04 | 10
115 | 88/1 | A+3 | DFR |  | 2026-03-22 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-02 |  | Afflux Construction | C | 2026-04-12 | 11
116 | 127/3 | A+0 | DFR |  | 2026-03-06 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-03 |  | Jai Shree Ram |  |  | 11
117 | 87/4 | A+0 | DFR |  | 2026-03-29 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-08 |  | Afflux Construction | C | 2026-04-22 | 10
118 | 124/0 | B2+0 | Wet Paddy |  | 2026-03-16 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-08 |  | B.L Construction | C | 2026-04-09 | 10
119 | 102/11 | A+9 | Wet Paddy |  | 2026-03-24 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-11 |  | Dhanraj | C | 2026-04-13 | 11
120 | 139/4 | A+0 | DFR |  | 2026-03-18 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-11 |  | Jai Shree Ram |  |  | 11
121 | 69/2 | A+0 | DFR |  | 2026-03-17 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-13 |  | Kalyan Singh | C | 2026-04-17 | 10
122 | 87/5 | A+3 | DFR |  | 2026-04-06 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-14 |  | Afflux Construction | C | 2026-04-19 | 11
123 | 121/9 | A+0 | DFR |  | 2026-04-03 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-15 |  | B.L Construction |  |  | 10
124 | 71/1 | A+3 | WFR |  | 2026-03-14 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-18 |  | Sohan Enterprises | C | 2026-04-21 | 11
125 | 87/2 | A+0 | DFR |  | 2026-04-06 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-18 |  | Afflux Construction | C | 2026-04-27 | 11
126 | 69/1 | A+0 | DFR |  | 2026-03-25 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-21 |  | Kalyan Singh | C | 2026-04-23 | 11
127 | 109/8 | A+3 | DFR |  | 2026-04-07 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-22 |  | B.L Construction |  |  | 11
128 | 125/0 | B2+3 | DFR |  | 2026-03-18 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-23 |  | BL. Construction |  |  | 10
129 | 71/2 | A-3 | DFR |  | 2026-03-18 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-24 |  | Soham Entp | C | 2026-04-27 | 11
130 | 136/0 | C2+9 | Wet Paddy |  | 2026-03-28 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-24 |  | Jai Shree Ram |  |  | 10
131 | 87/3 | A+3 | DFR |  | 2026-04-18 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-25 |  | Afflux Construction | C | 2026-05-03 | 11
132 | 69/3 | A+0 | DFR |  | 2026-04-07 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-28 |  | Kalyan Singh | C | 2026-04-28 | 11
133 | 71/3 | A+0 | DFR |  | 2026-04-21 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-30 |  | Soham Entp | C | 2026-05-02 | 11
134 | 88/3 | A-3 | DFR |  | 2026-04-18 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-30 |  | Afflux Construction | C | 2026-05-20 | 11
135 | 127/0 | B1+0 | DFR |  | 2026-03-20 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-30 |  | B.L Construction |  |  | 10
136 | 139/0 | B2+0 | Wet Paddy |  | 2026-03-30 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-04-30 |  | Jai Shree Ram | C | 2026-05-02 | 10
137 | 71/4 | A-3 | DFR |  | 2026-04-23 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-04 |  | Soham Entp | C | 2026-05-04 | 10
138 | 108/0 | C1+9 | DFR |  | 2026-04-24 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-04 |  | BL. Construction |  |  | 10
139 | 139/1 | A+3 | DFR |  | 2026-04-23 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-04 |  | Jai Shree Ram |  |  | 10
140 | 107/0 | C2+3 | DFR |  | 2026-03-27 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-06 |  | Dhanraj Construction |  |  | 10
141 | 69/4 | A+0 | DFR |  | 2026-05-01 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-08 |  | Soham Entp | C | 2026-05-23 | 10
142 | 126/0 | C2+0 | DFR |  | 2026-04-29 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-12 |  | BL. Construction |  |  | 10
143 | 88/0 | C2+3 | DFR |  | 2026-04-25 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-15 |  | Afflux |  |  | 10
144 | 135/0 | B2+9 | Wet Paddy |  | 2026-04-16 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-19 |  | Jai Shree Ram |  |  | 10
145 | 71/5 | A+3 | WFR |  | 2026-05-04 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-21 |  | Soham Entp | C | 2026-06-06 | 10
146 | 102/10 | A+0 | Wet Paddy |  | 2026-04-21 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-23 |  | Sawariya | C | 2026-06-04 | 10
147 | 109/0 | B2+0 | Wet |  | 2026-04-19 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-23 |  | BL. Construction |  |  | 10
148 | 123/0 | B2+0 | DFR |  | 2026-05-05 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-23 |  | BL. Construction |  |  | 10
149 | 88/5 | B1+0 | DFR |  | 2026-04-30 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-24 |  | Afflux | C | 2026-06-02 | 10
150 | 102/5 | A+0 | WET PADDY |  | 2026-04-16 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-26 |  | M./S Sanjay kumar |  |  | 10
151 | 72/1 | A+9 | DFR |  | 2026-05-19 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-27 |  | Soham Entp | C | 2026-06-06 | 10
152 | 88/4 | B1+3 | Wet Paddy |  | 2026-05-02 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-29 |  | Afflux | C | 2026-06-02 | 10
153 | 132/2 | A+0 | DFR |  | 2026-05-05 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-30 |  | Jai Shree Ram |  |  | 10
154 | 76/4 | A+0 | DFR |  | 2026-05-21 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-05-31 |  | Soham Entp | C | 2026-06-06 | 10
155 | 64/5 | A+3 | Wet Paddy |  | 2026-05-25 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-06-01 |  | Afflux |  |  | 10
156 | 104/0 | B2+3 | Wet Paddy |  | 2026-04-18 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-06-01 |  | Sawariya | C | 2026-06-02 | 10
157 | 116/0 | C1+3 | DFR |  | 2026-05-24 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-06-03 |  | B.L Construction | C | 2026-06-09 | 10
158 | 90/0 | C1+0 | DFR |  | 2026-05-17 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-06-04 |  | Afflux | C | 2026-06-10 | 10
159 | 116/3 | A+9 | DFR |  | 2026-06-03 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-06-07 |  | BL. Construction | 0 |  | 10
160 | 104/1 | A+9 | WET PADDY |  | 2026-05-29 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-06-09 |  | Sanjay Kumar |  |  | 10
161 | 64/4 | A+0 | DFR |  | 2026-05-25 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-06-09 |  | Afflux | C | 2026-06-11 | 10
162 | 70/0 | C2-3 | DFR |  | 2026-05-03 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-06-13 |  | Soham Entp | C | 2026-06-15 | 10
163 | 65/1 | A+0 | DFR |  | 2026-06-03 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-06-19 |  | Afflux | C | 2026-06-21 | 10
164 | 77/0 | B2+0 | DFR |  | 2026-06-03 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-06-21 |  | Soham Entp |  |  | 10
165 | 110/0 | D45+3 | DFR |  | 2026-06-17 |  | RCC Complete | RCC Complete | RCC Complete | RCC Complete | Completed | 2026-06-25 |  | BL. Construction |  | 110/0 | 7
166 | 63/3 | A-3 | DFR |  | 2026-06-12 | RCC WIP | Frustum Completed | Frustum Completed | Frustum Completed | Frustum Completed | WIP |  |  | Afflux |  |  | 6
167 | 63/4 | A+0 | DFR |  | 2026-06-12 | Block Level & Pit Dressing WIP | Bl;ock Level | Bl;ock Level | Pit Dressing WIP | Pit Dressing WIP | WIP |  |  | Afflux |  |  | 6
168 | 78/0 | C2-3 | DFR |  | 2026-06-15 | PCC Completed | PCC Completed | PCC Completed | PCC Completed | PCC Completed | WIP |  |  | Soham Entp |  |  | 6
169 | 65/0 | B2+0 |  |  | 411433 | Excavation WIP | Excavation WIP | Excavation WIP | Excavation WIP | Excavation WIP | wip | [5 empty] | 6
170 | 67/3 | A+6 | DFR |  | 2026-06-05 | ROW | Excavation WIP | Excavation WIP | Excavation WIP | Excavation WIP | ROW |  | ROW(10/06/2026) | Afflux
[10 empty] | Completed | 165 |  |  |  | 107
[10 empty] | WIP | 4

## FDN Completed (hidden)
Foundation
Sl. No. | Location No. | Tower Type | Classification | Starting Date | Cumulative Status | Completion Date | Remarks | Gang name | Earthing Status | Earthing Completion Date
1 | 125/2 | A+3 | DFR | 2025-09-02 | Completed | 2025-09-15 |  | Balaji Enterprises
2 | 125/3 | A+6 | DFR | 2025-09-09 | Completed | 2025-10-03 |  | Balaji Enterprises
3 | 123/1 | A+0 | WFR | 2025-10-01 | Completed | 2025-10-07 |  | R.K . Enterprises | C | 2025-10-10
4 | 124/1 | A+6 | WET Paddy | 2025-09-21 | Completed | 2025-10-08 |  | Balaji Enterprises | C | 2025-11-21
5 | 124/2 | A+6 | WFR | 2025-09-07 | Completed | 2025-10-15 |  | Jai Shri Ram Enterprises | C | 2025-10-20
6 | 121/7 | A+0 | WFR | 2025-09-24 | Completed | 2025-10-16 |  | Pawan enterprises | C | 2025-11-07
7 | 121/2 | A+6 | DFR | 2025-10-08 | Completed | 2025-10-19 |  | Balaji Enterprises | C | 2025-10-20
8 | 123/3 | A+9 | DFR | 2025-10-08 | Completed | 2025-10-19 |  | R.K . Enterprises | C | 2025-10-22
9 | 122/2 | A+0 | WFR | 2025-10-10 | Completed | 2025-10-25 |  | Jai Shri Ram Enterprises | C | 2025-11-02
10 | 126/5 | A+3 | DFR | 2025-10-11 | Completed | 2025-10-28 |  | Rajiya Infra. | C | 2025-11-03
11 | 116/1 | A+3 | DFR | 2025-10-12 | Completed | 2025-11-01 |  | B.L Construction | C | 2025-11-04
12 | 126/4 | A+0 | DFR | 2025-10-12 | Completed | 2025-11-01 |  | Rajiya Infra. | C | 2025-11-07
13 | 116/2 | A+3 | DFR | 2025-10-12 | Completed | 2025-11-03 |  | B.L Construction | C | 2025-11-08
14 | 124/3 | A+9 | WFR | 2025-09-10 | Completed | 2025-11-04 |  | Jai Shri Ram Enterprises
15 | 123/4 | A+0 | WET | 2025-09-30 | Completed | 2025-11-06 |  | Shri Balaji Construction | C | 2025-11-08
16 | 126/3 | A+3 | DFR | 2025-10-30 | Completed | 2025-11-06 |  | Rajiya Infra. | C | 2025-11-13
17 | 130/1 | A+0 | DFR | 2025-10-27 | Completed | 2025-11-08 |  | R.K . Enterprises | C | 2025-12-04
18 | 111/1 | A+0 | DFR | 2025-10-31 | Completed | 2025-11-09 |  | B.L Construction
19 | 126/9 | A+3 | DFR | 2025-10-11 | Completed | 2025-11-11 |  | Rajiya Infra. | C | 2025-11-24
20 | 123/2 | A+0 | WFR | 2025-10-28 | Completed | 2025-11-13 |  | Jai Shri Ram Enterprises | C | 2025-11-20
21 | 111/2 | A+3 | DFR | 2025-11-08 | Completed | 2025-11-14 |  | B.L Construction | C | 2025-11-24
22 | 126/10 | A+0 | DFR | 2025-10-10 | Completed | 2025-11-14 |  | Rajiya Infra. | C | 2025-11-25
23 | 121/6 | A+0 | DFR | 2025-11-07 | Completed | 2025-11-15 |  | Pawan enterprises
24 | 121/1 | A+0 | DFR | 2025-11-07 | Completed | 2025-11-16 |  | Shri Balaji Construction | C | 2025-11-19
25 | 111/3 | A+0 | WFR | 2025-11-07 | Completed | 2025-11-19 |  | B.L Construction | C | 2025-11-26
26 | 130/3 | A+3 | WFR | 2025-11-09 | Completed | 2025-11-19 |  | R.K . Enterprises | C | 2025-11-26
27 | 103/2 | A+0 | WET PADDY | 2025-11-09 | Completed | 2025-11-20 |  | MUKESH MEHTA | C | 2025-11-23
28 | 124/4 | A+3 | WFR | 2025-11-08 | Completed | 2025-11-21 |  | Jai Shri Ram Enterprises | C | 2025-11-23
29 | 126/2 | A+9 | WFR | 2025-11-13 | Completed | 2025-11-21 |  | Rajiya Infra. | C | 2025-11-23
30 | 121/4 | A+0 | DFR | 2025-11-16 | Completed | 2025-11-22 |  | Pawan enterprises | C | 2025-11-25
31 | 111/4 | A+0 | DFR | 2025-11-14 | Completed | 2025-11-23 |  | B.L Construction | C | 2025-11-25
32 | 103/3 | A+3 | WET PADDY | 2025-11-07 | Completed | 2025-11-24 |  | MUKESH MEHTA | C | 2025-11-26
33 | 134/2 | A+3 | WFR | 2025-11-15 | Completed | 2025-11-24 |  | R.K . Enterprises
34 | 103/1 | A+6 | WET PADDY | 2025-11-23 | Completed | 2025-11-28 |  | MUKESH MEHTA | C | 2025-12-02
35 | 111/5 | A+6 | DFR | 2025-11-20 | Completed | 2025-11-28 |  | B.L Construction | C | 2025-11-30
36 | 134/3 | A+6 | WFR | 2025-11-24 | Completed | 2025-11-28 |  | R.K . Enterprises
37 | 102/7 | A+0 | WET PADDY | 2025-11-07 | Completed | 2025-11-30 |  | Rajiya Infra. | C | 2025-12-09
38 | 110/2 | A+0 | DFR | 2025-11-23 | Completed | 2025-11-30 |  | Shri Balaji Construction | C | 2025-12-05
39 | 121/5 | A+0 | DFR | 2025-11-23 | Completed | 2025-11-30 |  | Pawan enterprises
40 | 134/5 | A+0 | DFR | 2025-11-23 | Completed | 2025-11-30 |  | Jai Shri Ram Enterprises
41 | 110/1 | A+7.5 | DFR | 2025-11-28 | Completed | 2025-12-03 |  | B.L Construction | C | 2025-12-05
42 | 134/4 | A+3 | DFR | 2025-11-20 | Completed | 2025-12-03 |  | R.K . Enterprises
43 | 99/1 | A+3 | WET PADDY | 2025-11-24 | Completed | 2025-12-06 |  | Dhanraj construction | C | 2025-12-09
44 | 109/1 | A+3 | WET PADDY | 2025-11-30 | Completed | 2025-12-06 |  | MUKESH MEHTA | C | 2025-12-07
45 | 134/6 | A+3 | DFR | 2025-11-25 | Completed | 2025-12-06 |  | Jai Shri Ram Enterprises
46 | 102/9 | A+3 | WET PADDY | 2025-11-21 | Completed | 2025-12-07 |  | Rajiya Infra. | C | 2025-12-09
47 | 109/10 | A-3 | DFR | 2025-12-03 | Completed | 2025-12-07 |  | B.L Construction
48 | 134/9 | A+0 | WET PADDY | 2025-12-01 | Completed | 2025-12-07 |  | R.K . Enterprises | C | 2025-12-08
49 | 134/7 | A+3 | DFR | 2025-12-01 | Completed | 2025-12-08 |  | Jai Shri Ram Enterprises
50 | 136/2 | A+3 | WET Paddy | 2025-12-01 | Completed | 2025-12-10 |  | R.K . Enterprises | C | 2025-12-21
51 | 110/3 | A+0 | DFR | 2025-11-29 | Completed | 2025-12-11 |  | Shri Balaji Construction | C | 2025-12-13
52 | 109/2 | A+0 | WET PADDY | 2025-12-07 | Completed | 2025-12-12 |  | MUKESH MEHTA | C | 2025-12-28
53 | 109/11 | A+3 | DFR | 2025-12-04 | Completed | 2025-12-12 |  | B.L Construction
54 | 136/7 | A+0 | WET PADDY | 2025-12-06 | Completed | 2025-12-12 |  | R.K . Enterprises | C | 2025-12-20
55 | 99/2 | A+3 | WET PADDY | 2025-12-07 | Completed | 2025-12-13 |  | Dhanraj construction | C | 2025-12-20
56 | 102/8 | A+0 | WET PADDY | 2025-12-07 | Completed | 2025-12-15 |  | Rajiya Infra. | C | 2025-12-21
57 | 108/7 | A-3 | WET PADDY | 2025-12-10 | Completed | 2025-12-16 |  | MUKESH MEHTA | C | 2025-12-27
58 | 136/8 | A+0 | WET PADDY | 2025-12-07 | Completed | 2025-12-16 |  | R.K . Enterprises | C | 2025-12-21
59 | 134/8 | A+3 | WFR | 2025-11-26 | Completed | 2025-12-17 |  | Jai Shri Ram Enterprises
60 | 136/5 | A+0 | WET PADDY | 2025-12-13 | Completed | 2025-12-17 |  | R.K . Enterprises | C | 2025-12-20
61 | 110/4 | A+0 | DFR | 2025-12-10 | Completed | 2025-12-19 |  | Shri Balaji Construction
62 | 136/9 | A+0 | WET PADDY | 2025-12-14 | Completed | 2025-12-19 |  | R.K . Enterprises | C | 2025-12-21
63 | 109/7 | A+3 | DFR | 2025-12-11 | Completed | 2025-12-20 |  | B.L Construction
64 | 108/5 | A-3 | WET PADDY | 2025-12-12 | Completed | 2025-12-22 |  | MUKESH MEHTA | C | 2025-12-24
65 | 136/6 | A+0 | WET Paddy | 2025-12-07 | Completed | 2025-12-22 |  | R.K . Enterprises | C | 2025-12-23
66 | 89/9 | A+0 | WFR | 2025-12-22 | Completed | 2025-12-24 |  | Shree Khatushyam | C | 2025-12-27
67 | 109/9 | A+3 | DFR | 2025-12-22 | Completed | 2025-12-24 |  | B.L Construction
68 | 139/3 | A+3 | DFR | 2025-12-22 | Completed | 2025-12-24 |  | Jai Shri Ram Enterprises
69 | 107/2 | A-3 | WFR | 2025-12-22 | Completed | 2025-12-26 |  | Rajiya Infra.
70 | 108/6 | A-3 | WET PADDY | 2025-12-22 | Completed | 2025-12-26 |  | MUKESH MEHTA | C | 2025-12-27
71 | 109/6 | A+3 | DFR | 2025-12-22 | Completed | 2025-12-27 |  | B.L Construction
72 | 130/2 | A+6 | DFR | 2025-11-06 | Completed | 2025-12-27 |  | R.K . Enterprises | C | 2025-12-29
73 | 89/8 | A+0 | DFR | 2025-12-22 | Completed | 2025-12-28 |  | Afflux Construction | C | 2025-12-30
74 | 136/1 | A+0 | WET PADDY | 2025-12-25 | Completed | 2025-12-29 |  | R.K . Enterprises | C | 2025-12-30
75 | 89/7 | A+0 | DFR | 2025-12-24 | Completed | 2025-12-30 |  | Shree Khatushyam | C | 2026-01-03
76 | 109/5 | A+3 | DFR | 2025-12-22 | Completed | 2025-12-30 |  | B.L Construction
77 | 139/2 | A+0 | DFR | 2025-12-25 | Completed | 2025-12-30 |  | Jai Shri Ram Enterprises
78 | 107/1 | A+0 | WFR | 2025-12-23 | Completed | 2026-01-03 |  | Rajiya Infra.
79 | 89/6 | A+0 | DFR | 2025-12-28 | Completed | 2026-01-04 |  | Afflux Construction | C | 2026-01-08
80 | 129A/1 | A-3 | DFR | 2026-01-04 | Completed | 2026-01-07 |  | R.K . Enterprises
81 | 139/5 | A+0 | DFR | 2025-12-31 | Completed | 2026-01-09 |  | Jai Shri Ram Enterprises
82 | 89/5 | A+3 | DFR | 2026-01-02 | Completed | 2026-01-10 |  | Shree Khatushyam | C | 2026-01-12
83 | 108/4 | A+3 | WFR | 2025-12-18 | Completed | 2026-01-11 |  | B.L Construction
84 | 129A/5 | A+9 | DFR | 2026-01-04 | Completed | 2026-01-11 |  | R.K . Enterprises
85 | 108/1 | A+9 | DFR | 2026-01-11 | Completed | 2026-01-17 |  | B.L Construction | C | 2026-01-19
86 | 76/2 | A+6 | DFR | 2026-01-14 | Completed | 2026-01-20 |  | Afflux Construction | C | 2026-01-24 | ROW Cleared on 29/04/25
87 | 136/4 | A+0 | WET PADDY | 2026-01-16 | Completed | 2026-01-20 |  | R.K . Enterprises | C | 2026-01-21
88 | 77/1 | A-3 | DFR | 2026-01-18 | Completed | 2026-01-24 |  | Shree Khatushyam | C | 2026-02-02
89 | 107/4 | A+3 | DFR | 2026-01-16 | Completed | 2026-01-25 |  | B.L Construction
90 | 76/1 | A+6 | DFR | 2026-01-14 | Completed | 2026-01-27 |  | Afflux Construction | C | 2026-02-04
91 | 129A/7 | A+1.5 | DFR | 2026-01-14 | Completed | 2026-01-27 |  | R.K . Enterprises
92 | 139/6 | A+0 | DFR | 2026-01-11 | Completed | 2026-01-28 |  | Jai Shri Ram Enterprises
93 | 127/7 | A-3 | DFR | 2026-01-19 | Completed | 2026-01-30 |  | B.L Construction | C | 2026-02-02
94 | 129A/2 | A+7.5 | DFR | 2026-01-23 | Completed | 2026-01-30 |  | R.K . Enterprises | C | 2026-02-02
95 | 76/6 | A+1.5 | DFR | 2026-01-20 | Completed | 2026-01-31 |  | Shree Khatushyam
96 | 129A/4 | A+6 | DFR | 2026-01-23 | Completed | 2026-01-31 |  | R.K . Enterprises | C | 2026-02-03
97 | 136/3 | A+3 | DFR | 2026-01-27 | Completed | 2026-01-31 |  | Jai Shri Ram Enterprises
98 | 82/2 | A+7.5 | WFR | 2026-01-27 | Completed | 2026-02-02 |  | Afflux Construction | C | 2026-02-04
99 | 127/4 | A+3 | WFR | 2026-01-20 | Completed | 2026-02-03 |  | B.L Construction | C | 2026-04-17
100 | 129A/10 | A+1.5 | DFR | 2026-01-30 | Completed | 2026-02-05 |  | R.K . Enterprises
101 | 82/3 | A+9 | WET | 2026-01-31 | Completed | 2026-02-08 |  | Afflux Construction | C | 2026-02-09
102 | 127/1 | A+3 | DFR | 2026-01-30 | Completed | 2026-02-09 |  | B.L Construction | C | 2026-02-10
103 | 129A/3 | A+3 | DFR | 2026-02-07 | Completed | 2026-02-11 |  | R.K . Enterprises | C | 2026-02-13
104 | 70/3 | A-3 | DFR | 2026-02-06 | Completed | 2026-02-13 |  | Afflux Construction | C | 2026-02-19
105 | 127/2 | A+0 | DFR | 2026-02-06 | Completed | 2026-02-13 |  | B.L Construction | C | 2026-02-14
106 | 129A/6 | A+9 | WFR | 2026-01-11 | Completed | 2026-02-16 |  | R.K . Enterprises | C | 2026-02-17
107 | 121/10 | A+9 | DFR | 2026-02-11 | Completed | 2026-02-17 |  | B.L Construction | C | 2026-02-27
108 | 70/1 | A+4.5 | DFR | 2026-02-06 | Completed | 2026-02-23 |  | Afflux Construction | C | 2026-02-24
109 | 125/1 | A+3 | WFR | 2026-02-17 | Completed | 2026-02-28 |  | B.L Construction
110 | 126/7 | A+0 | DFR | 2026-02-17 | Completed | 2026-03-03 |  | B.L Construction | C | 2026-03-10
111 | 70/2 | A+9 | WFR | 2026-02-13 | Completed | 2026-03-07 |  | Afflux Constrcutoin | C | 2026-03-08
112 | 124/5 | A+6 | DFR | 2026-02-08 | Completed | 2026-03-14 |  | B.L Construction
113 | 76/5 | A+9 | DFR | 2026-03-12 | Completed | 2026-03-21 |  | Afflux Constrcutoin | C | 2026-03-23
114 | 88/2 | A+0 | DFR | 2026-02-23 | Completed | 2026-03-30 |  | Afflux Constrcutoin | C | 2026-04-04
115 | 88/1 | A+3 | DFR | 2026-03-22 | Completed | 2026-04-02 |  | Afflux Construction | C | 2026-04-12
116 | 127/3 | A+0 | DFR | 2026-03-06 | Completed | 2026-04-03 |  | Jai Shree Ram
117 | 87/4 | A+0 | DFR | 2026-03-29 | Completed | 2026-04-08 |  | Afflux Construction | C | 2026-04-22
118 | 124/0 | B2+0 | Wet Paddy | 2026-03-16 | Completed | 2026-04-08 |  | B.L Construction | C | 2026-04-09
119 | 102/11 | A+9 | Wet Paddy | 2026-03-24 | Completed | 2026-04-11 |  | Dhanraj | C | 2026-04-13
120 | 139/4 | A+0 | DFR | 2026-03-18 | Completed | 2026-04-11 |  | Jai Shree Ram
121 | 69/2 | A+0 | DFR | 2026-03-17 | Completed | 2026-04-13 |  | Kalyan Singh | C | 2026-04-17
122 | 87/5 | A+3 | DFR | 2026-04-06 | Completed | 2026-04-14 |  | Afflux Construction | C | 2026-04-19
123 | 121/9 | A+0 | DFR | 2026-04-03 | Completed | 2026-04-15 |  | B.L Construction
124 | 71/1 | A+3 | WFR | 2026-03-14 | Completed | 2026-04-18 |  | Sohan Enterprises | C | 2026-04-21
125 | 87/2 | A+0 | DFR | 2026-04-06 | Completed | 2026-04-18 |  | Afflux Construction | C | 2026-04-27
126 | 69/1 | A+0 | DFR | 2026-03-25 | Completed | 2026-04-21 |  | Kalyan Singh | C | 2026-04-23
127 | 109/8 | A+3 | DFR | 2026-04-07 | Completed | 2026-04-22 |  | B.L Construction
128 | 125/0 | B2+3 | DFR | 2026-03-18 | Completed | 2026-04-23 |  | BL. Construction
129 | 71/2 | A-3 | DFR | 2026-03-18 | Completed | 2026-04-24 |  | Soham Entp | C | 2026-04-27
130 | 136/0 | C2+9 | Wet Paddy | 2026-03-28 | Completed | 2026-04-24 |  | Jai Shree Ram
131 | 87/3 | A+3 | DFR | 2026-04-18 | Completed | 2026-04-25 |  | Afflux Construction | C | 2026-05-03
132 | 69/3 | A+0 | DFR | 2026-04-07 | Completed | 2026-04-28 |  | Kalyan Singh | C | 2026-04-28
133 | 71/3 | A+0 | DFR | 2026-04-21 | Completed | 2026-04-30 |  | Soham Entp | C | 2026-05-02
134 | 88/3 | A-3 | DFR | 2026-04-18 | Completed | 2026-04-30 |  | Afflux Construction | C | 2026-05-20
135 | 127/0 | B1+0 | DFR | 2026-03-20 | Completed | 2026-04-30 |  | B.L Construction
136 | 139/0 | B2+0 | Wet Paddy | 2026-03-30 | Completed | 2026-04-30 |  | Jai Shree Ram | C | 2026-05-02
137 | 71/4 | A-3 | DFR | 2026-04-23 | Completed | 2026-05-04 |  | Soham Entp | C | 2026-05-04
138 | 108/0 | C1+9 | DFR | 2026-04-24 | Completed | 2026-05-04 |  | BL. Construction
139 | 139/1 | A+3 | DFR | 2026-04-23 | Completed | 2026-05-04 |  | Jai Shree Ram
140 | 107/0 | C2+3 | DFR | 2026-03-27 | Completed | 2026-05-06 |  | Dhanraj Construction
141 | 69/4 | A+0 | DFR | 2026-05-01 | Completed | 2026-05-08 |  | Soham Entp | C | 2026-05-23
142 | 126/0 | C2+0 | DFR | 2026-04-29 | Completed | 2026-05-12 |  | BL. Construction
143 | 88/0 | C2+3 | DFR | 2026-04-25 | Completed | 2026-05-15 |  | Afflux
144 | 135/0 | B2+9 | Wet Paddy | 2026-04-16 | Completed | 2026-05-19 |  | Jai Shree Ram
145 | 71/5 | A+3 | WFR | 2026-05-04 | Completed | 2026-05-21 |  | Soham Entp | C | 2026-05-31
146 | 102/10 | A+0 | Wet Paddy | 2026-04-21 | Completed | 2026-05-23 |  | Sawariya
147 | 109/0 | B2+0 | Wet | 2026-04-19 | Completed | 2026-05-23 |  | BL. Construction
148 | 123/0 | B2+0 | DFR | 2026-05-05 | Completed | 2026-05-23 |  | BL. Construction
149 | 88/5 | B1+0 | DFR | 2026-04-30 | Completed | 2026-05-24 |  | Afflux | C | 2026-06-02
150 | 102/5 | A+0 | WET PADDY | 2026-04-16 | Completed | 2026-05-26 |  | M./S Sanjay kumar
151 | 72/1 | A+9 | DFR | 2026-05-19 | Completed | 2026-05-27 |  | Soham Entp
152 | 88/4 | B1+3 | Wet Paddy | 2026-05-02 | Completed | 2026-05-29 |  | Afflux | C | 2026-06-02
153 | 132/2 | A+0 | DFR | 2026-05-05 | Completed | 2026-05-30 |  | Jai Shree Ram
154 | 76/4 | A+0 | DFR | 2026-05-21 | Completed | 2026-05-31 |  | Soham Entp
155 | 64/5 | A+3 | Wet Paddy | 2026-05-25 | Completed | 2026-06-01 |  | Afflux
156 | 104/0 | B2+3 | Wet Paddy | 2026-04-18 | Completed | 2026-06-01 |  | Sawariya | C | 2026-06-02
157 | 116/0 | C1+3 | DFR | 2026-05-24 | Completed | 2026-06-03 |  | B.L Construction
158 | 70/0 | C2-3 | DFR | 2026-05-03 | Completed |  |  | Soham Entp
159 | 90/0 | C1+0 | DFR | 2026-05-17 | Completed |  |  | Afflux
160 | 64/4 | A+0 | DFR | 2026-05-25 | Completed |  |  | Afflux
161 | 104/1 | A+9 | WET PADDY | 2026-05-29 | Completed |  |  | Sanjay Kumar
162 | 65/1 | A+0 | DFR | 2026-06-03 | Completed |  |  | Afflux
163 | 77/0 | B2+0 | DFR | 2026-06-03 | Completed |  |  | Soham Entp
164 | 116/3 | #REF! | FS | 2025-12-13 | Completed | 2025-12-24 |  |  | 0
Formulas:
Starting Date = VLOOKUP([Location No.],FDN!B3:F166,5,0)
Completion Date = VLOOKUP([Location No.],FDN!B3:M166,12,0)

## Erection
±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (Part- 6) Erection
Sl. No. | Location Number | Type of Tower |  | Starting Date | Tower Weight (MT) | Status | Completion Date | Gang Name | Manpower | Hindarnce Days | Remarks | Tackweldng Status | Tackwelding start date | Tackwelding Completion date | Sub Contractor name
1 | 125/2 | A+3 | A+3 | 2026-02-18 | 24.041 | C | 2026-02-22 | M/S Ratani Devi | 18
2 | 122/2 | A+0 | A+0 | 2026-02-25 | 22.9237 | C | 2026-02-28 | M/S Ratani Devi | 18
3 | 130/1 | A+0 | A+0 | 2026-02-22 | 22.9237 | C | 2026-02-28 | M/S Jwala | 35
4 | 126/10 | A+0 | A+0 | 2026-03-03 | 22.9237 | C | 2026-03-07 | M/s Ratani Devi | 23
5 | 129A/3 | A+3 | A+3 | 2026-03-01 | 24.041 | C | 2026-03-10 | M/s Jwala | 23
6 | 126/9 | A+3 | A+3 | 2026-03-01 | 24.041 | C | 2026-03-11 | M/s Ratani Devi | 38
7 | 129A/4 | A+6 | A+6 | 2026-03-11 | 26.7642 | C | 2026-03-14 | M/s Jwala | 35
8 | 126/5 | A+3 | A+3 | 2025-03-01 | 24.041 | C | 2026-03-15 | M/s Ratani Devi | 35
9 | 126/4 | A+0 | A+0 | 2026-03-15 | 22.9237 | C | 2026-03-19 | M/s Ratani Devi | 35
10 | 130/2 | A+6 | A+6 | 2026-03-15 | 26.7642 | C | 2026-03-19 | M/s Jwala | 18
11 | 130/3 | A+3 | A+3 | 2026-03-19 | 24.041 | C | 2026-03-22 | M/s Jwala | 23
12 | 126/3 | A+3 | A+3 | 2026-03-19 | 24.041 | C | 2026-03-23 | M/s Ratani Devi | 19
13 | 134/2 | A+3 | A+3 | 2026-03-23 | 24.041 | C | 2026-03-27 | M/s Jwala | 18
14 | 125/3 | A+6 | A+6 | 2026-03-23 | 26.7642 | C | 2026-03-28 | M/s Ratani Devi | 24
15 | 134/3 | A+6 | A+6 | 2026-03-27 | 26.7642 | C | 2026-03-30 | M/s Jwala | 20
16 | 124/4 | A+3 | A+3 | 2026-03-28 | 24.041 | C | 2026-04-02 | M/S Ratani Devi | 21
17 | 134/4 | A+3 | A+3 | 2026-03-31 | 24.041 | C | 2026-04-03 | M/s Jwala | 35
18 | 134/8 | A+3 | A+3 | 2026-04-04 | 24.041 | C | 2026-04-07 | M/s Jwala | 21
19 | 134/9 | A+0 | A+0 | 2026-04-07 | 22.9237 | C | 2026-04-11 | M/s Jwala | 35
20 | 134/7 | A+3 | A+3 | 2026-04-12 | 24.041 | C | 2026-04-15 | M/s Jwala | 35
21 | 134/5 | A+0 | A+0 | 2026-04-15 | 22.9237 | C | 2026-04-19 | M/s Jwala | 35
22 | 136/2 | A+3 | A+3 | 2026-04-19 | 24.041 | C | 2026-04-23 | M/s Jwala | 20
23 | 136/1 | A+0 | A+0 | 2026-04-24 | 22.9237 | C | 2026-04-28 | M/s Jwala Singh | 22
24 | 136/3 | A+3 | A+3 | 2026-04-28 | 24.041 | C | 2026-05-02 | M/s Jwala Singh | 20
25 | 102/7 | A+0 | A+0 | 2026-04-28 | 22.9237 | C | 2026-05-04 | M/s Aravali Infrastructure | 32
26 | 116/2 | A+3 | A+3 | 2026-04-28 | 24.041 | C | 2026-05-04 | M/s Amrendra Prasad | 42
27 | 121/2 | A+6 | A+6 | 2026-04-28 | 26.7642 | C | 2026-05-04 | M/S Gagan Entp. | 33
28 | 136/4 | A+0 | A+0 | 2026-05-02 | 22.9237 | C | 2026-05-04 | M/s Jwala Singh | 19
29 | 121/1 | A+0 | A+0 | 2026-05-04 | 22.9237 | C | 2026-05-08 | M/S Gagan Entp. | 20
30 | 136/5 | A+0 | A+0 | 2026-05-04 | 22.9237 | C | 2026-05-08 | M/s Jwala Singh | 20
31 | 116/1 | A+3 | A+3 | 2026-05-04 | 24.041 | C | 2026-05-09 | M/s Amrendra Prasad | 28
32 | 109/1 | A+3 | A+3 | 2026-05-03 | 24.041 | C | 2026-05-10 | M/s Mukesh Kumar Verma | 42
33 | 121/4 | A+0 | A+0 | 2026-05-08 | 22.9237 | C | 2026-05-12 | M/S Gagan Entp. | 22
34 | 139/2 | A+0 | A+0 | 2026-05-08 | 22.9237 | C | 2026-05-12 | M/s Jwala Singh | 22
35 | 111/1 | A+0 | A+0 | 2026-05-09 | 22.9237 | C | 2026-05-14 | M/s Amrendra Prasad | 26
36 | 139/5 | A+0 | A+0 | 2026-05-09 | 22.9237 | C | 2026-05-15 | M/s Jwala Singh | 35
37 | 109/2 | A+0 | A+0 | 2026-05-10 | 22.9237 | C | 2026-05-16 | M/s Mukesh Kumar Verma | 32
38 | 121/7 | A+0 | A+0 | 2026-05-12 | 22.9237 | C | 2026-05-16 | M/S Gagan Entp. | 18
39 | 111/2 | A+3 | A+3 | 2026-05-15 | 24.041 | C | 2026-05-18 | M/s Amrendra Prasad | 26
40 | 121/6 | A+0 | A+0 | 2026-01-16 | 22.9237 | C | 2026-05-18 | M/S Gagan Entp.
41 | 136/8 | A+0 | A+0 | 2026-05-16 | 22.9237 | C | 2026-05-18 | M/s Jwala Singh | 23
42 | 121/5 | A+0 | A+0 | 2026-05-18 | 22.9237 | C | 2026-05-20 | M/S Gagan Entp. | 24
43 | 109/5 | A+3 | A+3 | 2026-05-17 | 24.041 | C | 2026-05-21 | M/s Mukesh Kumar Verma | 32
44 | 139/1 | A+3 | A+3 | 2026-05-18 | 24.041 | C | 2026-05-21 | M/s Jwala Singh | 23
45 | 111/3 | A+0 | A+0 | 2026-05-18 | 22.9237 | C | 2026-05-22 | M/s Amrendra Prasad | 26
46 | 124/5 | A+6 | A+6 | 2026-05-21 | 26.7642 | C | 2026-05-23 | M/S Gagan Entp. | 35
47 | 125/1 | A+3 | A+3 | 2026-05-23 | 24.041 | C | 2026-05-25 | M/S Gagan Entp. | 24
48 | 111/4 | A+0 | A+0 | 2026-05-23 | 22.9237 | C | 2026-05-26 | M/s Amrendra Prasad | 32
49 | 109/6 | A+3 | A+3 | 2026-05-21 | 24.041 | C | 2026-05-28 | M/s Mukesh Kumar Verma | 26
50 | 125/0 | B2+3 | B+3 | 2026-05-26 | 31.6671 | C | 2026-05-29 | M/S Gagan Entp. | 23
51 | 136/0 | C2+9 | C+9 | 2206-05-22 | 42.1971 | C | 2026-05-29 | M/s Jwala Singh | 22
52 | 109/7 | A+3 | A+3 | 2026-05-21 | 24.041 | C | 2026-05-31 | M/s Mukesh Kumar Verma | 26
53 | 111/5 | A+6 | A+6 | 2026-05-27 | 26.7642 | C | 2026-06-01 | M/s Amrendra Prasad | 26
54 | 124/3 | A+9 | A+9 | 2026-05-30 | 27.9651 | C | 2026-06-02 | M/S Gagan Entp. | 25
55 | 123/1 | A+0 | A+0 | 2026-06-02 | 22.9237 | C | 2026-06-03 | M/S Gagan Entp. | 23
56 | 127/3 | A+0 | A+0 | 2026-05-30 | 22.9237 | C | 2026-06-03 | M/s Jwala | 24
57 | 124/2 | A+6 | A+6 | 2026-06-03 | 26.7642 | C | 2026-06-06 | M/S Gagan Entp. | 35
58 | 110/3 | A+0 | A+0 | 2026-06-01 | 22.9237 | C | 2026-06-07 | M/s Amrendra Prasad | 26
59 | 127/1 | A+3 | A+3 | 2026-06-03 | 24.041 | C | 2026-06-07 | M/s Jwala | 22
60 | 123/2 | A+3 | A+3 | 2026-06-06 | 24.041 | C | 2026-06-07 | M/S Gagan Entp.-2 | 23
61 | 108/1 | A+9 | A+9 | 2026-05-31 | 27.9651 | C | 2026-06-08 | M/s Mukesh Kumar Verma | 24
62 | 124/1 | A+6 | A+6 | 2026-06-07 | 26.7642 | C | 2026-06-11 | M/S Gagan Entp.-2 | 23
63 | 127/2 | A+0 | A+0 | 2026-06-07 | 22.9237 | C | 2026-06-11 | M/S Jwala Singh | 22
64 | 107/1 | A+0 | A+0 | 2026-06-08 | 22.9237 | C | 2026-06-12 | M/s Mukesh Kumar Verma | 24
65 | 123/0 | B2+0 | B+0 | 2026-06-10 | 30.2572 | C | 2026-06-13 | M/S Gagan Entp-3 | 26
66 | 123/3 | A+9 | A+9 | 2026-06-07 | 27.9651 | C | 2026-06-14 | M/S Gagan Entp.-2 | 26
67 | 126/7 | A+0 | A+0 | 2026-06-12 | 22.9237 | C | 2026-06-14 | M/S Jwala SIngh | 22
68 | 89/9 | A+0 | A+0 | 2026-06-08 | 22.9237 | C | 2026-06-15 | M/s Amrendra Prasad | 26
69 | 121/9 | A+0 | A+0 | 2026-06-13 | 22.9237 | C | 2026-06-15 | M/S Gagan Entp-2 | 26
70 | 107/4 | A+3 | A+3 | 2026-06-12 | 24.041 | C | 2026-06-17 | M/s Mukesh Kumar Verma | 24
71 | 89/6 | A+0 | A+0 | 2026-06-15 | 22.9237 | C | 2026-06-19 | M/s Amrendra Prasad | 26
72 | 116/0 | C1+3 | C+3 | 2026-06-16 | 36.1787 | C | 2026-06-19 | M/S Gagan Entp-2 | 26
73 | 127/0 | B1+0 | B+0 | 2026-06-14 | 30.2572 | C | 2026-06-21 | M/S Jwala Singh | 22
74 | 89/7 | A+0 | A+0 | 2026-06-20 | 22.9237 | C | 2026-06-25 | M/s Amrendra Prasad | 26
75 | 116/3 | A+9 | A+9 | 2206-06-20 | 27.9651 | C | 2026-06-25 | M/S Jwala | 26
76 | 108/0 | C1+9 | C+3 | 2026-06-18 | 36.1787 | C | 2026-06-26 | M/s Mukesh Kumar Verma | 24
77 | 129A/5 | A+9 | A+9 | 2026-06-22 | 27.9651 | C | 2026-06-26 | M/s Gagan Entp. | 22
78 | 89/5 | A+3 | A+3 | 2026-06-25 | 24.041 | WIP | 2026-06-26 | M/s Amrendra Prasad | 26
79 | 103/2 | A+0 | A+0 | 2026-03-25 | 22.9237 | WIP |  | M/S Jwala | 22
80 | 108/4 | A+3 | A+3 | 2026-06-26 | 24.041 | WIP |  | M/s Mukesh Kumar Verma | 24

## Erection Completed (hidden)
SL No. | Location No. | Tower Type | Starting Date | Tower Weight | Status | Completion Date | Gang Name | Gang Strength | Number of Fitters | Tower Tightening | Remark
1 | 125/2 | A+3 | A+3 | 46078 | 24.041 | C | 46075 | 32 |  | Yes
2 | 122/2 | A+0 | A+0 | 46075 | 22.9237 | C | 46081 | 24 |  | Yes
3 | 130/1 | A+0 | A+0 | 46084 | 22.9237 | C | 46081 | 42 |  | Yes
4 | 126/10 | A+0 | A+0 | 46082 | 22.9237 | C | 46088 | 32 |  | Yes
5 | 129A/3 | A+3 | A+3 | 46082 | 24.041 | C | 46091 | 32 |  | Yes
6 | 126/9 | A+3 | A+3 | 46092 | 24.041 | C | 46092 | 26 |  | Yes
7 | 129A/4 | A+6 | A+6 | 45717 | 26.7642 | C | 46095 | 26 |  | Yes
8 | 126/5 | A+3 | A+3 | 46096 | 24.041 | C | 46096 | 26 |  | Yes
9 | 126/4 | A+0 | A+0 | 46096 | 22.9237 | C | 46100 | 26 |  | Yes
10 | 130/2 | A+6 | A+6 | 46100 | 26.7642 | C | 46100 | 26 |  | Yes
11 | 130/3 | A+3 | A+3 | 46100 | 24.041 | C | 46103 | 26 |  | Yes
12 | 126/3 | A+3 | A+3 | 46104 | 24.041 | C | 46104 | 32 |  | Yes
13 | 134/2 | A+3 | A+3 | 46104 | 24.041 | C | 46108 | 26 |  | Yes
14 | 125/3 | A+6 | A+6 | 46108 | 26.7642 | C | 46109 | 28 |  | Yes
15 | 134/3 | A+6 | A+6 | 46109 | 26.7642 | C | 46111 | 42 |  | Yes
16 | 124/4 | A+3 | A+3 | 46112 | 24.041 | C | 46114 | 33 |  | Yes
17 | 134/4 | A+3 | A+3 | 46116 | 24.041 | C | 46115 | 22 |  | Yes
18 | 134/8 | A+3 | A+3 | 46119 | 24.041 | C | 46119 | 24 |  | Yes
19 | 134/9 | A+0 | A+0 | 46124 | 22.9237 | C | 46123 |  |  | Yes
20 | 134/7 | A+3 | A+3 | 46127 | 24.041 | C | 46127 | 18 |  | Yes
21 | 134/5 | A+0 | A+0 | 46131 | 22.9237 | C | 46131 | 18 |  | Yes
22 | 136/2 | A+3 | A+3 | 46136 | 24.041 | C | 46135 | 23 |  | Yes
23 | 136/1 | A+0 | A+0 | 46140 | 22.9237 | C | 46140 | 35 |  | Yes
24 | 136/3 | A+3 | A+3 | 46140 | 24.041 | C | 46144 | 25 |  | Yes
25 | 102/7 | A+0 | A+0 | 46140 | 22.9237 | C | 46146 | 21 |  | Yes
26 | 116/2 | A+3 | A+3 | 46140 | 24.041 | C | 46146 | 35 |  | Yes
27 | 121/2 | A+6 | A+6 | 46144 | 26.7642 | C | 46146 | 23 |  | Yes
28 | 136/4 | A+0 | A+0 | 46146 | 22.9237 | C | 46146 | 24 |  | Yes
29 | 121/1 | A+0 | A+0 | 46146 | 22.9237 | C | 46150 | 18 |  | Yes
30 | 136/5 | A+0 | A+0 | 46146 | 22.9237 | C | 46150 | 24 |  | Yes
31 | 116/1 | A+3 | A+3 | 46145 | 24.041 | C | 46151 | 19 |  | Yes
32 | 109/1 | A+3 | A+3 | 46150 | 24.041 | C | 46152 | 35 |  | Yes
33 | 121/4 | A+0 | A+0 | 46150 | 22.9237 | C | 46154 | 35 |  | Yes
34 | 139/2 | A+0 | A+0 | 46151 | 22.9237 | C | 46154 | 38 |  | Yes
35 | 111/1 | A+0 | A+0 | 46151 | 22.9237 | C | 46156 | 23 |  | Yes
36 | 139/5 | A+0 | A+0 | 46152 | 22.9237 | C | 46157 | 22 |  | Yes
37 | 109/2 | A+0 | A+0 | 46154 | 22.9237 | C | 46158 | 23 |  | Yes
38 | 121/7 | A+0 | A+0 | 46157 | 22.9237 | C | 46158 | 35 |  | Yes
39 | 111/2 | A+3 | A+3 | 46038 | 24.041 | C | 46160 | 35 |  | Yes
40 | 121/6 | A+0 | A+0 | 46158 | 22.9237 | C | 46160 | 18 |  | Yes
41 | 136/8 | A+0 | A+0 | 46160 | 22.9237 | C | 46160 | 20 |  | Yes
42 | 121/5 | A+0 | A+0 | 46159 | 22.9237 | C | 46162 | 35 |  | Yes
43 | 109/5 | A+3 | A+3 | 46160 | 24.041 | C | 46163 | 35 |  | Yes
44 | 139/1 | A+3 | A+3 | 46160 | 24.041 | C | 46163 | 35 |  | Yes
45 | 111/3 | A+0 | A+0 | 46163 | 22.9237 | C | 46164 | 22 |  | Yes
46 | 124/5 | A+6 | A+6 | 46165 | 26.7642 | C | 46165 | 20 |  | Yes
47 | 125/1 | A+3 | A+3 | 46165 | 24.041 | C | 46167 | 23 |  | Yes
48 | 111/4 | A+0 | A+0 | 46163 | 22.9237 | C | 46168 | 23 |  | Yes
49 | 109/6 | A+3 | A+3 | 46168 | 24.041 | C | 46170 | 20 |  | Yes
50 | 125/0 | B2+3 | B+3 | 111907 | 31.6671 | C | 46171 | 35 |  | Yes
51 | 136/0 | C2+9 | C+9 | 46163 | 42.1971 | C | 46171 | 20 |  | Yes
52 | 109/7 | A+3 | A+3 | 46169 | 24.041 | C | 46173 | 35 |  | Yes
53 | 111/5 | A+6 | A+6 | 46172 | 26.7642 | C | 46174 | 22 |  | Yes
54 | 124/3 | A+9 | A+9 | 46175 | 27.9651 | C | 46175 | 35 |  | Yes
55 | 123/1 | A+0 | A+0 | 46172 | 22.9237 | C | 46176 | 26 |  | Yes
56 | 127/3 | A+0 | A+0 | 46173 | 22.9237 | C | 46176 | 21 |  | Yes
57 | 108/1 | A+9 | A+9 | 46174 | 27.9651 | C | 46181 | 24 |  | Yes
58 | 110/3 | A+0 | A+0 | 46180 | 22.9237 | C | 46180 | 22 |  | Yes
59 | 123/3 | A+9 | A+9 | 46176 | 27.9651 | C | 46187 | 20 |  | Yes
60 | 124/2 | #N/A | A+6 | 46176 | 26.7642 |  | 46179 | 19 |  | Yes
61 | 127/1 | #N/A | A+3 | 22.925 | 24.041 |  | 46180 | 35 |  | Yes

## Erection Compiled (hidden)
SL No. | Location No. | Tower Type | Starting Date | Tower Weight | Status | Completion Date | Gang Name | Gang Strength | Number of Fitters | Tower Tightening | Remark
1 | 117/1 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
2 | 117/2 | DA+6 | #N/A | 44.7941 | #N/A | #N/A | #N/A | #N/A |  | #N/A
3 | 118/0 | DB2+0 | #N/A | 54.4178 | #N/A | #N/A | #N/A | #N/A |  | #N/A
4 | 119/0 | DD60+0 | #N/A | 80.408 | #N/A | #N/A | #N/A | #N/A |  | #N/A
5 | 119/1 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
6 | 119/2 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
7 | 119/3 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
8 | 120/0 | DD60+3 | #N/A | 84.2993 | #N/A | #N/A | #N/A | #N/A |  | #N/A
9 | 120/1 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
10 | 120/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
11 | 120/3 | DA+6 | #N/A | 44.7941 | #N/A | #N/A | #N/A | #N/A |  | #N/A
12 | 120/4 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
13 | 120/5 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
14 | 120/6 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
15 | 120/7 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
16 | 121/0 | DB2+9 | #N/A | 65.7565 | #N/A | #N/A | #N/A | #N/A |  | #N/A
17 | 121/1 | DB1+25 | A+0 | 91.0555 | Completed | C | 2026-05-08 | 18 |  | Yes
18 | 121/2 | DA+9 | A+6 | 46.6894 | Completed | C | 2026-05-04 | 23 |  | Yes
19 | 121/3 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
20 | 121/4 | DA+0 | A+0 | 37.7963 | Completed | C | 2026-05-12 | 35 |  | Yes
21 | 121/5 | DA-3 | A+0 | 36.0448 | Completed | C | 2026-05-20 | 35 |  | Yes
22 | 121/6 | DA+0 | A+0 | 37.7963 | Completed | C | 2026-05-18 | 18 |  | Yes
23 | 121/7 | DB1+0 | A+0 | 54.4178 | Completed | C | 2026-05-16 | 35 |  | Yes
24 | 121/8 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
25 | 121/9 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
26 | 121/10 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
27 | 121/11 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
28 | 124/0 | DD45+3 | #N/A | 75.4524 | #N/A | #N/A | #N/A | #N/A |  | #N/A
29 | 124/1 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
30 | 124/2 | DA+0 | A+6 | 37.7963 | Completed | 0 | 2026-06-06 | 19 |  | Yes
31 | 124/3 | DA+0 | A+9 | 37.7963 | Completed | C | 2026-06-02 | 35 |  | Yes
32 | 125/0 | DC2+3 | B+3 | 66.2679 | Completed | C | 2026-05-29 | 35 |  | Yes
33 | 125/1 | DA+9 | A+3 | 46.6894 | Completed | C | 2026-05-25 | 23 |  | Yes
34 | 125/2 | DA+9 | A+3 | 46.6894 | Completed | C | 2026-02-22 | 32 |  | Yes
35 | 126/0 | DD45+3 | #N/A | 75.4524 | #N/A | #N/A | #N/A | #N/A |  | #N/A
36 | 126/1 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
37 | 126/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
38 | 126/3 | DA+0 | A+3 | 37.7963 | Completed | C | 2026-03-23 | 32 |  | Yes
39 | 127/0 | DB2+0 | #N/A | 54.4178 | #N/A | #N/A | #N/A | #N/A |  | #N/A
40 | 127/1 | DA-3 | A+3 | 36.0448 | Completed | 0 | 2026-06-07 | 35 |  | Yes
41 | 127/2 | DB1+9 | #N/A | 65.7565 | #N/A | #N/A | #N/A | #N/A |  | #N/A
42 | 128/0 | DD60+25 (4X2MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
43 | 129/0 | DD45+25 | #N/A | 122.8048 | #N/A | #N/A | #N/A | #N/A |  | #N/A
44 | 130/0 | DD45+25 | #N/A | 122.8048 | #N/A | #N/A | #N/A | #N/A |  | #N/A
45 | 131/0 | DD60+9 (4X7MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
46 | 131/1 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
47 | 131/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
48 | 131/3 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
49 | 131/4 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
50 | 131/5 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
51 | 132/0 | DB2+0 | #N/A | 54.4178 | #N/A | #N/A | #N/A | #N/A |  | #N/A
52 | 132/1 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
53 | 132/2 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
54 | 132/3 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
55 | 133/0 | DC1+0 | #N/A | 64.2538 | #N/A | #N/A | #N/A | #N/A |  | #N/A
56 | 133/1 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
57 | 133/2 | DB1+0 | #N/A | 54.4178 | #N/A | #N/A | #N/A | #N/A |  | #N/A
58 | 133/3 | DB1+0 | #N/A | 54.4178 | #N/A | #N/A | #N/A | #N/A |  | #N/A
59 | 133/4 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
60 | 134/0 | DD45+0 | #N/A | 72.2376 | #N/A | #N/A | #N/A | #N/A |  | #N/A
61 | 135/0 | DD60+3 | #N/A | 84.2993 | #N/A | #N/A | #N/A | #N/A |  | #N/A
62 | 136/0 | DD60+6 | C+9 | 94.4077 | Completed | C | 2026-05-29 | 20 |  | Yes
63 | 136/1 | DB1+9 | A+0 | 65.7565 | Completed | C | 2026-04-28 | 35 |  | Yes
64 | 137/0 | DB2+3 | #N/A | 56.8632 | #N/A | #N/A | #N/A | #N/A |  | #N/A
65 | 137/1 | DA+6 | #N/A | 44.7941 | #N/A | #N/A | #N/A | #N/A |  | #N/A
66 | 137/2 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
67 | 138/0 | DC2+6 | #N/A | 74.6321 | #N/A | #N/A | #N/A | #N/A |  | #N/A
68 | 139/0 | DD45+6 | #N/A | 85.2305 | #N/A | #N/A | #N/A | #N/A |  | #N/A
69 | 139/1 | DA+6 | A+3 | 44.7941 | Completed | C | 2026-05-21 | 35 |  | Yes
70 | 139/2 | DB2+0 | A+0 | 54.4178 | Completed | C | 2026-05-12 | 38 |  | Yes
71 | 139/3 | DB1+0 | #N/A | 54.4178 | #N/A | #N/A | #N/A | #N/A |  | #N/A
72 | 140/0 | DD60+25 | #N/A | 141.874 | #N/A | #N/A | #N/A | #N/A |  | #N/A
73 | 141/0 | DD60+25 | #N/A | 141.874 | #N/A | #N/A | #N/A | #N/A |  | #N/A
74 | 141/1 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
75 | 141/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
76 | 141/3 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
77 | 141/4 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
78 | 141/5 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
79 | 141/6 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
80 | 142/0 | DC1+9 | #N/A | 77.7181 | #N/A | #N/A | #N/A | #N/A |  | #N/A
81 | 143/0 | DD60+18 | #N/A | 129.341 | #N/A | #N/A | #N/A | #N/A |  | #N/A
82 | 144/0 | DD60+18 | #N/A | 129.341 | #N/A | #N/A | #N/A | #N/A |  | #N/A
83 | 145/0 | DD45+9 | #N/A | 89.1428 | #N/A | #N/A | #N/A | #N/A |  | #N/A
84 | 145/1 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
85 | 145/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
86 | 145/3 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
87 | 145/4 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
88 | 145/5 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
89 | 145/6 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
90 | 145/7 | DB1+0 | #N/A | 54.4178 | #N/A | #N/A | #N/A | #N/A |  | #N/A
91 | 147/0 | DD60+25 | #N/A | 141.874 | #N/A | #N/A | #N/A | #N/A |  | #N/A
92 | 148/0 | DD60+25 | #N/A | 141.874 | #N/A | #N/A | #N/A | #N/A |  | #N/A
93 | 148/1 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
94 | 148/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
95 | 148/3 | DA+6 | #N/A | 44.7941 | #N/A | #N/A | #N/A | #N/A |  | #N/A
96 | 148/4 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
97 | 148/5 | DB1+3 | #N/A | 56.8632 | #N/A | #N/A | #N/A | #N/A |  | #N/A
98 | 149/0 | DD60+25 | #N/A | 141.874 | #N/A | #N/A | #N/A | #N/A |  | #N/A
99 | 150/0 | DD60+25 | #N/A | 141.874 | #N/A | #N/A | #N/A | #N/A |  | #N/A
100 | 150/1 | DB1+0 | #N/A | 54.4178 | #N/A | #N/A | #N/A | #N/A |  | #N/A
101 | 151/0 | DD60+6 | #N/A | 94.4077 | #N/A | #N/A | #N/A | #N/A |  | #N/A
102 | 150A/0 | DD60+18 | #N/A | 129.341 | #N/A | #N/A | #N/A | #N/A |  | #N/A
103 | 152/0 | DD60+3 | #N/A | 84.2993 | #N/A | #N/A | #N/A | #N/A |  | #N/A
104 | 153/0 | DD60+3 | #N/A | 84.2993 | #N/A | #N/A | #N/A | #N/A |  | #N/A
105 | 153/1 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
106 | 153/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
107 | 153A/0 | DD45+9 | #N/A | 89.1428 | #N/A | #N/A | #N/A | #N/A |  | #N/A
108 | 154/0 | DD60+9 | #N/A | 98.8356 | #N/A | #N/A | #N/A | #N/A |  | #N/A
109 | 155/0 | DD60+18 | #N/A | 129.341 | #N/A | #N/A | #N/A | #N/A |  | #N/A
110 | 156/0 | DD45+18 | #N/A | 112.4202 | #N/A | #N/A | #N/A | #N/A |  | #N/A
111 | 156/1 | DB2+9 | #N/A | 65.7565 | #N/A | #N/A | #N/A | #N/A |  | #N/A
112 | 157/0 | CDDN+41 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
113 | 158/0 | CDDN+41 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
114 | 159/0 | DD60+9 | #N/A | 98.8356 | #N/A | #N/A | #N/A | #N/A |  | #N/A
115 | 160/0 | DC2+0 | #N/A | 64.2538 | #N/A | #N/A | #N/A | #N/A |  | #N/A
116 | 161/0 | DB1+3 | #N/A | 56.8632 | #N/A | #N/A | #N/A | #N/A |  | #N/A
117 | 162/0 | DD60+25 | #N/A | 141.874 | #N/A | #N/A | #N/A | #N/A |  | #N/A
118 | 163/0 | DD60+30 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A |  | #N/A
119 | 163/1 | DB1+6 | #N/A | 63.509 | #N/A | #N/A | #N/A | #N/A |  | #N/A
120 | 164/0 | DC2+6 | #N/A | 74.6321 | #N/A | #N/A | #N/A | #N/A |  | #N/A
121 | 165/0 | DB1+25 | #N/A | 91.0555 | #N/A | #N/A | #N/A | #N/A |  | #N/A
122 | 165/1 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
123 | 165/2 | DA+6 | #N/A | 44.7941 | #N/A | #N/A | #N/A | #N/A |  | #N/A
124 | 165/3 | DA+6 | #N/A | 44.7941 | #N/A | #N/A | #N/A | #N/A |  | #N/A
125 | 165/4 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
126 | 165/5 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
127 | 165/6 | DCT+0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
128 | 165/7 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
129 | 166/0 | DD60+0 | #N/A | 80.408 | #N/A | #N/A | #N/A | #N/A |  | #N/A
130 | 167/0 | DD60+9 | #N/A | 98.8356 | #N/A | #N/A | #N/A | #N/A |  | #N/A
131 | 168/0 | DD60+30 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A |  | #N/A
132 | 169/0 | DD60+25 | #N/A | 141.874 | #N/A | #N/A | #N/A | #N/A |  | #N/A
133 | 170/0 | DD60+6 | #N/A | 94.4077 | #N/A | #N/A | #N/A | #N/A |  | #N/A
134 | 171/0 | DB1+18 | #N/A | 82.2388 | #N/A | #N/A | #N/A | #N/A |  | #N/A
135 | 172/0 | DD45+9 | #N/A | 89.1428 | #N/A | #N/A | #N/A | #N/A |  | #N/A
136 | 172/1 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
137 | 173/0 | DC2+18 | #N/A | 97.9336 | #N/A | #N/A | #N/A | #N/A |  | #N/A
138 | 174/0 | DD60+9 | #N/A | 98.8356 | #N/A | #N/A | #N/A | #N/A |  | #N/A
139 | 174/1 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
140 | 174/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
141 | 174/3 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
142 | 174/4 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
143 | 174/5 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
144 | 174/6 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
145 | 175/0 | DC2+6 | #N/A | 74.6321 | #N/A | #N/A | #N/A | #N/A |  | #N/A
146 | 175/1 | DB1+9 | #N/A | 65.7565 | #N/A | #N/A | #N/A | #N/A |  | #N/A
147 | 176/0 | DD45+0 | #N/A | 72.2376 | #N/A | #N/A | #N/A | #N/A |  | #N/A
148 | 176/1 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
149 | 176/2 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
150 | 177/0 | DD60+6 | #N/A | 94.4077 | #N/A | #N/A | #N/A | #N/A |  | #N/A
151 | 178/0 | DD60+6 | #N/A | 94.4077 | #N/A | #N/A | #N/A | #N/A |  | #N/A
152 | 178/1 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
153 | 178/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
154 | 178/3 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
155 | 179/0 | DB1+0 | #N/A | 54.4178 | #N/A | #N/A | #N/A | #N/A |  | #N/A
156 | 179/1 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
157 | 179/2 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
158 | 179/3 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
159 | 180/0 | DD45+0 | #N/A | 72.2376 | #N/A | #N/A | #N/A | #N/A |  | #N/A
160 | 180/1 | DA+3 | #N/A | 56.8632 | #N/A | #N/A | #N/A | #N/A |  | #N/A
161 | 180/2 | DB1+3 | #N/A | 56.8632 | #N/A | #N/A | #N/A | #N/A |  | #N/A
162 | 180/3 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
163 | 180/4 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
164 | 180/5 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
165 | 180/6 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
166 | 180/7 | DA+0 | #N/A | 141.874 | #N/A | #N/A | #N/A | #N/A |  | #N/A
167 | 182/0 | DD45+0 | #N/A | 72.2376 | #N/A | #N/A | #N/A | #N/A |  | #N/A
168 | 183/0 | DD60+0 | #N/A | 80.408 | #N/A | #N/A | #N/A | #N/A |  | #N/A
169 | 183/1 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
170 | 183/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
171 | 183/3 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
172 | 184/0 | DB1+18 | #N/A | 82.2388 | #N/A | #N/A | #N/A | #N/A |  | #N/A
173 | 185/0 | DD45+25 | #N/A | 122.8048 | #N/A | #N/A | #N/A | #N/A |  | #N/A
174 | 186/0 | DC1+18 | #N/A | 97.9336 | #N/A | #N/A | #N/A | #N/A |  | #N/A
175 | 187/0 | DC1+0 | #N/A | 64.2538 | #N/A | #N/A | #N/A | #N/A |  | #N/A
176 | 188/0 | DD60+35 | #N/A | 172.5195 | #N/A | #N/A | #N/A | #N/A |  | #N/A
177 | 189/0 | DD60+35 | #N/A | 172.5195 | #N/A | #N/A | #N/A | #N/A |  | #N/A
178 | 189/1 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
179 | 190/0 | DD60+9 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
180 | 191/0 | DD60+9 | #N/A | 98.8356 | #N/A | #N/A | #N/A | #N/A |  | #N/A
181 | 191/1 | DB1+3 | #N/A | 56.8632 | #N/A | #N/A | #N/A | #N/A |  | #N/A
182 | 192/0 | DC2+9 | #N/A | 77.7181 | #N/A | #N/A | #N/A | #N/A |  | #N/A
183 | 193/0 | DD60+30 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A |  | #N/A
184 | 194/0 | DD60+30 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A |  | #N/A
185 | 194/1 | DB1+9 | #N/A | 65.7565 | #N/A | #N/A | #N/A | #N/A |  | #N/A
186 | 195/0 | DC1+18 | #N/A | 97.9336 | #N/A | #N/A | #N/A | #N/A |  | #N/A
187 | 196/0 | DB2+18 | #N/A | 82.2388 | #N/A | #N/A | #N/A | #N/A |  | #N/A
188 | 196/1 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
189 | 196/2 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
190 | 197/0 | DB1+0 | #N/A | 54.4178 | #N/A | #N/A | #N/A | #N/A |  | #N/A
191 | 197/1 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
192 | 197/2 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
193 | 198/0 | DD60+6 | #N/A | 94.4077 | #N/A | #N/A | #N/A | #N/A |  | #N/A
194 | 199/0 | DD60+6 | #N/A | 94.4077 | #N/A | #N/A | #N/A | #N/A |  | #N/A
195 | 199/1 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
196 | 199/2 | DA+6 | #N/A | 44.7941 | #N/A | #N/A | #N/A | #N/A |  | #N/A
197 | 200/0 | DC2+0 | #N/A | 64.2538 | #N/A | #N/A | #N/A | #N/A |  | #N/A
198 | 200/1 | DA+6 | #N/A | 44.7941 | #N/A | #N/A | #N/A | #N/A |  | #N/A
199 | 201/0 | DC1+9 | #N/A | 77.7181 | #N/A | #N/A | #N/A | #N/A |  | #N/A
200 | 202/0 | DC2+18 | #N/A | 97.9336 | #N/A | #N/A | #N/A | #N/A |  | #N/A
201 | 203/0 | DD60+18 | #N/A | 129.341 | #N/A | #N/A | #N/A | #N/A |  | #N/A
202 | 203A/0 | DC1+9 | #N/A | 77.7181 | #N/A | #N/A | #N/A | #N/A |  | #N/A
203 | 203B/0 | DD60+0 | #N/A | 80.408 | #N/A | #N/A | #N/A | #N/A |  | #N/A
204 | 204/0 | DD60+25 | #N/A | 141.874 | #N/A | #N/A | #N/A | #N/A |  | #N/A
205 | 205/0 | DD60+25 (4X3MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
206 | 205/1 | DC1+9 | #N/A | 77.7181 | #N/A | #N/A | #N/A | #N/A |  | #N/A
207 | 205/2 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
208 | 206/0 | DC2+0 | #N/A | 64.2538 | #N/A | #N/A | #N/A | #N/A |  | #N/A
209 | 206/1 | DB1+6 | #N/A | 63.509 | #N/A | #N/A | #N/A | #N/A |  | #N/A
210 | 207/0 | DD60+25 | #N/A | 141.874 | #N/A | #N/A | #N/A | #N/A |  | #N/A
211 | 208/0 | DD45+35 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A |  | #N/A
212 | 209/0 | DD60+9 | #N/A | 98.8356 | #N/A | #N/A | #N/A | #N/A |  | #N/A
213 | 209/1 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
214 | 209/2 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
215 | 210/0 | DB2+9 (4X2MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
216 | 211/0 | DB2+9 | #N/A | 65.7565 | #N/A | #N/A | #N/A | #N/A |  | #N/A
217 | 211/1 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
218 | 211/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
219 | 211/3 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
220 | 211/4 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
221 | 211/5 | DB1+9 | #N/A | 65.7565 | #N/A | #N/A | #N/A | #N/A |  | #N/A
222 | 212/0 | DD45+30 (4X2MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
223 | 213/0 | DD60+35 | #N/A | 172.5195 | #N/A | #N/A | #N/A | #N/A |  | #N/A
224 | 214/0 | DD60+25 (4X2MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
225 | 214/1 | DA+6 | #N/A | 44.7941 | #N/A | #N/A | #N/A | #N/A |  | #N/A
226 | 214/2 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
227 | 214/3 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
228 | 214/4 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
229 | 214/5 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
230 | 214/6 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
231 | 214/7 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
232 | 215/0 | DD60+3 | #N/A | 84.2993 | #N/A | #N/A | #N/A | #N/A |  | #N/A
233 | 216/0 | DD60+3 | #N/A | 84.2993 | #N/A | #N/A | #N/A | #N/A |  | #N/A
234 | 216/1 | DA+9 (4X2MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
235 | 216/2 | DB1+18 (4X2MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
236 | 216/3 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
237 | 217/0 | DC2+9 | #N/A | 77.7181 | #N/A | #N/A | #N/A | #N/A |  | #N/A
238 | 217/1 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
239 | 217/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
240 | 217/3 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
241 | 217/4 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
242 | 217/5 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
243 | 218/0 | DD60+3 | #N/A | 84.2993 | #N/A | #N/A | #N/A | #N/A |  | #N/A
244 | 219/0 | DD45+3 | #N/A | 75.4524 | #N/A | #N/A | #N/A | #N/A |  | #N/A
245 | 219/1 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
246 | 220/0 | DD45+0 | #N/A | 72.2376 | #N/A | #N/A | #N/A | #N/A |  | #N/A
247 | 220/1 | DA+6 | #N/A | 44.7941 | #N/A | #N/A | #N/A | #N/A |  | #N/A
248 | 221/0 | DD60+18 | #N/A | 129.341 | #N/A | #N/A | #N/A | #N/A |  | #N/A
249 | 222/0 | DD60+25 | #N/A | 141.874 | #N/A | #N/A | #N/A | #N/A |  | #N/A
250 | 223/0 | DC1+6 | #N/A | 74.6321 | #N/A | #N/A | #N/A | #N/A |  | #N/A
251 | 223/1 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
252 | 223/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
253 | 223/3 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
254 | 224/0 | DC1+0 | #N/A | 64.2538 | #N/A | #N/A | #N/A | #N/A |  | #N/A
255 | 224/1 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
256 | 224/2 | DB1+6 | #N/A | 63.509 | #N/A | #N/A | #N/A | #N/A |  | #N/A
257 | 225/0 | DB2+0 | #N/A | 54.4178 | #N/A | #N/A | #N/A | #N/A |  | #N/A
258 | 225/1 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
259 | 225/2 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
260 | 225/3 | DA-3 | #N/A | 36.0448 | #N/A | #N/A | #N/A | #N/A |  | #N/A
261 | 225/4 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
262 | 225/5 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
263 | 225/6 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
264 | 225/7 | DA+6 | #N/A | 44.7941 | #N/A | #N/A | #N/A | #N/A |  | #N/A
265 | 226/0 | DB2+3 | #N/A | 56.8632 | #N/A | #N/A | #N/A | #N/A |  | #N/A
266 | 226/1 | DA+6 | #N/A | 44.7941 | #N/A | #N/A | #N/A | #N/A |  | #N/A
267 | 226/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
268 | 226/3 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
269 | 227/0 | DD45+0 | #N/A | 72.2376 | #N/A | #N/A | #N/A | #N/A |  | #N/A
270 | 227/1 | DA+6 | #N/A | 44.7941 | #N/A | #N/A | #N/A | #N/A |  | #N/A
271 | 227/2 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
272 | 228/0 | DD45+0 | #N/A | 72.2376 | #N/A | #N/A | #N/A | #N/A |  | #N/A
273 | 228/1 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
274 | 229/0 | DD45+0 | #N/A | 72.2376 | #N/A | #N/A | #N/A | #N/A |  | #N/A
275 | 229/1 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
276 | 229A/0 | DB1+25 | #N/A | 91.0555 | #N/A | #N/A | #N/A | #N/A |  | #N/A
277 | 229B/0 | DB2+25 | #N/A | 91.0555 | #N/A | #N/A | #N/A | #N/A |  | #N/A
278 | 230/0 | DC1+6 | #N/A | 74.6321 | #N/A | #N/A | #N/A | #N/A |  | #N/A
279 | 230/1 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
280 | 230A/0 | DD45+0 | #N/A | 72.2376 | #N/A | #N/A | #N/A | #N/A |  | #N/A
281 | 231/0 | DB1+0 | #N/A | 54.4178 | #N/A | #N/A | #N/A | #N/A |  | #N/A
282 | 232/0 | DB1+0 | #N/A | 54.4178 | #N/A | #N/A | #N/A | #N/A |  | #N/A
283 | 232/1 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
284 | 232/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
285 | 232/3 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
286 | 232/4 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
287 | 233/0 | DC1+0 | #N/A | 64.2538 | #N/A | #N/A | #N/A | #N/A |  | #N/A
288 | 234/0 | DD60+18 | #N/A | 129.341 | #N/A | #N/A | #N/A | #N/A |  | #N/A
289 | 235/0 | DD60+9 (4X2MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
290 | 235/1 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
291 | 235/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
292 | 235/3 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
293 | 235/4 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
294 | 236/0 | DB2+18 | #N/A | 82.2388 | #N/A | #N/A | #N/A | #N/A |  | #N/A
295 | 237/0 | DB1+25 (4X2MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
296 | 238/0 | DC1+25 | #N/A | 109.6077 | #N/A | #N/A | #N/A | #N/A |  | #N/A
297 | 239/0 | DD45+0 | #N/A | 72.2376 | #N/A | #N/A | #N/A | #N/A |  | #N/A
298 | 239/1 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
299 | 240/0 | DB2+0 | #N/A | 54.4178 | #N/A | #N/A | #N/A | #N/A |  | #N/A
300 | 240/1 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
301 | 241/0 | DD60+0 | #N/A | 80.408 | #N/A | #N/A | #N/A | #N/A |  | #N/A
302 | 241/1 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
303 | 241/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
304 | 241/3 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
305 | 241/4 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
306 | 242/0 | DD60+3 | #N/A | 84.2993 | #N/A | #N/A | #N/A | #N/A |  | #N/A
307 | 243/0 | DD60+3 | #N/A | 84.2993 | #N/A | #N/A | #N/A | #N/A |  | #N/A
308 | 243/1 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
309 | 243/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
310 | 243/3 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
311 | 244/0 | DD45+0 | #N/A | 72.2376 | #N/A | #N/A | #N/A | #N/A |  | #N/A
312 | 244/1 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
313 | 244/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
314 | 244/3 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
315 | 244/4 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
316 | 244/5 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
317 | 244/6 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
318 | 245/0 | DD45+0 | #N/A | 72.2376 | #N/A | #N/A | #N/A | #N/A |  | #N/A
319 | 245/1 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
320 | 246/0 | DD45+9 | #N/A | 89.1428 | #N/A | #N/A | #N/A | #N/A |  | #N/A
321 | 247/0 | DD60+35 (4X2MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
322 | 248/0 | DD60+35 (4X2MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
323 | 248/1 | DB1+9 | #N/A | 65.7565 | #N/A | #N/A | #N/A | #N/A |  | #N/A
324 | 248/2 | DA+6 | #N/A | 44.7941 | #N/A | #N/A | #N/A | #N/A |  | #N/A
325 | 249/0 | DD60+3 | #N/A | 84.2993 | #N/A | #N/A | #N/A | #N/A |  | #N/A
326 | 249/1 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
327 | 249/2 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
328 | 249/3 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
329 | 250/0 | DD45+3 | #N/A | 75.4524 | #N/A | #N/A | #N/A | #N/A |  | #N/A
330 | 250/1 | DA+9 (4X1MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
331 | 250/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
332 | 250/3 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
333 | 250A/0 | DB1+3 (4X3MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
334 | 250A/1 | DA+6 | #N/A | 44.7941 | #N/A | #N/A | #N/A | #N/A |  | #N/A
335 | 250A/2 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
336 | 251/0 | DD45+0 | #N/A | 72.2376 | #N/A | #N/A | #N/A | #N/A |  | #N/A
337 | 251/1 | DA+6 (4X1MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
338 | 252/0 | DB2+0 | #N/A | 54.4178 | #N/A | #N/A | #N/A | #N/A |  | #N/A
339 | 252/1 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
340 | 252/2 | DA+3 | #N/A | 39.4589 | #N/A | #N/A | #N/A | #N/A |  | #N/A
341 | 252/3 | DA+6 | #N/A | 44.7941 | #N/A | #N/A | #N/A | #N/A |  | #N/A
342 | 252/4 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
343 | 252/5 | DB1+9 | #N/A | 65.7565 | #N/A | #N/A | #N/A | #N/A |  | #N/A
344 | 253/0 | DD45+35 (4X2MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
345 | 254/0 | DD45+35 (4X2MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
346 | 254/1 | DB1+9 | #N/A | 65.7565 | #N/A | #N/A | #N/A | #N/A |  | #N/A
347 | 255/0 | DD60+0 | #N/A | 80.408 | #N/A | #N/A | #N/A | #N/A |  | #N/A
348 | 255/1 | DA+0 | #N/A | 37.7963 | #N/A | #N/A | #N/A | #N/A |  | #N/A
349 | 256/0 | DD60+0 | #N/A | 80.408 | #N/A | #N/A | #N/A | #N/A |  | #N/A
350 | 256/1 | DA+9 | #N/A | 46.6894 | #N/A | #N/A | #N/A | #N/A |  | #N/A
351 | 257/0 | DC1+9 | #N/A | 77.7181 | #N/A | #N/A | #N/A | #N/A |  | #N/A
352 | 258/0 | DD60+0 (4X1.5MRC) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A
Formulas:
Gang Name = VLOOKUP([Location No.],'Erection Completed '!$B2:J62,7,FALSE)
Completion Date = VLOOKUP([Location No.],'Erection Completed '!$B2:J62,6,FALSE)
Note on C108: Arun Sardar: Details Survey DD45+6+2M RC

## Stringing (hidden)
VNTL Stringing |  |  | 12.7516 | [12 empty] | 416
Sr. No. | Section | No of Towers | length( km) | Manual/TSE | Insulator and hardware fitting done | Engaged Date | Paying Out |  | Final Sag |  | P/O Completed | F/S Completed | Stringing Status As on Today | Cumulative Status | Sub Contractor name | Manpower | Hindarnce Days | Remarks
[7 empty] | Start Date | End Date | Start Date | End Date
1 | 175/1-176/0 | 2 | 0.44553 | Manual | 2/2 done | 2026-03-26 | 2026-04-06 | 2026-04-12 | 2026-04-07 | 2026-04-12 | 2026-04-11 | 2026-04-12 | 6 phase final sag complete | Completed | Maa Singhvasini | 27
2 | 176/0-177/0 | 4 | 1.0433 | TSE | 1/4 done | 2026-04-02 | 2026-04-24 | 2026-04-27 | 2026-04-24 | 2026-04-28 | 2026-04-27 | 2026-04-28 | 6 phase final sag done | Completed | Maa Singhvasini | 27
3 | 180/2-182/0 | 7 | 2.4126 | TSE | 7/7 done | 2026-04-02 | 2026-04-06 | 2026-04-13 | 2026-04-14 | 2026-04-16 | 2026-04-13 | 2026-04-16 | cliping done spacer u/p | Completed | Alam Construction | 68 | 5 | Gang idle due to 180/3 to 182/0 corridor area row
4 | 182/0-183/0 | 2 | 0.20891 | Hotline | 2/2 done | 2026-04-01 | 2026-04-05 | 2026-04-11 | 2026-04-05 | 2026-04-11 | 2026-04-11 | 2026-04-11 | 6 phase final sag complete | Completed | Sanjay Singh | 20 |  | Hotline
5 | 119/0-120/0 | 5 | 1.4216 | TSE | 5/5 done | 2026-04-02 | 2026-04-16 | 2026-05-18 |  |  | 2026-05-18 | 0 | 119/3-120/0 6 phase paying out done,ew paying out done | EW paying out, 6 phase paying out 119/0-119/3 | Enamul Haque 119/0-119/3,Dharmendra singh 119/3-120/0 | 63 | 22 | Gang idle due to 66kv shutdown till 30.04.26
6 | 121/1-121/7 | 7 | 2.284 | TSE | 7/7 done | 2026-04-06 | 2026-04-13 | 2026-04-16 | 2026-05-19 | 2026-05-21 | 2026-04-16 | 2026-05-21 | 6 phase final sag complete,EW final Sag Done | Completed | Enamul Haque | 49 | 1
7 | 197/0-198/0 | 4 | 0.98372 | TSE | 4/4 Done | 2026-04-08 | 2026-05-18 |  |  |  | 0 | 0 | middle right Phase conductor paying out u/p | 11 kv 3 cable bypass complete,Conductor paying out aarengment complete 11 kv 4 cable bypass complete | Abdul Odut | 20 | 4 | Due to non availablity of shutdown of 11kv cable bypass work could not be carried,so gang remain idle.
8 | 183/0-184/0 | 5 | 1.4794 | TSE | 5/5 done | 2026-04-09 | 2026-04-18 | 2026-04-21 | 2026-04-20 | 2026-04-22 | 2026-04-21 | 2026-04-22 | 6 phase final sag,EW final sag,cliping done | Completed | Alam Construction | 40 | 1 | Row due to 40 workers remain idle,shutdown cable 11kv removed 24-4-26
9 | 245/0-246/0 | 3 | 0.79163 | Manual | 3/3 Done | 2026-04-09 | 2026-04-11 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-15 | Cliping And Spacer Completed | Completed | Bhola Prasad+ Deepak Sarkar | 27
9 | 120/0-121/0 | 9 | 2.8617 | TSE | 9/9 done | 2026-04-10 | 2026-05-03 | 2026-05-08 | 2026-05-10 | 2026-05-15 | 2026-05-08 | 2026-05-15 | 6 phase final sag complete, EW final sag u/p | Completed | Enamul Haque | 45
10 | 178/0-179/0 | 5 | 1.3265 | TSE | 5/5 done | 2026-04-10 | 2026-05-14 |  | 2026-05-17 |  | 0 | 0 | bottom phase final sag u/p,178/0-178/1 bottom left phase paying complete,bottom right phase final sag u/p | top left phase final sag done,178/0-178/1 top right phase paying out u/p | Alam Construction 178/1-178/3 + Sanjay Singh-2 178/0-178/1 and 178/3 -179/0 | 74 | 2 | Due to non availablity of shutdown of 11kv cable bypass work could not be carried.
11 | 198/0-199/0 | 2 | 0.24674 | Hotline | 1/2 Done | 2026-04-13 | 2026-04-17 | 2026-04-23 | 2026-04-17 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 6 phase final sag,EW final sag,spacer done | Completed | Sanjay Singh | 20 | 1 | Due to ROW at 199/0 back stay arrangement not done
12 | 196/0-197/0 | 4 | 1.1484 | TSE | 2/4 done | 2026-04-16 |  |  |  |  | 0 | 0 | backstay arrangement done,11kv cable laying done |  | Abdul Odut | 20 | 2 | Due to non availablity of shutdown of 11kv cable bypass work could not be carried,so gang remain idle.
13 | 184/0-185/0 | 2 | 0.21017 | Hotline | 2/2 Done | 2026-04-25 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 6 phase final sag complete,EW finag sag done ,Spacer u/p | Completed | Sanjay Singh-1 | 20
14 | 174/0-175/0 | 8 | 2.6334 | TSE | 7/8 Done | 2026-04-26 | 2026-05-03 | 2026-05-09 |  |  | 2026-05-09 | 0 | 6 phase Conductor paying out complete | right phase pilot wire has been tightened,11kV 2 cable bypass complete | Alam Construction | 68 | 2 | ROW from 29-4-26, clear on 02-05-26 evening 4:00 PM
15 | 175/0-175/1 | 2 | 0.468 | Hotline | 2/2 done | 2026-04-27 | 2026-05-02 | 2026-05-07 | 2026-05-03 | 2026-05-07 | 2026-05-07 | 2026-05-07 | 6 phase final sag complete, EW final Sag Complete, spacer complete | Completed | Alam Construction | 40 | 1 | ROW
16 | 177/0-178/0 | 2 | 0.228 | Hotline | 2/2 done | 2026-05-15 | 2026-05-15 | 2026-05-20 | 2026-05-15 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 5 Phase conductor finag sag done | Completed | Sanjay singh 2 | 33
17 | 191/0-192/0 | 3 | 0.85499 | Manual | 3/3 done | 2026-05-16 |  |  |  |  | 0 | 0 | backstay arrangement done,11kv shifting work |  | Alamgir | 20
18 | 126/0-127/0 | 5 | 1.5842 | TSE | 3/5 done | 2026-05-17 |  |  |  |  | 0 | 0 | top left phase paying out complete, middle phase paying out u/p |  | Enamul Haque | 45
19 | 118/0-119/0 | 2 | 0.24382 | Hotline | 2/2 done | 2026-05-20 | 2026-05-23 |  | 2026-05-23 |  | 0 | 0 | top phase conductor final sag done, middle phase final sag u/p |  | Dharmendra | 24
20 | 185/0-186/0 | 2 | 0.271 | Hotline | 2/2 done | 2026-05-20 | 2026-05-24 |  |  |  | 0 | 0 | EW finag sag done,top left phase final sag done |  | Sanjay singh 2 | 33
Formulas:
P/O Completed = [End Date]
F/S Completed = [End Date]

## Stringing Completed (hidden)
VNTL Stringing
12.68
Sr. No. | Section | No of Towers | length( km) | Manual/TSE | Insulator and hardware fitting done | Engaged Date | Paying Out |  | Final Sag |  | P/O Completed | F/S Completed | Cumulative Status | Sub Contractor name | Manpower | Hindarnce Days | Remarks
[7 empty] | Start Date | End Date | Start Date | End Date
1 | 182/0-183/0 | 2 | 0.20891 | Hotline | 2/2 done | 2026-04-01 | 2026-04-05 | 2026-04-11 | 2026-04-05 | 2026-04-11 | 2026-04-11 | 2026-04-11 | Complete | Sanjay Singh | 20 |  | Hotline
2 | 175/1-176/0 | 2 | 0.44553 | Manual | 2/2 done | 2026-03-26 | 2026-04-06 | 2026-04-12 | 2026-04-07 | 2026-04-12 | 2026-04-11 | 2026-04-12 | Completed | Maa Singhvasini | 27
3 | 245/0-246/0 | 3 | 0.79163 | Manual | 3/3 Done | 2026-04-09 | 2026-04-11 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-15 | Completed | Bhola Prasad+ Deepak Sarkar | 27
4 | 180/2-182/0 | 7 | 2.4126 | TSE | 7/7 done | 2026-04-02 | 2026-04-06 | 2026-04-13 | 2026-04-14 | 2026-04-16 | 2026-04-13 | 2026-04-16 | Complete | Alam Construction | 68 | 5 | Gang idle due to 180/3 to 182/0 corridor area row
5 | 183/0-184/0 | 5 | 1.4794 | TSE | 5/5 done | 2026-04-09 | 2026-04-18 | 2026-04-21 | 2026-04-20 | 2026-04-22 | 2026-04-21 | 2026-04-22 | Complete | Alam Construction | 40 | 1 | Row due to 40 workers remain idle,shutdown cable 11kv removed 24-4-26
6 | 198/0-199/0 | 2 | 0.24674 | Hotline | 2/2 Done | 2026-04-13 | 2026-04-17 | 2026-04-23 | 2026-04-17 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Completed | Sanjay Singh | 20 | 1 | Due to ROW at 199/0 back stay arrangement not done
7 | 176/0-177/0 | 4 | 1.0433 | TSE | 4/4 done | 2026-04-02 | 2026-04-24 | 2026-04-27 | 2026-04-24 | 2026-04-28 | 2026-04-27 | 2026-04-28 | Complete | Alam Construction | 40
8 | 175/0-175/1 | 2 | 0.468 | Hotline | 2/2 done | 2026-04-27 | 2026-05-02 | 2026-05-07 | 2026-05-03 | 2026-05-07 | 2026-05-07 | 2026-05-07 | Complete | Alam Construction | 40 | 1 | Hotline
9 | 184/0-185/0 | 2 | 0.21017 | Hotline | 2/2 Done | 2026-04-25 | 2026-05-06 | 2026-05-13 | 2026-05-06 | 2026-05-13 | 2026-05-13 | 2026-05-13 | Complete | Sanjay Singh-1 | 20
10 | 120/0-121/0 | 9 | 2.8617 | TSE | 9/9 done | 2026-04-10 | 2026-05-03 | 2026-05-08 | 2026-05-10 | 2026-05-15 | 2026-05-08 | 2026-05-15 | Completed | Enamul Haque | 45
11 | 177/0-178/0 | 2 | 0.228 | Hotline | 2/2 done | 2026-05-15 | 2026-05-15 | 2026-05-20 | 2026-05-15 | 2026-05-20 | 2026-05-20 | 2026-05-20 | Completed | Sanjay singh 2 | 33
12 | 121/1-121/7 | 7 | 2.284 | TSE | 7/7 done | 2026-04-06 | 2026-04-13 | 2026-04-16 | 2026-05-19 | 2026-05-21 | 2026-04-16 | 2026-05-21 | Completed | Enamul Haque | 49 | 1
Formulas:
P/O Completed = [End Date]
F/S Completed = [End Date]

## Stringing Compiled (hidden)
|  |  | Number of TSE | 2 | 9.3192
S.no | Sec | From AP | To AP | Location Nos. | Span (M) | Method | Section Readiness | Insulator Hoisting | P/O Starting Date | P/O Completion Date | P/O | F/S Starting Date | F/S/ Completion Date | Jumpering | Spacering | Clipping | Length | Status | Gang Name | Gang Strength | Number of Fitters | Hindrance | Remarks
1 |  | 117/0 | 118/0 | 117/1,117/2 | 1142.762 | TSE | Ready
2 |  | 118/0 | 119/0 |  | 243.824 | Manual | WIP | Done
3 |  | 119/0 | 120/0 | 119/1,119/2,119/3 | 1421.595 | TSE | WIP | Done | [10 empty] | Enamul Haque | 49
4 |  | 120/0 | 121/0 | 120/1,120/2,120/3,120/4,120/5,120/6,120/7 | 2861.678 | TSE | Complete | Done | 2026-05-03 | 2026-05-08 | Completed | 2026-05-10 | 2026-05-15 |  | Done | Done |  |  | Enamul Haque | 49
5 |  | 121/0 | 121/1 |  | 276.141 | Hotline | Ready | [11 empty] | Enamul Haque | 49
6 |  | 121/1 | 121/7 | 121/2,121/3,121/4,121/5,121/6 | 2284 | TSE | Complete | Done | 2026-04-13 | 2026-04-16 | Completed | 2026-05-19 | 2026-05-21 | [5 empty] | Enamul Haque | 45
7 |  | 121/7 | 124/0 | 121/8,121/9,121/10,121/11 | 1937.394 | TSE | Not Ready
8 |  | 124/0 | 125/0 | 124/1,124/2,124/3 | 1472.589 | TSE | Not Ready
9 |  | 125/0 | 126/0 | 125/1,125/2 | 1288.931 | TSE | Ready
10 |  | 126/0 | 127/0 | 126/1,126/2,126/3 | 1584.22 | TSE | WIP
11 |  | 127/0 | 127/2 | 127/1 | 709.979 | Manual | Not Ready
12 |  | 127/2 | 128/0 |  | 339.13 | Manual | Not Ready
13 |  | 128/0 | 129/0 |  | 620 | Manual | Not Ready
14 |  | 129/0 | 130/0 |  | 620.06 | Manual | Not Ready
15 |  | 130/0 | 131/0 |  | 535.07 | Manual | Not Ready
16 |  | 131/0 | 132/0 | 131/1,131/2,131/3,131/4,131/5 | 2201.62 | TSE | Not Ready
17 |  | 132/0 | 133/0 | 132/1,132/2,132/3 | 1217.54 | TSE | Not Ready
18 |  | 133/0 | 133/2 | 133/1 | 767 | Manual | Not Ready
19 |  | 133/2 | 133/3 |  | 250 | Hotline | Ready
20 |  | 133/3 | 134/0 | 133/4 | 833.85 | Manual | Ready
21 |  | 134/0 | 135/0 |  | 360.67 | Manual | Not Ready
22 |  | 135/0 | 136/0 |  | 247.871 | Hotline | Not Ready
23 |  | 136/0 | 136/1 |  | 459.998 | Manual | Ready
24 |  | 136/1 | 137/0 |  | 455.963 | Hotline | Ready
25 |  | 137/0 | 138/0 | 137/1,137/2 | 1116.114 | TSE | Ready
26 |  | 138/0 | 139/0 |  | 460.541 | Manual | Ready
27 |  | 139/0 | 139/2 | 139/1 | 716.09 | Manual | Ready
28 |  | 139/2 | 139/3 |  | 340 | Manual | Not Ready
29 |  | 139/3 | 140/0 |  | 360.1 | Manual | Not Ready
30 |  | 140/0 | 141/0 |  | 204 | Hotline | Ready
31 |  | 141/0 | 142/0 | 141/1,141/2,141/3,141/4,141/5,141/6 | 2659.63 | TSE | Ready
32 |  | 142/0 | 143/0 |  | 164.303 | Manual | Ready
33 |  | 143/0 | 144/0 |  | 277.27 | Hotline | Ready
34 |  | 144/0 | 145/0 |  | 451.679 | Hotline | Ready
35 |  | 145/0 | 145/7 | 145/1,145/2,145/3,145/4,145/5,145/6 | 2776 | TSE | Not Ready
36 |  | 145/7 | 147/0 |  | 344.268 | Manual | Ready
37 |  | 147/0 | 148/0 |  | 251.645 | Hotline | Ready
38 |  | 148/0 | 148/5 | 148/1,148/2,148/3,148/4 | 2077.997 | TSE | Ready
39 |  | 148/5 | 149/0 |  | 508.088 | Manual | Ready
40 |  | 149/0 | 150/0 |  | 258.002 | Hotline | Not Ready
41 |  | 150/0 | 150/1 |  | 281 | Manual | Not Ready
42 |  | 150/1 | 151/0 |  | 367.61 | Manual | Not Ready
43 |  | 151/0 | 151A/0 |  | 266.99 | Manual | Not Ready
44 |  | 151A/0 | 152/0 |  | 500.05 | Manual | Not Ready
45 |  | 152/0 | 153/0 |  | 295 | Hotline | Not Ready
46 |  | 153/0 | 153A/0 | 153/1,153/2 | 1184.01 | TSE | Not Ready
47 |  | 153A/0 | 154/0 |  | 490.15 | Manual | Not Ready
48 |  | 154/0 | 155/0 |  | 295.36 | Manual | Not Ready
49 |  | 155/0 | 156/0 |  | 257.34 | Hotline | Not Ready
50 |  | 156/0 | 156/1 |  | 342.99 | Manual | Not Ready
51 |  | 156/1 | 157/0 |  | 335.33 | Manual | Not Ready
52 |  | 157/0 | 158/0 |  | 230 | Hotline | Not Ready
53 |  | 158/0 | 159/0 |  | 253.62 | Manual | Not Ready
54 |  | 159/0 | 160/0 |  | 333.34 | Hotline | Not Ready
55 |  | 160/0 | 161/0 |  | 392.23 | Manual | Ready
56 |  | 161/0 | 162/0 |  | 248.002 | Hotline | Not Ready
57 |  | 162/0 | 163/0 |  | 328.496 | Hotline | Not Ready
58 |  | 163/0 | 163/1 |  | 382.995 | Hotline | Not Ready
59 |  | 163/1 | 164/0 |  | 401.589 | Manual | Not Ready
60 |  | 164/0 | 165/0 |  | 285.055 | Hotline | Not Ready
61 |  | 165/0 | 165/6 | 165/1,165/2,165/3,165/4,165/5 | 2297.996 | TSE | Not Ready
62 |  | 165/6 | 166/0 | 165/7 | 730.096 | Manual | Not Ready
63 |  | 166/0 | 167/0 |  | 280 | Manual | Ready
64 |  | 167/0 | 168/0 |  | 576.145 | Manual | Not Ready
65 |  | 168/0 | 169/0 |  | 255.601 | Hotline | Not Ready
66 |  | 169/0 | 170/0 |  | 521.312 | Manual | Not Ready
67 |  | 170/0 | 171/0 |  | 261.446 | Hotline | Not Ready
68 |  | 171/0 | 172/0 |  | 186.772 | Hotline | Not Ready
69 |  | 172/0 | 173/0 | 172/1 | 689.629 | Manual | Not Ready
70 |  | 173/0 | 174/0 |  | 215.227 | Hotline | Not Ready
71 |  | 174/0 | 175/0 | 174/1,174/2,174/3,174/4,174/5,174/6 | 2633.369 | TSE | WIP | Done
72 |  | 175/0 | 175/1 |  | 468.001 | Hotline | Complete | Done | 2026-05-02 | 2026-05-07 | Completed | 2026-05-03 | 2026-05-07 | [5 empty] | Alam Construction | 40 |  |  | Hotline
73 |  | 175/1 | 176/0 |  | 445.528 | Manual | Complete | Done | 2026-04-06 | 2026-04-12 | Completed | 2026-04-07 | 2026-04-12 |  | Completed | Completed |  | Completed | Maa Singhvahini | 27
74 |  | 176/0 | 177/0 | 176/1,176/2 | 1043.334 | TSE | Complete | Done | 2026-04-24 | 2026-04-27 | Completed | 2026-04-24 | 2026-04-28 |  | Completed | Completed |  | Completed | Alam Construction | 40
75 |  | 177/0 | 178/0 |  | 228.09 | Hotline | Complete | Done | 2026-05-15 | 2026-05-20 | Completed | 2026-05-20 | 2026-05-20 |  | Completed |  |  |  | Sanjay singh 2 | 33
76 |  | 178/0 | 179/0 | 178/1,178/2,178/3 | 1326.507 | TSE | WIP | Done
77 |  | 179/0 | 180/0 | 179/1,179/2,179/3 | 1582.474 | TSE | Not Ready
78 |  | 180/0 | 180/2 | 180/1 | 821.997 | Manual | Not Ready
79 |  | 180/2 | 182/0 | 180/3,180/4,180/5,180/6,180/7 | 2412.62 | TSE | Complete | Done | 2026-04-06 | 2026-04-13 | Completed | 2026-04-14 | 2026-04-16 |  | Completed | Completed |  | Completed | Alam Construction | 68 |  | 5
80 |  | 182/0 | 183/0 |  | 208.909 | Hotline | Complete | Done | 2026-04-05 | 2026-04-11 | Completed | 2026-04-05 | 2026-04-11 |  | Completed | Completed |  | Completed | Sanjay Singh | 20 |  |  | Hotline
81 |  | 183/0 | 184/0 | 183/1,183/2,183/3 | 1479.41 | TSE | Complete | Done | 2026-04-18 | 2026-04-21 | Completed | 2026-04-20 | 2026-04-22 |  | Completed | Completed |  | Completed | Alam Construction | 40 |  | 1
82 |  | 184/0 | 185/0 |  | 210.17 | Hotline | Complete | Done | 2026-05-06 | 2026-05-13 | Completed | 2026-05-06 | 2026-05-13
83 |  | 185/0 | 186/0 |  | 271 | Hotline | WIP | Done
84 |  | 186/0 | 187/0 |  | 390.65 | Hotline | Ready | Done
85 |  | 187/0 | 188/0 |  | 428.21 | Manual | Not Ready
86 |  | 188/0 | 189/0 |  | 672.59 | Manual | Not Ready
87 |  | 189/0 | 190/0 | 189/1 | 807.98 | Manual | Not Ready
88 |  | 190/0 | 191/0 |  | 226.48 | Hotline | Ready
89 |  | 191/0 | 191/1 |  | 465.47 | Manual | WIP | Done
90 |  | 191/1 | 192/0 |  | 389.51 | Manual | WIP | Done
91 |  | 192/0 | 193/0 |  | 222.83 | Hotline | Not Ready
92 |  | 193/0 | 194/0 |  | 277.42 | Hotline | Not Ready
93 |  | 194/0 | 194/1 |  | 470 | Manual | Not Ready
94 |  | 194/1 | 195/0 |  | 479.7 | Manual | Not Ready
95 |  | 195/0 | 196/0 |  | 239.69 | Hotline | Not Ready
96 |  | 196/0 | 197/0 | 196/1,196/2 | 1148.42 | TSE | Ready
97 |  | 197/0 | 198/0 | 197/1,197/2 | 983.72 | Manual | WIP | Done
98 |  | 198/0 | 199/0 |  | 246.74 | Hotline | Complete | Done | 2026-04-17 | 2026-04-23 | Completed | 2026-04-17 | 2026-04-23 |  | Completed | NA |  | Completed
99 |  | 199/0 | 200/0 | 199/1,199/2 | 1266.29 | TSE | Not Ready
100 |  | 200/0 | 201/0 | 200/1 | 709.98 | Hotline | Not Ready
101 |  | 201/0 | 202/0 |  | 513.96 | Manual | Not Ready
102 |  | 202/0 | 203/0 |  | 233.14 | Hotline | Not Ready
103 |  | 203/0 | 203A/0 |  | 128.02 | Manual | Not Ready
104 |  | 203A/0 | 203B/0 |  | 282.82 | Manual | Not Ready
105 |  | 203B/0 | 204/0 |  | 339.95 | Manual | Not Ready
106 |  | 204/0 | 205/0 |  | 172.64 | Hotline | Not Ready
107 |  | 205/0 | 205/1 |  | 555.17 | Manual | Not Ready
108 |  | 205/1 | 206/0 | 205/2 | 811.52 | Manual | Not Ready
109 |  | 206/0 | 206/1 |  | 184.81 | Manual | Not Ready
110 |  | 206/1 | 207/0 |  | 214.27 | Manual | Not Ready
111 |  | 207/0 | 208/0 |  | 272.3 | Hotline | Not Ready
112 |  | 208/0 | 209/0 |  | 284.64 | Hotline | Not Ready
113 |  | 209/0 | 210/0 | 209/1,209/2 | 1036.29 | TSE | Not Ready
114 |  | 210/0 | 211/0 |  | 397.66 | Hotline | Not Ready
115 |  | 211/0 | 211/5 | 211/1,211/2,211/3,211/4 | 1872 | TSE | Not Ready
116 |  | 211/5 | 212/0 |  | 266.961 | Manual | Not Ready
117 |  | 212/0 | 213/0 |  | 378.221 | Hotline | Not Ready
118 |  | 213/0 | 214/0 |  | 325.229 | Hotline | Not Ready
119 |  | 214/0 | 215/0 | 214/1,214/2,214/3,214/4,214/5,214/6,214/7 | 2987.2165 | TSE | Not Ready
120 |  | 215/0 | 216/0 |  | 231.41 | Hotline | Ready
121 |  | 216/0 | 216/2 | 216/1 | 803 | Hotline | Not Ready
122 |  | 216/2 | 217/0 | 216/3 | 749.12 | Manual | Not Ready
123 |  | 217/0 | 218/0 | 217/1,217/2,217/3,217/4,217/5 | 2245.811 | TSE | Not Ready
124 |  | 218/0 | 219/0 |  | 239.47 | Hotline | Not Ready
125 |  | 219/0 | 220/0 | 219/1 | 798.41 | Manual | Not Ready
126 |  | 220/0 | 221/0 | 220/1 | 819.27 | Manual | Not Ready
127 |  | 221/0 | 222/0 |  | 191.81 | Hotline | Not Ready
128 |  | 222/0 | 223/0 |  | 248.6 | Hotline | Ready
129 |  | 223/0 | 224/0 | 223/1,223/2,223/3 | 1386.17 | TSE | Not Ready
130 |  | 224/0 | 224/2 | 224/1 | 714 | Manual | Not Ready
131 |  | 224/2 | 225/0 |  | 431.2 | Manual | Not Ready
132 |  | 225/0 | 226/0 | 225/1,225/2,225/3,225/4,225/5,225/6,225/7 | 2965.43 | TSE | Not Ready
133 |  | 226/0 | 227/0 | 226/1,226/2,226/3 | 1574.68 | TSE | Ready
134 |  | 227/0 | 228/0 | 227/1,227/2 | 1238.74 | TSE | Ready
135 |  | 228/0 | 229/0 | 228/1 | 767.07 | Manual | Not Ready
136 |  | 229/0 | 229A/0 | 229/1 | 791.5 | Manual | Not Ready
137 |  | 229A/0 | 229B/0 |  | 179.98 | Hotline | Not Ready
138 |  | 229B/0 | 230/0 |  | 390.65 | Manual | Not Ready
139 |  | 230/0 | 230A/0 | 230/1 | 786.67 | Manual | Not Ready
140 |  | 230A/0 | 231/0 |  | 239.51 | Manual | Not Ready
141 |  | 231/0 | 232/0 |  | 246.98 | Hotline | Not Ready
142 |  | 232/0 | 233/0 | 232/1,232/2,232/3,232/4 | 1728.185 | TSE | Not Ready
143 |  | 233/0 | 234/0 |  | 411.1429 | Manual | Not Ready
144 |  | 234/0 | 235/0 |  | 295 | Hotline | Not Ready
145 |  | 235/0 | 236/0 | 235/1,235/2,235/3,235/4 | 1763.541 | TSE | Not Ready
146 |  | 236/0 | 237/0 |  | 200.821 | Hotline | Not Ready
147 |  | 237/0 | 238/0 |  | 202.277 | Hotline | Not Ready
148 |  | 238/0 | 239/0 |  | 363.321 | Manual | Not Ready
149 |  | 239/0 | 240/0 | 239/1 | 737.403 | Manual | Ready
150 |  | 240/0 | 241/0 | 240/1 | 734.048 | Manual | Ready
151 |  | 241/0 | 242/0 | 241/1,241/2,241/3,241/4 | 1835.738 | TSE | Ready
152 |  | 242/0 | 243/0 |  | 280.015 | Hotline | Ready
153 |  | 243/0 | 244/0 | 243/1,243/2,243/3 | 1372.6 | TSE | Not Ready
154 |  | 244/0 | 245/0 | 244/1,244/2,244/3,244/4,244/5,244/6 | 2778.121 | TSE | Not Ready
155 |  | 245/0 | 246/0 | 245/1 | 791.626 | Manual | Complete | Done | 2026-04-11 | 2026-04-14 | Completed | 2026-04-14 | 2026-04-15 |  | Completed | Completed |  | Completed | Bhola prasad+ Deepak Sarkar | 30
156 |  | 246/0 | 247/0 |  | 463.1 | Manual | Not Ready
157 |  | 247/0 | 248/0 |  | 256.45 | Hotline | Not Ready
158 |  | 248/0 | 248/1 |  | 425.57 | Manual | Not Ready
159 |  | 248/1 | 249/0 | 248/2 | 566.9 | Manual | Not Ready
160 |  | 249/0 | 250/0 | 249/1,249/2,249/3 | 1620.626 | TSE | Not Ready
161 |  | 250/0 | 250A/0 | 250/1,250/2,250/3 | 1630.951 | TSE | Not Ready
162 |  | 250A/0 | 251/0 | 250A/1,250A/2 | 1133.974 | TSE | Ready
163 |  | 251/0 | 252/0 | 251/1 | 840.868 | Manual | Ready
164 |  | 252/0 | 252/5 | 252/1,252/2,252/3,252/4 | 2021.996 | TSE | Ready
165 |  | 252/5 | 253/0 |  | 487.454 | Manual | Not Ready
166 |  | 253/0 | 254/0 |  | 304.46 | Hotline | Not Ready
167 |  | 254/0 | 254/1 |  | 353.19 | Manual | Not Ready
168 |  | 254/1 | 255/0 |  | 263.06 | Manual | Ready
169 |  | 255/0 | 256/0 | 255/1 | 736.76 | Manual | Not Ready
170 |  | 256/0 | 257/0 | 256/1 | 583.35 | Hotline | Not Ready
171 |  | 257/0 | 258/0 |  | 94.77 | Manual | Not Ready
172 |  | 258/0 | Gantry |  | 79 | Manual | Not Ready

## TA-602Visual Chart (hidden)
KEC INTERNATIONAL LIMITED
l
Name of Line: ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line
CLIENT : M/S Powergrid West Central Transmission Ltd.
Date of Commencemen : 13-05-2025
| VISUAL CHART | [44 empty] | Progress as on date : |  |  | 2026-06-27 09:33
[45 empty] | CUM. | Total Loc. | BALANCE
[47 empty] | FDN. | Erec. | Earth | Tack Weld | String ing
[9 empty] | Route Diversion Proposed | [7 empty] | No Diversion DS Submitted | [21 empty] | Route Diversion Proposed
[9 empty] | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C1 | B1 |  |  | 12 | 0 | 0 | 0 | 0
[9 empty] | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D1 | A1
[9 empty] | 0 | - | 337 | 0 | - | 404 | 0 | - | 309 | 0 | - | 317 | 0 | - | 395 | 0 | - | 361 | 0 | - | 434 | 0 | - | 347 | 0 | - | 344 | 0 | - | 379 | 0 | - | 336 | 0 | - | 439.86 | [7 empty] | 4402.86
[9 empty] | 0/0 |  |  | 0/1 |  |  | 0/2 |  |  | 1/0 |  |  | 2/0 |  |  | 2/1 |  |  | 3/0 |  |  | 3/1 |  |  | 3/2 |  |  | 3/3 |  |  | 4/0 |  |  | 5/0
[9 empty] | D60+9 |  |  | A+9 |  |  | A+9 |  |  | D60(-)3 |  |  | D45+3 |  |  | A+0 |  |  | C2+0 |  |  | A+1.5 |  |  | A(-)3 |  |  | A(-)3 |  |  | D60+0 |  |  | B2+9
[9 empty] | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5 |  |  | 6 |  |  | 7 |  |  | 8 |  |  | 9 |  |  | 10 |  |  | 11 |  |  | 12
|  | Route Diversion Proposed | [14 empty] | DS Submitted | Route Diverison Proposed
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 437 | 0 | - | 335.734 | 0 | - |  | 0 | - | 341.753 | 0 | - | 407.786 | 0 | - | 412 | 0 | - | 426.82 | 0 | - | 337 | 0 | - | 454 | 0 | - | 344.906 | 0 | - | 399 | 0 | - | 379.984 | 0 | - | 464 | 0 | - | 364 | [7 empty] | 5103.983
|  |  | 6/0 |  |  | 6/1 |  |  | 7/0 |  |  | 8/0 |  |  | 9/0 |  |  | 10/0 |  |  | 10/1 |  |  | 11/0 |  |  | 11/1 |  |  | 11/2 |  |  | 12/0 |  |  | 12/1 |  |  | 13/0 |  |  | 13/1
|  |  | D45+3 |  |  | A+6 |  |  | B2(-)3 |  |  | C1+9 |  |  | D45+9 |  |  | C1+3 |  |  | A+6 |  |  | C1+3 |  |  | A+6 |  |  | A+6 |  |  | C1+9 |  |  | A+6 |  |  | D45+0 |  |  | A+9
|  |  | 13 |  |  | 14 |  |  | 15 |  |  | 16 |  |  | 17 |  |  | 18 |  |  | 19 |  |  | 20 |  |  | 21 |  |  | 22 |  |  | 23 |  |  | 24 |  |  | 25 |  |  | 26
|  | Route Diversion Proposed | [17 empty] | No Diversion DS Submitted
|  |  | C | B |  | C | B |  | C | B |  | C1 | B1 |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C1 | B1 |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D1 | A1 |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D1 | A1 |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 454 | 0 | - | 379.923 | 0 | - | 422.762 | 0 | - | 446 | 0 | - | 389.71 | 0 | - | 480.749 | 0 | - | 176 | 0 | - | 212 | 0 | - | 220 | 0 | - | 434 | 0 | - | 431 | 0 | - | 440 | 0 | - | 0 | 0 | - | 362 | [7 empty] | 4848.144
|  |  | 13/2 |  |  | 13/3 |  |  | 14/0 |  |  | 15/0 |  |  | 15/1 |  |  | 16/0 |  |  | 17/0 |  |  | 18/0 |  | NH-56 | 19/0 |  |  | 20/0 |  |  | 21/0 |  |  | 22/0 |  |  | 23/0 |  |  | 23/1
|  |  | A+6 |  |  | A+6 |  |  | D45+3 |  |  | B2+0 |  |  | A+3 |  |  | B2+6 |  |  | D45+3 |  |  | D45+0 |  |  | D60(-)3 |  |  | D45+6 |  |  | C2+9 |  |  | D60+0 |  |  | D60+3 |  |  | A+0
|  |  | 27 |  |  | 28 |  |  | 29 |  |  | 30 |  |  | 31 |  |  | 32 |  |  | 33 |  |  | 34 |  |  | 35 |  |  | 36 |  |  | 37 |  |  | 38 |  |  | 39 |  |  | 40
Route Diveriosn Proposed
|  |  | C2 | B2 |  | C2 | B2 |  | C2 | B2 |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D2 | A2 |  | D2 | A2 |  | D2 | A2 |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 365 | 0 | - | 365 | 0 | - | 390 | 0 | - | 390 | 0 | - | 381 | 0 | - | 390 | 0 | - | 369 | 0 | - | 432 | 0 | - | 446 | 0 | - | 395 | 0 | - | 400 | 0 | - | 440 | 0 | - | 439 | 0 | - | 372 | [7 empty] | 5574
|  |  | 23/2 |  |  | 23/3 |  |  | AP24 |  |  | 24/1 |  |  | 24/2 |  |  | 24/3 |  |  | AP25 |  |  | AP26 |  |  | AP27 |  |  | AP28 |  |  | 28/1 |  |  | AP29 |  |  | 29/1 |  |  | AP30
|  |  | A+0 |  |  | A+0 |  |  | D45+0 |  |  | A+6 |  |  | A+3 |  |  | A+6 |  |  | C2+0 |  |  | D45+0 |  |  | D45+0 |  |  | C1+0 |  |  | A+3 |  |  | C1+6 |  |  | B1+9 |  |  | C2+6
|  |  | 41 |  |  | 42 |  |  | 43 |  |  | 44 |  |  | 45 |  |  | 46 |  |  | 47 |  |  | 48 |  |  | 49 |  |  | 50 |  |  | 51 |  |  | 52 |  |  | 53 |  |  | 54
|  |  | Route Diversion Proposed | [26 empty] | DS Submiited
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 372 | 0 | - | 370 | 0 | - | 400 | 0 | - | 360 | 0 | - | 365 | 0 | - | 428 | 0 | - | 360.723 | 0 | - | 260.002 | 0 | - | 456.806 | 0 | - | 444.778 | 0 | - | 407 | 0 | - | 400.912 | 0 | - | 407 | 0 | - | 378 | [7 empty] | 5410.221
|  |  | 30/1 |  |  | 30/2 |  |  | AP31 |  |  | AP32 |  |  | 32/1 |  |  | AP33 |  |  | 33/1 |  |  | AP34 |  |  | 34/1 |  |  | AP35 |  |  | AP36 |  |  | 36/1 |  |  | AP37 |  |  | 37/1
|  |  | A+0 |  |  | A+0 |  |  | C1+3 |  |  | D45+3 |  |  | A+0 |  |  | C1-3 |  |  | A+0 |  |  | C2+0 |  |  | A+6 |  |  | B2+3 |  |  | C1+3 |  |  | A+0 |  |  | C1+3 |  |  | A+6
|  |  | 55 |  |  | 56 |  |  | 57 |  |  | 58 |  |  | 59 |  |  | 60 |  |  | 61 |  |  | 62 |  |  | 63 |  |  | 64 |  |  | 65 |  |  | 66 |  |  | 67 |  |  | 68
|  | DS Submitted | [33 empty] | Route Diversion Proposed
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 468 | 0 | - | 379 | 0 | - | 354 | 0 | - | 388 | 0 | - | 442.971 | 0 | - | 508 | 0 | - | 313.962 | 0 | - | 386 | 0 | - | 439 | 0 | - | 362 | 0 | - | 477.962 | 0 | - | 350 | 0 | - | 350 | 0 | - | 325 | [7 empty] | 5543.895
|  |  | 37/2 |  |  | 37/3 |  |  | 37/4 |  |  | 37/5 |  |  | 37/6 |  |  | 38/0 |  |  | 38/1 |  |  | 39/0 |  |  | 39/1 |  |  | 39/2 |  |  | 39/3 |  |  | 40/0 |  |  | 40/1 |  |  | 40/2
|  |  | A+4.5 |  |  | A+4.5 |  |  | A+7.5 |  |  | A+4.5 |  |  | A+9 |  |  | B2+6 |  |  | A+6 |  |  | C2+3 |  |  | A+9 |  |  | A+0 |  |  | A+9 |  |  | C1+9 |  |  | A+1.5 |  |  | A+0
|  |  | 69 |  |  | 70 |  |  | 71 |  |  | 72 |  |  | 73 |  |  | 74 |  |  | 75 |  |  | 76 |  |  | 77 |  |  | 78 |  |  | 79 |  |  | 80 |  |  | 81 |  |  | 82
Route Diversion Proposed
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C2 | B2 |  | C | B |  | C | B |  | C | B |  | C | B |  | C3 | B3 |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D2 | A2 |  | D | A |  | D | A |  | D | A |  | D | A |  | D3 | A3 |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 386 | 0 | - | 458.967 | 0 | - | 329.873 | 0 | - | 369 | 0 | - | 466.935 | 0 | - | 304.854 | 0 | - | 214.003 | 0 | - | 433.999 | 0 | - | 414 | 0 | - | 416 | 0 | - | 334.881 | 0 | - | 356 | 0 | - | 385 | 0 | - | 379.877 | [7 empty] | 5249.389
|  |  | 42/1 |  |  | 42/2 |  |  | 43/0 |  |  | 44/0 |  |  | 44/1 |  |  | 45/0 |  | SH-26 | 46/0 |  | 400 kV SC PL | 47/0 |  |  | 47/1 |  |  | 47/2 |  |  | 47/3 |  |  | 48/0 |  |  | 48/1 |  |  | 48/2
|  |  | A+7.5 |  |  | A+9 |  |  | D45(-)3 |  |  | C2(-)3 |  |  | A+6 |  |  | C1+6 |  |  | D60+18 |  |  | D60+25 |  |  | A+3 |  |  | A+9 |  |  | A+3 |  |  | C1+0 |  |  | A+0 |  |  | A+3
|  |  | 93 |  |  | 94 |  |  | 95 |  |  | 96 |  |  | 97 |  |  | 98 |  |  | 99 |  |  | 100 |  |  | 101 |  |  | 102 |  |  | 103 |  |  | 104 |  |  | 105 |  |  | 106
|  | Route Diversion Proposed | [16 empty] | CS Appproved
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 15 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 357.966 | 0 | - | 323.998 | 0 | - | 412 | 0 | - | 430.869 | 0 | - | 230 | 0 | - | 523 | 0 | - | 464 | 0 | - | 397 | 0 | - | 372.208 | 0 | - | 456.278 | 0 | - | 424.237 | 0 | - | 363 | 0 | - | 384.003 | 0 | - | 450.001 | [7 empty] | 5588.56
|  |  | 49/0 |  |  | 49A/0 |  |  | 49B/0 |  |  | 49B/1 |  |  | 50/0 |  | Rly | 51/0 |  |  | 51/1 |  |  | 52/0 |  |  | 52/1 |  |  | 53/0 |  |  | 54/0 |  |  | 55/0 |  |  | 55/1 |  |  | 55/2
|  |  | D45+6 |  |  | D45(-)3 |  |  | D45+3 |  |  | A+0 |  |  | D60+6 |  |  | D60+9 |  |  | B1+9 |  |  | C2+9 |  |  | A+0 |  |  | D45(-)3 |  |  | D60+18 |  |  | C1+9 |  |  | A(-)3 |  |  | A+9
|  |  | 107 |  |  | 108 |  |  | 109 |  |  | 110 |  |  | 111 |  |  | 112 |  |  | 113 |  |  | 114 |  |  | 115 |  |  | 116 |  |  | 117 |  |  | 118 |  |  | 119 |  |  | 120
CS Approved
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 362.999 | 0 | - | 373 | 0 | - | 333 | 0 | - | 497.019 | 0 | - | 355 | 0 | - | 439 | 0 | - | 408 | 0 | - | 438 | 0 | - | 258 | 0 | - | 323 | 0 | - | 331.079 | 0 | - | 392.003 | 0 | - | 400 | 0 | - | 400 | [7 empty] | 5310.1
|  |  | 56/0 |  |  | 56/1 |  |  | 57/0 |  |  | 57/1 |  |  | 58/0 |  |  | 58/1 |  |  | 58/2 |  |  | 58/3 |  |  | 59/0 |  | 132 kV SC PL | 60/0 |  |  | 60/1 |  |  | 61/0 |  |  | 62/0 |  |  | 62/1
|  |  | B2+9 |  |  | A+9 |  |  | C1+3 |  |  | A+9 |  |  | C2+9 |  |  | A+9 |  |  | A+9 |  |  | A+6 |  |  | D45+9 |  |  | D45+6 |  |  | A+0 |  |  | D45+0 |  |  | C2+0 |  |  | A+6
|  |  | 121 |  |  | 122 |  |  | 123 |  |  | 124 |  |  | 125 |  |  | 126 |  |  | 127 |  |  | 128 |  |  | 129 |  |  | 130 |  |  | 131 |  |  | 132 |  |  | 133 |  |  | 134
CS Appprved
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 400 | 0 | - | 402 | 0 | - | 400 | 0 | - | 400 | 0 | - | 410 | 0 | - | 410 | 0 | - | 395 | 0 | - | 388 | 0 | - | 382 | 0 | - | 406 | 0 | - | 380 | 0 | - | 436 | 0 | - | 409.052 | 0 | - | 423 | [7 empty] | 5641.052
|  |  | 62/2 |  |  | 62/3 |  |  | AP63 |  |  | 63/1 |  |  | 63/2 |  |  | 63/3 |  |  | 63/4 |  |  | AP-64 |  |  | 64/1 |  |  | 64/2 |  |  | 64/3 |  |  | 64/4 |  |  | 64/5 |  |  | 65/0
|  |  | A+6 |  |  | A+6 |  |  | C1+3 |  |  | A+9 |  |  | A+6 |  |  | A+6 |  |  | A+3 |  |  | B2+0 |  |  | A+0 |  |  | A+0 |  |  | A+3 |  |  | A+0 |  |  | A+3 |  |  | B2+0
146
|  |  | 135 |  |  | 136 |  |  | 137 |  |  | 138 |  |  | 139 |  |  | 140 |  |  | 141 |  |  | 142 |  |  | 143 |  |  | 144 |  |  | 145 |  |  | 146 |  |  | 147 |  |  | 148
CS Approved
[33 empty] | FC |  |  | FC |  |  | FC |  |  | FC |  |  |  | 12 | 0 | 0 | 0 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 4 | 0 | 3 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 372.008 | 0 | - | 369.995 | 0 | - | 352 | 0 | - | 432 | 0 | - | 417 | 0 | - | 428.062 | 0 | - | 379 | 0 | DFR | 396 | 0 | - | 396.008 | 0 | - | 400 | E | - | 397 | E | - | 378.998 | E | - | 379 | 0 | - | 352.701 | [7 empty] | 5449.772
|  |  | 65/1 |  |  | 66/0 |  |  | 67/0 |  |  | 67/1 |  |  | 67/2 |  |  | 67/3 |  |  | 68/0 |  |  | 68/1 |  |  | 68/2 |  |  | 69/0 |  |  | 69/1 |  |  | 69/2 |  |  | 69/3 |  |  | 69/4
|  |  | A+0 |  |  | D45+0 |  |  | D60+0 |  |  | A+0 |  |  | A+6 |  |  | A+6 |  |  | D45+0 |  |  | A+0 |  |  | A+3 |  |  | D45+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0
|  |  | 149 |  |  | 150 |  |  | 151 |  |  | 152 |  |  | 153 |  |  | 154 |  |  | 155 |  |  | 156 |  |  | 157 |  |  | 158 |  |  | 159 |  |  | 160 |  |  | 161 |  |  | 162
CS Approved
[46 empty] | 24 | #REF! | #REF! | 0 | #REF!
[6 empty] | FC |  |  | FC |  |  | FC | [5 empty] | FC |  |  | FC |  |  | FC |  |  | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 7 | 0 | 6 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 280 | E | DFR | 372 | E | WFR | 474 | E | DFR | 308.817 | 0 | - | 434.999 | E |  | 411.001 | E | - | 322 | E | - | 374 | 0 | - | 377 | 0 | - | 417.747 | 0 | - | 450 | 0 | - | 386.804 | 0 | - | 295.747 | 0 | - | 244.846 | [7 empty] | 5148.961
|  |  | 70/0 |  |  | 70/1 |  |  | 70/2 |  |  | 70/3 |  |  | 71/0 |  |  | 71/1 |  |  | 71/2 |  |  | 71/3 |  |  | 71/4 |  |  | 71/5 |  |  | 72/0 |  |  | 72/1 |  |  | 73/0 |  |  | 74/0
|  |  | C2-3 |  |  | A+4.5 |  |  | A+9 |  |  | A-3 |  |  | D45+3 |  |  | A+3 |  |  | A-3 |  |  | A+0 |  |  | A-3 |  |  | A+0 |  |  | D45+3 |  |  | A+9 |  |  | D45+3 |  |  | C2+18
|  |  | 163 |  |  | 164 |  |  | 165 |  |  | 166 |  |  | 167 |  |  | 168 |  |  | 169 |  |  | 170 |  |  | 171 |  |  | 172 |  |  | 173 |  |  | 174 |  |  | 175 |  |  | 176
|  | DS Submitted | [12 empty] | CS Approved
[18 empty] | FC |  |  | FC | [8 empty] | FC |  |  | FC | [5 empty] | FC | [6 empty] | 55 | #REF! | 0 | 0 | #REF!
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 5 | 0 | 4 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 338 | 0 | - | 324 | 0 | - | 261 | 0 | - | 315 | 0 | - | 426 | E | DFR | 418.999 | E | DFR | 367 | 0 | - | 431 | 0 | - | 403 | E | - | 438 | 0 | DFR | 356.71 | 0 | - | 305 | E | DFR | 337.839 | 0 | - | 317 | [7 empty] | 5038.548
|  | 132 kV SC PL | 75/0 |  |  | 75/1 |  |  | 75/2 |  |  | 75/3 |  |  | 76/0 |  |  | 76/1 |  |  | 76/2 |  |  | 76/3 |  |  | 76/4 |  |  | 76/5 |  |  | 76/6 |  |  | 77/0 |  |  | 77/1 |  |  | 78/0
|  |  | B2+9 |  |  | A+9 |  |  | A+0 |  |  | A+0 |  |  | C2+0 |  |  | A+6 |  |  | A+6 |  |  | A-3 |  |  | A+0 |  |  | A+9 |  |  | A+1.5 |  |  | B2+0 |  |  | A-3 |  |  | C2-3
|  |  | 177 |  |  | 178 |  |  | 179 |  |  | 180 |  |  | 181 |  |  | 182 |  |  | 183 |  |  | 184 |  |  | 185 |  |  | 186 |  |  | 187 |  |  | 188 |  |  | 189 |  |  | 190
CS Approved
[24 empty] | FC |  |  | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 2 | 0 | 2 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 317.777 | 0 | - | 457 | 0 | - | 389.816 | 0 | - | 298.846 | 0 | - | 330.931 | 0 | - | 338.998 | 0 | - | 427 | E | WFR | 401 | E | WET | 479.823 | 0 | - | 435 | 0 | - | 410 | 0 | - | 365 | 0 | - | 466.431 | 0 | - | 421.53 | [7 empty] | 5539.152
|  |  | 78/1 |  |  | 79/0 |  |  | 79/1 |  |  | 80/0 |  | 132 kV SC PL | 81/0 |  | SH-39 | 82/0 |  |  | 82/1 |  |  | 82/2 |  |  | 82/3 |  | River-Wagh | 83/0 |  |  | 83/1 |  |  | 83/2 |  |  | 83/3 |  |  | 85/0
|  |  | B1-3 |  |  | D45+3 |  |  | A+9 |  |  | B1-3 |  |  | B1+6 |  |  | C1+0 |  |  | A+0 |  |  | A+7.5 |  |  | A+9 |  |  | C2+0 |  |  | A+3 |  |  | A+9 |  |  | A+9 |  |  | B1+3
|  |  | 191 |  |  | 192 |  |  | 193 |  |  | 194 |  |  | 195 |  |  | 196 |  |  | 197 |  |  | 198 |  |  | 199 |  |  | 200 |  |  | 201 |  |  | 202 |  |  | 203 |  |  | 204
CS Approved
[12 empty] | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 8 | 0 | 6 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 208 | 0 | - | 449 | 0 | - | 398 | E | - | 404 | E | - | 427 | E | - | 400 | E | - | 386 |  | - | 400 | E | - | 442 | E | - | 384 |  | - | 390 |  | - | 539 |  | - | 412 |  | - | 375 | [7 empty] | 5614
|  | SH-26 | 86/0 |  | 132 kV SC PL | 87/0 |  |  | 87/1 |  |  | 87/2 |  |  | 87/3 |  |  | 87/4 |  |  | 87/5 |  |  | 88/0 |  |  | 88/1 |  |  | 88/2 |  |  | 88/3 |  |  | 88/4 |  |  | 88/5 |  |  | 88/6
|  |  | C1+6 |  |  | C1+9 |  |  | A+0 |  |  | A+0 |  |  | A+3 |  |  | A+0 |  |  | A+3 |  |  | C2+3 |  |  | A+3 |  |  | A+0 |  |  | A-3 |  |  | B1+3 |  |  | B1+0 |  |  | A+0
|  |  | 205 |  |  | 206 |  |  | 207 |  |  | 208 |  |  | 209 |  |  | 210 |  |  | 211 |  |  | 212 |  |  | 213 |  |  | 214 |  |  | 215 |  |  | 216 |  |  | 217 |  |  | 218
CS Approved
[33 empty] | FC |  |  | FC |  |  | FC |  |  | FC |  |  |  | 14 | 4 | 0 | 4 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 423 | 0 | - | 340 | 0 | - | 395 | 0 | - | 370 | 0 | - | 330 | 0 | - | 393 | 0 | - | 387 | 0 | - | 381 | 0 | - | 405 | 0 | - | 425 | E | DFR | 399 | E | DFR | 390 | E | DFR | 373 | E | DFR | 401 | [7 empty] | 5412
|  |  | 88/7 |  |  | 88/8 |  |  | 88/9 |  |  | 88/10 |  |  | 88/11 |  |  | 89/0 |  | River-Wagh uri | 89/1 |  |  | 89/2 |  |  | 89/3 |  |  | 89/4 |  |  | 89/5 |  |  | 89/6 |  |  | 89/7 |  |  | 89/8
|  |  | A+3 |  |  | A+0 |  |  | A-3 |  |  | A+0 |  |  | A-3 |  |  | C2+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+3 |  |  | A+0 |  |  | A+0 |  |  | A+0
|  |  | 219 |  |  | 220 |  |  | 221 |  |  | 222 |  |  | 223 |  |  | 224 |  |  | 225 |  |  | 226 |  |  | 227 |  |  | 228 |  |  | 229 |  |  | 230 |  |  | 231 |  |  | 232
CS Approved
FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 1 | 0 | 1 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | E | WFR | 369.825 | 0 | - | 390 | 0 | - | 387 | 0 | - | 392 | 0 | - | 394 | 0 | - | 401 | 0 | - | 426 | 0 | - | 378 | 0 | - | 422 | 0 | - | 425 | 0 | - | 407 | 0 | - | 378 | 0 | - | 376.944 | 0 | - | 405 | [7 empty] | 5551.769
|  |  | 89/9 |  |  | 90/0 |  |  | 90/1 |  |  | 90/2 |  |  | 90/3 |  |  | 90/4 |  |  | 90/5 |  |  | 90/6 |  |  | 90/7 |  |  | 90/8 |  |  | 90/9 |  |  | 90/10 |  |  | 90/11 |  |  | AP91
|  |  | A+0 |  |  | C1+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+3 |  |  | A+3 |  |  | A-3 |  |  | A+6 |  |  | A+6 |  |  | A-3 |  |  | A+0 |  |  | B2+0
|  |  | 233 |  |  | 234 |  |  | 235 |  |  | 236 |  |  | 237 |  |  | 238 |  |  | 239 |  |  | 240 |  |  | 241 |  |  | 242 |  |  | 243 |  |  | 244 |  |  | 245 |  |  | 246
CS Appproved
[46 empty] | 14 | 0 | 0 | 0 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 402 | 0 | - | 424 | 0 | - | 404 | 0 | - | 398 | 0 | - | 376 | 0 | - | 337 | 0 | - | 368 | 0 | - | 402 | 0 | - | 416 | 0 | - | 399 | 0 | - | 408 | 0 | - | 378 | 0 | - | 369 | 0 | - | 410 | [7 empty] | 5491
|  |  | 91/1 |  |  | 91/2 |  |  | 91/3 |  |  | 91/4 |  |  | 91/5 |  |  | 91/6 |  |  | 91/7 |  |  | 91/8 |  |  | 91/9 |  |  | 91/10 |  |  | AP92 |  |  | 92/1 |  |  | 92/2 |  |  | 92/3
|  |  | A+3 |  |  | A+3 |  |  | A+3 |  |  | A+3 |  |  | A+0 |  |  | A-3 |  |  | A-3 |  |  | A+0 |  |  | A+1.5 |  |  | A+3 |  |  | C2+0 |  |  | A+3 |  |  | A-3 |  |  | A+0
|  |  | 247 |  |  | 248 |  |  | 249 |  |  | 250 |  |  | 251 |  |  | 252 |  |  | 253 |  |  | 254 |  |  | 255 |  |  | 256 |  |  | 257 |  |  | 258 |  |  | 259 |  |  | 260
|  | CS Approved | [23 empty] | DS Submitted
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 416 | 0 | - | 392 | 0 | - | 381 | 0 | - | 380 | 0 | - | 397 | 0 | - | 407 | 0 | - | 412.8 | 0 | - | 0 | 0 | - | 399 | 0 | - | 399 | 0 | - | 399 | 0 | - | 399 | 0 | - | 399 | 0 | - | 399 | [7 empty] | 5179.8
|  |  | 92/4 |  |  | AP93 |  |  | 93/1 |  |  | 93/2 |  |  | 93/3 |  |  | 93/4 |  |  | 93/5 |  |  | 94/0 |  |  | 94/1 |  |  | 94/2 |  |  | 94/3 |  |  | 94/4 |  |  | 94/5 |  |  | 94/6
|  |  | A+3 |  |  | C2+0 |  |  | A+1.5 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+3 |  |  | B2+0 |  |  | A+3 |  |  | A+0 |  |  | A+3 |  |  | A+0 |  |  | A+3 |  |  | A+3
|  |  | 261 |  |  | 262 |  |  | 263 |  |  | 264 |  |  | 265 |  |  | 266 |  |  | 267 |  |  | 268 |  |  | 269 |  |  | 270 |  |  | 271 |  |  | 272 |  |  | 273 |  |  | 274
|  | DS Submitted | [27 empty] | CS Approved
[46 empty] | 14 | 2 | 0 | 2 | 0
[33 empty] | FC |  |  | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 399 | 0 | - | 399 | 0 | - | 399 | 0 | - | 300 | 0 | - | 855 | 0 | - | 300 | 0 | - | 399 | 0 | - | 390 | 0 | - | 390 | 0 | - | 409 | E | WET PADDY | 420 | E | WET PADDY | 423 | 0 | - | 400 | 0 | - | 372 | [7 empty] | 5855
|  |  | 94/7 |  |  | 94/8 |  |  | 94/9 |  |  | AP95 |  |  | AP96 |  | Narmda River | AP97 |  |  | AP98 |  |  | 98/1 |  |  | 98/2 |  |  | 99/0 |  |  | 99/1 |  |  | 99/2 |  |  | 99/3 |  |  | 99/4
|  |  | A+0 |  |  | A+6 |  |  | A+6 |  |  | D60+15 |  |  | D60+55 |  |  | D60+55 |  |  | D60+15 |  |  | A+6 |  |  | A+3 |  |  | C1+0 |  |  | A+3 |  |  | A+3 |  |  | A+3 |  |  | A+0
|  |  | 275 |  |  | 276 |  |  | 277 |  |  | 278 |  |  | 279 |  |  | 280 |  |  | 281 |  |  | 282 |  |  | 283 |  |  | 284 |  |  | 285 |  |  | 286 |  |  | 287 |  |  | 288
CS Approved
EC
[18 empty] | FC | [17 empty] | FC |  |  | FC |  |  | FC |  |  |  | 14 | 4 | 1 | 4 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 474 | 0 | - | 224 | 0 | - | 409 | 0 | - | 374 | 0 | - | 413 | E | WET PADDY | 393 | 0 | - | 435 | 0 | - | 390 | 0 | - | 416 | 0 | - | 403 | 0 | - | 384 | E | WET PADDY | 382 | E | WET PADDY | 407 | E | WET PADDY | 398 | [7 empty] | 5502
|  |  | 99/5 |  |  | 100/0 |  | 132 kV SC PL | 101/0 |  |  | 101/1 |  |  | 102/0 |  |  | 102/1 |  |  | 102/2 |  |  | 102/3 |  |  | 102/4 |  |  | 102/5 |  |  | 102/6 |  |  | 102/7 |  |  | 102/8 |  |  | 102/9
|  |  | A+6 |  |  | C1+9 |  |  | D60+9 |  |  | A+0 |  |  | C1+0 |  |  | A+9 |  |  | A+9 |  |  | A+0 |  |  | A+0 |  |  | A+3 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+3
|  |  | 289 |  |  | 290 |  |  | 291 |  |  | 292 |  |  | 293 |  |  | 294 |  |  | 295 |  |  | 296 |  |  | 297 |  |  | 298 |  |  | 299 |  |  | 300 |  |  | 301 |  |  | 302
CS Approved
[6 empty] | FC | [5 empty] | FC |  |  | FC |  |  | FC | [20 empty] | FC |  |  | FC |  |  |  | 14 | 6 | 0 | 4 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 395 | E | - | 450 | 0 | - | 464 | E | WET PADDY | 385 | E | WET PADDY | 334 | E | WET PADDY | 426 | 0 | - | 411 | 0 | - | 325 | 0 | - | 452 | 0 | - | 245 | 0 | - | 424 | 0 | - | 424.702 | 0 | - | 390 |  | WFR | 350 | [7 empty] | 5475.702
|  |  | 102/10 |  |  | 102/11 |  |  | 103/0 |  |  | 103/1 |  |  | 103/2 |  |  | 103/3 |  |  | 104/0 |  |  | 104/1 |  |  | 104/2 |  |  | 105/0 |  | NH-347 | 106/0 |  |  | 106/1 |  |  | 107/0 |  |  | 107/1
|  |  | A+0 |  |  | A+9 |  |  | C1+3 |  |  | A+6 |  |  | A+0 |  |  | A+3 |  |  | B2+3 |  |  | A+9 |  |  | A+7.5 |  |  | C2+6 |  |  | B2+0 |  |  | A+6 |  |  | C2+3 |  |  | A+0
|  |  | 303 |  |  | 304 |  |  | 305 |  |  | 306 |  |  | 307 |  |  | 308 |  |  | 309 |  |  | 310 |  |  | 311 |  |  | 312 |  |  | 313 |  |  | 314 |  |  | 315 |  |  | 316
CS APProved
EC
|  |  | FC | [5 empty] | FC | [5 empty] | FC |  |  | FC | [8 empty] | FC |  |  | FC |  |  | FC |  |  | FC | [5 empty] | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 9 | 1 | 5 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | WFR | 378 | 0 | - | 434 | 0 | DFR | 415 | 0 | - | 327.835 | 0 | - | 370 | E | DFR | 463 | 0 | - | 289 | 0 | - | 384 | 0 | WFR | 381 | E | WET PADDY | 300 | E | WET PADDY | 337 | E | WET PADDY | 351.969 | 0 | - | 377 | E | WET PADDY | 290 | [7 empty] | 5097.804
|  |  | 107/2 |  |  | 107/3 |  |  | 107/4 |  |  | 107/5 |  |  | 108/0 |  |  | 108/1 |  |  | 108/2 |  |  | 108/3 |  |  | 108/4 |  |  | 108/5 |  |  | 108/6 |  |  | 108/7 |  |  | 109/0 |  |  | 109/1
|  |  | A-3 |  |  | A+3 |  |  | A+3 |  |  | A+3 |  |  | C1+9 |  |  | A+9 |  |  | A+0 |  |  | A+9 |  |  | A+3 |  |  | A-3 |  |  | A-3 |  |  | A-3 |  |  | B2+0 |  |  | A+3
ROW
|  |  | 317 |  |  | 318 |  |  | 319 |  |  | 320 |  |  | 321 |  |  | 322 |  |  | 323 |  |  | 324 |  |  | 325 |  |  | 326 |  |  | 327 |  |  | 328 |  |  | 329 |  |  | 330
CS Approved
|  |  | EC | [42 empty] | 14 | 11 | 0 | 0 | 0
|  |  | FC | [8 empty] | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC | [5 empty] | FC |  |  | FC |  |  | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | E | WET PADDY | 426 | 0 | WET PADDY | 408 | 0 | - | 413 | E | DFR | 386 | E | DFR | 360 | E | DFR | 435 | 0 | - | 414 | 0 | DFR | 413 | E | DFR | 405 | 0 | DFR | 423.811 | 0 | - | 449 | E | DFR | 395 | E | DFR | 357 | E | DFR | 423 | [7 empty] | 5707.811
|  |  | 109/2 |  |  | 109/3 |  |  | 109/4 |  |  | 109/5 |  |  | 109/6 |  |  | 109/7 |  |  | 109/8 |  |  | 109/9 |  |  | 109/10 |  |  | 109/11 |  |  | 110/0 |  |  | 110/1 |  |  | 110/2 |  |  | 110/3
|  |  | A+0 |  |  | A+9 |  |  | A-3 |  |  | A+3 |  |  | A+3 |  |  | A+3 |  |  | A+3 |  |  | A+3 |  |  | A-3 |  |  | A+3 |  |  | D45+3 |  |  | A+7.5 |  |  | A+0 |  |  | A+0
|  |  | 331 |  |  | 332 |  |  | 333 |  |  | 334 |  |  | 335 |  |  | 336 |  |  | 337 |  |  | 338 |  |  | 339 |  |  | 340 |  |  | 341 |  |  | 342 |  |  | 343 |  |  | 344
CS Appproved
[10 empty] | EC |  | EC
|  |  | FC | [5 empty] | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC | [24 empty] | 14 | 6 | 2 | 5 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | DFR | 329 | 0 | - | 373 | E | DFR | 419 | E | DFR | 397 | E | WFR | 374 | E | DFR | 390 | E | DFR | 385 | 0 | - | 432 | 0 | - | 391 | 0 | - | 230 | 0 | - | 286 | 0 | - | 475 | 0 | - | 229 | 0 | - | 218 | [7 empty] | 4928
|  |  | 110/4 |  |  | 111/0 |  |  | 111/1 |  |  | 111/2 |  |  | 111/3 |  |  | 111/4 |  |  | 111/5 |  |  | 111/6 |  |  | 111/7 |  |  | 111A/0 |  | Rly | 111B/0 |  |  | 111B/1 |  |  | 112/0 |  | 132 kV SC PL | 113/0
|  |  | A+0 |  |  | D45+6 |  |  | A+0 |  |  | A+3 |  |  | A+0 |  |  | A+0 |  |  | A+6 |  |  | A+0 |  |  | A+0 |  |  | D60+9 |  |  | D60+6 |  |  | A+0 |  |  | D45+18 |  |  | B1+9 (RC = 3M)
|  |  | 345 |  |  | 346 |  |  | 347 |  |  | 348 |  |  | 349 |  |  | 350 |  |  | 351 |  |  | 352 |  |  | 353 |  |  | 354 |  |  | 355 |  |  | 356 |  |  | 357 |  |  | 358
CS Appproved
[19 empty] | EC |  | EC
[18 empty] | FC |  |  | FC | [24 empty] | 14 | 2 | 2 | 2 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 187 | 0 | - | 595 | 0 | - | 310 | 0 | - | 325 | 0 | - | 410 | E | DFR | 424 | E | DFR | 379 | 0 | - | 378 | 0 | - | 384 | 0 | - | 254 | 0 | - |  | 0 | - | 244 | 0 | - | 246 | 0 | - | 518 | [7 empty] | 4654
|  |  | 114/0 |  | 132 kV SC PL | 115/0 |  |  | 115/1 |  |  | 115/2 |  |  | 116/0 |  |  | 116/1 |  |  | 116/2 |  |  | 116/3 |  |  | 117/0 |  |  | 117/1 |  | Rly | 118/0 |  | NH-52 | 119/0 |  | 220 kV SC PL | 120/0 |  |  | 121/0
|  |  | B1+18 |  |  | D45+18 |  |  | B1+3(RC 1M) |  |  | A+0 |  |  | C1+3 |  |  | A+3 |  |  | A+3 |  |  | A+9 |  |  | B2+3 |  |  | A+0 |  |  | B1+0 |  |  | C1+18(RC2M) |  |  | D45+18 |  |  | B2+0
|  |  | 359 |  |  | 360 |  |  | 361 |  |  | 362 |  |  | 363 |  |  | 364 |  |  | 365 |  |  | 366 |  |  | 367 |  |  | 368 |  |  | 369 |  |  | 370 |  |  | 371 |  |  | 372
CS Approved
|  |  |  | FC |  | EC | [6 empty] | EC |  |  | EC |  |  | EC |  |  | EC | [16 empty] | EC
|  |  | FC |  |  | FC | [5 empty] | FC |  |  | FC |  |  | FC |  |  | FC | [5 empty] | FC |  |  | FC | [8 empty] | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 9 | 6 | 7 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | E | DFR | 430 | E | DFR | 415 | 0 | - | 415 | E | DFR | 425 | E | DFR | 415 |  | DFR | 400 | E | WFR | 337 | 0 | - | 331 | 0 | - | 442 | E | DFR | 435 | 0 | - | 297.195 | 0 | - | 322 | E | WFR | 451 | 0 | - | 379.154 | [7 empty] | 5494.349
|  |  | 121/1 |  |  | 121/2 |  |  | 121/3 |  |  | 121/4 |  |  | 121/5 |  |  | 121/6 |  |  | 121/7 |  |  | 121/8 |  |  | 121/9 |  |  | 121/10 |  |  | 122/0 |  |  | 122/1 |  |  | 122/2 |  |  | 123/0
|  |  | A+0 |  |  | A+6 |  |  | A+3 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | B1+3 |  |  | A+9 |  |  | B1+3 |  |  | B1+9 |  |  | A+0 |  |  | B2+0
|  |  | 373 |  |  | 374 |  |  | 375 |  |  | 376 |  |  | 377 |  |  | 378 |  |  | 379 |  |  | 380 |  |  | 381 |  |  | 382 |  |  | 383 |  |  | 384 |  |  | 385 |  |  | 386
CS Appproved
[28 empty] | EC | [14 empty] | EC
|  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC | [5 empty] | FC | [5 empty] | FC |  |  |  | 14 | 12 | 2 | 9 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | E | WFR | 365 | E | WFR | 371 | E | DFR | 395 | E | WET | 449 | E | - | 394.576 | E | WET PADDY | 455 | E | WFR | 393 | E | WFR | 452 | E | WFR | 396 | 0 | - | 442 | 0 | - | 407 | 0 | - | 424 | 0 | WFR | 319 |  | DFR | 409 | [7 empty] | 5671.576
|  |  | 123/1 |  |  | 123/2 |  |  | 123/3 |  |  | 123/4 |  |  | 124/0 |  |  | 124/1 |  |  | 124/2 |  |  | 124/3 |  |  | 124/4 |  |  | 124/5 |  |  | 124/6 |  |  | 125/0 |  |  | 125/1 |  |  | 125/2
|  |  | A+0 |  |  | A+0 |  |  | A+9 |  |  | A+0 |  |  | B2+0 |  |  | A+6 |  |  | A+6 |  |  | A+9 |  |  | A+3 |  |  | A+6 |  |  | A+6 |  |  | B2+3 |  |  | A+3 |  |  | A+3
|  |  | 387 |  |  | 388 |  |  | 389 |  |  | 390 |  |  | 391 |  |  | 392 |  |  | 393 |  |  | 394 |  |  | 395 |  |  | 396 |  |  | 397 |  |  | 398 |  |  | 399 |  |  | 400
CS Approved
|  |  |  | EC | [11 empty] | EC |  |  | EC |  | EC | [11 empty] | EC |  |  |  | EC
|  |  | FC |  |  | FC | [5 empty] | FC |  |  | FC |  |  | FC |  |  | FC | [5 empty] | FC | [5 empty] | FC |  |  | FC |  |  | FC |  |  | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 11 | 6 | 8 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  |  | DFR | 422 | 0 | - | 422.541 | 0 | - | 449 | E | WFR | 305 | E | DFR | 439 | E | DFR | 409 | E | DFR | 422 | 0 | - | 390 | E | - | 404 | 0 | - | 331 | E | DFR | 368 | E | DFR | 389 | 0 | - | 390.104 | E | DFR | 406 | [7 empty] | 5546.645
|  |  | 125/3 |  |  | 126/0 |  |  | 126/1 |  |  | 126/2 |  |  | 126/3 |  |  | 126/4 |  |  | 126/5 |  |  | 126/6 |  |  | 126/7 |  |  | 126/8 |  |  | 126/9 |  |  | 126/10 |  |  | 127/0 |  |  | 127/1
|  |  | A+6 |  |  | C2+0 |  |  | A+9 |  |  | A+9 |  |  | A+3 |  |  | A+0 |  |  | A+3 |  |  | A+3 |  |  | A+0 |  |  | A+0 |  |  | A+3 |  |  | A+0 |  |  | B1+0 |  |  | A+3
|  |  | 401 |  |  | 402 |  |  | 403 |  |  | 404 |  |  | 405 |  |  | 406 |  |  | 407 |  |  | 408 |  |  | 409 |  |  | 410 |  |  | 411 |  |  | 412 |  |  | 413 |  |  | 414
CS Appproved
[46 empty] | 14 | 6 | 0 | 4 | 0
|  |  | FC |  |  | FC |  |  | FC | [8 empty] | FC | [20 empty] | FC |  |  | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | E | DFR | 399 | 0 | - | 400 | E | WFR | 375 | 0 | - | 403 | 0 | - | 347 | E | DFR | 358 | 0 | - | 389 | 0 | - | 335 | 0 | - | 367 | 0 | - | 411.68 | 0 | - | 250 | 0 | - | 395.203 | 0 | DFR | 414 | E | DFR | 396 | [7 empty] | 5239.883
|  |  | 127/2 |  |  | 127/3 |  |  | 127/4 |  |  | 127/5 |  |  | 127/6 |  |  | 127/7 |  |  | 127/8 |  |  | 127/9 |  |  | 127/10 |  |  | 128/0 |  | 765 kV SC PL | 129/0 |  |  | 129A/0 |  |  | 129A/1 |  |  | 129A/2
|  |  | A+0 |  |  | A+0 |  |  | A+3 |  |  | A+4.5 |  |  | A-3 |  |  | A-3 |  |  | A-3 |  |  | A+0 |  |  | B1+3 |  |  | DN+36 |  |  | DN+48 |  |  | C1+9 |  |  | A-3 |  |  | A+7.5
ROW
|  |  | 415 |  |  | 416 |  |  | 417 |  |  | 418 |  |  | 419 |  |  | 420 |  |  | 421 |  |  | 422 |  |  | 423 |  |  | 424 |  |  | 425 |  |  | 426 |  |  | 427 |  |  | 428
CS Approved
|  |  | EC |  |  |  | EC | [22 empty] | EC |  |  |  | EC |  |  | EC
|  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC | [8 empty] | FC | [5 empty] | FC |  |  | FC |  |  | FC | [9 empty] | 14 | 9 | 5 | 6 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | E | DFR | 382 | E | DFR | 408 | 0 | DFR | 421 | E | WFR | 401 | 0 | DFR | 448 | 0 | - | 384 | 0 | - | 400 | 0 | DFR | 443 | 0 | - | 313.311 | E | DFR | 292.997 | E | WET PADDY | 448 | E | WFR | 383 | 0 | - | 446 | 0 | - | 403 | [7 empty] | 5573.308
|  |  | 129A/3 |  |  | 129A/4 |  |  | 129A/5 |  |  | 129A/6 |  |  | 129A/7 |  |  | 129A/8 |  |  | 129A/9 |  |  | 129A/10 |  |  | 130/0 |  |  | 130/1 |  |  | 130/2 |  |  | 130/3 |  |  | 130/4 |  |  | 130/5
|  |  | A+3 |  |  | A+6 |  |  | A+9 |  |  | A+9 |  |  | A+1.5 |  |  | A+0 |  |  | A+4.5 |  |  | A+1.5 |  |  | B2+0 |  |  | A+0 |  |  | A+6 |  |  | A+3 |  |  | A+6 |  |  | B1+9
|  |  | 429 |  |  | 430 |  |  | 431 |  |  | 432 |  |  | 433 |  |  | 434 |  |  | 435 |  |  | 436 |  |  | 437 |  |  | 438 |  |  | 439 |  |  | 440 |  |  | 441 |  |  | 442
CS Approved
[28 empty] | EC |  | EC |  |  | EC |  |  |  | EC | [5 empty] | EC
[27 empty] | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  |  | 14 | 6 | 5 | 0 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 464.078 | 0 | - | 180 | 0 | - | 360 | 0 | - | 310 | 0 | - | 362 | 0 | - | 251 | 0 | - | 222 | 0 | - | 451 | 0 | WFR | 394 | 0 | WFR | 452 | 0 | DFR | 396 | 0 | DFR | 435 | 0 | DFR | 407 | 0 | DFR | 439 | [7 empty] | 5123.078
|  |  | 131/0 |  | 220KV D/C | 132/0 |  |  | 132/1 |  |  | 132/2 |  |  | 132/3 |  |  | 133/0 |  | NH | 134/0 |  |  | 134/1 |  |  | 134/2 |  |  | 134/3 |  |  | 134/4 |  |  | 134/5 |  |  | 134/6 |  |  | 134/7
|  |  | D45+9 |  |  | D45+9 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | B1+0 |  |  | B2+6 |  |  | A+9 |  |  | A+3 |  |  | A+6 |  |  | A+3 |  |  | A+0 |  |  | A+3 |  |  | A+3
|  |  | 443 |  |  | 444 |  |  | 445 |  |  | 446 |  |  | 447 |  |  | 448 |  |  | 449 |  |  | 450 |  |  | 451 |  |  | 452 |  |  | 453 |  |  | 454 |  |  | 455 |  |  | 456
CS Approved
|  |  |  | EC |  |  | EC | [8 empty] | EC |  |  | EC |  |  | EC |  |  | EC |  |  | EC | [8 empty] | EC
|  |  | FC |  |  | FC | [5 empty] | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 13 | 8 | 10 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  |  | WFR | 410 | E | WET PADDY | 384 | 0 | - | 372.658 | 0 | - | 526.704 | E | WET PADDY | 455 | E | WET PADDY | 394 | 0 | DFR | 444 | E | WET PADDY | 405 | E | WET PADDY | 404 | E | WET PADDY | 400 | E | WET PADDY | 401 | E | WET PADDY | 384 | E | WET PADDY | 383 | E | - | 397 | [7 empty] | 5760.362
|  |  | 134/8 |  |  | 134/9 |  |  | 135/0 |  |  | 136/0 |  |  | 136/1 |  |  | 136/2 |  |  | 136/3 |  |  | 136/4 |  |  | 136/5 |  |  | 136/6 |  |  | 136/7 |  |  | 136/8 |  |  | 136/9 |  |  | 139/0
|  |  | A+3 |  |  | A+0 |  |  | B2+9 |  |  | C2+9 |  |  | A+0 |  |  | A+3 |  |  | A+3 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | B2+0
|  |  | 457 |  |  | 458 |  |  | 459 |  |  | 460 |  |  | 461 |  |  | 462 |  |  | 463 |  |  | 464 |  |  | 465 |  |  | 466 |  |  | 467 |  |  | 468 |  |  | 469 |  |  | 470
CS Approved
|  |  |  | EC |  |  | EC | [7 empty] | EC
|  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC | [27 empty] | 14 | 6 | 3 | 0 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 425 |  | DFR | 419 | 0 | DFR | 420 | 0 | - | 403 | 0 | DFR | 398 | 0 | DFR | 385 | 0 | - | 390 | 0 | - | 435.775 | 0 | - | 192.579 | [22 empty] | 3468.354
|  |  | 139/1 |  |  | 139/2 |  |  | 139/3 |  |  | 139/4 |  |  | 139/5 |  |  | 139/6 |  |  | 139/7 |  | 132 KV D/C | 140/0 |  |  | 141/0
|  |  | A+3 |  |  | A+0 |  |  | A+3 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | C2+9 |  |  | D45+9
|  |  | 471 |  |  | 472 |  |  | 473 |  |  | 474 |  |  | 475 |  |  | 476 |  |  | 477 |  |  | 478 |  |  | 479 |  |  | 480 |  |  | 481 |  |  | 482 |  |  | 483 |  |  | 484
[46 empty] | 480 | 161 | 61 | 104 | 0 | 0 | 185.065
Cummulative Progress
[11 empty] | INDEX | [19 empty] | Foundation Cumulative |  |  |  |  | Nos. |  | 161
[31 empty] | Earthing Cumulative |  |  |  |  | Nos. |  | 104
|  |  | Suspension Tower |  |  |  | Angel Tower | [23 empty] | Erection Cumulative |  |  |  |  | Nos. |  | 61
[5 empty] | Tower Erection | [25 empty] | Tack Welding |  |  |  |  | Nos.
[31 empty] | Stringing Paying out Cumulative |  |  |  |  | Km.
[31 empty] | Stringing Final sag Cumulative |  |  |  |  | Km.
Tack Welding
|  |  |  | C | B |  | C | B | Foundation
|  |  |  | D | A |  | D | A
|  |  |  | Classification | [9 empty] | Gas Pipe Line |  | NH/SH crossings |  | Railway |  | Power Line |  | River
Earthing
[15 empty] | Stringing Paying Out |  |  |  | Stringing Final Sag
OPGW Final Sag
Earthing completed
c
Note on I118: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR- Indore to Manmad

## Visual chart
Visual Chart | [31 empty] | 2026-06-27
Name of the Line : |  |  |  | ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 | [17 empty] | Completed
Name of Project: |  |  |  | TL06 | [17 empty] | DS (Aprd) | CS (Aprd) | SOIL INVSTGN | FOUNDATION |  |  | TOWER ERECTION |  |  |  | TW | TIG & PUN | STR P/O | STR F/S | OPGW STR
Name of Contractor: |  |  |  | KEC International Limited
[25 empty] | TOTAL | COMP. | BAL. | EAR | TOTAL | COMP. | BAL.
PROGRESS AT A GLANCE : | [10 empty] | CROSSING PROPOSAL STATUS :
Sl. No. | Activity |  |  | UoM | Total Qty |  | Completed Till Date |  | Balance |  | Sl. No. | Type of Crossing |  |  |  | No. of X-ing |  | Approved |  | Balance
1 | Detailed Survey |  |  | Kms | 184.986 |  | 178.3635 |  | 0 |  | 1 | Powerline X-ing |  |  |  | 12 |  | 12 |  | 0
2 | Check Survey |  |  | Kms | 184.986 |  | 166.5311 |  | 18.4549 |  | TRUE | 123 kV |  |  |  | 8 |  | 8 |  | 0
3 | Soil Investigation |  |  | Nos. | 32 |  | 17 |  | 15 |  | TRUE | 220 kV |  |  |  | 2 |  | 2 |  | 0
4 | Foundation |  |  | Nos. | 480 |  | 165 |  | 315 |  | TRUE | 400 kV |  |  |  | 1 |  | 1 |  | 0
5 | Earthing |  |  | Nos. | 480 |  | 106 |  | 374 |  | TRUE | 765 kV |  |  |  | 1 |  | 1 |  | 0
6 | Erection |  |  | Nos. | 480 |  | 77 |  | 403 |  | 2 | RLY X-ING |  |  |  | 2 |  | 0 |  | 2
7 | Tack Welding |  |  | Nos. | 480 |  | 0 |  | 480 |  | 3 | NH X-ING |  |  |  | 4 |  | 0 |  | 4
8 | Stringing (P/O) |  |  | Kms | 184.986 |  | 0 |  | 184.986 |  | 4 | BPCL |  |  |  | 1 |  | 0 |  | 1
9 | Stringing (F/S) |  |  | Kms | 184.986 |  | 0 |  | 184.986
1 | OPGW Stringing |  |  | Kms | 184.986 |  | 0 |  | 184.986
[22 empty] | -3.314 | -3.314 |  | 9 | 0 | 0 |  | 9 | 0 | 0
District : Alirajpur_ Tehsil Bhabhra_ (AP-0 to AP37/3) (26.445Kms) &TehSil Jobat_(37/4 to64/0)_( 67/2 to AP69)(29.755Kms)
|  |  | AP0 |  | 0/1 |  | 0/2 |  | 1/0 |  | 2/0 |  | 2/1 |  | 3/0 |  | 3/1 |  | 3/2
|  |  | 0 | 257 | 0 | 402 | 0 | 387 | 0 | 347.5 | 0 | 391 | 0 | 367.5 | 0 | 429 | 0 | 387 | 0 | 346 | 3314
|  |  | B1+9 |  | A+9 |  | A+9 |  | D60-3 |  | D45+3 |  | A-1.5 |  | C2-3 |  | A+4.5 |  | A-3
[22 empty] | -4.07 | -4.07 |  | 10 | 0 | 0 |  | 10 | 0 | 0
A |  |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9
| 3/3 |  | 4/0 |  | 4/1 |  | 6/0 |  | 7/0 |  | 8/0 |  | 9/0 |  | 9/1 |  | 10/0 |  | 10/1
| 0 | 343 | 0 | 458 | 0 | 451.5 | 0 | 483.5 | 0 | 485 | 0 | 372 | 0 | 396 | 0 | 371 | 0 | 354 | 0 | 356 | 4070
| A-3 |  | D45+1.5 |  | B1+9 |  | D45+9 |  | B2+0 |  | C2+9 |  | D45+7.5 |  | A-1.5 |  | C1+0 |  | A+0
[22 empty] | 4.0475 | 4.0475 |  | 10 | 0 | 0 |  | 10 | 0 | 0
A | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19
| 10/2 |  | 10/3 |  | 11/0 |  | 11/1 |  | 11/2 |  | 11/3 |  | 11/4 |  | 13/0 |  | 14/0 |  | 15/0
| 0 | 418 | 0 | 320.5 | 0 | 457 | 0 | 413 | 0 | 395 | 0 | 410 | 0 | 349 | 0 | 455 | 0 | 395 | 0 | 435 | 4047.5
| A+4.5 |  | A+7.5 |  | C2-3 |  | B1+9 |  | A+1.5 |  | A+9 |  | A+4.5 |  | C1+7.5 |  | B1+9 |  | D45-3
[22 empty] | 3.424 | 3.424 |  | 10 | 0 | 0 |  | 10 | 0 | 0
| 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29
| 15/1 |  | 16/0 |  | 17/0 |  | 18/0 |  | 19/0 |  | 20/0 |  | 21/0 |  | 22/0 |  | 23/0 |  | 23/1
| 0 | 401 | 0 | 487 | 0 | 177.5 | 0 | 206.5 | 0 | 220.5 | 0 | 434.5 | 0 | 431 | 0 | 440 | 0 | 295 | 0 | 331 | 3424
| A+6 |  | B2+6 |  | D45+4.5 |  | D45+0 |  | D60+0 |  | D45+6 |  | C2+6 |  | D60+0 |  | D60+3 |  | A+0
[22 empty] | 3.991 | 3.991 |  | 10 | 0 | 0 |  | 10 | 0 | 0
| 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39
| 23/2 |  | 23/3 |  | 24/0 |  | 24/1 |  | 24/2 |  | 24/3 |  | 25/0 |  | 26/0 |  | 27/0 |  | 28/0
| 0 | 323 | 0 | 507 | 0 | 426 | 0 | 351 | 0 | 352 | 0 | 422 | 0 | 370 | 0 | 431 | 0 | 429 | 0 | 380 | 3991
| A+9 |  | A-3 |  | D45+6 |  | A+7.5 |  | A+4.5 |  | A+7.5 |  | C2+9 |  | D60+0 |  | D60+6 |  | B2+4.5
[22 empty] | 3.5955 | 3.5955 |  | 10 | 0 | 0 |  | 10 | 0 | 0
| 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49
| 28/1 |  | 29/0 |  | 29/1 |  | 30/0 |  | 30/1 |  | 31/0 |  | 31/1 |  | 31A/0 |  | 32/0 |  | 32A/0
| 0 | 440 | 0 | 406 | 0 | 443 | 0 | 319 | 0 | 405 | 0 | 255 | 0 | 272 | 0 | 421 | 0 | 270 | 0 | 364.5 | 3595.5
| A-1.5 |  | C1-3 |  | A-3 |  | D60+0 |  | A+0 |  | B2-3 |  | A-1.5 |  | C1+0 |  | C2+3 |  | D45-3
[22 empty] | 4.003 | 4.003 |  | 10 | 0 | 0 |  | 10 | 0 | 0
| 50 |  | 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59
| 33/0 |  | 33/1 |  | 34/0 |  | 34/1 |  | 35/0 |  | 36/0 |  | 36/1 |  | 37/0 |  | 37/1 |  | 37/2
| 0 | 430 | 0 | 320 | 0 | 286 | 0 | 461 | 0 | 445 | 0 | 407 | 0 | 401 | 0 | 407 | 0 | 376 | 0 | 470 | 4003
| C1-3 |  | A-1.5 |  | C2-3 |  | A+6 |  | B2+3 |  | C1+3 |  | A-1.5 |  | C1+3 |  | A+4.5 |  | A+3
[22 empty] | 4.051 | 4.051 |  | 10 | 0 | 0 |  | 10 | 0 | 0
| 60 |  | 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69
| 37/3 |  | 37/4 |  | 37/5 |  | 37/6 |  | 38/0 |  | 38/1 |  | 39/0 |  | 39/1 |  | 39/2 |  | 39/3
| 0 | 379 | 0 | 359 | 0 | 398 | 0 | 428 | 0 | 508 | 0 | 314 | 0 | 388 | 0 | 428 | 0 | 366 | 0 | 483 | 4051
| A+4.5 |  | A+7.5 |  | A+6 |  | A+7.5 |  | B2+3 |  | A+9 |  | C2+1.5 |  | A+9 |  | A-3 |  | A+9
[22 empty] | 3.926 | 3.926 |  | 10 | 0 | 0 |  | 10 | 0 | 0
| 70 |  | 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79
| 40/0 |  | 40/1 |  | 40/2 |  | 40/3 |  | 40/4 |  | 40/5 |  | 41/0 |  | 41A/0 |  | 41A/1 |  | 41B/0
| 0 | 350 | 0 | 382 | 0 | 375 | 0 | 473 | 0 | 376 | 0 | 473 | 0 | 396 | 0 | 365 | 0 | 365 | 0 | 371 | 3926
| C1+7.5 |  | A-1.5 |  | A+9 |  | A+9 |  | A+6 |  | A+9 |  | C2+4.5 |  | C2-1.5 |  | A+3 |  | B1+0
[22 empty] | 3.341 | 3.341 |  | 10 | 0 | 0 |  | 10 | 0 | 0
| 80 |  | 81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89
| 41B/1 |  | 41B/2 |  | 42/0 |  | 42/1 |  | 42/2 |  | 43/0 |  | 43/1 |  | 44/0 |  | 44/1 |  | 45/0
| 0 | 360 | 0 | 384 | 0 | 301 | 0 | 444 | 0 | 367.5 | 0 | 229 | 0 | 268.5 | 0 | 318 | 0 | 363.5 | 0 | 305.5 | 3341
| A+1.5 |  | A-1.5 |  | D45-3 |  | A+9 |  | A+3 |  | D45-3 |  | A+1.5 |  | D45-3 |  | A+6 |  | C2-1.5
[22 empty] | 3.452 | 3.452 |  | 10 | 0 | 10 |  | 10 | 0 | 10
| 90 |  | 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99
| 46/0 |  | 47/0 |  | 47/1 |  | 47/2 |  | 48/0 |  | 48/1 |  | 48/2 |  | 48/3 |  | 48/4 |  | 49/0
| 0 | 214 | 0 | 443.999 | 0 | 398 | 0 | 313 | 0 | 237 | 0 | 325 | 0 | 306 | 0 | 361 | 0 | 398 | 0 | 456 | 3451.999
| D60+43 |  | D60+25 |  | A+3 |  | A+0 |  | C2-3 |  | A+3 |  | A-3 |  | A-1.5 |  | A-3 |  | D45+9
400KV PL
[22 empty] | 3.6471 | 3.6471 |  | 10 | 0 | 10 |  | 10 | 0 | 10
| 100 |  | 101 |  | 102 |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109
| 49N/0 |  | 49N/1 |  | 50/0 |  | 51/0 |  | 51/1 |  | 51/2 |  | 52/0 |  | 52/1 |  | 53/0 |  | 54/0
| 0 | 330 | 0 | 446 | 0 | 233.6 | 0 | 420 | 0 | 338 | 0 | 229 | 0 | 397 | 0 | 372.5 | 0 | 456.5 | 0 | 424.5 | 3647.1
| B2+3 |  | A+0 |  | D60+6 |  | D60+9 |  | A-3 |  | A-1.5 |  | C2-3 |  | A-3 |  | D45-3 |  | D45+9
[22 empty] | 3.968 | 3.968 |  | 10 | 0 | 10 |  | 10 | 0 | 10
| 110 |  | 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119
| 55/0 |  | 55/1 |  | 55/2 |  | 56/0 |  | 56/1 |  | 57/0 |  | 57/1 |  | 58/0 |  | 58/1 |  | 58/2
| 0 | 362.996 | 0 | 398.003 | 0 | 436.001 | 0 | 362.999 | 0 | 373 | 0 | 333 | 0 | 497 | 0 | 356 | 0 | 435 | 0 | 414 | 3967.999
| C1+9 |  | A-3 |  | A+6 |  | B2+9 |  | A+9 |  | C1+3 |  | A+9 |  | C2+9 |  | A+7.5 |  | A+9
| 120 |  | 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126 |  | 127 |  | 128 |  | 129 |  |  | 3.7215 | 3.7215 |  | 10 | 0 | 10 |  | 10 | 0 | 10
| 58/3 |  | 59/0 |  | 60/0 |  | 60/1 |  | 61/0 |  | 62/0 |  | 62/1 |  | 62/2 |  | 62/3 |  | 63/0
| 0 | 435 | 0 | 258 | 0 | 383 | 0 | 271 | 0 | 392.003 | 0 | 438 | 0 | 410 | 0 | 367 | 0 | 394.5 | 0 | 373 | 3721.503
| A+3 |  | D45+9 |  | D45+6 |  | A-1.5 |  | D45-3 |  | C2-3 |  | A+0 |  | A+3 |  | A+3 |  | C1+9
132KV
| 130 |  | 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  |  | 4.073 | 4.073 |  | 10 | 2 | 8 |  | 10 | 2 | 8
| 63/1 |  | 63/2 |  | 63/3 |  | 63/4 |  | 64/0 |  | 64/1 |  | 64/2 |  | 64/3 |  | 64/4 |  | 64/5
| 0 | 339 | 0 | 480 | WIP | 314 | WIP | 499 | 0 | 388 | 0 | 382 | 0 | 437 | 0 | 385 | C | 436 | C | 413 | 4073
| B1+9 |  | B1+9 |  | A-3 |  | A+0 |  | B2+0 |  | A+0 |  | A+0 |  | A+3 |  | A+0 |  | A+3
| 140 |  | 141 |  | 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  |  | 3.926 | 3.926 |  | 10 | 0 | 10 |  | 10 | 0 | 10
| 65/0 |  | 65/1 |  | 66/0 |  | 67/0 |  | 67/1 |  | 67/2 |  | 67/3 |  | 68/0 |  | 68/1 |  | 68/2
| 0 | 405 | WIP | 351 | 0 | 369.995 | 0 | 352 | 0 | 432 | 0 | 417 | ROW | 428 | 0 | 378.999 | WIP | 396 | WIP | 396 | 3925.994
| B2+0 |  | A+0 |  | D45+0 |  | D60+0 |  | A+0 |  | A+6 |  | A+6 |  | D45+0 |  | A+0 |  | A+3
| 150 |  | 151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  |  | 3.778 | 3.778 |  | 10 | 8 | 2 |  | 10 | 8 | 2 | 6
| 69/0 |  | 69/1 |  | 69/2 |  | 69/3 |  | 69/4 |  | 70/0 |  | 70/1 |  | 70/2 |  | 70/3 |  | 71/0
| 0 | 399.999 | C | 397 | C | 378.998 | C | 379 | C | 353 | C | 280 | C | 372 | C | 474 | C | 309 | 0 | 435 | 3777.997
| D45+0 |  | A+0 |  | A+0 |  | A+0 |  | A+0 |  | C2-3 |  | A+4.5 |  | A+9 |  | A-3 |  | D45+3
| 160 |  | 161 |  | 162 |  | 163 |  | 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169 |  |  | 3.846 | 3.846 |  | 10 | 6 | 4 |  | 10 | 6 | 4 | 2
| 71/1 |  | 71/2 |  | 71/3 |  | 71/4 |  | 71/5 |  | 72/0 |  | 72/1 |  | 73/0 |  | 74/0 |  | 75/0
| C | 411 | C | 322 | C | 374 | C | 389 | C | 420.5 | 0 | 436 | C | 387.5 | 0 | 376 | 0 | 236 | 0 | 494 | 3846
| A+3 |  | A-3 |  | A+0 |  | A-3 |  | A+3 |  | D45+0 |  | A+9 |  | D45+3 |  | D45+9(RC=2.0M) |  | B1+9
| C | [16 empty] | 132kV
| 170 |  | 171 |  | 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179 |  |  | 3.8297 | 3.8297 |  | 10 | 6 | 4 |  | 10 | 6 | 4 | 2
| 75/1 |  | 75/2 |  | 76/0 |  | 76/1 |  | 76/2 |  | 76/3 |  | 76/4 |  | 76/5 |  | 76/6 |  | 77/0
| 0 | 347 | 0 | 337 | 0 | 426 | C | 418.999 | C | 367 | 0 | 431 | C | 403 | C | 438 | C | 356.71 | C | 305 | 3829.709
| A+0 |  | A-3 |  | C2-3 |  | A+6 |  | A+6 |  | A-3 |  | A+0 |  | A+9 |  | A+1.5 |  | B2+0
| 180 |  | 181 |  | 182 |  | 183 |  | 184 |  | 185 |  | 186 |  | 187 |  | 188 |  | 189 |  |  | 3.6162 | 3.6162 |  | 10 | 2 | 8 |  | 10 | 2 | 8 | -6
| 77/1 |  | 78/0 |  | 78/1 |  | 79/0 |  | 79/1 |  | 80/0 |  | 81/0 |  | 82/0 |  | 82/1 |  | 82/2
| C | 337.839 | WIP | 317 | 0 | 317.777 | 0 | 457 | 0 | 389.816 | 0 | 298.846 | 0 | 330.931 | 0 | 338.998 | WIP | 427 | C | 401 | 3616.207
| A-3 |  | C2-3 |  | B1-3 |  | D45+3 |  | A+9 |  | B1-3 |  | B1+6 |  | C1+0 |  | A+0 |  | A+7.5
132kV
| 190 |  | 191 |  | 192 |  | 193 |  | 194 |  | 195 |  | 196 |  | 197 |  | 198 |  | 199 |  |  | 4.0368 | 4.0368 |  | 10 | 2 | 8 |  | 10 | 2 | 8
| 82/3 |  | 83/0 |  | 83/1 |  | 83/2 |  | 83/3 |  | 85/0 |  | 86/0 |  | 87/0 |  | 87/1 |  | 87/2
| C | 479.823 | 0 | 435 | 0 | 410 | 0 | 365 | 0 | 466.431 | 0 | 421.53 | 0 | 208 | 0 | 449 | 0 | 398 | C | 404 | 4036.784
| A+9 |  | C2+0 |  | A+3 |  | A+9 |  | A+9 |  | B1+3 |  | C1+6 |  | C1+9 |  | A+0 |  | A+0
132kV
A | 200 |  | 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207 |  | 208 |  | 209 |  |  | 4.155 | 4.155 |  | 10 | 9 | 1 |  | 10 | 0 | 10
| 87/3 |  | 87/4 |  | 87/5 |  | 88/0 |  | 88/1 |  | 88/2 |  | 88/3 |  | 88/4 |  | 88/5 |  | 88/6
| C | 427 | C | 400 | C | 386 | C | 400 | C | 442 | C | 384 | C | 390 | C | 539 | C | 412 | 0 | 375 | 4155
| A+3 |  | A+0 |  | A+3 |  | C2+3 |  | A+3 |  | A+0 |  | A-3 |  | B1+3 |  | B1+0 |  | A+0
A | 210 |  | 211 |  | 212 |  | 213 |  | 214 |  | 215 |  | 216 |  | 217 |  | 218 |  | 219
[22 empty] | 3.849 | 3.849 |  | 10 | 0 | 10 |  | 10 | 0 | 10
| 88/7 |  | 88/8 |  | 88/9 |  | 88/10 |  | 88/11 |  | 89/0 |  | 89/1 |  | 89/2 |  | 89/3 |  | 89/4
| 0 | 423 | 0 | 340 | 0 | 395 | 0 | 370 | 0 | 330 | 0 | 393 | 0 | 387 | 0 | 381 | 0 | 405 | 0 | 425 | 3849
| A+3 |  | A+0 |  | A-3 |  | A+0 |  | A-3 |  | C2+0 |  | A+0 |  | A+0 |  | A+0 |  | A+0
A | 220 |  | 221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229
[22 empty] | 3.8968 | 3.8968 |  | 10 | 6 | 4 |  | 10 | 0 | 10
| 89/5 |  | 89/6 |  | 89/7 |  | 89/8 |  | 89/9 |  | 90/0 |  | 90/1 |  | 90/2 |  | 90/3 |  | 90/4
| C | 399 | C | 390 | C | 373 | C | 401 | C | 369.825 | C | 390 | 0 | 387 | 0 | 392 | 0 | 394 | 0 | 401 | 3896.825
| A+3 |  | A+0 |  | A+0 |  | A+0 |  | A+0 |  | C1+0 |  | A+0 |  | A+0 |  | A+0 |  | A+0
A | 230 |  | 231 |  | 232 |  | 233 |  | 234 |  | 235 |  | 236 |  | 237 |  | 238 |  | 239
[22 empty] | 4.0439 | 4.0439 |  | 10 | 0 | 10 |  | 10 | 0 | 10
| 90/5 |  | 90/6 |  | 90/7 |  | 90/8 |  | 90/9 |  | 90/10 |  | 90/11 |  | 91/0 |  | 91/1 |  | 91/2
| 0 | 426 | 0 | 378 | 0 | 422 | 0 | 425 | 0 | 407 | 0 | 378 | 0 | 376.944 | 0 | 405 | 0 | 402 | 0 | 424 | 4043.944
| A+3 |  | A+3 |  | A-3 |  | A+6 |  | A+6 |  | A-3 |  | A+0 |  | B2+0 |  | A+3 |  | A+3
| 240 |  | 241 |  | 242 |  | 243 |  | 244 |  | 245 |  | 246 |  | 247 |  | 248 |  | 249
[22 empty] | 3.886 | 3.886 |  | 10 | 0 | 10 |  | 10 | 0 | 10
| 91/3 |  | 91/4 |  | 91/5 |  | 91/6 |  | 91/7 |  | 91/8 |  | 91/9 |  | 91/10 |  | 92/0 |  | 92/1
| 0 | 404 | 0 | 398 | 0 | 376 | 0 | 337 | 0 | 368 | 0 | 402 | 0 | 416 | 0 | 399 | 0 | 408 | 0 | 378 | 3886
| A+3 |  | A+3 |  | A+0 |  | A-3 |  | A-3 |  | A+0 |  | A+1.5 |  | A+3 |  | C2+0 |  | A+3
A | 250 |  | 251 |  | 252 |  | 253 |  | 254 |  | 255 |  | 256 |  | 257 |  | 258 |  | 259 |  |  | 3.9858 | 3.9858 |  | 10 | 9 | 1 | 9 | 10 | 5 | 5
| 92/2 |  | 92/3 |  | 92/4 |  | 93/0 |  | 93/1 |  | 93/2 |  | 93/3 |  | 93/4 |  | 93/5 |  | 94/0
| 0 | 369 | 0 | 410 | 0 | 416 | 0 | 392 | 0 | 381 | 0 | 380 | 0 | 397 | 0 | 407 | 0 | 412.8 | 0 | 421 | 3985.8
| A-3 |  | A+0 |  | A+3 |  | C2+0 |  | A+1.5 |  | A+0 |  | A+0 |  | A+0 |  | A+3 |  | B2+0
A | 260 |  | 261 |  | 262 |  | 263 |  | 264 |  | 265 |  | 266 |  | 267 |  | 268 |  | 269
[22 empty] | 3.899 | 3.899 |  | 10 | 7 | 3 | 6 | 10 | 5 | 5
| 94/1 |  | 94/2 |  | 94/3 |  | 94/4 |  | 94/5 |  | 94/6 |  | 94/7 |  | 94/8 |  | 94/9 |  | 95/0
| 0 | 424 | 0 | 418 | 0 | 424 | 0 | 409 | 0 | 411 | 0 | 412 | 0 | 381 | 0 | 349 | 0 | 341 | 0 | 330 | 3899
| A+4.5 |  | A+0 |  | A+3 |  | A+1.5 |  | A+0 |  | A+1.5 |  | A+0 |  | A-3 |  | A-3 |  | D60+9
| 270 |  | 271 |  | 272 |  | 273 |  | 274 |  | 275 |  | 276 |  | 277 |  | 278 |  | 279
[22 empty] | 4.326 | 4.326 |  | 10 | 9 | 1 | 9 | 10 | 0 | 10
| 96/0 |  | 97/0 |  | 98/0 |  | 98/1 |  | 98/2 |  | 99/0 |  | 99/1 |  | 99/2 |  | 99/3 |  | 99/4
| 0 | 825 | 0 | 300 | 0 | 470 | 0 | 355 | 0 | 352 | 0 | 409 | C | 420 | C | 423 | 0 | 400 | 0 | 372 | 4326
| D60+55 |  | D60+55 |  | D60+9 |  | A+7.5 |  | A-3 |  | C1+0 |  | A+3 |  | A+3 |  | A+3 |  | A+0
River
| 280 |  | 281 |  | 282 |  | 283 |  | 284 |  | 285 |  | 286 |  | 287 |  | 288 |  | 289
[22 empty] | 3.922 | 3.922 |  | 10 | 10 | 0 | 10 | 10 | 5 | 5
| 99/5 |  | 100/0 |  | 101/0 |  | 101/1 |  | 102/0 |  | 102/1 |  | 102/2 |  | 102/3 |  | 102/4 |  | 102/5
| 0 | 474 | 0 | 224 | 0 | 409 | 0 | 374 | 0 | 413 | 0 | 435 | 0 | 390 | 0 | 416 | 0 | 403 | C | 384 | 3922
| A+6 |  | C1+9 |  | D60+9 |  | A+0 |  | C1+0 |  | A+9 |  | A+0 |  | A+0 |  | A+3 |  | A+0
132kV
| 290 |  | 291 |  | 292 |  | 293 |  | 294 |  | 295 |  | 296 |  | 297 |  | 298 |  | 299
[22 empty] | 4.034 | 4.034 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0
| 102/6 |  | 102/7 |  | 102/8 |  | 102/9 |  | 102/10 |  | 102/11 |  | 103/0 |  | 103/1 |  | 103/2 |  | 103/3
| 0 | 382 | C | 393 | C | 407 | C | 398 | C | 395 | C | 450 | 0 | 464 | C | 385 | C | 334 | C | 426 | 4034
| A+0 |  | A+0 |  | A+0 |  | A+3 |  | A+0 |  | A+9 |  | C1+3 |  | A+6 |  | A+0 |  | A+3
| 300 |  | 301 |  | 302 |  | 303 |  | 304 |  | 305 |  | 306 |  | 307 |  | 308 |  | 309
[22 empty] | 3.8337 | 3.8337 |  | 10 | 10 | 0 | 8 | 10 | 7 | 3
| 104/0 |  | 104/1 |  | 104/2 |  | 105/0 |  | 106/0 |  | 106/1 |  | 107/0 |  | 107/1 |  | 107/2 |  | 107/3
| C | 411 | C | 325 | 0 | 452 | 0 | 245 | 0 | 424 | 0 | 424.702 | C | 390 | C | 350 | C | 378 | ROW | 434 | 3833.702
| B2+3 |  | A+9 |  | A+7.5 |  | C2+6 | NH347B | B2+0 |  | A+6 |  | C2+3 |  | A+0 |  | A-3 |  | A+3
| 310 |  | 311 |  | 312 |  | 313 |  | 314 |  | 315 |  | 316 |  | 317 |  | 318 |  | 319
[22 empty] | 3.6188 | 3.6188 |  | 10 | 9 | 1 | 9 | 10 | 4 | 6
| 107/4 |  | 107/5 |  | 108/0 |  | 108/1 |  | 108/2 |  | 108/3 |  | 108/4 |  | 108/5 |  | 108/6 |  | 108/7
| C | 415 | 0 | 327.835 | C | 370 | C | 463 | 0 | 289 | 0 | 384 | C | 381 | C | 300 | C | 337 | C | 351.969 | 3618.804
| A+3 |  | A+3 |  | C1+9 |  | A+9 |  | A+0 |  | A+9 |  | A+3 |  | A-3 |  | A-3 |  | A-3
| 320 |  | 321 |  | 322 |  | 323 |  | 324 |  | 325 |  | 326 |  | 327 |  | 328 |  | 329
[22 empty] | 3.922 | 3.922 |  | 10 | 10 | 0 | 10 | 10 | 9 | 1
| 109/0 |  | 109/1 |  | 109/2 |  | 109/3 |  | 109/4 |  | 109/5 |  | 109/6 |  | 109/7 |  | 109/8 |  | 109/9
| C | 377 | C | 290 | C | 426 | 0 | 408 | 0 | 413 | C | 386 | C | 360 | C | 435 | C | 414 | C | 413 | 3922
| B2+0 |  | A+3 |  | A+0 |  | A+9 |  | A-3 |  | A+3 |  | A+3 |  | A+3 |  | A+3 |  | A+3
| 330 |  | 331 |  | 332 |  | 333 |  | 334 |  | 335 |  | 336 |  | 337 |  | 338 |  | 339
[22 empty] | 3.9708 | 3.9708 |  | 10 | 8 | 2 | 8 | 10 | 7 | 3
| 109/10 |  | 109/11 |  | 110/0 |  | 110/1 |  | 110/2 |  | 110/3 |  | 110/4 |  | 111/0 |  | 111/1 |  | 111/2
| C | 405 | C | 423.811 | 0 | 449 | C | 395 | C | 357 | C | 423 | C | 329 | WIP | 373 | C | 419 | C | 397 | 3970.811
| A-3 |  | A+3 |  | D45+3 |  | A+7.5 |  | A+0 |  | A+0 |  | A+0 |  | D45+6 |  | A+0 |  | A+3
| 340 |  | 341 |  | 342 |  | 343 |  | 344 |  | 345 |  | 346 |  | 347 |  | 348 |  | 349
[15 empty] | Water Shrink/Logged | [6 empty] | 3.41 | 3.41 |  | 3 | 2 | 1 | 2 | 10 | 0 | 10
| 111/3 |  | 111/4 |  | 111/5 |  | 111/6 |  | 111/7 |  | 111A/0 |  | 111B/0 |  | 111B/1 |  | 112/0 |  | 113/0
| C | 374 | C | 390 | C | 385 | 0 | 432 | 0 | 391 | 0 | 230 | 0 | 286 | 0 | 475 | 0 | 229 | 0 | 218 | 3410
| A+0 |  | A+0 |  | A+6 |  | A+0 |  | A+0 |  | D60+9 |  | D60+6 |  | A+0 |  | D45+18 |  | B1+9 (RC = 3M)
[12 empty] | Rlwy | [5 empty] | 132kV
| 350 |  | 351 |  | 352 |  | 353 |  | 354 |  | 355 |  | 356 |  | 357 |  | 358 |  | 359
[22 empty] | 3.646 | 3.646 |  | 3 | 2 | 1 | 2 | 10 | 0 | 10
| 114/0 |  | 115/0 |  | 115/1 |  | 115/2 |  | 116/0 |  | 116/1 |  | 116/2 |  | 116/3 |  | 117/0 |  | 117/1
| 0 | 187 | 0 | 595 | 0 | 310 | 0 | 325 | C | 410 | C | 424 | C | 364 | C | 375 | 0 | 399 | 0 | 257 | 3646
| B1+18 |  | D45+18 |  | B1+3 |  | A+0 |  | C1+3 |  | A+3 |  | A+3 |  | A+9 |  | B2+3 |  | A-3
132kV
| 360 |  | 361 |  | 362 |  | 363 |  | 364 |  | 365 |  | 366 |  | 367 |  | 368 |  | 369
[22 empty] | 3.845 | 3.845 |  | 3 | 2 | 1 | 2 | 10 | 0 | 10
| 118/0 |  | 119/0 |  | 120/0 |  | 121/0 |  | 121/1 |  | 121/2 |  | 121/3 |  | 121/4 |  | 121/5 |  | 121/6
| 0 | 244 | 0 | 246 | 0 | 518 | 0 | 429.996 | C | 415 | C | 415 | 0 | 425 | C | 415 | C | 400 | C | 337 | 3844.996
| B1+0 |  | C1+18(RC2M) |  | D60+18 |  | B2+0 |  | A+0 |  | A+6 |  | A+3 |  | A+0 |  | A+0 |  | A+0
|  | NH 52 |  | 220kV
| 370 |  | 371 |  | 372 |  | 373 |  | 374 |  | 375 |  | 376 |  | 377 |  | 378 |  | 379
[22 empty] | 3.7884 | 3.7884 |  | 3 | 2 | 1 | 2 | 10 | 0 | 10
| 121/7 |  | 121/8 |  | 121/9 |  | 121/10 |  | 122/0 |  | 122/1 |  | 122/2 |  | 123/0 |  | 123/1 |  | 123/2
| C | 394.004 | 0 | 420 | C | 393.996 | C | 297.199 | 0 | 322 | 0 | 451 | C | 379.154 | C | 365 | C | 371 | C | 395 | 3788.353
| A+0 |  | A+9 |  | A+0 |  | A+9 |  | B1+3 |  | B1+9 |  | A+0 |  | B2+0 |  | A+0 |  | A+0
| 380 |  | 381 |  | 382 |  | 383 |  | 384 |  | 385 |  | 386 |  | 387 |  | 388 |  | 389
[22 empty] | 4.1316 | 4.1316 |  | 3 | 2 | 1 | 2 | 10 | 0 | 10
| 123/3 |  | 123/4 |  | 124/0 |  | 124/1 |  | 124/2 |  | 124/3 |  | 124/4 |  | 124/5 |  | 124/6 |  | 125/0
| C | 449 | C | 394.576 | C | 455 | C | 393 | C | 452 | C | 396 | C | 442 | C | 407 | 0 | 424 | C | 319 | 4131.576
| A+9 |  | A+0 |  | B2+0 |  | A+6 |  | A+6 |  | A+9 |  | A+3 |  | A+6 |  | A+6 |  | B2+3
| 390 |  | 391 |  | 392 |  | 393 |  | 394 |  | 395 |  | 396 |  | 397 |  | 398 |  | 399
[22 empty] | 4.0715 | 4.0715 |  | 3 | 2 | 1 | 2 | 10 | 0 | 10
| 125/1 |  | 125/2 |  | 125/3 |  | 126/0 |  | 126/1 |  | 126/2 |  | 126/3 |  | 126/4 |  | 126/5 |  | 126/6
| C | 409 | C | 422 | C | 422.541 | C | 449 | 0 | 305 | C | 439 | C | 409 | C | 422 | C | 390 | 0 | 404 | 4071.541
| A+3 |  | A+3 |  | A+6 |  | C2+0 |  | A+9 |  | A+9 |  | A+3 |  | A+0 |  | A+3 |  | A+3
| 400 |  | 401 |  | 402 |  | 403 |  | 404 |  | 405 |  | 406 |  | 407 |  | 408 |  | 409
[22 empty] | 3.8521 | 3.8521 |  | 3 | 2 | 1 | 2 | 10 | 0 | 10
| 126/7 |  | 126/8 |  | 126/9 |  | 126/10 |  | 127/0 |  | 127/1 |  | 127/2 |  | 127/3 |  | 127/4 |  | 127/5
| C | 375 | 0 | 368 | C | 389 | C | 390.104 | C | 406 | C | 399 | C | 400 | C | 375 | C | 403 | 0 | 347 | 3852.104
| A+0 |  | A+0 |  | A+3 |  | A+0 |  | B1+0 |  | A+3 |  | A+0 |  | A+0 |  | A+3 |  | A+4.5
| 410 |  | 411 |  | 412 |  | 413 |  | 414 |  | 415 |  | 416 |  | 417 |  | 418 |  | 419
[22 empty] | 3.6979 | 3.6979 |  | 3 | 2 | 1 | 2 | 10 | 0 | 10
| 127/6 |  | 127/7 |  | 127/8 |  | 127/9 |  | 127/10 |  | 128/0 |  | 129/0 |  | 129A/0 |  | 129A/1 |  | 129A/2
| 0 | 358 | C | 389 | 0 | 335 | 0 | 367 | 0 | 411.68 | 0 | 250 | C | 395.203 | 0 | 414 | C | 396 | C | 382 | 3697.883
| A-3 |  | A-3 |  | A-3 |  | A+0 |  | B1+0 |  | D60+43 |  | D60+55 |  | C1+9 |  | A-3 |  | A+7.5
765kV
| 420 |  | 421 |  | 422 |  | 423 |  | 424 |  | 425 |  | 426 |  | 427 |  | 428 |  | 429
[22 empty] | 3.9593 | 3.9593 |  | 3 | 2 | 1 | 2 | 10 | 0 | 10
| 129A/3 |  | 129A/4 |  | 129A/5 |  | 129A/6 |  | 129A/7 |  | 129A/8 |  | 129A/9 |  | 129A/10 |  | 130/0 |  | 130/1
| C | 408 | C | 421 | C | 401 | C | 448 | C | 384 | 0 | 400 | 0 | 443 | C | 313.311 | 0 | 292.997 | C | 448 | 3959.308
| A+3 |  | A+6 |  | A+9 |  | A+9 |  | A+1.5 |  | A+0 |  | A+4.5 |  | A+1.5 |  | B2+0 |  | A+0
| 430 |  | 431 |  | 432 |  | 433 |  | 434 |  | 435 |  | 436 |  | 437 |  | 438 |  | 439
[22 empty] | 3.3811 | 3.3811 |  | 3 | 2 | 1 | 2 | 10 | 0 | 10
| 130/2 |  | 130/3 |  | 130/4 |  | 130/5 |  | 131/0 |  | 132/0 |  | 132/1 |  | 132/2 |  | 132/3 |  | 133/0
| C | 383 | C | 446 | 0 | 403 | 0 | 464.078 | 0 | 180 | 0 | 360 | 0 | 310 | C | 362 | 0 | 251 | 0 | 222 | 3381.078
| A+6 |  | A+3 |  | A+6 |  | B1+9 |  | D45+9 |  | D45+9 |  | A+0 |  | A+0 |  | A+0 |  | B1+0
[10 empty] | 220kV | [9 empty] | NH347C
| 440 |  | 441 |  | 442 |  | 443 |  | 444 |  | 445 |  | 446 |  | 447 |  | 448 |  | 449
[22 empty] | 4.1407 | 4.1407 |  | 3 | 2 | 1 | 2 | 10 | 0 | 10
| 134/0 |  | 134/1 |  | 134/2 |  | 134/3 |  | 134/4 |  | 134/5 |  | 134/6 |  | 134/7 |  | 134/8 |  | 134/9
| 0 | 451 | 0 | 394 | C | 452 | C | 396 | C | 435 | C | 407 | C | 439 | C | 410 | C | 384 | C | 372.658 | 4140.658
| B2+6 |  | A+9 |  | A+3 |  | A+6 |  | A+3 |  | A+0 |  | A+3 |  | A+3 |  | A+3 |  | A+0
| 450 |  | 451 |  | 452 |  | 453 |  | 454 |  | 455 |  | 456 |  | 457 |  | 458 |  | 459
[22 empty] | 4.1967 | 4.1967 |  | 3 | 2 | 1 | 7 | 10 | 0 | 10
| 135/0 |  | 136/0 |  | 136/1 |  | 136/2 |  | 136/3 |  | 136/4 |  | 136/5 |  | 136/6 |  | 136/7 |  | 136/8
| C | 526.704 | C | 455 | C | 394 | C | 444 | C | 405 | C | 404 | C | 400 | C | 401 | C | 384 | C | 383 | 4196.704
| B2+9 |  | C2+9 |  | A+0 |  | A+3 |  | A+3 |  | A+0 |  | A+0 |  | A+0 |  | A+0 |  | A+0
| 460 |  | 461 |  | 462 |  | 463 |  | 464 |  | 465 |  | 466 |  | 467 |  | 468 |  | 469
[22 empty] | 3.8654 | 3.8654 |  | 10 | 2 | 8 | 2 | 10 | 0 | 10
| 136/9 |  | 139/0 |  | 139/1 |  | 139/2 |  | 139/3 |  | 139/4 |  | 139/5 |  | 139/6 |  | 139/7 |  | 140/0
| C | 397 | C | 425 | C | 419 | C | 420 | C | 403 | C | 398 | C | 385 | C | 390 | 0 | 435.775 | 0 | 192.579 | 3865.354
| A+0 |  | B2+0 |  | A+3 |  | A+0 |  | A+3 |  | A+0 |  | A+0 |  | A+0 |  | A+0 |  | C2+9
132kV
| 470 |  | 471 |  | 472 |  | 473 |  | 474 |  | 475 |  | 476 |  | 477 |  | 478 |  | 479
[22 empty] | 0 | 0 |  | 1 | 0 | 1 | 0 | 1 | 0 | 1
141/0
0
D45+9
480
[22 empty] | 184.986 | 0 | 0 | 480 | 162 | 318 | 105 | 480 | 68 | 412 | 0
GAS PIPELINE
c
c

## Pile Fdn (hidden)
129/0 Total Pile Completed: 16/16 |  |  | Pile Cap: 4/4 |  |  |  | VISUAL CHART VNTL PILE LOC- 129/0
Leg | PILE NO | PILE COM. DATE | PILE CAP | CH 1ST | CH 2ND | REMARKS | LEG - C | LEG - B
C | 1 | 2026-03-23 | Completed on 02.05.26 | Completed on 11.05.26 | Completed on 11.05.26 | Pile Complete
| 2 | 2026-03-28 |  |  |  | Pile Complete
| 3 | 2026-03-26 |  |  |  | Pile Complete
| 4 | 2026-03-11 |  |  |  | Pile Complete
B | 5 | 2026-02-24 | Completed on 20.04.26 | Completed on 27.04.26 | Completed on 07.05.26 | Pile Complete
| 6 | 2026-03-01 |  |  |  | Pile Complete
| 7 | 2026-02-26 |  |  |  | Pile Complete
| 8 | 2026-03-07 |  |  |  | Pile Complete
A | 9 | 2026-03-10 | Completed on 20.04.26 | Completed on 27.04.26 | Completed on 07.05.26 | Pile Complete | LEG - D | LEG - A
| 10 | 2026-03-16 |  |  |  | Pile Complete
| 11 | 2026-03-13 |  |  |  | Pile Complete
| 12 | 2026-03-18 |  |  |  | Pile Complete
D | 13 | 2026-02-21 | Completed on 03.05.26 | Completed on 09.05.26 | Completed on 11.05.26 | Pile Complete
| 14 | 2026-02-13 |  |  |  | Pile Complete
| 15 | 2026-04-16 |  |  |  | Pile Complete
| 16 | 2026-02-07 |  |  |  | Pile Complete
Sr. No. | Colour Indicate | Identification
1 |  | Complete
2 |  | WIP
3 |  | Not Start
130/0 Total Pile Completed: 16/16 |  |  | Pile Cap: 1/4 |  |  |  | VISUAL CHART VNTL PILE LOC- 130/0
Leg | PILE NO | PILE COM. DATE | PILE CAP | CH 1ST | CH 2ND | REMARKS | LEG - C | LEG - B
C | 1 | 2025-05-25 | Completed on 24.05.26 |  |  | Pile Complete
| 2 | 2025-06-04 |  |  |  | Pile Complete
| 3 | 2025-05-29 |  |  |  | Pile Complete
| 4 | 2025-06-07 |  |  |  | Pile Complete
B | 5 | 2025-05-31 | Completed on 14.05.26 |  |  | Pile Complete
| 6 | 2025-05-22 |  |  |  | Pile Complete
| 7 | 2025-06-06 |  |  |  | Pile Complete
| 8 | 2025-05-26 |  |  |  | Pile Complete
A | 9 | 2025-06-17 | Completed on 24.05.26 |  |  | Pile Complete | LEG - D | LEG - A
| 10 | 2025-06-11 |  |  |  | Pile Complete
| 11 | 2025-06-14 |  |  |  | Pile Complete
| 12 | 2025-05-14 |  |  |  | Pile Complete
D | 13 | 2025-05-15 | Completed on 16.05.26 |  |  | Pile Complete
| 14 | 2025-05-24 |  |  |  | Pile Complete
| 15 | 2025-05-12 |  |  |  | Pile Complete
| 16 | 2025-05-19 |  |  |  | Pile Complete
Sr. No. | Colour Indicate | Identification
1 |  | Complete
2 |  | WIP
3 |  | Not Start
04
03
02
01
LEG - C Cap
1st Step
2nd Step
16
15
14
13
LEG - D Cap
1st Step
2nd Step
08
07
06
05
LEG - B Cap
1st Step
2nd Step
12
11
10
09
LEG - A Cap
1st Step
2nd Step
04
03
02
01
LEG - C Cap
1st Step
2nd Step
16
15
14
13
LEG - D Cap
1st Step
2nd Step
08
07
06
05
LEG - B Cap
1st Step
2nd Step
12
11
10
09
LEG - A Cap
1st Step
2nd Step

## Crossing (hidden)
765KV D/C HEXA VATAMAN - NAVSARI TL -04 - CROSSING STATUS
Sl No | AP NO | Towe Type | AP No | Tower Type | Type of Crossings | Span Length | LINE OWNER | Line Name | Nos. | Work Portion | Status | Submitted to Client for Review | Proposal Submitted (Y/N) | Inspection Status (Y/N) | Remarks
1 | 118/0 | DB2+0 | 119/0 | DD60+0 | Power Line | 243.824 | GETCO | 66 KV S/C NANDEWAR-WAGRA LINE (H FRAME) | 1 | Bharuch | Submitted | 2024-07-10 | Y | Y | Approved
2 | 119/3 | DA+9 | 120/0 | DD60+3 | Power Line | 358.181 | GETCO | 66 KV D/C BHARUCH B TO VAGRA TAP VILAGAT LINE | 1 | Bharuch | Submitted | 2024-07-15 | Y | Y | Approved
3 | 121/0 | DB2+9 | 121/1 | DB1+25 | Power Line | 276.141 | GETCO | 220 kv D/C VAGRA- THAM TSS LINE (U/C) | 1 | Bharuch | Submitted | 2024-09-12 | Y | Y | Approved
4 | 121/11 | DA+9 | 124/0 | DD45+3 | Power Line | 396.394 | GETCO | 66 KV D/C Vilayat - Kukarwada Line | 1 | Bharuch | Submitted | 2024-07-15 | Y | Y | Approved
5 | 136/1 | DB1+9 | 137/0 | DB2+3 | Power Line | 455.963 | GETCO | 66 KV S/C Hansot Robban Line | 1 | Bharuch | Submitted | 2024-09-12 | Y | Y | Approved
6 | 140/0 | DD60+25 | 141/0 | DD60+25 | Power Line | 171.929 | ESSAR | 400 KV D/C HZR-GDR | 1 | Bharuch | Submitted | 2024-11-23 | Y | Y | Approved
7 | 141/6 | DA+3 | 142/0 | DC1+9 | Power Line | 452.63 | GETCO | 66 KV S/C Panoli-Hansot | 1 | Bharuch | Submitted | 2024-07-10 | Y | Y | Approved
8 | 147/0 | DD60+25 | 148/0 | DD60+25 | Power Line | 251.645 | GETCO | 400 KV D/C KOSAMBA - CHORANIA | 1 | Bharuch | Submitted | 2024-07-10 | Y | Y | Approved
9 | 149/0 | DD60+25 | 150/0 | DD60+25 | Power Line | 258.002 | TORRENT | 400 KV D/C DGEN-NAVASARI | 1 | Surat | Submitted | 2024-07-15 | Y | Y | Approved
10 | 155/0 | DD60+18 | 156/0 | DD45+18 | Power Line | 257.341 | POWERGRID | 220 KV D/C KWS-HAL | 1 | Surat | Submitted | 2024-07-15 | Y | Y | Approved
11 | 157/0 | CDDN+41 | 158/0 | CDDN+41 | Power Line | 279.356 | POWERGRID | 765 KV D/C AHMEDABAD-NAVSARI | 1 | Surat | Submitted | 2024-07-15 | Y | Y | Approved
12 | 159/0 | DD60+9 | 160/0 | DC2+0 | Power Line | 410.872 | GETCO | 66 KV S/C DINODA-KHARCH | 1 | Surat | Submitted | 2024-07-15 | Y | Y | Approved
13 | 162/0 | DD60+25 | 163/0 | DD60+30 | Power Line | 328.496 | TORRENT | 400 KV D/C DGEN-NAVASARI | 1 | Surat | Submitted | 2024-07-15 | Y | Y | Approved
14 | 163/0 | DD60+30 | 163/1 | DB1+6 | Power Line | 382.995 | GETCO | 66 KV D/C PALOD-KOSAMBA | 1 | Surat | Submitted | 2024-07-15 | Y | Y | Approved
15 | 164/0 | DC2+6 | 165/0 | DB1+25 | Power Line | 285.055 | GETCO | 220KV D/C GSECL(Hazira)-KOSAMBA | 1 | Surat | Submitted | 2024-07-15 | Y | Y | Approved
16 | 168/0 | DD60+30 | 169/0 | DD60+25 | Power Line | 255.601 | TORRENT | 400 KV D/C SUG-PIR | 1 | Surat | Submitted | 2024-07-22 | Y | Y | Approved
17 | 171/0 | DB1+18 | 172/0 | DD45+9 | Power Line | 186.772 | GETCO | 220 KV D/C KOSAMBA-VAV | 1 | Surat | Submitted | 2024-07-22 | Y | Y | Approved
18 | 173/0 | DC2+18 | 174/0 | DD60+9 | Power Line | 215.227 | GETCO | 220 KV D/C KIM-KOSAMBA | 1 | Surat | Submitted | 2024-07-22 | Y | Y | Approved
19 | 175/0 | DC2+6 | 175/1 | DB1+9 | Power Line | 468.001 | GETCO | 66 KV S/C KIM-MASOLI | 1 | Surat | Submitted | 2024-07-22 | Y | Y | Approved
20 | 177/0 | DD60+6 | 178/0 | DD60+6 | Power Line | 228.09 | TORRENT | 400 KV S/C GHT-TPL | 1 | Surat | Submitted | 2024-07-22 | Y | Y | Approved
21 | 184/0 | DB1+18 | 185/0 | DD45+25 | Power Line | 245.489 | TORRENT Power | 220 KV D/C SUGEN-BHATAR | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
22 | 185/0 | DD45+25 | 186/0 | DC1+18 | Power Line | 266.092 | TORRENT Power | 220 KV D/C SUGNA-PUNE | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
23 | 186/0 | DC1+18 | 187/0 | DC1+0 | Power Line | 370.267 | GETCO | 66 KV S/C KAMRAJ-ARETH | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
24 | 190/0 | DD60+9 | 191/0 | DD60+9 | Power Line | 226.477 | TORRENT Power | 400 KV S/C TPL-VAP | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
25 | 192/0 | DC2+9 | 193/0 | DD60+30 | Power Line | 222.827 | TORRENT Power | 220 KV D/C SUGEN-PUNE | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
26 | 193/0 | DD60+30 | 194/0 | DD60+30 | Power Line | 277.415 | GETCO | 400 KV D/C KOSAMBA-VAV | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
27 | 195/0 | DC1+18 | 196/0 | DB2+18 | Power Line | 239.69 | TORRENT Power | 220 KV D/C SUGEN-BHATAR | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
28 | 201/0 | DC1+9 | 202/0 | DC2+18 | Power Line | 506.5 | GETCO | 66 KV S/C VAV-SHAMPURA | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
29 | 202/0 | DC2+18 | 203/0 | DD60+18 | Power Line | 252.01 | PGCIL | 220 KV D/C KAP-VAV | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Route change pending Approval | r
30 | 204/0 | DD60+25 | 205/0 | DD60+25 | Power Line | 294.335 | PGCIL | 400 KV D/C GND-NAV | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Route change pending Approval
31 | 207/0 | DD60+25 | 208/0 | DD45+35 | Power Line | 272.301 | GETCO | 220 KV D/C | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
32 | 208/0 | DD45+35 | 209/0 | DD60+9 | Power Line | 284.637 | GETCO | 66 KV D/C | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
33 | 210/0 | DB2+9 | 211/0 | DB2+9 | Power Line | 397.662 | GETCO | 66 KV D/C Mota Madhi | 1 | Surat | Submitted | 2024-08-14 | Y | Y | Approved
34 | 210/0 | DB2+9 | 211/0 | DB2+9 | Power Line |  | GETCO | 66 KV D/C MOTA-Moti Fadoo | 1 | Surat | Submitted | 2024-08-14 | Y | Y | Approved
35 | 212/0 | DD45+30 | 213/0 | DD60+35 | Power Line | 378.221 | GETCO | 220kV D/C MOTA - AMBHETA TRANSMISSION LINE | 1 | Surat | Submitted | 2024-08-12 | Y | Y | Approved
36 | 213/0 | DD60+35 | 214/0 | DD60+25 | Power Line | 325.229 | POWERGRID | 400 KV D/C KAKARPAR - NAVSARI TRANSMISSION LINE | 1 | Surat | Submitted | 2024-08-12 | Y | Y | Approved
37 | 216/1 | DA+9 | 216/2 | DB1+18 | Power Line | 388 | GETCO | 66 KV KORODAR- AFVA LINE H FEAM | 1 | Surat | Submitted | 2024-08-12 | Y | Y | Approved
38 | 217/0 | DC2+9 | 217/1 | DA+3 | Power Line | 398.005 | GETCO | 66 KV D/C LINE MOTA TO SARWAN TRANSMISSION LINE | 1 | Surat | Submitted | 2024-08-12 | Y | Y | Approved
39 | 221/0 | DD60+18 | 222/0 | DD60+25 | Power Line | 213.017 | PGCIL | 400 KV D/C NAV-BSR | 1 | Surat | Submitted | 2025-04-14 | Y | Y | Approved
40 | 229/0 | DD45+0 | 230/0 | DC1+6 | Power Line | 179.981 | GETCO | 220 KV D/C Nav-Popda/Nav-Talangpur | 1 | Navsari | Submitted | 2025-04-14 | Y | Y | Approved
41 | 234/0 | DD60+18 | 235/0 | DD60+9 | Power Line | 313.955 | POWERGRID | 220 KV D/C NAVSARI-NAVSARI LINE | 1 | Navsari | Submitted | 2024-08-16 | Y | Y | Approved
42 | 236/0 | DB2+18 | 237/0 | DB1+25 | Power Line | 200.821 | GETCO | 132 KV S/C NAVSARI - POPDA CKT-1 LINE | 1 | Navsari | Submitted | 2024-07-07 | Y | Y | Approved
43 | 236/0 | DB2+18 | 237/0 | DB1+25 | Power Line |  | GETCO | 66 KV D/C NAV-EKL & TAVDI-VESSMA LINE | 1 | Navsari | Submitted | 2024-07-07 | Y | Y | Approved
44 | 237/0 | DB1+25 | 238/0 | DC1+25 | Power Line | 202.277 | GETCO | 132 KV S/C NAV-POPDA CKT-2 LINE | 1 | Navsari | Submitted | 2024-07-07 | Y | Y | Approved
45 | 247/0 | DD60+35 | 248/0 | DD60+35 | Power Line | 286.451 | POWERGRD | 765 KV D/C AHMEDABAD-NAVSARI | 1 | Navsari | Submitted | 2024-12-03 | Y | Y | Approved
46 | 250/3 | DA+9 | 250A/0 | DB1+3 | Power Line | 382.952 | GETCO | 66 KV D/C Talangpur-Mangrol line | 1 | Navsari | Submitted | 2025-01-10 | Y | Y | Approved
47 | 253/0 | DD45+35 | 254/0 | DD45+35 | Power Line | 304.46 | GETCO | LILO OF 220 KV TALANGPORE (SACHIN)-NAVSARI LINE AND TALANGPORE (SACHIN)-VAV LINE AT 765 KV NAVSARI(NEW)S/S OF ISTS | 1 | Navsari | Submitted | 2025-03-14 | Y | Y | Approved
48 | 256/1 | DA+9 | 257/0 | DC1+9 | Power Line | 272.781 | GETCO | 66 KV D/C Mangrol-Ubarhat Line | 1 | Navsari | Submitted | 2024-07-07 | Y | Y | Approved
49 | 151/0 | DD60+6 | 151A/0 | DD60+18 | Railway | 266.99 | IR | KOSAMBA - UMARPADA GAUGE CONVERSION RAILWAY LINE |  |  | Submitted | 2025-11-17 | Y | Y | Approval Pending
50 | 152/0 | DD60+3 | 153/0 | DD60+3 | Railway | 295 | IR | IR RAILWAY LINE DFCC RAILWAY LINE |  |  | Submitted | 2025-11-18 | Y | Y | Approval Pending
51 | 154/0 | DD60+9 | 155/0 | DD60+18 | Railway | 295.36 | IR | KOSAMBA - UMARPADA GAUGE CONVERSION RAILWAY LINE |  |  | Submitted | 2025-11-19 | Y | Y | Approval Pending
52 | 166/0 | DD60+0 | 167/0 | DD60+9 | Railway | 274.311 | IR | RAILWAY LINE NOT IN USE | 1 | Navsari | Submitted | 2024-09-21 | Y | Y | APPROVED
53 | 215/0 | DD60+3 | 216/0 | DD60+3 | Railway | 231.411 | IR | RAILWAY LINE BARDOLI-GANGADHARA | 1 | Navsari | Submitted | 2024-10-26 | Y | Y | Approved
54 | 242/0 | DD60+3 | 243/0 | DD60+3 | Railway | 280.015 | IR | RAILWAY LINE NAVSARI-MAROLI | 1 | Navsari | Submitted | 2024-09-12 | Y | Y | Approved
55 | 234/0 | DD60+18 | 235/0 | DD60+9 | Bullet Train |  | NHSRL | BULLET TRAIN | 1 | Navsari | Submitted | 2024-09-11 | Y | Y | Approved
56 | 143/0 | DD60+18 | 144/0 | DD60+18 | Bullet Train | 252.547 | NHSRL | BULLET TRAIN | 1 | Bharuch | Submitted | 2024-09-16 | Y | Y | Approved
57 | 133/2 | DB1+0 | 133/3 | DB1+0 | NH | 250 | NH | NH 64 ( Delhi - Mumbai ) | 1 | Bharuch | Submitted | 2024-09-04 | Y | Y | Approved
58 | 218/0 | DD60+3 | 219/0 | DD45+3 | NH | 239.469 | NH | NH 53 | 1 | Surat | Submitted | 2025-04-19 | Y | Y | Approved
59 | 231/0 | DB1+0 | 232/0 | DB1+0 | NH | 246.982 | NH | NH 48 | 1 | Navsari | Submitted | 2025-04-18 | Y | Y | Approved
60 | 135/0 | DD60+3 | 136/0 | DD60+6 | NH | 247.871 | Express Way | NE- 4 (Delhi - Mumbai) | 1 | Bharuch | Submitted | 2024-08-24 | Y | Y | Approved
61 | 182/0 | DD45+0 | 183/0 | DD60+0 | NH | 208.909 | Express Way | NE- 4 (Delhi - Mumbai) | 1 | Surat | Submitted | 2024-08-24 | Y | Y | Approved
62 | 222/0 | DD60+25 | 223/0 | DC1+6 | NH | 225.594 | Express Way | NE- 4 (Delhi - Mumbai) | 1 | Surat | Submitted | 2025-04-21 | Y | Y | Approved
63 | 198/0 | DD60+6 | 199/0 | DD60+6 | NH | 246.736 | Express Way | NE- 4 (Delhi - Mumbai) | 1 | Surat | Submitted | 2025-04-17 | Y | Y | Approved
64 | 161/0 | DB1+3 | 162/0 | DD60+25 | NH | 248.002 | NH | NH 48 | 1 | Surat | Submitted | 2024-09-04 | Y | Y | Approved
65 | 133/4 | DA+3 | 134/0 | DD45+0 | Gas Pipe Line |  | GSPL | GSPL (133/4 - 134/0) Gas Pipe Line Crossing | 1 | Bharuch | Submitted | 2024-09-16 | Y | Y | APPROVED
66 | 155/0 | DD60+18 | 156/0 | DD45+18 | Gas Pipe Line |  | GAIL | GAIL (155/0 - 156/0) Gas Pipe Line Crossing | 1 | Surat | Submitted | 2024-09-23 | Y | Y | APPROVED
67 | 233/0 | DC1+0 | 234/0 | DD60+18 | Gas Pipe Line |  | REPL | REPL (233/0 - 234/0) Gas Pipe Line Crossing | 1 | Navsari | Submitted | 2024-09-16 | Y | Y | APPROVED
68 | 233/0 | DC1+0 | 234/0 | DD60+18 | Gas Pipe Line |  | PIL | PIL (233/0 - 234/0) Gas Pipe Line Crossing | 1 | Navsari | Submitted | 2024-09-16 | Y | Y | APPROVED
69 | 239/0 | DD45+0 | 239/1 | DA+0 | Gas Pipe Line |  | GSPL | GSPL (239/0 - 239/1) Gas Pipe Line Crossing | 1 | Navsari | Submitted | 2024-09-16 | Y | Y | APPROVED
70 | 245/0 | DD45+0 | 245/1 | DA+0 | Gas Pipe Line |  | GAIL | GAIL (245/0 - 245/1) Gas Pipe Line Crossing | 1 | Navsari | Submitted | 2024-09-16 | Y | Y | APPROVED

## Survey (hidden)
|  |  | Date | 2026-06-27
Name of Line: Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line
Sl. No. | Particulars | UoM | Qty. | Remarks
1 | Total Section Length | Kms. | 127.7741
2 | Detail Survey Submitted | Kms. | 127.8161
3 | Balance to Submit | Kms. | -0.042
4 | Detail Survey Approved | Kms. | 126.9371
5 | Balance to Approve | Kms. | 0.879
6 | Check Survey Submitted | Kms. | 127.8161
7 | Check Survey Approved | Kms. | 126.9371
8 | Balance to Approve | Kms. | 0.879
9 | Route Diversion Approve with D/Survey Balance | Kms. | 0.879
10 | Balanceto Submit due to Crossing Section | Kms. | -0.879

## Soil Inv. (hidden)
VNTL PROJECT - SOIL INVESTIGATION LOCATIONS
Sl. No. | Loc. No. | TOT | RC | Status | Classification | Approval Letter Status
1 | 121/0 | DB2+9 |  | Done | WBC | Approved
2 | 129/0 | DD45+25 |  | Done | PILE | Approved
3 | 130/0 | DD45+25 |  | Done | PILE | Approved
4 | 131/0 | DD60+9 | 7 | Done | Sandy Dry Soil | Approved
5 | 135/0 | DD60+0 |  | Done | 2 Mtr WBC & 1.5 Mtr FS | Approved
6 | 140/0 | DD60+25 |  | Done | WBC | Approved
7 | 144/0 | DD60+25 |  | Done | WBC | Approved
8 | 147/0 | DD60+25 |  | Done | WBC | Approved
9 | 150/0 | DD60+25 |  | Done | WBC | Approved
10 | 153/0 | DD60+3 |  | Done | WBC | Approved
11 | 158/0 | DD60+41 |  | Done | WBC | Approved
12 | 162/0 | DD60+25 |  | Done | WBC | Approved
13 | 166/0 | DD60+0 |  | Done | WBC | Approved
14 | 169/0 | DD60+25 |  | Done | WBC | Approved
15 | 178/0 | DD60+6 |  | Done | WBC | Approved
16 | 182/0 | DD45+0 |  | Done | WBC | Approved
17 | 191/0 | DD60+9 |  | Done | 2 Mtr WBC & 1.5 Mtr Normal Dry | Approved
18 | 194/0 | DD60+25 |  | Done | WBC | Approved
19 | 198/0 | DD60+6 |  | Done | WBC | Approved
20 | 205/0 | DD60+25 |  | Done | WBC | Approved
21 | 214/0 | DD60+30 |  | Done | WBC | Approved
22 | 216/0 | DD60+3 |  | Done | WBC | Approved
23 | 219/0 | DD45+3 |  | Done | WBC | Approved
24 | 223/0 | DC2+6 |  | Done | WBC | Approved
25 | 232/0 | DB1+0 |  | Done | WBC | Approved
26 | 235/0 | DD60+9 | 2 | Done | WBC | Approved
27 | 243/0 | DD60+3 |  | Done | WBC | Approved
28 | 248/0 | DD60+35 | 2 | Done | WBC | Approved

## Survey Anx (hidden)
TL- 04 765 kV D/C Vataman-Navsari Transmission Line
District | Section | Total | Detail Survey |  |  | Check Survey
|  |  | Completed | Submitted | Approved | Completed | Submitted | Approved
Bharuch | AP117-AP127 | 14.513 | 14.513 | 14.513 | 14.513 | 14.513 | 14.513 | 14.513
Bharuch | AP127-AP128 | 1.049 | 1.049 | 1.049 | 1.049 | 1.049 | 1.049 | 1.049
Bharuch | AP128-AP131 | 1.7751 | 1.7751 | 1.7751 | 1.7751 | 1.7751 | 1.7751 | 1.7751
Bharuch | AP131-AP132 | 2.2016 | 2.2016 | 2.2016 | 2.2016 | 2.2016 | 2.2016 | 2.2016
Bharuch | AP132-AP137 | 4.5929 | 4.5929 | 4.5929 | 4.5929 | 4.5929 | 4.5929 | 4.5929
Bharuch | AP137-AP142 | 5.8546 | 5.8546 | 5.8546 | 5.8546 | 5.8546 | 5.8546 | 5.8546
Bharuch | AP142-AP145 | 0.9064 | 0.9064 | 0.9064 | 0.9064 | 0.9064 | 0.9064 | 0.9064
Bharuch | AP145-AP149 | 5.958 | 5.958 | 5.958 | 5.958 | 5.958 | 5.958 | 5.958
Surat | AP149-AP151 | 0.906 | 0.906 | 0.906 | 0.906 | 0.906 | 0.906 | 0.906
Surat | AP151-AP156/1 | 3.632 | 3.632 | 3.632 | 3.632 | 3.632 | 3.632 | 3.632
Surat | AP-156/1 TO 159 | 0.819 | 0.819 | 0.819 |  |  | 0.819
Surat | AP159-AP183 | 19.564 | 19.564 | 19.564 | 19.564 | 19.564 | 19.564 | 19.564
Surat | AP183-AP201 | 11.386 | 11.386 | 11.386 | 11.386 | 11.386 | 11.386 | 11.386
Surat | AP-201 TO 206 | 2.995 | 3.037 | 3.037 | 3.037 |  | 3.037
Surat | AP-206 TO 211 | 2.39 | 2.39 | 2.39 | 2.39 | 2.39 | 2.39 | 2.39
Surat | AP211-AP215 | 5.829 | 5.829 | 5.829 | 5.829 | 5.829 | 5.829 | 5.829
Surat | AP215-AP218 | 4.03 | 4.03 | 4.03 | 4.03 | 4.03 | 4.03 | 4.03
Surat | AP218-AP226 | 7.7925 | 7.7925 | 7.7925 | 7.7925 | 7.7925 | 7.7925 | 7.7925
Navsari | AP226-AP232 | 6.215 | 6.215 | 6.215 | 6.215 | 6.215 | 6.215 | 6.215
Navsari | AP232-AP245 | 12.704 | 12.704 | 12.704 | 12.704 | 12.704 | 12.704 | 12.704
Navsari | AP245-AP250 | 4.132 | 4.132 | 4.132 | 4.132 | 4.132 | 4.132 | 4.132
Navsari | AP250-AP253 | 6.115 | 6.115 | 6.115 | 6.115 | 6.115 | 6.115 | 6.115
Navsari | AP253-AP258 | 2.4139 | 2.4139 | 2.4139 | 2.3539 | 2.3539 | 2.3539 | 2.3539
Total |  | 127.7741 | 127.8161 | 127.8161 | 126.9371 | 123.9001 | 123.9001 | 123.9001