## Foundation Gap Monthly
Foundation Gap Monthly
Project | Source Type | Snapshot Limited | Month | Foundations Cumulative | Erections Cumulative | Gap Cumulative
TA 413 | detail | No | 2024-06 | 14 | 0 | 14
TA 413 | detail | No | 2024-07 | 34 | 0 | 34
TA 413 | detail | No | 2024-08 | 57 | 0 | 57
TA 413 | detail | No | 2024-09 | 97 | 2 | 95
TA 413 | detail | No | 2024-10 | 133 | 7 | 126
TA 413 | detail | No | 2024-11 | 157 | 9 | 148
TA 413 | detail | No | 2024-12 | 189 | 22 | 167
TA 413 | detail | No | 2025-01 | 224 | 47 | 177
TA 413 | detail | No | 2025-02 | 255 | 68 | 187
TA 413 | detail | No | 2025-03 | 274 | 93 | 181
TA 413 | detail | No | 2025-04 | 297 | 104 | 193
TA 413 | detail | No | 2025-05 | 307 | 104 | 203
TA 413 | detail | No | 2025-06 | 311 | 104 | 207
TA 413 | detail | No | 2025-07 | 313 | 112 | 201
TA 413 | detail | No | 2025-08 | 313 | 156 | 157
TA 413 | detail | No | 2025-09 | 313 | 221 | 92
TA 413 | detail | No | 2025-10 | 313 | 257 | 56
TA 413 | detail | No | 2025-11 | 313 | 281 | 32
TA 413 | detail | No | 2025-12 | 313 | 294 | 19
TA 413 | detail | No | 2026-01 | 314 | 300 | 14
TA 413 | detail | No | 2026-02 | 315 | 303 | 12
TA 413 | detail | No | 2026-03 | 316 | 303 | 13
TA 413 | detail | No | 2026-06 | 316 | 304 | 12
TA 413 | detail | No | 2026-07 | 316 | 305 | 11
TA 414 | detail | No | 2024-05 | 2 | 0 | 2
TA 414 | detail | No | 2024-10 | 3 | 0 | 3
TA 414 | detail | No | 2024-11 | 7 | 0 | 7
TA 414 | detail | No | 2024-12 | 19 | 0 | 19
TA 414 | detail | No | 2025-01 | 36 | 0 | 36
TA 414 | detail | No | 2025-02 | 56 | 0 | 56
TA 414 | detail | No | 2025-03 | 66 | 0 | 66
TA 414 | detail | No | 2025-04 | 84 | 1 | 83
TA 414 | detail | No | 2025-05 | 89 | 1 | 88
TA 414 | detail | No | 2025-06 | 91 | 5 | 86
TA 414 | detail | No | 2025-08 | 92 | 9 | 83
TA 414 | detail | No | 2025-09 | 95 | 11 | 84
TA 414 | detail | No | 2025-10 | 103 | 12 | 91
TA 414 | detail | No | 2025-11 | 127 | 12 | 115
TA 414 | detail | No | 2025-12 | 182 | 28 | 154
TA 414 | detail | No | 2026-01 | 236 | 73 | 163
TA 414 | detail | No | 2026-02 | 266 | 123 | 143
TA 414 | detail | No | 2026-03 | 290 | 173 | 117
TA 414 | detail | No | 2026-04 | 304 | 207 | 97
TA 414 | detail | No | 2026-05 | 319 | 235 | 84
TA 414 | detail | No | 2026-06 | 335 | 266 | 69
TA 414 | detail | No | 2026-07 | 335 | 278 | 57
TA 414 | detail | No | 2026-08 | 335 | 280 | 55
TA 416 | detail | No | 2024-05 | 6 | 0 | 6
TA 416 | detail | No | 2024-06 | 23 | 0 | 23
TA 416 | detail | No | 2024-07 | 33 | 0 | 33
TA 416 | detail | No | 2024-08 | 46 | 0 | 46
TA 416 | detail | No | 2024-09 | 77 | 2 | 75
TA 416 | detail | No | 2024-10 | 136 | 11 | 125
TA 416 | detail | No | 2024-11 | 193 | 22 | 171
TA 416 | detail | No | 2024-12 | 255 | 47 | 208
TA 416 | detail | No | 2025-01 | 316 | 73 | 243
TA 416 | detail | No | 2025-02 | 373 | 102 | 271
TA 416 | detail | No | 2025-03 | 419 | 132 | 287
TA 416 | detail | No | 2025-04 | 468 | 167 | 301
TA 416 | detail | No | 2025-05 | 512 | 205 | 307
TA 416 | detail | No | 2025-06 | 537 | 229 | 308
TA 416 | detail | No | 2025-07 | 543 | 235 | 308
TA 416 | detail | No | 2025-08 | 551 | 243 | 308
TA 416 | detail | No | 2025-09 | 568 | 260 | 308
TA 416 | detail | No | 2025-10 | 585 | 273 | 312
TA 416 | detail | No | 2025-11 | 603 | 285 | 318
TA 416 | detail | No | 2025-12 | 611 | 292 | 319
TA 416 | detail | No | 2026-01 | 613 | 299 | 314
TA 416 | detail | No | 2026-02 | 624 | 300 | 324
TA 416 | detail | No | 2026-03 | 626 | 302 | 324
TA 416 | detail | No | 2026-05 | 629 | 302 | 327
TA 416 | detail | No | 2026-06 | 630 | 302 | 328
TA 416 | detail | No | 2026-07 | 633 | 302 | 331
TA 418 | detail | No | 2024-01 | 2 | 0 | 2
TA 418 | detail | No | 2024-06 | 4 | 0 | 4
TA 418 | detail | No | 2024-07 | 12 | 0 | 12
TA 418 | detail | No | 2024-08 | 21 | 0 | 21
TA 418 | detail | No | 2024-09 | 29 | 0 | 29
TA 418 | detail | No | 2024-10 | 34 | 1 | 33
TA 418 | detail | No | 2024-11 | 43 | 5 | 38
TA 418 | detail | No | 2024-12 | 57 | 13 | 44
TA 418 | detail | No | 2025-01 | 69 | 21 | 48
TA 418 | detail | No | 2025-02 | 83 | 28 | 55
TA 418 | detail | No | 2025-03 | 98 | 34 | 64
TA 418 | detail | No | 2025-04 | 110 | 41 | 69
TA 418 | detail | No | 2025-05 | 127 | 48 | 79
TA 418 | detail | No | 2025-06 | 149 | 54 | 95
TA 418 | detail | No | 2025-07 | 174 | 62 | 112
TA 418 | detail | No | 2025-08 | 187 | 72 | 115
TA 418 | detail | No | 2025-09 | 198 | 82 | 116
TA 418 | detail | No | 2025-10 | 206 | 89 | 117
TA 418 | detail | No | 2025-11 | 222 | 97 | 125
TA 418 | detail | No | 2025-12 | 239 | 108 | 131
TA 418 | detail | No | 2026-01 | 252 | 118 | 134
TA 418 | detail | No | 2026-02 | 263 | 124 | 139
TA 418 | detail | No | 2026-03 | 268 | 124 | 144
TA 418 | detail | No | 2026-04 | 272 | 125 | 147
TA 418 | detail | No | 2026-05 | 276 | 125 | 151
TA 418 | detail | No | 2026-06 | 286 | 125 | 161
TA 418 | detail | No | 2026-07 | 292 | 125 | 167
TA 419 | detail | No | 2024-05 | 3 | 0 | 3
TA 419 | detail | No | 2024-06 | 12 | 0 | 12
TA 419 | detail | No | 2024-07 | 29 | 0 | 29
TA 419 | detail | No | 2024-08 | 37 | 0 | 37
TA 419 | detail | No | 2024-09 | 53 | 0 | 53
TA 419 | detail | No | 2024-10 | 71 | 0 | 71
TA 419 | detail | No | 2024-11 | 85 | 2 | 83
TA 419 | detail | No | 2024-12 | 97 | 16 | 81
TA 419 | detail | No | 2025-01 | 104 | 29 | 75
TA 419 | detail | No | 2025-02 | 114 | 46 | 68
TA 419 | detail | No | 2025-03 | 119 | 54 | 65
TA 419 | detail | No | 2025-04 | 133 | 70 | 63
TA 419 | detail | No | 2025-05 | 141 | 75 | 66
TA 419 | detail | No | 2025-06 | 151 | 79 | 72
TA 419 | detail | No | 2025-07 | 156 | 84 | 72
TA 419 | detail | No | 2025-08 | 158 | 92 | 66
TA 419 | detail | No | 2025-09 | 161 | 98 | 63
TA 419 | detail | No | 2025-10 | 167 | 106 | 61
TA 419 | detail | No | 2025-11 | 185 | 120 | 65
TA 419 | detail | No | 2025-12 | 203 | 157 | 46
TA 419 | detail | No | 2026-01 | 215 | 181 | 34
TA 419 | detail | No | 2026-02 | 222 | 183 | 39
TA 419 | detail | No | 2026-03 | 228 | 185 | 43
TA 419 | detail | No | 2026-04 | 236 | 195 | 41
TA 419 | detail | No | 2026-05 | 255 | 207 | 48
TA 419 | detail | No | 2026-06 | 272 | 222 | 50
TA 419 | detail | No | 2026-07 | 286 | 243 | 43
TA 419 | detail | No | 2026-08 | 287 | 246 | 41
TA 421 | detail | No | 2024-05 | 1 | 0 | 1
TA 421 | detail | No | 2024-06 | 15 | 0 | 15
TA 421 | detail | No | 2024-07 | 37 | 2 | 35
TA 421 | detail | No | 2024-08 | 64 | 8 | 56
TA 421 | detail | No | 2024-09 | 83 | 17 | 66
TA 421 | detail | No | 2024-10 | 110 | 31 | 79
TA 421 | detail | No | 2024-11 | 150 | 50 | 100
TA 421 | detail | No | 2024-12 | 199 | 65 | 134
TA 421 | detail | No | 2025-01 | 249 | 79 | 170
TA 421 | detail | No | 2025-02 | 294 | 94 | 200
TA 421 | detail | No | 2025-03 | 337 | 118 | 219
TA 421 | detail | No | 2025-04 | 372 | 142 | 230
TA 421 | detail | No | 2025-05 | 426 | 159 | 267
TA 421 | detail | No | 2025-06 | 461 | 169 | 292
TA 421 | detail | No | 2025-07 | 497 | 193 | 304
TA 421 | detail | No | 2025-08 | 522 | 216 | 306
TA 421 | detail | No | 2025-09 | 544 | 238 | 306
TA 421 | detail | No | 2025-10 | 565 | 256 | 309
TA 421 | detail | No | 2025-11 | 590 | 278 | 312
TA 421 | detail | No | 2025-12 | 614 | 299 | 315
TA 421 | detail | No | 2026-01 | 621 | 305 | 316
TA 421 | detail | No | 2026-02 | 629 | 305 | 324
TA 421 | detail | No | 2026-03 | 631 | 305 | 326
TA 421 | detail | No | 2026-06 | 634 | 305 | 329
TA 505 | detail | No | 2024-03 | 1 | 0 | 1
TA 505 | detail | No | 2024-04 | 3 | 0 | 3
TA 505 | detail | No | 2024-10 | 12 | 0 | 12
TA 505 | detail | No | 2024-11 | 38 | 0 | 38
TA 505 | detail | No | 2024-12 | 74 | 0 | 74
TA 505 | detail | No | 2025-01 | 104 | 4 | 100
TA 505 | detail | No | 2025-02 | 136 | 11 | 125
TA 505 | detail | No | 2025-03 | 157 | 22 | 135
TA 505 | detail | No | 2025-04 | 205 | 41 | 164
TA 505 | detail | No | 2025-05 | 252 | 65 | 187
TA 505 | detail | No | 2025-06 | 267 | 81 | 186
TA 505 | detail | No | 2025-07 | 269 | 90 | 179
TA 505 | detail | No | 2025-08 | 270 | 97 | 173
TA 505 | detail | No | 2025-09 | 280 | 127 | 153
TA 505 | detail | No | 2025-10 | 292 | 153 | 139
TA 505 | detail | No | 2025-11 | 309 | 187 | 122
TA 505 | detail | No | 2025-12 | 327 | 236 | 91
TA 505 | detail | No | 2026-01 | 344 | 276 | 68
TA 505 | detail | No | 2026-02 | 354 | 300 | 54
TA 505 | detail | No | 2026-03 | 362 | 321 | 41
TA 505 | detail | No | 2026-04 | 370 | 347 | 23
TA 505 | detail | No | 2026-05 | 374 | 357 | 17
TA 505 | detail | No | 2026-06 | 378 | 363 | 15
TA 505 | detail | No | 2026-07 | 378 | 365 | 13
TA 509 | snapshot_fallback | Yes | 2025-09 |  | 19
TA 509 | snapshot_fallback | Yes | 2025-10 |  | 30
TA 509 | snapshot_fallback | Yes | 2025-11 |  | 39
TA 509 | snapshot_fallback | Yes | 2025-12 |  | 59
TA 509 | snapshot_fallback | Yes | 2026-01 |  | 80
TA 509 | snapshot_fallback | Yes | 2026-02 |  | 111
TA 509 | snapshot_fallback | Yes | 2026-03 |  | 135
TA 509 | snapshot_fallback | Yes | 2026-04 |  | 180
TA 509 | snapshot_fallback | Yes | 2026-05 | 268 | 208 | 60
TA 509 | snapshot_fallback | Yes | 2026-06 | 274 | 220 | 54
TA 509 | snapshot_fallback | Yes | 2026-07 | 279 | 229 | 50
TA 509 | snapshot_fallback | Yes | 2026-08 | 283 | 230 | 53
TA 510 | detail | No | 2025-02 | 4 | 0 | 4
TA 510 | detail | No | 2025-03 | 9 | 0 | 9
TA 510 | detail | No | 2025-04 | 15 | 0 | 15
TA 510 | detail | No | 2025-05 | 22 | 0 | 22
TA 510 | detail | No | 2025-06 | 24 | 0 | 24
TA 510 | detail | No | 2025-08 | 25 | 0 | 25
TA 510 | detail | No | 2025-09 | 27 | 0 | 27
TA 510 | detail | No | 2025-10 | 32 | 0 | 32
TA 510 | detail | No | 2025-11 | 37 | 0 | 37
TA 510 | detail | No | 2025-12 | 47 | 0 | 47
TA 510 | detail | No | 2026-01 | 54 | 9 | 45
TA 510 | detail | No | 2026-02 | 60 | 17 | 43
TA 510 | detail | No | 2026-03 | 64 | 25 | 39
TA 510 | detail | No | 2026-04 | 72 | 29 | 43
TA 510 | detail | No | 2026-05 | 85 | 40 | 45
TA 510 | detail | No | 2026-06 | 95 | 45 | 50
TA 510 | detail | No | 2026-07 | 95 | 47 | 48
TA 510 | detail | No | 2026-08 | 95 | 48 | 47
TA 512 | detail | No | 2025-02 | 3 | 0 | 3
TA 512 | detail | No | 2025-03 | 29 | 0 | 29
TA 512 | detail | No | 2025-04 | 53 | 0 | 53
TA 512 | detail | No | 2025-05 | 76 | 0 | 76
TA 512 | detail | No | 2025-06 | 103 | 0 | 103
TA 512 | detail | No | 2025-07 | 142 | 0 | 142
TA 512 | detail | No | 2025-08 | 168 | 6 | 162
TA 512 | detail | No | 2025-09 | 187 | 23 | 164
TA 512 | detail | No | 2025-10 | 211 | 36 | 175
TA 512 | detail | No | 2025-11 | 240 | 52 | 188
TA 512 | detail | No | 2025-12 | 276 | 82 | 194
TA 512 | detail | No | 2026-01 | 287 | 126 | 161
TA 512 | detail | No | 2026-02 | 291 | 171 | 120
TA 512 | detail | No | 2026-03 | 294 | 203 | 91
TA 512 | detail | No | 2026-04 | 301 | 218 | 83
TA 512 | detail | No | 2026-05 | 306 | 226 | 80
TA 512 | detail | No | 2026-06 | 312 | 242 | 70
TA 512 | detail | No | 2026-07 | 316 | 270 | 46
TA 512 | detail | No | 2026-08 | 317 | 284 | 33
TA 513 | detail | No | 2025-03 | 1 | 0 | 1
TA 513 | detail | No | 2025-04 | 15 | 0 | 15
TA 513 | detail | No | 2025-05 | 30 | 0 | 30
TA 513 | detail | No | 2025-06 | 38 | 0 | 38
TA 513 | detail | No | 2025-07 | 49 | 0 | 49
TA 513 | detail | No | 2025-08 | 52 | 0 | 52
TA 513 | detail | No | 2025-09 | 59 | 2 | 57
TA 513 | detail | No | 2025-10 | 62 | 8 | 54
TA 513 | detail | No | 2025-11 | 64 | 14 | 50
TA 513 | detail | No | 2025-12 | 69 | 18 | 51
TA 513 | detail | No | 2026-01 | 69 | 20 | 49
TA 513 | detail | No | 2026-02 | 71 | 21 | 50
TA 513 | detail | No | 2026-03 | 72 | 27 | 45
TA 513 | detail | No | 2026-04 | 73 | 28 | 45
TA 513 | detail | No | 2026-05 | 89 | 31 | 58
TA 513 | detail | No | 2026-06 | 100 | 35 | 65
TA 513 | detail | No | 2026-07 | 105 | 35 | 70
TA 513 | detail | No | 2026-08 | 109 | 35 | 74
TA 515 | missing | No | 2026-03 |  | 2
TA 601 | detail | No | 2025-03 | 0 | 1 | -1
TA 601 | detail | No | 2025-08 | 2 | 1 | 1
TA 601 | detail | No | 2025-09 | 4 | 1 | 3
TA 601 | detail | No | 2025-10 | 12 | 1 | 11
TA 601 | detail | No | 2025-11 | 22 | 1 | 21
TA 601 | detail | No | 2025-12 | 44 | 4 | 40
TA 601 | detail | No | 2026-01 | 92 | 25 | 67
TA 601 | detail | No | 2026-02 | 138 | 54 | 84
TA 601 | detail | No | 2026-03 | 166 | 67 | 99
TA 601 | detail | No | 2026-04 | 182 | 70 | 112
TA 601 | detail | No | 2026-05 | 194 | 71 | 123
TA 601 | detail | No | 2026-06 | 235 | 88 | 147
TA 601 | detail | No | 2026-07 | 297 | 118 | 179
TA 601 | detail | No | 2026-08 | 315 | 126 | 189
TA 602 | snapshot_fallback | Yes | 2026-02 |  | 3
TA 602 | snapshot_fallback | Yes | 2026-03 |  | 15
TA 602 | snapshot_fallback | Yes | 2026-04 |  | 23
TA 602 | snapshot_fallback | Yes | 2026-05 |  | 52
TA 602 | snapshot_fallback | Yes | 2026-06 | 324 | 78 | 246
TA 602 | snapshot_fallback | Yes | 2026-07 | 172 | 89 | 83
TA 602 | snapshot_fallback | Yes | 2026-08 | 172 | 91 | 81
TB 408 | detail | No | 2023-10 | 1 | 0 | 1
TB 408 | detail | No | 2023-12 | 2 | 0 | 2
TB 408 | detail | No | 2024-01 | 3 | 0 | 3
TB 408 | detail | No | 2024-02 | 4 | 22 | -18
TB 408 | detail | No | 2024-03 | 5 | 42 | -37
TB 408 | detail | No | 2024-04 | 6 | 61 | -55
TB 408 | detail | No | 2024-05 | 7 | 75 | -68
TB 408 | detail | No | 2024-06 | 8 | 78 | -70
TB 408 | detail | No | 2024-07 | 9 | 80 | -71
TB 408 | detail | No | 2024-08 | 10 | 83 | -73
TB 408 | detail | No | 2024-09 | 12 | 99 | -87
TB 408 | detail | No | 2024-10 | 13 | 129 | -116
TB 408 | detail | No | 2024-11 | 16 | 159 | -143
TB 408 | detail | No | 2024-12 | 18 | 170 | -152
TB 408 | detail | No | 2025-01 | 19 | 186 | -167
TB 408 | detail | No | 2025-02 | 20 | 200 | -180
TB 408 | detail | No | 2025-03 | 21 | 213 | -192
TB 408 | detail | No | 2025-04 | 22 | 220 | -198
TB 408 | detail | No | 2025-05 | 23 | 222 | -199
TB 408 | detail | No | 2025-06 | 24 | 228 | -204
TB 408 | detail | No | 2025-07 | 25 | 251 | -226
TB 408 | detail | No | 2025-08 | 26 | 303 | -277
TB 408 | detail | No | 2025-09 | 27 | 350 | -323
TB 408 | detail | No | 2025-10 | 28 | 375 | -347
TB 408 | detail | No | 2025-11 | 29 | 408 | -379
TB 408 | detail | No | 2025-12 | 29 | 448 | -419
TB 408 | detail | No | 2026-01 | 29 | 459 | -430
TB 408 | detail | No | 2026-02 | 30 | 465 | -435
TB 408 | detail | No | 2026-03 | 31 | 475 | -444
TB 408 | detail | No | 2026-04 | 31 | 478 | -447
TB 408 | detail | No | 2026-05 | 31 | 484 | -453
TB 408 | detail | No | 2026-07 | 31 | 485 | -454
TB 501 | detail | No | 2024-08 | 3 | 0 | 3
TB 501 | detail | No | 2024-09 | 10 | 0 | 10
TB 501 | detail | No | 2024-10 | 35 | 0 | 35
TB 501 | detail | No | 2024-11 | 61 | 0 | 61
TB 501 | detail | No | 2024-12 | 88 | 5 | 83
TB 501 | detail | No | 2025-01 | 109 | 21 | 88
TB 501 | detail | No | 2025-02 | 130 | 60 | 70
TB 501 | detail | No | 2025-03 | 139 | 100 | 39
TB 501 | detail | No | 2025-04 | 150 | 120 | 30
TB 501 | detail | No | 2025-05 | 168 | 138 | 30
TB 501 | detail | No | 2025-06 | 174 | 156 | 18
TB 501 | detail | No | 2025-07 | 175 | 169 | 6
TB 501 | detail | No | 2025-08 | 178 | 173 | 5
TB 501 | detail | No | 2025-09 | 186 | 173 | 13
TB 501 | detail | No | 2025-10 | 192 | 178 | 14
TB 501 | detail | No | 2025-11 | 199 | 193 | 6
TB 501 | detail | No | 2025-12 | 209 | 203 | 6
TB 501 | detail | No | 2026-01 | 218 | 212 | 6
TB 501 | detail | No | 2026-02 | 222 | 219 | 3
TB 501 | detail | No | 2026-03 | 226 | 226 | 0
TB 501 | detail | No | 2026-04 | 231 | 228 | 3
TB 501 | detail | No | 2026-05 | 231 | 231 | 0
TB 501 | detail | No | 2026-06 | 234 | 233 | 1
TB 501 | detail | No | 2026-07 | 235 | 233 | 2
TB 507 | detail | No | 2025-01 | 2 | 0 | 2
TB 507 | detail | No | 2025-02 | 22 | 0 | 22
TB 507 | detail | No | 2025-03 | 38 | 0 | 38
TB 507 | detail | No | 2025-04 | 51 | 0 | 51
TB 507 | detail | No | 2025-05 | 60 | 1 | 59
TB 507 | detail | No | 2025-06 | 85 | 2 | 83
TB 507 | detail | No | 2025-07 | 135 | 13 | 122
TB 507 | detail | No | 2025-08 | 187 | 24 | 163
TB 507 | detail | No | 2025-09 | 207 | 62 | 145
TB 507 | detail | No | 2025-10 | 215 | 105 | 110
TB 507 | detail | No | 2025-11 | 234 | 138 | 96
TB 507 | detail | No | 2025-12 | 247 | 163 | 84
TB 507 | detail | No | 2026-01 | 262 | 177 | 85
TB 507 | detail | No | 2026-02 | 274 | 184 | 90
TB 507 | detail | No | 2026-03 | 291 | 189 | 102
TB 507 | detail | No | 2026-04 | 311 | 198 | 113
TB 507 | detail | No | 2026-05 | 342 | 221 | 121
TB 507 | detail | No | 2026-06 | 363 | 237 | 126
TB 507 | detail | No | 2026-07 | 380 | 267 | 113
TB 507 | detail | No | 2026-08 | 385 | 282 | 103
TB 605 | detail | No | 2025-08 | 1 | 0 | 1
TB 605 | detail | No | 2025-09 | 4 | 0 | 4
TB 605 | detail | No | 2025-10 | 19 | 0 | 19
TB 605 | detail | No | 2025-11 | 61 | 1 | 60
TB 605 | detail | No | 2025-12 | 118 | 4 | 114
TB 605 | detail | No | 2026-01 | 160 | 10 | 150
TB 605 | detail | No | 2026-02 | 202 | 55 | 147
TB 605 | detail | No | 2026-03 | 230 | 105 | 125
TB 605 | detail | No | 2026-04 | 256 | 157 | 99
TB 605 | detail | No | 2026-05 | 311 | 203 | 108
TB 605 | detail | No | 2026-06 | 352 | 248 | 104
TB 605 | detail | No | 2026-07 | 359 | 273 | 86
TB 605 | detail | No | 2026-08 | 361 | 282 | 79
TB 608 | detail | No | 2025-10 | 2 | 0 | 2
TB 608 | detail | No | 2025-11 | 22 | 0 | 22
TB 608 | detail | No | 2025-12 | 56 | 0 | 56
TB 608 | detail | No | 2026-01 | 86 | 3 | 83
TB 608 | detail | No | 2026-02 | 116 | 7 | 109
TB 608 | detail | No | 2026-03 | 133 | 12 | 121
TB 608 | detail | No | 2026-04 | 141 | 21 | 120
TB 608 | detail | No | 2026-05 | 153 | 31 | 122
TB 608 | detail | No | 2026-06 | 159 | 43 | 116
TB 608 | detail | No | 2026-07 | 165 | 56 | 109
TB 608 | detail | No | 2026-08 | 166 | 58 | 108

## Foundation Gap Weekly
Foundation Gap Weekly
Project | Source Type | Snapshot Limited | Week Start | Week End | Week | Foundations Cumulative | Erections Cumulative | Gap Cumulative
TA 413 | detail | No | 2024-06-02 | 2024-06-08 | 2024-06-02 to 2024-06-08 | 2 | 0 | 2
TA 413 | detail | No | 2024-06-09 | 2024-06-15 | 2024-06-09 to 2024-06-15 | 4 | 0 | 4
TA 413 | detail | No | 2024-06-16 | 2024-06-22 | 2024-06-16 to 2024-06-22 | 8 | 0 | 8
TA 413 | detail | No | 2024-06-23 | 2024-06-29 | 2024-06-23 to 2024-06-29 | 14 | 0 | 14
TA 413 | detail | No | 2024-06-30 | 2024-07-06 | 2024-06-30 to 2024-07-06 | 18 | 0 | 18
TA 413 | detail | No | 2024-07-07 | 2024-07-13 | 2024-07-07 to 2024-07-13 | 23 | 0 | 23
TA 413 | detail | No | 2024-07-14 | 2024-07-20 | 2024-07-14 to 2024-07-20 | 27 | 0 | 27
TA 413 | detail | No | 2024-07-21 | 2024-07-27 | 2024-07-21 to 2024-07-27 | 31 | 0 | 31
TA 413 | detail | No | 2024-07-28 | 2024-08-03 | 2024-07-28 to 2024-08-03 | 37 | 0 | 37
TA 413 | detail | No | 2024-08-04 | 2024-08-10 | 2024-08-04 to 2024-08-10 | 40 | 0 | 40
TA 413 | detail | No | 2024-08-11 | 2024-08-17 | 2024-08-11 to 2024-08-17 | 44 | 0 | 44
TA 413 | detail | No | 2024-08-18 | 2024-08-24 | 2024-08-18 to 2024-08-24 | 49 | 0 | 49
TA 413 | detail | No | 2024-08-25 | 2024-08-31 | 2024-08-25 to 2024-08-31 | 57 | 0 | 57
TA 413 | detail | No | 2024-09-01 | 2024-09-07 | 2024-09-01 to 2024-09-07 | 65 | 0 | 65
TA 413 | detail | No | 2024-09-08 | 2024-09-14 | 2024-09-08 to 2024-09-14 | 74 | 0 | 74
TA 413 | detail | No | 2024-09-15 | 2024-09-21 | 2024-09-15 to 2024-09-21 | 85 | 1 | 84
TA 413 | detail | No | 2024-09-22 | 2024-09-28 | 2024-09-22 to 2024-09-28 | 94 | 2 | 92
TA 413 | detail | No | 2024-09-29 | 2024-10-05 | 2024-09-29 to 2024-10-05 | 104 | 3 | 101
TA 413 | detail | No | 2024-10-06 | 2024-10-12 | 2024-10-06 to 2024-10-12 | 113 | 4 | 109
TA 413 | detail | No | 2024-10-13 | 2024-10-19 | 2024-10-13 to 2024-10-19 | 122 | 6 | 116
TA 413 | detail | No | 2024-10-20 | 2024-10-26 | 2024-10-20 to 2024-10-26 | 129 | 7 | 122
TA 413 | detail | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 | 133 | 7 | 126
TA 413 | detail | No | 2024-11-03 | 2024-11-09 | 2024-11-03 to 2024-11-09 | 137 | 7 | 130
TA 413 | detail | No | 2024-11-10 | 2024-11-16 | 2024-11-10 to 2024-11-16 | 141 | 7 | 134
TA 413 | detail | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 | 150 | 7 | 143
TA 413 | detail | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 | 157 | 9 | 148
TA 413 | detail | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 | 163 | 10 | 153
TA 413 | detail | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 | 170 | 11 | 159
TA 413 | detail | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 | 178 | 14 | 164
TA 413 | detail | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 | 183 | 19 | 164
TA 413 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 191 | 24 | 167
TA 413 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 199 | 30 | 169
TA 413 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 206 | 33 | 173
TA 413 | detail | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 | 217 | 41 | 176
TA 413 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 225 | 47 | 178
TA 413 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 232 | 52 | 180
TA 413 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 239 | 56 | 183
TA 413 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 248 | 61 | 187
TA 413 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 256 | 68 | 188
TA 413 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 262 | 73 | 189
TA 413 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 264 | 78 | 186
TA 413 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 266 | 84 | 182
TA 413 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 271 | 89 | 182
TA 413 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 277 | 94 | 183
TA 413 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 284 | 98 | 186
TA 413 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 291 | 101 | 190
TA 413 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 296 | 102 | 194
TA 413 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 299 | 104 | 195
TA 413 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 302 | 104 | 198
TA 413 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 304 | 104 | 200
TA 413 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 306 | 104 | 202
TA 413 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 307 | 104 | 203
TA 413 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 308 | 104 | 204
TA 413 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 310 | 104 | 206
TA 413 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 311 | 104 | 207
TA 413 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 312 | 104 | 208
TA 413 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 313 | 106 | 207
TA 413 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 313 | 110 | 203
TA 413 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 313 | 114 | 199
TA 413 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 313 | 123 | 190
TA 413 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 313 | 131 | 182
TA 413 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 313 | 144 | 169
TA 413 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 313 | 155 | 158
TA 413 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 313 | 169 | 144
TA 413 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 313 | 182 | 131
TA 413 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 313 | 199 | 114
TA 413 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 313 | 212 | 101
TA 413 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 313 | 225 | 88
TA 413 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 313 | 232 | 81
TA 413 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 313 | 240 | 73
TA 413 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 313 | 247 | 66
TA 413 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 313 | 257 | 56
TA 413 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 313 | 262 | 51
TA 413 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 313 | 270 | 43
TA 413 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 313 | 273 | 40
TA 413 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 313 | 281 | 32
TA 413 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 313 | 284 | 29
TA 413 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 313 | 285 | 28
TA 413 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 313 | 288 | 25
TA 413 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 313 | 292 | 21
TA 413 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 313 | 294 | 19
TA 413 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 313 | 295 | 18
TA 413 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 313 | 296 | 17
TA 413 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 314 | 298 | 16
TA 413 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 314 | 300 | 14
TA 413 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 314 | 301 | 13
TA 413 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 315 | 302 | 13
TA 413 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 315 | 303 | 12
TA 413 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 316 | 303 | 13
TA 413 | detail | No | 2026-06-14 | 2026-06-20 | 2026-06-14 to 2026-06-20 | 316 | 304 | 12
TA 413 | detail | No | 2026-07-26 | 2026-08-01 | 2026-07-26 to 2026-08-01 | 316 | 305 | 11
TA 414 | detail | No | 2024-05-19 | 2024-05-25 | 2024-05-19 to 2024-05-25 | 1 | 0 | 1
TA 414 | detail | No | 2024-05-26 | 2024-06-01 | 2024-05-26 to 2024-06-01 | 2 | 0 | 2
TA 414 | detail | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 | 3 | 0 | 3
TA 414 | detail | No | 2024-11-10 | 2024-11-16 | 2024-11-10 to 2024-11-16 | 4 | 0 | 4
TA 414 | detail | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 | 6 | 0 | 6
TA 414 | detail | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 | 7 | 0 | 7
TA 414 | detail | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 | 8 | 0 | 8
TA 414 | detail | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 | 9 | 0 | 9
TA 414 | detail | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 | 11 | 0 | 11
TA 414 | detail | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 | 17 | 0 | 17
TA 414 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 22 | 0 | 22
TA 414 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 25 | 0 | 25
TA 414 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 29 | 0 | 29
TA 414 | detail | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 | 33 | 0 | 33
TA 414 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 36 | 0 | 36
TA 414 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 44 | 0 | 44
TA 414 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 50 | 0 | 50
TA 414 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 52 | 0 | 52
TA 414 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 56 | 0 | 56
TA 414 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 58 | 0 | 58
TA 414 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 59 | 0 | 59
TA 414 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 62 | 0 | 62
TA 414 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 66 | 0 | 66
TA 414 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 70 | 1 | 69
TA 414 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 76 | 1 | 75
TA 414 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 79 | 1 | 78
TA 414 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 81 | 1 | 80
TA 414 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 85 | 1 | 84
TA 414 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 89 | 1 | 88
TA 414 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 90 | 2 | 88
TA 414 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 91 | 3 | 88
TA 414 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 91 | 4 | 87
TA 414 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 91 | 5 | 86
TA 414 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 91 | 6 | 85
TA 414 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 91 | 7 | 84
TA 414 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 92 | 7 | 85
TA 414 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 92 | 9 | 83
TA 414 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 93 | 9 | 84
TA 414 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 95 | 11 | 84
TA 414 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 95 | 12 | 83
TA 414 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 97 | 12 | 85
TA 414 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 101 | 12 | 89
TA 414 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 103 | 12 | 91
TA 414 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 105 | 12 | 93
TA 414 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 109 | 12 | 97
TA 414 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 115 | 12 | 103
TA 414 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 125 | 12 | 113
TA 414 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 136 | 12 | 124
TA 414 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 148 | 14 | 134
TA 414 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 160 | 20 | 140
TA 414 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 174 | 23 | 151
TA 414 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 184 | 30 | 154
TA 414 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 193 | 39 | 154
TA 414 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 207 | 47 | 160
TA 414 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 220 | 59 | 161
TA 414 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 236 | 73 | 163
TA 414 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 246 | 83 | 163
TA 414 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 251 | 98 | 153
TA 414 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 259 | 109 | 150
TA 414 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 266 | 123 | 143
TA 414 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 270 | 127 | 143
TA 414 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 274 | 142 | 132
TA 414 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 279 | 154 | 125
TA 414 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 287 | 167 | 120
TA 414 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 290 | 182 | 108
TA 414 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 292 | 192 | 100
TA 414 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 297 | 200 | 97
TA 414 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 301 | 206 | 95
TA 414 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 305 | 208 | 97
TA 414 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 310 | 216 | 94
TA 414 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 313 | 222 | 91
TA 414 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 317 | 227 | 90
TA 414 | detail | No | 2026-05-24 | 2026-05-30 | 2026-05-24 to 2026-05-30 | 318 | 235 | 83
TA 414 | detail | No | 2026-05-31 | 2026-06-06 | 2026-05-31 to 2026-06-06 | 322 | 242 | 80
TA 414 | detail | No | 2026-06-07 | 2026-06-13 | 2026-06-07 to 2026-06-13 | 327 | 247 | 80
TA 414 | detail | No | 2026-06-14 | 2026-06-20 | 2026-06-14 to 2026-06-20 | 330 | 257 | 73
TA 414 | detail | No | 2026-06-21 | 2026-06-27 | 2026-06-21 to 2026-06-27 | 335 | 263 | 72
TA 414 | detail | No | 2026-06-28 | 2026-07-04 | 2026-06-28 to 2026-07-04 | 335 | 267 | 68
TA 414 | detail | No | 2026-07-05 | 2026-07-11 | 2026-07-05 to 2026-07-11 | 335 | 268 | 67
TA 414 | detail | No | 2026-07-12 | 2026-07-18 | 2026-07-12 to 2026-07-18 | 335 | 274 | 61
TA 414 | detail | No | 2026-07-19 | 2026-07-25 | 2026-07-19 to 2026-07-25 | 335 | 275 | 60
TA 414 | detail | No | 2026-07-26 | 2026-08-01 | 2026-07-26 to 2026-08-01 | 335 | 278 | 57
TA 414 | detail | No | 2026-08-02 | 2026-08-08 | 2026-08-02 to 2026-08-08 | 335 | 279 | 56
TA 414 | detail | No | 2026-08-09 | 2026-08-15 | 2026-08-09 to 2026-08-15 | 335 | 280 | 55
TA 416 | detail | No | 2024-05-05 | 2024-05-11 | 2024-05-05 to 2024-05-11 | 2 | 0 | 2
TA 416 | detail | No | 2024-05-12 | 2024-05-18 | 2024-05-12 to 2024-05-18 | 4 | 0 | 4
TA 416 | detail | No | 2024-05-19 | 2024-05-25 | 2024-05-19 to 2024-05-25 | 5 | 0 | 5
TA 416 | detail | No | 2024-05-26 | 2024-06-01 | 2024-05-26 to 2024-06-01 | 6 | 0 | 6
TA 416 | detail | No | 2024-06-02 | 2024-06-08 | 2024-06-02 to 2024-06-08 | 10 | 0 | 10
TA 416 | detail | No | 2024-06-09 | 2024-06-15 | 2024-06-09 to 2024-06-15 | 15 | 0 | 15
TA 416 | detail | No | 2024-06-16 | 2024-06-22 | 2024-06-16 to 2024-06-22 | 19 | 0 | 19
TA 416 | detail | No | 2024-06-23 | 2024-06-29 | 2024-06-23 to 2024-06-29 | 22 | 0 | 22
TA 416 | detail | No | 2024-06-30 | 2024-07-06 | 2024-06-30 to 2024-07-06 | 23 | 0 | 23
TA 416 | detail | No | 2024-07-07 | 2024-07-13 | 2024-07-07 to 2024-07-13 | 24 | 0 | 24
TA 416 | detail | No | 2024-07-14 | 2024-07-20 | 2024-07-14 to 2024-07-20 | 27 | 0 | 27
TA 416 | detail | No | 2024-07-21 | 2024-07-27 | 2024-07-21 to 2024-07-27 | 29 | 0 | 29
TA 416 | detail | No | 2024-07-28 | 2024-08-03 | 2024-07-28 to 2024-08-03 | 34 | 0 | 34
TA 416 | detail | No | 2024-08-04 | 2024-08-10 | 2024-08-04 to 2024-08-10 | 38 | 0 | 38
TA 416 | detail | No | 2024-08-11 | 2024-08-17 | 2024-08-11 to 2024-08-17 | 39 | 0 | 39
TA 416 | detail | No | 2024-08-18 | 2024-08-24 | 2024-08-18 to 2024-08-24 | 42 | 0 | 42
TA 416 | detail | No | 2024-08-25 | 2024-08-31 | 2024-08-25 to 2024-08-31 | 46 | 0 | 46
TA 416 | detail | No | 2024-09-01 | 2024-09-07 | 2024-09-01 to 2024-09-07 | 47 | 0 | 47
TA 416 | detail | No | 2024-09-08 | 2024-09-14 | 2024-09-08 to 2024-09-14 | 55 | 0 | 55
TA 416 | detail | No | 2024-09-15 | 2024-09-21 | 2024-09-15 to 2024-09-21 | 59 | 1 | 58
TA 416 | detail | No | 2024-09-22 | 2024-09-28 | 2024-09-22 to 2024-09-28 | 69 | 1 | 68
TA 416 | detail | No | 2024-09-29 | 2024-10-05 | 2024-09-29 to 2024-10-05 | 83 | 3 | 80
TA 416 | detail | No | 2024-10-06 | 2024-10-12 | 2024-10-06 to 2024-10-12 | 97 | 4 | 93
TA 416 | detail | No | 2024-10-13 | 2024-10-19 | 2024-10-13 to 2024-10-19 | 110 | 7 | 103
TA 416 | detail | No | 2024-10-20 | 2024-10-26 | 2024-10-20 to 2024-10-26 | 132 | 9 | 123
TA 416 | detail | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 | 143 | 11 | 132
TA 416 | detail | No | 2024-11-03 | 2024-11-09 | 2024-11-03 to 2024-11-09 | 148 | 12 | 136
TA 416 | detail | No | 2024-11-10 | 2024-11-16 | 2024-11-10 to 2024-11-16 | 162 | 14 | 148
TA 416 | detail | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 | 175 | 16 | 159
TA 416 | detail | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 | 193 | 22 | 171
TA 416 | detail | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 | 204 | 27 | 177
TA 416 | detail | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 | 219 | 32 | 187
TA 416 | detail | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 | 237 | 38 | 199
TA 416 | detail | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 | 250 | 44 | 206
TA 416 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 262 | 50 | 212
TA 416 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 276 | 55 | 221
TA 416 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 290 | 60 | 230
TA 416 | detail | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 | 303 | 67 | 236
TA 416 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 317 | 74 | 243
TA 416 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 328 | 79 | 249
TA 416 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 343 | 87 | 256
TA 416 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 359 | 95 | 264
TA 416 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 373 | 102 | 271
TA 416 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 384 | 109 | 275
TA 416 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 393 | 114 | 279
TA 416 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 402 | 120 | 282
TA 416 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 411 | 125 | 286
TA 416 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 423 | 133 | 290
TA 416 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 435 | 142 | 293
TA 416 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 443 | 149 | 294
TA 416 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 456 | 160 | 296
TA 416 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 469 | 168 | 301
TA 416 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 477 | 176 | 301
TA 416 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 489 | 185 | 304
TA 416 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 503 | 197 | 306
TA 416 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 512 | 205 | 307
TA 416 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 519 | 211 | 308
TA 416 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 524 | 216 | 308
TA 416 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 528 | 220 | 308
TA 416 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 531 | 223 | 308
TA 416 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 538 | 230 | 308
TA 416 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 540 | 232 | 308
TA 416 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 541 | 233 | 308
TA 416 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 542 | 234 | 308
TA 416 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 543 | 235 | 308
TA 416 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 544 | 236 | 308
TA 416 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 545 | 237 | 308
TA 416 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 546 | 238 | 308
TA 416 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 551 | 243 | 308
TA 416 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 554 | 246 | 308
TA 416 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 556 | 248 | 308
TA 416 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 566 | 258 | 308
TA 416 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 568 | 260 | 308
TA 416 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 571 | 263 | 308
TA 416 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 578 | 269 | 309
TA 416 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 582 | 270 | 312
TA 416 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 586 | 273 | 313
TA 416 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 589 | 275 | 314
TA 416 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 594 | 279 | 315
TA 416 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 597 | 280 | 317
TA 416 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 599 | 282 | 317
TA 416 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 606 | 287 | 319
TA 416 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 607 | 288 | 319
TA 416 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 609 | 290 | 319
TA 416 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 611 | 292 | 319
TA 416 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 611 | 294 | 317
TA 416 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 611 | 297 | 314
TA 416 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 612 | 298 | 314
TA 416 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 613 | 299 | 314
TA 416 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 614 | 299 | 315
TA 416 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 618 | 300 | 318
TA 416 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 621 | 300 | 321
TA 416 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 624 | 300 | 324
TA 416 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 625 | 301 | 324
TA 416 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 626 | 302 | 324
TA 416 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 629 | 302 | 327
TA 416 | detail | No | 2026-06-28 | 2026-07-04 | 2026-06-28 to 2026-07-04 | 631 | 302 | 329
TA 416 | detail | No | 2026-07-05 | 2026-07-11 | 2026-07-05 to 2026-07-11 | 632 | 302 | 330
TA 416 | detail | No | 2026-07-12 | 2026-07-18 | 2026-07-12 to 2026-07-18 | 633 | 302 | 331
TA 418 | detail | No | 2023-12-31 | 2024-01-06 | 2023-12-31 to 2024-01-06 | 1 | 0 | 1
TA 418 | detail | No | 2024-01-07 | 2024-01-13 | 2024-01-07 to 2024-01-13 | 2 | 0 | 2
TA 418 | detail | No | 2024-06-16 | 2024-06-22 | 2024-06-16 to 2024-06-22 | 3 | 0 | 3
TA 418 | detail | No | 2024-06-23 | 2024-06-29 | 2024-06-23 to 2024-06-29 | 4 | 0 | 4
TA 418 | detail | No | 2024-07-07 | 2024-07-13 | 2024-07-07 to 2024-07-13 | 6 | 0 | 6
TA 418 | detail | No | 2024-07-14 | 2024-07-20 | 2024-07-14 to 2024-07-20 | 8 | 0 | 8
TA 418 | detail | No | 2024-07-21 | 2024-07-27 | 2024-07-21 to 2024-07-27 | 11 | 0 | 11
TA 418 | detail | No | 2024-07-28 | 2024-08-03 | 2024-07-28 to 2024-08-03 | 14 | 0 | 14
TA 418 | detail | No | 2024-08-04 | 2024-08-10 | 2024-08-04 to 2024-08-10 | 17 | 0 | 17
TA 418 | detail | No | 2024-08-11 | 2024-08-17 | 2024-08-11 to 2024-08-17 | 18 | 0 | 18
TA 418 | detail | No | 2024-08-18 | 2024-08-24 | 2024-08-18 to 2024-08-24 | 19 | 0 | 19
TA 418 | detail | No | 2024-08-25 | 2024-08-31 | 2024-08-25 to 2024-08-31 | 21 | 0 | 21
TA 418 | detail | No | 2024-09-01 | 2024-09-07 | 2024-09-01 to 2024-09-07 | 22 | 0 | 22
TA 418 | detail | No | 2024-09-08 | 2024-09-14 | 2024-09-08 to 2024-09-14 | 26 | 0 | 26
TA 418 | detail | No | 2024-09-15 | 2024-09-21 | 2024-09-15 to 2024-09-21 | 28 | 0 | 28
TA 418 | detail | No | 2024-09-22 | 2024-09-28 | 2024-09-22 to 2024-09-28 | 29 | 0 | 29
TA 418 | detail | No | 2024-09-29 | 2024-10-05 | 2024-09-29 to 2024-10-05 | 30 | 0 | 30
TA 418 | detail | No | 2024-10-06 | 2024-10-12 | 2024-10-06 to 2024-10-12 | 31 | 0 | 31
TA 418 | detail | No | 2024-10-13 | 2024-10-19 | 2024-10-13 to 2024-10-19 | 32 | 0 | 32
TA 418 | detail | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 | 34 | 1 | 33
TA 418 | detail | No | 2024-11-03 | 2024-11-09 | 2024-11-03 to 2024-11-09 | 36 | 2 | 34
TA 418 | detail | No | 2024-11-10 | 2024-11-16 | 2024-11-10 to 2024-11-16 | 38 | 3 | 35
TA 418 | detail | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 | 41 | 4 | 37
TA 418 | detail | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 | 43 | 5 | 38
TA 418 | detail | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 | 46 | 7 | 39
TA 418 | detail | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 | 48 | 9 | 39
TA 418 | detail | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 | 52 | 11 | 41
TA 418 | detail | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 | 55 | 12 | 43
TA 418 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 57 | 13 | 44
TA 418 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 59 | 16 | 43
TA 418 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 63 | 18 | 45
TA 418 | detail | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 | 68 | 20 | 48
TA 418 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 70 | 21 | 49
TA 418 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 73 | 23 | 50
TA 418 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 76 | 25 | 51
TA 418 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 81 | 27 | 54
TA 418 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 84 | 28 | 56
TA 418 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 88 | 30 | 58
TA 418 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 91 | 31 | 60
TA 418 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 94 | 32 | 62
TA 418 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 98 | 34 | 64
TA 418 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 102 | 36 | 66
TA 418 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 104 | 37 | 67
TA 418 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 106 | 38 | 68
TA 418 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 109 | 40 | 69
TA 418 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 112 | 42 | 70
TA 418 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 115 | 44 | 71
TA 418 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 119 | 45 | 74
TA 418 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 124 | 46 | 78
TA 418 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 127 | 48 | 79
TA 418 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 132 | 50 | 82
TA 418 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 137 | 52 | 85
TA 418 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 143 | 53 | 90
TA 418 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 147 | 54 | 93
TA 418 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 156 | 55 | 101
TA 418 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 160 | 56 | 104
TA 418 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 166 | 57 | 109
TA 418 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 171 | 60 | 111
TA 418 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 174 | 62 | 112
TA 418 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 179 | 65 | 114
TA 418 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 180 | 66 | 114
TA 418 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 183 | 69 | 114
TA 418 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 187 | 72 | 115
TA 418 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 188 | 73 | 115
TA 418 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 192 | 77 | 115
TA 418 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 195 | 80 | 115
TA 418 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 200 | 84 | 116
TA 418 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 202 | 85 | 117
TA 418 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 205 | 88 | 117
TA 418 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 206 | 89 | 117
TA 418 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 209 | 91 | 118
TA 418 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 213 | 93 | 120
TA 418 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 217 | 95 | 122
TA 418 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 221 | 97 | 124
TA 418 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 223 | 98 | 125
TA 418 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 227 | 100 | 127
TA 418 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 233 | 104 | 129
TA 418 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 238 | 107 | 131
TA 418 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 239 | 108 | 131
TA 418 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 243 | 111 | 132
TA 418 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 245 | 113 | 132
TA 418 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 247 | 115 | 132
TA 418 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 252 | 118 | 134
TA 418 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 255 | 120 | 135
TA 418 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 257 | 120 | 137
TA 418 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 260 | 122 | 138
TA 418 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 263 | 124 | 139
TA 418 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 264 | 124 | 140
TA 418 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 266 | 124 | 142
TA 418 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 267 | 124 | 143
TA 418 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 269 | 125 | 144
TA 418 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 270 | 125 | 145
TA 418 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 272 | 125 | 147
TA 418 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 273 | 125 | 148
TA 418 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 274 | 125 | 149
TA 418 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 275 | 125 | 150
TA 418 | detail | No | 2026-05-24 | 2026-05-30 | 2026-05-24 to 2026-05-30 | 276 | 125 | 151
TA 418 | detail | No | 2026-05-31 | 2026-06-06 | 2026-05-31 to 2026-06-06 | 277 | 125 | 152
TA 418 | detail | No | 2026-06-07 | 2026-06-13 | 2026-06-07 to 2026-06-13 | 279 | 125 | 154
TA 418 | detail | No | 2026-06-14 | 2026-06-20 | 2026-06-14 to 2026-06-20 | 281 | 125 | 156
TA 418 | detail | No | 2026-06-21 | 2026-06-27 | 2026-06-21 to 2026-06-27 | 285 | 125 | 160
TA 418 | detail | No | 2026-06-28 | 2026-07-04 | 2026-06-28 to 2026-07-04 | 287 | 125 | 162
TA 418 | detail | No | 2026-07-05 | 2026-07-11 | 2026-07-05 to 2026-07-11 | 288 | 125 | 163
TA 418 | detail | No | 2026-07-12 | 2026-07-18 | 2026-07-12 to 2026-07-18 | 291 | 125 | 166
TA 418 | detail | No | 2026-07-19 | 2026-07-25 | 2026-07-19 to 2026-07-25 | 292 | 125 | 167
TA 419 | detail | No | 2024-05-19 | 2024-05-25 | 2024-05-19 to 2024-05-25 | 1 | 0 | 1
TA 419 | detail | No | 2024-05-26 | 2024-06-01 | 2024-05-26 to 2024-06-01 | 4 | 0 | 4
TA 419 | detail | No | 2024-06-02 | 2024-06-08 | 2024-06-02 to 2024-06-08 | 6 | 0 | 6
TA 419 | detail | No | 2024-06-09 | 2024-06-15 | 2024-06-09 to 2024-06-15 | 7 | 0 | 7
TA 419 | detail | No | 2024-06-16 | 2024-06-22 | 2024-06-16 to 2024-06-22 | 8 | 0 | 8
TA 419 | detail | No | 2024-06-23 | 2024-06-29 | 2024-06-23 to 2024-06-29 | 11 | 0 | 11
TA 419 | detail | No | 2024-06-30 | 2024-07-06 | 2024-06-30 to 2024-07-06 | 12 | 0 | 12
TA 419 | detail | No | 2024-07-07 | 2024-07-13 | 2024-07-07 to 2024-07-13 | 16 | 0 | 16
TA 419 | detail | No | 2024-07-14 | 2024-07-20 | 2024-07-14 to 2024-07-20 | 21 | 0 | 21
TA 419 | detail | No | 2024-07-21 | 2024-07-27 | 2024-07-21 to 2024-07-27 | 26 | 0 | 26
TA 419 | detail | No | 2024-07-28 | 2024-08-03 | 2024-07-28 to 2024-08-03 | 29 | 0 | 29
TA 419 | detail | No | 2024-08-04 | 2024-08-10 | 2024-08-04 to 2024-08-10 | 33 | 0 | 33
TA 419 | detail | No | 2024-08-11 | 2024-08-17 | 2024-08-11 to 2024-08-17 | 36 | 0 | 36
TA 419 | detail | No | 2024-08-25 | 2024-08-31 | 2024-08-25 to 2024-08-31 | 37 | 0 | 37
TA 419 | detail | No | 2024-09-01 | 2024-09-07 | 2024-09-01 to 2024-09-07 | 40 | 0 | 40
TA 419 | detail | No | 2024-09-08 | 2024-09-14 | 2024-09-08 to 2024-09-14 | 41 | 0 | 41
TA 419 | detail | No | 2024-09-15 | 2024-09-21 | 2024-09-15 to 2024-09-21 | 45 | 0 | 45
TA 419 | detail | No | 2024-09-22 | 2024-09-28 | 2024-09-22 to 2024-09-28 | 50 | 0 | 50
TA 419 | detail | No | 2024-09-29 | 2024-10-05 | 2024-09-29 to 2024-10-05 | 54 | 0 | 54
TA 419 | detail | No | 2024-10-06 | 2024-10-12 | 2024-10-06 to 2024-10-12 | 59 | 0 | 59
TA 419 | detail | No | 2024-10-13 | 2024-10-19 | 2024-10-13 to 2024-10-19 | 64 | 0 | 64
TA 419 | detail | No | 2024-10-20 | 2024-10-26 | 2024-10-20 to 2024-10-26 | 68 | 0 | 68
TA 419 | detail | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 | 71 | 0 | 71
TA 419 | detail | No | 2024-11-03 | 2024-11-09 | 2024-11-03 to 2024-11-09 | 74 | 0 | 74
TA 419 | detail | No | 2024-11-10 | 2024-11-16 | 2024-11-10 to 2024-11-16 | 75 | 0 | 75
TA 419 | detail | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 | 79 | 0 | 79
TA 419 | detail | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 | 85 | 2 | 83
TA 419 | detail | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 | 86 | 4 | 82
TA 419 | detail | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 | 91 | 8 | 83
TA 419 | detail | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 | 93 | 10 | 83
TA 419 | detail | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 | 97 | 13 | 84
TA 419 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 98 | 16 | 82
TA 419 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 99 | 18 | 81
TA 419 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 101 | 22 | 79
TA 419 | detail | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 | 102 | 25 | 77
TA 419 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 104 | 30 | 74
TA 419 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 106 | 32 | 74
TA 419 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 109 | 38 | 71
TA 419 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 111 | 40 | 71
TA 419 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 114 | 46 | 68
TA 419 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 115 | 49 | 66
TA 419 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 116 | 50 | 66
TA 419 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 119 | 53 | 66
TA 419 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 120 | 56 | 64
TA 419 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 124 | 58 | 66
TA 419 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 126 | 64 | 62
TA 419 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 131 | 66 | 65
TA 419 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 133 | 70 | 63
TA 419 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 135 | 73 | 62
TA 419 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 138 | 74 | 64
TA 419 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 141 | 75 | 66
TA 419 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 145 | 76 | 69
TA 419 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 146 | 77 | 69
TA 419 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 148 | 78 | 70
TA 419 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 151 | 79 | 72
TA 419 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 152 | 79 | 73
TA 419 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 153 | 80 | 73
TA 419 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 154 | 82 | 72
TA 419 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 155 | 84 | 71
TA 419 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 156 | 85 | 71
TA 419 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 157 | 87 | 70
TA 419 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 157 | 88 | 69
TA 419 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 157 | 89 | 68
TA 419 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 157 | 91 | 66
TA 419 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 158 | 92 | 66
TA 419 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 159 | 95 | 64
TA 419 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 161 | 96 | 65
TA 419 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 161 | 98 | 63
TA 419 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 163 | 98 | 65
TA 419 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 164 | 100 | 64
TA 419 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 164 | 102 | 62
TA 419 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 166 | 103 | 63
TA 419 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 167 | 106 | 61
TA 419 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 168 | 108 | 60
TA 419 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 175 | 111 | 64
TA 419 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 177 | 112 | 65
TA 419 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 184 | 118 | 66
TA 419 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 186 | 124 | 62
TA 419 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 192 | 134 | 58
TA 419 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 197 | 144 | 53
TA 419 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 200 | 150 | 50
TA 419 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 205 | 158 | 47
TA 419 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 210 | 165 | 45
TA 419 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 212 | 170 | 42
TA 419 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 215 | 175 | 40
TA 419 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 215 | 181 | 34
TA 419 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 219 | 182 | 37
TA 419 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 220 | 183 | 37
TA 419 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 221 | 183 | 38
TA 419 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 222 | 183 | 39
TA 419 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 223 | 183 | 40
TA 419 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 225 | 184 | 41
TA 419 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 227 | 184 | 43
TA 419 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 228 | 185 | 43
TA 419 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 229 | 188 | 41
TA 419 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 232 | 192 | 40
TA 419 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 236 | 195 | 41
TA 419 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 242 | 197 | 45
TA 419 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 245 | 202 | 43
TA 419 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 249 | 204 | 45
TA 419 | detail | No | 2026-05-24 | 2026-05-30 | 2026-05-24 to 2026-05-30 | 253 | 207 | 46
TA 419 | detail | No | 2026-05-31 | 2026-06-06 | 2026-05-31 to 2026-06-06 | 261 | 208 | 53
TA 419 | detail | No | 2026-06-07 | 2026-06-13 | 2026-06-07 to 2026-06-13 | 265 | 213 | 52
TA 419 | detail | No | 2026-06-14 | 2026-06-20 | 2026-06-14 to 2026-06-20 | 266 | 216 | 50
TA 419 | detail | No | 2026-06-21 | 2026-06-27 | 2026-06-21 to 2026-06-27 | 270 | 218 | 52
TA 419 | detail | No | 2026-06-28 | 2026-07-04 | 2026-06-28 to 2026-07-04 | 275 | 226 | 49
TA 419 | detail | No | 2026-07-05 | 2026-07-11 | 2026-07-05 to 2026-07-11 | 275 | 228 | 47
TA 419 | detail | No | 2026-07-12 | 2026-07-18 | 2026-07-12 to 2026-07-18 | 279 | 233 | 46
TA 419 | detail | No | 2026-07-19 | 2026-07-25 | 2026-07-19 to 2026-07-25 | 284 | 237 | 47
TA 419 | detail | No | 2026-07-26 | 2026-08-01 | 2026-07-26 to 2026-08-01 | 286 | 243 | 43
TA 419 | detail | No | 2026-08-02 | 2026-08-08 | 2026-08-02 to 2026-08-08 | 287 | 245 | 42
TA 419 | detail | No | 2026-08-09 | 2026-08-15 | 2026-08-09 to 2026-08-15 | 287 | 246 | 41
TA 421 | detail | No | 2024-05-19 | 2024-05-25 | 2024-05-19 to 2024-05-25 | 1 | 0 | 1
TA 421 | detail | No | 2024-06-02 | 2024-06-08 | 2024-06-02 to 2024-06-08 | 3 | 0 | 3
TA 421 | detail | No | 2024-06-09 | 2024-06-15 | 2024-06-09 to 2024-06-15 | 5 | 0 | 5
TA 421 | detail | No | 2024-06-16 | 2024-06-22 | 2024-06-16 to 2024-06-22 | 8 | 0 | 8
TA 421 | detail | No | 2024-06-23 | 2024-06-29 | 2024-06-23 to 2024-06-29 | 14 | 0 | 14
TA 421 | detail | No | 2024-06-30 | 2024-07-06 | 2024-06-30 to 2024-07-06 | 18 | 0 | 18
TA 421 | detail | No | 2024-07-07 | 2024-07-13 | 2024-07-07 to 2024-07-13 | 24 | 0 | 24
TA 421 | detail | No | 2024-07-14 | 2024-07-20 | 2024-07-14 to 2024-07-20 | 30 | 1 | 29
TA 421 | detail | No | 2024-07-21 | 2024-07-27 | 2024-07-21 to 2024-07-27 | 32 | 1 | 31
TA 421 | detail | No | 2024-07-28 | 2024-08-03 | 2024-07-28 to 2024-08-03 | 38 | 3 | 35
TA 421 | detail | No | 2024-08-04 | 2024-08-10 | 2024-08-04 to 2024-08-10 | 41 | 4 | 37
TA 421 | detail | No | 2024-08-11 | 2024-08-17 | 2024-08-11 to 2024-08-17 | 51 | 5 | 46
TA 421 | detail | No | 2024-08-18 | 2024-08-24 | 2024-08-18 to 2024-08-24 | 58 | 7 | 51
TA 421 | detail | No | 2024-08-25 | 2024-08-31 | 2024-08-25 to 2024-08-31 | 64 | 8 | 56
TA 421 | detail | No | 2024-09-01 | 2024-09-07 | 2024-09-01 to 2024-09-07 | 65 | 9 | 56
TA 421 | detail | No | 2024-09-08 | 2024-09-14 | 2024-09-08 to 2024-09-14 | 70 | 11 | 59
TA 421 | detail | No | 2024-09-15 | 2024-09-21 | 2024-09-15 to 2024-09-21 | 76 | 13 | 63
TA 421 | detail | No | 2024-09-22 | 2024-09-28 | 2024-09-22 to 2024-09-28 | 80 | 15 | 65
TA 421 | detail | No | 2024-09-29 | 2024-10-05 | 2024-09-29 to 2024-10-05 | 88 | 20 | 68
TA 421 | detail | No | 2024-10-06 | 2024-10-12 | 2024-10-06 to 2024-10-12 | 91 | 21 | 70
TA 421 | detail | No | 2024-10-13 | 2024-10-19 | 2024-10-13 to 2024-10-19 | 98 | 25 | 73
TA 421 | detail | No | 2024-10-20 | 2024-10-26 | 2024-10-20 to 2024-10-26 | 104 | 28 | 76
TA 421 | detail | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 | 112 | 33 | 79
TA 421 | detail | No | 2024-11-03 | 2024-11-09 | 2024-11-03 to 2024-11-09 | 118 | 37 | 81
TA 421 | detail | No | 2024-11-10 | 2024-11-16 | 2024-11-10 to 2024-11-16 | 126 | 42 | 84
TA 421 | detail | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 | 132 | 45 | 87
TA 421 | detail | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 | 150 | 50 | 100
TA 421 | detail | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 | 157 | 53 | 104
TA 421 | detail | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 | 170 | 56 | 114
TA 421 | detail | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 | 179 | 59 | 120
TA 421 | detail | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 | 193 | 64 | 129
TA 421 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 202 | 66 | 136
TA 421 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 211 | 68 | 143
TA 421 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 224 | 72 | 152
TA 421 | detail | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 | 234 | 75 | 159
TA 421 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 249 | 79 | 170
TA 421 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 256 | 82 | 174
TA 421 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 269 | 86 | 183
TA 421 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 283 | 90 | 193
TA 421 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 297 | 96 | 201
TA 421 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 309 | 100 | 209
TA 421 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 317 | 105 | 212
TA 421 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 325 | 110 | 215
TA 421 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 335 | 117 | 218
TA 421 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 341 | 122 | 219
TA 421 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 346 | 125 | 221
TA 421 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 355 | 131 | 224
TA 421 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 363 | 137 | 226
TA 421 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 375 | 143 | 232
TA 421 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 387 | 150 | 237
TA 421 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 400 | 154 | 246
TA 421 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 413 | 157 | 256
TA 421 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 426 | 159 | 267
TA 421 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 435 | 162 | 273
TA 421 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 441 | 163 | 278
TA 421 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 452 | 166 | 286
TA 421 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 458 | 169 | 289
TA 421 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 466 | 173 | 293
TA 421 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 474 | 178 | 296
TA 421 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 483 | 183 | 300
TA 421 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 491 | 188 | 303
TA 421 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 500 | 196 | 304
TA 421 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 507 | 202 | 305
TA 421 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 512 | 207 | 305
TA 421 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 514 | 209 | 305
TA 421 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 520 | 214 | 306
TA 421 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 526 | 220 | 306
TA 421 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 533 | 227 | 306
TA 421 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 537 | 231 | 306
TA 421 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 541 | 235 | 306
TA 421 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 545 | 239 | 306
TA 421 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 550 | 244 | 306
TA 421 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 554 | 248 | 306
TA 421 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 561 | 253 | 308
TA 421 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 565 | 256 | 309
TA 421 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 569 | 260 | 309
TA 421 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 573 | 264 | 309
TA 421 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 578 | 269 | 309
TA 421 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 589 | 277 | 312
TA 421 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 594 | 281 | 313
TA 421 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 600 | 287 | 313
TA 421 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 605 | 292 | 313
TA 421 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 611 | 297 | 314
TA 421 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 615 | 300 | 315
TA 421 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 618 | 303 | 315
TA 421 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 620 | 305 | 315
TA 421 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 621 | 305 | 316
TA 421 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 623 | 305 | 318
TA 421 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 626 | 305 | 321
TA 421 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 628 | 305 | 323
TA 421 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 629 | 305 | 324
TA 421 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 630 | 305 | 325
TA 421 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 631 | 305 | 326
TA 421 | detail | No | 2026-06-14 | 2026-06-20 | 2026-06-14 to 2026-06-20 | 632 | 305 | 327
TA 421 | detail | No | 2026-06-21 | 2026-06-27 | 2026-06-21 to 2026-06-27 | 634 | 305 | 329
TA 505 | detail | No | 2024-03-24 | 2024-03-30 | 2024-03-24 to 2024-03-30 | 1 | 0 | 1
TA 505 | detail | No | 2024-03-31 | 2024-04-06 | 2024-03-31 to 2024-04-06 | 2 | 0 | 2
TA 505 | detail | No | 2024-04-28 | 2024-05-04 | 2024-04-28 to 2024-05-04 | 3 | 0 | 3
TA 505 | detail | No | 2024-10-06 | 2024-10-12 | 2024-10-06 to 2024-10-12 | 7 | 0 | 7
TA 505 | detail | No | 2024-10-20 | 2024-10-26 | 2024-10-20 to 2024-10-26 | 10 | 0 | 10
TA 505 | detail | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 | 13 | 0 | 13
TA 505 | detail | No | 2024-11-03 | 2024-11-09 | 2024-11-03 to 2024-11-09 | 15 | 0 | 15
TA 505 | detail | No | 2024-11-10 | 2024-11-16 | 2024-11-10 to 2024-11-16 | 19 | 0 | 19
TA 505 | detail | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 | 28 | 0 | 28
TA 505 | detail | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 | 38 | 0 | 38
TA 505 | detail | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 | 43 | 0 | 43
TA 505 | detail | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 | 50 | 0 | 50
TA 505 | detail | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 | 60 | 0 | 60
TA 505 | detail | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 | 68 | 0 | 68
TA 505 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 76 | 0 | 76
TA 505 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 79 | 0 | 79
TA 505 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 88 | 0 | 88
TA 505 | detail | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 | 97 | 2 | 95
TA 505 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 104 | 4 | 100
TA 505 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 110 | 6 | 104
TA 505 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 118 | 8 | 110
TA 505 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 125 | 9 | 116
TA 505 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 136 | 11 | 125
TA 505 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 141 | 13 | 128
TA 505 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 143 | 15 | 128
TA 505 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 146 | 17 | 129
TA 505 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 150 | 20 | 130
TA 505 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 158 | 23 | 135
TA 505 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 172 | 28 | 144
TA 505 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 181 | 33 | 148
TA 505 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 197 | 38 | 159
TA 505 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 208 | 43 | 165
TA 505 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 220 | 48 | 172
TA 505 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 229 | 53 | 176
TA 505 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 240 | 58 | 182
TA 505 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 252 | 65 | 187
TA 505 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 258 | 70 | 188
TA 505 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 264 | 72 | 192
TA 505 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 264 | 75 | 189
TA 505 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 265 | 79 | 186
TA 505 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 267 | 81 | 186
TA 505 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 267 | 84 | 183
TA 505 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 269 | 86 | 183
TA 505 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 269 | 87 | 182
TA 505 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 269 | 90 | 179
TA 505 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 269 | 91 | 178
TA 505 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 269 | 93 | 176
TA 505 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 269 | 95 | 174
TA 505 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 270 | 97 | 173
TA 505 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 271 | 98 | 173
TA 505 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 273 | 105 | 168
TA 505 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 275 | 111 | 164
TA 505 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 278 | 119 | 159
TA 505 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 280 | 130 | 150
TA 505 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 282 | 134 | 148
TA 505 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 288 | 145 | 143
TA 505 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 291 | 149 | 142
TA 505 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 293 | 153 | 140
TA 505 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 296 | 160 | 136
TA 505 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 300 | 167 | 133
TA 505 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 304 | 174 | 130
TA 505 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 309 | 185 | 124
TA 505 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 311 | 193 | 118
TA 505 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 316 | 206 | 110
TA 505 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 319 | 216 | 103
TA 505 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 322 | 227 | 95
TA 505 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 327 | 239 | 88
TA 505 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 331 | 247 | 84
TA 505 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 334 | 254 | 80
TA 505 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 339 | 265 | 74
TA 505 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 344 | 276 | 68
TA 505 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 347 | 280 | 67
TA 505 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 349 | 288 | 61
TA 505 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 352 | 293 | 59
TA 505 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 354 | 300 | 54
TA 505 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 355 | 303 | 52
TA 505 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 359 | 309 | 50
TA 505 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 361 | 312 | 49
TA 505 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 361 | 317 | 44
TA 505 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 362 | 324 | 38
TA 505 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 364 | 330 | 34
TA 505 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 368 | 338 | 30
TA 505 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 369 | 343 | 26
TA 505 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 370 | 347 | 23
TA 505 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 370 | 351 | 19
TA 505 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 372 | 354 | 18
TA 505 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 373 | 354 | 19
TA 505 | detail | No | 2026-05-24 | 2026-05-30 | 2026-05-24 to 2026-05-30 | 374 | 357 | 17
TA 505 | detail | No | 2026-05-31 | 2026-06-06 | 2026-05-31 to 2026-06-06 | 374 | 360 | 14
TA 505 | detail | No | 2026-06-07 | 2026-06-13 | 2026-06-07 to 2026-06-13 | 374 | 362 | 12
TA 505 | detail | No | 2026-06-14 | 2026-06-20 | 2026-06-14 to 2026-06-20 | 376 | 362 | 14
TA 505 | detail | No | 2026-06-21 | 2026-06-27 | 2026-06-21 to 2026-06-27 | 377 | 363 | 14
TA 505 | detail | No | 2026-06-28 | 2026-07-04 | 2026-06-28 to 2026-07-04 | 378 | 363 | 15
TA 505 | detail | No | 2026-07-12 | 2026-07-18 | 2026-07-12 to 2026-07-18 | 378 | 364 | 14
TA 505 | detail | No | 2026-07-26 | 2026-08-01 | 2026-07-26 to 2026-08-01 | 378 | 365 | 13
TA 509 | snapshot_fallback | Yes | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 |  | 1
TA 509 | snapshot_fallback | Yes | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 |  | 4
TA 509 | snapshot_fallback | Yes | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 |  | 11
TA 509 | snapshot_fallback | Yes | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 |  | 17
TA 509 | snapshot_fallback | Yes | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 |  | 22
TA 509 | snapshot_fallback | Yes | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 |  | 25
TA 509 | snapshot_fallback | Yes | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 |  | 28
TA 509 | snapshot_fallback | Yes | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 |  | 30
TA 509 | snapshot_fallback | Yes | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 |  | 32
TA 509 | snapshot_fallback | Yes | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 |  | 33
TA 509 | snapshot_fallback | Yes | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 |  | 34
TA 509 | snapshot_fallback | Yes | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 |  | 38
TA 509 | snapshot_fallback | Yes | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 |  | 43
TA 509 | snapshot_fallback | Yes | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 |  | 46
TA 509 | snapshot_fallback | Yes | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 |  | 51
TA 509 | snapshot_fallback | Yes | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 |  | 54
TA 509 | snapshot_fallback | Yes | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 |  | 60
TA 509 | snapshot_fallback | Yes | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 |  | 66
TA 509 | snapshot_fallback | Yes | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 |  | 69
TA 509 | snapshot_fallback | Yes | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 |  | 73
TA 509 | snapshot_fallback | Yes | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 |  | 80
TA 509 | snapshot_fallback | Yes | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 |  | 88
TA 509 | snapshot_fallback | Yes | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 |  | 96
TA 509 | snapshot_fallback | Yes | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 |  | 100
TA 509 | snapshot_fallback | Yes | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 |  | 111
TA 509 | snapshot_fallback | Yes | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 |  | 116
TA 509 | snapshot_fallback | Yes | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 |  | 125
TA 509 | snapshot_fallback | Yes | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 |  | 129
TA 509 | snapshot_fallback | Yes | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 |  | 141
TA 509 | snapshot_fallback | Yes | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 |  | 152
TA 509 | snapshot_fallback | Yes | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 |  | 162
TA 509 | snapshot_fallback | Yes | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 |  | 170
TA 509 | snapshot_fallback | Yes | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 |  | 182
TA 509 | snapshot_fallback | Yes | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 |  | 186
TA 509 | snapshot_fallback | Yes | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 |  | 196
TA 509 | snapshot_fallback | Yes | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 |  | 202
TA 509 | snapshot_fallback | Yes | 2026-05-24 | 2026-05-30 | 2026-05-24 to 2026-05-30 |  | 207
TA 509 | snapshot_fallback | Yes | 2026-05-31 | 2026-06-06 | 2026-05-31 to 2026-06-06 | 268 | 209 | 59
TA 509 | snapshot_fallback | Yes | 2026-06-07 | 2026-06-13 | 2026-06-07 to 2026-06-13 | 268 | 215 | 53
TA 509 | snapshot_fallback | Yes | 2026-06-14 | 2026-06-20 | 2026-06-14 to 2026-06-20 | 272 | 217 | 55
TA 509 | snapshot_fallback | Yes | 2026-06-21 | 2026-06-27 | 2026-06-21 to 2026-06-27 | 274 | 219 | 55
TA 509 | snapshot_fallback | Yes | 2026-06-28 | 2026-07-04 | 2026-06-28 to 2026-07-04 | 274 | 222 | 52
TA 509 | snapshot_fallback | Yes | 2026-07-05 | 2026-07-11 | 2026-07-05 to 2026-07-11 | 276 | 223 | 53
TA 509 | snapshot_fallback | Yes | 2026-07-12 | 2026-07-18 | 2026-07-12 to 2026-07-18 | 277 | 225 | 52
TA 509 | snapshot_fallback | Yes | 2026-07-19 | 2026-07-25 | 2026-07-19 to 2026-07-25 | 279 | 226 | 53
TA 509 | snapshot_fallback | Yes | 2026-07-26 | 2026-08-01 | 2026-07-26 to 2026-08-01 | 279 | 229 | 50
TA 509 | snapshot_fallback | Yes | 2026-08-02 | 2026-08-08 | 2026-08-02 to 2026-08-08 | 283 | 229 | 54
TA 509 | snapshot_fallback | Yes | 2026-08-09 | 2026-08-15 | 2026-08-09 to 2026-08-15 | 283 | 230 | 53
TA 510 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 2 | 0 | 2
TA 510 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 4 | 0 | 4
TA 510 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 6 | 0 | 6
TA 510 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 7 | 0 | 7
TA 510 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 8 | 0 | 8
TA 510 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 9 | 0 | 9
TA 510 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 10 | 0 | 10
TA 510 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 12 | 0 | 12
TA 510 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 15 | 0 | 15
TA 510 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 17 | 0 | 17
TA 510 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 19 | 0 | 19
TA 510 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 22 | 0 | 22
TA 510 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 24 | 0 | 24
TA 510 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 25 | 0 | 25
TA 510 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 27 | 0 | 27
TA 510 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 28 | 0 | 28
TA 510 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 30 | 0 | 30
TA 510 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 32 | 0 | 32
TA 510 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 33 | 0 | 33
TA 510 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 36 | 0 | 36
TA 510 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 37 | 0 | 37
TA 510 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 40 | 0 | 40
TA 510 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 41 | 0 | 41
TA 510 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 43 | 0 | 43
TA 510 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 47 | 0 | 47
TA 510 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 49 | 1 | 48
TA 510 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 51 | 3 | 48
TA 510 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 52 | 4 | 48
TA 510 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 54 | 9 | 45
TA 510 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 56 | 10 | 46
TA 510 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 59 | 12 | 47
TA 510 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 59 | 14 | 45
TA 510 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 60 | 17 | 43
TA 510 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 60 | 18 | 42
TA 510 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 61 | 19 | 42
TA 510 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 61 | 21 | 40
TA 510 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 63 | 23 | 40
TA 510 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 64 | 25 | 39
TA 510 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 65 | 26 | 39
TA 510 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 67 | 27 | 40
TA 510 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 70 | 28 | 42
TA 510 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 72 | 29 | 43
TA 510 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 73 | 31 | 42
TA 510 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 75 | 33 | 42
TA 510 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 80 | 37 | 43
TA 510 | detail | No | 2026-05-24 | 2026-05-30 | 2026-05-24 to 2026-05-30 | 82 | 40 | 42
TA 510 | detail | No | 2026-05-31 | 2026-06-06 | 2026-05-31 to 2026-06-06 | 87 | 42 | 45
TA 510 | detail | No | 2026-06-07 | 2026-06-13 | 2026-06-07 to 2026-06-13 | 89 | 45 | 44
TA 510 | detail | No | 2026-06-14 | 2026-06-20 | 2026-06-14 to 2026-06-20 | 93 | 45 | 48
TA 510 | detail | No | 2026-06-21 | 2026-06-27 | 2026-06-21 to 2026-06-27 | 95 | 45 | 50
TA 510 | detail | No | 2026-06-28 | 2026-07-04 | 2026-06-28 to 2026-07-04 | 95 | 46 | 49
TA 510 | detail | No | 2026-07-12 | 2026-07-18 | 2026-07-12 to 2026-07-18 | 95 | 47 | 48
TA 510 | detail | No | 2026-08-02 | 2026-08-08 | 2026-08-02 to 2026-08-08 | 95 | 48 | 47
TA 512 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 3 | 0 | 3
TA 512 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 6 | 0 | 6
TA 512 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 12 | 0 | 12
TA 512 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 18 | 0 | 18
TA 512 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 26 | 0 | 26
TA 512 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 33 | 0 | 33
TA 512 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 37 | 0 | 37
TA 512 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 44 | 0 | 44
TA 512 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 49 | 0 | 49
TA 512 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 53 | 0 | 53
TA 512 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 59 | 0 | 59
TA 512 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 65 | 0 | 65
TA 512 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 72 | 0 | 72
TA 512 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 76 | 0 | 76
TA 512 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 82 | 0 | 82
TA 512 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 88 | 0 | 88
TA 512 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 95 | 0 | 95
TA 512 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 101 | 0 | 101
TA 512 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 110 | 0 | 110
TA 512 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 117 | 0 | 117
TA 512 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 127 | 0 | 127
TA 512 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 137 | 0 | 137
TA 512 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 146 | 0 | 146
TA 512 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 157 | 0 | 157
TA 512 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 161 | 1 | 160
TA 512 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 165 | 3 | 162
TA 512 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 168 | 6 | 162
TA 512 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 174 | 10 | 164
TA 512 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 177 | 15 | 162
TA 512 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 181 | 18 | 163
TA 512 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 186 | 23 | 163
TA 512 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 191 | 26 | 165
TA 512 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 192 | 28 | 164
TA 512 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 199 | 32 | 167
TA 512 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 203 | 34 | 169
TA 512 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 213 | 36 | 177
TA 512 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 219 | 39 | 180
TA 512 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 227 | 42 | 185
TA 512 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 234 | 47 | 187
TA 512 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 240 | 52 | 188
TA 512 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 249 | 56 | 193
TA 512 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 257 | 65 | 192
TA 512 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 266 | 72 | 194
TA 512 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 273 | 77 | 196
TA 512 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 277 | 86 | 191
TA 512 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 279 | 90 | 189
TA 512 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 284 | 99 | 185
TA 512 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 286 | 110 | 176
TA 512 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 287 | 126 | 161
TA 512 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 289 | 139 | 150
TA 512 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 289 | 152 | 137
TA 512 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 290 | 160 | 130
TA 512 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 291 | 171 | 120
TA 512 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 292 | 178 | 114
TA 512 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 293 | 186 | 107
TA 512 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 294 | 193 | 101
TA 512 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 294 | 198 | 96
TA 512 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 295 | 206 | 89
TA 512 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 296 | 209 | 87
TA 512 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 298 | 215 | 83
TA 512 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 300 | 217 | 83
TA 512 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 301 | 218 | 83
TA 512 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 302 | 220 | 82
TA 512 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 302 | 222 | 80
TA 512 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 303 | 223 | 80
TA 512 | detail | No | 2026-05-24 | 2026-05-30 | 2026-05-24 to 2026-05-30 | 305 | 226 | 79
TA 512 | detail | No | 2026-05-31 | 2026-06-06 | 2026-05-31 to 2026-06-06 | 308 | 228 | 80
TA 512 | detail | No | 2026-06-07 | 2026-06-13 | 2026-06-07 to 2026-06-13 | 310 | 229 | 81
TA 512 | detail | No | 2026-06-14 | 2026-06-20 | 2026-06-14 to 2026-06-20 | 310 | 236 | 74
TA 512 | detail | No | 2026-06-21 | 2026-06-27 | 2026-06-21 to 2026-06-27 | 312 | 238 | 74
TA 512 | detail | No | 2026-06-28 | 2026-07-04 | 2026-06-28 to 2026-07-04 | 314 | 243 | 71
TA 512 | detail | No | 2026-07-05 | 2026-07-11 | 2026-07-05 to 2026-07-11 | 316 | 250 | 66
TA 512 | detail | No | 2026-07-12 | 2026-07-18 | 2026-07-12 to 2026-07-18 | 316 | 256 | 60
TA 512 | detail | No | 2026-07-19 | 2026-07-25 | 2026-07-19 to 2026-07-25 | 316 | 267 | 49
TA 512 | detail | No | 2026-07-26 | 2026-08-01 | 2026-07-26 to 2026-08-01 | 316 | 274 | 42
TA 512 | detail | No | 2026-08-02 | 2026-08-08 | 2026-08-02 to 2026-08-08 | 317 | 281 | 36
TA 512 | detail | No | 2026-08-09 | 2026-08-15 | 2026-08-09 to 2026-08-15 | 317 | 284 | 33
TA 513 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 1 | 0 | 1
TA 513 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 3 | 0 | 3
TA 513 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 6 | 0 | 6
TA 513 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 9 | 0 | 9
TA 513 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 12 | 0 | 12
TA 513 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 17 | 0 | 17
TA 513 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 22 | 0 | 22
TA 513 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 24 | 0 | 24
TA 513 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 28 | 0 | 28
TA 513 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 30 | 0 | 30
TA 513 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 33 | 0 | 33
TA 513 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 35 | 0 | 35
TA 513 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 36 | 0 | 36
TA 513 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 38 | 0 | 38
TA 513 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 41 | 0 | 41
TA 513 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 43 | 0 | 43
TA 513 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 45 | 0 | 45
TA 513 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 48 | 0 | 48
TA 513 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 49 | 0 | 49
TA 513 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 50 | 0 | 50
TA 513 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 51 | 0 | 51
TA 513 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 52 | 0 | 52
TA 513 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 53 | 0 | 53
TA 513 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 57 | 0 | 57
TA 513 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 59 | 1 | 58
TA 513 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 60 | 3 | 57
TA 513 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 62 | 4 | 58
TA 513 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 62 | 5 | 57
TA 513 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 62 | 7 | 55
TA 513 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 62 | 8 | 54
TA 513 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 62 | 10 | 52
TA 513 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 63 | 12 | 51
TA 513 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 63 | 13 | 50
TA 513 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 64 | 14 | 50
TA 513 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 65 | 15 | 50
TA 513 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 66 | 16 | 50
TA 513 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 68 | 17 | 51
TA 513 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 69 | 18 | 51
TA 513 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 69 | 19 | 50
TA 513 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 69 | 20 | 49
TA 513 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 69 | 21 | 48
TA 513 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 70 | 21 | 49
TA 513 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 71 | 21 | 50
TA 513 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 72 | 22 | 50
TA 513 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 72 | 23 | 49
TA 513 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 72 | 25 | 47
TA 513 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 72 | 26 | 46
TA 513 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 72 | 27 | 45
TA 513 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 73 | 28 | 45
TA 513 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 76 | 28 | 48
TA 513 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 80 | 28 | 52
TA 513 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 85 | 30 | 55
TA 513 | detail | No | 2026-05-24 | 2026-05-30 | 2026-05-24 to 2026-05-30 | 89 | 30 | 59
TA 513 | detail | No | 2026-05-31 | 2026-06-06 | 2026-05-31 to 2026-06-06 | 90 | 32 | 58
TA 513 | detail | No | 2026-06-07 | 2026-06-13 | 2026-06-07 to 2026-06-13 | 94 | 33 | 61
TA 513 | detail | No | 2026-06-14 | 2026-06-20 | 2026-06-14 to 2026-06-20 | 98 | 34 | 64
TA 513 | detail | No | 2026-06-21 | 2026-06-27 | 2026-06-21 to 2026-06-27 | 100 | 35 | 65
TA 513 | detail | No | 2026-07-05 | 2026-07-11 | 2026-07-05 to 2026-07-11 | 102 | 35 | 67
TA 513 | detail | No | 2026-07-12 | 2026-07-18 | 2026-07-12 to 2026-07-18 | 104 | 35 | 69
TA 513 | detail | No | 2026-07-19 | 2026-07-25 | 2026-07-19 to 2026-07-25 | 105 | 35 | 70
TA 513 | detail | No | 2026-07-26 | 2026-08-01 | 2026-07-26 to 2026-08-01 | 106 | 35 | 71
TA 513 | detail | No | 2026-08-02 | 2026-08-08 | 2026-08-02 to 2026-08-08 | 107 | 35 | 72
TA 513 | detail | No | 2026-08-09 | 2026-08-15 | 2026-08-09 to 2026-08-15 | 109 | 35 | 74
TA 515 | missing | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 |  | 1
TA 515 | missing | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 |  | 2
TA 601 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 0 | 1 | -1
TA 601 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 1 | 1 | 0
TA 601 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 2 | 1 | 1
TA 601 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 3 | 1 | 2
TA 601 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 4 | 1 | 3
TA 601 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 5 | 1 | 4
TA 601 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 10 | 1 | 9
TA 601 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 12 | 1 | 11
TA 601 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 14 | 1 | 13
TA 601 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 17 | 1 | 16
TA 601 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 18 | 1 | 17
TA 601 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 21 | 1 | 20
TA 601 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 23 | 1 | 22
TA 601 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 25 | 1 | 24
TA 601 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 30 | 2 | 28
TA 601 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 37 | 3 | 34
TA 601 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 44 | 4 | 40
TA 601 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 52 | 7 | 45
TA 601 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 62 | 11 | 51
TA 601 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 73 | 17 | 56
TA 601 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 92 | 25 | 67
TA 601 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 100 | 31 | 69
TA 601 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 114 | 38 | 76
TA 601 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 124 | 46 | 78
TA 601 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 138 | 54 | 84
TA 601 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 144 | 58 | 86
TA 601 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 151 | 61 | 90
TA 601 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 159 | 65 | 94
TA 601 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 164 | 66 | 98
TA 601 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 168 | 68 | 100
TA 601 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 171 | 69 | 102
TA 601 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 177 | 70 | 107
TA 601 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 179 | 70 | 109
TA 601 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 182 | 70 | 112
TA 601 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 184 | 70 | 114
TA 601 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 187 | 70 | 117
TA 601 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 191 | 71 | 120
TA 601 | detail | No | 2026-05-24 | 2026-05-30 | 2026-05-24 to 2026-05-30 | 193 | 71 | 122
TA 601 | detail | No | 2026-05-31 | 2026-06-06 | 2026-05-31 to 2026-06-06 | 197 | 72 | 125
TA 601 | detail | No | 2026-06-07 | 2026-06-13 | 2026-06-07 to 2026-06-13 | 204 | 75 | 129
TA 601 | detail | No | 2026-06-14 | 2026-06-20 | 2026-06-14 to 2026-06-20 | 214 | 79 | 135
TA 601 | detail | No | 2026-06-21 | 2026-06-27 | 2026-06-21 to 2026-06-27 | 228 | 84 | 144
TA 601 | detail | No | 2026-06-28 | 2026-07-04 | 2026-06-28 to 2026-07-04 | 240 | 90 | 150
TA 601 | detail | No | 2026-07-05 | 2026-07-11 | 2026-07-05 to 2026-07-11 | 257 | 98 | 159
TA 601 | detail | No | 2026-07-12 | 2026-07-18 | 2026-07-12 to 2026-07-18 | 271 | 104 | 167
TA 601 | detail | No | 2026-07-19 | 2026-07-25 | 2026-07-19 to 2026-07-25 | 283 | 112 | 171
TA 601 | detail | No | 2026-07-26 | 2026-08-01 | 2026-07-26 to 2026-08-01 | 298 | 118 | 180
TA 601 | detail | No | 2026-08-02 | 2026-08-08 | 2026-08-02 to 2026-08-08 | 305 | 121 | 184
TA 601 | detail | No | 2026-08-09 | 2026-08-15 | 2026-08-09 to 2026-08-15 | 315 | 126 | 189
TA 602 | snapshot_fallback | Yes | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 |  | 3
TA 602 | snapshot_fallback | Yes | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 |  | 4
TA 602 | snapshot_fallback | Yes | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 |  | 7
TA 602 | snapshot_fallback | Yes | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 |  | 10
TA 602 | snapshot_fallback | Yes | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 |  | 14
TA 602 | snapshot_fallback | Yes | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 |  | 17
TA 602 | snapshot_fallback | Yes | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 |  | 19
TA 602 | snapshot_fallback | Yes | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 |  | 20
TA 602 | snapshot_fallback | Yes | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 |  | 22
TA 602 | snapshot_fallback | Yes | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 |  | 24
TA 602 | snapshot_fallback | Yes | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 |  | 31
TA 602 | snapshot_fallback | Yes | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 |  | 38
TA 602 | snapshot_fallback | Yes | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 |  | 46
TA 602 | snapshot_fallback | Yes | 2026-05-24 | 2026-05-30 | 2026-05-24 to 2026-05-30 |  | 51
TA 602 | snapshot_fallback | Yes | 2026-05-31 | 2026-06-06 | 2026-05-31 to 2026-06-06 |  | 57
TA 602 | snapshot_fallback | Yes | 2026-06-07 | 2026-06-13 | 2026-06-07 to 2026-06-13 | 161 | 65 | 96
TA 602 | snapshot_fallback | Yes | 2026-06-14 | 2026-06-20 | 2026-06-14 to 2026-06-20 | 324 | 72 | 252
TA 602 | snapshot_fallback | Yes | 2026-06-21 | 2026-06-27 | 2026-06-21 to 2026-06-27 | 165 | 77 | 88
TA 602 | snapshot_fallback | Yes | 2026-06-28 | 2026-07-04 | 2026-06-28 to 2026-07-04 | 167 | 80 | 87
TA 602 | snapshot_fallback | Yes | 2026-07-05 | 2026-07-11 | 2026-07-05 to 2026-07-11 | 169 | 83 | 86
TA 602 | snapshot_fallback | Yes | 2026-07-12 | 2026-07-18 | 2026-07-12 to 2026-07-18 | 169 | 86 | 83
TA 602 | snapshot_fallback | Yes | 2026-07-19 | 2026-07-25 | 2026-07-19 to 2026-07-25 | 169 | 88 | 81
TA 602 | snapshot_fallback | Yes | 2026-07-26 | 2026-08-01 | 2026-07-26 to 2026-08-01 | 172 | 89 | 83
TA 602 | snapshot_fallback | Yes | 2026-08-02 | 2026-08-08 | 2026-08-02 to 2026-08-08 | 172 | 90 | 82
TA 602 | snapshot_fallback | Yes | 2026-08-09 | 2026-08-15 | 2026-08-09 to 2026-08-15 | 172 | 91 | 81
TB 408 | detail | No | 2023-10-01 | 2023-10-07 | 2023-10-01 to 2023-10-07 | 1 | 0 | 1
TB 408 | detail | No | 2023-11-26 | 2023-12-02 | 2023-11-26 to 2023-12-02 | 2 | 0 | 2
TB 408 | detail | No | 2023-12-31 | 2024-01-06 | 2023-12-31 to 2024-01-06 | 3 | 0 | 3
TB 408 | detail | No | 2024-01-28 | 2024-02-03 | 2024-01-28 to 2024-02-03 | 4 | 0 | 4
TB 408 | detail | No | 2024-02-04 | 2024-02-10 | 2024-02-04 to 2024-02-10 | 4 | 3 | 1
TB 408 | detail | No | 2024-02-11 | 2024-02-17 | 2024-02-11 to 2024-02-17 | 4 | 7 | -3
TB 408 | detail | No | 2024-02-18 | 2024-02-24 | 2024-02-18 to 2024-02-24 | 4 | 15 | -11
TB 408 | detail | No | 2024-02-25 | 2024-03-02 | 2024-02-25 to 2024-03-02 | 5 | 22 | -17
TB 408 | detail | No | 2024-03-03 | 2024-03-09 | 2024-03-03 to 2024-03-09 | 5 | 26 | -21
TB 408 | detail | No | 2024-03-10 | 2024-03-16 | 2024-03-10 to 2024-03-16 | 5 | 31 | -26
TB 408 | detail | No | 2024-03-17 | 2024-03-23 | 2024-03-17 to 2024-03-23 | 5 | 36 | -31
TB 408 | detail | No | 2024-03-24 | 2024-03-30 | 2024-03-24 to 2024-03-30 | 5 | 40 | -35
TB 408 | detail | No | 2024-03-31 | 2024-04-06 | 2024-03-31 to 2024-04-06 | 6 | 44 | -38
TB 408 | detail | No | 2024-04-07 | 2024-04-13 | 2024-04-07 to 2024-04-13 | 6 | 50 | -44
TB 408 | detail | No | 2024-04-14 | 2024-04-20 | 2024-04-14 to 2024-04-20 | 6 | 53 | -47
TB 408 | detail | No | 2024-04-21 | 2024-04-27 | 2024-04-21 to 2024-04-27 | 6 | 60 | -54
TB 408 | detail | No | 2024-04-28 | 2024-05-04 | 2024-04-28 to 2024-05-04 | 7 | 63 | -56
TB 408 | detail | No | 2024-05-05 | 2024-05-11 | 2024-05-05 to 2024-05-11 | 7 | 66 | -59
TB 408 | detail | No | 2024-05-12 | 2024-05-18 | 2024-05-12 to 2024-05-18 | 7 | 69 | -62
TB 408 | detail | No | 2024-05-19 | 2024-05-25 | 2024-05-19 to 2024-05-25 | 7 | 72 | -65
TB 408 | detail | No | 2024-05-26 | 2024-06-01 | 2024-05-26 to 2024-06-01 | 8 | 75 | -67
TB 408 | detail | No | 2024-06-09 | 2024-06-15 | 2024-06-09 to 2024-06-15 | 8 | 76 | -68
TB 408 | detail | No | 2024-06-16 | 2024-06-22 | 2024-06-16 to 2024-06-22 | 8 | 77 | -69
TB 408 | detail | No | 2024-06-23 | 2024-06-29 | 2024-06-23 to 2024-06-29 | 8 | 78 | -70
TB 408 | detail | No | 2024-06-30 | 2024-07-06 | 2024-06-30 to 2024-07-06 | 9 | 78 | -69
TB 408 | detail | No | 2024-07-07 | 2024-07-13 | 2024-07-07 to 2024-07-13 | 9 | 79 | -70
TB 408 | detail | No | 2024-07-21 | 2024-07-27 | 2024-07-21 to 2024-07-27 | 9 | 80 | -71
TB 408 | detail | No | 2024-07-28 | 2024-08-03 | 2024-07-28 to 2024-08-03 | 10 | 80 | -70
TB 408 | detail | No | 2024-08-18 | 2024-08-24 | 2024-08-18 to 2024-08-24 | 10 | 81 | -71
TB 408 | detail | No | 2024-08-25 | 2024-08-31 | 2024-08-25 to 2024-08-31 | 10 | 83 | -73
TB 408 | detail | No | 2024-09-01 | 2024-09-07 | 2024-09-01 to 2024-09-07 | 12 | 84 | -72
TB 408 | detail | No | 2024-09-08 | 2024-09-14 | 2024-09-08 to 2024-09-14 | 12 | 88 | -76
TB 408 | detail | No | 2024-09-15 | 2024-09-21 | 2024-09-15 to 2024-09-21 | 12 | 91 | -79
TB 408 | detail | No | 2024-09-22 | 2024-09-28 | 2024-09-22 to 2024-09-28 | 12 | 97 | -85
TB 408 | detail | No | 2024-09-29 | 2024-10-05 | 2024-09-29 to 2024-10-05 | 13 | 103 | -90
TB 408 | detail | No | 2024-10-06 | 2024-10-12 | 2024-10-06 to 2024-10-12 | 13 | 111 | -98
TB 408 | detail | No | 2024-10-13 | 2024-10-19 | 2024-10-13 to 2024-10-19 | 13 | 118 | -105
TB 408 | detail | No | 2024-10-20 | 2024-10-26 | 2024-10-20 to 2024-10-26 | 13 | 125 | -112
TB 408 | detail | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 | 16 | 132 | -116
TB 408 | detail | No | 2024-11-03 | 2024-11-09 | 2024-11-03 to 2024-11-09 | 16 | 138 | -122
TB 408 | detail | No | 2024-11-10 | 2024-11-16 | 2024-11-10 to 2024-11-16 | 16 | 143 | -127
TB 408 | detail | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 | 16 | 151 | -135
TB 408 | detail | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 | 16 | 159 | -143
TB 408 | detail | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 | 18 | 164 | -146
TB 408 | detail | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 | 18 | 167 | -149
TB 408 | detail | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 | 18 | 169 | -151
TB 408 | detail | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 | 18 | 170 | -152
TB 408 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 19 | 172 | -153
TB 408 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 19 | 175 | -156
TB 408 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 19 | 180 | -161
TB 408 | detail | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 | 19 | 182 | -163
TB 408 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 20 | 186 | -166
TB 408 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 20 | 190 | -170
TB 408 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 20 | 195 | -175
TB 408 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 20 | 198 | -178
TB 408 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 21 | 201 | -180
TB 408 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 21 | 203 | -182
TB 408 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 21 | 205 | -184
TB 408 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 21 | 208 | -187
TB 408 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 21 | 211 | -190
TB 408 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 22 | 215 | -193
TB 408 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 22 | 218 | -196
TB 408 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 22 | 219 | -197
TB 408 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 23 | 221 | -198
TB 408 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 23 | 222 | -199
TB 408 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 24 | 222 | -198
TB 408 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 24 | 223 | -199
TB 408 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 24 | 224 | -200
TB 408 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 24 | 226 | -202
TB 408 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 25 | 230 | -205
TB 408 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 25 | 231 | -206
TB 408 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 25 | 236 | -211
TB 408 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 25 | 243 | -218
TB 408 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 26 | 252 | -226
TB 408 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 26 | 263 | -237
TB 408 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 26 | 268 | -242
TB 408 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 26 | 284 | -258
TB 408 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 26 | 299 | -273
TB 408 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 27 | 314 | -287
TB 408 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 27 | 327 | -300
TB 408 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 27 | 334 | -307
TB 408 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 27 | 344 | -317
TB 408 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 28 | 351 | -323
TB 408 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 28 | 356 | -328
TB 408 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 28 | 362 | -334
TB 408 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 28 | 367 | -339
TB 408 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 29 | 375 | -346
TB 408 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 29 | 382 | -353
TB 408 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 29 | 389 | -360
TB 408 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 29 | 398 | -369
TB 408 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 29 | 403 | -374
TB 408 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 29 | 412 | -383
TB 408 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 29 | 418 | -389
TB 408 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 29 | 429 | -400
TB 408 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 29 | 438 | -409
TB 408 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 29 | 448 | -419
TB 408 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 29 | 454 | -425
TB 408 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 29 | 457 | -428
TB 408 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 29 | 458 | -429
TB 408 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 29 | 459 | -430
TB 408 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 30 | 460 | -430
TB 408 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 30 | 461 | -431
TB 408 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 30 | 465 | -435
TB 408 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 31 | 467 | -436
TB 408 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 31 | 469 | -438
TB 408 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 31 | 472 | -441
TB 408 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 31 | 475 | -444
TB 408 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 31 | 477 | -446
TB 408 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 31 | 478 | -447
TB 408 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 31 | 479 | -448
TB 408 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 31 | 482 | -451
TB 408 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 31 | 483 | -452
TB 408 | detail | No | 2026-05-24 | 2026-05-30 | 2026-05-24 to 2026-05-30 | 31 | 484 | -453
TB 408 | detail | No | 2026-07-12 | 2026-07-18 | 2026-07-12 to 2026-07-18 | 31 | 485 | -454
TB 501 | detail | No | 2024-08-11 | 2024-08-17 | 2024-08-11 to 2024-08-17 | 2 | 0 | 2
TB 501 | detail | No | 2024-08-18 | 2024-08-24 | 2024-08-18 to 2024-08-24 | 3 | 0 | 3
TB 501 | detail | No | 2024-09-08 | 2024-09-14 | 2024-09-08 to 2024-09-14 | 5 | 0 | 5
TB 501 | detail | No | 2024-09-15 | 2024-09-21 | 2024-09-15 to 2024-09-21 | 7 | 0 | 7
TB 501 | detail | No | 2024-09-22 | 2024-09-28 | 2024-09-22 to 2024-09-28 | 10 | 0 | 10
TB 501 | detail | No | 2024-09-29 | 2024-10-05 | 2024-09-29 to 2024-10-05 | 12 | 0 | 12
TB 501 | detail | No | 2024-10-06 | 2024-10-12 | 2024-10-06 to 2024-10-12 | 16 | 0 | 16
TB 501 | detail | No | 2024-10-13 | 2024-10-19 | 2024-10-13 to 2024-10-19 | 19 | 0 | 19
TB 501 | detail | No | 2024-10-20 | 2024-10-26 | 2024-10-20 to 2024-10-26 | 30 | 0 | 30
TB 501 | detail | No | 2024-10-27 | 2024-11-02 | 2024-10-27 to 2024-11-02 | 35 | 0 | 35
TB 501 | detail | No | 2024-11-03 | 2024-11-09 | 2024-11-03 to 2024-11-09 | 43 | 0 | 43
TB 501 | detail | No | 2024-11-10 | 2024-11-16 | 2024-11-10 to 2024-11-16 | 48 | 0 | 48
TB 501 | detail | No | 2024-11-17 | 2024-11-23 | 2024-11-17 to 2024-11-23 | 54 | 0 | 54
TB 501 | detail | No | 2024-11-24 | 2024-11-30 | 2024-11-24 to 2024-11-30 | 61 | 0 | 61
TB 501 | detail | No | 2024-12-01 | 2024-12-07 | 2024-12-01 to 2024-12-07 | 64 | 0 | 64
TB 501 | detail | No | 2024-12-08 | 2024-12-14 | 2024-12-08 to 2024-12-14 | 68 | 0 | 68
TB 501 | detail | No | 2024-12-15 | 2024-12-21 | 2024-12-15 to 2024-12-21 | 76 | 0 | 76
TB 501 | detail | No | 2024-12-22 | 2024-12-28 | 2024-12-22 to 2024-12-28 | 84 | 3 | 81
TB 501 | detail | No | 2024-12-29 | 2025-01-04 | 2024-12-29 to 2025-01-04 | 89 | 6 | 83
TB 501 | detail | No | 2025-01-05 | 2025-01-11 | 2025-01-05 to 2025-01-11 | 95 | 10 | 85
TB 501 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 101 | 14 | 87
TB 501 | detail | No | 2025-01-19 | 2025-01-25 | 2025-01-19 to 2025-01-25 | 105 | 18 | 87
TB 501 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 109 | 23 | 86
TB 501 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 116 | 27 | 89
TB 501 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 121 | 36 | 85
TB 501 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 126 | 47 | 79
TB 501 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 130 | 61 | 69
TB 501 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 131 | 74 | 57
TB 501 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 132 | 80 | 52
TB 501 | detail | No | 2025-03-16 | 2025-03-22 | 2025-03-16 to 2025-03-22 | 136 | 88 | 48
TB 501 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 139 | 96 | 43
TB 501 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 140 | 104 | 36
TB 501 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 141 | 109 | 32
TB 501 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 144 | 113 | 31
TB 501 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 147 | 118 | 29
TB 501 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 150 | 122 | 28
TB 501 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 151 | 124 | 27
TB 501 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 155 | 127 | 28
TB 501 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 160 | 132 | 28
TB 501 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 168 | 138 | 30
TB 501 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 172 | 141 | 31
TB 501 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 173 | 145 | 28
TB 501 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 173 | 149 | 24
TB 501 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 173 | 155 | 18
TB 501 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 174 | 160 | 14
TB 501 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 175 | 163 | 12
TB 501 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 175 | 166 | 9
TB 501 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 175 | 168 | 7
TB 501 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 175 | 169 | 6
TB 501 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 175 | 170 | 5
TB 501 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 177 | 172 | 5
TB 501 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 178 | 172 | 6
TB 501 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 179 | 173 | 6
TB 501 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 182 | 173 | 9
TB 501 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 183 | 173 | 10
TB 501 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 185 | 173 | 12
TB 501 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 186 | 173 | 13
TB 501 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 188 | 173 | 15
TB 501 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 190 | 173 | 17
TB 501 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 191 | 175 | 16
TB 501 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 192 | 178 | 14
TB 501 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 195 | 181 | 14
TB 501 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 196 | 184 | 12
TB 501 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 198 | 189 | 9
TB 501 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 199 | 193 | 6
TB 501 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 200 | 194 | 6
TB 501 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 202 | 197 | 5
TB 501 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 207 | 199 | 8
TB 501 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 208 | 202 | 6
TB 501 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 209 | 204 | 5
TB 501 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 211 | 207 | 4
TB 501 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 212 | 208 | 4
TB 501 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 214 | 209 | 5
TB 501 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 218 | 212 | 6
TB 501 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 219 | 214 | 5
TB 501 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 220 | 216 | 4
TB 501 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 221 | 218 | 3
TB 501 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 222 | 219 | 3
TB 501 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 224 | 219 | 5
TB 501 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 226 | 223 | 3
TB 501 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 226 | 226 | 0
TB 501 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 227 | 226 | 1
TB 501 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 229 | 226 | 3
TB 501 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 230 | 227 | 3
TB 501 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 231 | 228 | 3
TB 501 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 231 | 230 | 1
TB 501 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 231 | 231 | 0
TB 501 | detail | No | 2026-06-14 | 2026-06-20 | 2026-06-14 to 2026-06-20 | 233 | 232 | 1
TB 501 | detail | No | 2026-06-21 | 2026-06-27 | 2026-06-21 to 2026-06-27 | 234 | 233 | 1
TB 501 | detail | No | 2026-07-19 | 2026-07-25 | 2026-07-19 to 2026-07-25 | 235 | 233 | 2
TB 507 | detail | No | 2025-01-12 | 2025-01-18 | 2025-01-12 to 2025-01-18 | 1 | 0 | 1
TB 507 | detail | No | 2025-01-26 | 2025-02-01 | 2025-01-26 to 2025-02-01 | 2 | 0 | 2
TB 507 | detail | No | 2025-02-02 | 2025-02-08 | 2025-02-02 to 2025-02-08 | 6 | 0 | 6
TB 507 | detail | No | 2025-02-09 | 2025-02-15 | 2025-02-09 to 2025-02-15 | 9 | 0 | 9
TB 507 | detail | No | 2025-02-16 | 2025-02-22 | 2025-02-16 to 2025-02-22 | 15 | 0 | 15
TB 507 | detail | No | 2025-02-23 | 2025-03-01 | 2025-02-23 to 2025-03-01 | 22 | 0 | 22
TB 507 | detail | No | 2025-03-02 | 2025-03-08 | 2025-03-02 to 2025-03-08 | 27 | 0 | 27
TB 507 | detail | No | 2025-03-09 | 2025-03-15 | 2025-03-09 to 2025-03-15 | 32 | 0 | 32
TB 507 | detail | No | 2025-03-23 | 2025-03-29 | 2025-03-23 to 2025-03-29 | 34 | 0 | 34
TB 507 | detail | No | 2025-03-30 | 2025-04-05 | 2025-03-30 to 2025-04-05 | 39 | 0 | 39
TB 507 | detail | No | 2025-04-06 | 2025-04-12 | 2025-04-06 to 2025-04-12 | 40 | 0 | 40
TB 507 | detail | No | 2025-04-13 | 2025-04-19 | 2025-04-13 to 2025-04-19 | 44 | 0 | 44
TB 507 | detail | No | 2025-04-20 | 2025-04-26 | 2025-04-20 to 2025-04-26 | 48 | 0 | 48
TB 507 | detail | No | 2025-04-27 | 2025-05-03 | 2025-04-27 to 2025-05-03 | 51 | 0 | 51
TB 507 | detail | No | 2025-05-04 | 2025-05-10 | 2025-05-04 to 2025-05-10 | 52 | 1 | 51
TB 507 | detail | No | 2025-05-11 | 2025-05-17 | 2025-05-11 to 2025-05-17 | 53 | 1 | 52
TB 507 | detail | No | 2025-05-18 | 2025-05-24 | 2025-05-18 to 2025-05-24 | 56 | 1 | 55
TB 507 | detail | No | 2025-05-25 | 2025-05-31 | 2025-05-25 to 2025-05-31 | 60 | 1 | 59
TB 507 | detail | No | 2025-06-01 | 2025-06-07 | 2025-06-01 to 2025-06-07 | 64 | 1 | 63
TB 507 | detail | No | 2025-06-08 | 2025-06-14 | 2025-06-08 to 2025-06-14 | 68 | 1 | 67
TB 507 | detail | No | 2025-06-15 | 2025-06-21 | 2025-06-15 to 2025-06-21 | 75 | 1 | 74
TB 507 | detail | No | 2025-06-22 | 2025-06-28 | 2025-06-22 to 2025-06-28 | 81 | 2 | 79
TB 507 | detail | No | 2025-06-29 | 2025-07-05 | 2025-06-29 to 2025-07-05 | 87 | 5 | 82
TB 507 | detail | No | 2025-07-06 | 2025-07-12 | 2025-07-06 to 2025-07-12 | 96 | 6 | 90
TB 507 | detail | No | 2025-07-13 | 2025-07-19 | 2025-07-13 to 2025-07-19 | 109 | 8 | 101
TB 507 | detail | No | 2025-07-20 | 2025-07-26 | 2025-07-20 to 2025-07-26 | 119 | 10 | 109
TB 507 | detail | No | 2025-07-27 | 2025-08-02 | 2025-07-27 to 2025-08-02 | 137 | 13 | 124
TB 507 | detail | No | 2025-08-03 | 2025-08-09 | 2025-08-03 to 2025-08-09 | 149 | 16 | 133
TB 507 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 156 | 18 | 138
TB 507 | detail | No | 2025-08-17 | 2025-08-23 | 2025-08-17 to 2025-08-23 | 168 | 20 | 148
TB 507 | detail | No | 2025-08-24 | 2025-08-30 | 2025-08-24 to 2025-08-30 | 179 | 23 | 156
TB 507 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 190 | 27 | 163
TB 507 | detail | No | 2025-09-07 | 2025-09-13 | 2025-09-07 to 2025-09-13 | 194 | 32 | 162
TB 507 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 200 | 44 | 156
TB 507 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 203 | 56 | 147
TB 507 | detail | No | 2025-09-28 | 2025-10-04 | 2025-09-28 to 2025-10-04 | 207 | 65 | 142
TB 507 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 208 | 75 | 133
TB 507 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 211 | 85 | 126
TB 507 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 212 | 95 | 117
TB 507 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 215 | 106 | 109
TB 507 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 219 | 115 | 104
TB 507 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 223 | 124 | 99
TB 507 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 230 | 130 | 100
TB 507 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 232 | 136 | 96
TB 507 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 237 | 141 | 96
TB 507 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 239 | 147 | 92
TB 507 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 242 | 152 | 90
TB 507 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 243 | 160 | 83
TB 507 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 247 | 163 | 84
TB 507 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 250 | 168 | 82
TB 507 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 253 | 173 | 80
TB 507 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 256 | 176 | 80
TB 507 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 262 | 177 | 85
TB 507 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 264 | 178 | 86
TB 507 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 267 | 181 | 86
TB 507 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 270 | 182 | 88
TB 507 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 274 | 184 | 90
TB 507 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 275 | 185 | 90
TB 507 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 279 | 186 | 93
TB 507 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 283 | 188 | 95
TB 507 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 290 | 188 | 102
TB 507 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 293 | 189 | 104
TB 507 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 299 | 190 | 109
TB 507 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 305 | 192 | 113
TB 507 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 309 | 196 | 113
TB 507 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 313 | 200 | 113
TB 507 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 324 | 205 | 119
TB 507 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 329 | 210 | 119
TB 507 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 335 | 213 | 122
TB 507 | detail | No | 2026-05-24 | 2026-05-30 | 2026-05-24 to 2026-05-30 | 340 | 219 | 121
TB 507 | detail | No | 2026-05-31 | 2026-06-06 | 2026-05-31 to 2026-06-06 | 347 | 224 | 123
TB 507 | detail | No | 2026-06-07 | 2026-06-13 | 2026-06-07 to 2026-06-13 | 349 | 226 | 123
TB 507 | detail | No | 2026-06-14 | 2026-06-20 | 2026-06-14 to 2026-06-20 | 354 | 230 | 124
TB 507 | detail | No | 2026-06-21 | 2026-06-27 | 2026-06-21 to 2026-06-27 | 358 | 235 | 123
TB 507 | detail | No | 2026-06-28 | 2026-07-04 | 2026-06-28 to 2026-07-04 | 365 | 238 | 127
TB 507 | detail | No | 2026-07-05 | 2026-07-11 | 2026-07-05 to 2026-07-11 | 369 | 245 | 124
TB 507 | detail | No | 2026-07-12 | 2026-07-18 | 2026-07-12 to 2026-07-18 | 373 | 252 | 121
TB 507 | detail | No | 2026-07-19 | 2026-07-25 | 2026-07-19 to 2026-07-25 | 375 | 260 | 115
TB 507 | detail | No | 2026-07-26 | 2026-08-01 | 2026-07-26 to 2026-08-01 | 380 | 268 | 112
TB 507 | detail | No | 2026-08-02 | 2026-08-08 | 2026-08-02 to 2026-08-08 | 383 | 277 | 106
TB 507 | detail | No | 2026-08-09 | 2026-08-15 | 2026-08-09 to 2026-08-15 | 385 | 282 | 103
TB 605 | detail | No | 2025-08-10 | 2025-08-16 | 2025-08-10 to 2025-08-16 | 1 | 0 | 1
TB 605 | detail | No | 2025-08-31 | 2025-09-06 | 2025-08-31 to 2025-09-06 | 2 | 0 | 2
TB 605 | detail | No | 2025-09-14 | 2025-09-20 | 2025-09-14 to 2025-09-20 | 3 | 0 | 3
TB 605 | detail | No | 2025-09-21 | 2025-09-27 | 2025-09-21 to 2025-09-27 | 4 | 0 | 4
TB 605 | detail | No | 2025-10-05 | 2025-10-11 | 2025-10-05 to 2025-10-11 | 5 | 0 | 5
TB 605 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 7 | 0 | 7
TB 605 | detail | No | 2025-10-19 | 2025-10-25 | 2025-10-19 to 2025-10-25 | 9 | 0 | 9
TB 605 | detail | No | 2025-10-26 | 2025-11-01 | 2025-10-26 to 2025-11-01 | 19 | 0 | 19
TB 605 | detail | No | 2025-11-02 | 2025-11-08 | 2025-11-02 to 2025-11-08 | 24 | 0 | 24
TB 605 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 35 | 0 | 35
TB 605 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 44 | 1 | 43
TB 605 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 55 | 1 | 54
TB 605 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 69 | 2 | 67
TB 605 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 81 | 3 | 78
TB 605 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 93 | 3 | 90
TB 605 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 108 | 3 | 105
TB 605 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 118 | 4 | 114
TB 605 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 129 | 6 | 123
TB 605 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 138 | 7 | 131
TB 605 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 152 | 9 | 143
TB 605 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 160 | 10 | 150
TB 605 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 165 | 15 | 150
TB 605 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 176 | 26 | 150
TB 605 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 189 | 38 | 151
TB 605 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 202 | 55 | 147
TB 605 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 206 | 61 | 145
TB 605 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 212 | 75 | 137
TB 605 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 218 | 84 | 134
TB 605 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 223 | 95 | 128
TB 605 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 230 | 109 | 121
TB 605 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 235 | 119 | 116
TB 605 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 240 | 133 | 107
TB 605 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 245 | 145 | 100
TB 605 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 257 | 158 | 99
TB 605 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 266 | 172 | 94
TB 605 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 276 | 185 | 91
TB 605 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 294 | 194 | 100
TB 605 | detail | No | 2026-05-24 | 2026-05-30 | 2026-05-24 to 2026-05-30 | 309 | 201 | 108
TB 605 | detail | No | 2026-05-31 | 2026-06-06 | 2026-05-31 to 2026-06-06 | 321 | 211 | 110
TB 605 | detail | No | 2026-06-07 | 2026-06-13 | 2026-06-07 to 2026-06-13 | 330 | 224 | 106
TB 605 | detail | No | 2026-06-14 | 2026-06-20 | 2026-06-14 to 2026-06-20 | 337 | 232 | 105
TB 605 | detail | No | 2026-06-21 | 2026-06-27 | 2026-06-21 to 2026-06-27 | 349 | 244 | 105
TB 605 | detail | No | 2026-06-28 | 2026-07-04 | 2026-06-28 to 2026-07-04 | 353 | 249 | 104
TB 605 | detail | No | 2026-07-05 | 2026-07-11 | 2026-07-05 to 2026-07-11 | 354 | 254 | 100
TB 605 | detail | No | 2026-07-12 | 2026-07-18 | 2026-07-12 to 2026-07-18 | 356 | 262 | 94
TB 605 | detail | No | 2026-07-19 | 2026-07-25 | 2026-07-19 to 2026-07-25 | 357 | 266 | 91
TB 605 | detail | No | 2026-07-26 | 2026-08-01 | 2026-07-26 to 2026-08-01 | 359 | 273 | 86
TB 605 | detail | No | 2026-08-02 | 2026-08-08 | 2026-08-02 to 2026-08-08 | 359 | 278 | 81
TB 605 | detail | No | 2026-08-09 | 2026-08-15 | 2026-08-09 to 2026-08-15 | 361 | 282 | 79
TB 608 | detail | No | 2025-10-12 | 2025-10-18 | 2025-10-12 to 2025-10-18 | 2 | 0 | 2
TB 608 | detail | No | 2025-11-09 | 2025-11-15 | 2025-11-09 to 2025-11-15 | 7 | 0 | 7
TB 608 | detail | No | 2025-11-16 | 2025-11-22 | 2025-11-16 to 2025-11-22 | 12 | 0 | 12
TB 608 | detail | No | 2025-11-23 | 2025-11-29 | 2025-11-23 to 2025-11-29 | 16 | 0 | 16
TB 608 | detail | No | 2025-11-30 | 2025-12-06 | 2025-11-30 to 2025-12-06 | 24 | 0 | 24
TB 608 | detail | No | 2025-12-07 | 2025-12-13 | 2025-12-07 to 2025-12-13 | 29 | 0 | 29
TB 608 | detail | No | 2025-12-14 | 2025-12-20 | 2025-12-14 to 2025-12-20 | 36 | 0 | 36
TB 608 | detail | No | 2025-12-21 | 2025-12-27 | 2025-12-21 to 2025-12-27 | 48 | 0 | 48
TB 608 | detail | No | 2025-12-28 | 2026-01-03 | 2025-12-28 to 2026-01-03 | 58 | 0 | 58
TB 608 | detail | No | 2026-01-04 | 2026-01-10 | 2026-01-04 to 2026-01-10 | 62 | 1 | 61
TB 608 | detail | No | 2026-01-11 | 2026-01-17 | 2026-01-11 to 2026-01-17 | 69 | 1 | 68
TB 608 | detail | No | 2026-01-18 | 2026-01-24 | 2026-01-18 to 2026-01-24 | 73 | 2 | 71
TB 608 | detail | No | 2026-01-25 | 2026-01-31 | 2026-01-25 to 2026-01-31 | 86 | 3 | 83
TB 608 | detail | No | 2026-02-01 | 2026-02-07 | 2026-02-01 to 2026-02-07 | 91 | 3 | 88
TB 608 | detail | No | 2026-02-08 | 2026-02-14 | 2026-02-08 to 2026-02-14 | 99 | 4 | 95
TB 608 | detail | No | 2026-02-15 | 2026-02-21 | 2026-02-15 to 2026-02-21 | 107 | 5 | 102
TB 608 | detail | No | 2026-02-22 | 2026-02-28 | 2026-02-22 to 2026-02-28 | 116 | 7 | 109
TB 608 | detail | No | 2026-03-01 | 2026-03-07 | 2026-03-01 to 2026-03-07 | 117 | 9 | 108
TB 608 | detail | No | 2026-03-08 | 2026-03-14 | 2026-03-08 to 2026-03-14 | 125 | 10 | 115
TB 608 | detail | No | 2026-03-15 | 2026-03-21 | 2026-03-15 to 2026-03-21 | 127 | 11 | 116
TB 608 | detail | No | 2026-03-22 | 2026-03-28 | 2026-03-22 to 2026-03-28 | 129 | 12 | 117
TB 608 | detail | No | 2026-03-29 | 2026-04-04 | 2026-03-29 to 2026-04-04 | 133 | 12 | 121
TB 608 | detail | No | 2026-04-05 | 2026-04-11 | 2026-04-05 to 2026-04-11 | 133 | 14 | 119
TB 608 | detail | No | 2026-04-12 | 2026-04-18 | 2026-04-12 to 2026-04-18 | 137 | 16 | 121
TB 608 | detail | No | 2026-04-19 | 2026-04-25 | 2026-04-19 to 2026-04-25 | 140 | 19 | 121
TB 608 | detail | No | 2026-04-26 | 2026-05-02 | 2026-04-26 to 2026-05-02 | 142 | 21 | 121
TB 608 | detail | No | 2026-05-03 | 2026-05-09 | 2026-05-03 to 2026-05-09 | 146 | 23 | 123
TB 608 | detail | No | 2026-05-10 | 2026-05-16 | 2026-05-10 to 2026-05-16 | 148 | 26 | 122
TB 608 | detail | No | 2026-05-17 | 2026-05-23 | 2026-05-17 to 2026-05-23 | 149 | 28 | 121
TB 608 | detail | No | 2026-05-24 | 2026-05-30 | 2026-05-24 to 2026-05-30 | 153 | 31 | 122
TB 608 | detail | No | 2026-05-31 | 2026-06-06 | 2026-05-31 to 2026-06-06 | 153 | 32 | 121
TB 608 | detail | No | 2026-06-07 | 2026-06-13 | 2026-06-07 to 2026-06-13 | 155 | 34 | 121
TB 608 | detail | No | 2026-06-14 | 2026-06-20 | 2026-06-14 to 2026-06-20 | 156 | 40 | 116
TB 608 | detail | No | 2026-06-21 | 2026-06-27 | 2026-06-21 to 2026-06-27 | 157 | 40 | 117
TB 608 | detail | No | 2026-06-28 | 2026-07-04 | 2026-06-28 to 2026-07-04 | 159 | 44 | 115
TB 608 | detail | No | 2026-07-05 | 2026-07-11 | 2026-07-05 to 2026-07-11 | 160 | 48 | 112
TB 608 | detail | No | 2026-07-19 | 2026-07-25 | 2026-07-19 to 2026-07-25 | 161 | 54 | 107
TB 608 | detail | No | 2026-07-26 | 2026-08-01 | 2026-07-26 to 2026-08-01 | 165 | 56 | 109
TB 608 | detail | No | 2026-08-02 | 2026-08-08 | 2026-08-02 to 2026-08-08 | 166 | 57 | 109
TB 608 | detail | No | 2026-08-09 | 2026-08-15 | 2026-08-09 to 2026-08-15 | 166 | 58 | 108

## Foundation Gap Coverage
Foundation Gap Coverage
Project | Foundation Source Used | Coverage Status | Coverage Reason | Snapshot Limited | First Month Available | Last Month Available | First Week Available | Last Week Available | Detail Rows | Detail Completions | Snapshot Rows | Erection First Month | Erection Last Month | Notes
TA 413 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2024-06 | 2026-07 | 2024-06-02 to 2024-06-08 | 2026-07-26 to 2026-08-01 | 316 | 316 | 33 | 2024-09 | 2026-07
TA 414 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2024-05 | 2026-08 | 2024-05-19 to 2024-05-25 | 2026-08-09 to 2026-08-15 | 339 | 335 | 31 | 2025-04 | 2026-08
TA 416 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2024-05 | 2026-07 | 2024-05-05 to 2024-05-11 | 2026-07-12 to 2026-07-18 | 711 | 634 | 12 | 2024-09 | 2026-03
TA 418 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2024-01 | 2026-07 | 2023-12-31 to 2024-01-06 | 2026-07-19 to 2026-07-25 | 303 | 292 | 15 | 2024-10 | 2026-04
TA 419 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2024-05 | 2026-08 | 2024-05-19 to 2024-05-25 | 2026-08-09 to 2026-08-15 | 331 | 287 | 41 | 2024-11 | 2026-08
TA 421 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2024-05 | 2026-06 | 2024-05-19 to 2024-05-25 | 2026-06-21 to 2026-06-27 | 1010 | 634 | 14 | 2024-07 | 2026-01
TA 505 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2024-03 | 2026-07 | 2024-03-24 to 2024-03-30 | 2026-07-26 to 2026-08-01 | 379 | 378 | 29 | 2025-01 | 2026-07
TA 509 | snapshot_fallback | SNAPSHOT_FALLBACK | No parseable detail completion dates; used ProgressStatus cumulative foundation snapshots. | Yes | 2026-05 | 2026-08 | 2026-05-31 to 2026-06-06 | 2026-08-09 to 2026-08-15 | 287 | 0 | 24 | 2025-09 | 2026-08 | Snapshot values are carry-forwarded between reporting dates.
TA 510 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2025-02 | 2026-08 | 2025-02-16 to 2025-02-22 | 2026-08-02 to 2026-08-08 | 99 | 95 | 40 | 2026-01 | 2026-08
TA 512 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2025-02 | 2026-08 | 2025-02-23 to 2025-03-01 | 2026-08-09 to 2026-08-15 | 317 | 317 | 46 | 2025-08 | 2026-08
TA 513 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2025-03 | 2026-08 | 2025-03-23 to 2025-03-29 | 2026-08-09 to 2026-08-15 | 113 | 109 | 10 | 2025-09 | 2026-06
TA 515 | missing | MISSING | No parseable foundation detail/snapshot source found. | No |  |  |  |  | 13 | 0 | 0 | 2026-03 | 2026-03
TA 601 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2025-03 | 2026-08 | 2025-03-23 to 2025-03-29 | 2026-08-09 to 2026-08-15 | 446 | 315 | 43 | 2025-03 | 2026-08
TA 602 | snapshot_fallback | SNAPSHOT_FALLBACK | No parseable detail completion dates; used ProgressStatus cumulative foundation snapshots. | Yes | 2026-06 | 2026-08 | 2026-06-07 to 2026-06-13 | 2026-08-09 to 2026-08-15 | 16 | 0 | 19 | 2026-02 | 2026-08 | Snapshot values are carry-forwarded between reporting dates.
TB 408 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2023-10 | 2026-07 | 2023-10-01 to 2023-10-07 | 2026-07-12 to 2026-07-18 | 485 | 485 | 2 | 2024-02 | 2026-07
TB 501 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2024-08 | 2026-07 | 2024-08-11 to 2024-08-17 | 2026-07-19 to 2026-07-25 | 240 | 235 | 21 | 2024-12 | 2026-06
TB 507 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2025-01 | 2026-08 | 2025-01-12 to 2025-01-18 | 2026-08-09 to 2026-08-15 | 404 | 385 | 31 | 2025-05 | 2026-08
TB 605 | detail | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | No | 2025-08 | 2026-08 | 2025-08-10 to 2025-08-16 | 2026-08-09 to 2026-08-15 | 371 | 361 | 37 | 2025-11 | 2026-08
TB 608 | detail | DETAIL_STATUS_MISMATCH | Detail completion dates were parsed, but counts are materially below status cumulative foundation progress; keeping detail source and flagging mapping/status mismatch. | No | 2025-10 | 2026-08 | 2025-10-12 to 2025-10-18 | 2026-08-09 to 2026-08-15 | 204 | 166 | 18 | 2026-01 | 2026-08

## Foundation Delay Phases
Foundation Delay Phases
Project | Phase | Foundation Bucket Start % | Foundation Bucket End % | Foundation Count | Matched Count | Match % | Median Delay Days | Average Delay Days | P90 Delay Days | Negative Excluded | Unmatched | Source Type | Parser Modes | Coverage Status
TA 413 | Phase 1 | 0 | 20 | 63 | 63 | 100 | 341 | 300.2063 | 491.6 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | Phase 2 | 20 | 40 | 63 | 57 | 90.48 | 299 | 243.9474 | 402.2 | 0 | 6 | detail |  | OK_DETAIL
TA 413 | Phase 3 | 40 | 60 | 63 | 62 | 98.41 | 101.5 | 162.9677 | 310.5 | 0 | 1 | detail |  | OK_DETAIL
TA 413 | Phase 4 | 60 | 80 | 63 | 63 | 100 | 213.5 | 203.1613 | 287.8 | 1 | 0 | detail |  | OK_DETAIL
TA 413 | Phase 5 | 80 | 100 | 62 | 60 | 96.77 | 162 | 162.7833 | 219.9 | 0 | 2 | detail |  | OK_DETAIL
TA 414 | Phase 1 | 0 | 20 | 67 | 65 | 97.01 | 346.5 | 351.8281 | 459.7 | 1 | 2 | detail |  | OK_DETAIL
TA 414 | Phase 2 | 20 | 40 | 67 | 65 | 97.01 | 154 | 170.6 | 310.2 | 0 | 2 | detail |  | OK_DETAIL
TA 414 | Phase 3 | 40 | 60 | 67 | 61 | 91.04 | 49 | 60.6393 | 122 | 0 | 6 | detail |  | OK_DETAIL
TA 414 | Phase 4 | 60 | 80 | 67 | 54 | 80.6 | 51 | 60.5741 | 123.4 | 0 | 13 | detail |  | OK_DETAIL
TA 414 | Phase 5 | 80 | 100 | 67 | 35 | 52.24 | 29 | 33.2571 | 63.2 | 0 | 32 | detail |  | OK_DETAIL
TA 416 | Phase 1 | 0 | 20 | 67 | 67 | 100 | 175 | 176.9851 | 275 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | Phase 2 | 20 | 40 | 66 | 66 | 100 | 128.5 | 138.7273 | 220 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | Phase 3 | 40 | 60 | 66 | 66 | 100 | 108 | 123.6364 | 268.5 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | Phase 4 | 60 | 80 | 66 | 66 | 100 | 143 | 164.9091 | 313.5 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | Phase 5 | 80 | 100 | 66 | 38 | 57.58 | 155 | 164.2973 | 246 | 1 | 28 | detail |  | OK_DETAIL
TA 418 | Phase 1 | 0 | 20 | 34 | 33 | 97.06 | 173 | 184.3548 | 307 | 2 | 1 | detail |  | OK_DETAIL
TA 418 | Phase 2 | 20 | 40 | 33 | 32 | 96.97 | 90 | 112.0333 | 230.3 | 2 | 1 | detail |  | OK_DETAIL
TA 418 | Phase 3 | 40 | 60 | 34 | 33 | 97.06 | 96 | 102.7879 | 175.8 | 0 | 1 | detail |  | OK_DETAIL
TA 418 | Phase 4 | 60 | 80 | 33 | 26 | 78.79 | 116 | 99.48 | 161.4 | 1 | 7 | detail |  | OK_DETAIL
TA 418 | Phase 5 | 80 | 100 | 33 | 1 | 3.03 | 7 | 7 | 7 | 0 | 32 | detail |  | OK_DETAIL
TA 419 | Phase 1 | 0 | 20 | 57 | 57 | 100 | 196.5 | 206.4643 | 320 | 1 | 0 | detail |  | OK_DETAIL
TA 419 | Phase 2 | 20 | 40 | 57 | 57 | 100 | 204 | 201.7544 | 318.4 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | Phase 3 | 40 | 60 | 57 | 54 | 94.74 | 189.5 | 172.2037 | 264.7 | 0 | 3 | detail |  | OK_DETAIL
TA 419 | Phase 4 | 60 | 80 | 57 | 46 | 80.7 | 23 | 51.3478 | 130.5 | 0 | 11 | detail |  | OK_DETAIL
TA 419 | Phase 5 | 80 | 100 | 57 | 31 | 54.39 | 18 | 20.0333 | 35.2 | 1 | 26 | detail |  | OK_DETAIL
TA 421 | Phase 1 | 0 | 20 | 64 | 64 | 100 | 87.5 | 91.4688 | 167.1 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | Phase 2 | 20 | 40 | 64 | 64 | 100 | 98 | 128.4444 | 299.8 | 1 | 0 | detail |  | OK_DETAIL
TA 421 | Phase 3 | 40 | 60 | 64 | 64 | 100 | 102.5 | 120.9531 | 276.9 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | Phase 4 | 60 | 80 | 64 | 63 | 98.44 | 123 | 121.6825 | 213.4 | 0 | 1 | detail |  | OK_DETAIL
TA 421 | Phase 5 | 80 | 100 | 63 | 44 | 69.84 | 147 | 132.1136 | 179.7 | 0 | 19 | detail |  | OK_DETAIL
TA 505 | Phase 1 | 0 | 20 | 76 | 76 | 100 | 142.5 | 181.3816 | 308.5 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | Phase 2 | 20 | 40 | 76 | 76 | 100 | 227 | 225.5921 | 366 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | Phase 3 | 40 | 60 | 75 | 75 | 100 | 208 | 216.0933 | 349 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | Phase 4 | 60 | 80 | 76 | 76 | 100 | 122 | 142.1184 | 289.5 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | Phase 5 | 80 | 100 | 75 | 61 | 81.33 | 17.5 | 27.3333 | 58.6 | 1 | 14 | detail |  | OK_DETAIL
TA 510 | Phase 1 | 0 | 20 | 19 | 9 | 47.37 | 396 | 375.6667 | 429.8 | 0 | 10 | detail |  | OK_DETAIL
TA 510 | Phase 2 | 20 | 40 | 19 | 17 | 89.47 | 96 | 175.2941 | 345.2 | 0 | 2 | detail |  | OK_DETAIL
TA 510 | Phase 3 | 40 | 60 | 19 | 17 | 89.47 | 70 | 77.1765 | 117.4 | 0 | 2 | detail |  | OK_DETAIL
TA 510 | Phase 4 | 60 | 80 | 19 | 5 | 26.32 | 26 | 43 | 82.8 | 0 | 14 | detail |  | OK_DETAIL
TA 510 | Phase 5 | 80 | 100 | 19 | 0 | 0 |  |  |  | 0 | 19 | detail |  | OK_DETAIL
TA 512 | Phase 1 | 0 | 20 | 63 | 63 | 100 | 221 | 220.4921 | 311.8 | 0 | 0 | detail |  | OK_DETAIL
TA 512 | Phase 2 | 20 | 40 | 62 | 59 | 95.16 | 218 | 211.0339 | 278.2 | 0 | 3 | detail |  | OK_DETAIL
TA 512 | Phase 3 | 40 | 60 | 63 | 59 | 93.65 | 162 | 185.1356 | 320.2 | 0 | 4 | detail |  | OK_DETAIL
TA 512 | Phase 4 | 60 | 80 | 62 | 55 | 88.71 | 124 | 141.8909 | 245.2 | 0 | 7 | detail |  | OK_DETAIL
TA 512 | Phase 5 | 80 | 100 | 62 | 38 | 61.29 | 79.5 | 104.5 | 187 | 0 | 24 | detail |  | OK_DETAIL
TA 513 | Phase 1 | 0 | 20 | 22 | 10 | 45.45 | 182 | 186.2 | 208.3 | 0 | 12 | detail |  | OK_DETAIL
TA 513 | Phase 2 | 20 | 40 | 22 | 5 | 22.73 | 202 | 218.4 | 298.6 | 0 | 17 | detail |  | OK_DETAIL
TA 513 | Phase 3 | 40 | 60 | 22 | 12 | 54.55 | 130.5 | 121.75 | 172.9 | 0 | 10 | detail |  | OK_DETAIL
TA 513 | Phase 4 | 60 | 80 | 22 | 6 | 27.27 | 91 | 86.5 | 127.5 | 0 | 16 | detail |  | OK_DETAIL
TA 513 | Phase 5 | 80 | 100 | 21 | 0 | 0 |  |  |  | 0 | 21 | detail |  | OK_DETAIL
TA 601 | Phase 1 | 0 | 20 | 38 | 28 | 73.68 | 68 | 79.5357 | 144.4 | 0 | 10 | detail |  | OK_DETAIL
TA 601 | Phase 2 | 20 | 40 | 38 | 32 | 84.21 | 17 | 29.871 | 70 | 1 | 6 | detail |  | OK_DETAIL
TA 601 | Phase 3 | 40 | 60 | 38 | 32 | 84.21 | 52 | 56.3548 | 104 | 1 | 6 | detail |  | OK_DETAIL
TA 601 | Phase 4 | 60 | 80 | 38 | 23 | 60.53 | 17 | 21.2174 | 40.4 | 0 | 15 | detail |  | OK_DETAIL
TA 601 | Phase 5 | 80 | 100 | 37 | 9 | 24.32 | 12 | 12 | 16.6 | 0 | 28 | detail |  | OK_DETAIL
TB 408 | Phase 1 | 0 | 20 | 2 | 0 | 0 |  |  |  | 0 | 2 | detail |  | OK_DETAIL
TB 408 | Phase 2 | 20 | 40 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TB 408 | Phase 3 | 40 | 60 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TB 408 | Phase 4 | 60 | 80 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TB 408 | Phase 5 | 80 | 100 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TB 501 | Phase 1 | 0 | 20 | 47 | 47 | 100 | 118 | 124.8298 | 183 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | Phase 2 | 20 | 40 | 47 | 47 | 100 | 65 | 71.9787 | 110.8 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | Phase 3 | 40 | 60 | 47 | 47 | 100 | 61 | 72.4681 | 128.8 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | Phase 4 | 60 | 80 | 47 | 47 | 100 | 40 | 45.4255 | 84 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | Phase 5 | 80 | 100 | 47 | 45 | 95.74 | 14 | 16 | 35 | 4 | 2 | detail |  | OK_DETAIL
TB 507 | Phase 1 | 0 | 20 | 76 | 57 | 75 | 164 | 199.2632 | 387.4 | 0 | 19 | detail |  | OK_DETAIL
TB 507 | Phase 2 | 20 | 40 | 75 | 70 | 93.33 | 77 | 87.9286 | 147.3 | 0 | 5 | detail |  | OK_DETAIL
TB 507 | Phase 3 | 40 | 60 | 76 | 61 | 80.26 | 54.5 | 76.65 | 151.4 | 1 | 15 | detail |  | OK_DETAIL
TB 507 | Phase 4 | 60 | 80 | 75 | 54 | 72 | 80.5 | 81.5926 | 129.7 | 0 | 21 | detail |  | OK_DETAIL
TB 507 | Phase 5 | 80 | 100 | 75 | 34 | 45.33 | 25 | 33.4848 | 74.8 | 1 | 41 | detail |  | OK_DETAIL
TB 605 | Phase 1 | 0 | 20 | 73 | 64 | 87.67 | 95 | 111.7969 | 186 | 0 | 9 | detail |  | OK_DETAIL
TB 605 | Phase 2 | 20 | 40 | 72 | 64 | 88.89 | 90 | 91.2031 | 145.1 | 0 | 8 | detail |  | OK_DETAIL
TB 605 | Phase 3 | 40 | 60 | 72 | 62 | 86.11 | 53.5 | 58.7903 | 98.9 | 0 | 10 | detail |  | OK_DETAIL
TB 605 | Phase 4 | 60 | 80 | 72 | 37 | 51.39 | 25 | 30.3784 | 57 | 0 | 35 | detail |  | OK_DETAIL
TB 605 | Phase 5 | 80 | 100 | 72 | 26 | 36.11 | 10 | 14.9231 | 30.5 | 0 | 46 | detail |  | OK_DETAIL
TB 608 | Phase 1 | 0 | 20 | 32 | 21 | 65.62 | 145 | 137.3333 | 190 | 0 | 11 | detail |  | DETAIL_STATUS_MISMATCH
TB 608 | Phase 2 | 20 | 40 | 32 | 13 | 40.62 | 95 | 98.2308 | 162.8 | 0 | 19 | detail |  | DETAIL_STATUS_MISMATCH
TB 608 | Phase 3 | 40 | 60 | 32 | 9 | 28.12 | 132 | 117.5556 | 145.2 | 0 | 23 | detail |  | DETAIL_STATUS_MISMATCH
TB 608 | Phase 4 | 60 | 80 | 32 | 10 | 31.25 | 104 | 99 | 144 | 0 | 22 | detail |  | DETAIL_STATUS_MISMATCH
TB 608 | Phase 5 | 80 | 100 | 31 | 5 | 16.13 | 47 | 53.8 | 70.8 | 0 | 26 | detail |  | DETAIL_STATUS_MISMATCH

## Foundation Delay Monthly
Foundation Delay Monthly
Project | Month | Foundation Count | Matched Count | Match % | Median Delay Days | Average Delay Days | P90 Delay Days | Negative Excluded | Unmatched | Source Type | Parser Modes | Coverage Status
TA 413 | 2024-06 | 14 | 14 | 100 | 275 | 339.2857 | 493.4 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2024-07 | 20 | 20 | 100 | 380 | 316.2 | 495.3 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2024-08 | 23 | 23 | 100 | 341 | 259.2174 | 418.2 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2024-09 | 40 | 39 | 97.5 | 335 | 268.0256 | 399 | 0 | 1 | detail |  | OK_DETAIL
TA 413 | 2024-10 | 35 | 29 | 82.86 | 131 | 200.4483 | 356.6 | 0 | 6 | detail |  | OK_DETAIL
TA 413 | 2024-11 | 24 | 24 | 100 | 90.5 | 165.7083 | 306 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2024-12 | 32 | 32 | 100 | 101.5 | 165.3438 | 310.5 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2025-01 | 34 | 34 | 100 | 218 | 201.697 | 287.6 | 1 | 0 | detail |  | OK_DETAIL
TA 413 | 2025-02 | 31 | 31 | 100 | 215 | 211.3226 | 294 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2025-03 | 19 | 19 | 100 | 182 | 179.6842 | 225 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2025-04 | 23 | 23 | 100 | 154 | 160.2609 | 209.6 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2025-05 | 10 | 10 | 100 | 160.5 | 165.2 | 179.3 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2025-06 | 4 | 4 | 100 | 105 | 102.25 | 146.9 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2025-07 | 2 | 2 | 100 | 109 | 109 | 158.6 | 0 | 0 | detail |  | OK_DETAIL
TA 413 | 2026-01 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 413 | 2026-02 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 413 | 2026-03 | 1 | 1 | 100 | 129 | 129 | 129 | 0 | 0 | detail |  | OK_DETAIL
TA 414 | 2024-05 | 2 | 2 | 100 | 529.5 | 529.5 | 585.1 | 0 | 0 | detail |  | OK_DETAIL
TA 414 | 2024-10 | 1 | 1 | 100 | 212 | 212 | 212 | 0 | 0 | detail |  | OK_DETAIL
TA 414 | 2024-11 | 4 | 4 | 100 | 209 | 279.3333 | 391.4 | 1 | 0 | detail |  | OK_DETAIL
TA 414 | 2024-12 | 12 | 12 | 100 | 391 | 366.4167 | 439.8 | 0 | 0 | detail |  | OK_DETAIL
TA 414 | 2025-01 | 17 | 16 | 94.12 | 368.5 | 383.4375 | 486.5 | 0 | 1 | detail |  | OK_DETAIL
TA 414 | 2025-02 | 20 | 20 | 100 | 330 | 342.2 | 443.7 | 0 | 0 | detail |  | OK_DETAIL
TA 414 | 2025-03 | 10 | 9 | 90 | 281 | 292.3333 | 350.4 | 0 | 1 | detail |  | OK_DETAIL
TA 414 | 2025-04 | 18 | 18 | 100 | 294.5 | 304.7778 | 361.8 | 0 | 0 | detail |  | OK_DETAIL
TA 414 | 2025-05 | 5 | 4 | 80 | 250 | 257.25 | 305.7 | 0 | 1 | detail |  | OK_DETAIL
TA 414 | 2025-06 | 2 | 2 | 100 | 218.5 | 218.5 | 247.7 | 0 | 0 | detail |  | OK_DETAIL
TA 414 | 2025-08 | 1 | 1 | 100 | 133 | 133 | 133 | 0 | 0 | detail |  | OK_DETAIL
TA 414 | 2025-09 | 3 | 3 | 100 | 126 | 115.6667 | 129.2 | 0 | 0 | detail |  | OK_DETAIL
TA 414 | 2025-10 | 8 | 8 | 100 | 159.5 | 146.625 | 189.6 | 0 | 0 | detail |  | OK_DETAIL
TA 414 | 2025-11 | 24 | 23 | 95.83 | 90 | 104.4348 | 183.4 | 0 | 1 | detail |  | OK_DETAIL
TA 414 | 2025-12 | 55 | 51 | 92.73 | 52 | 62.098 | 119 | 0 | 4 | detail |  | OK_DETAIL
TA 414 | 2026-01 | 54 | 44 | 81.48 | 49 | 55.1364 | 123.4 | 0 | 10 | detail |  | OK_DETAIL
TA 414 | 2026-02 | 30 | 25 | 83.33 | 74 | 73.16 | 121.6 | 0 | 5 | detail |  | OK_DETAIL
TA 414 | 2026-03 | 24 | 21 | 87.5 | 23 | 32.381 | 66 | 0 | 3 | detail |  | OK_DETAIL
TA 414 | 2026-04 | 14 | 6 | 42.86 | 36 | 39.8333 | 56.5 | 0 | 8 | detail |  | OK_DETAIL
TA 414 | 2026-05 | 15 | 8 | 53.33 | 34 | 32.375 | 42.3 | 0 | 7 | detail |  | OK_DETAIL
TA 414 | 2026-06 | 16 | 2 | 12.5 | 8.5 | 8.5 | 9.7 | 0 | 14 | detail |  | OK_DETAIL
TA 416 | 2024-05 | 6 | 6 | 100 | 186 | 168.1667 | 200.5 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2024-06 | 17 | 17 | 100 | 187 | 202.7059 | 320.8 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2024-07 | 10 | 10 | 100 | 127 | 151.5 | 278.2 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2024-08 | 13 | 13 | 100 | 129 | 157.9231 | 269 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2024-09 | 29 | 29 | 100 | 206 | 176.7241 | 257.4 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2024-10 | 50 | 50 | 100 | 131.5 | 139.68 | 210 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2024-11 | 46 | 46 | 100 | 106 | 100.913 | 145 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2024-12 | 37 | 37 | 100 | 131 | 161.4595 | 317 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2025-01 | 34 | 34 | 100 | 151 | 186.5882 | 334.1 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2025-02 | 24 | 24 | 100 | 111 | 132 | 211.8 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2025-03 | 16 | 16 | 100 | 185.5 | 182.1875 | 250 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2025-04 | 13 | 13 | 100 | 128 | 152.9231 | 239 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2025-05 | 6 | 6 | 100 | 145 | 141.1667 | 208.5 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2025-06 | 1 | 1 | 100 | 127 | 127 | 127 | 0 | 0 | detail |  | OK_DETAIL
TA 416 | 2025-10 | 4 | 0 | 0 |  |  |  | 0 | 4 | detail |  | OK_DETAIL
TA 416 | 2025-11 | 6 | 0 | 0 |  |  |  | 0 | 6 | detail |  | OK_DETAIL
TA 416 | 2025-12 | 2 | 1 | 50 |  |  |  | 1 | 1 | detail |  | OK_DETAIL
TA 416 | 2026-02 | 10 | 0 | 0 |  |  |  | 0 | 10 | detail |  | OK_DETAIL
TA 416 | 2026-05 | 3 | 0 | 0 |  |  |  | 0 | 3 | detail |  | OK_DETAIL
TA 416 | 2026-06 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 416 | 2026-07 | 3 | 0 | 0 |  |  |  | 0 | 3 | detail |  | OK_DETAIL
TA 418 | 2024-01 | 2 | 2 | 100 | 358.5 | 358.5 | 358.9 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2024-06 | 2 | 2 | 100 | 165 | 165 | 171.4 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2024-07 | 8 | 8 | 100 | 184 | 183.5714 | 245.2 | 1 | 0 | detail |  | OK_DETAIL
TA 418 | 2024-08 | 9 | 8 | 88.89 | 165.5 | 175.25 | 257 | 0 | 1 | detail |  | OK_DETAIL
TA 418 | 2024-09 | 7 | 7 | 100 | 100 | 153.7143 | 332.8 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2024-10 | 4 | 4 | 100 | 175 | 160.3333 | 211 | 1 | 0 | detail |  | OK_DETAIL
TA 418 | 2024-11 | 5 | 5 | 100 | 202.5 | 182 | 212.4 | 1 | 0 | detail |  | OK_DETAIL
TA 418 | 2024-12 | 6 | 5 | 83.33 | 70 | 55.6 | 78 | 0 | 1 | detail |  | OK_DETAIL
TA 418 | 2025-01 | 6 | 6 | 100 | 66.5 | 74.1667 | 109.5 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2025-02 | 7 | 7 | 100 | 90 | 121.7143 | 231.2 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2025-03 | 9 | 9 | 100 | 124 | 154.6667 | 258.4 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2025-04 | 6 | 6 | 100 | 163 | 154.4 | 199.4 | 1 | 0 | detail |  | OK_DETAIL
TA 418 | 2025-05 | 10 | 10 | 100 | 108.5 | 116.9 | 177.7 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2025-06 | 16 | 15 | 93.75 | 58 | 71.6 | 140 | 0 | 1 | detail |  | OK_DETAIL
TA 418 | 2025-07 | 17 | 17 | 100 | 133 | 131.5882 | 175.2 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2025-08 | 3 | 3 | 100 | 134 | 100.3333 | 135.6 | 0 | 0 | detail |  | OK_DETAIL
TA 418 | 2025-09 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 418 | 2025-10 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 418 | 2025-11 | 8 | 5 | 62.5 | 66 | 59.6 | 74 | 0 | 3 | detail |  | OK_DETAIL
TA 418 | 2025-12 | 6 | 4 | 66.67 | 24 | 30.3333 | 44 | 1 | 2 | detail |  | OK_DETAIL
TA 418 | 2026-01 | 3 | 1 | 33.33 | 27 | 27 | 27 | 0 | 2 | detail |  | OK_DETAIL
TA 418 | 2026-02 | 4 | 1 | 25 | 7 | 7 | 7 | 0 | 3 | detail |  | OK_DETAIL
TA 418 | 2026-03 | 5 | 0 | 0 |  |  |  | 0 | 5 | detail |  | OK_DETAIL
TA 418 | 2026-04 | 2 | 0 | 0 |  |  |  | 0 | 2 | detail |  | OK_DETAIL
TA 418 | 2026-05 | 4 | 0 | 0 |  |  |  | 0 | 4 | detail |  | OK_DETAIL
TA 418 | 2026-06 | 10 | 0 | 0 |  |  |  | 0 | 10 | detail |  | OK_DETAIL
TA 418 | 2026-07 | 6 | 0 | 0 |  |  |  | 0 | 6 | detail |  | OK_DETAIL
TA 419 | 2024-05 | 3 | 3 | 100 | 234 | 239 | 250.8 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2024-06 | 9 | 9 | 100 | 236 | 213.4444 | 281.8 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2024-07 | 17 | 17 | 100 | 182 | 219.875 | 326 | 1 | 0 | detail |  | OK_DETAIL
TA 419 | 2024-08 | 8 | 8 | 100 | 206 | 230.375 | 374.5 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2024-09 | 16 | 16 | 100 | 174 | 191.9375 | 324 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2024-10 | 18 | 18 | 100 | 127 | 172.6111 | 296.4 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2024-11 | 14 | 14 | 100 | 108.5 | 165 | 310 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2024-12 | 12 | 12 | 100 | 122.5 | 188.8333 | 316.4 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2025-01 | 7 | 7 | 100 | 204 | 185.1429 | 212.2 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2025-02 | 10 | 10 | 100 | 285.5 | 301.3 | 313.2 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2025-03 | 5 | 5 | 100 | 259 | 225.8 | 267.4 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2025-04 | 14 | 14 | 100 | 226.5 | 219.2143 | 251.9 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2025-05 | 8 | 7 | 87.5 | 215 | 241.7143 | 362 | 0 | 1 | detail |  | OK_DETAIL
TA 419 | 2025-06 | 10 | 10 | 100 | 150.5 | 164.4 | 296.7 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2025-07 | 5 | 4 | 80 | 152.5 | 146.75 | 198.4 | 0 | 1 | detail |  | OK_DETAIL
TA 419 | 2025-08 | 2 | 1 | 50 | 136 | 136 | 136 | 0 | 1 | detail |  | OK_DETAIL
TA 419 | 2025-09 | 3 | 3 | 100 | 57 | 61.3333 | 69.8 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2025-10 | 6 | 6 | 100 | 45 | 64.3333 | 131.5 | 0 | 0 | detail |  | OK_DETAIL
TA 419 | 2025-11 | 18 | 15 | 83.33 | 24 | 77.3333 | 212.4 | 0 | 3 | detail |  | OK_DETAIL
TA 419 | 2025-12 | 18 | 16 | 88.89 | 20.5 | 31.1875 | 73.5 | 0 | 2 | detail |  | OK_DETAIL
TA 419 | 2026-01 | 12 | 9 | 75 | 20 | 61.2222 | 136.2 | 0 | 3 | detail |  | OK_DETAIL
TA 419 | 2026-02 | 7 | 5 | 71.43 | 78 | 91 | 122.4 | 0 | 2 | detail |  | OK_DETAIL
TA 419 | 2026-03 | 6 | 5 | 83.33 | 34 | 33.8 | 50 | 0 | 1 | detail |  | OK_DETAIL
TA 419 | 2026-04 | 8 | 5 | 62.5 | 14 | 18 | 31 | 0 | 3 | detail |  | OK_DETAIL
TA 419 | 2026-05 | 18 | 13 | 72.22 | 23.5 | 25.25 | 41.3 | 1 | 5 | detail |  | OK_DETAIL
TA 419 | 2026-06 | 16 | 11 | 68.75 | 15 | 17 | 32 | 0 | 5 | detail |  | OK_DETAIL
TA 419 | 2026-07 | 14 | 2 | 14.29 | 10.5 | 10.5 | 14.1 | 0 | 12 | detail |  | OK_DETAIL
TA 419 | 2026-08 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 421 | 2024-05 | 1 | 1 | 100 | 99 | 99 | 99 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2024-06 | 14 | 14 | 100 | 110.5 | 114.5714 | 181 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2024-07 | 20 | 20 | 100 | 83 | 85.85 | 134 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2024-08 | 21 | 21 | 100 | 77 | 78 | 105 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2024-09 | 10 | 10 | 100 | 94.5 | 105.4 | 169.9 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2024-10 | 13 | 13 | 100 | 102 | 172.4615 | 325.2 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2024-11 | 21 | 21 | 100 | 90 | 121.9048 | 250 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2024-12 | 34 | 34 | 100 | 88 | 109.3333 | 197.4 | 1 | 0 | detail |  | OK_DETAIL
TA 421 | 2025-01 | 36 | 36 | 100 | 98 | 120.6667 | 279 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2025-02 | 30 | 30 | 100 | 145 | 134.2667 | 226.1 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2025-03 | 19 | 19 | 100 | 133 | 118.9474 | 181.4 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2025-04 | 11 | 11 | 100 | 91 | 91 | 215 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2025-05 | 34 | 32 | 94.12 | 125 | 132.875 | 201.9 | 0 | 2 | detail |  | OK_DETAIL
TA 421 | 2025-06 | 23 | 23 | 100 | 154 | 143.2609 | 181.6 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2025-07 | 11 | 11 | 100 | 125 | 124.4545 | 163 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2025-08 | 2 | 1 | 50 | 37 | 37 | 37 | 0 | 1 | detail |  | OK_DETAIL
TA 421 | 2025-10 | 3 | 1 | 33.33 | 45 | 45 | 45 | 0 | 2 | detail |  | OK_DETAIL
TA 421 | 2025-11 | 1 | 1 | 100 | 13 | 13 | 13 | 0 | 0 | detail |  | OK_DETAIL
TA 421 | 2025-12 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 421 | 2026-01 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 421 | 2026-02 | 8 | 0 | 0 |  |  |  | 0 | 8 | detail |  | OK_DETAIL
TA 421 | 2026-03 | 2 | 0 | 0 |  |  |  | 0 | 2 | detail |  | OK_DETAIL
TA 421 | 2026-06 | 3 | 0 | 0 |  |  |  | 0 | 3 | detail |  | OK_DETAIL
TA 505 | 2024-03 | 1 | 1 | 100 | 637 | 637 | 637 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2024-04 | 2 | 2 | 100 | 574.5 | 574.5 | 626.9 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2024-10 | 9 | 9 | 100 | 123 | 144.3333 | 192.4 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2024-11 | 26 | 26 | 100 | 129 | 135.1154 | 175.5 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2024-12 | 36 | 36 | 100 | 151.5 | 185.6944 | 308.5 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-01 | 30 | 30 | 100 | 231 | 226.3333 | 362.1 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-02 | 32 | 32 | 100 | 211 | 215.25 | 367.3 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-03 | 21 | 21 | 100 | 251 | 230.1429 | 359 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-04 | 48 | 48 | 100 | 224 | 233.5625 | 352 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-05 | 47 | 47 | 100 | 196 | 195.0638 | 309 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-06 | 15 | 15 | 100 | 200 | 216.8 | 293.8 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-07 | 2 | 2 | 100 | 75 | 75 | 87.8 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-08 | 1 | 1 | 100 | 218 | 218 | 218 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-09 | 10 | 10 | 100 | 87 | 80.1 | 101.3 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-10 | 12 | 12 | 100 | 44.5 | 74.75 | 173.3 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2025-11 | 17 | 16 | 94.12 | 40 | 50 | 86 | 0 | 1 | detail |  | OK_DETAIL
TA 505 | 2025-12 | 18 | 16 | 88.89 | 19 | 21.6875 | 33 | 0 | 2 | detail |  | OK_DETAIL
TA 505 | 2026-01 | 17 | 17 | 100 | 14 | 30.6471 | 107.8 | 0 | 0 | detail |  | OK_DETAIL
TA 505 | 2026-02 | 10 | 8 | 80 | 7.5 | 9.875 | 18.6 | 0 | 2 | detail |  | OK_DETAIL
TA 505 | 2026-03 | 8 | 5 | 62.5 | 47 | 39.4 | 69.4 | 0 | 3 | detail |  | OK_DETAIL
TA 505 | 2026-04 | 8 | 4 | 50 | 16.5 | 17 | 27.4 | 0 | 4 | detail |  | OK_DETAIL
TA 505 | 2026-05 | 4 | 4 | 100 | 8 | 13.6667 | 24 | 1 | 0 | detail |  | OK_DETAIL
TA 505 | 2026-06 | 4 | 2 | 50 | 17 | 17 | 22.6 | 0 | 2 | detail |  | OK_DETAIL
TA 510 | 2025-02 | 4 | 0 | 0 |  |  |  | 0 | 4 | detail |  | OK_DETAIL
TA 510 | 2025-03 | 5 | 1 | 20 | 457 | 457 | 457 | 0 | 4 | detail |  | OK_DETAIL
TA 510 | 2025-04 | 6 | 4 | 66.67 | 410 | 409.75 | 419.1 | 0 | 2 | detail |  | OK_DETAIL
TA 510 | 2025-05 | 7 | 7 | 100 | 342 | 318.4286 | 363.4 | 0 | 0 | detail |  | OK_DETAIL
TA 510 | 2025-06 | 2 | 2 | 100 | 296.5 | 296.5 | 351.3 | 0 | 0 | detail |  | OK_DETAIL
TA 510 | 2025-08 | 1 | 1 | 100 | 296 | 296 | 296 | 0 | 0 | detail |  | OK_DETAIL
TA 510 | 2025-09 | 2 | 2 | 100 | 207 | 207 | 281.4 | 0 | 0 | detail |  | OK_DETAIL
TA 510 | 2025-10 | 5 | 4 | 80 | 92 | 88.25 | 95.7 | 0 | 1 | detail |  | OK_DETAIL
TA 510 | 2025-11 | 5 | 4 | 80 | 74 | 72.25 | 88 | 0 | 1 | detail |  | OK_DETAIL
TA 510 | 2025-12 | 10 | 10 | 100 | 70.5 | 75.9 | 114.1 | 0 | 0 | detail |  | OK_DETAIL
TA 510 | 2026-01 | 7 | 5 | 71.43 | 81 | 88.2 | 119.6 | 0 | 2 | detail |  | OK_DETAIL
TA 510 | 2026-02 | 6 | 6 | 100 | 69.5 | 62.8333 | 97 | 0 | 0 | detail |  | OK_DETAIL
TA 510 | 2026-03 | 4 | 1 | 25 | 15 | 15 | 15 | 0 | 3 | detail |  | OK_DETAIL
TA 510 | 2026-04 | 8 | 1 | 12.5 | 26 | 26 | 26 | 0 | 7 | detail |  | OK_DETAIL
TA 510 | 2026-05 | 13 | 0 | 0 |  |  |  | 0 | 13 | detail |  | OK_DETAIL
TA 510 | 2026-06 | 10 | 0 | 0 |  |  |  | 0 | 10 | detail |  | OK_DETAIL
TA 512 | 2025-02 | 3 | 3 | 100 | 180 | 198.3333 | 248.8 | 0 | 0 | detail |  | OK_DETAIL
TA 512 | 2025-03 | 26 | 26 | 100 | 224 | 230.2308 | 324 | 0 | 0 | detail |  | OK_DETAIL
TA 512 | 2025-04 | 24 | 24 | 100 | 225 | 214 | 286.2 | 0 | 0 | detail |  | OK_DETAIL
TA 512 | 2025-05 | 23 | 23 | 100 | 218 | 218.3043 | 283.8 | 0 | 0 | detail |  | OK_DETAIL
TA 512 | 2025-06 | 27 | 25 | 92.59 | 231 | 216.6 | 263 | 0 | 2 | detail |  | OK_DETAIL
TA 512 | 2025-07 | 35 | 34 | 97.14 | 176.5 | 202.7941 | 327.4 | 0 | 1 | detail |  | OK_DETAIL
TA 512 | 2025-08 | 26 | 25 | 96.15 | 165 | 187.76 | 341.8 | 0 | 1 | detail |  | OK_DETAIL
TA 512 | 2025-09 | 19 | 16 | 84.21 | 144.5 | 173.375 | 304 | 0 | 3 | detail |  | OK_DETAIL
TA 512 | 2025-10 | 23 | 21 | 91.3 | 165 | 155.0476 | 258 | 0 | 2 | detail |  | OK_DETAIL
TA 512 | 2025-11 | 29 | 28 | 96.55 | 130 | 144.3571 | 238.4 | 0 | 1 | detail |  | OK_DETAIL
TA 512 | 2025-12 | 36 | 28 | 77.78 | 93 | 115.5 | 209.3 | 0 | 8 | detail |  | OK_DETAIL
TA 512 | 2026-01 | 11 | 9 | 81.82 | 165 | 136.2222 | 185.4 | 0 | 2 | detail |  | OK_DETAIL
TA 512 | 2026-02 | 4 | 2 | 50 | 126 | 126 | 138.8 | 0 | 2 | detail |  | OK_DETAIL
TA 512 | 2026-03 | 3 | 2 | 66.67 | 54 | 54 | 86 | 0 | 1 | detail |  | OK_DETAIL
TA 512 | 2026-04 | 7 | 2 | 28.57 | 76.5 | 76.5 | 77.7 | 0 | 5 | detail |  | OK_DETAIL
TA 512 | 2026-05 | 5 | 4 | 80 | 49.5 | 49.5 | 55.7 | 0 | 1 | detail |  | OK_DETAIL
TA 512 | 2026-06 | 6 | 1 | 16.67 | 29 | 29 | 29 | 0 | 5 | detail |  | OK_DETAIL
TA 512 | 2026-07 | 4 | 1 | 25 | 26 | 26 | 26 | 0 | 3 | detail |  | OK_DETAIL
TA 512 | 2026-08 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 513 | 2025-03 | 1 | 1 | 100 | 179 | 179 | 179 | 0 | 0 | detail |  | OK_DETAIL
TA 513 | 2025-04 | 14 | 2 | 14.29 | 171.5 | 171.5 | 173.5 | 0 | 12 | detail |  | OK_DETAIL
TA 513 | 2025-05 | 15 | 9 | 60 | 183 | 183.1111 | 208.6 | 0 | 6 | detail |  | OK_DETAIL
TA 513 | 2025-06 | 8 | 1 | 12.5 | 253 | 253 | 253 | 0 | 7 | detail |  | OK_DETAIL
TA 513 | 2025-07 | 11 | 4 | 36.36 | 187 | 212.75 | 290.9 | 0 | 7 | detail |  | OK_DETAIL
TA 513 | 2025-08 | 3 | 2 | 66.67 | 232.5 | 232.5 | 280.1 | 0 | 1 | detail |  | OK_DETAIL
TA 513 | 2025-09 | 7 | 4 | 57.14 | 30.5 | 34.25 | 49.7 | 0 | 3 | detail |  | OK_DETAIL
TA 513 | 2025-10 | 3 | 0 | 0 |  |  |  | 0 | 3 | detail |  | OK_DETAIL
TA 513 | 2025-11 | 2 | 2 | 100 | 111.5 | 111.5 | 112.7 | 0 | 0 | detail |  | OK_DETAIL
TA 513 | 2025-12 | 5 | 5 | 100 | 151 | 131.6 | 159.2 | 0 | 0 | detail |  | OK_DETAIL
TA 513 | 2026-02 | 2 | 2 | 100 | 66 | 66 | 89.2 | 0 | 0 | detail |  | OK_DETAIL
TA 513 | 2026-03 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 513 | 2026-04 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TA 513 | 2026-05 | 16 | 1 | 6.25 | 45 | 45 | 45 | 0 | 15 | detail |  | OK_DETAIL
TA 513 | 2026-06 | 11 | 0 | 0 |  |  |  | 0 | 11 | detail |  | OK_DETAIL
TA 513 | 2026-07 | 5 | 0 | 0 |  |  |  | 0 | 5 | detail |  | OK_DETAIL
TA 513 | 2026-08 | 4 | 0 | 0 |  |  |  | 0 | 4 | detail |  | OK_DETAIL
TA 601 | 2025-08 | 2 | 1 | 50 | 142 | 142 | 142 | 0 | 1 | detail |  | OK_DETAIL
TA 601 | 2025-09 | 2 | 2 | 100 | 134.5 | 134.5 | 146.9 | 0 | 0 | detail |  | OK_DETAIL
TA 601 | 2025-10 | 8 | 7 | 87.5 | 89 | 88.5714 | 97.4 | 0 | 1 | detail |  | OK_DETAIL
TA 601 | 2025-11 | 10 | 7 | 70 | 44 | 70 | 129.2 | 0 | 3 | detail |  | OK_DETAIL
TA 601 | 2025-12 | 20 | 13 | 65 | 33 | 61 | 69.6 | 0 | 7 | detail |  | OK_DETAIL
TA 601 | 2026-01 | 27 | 25 | 92.59 | 17 | 31.875 | 66.2 | 1 | 2 | detail |  | OK_DETAIL
TA 601 | 2026-02 | 17 | 15 | 88.24 | 14 | 22.4667 | 28.4 | 0 | 2 | detail |  | OK_DETAIL
TA 601 | 2026-03 | 15 | 12 | 80 | 90 | 77.5833 | 109.4 | 0 | 3 | detail |  | OK_DETAIL
TA 601 | 2026-04 | 12 | 9 | 75 | 64.5 | 62.625 | 88.6 | 1 | 3 | detail |  | OK_DETAIL
TA 601 | 2026-05 | 11 | 7 | 63.64 | 38 | 36.5714 | 47.8 | 0 | 4 | detail |  | OK_DETAIL
TA 601 | 2026-06 | 24 | 13 | 54.17 | 16 | 17.5385 | 22.2 | 0 | 11 | detail |  | OK_DETAIL
TA 601 | 2026-07 | 32 | 13 | 40.62 | 14 | 12.6154 | 17.8 | 0 | 19 | detail |  | OK_DETAIL
TA 601 | 2026-08 | 9 | 0 | 0 |  |  |  | 0 | 9 | detail |  | OK_DETAIL
TB 408 | 2023-10 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TB 408 | 2024-09 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TB 408 | 2024-11 | 3 | 0 | 0 |  |  |  | 0 | 3 | detail |  | OK_DETAIL
TB 408 | 2024-12 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TB 501 | 2024-08 | 3 | 3 | 100 | 185 | 171.6667 | 189.8 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2024-09 | 7 | 7 | 100 | 144 | 133.2857 | 172.8 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2024-10 | 25 | 25 | 100 | 123 | 127.2 | 170.6 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2024-11 | 26 | 26 | 100 | 93 | 87.6923 | 121.5 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2024-12 | 27 | 27 | 100 | 68 | 70.1481 | 106.4 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-01 | 21 | 21 | 100 | 62 | 80.5238 | 133 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-02 | 21 | 21 | 100 | 63 | 75.6667 | 112 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-03 | 9 | 9 | 100 | 29 | 46.3333 | 85.6 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-04 | 11 | 11 | 100 | 41 | 49.9091 | 98 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-05 | 18 | 18 | 100 | 31.5 | 41.0556 | 72.7 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-06 | 6 | 6 | 100 | 22 | 25.5 | 39 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-07 | 1 | 1 | 100 | 49 | 49 | 49 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-08 | 3 | 3 | 100 | 74 | 72 | 77.2 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-09 | 8 | 8 | 100 | 48 | 64.875 | 111.5 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-10 | 6 | 6 | 100 | 28 | 30.1667 | 43.5 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-11 | 7 | 7 | 100 | 10 | 13.4286 | 28.4 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2025-12 | 10 | 10 | 100 | 12 | 13.1111 | 21.2 | 1 | 0 | detail |  | OK_DETAIL
TB 501 | 2026-01 | 9 | 9 | 100 | 14 | 17.4444 | 25.6 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2026-02 | 4 | 4 | 100 | 24 | 23.6667 | 34.4 | 1 | 0 | detail |  | OK_DETAIL
TB 501 | 2026-03 | 4 | 4 | 100 | 4.5 | 5.25 | 7.1 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2026-04 | 5 | 5 | 100 | 16 | 16.2 | 25.4 | 0 | 0 | detail |  | OK_DETAIL
TB 501 | 2026-06 | 3 | 2 | 66.67 |  |  |  | 2 | 1 | detail |  | OK_DETAIL
TB 501 | 2026-07 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | OK_DETAIL
TB 507 | 2025-01 | 2 | 2 | 100 | 188.5 | 188.5 | 216.9 | 0 | 0 | detail |  | OK_DETAIL
TB 507 | 2025-02 | 20 | 20 | 100 | 164 | 190.4 | 286.2 | 0 | 0 | detail |  | OK_DETAIL
TB 507 | 2025-03 | 16 | 8 | 50 | 189 | 267.5 | 447.4 | 0 | 8 | detail |  | OK_DETAIL
TB 507 | 2025-04 | 13 | 5 | 38.46 | 235 | 218 | 288.4 | 0 | 8 | detail |  | OK_DETAIL
TB 507 | 2025-05 | 9 | 7 | 77.78 | 210 | 245 | 383.2 | 0 | 2 | detail |  | OK_DETAIL
TB 507 | 2025-06 | 25 | 24 | 96 | 124.5 | 148.375 | 202.5 | 0 | 1 | detail |  | OK_DETAIL
TB 507 | 2025-07 | 50 | 45 | 90 | 71 | 78.7333 | 121.2 | 0 | 5 | detail |  | OK_DETAIL
TB 507 | 2025-08 | 52 | 45 | 86.54 | 62 | 82.0667 | 138.2 | 0 | 7 | detail |  | OK_DETAIL
TB 507 | 2025-09 | 20 | 13 | 65 | 48 | 81.5385 | 141.6 | 0 | 7 | detail |  | OK_DETAIL
TB 507 | 2025-10 | 8 | 8 | 100 | 43 | 61.2857 | 115 | 1 | 0 | detail |  | OK_DETAIL
TB 507 | 2025-11 | 19 | 18 | 94.74 | 25.5 | 54.9444 | 114.9 | 0 | 1 | detail |  | OK_DETAIL
TB 507 | 2025-12 | 13 | 9 | 69.23 | 64 | 100.4444 | 160.4 | 0 | 4 | detail |  | OK_DETAIL
TB 507 | 2026-01 | 15 | 10 | 66.67 | 84.5 | 90.2 | 126.3 | 0 | 5 | detail |  | OK_DETAIL
TB 507 | 2026-02 | 12 | 8 | 66.67 | 82.5 | 84.625 | 121.6 | 0 | 4 | detail |  | OK_DETAIL
TB 507 | 2026-03 | 16 | 11 | 68.75 | 106 | 87.8182 | 132 | 0 | 5 | detail |  | OK_DETAIL
TB 507 | 2026-04 | 20 | 16 | 80 | 79 | 64.375 | 119.5 | 0 | 4 | detail |  | OK_DETAIL
TB 507 | 2026-05 | 26 | 14 | 53.85 | 13 | 31 | 69.4 | 0 | 12 | detail |  | OK_DETAIL
TB 507 | 2026-06 | 20 | 10 | 50 | 27 | 29.4444 | 47 | 1 | 10 | detail |  | OK_DETAIL
TB 507 | 2026-07 | 16 | 3 | 18.75 | 9 | 13.3333 | 21.8 | 0 | 13 | detail |  | OK_DETAIL
TB 507 | 2026-08 | 5 | 0 | 0 |  |  |  | 0 | 5 | detail |  | OK_DETAIL
TB 605 | 2025-08 | 1 | 1 | 100 | 108 | 108 | 108 | 0 | 0 | detail |  | OK_DETAIL
TB 605 | 2025-09 | 3 | 3 | 100 | 90 | 131.6667 | 196.4 | 0 | 0 | detail |  | OK_DETAIL
TB 605 | 2025-10 | 15 | 13 | 86.67 | 110 | 140 | 210 | 0 | 2 | detail |  | OK_DETAIL
TB 605 | 2025-11 | 42 | 37 | 88.1 | 90 | 100.1351 | 166.8 | 0 | 5 | detail |  | OK_DETAIL
TB 605 | 2025-12 | 57 | 50 | 87.72 | 94.5 | 101.02 | 155.2 | 0 | 7 | detail |  | OK_DETAIL
TB 605 | 2026-01 | 42 | 39 | 92.86 | 69 | 70.5641 | 101 | 0 | 3 | detail |  | OK_DETAIL
TB 605 | 2026-02 | 42 | 36 | 85.71 | 62 | 65.25 | 107.5 | 0 | 6 | detail |  | OK_DETAIL
TB 605 | 2026-03 | 28 | 21 | 75 | 31 | 41.3333 | 70 | 0 | 7 | detail |  | OK_DETAIL
TB 605 | 2026-04 | 26 | 14 | 53.85 | 25 | 31.7143 | 59.7 | 0 | 12 | detail |  | OK_DETAIL
TB 605 | 2026-05 | 55 | 20 | 36.36 | 16.5 | 17.8 | 28.7 | 0 | 35 | detail |  | OK_DETAIL
TB 605 | 2026-06 | 41 | 16 | 39.02 | 14 | 17.9375 | 35 | 0 | 25 | detail |  | OK_DETAIL
TB 605 | 2026-07 | 7 | 3 | 42.86 | 5 | 4.6667 | 5 | 0 | 4 | detail |  | OK_DETAIL
TB 605 | 2026-08 | 2 | 0 | 0 |  |  |  | 0 | 2 | detail |  | OK_DETAIL
TB 608 | 2025-10 | 2 | 2 | 100 | 236 | 236 | 276 | 0 | 0 | detail |  | DETAIL_STATUS_MISMATCH
TB 608 | 2025-11 | 20 | 12 | 60 | 135.5 | 129.5833 | 187.3 | 0 | 8 | detail |  | DETAIL_STATUS_MISMATCH
TB 608 | 2025-12 | 34 | 16 | 47.06 | 109 | 111 | 171 | 0 | 18 | detail |  | DETAIL_STATUS_MISMATCH
TB 608 | 2026-01 | 30 | 10 | 33.33 | 123 | 112.4 | 144.6 | 0 | 20 | detail |  | DETAIL_STATUS_MISMATCH
TB 608 | 2026-02 | 30 | 11 | 36.67 | 109 | 97.0909 | 143 | 0 | 19 | detail |  | DETAIL_STATUS_MISMATCH
TB 608 | 2026-03 | 16 | 3 | 18.75 | 99 | 92.3333 | 111.8 | 0 | 13 | detail |  | DETAIL_STATUS_MISMATCH
TB 608 | 2026-04 | 6 | 2 | 33.33 | 61.5 | 61.5 | 73.1 | 0 | 4 | detail |  | DETAIL_STATUS_MISMATCH
TB 608 | 2026-05 | 9 | 1 | 11.11 | 47 | 47 | 47 | 0 | 8 | detail |  | DETAIL_STATUS_MISMATCH
TB 608 | 2026-06 | 5 | 1 | 20 | 36 | 36 | 36 | 0 | 4 | detail |  | DETAIL_STATUS_MISMATCH
TB 608 | 2026-07 | 6 | 0 | 0 |  |  |  | 0 | 6 | detail |  | DETAIL_STATUS_MISMATCH
TB 608 | 2026-08 | 1 | 0 | 0 |  |  |  | 0 | 1 | detail |  | DETAIL_STATUS_MISMATCH

## Foundation Delay Coverage
Foundation Delay Coverage
Project | Eligible | Coverage Status | Source Type | Parser Modes | Reason | Foundation Locations | Matched Locations | Negative Excluded | Unmatched Locations | Notes
TA 413 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 314 | 305 | 1 | 9 | Negative delays are excluded from trend statistics.
TA 414 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 335 | 280 | 1 | 55 | Negative delays are excluded from trend statistics.
TA 416 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 331 | 303 | 1 | 28 | Negative delays are excluded from trend statistics.
TA 418 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 167 | 125 | 5 | 42 | Negative delays are excluded from trend statistics.
TA 419 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 285 | 245 | 2 | 40 | Negative delays are excluded from trend statistics.
TA 421 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 319 | 299 | 1 | 20 | Negative delays are excluded from trend statistics.
TA 504 | No | SKIPPED_BLANK_CONFIG | missing |  | Foundation mapping intentionally blank in DPR_Config. | 0 | 0 | 0 | 0 | Negative delays are excluded from trend statistics.
TA 505 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 378 | 364 | 1 | 14 | Negative delays are excluded from trend statistics.
TA 506 | No | SKIPPED_BLANK_CONFIG | missing |  | Foundation mapping intentionally blank in DPR_Config. | 0 | 0 | 0 | 0 | Negative delays are excluded from trend statistics.
TA 509 | No | SNAPSHOT_FALLBACK | snapshot_fallback |  | Only snapshot/missing foundation source is available. | 0 | 0 | 0 | 0 | Negative delays are excluded from trend statistics.
TA 510 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 95 | 48 | 0 | 47 | Negative delays are excluded from trend statistics.
TA 512 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 312 | 274 | 0 | 38 | Negative delays are excluded from trend statistics.
TA 513 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 109 | 33 | 0 | 76 | Negative delays are excluded from trend statistics.
TA 515 | No | MISSING | missing |  | Only snapshot/missing foundation source is available. | 0 | 0 | 0 | 0 | Negative delays are excluded from trend statistics.
TA 601 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 189 | 124 | 2 | 65 | Negative delays are excluded from trend statistics.
TA 602 | No | SNAPSHOT_FALLBACK | snapshot_fallback |  | Only snapshot/missing foundation source is available. | 0 | 0 | 0 | 0 | Negative delays are excluded from trend statistics.
TB 408 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 6 | 0 | 0 | 6 | Negative delays are excluded from trend statistics.
TB 412 | No | SKIPPED_BLANK_CONFIG | missing |  | Foundation mapping intentionally blank in DPR_Config. | 0 | 0 | 0 | 0 | Negative delays are excluded from trend statistics.
TB 501 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 235 | 233 | 4 | 2 | Negative delays are excluded from trend statistics.
TB 507 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 377 | 276 | 2 | 101 | Negative delays are excluded from trend statistics.
TB 605 | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 361 | 253 | 0 | 108 | Negative delays are excluded from trend statistics.
TB 608 | Yes | DETAIL_STATUS_MISMATCH | detail |  | Detail completion dates were parsed, but counts are materially below status cumulative foundation progress; keeping detail source and flagging mapping/status mismatch. | 159 | 58 | 0 | 101 | Negative delays are excluded from trend statistics.

## Foundation Delay Anomalies
Foundation Delay Anomalies
Project | Location | Foundation Date | Erection Start | Delay Days | Issue | Foundation Line | Erection Line
TA 413 | 39/8 | 2025-01-24 | 2024-03-26 | -304 | NEGATIVE_DELAY_EXCLUDED
TA 413 | 37/1 | 2024-09-23 |  |  | UNMATCHED_LOCATION
TA 413 | 3/8 | 2024-10-05 |  |  | UNMATCHED_LOCATION
TA 413 | 3/9 | 2024-10-09 |  |  | UNMATCHED_LOCATION
TA 413 | 37/0 | 2024-10-14 |  |  | UNMATCHED_LOCATION
TA 413 | 3/7 | 2024-10-19 |  |  | UNMATCHED_LOCATION
TA 413 | 3/6 | 2024-10-22 |  |  | UNMATCHED_LOCATION
TA 413 | 3/4 | 2024-10-29 |  |  | UNMATCHED_LOCATION
TA 413 | 36B/0-N | 2026-01-23 |  |  | UNMATCHED_LOCATION
TA 413 | 36C/0-N | 2026-02-08 |  |  | UNMATCHED_LOCATION
TA 414 | 121/4 | 2024-11-29 | 2024-03-27 | -247 | NEGATIVE_DELAY_EXCLUDED
TA 414 | 249/2 | 2025-01-03 |  |  | UNMATCHED_LOCATION
TA 414 | 172/0 | 2025-03-26 |  |  | UNMATCHED_LOCATION
TA 414 | 165/2 | 2025-05-15 |  |  | UNMATCHED_LOCATION
TA 414 | 224/0 | 2025-11-08 |  |  | UNMATCHED_LOCATION
TA 414 | 165/6 | 2025-12-23 |  |  | UNMATCHED_LOCATION
TA 414 | 257/0 | 2025-12-23 |  |  | UNMATCHED_LOCATION
TA 414 | 170/0 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TA 414 | 216/2 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 414 | 216/3 | 2026-01-12 |  |  | UNMATCHED_LOCATION
TA 414 | 162/0 | 2026-01-13 |  |  | UNMATCHED_LOCATION
TA 414 | 194/0 | 2026-01-17 |  |  | UNMATCHED_LOCATION
TA 414 | 165/4 | 2026-01-22 |  |  | UNMATCHED_LOCATION
TA 414 | 211/4 | 2026-01-22 |  |  | UNMATCHED_LOCATION
TA 414 | 193/0 | 2026-01-23 |  |  | UNMATCHED_LOCATION
TA 414 | 233/0 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TA 414 | 236/0 | 2026-01-28 |  |  | UNMATCHED_LOCATION
TA 414 | 168/0 | 2026-01-29 |  |  | UNMATCHED_LOCATION
TA 414 | 188/0 | 2026-01-29 |  |  | UNMATCHED_LOCATION
TA 414 | 211/0 | 2026-02-01 |  |  | UNMATCHED_LOCATION
TA 414 | 235/0 | 2026-02-07 |  |  | UNMATCHED_LOCATION
TA 414 | 232/4 | 2026-02-20 |  |  | UNMATCHED_LOCATION
TA 414 | 173/0 | 2026-02-27 |  |  | UNMATCHED_LOCATION
TA 414 | 219/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TA 414 | 163/0 | 2026-03-04 |  |  | UNMATCHED_LOCATION
TA 414 | 231/0 | 2026-03-16 |  |  | UNMATCHED_LOCATION
TA 414 | 150/1 | 2026-03-24 |  |  | UNMATCHED_LOCATION
TA 414 | 180/0 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 414 | 156/0 | 2026-04-06 |  |  | UNMATCHED_LOCATION
TA 414 | 150/0 | 2026-04-12 |  |  | UNMATCHED_LOCATION
TA 414 | 131/0 | 2026-04-16 |  |  | UNMATCHED_LOCATION
TA 414 | 155/0 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 414 | 200/0 | 2026-04-19 |  |  | UNMATCHED_LOCATION
TA 414 | 131/1 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 414 | 189/0 | 2026-04-28 |  |  | UNMATCHED_LOCATION
TA 414 | 169/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 414 | 232/3 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 414 | 129/0 | 2026-05-11 |  |  | UNMATCHED_LOCATION
TA 414 | 145/1 | 2026-05-16 |  |  | UNMATCHED_LOCATION
TA 414 | 206/1 | 2026-05-17 |  |  | UNMATCHED_LOCATION
TA 414 | 229B/0 | 2026-05-22 |  |  | UNMATCHED_LOCATION
TA 414 | 229A/0 | 2026-05-28 |  |  | UNMATCHED_LOCATION
TA 414 | 154/0 | 2026-06-01 |  |  | UNMATCHED_LOCATION
TA 414 | 212/0 | 2026-06-01 |  |  | UNMATCHED_LOCATION
TA 414 | 254/0 | 2026-06-06 |  |  | UNMATCHED_LOCATION
TA 414 | 132/2 | 2026-06-07 |  |  | UNMATCHED_LOCATION
TA 414 | 208/0 | 2026-06-08 |  |  | UNMATCHED_LOCATION
TA 414 | 130/0 | 2026-06-12 |  |  | UNMATCHED_LOCATION
TA 414 | 152/0 | 2026-06-12 |  |  | UNMATCHED_LOCATION
TA 414 | 253/0 | 2026-06-15 |  |  | UNMATCHED_LOCATION
TA 414 | 165/3 | 2026-06-17 |  |  | UNMATCHED_LOCATION
TA 414 | 165/1 | 2026-06-21 |  |  | UNMATCHED_LOCATION
TA 414 | 202/0 | 2026-06-21 |  |  | UNMATCHED_LOCATION
TA 414 | 135/0 | 2026-06-22 |  |  | UNMATCHED_LOCATION
TA 414 | 153/2 | 2026-06-26 |  |  | UNMATCHED_LOCATION
TA 414 | 200/1 | 2026-06-26 |  |  | UNMATCHED_LOCATION
TA 416 | 66/0 | 2025-12-19 | 2025-12-05 | -14 | NEGATIVE_DELAY_EXCLUDED
TA 416 | 4/0-5/0 | 2025-10-14 |  |  | UNMATCHED_LOCATION
TA 416 | 5/0-7/6 | 2025-10-22 |  |  | UNMATCHED_LOCATION
TA 416 | 7/6-8B/0 | 2025-10-25 |  |  | UNMATCHED_LOCATION
TA 416 | 34/0-35/0 | 2025-10-28 |  |  | UNMATCHED_LOCATION
TA 416 | 35/0-36/0 | 2025-11-01 |  |  | UNMATCHED_LOCATION
TA 416 | 33/0-34/0 | 2025-11-04 |  |  | UNMATCHED_LOCATION
TA 416 | 31/0-33/0 | 2025-11-10 |  |  | UNMATCHED_LOCATION
TA 416 | 30/0-31/0 | 2025-11-16 |  |  | UNMATCHED_LOCATION
TA 416 | 12/0-14/0 | 2025-11-20 |  |  | UNMATCHED_LOCATION
TA 416 | 20/0-21/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TA 416 | 19/0-20/0 | 2025-12-06 |  |  | UNMATCHED_LOCATION
TA 416 | 0/0-2/0 | 2026-02-06 |  |  | UNMATCHED_LOCATION
TA 416 | 2/0-3/0 | 2026-02-10 |  |  | UNMATCHED_LOCATION
TA 416 | 36/0-37/0 | 2026-02-10 |  |  | UNMATCHED_LOCATION
TA 416 | 14/0-17/0 | 2026-02-14 |  |  | UNMATCHED_LOCATION
TA 416 | 37/0-38/11 | 2026-02-16 |  |  | UNMATCHED_LOCATION
TA 416 | 8B/0-12/0 | 2026-02-18 |  |  | UNMATCHED_LOCATION
TA 416 | 38/11-40/0 | 2026-02-20 |  |  | UNMATCHED_LOCATION
TA 416 | 21/0-25/0 | 2026-02-23 |  |  | UNMATCHED_LOCATION
TA 416 | 17/0-19/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TA 416 | 25/0-30/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TA 416 | 40/0-47/0 | 2026-05-03 |  |  | UNMATCHED_LOCATION
TA 416 | 52/1-53/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 416 | 53/0-54/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 416 | 54/0-56/6 | 2026-06-29 |  |  | UNMATCHED_LOCATION
TA 416 | 56/6-64/0 | 2026-07-03 |  |  | UNMATCHED_LOCATION
TA 416 | 64/0-Gantry | 2026-07-08 |  |  | UNMATCHED_LOCATION
TA 416 | 52/1-64/0 | 2026-07-12 |  |  | UNMATCHED_LOCATION
TA 418 | 54/4 | 2024-07-11 | 2024-01-09 | -184 | NEGATIVE_DELAY_EXCLUDED |  | nan
TA 418 | 46/14 | 2024-10-11 | 2024-01-07 | -278 | NEGATIVE_DELAY_EXCLUDED |  | nan
TA 418 | 35/06 | 2024-11-13 | 2024-11-05 | -8 | NEGATIVE_DELAY_EXCLUDED |  | nan
TA 418 | 45/2 | 2025-04-01 | 2025-03-28 | -4 | NEGATIVE_DELAY_EXCLUDED |  | nan
TA 418 | 57/0 | 2025-12-20 | 2025-01-16 | -338 | NEGATIVE_DELAY_EXCLUDED |  | nan
TA 418 | 35/6 | 2024-08-21 |  |  | UNMATCHED_LOCATION
TA 418 | 45/02 | 2024-12-20 |  |  | UNMATCHED_LOCATION
TA 418 | 46/1 | 2025-06-30 |  |  | UNMATCHED_LOCATION
TA 418 | 42/0 - 43/0 | 2025-09-28 |  |  | UNMATCHED_LOCATION
TA 418 | 41/0 - 42/0 | 2025-10-06 |  |  | UNMATCHED_LOCATION
TA 418 | 36/0 - 36/1 | 2025-11-03 |  |  | UNMATCHED_LOCATION
TA 418 | 35/0 - 36/0 | 2025-11-17 |  |  | UNMATCHED_LOCATION
TA 418 | 34/0 - 35/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TA 418 | 59/1 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 418 | 40/0 - 41/0 | 2025-12-26 |  |  | UNMATCHED_LOCATION
TA 418 | 33/6 - 34/0 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TA 418 | 33/5 - 33/6 | 2026-01-30 |  |  | UNMATCHED_LOCATION
TA 418 | 33/0 - 33/5 | 2026-02-09 |  |  | UNMATCHED_LOCATION
TA 418 | 39/0-40/0 | 2026-02-10 |  |  | UNMATCHED_LOCATION
TA 418 | 32/0-33/0 | 2026-02-22 |  |  | UNMATCHED_LOCATION
TA 418 | 45/1-46/0 | 2026-03-03 |  |  | UNMATCHED_LOCATION
TA 418 | 43/0 - 44/0 | 2026-03-11 |  |  | UNMATCHED_LOCATION
TA 418 | 45/0 - 45/1 | 2026-03-12 |  |  | UNMATCHED_LOCATION
TA 418 | 44/0-45/0 | 2026-03-18 |  |  | UNMATCHED_LOCATION
TA 418 | 56/0-56/3 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TA 418 | 61/0-62/0 | 2026-04-15 |  |  | UNMATCHED_LOCATION
TA 418 | 63/0-GNTY | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 418 | 55/0-56/0 | 2026-05-03 |  |  | UNMATCHED_LOCATION
TA 418 | 37/0-38/0 | 2026-05-12 |  |  | UNMATCHED_LOCATION
TA 418 | 36/01 - 37/00 | 2026-05-23 |  |  | UNMATCHED_LOCATION
TA 418 | 38/0-39/0 | 2026-05-26 |  |  | UNMATCHED_LOCATION
TA 418 | 52/00 - 53/00 | 2026-06-06 |  |  | UNMATCHED_LOCATION
TA 418 | 51/00 - 52/00 | 2026-06-08 |  |  | UNMATCHED_LOCATION
TA 418 | 56/03 - 57/00 | 2026-06-09 |  |  | UNMATCHED_LOCATION
TA 418 | 54/00 - 55/00 | 2026-06-19 |  |  | UNMATCHED_LOCATION
TA 418 | 53/00 - 54/00 | 2026-06-20 |  |  | UNMATCHED_LOCATION
TA 418 | 57/00 - 58/00 | 2026-06-23 |  |  | UNMATCHED_LOCATION
TA 418 | 48A/0-49/0 | 2026-06-26 |  |  | UNMATCHED_LOCATION
TA 418 | 62/0-63/0 | 2026-06-26 |  |  | UNMATCHED_LOCATION
TA 418 | 59/0 - 60/0 | 2026-06-27 |  |  | UNMATCHED_LOCATION
TA 418 | 58/0 - 59/0 | 2026-06-28 |  |  | UNMATCHED_LOCATION
TA 418 | 60/0-61/0 | 2026-07-04 |  |  | UNMATCHED_LOCATION
TA 418 | 48/0-48A/0 | 2026-07-05 |  |  | UNMATCHED_LOCATION
TA 418 | 47/0-48/0 | 2026-07-12 |  |  | UNMATCHED_LOCATION
TA 418 | 49/0-50/0 | 2026-07-12 |  |  | UNMATCHED_LOCATION
TA 418 | 50/0-51/0 | 2026-07-12 |  |  | UNMATCHED_LOCATION
TA 418 | 46/0-46/7 | 2026-07-21 |  |  | UNMATCHED_LOCATION
TA 419 | 6/9 | 2024-07-14 | 2024-01-06 | -190 | NEGATIVE_DELAY_EXCLUDED
TA 419 | 52/1 | 2026-05-31 | 2026-04-03 | -58 | NEGATIVE_DELAY_EXCLUDED
TA 419 | 83/6 | 2025-05-19 |  |  | UNMATCHED_LOCATION
TA 419 | 8/0 | 2025-07-28 |  |  | UNMATCHED_LOCATION
TA 419 | 46/0 | 2025-08-31 |  |  | UNMATCHED_LOCATION
TA 419 | 43/1 | 2025-11-13 |  |  | UNMATCHED_LOCATION
TA 419 | 36/9 | 2025-11-23 |  |  | UNMATCHED_LOCATION
TA 419 | 83/8 | 2025-11-28 |  |  | UNMATCHED_LOCATION
TA 419 | 84/0 | 2025-12-26 |  |  | UNMATCHED_LOCATION
TA 419 | 63/6 | 2025-12-28 |  |  | UNMATCHED_LOCATION
TA 419 | 63B/6 | 2026-01-02 |  |  | UNMATCHED_LOCATION
TA 419 | 36/3 | 2026-01-09 |  |  | UNMATCHED_LOCATION
TA 419 | 63/3 | 2026-01-17 |  |  | UNMATCHED_LOCATION
TA 419 | 64/0 | 2026-02-01 |  |  | UNMATCHED_LOCATION
TA 419 | 77/0 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TA 419 | 81/0 | 2026-03-29 |  |  | UNMATCHED_LOCATION
TA 419 | 80/0 | 2026-04-25 |  |  | UNMATCHED_LOCATION
TA 419 | 76/2 | 2026-04-28 |  |  | UNMATCHED_LOCATION
TA 419 | 60/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 419 | 84/2 | 2026-05-10 |  |  | UNMATCHED_LOCATION
TA 419 | 69/0 | 2026-05-20 |  |  | UNMATCHED_LOCATION
TA 419 | 54/0 | 2026-05-25 |  |  | UNMATCHED_LOCATION
TA 419 | 68/0 | 2026-05-28 |  |  | UNMATCHED_LOCATION
TA 419 | 95A/0 | 2026-05-28 |  |  | UNMATCHED_LOCATION
TA 419 | 75/0 | 2026-06-01 |  |  | UNMATCHED_LOCATION
TA 419 | 72/0 | 2026-06-05 |  |  | UNMATCHED_LOCATION
TA 419 | 59/0 | 2026-06-23 |  |  | UNMATCHED_LOCATION
TA 419 | 63B/3 | 2026-06-23 |  |  | UNMATCHED_LOCATION
TA 419 | 39/0 | 2026-06-29 |  |  | UNMATCHED_LOCATION
TA 419 | 66/0 | 2026-07-04 |  |  | UNMATCHED_LOCATION
TA 419 | 96/2 | 2026-07-04 |  |  | UNMATCHED_LOCATION
TA 419 | 50/0 | 2026-07-14 |  |  | UNMATCHED_LOCATION
TA 419 | 96/0 | 2026-07-14 |  |  | UNMATCHED_LOCATION
TA 419 | 79/0 | 2026-07-18 |  |  | UNMATCHED_LOCATION
TA 419 | 98/0 | 2026-07-18 |  |  | UNMATCHED_LOCATION
TA 419 | 57/0 | 2026-07-19 |  |  | UNMATCHED_LOCATION
TA 419 | 47/0 | 2026-07-22 |  |  | UNMATCHED_LOCATION
TA 419 | 86/1 | 2026-07-23 |  |  | UNMATCHED_LOCATION
TA 419 | 93C/0 | 2026-07-25 |  |  | UNMATCHED_LOCATION
TA 419 | 51/0 | 2026-07-30 |  |  | UNMATCHED_LOCATION
TA 419 | 82/0 | 2026-07-31 |  |  | UNMATCHED_LOCATION
TA 419 | 99/0 | 2026-08-04 |  |  | UNMATCHED_LOCATION
TA 421 | 30/2 | 2024-12-21 | 2024-12-02 | -19 | NEGATIVE_DELAY_EXCLUDED
TA 421 | 8/11 | 2025-05-22 |  |  | UNMATCHED_LOCATION
TA 421 | 4/16 | 2025-05-31 |  |  | UNMATCHED_LOCATION
TA 421 | 43A/0 | 2025-08-03 |  |  | UNMATCHED_LOCATION
TA 421 | 19/0-20/0 | 2025-10-19 |  |  | UNMATCHED_LOCATION
TA 421 | 18/0-19/0 | 2025-10-21 |  |  | UNMATCHED_LOCATION
TA 421 | 8/0 | 2025-12-05 |  |  | UNMATCHED_LOCATION
TA 421 | 7/0 - 8/0 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TA 421 | Gantry - 1/0 | 2026-02-01 |  |  | UNMATCHED_LOCATION
TA 421 | 8/2 - 8/3 | 2026-02-04 |  |  | UNMATCHED_LOCATION
TA 421 | 1/0-1A/0 | 2026-02-08 |  |  | UNMATCHED_LOCATION
TA 421 | 1A/0 - 1B/0 | 2026-02-11 |  |  | UNMATCHED_LOCATION
TA 421 | 4/12 - 5/0 | 2026-02-12 |  |  | UNMATCHED_LOCATION
TA 421 | 8/0 - 8/1 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TA 421 | 8/1-8/2 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TA 421 | 1C/0 - 2/0 | 2026-02-25 |  |  | UNMATCHED_LOCATION
TA 421 | 5/0 - 6/0 | 2026-03-02 |  |  | UNMATCHED_LOCATION
TA 421 | 3/0-4/0 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TA 421 | 43A/0 - 43A/1 | 2026-06-18 |  |  | UNMATCHED_LOCATION
TA 421 | 43A/1 - 43B/0 | 2026-06-21 |  |  | UNMATCHED_LOCATION
TA 421 | 43B/0 - 44/0 | 2026-06-24 |  |  | UNMATCHED_LOCATION
TA 505 | 177/0 | 2026-05-15 | 2025-12-04 | -162 | NEGATIVE_DELAY_EXCLUDED
TA 505 | 138/0 | 2025-11-29 |  |  | UNMATCHED_LOCATION
TA 505 | 149B/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 505 | 158/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 505 | 148C/0 | 2026-02-21 |  |  | UNMATCHED_LOCATION
TA 505 | 148B/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TA 505 | 157/0 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TA 505 | 144/0 | 2026-03-21 |  |  | UNMATCHED_LOCATION
TA 505 | 143/0 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TA 505 | 134/0 | 2026-04-09 |  |  | UNMATCHED_LOCATION
TA 505 | 129/0 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TA 505 | 133/0 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TA 505 | 129/1 | 2026-04-23 |  |  | UNMATCHED_LOCATION
TA 505 | 182B/0 | 2026-06-20 |  |  | UNMATCHED_LOCATION
TA 505 | 179/3 | 2026-06-30 |  |  | UNMATCHED_LOCATION
TA 510 | 155/1 | 2025-02-17 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 155/4 | 2025-02-22 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 155/3 | 2025-02-25 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 155/5 | 2025-02-27 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 156/0 | 2025-03-12 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 156/1 | 2025-03-13 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 156/3 | 2025-03-16 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 156/4 | 2025-03-25 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 137/0 | 2025-04-27 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 139/4 | 2025-04-28 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 138/2 | 2025-10-05 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 138/3 | 2025-11-27 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 192/7 | 2026-01-21 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 192/12 | 2026-01-25 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 157B/0 | 2026-03-11 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 157A/0 | 2026-03-22 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 157/2 | 2026-03-23 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 192/9 | 2026-04-07 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 193/2 | 2026-04-13 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 193/1 | 2026-04-19 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 193/5 | 2026-04-20 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 139/0 | 2026-04-21 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 193/0 | 2026-04-28 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 193/4 | 2026-04-29 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 192/8 | 2026-05-06 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 167/2 | 2026-05-13 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 157B/1 | 2026-05-16 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 167/3 | 2026-05-17 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 133/0 | 2026-05-18 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 153/0 | 2026-05-20 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 167/4 | 2026-05-20 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 133/1 | 2026-05-23 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 167/1 | 2026-05-26 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 194/0 | 2026-05-27 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 150/2 | 2026-05-31 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 153/1 | 2026-05-31 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 155/0 | 2026-05-31 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 150/4 | 2026-06-06 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 155/2 | 2026-06-06 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 154/0 | 2026-06-10 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 150/3 | 2026-06-11 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 154/1 | 2026-06-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 160/3 | 2026-06-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 150/1 | 2026-06-15 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 154/2 | 2026-06-20 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 148A/0 | 2026-06-25 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 152/1 | 2026-06-25 |  |  | UNMATCHED_LOCATION | FDN
TA 512 | 31/11 | 2025-06-10 |  |  | UNMATCHED_LOCATION
TA 512 | 27/2 | 2025-06-17 |  |  | UNMATCHED_LOCATION
TA 512 | 16/2 | 2025-07-10 |  |  | UNMATCHED_LOCATION
TA 512 | 2/1 | 2025-08-13 |  |  | UNMATCHED_LOCATION
TA 512 | 4/5 | 2025-09-03 |  |  | UNMATCHED_LOCATION
TA 512 | 37/6 | 2025-09-06 |  |  | UNMATCHED_LOCATION
TA 512 | 36/4 | 2025-09-26 |  |  | UNMATCHED_LOCATION
TA 512 | 3/2 | 2025-10-28 |  |  | UNMATCHED_LOCATION
TA 512 | 31/0 | 2025-10-30 |  |  | UNMATCHED_LOCATION
TA 512 | 37/1 | 2025-11-03 |  |  | UNMATCHED_LOCATION
TA 512 | 32/1 | 2025-12-01 |  |  | UNMATCHED_LOCATION
TA 512 | 32/3 | 2025-12-02 |  |  | UNMATCHED_LOCATION
TA 512 | 32/6 | 2025-12-06 |  |  | UNMATCHED_LOCATION
TA 512 | 2A/3 | 2025-12-09 |  |  | UNMATCHED_LOCATION
TA 512 | 4/1 | 2025-12-14 |  |  | UNMATCHED_LOCATION
TA 512 | 32/7 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 512 | 36/0 | 2025-12-26 |  |  | UNMATCHED_LOCATION
TA 512 | 36/1 | 2025-12-30 |  |  | UNMATCHED_LOCATION
TA 512 | 42/0 | 2026-01-11 |  |  | UNMATCHED_LOCATION
TA 512 | 33/1 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TA 512 | 16/3 | 2026-02-07 |  |  | UNMATCHED_LOCATION
TA 512 | 32/8 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TA 512 | 44/0 | 2026-03-09 |  |  | UNMATCHED_LOCATION
TA 512 | 47/0 | 2026-04-08 |  |  | UNMATCHED_LOCATION
TA 512 | 44/1 | 2026-04-15 |  |  | UNMATCHED_LOCATION
TA 512 | 45/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION
TA 512 | 46/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION
TA 512 | 34/1 | 2026-04-29 |  |  | UNMATCHED_LOCATION
TA 512 | 31/10 | 2026-05-21 |  |  | UNMATCHED_LOCATION
TA 512 | 1A/0 | 2026-06-03 |  |  | UNMATCHED_LOCATION
TA 512 | 16/0 | 2026-06-04 |  |  | UNMATCHED_LOCATION
TA 512 | 26/0 | 2026-06-10 |  |  | UNMATCHED_LOCATION
TA 512 | 1/2 | 2026-06-24 |  |  | UNMATCHED_LOCATION
TA 512 | 24/0 | 2026-06-25 |  |  | UNMATCHED_LOCATION
TA 512 | 1/1 | 2026-07-01 |  |  | UNMATCHED_LOCATION
TA 512 | 32/10 | 2026-07-03 |  |  | UNMATCHED_LOCATION
TA 512 | 1/0 | 2026-07-09 |  |  | UNMATCHED_LOCATION
TA 512 | 30/15 | 2026-08-05 |  |  | UNMATCHED_LOCATION
TA 513 | 24/2 | 2025-04-04 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 24/1 | 2025-04-07 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 30/2 | 2025-04-12 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 23/6 | 2025-04-14 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 23/5 | 2025-04-16 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 31/1 | 2025-04-17 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 30/3 | 2025-04-22 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 37/1 | 2025-04-24 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 30/1 | 2025-04-25 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 30/2 | 2025-04-28 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 24/3 | 2025-04-29 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 31/2 | 2025-04-30 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 3/5 | 2025-05-20 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 55/7 | 2025-05-20 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 23/3 | 2025-05-24 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 3/6 | 2025-05-24 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 3/10 | 2025-05-27 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 32B/1 | 2025-05-28 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 21/7 | 2025-06-02 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 21/6 | 2025-06-05 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 23/1 | 2025-06-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 23/3 | 2025-06-09 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 23/2 | 2025-06-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 23/4 | 2025-06-15 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 18/4 | 2025-06-28 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 14/4 | 2025-07-01 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 26/1 | 2025-07-03 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 14/3 | 2025-07-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 14/2 | 2025-07-13 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 56/0 | 2025-07-15 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 15B/4 | 2025-07-21 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 55/0 | 2025-07-24 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 36/3 | 2025-08-20 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 36/4 | 2025-09-01 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 30/0 | 2025-09-19 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 24/0 | 2025-09-24 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 19/0 | 2025-10-01 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 28/0 | 2025-10-05 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 18/0 | 2025-10-06 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 55/1 | 2026-03-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 55/2 | 2026-04-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 55/4 | 2026-05-04 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 52/0 | 2026-05-05 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 52/1 | 2026-05-10 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 52/5 | 2026-05-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 55/3 | 2026-05-15 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 64/2 | 2026-05-16 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 30/0 | 2026-05-17 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 64/5 | 2026-05-19 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 64/3 | 2026-05-21 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 28/1 | 2026-05-22 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 51/3 | 2026-05-23 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 64/4 | 2026-05-25 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 64/6 | 2026-05-29 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 61/2 | 2026-05-30 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 74/9 | 2026-05-30 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 64/1 | 2026-06-01 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 54/1 | 2026-06-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 74/8 | 2026-06-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 55/1 | 2026-06-09 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 62/1 | 2026-06-09 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 61/0 | 2026-06-14 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 74/7 | 2026-06-14 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 51/1 | 2026-06-17 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 61/1 | 2026-06-18 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 51/0 | 2026-06-25 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 54/2 | 2026-06-27 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 44/2 | 2026-07-08 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 46/1 | 2026-07-10 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 36/5 | 2026-07-16 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 43/0 | 2026-07-17 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 45/2 | 2026-07-20 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 45/1 | 2026-08-01 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 42/1 | 2026-08-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 12/4 | 2026-08-09 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 45/0 | 2026-08-11 |  |  | UNMATCHED_LOCATION | S-P
TA 601 | 56/7 | 2026-01-16 | 2025-12-15 | -32 | NEGATIVE_DELAY_EXCLUDED
TA 601 | 50/0 | 2026-04-16 | 2025-06-26 | -294 | NEGATIVE_DELAY_EXCLUDED
TA 601 | 81/2 | 2025-08-07 |  |  | UNMATCHED_LOCATION
TA 601 | 80/4 | 2025-10-27 |  |  | UNMATCHED_LOCATION
TA 601 | 77/8 | 2025-11-13 |  |  | UNMATCHED_LOCATION
TA 601 | 60/8 | 2025-11-23 |  |  | UNMATCHED_LOCATION
TA 601 | 59/1 | 2025-11-29 |  |  | UNMATCHED_LOCATION
TA 601 | 77/6 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 601 | 73/1 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TA 601 | 56/1 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 601 | 73/2 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 601 | 79/1 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TA 601 | 84/6 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 601 | 94/1 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 601 | 99/12 | 2026-01-06 |  |  | UNMATCHED_LOCATION
TA 601 | 83/0 | 2026-01-14 |  |  | UNMATCHED_LOCATION
TA 601 | 78/3 | 2026-02-06 |  |  | UNMATCHED_LOCATION
TA 601 | 50/1 | 2026-02-12 |  |  | UNMATCHED_LOCATION
TA 601 | 89/1 | 2026-03-03 |  |  | UNMATCHED_LOCATION
TA 601 | 90/0 | 2026-03-18 |  |  | UNMATCHED_LOCATION
TA 601 | 53/3 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TA 601 | 70/4 | 2026-04-16 |  |  | UNMATCHED_LOCATION
TA 601 | 70/3 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 601 | 66/1 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 601 | 48/7 | 2026-05-10 |  |  | UNMATCHED_LOCATION
TA 601 | 69/1 | 2026-05-20 |  |  | UNMATCHED_LOCATION
TA 601 | 68/2 | 2026-05-23 |  |  | UNMATCHED_LOCATION
TA 601 | 68/0 | 2026-05-30 |  |  | UNMATCHED_LOCATION
TA 601 | 72/1 | 2026-06-01 |  |  | UNMATCHED_LOCATION
TA 601 | 73/0 | 2026-06-05 |  |  | UNMATCHED_LOCATION
TA 601 | 75/2 | 2026-06-07 |  |  | UNMATCHED_LOCATION
TA 601 | 75/3 | 2026-06-09 |  |  | UNMATCHED_LOCATION
TA 601 | 75/1 | 2026-06-12 |  |  | UNMATCHED_LOCATION
TA 601 | 77/5 | 2026-06-15 |  |  | UNMATCHED_LOCATION
TA 601 | 60/4 | 2026-06-19 |  |  | UNMATCHED_LOCATION
TA 601 | 48/0 | 2026-06-22 |  |  | UNMATCHED_LOCATION
TA 601 | 51/4 | 2026-06-23 |  |  | UNMATCHED_LOCATION
TA 601 | 102/0 | 2026-06-25 |  |  | UNMATCHED_LOCATION
TA 601 | 51/5 | 2026-06-26 |  |  | UNMATCHED_LOCATION
TA 601 | 51/3 | 2026-07-08 |  |  | UNMATCHED_LOCATION
TA 601 | 52/3 | 2026-07-10 |  |  | UNMATCHED_LOCATION
TA 601 | 71/0 | 2026-07-10 |  |  | UNMATCHED_LOCATION
TA 601 | 63/2 | 2026-07-13 |  |  | UNMATCHED_LOCATION
TA 601 | 58/0 | 2026-07-15 |  |  | UNMATCHED_LOCATION
TA 601 | 98/0 | 2026-07-15 |  |  | UNMATCHED_LOCATION
TA 601 | 76/0 | 2026-07-16 |  |  | UNMATCHED_LOCATION
TA 601 | 101/4 | 2026-07-17 |  |  | UNMATCHED_LOCATION
TA 601 | 49/3 | 2026-07-17 |  |  | UNMATCHED_LOCATION
TA 601 | 65/2 | 2026-07-18 |  |  | UNMATCHED_LOCATION
TA 601 | 78/1 | 2026-07-21 |  |  | UNMATCHED_LOCATION
TA 601 | 53/6 | 2026-07-23 |  |  | UNMATCHED_LOCATION
TA 601 | 101/9 | 2026-07-24 |  |  | UNMATCHED_LOCATION
TA 601 | 78/0 | 2026-07-26 |  |  | UNMATCHED_LOCATION
TA 601 | 52/4 | 2026-07-27 |  |  | UNMATCHED_LOCATION
TA 601 | 63/1 | 2026-07-27 |  |  | UNMATCHED_LOCATION
TA 601 | 96/8 | 2026-07-27 |  |  | UNMATCHED_LOCATION
TA 601 | 80/2 | 2026-07-28 |  |  | UNMATCHED_LOCATION
TA 601 | 96/7 | 2026-07-30 |  |  | UNMATCHED_LOCATION
TA 601 | 97/4 | 2026-08-01 |  |  | UNMATCHED_LOCATION
TA 601 | 82/2 | 2026-08-03 |  |  | UNMATCHED_LOCATION
TA 601 | 97/3 | 2026-08-03 |  |  | UNMATCHED_LOCATION
TA 601 | 96/4 | 2026-08-06 |  |  | UNMATCHED_LOCATION
TA 601 | 101/8 | 2026-08-08 |  |  | UNMATCHED_LOCATION
TA 601 | 63/3 | 2026-08-09 |  |  | UNMATCHED_LOCATION
TA 601 | 96/5 | 2026-08-09 |  |  | UNMATCHED_LOCATION
TA 601 | 96/6 | 2026-08-11 |  |  | UNMATCHED_LOCATION
TA 601 | 49/5 | 2026-08-12 |  |  | UNMATCHED_LOCATION
TB 408 | 0 | 2023-10-01 |  |  | UNMATCHED_LOCATION
TB 408 | 1 | 2024-09-01 |  |  | UNMATCHED_LOCATION
TB 408 | 2 | 2024-11-01 |  |  | UNMATCHED_LOCATION
TB 408 | 3 | 2024-11-01 |  |  | UNMATCHED_LOCATION
TB 408 | 4 | 2024-11-01 |  |  | UNMATCHED_LOCATION
TB 408 | 5 | 2024-12-01 |  |  | UNMATCHED_LOCATION
TB 501 | 8D/0A | 2025-12-07 | 2025-12-04 | -3 | NEGATIVE_DELAY_EXCLUDED | 220kV | 220kV
TB 501 | 6/0 | 2026-02-19 | 2026-02-17 | -2 | NEGATIVE_DELAY_EXCLUDED | 132kV | 132kV
TB 501 | 2/0 | 2026-06-19 | 2026-06-17 | -2 | NEGATIVE_DELAY_EXCLUDED | 132kV | 132kV
TB 501 | 1/0 | 2026-06-23 | 2026-06-20 | -3 | NEGATIVE_DELAY_EXCLUDED | 132kV | 132kV
TB 501 | SC-2 | 2026-06-19 |  |  | UNMATCHED_LOCATION | 132kV
TB 501 | SC-1 | 2026-07-24 |  |  | UNMATCHED_LOCATION | 132kV
TB 507 | 71/2 | 2025-10-30 | 2025-01-14 | -289 | NEGATIVE_DELAY_EXCLUDED | MAIN | MAIN
TB 507 | 10/9 | 2026-06-27 | 2025-07-10 | -352 | NEGATIVE_DELAY_EXCLUDED | MAIN | MAIN
TB 507 | 66/2 | 2025-03-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 64/3 | 2025-03-07 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 96/2 | 2025-03-07 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 64/4 | 2025-03-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 99/1 | 2025-03-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 66/3 | 2025-03-11 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 64/6 | 2025-03-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 64/5 | 2025-03-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 71/1 | 2025-04-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 91/2 | 2025-04-16 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 51/2 | 2025-04-17 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 95/2 | 2025-04-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 51/3 | 2025-04-23 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 99/2 | 2025-04-25 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 104B/1 | 2025-04-29 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 62/4 | 2025-04-29 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 105/0 | 2025-05-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 62/5 | 2025-05-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 96/0 | 2025-06-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 106/0 | 2025-07-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 125/1 | 2025-07-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 125/0 | 2025-07-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 94/0 | 2025-07-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 99/3 | 2025-07-29 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 99/0 | 2025-08-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 99/4 | 2025-08-22 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 63/1 | 2025-08-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 56/4 | 2025-08-26 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 56/2 | 2025-08-27 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 56/5 | 2025-08-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 99A/0 | 2025-08-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 57/0 | 2025-09-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 59/0 | 2025-09-12 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 64/0 | 2025-09-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 58/0 | 2025-09-17 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 125/2 | 2025-09-18 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 56/1 | 2025-09-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 48/0 | 2025-09-25 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 71/0 | 2025-11-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 98B/2 | 2025-12-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 117/0 | 2025-12-13 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 104A/0 | 2025-12-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 124/0 | 2025-12-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 122/2 | 2026-01-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 69/3 | 2026-01-15 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 108/0 | 2026-01-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 10/3 | 2026-01-23 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 109/0 | 2026-01-23 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 7/0 | 2026-02-11 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 1/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 117/2 | 2026-02-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 6/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 157/0 | 2026-03-04 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 98B/1 | 2026-03-11 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 2/0 | 2026-03-13 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 103/0 | 2026-03-19 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5/2 | 2026-03-31 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5/1 | 2026-04-02 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 3/1 | 2026-04-04 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5/0 | 2026-04-12 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 3/3 | 2026-04-18 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 2/0 | 2026-05-02 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 155/0 | 2026-05-03 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 154/1B | 2026-05-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 154/2B | 2026-05-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 154/1A | 2026-05-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 154/2A | 2026-05-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 13/2 | 2026-05-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 4/0 | 2026-05-15 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 1/0 | 2026-05-27 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 27/0 | 2026-05-27 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 1A/0 | 2026-05-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 3A/1 | 2026-05-31 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5/3 | 2026-06-03 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 3A/0 | 2026-06-05 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 3B/0 | 2026-06-15 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5/0 | 2026-06-15 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 56/3 | 2026-06-17 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 107/1 | 2026-06-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 43/0 | 2026-06-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5A/0 | 2026-06-29 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 121/0 | 2026-06-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 42/0 | 2026-06-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 41/3 | 2026-07-04 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 42/1 | 2026-07-11 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5/6 | 2026-07-11 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 7/0 | 2026-07-16 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 41/1 | 2026-07-17 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 44/0 | 2026-07-18 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 122/1 | 2026-07-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 122/0 | 2026-07-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 102/0 | 2026-07-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 39/4 | 2026-07-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 2A/0 | 2026-07-30 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 45/3 | 2026-07-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5A/0 | 2026-07-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5B/0 | 2026-08-03 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 39/3 | 2026-08-04 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 40/0 | 2026-08-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 40/1 | 2026-08-12 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5C/0 | 2026-08-12 |  |  | UNMATCHED_LOCATION | MAIN
TB 605 | 18/0 | 2025-10-16 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 22/0 | 2025-10-31 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 74/0 | 2025-11-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 72/0 | 2025-11-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 17/0 | 2025-11-23 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 20/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP116 | 2025-11-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 40/0 | 2025-12-03 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 23/0 | 2025-12-09 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 29/0 | 2025-12-10 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 85/1 | 2025-12-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 106/1 | 2025-12-17 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 102/1 | 2025-12-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 138/2 | 2025-12-31 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 137/2 | 2026-01-10 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 152/2 | 2026-01-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP138 | 2026-01-20 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 153/0 | 2026-02-05 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP139 | 2026-02-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP130 | 2026-02-12 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP92 | 2026-02-13 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP91 | 2026-02-27 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP159 | 2026-02-28 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP149 | 2026-03-10 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 67/2 | 2026-03-13 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP127 | 2026-03-15 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP148 | 2026-03-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP152 | 2026-03-26 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP108 | 2026-03-28 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 56/3 | 2026-03-31 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP125 | 2026-04-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 65/2 | 2026-04-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP109 | 2026-04-12 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP126 | 2026-04-15 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP1 | 2026-04-18 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP61 | 2026-04-21 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP165 | 2026-04-22 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP86 | 2026-04-23 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 56/2 | 2026-04-25 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP59 | 2026-04-27 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP41 | 2026-04-30 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP6 | 2026-04-30 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP64 | 2026-05-01 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP144 | 2026-05-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 61/1 | 2026-05-08 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 57/1 | 2026-05-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP161 | 2026-05-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP163 | 2026-05-11 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 56/4 | 2026-05-13 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 62/2 | 2026-05-14 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP110 | 2026-05-14 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP57 | 2026-05-15 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 159/3 | 2026-05-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 50A/2 | 2026-05-17 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP162 | 2026-05-17 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 62/1 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP128 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP63 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 159/2 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 57/2 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP112 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 159/1 | 2026-05-22 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 60/1 | 2026-05-22 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 143/1 | 2026-05-23 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 50A/1 | 2026-05-23 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP113 | 2026-05-23 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP158 | 2026-05-23 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP7 | 2026-05-24 |  |  | UNMATCHED_LOCATION | LILO
TB 605 | AP84 | 2026-05-24 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP55 | 2026-05-25 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP42 | 2026-05-26 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 65/5 | 2026-05-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP105 | 2026-05-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP168 | 2026-05-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP174 | 2026-05-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP167 | 2026-05-31 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP81 | 2026-05-31 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 65/3 | 2026-06-03 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 50A/4 | 2026-06-06 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP173 | 2026-06-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP58 | 2026-06-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 143/2 | 2026-06-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 42/1 | 2026-06-09 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP175 | 2026-06-10 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP78 | 2026-06-10 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 77/3 | 2026-06-12 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 37/2 | 2026-06-14 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 47/3 | 2026-06-15 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP53 | 2026-06-17 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 180/1 | 2026-06-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 50A/5 | 2026-06-19 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 52/1 | 2026-06-20 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 8/1 | 2026-06-22 |  |  | UNMATCHED_LOCATION | LILO
TB 605 | AP62 | 2026-06-22 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP48 | 2026-06-23 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP6 | 2026-06-24 |  |  | UNMATCHED_LOCATION | LILO
TB 605 | 171/1 | 2026-06-25 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP151 | 2026-06-25 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 56/1 | 2026-06-26 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP180 | 2026-06-27 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP8 | 2026-06-27 |  |  | UNMATCHED_LOCATION | LILO
TB 605 | AP5 | 2026-06-30 |  |  | UNMATCHED_LOCATION | LILO
TB 605 | AP176 | 2026-07-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP51 | 2026-07-13 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP8 | 2026-07-27 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | AP182 | 2026-07-31 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | AP4 | 2026-08-11 |  |  | UNMATCHED_LOCATION | LILO
TB 605 | AP9 | 2026-08-11 |  |  | UNMATCHED_LOCATION | LILO
TB 608 | 75/5 | 2025-11-15 |  |  | UNMATCHED_LOCATION
TB 608 | 34/3 | 2025-11-18 |  |  | UNMATCHED_LOCATION
TB 608 | 101/0 | 2025-11-19 |  |  | UNMATCHED_LOCATION
TB 608 | 33/2 | 2025-11-22 |  |  | UNMATCHED_LOCATION
TB 608 | 29/0 | 2025-11-25 |  |  | UNMATCHED_LOCATION
TB 608 | 100/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TB 608 | 109/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TB 608 | 71/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TB 608 | 29/1 | 2025-12-02 |  |  | UNMATCHED_LOCATION
TB 608 | 5/0 | 2025-12-10 |  |  | UNMATCHED_LOCATION
TB 608 | 108/0 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TB 608 | 75/4 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TB 608 | 99/0 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TB 608 | 102/0 | 2025-12-19 |  |  | UNMATCHED_LOCATION
TB 608 | 84/0 | 2025-12-19 |  |  | UNMATCHED_LOCATION
TB 608 | 111/1 | 2025-12-21 |  |  | UNMATCHED_LOCATION
TB 608 | 83/0 | 2025-12-21 |  |  | UNMATCHED_LOCATION
TB 608 | 91/0 | 2025-12-21 |  |  | UNMATCHED_LOCATION
TB 608 | 93/0 | 2025-12-21 |  |  | UNMATCHED_LOCATION
TB 608 | 34/1 | 2025-12-22 |  |  | UNMATCHED_LOCATION
TB 608 | 25/1 | 2025-12-23 |  |  | UNMATCHED_LOCATION
TB 608 | 4/1 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TB 608 | 91/1 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TB 608 | 91/2 | 2025-12-28 |  |  | UNMATCHED_LOCATION
TB 608 | 114/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TB 608 | 86/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TB 608 | 41/2 | 2026-01-02 |  |  | UNMATCHED_LOCATION
TB 608 | 11/2 | 2026-01-03 |  |  | UNMATCHED_LOCATION
TB 608 | 97/0 | 2026-01-09 |  |  | UNMATCHED_LOCATION
TB 608 | 113/0 | 2026-01-11 |  |  | UNMATCHED_LOCATION
TB 608 | 91/5 | 2026-01-12 |  |  | UNMATCHED_LOCATION
TB 608 | 110/0 | 2026-01-13 |  |  | UNMATCHED_LOCATION
TB 608 | 76/0 | 2026-01-15 |  |  | UNMATCHED_LOCATION
TB 608 | 69/4 | 2026-01-18 |  |  | UNMATCHED_LOCATION
TB 608 | 75/1 | 2026-01-19 |  |  | UNMATCHED_LOCATION
TB 608 | 11/1 | 2026-01-24 |  |  | UNMATCHED_LOCATION
TB 608 | 123/2 | 2026-01-25 |  |  | UNMATCHED_LOCATION
TB 608 | 129/1 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TB 608 | 34/2 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TB 608 | 132/1 | 2026-01-29 |  |  | UNMATCHED_LOCATION
TB 608 | 91/7 | 2026-01-29 |  |  | UNMATCHED_LOCATION
TB 608 | 96/0 | 2026-01-30 |  |  | UNMATCHED_LOCATION
TB 608 | 128/0 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TB 608 | 131/0 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TB 608 | 75/2 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TB 608 | 91/4 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TB 608 | 59/1 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TB 608 | 73/6 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TB 608 | 76/1 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TB 608 | 96/1 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TB 608 | 104/0 | 2026-02-08 |  |  | UNMATCHED_LOCATION
TB 608 | 126/0 | 2026-02-10 |  |  | UNMATCHED_LOCATION
TB 608 | 72/7 | 2026-02-11 |  |  | UNMATCHED_LOCATION
TB 608 | 95/3 | 2026-02-14 |  |  | UNMATCHED_LOCATION
TB 608 | 129/2 | 2026-02-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6/1 | 2026-02-18 |  |  | UNMATCHED_LOCATION
TB 608 | 95/0 | 2026-02-18 |  |  | UNMATCHED_LOCATION
TB 608 | 131/1 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TB 608 | 44/0 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TB 608 | 30/0 | 2026-02-20 |  |  | UNMATCHED_LOCATION
TB 608 | 10/3 | 2026-02-22 |  |  | UNMATCHED_LOCATION
TB 608 | 124/0 | 2026-02-22 |  |  | UNMATCHED_LOCATION
TB 608 | 127/0 | 2026-02-25 |  |  | UNMATCHED_LOCATION
TB 608 | 132/2 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TB 608 | 132/3 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TB 608 | 31/0 | 2026-03-06 |  |  | UNMATCHED_LOCATION
TB 608 | 35/0 | 2026-03-08 |  |  | UNMATCHED_LOCATION
TB 608 | 10/1 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TB 608 | 129/0 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TB 608 | 130/0 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TB 608 | 82/2 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TB 608 | 82/1 | 2026-03-11 |  |  | UNMATCHED_LOCATION
TB 608 | 27/0 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TB 608 | 125/0 | 2026-03-19 |  |  | UNMATCHED_LOCATION
TB 608 | 6/0 | 2026-03-28 |  |  | UNMATCHED_LOCATION
TB 608 | 7/0 | 2026-03-30 |  |  | UNMATCHED_LOCATION
TB 608 | 34/0 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TB 608 | 7/2 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TB 608 | 9/0 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TB 608 | 107/1 | 2026-04-19 |  |  | UNMATCHED_LOCATION
TB 608 | 7/1 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TB 608 | 106/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TB 608 | 1/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TB 608 | 38/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TB 608 | 61/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TB 608 | 105/0 | 2026-05-07 |  |  | UNMATCHED_LOCATION
TB 608 | 39/0 | 2026-05-12 |  |  | UNMATCHED_LOCATION
TB 608 | 3/0 | 2026-05-17 |  |  | UNMATCHED_LOCATION
TB 608 | 4/0 | 2026-05-24 |  |  | UNMATCHED_LOCATION
TB 608 | 18/0 | 2026-05-26 |  |  | UNMATCHED_LOCATION
TB 608 | 91/9 | 2026-06-18 |  |  | UNMATCHED_LOCATION
TB 608 | 5/1 | 2026-06-21 |  |  | UNMATCHED_LOCATION
TB 608 | 118/0 | 2026-06-30 |  |  | UNMATCHED_LOCATION
TB 608 | 42/0 | 2026-06-30 |  |  | UNMATCHED_LOCATION
TB 608 | 73/5 | 2026-07-10 |  |  | UNMATCHED_LOCATION
TB 608 | 119/0 | 2026-07-19 |  |  | UNMATCHED_LOCATION
TB 608 | 14/0 | 2026-07-27 |  |  | UNMATCHED_LOCATION
TB 608 | 62/3 | 2026-07-29 |  |  | UNMATCHED_LOCATION
TB 608 | 20/1 | 2026-07-31 |  |  | UNMATCHED_LOCATION
TB 608 | 68/0 | 2026-07-31 |  |  | UNMATCHED_LOCATION
TB 608 | 37/0 | 2026-08-04 |  |  | UNMATCHED_LOCATION

## Delay Phase - Project
Delay Phase - Project
Project | Phase | Foundation Bucket Start % | Foundation Bucket End % | Foundation Count | Matched Count | Match % | Median Delay Days | Average Delay Days | P90 Delay Days | Negative Excluded | Unmatched | Scope Total | Phase Foundations % of Scope | Phase Start Date | Phase End Date | Phase Duration Days | Monsoon Overlap | Monsoon Overlap Days | Monsoon Foundation Count | Source Type | Parser Modes | Coverage Status | Scope Source | Scope Report Date
TA 413 | 0-20 | 0 | 20 | 63 | 63 | 100 | 341 | 300.2063 | 491.6 | 0 | 0 | 316 | 19.94 | 2024-06-06 | 2024-09-06 | 93 | Yes | 93 | 63 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 413 | 20-40 | 20 | 40 | 63 | 57 | 90.48 | 299 | 243.9474 | 402.2 | 0 | 6 | 316 | 19.94 | 2024-09-06 | 2024-10-25 | 50 | Yes | 25 | 34 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 413 | 40-60 | 40 | 60 | 63 | 62 | 98.41 | 101.5 | 162.9677 | 310.5 | 0 | 1 | 316 | 19.94 | 2024-10-25 | 2025-01-03 | 71 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 413 | 60-80 | 60 | 80 | 63 | 63 | 100 | 213.5 | 203.1613 | 287.8 | 1 | 0 | 316 | 19.94 | 2025-01-03 | 2025-02-26 | 55 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 413 | 80-100+ | 80 | 100 | 62 | 61 | 98.39 | 163 | 163.2459 | 219 | 0 | 1 | 316 | 19.62 | 2025-02-27 | 2026-03-05 | 372 | Yes | 122 | 6 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 414 | 0-20 | 0 | 20 | 70 | 68 | 97.14 | 345 | 351.6119 | 459.4 | 1 | 2 | 352 | 19.89 | 2024-05-25 | 2025-04-05 | 316 | Yes | 122 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 414 | 20-40 | 20 | 40 | 70 | 68 | 97.14 | 136 | 154.0735 | 290.4 | 0 | 2 | 352 | 19.89 | 2025-04-06 | 2025-12-11 | 250 | Yes | 122 | 6 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 414 | 40-60 | 40 | 60 | 71 | 64 | 90.14 | 47 | 56.4062 | 104.9 | 0 | 7 | 352 | 20.17 | 2025-12-11 | 2026-01-21 | 42 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 414 | 60-80 | 60 | 80 | 70 | 56 | 80 | 50 | 58.2143 | 123 | 0 | 14 | 352 | 19.89 | 2026-01-22 | 2026-03-22 | 60 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 414 | 80-100+ | 80 | 100 | 54 | 24 | 44.44 | 34 | 34.7917 | 61.2 | 0 | 30 | 352 | 15.34 | 2026-03-24 | 2026-06-26 | 95 | Yes | 26 | 16 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 416 | 0-20 | 0 | 20 | 60 | 60 | 100 | 160 | 175.4167 | 273.5 | 0 | 0 | 302 | 19.87 | 2024-05-06 | 2024-09-22 | 140 | Yes | 114 | 54 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-16
TA 416 | 20-40 | 20 | 40 | 60 | 60 | 100 | 148.5 | 151.0833 | 237.1 | 0 | 0 | 302 | 19.87 | 2024-09-22 | 2024-10-26 | 35 | Yes | 9 | 15 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-16
TA 416 | 40-60 | 40 | 60 | 61 | 61 | 100 | 106 | 107.5082 | 153 | 0 | 0 | 302 | 20.2 | 2024-10-26 | 2024-12-09 | 45 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-16
TA 416 | 60-80 | 60 | 80 | 60 | 60 | 100 | 148.5 | 181.3333 | 333.2 | 0 | 0 | 302 | 19.87 | 2024-12-09 | 2025-01-31 | 54 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-16
TA 416 | 80-100+ | 80 | 100 | 90 | 62 | 68.89 | 139 | 149.3279 | 245 | 1 | 28 | 302 | 29.8 | 2025-01-31 | 2026-07-12 | 528 | Yes | 164 | 5 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-16
TA 418 | 0-20 | 0 | 20 | 25 | 24 | 96 | 167 | 187.087 | 304 | 1 | 1 | 127 | 19.69 | 2024-01-05 | 2024-09-12 | 252 | Yes | 104 | 23 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-21
TA 418 | 20-40 | 20 | 40 | 25 | 24 | 96 | 82 | 121.4545 | 219.3 | 2 | 1 | 127 | 19.69 | 2024-09-16 | 2025-02-01 | 139 | Yes | 15 | 3 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-21
TA 418 | 40-60 | 40 | 60 | 26 | 26 | 100 | 124 | 135.76 | 234.8 | 1 | 0 | 127 | 20.47 | 2025-02-03 | 2025-05-15 | 102 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-21
TA 418 | 60-80 | 60 | 80 | 25 | 24 | 96 | 75.5 | 87.4583 | 165.3 | 0 | 1 | 127 | 19.69 | 2025-05-19 | 2025-07-03 | 46 | Yes | 33 | 20 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-21
TA 418 | 80-100+ | 80 | 100 | 66 | 27 | 40.91 | 96 | 95.9231 | 161 | 1 | 39 | 127 | 51.97 | 2025-07-05 | 2026-07-21 | 382 | Yes | 139 | 33 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-21
TA 419 | 0-20 | 0 | 20 | 66 | 66 | 100 | 179 | 203.8923 | 327 | 1 | 0 | 331 | 19.94 | 2024-05-24 | 2024-10-25 | 155 | Yes | 122 | 50 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-11
TA 419 | 20-40 | 20 | 40 | 66 | 66 | 100 | 224.5 | 209.303 | 298 | 0 | 0 | 331 | 19.94 | 2024-10-25 | 2025-04-28 | 186 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-11
TA 419 | 40-60 | 40 | 60 | 66 | 63 | 95.45 | 73 | 112.8254 | 230 | 0 | 3 | 331 | 19.94 | 2025-04-29 | 2025-12-26 | 242 | Yes | 122 | 20 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-11
TA 419 | 60-80 | 60 | 80 | 66 | 61 | 92.42 | 25.5 | 46.8667 | 117.1 | 1 | 5 | 331 | 19.94 | 2025-12-26 | 2026-06-13 | 170 | Yes | 13 | 10 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-11
TA 419 | 80-100+ | 80 | 100 | 21 | 10 | 47.62 | 15 | 14 | 24.5 | 0 | 11 | 331 | 6.34 | 2026-06-18 | 2026-08-04 | 48 | Yes | 48 | 21 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-11
TA 421 | 0-20 | 0 | 20 | 61 | 61 | 100 | 87 | 91.4098 | 174 | 0 | 0 | 309 | 19.74 | 2024-05-22 | 2024-09-20 | 122 | Yes | 112 | 60 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-11
TA 421 | 20-40 | 20 | 40 | 62 | 62 | 100 | 99 | 128.0492 | 291 | 1 | 0 | 309 | 20.06 | 2024-09-20 | 2024-12-23 | 95 | Yes | 11 | 5 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-11
TA 421 | 40-60 | 40 | 60 | 62 | 62 | 100 | 98 | 118.2419 | 278.3 | 0 | 0 | 309 | 20.06 | 2024-12-23 | 2025-02-16 | 56 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-11
TA 421 | 60-80 | 60 | 80 | 62 | 62 | 100 | 124.5 | 121.7581 | 214.2 | 0 | 0 | 309 | 20.06 | 2025-02-16 | 2025-05-20 | 94 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-11
TA 421 | 80-100+ | 80 | 100 | 72 | 54 | 75 | 140 | 130.6296 | 182 | 0 | 18 | 309 | 23.3 | 2025-05-20 | 2026-06-24 | 401 | Yes | 146 | 39 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-11
TA 505 | 0-20 | 0 | 20 | 75 | 75 | 100 | 142 | 180.7867 | 308.8 | 0 | 0 | 379 | 19.79 | 2024-03-28 | 2025-01-02 | 281 | Yes | 122 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-29
TA 505 | 20-40 | 20 | 40 | 76 | 76 | 100 | 222 | 224.1974 | 366 | 0 | 0 | 379 | 20.05 | 2025-01-04 | 2025-03-30 | 86 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-29
TA 505 | 40-60 | 40 | 60 | 76 | 76 | 100 | 209.5 | 217.6184 | 349 | 0 | 0 | 379 | 20.05 | 2025-03-31 | 2025-05-16 | 47 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-29
TA 505 | 60-80 | 60 | 80 | 76 | 76 | 100 | 122 | 142.1184 | 289.5 | 0 | 0 | 379 | 20.05 | 2025-05-17 | 2025-11-19 | 187 | Yes | 122 | 28 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-29
TA 505 | 80-100+ | 80 | 100 | 75 | 62 | 82.67 | 18 | 27.4918 | 58 | 1 | 13 | 379 | 19.79 | 2025-11-20 | 2026-06-30 | 223 | Yes | 30 | 4 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-29
TA 510 | 0-20 | 0 | 20 | 58 | 45 | 77.59 | 104 | 177.2444 | 389.2 | 0 | 13 | 293 | 19.8 | 2025-02-17 | 2026-02-12 | 361 | Yes | 122 | 5 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 510 | 20-40 | 20 | 40 | 37 | 4 | 10.81 | 20.5 | 32.75 | 64.5 | 0 | 33 | 293 | 12.63 | 2026-02-14 | 2026-06-25 | 132 | Yes | 25 | 10 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 512 | 0-20 | 0 | 20 | 63 | 63 | 100 | 221 | 220.4921 | 311.8 | 0 | 0 | 319 | 19.75 | 2025-02-23 | 2025-05-15 | 82 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 512 | 20-40 | 20 | 40 | 64 | 62 | 96.88 | 215.5 | 212.7903 | 285.9 | 0 | 2 | 319 | 20.06 | 2025-05-17 | 2025-07-21 | 66 | Yes | 51 | 51 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 512 | 40-60 | 40 | 60 | 64 | 61 | 95.31 | 165 | 188.6885 | 337 | 0 | 3 | 319 | 20.06 | 2025-07-22 | 2025-10-16 | 87 | Yes | 71 | 56 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 512 | 60-80 | 60 | 80 | 64 | 57 | 89.06 | 124 | 143.1228 | 244.8 | 0 | 7 | 319 | 20.06 | 2025-10-17 | 2025-12-16 | 61 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 512 | 80-100+ | 80 | 100 | 57 | 40 | 70.18 | 79.5 | 101.125 | 185.2 | 0 | 17 | 319 | 17.87 | 2025-12-16 | 2026-08-05 | 233 | Yes | 66 | 11 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 513 | 0-20 | 0 | 20 | 109 | 33 | 30.28 | 169 | 149.5152 | 210.4 | 0 | 76 | 619 | 17.61 | 2025-03-28 | 2026-08-11 | 502 | Yes | 194 | 49 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-06-22
TA 601 | 0-20 | 0 | 20 | 58 | 44 | 75.86 | 39 | 65.093 | 137.4 | 1 | 14 | 292 | 19.86 | 2025-08-07 | 2026-01-24 | 171 | Yes | 55 | 4 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 601 | 20-40 | 20 | 40 | 58 | 49 | 84.48 | 24 | 44.5208 | 97 | 1 | 9 | 292 | 19.86 | 2026-01-26 | 2026-05-10 | 105 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 601 | 40-60 | 40 | 60 | 59 | 31 | 52.54 | 16 | 18.0645 | 38 | 0 | 28 | 292 | 20.21 | 2026-05-13 | 2026-07-26 | 75 | Yes | 56 | 51 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TA 601 | 60-80 | 60 | 80 | 14 | 0 | 0 |  |  |  | 0 | 14 | 292 | 4.79 | 2026-07-27 | 2026-08-12 | 17 | Yes | 17 | 14 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TB 408 | 0-20 | 0 | 20 | 6 | 0 | 0 |  |  |  | 0 | 6 | 485 | 1.24 | 2023-10-01 | 2024-12-01 | 428 | Yes | 122 | 1 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-30
TB 501 | 0-20 | 0 | 20 | 47 | 47 | 100 | 118 | 124.8298 | 183 | 0 | 0 | 238 | 19.75 | 2024-08-12 | 2024-11-15 | 96 | Yes | 50 | 10 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-30
TB 501 | 20-40 | 20 | 40 | 48 | 48 | 100 | 63.5 | 71.5625 | 110.6 | 0 | 0 | 238 | 20.17 | 2024-11-15 | 2025-01-10 | 57 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-30
TB 501 | 40-60 | 40 | 60 | 47 | 47 | 100 | 61 | 72.0426 | 128.8 | 0 | 0 | 238 | 19.75 | 2025-01-12 | 2025-04-15 | 94 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-30
TB 501 | 60-80 | 60 | 80 | 48 | 48 | 100 | 40 | 45.3958 | 82.5 | 0 | 0 | 238 | 20.17 | 2025-04-17 | 2025-10-17 | 184 | Yes | 122 | 18 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-30
TB 501 | 80-100+ | 80 | 100 | 45 | 43 | 95.56 | 13 | 14.8718 | 26.6 | 4 | 2 | 238 | 18.91 | 2025-10-23 | 2026-07-24 | 275 | Yes | 54 | 4 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-07-30
TB 507 | 0-20 | 0 | 20 | 111 | 91 | 81.98 | 143 | 166.7143 | 356 | 0 | 20 | 556 | 19.96 | 2025-01-17 | 2025-07-21 | 186 | Yes | 51 | 51 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TB 507 | 20-40 | 20 | 40 | 111 | 95 | 85.59 | 59 | 79.3723 | 138.4 | 1 | 16 | 556 | 19.96 | 2025-07-21 | 2025-11-12 | 115 | Yes | 72 | 96 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TB 507 | 40-60 | 40 | 60 | 111 | 79 | 71.17 | 69 | 72.2152 | 130.2 | 0 | 32 | 556 | 19.96 | 2025-11-14 | 2026-05-27 | 195 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TB 507 | 60-80 | 60 | 80 | 44 | 16 | 36.36 | 25 | 24.6667 | 41.6 | 1 | 28 | 556 | 7.91 | 2026-05-30 | 2026-08-12 | 75 | Yes | 73 | 41 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TB 605 | 0-20 | 0 | 20 | 104 | 91 | 87.5 | 94 | 109.033 | 179 | 0 | 13 | 523 | 19.89 | 2025-08-11 | 2025-12-26 | 138 | Yes | 51 | 4 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TB 605 | 20-40 | 20 | 40 | 105 | 95 | 90.48 | 65 | 69.4737 | 117.8 | 0 | 10 | 523 | 20.08 | 2025-12-26 | 2026-03-09 | 74 | No | 0 | 0 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TB 605 | 40-60 | 40 | 60 | 104 | 51 | 49.04 | 22 | 29.6275 | 63 | 0 | 53 | 523 | 19.89 | 2026-03-10 | 2026-06-03 | 86 | Yes | 3 | 2 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TB 605 | 60-80 | 60 | 80 | 48 | 22 | 45.83 | 13.5 | 19.8182 | 46.3 | 0 | 26 | 523 | 9.18 | 2026-06-03 | 2026-08-11 | 70 | Yes | 70 | 48 | detail |  | OK_DETAIL | status_quantity_primary_latest | 2026-08-12
TB 608 | 0-20 | 0 | 20 | 94 | 45 | 47.87 | 133 | 128.2222 | 190 | 0 | 49 | 472 | 19.92 | 2025-10-18 | 2026-02-10 | 116 | No | 0 | 0 | detail |  | DETAIL_STATUS_MISMATCH | status_quantity_primary_latest | 2026-08-11
TB 608 | 20-40 | 20 | 40 | 65 | 18 | 27.69 | 77 | 88.9444 | 146 | 0 | 47 | 472 | 13.77 | 2026-02-10 | 2026-08-04 | 176 | Yes | 65 | 12 | detail |  | DETAIL_STATUS_MISMATCH | status_quantity_primary_latest | 2026-08-11

## Delay Phase - Series
Delay Phase - Series
Series | Phase | Foundation Bucket Start % | Foundation Bucket End % | Foundation Count | Matched Count | Match % | Median Delay Days | Average Delay Days | P90 Delay Days | Negative Excluded | Unmatched | Scope Total | Phase Foundations % of Scope | Phase Start Date | Phase End Date | Phase Duration Days | Monsoon Overlap | Monsoon Overlap Days | Monsoon Foundation Count
4xx | 0-20 | 0 | 20 | 351 | 342 | 97.44 | 204 | 224.5664 | 420.2 | 3 | 9 | 2222 | 15.8 | 2023-10-01 | 2025-04-05 | 553 | Yes | 122 | 251
4xx | 20-40 | 20 | 40 | 346 | 337 | 97.4 | 146 | 172.8862 | 325.7 | 3 | 9 | 2222 | 15.57 | 2024-09-06 | 2025-12-11 | 462 | Yes | 147 | 63
4xx | 40-60 | 40 | 60 | 349 | 338 | 96.85 | 88 | 113.0712 | 273.6 | 1 | 11 | 2222 | 15.71 | 2024-10-25 | 2026-01-21 | 454 | Yes | 122 | 20
4xx | 60-80 | 60 | 80 | 346 | 326 | 94.22 | 107.5 | 120.9753 | 254 | 2 | 20 | 2222 | 15.57 | 2024-12-09 | 2026-06-13 | 552 | Yes | 135 | 30
4xx | 80-100+ | 80 | 100 | 365 | 238 | 65.21 | 132.5 | 125.3814 | 213 | 2 | 127 | 2222 | 16.43 | 2025-01-31 | 2026-08-04 | 551 | Yes | 187 | 120
5xx | 0-20 | 0 | 20 | 463 | 354 | 76.46 | 148 | 173.4407 | 316.1 | 0 | 109 | 2404 | 19.26 | 2024-03-28 | 2026-08-11 | 867 | Yes | 316 | 115
5xx | 20-40 | 20 | 40 | 336 | 285 | 84.82 | 114 | 145.2782 | 284.9 | 1 | 51 | 2404 | 13.98 | 2024-11-15 | 2026-06-25 | 588 | Yes | 147 | 157
5xx | 40-60 | 40 | 60 | 298 | 263 | 88.26 | 128 | 141.2167 | 294.4 | 0 | 35 | 2404 | 12.4 | 2025-01-12 | 2026-05-27 | 501 | Yes | 122 | 56
5xx | 60-80 | 60 | 80 | 232 | 197 | 84.91 | 77.5 | 109.7347 | 245 | 1 | 35 | 2404 | 9.65 | 2025-04-17 | 2026-08-12 | 483 | Yes | 195 | 87
5xx | 80-100+ | 80 | 100 | 177 | 145 | 81.92 | 20.5 | 45.0143 | 133 | 5 | 32 | 2404 | 7.36 | 2025-10-23 | 2026-08-05 | 287 | Yes | 66 | 19
6xx | 0-20 | 0 | 20 | 256 | 180 | 70.31 | 92 | 103.3017 | 181 | 1 | 76 | 1287 | 19.89 | 2025-08-07 | 2026-02-10 | 188 | Yes | 55 | 8
6xx | 20-40 | 20 | 40 | 228 | 162 | 71.05 | 61 | 64.2112 | 116 | 1 | 66 | 1287 | 17.72 | 2025-12-26 | 2026-08-04 | 222 | Yes | 65 | 12
6xx | 40-60 | 40 | 60 | 163 | 82 | 50.31 | 17.5 | 25.2561 | 51.9 | 0 | 81 | 1287 | 12.67 | 2026-03-10 | 2026-07-26 | 139 | Yes | 56 | 53
6xx | 60-80 | 60 | 80 | 62 | 22 | 35.48 | 13.5 | 19.8182 | 46.3 | 0 | 40 | 1287 | 4.82 | 2026-06-03 | 2026-08-12 | 71 | Yes | 71 | 62

## Delay Phase - Ownership
Delay Phase - Ownership
Ownership | Phase | Foundation Bucket Start % | Foundation Bucket End % | Foundation Count | Matched Count | Match % | Median Delay Days | Average Delay Days | P90 Delay Days | Negative Excluded | Unmatched | Scope Total | Phase Foundations % of Scope | Phase Start Date | Phase End Date | Phase Duration Days | Monsoon Overlap | Monsoon Overlap Days | Monsoon Foundation Count
Government | 0-20 | 0 | 20 | 708 | 602 | 85.03 | 168 | 199.4766 | 383.9 | 4 | 106 | 3639 | 19.46 | 2024-01-05 | 2026-08-11 | 950 | Yes | 316 | 308
Government | 20-40 | 20 | 40 | 581 | 528 | 90.88 | 153 | 172.2214 | 325.7 | 4 | 53 | 3639 | 15.97 | 2024-09-06 | 2026-06-25 | 658 | Yes | 172 | 124
Government | 40-60 | 40 | 60 | 548 | 506 | 92.34 | 111 | 132.1069 | 291.6 | 1 | 42 | 3639 | 15.06 | 2024-10-25 | 2026-07-26 | 640 | Yes | 178 | 127
Government | 60-80 | 60 | 80 | 500 | 459 | 91.8 | 112 | 127.2538 | 256 | 2 | 41 | 3639 | 13.74 | 2024-12-09 | 2026-08-12 | 612 | Yes | 195 | 72
Government | 80-100+ | 80 | 100 | 497 | 340 | 68.41 | 98 | 104.7834 | 195.4 | 3 | 157 | 3639 | 13.66 | 2025-01-31 | 2026-08-05 | 552 | Yes | 188 | 135
Private | 0-20 | 0 | 20 | 362 | 274 | 75.69 | 117 | 134.0511 | 200.7 | 0 | 88 | 2274 | 15.92 | 2023-10-01 | 2026-02-10 | 864 | Yes | 244 | 66
Private | 20-40 | 20 | 40 | 329 | 256 | 77.81 | 62 | 74.8902 | 129.2 | 1 | 73 | 2274 | 14.47 | 2024-11-15 | 2026-08-04 | 628 | Yes | 187 | 108
Private | 40-60 | 40 | 60 | 262 | 177 | 67.56 | 51 | 59.8983 | 124.2 | 0 | 85 | 2274 | 11.52 | 2025-01-12 | 2026-06-03 | 508 | Yes | 125 | 2
Private | 60-80 | 60 | 80 | 140 | 86 | 61.43 | 30 | 35.1176 | 64 | 1 | 54 | 2274 | 6.16 | 2025-04-17 | 2026-08-12 | 483 | Yes | 195 | 107
Private | 80-100+ | 80 | 100 | 45 | 43 | 95.56 | 13 | 14.8718 | 26.6 | 4 | 2 | 2274 | 1.98 | 2025-10-23 | 2026-07-24 | 275 | Yes | 54 | 4

## Delay Buckets - Project
Delay Buckets - Project
Project | Bucket | Bucket Start Days | Bucket End Days | Foundations In Bucket | % of Foundations Done Till Date | % of Scope | Foundations Done Till Date | Scope Total | Matched Non-Negative | Unmatched | Negative Excluded
TA 413 | 0-30 | 0 | 30 | 3 | 0.96 | 0.95 | 314 | 316 | 305 | 8 | 1
TA 413 | 31-60 | 31 | 60 | 23 | 7.32 | 7.28 | 314 | 316 | 305 | 8 | 1
TA 413 | 61-90 | 61 | 90 | 34 | 10.83 | 10.76 | 314 | 316 | 305 | 8 | 1
TA 413 | 91-120 | 91 | 120 | 24 | 7.64 | 7.59 | 314 | 316 | 305 | 8 | 1
TA 413 | 121-150 | 121 | 150 | 20 | 6.37 | 6.33 | 314 | 316 | 305 | 8 | 1
TA 413 | 151-180 | 151 | 180 | 33 | 10.51 | 10.44 | 314 | 316 | 305 | 8 | 1
TA 413 | 181-210 | 181 | 210 | 29 | 9.24 | 9.18 | 314 | 316 | 305 | 8 | 1
TA 413 | 211-240 | 211 | 240 | 16 | 5.1 | 5.06 | 314 | 316 | 305 | 8 | 1
TA 413 | 241-270 | 241 | 270 | 22 | 7.01 | 6.96 | 314 | 316 | 305 | 8 | 1
TA 413 | 271-300 | 271 | 300 | 21 | 6.69 | 6.65 | 314 | 316 | 305 | 8 | 1
TA 413 | 301-330 | 301 | 330 | 21 | 6.69 | 6.65 | 314 | 316 | 305 | 8 | 1
TA 413 | 331-360 | 331 | 360 | 19 | 6.05 | 6.01 | 314 | 316 | 305 | 8 | 1
TA 413 | 361-390 | 361 | 390 | 10 | 3.18 | 3.16 | 314 | 316 | 305 | 8 | 1
TA 413 | 391-420 | 391 | 420 | 9 | 2.87 | 2.85 | 314 | 316 | 305 | 8 | 1
TA 413 | 421-450 | 421 | 450 | 9 | 2.87 | 2.85 | 314 | 316 | 305 | 8 | 1
TA 413 | 451-480 | 451 | 480 | 2 | 0.64 | 0.63 | 314 | 316 | 305 | 8 | 1
TA 413 | 481-510 | 481 | 510 | 9 | 2.87 | 2.85 | 314 | 316 | 305 | 8 | 1
TA 413 | 511-540 | 511 | 540 | 1 | 0.32 | 0.32 | 314 | 316 | 305 | 8 | 1
TA 414 | 0-30 | 0 | 30 | 56 | 16.72 | 15.91 | 335 | 352 | 279 | 55 | 1
TA 414 | 31-60 | 31 | 60 | 52 | 15.52 | 14.77 | 335 | 352 | 279 | 55 | 1
TA 414 | 61-90 | 61 | 90 | 36 | 10.75 | 10.23 | 335 | 352 | 279 | 55 | 1
TA 414 | 91-120 | 91 | 120 | 18 | 5.37 | 5.11 | 335 | 352 | 279 | 55 | 1
TA 414 | 121-150 | 121 | 150 | 15 | 4.48 | 4.26 | 335 | 352 | 279 | 55 | 1
TA 414 | 151-180 | 151 | 180 | 8 | 2.39 | 2.27 | 335 | 352 | 279 | 55 | 1
TA 414 | 181-210 | 181 | 210 | 12 | 3.58 | 3.41 | 335 | 352 | 279 | 55 | 1
TA 414 | 211-240 | 211 | 240 | 9 | 2.69 | 2.56 | 335 | 352 | 279 | 55 | 1
TA 414 | 241-270 | 241 | 270 | 6 | 1.79 | 1.7 | 335 | 352 | 279 | 55 | 1
TA 414 | 271-300 | 271 | 300 | 10 | 2.99 | 2.84 | 335 | 352 | 279 | 55 | 1
TA 414 | 301-330 | 301 | 330 | 16 | 4.78 | 4.55 | 335 | 352 | 279 | 55 | 1
TA 414 | 331-360 | 331 | 360 | 13 | 3.88 | 3.69 | 335 | 352 | 279 | 55 | 1
TA 414 | 361-390 | 361 | 390 | 5 | 1.49 | 1.42 | 335 | 352 | 279 | 55 | 1
TA 414 | 391-420 | 391 | 420 | 7 | 2.09 | 1.99 | 335 | 352 | 279 | 55 | 1
TA 414 | 421-450 | 421 | 450 | 7 | 2.09 | 1.99 | 335 | 352 | 279 | 55 | 1
TA 414 | 451-480 | 451 | 480 | 5 | 1.49 | 1.42 | 335 | 352 | 279 | 55 | 1
TA 414 | 481-510 | 481 | 510 | 1 | 0.3 | 0.28 | 335 | 352 | 279 | 55 | 1
TA 414 | 511-540 | 511 | 540 | 1 | 0.3 | 0.28 | 335 | 352 | 279 | 55 | 1
TA 414 | 541-570 | 541 | 570 | 1 | 0.3 | 0.28 | 335 | 352 | 279 | 55 | 1
TA 414 | 571-600 | 571 | 600 | 1 | 0.3 | 0.28 | 335 | 352 | 279 | 55 | 1
TA 416 | 0-30 | 0 | 30 | 7 | 2.11 | 2.32 | 331 | 302 | 302 | 28 | 1
TA 416 | 31-60 | 31 | 60 | 20 | 6.04 | 6.62 | 331 | 302 | 302 | 28 | 1
TA 416 | 61-90 | 61 | 90 | 40 | 12.08 | 13.25 | 331 | 302 | 302 | 28 | 1
TA 416 | 91-120 | 91 | 120 | 61 | 18.43 | 20.2 | 331 | 302 | 302 | 28 | 1
TA 416 | 121-150 | 121 | 150 | 47 | 14.2 | 15.56 | 331 | 302 | 302 | 28 | 1
TA 416 | 151-180 | 151 | 180 | 29 | 8.76 | 9.6 | 331 | 302 | 302 | 28 | 1
TA 416 | 181-210 | 181 | 210 | 26 | 7.85 | 8.61 | 331 | 302 | 302 | 28 | 1
TA 416 | 211-240 | 211 | 240 | 24 | 7.25 | 7.95 | 331 | 302 | 302 | 28 | 1
TA 416 | 241-270 | 241 | 270 | 21 | 6.34 | 6.95 | 331 | 302 | 302 | 28 | 1
TA 416 | 271-300 | 271 | 300 | 9 | 2.72 | 2.98 | 331 | 302 | 302 | 28 | 1
TA 416 | 301-330 | 301 | 330 | 9 | 2.72 | 2.98 | 331 | 302 | 302 | 28 | 1
TA 416 | 331-360 | 331 | 360 | 6 | 1.81 | 1.99 | 331 | 302 | 302 | 28 | 1
TA 416 | 361-390 | 361 | 390 | 1 | 0.3 | 0.33 | 331 | 302 | 302 | 28 | 1
TA 416 | 391-420 | 391 | 420 | 1 | 0.3 | 0.33 | 331 | 302 | 302 | 28 | 1
TA 416 | 421-450 | 421 | 450 | 0 | 0 | 0 | 331 | 302 | 302 | 28 | 1
TA 416 | 451-480 | 451 | 480 | 1 | 0.3 | 0.33 | 331 | 302 | 302 | 28 | 1
TA 418 | 0-30 | 0 | 30 | 11 | 6.59 | 8.66 | 167 | 127 | 120 | 42 | 5
TA 418 | 31-60 | 31 | 60 | 18 | 10.78 | 14.17 | 167 | 127 | 120 | 42 | 5
TA 418 | 61-90 | 61 | 90 | 20 | 11.98 | 15.75 | 167 | 127 | 120 | 42 | 5
TA 418 | 91-120 | 91 | 120 | 14 | 8.38 | 11.02 | 167 | 127 | 120 | 42 | 5
TA 418 | 121-150 | 121 | 150 | 18 | 10.78 | 14.17 | 167 | 127 | 120 | 42 | 5
TA 418 | 151-180 | 151 | 180 | 15 | 8.98 | 11.81 | 167 | 127 | 120 | 42 | 5
TA 418 | 181-210 | 181 | 210 | 5 | 2.99 | 3.94 | 167 | 127 | 120 | 42 | 5
TA 418 | 211-240 | 211 | 240 | 10 | 5.99 | 7.87 | 167 | 127 | 120 | 42 | 5
TA 418 | 241-270 | 241 | 270 | 3 | 1.8 | 2.36 | 167 | 127 | 120 | 42 | 5
TA 418 | 271-300 | 271 | 300 | 1 | 0.6 | 0.79 | 167 | 127 | 120 | 42 | 5
TA 418 | 301-330 | 301 | 330 | 2 | 1.2 | 1.57 | 167 | 127 | 120 | 42 | 5
TA 418 | 331-360 | 331 | 360 | 2 | 1.2 | 1.57 | 167 | 127 | 120 | 42 | 5
TA 418 | 361-390 | 361 | 390 | 0 | 0 | 0 | 167 | 127 | 120 | 42 | 5
TA 418 | 391-420 | 391 | 420 | 0 | 0 | 0 | 167 | 127 | 120 | 42 | 5
TA 418 | 421-450 | 421 | 450 | 0 | 0 | 0 | 167 | 127 | 120 | 42 | 5
TA 418 | 451-480 | 451 | 480 | 1 | 0.6 | 0.79 | 167 | 127 | 120 | 42 | 5
TA 419 | 0-30 | 0 | 30 | 63 | 22.11 | 19.03 | 285 | 331 | 264 | 19 | 2
TA 419 | 31-60 | 31 | 60 | 22 | 7.72 | 6.65 | 285 | 331 | 264 | 19 | 2
TA 419 | 61-90 | 61 | 90 | 19 | 6.67 | 5.74 | 285 | 331 | 264 | 19 | 2
TA 419 | 91-120 | 91 | 120 | 24 | 8.42 | 7.25 | 285 | 331 | 264 | 19 | 2
TA 419 | 121-150 | 121 | 150 | 21 | 7.37 | 6.34 | 285 | 331 | 264 | 19 | 2
TA 419 | 151-180 | 151 | 180 | 21 | 7.37 | 6.34 | 285 | 331 | 264 | 19 | 2
TA 419 | 181-210 | 181 | 210 | 19 | 6.67 | 5.74 | 285 | 331 | 264 | 19 | 2
TA 419 | 211-240 | 211 | 240 | 22 | 7.72 | 6.65 | 285 | 331 | 264 | 19 | 2
TA 419 | 241-270 | 241 | 270 | 21 | 7.37 | 6.34 | 285 | 331 | 264 | 19 | 2
TA 419 | 271-300 | 271 | 300 | 14 | 4.91 | 4.23 | 285 | 331 | 264 | 19 | 2
TA 419 | 301-330 | 301 | 330 | 5 | 1.75 | 1.51 | 285 | 331 | 264 | 19 | 2
TA 419 | 331-360 | 331 | 360 | 1 | 0.35 | 0.3 | 285 | 331 | 264 | 19 | 2
TA 419 | 361-390 | 361 | 390 | 5 | 1.75 | 1.51 | 285 | 331 | 264 | 19 | 2
TA 419 | 391-420 | 391 | 420 | 3 | 1.05 | 0.91 | 285 | 331 | 264 | 19 | 2
TA 419 | 421-450 | 421 | 450 | 1 | 0.35 | 0.3 | 285 | 331 | 264 | 19 | 2
TA 419 | 451-480 | 451 | 480 | 1 | 0.35 | 0.3 | 285 | 331 | 264 | 19 | 2
TA 419 | 481-510 | 481 | 510 | 1 | 0.35 | 0.3 | 285 | 331 | 264 | 19 | 2
TA 419 | 511-540 | 511 | 540 | 1 | 0.35 | 0.3 | 285 | 331 | 264 | 19 | 2
TA 421 | 0-30 | 0 | 30 | 26 | 8.15 | 8.41 | 319 | 309 | 300 | 18 | 1
TA 421 | 31-60 | 31 | 60 | 49 | 15.36 | 15.86 | 319 | 309 | 300 | 18 | 1
TA 421 | 61-90 | 61 | 90 | 47 | 14.73 | 15.21 | 319 | 309 | 300 | 18 | 1
TA 421 | 91-120 | 91 | 120 | 56 | 17.55 | 18.12 | 319 | 309 | 300 | 18 | 1
TA 421 | 121-150 | 121 | 150 | 34 | 10.66 | 11 | 319 | 309 | 300 | 18 | 1
TA 421 | 151-180 | 151 | 180 | 40 | 12.54 | 12.94 | 319 | 309 | 300 | 18 | 1
TA 421 | 181-210 | 181 | 210 | 14 | 4.39 | 4.53 | 319 | 309 | 300 | 18 | 1
TA 421 | 211-240 | 211 | 240 | 13 | 4.08 | 4.21 | 319 | 309 | 300 | 18 | 1
TA 421 | 241-270 | 241 | 270 | 5 | 1.57 | 1.62 | 319 | 309 | 300 | 18 | 1
TA 421 | 271-300 | 271 | 300 | 8 | 2.51 | 2.59 | 319 | 309 | 300 | 18 | 1
TA 421 | 301-330 | 301 | 330 | 6 | 1.88 | 1.94 | 319 | 309 | 300 | 18 | 1
TA 421 | 331-360 | 331 | 360 | 1 | 0.31 | 0.32 | 319 | 309 | 300 | 18 | 1
TA 421 | 361-390 | 361 | 390 | 0 | 0 | 0 | 319 | 309 | 300 | 18 | 1
TA 421 | 391-420 | 391 | 420 | 1 | 0.31 | 0.32 | 319 | 309 | 300 | 18 | 1
TA 505 | 0-30 | 0 | 30 | 53 | 14.02 | 13.98 | 378 | 379 | 364 | 13 | 1
TA 505 | 31-60 | 31 | 60 | 29 | 7.67 | 7.65 | 378 | 379 | 364 | 13 | 1
TA 505 | 61-90 | 61 | 90 | 15 | 3.97 | 3.96 | 378 | 379 | 364 | 13 | 1
TA 505 | 91-120 | 91 | 120 | 41 | 10.85 | 10.82 | 378 | 379 | 364 | 13 | 1
TA 505 | 121-150 | 121 | 150 | 51 | 13.49 | 13.46 | 378 | 379 | 364 | 13 | 1
TA 505 | 151-180 | 151 | 180 | 29 | 7.67 | 7.65 | 378 | 379 | 364 | 13 | 1
TA 505 | 181-210 | 181 | 210 | 28 | 7.41 | 7.39 | 378 | 379 | 364 | 13 | 1
TA 505 | 211-240 | 211 | 240 | 28 | 7.41 | 7.39 | 378 | 379 | 364 | 13 | 1
TA 505 | 241-270 | 241 | 270 | 22 | 5.82 | 5.8 | 378 | 379 | 364 | 13 | 1
TA 505 | 271-300 | 271 | 300 | 22 | 5.82 | 5.8 | 378 | 379 | 364 | 13 | 1
TA 505 | 301-330 | 301 | 330 | 12 | 3.17 | 3.17 | 378 | 379 | 364 | 13 | 1
TA 505 | 331-360 | 331 | 360 | 19 | 5.03 | 5.01 | 378 | 379 | 364 | 13 | 1
TA 505 | 361-390 | 361 | 390 | 4 | 1.06 | 1.06 | 378 | 379 | 364 | 13 | 1
TA 505 | 391-420 | 391 | 420 | 3 | 0.79 | 0.79 | 378 | 379 | 364 | 13 | 1
TA 505 | 421-450 | 421 | 450 | 5 | 1.32 | 1.32 | 378 | 379 | 364 | 13 | 1
TA 505 | 451-480 | 451 | 480 | 0 | 0 | 0 | 378 | 379 | 364 | 13 | 1
TA 505 | 481-510 | 481 | 510 | 1 | 0.26 | 0.26 | 378 | 379 | 364 | 13 | 1
TA 505 | 511-540 | 511 | 540 | 0 | 0 | 0 | 378 | 379 | 364 | 13 | 1
TA 505 | 541-570 | 541 | 570 | 0 | 0 | 0 | 378 | 379 | 364 | 13 | 1
TA 505 | 571-600 | 571 | 600 | 0 | 0 | 0 | 378 | 379 | 364 | 13 | 1
TA 505 | 601-630 | 601 | 630 | 0 | 0 | 0 | 378 | 379 | 364 | 13 | 1
TA 505 | 631-660 | 631 | 660 | 2 | 0.53 | 0.53 | 378 | 379 | 364 | 13 | 1
TA 510 | 0-30 | 0 | 30 | 4 | 4.21 | 1.37 | 95 | 293 | 49 | 46 | 0
TA 510 | 31-60 | 31 | 60 | 5 | 5.26 | 1.71 | 95 | 293 | 49 | 46 | 0
TA 510 | 61-90 | 61 | 90 | 12 | 12.63 | 4.1 | 95 | 293 | 49 | 46 | 0
TA 510 | 91-120 | 91 | 120 | 9 | 9.47 | 3.07 | 95 | 293 | 49 | 46 | 0
TA 510 | 121-150 | 121 | 150 | 2 | 2.11 | 0.68 | 95 | 293 | 49 | 46 | 0
TA 510 | 151-180 | 151 | 180 | 0 | 0 | 0 | 95 | 293 | 49 | 46 | 0
TA 510 | 181-210 | 181 | 210 | 0 | 0 | 0 | 95 | 293 | 49 | 46 | 0
TA 510 | 211-240 | 211 | 240 | 2 | 2.11 | 0.68 | 95 | 293 | 49 | 46 | 0
TA 510 | 241-270 | 241 | 270 | 1 | 1.05 | 0.34 | 95 | 293 | 49 | 46 | 0
TA 510 | 271-300 | 271 | 300 | 4 | 4.21 | 1.37 | 95 | 293 | 49 | 46 | 0
TA 510 | 301-330 | 301 | 330 | 0 | 0 | 0 | 95 | 293 | 49 | 46 | 0
TA 510 | 331-360 | 331 | 360 | 3 | 3.16 | 1.02 | 95 | 293 | 49 | 46 | 0
TA 510 | 361-390 | 361 | 390 | 2 | 2.11 | 0.68 | 95 | 293 | 49 | 46 | 0
TA 510 | 391-420 | 391 | 420 | 3 | 3.16 | 1.02 | 95 | 293 | 49 | 46 | 0
TA 510 | 421-450 | 421 | 450 | 1 | 1.05 | 0.34 | 95 | 293 | 49 | 46 | 0
TA 510 | 451-480 | 451 | 480 | 1 | 1.05 | 0.34 | 95 | 293 | 49 | 46 | 0
TA 512 | 0-30 | 0 | 30 | 6 | 1.92 | 1.88 | 312 | 319 | 283 | 29 | 0
TA 512 | 31-60 | 31 | 60 | 15 | 4.81 | 4.7 | 312 | 319 | 283 | 29 | 0
TA 512 | 61-90 | 61 | 90 | 26 | 8.33 | 8.15 | 312 | 319 | 283 | 29 | 0
TA 512 | 91-120 | 91 | 120 | 23 | 7.37 | 7.21 | 312 | 319 | 283 | 29 | 0
TA 512 | 121-150 | 121 | 150 | 37 | 11.86 | 11.6 | 312 | 319 | 283 | 29 | 0
TA 512 | 151-180 | 151 | 180 | 50 | 16.03 | 15.67 | 312 | 319 | 283 | 29 | 0
TA 512 | 181-210 | 181 | 210 | 24 | 7.69 | 7.52 | 312 | 319 | 283 | 29 | 0
TA 512 | 211-240 | 211 | 240 | 34 | 10.9 | 10.66 | 312 | 319 | 283 | 29 | 0
TA 512 | 241-270 | 241 | 270 | 30 | 9.62 | 9.4 | 312 | 319 | 283 | 29 | 0
TA 512 | 271-300 | 271 | 300 | 15 | 4.81 | 4.7 | 312 | 319 | 283 | 29 | 0
TA 512 | 301-330 | 301 | 330 | 7 | 2.24 | 2.19 | 312 | 319 | 283 | 29 | 0
TA 512 | 331-360 | 331 | 360 | 9 | 2.88 | 2.82 | 312 | 319 | 283 | 29 | 0
TA 512 | 361-390 | 361 | 390 | 5 | 1.6 | 1.57 | 312 | 319 | 283 | 29 | 0
TA 512 | 391-420 | 391 | 420 | 1 | 0.32 | 0.31 | 312 | 319 | 283 | 29 | 0
TA 512 | 421-450 | 421 | 450 | 0 | 0 | 0 | 312 | 319 | 283 | 29 | 0
TA 512 | 451-480 | 451 | 480 | 1 | 0.32 | 0.31 | 312 | 319 | 283 | 29 | 0
TA 513 | 0-30 | 0 | 30 | 2 | 1.83 | 0.32 | 109 | 619 | 33 | 76 | 0
TA 513 | 31-60 | 31 | 60 | 4 | 3.67 | 0.65 | 109 | 619 | 33 | 76 | 0
TA 513 | 61-90 | 61 | 90 | 1 | 0.92 | 0.16 | 109 | 619 | 33 | 76 | 0
TA 513 | 91-120 | 91 | 120 | 4 | 3.67 | 0.65 | 109 | 619 | 33 | 76 | 0
TA 513 | 121-150 | 121 | 150 | 2 | 1.83 | 0.32 | 109 | 619 | 33 | 76 | 0
TA 513 | 151-180 | 151 | 180 | 10 | 9.17 | 1.62 | 109 | 619 | 33 | 76 | 0
TA 513 | 181-210 | 181 | 210 | 6 | 5.5 | 0.97 | 109 | 619 | 33 | 76 | 0
TA 513 | 211-240 | 211 | 240 | 1 | 0.92 | 0.16 | 109 | 619 | 33 | 76 | 0
TA 513 | 241-270 | 241 | 270 | 1 | 0.92 | 0.16 | 109 | 619 | 33 | 76 | 0
TA 513 | 271-300 | 271 | 300 | 1 | 0.92 | 0.16 | 109 | 619 | 33 | 76 | 0
TA 513 | 301-330 | 301 | 330 | 1 | 0.92 | 0.16 | 109 | 619 | 33 | 76 | 0
TA 601 | 0-30 | 0 | 30 | 70 | 37.04 | 23.97 | 189 | 292 | 122 | 65 | 2
TA 601 | 31-60 | 31 | 60 | 18 | 9.52 | 6.16 | 189 | 292 | 122 | 65 | 2
TA 601 | 61-90 | 61 | 90 | 17 | 8.99 | 5.82 | 189 | 292 | 122 | 65 | 2
TA 601 | 91-120 | 91 | 120 | 11 | 5.82 | 3.77 | 189 | 292 | 122 | 65 | 2
TA 601 | 121-150 | 121 | 150 | 3 | 1.59 | 1.03 | 189 | 292 | 122 | 65 | 2
TA 601 | 151-180 | 151 | 180 | 0 | 0 | 0 | 189 | 292 | 122 | 65 | 2
TA 601 | 181-210 | 181 | 210 | 2 | 1.06 | 0.68 | 189 | 292 | 122 | 65 | 2
TA 601 | 211-240 | 211 | 240 | 0 | 0 | 0 | 189 | 292 | 122 | 65 | 2
TA 601 | 241-270 | 241 | 270 | 0 | 0 | 0 | 189 | 292 | 122 | 65 | 2
TA 601 | 271-300 | 271 | 300 | 0 | 0 | 0 | 189 | 292 | 122 | 65 | 2
TA 601 | 301-330 | 301 | 330 | 0 | 0 | 0 | 189 | 292 | 122 | 65 | 2
TA 601 | 331-360 | 331 | 360 | 1 | 0.53 | 0.34 | 189 | 292 | 122 | 65 | 2
TB 408 | No Matched Delays |  |  | 0 | 0 | 0 | 6 | 485 | 0 | 6 | 0
TB 501 | 0-30 | 0 | 30 | 62 | 26.38 | 26.05 | 235 | 238 | 229 | 2 | 4
TB 501 | 31-60 | 31 | 60 | 60 | 25.53 | 25.21 | 235 | 238 | 229 | 2 | 4
TB 501 | 61-90 | 61 | 90 | 38 | 16.17 | 15.97 | 235 | 238 | 229 | 2 | 4
TB 501 | 91-120 | 91 | 120 | 36 | 15.32 | 15.13 | 235 | 238 | 229 | 2 | 4
TB 501 | 121-150 | 121 | 150 | 19 | 8.09 | 7.98 | 235 | 238 | 229 | 2 | 4
TB 501 | 151-180 | 151 | 180 | 5 | 2.13 | 2.1 | 235 | 238 | 229 | 2 | 4
TB 501 | 181-210 | 181 | 210 | 8 | 3.4 | 3.36 | 235 | 238 | 229 | 2 | 4
TB 501 | 211-240 | 211 | 240 | 0 | 0 | 0 | 235 | 238 | 229 | 2 | 4
TB 501 | 241-270 | 241 | 270 | 1 | 0.43 | 0.42 | 235 | 238 | 229 | 2 | 4
TB 507 | 0-30 | 0 | 30 | 42 | 11.14 | 7.55 | 377 | 556 | 279 | 96 | 2
TB 507 | 31-60 | 31 | 60 | 67 | 17.77 | 12.05 | 377 | 556 | 279 | 96 | 2
TB 507 | 61-90 | 61 | 90 | 53 | 14.06 | 9.53 | 377 | 556 | 279 | 96 | 2
TB 507 | 91-120 | 91 | 120 | 32 | 8.49 | 5.76 | 377 | 556 | 279 | 96 | 2
TB 507 | 121-150 | 121 | 150 | 30 | 7.96 | 5.4 | 377 | 556 | 279 | 96 | 2
TB 507 | 151-180 | 151 | 180 | 24 | 6.37 | 4.32 | 377 | 556 | 279 | 96 | 2
TB 507 | 181-210 | 181 | 210 | 8 | 2.12 | 1.44 | 377 | 556 | 279 | 96 | 2
TB 507 | 211-240 | 211 | 240 | 4 | 1.06 | 0.72 | 377 | 556 | 279 | 96 | 2
TB 507 | 241-270 | 241 | 270 | 3 | 0.8 | 0.54 | 377 | 556 | 279 | 96 | 2
TB 507 | 271-300 | 271 | 300 | 1 | 0.27 | 0.18 | 377 | 556 | 279 | 96 | 2
TB 507 | 301-330 | 301 | 330 | 2 | 0.53 | 0.36 | 377 | 556 | 279 | 96 | 2
TB 507 | 331-360 | 331 | 360 | 3 | 0.8 | 0.54 | 377 | 556 | 279 | 96 | 2
TB 507 | 361-390 | 361 | 390 | 4 | 1.06 | 0.72 | 377 | 556 | 279 | 96 | 2
TB 507 | 391-420 | 391 | 420 | 2 | 0.53 | 0.36 | 377 | 556 | 279 | 96 | 2
TB 507 | 421-450 | 421 | 450 | 2 | 0.53 | 0.36 | 377 | 556 | 279 | 96 | 2
TB 507 | 451-480 | 451 | 480 | 2 | 0.53 | 0.36 | 377 | 556 | 279 | 96 | 2
TB 605 | 0-30 | 0 | 30 | 62 | 17.17 | 11.85 | 361 | 523 | 259 | 102 | 0
TB 605 | 31-60 | 31 | 60 | 54 | 14.96 | 10.33 | 361 | 523 | 259 | 102 | 0
TB 605 | 61-90 | 61 | 90 | 62 | 17.17 | 11.85 | 361 | 523 | 259 | 102 | 0
TB 605 | 91-120 | 91 | 120 | 48 | 13.3 | 9.18 | 361 | 523 | 259 | 102 | 0
TB 605 | 121-150 | 121 | 150 | 15 | 4.16 | 2.87 | 361 | 523 | 259 | 102 | 0
TB 605 | 151-180 | 151 | 180 | 10 | 2.77 | 1.91 | 361 | 523 | 259 | 102 | 0
TB 605 | 181-210 | 181 | 210 | 4 | 1.11 | 0.76 | 361 | 523 | 259 | 102 | 0
TB 605 | 211-240 | 211 | 240 | 4 | 1.11 | 0.76 | 361 | 523 | 259 | 102 | 0
TB 608 | 0-30 | 0 | 30 | 0 | 0 | 0 | 159 | 472 | 63 | 96 | 0
TB 608 | 31-60 | 31 | 60 | 14 | 8.81 | 2.97 | 159 | 472 | 63 | 96 | 0
TB 608 | 61-90 | 61 | 90 | 10 | 6.29 | 2.12 | 159 | 472 | 63 | 96 | 0
TB 608 | 91-120 | 91 | 120 | 8 | 5.03 | 1.69 | 159 | 472 | 63 | 96 | 0
TB 608 | 121-150 | 121 | 150 | 13 | 8.18 | 2.75 | 159 | 472 | 63 | 96 | 0
TB 608 | 151-180 | 151 | 180 | 10 | 6.29 | 2.12 | 159 | 472 | 63 | 96 | 0
TB 608 | 181-210 | 181 | 210 | 4 | 2.52 | 0.85 | 159 | 472 | 63 | 96 | 0
TB 608 | 211-240 | 211 | 240 | 2 | 1.26 | 0.42 | 159 | 472 | 63 | 96 | 0
TB 608 | 241-270 | 241 | 270 | 1 | 0.63 | 0.21 | 159 | 472 | 63 | 96 | 0
TB 608 | 271-300 | 271 | 300 | 1 | 0.63 | 0.21 | 159 | 472 | 63 | 96 | 0

## Delay Buckets - Series
Delay Buckets - Series
Series | Bucket | Bucket Start Days | Bucket End Days | Foundations In Bucket | % of Foundations Done Till Date | % of Scope | Foundations Done Till Date | Scope Total | Matched Non-Negative | Unmatched | Negative Excluded
4xx | 0-30 | 0 | 30 | 166 | 9.45 | 7.47 | 1757 | 2222 | 1570 | 176 | 11
4xx | 31-60 | 31 | 60 | 184 | 10.47 | 8.28 | 1757 | 2222 | 1570 | 176 | 11
4xx | 61-90 | 61 | 90 | 196 | 11.16 | 8.82 | 1757 | 2222 | 1570 | 176 | 11
4xx | 91-120 | 91 | 120 | 197 | 11.21 | 8.87 | 1757 | 2222 | 1570 | 176 | 11
4xx | 121-150 | 121 | 150 | 155 | 8.82 | 6.98 | 1757 | 2222 | 1570 | 176 | 11
4xx | 151-180 | 151 | 180 | 146 | 8.31 | 6.57 | 1757 | 2222 | 1570 | 176 | 11
4xx | 181-210 | 181 | 210 | 105 | 5.98 | 4.73 | 1757 | 2222 | 1570 | 176 | 11
4xx | 211-240 | 211 | 240 | 94 | 5.35 | 4.23 | 1757 | 2222 | 1570 | 176 | 11
4xx | 241-270 | 241 | 270 | 78 | 4.44 | 3.51 | 1757 | 2222 | 1570 | 176 | 11
4xx | 271-300 | 271 | 300 | 63 | 3.59 | 2.84 | 1757 | 2222 | 1570 | 176 | 11
4xx | 301-330 | 301 | 330 | 59 | 3.36 | 2.66 | 1757 | 2222 | 1570 | 176 | 11
4xx | 331-360 | 331 | 360 | 42 | 2.39 | 1.89 | 1757 | 2222 | 1570 | 176 | 11
4xx | 361-390 | 361 | 390 | 21 | 1.2 | 0.95 | 1757 | 2222 | 1570 | 176 | 11
4xx | 391-420 | 391 | 420 | 21 | 1.2 | 0.95 | 1757 | 2222 | 1570 | 176 | 11
4xx | 421-450 | 421 | 450 | 17 | 0.97 | 0.77 | 1757 | 2222 | 1570 | 176 | 11
4xx | 451-480 | 451 | 480 | 10 | 0.57 | 0.45 | 1757 | 2222 | 1570 | 176 | 11
4xx | 481-510 | 481 | 510 | 11 | 0.63 | 0.5 | 1757 | 2222 | 1570 | 176 | 11
4xx | 511-540 | 511 | 540 | 3 | 0.17 | 0.14 | 1757 | 2222 | 1570 | 176 | 11
4xx | 541-570 | 541 | 570 | 1 | 0.06 | 0.05 | 1757 | 2222 | 1570 | 176 | 11
4xx | 571-600 | 571 | 600 | 1 | 0.06 | 0.05 | 1757 | 2222 | 1570 | 176 | 11
5xx | 0-30 | 0 | 30 | 169 | 11.22 | 7.03 | 1506 | 2404 | 1237 | 262 | 7
5xx | 31-60 | 31 | 60 | 180 | 11.95 | 7.49 | 1506 | 2404 | 1237 | 262 | 7
5xx | 61-90 | 61 | 90 | 145 | 9.63 | 6.03 | 1506 | 2404 | 1237 | 262 | 7
5xx | 91-120 | 91 | 120 | 145 | 9.63 | 6.03 | 1506 | 2404 | 1237 | 262 | 7
5xx | 121-150 | 121 | 150 | 141 | 9.36 | 5.87 | 1506 | 2404 | 1237 | 262 | 7
5xx | 151-180 | 151 | 180 | 118 | 7.84 | 4.91 | 1506 | 2404 | 1237 | 262 | 7
5xx | 181-210 | 181 | 210 | 74 | 4.91 | 3.08 | 1506 | 2404 | 1237 | 262 | 7
5xx | 211-240 | 211 | 240 | 69 | 4.58 | 2.87 | 1506 | 2404 | 1237 | 262 | 7
5xx | 241-270 | 241 | 270 | 58 | 3.85 | 2.41 | 1506 | 2404 | 1237 | 262 | 7
5xx | 271-300 | 271 | 300 | 43 | 2.86 | 1.79 | 1506 | 2404 | 1237 | 262 | 7
5xx | 301-330 | 301 | 330 | 22 | 1.46 | 0.92 | 1506 | 2404 | 1237 | 262 | 7
5xx | 331-360 | 331 | 360 | 34 | 2.26 | 1.41 | 1506 | 2404 | 1237 | 262 | 7
5xx | 361-390 | 361 | 390 | 15 | 1 | 0.62 | 1506 | 2404 | 1237 | 262 | 7
5xx | 391-420 | 391 | 420 | 9 | 0.6 | 0.37 | 1506 | 2404 | 1237 | 262 | 7
5xx | 421-450 | 421 | 450 | 8 | 0.53 | 0.33 | 1506 | 2404 | 1237 | 262 | 7
5xx | 451-480 | 451 | 480 | 4 | 0.27 | 0.17 | 1506 | 2404 | 1237 | 262 | 7
5xx | 481-510 | 481 | 510 | 1 | 0.07 | 0.04 | 1506 | 2404 | 1237 | 262 | 7
5xx | 511-540 | 511 | 540 | 0 | 0 | 0 | 1506 | 2404 | 1237 | 262 | 7
5xx | 541-570 | 541 | 570 | 0 | 0 | 0 | 1506 | 2404 | 1237 | 262 | 7
5xx | 571-600 | 571 | 600 | 0 | 0 | 0 | 1506 | 2404 | 1237 | 262 | 7
5xx | 601-630 | 601 | 630 | 0 | 0 | 0 | 1506 | 2404 | 1237 | 262 | 7
5xx | 631-660 | 631 | 660 | 2 | 0.13 | 0.08 | 1506 | 2404 | 1237 | 262 | 7
6xx | 0-30 | 0 | 30 | 132 | 18.62 | 10.26 | 709 | 1287 | 444 | 263 | 2
6xx | 31-60 | 31 | 60 | 86 | 12.13 | 6.68 | 709 | 1287 | 444 | 263 | 2
6xx | 61-90 | 61 | 90 | 89 | 12.55 | 6.92 | 709 | 1287 | 444 | 263 | 2
6xx | 91-120 | 91 | 120 | 67 | 9.45 | 5.21 | 709 | 1287 | 444 | 263 | 2
6xx | 121-150 | 121 | 150 | 31 | 4.37 | 2.41 | 709 | 1287 | 444 | 263 | 2
6xx | 151-180 | 151 | 180 | 20 | 2.82 | 1.55 | 709 | 1287 | 444 | 263 | 2
6xx | 181-210 | 181 | 210 | 10 | 1.41 | 0.78 | 709 | 1287 | 444 | 263 | 2
6xx | 211-240 | 211 | 240 | 6 | 0.85 | 0.47 | 709 | 1287 | 444 | 263 | 2
6xx | 241-270 | 241 | 270 | 1 | 0.14 | 0.08 | 709 | 1287 | 444 | 263 | 2
6xx | 271-300 | 271 | 300 | 1 | 0.14 | 0.08 | 709 | 1287 | 444 | 263 | 2
6xx | 301-330 | 301 | 330 | 0 | 0 | 0 | 709 | 1287 | 444 | 263 | 2
6xx | 331-360 | 331 | 360 | 1 | 0.14 | 0.08 | 709 | 1287 | 444 | 263 | 2

## Delay Buckets - Ownership
Delay Buckets - Ownership
Ownership | Bucket | Bucket Start Days | Bucket End Days | Foundations In Bucket | % of Foundations Done Till Date | % of Scope | Foundations Done Till Date | Scope Total | Matched Non-Negative | Unmatched | Negative Excluded
Government | 0-30 | 0 | 30 | 301 | 10.62 | 8.27 | 2834 | 3639 | 2421 | 399 | 14
Government | 31-60 | 31 | 60 | 255 | 9 | 7.01 | 2834 | 3639 | 2421 | 399 | 14
Government | 61-90 | 61 | 90 | 267 | 9.42 | 7.34 | 2834 | 3639 | 2421 | 399 | 14
Government | 91-120 | 91 | 120 | 285 | 10.06 | 7.83 | 2834 | 3639 | 2421 | 399 | 14
Government | 121-150 | 121 | 150 | 250 | 8.82 | 6.87 | 2834 | 3639 | 2421 | 399 | 14
Government | 151-180 | 151 | 180 | 235 | 8.29 | 6.46 | 2834 | 3639 | 2421 | 399 | 14
Government | 181-210 | 181 | 210 | 165 | 5.82 | 4.53 | 2834 | 3639 | 2421 | 399 | 14
Government | 211-240 | 211 | 240 | 159 | 5.61 | 4.37 | 2834 | 3639 | 2421 | 399 | 14
Government | 241-270 | 241 | 270 | 132 | 4.66 | 3.63 | 2834 | 3639 | 2421 | 399 | 14
Government | 271-300 | 271 | 300 | 105 | 3.71 | 2.89 | 2834 | 3639 | 2421 | 399 | 14
Government | 301-330 | 301 | 330 | 79 | 2.79 | 2.17 | 2834 | 3639 | 2421 | 399 | 14
Government | 331-360 | 331 | 360 | 74 | 2.61 | 2.03 | 2834 | 3639 | 2421 | 399 | 14
Government | 361-390 | 361 | 390 | 32 | 1.13 | 0.88 | 2834 | 3639 | 2421 | 399 | 14
Government | 391-420 | 391 | 420 | 28 | 0.99 | 0.77 | 2834 | 3639 | 2421 | 399 | 14
Government | 421-450 | 421 | 450 | 23 | 0.81 | 0.63 | 2834 | 3639 | 2421 | 399 | 14
Government | 451-480 | 451 | 480 | 12 | 0.42 | 0.33 | 2834 | 3639 | 2421 | 399 | 14
Government | 481-510 | 481 | 510 | 12 | 0.42 | 0.33 | 2834 | 3639 | 2421 | 399 | 14
Government | 511-540 | 511 | 540 | 3 | 0.11 | 0.08 | 2834 | 3639 | 2421 | 399 | 14
Government | 541-570 | 541 | 570 | 1 | 0.04 | 0.03 | 2834 | 3639 | 2421 | 399 | 14
Government | 571-600 | 571 | 600 | 1 | 0.04 | 0.03 | 2834 | 3639 | 2421 | 399 | 14
Government | 601-630 | 601 | 630 | 0 | 0 | 0 | 2834 | 3639 | 2421 | 399 | 14
Government | 631-660 | 631 | 660 | 2 | 0.07 | 0.05 | 2834 | 3639 | 2421 | 399 | 14
Private | 0-30 | 0 | 30 | 166 | 14.59 | 7.3 | 1138 | 2274 | 830 | 302 | 6
Private | 31-60 | 31 | 60 | 195 | 17.14 | 8.58 | 1138 | 2274 | 830 | 302 | 6
Private | 61-90 | 61 | 90 | 163 | 14.32 | 7.17 | 1138 | 2274 | 830 | 302 | 6
Private | 91-120 | 91 | 120 | 124 | 10.9 | 5.45 | 1138 | 2274 | 830 | 302 | 6
Private | 121-150 | 121 | 150 | 77 | 6.77 | 3.39 | 1138 | 2274 | 830 | 302 | 6
Private | 151-180 | 151 | 180 | 49 | 4.31 | 2.15 | 1138 | 2274 | 830 | 302 | 6
Private | 181-210 | 181 | 210 | 24 | 2.11 | 1.06 | 1138 | 2274 | 830 | 302 | 6
Private | 211-240 | 211 | 240 | 10 | 0.88 | 0.44 | 1138 | 2274 | 830 | 302 | 6
Private | 241-270 | 241 | 270 | 5 | 0.44 | 0.22 | 1138 | 2274 | 830 | 302 | 6
Private | 271-300 | 271 | 300 | 2 | 0.18 | 0.09 | 1138 | 2274 | 830 | 302 | 6
Private | 301-330 | 301 | 330 | 2 | 0.18 | 0.09 | 1138 | 2274 | 830 | 302 | 6
Private | 331-360 | 331 | 360 | 3 | 0.26 | 0.13 | 1138 | 2274 | 830 | 302 | 6
Private | 361-390 | 361 | 390 | 4 | 0.35 | 0.18 | 1138 | 2274 | 830 | 302 | 6
Private | 391-420 | 391 | 420 | 2 | 0.18 | 0.09 | 1138 | 2274 | 830 | 302 | 6
Private | 421-450 | 421 | 450 | 2 | 0.18 | 0.09 | 1138 | 2274 | 830 | 302 | 6
Private | 451-480 | 451 | 480 | 2 | 0.18 | 0.09 | 1138 | 2274 | 830 | 302 | 6

## Delay Coverage
Delay Coverage
Project | Series | Ownership | Eligible | Coverage Status | Source Type | Parser Modes | Reason | Foundation Locations | Matched Locations | RawData Start-Date Matches | Dropped-by-Daily Recovered | Alias Matches | Negative Excluded | Unmatched Locations | Scope Total | Scope Source | Scope Report Date | Status Rows Considered | Status Rows Used | Duplicate Rows Dropped | Notes
TA 413 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 314 | 306 | 306 | 1 | 0 | 1 | 8 | 316 | status_quantity_primary_latest | 2026-08-12 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 414 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 335 | 280 | 280 | 0 | 0 | 1 | 55 | 352 | status_quantity_primary_latest | 2026-08-12 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 416 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 331 | 303 | 303 | 2 | 2 | 1 | 28 | 302 | status_quantity_primary_latest | 2026-07-16 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 418 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 167 | 125 | 125 | 0 | 0 | 5 | 42 | 127 | status_quantity_primary_latest | 2026-07-21 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 419 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 285 | 266 | 266 | 21 | 0 | 2 | 19 | 331 | status_quantity_primary_latest | 2026-08-11 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 421 | 4xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 319 | 301 | 301 | 2 | 0 | 1 | 18 | 309 | status_quantity_primary_latest | 2026-07-11 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 505 | 5xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 378 | 365 | 365 | 1 | 0 | 1 | 13 | 379 | status_quantity_primary_latest | 2026-07-29 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 510 | 5xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 95 | 49 | 49 | 1 | 0 | 0 | 46 | 293 | status_quantity_primary_latest | 2026-08-12 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 512 | 5xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 312 | 283 | 283 | 9 | 0 | 0 | 29 | 319 | status_quantity_primary_latest | 2026-08-12 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 513 | 5xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 109 | 33 | 33 | 0 | 0 | 0 | 76 | 619 | status_quantity_primary_latest | 2026-06-22 | 2 | 2 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TA 601 | 6xx | Government | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 189 | 124 | 124 | 3 | 0 | 2 | 65 | 292 | status_quantity_primary_latest | 2026-08-12 | 2 | 2 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TB 408 | 4xx | Private | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 485 | status_quantity_primary_latest | 2026-07-30 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TB 501 | 5xx | Private | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 235 | 233 | 233 | 0 | 0 | 4 | 2 | 238 | status_quantity_primary_latest | 2026-07-30 | 2 | 2 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TB 507 | 5xx | Private | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 377 | 281 | 281 | 7 | 0 | 2 | 96 | 556 | status_quantity_primary_latest | 2026-08-12 | 2 | 2 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TB 605 | 6xx | Private | Yes | OK_DETAIL | detail |  | Detail foundation completion dates parsed from configured sheet(s). | 361 | 259 | 259 | 7 | 0 | 0 | 102 | 523 | status_quantity_primary_latest | 2026-08-12 | 1 | 1 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.
TB 608 | 6xx | Private | Yes | DETAIL_STATUS_MISMATCH | detail |  | Detail completion dates were parsed, but counts are materially below status cumulative foundation progress; keeping detail source and flagging mapping/status mismatch. | 159 | 63 | 63 | 5 | 0 | 0 | 96 | 472 | status_quantity_primary_latest | 2026-08-11 | 10 | 10 | 0 | Negative delays are excluded from trend stats; dynamic buckets use non-negative matched delays only.

## Delay Anomalies
Delay Anomalies
Project | Series | Ownership | Phase | Location | Foundation Date | Erection Start | Delay Days | Issue | Foundation Line | Erection Line
TA 413 | 4xx | Government | 60-80 | 39/8 | 2025-01-24 | 2024-03-26 | -304 | NEGATIVE_DELAY_EXCLUDED
TA 413 | 4xx | Government | 20-40 | 37/1 | 2024-09-23 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 20-40 | 3/8 | 2024-10-05 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 20-40 | 3/9 | 2024-10-09 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 20-40 | 37/0 | 2024-10-14 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 20-40 | 3/7 | 2024-10-19 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 20-40 | 3/6 | 2024-10-22 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 40-60 | 3/4 | 2024-10-29 |  |  | UNMATCHED_LOCATION
TA 413 | 4xx | Government | 80-100+ | 36C/0-N | 2026-02-08 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 121/4 | 2024-11-29 | 2024-03-27 | -247 | NEGATIVE_DELAY_EXCLUDED
TA 414 | 4xx | Government | 0-20 | 249/2 | 2025-01-03 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 0-20 | 172/0 | 2025-03-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 165/2 | 2025-05-15 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 20-40 | 224/0 | 2025-11-08 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 165/6 | 2025-12-23 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 257/0 | 2025-12-23 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 170/0 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 216/2 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 216/3 | 2026-01-12 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 162/0 | 2026-01-13 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 40-60 | 194/0 | 2026-01-17 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 165/4 | 2026-01-22 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 211/4 | 2026-01-22 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 193/0 | 2026-01-23 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 233/0 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 236/0 | 2026-01-28 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 168/0 | 2026-01-29 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 188/0 | 2026-01-29 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 211/0 | 2026-02-01 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 235/0 | 2026-02-07 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 232/4 | 2026-02-20 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 173/0 | 2026-02-27 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 219/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 163/0 | 2026-03-04 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 60-80 | 231/0 | 2026-03-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 150/1 | 2026-03-24 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 180/0 | 2026-04-05 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 156/0 | 2026-04-06 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 150/0 | 2026-04-12 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 131/0 | 2026-04-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 155/0 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 200/0 | 2026-04-19 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 131/1 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 189/0 | 2026-04-28 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 169/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 232/3 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 129/0 | 2026-05-11 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 145/1 | 2026-05-16 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 206/1 | 2026-05-17 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 229B/0 | 2026-05-22 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 229A/0 | 2026-05-28 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 154/0 | 2026-06-01 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 212/0 | 2026-06-01 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 254/0 | 2026-06-06 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 132/2 | 2026-06-07 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 208/0 | 2026-06-08 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 130/0 | 2026-06-12 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 152/0 | 2026-06-12 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 253/0 | 2026-06-15 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 165/3 | 2026-06-17 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 165/1 | 2026-06-21 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 202/0 | 2026-06-21 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 135/0 | 2026-06-22 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 153/2 | 2026-06-26 |  |  | UNMATCHED_LOCATION
TA 414 | 4xx | Government | 80-100+ | 200/1 | 2026-06-26 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 66/0 | 2025-12-19 | 2025-12-05 | -14 | NEGATIVE_DELAY_EXCLUDED
TA 416 | 4xx | Government | 80-100+ | 4/0-5/0 | 2025-10-14 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 5/0-7/6 | 2025-10-22 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 7/6-8B/0 | 2025-10-25 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 34/0-35/0 | 2025-10-28 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 35/0-36/0 | 2025-11-01 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 33/0-34/0 | 2025-11-04 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 31/0-33/0 | 2025-11-10 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 30/0-31/0 | 2025-11-16 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 12/0-14/0 | 2025-11-20 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 20/0-21/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 19/0-20/0 | 2025-12-06 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 0/0-2/0 | 2026-02-06 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 2/0-3/0 | 2026-02-10 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 36/0-37/0 | 2026-02-10 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 14/0-17/0 | 2026-02-14 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 37/0-38/11 | 2026-02-16 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 8B/0-12/0 | 2026-02-18 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 38/11-40/0 | 2026-02-20 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 21/0-25/0 | 2026-02-23 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 17/0-19/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 25/0-30/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 40/0-47/0 | 2026-05-03 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 52/1-53/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 53/0-54/0 | 2026-05-09 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 54/0-56/6 | 2026-06-29 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 56/6-64/0 | 2026-07-03 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 64/0-Gantry | 2026-07-08 |  |  | UNMATCHED_LOCATION
TA 416 | 4xx | Government | 80-100+ | 52/1-64/0 | 2026-07-12 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 0-20 | 54/4 | 2024-07-11 | 2024-01-09 | -184 | NEGATIVE_DELAY_EXCLUDED
TA 418 | 4xx | Government | 20-40 | 46/14 | 2024-10-11 | 2024-01-07 | -278 | NEGATIVE_DELAY_EXCLUDED
TA 418 | 4xx | Government | 20-40 | 35/06 | 2024-11-13 | 2024-11-05 | -8 | NEGATIVE_DELAY_EXCLUDED
TA 418 | 4xx | Government | 40-60 | 45/2 | 2025-04-01 | 2025-03-28 | -4 | NEGATIVE_DELAY_EXCLUDED
TA 418 | 4xx | Government | 80-100+ | 57/0 | 2025-12-20 | 2025-01-16 | -338 | NEGATIVE_DELAY_EXCLUDED
TA 418 | 4xx | Government | 0-20 | 35/6 | 2024-08-21 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 20-40 | 45/02 | 2024-12-20 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 60-80 | 46/1 | 2025-06-30 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 42/0 - 43/0 | 2025-09-28 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 41/0 - 42/0 | 2025-10-06 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 36/0 - 36/1 | 2025-11-03 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 35/0 - 36/0 | 2025-11-17 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 34/0 - 35/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 59/1 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 40/0 - 41/0 | 2025-12-26 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 33/6 - 34/0 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 33/5 - 33/6 | 2026-01-30 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 33/0 - 33/5 | 2026-02-09 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 39/0-40/0 | 2026-02-10 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 32/0-33/0 | 2026-02-22 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 45/1-46/0 | 2026-03-03 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 43/0 - 44/0 | 2026-03-11 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 45/0 - 45/1 | 2026-03-12 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 44/0-45/0 | 2026-03-18 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 56/0-56/3 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 61/0-62/0 | 2026-04-15 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 63/0-GNTY | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 55/0-56/0 | 2026-05-03 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 37/0-38/0 | 2026-05-12 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 36/01 - 37/00 | 2026-05-23 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 38/0-39/0 | 2026-05-26 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 52/00 - 53/00 | 2026-06-06 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 51/00 - 52/00 | 2026-06-08 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 56/03 - 57/00 | 2026-06-09 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 54/00 - 55/00 | 2026-06-19 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 53/00 - 54/00 | 2026-06-20 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 57/00 - 58/00 | 2026-06-23 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 48A/0-49/0 | 2026-06-26 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 62/0-63/0 | 2026-06-26 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 59/0 - 60/0 | 2026-06-27 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 58/0 - 59/0 | 2026-06-28 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 60/0-61/0 | 2026-07-04 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 48/0-48A/0 | 2026-07-05 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 47/0-48/0 | 2026-07-12 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 49/0-50/0 | 2026-07-12 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 50/0-51/0 | 2026-07-12 |  |  | UNMATCHED_LOCATION
TA 418 | 4xx | Government | 80-100+ | 46/0-46/7 | 2026-07-21 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 0-20 | 6/9 | 2024-07-14 | 2024-01-06 | -190 | NEGATIVE_DELAY_EXCLUDED
TA 419 | 4xx | Government | 60-80 | 52/1 | 2026-05-31 | 2026-04-03 | -58 | NEGATIVE_DELAY_EXCLUDED
TA 419 | 4xx | Government | 40-60 | 46/0 | 2025-08-31 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 43/1 | 2025-11-13 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 40-60 | 36/9 | 2025-11-23 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 63B/6 | 2026-01-02 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 77/0 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 60/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 95A/0 | 2026-05-28 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 60-80 | 72/0 | 2026-06-05 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 59/0 | 2026-06-23 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 63B/3 | 2026-06-23 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 39/0 | 2026-06-29 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 96/2 | 2026-07-04 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 79/0 | 2026-07-18 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 98/0 | 2026-07-18 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 86/1 | 2026-07-23 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 93C/0 | 2026-07-25 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 51/0 | 2026-07-30 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 82/0 | 2026-07-31 |  |  | UNMATCHED_LOCATION
TA 419 | 4xx | Government | 80-100+ | 99/0 | 2026-08-04 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 20-40 | 30/2 | 2024-12-21 | 2024-12-02 | -19 | NEGATIVE_DELAY_EXCLUDED
TA 421 | 4xx | Government | 80-100+ | 8/11 | 2025-05-22 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 4/16 | 2025-05-31 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 19/0-20/0 | 2025-10-19 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 18/0-19/0 | 2025-10-21 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 7/0 - 8/0 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | Gantry - 1/0 | 2026-02-01 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 8/2 - 8/3 | 2026-02-04 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 1/0-1A/0 | 2026-02-08 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 1A/0 - 1B/0 | 2026-02-11 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 4/12 - 5/0 | 2026-02-12 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 8/0 - 8/1 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 8/1-8/2 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 1C/0 - 2/0 | 2026-02-25 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 5/0 - 6/0 | 2026-03-02 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 3/0-4/0 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 43A/0 - 43A/1 | 2026-06-18 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 43A/1 - 43B/0 | 2026-06-21 |  |  | UNMATCHED_LOCATION
TA 421 | 4xx | Government | 80-100+ | 43B/0 - 44/0 | 2026-06-24 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 177/0 | 2026-05-15 | 2025-12-04 | -162 | NEGATIVE_DELAY_EXCLUDED
TA 505 | 5xx | Government | 80-100+ | 138/0 | 2025-11-29 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 149B/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 158/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 148C/0 | 2026-02-21 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 148B/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 157/0 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 144/0 | 2026-03-21 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 143/0 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 134/0 | 2026-04-09 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 129/0 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 133/0 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 129/1 | 2026-04-23 |  |  | UNMATCHED_LOCATION
TA 505 | 5xx | Government | 80-100+ | 179/3 | 2026-06-30 |  |  | UNMATCHED_LOCATION
TA 510 | 5xx | Government | 0-20 | 155/1 | 2025-02-17 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 155/4 | 2025-02-22 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 155/3 | 2025-02-25 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 155/5 | 2025-02-27 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 156/0 | 2025-03-12 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 156/1 | 2025-03-13 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 156/3 | 2025-03-16 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 156/4 | 2025-03-25 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 137/0 | 2025-04-27 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 139/4 | 2025-04-28 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 138/2 | 2025-10-05 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 192/7 | 2026-01-21 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 0-20 | 192/12 | 2026-01-25 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 157B/0 | 2026-03-11 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 157A/0 | 2026-03-22 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 157/2 | 2026-03-23 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 192/9 | 2026-04-07 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 193/2 | 2026-04-13 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 193/1 | 2026-04-19 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 193/5 | 2026-04-20 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 139/0 | 2026-04-21 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 193/0 | 2026-04-28 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 193/4 | 2026-04-29 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 192/8 | 2026-05-06 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 167/2 | 2026-05-13 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 157B/1 | 2026-05-16 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 167/3 | 2026-05-17 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 133/0 | 2026-05-18 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 153/0 | 2026-05-20 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 167/4 | 2026-05-20 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 133/1 | 2026-05-23 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 167/1 | 2026-05-26 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 194/0 | 2026-05-27 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 150/2 | 2026-05-31 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 153/1 | 2026-05-31 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 155/0 | 2026-05-31 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 150/4 | 2026-06-06 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 155/2 | 2026-06-06 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 154/0 | 2026-06-10 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 150/3 | 2026-06-11 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 154/1 | 2026-06-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 160/3 | 2026-06-14 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 150/1 | 2026-06-15 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 154/2 | 2026-06-20 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 148A/0 | 2026-06-25 |  |  | UNMATCHED_LOCATION | FDN
TA 510 | 5xx | Government | 20-40 | 152/1 | 2026-06-25 |  |  | UNMATCHED_LOCATION | FDN
TA 512 | 5xx | Government | 20-40 | 31/11 | 2025-06-10 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 20-40 | 27/2 | 2025-06-17 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 2/1 | 2025-08-13 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 4/5 | 2025-09-03 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 40-60 | 36/4 | 2025-09-26 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 3/2 | 2025-10-28 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 31/0 | 2025-10-30 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 37/1 | 2025-11-03 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 32/3 | 2025-12-02 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 32/6 | 2025-12-06 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 2A/3 | 2025-12-09 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 60-80 | 4/1 | 2025-12-14 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 32/7 | 2025-12-16 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 36/1 | 2025-12-30 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 33/1 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 16/3 | 2026-02-07 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 32/8 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 47/0 | 2026-04-08 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 44/1 | 2026-04-15 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 45/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 46/0 | 2026-04-24 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 34/1 | 2026-04-29 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 16/0 | 2026-06-04 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 1/2 | 2026-06-24 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 24/0 | 2026-06-25 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 1/1 | 2026-07-01 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 32/10 | 2026-07-03 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 1/0 | 2026-07-09 |  |  | UNMATCHED_LOCATION
TA 512 | 5xx | Government | 80-100+ | 30/15 | 2026-08-05 |  |  | UNMATCHED_LOCATION
TA 513 | 5xx | Government | 0-20 | 24/2 | 2025-04-04 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 24/1 | 2025-04-07 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 30/2 | 2025-04-12 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 23/6 | 2025-04-14 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 23/5 | 2025-04-16 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 31/1 | 2025-04-17 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 30/3 | 2025-04-22 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 37/1 | 2025-04-24 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 30/1 | 2025-04-25 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 30/2 | 2025-04-28 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 24/3 | 2025-04-29 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 31/2 | 2025-04-30 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 3/5 | 2025-05-20 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 55/7 | 2025-05-20 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 23/3 | 2025-05-24 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 3/6 | 2025-05-24 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 3/10 | 2025-05-27 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 32B/1 | 2025-05-28 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 21/7 | 2025-06-02 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 21/6 | 2025-06-05 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 23/1 | 2025-06-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 23/3 | 2025-06-09 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 23/2 | 2025-06-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 23/4 | 2025-06-15 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 18/4 | 2025-06-28 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 14/4 | 2025-07-01 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 26/1 | 2025-07-03 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 14/3 | 2025-07-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 14/2 | 2025-07-13 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 56/0 | 2025-07-15 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 15B/4 | 2025-07-21 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 55/0 | 2025-07-24 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 36/3 | 2025-08-20 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 36/4 | 2025-09-01 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 30/0 | 2025-09-19 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 24/0 | 2025-09-24 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 19/0 | 2025-10-01 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 28/0 | 2025-10-05 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 18/0 | 2025-10-06 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 55/1 | 2026-03-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 55/2 | 2026-04-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 55/4 | 2026-05-04 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 52/0 | 2026-05-05 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 52/1 | 2026-05-10 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 52/5 | 2026-05-11 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 55/3 | 2026-05-15 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 64/2 | 2026-05-16 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 30/0 | 2026-05-17 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 64/5 | 2026-05-19 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 64/3 | 2026-05-21 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 28/1 | 2026-05-22 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 51/3 | 2026-05-23 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 64/4 | 2026-05-25 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 64/6 | 2026-05-29 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 61/2 | 2026-05-30 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 74/9 | 2026-05-30 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 64/1 | 2026-06-01 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 54/1 | 2026-06-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 74/8 | 2026-06-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 55/1 | 2026-06-09 |  |  | UNMATCHED_LOCATION | S-F
TA 513 | 5xx | Government | 0-20 | 62/1 | 2026-06-09 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 61/0 | 2026-06-14 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 74/7 | 2026-06-14 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 51/1 | 2026-06-17 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 61/1 | 2026-06-18 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 51/0 | 2026-06-25 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 54/2 | 2026-06-27 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 44/2 | 2026-07-08 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 46/1 | 2026-07-10 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 36/5 | 2026-07-16 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 43/0 | 2026-07-17 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 45/2 | 2026-07-20 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 45/1 | 2026-08-01 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 42/1 | 2026-08-07 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 12/4 | 2026-08-09 |  |  | UNMATCHED_LOCATION | S-P
TA 513 | 5xx | Government | 0-20 | 45/0 | 2026-08-11 |  |  | UNMATCHED_LOCATION | S-P
TA 601 | 6xx | Government | 0-20 | 56/7 | 2026-01-16 | 2025-12-15 | -32 | NEGATIVE_DELAY_EXCLUDED
TA 601 | 6xx | Government | 20-40 | 50/0 | 2026-04-16 | 2025-06-26 | -294 | NEGATIVE_DELAY_EXCLUDED
TA 601 | 6xx | Government | 0-20 | 81/2 | 2025-08-07 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 80/4 | 2025-10-27 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 77/8 | 2025-11-13 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 60/8 | 2025-11-23 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 59/1 | 2025-11-29 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 77/6 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 73/1 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 56/1 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 73/2 | 2025-12-24 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 79/1 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 84/6 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 94/1 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 99/12 | 2026-01-06 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 0-20 | 83/0 | 2026-01-14 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 78/3 | 2026-02-06 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 50/1 | 2026-02-12 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 89/1 | 2026-03-03 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 90/0 | 2026-03-18 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 53/3 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 70/4 | 2026-04-16 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 70/3 | 2026-04-18 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 66/1 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 20-40 | 48/7 | 2026-05-10 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 69/1 | 2026-05-20 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 68/2 | 2026-05-23 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 68/0 | 2026-05-30 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 72/1 | 2026-06-01 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 73/0 | 2026-06-05 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 75/2 | 2026-06-07 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 75/3 | 2026-06-09 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 75/1 | 2026-06-12 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 77/5 | 2026-06-15 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 60/4 | 2026-06-19 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 48/0 | 2026-06-22 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 51/4 | 2026-06-23 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 102/0 | 2026-06-25 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 51/5 | 2026-06-26 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 51/3 | 2026-07-08 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 52/3 | 2026-07-10 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 71/0 | 2026-07-10 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 63/2 | 2026-07-13 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 58/0 | 2026-07-15 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 98/0 | 2026-07-15 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 76/0 | 2026-07-16 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 101/4 | 2026-07-17 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 49/3 | 2026-07-17 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 65/2 | 2026-07-18 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 78/1 | 2026-07-21 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 53/6 | 2026-07-23 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 101/9 | 2026-07-24 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 40-60 | 78/0 | 2026-07-26 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 60-80 | 52/4 | 2026-07-27 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 60-80 | 63/1 | 2026-07-27 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 60-80 | 96/8 | 2026-07-27 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 60-80 | 80/2 | 2026-07-28 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 60-80 | 96/7 | 2026-07-30 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 60-80 | 97/4 | 2026-08-01 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 60-80 | 82/2 | 2026-08-03 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 60-80 | 97/3 | 2026-08-03 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 60-80 | 96/4 | 2026-08-06 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 60-80 | 101/8 | 2026-08-08 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 60-80 | 63/3 | 2026-08-09 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 60-80 | 96/5 | 2026-08-09 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 60-80 | 96/6 | 2026-08-11 |  |  | UNMATCHED_LOCATION
TA 601 | 6xx | Government | 60-80 | 49/5 | 2026-08-12 |  |  | UNMATCHED_LOCATION
TB 408 | 4xx | Private | 0-20 | 0 | 2023-10-01 |  |  | UNMATCHED_LOCATION
TB 408 | 4xx | Private | 0-20 | 1 | 2024-09-01 |  |  | UNMATCHED_LOCATION
TB 408 | 4xx | Private | 0-20 | 2 | 2024-11-01 |  |  | UNMATCHED_LOCATION
TB 408 | 4xx | Private | 0-20 | 3 | 2024-11-01 |  |  | UNMATCHED_LOCATION
TB 408 | 4xx | Private | 0-20 | 4 | 2024-11-01 |  |  | UNMATCHED_LOCATION
TB 408 | 4xx | Private | 0-20 | 5 | 2024-12-01 |  |  | UNMATCHED_LOCATION
TB 501 | 5xx | Private | 80-100+ | 8D/0A | 2025-12-07 | 2025-12-04 | -3 | NEGATIVE_DELAY_EXCLUDED | 220kV | 220kV
TB 501 | 5xx | Private | 80-100+ | 6/0 | 2026-02-19 | 2026-02-17 | -2 | NEGATIVE_DELAY_EXCLUDED | 132kV | 132kV
TB 501 | 5xx | Private | 80-100+ | 2/0 | 2026-06-19 | 2026-06-17 | -2 | NEGATIVE_DELAY_EXCLUDED | 132kV | 132kV
TB 501 | 5xx | Private | 80-100+ | 1/0 | 2026-06-23 | 2026-06-20 | -3 | NEGATIVE_DELAY_EXCLUDED | 132kV | 132kV
TB 501 | 5xx | Private | 80-100+ | SC-2 | 2026-06-19 |  |  | UNMATCHED_LOCATION | 132kV
TB 501 | 5xx | Private | 80-100+ | SC-1 | 2026-07-24 |  |  | UNMATCHED_LOCATION | 132kV
TB 507 | 5xx | Private | 20-40 | 71/2 | 2025-10-30 | 2025-01-14 | -289 | NEGATIVE_DELAY_EXCLUDED | MAIN | MAIN
TB 507 | 5xx | Private | 60-80 | 10/9 | 2026-06-27 | 2025-07-10 | -352 | NEGATIVE_DELAY_EXCLUDED | MAIN | MAIN
TB 507 | 5xx | Private | 0-20 | 66/2 | 2025-03-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 64/3 | 2025-03-07 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 96/2 | 2025-03-07 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 64/4 | 2025-03-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 99/1 | 2025-03-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 66/3 | 2025-03-11 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 64/6 | 2025-03-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 64/5 | 2025-03-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 71/1 | 2025-04-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 91/2 | 2025-04-16 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 51/2 | 2025-04-17 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 95/2 | 2025-04-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 51/3 | 2025-04-23 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 99/2 | 2025-04-25 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 104B/1 | 2025-04-29 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 62/4 | 2025-04-29 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 62/5 | 2025-05-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 96/0 | 2025-06-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 106/0 | 2025-07-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 0-20 | 125/1 | 2025-07-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 125/0 | 2025-07-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 99/3 | 2025-07-29 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 99/0 | 2025-08-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 99/4 | 2025-08-22 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 63/1 | 2025-08-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 56/4 | 2025-08-26 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 56/2 | 2025-08-27 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 56/5 | 2025-08-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 99A/0 | 2025-08-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 57/0 | 2025-09-10 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 59/0 | 2025-09-12 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 64/0 | 2025-09-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 58/0 | 2025-09-17 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 125/2 | 2025-09-18 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 56/1 | 2025-09-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 20-40 | 48/0 | 2025-09-25 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 71/0 | 2025-11-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 98B/2 | 2025-12-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 117/0 | 2025-12-13 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 124/0 | 2025-12-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 122/2 | 2026-01-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 69/3 | 2026-01-15 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 108/0 | 2026-01-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 10/3 | 2026-01-23 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 109/0 | 2026-01-23 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 7/0 | 2026-02-11 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 1/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 117/2 | 2026-02-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 6/0 | 2026-02-28 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 157/0 | 2026-03-04 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 98B/1 | 2026-03-11 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 2/0 | 2026-03-13 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 103/0 | 2026-03-19 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 5/2 | 2026-03-31 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 5/1 | 2026-04-02 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 3/1 | 2026-04-04 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 5/0 | 2026-04-12 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 3/3 | 2026-04-18 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 2/0 | 2026-05-02 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 155/0 | 2026-05-03 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 154/1B | 2026-05-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 154/2B | 2026-05-08 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 154/1A | 2026-05-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 154/2A | 2026-05-09 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 13/2 | 2026-05-14 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 4/0 | 2026-05-15 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 40-60 | 1/0 | 2026-05-27 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 40-60 | 27/0 | 2026-05-27 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 1A/0 | 2026-05-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 3A/1 | 2026-05-31 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 60-80 | 5/3 | 2026-06-03 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 3A/0 | 2026-06-05 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 60-80 | 3B/0 | 2026-06-15 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 60-80 | 5/0 | 2026-06-15 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 56/3 | 2026-06-17 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 107/1 | 2026-06-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 43/0 | 2026-06-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 5A/0 | 2026-06-29 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 60-80 | 121/0 | 2026-06-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 42/0 | 2026-06-30 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 41/3 | 2026-07-04 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 42/1 | 2026-07-11 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 7/0 | 2026-07-16 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 41/1 | 2026-07-17 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 122/1 | 2026-07-20 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 122/0 | 2026-07-24 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 102/0 | 2026-07-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 39/4 | 2026-07-28 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 2A/0 | 2026-07-30 |  |  | UNMATCHED_LOCATION | 765kV
TB 507 | 5xx | Private | 60-80 | 45/3 | 2026-07-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 5A/0 | 2026-07-31 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 5B/0 | 2026-08-03 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 39/3 | 2026-08-04 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 40/0 | 2026-08-06 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 40/1 | 2026-08-12 |  |  | UNMATCHED_LOCATION | MAIN
TB 507 | 5xx | Private | 60-80 | 5C/0 | 2026-08-12 |  |  | UNMATCHED_LOCATION | MAIN
TB 605 | 6xx | Private | 0-20 | 18/0 | 2025-10-16 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 22/0 | 2025-10-31 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 74/0 | 2025-11-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 72/0 | 2025-11-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 17/0 | 2025-11-23 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 20/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | AP116 | 2025-11-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 40/0 | 2025-12-03 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 23/0 | 2025-12-09 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 29/0 | 2025-12-10 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 0-20 | 85/1 | 2025-12-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 106/1 | 2025-12-17 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 0-20 | 102/1 | 2025-12-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 138/2 | 2025-12-31 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 137/2 | 2026-01-10 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 152/2 | 2026-01-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP138 | 2026-01-20 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | 153/0 | 2026-02-05 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP139 | 2026-02-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP130 | 2026-02-12 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP92 | 2026-02-13 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP91 | 2026-02-27 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 20-40 | AP159 | 2026-02-28 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP149 | 2026-03-10 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 67/2 | 2026-03-13 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP127 | 2026-03-15 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP148 | 2026-03-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP152 | 2026-03-26 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP108 | 2026-03-28 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 56/3 | 2026-03-31 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP125 | 2026-04-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 65/2 | 2026-04-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP109 | 2026-04-12 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP126 | 2026-04-15 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP1 | 2026-04-18 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | AP61 | 2026-04-21 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP165 | 2026-04-22 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 56/2 | 2026-04-25 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP59 | 2026-04-27 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP41 | 2026-04-30 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | AP6 | 2026-04-30 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | AP64 | 2026-05-01 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP144 | 2026-05-07 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 61/1 | 2026-05-08 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 57/1 | 2026-05-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP161 | 2026-05-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP163 | 2026-05-11 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 56/4 | 2026-05-13 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 62/2 | 2026-05-14 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP110 | 2026-05-14 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP57 | 2026-05-15 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 159/3 | 2026-05-16 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 50A/2 | 2026-05-17 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | AP162 | 2026-05-17 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 62/1 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP128 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP63 | 2026-05-18 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 159/2 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 57/2 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP112 | 2026-05-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 159/1 | 2026-05-22 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 60/1 | 2026-05-22 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 143/1 | 2026-05-23 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 50A/1 | 2026-05-23 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 40-60 | AP113 | 2026-05-23 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP158 | 2026-05-23 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP7 | 2026-05-24 |  |  | UNMATCHED_LOCATION | LILO
TB 605 | 6xx | Private | 40-60 | AP84 | 2026-05-24 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP55 | 2026-05-25 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 65/5 | 2026-05-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP105 | 2026-05-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP168 | 2026-05-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP174 | 2026-05-30 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP167 | 2026-05-31 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | AP81 | 2026-05-31 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 40-60 | 65/3 | 2026-06-03 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 60-80 | 50A/4 | 2026-06-06 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 60-80 | AP173 | 2026-06-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 60-80 | AP58 | 2026-06-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 60-80 | 143/2 | 2026-06-09 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 60-80 | 42/1 | 2026-06-09 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 60-80 | AP175 | 2026-06-10 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 60-80 | AP78 | 2026-06-10 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 60-80 | 77/3 | 2026-06-12 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 60-80 | 37/2 | 2026-06-14 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 60-80 | 47/3 | 2026-06-15 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 60-80 | 180/1 | 2026-06-19 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 60-80 | 8/1 | 2026-06-22 |  |  | UNMATCHED_LOCATION | LILO
TB 605 | 6xx | Private | 60-80 | AP62 | 2026-06-22 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 60-80 | AP48 | 2026-06-23 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 60-80 | AP6 | 2026-06-24 |  |  | UNMATCHED_LOCATION | LILO
TB 605 | 6xx | Private | 60-80 | 171/1 | 2026-06-25 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 60-80 | AP151 | 2026-06-25 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 60-80 | 56/1 | 2026-06-26 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 60-80 | AP180 | 2026-06-27 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 60-80 | AP8 | 2026-06-27 |  |  | UNMATCHED_LOCATION | LILO
TB 605 | 6xx | Private | 60-80 | AP5 | 2026-06-30 |  |  | UNMATCHED_LOCATION | LILO
TB 605 | 6xx | Private | 60-80 | AP176 | 2026-07-06 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 60-80 | AP8 | 2026-07-27 |  |  | UNMATCHED_LOCATION | Jammu
TB 605 | 6xx | Private | 60-80 | AP182 | 2026-07-31 |  |  | UNMATCHED_LOCATION | Punjab
TB 605 | 6xx | Private | 60-80 | AP4 | 2026-08-11 |  |  | UNMATCHED_LOCATION | LILO
TB 605 | 6xx | Private | 60-80 | AP9 | 2026-08-11 |  |  | UNMATCHED_LOCATION | LILO
TB 608 | 6xx | Private | 0-20 | 75/5 | 2025-11-15 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 34/3 | 2025-11-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 101/0 | 2025-11-19 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 33/2 | 2025-11-22 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 29/0 | 2025-11-25 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 100/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 71/0 | 2025-11-30 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 29/1 | 2025-12-02 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 5/0 | 2025-12-10 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 108/0 | 2025-12-12 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 75/4 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 99/0 | 2025-12-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 102/0 | 2025-12-19 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 111/1 | 2025-12-21 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 83/0 | 2025-12-21 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 91/0 | 2025-12-21 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 93/0 | 2025-12-21 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 34/1 | 2025-12-22 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 25/1 | 2025-12-23 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 4/1 | 2025-12-25 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 91/1 | 2025-12-27 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 91/2 | 2025-12-28 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 114/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 86/0 | 2025-12-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 41/2 | 2026-01-02 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 11/2 | 2026-01-03 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 97/0 | 2026-01-09 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 113/0 | 2026-01-11 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 91/5 | 2026-01-12 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 110/0 | 2026-01-13 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 76/0 | 2026-01-15 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 69/4 | 2026-01-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 75/1 | 2026-01-19 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 11/1 | 2026-01-24 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 123/2 | 2026-01-25 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 129/1 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 34/2 | 2026-01-27 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 132/1 | 2026-01-29 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 91/7 | 2026-01-29 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 96/0 | 2026-01-30 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 128/0 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 131/0 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 91/4 | 2026-01-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 59/1 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 73/6 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 76/1 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 96/1 | 2026-02-05 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 104/0 | 2026-02-08 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 0-20 | 126/0 | 2026-02-10 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 72/7 | 2026-02-11 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 95/3 | 2026-02-14 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 129/2 | 2026-02-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 6/1 | 2026-02-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 95/0 | 2026-02-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 131/1 | 2026-02-19 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 30/0 | 2026-02-20 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 10/3 | 2026-02-22 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 124/0 | 2026-02-22 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 127/0 | 2026-02-25 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 132/2 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 132/3 | 2026-02-28 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 31/0 | 2026-03-06 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 35/0 | 2026-03-08 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 10/1 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 129/0 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 130/0 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 82/2 | 2026-03-10 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 82/1 | 2026-03-11 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 27/0 | 2026-03-14 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 125/0 | 2026-03-19 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 6/0 | 2026-03-28 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 7/0 | 2026-03-30 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 34/0 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 7/2 | 2026-03-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 9/0 | 2026-04-14 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 107/1 | 2026-04-19 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 7/1 | 2026-04-21 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 106/0 | 2026-04-30 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 1/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 38/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 61/0 | 2026-05-06 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 105/0 | 2026-05-07 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 39/0 | 2026-05-12 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 3/0 | 2026-05-17 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 4/0 | 2026-05-24 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 91/9 | 2026-06-18 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 5/1 | 2026-06-21 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 118/0 | 2026-06-30 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 42/0 | 2026-06-30 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 73/5 | 2026-07-10 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 119/0 | 2026-07-19 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 14/0 | 2026-07-27 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 62/3 | 2026-07-29 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 20/1 | 2026-07-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 68/0 | 2026-07-31 |  |  | UNMATCHED_LOCATION
TB 608 | 6xx | Private | 20-40 | 37/0 | 2026-08-04 |  |  | UNMATCHED_LOCATION

## Scope Snapshot
Scope Snapshot
Project | Project Rollup Key | Project Base Code | Series | Ownership | Scope Total | Scope Source | Scope Report Date | Status Rows Considered | Status Rows Used | Duplicate Rows Dropped | Quantity Primary Sum | Cumulative Progress Sum | Balance Progress Sum | Fallback Foundation Done Count | Coverage Status | Coverage Reason | Note
TA 413 | ta413 | TA 413 | 4xx | Government | 316 | status_quantity_primary_latest | 2026-08-12 | 1 | 1 | 0 | 316 | 316 | 0 | 314 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 414 | ta414 | TA 414 | 4xx | Government | 352 | status_quantity_primary_latest | 2026-08-12 | 1 | 1 | 0 | 352 | 336 | 16 | 335 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 416 | ta416 | TA 416 | 4xx | Government | 302 | status_quantity_primary_latest | 2026-07-16 | 1 | 1 | 0 | 302 | 302 | 0 | 331 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 418 | ta418 | TA 418 | 4xx | Government | 127 | status_quantity_primary_latest | 2026-07-21 | 1 | 1 | 0 | 127 | 127 | 0 | 167 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 419 | ta419 | TA 419 | 4xx | Government | 331 | status_quantity_primary_latest | 2026-08-11 | 1 | 1 | 0 | 331 | 287 | 44 | 285 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 421 | ta421 | TA 421 | 4xx | Government | 309 | status_quantity_primary_latest | 2026-07-11 | 1 | 1 | 0 | 309 | 309 | 0 | 319 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 505 | ta505 | TA 505 | 5xx | Government | 379 | status_quantity_primary_latest | 2026-07-29 | 1 | 1 | 0 | 379 | 379 | 0 | 378 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 510 | ta510 | TA 510 | 5xx | Government | 293 | status_quantity_primary_latest | 2026-08-12 | 1 | 1 | 0 | 293 | 95 | 198 | 95 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 512 | ta512 | TA 512 | 5xx | Government | 319 | status_quantity_primary_latest | 2026-08-12 | 1 | 1 | 0 | 319 | 317 | 2 | 312 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 513 | ta513 | TA 513 | 5xx | Government | 619 | status_quantity_primary_latest | 2026-06-22 | 2 | 2 | 0 | 619 | 98 | 521 | 109 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TA 601 | ta601 | TA 601 | 6xx | Government | 292 | status_quantity_primary_latest | 2026-08-12 | 2 | 2 | 0 | 292 | 189 | 103 | 189 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TB 408 | tb408 | TB 408 | 4xx | Private | 485 | status_quantity_primary_latest | 2026-07-30 | 1 | 1 | 0 | 485 | 485 | 0 | 6 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TB 501 | tb501 | TB 501 | 5xx | Private | 238 | status_quantity_primary_latest | 2026-07-30 | 2 | 2 | 0 | 238 | 238 | 0 | 235 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TB 507 | tb507 | TB 507 | 5xx | Private | 556 | status_quantity_primary_latest | 2026-08-12 | 2 | 2 | 0 | 556 | 385 | 171 | 377 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TB 605 | tb605 | TB 605 | 6xx | Private | 523 | status_quantity_primary_latest | 2026-08-12 | 1 | 1 | 0 | 523 | 434 | 89 | 361 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s).
TB 608 | tb608 | TB 608 | 6xx | Private | 472 | status_quantity_primary_latest | 2026-08-11 | 10 | 10 | 0 | 472 | 158 | 160 | 159 | DETAIL_STATUS_MISMATCH | Detail completion dates were parsed, but counts are materially below status cumulative foundation progress; keeping detail source and flagging mapping/status mismatch.

## Mechanism Summary - Project
Mechanism Summary - Project
Project | Cohort Window | Cohort Months | Start Window | Start Months | Foundations Total | Matched Non-Negative | Starts In Window | % of All Foundations | % Within Matched | Match Coverage % | Min Foundations Threshold | Threshold Applied
TA 413 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 314 | 305 | 64 | 20.38 | 20.98 | 97.13 | 5 | Yes
TA 413 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 314 | 305 | 88 | 28.03 | 28.85 | 97.13 | 5 | Yes
TA 413 | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 33 | 33 | 13 | 39.39 | 39.39 | 100 | 5 | Yes
TA 413 | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 33 | 33 | 13 | 39.39 | 39.39 | 100 | 5 | Yes
TA 413 | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 103 | 102 | 21 | 20.39 | 20.59 | 99.03 | 5 | Yes
TA 413 | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 103 | 102 | 33 | 32.04 | 32.35 | 99.03 | 5 | Yes
TA 413 | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 119 | 117 | 25 | 21.01 | 21.37 | 98.32 | 5 | Yes
TA 413 | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 119 | 117 | 30 | 25.21 | 25.64 | 98.32 | 5 | Yes
TA 414 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 335 | 279 | 1 | 0.3 | 0.36 | 83.28 | 5 | Yes
TA 414 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 335 | 279 | 31 | 9.25 | 11.11 | 83.28 | 5 | Yes
TA 414 | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 54 | 38 | 0 | 0 | 0 | 70.37 | 5 | Yes
TA 414 | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 54 | 38 | 4 | 7.41 | 10.53 | 70.37 | 5 | Yes
TA 414 | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 22 | 8 | 1 | 4.55 | 12.5 | 36.36 | 5 | Yes
TA 414 | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 22 | 8 | 2 | 9.09 | 25 | 36.36 | 5 | Yes
TA 414 | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 222 | 198 | 0 | 0 | 0 | 89.19 | 5 | Yes
TA 414 | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 222 | 198 | 21 | 9.46 | 10.61 | 89.19 | 5 | Yes
TA 416 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 331 | 302 | 45 | 13.6 | 14.9 | 91.24 | 5 | Yes
TA 416 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 331 | 302 | 78 | 23.56 | 25.83 | 91.24 | 5 | Yes
TA 416 | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 28 | 25 | 8 | 28.57 | 32 | 89.29 | 5 | Yes
TA 416 | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 28 | 25 | 13 | 46.43 | 52 | 89.29 | 5 | Yes
TA 416 | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 74 | 70 | 22 | 29.73 | 31.43 | 94.59 | 5 | Yes
TA 416 | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 74 | 70 | 29 | 39.19 | 41.43 | 94.59 | 5 | Yes
TA 416 | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 123 | 111 | 13 | 10.57 | 11.71 | 90.24 | 5 | Yes
TA 416 | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 123 | 111 | 20 | 16.26 | 18.02 | 90.24 | 5 | Yes
TA 418 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 167 | 120 | 17 | 10.18 | 14.17 | 71.86 | 5 | Yes
TA 418 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 167 | 120 | 38 | 22.75 | 31.67 | 71.86 | 5 | Yes
TA 418 | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 22 | 15 | 2 | 9.09 | 13.33 | 68.18 | 5 | Yes
TA 418 | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 22 | 15 | 2 | 9.09 | 13.33 | 68.18 | 5 | Yes
TA 418 | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 79 | 59 | 12 | 15.19 | 20.34 | 74.68 | 5 | Yes
TA 418 | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 79 | 59 | 29 | 36.71 | 49.15 | 74.68 | 5 | Yes
TA 418 | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 48 | 34 | 3 | 6.25 | 8.82 | 70.83 | 5 | Yes
TA 418 | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 48 | 34 | 6 | 12.5 | 17.65 | 70.83 | 5 | Yes
TA 419 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 285 | 264 | 36 | 12.63 | 13.64 | 92.63 | 5 | Yes
TA 419 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 285 | 264 | 85 | 29.82 | 32.2 | 92.63 | 5 | Yes
TA 419 | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 51 | 48 | 9 | 17.65 | 18.75 | 94.12 | 5 | Yes
TA 419 | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 51 | 48 | 18 | 35.29 | 37.5 | 94.12 | 5 | Yes
TA 419 | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 101 | 87 | 14 | 13.86 | 16.09 | 86.14 | 5 | Yes
TA 419 | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 101 | 87 | 29 | 28.71 | 33.33 | 86.14 | 5 | Yes
TA 419 | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 77 | 75 | 7 | 9.09 | 9.33 | 97.4 | 5 | Yes
TA 419 | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 77 | 75 | 20 | 25.97 | 26.67 | 97.4 | 5 | Yes
TA 421 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 319 | 300 | 70 | 21.94 | 23.33 | 94.04 | 5 | Yes
TA 421 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 319 | 300 | 106 | 33.23 | 35.33 | 94.04 | 5 | Yes
TA 421 | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 46 | 44 | 11 | 23.91 | 25 | 95.65 | 5 | Yes
TA 421 | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 46 | 44 | 14 | 30.43 | 31.82 | 95.65 | 5 | Yes
TA 421 | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 104 | 101 | 44 | 42.31 | 43.56 | 97.12 | 5 | Yes
TA 421 | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 104 | 101 | 64 | 61.54 | 63.37 | 97.12 | 5 | Yes
TA 421 | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 131 | 119 | 12 | 9.16 | 10.08 | 90.84 | 5 | Yes
TA 421 | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 131 | 119 | 17 | 12.98 | 14.29 | 90.84 | 5 | Yes
TA 505 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 378 | 364 | 61 | 16.14 | 16.76 | 96.3 | 5 | Yes
TA 505 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 378 | 364 | 107 | 28.31 | 29.4 | 96.3 | 5 | Yes
TA 505 | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 109 | 104 | 27 | 24.77 | 25.96 | 95.41 | 5 | Yes
TA 505 | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 109 | 104 | 37 | 33.94 | 35.58 | 95.41 | 5 | Yes
TA 505 | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 32 | 31 | 8 | 25 | 25.81 | 96.88 | 5 | Yes
TA 505 | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 32 | 31 | 15 | 46.88 | 48.39 | 96.88 | 5 | Yes
TA 505 | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 173 | 166 | 19 | 10.98 | 11.45 | 95.95 | 5 | Yes
TA 505 | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 173 | 166 | 37 | 21.39 | 22.29 | 95.95 | 5 | Yes
TA 510 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 95 | 49 | 0 | 0 | 0 | 51.58 | 5 | Yes
TA 510 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 95 | 49 | 0 | 0 | 0 | 51.58 | 5 | Yes
TA 510 | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 34 | 12 | 0 | 0 | 0 | 35.29 | 5 | Yes
TA 510 | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 34 | 12 | 0 | 0 | 0 | 35.29 | 5 | Yes
TA 510 | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 15 | 5 | 0 | 0 | 0 | 33.33 | 5 | Yes
TA 510 | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 15 | 5 | 0 | 0 | 0 | 33.33 | 5 | Yes
TA 510 | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 36 | 23 | 0 | 0 | 0 | 63.89 | 5 | Yes
TA 510 | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 36 | 23 | 0 | 0 | 0 | 63.89 | 5 | Yes
TA 512 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 312 | 283 | 31 | 9.94 | 10.95 | 90.71 | 5 | Yes
TA 512 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 312 | 283 | 65 | 20.83 | 22.97 | 90.71 | 5 | Yes
TA 512 | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 59 | 54 | 7 | 11.86 | 12.96 | 91.53 | 5 | Yes
TA 512 | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 59 | 54 | 18 | 30.51 | 33.33 | 91.53 | 5 | Yes
TA 512 | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 118 | 106 | 16 | 13.56 | 15.09 | 89.83 | 5 | Yes
TA 512 | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 118 | 106 | 33 | 27.97 | 31.13 | 89.83 | 5 | Yes
TA 512 | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 83 | 74 | 8 | 9.64 | 10.81 | 89.16 | 5 | Yes
TA 512 | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 83 | 74 | 9 | 10.84 | 12.16 | 89.16 | 5 | Yes
TA 513 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 109 | 33 | 12 | 11.01 | 36.36 | 30.28 | 5 | Yes
TA 513 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 109 | 33 | 14 | 12.84 | 42.42 | 30.28 | 5 | Yes
TA 513 | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 46 | 12 | 8 | 17.39 | 66.67 | 26.09 | 5 | Yes
TA 513 | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 46 | 12 | 9 | 19.57 | 75 | 26.09 | 5 | Yes
TA 513 | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 49 | 11 | 4 | 8.16 | 36.36 | 22.45 | 5 | Yes
TA 513 | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 49 | 11 | 5 | 10.2 | 45.45 | 22.45 | 5 | Yes
TA 513 | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 9 | 8 | 0 | 0 | 0 | 88.89 | 5 | Yes
TA 513 | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 9 | 8 | 0 | 0 | 0 | 88.89 | 5 | Yes
TA 601 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 189 | 122 | 0 | 0 | 0 | 64.55 | 5 | Yes
TA 601 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 189 | 122 | 5 | 2.65 | 4.1 | 64.55 | 5 | Yes
TA 601 | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 23 | 15 | 0 | 0 | 0 | 65.22 | 5 | Yes
TA 601 | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 23 | 15 | 0 | 0 | 0 | 65.22 | 5 | Yes
TA 601 | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 69 | 29 | 0 | 0 | 0 | 42.03 | 5 | Yes
TA 601 | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 69 | 29 | 0 | 0 | 0 | 42.03 | 5 | Yes
TA 601 | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 79 | 64 | 0 | 0 | 0 | 81.01 | 5 | Yes
TA 601 | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 79 | 64 | 2 | 2.53 | 3.12 | 81.01 | 5 | Yes
TB 408 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 6 | 0 | 0 | 0 |  | 0 | 5 | Yes
TB 408 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 6 | 0 | 0 | 0 |  | 0 | 5 | Yes
TB 501 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 235 | 229 | 22 | 9.36 | 9.61 | 97.45 | 5 | Yes
TB 501 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 235 | 229 | 35 | 14.89 | 15.28 | 97.45 | 5 | Yes
TB 501 | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 34 | 34 | 1 | 2.94 | 2.94 | 100 | 5 | Yes
TB 501 | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 34 | 34 | 1 | 2.94 | 2.94 | 100 | 5 | Yes
TB 501 | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 32 | 28 | 9 | 28.12 | 32.14 | 87.5 | 5 | Yes
TB 501 | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 32 | 28 | 13 | 40.62 | 46.43 | 87.5 | 5 | Yes
TB 501 | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 105 | 103 | 1 | 0.95 | 0.97 | 98.1 | 5 | Yes
TB 501 | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 105 | 103 | 7 | 6.67 | 6.8 | 98.1 | 5 | Yes
TB 507 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 377 | 279 | 74 | 19.63 | 26.52 | 74.01 | 5 | Yes
TB 507 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 377 | 279 | 98 | 25.99 | 35.13 | 74.01 | 5 | Yes
TB 507 | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 68 | 43 | 1 | 1.47 | 2.33 | 63.24 | 5 | Yes
TB 507 | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 68 | 43 | 4 | 5.88 | 9.3 | 63.24 | 5 | Yes
TB 507 | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 188 | 142 | 65 | 34.57 | 45.77 | 75.53 | 5 | Yes
TB 507 | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 188 | 142 | 76 | 40.43 | 53.52 | 75.53 | 5 | Yes
TB 507 | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 94 | 69 | 1 | 1.06 | 1.45 | 73.4 | 5 | Yes
TB 507 | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 94 | 69 | 1 | 1.06 | 1.45 | 73.4 | 5 | Yes
TB 605 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 361 | 259 | 1 | 0.28 | 0.39 | 71.75 | 5 | Yes
TB 605 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 361 | 259 | 6 | 1.66 | 2.32 | 71.75 | 5 | Yes
TB 605 | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 81 | 36 | 0 | 0 | 0 | 44.44 | 5 | Yes
TB 605 | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 81 | 36 | 0 | 0 | 0 | 44.44 | 5 | Yes
TB 605 | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 54 | 27 | 1 | 1.85 | 3.7 | 50 | 5 | Yes
TB 605 | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 54 | 27 | 3 | 5.56 | 11.11 | 50 | 5 | Yes
TB 605 | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 169 | 146 | 0 | 0 | 0 | 86.39 | 5 | Yes
TB 605 | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 169 | 146 | 0 | 0 | 0 | 86.39 | 5 | Yes
TB 608 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 159 | 63 | 0 | 0 | 0 | 39.62 | 5 | Yes
TB 608 | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 159 | 63 | 2 | 1.26 | 3.17 | 39.62 | 5 | Yes
TB 608 | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 15 | 4 | 0 | 0 | 0 | 26.67 | 5 | Yes
TB 608 | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 15 | 4 | 0 | 0 | 0 | 26.67 | 5 | Yes
TB 608 | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 12 | 1 | 0 | 0 | 0 | 8.33 | 5 | Yes
TB 608 | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 12 | 1 | 0 | 0 | 0 | 8.33 | 5 | Yes
TB 608 | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 110 | 43 | 0 | 0 | 0 | 39.09 | 5 | Yes
TB 608 | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 110 | 43 | 0 | 0 | 0 | 39.09 | 5 | Yes

## Mechanism Summary - Series
Mechanism Summary - Series
Series | Cohort Window | Cohort Months | Start Window | Start Months | Foundations Total | Matched Non-Negative | Starts In Window | % of All Foundations | % Within Matched | Match Coverage % | Min Foundations Threshold | Threshold Applied
4xx | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 1757 | 1570 | 233 | 13.26 | 14.84 | 89.36 | 5 | Yes
4xx | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 1757 | 1570 | 426 | 24.25 | 27.13 | 89.36 | 5 | Yes
4xx | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 234 | 203 | 43 | 18.38 | 21.18 | 86.75 | 5 | Yes
4xx | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 234 | 203 | 64 | 27.35 | 31.53 | 86.75 | 5 | Yes
4xx | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 484 | 427 | 114 | 23.55 | 26.7 | 88.22 | 5 | Yes
4xx | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 484 | 427 | 186 | 38.43 | 43.56 | 88.22 | 5 | Yes
4xx | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 721 | 654 | 60 | 8.32 | 9.17 | 90.71 | 5 | Yes
4xx | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 721 | 654 | 114 | 15.81 | 17.43 | 90.71 | 5 | Yes
5xx | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 1506 | 1237 | 200 | 13.28 | 16.17 | 82.14 | 5 | Yes
5xx | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 1506 | 1237 | 319 | 21.18 | 25.79 | 82.14 | 5 | Yes
5xx | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 350 | 259 | 44 | 12.57 | 16.99 | 74 | 5 | Yes
5xx | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 350 | 259 | 69 | 19.71 | 26.64 | 74 | 5 | Yes
5xx | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 434 | 323 | 102 | 23.5 | 31.58 | 74.42 | 5 | Yes
5xx | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 434 | 323 | 142 | 32.72 | 43.96 | 74.42 | 5 | Yes
5xx | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 500 | 443 | 29 | 5.8 | 6.55 | 88.6 | 5 | Yes
5xx | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 500 | 443 | 54 | 10.8 | 12.19 | 88.6 | 5 | Yes
6xx | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 709 | 444 | 1 | 0.14 | 0.23 | 62.62 | 5 | Yes
6xx | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 709 | 444 | 13 | 1.83 | 2.93 | 62.62 | 5 | Yes
6xx | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 119 | 55 | 0 | 0 | 0 | 46.22 | 5 | Yes
6xx | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 119 | 55 | 0 | 0 | 0 | 46.22 | 5 | Yes
6xx | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 135 | 57 | 1 | 0.74 | 1.75 | 42.22 | 5 | Yes
6xx | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 135 | 57 | 3 | 2.22 | 5.26 | 42.22 | 5 | Yes
6xx | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 358 | 253 | 0 | 0 | 0 | 70.67 | 5 | Yes
6xx | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 358 | 253 | 2 | 0.56 | 0.79 | 70.67 | 5 | Yes

## Mechanism Summary - Ownership
Mechanism Summary - Ownership
Ownership | Cohort Window | Cohort Months | Start Window | Start Months | Foundations Total | Matched Non-Negative | Starts In Window | % of All Foundations | % Within Matched | Match Coverage % | Min Foundations Threshold | Threshold Applied
Government | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 2834 | 2421 | 337 | 11.89 | 13.92 | 85.43 | 5 | Yes
Government | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 2834 | 2421 | 617 | 21.77 | 25.49 | 85.43 | 5 | Yes
Government | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 505 | 400 | 85 | 16.83 | 21.25 | 79.21 | 5 | Yes
Government | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 505 | 400 | 128 | 25.35 | 32 | 79.21 | 5 | Yes
Government | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 766 | 609 | 142 | 18.54 | 23.32 | 79.5 | 5 | Yes
Government | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 766 | 609 | 239 | 31.2 | 39.24 | 79.5 | 5 | Yes
Government | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 1100 | 989 | 87 | 7.91 | 8.8 | 89.91 | 5 | Yes
Government | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 1100 | 989 | 162 | 14.73 | 16.38 | 89.91 | 5 | Yes
Private | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon | 10,11 | 1138 | 830 | 97 | 8.52 | 11.69 | 72.93 | 5 | Yes
Private | All Foundations | 1,2,3,4,5,6,7,8,9,10,11,12 | Post-Monsoon Wide | 10,11,12 | 1138 | 830 | 141 | 12.39 | 16.99 | 72.93 | 5 | Yes
Private | Pre-Monsoon | 4,5 | Post-Monsoon | 10,11 | 198 | 117 | 2 | 1.01 | 1.71 | 59.09 | 5 | Yes
Private | Pre-Monsoon | 4,5 | Post-Monsoon Wide | 10,11,12 | 198 | 117 | 5 | 2.53 | 4.27 | 59.09 | 5 | Yes
Private | Monsoon | 6,7,8,9 | Post-Monsoon | 10,11 | 287 | 198 | 75 | 26.13 | 37.88 | 68.99 | 5 | Yes
Private | Monsoon | 6,7,8,9 | Post-Monsoon Wide | 10,11,12 | 287 | 198 | 92 | 32.06 | 46.46 | 68.99 | 5 | Yes
Private | Dry Season | 12,1,2,3 | Post-Monsoon | 10,11 | 479 | 361 | 2 | 0.42 | 0.55 | 75.37 | 5 | Yes
Private | Dry Season | 12,1,2,3 | Post-Monsoon Wide | 10,11,12 | 479 | 361 | 8 | 1.67 | 2.22 | 75.37 | 5 | Yes

## Mechanism Matrix - Project
Mechanism Matrix - Project
Project | Foundation Month | Erection Start Month | Foundations In Pair | Foundations Total (Month) | Matched Non-Negative (Month) | % of All Foundations In Month | % of Matched Non-Negative In Month
TA 413 | 2024-06 | 2025-01 | 1 | 14 | 14 | 7.14 | 7.14
TA 413 | 2024-06 | 2025-03 | 8 | 14 | 14 | 57.14 | 57.14
TA 413 | 2024-06 | 2025-08 | 1 | 14 | 14 | 7.14 | 7.14
TA 413 | 2024-06 | 2025-10 | 3 | 14 | 14 | 21.43 | 21.43
TA 413 | 2024-06 | 2025-11 | 1 | 14 | 14 | 7.14 | 7.14
TA 413 | 2024-07 | 2024-09 | 1 | 20 | 20 | 5 | 5
TA 413 | 2024-07 | 2024-10 | 1 | 20 | 20 | 5 | 5
TA 413 | 2024-07 | 2024-12 | 1 | 20 | 20 | 5 | 5
TA 413 | 2024-07 | 2025-01 | 4 | 20 | 20 | 20 | 20
TA 413 | 2024-07 | 2025-02 | 2 | 20 | 20 | 10 | 10
TA 413 | 2024-07 | 2025-08 | 3 | 20 | 20 | 15 | 15
TA 413 | 2024-07 | 2025-09 | 4 | 20 | 20 | 20 | 20
TA 413 | 2024-07 | 2025-11 | 3 | 20 | 20 | 15 | 15
TA 413 | 2024-07 | 2025-12 | 1 | 20 | 20 | 5 | 5
TA 413 | 2024-08 | 2024-09 | 2 | 23 | 23 | 8.7 | 8.7
TA 413 | 2024-08 | 2024-10 | 3 | 23 | 23 | 13.04 | 13.04
TA 413 | 2024-08 | 2024-12 | 3 | 23 | 23 | 13.04 | 13.04
TA 413 | 2024-08 | 2025-01 | 2 | 23 | 23 | 8.7 | 8.7
TA 413 | 2024-08 | 2025-07 | 2 | 23 | 23 | 8.7 | 8.7
TA 413 | 2024-08 | 2025-08 | 4 | 23 | 23 | 17.39 | 17.39
TA 413 | 2024-08 | 2025-09 | 3 | 23 | 23 | 13.04 | 13.04
TA 413 | 2024-08 | 2025-10 | 3 | 23 | 23 | 13.04 | 13.04
TA 413 | 2024-08 | 2025-12 | 1 | 23 | 23 | 4.35 | 4.35
TA 413 | 2024-09 | 2024-11 | 3 | 40 | 39 | 7.5 | 7.69
TA 413 | 2024-09 | 2024-12 | 5 | 40 | 39 | 12.5 | 12.82
TA 413 | 2024-09 | 2025-01 | 6 | 40 | 39 | 15 | 15.38
TA 413 | 2024-09 | 2025-08 | 13 | 40 | 39 | 32.5 | 33.33
TA 413 | 2024-09 | 2025-09 | 7 | 40 | 39 | 17.5 | 17.95
TA 413 | 2024-09 | 2025-10 | 1 | 40 | 39 | 2.5 | 2.56
TA 413 | 2024-09 | 2025-11 | 1 | 40 | 39 | 2.5 | 2.56
TA 413 | 2024-09 | 2025-12 | 1 | 40 | 39 | 2.5 | 2.56
TA 413 | 2024-09 | 2026-01 | 2 | 40 | 39 | 5 | 5.13
TA 413 | 2024-10 | 2024-11 | 1 | 35 | 29 | 2.86 | 3.45
TA 413 | 2024-10 | 2024-12 | 5 | 35 | 29 | 14.29 | 17.24
TA 413 | 2024-10 | 2025-01 | 4 | 35 | 29 | 11.43 | 13.79
TA 413 | 2024-10 | 2025-02 | 5 | 35 | 29 | 14.29 | 17.24
TA 413 | 2024-10 | 2025-04 | 1 | 35 | 29 | 2.86 | 3.45
TA 413 | 2024-10 | 2025-07 | 3 | 35 | 29 | 8.57 | 10.34
TA 413 | 2024-10 | 2025-08 | 6 | 35 | 29 | 17.14 | 20.69
TA 413 | 2024-10 | 2025-09 | 1 | 35 | 29 | 2.86 | 3.45
TA 413 | 2024-10 | 2025-11 | 2 | 35 | 29 | 5.71 | 6.9
TA 413 | 2024-10 | 2025-12 | 1 | 35 | 29 | 2.86 | 3.45
TA 413 | 2024-11 | 2024-12 | 1 | 24 | 24 | 4.17 | 4.17
TA 413 | 2024-11 | 2025-01 | 7 | 24 | 24 | 29.17 | 29.17
TA 413 | 2024-11 | 2025-02 | 5 | 24 | 24 | 20.83 | 20.83
TA 413 | 2024-11 | 2025-03 | 2 | 24 | 24 | 8.33 | 8.33
TA 413 | 2024-11 | 2025-08 | 2 | 24 | 24 | 8.33 | 8.33
TA 413 | 2024-11 | 2025-09 | 4 | 24 | 24 | 16.67 | 16.67
TA 413 | 2024-11 | 2025-10 | 2 | 24 | 24 | 8.33 | 8.33
TA 413 | 2024-11 | 2026-01 | 1 | 24 | 24 | 4.17 | 4.17
TA 413 | 2024-12 | 2024-12 | 1 | 32 | 32 | 3.12 | 3.12
TA 413 | 2024-12 | 2025-01 | 2 | 32 | 32 | 6.25 | 6.25
TA 413 | 2024-12 | 2025-02 | 4 | 32 | 32 | 12.5 | 12.5
TA 413 | 2024-12 | 2025-03 | 10 | 32 | 32 | 31.25 | 31.25
TA 413 | 2024-12 | 2025-04 | 3 | 32 | 32 | 9.38 | 9.38
TA 413 | 2024-12 | 2025-08 | 1 | 32 | 32 | 3.12 | 3.12
TA 413 | 2024-12 | 2025-09 | 4 | 32 | 32 | 12.5 | 12.5
TA 413 | 2024-12 | 2025-10 | 4 | 32 | 32 | 12.5 | 12.5
TA 413 | 2024-12 | 2025-11 | 2 | 32 | 32 | 6.25 | 6.25
TA 413 | 2024-12 | 2026-06 | 1 | 32 | 32 | 3.12 | 3.12
TA 413 | 2025-01 | 2025-02 | 3 | 34 | 33 | 8.82 | 9.09
TA 413 | 2025-01 | 2025-03 | 3 | 34 | 33 | 8.82 | 9.09
TA 413 | 2025-01 | 2025-04 | 1 | 34 | 33 | 2.94 | 3.03
TA 413 | 2025-01 | 2025-07 | 3 | 34 | 33 | 8.82 | 9.09
TA 413 | 2025-01 | 2025-08 | 7 | 34 | 33 | 20.59 | 21.21
TA 413 | 2025-01 | 2025-09 | 8 | 34 | 33 | 23.53 | 24.24
TA 413 | 2025-01 | 2025-10 | 4 | 34 | 33 | 11.76 | 12.12
TA 413 | 2025-01 | 2025-11 | 2 | 34 | 33 | 5.88 | 6.06
TA 413 | 2025-01 | 2025-12 | 1 | 34 | 33 | 2.94 | 3.03
TA 413 | 2025-01 | 2026-02 | 1 | 34 | 33 | 2.94 | 3.03
TA 413 | 2025-02 | 2025-03 | 2 | 31 | 31 | 6.45 | 6.45
TA 413 | 2025-02 | 2025-07 | 3 | 31 | 31 | 9.68 | 9.68
TA 413 | 2025-02 | 2025-08 | 9 | 31 | 31 | 29.03 | 29.03
TA 413 | 2025-02 | 2025-09 | 5 | 31 | 31 | 16.13 | 16.13
TA 413 | 2025-02 | 2025-10 | 3 | 31 | 31 | 9.68 | 9.68
TA 413 | 2025-02 | 2025-11 | 6 | 31 | 31 | 19.35 | 19.35
TA 413 | 2025-02 | 2025-12 | 2 | 31 | 31 | 6.45 | 6.45
TA 413 | 2025-02 | 2026-01 | 1 | 31 | 31 | 3.23 | 3.23
TA 413 | 2025-03 | 2025-04 | 1 | 19 | 19 | 5.26 | 5.26
TA 413 | 2025-03 | 2025-07 | 1 | 19 | 19 | 5.26 | 5.26
TA 413 | 2025-03 | 2025-08 | 2 | 19 | 19 | 10.53 | 10.53
TA 413 | 2025-03 | 2025-09 | 10 | 19 | 19 | 52.63 | 52.63
TA 413 | 2025-03 | 2025-10 | 3 | 19 | 19 | 15.79 | 15.79
TA 413 | 2025-03 | 2025-11 | 1 | 19 | 19 | 5.26 | 5.26
TA 413 | 2025-03 | 2025-12 | 1 | 19 | 19 | 5.26 | 5.26
TA 413 | 2025-04 | 2025-07 | 2 | 23 | 23 | 8.7 | 8.7
TA 413 | 2025-04 | 2025-08 | 4 | 23 | 23 | 17.39 | 17.39
TA 413 | 2025-04 | 2025-09 | 9 | 23 | 23 | 39.13 | 39.13
TA 413 | 2025-04 | 2025-10 | 4 | 23 | 23 | 17.39 | 17.39
TA 413 | 2025-04 | 2025-11 | 3 | 23 | 23 | 13.04 | 13.04
TA 413 | 2025-04 | 2026-01 | 1 | 23 | 23 | 4.35 | 4.35
TA 413 | 2025-05 | 2025-08 | 1 | 10 | 10 | 10 | 10
TA 413 | 2025-05 | 2025-09 | 2 | 10 | 10 | 20 | 20
TA 413 | 2025-05 | 2025-10 | 5 | 10 | 10 | 50 | 50
TA 413 | 2025-05 | 2025-11 | 1 | 10 | 10 | 10 | 10
TA 413 | 2025-05 | 2026-02 | 1 | 10 | 10 | 10 | 10
TA 413 | 2025-06 | 2025-08 | 1 | 4 | 4 | 25 | 25
TA 413 | 2025-06 | 2025-09 | 1 | 4 | 4 | 25 | 25
TA 413 | 2025-06 | 2025-10 | 1 | 4 | 4 | 25 | 25
TA 413 | 2025-06 | 2025-11 | 1 | 4 | 4 | 25 | 25
TA 413 | 2025-07 | 2025-08 | 1 | 2 | 2 | 50 | 50
TA 413 | 2025-07 | 2026-01 | 1 | 2 | 2 | 50 | 50
TA 413 | 2026-01 | 2026-08 | 1 | 1 | 1 | 100 | 100
TA 413 | 2026-03 | 2026-07 | 1 | 1 | 1 | 100 | 100
TA 414 | 2024-05 | 2025-09 | 1 | 2 | 2 | 50 | 50
TA 414 | 2024-05 | 2026-01 | 1 | 2 | 2 | 50 | 50
TA 414 | 2024-10 | 2025-05 | 1 | 1 | 1 | 100 | 100
TA 414 | 2024-11 | 2025-06 | 2 | 4 | 3 | 50 | 66.67
TA 414 | 2024-11 | 2026-01 | 1 | 4 | 3 | 25 | 33.33
TA 414 | 2024-12 | 2025-07 | 1 | 12 | 12 | 8.33 | 8.33
TA 414 | 2024-12 | 2025-08 | 2 | 12 | 12 | 16.67 | 16.67
TA 414 | 2024-12 | 2025-12 | 2 | 12 | 12 | 16.67 | 16.67
TA 414 | 2024-12 | 2026-01 | 3 | 12 | 12 | 25 | 25
TA 414 | 2024-12 | 2026-02 | 3 | 12 | 12 | 25 | 25
TA 414 | 2024-12 | 2026-06 | 1 | 12 | 12 | 8.33 | 8.33
TA 414 | 2025-01 | 2025-06 | 1 | 17 | 16 | 5.88 | 6.25
TA 414 | 2025-01 | 2025-09 | 1 | 17 | 16 | 5.88 | 6.25
TA 414 | 2025-01 | 2025-12 | 4 | 17 | 16 | 23.53 | 25
TA 414 | 2025-01 | 2026-01 | 2 | 17 | 16 | 11.76 | 12.5
TA 414 | 2025-01 | 2026-02 | 1 | 17 | 16 | 5.88 | 6.25
TA 414 | 2025-01 | 2026-03 | 2 | 17 | 16 | 11.76 | 12.5
TA 414 | 2025-01 | 2026-04 | 2 | 17 | 16 | 11.76 | 12.5
TA 414 | 2025-01 | 2026-05 | 1 | 17 | 16 | 5.88 | 6.25
TA 414 | 2025-01 | 2026-06 | 2 | 17 | 16 | 11.76 | 12.5
TA 414 | 2025-02 | 2025-09 | 2 | 20 | 20 | 10 | 10
TA 414 | 2025-02 | 2025-12 | 5 | 20 | 20 | 25 | 25
TA 414 | 2025-02 | 2026-01 | 8 | 20 | 20 | 40 | 40
TA 414 | 2025-02 | 2026-03 | 1 | 20 | 20 | 5 | 5
TA 414 | 2025-02 | 2026-04 | 2 | 20 | 20 | 10 | 10
TA 414 | 2025-02 | 2026-05 | 2 | 20 | 20 | 10 | 10
TA 414 | 2025-03 | 2025-08 | 1 | 10 | 9 | 10 | 11.11
TA 414 | 2025-03 | 2025-12 | 4 | 10 | 9 | 40 | 44.44
TA 414 | 2025-03 | 2026-01 | 1 | 10 | 9 | 10 | 11.11
TA 414 | 2025-03 | 2026-02 | 2 | 10 | 9 | 20 | 22.22
TA 414 | 2025-03 | 2026-04 | 1 | 10 | 9 | 10 | 11.11
TA 414 | 2025-04 | 2025-12 | 3 | 18 | 18 | 16.67 | 16.67
TA 414 | 2025-04 | 2026-01 | 5 | 18 | 18 | 27.78 | 27.78
TA 414 | 2025-04 | 2026-02 | 5 | 18 | 18 | 27.78 | 27.78
TA 414 | 2025-04 | 2026-03 | 3 | 18 | 18 | 16.67 | 16.67
TA 414 | 2025-04 | 2026-05 | 2 | 18 | 18 | 11.11 | 11.11
TA 414 | 2025-05 | 2025-12 | 1 | 5 | 4 | 20 | 25
TA 414 | 2025-05 | 2026-01 | 1 | 5 | 4 | 20 | 25
TA 414 | 2025-05 | 2026-02 | 1 | 5 | 4 | 20 | 25
TA 414 | 2025-05 | 2026-03 | 1 | 5 | 4 | 20 | 25
TA 414 | 2025-06 | 2025-11 | 1 | 2 | 2 | 50 | 50
TA 414 | 2025-06 | 2026-02 | 1 | 2 | 2 | 50 | 50
TA 414 | 2025-08 | 2026-01 | 1 | 1 | 1 | 100 | 100
TA 414 | 2025-09 | 2025-12 | 1 | 3 | 3 | 33.33 | 33.33
TA 414 | 2025-09 | 2026-01 | 2 | 3 | 3 | 66.67 | 66.67
TA 414 | 2025-10 | 2025-12 | 1 | 8 | 8 | 12.5 | 12.5
TA 414 | 2025-10 | 2026-01 | 1 | 8 | 8 | 12.5 | 12.5
TA 414 | 2025-10 | 2026-03 | 2 | 8 | 8 | 25 | 25
TA 414 | 2025-10 | 2026-04 | 4 | 8 | 8 | 50 | 50
TA 414 | 2025-11 | 2025-12 | 3 | 24 | 23 | 12.5 | 13.04
TA 414 | 2025-11 | 2026-01 | 2 | 24 | 23 | 8.33 | 8.7
TA 414 | 2025-11 | 2026-02 | 7 | 24 | 23 | 29.17 | 30.43
TA 414 | 2025-11 | 2026-03 | 4 | 24 | 23 | 16.67 | 17.39
TA 414 | 2025-11 | 2026-04 | 2 | 24 | 23 | 8.33 | 8.7
TA 414 | 2025-11 | 2026-05 | 3 | 24 | 23 | 12.5 | 13.04
TA 414 | 2025-11 | 2026-06 | 2 | 24 | 23 | 8.33 | 8.7
TA 414 | 2025-12 | 2025-12 | 6 | 55 | 51 | 10.91 | 11.76
TA 414 | 2025-12 | 2026-01 | 15 | 55 | 51 | 27.27 | 29.41
TA 414 | 2025-12 | 2026-02 | 16 | 55 | 51 | 29.09 | 31.37
TA 414 | 2025-12 | 2026-03 | 7 | 55 | 51 | 12.73 | 13.73
TA 414 | 2025-12 | 2026-04 | 2 | 55 | 51 | 3.64 | 3.92
TA 414 | 2025-12 | 2026-05 | 1 | 55 | 51 | 1.82 | 1.96
TA 414 | 2025-12 | 2026-06 | 3 | 55 | 51 | 5.45 | 5.88
TA 414 | 2025-12 | 2026-07 | 1 | 55 | 51 | 1.82 | 1.96
TA 414 | 2026-01 | 2026-01 | 6 | 54 | 44 | 11.11 | 13.64
TA 414 | 2026-01 | 2026-02 | 14 | 54 | 44 | 25.93 | 31.82
TA 414 | 2026-01 | 2026-03 | 13 | 54 | 44 | 24.07 | 29.55
TA 414 | 2026-01 | 2026-04 | 4 | 54 | 44 | 7.41 | 9.09
TA 414 | 2026-01 | 2026-05 | 5 | 54 | 44 | 9.26 | 11.36
TA 414 | 2026-01 | 2026-06 | 2 | 54 | 44 | 3.7 | 4.55
TA 414 | 2026-02 | 2026-02 | 1 | 30 | 25 | 3.33 | 4
TA 414 | 2026-02 | 2026-03 | 6 | 30 | 25 | 20 | 24
TA 414 | 2026-02 | 2026-04 | 6 | 30 | 25 | 20 | 24
TA 414 | 2026-02 | 2026-05 | 5 | 30 | 25 | 16.67 | 20
TA 414 | 2026-02 | 2026-06 | 7 | 30 | 25 | 23.33 | 28
TA 414 | 2026-03 | 2026-03 | 7 | 24 | 21 | 29.17 | 33.33
TA 414 | 2026-03 | 2026-04 | 6 | 24 | 21 | 25 | 28.57
TA 414 | 2026-03 | 2026-05 | 6 | 24 | 21 | 25 | 28.57
TA 414 | 2026-03 | 2026-06 | 2 | 24 | 21 | 8.33 | 9.52
TA 414 | 2026-04 | 2026-05 | 3 | 14 | 6 | 21.43 | 50
TA 414 | 2026-04 | 2026-06 | 3 | 14 | 6 | 21.43 | 50
TA 414 | 2026-05 | 2026-06 | 8 | 15 | 8 | 53.33 | 100
TA 414 | 2026-06 | 2026-06 | 2 | 16 | 2 | 12.5 | 100
TA 416 | 2024-05 | 2024-09 | 2 | 6 | 6 | 33.33 | 33.33
TA 416 | 2024-05 | 2024-11 | 2 | 6 | 6 | 33.33 | 33.33
TA 416 | 2024-05 | 2024-12 | 2 | 6 | 6 | 33.33 | 33.33
TA 416 | 2024-06 | 2024-09 | 1 | 17 | 17 | 5.88 | 5.88
TA 416 | 2024-06 | 2024-10 | 5 | 17 | 17 | 29.41 | 29.41
TA 416 | 2024-06 | 2024-11 | 2 | 17 | 17 | 11.76 | 11.76
TA 416 | 2024-06 | 2024-12 | 1 | 17 | 17 | 5.88 | 5.88
TA 416 | 2024-06 | 2025-01 | 4 | 17 | 17 | 23.53 | 23.53
TA 416 | 2024-06 | 2025-04 | 1 | 17 | 17 | 5.88 | 5.88
TA 416 | 2024-06 | 2025-05 | 2 | 17 | 17 | 11.76 | 11.76
TA 416 | 2024-06 | 2025-09 | 1 | 17 | 17 | 5.88 | 5.88
TA 416 | 2024-07 | 2024-10 | 1 | 10 | 10 | 10 | 10
TA 416 | 2024-07 | 2024-11 | 4 | 10 | 10 | 40 | 40
TA 416 | 2024-07 | 2024-12 | 2 | 10 | 10 | 20 | 20
TA 416 | 2024-07 | 2025-01 | 1 | 10 | 10 | 10 | 10
TA 416 | 2024-07 | 2025-04 | 1 | 10 | 10 | 10 | 10
TA 416 | 2024-07 | 2025-05 | 1 | 10 | 10 | 10 | 10
TA 416 | 2024-08 | 2024-10 | 2 | 13 | 13 | 15.38 | 15.38
TA 416 | 2024-08 | 2024-11 | 3 | 13 | 13 | 23.08 | 23.08
TA 416 | 2024-08 | 2024-12 | 1 | 13 | 13 | 7.69 | 7.69
TA 416 | 2024-08 | 2025-01 | 2 | 13 | 13 | 15.38 | 15.38
TA 416 | 2024-08 | 2025-02 | 1 | 13 | 13 | 7.69 | 7.69
TA 416 | 2024-08 | 2025-04 | 1 | 13 | 13 | 7.69 | 7.69
TA 416 | 2024-08 | 2025-05 | 3 | 13 | 13 | 23.08 | 23.08
TA 416 | 2024-09 | 2024-11 | 4 | 29 | 29 | 13.79 | 13.79
TA 416 | 2024-09 | 2024-12 | 3 | 29 | 29 | 10.34 | 10.34
TA 416 | 2024-09 | 2025-01 | 3 | 29 | 29 | 10.34 | 10.34
TA 416 | 2024-09 | 2025-03 | 3 | 29 | 29 | 10.34 | 10.34
TA 416 | 2024-09 | 2025-04 | 6 | 29 | 29 | 20.69 | 20.69
TA 416 | 2024-09 | 2025-05 | 7 | 29 | 29 | 24.14 | 24.14
TA 416 | 2024-09 | 2025-06 | 2 | 29 | 29 | 6.9 | 6.9
TA 416 | 2024-09 | 2025-07 | 1 | 29 | 29 | 3.45 | 3.45
TA 416 | 2024-10 | 2024-11 | 1 | 50 | 50 | 2 | 2
TA 416 | 2024-10 | 2024-12 | 7 | 50 | 50 | 14 | 14
TA 416 | 2024-10 | 2025-01 | 7 | 50 | 50 | 14 | 14
TA 416 | 2024-10 | 2025-02 | 11 | 50 | 50 | 22 | 22
TA 416 | 2024-10 | 2025-03 | 9 | 50 | 50 | 18 | 18
TA 416 | 2024-10 | 2025-04 | 7 | 50 | 50 | 14 | 14
TA 416 | 2024-10 | 2025-05 | 4 | 50 | 50 | 8 | 8
TA 416 | 2024-10 | 2025-06 | 3 | 50 | 50 | 6 | 6
TA 416 | 2024-10 | 2025-08 | 1 | 50 | 50 | 2 | 2
TA 416 | 2024-11 | 2024-11 | 1 | 46 | 46 | 2.17 | 2.17
TA 416 | 2024-11 | 2024-12 | 7 | 46 | 46 | 15.22 | 15.22
TA 416 | 2024-11 | 2025-01 | 7 | 46 | 46 | 15.22 | 15.22
TA 416 | 2024-11 | 2025-02 | 9 | 46 | 46 | 19.57 | 19.57
TA 416 | 2024-11 | 2025-03 | 10 | 46 | 46 | 21.74 | 21.74
TA 416 | 2024-11 | 2025-04 | 9 | 46 | 46 | 19.57 | 19.57
TA 416 | 2024-11 | 2025-05 | 2 | 46 | 46 | 4.35 | 4.35
TA 416 | 2024-11 | 2025-08 | 1 | 46 | 46 | 2.17 | 2.17
TA 416 | 2024-12 | 2024-12 | 1 | 37 | 37 | 2.7 | 2.7
TA 416 | 2024-12 | 2025-01 | 3 | 37 | 37 | 8.11 | 8.11
TA 416 | 2024-12 | 2025-02 | 6 | 37 | 37 | 16.22 | 16.22
TA 416 | 2024-12 | 2025-03 | 5 | 37 | 37 | 13.51 | 13.51
TA 416 | 2024-12 | 2025-04 | 4 | 37 | 37 | 10.81 | 10.81
TA 416 | 2024-12 | 2025-05 | 5 | 37 | 37 | 13.51 | 13.51
TA 416 | 2024-12 | 2025-06 | 1 | 37 | 37 | 2.7 | 2.7
TA 416 | 2024-12 | 2025-08 | 1 | 37 | 37 | 2.7 | 2.7
TA 416 | 2024-12 | 2025-09 | 6 | 37 | 37 | 16.22 | 16.22
TA 416 | 2024-12 | 2025-10 | 1 | 37 | 37 | 2.7 | 2.7
TA 416 | 2024-12 | 2025-11 | 2 | 37 | 37 | 5.41 | 5.41
TA 416 | 2024-12 | 2025-12 | 1 | 37 | 37 | 2.7 | 2.7
TA 416 | 2024-12 | 2026-02 | 1 | 37 | 37 | 2.7 | 2.7
TA 416 | 2025-01 | 2025-03 | 1 | 34 | 34 | 2.94 | 2.94
TA 416 | 2025-01 | 2025-04 | 7 | 34 | 34 | 20.59 | 20.59
TA 416 | 2025-01 | 2025-05 | 5 | 34 | 34 | 14.71 | 14.71
TA 416 | 2025-01 | 2025-06 | 6 | 34 | 34 | 17.65 | 17.65
TA 416 | 2025-01 | 2025-07 | 3 | 34 | 34 | 8.82 | 8.82
TA 416 | 2025-01 | 2025-09 | 3 | 34 | 34 | 8.82 | 8.82
TA 416 | 2025-01 | 2025-10 | 1 | 34 | 34 | 2.94 | 2.94
TA 416 | 2025-01 | 2025-11 | 2 | 34 | 34 | 5.88 | 5.88
TA 416 | 2025-01 | 2025-12 | 5 | 34 | 34 | 14.71 | 14.71
TA 416 | 2025-01 | 2026-01 | 1 | 34 | 34 | 2.94 | 2.94
TA 416 | 2025-02 | 2025-03 | 2 | 24 | 24 | 8.33 | 8.33
TA 416 | 2025-02 | 2025-04 | 3 | 24 | 24 | 12.5 | 12.5
TA 416 | 2025-02 | 2025-05 | 5 | 24 | 24 | 20.83 | 20.83
TA 416 | 2025-02 | 2025-06 | 4 | 24 | 24 | 16.67 | 16.67
TA 416 | 2025-02 | 2025-07 | 1 | 24 | 24 | 4.17 | 4.17
TA 416 | 2025-02 | 2025-08 | 5 | 24 | 24 | 20.83 | 20.83
TA 416 | 2025-02 | 2025-09 | 2 | 24 | 24 | 8.33 | 8.33
TA 416 | 2025-02 | 2025-10 | 1 | 24 | 24 | 4.17 | 4.17
TA 416 | 2025-02 | 2025-11 | 1 | 24 | 24 | 4.17 | 4.17
TA 416 | 2025-03 | 2025-05 | 1 | 16 | 16 | 6.25 | 6.25
TA 416 | 2025-03 | 2025-06 | 2 | 16 | 16 | 12.5 | 12.5
TA 416 | 2025-03 | 2025-07 | 1 | 16 | 16 | 6.25 | 6.25
TA 416 | 2025-03 | 2025-08 | 3 | 16 | 16 | 18.75 | 18.75
TA 416 | 2025-03 | 2025-09 | 3 | 16 | 16 | 18.75 | 18.75
TA 416 | 2025-03 | 2025-10 | 1 | 16 | 16 | 6.25 | 6.25
TA 416 | 2025-03 | 2025-11 | 4 | 16 | 16 | 25 | 25
TA 416 | 2025-03 | 2026-02 | 1 | 16 | 16 | 6.25 | 6.25
TA 416 | 2025-04 | 2025-05 | 1 | 13 | 13 | 7.69 | 7.69
TA 416 | 2025-04 | 2025-06 | 1 | 13 | 13 | 7.69 | 7.69
TA 416 | 2025-04 | 2025-07 | 1 | 13 | 13 | 7.69 | 7.69
TA 416 | 2025-04 | 2025-08 | 3 | 13 | 13 | 23.08 | 23.08
TA 416 | 2025-04 | 2025-09 | 1 | 13 | 13 | 7.69 | 7.69
TA 416 | 2025-04 | 2025-11 | 3 | 13 | 13 | 23.08 | 23.08
TA 416 | 2025-04 | 2025-12 | 3 | 13 | 13 | 23.08 | 23.08
TA 416 | 2025-05 | 2025-05 | 1 | 6 | 6 | 16.67 | 16.67
TA 416 | 2025-05 | 2025-09 | 1 | 6 | 6 | 16.67 | 16.67
TA 416 | 2025-05 | 2025-10 | 2 | 6 | 6 | 33.33 | 33.33
TA 416 | 2025-05 | 2025-11 | 1 | 6 | 6 | 16.67 | 16.67
TA 416 | 2025-05 | 2026-01 | 1 | 6 | 6 | 16.67 | 16.67
TA 416 | 2025-06 | 2025-10 | 1 | 1 | 1 | 100 | 100
TA 418 | 2024-01 | 2024-12 | 2 | 2 | 2 | 100 | 100
TA 418 | 2024-06 | 2024-12 | 2 | 2 | 2 | 100 | 100
TA 418 | 2024-07 | 2024-11 | 1 | 8 | 7 | 12.5 | 14.29
TA 418 | 2024-07 | 2024-12 | 2 | 8 | 7 | 25 | 28.57
TA 418 | 2024-07 | 2025-01 | 2 | 8 | 7 | 25 | 28.57
TA 418 | 2024-07 | 2025-02 | 1 | 8 | 7 | 12.5 | 14.29
TA 418 | 2024-07 | 2025-05 | 1 | 8 | 7 | 12.5 | 14.29
TA 418 | 2024-08 | 2024-11 | 1 | 9 | 8 | 11.11 | 12.5
TA 418 | 2024-08 | 2024-12 | 2 | 9 | 8 | 22.22 | 25
TA 418 | 2024-08 | 2025-01 | 1 | 9 | 8 | 11.11 | 12.5
TA 418 | 2024-08 | 2025-02 | 2 | 9 | 8 | 22.22 | 25
TA 418 | 2024-08 | 2025-04 | 1 | 9 | 8 | 11.11 | 12.5
TA 418 | 2024-08 | 2025-05 | 1 | 9 | 8 | 11.11 | 12.5
TA 418 | 2024-09 | 2024-10 | 2 | 7 | 7 | 28.57 | 28.57
TA 418 | 2024-09 | 2024-11 | 1 | 7 | 7 | 14.29 | 14.29
TA 418 | 2024-09 | 2024-12 | 1 | 7 | 7 | 14.29 | 14.29
TA 418 | 2024-09 | 2025-01 | 1 | 7 | 7 | 14.29 | 14.29
TA 418 | 2024-09 | 2025-05 | 1 | 7 | 7 | 14.29 | 14.29
TA 418 | 2024-09 | 2025-12 | 1 | 7 | 7 | 14.29 | 14.29
TA 418 | 2024-10 | 2025-01 | 1 | 4 | 3 | 25 | 33.33
TA 418 | 2024-10 | 2025-04 | 1 | 4 | 3 | 25 | 33.33
TA 418 | 2024-10 | 2025-05 | 1 | 4 | 3 | 25 | 33.33
TA 418 | 2024-11 | 2025-03 | 1 | 5 | 4 | 20 | 25
TA 418 | 2024-11 | 2025-06 | 3 | 5 | 4 | 60 | 75
TA 418 | 2024-12 | 2025-01 | 2 | 6 | 5 | 33.33 | 40
TA 418 | 2024-12 | 2025-02 | 2 | 6 | 5 | 33.33 | 40
TA 418 | 2024-12 | 2025-03 | 1 | 6 | 5 | 16.67 | 20
TA 418 | 2025-01 | 2025-03 | 3 | 6 | 6 | 50 | 50
TA 418 | 2025-01 | 2025-04 | 2 | 6 | 6 | 33.33 | 33.33
TA 418 | 2025-01 | 2025-05 | 1 | 6 | 6 | 16.67 | 16.67
TA 418 | 2025-02 | 2025-04 | 3 | 7 | 7 | 42.86 | 42.86
TA 418 | 2025-02 | 2025-05 | 1 | 7 | 7 | 14.29 | 14.29
TA 418 | 2025-02 | 2025-07 | 1 | 7 | 7 | 14.29 | 14.29
TA 418 | 2025-02 | 2025-09 | 1 | 7 | 7 | 14.29 | 14.29
TA 418 | 2025-02 | 2025-10 | 1 | 7 | 7 | 14.29 | 14.29
TA 418 | 2025-03 | 2025-04 | 1 | 9 | 9 | 11.11 | 11.11
TA 418 | 2025-03 | 2025-05 | 1 | 9 | 9 | 11.11 | 11.11
TA 418 | 2025-03 | 2025-07 | 3 | 9 | 9 | 33.33 | 33.33
TA 418 | 2025-03 | 2025-08 | 1 | 9 | 9 | 11.11 | 11.11
TA 418 | 2025-03 | 2025-10 | 1 | 9 | 9 | 11.11 | 11.11
TA 418 | 2025-03 | 2025-11 | 1 | 9 | 9 | 11.11 | 11.11
TA 418 | 2025-03 | 2026-01 | 1 | 9 | 9 | 11.11 | 11.11
TA 418 | 2025-04 | 2025-07 | 1 | 6 | 5 | 16.67 | 20
TA 418 | 2025-04 | 2025-08 | 1 | 6 | 5 | 16.67 | 20
TA 418 | 2025-04 | 2025-09 | 2 | 6 | 5 | 33.33 | 40
TA 418 | 2025-04 | 2025-11 | 1 | 6 | 5 | 16.67 | 20
TA 418 | 2025-05 | 2025-06 | 1 | 10 | 10 | 10 | 10
TA 418 | 2025-05 | 2025-08 | 3 | 10 | 10 | 30 | 30
TA 418 | 2025-05 | 2025-09 | 4 | 10 | 10 | 40 | 40
TA 418 | 2025-05 | 2025-11 | 1 | 10 | 10 | 10 | 10
TA 418 | 2025-05 | 2026-01 | 1 | 10 | 10 | 10 | 10
TA 418 | 2025-06 | 2025-06 | 2 | 16 | 15 | 12.5 | 13.33
TA 418 | 2025-06 | 2025-07 | 4 | 16 | 15 | 25 | 26.67
TA 418 | 2025-06 | 2025-08 | 4 | 16 | 15 | 25 | 26.67
TA 418 | 2025-06 | 2025-09 | 2 | 16 | 15 | 12.5 | 13.33
TA 418 | 2025-06 | 2025-10 | 1 | 16 | 15 | 6.25 | 6.67
TA 418 | 2025-06 | 2025-11 | 1 | 16 | 15 | 6.25 | 6.67
TA 418 | 2025-06 | 2026-01 | 1 | 16 | 15 | 6.25 | 6.67
TA 418 | 2025-07 | 2025-08 | 1 | 17 | 17 | 5.88 | 5.88
TA 418 | 2025-07 | 2025-09 | 2 | 17 | 17 | 11.76 | 11.76
TA 418 | 2025-07 | 2025-10 | 2 | 17 | 17 | 11.76 | 11.76
TA 418 | 2025-07 | 2025-11 | 3 | 17 | 17 | 17.65 | 17.65
TA 418 | 2025-07 | 2025-12 | 7 | 17 | 17 | 41.18 | 41.18
TA 418 | 2025-07 | 2026-01 | 1 | 17 | 17 | 5.88 | 5.88
TA 418 | 2025-07 | 2026-02 | 1 | 17 | 17 | 5.88 | 5.88
TA 418 | 2025-08 | 2025-09 | 1 | 3 | 3 | 33.33 | 33.33
TA 418 | 2025-08 | 2025-12 | 2 | 3 | 3 | 66.67 | 66.67
TA 418 | 2025-11 | 2025-12 | 1 | 8 | 5 | 12.5 | 20
TA 418 | 2025-11 | 2026-01 | 2 | 8 | 5 | 25 | 40
TA 418 | 2025-11 | 2026-02 | 2 | 8 | 5 | 25 | 40
TA 418 | 2025-12 | 2025-12 | 1 | 6 | 3 | 16.67 | 33.33
TA 418 | 2025-12 | 2026-01 | 2 | 6 | 3 | 33.33 | 66.67
TA 418 | 2026-01 | 2026-02 | 1 | 3 | 1 | 33.33 | 100
TA 418 | 2026-02 | 2026-02 | 1 | 4 | 1 | 25 | 100
TA 419 | 2024-05 | 2025-01 | 2 | 3 | 3 | 66.67 | 66.67
TA 419 | 2024-05 | 2025-02 | 1 | 3 | 3 | 33.33 | 33.33
TA 419 | 2024-06 | 2024-11 | 3 | 9 | 9 | 33.33 | 33.33
TA 419 | 2024-06 | 2024-12 | 1 | 9 | 9 | 11.11 | 11.11
TA 419 | 2024-06 | 2025-01 | 2 | 9 | 9 | 22.22 | 22.22
TA 419 | 2024-06 | 2025-02 | 1 | 9 | 9 | 11.11 | 11.11
TA 419 | 2024-06 | 2025-04 | 2 | 9 | 9 | 22.22 | 22.22
TA 419 | 2024-07 | 2024-11 | 1 | 17 | 16 | 5.88 | 6.25
TA 419 | 2024-07 | 2024-12 | 6 | 17 | 16 | 35.29 | 37.5
TA 419 | 2024-07 | 2025-01 | 1 | 17 | 16 | 5.88 | 6.25
TA 419 | 2024-07 | 2025-02 | 1 | 17 | 16 | 5.88 | 6.25
TA 419 | 2024-07 | 2025-03 | 2 | 17 | 16 | 11.76 | 12.5
TA 419 | 2024-07 | 2025-04 | 2 | 17 | 16 | 11.76 | 12.5
TA 419 | 2024-07 | 2025-05 | 1 | 17 | 16 | 5.88 | 6.25
TA 419 | 2024-07 | 2025-07 | 1 | 17 | 16 | 5.88 | 6.25
TA 419 | 2024-07 | 2025-10 | 1 | 17 | 16 | 5.88 | 6.25
TA 419 | 2024-08 | 2024-11 | 1 | 8 | 8 | 12.5 | 12.5
TA 419 | 2024-08 | 2024-12 | 1 | 8 | 8 | 12.5 | 12.5
TA 419 | 2024-08 | 2025-01 | 1 | 8 | 8 | 12.5 | 12.5
TA 419 | 2024-08 | 2025-02 | 1 | 8 | 8 | 12.5 | 12.5
TA 419 | 2024-08 | 2025-04 | 2 | 8 | 8 | 25 | 25
TA 419 | 2024-08 | 2025-07 | 1 | 8 | 8 | 12.5 | 12.5
TA 419 | 2024-08 | 2025-09 | 1 | 8 | 8 | 12.5 | 12.5
TA 419 | 2024-09 | 2024-12 | 2 | 16 | 16 | 12.5 | 12.5
TA 419 | 2024-09 | 2025-01 | 5 | 16 | 16 | 31.25 | 31.25
TA 419 | 2024-09 | 2025-02 | 1 | 16 | 16 | 6.25 | 6.25
TA 419 | 2024-09 | 2025-03 | 1 | 16 | 16 | 6.25 | 6.25
TA 419 | 2024-09 | 2025-04 | 3 | 16 | 16 | 18.75 | 18.75
TA 419 | 2024-09 | 2025-06 | 2 | 16 | 16 | 12.5 | 12.5
TA 419 | 2024-09 | 2025-09 | 1 | 16 | 16 | 6.25 | 6.25
TA 419 | 2024-09 | 2025-12 | 1 | 16 | 16 | 6.25 | 6.25
TA 419 | 2024-10 | 2024-12 | 1 | 18 | 18 | 5.56 | 5.56
TA 419 | 2024-10 | 2025-01 | 3 | 18 | 18 | 16.67 | 16.67
TA 419 | 2024-10 | 2025-02 | 5 | 18 | 18 | 27.78 | 27.78
TA 419 | 2024-10 | 2025-03 | 2 | 18 | 18 | 11.11 | 11.11
TA 419 | 2024-10 | 2025-04 | 2 | 18 | 18 | 11.11 | 11.11
TA 419 | 2024-10 | 2025-05 | 1 | 18 | 18 | 5.56 | 5.56
TA 419 | 2024-10 | 2025-06 | 2 | 18 | 18 | 11.11 | 11.11
TA 419 | 2024-10 | 2025-11 | 1 | 18 | 18 | 5.56 | 5.56
TA 419 | 2024-10 | 2025-12 | 1 | 18 | 18 | 5.56 | 5.56
TA 419 | 2024-11 | 2025-01 | 2 | 14 | 14 | 14.29 | 14.29
TA 419 | 2024-11 | 2025-02 | 4 | 14 | 14 | 28.57 | 28.57
TA 419 | 2024-11 | 2025-03 | 3 | 14 | 14 | 21.43 | 21.43
TA 419 | 2024-11 | 2025-08 | 2 | 14 | 14 | 14.29 | 14.29
TA 419 | 2024-11 | 2025-09 | 2 | 14 | 14 | 14.29 | 14.29
TA 419 | 2024-11 | 2025-10 | 1 | 14 | 14 | 7.14 | 7.14
TA 419 | 2024-12 | 2025-01 | 1 | 12 | 12 | 8.33 | 8.33
TA 419 | 2024-12 | 2025-02 | 1 | 12 | 12 | 8.33 | 8.33
TA 419 | 2024-12 | 2025-03 | 2 | 12 | 12 | 16.67 | 16.67
TA 419 | 2024-12 | 2025-04 | 3 | 12 | 12 | 25 | 25
TA 419 | 2024-12 | 2025-08 | 2 | 12 | 12 | 16.67 | 16.67
TA 419 | 2024-12 | 2025-10 | 2 | 12 | 12 | 16.67 | 16.67
TA 419 | 2024-12 | 2026-05 | 1 | 12 | 12 | 8.33 | 8.33
TA 419 | 2025-01 | 2025-04 | 1 | 7 | 7 | 14.29 | 14.29
TA 419 | 2025-01 | 2025-07 | 1 | 7 | 7 | 14.29 | 14.29
TA 419 | 2025-01 | 2025-08 | 5 | 7 | 7 | 71.43 | 71.43
TA 419 | 2025-02 | 2025-11 | 3 | 10 | 10 | 30 | 30
TA 419 | 2025-02 | 2025-12 | 6 | 10 | 10 | 60 | 60
TA 419 | 2025-02 | 2026-06 | 1 | 10 | 10 | 10 | 10
TA 419 | 2025-03 | 2025-07 | 1 | 5 | 5 | 20 | 20
TA 419 | 2025-03 | 2025-11 | 2 | 5 | 5 | 40 | 40
TA 419 | 2025-03 | 2025-12 | 2 | 5 | 5 | 40 | 40
TA 419 | 2025-04 | 2025-07 | 1 | 14 | 14 | 7.14 | 7.14
TA 419 | 2025-04 | 2025-11 | 6 | 14 | 14 | 42.86 | 42.86
TA 419 | 2025-04 | 2025-12 | 7 | 14 | 14 | 50 | 50
TA 419 | 2025-05 | 2025-10 | 1 | 8 | 8 | 12.5 | 12.5
TA 419 | 2025-05 | 2025-11 | 2 | 8 | 8 | 25 | 25
TA 419 | 2025-05 | 2025-12 | 2 | 8 | 8 | 25 | 25
TA 419 | 2025-05 | 2026-01 | 1 | 8 | 8 | 12.5 | 12.5
TA 419 | 2025-05 | 2026-04 | 1 | 8 | 8 | 12.5 | 12.5
TA 419 | 2025-05 | 2026-06 | 1 | 8 | 8 | 12.5 | 12.5
TA 419 | 2025-06 | 2025-07 | 2 | 10 | 10 | 20 | 20
TA 419 | 2025-06 | 2025-10 | 2 | 10 | 10 | 20 | 20
TA 419 | 2025-06 | 2025-11 | 3 | 10 | 10 | 30 | 30
TA 419 | 2025-06 | 2025-12 | 1 | 10 | 10 | 10 | 10
TA 419 | 2025-06 | 2026-03 | 1 | 10 | 10 | 10 | 10
TA 419 | 2025-06 | 2026-07 | 1 | 10 | 10 | 10 | 10
TA 419 | 2025-07 | 2025-09 | 1 | 5 | 5 | 20 | 20
TA 419 | 2025-07 | 2025-12 | 2 | 5 | 5 | 40 | 40
TA 419 | 2025-07 | 2026-02 | 1 | 5 | 5 | 20 | 20
TA 419 | 2025-07 | 2026-08 | 1 | 5 | 5 | 20 | 20
TA 419 | 2025-08 | 2025-12 | 1 | 2 | 1 | 50 | 100
TA 419 | 2025-09 | 2025-11 | 3 | 3 | 3 | 100 | 100
TA 419 | 2025-10 | 2025-10 | 1 | 6 | 6 | 16.67 | 16.67
TA 419 | 2025-10 | 2025-11 | 2 | 6 | 6 | 33.33 | 33.33
TA 419 | 2025-10 | 2025-12 | 1 | 6 | 6 | 16.67 | 16.67
TA 419 | 2025-10 | 2026-01 | 1 | 6 | 6 | 16.67 | 16.67
TA 419 | 2025-10 | 2026-04 | 1 | 6 | 6 | 16.67 | 16.67
TA 419 | 2025-11 | 2025-11 | 1 | 18 | 16 | 5.56 | 6.25
TA 419 | 2025-11 | 2025-12 | 9 | 18 | 16 | 50 | 56.25
TA 419 | 2025-11 | 2026-01 | 1 | 18 | 16 | 5.56 | 6.25
TA 419 | 2025-11 | 2026-04 | 2 | 18 | 16 | 11.11 | 12.5
TA 419 | 2025-11 | 2026-05 | 1 | 18 | 16 | 5.56 | 6.25
TA 419 | 2025-11 | 2026-07 | 2 | 18 | 16 | 11.11 | 12.5
TA 419 | 2025-12 | 2025-12 | 5 | 18 | 18 | 27.78 | 27.78
TA 419 | 2025-12 | 2026-01 | 11 | 18 | 18 | 61.11 | 61.11
TA 419 | 2025-12 | 2026-04 | 2 | 18 | 18 | 11.11 | 11.11
TA 419 | 2026-01 | 2026-01 | 5 | 12 | 11 | 41.67 | 45.45
TA 419 | 2026-01 | 2026-04 | 2 | 12 | 11 | 16.67 | 18.18
TA 419 | 2026-01 | 2026-05 | 1 | 12 | 11 | 8.33 | 9.09
TA 419 | 2026-01 | 2026-07 | 2 | 12 | 11 | 16.67 | 18.18
TA 419 | 2026-01 | 2026-08 | 1 | 12 | 11 | 8.33 | 9.09
TA 419 | 2026-02 | 2026-04 | 2 | 7 | 6 | 28.57 | 33.33
TA 419 | 2026-02 | 2026-05 | 2 | 7 | 6 | 28.57 | 33.33
TA 419 | 2026-02 | 2026-07 | 2 | 7 | 6 | 28.57 | 33.33
TA 419 | 2026-03 | 2026-04 | 4 | 6 | 6 | 66.67 | 66.67
TA 419 | 2026-03 | 2026-05 | 2 | 6 | 6 | 33.33 | 33.33
TA 419 | 2026-04 | 2026-04 | 1 | 8 | 7 | 12.5 | 14.29
TA 419 | 2026-04 | 2026-05 | 4 | 8 | 7 | 50 | 57.14
TA 419 | 2026-04 | 2026-07 | 1 | 8 | 7 | 12.5 | 14.29
TA 419 | 2026-04 | 2026-08 | 1 | 8 | 7 | 12.5 | 14.29
TA 419 | 2026-05 | 2026-05 | 3 | 18 | 16 | 16.67 | 18.75
TA 419 | 2026-05 | 2026-06 | 9 | 18 | 16 | 50 | 56.25
TA 419 | 2026-05 | 2026-07 | 4 | 18 | 16 | 22.22 | 25
TA 419 | 2026-06 | 2026-06 | 6 | 16 | 12 | 37.5 | 50
TA 419 | 2026-06 | 2026-07 | 6 | 16 | 12 | 37.5 | 50
TA 419 | 2026-07 | 2026-07 | 5 | 14 | 7 | 35.71 | 71.43
TA 419 | 2026-07 | 2026-08 | 2 | 14 | 7 | 14.29 | 28.57
TA 421 | 2024-05 | 2024-08 | 1 | 1 | 1 | 100 | 100
TA 421 | 2024-06 | 2024-07 | 1 | 14 | 14 | 7.14 | 7.14
TA 421 | 2024-06 | 2024-08 | 3 | 14 | 14 | 21.43 | 21.43
TA 421 | 2024-06 | 2024-09 | 1 | 14 | 14 | 7.14 | 7.14
TA 421 | 2024-06 | 2024-10 | 5 | 14 | 14 | 35.71 | 35.71
TA 421 | 2024-06 | 2024-11 | 1 | 14 | 14 | 7.14 | 7.14
TA 421 | 2024-06 | 2024-12 | 2 | 14 | 14 | 14.29 | 14.29
TA 421 | 2024-06 | 2025-02 | 1 | 14 | 14 | 7.14 | 7.14
TA 421 | 2024-07 | 2024-07 | 2 | 20 | 20 | 10 | 10
TA 421 | 2024-07 | 2024-08 | 4 | 20 | 20 | 20 | 20
TA 421 | 2024-07 | 2024-09 | 3 | 20 | 20 | 15 | 15
TA 421 | 2024-07 | 2024-10 | 4 | 20 | 20 | 20 | 20
TA 421 | 2024-07 | 2024-11 | 4 | 20 | 20 | 20 | 20
TA 421 | 2024-07 | 2024-12 | 1 | 20 | 20 | 5 | 5
TA 421 | 2024-07 | 2025-02 | 1 | 20 | 20 | 5 | 5
TA 421 | 2024-07 | 2025-03 | 1 | 20 | 20 | 5 | 5
TA 421 | 2024-08 | 2024-09 | 5 | 21 | 21 | 23.81 | 23.81
TA 421 | 2024-08 | 2024-10 | 4 | 21 | 21 | 19.05 | 19.05
TA 421 | 2024-08 | 2024-11 | 9 | 21 | 21 | 42.86 | 42.86
TA 421 | 2024-08 | 2024-12 | 2 | 21 | 21 | 9.52 | 9.52
TA 421 | 2024-08 | 2025-04 | 1 | 21 | 21 | 4.76 | 4.76
TA 421 | 2024-09 | 2024-10 | 2 | 10 | 10 | 20 | 20
TA 421 | 2024-09 | 2024-11 | 2 | 10 | 10 | 20 | 20
TA 421 | 2024-09 | 2024-12 | 1 | 10 | 10 | 10 | 10
TA 421 | 2024-09 | 2025-01 | 3 | 10 | 10 | 30 | 30
TA 421 | 2024-09 | 2025-03 | 1 | 10 | 10 | 10 | 10
TA 421 | 2024-09 | 2025-06 | 1 | 10 | 10 | 10 | 10
TA 421 | 2024-10 | 2024-11 | 1 | 13 | 13 | 7.69 | 7.69
TA 421 | 2024-10 | 2024-12 | 4 | 13 | 13 | 30.77 | 30.77
TA 421 | 2024-10 | 2025-01 | 1 | 13 | 13 | 7.69 | 7.69
TA 421 | 2024-10 | 2025-02 | 1 | 13 | 13 | 7.69 | 7.69
TA 421 | 2024-10 | 2025-04 | 1 | 13 | 13 | 7.69 | 7.69
TA 421 | 2024-10 | 2025-06 | 1 | 13 | 13 | 7.69 | 7.69
TA 421 | 2024-10 | 2025-08 | 1 | 13 | 13 | 7.69 | 7.69
TA 421 | 2024-10 | 2025-09 | 2 | 13 | 13 | 15.38 | 15.38
TA 421 | 2024-10 | 2025-11 | 1 | 13 | 13 | 7.69 | 7.69
TA 421 | 2024-11 | 2024-12 | 2 | 21 | 21 | 9.52 | 9.52
TA 421 | 2024-11 | 2025-01 | 4 | 21 | 21 | 19.05 | 19.05
TA 421 | 2024-11 | 2025-02 | 5 | 21 | 21 | 23.81 | 23.81
TA 421 | 2024-11 | 2025-03 | 5 | 21 | 21 | 23.81 | 23.81
TA 421 | 2024-11 | 2025-05 | 1 | 21 | 21 | 4.76 | 4.76
TA 421 | 2024-11 | 2025-07 | 1 | 21 | 21 | 4.76 | 4.76
TA 421 | 2024-11 | 2025-08 | 1 | 21 | 21 | 4.76 | 4.76
TA 421 | 2024-11 | 2025-09 | 1 | 21 | 21 | 4.76 | 4.76
TA 421 | 2024-11 | 2025-10 | 1 | 21 | 21 | 4.76 | 4.76
TA 421 | 2024-12 | 2024-12 | 3 | 34 | 33 | 8.82 | 9.09
TA 421 | 2024-12 | 2025-01 | 3 | 34 | 33 | 8.82 | 9.09
TA 421 | 2024-12 | 2025-02 | 6 | 34 | 33 | 17.65 | 18.18
TA 421 | 2024-12 | 2025-03 | 8 | 34 | 33 | 23.53 | 24.24
TA 421 | 2024-12 | 2025-04 | 3 | 34 | 33 | 8.82 | 9.09
TA 421 | 2024-12 | 2025-05 | 1 | 34 | 33 | 2.94 | 3.03
TA 421 | 2024-12 | 2025-06 | 6 | 34 | 33 | 17.65 | 18.18
TA 421 | 2024-12 | 2025-08 | 1 | 34 | 33 | 2.94 | 3.03
TA 421 | 2024-12 | 2025-09 | 1 | 34 | 33 | 2.94 | 3.03
TA 421 | 2024-12 | 2025-11 | 1 | 34 | 33 | 2.94 | 3.03
TA 421 | 2025-01 | 2025-01 | 3 | 36 | 36 | 8.33 | 8.33
TA 421 | 2025-01 | 2025-02 | 2 | 36 | 36 | 5.56 | 5.56
TA 421 | 2025-01 | 2025-03 | 6 | 36 | 36 | 16.67 | 16.67
TA 421 | 2025-01 | 2025-04 | 7 | 36 | 36 | 19.44 | 19.44
TA 421 | 2025-01 | 2025-05 | 7 | 36 | 36 | 19.44 | 19.44
TA 421 | 2025-01 | 2025-06 | 1 | 36 | 36 | 2.78 | 2.78
TA 421 | 2025-01 | 2025-07 | 3 | 36 | 36 | 8.33 | 8.33
TA 421 | 2025-01 | 2025-08 | 1 | 36 | 36 | 2.78 | 2.78
TA 421 | 2025-01 | 2025-10 | 4 | 36 | 36 | 11.11 | 11.11
TA 421 | 2025-01 | 2025-11 | 1 | 36 | 36 | 2.78 | 2.78
TA 421 | 2025-01 | 2025-12 | 1 | 36 | 36 | 2.78 | 2.78
TA 421 | 2025-02 | 2025-03 | 3 | 30 | 30 | 10 | 10
TA 421 | 2025-02 | 2025-04 | 3 | 30 | 30 | 10 | 10
TA 421 | 2025-02 | 2025-05 | 6 | 30 | 30 | 20 | 20
TA 421 | 2025-02 | 2025-06 | 1 | 30 | 30 | 3.33 | 3.33
TA 421 | 2025-02 | 2025-07 | 9 | 30 | 30 | 30 | 30
TA 421 | 2025-02 | 2025-08 | 3 | 30 | 30 | 10 | 10
TA 421 | 2025-02 | 2025-09 | 1 | 30 | 30 | 3.33 | 3.33
TA 421 | 2025-02 | 2025-10 | 1 | 30 | 30 | 3.33 | 3.33
TA 421 | 2025-02 | 2025-11 | 3 | 30 | 30 | 10 | 10
TA 421 | 2025-03 | 2025-03 | 1 | 19 | 19 | 5.26 | 5.26
TA 421 | 2025-03 | 2025-04 | 5 | 19 | 19 | 26.32 | 26.32
TA 421 | 2025-03 | 2025-06 | 1 | 19 | 19 | 5.26 | 5.26
TA 421 | 2025-03 | 2025-07 | 2 | 19 | 19 | 10.53 | 10.53
TA 421 | 2025-03 | 2025-08 | 8 | 19 | 19 | 42.11 | 42.11
TA 421 | 2025-03 | 2025-10 | 2 | 19 | 19 | 10.53 | 10.53
TA 421 | 2025-04 | 2025-04 | 1 | 11 | 11 | 9.09 | 9.09
TA 421 | 2025-04 | 2025-05 | 2 | 11 | 11 | 18.18 | 18.18
TA 421 | 2025-04 | 2025-06 | 1 | 11 | 11 | 9.09 | 9.09
TA 421 | 2025-04 | 2025-07 | 4 | 11 | 11 | 36.36 | 36.36
TA 421 | 2025-04 | 2025-08 | 1 | 11 | 11 | 9.09 | 9.09
TA 421 | 2025-04 | 2025-11 | 1 | 11 | 11 | 9.09 | 9.09
TA 421 | 2025-04 | 2025-12 | 1 | 11 | 11 | 9.09 | 9.09
TA 421 | 2025-05 | 2025-06 | 1 | 34 | 32 | 2.94 | 3.12
TA 421 | 2025-05 | 2025-07 | 5 | 34 | 32 | 14.71 | 15.62
TA 421 | 2025-05 | 2025-08 | 2 | 34 | 32 | 5.88 | 6.25
TA 421 | 2025-05 | 2025-09 | 10 | 34 | 32 | 29.41 | 31.25
TA 421 | 2025-05 | 2025-10 | 3 | 34 | 32 | 8.82 | 9.38
TA 421 | 2025-05 | 2025-11 | 7 | 34 | 32 | 20.59 | 21.88
TA 421 | 2025-05 | 2025-12 | 2 | 34 | 32 | 5.88 | 6.25
TA 421 | 2025-05 | 2026-01 | 2 | 34 | 32 | 5.88 | 6.25
TA 421 | 2025-06 | 2025-08 | 2 | 23 | 23 | 8.7 | 8.7
TA 421 | 2025-06 | 2025-09 | 4 | 23 | 23 | 17.39 | 17.39
TA 421 | 2025-06 | 2025-10 | 4 | 23 | 23 | 17.39 | 17.39
TA 421 | 2025-06 | 2025-11 | 3 | 23 | 23 | 13.04 | 13.04
TA 421 | 2025-06 | 2025-12 | 9 | 23 | 23 | 39.13 | 39.13
TA 421 | 2025-06 | 2026-01 | 1 | 23 | 23 | 4.35 | 4.35
TA 421 | 2025-07 | 2025-09 | 2 | 11 | 11 | 18.18 | 18.18
TA 421 | 2025-07 | 2025-10 | 1 | 11 | 11 | 9.09 | 9.09
TA 421 | 2025-07 | 2025-11 | 4 | 11 | 11 | 36.36 | 36.36
TA 421 | 2025-07 | 2025-12 | 4 | 11 | 11 | 36.36 | 36.36
TA 421 | 2025-08 | 2025-10 | 1 | 2 | 2 | 50 | 50
TA 421 | 2025-08 | 2025-12 | 1 | 2 | 2 | 50 | 50
TA 421 | 2025-10 | 2025-12 | 1 | 3 | 1 | 33.33 | 100
TA 421 | 2025-11 | 2025-12 | 1 | 1 | 1 | 100 | 100
TA 421 | 2025-12 | 2025-12 | 1 | 1 | 1 | 100 | 100
TA 505 | 2024-03 | 2025-12 | 1 | 1 | 1 | 100 | 100
TA 505 | 2024-04 | 2025-09 | 1 | 2 | 2 | 50 | 50
TA 505 | 2024-04 | 2026-01 | 1 | 2 | 2 | 50 | 50
TA 505 | 2024-10 | 2025-01 | 3 | 9 | 9 | 33.33 | 33.33
TA 505 | 2024-10 | 2025-02 | 2 | 9 | 9 | 22.22 | 22.22
TA 505 | 2024-10 | 2025-03 | 2 | 9 | 9 | 22.22 | 22.22
TA 505 | 2024-10 | 2025-04 | 1 | 9 | 9 | 11.11 | 11.11
TA 505 | 2024-10 | 2025-09 | 1 | 9 | 9 | 11.11 | 11.11
TA 505 | 2024-11 | 2025-01 | 1 | 26 | 26 | 3.85 | 3.85
TA 505 | 2024-11 | 2025-02 | 5 | 26 | 26 | 19.23 | 19.23
TA 505 | 2024-11 | 2025-03 | 8 | 26 | 26 | 30.77 | 30.77
TA 505 | 2024-11 | 2025-04 | 8 | 26 | 26 | 30.77 | 30.77
TA 505 | 2024-11 | 2025-05 | 2 | 26 | 26 | 7.69 | 7.69
TA 505 | 2024-11 | 2025-09 | 2 | 26 | 26 | 7.69 | 7.69
TA 505 | 2024-12 | 2025-03 | 3 | 36 | 36 | 8.33 | 8.33
TA 505 | 2024-12 | 2025-04 | 8 | 36 | 36 | 22.22 | 22.22
TA 505 | 2024-12 | 2025-05 | 9 | 36 | 36 | 25 | 25
TA 505 | 2024-12 | 2025-06 | 6 | 36 | 36 | 16.67 | 16.67
TA 505 | 2024-12 | 2025-08 | 2 | 36 | 36 | 5.56 | 5.56
TA 505 | 2024-12 | 2025-09 | 2 | 36 | 36 | 5.56 | 5.56
TA 505 | 2024-12 | 2025-10 | 2 | 36 | 36 | 5.56 | 5.56
TA 505 | 2024-12 | 2025-11 | 1 | 36 | 36 | 2.78 | 2.78
TA 505 | 2024-12 | 2025-12 | 2 | 36 | 36 | 5.56 | 5.56
TA 505 | 2024-12 | 2026-01 | 1 | 36 | 36 | 2.78 | 2.78
TA 505 | 2025-01 | 2025-04 | 2 | 30 | 30 | 6.67 | 6.67
TA 505 | 2025-01 | 2025-05 | 7 | 30 | 30 | 23.33 | 23.33
TA 505 | 2025-01 | 2025-06 | 1 | 30 | 30 | 3.33 | 3.33
TA 505 | 2025-01 | 2025-07 | 4 | 30 | 30 | 13.33 | 13.33
TA 505 | 2025-01 | 2025-08 | 1 | 30 | 30 | 3.33 | 3.33
TA 505 | 2025-01 | 2025-09 | 3 | 30 | 30 | 10 | 10
TA 505 | 2025-01 | 2025-10 | 4 | 30 | 30 | 13.33 | 13.33
TA 505 | 2025-01 | 2025-11 | 1 | 30 | 30 | 3.33 | 3.33
TA 505 | 2025-01 | 2025-12 | 4 | 30 | 30 | 13.33 | 13.33
TA 505 | 2025-01 | 2026-04 | 3 | 30 | 30 | 10 | 10
TA 505 | 2025-02 | 2025-03 | 1 | 32 | 32 | 3.12 | 3.12
TA 505 | 2025-02 | 2025-05 | 3 | 32 | 32 | 9.38 | 9.38
TA 505 | 2025-02 | 2025-06 | 6 | 32 | 32 | 18.75 | 18.75
TA 505 | 2025-02 | 2025-07 | 1 | 32 | 32 | 3.12 | 3.12
TA 505 | 2025-02 | 2025-08 | 3 | 32 | 32 | 9.38 | 9.38
TA 505 | 2025-02 | 2025-09 | 4 | 32 | 32 | 12.5 | 12.5
TA 505 | 2025-02 | 2025-10 | 3 | 32 | 32 | 9.38 | 9.38
TA 505 | 2025-02 | 2025-11 | 5 | 32 | 32 | 15.62 | 15.62
TA 505 | 2025-02 | 2025-12 | 1 | 32 | 32 | 3.12 | 3.12
TA 505 | 2025-02 | 2026-02 | 2 | 32 | 32 | 6.25 | 6.25
TA 505 | 2025-02 | 2026-03 | 1 | 32 | 32 | 3.12 | 3.12
TA 505 | 2025-02 | 2026-04 | 2 | 32 | 32 | 6.25 | 6.25
TA 505 | 2025-03 | 2025-04 | 1 | 21 | 21 | 4.76 | 4.76
TA 505 | 2025-03 | 2025-05 | 3 | 21 | 21 | 14.29 | 14.29
TA 505 | 2025-03 | 2025-08 | 1 | 21 | 21 | 4.76 | 4.76
TA 505 | 2025-03 | 2025-09 | 2 | 21 | 21 | 9.52 | 9.52
TA 505 | 2025-03 | 2025-10 | 1 | 21 | 21 | 4.76 | 4.76
TA 505 | 2025-03 | 2025-11 | 2 | 21 | 21 | 9.52 | 9.52
TA 505 | 2025-03 | 2025-12 | 6 | 21 | 21 | 28.57 | 28.57
TA 505 | 2025-03 | 2026-01 | 1 | 21 | 21 | 4.76 | 4.76
TA 505 | 2025-03 | 2026-02 | 1 | 21 | 21 | 4.76 | 4.76
TA 505 | 2025-03 | 2026-03 | 2 | 21 | 21 | 9.52 | 9.52
TA 505 | 2025-03 | 2026-05 | 1 | 21 | 21 | 4.76 | 4.76
TA 505 | 2025-04 | 2025-06 | 1 | 48 | 48 | 2.08 | 2.08
TA 505 | 2025-04 | 2025-08 | 3 | 48 | 48 | 6.25 | 6.25
TA 505 | 2025-04 | 2025-09 | 6 | 48 | 48 | 12.5 | 12.5
TA 505 | 2025-04 | 2025-10 | 7 | 48 | 48 | 14.58 | 14.58
TA 505 | 2025-04 | 2025-11 | 10 | 48 | 48 | 20.83 | 20.83
TA 505 | 2025-04 | 2025-12 | 5 | 48 | 48 | 10.42 | 10.42
TA 505 | 2025-04 | 2026-01 | 3 | 48 | 48 | 6.25 | 6.25
TA 505 | 2025-04 | 2026-02 | 1 | 48 | 48 | 2.08 | 2.08
TA 505 | 2025-04 | 2026-03 | 4 | 48 | 48 | 8.33 | 8.33
TA 505 | 2025-04 | 2026-04 | 8 | 48 | 48 | 16.67 | 16.67
TA 505 | 2025-05 | 2025-07 | 2 | 47 | 47 | 4.26 | 4.26
TA 505 | 2025-05 | 2025-08 | 4 | 47 | 47 | 8.51 | 8.51
TA 505 | 2025-05 | 2025-09 | 8 | 47 | 47 | 17.02 | 17.02
TA 505 | 2025-05 | 2025-10 | 8 | 47 | 47 | 17.02 | 17.02
TA 505 | 2025-05 | 2025-11 | 2 | 47 | 47 | 4.26 | 4.26
TA 505 | 2025-05 | 2025-12 | 5 | 47 | 47 | 10.64 | 10.64
TA 505 | 2025-05 | 2026-01 | 7 | 47 | 47 | 14.89 | 14.89
TA 505 | 2025-05 | 2026-02 | 3 | 47 | 47 | 6.38 | 6.38
TA 505 | 2025-05 | 2026-03 | 3 | 47 | 47 | 6.38 | 6.38
TA 505 | 2025-05 | 2026-04 | 5 | 47 | 47 | 10.64 | 10.64
TA 505 | 2025-06 | 2025-08 | 1 | 15 | 15 | 6.67 | 6.67
TA 505 | 2025-06 | 2025-10 | 1 | 15 | 15 | 6.67 | 6.67
TA 505 | 2025-06 | 2025-11 | 3 | 15 | 15 | 20 | 20
TA 505 | 2025-06 | 2025-12 | 2 | 15 | 15 | 13.33 | 13.33
TA 505 | 2025-06 | 2026-01 | 2 | 15 | 15 | 13.33 | 13.33
TA 505 | 2025-06 | 2026-03 | 4 | 15 | 15 | 26.67 | 26.67
TA 505 | 2025-06 | 2026-04 | 2 | 15 | 15 | 13.33 | 13.33
TA 505 | 2025-07 | 2025-09 | 1 | 2 | 2 | 50 | 50
TA 505 | 2025-07 | 2025-10 | 1 | 2 | 2 | 50 | 50
TA 505 | 2025-08 | 2026-04 | 1 | 1 | 1 | 100 | 100
TA 505 | 2025-09 | 2025-10 | 1 | 10 | 10 | 10 | 10
TA 505 | 2025-09 | 2025-11 | 2 | 10 | 10 | 20 | 20
TA 505 | 2025-09 | 2025-12 | 5 | 10 | 10 | 50 | 50
TA 505 | 2025-09 | 2026-01 | 2 | 10 | 10 | 20 | 20
TA 505 | 2025-10 | 2025-11 | 6 | 12 | 12 | 50 | 50
TA 505 | 2025-10 | 2025-12 | 2 | 12 | 12 | 16.67 | 16.67
TA 505 | 2025-10 | 2026-02 | 2 | 12 | 12 | 16.67 | 16.67
TA 505 | 2025-10 | 2026-04 | 1 | 12 | 12 | 8.33 | 8.33
TA 505 | 2025-10 | 2026-05 | 1 | 12 | 12 | 8.33 | 8.33
TA 505 | 2025-11 | 2025-11 | 1 | 17 | 16 | 5.88 | 6.25
TA 505 | 2025-11 | 2025-12 | 9 | 17 | 16 | 52.94 | 56.25
TA 505 | 2025-11 | 2026-01 | 4 | 17 | 16 | 23.53 | 25
TA 505 | 2025-11 | 2026-02 | 1 | 17 | 16 | 5.88 | 6.25
TA 505 | 2025-11 | 2026-05 | 1 | 17 | 16 | 5.88 | 6.25
TA 505 | 2025-12 | 2025-12 | 4 | 18 | 16 | 22.22 | 25
TA 505 | 2025-12 | 2026-01 | 11 | 18 | 16 | 61.11 | 68.75
TA 505 | 2025-12 | 2026-02 | 1 | 18 | 16 | 5.56 | 6.25
TA 505 | 2026-01 | 2026-01 | 6 | 17 | 17 | 35.29 | 35.29
TA 505 | 2026-01 | 2026-02 | 8 | 17 | 17 | 47.06 | 47.06
TA 505 | 2026-01 | 2026-04 | 1 | 17 | 17 | 5.88 | 5.88
TA 505 | 2026-01 | 2026-05 | 1 | 17 | 17 | 5.88 | 5.88
TA 505 | 2026-01 | 2026-06 | 1 | 17 | 17 | 5.88 | 5.88
TA 505 | 2026-02 | 2026-02 | 6 | 10 | 8 | 60 | 75
TA 505 | 2026-02 | 2026-03 | 2 | 10 | 8 | 20 | 25
TA 505 | 2026-03 | 2026-03 | 2 | 8 | 5 | 25 | 40
TA 505 | 2026-03 | 2026-04 | 1 | 8 | 5 | 12.5 | 20
TA 505 | 2026-03 | 2026-05 | 1 | 8 | 5 | 12.5 | 20
TA 505 | 2026-03 | 2026-06 | 1 | 8 | 5 | 12.5 | 20
TA 505 | 2026-04 | 2026-04 | 1 | 8 | 4 | 12.5 | 25
TA 505 | 2026-04 | 2026-05 | 3 | 8 | 4 | 37.5 | 75
TA 505 | 2026-05 | 2026-05 | 2 | 4 | 3 | 50 | 66.67
TA 505 | 2026-05 | 2026-06 | 1 | 4 | 3 | 25 | 33.33
TA 505 | 2026-06 | 2026-06 | 1 | 4 | 3 | 25 | 33.33
TA 505 | 2026-06 | 2026-07 | 2 | 4 | 3 | 50 | 66.67
TA 510 | 2025-03 | 2026-06 | 1 | 5 | 1 | 20 | 100
TA 510 | 2025-04 | 2026-05 | 2 | 6 | 4 | 33.33 | 50
TA 510 | 2025-04 | 2026-06 | 2 | 6 | 4 | 33.33 | 50
TA 510 | 2025-05 | 2026-02 | 3 | 7 | 7 | 42.86 | 42.86
TA 510 | 2025-05 | 2026-05 | 4 | 7 | 7 | 57.14 | 57.14
TA 510 | 2025-06 | 2026-01 | 1 | 2 | 2 | 50 | 50
TA 510 | 2025-06 | 2026-06 | 1 | 2 | 2 | 50 | 50
TA 510 | 2025-08 | 2026-05 | 1 | 1 | 1 | 100 | 100
TA 510 | 2025-09 | 2026-01 | 1 | 2 | 2 | 50 | 50
TA 510 | 2025-09 | 2026-07 | 1 | 2 | 2 | 50 | 50
TA 510 | 2025-10 | 2026-01 | 4 | 5 | 4 | 80 | 100
TA 510 | 2025-11 | 2026-01 | 2 | 5 | 5 | 40 | 40
TA 510 | 2025-11 | 2026-02 | 1 | 5 | 5 | 20 | 20
TA 510 | 2025-11 | 2026-03 | 1 | 5 | 5 | 20 | 20
TA 510 | 2025-11 | 2026-07 | 1 | 5 | 5 | 20 | 20
TA 510 | 2025-12 | 2026-01 | 2 | 10 | 10 | 20 | 20
TA 510 | 2025-12 | 2026-02 | 3 | 10 | 10 | 30 | 30
TA 510 | 2025-12 | 2026-03 | 2 | 10 | 10 | 20 | 20
TA 510 | 2025-12 | 2026-04 | 3 | 10 | 10 | 30 | 30
TA 510 | 2026-01 | 2026-03 | 3 | 7 | 5 | 42.86 | 60
TA 510 | 2026-01 | 2026-05 | 2 | 7 | 5 | 28.57 | 40
TA 510 | 2026-02 | 2026-02 | 1 | 6 | 6 | 16.67 | 16.67
TA 510 | 2026-02 | 2026-03 | 1 | 6 | 6 | 16.67 | 16.67
TA 510 | 2026-02 | 2026-04 | 1 | 6 | 6 | 16.67 | 16.67
TA 510 | 2026-02 | 2026-05 | 3 | 6 | 6 | 50 | 50
TA 510 | 2026-03 | 2026-04 | 1 | 4 | 1 | 25 | 100
TA 510 | 2026-04 | 2026-05 | 1 | 8 | 1 | 12.5 | 100
TA 512 | 2025-02 | 2025-07 | 1 | 3 | 3 | 33.33 | 33.33
TA 512 | 2025-02 | 2025-08 | 1 | 3 | 3 | 33.33 | 33.33
TA 512 | 2025-02 | 2025-11 | 1 | 3 | 3 | 33.33 | 33.33
TA 512 | 2025-03 | 2025-08 | 5 | 26 | 26 | 19.23 | 19.23
TA 512 | 2025-03 | 2025-09 | 6 | 26 | 26 | 23.08 | 23.08
TA 512 | 2025-03 | 2025-10 | 3 | 26 | 26 | 11.54 | 11.54
TA 512 | 2025-03 | 2025-11 | 4 | 26 | 26 | 15.38 | 15.38
TA 512 | 2025-03 | 2025-12 | 1 | 26 | 26 | 3.85 | 3.85
TA 512 | 2025-03 | 2026-01 | 3 | 26 | 26 | 11.54 | 11.54
TA 512 | 2025-03 | 2026-02 | 3 | 26 | 26 | 11.54 | 11.54
TA 512 | 2025-03 | 2026-03 | 1 | 26 | 26 | 3.85 | 3.85
TA 512 | 2025-04 | 2025-08 | 3 | 24 | 24 | 12.5 | 12.5
TA 512 | 2025-04 | 2025-09 | 5 | 24 | 24 | 20.83 | 20.83
TA 512 | 2025-04 | 2025-10 | 2 | 24 | 24 | 8.33 | 8.33
TA 512 | 2025-04 | 2025-11 | 2 | 24 | 24 | 8.33 | 8.33
TA 512 | 2025-04 | 2025-12 | 6 | 24 | 24 | 25 | 25
TA 512 | 2025-04 | 2026-01 | 4 | 24 | 24 | 16.67 | 16.67
TA 512 | 2025-04 | 2026-02 | 2 | 24 | 24 | 8.33 | 8.33
TA 512 | 2025-05 | 2025-08 | 1 | 23 | 23 | 4.35 | 4.35
TA 512 | 2025-05 | 2025-09 | 4 | 23 | 23 | 17.39 | 17.39
TA 512 | 2025-05 | 2025-10 | 1 | 23 | 23 | 4.35 | 4.35
TA 512 | 2025-05 | 2025-11 | 2 | 23 | 23 | 8.7 | 8.7
TA 512 | 2025-05 | 2025-12 | 5 | 23 | 23 | 21.74 | 21.74
TA 512 | 2025-05 | 2026-01 | 4 | 23 | 23 | 17.39 | 17.39
TA 512 | 2025-05 | 2026-02 | 4 | 23 | 23 | 17.39 | 17.39
TA 512 | 2025-05 | 2026-05 | 1 | 23 | 23 | 4.35 | 4.35
TA 512 | 2025-05 | 2026-07 | 1 | 23 | 23 | 4.35 | 4.35
TA 512 | 2025-06 | 2025-10 | 2 | 27 | 25 | 7.41 | 8
TA 512 | 2025-06 | 2025-11 | 3 | 27 | 25 | 11.11 | 12
TA 512 | 2025-06 | 2025-12 | 5 | 27 | 25 | 18.52 | 20
TA 512 | 2025-06 | 2026-01 | 3 | 27 | 25 | 11.11 | 12
TA 512 | 2025-06 | 2026-02 | 9 | 27 | 25 | 33.33 | 36
TA 512 | 2025-06 | 2026-03 | 1 | 27 | 25 | 3.7 | 4
TA 512 | 2025-06 | 2026-05 | 1 | 27 | 25 | 3.7 | 4
TA 512 | 2025-06 | 2026-07 | 1 | 27 | 25 | 3.7 | 4
TA 512 | 2025-07 | 2025-10 | 1 | 35 | 35 | 2.86 | 2.86
TA 512 | 2025-07 | 2025-11 | 6 | 35 | 35 | 17.14 | 17.14
TA 512 | 2025-07 | 2025-12 | 8 | 35 | 35 | 22.86 | 22.86
TA 512 | 2025-07 | 2026-01 | 4 | 35 | 35 | 11.43 | 11.43
TA 512 | 2025-07 | 2026-02 | 4 | 35 | 35 | 11.43 | 11.43
TA 512 | 2025-07 | 2026-03 | 4 | 35 | 35 | 11.43 | 11.43
TA 512 | 2025-07 | 2026-04 | 2 | 35 | 35 | 5.71 | 5.71
TA 512 | 2025-07 | 2026-05 | 1 | 35 | 35 | 2.86 | 2.86
TA 512 | 2025-07 | 2026-07 | 4 | 35 | 35 | 11.43 | 11.43
TA 512 | 2025-07 | 2026-08 | 1 | 35 | 35 | 2.86 | 2.86
TA 512 | 2025-08 | 2025-09 | 1 | 26 | 25 | 3.85 | 4
TA 512 | 2025-08 | 2025-10 | 2 | 26 | 25 | 7.69 | 8
TA 512 | 2025-08 | 2025-11 | 1 | 26 | 25 | 3.85 | 4
TA 512 | 2025-08 | 2025-12 | 3 | 26 | 25 | 11.54 | 12
TA 512 | 2025-08 | 2026-01 | 7 | 26 | 25 | 26.92 | 28
TA 512 | 2025-08 | 2026-02 | 1 | 26 | 25 | 3.85 | 4
TA 512 | 2025-08 | 2026-03 | 4 | 26 | 25 | 15.38 | 16
TA 512 | 2025-08 | 2026-04 | 1 | 26 | 25 | 3.85 | 4
TA 512 | 2025-08 | 2026-05 | 1 | 26 | 25 | 3.85 | 4
TA 512 | 2025-08 | 2026-07 | 3 | 26 | 25 | 11.54 | 12
TA 512 | 2025-08 | 2026-08 | 1 | 26 | 25 | 3.85 | 4
TA 512 | 2025-09 | 2025-11 | 1 | 19 | 17 | 5.26 | 5.88
TA 512 | 2025-09 | 2025-12 | 1 | 19 | 17 | 5.26 | 5.88
TA 512 | 2025-09 | 2026-01 | 4 | 19 | 17 | 21.05 | 23.53
TA 512 | 2025-09 | 2026-02 | 5 | 19 | 17 | 26.32 | 29.41
TA 512 | 2025-09 | 2026-03 | 1 | 19 | 17 | 5.26 | 5.88
TA 512 | 2025-09 | 2026-05 | 1 | 19 | 17 | 5.26 | 5.88
TA 512 | 2025-09 | 2026-06 | 1 | 19 | 17 | 5.26 | 5.88
TA 512 | 2025-09 | 2026-07 | 1 | 19 | 17 | 5.26 | 5.88
TA 512 | 2025-09 | 2026-08 | 2 | 19 | 17 | 10.53 | 11.76
TA 512 | 2025-10 | 2025-12 | 4 | 23 | 21 | 17.39 | 19.05
TA 512 | 2025-10 | 2026-01 | 3 | 23 | 21 | 13.04 | 14.29
TA 512 | 2025-10 | 2026-02 | 2 | 23 | 21 | 8.7 | 9.52
TA 512 | 2025-10 | 2026-03 | 3 | 23 | 21 | 13.04 | 14.29
TA 512 | 2025-10 | 2026-04 | 3 | 23 | 21 | 13.04 | 14.29
TA 512 | 2025-10 | 2026-06 | 3 | 23 | 21 | 13.04 | 14.29
TA 512 | 2025-10 | 2026-07 | 3 | 23 | 21 | 13.04 | 14.29
TA 512 | 2025-11 | 2025-12 | 1 | 29 | 28 | 3.45 | 3.57
TA 512 | 2025-11 | 2026-01 | 7 | 29 | 28 | 24.14 | 25
TA 512 | 2025-11 | 2026-02 | 3 | 29 | 28 | 10.34 | 10.71
TA 512 | 2025-11 | 2026-03 | 5 | 29 | 28 | 17.24 | 17.86
TA 512 | 2025-11 | 2026-04 | 1 | 29 | 28 | 3.45 | 3.57
TA 512 | 2025-11 | 2026-05 | 1 | 29 | 28 | 3.45 | 3.57
TA 512 | 2025-11 | 2026-06 | 5 | 29 | 28 | 17.24 | 17.86
TA 512 | 2025-11 | 2026-07 | 5 | 29 | 28 | 17.24 | 17.86
TA 512 | 2025-12 | 2026-01 | 3 | 36 | 30 | 8.33 | 10
TA 512 | 2025-12 | 2026-02 | 7 | 36 | 30 | 19.44 | 23.33
TA 512 | 2025-12 | 2026-03 | 7 | 36 | 30 | 19.44 | 23.33
TA 512 | 2025-12 | 2026-04 | 2 | 36 | 30 | 5.56 | 6.67
TA 512 | 2025-12 | 2026-05 | 1 | 36 | 30 | 2.78 | 3.33
TA 512 | 2025-12 | 2026-06 | 4 | 36 | 30 | 11.11 | 13.33
TA 512 | 2025-12 | 2026-07 | 4 | 36 | 30 | 11.11 | 13.33
TA 512 | 2025-12 | 2026-08 | 2 | 36 | 30 | 5.56 | 6.67
TA 512 | 2026-01 | 2026-02 | 1 | 11 | 10 | 9.09 | 10
TA 512 | 2026-01 | 2026-03 | 1 | 11 | 10 | 9.09 | 10
TA 512 | 2026-01 | 2026-04 | 1 | 11 | 10 | 9.09 | 10
TA 512 | 2026-01 | 2026-06 | 3 | 11 | 10 | 27.27 | 30
TA 512 | 2026-01 | 2026-07 | 3 | 11 | 10 | 27.27 | 30
TA 512 | 2026-01 | 2026-08 | 1 | 11 | 10 | 9.09 | 10
TA 512 | 2026-02 | 2026-06 | 2 | 4 | 2 | 50 | 100
TA 512 | 2026-03 | 2026-03 | 1 | 3 | 3 | 33.33 | 33.33
TA 512 | 2026-03 | 2026-06 | 1 | 3 | 3 | 33.33 | 33.33
TA 512 | 2026-03 | 2026-08 | 1 | 3 | 3 | 33.33 | 33.33
TA 512 | 2026-04 | 2026-06 | 2 | 7 | 2 | 28.57 | 100
TA 512 | 2026-05 | 2026-07 | 4 | 5 | 5 | 80 | 80
TA 512 | 2026-05 | 2026-08 | 1 | 5 | 5 | 20 | 20
TA 512 | 2026-06 | 2026-07 | 2 | 6 | 3 | 33.33 | 66.67
TA 512 | 2026-06 | 2026-08 | 1 | 6 | 3 | 16.67 | 33.33
TA 512 | 2026-07 | 2026-07 | 1 | 4 | 1 | 25 | 100
TA 513 | 2025-03 | 2025-09 | 1 | 1 | 1 | 100 | 100
TA 513 | 2025-04 | 2025-09 | 1 | 14 | 2 | 7.14 | 50
TA 513 | 2025-04 | 2025-10 | 1 | 14 | 2 | 7.14 | 50
TA 513 | 2025-05 | 2025-09 | 1 | 15 | 9 | 6.67 | 11.11
TA 513 | 2025-05 | 2025-10 | 2 | 15 | 9 | 13.33 | 22.22
TA 513 | 2025-05 | 2025-11 | 5 | 15 | 9 | 33.33 | 55.56
TA 513 | 2025-05 | 2025-12 | 1 | 15 | 9 | 6.67 | 11.11
TA 513 | 2025-06 | 2026-03 | 1 | 8 | 1 | 12.5 | 100
TA 513 | 2025-07 | 2025-12 | 1 | 11 | 4 | 9.09 | 25
TA 513 | 2025-07 | 2026-01 | 2 | 11 | 4 | 18.18 | 50
TA 513 | 2025-07 | 2026-06 | 1 | 11 | 4 | 9.09 | 25
TA 513 | 2025-08 | 2026-01 | 1 | 3 | 2 | 33.33 | 50
TA 513 | 2025-08 | 2026-06 | 1 | 3 | 2 | 33.33 | 50
TA 513 | 2025-09 | 2025-10 | 3 | 7 | 4 | 42.86 | 75
TA 513 | 2025-09 | 2025-11 | 1 | 7 | 4 | 14.29 | 25
TA 513 | 2025-11 | 2026-03 | 2 | 2 | 2 | 100 | 100
TA 513 | 2025-12 | 2026-03 | 1 | 5 | 5 | 20 | 20
TA 513 | 2025-12 | 2026-04 | 1 | 5 | 5 | 20 | 20
TA 513 | 2025-12 | 2026-05 | 3 | 5 | 5 | 60 | 60
TA 513 | 2026-02 | 2026-03 | 1 | 2 | 2 | 50 | 50
TA 513 | 2026-02 | 2026-05 | 1 | 2 | 2 | 50 | 50
TA 513 | 2026-05 | 2026-06 | 1 | 16 | 1 | 6.25 | 100
TA 601 | 2025-08 | 2026-01 | 1 | 2 | 1 | 50 | 100
TA 601 | 2025-09 | 2026-01 | 1 | 2 | 2 | 50 | 50
TA 601 | 2025-09 | 2026-02 | 1 | 2 | 2 | 50 | 50
TA 601 | 2025-10 | 2026-01 | 7 | 8 | 7 | 87.5 | 100
TA 601 | 2025-11 | 2025-12 | 3 | 10 | 7 | 30 | 42.86
TA 601 | 2025-11 | 2026-01 | 3 | 10 | 7 | 30 | 42.86
TA 601 | 2025-11 | 2026-06 | 1 | 10 | 7 | 10 | 14.29
TA 601 | 2025-12 | 2025-12 | 1 | 20 | 13 | 5 | 7.69
TA 601 | 2025-12 | 2026-01 | 7 | 20 | 13 | 35 | 53.85
TA 601 | 2025-12 | 2026-02 | 3 | 20 | 13 | 15 | 23.08
TA 601 | 2025-12 | 2026-03 | 1 | 20 | 13 | 5 | 7.69
TA 601 | 2025-12 | 2026-12 | 1 | 20 | 13 | 5 | 7.69
TA 601 | 2026-01 | 2026-01 | 6 | 27 | 24 | 22.22 | 25
TA 601 | 2026-01 | 2026-02 | 14 | 27 | 24 | 51.85 | 58.33
TA 601 | 2026-01 | 2026-03 | 2 | 27 | 24 | 7.41 | 8.33
TA 601 | 2026-01 | 2026-05 | 1 | 27 | 24 | 3.7 | 4.17
TA 601 | 2026-01 | 2026-07 | 1 | 27 | 24 | 3.7 | 4.17
TA 601 | 2026-02 | 2026-02 | 8 | 17 | 15 | 47.06 | 53.33
TA 601 | 2026-02 | 2026-03 | 6 | 17 | 15 | 35.29 | 40
TA 601 | 2026-02 | 2026-06 | 1 | 17 | 15 | 5.88 | 6.67
TA 601 | 2026-03 | 2026-03 | 1 | 15 | 12 | 6.67 | 8.33
TA 601 | 2026-03 | 2026-04 | 2 | 15 | 12 | 13.33 | 16.67
TA 601 | 2026-03 | 2026-06 | 6 | 15 | 12 | 40 | 50
TA 601 | 2026-03 | 2026-07 | 3 | 15 | 12 | 20 | 25
TA 601 | 2026-04 | 2026-05 | 1 | 12 | 8 | 8.33 | 12.5
TA 601 | 2026-04 | 2026-06 | 5 | 12 | 8 | 41.67 | 62.5
TA 601 | 2026-04 | 2026-07 | 2 | 12 | 8 | 16.67 | 25
TA 601 | 2026-05 | 2026-06 | 6 | 11 | 7 | 54.55 | 85.71
TA 601 | 2026-05 | 2026-07 | 1 | 11 | 7 | 9.09 | 14.29
TA 601 | 2026-06 | 2026-06 | 2 | 24 | 13 | 8.33 | 15.38
TA 601 | 2026-06 | 2026-07 | 11 | 24 | 13 | 45.83 | 84.62
TA 601 | 2026-07 | 2026-07 | 12 | 32 | 13 | 37.5 | 92.31
TA 601 | 2026-07 | 2026-08 | 1 | 32 | 13 | 3.12 | 7.69
TB 501 | 2024-08 | 2025-01 | 1 | 3 | 3 | 33.33 | 33.33
TB 501 | 2024-08 | 2025-02 | 2 | 3 | 3 | 66.67 | 66.67
TB 501 | 2024-09 | 2024-12 | 3 | 7 | 7 | 42.86 | 42.86
TB 501 | 2024-09 | 2025-02 | 2 | 7 | 7 | 28.57 | 28.57
TB 501 | 2024-09 | 2025-03 | 2 | 7 | 7 | 28.57 | 28.57
TB 501 | 2024-10 | 2025-01 | 5 | 25 | 25 | 20 | 20
TB 501 | 2024-10 | 2025-02 | 12 | 25 | 25 | 48 | 48
TB 501 | 2024-10 | 2025-03 | 5 | 25 | 25 | 20 | 20
TB 501 | 2024-10 | 2025-04 | 2 | 25 | 25 | 8 | 8
TB 501 | 2024-10 | 2025-05 | 1 | 25 | 25 | 4 | 4
TB 501 | 2024-11 | 2024-12 | 1 | 26 | 26 | 3.85 | 3.85
TB 501 | 2024-11 | 2025-01 | 9 | 26 | 26 | 34.62 | 34.62
TB 501 | 2024-11 | 2025-02 | 11 | 26 | 26 | 42.31 | 42.31
TB 501 | 2024-11 | 2025-03 | 3 | 26 | 26 | 11.54 | 11.54
TB 501 | 2024-11 | 2025-05 | 2 | 26 | 26 | 7.69 | 7.69
TB 501 | 2024-12 | 2024-12 | 1 | 27 | 27 | 3.7 | 3.7
TB 501 | 2024-12 | 2025-01 | 3 | 27 | 27 | 11.11 | 11.11
TB 501 | 2024-12 | 2025-02 | 11 | 27 | 27 | 40.74 | 40.74
TB 501 | 2024-12 | 2025-03 | 9 | 27 | 27 | 33.33 | 33.33
TB 501 | 2024-12 | 2025-04 | 3 | 27 | 27 | 11.11 | 11.11
TB 501 | 2025-01 | 2025-02 | 2 | 21 | 21 | 9.52 | 9.52
TB 501 | 2025-01 | 2025-03 | 12 | 21 | 21 | 57.14 | 57.14
TB 501 | 2025-01 | 2025-04 | 3 | 21 | 21 | 14.29 | 14.29
TB 501 | 2025-01 | 2025-05 | 1 | 21 | 21 | 4.76 | 4.76
TB 501 | 2025-01 | 2025-06 | 1 | 21 | 21 | 4.76 | 4.76
TB 501 | 2025-01 | 2025-07 | 2 | 21 | 21 | 9.52 | 9.52
TB 501 | 2025-02 | 2025-03 | 7 | 21 | 21 | 33.33 | 33.33
TB 501 | 2025-02 | 2025-04 | 6 | 21 | 21 | 28.57 | 28.57
TB 501 | 2025-02 | 2025-05 | 6 | 21 | 21 | 28.57 | 28.57
TB 501 | 2025-02 | 2025-08 | 1 | 21 | 21 | 4.76 | 4.76
TB 501 | 2025-02 | 2025-11 | 1 | 21 | 21 | 4.76 | 4.76
TB 501 | 2025-03 | 2025-04 | 6 | 9 | 9 | 66.67 | 66.67
TB 501 | 2025-03 | 2025-05 | 1 | 9 | 9 | 11.11 | 11.11
TB 501 | 2025-03 | 2025-06 | 1 | 9 | 9 | 11.11 | 11.11
TB 501 | 2025-03 | 2025-07 | 1 | 9 | 9 | 11.11 | 11.11
TB 501 | 2025-04 | 2025-05 | 6 | 11 | 11 | 54.55 | 54.55
TB 501 | 2025-04 | 2025-06 | 3 | 11 | 11 | 27.27 | 27.27
TB 501 | 2025-04 | 2025-07 | 2 | 11 | 11 | 18.18 | 18.18
TB 501 | 2025-05 | 2025-06 | 10 | 18 | 18 | 55.56 | 55.56
TB 501 | 2025-05 | 2025-07 | 6 | 18 | 18 | 33.33 | 33.33
TB 501 | 2025-05 | 2025-08 | 1 | 18 | 18 | 5.56 | 5.56
TB 501 | 2025-05 | 2025-10 | 1 | 18 | 18 | 5.56 | 5.56
TB 501 | 2025-06 | 2025-06 | 3 | 6 | 6 | 50 | 50
TB 501 | 2025-06 | 2025-07 | 2 | 6 | 6 | 33.33 | 33.33
TB 501 | 2025-06 | 2025-08 | 1 | 6 | 6 | 16.67 | 16.67
TB 501 | 2025-07 | 2025-08 | 1 | 1 | 1 | 100 | 100
TB 501 | 2025-08 | 2025-11 | 3 | 3 | 3 | 100 | 100
TB 501 | 2025-09 | 2025-10 | 3 | 8 | 8 | 37.5 | 37.5
TB 501 | 2025-09 | 2025-11 | 3 | 8 | 8 | 37.5 | 37.5
TB 501 | 2025-09 | 2025-12 | 1 | 8 | 8 | 12.5 | 12.5
TB 501 | 2025-09 | 2026-01 | 1 | 8 | 8 | 12.5 | 12.5
TB 501 | 2025-10 | 2025-10 | 1 | 6 | 6 | 16.67 | 16.67
TB 501 | 2025-10 | 2025-11 | 5 | 6 | 6 | 83.33 | 83.33
TB 501 | 2025-11 | 2025-11 | 5 | 7 | 7 | 71.43 | 71.43
TB 501 | 2025-11 | 2025-12 | 2 | 7 | 7 | 28.57 | 28.57
TB 501 | 2025-12 | 2025-12 | 5 | 10 | 9 | 50 | 55.56
TB 501 | 2025-12 | 2026-01 | 4 | 10 | 9 | 40 | 44.44
TB 501 | 2026-01 | 2026-01 | 3 | 9 | 9 | 33.33 | 33.33
TB 501 | 2026-01 | 2026-02 | 5 | 9 | 9 | 55.56 | 55.56
TB 501 | 2026-01 | 2026-03 | 1 | 9 | 9 | 11.11 | 11.11
TB 501 | 2026-02 | 2026-02 | 1 | 4 | 3 | 25 | 33.33
TB 501 | 2026-02 | 2026-03 | 2 | 4 | 3 | 50 | 66.67
TB 501 | 2026-03 | 2026-03 | 4 | 4 | 4 | 100 | 100
TB 501 | 2026-04 | 2026-04 | 2 | 5 | 5 | 40 | 40
TB 501 | 2026-04 | 2026-05 | 3 | 5 | 5 | 60 | 60
TB 507 | 2025-01 | 2025-06 | 1 | 2 | 2 | 50 | 50
TB 507 | 2025-01 | 2025-08 | 1 | 2 | 2 | 50 | 50
TB 507 | 2025-02 | 2025-06 | 2 | 20 | 20 | 10 | 10
TB 507 | 2025-02 | 2025-07 | 9 | 20 | 20 | 45 | 45
TB 507 | 2025-02 | 2025-08 | 5 | 20 | 20 | 25 | 25
TB 507 | 2025-02 | 2025-09 | 1 | 20 | 20 | 5 | 5
TB 507 | 2025-02 | 2025-11 | 1 | 20 | 20 | 5 | 5
TB 507 | 2025-02 | 2026-03 | 1 | 20 | 20 | 5 | 5
TB 507 | 2025-02 | 2026-05 | 1 | 20 | 20 | 5 | 5
TB 507 | 2025-03 | 2025-08 | 2 | 16 | 8 | 12.5 | 25
TB 507 | 2025-03 | 2025-09 | 3 | 16 | 8 | 18.75 | 37.5
TB 507 | 2025-03 | 2026-03 | 1 | 16 | 8 | 6.25 | 12.5
TB 507 | 2025-03 | 2026-06 | 2 | 16 | 8 | 12.5 | 25
TB 507 | 2025-04 | 2025-09 | 2 | 13 | 5 | 15.38 | 40
TB 507 | 2025-04 | 2025-12 | 2 | 13 | 5 | 15.38 | 40
TB 507 | 2025-04 | 2026-02 | 1 | 13 | 5 | 7.69 | 20
TB 507 | 2025-05 | 2025-09 | 2 | 9 | 8 | 22.22 | 25
TB 507 | 2025-05 | 2025-10 | 1 | 9 | 8 | 11.11 | 12.5
TB 507 | 2025-05 | 2025-12 | 1 | 9 | 8 | 11.11 | 12.5
TB 507 | 2025-05 | 2026-04 | 1 | 9 | 8 | 11.11 | 12.5
TB 507 | 2025-05 | 2026-06 | 2 | 9 | 8 | 22.22 | 25
TB 507 | 2025-05 | 2026-08 | 1 | 9 | 8 | 11.11 | 12.5
TB 507 | 2025-06 | 2025-08 | 4 | 25 | 24 | 16 | 16.67
TB 507 | 2025-06 | 2025-09 | 3 | 25 | 24 | 12 | 12.5
TB 507 | 2025-06 | 2025-10 | 9 | 25 | 24 | 36 | 37.5
TB 507 | 2025-06 | 2025-12 | 4 | 25 | 24 | 16 | 16.67
TB 507 | 2025-06 | 2026-01 | 2 | 25 | 24 | 8 | 8.33
TB 507 | 2025-06 | 2026-07 | 2 | 25 | 24 | 8 | 8.33
TB 507 | 2025-07 | 2025-08 | 3 | 50 | 46 | 6 | 6.52
TB 507 | 2025-07 | 2025-09 | 22 | 50 | 46 | 44 | 47.83
TB 507 | 2025-07 | 2025-10 | 9 | 50 | 46 | 18 | 19.57
TB 507 | 2025-07 | 2025-11 | 9 | 50 | 46 | 18 | 19.57
TB 507 | 2025-07 | 2025-12 | 2 | 50 | 46 | 4 | 4.35
TB 507 | 2025-07 | 2026-08 | 1 | 50 | 46 | 2 | 2.17
TB 507 | 2025-08 | 2025-08 | 1 | 52 | 45 | 1.92 | 2.22
TB 507 | 2025-08 | 2025-09 | 6 | 52 | 45 | 11.54 | 13.33
TB 507 | 2025-08 | 2025-10 | 18 | 52 | 45 | 34.62 | 40
TB 507 | 2025-08 | 2025-11 | 12 | 52 | 45 | 23.08 | 26.67
TB 507 | 2025-08 | 2025-12 | 2 | 52 | 45 | 3.85 | 4.44
TB 507 | 2025-08 | 2026-01 | 4 | 52 | 45 | 7.69 | 8.89
TB 507 | 2025-08 | 2026-05 | 1 | 52 | 45 | 1.92 | 2.22
TB 507 | 2025-08 | 2026-07 | 1 | 52 | 45 | 1.92 | 2.22
TB 507 | 2025-09 | 2025-10 | 5 | 20 | 13 | 25 | 38.46
TB 507 | 2025-09 | 2025-11 | 3 | 20 | 13 | 15 | 23.08
TB 507 | 2025-09 | 2025-12 | 3 | 20 | 13 | 15 | 23.08
TB 507 | 2025-09 | 2026-01 | 1 | 20 | 13 | 5 | 7.69
TB 507 | 2025-09 | 2026-08 | 1 | 20 | 13 | 5 | 7.69
TB 507 | 2025-10 | 2025-11 | 5 | 8 | 7 | 62.5 | 71.43
TB 507 | 2025-10 | 2025-12 | 1 | 8 | 7 | 12.5 | 14.29
TB 507 | 2025-10 | 2026-05 | 1 | 8 | 7 | 12.5 | 14.29
TB 507 | 2025-11 | 2025-11 | 2 | 19 | 18 | 10.53 | 11.11
TB 507 | 2025-11 | 2025-12 | 9 | 19 | 18 | 47.37 | 50
TB 507 | 2025-11 | 2026-01 | 3 | 19 | 18 | 15.79 | 16.67
TB 507 | 2025-11 | 2026-02 | 2 | 19 | 18 | 10.53 | 11.11
TB 507 | 2025-11 | 2026-05 | 1 | 19 | 18 | 5.26 | 5.56
TB 507 | 2025-11 | 2026-07 | 1 | 19 | 18 | 5.26 | 5.56
TB 507 | 2025-12 | 2026-01 | 1 | 13 | 10 | 7.69 | 10
TB 507 | 2025-12 | 2026-02 | 4 | 13 | 10 | 30.77 | 40
TB 507 | 2025-12 | 2026-05 | 3 | 13 | 10 | 23.08 | 30
TB 507 | 2025-12 | 2026-07 | 1 | 13 | 10 | 7.69 | 10
TB 507 | 2025-12 | 2026-08 | 1 | 13 | 10 | 7.69 | 10
TB 507 | 2026-01 | 2026-03 | 2 | 15 | 10 | 13.33 | 20
TB 507 | 2026-01 | 2026-04 | 4 | 15 | 10 | 26.67 | 40
TB 507 | 2026-01 | 2026-05 | 4 | 15 | 10 | 26.67 | 40
TB 507 | 2026-02 | 2026-03 | 1 | 12 | 8 | 8.33 | 12.5
TB 507 | 2026-02 | 2026-04 | 3 | 12 | 8 | 25 | 37.5
TB 507 | 2026-02 | 2026-05 | 1 | 12 | 8 | 8.33 | 12.5
TB 507 | 2026-02 | 2026-06 | 3 | 12 | 8 | 25 | 37.5
TB 507 | 2026-03 | 2026-04 | 3 | 16 | 11 | 18.75 | 27.27
TB 507 | 2026-03 | 2026-05 | 1 | 16 | 11 | 6.25 | 9.09
TB 507 | 2026-03 | 2026-06 | 1 | 16 | 11 | 6.25 | 9.09
TB 507 | 2026-03 | 2026-07 | 3 | 16 | 11 | 18.75 | 27.27
TB 507 | 2026-03 | 2026-08 | 3 | 16 | 11 | 18.75 | 27.27
TB 507 | 2026-04 | 2026-04 | 2 | 20 | 16 | 10 | 12.5
TB 507 | 2026-04 | 2026-05 | 5 | 20 | 16 | 25 | 31.25
TB 507 | 2026-04 | 2026-06 | 1 | 20 | 16 | 5 | 6.25
TB 507 | 2026-04 | 2026-07 | 4 | 20 | 16 | 20 | 25
TB 507 | 2026-04 | 2026-08 | 4 | 20 | 16 | 20 | 25
TB 507 | 2026-05 | 2026-05 | 7 | 26 | 14 | 26.92 | 50
TB 507 | 2026-05 | 2026-06 | 2 | 26 | 14 | 7.69 | 14.29
TB 507 | 2026-05 | 2026-07 | 5 | 26 | 14 | 19.23 | 35.71
TB 507 | 2026-06 | 2026-06 | 3 | 20 | 9 | 15 | 33.33
TB 507 | 2026-06 | 2026-07 | 3 | 20 | 9 | 15 | 33.33
TB 507 | 2026-06 | 2026-08 | 3 | 20 | 9 | 15 | 33.33
TB 507 | 2026-07 | 2026-07 | 2 | 16 | 5 | 12.5 | 40
TB 507 | 2026-07 | 2026-08 | 3 | 16 | 5 | 18.75 | 60
TB 605 | 2025-08 | 2025-11 | 1 | 1 | 1 | 100 | 100
TB 605 | 2025-09 | 2025-12 | 2 | 3 | 3 | 66.67 | 66.67
TB 605 | 2025-09 | 2026-05 | 1 | 3 | 3 | 33.33 | 33.33
TB 605 | 2025-10 | 2025-12 | 1 | 15 | 13 | 6.67 | 7.69
TB 605 | 2025-10 | 2026-01 | 1 | 15 | 13 | 6.67 | 7.69
TB 605 | 2025-10 | 2026-02 | 5 | 15 | 13 | 33.33 | 38.46
TB 605 | 2025-10 | 2026-03 | 1 | 15 | 13 | 6.67 | 7.69
TB 605 | 2025-10 | 2026-04 | 1 | 15 | 13 | 6.67 | 7.69
TB 605 | 2025-10 | 2026-05 | 3 | 15 | 13 | 20 | 23.08
TB 605 | 2025-10 | 2026-06 | 1 | 15 | 13 | 6.67 | 7.69
TB 605 | 2025-11 | 2025-12 | 2 | 42 | 37 | 4.76 | 5.41
TB 605 | 2025-11 | 2026-01 | 2 | 42 | 37 | 4.76 | 5.41
TB 605 | 2025-11 | 2026-02 | 25 | 42 | 37 | 59.52 | 67.57
TB 605 | 2025-11 | 2026-03 | 2 | 42 | 37 | 4.76 | 5.41
TB 605 | 2025-11 | 2026-04 | 2 | 42 | 37 | 4.76 | 5.41
TB 605 | 2025-11 | 2026-05 | 2 | 42 | 37 | 4.76 | 5.41
TB 605 | 2025-11 | 2026-06 | 1 | 42 | 37 | 2.38 | 2.7
TB 605 | 2025-11 | 2026-07 | 1 | 42 | 37 | 2.38 | 2.7
TB 605 | 2025-12 | 2026-01 | 1 | 57 | 50 | 1.75 | 2
TB 605 | 2025-12 | 2026-02 | 9 | 57 | 50 | 15.79 | 18
TB 605 | 2025-12 | 2026-03 | 20 | 57 | 50 | 35.09 | 40
TB 605 | 2025-12 | 2026-04 | 9 | 57 | 50 | 15.79 | 18
TB 605 | 2025-12 | 2026-05 | 7 | 57 | 50 | 12.28 | 14
TB 605 | 2025-12 | 2026-06 | 4 | 57 | 50 | 7.02 | 8
TB 605 | 2026-01 | 2026-02 | 9 | 42 | 39 | 21.43 | 23.08
TB 605 | 2026-01 | 2026-03 | 10 | 42 | 39 | 23.81 | 25.64
TB 605 | 2026-01 | 2026-04 | 16 | 42 | 39 | 38.1 | 41.03
TB 605 | 2026-01 | 2026-05 | 2 | 42 | 39 | 4.76 | 5.13
TB 605 | 2026-01 | 2026-06 | 2 | 42 | 39 | 4.76 | 5.13
TB 605 | 2026-02 | 2026-03 | 13 | 42 | 36 | 30.95 | 36.11
TB 605 | 2026-02 | 2026-04 | 8 | 42 | 36 | 19.05 | 22.22
TB 605 | 2026-02 | 2026-05 | 9 | 42 | 36 | 21.43 | 25
TB 605 | 2026-02 | 2026-06 | 5 | 42 | 36 | 11.9 | 13.89
TB 605 | 2026-02 | 2026-07 | 1 | 42 | 36 | 2.38 | 2.78
TB 605 | 2026-03 | 2026-03 | 4 | 28 | 21 | 14.29 | 19.05
TB 605 | 2026-03 | 2026-04 | 10 | 28 | 21 | 35.71 | 47.62
TB 605 | 2026-03 | 2026-05 | 4 | 28 | 21 | 14.29 | 19.05
TB 605 | 2026-03 | 2026-06 | 2 | 28 | 21 | 7.14 | 9.52
TB 605 | 2026-03 | 2026-07 | 1 | 28 | 21 | 3.57 | 4.76
TB 605 | 2026-04 | 2026-04 | 3 | 26 | 15 | 11.54 | 20
TB 605 | 2026-04 | 2026-05 | 6 | 26 | 15 | 23.08 | 40
TB 605 | 2026-04 | 2026-06 | 4 | 26 | 15 | 15.38 | 26.67
TB 605 | 2026-04 | 2026-07 | 2 | 26 | 15 | 7.69 | 13.33
TB 605 | 2026-05 | 2026-05 | 7 | 55 | 21 | 12.73 | 33.33
TB 605 | 2026-05 | 2026-06 | 13 | 55 | 21 | 23.64 | 61.9
TB 605 | 2026-05 | 2026-08 | 1 | 55 | 21 | 1.82 | 4.76
TB 605 | 2026-06 | 2026-06 | 9 | 41 | 19 | 21.95 | 47.37
TB 605 | 2026-06 | 2026-07 | 8 | 41 | 19 | 19.51 | 42.11
TB 605 | 2026-06 | 2026-08 | 2 | 41 | 19 | 4.88 | 10.53
TB 605 | 2026-07 | 2026-07 | 4 | 7 | 4 | 57.14 | 100
TB 608 | 2025-10 | 2026-04 | 1 | 2 | 2 | 50 | 50
TB 608 | 2025-10 | 2026-07 | 1 | 2 | 2 | 50 | 50
TB 608 | 2025-11 | 2025-12 | 2 | 20 | 13 | 10 | 15.38
TB 608 | 2025-11 | 2026-01 | 1 | 20 | 13 | 5 | 7.69
TB 608 | 2025-11 | 2026-03 | 3 | 20 | 13 | 15 | 23.08
TB 608 | 2025-11 | 2026-04 | 2 | 20 | 13 | 10 | 15.38
TB 608 | 2025-11 | 2026-05 | 3 | 20 | 13 | 15 | 23.08
TB 608 | 2025-11 | 2026-07 | 1 | 20 | 13 | 5 | 7.69
TB 608 | 2025-11 | 2026-08 | 1 | 20 | 13 | 5 | 7.69
TB 608 | 2025-12 | 2026-01 | 2 | 34 | 17 | 5.88 | 11.76
TB 608 | 2025-12 | 2026-02 | 3 | 34 | 17 | 8.82 | 17.65
TB 608 | 2025-12 | 2026-03 | 3 | 34 | 17 | 8.82 | 17.65
TB 608 | 2025-12 | 2026-05 | 4 | 34 | 17 | 11.76 | 23.53
TB 608 | 2025-12 | 2026-06 | 4 | 34 | 17 | 11.76 | 23.53
TB 608 | 2025-12 | 2026-08 | 1 | 34 | 17 | 2.94 | 5.88
TB 608 | 2026-01 | 2026-02 | 1 | 30 | 11 | 3.33 | 9.09
TB 608 | 2026-01 | 2026-04 | 4 | 30 | 11 | 13.33 | 36.36
TB 608 | 2026-01 | 2026-05 | 1 | 30 | 11 | 3.33 | 9.09
TB 608 | 2026-01 | 2026-06 | 4 | 30 | 11 | 13.33 | 36.36
TB 608 | 2026-01 | 2026-07 | 1 | 30 | 11 | 3.33 | 9.09
TB 608 | 2026-02 | 2026-03 | 1 | 30 | 12 | 3.33 | 8.33
TB 608 | 2026-02 | 2026-04 | 3 | 30 | 12 | 10 | 25
TB 608 | 2026-02 | 2026-05 | 2 | 30 | 12 | 6.67 | 16.67
TB 608 | 2026-02 | 2026-06 | 2 | 30 | 12 | 6.67 | 16.67
TB 608 | 2026-02 | 2026-07 | 3 | 30 | 12 | 10 | 25
TB 608 | 2026-02 | 2026-08 | 1 | 30 | 12 | 3.33 | 8.33
TB 608 | 2026-03 | 2026-05 | 1 | 16 | 3 | 6.25 | 33.33
TB 608 | 2026-03 | 2026-07 | 2 | 16 | 3 | 12.5 | 66.67
TB 608 | 2026-04 | 2026-06 | 2 | 6 | 2 | 33.33 | 100
TB 608 | 2026-05 | 2026-06 | 1 | 9 | 2 | 11.11 | 50
TB 608 | 2026-05 | 2026-07 | 1 | 9 | 2 | 11.11 | 50
TB 608 | 2026-06 | 2026-07 | 1 | 5 | 1 | 20 | 100

## Mechanism Matrix - Overall
Mechanism Matrix - Overall
Foundation Month | Erection Start Month | Foundations In Pair | Foundations Total (Month) | Matched Non-Negative (Month) | % of All Foundations In Month | % of Matched Non-Negative In Month
2024-01 | 2024-12 | 2 | 2 | 2 | 100 | 100
2024-03 | 2025-12 | 1 | 1 | 1 | 100 | 100
2024-04 | 2025-09 | 1 | 2 | 2 | 50 | 50
2024-04 | 2026-01 | 1 | 2 | 2 | 50 | 50
2024-05 | 2024-08 | 1 | 12 | 12 | 8.33 | 8.33
2024-05 | 2024-09 | 2 | 12 | 12 | 16.67 | 16.67
2024-05 | 2024-11 | 2 | 12 | 12 | 16.67 | 16.67
2024-05 | 2024-12 | 2 | 12 | 12 | 16.67 | 16.67
2024-05 | 2025-01 | 2 | 12 | 12 | 16.67 | 16.67
2024-05 | 2025-02 | 1 | 12 | 12 | 8.33 | 8.33
2024-05 | 2025-09 | 1 | 12 | 12 | 8.33 | 8.33
2024-05 | 2026-01 | 1 | 12 | 12 | 8.33 | 8.33
2024-06 | 2024-07 | 1 | 56 | 56 | 1.79 | 1.79
2024-06 | 2024-08 | 3 | 56 | 56 | 5.36 | 5.36
2024-06 | 2024-09 | 2 | 56 | 56 | 3.57 | 3.57
2024-06 | 2024-10 | 10 | 56 | 56 | 17.86 | 17.86
2024-06 | 2024-11 | 6 | 56 | 56 | 10.71 | 10.71
2024-06 | 2024-12 | 6 | 56 | 56 | 10.71 | 10.71
2024-06 | 2025-01 | 7 | 56 | 56 | 12.5 | 12.5
2024-06 | 2025-02 | 2 | 56 | 56 | 3.57 | 3.57
2024-06 | 2025-03 | 8 | 56 | 56 | 14.29 | 14.29
2024-06 | 2025-04 | 3 | 56 | 56 | 5.36 | 5.36
2024-06 | 2025-05 | 2 | 56 | 56 | 3.57 | 3.57
2024-06 | 2025-08 | 1 | 56 | 56 | 1.79 | 1.79
2024-06 | 2025-09 | 1 | 56 | 56 | 1.79 | 1.79
2024-06 | 2025-10 | 3 | 56 | 56 | 5.36 | 5.36
2024-06 | 2025-11 | 1 | 56 | 56 | 1.79 | 1.79
2024-07 | 2024-07 | 2 | 75 | 73 | 2.67 | 2.74
2024-07 | 2024-08 | 4 | 75 | 73 | 5.33 | 5.48
2024-07 | 2024-09 | 4 | 75 | 73 | 5.33 | 5.48
2024-07 | 2024-10 | 6 | 75 | 73 | 8 | 8.22
2024-07 | 2024-11 | 10 | 75 | 73 | 13.33 | 13.7
2024-07 | 2024-12 | 12 | 75 | 73 | 16 | 16.44
2024-07 | 2025-01 | 8 | 75 | 73 | 10.67 | 10.96
2024-07 | 2025-02 | 5 | 75 | 73 | 6.67 | 6.85
2024-07 | 2025-03 | 3 | 75 | 73 | 4 | 4.11
2024-07 | 2025-04 | 3 | 75 | 73 | 4 | 4.11
2024-07 | 2025-05 | 3 | 75 | 73 | 4 | 4.11
2024-07 | 2025-07 | 1 | 75 | 73 | 1.33 | 1.37
2024-07 | 2025-08 | 3 | 75 | 73 | 4 | 4.11
2024-07 | 2025-09 | 4 | 75 | 73 | 5.33 | 5.48
2024-07 | 2025-10 | 1 | 75 | 73 | 1.33 | 1.37
2024-07 | 2025-11 | 3 | 75 | 73 | 4 | 4.11
2024-07 | 2025-12 | 1 | 75 | 73 | 1.33 | 1.37
2024-08 | 2024-09 | 7 | 77 | 76 | 9.09 | 9.21
2024-08 | 2024-10 | 9 | 77 | 76 | 11.69 | 11.84
2024-08 | 2024-11 | 14 | 77 | 76 | 18.18 | 18.42
2024-08 | 2024-12 | 9 | 77 | 76 | 11.69 | 11.84
2024-08 | 2025-01 | 7 | 77 | 76 | 9.09 | 9.21
2024-08 | 2025-02 | 6 | 77 | 76 | 7.79 | 7.89
2024-08 | 2025-04 | 5 | 77 | 76 | 6.49 | 6.58
2024-08 | 2025-05 | 4 | 77 | 76 | 5.19 | 5.26
2024-08 | 2025-07 | 3 | 77 | 76 | 3.9 | 3.95
2024-08 | 2025-08 | 4 | 77 | 76 | 5.19 | 5.26
2024-08 | 2025-09 | 4 | 77 | 76 | 5.19 | 5.26
2024-08 | 2025-10 | 3 | 77 | 76 | 3.9 | 3.95
2024-08 | 2025-12 | 1 | 77 | 76 | 1.3 | 1.32
2024-09 | 2024-10 | 4 | 110 | 108 | 3.64 | 3.7
2024-09 | 2024-11 | 10 | 110 | 108 | 9.09 | 9.26
2024-09 | 2024-12 | 15 | 110 | 108 | 13.64 | 13.89
2024-09 | 2025-01 | 18 | 110 | 108 | 16.36 | 16.67
2024-09 | 2025-02 | 3 | 110 | 108 | 2.73 | 2.78
2024-09 | 2025-03 | 7 | 110 | 108 | 6.36 | 6.48
2024-09 | 2025-04 | 9 | 110 | 108 | 8.18 | 8.33
2024-09 | 2025-05 | 8 | 110 | 108 | 7.27 | 7.41
2024-09 | 2025-06 | 5 | 110 | 108 | 4.55 | 4.63
2024-09 | 2025-07 | 1 | 110 | 108 | 0.91 | 0.93
2024-09 | 2025-08 | 13 | 110 | 108 | 11.82 | 12.04
2024-09 | 2025-09 | 8 | 110 | 108 | 7.27 | 7.41
2024-09 | 2025-10 | 1 | 110 | 108 | 0.91 | 0.93
2024-09 | 2025-11 | 1 | 110 | 108 | 0.91 | 0.93
2024-09 | 2025-12 | 3 | 110 | 108 | 2.73 | 2.78
2024-09 | 2026-01 | 2 | 110 | 108 | 1.82 | 1.85
2024-10 | 2024-11 | 3 | 155 | 148 | 1.94 | 2.03
2024-10 | 2024-12 | 17 | 155 | 148 | 10.97 | 11.49
2024-10 | 2025-01 | 24 | 155 | 148 | 15.48 | 16.22
2024-10 | 2025-02 | 36 | 155 | 148 | 23.23 | 24.32
2024-10 | 2025-03 | 18 | 155 | 148 | 11.61 | 12.16
2024-10 | 2025-04 | 15 | 155 | 148 | 9.68 | 10.14
2024-10 | 2025-05 | 8 | 155 | 148 | 5.16 | 5.41
2024-10 | 2025-06 | 6 | 155 | 148 | 3.87 | 4.05
2024-10 | 2025-07 | 3 | 155 | 148 | 1.94 | 2.03
2024-10 | 2025-08 | 8 | 155 | 148 | 5.16 | 5.41
2024-10 | 2025-09 | 4 | 155 | 148 | 2.58 | 2.7
2024-10 | 2025-11 | 4 | 155 | 148 | 2.58 | 2.7
2024-10 | 2025-12 | 2 | 155 | 148 | 1.29 | 1.35
2024-11 | 2024-11 | 1 | 169 | 164 | 0.59 | 0.61
2024-11 | 2024-12 | 11 | 169 | 164 | 6.51 | 6.71
2024-11 | 2025-01 | 30 | 169 | 164 | 17.75 | 18.29
2024-11 | 2025-02 | 39 | 169 | 164 | 23.08 | 23.78
2024-11 | 2025-03 | 32 | 169 | 164 | 18.93 | 19.51
2024-11 | 2025-04 | 17 | 169 | 164 | 10.06 | 10.37
2024-11 | 2025-05 | 7 | 169 | 164 | 4.14 | 4.27
2024-11 | 2025-06 | 5 | 169 | 164 | 2.96 | 3.05
2024-11 | 2025-07 | 1 | 169 | 164 | 0.59 | 0.61
2024-11 | 2025-08 | 6 | 169 | 164 | 3.55 | 3.66
2024-11 | 2025-09 | 9 | 169 | 164 | 5.33 | 5.49
2024-11 | 2025-10 | 4 | 169 | 164 | 2.37 | 2.44
2024-11 | 2026-01 | 2 | 169 | 164 | 1.18 | 1.22
2024-12 | 2024-12 | 6 | 197 | 194 | 3.05 | 3.09
2024-12 | 2025-01 | 14 | 197 | 194 | 7.11 | 7.22
2024-12 | 2025-02 | 30 | 197 | 194 | 15.23 | 15.46
2024-12 | 2025-03 | 38 | 197 | 194 | 19.29 | 19.59
2024-12 | 2025-04 | 24 | 197 | 194 | 12.18 | 12.37
2024-12 | 2025-05 | 15 | 197 | 194 | 7.61 | 7.73
2024-12 | 2025-06 | 13 | 197 | 194 | 6.6 | 6.7
2024-12 | 2025-07 | 1 | 197 | 194 | 0.51 | 0.52
2024-12 | 2025-08 | 9 | 197 | 194 | 4.57 | 4.64
2024-12 | 2025-09 | 13 | 197 | 194 | 6.6 | 6.7
2024-12 | 2025-10 | 9 | 197 | 194 | 4.57 | 4.64
2024-12 | 2025-11 | 6 | 197 | 194 | 3.05 | 3.09
2024-12 | 2025-12 | 5 | 197 | 194 | 2.54 | 2.58
2024-12 | 2026-01 | 4 | 197 | 194 | 2.03 | 2.06
2024-12 | 2026-02 | 4 | 197 | 194 | 2.03 | 2.06
2024-12 | 2026-05 | 1 | 197 | 194 | 0.51 | 0.52
2024-12 | 2026-06 | 2 | 197 | 194 | 1.02 | 1.03
2025-01 | 2025-01 | 3 | 187 | 185 | 1.6 | 1.62
2025-01 | 2025-02 | 7 | 187 | 185 | 3.74 | 3.78
2025-01 | 2025-03 | 25 | 187 | 185 | 13.37 | 13.51
2025-01 | 2025-04 | 23 | 187 | 185 | 12.3 | 12.43
2025-01 | 2025-05 | 21 | 187 | 185 | 11.23 | 11.35
2025-01 | 2025-06 | 11 | 187 | 185 | 5.88 | 5.95
2025-01 | 2025-07 | 16 | 187 | 185 | 8.56 | 8.65
2025-01 | 2025-08 | 15 | 187 | 185 | 8.02 | 8.11
2025-01 | 2025-09 | 15 | 187 | 185 | 8.02 | 8.11
2025-01 | 2025-10 | 13 | 187 | 185 | 6.95 | 7.03
2025-01 | 2025-11 | 6 | 187 | 185 | 3.21 | 3.24
2025-01 | 2025-12 | 15 | 187 | 185 | 8.02 | 8.11
2025-01 | 2026-01 | 3 | 187 | 185 | 1.6 | 1.62
2025-01 | 2026-02 | 2 | 187 | 185 | 1.07 | 1.08
2025-01 | 2026-03 | 2 | 187 | 185 | 1.07 | 1.08
2025-01 | 2026-04 | 5 | 187 | 185 | 2.67 | 2.7
2025-01 | 2026-05 | 1 | 187 | 185 | 0.53 | 0.54
2025-01 | 2026-06 | 2 | 187 | 185 | 1.07 | 1.08
2025-02 | 2025-03 | 15 | 202 | 198 | 7.43 | 7.58
2025-02 | 2025-04 | 15 | 202 | 198 | 7.43 | 7.58
2025-02 | 2025-05 | 21 | 202 | 198 | 10.4 | 10.61
2025-02 | 2025-06 | 13 | 202 | 198 | 6.44 | 6.57
2025-02 | 2025-07 | 25 | 202 | 198 | 12.38 | 12.63
2025-02 | 2025-08 | 27 | 202 | 198 | 13.37 | 13.64
2025-02 | 2025-09 | 16 | 202 | 198 | 7.92 | 8.08
2025-02 | 2025-10 | 9 | 202 | 198 | 4.46 | 4.55
2025-02 | 2025-11 | 21 | 202 | 198 | 10.4 | 10.61
2025-02 | 2025-12 | 14 | 202 | 198 | 6.93 | 7.07
2025-02 | 2026-01 | 9 | 202 | 198 | 4.46 | 4.55
2025-02 | 2026-02 | 2 | 202 | 198 | 0.99 | 1.01
2025-02 | 2026-03 | 3 | 202 | 198 | 1.49 | 1.52
2025-02 | 2026-04 | 4 | 202 | 198 | 1.98 | 2.02
2025-02 | 2026-05 | 3 | 202 | 198 | 1.49 | 1.52
2025-02 | 2026-06 | 1 | 202 | 198 | 0.5 | 0.51
2025-03 | 2025-03 | 1 | 156 | 143 | 0.64 | 0.7
2025-03 | 2025-04 | 14 | 156 | 143 | 8.97 | 9.79
2025-03 | 2025-05 | 6 | 156 | 143 | 3.85 | 4.2
2025-03 | 2025-06 | 4 | 156 | 143 | 2.56 | 2.8
2025-03 | 2025-07 | 9 | 156 | 143 | 5.77 | 6.29
2025-03 | 2025-08 | 23 | 156 | 143 | 14.74 | 16.08
2025-03 | 2025-09 | 25 | 156 | 143 | 16.03 | 17.48
2025-03 | 2025-10 | 11 | 156 | 143 | 7.05 | 7.69
2025-03 | 2025-11 | 14 | 156 | 143 | 8.97 | 9.79
2025-03 | 2025-12 | 14 | 156 | 143 | 8.97 | 9.79
2025-03 | 2026-01 | 6 | 156 | 143 | 3.85 | 4.2
2025-03 | 2026-02 | 7 | 156 | 143 | 4.49 | 4.9
2025-03 | 2026-03 | 4 | 156 | 143 | 2.56 | 2.8
2025-03 | 2026-04 | 1 | 156 | 143 | 0.64 | 0.7
2025-03 | 2026-05 | 1 | 156 | 143 | 0.64 | 0.7
2025-03 | 2026-06 | 3 | 156 | 143 | 1.92 | 2.1
2025-04 | 2025-04 | 1 | 201 | 178 | 0.5 | 0.56
2025-04 | 2025-05 | 9 | 201 | 178 | 4.48 | 5.06
2025-04 | 2025-06 | 6 | 201 | 178 | 2.99 | 3.37
2025-04 | 2025-07 | 11 | 201 | 178 | 5.47 | 6.18
2025-04 | 2025-08 | 15 | 201 | 178 | 7.46 | 8.43
2025-04 | 2025-09 | 26 | 201 | 178 | 12.94 | 14.61
2025-04 | 2025-10 | 14 | 201 | 178 | 6.97 | 7.87
2025-04 | 2025-11 | 26 | 201 | 178 | 12.94 | 14.61
2025-04 | 2025-12 | 27 | 201 | 178 | 13.43 | 15.17
2025-04 | 2026-01 | 13 | 201 | 178 | 6.47 | 7.3
2025-04 | 2026-02 | 9 | 201 | 178 | 4.48 | 5.06
2025-04 | 2026-03 | 7 | 201 | 178 | 3.48 | 3.93
2025-04 | 2026-04 | 8 | 201 | 178 | 3.98 | 4.49
2025-04 | 2026-05 | 4 | 201 | 178 | 1.99 | 2.25
2025-04 | 2026-06 | 2 | 201 | 178 | 1 | 1.12
2025-05 | 2025-05 | 1 | 192 | 182 | 0.52 | 0.55
2025-05 | 2025-06 | 12 | 192 | 182 | 6.25 | 6.59
2025-05 | 2025-07 | 13 | 192 | 182 | 6.77 | 7.14
2025-05 | 2025-08 | 12 | 192 | 182 | 6.25 | 6.59
2025-05 | 2025-09 | 32 | 192 | 182 | 16.67 | 17.58
2025-05 | 2025-10 | 24 | 192 | 182 | 12.5 | 13.19
2025-05 | 2025-11 | 21 | 192 | 182 | 10.94 | 11.54
2025-05 | 2025-12 | 17 | 192 | 182 | 8.85 | 9.34
2025-05 | 2026-01 | 17 | 192 | 182 | 8.85 | 9.34
2025-05 | 2026-02 | 12 | 192 | 182 | 6.25 | 6.59
2025-05 | 2026-03 | 4 | 192 | 182 | 2.08 | 2.2
2025-05 | 2026-04 | 7 | 192 | 182 | 3.65 | 3.85
2025-05 | 2026-05 | 5 | 192 | 182 | 2.6 | 2.75
2025-05 | 2026-06 | 3 | 192 | 182 | 1.56 | 1.65
2025-05 | 2026-07 | 1 | 192 | 182 | 0.52 | 0.55
2025-05 | 2026-08 | 1 | 192 | 182 | 0.52 | 0.55
2025-06 | 2025-06 | 5 | 139 | 128 | 3.6 | 3.91
2025-06 | 2025-07 | 8 | 139 | 128 | 5.76 | 6.25
2025-06 | 2025-08 | 13 | 139 | 128 | 9.35 | 10.16
2025-06 | 2025-09 | 10 | 139 | 128 | 7.19 | 7.81
2025-06 | 2025-10 | 21 | 139 | 128 | 15.11 | 16.41
2025-06 | 2025-11 | 15 | 139 | 128 | 10.79 | 11.72
2025-06 | 2025-12 | 21 | 139 | 128 | 15.11 | 16.41
2025-06 | 2026-01 | 10 | 139 | 128 | 7.19 | 7.81
2025-06 | 2026-02 | 10 | 139 | 128 | 7.19 | 7.81
2025-06 | 2026-03 | 7 | 139 | 128 | 5.04 | 5.47
2025-06 | 2026-04 | 2 | 139 | 128 | 1.44 | 1.56
2025-06 | 2026-05 | 1 | 139 | 128 | 0.72 | 0.78
2025-06 | 2026-06 | 1 | 139 | 128 | 0.72 | 0.78
2025-06 | 2026-07 | 4 | 139 | 128 | 2.88 | 3.12
2025-07 | 2025-08 | 6 | 134 | 123 | 4.48 | 4.88
2025-07 | 2025-09 | 28 | 134 | 123 | 20.9 | 22.76
2025-07 | 2025-10 | 14 | 134 | 123 | 10.45 | 11.38
2025-07 | 2025-11 | 22 | 134 | 123 | 16.42 | 17.89
2025-07 | 2025-12 | 24 | 134 | 123 | 17.91 | 19.51
2025-07 | 2026-01 | 8 | 134 | 123 | 5.97 | 6.5
2025-07 | 2026-02 | 6 | 134 | 123 | 4.48 | 4.88
2025-07 | 2026-03 | 4 | 134 | 123 | 2.99 | 3.25
2025-07 | 2026-04 | 2 | 134 | 123 | 1.49 | 1.63
2025-07 | 2026-05 | 1 | 134 | 123 | 0.75 | 0.81
2025-07 | 2026-06 | 1 | 134 | 123 | 0.75 | 0.81
2025-07 | 2026-07 | 4 | 134 | 123 | 2.99 | 3.25
2025-07 | 2026-08 | 3 | 134 | 123 | 2.24 | 2.44
2025-08 | 2025-08 | 1 | 97 | 86 | 1.03 | 1.16
2025-08 | 2025-09 | 8 | 97 | 86 | 8.25 | 9.3
2025-08 | 2025-10 | 21 | 97 | 86 | 21.65 | 24.42
2025-08 | 2025-11 | 17 | 97 | 86 | 17.53 | 19.77
2025-08 | 2025-12 | 9 | 97 | 86 | 9.28 | 10.47
2025-08 | 2026-01 | 14 | 97 | 86 | 14.43 | 16.28
2025-08 | 2026-02 | 1 | 97 | 86 | 1.03 | 1.16
2025-08 | 2026-03 | 4 | 97 | 86 | 4.12 | 4.65
2025-08 | 2026-04 | 2 | 97 | 86 | 2.06 | 2.33
2025-08 | 2026-05 | 3 | 97 | 86 | 3.09 | 3.49
2025-08 | 2026-06 | 1 | 97 | 86 | 1.03 | 1.16
2025-08 | 2026-07 | 4 | 97 | 86 | 4.12 | 4.65
2025-08 | 2026-08 | 1 | 97 | 86 | 1.03 | 1.16
2025-09 | 2025-10 | 12 | 78 | 65 | 15.38 | 18.46
2025-09 | 2025-11 | 13 | 78 | 65 | 16.67 | 20
2025-09 | 2025-12 | 13 | 78 | 65 | 16.67 | 20
2025-09 | 2026-01 | 12 | 78 | 65 | 15.38 | 18.46
2025-09 | 2026-02 | 6 | 78 | 65 | 7.69 | 9.23
2025-09 | 2026-03 | 1 | 78 | 65 | 1.28 | 1.54
2025-09 | 2026-05 | 2 | 78 | 65 | 2.56 | 3.08
2025-09 | 2026-06 | 1 | 78 | 65 | 1.28 | 1.54
2025-09 | 2026-07 | 2 | 78 | 65 | 2.56 | 3.08
2025-09 | 2026-08 | 3 | 78 | 65 | 3.85 | 4.62
2025-10 | 2025-10 | 2 | 104 | 87 | 1.92 | 2.3
2025-10 | 2025-11 | 18 | 104 | 87 | 17.31 | 20.69
2025-10 | 2025-12 | 11 | 104 | 87 | 10.58 | 12.64
2025-10 | 2026-01 | 17 | 104 | 87 | 16.35 | 19.54
2025-10 | 2026-02 | 9 | 104 | 87 | 8.65 | 10.34
2025-10 | 2026-03 | 6 | 104 | 87 | 5.77 | 6.9
2025-10 | 2026-04 | 11 | 104 | 87 | 10.58 | 12.64
2025-10 | 2026-05 | 5 | 104 | 87 | 4.81 | 5.75
2025-10 | 2026-06 | 4 | 104 | 87 | 3.85 | 4.6
2025-10 | 2026-07 | 4 | 104 | 87 | 3.85 | 4.6
2025-11 | 2025-11 | 9 | 208 | 178 | 4.33 | 5.06
2025-11 | 2025-12 | 42 | 208 | 178 | 20.19 | 23.6
2025-11 | 2026-01 | 27 | 208 | 178 | 12.98 | 15.17
2025-11 | 2026-02 | 41 | 208 | 178 | 19.71 | 23.03
2025-11 | 2026-03 | 17 | 208 | 178 | 8.17 | 9.55
2025-11 | 2026-04 | 9 | 208 | 178 | 4.33 | 5.06
2025-11 | 2026-05 | 12 | 208 | 178 | 5.77 | 6.74
2025-11 | 2026-06 | 9 | 208 | 178 | 4.33 | 5.06
2025-11 | 2026-07 | 11 | 208 | 178 | 5.29 | 6.18
2025-11 | 2026-08 | 1 | 208 | 178 | 0.48 | 0.56
2025-12 | 2025-12 | 23 | 285 | 233 | 8.07 | 9.87
2025-12 | 2026-01 | 59 | 285 | 233 | 20.7 | 25.32
2025-12 | 2026-02 | 46 | 285 | 233 | 16.14 | 19.74
2025-12 | 2026-03 | 41 | 285 | 233 | 14.39 | 17.6
2025-12 | 2026-04 | 19 | 285 | 233 | 6.67 | 8.15
2025-12 | 2026-05 | 19 | 285 | 233 | 6.67 | 8.15
2025-12 | 2026-06 | 15 | 285 | 233 | 5.26 | 6.44
2025-12 | 2026-07 | 6 | 285 | 233 | 2.11 | 2.58
2025-12 | 2026-08 | 4 | 285 | 233 | 1.4 | 1.72
2025-12 | 2026-12 | 1 | 285 | 233 | 0.35 | 0.43
2026-01 | 2026-01 | 26 | 229 | 182 | 11.35 | 14.29
2026-01 | 2026-02 | 53 | 229 | 182 | 23.14 | 29.12
2026-01 | 2026-03 | 32 | 229 | 182 | 13.97 | 17.58
2026-01 | 2026-04 | 32 | 229 | 182 | 13.97 | 17.58
2026-01 | 2026-05 | 17 | 229 | 182 | 7.42 | 9.34
2026-01 | 2026-06 | 12 | 229 | 182 | 5.24 | 6.59
2026-01 | 2026-07 | 7 | 229 | 182 | 3.06 | 3.85
2026-01 | 2026-08 | 3 | 229 | 182 | 1.31 | 1.65
2026-02 | 2026-02 | 18 | 187 | 124 | 9.63 | 14.52
2026-02 | 2026-03 | 33 | 187 | 124 | 17.65 | 26.61
2026-02 | 2026-04 | 23 | 187 | 124 | 12.3 | 18.55
2026-02 | 2026-05 | 23 | 187 | 124 | 12.3 | 18.55
2026-02 | 2026-06 | 20 | 187 | 124 | 10.7 | 16.13
2026-02 | 2026-07 | 6 | 187 | 124 | 3.21 | 4.84
2026-02 | 2026-08 | 1 | 187 | 124 | 0.53 | 0.81
2026-03 | 2026-03 | 19 | 133 | 88 | 14.29 | 21.59
2026-03 | 2026-04 | 27 | 133 | 88 | 20.3 | 30.68
2026-03 | 2026-05 | 15 | 133 | 88 | 11.28 | 17.05
2026-03 | 2026-06 | 13 | 133 | 88 | 9.77 | 14.77
2026-03 | 2026-07 | 10 | 133 | 88 | 7.52 | 11.36
2026-03 | 2026-08 | 4 | 133 | 88 | 3.01 | 4.55
2026-04 | 2026-04 | 9 | 117 | 66 | 7.69 | 13.64
2026-04 | 2026-05 | 26 | 117 | 66 | 22.22 | 39.39
2026-04 | 2026-06 | 17 | 117 | 66 | 14.53 | 25.76
2026-04 | 2026-07 | 9 | 117 | 66 | 7.69 | 13.64
2026-04 | 2026-08 | 5 | 117 | 66 | 4.27 | 7.58
2026-05 | 2026-05 | 19 | 179 | 77 | 10.61 | 24.68
2026-05 | 2026-06 | 41 | 179 | 77 | 22.91 | 53.25
2026-05 | 2026-07 | 15 | 179 | 77 | 8.38 | 19.48
2026-05 | 2026-08 | 2 | 179 | 77 | 1.12 | 2.6
2026-06 | 2026-06 | 23 | 170 | 62 | 13.53 | 37.1
2026-06 | 2026-07 | 33 | 170 | 62 | 19.41 | 53.23
2026-06 | 2026-08 | 6 | 170 | 62 | 3.53 | 9.68
2026-07 | 2026-07 | 24 | 94 | 30 | 25.53 | 80
2026-07 | 2026-08 | 6 | 94 | 30 | 6.38 | 20

## Mechanism Evidence Audit
Mechanism Evidence Audit
Project | Series | Ownership | Project Rollup Key | Location | Foundation Date | Foundation Month | Foundation Month Num | Erection Start | Erection Start Month | Erection Start Month Num | Delay Days | Matched | Negative Excluded | Match Basis | Foundation Line | Erection Line | Foundation Source File | Foundation Source Sheet | Erection Source File | Erection Source Sheet
TA 413 | 4xx | Government | ta413 | 9/4 | 2024-06-06 | 2024-06 | 6 | 2025-03-05 | 2025-03 | 3 | 272 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 10/1 | 2024-06-07 | 2024-06 | 6 | 2025-10-12 | 2025-10 | 10 | 492 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 10/2 | 2024-06-09 | 2024-06 | 6 | 2025-11-01 | 2025-11 | 11 | 510 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/11 | 2024-06-11 | 2024-06 | 6 | 2025-10-18 | 2025-10 | 10 | 494 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/2 | 2024-06-17 | 2024-06 | 6 | 2025-03-14 | 2025-03 | 3 | 270 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/5 | 2024-06-17 | 2024-06 | 6 | 2025-08-15 | 2025-08 | 8 | 424 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/3 | 2024-06-18 | 2024-06 | 6 | 2025-03-19 | 2025-03 | 3 | 274 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/4 | 2024-06-21 | 2024-06 | 6 | 2025-03-23 | 2025-03 | 3 | 275 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/3 | 2024-06-23 | 2024-06 | 6 | 2025-03-01 | 2025-03 | 3 | 251 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/5 | 2024-06-24 | 2024-06 | 6 | 2025-03-26 | 2025-03 | 3 | 275 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/5 | 2024-06-26 | 2024-06 | 6 | 2025-01-04 | 2025-01 | 1 | 192 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/6 | 2024-06-27 | 2024-06 | 6 | 2025-03-31 | 2025-03 | 3 | 277 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/10 | 2024-06-28 | 2024-06 | 6 | 2025-10-31 | 2025-10 | 10 | 490 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/2 | 2024-06-29 | 2024-06 | 6 | 2025-03-10 | 2025-03 | 3 | 254 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/9 | 2024-07-03 | 2024-07 | 7 | 2025-11-22 | 2025-11 | 11 | 507 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/6 | 2024-07-03 | 2024-07 | 7 | 2025-01-10 | 2025-01 | 1 | 191 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/8 | 2024-07-06 | 2024-07 | 7 | 2025-09-27 | 2025-09 | 9 | 448 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/9 | 2024-07-06 | 2024-07 | 7 | 2025-08-23 | 2025-08 | 8 | 413 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/7 | 2024-07-09 | 2024-07 | 7 | 2025-01-16 | 2025-01 | 1 | 191 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/10 | 2024-07-10 | 2024-07 | 7 | 2025-11-16 | 2025-11 | 11 | 494 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/8 | 2024-07-10 | 2024-07 | 7 | 2025-09-15 | 2025-09 | 9 | 432 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/1 | 2024-07-10 | 2024-07 | 7 | 2025-02-24 | 2025-02 | 2 | 229 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/7 | 2024-07-11 | 2024-07 | 7 | 2025-11-10 | 2025-11 | 11 | 487 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/7 | 2024-07-15 | 2024-07 | 7 | 2025-09-10 | 2025-09 | 9 | 422 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/11 | 2024-07-18 | 2024-07 | 7 | 2025-12-07 | 2025-12 | 12 | 507 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/8 | 2024-07-19 | 2024-07 | 7 | 2025-01-20 | 2025-01 | 1 | 185 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/1 | 2024-07-20 | 2024-07 | 7 | 2024-12-07 | 2024-12 | 12 | 140 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/6 | 2024-07-22 | 2024-07 | 7 | 2025-09-04 | 2025-09 | 9 | 409 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29/4 | 2024-07-24 | 2024-07 | 7 | 2024-10-03 | 2024-10 | 10 | 71 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/2 | 2024-07-25 | 2024-07 | 7 | 2025-02-03 | 2025-02 | 2 | 193 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/9 | 2024-07-25 | 2024-07 | 7 | 2025-01-25 | 2025-01 | 1 | 184 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/10 | 2024-07-28 | 2024-07 | 7 | 2025-08-15 | 2025-08 | 8 | 383 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29/3 | 2024-07-29 | 2024-07 | 7 | 2024-09-28 | 2024-09 | 9 | 61 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/3 | 2024-07-31 | 2024-07 | 7 | 2025-08-12 | 2025-08 | 8 | 377 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/1 | 2024-08-01 | 2024-08 | 8 | 2024-10-09 | 2024-10 | 10 | 69 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29/5 | 2024-08-03 | 2024-08 | 8 | 2024-09-21 | 2024-09 | 9 | 49 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/1 | 2024-08-03 | 2024-08 | 8 | 2025-08-02 | 2025-08 | 8 | 364 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29A/2 | 2024-08-08 | 2024-08 | 8 | 2024-09-12 | 2024-09 | 9 | 35 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/3 | 2024-08-08 | 2024-08 | 8 | 2025-09-09 | 2025-09 | 9 | 397 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7/1 | 2024-08-10 | 2024-08 | 8 | 2024-12-15 | 2024-12 | 12 | 127 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/10 | 2024-08-13 | 2024-08 | 8 | 2025-01-30 | 2025-01 | 1 | 170 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29A/1 | 2024-08-14 | 2024-08 | 8 | 2024-10-14 | 2024-10 | 10 | 61 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 27/4 | 2024-08-16 | 2024-08 | 8 | 2025-10-27 | 2025-10 | 10 | 437 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7A/5 | 2024-08-17 | 2024-08 | 8 | 2024-12-17 | 2024-12 | 12 | 122 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/8 | 2024-08-18 | 2024-08 | 8 | 2025-09-10 | 2025-09 | 9 | 388 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29A/3 | 2024-08-20 | 2024-08 | 8 | 2025-12-27 | 2025-12 | 12 | 494 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32/3 | 2024-08-20 | 2024-08 | 8 | 2025-07-27 | 2025-07 | 7 | 341 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7A/4 | 2024-08-23 | 2024-08 | 8 | 2024-12-24 | 2024-12 | 12 | 123 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29A/4 | 2024-08-24 | 2024-08 | 8 | 2025-10-05 | 2025-10 | 10 | 407 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/4 | 2024-08-25 | 2024-08 | 8 | 2025-08-29 | 2025-08 | 8 | 369 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32/4 | 2024-08-26 | 2024-08 | 8 | 2025-08-07 | 2025-08 | 8 | 346 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29A/5 | 2024-08-27 | 2024-08 | 8 | 2025-09-26 | 2025-09 | 9 | 395 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/2 | 2024-08-27 | 2024-08 | 8 | 2025-08-04 | 2025-08 | 8 | 342 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 27/5 | 2024-08-28 | 2024-08 | 8 | 2025-10-23 | 2025-10 | 10 | 421 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/6 | 2024-08-30 | 2024-08 | 8 | 2025-01-29 | 2025-01 | 1 | 152 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/1 | 2024-08-30 | 2024-08 | 8 | 2025-07-16 | 2025-07 | 7 | 320 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29A/6 | 2024-08-31 | 2024-08 | 8 | 2024-10-03 | 2024-10 | 10 | 33 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4A/5 | 2024-09-01 | 2024-09 | 9 | 2025-08-25 | 2025-08 | 8 | 358 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7A/1 | 2024-09-01 | 2024-09 | 9 | 2025-01-17 | 2025-01 | 1 | 138 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/7 | 2024-09-04 | 2024-09 | 9 | 2025-08-23 | 2025-08 | 8 | 353 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/10 | 2024-09-04 | 2024-09 | 9 | 2025-08-22 | 2025-08 | 8 | 352 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/12 | 2024-09-05 | 2024-09 | 9 | 2025-08-01 | 2025-08 | 8 | 330 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4A/4 | 2024-09-06 | 2024-09 | 9 | 2025-08-18 | 2025-08 | 8 | 346 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7A/2 | 2024-09-06 | 2024-09 | 9 | 2025-01-08 | 2025-01 | 1 | 124 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/3 | 2024-09-07 | 2024-09 | 9 | 2025-08-08 | 2025-08 | 8 | 335 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/4 | 2024-09-09 | 2024-09 | 9 | 2025-09-05 | 2025-09 | 9 | 361 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4A/3 | 2024-09-09 | 2024-09 | 9 | 2025-08-29 | 2025-08 | 8 | 354 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29/1 | 2024-09-10 | 2024-09 | 9 | 2025-10-07 | 2025-10 | 10 | 392 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7A/3 | 2024-09-10 | 2024-09 | 9 | 2025-01-01 | 2025-01 | 1 | 113 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4A/6 | 2024-09-12 | 2024-09 | 9 | 2025-09-09 | 2025-09 | 9 | 362 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/7 | 2024-09-12 | 2024-09 | 9 | 2025-09-02 | 2025-09 | 9 | 355 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/3 | 2024-09-13 | 2024-09 | 9 | 2025-08-31 | 2025-08 | 8 | 352 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/12 | 2024-09-13 | 2024-09 | 9 | 2024-11-14 | 2024-11 | 11 | 62 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/11 | 2024-09-14 | 2024-09 | 9 | 2025-08-19 | 2025-08 | 8 | 339 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/1 | 2024-09-15 | 2024-09 | 9 | 2025-01-21 | 2025-01 | 1 | 128 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 36A/1 | 2024-09-15 | 2024-09 | 9 | 2024-12-13 | 2024-12 | 12 | 89 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/6 | 2024-09-15 | 2024-09 | 9 | 2025-08-08 | 2025-08 | 8 | 327 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4A/2 | 2024-09-16 | 2024-09 | 9 | 2025-09-07 | 2025-09 | 9 | 356 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/3 | 2024-09-18 | 2024-09 | 9 | 2024-12-05 | 2024-12 | 12 | 78 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 36A/2 | 2024-09-19 | 2024-09 | 9 | 2025-01-04 | 2025-01 | 1 | 107 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 27/2 | 2024-09-20 | 2024-09 | 9 | 2025-11-21 | 2025-11 | 11 | 427 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/11 | 2024-09-20 | 2024-09 | 9 | 2024-12-30 | 2024-12 | 12 | 101 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/4 | 2024-09-20 | 2024-09 | 9 | 2025-08-15 | 2025-08 | 8 | 329 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/4 | 2024-09-21 | 2024-09 | 9 | 2024-11-25 | 2024-11 | 11 | 65 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4A/1 | 2024-09-21 | 2024-09 | 9 | 2025-09-18 | 2025-09 | 9 | 362 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37/1 | 2024-09-23 | 2024-09 | 9 |  |  |  |  | No | No |  |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation
TA 413 | 4xx | Government | ta413 | 5/2 | 2024-09-23 | 2024-09 | 9 | 2025-09-26 | 2025-09 | 9 | 368 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/6 | 2024-09-23 | 2024-09 | 9 | 2025-08-14 | 2025-08 | 8 | 325 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/5 | 2024-09-25 | 2024-09 | 9 | 2024-12-17 | 2024-12 | 12 | 83 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/1 | 2024-09-26 | 2024-09 | 9 | 2025-01-07 | 2025-01 | 1 | 103 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37/2 | 2024-09-27 | 2024-09 | 9 | 2026-01-12 | 2026-01 | 1 | 472 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4/1 | 2024-09-27 | 2024-09 | 9 | 2025-09-06 | 2025-09 | 9 | 344 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 27/1 | 2024-09-28 | 2024-09 | 9 | 2025-12-05 | 2025-12 | 12 | 433 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/6 | 2024-09-28 | 2024-09 | 9 | 2024-12-30 | 2024-12 | 12 | 93 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/10 | 2024-09-29 | 2024-09 | 9 | 2025-08-09 | 2025-08 | 8 | 314 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/8 | 2024-09-30 | 2024-09 | 9 | 2024-11-12 | 2024-11 | 11 | 43 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37/3 | 2024-09-30 | 2024-09 | 9 | 2026-01-23 | 2026-01 | 1 | 480 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4A/0 | 2024-10-01 | 2024-10 | 10 | 2025-09-13 | 2025-09 | 9 | 347 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/9 | 2024-10-01 | 2024-10 | 10 | 2025-08-23 | 2025-08 | 8 | 326 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7/0 | 2024-10-01 | 2024-10 | 10 | 2025-07-22 | 2025-07 | 7 | 294 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/5 | 2024-10-03 | 2024-10 | 10 | 2025-01-06 | 2025-01 | 1 | 95 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/7 | 2024-10-04 | 2024-10 | 10 | 2024-11-26 | 2024-11 | 11 | 53 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 36A/0 | 2024-10-05 | 2024-10 | 10 | 2025-04-18 | 2025-04 | 4 | 195 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3/8 | 2024-10-05 | 2024-10 | 10 |  |  |  |  | No | No |  |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation
TA 413 | 4xx | Government | ta413 | 34/9 | 2024-10-07 | 2024-10 | 10 | 2024-12-13 | 2024-12 | 12 | 67 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/9 | 2024-10-07 | 2024-10 | 10 | 2025-08-29 | 2025-08 | 8 | 326 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 27/3 | 2024-10-08 | 2024-10 | 10 | 2025-11-28 | 2025-11 | 11 | 416 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7/3 | 2024-10-08 | 2024-10 | 10 | 2025-07-09 | 2025-07 | 7 | 274 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/6 | 2024-10-09 | 2024-10 | 10 | 2024-12-29 | 2024-12 | 12 | 81 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3/9 | 2024-10-09 | 2024-10 | 10 |  |  |  |  | No | No |  |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation
TA 413 | 4xx | Government | ta413 | 3/10 | 2024-10-12 | 2024-10 | 10 | 2025-07-16 | 2025-07 | 7 | 277 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/10 | 2024-10-12 | 2024-10 | 10 | 2024-12-22 | 2024-12 | 12 | 71 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7/4 | 2024-10-12 | 2024-10 | 10 | 2025-02-20 | 2025-02 | 2 | 131 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 27/6 | 2024-10-14 | 2024-10 | 10 | 2025-11-13 | 2025-11 | 11 | 395 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37/0 | 2024-10-14 | 2024-10 | 10 |  |  |  |  | No | No |  |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation
TA 413 | 4xx | Government | ta413 | 34/2 | 2024-10-16 | 2024-10 | 10 | 2025-01-10 | 2025-01 | 1 | 86 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/7 | 2024-10-16 | 2024-10 | 10 | 2025-08-22 | 2025-08 | 8 | 310 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/7 | 2024-10-17 | 2024-10 | 10 | 2024-12-13 | 2024-12 | 12 | 57 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/0 | 2024-10-18 | 2024-10 | 10 | 2025-08-13 | 2025-08 | 8 | 299 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3/7 | 2024-10-19 | 2024-10 | 10 |  |  |  |  | No | No |  |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation
TA 413 | 4xx | Government | ta413 | 6/5 | 2024-10-19 | 2024-10 | 10 | 2025-08-02 | 2025-08 | 8 | 287 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37A/4 | 2024-10-21 | 2024-10 | 10 | 2025-02-25 | 2025-02 | 2 | 127 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/5 | 2024-10-22 | 2024-10 | 10 | 2025-01-31 | 2025-01 | 1 | 101 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3/6 | 2024-10-22 | 2024-10 | 10 |  |  |  |  | No | No |  |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation
TA 413 | 4xx | Government | ta413 | 5/5 | 2024-10-23 | 2024-10 | 10 | 2025-08-20 | 2025-08 | 8 | 301 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29/2 | 2024-10-25 | 2024-10 | 10 | 2025-12-12 | 2025-12 | 12 | 413 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/8 | 2024-10-25 | 2024-10 | 10 | 2025-02-18 | 2025-02 | 2 | 116 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37A/5 | 2024-10-25 | 2024-10 | 10 | 2025-02-24 | 2025-02 | 2 | 122 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/9 | 2024-10-27 | 2024-10 | 10 | 2025-01-17 | 2025-01 | 1 | 82 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3/4 | 2024-10-29 | 2024-10 | 10 |  |  |  |  | No | No |  |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation
TA 413 | 4xx | Government | ta413 | 35/8 | 2024-10-29 | 2024-10 | 10 | 2024-12-23 | 2024-12 | 12 | 55 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37A/3 | 2024-10-30 | 2024-10 | 10 | 2025-02-16 | 2025-02 | 2 | 109 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29A/0 | 2024-11-07 | 2024-11 | 11 | 2025-10-06 | 2025-10 | 10 | 333 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37A/2 | 2024-11-08 | 2024-11 | 11 | 2025-01-29 | 2025-01 | 1 | 82 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/8 | 2024-11-08 | 2024-11 | 11 | 2025-08-29 | 2025-08 | 8 | 294 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/11 | 2024-11-09 | 2024-11 | 11 | 2024-12-24 | 2024-12 | 12 | 45 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/9 | 2024-11-11 | 2024-11 | 11 | 2025-08-18 | 2025-08 | 8 | 280 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 18/0 | 2024-11-12 | 2024-11 | 11 | 2025-09-07 | 2025-09 | 9 | 299 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37A/1 | 2024-11-12 | 2024-11 | 11 | 2025-02-08 | 2025-02 | 2 | 88 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 18/1 | 2024-11-16 | 2024-11 | 11 | 2025-09-16 | 2025-09 | 9 | 304 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37/4 | 2024-11-17 | 2024-11 | 11 | 2025-01-11 | 2025-01 | 1 | 55 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 18/2 | 2024-11-19 | 2024-11 | 11 | 2025-09-21 | 2025-09 | 9 | 306 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 36/0 | 2024-11-20 | 2024-11 | 11 | 2026-01-22 | 2026-01 | 1 | 428 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/8 | 2024-11-20 | 2024-11 | 11 | 2025-03-19 | 2025-03 | 3 | 119 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37/5 | 2024-11-21 | 2024-11 | 11 | 2025-01-22 | 2025-01 | 1 | 62 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/9 | 2024-11-21 | 2024-11 | 11 | 2025-02-15 | 2025-02 | 2 | 86 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7A/0 | 2024-11-22 | 2024-11 | 11 | 2025-01-22 | 2025-01 | 1 | 61 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/0 | 2024-11-23 | 2024-11 | 11 | 2025-01-17 | 2025-01 | 1 | 55 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/10 | 2024-11-23 | 2024-11 | 11 | 2025-02-18 | 2025-02 | 2 | 87 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 18/3 | 2024-11-24 | 2024-11 | 11 | 2025-09-26 | 2025-09 | 9 | 306 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/7 | 2024-11-26 | 2024-11 | 11 | 2025-03-12 | 2025-03 | 3 | 106 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/4 | 2024-11-27 | 2024-11 | 11 | 2025-01-14 | 2025-01 | 1 | 48 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37A/0 | 2024-11-27 | 2024-11 | 11 | 2025-02-28 | 2025-02 | 2 | 93 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 18/4 | 2024-11-29 | 2024-11 | 11 | 2025-10-01 | 2025-10 | 10 | 306 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/6 | 2024-11-29 | 2024-11 | 11 | 2025-01-29 | 2025-01 | 1 | 61 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/5 | 2024-11-30 | 2024-11 | 11 | 2025-02-11 | 2025-02 | 2 | 73 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7/2 | 2024-12-01 | 2024-12 | 12 | 2024-12-27 | 2024-12 | 12 | 26 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 18/6 | 2024-12-04 | 2024-12 | 12 | 2025-10-11 | 2025-10 | 10 | 311 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/0 | 2024-12-04 | 2024-12 | 12 | 2025-03-29 | 2025-03 | 3 | 115 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/0 | 2024-12-06 | 2024-12 | 12 | 2025-02-09 | 2025-02 | 2 | 65 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/3 | 2024-12-06 | 2024-12 | 12 | 2025-01-24 | 2025-01 | 1 | 49 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 18/5 | 2024-12-07 | 2024-12 | 12 | 2025-10-07 | 2025-10 | 10 | 304 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37A/6 | 2024-12-08 | 2024-12 | 12 | 2025-02-24 | 2025-02 | 2 | 78 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/4 | 2024-12-08 | 2024-12 | 12 | 2025-02-05 | 2025-02 | 2 | 59 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/3 | 2024-12-10 | 2024-12 | 12 | 2025-10-12 | 2025-10 | 10 | 306 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/2 | 2024-12-12 | 2024-12 | 12 | 2025-03-07 | 2025-03 | 3 | 85 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/2 | 2024-12-12 | 2024-12 | 12 | 2025-03-26 | 2025-03 | 3 | 104 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/1 | 2024-12-13 | 2024-12 | 12 | 2025-03-01 | 2025-03 | 3 | 78 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/3 | 2024-12-14 | 2024-12 | 12 | 2025-03-31 | 2025-03 | 3 | 107 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/1 | 2024-12-15 | 2024-12 | 12 | 2025-03-22 | 2025-03 | 3 | 97 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7/5 | 2024-12-17 | 2024-12 | 12 | 2025-02-11 | 2025-02 | 2 | 56 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/0 | 2024-12-18 | 2024-12 | 12 | 2025-09-11 | 2025-09 | 9 | 267 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 17/0 | 2024-12-19 | 2024-12 | 12 | 2025-11-16 | 2025-11 | 11 | 332 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/7 | 2024-12-19 | 2024-12 | 12 | 2025-08-14 | 2025-08 | 8 | 238 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/0 | 2024-12-21 | 2024-12 | 12 | 2025-03-09 | 2025-03 | 3 | 78 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/2 | 2024-12-21 | 2024-12 | 12 | 2025-03-12 | 2025-03 | 3 | 81 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/6 | 2024-12-21 | 2024-12 | 12 | 2025-04-14 | 2025-04 | 4 | 114 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/2 | 2024-12-22 | 2024-12 | 12 | 2025-09-24 | 2025-09 | 9 | 276 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/4 | 2024-12-23 | 2024-12 | 12 | 2025-03-21 | 2025-03 | 3 | 88 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/8 | 2024-12-25 | 2024-12 | 12 | 2025-10-10 | 2025-10 | 10 | 289 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 41/1 | 2024-12-27 | 2024-12 | 12 | 2025-09-24 | 2025-09 | 9 | 271 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 16/0 | 2024-12-28 | 2024-12 | 12 | 2026-06-02 | 2026-06 | 6 | 521 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/4 | 2024-12-29 | 2024-12 | 12 | 2025-09-09 | 2025-09 | 9 | 254 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/3 | 2024-12-29 | 2024-12 | 12 | 2025-03-20 | 2025-03 | 3 | 81 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/5 | 2024-12-29 | 2024-12 | 12 | 2025-04-05 | 2025-04 | 4 | 97 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7/6 | 2024-12-30 | 2024-12 | 12 | 2025-01-31 | 2025-01 | 1 | 32 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/12 | 2024-12-31 | 2024-12 | 12 | 2025-11-29 | 2025-11 | 11 | 333 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/4 | 2024-12-31 | 2024-12 | 12 | 2025-04-09 | 2025-04 | 4 | 99 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/5 | 2025-01-03 | 2025-01 | 1 | 2025-12-21 | 2025-12 | 12 | 352 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 42/0 | 2025-01-03 | 2025-01 | 1 | 2025-07-21 | 2025-07 | 7 | 199 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/5 | 2025-01-05 | 2025-01 | 1 | 2025-03-14 | 2025-03 | 3 | 68 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/9 | 2025-01-05 | 2025-01 | 1 | 2025-08-01 | 2025-08 | 8 | 208 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/3 | 2025-01-06 | 2025-01 | 1 | 2025-02-14 | 2025-02 | 2 | 39 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/6 | 2025-01-07 | 2025-01 | 1 | 2025-08-29 | 2025-08 | 8 | 234 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 42/1 | 2025-01-08 | 2025-01 | 1 | 2025-08-02 | 2025-08 | 8 | 206 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/6 | 2025-01-09 | 2025-01 | 1 | 2025-04-09 | 2025-04 | 4 | 90 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/10 | 2025-01-09 | 2025-01 | 1 | 2025-09-30 | 2025-09 | 9 | 264 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/7 | 2025-01-10 | 2025-01 | 1 | 2025-09-09 | 2025-09 | 9 | 242 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/8 | 2025-01-13 | 2025-01 | 1 | 2025-09-14 | 2025-09 | 9 | 244 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/11 | 2025-01-13 | 2025-01 | 1 | 2025-09-21 | 2025-09 | 9 | 251 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 42/2 | 2025-01-13 | 2025-01 | 1 | 2025-08-07 | 2025-08 | 8 | 206 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/0 | 2025-01-13 | 2025-01 | 1 | 2025-02-09 | 2025-02 | 2 | 27 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 22/0 | 2025-01-15 | 2025-01 | 1 | 2025-10-28 | 2025-10 | 10 | 286 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/9 | 2025-01-17 | 2025-01 | 1 | 2025-08-12 | 2025-08 | 8 | 207 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/7 | 2025-01-17 | 2025-01 | 1 | 2025-03-07 | 2025-03 | 3 | 49 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 41/0 | 2025-01-19 | 2025-01 | 1 | 2025-10-08 | 2025-10 | 10 | 262 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40A/0 | 2025-01-20 | 2025-01 | 1 | 2025-09-04 | 2025-09 | 9 | 227 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 10/0 | 2025-01-21 | 2025-01 | 1 | 2025-10-02 | 2025-10 | 10 | 254 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/10 | 2025-01-21 | 2025-01 | 1 | 2025-07-18 | 2025-07 | 7 | 178 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43/7 | 2025-01-21 | 2025-01 | 1 | 2025-09-24 | 2025-09 | 9 | 246 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 23/0 | 2025-01-22 | 2025-01 | 1 | 2025-10-12 | 2025-10 | 10 | 263 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43/3 | 2025-01-23 | 2025-01 | 1 | 2025-08-23 | 2025-08 | 8 | 212 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/8 | 2025-01-24 | 2025-01 | 1 | 2024-03-26 | 2024-03 | 3 | -304 | Yes | Yes | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/4 | 2025-01-24 | 2025-01 | 1 | 2025-02-20 | 2025-02 | 2 | 27 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43/0 | 2025-01-25 | 2025-01 | 1 | 2026-02-01 | 2026-02 | 2 | 372 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43/8 | 2025-01-25 | 2025-01 | 1 | 2025-09-14 | 2025-09 | 9 | 232 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/1 | 2025-01-27 | 2025-01 | 1 | 2025-11-27 | 2025-11 | 11 | 304 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43/4 | 2025-01-28 | 2025-01 | 1 | 2025-09-03 | 2025-09 | 9 | 218 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 23A/0 | 2025-01-30 | 2025-01 | 1 | 2025-11-14 | 2025-11 | 11 | 288 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32/1 | 2025-01-31 | 2025-01 | 1 | 2025-07-05 | 2025-07 | 7 | 155 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/9 | 2025-01-31 | 2025-01 | 1 | 2025-03-25 | 2025-03 | 3 | 53 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 42A/0 | 2025-01-31 | 2025-01 | 1 | 2025-08-12 | 2025-08 | 8 | 193 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/2 | 2025-02-01 | 2025-02 | 2 | 2025-08-04 | 2025-08 | 8 | 184 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43/6 | 2025-02-02 | 2025-02 | 2 | 2025-09-08 | 2025-09 | 9 | 218 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 18/7 | 2025-02-04 | 2025-02 | 2 | 2025-10-16 | 2025-10 | 10 | 254 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32/2 | 2025-02-04 | 2025-02 | 2 | 2025-07-18 | 2025-07 | 7 | 164 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 44/0 | 2025-02-04 | 2025-02 | 2 | 2025-09-20 | 2025-09 | 9 | 228 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43/1 | 2025-02-05 | 2025-02 | 2 | 2025-12-22 | 2025-12 | 12 | 320 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/4 | 2025-02-07 | 2025-02 | 2 | 2025-08-22 | 2025-08 | 8 | 196 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43/2 | 2025-02-08 | 2025-02 | 2 | 2025-08-20 | 2025-08 | 8 | 193 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32/0 | 2025-02-09 | 2025-02 | 2 | 2025-09-04 | 2025-09 | 9 | 207 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43A/0 | 2025-02-09 | 2025-02 | 2 | 2025-11-30 | 2025-11 | 11 | 294 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/5 | 2025-02-10 | 2025-02 | 2 | 2025-08-23 | 2025-08 | 8 | 194 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 13/0 | 2025-02-11 | 2025-02 | 2 | 2025-12-18 | 2025-12 | 12 | 310 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/10 | 2025-02-11 | 2025-02 | 2 | 2025-03-31 | 2025-03 | 3 | 48 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 20/2 | 2025-02-12 | 2025-02 | 2 | 2025-09-26 | 2025-09 | 9 | 226 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/11 | 2025-02-13 | 2025-02 | 2 | 2025-07-15 | 2025-07 | 7 | 152 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 20/1 | 2025-02-16 | 2025-02 | 2 | 2025-09-19 | 2025-09 | 9 | 215 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 21/5 | 2025-02-16 | 2025-02 | 2 | 2025-11-07 | 2025-11 | 11 | 264 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32/7 | 2025-02-17 | 2025-02 | 2 | 2025-07-26 | 2025-07 | 7 | 159 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 13A/0 | 2025-02-18 | 2025-02 | 2 | 2026-01-01 | 2026-01 | 1 | 317 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32A/0 | 2025-02-18 | 2025-02 | 2 | 2025-08-01 | 2025-08 | 8 | 164 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/6 | 2025-02-19 | 2025-02 | 2 | 2025-08-20 | 2025-08 | 8 | 182 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/2 | 2025-02-20 | 2025-02 | 2 | 2025-08-09 | 2025-08 | 8 | 170 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 21/4 | 2025-02-22 | 2025-02 | 2 | 2025-11-13 | 2025-11 | 11 | 264 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32A/1 | 2025-02-22 | 2025-02 | 2 | 2025-08-14 | 2025-08 | 8 | 173 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29/0 | 2025-02-23 | 2025-02 | 2 | 2025-10-08 | 2025-10 | 10 | 227 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/11 | 2025-02-24 | 2025-02 | 2 | 2025-03-30 | 2025-03 | 3 | 34 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 27/0 | 2025-02-25 | 2025-02 | 2 | 2025-11-08 | 2025-11 | 11 | 256 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/9 | 2025-02-25 | 2025-02 | 2 | 2025-11-06 | 2025-11 | 11 | 254 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 28/0 | 2025-02-26 | 2025-02 | 2 | 2025-10-31 | 2025-10 | 10 | 247 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/7 | 2025-02-26 | 2025-02 | 2 | 2025-08-23 | 2025-08 | 8 | 178 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 24/0 | 2025-02-27 | 2025-02 | 2 | 2025-11-13 | 2025-11 | 11 | 259 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 44/1 | 2025-03-01 | 2025-03 | 3 | 2025-08-25 | 2025-08 | 8 | 177 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 26/0 | 2025-03-05 | 2025-03 | 3 | 2025-10-10 | 2025-10 | 10 | 219 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/8 | 2025-03-05 | 2025-03 | 3 | 2025-12-04 | 2025-12 | 12 | 274 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/0 | 2025-03-06 | 2025-03 | 3 | 2025-10-05 | 2025-10 | 10 | 213 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 44/2 | 2025-03-06 | 2025-03 | 3 | 2025-09-04 | 2025-09 | 9 | 182 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 25/0 | 2025-03-08 | 2025-03 | 3 | 2025-11-12 | 2025-11 | 11 | 249 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/0 | 2025-03-08 | 2025-03 | 3 | 2025-04-18 | 2025-04 | 4 | 41 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 44/4 | 2025-03-12 | 2025-03 | 3 | 2025-09-16 | 2025-09 | 9 | 188 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 44/3 | 2025-03-13 | 2025-03 | 3 | 2025-09-10 | 2025-09 | 9 | 181 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/0 | 2025-03-16 | 2025-03 | 3 | 2025-09-19 | 2025-09 | 9 | 187 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 44/5 | 2025-03-17 | 2025-03 | 3 | 2025-09-20 | 2025-09 | 9 | 187 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 2A/2 | 2025-03-23 | 2025-03 | 3 | 2025-08-28 | 2025-08 | 8 | 158 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3B/2 | 2025-03-23 | 2025-03 | 3 | 2025-09-26 | 2025-09 | 9 | 187 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/1 | 2025-03-23 | 2025-03 | 3 | 2025-09-13 | 2025-09 | 9 | 174 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3B/1 | 2025-03-26 | 2025-03 | 3 | 2025-10-09 | 2025-10 | 10 | 197 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 2A/3 | 2025-03-27 | 2025-03 | 3 | 2025-09-03 | 2025-09 | 9 | 160 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 2A/4 | 2025-03-30 | 2025-03 | 3 | 2025-09-09 | 2025-09 | 9 | 163 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3B/0 | 2025-03-30 | 2025-03 | 3 | 2025-09-25 | 2025-09 | 9 | 179 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/1 | 2025-03-30 | 2025-03 | 3 | 2025-07-06 | 2025-07 | 7 | 98 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5A/0 | 2025-04-01 | 2025-04 | 4 | 2025-08-22 | 2025-08 | 8 | 143 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3A/6 | 2025-04-03 | 2025-04 | 4 | 2025-09-16 | 2025-09 | 9 | 166 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 2A/5 | 2025-04-05 | 2025-04 | 4 | 2025-09-16 | 2025-09 | 9 | 164 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32/5 | 2025-04-08 | 2025-04 | 4 | 2025-07-16 | 2025-07 | 7 | 99 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3A/1 | 2025-04-08 | 2025-04 | 4 | 2025-09-03 | 2025-09 | 9 | 148 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3A/5 | 2025-04-08 | 2025-04 | 4 | 2025-09-07 | 2025-09 | 9 | 152 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3A/4 | 2025-04-10 | 2025-04 | 4 | 2025-10-01 | 2025-10 | 10 | 174 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32/6 | 2025-04-11 | 2025-04 | 4 | 2025-07-06 | 2025-07 | 7 | 86 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/3 | 2025-04-12 | 2025-04 | 4 | 2026-01-07 | 2026-01 | 1 | 270 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3A/3 | 2025-04-12 | 2025-04 | 4 | 2025-09-20 | 2025-09 | 9 | 161 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/1 | 2025-04-14 | 2025-04 | 4 | 2025-08-25 | 2025-08 | 8 | 133 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/2 | 2025-04-15 | 2025-04 | 4 | 2025-08-01 | 2025-08 | 8 | 108 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3A/2 | 2025-04-15 | 2025-04 | 4 | 2025-09-12 | 2025-09 | 9 | 150 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 14/0 | 2025-04-16 | 2025-04 | 4 | 2025-11-30 | 2025-11 | 11 | 228 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/0 | 2025-04-17 | 2025-04 | 4 | 2025-09-03 | 2025-09 | 9 | 139 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3A/0 | 2025-04-18 | 2025-04 | 4 | 2025-10-11 | 2025-10 | 10 | 176 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3B/3 | 2025-04-19 | 2025-04 | 4 | 2025-10-27 | 2025-10 | 10 | 191 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 21/3 | 2025-04-22 | 2025-04 | 4 | 2025-11-21 | 2025-11 | 11 | 213 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 2A/6 | 2025-04-23 | 2025-04 | 4 | 2025-09-24 | 2025-09 | 9 | 154 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 21/2 | 2025-04-24 | 2025-04 | 4 | 2025-11-06 | 2025-11 | 11 | 196 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4/0 | 2025-04-25 | 2025-04 | 4 | 2025-09-25 | 2025-09 | 9 | 153 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8A/0 | 2025-04-25 | 2025-04 | 4 | 2025-08-07 | 2025-08 | 8 | 104 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 21/1 | 2025-04-29 | 2025-04 | 4 | 2025-10-24 | 2025-10 | 10 | 178 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/10 | 2025-05-02 | 2025-05 | 5 | 2026-02-07 | 2026-02 | 2 | 281 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/0 | 2025-05-03 | 2025-05 | 5 | 2025-08-30 | 2025-08 | 8 | 119 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 45/0 | 2025-05-05 | 2025-05 | 5 | 2025-09-28 | 2025-09 | 9 | 146 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 46/0 | 2025-05-07 | 2025-05 | 5 | 2025-09-30 | 2025-09 | 9 | 146 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 20/6 | 2025-05-09 | 2025-05 | 5 | 2025-10-17 | 2025-10 | 10 | 161 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 20/5 | 2025-05-13 | 2025-05 | 5 | 2025-10-28 | 2025-10 | 10 | 168 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 21/0 | 2025-05-13 | 2025-05 | 5 | 2025-10-20 | 2025-10 | 10 | 160 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 20/4 | 2025-05-18 | 2025-05 | 5 | 2025-11-01 | 2025-11 | 11 | 167 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 20/3 | 2025-05-22 | 2025-05 | 5 | 2025-10-30 | 2025-10 | 10 | 161 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 19/0 | 2025-05-26 | 2025-05 | 5 | 2025-10-16 | 2025-10 | 10 | 143 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 20/0 | 2025-06-02 | 2025-06 | 6 | 2025-10-01 | 2025-10 | 10 | 121 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 11/0 | 2025-06-08 | 2025-06 | 6 | 2025-11-13 | 2025-11 | 11 | 158 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 12/0 | 2025-06-14 | 2025-06 | 6 | 2025-09-11 | 2025-09 | 9 | 89 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 1/0 | 2025-06-27 | 2025-06 | 6 | 2025-08-07 | 2025-08 | 8 | 41 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 2A/1 | 2025-07-05 | 2025-07 | 7 | 2025-08-21 | 2025-08 | 8 | 47 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 2A/0 | 2025-07-14 | 2025-07 | 7 | 2026-01-01 | 2026-01 | 1 | 171 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 36B/0-N | 2026-01-23 | 2026-01 | 1 | 2026-08-02 | 2026-08 | 8 | 191 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 36C/0-N | 2026-02-08 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation
TA 413 | 4xx | Government | ta413 | 37/0-N | 2026-03-05 | 2026-03 | 3 | 2026-07-12 | 2026-07 | 7 | 129 | Yes | No | exact |  |  | TA 413 - DPR - 2026-08-12.xlsx | Foundation | TA 413 - DPR - 2026-08-12.xlsx | Erection
TA 414 | 4xx | Government | ta414 | 241/2 | 2024-05-25 | 2024-05 | 5 | 2026-01-14 | 2026-01 | 1 | 599 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 241/0 | 2024-05-30 | 2024-05 | 5 | 2025-09-02 | 2025-09 | 9 | 460 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 118/0 | 2024-10-31 | 2024-10 | 10 | 2025-05-31 | 2025-05 | 5 | 212 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 120/3 | 2024-11-12 | 2024-11 | 11 | 2025-06-09 | 2025-06 | 6 | 209 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/5 | 2024-11-19 | 2024-11 | 11 | 2026-01-30 | 2026-01 | 1 | 437 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 120/2 | 2024-11-22 | 2024-11 | 11 | 2025-06-02 | 2025-06 | 6 | 192 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/4 | 2024-11-29 | 2024-11 | 11 | 2024-03-27 | 2024-03 | 3 | -247 | Yes | Yes | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/2 | 2024-12-07 | 2024-12 | 12 | 2025-12-30 | 2025-12 | 12 | 388 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 183/1 | 2024-12-09 | 2024-12 | 12 | 2026-02-23 | 2026-02 | 2 | 441 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 119/0 | 2024-12-16 | 2024-12 | 12 | 2025-08-10 | 2025-08 | 8 | 237 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/3 | 2024-12-21 | 2024-12 | 12 | 2026-01-19 | 2026-01 | 1 | 394 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 120/0 | 2024-12-22 | 2024-12 | 12 | 2026-01-21 | 2026-01 | 1 | 395 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 120/5 | 2024-12-22 | 2024-12 | 12 | 2025-12-08 | 2025-12 | 12 | 351 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 244/6 | 2024-12-23 | 2024-12 | 12 | 2026-02-25 | 2026-02 | 2 | 429 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 145/4 | 2024-12-27 | 2024-12 | 12 | 2026-01-09 | 2026-01 | 1 | 378 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 249/1 | 2024-12-27 | 2024-12 | 12 | 2026-06-25 | 2026-06 | 6 | 545 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 119/2 | 2024-12-28 | 2024-12 | 12 | 2025-08-07 | 2025-08 | 8 | 222 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 119/3 | 2024-12-30 | 2024-12 | 12 | 2025-07-26 | 2025-07 | 7 | 208 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/6 | 2024-12-31 | 2024-12 | 12 | 2026-02-13 | 2026-02 | 2 | 409 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 249/0 | 2025-01-02 | 2025-01 | 1 | 2026-06-13 | 2026-06 | 6 | 527 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 249/2 | 2025-01-03 | 2025-01 | 1 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 120/6 | 2025-01-04 | 2025-01 | 1 | 2025-06-16 | 2025-06 | 6 | 163 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 126/3 | 2025-01-08 | 2025-01 | 1 | 2026-03-27 | 2026-03 | 3 | 443 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/1 | 2025-01-10 | 2025-01 | 1 | 2026-03-29 | 2026-03 | 3 | 443 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 137/2 | 2025-01-10 | 2025-01 | 1 | 2025-12-28 | 2025-12 | 12 | 352 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/7 | 2025-01-12 | 2025-01 | 1 | 2025-09-15 | 2025-09 | 9 | 246 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 145/3 | 2025-01-13 | 2025-01 | 1 | 2026-01-15 | 2026-01 | 1 | 367 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 120/7 | 2025-01-14 | 2025-01 | 1 | 2025-12-28 | 2025-12 | 12 | 348 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 244/5 | 2025-01-16 | 2025-01 | 1 | 2025-12-14 | 2025-12 | 12 | 332 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/8 | 2025-01-20 | 2025-01 | 1 | 2026-05-07 | 2026-05 | 5 | 472 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 250/0 | 2025-01-20 | 2025-01 | 1 | 2026-06-05 | 2026-06 | 6 | 501 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 252/3 | 2025-01-22 | 2025-01 | 1 | 2026-04-14 | 2026-04 | 4 | 447 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 136/1 | 2025-01-24 | 2025-01 | 1 | 2025-12-20 | 2025-12 | 12 | 330 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 145/2 | 2025-01-26 | 2025-01 | 1 | 2026-04-24 | 2026-04 | 4 | 453 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 250A/2 | 2025-01-28 | 2025-01 | 1 | 2026-01-04 | 2026-01 | 1 | 341 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 252/0 | 2025-01-31 | 2025-01 | 1 | 2026-02-05 | 2026-02 | 2 | 370 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 248/2 | 2025-02-03 | 2025-02 | 2 | 2025-09-11 | 2025-09 | 9 | 220 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/10 | 2025-02-04 | 2025-02 | 2 | 2025-09-08 | 2025-09 | 9 | 216 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 141/4 | 2025-02-04 | 2025-02 | 2 | 2026-01-29 | 2026-01 | 1 | 359 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 241/4 | 2025-02-04 | 2025-02 | 2 | 2025-12-06 | 2025-12 | 12 | 305 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 124/1 | 2025-02-06 | 2025-02 | 2 | 2026-04-24 | 2026-04 | 4 | 442 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 137/1 | 2025-02-07 | 2025-02 | 2 | 2026-01-22 | 2026-01 | 1 | 349 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 141/3 | 2025-02-08 | 2025-02 | 2 | 2026-01-04 | 2026-01 | 1 | 330 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 145/7 | 2025-02-08 | 2025-02 | 2 | 2026-01-19 | 2026-01 | 1 | 345 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/9 | 2025-02-11 | 2025-02 | 2 | 2026-05-16 | 2026-05 | 5 | 459 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 126/1 | 2025-02-13 | 2025-02 | 2 | 2025-12-30 | 2025-12 | 12 | 320 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 141/5 | 2025-02-13 | 2025-02 | 2 | 2026-01-09 | 2026-01 | 1 | 330 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 243/3 | 2025-02-13 | 2025-02 | 2 | 2026-05-29 | 2026-05 | 5 | 470 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 248/1 | 2025-02-13 | 2025-02 | 2 | 2025-12-26 | 2025-12 | 12 | 316 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 137/0 | 2025-02-14 | 2025-02 | 2 | 2026-01-04 | 2026-01 | 1 | 324 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 124/0 | 2025-02-19 | 2025-02 | 2 | 2026-04-08 | 2026-04 | 4 | 413 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 243/2 | 2025-02-21 | 2025-02 | 2 | 2025-12-19 | 2025-12 | 12 | 301 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 250/3 | 2025-02-23 | 2025-02 | 2 | 2025-12-23 | 2025-12 | 12 | 303 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 126/2 | 2025-02-26 | 2025-02 | 2 | 2026-03-14 | 2026-03 | 3 | 381 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 148/0 | 2025-02-27 | 2025-02 | 2 | 2026-01-31 | 2026-01 | 1 | 338 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 126/0 | 2025-02-28 | 2025-02 | 2 | 2026-01-17 | 2026-01 | 1 | 323 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 244/1 | 2025-03-07 | 2025-03 | 3 | 2025-12-04 | 2025-12 | 12 | 272 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 132/0 | 2025-03-08 | 2025-03 | 3 | 2025-12-08 | 2025-12 | 12 | 275 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 117/1 | 2025-03-13 | 2025-03 | 3 | 2026-01-15 | 2026-01 | 1 | 308 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 117/2 | 2025-03-17 | 2025-03 | 3 | 2025-08-19 | 2025-08 | 8 | 155 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 251/0 | 2025-03-20 | 2025-03 | 3 | 2026-02-07 | 2026-02 | 2 | 324 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 171/0 | 2025-03-22 | 2025-03 | 3 | 2026-04-26 | 2026-04 | 4 | 400 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/0 | 2025-03-23 | 2025-03 | 3 | 2026-02-24 | 2026-02 | 2 | 338 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 180/3 | 2025-03-23 | 2025-03 | 3 | 2025-12-29 | 2025-12 | 12 | 281 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 172/0 | 2025-03-26 | 2025-03 | 3 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 180/4 | 2025-03-27 | 2025-03 | 3 | 2025-12-30 | 2025-12 | 12 | 278 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 172/1 | 2025-04-01 | 2025-04 | 4 | 2026-05-07 | 2026-05 | 5 | 401 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 179/3 | 2025-04-01 | 2025-04 | 4 | 2026-03-12 | 2026-03 | 3 | 345 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 165/7 | 2025-04-05 | 2025-04 | 4 | 2026-05-13 | 2026-05 | 5 | 403 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 180/2 | 2025-04-05 | 2025-04 | 4 | 2026-01-23 | 2026-01 | 1 | 293 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 180/5 | 2025-04-06 | 2025-04 | 4 | 2025-12-17 | 2025-12 | 12 | 255 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 180/7 | 2025-04-08 | 2025-04 | 4 | 2026-01-29 | 2026-01 | 1 | 296 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 179/1 | 2025-04-09 | 2025-04 | 4 | 2025-12-08 | 2025-12 | 12 | 243 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 132/1 | 2025-04-10 | 2025-04 | 4 | 2026-02-24 | 2026-02 | 2 | 320 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 174/4 | 2025-04-10 | 2025-04 | 4 | 2026-03-16 | 2026-03 | 3 | 340 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 174/6 | 2025-04-11 | 2025-04 | 4 | 2026-01-23 | 2026-01 | 1 | 287 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 174/5 | 2025-04-15 | 2025-04 | 4 | 2026-03-23 | 2026-03 | 3 | 342 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 174/1 | 2025-04-16 | 2025-04 | 4 | 2026-02-25 | 2026-02 | 2 | 315 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 176/1 | 2025-04-18 | 2025-04 | 4 | 2026-02-15 | 2026-02 | 2 | 303 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 175/0 | 2025-04-23 | 2025-04 | 4 | 2026-01-06 | 2026-01 | 1 | 258 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 177/0 | 2025-04-23 | 2025-04 | 4 | 2026-01-25 | 2026-01 | 1 | 277 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 176/2 | 2025-04-27 | 2025-04 | 4 | 2026-02-09 | 2026-02 | 2 | 288 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 148/4 | 2025-04-28 | 2025-04 | 4 | 2025-12-20 | 2025-12 | 12 | 236 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 178/3 | 2025-04-28 | 2025-04 | 4 | 2026-02-06 | 2026-02 | 2 | 284 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 165/5 | 2025-05-03 | 2025-05 | 5 | 2026-03-20 | 2026-03 | 3 | 321 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 148/2 | 2025-05-12 | 2025-05 | 5 | 2025-12-06 | 2025-12 | 12 | 208 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 180/1 | 2025-05-13 | 2025-05 | 5 | 2026-02-07 | 2026-02 | 2 | 270 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 165/2 | 2025-05-15 | 2025-05 | 5 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 252/5 | 2025-05-17 | 2025-05 | 5 | 2026-01-02 | 2026-01 | 1 | 230 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 243/0 | 2025-06-01 | 2025-06 | 6 | 2025-11-30 | 2025-11 | 11 | 182 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 256/0 | 2025-06-14 | 2025-06 | 6 | 2026-02-24 | 2026-02 | 2 | 255 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 246/0 | 2025-08-23 | 2025-08 | 8 | 2026-01-03 | 2026-01 | 1 | 133 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 250A/1 | 2025-09-09 | 2025-09 | 9 | 2026-01-13 | 2026-01 | 1 | 126 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 131/2 | 2025-09-15 | 2025-09 | 9 | 2025-12-15 | 2025-12 | 12 | 91 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 241/3 | 2025-09-20 | 2025-09 | 9 | 2026-01-28 | 2026-01 | 1 | 130 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 178/0 | 2025-10-14 | 2025-10 | 10 | 2026-03-17 | 2026-03 | 3 | 154 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 120/1 | 2025-10-16 | 2025-10 | 10 | 2026-04-13 | 2026-04 | 4 | 179 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 224/1 | 2025-10-19 | 2025-10 | 10 | 2026-04-02 | 2026-04 | 4 | 165 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 119/1 | 2025-10-20 | 2025-10 | 10 | 2026-01-09 | 2026-01 | 1 | 81 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 224/2 | 2025-10-20 | 2025-10 | 10 | 2026-04-29 | 2026-04 | 4 | 191 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 225/0 | 2025-10-22 | 2025-10 | 10 | 2026-04-29 | 2026-04 | 4 | 189 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 120/4 | 2025-10-26 | 2025-10 | 10 | 2025-12-28 | 2025-12 | 12 | 63 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 223/3 | 2025-10-27 | 2025-10 | 10 | 2026-03-27 | 2026-03 | 3 | 151 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 221/0 | 2025-11-05 | 2025-11 | 11 | 2026-05-08 | 2026-05 | 5 | 184 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 224/0 | 2025-11-08 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 138/0 | 2025-11-13 | 2025-11 | 11 | 2026-01-12 | 2026-01 | 1 | 60 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 220/1 | 2025-11-14 | 2025-11 | 11 | 2026-02-05 | 2026-02 | 2 | 83 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 223/1 | 2025-11-14 | 2025-11 | 11 | 2026-03-11 | 2026-03 | 3 | 117 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 222/0 | 2025-11-15 | 2025-11 | 11 | 2026-03-13 | 2026-03 | 3 | 118 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 185/0 | 2025-11-16 | 2025-11 | 11 | 2026-04-04 | 2026-04 | 4 | 139 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 141/6 | 2025-11-17 | 2025-11 | 11 | 2025-12-04 | 2025-12 | 12 | 17 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 220/0 | 2025-11-17 | 2025-11 | 11 | 2026-04-10 | 2026-04 | 4 | 144 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 223/2 | 2025-11-18 | 2025-11 | 11 | 2026-05-18 | 2026-05 | 5 | 181 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 219/1 | 2025-11-21 | 2025-11 | 11 | 2026-05-18 | 2026-05 | 5 | 178 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 223/0 | 2025-11-22 | 2025-11 | 11 | 2026-02-20 | 2026-02 | 2 | 90 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 218/0 | 2025-11-23 | 2025-11 | 11 | 2026-02-16 | 2026-02 | 2 | 85 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 144/0 | 2025-11-24 | 2025-11 | 11 | 2026-03-16 | 2026-03 | 3 | 112 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 196/0 | 2025-11-24 | 2025-11 | 11 | 2026-02-06 | 2026-02 | 2 | 74 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 142/0 | 2025-11-25 | 2025-11 | 11 | 2025-12-19 | 2025-12 | 12 | 24 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 225/1 | 2025-11-25 | 2025-11 | 11 | 2026-06-26 | 2026-06 | 6 | 213 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 125/1 | 2025-11-26 | 2025-11 | 11 | 2026-02-18 | 2026-02 | 2 | 84 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 187/0 | 2025-11-26 | 2025-11 | 11 | 2025-12-11 | 2025-12 | 12 | 15 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 136/0 | 2025-11-27 | 2025-11 | 11 | 2026-02-14 | 2026-02 | 2 | 79 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 214/2 | 2025-11-27 | 2025-11 | 11 | 2026-02-04 | 2026-02 | 2 | 69 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 225/4 | 2025-11-29 | 2025-11 | 11 | 2026-06-08 | 2026-06 | 6 | 191 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 148/5 | 2025-11-30 | 2025-11 | 11 | 2026-01-21 | 2026-01 | 1 | 52 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 215/0 | 2025-11-30 | 2025-11 | 11 | 2026-03-03 | 2026-03 | 3 | 93 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 186/0 | 2025-12-01 | 2025-12 | 12 | 2026-02-27 | 2026-02 | 2 | 88 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 194/1 | 2025-12-02 | 2025-12 | 12 | 2026-02-16 | 2026-02 | 2 | 76 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 176/0 | 2025-12-03 | 2025-12 | 12 | 2025-12-21 | 2025-12 | 12 | 18 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 214/5 | 2025-12-03 | 2025-12 | 12 | 2026-02-12 | 2026-02 | 2 | 71 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 214/7 | 2025-12-04 | 2025-12 | 12 | 2026-04-02 | 2026-04 | 4 | 119 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 143/0 | 2025-12-05 | 2025-12 | 12 | 2026-01-13 | 2026-01 | 1 | 39 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 184/0 | 2025-12-05 | 2025-12 | 12 | 2026-02-15 | 2026-02 | 2 | 72 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 214/4 | 2025-12-05 | 2025-12 | 12 | 2026-02-08 | 2026-02 | 2 | 65 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 244/2 | 2025-12-06 | 2025-12 | 12 | 2026-01-21 | 2026-01 | 1 | 46 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 145/5 | 2025-12-07 | 2025-12 | 12 | 2025-12-28 | 2025-12 | 12 | 21 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 225/3 | 2025-12-10 | 2025-12 | 12 | 2026-07-12 | 2026-07 | 7 | 214 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 139/0 | 2025-12-11 | 2025-12 | 12 | 2026-02-06 | 2026-02 | 2 | 57 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 148/3 | 2025-12-11 | 2025-12 | 12 | 2026-01-06 | 2026-01 | 1 | 26 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 183/0 | 2025-12-11 | 2025-12 | 12 | 2026-01-11 | 2026-01 | 1 | 31 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 217/4 | 2025-12-11 | 2025-12 | 12 | 2026-03-13 | 2026-03 | 3 | 92 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 250/2 | 2025-12-11 | 2025-12 | 12 | 2026-02-01 | 2026-02 | 2 | 52 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 127/2 | 2025-12-12 | 2025-12 | 12 | 2026-06-14 | 2026-06 | 6 | 184 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 183/2 | 2025-12-12 | 2025-12 | 12 | 2026-02-02 | 2026-02 | 2 | 52 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 214/3 | 2025-12-12 | 2025-12 | 12 | 2026-03-13 | 2026-03 | 3 | 91 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 214/6 | 2025-12-12 | 2025-12 | 12 | 2026-02-27 | 2026-02 | 2 | 77 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 249/3 | 2025-12-13 | 2025-12 | 12 | 2025-12-24 | 2025-12 | 12 | 11 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 182/0 | 2025-12-14 | 2025-12 | 12 | 2026-01-03 | 2026-01 | 1 | 20 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 225/2 | 2025-12-14 | 2025-12 | 12 | 2026-06-23 | 2026-06 | 6 | 191 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 141/1 | 2025-12-15 | 2025-12 | 12 | 2025-12-25 | 2025-12 | 12 | 10 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 161/0 | 2025-12-16 | 2025-12 | 12 | 2026-03-12 | 2026-03 | 3 | 86 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 243/1 | 2025-12-16 | 2025-12 | 12 | 2025-12-29 | 2025-12 | 12 | 13 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 189/1 | 2025-12-17 | 2025-12 | 12 | 2026-01-30 | 2026-01 | 1 | 44 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 145/6 | 2025-12-18 | 2025-12 | 12 | 2026-01-04 | 2026-01 | 1 | 17 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 141/2 | 2025-12-19 | 2025-12 | 12 | 2026-01-02 | 2026-01 | 1 | 14 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 175/1 | 2025-12-19 | 2025-12 | 12 | 2025-12-28 | 2025-12 | 12 | 9 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 217/2 | 2025-12-19 | 2025-12 | 12 | 2026-03-23 | 2026-03 | 3 | 94 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 217/3 | 2025-12-19 | 2025-12 | 12 | 2026-03-19 | 2026-03 | 3 | 90 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 166/0 | 2025-12-20 | 2025-12 | 12 | 2026-04-06 | 2026-04 | 4 | 107 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 165/6 | 2025-12-23 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 180/6 | 2025-12-23 | 2025-12 | 12 | 2026-01-06 | 2026-01 | 1 | 14 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 191/1 | 2025-12-23 | 2025-12 | 12 | 2026-02-20 | 2026-02 | 2 | 59 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 199/1 | 2025-12-23 | 2025-12 | 12 | 2026-02-27 | 2026-02 | 2 | 66 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 257/0 | 2025-12-23 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 216/1 | 2025-12-24 | 2025-12 | 12 | 2026-06-15 | 2026-06 | 6 | 173 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 254/1 | 2025-12-24 | 2025-12 | 12 | 2026-02-02 | 2026-02 | 2 | 40 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 127/0 | 2025-12-25 | 2025-12 | 12 | 2026-02-22 | 2026-02 | 2 | 59 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 148/1 | 2025-12-25 | 2025-12 | 12 | 2026-01-25 | 2026-01 | 1 | 31 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 190/0 | 2025-12-25 | 2025-12 | 12 | 2026-01-17 | 2026-01 | 1 | 23 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 196/1 | 2025-12-25 | 2025-12 | 12 | 2026-02-23 | 2026-02 | 2 | 60 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 197/0 | 2025-12-26 | 2025-12 | 12 | 2026-02-10 | 2026-02 | 2 | 46 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 170/0 | 2025-12-27 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 252/2 | 2025-12-27 | 2025-12 | 12 | 2026-01-23 | 2026-01 | 1 | 27 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 197/2 | 2025-12-29 | 2025-12 | 12 | 2026-01-15 | 2026-01 | 1 | 17 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 196/2 | 2025-12-30 | 2025-12 | 12 | 2026-02-16 | 2026-02 | 2 | 48 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 252/1 | 2025-12-30 | 2025-12 | 12 | 2026-01-19 | 2026-01 | 1 | 20 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 128/0 | 2025-12-31 | 2025-12 | 12 | 2026-03-12 | 2026-03 | 3 | 71 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 179/0 | 2025-12-31 | 2025-12 | 12 | 2026-01-19 | 2026-01 | 1 | 19 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 183/3 | 2025-12-31 | 2025-12 | 12 | 2026-03-16 | 2026-03 | 3 | 75 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 216/2 | 2025-12-31 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 241/1 | 2025-12-31 | 2025-12 | 12 | 2026-05-02 | 2026-05 | 5 | 122 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 141/0 | 2026-01-03 | 2026-01 | 1 | 2026-01-28 | 2026-01 | 1 | 25 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 149/0 | 2026-01-03 | 2026-01 | 1 | 2026-01-31 | 2026-01 | 1 | 28 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 167/0 | 2026-01-04 | 2026-01 | 1 | 2026-04-14 | 2026-04 | 4 | 100 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 127/1 | 2026-01-05 | 2026-01 | 1 | 2026-03-27 | 2026-03 | 3 | 81 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 139/1 | 2026-01-05 | 2026-01 | 1 | 2026-01-31 | 2026-01 | 1 | 26 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 210/0 | 2026-01-05 | 2026-01 | 1 | 2026-06-04 | 2026-06 | 6 | 150 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 192/0 | 2026-01-06 | 2026-01 | 1 | 2026-02-27 | 2026-02 | 2 | 52 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 178/2 | 2026-01-07 | 2026-01 | 1 | 2026-02-11 | 2026-02 | 2 | 35 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 244/0 | 2026-01-09 | 2026-01 | 1 | 2026-05-18 | 2026-05 | 5 | 129 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 211/3 | 2026-01-10 | 2026-01 | 1 | 2026-03-02 | 2026-03 | 3 | 51 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 255/0 | 2026-01-10 | 2026-01 | 1 | 2026-03-12 | 2026-03 | 3 | 61 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 216/3 | 2026-01-12 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 132/3 | 2026-01-13 | 2026-01 | 1 | 2026-03-20 | 2026-03 | 3 | 66 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 162/0 | 2026-01-13 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 199/2 | 2026-01-13 | 2026-01 | 1 | 2026-02-21 | 2026-02 | 2 | 39 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 211/1 | 2026-01-13 | 2026-01 | 1 | 2026-03-03 | 2026-03 | 3 | 49 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 230/0 | 2026-01-13 | 2026-01 | 1 | 2026-02-28 | 2026-02 | 2 | 46 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 245/0 | 2026-01-13 | 2026-01 | 1 | 2026-02-14 | 2026-02 | 2 | 32 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 125/2 | 2026-01-15 | 2026-01 | 1 | 2026-03-01 | 2026-03 | 3 | 45 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 160/0 | 2026-01-15 | 2026-01 | 1 | 2026-02-27 | 2026-02 | 2 | 43 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 191/0 | 2026-01-15 | 2026-01 | 1 | 2026-02-08 | 2026-02 | 2 | 24 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 178/1 | 2026-01-16 | 2026-01 | 1 | 2026-02-05 | 2026-02 | 2 | 20 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 199/0 | 2026-01-16 | 2026-01 | 1 | 2026-01-21 | 2026-01 | 1 | 5 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 245/1 | 2026-01-16 | 2026-01 | 1 | 2026-01-31 | 2026-01 | 1 | 15 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 194/0 | 2026-01-17 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 133/0 | 2026-01-20 | 2026-01 | 1 | 2026-04-08 | 2026-04 | 4 | 78 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 174/3 | 2026-01-20 | 2026-01 | 1 | 2026-03-29 | 2026-03 | 3 | 68 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 227/0 | 2026-01-21 | 2026-01 | 1 | 2026-03-13 | 2026-03 | 3 | 51 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 250A/0 | 2026-01-21 | 2026-01 | 1 | 2026-02-26 | 2026-02 | 2 | 36 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 165/4 | 2026-01-22 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 211/4 | 2026-01-22 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 217/5 | 2026-01-22 | 2026-01 | 1 | 2026-05-27 | 2026-05 | 5 | 125 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 140/0 | 2026-01-23 | 2026-01 | 1 | 2026-02-14 | 2026-02 | 2 | 22 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 193/0 | 2026-01-23 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 198/0 | 2026-01-23 | 2026-01 | 1 | 2026-02-04 | 2026-02 | 2 | 12 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 216/0 | 2026-01-23 | 2026-01 | 1 | 2026-02-17 | 2026-02 | 2 | 25 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 244/3 | 2026-01-23 | 2026-01 | 1 | 2026-05-27 | 2026-05 | 5 | 124 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 197/1 | 2026-01-24 | 2026-01 | 1 | 2026-01-30 | 2026-01 | 1 | 6 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 244/4 | 2026-01-25 | 2026-01 | 1 | 2026-03-15 | 2026-03 | 3 | 49 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 133/1 | 2026-01-26 | 2026-01 | 1 | 2026-05-28 | 2026-05 | 5 | 122 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 125/0 | 2026-01-27 | 2026-01 | 1 | 2026-05-03 | 2026-05 | 5 | 96 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 226/3 | 2026-01-27 | 2026-01 | 1 | 2026-03-19 | 2026-03 | 3 | 51 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 233/0 | 2026-01-27 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 211/2 | 2026-01-28 | 2026-01 | 1 | 2026-03-27 | 2026-03 | 3 | 58 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 236/0 | 2026-01-28 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 139/3 | 2026-01-29 | 2026-01 | 1 | 2026-06-04 | 2026-06 | 6 | 126 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 168/0 | 2026-01-29 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 188/0 | 2026-01-29 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 227/1 | 2026-01-29 | 2026-01 | 1 | 2026-03-27 | 2026-03 | 3 | 57 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 139/2 | 2026-01-30 | 2026-01 | 1 | 2026-02-08 | 2026-02 | 2 | 9 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 209/2 | 2026-01-30 | 2026-01 | 1 | 2026-03-03 | 2026-03 | 3 | 32 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 235/2 | 2026-01-30 | 2026-01 | 1 | 2026-04-05 | 2026-04 | 4 | 65 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 133/2 | 2026-01-31 | 2026-01 | 1 | 2026-02-28 | 2026-02 | 2 | 28 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 211/5 | 2026-01-31 | 2026-01 | 1 | 2026-04-05 | 2026-04 | 4 | 64 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 211/0 | 2026-02-01 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 238/0 | 2026-02-01 | 2026-02 | 2 | 2026-06-18 | 2026-06 | 6 | 137 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 174/2 | 2026-02-02 | 2026-02 | 2 | 2026-03-11 | 2026-03 | 3 | 37 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 250/1 | 2026-02-02 | 2026-02 | 2 | 2026-06-08 | 2026-06 | 6 | 126 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 252/4 | 2026-02-02 | 2026-02 | 2 | 2026-03-24 | 2026-03 | 3 | 50 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 240/0 | 2026-02-03 | 2026-02 | 2 | 2026-02-26 | 2026-02 | 2 | 23 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 124/3 | 2026-02-05 | 2026-02 | 2 | 2026-04-28 | 2026-04 | 4 | 82 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 213/0 | 2026-02-05 | 2026-02 | 2 | 2026-05-31 | 2026-05 | 5 | 115 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 235/0 | 2026-02-07 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 256/1 | 2026-02-07 | 2026-02 | 2 | 2026-06-15 | 2026-06 | 6 | 128 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 228/0 | 2026-02-10 | 2026-02 | 2 | 2026-05-11 | 2026-05 | 5 | 90 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 134/0 | 2026-02-11 | 2026-02 | 2 | 2026-03-13 | 2026-03 | 3 | 30 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 124/2 | 2026-02-12 | 2026-02 | 2 | 2026-05-22 | 2026-05 | 5 | 99 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 235/3 | 2026-02-13 | 2026-02 | 2 | 2026-03-19 | 2026-03 | 3 | 34 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 242/0 | 2026-02-13 | 2026-02 | 2 | 2026-04-09 | 2026-04 | 4 | 55 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 214/0 | 2026-02-16 | 2026-02 | 2 | 2026-04-29 | 2026-04 | 4 | 72 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 217/1 | 2026-02-16 | 2026-02 | 2 | 2026-06-10 | 2026-06 | 6 | 114 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 237/0 | 2026-02-16 | 2026-02 | 2 | 2026-05-03 | 2026-05 | 5 | 76 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 147/0 | 2026-02-17 | 2026-02 | 2 | 2026-04-07 | 2026-04 | 4 | 49 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 228/1 | 2026-02-17 | 2026-02 | 2 | 2026-03-12 | 2026-03 | 3 | 23 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 174/0 | 2026-02-18 | 2026-02 | 2 | 2026-05-03 | 2026-05 | 5 | 74 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 235/1 | 2026-02-19 | 2026-02 | 2 | 2026-06-05 | 2026-06 | 6 | 106 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 232/4 | 2026-02-20 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 240/1 | 2026-02-22 | 2026-02 | 2 | 2026-03-12 | 2026-03 | 3 | 18 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 133/4 | 2026-02-23 | 2026-02 | 2 | 2026-04-03 | 2026-04 | 4 | 39 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 214/1 | 2026-02-23 | 2026-02 | 2 | 2026-04-09 | 2026-04 | 4 | 45 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 217/0 | 2026-02-24 | 2026-02 | 2 | 2026-06-02 | 2026-06 | 6 | 98 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 173/0 | 2026-02-27 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 248/0 | 2026-02-27 | 2026-02 | 2 | 2026-06-16 | 2026-06 | 6 | 109 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 219/0 | 2026-02-28 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 239/0 | 2026-03-02 | 2026-03 | 3 | 2026-03-25 | 2026-03 | 3 | 23 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 209/0 | 2026-03-03 | 2026-03 | 3 | 2026-03-11 | 2026-03 | 3 | 8 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 209/1 | 2026-03-03 | 2026-03 | 3 | 2026-03-18 | 2026-03 | 3 | 15 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 163/0 | 2026-03-04 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 226/1 | 2026-03-08 | 2026-03 | 3 | 2026-05-06 | 2026-05 | 5 | 59 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 226/2 | 2026-03-09 | 2026-03 | 3 | 2026-03-31 | 2026-03 | 3 | 22 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 232/0 | 2026-03-11 | 2026-03 | 3 | 2026-05-21 | 2026-05 | 5 | 71 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 239/1 | 2026-03-12 | 2026-03 | 3 | 2026-04-05 | 2026-04 | 4 | 24 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 133/3 | 2026-03-15 | 2026-03 | 3 | 2026-03-25 | 2026-03 | 3 | 10 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 207/0 | 2026-03-15 | 2026-03 | 3 | 2026-04-02 | 2026-04 | 4 | 18 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 227/2 | 2026-03-16 | 2026-03 | 3 | 2026-04-08 | 2026-04 | 4 | 23 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 231/0 | 2026-03-16 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 145/0 | 2026-03-18 | 2026-03 | 3 | 2026-03-29 | 2026-03 | 3 | 11 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 225/7 | 2026-03-22 | 2026-03 | 3 | 2026-05-11 | 2026-05 | 5 | 50 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 251/1 | 2026-03-22 | 2026-03 | 3 | 2026-04-17 | 2026-04 | 4 | 26 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/11 | 2026-03-24 | 2026-03 | 3 | 2026-04-01 | 2026-04 | 4 | 8 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 150/1 | 2026-03-24 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 225/5 | 2026-03-24 | 2026-03 | 3 | 2026-05-11 | 2026-05 | 5 | 48 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 234/0 | 2026-03-24 | 2026-03 | 3 | 2026-05-12 | 2026-05 | 5 | 49 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 179/2 | 2026-03-27 | 2026-03 | 3 | 2026-03-27 | 2026-03 | 3 | 0 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 226/0 | 2026-03-28 | 2026-03 | 3 | 2026-04-20 | 2026-04 | 4 | 23 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 230/1 | 2026-03-29 | 2026-03 | 3 | 2026-06-22 | 2026-06 | 6 | 85 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 255/1 | 2026-03-29 | 2026-03 | 3 | 2026-05-09 | 2026-05 | 5 | 41 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 232/2 | 2026-03-31 | 2026-03 | 3 | 2026-06-05 | 2026-06 | 6 | 66 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 180/0 | 2026-04-05 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 156/0 | 2026-04-06 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 150/0 | 2026-04-12 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 195/0 | 2026-04-12 | 2026-04 | 4 | 2026-06-20 | 2026-06 | 6 | 69 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 131/0 | 2026-04-16 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 155/0 | 2026-04-18 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 230A/0 | 2026-04-18 | 2026-04 | 4 | 2026-06-01 | 2026-06 | 6 | 44 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 200/0 | 2026-04-19 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 131/1 | 2026-04-21 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 151/0 | 2026-04-21 | 2026-04 | 4 | 2026-05-19 | 2026-05 | 5 | 28 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 156/1 | 2026-04-24 | 2026-04 | 4 | 2026-05-20 | 2026-05 | 5 | 26 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 153/1 | 2026-04-26 | 2026-04 | 4 | 2026-06-08 | 2026-06 | 6 | 43 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 159/0 | 2026-04-28 | 2026-04 | 4 | 2026-05-27 | 2026-05 | 5 | 29 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 189/0 | 2026-04-28 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 151A/0 | 2026-05-01 | 2026-05 | 5 | 2026-06-06 | 2026-06 | 6 | 36 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 164/0 | 2026-05-03 | 2026-05 | 5 | 2026-06-22 | 2026-06 | 6 | 50 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 235/4 | 2026-05-05 | 2026-05 | 5 | 2026-06-05 | 2026-06 | 6 | 31 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 169/0 | 2026-05-06 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 165/0 | 2026-05-09 | 2026-05 | 5 | 2026-06-17 | 2026-06 | 6 | 39 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 232/3 | 2026-05-09 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 129/0 | 2026-05-11 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 206/0 | 2026-05-11 | 2026-05 | 5 | 2026-06-12 | 2026-06 | 6 | 32 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 145/1 | 2026-05-16 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 206/1 | 2026-05-17 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 153A/0 | 2026-05-20 | 2026-05 | 5 | 2026-06-08 | 2026-06 | 6 | 19 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 201/0 | 2026-05-20 | 2026-05 | 5 | 2026-06-26 | 2026-06 | 6 | 37 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 229B/0 | 2026-05-22 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 229A/0 | 2026-05-28 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 229/0 | 2026-05-31 | 2026-05 | 5 | 2026-06-15 | 2026-06 | 6 | 15 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 154/0 | 2026-06-01 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 212/0 | 2026-06-01 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 254/0 | 2026-06-06 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 132/2 | 2026-06-07 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 208/0 | 2026-06-08 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 225/6 | 2026-06-08 | 2026-06 | 6 | 2026-06-18 | 2026-06 | 6 | 10 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 130/0 | 2026-06-12 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 152/0 | 2026-06-12 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 253/0 | 2026-06-15 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 165/3 | 2026-06-17 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 229/1 | 2026-06-19 | 2026-06 | 6 | 2026-06-26 | 2026-06 | 6 | 7 | Yes | No | exact |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN | TA 414 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 165/1 | 2026-06-21 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 202/0 | 2026-06-21 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 135/0 | 2026-06-22 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 153/2 | 2026-06-26 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 200/1 | 2026-06-26 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 414 - DPR - 2026-08-12.xlsx | FDN
TA 416 | 4xx | Government | ta416 | 2/8 | 2024-05-06 | 2024-05 | 5 | 2024-09-01 | 2024-09 | 9 | 118 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 2/7 | 2024-05-10 | 2024-05 | 5 | 2024-11-26 | 2024-11 | 11 | 200 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 2/6 | 2024-05-14 | 2024-05 | 5 | 2024-12-01 | 2024-12 | 12 | 201 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 2/5 | 2024-05-18 | 2024-05 | 5 | 2024-11-10 | 2024-11 | 11 | 176 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 2/4 | 2024-05-21 | 2024-05 | 5 | 2024-09-16 | 2024-09 | 9 | 118 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 2/3 | 2024-05-28 | 2024-05 | 5 | 2024-12-10 | 2024-12 | 12 | 196 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/4 | 2024-06-03 | 2024-06 | 6 | 2025-01-01 | 2025-01 | 1 | 212 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/10 | 2024-06-04 | 2024-06 | 6 | 2024-09-16 | 2024-09 | 9 | 104 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/5 | 2024-06-06 | 2024-06 | 6 | 2025-01-24 | 2025-01 | 1 | 232 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/8 | 2024-06-08 | 2024-06 | 6 | 2024-10-03 | 2024-10 | 10 | 117 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/3 | 2024-06-09 | 2024-06 | 6 | 2025-01-10 | 2025-01 | 1 | 215 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/6 | 2024-06-11 | 2024-06 | 6 | 2025-09-15 | 2025-09 | 9 | 461 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 6/2 | 2024-06-12 | 2024-06 | 6 | 2024-11-14 | 2024-11 | 11 | 155 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/9 | 2024-06-13 | 2024-06 | 6 | 2024-10-24 | 2024-10 | 10 | 133 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/7 | 2024-06-14 | 2024-06 | 6 | 2025-01-30 | 2025-01 | 1 | 230 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/8 | 2024-06-17 | 2024-06 | 6 | 2025-05-11 | 2025-05 | 5 | 328 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/7 | 2024-06-19 | 2024-06 | 6 | 2024-10-15 | 2024-10 | 10 | 118 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/1 | 2024-06-20 | 2024-06 | 6 | 2024-12-24 | 2024-12 | 12 | 187 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/6 | 2024-06-22 | 2024-06 | 6 | 2024-10-08 | 2024-10 | 10 | 108 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/1 | 2024-06-23 | 2024-06 | 6 | 2025-04-01 | 2025-04 | 4 | 282 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/6 | 2024-06-25 | 2024-06 | 6 | 2024-11-01 | 2024-11 | 11 | 129 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/7 | 2024-06-27 | 2024-06 | 6 | 2024-10-24 | 2024-10 | 10 | 119 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/11 | 2024-06-30 | 2024-06 | 6 | 2025-05-12 | 2025-05 | 5 | 316 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/1 | 2024-07-11 | 2024-07 | 7 | 2025-01-07 | 2025-01 | 1 | 180 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/12 | 2024-07-15 | 2024-07 | 7 | 2024-11-01 | 2024-11 | 11 | 109 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/2 | 2024-07-18 | 2024-07 | 7 | 2024-12-06 | 2024-12 | 12 | 141 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/5 | 2024-07-20 | 2024-07 | 7 | 2024-11-10 | 2024-11 | 11 | 113 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/11 | 2024-07-23 | 2024-07 | 7 | 2025-04-27 | 2025-04 | 4 | 278 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/3 | 2024-07-25 | 2024-07 | 7 | 2024-11-10 | 2024-11 | 11 | 108 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/6 | 2024-07-28 | 2024-07 | 7 | 2024-11-05 | 2024-11 | 11 | 100 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/8 | 2024-07-29 | 2024-07 | 7 | 2024-10-01 | 2024-10 | 10 | 64 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/8 | 2024-07-30 | 2024-07 | 7 | 2025-05-06 | 2025-05 | 5 | 280 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/4 | 2024-07-31 | 2024-07 | 7 | 2024-12-20 | 2024-12 | 12 | 142 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/9 | 2024-08-03 | 2024-08 | 8 | 2024-10-14 | 2024-10 | 10 | 72 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/9 | 2024-08-04 | 2024-08 | 8 | 2025-01-16 | 2025-01 | 1 | 165 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/12 | 2024-08-08 | 2024-08 | 8 | 2024-11-29 | 2024-11 | 11 | 113 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/4 | 2024-08-09 | 2024-08 | 8 | 2024-11-17 | 2024-11 | 11 | 100 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/5 | 2024-08-10 | 2024-08 | 8 | 2024-10-20 | 2024-10 | 10 | 71 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/11 | 2024-08-14 | 2024-08 | 8 | 2025-05-14 | 2025-05 | 5 | 273 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 23/3 | 2024-08-18 | 2024-08 | 8 | 2025-05-15 | 2025-05 | 5 | 270 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/3 | 2024-08-21 | 2024-08 | 8 | 2024-12-06 | 2024-12 | 12 | 107 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/12 | 2024-08-24 | 2024-08 | 8 | 2025-04-23 | 2025-04 | 4 | 242 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/7 | 2024-08-30 | 2024-08 | 8 | 2024-11-29 | 2024-11 | 11 | 91 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/9 | 2024-08-31 | 2024-08 | 8 | 2025-02-02 | 2025-02 | 2 | 155 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 23/4 | 2024-08-31 | 2024-08 | 8 | 2025-05-23 | 2025-05 | 5 | 265 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/3 | 2024-08-31 | 2024-08 | 8 | 2025-01-07 | 2025-01 | 1 | 129 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/3 | 2024-09-05 | 2024-09 | 9 | 2024-11-10 | 2024-11 | 11 | 66 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/4 | 2024-09-08 | 2024-09 | 9 | 2025-01-21 | 2025-01 | 1 | 135 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/8 | 2024-09-08 | 2024-09 | 9 | 2025-03-21 | 2025-03 | 3 | 194 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/4 | 2024-09-08 | 2024-09 | 9 | 2025-04-29 | 2025-04 | 4 | 233 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 45/3 | 2024-09-08 | 2024-09 | 9 | 2024-12-10 | 2024-12 | 12 | 93 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/8 | 2024-09-09 | 2024-09 | 9 | 2025-05-26 | 2025-05 | 5 | 259 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/7 | 2024-09-09 | 2024-09 | 9 | 2025-04-23 | 2025-04 | 4 | 226 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 23/5 | 2024-09-11 | 2024-09 | 9 | 2025-05-10 | 2025-05 | 5 | 241 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 50/1 | 2024-09-11 | 2024-09 | 9 | 2025-06-08 | 2025-06 | 6 | 270 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 23/2 | 2024-09-20 | 2024-09 | 9 | 2025-06-04 | 2025-06 | 6 | 257 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/6 | 2024-09-20 | 2024-09 | 9 | 2025-04-12 | 2025-04 | 4 | 204 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 41/1 | 2024-09-20 | 2024-09 | 9 | 2024-11-10 | 2024-11 | 11 | 51 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/2 | 2024-09-22 | 2024-09 | 9 | 2024-11-28 | 2024-11 | 11 | 67 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/1 | 2024-09-22 | 2024-09 | 9 | 2025-04-16 | 2025-04 | 4 | 206 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 30/3 | 2024-09-22 | 2024-09 | 9 | 2025-04-30 | 2025-04 | 4 | 220 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/2 | 2024-09-24 | 2024-09 | 9 | 2025-01-03 | 2025-01 | 1 | 101 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 30/6 | 2024-09-24 | 2024-09 | 9 | 2025-04-22 | 2025-04 | 4 | 210 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/9 | 2024-09-24 | 2024-09 | 9 | 2025-05-20 | 2025-05 | 5 | 238 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 25/1 | 2024-09-26 | 2024-09 | 9 | 2025-07-01 | 2025-07 | 7 | 278 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/2 | 2024-09-26 | 2024-09 | 9 | 2025-03-20 | 2025-03 | 3 | 175 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/5 | 2024-09-26 | 2024-09 | 9 | 2025-01-15 | 2025-01 | 1 | 111 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 41/2 | 2024-09-26 | 2024-09 | 9 | 2024-11-30 | 2024-11 | 11 | 65 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 45/2 | 2024-09-29 | 2024-09 | 9 | 2024-12-21 | 2024-12 | 12 | 83 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/1 | 2024-09-30 | 2024-09 | 9 | 2025-05-04 | 2025-05 | 5 | 216 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/6 | 2024-09-30 | 2024-09 | 9 | 2025-05-11 | 2025-05 | 5 | 223 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/1 | 2024-09-30 | 2024-09 | 9 | 2024-12-13 | 2024-12 | 12 | 74 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 23/1 | 2024-09-30 | 2024-09 | 9 | 2025-05-28 | 2025-05 | 5 | 240 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 30/4 | 2024-09-30 | 2024-09 | 9 | 2025-03-01 | 2025-03 | 3 | 152 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/10 | 2024-09-30 | 2024-09 | 9 | 2025-05-25 | 2025-05 | 5 | 237 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/1 | 2024-10-01 | 2024-10 | 10 | 2025-01-16 | 2025-01 | 1 | 107 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/3 | 2024-10-01 | 2024-10 | 10 | 2025-02-28 | 2025-02 | 2 | 150 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 34/7 | 2024-10-03 | 2024-10 | 10 | 2025-02-12 | 2025-02 | 2 | 132 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 46/2 | 2024-10-03 | 2024-10 | 10 | 2025-08-14 | 2025-08 | 8 | 315 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 25/2 | 2024-10-04 | 2024-10 | 10 | 2025-04-15 | 2025-04 | 4 | 193 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/7 | 2024-10-06 | 2024-10 | 10 | 2025-06-24 | 2025-06 | 6 | 261 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/8 | 2024-10-06 | 2024-10 | 10 | 2025-04-29 | 2025-04 | 4 | 205 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/3 | 2024-10-07 | 2024-10 | 10 | 2025-01-12 | 2025-01 | 1 | 97 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 30/2 | 2024-10-07 | 2024-10 | 10 | 2025-05-14 | 2025-05 | 5 | 219 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/2 | 2024-10-07 | 2024-10 | 10 | 2025-01-11 | 2025-01 | 1 | 96 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 25/3 | 2024-10-08 | 2024-10 | 10 | 2025-04-30 | 2025-04 | 4 | 204 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 34/6 | 2024-10-08 | 2024-10 | 10 | 2025-02-21 | 2025-02 | 2 | 136 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/5 | 2024-10-08 | 2024-10 | 10 | 2025-05-05 | 2025-05 | 5 | 209 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/1 | 2024-10-10 | 2024-10 | 10 | 2025-01-25 | 2025-01 | 1 | 107 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 34/3 | 2024-10-10 | 2024-10 | 10 | 2025-04-29 | 2025-04 | 4 | 201 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 34/4 | 2024-10-10 | 2024-10 | 10 | 2025-04-03 | 2025-04 | 4 | 175 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/9 | 2024-10-10 | 2024-10 | 10 | 2025-02-08 | 2025-02 | 2 | 121 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 46/1 | 2024-10-10 | 2024-10 | 10 | 2024-12-28 | 2024-12 | 12 | 79 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/5 | 2024-10-13 | 2024-10 | 10 | 2025-01-25 | 2025-01 | 1 | 104 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 34/2 | 2024-10-13 | 2024-10 | 10 | 2025-04-23 | 2025-04 | 4 | 192 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 30/1 | 2024-10-14 | 2024-10 | 10 | 2025-05-07 | 2025-05 | 5 | 205 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/8 | 2024-10-14 | 2024-10 | 10 | 2025-03-16 | 2025-03 | 3 | 153 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/2 | 2024-10-14 | 2024-10 | 10 | 2024-12-12 | 2024-12 | 12 | 59 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 30/5 | 2024-10-16 | 2024-10 | 10 | 2025-03-10 | 2025-03 | 3 | 145 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/1 | 2024-10-16 | 2024-10 | 10 | 2025-03-12 | 2025-03 | 3 | 147 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/2 | 2024-10-16 | 2024-10 | 10 | 2025-02-02 | 2025-02 | 2 | 109 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/10 | 2024-10-18 | 2024-10 | 10 | 2025-03-24 | 2025-03 | 3 | 157 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/11 | 2024-10-18 | 2024-10 | 10 | 2025-02-02 | 2025-02 | 2 | 107 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/2 | 2024-10-20 | 2024-10 | 10 | 2024-12-12 | 2024-12 | 12 | 53 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/3 | 2024-10-20 | 2024-10 | 10 | 2024-12-24 | 2024-12 | 12 | 65 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/2 | 2024-10-20 | 2024-10 | 10 | 2025-03-19 | 2025-03 | 3 | 150 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/2 | 2024-10-21 | 2024-10 | 10 | 2025-02-07 | 2025-02 | 2 | 109 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 34/1 | 2024-10-21 | 2024-10 | 10 | 2025-03-01 | 2025-03 | 3 | 131 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/8 | 2024-10-21 | 2024-10 | 10 | 2025-03-22 | 2025-03 | 3 | 152 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/9 | 2024-10-22 | 2024-10 | 10 | 2025-05-13 | 2025-05 | 5 | 203 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/10 | 2024-10-23 | 2024-10 | 10 | 2025-01-21 | 2025-01 | 1 | 90 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/3 | 2024-10-23 | 2024-10 | 10 | 2024-11-28 | 2024-11 | 11 | 36 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/1 | 2024-10-24 | 2024-10 | 10 | 2024-12-18 | 2024-12 | 12 | 55 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 28/1 | 2024-10-24 | 2024-10 | 10 | 2025-06-24 | 2025-06 | 6 | 243 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/9 | 2024-10-24 | 2024-10 | 10 | 2025-02-11 | 2025-02 | 2 | 110 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/5 | 2024-10-24 | 2024-10 | 10 | 2025-06-02 | 2025-06 | 6 | 221 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/1 | 2024-10-24 | 2024-10 | 10 | 2025-01-25 | 2025-01 | 1 | 93 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/5 | 2024-10-25 | 2024-10 | 10 | 2025-04-12 | 2025-04 | 4 | 169 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/10 | 2024-10-25 | 2024-10 | 10 | 2024-12-18 | 2024-12 | 12 | 54 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/3 | 2024-10-26 | 2024-10 | 10 | 2025-02-26 | 2025-02 | 2 | 123 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/9 | 2024-10-26 | 2024-10 | 10 | 2025-02-14 | 2025-02 | 2 | 111 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/7 | 2024-10-26 | 2024-10 | 10 | 2025-02-16 | 2025-02 | 2 | 113 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8B/3 | 2024-10-26 | 2024-10 | 10 | 2025-03-28 | 2025-03 | 3 | 153 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/4 | 2024-10-27 | 2024-10 | 10 | 2024-12-06 | 2024-12 | 12 | 40 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/11 | 2024-10-27 | 2024-10 | 10 | 2025-03-01 | 2025-03 | 3 | 125 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/8 | 2024-11-01 | 2024-11 | 11 | 2024-11-22 | 2024-11 | 11 | 21 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/4 | 2024-11-01 | 2024-11 | 11 | 2025-02-20 | 2025-02 | 2 | 111 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/6 | 2024-11-01 | 2024-11 | 11 | 2025-01-20 | 2025-01 | 1 | 80 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/7 | 2024-11-01 | 2024-11 | 11 | 2025-02-03 | 2025-02 | 2 | 94 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/10 | 2024-11-01 | 2024-11 | 11 | 2025-05-16 | 2025-05 | 5 | 196 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/4 | 2024-11-02 | 2024-11 | 11 | 2025-03-08 | 2025-03 | 3 | 126 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/5 | 2024-11-02 | 2024-11 | 11 | 2025-02-27 | 2025-02 | 2 | 117 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8B/1 | 2024-11-05 | 2024-11 | 11 | 2025-03-22 | 2025-03 | 3 | 137 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/6 | 2024-11-08 | 2024-11 | 11 | 2025-02-14 | 2025-02 | 2 | 98 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/4 | 2024-11-09 | 2024-11 | 11 | 2025-01-04 | 2025-01 | 1 | 56 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 34/0 | 2024-11-09 | 2024-11 | 11 | 2025-03-24 | 2025-03 | 3 | 135 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/2 | 2024-11-10 | 2024-11 | 11 | 2025-01-17 | 2025-01 | 1 | 68 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/4 | 2024-11-10 | 2024-11 | 11 | 2025-02-20 | 2025-02 | 2 | 102 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/4 | 2024-11-11 | 2024-11 | 11 | 2024-12-06 | 2024-12 | 12 | 25 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/8 | 2024-11-11 | 2024-11 | 11 | 2025-03-03 | 2025-03 | 3 | 112 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/9 | 2024-11-11 | 2024-11 | 11 | 2024-12-24 | 2024-12 | 12 | 43 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/7 | 2024-11-13 | 2024-11 | 11 | 2025-01-09 | 2025-01 | 1 | 57 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/0 | 2024-11-13 | 2024-11 | 11 | 2025-01-28 | 2025-01 | 1 | 76 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/3 | 2024-11-13 | 2024-11 | 11 | 2025-02-12 | 2025-02 | 2 | 91 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8B/2 | 2024-11-13 | 2024-11 | 11 | 2025-04-08 | 2025-04 | 4 | 146 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/7 | 2024-11-15 | 2024-11 | 11 | 2025-02-21 | 2025-02 | 2 | 98 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/8 | 2024-11-15 | 2024-11 | 11 | 2025-01-08 | 2025-01 | 1 | 54 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 32/0 | 2024-11-16 | 2024-11 | 11 | 2025-04-01 | 2025-04 | 4 | 136 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 10/1 | 2024-11-18 | 2024-11 | 11 | 2025-04-12 | 2025-04 | 4 | 145 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/5 | 2024-11-18 | 2024-11 | 11 | 2024-12-22 | 2024-12 | 12 | 34 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/3 | 2024-11-20 | 2024-11 | 11 | 2025-03-24 | 2025-03 | 3 | 124 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/6 | 2024-11-21 | 2024-11 | 11 | 2024-12-28 | 2024-12 | 12 | 37 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/0 | 2024-11-21 | 2024-11 | 11 | 2025-04-12 | 2025-04 | 4 | 142 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/4 | 2024-11-21 | 2024-11 | 11 | 2025-05-07 | 2025-05 | 5 | 167 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/8 | 2024-11-21 | 2024-11 | 11 | 2024-12-17 | 2024-12 | 12 | 26 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8B/4 | 2024-11-21 | 2024-11 | 11 | 2025-04-14 | 2025-04 | 4 | 144 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 21/0 | 2024-11-22 | 2024-11 | 11 | 2025-02-06 | 2025-02 | 2 | 76 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8/3 | 2024-11-22 | 2024-11 | 11 | 2025-03-08 | 2025-03 | 3 | 106 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 54/1 | 2024-11-23 | 2024-11 | 11 | 2025-08-18 | 2025-08 | 8 | 268 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/11 | 2024-11-24 | 2024-11 | 11 | 2025-03-31 | 2025-03 | 3 | 127 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/2 | 2024-11-26 | 2024-11 | 11 | 2025-04-20 | 2025-04 | 4 | 145 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/3 | 2024-11-26 | 2024-11 | 11 | 2025-03-20 | 2025-03 | 3 | 114 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/0 | 2024-11-27 | 2024-11 | 11 | 2025-04-02 | 2025-04 | 4 | 126 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8/4 | 2024-11-27 | 2024-11 | 11 | 2025-03-13 | 2025-03 | 3 | 106 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/0 | 2024-11-29 | 2024-11 | 11 | 2025-02-19 | 2025-02 | 2 | 82 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/0 | 2024-11-29 | 2024-11 | 11 | 2025-01-29 | 2025-01 | 1 | 61 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/6 | 2024-11-29 | 2024-11 | 11 | 2025-04-01 | 2025-04 | 4 | 123 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/7 | 2024-11-29 | 2024-11 | 11 | 2024-12-24 | 2024-12 | 12 | 25 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/2 | 2024-11-29 | 2024-11 | 11 | 2024-12-31 | 2024-12 | 12 | 32 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8B/5 | 2024-11-29 | 2024-11 | 11 | 2025-03-24 | 2025-03 | 3 | 115 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 10/0 | 2024-11-30 | 2024-11 | 11 | 2025-04-17 | 2025-04 | 4 | 138 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 54/2 | 2024-12-01 | 2024-12 | 12 | 2025-10-08 | 2025-10 | 10 | 311 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/0 | 2024-12-02 | 2024-12 | 12 | 2025-04-12 | 2025-04 | 4 | 131 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8/2 | 2024-12-03 | 2024-12 | 12 | 2025-02-16 | 2025-02 | 2 | 75 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 26/0 | 2024-12-04 | 2024-12 | 12 | 2025-09-15 | 2025-09 | 9 | 285 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/1 | 2024-12-04 | 2024-12 | 12 | 2025-02-19 | 2025-02 | 2 | 77 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/5 | 2024-12-06 | 2024-12 | 12 | 2024-12-28 | 2024-12 | 12 | 22 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/0 | 2024-12-09 | 2024-12 | 12 | 2025-09-11 | 2025-09 | 9 | 276 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 5/1 | 2024-12-09 | 2024-12 | 12 | 2025-03-16 | 2025-03 | 3 | 97 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/4 | 2024-12-09 | 2024-12 | 12 | 2025-02-10 | 2025-02 | 2 | 63 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/7 | 2024-12-09 | 2024-12 | 12 | 2025-01-15 | 2025-01 | 1 | 37 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8/1 | 2024-12-09 | 2024-12 | 12 | 2025-02-09 | 2025-02 | 2 | 62 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 3/0 | 2024-12-10 | 2024-12 | 12 | 2025-06-12 | 2025-06 | 6 | 184 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/5 | 2024-12-10 | 2024-12 | 12 | 2025-05-30 | 2025-05 | 5 | 171 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/10 | 2024-12-11 | 2024-12 | 12 | 2025-05-20 | 2025-05 | 5 | 160 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 55/1 | 2024-12-11 | 2024-12 | 12 | 2025-11-09 | 2025-11 | 11 | 333 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/5 | 2024-12-13 | 2024-12 | 12 | 2025-01-29 | 2025-01 | 1 | 47 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 49/0 | 2024-12-15 | 2024-12 | 12 | 2025-11-06 | 2025-11 | 11 | 326 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/9 | 2024-12-16 | 2024-12 | 12 | 2025-05-04 | 2025-05 | 5 | 139 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 6/1 | 2024-12-16 | 2024-12 | 12 | 2025-03-09 | 2025-03 | 3 | 83 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/6 | 2024-12-16 | 2024-12 | 12 | 2025-01-21 | 2025-01 | 1 | 36 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/7 | 2024-12-17 | 2024-12 | 12 | 2025-04-12 | 2025-04 | 4 | 116 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/0 | 2024-12-17 | 2024-12 | 12 | 2025-04-06 | 2025-04 | 4 | 110 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/8 | 2024-12-17 | 2024-12 | 12 | 2025-08-18 | 2025-08 | 8 | 244 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/7 | 2024-12-18 | 2024-12 | 12 | 2025-12-06 | 2025-12 | 12 | 353 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 48/1 | 2024-12-20 | 2024-12 | 12 | 2025-09-15 | 2025-09 | 9 | 269 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/0 | 2024-12-20 | 2024-12 | 12 | 2025-02-27 | 2025-02 | 2 | 69 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8/0 | 2024-12-20 | 2024-12 | 12 | 2025-02-22 | 2025-02 | 2 | 64 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 47/0 | 2024-12-21 | 2024-12 | 12 | 2025-09-07 | 2025-09 | 9 | 260 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/1 | 2024-12-22 | 2024-12 | 12 | 2025-05-14 | 2025-05 | 5 | 143 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/10 | 2024-12-24 | 2024-12 | 12 | 2025-03-01 | 2025-03 | 3 | 67 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 9/0 | 2024-12-24 | 2024-12 | 12 | 2025-04-01 | 2025-04 | 4 | 98 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/8 | 2024-12-27 | 2024-12 | 12 | 2025-05-22 | 2025-05 | 5 | 146 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/7 | 2024-12-27 | 2024-12 | 12 | 2026-02-09 | 2026-02 | 2 | 409 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 6/0 | 2024-12-27 | 2024-12 | 12 | 2025-03-22 | 2025-03 | 3 | 85 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 46/0 | 2024-12-28 | 2024-12 | 12 | 2025-09-25 | 2025-09 | 9 | 271 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/6 | 2024-12-31 | 2024-12 | 12 | 2025-03-28 | 2025-03 | 3 | 87 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 54/0 | 2024-12-31 | 2024-12 | 12 | 2025-09-25 | 2025-09 | 9 | 268 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53A/5 | 2025-01-02 | 2025-01 | 1 | 2025-06-02 | 2025-06 | 6 | 151 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 64/1 | 2025-01-02 | 2025-01 | 1 | 2025-11-06 | 2025-11 | 11 | 308 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 15/0 | 2025-01-03 | 2025-01 | 1 | 2025-05-16 | 2025-05 | 5 | 133 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/9 | 2025-01-03 | 2025-01 | 1 | 2025-04-23 | 2025-04 | 4 | 110 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53A/7 | 2025-01-07 | 2025-01 | 1 | 2025-12-08 | 2025-12 | 12 | 335 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 5/0 | 2025-01-09 | 2025-01 | 1 | 2025-03-01 | 2025-03 | 3 | 51 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8A/0 | 2025-01-09 | 2025-01 | 1 | 2025-04-22 | 2025-04 | 4 | 103 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53A/0 | 2025-01-10 | 2025-01 | 1 | 2025-11-15 | 2025-11 | 11 | 309 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 70/0 | 2025-01-10 | 2025-01 | 1 | 2025-12-20 | 2025-12 | 12 | 344 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/0 | 2025-01-11 | 2025-01 | 1 | 2025-09-05 | 2025-09 | 9 | 237 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53A/4 | 2025-01-11 | 2025-01 | 1 | 2025-04-01 | 2025-04 | 4 | 80 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/0 | 2025-01-11 | 2025-01 | 1 | 2025-06-28 | 2025-06 | 6 | 168 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 64/2 | 2025-01-11 | 2025-01 | 1 | 2026-01-20 | 2026-01 | 1 | 374 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 28/0 | 2025-01-12 | 2025-01 | 1 | 2025-07-08 | 2025-07 | 7 | 177 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 48/0 | 2025-01-12 | 2025-01 | 1 | 2025-06-15 | 2025-06 | 6 | 154 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/10 | 2025-01-14 | 2025-01 | 1 | 2025-04-30 | 2025-04 | 4 | 106 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8B/0 | 2025-01-14 | 2025-01 | 1 | 2025-05-05 | 2025-05 | 5 | 111 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53/0 | 2025-01-15 | 2025-01 | 1 | 2025-09-26 | 2025-09 | 9 | 254 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 22A/0 | 2025-01-17 | 2025-01 | 1 | 2025-12-15 | 2025-12 | 12 | 332 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 57/0 | 2025-01-17 | 2025-01 | 1 | 2025-12-22 | 2025-12 | 12 | 339 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 58/0 | 2025-01-17 | 2025-01 | 1 | 2025-12-01 | 2025-12 | 12 | 318 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53A/2 | 2025-01-18 | 2025-01 | 1 | 2025-06-10 | 2025-06 | 6 | 143 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/10 | 2025-01-20 | 2025-01 | 1 | 2025-04-09 | 2025-04 | 4 | 79 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/3 | 2025-01-20 | 2025-01 | 1 | 2025-04-30 | 2025-04 | 4 | 100 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 55/0 | 2025-01-22 | 2025-01 | 1 | 2025-10-15 | 2025-10 | 10 | 266 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53A/6 | 2025-01-23 | 2025-01 | 1 | 2025-07-27 | 2025-07 | 7 | 185 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 51/0 | 2025-01-24 | 2025-01 | 1 | 2025-05-27 | 2025-05 | 5 | 123 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53A/3 | 2025-01-25 | 2025-01 | 1 | 2025-06-20 | 2025-06 | 6 | 146 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 27/0 | 2025-01-29 | 2025-01 | 1 | 2025-09-22 | 2025-09 | 9 | 236 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 45/1 | 2025-01-30 | 2025-01 | 1 | 2025-06-10 | 2025-06 | 6 | 131 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 0/2 | 2025-01-31 | 2025-01 | 1 | 2025-05-23 | 2025-05 | 5 | 112 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 0/3 | 2025-01-31 | 2025-01 | 1 | 2025-05-25 | 2025-05 | 5 | 114 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 21/3 | 2025-01-31 | 2025-01 | 1 | 2025-07-01 | 2025-07 | 7 | 151 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/6 | 2025-01-31 | 2025-01 | 1 | 2025-04-05 | 2025-04 | 4 | 64 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53/1 | 2025-02-03 | 2025-02 | 2 | 2025-05-12 | 2025-05 | 5 | 98 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 24/0 | 2025-02-04 | 2025-02 | 2 | 2025-07-26 | 2025-07 | 7 | 172 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 42/0 | 2025-02-05 | 2025-02 | 2 | 2025-09-23 | 2025-09 | 9 | 230 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/6 | 2025-02-06 | 2025-02 | 2 | 2025-03-10 | 2025-03 | 3 | 32 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 22/0 | 2025-02-07 | 2025-02 | 2 | 2025-06-12 | 2025-06 | 6 | 125 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/2 | 2025-02-07 | 2025-02 | 2 | 2025-05-07 | 2025-05 | 5 | 89 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 0/4 | 2025-02-09 | 2025-02 | 2 | 2025-04-12 | 2025-04 | 4 | 62 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 29/0 | 2025-02-09 | 2025-02 | 2 | 2025-08-06 | 2025-08 | 8 | 178 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/4 | 2025-02-10 | 2025-02 | 2 | 2025-04-26 | 2025-04 | 4 | 75 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 0/1 | 2025-02-15 | 2025-02 | 2 | 2025-06-04 | 2025-06 | 6 | 109 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 40/0 | 2025-02-15 | 2025-02 | 2 | 2025-06-04 | 2025-06 | 6 | 109 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/5 | 2025-02-15 | 2025-02 | 2 | 2025-04-17 | 2025-04 | 4 | 61 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 59/0 | 2025-02-15 | 2025-02 | 2 | 2025-11-16 | 2025-11 | 11 | 274 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 25/0 | 2025-02-18 | 2025-02 | 2 | 2025-08-28 | 2025-08 | 8 | 191 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 64/0 | 2025-02-18 | 2025-02 | 2 | 2025-08-31 | 2025-08 | 8 | 194 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 30/0 | 2025-02-21 | 2025-02 | 2 | 2025-05-25 | 2025-05 | 5 | 93 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 43/0 | 2025-02-21 | 2025-02 | 2 | 2025-08-10 | 2025-08 | 8 | 170 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/2 | 2025-02-21 | 2025-02 | 2 | 2025-05-07 | 2025-05 | 5 | 75 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/1 | 2025-02-22 | 2025-02 | 2 | 2025-03-31 | 2025-03 | 3 | 37 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/3 | 2025-02-23 | 2025-02 | 2 | 2025-05-20 | 2025-05 | 5 | 86 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 63/0 | 2025-02-27 | 2025-02 | 2 | 2025-10-01 | 2025-10 | 10 | 216 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 11/0 | 2025-02-28 | 2025-02 | 2 | 2025-08-24 | 2025-08 | 8 | 177 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 21/2 | 2025-02-28 | 2025-02 | 2 | 2025-06-21 | 2025-06 | 6 | 113 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53A/1 | 2025-02-28 | 2025-02 | 2 | 2025-09-18 | 2025-09 | 9 | 202 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 13/0 | 2025-03-03 | 2025-03 | 3 | 2025-07-09 | 2025-07 | 7 | 128 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 50/0 | 2025-03-04 | 2025-03 | 3 | 2025-09-25 | 2025-09 | 9 | 205 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 23/0 | 2025-03-08 | 2025-03 | 3 | 2025-11-17 | 2025-11 | 11 | 254 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 60/0 | 2025-03-08 | 2025-03 | 3 | 2025-11-08 | 2025-11 | 11 | 245 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/0 | 2025-03-09 | 2025-03 | 3 | 2025-06-01 | 2025-06 | 6 | 84 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 34/5 | 2025-03-09 | 2025-03 | 3 | 2025-06-12 | 2025-06 | 6 | 95 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/0 | 2025-03-10 | 2025-03 | 3 | 2025-08-12 | 2025-08 | 8 | 155 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/4 | 2025-03-11 | 2025-03 | 3 | 2025-05-23 | 2025-05 | 5 | 73 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 61/0 | 2025-03-20 | 2025-03 | 3 | 2025-09-25 | 2025-09 | 9 | 189 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 67/0 | 2025-03-20 | 2025-03 | 3 | 2026-02-09 | 2026-02 | 2 | 326 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/1 | 2025-03-22 | 2025-03 | 3 | 2025-10-27 | 2025-10 | 10 | 219 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 18/0 | 2025-03-25 | 2025-03 | 3 | 2025-08-04 | 2025-08 | 8 | 132 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 64/3 | 2025-03-26 | 2025-03 | 3 | 2025-09-24 | 2025-09 | 9 | 182 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 66/1 | 2025-03-26 | 2025-03 | 3 | 2025-11-27 | 2025-11 | 11 | 246 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 62/0 | 2025-03-27 | 2025-03 | 3 | 2025-11-10 | 2025-11 | 11 | 228 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/0 | 2025-03-30 | 2025-03 | 3 | 2025-08-31 | 2025-08 | 8 | 154 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/6 | 2025-04-02 | 2025-04 | 4 | 2025-11-01 | 2025-11 | 11 | 213 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 57/1 | 2025-04-02 | 2025-04 | 4 | 2025-12-07 | 2025-12 | 12 | 249 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 21/1 | 2025-04-03 | 2025-04 | 4 | 2025-06-27 | 2025-06 | 6 | 85 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 16/0 | 2025-04-10 | 2025-04 | 4 | 2025-08-16 | 2025-08 | 8 | 128 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 66/0 A,B | 2025-04-10 | 2025-04 | 4 | 2025-12-05 | 2025-12 | 12 | 239 | Yes | No | alias |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 66/0 C,D | 2025-04-10 | 2025-04 | 4 | 2025-12-05 | 2025-12 | 12 | 239 | Yes | No | alias |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 68/0 | 2025-04-17 | 2025-04 | 4 | 2025-11-30 | 2025-11 | 11 | 227 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 2/1 | 2025-04-21 | 2025-04 | 4 | 2025-05-12 | 2025-05 | 5 | 21 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 44/0 | 2025-04-21 | 2025-04 | 4 | 2025-07-05 | 2025-07 | 7 | 75 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 1/0 | 2025-04-27 | 2025-04 | 4 | 2025-08-09 | 2025-08 | 8 | 104 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 65/0 | 2025-04-28 | 2025-04 | 4 | 2025-08-02 | 2025-08 | 8 | 96 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 2/0 | 2025-04-29 | 2025-04 | 4 | 2025-09-03 | 2025-09 | 9 | 127 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 2/2 | 2025-04-30 | 2025-04 | 4 | 2025-11-01 | 2025-11 | 11 | 185 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/5 | 2025-05-11 | 2025-05 | 5 | 2025-05-28 | 2025-05 | 5 | 17 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 45/0 | 2025-05-11 | 2025-05 | 5 | 2025-10-09 | 2025-10 | 10 | 151 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 0/0 | 2025-05-17 | 2025-05 | 5 | 2025-10-03 | 2025-10 | 10 | 139 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 69/0 | 2025-05-19 | 2025-05 | 5 | 2026-01-20 | 2026-01 | 1 | 246 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 37/0 | 2025-05-23 | 2025-05 | 5 | 2025-09-23 | 2025-09 | 9 | 123 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 69A/0 | 2025-05-28 | 2025-05 | 5 | 2025-11-15 | 2025-11 | 11 | 171 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/0 | 2025-06-03 | 2025-06 | 6 | 2025-10-08 | 2025-10 | 10 | 127 | Yes | No | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/0-5/0 | 2025-10-14 | 2025-10 | 10 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 5/0-7/6 | 2025-10-22 | 2025-10 | 10 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 7/6-8B/0 | 2025-10-25 | 2025-10 | 10 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 34/0-35/0 | 2025-10-28 | 2025-10 | 10 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 35/0-36/0 | 2025-11-01 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 33/0-34/0 | 2025-11-04 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 31/0-33/0 | 2025-11-10 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 30/0-31/0 | 2025-11-16 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 12/0-14/0 | 2025-11-20 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 20/0-21/0 | 2025-11-30 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 19/0-20/0 | 2025-12-06 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 66/0 | 2025-12-19 | 2025-12 | 12 | 2025-12-05 | 2025-12 | 12 | -14 | Yes | Yes | exact |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 0/0-2/0 | 2026-02-06 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 2/0-3/0 | 2026-02-10 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 36/0-37/0 | 2026-02-10 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 14/0-17/0 | 2026-02-14 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 37/0-38/11 | 2026-02-16 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 8B/0-12/0 | 2026-02-18 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 38/11-40/0 | 2026-02-20 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 21/0-25/0 | 2026-02-23 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 17/0-19/0 | 2026-02-28 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 25/0-30/0 | 2026-02-28 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 40/0-47/0 | 2026-05-03 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 52/1-53/0 | 2026-05-06 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 53/0-54/0 | 2026-05-09 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 54/0-56/6 | 2026-06-29 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 56/6-64/0 | 2026-07-03 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 64/0-Gantry | 2026-07-08 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 52/1-64/0 | 2026-07-12 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 418 | 4xx | Government | ta418 | 33/10 | 2024-01-05 | 2024-01 | 1 | 2024-12-29 | 2024-12 | 12 | 359 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 40/4 | 2024-01-07 | 2024-01 | 1 | 2024-12-30 | 2024-12 | 12 | 358 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 42/1 | 2024-06-22 | 2024-06 | 6 | 2024-12-12 | 2024-12 | 12 | 173 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 42/2 | 2024-06-29 | 2024-06 | 6 | 2024-12-03 | 2024-12 | 12 | 157 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 54/4 | 2024-07-11 | 2024-07 | 7 | 2024-01-09 | 2024-01 | 1 | -184 | Yes | Yes | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 41/3 | 2024-07-12 | 2024-07 | 7 | 2024-12-06 | 2024-12 | 12 | 147 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 40/1 | 2024-07-16 | 2024-07 | 7 | 2024-11-26 | 2024-11 | 11 | 133 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 55/1 | 2024-07-16 | 2024-07 | 7 | 2025-01-16 | 2025-01 | 1 | 184 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 41/2 | 2024-07-23 | 2024-07 | 7 | 2025-02-12 | 2025-02 | 2 | 204 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 55/2 | 2024-07-23 | 2024-07 | 7 | 2025-01-25 | 2025-01 | 1 | 186 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 40/5 | 2024-07-26 | 2024-07 | 7 | 2025-05-29 | 2025-05 | 5 | 307 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 40/2 | 2024-07-31 | 2024-07 | 7 | 2024-12-02 | 2024-12 | 12 | 124 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 54/3 | 2024-08-02 | 2024-08 | 8 | 2025-02-12 | 2025-02 | 2 | 194 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 40/3 | 2024-08-03 | 2024-08 | 8 | 2025-04-02 | 2025-04 | 4 | 242 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/4 | 2024-08-06 | 2024-08 | 8 | 2024-11-19 | 2024-11 | 11 | 105 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 41/4 | 2024-08-10 | 2024-08 | 8 | 2024-12-12 | 2024-12 | 12 | 124 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 55/3 | 2024-08-10 | 2024-08 | 8 | 2025-01-24 | 2025-01 | 1 | 167 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/3 | 2024-08-11 | 2024-08 | 8 | 2025-05-30 | 2025-05 | 5 | 292 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/6 | 2024-08-21 | 2024-08 | 8 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 41/1 | 2024-08-26 | 2024-08 | 8 | 2025-02-06 | 2025-02 | 2 | 164 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/7 | 2024-08-27 | 2024-08 | 8 | 2024-12-19 | 2024-12 | 12 | 114 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/8 | 2024-09-03 | 2024-09 | 9 | 2025-01-31 | 2025-01 | 1 | 150 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 34/3 | 2024-09-08 | 2024-09 | 9 | 2024-11-14 | 2024-11 | 11 | 67 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/11 | 2024-09-10 | 2024-09 | 9 | 2024-12-19 | 2024-12 | 12 | 100 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 34/4 | 2024-09-12 | 2024-09 | 9 | 2025-05-22 | 2025-05 | 5 | 252 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 34/1 | 2024-09-16 | 2024-09 | 9 | 2024-10-09 | 2024-10 | 10 | 23 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 52/2 | 2024-09-19 | 2024-09 | 9 | 2025-12-17 | 2025-12 | 12 | 454 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/12 | 2024-09-28 | 2024-09 | 9 | 2024-10-28 | 2024-10 | 10 | 30 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/11 | 2024-10-03 | 2024-10 | 10 | 2025-05-11 | 2025-05 | 5 | 220 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/14 | 2024-10-11 | 2024-10 | 10 | 2024-01-07 | 2024-01 | 1 | -278 | Yes | Yes | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/8 | 2024-10-19 | 2024-10 | 10 | 2025-01-13 | 2025-01 | 1 | 86 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 34/0 | 2024-10-29 | 2024-10 | 10 | 2025-04-22 | 2025-04 | 4 | 175 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/7 | 2024-11-04 | 2024-11 | 11 | 2025-06-03 | 2025-06 | 6 | 211 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/9 | 2024-11-11 | 2024-11 | 11 | 2025-06-12 | 2025-06 | 6 | 213 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/06 | 2024-11-13 | 2024-11 | 11 | 2024-11-05 | 2024-11 | 11 | -8 | Yes | Yes | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/7 | 2024-11-22 | 2024-11 | 11 | 2025-03-12 | 2025-03 | 3 | 110 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/8 | 2024-11-27 | 2024-11 | 11 | 2025-06-09 | 2025-06 | 6 | 194 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 41/0 | 2024-12-05 | 2024-12 | 12 | 2025-02-21 | 2025-02 | 2 | 78 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 43/0 | 2024-12-18 | 2024-12 | 12 | 2025-02-26 | 2025-02 | 2 | 70 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 45/02 | 2024-12-20 | 2024-12 | 12 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/4 | 2024-12-24 | 2024-12 | 12 | 2025-01-16 | 2025-01 | 1 | 23 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 34/2 | 2024-12-26 | 2024-12 | 12 | 2025-01-24 | 2025-01 | 1 | 29 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 45/0 | 2024-12-30 | 2024-12 | 12 | 2025-03-18 | 2025-03 | 3 | 78 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/0 | 2025-01-11 | 2025-01 | 1 | 2025-03-03 | 2025-03 | 3 | 51 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/0 | 2025-01-13 | 2025-01 | 1 | 2025-05-08 | 2025-05 | 5 | 115 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/15 | 2025-01-13 | 2025-01 | 1 | 2025-04-27 | 2025-04 | 4 | 104 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 45/1 | 2025-01-21 | 2025-01 | 1 | 2025-03-18 | 2025-03 | 3 | 56 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/9 | 2025-01-23 | 2025-01 | 1 | 2025-03-06 | 2025-03 | 3 | 42 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/5 | 2025-01-24 | 2025-01 | 1 | 2025-04-11 | 2025-04 | 4 | 77 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/1 | 2025-02-01 | 2025-02 | 2 | 2025-09-22 | 2025-09 | 9 | 233 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 42/0 | 2025-02-03 | 2025-02 | 2 | 2025-04-05 | 2025-04 | 4 | 61 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/5 | 2025-02-10 | 2025-02 | 2 | 2025-05-11 | 2025-05 | 5 | 90 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 32/0 | 2025-02-16 | 2025-02 | 2 | 2025-10-04 | 2025-10 | 10 | 230 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 55/0 | 2025-02-19 | 2025-02 | 2 | 2025-04-18 | 2025-04 | 4 | 58 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 40/0 | 2025-02-20 | 2025-02 | 2 | 2025-07-03 | 2025-07 | 7 | 133 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 55/4 | 2025-02-24 | 2025-02 | 2 | 2025-04-12 | 2025-04 | 4 | 47 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 37/0 | 2025-03-01 | 2025-03 | 3 | 2025-07-03 | 2025-07 | 7 | 124 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 37/1 | 2025-03-02 | 2025-03 | 3 | 2025-04-29 | 2025-04 | 4 | 58 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 48A/0 | 2025-03-05 | 2025-03 | 3 | 2025-08-07 | 2025-08 | 8 | 155 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 60/4 | 2025-03-10 | 2025-03 | 3 | 2025-10-18 | 2025-10 | 10 | 222 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 37/2 | 2025-03-12 | 2025-03 | 3 | 2025-07-14 | 2025-07 | 7 | 124 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 47/1 | 2025-03-19 | 2025-03 | 3 | 2025-11-21 | 2025-11 | 11 | 247 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/2 | 2025-03-21 | 2025-03 | 3 | 2025-05-05 | 2025-05 | 5 | 45 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 38/1 | 2025-03-24 | 2025-03 | 3 | 2025-07-15 | 2025-07 | 7 | 113 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 54/2 | 2025-03-24 | 2025-03 | 3 | 2026-01-22 | 2026-01 | 1 | 304 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 45/2 | 2025-04-01 | 2025-04 | 4 | 2025-03-28 | 2025-03 | 3 | -4 | Yes | Yes | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 38/2 | 2025-04-04 | 2025-04 | 4 | 2025-07-03 | 2025-07 | 7 | 90 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 61/0 | 2025-04-04 | 2025-04 | 4 | 2025-09-14 | 2025-09 | 9 | 163 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 54/1 | 2025-04-11 | 2025-04 | 4 | 2025-09-28 | 2025-09 | 9 | 170 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 60/2 | 2025-04-18 | 2025-04 | 4 | 2025-08-26 | 2025-08 | 8 | 130 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 60/0 | 2025-04-25 | 2025-04 | 4 | 2025-11-30 | 2025-11 | 11 | 219 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 56/0 | 2025-05-01 | 2025-05 | 5 | 2025-09-05 | 2025-09 | 9 | 127 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/13 | 2025-05-05 | 2025-05 | 5 | 2025-08-09 | 2025-08 | 8 | 96 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 36/0 | 2025-05-11 | 2025-05 | 5 | 2025-06-19 | 2025-06 | 6 | 39 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 59/0 | 2025-05-14 | 2025-05 | 5 | 2026-01-07 | 2026-01 | 1 | 238 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/12 | 2025-05-15 | 2025-05 | 5 | 2025-09-03 | 2025-09 | 9 | 111 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 43/2 | 2025-05-19 | 2025-05 | 5 | 2025-11-06 | 2025-11 | 11 | 171 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 45/3 | 2025-05-23 | 2025-05 | 5 | 2025-09-09 | 2025-09 | 9 | 109 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 48/1 | 2025-05-23 | 2025-05 | 5 | 2025-08-16 | 2025-08 | 8 | 85 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 48/2 | 2025-05-24 | 2025-05 | 5 | 2025-09-09 | 2025-09 | 9 | 108 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 52/0 | 2025-05-26 | 2025-05 | 5 | 2025-08-19 | 2025-08 | 8 | 85 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 41/5 | 2025-06-01 | 2025-06 | 6 | 2025-07-24 | 2025-07 | 7 | 53 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/6 | 2025-06-02 | 2025-06 | 6 | 2025-06-14 | 2025-06 | 6 | 12 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/1 | 2025-06-03 | 2025-06 | 6 | 2025-07-21 | 2025-07 | 7 | 48 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/2 | 2025-06-09 | 2025-06 | 6 | 2025-06-29 | 2025-06 | 6 | 20 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/10 | 2025-06-10 | 2025-06 | 6 | 2025-08-07 | 2025-08 | 8 | 58 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/5 | 2025-06-11 | 2025-06 | 6 | 2025-07-22 | 2025-07 | 7 | 41 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/0 | 2025-06-16 | 2025-06 | 6 | 2025-10-16 | 2025-10 | 10 | 122 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 43/1 | 2025-06-18 | 2025-06 | 6 | 2025-08-18 | 2025-08 | 8 | 61 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/9 | 2025-06-20 | 2025-06 | 6 | 2025-07-21 | 2025-07 | 7 | 31 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 36/1 | 2025-06-20 | 2025-06 | 6 | 2025-08-06 | 2025-08 | 8 | 47 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/2 | 2025-06-21 | 2025-06 | 6 | 2025-09-12 | 2025-09 | 9 | 83 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 44/1 | 2025-06-24 | 2025-06 | 6 | 2025-11-23 | 2025-11 | 11 | 152 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 62/0 | 2025-06-25 | 2025-06 | 6 | 2025-09-01 | 2025-09 | 9 | 68 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 57/2 | 2025-06-27 | 2025-06 | 6 | 2026-01-29 | 2026-01 | 1 | 216 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/3 | 2025-06-30 | 2025-06 | 6 | 2025-08-31 | 2025-08 | 8 | 62 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/1 | 2025-06-30 | 2025-06 | 6 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 39/0 | 2025-07-01 | 2025-07 | 7 | 2025-10-16 | 2025-10 | 10 | 107 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/4 | 2025-07-02 | 2025-07 | 7 | 2025-11-12 | 2025-11 | 11 | 133 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 57/1 | 2025-07-02 | 2025-07 | 7 | 2025-12-26 | 2025-12 | 12 | 177 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/3 | 2025-07-03 | 2025-07 | 7 | 2025-08-22 | 2025-08 | 8 | 50 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/10 | 2025-07-05 | 2025-07 | 7 | 2025-10-29 | 2025-10 | 10 | 116 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 52/1 | 2025-07-05 | 2025-07 | 7 | 2025-12-10 | 2025-12 | 12 | 158 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 48/0 | 2025-07-08 | 2025-07 | 7 | 2025-11-11 | 2025-11 | 11 | 126 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/6 | 2025-07-09 | 2025-07 | 7 | 2025-11-04 | 2025-11 | 11 | 118 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 60/1 | 2025-07-10 | 2025-07 | 7 | 2025-12-16 | 2025-12 | 12 | 159 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 47/0 | 2025-07-13 | 2025-07 | 7 | 2025-12-01 | 2025-12 | 12 | 141 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 53/0 | 2025-07-14 | 2025-07 | 7 | 2025-09-16 | 2025-09 | 9 | 64 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 43/3 | 2025-07-16 | 2025-07 | 7 | 2026-02-20 | 2026-02 | 2 | 219 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 58/0 | 2025-07-16 | 2025-07 | 7 | 2025-12-26 | 2025-12 | 12 | 163 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 57/3 | 2025-07-18 | 2025-07 | 7 | 2026-01-08 | 2026-01 | 1 | 174 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 44/0 | 2025-07-20 | 2025-07 | 7 | 2025-09-25 | 2025-09 | 9 | 67 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/11 | 2025-07-23 | 2025-07 | 7 | 2025-12-04 | 2025-12 | 12 | 134 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 56/1 | 2025-07-29 | 2025-07 | 7 | 2025-12-07 | 2025-12 | 12 | 131 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 56/2 | 2025-08-03 | 2025-08 | 8 | 2025-12-15 | 2025-12 | 12 | 134 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 56/3 | 2025-08-06 | 2025-08 | 8 | 2025-12-20 | 2025-12 | 12 | 136 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 54/0 | 2025-08-29 | 2025-08 | 8 | 2025-09-29 | 2025-09 | 9 | 31 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 42/0 - 43/0 | 2025-09-28 | 2025-09 | 9 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 41/0 - 42/0 | 2025-10-06 | 2025-10 | 10 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 36/0 - 36/1 | 2025-11-03 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 55/6 | 2025-11-10 | 2025-11 | 11 | 2026-01-08 | 2026-01 | 1 | 59 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 55/5 | 2025-11-15 | 2025-11 | 11 | 2026-01-20 | 2026-01 | 1 | 66 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/0 - 36/0 | 2025-11-17 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 51/0 | 2025-11-21 | 2025-11 | 11 | 2026-02-05 | 2026-02 | 2 | 76 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 50/0 | 2025-11-25 | 2025-11 | 11 | 2026-02-04 | 2026-02 | 2 | 71 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 48A/1 | 2025-11-27 | 2025-11 | 11 | 2025-12-23 | 2025-12 | 12 | 26 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 34/0 - 35/0 | 2025-11-30 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 49/0 | 2025-12-10 | 2025-12 | 12 | 2026-01-28 | 2026-01 | 1 | 49 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 48A/2 | 2025-12-13 | 2025-12 | 12 | 2025-12-31 | 2025-12 | 12 | 18 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 59/1 | 2025-12-16 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 57/0 | 2025-12-20 | 2025-12 | 12 | 2025-01-16 | 2025-01 | 1 | -338 | Yes | Yes | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 60/3 | 2025-12-23 | 2025-12 | 12 | 2026-01-16 | 2026-01 | 1 | 24 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 40/0 - 41/0 | 2025-12-26 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 63/0 | 2026-01-09 | 2026-01 | 1 | 2026-02-05 | 2026-02 | 2 | 27 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/6 - 34/0 | 2026-01-27 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/5 - 33/6 | 2026-01-30 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/0 - 33/5 | 2026-02-09 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 39/0-40/0 | 2026-02-10 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 38/0 | 2026-02-17 | 2026-02 | 2 | 2026-02-24 | 2026-02 | 2 | 7 | Yes | No | fallback_single_line |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 32/0-33/0 | 2026-02-22 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 45/1-46/0 | 2026-03-03 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 43/0 - 44/0 | 2026-03-11 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 45/0 - 45/1 | 2026-03-12 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 44/0-45/0 | 2026-03-18 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 56/0-56/3 | 2026-03-31 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 61/0-62/0 | 2026-04-15 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 63/0-GNTY | 2026-04-18 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 55/0-56/0 | 2026-05-03 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 37/0-38/0 | 2026-05-12 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 36/01 - 37/00 | 2026-05-23 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 38/0-39/0 | 2026-05-26 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 52/00 - 53/00 | 2026-06-06 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 51/00 - 52/00 | 2026-06-08 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 56/03 - 57/00 | 2026-06-09 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 54/00 - 55/00 | 2026-06-19 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 53/00 - 54/00 | 2026-06-20 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 57/00 - 58/00 | 2026-06-23 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 48A/0-49/0 | 2026-06-26 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 62/0-63/0 | 2026-06-26 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 59/0 - 60/0 | 2026-06-27 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 58/0 - 59/0 | 2026-06-28 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 60/0-61/0 | 2026-07-04 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 48/0-48A/0 | 2026-07-05 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 47/0-48/0 | 2026-07-12 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 49/0-50/0 | 2026-07-12 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 50/0-51/0 | 2026-07-12 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/0-46/7 | 2026-07-21 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 419 | 4xx | Government | ta419 | 19/5 | 2024-05-24 | 2024-05 | 5 | 2025-02-03 | 2025-02 | 2 | 255 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 19/4 | 2024-05-28 | 2024-05 | 5 | 2025-01-11 | 2025-01 | 1 | 228 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 19/3 | 2024-05-29 | 2024-05 | 5 | 2025-01-18 | 2025-01 | 1 | 234 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 19/1 | 2024-06-01 | 2024-06 | 6 | 2025-01-23 | 2025-01 | 1 | 236 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 17/2 | 2024-06-04 | 2024-06 | 6 | 2025-01-31 | 2025-01 | 1 | 241 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 17/1 | 2024-06-07 | 2024-06 | 6 | 2025-02-08 | 2025-02 | 2 | 246 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 19/2 | 2024-06-09 | 2024-06 | 6 | 2024-11-19 | 2024-11 | 11 | 163 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 20/1 | 2024-06-21 | 2024-06 | 6 | 2024-11-21 | 2024-11 | 11 | 153 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 20/2 | 2024-06-23 | 2024-06 | 6 | 2024-11-28 | 2024-11 | 11 | 158 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 11/4 | 2024-06-26 | 2024-06 | 6 | 2025-04-03 | 2025-04 | 4 | 281 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 22/2 | 2024-06-29 | 2024-06 | 6 | 2024-12-04 | 2024-12 | 12 | 158 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 11/3 | 2024-06-30 | 2024-06 | 6 | 2025-04-11 | 2025-04 | 4 | 285 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 12/1 | 2024-07-07 | 2024-07 | 7 | 2025-03-26 | 2025-03 | 3 | 262 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 23/1 | 2024-07-09 | 2024-07 | 7 | 2024-12-14 | 2024-12 | 12 | 158 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 22/3 | 2024-07-10 | 2024-07 | 7 | 2024-12-09 | 2024-12 | 12 | 152 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/10 | 2024-07-10 | 2024-07 | 7 | 2024-12-17 | 2024-12 | 12 | 160 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 23/2 | 2024-07-14 | 2024-07 | 7 | 2024-12-18 | 2024-12 | 12 | 157 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/9 | 2024-07-14 | 2024-07 | 7 | 2024-01-06 | 2024-01 | 1 | -190 | Yes | Yes | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/8 | 2024-07-16 | 2024-07 | 7 | 2024-11-21 | 2024-11 | 11 | 128 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/12 | 2024-07-18 | 2024-07 | 7 | 2024-12-22 | 2024-12 | 12 | 157 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 23/3 | 2024-07-19 | 2024-07 | 7 | 2025-03-06 | 2025-03 | 3 | 230 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 3/2 | 2024-07-21 | 2024-07 | 7 | 2025-07-29 | 2025-07 | 7 | 373 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 26/4 | 2024-07-22 | 2024-07 | 7 | 2025-04-17 | 2025-04 | 4 | 269 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 26/3 | 2024-07-25 | 2024-07 | 7 | 2025-04-12 | 2025-04 | 4 | 261 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/3 | 2024-07-25 | 2024-07 | 7 | 2024-12-06 | 2024-12 | 12 | 134 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 3/3 | 2024-07-26 | 2024-07 | 7 | 2025-10-06 | 2025-10 | 10 | 437 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/6 | 2024-07-29 | 2024-07 | 7 | 2025-02-18 | 2025-02 | 2 | 204 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 24/1 | 2024-07-30 | 2024-07 | 7 | 2025-01-03 | 2025-01 | 1 | 157 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 3/5 | 2024-07-30 | 2024-07 | 7 | 2025-05-05 | 2025-05 | 5 | 279 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 3/4 | 2024-08-04 | 2024-08 | 8 | 2025-09-28 | 2025-09 | 9 | 420 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/2 | 2024-08-04 | 2024-08 | 8 | 2024-12-12 | 2024-12 | 12 | 130 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 26/2 | 2024-08-07 | 2024-08 | 8 | 2025-07-28 | 2025-07 | 7 | 355 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/5 | 2024-08-10 | 2024-08 | 8 | 2025-01-17 | 2025-01 | 1 | 160 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 4/1 | 2024-08-11 | 2024-08 | 8 | 2025-04-28 | 2025-04 | 4 | 260 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/11 | 2024-08-14 | 2024-08 | 8 | 2024-11-28 | 2024-11 | 11 | 106 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 5/1 | 2024-08-17 | 2024-08 | 8 | 2025-04-07 | 2025-04 | 4 | 233 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 5/3 | 2024-08-28 | 2024-08 | 8 | 2025-02-23 | 2025-02 | 2 | 179 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 27/2 | 2024-09-01 | 2024-09 | 9 | 2025-06-12 | 2025-06 | 6 | 284 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0D/3 | 2024-09-03 | 2024-09 | 9 | 2025-01-28 | 2025-01 | 1 | 147 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 5/2 | 2024-09-04 | 2024-09 | 9 | 2025-03-24 | 2025-03 | 3 | 201 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0D/2 | 2024-09-10 | 2024-09 | 9 | 2025-01-12 | 2025-01 | 1 | 124 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 12/0 | 2024-09-16 | 2024-09 | 9 | 2025-04-19 | 2025-04 | 4 | 215 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 4/0 | 2024-09-16 | 2024-09 | 9 | 2025-09-15 | 2025-09 | 9 | 364 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0E/2 | 2024-09-18 | 2024-09 | 9 | 2025-01-04 | 2025-01 | 1 | 108 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 7/0 | 2024-09-21 | 2024-09 | 9 | 2025-12-24 | 2025-12 | 12 | 459 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/1 | 2024-09-23 | 2024-09 | 9 | 2025-01-11 | 2025-01 | 1 | 110 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0E/1 | 2024-09-24 | 2024-09 | 9 | 2025-01-11 | 2025-01 | 1 | 109 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 27/1 | 2024-09-26 | 2024-09 | 9 | 2025-06-05 | 2025-06 | 6 | 252 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 24/2 | 2024-09-27 | 2024-09 | 9 | 2025-04-23 | 2025-04 | 4 | 208 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0B/2 | 2024-09-28 | 2024-09 | 9 | 2024-12-04 | 2024-12 | 12 | 67 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0D/1 | 2024-09-30 | 2024-09 | 9 | 2024-12-22 | 2024-12 | 12 | 83 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0D/5 | 2024-09-30 | 2024-09 | 9 | 2025-02-07 | 2025-02 | 2 | 130 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 12A/0 | 2024-09-30 | 2024-09 | 9 | 2025-04-28 | 2025-04 | 4 | 210 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 5/0 | 2024-10-04 | 2024-10 | 10 | 2025-04-14 | 2025-04 | 4 | 192 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0B/3 | 2024-10-07 | 2024-10 | 10 | 2025-01-19 | 2025-01 | 1 | 104 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 23/0 | 2024-10-07 | 2024-10 | 10 | 2024-12-22 | 2024-12 | 12 | 76 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0D/4 | 2024-10-11 | 2024-10 | 10 | 2025-02-08 | 2025-02 | 2 | 120 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 5/4 | 2024-10-11 | 2024-10 | 10 | 2025-02-09 | 2025-02 | 2 | 121 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 28/0 | 2024-10-12 | 2024-10 | 10 | 2025-06-27 | 2025-06 | 6 | 258 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0D/0 | 2024-10-14 | 2024-10 | 10 | 2025-02-13 | 2025-02 | 2 | 122 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 27/3 | 2024-10-14 | 2024-10 | 10 | 2025-06-21 | 2025-06 | 6 | 250 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/4 | 2024-10-15 | 2024-10 | 10 | 2025-01-20 | 2025-01 | 1 | 97 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 26/5 | 2024-10-16 | 2024-10 | 10 | 2025-03-31 | 2025-03 | 3 | 166 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 26/6 | 2024-10-19 | 2024-10 | 10 | 2025-04-08 | 2025-04 | 4 | 171 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0B/1 | 2024-10-22 | 2024-10 | 10 | 2025-02-19 | 2025-02 | 2 | 120 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0C/0 | 2024-10-25 | 2024-10 | 10 | 2025-11-15 | 2025-11 | 11 | 386 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0C/1 | 2024-10-25 | 2024-10 | 10 | 2025-01-20 | 2025-01 | 1 | 87 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 27/0 | 2024-10-25 | 2024-10 | 10 | 2025-05-19 | 2025-05 | 5 | 206 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 24/0 | 2024-10-27 | 2024-10 | 10 | 2025-03-08 | 2025-03 | 3 | 132 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/0 | 2024-10-27 | 2024-10 | 10 | 2025-02-02 | 2025-02 | 2 | 98 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0E/0 | 2024-10-28 | 2024-10 | 10 | 2025-12-03 | 2025-12 | 12 | 401 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0B/0 | 2024-11-08 | 2024-11 | 11 | 2025-09-23 | 2025-09 | 9 | 319 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 20/0 | 2024-11-08 | 2024-11 | 11 | 2025-02-07 | 2025-02 | 2 | 91 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 18/0 | 2024-11-09 | 2024-11 | 11 | 2025-02-14 | 2025-02 | 2 | 97 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 19/0 | 2024-11-13 | 2024-11 | 11 | 2025-01-27 | 2025-01 | 1 | 75 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 24/3 | 2024-11-20 | 2024-11 | 11 | 2025-03-27 | 2025-03 | 3 | 127 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 11/2 | 2024-11-22 | 2024-11 | 11 | 2025-08-31 | 2025-08 | 8 | 282 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 12/2 | 2024-11-22 | 2024-11 | 11 | 2025-09-07 | 2025-09 | 9 | 289 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 26/1 | 2024-11-22 | 2024-11 | 11 | 2025-03-22 | 2025-03 | 3 | 120 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 17/0 | 2024-11-27 | 2024-11 | 11 | 2025-02-22 | 2025-02 | 2 | 87 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/7 | 2024-11-28 | 2024-11 | 11 | 2025-01-27 | 2025-01 | 1 | 60 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 3/1 | 2024-11-29 | 2024-11 | 11 | 2025-08-12 | 2025-08 | 8 | 256 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/6 | 2024-11-29 | 2024-11 | 11 | 2025-10-23 | 2025-10 | 10 | 328 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 7/1 | 2024-11-29 | 2024-11 | 11 | 2025-03-01 | 2025-03 | 3 | 92 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0F/0 | 2024-11-30 | 2024-11 | 11 | 2025-02-25 | 2025-02 | 2 | 87 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/7 | 2024-12-02 | 2024-12 | 12 | 2025-10-16 | 2025-10 | 10 | 318 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 11/1 | 2024-12-09 | 2024-12 | 12 | 2025-08-04 | 2025-08 | 8 | 238 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 15A/0 | 2024-12-10 | 2024-12 | 12 | 2025-03-02 | 2025-03 | 3 | 82 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 22/1 | 2024-12-10 | 2024-12 | 12 | 2025-02-19 | 2025-02 | 2 | 71 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0G/0 | 2024-12-11 | 2024-12 | 12 | 2025-08-15 | 2025-08 | 8 | 247 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 16/0 | 2024-12-14 | 2024-12 | 12 | 2025-10-12 | 2025-10 | 10 | 302 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 28/1 | 2024-12-17 | 2024-12 | 12 | 2025-04-12 | 2025-04 | 4 | 116 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 30/1 | 2024-12-21 | 2024-12 | 12 | 2025-03-31 | 2025-03 | 3 | 100 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 15/0 | 2024-12-23 | 2024-12 | 12 | 2026-05-20 | 2026-05 | 5 | 513 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 31/0 | 2024-12-23 | 2024-12 | 12 | 2025-04-28 | 2025-04 | 4 | 126 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0A/0 (CT) | 2024-12-24 | 2024-12 | 12 | 2025-01-27 | 2025-01 | 1 | 34 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 31/1 | 2024-12-24 | 2024-12 | 12 | 2025-04-22 | 2025-04 | 4 | 119 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 1/0 | 2025-01-04 | 2025-01 | 1 | 2025-08-01 | 2025-08 | 8 | 209 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0H/0 | 2025-01-09 | 2025-01 | 1 | 2025-08-01 | 2025-08 | 8 | 204 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0G/1 | 2025-01-15 | 2025-01 | 1 | 2025-08-20 | 2025-08 | 8 | 217 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 10/0 | 2025-01-18 | 2025-01 | 1 | 2025-08-14 | 2025-08 | 8 | 208 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 22/0 | 2025-01-25 | 2025-01 | 1 | 2025-04-29 | 2025-04 | 4 | 94 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/1 | 2025-01-28 | 2025-01 | 1 | 2025-07-26 | 2025-07 | 7 | 179 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/2 | 2025-01-29 | 2025-01 | 1 | 2025-08-02 | 2025-08 | 8 | 185 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/4 | 2025-02-07 | 2025-02 | 2 | 2026-06-08 | 2026-06 | 6 | 486 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/8 | 2025-02-07 | 2025-02 | 2 | 2025-11-01 | 2025-11 | 11 | 267 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/7 | 2025-02-11 | 2025-02 | 2 | 2025-11-12 | 2025-11 | 11 | 274 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 62/2 | 2025-02-13 | 2025-02 | 2 | 2025-12-04 | 2025-12 | 12 | 294 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/10 | 2025-02-15 | 2025-02 | 2 | 2025-12-04 | 2025-12 | 12 | 292 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/5 | 2025-02-20 | 2025-02 | 2 | 2025-12-04 | 2025-12 | 12 | 287 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 62/1 | 2025-02-22 | 2025-02 | 2 | 2025-11-15 | 2025-11 | 11 | 266 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/6 | 2025-02-28 | 2025-02 | 2 | 2025-12-01 | 2025-12 | 12 | 276 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/8 | 2025-02-28 | 2025-02 | 2 | 2025-12-11 | 2025-12 | 12 | 286 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 62/5 | 2025-02-28 | 2025-02 | 2 | 2025-12-10 | 2025-12 | 12 | 285 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 62/4 | 2025-03-05 | 2025-03 | 3 | 2025-11-29 | 2025-11 | 11 | 269 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/0 | 2025-03-15 | 2025-03 | 3 | 2025-11-12 | 2025-11 | 11 | 242 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/11 | 2025-03-26 | 2025-03 | 3 | 2025-12-10 | 2025-12 | 12 | 259 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/9 | 2025-03-27 | 2025-03 | 3 | 2025-12-17 | 2025-12 | 12 | 265 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 34/0 | 2025-03-29 | 2025-03 | 3 | 2025-07-01 | 2025-07 | 7 | 94 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/0 | 2025-04-05 | 2025-04 | 4 | 2025-12-18 | 2025-12 | 12 | 257 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 20/3 | 2025-04-08 | 2025-04 | 4 | 2025-07-19 | 2025-07 | 7 | 102 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/6 | 2025-04-08 | 2025-04 | 4 | 2025-11-17 | 2025-11 | 11 | 223 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 62/3 | 2025-04-08 | 2025-04 | 4 | 2025-12-28 | 2025-12 | 12 | 264 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/3 | 2025-04-11 | 2025-04 | 4 | 2025-11-29 | 2025-11 | 11 | 232 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/7 | 2025-04-14 | 2025-04 | 4 | 2025-12-10 | 2025-12 | 12 | 240 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/5 | 2025-04-17 | 2025-04 | 4 | 2025-11-08 | 2025-11 | 11 | 205 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/4 | 2025-04-21 | 2025-04 | 4 | 2025-11-24 | 2025-11 | 11 | 217 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/2 | 2025-04-22 | 2025-04 | 4 | 2025-12-05 | 2025-12 | 12 | 227 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 46/4 | 2025-04-22 | 2025-04 | 4 | 2025-12-04 | 2025-12 | 12 | 226 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/9 | 2025-04-23 | 2025-04 | 4 | 2025-12-17 | 2025-12 | 12 | 238 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/1 | 2025-04-24 | 2025-04 | 4 | 2025-12-10 | 2025-12 | 12 | 230 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/7 | 2025-04-28 | 2025-04 | 4 | 2025-11-29 | 2025-11 | 11 | 215 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/5 | 2025-04-29 | 2025-04 | 4 | 2025-11-08 | 2025-11 | 11 | 193 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/8 | 2025-05-04 | 2025-05 | 5 | 2025-12-05 | 2025-12 | 12 | 215 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/0 | 2025-05-07 | 2025-05 | 5 | 2026-06-21 | 2026-06 | 6 | 410 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/3 | 2025-05-11 | 2025-05 | 5 | 2025-11-24 | 2025-11 | 11 | 197 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/4 | 2025-05-12 | 2025-05 | 5 | 2025-11-15 | 2025-11 | 11 | 187 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 84/1 | 2025-05-15 | 2025-05 | 5 | 2025-12-16 | 2025-12 | 12 | 215 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 25/0 | 2025-05-19 | 2025-05 | 5 | 2026-04-14 | 2026-04 | 4 | 330 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 83/6 | 2025-05-19 | 2025-05 | 5 | 2026-01-05 | 2026-01 | 1 | 231 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 26/0 | 2025-05-21 | 2025-05 | 5 | 2025-10-06 | 2025-10 | 10 | 138 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 83/7 | 2025-06-05 | 2025-06 | 6 | 2025-11-19 | 2025-11 | 11 | 167 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 35/0 | 2025-06-06 | 2025-06 | 6 | 2025-10-27 | 2025-10 | 10 | 143 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 3/0 | 2025-06-07 | 2025-06 | 6 | 2026-03-21 | 2026-03 | 3 | 287 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/0 | 2025-06-07 | 2025-06 | 6 | 2025-11-12 | 2025-11 | 11 | 158 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 34/1 | 2025-06-08 | 2025-06 | 6 | 2025-07-18 | 2025-07 | 7 | 40 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 29/0 | 2025-06-15 | 2025-06 | 6 | 2025-07-09 | 2025-07 | 7 | 24 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 83/5 | 2025-06-19 | 2025-06 | 6 | 2025-12-21 | 2025-12 | 12 | 185 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 11/0 | 2025-06-23 | 2025-06 | 6 | 2025-11-05 | 2025-11 | 11 | 135 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 78/3 | 2025-06-26 | 2025-06 | 6 | 2026-07-15 | 2026-07 | 7 | 384 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 30/0 | 2025-06-27 | 2025-06 | 6 | 2025-10-26 | 2025-10 | 10 | 121 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 84/4 | 2025-07-04 | 2025-07 | 7 | 2025-12-13 | 2025-12 | 12 | 162 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 21/0 | 2025-07-08 | 2025-07 | 7 | 2025-09-14 | 2025-09 | 9 | 68 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 2/0 | 2025-07-14 | 2025-07 | 7 | 2026-02-13 | 2026-02 | 2 | 214 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 9/0 | 2025-07-23 | 2025-07 | 7 | 2025-12-13 | 2025-12 | 12 | 143 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 8/0 | 2025-07-28 | 2025-07 | 7 | 2026-08-06 | 2026-08 | 8 | 374 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/6 | 2025-08-03 | 2025-08 | 8 | 2025-12-17 | 2025-12 | 12 | 136 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 46/0 | 2025-08-31 | 2025-08 | 8 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 46/1 | 2025-09-12 | 2025-09 | 9 | 2025-11-24 | 2025-11 | 11 | 73 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 46/2 | 2025-09-16 | 2025-09 | 9 | 2025-11-12 | 2025-11 | 11 | 57 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 46/3 | 2025-09-19 | 2025-09 | 9 | 2025-11-12 | 2025-11 | 11 | 54 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 31/2 | 2025-10-03 | 2025-10 | 10 | 2025-10-14 | 2025-10 | 10 | 11 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 78/1 | 2025-10-03 | 2025-10 | 10 | 2026-04-07 | 2026-04 | 4 | 186 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 45/0 | 2025-10-09 | 2025-10 | 10 | 2025-12-12 | 2025-12 | 12 | 64 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 78/0 | 2025-10-23 | 2025-10 | 10 | 2026-01-08 | 2026-01 | 1 | 77 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 76/3 | 2025-10-24 | 2025-10 | 10 | 2025-11-19 | 2025-11 | 11 | 26 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 83/1 | 2025-10-30 | 2025-10 | 10 | 2025-11-21 | 2025-11 | 11 | 22 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 43/5 | 2025-11-04 | 2025-11 | 11 | 2025-11-19 | 2025-11 | 11 | 15 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 43/3 | 2025-11-09 | 2025-11 | 11 | 2026-07-08 | 2026-07 | 7 | 241 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 43/6 | 2025-11-09 | 2025-11 | 11 | 2025-12-03 | 2025-12 | 12 | 24 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63/5 | 2025-11-09 | 2025-11 | 11 | 2026-05-20 | 2026-05 | 5 | 192 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 43/0 | 2025-11-10 | 2025-11 | 11 | 2025-12-03 | 2025-12 | 12 | 23 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 54/5 | 2025-11-11 | 2025-11 | 11 | 2026-04-19 | 2026-04 | 4 | 159 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/10 | 2025-11-13 | 2025-11 | 11 | 2025-12-19 | 2025-12 | 12 | 36 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 43/1 | 2025-11-13 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 43/2 | 2025-11-18 | 2025-11 | 11 | 2026-07-02 | 2026-07 | 7 | 226 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 83/0 | 2025-11-20 | 2025-11 | 11 | 2025-12-09 | 2025-12 | 12 | 19 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/9 | 2025-11-23 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 84/3 | 2025-11-24 | 2025-11 | 11 | 2025-12-26 | 2025-12 | 12 | 32 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 43/4 | 2025-11-25 | 2025-11 | 11 | 2025-12-09 | 2025-12 | 12 | 14 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 54/6 | 2025-11-25 | 2025-11 | 11 | 2025-12-08 | 2025-12 | 12 | 13 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 12A/1 | 2025-11-28 | 2025-11 | 11 | 2025-12-12 | 2025-12 | 12 | 14 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 83/8 | 2025-11-28 | 2025-11 | 11 | 2026-01-15 | 2026-01 | 1 | 48 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63/4 | 2025-11-29 | 2025-11 | 11 | 2025-12-17 | 2025-12 | 12 | 18 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 54/2 | 2025-11-30 | 2025-11 | 11 | 2026-04-13 | 2026-04 | 4 | 134 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 55/6 | 2025-12-04 | 2025-12 | 12 | 2026-01-14 | 2026-01 | 1 | 41 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 33/1 | 2025-12-07 | 2025-12 | 12 | 2025-12-28 | 2025-12 | 12 | 21 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 54/4 | 2025-12-07 | 2025-12 | 12 | 2026-01-19 | 2026-01 | 1 | 43 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63A/0 | 2025-12-07 | 2025-12 | 12 | 2025-12-30 | 2025-12 | 12 | 23 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63/2 | 2025-12-09 | 2025-12 | 12 | 2025-12-29 | 2025-12 | 12 | 20 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 55/5 | 2025-12-12 | 2025-12 | 12 | 2026-01-03 | 2026-01 | 1 | 22 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 54/3 | 2025-12-13 | 2025-12 | 12 | 2025-12-22 | 2025-12 | 12 | 9 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 84/5 | 2025-12-15 | 2025-12 | 12 | 2026-01-08 | 2026-01 | 1 | 24 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 54/7 | 2025-12-18 | 2025-12 | 12 | 2026-04-01 | 2026-04 | 4 | 104 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 64/1 | 2025-12-18 | 2025-12 | 12 | 2026-04-21 | 2026-04 | 4 | 124 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 78/4 | 2025-12-18 | 2025-12 | 12 | 2025-12-26 | 2025-12 | 12 | 8 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 57/1 | 2025-12-20 | 2025-12 | 12 | 2026-01-09 | 2026-01 | 1 | 20 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 59/1 | 2025-12-26 | 2025-12 | 12 | 2026-01-09 | 2026-01 | 1 | 14 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 84/0 | 2025-12-26 | 2025-12 | 12 | 2026-01-09 | 2026-01 | 1 | 14 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 55/1 | 2025-12-27 | 2025-12 | 12 | 2026-01-03 | 2026-01 | 1 | 7 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63/6 | 2025-12-28 | 2025-12 | 12 | 2026-01-20 | 2026-01 | 1 | 23 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/5 | 2025-12-31 | 2025-12 | 12 | 2026-01-10 | 2026-01 | 1 | 10 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63/0 | 2025-12-31 | 2025-12 | 12 | 2026-01-09 | 2026-01 | 1 | 9 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63/1 | 2026-01-02 | 2026-01 | 1 | 2026-01-22 | 2026-01 | 1 | 20 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63B/6 | 2026-01-02 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 62/0 | 2026-01-04 | 2026-01 | 1 | 2026-01-15 | 2026-01 | 1 | 11 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 64/5 | 2026-01-04 | 2026-01 | 1 | 2026-04-30 | 2026-04 | 4 | 116 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 84A/0 | 2026-01-07 | 2026-01 | 1 | 2026-01-19 | 2026-01 | 1 | 12 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/3 | 2026-01-09 | 2026-01 | 1 | 2026-08-01 | 2026-08 | 8 | 204 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 55/4 | 2026-01-10 | 2026-01 | 1 | 2026-01-14 | 2026-01 | 1 | 4 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 55/0 | 2026-01-14 | 2026-01 | 1 | 2026-01-20 | 2026-01 | 1 | 6 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63/3 | 2026-01-17 | 2026-01 | 1 | 2026-07-30 | 2026-07 | 7 | 194 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 55/3 | 2026-01-18 | 2026-01 | 1 | 2026-04-10 | 2026-04 | 4 | 82 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 64A/0 | 2026-01-18 | 2026-01 | 1 | 2026-05-25 | 2026-05 | 5 | 127 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/1 | 2026-01-24 | 2026-01 | 1 | 2026-07-16 | 2026-07 | 7 | 173 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 64/0 | 2026-02-01 | 2026-02 | 2 | 2026-07-29 | 2026-07 | 7 | 178 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 55/2 | 2026-02-07 | 2026-02 | 2 | 2026-04-13 | 2026-04 | 4 | 65 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63B/1 | 2026-02-07 | 2026-02 | 2 | 2026-04-26 | 2026-04 | 4 | 78 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 64/2 | 2026-02-07 | 2026-02 | 2 | 2026-05-11 | 2026-05 | 5 | 93 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 78A/0 | 2026-02-13 | 2026-02 | 2 | 2026-07-05 | 2026-07 | 7 | 142 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 77/0 | 2026-02-19 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 42/0 | 2026-02-22 | 2026-02 | 2 | 2026-05-10 | 2026-05 | 5 | 77 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63B/0 | 2026-03-03 | 2026-03 | 3 | 2026-04-26 | 2026-04 | 4 | 54 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 54/1 | 2026-03-16 | 2026-03 | 3 | 2026-04-03 | 2026-04 | 4 | 18 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 33/0 | 2026-03-18 | 2026-03 | 3 | 2026-04-21 | 2026-04 | 4 | 34 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 78/2 | 2026-03-25 | 2026-03 | 3 | 2026-04-13 | 2026-04 | 4 | 19 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/8 | 2026-03-27 | 2026-03 | 3 | 2026-05-10 | 2026-05 | 5 | 44 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 81/0 | 2026-03-29 | 2026-03 | 3 | 2026-05-03 | 2026-05 | 5 | 35 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 13/0 | 2026-04-15 | 2026-04 | 4 | 2026-05-10 | 2026-05 | 5 | 25 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 32/0 | 2026-04-20 | 2026-04 | 4 | 2026-05-25 | 2026-05 | 5 | 35 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 14/0 | 2026-04-23 | 2026-04 | 4 | 2026-04-30 | 2026-04 | 4 | 7 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 80/0 | 2026-04-25 | 2026-04 | 4 | 2026-08-12 | 2026-08 | 8 | 109 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 76/2 | 2026-04-28 | 2026-04 | 4 | 2026-07-29 | 2026-07 | 7 | 92 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 14/1 | 2026-04-29 | 2026-04 | 4 | 2026-05-13 | 2026-05 | 5 | 14 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/1 | 2026-04-29 | 2026-04 | 4 | 2026-05-08 | 2026-05 | 5 | 9 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 60/0 | 2026-04-30 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 64/3 | 2026-05-04 | 2026-05 | 5 | 2026-05-10 | 2026-05 | 5 | 6 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 66/1 | 2026-05-04 | 2026-05 | 5 | 2026-06-27 | 2026-06 | 6 | 54 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/2 | 2026-05-05 | 2026-05 | 5 | 2026-06-01 | 2026-06 | 6 | 27 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 64/4 | 2026-05-08 | 2026-05 | 5 | 2026-05-31 | 2026-05 | 5 | 23 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 53/0 | 2026-05-09 | 2026-05 | 5 | 2026-05-27 | 2026-05 | 5 | 18 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 84/2 | 2026-05-10 | 2026-05 | 5 | 2026-07-20 | 2026-07 | 7 | 71 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/3 | 2026-05-11 | 2026-05 | 5 | 2026-06-01 | 2026-06 | 6 | 21 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 71/0 | 2026-05-11 | 2026-05 | 5 | 2026-06-06 | 2026-06 | 6 | 26 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 65/0 | 2026-05-17 | 2026-05 | 5 | 2026-06-10 | 2026-06 | 6 | 24 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 52/0 | 2026-05-18 | 2026-05 | 5 | 2026-06-22 | 2026-06 | 6 | 35 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 67/0 | 2026-05-20 | 2026-05 | 5 | 2026-07-01 | 2026-07 | 7 | 42 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 69/0 | 2026-05-20 | 2026-05 | 5 | 2026-07-27 | 2026-07 | 7 | 68 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 54/0 | 2026-05-25 | 2026-05 | 5 | 2026-06-10 | 2026-06 | 6 | 16 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 37/0 | 2026-05-26 | 2026-05 | 5 | 2026-06-10 | 2026-06 | 6 | 15 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 68/0 | 2026-05-28 | 2026-05 | 5 | 2026-07-13 | 2026-07 | 7 | 46 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 95A/0 | 2026-05-28 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 52/1 | 2026-05-31 | 2026-05 | 5 | 2026-04-03 | 2026-04 | 4 | -58 | Yes | Yes | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 65/2 | 2026-05-31 | 2026-05 | 5 | 2026-06-12 | 2026-06 | 6 | 12 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 70/0 | 2026-06-01 | 2026-06 | 6 | 2026-07-02 | 2026-07 | 7 | 31 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 75/0 | 2026-06-01 | 2026-06 | 6 | 2026-06-25 | 2026-06 | 6 | 24 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 72/0 | 2026-06-05 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 38/2 | 2026-06-06 | 2026-06 | 6 | 2026-06-14 | 2026-06 | 6 | 8 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 65/1 | 2026-06-06 | 2026-06 | 6 | 2026-07-13 | 2026-07 | 7 | 37 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 76/0 | 2026-06-06 | 2026-06 | 6 | 2026-06-10 | 2026-06 | 6 | 4 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 73/0 | 2026-06-08 | 2026-06 | 6 | 2026-06-17 | 2026-06 | 6 | 9 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 52/2 | 2026-06-09 | 2026-06 | 6 | 2026-06-14 | 2026-06 | 6 | 5 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 76/1 | 2026-06-11 | 2026-06 | 6 | 2026-07-13 | 2026-07 | 7 | 32 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 48/1 | 2026-06-13 | 2026-06 | 6 | 2026-07-01 | 2026-07 | 7 | 18 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 44/0 | 2026-06-18 | 2026-06 | 6 | 2026-06-26 | 2026-06 | 6 | 8 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 59/0 | 2026-06-23 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 63B/3 | 2026-06-23 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 74/0 | 2026-06-23 | 2026-06 | 6 | 2026-07-13 | 2026-07 | 7 | 20 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 48/0 | 2026-06-24 | 2026-06 | 6 | 2026-07-09 | 2026-07 | 7 | 15 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 39/0 | 2026-06-29 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 50/1 | 2026-07-02 | 2026-07 | 7 | 2026-07-17 | 2026-07 | 7 | 15 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 66/0 | 2026-07-04 | 2026-07 | 7 | 2026-07-20 | 2026-07 | 7 | 16 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 96/2 | 2026-07-04 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 50/0 | 2026-07-14 | 2026-07 | 7 | 2026-07-16 | 2026-07 | 7 | 2 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 96/0 | 2026-07-14 | 2026-07 | 7 | 2026-08-12 | 2026-08 | 8 | 29 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 79/0 | 2026-07-18 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 98/0 | 2026-07-18 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 57/0 | 2026-07-19 | 2026-07 | 7 | 2026-08-12 | 2026-08 | 8 | 24 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/4 | 2026-07-20 | 2026-07 | 7 | 2026-07-26 | 2026-07 | 7 | 6 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 47/0 | 2026-07-22 | 2026-07 | 7 | 2026-07-27 | 2026-07 | 7 | 5 | Yes | No | exact |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 86/1 | 2026-07-23 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 93C/0 | 2026-07-25 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 51/0 | 2026-07-30 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 82/0 | 2026-07-31 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 99/0 | 2026-08-04 | 2026-08 | 8 |  |  |  |  | No | No |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 421 | 4xx | Government | ta421 | 24/4 | 2024-05-22 | 2024-05 | 5 | 2024-08-29 | 2024-08 | 8 | 99 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 24/2 | 2024-06-02 | 2024-06 | 6 | 2024-12-03 | 2024-12 | 12 | 184 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 24/3 | 2024-06-07 | 2024-06 | 6 | 2024-08-29 | 2024-08 | 8 | 83 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 24/5 | 2024-06-11 | 2024-06 | 6 | 2024-08-22 | 2024-08 | 8 | 72 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 24/6 | 2024-06-15 | 2024-06 | 6 | 2024-11-13 | 2024-11 | 11 | 151 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 24/7 | 2024-06-19 | 2024-06 | 6 | 2024-10-27 | 2024-10 | 10 | 130 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 23/4 | 2024-06-20 | 2024-06 | 6 | 2024-10-05 | 2024-10 | 10 | 107 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 25/4 | 2024-06-22 | 2024-06 | 6 | 2024-07-10 | 2024-07 | 7 | 18 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 25/5 | 2024-06-25 | 2024-06 | 6 | 2025-02-19 | 2025-02 | 2 | 239 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 23/3 | 2024-06-27 | 2024-06 | 6 | 2024-10-16 | 2024-10 | 10 | 111 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 25/1 | 2024-06-28 | 2024-06 | 6 | 2024-08-02 | 2024-08 | 8 | 35 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 22/4 | 2024-06-29 | 2024-06 | 6 | 2024-10-17 | 2024-10 | 10 | 110 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 24/8 | 2024-06-29 | 2024-06 | 6 | 2024-10-21 | 2024-10 | 10 | 114 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/1 | 2024-06-29 | 2024-06 | 6 | 2024-12-20 | 2024-12 | 12 | 174 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/3 | 2024-06-30 | 2024-06 | 6 | 2024-09-14 | 2024-09 | 9 | 76 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 26/1 | 2024-07-04 | 2024-07 | 7 | 2024-07-18 | 2024-07 | 7 | 14 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/4 | 2024-07-05 | 2024-07 | 7 | 2024-10-01 | 2024-10 | 10 | 88 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 22/5 | 2024-07-06 | 2024-07 | 7 | 2024-08-23 | 2024-08 | 8 | 48 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 26/3 | 2024-07-07 | 2024-07 | 7 | 2024-08-16 | 2024-08 | 8 | 40 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/2 | 2024-07-10 | 2024-07 | 7 | 2024-10-19 | 2024-10 | 10 | 101 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 23/2 | 2024-07-10 | 2024-07 | 7 | 2024-09-26 | 2024-09 | 9 | 78 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 26/2 | 2024-07-10 | 2024-07 | 7 | 2024-08-09 | 2024-08 | 8 | 30 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/11 | 2024-07-11 | 2024-07 | 7 | 2025-02-11 | 2025-02 | 2 | 215 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 26/4 | 2024-07-13 | 2024-07 | 7 | 2024-07-27 | 2024-07 | 7 | 14 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 22/3 | 2024-07-14 | 2024-07 | 7 | 2025-03-03 | 2025-03 | 3 | 232 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 24/1 | 2024-07-16 | 2024-07 | 7 | 2024-11-15 | 2024-11 | 11 | 122 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/7 | 2024-07-17 | 2024-07 | 7 | 2024-11-14 | 2024-11 | 11 | 120 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 22/2 | 2024-07-17 | 2024-07 | 7 | 2024-10-29 | 2024-10 | 10 | 104 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/1 | 2024-07-19 | 2024-07 | 7 | 2024-08-19 | 2024-08 | 8 | 31 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/9 | 2024-07-22 | 2024-07 | 7 | 2024-09-09 | 2024-09 | 9 | 49 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/6 | 2024-07-23 | 2024-07 | 7 | 2024-11-07 | 2024-11 | 11 | 107 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/8 | 2024-07-30 | 2024-07 | 7 | 2024-10-01 | 2024-10 | 10 | 63 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/5 | 2024-07-31 | 2024-07 | 7 | 2024-11-01 | 2024-11 | 11 | 93 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/7 | 2024-07-31 | 2024-07 | 7 | 2024-09-12 | 2024-09 | 9 | 43 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/8 | 2024-07-31 | 2024-07 | 7 | 2024-12-03 | 2024-12 | 12 | 125 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/4 | 2024-08-05 | 2024-08 | 8 | 2024-09-19 | 2024-09 | 9 | 45 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/5 | 2024-08-08 | 2024-08 | 8 | 2024-09-24 | 2024-09 | 9 | 47 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/8 | 2024-08-11 | 2024-08 | 8 | 2024-11-12 | 2024-11 | 11 | 93 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 23/0 | 2024-08-11 | 2024-08 | 8 | 2024-11-21 | 2024-11 | 11 | 102 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/0 | 2024-08-11 | 2024-08 | 8 | 2024-11-24 | 2024-11 | 11 | 105 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/6 | 2024-08-13 | 2024-08 | 8 | 2024-09-29 | 2024-09 | 9 | 47 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/7 | 2024-08-13 | 2024-08 | 8 | 2024-10-03 | 2024-10 | 10 | 51 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 26/0 | 2024-08-14 | 2024-08 | 8 | 2024-11-19 | 2024-11 | 11 | 97 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/4 | 2024-08-16 | 2024-08 | 8 | 2024-11-16 | 2024-11 | 11 | 92 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 25/0 | 2024-08-16 | 2024-08 | 8 | 2024-11-02 | 2024-11 | 11 | 78 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 24/0 | 2024-08-17 | 2024-08 | 8 | 2024-11-02 | 2024-11 | 11 | 77 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/2 | 2024-08-19 | 2024-08 | 8 | 2024-09-14 | 2024-09 | 9 | 26 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/9 | 2024-08-22 | 2024-08 | 8 | 2024-10-01 | 2024-10 | 10 | 40 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 22/1 | 2024-08-23 | 2024-08 | 8 | 2024-10-18 | 2024-10 | 10 | 56 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/9 | 2024-08-23 | 2024-08 | 8 | 2025-04-29 | 2025-04 | 4 | 249 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/4 | 2024-08-24 | 2024-08 | 8 | 2024-09-21 | 2024-09 | 9 | 28 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 22/0 | 2024-08-25 | 2024-08 | 8 | 2024-11-05 | 2024-11 | 11 | 72 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/5 | 2024-08-27 | 2024-08 | 8 | 2024-10-05 | 2024-10 | 10 | 39 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/11 | 2024-08-28 | 2024-08 | 8 | 2024-12-12 | 2024-12 | 12 | 106 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/3 | 2024-08-30 | 2024-08 | 8 | 2024-12-09 | 2024-12 | 12 | 101 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/2 | 2024-08-31 | 2024-08 | 8 | 2024-11-26 | 2024-11 | 11 | 87 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/0 | 2024-09-08 | 2024-09 | 9 | 2024-11-22 | 2024-11 | 11 | 75 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/9 | 2024-09-11 | 2024-09 | 9 | 2025-06-06 | 2025-06 | 6 | 268 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 30/4 | 2024-09-11 | 2024-09 | 9 | 2024-10-16 | 2024-10 | 10 | 35 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/8 | 2024-09-16 | 2024-09 | 9 | 2024-12-15 | 2024-12 | 12 | 90 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 23/1 | 2024-09-20 | 2024-09 | 9 | 2024-11-09 | 2024-11 | 11 | 50 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/6 | 2024-09-20 | 2024-09 | 9 | 2025-01-16 | 2025-01 | 1 | 118 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 30/5 | 2024-09-20 | 2024-09 | 9 | 2025-01-23 | 2025-01 | 1 | 125 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/10 | 2024-09-22 | 2024-09 | 9 | 2024-10-27 | 2024-10 | 10 | 35 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 30/1 | 2024-09-27 | 2024-09 | 9 | 2025-01-04 | 2025-01 | 1 | 99 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/0 | 2024-09-30 | 2024-09 | 9 | 2025-03-08 | 2025-03 | 3 | 159 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 30/3 | 2024-10-03 | 2024-10 | 10 | 2024-12-26 | 2024-12 | 12 | 84 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 25/2 | 2024-10-04 | 2024-10 | 10 | 2024-11-08 | 2024-11 | 11 | 35 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 19/3 | 2024-10-10 | 2024-10 | 10 | 2024-12-11 | 2024-12 | 12 | 62 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 30/0 | 2024-10-12 | 2024-10 | 10 | 2025-06-03 | 2025-06 | 6 | 234 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/1 | 2024-10-14 | 2024-10 | 10 | 2025-08-23 | 2025-08 | 8 | 313 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 19/2 | 2024-10-17 | 2024-10 | 10 | 2024-12-16 | 2024-12 | 12 | 60 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/3 | 2024-10-18 | 2024-10 | 10 | 2025-11-26 | 2025-11 | 11 | 404 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 31/1 | 2024-10-21 | 2024-10 | 10 | 2025-01-28 | 2025-01 | 1 | 99 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/7 | 2024-10-21 | 2024-10 | 10 | 2025-09-13 | 2025-09 | 9 | 327 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 17/3 | 2024-10-24 | 2024-10 | 10 | 2025-04-12 | 2025-04 | 4 | 170 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/1 | 2024-10-30 | 2024-10 | 10 | 2025-02-09 | 2025-02 | 2 | 102 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/6 | 2024-10-30 | 2024-10 | 10 | 2024-12-03 | 2024-12 | 12 | 34 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/0 | 2024-10-30 | 2024-10 | 10 | 2025-09-13 | 2025-09 | 9 | 318 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 41/1 | 2024-11-07 | 2024-11 | 11 | 2025-10-22 | 2025-10 | 10 | 349 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 15/2 | 2024-11-08 | 2024-11 | 11 | 2025-03-27 | 2025-03 | 3 | 139 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/6 | 2024-11-13 | 2024-11 | 11 | 2025-01-16 | 2025-01 | 1 | 64 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 18/3 | 2024-11-15 | 2024-11 | 11 | 2024-12-19 | 2024-12 | 12 | 34 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 15/1 | 2024-11-16 | 2024-11 | 11 | 2025-03-23 | 2025-03 | 3 | 127 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/1 | 2024-11-18 | 2024-11 | 11 | 2025-09-16 | 2025-09 | 9 | 302 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/10 | 2024-11-19 | 2024-11 | 11 | 2025-01-02 | 2025-01 | 1 | 44 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 15/4 | 2024-11-23 | 2024-11 | 11 | 2025-03-29 | 2025-03 | 3 | 126 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/9 | 2024-11-24 | 2024-11 | 11 | 2025-02-22 | 2025-02 | 2 | 90 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/4 | 2024-11-24 | 2024-11 | 11 | 2025-02-19 | 2025-02 | 2 | 87 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 38/3 | 2024-11-24 | 2024-11 | 11 | 2025-03-03 | 2025-03 | 3 | 99 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/6 | 2024-11-26 | 2024-11 | 11 | 2025-01-14 | 2025-01 | 1 | 49 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 17/1 | 2024-11-26 | 2024-11 | 11 | 2025-01-03 | 2025-01 | 1 | 38 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 38/1 | 2024-11-28 | 2024-11 | 11 | 2025-02-26 | 2025-02 | 2 | 90 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/3 | 2024-11-29 | 2024-11 | 11 | 2025-02-13 | 2025-02 | 2 | 76 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 18/0 | 2024-11-29 | 2024-11 | 11 | 2024-12-27 | 2024-12 | 12 | 28 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/3 | 2024-11-29 | 2024-11 | 11 | 2025-07-06 | 2025-07 | 7 | 219 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/8 | 2024-11-30 | 2024-11 | 11 | 2025-08-07 | 2025-08 | 8 | 250 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/5 | 2024-11-30 | 2024-11 | 11 | 2025-02-28 | 2025-02 | 2 | 90 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/9 | 2024-11-30 | 2024-11 | 11 | 2025-03-16 | 2025-03 | 3 | 106 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 38/2 | 2024-11-30 | 2024-11 | 11 | 2025-05-02 | 2025-05 | 5 | 153 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/9 | 2024-12-05 | 2024-12 | 12 | 2025-01-22 | 2025-01 | 1 | 48 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/2 | 2024-12-06 | 2024-12 | 12 | 2025-02-04 | 2025-02 | 2 | 60 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 18/1 | 2024-12-07 | 2024-12 | 12 | 2024-12-26 | 2024-12 | 12 | 19 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 37/5 | 2024-12-07 | 2024-12 | 12 | 2025-03-29 | 2025-03 | 3 | 112 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 35/2 | 2024-12-08 | 2024-12 | 12 | 2025-06-25 | 2025-06 | 6 | 199 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 18/2 | 2024-12-09 | 2024-12 | 12 | 2024-12-23 | 2024-12 | 12 | 14 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/2 | 2024-12-10 | 2024-12 | 12 | 2025-09-27 | 2025-09 | 9 | 291 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/0 | 2024-12-11 | 2024-12 | 12 | 2025-08-01 | 2025-08 | 8 | 233 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 31/3 | 2024-12-11 | 2024-12 | 12 | 2025-06-01 | 2025-06 | 6 | 172 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/10 | 2024-12-12 | 2024-12 | 12 | 2025-03-20 | 2025-03 | 3 | 98 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 38/4 | 2024-12-12 | 2024-12 | 12 | 2025-03-10 | 2025-03 | 3 | 88 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/6 | 2024-12-13 | 2024-12 | 12 | 2025-02-24 | 2025-02 | 2 | 73 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/5 | 2024-12-13 | 2024-12 | 12 | 2025-06-05 | 2025-06 | 6 | 174 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/1 | 2024-12-14 | 2024-12 | 12 | 2024-12-28 | 2024-12 | 12 | 14 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 31/5 | 2024-12-15 | 2024-12 | 12 | 2025-02-10 | 2025-02 | 2 | 57 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/4 | 2024-12-15 | 2024-12 | 12 | 2025-06-24 | 2025-06 | 6 | 191 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 35/3 | 2024-12-16 | 2024-12 | 12 | 2025-04-15 | 2025-04 | 4 | 120 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 31/2 | 2024-12-19 | 2024-12 | 12 | 2025-02-21 | 2025-02 | 2 | 64 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 38/5 | 2024-12-20 | 2024-12 | 12 | 2025-03-15 | 2025-03 | 3 | 85 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 30/2 | 2024-12-21 | 2024-12 | 12 | 2024-12-02 | 2024-12 | 12 | -19 | Yes | Yes | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/3 | 2024-12-22 | 2024-12 | 12 | 2025-03-13 | 2025-03 | 3 | 81 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 38/7 | 2024-12-22 | 2024-12 | 12 | 2025-03-24 | 2025-03 | 3 | 92 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/3 | 2024-12-23 | 2024-12 | 12 | 2025-06-29 | 2025-06 | 6 | 188 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/11 | 2024-12-23 | 2024-12 | 12 | 2025-11-16 | 2025-11 | 11 | 328 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 31/4 | 2024-12-23 | 2024-12 | 12 | 2025-02-04 | 2025-02 | 2 | 43 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 37/4 | 2024-12-24 | 2024-12 | 12 | 2025-04-18 | 2025-04 | 4 | 115 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 25/3 | 2024-12-25 | 2024-12 | 12 | 2025-02-10 | 2025-02 | 2 | 47 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/10 | 2024-12-27 | 2024-12 | 12 | 2025-01-22 | 2025-01 | 1 | 26 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 31/0 | 2024-12-28 | 2024-12 | 12 | 2025-03-02 | 2025-03 | 3 | 64 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/2 | 2024-12-30 | 2024-12 | 12 | 2025-06-25 | 2025-06 | 6 | 177 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/0 | 2024-12-30 | 2024-12 | 12 | 2025-05-03 | 2025-05 | 5 | 124 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/8 | 2024-12-31 | 2024-12 | 12 | 2025-01-18 | 2025-01 | 1 | 18 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 28/0 | 2024-12-31 | 2024-12 | 12 | 2025-04-24 | 2025-04 | 4 | 114 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 38/6 | 2024-12-31 | 2024-12 | 12 | 2025-03-20 | 2025-03 | 3 | 79 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/2 | 2025-01-03 | 2025-01 | 1 | 2025-01-19 | 2025-01 | 1 | 16 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/7 | 2025-01-04 | 2025-01 | 1 | 2025-10-10 | 2025-10 | 10 | 279 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/4 | 2025-01-05 | 2025-01 | 1 | 2025-10-23 | 2025-10 | 10 | 291 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/7 | 2025-01-05 | 2025-01 | 1 | 2025-07-08 | 2025-07 | 7 | 184 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 19/1 | 2025-01-05 | 2025-01 | 1 | 2025-03-28 | 2025-03 | 3 | 82 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/8 | 2025-01-05 | 2025-01 | 1 | 2025-10-21 | 2025-10 | 10 | 289 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/7 | 2025-01-06 | 2025-01 | 1 | 2025-02-26 | 2025-02 | 2 | 51 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/6 | 2025-01-09 | 2025-01 | 1 | 2025-05-11 | 2025-05 | 5 | 122 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/5 | 2025-01-10 | 2025-01 | 1 | 2025-01-30 | 2025-01 | 1 | 20 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 31/6 | 2025-01-12 | 2025-01 | 1 | 2025-02-15 | 2025-02 | 2 | 34 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/7 | 2025-01-13 | 2025-01 | 1 | 2025-03-03 | 2025-03 | 3 | 49 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 38/0 | 2025-01-15 | 2025-01 | 1 | 2025-04-05 | 2025-04 | 4 | 80 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 17/0 | 2025-01-16 | 2025-01 | 1 | 2025-05-10 | 2025-05 | 5 | 114 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 33/0 | 2025-01-16 | 2025-01 | 1 | 2025-04-02 | 2025-04 | 4 | 76 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 37/6 | 2025-01-16 | 2025-01 | 1 | 2025-05-11 | 2025-05 | 5 | 115 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/1 | 2025-01-17 | 2025-01 | 1 | 2025-05-05 | 2025-05 | 5 | 108 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 17/2 | 2025-01-18 | 2025-01 | 1 | 2025-04-27 | 2025-04 | 4 | 99 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/5 | 2025-01-18 | 2025-01 | 1 | 2025-04-14 | 2025-04 | 4 | 86 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/0 | 2025-01-19 | 2025-01 | 1 | 2025-04-19 | 2025-04 | 4 | 90 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/2 | 2025-01-21 | 2025-01 | 1 | 2025-01-30 | 2025-01 | 1 | 9 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 33/2 | 2025-01-22 | 2025-01 | 1 | 2025-06-05 | 2025-06 | 6 | 134 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/4 | 2025-01-24 | 2025-01 | 1 | 2025-04-22 | 2025-04 | 4 | 88 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/5 | 2025-01-24 | 2025-01 | 1 | 2025-08-08 | 2025-08 | 8 | 196 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 33/1 | 2025-01-25 | 2025-01 | 1 | 2025-03-13 | 2025-03 | 3 | 47 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 37/1 | 2025-01-25 | 2025-01 | 1 | 2025-12-13 | 2025-12 | 12 | 322 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/0 | 2025-01-27 | 2025-01 | 1 | 2025-07-03 | 2025-07 | 7 | 157 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 32/1 | 2025-01-27 | 2025-01 | 1 | 2025-03-08 | 2025-03 | 3 | 40 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/6 | 2025-01-28 | 2025-01 | 1 | 2025-10-14 | 2025-10 | 10 | 259 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 32/2 | 2025-01-29 | 2025-01 | 1 | 2025-03-23 | 2025-03 | 3 | 53 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/2 | 2025-01-30 | 2025-01 | 1 | 2025-05-14 | 2025-05 | 5 | 104 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 14/0 | 2025-01-30 | 2025-01 | 1 | 2025-07-05 | 2025-07 | 7 | 156 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/3 | 2025-01-30 | 2025-01 | 1 | 2025-03-01 | 2025-03 | 3 | 30 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 37/2 | 2025-01-30 | 2025-01 | 1 | 2025-04-24 | 2025-04 | 4 | 84 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 19/0 | 2025-01-31 | 2025-01 | 1 | 2025-05-15 | 2025-05 | 5 | 104 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 35/1 | 2025-01-31 | 2025-01 | 1 | 2025-05-08 | 2025-05 | 5 | 97 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/8 | 2025-01-31 | 2025-01 | 1 | 2025-11-06 | 2025-11 | 11 | 279 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 35/4 | 2025-02-02 | 2025-02 | 2 | 2025-04-10 | 2025-04 | 4 | 67 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/1 | 2025-02-04 | 2025-02 | 2 | 2025-05-18 | 2025-05 | 5 | 103 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/1 | 2025-02-06 | 2025-02 | 2 | 2025-03-30 | 2025-03 | 3 | 52 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/10 | 2025-02-06 | 2025-02 | 2 | 2025-07-08 | 2025-07 | 7 | 152 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/0 | 2025-02-09 | 2025-02 | 2 | 2025-11-08 | 2025-11 | 11 | 272 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/9 | 2025-02-09 | 2025-02 | 2 | 2025-09-01 | 2025-09 | 9 | 204 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/0 | 2025-02-10 | 2025-02 | 2 | 2025-04-03 | 2025-04 | 4 | 52 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 37/0 | 2025-02-10 | 2025-02 | 2 | 2025-11-20 | 2025-11 | 11 | 283 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/4 | 2025-02-12 | 2025-02 | 2 | 2025-05-10 | 2025-05 | 5 | 87 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 32/0 | 2025-02-13 | 2025-02 | 2 | 2025-03-17 | 2025-03 | 3 | 32 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/2 | 2025-02-14 | 2025-02 | 2 | 2025-04-06 | 2025-04 | 4 | 51 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/7 | 2025-02-14 | 2025-02 | 2 | 2025-07-17 | 2025-07 | 7 | 153 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/3 | 2025-02-15 | 2025-02 | 2 | 2025-05-21 | 2025-05 | 5 | 95 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/5 | 2025-02-16 | 2025-02 | 2 | 2025-05-29 | 2025-05 | 5 | 102 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/0 | 2025-02-16 | 2025-02 | 2 | 2025-07-13 | 2025-07 | 7 | 147 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/5 | 2025-02-16 | 2025-02 | 2 | 2025-07-26 | 2025-07 | 7 | 160 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/9 | 2025-02-18 | 2025-02 | 2 | 2025-11-27 | 2025-11 | 11 | 282 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/9 | 2025-02-19 | 2025-02 | 2 | 2025-05-07 | 2025-05 | 5 | 77 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 35/0 | 2025-02-20 | 2025-02 | 2 | 2025-07-17 | 2025-07 | 7 | 147 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/8 | 2025-02-20 | 2025-02 | 2 | 2025-07-13 | 2025-07 | 7 | 143 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/8 | 2025-02-21 | 2025-02 | 2 | 2025-03-12 | 2025-03 | 3 | 19 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/4 | 2025-02-21 | 2025-02 | 2 | 2025-07-12 | 2025-07 | 7 | 141 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/6 | 2025-02-21 | 2025-02 | 2 | 2025-08-05 | 2025-08 | 8 | 165 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/7 | 2025-02-23 | 2025-02 | 2 | 2025-05-01 | 2025-05 | 5 | 67 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/5 | 2025-02-23 | 2025-02 | 2 | 2025-07-30 | 2025-07 | 7 | 157 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/6 | 2025-02-24 | 2025-02 | 2 | 2025-07-21 | 2025-07 | 7 | 147 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/6 | 2025-02-25 | 2025-02 | 2 | 2025-06-19 | 2025-06 | 6 | 114 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/4 | 2025-02-27 | 2025-02 | 2 | 2025-08-13 | 2025-08 | 8 | 167 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/7 | 2025-02-28 | 2025-02 | 2 | 2025-08-16 | 2025-08 | 8 | 169 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/3 | 2025-02-28 | 2025-02 | 2 | 2025-10-07 | 2025-10 | 10 | 221 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/3 | 2025-03-01 | 2025-03 | 3 | 2025-07-21 | 2025-07 | 7 | 142 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 15/0 | 2025-03-04 | 2025-03 | 3 | 2025-06-24 | 2025-06 | 6 | 112 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/4 | 2025-03-04 | 2025-03 | 3 | 2025-04-19 | 2025-04 | 4 | 46 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/2 | 2025-03-04 | 2025-03 | 3 | 2025-08-19 | 2025-08 | 8 | 168 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 40/0 | 2025-03-06 | 2025-03 | 3 | 2025-08-13 | 2025-08 | 8 | 160 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/2 | 2025-03-07 | 2025-03 | 3 | 2025-10-17 | 2025-10 | 10 | 224 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/1 | 2025-03-07 | 2025-03 | 3 | 2025-08-12 | 2025-08 | 8 | 158 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/5 | 2025-03-08 | 2025-03 | 3 | 2025-04-22 | 2025-04 | 4 | 45 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 32/3 | 2025-03-08 | 2025-03 | 3 | 2025-03-28 | 2025-03 | 3 | 20 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 40/1 | 2025-03-12 | 2025-03 | 3 | 2025-08-30 | 2025-08 | 8 | 171 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/1 | 2025-03-13 | 2025-03 | 3 | 2025-04-11 | 2025-04 | 4 | 29 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/15 | 2025-03-13 | 2025-03 | 3 | 2025-08-31 | 2025-08 | 8 | 171 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/3 | 2025-03-18 | 2025-03 | 3 | 2025-04-16 | 2025-04 | 4 | 29 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/14 | 2025-03-18 | 2025-03 | 3 | 2025-07-22 | 2025-07 | 7 | 126 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/7 | 2025-03-19 | 2025-03 | 3 | 2025-10-28 | 2025-10 | 10 | 223 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/0 | 2025-03-24 | 2025-03 | 3 | 2025-08-14 | 2025-08 | 8 | 143 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 34/1 | 2025-03-26 | 2025-03 | 3 | 2025-08-04 | 2025-08 | 8 | 131 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/12 | 2025-03-28 | 2025-03 | 3 | 2025-08-08 | 2025-08 | 8 | 133 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/11 | 2025-03-30 | 2025-03 | 3 | 2025-04-28 | 2025-04 | 4 | 29 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 15/3 | 2025-04-08 | 2025-04 | 4 | 2025-04-25 | 2025-04 | 4 | 17 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 34/2 | 2025-04-11 | 2025-04 | 4 | 2025-07-05 | 2025-07 | 7 | 85 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/8 | 2025-04-14 | 2025-04 | 4 | 2025-11-15 | 2025-11 | 11 | 215 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 6/2 | 2025-04-18 | 2025-04 | 4 | 2025-07-19 | 2025-07 | 7 | 92 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 37/3 | 2025-04-19 | 2025-04 | 4 | 2025-05-06 | 2025-05 | 5 | 17 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 6/1 | 2025-04-22 | 2025-04 | 4 | 2025-07-22 | 2025-07 | 7 | 91 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 20/0 | 2025-04-25 | 2025-04 | 4 | 2025-05-10 | 2025-05 | 5 | 15 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 6/6 | 2025-04-27 | 2025-04 | 4 | 2025-08-02 | 2025-08 | 8 | 97 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/1 | 2025-04-28 | 2025-04 | 4 | 2025-07-29 | 2025-07 | 7 | 92 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 6/7 | 2025-04-29 | 2025-04 | 4 | 2025-12-14 | 2025-12 | 12 | 229 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 20A/0 | 2025-04-30 | 2025-04 | 4 | 2025-06-20 | 2025-06 | 6 | 51 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 34/0 | 2025-05-03 | 2025-05 | 5 | 2025-06-17 | 2025-06 | 6 | 45 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/8 | 2025-05-03 | 2025-05 | 5 | 2025-07-30 | 2025-07 | 7 | 88 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/7 | 2025-05-04 | 2025-05 | 5 | 2025-09-08 | 2025-09 | 9 | 127 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/7 | 2025-05-04 | 2025-05 | 5 | 2025-08-03 | 2025-08 | 8 | 91 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/8 | 2025-05-07 | 2025-05 | 5 | 2026-01-03 | 2026-01 | 1 | 241 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/9 | 2025-05-08 | 2025-05 | 5 | 2025-09-08 | 2025-09 | 9 | 123 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 41/0 | 2025-05-11 | 2025-05 | 5 | 2025-09-06 | 2025-09 | 9 | 118 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/9 | 2025-05-11 | 2025-05 | 5 | 2025-09-10 | 2025-09 | 9 | 122 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/5 | 2025-05-12 | 2025-05 | 5 | 2025-12-05 | 2025-12 | 12 | 207 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/6 | 2025-05-13 | 2025-05 | 5 | 2025-09-05 | 2025-09 | 9 | 115 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/10 | 2025-05-13 | 2025-05 | 5 | 2025-11-20 | 2025-11 | 11 | 191 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/9 | 2025-05-15 | 2025-05 | 5 | 2025-09-07 | 2025-09 | 9 | 115 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/6 | 2025-05-15 | 2025-05 | 5 | 2025-07-14 | 2025-07 | 7 | 60 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/12 | 2025-05-16 | 2025-05 | 5 | 2025-09-09 | 2025-09 | 9 | 116 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/3 | 2025-05-17 | 2025-05 | 5 | 2025-10-10 | 2025-10 | 10 | 146 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 6/3 | 2025-05-19 | 2025-05 | 5 | 2025-07-15 | 2025-07 | 7 | 57 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/19 | 2025-05-20 | 2025-05 | 5 | 2025-10-17 | 2025-10 | 10 | 150 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/5 | 2025-05-20 | 2025-05 | 5 | 2025-11-28 | 2025-11 | 11 | 192 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 6/4 | 2025-05-20 | 2025-05 | 5 | 2025-07-11 | 2025-07 | 7 | 52 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/18 | 2025-05-21 | 2025-05 | 5 | 2025-09-28 | 2025-09 | 9 | 130 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43A/2 | 2025-05-22 | 2025-05 | 5 | 2026-01-08 | 2026-01 | 1 | 231 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/11 | 2025-05-22 | 2025-05 | 5 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 6/5 | 2025-05-23 | 2025-05 | 5 | 2025-07-04 | 2025-07 | 7 | 42 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43A/3 | 2025-05-25 | 2025-05 | 5 | 2025-11-23 | 2025-11 | 11 | 182 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/4 | 2025-05-25 | 2025-05 | 5 | 2025-10-17 | 2025-10 | 10 | 145 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/17 | 2025-05-27 | 2025-05 | 5 | 2025-09-16 | 2025-09 | 9 | 112 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/14 | 2025-05-28 | 2025-05 | 5 | 2025-11-18 | 2025-11 | 11 | 174 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43A/4 | 2025-05-28 | 2025-05 | 5 | 2025-11-18 | 2025-11 | 11 | 174 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/15 | 2025-05-30 | 2025-05 | 5 | 2025-11-21 | 2025-11 | 11 | 175 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/13 | 2025-05-30 | 2025-05 | 5 | 2025-08-05 | 2025-08 | 8 | 67 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 3/3 | 2025-05-31 | 2025-05 | 5 | 2025-12-20 | 2025-12 | 12 | 203 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/0 | 2025-05-31 | 2025-05 | 5 | 2025-09-05 | 2025-09 | 9 | 97 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/16 | 2025-05-31 | 2025-05 | 5 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 43A/5 | 2025-05-31 | 2025-05 | 5 | 2025-11-11 | 2025-11 | 11 | 164 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/13 | 2025-06-01 | 2025-06 | 6 | 2025-10-31 | 2025-10 | 10 | 152 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/2 | 2025-06-03 | 2025-06 | 6 | 2025-09-21 | 2025-09 | 9 | 110 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43/3 | 2025-06-04 | 2025-06 | 6 | 2025-10-07 | 2025-10 | 10 | 125 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 3/0 | 2025-06-06 | 2025-06 | 6 | 2025-11-11 | 2025-11 | 11 | 158 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 1B/3 | 2025-06-08 | 2025-06 | 6 | 2025-12-07 | 2025-12 | 12 | 182 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 28/1 | 2025-06-08 | 2025-06 | 6 | 2026-01-07 | 2026-01 | 1 | 213 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43/2 | 2025-06-09 | 2025-06 | 6 | 2025-09-24 | 2025-09 | 9 | 107 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 2/5 | 2025-06-14 | 2025-06 | 6 | 2025-12-24 | 2025-12 | 12 | 193 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/8 | 2025-06-14 | 2025-06 | 6 | 2025-09-01 | 2025-09 | 9 | 79 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 1B/2 | 2025-06-15 | 2025-06 | 6 | 2025-12-04 | 2025-12 | 12 | 172 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/1 | 2025-06-15 | 2025-06 | 6 | 2025-10-22 | 2025-10 | 10 | 129 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 3/1 | 2025-06-17 | 2025-06 | 6 | 2025-11-06 | 2025-11 | 11 | 142 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 1B/0 | 2025-06-19 | 2025-06 | 6 | 2025-12-09 | 2025-12 | 12 | 173 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 1A/0 | 2025-06-21 | 2025-06 | 6 | 2025-08-20 | 2025-08 | 8 | 60 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 1B/1 | 2025-06-21 | 2025-06 | 6 | 2025-11-30 | 2025-11 | 11 | 162 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 3/2 | 2025-06-21 | 2025-06 | 6 | 2025-12-17 | 2025-12 | 12 | 179 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43/1 | 2025-06-21 | 2025-06 | 6 | 2025-10-26 | 2025-10 | 10 | 127 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 2/3 | 2025-06-23 | 2025-06 | 6 | 2025-08-31 | 2025-08 | 8 | 69 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43/4 | 2025-06-24 | 2025-06 | 6 | 2025-09-21 | 2025-09 | 9 | 89 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/2 | 2025-06-25 | 2025-06 | 6 | 2025-12-17 | 2025-12 | 12 | 175 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 1C/0 | 2025-06-29 | 2025-06 | 6 | 2025-12-26 | 2025-12 | 12 | 180 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 2/1 | 2025-06-29 | 2025-06 | 6 | 2025-12-11 | 2025-12 | 12 | 165 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43/0 | 2025-06-30 | 2025-06 | 6 | 2025-12-01 | 2025-12 | 12 | 154 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 2/2 | 2025-07-03 | 2025-07 | 7 | 2025-09-25 | 2025-09 | 9 | 84 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/4 | 2025-07-08 | 2025-07 | 7 | 2025-11-10 | 2025-11 | 11 | 125 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 2/0 | 2025-07-10 | 2025-07 | 7 | 2025-12-31 | 2025-12 | 12 | 174 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 2/4 | 2025-07-12 | 2025-07 | 7 | 2025-12-22 | 2025-12 | 12 | 163 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 6/0 | 2025-07-13 | 2025-07 | 7 | 2025-11-27 | 2025-11 | 11 | 137 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43/5 | 2025-07-14 | 2025-07 | 7 | 2025-10-12 | 2025-10 | 10 | 90 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 5/0 | 2025-07-16 | 2025-07 | 7 | 2025-09-21 | 2025-09 | 9 | 67 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/3 | 2025-07-18 | 2025-07 | 7 | 2025-11-04 | 2025-11 | 11 | 109 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43A/1 | 2025-07-20 | 2025-07 | 7 | 2025-12-30 | 2025-12 | 12 | 163 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/1 | 2025-07-22 | 2025-07 | 7 | 2025-12-27 | 2025-12 | 12 | 158 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43B/0 | 2025-07-28 | 2025-07 | 7 | 2025-11-04 | 2025-11 | 11 | 99 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43A/0 | 2025-08-03 | 2025-08 | 8 | 2025-12-19 | 2025-12 | 12 | 138 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 1/0 | 2025-08-25 | 2025-08 | 8 | 2025-10-01 | 2025-10 | 10 | 37 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 19/0-20/0 | 2025-10-19 | 2025-10 | 10 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 18/0-19/0 | 2025-10-21 | 2025-10 | 10 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 44/0 | 2025-10-26 | 2025-10 | 10 | 2025-12-10 | 2025-12 | 12 | 45 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 7/0 | 2025-11-26 | 2025-11 | 11 | 2025-12-09 | 2025-12 | 12 | 13 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/0 | 2025-12-05 | 2025-12 | 12 | 2025-12-22 | 2025-12 | 12 | 17 | Yes | No | exact |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 7/0 - 8/0 | 2026-01-31 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | Gantry - 1/0 | 2026-02-01 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 8/2 - 8/3 | 2026-02-04 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 1/0-1A/0 | 2026-02-08 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 1A/0 - 1B/0 | 2026-02-11 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 4/12 - 5/0 | 2026-02-12 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 8/0 - 8/1 | 2026-02-19 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 8/1-8/2 | 2026-02-19 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 1C/0 - 2/0 | 2026-02-25 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 5/0 - 6/0 | 2026-03-02 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 3/0-4/0 | 2026-03-14 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 43A/0 - 43A/1 | 2026-06-18 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 43A/1 - 43B/0 | 2026-06-21 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 43B/0 - 44/0 | 2026-06-24 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 505 | 5xx | Government | ta505 | 164/3 | 2024-03-28 | 2024-03 | 3 | 2025-12-25 | 2025-12 | 12 | 637 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/4 | 2024-04-04 | 2024-04 | 4 | 2026-01-04 | 2026-01 | 1 | 640 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 136/0 | 2024-04-28 | 2024-04 | 4 | 2025-09-19 | 2025-09 | 9 | 509 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/2 | 2024-10-06 | 2024-10 | 10 | 2025-01-14 | 2025-01 | 1 | 100 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 109/2 | 2024-10-07 | 2024-10 | 10 | 2025-02-25 | 2025-02 | 2 | 141 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/3 | 2024-10-11 | 2024-10 | 10 | 2025-01-24 | 2025-01 | 1 | 105 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110A/2 | 2024-10-11 | 2024-10 | 10 | 2025-09-10 | 2025-09 | 9 | 334 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/4 | 2024-10-21 | 2024-10 | 10 | 2025-01-27 | 2025-01 | 1 | 98 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/6 | 2024-10-24 | 2024-10 | 10 | 2025-03-15 | 2025-03 | 3 | 142 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/5 | 2024-10-25 | 2024-10 | 10 | 2025-02-01 | 2025-02 | 2 | 99 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 108/4 | 2024-10-28 | 2024-10 | 10 | 2025-04-03 | 2025-04 | 4 | 157 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 109/1 | 2024-10-29 | 2024-10 | 10 | 2025-03-01 | 2025-03 | 3 | 123 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/6 | 2024-11-02 | 2024-11 | 11 | 2025-02-05 | 2025-02 | 2 | 95 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 111/1 | 2024-11-04 | 2024-11 | 11 | 2025-05-02 | 2025-05 | 5 | 179 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/8 | 2024-11-08 | 2024-11 | 11 | 2025-02-13 | 2025-02 | 2 | 97 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110A/1 | 2024-11-10 | 2024-11 | 11 | 2025-03-26 | 2025-03 | 3 | 136 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/1 | 2024-11-14 | 2024-11 | 11 | 2025-01-21 | 2025-01 | 1 | 68 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 113/2 | 2024-11-14 | 2024-11 | 11 | 2025-04-11 | 2025-04 | 4 | 148 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/8 | 2024-11-15 | 2024-11 | 11 | 2025-03-30 | 2025-03 | 3 | 135 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/3 | 2024-11-17 | 2024-11 | 11 | 2025-03-22 | 2025-03 | 3 | 125 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/7 | 2024-11-18 | 2024-11 | 11 | 2025-02-09 | 2025-02 | 2 | 83 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 111/2 | 2024-11-18 | 2024-11 | 11 | 2025-05-09 | 2025-05 | 5 | 172 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 105/1 | 2024-11-19 | 2024-11 | 11 | 2025-04-26 | 2025-04 | 4 | 158 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/10 | 2024-11-20 | 2024-11 | 11 | 2025-04-06 | 2025-04 | 4 | 137 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/1 | 2024-11-22 | 2024-11 | 11 | 2025-03-05 | 2025-03 | 3 | 103 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 113/1 | 2024-11-22 | 2024-11 | 11 | 2025-04-18 | 2025-04 | 4 | 147 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/5 | 2024-11-23 | 2024-11 | 11 | 2025-02-21 | 2025-02 | 2 | 90 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/8 | 2024-11-23 | 2024-11 | 11 | 2025-09-19 | 2025-09 | 9 | 300 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 104/1 | 2024-11-27 | 2024-11 | 11 | 2025-04-18 | 2025-04 | 4 | 142 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/9 | 2024-11-27 | 2024-11 | 11 | 2025-03-30 | 2025-03 | 3 | 123 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/7 | 2024-11-28 | 2024-11 | 11 | 2025-04-18 | 2025-04 | 4 | 141 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/2 | 2024-11-29 | 2024-11 | 11 | 2025-03-19 | 2025-03 | 3 | 110 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/7 | 2024-11-29 | 2024-11 | 11 | 2025-02-17 | 2025-02 | 2 | 80 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 113/3 | 2024-11-29 | 2024-11 | 11 | 2025-04-01 | 2025-04 | 4 | 123 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 105/0 | 2024-11-30 | 2024-11 | 11 | 2025-09-21 | 2025-09 | 9 | 295 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 108/2 | 2024-11-30 | 2024-11 | 11 | 2025-04-12 | 2025-04 | 4 | 133 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 109/3 | 2024-11-30 | 2024-11 | 11 | 2025-03-06 | 2025-03 | 3 | 96 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/6 | 2024-11-30 | 2024-11 | 11 | 2025-03-07 | 2025-03 | 3 | 97 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 116/2 | 2024-12-01 | 2024-12 | 12 | 2025-05-02 | 2025-05 | 5 | 152 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 104/2 | 2024-12-03 | 2024-12 | 12 | 2025-04-22 | 2025-04 | 4 | 140 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 113/5 | 2024-12-05 | 2024-12 | 12 | 2025-03-29 | 2025-03 | 3 | 114 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/3 | 2024-12-07 | 2024-12 | 12 | 2025-04-17 | 2025-04 | 4 | 131 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/5 | 2024-12-07 | 2024-12 | 12 | 2025-03-30 | 2025-03 | 3 | 113 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 111/3 | 2024-12-08 | 2024-12 | 12 | 2025-05-06 | 2025-05 | 5 | 149 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 113/4 | 2024-12-09 | 2024-12 | 12 | 2025-03-12 | 2025-03 | 3 | 93 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 127/3 | 2024-12-10 | 2024-12 | 12 | 2025-05-27 | 2025-05 | 5 | 168 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 113/6 | 2024-12-12 | 2024-12 | 12 | 2025-04-24 | 2025-04 | 4 | 133 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 108/1 | 2024-12-13 | 2024-12 | 12 | 2025-04-15 | 2025-04 | 4 | 123 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 102/0 | 2024-12-14 | 2024-12 | 12 | 2025-10-13 | 2025-10 | 10 | 303 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/2 | 2024-12-14 | 2024-12 | 12 | 2025-04-12 | 2025-04 | 4 | 119 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 127/2 | 2024-12-15 | 2024-12 | 12 | 2025-05-08 | 2025-05 | 5 | 144 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 111/4 | 2024-12-16 | 2024-12 | 12 | 2025-04-30 | 2025-04 | 4 | 135 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 126/0 | 2024-12-16 | 2024-12 | 12 | 2025-08-17 | 2025-08 | 8 | 244 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/0 | 2024-12-17 | 2024-12 | 12 | 2026-01-20 | 2026-01 | 1 | 399 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 126/4 | 2024-12-17 | 2024-12 | 12 | 2025-05-17 | 2025-05 | 5 | 151 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 108/3 | 2024-12-19 | 2024-12 | 12 | 2025-04-08 | 2025-04 | 4 | 110 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/0 | 2024-12-19 | 2024-12 | 12 | 2025-10-22 | 2025-10 | 10 | 307 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 147A/4 | 2024-12-19 | 2024-12 | 12 | 2025-06-01 | 2025-06 | 6 | 164 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 127/1 | 2024-12-20 | 2024-12 | 12 | 2025-05-13 | 2025-05 | 5 | 144 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 150/3 | 2024-12-21 | 2024-12 | 12 | 2025-06-11 | 2025-06 | 6 | 172 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/3 | 2024-12-22 | 2024-12 | 12 | 2025-05-14 | 2025-05 | 5 | 143 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 147A/5 | 2024-12-24 | 2024-12 | 12 | 2025-09-01 | 2025-09 | 9 | 251 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 150/4 | 2024-12-24 | 2024-12 | 12 | 2025-06-27 | 2025-06 | 6 | 185 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 116/1 | 2024-12-26 | 2024-12 | 12 | 2025-05-08 | 2025-05 | 5 | 133 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152/2 | 2024-12-26 | 2024-12 | 12 | 2025-12-28 | 2025-12 | 12 | 367 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 147A/1 | 2024-12-27 | 2024-12 | 12 | 2025-09-20 | 2025-09 | 9 | 267 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/4 | 2024-12-27 | 2024-12 | 12 | 2025-05-27 | 2025-05 | 5 | 151 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 150/5 | 2024-12-28 | 2024-12 | 12 | 2025-06-06 | 2025-06 | 6 | 160 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 127/0 | 2024-12-29 | 2024-12 | 12 | 2025-08-01 | 2025-08 | 8 | 215 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/9 | 2024-12-29 | 2024-12 | 12 | 2025-06-17 | 2025-06 | 6 | 170 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152/1 | 2024-12-30 | 2024-12 | 12 | 2025-12-17 | 2025-12 | 12 | 352 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 109/0 | 2024-12-31 | 2024-12 | 12 | 2025-11-06 | 2025-11 | 11 | 310 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/1 | 2024-12-31 | 2024-12 | 12 | 2025-04-25 | 2025-04 | 4 | 115 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 147A/2 | 2024-12-31 | 2024-12 | 12 | 2025-06-07 | 2025-06 | 6 | 158 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/5 | 2025-01-02 | 2025-01 | 1 | 2025-10-05 | 2025-10 | 10 | 276 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 111/0 | 2025-01-04 | 2025-01 | 1 | 2025-08-18 | 2025-08 | 8 | 226 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 147/1 | 2025-01-05 | 2025-01 | 1 | 2025-06-26 | 2025-06 | 6 | 172 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/7 | 2025-01-05 | 2025-01 | 1 | 2025-12-25 | 2025-12 | 12 | 354 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/1 | 2025-01-10 | 2025-01 | 1 | 2025-05-17 | 2025-05 | 5 | 127 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 120/1 | 2025-01-12 | 2025-01 | 1 | 2025-04-27 | 2025-04 | 4 | 105 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 150/1 | 2025-01-12 | 2025-01 | 1 | 2025-07-07 | 2025-07 | 7 | 176 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/7 | 2025-01-15 | 2025-01 | 1 | 2025-07-15 | 2025-07 | 7 | 181 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 155/5 | 2025-01-15 | 2025-01 | 1 | 2025-05-28 | 2025-05 | 5 | 133 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 144A/1 | 2025-01-16 | 2025-01 | 1 | 2025-09-12 | 2025-09 | 9 | 239 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/8 | 2025-01-16 | 2025-01 | 1 | 2025-05-31 | 2025-05 | 5 | 135 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 131/0 | 2025-01-17 | 2025-01 | 1 | 2025-09-10 | 2025-09 | 9 | 236 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/0 | 2025-01-17 | 2025-01 | 1 | 2025-12-12 | 2025-12 | 12 | 329 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 126/2 | 2025-01-18 | 2025-01 | 1 | 2025-05-23 | 2025-05 | 5 | 125 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 144A/3 | 2025-01-19 | 2025-01 | 1 | 2025-10-19 | 2025-10 | 10 | 273 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 126/3 | 2025-01-20 | 2025-01 | 1 | 2025-11-10 | 2025-11 | 11 | 294 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/11 | 2025-01-21 | 2025-01 | 1 | 2026-04-01 | 2026-04 | 4 | 435 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 155/3 | 2025-01-21 | 2025-01 | 1 | 2025-05-23 | 2025-05 | 5 | 122 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 150/2 | 2025-01-22 | 2025-01 | 1 | 2025-07-01 | 2025-07 | 7 | 160 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/6 | 2025-01-23 | 2025-01 | 1 | 2025-12-20 | 2025-12 | 12 | 331 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 120/3 | 2025-01-24 | 2025-01 | 1 | 2025-05-02 | 2025-05 | 5 | 98 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152/3 | 2025-01-25 | 2025-01 | 1 | 2026-04-06 | 2026-04 | 4 | 436 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/10 | 2025-01-25 | 2025-01 | 1 | 2026-04-08 | 2026-04 | 4 | 438 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 112/0 | 2025-01-27 | 2025-01 | 1 | 2025-10-01 | 2025-10 | 10 | 247 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/2 | 2025-01-28 | 2025-01 | 1 | 2025-05-22 | 2025-05 | 5 | 114 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 120/2 | 2025-01-30 | 2025-01 | 1 | 2025-04-22 | 2025-04 | 4 | 82 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 154/1 | 2025-01-30 | 2025-01 | 1 | 2025-07-01 | 2025-07 | 7 | 152 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 128/0 | 2025-01-31 | 2025-01 | 1 | 2025-10-01 | 2025-10 | 10 | 243 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 130/1 | 2025-01-31 | 2025-01 | 1 | 2025-09-26 | 2025-09 | 9 | 238 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 148/0 | 2025-01-31 | 2025-01 | 1 | 2025-12-10 | 2025-12 | 12 | 313 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 154/2 | 2025-02-04 | 2025-02 | 2 | 2025-06-24 | 2025-06 | 6 | 140 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 140/1 | 2025-02-05 | 2025-02 | 2 | 2025-10-10 | 2025-10 | 10 | 247 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 156/4 | 2025-02-05 | 2025-02 | 2 | 2025-06-16 | 2025-06 | 6 | 131 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 129A/3 | 2025-02-06 | 2025-02 | 2 | 2025-05-19 | 2025-05 | 5 | 102 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 104/0 | 2025-02-07 | 2025-02 | 2 | 2025-08-23 | 2025-08 | 8 | 197 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 154/5 | 2025-02-08 | 2025-02 | 2 | 2025-05-16 | 2025-05 | 5 | 97 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 130/2 | 2025-02-09 | 2025-02 | 2 | 2025-11-23 | 2025-11 | 11 | 287 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 129A/2 | 2025-02-10 | 2025-02 | 2 | 2025-11-12 | 2025-11 | 11 | 275 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 155/4 | 2025-02-10 | 2025-02 | 2 | 2025-06-01 | 2025-06 | 6 | 111 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 129A/1 | 2025-02-11 | 2025-02 | 2 | 2025-06-08 | 2025-06 | 6 | 117 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 156/1 | 2025-02-12 | 2025-02 | 2 | 2025-06-08 | 2025-06 | 6 | 116 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 148A/0 | 2025-02-13 | 2025-02 | 2 | 2025-10-25 | 2025-10 | 10 | 254 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 130/0 | 2025-02-14 | 2025-02 | 2 | 2025-08-27 | 2025-08 | 8 | 194 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 160/3 | 2025-02-15 | 2025-02 | 2 | 2025-06-08 | 2025-06 | 6 | 113 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 159/3 | 2025-02-16 | 2025-02 | 2 | 2026-03-19 | 2026-03 | 3 | 396 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 109/4 | 2025-02-17 | 2025-02 | 2 | 2025-03-11 | 2025-03 | 3 | 22 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 135/1 | 2025-02-17 | 2025-02 | 2 | 2025-11-03 | 2025-11 | 11 | 259 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110A/0 | 2025-02-20 | 2025-02 | 2 | 2025-09-20 | 2025-09 | 9 | 212 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 135/2 | 2025-02-21 | 2025-02 | 2 | 2025-09-08 | 2025-09 | 9 | 199 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 135/3 | 2025-02-22 | 2025-02 | 2 | 2026-02-25 | 2026-02 | 2 | 368 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 156/3 | 2025-02-22 | 2025-02 | 2 | 2026-02-18 | 2026-02 | 2 | 361 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 155/1 | 2025-02-24 | 2025-02 | 2 | 2026-04-23 | 2026-04 | 4 | 423 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 159/0 | 2025-02-24 | 2025-02 | 2 | 2025-10-19 | 2025-10 | 10 | 237 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 136/1 | 2025-02-25 | 2025-02 | 2 | 2025-08-25 | 2025-08 | 8 | 181 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 160/0 | 2025-02-25 | 2025-02 | 2 | 2025-09-26 | 2025-09 | 9 | 213 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 164/5 | 2025-02-26 | 2025-02 | 2 | 2025-11-09 | 2025-11 | 11 | 256 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 118/0 | 2025-02-27 | 2025-02 | 2 | 2025-12-11 | 2025-12 | 12 | 287 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 136/5 | 2025-02-27 | 2025-02 | 2 | 2025-11-11 | 2025-11 | 11 | 257 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 161/4 | 2025-02-27 | 2025-02 | 2 | 2025-05-08 | 2025-05 | 5 | 70 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 154/3 | 2025-02-28 | 2025-02 | 2 | 2025-07-08 | 2025-07 | 7 | 130 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 155/2 | 2025-02-28 | 2025-02 | 2 | 2026-04-30 | 2026-04 | 4 | 426 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 160/2 | 2025-02-28 | 2025-02 | 2 | 2025-09-26 | 2025-09 | 9 | 210 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 160/1 | 2025-03-04 | 2025-03 | 3 | 2025-10-08 | 2025-10 | 10 | 218 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 135/0 | 2025-03-05 | 2025-03 | 3 | 2025-08-25 | 2025-08 | 8 | 173 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 161/2 | 2025-03-06 | 2025-03 | 3 | 2025-09-10 | 2025-09 | 9 | 188 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 164/6 | 2025-03-07 | 2025-03 | 3 | 2025-12-12 | 2025-12 | 12 | 280 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 160/4 | 2025-03-08 | 2025-03 | 3 | 2025-05-24 | 2025-05 | 5 | 77 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 161/5 | 2025-03-11 | 2025-03 | 3 | 2025-12-31 | 2025-12 | 12 | 295 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 140/0 | 2025-03-12 | 2025-03 | 3 | 2025-12-01 | 2025-12 | 12 | 264 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 164/4 | 2025-03-16 | 2025-03 | 3 | 2025-12-18 | 2025-12 | 12 | 277 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 159/1 | 2025-03-19 | 2025-03 | 3 | 2025-04-22 | 2025-04 | 4 | 34 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 144A/0 | 2025-03-22 | 2025-03 | 3 | 2025-09-23 | 2025-09 | 9 | 185 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 161/1 | 2025-03-26 | 2025-03 | 3 | 2026-03-25 | 2026-03 | 3 | 364 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 144A/2 | 2025-03-28 | 2025-03 | 3 | 2026-03-22 | 2026-03 | 3 | 359 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/4 | 2025-03-28 | 2025-03 | 3 | 2025-12-04 | 2025-12 | 12 | 251 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/3 | 2025-03-29 | 2025-03 | 3 | 2025-12-28 | 2025-12 | 12 | 274 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/2 | 2025-03-30 | 2025-03 | 3 | 2026-05-02 | 2026-05 | 5 | 398 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 147/0 | 2025-03-31 | 2025-03 | 3 | 2026-02-26 | 2026-02 | 2 | 332 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 160/5 | 2025-03-31 | 2025-03 | 3 | 2025-05-08 | 2025-05 | 5 | 38 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 161/3 | 2025-03-31 | 2025-03 | 3 | 2025-05-28 | 2025-05 | 5 | 58 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 164/2 | 2025-03-31 | 2025-03 | 3 | 2026-01-28 | 2026-01 | 1 | 303 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/5 | 2025-03-31 | 2025-03 | 3 | 2025-11-30 | 2025-11 | 11 | 244 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/8 | 2025-03-31 | 2025-03 | 3 | 2025-11-07 | 2025-11 | 11 | 221 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 115/0 | 2025-04-03 | 2025-04 | 4 | 2025-09-24 | 2025-09 | 9 | 174 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 116/0 | 2025-04-07 | 2025-04 | 4 | 2025-10-05 | 2025-10 | 10 | 181 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/3 | 2025-04-07 | 2025-04 | 4 | 2025-09-22 | 2025-09 | 9 | 168 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/9 | 2025-04-07 | 2025-04 | 4 | 2026-04-01 | 2026-04 | 4 | 359 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 164/7 | 2025-04-08 | 2025-04 | 4 | 2025-12-04 | 2025-12 | 12 | 240 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/8 | 2025-04-08 | 2025-04 | 4 | 2025-11-14 | 2025-11 | 11 | 220 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 165/6 | 2025-04-09 | 2025-04 | 4 | 2025-11-03 | 2025-11 | 11 | 208 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 147A/0 | 2025-04-10 | 2025-04 | 4 | 2025-10-13 | 2025-10 | 10 | 186 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 147A/3 | 2025-04-10 | 2025-04 | 4 | 2025-06-11 | 2025-06 | 6 | 62 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 172/2 | 2025-04-10 | 2025-04 | 4 | 2025-11-29 | 2025-11 | 11 | 233 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/1 | 2025-04-11 | 2025-04 | 4 | 2025-11-21 | 2025-11 | 11 | 224 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 120/0 | 2025-04-12 | 2025-04 | 4 | 2025-09-08 | 2025-09 | 9 | 149 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 148/1 | 2025-04-12 | 2025-04 | 4 | 2025-09-30 | 2025-09 | 9 | 171 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/10 | 2025-04-12 | 2025-04 | 4 | 2026-04-04 | 2026-04 | 4 | 357 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 173/3 | 2025-04-12 | 2025-04 | 4 | 2025-12-31 | 2025-12 | 12 | 263 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 165/4 | 2025-04-13 | 2025-04 | 4 | 2026-01-09 | 2026-01 | 1 | 271 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/6 | 2025-04-13 | 2025-04 | 4 | 2025-11-25 | 2025-11 | 11 | 226 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/2 | 2025-04-14 | 2025-04 | 4 | 2025-10-22 | 2025-10 | 10 | 191 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 119/0 | 2025-04-15 | 2025-04 | 4 | 2025-08-25 | 2025-08 | 8 | 132 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 164/8 | 2025-04-15 | 2025-04 | 4 | 2025-11-25 | 2025-11 | 11 | 224 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 173/4 | 2025-04-16 | 2025-04 | 4 | 2026-01-02 | 2026-01 | 1 | 261 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/7 | 2025-04-17 | 2025-04 | 4 | 2025-11-14 | 2025-11 | 11 | 211 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 165/3 | 2025-04-18 | 2025-04 | 4 | 2026-04-11 | 2026-04 | 4 | 358 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 172/3 | 2025-04-18 | 2025-04 | 4 | 2025-11-18 | 2025-11 | 11 | 214 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/3 | 2025-04-20 | 2025-04 | 4 | 2026-04-05 | 2026-04 | 4 | 350 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/9 | 2025-04-20 | 2025-04 | 4 | 2025-11-04 | 2025-11 | 11 | 198 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 173/2 | 2025-04-20 | 2025-04 | 4 | 2025-12-13 | 2025-12 | 12 | 237 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/4 | 2025-04-22 | 2025-04 | 4 | 2025-10-27 | 2025-10 | 10 | 188 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 106/0 | 2025-04-22 | 2025-04 | 4 | 2025-08-04 | 2025-08 | 8 | 104 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 132/0 | 2025-04-22 | 2025-04 | 4 | 2025-12-17 | 2025-12 | 12 | 239 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/5 | 2025-04-22 | 2025-04 | 4 | 2026-04-09 | 2026-04 | 4 | 352 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/1 | 2025-04-22 | 2025-04 | 4 | 2026-04-09 | 2026-04 | 4 | 352 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/0 | 2025-04-24 | 2025-04 | 4 | 2025-11-08 | 2025-11 | 11 | 198 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/1 | 2025-04-24 | 2025-04 | 4 | 2025-10-31 | 2025-10 | 10 | 190 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 175/4 | 2025-04-24 | 2025-04 | 4 | 2026-04-08 | 2026-04 | 4 | 349 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 167/4 | 2025-04-26 | 2025-04 | 4 | 2025-09-26 | 2025-09 | 9 | 153 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/2 | 2025-04-26 | 2025-04 | 4 | 2026-03-05 | 2026-03 | 3 | 313 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 172/1 | 2025-04-26 | 2025-04 | 4 | 2025-12-07 | 2025-12 | 12 | 225 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 173/1 | 2025-04-26 | 2025-04 | 4 | 2025-10-27 | 2025-10 | 10 | 184 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 175/3 | 2025-04-26 | 2025-04 | 4 | 2026-04-13 | 2026-04 | 4 | 352 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 108/0 | 2025-04-27 | 2025-04 | 4 | 2025-08-12 | 2025-08 | 8 | 107 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 161/0 | 2025-04-28 | 2025-04 | 4 | 2025-10-16 | 2025-10 | 10 | 171 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/2 | 2025-04-28 | 2025-04 | 4 | 2026-02-14 | 2026-02 | 2 | 292 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/6 | 2025-04-28 | 2025-04 | 4 | 2026-03-26 | 2026-03 | 3 | 332 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 165/5 | 2025-04-29 | 2025-04 | 4 | 2026-01-19 | 2026-01 | 1 | 265 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 165/1 | 2025-04-30 | 2025-04 | 4 | 2026-03-10 | 2026-03 | 3 | 314 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 167/5 | 2025-04-30 | 2025-04 | 4 | 2025-09-14 | 2025-09 | 9 | 137 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 176/1 | 2025-04-30 | 2025-04 | 4 | 2026-03-22 | 2026-03 | 3 | 326 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/5A | 2025-05-03 | 2025-05 | 5 | 2025-08-21 | 2025-08 | 8 | 110 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 136/2 | 2025-05-03 | 2025-05 | 5 | 2025-11-23 | 2025-11 | 11 | 204 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 167/0 | 2025-05-03 | 2025-05 | 5 | 2025-10-16 | 2025-10 | 10 | 166 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 159/2 | 2025-05-04 | 2025-05 | 5 | 2025-09-13 | 2025-09 | 9 | 132 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/4 | 2025-05-04 | 2025-05 | 5 | 2025-09-30 | 2025-09 | 9 | 149 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/9 | 2025-05-04 | 2025-05 | 5 | 2026-01-15 | 2026-01 | 1 | 256 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 176/0 | 2025-05-04 | 2025-05 | 5 | 2026-03-15 | 2026-03 | 3 | 315 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/5A1 | 2025-05-05 | 2025-05 | 5 | 2025-08-04 | 2025-08 | 8 | 91 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 176/2 | 2025-05-06 | 2025-05 | 5 | 2026-04-16 | 2026-04 | 4 | 345 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/3 | 2025-05-08 | 2025-05 | 5 | 2025-09-10 | 2025-09 | 9 | 125 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 178/1 | 2025-05-08 | 2025-05 | 5 | 2026-02-03 | 2026-02 | 2 | 271 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 158/3 | 2025-05-09 | 2025-05 | 5 | 2025-08-25 | 2025-08 | 8 | 108 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 167/1 | 2025-05-09 | 2025-05 | 5 | 2025-10-26 | 2025-10 | 10 | 170 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 174A/3 | 2025-05-10 | 2025-05 | 5 | 2025-12-01 | 2025-12 | 12 | 205 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 176/3 | 2025-05-10 | 2025-05 | 5 | 2026-04-24 | 2026-04 | 4 | 349 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/1 | 2025-05-11 | 2025-05 | 5 | 2025-09-18 | 2025-09 | 9 | 130 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/5 | 2025-05-11 | 2025-05 | 5 | 2025-10-09 | 2025-10 | 10 | 151 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/2 | 2025-05-13 | 2025-05 | 5 | 2025-09-25 | 2025-09 | 9 | 135 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 141/0 | 2025-05-13 | 2025-05 | 5 | 2026-01-18 | 2026-01 | 1 | 250 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/1 | 2025-05-13 | 2025-05 | 5 | 2025-09-14 | 2025-09 | 9 | 124 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 158/2 | 2025-05-16 | 2025-05 | 5 | 2025-10-13 | 2025-10 | 10 | 150 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/0 | 2025-05-16 | 2025-05 | 5 | 2025-11-28 | 2025-11 | 11 | 196 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/8 | 2025-05-17 | 2025-05 | 5 | 2026-04-14 | 2026-04 | 4 | 332 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/1 | 2025-05-17 | 2025-05 | 5 | 2025-12-21 | 2025-12 | 12 | 218 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/6A | 2025-05-18 | 2025-05 | 5 | 2025-08-09 | 2025-08 | 8 | 83 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 178/0 | 2025-05-18 | 2025-05 | 5 | 2026-01-21 | 2026-01 | 1 | 248 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 142/0 | 2025-05-20 | 2025-05 | 5 | 2026-01-02 | 2026-01 | 1 | 227 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/4 | 2025-05-21 | 2025-05 | 5 | 2026-03-17 | 2026-03 | 3 | 300 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 172/4 | 2025-05-21 | 2025-05 | 5 | 2025-12-09 | 2025-12 | 12 | 202 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/2 | 2025-05-21 | 2025-05 | 5 | 2026-01-19 | 2026-01 | 1 | 243 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/0 | 2025-05-22 | 2025-05 | 5 | 2025-09-10 | 2025-09 | 9 | 111 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 172/6 | 2025-05-23 | 2025-05 | 5 | 2025-10-27 | 2025-10 | 10 | 157 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 174A/4 | 2025-05-23 | 2025-05 | 5 | 2026-04-26 | 2026-04 | 4 | 338 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/3 | 2025-05-23 | 2025-05 | 5 | 2025-12-28 | 2025-12 | 12 | 219 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/8 | 2025-05-24 | 2025-05 | 5 | 2025-07-25 | 2025-07 | 7 | 62 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/6 | 2025-05-25 | 2025-05 | 5 | 2025-09-11 | 2025-09 | 9 | 109 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/8 | 2025-05-25 | 2025-05 | 5 | 2026-03-09 | 2026-03 | 3 | 288 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 167/2 | 2025-05-27 | 2025-05 | 5 | 2025-10-02 | 2025-10 | 10 | 128 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/4 | 2025-05-27 | 2025-05 | 5 | 2026-01-03 | 2026-01 | 1 | 221 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 167/3 | 2025-05-29 | 2025-05 | 5 | 2025-10-10 | 2025-10 | 10 | 134 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 174A/5 | 2025-05-29 | 2025-05 | 5 | 2026-02-08 | 2026-02 | 2 | 255 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/5 | 2025-05-29 | 2025-05 | 5 | 2026-01-12 | 2026-01 | 1 | 228 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 172/5 | 2025-05-30 | 2025-05 | 5 | 2026-02-24 | 2026-02 | 2 | 270 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 178/3 | 2025-05-30 | 2025-05 | 5 | 2025-12-03 | 2025-12 | 12 | 187 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/0 | 2025-05-31 | 2025-05 | 5 | 2025-10-01 | 2025-10 | 10 | 123 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 150/0 | 2025-05-31 | 2025-05 | 5 | 2025-07-18 | 2025-07 | 7 | 48 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/6 | 2025-05-31 | 2025-05 | 5 | 2026-04-01 | 2026-04 | 4 | 305 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 121/0 | 2025-06-02 | 2025-06 | 6 | 2025-10-14 | 2025-10 | 10 | 134 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/7 | 2025-06-03 | 2025-06 | 6 | 2026-04-20 | 2026-04 | 4 | 321 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/7 | 2025-06-03 | 2025-06 | 6 | 2026-03-22 | 2026-03 | 3 | 292 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 174A/1 | 2025-06-04 | 2025-06 | 6 | 2025-12-10 | 2025-12 | 12 | 189 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 173/0 | 2025-06-05 | 2025-06 | 6 | 2025-12-22 | 2025-12 | 12 | 200 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/4 | 2025-06-07 | 2025-06 | 6 | 2025-08-12 | 2025-08 | 8 | 66 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/0 | 2025-06-08 | 2025-06 | 6 | 2026-03-30 | 2026-03 | 3 | 295 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/3 | 2025-06-08 | 2025-06 | 6 | 2026-03-22 | 2026-03 | 3 | 287 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 172/0 | 2025-06-09 | 2025-06 | 6 | 2026-01-27 | 2026-01 | 1 | 232 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152/0 | 2025-06-11 | 2025-06 | 6 | 2025-11-29 | 2025-11 | 11 | 171 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/12 | 2025-06-13 | 2025-06 | 6 | 2026-03-26 | 2026-03 | 3 | 286 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 174A/0 | 2025-06-13 | 2025-06 | 6 | 2025-11-10 | 2025-11 | 11 | 150 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 174A/2 | 2025-06-28 | 2025-06 | 6 | 2025-11-24 | 2025-11 | 11 | 149 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 151/0 | 2025-06-29 | 2025-06 | 6 | 2026-01-04 | 2026-01 | 1 | 189 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/6 | 2025-06-29 | 2025-06 | 6 | 2026-04-16 | 2026-04 | 4 | 291 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 156/0 | 2025-07-15 | 2025-07 | 7 | 2025-09-12 | 2025-09 | 9 | 59 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/7 | 2025-07-17 | 2025-07 | 7 | 2025-10-16 | 2025-10 | 10 | 91 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/7 | 2025-08-29 | 2025-08 | 8 | 2026-04-04 | 2026-04 | 4 | 218 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 178/4 | 2025-09-04 | 2025-09 | 9 | 2025-12-12 | 2025-12 | 12 | 99 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 178/5 | 2025-09-12 | 2025-09 | 9 | 2025-12-03 | 2025-12 | 12 | 82 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/6 | 2025-09-12 | 2025-09 | 9 | 2026-01-12 | 2026-01 | 1 | 122 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 145/0 | 2025-09-14 | 2025-09 | 9 | 2025-11-11 | 2025-11 | 11 | 58 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/4 | 2025-09-19 | 2025-09 | 9 | 2025-11-17 | 2025-11 | 11 | 59 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/1 | 2025-09-23 | 2025-09 | 9 | 2025-12-29 | 2025-12 | 12 | 97 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/4 | 2025-09-26 | 2025-09 | 9 | 2025-12-27 | 2025-12 | 12 | 92 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149B/3 | 2025-09-27 | 2025-09 | 9 | 2025-10-27 | 2025-10 | 10 | 30 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/2 | 2025-09-29 | 2025-09 | 9 | 2026-01-02 | 2026-01 | 1 | 95 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 154/4 | 2025-09-30 | 2025-09 | 9 | 2025-12-06 | 2025-12 | 12 | 67 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 126/1 | 2025-10-05 | 2025-10 | 10 | 2025-11-01 | 2025-11 | 11 | 27 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149B/1 | 2025-10-09 | 2025-10 | 10 | 2026-02-06 | 2026-02 | 2 | 120 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149B/2 | 2025-10-15 | 2025-10 | 10 | 2025-11-12 | 2025-11 | 11 | 28 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 100/0 | 2025-10-16 | 2025-10 | 10 | 2025-11-19 | 2025-11 | 11 | 34 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 178/2 | 2025-10-16 | 2025-10 | 10 | 2026-02-15 | 2026-02 | 2 | 122 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149B/4 | 2025-10-17 | 2025-10 | 10 | 2025-11-26 | 2025-11 | 11 | 40 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 155/0 | 2025-10-17 | 2025-10 | 10 | 2026-04-14 | 2026-04 | 4 | 179 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 99/8 | 2025-10-17 | 2025-10 | 10 | 2025-11-30 | 2025-11 | 11 | 44 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 165/0 | 2025-10-22 | 2025-10 | 10 | 2025-11-16 | 2025-11 | 11 | 25 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 168/0 | 2025-10-25 | 2025-10 | 10 | 2025-12-09 | 2025-12 | 12 | 45 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 99/6 | 2025-10-25 | 2025-10 | 10 | 2025-12-13 | 2025-12 | 12 | 49 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 180/0 | 2025-10-30 | 2025-10 | 10 | 2026-05-02 | 2026-05 | 5 | 184 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 99/4 | 2025-11-01 | 2025-11 | 11 | 2025-12-10 | 2025-12 | 12 | 39 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 99/5 | 2025-11-03 | 2025-11 | 11 | 2025-12-05 | 2025-12 | 12 | 32 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 99/3 | 2025-11-06 | 2025-11 | 11 | 2025-12-18 | 2025-12 | 12 | 42 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 165/2 | 2025-11-07 | 2025-11 | 11 | 2026-02-23 | 2026-02 | 2 | 108 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 99/2 | 2025-11-09 | 2025-11 | 11 | 2026-01-02 | 2026-01 | 1 | 54 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 181/6 | 2025-11-10 | 2025-11 | 11 | 2025-12-12 | 2025-12 | 12 | 32 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 99/1 | 2025-11-11 | 2025-11 | 11 | 2025-12-27 | 2025-12 | 12 | 46 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/5 | 2025-11-14 | 2025-11 | 11 | 2025-11-25 | 2025-11 | 11 | 11 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 99/7 | 2025-11-16 | 2025-11 | 11 | 2025-12-22 | 2025-12 | 12 | 36 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 181/1 | 2025-11-18 | 2025-11 | 11 | 2025-12-21 | 2025-12 | 12 | 33 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/9 | 2025-11-19 | 2025-11 | 11 | 2025-12-03 | 2025-12 | 12 | 14 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/0 | 2025-11-20 | 2025-11 | 11 | 2025-12-10 | 2025-12 | 12 | 20 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 122/0 | 2025-11-26 | 2025-11 | 11 | 2026-01-29 | 2026-01 | 1 | 64 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 175/2 | 2025-11-26 | 2025-11 | 11 | 2026-01-10 | 2026-01 | 1 | 45 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/10 | 2025-11-27 | 2025-11 | 11 | 2026-05-29 | 2026-05 | 5 | 183 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 181/4 | 2025-11-27 | 2025-11 | 11 | 2026-01-07 | 2026-01 | 1 | 41 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 138/0 | 2025-11-29 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 123/0 | 2025-12-03 | 2025-12 | 12 | 2025-12-22 | 2025-12 | 12 | 19 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 181/5 | 2025-12-06 | 2025-12 | 12 | 2026-01-07 | 2026-01 | 1 | 32 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 123/1 | 2025-12-08 | 2025-12 | 12 | 2026-01-05 | 2026-01 | 1 | 28 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/9 | 2025-12-08 | 2025-12 | 12 | 2025-12-20 | 2025-12 | 12 | 12 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/5 | 2025-12-10 | 2025-12 | 12 | 2025-12-21 | 2025-12 | 12 | 11 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 123/3 | 2025-12-12 | 2025-12 | 12 | 2026-01-15 | 2026-01 | 1 | 34 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 153/0 | 2025-12-13 | 2025-12 | 12 | 2026-01-11 | 2026-01 | 1 | 29 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 154/0 | 2025-12-14 | 2025-12 | 12 | 2026-01-02 | 2026-01 | 1 | 19 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 125/1 | 2025-12-15 | 2025-12 | 12 | 2026-01-12 | 2026-01 | 1 | 28 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 175/1 | 2025-12-15 | 2025-12 | 12 | 2026-02-01 | 2026-02 | 2 | 48 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 123/2 | 2025-12-22 | 2025-12 | 12 | 2026-01-21 | 2026-01 | 1 | 30 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 129A/0 | 2025-12-23 | 2025-12 | 12 | 2025-12-31 | 2025-12 | 12 | 8 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 181/0 | 2025-12-24 | 2025-12 | 12 | 2026-01-12 | 2026-01 | 1 | 19 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 113/0 | 2025-12-28 | 2025-12 | 12 | 2026-01-06 | 2026-01 | 1 | 9 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 175/0 | 2025-12-30 | 2025-12 | 12 | 2026-01-09 | 2026-01 | 1 | 10 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149B/0 | 2025-12-31 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 158/0 | 2025-12-31 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 158/1 | 2025-12-31 | 2025-12 | 12 | 2026-01-11 | 2026-01 | 1 | 11 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 125/0 | 2026-01-04 | 2026-01 | 1 | 2026-01-21 | 2026-01 | 1 | 17 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 162/0 | 2026-01-07 | 2026-01 | 1 | 2026-04-24 | 2026-04 | 4 | 107 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 162/2 | 2026-01-08 | 2026-01 | 1 | 2026-01-20 | 2026-01 | 1 | 12 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 124/0 | 2026-01-09 | 2026-01 | 1 | 2026-02-01 | 2026-02 | 2 | 23 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/9 | 2026-01-11 | 2026-01 | 1 | 2026-02-01 | 2026-02 | 2 | 21 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149/0 | 2026-01-13 | 2026-01 | 1 | 2026-01-19 | 2026-01 | 1 | 6 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149/2 | 2026-01-16 | 2026-01 | 1 | 2026-01-24 | 2026-01 | 1 | 8 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149/1 | 2026-01-18 | 2026-01 | 1 | 2026-02-01 | 2026-02 | 2 | 14 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 164/0 | 2026-01-19 | 2026-01 | 1 | 2026-02-16 | 2026-02 | 2 | 28 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 174B/0 | 2026-01-22 | 2026-01 | 1 | 2026-06-03 | 2026-06 | 6 | 132 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 163/0 | 2026-01-23 | 2026-01 | 1 | 2026-02-06 | 2026-02 | 2 | 14 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 162/1 | 2026-01-24 | 2026-01 | 1 | 2026-01-28 | 2026-01 | 1 | 4 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 146/1 | 2026-01-25 | 2026-01 | 1 | 2026-01-31 | 2026-01 | 1 | 6 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 164/1 | 2026-01-25 | 2026-01 | 1 | 2026-02-01 | 2026-02 | 2 | 7 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 182/0 | 2026-01-25 | 2026-01 | 1 | 2026-05-14 | 2026-05 | 5 | 109 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 148B/1 | 2026-01-29 | 2026-01 | 1 | 2026-02-01 | 2026-02 | 2 | 3 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149A/0 | 2026-01-31 | 2026-01 | 1 | 2026-02-10 | 2026-02 | 2 | 10 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 139/0 | 2026-02-04 | 2026-02 | 2 | 2026-02-22 | 2026-02 | 2 | 18 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 139/1 | 2026-02-06 | 2026-02 | 2 | 2026-02-12 | 2026-02 | 2 | 6 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 156/6 | 2026-02-07 | 2026-02 | 2 | 2026-02-08 | 2026-02 | 2 | 1 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 138/1 | 2026-02-10 | 2026-02 | 2 | 2026-02-15 | 2026-02 | 2 | 5 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 138/3 | 2026-02-12 | 2026-02 | 2 | 2026-03-01 | 2026-03 | 3 | 17 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 148B/2 | 2026-02-15 | 2026-02 | 2 | 2026-02-24 | 2026-02 | 2 | 9 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 146/0 | 2026-02-19 | 2026-02 | 2 | 2026-03-11 | 2026-03 | 3 | 20 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 148C/0 | 2026-02-21 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 142/1 | 2026-02-24 | 2026-02 | 2 | 2026-02-27 | 2026-02 | 2 | 3 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 148B/0 | 2026-02-28 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 156/5 | 2026-03-03 | 2026-03 | 3 | 2026-03-15 | 2026-03 | 3 | 12 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/8 | 2026-03-08 | 2026-03 | 3 | 2026-04-24 | 2026-04 | 4 | 47 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 156/2 | 2026-03-10 | 2026-03 | 3 | 2026-05-07 | 2026-05 | 5 | 58 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 157/0 | 2026-03-10 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 138/2 | 2026-03-11 | 2026-03 | 3 | 2026-03-14 | 2026-03 | 3 | 3 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 144/0 | 2026-03-21 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 171/5 | 2026-03-21 | 2026-03 | 3 | 2026-06-06 | 2026-06 | 6 | 77 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 143/0 | 2026-03-31 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 134/0 | 2026-04-09 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 137A/0 | 2026-04-09 | 2026-04 | 4 | 2026-04-13 | 2026-04 | 4 | 4 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 129/0 | 2026-04-14 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 133/0 | 2026-04-14 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 136/4 | 2026-04-15 | 2026-04 | 4 | 2026-05-16 | 2026-05 | 5 | 31 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 136/3 | 2026-04-18 | 2026-04 | 4 | 2026-05-07 | 2026-05 | 5 | 19 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 129/1 | 2026-04-23 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 117/0 | 2026-04-30 | 2026-04 | 4 | 2026-05-14 | 2026-05 | 5 | 14 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 137/0 | 2026-05-15 | 2026-05 | 5 | 2026-06-12 | 2026-06 | 6 | 28 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/0 | 2026-05-15 | 2026-05 | 5 | 2025-12-04 | 2025-12 | 12 | -162 | Yes | Yes | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 181/2 | 2026-05-18 | 2026-05 | 5 | 2026-05-26 | 2026-05 | 5 | 8 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 181/3 | 2026-05-25 | 2026-05 | 5 | 2026-05-30 | 2026-05 | 5 | 5 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/0 | 2026-06-15 | 2026-06 | 6 | 2026-06-25 | 2026-06 | 6 | 10 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 182B/0 | 2026-06-20 | 2026-06 | 6 | 2026-07-27 | 2026-07 | 7 | 37 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/8 | 2026-06-23 | 2026-06 | 6 | 2026-07-17 | 2026-07 | 7 | 24 | Yes | No | exact |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/3 | 2026-06-30 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 510 | 5xx | Government | ta510 | 155/1 | 2025-02-17 | 2025-02 | 2 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 155/4 | 2025-02-22 | 2025-02 | 2 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 155/3 | 2025-02-25 | 2025-02 | 2 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 155/5 | 2025-02-27 | 2025-02 | 2 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 156/0 | 2025-03-12 | 2025-03 | 3 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 156/1 | 2025-03-13 | 2025-03 | 3 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 156/3 | 2025-03-16 | 2025-03 | 3 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 156/4 | 2025-03-25 | 2025-03 | 3 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 156/2 | 2025-03-30 | 2025-03 | 3 | 2026-06-30 | 2026-06 | 6 | 457 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 139/1 | 2025-04-16 | 2025-04 | 4 | 2026-05-31 | 2026-05 | 5 | 410 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 138/0 | 2025-04-21 | 2025-04 | 4 | 2026-06-05 | 2026-06 | 6 | 410 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 139/5 | 2025-04-21 | 2025-04 | 4 | 2026-05-22 | 2026-05 | 5 | 396 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 137/0 | 2025-04-27 | 2025-04 | 4 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 139/4 | 2025-04-28 | 2025-04 | 4 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 138/1 | 2025-04-29 | 2025-04 | 4 | 2026-06-26 | 2026-06 | 6 | 423 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 136/0 | 2025-05-14 | 2025-05 | 5 | 2026-05-28 | 2026-05 | 5 | 379 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148/5 | 2025-05-15 | 2025-05 | 5 | 2026-05-03 | 2026-05 | 5 | 353 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148/4 | 2025-05-21 | 2025-05 | 5 | 2026-02-27 | 2026-02 | 2 | 282 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148/2 | 2025-05-23 | 2025-05 | 5 | 2026-02-18 | 2026-02 | 2 | 271 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 134/0 | 2025-05-25 | 2025-05 | 5 | 2026-02-01 | 2026-02 | 2 | 252 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148/7 | 2025-05-28 | 2025-05 | 5 | 2026-05-13 | 2026-05 | 5 | 350 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148/6 | 2025-05-31 | 2025-05 | 5 | 2026-05-08 | 2026-05 | 5 | 342 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 143/1 | 2025-06-02 | 2025-06 | 6 | 2026-01-16 | 2026-01 | 1 | 228 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 143/2 | 2025-06-05 | 2025-06 | 6 | 2026-06-05 | 2026-06 | 6 | 365 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 144/0 | 2025-08-06 | 2025-08 | 8 | 2026-05-29 | 2026-05 | 5 | 296 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 141/0 | 2025-09-16 | 2025-09 | 9 | 2026-01-08 | 2026-01 | 1 | 114 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 133/2 | 2025-09-18 | 2025-09 | 9 | 2026-07-15 | 2026-07 | 7 | 300 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 141/1 | 2025-10-04 | 2025-10 | 10 | 2026-01-01 | 2026-01 | 1 | 89 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 138/2 | 2025-10-05 | 2025-10 | 10 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 140/1 | 2025-10-10 | 2025-10 | 10 | 2026-01-14 | 2026-01 | 1 | 96 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 145/0 | 2025-10-19 | 2025-10 | 10 | 2026-01-22 | 2026-01 | 1 | 95 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 139/2 | 2025-10-24 | 2025-10 | 10 | 2026-01-05 | 2026-01 | 1 | 73 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 140/2 | 2025-11-19 | 2025-11 | 11 | 2026-02-08 | 2026-02 | 2 | 81 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 135/0 | 2025-11-24 | 2025-11 | 11 | 2026-01-13 | 2026-01 | 1 | 50 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 145/1 | 2025-11-24 | 2025-11 | 11 | 2026-01-30 | 2026-01 | 1 | 67 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 138/3 | 2025-11-27 | 2025-11 | 11 | 2026-07-04 | 2026-07 | 7 | 219 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 192/11 | 2025-11-30 | 2025-11 | 11 | 2026-03-01 | 2026-03 | 3 | 91 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 141/2 | 2025-12-07 | 2025-12 | 12 | 2026-03-08 | 2026-03 | 3 | 91 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 143/0 | 2025-12-09 | 2025-12 | 12 | 2026-02-12 | 2026-02 | 2 | 65 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 145/5 | 2025-12-09 | 2025-12 | 12 | 2026-01-27 | 2026-01 | 1 | 49 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148/3 | 2025-12-14 | 2025-12 | 12 | 2026-02-13 | 2026-02 | 2 | 61 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 192/13 | 2025-12-23 | 2025-12 | 12 | 2026-02-22 | 2026-02 | 2 | 61 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 145/3 | 2025-12-27 | 2025-12 | 12 | 2026-04-30 | 2026-04 | 4 | 124 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 146/1 | 2025-12-29 | 2025-12 | 12 | 2026-04-09 | 2026-04 | 4 | 101 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 140/0 | 2025-12-30 | 2025-12 | 12 | 2026-03-16 | 2026-03 | 3 | 76 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 146/3 | 2025-12-30 | 2025-12 | 12 | 2026-04-22 | 2026-04 | 4 | 113 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 145/4 | 2025-12-31 | 2025-12 | 12 | 2026-01-18 | 2026-01 | 1 | 18 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 192/10 | 2026-01-04 | 2026-01 | 1 | 2026-03-26 | 2026-03 | 3 | 81 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 147/2 | 2026-01-08 | 2026-01 | 1 | 2026-05-18 | 2026-05 | 5 | 130 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 146A/0 | 2026-01-13 | 2026-01 | 1 | 2026-03-24 | 2026-03 | 3 | 70 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 186/1 | 2026-01-13 | 2026-01 | 1 | 2026-03-10 | 2026-03 | 3 | 56 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 192/7 | 2026-01-21 | 2026-01 | 1 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 192/12 | 2026-01-25 | 2026-01 | 1 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 147/1 | 2026-01-30 | 2026-01 | 1 | 2026-05-14 | 2026-05 | 5 | 104 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 142/0 | 2026-02-02 | 2026-02 | 2 | 2026-05-23 | 2026-05 | 5 | 110 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 146/0 | 2026-02-03 | 2026-02 | 2 | 2026-04-02 | 2026-04 | 4 | 58 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 194/1 | 2026-02-10 | 2026-02 | 2 | 2026-03-17 | 2026-03 | 3 | 35 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 146A/1 | 2026-02-12 | 2026-02 | 2 | 2026-05-07 | 2026-05 | 5 | 84 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148/1 | 2026-02-14 | 2026-02 | 2 | 2026-02-23 | 2026-02 | 2 | 9 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148/0 | 2026-02-27 | 2026-02 | 2 | 2026-05-19 | 2026-05 | 5 | 81 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 157B/0 | 2026-03-11 | 2026-03 | 3 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 157A/0 | 2026-03-22 | 2026-03 | 3 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 157/2 | 2026-03-23 | 2026-03 | 3 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 146/2 | 2026-03-31 | 2026-03 | 3 | 2026-04-15 | 2026-04 | 4 | 15 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 192/9 | 2026-04-07 | 2026-04 | 4 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 139/3 | 2026-04-13 | 2026-04 | 4 | 2026-05-09 | 2026-05 | 5 | 26 | Yes | No | fallback_single_line | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 193/2 | 2026-04-13 | 2026-04 | 4 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 193/1 | 2026-04-19 | 2026-04 | 4 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 193/5 | 2026-04-20 | 2026-04 | 4 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 139/0 | 2026-04-21 | 2026-04 | 4 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 193/0 | 2026-04-28 | 2026-04 | 4 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 193/4 | 2026-04-29 | 2026-04 | 4 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 192/8 | 2026-05-06 | 2026-05 | 5 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 167/2 | 2026-05-13 | 2026-05 | 5 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 157B/1 | 2026-05-16 | 2026-05 | 5 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 167/3 | 2026-05-17 | 2026-05 | 5 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 133/0 | 2026-05-18 | 2026-05 | 5 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 153/0 | 2026-05-20 | 2026-05 | 5 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 167/4 | 2026-05-20 | 2026-05 | 5 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 133/1 | 2026-05-23 | 2026-05 | 5 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 167/1 | 2026-05-26 | 2026-05 | 5 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 194/0 | 2026-05-27 | 2026-05 | 5 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 150/2 | 2026-05-31 | 2026-05 | 5 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 153/1 | 2026-05-31 | 2026-05 | 5 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 155/0 | 2026-05-31 | 2026-05 | 5 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 150/4 | 2026-06-06 | 2026-06 | 6 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 155/2 | 2026-06-06 | 2026-06 | 6 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 154/0 | 2026-06-10 | 2026-06 | 6 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 150/3 | 2026-06-11 | 2026-06 | 6 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 154/1 | 2026-06-14 | 2026-06 | 6 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 160/3 | 2026-06-14 | 2026-06 | 6 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 150/1 | 2026-06-15 | 2026-06 | 6 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 154/2 | 2026-06-20 | 2026-06 | 6 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148A/0 | 2026-06-25 | 2026-06 | 6 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 152/1 | 2026-06-25 | 2026-06 | 6 |  |  |  |  | No | No |  | FDN |  | TA 510 - DPR - 2026-08-12.xlsx | FDN
TA 512 | 5xx | Government | ta512 | 8/1 | 2025-02-23 | 2025-02 | 2 | 2025-11-16 | 2025-11 | 11 | 266 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 8/3 | 2025-02-26 | 2025-02 | 2 | 2025-07-25 | 2025-07 | 7 | 149 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 8/6 | 2025-02-28 | 2025-02 | 2 | 2025-08-27 | 2025-08 | 8 | 180 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 8/2 | 2025-03-05 | 2025-03 | 3 | 2026-03-08 | 2026-03 | 3 | 368 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 8/5 | 2025-03-05 | 2025-03 | 3 | 2025-09-04 | 2025-09 | 9 | 183 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 12/1 | 2025-03-07 | 2025-03 | 3 | 2025-10-10 | 2025-10 | 10 | 217 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 12/2 | 2025-03-10 | 2025-03 | 3 | 2026-01-07 | 2026-01 | 1 | 303 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 12/3 | 2025-03-10 | 2025-03 | 3 | 2025-10-27 | 2025-10 | 10 | 231 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 8/4 | 2025-03-10 | 2025-03 | 3 | 2026-02-04 | 2026-02 | 2 | 331 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 8/8 | 2025-03-10 | 2025-03 | 3 | 2025-08-11 | 2025-08 | 8 | 154 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 12/4 | 2025-03-13 | 2025-03 | 3 | 2025-11-16 | 2025-11 | 11 | 248 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/7 | 2025-03-15 | 2025-03 | 3 | 2026-02-14 | 2026-02 | 2 | 336 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 18/5 | 2025-03-17 | 2025-03 | 3 | 2025-08-18 | 2025-08 | 8 | 154 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/6 | 2025-03-17 | 2025-03 | 3 | 2025-08-26 | 2025-08 | 8 | 162 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 18/4 | 2025-03-18 | 2025-03 | 3 | 2025-11-16 | 2025-11 | 11 | 243 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/8 | 2025-03-20 | 2025-03 | 3 | 2025-12-12 | 2025-12 | 12 | 267 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 18/3 | 2025-03-21 | 2025-03 | 3 | 2025-11-23 | 2025-11 | 11 | 247 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/5 | 2025-03-21 | 2025-03 | 3 | 2026-01-29 | 2026-01 | 1 | 314 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 19/1 | 2025-03-23 | 2025-03 | 3 | 2025-08-26 | 2025-08 | 8 | 156 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 19/2 | 2025-03-24 | 2025-03 | 3 | 2025-10-31 | 2025-10 | 10 | 221 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 8/7 | 2025-03-24 | 2025-03 | 3 | 2025-08-21 | 2025-08 | 8 | 150 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 19/3 | 2025-03-25 | 2025-03 | 3 | 2025-11-07 | 2025-11 | 11 | 227 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/10 | 2025-03-26 | 2025-03 | 3 | 2026-02-06 | 2026-02 | 2 | 317 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/7 | 2025-03-26 | 2025-03 | 3 | 2026-01-19 | 2026-01 | 1 | 299 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 19/6 | 2025-03-27 | 2025-03 | 3 | 2025-09-23 | 2025-09 | 9 | 180 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 19/4 | 2025-03-28 | 2025-03 | 3 | 2025-09-08 | 2025-09 | 9 | 164 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 19/7 | 2025-03-30 | 2025-03 | 3 | 2025-09-14 | 2025-09 | 9 | 168 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 9/2 | 2025-03-30 | 2025-03 | 3 | 2025-09-11 | 2025-09 | 9 | 165 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20/1 | 2025-03-31 | 2025-03 | 3 | 2025-09-28 | 2025-09 | 9 | 181 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/8 | 2025-04-01 | 2025-04 | 4 | 2025-08-21 | 2025-08 | 8 | 142 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/9 | 2025-04-02 | 2025-04 | 4 | 2026-02-26 | 2026-02 | 2 | 330 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 9/3 | 2025-04-03 | 2025-04 | 4 | 2025-09-20 | 2025-09 | 9 | 170 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20/5 | 2025-04-04 | 2025-04 | 4 | 2025-12-14 | 2025-12 | 12 | 254 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/9 | 2025-04-06 | 2025-04 | 4 | 2025-08-13 | 2025-08 | 8 | 129 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/6 | 2025-04-07 | 2025-04 | 4 | 2025-12-31 | 2025-12 | 12 | 268 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20/2 | 2025-04-10 | 2025-04 | 4 | 2025-10-05 | 2025-10 | 10 | 178 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/11 | 2025-04-11 | 2025-04 | 4 | 2025-11-23 | 2025-11 | 11 | 226 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/5 | 2025-04-13 | 2025-04 | 4 | 2026-01-11 | 2026-01 | 1 | 273 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/4 | 2025-04-13 | 2025-04 | 4 | 2026-01-29 | 2026-01 | 1 | 291 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20/3 | 2025-04-15 | 2025-04 | 4 | 2025-12-01 | 2025-12 | 12 | 230 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/4 | 2025-04-15 | 2025-04 | 4 | 2026-01-22 | 2026-01 | 1 | 282 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/10 | 2025-04-16 | 2025-04 | 4 | 2025-11-26 | 2025-11 | 11 | 224 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 19/5 | 2025-04-19 | 2025-04 | 4 | 2025-08-31 | 2025-08 | 8 | 134 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/7 | 2025-04-19 | 2025-04 | 4 | 2025-09-28 | 2025-09 | 9 | 162 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/4 | 2025-04-21 | 2025-04 | 4 | 2025-09-12 | 2025-09 | 9 | 144 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/8 | 2025-04-23 | 2025-04 | 4 | 2025-12-24 | 2025-12 | 12 | 245 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 28/2 | 2025-04-24 | 2025-04 | 4 | 2025-10-13 | 2025-10 | 10 | 172 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20/6 | 2025-04-25 | 2025-04 | 4 | 2026-01-04 | 2026-01 | 1 | 254 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/10 | 2025-04-26 | 2025-04 | 4 | 2025-12-13 | 2025-12 | 12 | 231 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 28/1 | 2025-04-28 | 2025-04 | 4 | 2025-09-24 | 2025-09 | 9 | 149 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/3 | 2025-04-28 | 2025-04 | 4 | 2025-09-18 | 2025-09 | 9 | 143 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 23/3 | 2025-04-30 | 2025-04 | 4 | 2026-02-12 | 2026-02 | 2 | 288 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/12 | 2025-04-30 | 2025-04 | 4 | 2025-12-03 | 2025-12 | 12 | 217 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 23/2 | 2025-05-04 | 2025-05 | 5 | 2026-02-07 | 2026-02 | 2 | 279 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/11 | 2025-05-04 | 2025-05 | 5 | 2026-02-13 | 2026-02 | 2 | 285 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/2 | 2025-05-04 | 2025-05 | 5 | 2026-07-30 | 2026-07 | 7 | 452 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/13 | 2025-05-07 | 2025-05 | 5 | 2026-02-06 | 2026-02 | 2 | 275 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/14 | 2025-05-09 | 2025-05 | 5 | 2025-11-22 | 2025-11 | 11 | 197 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/1 | 2025-05-10 | 2025-05 | 5 | 2025-09-02 | 2025-09 | 9 | 115 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/18 | 2025-05-11 | 2025-05 | 5 | 2025-09-21 | 2025-09 | 9 | 133 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 11/4 | 2025-05-12 | 2025-05 | 5 | 2025-12-04 | 2025-12 | 12 | 206 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/1 | 2025-05-14 | 2025-05 | 5 | 2025-09-13 | 2025-09 | 9 | 122 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/2 | 2025-05-15 | 2025-05 | 5 | 2025-09-02 | 2025-09 | 9 | 110 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/3 | 2025-05-17 | 2025-05 | 5 | 2026-01-06 | 2026-01 | 1 | 234 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/1 | 2025-05-17 | 2025-05 | 5 | 2025-08-21 | 2025-08 | 8 | 96 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/4 | 2025-05-18 | 2025-05 | 5 | 2026-02-08 | 2026-02 | 2 | 266 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 28/4 | 2025-05-19 | 2025-05 | 5 | 2025-11-01 | 2025-11 | 11 | 166 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/8 | 2025-05-19 | 2025-05 | 5 | 2026-05-21 | 2026-05 | 5 | 367 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/5 | 2025-05-20 | 2025-05 | 5 | 2026-01-11 | 2026-01 | 1 | 236 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 11/2 | 2025-05-21 | 2025-05 | 5 | 2025-12-25 | 2025-12 | 12 | 218 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/6 | 2025-05-23 | 2025-05 | 5 | 2026-01-19 | 2026-01 | 1 | 241 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/10 | 2025-05-23 | 2025-05 | 5 | 2025-12-14 | 2025-12 | 12 | 205 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/2 | 2025-05-25 | 2025-05 | 5 | 2025-12-29 | 2025-12 | 12 | 218 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 11/3 | 2025-05-26 | 2025-05 | 5 | 2025-12-14 | 2025-12 | 12 | 202 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/7 | 2025-05-26 | 2025-05 | 5 | 2026-01-27 | 2026-01 | 1 | 246 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 28/7 | 2025-05-27 | 2025-05 | 5 | 2025-10-26 | 2025-10 | 10 | 152 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 28/6 | 2025-06-01 | 2025-06 | 6 | 2025-11-05 | 2025-11 | 11 | 157 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/3 | 2025-06-01 | 2025-06 | 6 | 2026-01-18 | 2026-01 | 1 | 231 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 11/5 | 2025-06-04 | 2025-06 | 6 | 2025-11-27 | 2025-11 | 11 | 176 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/8 | 2025-06-04 | 2025-06 | 6 | 2026-02-01 | 2026-02 | 2 | 242 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 28/3 | 2025-06-06 | 2025-06 | 6 | 2026-02-02 | 2026-02 | 2 | 241 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/12 | 2025-06-07 | 2025-06 | 6 | 2026-02-13 | 2026-02 | 2 | 251 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/9 | 2025-06-08 | 2025-06 | 6 | 2025-12-08 | 2025-12 | 12 | 183 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/11 | 2025-06-10 | 2025-06 | 6 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 28/5 | 2025-06-11 | 2025-06 | 6 | 2025-10-03 | 2025-10 | 10 | 114 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/13 | 2025-06-11 | 2025-06 | 6 | 2026-02-07 | 2026-02 | 2 | 241 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/11 | 2025-06-11 | 2025-06 | 6 | 2025-12-21 | 2025-12 | 12 | 193 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/6 | 2025-06-11 | 2025-06 | 6 | 2026-02-03 | 2026-02 | 2 | 237 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/5 | 2025-06-16 | 2025-06 | 6 | 2025-12-01 | 2025-12 | 12 | 168 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/5 | 2025-06-16 | 2025-06 | 6 | 2026-02-09 | 2026-02 | 2 | 238 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 27/2 | 2025-06-17 | 2025-06 | 6 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 31/9 | 2025-06-17 | 2025-06 | 6 | 2026-02-21 | 2026-02 | 2 | 249 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/9 | 2025-06-18 | 2025-06 | 6 | 2026-02-21 | 2026-02 | 2 | 248 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/4 | 2025-06-18 | 2025-06 | 6 | 2026-01-15 | 2026-01 | 1 | 211 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 27/3 | 2025-06-20 | 2025-06 | 6 | 2026-07-07 | 2026-07 | 7 | 382 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/0 | 2025-06-22 | 2025-06 | 6 | 2025-12-16 | 2025-12 | 12 | 177 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/3 | 2025-06-23 | 2025-06 | 6 | 2026-02-11 | 2026-02 | 2 | 233 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 19/0 | 2025-06-26 | 2025-06 | 6 | 2025-10-13 | 2025-10 | 10 | 109 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/1 | 2025-06-26 | 2025-06 | 6 | 2025-11-29 | 2025-11 | 11 | 156 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/14 | 2025-06-26 | 2025-06 | 6 | 2026-03-24 | 2026-03 | 3 | 271 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/2 | 2025-06-26 | 2025-06 | 6 | 2026-01-25 | 2026-01 | 1 | 213 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20/0 | 2025-06-30 | 2025-06 | 6 | 2025-12-20 | 2025-12 | 12 | 173 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/4 | 2025-06-30 | 2025-06 | 6 | 2026-05-17 | 2026-05 | 5 | 321 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 41/6 | 2025-07-01 | 2025-07 | 7 | 2026-04-14 | 2026-04 | 4 | 287 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/2 | 2025-07-03 | 2025-07 | 7 | 2025-10-13 | 2025-10 | 10 | 102 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/1 | 2025-07-03 | 2025-07 | 7 | 2026-02-26 | 2026-02 | 2 | 238 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 12/5 | 2025-07-04 | 2025-07 | 7 | 2025-11-17 | 2025-11 | 11 | 136 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/7 | 2025-07-04 | 2025-07 | 7 | 2025-11-13 | 2025-11 | 11 | 132 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/13 | 2025-07-05 | 2025-07 | 7 | 2026-03-07 | 2026-03 | 3 | 245 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 41/5 | 2025-07-05 | 2025-07 | 7 | 2026-04-07 | 2026-04 | 4 | 276 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 11/6 | 2025-07-07 | 2025-07 | 7 | 2025-12-31 | 2025-12 | 12 | 177 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/3 | 2025-07-09 | 2025-07 | 7 | 2025-11-03 | 2025-11 | 11 | 117 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/11 | 2025-07-09 | 2025-07 | 7 | 2026-03-01 | 2026-03 | 3 | 235 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 16/2 | 2025-07-10 | 2025-07 | 7 | 2026-08-08 | 2026-08 | 8 | 394 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/6 | 2025-07-10 | 2025-07 | 7 | 2025-11-17 | 2025-11 | 11 | 130 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/4 | 2025-07-12 | 2025-07 | 7 | 2025-11-25 | 2025-11 | 11 | 136 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/12 | 2025-07-13 | 2025-07 | 7 | 2026-03-21 | 2026-03 | 3 | 251 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 1A/1 | 2025-07-15 | 2025-07 | 7 | 2026-02-23 | 2026-02 | 2 | 223 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/8 | 2025-07-15 | 2025-07 | 7 | 2025-12-24 | 2025-12 | 12 | 162 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/10 | 2025-07-16 | 2025-07 | 7 | 2025-12-22 | 2025-12 | 12 | 159 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/26 | 2025-07-17 | 2025-07 | 7 | 2025-12-01 | 2025-12 | 12 | 137 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/3 | 2025-07-17 | 2025-07 | 7 | 2026-07-26 | 2026-07 | 7 | 374 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/9 | 2025-07-18 | 2025-07 | 7 | 2026-01-05 | 2026-01 | 1 | 171 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/5 | 2025-07-19 | 2025-07 | 7 | 2025-11-21 | 2025-11 | 11 | 125 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 1A/3 | 2025-07-20 | 2025-07 | 7 | 2026-07-31 | 2026-07 | 7 | 376 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/9 | 2025-07-20 | 2025-07 | 7 | 2025-12-20 | 2025-12 | 12 | 153 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/14 | 2025-07-21 | 2025-07 | 7 | 2026-02-01 | 2026-02 | 2 | 195 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 1A/2 | 2025-07-22 | 2025-07 | 7 | 2026-03-01 | 2026-03 | 3 | 222 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/15 | 2025-07-23 | 2025-07 | 7 | 2026-01-22 | 2026-01 | 1 | 183 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/10 | 2025-07-25 | 2025-07 | 7 | 2025-12-17 | 2025-12 | 12 | 145 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/11 | 2025-07-25 | 2025-07 | 7 | 2025-12-29 | 2025-12 | 12 | 157 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 40/2 | 2025-07-25 | 2025-07 | 7 | 2026-07-13 | 2026-07 | 7 | 353 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/8 | 2025-07-26 | 2025-07 | 7 | 2026-01-04 | 2026-01 | 1 | 162 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2/2 | 2025-07-29 | 2025-07 | 7 | 2026-02-07 | 2026-02 | 2 | 193 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/24 | 2025-07-29 | 2025-07 | 7 | 2026-07-07 | 2026-07 | 7 | 343 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 40/3 | 2025-07-29 | 2025-07 | 7 | 2026-05-16 | 2026-05 | 5 | 291 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/0 | 2025-07-30 | 2025-07 | 7 | 2026-01-22 | 2026-01 | 1 | 176 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/20 | 2025-07-31 | 2025-07 | 7 | 2025-12-11 | 2025-12 | 12 | 133 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/0 | 2025-08-01 | 2025-08 | 8 | 2025-10-19 | 2025-10 | 10 | 79 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/12 | 2025-08-01 | 2025-08 | 8 | 2025-12-09 | 2025-12 | 12 | 130 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/19 | 2025-08-01 | 2025-08 | 8 | 2026-03-02 | 2026-03 | 3 | 213 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/7 | 2025-08-02 | 2025-08 | 8 | 2025-12-20 | 2025-12 | 12 | 140 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2/4 | 2025-08-03 | 2025-08 | 8 | 2026-01-27 | 2026-01 | 1 | 177 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3A/3 | 2025-08-03 | 2025-08 | 8 | 2026-01-15 | 2026-01 | 1 | 165 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 40/4 | 2025-08-03 | 2025-08 | 8 | 2026-07-20 | 2026-07 | 7 | 351 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/20 | 2025-08-05 | 2025-08 | 8 | 2026-01-02 | 2026-01 | 1 | 150 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/16 | 2025-08-05 | 2025-08 | 8 | 2026-01-11 | 2026-01 | 1 | 159 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/6 | 2025-08-06 | 2025-08 | 8 | 2026-03-06 | 2026-03 | 3 | 212 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/15 | 2025-08-07 | 2025-08 | 8 | 2025-12-05 | 2025-12 | 12 | 120 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/21 | 2025-08-07 | 2025-08 | 8 | 2026-07-18 | 2026-07 | 7 | 345 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/23 | 2025-08-07 | 2025-08 | 8 | 2026-03-14 | 2026-03 | 3 | 219 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3A/2 | 2025-08-07 | 2025-08 | 8 | 2026-01-15 | 2026-01 | 1 | 161 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2/5 | 2025-08-08 | 2025-08 | 8 | 2026-01-10 | 2026-01 | 1 | 155 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2/1 | 2025-08-13 | 2025-08 | 8 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 30/2 | 2025-08-13 | 2025-08 | 8 | 2025-10-05 | 2025-10 | 10 | 53 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/5 | 2025-08-14 | 2025-08 | 8 | 2026-05-13 | 2026-05 | 5 | 272 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3A/1 | 2025-08-14 | 2025-08 | 8 | 2026-01-22 | 2026-01 | 1 | 161 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 9/1 | 2025-08-21 | 2025-08 | 8 | 2025-11-29 | 2025-11 | 11 | 100 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/16 | 2025-08-22 | 2025-08 | 8 | 2026-08-03 | 2026-08 | 8 | 346 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/22 | 2025-08-22 | 2025-08 | 8 | 2026-07-25 | 2026-07 | 7 | 337 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/3 | 2025-08-23 | 2025-08 | 8 | 2026-03-10 | 2026-03 | 3 | 199 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 41/0 | 2025-08-28 | 2025-08 | 8 | 2026-02-22 | 2026-02 | 2 | 178 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 9/0 | 2025-08-28 | 2025-08 | 8 | 2025-09-25 | 2025-09 | 9 | 28 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/7 | 2025-08-29 | 2025-08 | 8 | 2026-04-30 | 2026-04 | 4 | 244 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/18 | 2025-09-03 | 2025-09 | 9 | 2026-06-25 | 2026-06 | 6 | 295 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 36/9 | 2025-09-03 | 2025-09 | 9 | 2026-07-13 | 2026-07 | 7 | 313 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/5 | 2025-09-03 | 2025-09 | 9 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 36/8 | 2025-09-06 | 2025-09 | 9 | 2026-01-29 | 2026-01 | 1 | 145 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/6 | 2025-09-06 | 2025-09 | 9 | 2026-08-10 | 2026-08 | 8 | 338 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 8/0 | 2025-09-06 | 2025-09 | 9 | 2025-11-20 | 2025-11 | 11 | 75 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/2 | 2025-09-09 | 2025-09 | 9 | 2026-05-26 | 2026-05 | 5 | 259 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/14 | 2025-09-11 | 2025-09 | 9 | 2026-01-22 | 2026-01 | 1 | 133 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 36/7 | 2025-09-11 | 2025-09 | 9 | 2026-02-12 | 2026-02 | 2 | 154 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 36/6 | 2025-09-16 | 2025-09 | 9 | 2026-02-06 | 2026-02 | 2 | 143 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/5 | 2025-09-16 | 2025-09 | 9 | 2026-01-18 | 2026-01 | 1 | 124 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/6 | 2025-09-16 | 2025-09 | 9 | 2025-12-25 | 2025-12 | 12 | 100 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/0 | 2025-09-16 | 2025-09 | 9 | 2026-02-14 | 2026-02 | 2 | 151 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 36/5 | 2025-09-21 | 2025-09 | 9 | 2026-08-03 | 2026-08 | 8 | 316 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/8 | 2025-09-22 | 2025-09 | 9 | 2026-02-09 | 2026-02 | 2 | 140 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 13/0 | 2025-09-23 | 2025-09 | 9 | 2026-01-16 | 2026-01 | 1 | 115 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/9 | 2025-09-25 | 2025-09 | 9 | 2026-02-16 | 2026-02 | 2 | 144 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 36/4 | 2025-09-26 | 2025-09 | 9 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 36/3 | 2025-09-29 | 2025-09 | 9 | 2026-03-15 | 2026-03 | 3 | 167 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/19 | 2025-10-01 | 2025-10 | 10 | 2026-06-16 | 2026-06 | 6 | 258 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/9 | 2025-10-04 | 2025-10 | 10 | 2026-04-03 | 2026-04 | 4 | 181 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/0 | 2025-10-04 | 2025-10 | 10 | 2026-03-22 | 2026-03 | 3 | 169 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/7 | 2025-10-09 | 2025-10 | 10 | 2026-01-02 | 2026-01 | 1 | 85 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20/4 | 2025-10-12 | 2025-10 | 10 | 2025-12-07 | 2025-12 | 12 | 56 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/10 | 2025-10-12 | 2025-10 | 10 | 2026-03-06 | 2026-03 | 3 | 145 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 36/2 | 2025-10-12 | 2025-10 | 10 | 2026-07-26 | 2026-07 | 7 | 287 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/2 | 2025-10-16 | 2025-10 | 10 | 2026-03-30 | 2026-03 | 3 | 165 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 18/2 | 2025-10-17 | 2025-10 | 10 | 2026-01-22 | 2026-01 | 1 | 97 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/0 | 2025-10-17 | 2025-10 | 10 | 2026-06-30 | 2026-06 | 6 | 256 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/3 | 2025-10-18 | 2025-10 | 10 | 2026-04-03 | 2026-04 | 4 | 167 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/17 | 2025-10-19 | 2025-10 | 10 | 2025-12-21 | 2025-12 | 12 | 63 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3/1 | 2025-10-23 | 2025-10 | 10 | 2026-07-20 | 2026-07 | 7 | 270 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/13 | 2025-10-25 | 2025-10 | 10 | 2026-01-17 | 2026-01 | 1 | 84 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 35/0 | 2025-10-25 | 2025-10 | 10 | 2026-02-17 | 2026-02 | 2 | 115 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/18 | 2025-10-26 | 2025-10 | 10 | 2025-12-30 | 2025-12 | 12 | 65 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/4 | 2025-10-26 | 2025-10 | 10 | 2026-04-10 | 2026-04 | 4 | 166 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 12/0 | 2025-10-27 | 2025-10 | 10 | 2026-07-10 | 2026-07 | 7 | 256 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3/2 | 2025-10-28 | 2025-10 | 10 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 31/0 | 2025-10-30 | 2025-10 | 10 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 3/3 | 2025-10-30 | 2025-10 | 10 | 2026-02-15 | 2026-02 | 2 | 108 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 40/1 | 2025-10-30 | 2025-10 | 10 | 2026-06-11 | 2026-06 | 6 | 224 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 9/4 | 2025-10-30 | 2025-10 | 10 | 2025-12-08 | 2025-12 | 12 | 39 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/21 | 2025-11-01 | 2025-11 | 11 | 2026-01-09 | 2026-01 | 1 | 69 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 35/1 | 2025-11-01 | 2025-11 | 11 | 2026-02-25 | 2026-02 | 2 | 116 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3/4 | 2025-11-02 | 2025-11 | 11 | 2026-02-25 | 2026-02 | 2 | 115 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/1 | 2025-11-03 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 30/17 | 2025-11-04 | 2025-11 | 11 | 2026-03-08 | 2026-03 | 3 | 124 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 11/1 | 2025-11-05 | 2025-11 | 11 | 2025-12-19 | 2025-12 | 12 | 44 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3/5 | 2025-11-06 | 2025-11 | 11 | 2026-02-05 | 2026-02 | 2 | 91 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 35/2 | 2025-11-07 | 2025-11 | 11 | 2026-03-29 | 2026-03 | 3 | 142 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/17 | 2025-11-09 | 2025-11 | 11 | 2026-01-13 | 2026-01 | 1 | 65 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3/6 | 2025-11-09 | 2025-11 | 11 | 2026-01-31 | 2026-01 | 1 | 83 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 40/0 | 2025-11-10 | 2025-11 | 11 | 2026-06-19 | 2026-06 | 6 | 221 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 16/1 | 2025-11-11 | 2025-11 | 11 | 2026-06-08 | 2026-06 | 6 | 209 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/25 | 2025-11-12 | 2025-11 | 11 | 2026-03-22 | 2026-03 | 3 | 130 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3/7 | 2025-11-12 | 2025-11 | 11 | 2026-01-27 | 2026-01 | 1 | 76 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 35/3 | 2025-11-13 | 2025-11 | 11 | 2026-03-10 | 2026-03 | 3 | 117 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 39/0 | 2025-11-14 | 2025-11 | 11 | 2026-07-22 | 2026-07 | 7 | 250 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 11/8 | 2025-11-16 | 2025-11 | 11 | 2026-01-27 | 2026-01 | 1 | 72 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 38/2 | 2025-11-16 | 2025-11 | 11 | 2026-07-20 | 2026-07 | 7 | 246 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/27 | 2025-11-17 | 2025-11 | 11 | 2026-01-19 | 2026-01 | 1 | 63 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/1 | 2025-11-18 | 2025-11 | 11 | 2026-06-21 | 2026-06 | 6 | 215 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3A/0 | 2025-11-19 | 2025-11 | 11 | 2026-03-29 | 2026-03 | 3 | 130 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20/7 | 2025-11-21 | 2025-11 | 11 | 2026-01-15 | 2026-01 | 1 | 55 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 38/0 | 2025-11-22 | 2025-11 | 11 | 2026-04-08 | 2026-04 | 4 | 137 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/16 | 2025-11-24 | 2025-11 | 11 | 2026-06-09 | 2026-06 | 6 | 197 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 38/1 | 2025-11-24 | 2025-11 | 11 | 2026-07-11 | 2026-07 | 7 | 229 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 32/0 | 2025-11-25 | 2025-11 | 11 | 2026-06-21 | 2026-06 | 6 | 208 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 32/4 | 2025-11-28 | 2025-11 | 11 | 2026-07-22 | 2026-07 | 7 | 236 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3/0 | 2025-11-29 | 2025-11 | 11 | 2026-07-31 | 2026-07 | 7 | 244 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/8 | 2025-11-29 | 2025-11 | 11 | 2026-05-06 | 2026-05 | 5 | 158 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 21/0 | 2025-12-01 | 2025-12 | 12 | 2026-06-29 | 2026-06 | 6 | 210 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 32/1 | 2025-12-01 | 2025-12 | 12 | 2026-08-07 | 2026-08 | 8 | 249 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2A/5 | 2025-12-02 | 2025-12 | 12 | 2026-07-07 | 2026-07 | 7 | 217 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 32/3 | 2025-12-02 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 5/0 | 2025-12-02 | 2025-12 | 12 | 2026-02-01 | 2026-02 | 2 | 61 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 35/5 | 2025-12-03 | 2025-12 | 12 | 2026-03-17 | 2026-03 | 3 | 104 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 32/5 | 2025-12-04 | 2025-12 | 12 | 2026-01-30 | 2026-01 | 1 | 57 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2A/4 | 2025-12-05 | 2025-12 | 12 | 2026-04-06 | 2026-04 | 4 | 122 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 32/6 | 2025-12-06 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 35/4 | 2025-12-07 | 2025-12 | 12 | 2026-03-23 | 2026-03 | 3 | 106 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/4 | 2025-12-07 | 2025-12 | 12 | 2026-02-01 | 2026-02 | 2 | 56 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/3 | 2025-12-08 | 2025-12 | 12 | 2026-01-28 | 2026-01 | 1 | 51 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2A/3 | 2025-12-09 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 35/6 | 2025-12-10 | 2025-12 | 12 | 2026-03-21 | 2026-03 | 3 | 101 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2A/2 | 2025-12-12 | 2025-12 | 12 | 2026-05-31 | 2026-05 | 5 | 170 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/2 | 2025-12-12 | 2025-12 | 12 | 2026-07-31 | 2026-07 | 7 | 231 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20A/0 | 2025-12-13 | 2025-12 | 12 | 2026-07-10 | 2026-07 | 7 | 209 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 35/8 | 2025-12-14 | 2025-12 | 12 | 2026-02-27 | 2026-02 | 2 | 75 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/1 | 2025-12-14 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 2A/1 | 2025-12-16 | 2025-12 | 12 | 2026-06-21 | 2026-06 | 6 | 187 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 32/7 | 2025-12-16 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 23/1 | 2025-12-17 | 2025-12 | 12 | 2026-02-24 | 2026-02 | 2 | 69 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 28/0 | 2025-12-17 | 2025-12 | 12 | 2026-02-15 | 2026-02 | 2 | 60 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 33/2 | 2025-12-17 | 2025-12 | 12 | 2026-02-27 | 2026-02 | 2 | 72 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 35/7 | 2025-12-17 | 2025-12 | 12 | 2026-03-12 | 2026-03 | 3 | 85 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/6 | 2025-12-19 | 2025-12 | 12 | 2026-03-10 | 2026-03 | 3 | 81 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 35/9 | 2025-12-21 | 2025-12 | 12 | 2026-02-19 | 2026-02 | 2 | 60 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 33/4 | 2025-12-23 | 2025-12 | 12 | 2026-04-24 | 2026-04 | 4 | 122 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2A/0 | 2025-12-25 | 2025-12 | 12 | 2026-06-27 | 2026-06 | 6 | 184 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 36/0 | 2025-12-26 | 2025-12 | 12 | 2026-08-10 | 2026-08 | 8 | 227 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/7 | 2025-12-26 | 2025-12 | 12 | 2026-03-14 | 2026-03 | 3 | 78 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 22/0 | 2025-12-27 | 2025-12 | 12 | 2026-06-19 | 2026-06 | 6 | 174 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 27/1 | 2025-12-27 | 2025-12 | 12 | 2026-07-10 | 2026-07 | 7 | 195 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2/6 | 2025-12-30 | 2025-12 | 12 | 2026-03-10 | 2026-03 | 3 | 70 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 36/1 | 2025-12-30 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 29/22 | 2025-12-31 | 2025-12 | 12 | 2026-01-27 | 2026-01 | 1 | 27 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2/3 | 2026-01-03 | 2026-01 | 1 | 2026-03-19 | 2026-03 | 3 | 75 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 23/0 | 2026-01-04 | 2026-01 | 1 | 2026-06-03 | 2026-06 | 6 | 150 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 33A/0 | 2026-01-05 | 2026-01 | 1 | 2026-06-19 | 2026-06 | 6 | 165 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 18/1 | 2026-01-11 | 2026-01 | 1 | 2026-02-10 | 2026-02 | 2 | 30 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 42/0 | 2026-01-11 | 2026-01 | 1 | 2026-08-06 | 2026-08 | 8 | 207 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 13/1 | 2026-01-12 | 2026-01 | 1 | 2026-07-18 | 2026-07 | 7 | 187 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/0 | 2026-01-13 | 2026-01 | 1 | 2026-06-30 | 2026-06 | 6 | 168 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 43/0 | 2026-01-16 | 2026-01 | 1 | 2026-07-20 | 2026-07 | 7 | 185 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2/0 | 2026-01-20 | 2026-01 | 1 | 2026-07-18 | 2026-07 | 7 | 179 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 33/3 | 2026-01-21 | 2026-01 | 1 | 2026-04-18 | 2026-04 | 4 | 87 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 33/1 | 2026-01-31 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 10/0 | 2026-02-02 | 2026-02 | 2 | 2026-06-24 | 2026-06 | 6 | 142 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 16/3 | 2026-02-07 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 32/8 | 2026-02-19 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 32/9 | 2026-02-22 | 2026-02 | 2 | 2026-06-12 | 2026-06 | 6 | 110 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 33/0 | 2026-03-03 | 2026-03 | 3 | 2026-06-05 | 2026-06 | 6 | 94 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 44/0 | 2026-03-09 | 2026-03 | 3 | 2026-08-09 | 2026-08 | 8 | 153 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 32/2 | 2026-03-15 | 2026-03 | 3 | 2026-03-29 | 2026-03 | 3 | 14 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 17/0 | 2026-04-03 | 2026-04 | 4 | 2026-06-17 | 2026-06 | 6 | 75 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 47/0 | 2026-04-08 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 18/0 | 2026-04-12 | 2026-04 | 4 | 2026-06-29 | 2026-06 | 6 | 78 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 44/1 | 2026-04-15 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 45/0 | 2026-04-24 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 46/0 | 2026-04-24 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 34/1 | 2026-04-29 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 11/7 | 2026-05-09 | 2026-05 | 5 | 2026-07-04 | 2026-07 | 7 | 56 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/10 | 2026-05-21 | 2026-05 | 5 | 2026-08-11 | 2026-08 | 8 | 82 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 27/0 | 2026-05-25 | 2026-05 | 5 | 2026-07-19 | 2026-07 | 7 | 55 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 11/0 | 2026-05-29 | 2026-05 | 5 | 2026-07-12 | 2026-07 | 7 | 44 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 25/1 | 2026-05-31 | 2026-05 | 5 | 2026-07-13 | 2026-07 | 7 | 43 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 1A/0 | 2026-06-03 | 2026-06 | 6 | 2026-08-08 | 2026-08 | 8 | 66 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 16/0 | 2026-06-04 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 26/0 | 2026-06-10 | 2026-06 | 6 | 2026-07-21 | 2026-07 | 7 | 41 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 23/4 | 2026-06-12 | 2026-06 | 6 | 2026-07-11 | 2026-07 | 7 | 29 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 1/2 | 2026-06-24 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 24/0 | 2026-06-25 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 1/1 | 2026-07-01 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 32/10 | 2026-07-03 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 25/0 | 2026-07-05 | 2026-07 | 7 | 2026-07-31 | 2026-07 | 7 | 26 | Yes | No | exact |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation | TA 512 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 1/0 | 2026-07-09 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 30/15 | 2026-08-05 | 2026-08 | 8 |  |  |  |  | No | No |  |  |  | TA 512 - DPR - 2026-08-12.xlsx | Foundation
TA 513 | 5xx | Government | ta513 | 25/1 | 2025-03-28 | 2025-03 | 3 | 2025-09-23 | 2025-09 | 9 | 179 | Yes | No | fallback_single_line | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 25/2 | 2025-04-01 | 2025-04 | 4 | 2025-09-17 | 2025-09 | 9 | 169 | Yes | No | fallback_single_line | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 24/2 | 2025-04-04 | 2025-04 | 4 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 24/1 | 2025-04-07 | 2025-04 | 4 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 26/2 | 2025-04-12 | 2025-04 | 4 | 2025-10-03 | 2025-10 | 10 | 174 | Yes | No | fallback_single_line | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 30/2 | 2025-04-12 | 2025-04 | 4 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 23/6 | 2025-04-14 | 2025-04 | 4 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 23/5 | 2025-04-16 | 2025-04 | 4 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 31/1 | 2025-04-17 | 2025-04 | 4 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 30/3 | 2025-04-22 | 2025-04 | 4 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 37/1 | 2025-04-24 | 2025-04 | 4 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 30/1 | 2025-04-25 | 2025-04 | 4 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 30/2 | 2025-04-28 | 2025-04 | 4 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 24/3 | 2025-04-29 | 2025-04 | 4 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 31/2 | 2025-04-30 | 2025-04 | 4 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 29/5 | 2025-05-01 | 2025-05 | 5 | 2025-11-11 | 2025-11 | 11 | 194 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 29/2 | 2025-05-03 | 2025-05 | 5 | 2025-11-27 | 2025-11 | 11 | 208 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 29/4 | 2025-05-04 | 2025-05 | 5 | 2025-11-03 | 2025-11 | 11 | 183 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 29/3 | 2025-05-05 | 2025-05 | 5 | 2025-11-15 | 2025-11 | 11 | 194 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 29/1 | 2025-05-06 | 2025-05 | 5 | 2025-12-03 | 2025-12 | 12 | 211 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 28/3 | 2025-05-09 | 2025-05 | 5 | 2025-10-25 | 2025-10 | 10 | 169 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 28/4 | 2025-05-09 | 2025-05 | 5 | 2025-11-06 | 2025-11 | 11 | 181 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 28/2 | 2025-05-11 | 2025-05 | 5 | 2025-10-31 | 2025-10 | 10 | 173 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 24/4 | 2025-05-17 | 2025-05 | 5 | 2025-09-29 | 2025-09 | 9 | 135 | Yes | No | fallback_single_line | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 3/5 | 2025-05-20 | 2025-05 | 5 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/7 | 2025-05-20 | 2025-05 | 5 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 23/3 | 2025-05-24 | 2025-05 | 5 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 3/6 | 2025-05-24 | 2025-05 | 5 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 3/10 | 2025-05-27 | 2025-05 | 5 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 32B/1 | 2025-05-28 | 2025-05 | 5 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 21/7 | 2025-06-02 | 2025-06 | 6 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 21/6 | 2025-06-05 | 2025-06 | 6 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 23/1 | 2025-06-07 | 2025-06 | 6 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 23/3 | 2025-06-09 | 2025-06 | 6 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 23/2 | 2025-06-11 | 2025-06 | 6 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 23/4 | 2025-06-15 | 2025-06 | 6 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 18/4 | 2025-06-28 | 2025-06 | 6 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 56/1 | 2025-06-28 | 2025-06 | 6 | 2026-03-08 | 2026-03 | 3 | 253 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 14/4 | 2025-07-01 | 2025-07 | 7 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 26/1 | 2025-07-03 | 2025-07 | 7 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 56/2 | 2025-07-05 | 2025-07 | 7 | 2026-01-23 | 2026-01 | 1 | 202 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 14/3 | 2025-07-07 | 2025-07 | 7 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 56/4 | 2025-07-10 | 2025-07 | 7 | 2026-06-04 | 2026-06 | 6 | 329 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 14/2 | 2025-07-13 | 2025-07 | 7 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 56/0 | 2025-07-15 | 2025-07 | 7 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/5 | 2025-07-20 | 2025-07 | 7 | 2025-12-15 | 2025-12 | 12 | 148 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 15B/4 | 2025-07-21 | 2025-07 | 7 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/0 | 2025-07-24 | 2025-07 | 7 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/6 | 2025-07-28 | 2025-07 | 7 | 2026-01-16 | 2026-01 | 1 | 172 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 54/6 | 2025-08-09 | 2025-08 | 8 | 2026-01-29 | 2026-01 | 1 | 173 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 36/3 | 2025-08-20 | 2025-08 | 8 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 56/3 | 2025-08-24 | 2025-08 | 8 | 2026-06-12 | 2026-06 | 6 | 292 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 36/4 | 2025-09-01 | 2025-09 | 9 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 27/0 | 2025-09-14 | 2025-09 | 9 | 2025-10-19 | 2025-10 | 10 | 35 | Yes | No | fallback_single_line | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 26/0 | 2025-09-18 | 2025-09 | 9 | 2025-10-14 | 2025-10 | 10 | 26 | Yes | No | fallback_single_line | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 30/0 | 2025-09-19 | 2025-09 | 9 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 25/0 | 2025-09-20 | 2025-09 | 9 | 2025-10-10 | 2025-10 | 10 | 20 | Yes | No | fallback_single_line | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 24/0 | 2025-09-24 | 2025-09 | 9 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 29/0 | 2025-09-24 | 2025-09 | 9 | 2025-11-19 | 2025-11 | 11 | 56 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 19/0 | 2025-10-01 | 2025-10 | 10 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 28/0 | 2025-10-05 | 2025-10 | 10 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 18/0 | 2025-10-06 | 2025-10 | 10 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 54/3 | 2025-11-11 | 2025-11 | 11 | 2026-03-01 | 2026-03 | 3 | 110 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 54/7 | 2025-11-23 | 2025-11 | 11 | 2026-03-16 | 2026-03 | 3 | 113 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 51/4 | 2025-12-05 | 2025-12 | 12 | 2026-05-18 | 2026-05 | 5 | 164 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 51/2 | 2025-12-09 | 2025-12 | 12 | 2026-05-10 | 2026-05 | 5 | 152 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 54/5 | 2025-12-15 | 2025-12 | 12 | 2026-03-12 | 2026-03 | 3 | 87 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 52/4 | 2025-12-18 | 2025-12 | 12 | 2026-04-01 | 2026-04 | 4 | 104 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 51/5 | 2025-12-23 | 2025-12 | 12 | 2026-05-23 | 2026-05 | 5 | 151 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 54/8 | 2026-02-15 | 2026-02 | 2 | 2026-03-24 | 2026-03 | 3 | 37 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 52/3 | 2026-02-25 | 2026-02 | 2 | 2026-05-31 | 2026-05 | 5 | 95 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/1 | 2026-03-07 | 2026-03 | 3 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/2 | 2026-04-11 | 2026-04 | 4 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 52/2 | 2026-05-03 | 2026-05 | 5 | 2026-06-17 | 2026-06 | 6 | 45 | Yes | No | fallback_single_line | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/4 | 2026-05-04 | 2026-05 | 5 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 52/0 | 2026-05-05 | 2026-05 | 5 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 52/1 | 2026-05-10 | 2026-05 | 5 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 52/5 | 2026-05-11 | 2026-05 | 5 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/3 | 2026-05-15 | 2026-05 | 5 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 64/2 | 2026-05-16 | 2026-05 | 5 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 30/0 | 2026-05-17 | 2026-05 | 5 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 64/5 | 2026-05-19 | 2026-05 | 5 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 64/3 | 2026-05-21 | 2026-05 | 5 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 28/1 | 2026-05-22 | 2026-05 | 5 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 51/3 | 2026-05-23 | 2026-05 | 5 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 64/4 | 2026-05-25 | 2026-05 | 5 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 64/6 | 2026-05-29 | 2026-05 | 5 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 61/2 | 2026-05-30 | 2026-05 | 5 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 74/9 | 2026-05-30 | 2026-05 | 5 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 64/1 | 2026-06-01 | 2026-06 | 6 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 54/1 | 2026-06-07 | 2026-06 | 6 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 74/8 | 2026-06-07 | 2026-06 | 6 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/1 | 2026-06-09 | 2026-06 | 6 |  |  |  |  | No | No |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 62/1 | 2026-06-09 | 2026-06 | 6 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 61/0 | 2026-06-14 | 2026-06 | 6 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 74/7 | 2026-06-14 | 2026-06 | 6 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 51/1 | 2026-06-17 | 2026-06 | 6 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 61/1 | 2026-06-18 | 2026-06 | 6 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 51/0 | 2026-06-25 | 2026-06 | 6 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 54/2 | 2026-06-27 | 2026-06 | 6 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 44/2 | 2026-07-08 | 2026-07 | 7 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 46/1 | 2026-07-10 | 2026-07 | 7 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 36/5 | 2026-07-16 | 2026-07 | 7 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 43/0 | 2026-07-17 | 2026-07 | 7 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 45/2 | 2026-07-20 | 2026-07 | 7 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 45/1 | 2026-08-01 | 2026-08 | 8 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 42/1 | 2026-08-07 | 2026-08 | 8 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 12/4 | 2026-08-09 | 2026-08 | 8 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 45/0 | 2026-08-11 | 2026-08 | 8 |  |  |  |  | No | No |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 601 | 6xx | Government | ta601 | 81/2 | 2025-08-07 | 2025-08 | 8 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 82/1 | 2025-08-22 | 2025-08 | 8 | 2026-01-11 | 2026-01 | 1 | 142 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 81/1 | 2025-09-13 | 2025-09 | 9 | 2026-02-10 | 2026-02 | 2 | 150 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 80/5 | 2025-09-18 | 2025-09 | 9 | 2026-01-15 | 2026-01 | 1 | 119 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 80/1 | 2025-10-10 | 2025-10 | 10 | 2026-01-19 | 2026-01 | 1 | 101 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 59/5 | 2025-10-19 | 2025-10 | 10 | 2026-01-22 | 2026-01 | 1 | 95 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 84/3 | 2025-10-19 | 2025-10 | 10 | 2026-01-16 | 2026-01 | 1 | 89 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 59/4 | 2025-10-21 | 2025-10 | 10 | 2026-01-15 | 2026-01 | 1 | 86 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 84/4 | 2025-10-24 | 2025-10 | 10 | 2026-01-19 | 2026-01 | 1 | 87 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 60/2 | 2025-10-25 | 2025-10 | 10 | 2026-01-27 | 2026-01 | 1 | 94 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 80/4 | 2025-10-27 | 2025-10 | 10 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 77/4 | 2025-10-31 | 2025-10 | 10 | 2026-01-07 | 2026-01 | 1 | 68 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 77/10 | 2025-11-05 | 2025-11 | 11 | 2026-01-26 | 2026-01 | 1 | 82 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 59/2 | 2025-11-08 | 2025-11 | 11 | 2025-12-22 | 2025-12 | 12 | 44 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 77/7 | 2025-11-09 | 2025-11 | 11 | 2026-01-17 | 2026-01 | 1 | 69 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 77/8 | 2025-11-13 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 60/3 | 2025-11-15 | 2025-11 | 11 | 2026-06-03 | 2026-06 | 6 | 200 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 77/3 | 2025-11-19 | 2025-11 | 11 | 2025-12-22 | 2025-12 | 12 | 33 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 60/8 | 2025-11-23 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 77/1 | 2025-11-25 | 2025-11 | 11 | 2026-01-01 | 2026-01 | 1 | 37 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 59/1 | 2025-11-29 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 77/2 | 2025-11-30 | 2025-11 | 11 | 2025-12-25 | 2025-12 | 12 | 25 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 58/2 | 2025-12-03 | 2025-12 | 12 | 2025-12-25 | 2025-12 | 12 | 22 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 58/1 | 2025-12-08 | 2025-12 | 12 | 2026-01-02 | 2026-01 | 1 | 25 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 77/6 | 2025-12-12 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 58/3 | 2025-12-14 | 2025-12 | 12 | 2026-01-09 | 2026-01 | 1 | 26 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/7 | 2025-12-15 | 2025-12 | 12 | 2026-01-12 | 2026-01 | 1 | 28 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 73/1 | 2025-12-18 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 56/3 | 2025-12-19 | 2025-12 | 12 | 2026-02-25 | 2026-02 | 2 | 68 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/6 | 2025-12-20 | 2025-12 | 12 | 2026-12-05 | 2026-12 | 12 | 350 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/9 | 2025-12-23 | 2025-12 | 12 | 2026-01-31 | 2026-01 | 1 | 39 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 56/1 | 2025-12-24 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 73/2 | 2025-12-24 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 79/1 | 2025-12-25 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 99/8 | 2025-12-26 | 2025-12 | 12 | 2026-01-30 | 2026-01 | 1 | 35 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 56/2 | 2025-12-27 | 2025-12 | 12 | 2026-02-20 | 2026-02 | 2 | 55 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/10 | 2025-12-29 | 2025-12 | 12 | 2026-01-23 | 2026-01 | 1 | 25 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 79/3 | 2025-12-30 | 2025-12 | 12 | 2026-02-01 | 2026-02 | 2 | 33 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 55/3 | 2025-12-31 | 2025-12 | 12 | 2026-03-11 | 2026-03 | 3 | 70 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 84/6 | 2025-12-31 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 94/1 | 2025-12-31 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 99/11 | 2025-12-31 | 2025-12 | 12 | 2026-01-17 | 2026-01 | 1 | 17 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 79/2 | 2026-01-05 | 2026-01 | 1 | 2026-01-27 | 2026-01 | 1 | 22 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 56/4 | 2026-01-06 | 2026-01 | 1 | 2026-03-18 | 2026-03 | 3 | 71 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/12 | 2026-01-06 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 84/5 | 2026-01-08 | 2026-01 | 1 | 2026-01-28 | 2026-01 | 1 | 20 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 56/9 | 2026-01-10 | 2026-01 | 1 | 2026-02-10 | 2026-02 | 2 | 31 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/2 | 2026-01-12 | 2026-01 | 1 | 2026-01-27 | 2026-01 | 1 | 15 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 84/1 | 2026-01-12 | 2026-01 | 1 | 2026-01-25 | 2026-01 | 1 | 13 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/3 | 2026-01-14 | 2026-01 | 1 | 2026-07-28 | 2026-07 | 7 | 195 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 83/0 | 2026-01-14 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 56/7 | 2026-01-16 | 2026-01 | 1 | 2025-12-15 | 2025-12 | 12 | -32 | Yes | Yes | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 56/6 | 2026-01-17 | 2026-01 | 1 | 2026-02-03 | 2026-02 | 2 | 17 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 56/8 | 2026-01-21 | 2026-01 | 1 | 2026-02-06 | 2026-02 | 2 | 16 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 101/2 | 2026-01-22 | 2026-01 | 1 | 2026-02-05 | 2026-02 | 2 | 14 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 85/2 | 2026-01-22 | 2026-01 | 1 | 2026-01-31 | 2026-01 | 1 | 9 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/1 | 2026-01-23 | 2026-01 | 1 | 2026-01-30 | 2026-01 | 1 | 7 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/4 | 2026-01-24 | 2026-01 | 1 | 2026-03-20 | 2026-03 | 3 | 55 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 102/4 | 2026-01-26 | 2026-01 | 1 | 2026-02-14 | 2026-02 | 2 | 19 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 59/0 | 2026-01-26 | 2026-01 | 1 | 2026-05-19 | 2026-05 | 5 | 113 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 84/0 | 2026-01-26 | 2026-01 | 1 | 2026-02-05 | 2026-02 | 2 | 10 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/5 | 2026-01-27 | 2026-01 | 1 | 2026-02-08 | 2026-02 | 2 | 12 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 101/1 | 2026-01-28 | 2026-01 | 1 | 2026-02-16 | 2026-02 | 2 | 19 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 55/1 | 2026-01-28 | 2026-01 | 1 | 2026-02-14 | 2026-02 | 2 | 17 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 53/2 | 2026-01-30 | 2026-01 | 1 | 2026-02-25 | 2026-02 | 2 | 26 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 101/0 | 2026-01-31 | 2026-01 | 1 | 2026-02-20 | 2026-02 | 2 | 20 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 101/3 | 2026-01-31 | 2026-01 | 1 | 2026-02-12 | 2026-02 | 2 | 12 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 102/5 | 2026-01-31 | 2026-01 | 1 | 2026-02-15 | 2026-02 | 2 | 15 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 52/0 | 2026-01-31 | 2026-01 | 1 | 2026-02-17 | 2026-02 | 2 | 17 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/9 | 2026-02-05 | 2026-02 | 2 | 2026-02-28 | 2026-02 | 2 | 23 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 78/3 | 2026-02-06 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 102/3 | 2026-02-08 | 2026-02 | 2 | 2026-02-22 | 2026-02 | 2 | 14 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 53/1 | 2026-02-08 | 2026-02 | 2 | 2026-02-22 | 2026-02 | 2 | 14 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 77/9 | 2026-02-10 | 2026-02 | 2 | 2026-02-24 | 2026-02 | 2 | 14 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 102/2 | 2026-02-11 | 2026-02 | 2 | 2026-02-20 | 2026-02 | 2 | 9 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 50/1 | 2026-02-12 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 101/5 | 2026-02-14 | 2026-02 | 2 | 2026-02-27 | 2026-02 | 2 | 13 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 102/1 | 2026-02-14 | 2026-02 | 2 | 2026-02-24 | 2026-02 | 2 | 10 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 83/1 | 2026-02-15 | 2026-02 | 2 | 2026-02-24 | 2026-02 | 2 | 9 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 50/2 | 2026-02-17 | 2026-02 | 2 | 2026-06-20 | 2026-06 | 6 | 123 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 101/6 | 2026-02-22 | 2026-02 | 2 | 2026-03-13 | 2026-03 | 3 | 19 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/6 | 2026-02-24 | 2026-02 | 2 | 2026-03-10 | 2026-03 | 3 | 14 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 85/1 | 2026-02-25 | 2026-02 | 2 | 2026-03-08 | 2026-03 | 3 | 11 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/8 | 2026-02-26 | 2026-02 | 2 | 2026-03-30 | 2026-03 | 3 | 32 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/7 | 2026-02-28 | 2026-02 | 2 | 2026-03-16 | 2026-03 | 3 | 16 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 101/7 | 2026-02-28 | 2026-02 | 2 | 2026-03-16 | 2026-03 | 3 | 16 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 89/1 | 2026-03-03 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 53/4 | 2026-03-06 | 2026-03 | 3 | 2026-03-26 | 2026-03 | 3 | 20 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 53/5 | 2026-03-08 | 2026-03 | 3 | 2026-04-02 | 2026-04 | 4 | 25 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 49/10 | 2026-03-11 | 2026-03 | 3 | 2026-06-08 | 2026-06 | 6 | 89 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/7 | 2026-03-13 | 2026-03 | 3 | 2026-07-07 | 2026-07 | 7 | 116 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 49/11 | 2026-03-14 | 2026-03 | 3 | 2026-06-13 | 2026-06 | 6 | 91 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/8 | 2026-03-14 | 2026-03 | 3 | 2026-06-16 | 2026-06 | 6 | 94 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/10 | 2026-03-17 | 2026-03 | 3 | 2026-06-09 | 2026-06 | 6 | 84 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/0 | 2026-03-18 | 2026-03 | 3 | 2026-04-05 | 2026-04 | 4 | 18 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 90/0 | 2026-03-18 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 51/6 | 2026-03-19 | 2026-03 | 3 | 2026-07-01 | 2026-07 | 7 | 104 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 52/1 | 2026-03-22 | 2026-03 | 3 | 2026-06-24 | 2026-06 | 6 | 94 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 50/3 | 2026-03-25 | 2026-03 | 3 | 2026-06-19 | 2026-06 | 6 | 86 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/2 | 2026-03-27 | 2026-03 | 3 | 2026-07-15 | 2026-07 | 7 | 110 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 53/3 | 2026-03-31 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 60/0 | 2026-04-06 | 2026-04 | 4 | 2026-05-05 | 2026-05 | 5 | 29 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 70/1 | 2026-04-11 | 2026-04 | 4 | 2026-06-15 | 2026-06 | 6 | 65 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 53/0 | 2026-04-13 | 2026-04 | 4 | 2026-07-12 | 2026-07 | 7 | 90 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 70/2 | 2026-04-13 | 2026-04 | 4 | 2026-06-29 | 2026-06 | 6 | 77 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 50/0 | 2026-04-16 | 2026-04 | 4 | 2025-06-26 | 2025-06 | 6 | -294 | Yes | Yes | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 70/4 | 2026-04-16 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 70/3 | 2026-04-18 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 66/1 | 2026-04-21 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 49/9 | 2026-04-23 | 2026-04 | 4 | 2026-07-20 | 2026-07 | 7 | 88 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 67/0 | 2026-04-26 | 2026-04 | 4 | 2026-06-29 | 2026-06 | 6 | 64 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 65/3 | 2026-04-29 | 2026-04 | 4 | 2026-06-19 | 2026-06 | 6 | 51 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 49/8 | 2026-04-30 | 2026-04 | 4 | 2026-06-06 | 2026-06 | 6 | 37 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 66/0 | 2026-05-03 | 2026-05 | 5 | 2026-06-24 | 2026-06 | 6 | 52 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 67/1 | 2026-05-05 | 2026-05 | 5 | 2026-06-10 | 2026-06 | 6 | 36 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 48/7 | 2026-05-10 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 69/0 | 2026-05-13 | 2026-05 | 5 | 2026-06-27 | 2026-06 | 6 | 45 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 69/2 | 2026-05-16 | 2026-05 | 5 | 2026-06-15 | 2026-06 | 6 | 30 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 48/3 | 2026-05-19 | 2026-05 | 5 | 2026-06-26 | 2026-06 | 6 | 38 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 69/1 | 2026-05-20 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 68/2 | 2026-05-23 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 48/2 | 2026-05-24 | 2026-05 | 5 | 2026-07-04 | 2026-07 | 7 | 41 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 68/0 | 2026-05-30 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 56/5 | 2026-05-31 | 2026-05 | 5 | 2026-06-14 | 2026-06 | 6 | 14 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 72/1 | 2026-06-01 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 73/0 | 2026-06-05 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 56/10 | 2026-06-07 | 2026-06 | 6 | 2026-06-21 | 2026-06 | 6 | 14 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 75/2 | 2026-06-07 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 75/3 | 2026-06-09 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 56/12 | 2026-06-12 | 2026-06 | 6 | 2026-06-29 | 2026-06 | 6 | 17 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 75/1 | 2026-06-12 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 77/5 | 2026-06-15 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 49/0 | 2026-06-17 | 2026-06 | 6 | 2026-07-29 | 2026-07 | 7 | 42 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 60/4 | 2026-06-19 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 49/1 | 2026-06-20 | 2026-06 | 6 | 2026-07-07 | 2026-07 | 7 | 17 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/1 | 2026-06-20 | 2026-06 | 6 | 2026-07-09 | 2026-07 | 7 | 19 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 48/0 | 2026-06-22 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 99/3 | 2026-06-22 | 2026-06 | 6 | 2026-07-07 | 2026-07 | 7 | 15 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/4 | 2026-06-23 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 56/11 | 2026-06-23 | 2026-06 | 6 | 2026-07-06 | 2026-07 | 7 | 13 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/4 | 2026-06-24 | 2026-06 | 6 | 2026-07-17 | 2026-07 | 7 | 23 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 102/0 | 2026-06-25 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 51/5 | 2026-06-26 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 99/2 | 2026-06-26 | 2026-06 | 6 | 2026-07-13 | 2026-07 | 7 | 17 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/1 | 2026-06-27 | 2026-06 | 6 | 2026-07-13 | 2026-07 | 7 | 16 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 49/2 | 2026-06-30 | 2026-06 | 6 | 2026-07-14 | 2026-07 | 7 | 14 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 56/0 | 2026-06-30 | 2026-06 | 6 | 2026-07-12 | 2026-07 | 7 | 12 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/0 | 2026-06-30 | 2026-06 | 6 | 2026-07-09 | 2026-07 | 7 | 9 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/0 | 2026-07-03 | 2026-07 | 7 | 2026-07-20 | 2026-07 | 7 | 17 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/5 | 2026-07-03 | 2026-07 | 7 | 2026-07-21 | 2026-07 | 7 | 18 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 98/4 | 2026-07-04 | 2026-07 | 7 | 2026-07-10 | 2026-07 | 7 | 6 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 52/2 | 2026-07-05 | 2026-07 | 7 | 2026-07-20 | 2026-07 | 7 | 15 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 98/3 | 2026-07-06 | 2026-07 | 7 | 2026-07-22 | 2026-07 | 7 | 16 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 72/0 | 2026-07-07 | 2026-07 | 7 | 2026-07-26 | 2026-07 | 7 | 19 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/3 | 2026-07-08 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 98/2 | 2026-07-08 | 2026-07 | 7 | 2026-07-17 | 2026-07 | 7 | 9 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 52/3 | 2026-07-10 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 57/0 | 2026-07-10 | 2026-07 | 7 | 2026-07-22 | 2026-07 | 7 | 12 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 71/0 | 2026-07-10 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 98/5 | 2026-07-10 | 2026-07 | 7 | 2026-07-24 | 2026-07 | 7 | 14 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 98/1 | 2026-07-12 | 2026-07 | 7 | 2026-07-28 | 2026-07 | 7 | 16 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 63/2 | 2026-07-13 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 58/0 | 2026-07-15 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 98/0 | 2026-07-15 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 76/0 | 2026-07-16 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 101/4 | 2026-07-17 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 49/3 | 2026-07-17 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 65/2 | 2026-07-18 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 54/0 | 2026-07-21 | 2026-07 | 7 | 2026-07-28 | 2026-07 | 7 | 7 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 78/1 | 2026-07-21 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 53/6 | 2026-07-23 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 101/9 | 2026-07-24 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 49/4 | 2026-07-26 | 2026-07 | 7 | 2026-07-30 | 2026-07 | 7 | 4 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 78/0 | 2026-07-26 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 97/1 | 2026-07-26 | 2026-07 | 7 | 2026-08-06 | 2026-08 | 8 | 11 | Yes | No | exact |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-12.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 52/4 | 2026-07-27 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 63/1 | 2026-07-27 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 96/8 | 2026-07-27 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 80/2 | 2026-07-28 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 96/7 | 2026-07-30 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 97/4 | 2026-08-01 | 2026-08 | 8 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 82/2 | 2026-08-03 | 2026-08 | 8 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 97/3 | 2026-08-03 | 2026-08 | 8 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 96/4 | 2026-08-06 | 2026-08 | 8 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 101/8 | 2026-08-08 | 2026-08 | 8 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 63/3 | 2026-08-09 | 2026-08 | 8 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 96/5 | 2026-08-09 | 2026-08 | 8 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 96/6 | 2026-08-11 | 2026-08 | 8 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 49/5 | 2026-08-12 | 2026-08 | 8 |  |  |  |  | No | No |  |  |  | TA 601 - DPR - 2026-08-12.xlsx | Progress Sheet
TB 408 | 4xx | Private | tb408 | 0 | 2023-10-01 | 2023-10 | 10 |  |  |  |  | No | No |  |  |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 408 | 4xx | Private | tb408 | 1 | 2024-09-01 | 2024-09 | 9 |  |  |  |  | No | No |  |  |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 408 | 4xx | Private | tb408 | 2 | 2024-11-01 | 2024-11 | 11 |  |  |  |  | No | No |  |  |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 408 | 4xx | Private | tb408 | 3 | 2024-11-01 | 2024-11 | 11 |  |  |  |  | No | No |  |  |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 408 | 4xx | Private | tb408 | 4 | 2024-11-01 | 2024-11 | 11 |  |  |  |  | No | No |  |  |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 408 | 4xx | Private | tb408 | 5 | 2024-12-01 | 2024-12 | 12 |  |  |  |  | No | No |  |  |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 501 | 5xx | Private | tb501 | 20/7 | 2024-08-12 | 2024-08 | 8 | 2025-02-19 | 2025-02 | 2 | 191 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 20/5 | 2024-08-16 | 2024-08 | 8 | 2025-02-17 | 2025-02 | 2 | 185 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/3 | 2024-08-19 | 2024-08 | 8 | 2025-01-05 | 2025-01 | 1 | 139 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 10/3 | 2024-09-09 | 2024-09 | 9 | 2025-03-11 | 2025-03 | 3 | 183 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/2 | 2024-09-11 | 2024-09 | 9 | 2024-12-24 | 2024-12 | 12 | 104 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/3 | 2024-09-15 | 2024-09 | 9 | 2024-12-25 | 2024-12 | 12 | 101 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/6 | 2024-09-19 | 2024-09 | 9 | 2025-02-13 | 2025-02 | 2 | 147 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/1 | 2024-09-22 | 2024-09 | 9 | 2024-12-19 | 2024-12 | 12 | 88 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/7 | 2024-09-23 | 2024-09 | 9 | 2025-02-14 | 2025-02 | 2 | 144 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/8 | 2024-09-28 | 2024-09 | 9 | 2025-03-13 | 2025-03 | 3 | 166 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 16/1 | 2024-10-01 | 2024-10 | 10 | 2025-02-14 | 2025-02 | 2 | 136 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 19/2 | 2024-10-04 | 2024-10 | 10 | 2025-01-20 | 2025-01 | 1 | 108 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 17/3 | 2024-10-06 | 2024-10 | 10 | 2025-01-29 | 2025-01 | 1 | 115 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 22/2 | 2024-10-09 | 2024-10 | 10 | 2025-02-25 | 2025-02 | 2 | 139 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-16 | 2024-10-10 | 2024-10 | 10 | 2025-02-14 | 2025-02 | 2 | 127 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 17/2 | 2024-10-11 | 2024-10 | 10 | 2025-02-01 | 2025-02 | 2 | 113 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 16/3 | 2024-10-16 | 2024-10 | 10 | 2025-02-18 | 2025-02 | 2 | 125 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/5 | 2024-10-18 | 2024-10 | 10 | 2025-01-03 | 2025-01 | 1 | 77 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-12 | 2024-10-19 | 2024-10 | 10 | 2025-03-20 | 2025-03 | 3 | 152 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-11 | 2024-10-20 | 2024-10 | 10 | 2025-04-30 | 2025-04 | 4 | 192 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-19 | 2024-10-20 | 2024-10 | 10 | 2025-01-16 | 2025-01 | 1 | 88 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/12 | 2024-10-21 | 2024-10 | 10 | 2025-03-03 | 2025-03 | 3 | 133 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-18 | 2024-10-21 | 2024-10 | 10 | 2025-02-21 | 2025-02 | 2 | 123 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 10/4 | 2024-10-22 | 2024-10 | 10 | 2025-04-23 | 2025-04 | 4 | 183 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 20/6 | 2024-10-22 | 2024-10 | 10 | 2025-03-05 | 2025-03 | 3 | 134 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/4 | 2024-10-24 | 2024-10 | 10 | 2025-02-05 | 2025-02 | 2 | 104 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 17/1 | 2024-10-24 | 2024-10 | 10 | 2025-02-18 | 2025-02 | 2 | 117 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/11 | 2024-10-24 | 2024-10 | 10 | 2025-01-28 | 2025-01 | 1 | 96 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 20/3 | 2024-10-26 | 2024-10 | 10 | 2025-02-28 | 2025-02 | 2 | 125 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/3 | 2024-10-26 | 2024-10 | 10 | 2025-02-18 | 2025-02 | 2 | 115 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 11/1 | 2024-10-27 | 2024-10 | 10 | 2025-03-13 | 2025-03 | 3 | 137 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 16/2 | 2024-10-27 | 2024-10 | 10 | 2025-02-22 | 2025-02 | 2 | 118 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 20/4 | 2024-10-30 | 2024-10 | 10 | 2025-03-02 | 2025-03 | 3 | 123 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/9 | 2024-10-30 | 2024-10 | 10 | 2025-05-19 | 2025-05 | 5 | 201 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-17 | 2024-10-31 | 2024-10 | 10 | 2025-02-07 | 2025-02 | 2 | 99 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/7 | 2024-11-03 | 2024-11 | 11 | 2025-02-09 | 2025-02 | 2 | 98 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/4 | 2024-11-04 | 2024-11 | 11 | 2025-01-02 | 2025-01 | 1 | 59 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 20/2 | 2024-11-05 | 2024-11 | 11 | 2025-02-23 | 2025-02 | 2 | 110 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/6 | 2024-11-06 | 2024-11 | 11 | 2025-02-11 | 2025-02 | 2 | 97 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 20/1 | 2024-11-08 | 2024-11 | 11 | 2025-02-21 | 2025-02 | 2 | 105 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-14 | 2024-11-08 | 2024-11 | 11 | 2025-05-08 | 2025-05 | 5 | 181 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/8 | 2024-11-09 | 2024-11 | 11 | 2025-02-11 | 2025-02 | 2 | 94 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-21 | 2024-11-09 | 2024-11 | 11 | 2025-03-06 | 2025-03 | 3 | 117 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/9 | 2024-11-12 | 2024-11 | 11 | 2025-02-16 | 2025-02 | 2 | 96 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-20 | 2024-11-12 | 2024-11 | 11 | 2025-02-26 | 2025-02 | 2 | 106 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/6 | 2024-11-14 | 2024-11 | 11 | 2025-01-07 | 2025-01 | 1 | 54 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 10/2 | 2024-11-15 | 2024-11 | 11 | 2025-03-17 | 2025-03 | 3 | 122 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/5 | 2024-11-15 | 2024-11 | 11 | 2025-02-10 | 2025-02 | 2 | 87 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/4 | 2024-11-17 | 2024-11 | 11 | 2025-02-07 | 2025-02 | 2 | 82 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 19/3 | 2024-11-18 | 2024-11 | 11 | 2025-01-22 | 2025-01 | 1 | 65 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/10 | 2024-11-19 | 2024-11 | 11 | 2025-02-23 | 2025-02 | 2 | 96 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/8 | 2024-11-19 | 2024-11 | 11 | 2025-02-19 | 2025-02 | 2 | 92 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/7 | 2024-11-20 | 2024-11 | 11 | 2025-01-14 | 2025-01 | 1 | 55 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 19/5 | 2024-11-21 | 2024-11 | 11 | 2025-05-09 | 2025-05 | 5 | 169 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 19/4 | 2024-11-24 | 2024-11 | 11 | 2025-01-24 | 2025-01 | 1 | 61 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/9 | 2024-11-26 | 2024-11 | 11 | 2025-01-11 | 2025-01 | 1 | 46 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 19/1 | 2024-11-26 | 2024-11 | 11 | 2025-01-18 | 2025-01 | 1 | 53 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-10 | 2024-11-26 | 2024-11 | 11 | 2025-03-27 | 2025-03 | 3 | 121 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/1 | 2024-11-29 | 2024-11 | 11 | 2024-12-30 | 2024-12 | 12 | 31 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/10 | 2024-11-30 | 2024-11 | 11 | 2025-01-12 | 2025-01 | 1 | 43 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/8 | 2024-11-30 | 2024-11 | 11 | 2025-01-09 | 2025-01 | 1 | 40 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/9 | 2024-12-04 | 2024-12 | 12 | 2025-02-21 | 2025-02 | 2 | 79 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 5/2 | 2024-12-06 | 2024-12 | 12 | 2025-03-26 | 2025-03 | 3 | 110 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 5/3 | 2024-12-07 | 2024-12 | 12 | 2025-03-29 | 2025-03 | 3 | 112 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/2 | 2024-12-08 | 2024-12 | 12 | 2024-12-27 | 2024-12 | 12 | 19 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/5 | 2024-12-09 | 2024-12 | 12 | 2025-02-07 | 2025-02 | 2 | 60 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8B/0 | 2024-12-11 | 2024-12 | 12 | 2025-04-20 | 2025-04 | 4 | 130 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-22 | 2024-12-11 | 2024-12 | 12 | 2025-02-26 | 2025-02 | 2 | 77 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 23/4 | 2024-12-15 | 2024-12 | 12 | 2025-03-02 | 2025-03 | 3 | 77 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-15 | 2024-12-15 | 2024-12 | 12 | 2025-02-04 | 2025-02 | 2 | 51 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 14/9 | 2024-12-19 | 2024-12 | 12 | 2025-02-01 | 2025-02 | 2 | 44 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 22/1 | 2024-12-19 | 2024-12 | 12 | 2025-02-27 | 2025-02 | 2 | 70 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/14 | 2024-12-19 | 2024-12 | 12 | 2025-03-16 | 2025-03 | 3 | 87 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8B/1 | 2024-12-19 | 2024-12 | 12 | 2025-04-02 | 2025-04 | 4 | 104 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 29A/2 | 2024-12-20 | 2024-12 | 12 | 2025-02-19 | 2025-02 | 2 | 61 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/13 | 2024-12-20 | 2024-12 | 12 | 2025-03-13 | 2025-03 | 3 | 83 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 23/2 | 2024-12-23 | 2024-12 | 12 | 2025-03-01 | 2025-03 | 3 | 68 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 14/7 | 2024-12-25 | 2024-12 | 12 | 2025-01-29 | 2025-01 | 1 | 35 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 29A/3 | 2024-12-25 | 2024-12 | 12 | 2025-02-21 | 2025-02 | 2 | 58 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/15 | 2024-12-25 | 2024-12 | 12 | 2025-03-23 | 2025-03 | 3 | 88 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 29A/1 | 2024-12-26 | 2024-12 | 12 | 2025-02-18 | 2025-02 | 2 | 54 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8B/2 | 2024-12-27 | 2024-12 | 12 | 2025-04-03 | 2025-04 | 4 | 97 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 30/1 | 2024-12-28 | 2024-12 | 12 | 2025-02-26 | 2025-02 | 2 | 60 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-30 | 2024-12-28 | 2024-12 | 12 | 2025-02-23 | 2025-02 | 2 | 57 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 5A/0 | 2024-12-29 | 2024-12 | 12 | 2025-03-30 | 2025-03 | 3 | 91 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 30/6 | 2024-12-30 | 2024-12 | 12 | 2025-03-02 | 2025-03 | 3 | 62 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 14/8 | 2024-12-31 | 2024-12 | 12 | 2025-01-30 | 2025-01 | 1 | 30 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 30/3 | 2024-12-31 | 2024-12 | 12 | 2025-01-30 | 2025-01 | 1 | 30 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8A/0 | 2025-01-04 | 2025-01 | 1 | 2025-04-28 | 2025-04 | 4 | 114 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 30/4 | 2025-01-05 | 2025-01 | 1 | 2025-03-05 | 2025-03 | 3 | 59 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 5/1 | 2025-01-05 | 2025-01 | 1 | 2025-04-12 | 2025-04 | 4 | 97 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 30/2 | 2025-01-06 | 2025-01 | 1 | 2025-03-02 | 2025-03 | 3 | 55 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-31 | 2025-01-07 | 2025-01 | 1 | 2025-02-28 | 2025-02 | 2 | 52 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/4 | 2025-01-08 | 2025-01 | 1 | 2025-03-20 | 2025-03 | 3 | 71 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 30/5 | 2025-01-10 | 2025-01 | 1 | 2025-03-03 | 2025-03 | 3 | 52 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/11 | 2025-01-12 | 2025-01 | 1 | 2025-03-11 | 2025-03 | 3 | 58 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/3 | 2025-01-14 | 2025-01 | 1 | 2025-03-18 | 2025-03 | 3 | 63 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/6 | 2025-01-14 | 2025-01 | 1 | 2025-03-09 | 2025-03 | 3 | 54 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 31/1 | 2025-01-15 | 2025-01 | 1 | 2025-07-11 | 2025-07 | 7 | 177 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8D/0 | 2025-01-16 | 2025-01 | 1 | 2025-04-15 | 2025-04 | 4 | 89 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/2 | 2025-01-18 | 2025-01 | 1 | 2025-03-21 | 2025-03 | 3 | 62 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 29A/4 | 2025-01-19 | 2025-01 | 1 | 2025-02-26 | 2025-02 | 2 | 38 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/5 | 2025-01-19 | 2025-01 | 1 | 2025-03-23 | 2025-03 | 3 | 63 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 32/1 | 2025-01-23 | 2025-01 | 1 | 2025-05-29 | 2025-05 | 5 | 126 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/1 | 2025-01-24 | 2025-01 | 1 | 2025-03-26 | 2025-03 | 3 | 61 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/2 | 2025-01-27 | 2025-01 | 1 | 2025-06-09 | 2025-06 | 6 | 133 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-32 | 2025-01-29 | 2025-01 | 1 | 2025-07-14 | 2025-07 | 7 | 166 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/9 | 2025-01-30 | 2025-01 | 1 | 2025-03-15 | 2025-03 | 3 | 44 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1D/0 | 2025-01-31 | 2025-01 | 1 | 2025-03-29 | 2025-03 | 3 | 57 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1A/2 | 2025-02-02 | 2025-02 | 2 | 2025-04-14 | 2025-04 | 4 | 71 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 2/0 | 2025-02-02 | 2025-02 | 2 | 2025-04-19 | 2025-04 | 4 | 76 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1A/1 | 2025-02-05 | 2025-02 | 2 | 2025-04-04 | 2025-04 | 4 | 58 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/0 | 2025-02-05 | 2025-02 | 2 | 2025-05-28 | 2025-05 | 5 | 112 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1/2 | 2025-02-06 | 2025-02 | 2 | 2025-03-29 | 2025-03 | 3 | 51 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-23 | 2025-02-06 | 2025-02 | 2 | 2025-08-17 | 2025-08 | 8 | 192 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/10 | 2025-02-08 | 2025-02 | 2 | 2025-03-11 | 2025-03 | 3 | 31 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 0/1 | 2025-02-09 | 2025-02 | 2 | 2025-04-02 | 2025-04 | 4 | 52 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 23/1 | 2025-02-10 | 2025-02 | 2 | 2025-03-05 | 2025-03 | 3 | 23 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/16 | 2025-02-12 | 2025-02 | 2 | 2025-03-21 | 2025-03 | 3 | 37 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 32/2 | 2025-02-15 | 2025-02 | 2 | 2025-05-24 | 2025-05 | 5 | 98 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/17 | 2025-02-15 | 2025-02 | 2 | 2025-03-19 | 2025-03 | 3 | 32 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1A/0 | 2025-02-17 | 2025-02 | 2 | 2025-04-21 | 2025-04 | 4 | 63 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 3/0 | 2025-02-18 | 2025-02 | 2 | 2025-05-01 | 2025-05 | 5 | 72 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/11 | 2025-02-19 | 2025-02 | 2 | 2025-05-10 | 2025-05 | 5 | 80 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 0/0 | 2025-02-20 | 2025-02 | 2 | 2025-04-07 | 2025-04 | 4 | 46 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1D/1 | 2025-02-22 | 2025-02 | 2 | 2025-03-27 | 2025-03 | 3 | 33 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1/1 | 2025-02-23 | 2025-02 | 2 | 2025-03-31 | 2025-03 | 3 | 36 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1C/1 | 2025-02-25 | 2025-02 | 2 | 2025-05-17 | 2025-05 | 5 | 81 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 20/8 | 2025-02-25 | 2025-02 | 2 | 2025-11-10 | 2025-11 | 11 | 258 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 23/3 | 2025-02-28 | 2025-02 | 2 | 2025-05-26 | 2025-05 | 5 | 87 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1B/0 | 2025-03-05 | 2025-03 | 3 | 2025-04-25 | 2025-04 | 4 | 51 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 7/1 | 2025-03-09 | 2025-03 | 3 | 2025-04-05 | 2025-04 | 4 | 27 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 7/0 | 2025-03-16 | 2025-03 | 3 | 2025-04-08 | 2025-04 | 4 | 23 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 7/2 | 2025-03-16 | 2025-03 | 3 | 2025-04-05 | 2025-04 | 4 | 20 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-26 | 2025-03-16 | 2025-03 | 3 | 2025-06-04 | 2025-06 | 6 | 80 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1E/0 | 2025-03-22 | 2025-03 | 3 | 2025-05-25 | 2025-05 | 5 | 64 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 7/3 | 2025-03-23 | 2025-03 | 3 | 2025-04-21 | 2025-04 | 4 | 29 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1/0 | 2025-03-27 | 2025-03 | 3 | 2025-04-11 | 2025-04 | 4 | 15 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 5/0 | 2025-03-28 | 2025-03 | 3 | 2025-07-14 | 2025-07 | 7 | 108 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-27 | 2025-04-03 | 2025-04 | 4 | 2025-07-24 | 2025-07 | 7 | 112 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-13 | 2025-04-08 | 2025-04 | 4 | 2025-05-23 | 2025-05 | 5 | 45 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/1 | 2025-04-15 | 2025-04 | 4 | 2025-05-17 | 2025-05 | 5 | 32 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-25 | 2025-04-17 | 2025-04 | 4 | 2025-07-24 | 2025-07 | 7 | 98 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 10/1 | 2025-04-19 | 2025-04 | 4 | 2025-05-21 | 2025-05 | 5 | 32 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/2 | 2025-04-21 | 2025-04 | 4 | 2025-05-14 | 2025-05 | 5 | 23 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/5 | 2025-04-25 | 2025-04 | 4 | 2025-06-25 | 2025-06 | 6 | 61 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/4 | 2025-04-26 | 2025-04 | 4 | 2025-06-21 | 2025-06 | 6 | 56 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/13 | 2025-04-27 | 2025-04 | 4 | 2025-05-17 | 2025-05 | 5 | 20 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-24 | 2025-04-29 | 2025-04 | 4 | 2025-06-09 | 2025-06 | 6 | 41 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 23/5 | 2025-04-30 | 2025-04 | 4 | 2025-05-29 | 2025-05 | 5 | 29 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 29A/0 | 2025-05-10 | 2025-05 | 5 | 2025-08-11 | 2025-08 | 8 | 93 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8C/0 | 2025-05-12 | 2025-05 | 5 | 2025-06-04 | 2025-06 | 6 | 23 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/12 | 2025-05-13 | 2025-05 | 5 | 2025-06-04 | 2025-06 | 6 | 22 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-29 | 2025-05-14 | 2025-05 | 5 | 2025-06-13 | 2025-06 | 6 | 30 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/1 | 2025-05-17 | 2025-05 | 5 | 2025-07-04 | 2025-07 | 7 | 48 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8/0 | 2025-05-18 | 2025-05 | 5 | 2025-06-06 | 2025-06 | 6 | 19 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-9 | 2025-05-18 | 2025-05 | 5 | 2025-07-02 | 2025-07 | 7 | 45 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/2 | 2025-05-22 | 2025-05 | 5 | 2025-07-01 | 2025-07 | 7 | 40 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/6 | 2025-05-23 | 2025-05 | 5 | 2025-06-27 | 2025-06 | 6 | 35 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 28/1 | 2025-05-24 | 2025-05 | 5 | 2025-10-18 | 2025-10 | 10 | 147 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/10 | 2025-05-25 | 2025-05 | 5 | 2025-06-13 | 2025-06 | 6 | 19 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/5 | 2025-05-25 | 2025-05 | 5 | 2025-07-28 | 2025-07 | 7 | 64 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-28 | 2025-05-25 | 2025-05 | 5 | 2025-06-15 | 2025-06 | 6 | 21 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/8 | 2025-05-26 | 2025-05 | 5 | 2025-06-20 | 2025-06 | 6 | 25 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/12 | 2025-05-27 | 2025-05 | 5 | 2025-07-06 | 2025-07 | 7 | 40 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/9 | 2025-05-29 | 2025-05 | 5 | 2025-06-17 | 2025-06 | 6 | 19 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/7 | 2025-05-29 | 2025-05 | 5 | 2025-07-01 | 2025-07 | 7 | 33 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/11 | 2025-05-30 | 2025-05 | 5 | 2025-06-15 | 2025-06 | 6 | 16 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/6 | 2025-06-04 | 2025-06 | 6 | 2025-06-20 | 2025-06 | 6 | 16 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/3 | 2025-06-05 | 2025-06 | 6 | 2025-07-03 | 2025-07 | 7 | 28 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/4 | 2025-06-05 | 2025-06 | 6 | 2025-07-07 | 2025-07 | 7 | 32 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/3 | 2025-06-06 | 2025-06 | 6 | 2025-06-22 | 2025-06 | 6 | 16 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/1 | 2025-06-08 | 2025-06 | 6 | 2025-06-23 | 2025-06 | 6 | 15 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 28/2 | 2025-06-29 | 2025-06 | 6 | 2025-08-14 | 2025-08 | 8 | 46 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 17/0 | 2025-07-10 | 2025-07 | 7 | 2025-08-28 | 2025-08 | 8 | 49 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 8D/5 | 2025-08-17 | 2025-08 | 8 | 2025-11-03 | 2025-11 | 11 | 78 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8D/6 | 2025-08-23 | 2025-08 | 8 | 2025-11-05 | 2025-11 | 11 | 74 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8D/4 | 2025-08-30 | 2025-08 | 8 | 2025-11-02 | 2025-11 | 11 | 64 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/8 | 2025-09-03 | 2025-09 | 9 | 2025-12-22 | 2025-12 | 12 | 110 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 14/1 | 2025-09-07 | 2025-09 | 9 | 2025-10-26 | 2025-10 | 10 | 49 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8D/3 | 2025-09-10 | 2025-09 | 9 | 2025-11-26 | 2025-11 | 11 | 77 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 14/3 | 2025-09-12 | 2025-09 | 9 | 2025-10-27 | 2025-10 | 10 | 45 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 14/2 | 2025-09-20 | 2025-09 | 9 | 2025-10-21 | 2025-10 | 10 | 31 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/0 | 2025-09-21 | 2025-09 | 9 | 2025-11-07 | 2025-11 | 11 | 47 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/7 | 2025-09-26 | 2025-09 | 9 | 2026-01-19 | 2026-01 | 1 | 115 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 14/4 | 2025-09-30 | 2025-09 | 9 | 2025-11-14 | 2025-11 | 11 | 45 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 14/5 | 2025-10-08 | 2025-10 | 10 | 2025-10-29 | 2025-10 | 10 | 21 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 5A/1 | 2025-10-08 | 2025-10 | 10 | 2025-11-23 | 2025-11 | 11 | 46 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 5A/2 | 2025-10-12 | 2025-10 | 10 | 2025-11-22 | 2025-11 | 11 | 41 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 5B/0 | 2025-10-17 | 2025-10 | 10 | 2025-11-21 | 2025-11 | 11 | 35 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 16/0 | 2025-10-23 | 2025-10 | 10 | 2025-11-12 | 2025-11 | 11 | 20 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 16/1 | 2025-10-27 | 2025-10 | 10 | 2025-11-14 | 2025-11 | 11 | 18 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 14/6 | 2025-11-05 | 2025-11 | 11 | 2025-11-15 | 2025-11 | 11 | 10 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/0 | 2025-11-07 | 2025-11 | 11 | 2025-12-15 | 2025-12 | 12 | 38 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 13/1 | 2025-11-08 | 2025-11 | 11 | 2025-11-10 | 2025-11 | 11 | 2 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 16/2 | 2025-11-15 | 2025-11 | 11 | 2025-11-17 | 2025-11 | 11 | 2 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 8E/7 | 2025-11-16 | 2025-11 | 11 | 2025-11-29 | 2025-11 | 11 | 13 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8D/1 | 2025-11-20 | 2025-11 | 11 | 2025-11-27 | 2025-11 | 11 | 7 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 6/0 | 2025-11-26 | 2025-11 | 11 | 2025-12-18 | 2025-12 | 12 | 22 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8D/2 | 2025-12-03 | 2025-12 | 12 | 2025-12-07 | 2025-12 | 12 | 4 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8D/0A | 2025-12-07 | 2025-12 | 12 | 2025-12-04 | 2025-12 | 12 | -3 | Yes | Yes | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 10/0 | 2025-12-13 | 2025-12 | 12 | 2025-12-28 | 2025-12 | 12 | 15 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 15/2 | 2025-12-15 | 2025-12 | 12 | 2025-12-27 | 2025-12 | 12 | 12 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 11/0 | 2025-12-16 | 2025-12 | 12 | 2026-01-11 | 2026-01 | 1 | 26 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 15/1 | 2025-12-16 | 2025-12 | 12 | 2025-12-31 | 2025-12 | 12 | 15 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 12/0 | 2025-12-17 | 2025-12 | 12 | 2026-01-06 | 2026-01 | 1 | 20 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 15/3 | 2025-12-19 | 2025-12 | 12 | 2025-12-25 | 2025-12 | 12 | 6 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 13/0 | 2025-12-25 | 2025-12 | 12 | 2026-01-03 | 2026-01 | 1 | 9 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 14/0 | 2025-12-28 | 2025-12 | 12 | 2026-01-08 | 2026-01 | 1 | 11 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 12/1 | 2026-01-10 | 2026-01 | 1 | 2026-01-30 | 2026-01 | 1 | 20 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 13/2 | 2026-01-10 | 2026-01 | 1 | 2026-01-24 | 2026-01 | 1 | 14 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 13/1 | 2026-01-14 | 2026-01 | 1 | 2026-01-28 | 2026-01 | 1 | 14 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 8/0 | 2026-01-21 | 2026-01 | 1 | 2026-02-01 | 2026-02 | 2 | 11 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 9/0 | 2026-01-21 | 2026-01 | 1 | 2026-02-04 | 2026-02 | 2 | 14 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 7/0 | 2026-01-25 | 2026-01 | 1 | 2026-02-06 | 2026-02 | 2 | 12 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 6/2 | 2026-01-27 | 2026-01 | 1 | 2026-03-16 | 2026-03 | 3 | 48 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 6/1 | 2026-01-30 | 2026-01 | 1 | 2026-02-09 | 2026-02 | 2 | 10 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 6/3 | 2026-01-31 | 2026-01 | 1 | 2026-02-14 | 2026-02 | 2 | 14 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 5/0 | 2026-02-05 | 2026-02 | 2 | 2026-03-14 | 2026-03 | 3 | 37 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 15/0 | 2026-02-10 | 2026-02 | 2 | 2026-02-20 | 2026-02 | 2 | 10 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 6/0 | 2026-02-19 | 2026-02 | 2 | 2026-02-17 | 2026-02 | 2 | -2 | Yes | Yes | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 1C/0 | 2026-02-24 | 2026-02 | 2 | 2026-03-20 | 2026-03 | 3 | 24 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/0 | 2026-03-08 | 2026-03 | 3 | 2026-03-16 | 2026-03 | 3 | 8 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 6/4 | 2026-03-14 | 2026-03 | 3 | 2026-03-18 | 2026-03 | 3 | 4 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 4/1 | 2026-03-16 | 2026-03 | 3 | 2026-03-20 | 2026-03 | 3 | 4 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 4/2 | 2026-03-17 | 2026-03 | 3 | 2026-03-22 | 2026-03 | 3 | 5 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 33/0 (New) | 2026-04-09 | 2026-04 | 4 | 2026-05-08 | 2026-05 | 5 | 29 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 3/1 | 2026-04-12 | 2026-04 | 4 | 2026-04-18 | 2026-04 | 4 | 6 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 3/0 | 2026-04-14 | 2026-04 | 4 | 2026-04-24 | 2026-04 | 4 | 10 | Yes | No | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 33/1 (New) | 2026-04-20 | 2026-04 | 4 | 2026-05-10 | 2026-05 | 5 | 20 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 34/0 (New) | 2026-04-30 | 2026-04 | 4 | 2026-05-16 | 2026-05 | 5 | 16 | Yes | No | exact | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 2/0 | 2026-06-19 | 2026-06 | 6 | 2026-06-17 | 2026-06 | 6 | -2 | Yes | Yes | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | SC-2 | 2026-06-19 | 2026-06 | 6 |  |  |  |  | No | No |  | 132kV |  | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 1/0 | 2026-06-23 | 2026-06 | 6 | 2026-06-20 | 2026-06 | 6 | -3 | Yes | Yes | exact | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | SC-1 | 2026-07-24 | 2026-07 | 7 |  |  |  |  | No | No |  | 132kV |  | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 507 | 5xx | Private | tb507 | 83/1 | 2025-01-17 | 2025-01 | 1 | 2025-08-29 | 2025-08 | 8 | 224 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 75/7 | 2025-01-27 | 2025-01 | 1 | 2025-06-29 | 2025-06 | 6 | 153 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 75/6 | 2025-02-02 | 2025-02 | 2 | 2025-07-15 | 2025-07 | 7 | 163 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 75/4 | 2025-02-05 | 2025-02 | 2 | 2025-07-22 | 2025-07 | 7 | 167 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 75/5 | 2025-02-05 | 2025-02 | 2 | 2025-07-19 | 2025-07 | 7 | 164 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 77/1 | 2025-02-06 | 2025-02 | 2 | 2025-07-11 | 2025-07 | 7 | 155 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 77/2 | 2025-02-09 | 2025-02 | 2 | 2025-06-23 | 2025-06 | 6 | 134 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 75/3 | 2025-02-10 | 2025-02 | 2 | 2025-07-25 | 2025-07 | 7 | 165 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 77/3 | 2025-02-14 | 2025-02 | 2 | 2025-07-07 | 2025-07 | 7 | 143 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 75/1 | 2025-02-17 | 2025-02 | 2 | 2025-08-01 | 2025-08 | 8 | 165 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 77/4 | 2025-02-17 | 2025-02 | 2 | 2025-06-28 | 2025-06 | 6 | 131 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 75/2 | 2025-02-18 | 2025-02 | 2 | 2025-07-29 | 2025-07 | 7 | 161 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 77/5 | 2025-02-19 | 2025-02 | 2 | 2025-07-03 | 2025-07 | 7 | 134 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 73/3 | 2025-02-22 | 2025-02 | 2 | 2025-08-01 | 2025-08 | 8 | 160 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 86/2 | 2025-02-22 | 2025-02 | 2 | 2026-05-21 | 2026-05 | 5 | 453 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 79/1 | 2025-02-23 | 2025-02 | 2 | 2025-11-25 | 2025-11 | 11 | 275 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 73/2 | 2025-02-25 | 2025-02 | 2 | 2025-08-08 | 2025-08 | 8 | 164 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 95A/1 | 2025-02-25 | 2025-02 | 2 | 2025-08-23 | 2025-08 | 8 | 179 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 80/1 | 2025-02-27 | 2025-02 | 2 | 2025-08-23 | 2025-08 | 8 | 177 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 66/1 | 2025-02-28 | 2025-02 | 2 | 2026-03-22 | 2026-03 | 3 | 387 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 74/1 | 2025-02-28 | 2025-02 | 2 | 2025-07-24 | 2025-07 | 7 | 146 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 96/1 | 2025-02-28 | 2025-02 | 2 | 2025-09-01 | 2025-09 | 9 | 185 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 76/1 | 2025-03-02 | 2025-03 | 3 | 2025-09-19 | 2025-09 | 9 | 201 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 66/2 | 2025-03-06 | 2025-03 | 3 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 64/3 | 2025-03-07 | 2025-03 | 3 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 96/2 | 2025-03-07 | 2025-03 | 3 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 81/2 | 2025-03-08 | 2025-03 | 3 | 2025-09-01 | 2025-09 | 9 | 177 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 86/1 | 2025-03-09 | 2025-03 | 3 | 2025-08-23 | 2025-08 | 8 | 167 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 64/4 | 2025-03-10 | 2025-03 | 3 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 85/1 | 2025-03-10 | 2025-03 | 3 | 2025-08-17 | 2025-08 | 8 | 160 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 99/1 | 2025-03-10 | 2025-03 | 3 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 66/3 | 2025-03-11 | 2025-03 | 3 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 87/1 | 2025-03-24 | 2025-03 | 3 | 2026-06-27 | 2026-06 | 6 | 460 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 64/7 | 2025-03-26 | 2025-03 | 3 | 2026-03-17 | 2026-03 | 3 | 356 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 64/6 | 2025-03-30 | 2025-03 | 3 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 87/2 | 2025-03-30 | 2025-03 | 3 | 2026-06-15 | 2026-06 | 6 | 442 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 98A/1 | 2025-03-30 | 2025-03 | 3 | 2025-09-23 | 2025-09 | 9 | 177 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 64/5 | 2025-03-31 | 2025-03 | 3 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 98/1 | 2025-04-04 | 2025-04 | 4 | 2025-09-15 | 2025-09 | 9 | 164 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 71/1 | 2025-04-09 | 2025-04 | 4 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 91/1 | 2025-04-13 | 2025-04 | 4 | 2026-02-25 | 2026-02 | 2 | 318 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 91/2 | 2025-04-16 | 2025-04 | 4 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 51/2 | 2025-04-17 | 2025-04 | 4 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 119/1 | 2025-04-18 | 2025-04 | 4 | 2025-12-18 | 2025-12 | 12 | 244 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 95/2 | 2025-04-20 | 2025-04 | 4 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 119/2 | 2025-04-22 | 2025-04 | 4 | 2025-12-13 | 2025-12 | 12 | 235 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 51/3 | 2025-04-23 | 2025-04 | 4 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 99/2 | 2025-04-25 | 2025-04 | 4 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 104B/1 | 2025-04-29 | 2025-04 | 4 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 62/4 | 2025-04-29 | 2025-04 | 4 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 81/4 | 2025-04-29 | 2025-04 | 4 | 2025-09-05 | 2025-09 | 9 | 129 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 104B/2 | 2025-05-05 | 2025-05 | 5 | 2025-10-18 | 2025-10 | 10 | 166 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 105/1 | 2025-05-15 | 2025-05 | 5 | 2026-04-30 | 2026-04 | 4 | 350 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 100/1 | 2025-05-18 | 2025-05 | 5 | 2026-06-02 | 2026-06 | 6 | 380 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 81/5 | 2025-05-21 | 2025-05 | 5 | 2025-12-17 | 2025-12 | 12 | 210 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 97/0 | 2025-05-23 | 2025-05 | 5 | 2025-09-01 | 2025-09 | 9 | 101 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 99C/2 | 2025-05-25 | 2025-05 | 5 | 2026-06-17 | 2026-06 | 6 | 388 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 105/0 | 2025-05-28 | 2025-05 | 5 | 2026-08-04 | 2026-08 | 8 | 433 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 98A/0 | 2025-05-29 | 2025-05 | 5 | 2025-09-26 | 2025-09 | 9 | 120 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 62/5 | 2025-05-31 | 2025-05 | 5 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 81/3 | 2025-06-04 | 2025-06 | 6 | 2025-08-29 | 2025-08 | 8 | 86 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 120/1 | 2025-06-05 | 2025-06 | 6 | 2025-12-21 | 2025-12 | 12 | 199 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 96/0 | 2025-06-06 | 2025-06 | 6 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 75/0 | 2025-06-07 | 2025-06 | 6 | 2025-08-04 | 2025-08 | 8 | 58 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/2 | 2025-06-08 | 2025-06 | 6 | 2025-10-15 | 2025-10 | 10 | 129 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 82/2 | 2025-06-10 | 2025-06 | 6 | 2025-10-19 | 2025-10 | 10 | 131 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/5 | 2025-06-12 | 2025-06 | 6 | 2025-10-27 | 2025-10 | 10 | 137 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 79/0 | 2025-06-12 | 2025-06 | 6 | 2025-08-17 | 2025-08 | 8 | 66 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 119/0 | 2025-06-15 | 2025-06 | 6 | 2026-07-28 | 2026-07 | 7 | 408 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/0 | 2025-06-15 | 2025-06 | 6 | 2025-10-10 | 2025-10 | 10 | 117 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 82/1 | 2025-06-15 | 2025-06 | 6 | 2025-09-09 | 2025-09 | 9 | 86 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/4 | 2025-06-16 | 2025-06 | 6 | 2025-10-28 | 2025-10 | 10 | 134 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 78/0 | 2025-06-16 | 2025-06 | 6 | 2025-08-10 | 2025-08 | 8 | 55 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 74/0 | 2025-06-20 | 2025-06 | 6 | 2026-07-27 | 2026-07 | 7 | 402 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/1 | 2025-06-21 | 2025-06 | 6 | 2025-10-19 | 2025-10 | 10 | 120 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/7 | 2025-06-22 | 2025-06 | 6 | 2025-09-30 | 2025-09 | 9 | 100 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 95A/0 | 2025-06-23 | 2025-06 | 6 | 2026-01-07 | 2026-01 | 1 | 198 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 146/2 | 2025-06-25 | 2025-06 | 6 | 2025-10-03 | 2025-10 | 10 | 100 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/3 | 2025-06-25 | 2025-06 | 6 | 2025-10-12 | 2025-10 | 10 | 109 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 73/0 | 2025-06-26 | 2025-06 | 6 | 2025-12-19 | 2025-12 | 12 | 176 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 86/0 | 2025-06-27 | 2025-06 | 6 | 2025-12-28 | 2025-12 | 12 | 184 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 114/0 | 2025-06-30 | 2025-06 | 6 | 2026-01-20 | 2026-01 | 1 | 204 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 146/1 | 2025-06-30 | 2025-06 | 6 | 2025-09-30 | 2025-09 | 9 | 92 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/8 | 2025-06-30 | 2025-06 | 6 | 2025-10-19 | 2025-10 | 10 | 111 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 72/2 | 2025-06-30 | 2025-06 | 6 | 2025-12-06 | 2025-12 | 12 | 159 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 95/1 | 2025-07-04 | 2025-07 | 7 | 2025-12-27 | 2025-12 | 12 | 176 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 148/3 | 2025-07-05 | 2025-07 | 7 | 2025-08-29 | 2025-08 | 8 | 55 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 106/0 | 2025-07-06 | 2025-07 | 7 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 146/0 | 2025-07-08 | 2025-07 | 7 | 2025-10-05 | 2025-10 | 10 | 89 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 148/1 | 2025-07-08 | 2025-07 | 7 | 2025-10-23 | 2025-10 | 10 | 107 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 114/1 | 2025-07-10 | 2025-07 | 7 | 2025-09-24 | 2025-09 | 9 | 76 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 148/2 | 2025-07-10 | 2025-07 | 7 | 2025-09-05 | 2025-09 | 9 | 57 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 80/0 | 2025-07-10 | 2025-07 | 7 | 2025-11-10 | 2025-11 | 11 | 123 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 141/1 | 2025-07-11 | 2025-07 | 7 | 2025-09-27 | 2025-09 | 9 | 78 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 95/0 | 2025-07-11 | 2025-07 | 7 | 2025-11-29 | 2025-11 | 11 | 141 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 148/4 | 2025-07-12 | 2025-07 | 7 | 2025-08-27 | 2025-08 | 8 | 46 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 141/2 | 2025-07-13 | 2025-07 | 7 | 2025-09-24 | 2025-09 | 9 | 73 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 145/4 | 2025-07-13 | 2025-07 | 7 | 2025-09-20 | 2025-09 | 9 | 69 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 125/1 | 2025-07-14 | 2025-07 | 7 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 133/6 | 2025-07-14 | 2025-07 | 7 | 2025-09-23 | 2025-09 | 9 | 71 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 148/5 | 2025-07-15 | 2025-07 | 7 | 2025-09-11 | 2025-09 | 9 | 58 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 109A/0 | 2025-07-16 | 2025-07 | 7 | 2025-11-13 | 2025-11 | 11 | 120 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 113A/0 | 2025-07-16 | 2025-07 | 7 | 2025-09-14 | 2025-09 | 9 | 60 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 133/5 | 2025-07-16 | 2025-07 | 7 | 2025-11-15 | 2025-11 | 11 | 122 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 145/2 | 2025-07-16 | 2025-07 | 7 | 2025-09-09 | 2025-09 | 9 | 55 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 142/0 | 2025-07-17 | 2025-07 | 7 | 2025-10-01 | 2025-10 | 10 | 76 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 115/0 | 2025-07-18 | 2025-07 | 7 | 2025-10-08 | 2025-10 | 10 | 82 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 148/6 | 2025-07-18 | 2025-07 | 7 | 2025-09-14 | 2025-09 | 9 | 58 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 77/0 | 2025-07-19 | 2025-07 | 7 | 2025-11-01 | 2025-11 | 11 | 105 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 133/4 | 2025-07-21 | 2025-07 | 7 | 2025-10-11 | 2025-10 | 10 | 82 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 143/0 | 2025-07-21 | 2025-07 | 7 | 2025-09-27 | 2025-09 | 9 | 68 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 145/1 | 2025-07-21 | 2025-07 | 7 | 2025-08-27 | 2025-08 | 8 | 37 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 148/7 | 2025-07-23 | 2025-07 | 7 | 2025-09-20 | 2025-09 | 9 | 59 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 125/0 | 2025-07-24 | 2025-07 | 7 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 133/3 | 2025-07-24 | 2025-07 | 7 | 2025-09-17 | 2025-09 | 9 | 55 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 94/0 | 2025-07-24 | 2025-07 | 7 | 2026-08-08 | 2026-08 | 8 | 380 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 145/3 | 2025-07-25 | 2025-07 | 7 | 2025-09-14 | 2025-09 | 9 | 51 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 126/2 | 2025-07-26 | 2025-07 | 7 | 2025-12-06 | 2025-12 | 12 | 133 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 143/3 | 2025-07-26 | 2025-07 | 7 | 2025-09-21 | 2025-09 | 9 | 57 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 133/8 | 2025-07-27 | 2025-07 | 7 | 2025-10-05 | 2025-10 | 10 | 70 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 149B/1 | 2025-07-27 | 2025-07 | 7 | 2025-09-24 | 2025-09 | 9 | 59 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 79/2 | 2025-07-27 | 2025-07 | 7 | 2025-09-11 | 2025-09 | 9 | 46 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 110/0 | 2025-07-28 | 2025-07 | 7 | 2025-10-13 | 2025-10 | 10 | 77 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 143/1 | 2025-07-29 | 2025-07 | 7 | 2025-09-22 | 2025-09 | 9 | 55 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 99/3 | 2025-07-29 | 2025-07 | 7 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 133/1 | 2025-07-30 | 2025-07 | 7 | 2025-10-15 | 2025-10 | 10 | 77 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 149B/2 | 2025-07-30 | 2025-07 | 7 | 2025-09-27 | 2025-09 | 9 | 59 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 111/0 | 2025-07-31 | 2025-07 | 7 | 2025-11-03 | 2025-11 | 11 | 95 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 116/0 | 2025-07-31 | 2025-07 | 7 | 2025-09-30 | 2025-09 | 9 | 61 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 129/1 | 2025-07-31 | 2025-07 | 7 | 2025-11-01 | 2025-11 | 11 | 93 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 133/7 | 2025-07-31 | 2025-07 | 7 | 2025-09-29 | 2025-09 | 9 | 60 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 143/6 | 2025-07-31 | 2025-07 | 7 | 2025-09-18 | 2025-09 | 9 | 49 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 145/0 | 2025-07-31 | 2025-07 | 7 | 2025-11-12 | 2025-11 | 11 | 104 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 76/0 | 2025-07-31 | 2025-07 | 7 | 2025-10-24 | 2025-10 | 10 | 85 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 98B/0 | 2025-07-31 | 2025-07 | 7 | 2025-11-22 | 2025-11 | 11 | 114 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 126/1 | 2025-08-02 | 2025-08 | 8 | 2025-12-12 | 2025-12 | 12 | 132 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 143/7 | 2025-08-02 | 2025-08 | 8 | 2025-09-21 | 2025-09 | 9 | 50 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 130/0 | 2025-08-04 | 2025-08 | 8 | 2025-11-28 | 2025-11 | 11 | 116 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 143/5 | 2025-08-04 | 2025-08 | 8 | 2025-09-11 | 2025-09 | 9 | 38 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 97/1 | 2025-08-05 | 2025-08 | 8 | 2025-09-11 | 2025-09 | 9 | 37 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 143/2 | 2025-08-06 | 2025-08 | 8 | 2025-09-18 | 2025-09 | 9 | 43 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 102/2 | 2025-08-07 | 2025-08 | 8 | 2026-01-17 | 2026-01 | 1 | 163 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 133/2 | 2025-08-07 | 2025-08 | 8 | 2025-08-28 | 2025-08 | 8 | 21 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 144/0 | 2025-08-07 | 2025-08 | 8 | 2025-10-01 | 2025-10 | 10 | 55 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 98/0 | 2025-08-07 | 2025-08 | 8 | 2025-11-06 | 2025-11 | 11 | 91 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 112/0 | 2025-08-08 | 2025-08 | 8 | 2025-10-19 | 2025-10 | 10 | 72 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 129/0 | 2025-08-08 | 2025-08 | 8 | 2025-11-09 | 2025-11 | 11 | 93 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 143/4 | 2025-08-09 | 2025-08 | 8 | 2025-09-11 | 2025-09 | 9 | 33 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 83/0 | 2025-08-09 | 2025-08 | 8 | 2026-01-02 | 2026-01 | 1 | 146 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 131/1 | 2025-08-12 | 2025-08 | 8 | 2025-11-06 | 2025-11 | 11 | 86 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 149B/0 | 2025-08-12 | 2025-08 | 8 | 2025-11-23 | 2025-11 | 11 | 103 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 102/1 | 2025-08-14 | 2025-08 | 8 | 2026-05-10 | 2026-05 | 5 | 269 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 140/3 | 2025-08-14 | 2025-08 | 8 | 2025-10-10 | 2025-10 | 10 | 57 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 99/0 | 2025-08-14 | 2025-08 | 8 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 115/1 | 2025-08-16 | 2025-08 | 8 | 2025-10-27 | 2025-10 | 10 | 72 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 134A/4 | 2025-08-16 | 2025-08 | 8 | 2025-11-04 | 2025-11 | 11 | 80 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 140/2 | 2025-08-17 | 2025-08 | 8 | 2025-10-08 | 2025-10 | 10 | 52 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 126/0 | 2025-08-19 | 2025-08 | 8 | 2026-01-05 | 2026-01 | 1 | 139 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 135/0 | 2025-08-19 | 2025-08 | 8 | 2025-10-29 | 2025-10 | 10 | 71 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 149A/0 | 2025-08-19 | 2025-08 | 8 | 2025-10-10 | 2025-10 | 10 | 52 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 128/0 | 2025-08-20 | 2025-08 | 8 | 2025-11-21 | 2025-11 | 11 | 93 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 131/2 | 2025-08-20 | 2025-08 | 8 | 2025-11-11 | 2025-11 | 11 | 83 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 141/0 | 2025-08-20 | 2025-08 | 8 | 2025-10-11 | 2025-10 | 10 | 52 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 87/0 | 2025-08-22 | 2025-08 | 8 | 2026-07-20 | 2026-07 | 7 | 332 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 99/4 | 2025-08-22 | 2025-08 | 8 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 129/2 | 2025-08-23 | 2025-08 | 8 | 2026-01-07 | 2026-01 | 1 | 137 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 135/1 | 2025-08-23 | 2025-08 | 8 | 2025-10-19 | 2025-10 | 10 | 57 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 138/1 | 2025-08-23 | 2025-08 | 8 | 2025-10-08 | 2025-10 | 10 | 46 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 137/0 | 2025-08-24 | 2025-08 | 8 | 2025-11-06 | 2025-11 | 11 | 74 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 63/1 | 2025-08-24 | 2025-08 | 8 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 132/1 | 2025-08-25 | 2025-08 | 8 | 2025-11-05 | 2025-11 | 11 | 72 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 138/2 | 2025-08-25 | 2025-08 | 8 | 2025-10-13 | 2025-10 | 10 | 49 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 134A/2 | 2025-08-26 | 2025-08 | 8 | 2025-10-24 | 2025-10 | 10 | 59 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 56/4 | 2025-08-26 | 2025-08 | 8 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 56/2 | 2025-08-27 | 2025-08 | 8 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 138/0 | 2025-08-28 | 2025-08 | 8 | 2025-10-19 | 2025-10 | 10 | 52 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 149/0 | 2025-08-28 | 2025-08 | 8 | 2025-10-03 | 2025-10 | 10 | 36 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 134/0 | 2025-08-29 | 2025-08 | 8 | 2025-10-27 | 2025-10 | 10 | 59 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 134A/1 | 2025-08-29 | 2025-08 | 8 | 2025-10-29 | 2025-10 | 10 | 61 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 116/1 | 2025-08-31 | 2025-08 | 8 | 2025-09-27 | 2025-09 | 9 | 27 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 132/3 | 2025-08-31 | 2025-08 | 8 | 2025-11-01 | 2025-11 | 11 | 62 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 134A/0 | 2025-08-31 | 2025-08 | 8 | 2025-10-16 | 2025-10 | 10 | 46 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 138/3 | 2025-08-31 | 2025-08 | 8 | 2025-10-16 | 2025-10 | 10 | 46 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 56/5 | 2025-08-31 | 2025-08 | 8 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 82/0 | 2025-08-31 | 2025-08 | 8 | 2025-11-15 | 2025-11 | 11 | 76 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 85/0 | 2025-08-31 | 2025-08 | 8 | 2025-12-12 | 2025-12 | 12 | 103 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 99A/0 | 2025-08-31 | 2025-08 | 8 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 131/0 | 2025-09-04 | 2025-09 | 9 | 2026-01-31 | 2026-01 | 1 | 149 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 139/0 | 2025-09-05 | 2025-09 | 9 | 2025-10-26 | 2025-10 | 10 | 51 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/6 | 2025-09-05 | 2025-09 | 9 | 2025-10-23 | 2025-10 | 10 | 48 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 125/3 | 2025-09-10 | 2025-09 | 9 | 2025-12-31 | 2025-12 | 12 | 112 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 57/0 | 2025-09-10 | 2025-09 | 9 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 59/0 | 2025-09-12 | 2025-09 | 9 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 81/0 | 2025-09-12 | 2025-09 | 9 | 2025-12-06 | 2025-12 | 12 | 85 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/9 | 2025-09-14 | 2025-09 | 9 | 2025-10-16 | 2025-10 | 10 | 32 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 64/0 | 2025-09-14 | 2025-09 | 9 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 58/0 | 2025-09-17 | 2025-09 | 9 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 125/2 | 2025-09-18 | 2025-09 | 9 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 72/1 | 2025-09-19 | 2025-09 | 9 | 2026-08-09 | 2026-08 | 8 | 324 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 56/1 | 2025-09-20 | 2025-09 | 9 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 136/0 | 2025-09-21 | 2025-09 | 9 | 2025-11-03 | 2025-11 | 11 | 43 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 132/4 | 2025-09-25 | 2025-09 | 9 | 2025-11-08 | 2025-11 | 11 | 44 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 48/0 | 2025-09-25 | 2025-09 | 9 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 123/0 | 2025-09-30 | 2025-09 | 9 | 2025-12-28 | 2025-12 | 12 | 89 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 133/0 | 2025-09-30 | 2025-09 | 9 | 2025-10-24 | 2025-10 | 10 | 24 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 152/0 | 2025-09-30 | 2025-09 | 9 | 2025-11-01 | 2025-11 | 11 | 32 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 153A/0 | 2025-09-30 | 2025-09 | 9 | 2025-10-27 | 2025-10 | 10 | 27 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 135/2 | 2025-10-11 | 2025-10 | 10 | 2025-11-25 | 2025-11 | 11 | 45 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 149B/3 | 2025-10-13 | 2025-10 | 10 | 2025-11-14 | 2025-11 | 11 | 32 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 135/3 | 2025-10-16 | 2025-10 | 10 | 2025-11-28 | 2025-11 | 11 | 43 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 73/1 | 2025-10-16 | 2025-10 | 10 | 2026-05-03 | 2026-05 | 5 | 199 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 84/0 | 2025-10-19 | 2025-10 | 10 | 2025-12-17 | 2025-12 | 12 | 59 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 150/0 | 2025-10-29 | 2025-10 | 10 | 2025-11-28 | 2025-11 | 11 | 30 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 71/2 | 2025-10-30 | 2025-10 | 10 | 2025-01-14 | 2025-01 | 1 | -289 | Yes | Yes | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 134A/3 | 2025-10-31 | 2025-10 | 10 | 2025-11-21 | 2025-11 | 11 | 21 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 148/0 | 2025-11-04 | 2025-11 | 11 | 2025-11-16 | 2025-11 | 11 | 12 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 71/3 | 2025-11-07 | 2025-11 | 11 | 2026-01-08 | 2026-01 | 1 | 62 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 151/0 | 2025-11-08 | 2025-11 | 11 | 2025-12-07 | 2025-12 | 12 | 29 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 78/1 | 2025-11-08 | 2025-11 | 11 | 2025-11-21 | 2025-11 | 11 | 13 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 81/1 | 2025-11-10 | 2025-11 | 11 | 2025-12-01 | 2025-12 | 12 | 21 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 140/1 | 2025-11-11 | 2025-11 | 11 | 2025-12-01 | 2025-12 | 12 | 20 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 89/0 | 2025-11-12 | 2025-11 | 11 | 2026-07-16 | 2026-07 | 7 | 246 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 71/0 | 2025-11-14 | 2025-11 | 11 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 113/0 | 2025-11-16 | 2025-11 | 11 | 2026-01-12 | 2026-01 | 1 | 57 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 139/1 | 2025-11-16 | 2025-11 | 11 | 2025-12-06 | 2025-12 | 12 | 20 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 72/0 | 2025-11-17 | 2025-11 | 11 | 2026-05-09 | 2026-05 | 5 | 173 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 89/1 | 2025-11-18 | 2025-11 | 11 | 2025-12-31 | 2025-12 | 12 | 43 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 140/0 | 2025-11-22 | 2025-11 | 11 | 2025-12-09 | 2025-12 | 12 | 17 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 154/0 | 2025-11-22 | 2025-11 | 11 | 2025-12-14 | 2025-12 | 12 | 22 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 90/0 | 2025-11-22 | 2025-11 | 11 | 2026-02-20 | 2026-02 | 2 | 90 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 90/1 | 2025-11-26 | 2025-11 | 11 | 2025-12-12 | 2025-12 | 12 | 16 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 127/1 | 2025-11-28 | 2025-11 | 11 | 2026-01-13 | 2026-01 | 1 | 46 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 153/0 | 2025-11-30 | 2025-11 | 11 | 2025-12-21 | 2025-12 | 12 | 21 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 66/0 | 2025-11-30 | 2025-11 | 11 | 2026-02-19 | 2026-02 | 2 | 81 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 118/0 | 2025-12-05 | 2025-12 | 12 | 2026-01-27 | 2026-01 | 1 | 53 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 88/0 | 2025-12-05 | 2025-12 | 12 | 2026-07-11 | 2026-07 | 7 | 218 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 130/1 | 2025-12-06 | 2025-12 | 12 | 2026-02-08 | 2026-02 | 2 | 64 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 98B/2 | 2025-12-08 | 2025-12 | 12 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 117/0 | 2025-12-13 | 2025-12 | 12 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 128/1 | 2025-12-14 | 2025-12 | 12 | 2026-02-05 | 2026-02 | 2 | 53 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 117/1 | 2025-12-19 | 2025-12 | 12 | 2026-05-11 | 2026-05 | 5 | 143 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 132/2 | 2025-12-20 | 2025-12 | 12 | 2026-02-11 | 2026-02 | 2 | 53 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 91/0 | 2025-12-24 | 2025-12 | 12 | 2026-05-19 | 2026-05 | 5 | 146 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 132/0 | 2025-12-28 | 2025-12 | 12 | 2026-02-12 | 2026-02 | 2 | 46 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 104A/0 | 2025-12-30 | 2025-12 | 12 | 2026-08-09 | 2026-08 | 8 | 222 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 124/0 | 2025-12-30 | 2025-12 | 12 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 91/3 | 2025-12-31 | 2025-12 | 12 | 2026-05-08 | 2026-05 | 5 | 128 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 104B/0 | 2026-01-04 | 2026-01 | 1 | 2026-05-10 | 2026-05 | 5 | 126 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 65/0 | 2026-01-07 | 2026-01 | 1 | 2026-03-10 | 2026-03 | 3 | 62 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 122/2 | 2026-01-08 | 2026-01 | 1 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 126/3 | 2026-01-15 | 2026-01 | 1 | 2026-05-24 | 2026-05 | 5 | 129 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 65/1 | 2026-01-15 | 2026-01 | 1 | 2026-03-01 | 2026-03 | 3 | 45 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 69/3 | 2026-01-15 | 2026-01 | 1 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 108/0 | 2026-01-20 | 2026-01 | 1 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 10/3 | 2026-01-23 | 2026-01 | 1 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 109/0 | 2026-01-23 | 2026-01 | 1 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 120/0 | 2026-01-25 | 2026-01 | 1 | 2026-05-19 | 2026-05 | 5 | 114 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 10/5 | 2026-01-26 | 2026-01 | 1 | 2026-04-10 | 2026-04 | 4 | 74 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 10/6 | 2026-01-28 | 2026-01 | 1 | 2026-04-17 | 2026-04 | 4 | 79 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 92/0 | 2026-01-28 | 2026-01 | 1 | 2026-04-27 | 2026-04 | 4 | 89 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 10/7 | 2026-01-30 | 2026-01 | 1 | 2026-04-20 | 2026-04 | 4 | 80 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 93/0 | 2026-01-30 | 2026-01 | 1 | 2026-05-14 | 2026-05 | 5 | 104 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 7/7 | 2026-02-04 | 2026-02 | 2 | 2026-04-24 | 2026-04 | 4 | 79 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 7/9 | 2026-02-06 | 2026-02 | 2 | 2026-04-16 | 2026-04 | 4 | 69 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 7/0 | 2026-02-11 | 2026-02 | 2 |  |  |  |  | No | No |  | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 10/12 | 2026-02-12 | 2026-02 | 2 | 2026-06-02 | 2026-06 | 6 | 110 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 1/1 | 2026-02-14 | 2026-02 | 2 | 2026-03-27 | 2026-03 | 3 | 41 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 6/2 | 2026-02-16 | 2026-02 | 2 | 2026-06-19 | 2026-06 | 6 | 123 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 1/2 | 2026-02-18 | 2026-02 | 2 | 2026-04-07 | 2026-04 | 4 | 48 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 6/1 | 2026-02-20 | 2026-02 | 2 | 2026-06-21 | 2026-06 | 6 | 121 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 1/0 | 2026-02-28 | 2026-02 | 2 |  |  |  |  | No | No |  | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 117/2 | 2026-02-28 | 2026-02 | 2 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 4/0 | 2026-02-28 | 2026-02 | 2 | 2026-05-25 | 2026-05 | 5 | 86 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 6/0 | 2026-02-28 | 2026-02 | 2 |  |  |  |  | No | No |  | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 157/0 | 2026-03-04 | 2026-03 | 3 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 156/0 | 2026-03-10 | 2026-03 | 3 | 2026-08-08 | 2026-08 | 8 | 151 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 2/1 | 2026-03-11 | 2026-03 | 3 | 2026-04-15 | 2026-04 | 4 | 35 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 98B/1 | 2026-03-11 | 2026-03 | 3 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 2/0 | 2026-03-13 | 2026-03 | 3 |  |  |  |  | No | No |  | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 2/2 | 2026-03-15 | 2026-03 | 3 | 2026-06-11 | 2026-06 | 6 | 88 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 2/3 | 2026-03-16 | 2026-03 | 3 | 2026-07-05 | 2026-07 | 7 | 111 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 2/4 | 2026-03-17 | 2026-03 | 3 | 2026-07-07 | 2026-07 | 7 | 112 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 103/0 | 2026-03-19 | 2026-03 | 3 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 10/8 | 2026-03-22 | 2026-03 | 3 | 2026-04-20 | 2026-04 | 4 | 29 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 8/2 | 2026-03-25 | 2026-03 | 3 | 2026-04-29 | 2026-04 | 4 | 35 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 3/0B | 2026-03-26 | 2026-03 | 3 | 2026-08-05 | 2026-08 | 8 | 132 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 7/1 | 2026-03-26 | 2026-03 | 3 | 2026-05-02 | 2026-05 | 5 | 37 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 2/5 | 2026-03-27 | 2026-03 | 3 | 2026-07-11 | 2026-07 | 7 | 106 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 3/0A | 2026-03-28 | 2026-03 | 3 | 2026-08-05 | 2026-08 | 8 | 130 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 5/2 | 2026-03-31 | 2026-03 | 3 |  |  |  |  | No | No |  | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 5/1 | 2026-04-02 | 2026-04 | 4 |  |  |  |  | No | No |  | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 3/1 | 2026-04-04 | 2026-04 | 4 |  |  |  |  | No | No |  | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 8/1 | 2026-04-06 | 2026-04 | 4 | 2026-04-23 | 2026-04 | 4 | 17 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 3/1 | 2026-04-07 | 2026-04 | 4 | 2026-08-06 | 2026-08 | 8 | 121 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 2/1B | 2026-04-08 | 2026-04 | 4 | 2026-08-04 | 2026-08 | 8 | 118 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 2/1 A | 2026-04-09 | 2026-04 | 4 | 2026-08-02 | 2026-08 | 8 | 115 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 103/1 | 2026-04-10 | 2026-04 | 4 | 2026-06-27 | 2026-06 | 6 | 78 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 8/0 | 2026-04-11 | 2026-04 | 4 | 2026-07-06 | 2026-07 | 7 | 86 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 5/0 | 2026-04-12 | 2026-04 | 4 |  |  |  |  | No | No |  | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 9/3 | 2026-04-14 | 2026-04 | 4 | 2026-05-02 | 2026-05 | 5 | 18 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 9/4 | 2026-04-15 | 2026-04 | 4 | 2026-05-04 | 2026-05 | 5 | 19 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 99C/0 | 2026-04-15 | 2026-04 | 4 | 2026-07-16 | 2026-07 | 7 | 92 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 4/5 | 2026-04-16 | 2026-04 | 4 | 2026-07-15 | 2026-07 | 7 | 90 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 3/3 | 2026-04-18 | 2026-04 | 4 |  |  |  |  | No | No |  | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 3/2 | 2026-04-21 | 2026-04 | 4 | 2026-08-30 | 2026-08 | 8 | 131 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 9/5 | 2026-04-21 | 2026-04 | 4 | 2026-05-07 | 2026-05 | 5 | 16 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 10/14 | 2026-04-23 | 2026-04 | 4 | 2026-05-13 | 2026-05 | 5 | 20 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 100/0 | 2026-04-24 | 2026-04 | 4 | 2026-04-24 | 2026-04 | 4 | 0 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 10/11 | 2026-04-28 | 2026-04 | 4 | 2026-05-27 | 2026-05 | 5 | 29 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 3/4 | 2026-04-29 | 2026-04 | 4 | 2026-07-18 | 2026-07 | 7 | 80 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 10/0 | 2026-05-02 | 2026-05 | 5 | 2026-05-12 | 2026-05 | 5 | 10 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 2/0 | 2026-05-02 | 2026-05 | 5 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 10/2 | 2026-05-03 | 2026-05 | 5 | 2026-05-08 | 2026-05 | 5 | 5 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 155/0 | 2026-05-03 | 2026-05 | 5 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 9/2 | 2026-05-03 | 2026-05 | 5 | 2026-05-07 | 2026-05 | 5 | 4 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 3/5 | 2026-05-05 | 2026-05 | 5 | 2026-07-20 | 2026-07 | 7 | 76 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 154/1B | 2026-05-06 | 2026-05 | 5 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 10/13 | 2026-05-08 | 2026-05 | 5 | 2026-06-07 | 2026-06 | 6 | 30 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 154/2B | 2026-05-08 | 2026-05 | 5 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 4/2 | 2026-05-08 | 2026-05 | 5 | 2026-07-17 | 2026-07 | 7 | 70 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 154/1A | 2026-05-09 | 2026-05 | 5 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 154/2A | 2026-05-09 | 2026-05 | 5 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 4/4 | 2026-05-10 | 2026-05 | 5 | 2026-07-17 | 2026-07 | 7 | 68 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 7/6 | 2026-05-11 | 2026-05 | 5 | 2026-05-16 | 2026-05 | 5 | 5 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 13/2 | 2026-05-14 | 2026-05 | 5 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 4/0 | 2026-05-15 | 2026-05 | 5 |  |  |  |  | No | No |  | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 7/8 | 2026-05-16 | 2026-05 | 5 | 2026-05-16 | 2026-05 | 5 | 0 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 8/3 | 2026-05-17 | 2026-05 | 5 | 2026-05-24 | 2026-05 | 5 | 7 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 4/1 | 2026-05-18 | 2026-05 | 5 | 2026-07-23 | 2026-07 | 7 | 66 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 4/3 | 2026-05-19 | 2026-05 | 5 | 2026-07-26 | 2026-07 | 7 | 68 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 8/4 | 2026-05-19 | 2026-05 | 5 | 2026-05-28 | 2026-05 | 5 | 9 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 1/0 | 2026-05-27 | 2026-05 | 5 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 27/0 | 2026-05-27 | 2026-05 | 5 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 1A/0 | 2026-05-30 | 2026-05 | 5 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 10/10 | 2026-05-31 | 2026-05 | 5 | 2026-06-16 | 2026-06 | 6 | 16 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 3A/1 | 2026-05-31 | 2026-05 | 5 |  |  |  |  | No | No |  | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 7/2 | 2026-06-01 | 2026-06 | 6 | 2026-06-27 | 2026-06 | 6 | 26 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 5/3 | 2026-06-03 | 2026-06 | 6 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 3A/0 | 2026-06-05 | 2026-06 | 6 |  |  |  |  | No | No |  | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 5/4 | 2026-06-05 | 2026-06 | 6 | 2026-08-03 | 2026-08 | 8 | 59 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 9/0 | 2026-06-05 | 2026-06 | 6 | 2026-06-10 | 2026-06 | 6 | 5 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 10/1 | 2026-06-09 | 2026-06 | 6 | 2026-07-06 | 2026-07 | 7 | 27 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 5/5 | 2026-06-09 | 2026-06 | 6 | 2026-07-15 | 2026-07 | 7 | 36 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 10/4 | 2026-06-15 | 2026-06 | 6 | 2026-06-21 | 2026-06 | 6 | 6 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 3B/0 | 2026-06-15 | 2026-06 | 6 |  |  |  |  | No | No |  | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 5/0 | 2026-06-15 | 2026-06 | 6 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 56/3 | 2026-06-17 | 2026-06 | 6 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 7/3 | 2026-06-19 | 2026-06 | 6 | 2026-07-13 | 2026-07 | 7 | 24 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 3/0 | 2026-06-24 | 2026-06 | 6 | 2026-08-01 | 2026-08 | 8 | 38 | Yes | No | fallback_single_line | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 5/2 | 2026-06-24 | 2026-06 | 6 | 2026-08-07 | 2026-08 | 8 | 44 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 10/9 | 2026-06-27 | 2026-06 | 6 | 2025-07-10 | 2025-07 | 7 | -352 | Yes | Yes | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 107/1 | 2026-06-28 | 2026-06 | 6 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 43/0 | 2026-06-28 | 2026-06 | 6 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 5A/0 | 2026-06-29 | 2026-06 | 6 |  |  |  |  | No | No |  | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 121/0 | 2026-06-30 | 2026-06 | 6 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 42/0 | 2026-06-30 | 2026-06 | 6 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 41/3 | 2026-07-04 | 2026-07 | 7 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 6D/5 | 2026-07-06 | 2026-07 | 7 | 2026-07-15 | 2026-07 | 7 | 9 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 9A/0 | 2026-07-10 | 2026-07 | 7 | 2026-07-16 | 2026-07 | 7 | 6 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 42/1 | 2026-07-11 | 2026-07 | 7 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 5/6 | 2026-07-11 | 2026-07 | 7 | 2026-08-11 | 2026-08 | 8 | 31 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 5/1 | 2026-07-13 | 2026-07 | 7 | 2026-08-07 | 2026-08 | 8 | 25 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 7/0 | 2026-07-16 | 2026-07 | 7 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 41/1 | 2026-07-17 | 2026-07 | 7 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 44/0 | 2026-07-18 | 2026-07 | 7 | 2026-08-05 | 2026-08 | 8 | 18 | Yes | No | exact | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 122/1 | 2026-07-20 | 2026-07 | 7 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 122/0 | 2026-07-24 | 2026-07 | 7 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 102/0 | 2026-07-28 | 2026-07 | 7 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 39/4 | 2026-07-28 | 2026-07 | 7 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 2A/0 | 2026-07-30 | 2026-07 | 7 |  |  |  |  | No | No |  | 765kV |  | TB 507 - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 45/3 | 2026-07-31 | 2026-07 | 7 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 5A/0 | 2026-07-31 | 2026-07 | 7 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 5B/0 | 2026-08-03 | 2026-08 | 8 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 39/3 | 2026-08-04 | 2026-08 | 8 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 40/0 | 2026-08-06 | 2026-08 | 8 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 40/1 | 2026-08-12 | 2026-08 | 8 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 5C/0 | 2026-08-12 | 2026-08 | 8 |  |  |  |  | No | No |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-12.xlsx | Foundation
TB 605 | 6xx | Private | tb605 | 29/5 | 2025-08-11 | 2025-08 | 8 | 2025-11-27 | 2025-11 | 11 | 108 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 29/4 | 2025-09-06 | 2025-09 | 9 | 2025-12-05 | 2025-12 | 12 | 90 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 27/0 | 2025-09-20 | 2025-09 | 9 | 2025-12-11 | 2025-12 | 12 | 82 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 29/3 | 2025-09-24 | 2025-09 | 9 | 2026-05-05 | 2026-05 | 5 | 223 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 29/1 | 2025-10-10 | 2025-10 | 10 | 2026-03-09 | 2026-03 | 3 | 150 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 18/0 | 2025-10-16 | 2025-10 | 10 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | 29/6 | 2025-10-16 | 2025-10 | 10 | 2025-12-22 | 2025-12 | 12 | 67 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 117/1 | 2025-10-20 | 2025-10 | 10 | 2026-02-07 | 2026-02 | 2 | 110 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 71/3 | 2025-10-23 | 2025-10 | 10 | 2026-05-05 | 2026-05 | 5 | 194 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 92/3 | 2025-10-27 | 2025-10 | 10 | 2026-02-12 | 2026-02 | 2 | 108 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 22/1 | 2025-10-28 | 2025-10 | 10 | 2026-05-30 | 2026-05 | 5 | 214 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 72/2 | 2025-10-28 | 2025-10 | 10 | 2026-04-25 | 2026-04 | 4 | 179 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 92/2 | 2025-10-28 | 2025-10 | 10 | 2026-02-02 | 2026-02 | 2 | 97 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 117/3 | 2025-10-29 | 2025-10 | 10 | 2026-02-03 | 2026-02 | 2 | 97 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 31/1 | 2025-10-30 | 2025-10 | 10 | 2026-01-25 | 2026-01 | 1 | 87 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 21/1 | 2025-10-31 | 2025-10 | 10 | 2026-06-22 | 2026-06 | 6 | 234 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 22/0 | 2025-10-31 | 2025-10 | 10 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | 89/1 | 2025-10-31 | 2025-10 | 10 | 2026-02-02 | 2026-02 | 2 | 94 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 93/1 | 2025-10-31 | 2025-10 | 10 | 2026-05-08 | 2026-05 | 5 | 189 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 117/2 | 2025-11-04 | 2025-11 | 11 | 2026-02-11 | 2026-02 | 2 | 99 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 93/2 | 2025-11-04 | 2025-11 | 11 | 2026-02-17 | 2026-02 | 2 | 105 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 118/1 | 2025-11-06 | 2025-11 | 11 | 2026-02-21 | 2026-02 | 2 | 107 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 74/0 | 2025-11-06 | 2025-11 | 11 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 95/2 | 2025-11-08 | 2025-11 | 11 | 2026-02-08 | 2026-02 | 2 | 92 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 72/0 | 2025-11-09 | 2025-11 | 11 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 23/1 | 2025-11-10 | 2025-11 | 11 | 2026-02-05 | 2026-02 | 2 | 87 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 92/1 | 2025-11-10 | 2025-11 | 11 | 2026-02-25 | 2026-02 | 2 | 107 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 95/3 | 2025-11-10 | 2025-11 | 11 | 2026-02-06 | 2026-02 | 2 | 88 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 31/3 | 2025-11-11 | 2025-11 | 11 | 2026-02-06 | 2026-02 | 2 | 87 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 97/2 | 2025-11-12 | 2025-11 | 11 | 2026-02-05 | 2026-02 | 2 | 85 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 22/2 | 2025-11-13 | 2025-11 | 11 | 2026-06-01 | 2026-06 | 6 | 200 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 97/1 | 2025-11-13 | 2025-11 | 11 | 2026-02-09 | 2026-02 | 2 | 88 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 76/2 | 2025-11-14 | 2025-11 | 11 | 2026-02-22 | 2026-02 | 2 | 100 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 131/1 | 2025-11-15 | 2025-11 | 11 | 2026-02-27 | 2026-02 | 2 | 104 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 95/1 | 2025-11-15 | 2025-11 | 11 | 2026-03-12 | 2026-03 | 3 | 117 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP118 | 2025-11-16 | 2025-11 | 11 | 2026-04-27 | 2026-04 | 4 | 162 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 15/1 | 2025-11-17 | 2025-11 | 11 | 2025-12-25 | 2025-12 | 12 | 38 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 76/1 | 2025-11-18 | 2025-11 | 11 | 2026-02-17 | 2026-02 | 2 | 91 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 131/3 | 2025-11-19 | 2025-11 | 11 | 2026-02-23 | 2026-02 | 2 | 96 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 15/2 | 2025-11-19 | 2025-11 | 11 | 2026-01-07 | 2026-01 | 1 | 49 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP93 | 2025-11-19 | 2025-11 | 11 | 2026-02-20 | 2026-02 | 2 | 93 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 95/4 | 2025-11-20 | 2025-11 | 11 | 2026-02-11 | 2026-02 | 2 | 83 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 97/3 | 2025-11-20 | 2025-11 | 11 | 2026-02-12 | 2026-02 | 2 | 84 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP90 | 2025-11-22 | 2025-11 | 11 | 2026-05-16 | 2026-05 | 5 | 175 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 17/0 | 2025-11-23 | 2025-11 | 11 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | 27/1 | 2025-11-23 | 2025-11 | 11 | 2026-05-16 | 2026-05 | 5 | 174 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 131/2 | 2025-11-24 | 2025-11 | 11 | 2026-04-30 | 2026-04 | 4 | 157 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 30/3 | 2025-11-24 | 2025-11 | 11 | 2025-12-29 | 2025-12 | 12 | 35 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP98 | 2025-11-24 | 2025-11 | 11 | 2026-02-22 | 2026-02 | 2 | 90 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 98/1 | 2025-11-26 | 2025-11 | 11 | 2026-02-17 | 2026-02 | 2 | 83 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP32 | 2025-11-26 | 2025-11 | 11 | 2026-02-13 | 2026-02 | 2 | 79 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP94 | 2025-11-27 | 2025-11 | 11 | 2026-02-17 | 2026-02 | 2 | 82 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 103/1 | 2025-11-28 | 2025-11 | 11 | 2026-03-02 | 2026-03 | 3 | 94 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 30/5 | 2025-11-29 | 2025-11 | 11 | 2026-01-09 | 2026-01 | 1 | 41 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP96 | 2025-11-29 | 2025-11 | 11 | 2026-02-13 | 2026-02 | 2 | 76 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 131/4 | 2025-11-30 | 2025-11 | 11 | 2026-02-12 | 2026-02 | 2 | 74 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 20/0 | 2025-11-30 | 2025-11 | 11 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | 40/1 | 2025-11-30 | 2025-11 | 11 | 2026-02-16 | 2026-02 | 2 | 78 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP116 | 2025-11-30 | 2025-11 | 11 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP87 | 2025-11-30 | 2025-11 | 11 | 2026-07-05 | 2026-07 | 7 | 217 | Yes | No | fallback_single_line | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP99 | 2025-11-30 | 2025-11 | 11 | 2026-02-26 | 2026-02 | 2 | 88 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP75 | 2025-12-01 | 2025-12 | 12 | 2026-04-21 | 2026-04 | 4 | 141 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 40/0 | 2025-12-03 | 2025-12 | 12 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | 104/1 | 2025-12-04 | 2025-12 | 12 | 2026-03-23 | 2026-03 | 3 | 109 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP28 | 2025-12-04 | 2025-12 | 12 | 2026-05-19 | 2026-05 | 5 | 166 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 82/2 | 2025-12-05 | 2025-12 | 12 | 2026-05-03 | 2026-05 | 5 | 149 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 18/1 | 2025-12-06 | 2025-12 | 12 | 2026-03-05 | 2026-03 | 3 | 89 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 76/3 | 2025-12-06 | 2025-12 | 12 | 2026-03-05 | 2026-03 | 3 | 89 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 99/1 | 2025-12-06 | 2025-12 | 12 | 2026-04-19 | 2026-04 | 4 | 134 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP100 | 2025-12-07 | 2025-12 | 12 | 2026-03-14 | 2026-03 | 3 | 97 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP95 | 2025-12-07 | 2025-12 | 12 | 2026-02-21 | 2026-02 | 2 | 76 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 23/0 | 2025-12-09 | 2025-12 | 12 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP117 | 2025-12-09 | 2025-12 | 12 | 2026-02-24 | 2026-02 | 2 | 77 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 29/0 | 2025-12-10 | 2025-12 | 12 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | 77/2 | 2025-12-10 | 2025-12 | 12 | 2026-03-22 | 2026-03 | 3 | 102 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 82/1 | 2025-12-10 | 2025-12 | 12 | 2026-04-17 | 2026-04 | 4 | 128 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 30/2 | 2025-12-12 | 2025-12 | 12 | 2026-05-15 | 2026-05 | 5 | 154 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 19/2 | 2025-12-13 | 2025-12 | 12 | 2026-02-01 | 2026-02 | 2 | 50 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 39/2 | 2025-12-13 | 2025-12 | 12 | 2026-02-24 | 2026-02 | 2 | 73 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP104 | 2025-12-13 | 2025-12 | 12 | 2026-03-20 | 2026-03 | 3 | 97 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP77 | 2025-12-13 | 2025-12 | 12 | 2026-03-11 | 2026-03 | 3 | 88 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP106 | 2025-12-15 | 2025-12 | 12 | 2026-03-01 | 2026-03 | 3 | 76 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 77/1 | 2025-12-16 | 2025-12 | 12 | 2026-03-17 | 2026-03 | 3 | 91 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 85/1 | 2025-12-16 | 2025-12 | 12 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP135 | 2025-12-16 | 2025-12 | 12 | 2026-04-18 | 2026-04 | 4 | 123 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 106/1 | 2025-12-17 | 2025-12 | 12 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 130/2 | 2025-12-17 | 2025-12 | 12 | 2026-03-08 | 2026-03 | 3 | 81 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 102/1 | 2025-12-18 | 2025-12 | 12 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP103 | 2025-12-18 | 2025-12 | 12 | 2026-03-26 | 2026-03 | 3 | 98 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 136/1 | 2025-12-19 | 2025-12 | 12 | 2026-03-21 | 2026-03 | 3 | 92 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 30/4 | 2025-12-19 | 2025-12 | 12 | 2026-01-18 | 2026-01 | 1 | 30 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 116/1 | 2025-12-20 | 2025-12 | 12 | 2026-03-07 | 2026-03 | 3 | 77 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 130/1 | 2025-12-20 | 2025-12 | 12 | 2026-05-15 | 2026-05 | 5 | 146 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 135/2 | 2025-12-21 | 2025-12 | 12 | 2026-06-12 | 2026-06 | 6 | 173 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 23/5 | 2025-12-21 | 2025-12 | 12 | 2026-02-15 | 2026-02 | 2 | 56 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP45 | 2025-12-23 | 2025-12 | 12 | 2026-05-15 | 2026-05 | 5 | 143 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 131/6 | 2025-12-24 | 2025-12 | 12 | 2026-03-13 | 2026-03 | 3 | 79 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 139/1 | 2025-12-24 | 2025-12 | 12 | 2026-06-21 | 2026-06 | 6 | 179 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP19 | 2025-12-24 | 2025-12 | 12 | 2026-02-13 | 2026-02 | 2 | 51 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP85 | 2025-12-24 | 2025-12 | 12 | 2026-04-04 | 2026-04 | 4 | 101 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 46/1 | 2025-12-25 | 2025-12 | 12 | 2026-03-23 | 2026-03 | 3 | 88 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP43 | 2025-12-25 | 2025-12 | 12 | 2026-04-21 | 2026-04 | 4 | 117 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP80 | 2025-12-25 | 2025-12 | 12 | 2026-03-28 | 2026-03 | 3 | 93 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 138/1 | 2025-12-26 | 2025-12 | 12 | 2026-06-25 | 2026-06 | 6 | 181 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 156/4 | 2025-12-26 | 2025-12 | 12 | 2026-03-07 | 2026-03 | 3 | 71 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 131/5 | 2025-12-27 | 2025-12 | 12 | 2026-02-17 | 2026-02 | 2 | 52 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 150/1 | 2025-12-27 | 2025-12 | 12 | 2026-04-22 | 2026-04 | 4 | 116 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 31/2 | 2025-12-27 | 2025-12 | 12 | 2026-02-01 | 2026-02 | 2 | 36 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 137/1 | 2025-12-28 | 2025-12 | 12 | 2026-05-05 | 2026-05 | 5 | 128 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 135/1 | 2025-12-29 | 2025-12 | 12 | 2026-04-04 | 2026-04 | 4 | 96 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP102 | 2025-12-29 | 2025-12 | 12 | 2026-03-11 | 2026-03 | 3 | 72 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 156/3 | 2025-12-30 | 2025-12 | 12 | 2026-04-10 | 2026-04 | 4 | 101 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 80/1 | 2025-12-30 | 2025-12 | 12 | 2026-06-15 | 2026-06 | 6 | 167 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 86/1 | 2025-12-30 | 2025-12 | 12 | 2026-05-14 | 2026-05 | 5 | 135 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 132/1 | 2025-12-31 | 2025-12 | 12 | 2026-03-02 | 2026-03 | 3 | 61 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 138/2 | 2025-12-31 | 2025-12 | 12 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 23/4 | 2025-12-31 | 2025-12 | 12 | 2026-02-20 | 2026-02 | 2 | 51 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP33 | 2025-12-31 | 2025-12 | 12 | 2026-03-12 | 2026-03 | 3 | 71 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 150/2 | 2026-01-04 | 2026-01 | 1 | 2026-04-12 | 2026-04 | 4 | 98 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 43/1 | 2026-01-04 | 2026-01 | 1 | 2026-04-06 | 2026-04 | 4 | 92 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP146 | 2026-01-05 | 2026-01 | 1 | 2026-04-04 | 2026-04 | 4 | 89 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 69/3 | 2026-01-07 | 2026-01 | 1 | 2026-03-17 | 2026-03 | 3 | 69 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 156/2 | 2026-01-08 | 2026-01 | 1 | 2026-04-04 | 2026-04 | 4 | 86 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 18/2 | 2026-01-08 | 2026-01 | 1 | 2026-02-24 | 2026-02 | 2 | 47 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP26 | 2026-01-08 | 2026-01 | 1 | 2026-02-22 | 2026-02 | 2 | 45 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 155/1 | 2026-01-09 | 2026-01 | 1 | 2026-04-14 | 2026-04 | 4 | 95 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 31/4 | 2026-01-09 | 2026-01 | 1 | 2026-02-09 | 2026-02 | 2 | 31 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 46/3 | 2026-01-09 | 2026-01 | 1 | 2026-04-18 | 2026-04 | 4 | 99 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 137/2 | 2026-01-10 | 2026-01 | 1 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 152/1 | 2026-01-11 | 2026-01 | 1 | 2026-04-16 | 2026-04 | 4 | 95 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 90/1 | 2026-01-11 | 2026-01 | 1 | 2026-05-10 | 2026-05 | 5 | 119 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP131 | 2026-01-11 | 2026-01 | 1 | 2026-06-02 | 2026-06 | 6 | 142 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 43/2 | 2026-01-12 | 2026-01 | 1 | 2026-04-02 | 2026-04 | 4 | 80 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 87/2 | 2026-01-12 | 2026-01 | 1 | 2026-02-25 | 2026-02 | 2 | 44 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 152/2 | 2026-01-16 | 2026-01 | 1 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 90/2 | 2026-01-16 | 2026-01 | 1 | 2026-03-09 | 2026-03 | 3 | 52 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP147 | 2026-01-16 | 2026-01 | 1 | 2026-04-26 | 2026-04 | 4 | 100 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP157 | 2026-01-17 | 2026-01 | 1 | 2026-03-13 | 2026-03 | 3 | 55 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP154 | 2026-01-18 | 2026-01 | 1 | 2026-06-16 | 2026-06 | 6 | 149 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP31 | 2026-01-18 | 2026-01 | 1 | 2026-03-29 | 2026-03 | 3 | 70 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 145/2 | 2026-01-20 | 2026-01 | 1 | 2026-04-19 | 2026-04 | 4 | 89 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 19/1 | 2026-01-20 | 2026-01 | 1 | 2026-02-08 | 2026-02 | 2 | 19 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP129 | 2026-01-20 | 2026-01 | 1 | 2026-05-05 | 2026-05 | 5 | 105 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP138 | 2026-01-20 | 2026-01 | 1 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 25/2 | 2026-01-21 | 2026-01 | 1 | 2026-03-05 | 2026-03 | 3 | 43 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 44/3 | 2026-01-21 | 2026-01 | 1 | 2026-03-08 | 2026-03 | 3 | 46 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 45/2 | 2026-01-21 | 2026-01 | 1 | 2026-02-17 | 2026-02 | 2 | 27 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 71/2 | 2026-01-21 | 2026-01 | 1 | 2026-02-27 | 2026-02 | 2 | 37 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 156/1 | 2026-01-22 | 2026-01 | 1 | 2026-04-27 | 2026-04 | 4 | 95 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 31/5 | 2026-01-22 | 2026-01 | 1 | 2026-03-07 | 2026-03 | 3 | 44 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 69/2 | 2026-01-22 | 2026-01 | 1 | 2026-03-21 | 2026-03 | 3 | 58 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP115 | 2026-01-22 | 2026-01 | 1 | 2026-02-16 | 2026-02 | 2 | 25 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP16 | 2026-01-25 | 2026-01 | 1 | 2026-04-15 | 2026-04 | 4 | 80 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 69/1 | 2026-01-27 | 2026-01 | 1 | 2026-03-29 | 2026-03 | 3 | 61 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 155/2 | 2026-01-30 | 2026-01 | 1 | 2026-04-18 | 2026-04 | 4 | 78 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 32/1 | 2026-01-30 | 2026-01 | 1 | 2026-02-20 | 2026-02 | 2 | 21 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 115/1 | 2026-01-31 | 2026-01 | 1 | 2026-03-26 | 2026-03 | 3 | 54 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 151/1 | 2026-01-31 | 2026-01 | 1 | 2026-04-10 | 2026-04 | 4 | 69 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 155/3 | 2026-01-31 | 2026-01 | 1 | 2026-04-22 | 2026-04 | 4 | 81 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP30 | 2026-01-31 | 2026-01 | 1 | 2026-04-04 | 2026-04 | 4 | 63 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 153/0 | 2026-02-05 | 2026-02 | 2 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 45/1 | 2026-02-05 | 2026-02 | 2 | 2026-03-16 | 2026-03 | 3 | 39 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP139 | 2026-02-06 | 2026-02 | 2 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 151/2 | 2026-02-07 | 2026-02 | 2 | 2026-05-07 | 2026-05 | 5 | 89 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 44/2 | 2026-02-07 | 2026-02 | 2 | 2026-03-12 | 2026-03 | 3 | 33 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP15 | 2026-02-08 | 2026-02 | 2 | 2026-06-26 | 2026-06 | 6 | 138 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP97 | 2026-02-08 | 2026-02 | 2 | 2026-03-01 | 2026-03 | 3 | 21 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP155 | 2026-02-09 | 2026-02 | 2 | 2026-05-24 | 2026-05 | 5 | 104 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 136/2 | 2026-02-11 | 2026-02 | 2 | 2026-04-13 | 2026-04 | 4 | 61 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 152/4 | 2026-02-12 | 2026-02 | 2 | 2026-05-14 | 2026-05 | 5 | 91 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP130 | 2026-02-12 | 2026-02 | 2 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 153/1 | 2026-02-13 | 2026-02 | 2 | 2026-05-10 | 2026-05 | 5 | 86 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 25/1 | 2026-02-13 | 2026-02 | 2 | 2026-03-12 | 2026-03 | 3 | 27 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP92 | 2026-02-13 | 2026-02 | 2 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 50A/7 | 2026-02-14 | 2026-02 | 2 | 2026-04-20 | 2026-04 | 4 | 65 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP156 | 2026-02-14 | 2026-02 | 2 | 2026-03-21 | 2026-03 | 3 | 35 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 136/3 | 2026-02-15 | 2026-02 | 2 | 2026-04-25 | 2026-04 | 4 | 69 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 157/1 | 2026-02-15 | 2026-02 | 2 | 2026-03-29 | 2026-03 | 3 | 42 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 72/1 | 2026-02-17 | 2026-02 | 2 | 2026-04-21 | 2026-04 | 4 | 63 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 153/2 | 2026-02-18 | 2026-02 | 2 | 2026-05-19 | 2026-05 | 5 | 90 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP150 | 2026-02-18 | 2026-02 | 2 | 2026-06-09 | 2026-06 | 6 | 111 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP70 | 2026-02-18 | 2026-02 | 2 | 2026-03-31 | 2026-03 | 3 | 41 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP111 | 2026-02-19 | 2026-02 | 2 | 2026-03-13 | 2026-03 | 3 | 22 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 136/4 | 2026-02-20 | 2026-02 | 2 | 2026-05-28 | 2026-05 | 5 | 97 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP12 | 2026-02-20 | 2026-02 | 2 | 2026-07-14 | 2026-07 | 7 | 144 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP44 | 2026-02-20 | 2026-02 | 2 | 2026-03-24 | 2026-03 | 3 | 32 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP46 | 2026-02-20 | 2026-02 | 2 | 2026-05-10 | 2026-05 | 5 | 79 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 70/2 | 2026-02-21 | 2026-02 | 2 | 2026-04-13 | 2026-04 | 4 | 51 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP68 | 2026-02-21 | 2026-02 | 2 | 2026-03-24 | 2026-03 | 3 | 31 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP132 | 2026-02-24 | 2026-02 | 2 | 2026-06-03 | 2026-06 | 6 | 99 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 50A/8 | 2026-02-25 | 2026-02 | 2 | 2026-04-26 | 2026-04 | 4 | 60 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP25 | 2026-02-25 | 2026-02 | 2 | 2026-03-16 | 2026-03 | 3 | 19 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP79 | 2026-02-25 | 2026-02 | 2 | 2026-04-06 | 2026-04 | 4 | 40 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 67/3 | 2026-02-26 | 2026-02 | 2 | 2026-05-08 | 2026-05 | 5 | 71 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 70/1 | 2026-02-26 | 2026-02 | 2 | 2026-06-26 | 2026-06 | 6 | 120 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 44/1 | 2026-02-27 | 2026-02 | 2 | 2026-03-16 | 2026-03 | 3 | 17 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP137 | 2026-02-27 | 2026-02 | 2 | 2026-06-05 | 2026-06 | 6 | 98 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP21 | 2026-02-27 | 2026-02 | 2 | 2026-05-28 | 2026-05 | 5 | 90 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP91 | 2026-02-27 | 2026-02 | 2 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 145/1 | 2026-02-28 | 2026-02 | 2 | 2026-03-31 | 2026-03 | 3 | 31 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP114 | 2026-02-28 | 2026-02 | 2 | 2026-04-12 | 2026-04 | 4 | 43 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP159 | 2026-02-28 | 2026-02 | 2 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP69 | 2026-03-02 | 2026-03 | 3 | 2026-04-17 | 2026-04 | 4 | 46 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 46/5 | 2026-03-05 | 2026-03 | 3 | 2026-04-05 | 2026-04 | 4 | 31 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 50A/3 | 2026-03-06 | 2026-03 | 3 | 2026-04-28 | 2026-04 | 4 | 53 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 29/2 | 2026-03-07 | 2026-03 | 3 | 2026-04-19 | 2026-04 | 4 | 43 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 43/3 | 2026-03-08 | 2026-03 | 3 | 2026-03-30 | 2026-03 | 3 | 22 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP14 | 2026-03-08 | 2026-03 | 3 | 2026-07-18 | 2026-07 | 7 | 132 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 33/2 | 2026-03-09 | 2026-03 | 3 | 2026-03-24 | 2026-03 | 3 | 15 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP149 | 2026-03-10 | 2026-03 | 3 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 46/4 | 2026-03-11 | 2026-03 | 3 | 2026-03-30 | 2026-03 | 3 | 19 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 67/2 | 2026-03-13 | 2026-03 | 3 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP127 | 2026-03-15 | 2026-03 | 3 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP24 | 2026-03-15 | 2026-03 | 3 | 2026-03-25 | 2026-03 | 3 | 10 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP148 | 2026-03-16 | 2026-03 | 3 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP136 | 2026-03-18 | 2026-03 | 3 | 2026-05-20 | 2026-05 | 5 | 63 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 67/1 | 2026-03-19 | 2026-03 | 3 | 2026-04-11 | 2026-04 | 4 | 23 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 43/4 | 2026-03-21 | 2026-03 | 3 | 2026-04-10 | 2026-04 | 4 | 20 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP71 | 2026-03-23 | 2026-03 | 3 | 2026-06-21 | 2026-06 | 6 | 90 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP145 | 2026-03-25 | 2026-03 | 3 | 2026-05-05 | 2026-05 | 5 | 41 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP152 | 2026-03-26 | 2026-03 | 3 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 46/2 | 2026-03-28 | 2026-03 | 3 | 2026-04-14 | 2026-04 | 4 | 17 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP108 | 2026-03-28 | 2026-03 | 3 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 15/3 | 2026-03-30 | 2026-03 | 3 | 2026-04-12 | 2026-04 | 4 | 13 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 38/1 | 2026-03-30 | 2026-03 | 3 | 2026-04-30 | 2026-04 | 4 | 31 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP124 | 2026-03-30 | 2026-03 | 3 | 2026-06-08 | 2026-06 | 6 | 70 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP67 | 2026-03-30 | 2026-03 | 3 | 2026-05-22 | 2026-05 | 5 | 53 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 152/3 | 2026-03-31 | 2026-03 | 3 | 2026-05-16 | 2026-05 | 5 | 46 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 42/3 | 2026-03-31 | 2026-03 | 3 | 2026-04-30 | 2026-04 | 4 | 30 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 56/3 | 2026-03-31 | 2026-03 | 3 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 144/4 | 2026-04-05 | 2026-04 | 4 | 2026-04-30 | 2026-04 | 4 | 25 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 47/1 | 2026-04-05 | 2026-04 | 4 | 2026-04-24 | 2026-04 | 4 | 19 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP125 | 2026-04-06 | 2026-04 | 4 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 144/3 | 2026-04-07 | 2026-04 | 4 | 2026-05-28 | 2026-05 | 5 | 51 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 65/2 | 2026-04-07 | 2026-04 | 4 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP109 | 2026-04-12 | 2026-04 | 4 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 40/2 | 2026-04-13 | 2026-04 | 4 | 2026-04-29 | 2026-04 | 4 | 16 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP126 | 2026-04-15 | 2026-04 | 4 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 42/2 | 2026-04-16 | 2026-04 | 4 | 2026-05-03 | 2026-05 | 5 | 17 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP1 | 2026-04-18 | 2026-04 | 4 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP61 | 2026-04-21 | 2026-04 | 4 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP165 | 2026-04-22 | 2026-04 | 4 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP86 | 2026-04-23 | 2026-04 | 4 | 2026-07-31 | 2026-07 | 7 | 99 | Yes | No | fallback_single_line | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 56/2 | 2026-04-25 | 2026-04 | 4 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP34 | 2026-04-25 | 2026-04 | 4 | 2026-05-08 | 2026-05 | 5 | 13 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP123 | 2026-04-26 | 2026-04 | 4 | 2026-06-14 | 2026-06 | 6 | 49 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP47 | 2026-04-26 | 2026-04 | 4 | 2026-05-03 | 2026-05 | 5 | 7 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP59 | 2026-04-27 | 2026-04 | 4 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 55/1 | 2026-04-28 | 2026-04 | 4 | 2026-06-30 | 2026-06 | 6 | 63 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 37/1 | 2026-04-29 | 2026-04 | 4 | 2026-05-07 | 2026-05 | 5 | 8 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP142 | 2026-04-29 | 2026-04 | 4 | 2026-06-03 | 2026-06 | 6 | 35 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP7 | 2026-04-29 | 2026-04 | 4 | 2026-07-02 | 2026-07 | 7 | 64 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 122/1 | 2026-04-30 | 2026-04 | 4 | 2026-05-25 | 2026-05 | 5 | 25 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP166 | 2026-04-30 | 2026-04 | 4 | 2026-06-21 | 2026-06 | 6 | 52 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP41 | 2026-04-30 | 2026-04 | 4 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP6 | 2026-04-30 | 2026-04 | 4 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP64 | 2026-05-01 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 33/1 | 2026-05-07 | 2026-05 | 5 | 2026-05-17 | 2026-05 | 5 | 10 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 64/1 | 2026-05-07 | 2026-05 | 5 | 2026-06-11 | 2026-06 | 6 | 35 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP144 | 2026-05-07 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP56 | 2026-05-07 | 2026-05 | 5 | 2026-06-23 | 2026-06 | 6 | 47 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 142/1 | 2026-05-08 | 2026-05 | 5 | 2026-05-31 | 2026-05 | 5 | 23 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 61/1 | 2026-05-08 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP82 | 2026-05-08 | 2026-05 | 5 | 2026-06-03 | 2026-06 | 6 | 26 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 57/1 | 2026-05-09 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP161 | 2026-05-09 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP163 | 2026-05-11 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 56/4 | 2026-05-13 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 62/2 | 2026-05-14 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 71/1 | 2026-05-14 | 2026-05 | 5 | 2026-06-02 | 2026-06 | 6 | 19 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP110 | 2026-05-14 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP38 | 2026-05-14 | 2026-05 | 5 | 2026-05-21 | 2026-05 | 5 | 7 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP57 | 2026-05-15 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 159/3 | 2026-05-16 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 40/3 | 2026-05-16 | 2026-05 | 5 | 2026-05-26 | 2026-05 | 5 | 10 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 65/4 | 2026-05-16 | 2026-05 | 5 | 2026-05-28 | 2026-05 | 5 | 12 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 50A/2 | 2026-05-17 | 2026-05 | 5 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP162 | 2026-05-17 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP60 | 2026-05-17 | 2026-05 | 5 | 2026-06-14 | 2026-06 | 6 | 28 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 62/1 | 2026-05-18 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP128 | 2026-05-18 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP143 | 2026-05-18 | 2026-05 | 5 | 2026-06-10 | 2026-06 | 6 | 23 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP63 | 2026-05-18 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 159/2 | 2026-05-19 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 23/2 | 2026-05-19 | 2026-05 | 5 | 2026-05-26 | 2026-05 | 5 | 7 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 57/2 | 2026-05-19 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP112 | 2026-05-19 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP70/3 | 2026-05-19 | 2026-05 | 5 | 2026-06-10 | 2026-06 | 6 | 22 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 159/1 | 2026-05-22 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 60/1 | 2026-05-22 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 143/1 | 2026-05-23 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 50A/1 | 2026-05-23 | 2026-05 | 5 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP113 | 2026-05-23 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP158 | 2026-05-23 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP7 | 2026-05-24 | 2026-05 | 5 |  |  |  |  | No | No |  | LILO |  | TB 605 - DPR - 2026-08-12.xlsx | LILO
TB 605 | 6xx | Private | tb605 | AP84 | 2026-05-24 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 39/1 | 2026-05-25 | 2026-05 | 5 | 2026-06-08 | 2026-06 | 6 | 14 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP39 | 2026-05-25 | 2026-05 | 5 | 2026-06-02 | 2026-06 | 6 | 8 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP55 | 2026-05-25 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 59/1 | 2026-05-26 | 2026-05 | 5 | 2026-06-17 | 2026-06 | 6 | 22 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP42 | 2026-05-26 | 2026-05 | 5 | 2026-08-09 | 2026-08 | 8 | 75 | Yes | No | fallback_single_line | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP66 | 2026-05-26 | 2026-05 | 5 | 2026-05-30 | 2026-05 | 5 | 4 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 34/1 | 2026-05-28 | 2026-05 | 5 | 2026-06-19 | 2026-06 | 6 | 22 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 65/1 | 2026-05-28 | 2026-05 | 5 | 2026-06-07 | 2026-06 | 6 | 10 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP65 | 2026-05-28 | 2026-05 | 5 | 2026-06-04 | 2026-06 | 6 | 7 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 65/5 | 2026-05-30 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP105 | 2026-05-30 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP168 | 2026-05-30 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP174 | 2026-05-30 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP167 | 2026-05-31 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP81 | 2026-05-31 | 2026-05 | 5 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 35/1 | 2026-06-03 | 2026-06 | 6 | 2026-06-14 | 2026-06 | 6 | 11 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 65/3 | 2026-06-03 | 2026-06 | 6 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP35 | 2026-06-03 | 2026-06 | 6 | 2026-06-24 | 2026-06 | 6 | 21 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 144/1 | 2026-06-04 | 2026-06 | 6 | 2026-06-21 | 2026-06 | 6 | 17 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP54 | 2026-06-05 | 2026-06 | 6 | 2026-06-29 | 2026-06 | 6 | 24 | Yes | No | fallback_single_line | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP76 | 2026-06-05 | 2026-06 | 6 | 2026-06-15 | 2026-06 | 6 | 10 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP89 | 2026-06-05 | 2026-06 | 6 | 2026-07-05 | 2026-07 | 7 | 30 | Yes | No | fallback_single_line | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 50A/4 | 2026-06-06 | 2026-06 | 6 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP173 | 2026-06-06 | 2026-06 | 6 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP58 | 2026-06-06 | 2026-06 | 6 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 143/2 | 2026-06-09 | 2026-06 | 6 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 23/3 | 2026-06-09 | 2026-06 | 6 | 2026-06-16 | 2026-06 | 6 | 7 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 42/1 | 2026-06-09 | 2026-06 | 6 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP36 | 2026-06-09 | 2026-06 | 6 | 2026-07-26 | 2026-07 | 7 | 47 | Yes | No | fallback_single_line | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP88 | 2026-06-09 | 2026-06 | 6 | 2026-07-18 | 2026-07 | 7 | 39 | Yes | No | fallback_single_line | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP175 | 2026-06-10 | 2026-06 | 6 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP78 | 2026-06-10 | 2026-06 | 6 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 144/2 | 2026-06-12 | 2026-06 | 6 | 2026-06-17 | 2026-06 | 6 | 5 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 77/3 | 2026-06-12 | 2026-06 | 6 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 37/2 | 2026-06-14 | 2026-06 | 6 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | 47/3 | 2026-06-15 | 2026-06 | 6 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP53 | 2026-06-17 | 2026-06 | 6 | 2026-07-27 | 2026-07 | 7 | 40 | Yes | No | fallback_single_line | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 180/1 | 2026-06-19 | 2026-06 | 6 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 47/2 | 2026-06-19 | 2026-06 | 6 | 2026-07-20 | 2026-07 | 7 | 31 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 50A/5 | 2026-06-19 | 2026-06 | 6 | 2026-08-06 | 2026-08 | 8 | 48 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 52/1 | 2026-06-20 | 2026-06 | 6 | 2026-08-10 | 2026-08 | 8 | 51 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 8/1 | 2026-06-22 | 2026-06 | 6 |  |  |  |  | No | No |  | LILO |  | TB 605 - DPR - 2026-08-12.xlsx | LILO
TB 605 | 6xx | Private | tb605 | AP172 | 2026-06-22 | 2026-06 | 6 | 2026-06-28 | 2026-06 | 6 | 6 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP62 | 2026-06-22 | 2026-06 | 6 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP48 | 2026-06-23 | 2026-06 | 6 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP140 | 2026-06-24 | 2026-06 | 6 | 2026-06-29 | 2026-06 | 6 | 5 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP6 | 2026-06-24 | 2026-06 | 6 |  |  |  |  | No | No |  | LILO |  | TB 605 - DPR - 2026-08-12.xlsx | LILO
TB 605 | 6xx | Private | tb605 | 171/1 | 2026-06-25 | 2026-06 | 6 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 50A/9 | 2026-06-25 | 2026-06 | 6 | 2026-07-16 | 2026-07 | 7 | 21 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP151 | 2026-06-25 | 2026-06 | 6 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 56/1 | 2026-06-26 | 2026-06 | 6 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP180 | 2026-06-27 | 2026-06 | 6 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP8 | 2026-06-27 | 2026-06 | 6 |  |  |  |  | No | No |  | LILO |  | TB 605 - DPR - 2026-08-12.xlsx | LILO
TB 605 | 6xx | Private | tb605 | 50A/10 | 2026-06-30 | 2026-06 | 6 | 2026-07-07 | 2026-07 | 7 | 7 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP10 | 2026-06-30 | 2026-06 | 6 | 2026-07-06 | 2026-07 | 7 | 6 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP5 | 2026-06-30 | 2026-06 | 6 |  |  |  |  | No | No |  | LILO |  | TB 605 - DPR - 2026-08-12.xlsx | LILO
TB 605 | 6xx | Private | tb605 | AP52 | 2026-07-03 | 2026-07 | 7 | 2026-07-07 | 2026-07 | 7 | 4 | Yes | No | exact | Punjab | Punjab | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-12.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP176 | 2026-07-06 | 2026-07 | 7 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP51 | 2026-07-13 | 2026-07 | 7 | 2026-07-20 | 2026-07 | 7 | 7 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP13 | 2026-07-14 | 2026-07 | 7 | 2026-07-19 | 2026-07 | 7 | 5 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 50A/6 | 2026-07-25 | 2026-07 | 7 | 2026-07-30 | 2026-07 | 7 | 5 | Yes | No | exact | Jammu | Jammu | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-12.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP8 | 2026-07-27 | 2026-07 | 7 |  |  |  |  | No | No |  | Jammu |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP182 | 2026-07-31 | 2026-07 | 7 |  |  |  |  | No | No |  | Punjab |  | TB 605 - DPR - 2026-08-12.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP4 | 2026-08-11 | 2026-08 | 8 |  |  |  |  | No | No |  | LILO |  | TB 605 - DPR - 2026-08-12.xlsx | LILO
TB 605 | 6xx | Private | tb605 | AP9 | 2026-08-11 | 2026-08 | 8 |  |  |  |  | No | No |  | LILO |  | TB 605 - DPR - 2026-08-12.xlsx | LILO
TB 608 | 6xx | Private | tb608 | 65/3 | 2025-10-18 | 2025-10 | 10 | 2026-07-31 | 2026-07 | 7 | 286 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 69/2 | 2025-10-18 | 2025-10 | 10 | 2026-04-22 | 2026-04 | 4 | 186 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 131/2 | 2025-11-09 | 2025-11 | 11 | 2026-03-17 | 2026-03 | 3 | 128 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 58/1 | 2025-11-10 | 2025-11 | 11 | 2025-12-27 | 2025-12 | 12 | 47 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 69/0 | 2025-11-10 | 2025-11 | 11 | 2026-04-11 | 2026-04 | 4 | 152 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 58/0 | 2025-11-11 | 2025-11 | 11 | 2026-04-03 | 2026-04 | 4 | 143 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 75/5 | 2025-11-15 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 34/3 | 2025-11-18 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 101/0 | 2025-11-19 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 71/1 | 2025-11-20 | 2025-11 | 11 | 2025-12-28 | 2025-12 | 12 | 38 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 33/2 | 2025-11-22 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 90/0 | 2025-11-22 | 2025-11 | 11 | 2026-05-31 | 2026-05 | 5 | 190 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 29/0 | 2025-11-25 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 40/0 | 2025-11-25 | 2025-11 | 11 | 2026-03-31 | 2026-03 | 3 | 126 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 72/6 | 2025-11-28 | 2025-11 | 11 | 2026-01-21 | 2026-01 | 1 | 54 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 88/0 | 2025-11-28 | 2025-11 | 11 | 2026-03-25 | 2026-03 | 3 | 117 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 100/0 | 2025-11-30 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 103/0 | 2025-11-30 | 2025-11 | 11 | 2026-05-08 | 2026-05 | 5 | 159 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 109/0 | 2025-11-30 | 2025-11 | 11 | 2026-08-06 | 2026-08 | 8 | 249 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 71/0 | 2025-11-30 | 2025-11 | 11 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 85/0 | 2025-11-30 | 2025-11 | 11 | 2026-07-26 | 2026-07 | 7 | 238 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 89/0 | 2025-11-30 | 2025-11 | 11 | 2026-05-12 | 2026-05 | 5 | 163 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 29/1 | 2025-12-02 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 75/3 | 2025-12-03 | 2025-12 | 12 | 2026-02-18 | 2026-02 | 2 | 77 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 69/3 | 2025-12-08 | 2025-12 | 12 | 2026-05-13 | 2026-05 | 5 | 156 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 5/0 | 2025-12-10 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 80/0 | 2025-12-11 | 2025-12 | 12 | 2026-06-19 | 2026-06 | 6 | 190 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 108/0 | 2025-12-12 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 111/0 | 2025-12-12 | 2025-12 | 12 | 2026-06-03 | 2026-06 | 6 | 173 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 29/4 | 2025-12-14 | 2025-12 | 12 | 2026-01-29 | 2026-01 | 1 | 46 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 48/0 | 2025-12-14 | 2025-12 | 12 | 2026-05-08 | 2026-05 | 5 | 145 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 29/3 | 2025-12-17 | 2025-12 | 12 | 2026-02-25 | 2026-02 | 2 | 70 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 75/4 | 2025-12-18 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 99/0 | 2025-12-18 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 102/0 | 2025-12-19 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 84/0 | 2025-12-19 | 2025-12 | 12 | 2026-08-11 | 2026-08 | 8 | 235 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 111/1 | 2025-12-21 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 83/0 | 2025-12-21 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 91/0 | 2025-12-21 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 93/0 | 2025-12-21 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 34/1 | 2025-12-22 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 25/1 | 2025-12-23 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 70/3 | 2025-12-23 | 2025-12 | 12 | 2026-01-31 | 2026-01 | 1 | 39 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 29/2 | 2025-12-25 | 2025-12 | 12 | 2026-03-04 | 2026-03 | 3 | 69 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 4/1 | 2025-12-25 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 112/0 | 2025-12-27 | 2025-12 | 12 | 2026-06-14 | 2026-06 | 6 | 169 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 49/0 | 2025-12-27 | 2025-12 | 12 | 2026-05-17 | 2026-05 | 5 | 141 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 91/1 | 2025-12-27 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 79/1 | 2025-12-28 | 2025-12 | 12 | 2026-05-31 | 2026-05 | 5 | 154 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 91/2 | 2025-12-28 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 114/0 | 2025-12-31 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 70/2 | 2025-12-31 | 2025-12 | 12 | 2026-02-10 | 2026-02 | 2 | 41 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 77/0 | 2025-12-31 | 2025-12 | 12 | 2026-03-06 | 2026-03 | 3 | 65 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 86/0 | 2025-12-31 | 2025-12 | 12 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 91/8 | 2025-12-31 | 2025-12 | 12 | 2026-03-17 | 2026-03 | 3 | 76 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 94/0 | 2025-12-31 | 2025-12 | 12 | 2026-06-14 | 2026-06 | 6 | 165 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 41/2 | 2026-01-02 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 11/2 | 2026-01-03 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 70/0 | 2026-01-04 | 2026-01 | 1 | 2026-04-30 | 2026-04 | 4 | 116 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 40/1 | 2026-01-07 | 2026-01 | 1 | 2026-04-12 | 2026-04 | 4 | 95 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 97/0 | 2026-01-09 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 41/0 | 2026-01-10 | 2026-01 | 1 | 2026-04-19 | 2026-04 | 4 | 99 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 113/0 | 2026-01-11 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 76/3 | 2026-01-11 | 2026-01 | 1 | 2026-02-28 | 2026-02 | 2 | 48 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 91/5 | 2026-01-12 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 110/0 | 2026-01-13 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 115/0 | 2026-01-14 | 2026-01 | 1 | 2026-06-03 | 2026-06 | 6 | 140 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 8/0 | 2026-01-14 | 2026-01 | 1 | 2026-06-13 | 2026-06 | 6 | 150 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 76/0 | 2026-01-15 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 69/4 | 2026-01-18 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 75/1 | 2026-01-19 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 50/0 | 2026-01-21 | 2026-01 | 1 | 2026-05-31 | 2026-05 | 5 | 130 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 11/1 | 2026-01-24 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 123/2 | 2026-01-25 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 129/1 | 2026-01-27 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 34/2 | 2026-01-27 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 47/1 | 2026-01-28 | 2026-01 | 1 | 2026-06-21 | 2026-06 | 6 | 144 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 79/0 | 2026-01-28 | 2026-01 | 1 | 2026-06-09 | 2026-06 | 6 | 132 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 132/1 | 2026-01-29 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 69/1 | 2026-01-29 | 2026-01 | 1 | 2026-04-09 | 2026-04 | 4 | 70 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 91/7 | 2026-01-29 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 96/0 | 2026-01-30 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 128/0 | 2026-01-31 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 131/0 | 2026-01-31 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 75/2 | 2026-01-31 | 2026-01 | 1 | 2026-07-31 | 2026-07 | 7 | 181 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 91/4 | 2026-01-31 | 2026-01 | 1 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 59/1 | 2026-02-05 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 73/6 | 2026-02-05 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 76/1 | 2026-02-05 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 81/0 | 2026-02-05 | 2026-02 | 2 | 2026-03-22 | 2026-03 | 3 | 45 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 96/1 | 2026-02-05 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 104/0 | 2026-02-08 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 42/1 | 2026-02-08 | 2026-02 | 2 | 2026-06-21 | 2026-06 | 6 | 133 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 126/0 | 2026-02-10 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 43/0 | 2026-02-10 | 2026-02 | 2 | 2026-06-04 | 2026-06 | 6 | 114 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 72/7 | 2026-02-11 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 9/1 | 2026-02-11 | 2026-02 | 2 | 2026-05-31 | 2026-05 | 5 | 109 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 78/2 | 2026-02-12 | 2026-02 | 2 | 2026-07-05 | 2026-07 | 7 | 143 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 95/3 | 2026-02-14 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 95/1 | 2026-02-16 | 2026-02 | 2 | 2026-07-19 | 2026-07 | 7 | 153 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 131/3 | 2026-02-17 | 2026-02 | 2 | 2026-04-23 | 2026-04 | 4 | 65 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 129/2 | 2026-02-18 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 6/1 | 2026-02-18 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 95/0 | 2026-02-18 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 131/1 | 2026-02-19 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 44/0 | 2026-02-19 | 2026-02 | 2 | 2026-08-09 | 2026-08 | 8 | 171 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 30/0 | 2026-02-20 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 10/3 | 2026-02-22 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 124/0 | 2026-02-22 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 71/2 | 2026-02-22 | 2026-02 | 2 | 2026-04-11 | 2026-04 | 4 | 48 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 70/1 | 2026-02-23 | 2026-02 | 2 | 2026-05-12 | 2026-05 | 5 | 78 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 72/0 | 2026-02-23 | 2026-02 | 2 | 2026-04-11 | 2026-04 | 4 | 47 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 127/0 | 2026-02-25 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 132/2 | 2026-02-28 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 132/3 | 2026-02-28 | 2026-02 | 2 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 95/2 | 2026-02-28 | 2026-02 | 2 | 2026-07-11 | 2026-07 | 7 | 133 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 31/0 | 2026-03-06 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 35/0 | 2026-03-08 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 10/1 | 2026-03-10 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 129/0 | 2026-03-10 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 130/0 | 2026-03-10 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 82/2 | 2026-03-10 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 82/1 | 2026-03-11 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 116/0 | 2026-03-12 | 2026-03 | 3 | 2026-07-05 | 2026-07 | 7 | 115 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 27/0 | 2026-03-14 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 125/0 | 2026-03-19 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 47/0 | 2026-03-28 | 2026-03 | 3 | 2026-07-05 | 2026-07 | 7 | 99 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 6/0 | 2026-03-28 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 132/0 | 2026-03-29 | 2026-03 | 3 | 2026-05-31 | 2026-05 | 5 | 63 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 7/0 | 2026-03-30 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 34/0 | 2026-03-31 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 7/2 | 2026-03-31 | 2026-03 | 3 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 92/0 | 2026-04-13 | 2026-04 | 4 | 2026-06-28 | 2026-06 | 6 | 76 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 9/0 | 2026-04-14 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 107/1 | 2026-04-19 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 7/1 | 2026-04-21 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 61A/0 | 2026-04-23 | 2026-04 | 4 | 2026-06-09 | 2026-06 | 6 | 47 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 106/0 | 2026-04-30 | 2026-04 | 4 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 1/0 | 2026-05-06 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 38/0 | 2026-05-06 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 61/0 | 2026-05-06 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 105/0 | 2026-05-07 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 39/0 | 2026-05-12 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 20/0 | 2026-05-14 | 2026-05 | 5 | 2026-06-30 | 2026-06 | 6 | 47 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 3/0 | 2026-05-17 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 4/0 | 2026-05-24 | 2026-05 | 5 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 18/0 | 2026-05-26 | 2026-05 | 5 | 2026-07-22 | 2026-07 | 7 | 57 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 70/4 | 2026-06-13 | 2026-06 | 6 | 2026-07-19 | 2026-07 | 7 | 36 | Yes | No | fallback_single_line |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 91/9 | 2026-06-18 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 5/1 | 2026-06-21 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 118/0 | 2026-06-30 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 42/0 | 2026-06-30 | 2026-06 | 6 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 73/5 | 2026-07-10 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 119/0 | 2026-07-19 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 14/0 | 2026-07-27 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 62/3 | 2026-07-29 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 20/1 | 2026-07-31 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 68/0 | 2026-07-31 | 2026-07 | 7 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 37/0 | 2026-08-04 | 2026-08 | 8 |  |  |  |  | No | No |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN

## Mechanism Config
Mechanism Config
Parameter | Value
pre_monsoon | 4,5
monsoon | 6,7,8,9
post_monsoon | 10,11
post_monsoon_wide | 10,11,12
dry | 12,1,2,3
min_foundation_count | 5