## Raw Project Wise
Project | Series | Ownership | Project Rollup Key | Location | Foundation Date | Foundation Month | Erection Start | Erection Start Month | Delay Days | Delay Used In Matched Stats | Matched | Negative Excluded | Match Basis | Censoring Status | Exposure Days As Of 2026-08-12 | Eligible For 30D Horizon | Erected Within 30D | Eligible For 60D Horizon | Erected Within 60D | Analysis Period | Foundation Line | Erection Line | Foundation Source File | Foundation Source Sheet | Erection Source File | Erection Source Sheet
TA 413 | 4xx | Government | ta413 | 9/4 | 2024-06-06 | 2024-06 | 2025-03-05 | 2025-03 | 272 | 272 | Yes | No | exact | Observed matched delay | 797 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 10/1 | 2024-06-07 | 2024-06 | 2025-10-12 | 2025-10 | 492 | 492 | Yes | No | exact | Observed matched delay | 796 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 10/2 | 2024-06-09 | 2024-06 | 2025-11-01 | 2025-11 | 510 | 510 | Yes | No | exact | Observed matched delay | 794 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/11 | 2024-06-11 | 2024-06 | 2025-10-18 | 2025-10 | 494 | 494 | Yes | No | exact | Observed matched delay | 792 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/2 | 2024-06-17 | 2024-06 | 2025-03-14 | 2025-03 | 270 | 270 | Yes | No | exact | Observed matched delay | 786 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/5 | 2024-06-17 | 2024-06 | 2025-08-15 | 2025-08 | 424 | 424 | Yes | No | exact | Observed matched delay | 786 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/3 | 2024-06-18 | 2024-06 | 2025-03-19 | 2025-03 | 274 | 274 | Yes | No | exact | Observed matched delay | 785 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/4 | 2024-06-21 | 2024-06 | 2025-03-23 | 2025-03 | 275 | 275 | Yes | No | exact | Observed matched delay | 782 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/3 | 2024-06-23 | 2024-06 | 2025-03-01 | 2025-03 | 251 | 251 | Yes | No | exact | Observed matched delay | 780 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/5 | 2024-06-24 | 2024-06 | 2025-03-26 | 2025-03 | 275 | 275 | Yes | No | exact | Observed matched delay | 779 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/5 | 2024-06-26 | 2024-06 | 2025-01-04 | 2025-01 | 192 | 192 | Yes | No | exact | Observed matched delay | 777 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/6 | 2024-06-27 | 2024-06 | 2025-03-31 | 2025-03 | 277 | 277 | Yes | No | exact | Observed matched delay | 776 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/10 | 2024-06-28 | 2024-06 | 2025-10-31 | 2025-10 | 490 | 490 | Yes | No | exact | Observed matched delay | 775 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/2 | 2024-06-29 | 2024-06 | 2025-03-10 | 2025-03 | 254 | 254 | Yes | No | exact | Observed matched delay | 774 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/9 | 2024-07-03 | 2024-07 | 2025-11-22 | 2025-11 | 507 | 507 | Yes | No | exact | Observed matched delay | 770 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/6 | 2024-07-03 | 2024-07 | 2025-01-10 | 2025-01 | 191 | 191 | Yes | No | exact | Observed matched delay | 770 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/8 | 2024-07-06 | 2024-07 | 2025-09-27 | 2025-09 | 448 | 448 | Yes | No | exact | Observed matched delay | 767 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/9 | 2024-07-06 | 2024-07 | 2025-08-23 | 2025-08 | 413 | 413 | Yes | No | exact | Observed matched delay | 767 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/7 | 2024-07-09 | 2024-07 | 2025-01-16 | 2025-01 | 191 | 191 | Yes | No | exact | Observed matched delay | 764 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/10 | 2024-07-10 | 2024-07 | 2025-11-16 | 2025-11 | 494 | 494 | Yes | No | exact | Observed matched delay | 763 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/8 | 2024-07-10 | 2024-07 | 2025-09-15 | 2025-09 | 432 | 432 | Yes | No | exact | Observed matched delay | 763 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/1 | 2024-07-10 | 2024-07 | 2025-02-24 | 2025-02 | 229 | 229 | Yes | No | exact | Observed matched delay | 763 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/7 | 2024-07-11 | 2024-07 | 2025-11-10 | 2025-11 | 487 | 487 | Yes | No | exact | Observed matched delay | 762 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/7 | 2024-07-15 | 2024-07 | 2025-09-10 | 2025-09 | 422 | 422 | Yes | No | exact | Observed matched delay | 758 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/11 | 2024-07-18 | 2024-07 | 2025-12-07 | 2025-12 | 507 | 507 | Yes | No | exact | Observed matched delay | 755 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/8 | 2024-07-19 | 2024-07 | 2025-01-20 | 2025-01 | 185 | 185 | Yes | No | exact | Observed matched delay | 754 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/1 | 2024-07-20 | 2024-07 | 2024-12-07 | 2024-12 | 140 | 140 | Yes | No | exact | Observed matched delay | 753 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/6 | 2024-07-22 | 2024-07 | 2025-09-04 | 2025-09 | 409 | 409 | Yes | No | exact | Observed matched delay | 751 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29/4 | 2024-07-24 | 2024-07 | 2024-10-03 | 2024-10 | 71 | 71 | Yes | No | exact | Observed matched delay | 749 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/2 | 2024-07-25 | 2024-07 | 2025-02-03 | 2025-02 | 193 | 193 | Yes | No | exact | Observed matched delay | 748 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/9 | 2024-07-25 | 2024-07 | 2025-01-25 | 2025-01 | 184 | 184 | Yes | No | exact | Observed matched delay | 748 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/10 | 2024-07-28 | 2024-07 | 2025-08-15 | 2025-08 | 383 | 383 | Yes | No | exact | Observed matched delay | 745 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29/3 | 2024-07-29 | 2024-07 | 2024-09-28 | 2024-09 | 61 | 61 | Yes | No | exact | Observed matched delay | 744 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/3 | 2024-07-31 | 2024-07 | 2025-08-12 | 2025-08 | 377 | 377 | Yes | No | exact | Observed matched delay | 742 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/1 | 2024-08-01 | 2024-08 | 2024-10-09 | 2024-10 | 69 | 69 | Yes | No | exact | Observed matched delay | 741 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29/5 | 2024-08-03 | 2024-08 | 2024-09-21 | 2024-09 | 49 | 49 | Yes | No | exact | Observed matched delay | 739 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/1 | 2024-08-03 | 2024-08 | 2025-08-02 | 2025-08 | 364 | 364 | Yes | No | exact | Observed matched delay | 739 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29A/2 | 2024-08-08 | 2024-08 | 2024-09-12 | 2024-09 | 35 | 35 | Yes | No | exact | Observed matched delay | 734 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/3 | 2024-08-08 | 2024-08 | 2025-09-09 | 2025-09 | 397 | 397 | Yes | No | exact | Observed matched delay | 734 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7/1 | 2024-08-10 | 2024-08 | 2024-12-15 | 2024-12 | 127 | 127 | Yes | No | exact | Observed matched delay | 732 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/10 | 2024-08-13 | 2024-08 | 2025-01-30 | 2025-01 | 170 | 170 | Yes | No | exact | Observed matched delay | 729 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29A/1 | 2024-08-14 | 2024-08 | 2024-10-14 | 2024-10 | 61 | 61 | Yes | No | exact | Observed matched delay | 728 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 27/4 | 2024-08-16 | 2024-08 | 2025-10-27 | 2025-10 | 437 | 437 | Yes | No | exact | Observed matched delay | 726 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7A/5 | 2024-08-17 | 2024-08 | 2024-12-17 | 2024-12 | 122 | 122 | Yes | No | exact | Observed matched delay | 725 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/8 | 2024-08-18 | 2024-08 | 2025-09-10 | 2025-09 | 388 | 388 | Yes | No | exact | Observed matched delay | 724 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29A/3 | 2024-08-20 | 2024-08 | 2025-12-27 | 2025-12 | 494 | 494 | Yes | No | exact | Observed matched delay | 722 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32/3 | 2024-08-20 | 2024-08 | 2025-07-27 | 2025-07 | 341 | 341 | Yes | No | exact | Observed matched delay | 722 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7A/4 | 2024-08-23 | 2024-08 | 2024-12-24 | 2024-12 | 123 | 123 | Yes | No | exact | Observed matched delay | 719 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29A/4 | 2024-08-24 | 2024-08 | 2025-10-05 | 2025-10 | 407 | 407 | Yes | No | exact | Observed matched delay | 718 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/4 | 2024-08-25 | 2024-08 | 2025-08-29 | 2025-08 | 369 | 369 | Yes | No | exact | Observed matched delay | 717 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32/4 | 2024-08-26 | 2024-08 | 2025-08-07 | 2025-08 | 346 | 346 | Yes | No | exact | Observed matched delay | 716 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29A/5 | 2024-08-27 | 2024-08 | 2025-09-26 | 2025-09 | 395 | 395 | Yes | No | exact | Observed matched delay | 715 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/2 | 2024-08-27 | 2024-08 | 2025-08-04 | 2025-08 | 342 | 342 | Yes | No | exact | Observed matched delay | 715 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 27/5 | 2024-08-28 | 2024-08 | 2025-10-23 | 2025-10 | 421 | 421 | Yes | No | exact | Observed matched delay | 714 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/6 | 2024-08-30 | 2024-08 | 2025-01-29 | 2025-01 | 152 | 152 | Yes | No | exact | Observed matched delay | 712 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/1 | 2024-08-30 | 2024-08 | 2025-07-16 | 2025-07 | 320 | 320 | Yes | No | exact | Observed matched delay | 712 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29A/6 | 2024-08-31 | 2024-08 | 2024-10-03 | 2024-10 | 33 | 33 | Yes | No | exact | Observed matched delay | 711 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4A/5 | 2024-09-01 | 2024-09 | 2025-08-25 | 2025-08 | 358 | 358 | Yes | No | exact | Observed matched delay | 710 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7A/1 | 2024-09-01 | 2024-09 | 2025-01-17 | 2025-01 | 138 | 138 | Yes | No | exact | Observed matched delay | 710 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/7 | 2024-09-04 | 2024-09 | 2025-08-23 | 2025-08 | 353 | 353 | Yes | No | exact | Observed matched delay | 707 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/10 | 2024-09-04 | 2024-09 | 2025-08-22 | 2025-08 | 352 | 352 | Yes | No | exact | Observed matched delay | 707 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/12 | 2024-09-05 | 2024-09 | 2025-08-01 | 2025-08 | 330 | 330 | Yes | No | exact | Observed matched delay | 706 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4A/4 | 2024-09-06 | 2024-09 | 2025-08-18 | 2025-08 | 346 | 346 | Yes | No | exact | Observed matched delay | 705 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7A/2 | 2024-09-06 | 2024-09 | 2025-01-08 | 2025-01 | 124 | 124 | Yes | No | exact | Observed matched delay | 705 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/3 | 2024-09-07 | 2024-09 | 2025-08-08 | 2025-08 | 335 | 335 | Yes | No | exact | Observed matched delay | 704 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/4 | 2024-09-09 | 2024-09 | 2025-09-05 | 2025-09 | 361 | 361 | Yes | No | exact | Observed matched delay | 702 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4A/3 | 2024-09-09 | 2024-09 | 2025-08-29 | 2025-08 | 354 | 354 | Yes | No | exact | Observed matched delay | 702 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29/1 | 2024-09-10 | 2024-09 | 2025-10-07 | 2025-10 | 392 | 392 | Yes | No | exact | Observed matched delay | 701 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7A/3 | 2024-09-10 | 2024-09 | 2025-01-01 | 2025-01 | 113 | 113 | Yes | No | exact | Observed matched delay | 701 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4A/6 | 2024-09-12 | 2024-09 | 2025-09-09 | 2025-09 | 362 | 362 | Yes | No | exact | Observed matched delay | 699 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/7 | 2024-09-12 | 2024-09 | 2025-09-02 | 2025-09 | 355 | 355 | Yes | No | exact | Observed matched delay | 699 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/3 | 2024-09-13 | 2024-09 | 2025-08-31 | 2025-08 | 352 | 352 | Yes | No | exact | Observed matched delay | 698 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/12 | 2024-09-13 | 2024-09 | 2024-11-14 | 2024-11 | 62 | 62 | Yes | No | exact | Observed matched delay | 698 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/11 | 2024-09-14 | 2024-09 | 2025-08-19 | 2025-08 | 339 | 339 | Yes | No | exact | Observed matched delay | 697 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/1 | 2024-09-15 | 2024-09 | 2025-01-21 | 2025-01 | 128 | 128 | Yes | No | exact | Observed matched delay | 696 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 36A/1 | 2024-09-15 | 2024-09 | 2024-12-13 | 2024-12 | 89 | 89 | Yes | No | exact | Observed matched delay | 696 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/6 | 2024-09-15 | 2024-09 | 2025-08-08 | 2025-08 | 327 | 327 | Yes | No | exact | Observed matched delay | 696 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4A/2 | 2024-09-16 | 2024-09 | 2025-09-07 | 2025-09 | 356 | 356 | Yes | No | exact | Observed matched delay | 695 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/3 | 2024-09-18 | 2024-09 | 2024-12-05 | 2024-12 | 78 | 78 | Yes | No | exact | Observed matched delay | 693 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 36A/2 | 2024-09-19 | 2024-09 | 2025-01-04 | 2025-01 | 107 | 107 | Yes | No | exact | Observed matched delay | 692 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 27/2 | 2024-09-20 | 2024-09 | 2025-11-21 | 2025-11 | 427 | 427 | Yes | No | exact | Observed matched delay | 691 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/11 | 2024-09-20 | 2024-09 | 2024-12-30 | 2024-12 | 101 | 101 | Yes | No | exact | Observed matched delay | 691 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/4 | 2024-09-20 | 2024-09 | 2025-08-15 | 2025-08 | 329 | 329 | Yes | No | exact | Observed matched delay | 691 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/4 | 2024-09-21 | 2024-09 | 2024-11-25 | 2024-11 | 65 | 65 | Yes | No | exact | Observed matched delay | 690 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4A/1 | 2024-09-21 | 2024-09 | 2025-09-18 | 2025-09 | 362 | 362 | Yes | No | exact | Observed matched delay | 690 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37/1 | 2024-09-23 | 2024-09 |  |  |  |  | No | No |  | Unmatched/right-censored | 688 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation
TA 413 | 4xx | Government | ta413 | 5/2 | 2024-09-23 | 2024-09 | 2025-09-26 | 2025-09 | 368 | 368 | Yes | No | exact | Observed matched delay | 688 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/6 | 2024-09-23 | 2024-09 | 2025-08-14 | 2025-08 | 325 | 325 | Yes | No | exact | Observed matched delay | 688 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/5 | 2024-09-25 | 2024-09 | 2024-12-17 | 2024-12 | 83 | 83 | Yes | No | exact | Observed matched delay | 686 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/1 | 2024-09-26 | 2024-09 | 2025-01-07 | 2025-01 | 103 | 103 | Yes | No | exact | Observed matched delay | 685 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37/2 | 2024-09-27 | 2024-09 | 2026-01-12 | 2026-01 | 472 | 472 | Yes | No | exact | Observed matched delay | 684 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4/1 | 2024-09-27 | 2024-09 | 2025-09-06 | 2025-09 | 344 | 344 | Yes | No | exact | Observed matched delay | 684 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 27/1 | 2024-09-28 | 2024-09 | 2025-12-05 | 2025-12 | 433 | 433 | Yes | No | exact | Observed matched delay | 683 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/6 | 2024-09-28 | 2024-09 | 2024-12-30 | 2024-12 | 93 | 93 | Yes | No | exact | Observed matched delay | 683 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/10 | 2024-09-29 | 2024-09 | 2025-08-09 | 2025-08 | 314 | 314 | Yes | No | exact | Observed matched delay | 682 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/8 | 2024-09-30 | 2024-09 | 2024-11-12 | 2024-11 | 43 | 43 | Yes | No | exact | Observed matched delay | 681 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37/3 | 2024-09-30 | 2024-09 | 2026-01-23 | 2026-01 | 480 | 480 | Yes | No | exact | Observed matched delay | 681 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4A/0 | 2024-10-01 | 2024-10 | 2025-09-13 | 2025-09 | 347 | 347 | Yes | No | exact | Observed matched delay | 680 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/9 | 2024-10-01 | 2024-10 | 2025-08-23 | 2025-08 | 326 | 326 | Yes | No | exact | Observed matched delay | 680 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7/0 | 2024-10-01 | 2024-10 | 2025-07-22 | 2025-07 | 294 | 294 | Yes | No | exact | Observed matched delay | 680 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/5 | 2024-10-03 | 2024-10 | 2025-01-06 | 2025-01 | 95 | 95 | Yes | No | exact | Observed matched delay | 678 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/7 | 2024-10-04 | 2024-10 | 2024-11-26 | 2024-11 | 53 | 53 | Yes | No | exact | Observed matched delay | 677 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3/8 | 2024-10-05 | 2024-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 676 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation
TA 413 | 4xx | Government | ta413 | 36A/0 | 2024-10-05 | 2024-10 | 2025-04-18 | 2025-04 | 195 | 195 | Yes | No | exact | Observed matched delay | 676 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/9 | 2024-10-07 | 2024-10 | 2024-12-13 | 2024-12 | 67 | 67 | Yes | No | exact | Observed matched delay | 674 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/9 | 2024-10-07 | 2024-10 | 2025-08-29 | 2025-08 | 326 | 326 | Yes | No | exact | Observed matched delay | 674 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 27/3 | 2024-10-08 | 2024-10 | 2025-11-28 | 2025-11 | 416 | 416 | Yes | No | exact | Observed matched delay | 673 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7/3 | 2024-10-08 | 2024-10 | 2025-07-09 | 2025-07 | 274 | 274 | Yes | No | exact | Observed matched delay | 673 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3/9 | 2024-10-09 | 2024-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 672 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation
TA 413 | 4xx | Government | ta413 | 35/6 | 2024-10-09 | 2024-10 | 2024-12-29 | 2024-12 | 81 | 81 | Yes | No | exact | Observed matched delay | 672 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3/10 | 2024-10-12 | 2024-10 | 2025-07-16 | 2025-07 | 277 | 277 | Yes | No | exact | Observed matched delay | 669 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/10 | 2024-10-12 | 2024-10 | 2024-12-22 | 2024-12 | 71 | 71 | Yes | No | exact | Observed matched delay | 669 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7/4 | 2024-10-12 | 2024-10 | 2025-02-20 | 2025-02 | 131 | 131 | Yes | No | exact | Observed matched delay | 669 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 27/6 | 2024-10-14 | 2024-10 | 2025-11-13 | 2025-11 | 395 | 395 | Yes | No | exact | Observed matched delay | 667 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37/0 | 2024-10-14 | 2024-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 667 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation
TA 413 | 4xx | Government | ta413 | 34/2 | 2024-10-16 | 2024-10 | 2025-01-10 | 2025-01 | 86 | 86 | Yes | No | exact | Observed matched delay | 665 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/7 | 2024-10-16 | 2024-10 | 2025-08-22 | 2025-08 | 310 | 310 | Yes | No | exact | Observed matched delay | 665 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/7 | 2024-10-17 | 2024-10 | 2024-12-13 | 2024-12 | 57 | 57 | Yes | No | exact | Observed matched delay | 664 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/0 | 2024-10-18 | 2024-10 | 2025-08-13 | 2025-08 | 299 | 299 | Yes | No | exact | Observed matched delay | 663 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3/7 | 2024-10-19 | 2024-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 662 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation
TA 413 | 4xx | Government | ta413 | 6/5 | 2024-10-19 | 2024-10 | 2025-08-02 | 2025-08 | 287 | 287 | Yes | No | exact | Observed matched delay | 662 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37A/4 | 2024-10-21 | 2024-10 | 2025-02-25 | 2025-02 | 127 | 127 | Yes | No | exact | Observed matched delay | 660 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3/6 | 2024-10-22 | 2024-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 659 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation
TA 413 | 4xx | Government | ta413 | 33/5 | 2024-10-22 | 2024-10 | 2025-01-31 | 2025-01 | 101 | 101 | Yes | No | exact | Observed matched delay | 659 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/5 | 2024-10-23 | 2024-10 | 2025-08-20 | 2025-08 | 301 | 301 | Yes | No | exact | Observed matched delay | 658 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29/2 | 2024-10-25 | 2024-10 | 2025-12-12 | 2025-12 | 413 | 413 | Yes | No | exact | Observed matched delay | 656 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/8 | 2024-10-25 | 2024-10 | 2025-02-18 | 2025-02 | 116 | 116 | Yes | No | exact | Observed matched delay | 656 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37A/5 | 2024-10-25 | 2024-10 | 2025-02-24 | 2025-02 | 122 | 122 | Yes | No | exact | Observed matched delay | 656 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/9 | 2024-10-27 | 2024-10 | 2025-01-17 | 2025-01 | 82 | 82 | Yes | No | exact | Observed matched delay | 654 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3/4 | 2024-10-29 | 2024-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 652 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation
TA 413 | 4xx | Government | ta413 | 35/8 | 2024-10-29 | 2024-10 | 2024-12-23 | 2024-12 | 55 | 55 | Yes | No | exact | Observed matched delay | 652 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37A/3 | 2024-10-30 | 2024-10 | 2025-02-16 | 2025-02 | 109 | 109 | Yes | No | exact | Observed matched delay | 651 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29A/0 | 2024-11-07 | 2024-11 | 2025-10-06 | 2025-10 | 333 | 333 | Yes | No | exact | Observed matched delay | 643 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37A/2 | 2024-11-08 | 2024-11 | 2025-01-29 | 2025-01 | 82 | 82 | Yes | No | exact | Observed matched delay | 642 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 6/8 | 2024-11-08 | 2024-11 | 2025-08-29 | 2025-08 | 294 | 294 | Yes | No | exact | Observed matched delay | 642 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/11 | 2024-11-09 | 2024-11 | 2024-12-24 | 2024-12 | 45 | 45 | Yes | No | exact | Observed matched delay | 641 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/9 | 2024-11-11 | 2024-11 | 2025-08-18 | 2025-08 | 280 | 280 | Yes | No | exact | Observed matched delay | 639 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 18/0 | 2024-11-12 | 2024-11 | 2025-09-07 | 2025-09 | 299 | 299 | Yes | No | exact | Observed matched delay | 638 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37A/1 | 2024-11-12 | 2024-11 | 2025-02-08 | 2025-02 | 88 | 88 | Yes | No | exact | Observed matched delay | 638 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 18/1 | 2024-11-16 | 2024-11 | 2025-09-16 | 2025-09 | 304 | 304 | Yes | No | exact | Observed matched delay | 634 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37/4 | 2024-11-17 | 2024-11 | 2025-01-11 | 2025-01 | 55 | 55 | Yes | No | exact | Observed matched delay | 633 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 18/2 | 2024-11-19 | 2024-11 | 2025-09-21 | 2025-09 | 306 | 306 | Yes | No | exact | Observed matched delay | 631 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 36/0 | 2024-11-20 | 2024-11 | 2026-01-22 | 2026-01 | 428 | 428 | Yes | No | exact | Observed matched delay | 630 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/8 | 2024-11-20 | 2024-11 | 2025-03-19 | 2025-03 | 119 | 119 | Yes | No | exact | Observed matched delay | 630 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37/5 | 2024-11-21 | 2024-11 | 2025-01-22 | 2025-01 | 62 | 62 | Yes | No | exact | Observed matched delay | 629 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/9 | 2024-11-21 | 2024-11 | 2025-02-15 | 2025-02 | 86 | 86 | Yes | No | exact | Observed matched delay | 629 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7A/0 | 2024-11-22 | 2024-11 | 2025-01-22 | 2025-01 | 61 | 61 | Yes | No | exact | Observed matched delay | 628 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 34/0 | 2024-11-23 | 2024-11 | 2025-01-17 | 2025-01 | 55 | 55 | Yes | No | exact | Observed matched delay | 627 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/10 | 2024-11-23 | 2024-11 | 2025-02-18 | 2025-02 | 87 | 87 | Yes | No | exact | Observed matched delay | 627 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 18/3 | 2024-11-24 | 2024-11 | 2025-09-26 | 2025-09 | 306 | 306 | Yes | No | exact | Observed matched delay | 626 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/7 | 2024-11-26 | 2024-11 | 2025-03-12 | 2025-03 | 106 | 106 | Yes | No | exact | Observed matched delay | 624 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/4 | 2024-11-27 | 2024-11 | 2025-01-14 | 2025-01 | 48 | 48 | Yes | No | exact | Observed matched delay | 623 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37A/0 | 2024-11-27 | 2024-11 | 2025-02-28 | 2025-02 | 93 | 93 | Yes | No | exact | Observed matched delay | 623 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 18/4 | 2024-11-29 | 2024-11 | 2025-10-01 | 2025-10 | 306 | 306 | Yes | No | exact | Observed matched delay | 621 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/6 | 2024-11-29 | 2024-11 | 2025-01-29 | 2025-01 | 61 | 61 | Yes | No | exact | Observed matched delay | 621 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/5 | 2024-11-30 | 2024-11 | 2025-02-11 | 2025-02 | 73 | 73 | Yes | No | exact | Observed matched delay | 620 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7/2 | 2024-12-01 | 2024-12 | 2024-12-27 | 2024-12 | 26 | 26 | Yes | No | exact | Observed matched delay | 619 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 18/6 | 2024-12-04 | 2024-12 | 2025-10-11 | 2025-10 | 311 | 311 | Yes | No | exact | Observed matched delay | 616 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/0 | 2024-12-04 | 2024-12 | 2025-03-29 | 2025-03 | 115 | 115 | Yes | No | exact | Observed matched delay | 616 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/0 | 2024-12-06 | 2024-12 | 2025-02-09 | 2025-02 | 65 | 65 | Yes | No | exact | Observed matched delay | 614 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/3 | 2024-12-06 | 2024-12 | 2025-01-24 | 2025-01 | 49 | 49 | Yes | No | exact | Observed matched delay | 614 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 18/5 | 2024-12-07 | 2024-12 | 2025-10-07 | 2025-10 | 304 | 304 | Yes | No | exact | Observed matched delay | 613 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 37A/6 | 2024-12-08 | 2024-12 | 2025-02-24 | 2025-02 | 78 | 78 | Yes | No | exact | Observed matched delay | 612 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/4 | 2024-12-08 | 2024-12 | 2025-02-05 | 2025-02 | 59 | 59 | Yes | No | exact | Observed matched delay | 612 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/3 | 2024-12-10 | 2024-12 | 2025-10-12 | 2025-10 | 306 | 306 | Yes | No | exact | Observed matched delay | 610 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/2 | 2024-12-12 | 2024-12 | 2025-03-07 | 2025-03 | 85 | 85 | Yes | No | exact | Observed matched delay | 608 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/2 | 2024-12-12 | 2024-12 | 2025-03-26 | 2025-03 | 104 | 104 | Yes | No | exact | Observed matched delay | 608 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 38/1 | 2024-12-13 | 2024-12 | 2025-03-01 | 2025-03 | 78 | 78 | Yes | No | exact | Observed matched delay | 607 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/3 | 2024-12-14 | 2024-12 | 2025-03-31 | 2025-03 | 107 | 107 | Yes | No | exact | Observed matched delay | 606 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/1 | 2024-12-15 | 2024-12 | 2025-03-22 | 2025-03 | 97 | 97 | Yes | No | exact | Observed matched delay | 605 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7/5 | 2024-12-17 | 2024-12 | 2025-02-11 | 2025-02 | 56 | 56 | Yes | No | exact | Observed matched delay | 603 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/0 | 2024-12-18 | 2024-12 | 2025-09-11 | 2025-09 | 267 | 267 | Yes | No | exact | Observed matched delay | 602 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 17/0 | 2024-12-19 | 2024-12 | 2025-11-16 | 2025-11 | 332 | 332 | Yes | No | exact | Observed matched delay | 601 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/7 | 2024-12-19 | 2024-12 | 2025-08-14 | 2025-08 | 238 | 238 | Yes | No | exact | Observed matched delay | 601 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/0 | 2024-12-21 | 2024-12 | 2025-03-09 | 2025-03 | 78 | 78 | Yes | No | exact | Observed matched delay | 599 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/2 | 2024-12-21 | 2024-12 | 2025-03-12 | 2025-03 | 81 | 81 | Yes | No | exact | Observed matched delay | 599 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/6 | 2024-12-21 | 2024-12 | 2025-04-14 | 2025-04 | 114 | 114 | Yes | No | exact | Observed matched delay | 599 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/2 | 2024-12-22 | 2024-12 | 2025-09-24 | 2025-09 | 276 | 276 | Yes | No | exact | Observed matched delay | 598 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/4 | 2024-12-23 | 2024-12 | 2025-03-21 | 2025-03 | 88 | 88 | Yes | No | exact | Observed matched delay | 597 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/8 | 2024-12-25 | 2024-12 | 2025-10-10 | 2025-10 | 289 | 289 | Yes | No | exact | Observed matched delay | 595 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 41/1 | 2024-12-27 | 2024-12 | 2025-09-24 | 2025-09 | 271 | 271 | Yes | No | exact | Observed matched delay | 593 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 16/0 | 2024-12-28 | 2024-12 | 2026-06-02 | 2026-06 | 521 | 521 | Yes | No | exact | Observed matched delay | 592 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/4 | 2024-12-29 | 2024-12 | 2025-09-09 | 2025-09 | 254 | 254 | Yes | No | exact | Observed matched delay | 591 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/3 | 2024-12-29 | 2024-12 | 2025-03-20 | 2025-03 | 81 | 81 | Yes | No | exact | Observed matched delay | 591 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/5 | 2024-12-29 | 2024-12 | 2025-04-05 | 2025-04 | 97 | 97 | Yes | No | exact | Observed matched delay | 591 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 7/6 | 2024-12-30 | 2024-12 | 2025-01-31 | 2025-01 | 32 | 32 | Yes | No | exact | Observed matched delay | 590 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/12 | 2024-12-31 | 2024-12 | 2025-11-29 | 2025-11 | 333 | 333 | Yes | No | exact | Observed matched delay | 589 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/4 | 2024-12-31 | 2024-12 | 2025-04-09 | 2025-04 | 99 | 99 | Yes | No | exact | Observed matched delay | 589 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/5 | 2025-01-03 | 2025-01 | 2025-12-21 | 2025-12 | 352 | 352 | Yes | No | exact | Observed matched delay | 586 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 42/0 | 2025-01-03 | 2025-01 | 2025-07-21 | 2025-07 | 199 | 199 | Yes | No | exact | Observed matched delay | 586 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/5 | 2025-01-05 | 2025-01 | 2025-03-14 | 2025-03 | 68 | 68 | Yes | No | exact | Observed matched delay | 584 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/9 | 2025-01-05 | 2025-01 | 2025-08-01 | 2025-08 | 208 | 208 | Yes | No | exact | Observed matched delay | 584 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/3 | 2025-01-06 | 2025-01 | 2025-02-14 | 2025-02 | 39 | 39 | Yes | No | exact | Observed matched delay | 583 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/6 | 2025-01-07 | 2025-01 | 2025-08-29 | 2025-08 | 234 | 234 | Yes | No | exact | Observed matched delay | 582 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 42/1 | 2025-01-08 | 2025-01 | 2025-08-02 | 2025-08 | 206 | 206 | Yes | No | exact | Observed matched delay | 581 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/6 | 2025-01-09 | 2025-01 | 2025-04-09 | 2025-04 | 90 | 90 | Yes | No | exact | Observed matched delay | 580 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/10 | 2025-01-09 | 2025-01 | 2025-09-30 | 2025-09 | 264 | 264 | Yes | No | exact | Observed matched delay | 580 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/7 | 2025-01-10 | 2025-01 | 2025-09-09 | 2025-09 | 242 | 242 | Yes | No | exact | Observed matched delay | 579 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/8 | 2025-01-13 | 2025-01 | 2025-09-14 | 2025-09 | 244 | 244 | Yes | No | exact | Observed matched delay | 576 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/11 | 2025-01-13 | 2025-01 | 2025-09-21 | 2025-09 | 251 | 251 | Yes | No | exact | Observed matched delay | 576 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 42/2 | 2025-01-13 | 2025-01 | 2025-08-07 | 2025-08 | 206 | 206 | Yes | No | exact | Observed matched delay | 576 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/0 | 2025-01-13 | 2025-01 | 2025-02-09 | 2025-02 | 27 | 27 | Yes | No | exact | Observed matched delay | 576 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 22/0 | 2025-01-15 | 2025-01 | 2025-10-28 | 2025-10 | 286 | 286 | Yes | No | exact | Observed matched delay | 574 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/9 | 2025-01-17 | 2025-01 | 2025-08-12 | 2025-08 | 207 | 207 | Yes | No | exact | Observed matched delay | 572 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/7 | 2025-01-17 | 2025-01 | 2025-03-07 | 2025-03 | 49 | 49 | Yes | No | exact | Observed matched delay | 572 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 41/0 | 2025-01-19 | 2025-01 | 2025-10-08 | 2025-10 | 262 | 262 | Yes | No | exact | Observed matched delay | 570 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40A/0 | 2025-01-20 | 2025-01 | 2025-09-04 | 2025-09 | 227 | 227 | Yes | No | exact | Observed matched delay | 569 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 10/0 | 2025-01-21 | 2025-01 | 2025-10-02 | 2025-10 | 254 | 254 | Yes | No | exact | Observed matched delay | 568 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 30/10 | 2025-01-21 | 2025-01 | 2025-07-18 | 2025-07 | 178 | 178 | Yes | No | exact | Observed matched delay | 568 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43/7 | 2025-01-21 | 2025-01 | 2025-09-24 | 2025-09 | 246 | 246 | Yes | No | exact | Observed matched delay | 568 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 23/0 | 2025-01-22 | 2025-01 | 2025-10-12 | 2025-10 | 263 | 263 | Yes | No | exact | Observed matched delay | 567 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43/3 | 2025-01-23 | 2025-01 | 2025-08-23 | 2025-08 | 212 | 212 | Yes | No | exact | Observed matched delay | 566 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/8 | 2025-01-24 | 2025-01 | 2024-03-26 | 2024-03 | -304 |  | Yes | Yes | exact | Negative delay excluded | 565 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/4 | 2025-01-24 | 2025-01 | 2025-02-20 | 2025-02 | 27 | 27 | Yes | No | exact | Observed matched delay | 565 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43/0 | 2025-01-25 | 2025-01 | 2026-02-01 | 2026-02 | 372 | 372 | Yes | No | exact | Observed matched delay | 564 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43/8 | 2025-01-25 | 2025-01 | 2025-09-14 | 2025-09 | 232 | 232 | Yes | No | exact | Observed matched delay | 564 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/1 | 2025-01-27 | 2025-01 | 2025-11-27 | 2025-11 | 304 | 304 | Yes | No | exact | Observed matched delay | 562 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43/4 | 2025-01-28 | 2025-01 | 2025-09-03 | 2025-09 | 218 | 218 | Yes | No | exact | Observed matched delay | 561 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 23A/0 | 2025-01-30 | 2025-01 | 2025-11-14 | 2025-11 | 288 | 288 | Yes | No | exact | Observed matched delay | 559 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32/1 | 2025-01-31 | 2025-01 | 2025-07-05 | 2025-07 | 155 | 155 | Yes | No | exact | Observed matched delay | 558 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/9 | 2025-01-31 | 2025-01 | 2025-03-25 | 2025-03 | 53 | 53 | Yes | No | exact | Observed matched delay | 558 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 42A/0 | 2025-01-31 | 2025-01 | 2025-08-12 | 2025-08 | 193 | 193 | Yes | No | exact | Observed matched delay | 558 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/2 | 2025-02-01 | 2025-02 | 2025-08-04 | 2025-08 | 184 | 184 | Yes | No | exact | Observed matched delay | 557 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43/6 | 2025-02-02 | 2025-02 | 2025-09-08 | 2025-09 | 218 | 218 | Yes | No | exact | Observed matched delay | 556 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 18/7 | 2025-02-04 | 2025-02 | 2025-10-16 | 2025-10 | 254 | 254 | Yes | No | exact | Observed matched delay | 554 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32/2 | 2025-02-04 | 2025-02 | 2025-07-18 | 2025-07 | 164 | 164 | Yes | No | exact | Observed matched delay | 554 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 44/0 | 2025-02-04 | 2025-02 | 2025-09-20 | 2025-09 | 228 | 228 | Yes | No | exact | Observed matched delay | 554 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43/1 | 2025-02-05 | 2025-02 | 2025-12-22 | 2025-12 | 320 | 320 | Yes | No | exact | Observed matched delay | 553 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/4 | 2025-02-07 | 2025-02 | 2025-08-22 | 2025-08 | 196 | 196 | Yes | No | exact | Observed matched delay | 551 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43/2 | 2025-02-08 | 2025-02 | 2025-08-20 | 2025-08 | 193 | 193 | Yes | No | exact | Observed matched delay | 550 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32/0 | 2025-02-09 | 2025-02 | 2025-09-04 | 2025-09 | 207 | 207 | Yes | No | exact | Observed matched delay | 549 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 43A/0 | 2025-02-09 | 2025-02 | 2025-11-30 | 2025-11 | 294 | 294 | Yes | No | exact | Observed matched delay | 549 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 31/5 | 2025-02-10 | 2025-02 | 2025-08-23 | 2025-08 | 194 | 194 | Yes | No | exact | Observed matched delay | 548 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 13/0 | 2025-02-11 | 2025-02 | 2025-12-18 | 2025-12 | 310 | 310 | Yes | No | exact | Observed matched delay | 547 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/10 | 2025-02-11 | 2025-02 | 2025-03-31 | 2025-03 | 48 | 48 | Yes | No | exact | Observed matched delay | 547 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 20/2 | 2025-02-12 | 2025-02 | 2025-09-26 | 2025-09 | 226 | 226 | Yes | No | exact | Observed matched delay | 546 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8/11 | 2025-02-13 | 2025-02 | 2025-07-15 | 2025-07 | 152 | 152 | Yes | No | exact | Observed matched delay | 545 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 20/1 | 2025-02-16 | 2025-02 | 2025-09-19 | 2025-09 | 215 | 215 | Yes | No | exact | Observed matched delay | 542 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 21/5 | 2025-02-16 | 2025-02 | 2025-11-07 | 2025-11 | 264 | 264 | Yes | No | exact | Observed matched delay | 542 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32/7 | 2025-02-17 | 2025-02 | 2025-07-26 | 2025-07 | 159 | 159 | Yes | No | exact | Observed matched delay | 541 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 13A/0 | 2025-02-18 | 2025-02 | 2026-01-01 | 2026-01 | 317 | 317 | Yes | No | exact | Observed matched delay | 540 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32A/0 | 2025-02-18 | 2025-02 | 2025-08-01 | 2025-08 | 164 | 164 | Yes | No | exact | Observed matched delay | 540 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/6 | 2025-02-19 | 2025-02 | 2025-08-20 | 2025-08 | 182 | 182 | Yes | No | exact | Observed matched delay | 539 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/2 | 2025-02-20 | 2025-02 | 2025-08-09 | 2025-08 | 170 | 170 | Yes | No | exact | Observed matched delay | 538 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 21/4 | 2025-02-22 | 2025-02 | 2025-11-13 | 2025-11 | 264 | 264 | Yes | No | exact | Observed matched delay | 536 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32A/1 | 2025-02-22 | 2025-02 | 2025-08-14 | 2025-08 | 173 | 173 | Yes | No | exact | Observed matched delay | 536 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 29/0 | 2025-02-23 | 2025-02 | 2025-10-08 | 2025-10 | 227 | 227 | Yes | No | exact | Observed matched delay | 535 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 39/11 | 2025-02-24 | 2025-02 | 2025-03-30 | 2025-03 | 34 | 34 | Yes | No | exact | Observed matched delay | 534 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 27/0 | 2025-02-25 | 2025-02 | 2025-11-08 | 2025-11 | 256 | 256 | Yes | No | exact | Observed matched delay | 533 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/9 | 2025-02-25 | 2025-02 | 2025-11-06 | 2025-11 | 254 | 254 | Yes | No | exact | Observed matched delay | 533 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 28/0 | 2025-02-26 | 2025-02 | 2025-10-31 | 2025-10 | 247 | 247 | Yes | No | exact | Observed matched delay | 532 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/7 | 2025-02-26 | 2025-02 | 2025-08-23 | 2025-08 | 178 | 178 | Yes | No | exact | Observed matched delay | 532 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 24/0 | 2025-02-27 | 2025-02 | 2025-11-13 | 2025-11 | 259 | 259 | Yes | No | exact | Observed matched delay | 531 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 44/1 | 2025-03-01 | 2025-03 | 2025-08-25 | 2025-08 | 177 | 177 | Yes | No | exact | Observed matched delay | 529 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 26/0 | 2025-03-05 | 2025-03 | 2025-10-10 | 2025-10 | 219 | 219 | Yes | No | exact | Observed matched delay | 525 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/8 | 2025-03-05 | 2025-03 | 2025-12-04 | 2025-12 | 274 | 274 | Yes | No | exact | Observed matched delay | 525 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 15/0 | 2025-03-06 | 2025-03 | 2025-10-05 | 2025-10 | 213 | 213 | Yes | No | exact | Observed matched delay | 524 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 44/2 | 2025-03-06 | 2025-03 | 2025-09-04 | 2025-09 | 182 | 182 | Yes | No | exact | Observed matched delay | 524 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 25/0 | 2025-03-08 | 2025-03 | 2025-11-12 | 2025-11 | 249 | 249 | Yes | No | exact | Observed matched delay | 522 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/0 | 2025-03-08 | 2025-03 | 2025-04-18 | 2025-04 | 41 | 41 | Yes | No | exact | Observed matched delay | 522 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 44/4 | 2025-03-12 | 2025-03 | 2025-09-16 | 2025-09 | 188 | 188 | Yes | No | exact | Observed matched delay | 518 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 44/3 | 2025-03-13 | 2025-03 | 2025-09-10 | 2025-09 | 181 | 181 | Yes | No | exact | Observed matched delay | 517 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/0 | 2025-03-16 | 2025-03 | 2025-09-19 | 2025-09 | 187 | 187 | Yes | No | exact | Observed matched delay | 514 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 44/5 | 2025-03-17 | 2025-03 | 2025-09-20 | 2025-09 | 187 | 187 | Yes | No | exact | Observed matched delay | 513 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 2A/2 | 2025-03-23 | 2025-03 | 2025-08-28 | 2025-08 | 158 | 158 | Yes | No | exact | Observed matched delay | 507 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3B/2 | 2025-03-23 | 2025-03 | 2025-09-26 | 2025-09 | 187 | 187 | Yes | No | exact | Observed matched delay | 507 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5/1 | 2025-03-23 | 2025-03 | 2025-09-13 | 2025-09 | 174 | 174 | Yes | No | exact | Observed matched delay | 507 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3B/1 | 2025-03-26 | 2025-03 | 2025-10-09 | 2025-10 | 197 | 197 | Yes | No | exact | Observed matched delay | 504 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 2A/3 | 2025-03-27 | 2025-03 | 2025-09-03 | 2025-09 | 160 | 160 | Yes | No | exact | Observed matched delay | 503 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 2A/4 | 2025-03-30 | 2025-03 | 2025-09-09 | 2025-09 | 163 | 163 | Yes | No | exact | Observed matched delay | 500 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3B/0 | 2025-03-30 | 2025-03 | 2025-09-25 | 2025-09 | 179 | 179 | Yes | No | exact | Observed matched delay | 500 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 40/1 | 2025-03-30 | 2025-03 | 2025-07-06 | 2025-07 | 98 | 98 | Yes | No | exact | Observed matched delay | 500 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 5A/0 | 2025-04-01 | 2025-04 | 2025-08-22 | 2025-08 | 143 | 143 | Yes | No | exact | Observed matched delay | 498 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3A/6 | 2025-04-03 | 2025-04 | 2025-09-16 | 2025-09 | 166 | 166 | Yes | No | exact | Observed matched delay | 496 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 2A/5 | 2025-04-05 | 2025-04 | 2025-09-16 | 2025-09 | 164 | 164 | Yes | No | exact | Observed matched delay | 494 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32/5 | 2025-04-08 | 2025-04 | 2025-07-16 | 2025-07 | 99 | 99 | Yes | No | exact | Observed matched delay | 491 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3A/1 | 2025-04-08 | 2025-04 | 2025-09-03 | 2025-09 | 148 | 148 | Yes | No | exact | Observed matched delay | 491 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3A/5 | 2025-04-08 | 2025-04 | 2025-09-07 | 2025-09 | 152 | 152 | Yes | No | exact | Observed matched delay | 491 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3A/4 | 2025-04-10 | 2025-04 | 2025-10-01 | 2025-10 | 174 | 174 | Yes | No | exact | Observed matched delay | 489 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 32/6 | 2025-04-11 | 2025-04 | 2025-07-06 | 2025-07 | 86 | 86 | Yes | No | exact | Observed matched delay | 488 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/3 | 2025-04-12 | 2025-04 | 2026-01-07 | 2026-01 | 270 | 270 | Yes | No | exact | Observed matched delay | 487 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3A/3 | 2025-04-12 | 2025-04 | 2025-09-20 | 2025-09 | 161 | 161 | Yes | No | exact | Observed matched delay | 487 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/1 | 2025-04-14 | 2025-04 | 2025-08-25 | 2025-08 | 133 | 133 | Yes | No | exact | Observed matched delay | 485 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/2 | 2025-04-15 | 2025-04 | 2025-08-01 | 2025-08 | 108 | 108 | Yes | No | exact | Observed matched delay | 484 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3A/2 | 2025-04-15 | 2025-04 | 2025-09-12 | 2025-09 | 150 | 150 | Yes | No | exact | Observed matched delay | 484 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 14/0 | 2025-04-16 | 2025-04 | 2025-11-30 | 2025-11 | 228 | 228 | Yes | No | exact | Observed matched delay | 483 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 33/0 | 2025-04-17 | 2025-04 | 2025-09-03 | 2025-09 | 139 | 139 | Yes | No | exact | Observed matched delay | 482 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3A/0 | 2025-04-18 | 2025-04 | 2025-10-11 | 2025-10 | 176 | 176 | Yes | No | exact | Observed matched delay | 481 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 3B/3 | 2025-04-19 | 2025-04 | 2025-10-27 | 2025-10 | 191 | 191 | Yes | No | exact | Observed matched delay | 480 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 21/3 | 2025-04-22 | 2025-04 | 2025-11-21 | 2025-11 | 213 | 213 | Yes | No | exact | Observed matched delay | 477 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 2A/6 | 2025-04-23 | 2025-04 | 2025-09-24 | 2025-09 | 154 | 154 | Yes | No | exact | Observed matched delay | 476 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 21/2 | 2025-04-24 | 2025-04 | 2025-11-06 | 2025-11 | 196 | 196 | Yes | No | exact | Observed matched delay | 475 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 4/0 | 2025-04-25 | 2025-04 | 2025-09-25 | 2025-09 | 153 | 153 | Yes | No | exact | Observed matched delay | 474 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 8A/0 | 2025-04-25 | 2025-04 | 2025-08-07 | 2025-08 | 104 | 104 | Yes | No | exact | Observed matched delay | 474 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 21/1 | 2025-04-29 | 2025-04 | 2025-10-24 | 2025-10 | 178 | 178 | Yes | No | exact | Observed matched delay | 470 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 35/10 | 2025-05-02 | 2025-05 | 2026-02-07 | 2026-02 | 281 | 281 | Yes | No | exact | Observed matched delay | 467 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 9/0 | 2025-05-03 | 2025-05 | 2025-08-30 | 2025-08 | 119 | 119 | Yes | No | exact | Observed matched delay | 466 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 45/0 | 2025-05-05 | 2025-05 | 2025-09-28 | 2025-09 | 146 | 146 | Yes | No | exact | Observed matched delay | 464 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 46/0 | 2025-05-07 | 2025-05 | 2025-09-30 | 2025-09 | 146 | 146 | Yes | No | exact | Observed matched delay | 462 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 20/6 | 2025-05-09 | 2025-05 | 2025-10-17 | 2025-10 | 161 | 161 | Yes | No | exact | Observed matched delay | 460 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 20/5 | 2025-05-13 | 2025-05 | 2025-10-28 | 2025-10 | 168 | 168 | Yes | No | exact | Observed matched delay | 456 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 21/0 | 2025-05-13 | 2025-05 | 2025-10-20 | 2025-10 | 160 | 160 | Yes | No | exact | Observed matched delay | 456 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 20/4 | 2025-05-18 | 2025-05 | 2025-11-01 | 2025-11 | 167 | 167 | Yes | No | exact | Observed matched delay | 451 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 20/3 | 2025-05-22 | 2025-05 | 2025-10-30 | 2025-10 | 161 | 161 | Yes | No | exact | Observed matched delay | 447 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 19/0 | 2025-05-26 | 2025-05 | 2025-10-16 | 2025-10 | 143 | 143 | Yes | No | exact | Observed matched delay | 443 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 20/0 | 2025-06-02 | 2025-06 | 2025-10-01 | 2025-10 | 121 | 121 | Yes | No | exact | Observed matched delay | 436 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 11/0 | 2025-06-08 | 2025-06 | 2025-11-13 | 2025-11 | 158 | 158 | Yes | No | exact | Observed matched delay | 430 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 12/0 | 2025-06-14 | 2025-06 | 2025-09-11 | 2025-09 | 89 | 89 | Yes | No | exact | Observed matched delay | 424 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 1/0 | 2025-06-27 | 2025-06 | 2025-08-07 | 2025-08 | 41 | 41 | Yes | No | exact | Observed matched delay | 411 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 2A/1 | 2025-07-05 | 2025-07 | 2025-08-21 | 2025-08 | 47 | 47 | Yes | No | exact | Observed matched delay | 403 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 2A/0 | 2025-07-14 | 2025-07 | 2026-01-01 | 2026-01 | 171 | 171 | Yes | No | exact | Observed matched delay | 394 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 36B/0-N | 2026-01-23 | 2026-01 | 2026-08-02 | 2026-08 | 191 | 191 | Yes | No | exact | Observed matched delay | 201 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 413 | 4xx | Government | ta413 | 36C/0-N | 2026-02-08 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 185 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation
TA 413 | 4xx | Government | ta413 | 37/0-N | 2026-03-05 | 2026-03 | 2026-07-12 | 2026-07 | 129 | 129 | Yes | No | exact | Observed matched delay | 160 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 413 - DPR - 2026-08-11.xlsx | Foundation | TA 413 - DPR - 2026-08-11.xlsx | Erection
TA 414 | 4xx | Government | ta414 | 241/2 | 2024-05-25 | 2024-05 | 2026-01-14 | 2026-01 | 599 | 599 | Yes | No | exact | Observed matched delay | 809 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 241/0 | 2024-05-30 | 2024-05 | 2025-09-02 | 2025-09 | 460 | 460 | Yes | No | exact | Observed matched delay | 804 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 118/0 | 2024-10-31 | 2024-10 | 2025-05-31 | 2025-05 | 212 | 212 | Yes | No | exact | Observed matched delay | 650 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 120/3 | 2024-11-12 | 2024-11 | 2025-06-09 | 2025-06 | 209 | 209 | Yes | No | exact | Observed matched delay | 638 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/5 | 2024-11-19 | 2024-11 | 2026-01-30 | 2026-01 | 437 | 437 | Yes | No | exact | Observed matched delay | 631 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 120/2 | 2024-11-22 | 2024-11 | 2025-06-02 | 2025-06 | 192 | 192 | Yes | No | exact | Observed matched delay | 628 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/4 | 2024-11-29 | 2024-11 | 2024-03-27 | 2024-03 | -247 |  | Yes | Yes | exact | Negative delay excluded | 621 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/2 | 2024-12-07 | 2024-12 | 2025-12-30 | 2025-12 | 388 | 388 | Yes | No | exact | Observed matched delay | 613 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 183/1 | 2024-12-09 | 2024-12 | 2026-02-23 | 2026-02 | 441 | 441 | Yes | No | exact | Observed matched delay | 611 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 119/0 | 2024-12-16 | 2024-12 | 2025-08-10 | 2025-08 | 237 | 237 | Yes | No | exact | Observed matched delay | 604 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/3 | 2024-12-21 | 2024-12 | 2026-01-19 | 2026-01 | 394 | 394 | Yes | No | exact | Observed matched delay | 599 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 120/0 | 2024-12-22 | 2024-12 | 2026-01-21 | 2026-01 | 395 | 395 | Yes | No | exact | Observed matched delay | 598 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 120/5 | 2024-12-22 | 2024-12 | 2025-12-08 | 2025-12 | 351 | 351 | Yes | No | exact | Observed matched delay | 598 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 244/6 | 2024-12-23 | 2024-12 | 2026-02-25 | 2026-02 | 429 | 429 | Yes | No | exact | Observed matched delay | 597 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 145/4 | 2024-12-27 | 2024-12 | 2026-01-09 | 2026-01 | 378 | 378 | Yes | No | exact | Observed matched delay | 593 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 249/1 | 2024-12-27 | 2024-12 | 2026-06-25 | 2026-06 | 545 | 545 | Yes | No | exact | Observed matched delay | 593 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 119/2 | 2024-12-28 | 2024-12 | 2025-08-07 | 2025-08 | 222 | 222 | Yes | No | exact | Observed matched delay | 592 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 119/3 | 2024-12-30 | 2024-12 | 2025-07-26 | 2025-07 | 208 | 208 | Yes | No | exact | Observed matched delay | 590 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/6 | 2024-12-31 | 2024-12 | 2026-02-13 | 2026-02 | 409 | 409 | Yes | No | exact | Observed matched delay | 589 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 249/0 | 2025-01-02 | 2025-01 | 2026-06-13 | 2026-06 | 527 | 527 | Yes | No | exact | Observed matched delay | 587 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 249/2 | 2025-01-03 | 2025-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 586 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 120/6 | 2025-01-04 | 2025-01 | 2025-06-16 | 2025-06 | 163 | 163 | Yes | No | exact | Observed matched delay | 585 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 126/3 | 2025-01-08 | 2025-01 | 2026-03-27 | 2026-03 | 443 | 443 | Yes | No | exact | Observed matched delay | 581 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/1 | 2025-01-10 | 2025-01 | 2026-03-29 | 2026-03 | 443 | 443 | Yes | No | exact | Observed matched delay | 579 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 137/2 | 2025-01-10 | 2025-01 | 2025-12-28 | 2025-12 | 352 | 352 | Yes | No | exact | Observed matched delay | 579 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/7 | 2025-01-12 | 2025-01 | 2025-09-15 | 2025-09 | 246 | 246 | Yes | No | exact | Observed matched delay | 577 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 145/3 | 2025-01-13 | 2025-01 | 2026-01-15 | 2026-01 | 367 | 367 | Yes | No | exact | Observed matched delay | 576 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 120/7 | 2025-01-14 | 2025-01 | 2025-12-28 | 2025-12 | 348 | 348 | Yes | No | exact | Observed matched delay | 575 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 244/5 | 2025-01-16 | 2025-01 | 2025-12-14 | 2025-12 | 332 | 332 | Yes | No | exact | Observed matched delay | 573 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/8 | 2025-01-20 | 2025-01 | 2026-05-07 | 2026-05 | 472 | 472 | Yes | No | exact | Observed matched delay | 569 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 250/0 | 2025-01-20 | 2025-01 | 2026-06-05 | 2026-06 | 501 | 501 | Yes | No | exact | Observed matched delay | 569 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 252/3 | 2025-01-22 | 2025-01 | 2026-04-14 | 2026-04 | 447 | 447 | Yes | No | exact | Observed matched delay | 567 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 136/1 | 2025-01-24 | 2025-01 | 2025-12-20 | 2025-12 | 330 | 330 | Yes | No | exact | Observed matched delay | 565 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 145/2 | 2025-01-26 | 2025-01 | 2026-04-24 | 2026-04 | 453 | 453 | Yes | No | exact | Observed matched delay | 563 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 250A/2 | 2025-01-28 | 2025-01 | 2026-01-04 | 2026-01 | 341 | 341 | Yes | No | exact | Observed matched delay | 561 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 252/0 | 2025-01-31 | 2025-01 | 2026-02-05 | 2026-02 | 370 | 370 | Yes | No | exact | Observed matched delay | 558 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 248/2 | 2025-02-03 | 2025-02 | 2025-09-11 | 2025-09 | 220 | 220 | Yes | No | exact | Observed matched delay | 555 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/10 | 2025-02-04 | 2025-02 | 2025-09-08 | 2025-09 | 216 | 216 | Yes | No | exact | Observed matched delay | 554 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 141/4 | 2025-02-04 | 2025-02 | 2026-01-29 | 2026-01 | 359 | 359 | Yes | No | exact | Observed matched delay | 554 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 241/4 | 2025-02-04 | 2025-02 | 2025-12-06 | 2025-12 | 305 | 305 | Yes | No | exact | Observed matched delay | 554 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 124/1 | 2025-02-06 | 2025-02 | 2026-04-24 | 2026-04 | 442 | 442 | Yes | No | exact | Observed matched delay | 552 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 137/1 | 2025-02-07 | 2025-02 | 2026-01-22 | 2026-01 | 349 | 349 | Yes | No | exact | Observed matched delay | 551 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 141/3 | 2025-02-08 | 2025-02 | 2026-01-04 | 2026-01 | 330 | 330 | Yes | No | exact | Observed matched delay | 550 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 145/7 | 2025-02-08 | 2025-02 | 2026-01-19 | 2026-01 | 345 | 345 | Yes | No | exact | Observed matched delay | 550 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/9 | 2025-02-11 | 2025-02 | 2026-05-16 | 2026-05 | 459 | 459 | Yes | No | exact | Observed matched delay | 547 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 126/1 | 2025-02-13 | 2025-02 | 2025-12-30 | 2025-12 | 320 | 320 | Yes | No | exact | Observed matched delay | 545 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 141/5 | 2025-02-13 | 2025-02 | 2026-01-09 | 2026-01 | 330 | 330 | Yes | No | exact | Observed matched delay | 545 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 243/3 | 2025-02-13 | 2025-02 | 2026-05-29 | 2026-05 | 470 | 470 | Yes | No | exact | Observed matched delay | 545 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 248/1 | 2025-02-13 | 2025-02 | 2025-12-26 | 2025-12 | 316 | 316 | Yes | No | exact | Observed matched delay | 545 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 137/0 | 2025-02-14 | 2025-02 | 2026-01-04 | 2026-01 | 324 | 324 | Yes | No | exact | Observed matched delay | 544 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 124/0 | 2025-02-19 | 2025-02 | 2026-04-08 | 2026-04 | 413 | 413 | Yes | No | exact | Observed matched delay | 539 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 243/2 | 2025-02-21 | 2025-02 | 2025-12-19 | 2025-12 | 301 | 301 | Yes | No | exact | Observed matched delay | 537 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 250/3 | 2025-02-23 | 2025-02 | 2025-12-23 | 2025-12 | 303 | 303 | Yes | No | exact | Observed matched delay | 535 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 126/2 | 2025-02-26 | 2025-02 | 2026-03-14 | 2026-03 | 381 | 381 | Yes | No | exact | Observed matched delay | 532 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 148/0 | 2025-02-27 | 2025-02 | 2026-01-31 | 2026-01 | 338 | 338 | Yes | No | exact | Observed matched delay | 531 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 126/0 | 2025-02-28 | 2025-02 | 2026-01-17 | 2026-01 | 323 | 323 | Yes | No | exact | Observed matched delay | 530 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 244/1 | 2025-03-07 | 2025-03 | 2025-12-04 | 2025-12 | 272 | 272 | Yes | No | exact | Observed matched delay | 523 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 132/0 | 2025-03-08 | 2025-03 | 2025-12-08 | 2025-12 | 275 | 275 | Yes | No | exact | Observed matched delay | 522 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 117/1 | 2025-03-13 | 2025-03 | 2026-01-15 | 2026-01 | 308 | 308 | Yes | No | exact | Observed matched delay | 517 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 117/2 | 2025-03-17 | 2025-03 | 2025-08-19 | 2025-08 | 155 | 155 | Yes | No | exact | Observed matched delay | 513 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 251/0 | 2025-03-20 | 2025-03 | 2026-02-07 | 2026-02 | 324 | 324 | Yes | No | exact | Observed matched delay | 510 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 171/0 | 2025-03-22 | 2025-03 | 2026-04-26 | 2026-04 | 400 | 400 | Yes | No | exact | Observed matched delay | 508 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/0 | 2025-03-23 | 2025-03 | 2026-02-24 | 2026-02 | 338 | 338 | Yes | No | exact | Observed matched delay | 507 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 180/3 | 2025-03-23 | 2025-03 | 2025-12-29 | 2025-12 | 281 | 281 | Yes | No | exact | Observed matched delay | 507 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 172/0 | 2025-03-26 | 2025-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 504 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 180/4 | 2025-03-27 | 2025-03 | 2025-12-30 | 2025-12 | 278 | 278 | Yes | No | exact | Observed matched delay | 503 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 172/1 | 2025-04-01 | 2025-04 | 2026-05-07 | 2026-05 | 401 | 401 | Yes | No | exact | Observed matched delay | 498 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 179/3 | 2025-04-01 | 2025-04 | 2026-03-12 | 2026-03 | 345 | 345 | Yes | No | exact | Observed matched delay | 498 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 165/7 | 2025-04-05 | 2025-04 | 2026-05-13 | 2026-05 | 403 | 403 | Yes | No | exact | Observed matched delay | 494 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 180/2 | 2025-04-05 | 2025-04 | 2026-01-23 | 2026-01 | 293 | 293 | Yes | No | exact | Observed matched delay | 494 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 180/5 | 2025-04-06 | 2025-04 | 2025-12-17 | 2025-12 | 255 | 255 | Yes | No | exact | Observed matched delay | 493 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 180/7 | 2025-04-08 | 2025-04 | 2026-01-29 | 2026-01 | 296 | 296 | Yes | No | exact | Observed matched delay | 491 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 179/1 | 2025-04-09 | 2025-04 | 2025-12-08 | 2025-12 | 243 | 243 | Yes | No | exact | Observed matched delay | 490 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 132/1 | 2025-04-10 | 2025-04 | 2026-02-24 | 2026-02 | 320 | 320 | Yes | No | exact | Observed matched delay | 489 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 174/4 | 2025-04-10 | 2025-04 | 2026-03-16 | 2026-03 | 340 | 340 | Yes | No | exact | Observed matched delay | 489 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 174/6 | 2025-04-11 | 2025-04 | 2026-01-23 | 2026-01 | 287 | 287 | Yes | No | exact | Observed matched delay | 488 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 174/5 | 2025-04-15 | 2025-04 | 2026-03-23 | 2026-03 | 342 | 342 | Yes | No | exact | Observed matched delay | 484 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 174/1 | 2025-04-16 | 2025-04 | 2026-02-25 | 2026-02 | 315 | 315 | Yes | No | exact | Observed matched delay | 483 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 176/1 | 2025-04-18 | 2025-04 | 2026-02-15 | 2026-02 | 303 | 303 | Yes | No | exact | Observed matched delay | 481 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 175/0 | 2025-04-23 | 2025-04 | 2026-01-06 | 2026-01 | 258 | 258 | Yes | No | exact | Observed matched delay | 476 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 177/0 | 2025-04-23 | 2025-04 | 2026-01-25 | 2026-01 | 277 | 277 | Yes | No | exact | Observed matched delay | 476 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 176/2 | 2025-04-27 | 2025-04 | 2026-02-09 | 2026-02 | 288 | 288 | Yes | No | exact | Observed matched delay | 472 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 148/4 | 2025-04-28 | 2025-04 | 2025-12-20 | 2025-12 | 236 | 236 | Yes | No | exact | Observed matched delay | 471 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 178/3 | 2025-04-28 | 2025-04 | 2026-02-06 | 2026-02 | 284 | 284 | Yes | No | exact | Observed matched delay | 471 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 165/5 | 2025-05-03 | 2025-05 | 2026-03-20 | 2026-03 | 321 | 321 | Yes | No | exact | Observed matched delay | 466 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 148/2 | 2025-05-12 | 2025-05 | 2025-12-06 | 2025-12 | 208 | 208 | Yes | No | exact | Observed matched delay | 457 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 180/1 | 2025-05-13 | 2025-05 | 2026-02-07 | 2026-02 | 270 | 270 | Yes | No | exact | Observed matched delay | 456 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 165/2 | 2025-05-15 | 2025-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 454 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 252/5 | 2025-05-17 | 2025-05 | 2026-01-02 | 2026-01 | 230 | 230 | Yes | No | exact | Observed matched delay | 452 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 243/0 | 2025-06-01 | 2025-06 | 2025-11-30 | 2025-11 | 182 | 182 | Yes | No | exact | Observed matched delay | 437 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 256/0 | 2025-06-14 | 2025-06 | 2026-02-24 | 2026-02 | 255 | 255 | Yes | No | exact | Observed matched delay | 424 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 246/0 | 2025-08-23 | 2025-08 | 2026-01-03 | 2026-01 | 133 | 133 | Yes | No | exact | Observed matched delay | 354 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 250A/1 | 2025-09-09 | 2025-09 | 2026-01-13 | 2026-01 | 126 | 126 | Yes | No | exact | Observed matched delay | 337 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 131/2 | 2025-09-15 | 2025-09 | 2025-12-15 | 2025-12 | 91 | 91 | Yes | No | exact | Observed matched delay | 331 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 241/3 | 2025-09-20 | 2025-09 | 2026-01-28 | 2026-01 | 130 | 130 | Yes | No | exact | Observed matched delay | 326 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 178/0 | 2025-10-14 | 2025-10 | 2026-03-17 | 2026-03 | 154 | 154 | Yes | No | exact | Observed matched delay | 302 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 120/1 | 2025-10-16 | 2025-10 | 2026-04-13 | 2026-04 | 179 | 179 | Yes | No | exact | Observed matched delay | 300 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 224/1 | 2025-10-19 | 2025-10 | 2026-04-02 | 2026-04 | 165 | 165 | Yes | No | exact | Observed matched delay | 297 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 119/1 | 2025-10-20 | 2025-10 | 2026-01-09 | 2026-01 | 81 | 81 | Yes | No | exact | Observed matched delay | 296 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 224/2 | 2025-10-20 | 2025-10 | 2026-04-29 | 2026-04 | 191 | 191 | Yes | No | exact | Observed matched delay | 296 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 225/0 | 2025-10-22 | 2025-10 | 2026-04-29 | 2026-04 | 189 | 189 | Yes | No | exact | Observed matched delay | 294 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 120/4 | 2025-10-26 | 2025-10 | 2025-12-28 | 2025-12 | 63 | 63 | Yes | No | exact | Observed matched delay | 290 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 223/3 | 2025-10-27 | 2025-10 | 2026-03-27 | 2026-03 | 151 | 151 | Yes | No | exact | Observed matched delay | 289 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 221/0 | 2025-11-05 | 2025-11 | 2026-05-08 | 2026-05 | 184 | 184 | Yes | No | exact | Observed matched delay | 280 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 224/0 | 2025-11-08 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 277 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 138/0 | 2025-11-13 | 2025-11 | 2026-01-12 | 2026-01 | 60 | 60 | Yes | No | exact | Observed matched delay | 272 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 220/1 | 2025-11-14 | 2025-11 | 2026-02-05 | 2026-02 | 83 | 83 | Yes | No | exact | Observed matched delay | 271 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 223/1 | 2025-11-14 | 2025-11 | 2026-03-11 | 2026-03 | 117 | 117 | Yes | No | exact | Observed matched delay | 271 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 222/0 | 2025-11-15 | 2025-11 | 2026-03-13 | 2026-03 | 118 | 118 | Yes | No | exact | Observed matched delay | 270 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 185/0 | 2025-11-16 | 2025-11 | 2026-04-04 | 2026-04 | 139 | 139 | Yes | No | exact | Observed matched delay | 269 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 141/6 | 2025-11-17 | 2025-11 | 2025-12-04 | 2025-12 | 17 | 17 | Yes | No | exact | Observed matched delay | 268 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 220/0 | 2025-11-17 | 2025-11 | 2026-04-10 | 2026-04 | 144 | 144 | Yes | No | exact | Observed matched delay | 268 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 223/2 | 2025-11-18 | 2025-11 | 2026-05-18 | 2026-05 | 181 | 181 | Yes | No | exact | Observed matched delay | 267 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 219/1 | 2025-11-21 | 2025-11 | 2026-05-18 | 2026-05 | 178 | 178 | Yes | No | exact | Observed matched delay | 264 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 223/0 | 2025-11-22 | 2025-11 | 2026-02-20 | 2026-02 | 90 | 90 | Yes | No | exact | Observed matched delay | 263 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 218/0 | 2025-11-23 | 2025-11 | 2026-02-16 | 2026-02 | 85 | 85 | Yes | No | exact | Observed matched delay | 262 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 144/0 | 2025-11-24 | 2025-11 | 2026-03-16 | 2026-03 | 112 | 112 | Yes | No | exact | Observed matched delay | 261 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 196/0 | 2025-11-24 | 2025-11 | 2026-02-06 | 2026-02 | 74 | 74 | Yes | No | exact | Observed matched delay | 261 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 142/0 | 2025-11-25 | 2025-11 | 2025-12-19 | 2025-12 | 24 | 24 | Yes | No | exact | Observed matched delay | 260 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 225/1 | 2025-11-25 | 2025-11 | 2026-06-26 | 2026-06 | 213 | 213 | Yes | No | exact | Observed matched delay | 260 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 125/1 | 2025-11-26 | 2025-11 | 2026-02-18 | 2026-02 | 84 | 84 | Yes | No | exact | Observed matched delay | 259 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 187/0 | 2025-11-26 | 2025-11 | 2025-12-11 | 2025-12 | 15 | 15 | Yes | No | exact | Observed matched delay | 259 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 136/0 | 2025-11-27 | 2025-11 | 2026-02-14 | 2026-02 | 79 | 79 | Yes | No | exact | Observed matched delay | 258 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 214/2 | 2025-11-27 | 2025-11 | 2026-02-04 | 2026-02 | 69 | 69 | Yes | No | exact | Observed matched delay | 258 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 225/4 | 2025-11-29 | 2025-11 | 2026-06-08 | 2026-06 | 191 | 191 | Yes | No | exact | Observed matched delay | 256 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 148/5 | 2025-11-30 | 2025-11 | 2026-01-21 | 2026-01 | 52 | 52 | Yes | No | exact | Observed matched delay | 255 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 215/0 | 2025-11-30 | 2025-11 | 2026-03-03 | 2026-03 | 93 | 93 | Yes | No | exact | Observed matched delay | 255 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 186/0 | 2025-12-01 | 2025-12 | 2026-02-27 | 2026-02 | 88 | 88 | Yes | No | exact | Observed matched delay | 254 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 194/1 | 2025-12-02 | 2025-12 | 2026-02-16 | 2026-02 | 76 | 76 | Yes | No | exact | Observed matched delay | 253 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 176/0 | 2025-12-03 | 2025-12 | 2025-12-21 | 2025-12 | 18 | 18 | Yes | No | exact | Observed matched delay | 252 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 214/5 | 2025-12-03 | 2025-12 | 2026-02-12 | 2026-02 | 71 | 71 | Yes | No | exact | Observed matched delay | 252 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 214/7 | 2025-12-04 | 2025-12 | 2026-04-02 | 2026-04 | 119 | 119 | Yes | No | exact | Observed matched delay | 251 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 143/0 | 2025-12-05 | 2025-12 | 2026-01-13 | 2026-01 | 39 | 39 | Yes | No | exact | Observed matched delay | 250 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 184/0 | 2025-12-05 | 2025-12 | 2026-02-15 | 2026-02 | 72 | 72 | Yes | No | exact | Observed matched delay | 250 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 214/4 | 2025-12-05 | 2025-12 | 2026-02-08 | 2026-02 | 65 | 65 | Yes | No | exact | Observed matched delay | 250 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 244/2 | 2025-12-06 | 2025-12 | 2026-01-21 | 2026-01 | 46 | 46 | Yes | No | exact | Observed matched delay | 249 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 145/5 | 2025-12-07 | 2025-12 | 2025-12-28 | 2025-12 | 21 | 21 | Yes | No | exact | Observed matched delay | 248 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 225/3 | 2025-12-10 | 2025-12 | 2026-07-12 | 2026-07 | 214 | 214 | Yes | No | exact | Observed matched delay | 245 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 139/0 | 2025-12-11 | 2025-12 | 2026-02-06 | 2026-02 | 57 | 57 | Yes | No | exact | Observed matched delay | 244 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 148/3 | 2025-12-11 | 2025-12 | 2026-01-06 | 2026-01 | 26 | 26 | Yes | No | exact | Observed matched delay | 244 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 183/0 | 2025-12-11 | 2025-12 | 2026-01-11 | 2026-01 | 31 | 31 | Yes | No | exact | Observed matched delay | 244 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 217/4 | 2025-12-11 | 2025-12 | 2026-03-13 | 2026-03 | 92 | 92 | Yes | No | exact | Observed matched delay | 244 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 250/2 | 2025-12-11 | 2025-12 | 2026-02-01 | 2026-02 | 52 | 52 | Yes | No | exact | Observed matched delay | 244 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 127/2 | 2025-12-12 | 2025-12 | 2026-06-14 | 2026-06 | 184 | 184 | Yes | No | exact | Observed matched delay | 243 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 183/2 | 2025-12-12 | 2025-12 | 2026-02-02 | 2026-02 | 52 | 52 | Yes | No | exact | Observed matched delay | 243 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 214/3 | 2025-12-12 | 2025-12 | 2026-03-13 | 2026-03 | 91 | 91 | Yes | No | exact | Observed matched delay | 243 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 214/6 | 2025-12-12 | 2025-12 | 2026-02-27 | 2026-02 | 77 | 77 | Yes | No | exact | Observed matched delay | 243 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 249/3 | 2025-12-13 | 2025-12 | 2025-12-24 | 2025-12 | 11 | 11 | Yes | No | exact | Observed matched delay | 242 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 182/0 | 2025-12-14 | 2025-12 | 2026-01-03 | 2026-01 | 20 | 20 | Yes | No | exact | Observed matched delay | 241 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 225/2 | 2025-12-14 | 2025-12 | 2026-06-23 | 2026-06 | 191 | 191 | Yes | No | exact | Observed matched delay | 241 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 141/1 | 2025-12-15 | 2025-12 | 2025-12-25 | 2025-12 | 10 | 10 | Yes | No | exact | Observed matched delay | 240 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 161/0 | 2025-12-16 | 2025-12 | 2026-03-12 | 2026-03 | 86 | 86 | Yes | No | exact | Observed matched delay | 239 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 243/1 | 2025-12-16 | 2025-12 | 2025-12-29 | 2025-12 | 13 | 13 | Yes | No | exact | Observed matched delay | 239 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 189/1 | 2025-12-17 | 2025-12 | 2026-01-30 | 2026-01 | 44 | 44 | Yes | No | exact | Observed matched delay | 238 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 145/6 | 2025-12-18 | 2025-12 | 2026-01-04 | 2026-01 | 17 | 17 | Yes | No | exact | Observed matched delay | 237 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 141/2 | 2025-12-19 | 2025-12 | 2026-01-02 | 2026-01 | 14 | 14 | Yes | No | exact | Observed matched delay | 236 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 175/1 | 2025-12-19 | 2025-12 | 2025-12-28 | 2025-12 | 9 | 9 | Yes | No | exact | Observed matched delay | 236 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 217/2 | 2025-12-19 | 2025-12 | 2026-03-23 | 2026-03 | 94 | 94 | Yes | No | exact | Observed matched delay | 236 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 217/3 | 2025-12-19 | 2025-12 | 2026-03-19 | 2026-03 | 90 | 90 | Yes | No | exact | Observed matched delay | 236 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 166/0 | 2025-12-20 | 2025-12 | 2026-04-06 | 2026-04 | 107 | 107 | Yes | No | exact | Observed matched delay | 235 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 165/6 | 2025-12-23 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 232 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 180/6 | 2025-12-23 | 2025-12 | 2026-01-06 | 2026-01 | 14 | 14 | Yes | No | exact | Observed matched delay | 232 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 191/1 | 2025-12-23 | 2025-12 | 2026-02-20 | 2026-02 | 59 | 59 | Yes | No | exact | Observed matched delay | 232 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 199/1 | 2025-12-23 | 2025-12 | 2026-02-27 | 2026-02 | 66 | 66 | Yes | No | exact | Observed matched delay | 232 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 257/0 | 2025-12-23 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 232 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 216/1 | 2025-12-24 | 2025-12 | 2026-06-15 | 2026-06 | 173 | 173 | Yes | No | exact | Observed matched delay | 231 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 254/1 | 2025-12-24 | 2025-12 | 2026-02-02 | 2026-02 | 40 | 40 | Yes | No | exact | Observed matched delay | 231 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 127/0 | 2025-12-25 | 2025-12 | 2026-02-22 | 2026-02 | 59 | 59 | Yes | No | exact | Observed matched delay | 230 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 148/1 | 2025-12-25 | 2025-12 | 2026-01-25 | 2026-01 | 31 | 31 | Yes | No | exact | Observed matched delay | 230 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 190/0 | 2025-12-25 | 2025-12 | 2026-01-17 | 2026-01 | 23 | 23 | Yes | No | exact | Observed matched delay | 230 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 196/1 | 2025-12-25 | 2025-12 | 2026-02-23 | 2026-02 | 60 | 60 | Yes | No | exact | Observed matched delay | 230 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 197/0 | 2025-12-26 | 2025-12 | 2026-02-10 | 2026-02 | 46 | 46 | Yes | No | exact | Observed matched delay | 229 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 170/0 | 2025-12-27 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 228 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 252/2 | 2025-12-27 | 2025-12 | 2026-01-23 | 2026-01 | 27 | 27 | Yes | No | exact | Observed matched delay | 228 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 197/2 | 2025-12-29 | 2025-12 | 2026-01-15 | 2026-01 | 17 | 17 | Yes | No | exact | Observed matched delay | 226 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 196/2 | 2025-12-30 | 2025-12 | 2026-02-16 | 2026-02 | 48 | 48 | Yes | No | exact | Observed matched delay | 225 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 252/1 | 2025-12-30 | 2025-12 | 2026-01-19 | 2026-01 | 20 | 20 | Yes | No | exact | Observed matched delay | 225 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 128/0 | 2025-12-31 | 2025-12 | 2026-03-12 | 2026-03 | 71 | 71 | Yes | No | exact | Observed matched delay | 224 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 179/0 | 2025-12-31 | 2025-12 | 2026-01-19 | 2026-01 | 19 | 19 | Yes | No | exact | Observed matched delay | 224 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 183/3 | 2025-12-31 | 2025-12 | 2026-03-16 | 2026-03 | 75 | 75 | Yes | No | exact | Observed matched delay | 224 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 216/2 | 2025-12-31 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 224 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 241/1 | 2025-12-31 | 2025-12 | 2026-05-02 | 2026-05 | 122 | 122 | Yes | No | exact | Observed matched delay | 224 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 141/0 | 2026-01-03 | 2026-01 | 2026-01-28 | 2026-01 | 25 | 25 | Yes | No | exact | Observed matched delay | 221 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 149/0 | 2026-01-03 | 2026-01 | 2026-01-31 | 2026-01 | 28 | 28 | Yes | No | exact | Observed matched delay | 221 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 167/0 | 2026-01-04 | 2026-01 | 2026-04-14 | 2026-04 | 100 | 100 | Yes | No | exact | Observed matched delay | 220 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 127/1 | 2026-01-05 | 2026-01 | 2026-03-27 | 2026-03 | 81 | 81 | Yes | No | exact | Observed matched delay | 219 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 139/1 | 2026-01-05 | 2026-01 | 2026-01-31 | 2026-01 | 26 | 26 | Yes | No | exact | Observed matched delay | 219 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 210/0 | 2026-01-05 | 2026-01 | 2026-06-04 | 2026-06 | 150 | 150 | Yes | No | exact | Observed matched delay | 219 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 192/0 | 2026-01-06 | 2026-01 | 2026-02-27 | 2026-02 | 52 | 52 | Yes | No | exact | Observed matched delay | 218 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 178/2 | 2026-01-07 | 2026-01 | 2026-02-11 | 2026-02 | 35 | 35 | Yes | No | exact | Observed matched delay | 217 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 244/0 | 2026-01-09 | 2026-01 | 2026-05-18 | 2026-05 | 129 | 129 | Yes | No | exact | Observed matched delay | 215 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 211/3 | 2026-01-10 | 2026-01 | 2026-03-02 | 2026-03 | 51 | 51 | Yes | No | exact | Observed matched delay | 214 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 255/0 | 2026-01-10 | 2026-01 | 2026-03-12 | 2026-03 | 61 | 61 | Yes | No | exact | Observed matched delay | 214 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 216/3 | 2026-01-12 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 212 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 132/3 | 2026-01-13 | 2026-01 | 2026-03-20 | 2026-03 | 66 | 66 | Yes | No | exact | Observed matched delay | 211 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 162/0 | 2026-01-13 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 211 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 199/2 | 2026-01-13 | 2026-01 | 2026-02-21 | 2026-02 | 39 | 39 | Yes | No | exact | Observed matched delay | 211 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 211/1 | 2026-01-13 | 2026-01 | 2026-03-03 | 2026-03 | 49 | 49 | Yes | No | exact | Observed matched delay | 211 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 230/0 | 2026-01-13 | 2026-01 | 2026-02-28 | 2026-02 | 46 | 46 | Yes | No | exact | Observed matched delay | 211 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 245/0 | 2026-01-13 | 2026-01 | 2026-02-14 | 2026-02 | 32 | 32 | Yes | No | exact | Observed matched delay | 211 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 125/2 | 2026-01-15 | 2026-01 | 2026-03-01 | 2026-03 | 45 | 45 | Yes | No | exact | Observed matched delay | 209 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 160/0 | 2026-01-15 | 2026-01 | 2026-02-27 | 2026-02 | 43 | 43 | Yes | No | exact | Observed matched delay | 209 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 191/0 | 2026-01-15 | 2026-01 | 2026-02-08 | 2026-02 | 24 | 24 | Yes | No | exact | Observed matched delay | 209 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 178/1 | 2026-01-16 | 2026-01 | 2026-02-05 | 2026-02 | 20 | 20 | Yes | No | exact | Observed matched delay | 208 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 199/0 | 2026-01-16 | 2026-01 | 2026-01-21 | 2026-01 | 5 | 5 | Yes | No | exact | Observed matched delay | 208 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 245/1 | 2026-01-16 | 2026-01 | 2026-01-31 | 2026-01 | 15 | 15 | Yes | No | exact | Observed matched delay | 208 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 194/0 | 2026-01-17 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 207 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 133/0 | 2026-01-20 | 2026-01 | 2026-04-08 | 2026-04 | 78 | 78 | Yes | No | exact | Observed matched delay | 204 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 174/3 | 2026-01-20 | 2026-01 | 2026-03-29 | 2026-03 | 68 | 68 | Yes | No | exact | Observed matched delay | 204 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 227/0 | 2026-01-21 | 2026-01 | 2026-03-13 | 2026-03 | 51 | 51 | Yes | No | exact | Observed matched delay | 203 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 250A/0 | 2026-01-21 | 2026-01 | 2026-02-26 | 2026-02 | 36 | 36 | Yes | No | exact | Observed matched delay | 203 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 165/4 | 2026-01-22 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 202 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 211/4 | 2026-01-22 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 202 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 217/5 | 2026-01-22 | 2026-01 | 2026-05-27 | 2026-05 | 125 | 125 | Yes | No | exact | Observed matched delay | 202 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 140/0 | 2026-01-23 | 2026-01 | 2026-02-14 | 2026-02 | 22 | 22 | Yes | No | exact | Observed matched delay | 201 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 193/0 | 2026-01-23 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 201 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 198/0 | 2026-01-23 | 2026-01 | 2026-02-04 | 2026-02 | 12 | 12 | Yes | No | exact | Observed matched delay | 201 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 216/0 | 2026-01-23 | 2026-01 | 2026-02-17 | 2026-02 | 25 | 25 | Yes | No | exact | Observed matched delay | 201 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 244/3 | 2026-01-23 | 2026-01 | 2026-05-27 | 2026-05 | 124 | 124 | Yes | No | exact | Observed matched delay | 201 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 197/1 | 2026-01-24 | 2026-01 | 2026-01-30 | 2026-01 | 6 | 6 | Yes | No | exact | Observed matched delay | 200 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 244/4 | 2026-01-25 | 2026-01 | 2026-03-15 | 2026-03 | 49 | 49 | Yes | No | exact | Observed matched delay | 199 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 133/1 | 2026-01-26 | 2026-01 | 2026-05-28 | 2026-05 | 122 | 122 | Yes | No | exact | Observed matched delay | 198 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 125/0 | 2026-01-27 | 2026-01 | 2026-05-03 | 2026-05 | 96 | 96 | Yes | No | exact | Observed matched delay | 197 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 226/3 | 2026-01-27 | 2026-01 | 2026-03-19 | 2026-03 | 51 | 51 | Yes | No | exact | Observed matched delay | 197 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 233/0 | 2026-01-27 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 197 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 211/2 | 2026-01-28 | 2026-01 | 2026-03-27 | 2026-03 | 58 | 58 | Yes | No | exact | Observed matched delay | 196 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 236/0 | 2026-01-28 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 196 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 139/3 | 2026-01-29 | 2026-01 | 2026-06-04 | 2026-06 | 126 | 126 | Yes | No | exact | Observed matched delay | 195 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 168/0 | 2026-01-29 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 195 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 188/0 | 2026-01-29 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 195 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 227/1 | 2026-01-29 | 2026-01 | 2026-03-27 | 2026-03 | 57 | 57 | Yes | No | exact | Observed matched delay | 195 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 139/2 | 2026-01-30 | 2026-01 | 2026-02-08 | 2026-02 | 9 | 9 | Yes | No | exact | Observed matched delay | 194 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 209/2 | 2026-01-30 | 2026-01 | 2026-03-03 | 2026-03 | 32 | 32 | Yes | No | exact | Observed matched delay | 194 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 235/2 | 2026-01-30 | 2026-01 | 2026-04-05 | 2026-04 | 65 | 65 | Yes | No | exact | Observed matched delay | 194 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 133/2 | 2026-01-31 | 2026-01 | 2026-02-28 | 2026-02 | 28 | 28 | Yes | No | exact | Observed matched delay | 193 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 211/5 | 2026-01-31 | 2026-01 | 2026-04-05 | 2026-04 | 64 | 64 | Yes | No | exact | Observed matched delay | 193 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 211/0 | 2026-02-01 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 192 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 238/0 | 2026-02-01 | 2026-02 | 2026-06-18 | 2026-06 | 137 | 137 | Yes | No | exact | Observed matched delay | 192 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 174/2 | 2026-02-02 | 2026-02 | 2026-03-11 | 2026-03 | 37 | 37 | Yes | No | exact | Observed matched delay | 191 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 250/1 | 2026-02-02 | 2026-02 | 2026-06-08 | 2026-06 | 126 | 126 | Yes | No | exact | Observed matched delay | 191 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 252/4 | 2026-02-02 | 2026-02 | 2026-03-24 | 2026-03 | 50 | 50 | Yes | No | exact | Observed matched delay | 191 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 240/0 | 2026-02-03 | 2026-02 | 2026-02-26 | 2026-02 | 23 | 23 | Yes | No | exact | Observed matched delay | 190 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 124/3 | 2026-02-05 | 2026-02 | 2026-04-28 | 2026-04 | 82 | 82 | Yes | No | exact | Observed matched delay | 188 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 213/0 | 2026-02-05 | 2026-02 | 2026-05-31 | 2026-05 | 115 | 115 | Yes | No | exact | Observed matched delay | 188 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 235/0 | 2026-02-07 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 186 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 256/1 | 2026-02-07 | 2026-02 | 2026-06-15 | 2026-06 | 128 | 128 | Yes | No | exact | Observed matched delay | 186 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 228/0 | 2026-02-10 | 2026-02 | 2026-05-11 | 2026-05 | 90 | 90 | Yes | No | exact | Observed matched delay | 183 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 134/0 | 2026-02-11 | 2026-02 | 2026-03-13 | 2026-03 | 30 | 30 | Yes | No | exact | Observed matched delay | 182 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 124/2 | 2026-02-12 | 2026-02 | 2026-05-22 | 2026-05 | 99 | 99 | Yes | No | exact | Observed matched delay | 181 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 235/3 | 2026-02-13 | 2026-02 | 2026-03-19 | 2026-03 | 34 | 34 | Yes | No | exact | Observed matched delay | 180 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 242/0 | 2026-02-13 | 2026-02 | 2026-04-09 | 2026-04 | 55 | 55 | Yes | No | exact | Observed matched delay | 180 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 214/0 | 2026-02-16 | 2026-02 | 2026-04-29 | 2026-04 | 72 | 72 | Yes | No | exact | Observed matched delay | 177 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 217/1 | 2026-02-16 | 2026-02 | 2026-06-10 | 2026-06 | 114 | 114 | Yes | No | exact | Observed matched delay | 177 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 237/0 | 2026-02-16 | 2026-02 | 2026-05-03 | 2026-05 | 76 | 76 | Yes | No | exact | Observed matched delay | 177 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 147/0 | 2026-02-17 | 2026-02 | 2026-04-07 | 2026-04 | 49 | 49 | Yes | No | exact | Observed matched delay | 176 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 228/1 | 2026-02-17 | 2026-02 | 2026-03-12 | 2026-03 | 23 | 23 | Yes | No | exact | Observed matched delay | 176 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 174/0 | 2026-02-18 | 2026-02 | 2026-05-03 | 2026-05 | 74 | 74 | Yes | No | exact | Observed matched delay | 175 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 235/1 | 2026-02-19 | 2026-02 | 2026-06-05 | 2026-06 | 106 | 106 | Yes | No | exact | Observed matched delay | 174 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 232/4 | 2026-02-20 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 173 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 240/1 | 2026-02-22 | 2026-02 | 2026-03-12 | 2026-03 | 18 | 18 | Yes | No | exact | Observed matched delay | 171 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 133/4 | 2026-02-23 | 2026-02 | 2026-04-03 | 2026-04 | 39 | 39 | Yes | No | exact | Observed matched delay | 170 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 214/1 | 2026-02-23 | 2026-02 | 2026-04-09 | 2026-04 | 45 | 45 | Yes | No | exact | Observed matched delay | 170 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 217/0 | 2026-02-24 | 2026-02 | 2026-06-02 | 2026-06 | 98 | 98 | Yes | No | exact | Observed matched delay | 169 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 173/0 | 2026-02-27 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 166 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 248/0 | 2026-02-27 | 2026-02 | 2026-06-16 | 2026-06 | 109 | 109 | Yes | No | exact | Observed matched delay | 166 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 219/0 | 2026-02-28 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 165 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 239/0 | 2026-03-02 | 2026-03 | 2026-03-25 | 2026-03 | 23 | 23 | Yes | No | exact | Observed matched delay | 163 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 209/0 | 2026-03-03 | 2026-03 | 2026-03-11 | 2026-03 | 8 | 8 | Yes | No | exact | Observed matched delay | 162 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 209/1 | 2026-03-03 | 2026-03 | 2026-03-18 | 2026-03 | 15 | 15 | Yes | No | exact | Observed matched delay | 162 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 163/0 | 2026-03-04 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 161 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 226/1 | 2026-03-08 | 2026-03 | 2026-05-06 | 2026-05 | 59 | 59 | Yes | No | exact | Observed matched delay | 157 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 226/2 | 2026-03-09 | 2026-03 | 2026-03-31 | 2026-03 | 22 | 22 | Yes | No | exact | Observed matched delay | 156 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 232/0 | 2026-03-11 | 2026-03 | 2026-05-21 | 2026-05 | 71 | 71 | Yes | No | exact | Observed matched delay | 154 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 239/1 | 2026-03-12 | 2026-03 | 2026-04-05 | 2026-04 | 24 | 24 | Yes | No | exact | Observed matched delay | 153 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 133/3 | 2026-03-15 | 2026-03 | 2026-03-25 | 2026-03 | 10 | 10 | Yes | No | exact | Observed matched delay | 150 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 207/0 | 2026-03-15 | 2026-03 | 2026-04-02 | 2026-04 | 18 | 18 | Yes | No | exact | Observed matched delay | 150 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 227/2 | 2026-03-16 | 2026-03 | 2026-04-08 | 2026-04 | 23 | 23 | Yes | No | exact | Observed matched delay | 149 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 231/0 | 2026-03-16 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 149 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 145/0 | 2026-03-18 | 2026-03 | 2026-03-29 | 2026-03 | 11 | 11 | Yes | No | exact | Observed matched delay | 147 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 225/7 | 2026-03-22 | 2026-03 | 2026-05-11 | 2026-05 | 50 | 50 | Yes | No | exact | Observed matched delay | 143 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 251/1 | 2026-03-22 | 2026-03 | 2026-04-17 | 2026-04 | 26 | 26 | Yes | No | exact | Observed matched delay | 143 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 121/11 | 2026-03-24 | 2026-03 | 2026-04-01 | 2026-04 | 8 | 8 | Yes | No | exact | Observed matched delay | 141 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 150/1 | 2026-03-24 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 141 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 225/5 | 2026-03-24 | 2026-03 | 2026-05-11 | 2026-05 | 48 | 48 | Yes | No | exact | Observed matched delay | 141 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 234/0 | 2026-03-24 | 2026-03 | 2026-05-12 | 2026-05 | 49 | 49 | Yes | No | exact | Observed matched delay | 141 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 179/2 | 2026-03-27 | 2026-03 | 2026-03-27 | 2026-03 | 0 | 0 | Yes | No | exact | Observed matched delay | 138 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 226/0 | 2026-03-28 | 2026-03 | 2026-04-20 | 2026-04 | 23 | 23 | Yes | No | exact | Observed matched delay | 137 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 230/1 | 2026-03-29 | 2026-03 | 2026-06-22 | 2026-06 | 85 | 85 | Yes | No | exact | Observed matched delay | 136 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 255/1 | 2026-03-29 | 2026-03 | 2026-05-09 | 2026-05 | 41 | 41 | Yes | No | exact | Observed matched delay | 136 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 232/2 | 2026-03-31 | 2026-03 | 2026-06-05 | 2026-06 | 66 | 66 | Yes | No | exact | Observed matched delay | 134 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 180/0 | 2026-04-05 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 129 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 156/0 | 2026-04-06 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 128 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 150/0 | 2026-04-12 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 122 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 195/0 | 2026-04-12 | 2026-04 | 2026-06-20 | 2026-06 | 69 | 69 | Yes | No | exact | Observed matched delay | 122 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 131/0 | 2026-04-16 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 118 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 155/0 | 2026-04-18 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 116 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 230A/0 | 2026-04-18 | 2026-04 | 2026-06-01 | 2026-06 | 44 | 44 | Yes | No | exact | Observed matched delay | 116 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 200/0 | 2026-04-19 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 115 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 131/1 | 2026-04-21 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 113 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 151/0 | 2026-04-21 | 2026-04 | 2026-05-19 | 2026-05 | 28 | 28 | Yes | No | exact | Observed matched delay | 113 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 156/1 | 2026-04-24 | 2026-04 | 2026-05-20 | 2026-05 | 26 | 26 | Yes | No | exact | Observed matched delay | 110 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 153/1 | 2026-04-26 | 2026-04 | 2026-06-08 | 2026-06 | 43 | 43 | Yes | No | exact | Observed matched delay | 108 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 159/0 | 2026-04-28 | 2026-04 | 2026-05-27 | 2026-05 | 29 | 29 | Yes | No | exact | Observed matched delay | 106 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 189/0 | 2026-04-28 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 106 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 151A/0 | 2026-05-01 | 2026-05 | 2026-06-06 | 2026-06 | 36 | 36 | Yes | No | exact | Observed matched delay | 103 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 164/0 | 2026-05-03 | 2026-05 | 2026-06-22 | 2026-06 | 50 | 50 | Yes | No | exact | Observed matched delay | 101 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 235/4 | 2026-05-05 | 2026-05 | 2026-06-05 | 2026-06 | 31 | 31 | Yes | No | exact | Observed matched delay | 99 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 169/0 | 2026-05-06 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 98 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 165/0 | 2026-05-09 | 2026-05 | 2026-06-17 | 2026-06 | 39 | 39 | Yes | No | exact | Observed matched delay | 95 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 232/3 | 2026-05-09 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 95 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 129/0 | 2026-05-11 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 93 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 206/0 | 2026-05-11 | 2026-05 | 2026-06-12 | 2026-06 | 32 | 32 | Yes | No | exact | Observed matched delay | 93 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 145/1 | 2026-05-16 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 88 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 206/1 | 2026-05-17 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 87 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 153A/0 | 2026-05-20 | 2026-05 | 2026-06-08 | 2026-06 | 19 | 19 | Yes | No | exact | Observed matched delay | 84 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 201/0 | 2026-05-20 | 2026-05 | 2026-06-26 | 2026-06 | 37 | 37 | Yes | No | exact | Observed matched delay | 84 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 229B/0 | 2026-05-22 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 82 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 229A/0 | 2026-05-28 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 76 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 229/0 | 2026-05-31 | 2026-05 | 2026-06-15 | 2026-06 | 15 | 15 | Yes | No | exact | Observed matched delay | 73 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 154/0 | 2026-06-01 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 72 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 212/0 | 2026-06-01 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 72 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 254/0 | 2026-06-06 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 67 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 132/2 | 2026-06-07 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 66 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 208/0 | 2026-06-08 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 65 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 225/6 | 2026-06-08 | 2026-06 | 2026-06-18 | 2026-06 | 10 | 10 | Yes | No | exact | Observed matched delay | 65 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 130/0 | 2026-06-12 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 61 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 152/0 | 2026-06-12 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 61 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 253/0 | 2026-06-15 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 58 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 165/3 | 2026-06-17 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 56 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 229/1 | 2026-06-19 | 2026-06 | 2026-06-26 | 2026-06 | 7 | 7 | Yes | No | exact | Observed matched delay | 54 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN | TA 414 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 414 | 4xx | Government | ta414 | 165/1 | 2026-06-21 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 52 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 202/0 | 2026-06-21 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 52 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 135/0 | 2026-06-22 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 51 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 153/2 | 2026-06-26 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 47 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 414 | 4xx | Government | ta414 | 200/1 | 2026-06-26 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 47 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 414 - DPR - 2026-08-11.xlsx | FDN
TA 416 | 4xx | Government | ta416 | 2/8 | 2024-05-06 | 2024-05 | 2024-09-01 | 2024-09 | 118 | 118 | Yes | No | exact | Observed matched delay | 828 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 2/7 | 2024-05-10 | 2024-05 | 2024-11-26 | 2024-11 | 200 | 200 | Yes | No | exact | Observed matched delay | 824 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 2/6 | 2024-05-14 | 2024-05 | 2024-12-01 | 2024-12 | 201 | 201 | Yes | No | exact | Observed matched delay | 820 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 2/5 | 2024-05-18 | 2024-05 | 2024-11-10 | 2024-11 | 176 | 176 | Yes | No | exact | Observed matched delay | 816 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 2/4 | 2024-05-21 | 2024-05 | 2024-09-16 | 2024-09 | 118 | 118 | Yes | No | exact | Observed matched delay | 813 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 2/3 | 2024-05-28 | 2024-05 | 2024-12-10 | 2024-12 | 196 | 196 | Yes | No | exact | Observed matched delay | 806 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/4 | 2024-06-03 | 2024-06 | 2025-01-01 | 2025-01 | 212 | 212 | Yes | No | exact | Observed matched delay | 800 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/10 | 2024-06-04 | 2024-06 | 2024-09-16 | 2024-09 | 104 | 104 | Yes | No | exact | Observed matched delay | 799 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/5 | 2024-06-06 | 2024-06 | 2025-01-24 | 2025-01 | 232 | 232 | Yes | No | exact | Observed matched delay | 797 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/8 | 2024-06-08 | 2024-06 | 2024-10-03 | 2024-10 | 117 | 117 | Yes | No | exact | Observed matched delay | 795 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/3 | 2024-06-09 | 2024-06 | 2025-01-10 | 2025-01 | 215 | 215 | Yes | No | exact | Observed matched delay | 794 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/6 | 2024-06-11 | 2024-06 | 2025-09-15 | 2025-09 | 461 | 461 | Yes | No | exact | Observed matched delay | 792 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 6/2 | 2024-06-12 | 2024-06 | 2024-11-14 | 2024-11 | 155 | 155 | Yes | No | exact | Observed matched delay | 791 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/9 | 2024-06-13 | 2024-06 | 2024-10-24 | 2024-10 | 133 | 133 | Yes | No | exact | Observed matched delay | 790 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/7 | 2024-06-14 | 2024-06 | 2025-01-30 | 2025-01 | 230 | 230 | Yes | No | exact | Observed matched delay | 789 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/8 | 2024-06-17 | 2024-06 | 2025-05-11 | 2025-05 | 328 | 328 | Yes | No | exact | Observed matched delay | 786 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/7 | 2024-06-19 | 2024-06 | 2024-10-15 | 2024-10 | 118 | 118 | Yes | No | exact | Observed matched delay | 784 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/1 | 2024-06-20 | 2024-06 | 2024-12-24 | 2024-12 | 187 | 187 | Yes | No | exact | Observed matched delay | 783 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/6 | 2024-06-22 | 2024-06 | 2024-10-08 | 2024-10 | 108 | 108 | Yes | No | exact | Observed matched delay | 781 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/1 | 2024-06-23 | 2024-06 | 2025-04-01 | 2025-04 | 282 | 282 | Yes | No | exact | Observed matched delay | 780 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/6 | 2024-06-25 | 2024-06 | 2024-11-01 | 2024-11 | 129 | 129 | Yes | No | exact | Observed matched delay | 778 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/7 | 2024-06-27 | 2024-06 | 2024-10-24 | 2024-10 | 119 | 119 | Yes | No | exact | Observed matched delay | 776 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/11 | 2024-06-30 | 2024-06 | 2025-05-12 | 2025-05 | 316 | 316 | Yes | No | exact | Observed matched delay | 773 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/1 | 2024-07-11 | 2024-07 | 2025-01-07 | 2025-01 | 180 | 180 | Yes | No | exact | Observed matched delay | 762 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/12 | 2024-07-15 | 2024-07 | 2024-11-01 | 2024-11 | 109 | 109 | Yes | No | exact | Observed matched delay | 758 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/2 | 2024-07-18 | 2024-07 | 2024-12-06 | 2024-12 | 141 | 141 | Yes | No | exact | Observed matched delay | 755 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/5 | 2024-07-20 | 2024-07 | 2024-11-10 | 2024-11 | 113 | 113 | Yes | No | exact | Observed matched delay | 753 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/11 | 2024-07-23 | 2024-07 | 2025-04-27 | 2025-04 | 278 | 278 | Yes | No | exact | Observed matched delay | 750 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/3 | 2024-07-25 | 2024-07 | 2024-11-10 | 2024-11 | 108 | 108 | Yes | No | exact | Observed matched delay | 748 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/6 | 2024-07-28 | 2024-07 | 2024-11-05 | 2024-11 | 100 | 100 | Yes | No | exact | Observed matched delay | 745 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/8 | 2024-07-29 | 2024-07 | 2024-10-01 | 2024-10 | 64 | 64 | Yes | No | exact | Observed matched delay | 744 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/8 | 2024-07-30 | 2024-07 | 2025-05-06 | 2025-05 | 280 | 280 | Yes | No | exact | Observed matched delay | 743 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/4 | 2024-07-31 | 2024-07 | 2024-12-20 | 2024-12 | 142 | 142 | Yes | No | exact | Observed matched delay | 742 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/9 | 2024-08-03 | 2024-08 | 2024-10-14 | 2024-10 | 72 | 72 | Yes | No | exact | Observed matched delay | 739 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/9 | 2024-08-04 | 2024-08 | 2025-01-16 | 2025-01 | 165 | 165 | Yes | No | exact | Observed matched delay | 738 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/12 | 2024-08-08 | 2024-08 | 2024-11-29 | 2024-11 | 113 | 113 | Yes | No | exact | Observed matched delay | 734 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/4 | 2024-08-09 | 2024-08 | 2024-11-17 | 2024-11 | 100 | 100 | Yes | No | exact | Observed matched delay | 733 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/5 | 2024-08-10 | 2024-08 | 2024-10-20 | 2024-10 | 71 | 71 | Yes | No | exact | Observed matched delay | 732 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/11 | 2024-08-14 | 2024-08 | 2025-05-14 | 2025-05 | 273 | 273 | Yes | No | exact | Observed matched delay | 728 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 23/3 | 2024-08-18 | 2024-08 | 2025-05-15 | 2025-05 | 270 | 270 | Yes | No | exact | Observed matched delay | 724 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/3 | 2024-08-21 | 2024-08 | 2024-12-06 | 2024-12 | 107 | 107 | Yes | No | exact | Observed matched delay | 721 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/12 | 2024-08-24 | 2024-08 | 2025-04-23 | 2025-04 | 242 | 242 | Yes | No | exact | Observed matched delay | 718 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/7 | 2024-08-30 | 2024-08 | 2024-11-29 | 2024-11 | 91 | 91 | Yes | No | exact | Observed matched delay | 712 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/9 | 2024-08-31 | 2024-08 | 2025-02-02 | 2025-02 | 155 | 155 | Yes | No | exact | Observed matched delay | 711 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 23/4 | 2024-08-31 | 2024-08 | 2025-05-23 | 2025-05 | 265 | 265 | Yes | No | exact | Observed matched delay | 711 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/3 | 2024-08-31 | 2024-08 | 2025-01-07 | 2025-01 | 129 | 129 | Yes | No | exact | Observed matched delay | 711 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/3 | 2024-09-05 | 2024-09 | 2024-11-10 | 2024-11 | 66 | 66 | Yes | No | exact | Observed matched delay | 706 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/4 | 2024-09-08 | 2024-09 | 2025-01-21 | 2025-01 | 135 | 135 | Yes | No | exact | Observed matched delay | 703 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/8 | 2024-09-08 | 2024-09 | 2025-03-21 | 2025-03 | 194 | 194 | Yes | No | exact | Observed matched delay | 703 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/4 | 2024-09-08 | 2024-09 | 2025-04-29 | 2025-04 | 233 | 233 | Yes | No | exact | Observed matched delay | 703 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 45/3 | 2024-09-08 | 2024-09 | 2024-12-10 | 2024-12 | 93 | 93 | Yes | No | exact | Observed matched delay | 703 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/8 | 2024-09-09 | 2024-09 | 2025-05-26 | 2025-05 | 259 | 259 | Yes | No | exact | Observed matched delay | 702 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/7 | 2024-09-09 | 2024-09 | 2025-04-23 | 2025-04 | 226 | 226 | Yes | No | exact | Observed matched delay | 702 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 23/5 | 2024-09-11 | 2024-09 | 2025-05-10 | 2025-05 | 241 | 241 | Yes | No | exact | Observed matched delay | 700 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 50/1 | 2024-09-11 | 2024-09 | 2025-06-08 | 2025-06 | 270 | 270 | Yes | No | exact | Observed matched delay | 700 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 23/2 | 2024-09-20 | 2024-09 | 2025-06-04 | 2025-06 | 257 | 257 | Yes | No | exact | Observed matched delay | 691 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/6 | 2024-09-20 | 2024-09 | 2025-04-12 | 2025-04 | 204 | 204 | Yes | No | exact | Observed matched delay | 691 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 41/1 | 2024-09-20 | 2024-09 | 2024-11-10 | 2024-11 | 51 | 51 | Yes | No | exact | Observed matched delay | 691 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/2 | 2024-09-22 | 2024-09 | 2024-11-28 | 2024-11 | 67 | 67 | Yes | No | exact | Observed matched delay | 689 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/1 | 2024-09-22 | 2024-09 | 2025-04-16 | 2025-04 | 206 | 206 | Yes | No | exact | Observed matched delay | 689 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 30/3 | 2024-09-22 | 2024-09 | 2025-04-30 | 2025-04 | 220 | 220 | Yes | No | exact | Observed matched delay | 689 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/2 | 2024-09-24 | 2024-09 | 2025-01-03 | 2025-01 | 101 | 101 | Yes | No | exact | Observed matched delay | 687 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 30/6 | 2024-09-24 | 2024-09 | 2025-04-22 | 2025-04 | 210 | 210 | Yes | No | exact | Observed matched delay | 687 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/9 | 2024-09-24 | 2024-09 | 2025-05-20 | 2025-05 | 238 | 238 | Yes | No | exact | Observed matched delay | 687 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 25/1 | 2024-09-26 | 2024-09 | 2025-07-01 | 2025-07 | 278 | 278 | Yes | No | exact | Observed matched delay | 685 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/2 | 2024-09-26 | 2024-09 | 2025-03-20 | 2025-03 | 175 | 175 | Yes | No | exact | Observed matched delay | 685 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/5 | 2024-09-26 | 2024-09 | 2025-01-15 | 2025-01 | 111 | 111 | Yes | No | exact | Observed matched delay | 685 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 41/2 | 2024-09-26 | 2024-09 | 2024-11-30 | 2024-11 | 65 | 65 | Yes | No | exact | Observed matched delay | 685 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 45/2 | 2024-09-29 | 2024-09 | 2024-12-21 | 2024-12 | 83 | 83 | Yes | No | exact | Observed matched delay | 682 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/1 | 2024-09-30 | 2024-09 | 2025-05-04 | 2025-05 | 216 | 216 | Yes | No | exact | Observed matched delay | 681 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/6 | 2024-09-30 | 2024-09 | 2025-05-11 | 2025-05 | 223 | 223 | Yes | No | exact | Observed matched delay | 681 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/1 | 2024-09-30 | 2024-09 | 2024-12-13 | 2024-12 | 74 | 74 | Yes | No | exact | Observed matched delay | 681 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 23/1 | 2024-09-30 | 2024-09 | 2025-05-28 | 2025-05 | 240 | 240 | Yes | No | exact | Observed matched delay | 681 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 30/4 | 2024-09-30 | 2024-09 | 2025-03-01 | 2025-03 | 152 | 152 | Yes | No | exact | Observed matched delay | 681 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/10 | 2024-09-30 | 2024-09 | 2025-05-25 | 2025-05 | 237 | 237 | Yes | No | exact | Observed matched delay | 681 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/1 | 2024-10-01 | 2024-10 | 2025-01-16 | 2025-01 | 107 | 107 | Yes | No | exact | Observed matched delay | 680 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/3 | 2024-10-01 | 2024-10 | 2025-02-28 | 2025-02 | 150 | 150 | Yes | No | exact | Observed matched delay | 680 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 34/7 | 2024-10-03 | 2024-10 | 2025-02-12 | 2025-02 | 132 | 132 | Yes | No | exact | Observed matched delay | 678 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 46/2 | 2024-10-03 | 2024-10 | 2025-08-14 | 2025-08 | 315 | 315 | Yes | No | exact | Observed matched delay | 678 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 25/2 | 2024-10-04 | 2024-10 | 2025-04-15 | 2025-04 | 193 | 193 | Yes | No | exact | Observed matched delay | 677 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/7 | 2024-10-06 | 2024-10 | 2025-06-24 | 2025-06 | 261 | 261 | Yes | No | exact | Observed matched delay | 675 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/8 | 2024-10-06 | 2024-10 | 2025-04-29 | 2025-04 | 205 | 205 | Yes | No | exact | Observed matched delay | 675 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/3 | 2024-10-07 | 2024-10 | 2025-01-12 | 2025-01 | 97 | 97 | Yes | No | exact | Observed matched delay | 674 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 30/2 | 2024-10-07 | 2024-10 | 2025-05-14 | 2025-05 | 219 | 219 | Yes | No | exact | Observed matched delay | 674 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/2 | 2024-10-07 | 2024-10 | 2025-01-11 | 2025-01 | 96 | 96 | Yes | No | exact | Observed matched delay | 674 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 25/3 | 2024-10-08 | 2024-10 | 2025-04-30 | 2025-04 | 204 | 204 | Yes | No | exact | Observed matched delay | 673 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 34/6 | 2024-10-08 | 2024-10 | 2025-02-21 | 2025-02 | 136 | 136 | Yes | No | exact | Observed matched delay | 673 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/5 | 2024-10-08 | 2024-10 | 2025-05-05 | 2025-05 | 209 | 209 | Yes | No | exact | Observed matched delay | 673 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/1 | 2024-10-10 | 2024-10 | 2025-01-25 | 2025-01 | 107 | 107 | Yes | No | exact | Observed matched delay | 671 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 34/3 | 2024-10-10 | 2024-10 | 2025-04-29 | 2025-04 | 201 | 201 | Yes | No | exact | Observed matched delay | 671 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 34/4 | 2024-10-10 | 2024-10 | 2025-04-03 | 2025-04 | 175 | 175 | Yes | No | exact | Observed matched delay | 671 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/9 | 2024-10-10 | 2024-10 | 2025-02-08 | 2025-02 | 121 | 121 | Yes | No | exact | Observed matched delay | 671 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 46/1 | 2024-10-10 | 2024-10 | 2024-12-28 | 2024-12 | 79 | 79 | Yes | No | exact | Observed matched delay | 671 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/5 | 2024-10-13 | 2024-10 | 2025-01-25 | 2025-01 | 104 | 104 | Yes | No | exact | Observed matched delay | 668 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 34/2 | 2024-10-13 | 2024-10 | 2025-04-23 | 2025-04 | 192 | 192 | Yes | No | exact | Observed matched delay | 668 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 30/1 | 2024-10-14 | 2024-10 | 2025-05-07 | 2025-05 | 205 | 205 | Yes | No | exact | Observed matched delay | 667 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/8 | 2024-10-14 | 2024-10 | 2025-03-16 | 2025-03 | 153 | 153 | Yes | No | exact | Observed matched delay | 667 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/2 | 2024-10-14 | 2024-10 | 2024-12-12 | 2024-12 | 59 | 59 | Yes | No | exact | Observed matched delay | 667 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 30/5 | 2024-10-16 | 2024-10 | 2025-03-10 | 2025-03 | 145 | 145 | Yes | No | exact | Observed matched delay | 665 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/1 | 2024-10-16 | 2024-10 | 2025-03-12 | 2025-03 | 147 | 147 | Yes | No | exact | Observed matched delay | 665 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/2 | 2024-10-16 | 2024-10 | 2025-02-02 | 2025-02 | 109 | 109 | Yes | No | exact | Observed matched delay | 665 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/10 | 2024-10-18 | 2024-10 | 2025-03-24 | 2025-03 | 157 | 157 | Yes | No | exact | Observed matched delay | 663 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/11 | 2024-10-18 | 2024-10 | 2025-02-02 | 2025-02 | 107 | 107 | Yes | No | exact | Observed matched delay | 663 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/2 | 2024-10-20 | 2024-10 | 2024-12-12 | 2024-12 | 53 | 53 | Yes | No | exact | Observed matched delay | 661 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/3 | 2024-10-20 | 2024-10 | 2024-12-24 | 2024-12 | 65 | 65 | Yes | No | exact | Observed matched delay | 661 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/2 | 2024-10-20 | 2024-10 | 2025-03-19 | 2025-03 | 150 | 150 | Yes | No | exact | Observed matched delay | 661 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/2 | 2024-10-21 | 2024-10 | 2025-02-07 | 2025-02 | 109 | 109 | Yes | No | exact | Observed matched delay | 660 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 34/1 | 2024-10-21 | 2024-10 | 2025-03-01 | 2025-03 | 131 | 131 | Yes | No | exact | Observed matched delay | 660 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/8 | 2024-10-21 | 2024-10 | 2025-03-22 | 2025-03 | 152 | 152 | Yes | No | exact | Observed matched delay | 660 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/9 | 2024-10-22 | 2024-10 | 2025-05-13 | 2025-05 | 203 | 203 | Yes | No | exact | Observed matched delay | 659 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/10 | 2024-10-23 | 2024-10 | 2025-01-21 | 2025-01 | 90 | 90 | Yes | No | exact | Observed matched delay | 658 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/3 | 2024-10-23 | 2024-10 | 2024-11-28 | 2024-11 | 36 | 36 | Yes | No | exact | Observed matched delay | 658 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/1 | 2024-10-24 | 2024-10 | 2024-12-18 | 2024-12 | 55 | 55 | Yes | No | exact | Observed matched delay | 657 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 28/1 | 2024-10-24 | 2024-10 | 2025-06-24 | 2025-06 | 243 | 243 | Yes | No | exact | Observed matched delay | 657 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/9 | 2024-10-24 | 2024-10 | 2025-02-11 | 2025-02 | 110 | 110 | Yes | No | exact | Observed matched delay | 657 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/5 | 2024-10-24 | 2024-10 | 2025-06-02 | 2025-06 | 221 | 221 | Yes | No | exact | Observed matched delay | 657 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/1 | 2024-10-24 | 2024-10 | 2025-01-25 | 2025-01 | 93 | 93 | Yes | No | exact | Observed matched delay | 657 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/5 | 2024-10-25 | 2024-10 | 2025-04-12 | 2025-04 | 169 | 169 | Yes | No | exact | Observed matched delay | 656 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/10 | 2024-10-25 | 2024-10 | 2024-12-18 | 2024-12 | 54 | 54 | Yes | No | exact | Observed matched delay | 656 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/3 | 2024-10-26 | 2024-10 | 2025-02-26 | 2025-02 | 123 | 123 | Yes | No | exact | Observed matched delay | 655 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/9 | 2024-10-26 | 2024-10 | 2025-02-14 | 2025-02 | 111 | 111 | Yes | No | exact | Observed matched delay | 655 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/7 | 2024-10-26 | 2024-10 | 2025-02-16 | 2025-02 | 113 | 113 | Yes | No | exact | Observed matched delay | 655 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8B/3 | 2024-10-26 | 2024-10 | 2025-03-28 | 2025-03 | 153 | 153 | Yes | No | exact | Observed matched delay | 655 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/4 | 2024-10-27 | 2024-10 | 2024-12-06 | 2024-12 | 40 | 40 | Yes | No | exact | Observed matched delay | 654 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/11 | 2024-10-27 | 2024-10 | 2025-03-01 | 2025-03 | 125 | 125 | Yes | No | exact | Observed matched delay | 654 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/8 | 2024-11-01 | 2024-11 | 2024-11-22 | 2024-11 | 21 | 21 | Yes | No | exact | Observed matched delay | 649 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/4 | 2024-11-01 | 2024-11 | 2025-02-20 | 2025-02 | 111 | 111 | Yes | No | exact | Observed matched delay | 649 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/6 | 2024-11-01 | 2024-11 | 2025-01-20 | 2025-01 | 80 | 80 | Yes | No | exact | Observed matched delay | 649 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/7 | 2024-11-01 | 2024-11 | 2025-02-03 | 2025-02 | 94 | 94 | Yes | No | exact | Observed matched delay | 649 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/10 | 2024-11-01 | 2024-11 | 2025-05-16 | 2025-05 | 196 | 196 | Yes | No | exact | Observed matched delay | 649 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/4 | 2024-11-02 | 2024-11 | 2025-03-08 | 2025-03 | 126 | 126 | Yes | No | exact | Observed matched delay | 648 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/5 | 2024-11-02 | 2024-11 | 2025-02-27 | 2025-02 | 117 | 117 | Yes | No | exact | Observed matched delay | 648 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8B/1 | 2024-11-05 | 2024-11 | 2025-03-22 | 2025-03 | 137 | 137 | Yes | No | exact | Observed matched delay | 645 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/6 | 2024-11-08 | 2024-11 | 2025-02-14 | 2025-02 | 98 | 98 | Yes | No | exact | Observed matched delay | 642 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/4 | 2024-11-09 | 2024-11 | 2025-01-04 | 2025-01 | 56 | 56 | Yes | No | exact | Observed matched delay | 641 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 34/0 | 2024-11-09 | 2024-11 | 2025-03-24 | 2025-03 | 135 | 135 | Yes | No | exact | Observed matched delay | 641 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/2 | 2024-11-10 | 2024-11 | 2025-01-17 | 2025-01 | 68 | 68 | Yes | No | exact | Observed matched delay | 640 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/4 | 2024-11-10 | 2024-11 | 2025-02-20 | 2025-02 | 102 | 102 | Yes | No | exact | Observed matched delay | 640 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/4 | 2024-11-11 | 2024-11 | 2024-12-06 | 2024-12 | 25 | 25 | Yes | No | exact | Observed matched delay | 639 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/8 | 2024-11-11 | 2024-11 | 2025-03-03 | 2025-03 | 112 | 112 | Yes | No | exact | Observed matched delay | 639 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/9 | 2024-11-11 | 2024-11 | 2024-12-24 | 2024-12 | 43 | 43 | Yes | No | exact | Observed matched delay | 639 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/7 | 2024-11-13 | 2024-11 | 2025-01-09 | 2025-01 | 57 | 57 | Yes | No | exact | Observed matched delay | 637 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/0 | 2024-11-13 | 2024-11 | 2025-01-28 | 2025-01 | 76 | 76 | Yes | No | exact | Observed matched delay | 637 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/3 | 2024-11-13 | 2024-11 | 2025-02-12 | 2025-02 | 91 | 91 | Yes | No | exact | Observed matched delay | 637 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8B/2 | 2024-11-13 | 2024-11 | 2025-04-08 | 2025-04 | 146 | 146 | Yes | No | exact | Observed matched delay | 637 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/7 | 2024-11-15 | 2024-11 | 2025-02-21 | 2025-02 | 98 | 98 | Yes | No | exact | Observed matched delay | 635 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/8 | 2024-11-15 | 2024-11 | 2025-01-08 | 2025-01 | 54 | 54 | Yes | No | exact | Observed matched delay | 635 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 32/0 | 2024-11-16 | 2024-11 | 2025-04-01 | 2025-04 | 136 | 136 | Yes | No | exact | Observed matched delay | 634 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 10/1 | 2024-11-18 | 2024-11 | 2025-04-12 | 2025-04 | 145 | 145 | Yes | No | exact | Observed matched delay | 632 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/5 | 2024-11-18 | 2024-11 | 2024-12-22 | 2024-12 | 34 | 34 | Yes | No | exact | Observed matched delay | 632 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/3 | 2024-11-20 | 2024-11 | 2025-03-24 | 2025-03 | 124 | 124 | Yes | No | exact | Observed matched delay | 630 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/6 | 2024-11-21 | 2024-11 | 2024-12-28 | 2024-12 | 37 | 37 | Yes | No | exact | Observed matched delay | 629 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 33/0 | 2024-11-21 | 2024-11 | 2025-04-12 | 2025-04 | 142 | 142 | Yes | No | exact | Observed matched delay | 629 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/4 | 2024-11-21 | 2024-11 | 2025-05-07 | 2025-05 | 167 | 167 | Yes | No | exact | Observed matched delay | 629 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/8 | 2024-11-21 | 2024-11 | 2024-12-17 | 2024-12 | 26 | 26 | Yes | No | exact | Observed matched delay | 629 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8B/4 | 2024-11-21 | 2024-11 | 2025-04-14 | 2025-04 | 144 | 144 | Yes | No | exact | Observed matched delay | 629 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 21/0 | 2024-11-22 | 2024-11 | 2025-02-06 | 2025-02 | 76 | 76 | Yes | No | exact | Observed matched delay | 628 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8/3 | 2024-11-22 | 2024-11 | 2025-03-08 | 2025-03 | 106 | 106 | Yes | No | exact | Observed matched delay | 628 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 54/1 | 2024-11-23 | 2024-11 | 2025-08-18 | 2025-08 | 268 | 268 | Yes | No | exact | Observed matched delay | 627 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/11 | 2024-11-24 | 2024-11 | 2025-03-31 | 2025-03 | 127 | 127 | Yes | No | exact | Observed matched delay | 626 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/2 | 2024-11-26 | 2024-11 | 2025-04-20 | 2025-04 | 145 | 145 | Yes | No | exact | Observed matched delay | 624 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/3 | 2024-11-26 | 2024-11 | 2025-03-20 | 2025-03 | 114 | 114 | Yes | No | exact | Observed matched delay | 624 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 36/0 | 2024-11-27 | 2024-11 | 2025-04-02 | 2025-04 | 126 | 126 | Yes | No | exact | Observed matched delay | 623 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8/4 | 2024-11-27 | 2024-11 | 2025-03-13 | 2025-03 | 106 | 106 | Yes | No | exact | Observed matched delay | 623 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 31/0 | 2024-11-29 | 2024-11 | 2025-02-19 | 2025-02 | 82 | 82 | Yes | No | exact | Observed matched delay | 621 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/0 | 2024-11-29 | 2024-11 | 2025-01-29 | 2025-01 | 61 | 61 | Yes | No | exact | Observed matched delay | 621 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/6 | 2024-11-29 | 2024-11 | 2025-04-01 | 2025-04 | 123 | 123 | Yes | No | exact | Observed matched delay | 621 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/7 | 2024-11-29 | 2024-11 | 2024-12-24 | 2024-12 | 25 | 25 | Yes | No | exact | Observed matched delay | 621 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/2 | 2024-11-29 | 2024-11 | 2024-12-31 | 2024-12 | 32 | 32 | Yes | No | exact | Observed matched delay | 621 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8B/5 | 2024-11-29 | 2024-11 | 2025-03-24 | 2025-03 | 115 | 115 | Yes | No | exact | Observed matched delay | 621 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 10/0 | 2024-11-30 | 2024-11 | 2025-04-17 | 2025-04 | 138 | 138 | Yes | No | exact | Observed matched delay | 620 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 54/2 | 2024-12-01 | 2024-12 | 2025-10-08 | 2025-10 | 311 | 311 | Yes | No | exact | Observed matched delay | 619 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 39/0 | 2024-12-02 | 2024-12 | 2025-04-12 | 2025-04 | 131 | 131 | Yes | No | exact | Observed matched delay | 618 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8/2 | 2024-12-03 | 2024-12 | 2025-02-16 | 2025-02 | 75 | 75 | Yes | No | exact | Observed matched delay | 617 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 26/0 | 2024-12-04 | 2024-12 | 2025-09-15 | 2025-09 | 285 | 285 | Yes | No | exact | Observed matched delay | 616 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/1 | 2024-12-04 | 2024-12 | 2025-02-19 | 2025-02 | 77 | 77 | Yes | No | exact | Observed matched delay | 616 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/5 | 2024-12-06 | 2024-12 | 2024-12-28 | 2024-12 | 22 | 22 | Yes | No | exact | Observed matched delay | 614 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 17/0 | 2024-12-09 | 2024-12 | 2025-09-11 | 2025-09 | 276 | 276 | Yes | No | exact | Observed matched delay | 611 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 5/1 | 2024-12-09 | 2024-12 | 2025-03-16 | 2025-03 | 97 | 97 | Yes | No | exact | Observed matched delay | 611 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/4 | 2024-12-09 | 2024-12 | 2025-02-10 | 2025-02 | 63 | 63 | Yes | No | exact | Observed matched delay | 611 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/7 | 2024-12-09 | 2024-12 | 2025-01-15 | 2025-01 | 37 | 37 | Yes | No | exact | Observed matched delay | 611 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8/1 | 2024-12-09 | 2024-12 | 2025-02-09 | 2025-02 | 62 | 62 | Yes | No | exact | Observed matched delay | 611 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 3/0 | 2024-12-10 | 2024-12 | 2025-06-12 | 2025-06 | 184 | 184 | Yes | No | exact | Observed matched delay | 610 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/5 | 2024-12-10 | 2024-12 | 2025-05-30 | 2025-05 | 171 | 171 | Yes | No | exact | Observed matched delay | 610 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/10 | 2024-12-11 | 2024-12 | 2025-05-20 | 2025-05 | 160 | 160 | Yes | No | exact | Observed matched delay | 609 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 55/1 | 2024-12-11 | 2024-12 | 2025-11-09 | 2025-11 | 333 | 333 | Yes | No | exact | Observed matched delay | 609 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/5 | 2024-12-13 | 2024-12 | 2025-01-29 | 2025-01 | 47 | 47 | Yes | No | exact | Observed matched delay | 607 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 49/0 | 2024-12-15 | 2024-12 | 2025-11-06 | 2025-11 | 326 | 326 | Yes | No | exact | Observed matched delay | 605 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/9 | 2024-12-16 | 2024-12 | 2025-05-04 | 2025-05 | 139 | 139 | Yes | No | exact | Observed matched delay | 604 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 6/1 | 2024-12-16 | 2024-12 | 2025-03-09 | 2025-03 | 83 | 83 | Yes | No | exact | Observed matched delay | 604 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/6 | 2024-12-16 | 2024-12 | 2025-01-21 | 2025-01 | 36 | 36 | Yes | No | exact | Observed matched delay | 604 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/7 | 2024-12-17 | 2024-12 | 2025-04-12 | 2025-04 | 116 | 116 | Yes | No | exact | Observed matched delay | 603 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/0 | 2024-12-17 | 2024-12 | 2025-04-06 | 2025-04 | 110 | 110 | Yes | No | exact | Observed matched delay | 603 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/8 | 2024-12-17 | 2024-12 | 2025-08-18 | 2025-08 | 244 | 244 | Yes | No | exact | Observed matched delay | 603 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/7 | 2024-12-18 | 2024-12 | 2025-12-06 | 2025-12 | 353 | 353 | Yes | No | exact | Observed matched delay | 602 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 48/1 | 2024-12-20 | 2024-12 | 2025-09-15 | 2025-09 | 269 | 269 | Yes | No | exact | Observed matched delay | 600 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 7/0 | 2024-12-20 | 2024-12 | 2025-02-27 | 2025-02 | 69 | 69 | Yes | No | exact | Observed matched delay | 600 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8/0 | 2024-12-20 | 2024-12 | 2025-02-22 | 2025-02 | 64 | 64 | Yes | No | exact | Observed matched delay | 600 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 47/0 | 2024-12-21 | 2024-12 | 2025-09-07 | 2025-09 | 260 | 260 | Yes | No | exact | Observed matched delay | 599 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/1 | 2024-12-22 | 2024-12 | 2025-05-14 | 2025-05 | 143 | 143 | Yes | No | exact | Observed matched delay | 598 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/10 | 2024-12-24 | 2024-12 | 2025-03-01 | 2025-03 | 67 | 67 | Yes | No | exact | Observed matched delay | 596 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 9/0 | 2024-12-24 | 2024-12 | 2025-04-01 | 2025-04 | 98 | 98 | Yes | No | exact | Observed matched delay | 596 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/8 | 2024-12-27 | 2024-12 | 2025-05-22 | 2025-05 | 146 | 146 | Yes | No | exact | Observed matched delay | 593 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/7 | 2024-12-27 | 2024-12 | 2026-02-09 | 2026-02 | 409 | 409 | Yes | No | exact | Observed matched delay | 593 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 6/0 | 2024-12-27 | 2024-12 | 2025-03-22 | 2025-03 | 85 | 85 | Yes | No | exact | Observed matched delay | 593 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 46/0 | 2024-12-28 | 2024-12 | 2025-09-25 | 2025-09 | 271 | 271 | Yes | No | exact | Observed matched delay | 592 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/6 | 2024-12-31 | 2024-12 | 2025-03-28 | 2025-03 | 87 | 87 | Yes | No | exact | Observed matched delay | 589 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 54/0 | 2024-12-31 | 2024-12 | 2025-09-25 | 2025-09 | 268 | 268 | Yes | No | exact | Observed matched delay | 589 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53A/5 | 2025-01-02 | 2025-01 | 2025-06-02 | 2025-06 | 151 | 151 | Yes | No | exact | Observed matched delay | 587 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 64/1 | 2025-01-02 | 2025-01 | 2025-11-06 | 2025-11 | 308 | 308 | Yes | No | exact | Observed matched delay | 587 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 15/0 | 2025-01-03 | 2025-01 | 2025-05-16 | 2025-05 | 133 | 133 | Yes | No | exact | Observed matched delay | 586 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/9 | 2025-01-03 | 2025-01 | 2025-04-23 | 2025-04 | 110 | 110 | Yes | No | exact | Observed matched delay | 586 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53A/7 | 2025-01-07 | 2025-01 | 2025-12-08 | 2025-12 | 335 | 335 | Yes | No | exact | Observed matched delay | 582 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 5/0 | 2025-01-09 | 2025-01 | 2025-03-01 | 2025-03 | 51 | 51 | Yes | No | exact | Observed matched delay | 580 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8A/0 | 2025-01-09 | 2025-01 | 2025-04-22 | 2025-04 | 103 | 103 | Yes | No | exact | Observed matched delay | 580 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53A/0 | 2025-01-10 | 2025-01 | 2025-11-15 | 2025-11 | 309 | 309 | Yes | No | exact | Observed matched delay | 579 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 70/0 | 2025-01-10 | 2025-01 | 2025-12-20 | 2025-12 | 344 | 344 | Yes | No | exact | Observed matched delay | 579 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/0 | 2025-01-11 | 2025-01 | 2025-09-05 | 2025-09 | 237 | 237 | Yes | No | exact | Observed matched delay | 578 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53A/4 | 2025-01-11 | 2025-01 | 2025-04-01 | 2025-04 | 80 | 80 | Yes | No | exact | Observed matched delay | 578 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/0 | 2025-01-11 | 2025-01 | 2025-06-28 | 2025-06 | 168 | 168 | Yes | No | exact | Observed matched delay | 578 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 64/2 | 2025-01-11 | 2025-01 | 2026-01-20 | 2026-01 | 374 | 374 | Yes | No | exact | Observed matched delay | 578 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 28/0 | 2025-01-12 | 2025-01 | 2025-07-08 | 2025-07 | 177 | 177 | Yes | No | exact | Observed matched delay | 577 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 48/0 | 2025-01-12 | 2025-01 | 2025-06-15 | 2025-06 | 154 | 154 | Yes | No | exact | Observed matched delay | 577 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/10 | 2025-01-14 | 2025-01 | 2025-04-30 | 2025-04 | 106 | 106 | Yes | No | exact | Observed matched delay | 575 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 8B/0 | 2025-01-14 | 2025-01 | 2025-05-05 | 2025-05 | 111 | 111 | Yes | No | exact | Observed matched delay | 575 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53/0 | 2025-01-15 | 2025-01 | 2025-09-26 | 2025-09 | 254 | 254 | Yes | No | exact | Observed matched delay | 574 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 22A/0 | 2025-01-17 | 2025-01 | 2025-12-15 | 2025-12 | 332 | 332 | Yes | No | exact | Observed matched delay | 572 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 57/0 | 2025-01-17 | 2025-01 | 2025-12-22 | 2025-12 | 339 | 339 | Yes | No | exact | Observed matched delay | 572 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 58/0 | 2025-01-17 | 2025-01 | 2025-12-01 | 2025-12 | 318 | 318 | Yes | No | exact | Observed matched delay | 572 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53A/2 | 2025-01-18 | 2025-01 | 2025-06-10 | 2025-06 | 143 | 143 | Yes | No | exact | Observed matched delay | 571 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 20/10 | 2025-01-20 | 2025-01 | 2025-04-09 | 2025-04 | 79 | 79 | Yes | No | exact | Observed matched delay | 569 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/3 | 2025-01-20 | 2025-01 | 2025-04-30 | 2025-04 | 100 | 100 | Yes | No | exact | Observed matched delay | 569 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 55/0 | 2025-01-22 | 2025-01 | 2025-10-15 | 2025-10 | 266 | 266 | Yes | No | exact | Observed matched delay | 567 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53A/6 | 2025-01-23 | 2025-01 | 2025-07-27 | 2025-07 | 185 | 185 | Yes | No | exact | Observed matched delay | 566 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 51/0 | 2025-01-24 | 2025-01 | 2025-05-27 | 2025-05 | 123 | 123 | Yes | No | exact | Observed matched delay | 565 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53A/3 | 2025-01-25 | 2025-01 | 2025-06-20 | 2025-06 | 146 | 146 | Yes | No | exact | Observed matched delay | 564 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 27/0 | 2025-01-29 | 2025-01 | 2025-09-22 | 2025-09 | 236 | 236 | Yes | No | exact | Observed matched delay | 560 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 45/1 | 2025-01-30 | 2025-01 | 2025-06-10 | 2025-06 | 131 | 131 | Yes | No | exact | Observed matched delay | 559 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 0/2 | 2025-01-31 | 2025-01 | 2025-05-23 | 2025-05 | 112 | 112 | Yes | No | exact | Observed matched delay | 558 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 0/3 | 2025-01-31 | 2025-01 | 2025-05-25 | 2025-05 | 114 | 114 | Yes | No | exact | Observed matched delay | 558 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 21/3 | 2025-01-31 | 2025-01 | 2025-07-01 | 2025-07 | 151 | 151 | Yes | No | exact | Observed matched delay | 558 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/6 | 2025-01-31 | 2025-01 | 2025-04-05 | 2025-04 | 64 | 64 | Yes | No | exact | Observed matched delay | 558 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53/1 | 2025-02-03 | 2025-02 | 2025-05-12 | 2025-05 | 98 | 98 | Yes | No | exact | Observed matched delay | 555 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 24/0 | 2025-02-04 | 2025-02 | 2025-07-26 | 2025-07 | 172 | 172 | Yes | No | exact | Observed matched delay | 554 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 42/0 | 2025-02-05 | 2025-02 | 2025-09-23 | 2025-09 | 230 | 230 | Yes | No | exact | Observed matched delay | 553 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 35/6 | 2025-02-06 | 2025-02 | 2025-03-10 | 2025-03 | 32 | 32 | Yes | No | exact | Observed matched delay | 552 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 22/0 | 2025-02-07 | 2025-02 | 2025-06-12 | 2025-06 | 125 | 125 | Yes | No | exact | Observed matched delay | 551 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/2 | 2025-02-07 | 2025-02 | 2025-05-07 | 2025-05 | 89 | 89 | Yes | No | exact | Observed matched delay | 551 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 0/4 | 2025-02-09 | 2025-02 | 2025-04-12 | 2025-04 | 62 | 62 | Yes | No | exact | Observed matched delay | 549 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 29/0 | 2025-02-09 | 2025-02 | 2025-08-06 | 2025-08 | 178 | 178 | Yes | No | exact | Observed matched delay | 549 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/4 | 2025-02-10 | 2025-02 | 2025-04-26 | 2025-04 | 75 | 75 | Yes | No | exact | Observed matched delay | 548 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 0/1 | 2025-02-15 | 2025-02 | 2025-06-04 | 2025-06 | 109 | 109 | Yes | No | exact | Observed matched delay | 543 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 40/0 | 2025-02-15 | 2025-02 | 2025-06-04 | 2025-06 | 109 | 109 | Yes | No | exact | Observed matched delay | 543 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/5 | 2025-02-15 | 2025-02 | 2025-04-17 | 2025-04 | 61 | 61 | Yes | No | exact | Observed matched delay | 543 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 59/0 | 2025-02-15 | 2025-02 | 2025-11-16 | 2025-11 | 274 | 274 | Yes | No | exact | Observed matched delay | 543 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 25/0 | 2025-02-18 | 2025-02 | 2025-08-28 | 2025-08 | 191 | 191 | Yes | No | exact | Observed matched delay | 540 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 64/0 | 2025-02-18 | 2025-02 | 2025-08-31 | 2025-08 | 194 | 194 | Yes | No | exact | Observed matched delay | 540 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 30/0 | 2025-02-21 | 2025-02 | 2025-05-25 | 2025-05 | 93 | 93 | Yes | No | exact | Observed matched delay | 537 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 43/0 | 2025-02-21 | 2025-02 | 2025-08-10 | 2025-08 | 170 | 170 | Yes | No | exact | Observed matched delay | 537 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/2 | 2025-02-21 | 2025-02 | 2025-05-07 | 2025-05 | 75 | 75 | Yes | No | exact | Observed matched delay | 537 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/1 | 2025-02-22 | 2025-02 | 2025-03-31 | 2025-03 | 37 | 37 | Yes | No | exact | Observed matched delay | 536 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/3 | 2025-02-23 | 2025-02 | 2025-05-20 | 2025-05 | 86 | 86 | Yes | No | exact | Observed matched delay | 535 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 63/0 | 2025-02-27 | 2025-02 | 2025-10-01 | 2025-10 | 216 | 216 | Yes | No | exact | Observed matched delay | 531 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 11/0 | 2025-02-28 | 2025-02 | 2025-08-24 | 2025-08 | 177 | 177 | Yes | No | exact | Observed matched delay | 530 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 21/2 | 2025-02-28 | 2025-02 | 2025-06-21 | 2025-06 | 113 | 113 | Yes | No | exact | Observed matched delay | 530 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 53A/1 | 2025-02-28 | 2025-02 | 2025-09-18 | 2025-09 | 202 | 202 | Yes | No | exact | Observed matched delay | 530 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 13/0 | 2025-03-03 | 2025-03 | 2025-07-09 | 2025-07 | 128 | 128 | Yes | No | exact | Observed matched delay | 527 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 50/0 | 2025-03-04 | 2025-03 | 2025-09-25 | 2025-09 | 205 | 205 | Yes | No | exact | Observed matched delay | 526 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 23/0 | 2025-03-08 | 2025-03 | 2025-11-17 | 2025-11 | 254 | 254 | Yes | No | exact | Observed matched delay | 522 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 60/0 | 2025-03-08 | 2025-03 | 2025-11-08 | 2025-11 | 245 | 245 | Yes | No | exact | Observed matched delay | 522 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 14/0 | 2025-03-09 | 2025-03 | 2025-06-01 | 2025-06 | 84 | 84 | Yes | No | exact | Observed matched delay | 521 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 34/5 | 2025-03-09 | 2025-03 | 2025-06-12 | 2025-06 | 95 | 95 | Yes | No | exact | Observed matched delay | 521 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 12/0 | 2025-03-10 | 2025-03 | 2025-08-12 | 2025-08 | 155 | 155 | Yes | No | exact | Observed matched delay | 520 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/4 | 2025-03-11 | 2025-03 | 2025-05-23 | 2025-05 | 73 | 73 | Yes | No | exact | Observed matched delay | 519 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 61/0 | 2025-03-20 | 2025-03 | 2025-09-25 | 2025-09 | 189 | 189 | Yes | No | exact | Observed matched delay | 510 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 67/0 | 2025-03-20 | 2025-03 | 2026-02-09 | 2026-02 | 326 | 326 | Yes | No | exact | Observed matched delay | 510 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 52/1 | 2025-03-22 | 2025-03 | 2025-10-27 | 2025-10 | 219 | 219 | Yes | No | exact | Observed matched delay | 508 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 18/0 | 2025-03-25 | 2025-03 | 2025-08-04 | 2025-08 | 132 | 132 | Yes | No | exact | Observed matched delay | 505 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 64/3 | 2025-03-26 | 2025-03 | 2025-09-24 | 2025-09 | 182 | 182 | Yes | No | exact | Observed matched delay | 504 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 66/1 | 2025-03-26 | 2025-03 | 2025-11-27 | 2025-11 | 246 | 246 | Yes | No | exact | Observed matched delay | 504 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 62/0 | 2025-03-27 | 2025-03 | 2025-11-10 | 2025-11 | 228 | 228 | Yes | No | exact | Observed matched delay | 503 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 19/0 | 2025-03-30 | 2025-03 | 2025-08-31 | 2025-08 | 154 | 154 | Yes | No | exact | Observed matched delay | 500 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 56/6 | 2025-04-02 | 2025-04 | 2025-11-01 | 2025-11 | 213 | 213 | Yes | No | exact | Observed matched delay | 497 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 57/1 | 2025-04-02 | 2025-04 | 2025-12-07 | 2025-12 | 249 | 249 | Yes | No | exact | Observed matched delay | 497 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 21/1 | 2025-04-03 | 2025-04 | 2025-06-27 | 2025-06 | 85 | 85 | Yes | No | exact | Observed matched delay | 496 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 16/0 | 2025-04-10 | 2025-04 | 2025-08-16 | 2025-08 | 128 | 128 | Yes | No | exact | Observed matched delay | 489 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 66/0 A,B | 2025-04-10 | 2025-04 | 2025-12-05 | 2025-12 | 239 | 239 | Yes | No | alias | Observed matched delay | 489 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 66/0 C,D | 2025-04-10 | 2025-04 | 2025-12-05 | 2025-12 | 239 | 239 | Yes | No | alias | Observed matched delay | 489 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 68/0 | 2025-04-17 | 2025-04 | 2025-11-30 | 2025-11 | 227 | 227 | Yes | No | exact | Observed matched delay | 482 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 2/1 | 2025-04-21 | 2025-04 | 2025-05-12 | 2025-05 | 21 | 21 | Yes | No | exact | Observed matched delay | 478 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 44/0 | 2025-04-21 | 2025-04 | 2025-07-05 | 2025-07 | 75 | 75 | Yes | No | exact | Observed matched delay | 478 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 1/0 | 2025-04-27 | 2025-04 | 2025-08-09 | 2025-08 | 104 | 104 | Yes | No | exact | Observed matched delay | 472 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 65/0 | 2025-04-28 | 2025-04 | 2025-08-02 | 2025-08 | 96 | 96 | Yes | No | exact | Observed matched delay | 471 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 2/0 | 2025-04-29 | 2025-04 | 2025-09-03 | 2025-09 | 127 | 127 | Yes | No | exact | Observed matched delay | 470 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 2/2 | 2025-04-30 | 2025-04 | 2025-11-01 | 2025-11 | 185 | 185 | Yes | No | exact | Observed matched delay | 469 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/5 | 2025-05-11 | 2025-05 | 2025-05-28 | 2025-05 | 17 | 17 | Yes | No | exact | Observed matched delay | 458 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 45/0 | 2025-05-11 | 2025-05 | 2025-10-09 | 2025-10 | 151 | 151 | Yes | No | exact | Observed matched delay | 458 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 0/0 | 2025-05-17 | 2025-05 | 2025-10-03 | 2025-10 | 139 | 139 | Yes | No | exact | Observed matched delay | 452 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 69/0 | 2025-05-19 | 2025-05 | 2026-01-20 | 2026-01 | 246 | 246 | Yes | No | exact | Observed matched delay | 450 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 37/0 | 2025-05-23 | 2025-05 | 2025-09-23 | 2025-09 | 123 | 123 | Yes | No | exact | Observed matched delay | 446 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 69A/0 | 2025-05-28 | 2025-05 | 2025-11-15 | 2025-11 | 171 | 171 | Yes | No | exact | Observed matched delay | 441 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 38/0 | 2025-06-03 | 2025-06 | 2025-10-08 | 2025-10 | 127 | 127 | Yes | No | exact | Observed matched delay | 435 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 4/0-5/0 | 2025-10-14 | 2025-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 302 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 5/0-7/6 | 2025-10-22 | 2025-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 294 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 7/6-8B/0 | 2025-10-25 | 2025-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 291 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 34/0-35/0 | 2025-10-28 | 2025-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 288 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 35/0-36/0 | 2025-11-01 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 284 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 33/0-34/0 | 2025-11-04 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 281 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 31/0-33/0 | 2025-11-10 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 275 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 30/0-31/0 | 2025-11-16 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 269 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 12/0-14/0 | 2025-11-20 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 265 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 20/0-21/0 | 2025-11-30 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 255 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 19/0-20/0 | 2025-12-06 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 249 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 66/0 | 2025-12-19 | 2025-12 | 2025-12-05 | 2025-12 | -14 |  | Yes | Yes | exact | Negative delay excluded | 236 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress. | TA 416 - DPR - 2026-07-16.xlsx | Erection Compiled
TA 416 | 4xx | Government | ta416 | 0/0-2/0 | 2026-02-06 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 187 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 2/0-3/0 | 2026-02-10 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 183 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 36/0-37/0 | 2026-02-10 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 183 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 14/0-17/0 | 2026-02-14 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 179 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 37/0-38/11 | 2026-02-16 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 177 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 8B/0-12/0 | 2026-02-18 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 175 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 38/11-40/0 | 2026-02-20 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 173 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 21/0-25/0 | 2026-02-23 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 170 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 17/0-19/0 | 2026-02-28 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 165 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 25/0-30/0 | 2026-02-28 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 165 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 40/0-47/0 | 2026-05-03 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 101 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 52/1-53/0 | 2026-05-06 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 98 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 53/0-54/0 | 2026-05-09 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 95 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 54/0-56/6 | 2026-06-29 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 44 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 56/6-64/0 | 2026-07-03 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 40 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 64/0-Gantry | 2026-07-08 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 35 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 416 | 4xx | Government | ta416 | 52/1-64/0 | 2026-07-12 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 31 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 416 - DPR - 2026-07-16.xlsx | Progress.
TA 418 | 4xx | Government | ta418 | 33/10 | 2024-01-05 | 2024-01 | 2024-12-29 | 2024-12 | 359 | 359 | Yes | No | fallback_single_line | Observed matched delay | 950 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 40/4 | 2024-01-07 | 2024-01 | 2024-12-30 | 2024-12 | 358 | 358 | Yes | No | fallback_single_line | Observed matched delay | 948 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 42/1 | 2024-06-22 | 2024-06 | 2024-12-12 | 2024-12 | 173 | 173 | Yes | No | fallback_single_line | Observed matched delay | 781 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 42/2 | 2024-06-29 | 2024-06 | 2024-12-03 | 2024-12 | 157 | 157 | Yes | No | fallback_single_line | Observed matched delay | 774 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 54/4 | 2024-07-11 | 2024-07 | 2024-01-09 | 2024-01 | -184 |  | Yes | Yes | fallback_single_line | Negative delay excluded | 762 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 41/3 | 2024-07-12 | 2024-07 | 2024-12-06 | 2024-12 | 147 | 147 | Yes | No | fallback_single_line | Observed matched delay | 761 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 40/1 | 2024-07-16 | 2024-07 | 2024-11-26 | 2024-11 | 133 | 133 | Yes | No | fallback_single_line | Observed matched delay | 757 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 55/1 | 2024-07-16 | 2024-07 | 2025-01-16 | 2025-01 | 184 | 184 | Yes | No | fallback_single_line | Observed matched delay | 757 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 41/2 | 2024-07-23 | 2024-07 | 2025-02-12 | 2025-02 | 204 | 204 | Yes | No | fallback_single_line | Observed matched delay | 750 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 55/2 | 2024-07-23 | 2024-07 | 2025-01-25 | 2025-01 | 186 | 186 | Yes | No | fallback_single_line | Observed matched delay | 750 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 40/5 | 2024-07-26 | 2024-07 | 2025-05-29 | 2025-05 | 307 | 307 | Yes | No | fallback_single_line | Observed matched delay | 747 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 40/2 | 2024-07-31 | 2024-07 | 2024-12-02 | 2024-12 | 124 | 124 | Yes | No | fallback_single_line | Observed matched delay | 742 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 54/3 | 2024-08-02 | 2024-08 | 2025-02-12 | 2025-02 | 194 | 194 | Yes | No | fallback_single_line | Observed matched delay | 740 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 40/3 | 2024-08-03 | 2024-08 | 2025-04-02 | 2025-04 | 242 | 242 | Yes | No | fallback_single_line | Observed matched delay | 739 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/4 | 2024-08-06 | 2024-08 | 2024-11-19 | 2024-11 | 105 | 105 | Yes | No | fallback_single_line | Observed matched delay | 736 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 41/4 | 2024-08-10 | 2024-08 | 2024-12-12 | 2024-12 | 124 | 124 | Yes | No | fallback_single_line | Observed matched delay | 732 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 55/3 | 2024-08-10 | 2024-08 | 2025-01-24 | 2025-01 | 167 | 167 | Yes | No | fallback_single_line | Observed matched delay | 732 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/3 | 2024-08-11 | 2024-08 | 2025-05-30 | 2025-05 | 292 | 292 | Yes | No | fallback_single_line | Observed matched delay | 731 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/6 | 2024-08-21 | 2024-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 721 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 41/1 | 2024-08-26 | 2024-08 | 2025-02-06 | 2025-02 | 164 | 164 | Yes | No | fallback_single_line | Observed matched delay | 716 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/7 | 2024-08-27 | 2024-08 | 2024-12-19 | 2024-12 | 114 | 114 | Yes | No | fallback_single_line | Observed matched delay | 715 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/8 | 2024-09-03 | 2024-09 | 2025-01-31 | 2025-01 | 150 | 150 | Yes | No | fallback_single_line | Observed matched delay | 708 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 34/3 | 2024-09-08 | 2024-09 | 2024-11-14 | 2024-11 | 67 | 67 | Yes | No | fallback_single_line | Observed matched delay | 703 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/11 | 2024-09-10 | 2024-09 | 2024-12-19 | 2024-12 | 100 | 100 | Yes | No | fallback_single_line | Observed matched delay | 701 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 34/4 | 2024-09-12 | 2024-09 | 2025-05-22 | 2025-05 | 252 | 252 | Yes | No | fallback_single_line | Observed matched delay | 699 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 34/1 | 2024-09-16 | 2024-09 | 2024-10-09 | 2024-10 | 23 | 23 | Yes | No | fallback_single_line | Observed matched delay | 695 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 52/2 | 2024-09-19 | 2024-09 | 2025-12-17 | 2025-12 | 454 | 454 | Yes | No | fallback_single_line | Observed matched delay | 692 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/12 | 2024-09-28 | 2024-09 | 2024-10-28 | 2024-10 | 30 | 30 | Yes | No | fallback_single_line | Observed matched delay | 683 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/11 | 2024-10-03 | 2024-10 | 2025-05-11 | 2025-05 | 220 | 220 | Yes | No | fallback_single_line | Observed matched delay | 678 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/14 | 2024-10-11 | 2024-10 | 2024-01-07 | 2024-01 | -278 |  | Yes | Yes | fallback_single_line | Negative delay excluded | 670 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/8 | 2024-10-19 | 2024-10 | 2025-01-13 | 2025-01 | 86 | 86 | Yes | No | fallback_single_line | Observed matched delay | 662 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 34/0 | 2024-10-29 | 2024-10 | 2025-04-22 | 2025-04 | 175 | 175 | Yes | No | fallback_single_line | Observed matched delay | 652 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/7 | 2024-11-04 | 2024-11 | 2025-06-03 | 2025-06 | 211 | 211 | Yes | No | fallback_single_line | Observed matched delay | 646 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/9 | 2024-11-11 | 2024-11 | 2025-06-12 | 2025-06 | 213 | 213 | Yes | No | fallback_single_line | Observed matched delay | 639 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/06 | 2024-11-13 | 2024-11 | 2024-11-05 | 2024-11 | -8 |  | Yes | Yes | fallback_single_line | Negative delay excluded | 637 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/7 | 2024-11-22 | 2024-11 | 2025-03-12 | 2025-03 | 110 | 110 | Yes | No | fallback_single_line | Observed matched delay | 628 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/8 | 2024-11-27 | 2024-11 | 2025-06-09 | 2025-06 | 194 | 194 | Yes | No | fallback_single_line | Observed matched delay | 623 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 41/0 | 2024-12-05 | 2024-12 | 2025-02-21 | 2025-02 | 78 | 78 | Yes | No | fallback_single_line | Observed matched delay | 615 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 43/0 | 2024-12-18 | 2024-12 | 2025-02-26 | 2025-02 | 70 | 70 | Yes | No | fallback_single_line | Observed matched delay | 602 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 45/02 | 2024-12-20 | 2024-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 600 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/4 | 2024-12-24 | 2024-12 | 2025-01-16 | 2025-01 | 23 | 23 | Yes | No | fallback_single_line | Observed matched delay | 596 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 34/2 | 2024-12-26 | 2024-12 | 2025-01-24 | 2025-01 | 29 | 29 | Yes | No | fallback_single_line | Observed matched delay | 594 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 45/0 | 2024-12-30 | 2024-12 | 2025-03-18 | 2025-03 | 78 | 78 | Yes | No | fallback_single_line | Observed matched delay | 590 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/0 | 2025-01-11 | 2025-01 | 2025-03-03 | 2025-03 | 51 | 51 | Yes | No | fallback_single_line | Observed matched delay | 578 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/0 | 2025-01-13 | 2025-01 | 2025-05-08 | 2025-05 | 115 | 115 | Yes | No | fallback_single_line | Observed matched delay | 576 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/15 | 2025-01-13 | 2025-01 | 2025-04-27 | 2025-04 | 104 | 104 | Yes | No | fallback_single_line | Observed matched delay | 576 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 45/1 | 2025-01-21 | 2025-01 | 2025-03-18 | 2025-03 | 56 | 56 | Yes | No | fallback_single_line | Observed matched delay | 568 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/9 | 2025-01-23 | 2025-01 | 2025-03-06 | 2025-03 | 42 | 42 | Yes | No | fallback_single_line | Observed matched delay | 566 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/5 | 2025-01-24 | 2025-01 | 2025-04-11 | 2025-04 | 77 | 77 | Yes | No | fallback_single_line | Observed matched delay | 565 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/1 | 2025-02-01 | 2025-02 | 2025-09-22 | 2025-09 | 233 | 233 | Yes | No | fallback_single_line | Observed matched delay | 557 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 42/0 | 2025-02-03 | 2025-02 | 2025-04-05 | 2025-04 | 61 | 61 | Yes | No | fallback_single_line | Observed matched delay | 555 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/5 | 2025-02-10 | 2025-02 | 2025-05-11 | 2025-05 | 90 | 90 | Yes | No | fallback_single_line | Observed matched delay | 548 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 32/0 | 2025-02-16 | 2025-02 | 2025-10-04 | 2025-10 | 230 | 230 | Yes | No | fallback_single_line | Observed matched delay | 542 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 55/0 | 2025-02-19 | 2025-02 | 2025-04-18 | 2025-04 | 58 | 58 | Yes | No | fallback_single_line | Observed matched delay | 539 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 40/0 | 2025-02-20 | 2025-02 | 2025-07-03 | 2025-07 | 133 | 133 | Yes | No | fallback_single_line | Observed matched delay | 538 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 55/4 | 2025-02-24 | 2025-02 | 2025-04-12 | 2025-04 | 47 | 47 | Yes | No | fallback_single_line | Observed matched delay | 534 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 37/0 | 2025-03-01 | 2025-03 | 2025-07-03 | 2025-07 | 124 | 124 | Yes | No | fallback_single_line | Observed matched delay | 529 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 37/1 | 2025-03-02 | 2025-03 | 2025-04-29 | 2025-04 | 58 | 58 | Yes | No | fallback_single_line | Observed matched delay | 528 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 48A/0 | 2025-03-05 | 2025-03 | 2025-08-07 | 2025-08 | 155 | 155 | Yes | No | fallback_single_line | Observed matched delay | 525 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 60/4 | 2025-03-10 | 2025-03 | 2025-10-18 | 2025-10 | 222 | 222 | Yes | No | fallback_single_line | Observed matched delay | 520 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 37/2 | 2025-03-12 | 2025-03 | 2025-07-14 | 2025-07 | 124 | 124 | Yes | No | fallback_single_line | Observed matched delay | 518 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 47/1 | 2025-03-19 | 2025-03 | 2025-11-21 | 2025-11 | 247 | 247 | Yes | No | fallback_single_line | Observed matched delay | 511 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/2 | 2025-03-21 | 2025-03 | 2025-05-05 | 2025-05 | 45 | 45 | Yes | No | fallback_single_line | Observed matched delay | 509 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 38/1 | 2025-03-24 | 2025-03 | 2025-07-15 | 2025-07 | 113 | 113 | Yes | No | fallback_single_line | Observed matched delay | 506 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 54/2 | 2025-03-24 | 2025-03 | 2026-01-22 | 2026-01 | 304 | 304 | Yes | No | fallback_single_line | Observed matched delay | 506 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 45/2 | 2025-04-01 | 2025-04 | 2025-03-28 | 2025-03 | -4 |  | Yes | Yes | fallback_single_line | Negative delay excluded | 498 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 38/2 | 2025-04-04 | 2025-04 | 2025-07-03 | 2025-07 | 90 | 90 | Yes | No | fallback_single_line | Observed matched delay | 495 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 61/0 | 2025-04-04 | 2025-04 | 2025-09-14 | 2025-09 | 163 | 163 | Yes | No | fallback_single_line | Observed matched delay | 495 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 54/1 | 2025-04-11 | 2025-04 | 2025-09-28 | 2025-09 | 170 | 170 | Yes | No | fallback_single_line | Observed matched delay | 488 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 60/2 | 2025-04-18 | 2025-04 | 2025-08-26 | 2025-08 | 130 | 130 | Yes | No | fallback_single_line | Observed matched delay | 481 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 60/0 | 2025-04-25 | 2025-04 | 2025-11-30 | 2025-11 | 219 | 219 | Yes | No | fallback_single_line | Observed matched delay | 474 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 56/0 | 2025-05-01 | 2025-05 | 2025-09-05 | 2025-09 | 127 | 127 | Yes | No | fallback_single_line | Observed matched delay | 468 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/13 | 2025-05-05 | 2025-05 | 2025-08-09 | 2025-08 | 96 | 96 | Yes | No | fallback_single_line | Observed matched delay | 464 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 36/0 | 2025-05-11 | 2025-05 | 2025-06-19 | 2025-06 | 39 | 39 | Yes | No | fallback_single_line | Observed matched delay | 458 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 59/0 | 2025-05-14 | 2025-05 | 2026-01-07 | 2026-01 | 238 | 238 | Yes | No | fallback_single_line | Observed matched delay | 455 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/12 | 2025-05-15 | 2025-05 | 2025-09-03 | 2025-09 | 111 | 111 | Yes | No | fallback_single_line | Observed matched delay | 454 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 43/2 | 2025-05-19 | 2025-05 | 2025-11-06 | 2025-11 | 171 | 171 | Yes | No | fallback_single_line | Observed matched delay | 450 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 45/3 | 2025-05-23 | 2025-05 | 2025-09-09 | 2025-09 | 109 | 109 | Yes | No | fallback_single_line | Observed matched delay | 446 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 48/1 | 2025-05-23 | 2025-05 | 2025-08-16 | 2025-08 | 85 | 85 | Yes | No | fallback_single_line | Observed matched delay | 446 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 48/2 | 2025-05-24 | 2025-05 | 2025-09-09 | 2025-09 | 108 | 108 | Yes | No | fallback_single_line | Observed matched delay | 445 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 52/0 | 2025-05-26 | 2025-05 | 2025-08-19 | 2025-08 | 85 | 85 | Yes | No | fallback_single_line | Observed matched delay | 443 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 41/5 | 2025-06-01 | 2025-06 | 2025-07-24 | 2025-07 | 53 | 53 | Yes | No | fallback_single_line | Observed matched delay | 437 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/6 | 2025-06-02 | 2025-06 | 2025-06-14 | 2025-06 | 12 | 12 | Yes | No | fallback_single_line | Observed matched delay | 436 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/1 | 2025-06-03 | 2025-06 | 2025-07-21 | 2025-07 | 48 | 48 | Yes | No | fallback_single_line | Observed matched delay | 435 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/2 | 2025-06-09 | 2025-06 | 2025-06-29 | 2025-06 | 20 | 20 | Yes | No | fallback_single_line | Observed matched delay | 429 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/10 | 2025-06-10 | 2025-06 | 2025-08-07 | 2025-08 | 58 | 58 | Yes | No | fallback_single_line | Observed matched delay | 428 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/5 | 2025-06-11 | 2025-06 | 2025-07-22 | 2025-07 | 41 | 41 | Yes | No | fallback_single_line | Observed matched delay | 427 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/0 | 2025-06-16 | 2025-06 | 2025-10-16 | 2025-10 | 122 | 122 | Yes | No | fallback_single_line | Observed matched delay | 422 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 43/1 | 2025-06-18 | 2025-06 | 2025-08-18 | 2025-08 | 61 | 61 | Yes | No | fallback_single_line | Observed matched delay | 420 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/9 | 2025-06-20 | 2025-06 | 2025-07-21 | 2025-07 | 31 | 31 | Yes | No | fallback_single_line | Observed matched delay | 418 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 36/1 | 2025-06-20 | 2025-06 | 2025-08-06 | 2025-08 | 47 | 47 | Yes | No | fallback_single_line | Observed matched delay | 418 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/2 | 2025-06-21 | 2025-06 | 2025-09-12 | 2025-09 | 83 | 83 | Yes | No | fallback_single_line | Observed matched delay | 417 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 44/1 | 2025-06-24 | 2025-06 | 2025-11-23 | 2025-11 | 152 | 152 | Yes | No | fallback_single_line | Observed matched delay | 414 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 62/0 | 2025-06-25 | 2025-06 | 2025-09-01 | 2025-09 | 68 | 68 | Yes | No | fallback_single_line | Observed matched delay | 413 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 57/2 | 2025-06-27 | 2025-06 | 2026-01-29 | 2026-01 | 216 | 216 | Yes | No | fallback_single_line | Observed matched delay | 411 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/3 | 2025-06-30 | 2025-06 | 2025-08-31 | 2025-08 | 62 | 62 | Yes | No | fallback_single_line | Observed matched delay | 408 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/1 | 2025-06-30 | 2025-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 408 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 39/0 | 2025-07-01 | 2025-07 | 2025-10-16 | 2025-10 | 107 | 107 | Yes | No | fallback_single_line | Observed matched delay | 407 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/4 | 2025-07-02 | 2025-07 | 2025-11-12 | 2025-11 | 133 | 133 | Yes | No | fallback_single_line | Observed matched delay | 406 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 57/1 | 2025-07-02 | 2025-07 | 2025-12-26 | 2025-12 | 177 | 177 | Yes | No | fallback_single_line | Observed matched delay | 406 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/3 | 2025-07-03 | 2025-07 | 2025-08-22 | 2025-08 | 50 | 50 | Yes | No | fallback_single_line | Observed matched delay | 405 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/10 | 2025-07-05 | 2025-07 | 2025-10-29 | 2025-10 | 116 | 116 | Yes | No | fallback_single_line | Observed matched delay | 403 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 52/1 | 2025-07-05 | 2025-07 | 2025-12-10 | 2025-12 | 158 | 158 | Yes | No | fallback_single_line | Observed matched delay | 403 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 48/0 | 2025-07-08 | 2025-07 | 2025-11-11 | 2025-11 | 126 | 126 | Yes | No | fallback_single_line | Observed matched delay | 400 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/6 | 2025-07-09 | 2025-07 | 2025-11-04 | 2025-11 | 118 | 118 | Yes | No | fallback_single_line | Observed matched delay | 399 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 60/1 | 2025-07-10 | 2025-07 | 2025-12-16 | 2025-12 | 159 | 159 | Yes | No | fallback_single_line | Observed matched delay | 398 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 47/0 | 2025-07-13 | 2025-07 | 2025-12-01 | 2025-12 | 141 | 141 | Yes | No | fallback_single_line | Observed matched delay | 395 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 53/0 | 2025-07-14 | 2025-07 | 2025-09-16 | 2025-09 | 64 | 64 | Yes | No | fallback_single_line | Observed matched delay | 394 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 43/3 | 2025-07-16 | 2025-07 | 2026-02-20 | 2026-02 | 219 | 219 | Yes | No | fallback_single_line | Observed matched delay | 392 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 58/0 | 2025-07-16 | 2025-07 | 2025-12-26 | 2025-12 | 163 | 163 | Yes | No | fallback_single_line | Observed matched delay | 392 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 57/3 | 2025-07-18 | 2025-07 | 2026-01-08 | 2026-01 | 174 | 174 | Yes | No | fallback_single_line | Observed matched delay | 390 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 44/0 | 2025-07-20 | 2025-07 | 2025-09-25 | 2025-09 | 67 | 67 | Yes | No | fallback_single_line | Observed matched delay | 388 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/11 | 2025-07-23 | 2025-07 | 2025-12-04 | 2025-12 | 134 | 134 | Yes | No | fallback_single_line | Observed matched delay | 385 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 56/1 | 2025-07-29 | 2025-07 | 2025-12-07 | 2025-12 | 131 | 131 | Yes | No | fallback_single_line | Observed matched delay | 379 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 56/2 | 2025-08-03 | 2025-08 | 2025-12-15 | 2025-12 | 134 | 134 | Yes | No | fallback_single_line | Observed matched delay | 374 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 56/3 | 2025-08-06 | 2025-08 | 2025-12-20 | 2025-12 | 136 | 136 | Yes | No | fallback_single_line | Observed matched delay | 371 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 54/0 | 2025-08-29 | 2025-08 | 2025-09-29 | 2025-09 | 31 | 31 | Yes | No | fallback_single_line | Observed matched delay | 348 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 42/0 - 43/0 | 2025-09-28 | 2025-09 |  |  |  |  | No | No |  | Unmatched/right-censored | 318 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 41/0 - 42/0 | 2025-10-06 | 2025-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 310 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 36/0 - 36/1 | 2025-11-03 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 282 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 55/6 | 2025-11-10 | 2025-11 | 2026-01-08 | 2026-01 | 59 | 59 | Yes | No | fallback_single_line | Observed matched delay | 275 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 55/5 | 2025-11-15 | 2025-11 | 2026-01-20 | 2026-01 | 66 | 66 | Yes | No | fallback_single_line | Observed matched delay | 270 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 35/0 - 36/0 | 2025-11-17 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 268 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 51/0 | 2025-11-21 | 2025-11 | 2026-02-05 | 2026-02 | 76 | 76 | Yes | No | fallback_single_line | Observed matched delay | 264 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 50/0 | 2025-11-25 | 2025-11 | 2026-02-04 | 2026-02 | 71 | 71 | Yes | No | fallback_single_line | Observed matched delay | 260 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 48A/1 | 2025-11-27 | 2025-11 | 2025-12-23 | 2025-12 | 26 | 26 | Yes | No | fallback_single_line | Observed matched delay | 258 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 34/0 - 35/0 | 2025-11-30 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 255 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 49/0 | 2025-12-10 | 2025-12 | 2026-01-28 | 2026-01 | 49 | 49 | Yes | No | fallback_single_line | Observed matched delay | 245 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 48A/2 | 2025-12-13 | 2025-12 | 2025-12-31 | 2025-12 | 18 | 18 | Yes | No | fallback_single_line | Observed matched delay | 242 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 59/1 | 2025-12-16 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 239 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 57/0 | 2025-12-20 | 2025-12 | 2025-01-16 | 2025-01 | -338 |  | Yes | Yes | fallback_single_line | Negative delay excluded | 235 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 60/3 | 2025-12-23 | 2025-12 | 2026-01-16 | 2026-01 | 24 | 24 | Yes | No | fallback_single_line | Observed matched delay | 232 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 40/0 - 41/0 | 2025-12-26 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 229 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 63/0 | 2026-01-09 | 2026-01 | 2026-02-05 | 2026-02 | 27 | 27 | Yes | No | fallback_single_line | Observed matched delay | 215 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/6 - 34/0 | 2026-01-27 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 197 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/5 - 33/6 | 2026-01-30 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 194 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 33/0 - 33/5 | 2026-02-09 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 184 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 39/0-40/0 | 2026-02-10 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 183 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 38/0 | 2026-02-17 | 2026-02 | 2026-02-24 | 2026-02 | 7 | 7 | Yes | No | fallback_single_line | Observed matched delay | 176 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 32/0-33/0 | 2026-02-22 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 171 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 45/1-46/0 | 2026-03-03 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 162 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 43/0 - 44/0 | 2026-03-11 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 154 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 45/0 - 45/1 | 2026-03-12 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 153 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 44/0-45/0 | 2026-03-18 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 147 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 56/0-56/3 | 2026-03-31 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 134 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 61/0-62/0 | 2026-04-15 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 119 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 63/0-GNTY | 2026-04-18 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 116 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 55/0-56/0 | 2026-05-03 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 101 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 37/0-38/0 | 2026-05-12 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 92 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 36/01 - 37/00 | 2026-05-23 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 81 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 38/0-39/0 | 2026-05-26 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 78 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 52/00 - 53/00 | 2026-06-06 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 67 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 51/00 - 52/00 | 2026-06-08 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 65 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 56/03 - 57/00 | 2026-06-09 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 64 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 54/00 - 55/00 | 2026-06-19 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 54 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 53/00 - 54/00 | 2026-06-20 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 53 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 57/00 - 58/00 | 2026-06-23 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 50 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 48A/0-49/0 | 2026-06-26 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 47 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 62/0-63/0 | 2026-06-26 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 47 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 59/0 - 60/0 | 2026-06-27 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 46 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 58/0 - 59/0 | 2026-06-28 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 45 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 60/0-61/0 | 2026-07-04 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 39 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 48/0-48A/0 | 2026-07-05 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 38 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 47/0-48/0 | 2026-07-12 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 31 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 49/0-50/0 | 2026-07-12 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 31 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 50/0-51/0 | 2026-07-12 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 31 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 418 | 4xx | Government | ta418 | 46/0-46/7 | 2026-07-21 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 22 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 418 - DPR - 2026-07-21.xlsx | Progress
TA 419 | 4xx | Government | ta419 | 19/5 | 2024-05-24 | 2024-05 | 2025-02-03 | 2025-02 | 255 | 255 | Yes | No | exact | Observed matched delay | 810 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 19/4 | 2024-05-28 | 2024-05 | 2025-01-11 | 2025-01 | 228 | 228 | Yes | No | exact | Observed matched delay | 806 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 19/3 | 2024-05-29 | 2024-05 | 2025-01-18 | 2025-01 | 234 | 234 | Yes | No | exact | Observed matched delay | 805 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 19/1 | 2024-06-01 | 2024-06 | 2025-01-23 | 2025-01 | 236 | 236 | Yes | No | exact | Observed matched delay | 802 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 17/2 | 2024-06-04 | 2024-06 | 2025-01-31 | 2025-01 | 241 | 241 | Yes | No | exact | Observed matched delay | 799 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 17/1 | 2024-06-07 | 2024-06 | 2025-02-08 | 2025-02 | 246 | 246 | Yes | No | exact | Observed matched delay | 796 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 19/2 | 2024-06-09 | 2024-06 | 2024-11-19 | 2024-11 | 163 | 163 | Yes | No | exact | Observed matched delay | 794 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 20/1 | 2024-06-21 | 2024-06 | 2024-11-21 | 2024-11 | 153 | 153 | Yes | No | exact | Observed matched delay | 782 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 20/2 | 2024-06-23 | 2024-06 | 2024-11-28 | 2024-11 | 158 | 158 | Yes | No | exact | Observed matched delay | 780 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 11/4 | 2024-06-26 | 2024-06 | 2025-04-03 | 2025-04 | 281 | 281 | Yes | No | exact | Observed matched delay | 777 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 22/2 | 2024-06-29 | 2024-06 | 2024-12-04 | 2024-12 | 158 | 158 | Yes | No | exact | Observed matched delay | 774 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 11/3 | 2024-06-30 | 2024-06 | 2025-04-11 | 2025-04 | 285 | 285 | Yes | No | exact | Observed matched delay | 773 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 12/1 | 2024-07-07 | 2024-07 | 2025-03-26 | 2025-03 | 262 | 262 | Yes | No | exact | Observed matched delay | 766 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 23/1 | 2024-07-09 | 2024-07 | 2024-12-14 | 2024-12 | 158 | 158 | Yes | No | exact | Observed matched delay | 764 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 22/3 | 2024-07-10 | 2024-07 | 2024-12-09 | 2024-12 | 152 | 152 | Yes | No | exact | Observed matched delay | 763 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/10 | 2024-07-10 | 2024-07 | 2024-12-17 | 2024-12 | 160 | 160 | Yes | No | exact | Observed matched delay | 763 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 23/2 | 2024-07-14 | 2024-07 | 2024-12-18 | 2024-12 | 157 | 157 | Yes | No | exact | Observed matched delay | 759 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/9 | 2024-07-14 | 2024-07 | 2024-01-06 | 2024-01 | -190 |  | Yes | Yes | exact | Negative delay excluded | 759 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/8 | 2024-07-16 | 2024-07 | 2024-11-21 | 2024-11 | 128 | 128 | Yes | No | exact | Observed matched delay | 757 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/12 | 2024-07-18 | 2024-07 | 2024-12-22 | 2024-12 | 157 | 157 | Yes | No | exact | Observed matched delay | 755 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 23/3 | 2024-07-19 | 2024-07 | 2025-03-06 | 2025-03 | 230 | 230 | Yes | No | exact | Observed matched delay | 754 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 3/2 | 2024-07-21 | 2024-07 | 2025-07-29 | 2025-07 | 373 | 373 | Yes | No | exact | Observed matched delay | 752 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 26/4 | 2024-07-22 | 2024-07 | 2025-04-17 | 2025-04 | 269 | 269 | Yes | No | exact | Observed matched delay | 751 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 26/3 | 2024-07-25 | 2024-07 | 2025-04-12 | 2025-04 | 261 | 261 | Yes | No | exact | Observed matched delay | 748 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/3 | 2024-07-25 | 2024-07 | 2024-12-06 | 2024-12 | 134 | 134 | Yes | No | exact | Observed matched delay | 748 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 3/3 | 2024-07-26 | 2024-07 | 2025-10-06 | 2025-10 | 437 | 437 | Yes | No | exact | Observed matched delay | 747 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/6 | 2024-07-29 | 2024-07 | 2025-02-18 | 2025-02 | 204 | 204 | Yes | No | exact | Observed matched delay | 744 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 24/1 | 2024-07-30 | 2024-07 | 2025-01-03 | 2025-01 | 157 | 157 | Yes | No | exact | Observed matched delay | 743 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 3/5 | 2024-07-30 | 2024-07 | 2025-05-05 | 2025-05 | 279 | 279 | Yes | No | exact | Observed matched delay | 743 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 3/4 | 2024-08-04 | 2024-08 | 2025-09-28 | 2025-09 | 420 | 420 | Yes | No | exact | Observed matched delay | 738 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/2 | 2024-08-04 | 2024-08 | 2024-12-12 | 2024-12 | 130 | 130 | Yes | No | exact | Observed matched delay | 738 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 26/2 | 2024-08-07 | 2024-08 | 2025-07-28 | 2025-07 | 355 | 355 | Yes | No | exact | Observed matched delay | 735 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/5 | 2024-08-10 | 2024-08 | 2025-01-17 | 2025-01 | 160 | 160 | Yes | No | exact | Observed matched delay | 732 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 4/1 | 2024-08-11 | 2024-08 | 2025-04-28 | 2025-04 | 260 | 260 | Yes | No | exact | Observed matched delay | 731 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/11 | 2024-08-14 | 2024-08 | 2024-11-28 | 2024-11 | 106 | 106 | Yes | No | exact | Observed matched delay | 728 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 5/1 | 2024-08-17 | 2024-08 | 2025-04-07 | 2025-04 | 233 | 233 | Yes | No | exact | Observed matched delay | 725 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 5/3 | 2024-08-28 | 2024-08 | 2025-02-23 | 2025-02 | 179 | 179 | Yes | No | exact | Observed matched delay | 714 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 27/2 | 2024-09-01 | 2024-09 | 2025-06-12 | 2025-06 | 284 | 284 | Yes | No | exact | Observed matched delay | 710 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0D/3 | 2024-09-03 | 2024-09 | 2025-01-28 | 2025-01 | 147 | 147 | Yes | No | exact | Observed matched delay | 708 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 5/2 | 2024-09-04 | 2024-09 | 2025-03-24 | 2025-03 | 201 | 201 | Yes | No | exact | Observed matched delay | 707 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0D/2 | 2024-09-10 | 2024-09 | 2025-01-12 | 2025-01 | 124 | 124 | Yes | No | exact | Observed matched delay | 701 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 12/0 | 2024-09-16 | 2024-09 | 2025-04-19 | 2025-04 | 215 | 215 | Yes | No | exact | Observed matched delay | 695 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 4/0 | 2024-09-16 | 2024-09 | 2025-09-15 | 2025-09 | 364 | 364 | Yes | No | exact | Observed matched delay | 695 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0E/2 | 2024-09-18 | 2024-09 | 2025-01-04 | 2025-01 | 108 | 108 | Yes | No | exact | Observed matched delay | 693 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 7/0 | 2024-09-21 | 2024-09 | 2025-12-24 | 2025-12 | 459 | 459 | Yes | No | exact | Observed matched delay | 690 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/1 | 2024-09-23 | 2024-09 | 2025-01-11 | 2025-01 | 110 | 110 | Yes | No | exact | Observed matched delay | 688 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0E/1 | 2024-09-24 | 2024-09 | 2025-01-11 | 2025-01 | 109 | 109 | Yes | No | exact | Observed matched delay | 687 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 27/1 | 2024-09-26 | 2024-09 | 2025-06-05 | 2025-06 | 252 | 252 | Yes | No | exact | Observed matched delay | 685 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 24/2 | 2024-09-27 | 2024-09 | 2025-04-23 | 2025-04 | 208 | 208 | Yes | No | exact | Observed matched delay | 684 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0B/2 | 2024-09-28 | 2024-09 | 2024-12-04 | 2024-12 | 67 | 67 | Yes | No | exact | Observed matched delay | 683 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0D/1 | 2024-09-30 | 2024-09 | 2024-12-22 | 2024-12 | 83 | 83 | Yes | No | exact | Observed matched delay | 681 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0D/5 | 2024-09-30 | 2024-09 | 2025-02-07 | 2025-02 | 130 | 130 | Yes | No | exact | Observed matched delay | 681 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 12A/0 | 2024-09-30 | 2024-09 | 2025-04-28 | 2025-04 | 210 | 210 | Yes | No | exact | Observed matched delay | 681 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 5/0 | 2024-10-04 | 2024-10 | 2025-04-14 | 2025-04 | 192 | 192 | Yes | No | exact | Observed matched delay | 677 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0B/3 | 2024-10-07 | 2024-10 | 2025-01-19 | 2025-01 | 104 | 104 | Yes | No | exact | Observed matched delay | 674 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 23/0 | 2024-10-07 | 2024-10 | 2024-12-22 | 2024-12 | 76 | 76 | Yes | No | exact | Observed matched delay | 674 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0D/4 | 2024-10-11 | 2024-10 | 2025-02-08 | 2025-02 | 120 | 120 | Yes | No | exact | Observed matched delay | 670 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 5/4 | 2024-10-11 | 2024-10 | 2025-02-09 | 2025-02 | 121 | 121 | Yes | No | exact | Observed matched delay | 670 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 28/0 | 2024-10-12 | 2024-10 | 2025-06-27 | 2025-06 | 258 | 258 | Yes | No | exact | Observed matched delay | 669 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0D/0 | 2024-10-14 | 2024-10 | 2025-02-13 | 2025-02 | 122 | 122 | Yes | No | exact | Observed matched delay | 667 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 27/3 | 2024-10-14 | 2024-10 | 2025-06-21 | 2025-06 | 250 | 250 | Yes | No | exact | Observed matched delay | 667 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/4 | 2024-10-15 | 2024-10 | 2025-01-20 | 2025-01 | 97 | 97 | Yes | No | exact | Observed matched delay | 666 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 26/5 | 2024-10-16 | 2024-10 | 2025-03-31 | 2025-03 | 166 | 166 | Yes | No | exact | Observed matched delay | 665 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 26/6 | 2024-10-19 | 2024-10 | 2025-04-08 | 2025-04 | 171 | 171 | Yes | No | exact | Observed matched delay | 662 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0B/1 | 2024-10-22 | 2024-10 | 2025-02-19 | 2025-02 | 120 | 120 | Yes | No | exact | Observed matched delay | 659 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0C/0 | 2024-10-25 | 2024-10 | 2025-11-15 | 2025-11 | 386 | 386 | Yes | No | exact | Observed matched delay | 656 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0C/1 | 2024-10-25 | 2024-10 | 2025-01-20 | 2025-01 | 87 | 87 | Yes | No | exact | Observed matched delay | 656 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 27/0 | 2024-10-25 | 2024-10 | 2025-05-19 | 2025-05 | 206 | 206 | Yes | No | exact | Observed matched delay | 656 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 24/0 | 2024-10-27 | 2024-10 | 2025-03-08 | 2025-03 | 132 | 132 | Yes | No | exact | Observed matched delay | 654 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/0 | 2024-10-27 | 2024-10 | 2025-02-02 | 2025-02 | 98 | 98 | Yes | No | exact | Observed matched delay | 654 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0E/0 | 2024-10-28 | 2024-10 | 2025-12-03 | 2025-12 | 401 | 401 | Yes | No | exact | Observed matched delay | 653 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0B/0 | 2024-11-08 | 2024-11 | 2025-09-23 | 2025-09 | 319 | 319 | Yes | No | exact | Observed matched delay | 642 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 20/0 | 2024-11-08 | 2024-11 | 2025-02-07 | 2025-02 | 91 | 91 | Yes | No | exact | Observed matched delay | 642 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 18/0 | 2024-11-09 | 2024-11 | 2025-02-14 | 2025-02 | 97 | 97 | Yes | No | exact | Observed matched delay | 641 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 19/0 | 2024-11-13 | 2024-11 | 2025-01-27 | 2025-01 | 75 | 75 | Yes | No | exact | Observed matched delay | 637 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 24/3 | 2024-11-20 | 2024-11 | 2025-03-27 | 2025-03 | 127 | 127 | Yes | No | exact | Observed matched delay | 630 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 11/2 | 2024-11-22 | 2024-11 | 2025-08-31 | 2025-08 | 282 | 282 | Yes | No | exact | Observed matched delay | 628 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 12/2 | 2024-11-22 | 2024-11 | 2025-09-07 | 2025-09 | 289 | 289 | Yes | No | exact | Observed matched delay | 628 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 26/1 | 2024-11-22 | 2024-11 | 2025-03-22 | 2025-03 | 120 | 120 | Yes | No | exact | Observed matched delay | 628 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 17/0 | 2024-11-27 | 2024-11 | 2025-02-22 | 2025-02 | 87 | 87 | Yes | No | exact | Observed matched delay | 623 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 6/7 | 2024-11-28 | 2024-11 | 2025-01-27 | 2025-01 | 60 | 60 | Yes | No | exact | Observed matched delay | 622 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 3/1 | 2024-11-29 | 2024-11 | 2025-08-12 | 2025-08 | 256 | 256 | Yes | No | exact | Observed matched delay | 621 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/6 | 2024-11-29 | 2024-11 | 2025-10-23 | 2025-10 | 328 | 328 | Yes | No | exact | Observed matched delay | 621 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 7/1 | 2024-11-29 | 2024-11 | 2025-03-01 | 2025-03 | 92 | 92 | Yes | No | exact | Observed matched delay | 621 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0F/0 | 2024-11-30 | 2024-11 | 2025-02-25 | 2025-02 | 87 | 87 | Yes | No | exact | Observed matched delay | 620 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/7 | 2024-12-02 | 2024-12 | 2025-10-16 | 2025-10 | 318 | 318 | Yes | No | exact | Observed matched delay | 618 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 11/1 | 2024-12-09 | 2024-12 | 2025-08-04 | 2025-08 | 238 | 238 | Yes | No | exact | Observed matched delay | 611 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 15A/0 | 2024-12-10 | 2024-12 | 2025-03-02 | 2025-03 | 82 | 82 | Yes | No | exact | Observed matched delay | 610 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 22/1 | 2024-12-10 | 2024-12 | 2025-02-19 | 2025-02 | 71 | 71 | Yes | No | exact | Observed matched delay | 610 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0G/0 | 2024-12-11 | 2024-12 | 2025-08-15 | 2025-08 | 247 | 247 | Yes | No | exact | Observed matched delay | 609 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 16/0 | 2024-12-14 | 2024-12 | 2025-10-12 | 2025-10 | 302 | 302 | Yes | No | exact | Observed matched delay | 606 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 28/1 | 2024-12-17 | 2024-12 | 2025-04-12 | 2025-04 | 116 | 116 | Yes | No | exact | Observed matched delay | 603 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 30/1 | 2024-12-21 | 2024-12 | 2025-03-31 | 2025-03 | 100 | 100 | Yes | No | exact | Observed matched delay | 599 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 15/0 | 2024-12-23 | 2024-12 | 2026-05-20 | 2026-05 | 513 | 513 | Yes | No | exact | Observed matched delay | 597 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 31/0 | 2024-12-23 | 2024-12 | 2025-04-28 | 2025-04 | 126 | 126 | Yes | No | exact | Observed matched delay | 597 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0A/0 (CT) | 2024-12-24 | 2024-12 | 2025-01-27 | 2025-01 | 34 | 34 | Yes | No | exact | Observed matched delay | 596 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 31/1 | 2024-12-24 | 2024-12 | 2025-04-22 | 2025-04 | 119 | 119 | Yes | No | exact | Observed matched delay | 596 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 1/0 | 2025-01-04 | 2025-01 | 2025-08-01 | 2025-08 | 209 | 209 | Yes | No | exact | Observed matched delay | 585 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0H/0 | 2025-01-09 | 2025-01 | 2025-08-01 | 2025-08 | 204 | 204 | Yes | No | exact | Observed matched delay | 580 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 0G/1 | 2025-01-15 | 2025-01 | 2025-08-20 | 2025-08 | 217 | 217 | Yes | No | exact | Observed matched delay | 574 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 10/0 | 2025-01-18 | 2025-01 | 2025-08-14 | 2025-08 | 208 | 208 | Yes | No | exact | Observed matched delay | 571 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 22/0 | 2025-01-25 | 2025-01 | 2025-04-29 | 2025-04 | 94 | 94 | Yes | No | exact | Observed matched delay | 564 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/1 | 2025-01-28 | 2025-01 | 2025-07-26 | 2025-07 | 179 | 179 | Yes | No | exact | Observed matched delay | 561 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/2 | 2025-01-29 | 2025-01 | 2025-08-02 | 2025-08 | 185 | 185 | Yes | No | exact | Observed matched delay | 560 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/4 | 2025-02-07 | 2025-02 | 2026-06-08 | 2026-06 | 486 | 486 | Yes | No | exact | Observed matched delay | 551 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/8 | 2025-02-07 | 2025-02 | 2025-11-01 | 2025-11 | 267 | 267 | Yes | No | exact | Observed matched delay | 551 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/7 | 2025-02-11 | 2025-02 | 2025-11-12 | 2025-11 | 274 | 274 | Yes | No | exact | Observed matched delay | 547 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 62/2 | 2025-02-13 | 2025-02 | 2025-12-04 | 2025-12 | 294 | 294 | Yes | No | exact | Observed matched delay | 545 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/10 | 2025-02-15 | 2025-02 | 2025-12-04 | 2025-12 | 292 | 292 | Yes | No | exact | Observed matched delay | 543 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/5 | 2025-02-20 | 2025-02 | 2025-12-04 | 2025-12 | 287 | 287 | Yes | No | exact | Observed matched delay | 538 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 62/1 | 2025-02-22 | 2025-02 | 2025-11-15 | 2025-11 | 266 | 266 | Yes | No | exact | Observed matched delay | 536 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/6 | 2025-02-28 | 2025-02 | 2025-12-01 | 2025-12 | 276 | 276 | Yes | No | exact | Observed matched delay | 530 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/8 | 2025-02-28 | 2025-02 | 2025-12-11 | 2025-12 | 286 | 286 | Yes | No | exact | Observed matched delay | 530 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 62/5 | 2025-02-28 | 2025-02 | 2025-12-10 | 2025-12 | 285 | 285 | Yes | No | exact | Observed matched delay | 530 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 62/4 | 2025-03-05 | 2025-03 | 2025-11-29 | 2025-11 | 269 | 269 | Yes | No | exact | Observed matched delay | 525 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/0 | 2025-03-15 | 2025-03 | 2025-11-12 | 2025-11 | 242 | 242 | Yes | No | exact | Observed matched delay | 515 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/11 | 2025-03-26 | 2025-03 | 2025-12-10 | 2025-12 | 259 | 259 | Yes | No | exact | Observed matched delay | 504 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/9 | 2025-03-27 | 2025-03 | 2025-12-17 | 2025-12 | 265 | 265 | Yes | No | exact | Observed matched delay | 503 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 34/0 | 2025-03-29 | 2025-03 | 2025-07-01 | 2025-07 | 94 | 94 | Yes | No | exact | Observed matched delay | 501 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/0 | 2025-04-05 | 2025-04 | 2025-12-18 | 2025-12 | 257 | 257 | Yes | No | exact | Observed matched delay | 494 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 20/3 | 2025-04-08 | 2025-04 | 2025-07-19 | 2025-07 | 102 | 102 | Yes | No | exact | Observed matched delay | 491 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/6 | 2025-04-08 | 2025-04 | 2025-11-17 | 2025-11 | 223 | 223 | Yes | No | exact | Observed matched delay | 491 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 62/3 | 2025-04-08 | 2025-04 | 2025-12-28 | 2025-12 | 264 | 264 | Yes | No | exact | Observed matched delay | 491 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/3 | 2025-04-11 | 2025-04 | 2025-11-29 | 2025-11 | 232 | 232 | Yes | No | exact | Observed matched delay | 488 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/7 | 2025-04-14 | 2025-04 | 2025-12-10 | 2025-12 | 240 | 240 | Yes | No | exact | Observed matched delay | 485 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/5 | 2025-04-17 | 2025-04 | 2025-11-08 | 2025-11 | 205 | 205 | Yes | No | exact | Observed matched delay | 482 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/4 | 2025-04-21 | 2025-04 | 2025-11-24 | 2025-11 | 217 | 217 | Yes | No | exact | Observed matched delay | 478 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/2 | 2025-04-22 | 2025-04 | 2025-12-05 | 2025-12 | 227 | 227 | Yes | No | exact | Observed matched delay | 477 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 46/4 | 2025-04-22 | 2025-04 | 2025-12-04 | 2025-12 | 226 | 226 | Yes | No | exact | Observed matched delay | 477 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/9 | 2025-04-23 | 2025-04 | 2025-12-17 | 2025-12 | 238 | 238 | Yes | No | exact | Observed matched delay | 476 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/1 | 2025-04-24 | 2025-04 | 2025-12-10 | 2025-12 | 230 | 230 | Yes | No | exact | Observed matched delay | 475 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/7 | 2025-04-28 | 2025-04 | 2025-11-29 | 2025-11 | 215 | 215 | Yes | No | exact | Observed matched delay | 471 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/5 | 2025-04-29 | 2025-04 | 2025-11-08 | 2025-11 | 193 | 193 | Yes | No | exact | Observed matched delay | 470 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/8 | 2025-05-04 | 2025-05 | 2025-12-05 | 2025-12 | 215 | 215 | Yes | No | exact | Observed matched delay | 465 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/0 | 2025-05-07 | 2025-05 | 2026-06-21 | 2026-06 | 410 | 410 | Yes | No | exact | Observed matched delay | 462 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/3 | 2025-05-11 | 2025-05 | 2025-11-24 | 2025-11 | 197 | 197 | Yes | No | exact | Observed matched delay | 458 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/4 | 2025-05-12 | 2025-05 | 2025-11-15 | 2025-11 | 187 | 187 | Yes | No | exact | Observed matched delay | 457 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 84/1 | 2025-05-15 | 2025-05 | 2025-12-16 | 2025-12 | 215 | 215 | Yes | No | exact | Observed matched delay | 454 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 25/0 | 2025-05-19 | 2025-05 | 2026-04-14 | 2026-04 | 330 | 330 | Yes | No | exact | Observed matched delay | 450 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 83/6 | 2025-05-19 | 2025-05 | 2026-01-05 | 2026-01 | 231 | 231 | Yes | No | exact | Observed matched delay | 450 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 26/0 | 2025-05-21 | 2025-05 | 2025-10-06 | 2025-10 | 138 | 138 | Yes | No | exact | Observed matched delay | 448 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 83/7 | 2025-06-05 | 2025-06 | 2025-11-19 | 2025-11 | 167 | 167 | Yes | No | exact | Observed matched delay | 433 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 35/0 | 2025-06-06 | 2025-06 | 2025-10-27 | 2025-10 | 143 | 143 | Yes | No | exact | Observed matched delay | 432 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 3/0 | 2025-06-07 | 2025-06 | 2026-03-21 | 2026-03 | 287 | 287 | Yes | No | exact | Observed matched delay | 431 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/0 | 2025-06-07 | 2025-06 | 2025-11-12 | 2025-11 | 158 | 158 | Yes | No | exact | Observed matched delay | 431 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 34/1 | 2025-06-08 | 2025-06 | 2025-07-18 | 2025-07 | 40 | 40 | Yes | No | exact | Observed matched delay | 430 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 29/0 | 2025-06-15 | 2025-06 | 2025-07-09 | 2025-07 | 24 | 24 | Yes | No | exact | Observed matched delay | 423 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 83/5 | 2025-06-19 | 2025-06 | 2025-12-21 | 2025-12 | 185 | 185 | Yes | No | exact | Observed matched delay | 419 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 11/0 | 2025-06-23 | 2025-06 | 2025-11-05 | 2025-11 | 135 | 135 | Yes | No | exact | Observed matched delay | 415 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 78/3 | 2025-06-26 | 2025-06 | 2026-07-15 | 2026-07 | 384 | 384 | Yes | No | exact | Observed matched delay | 412 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 30/0 | 2025-06-27 | 2025-06 | 2025-10-26 | 2025-10 | 121 | 121 | Yes | No | exact | Observed matched delay | 411 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 84/4 | 2025-07-04 | 2025-07 | 2025-12-13 | 2025-12 | 162 | 162 | Yes | No | exact | Observed matched delay | 404 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 21/0 | 2025-07-08 | 2025-07 | 2025-09-14 | 2025-09 | 68 | 68 | Yes | No | exact | Observed matched delay | 400 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 2/0 | 2025-07-14 | 2025-07 | 2026-02-13 | 2026-02 | 214 | 214 | Yes | No | exact | Observed matched delay | 394 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 9/0 | 2025-07-23 | 2025-07 | 2025-12-13 | 2025-12 | 143 | 143 | Yes | No | exact | Observed matched delay | 385 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 8/0 | 2025-07-28 | 2025-07 | 2026-08-06 | 2026-08 | 374 | 374 | Yes | No | exact | Observed matched delay | 380 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/6 | 2025-08-03 | 2025-08 | 2025-12-17 | 2025-12 | 136 | 136 | Yes | No | exact | Observed matched delay | 374 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 46/0 | 2025-08-31 | 2025-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 346 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 46/1 | 2025-09-12 | 2025-09 | 2025-11-24 | 2025-11 | 73 | 73 | Yes | No | exact | Observed matched delay | 334 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 46/2 | 2025-09-16 | 2025-09 | 2025-11-12 | 2025-11 | 57 | 57 | Yes | No | exact | Observed matched delay | 330 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 46/3 | 2025-09-19 | 2025-09 | 2025-11-12 | 2025-11 | 54 | 54 | Yes | No | exact | Observed matched delay | 327 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 31/2 | 2025-10-03 | 2025-10 | 2025-10-14 | 2025-10 | 11 | 11 | Yes | No | exact | Observed matched delay | 313 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 78/1 | 2025-10-03 | 2025-10 | 2026-04-07 | 2026-04 | 186 | 186 | Yes | No | exact | Observed matched delay | 313 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 45/0 | 2025-10-09 | 2025-10 | 2025-12-12 | 2025-12 | 64 | 64 | Yes | No | exact | Observed matched delay | 307 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 78/0 | 2025-10-23 | 2025-10 | 2026-01-08 | 2026-01 | 77 | 77 | Yes | No | exact | Observed matched delay | 293 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 76/3 | 2025-10-24 | 2025-10 | 2025-11-19 | 2025-11 | 26 | 26 | Yes | No | exact | Observed matched delay | 292 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 83/1 | 2025-10-30 | 2025-10 | 2025-11-21 | 2025-11 | 22 | 22 | Yes | No | exact | Observed matched delay | 286 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 43/5 | 2025-11-04 | 2025-11 | 2025-11-19 | 2025-11 | 15 | 15 | Yes | No | exact | Observed matched delay | 281 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 43/3 | 2025-11-09 | 2025-11 | 2026-07-08 | 2026-07 | 241 | 241 | Yes | No | exact | Observed matched delay | 276 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 43/6 | 2025-11-09 | 2025-11 | 2025-12-03 | 2025-12 | 24 | 24 | Yes | No | exact | Observed matched delay | 276 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63/5 | 2025-11-09 | 2025-11 | 2026-05-20 | 2026-05 | 192 | 192 | Yes | No | exact | Observed matched delay | 276 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 43/0 | 2025-11-10 | 2025-11 | 2025-12-03 | 2025-12 | 23 | 23 | Yes | No | exact | Observed matched delay | 275 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 54/5 | 2025-11-11 | 2025-11 | 2026-04-19 | 2026-04 | 159 | 159 | Yes | No | exact | Observed matched delay | 274 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/10 | 2025-11-13 | 2025-11 | 2025-12-19 | 2025-12 | 36 | 36 | Yes | No | exact | Observed matched delay | 272 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 43/1 | 2025-11-13 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 272 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 43/2 | 2025-11-18 | 2025-11 | 2026-07-02 | 2026-07 | 226 | 226 | Yes | No | exact | Observed matched delay | 267 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 83/0 | 2025-11-20 | 2025-11 | 2025-12-09 | 2025-12 | 19 | 19 | Yes | No | exact | Observed matched delay | 265 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/9 | 2025-11-23 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 262 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 84/3 | 2025-11-24 | 2025-11 | 2025-12-26 | 2025-12 | 32 | 32 | Yes | No | exact | Observed matched delay | 261 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 43/4 | 2025-11-25 | 2025-11 | 2025-12-09 | 2025-12 | 14 | 14 | Yes | No | exact | Observed matched delay | 260 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 54/6 | 2025-11-25 | 2025-11 | 2025-12-08 | 2025-12 | 13 | 13 | Yes | No | exact | Observed matched delay | 260 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 12A/1 | 2025-11-28 | 2025-11 | 2025-12-12 | 2025-12 | 14 | 14 | Yes | No | exact | Observed matched delay | 257 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 83/8 | 2025-11-28 | 2025-11 | 2026-01-15 | 2026-01 | 48 | 48 | Yes | No | exact | Observed matched delay | 257 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63/4 | 2025-11-29 | 2025-11 | 2025-12-17 | 2025-12 | 18 | 18 | Yes | No | exact | Observed matched delay | 256 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 54/2 | 2025-11-30 | 2025-11 | 2026-04-13 | 2026-04 | 134 | 134 | Yes | No | exact | Observed matched delay | 255 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 55/6 | 2025-12-04 | 2025-12 | 2026-01-14 | 2026-01 | 41 | 41 | Yes | No | exact | Observed matched delay | 251 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 33/1 | 2025-12-07 | 2025-12 | 2025-12-28 | 2025-12 | 21 | 21 | Yes | No | exact | Observed matched delay | 248 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 54/4 | 2025-12-07 | 2025-12 | 2026-01-19 | 2026-01 | 43 | 43 | Yes | No | exact | Observed matched delay | 248 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63A/0 | 2025-12-07 | 2025-12 | 2025-12-30 | 2025-12 | 23 | 23 | Yes | No | exact | Observed matched delay | 248 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63/2 | 2025-12-09 | 2025-12 | 2025-12-29 | 2025-12 | 20 | 20 | Yes | No | exact | Observed matched delay | 246 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 55/5 | 2025-12-12 | 2025-12 | 2026-01-03 | 2026-01 | 22 | 22 | Yes | No | exact | Observed matched delay | 243 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 54/3 | 2025-12-13 | 2025-12 | 2025-12-22 | 2025-12 | 9 | 9 | Yes | No | exact | Observed matched delay | 242 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 84/5 | 2025-12-15 | 2025-12 | 2026-01-08 | 2026-01 | 24 | 24 | Yes | No | exact | Observed matched delay | 240 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 54/7 | 2025-12-18 | 2025-12 | 2026-04-01 | 2026-04 | 104 | 104 | Yes | No | exact | Observed matched delay | 237 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 64/1 | 2025-12-18 | 2025-12 | 2026-04-21 | 2026-04 | 124 | 124 | Yes | No | exact | Observed matched delay | 237 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 78/4 | 2025-12-18 | 2025-12 | 2025-12-26 | 2025-12 | 8 | 8 | Yes | No | exact | Observed matched delay | 237 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 57/1 | 2025-12-20 | 2025-12 | 2026-01-09 | 2026-01 | 20 | 20 | Yes | No | exact | Observed matched delay | 235 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 59/1 | 2025-12-26 | 2025-12 | 2026-01-09 | 2026-01 | 14 | 14 | Yes | No | exact | Observed matched delay | 229 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 84/0 | 2025-12-26 | 2025-12 | 2026-01-09 | 2026-01 | 14 | 14 | Yes | No | exact | Observed matched delay | 229 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 55/1 | 2025-12-27 | 2025-12 | 2026-01-03 | 2026-01 | 7 | 7 | Yes | No | exact | Observed matched delay | 228 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63/6 | 2025-12-28 | 2025-12 | 2026-01-20 | 2026-01 | 23 | 23 | Yes | No | exact | Observed matched delay | 227 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/5 | 2025-12-31 | 2025-12 | 2026-01-10 | 2026-01 | 10 | 10 | Yes | No | exact | Observed matched delay | 224 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63/0 | 2025-12-31 | 2025-12 | 2026-01-09 | 2026-01 | 9 | 9 | Yes | No | exact | Observed matched delay | 224 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63/1 | 2026-01-02 | 2026-01 | 2026-01-22 | 2026-01 | 20 | 20 | Yes | No | exact | Observed matched delay | 222 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63B/6 | 2026-01-02 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 222 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 62/0 | 2026-01-04 | 2026-01 | 2026-01-15 | 2026-01 | 11 | 11 | Yes | No | exact | Observed matched delay | 220 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 64/5 | 2026-01-04 | 2026-01 | 2026-04-30 | 2026-04 | 116 | 116 | Yes | No | exact | Observed matched delay | 220 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 84A/0 | 2026-01-07 | 2026-01 | 2026-01-19 | 2026-01 | 12 | 12 | Yes | No | exact | Observed matched delay | 217 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 36/3 | 2026-01-09 | 2026-01 | 2026-08-01 | 2026-08 | 204 | 204 | Yes | No | exact | Observed matched delay | 215 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 55/4 | 2026-01-10 | 2026-01 | 2026-01-14 | 2026-01 | 4 | 4 | Yes | No | exact | Observed matched delay | 214 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 55/0 | 2026-01-14 | 2026-01 | 2026-01-20 | 2026-01 | 6 | 6 | Yes | No | exact | Observed matched delay | 210 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63/3 | 2026-01-17 | 2026-01 | 2026-07-30 | 2026-07 | 194 | 194 | Yes | No | exact | Observed matched delay | 207 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 55/3 | 2026-01-18 | 2026-01 | 2026-04-10 | 2026-04 | 82 | 82 | Yes | No | exact | Observed matched delay | 206 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 64A/0 | 2026-01-18 | 2026-01 | 2026-05-25 | 2026-05 | 127 | 127 | Yes | No | exact | Observed matched delay | 206 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/1 | 2026-01-24 | 2026-01 | 2026-07-16 | 2026-07 | 173 | 173 | Yes | No | exact | Observed matched delay | 200 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 64/0 | 2026-02-01 | 2026-02 | 2026-07-29 | 2026-07 | 178 | 178 | Yes | No | exact | Observed matched delay | 192 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 55/2 | 2026-02-07 | 2026-02 | 2026-04-13 | 2026-04 | 65 | 65 | Yes | No | exact | Observed matched delay | 186 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63B/1 | 2026-02-07 | 2026-02 | 2026-04-26 | 2026-04 | 78 | 78 | Yes | No | exact | Observed matched delay | 186 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 64/2 | 2026-02-07 | 2026-02 | 2026-05-11 | 2026-05 | 93 | 93 | Yes | No | exact | Observed matched delay | 186 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 78A/0 | 2026-02-13 | 2026-02 | 2026-07-05 | 2026-07 | 142 | 142 | Yes | No | exact | Observed matched delay | 180 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 77/0 | 2026-02-19 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 174 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 42/0 | 2026-02-22 | 2026-02 | 2026-05-10 | 2026-05 | 77 | 77 | Yes | No | exact | Observed matched delay | 171 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 63B/0 | 2026-03-03 | 2026-03 | 2026-04-26 | 2026-04 | 54 | 54 | Yes | No | exact | Observed matched delay | 162 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 54/1 | 2026-03-16 | 2026-03 | 2026-04-03 | 2026-04 | 18 | 18 | Yes | No | exact | Observed matched delay | 149 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 33/0 | 2026-03-18 | 2026-03 | 2026-04-21 | 2026-04 | 34 | 34 | Yes | No | exact | Observed matched delay | 147 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 78/2 | 2026-03-25 | 2026-03 | 2026-04-13 | 2026-04 | 19 | 19 | Yes | No | exact | Observed matched delay | 140 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/8 | 2026-03-27 | 2026-03 | 2026-05-10 | 2026-05 | 44 | 44 | Yes | No | exact | Observed matched delay | 138 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 81/0 | 2026-03-29 | 2026-03 | 2026-05-03 | 2026-05 | 35 | 35 | Yes | No | exact | Observed matched delay | 136 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 13/0 | 2026-04-15 | 2026-04 | 2026-05-10 | 2026-05 | 25 | 25 | Yes | No | exact | Observed matched delay | 119 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 32/0 | 2026-04-20 | 2026-04 | 2026-05-25 | 2026-05 | 35 | 35 | Yes | No | exact | Observed matched delay | 114 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 14/0 | 2026-04-23 | 2026-04 | 2026-04-30 | 2026-04 | 7 | 7 | Yes | No | exact | Observed matched delay | 111 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 80/0 | 2026-04-25 | 2026-04 | 2026-08-12 | 2026-08 | 109 | 109 | Yes | No | exact | Observed matched delay | 109 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 76/2 | 2026-04-28 | 2026-04 | 2026-07-29 | 2026-07 | 92 | 92 | Yes | No | exact | Observed matched delay | 106 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 14/1 | 2026-04-29 | 2026-04 | 2026-05-13 | 2026-05 | 14 | 14 | Yes | No | exact | Observed matched delay | 105 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 40/1 | 2026-04-29 | 2026-04 | 2026-05-08 | 2026-05 | 9 | 9 | Yes | No | exact | Observed matched delay | 105 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 60/0 | 2026-04-30 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 104 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 64/3 | 2026-05-04 | 2026-05 | 2026-05-10 | 2026-05 | 6 | 6 | Yes | No | exact | Observed matched delay | 100 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 66/1 | 2026-05-04 | 2026-05 | 2026-06-27 | 2026-06 | 54 | 54 | Yes | No | exact | Observed matched delay | 100 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 41/2 | 2026-05-05 | 2026-05 | 2026-06-01 | 2026-06 | 27 | 27 | Yes | No | exact | Observed matched delay | 99 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 64/4 | 2026-05-08 | 2026-05 | 2026-05-31 | 2026-05 | 23 | 23 | Yes | No | exact | Observed matched delay | 96 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 53/0 | 2026-05-09 | 2026-05 | 2026-05-27 | 2026-05 | 18 | 18 | Yes | No | exact | Observed matched delay | 95 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 84/2 | 2026-05-10 | 2026-05 | 2026-07-20 | 2026-07 | 71 | 71 | Yes | No | exact | Observed matched delay | 94 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/3 | 2026-05-11 | 2026-05 | 2026-06-01 | 2026-06 | 21 | 21 | Yes | No | exact | Observed matched delay | 93 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 71/0 | 2026-05-11 | 2026-05 | 2026-06-06 | 2026-06 | 26 | 26 | Yes | No | exact | Observed matched delay | 93 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 65/0 | 2026-05-17 | 2026-05 | 2026-06-10 | 2026-06 | 24 | 24 | Yes | No | exact | Observed matched delay | 87 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 52/0 | 2026-05-18 | 2026-05 | 2026-06-22 | 2026-06 | 35 | 35 | Yes | No | exact | Observed matched delay | 86 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 67/0 | 2026-05-20 | 2026-05 | 2026-07-01 | 2026-07 | 42 | 42 | Yes | No | exact | Observed matched delay | 84 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 69/0 | 2026-05-20 | 2026-05 | 2026-07-27 | 2026-07 | 68 | 68 | Yes | No | exact | Observed matched delay | 84 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 54/0 | 2026-05-25 | 2026-05 | 2026-06-10 | 2026-06 | 16 | 16 | Yes | No | exact | Observed matched delay | 79 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 37/0 | 2026-05-26 | 2026-05 | 2026-06-10 | 2026-06 | 15 | 15 | Yes | No | exact | Observed matched delay | 78 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 68/0 | 2026-05-28 | 2026-05 | 2026-07-13 | 2026-07 | 46 | 46 | Yes | No | exact | Observed matched delay | 76 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 95A/0 | 2026-05-28 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 76 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 52/1 | 2026-05-31 | 2026-05 | 2026-04-03 | 2026-04 | -58 |  | Yes | Yes | exact | Negative delay excluded | 73 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 65/2 | 2026-05-31 | 2026-05 | 2026-06-12 | 2026-06 | 12 | 12 | Yes | No | exact | Observed matched delay | 73 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 70/0 | 2026-06-01 | 2026-06 | 2026-07-02 | 2026-07 | 31 | 31 | Yes | No | exact | Observed matched delay | 72 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 75/0 | 2026-06-01 | 2026-06 | 2026-06-25 | 2026-06 | 24 | 24 | Yes | No | exact | Observed matched delay | 72 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 72/0 | 2026-06-05 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 68 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 38/2 | 2026-06-06 | 2026-06 | 2026-06-14 | 2026-06 | 8 | 8 | Yes | No | exact | Observed matched delay | 67 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 65/1 | 2026-06-06 | 2026-06 | 2026-07-13 | 2026-07 | 37 | 37 | Yes | No | exact | Observed matched delay | 67 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 76/0 | 2026-06-06 | 2026-06 | 2026-06-10 | 2026-06 | 4 | 4 | Yes | No | exact | Observed matched delay | 67 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 73/0 | 2026-06-08 | 2026-06 | 2026-06-17 | 2026-06 | 9 | 9 | Yes | No | exact | Observed matched delay | 65 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 52/2 | 2026-06-09 | 2026-06 | 2026-06-14 | 2026-06 | 5 | 5 | Yes | No | exact | Observed matched delay | 64 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 76/1 | 2026-06-11 | 2026-06 | 2026-07-13 | 2026-07 | 32 | 32 | Yes | No | exact | Observed matched delay | 62 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 48/1 | 2026-06-13 | 2026-06 | 2026-07-01 | 2026-07 | 18 | 18 | Yes | No | exact | Observed matched delay | 60 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 44/0 | 2026-06-18 | 2026-06 | 2026-06-26 | 2026-06 | 8 | 8 | Yes | No | exact | Observed matched delay | 55 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 59/0 | 2026-06-23 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 50 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 63B/3 | 2026-06-23 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 50 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 74/0 | 2026-06-23 | 2026-06 | 2026-07-13 | 2026-07 | 20 | 20 | Yes | No | exact | Observed matched delay | 50 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 48/0 | 2026-06-24 | 2026-06 | 2026-07-09 | 2026-07 | 15 | 15 | Yes | No | exact | Observed matched delay | 49 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 39/0 | 2026-06-29 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 44 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 50/1 | 2026-07-02 | 2026-07 | 2026-07-17 | 2026-07 | 15 | 15 | Yes | No | exact | Observed matched delay | 41 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 66/0 | 2026-07-04 | 2026-07 | 2026-07-20 | 2026-07 | 16 | 16 | Yes | No | exact | Observed matched delay | 39 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 96/2 | 2026-07-04 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 39 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 50/0 | 2026-07-14 | 2026-07 | 2026-07-16 | 2026-07 | 2 | 2 | Yes | No | exact | Observed matched delay | 29 | FALSE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 96/0 | 2026-07-14 | 2026-07 | 2026-08-12 | 2026-08 | 29 | 29 | Yes | No | exact | Observed matched delay | 29 | FALSE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 79/0 | 2026-07-18 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 25 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 98/0 | 2026-07-18 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 25 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 57/0 | 2026-07-19 | 2026-07 | 2026-08-12 | 2026-08 | 24 | 24 | Yes | No | exact | Observed matched delay | 24 | FALSE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 38/4 | 2026-07-20 | 2026-07 | 2026-07-26 | 2026-07 | 6 | 6 | Yes | No | exact | Observed matched delay | 23 | FALSE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 47/0 | 2026-07-22 | 2026-07 | 2026-07-27 | 2026-07 | 5 | 5 | Yes | No | exact | Observed matched delay | 21 | FALSE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN | TA 419 - DPR - 2026-08-11.xlsx | ERECTION COMPILED
TA 419 | 4xx | Government | ta419 | 86/1 | 2026-07-23 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 20 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 93C/0 | 2026-07-25 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 18 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 51/0 | 2026-07-30 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 13 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 82/0 | 2026-07-31 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 12 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 419 | 4xx | Government | ta419 | 99/0 | 2026-08-04 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 8 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 419 - DPR - 2026-08-11.xlsx | FDN
TA 421 | 4xx | Government | ta421 | 24/4 | 2024-05-22 | 2024-05 | 2024-08-29 | 2024-08 | 99 | 99 | Yes | No | exact | Observed matched delay | 812 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 24/2 | 2024-06-02 | 2024-06 | 2024-12-03 | 2024-12 | 184 | 184 | Yes | No | exact | Observed matched delay | 801 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 24/3 | 2024-06-07 | 2024-06 | 2024-08-29 | 2024-08 | 83 | 83 | Yes | No | exact | Observed matched delay | 796 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 24/5 | 2024-06-11 | 2024-06 | 2024-08-22 | 2024-08 | 72 | 72 | Yes | No | exact | Observed matched delay | 792 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 24/6 | 2024-06-15 | 2024-06 | 2024-11-13 | 2024-11 | 151 | 151 | Yes | No | exact | Observed matched delay | 788 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 24/7 | 2024-06-19 | 2024-06 | 2024-10-27 | 2024-10 | 130 | 130 | Yes | No | exact | Observed matched delay | 784 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 23/4 | 2024-06-20 | 2024-06 | 2024-10-05 | 2024-10 | 107 | 107 | Yes | No | exact | Observed matched delay | 783 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 25/4 | 2024-06-22 | 2024-06 | 2024-07-10 | 2024-07 | 18 | 18 | Yes | No | exact | Observed matched delay | 781 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 25/5 | 2024-06-25 | 2024-06 | 2025-02-19 | 2025-02 | 239 | 239 | Yes | No | exact | Observed matched delay | 778 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 23/3 | 2024-06-27 | 2024-06 | 2024-10-16 | 2024-10 | 111 | 111 | Yes | No | exact | Observed matched delay | 776 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 25/1 | 2024-06-28 | 2024-06 | 2024-08-02 | 2024-08 | 35 | 35 | Yes | No | exact | Observed matched delay | 775 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 22/4 | 2024-06-29 | 2024-06 | 2024-10-17 | 2024-10 | 110 | 110 | Yes | No | exact | Observed matched delay | 774 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 24/8 | 2024-06-29 | 2024-06 | 2024-10-21 | 2024-10 | 114 | 114 | Yes | No | exact | Observed matched delay | 774 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/1 | 2024-06-29 | 2024-06 | 2024-12-20 | 2024-12 | 174 | 174 | Yes | No | exact | Observed matched delay | 774 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/3 | 2024-06-30 | 2024-06 | 2024-09-14 | 2024-09 | 76 | 76 | Yes | No | exact | Observed matched delay | 773 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 26/1 | 2024-07-04 | 2024-07 | 2024-07-18 | 2024-07 | 14 | 14 | Yes | No | exact | Observed matched delay | 769 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/4 | 2024-07-05 | 2024-07 | 2024-10-01 | 2024-10 | 88 | 88 | Yes | No | exact | Observed matched delay | 768 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 22/5 | 2024-07-06 | 2024-07 | 2024-08-23 | 2024-08 | 48 | 48 | Yes | No | exact | Observed matched delay | 767 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 26/3 | 2024-07-07 | 2024-07 | 2024-08-16 | 2024-08 | 40 | 40 | Yes | No | exact | Observed matched delay | 766 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/2 | 2024-07-10 | 2024-07 | 2024-10-19 | 2024-10 | 101 | 101 | Yes | No | exact | Observed matched delay | 763 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 23/2 | 2024-07-10 | 2024-07 | 2024-09-26 | 2024-09 | 78 | 78 | Yes | No | exact | Observed matched delay | 763 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 26/2 | 2024-07-10 | 2024-07 | 2024-08-09 | 2024-08 | 30 | 30 | Yes | No | exact | Observed matched delay | 763 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/11 | 2024-07-11 | 2024-07 | 2025-02-11 | 2025-02 | 215 | 215 | Yes | No | exact | Observed matched delay | 762 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 26/4 | 2024-07-13 | 2024-07 | 2024-07-27 | 2024-07 | 14 | 14 | Yes | No | exact | Observed matched delay | 760 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 22/3 | 2024-07-14 | 2024-07 | 2025-03-03 | 2025-03 | 232 | 232 | Yes | No | exact | Observed matched delay | 759 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 24/1 | 2024-07-16 | 2024-07 | 2024-11-15 | 2024-11 | 122 | 122 | Yes | No | exact | Observed matched delay | 757 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/7 | 2024-07-17 | 2024-07 | 2024-11-14 | 2024-11 | 120 | 120 | Yes | No | exact | Observed matched delay | 756 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 22/2 | 2024-07-17 | 2024-07 | 2024-10-29 | 2024-10 | 104 | 104 | Yes | No | exact | Observed matched delay | 756 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/1 | 2024-07-19 | 2024-07 | 2024-08-19 | 2024-08 | 31 | 31 | Yes | No | exact | Observed matched delay | 754 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/9 | 2024-07-22 | 2024-07 | 2024-09-09 | 2024-09 | 49 | 49 | Yes | No | exact | Observed matched delay | 751 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/6 | 2024-07-23 | 2024-07 | 2024-11-07 | 2024-11 | 107 | 107 | Yes | No | exact | Observed matched delay | 750 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/8 | 2024-07-30 | 2024-07 | 2024-10-01 | 2024-10 | 63 | 63 | Yes | No | exact | Observed matched delay | 743 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/5 | 2024-07-31 | 2024-07 | 2024-11-01 | 2024-11 | 93 | 93 | Yes | No | exact | Observed matched delay | 742 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/7 | 2024-07-31 | 2024-07 | 2024-09-12 | 2024-09 | 43 | 43 | Yes | No | exact | Observed matched delay | 742 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/8 | 2024-07-31 | 2024-07 | 2024-12-03 | 2024-12 | 125 | 125 | Yes | No | exact | Observed matched delay | 742 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/4 | 2024-08-05 | 2024-08 | 2024-09-19 | 2024-09 | 45 | 45 | Yes | No | exact | Observed matched delay | 737 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/5 | 2024-08-08 | 2024-08 | 2024-09-24 | 2024-09 | 47 | 47 | Yes | No | exact | Observed matched delay | 734 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/8 | 2024-08-11 | 2024-08 | 2024-11-12 | 2024-11 | 93 | 93 | Yes | No | exact | Observed matched delay | 731 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 23/0 | 2024-08-11 | 2024-08 | 2024-11-21 | 2024-11 | 102 | 102 | Yes | No | exact | Observed matched delay | 731 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/0 | 2024-08-11 | 2024-08 | 2024-11-24 | 2024-11 | 105 | 105 | Yes | No | exact | Observed matched delay | 731 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/6 | 2024-08-13 | 2024-08 | 2024-09-29 | 2024-09 | 47 | 47 | Yes | No | exact | Observed matched delay | 729 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/7 | 2024-08-13 | 2024-08 | 2024-10-03 | 2024-10 | 51 | 51 | Yes | No | exact | Observed matched delay | 729 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 26/0 | 2024-08-14 | 2024-08 | 2024-11-19 | 2024-11 | 97 | 97 | Yes | No | exact | Observed matched delay | 728 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/4 | 2024-08-16 | 2024-08 | 2024-11-16 | 2024-11 | 92 | 92 | Yes | No | exact | Observed matched delay | 726 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 25/0 | 2024-08-16 | 2024-08 | 2024-11-02 | 2024-11 | 78 | 78 | Yes | No | exact | Observed matched delay | 726 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 24/0 | 2024-08-17 | 2024-08 | 2024-11-02 | 2024-11 | 77 | 77 | Yes | No | exact | Observed matched delay | 725 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/2 | 2024-08-19 | 2024-08 | 2024-09-14 | 2024-09 | 26 | 26 | Yes | No | exact | Observed matched delay | 723 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/9 | 2024-08-22 | 2024-08 | 2024-10-01 | 2024-10 | 40 | 40 | Yes | No | exact | Observed matched delay | 720 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 22/1 | 2024-08-23 | 2024-08 | 2024-10-18 | 2024-10 | 56 | 56 | Yes | No | exact | Observed matched delay | 719 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/9 | 2024-08-23 | 2024-08 | 2025-04-29 | 2025-04 | 249 | 249 | Yes | No | exact | Observed matched delay | 719 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/4 | 2024-08-24 | 2024-08 | 2024-09-21 | 2024-09 | 28 | 28 | Yes | No | exact | Observed matched delay | 718 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 22/0 | 2024-08-25 | 2024-08 | 2024-11-05 | 2024-11 | 72 | 72 | Yes | No | exact | Observed matched delay | 717 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/5 | 2024-08-27 | 2024-08 | 2024-10-05 | 2024-10 | 39 | 39 | Yes | No | exact | Observed matched delay | 715 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/11 | 2024-08-28 | 2024-08 | 2024-12-12 | 2024-12 | 106 | 106 | Yes | No | exact | Observed matched delay | 714 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/3 | 2024-08-30 | 2024-08 | 2024-12-09 | 2024-12 | 101 | 101 | Yes | No | exact | Observed matched delay | 712 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/2 | 2024-08-31 | 2024-08 | 2024-11-26 | 2024-11 | 87 | 87 | Yes | No | exact | Observed matched delay | 711 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/0 | 2024-09-08 | 2024-09 | 2024-11-22 | 2024-11 | 75 | 75 | Yes | No | exact | Observed matched delay | 703 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/9 | 2024-09-11 | 2024-09 | 2025-06-06 | 2025-06 | 268 | 268 | Yes | No | exact | Observed matched delay | 700 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 30/4 | 2024-09-11 | 2024-09 | 2024-10-16 | 2024-10 | 35 | 35 | Yes | No | exact | Observed matched delay | 700 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/8 | 2024-09-16 | 2024-09 | 2024-12-15 | 2024-12 | 90 | 90 | Yes | No | exact | Observed matched delay | 695 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 23/1 | 2024-09-20 | 2024-09 | 2024-11-09 | 2024-11 | 50 | 50 | Yes | No | exact | Observed matched delay | 691 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/6 | 2024-09-20 | 2024-09 | 2025-01-16 | 2025-01 | 118 | 118 | Yes | No | exact | Observed matched delay | 691 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 30/5 | 2024-09-20 | 2024-09 | 2025-01-23 | 2025-01 | 125 | 125 | Yes | No | exact | Observed matched delay | 691 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/10 | 2024-09-22 | 2024-09 | 2024-10-27 | 2024-10 | 35 | 35 | Yes | No | exact | Observed matched delay | 689 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 30/1 | 2024-09-27 | 2024-09 | 2025-01-04 | 2025-01 | 99 | 99 | Yes | No | exact | Observed matched delay | 684 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/0 | 2024-09-30 | 2024-09 | 2025-03-08 | 2025-03 | 159 | 159 | Yes | No | exact | Observed matched delay | 681 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 30/3 | 2024-10-03 | 2024-10 | 2024-12-26 | 2024-12 | 84 | 84 | Yes | No | exact | Observed matched delay | 678 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 25/2 | 2024-10-04 | 2024-10 | 2024-11-08 | 2024-11 | 35 | 35 | Yes | No | exact | Observed matched delay | 677 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 19/3 | 2024-10-10 | 2024-10 | 2024-12-11 | 2024-12 | 62 | 62 | Yes | No | exact | Observed matched delay | 671 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 30/0 | 2024-10-12 | 2024-10 | 2025-06-03 | 2025-06 | 234 | 234 | Yes | No | exact | Observed matched delay | 669 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 12/1 | 2024-10-14 | 2024-10 | 2025-08-23 | 2025-08 | 313 | 313 | Yes | No | exact | Observed matched delay | 667 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 19/2 | 2024-10-17 | 2024-10 | 2024-12-16 | 2024-12 | 60 | 60 | Yes | No | exact | Observed matched delay | 664 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 27/3 | 2024-10-18 | 2024-10 | 2025-11-26 | 2025-11 | 404 | 404 | Yes | No | exact | Observed matched delay | 663 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 31/1 | 2024-10-21 | 2024-10 | 2025-01-28 | 2025-01 | 99 | 99 | Yes | No | exact | Observed matched delay | 660 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/7 | 2024-10-21 | 2024-10 | 2025-09-13 | 2025-09 | 327 | 327 | Yes | No | exact | Observed matched delay | 660 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 17/3 | 2024-10-24 | 2024-10 | 2025-04-12 | 2025-04 | 170 | 170 | Yes | No | exact | Observed matched delay | 657 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/1 | 2024-10-30 | 2024-10 | 2025-02-09 | 2025-02 | 102 | 102 | Yes | No | exact | Observed matched delay | 651 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/6 | 2024-10-30 | 2024-10 | 2024-12-03 | 2024-12 | 34 | 34 | Yes | No | exact | Observed matched delay | 651 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/0 | 2024-10-30 | 2024-10 | 2025-09-13 | 2025-09 | 318 | 318 | Yes | No | exact | Observed matched delay | 651 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 41/1 | 2024-11-07 | 2024-11 | 2025-10-22 | 2025-10 | 349 | 349 | Yes | No | exact | Observed matched delay | 643 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 15/2 | 2024-11-08 | 2024-11 | 2025-03-27 | 2025-03 | 139 | 139 | Yes | No | exact | Observed matched delay | 642 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/6 | 2024-11-13 | 2024-11 | 2025-01-16 | 2025-01 | 64 | 64 | Yes | No | exact | Observed matched delay | 637 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 18/3 | 2024-11-15 | 2024-11 | 2024-12-19 | 2024-12 | 34 | 34 | Yes | No | exact | Observed matched delay | 635 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 15/1 | 2024-11-16 | 2024-11 | 2025-03-23 | 2025-03 | 127 | 127 | Yes | No | exact | Observed matched delay | 634 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/1 | 2024-11-18 | 2024-11 | 2025-09-16 | 2025-09 | 302 | 302 | Yes | No | exact | Observed matched delay | 632 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/10 | 2024-11-19 | 2024-11 | 2025-01-02 | 2025-01 | 44 | 44 | Yes | No | exact | Observed matched delay | 631 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 15/4 | 2024-11-23 | 2024-11 | 2025-03-29 | 2025-03 | 126 | 126 | Yes | No | exact | Observed matched delay | 627 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/9 | 2024-11-24 | 2024-11 | 2025-02-22 | 2025-02 | 90 | 90 | Yes | No | exact | Observed matched delay | 626 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/4 | 2024-11-24 | 2024-11 | 2025-02-19 | 2025-02 | 87 | 87 | Yes | No | exact | Observed matched delay | 626 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 38/3 | 2024-11-24 | 2024-11 | 2025-03-03 | 2025-03 | 99 | 99 | Yes | No | exact | Observed matched delay | 626 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/6 | 2024-11-26 | 2024-11 | 2025-01-14 | 2025-01 | 49 | 49 | Yes | No | exact | Observed matched delay | 624 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 17/1 | 2024-11-26 | 2024-11 | 2025-01-03 | 2025-01 | 38 | 38 | Yes | No | exact | Observed matched delay | 624 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 38/1 | 2024-11-28 | 2024-11 | 2025-02-26 | 2025-02 | 90 | 90 | Yes | No | exact | Observed matched delay | 622 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/3 | 2024-11-29 | 2024-11 | 2025-02-13 | 2025-02 | 76 | 76 | Yes | No | exact | Observed matched delay | 621 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 18/0 | 2024-11-29 | 2024-11 | 2024-12-27 | 2024-12 | 28 | 28 | Yes | No | exact | Observed matched delay | 621 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/3 | 2024-11-29 | 2024-11 | 2025-07-06 | 2025-07 | 219 | 219 | Yes | No | exact | Observed matched delay | 621 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/8 | 2024-11-30 | 2024-11 | 2025-08-07 | 2025-08 | 250 | 250 | Yes | No | exact | Observed matched delay | 620 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/5 | 2024-11-30 | 2024-11 | 2025-02-28 | 2025-02 | 90 | 90 | Yes | No | exact | Observed matched delay | 620 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/9 | 2024-11-30 | 2024-11 | 2025-03-16 | 2025-03 | 106 | 106 | Yes | No | exact | Observed matched delay | 620 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 38/2 | 2024-11-30 | 2024-11 | 2025-05-02 | 2025-05 | 153 | 153 | Yes | No | exact | Observed matched delay | 620 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/9 | 2024-12-05 | 2024-12 | 2025-01-22 | 2025-01 | 48 | 48 | Yes | No | exact | Observed matched delay | 615 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/2 | 2024-12-06 | 2024-12 | 2025-02-04 | 2025-02 | 60 | 60 | Yes | No | exact | Observed matched delay | 614 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 18/1 | 2024-12-07 | 2024-12 | 2024-12-26 | 2024-12 | 19 | 19 | Yes | No | exact | Observed matched delay | 613 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 37/5 | 2024-12-07 | 2024-12 | 2025-03-29 | 2025-03 | 112 | 112 | Yes | No | exact | Observed matched delay | 613 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 35/2 | 2024-12-08 | 2024-12 | 2025-06-25 | 2025-06 | 199 | 199 | Yes | No | exact | Observed matched delay | 612 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 18/2 | 2024-12-09 | 2024-12 | 2024-12-23 | 2024-12 | 14 | 14 | Yes | No | exact | Observed matched delay | 611 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/2 | 2024-12-10 | 2024-12 | 2025-09-27 | 2025-09 | 291 | 291 | Yes | No | exact | Observed matched delay | 610 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/0 | 2024-12-11 | 2024-12 | 2025-08-01 | 2025-08 | 233 | 233 | Yes | No | exact | Observed matched delay | 609 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 31/3 | 2024-12-11 | 2024-12 | 2025-06-01 | 2025-06 | 172 | 172 | Yes | No | exact | Observed matched delay | 609 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/10 | 2024-12-12 | 2024-12 | 2025-03-20 | 2025-03 | 98 | 98 | Yes | No | exact | Observed matched delay | 608 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 38/4 | 2024-12-12 | 2024-12 | 2025-03-10 | 2025-03 | 88 | 88 | Yes | No | exact | Observed matched delay | 608 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/6 | 2024-12-13 | 2024-12 | 2025-02-24 | 2025-02 | 73 | 73 | Yes | No | exact | Observed matched delay | 607 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/5 | 2024-12-13 | 2024-12 | 2025-06-05 | 2025-06 | 174 | 174 | Yes | No | exact | Observed matched delay | 607 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/1 | 2024-12-14 | 2024-12 | 2024-12-28 | 2024-12 | 14 | 14 | Yes | No | exact | Observed matched delay | 606 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 31/5 | 2024-12-15 | 2024-12 | 2025-02-10 | 2025-02 | 57 | 57 | Yes | No | exact | Observed matched delay | 605 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/4 | 2024-12-15 | 2024-12 | 2025-06-24 | 2025-06 | 191 | 191 | Yes | No | exact | Observed matched delay | 605 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 35/3 | 2024-12-16 | 2024-12 | 2025-04-15 | 2025-04 | 120 | 120 | Yes | No | exact | Observed matched delay | 604 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 31/2 | 2024-12-19 | 2024-12 | 2025-02-21 | 2025-02 | 64 | 64 | Yes | No | exact | Observed matched delay | 601 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 38/5 | 2024-12-20 | 2024-12 | 2025-03-15 | 2025-03 | 85 | 85 | Yes | No | exact | Observed matched delay | 600 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 30/2 | 2024-12-21 | 2024-12 | 2024-12-02 | 2024-12 | -19 |  | Yes | Yes | exact | Negative delay excluded | 599 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/3 | 2024-12-22 | 2024-12 | 2025-03-13 | 2025-03 | 81 | 81 | Yes | No | exact | Observed matched delay | 598 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 38/7 | 2024-12-22 | 2024-12 | 2025-03-24 | 2025-03 | 92 | 92 | Yes | No | exact | Observed matched delay | 598 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/3 | 2024-12-23 | 2024-12 | 2025-06-29 | 2025-06 | 188 | 188 | Yes | No | exact | Observed matched delay | 597 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/11 | 2024-12-23 | 2024-12 | 2025-11-16 | 2025-11 | 328 | 328 | Yes | No | exact | Observed matched delay | 597 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 31/4 | 2024-12-23 | 2024-12 | 2025-02-04 | 2025-02 | 43 | 43 | Yes | No | exact | Observed matched delay | 597 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 37/4 | 2024-12-24 | 2024-12 | 2025-04-18 | 2025-04 | 115 | 115 | Yes | No | exact | Observed matched delay | 596 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 25/3 | 2024-12-25 | 2024-12 | 2025-02-10 | 2025-02 | 47 | 47 | Yes | No | exact | Observed matched delay | 595 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/10 | 2024-12-27 | 2024-12 | 2025-01-22 | 2025-01 | 26 | 26 | Yes | No | exact | Observed matched delay | 593 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 31/0 | 2024-12-28 | 2024-12 | 2025-03-02 | 2025-03 | 64 | 64 | Yes | No | exact | Observed matched delay | 592 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/2 | 2024-12-30 | 2024-12 | 2025-06-25 | 2025-06 | 177 | 177 | Yes | No | exact | Observed matched delay | 590 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 21/0 | 2024-12-30 | 2024-12 | 2025-05-03 | 2025-05 | 124 | 124 | Yes | No | exact | Observed matched delay | 590 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/8 | 2024-12-31 | 2024-12 | 2025-01-18 | 2025-01 | 18 | 18 | Yes | No | exact | Observed matched delay | 589 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 28/0 | 2024-12-31 | 2024-12 | 2025-04-24 | 2025-04 | 114 | 114 | Yes | No | exact | Observed matched delay | 589 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 38/6 | 2024-12-31 | 2024-12 | 2025-03-20 | 2025-03 | 79 | 79 | Yes | No | exact | Observed matched delay | 589 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/2 | 2025-01-03 | 2025-01 | 2025-01-19 | 2025-01 | 16 | 16 | Yes | No | exact | Observed matched delay | 586 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/7 | 2025-01-04 | 2025-01 | 2025-10-10 | 2025-10 | 279 | 279 | Yes | No | exact | Observed matched delay | 585 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/4 | 2025-01-05 | 2025-01 | 2025-10-23 | 2025-10 | 291 | 291 | Yes | No | exact | Observed matched delay | 584 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/7 | 2025-01-05 | 2025-01 | 2025-07-08 | 2025-07 | 184 | 184 | Yes | No | exact | Observed matched delay | 584 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 19/1 | 2025-01-05 | 2025-01 | 2025-03-28 | 2025-03 | 82 | 82 | Yes | No | exact | Observed matched delay | 584 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/8 | 2025-01-05 | 2025-01 | 2025-10-21 | 2025-10 | 289 | 289 | Yes | No | exact | Observed matched delay | 584 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/7 | 2025-01-06 | 2025-01 | 2025-02-26 | 2025-02 | 51 | 51 | Yes | No | exact | Observed matched delay | 583 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/6 | 2025-01-09 | 2025-01 | 2025-05-11 | 2025-05 | 122 | 122 | Yes | No | exact | Observed matched delay | 580 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/5 | 2025-01-10 | 2025-01 | 2025-01-30 | 2025-01 | 20 | 20 | Yes | No | exact | Observed matched delay | 579 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 31/6 | 2025-01-12 | 2025-01 | 2025-02-15 | 2025-02 | 34 | 34 | Yes | No | exact | Observed matched delay | 577 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/7 | 2025-01-13 | 2025-01 | 2025-03-03 | 2025-03 | 49 | 49 | Yes | No | exact | Observed matched delay | 576 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 38/0 | 2025-01-15 | 2025-01 | 2025-04-05 | 2025-04 | 80 | 80 | Yes | No | exact | Observed matched delay | 574 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 17/0 | 2025-01-16 | 2025-01 | 2025-05-10 | 2025-05 | 114 | 114 | Yes | No | exact | Observed matched delay | 573 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 33/0 | 2025-01-16 | 2025-01 | 2025-04-02 | 2025-04 | 76 | 76 | Yes | No | exact | Observed matched delay | 573 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 37/6 | 2025-01-16 | 2025-01 | 2025-05-11 | 2025-05 | 115 | 115 | Yes | No | exact | Observed matched delay | 573 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/1 | 2025-01-17 | 2025-01 | 2025-05-05 | 2025-05 | 108 | 108 | Yes | No | exact | Observed matched delay | 572 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 17/2 | 2025-01-18 | 2025-01 | 2025-04-27 | 2025-04 | 99 | 99 | Yes | No | exact | Observed matched delay | 571 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/5 | 2025-01-18 | 2025-01 | 2025-04-14 | 2025-04 | 86 | 86 | Yes | No | exact | Observed matched delay | 571 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 29/0 | 2025-01-19 | 2025-01 | 2025-04-19 | 2025-04 | 90 | 90 | Yes | No | exact | Observed matched delay | 570 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/2 | 2025-01-21 | 2025-01 | 2025-01-30 | 2025-01 | 9 | 9 | Yes | No | exact | Observed matched delay | 568 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 33/2 | 2025-01-22 | 2025-01 | 2025-06-05 | 2025-06 | 134 | 134 | Yes | No | exact | Observed matched delay | 567 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/4 | 2025-01-24 | 2025-01 | 2025-04-22 | 2025-04 | 88 | 88 | Yes | No | exact | Observed matched delay | 565 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/5 | 2025-01-24 | 2025-01 | 2025-08-08 | 2025-08 | 196 | 196 | Yes | No | exact | Observed matched delay | 565 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 33/1 | 2025-01-25 | 2025-01 | 2025-03-13 | 2025-03 | 47 | 47 | Yes | No | exact | Observed matched delay | 564 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 37/1 | 2025-01-25 | 2025-01 | 2025-12-13 | 2025-12 | 322 | 322 | Yes | No | exact | Observed matched delay | 564 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/0 | 2025-01-27 | 2025-01 | 2025-07-03 | 2025-07 | 157 | 157 | Yes | No | exact | Observed matched delay | 562 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 32/1 | 2025-01-27 | 2025-01 | 2025-03-08 | 2025-03 | 40 | 40 | Yes | No | exact | Observed matched delay | 562 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/6 | 2025-01-28 | 2025-01 | 2025-10-14 | 2025-10 | 259 | 259 | Yes | No | exact | Observed matched delay | 561 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 32/2 | 2025-01-29 | 2025-01 | 2025-03-23 | 2025-03 | 53 | 53 | Yes | No | exact | Observed matched delay | 560 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/2 | 2025-01-30 | 2025-01 | 2025-05-14 | 2025-05 | 104 | 104 | Yes | No | exact | Observed matched delay | 559 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 14/0 | 2025-01-30 | 2025-01 | 2025-07-05 | 2025-07 | 156 | 156 | Yes | No | exact | Observed matched delay | 559 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/3 | 2025-01-30 | 2025-01 | 2025-03-01 | 2025-03 | 30 | 30 | Yes | No | exact | Observed matched delay | 559 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 37/2 | 2025-01-30 | 2025-01 | 2025-04-24 | 2025-04 | 84 | 84 | Yes | No | exact | Observed matched delay | 559 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 19/0 | 2025-01-31 | 2025-01 | 2025-05-15 | 2025-05 | 104 | 104 | Yes | No | exact | Observed matched delay | 558 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 35/1 | 2025-01-31 | 2025-01 | 2025-05-08 | 2025-05 | 97 | 97 | Yes | No | exact | Observed matched delay | 558 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/8 | 2025-01-31 | 2025-01 | 2025-11-06 | 2025-11 | 279 | 279 | Yes | No | exact | Observed matched delay | 558 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 35/4 | 2025-02-02 | 2025-02 | 2025-04-10 | 2025-04 | 67 | 67 | Yes | No | exact | Observed matched delay | 556 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/1 | 2025-02-04 | 2025-02 | 2025-05-18 | 2025-05 | 103 | 103 | Yes | No | exact | Observed matched delay | 554 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/1 | 2025-02-06 | 2025-02 | 2025-03-30 | 2025-03 | 52 | 52 | Yes | No | exact | Observed matched delay | 552 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/10 | 2025-02-06 | 2025-02 | 2025-07-08 | 2025-07 | 152 | 152 | Yes | No | exact | Observed matched delay | 552 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/0 | 2025-02-09 | 2025-02 | 2025-11-08 | 2025-11 | 272 | 272 | Yes | No | exact | Observed matched delay | 549 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/9 | 2025-02-09 | 2025-02 | 2025-09-01 | 2025-09 | 204 | 204 | Yes | No | exact | Observed matched delay | 549 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/0 | 2025-02-10 | 2025-02 | 2025-04-03 | 2025-04 | 52 | 52 | Yes | No | exact | Observed matched delay | 548 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 37/0 | 2025-02-10 | 2025-02 | 2025-11-20 | 2025-11 | 283 | 283 | Yes | No | exact | Observed matched delay | 548 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/4 | 2025-02-12 | 2025-02 | 2025-05-10 | 2025-05 | 87 | 87 | Yes | No | exact | Observed matched delay | 546 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 32/0 | 2025-02-13 | 2025-02 | 2025-03-17 | 2025-03 | 32 | 32 | Yes | No | exact | Observed matched delay | 545 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 36/2 | 2025-02-14 | 2025-02 | 2025-04-06 | 2025-04 | 51 | 51 | Yes | No | exact | Observed matched delay | 544 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/7 | 2025-02-14 | 2025-02 | 2025-07-17 | 2025-07 | 153 | 153 | Yes | No | exact | Observed matched delay | 544 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/3 | 2025-02-15 | 2025-02 | 2025-05-21 | 2025-05 | 95 | 95 | Yes | No | exact | Observed matched delay | 543 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/5 | 2025-02-16 | 2025-02 | 2025-05-29 | 2025-05 | 102 | 102 | Yes | No | exact | Observed matched delay | 542 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/0 | 2025-02-16 | 2025-02 | 2025-07-13 | 2025-07 | 147 | 147 | Yes | No | exact | Observed matched delay | 542 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/5 | 2025-02-16 | 2025-02 | 2025-07-26 | 2025-07 | 160 | 160 | Yes | No | exact | Observed matched delay | 542 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 39/9 | 2025-02-18 | 2025-02 | 2025-11-27 | 2025-11 | 282 | 282 | Yes | No | exact | Observed matched delay | 540 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/9 | 2025-02-19 | 2025-02 | 2025-05-07 | 2025-05 | 77 | 77 | Yes | No | exact | Observed matched delay | 539 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 35/0 | 2025-02-20 | 2025-02 | 2025-07-17 | 2025-07 | 147 | 147 | Yes | No | exact | Observed matched delay | 538 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/8 | 2025-02-20 | 2025-02 | 2025-07-13 | 2025-07 | 143 | 143 | Yes | No | exact | Observed matched delay | 538 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/8 | 2025-02-21 | 2025-02 | 2025-03-12 | 2025-03 | 19 | 19 | Yes | No | exact | Observed matched delay | 537 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/4 | 2025-02-21 | 2025-02 | 2025-07-12 | 2025-07 | 141 | 141 | Yes | No | exact | Observed matched delay | 537 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/6 | 2025-02-21 | 2025-02 | 2025-08-05 | 2025-08 | 165 | 165 | Yes | No | exact | Observed matched delay | 537 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/7 | 2025-02-23 | 2025-02 | 2025-05-01 | 2025-05 | 67 | 67 | Yes | No | exact | Observed matched delay | 535 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/5 | 2025-02-23 | 2025-02 | 2025-07-30 | 2025-07 | 157 | 157 | Yes | No | exact | Observed matched delay | 535 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/6 | 2025-02-24 | 2025-02 | 2025-07-21 | 2025-07 | 147 | 147 | Yes | No | exact | Observed matched delay | 534 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 10/6 | 2025-02-25 | 2025-02 | 2025-06-19 | 2025-06 | 114 | 114 | Yes | No | exact | Observed matched delay | 533 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/4 | 2025-02-27 | 2025-02 | 2025-08-13 | 2025-08 | 167 | 167 | Yes | No | exact | Observed matched delay | 531 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/7 | 2025-02-28 | 2025-02 | 2025-08-16 | 2025-08 | 169 | 169 | Yes | No | exact | Observed matched delay | 530 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/3 | 2025-02-28 | 2025-02 | 2025-10-07 | 2025-10 | 221 | 221 | Yes | No | exact | Observed matched delay | 530 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/3 | 2025-03-01 | 2025-03 | 2025-07-21 | 2025-07 | 142 | 142 | Yes | No | exact | Observed matched delay | 529 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 15/0 | 2025-03-04 | 2025-03 | 2025-06-24 | 2025-06 | 112 | 112 | Yes | No | exact | Observed matched delay | 526 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/4 | 2025-03-04 | 2025-03 | 2025-04-19 | 2025-04 | 46 | 46 | Yes | No | exact | Observed matched delay | 526 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/2 | 2025-03-04 | 2025-03 | 2025-08-19 | 2025-08 | 168 | 168 | Yes | No | exact | Observed matched delay | 526 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 40/0 | 2025-03-06 | 2025-03 | 2025-08-13 | 2025-08 | 160 | 160 | Yes | No | exact | Observed matched delay | 524 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/2 | 2025-03-07 | 2025-03 | 2025-10-17 | 2025-10 | 224 | 224 | Yes | No | exact | Observed matched delay | 523 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/1 | 2025-03-07 | 2025-03 | 2025-08-12 | 2025-08 | 158 | 158 | Yes | No | exact | Observed matched delay | 523 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/5 | 2025-03-08 | 2025-03 | 2025-04-22 | 2025-04 | 45 | 45 | Yes | No | exact | Observed matched delay | 522 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 32/3 | 2025-03-08 | 2025-03 | 2025-03-28 | 2025-03 | 20 | 20 | Yes | No | exact | Observed matched delay | 522 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 40/1 | 2025-03-12 | 2025-03 | 2025-08-30 | 2025-08 | 171 | 171 | Yes | No | exact | Observed matched delay | 518 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/1 | 2025-03-13 | 2025-03 | 2025-04-11 | 2025-04 | 29 | 29 | Yes | No | exact | Observed matched delay | 517 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/15 | 2025-03-13 | 2025-03 | 2025-08-31 | 2025-08 | 171 | 171 | Yes | No | exact | Observed matched delay | 517 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 16/3 | 2025-03-18 | 2025-03 | 2025-04-16 | 2025-04 | 29 | 29 | Yes | No | exact | Observed matched delay | 512 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/14 | 2025-03-18 | 2025-03 | 2025-07-22 | 2025-07 | 126 | 126 | Yes | No | exact | Observed matched delay | 512 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/7 | 2025-03-19 | 2025-03 | 2025-10-28 | 2025-10 | 223 | 223 | Yes | No | exact | Observed matched delay | 511 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 9/0 | 2025-03-24 | 2025-03 | 2025-08-14 | 2025-08 | 143 | 143 | Yes | No | exact | Observed matched delay | 506 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 34/1 | 2025-03-26 | 2025-03 | 2025-08-04 | 2025-08 | 131 | 131 | Yes | No | exact | Observed matched delay | 504 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/12 | 2025-03-28 | 2025-03 | 2025-08-08 | 2025-08 | 133 | 133 | Yes | No | exact | Observed matched delay | 502 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 13/11 | 2025-03-30 | 2025-03 | 2025-04-28 | 2025-04 | 29 | 29 | Yes | No | exact | Observed matched delay | 500 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 15/3 | 2025-04-08 | 2025-04 | 2025-04-25 | 2025-04 | 17 | 17 | Yes | No | exact | Observed matched delay | 491 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 34/2 | 2025-04-11 | 2025-04 | 2025-07-05 | 2025-07 | 85 | 85 | Yes | No | exact | Observed matched delay | 488 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 11/8 | 2025-04-14 | 2025-04 | 2025-11-15 | 2025-11 | 215 | 215 | Yes | No | exact | Observed matched delay | 485 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 6/2 | 2025-04-18 | 2025-04 | 2025-07-19 | 2025-07 | 92 | 92 | Yes | No | exact | Observed matched delay | 481 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 37/3 | 2025-04-19 | 2025-04 | 2025-05-06 | 2025-05 | 17 | 17 | Yes | No | exact | Observed matched delay | 480 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 6/1 | 2025-04-22 | 2025-04 | 2025-07-22 | 2025-07 | 91 | 91 | Yes | No | exact | Observed matched delay | 477 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 20/0 | 2025-04-25 | 2025-04 | 2025-05-10 | 2025-05 | 15 | 15 | Yes | No | exact | Observed matched delay | 474 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 6/6 | 2025-04-27 | 2025-04 | 2025-08-02 | 2025-08 | 97 | 97 | Yes | No | exact | Observed matched delay | 472 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/1 | 2025-04-28 | 2025-04 | 2025-07-29 | 2025-07 | 92 | 92 | Yes | No | exact | Observed matched delay | 471 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 6/7 | 2025-04-29 | 2025-04 | 2025-12-14 | 2025-12 | 229 | 229 | Yes | No | exact | Observed matched delay | 470 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 20A/0 | 2025-04-30 | 2025-04 | 2025-06-20 | 2025-06 | 51 | 51 | Yes | No | exact | Observed matched delay | 469 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 34/0 | 2025-05-03 | 2025-05 | 2025-06-17 | 2025-06 | 45 | 45 | Yes | No | exact | Observed matched delay | 466 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/8 | 2025-05-03 | 2025-05 | 2025-07-30 | 2025-07 | 88 | 88 | Yes | No | exact | Observed matched delay | 466 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/7 | 2025-05-04 | 2025-05 | 2025-09-08 | 2025-09 | 127 | 127 | Yes | No | exact | Observed matched delay | 465 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/7 | 2025-05-04 | 2025-05 | 2025-08-03 | 2025-08 | 91 | 91 | Yes | No | exact | Observed matched delay | 465 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/8 | 2025-05-07 | 2025-05 | 2026-01-03 | 2026-01 | 241 | 241 | Yes | No | exact | Observed matched delay | 462 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/9 | 2025-05-08 | 2025-05 | 2025-09-08 | 2025-09 | 123 | 123 | Yes | No | exact | Observed matched delay | 461 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/9 | 2025-05-11 | 2025-05 | 2025-09-10 | 2025-09 | 122 | 122 | Yes | No | exact | Observed matched delay | 458 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 41/0 | 2025-05-11 | 2025-05 | 2025-09-06 | 2025-09 | 118 | 118 | Yes | No | exact | Observed matched delay | 458 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/5 | 2025-05-12 | 2025-05 | 2025-12-05 | 2025-12 | 207 | 207 | Yes | No | exact | Observed matched delay | 457 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/6 | 2025-05-13 | 2025-05 | 2025-09-05 | 2025-09 | 115 | 115 | Yes | No | exact | Observed matched delay | 456 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/10 | 2025-05-13 | 2025-05 | 2025-11-20 | 2025-11 | 191 | 191 | Yes | No | exact | Observed matched delay | 456 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/9 | 2025-05-15 | 2025-05 | 2025-09-07 | 2025-09 | 115 | 115 | Yes | No | exact | Observed matched delay | 454 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/6 | 2025-05-15 | 2025-05 | 2025-07-14 | 2025-07 | 60 | 60 | Yes | No | exact | Observed matched delay | 454 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/12 | 2025-05-16 | 2025-05 | 2025-09-09 | 2025-09 | 116 | 116 | Yes | No | exact | Observed matched delay | 453 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/3 | 2025-05-17 | 2025-05 | 2025-10-10 | 2025-10 | 146 | 146 | Yes | No | exact | Observed matched delay | 452 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 6/3 | 2025-05-19 | 2025-05 | 2025-07-15 | 2025-07 | 57 | 57 | Yes | No | exact | Observed matched delay | 450 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/19 | 2025-05-20 | 2025-05 | 2025-10-17 | 2025-10 | 150 | 150 | Yes | No | exact | Observed matched delay | 449 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/5 | 2025-05-20 | 2025-05 | 2025-11-28 | 2025-11 | 192 | 192 | Yes | No | exact | Observed matched delay | 449 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 6/4 | 2025-05-20 | 2025-05 | 2025-07-11 | 2025-07 | 52 | 52 | Yes | No | exact | Observed matched delay | 449 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/18 | 2025-05-21 | 2025-05 | 2025-09-28 | 2025-09 | 130 | 130 | Yes | No | exact | Observed matched delay | 448 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43A/2 | 2025-05-22 | 2025-05 | 2026-01-08 | 2026-01 | 231 | 231 | Yes | No | exact | Observed matched delay | 447 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/11 | 2025-05-22 | 2025-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 447 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 6/5 | 2025-05-23 | 2025-05 | 2025-07-04 | 2025-07 | 42 | 42 | Yes | No | exact | Observed matched delay | 446 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/4 | 2025-05-25 | 2025-05 | 2025-10-17 | 2025-10 | 145 | 145 | Yes | No | exact | Observed matched delay | 444 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43A/3 | 2025-05-25 | 2025-05 | 2025-11-23 | 2025-11 | 182 | 182 | Yes | No | exact | Observed matched delay | 444 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/17 | 2025-05-27 | 2025-05 | 2025-09-16 | 2025-09 | 112 | 112 | Yes | No | exact | Observed matched delay | 442 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/14 | 2025-05-28 | 2025-05 | 2025-11-18 | 2025-11 | 174 | 174 | Yes | No | exact | Observed matched delay | 441 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43A/4 | 2025-05-28 | 2025-05 | 2025-11-18 | 2025-11 | 174 | 174 | Yes | No | exact | Observed matched delay | 441 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/15 | 2025-05-30 | 2025-05 | 2025-11-21 | 2025-11 | 175 | 175 | Yes | No | exact | Observed matched delay | 439 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/13 | 2025-05-30 | 2025-05 | 2025-08-05 | 2025-08 | 67 | 67 | Yes | No | exact | Observed matched delay | 439 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 3/3 | 2025-05-31 | 2025-05 | 2025-12-20 | 2025-12 | 203 | 203 | Yes | No | exact | Observed matched delay | 438 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/0 | 2025-05-31 | 2025-05 | 2025-09-05 | 2025-09 | 97 | 97 | Yes | No | exact | Observed matched delay | 438 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/16 | 2025-05-31 | 2025-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 438 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 43A/5 | 2025-05-31 | 2025-05 | 2025-11-11 | 2025-11 | 164 | 164 | Yes | No | exact | Observed matched delay | 438 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/13 | 2025-06-01 | 2025-06 | 2025-10-31 | 2025-10 | 152 | 152 | Yes | No | exact | Observed matched delay | 437 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/2 | 2025-06-03 | 2025-06 | 2025-09-21 | 2025-09 | 110 | 110 | Yes | No | exact | Observed matched delay | 435 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43/3 | 2025-06-04 | 2025-06 | 2025-10-07 | 2025-10 | 125 | 125 | Yes | No | exact | Observed matched delay | 434 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 3/0 | 2025-06-06 | 2025-06 | 2025-11-11 | 2025-11 | 158 | 158 | Yes | No | exact | Observed matched delay | 432 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 1B/3 | 2025-06-08 | 2025-06 | 2025-12-07 | 2025-12 | 182 | 182 | Yes | No | exact | Observed matched delay | 430 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 28/1 | 2025-06-08 | 2025-06 | 2026-01-07 | 2026-01 | 213 | 213 | Yes | No | exact | Observed matched delay | 430 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43/2 | 2025-06-09 | 2025-06 | 2025-09-24 | 2025-09 | 107 | 107 | Yes | No | exact | Observed matched delay | 429 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 2/5 | 2025-06-14 | 2025-06 | 2025-12-24 | 2025-12 | 193 | 193 | Yes | No | exact | Observed matched delay | 424 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 42/8 | 2025-06-14 | 2025-06 | 2025-09-01 | 2025-09 | 79 | 79 | Yes | No | exact | Observed matched delay | 424 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 1B/2 | 2025-06-15 | 2025-06 | 2025-12-04 | 2025-12 | 172 | 172 | Yes | No | exact | Observed matched delay | 423 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 4/1 | 2025-06-15 | 2025-06 | 2025-10-22 | 2025-10 | 129 | 129 | Yes | No | exact | Observed matched delay | 423 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 3/1 | 2025-06-17 | 2025-06 | 2025-11-06 | 2025-11 | 142 | 142 | Yes | No | exact | Observed matched delay | 421 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 1B/0 | 2025-06-19 | 2025-06 | 2025-12-09 | 2025-12 | 173 | 173 | Yes | No | exact | Observed matched delay | 419 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 1A/0 | 2025-06-21 | 2025-06 | 2025-08-20 | 2025-08 | 60 | 60 | Yes | No | exact | Observed matched delay | 417 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 1B/1 | 2025-06-21 | 2025-06 | 2025-11-30 | 2025-11 | 162 | 162 | Yes | No | exact | Observed matched delay | 417 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 3/2 | 2025-06-21 | 2025-06 | 2025-12-17 | 2025-12 | 179 | 179 | Yes | No | exact | Observed matched delay | 417 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43/1 | 2025-06-21 | 2025-06 | 2025-10-26 | 2025-10 | 127 | 127 | Yes | No | exact | Observed matched delay | 417 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 2/3 | 2025-06-23 | 2025-06 | 2025-08-31 | 2025-08 | 69 | 69 | Yes | No | exact | Observed matched delay | 415 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43/4 | 2025-06-24 | 2025-06 | 2025-09-21 | 2025-09 | 89 | 89 | Yes | No | exact | Observed matched delay | 414 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/2 | 2025-06-25 | 2025-06 | 2025-12-17 | 2025-12 | 175 | 175 | Yes | No | exact | Observed matched delay | 413 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 1C/0 | 2025-06-29 | 2025-06 | 2025-12-26 | 2025-12 | 180 | 180 | Yes | No | exact | Observed matched delay | 409 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 2/1 | 2025-06-29 | 2025-06 | 2025-12-11 | 2025-12 | 165 | 165 | Yes | No | exact | Observed matched delay | 409 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43/0 | 2025-06-30 | 2025-06 | 2025-12-01 | 2025-12 | 154 | 154 | Yes | No | exact | Observed matched delay | 408 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 2/2 | 2025-07-03 | 2025-07 | 2025-09-25 | 2025-09 | 84 | 84 | Yes | No | exact | Observed matched delay | 405 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/4 | 2025-07-08 | 2025-07 | 2025-11-10 | 2025-11 | 125 | 125 | Yes | No | exact | Observed matched delay | 400 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 2/0 | 2025-07-10 | 2025-07 | 2025-12-31 | 2025-12 | 174 | 174 | Yes | No | exact | Observed matched delay | 398 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 2/4 | 2025-07-12 | 2025-07 | 2025-12-22 | 2025-12 | 163 | 163 | Yes | No | exact | Observed matched delay | 396 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 6/0 | 2025-07-13 | 2025-07 | 2025-11-27 | 2025-11 | 137 | 137 | Yes | No | exact | Observed matched delay | 395 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43/5 | 2025-07-14 | 2025-07 | 2025-10-12 | 2025-10 | 90 | 90 | Yes | No | exact | Observed matched delay | 394 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 5/0 | 2025-07-16 | 2025-07 | 2025-09-21 | 2025-09 | 67 | 67 | Yes | No | exact | Observed matched delay | 392 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/3 | 2025-07-18 | 2025-07 | 2025-11-04 | 2025-11 | 109 | 109 | Yes | No | exact | Observed matched delay | 390 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43A/1 | 2025-07-20 | 2025-07 | 2025-12-30 | 2025-12 | 163 | 163 | Yes | No | exact | Observed matched delay | 388 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/1 | 2025-07-22 | 2025-07 | 2025-12-27 | 2025-12 | 158 | 158 | Yes | No | exact | Observed matched delay | 386 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43B/0 | 2025-07-28 | 2025-07 | 2025-11-04 | 2025-11 | 99 | 99 | Yes | No | exact | Observed matched delay | 380 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 43A/0 | 2025-08-03 | 2025-08 | 2025-12-19 | 2025-12 | 138 | 138 | Yes | No | exact | Observed matched delay | 374 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 1/0 | 2025-08-25 | 2025-08 | 2025-10-01 | 2025-10 | 37 | 37 | Yes | No | exact | Observed matched delay | 352 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 19/0-20/0 | 2025-10-19 | 2025-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 297 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 18/0-19/0 | 2025-10-21 | 2025-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 295 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 44/0 | 2025-10-26 | 2025-10 | 2025-12-10 | 2025-12 | 45 | 45 | Yes | No | exact | Observed matched delay | 290 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 7/0 | 2025-11-26 | 2025-11 | 2025-12-09 | 2025-12 | 13 | 13 | Yes | No | exact | Observed matched delay | 259 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 8/0 | 2025-12-05 | 2025-12 | 2025-12-22 | 2025-12 | 17 | 17 | Yes | No | exact | Observed matched delay | 250 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet | TA 421 - DPR - 2026-07-11.xlsx | Erection Compiled
TA 421 | 4xx | Government | ta421 | 7/0 - 8/0 | 2026-01-31 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 193 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | Gantry - 1/0 | 2026-02-01 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 192 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 8/2 - 8/3 | 2026-02-04 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 189 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 1/0-1A/0 | 2026-02-08 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 185 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 1A/0 - 1B/0 | 2026-02-11 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 182 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 4/12 - 5/0 | 2026-02-12 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 181 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 8/0 - 8/1 | 2026-02-19 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 174 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 8/1-8/2 | 2026-02-19 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 174 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 1C/0 - 2/0 | 2026-02-25 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 168 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 5/0 - 6/0 | 2026-03-02 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 163 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 3/0-4/0 | 2026-03-14 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 151 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 43A/0 - 43A/1 | 2026-06-18 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 55 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 43A/1 - 43B/0 | 2026-06-21 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 52 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 421 | 4xx | Government | ta421 | 43B/0 - 44/0 | 2026-06-24 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 49 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 421 - DPR - 2026-07-11.xlsx | ProGress Sheet
TA 505 | 5xx | Government | ta505 | 164/3 | 2024-03-28 | 2024-03 | 2025-12-25 | 2025-12 | 637 | 637 | Yes | No | exact | Observed matched delay | 867 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/4 | 2024-04-04 | 2024-04 | 2026-01-04 | 2026-01 | 640 | 640 | Yes | No | exact | Observed matched delay | 860 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 136/0 | 2024-04-28 | 2024-04 | 2025-09-19 | 2025-09 | 509 | 509 | Yes | No | exact | Observed matched delay | 836 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/2 | 2024-10-06 | 2024-10 | 2025-01-14 | 2025-01 | 100 | 100 | Yes | No | exact | Observed matched delay | 675 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 109/2 | 2024-10-07 | 2024-10 | 2025-02-25 | 2025-02 | 141 | 141 | Yes | No | exact | Observed matched delay | 674 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/3 | 2024-10-11 | 2024-10 | 2025-01-24 | 2025-01 | 105 | 105 | Yes | No | exact | Observed matched delay | 670 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110A/2 | 2024-10-11 | 2024-10 | 2025-09-10 | 2025-09 | 334 | 334 | Yes | No | exact | Observed matched delay | 670 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/4 | 2024-10-21 | 2024-10 | 2025-01-27 | 2025-01 | 98 | 98 | Yes | No | exact | Observed matched delay | 660 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/6 | 2024-10-24 | 2024-10 | 2025-03-15 | 2025-03 | 142 | 142 | Yes | No | exact | Observed matched delay | 657 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/5 | 2024-10-25 | 2024-10 | 2025-02-01 | 2025-02 | 99 | 99 | Yes | No | exact | Observed matched delay | 656 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 108/4 | 2024-10-28 | 2024-10 | 2025-04-03 | 2025-04 | 157 | 157 | Yes | No | exact | Observed matched delay | 653 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 109/1 | 2024-10-29 | 2024-10 | 2025-03-01 | 2025-03 | 123 | 123 | Yes | No | exact | Observed matched delay | 652 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/6 | 2024-11-02 | 2024-11 | 2025-02-05 | 2025-02 | 95 | 95 | Yes | No | exact | Observed matched delay | 648 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 111/1 | 2024-11-04 | 2024-11 | 2025-05-02 | 2025-05 | 179 | 179 | Yes | No | exact | Observed matched delay | 646 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/8 | 2024-11-08 | 2024-11 | 2025-02-13 | 2025-02 | 97 | 97 | Yes | No | exact | Observed matched delay | 642 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110A/1 | 2024-11-10 | 2024-11 | 2025-03-26 | 2025-03 | 136 | 136 | Yes | No | exact | Observed matched delay | 640 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/1 | 2024-11-14 | 2024-11 | 2025-01-21 | 2025-01 | 68 | 68 | Yes | No | exact | Observed matched delay | 636 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 113/2 | 2024-11-14 | 2024-11 | 2025-04-11 | 2025-04 | 148 | 148 | Yes | No | exact | Observed matched delay | 636 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/8 | 2024-11-15 | 2024-11 | 2025-03-30 | 2025-03 | 135 | 135 | Yes | No | exact | Observed matched delay | 635 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/3 | 2024-11-17 | 2024-11 | 2025-03-22 | 2025-03 | 125 | 125 | Yes | No | exact | Observed matched delay | 633 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/7 | 2024-11-18 | 2024-11 | 2025-02-09 | 2025-02 | 83 | 83 | Yes | No | exact | Observed matched delay | 632 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 111/2 | 2024-11-18 | 2024-11 | 2025-05-09 | 2025-05 | 172 | 172 | Yes | No | exact | Observed matched delay | 632 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 105/1 | 2024-11-19 | 2024-11 | 2025-04-26 | 2025-04 | 158 | 158 | Yes | No | exact | Observed matched delay | 631 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/10 | 2024-11-20 | 2024-11 | 2025-04-06 | 2025-04 | 137 | 137 | Yes | No | exact | Observed matched delay | 630 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/1 | 2024-11-22 | 2024-11 | 2025-03-05 | 2025-03 | 103 | 103 | Yes | No | exact | Observed matched delay | 628 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 113/1 | 2024-11-22 | 2024-11 | 2025-04-18 | 2025-04 | 147 | 147 | Yes | No | exact | Observed matched delay | 628 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/5 | 2024-11-23 | 2024-11 | 2025-02-21 | 2025-02 | 90 | 90 | Yes | No | exact | Observed matched delay | 627 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/8 | 2024-11-23 | 2024-11 | 2025-09-19 | 2025-09 | 300 | 300 | Yes | No | exact | Observed matched delay | 627 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 104/1 | 2024-11-27 | 2024-11 | 2025-04-18 | 2025-04 | 142 | 142 | Yes | No | exact | Observed matched delay | 623 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/9 | 2024-11-27 | 2024-11 | 2025-03-30 | 2025-03 | 123 | 123 | Yes | No | exact | Observed matched delay | 623 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/7 | 2024-11-28 | 2024-11 | 2025-04-18 | 2025-04 | 141 | 141 | Yes | No | exact | Observed matched delay | 622 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/2 | 2024-11-29 | 2024-11 | 2025-03-19 | 2025-03 | 110 | 110 | Yes | No | exact | Observed matched delay | 621 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/7 | 2024-11-29 | 2024-11 | 2025-02-17 | 2025-02 | 80 | 80 | Yes | No | exact | Observed matched delay | 621 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 113/3 | 2024-11-29 | 2024-11 | 2025-04-01 | 2025-04 | 123 | 123 | Yes | No | exact | Observed matched delay | 621 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 105/0 | 2024-11-30 | 2024-11 | 2025-09-21 | 2025-09 | 295 | 295 | Yes | No | exact | Observed matched delay | 620 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 108/2 | 2024-11-30 | 2024-11 | 2025-04-12 | 2025-04 | 133 | 133 | Yes | No | exact | Observed matched delay | 620 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 109/3 | 2024-11-30 | 2024-11 | 2025-03-06 | 2025-03 | 96 | 96 | Yes | No | exact | Observed matched delay | 620 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/6 | 2024-11-30 | 2024-11 | 2025-03-07 | 2025-03 | 97 | 97 | Yes | No | exact | Observed matched delay | 620 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 116/2 | 2024-12-01 | 2024-12 | 2025-05-02 | 2025-05 | 152 | 152 | Yes | No | exact | Observed matched delay | 619 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 104/2 | 2024-12-03 | 2024-12 | 2025-04-22 | 2025-04 | 140 | 140 | Yes | No | exact | Observed matched delay | 617 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 113/5 | 2024-12-05 | 2024-12 | 2025-03-29 | 2025-03 | 114 | 114 | Yes | No | exact | Observed matched delay | 615 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/3 | 2024-12-07 | 2024-12 | 2025-04-17 | 2025-04 | 131 | 131 | Yes | No | exact | Observed matched delay | 613 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/5 | 2024-12-07 | 2024-12 | 2025-03-30 | 2025-03 | 113 | 113 | Yes | No | exact | Observed matched delay | 613 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 111/3 | 2024-12-08 | 2024-12 | 2025-05-06 | 2025-05 | 149 | 149 | Yes | No | exact | Observed matched delay | 612 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 113/4 | 2024-12-09 | 2024-12 | 2025-03-12 | 2025-03 | 93 | 93 | Yes | No | exact | Observed matched delay | 611 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 127/3 | 2024-12-10 | 2024-12 | 2025-05-27 | 2025-05 | 168 | 168 | Yes | No | exact | Observed matched delay | 610 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 113/6 | 2024-12-12 | 2024-12 | 2025-04-24 | 2025-04 | 133 | 133 | Yes | No | exact | Observed matched delay | 608 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 108/1 | 2024-12-13 | 2024-12 | 2025-04-15 | 2025-04 | 123 | 123 | Yes | No | exact | Observed matched delay | 607 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 102/0 | 2024-12-14 | 2024-12 | 2025-10-13 | 2025-10 | 303 | 303 | Yes | No | exact | Observed matched delay | 606 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/2 | 2024-12-14 | 2024-12 | 2025-04-12 | 2025-04 | 119 | 119 | Yes | No | exact | Observed matched delay | 606 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 127/2 | 2024-12-15 | 2024-12 | 2025-05-08 | 2025-05 | 144 | 144 | Yes | No | exact | Observed matched delay | 605 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 111/4 | 2024-12-16 | 2024-12 | 2025-04-30 | 2025-04 | 135 | 135 | Yes | No | exact | Observed matched delay | 604 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 126/0 | 2024-12-16 | 2024-12 | 2025-08-17 | 2025-08 | 244 | 244 | Yes | No | exact | Observed matched delay | 604 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/0 | 2024-12-17 | 2024-12 | 2026-01-20 | 2026-01 | 399 | 399 | Yes | No | exact | Observed matched delay | 603 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 126/4 | 2024-12-17 | 2024-12 | 2025-05-17 | 2025-05 | 151 | 151 | Yes | No | exact | Observed matched delay | 603 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 108/3 | 2024-12-19 | 2024-12 | 2025-04-08 | 2025-04 | 110 | 110 | Yes | No | exact | Observed matched delay | 601 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/0 | 2024-12-19 | 2024-12 | 2025-10-22 | 2025-10 | 307 | 307 | Yes | No | exact | Observed matched delay | 601 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 147A/4 | 2024-12-19 | 2024-12 | 2025-06-01 | 2025-06 | 164 | 164 | Yes | No | exact | Observed matched delay | 601 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 127/1 | 2024-12-20 | 2024-12 | 2025-05-13 | 2025-05 | 144 | 144 | Yes | No | exact | Observed matched delay | 600 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 150/3 | 2024-12-21 | 2024-12 | 2025-06-11 | 2025-06 | 172 | 172 | Yes | No | exact | Observed matched delay | 599 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/3 | 2024-12-22 | 2024-12 | 2025-05-14 | 2025-05 | 143 | 143 | Yes | No | exact | Observed matched delay | 598 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 147A/5 | 2024-12-24 | 2024-12 | 2025-09-01 | 2025-09 | 251 | 251 | Yes | No | exact | Observed matched delay | 596 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 150/4 | 2024-12-24 | 2024-12 | 2025-06-27 | 2025-06 | 185 | 185 | Yes | No | exact | Observed matched delay | 596 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 116/1 | 2024-12-26 | 2024-12 | 2025-05-08 | 2025-05 | 133 | 133 | Yes | No | exact | Observed matched delay | 594 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152/2 | 2024-12-26 | 2024-12 | 2025-12-28 | 2025-12 | 367 | 367 | Yes | No | exact | Observed matched delay | 594 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 147A/1 | 2024-12-27 | 2024-12 | 2025-09-20 | 2025-09 | 267 | 267 | Yes | No | exact | Observed matched delay | 593 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/4 | 2024-12-27 | 2024-12 | 2025-05-27 | 2025-05 | 151 | 151 | Yes | No | exact | Observed matched delay | 593 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 150/5 | 2024-12-28 | 2024-12 | 2025-06-06 | 2025-06 | 160 | 160 | Yes | No | exact | Observed matched delay | 592 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 127/0 | 2024-12-29 | 2024-12 | 2025-08-01 | 2025-08 | 215 | 215 | Yes | No | exact | Observed matched delay | 591 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/9 | 2024-12-29 | 2024-12 | 2025-06-17 | 2025-06 | 170 | 170 | Yes | No | exact | Observed matched delay | 591 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152/1 | 2024-12-30 | 2024-12 | 2025-12-17 | 2025-12 | 352 | 352 | Yes | No | exact | Observed matched delay | 590 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 109/0 | 2024-12-31 | 2024-12 | 2025-11-06 | 2025-11 | 310 | 310 | Yes | No | exact | Observed matched delay | 589 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/1 | 2024-12-31 | 2024-12 | 2025-04-25 | 2025-04 | 115 | 115 | Yes | No | exact | Observed matched delay | 589 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 147A/2 | 2024-12-31 | 2024-12 | 2025-06-07 | 2025-06 | 158 | 158 | Yes | No | exact | Observed matched delay | 589 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/5 | 2025-01-02 | 2025-01 | 2025-10-05 | 2025-10 | 276 | 276 | Yes | No | exact | Observed matched delay | 587 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 111/0 | 2025-01-04 | 2025-01 | 2025-08-18 | 2025-08 | 226 | 226 | Yes | No | exact | Observed matched delay | 585 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 147/1 | 2025-01-05 | 2025-01 | 2025-06-26 | 2025-06 | 172 | 172 | Yes | No | exact | Observed matched delay | 584 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/7 | 2025-01-05 | 2025-01 | 2025-12-25 | 2025-12 | 354 | 354 | Yes | No | exact | Observed matched delay | 584 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/1 | 2025-01-10 | 2025-01 | 2025-05-17 | 2025-05 | 127 | 127 | Yes | No | exact | Observed matched delay | 579 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 120/1 | 2025-01-12 | 2025-01 | 2025-04-27 | 2025-04 | 105 | 105 | Yes | No | exact | Observed matched delay | 577 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 150/1 | 2025-01-12 | 2025-01 | 2025-07-07 | 2025-07 | 176 | 176 | Yes | No | exact | Observed matched delay | 577 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/7 | 2025-01-15 | 2025-01 | 2025-07-15 | 2025-07 | 181 | 181 | Yes | No | exact | Observed matched delay | 574 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 155/5 | 2025-01-15 | 2025-01 | 2025-05-28 | 2025-05 | 133 | 133 | Yes | No | exact | Observed matched delay | 574 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 144A/1 | 2025-01-16 | 2025-01 | 2025-09-12 | 2025-09 | 239 | 239 | Yes | No | exact | Observed matched delay | 573 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/8 | 2025-01-16 | 2025-01 | 2025-05-31 | 2025-05 | 135 | 135 | Yes | No | exact | Observed matched delay | 573 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 131/0 | 2025-01-17 | 2025-01 | 2025-09-10 | 2025-09 | 236 | 236 | Yes | No | exact | Observed matched delay | 572 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/0 | 2025-01-17 | 2025-01 | 2025-12-12 | 2025-12 | 329 | 329 | Yes | No | exact | Observed matched delay | 572 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 126/2 | 2025-01-18 | 2025-01 | 2025-05-23 | 2025-05 | 125 | 125 | Yes | No | exact | Observed matched delay | 571 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 144A/3 | 2025-01-19 | 2025-01 | 2025-10-19 | 2025-10 | 273 | 273 | Yes | No | exact | Observed matched delay | 570 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 126/3 | 2025-01-20 | 2025-01 | 2025-11-10 | 2025-11 | 294 | 294 | Yes | No | exact | Observed matched delay | 569 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/11 | 2025-01-21 | 2025-01 | 2026-04-01 | 2026-04 | 435 | 435 | Yes | No | exact | Observed matched delay | 568 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 155/3 | 2025-01-21 | 2025-01 | 2025-05-23 | 2025-05 | 122 | 122 | Yes | No | exact | Observed matched delay | 568 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 150/2 | 2025-01-22 | 2025-01 | 2025-07-01 | 2025-07 | 160 | 160 | Yes | No | exact | Observed matched delay | 567 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/6 | 2025-01-23 | 2025-01 | 2025-12-20 | 2025-12 | 331 | 331 | Yes | No | exact | Observed matched delay | 566 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 120/3 | 2025-01-24 | 2025-01 | 2025-05-02 | 2025-05 | 98 | 98 | Yes | No | exact | Observed matched delay | 565 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152/3 | 2025-01-25 | 2025-01 | 2026-04-06 | 2026-04 | 436 | 436 | Yes | No | exact | Observed matched delay | 564 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/10 | 2025-01-25 | 2025-01 | 2026-04-08 | 2026-04 | 438 | 438 | Yes | No | exact | Observed matched delay | 564 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 112/0 | 2025-01-27 | 2025-01 | 2025-10-01 | 2025-10 | 247 | 247 | Yes | No | exact | Observed matched delay | 562 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/2 | 2025-01-28 | 2025-01 | 2025-05-22 | 2025-05 | 114 | 114 | Yes | No | exact | Observed matched delay | 561 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 120/2 | 2025-01-30 | 2025-01 | 2025-04-22 | 2025-04 | 82 | 82 | Yes | No | exact | Observed matched delay | 559 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 154/1 | 2025-01-30 | 2025-01 | 2025-07-01 | 2025-07 | 152 | 152 | Yes | No | exact | Observed matched delay | 559 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 128/0 | 2025-01-31 | 2025-01 | 2025-10-01 | 2025-10 | 243 | 243 | Yes | No | exact | Observed matched delay | 558 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 130/1 | 2025-01-31 | 2025-01 | 2025-09-26 | 2025-09 | 238 | 238 | Yes | No | exact | Observed matched delay | 558 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 148/0 | 2025-01-31 | 2025-01 | 2025-12-10 | 2025-12 | 313 | 313 | Yes | No | exact | Observed matched delay | 558 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 154/2 | 2025-02-04 | 2025-02 | 2025-06-24 | 2025-06 | 140 | 140 | Yes | No | exact | Observed matched delay | 554 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 140/1 | 2025-02-05 | 2025-02 | 2025-10-10 | 2025-10 | 247 | 247 | Yes | No | exact | Observed matched delay | 553 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 156/4 | 2025-02-05 | 2025-02 | 2025-06-16 | 2025-06 | 131 | 131 | Yes | No | exact | Observed matched delay | 553 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 129A/3 | 2025-02-06 | 2025-02 | 2025-05-19 | 2025-05 | 102 | 102 | Yes | No | exact | Observed matched delay | 552 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 104/0 | 2025-02-07 | 2025-02 | 2025-08-23 | 2025-08 | 197 | 197 | Yes | No | exact | Observed matched delay | 551 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 154/5 | 2025-02-08 | 2025-02 | 2025-05-16 | 2025-05 | 97 | 97 | Yes | No | exact | Observed matched delay | 550 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 130/2 | 2025-02-09 | 2025-02 | 2025-11-23 | 2025-11 | 287 | 287 | Yes | No | exact | Observed matched delay | 549 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 129A/2 | 2025-02-10 | 2025-02 | 2025-11-12 | 2025-11 | 275 | 275 | Yes | No | exact | Observed matched delay | 548 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 155/4 | 2025-02-10 | 2025-02 | 2025-06-01 | 2025-06 | 111 | 111 | Yes | No | exact | Observed matched delay | 548 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 129A/1 | 2025-02-11 | 2025-02 | 2025-06-08 | 2025-06 | 117 | 117 | Yes | No | exact | Observed matched delay | 547 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 156/1 | 2025-02-12 | 2025-02 | 2025-06-08 | 2025-06 | 116 | 116 | Yes | No | exact | Observed matched delay | 546 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 148A/0 | 2025-02-13 | 2025-02 | 2025-10-25 | 2025-10 | 254 | 254 | Yes | No | exact | Observed matched delay | 545 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 130/0 | 2025-02-14 | 2025-02 | 2025-08-27 | 2025-08 | 194 | 194 | Yes | No | exact | Observed matched delay | 544 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 160/3 | 2025-02-15 | 2025-02 | 2025-06-08 | 2025-06 | 113 | 113 | Yes | No | exact | Observed matched delay | 543 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 159/3 | 2025-02-16 | 2025-02 | 2026-03-19 | 2026-03 | 396 | 396 | Yes | No | exact | Observed matched delay | 542 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 109/4 | 2025-02-17 | 2025-02 | 2025-03-11 | 2025-03 | 22 | 22 | Yes | No | exact | Observed matched delay | 541 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 135/1 | 2025-02-17 | 2025-02 | 2025-11-03 | 2025-11 | 259 | 259 | Yes | No | exact | Observed matched delay | 541 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110A/0 | 2025-02-20 | 2025-02 | 2025-09-20 | 2025-09 | 212 | 212 | Yes | No | exact | Observed matched delay | 538 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 135/2 | 2025-02-21 | 2025-02 | 2025-09-08 | 2025-09 | 199 | 199 | Yes | No | exact | Observed matched delay | 537 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 135/3 | 2025-02-22 | 2025-02 | 2026-02-25 | 2026-02 | 368 | 368 | Yes | No | exact | Observed matched delay | 536 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 156/3 | 2025-02-22 | 2025-02 | 2026-02-18 | 2026-02 | 361 | 361 | Yes | No | exact | Observed matched delay | 536 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 155/1 | 2025-02-24 | 2025-02 | 2026-04-23 | 2026-04 | 423 | 423 | Yes | No | exact | Observed matched delay | 534 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 159/0 | 2025-02-24 | 2025-02 | 2025-10-19 | 2025-10 | 237 | 237 | Yes | No | exact | Observed matched delay | 534 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 136/1 | 2025-02-25 | 2025-02 | 2025-08-25 | 2025-08 | 181 | 181 | Yes | No | exact | Observed matched delay | 533 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 160/0 | 2025-02-25 | 2025-02 | 2025-09-26 | 2025-09 | 213 | 213 | Yes | No | exact | Observed matched delay | 533 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 164/5 | 2025-02-26 | 2025-02 | 2025-11-09 | 2025-11 | 256 | 256 | Yes | No | exact | Observed matched delay | 532 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 118/0 | 2025-02-27 | 2025-02 | 2025-12-11 | 2025-12 | 287 | 287 | Yes | No | exact | Observed matched delay | 531 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 136/5 | 2025-02-27 | 2025-02 | 2025-11-11 | 2025-11 | 257 | 257 | Yes | No | exact | Observed matched delay | 531 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 161/4 | 2025-02-27 | 2025-02 | 2025-05-08 | 2025-05 | 70 | 70 | Yes | No | exact | Observed matched delay | 531 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 154/3 | 2025-02-28 | 2025-02 | 2025-07-08 | 2025-07 | 130 | 130 | Yes | No | exact | Observed matched delay | 530 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 155/2 | 2025-02-28 | 2025-02 | 2026-04-30 | 2026-04 | 426 | 426 | Yes | No | exact | Observed matched delay | 530 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 160/2 | 2025-02-28 | 2025-02 | 2025-09-26 | 2025-09 | 210 | 210 | Yes | No | exact | Observed matched delay | 530 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 160/1 | 2025-03-04 | 2025-03 | 2025-10-08 | 2025-10 | 218 | 218 | Yes | No | exact | Observed matched delay | 526 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 135/0 | 2025-03-05 | 2025-03 | 2025-08-25 | 2025-08 | 173 | 173 | Yes | No | exact | Observed matched delay | 525 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 161/2 | 2025-03-06 | 2025-03 | 2025-09-10 | 2025-09 | 188 | 188 | Yes | No | exact | Observed matched delay | 524 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 164/6 | 2025-03-07 | 2025-03 | 2025-12-12 | 2025-12 | 280 | 280 | Yes | No | exact | Observed matched delay | 523 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 160/4 | 2025-03-08 | 2025-03 | 2025-05-24 | 2025-05 | 77 | 77 | Yes | No | exact | Observed matched delay | 522 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 161/5 | 2025-03-11 | 2025-03 | 2025-12-31 | 2025-12 | 295 | 295 | Yes | No | exact | Observed matched delay | 519 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 140/0 | 2025-03-12 | 2025-03 | 2025-12-01 | 2025-12 | 264 | 264 | Yes | No | exact | Observed matched delay | 518 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 164/4 | 2025-03-16 | 2025-03 | 2025-12-18 | 2025-12 | 277 | 277 | Yes | No | exact | Observed matched delay | 514 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 159/1 | 2025-03-19 | 2025-03 | 2025-04-22 | 2025-04 | 34 | 34 | Yes | No | exact | Observed matched delay | 511 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 144A/0 | 2025-03-22 | 2025-03 | 2025-09-23 | 2025-09 | 185 | 185 | Yes | No | exact | Observed matched delay | 508 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 161/1 | 2025-03-26 | 2025-03 | 2026-03-25 | 2026-03 | 364 | 364 | Yes | No | exact | Observed matched delay | 504 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 144A/2 | 2025-03-28 | 2025-03 | 2026-03-22 | 2026-03 | 359 | 359 | Yes | No | exact | Observed matched delay | 502 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/4 | 2025-03-28 | 2025-03 | 2025-12-04 | 2025-12 | 251 | 251 | Yes | No | exact | Observed matched delay | 502 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/3 | 2025-03-29 | 2025-03 | 2025-12-28 | 2025-12 | 274 | 274 | Yes | No | exact | Observed matched delay | 501 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/2 | 2025-03-30 | 2025-03 | 2026-05-02 | 2026-05 | 398 | 398 | Yes | No | exact | Observed matched delay | 500 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 147/0 | 2025-03-31 | 2025-03 | 2026-02-26 | 2026-02 | 332 | 332 | Yes | No | exact | Observed matched delay | 499 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 160/5 | 2025-03-31 | 2025-03 | 2025-05-08 | 2025-05 | 38 | 38 | Yes | No | exact | Observed matched delay | 499 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 161/3 | 2025-03-31 | 2025-03 | 2025-05-28 | 2025-05 | 58 | 58 | Yes | No | exact | Observed matched delay | 499 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 164/2 | 2025-03-31 | 2025-03 | 2026-01-28 | 2026-01 | 303 | 303 | Yes | No | exact | Observed matched delay | 499 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/5 | 2025-03-31 | 2025-03 | 2025-11-30 | 2025-11 | 244 | 244 | Yes | No | exact | Observed matched delay | 499 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/8 | 2025-03-31 | 2025-03 | 2025-11-07 | 2025-11 | 221 | 221 | Yes | No | exact | Observed matched delay | 499 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 115/0 | 2025-04-03 | 2025-04 | 2025-09-24 | 2025-09 | 174 | 174 | Yes | No | exact | Observed matched delay | 496 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 116/0 | 2025-04-07 | 2025-04 | 2025-10-05 | 2025-10 | 181 | 181 | Yes | No | exact | Observed matched delay | 492 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/3 | 2025-04-07 | 2025-04 | 2025-09-22 | 2025-09 | 168 | 168 | Yes | No | exact | Observed matched delay | 492 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/9 | 2025-04-07 | 2025-04 | 2026-04-01 | 2026-04 | 359 | 359 | Yes | No | exact | Observed matched delay | 492 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 164/7 | 2025-04-08 | 2025-04 | 2025-12-04 | 2025-12 | 240 | 240 | Yes | No | exact | Observed matched delay | 491 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/8 | 2025-04-08 | 2025-04 | 2025-11-14 | 2025-11 | 220 | 220 | Yes | No | exact | Observed matched delay | 491 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 165/6 | 2025-04-09 | 2025-04 | 2025-11-03 | 2025-11 | 208 | 208 | Yes | No | exact | Observed matched delay | 490 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 147A/0 | 2025-04-10 | 2025-04 | 2025-10-13 | 2025-10 | 186 | 186 | Yes | No | exact | Observed matched delay | 489 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 147A/3 | 2025-04-10 | 2025-04 | 2025-06-11 | 2025-06 | 62 | 62 | Yes | No | exact | Observed matched delay | 489 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 172/2 | 2025-04-10 | 2025-04 | 2025-11-29 | 2025-11 | 233 | 233 | Yes | No | exact | Observed matched delay | 489 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/1 | 2025-04-11 | 2025-04 | 2025-11-21 | 2025-11 | 224 | 224 | Yes | No | exact | Observed matched delay | 488 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 120/0 | 2025-04-12 | 2025-04 | 2025-09-08 | 2025-09 | 149 | 149 | Yes | No | exact | Observed matched delay | 487 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 148/1 | 2025-04-12 | 2025-04 | 2025-09-30 | 2025-09 | 171 | 171 | Yes | No | exact | Observed matched delay | 487 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/10 | 2025-04-12 | 2025-04 | 2026-04-04 | 2026-04 | 357 | 357 | Yes | No | exact | Observed matched delay | 487 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 173/3 | 2025-04-12 | 2025-04 | 2025-12-31 | 2025-12 | 263 | 263 | Yes | No | exact | Observed matched delay | 487 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 165/4 | 2025-04-13 | 2025-04 | 2026-01-09 | 2026-01 | 271 | 271 | Yes | No | exact | Observed matched delay | 486 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/6 | 2025-04-13 | 2025-04 | 2025-11-25 | 2025-11 | 226 | 226 | Yes | No | exact | Observed matched delay | 486 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/2 | 2025-04-14 | 2025-04 | 2025-10-22 | 2025-10 | 191 | 191 | Yes | No | exact | Observed matched delay | 485 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 119/0 | 2025-04-15 | 2025-04 | 2025-08-25 | 2025-08 | 132 | 132 | Yes | No | exact | Observed matched delay | 484 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 164/8 | 2025-04-15 | 2025-04 | 2025-11-25 | 2025-11 | 224 | 224 | Yes | No | exact | Observed matched delay | 484 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 173/4 | 2025-04-16 | 2025-04 | 2026-01-02 | 2026-01 | 261 | 261 | Yes | No | exact | Observed matched delay | 483 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/7 | 2025-04-17 | 2025-04 | 2025-11-14 | 2025-11 | 211 | 211 | Yes | No | exact | Observed matched delay | 482 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 165/3 | 2025-04-18 | 2025-04 | 2026-04-11 | 2026-04 | 358 | 358 | Yes | No | exact | Observed matched delay | 481 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 172/3 | 2025-04-18 | 2025-04 | 2025-11-18 | 2025-11 | 214 | 214 | Yes | No | exact | Observed matched delay | 481 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/3 | 2025-04-20 | 2025-04 | 2026-04-05 | 2026-04 | 350 | 350 | Yes | No | exact | Observed matched delay | 479 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/9 | 2025-04-20 | 2025-04 | 2025-11-04 | 2025-11 | 198 | 198 | Yes | No | exact | Observed matched delay | 479 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 173/2 | 2025-04-20 | 2025-04 | 2025-12-13 | 2025-12 | 237 | 237 | Yes | No | exact | Observed matched delay | 479 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/4 | 2025-04-22 | 2025-04 | 2025-10-27 | 2025-10 | 188 | 188 | Yes | No | exact | Observed matched delay | 477 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 106/0 | 2025-04-22 | 2025-04 | 2025-08-04 | 2025-08 | 104 | 104 | Yes | No | exact | Observed matched delay | 477 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 132/0 | 2025-04-22 | 2025-04 | 2025-12-17 | 2025-12 | 239 | 239 | Yes | No | exact | Observed matched delay | 477 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/5 | 2025-04-22 | 2025-04 | 2026-04-09 | 2026-04 | 352 | 352 | Yes | No | exact | Observed matched delay | 477 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/1 | 2025-04-22 | 2025-04 | 2026-04-09 | 2026-04 | 352 | 352 | Yes | No | exact | Observed matched delay | 477 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/0 | 2025-04-24 | 2025-04 | 2025-11-08 | 2025-11 | 198 | 198 | Yes | No | exact | Observed matched delay | 475 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/1 | 2025-04-24 | 2025-04 | 2025-10-31 | 2025-10 | 190 | 190 | Yes | No | exact | Observed matched delay | 475 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 175/4 | 2025-04-24 | 2025-04 | 2026-04-08 | 2026-04 | 349 | 349 | Yes | No | exact | Observed matched delay | 475 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 167/4 | 2025-04-26 | 2025-04 | 2025-09-26 | 2025-09 | 153 | 153 | Yes | No | exact | Observed matched delay | 473 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/2 | 2025-04-26 | 2025-04 | 2026-03-05 | 2026-03 | 313 | 313 | Yes | No | exact | Observed matched delay | 473 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 172/1 | 2025-04-26 | 2025-04 | 2025-12-07 | 2025-12 | 225 | 225 | Yes | No | exact | Observed matched delay | 473 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 173/1 | 2025-04-26 | 2025-04 | 2025-10-27 | 2025-10 | 184 | 184 | Yes | No | exact | Observed matched delay | 473 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 175/3 | 2025-04-26 | 2025-04 | 2026-04-13 | 2026-04 | 352 | 352 | Yes | No | exact | Observed matched delay | 473 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 108/0 | 2025-04-27 | 2025-04 | 2025-08-12 | 2025-08 | 107 | 107 | Yes | No | exact | Observed matched delay | 472 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 161/0 | 2025-04-28 | 2025-04 | 2025-10-16 | 2025-10 | 171 | 171 | Yes | No | exact | Observed matched delay | 471 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/2 | 2025-04-28 | 2025-04 | 2026-02-14 | 2026-02 | 292 | 292 | Yes | No | exact | Observed matched delay | 471 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/6 | 2025-04-28 | 2025-04 | 2026-03-26 | 2026-03 | 332 | 332 | Yes | No | exact | Observed matched delay | 471 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 165/5 | 2025-04-29 | 2025-04 | 2026-01-19 | 2026-01 | 265 | 265 | Yes | No | exact | Observed matched delay | 470 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 165/1 | 2025-04-30 | 2025-04 | 2026-03-10 | 2026-03 | 314 | 314 | Yes | No | exact | Observed matched delay | 469 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 167/5 | 2025-04-30 | 2025-04 | 2025-09-14 | 2025-09 | 137 | 137 | Yes | No | exact | Observed matched delay | 469 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 176/1 | 2025-04-30 | 2025-04 | 2026-03-22 | 2026-03 | 326 | 326 | Yes | No | exact | Observed matched delay | 469 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/5A | 2025-05-03 | 2025-05 | 2025-08-21 | 2025-08 | 110 | 110 | Yes | No | exact | Observed matched delay | 466 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 136/2 | 2025-05-03 | 2025-05 | 2025-11-23 | 2025-11 | 204 | 204 | Yes | No | exact | Observed matched delay | 466 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 167/0 | 2025-05-03 | 2025-05 | 2025-10-16 | 2025-10 | 166 | 166 | Yes | No | exact | Observed matched delay | 466 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 159/2 | 2025-05-04 | 2025-05 | 2025-09-13 | 2025-09 | 132 | 132 | Yes | No | exact | Observed matched delay | 465 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/4 | 2025-05-04 | 2025-05 | 2025-09-30 | 2025-09 | 149 | 149 | Yes | No | exact | Observed matched delay | 465 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/9 | 2025-05-04 | 2025-05 | 2026-01-15 | 2026-01 | 256 | 256 | Yes | No | exact | Observed matched delay | 465 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 176/0 | 2025-05-04 | 2025-05 | 2026-03-15 | 2026-03 | 315 | 315 | Yes | No | exact | Observed matched delay | 465 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/5A1 | 2025-05-05 | 2025-05 | 2025-08-04 | 2025-08 | 91 | 91 | Yes | No | exact | Observed matched delay | 464 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 176/2 | 2025-05-06 | 2025-05 | 2026-04-16 | 2026-04 | 345 | 345 | Yes | No | exact | Observed matched delay | 463 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/3 | 2025-05-08 | 2025-05 | 2025-09-10 | 2025-09 | 125 | 125 | Yes | No | exact | Observed matched delay | 461 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 178/1 | 2025-05-08 | 2025-05 | 2026-02-03 | 2026-02 | 271 | 271 | Yes | No | exact | Observed matched delay | 461 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 158/3 | 2025-05-09 | 2025-05 | 2025-08-25 | 2025-08 | 108 | 108 | Yes | No | exact | Observed matched delay | 460 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 167/1 | 2025-05-09 | 2025-05 | 2025-10-26 | 2025-10 | 170 | 170 | Yes | No | exact | Observed matched delay | 460 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 174A/3 | 2025-05-10 | 2025-05 | 2025-12-01 | 2025-12 | 205 | 205 | Yes | No | exact | Observed matched delay | 459 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 176/3 | 2025-05-10 | 2025-05 | 2026-04-24 | 2026-04 | 349 | 349 | Yes | No | exact | Observed matched delay | 459 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/1 | 2025-05-11 | 2025-05 | 2025-09-18 | 2025-09 | 130 | 130 | Yes | No | exact | Observed matched delay | 458 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/5 | 2025-05-11 | 2025-05 | 2025-10-09 | 2025-10 | 151 | 151 | Yes | No | exact | Observed matched delay | 458 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/2 | 2025-05-13 | 2025-05 | 2025-09-25 | 2025-09 | 135 | 135 | Yes | No | exact | Observed matched delay | 456 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 141/0 | 2025-05-13 | 2025-05 | 2026-01-18 | 2026-01 | 250 | 250 | Yes | No | exact | Observed matched delay | 456 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 166/1 | 2025-05-13 | 2025-05 | 2025-09-14 | 2025-09 | 124 | 124 | Yes | No | exact | Observed matched delay | 456 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 158/2 | 2025-05-16 | 2025-05 | 2025-10-13 | 2025-10 | 150 | 150 | Yes | No | exact | Observed matched delay | 453 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 170/0 | 2025-05-16 | 2025-05 | 2025-11-28 | 2025-11 | 196 | 196 | Yes | No | exact | Observed matched delay | 453 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/8 | 2025-05-17 | 2025-05 | 2026-04-14 | 2026-04 | 332 | 332 | Yes | No | exact | Observed matched delay | 452 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/1 | 2025-05-17 | 2025-05 | 2025-12-21 | 2025-12 | 218 | 218 | Yes | No | exact | Observed matched delay | 452 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/6A | 2025-05-18 | 2025-05 | 2025-08-09 | 2025-08 | 83 | 83 | Yes | No | exact | Observed matched delay | 451 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 178/0 | 2025-05-18 | 2025-05 | 2026-01-21 | 2026-01 | 248 | 248 | Yes | No | exact | Observed matched delay | 451 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 142/0 | 2025-05-20 | 2025-05 | 2026-01-02 | 2026-01 | 227 | 227 | Yes | No | exact | Observed matched delay | 449 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/4 | 2025-05-21 | 2025-05 | 2026-03-17 | 2026-03 | 300 | 300 | Yes | No | exact | Observed matched delay | 448 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 172/4 | 2025-05-21 | 2025-05 | 2025-12-09 | 2025-12 | 202 | 202 | Yes | No | exact | Observed matched delay | 448 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/2 | 2025-05-21 | 2025-05 | 2026-01-19 | 2026-01 | 243 | 243 | Yes | No | exact | Observed matched delay | 448 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/0 | 2025-05-22 | 2025-05 | 2025-09-10 | 2025-09 | 111 | 111 | Yes | No | exact | Observed matched delay | 447 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 172/6 | 2025-05-23 | 2025-05 | 2025-10-27 | 2025-10 | 157 | 157 | Yes | No | exact | Observed matched delay | 446 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 174A/4 | 2025-05-23 | 2025-05 | 2026-04-26 | 2026-04 | 338 | 338 | Yes | No | exact | Observed matched delay | 446 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/3 | 2025-05-23 | 2025-05 | 2025-12-28 | 2025-12 | 219 | 219 | Yes | No | exact | Observed matched delay | 446 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/8 | 2025-05-24 | 2025-05 | 2025-07-25 | 2025-07 | 62 | 62 | Yes | No | exact | Observed matched delay | 445 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/6 | 2025-05-25 | 2025-05 | 2025-09-11 | 2025-09 | 109 | 109 | Yes | No | exact | Observed matched delay | 444 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/8 | 2025-05-25 | 2025-05 | 2026-03-09 | 2026-03 | 288 | 288 | Yes | No | exact | Observed matched delay | 444 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 167/2 | 2025-05-27 | 2025-05 | 2025-10-02 | 2025-10 | 128 | 128 | Yes | No | exact | Observed matched delay | 442 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/4 | 2025-05-27 | 2025-05 | 2026-01-03 | 2026-01 | 221 | 221 | Yes | No | exact | Observed matched delay | 442 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 167/3 | 2025-05-29 | 2025-05 | 2025-10-10 | 2025-10 | 134 | 134 | Yes | No | exact | Observed matched delay | 440 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 174A/5 | 2025-05-29 | 2025-05 | 2026-02-08 | 2026-02 | 255 | 255 | Yes | No | exact | Observed matched delay | 440 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/5 | 2025-05-29 | 2025-05 | 2026-01-12 | 2026-01 | 228 | 228 | Yes | No | exact | Observed matched delay | 440 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 172/5 | 2025-05-30 | 2025-05 | 2026-02-24 | 2026-02 | 270 | 270 | Yes | No | exact | Observed matched delay | 439 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 178/3 | 2025-05-30 | 2025-05 | 2025-12-03 | 2025-12 | 187 | 187 | Yes | No | exact | Observed matched delay | 439 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 101/0 | 2025-05-31 | 2025-05 | 2025-10-01 | 2025-10 | 123 | 123 | Yes | No | exact | Observed matched delay | 438 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 150/0 | 2025-05-31 | 2025-05 | 2025-07-18 | 2025-07 | 48 | 48 | Yes | No | exact | Observed matched delay | 438 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/6 | 2025-05-31 | 2025-05 | 2026-04-01 | 2026-04 | 305 | 305 | Yes | No | exact | Observed matched delay | 438 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 121/0 | 2025-06-02 | 2025-06 | 2025-10-14 | 2025-10 | 134 | 134 | Yes | No | exact | Observed matched delay | 436 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/7 | 2025-06-03 | 2025-06 | 2026-04-20 | 2026-04 | 321 | 321 | Yes | No | exact | Observed matched delay | 435 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/7 | 2025-06-03 | 2025-06 | 2026-03-22 | 2026-03 | 292 | 292 | Yes | No | exact | Observed matched delay | 435 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 174A/1 | 2025-06-04 | 2025-06 | 2025-12-10 | 2025-12 | 189 | 189 | Yes | No | exact | Observed matched delay | 434 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 173/0 | 2025-06-05 | 2025-06 | 2025-12-22 | 2025-12 | 200 | 200 | Yes | No | exact | Observed matched delay | 433 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 110/4 | 2025-06-07 | 2025-06 | 2025-08-12 | 2025-08 | 66 | 66 | Yes | No | exact | Observed matched delay | 431 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/0 | 2025-06-08 | 2025-06 | 2026-03-30 | 2026-03 | 295 | 295 | Yes | No | exact | Observed matched delay | 430 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/3 | 2025-06-08 | 2025-06 | 2026-03-22 | 2026-03 | 287 | 287 | Yes | No | exact | Observed matched delay | 430 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 172/0 | 2025-06-09 | 2025-06 | 2026-01-27 | 2026-01 | 232 | 232 | Yes | No | exact | Observed matched delay | 429 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152/0 | 2025-06-11 | 2025-06 | 2025-11-29 | 2025-11 | 171 | 171 | Yes | No | exact | Observed matched delay | 427 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 152A/12 | 2025-06-13 | 2025-06 | 2026-03-26 | 2026-03 | 286 | 286 | Yes | No | exact | Observed matched delay | 425 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 174A/0 | 2025-06-13 | 2025-06 | 2025-11-10 | 2025-11 | 150 | 150 | Yes | No | exact | Observed matched delay | 425 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 174A/2 | 2025-06-28 | 2025-06 | 2025-11-24 | 2025-11 | 149 | 149 | Yes | No | exact | Observed matched delay | 410 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 151/0 | 2025-06-29 | 2025-06 | 2026-01-04 | 2026-01 | 189 | 189 | Yes | No | exact | Observed matched delay | 409 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/6 | 2025-06-29 | 2025-06 | 2026-04-16 | 2026-04 | 291 | 291 | Yes | No | exact | Observed matched delay | 409 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 156/0 | 2025-07-15 | 2025-07 | 2025-09-12 | 2025-09 | 59 | 59 | Yes | No | exact | Observed matched delay | 393 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/7 | 2025-07-17 | 2025-07 | 2025-10-16 | 2025-10 | 91 | 91 | Yes | No | exact | Observed matched delay | 391 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/7 | 2025-08-29 | 2025-08 | 2026-04-04 | 2026-04 | 218 | 218 | Yes | No | exact | Observed matched delay | 348 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 178/4 | 2025-09-04 | 2025-09 | 2025-12-12 | 2025-12 | 99 | 99 | Yes | No | exact | Observed matched delay | 342 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 178/5 | 2025-09-12 | 2025-09 | 2025-12-03 | 2025-12 | 82 | 82 | Yes | No | exact | Observed matched delay | 334 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/6 | 2025-09-12 | 2025-09 | 2026-01-12 | 2026-01 | 122 | 122 | Yes | No | exact | Observed matched delay | 334 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 145/0 | 2025-09-14 | 2025-09 | 2025-11-11 | 2025-11 | 58 | 58 | Yes | No | exact | Observed matched delay | 332 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 114/4 | 2025-09-19 | 2025-09 | 2025-11-17 | 2025-11 | 59 | 59 | Yes | No | exact | Observed matched delay | 327 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/1 | 2025-09-23 | 2025-09 | 2025-12-29 | 2025-12 | 97 | 97 | Yes | No | exact | Observed matched delay | 323 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/4 | 2025-09-26 | 2025-09 | 2025-12-27 | 2025-12 | 92 | 92 | Yes | No | exact | Observed matched delay | 320 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149B/3 | 2025-09-27 | 2025-09 | 2025-10-27 | 2025-10 | 30 | 30 | Yes | No | exact | Observed matched delay | 319 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/2 | 2025-09-29 | 2025-09 | 2026-01-02 | 2026-01 | 95 | 95 | Yes | No | exact | Observed matched delay | 317 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 154/4 | 2025-09-30 | 2025-09 | 2025-12-06 | 2025-12 | 67 | 67 | Yes | No | exact | Observed matched delay | 316 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 126/1 | 2025-10-05 | 2025-10 | 2025-11-01 | 2025-11 | 27 | 27 | Yes | No | exact | Observed matched delay | 311 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149B/1 | 2025-10-09 | 2025-10 | 2026-02-06 | 2026-02 | 120 | 120 | Yes | No | exact | Observed matched delay | 307 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149B/2 | 2025-10-15 | 2025-10 | 2025-11-12 | 2025-11 | 28 | 28 | Yes | No | exact | Observed matched delay | 301 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 100/0 | 2025-10-16 | 2025-10 | 2025-11-19 | 2025-11 | 34 | 34 | Yes | No | exact | Observed matched delay | 300 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 178/2 | 2025-10-16 | 2025-10 | 2026-02-15 | 2026-02 | 122 | 122 | Yes | No | exact | Observed matched delay | 300 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149B/4 | 2025-10-17 | 2025-10 | 2025-11-26 | 2025-11 | 40 | 40 | Yes | No | exact | Observed matched delay | 299 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 155/0 | 2025-10-17 | 2025-10 | 2026-04-14 | 2026-04 | 179 | 179 | Yes | No | exact | Observed matched delay | 299 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 99/8 | 2025-10-17 | 2025-10 | 2025-11-30 | 2025-11 | 44 | 44 | Yes | No | exact | Observed matched delay | 299 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 165/0 | 2025-10-22 | 2025-10 | 2025-11-16 | 2025-11 | 25 | 25 | Yes | No | exact | Observed matched delay | 294 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 168/0 | 2025-10-25 | 2025-10 | 2025-12-09 | 2025-12 | 45 | 45 | Yes | No | exact | Observed matched delay | 291 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 99/6 | 2025-10-25 | 2025-10 | 2025-12-13 | 2025-12 | 49 | 49 | Yes | No | exact | Observed matched delay | 291 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 180/0 | 2025-10-30 | 2025-10 | 2026-05-02 | 2026-05 | 184 | 184 | Yes | No | exact | Observed matched delay | 286 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 99/4 | 2025-11-01 | 2025-11 | 2025-12-10 | 2025-12 | 39 | 39 | Yes | No | exact | Observed matched delay | 284 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 99/5 | 2025-11-03 | 2025-11 | 2025-12-05 | 2025-12 | 32 | 32 | Yes | No | exact | Observed matched delay | 282 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 99/3 | 2025-11-06 | 2025-11 | 2025-12-18 | 2025-12 | 42 | 42 | Yes | No | exact | Observed matched delay | 279 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 165/2 | 2025-11-07 | 2025-11 | 2026-02-23 | 2026-02 | 108 | 108 | Yes | No | exact | Observed matched delay | 278 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 99/2 | 2025-11-09 | 2025-11 | 2026-01-02 | 2026-01 | 54 | 54 | Yes | No | exact | Observed matched delay | 276 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 181/6 | 2025-11-10 | 2025-11 | 2025-12-12 | 2025-12 | 32 | 32 | Yes | No | exact | Observed matched delay | 275 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 99/1 | 2025-11-11 | 2025-11 | 2025-12-27 | 2025-12 | 46 | 46 | Yes | No | exact | Observed matched delay | 274 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/5 | 2025-11-14 | 2025-11 | 2025-11-25 | 2025-11 | 11 | 11 | Yes | No | exact | Observed matched delay | 271 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 99/7 | 2025-11-16 | 2025-11 | 2025-12-22 | 2025-12 | 36 | 36 | Yes | No | exact | Observed matched delay | 269 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 181/1 | 2025-11-18 | 2025-11 | 2025-12-21 | 2025-12 | 33 | 33 | Yes | No | exact | Observed matched delay | 267 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 103/9 | 2025-11-19 | 2025-11 | 2025-12-03 | 2025-12 | 14 | 14 | Yes | No | exact | Observed matched delay | 266 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/0 | 2025-11-20 | 2025-11 | 2025-12-10 | 2025-12 | 20 | 20 | Yes | No | exact | Observed matched delay | 265 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 122/0 | 2025-11-26 | 2025-11 | 2026-01-29 | 2026-01 | 64 | 64 | Yes | No | exact | Observed matched delay | 259 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 175/2 | 2025-11-26 | 2025-11 | 2026-01-10 | 2026-01 | 45 | 45 | Yes | No | exact | Observed matched delay | 259 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 171/10 | 2025-11-27 | 2025-11 | 2026-05-29 | 2026-05 | 183 | 183 | Yes | No | exact | Observed matched delay | 258 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 181/4 | 2025-11-27 | 2025-11 | 2026-01-07 | 2026-01 | 41 | 41 | Yes | No | exact | Observed matched delay | 258 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 138/0 | 2025-11-29 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 256 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 123/0 | 2025-12-03 | 2025-12 | 2025-12-22 | 2025-12 | 19 | 19 | Yes | No | exact | Observed matched delay | 252 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 181/5 | 2025-12-06 | 2025-12 | 2026-01-07 | 2026-01 | 32 | 32 | Yes | No | exact | Observed matched delay | 249 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 123/1 | 2025-12-08 | 2025-12 | 2026-01-05 | 2026-01 | 28 | 28 | Yes | No | exact | Observed matched delay | 247 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/9 | 2025-12-08 | 2025-12 | 2025-12-20 | 2025-12 | 12 | 12 | Yes | No | exact | Observed matched delay | 247 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/5 | 2025-12-10 | 2025-12 | 2025-12-21 | 2025-12 | 11 | 11 | Yes | No | exact | Observed matched delay | 245 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 123/3 | 2025-12-12 | 2025-12 | 2026-01-15 | 2026-01 | 34 | 34 | Yes | No | exact | Observed matched delay | 243 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 153/0 | 2025-12-13 | 2025-12 | 2026-01-11 | 2026-01 | 29 | 29 | Yes | No | exact | Observed matched delay | 242 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 154/0 | 2025-12-14 | 2025-12 | 2026-01-02 | 2026-01 | 19 | 19 | Yes | No | exact | Observed matched delay | 241 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 125/1 | 2025-12-15 | 2025-12 | 2026-01-12 | 2026-01 | 28 | 28 | Yes | No | exact | Observed matched delay | 240 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 175/1 | 2025-12-15 | 2025-12 | 2026-02-01 | 2026-02 | 48 | 48 | Yes | No | exact | Observed matched delay | 240 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 123/2 | 2025-12-22 | 2025-12 | 2026-01-21 | 2026-01 | 30 | 30 | Yes | No | exact | Observed matched delay | 233 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 129A/0 | 2025-12-23 | 2025-12 | 2025-12-31 | 2025-12 | 8 | 8 | Yes | No | exact | Observed matched delay | 232 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 181/0 | 2025-12-24 | 2025-12 | 2026-01-12 | 2026-01 | 19 | 19 | Yes | No | exact | Observed matched delay | 231 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 113/0 | 2025-12-28 | 2025-12 | 2026-01-06 | 2026-01 | 9 | 9 | Yes | No | exact | Observed matched delay | 227 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 175/0 | 2025-12-30 | 2025-12 | 2026-01-09 | 2026-01 | 10 | 10 | Yes | No | exact | Observed matched delay | 225 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149B/0 | 2025-12-31 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 224 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 158/0 | 2025-12-31 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 224 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 158/1 | 2025-12-31 | 2025-12 | 2026-01-11 | 2026-01 | 11 | 11 | Yes | No | exact | Observed matched delay | 224 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 125/0 | 2026-01-04 | 2026-01 | 2026-01-21 | 2026-01 | 17 | 17 | Yes | No | exact | Observed matched delay | 220 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 162/0 | 2026-01-07 | 2026-01 | 2026-04-24 | 2026-04 | 107 | 107 | Yes | No | exact | Observed matched delay | 217 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 162/2 | 2026-01-08 | 2026-01 | 2026-01-20 | 2026-01 | 12 | 12 | Yes | No | exact | Observed matched delay | 216 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 124/0 | 2026-01-09 | 2026-01 | 2026-02-01 | 2026-02 | 23 | 23 | Yes | No | exact | Observed matched delay | 215 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/9 | 2026-01-11 | 2026-01 | 2026-02-01 | 2026-02 | 21 | 21 | Yes | No | exact | Observed matched delay | 213 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149/0 | 2026-01-13 | 2026-01 | 2026-01-19 | 2026-01 | 6 | 6 | Yes | No | exact | Observed matched delay | 211 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149/2 | 2026-01-16 | 2026-01 | 2026-01-24 | 2026-01 | 8 | 8 | Yes | No | exact | Observed matched delay | 208 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149/1 | 2026-01-18 | 2026-01 | 2026-02-01 | 2026-02 | 14 | 14 | Yes | No | exact | Observed matched delay | 206 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 164/0 | 2026-01-19 | 2026-01 | 2026-02-16 | 2026-02 | 28 | 28 | Yes | No | exact | Observed matched delay | 205 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 174B/0 | 2026-01-22 | 2026-01 | 2026-06-03 | 2026-06 | 132 | 132 | Yes | No | exact | Observed matched delay | 202 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 163/0 | 2026-01-23 | 2026-01 | 2026-02-06 | 2026-02 | 14 | 14 | Yes | No | exact | Observed matched delay | 201 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 162/1 | 2026-01-24 | 2026-01 | 2026-01-28 | 2026-01 | 4 | 4 | Yes | No | exact | Observed matched delay | 200 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 146/1 | 2026-01-25 | 2026-01 | 2026-01-31 | 2026-01 | 6 | 6 | Yes | No | exact | Observed matched delay | 199 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 164/1 | 2026-01-25 | 2026-01 | 2026-02-01 | 2026-02 | 7 | 7 | Yes | No | exact | Observed matched delay | 199 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 182/0 | 2026-01-25 | 2026-01 | 2026-05-14 | 2026-05 | 109 | 109 | Yes | No | exact | Observed matched delay | 199 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 148B/1 | 2026-01-29 | 2026-01 | 2026-02-01 | 2026-02 | 3 | 3 | Yes | No | exact | Observed matched delay | 195 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 149A/0 | 2026-01-31 | 2026-01 | 2026-02-10 | 2026-02 | 10 | 10 | Yes | No | exact | Observed matched delay | 193 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 139/0 | 2026-02-04 | 2026-02 | 2026-02-22 | 2026-02 | 18 | 18 | Yes | No | exact | Observed matched delay | 189 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 139/1 | 2026-02-06 | 2026-02 | 2026-02-12 | 2026-02 | 6 | 6 | Yes | No | exact | Observed matched delay | 187 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 156/6 | 2026-02-07 | 2026-02 | 2026-02-08 | 2026-02 | 1 | 1 | Yes | No | exact | Observed matched delay | 186 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 138/1 | 2026-02-10 | 2026-02 | 2026-02-15 | 2026-02 | 5 | 5 | Yes | No | exact | Observed matched delay | 183 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 138/3 | 2026-02-12 | 2026-02 | 2026-03-01 | 2026-03 | 17 | 17 | Yes | No | exact | Observed matched delay | 181 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 148B/2 | 2026-02-15 | 2026-02 | 2026-02-24 | 2026-02 | 9 | 9 | Yes | No | exact | Observed matched delay | 178 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 146/0 | 2026-02-19 | 2026-02 | 2026-03-11 | 2026-03 | 20 | 20 | Yes | No | exact | Observed matched delay | 174 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 148C/0 | 2026-02-21 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 172 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 142/1 | 2026-02-24 | 2026-02 | 2026-02-27 | 2026-02 | 3 | 3 | Yes | No | exact | Observed matched delay | 169 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 148B/0 | 2026-02-28 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 165 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 156/5 | 2026-03-03 | 2026-03 | 2026-03-15 | 2026-03 | 12 | 12 | Yes | No | exact | Observed matched delay | 162 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 169/8 | 2026-03-08 | 2026-03 | 2026-04-24 | 2026-04 | 47 | 47 | Yes | No | exact | Observed matched delay | 157 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 156/2 | 2026-03-10 | 2026-03 | 2026-05-07 | 2026-05 | 58 | 58 | Yes | No | exact | Observed matched delay | 155 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 157/0 | 2026-03-10 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 155 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 138/2 | 2026-03-11 | 2026-03 | 2026-03-14 | 2026-03 | 3 | 3 | Yes | No | exact | Observed matched delay | 154 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 144/0 | 2026-03-21 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 144 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 171/5 | 2026-03-21 | 2026-03 | 2026-06-06 | 2026-06 | 77 | 77 | Yes | No | exact | Observed matched delay | 144 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 143/0 | 2026-03-31 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 134 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 134/0 | 2026-04-09 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 125 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 137A/0 | 2026-04-09 | 2026-04 | 2026-04-13 | 2026-04 | 4 | 4 | Yes | No | exact | Observed matched delay | 125 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 129/0 | 2026-04-14 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 120 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 133/0 | 2026-04-14 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 120 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 136/4 | 2026-04-15 | 2026-04 | 2026-05-16 | 2026-05 | 31 | 31 | Yes | No | exact | Observed matched delay | 119 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 136/3 | 2026-04-18 | 2026-04 | 2026-05-07 | 2026-05 | 19 | 19 | Yes | No | exact | Observed matched delay | 116 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 129/1 | 2026-04-23 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 111 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 505 | 5xx | Government | ta505 | 117/0 | 2026-04-30 | 2026-04 | 2026-05-14 | 2026-05 | 14 | 14 | Yes | No | exact | Observed matched delay | 104 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 137/0 | 2026-05-15 | 2026-05 | 2026-06-12 | 2026-06 | 28 | 28 | Yes | No | exact | Observed matched delay | 89 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 177/0 | 2026-05-15 | 2026-05 | 2025-12-04 | 2025-12 | -162 |  | Yes | Yes | exact | Negative delay excluded | 89 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 181/2 | 2026-05-18 | 2026-05 | 2026-05-26 | 2026-05 | 8 | 8 | Yes | No | exact | Observed matched delay | 86 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 181/3 | 2026-05-25 | 2026-05 | 2026-05-30 | 2026-05 | 5 | 5 | Yes | No | exact | Observed matched delay | 79 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/0 | 2026-06-15 | 2026-06 | 2026-06-25 | 2026-06 | 10 | 10 | Yes | No | exact | Observed matched delay | 58 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 182B/0 | 2026-06-20 | 2026-06 | 2026-07-27 | 2026-07 | 37 | 37 | Yes | No | exact | Observed matched delay | 53 | TRUE | FALSE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/8 | 2026-06-23 | 2026-06 | 2026-07-17 | 2026-07 | 24 | 24 | Yes | No | exact | Observed matched delay | 50 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation | TA 505 - DPR - 2026-07-29.xlsx | Erection Compiled
TA 505 | 5xx | Government | ta505 | 179/3 | 2026-06-30 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 43 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 505 - DPR - 2026-07-29.xlsx | Foundation
TA 510 | 5xx | Government | ta510 | 155/1 | 2025-02-17 | 2025-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 541 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 155/4 | 2025-02-22 | 2025-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 536 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 155/3 | 2025-02-25 | 2025-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 533 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 155/5 | 2025-02-27 | 2025-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 531 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 156/0 | 2025-03-12 | 2025-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 518 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 156/1 | 2025-03-13 | 2025-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 517 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 156/3 | 2025-03-16 | 2025-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 514 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 156/4 | 2025-03-25 | 2025-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 505 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 156/2 | 2025-03-30 | 2025-03 | 2026-06-30 | 2026-06 | 457 | 457 | Yes | No | fallback_single_line | Observed matched delay | 500 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 139/1 | 2025-04-16 | 2025-04 | 2026-05-31 | 2026-05 | 410 | 410 | Yes | No | fallback_single_line | Observed matched delay | 483 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 138/0 | 2025-04-21 | 2025-04 | 2026-06-05 | 2026-06 | 410 | 410 | Yes | No | fallback_single_line | Observed matched delay | 478 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 139/5 | 2025-04-21 | 2025-04 | 2026-05-22 | 2026-05 | 396 | 396 | Yes | No | fallback_single_line | Observed matched delay | 478 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 137/0 | 2025-04-27 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 472 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 139/4 | 2025-04-28 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 471 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 138/1 | 2025-04-29 | 2025-04 | 2026-06-26 | 2026-06 | 423 | 423 | Yes | No | fallback_single_line | Observed matched delay | 470 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 136/0 | 2025-05-14 | 2025-05 | 2026-05-28 | 2026-05 | 379 | 379 | Yes | No | fallback_single_line | Observed matched delay | 455 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148/5 | 2025-05-15 | 2025-05 | 2026-05-03 | 2026-05 | 353 | 353 | Yes | No | fallback_single_line | Observed matched delay | 454 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148/4 | 2025-05-21 | 2025-05 | 2026-02-27 | 2026-02 | 282 | 282 | Yes | No | fallback_single_line | Observed matched delay | 448 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148/2 | 2025-05-23 | 2025-05 | 2026-02-18 | 2026-02 | 271 | 271 | Yes | No | fallback_single_line | Observed matched delay | 446 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 134/0 | 2025-05-25 | 2025-05 | 2026-02-01 | 2026-02 | 252 | 252 | Yes | No | fallback_single_line | Observed matched delay | 444 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148/7 | 2025-05-28 | 2025-05 | 2026-05-13 | 2026-05 | 350 | 350 | Yes | No | fallback_single_line | Observed matched delay | 441 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148/6 | 2025-05-31 | 2025-05 | 2026-05-08 | 2026-05 | 342 | 342 | Yes | No | fallback_single_line | Observed matched delay | 438 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 143/1 | 2025-06-02 | 2025-06 | 2026-01-16 | 2026-01 | 228 | 228 | Yes | No | fallback_single_line | Observed matched delay | 436 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 143/2 | 2025-06-05 | 2025-06 | 2026-06-05 | 2026-06 | 365 | 365 | Yes | No | fallback_single_line | Observed matched delay | 433 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 144/0 | 2025-08-06 | 2025-08 | 2026-05-29 | 2026-05 | 296 | 296 | Yes | No | fallback_single_line | Observed matched delay | 371 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 141/0 | 2025-09-16 | 2025-09 | 2026-01-08 | 2026-01 | 114 | 114 | Yes | No | fallback_single_line | Observed matched delay | 330 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 133/2 | 2025-09-18 | 2025-09 | 2026-07-15 | 2026-07 | 300 | 300 | Yes | No | fallback_single_line | Observed matched delay | 328 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 141/1 | 2025-10-04 | 2025-10 | 2026-01-01 | 2026-01 | 89 | 89 | Yes | No | fallback_single_line | Observed matched delay | 312 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 138/2 | 2025-10-05 | 2025-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 311 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 140/1 | 2025-10-10 | 2025-10 | 2026-01-14 | 2026-01 | 96 | 96 | Yes | No | fallback_single_line | Observed matched delay | 306 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 145/0 | 2025-10-19 | 2025-10 | 2026-01-22 | 2026-01 | 95 | 95 | Yes | No | fallback_single_line | Observed matched delay | 297 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 139/2 | 2025-10-24 | 2025-10 | 2026-01-05 | 2026-01 | 73 | 73 | Yes | No | fallback_single_line | Observed matched delay | 292 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 140/2 | 2025-11-19 | 2025-11 | 2026-02-08 | 2026-02 | 81 | 81 | Yes | No | fallback_single_line | Observed matched delay | 266 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 135/0 | 2025-11-24 | 2025-11 | 2026-01-13 | 2026-01 | 50 | 50 | Yes | No | fallback_single_line | Observed matched delay | 261 | TRUE | FALSE | TRUE | TRUE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 145/1 | 2025-11-24 | 2025-11 | 2026-01-30 | 2026-01 | 67 | 67 | Yes | No | fallback_single_line | Observed matched delay | 261 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 138/3 | 2025-11-27 | 2025-11 | 2026-07-04 | 2026-07 | 219 | 219 | Yes | No | fallback_single_line | Observed matched delay | 258 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 192/11 | 2025-11-30 | 2025-11 | 2026-03-01 | 2026-03 | 91 | 91 | Yes | No | fallback_single_line | Observed matched delay | 255 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 141/2 | 2025-12-07 | 2025-12 | 2026-03-08 | 2026-03 | 91 | 91 | Yes | No | fallback_single_line | Observed matched delay | 248 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 143/0 | 2025-12-09 | 2025-12 | 2026-02-12 | 2026-02 | 65 | 65 | Yes | No | fallback_single_line | Observed matched delay | 246 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 145/5 | 2025-12-09 | 2025-12 | 2026-01-27 | 2026-01 | 49 | 49 | Yes | No | fallback_single_line | Observed matched delay | 246 | TRUE | FALSE | TRUE | TRUE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148/3 | 2025-12-14 | 2025-12 | 2026-02-13 | 2026-02 | 61 | 61 | Yes | No | fallback_single_line | Observed matched delay | 241 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 192/13 | 2025-12-23 | 2025-12 | 2026-02-22 | 2026-02 | 61 | 61 | Yes | No | fallback_single_line | Observed matched delay | 232 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 145/3 | 2025-12-27 | 2025-12 | 2026-04-30 | 2026-04 | 124 | 124 | Yes | No | fallback_single_line | Observed matched delay | 228 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 146/1 | 2025-12-29 | 2025-12 | 2026-04-09 | 2026-04 | 101 | 101 | Yes | No | fallback_single_line | Observed matched delay | 226 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 140/0 | 2025-12-30 | 2025-12 | 2026-03-16 | 2026-03 | 76 | 76 | Yes | No | fallback_single_line | Observed matched delay | 225 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 146/3 | 2025-12-30 | 2025-12 | 2026-04-22 | 2026-04 | 113 | 113 | Yes | No | fallback_single_line | Observed matched delay | 225 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 145/4 | 2025-12-31 | 2025-12 | 2026-01-18 | 2026-01 | 18 | 18 | Yes | No | fallback_single_line | Observed matched delay | 224 | TRUE | TRUE | TRUE | TRUE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 192/10 | 2026-01-04 | 2026-01 | 2026-03-26 | 2026-03 | 81 | 81 | Yes | No | fallback_single_line | Observed matched delay | 220 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 147/2 | 2026-01-08 | 2026-01 | 2026-05-18 | 2026-05 | 130 | 130 | Yes | No | fallback_single_line | Observed matched delay | 216 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 146A/0 | 2026-01-13 | 2026-01 | 2026-03-24 | 2026-03 | 70 | 70 | Yes | No | fallback_single_line | Observed matched delay | 211 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 186/1 | 2026-01-13 | 2026-01 | 2026-03-10 | 2026-03 | 56 | 56 | Yes | No | fallback_single_line | Observed matched delay | 211 | TRUE | FALSE | TRUE | TRUE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 192/7 | 2026-01-21 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 203 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 192/12 | 2026-01-25 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 199 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 147/1 | 2026-01-30 | 2026-01 | 2026-05-14 | 2026-05 | 104 | 104 | Yes | No | fallback_single_line | Observed matched delay | 194 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 142/0 | 2026-02-02 | 2026-02 | 2026-05-23 | 2026-05 | 110 | 110 | Yes | No | fallback_single_line | Observed matched delay | 191 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 146/0 | 2026-02-03 | 2026-02 | 2026-04-02 | 2026-04 | 58 | 58 | Yes | No | fallback_single_line | Observed matched delay | 190 | TRUE | FALSE | TRUE | TRUE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 194/1 | 2026-02-10 | 2026-02 | 2026-03-17 | 2026-03 | 35 | 35 | Yes | No | fallback_single_line | Observed matched delay | 183 | TRUE | FALSE | TRUE | TRUE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 146A/1 | 2026-02-12 | 2026-02 | 2026-05-07 | 2026-05 | 84 | 84 | Yes | No | fallback_single_line | Observed matched delay | 181 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148/1 | 2026-02-14 | 2026-02 | 2026-02-23 | 2026-02 | 9 | 9 | Yes | No | fallback_single_line | Observed matched delay | 179 | TRUE | TRUE | TRUE | TRUE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148/0 | 2026-02-27 | 2026-02 | 2026-05-19 | 2026-05 | 81 | 81 | Yes | No | fallback_single_line | Observed matched delay | 166 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 157B/0 | 2026-03-11 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 154 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 157A/0 | 2026-03-22 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 143 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 157/2 | 2026-03-23 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 142 | TRUE | FALSE | TRUE | FALSE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 146/2 | 2026-03-31 | 2026-03 | 2026-04-15 | 2026-04 | 15 | 15 | Yes | No | fallback_single_line | Observed matched delay | 134 | TRUE | TRUE | TRUE | TRUE |  | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 192/9 | 2026-04-07 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 127 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 139/3 | 2026-04-13 | 2026-04 | 2026-05-09 | 2026-05 | 26 | 26 | Yes | No | fallback_single_line | Observed matched delay | 121 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 193/2 | 2026-04-13 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 121 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 193/1 | 2026-04-19 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 115 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 193/5 | 2026-04-20 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 114 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 139/0 | 2026-04-21 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 113 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 193/0 | 2026-04-28 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 106 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 193/4 | 2026-04-29 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 105 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 192/8 | 2026-05-06 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 98 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 167/2 | 2026-05-13 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 91 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 157B/1 | 2026-05-16 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 88 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 167/3 | 2026-05-17 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 87 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 133/0 | 2026-05-18 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 86 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 153/0 | 2026-05-20 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 84 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 167/4 | 2026-05-20 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 84 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 133/1 | 2026-05-23 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 81 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 167/1 | 2026-05-26 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 78 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 194/0 | 2026-05-27 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 77 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 150/2 | 2026-05-31 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 73 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 153/1 | 2026-05-31 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 73 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 155/0 | 2026-05-31 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 73 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 150/4 | 2026-06-06 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 67 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 155/2 | 2026-06-06 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 67 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 154/0 | 2026-06-10 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 63 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 150/3 | 2026-06-11 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 62 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 154/1 | 2026-06-14 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 59 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 160/3 | 2026-06-14 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 59 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 150/1 | 2026-06-15 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 58 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 154/2 | 2026-06-20 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 53 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 148A/0 | 2026-06-25 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 48 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 510 | 5xx | Government | ta510 | 152/1 | 2026-06-25 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 48 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | FDN |  | TA 510 - DPR - 2026-08-11.xlsx | FDN
TA 512 | 5xx | Government | ta512 | 8/1 | 2025-02-23 | 2025-02 | 2025-11-16 | 2025-11 | 266 | 266 | Yes | No | exact | Observed matched delay | 535 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 8/3 | 2025-02-26 | 2025-02 | 2025-07-25 | 2025-07 | 149 | 149 | Yes | No | exact | Observed matched delay | 532 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 8/6 | 2025-02-28 | 2025-02 | 2025-08-27 | 2025-08 | 180 | 180 | Yes | No | exact | Observed matched delay | 530 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 8/2 | 2025-03-05 | 2025-03 | 2026-03-08 | 2026-03 | 368 | 368 | Yes | No | exact | Observed matched delay | 525 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 8/5 | 2025-03-05 | 2025-03 | 2025-09-04 | 2025-09 | 183 | 183 | Yes | No | exact | Observed matched delay | 525 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 12/1 | 2025-03-07 | 2025-03 | 2025-10-10 | 2025-10 | 217 | 217 | Yes | No | exact | Observed matched delay | 523 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 12/2 | 2025-03-10 | 2025-03 | 2026-01-07 | 2026-01 | 303 | 303 | Yes | No | exact | Observed matched delay | 520 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 12/3 | 2025-03-10 | 2025-03 | 2025-10-27 | 2025-10 | 231 | 231 | Yes | No | exact | Observed matched delay | 520 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 8/4 | 2025-03-10 | 2025-03 | 2026-02-04 | 2026-02 | 331 | 331 | Yes | No | exact | Observed matched delay | 520 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 8/8 | 2025-03-10 | 2025-03 | 2025-08-11 | 2025-08 | 154 | 154 | Yes | No | exact | Observed matched delay | 520 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 12/4 | 2025-03-13 | 2025-03 | 2025-11-16 | 2025-11 | 248 | 248 | Yes | No | exact | Observed matched delay | 517 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/7 | 2025-03-15 | 2025-03 | 2026-02-14 | 2026-02 | 336 | 336 | Yes | No | exact | Observed matched delay | 515 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 18/5 | 2025-03-17 | 2025-03 | 2025-08-18 | 2025-08 | 154 | 154 | Yes | No | exact | Observed matched delay | 513 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/6 | 2025-03-17 | 2025-03 | 2025-08-26 | 2025-08 | 162 | 162 | Yes | No | exact | Observed matched delay | 513 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 18/4 | 2025-03-18 | 2025-03 | 2025-11-16 | 2025-11 | 243 | 243 | Yes | No | exact | Observed matched delay | 512 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/8 | 2025-03-20 | 2025-03 | 2025-12-12 | 2025-12 | 267 | 267 | Yes | No | exact | Observed matched delay | 510 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 18/3 | 2025-03-21 | 2025-03 | 2025-11-23 | 2025-11 | 247 | 247 | Yes | No | exact | Observed matched delay | 509 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/5 | 2025-03-21 | 2025-03 | 2026-01-29 | 2026-01 | 314 | 314 | Yes | No | exact | Observed matched delay | 509 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 19/1 | 2025-03-23 | 2025-03 | 2025-08-26 | 2025-08 | 156 | 156 | Yes | No | exact | Observed matched delay | 507 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 19/2 | 2025-03-24 | 2025-03 | 2025-10-31 | 2025-10 | 221 | 221 | Yes | No | exact | Observed matched delay | 506 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 8/7 | 2025-03-24 | 2025-03 | 2025-08-21 | 2025-08 | 150 | 150 | Yes | No | exact | Observed matched delay | 506 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 19/3 | 2025-03-25 | 2025-03 | 2025-11-07 | 2025-11 | 227 | 227 | Yes | No | exact | Observed matched delay | 505 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/10 | 2025-03-26 | 2025-03 | 2026-02-06 | 2026-02 | 317 | 317 | Yes | No | exact | Observed matched delay | 504 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/7 | 2025-03-26 | 2025-03 | 2026-01-19 | 2026-01 | 299 | 299 | Yes | No | exact | Observed matched delay | 504 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 19/6 | 2025-03-27 | 2025-03 | 2025-09-23 | 2025-09 | 180 | 180 | Yes | No | exact | Observed matched delay | 503 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 19/4 | 2025-03-28 | 2025-03 | 2025-09-08 | 2025-09 | 164 | 164 | Yes | No | exact | Observed matched delay | 502 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 19/7 | 2025-03-30 | 2025-03 | 2025-09-14 | 2025-09 | 168 | 168 | Yes | No | exact | Observed matched delay | 500 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 9/2 | 2025-03-30 | 2025-03 | 2025-09-11 | 2025-09 | 165 | 165 | Yes | No | exact | Observed matched delay | 500 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20/1 | 2025-03-31 | 2025-03 | 2025-09-28 | 2025-09 | 181 | 181 | Yes | No | exact | Observed matched delay | 499 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/8 | 2025-04-01 | 2025-04 | 2025-08-21 | 2025-08 | 142 | 142 | Yes | No | exact | Observed matched delay | 498 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/9 | 2025-04-02 | 2025-04 | 2026-02-26 | 2026-02 | 330 | 330 | Yes | No | exact | Observed matched delay | 497 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 9/3 | 2025-04-03 | 2025-04 | 2025-09-20 | 2025-09 | 170 | 170 | Yes | No | exact | Observed matched delay | 496 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20/5 | 2025-04-04 | 2025-04 | 2025-12-14 | 2025-12 | 254 | 254 | Yes | No | exact | Observed matched delay | 495 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/9 | 2025-04-06 | 2025-04 | 2025-08-13 | 2025-08 | 129 | 129 | Yes | No | exact | Observed matched delay | 493 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/6 | 2025-04-07 | 2025-04 | 2025-12-31 | 2025-12 | 268 | 268 | Yes | No | exact | Observed matched delay | 492 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20/2 | 2025-04-10 | 2025-04 | 2025-10-05 | 2025-10 | 178 | 178 | Yes | No | exact | Observed matched delay | 489 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/11 | 2025-04-11 | 2025-04 | 2025-11-23 | 2025-11 | 226 | 226 | Yes | No | exact | Observed matched delay | 488 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/5 | 2025-04-13 | 2025-04 | 2026-01-11 | 2026-01 | 273 | 273 | Yes | No | exact | Observed matched delay | 486 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/4 | 2025-04-13 | 2025-04 | 2026-01-29 | 2026-01 | 291 | 291 | Yes | No | exact | Observed matched delay | 486 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20/3 | 2025-04-15 | 2025-04 | 2025-12-01 | 2025-12 | 230 | 230 | Yes | No | exact | Observed matched delay | 484 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/4 | 2025-04-15 | 2025-04 | 2026-01-22 | 2026-01 | 282 | 282 | Yes | No | exact | Observed matched delay | 484 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/10 | 2025-04-16 | 2025-04 | 2025-11-26 | 2025-11 | 224 | 224 | Yes | No | exact | Observed matched delay | 483 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 19/5 | 2025-04-19 | 2025-04 | 2025-08-31 | 2025-08 | 134 | 134 | Yes | No | exact | Observed matched delay | 480 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/7 | 2025-04-19 | 2025-04 | 2025-09-28 | 2025-09 | 162 | 162 | Yes | No | exact | Observed matched delay | 480 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/4 | 2025-04-21 | 2025-04 | 2025-09-12 | 2025-09 | 144 | 144 | Yes | No | exact | Observed matched delay | 478 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/8 | 2025-04-23 | 2025-04 | 2025-12-24 | 2025-12 | 245 | 245 | Yes | No | exact | Observed matched delay | 476 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 28/2 | 2025-04-24 | 2025-04 | 2025-10-13 | 2025-10 | 172 | 172 | Yes | No | exact | Observed matched delay | 475 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20/6 | 2025-04-25 | 2025-04 | 2026-01-04 | 2026-01 | 254 | 254 | Yes | No | exact | Observed matched delay | 474 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/10 | 2025-04-26 | 2025-04 | 2025-12-13 | 2025-12 | 231 | 231 | Yes | No | exact | Observed matched delay | 473 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 28/1 | 2025-04-28 | 2025-04 | 2025-09-24 | 2025-09 | 149 | 149 | Yes | No | exact | Observed matched delay | 471 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/3 | 2025-04-28 | 2025-04 | 2025-09-18 | 2025-09 | 143 | 143 | Yes | No | exact | Observed matched delay | 471 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 23/3 | 2025-04-30 | 2025-04 | 2026-02-12 | 2026-02 | 288 | 288 | Yes | No | exact | Observed matched delay | 469 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/12 | 2025-04-30 | 2025-04 | 2025-12-03 | 2025-12 | 217 | 217 | Yes | No | exact | Observed matched delay | 469 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 23/2 | 2025-05-04 | 2025-05 | 2026-02-07 | 2026-02 | 279 | 279 | Yes | No | exact | Observed matched delay | 465 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/11 | 2025-05-04 | 2025-05 | 2026-02-13 | 2026-02 | 285 | 285 | Yes | No | exact | Observed matched delay | 465 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/2 | 2025-05-04 | 2025-05 | 2026-07-30 | 2026-07 | 452 | 452 | Yes | No | exact | Observed matched delay | 465 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/13 | 2025-05-07 | 2025-05 | 2026-02-06 | 2026-02 | 275 | 275 | Yes | No | exact | Observed matched delay | 462 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/14 | 2025-05-09 | 2025-05 | 2025-11-22 | 2025-11 | 197 | 197 | Yes | No | exact | Observed matched delay | 460 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/1 | 2025-05-10 | 2025-05 | 2025-09-02 | 2025-09 | 115 | 115 | Yes | No | exact | Observed matched delay | 459 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/18 | 2025-05-11 | 2025-05 | 2025-09-21 | 2025-09 | 133 | 133 | Yes | No | exact | Observed matched delay | 458 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 11/4 | 2025-05-12 | 2025-05 | 2025-12-04 | 2025-12 | 206 | 206 | Yes | No | exact | Observed matched delay | 457 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/1 | 2025-05-14 | 2025-05 | 2025-09-13 | 2025-09 | 122 | 122 | Yes | No | exact | Observed matched delay | 455 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/2 | 2025-05-15 | 2025-05 | 2025-09-02 | 2025-09 | 110 | 110 | Yes | No | exact | Observed matched delay | 454 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/3 | 2025-05-17 | 2025-05 | 2026-01-06 | 2026-01 | 234 | 234 | Yes | No | exact | Observed matched delay | 452 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/1 | 2025-05-17 | 2025-05 | 2025-08-21 | 2025-08 | 96 | 96 | Yes | No | exact | Observed matched delay | 452 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/4 | 2025-05-18 | 2025-05 | 2026-02-08 | 2026-02 | 266 | 266 | Yes | No | exact | Observed matched delay | 451 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 28/4 | 2025-05-19 | 2025-05 | 2025-11-01 | 2025-11 | 166 | 166 | Yes | No | exact | Observed matched delay | 450 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/8 | 2025-05-19 | 2025-05 | 2026-05-21 | 2026-05 | 367 | 367 | Yes | No | exact | Observed matched delay | 450 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/5 | 2025-05-20 | 2025-05 | 2026-01-11 | 2026-01 | 236 | 236 | Yes | No | exact | Observed matched delay | 449 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 11/2 | 2025-05-21 | 2025-05 | 2025-12-25 | 2025-12 | 218 | 218 | Yes | No | exact | Observed matched delay | 448 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/6 | 2025-05-23 | 2025-05 | 2026-01-19 | 2026-01 | 241 | 241 | Yes | No | exact | Observed matched delay | 446 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/10 | 2025-05-23 | 2025-05 | 2025-12-14 | 2025-12 | 205 | 205 | Yes | No | exact | Observed matched delay | 446 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/2 | 2025-05-25 | 2025-05 | 2025-12-29 | 2025-12 | 218 | 218 | Yes | No | exact | Observed matched delay | 444 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 11/3 | 2025-05-26 | 2025-05 | 2025-12-14 | 2025-12 | 202 | 202 | Yes | No | exact | Observed matched delay | 443 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/7 | 2025-05-26 | 2025-05 | 2026-01-27 | 2026-01 | 246 | 246 | Yes | No | exact | Observed matched delay | 443 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 28/7 | 2025-05-27 | 2025-05 | 2025-10-26 | 2025-10 | 152 | 152 | Yes | No | exact | Observed matched delay | 442 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 28/6 | 2025-06-01 | 2025-06 | 2025-11-05 | 2025-11 | 157 | 157 | Yes | No | exact | Observed matched delay | 437 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/3 | 2025-06-01 | 2025-06 | 2026-01-18 | 2026-01 | 231 | 231 | Yes | No | exact | Observed matched delay | 437 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 11/5 | 2025-06-04 | 2025-06 | 2025-11-27 | 2025-11 | 176 | 176 | Yes | No | exact | Observed matched delay | 434 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/8 | 2025-06-04 | 2025-06 | 2026-02-01 | 2026-02 | 242 | 242 | Yes | No | exact | Observed matched delay | 434 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 28/3 | 2025-06-06 | 2025-06 | 2026-02-02 | 2026-02 | 241 | 241 | Yes | No | exact | Observed matched delay | 432 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/12 | 2025-06-07 | 2025-06 | 2026-02-13 | 2026-02 | 251 | 251 | Yes | No | exact | Observed matched delay | 431 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/9 | 2025-06-08 | 2025-06 | 2025-12-08 | 2025-12 | 183 | 183 | Yes | No | exact | Observed matched delay | 430 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/11 | 2025-06-10 | 2025-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 428 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 28/5 | 2025-06-11 | 2025-06 | 2025-10-03 | 2025-10 | 114 | 114 | Yes | No | exact | Observed matched delay | 427 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/13 | 2025-06-11 | 2025-06 | 2026-02-07 | 2026-02 | 241 | 241 | Yes | No | exact | Observed matched delay | 427 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/11 | 2025-06-11 | 2025-06 | 2025-12-21 | 2025-12 | 193 | 193 | Yes | No | exact | Observed matched delay | 427 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/6 | 2025-06-11 | 2025-06 | 2026-02-03 | 2026-02 | 237 | 237 | Yes | No | exact | Observed matched delay | 427 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/5 | 2025-06-16 | 2025-06 | 2025-12-01 | 2025-12 | 168 | 168 | Yes | No | exact | Observed matched delay | 422 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/5 | 2025-06-16 | 2025-06 | 2026-02-09 | 2026-02 | 238 | 238 | Yes | No | exact | Observed matched delay | 422 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 27/2 | 2025-06-17 | 2025-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 421 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 31/9 | 2025-06-17 | 2025-06 | 2026-02-21 | 2026-02 | 249 | 249 | Yes | No | exact | Observed matched delay | 421 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/9 | 2025-06-18 | 2025-06 | 2026-02-21 | 2026-02 | 248 | 248 | Yes | No | exact | Observed matched delay | 420 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/4 | 2025-06-18 | 2025-06 | 2026-01-15 | 2026-01 | 211 | 211 | Yes | No | exact | Observed matched delay | 420 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 27/3 | 2025-06-20 | 2025-06 | 2026-07-07 | 2026-07 | 382 | 382 | Yes | No | exact | Observed matched delay | 418 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 6/0 | 2025-06-22 | 2025-06 | 2025-12-16 | 2025-12 | 177 | 177 | Yes | No | exact | Observed matched delay | 416 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/3 | 2025-06-23 | 2025-06 | 2026-02-11 | 2026-02 | 233 | 233 | Yes | No | exact | Observed matched delay | 415 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 19/0 | 2025-06-26 | 2025-06 | 2025-10-13 | 2025-10 | 109 | 109 | Yes | No | exact | Observed matched delay | 412 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/1 | 2025-06-26 | 2025-06 | 2025-11-29 | 2025-11 | 156 | 156 | Yes | No | exact | Observed matched delay | 412 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/14 | 2025-06-26 | 2025-06 | 2026-03-24 | 2026-03 | 271 | 271 | Yes | No | exact | Observed matched delay | 412 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/2 | 2025-06-26 | 2025-06 | 2026-01-25 | 2026-01 | 213 | 213 | Yes | No | exact | Observed matched delay | 412 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20/0 | 2025-06-30 | 2025-06 | 2025-12-20 | 2025-12 | 173 | 173 | Yes | No | exact | Observed matched delay | 408 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/4 | 2025-06-30 | 2025-06 | 2026-05-17 | 2026-05 | 321 | 321 | Yes | No | exact | Observed matched delay | 408 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 41/6 | 2025-07-01 | 2025-07 | 2026-04-14 | 2026-04 | 287 | 287 | Yes | No | exact | Observed matched delay | 407 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/2 | 2025-07-03 | 2025-07 | 2025-10-13 | 2025-10 | 102 | 102 | Yes | No | exact | Observed matched delay | 405 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/1 | 2025-07-03 | 2025-07 | 2026-02-26 | 2026-02 | 238 | 238 | Yes | No | exact | Observed matched delay | 405 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 12/5 | 2025-07-04 | 2025-07 | 2025-11-17 | 2025-11 | 136 | 136 | Yes | No | exact | Observed matched delay | 404 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/7 | 2025-07-04 | 2025-07 | 2025-11-13 | 2025-11 | 132 | 132 | Yes | No | exact | Observed matched delay | 404 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/13 | 2025-07-05 | 2025-07 | 2026-03-07 | 2026-03 | 245 | 245 | Yes | No | exact | Observed matched delay | 403 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 41/5 | 2025-07-05 | 2025-07 | 2026-04-07 | 2026-04 | 276 | 276 | Yes | No | exact | Observed matched delay | 403 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 11/6 | 2025-07-07 | 2025-07 | 2025-12-31 | 2025-12 | 177 | 177 | Yes | No | exact | Observed matched delay | 401 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/3 | 2025-07-09 | 2025-07 | 2025-11-03 | 2025-11 | 117 | 117 | Yes | No | exact | Observed matched delay | 399 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/11 | 2025-07-09 | 2025-07 | 2026-03-01 | 2026-03 | 235 | 235 | Yes | No | exact | Observed matched delay | 399 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 16/2 | 2025-07-10 | 2025-07 | 2026-08-08 | 2026-08 | 394 | 394 | Yes | No | exact | Observed matched delay | 398 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/6 | 2025-07-10 | 2025-07 | 2025-11-17 | 2025-11 | 130 | 130 | Yes | No | exact | Observed matched delay | 398 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/4 | 2025-07-12 | 2025-07 | 2025-11-25 | 2025-11 | 136 | 136 | Yes | No | exact | Observed matched delay | 396 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/12 | 2025-07-13 | 2025-07 | 2026-03-21 | 2026-03 | 251 | 251 | Yes | No | exact | Observed matched delay | 395 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 1A/1 | 2025-07-15 | 2025-07 | 2026-02-23 | 2026-02 | 223 | 223 | Yes | No | exact | Observed matched delay | 393 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/8 | 2025-07-15 | 2025-07 | 2025-12-24 | 2025-12 | 162 | 162 | Yes | No | exact | Observed matched delay | 393 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/10 | 2025-07-16 | 2025-07 | 2025-12-22 | 2025-12 | 159 | 159 | Yes | No | exact | Observed matched delay | 392 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/26 | 2025-07-17 | 2025-07 | 2025-12-01 | 2025-12 | 137 | 137 | Yes | No | exact | Observed matched delay | 391 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/3 | 2025-07-17 | 2025-07 | 2026-07-26 | 2026-07 | 374 | 374 | Yes | No | exact | Observed matched delay | 391 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/9 | 2025-07-18 | 2025-07 | 2026-01-05 | 2026-01 | 171 | 171 | Yes | No | exact | Observed matched delay | 390 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/5 | 2025-07-19 | 2025-07 | 2025-11-21 | 2025-11 | 125 | 125 | Yes | No | exact | Observed matched delay | 389 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 1A/3 | 2025-07-20 | 2025-07 | 2026-07-31 | 2026-07 | 376 | 376 | Yes | No | exact | Observed matched delay | 388 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/9 | 2025-07-20 | 2025-07 | 2025-12-20 | 2025-12 | 153 | 153 | Yes | No | exact | Observed matched delay | 388 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/14 | 2025-07-21 | 2025-07 | 2026-02-01 | 2026-02 | 195 | 195 | Yes | No | exact | Observed matched delay | 387 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 1A/2 | 2025-07-22 | 2025-07 | 2026-03-01 | 2026-03 | 222 | 222 | Yes | No | exact | Observed matched delay | 386 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/15 | 2025-07-23 | 2025-07 | 2026-01-22 | 2026-01 | 183 | 183 | Yes | No | exact | Observed matched delay | 385 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/10 | 2025-07-25 | 2025-07 | 2025-12-17 | 2025-12 | 145 | 145 | Yes | No | exact | Observed matched delay | 383 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/11 | 2025-07-25 | 2025-07 | 2025-12-29 | 2025-12 | 157 | 157 | Yes | No | exact | Observed matched delay | 383 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 40/2 | 2025-07-25 | 2025-07 | 2026-07-13 | 2026-07 | 353 | 353 | Yes | No | exact | Observed matched delay | 383 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/8 | 2025-07-26 | 2025-07 | 2026-01-04 | 2026-01 | 162 | 162 | Yes | No | exact | Observed matched delay | 382 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2/2 | 2025-07-29 | 2025-07 | 2026-02-07 | 2026-02 | 193 | 193 | Yes | No | exact | Observed matched delay | 379 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/24 | 2025-07-29 | 2025-07 | 2026-07-07 | 2026-07 | 343 | 343 | Yes | No | exact | Observed matched delay | 379 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 40/3 | 2025-07-29 | 2025-07 | 2026-05-16 | 2026-05 | 291 | 291 | Yes | No | exact | Observed matched delay | 379 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/0 | 2025-07-30 | 2025-07 | 2026-01-22 | 2026-01 | 176 | 176 | Yes | No | exact | Observed matched delay | 378 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/20 | 2025-07-31 | 2025-07 | 2025-12-11 | 2025-12 | 133 | 133 | Yes | No | exact | Observed matched delay | 377 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/0 | 2025-08-01 | 2025-08 | 2025-10-19 | 2025-10 | 79 | 79 | Yes | No | exact | Observed matched delay | 376 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/12 | 2025-08-01 | 2025-08 | 2025-12-09 | 2025-12 | 130 | 130 | Yes | No | exact | Observed matched delay | 376 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/19 | 2025-08-01 | 2025-08 | 2026-03-02 | 2026-03 | 213 | 213 | Yes | No | exact | Observed matched delay | 376 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/7 | 2025-08-02 | 2025-08 | 2025-12-20 | 2025-12 | 140 | 140 | Yes | No | exact | Observed matched delay | 375 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2/4 | 2025-08-03 | 2025-08 | 2026-01-27 | 2026-01 | 177 | 177 | Yes | No | exact | Observed matched delay | 374 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3A/3 | 2025-08-03 | 2025-08 | 2026-01-15 | 2026-01 | 165 | 165 | Yes | No | exact | Observed matched delay | 374 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 40/4 | 2025-08-03 | 2025-08 | 2026-07-20 | 2026-07 | 351 | 351 | Yes | No | exact | Observed matched delay | 374 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/20 | 2025-08-05 | 2025-08 | 2026-01-02 | 2026-01 | 150 | 150 | Yes | No | exact | Observed matched delay | 372 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/16 | 2025-08-05 | 2025-08 | 2026-01-11 | 2026-01 | 159 | 159 | Yes | No | exact | Observed matched delay | 372 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/6 | 2025-08-06 | 2025-08 | 2026-03-06 | 2026-03 | 212 | 212 | Yes | No | exact | Observed matched delay | 371 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/15 | 2025-08-07 | 2025-08 | 2025-12-05 | 2025-12 | 120 | 120 | Yes | No | exact | Observed matched delay | 370 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/21 | 2025-08-07 | 2025-08 | 2026-07-18 | 2026-07 | 345 | 345 | Yes | No | exact | Observed matched delay | 370 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/23 | 2025-08-07 | 2025-08 | 2026-03-14 | 2026-03 | 219 | 219 | Yes | No | exact | Observed matched delay | 370 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3A/2 | 2025-08-07 | 2025-08 | 2026-01-15 | 2026-01 | 161 | 161 | Yes | No | exact | Observed matched delay | 370 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2/5 | 2025-08-08 | 2025-08 | 2026-01-10 | 2026-01 | 155 | 155 | Yes | No | exact | Observed matched delay | 369 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2/1 | 2025-08-13 | 2025-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 364 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 30/2 | 2025-08-13 | 2025-08 | 2025-10-05 | 2025-10 | 53 | 53 | Yes | No | exact | Observed matched delay | 364 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/5 | 2025-08-14 | 2025-08 | 2026-05-13 | 2026-05 | 272 | 272 | Yes | No | exact | Observed matched delay | 363 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3A/1 | 2025-08-14 | 2025-08 | 2026-01-22 | 2026-01 | 161 | 161 | Yes | No | exact | Observed matched delay | 363 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 9/1 | 2025-08-21 | 2025-08 | 2025-11-29 | 2025-11 | 100 | 100 | Yes | No | exact | Observed matched delay | 356 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/16 | 2025-08-22 | 2025-08 | 2026-08-03 | 2026-08 | 346 | 346 | Yes | No | exact | Observed matched delay | 355 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/22 | 2025-08-22 | 2025-08 | 2026-07-25 | 2026-07 | 337 | 337 | Yes | No | exact | Observed matched delay | 355 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/3 | 2025-08-23 | 2025-08 | 2026-03-10 | 2026-03 | 199 | 199 | Yes | No | exact | Observed matched delay | 354 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 41/0 | 2025-08-28 | 2025-08 | 2026-02-22 | 2026-02 | 178 | 178 | Yes | No | exact | Observed matched delay | 349 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 9/0 | 2025-08-28 | 2025-08 | 2025-09-25 | 2025-09 | 28 | 28 | Yes | No | exact | Observed matched delay | 349 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/7 | 2025-08-29 | 2025-08 | 2026-04-30 | 2026-04 | 244 | 244 | Yes | No | exact | Observed matched delay | 348 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/18 | 2025-09-03 | 2025-09 | 2026-06-25 | 2026-06 | 295 | 295 | Yes | No | exact | Observed matched delay | 343 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 36/9 | 2025-09-03 | 2025-09 | 2026-07-13 | 2026-07 | 313 | 313 | Yes | No | exact | Observed matched delay | 343 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/5 | 2025-09-03 | 2025-09 |  |  |  |  | No | No |  | Unmatched/right-censored | 343 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 36/8 | 2025-09-06 | 2025-09 | 2026-01-29 | 2026-01 | 145 | 145 | Yes | No | exact | Observed matched delay | 340 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/6 | 2025-09-06 | 2025-09 | 2026-08-10 | 2026-08 | 338 | 338 | Yes | No | exact | Observed matched delay | 340 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 8/0 | 2025-09-06 | 2025-09 | 2025-11-20 | 2025-11 | 75 | 75 | Yes | No | exact | Observed matched delay | 340 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/2 | 2025-09-09 | 2025-09 | 2026-05-26 | 2026-05 | 259 | 259 | Yes | No | exact | Observed matched delay | 337 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/14 | 2025-09-11 | 2025-09 | 2026-01-22 | 2026-01 | 133 | 133 | Yes | No | exact | Observed matched delay | 335 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 36/7 | 2025-09-11 | 2025-09 | 2026-02-12 | 2026-02 | 154 | 154 | Yes | No | exact | Observed matched delay | 335 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 36/6 | 2025-09-16 | 2025-09 | 2026-02-06 | 2026-02 | 143 | 143 | Yes | No | exact | Observed matched delay | 330 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/5 | 2025-09-16 | 2025-09 | 2026-01-18 | 2026-01 | 124 | 124 | Yes | No | exact | Observed matched delay | 330 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/6 | 2025-09-16 | 2025-09 | 2025-12-25 | 2025-12 | 100 | 100 | Yes | No | exact | Observed matched delay | 330 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 7/0 | 2025-09-16 | 2025-09 | 2026-02-14 | 2026-02 | 151 | 151 | Yes | No | exact | Observed matched delay | 330 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 36/5 | 2025-09-21 | 2025-09 | 2026-08-03 | 2026-08 | 316 | 316 | Yes | No | exact | Observed matched delay | 325 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/8 | 2025-09-22 | 2025-09 | 2026-02-09 | 2026-02 | 140 | 140 | Yes | No | exact | Observed matched delay | 324 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 13/0 | 2025-09-23 | 2025-09 | 2026-01-16 | 2026-01 | 115 | 115 | Yes | No | exact | Observed matched delay | 323 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/9 | 2025-09-25 | 2025-09 | 2026-02-16 | 2026-02 | 144 | 144 | Yes | No | exact | Observed matched delay | 321 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 36/4 | 2025-09-26 | 2025-09 |  |  |  |  | No | No |  | Unmatched/right-censored | 320 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 36/3 | 2025-09-29 | 2025-09 | 2026-03-15 | 2026-03 | 167 | 167 | Yes | No | exact | Observed matched delay | 317 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/19 | 2025-10-01 | 2025-10 | 2026-06-16 | 2026-06 | 258 | 258 | Yes | No | exact | Observed matched delay | 315 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/9 | 2025-10-04 | 2025-10 | 2026-04-03 | 2026-04 | 181 | 181 | Yes | No | exact | Observed matched delay | 312 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/0 | 2025-10-04 | 2025-10 | 2026-03-22 | 2026-03 | 169 | 169 | Yes | No | exact | Observed matched delay | 312 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/7 | 2025-10-09 | 2025-10 | 2026-01-02 | 2026-01 | 85 | 85 | Yes | No | exact | Observed matched delay | 307 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20/4 | 2025-10-12 | 2025-10 | 2025-12-07 | 2025-12 | 56 | 56 | Yes | No | exact | Observed matched delay | 304 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/10 | 2025-10-12 | 2025-10 | 2026-03-06 | 2026-03 | 145 | 145 | Yes | No | exact | Observed matched delay | 304 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 36/2 | 2025-10-12 | 2025-10 | 2026-07-26 | 2026-07 | 287 | 287 | Yes | No | exact | Observed matched delay | 304 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/2 | 2025-10-16 | 2025-10 | 2026-03-30 | 2026-03 | 165 | 165 | Yes | No | exact | Observed matched delay | 300 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 18/2 | 2025-10-17 | 2025-10 | 2026-01-22 | 2026-01 | 97 | 97 | Yes | No | exact | Observed matched delay | 299 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/0 | 2025-10-17 | 2025-10 | 2026-06-30 | 2026-06 | 256 | 256 | Yes | No | exact | Observed matched delay | 299 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/3 | 2025-10-18 | 2025-10 | 2026-04-03 | 2026-04 | 167 | 167 | Yes | No | exact | Observed matched delay | 298 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/17 | 2025-10-19 | 2025-10 | 2025-12-21 | 2025-12 | 63 | 63 | Yes | No | exact | Observed matched delay | 297 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3/1 | 2025-10-23 | 2025-10 | 2026-07-20 | 2026-07 | 270 | 270 | Yes | No | exact | Observed matched delay | 293 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/13 | 2025-10-25 | 2025-10 | 2026-01-17 | 2026-01 | 84 | 84 | Yes | No | exact | Observed matched delay | 291 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 35/0 | 2025-10-25 | 2025-10 | 2026-02-17 | 2026-02 | 115 | 115 | Yes | No | exact | Observed matched delay | 291 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/18 | 2025-10-26 | 2025-10 | 2025-12-30 | 2025-12 | 65 | 65 | Yes | No | exact | Observed matched delay | 290 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/4 | 2025-10-26 | 2025-10 | 2026-04-10 | 2026-04 | 166 | 166 | Yes | No | exact | Observed matched delay | 290 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 12/0 | 2025-10-27 | 2025-10 | 2026-07-10 | 2026-07 | 256 | 256 | Yes | No | exact | Observed matched delay | 289 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3/2 | 2025-10-28 | 2025-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 288 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 3/3 | 2025-10-30 | 2025-10 | 2026-02-15 | 2026-02 | 108 | 108 | Yes | No | exact | Observed matched delay | 286 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/0 | 2025-10-30 | 2025-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 286 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 40/1 | 2025-10-30 | 2025-10 | 2026-06-11 | 2026-06 | 224 | 224 | Yes | No | exact | Observed matched delay | 286 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 9/4 | 2025-10-30 | 2025-10 | 2025-12-08 | 2025-12 | 39 | 39 | Yes | No | exact | Observed matched delay | 286 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/21 | 2025-11-01 | 2025-11 | 2026-01-09 | 2026-01 | 69 | 69 | Yes | No | exact | Observed matched delay | 284 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 35/1 | 2025-11-01 | 2025-11 | 2026-02-25 | 2026-02 | 116 | 116 | Yes | No | exact | Observed matched delay | 284 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3/4 | 2025-11-02 | 2025-11 | 2026-02-25 | 2026-02 | 115 | 115 | Yes | No | exact | Observed matched delay | 283 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 37/1 | 2025-11-03 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 282 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 30/17 | 2025-11-04 | 2025-11 | 2026-03-08 | 2026-03 | 124 | 124 | Yes | No | exact | Observed matched delay | 281 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 11/1 | 2025-11-05 | 2025-11 | 2025-12-19 | 2025-12 | 44 | 44 | Yes | No | exact | Observed matched delay | 280 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3/5 | 2025-11-06 | 2025-11 | 2026-02-05 | 2026-02 | 91 | 91 | Yes | No | exact | Observed matched delay | 279 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 35/2 | 2025-11-07 | 2025-11 | 2026-03-29 | 2026-03 | 142 | 142 | Yes | No | exact | Observed matched delay | 278 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/17 | 2025-11-09 | 2025-11 | 2026-01-13 | 2026-01 | 65 | 65 | Yes | No | exact | Observed matched delay | 276 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3/6 | 2025-11-09 | 2025-11 | 2026-01-31 | 2026-01 | 83 | 83 | Yes | No | exact | Observed matched delay | 276 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 40/0 | 2025-11-10 | 2025-11 | 2026-06-19 | 2026-06 | 221 | 221 | Yes | No | exact | Observed matched delay | 275 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 16/1 | 2025-11-11 | 2025-11 | 2026-06-08 | 2026-06 | 209 | 209 | Yes | No | exact | Observed matched delay | 274 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3/7 | 2025-11-12 | 2025-11 | 2026-01-27 | 2026-01 | 76 | 76 | Yes | No | exact | Observed matched delay | 273 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/25 | 2025-11-12 | 2025-11 | 2026-03-22 | 2026-03 | 130 | 130 | Yes | No | exact | Observed matched delay | 273 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 35/3 | 2025-11-13 | 2025-11 | 2026-03-10 | 2026-03 | 117 | 117 | Yes | No | exact | Observed matched delay | 272 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 39/0 | 2025-11-14 | 2025-11 | 2026-07-22 | 2026-07 | 250 | 250 | Yes | No | exact | Observed matched delay | 271 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 11/8 | 2025-11-16 | 2025-11 | 2026-01-27 | 2026-01 | 72 | 72 | Yes | No | exact | Observed matched delay | 269 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 38/2 | 2025-11-16 | 2025-11 | 2026-07-20 | 2026-07 | 246 | 246 | Yes | No | exact | Observed matched delay | 269 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/27 | 2025-11-17 | 2025-11 | 2026-01-19 | 2026-01 | 63 | 63 | Yes | No | exact | Observed matched delay | 268 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/1 | 2025-11-18 | 2025-11 | 2026-06-21 | 2026-06 | 215 | 215 | Yes | No | exact | Observed matched delay | 267 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3A/0 | 2025-11-19 | 2025-11 | 2026-03-29 | 2026-03 | 130 | 130 | Yes | No | exact | Observed matched delay | 266 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20/7 | 2025-11-21 | 2025-11 | 2026-01-15 | 2026-01 | 55 | 55 | Yes | No | exact | Observed matched delay | 264 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 38/0 | 2025-11-22 | 2025-11 | 2026-04-08 | 2026-04 | 137 | 137 | Yes | No | exact | Observed matched delay | 263 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 29/16 | 2025-11-24 | 2025-11 | 2026-06-09 | 2026-06 | 197 | 197 | Yes | No | exact | Observed matched delay | 261 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 38/1 | 2025-11-24 | 2025-11 | 2026-07-11 | 2026-07 | 229 | 229 | Yes | No | exact | Observed matched delay | 261 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 32/0 | 2025-11-25 | 2025-11 | 2026-06-21 | 2026-06 | 208 | 208 | Yes | No | exact | Observed matched delay | 260 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 32/4 | 2025-11-28 | 2025-11 | 2026-07-22 | 2026-07 | 236 | 236 | Yes | No | exact | Observed matched delay | 257 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 3/0 | 2025-11-29 | 2025-11 | 2026-07-31 | 2026-07 | 244 | 244 | Yes | No | exact | Observed matched delay | 256 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/8 | 2025-11-29 | 2025-11 | 2026-05-06 | 2026-05 | 158 | 158 | Yes | No | exact | Observed matched delay | 256 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 21/0 | 2025-12-01 | 2025-12 | 2026-06-29 | 2026-06 | 210 | 210 | Yes | No | exact | Observed matched delay | 254 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 32/1 | 2025-12-01 | 2025-12 | 2026-08-07 | 2026-08 | 249 | 249 | Yes | No | exact | Observed matched delay | 254 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2A/5 | 2025-12-02 | 2025-12 | 2026-07-07 | 2026-07 | 217 | 217 | Yes | No | exact | Observed matched delay | 253 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 32/3 | 2025-12-02 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 253 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 5/0 | 2025-12-02 | 2025-12 | 2026-02-01 | 2026-02 | 61 | 61 | Yes | No | exact | Observed matched delay | 253 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 35/5 | 2025-12-03 | 2025-12 | 2026-03-17 | 2026-03 | 104 | 104 | Yes | No | exact | Observed matched delay | 252 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 32/5 | 2025-12-04 | 2025-12 | 2026-01-30 | 2026-01 | 57 | 57 | Yes | No | exact | Observed matched delay | 251 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2A/4 | 2025-12-05 | 2025-12 | 2026-04-06 | 2026-04 | 122 | 122 | Yes | No | exact | Observed matched delay | 250 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 32/6 | 2025-12-06 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 249 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 35/4 | 2025-12-07 | 2025-12 | 2026-03-23 | 2026-03 | 106 | 106 | Yes | No | exact | Observed matched delay | 248 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/4 | 2025-12-07 | 2025-12 | 2026-02-01 | 2026-02 | 56 | 56 | Yes | No | exact | Observed matched delay | 248 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 30/3 | 2025-12-08 | 2025-12 | 2026-01-28 | 2026-01 | 51 | 51 | Yes | No | exact | Observed matched delay | 247 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2A/3 | 2025-12-09 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 246 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 35/6 | 2025-12-10 | 2025-12 | 2026-03-21 | 2026-03 | 101 | 101 | Yes | No | exact | Observed matched delay | 245 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2A/2 | 2025-12-12 | 2025-12 | 2026-05-31 | 2026-05 | 170 | 170 | Yes | No | exact | Observed matched delay | 243 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/2 | 2025-12-12 | 2025-12 | 2026-07-31 | 2026-07 | 231 | 231 | Yes | No | exact | Observed matched delay | 243 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 20A/0 | 2025-12-13 | 2025-12 | 2026-07-10 | 2026-07 | 209 | 209 | Yes | No | exact | Observed matched delay | 242 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 35/8 | 2025-12-14 | 2025-12 | 2026-02-27 | 2026-02 | 75 | 75 | Yes | No | exact | Observed matched delay | 241 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 4/1 | 2025-12-14 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 241 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 2A/1 | 2025-12-16 | 2025-12 | 2026-06-21 | 2026-06 | 187 | 187 | Yes | No | exact | Observed matched delay | 239 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 32/7 | 2025-12-16 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 239 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 23/1 | 2025-12-17 | 2025-12 | 2026-02-24 | 2026-02 | 69 | 69 | Yes | No | exact | Observed matched delay | 238 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 28/0 | 2025-12-17 | 2025-12 | 2026-02-15 | 2026-02 | 60 | 60 | Yes | No | exact | Observed matched delay | 238 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 33/2 | 2025-12-17 | 2025-12 | 2026-02-27 | 2026-02 | 72 | 72 | Yes | No | exact | Observed matched delay | 238 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 35/7 | 2025-12-17 | 2025-12 | 2026-03-12 | 2026-03 | 85 | 85 | Yes | No | exact | Observed matched delay | 238 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/6 | 2025-12-19 | 2025-12 | 2026-03-10 | 2026-03 | 81 | 81 | Yes | No | exact | Observed matched delay | 236 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 35/9 | 2025-12-21 | 2025-12 | 2026-02-19 | 2026-02 | 60 | 60 | Yes | No | exact | Observed matched delay | 234 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 33/4 | 2025-12-23 | 2025-12 | 2026-04-24 | 2026-04 | 122 | 122 | Yes | No | exact | Observed matched delay | 232 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2A/0 | 2025-12-25 | 2025-12 | 2026-06-27 | 2026-06 | 184 | 184 | Yes | No | exact | Observed matched delay | 230 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 36/0 | 2025-12-26 | 2025-12 | 2026-08-10 | 2026-08 | 227 | 227 | Yes | No | exact | Observed matched delay | 229 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 5/7 | 2025-12-26 | 2025-12 | 2026-03-14 | 2026-03 | 78 | 78 | Yes | No | exact | Observed matched delay | 229 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 22/0 | 2025-12-27 | 2025-12 | 2026-06-19 | 2026-06 | 174 | 174 | Yes | No | exact | Observed matched delay | 228 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 27/1 | 2025-12-27 | 2025-12 | 2026-07-10 | 2026-07 | 195 | 195 | Yes | No | exact | Observed matched delay | 228 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2/6 | 2025-12-30 | 2025-12 | 2026-03-10 | 2026-03 | 70 | 70 | Yes | No | exact | Observed matched delay | 225 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 36/1 | 2025-12-30 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 225 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 29/22 | 2025-12-31 | 2025-12 | 2026-01-27 | 2026-01 | 27 | 27 | Yes | No | exact | Observed matched delay | 224 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2/3 | 2026-01-03 | 2026-01 | 2026-03-19 | 2026-03 | 75 | 75 | Yes | No | exact | Observed matched delay | 221 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 23/0 | 2026-01-04 | 2026-01 | 2026-06-03 | 2026-06 | 150 | 150 | Yes | No | exact | Observed matched delay | 220 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 33A/0 | 2026-01-05 | 2026-01 | 2026-06-19 | 2026-06 | 165 | 165 | Yes | No | exact | Observed matched delay | 219 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 18/1 | 2026-01-11 | 2026-01 | 2026-02-10 | 2026-02 | 30 | 30 | Yes | No | exact | Observed matched delay | 213 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 42/0 | 2026-01-11 | 2026-01 | 2026-08-06 | 2026-08 | 207 | 207 | Yes | No | exact | Observed matched delay | 213 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 13/1 | 2026-01-12 | 2026-01 | 2026-07-18 | 2026-07 | 187 | 187 | Yes | No | exact | Observed matched delay | 212 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 34/0 | 2026-01-13 | 2026-01 | 2026-06-30 | 2026-06 | 168 | 168 | Yes | No | exact | Observed matched delay | 211 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 43/0 | 2026-01-16 | 2026-01 | 2026-07-20 | 2026-07 | 185 | 185 | Yes | No | exact | Observed matched delay | 208 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 2/0 | 2026-01-20 | 2026-01 | 2026-07-18 | 2026-07 | 179 | 179 | Yes | No | exact | Observed matched delay | 204 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 33/3 | 2026-01-21 | 2026-01 | 2026-04-18 | 2026-04 | 87 | 87 | Yes | No | exact | Observed matched delay | 203 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 33/1 | 2026-01-31 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 193 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 10/0 | 2026-02-02 | 2026-02 | 2026-06-24 | 2026-06 | 142 | 142 | Yes | No | exact | Observed matched delay | 191 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 16/3 | 2026-02-07 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 186 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 32/8 | 2026-02-19 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 174 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 32/9 | 2026-02-22 | 2026-02 | 2026-06-12 | 2026-06 | 110 | 110 | Yes | No | exact | Observed matched delay | 171 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 33/0 | 2026-03-03 | 2026-03 | 2026-06-05 | 2026-06 | 94 | 94 | Yes | No | exact | Observed matched delay | 162 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 44/0 | 2026-03-09 | 2026-03 | 2026-08-09 | 2026-08 | 153 | 153 | Yes | No | exact | Observed matched delay | 156 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 32/2 | 2026-03-15 | 2026-03 | 2026-03-29 | 2026-03 | 14 | 14 | Yes | No | exact | Observed matched delay | 150 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 17/0 | 2026-04-03 | 2026-04 | 2026-06-17 | 2026-06 | 75 | 75 | Yes | No | exact | Observed matched delay | 131 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 47/0 | 2026-04-08 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 126 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 18/0 | 2026-04-12 | 2026-04 | 2026-06-29 | 2026-06 | 78 | 78 | Yes | No | exact | Observed matched delay | 122 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 44/1 | 2026-04-15 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 119 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 45/0 | 2026-04-24 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 110 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 46/0 | 2026-04-24 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 110 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 34/1 | 2026-04-29 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 105 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 11/7 | 2026-05-09 | 2026-05 | 2026-07-04 | 2026-07 | 56 | 56 | Yes | No | exact | Observed matched delay | 95 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 31/10 | 2026-05-21 | 2026-05 | 2026-08-11 | 2026-08 | 82 | 82 | Yes | No | exact | Observed matched delay | 83 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 27/0 | 2026-05-25 | 2026-05 | 2026-07-19 | 2026-07 | 55 | 55 | Yes | No | exact | Observed matched delay | 79 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 11/0 | 2026-05-29 | 2026-05 | 2026-07-12 | 2026-07 | 44 | 44 | Yes | No | exact | Observed matched delay | 75 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 25/1 | 2026-05-31 | 2026-05 | 2026-07-13 | 2026-07 | 43 | 43 | Yes | No | exact | Observed matched delay | 73 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 1A/0 | 2026-06-03 | 2026-06 | 2026-08-08 | 2026-08 | 66 | 66 | Yes | No | exact | Observed matched delay | 70 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 16/0 | 2026-06-04 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 69 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 26/0 | 2026-06-10 | 2026-06 | 2026-07-21 | 2026-07 | 41 | 41 | Yes | No | exact | Observed matched delay | 63 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 23/4 | 2026-06-12 | 2026-06 | 2026-07-11 | 2026-07 | 29 | 29 | Yes | No | exact | Observed matched delay | 61 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 1/2 | 2026-06-24 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 49 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 24/0 | 2026-06-25 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 48 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 1/1 | 2026-07-01 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 42 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 32/10 | 2026-07-03 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 40 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 25/0 | 2026-07-05 | 2026-07 | 2026-07-31 | 2026-07 | 26 | 26 | Yes | No | exact | Observed matched delay | 38 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation | TA 512 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 512 | 5xx | Government | ta512 | 1/0 | 2026-07-09 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 34 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 512 | 5xx | Government | ta512 | 30/15 | 2026-08-05 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 7 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 512 - DPR - 2026-08-11.xlsx | Foundation
TA 513 | 5xx | Government | ta513 | 25/1 | 2025-03-28 | 2025-03 | 2025-09-23 | 2025-09 | 179 | 179 | Yes | No | fallback_single_line | Observed matched delay | 502 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 25/2 | 2025-04-01 | 2025-04 | 2025-09-17 | 2025-09 | 169 | 169 | Yes | No | fallback_single_line | Observed matched delay | 498 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 24/2 | 2025-04-04 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 495 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 24/1 | 2025-04-07 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 492 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 26/2 | 2025-04-12 | 2025-04 | 2025-10-03 | 2025-10 | 174 | 174 | Yes | No | fallback_single_line | Observed matched delay | 487 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 30/2 | 2025-04-12 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 487 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 23/6 | 2025-04-14 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 485 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 23/5 | 2025-04-16 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 483 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 31/1 | 2025-04-17 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 482 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 30/3 | 2025-04-22 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 477 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 37/1 | 2025-04-24 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 475 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 30/1 | 2025-04-25 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 474 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 30/2 | 2025-04-28 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 471 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 24/3 | 2025-04-29 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 470 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 31/2 | 2025-04-30 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 469 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 29/5 | 2025-05-01 | 2025-05 | 2025-11-11 | 2025-11 | 194 | 194 | Yes | No | fallback_single_line | Observed matched delay | 468 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 29/2 | 2025-05-03 | 2025-05 | 2025-11-27 | 2025-11 | 208 | 208 | Yes | No | fallback_single_line | Observed matched delay | 466 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 29/4 | 2025-05-04 | 2025-05 | 2025-11-03 | 2025-11 | 183 | 183 | Yes | No | fallback_single_line | Observed matched delay | 465 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 29/3 | 2025-05-05 | 2025-05 | 2025-11-15 | 2025-11 | 194 | 194 | Yes | No | fallback_single_line | Observed matched delay | 464 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 29/1 | 2025-05-06 | 2025-05 | 2025-12-03 | 2025-12 | 211 | 211 | Yes | No | fallback_single_line | Observed matched delay | 463 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 28/3 | 2025-05-09 | 2025-05 | 2025-10-25 | 2025-10 | 169 | 169 | Yes | No | fallback_single_line | Observed matched delay | 460 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 28/4 | 2025-05-09 | 2025-05 | 2025-11-06 | 2025-11 | 181 | 181 | Yes | No | fallback_single_line | Observed matched delay | 460 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 28/2 | 2025-05-11 | 2025-05 | 2025-10-31 | 2025-10 | 173 | 173 | Yes | No | fallback_single_line | Observed matched delay | 458 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 24/4 | 2025-05-17 | 2025-05 | 2025-09-29 | 2025-09 | 135 | 135 | Yes | No | fallback_single_line | Observed matched delay | 452 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 3/5 | 2025-05-20 | 2025-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 449 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/7 | 2025-05-20 | 2025-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 449 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 23/3 | 2025-05-24 | 2025-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 445 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 3/6 | 2025-05-24 | 2025-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 445 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 3/10 | 2025-05-27 | 2025-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 442 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 32B/1 | 2025-05-28 | 2025-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 441 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 21/7 | 2025-06-02 | 2025-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 436 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 21/6 | 2025-06-05 | 2025-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 433 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 23/1 | 2025-06-07 | 2025-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 431 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 23/3 | 2025-06-09 | 2025-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 429 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 23/2 | 2025-06-11 | 2025-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 427 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 23/4 | 2025-06-15 | 2025-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 423 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 18/4 | 2025-06-28 | 2025-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 410 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 56/1 | 2025-06-28 | 2025-06 | 2026-03-08 | 2026-03 | 253 | 253 | Yes | No | fallback_single_line | Observed matched delay | 410 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 14/4 | 2025-07-01 | 2025-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 407 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 26/1 | 2025-07-03 | 2025-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 405 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 56/2 | 2025-07-05 | 2025-07 | 2026-01-23 | 2026-01 | 202 | 202 | Yes | No | fallback_single_line | Observed matched delay | 403 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 14/3 | 2025-07-07 | 2025-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 401 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 56/4 | 2025-07-10 | 2025-07 | 2026-06-04 | 2026-06 | 329 | 329 | Yes | No | fallback_single_line | Observed matched delay | 398 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 14/2 | 2025-07-13 | 2025-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 395 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 56/0 | 2025-07-15 | 2025-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 393 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/5 | 2025-07-20 | 2025-07 | 2025-12-15 | 2025-12 | 148 | 148 | Yes | No | fallback_single_line | Observed matched delay | 388 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 15B/4 | 2025-07-21 | 2025-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 387 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/0 | 2025-07-24 | 2025-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 384 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/6 | 2025-07-28 | 2025-07 | 2026-01-16 | 2026-01 | 172 | 172 | Yes | No | fallback_single_line | Observed matched delay | 380 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 54/6 | 2025-08-09 | 2025-08 | 2026-01-29 | 2026-01 | 173 | 173 | Yes | No | fallback_single_line | Observed matched delay | 368 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 36/3 | 2025-08-20 | 2025-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 357 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 56/3 | 2025-08-24 | 2025-08 | 2026-06-12 | 2026-06 | 292 | 292 | Yes | No | fallback_single_line | Observed matched delay | 353 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 36/4 | 2025-09-01 | 2025-09 |  |  |  |  | No | No |  | Unmatched/right-censored | 345 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 27/0 | 2025-09-14 | 2025-09 | 2025-10-19 | 2025-10 | 35 | 35 | Yes | No | fallback_single_line | Observed matched delay | 332 | TRUE | FALSE | TRUE | TRUE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 26/0 | 2025-09-18 | 2025-09 | 2025-10-14 | 2025-10 | 26 | 26 | Yes | No | fallback_single_line | Observed matched delay | 328 | TRUE | TRUE | TRUE | TRUE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 30/0 | 2025-09-19 | 2025-09 |  |  |  |  | No | No |  | Unmatched/right-censored | 327 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 25/0 | 2025-09-20 | 2025-09 | 2025-10-10 | 2025-10 | 20 | 20 | Yes | No | fallback_single_line | Observed matched delay | 326 | TRUE | TRUE | TRUE | TRUE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 24/0 | 2025-09-24 | 2025-09 |  |  |  |  | No | No |  | Unmatched/right-censored | 322 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 29/0 | 2025-09-24 | 2025-09 | 2025-11-19 | 2025-11 | 56 | 56 | Yes | No | fallback_single_line | Observed matched delay | 322 | TRUE | FALSE | TRUE | TRUE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 19/0 | 2025-10-01 | 2025-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 315 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 28/0 | 2025-10-05 | 2025-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 311 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 18/0 | 2025-10-06 | 2025-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 310 | TRUE | FALSE | TRUE | FALSE |  | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 54/3 | 2025-11-11 | 2025-11 | 2026-03-01 | 2026-03 | 110 | 110 | Yes | No | fallback_single_line | Observed matched delay | 274 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 54/7 | 2025-11-23 | 2025-11 | 2026-03-16 | 2026-03 | 113 | 113 | Yes | No | fallback_single_line | Observed matched delay | 262 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 51/4 | 2025-12-05 | 2025-12 | 2026-05-18 | 2026-05 | 164 | 164 | Yes | No | fallback_single_line | Observed matched delay | 250 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 51/2 | 2025-12-09 | 2025-12 | 2026-05-10 | 2026-05 | 152 | 152 | Yes | No | fallback_single_line | Observed matched delay | 246 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 54/5 | 2025-12-15 | 2025-12 | 2026-03-12 | 2026-03 | 87 | 87 | Yes | No | fallback_single_line | Observed matched delay | 240 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 52/4 | 2025-12-18 | 2025-12 | 2026-04-01 | 2026-04 | 104 | 104 | Yes | No | fallback_single_line | Observed matched delay | 237 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 51/5 | 2025-12-23 | 2025-12 | 2026-05-23 | 2026-05 | 151 | 151 | Yes | No | fallback_single_line | Observed matched delay | 232 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 54/8 | 2026-02-15 | 2026-02 | 2026-03-24 | 2026-03 | 37 | 37 | Yes | No | fallback_single_line | Observed matched delay | 178 | TRUE | FALSE | TRUE | TRUE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 52/3 | 2026-02-25 | 2026-02 | 2026-05-31 | 2026-05 | 95 | 95 | Yes | No | fallback_single_line | Observed matched delay | 168 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/1 | 2026-03-07 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 158 | TRUE | FALSE | TRUE | FALSE |  | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/2 | 2026-04-11 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 123 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 52/2 | 2026-05-03 | 2026-05 | 2026-06-17 | 2026-06 | 45 | 45 | Yes | No | fallback_single_line | Observed matched delay | 101 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/4 | 2026-05-04 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 100 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 52/0 | 2026-05-05 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 99 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 52/1 | 2026-05-10 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 94 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 52/5 | 2026-05-11 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 93 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/3 | 2026-05-15 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 89 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 64/2 | 2026-05-16 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 88 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 30/0 | 2026-05-17 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 87 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 64/5 | 2026-05-19 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 85 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 64/3 | 2026-05-21 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 83 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 28/1 | 2026-05-22 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 82 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 51/3 | 2026-05-23 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 81 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 64/4 | 2026-05-25 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 79 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 64/6 | 2026-05-29 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 75 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 61/2 | 2026-05-30 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 74 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 74/9 | 2026-05-30 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 74 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 64/1 | 2026-06-01 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 72 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 54/1 | 2026-06-07 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 66 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 74/8 | 2026-06-07 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 66 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 55/1 | 2026-06-09 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 64 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-F |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-F
TA 513 | 5xx | Government | ta513 | 62/1 | 2026-06-09 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 64 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 61/0 | 2026-06-14 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 59 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 74/7 | 2026-06-14 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 59 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 51/1 | 2026-06-17 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 56 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 61/1 | 2026-06-18 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 55 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 51/0 | 2026-06-25 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 48 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 54/2 | 2026-06-27 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 46 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 44/2 | 2026-07-08 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 35 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 46/1 | 2026-07-10 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 33 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 36/5 | 2026-07-16 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 27 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 43/0 | 2026-07-17 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 26 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 45/2 | 2026-07-20 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 23 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 45/1 | 2026-08-01 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 11 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 42/1 | 2026-08-07 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 5 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 12/4 | 2026-08-09 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 3 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 513 | 5xx | Government | ta513 | 45/0 | 2026-08-11 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 1 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | S-P |  | TA 513 - DPR - 2026-08-11.xlsx | FDN S-P
TA 601 | 6xx | Government | ta601 | 81/2 | 2025-08-07 | 2025-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 370 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 82/1 | 2025-08-22 | 2025-08 | 2026-01-11 | 2026-01 | 142 | 142 | Yes | No | exact | Observed matched delay | 355 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 81/1 | 2025-09-13 | 2025-09 | 2026-02-10 | 2026-02 | 150 | 150 | Yes | No | exact | Observed matched delay | 333 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 80/5 | 2025-09-18 | 2025-09 | 2026-01-15 | 2026-01 | 119 | 119 | Yes | No | exact | Observed matched delay | 328 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 80/1 | 2025-10-10 | 2025-10 | 2026-01-19 | 2026-01 | 101 | 101 | Yes | No | exact | Observed matched delay | 306 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 59/5 | 2025-10-19 | 2025-10 | 2026-01-22 | 2026-01 | 95 | 95 | Yes | No | exact | Observed matched delay | 297 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 84/3 | 2025-10-19 | 2025-10 | 2026-01-16 | 2026-01 | 89 | 89 | Yes | No | exact | Observed matched delay | 297 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 59/4 | 2025-10-21 | 2025-10 | 2026-01-15 | 2026-01 | 86 | 86 | Yes | No | exact | Observed matched delay | 295 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 84/4 | 2025-10-24 | 2025-10 | 2026-01-19 | 2026-01 | 87 | 87 | Yes | No | exact | Observed matched delay | 292 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 60/2 | 2025-10-25 | 2025-10 | 2026-01-27 | 2026-01 | 94 | 94 | Yes | No | exact | Observed matched delay | 291 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 80/4 | 2025-10-27 | 2025-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 289 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 77/4 | 2025-10-31 | 2025-10 | 2026-01-07 | 2026-01 | 68 | 68 | Yes | No | exact | Observed matched delay | 285 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 77/10 | 2025-11-05 | 2025-11 | 2026-01-26 | 2026-01 | 82 | 82 | Yes | No | exact | Observed matched delay | 280 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 59/2 | 2025-11-08 | 2025-11 | 2025-12-22 | 2025-12 | 44 | 44 | Yes | No | exact | Observed matched delay | 277 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 77/7 | 2025-11-09 | 2025-11 | 2026-01-17 | 2026-01 | 69 | 69 | Yes | No | exact | Observed matched delay | 276 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 77/8 | 2025-11-13 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 272 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 60/3 | 2025-11-15 | 2025-11 | 2026-06-03 | 2026-06 | 200 | 200 | Yes | No | exact | Observed matched delay | 270 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 77/3 | 2025-11-19 | 2025-11 | 2025-12-22 | 2025-12 | 33 | 33 | Yes | No | exact | Observed matched delay | 266 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 60/8 | 2025-11-23 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 262 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 77/1 | 2025-11-25 | 2025-11 | 2026-01-01 | 2026-01 | 37 | 37 | Yes | No | exact | Observed matched delay | 260 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 59/1 | 2025-11-29 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 256 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 77/2 | 2025-11-30 | 2025-11 | 2025-12-25 | 2025-12 | 25 | 25 | Yes | No | exact | Observed matched delay | 255 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 58/2 | 2025-12-03 | 2025-12 | 2025-12-25 | 2025-12 | 22 | 22 | Yes | No | exact | Observed matched delay | 252 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 58/1 | 2025-12-08 | 2025-12 | 2026-01-02 | 2026-01 | 25 | 25 | Yes | No | exact | Observed matched delay | 247 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 77/6 | 2025-12-12 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 243 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 58/3 | 2025-12-14 | 2025-12 | 2026-01-09 | 2026-01 | 26 | 26 | Yes | No | exact | Observed matched delay | 241 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/7 | 2025-12-15 | 2025-12 | 2026-01-12 | 2026-01 | 28 | 28 | Yes | No | exact | Observed matched delay | 240 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 73/1 | 2025-12-18 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 237 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 56/3 | 2025-12-19 | 2025-12 | 2026-02-25 | 2026-02 | 68 | 68 | Yes | No | exact | Observed matched delay | 236 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/6 | 2025-12-20 | 2025-12 | 2026-12-05 | 2026-12 | 350 | 350 | Yes | No | exact | Observed matched delay | 235 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/9 | 2025-12-23 | 2025-12 | 2026-01-31 | 2026-01 | 39 | 39 | Yes | No | exact | Observed matched delay | 232 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 56/1 | 2025-12-24 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 231 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 73/2 | 2025-12-24 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 231 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 79/1 | 2025-12-25 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 230 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 99/8 | 2025-12-26 | 2025-12 | 2026-01-30 | 2026-01 | 35 | 35 | Yes | No | exact | Observed matched delay | 229 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 56/2 | 2025-12-27 | 2025-12 | 2026-02-20 | 2026-02 | 55 | 55 | Yes | No | exact | Observed matched delay | 228 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/10 | 2025-12-29 | 2025-12 | 2026-01-23 | 2026-01 | 25 | 25 | Yes | No | exact | Observed matched delay | 226 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 79/3 | 2025-12-30 | 2025-12 | 2026-02-01 | 2026-02 | 33 | 33 | Yes | No | exact | Observed matched delay | 225 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 55/3 | 2025-12-31 | 2025-12 | 2026-03-11 | 2026-03 | 70 | 70 | Yes | No | exact | Observed matched delay | 224 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 84/6 | 2025-12-31 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 224 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 94/1 | 2025-12-31 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 224 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 99/11 | 2025-12-31 | 2025-12 | 2026-01-17 | 2026-01 | 17 | 17 | Yes | No | exact | Observed matched delay | 224 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 79/2 | 2026-01-05 | 2026-01 | 2026-01-27 | 2026-01 | 22 | 22 | Yes | No | exact | Observed matched delay | 219 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 56/4 | 2026-01-06 | 2026-01 | 2026-03-18 | 2026-03 | 71 | 71 | Yes | No | exact | Observed matched delay | 218 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/12 | 2026-01-06 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 218 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 84/5 | 2026-01-08 | 2026-01 | 2026-01-28 | 2026-01 | 20 | 20 | Yes | No | exact | Observed matched delay | 216 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 56/9 | 2026-01-10 | 2026-01 | 2026-02-10 | 2026-02 | 31 | 31 | Yes | No | exact | Observed matched delay | 214 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/2 | 2026-01-12 | 2026-01 | 2026-01-27 | 2026-01 | 15 | 15 | Yes | No | exact | Observed matched delay | 212 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 84/1 | 2026-01-12 | 2026-01 | 2026-01-25 | 2026-01 | 13 | 13 | Yes | No | exact | Observed matched delay | 212 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/3 | 2026-01-14 | 2026-01 | 2026-07-28 | 2026-07 | 195 | 195 | Yes | No | exact | Observed matched delay | 210 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 83/0 | 2026-01-14 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 210 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 56/7 | 2026-01-16 | 2026-01 | 2025-12-15 | 2025-12 | -32 |  | Yes | Yes | exact | Negative delay excluded | 208 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 56/6 | 2026-01-17 | 2026-01 | 2026-02-03 | 2026-02 | 17 | 17 | Yes | No | exact | Observed matched delay | 207 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 56/8 | 2026-01-21 | 2026-01 | 2026-02-06 | 2026-02 | 16 | 16 | Yes | No | exact | Observed matched delay | 203 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 101/2 | 2026-01-22 | 2026-01 | 2026-02-05 | 2026-02 | 14 | 14 | Yes | No | exact | Observed matched delay | 202 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 85/2 | 2026-01-22 | 2026-01 | 2026-01-31 | 2026-01 | 9 | 9 | Yes | No | exact | Observed matched delay | 202 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/1 | 2026-01-23 | 2026-01 | 2026-01-30 | 2026-01 | 7 | 7 | Yes | No | exact | Observed matched delay | 201 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/4 | 2026-01-24 | 2026-01 | 2026-03-20 | 2026-03 | 55 | 55 | Yes | No | exact | Observed matched delay | 200 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 102/4 | 2026-01-26 | 2026-01 | 2026-02-14 | 2026-02 | 19 | 19 | Yes | No | exact | Observed matched delay | 198 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 59/0 | 2026-01-26 | 2026-01 | 2026-05-19 | 2026-05 | 113 | 113 | Yes | No | exact | Observed matched delay | 198 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 84/0 | 2026-01-26 | 2026-01 | 2026-02-05 | 2026-02 | 10 | 10 | Yes | No | exact | Observed matched delay | 198 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/5 | 2026-01-27 | 2026-01 | 2026-02-08 | 2026-02 | 12 | 12 | Yes | No | exact | Observed matched delay | 197 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 101/1 | 2026-01-28 | 2026-01 | 2026-02-16 | 2026-02 | 19 | 19 | Yes | No | exact | Observed matched delay | 196 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 55/1 | 2026-01-28 | 2026-01 | 2026-02-14 | 2026-02 | 17 | 17 | Yes | No | exact | Observed matched delay | 196 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 53/2 | 2026-01-30 | 2026-01 | 2026-02-25 | 2026-02 | 26 | 26 | Yes | No | exact | Observed matched delay | 194 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 101/0 | 2026-01-31 | 2026-01 | 2026-02-20 | 2026-02 | 20 | 20 | Yes | No | exact | Observed matched delay | 193 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 101/3 | 2026-01-31 | 2026-01 | 2026-02-12 | 2026-02 | 12 | 12 | Yes | No | exact | Observed matched delay | 193 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 102/5 | 2026-01-31 | 2026-01 | 2026-02-15 | 2026-02 | 15 | 15 | Yes | No | exact | Observed matched delay | 193 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 52/0 | 2026-01-31 | 2026-01 | 2026-02-17 | 2026-02 | 17 | 17 | Yes | No | exact | Observed matched delay | 193 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/9 | 2026-02-05 | 2026-02 | 2026-02-28 | 2026-02 | 23 | 23 | Yes | No | exact | Observed matched delay | 188 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 78/3 | 2026-02-06 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 187 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 102/3 | 2026-02-08 | 2026-02 | 2026-02-22 | 2026-02 | 14 | 14 | Yes | No | exact | Observed matched delay | 185 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 53/1 | 2026-02-08 | 2026-02 | 2026-02-22 | 2026-02 | 14 | 14 | Yes | No | exact | Observed matched delay | 185 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 77/9 | 2026-02-10 | 2026-02 | 2026-02-24 | 2026-02 | 14 | 14 | Yes | No | exact | Observed matched delay | 183 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 102/2 | 2026-02-11 | 2026-02 | 2026-02-20 | 2026-02 | 9 | 9 | Yes | No | exact | Observed matched delay | 182 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 50/1 | 2026-02-12 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 181 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 101/5 | 2026-02-14 | 2026-02 | 2026-02-27 | 2026-02 | 13 | 13 | Yes | No | exact | Observed matched delay | 179 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 102/1 | 2026-02-14 | 2026-02 | 2026-02-24 | 2026-02 | 10 | 10 | Yes | No | exact | Observed matched delay | 179 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 83/1 | 2026-02-15 | 2026-02 | 2026-02-24 | 2026-02 | 9 | 9 | Yes | No | exact | Observed matched delay | 178 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 50/2 | 2026-02-17 | 2026-02 | 2026-06-20 | 2026-06 | 123 | 123 | Yes | No | exact | Observed matched delay | 176 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 101/6 | 2026-02-22 | 2026-02 | 2026-03-13 | 2026-03 | 19 | 19 | Yes | No | exact | Observed matched delay | 171 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/6 | 2026-02-24 | 2026-02 | 2026-03-10 | 2026-03 | 14 | 14 | Yes | No | exact | Observed matched delay | 169 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 85/1 | 2026-02-25 | 2026-02 | 2026-03-08 | 2026-03 | 11 | 11 | Yes | No | exact | Observed matched delay | 168 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/8 | 2026-02-26 | 2026-02 | 2026-03-30 | 2026-03 | 32 | 32 | Yes | No | exact | Observed matched delay | 167 | TRUE | FALSE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/7 | 2026-02-28 | 2026-02 | 2026-03-16 | 2026-03 | 16 | 16 | Yes | No | exact | Observed matched delay | 165 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 101/7 | 2026-02-28 | 2026-02 | 2026-03-16 | 2026-03 | 16 | 16 | Yes | No | exact | Observed matched delay | 165 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 89/1 | 2026-03-03 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 162 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 53/4 | 2026-03-06 | 2026-03 | 2026-03-26 | 2026-03 | 20 | 20 | Yes | No | exact | Observed matched delay | 159 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 53/5 | 2026-03-08 | 2026-03 | 2026-04-02 | 2026-04 | 25 | 25 | Yes | No | exact | Observed matched delay | 157 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 49/10 | 2026-03-11 | 2026-03 | 2026-06-08 | 2026-06 | 89 | 89 | Yes | No | exact | Observed matched delay | 154 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/7 | 2026-03-13 | 2026-03 | 2026-07-07 | 2026-07 | 116 | 116 | Yes | No | exact | Observed matched delay | 152 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 49/11 | 2026-03-14 | 2026-03 | 2026-06-13 | 2026-06 | 91 | 91 | Yes | No | exact | Observed matched delay | 151 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/8 | 2026-03-14 | 2026-03 | 2026-06-16 | 2026-06 | 94 | 94 | Yes | No | exact | Observed matched delay | 151 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/10 | 2026-03-17 | 2026-03 | 2026-06-09 | 2026-06 | 84 | 84 | Yes | No | exact | Observed matched delay | 148 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 100/0 | 2026-03-18 | 2026-03 | 2026-04-05 | 2026-04 | 18 | 18 | Yes | No | exact | Observed matched delay | 147 | TRUE | TRUE | TRUE | TRUE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 90/0 | 2026-03-18 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 147 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 51/6 | 2026-03-19 | 2026-03 | 2026-07-01 | 2026-07 | 104 | 104 | Yes | No | exact | Observed matched delay | 146 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 52/1 | 2026-03-22 | 2026-03 | 2026-06-24 | 2026-06 | 94 | 94 | Yes | No | exact | Observed matched delay | 143 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 50/3 | 2026-03-25 | 2026-03 | 2026-06-19 | 2026-06 | 86 | 86 | Yes | No | exact | Observed matched delay | 140 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/2 | 2026-03-27 | 2026-03 | 2026-07-15 | 2026-07 | 110 | 110 | Yes | No | exact | Observed matched delay | 138 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 53/3 | 2026-03-31 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 134 | TRUE | FALSE | TRUE | FALSE |  |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 60/0 | 2026-04-06 | 2026-04 | 2026-05-05 | 2026-05 | 29 | 29 | Yes | No | exact | Observed matched delay | 128 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 70/1 | 2026-04-11 | 2026-04 | 2026-06-15 | 2026-06 | 65 | 65 | Yes | No | exact | Observed matched delay | 123 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 53/0 | 2026-04-13 | 2026-04 | 2026-07-12 | 2026-07 | 90 | 90 | Yes | No | exact | Observed matched delay | 121 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 70/2 | 2026-04-13 | 2026-04 | 2026-06-29 | 2026-06 | 77 | 77 | Yes | No | exact | Observed matched delay | 121 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 50/0 | 2026-04-16 | 2026-04 | 2025-06-26 | 2025-06 | -294 |  | Yes | Yes | exact | Negative delay excluded | 118 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 70/4 | 2026-04-16 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 118 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 70/3 | 2026-04-18 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 116 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 66/1 | 2026-04-21 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 113 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 49/9 | 2026-04-23 | 2026-04 | 2026-07-20 | 2026-07 | 88 | 88 | Yes | No | exact | Observed matched delay | 111 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 67/0 | 2026-04-26 | 2026-04 | 2026-06-29 | 2026-06 | 64 | 64 | Yes | No | exact | Observed matched delay | 108 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 65/3 | 2026-04-29 | 2026-04 | 2026-06-19 | 2026-06 | 51 | 51 | Yes | No | exact | Observed matched delay | 105 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 49/8 | 2026-04-30 | 2026-04 | 2026-06-06 | 2026-06 | 37 | 37 | Yes | No | exact | Observed matched delay | 104 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 66/0 | 2026-05-03 | 2026-05 | 2026-06-24 | 2026-06 | 52 | 52 | Yes | No | exact | Observed matched delay | 101 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 67/1 | 2026-05-05 | 2026-05 | 2026-06-10 | 2026-06 | 36 | 36 | Yes | No | exact | Observed matched delay | 99 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 48/7 | 2026-05-10 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 94 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 69/0 | 2026-05-13 | 2026-05 | 2026-06-27 | 2026-06 | 45 | 45 | Yes | No | exact | Observed matched delay | 91 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 69/2 | 2026-05-16 | 2026-05 | 2026-06-15 | 2026-06 | 30 | 30 | Yes | No | exact | Observed matched delay | 88 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 48/3 | 2026-05-19 | 2026-05 | 2026-06-26 | 2026-06 | 38 | 38 | Yes | No | exact | Observed matched delay | 85 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 69/1 | 2026-05-20 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 84 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 68/2 | 2026-05-23 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 81 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 48/2 | 2026-05-24 | 2026-05 | 2026-07-04 | 2026-07 | 41 | 41 | Yes | No | exact | Observed matched delay | 80 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 68/0 | 2026-05-30 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 74 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 56/5 | 2026-05-31 | 2026-05 | 2026-06-14 | 2026-06 | 14 | 14 | Yes | No | exact | Observed matched delay | 73 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 72/1 | 2026-06-01 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 72 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 73/0 | 2026-06-05 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 68 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 56/10 | 2026-06-07 | 2026-06 | 2026-06-21 | 2026-06 | 14 | 14 | Yes | No | exact | Observed matched delay | 66 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 75/2 | 2026-06-07 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 66 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 75/3 | 2026-06-09 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 64 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 56/12 | 2026-06-12 | 2026-06 | 2026-06-29 | 2026-06 | 17 | 17 | Yes | No | exact | Observed matched delay | 61 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 75/1 | 2026-06-12 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 61 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 77/5 | 2026-06-15 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 58 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 49/0 | 2026-06-17 | 2026-06 | 2026-07-29 | 2026-07 | 42 | 42 | Yes | No | exact | Observed matched delay | 56 | TRUE | FALSE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 60/4 | 2026-06-19 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 54 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 49/1 | 2026-06-20 | 2026-06 | 2026-07-07 | 2026-07 | 17 | 17 | Yes | No | exact | Observed matched delay | 53 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/1 | 2026-06-20 | 2026-06 | 2026-07-09 | 2026-07 | 19 | 19 | Yes | No | exact | Observed matched delay | 53 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 48/0 | 2026-06-22 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 51 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 99/3 | 2026-06-22 | 2026-06 | 2026-07-07 | 2026-07 | 15 | 15 | Yes | No | exact | Observed matched delay | 51 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/4 | 2026-06-23 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 50 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 56/11 | 2026-06-23 | 2026-06 | 2026-07-06 | 2026-07 | 13 | 13 | Yes | No | exact | Observed matched delay | 50 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/4 | 2026-06-24 | 2026-06 | 2026-07-17 | 2026-07 | 23 | 23 | Yes | No | exact | Observed matched delay | 49 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 102/0 | 2026-06-25 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 48 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 51/5 | 2026-06-26 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 47 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 99/2 | 2026-06-26 | 2026-06 | 2026-07-13 | 2026-07 | 17 | 17 | Yes | No | exact | Observed matched delay | 47 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/1 | 2026-06-27 | 2026-06 | 2026-07-13 | 2026-07 | 16 | 16 | Yes | No | exact | Observed matched delay | 46 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 49/2 | 2026-06-30 | 2026-06 | 2026-07-14 | 2026-07 | 14 | 14 | Yes | No | exact | Observed matched delay | 43 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 56/0 | 2026-06-30 | 2026-06 | 2026-07-12 | 2026-07 | 12 | 12 | Yes | No | exact | Observed matched delay | 43 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/0 | 2026-06-30 | 2026-06 | 2026-07-09 | 2026-07 | 9 | 9 | Yes | No | exact | Observed matched delay | 43 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/0 | 2026-07-03 | 2026-07 | 2026-07-20 | 2026-07 | 17 | 17 | Yes | No | exact | Observed matched delay | 40 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 99/5 | 2026-07-03 | 2026-07 | 2026-07-21 | 2026-07 | 18 | 18 | Yes | No | exact | Observed matched delay | 40 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 98/4 | 2026-07-04 | 2026-07 | 2026-07-10 | 2026-07 | 6 | 6 | Yes | No | exact | Observed matched delay | 39 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 52/2 | 2026-07-05 | 2026-07 | 2026-07-20 | 2026-07 | 15 | 15 | Yes | No | exact | Observed matched delay | 38 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 98/3 | 2026-07-06 | 2026-07 | 2026-07-22 | 2026-07 | 16 | 16 | Yes | No | exact | Observed matched delay | 37 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 72/0 | 2026-07-07 | 2026-07 | 2026-07-26 | 2026-07 | 19 | 19 | Yes | No | exact | Observed matched delay | 36 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 51/3 | 2026-07-08 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 35 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 98/2 | 2026-07-08 | 2026-07 | 2026-07-17 | 2026-07 | 9 | 9 | Yes | No | exact | Observed matched delay | 35 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 52/3 | 2026-07-10 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 33 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 57/0 | 2026-07-10 | 2026-07 | 2026-07-22 | 2026-07 | 12 | 12 | Yes | No | exact | Observed matched delay | 33 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 71/0 | 2026-07-10 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 33 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 98/5 | 2026-07-10 | 2026-07 | 2026-07-24 | 2026-07 | 14 | 14 | Yes | No | exact | Observed matched delay | 33 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 98/1 | 2026-07-12 | 2026-07 | 2026-07-28 | 2026-07 | 16 | 16 | Yes | No | exact | Observed matched delay | 31 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 63/2 | 2026-07-13 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 30 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 58/0 | 2026-07-15 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 28 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 98/0 | 2026-07-15 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 28 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 76/0 | 2026-07-16 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 27 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 101/4 | 2026-07-17 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 26 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 49/3 | 2026-07-17 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 26 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 65/2 | 2026-07-18 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 25 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 54/0 | 2026-07-21 | 2026-07 | 2026-07-28 | 2026-07 | 7 | 7 | Yes | No | exact | Observed matched delay | 22 | FALSE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 78/1 | 2026-07-21 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 22 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 53/6 | 2026-07-23 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 20 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 101/9 | 2026-07-24 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 19 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 49/4 | 2026-07-26 | 2026-07 | 2026-07-30 | 2026-07 | 4 | 4 | Yes | No | exact | Observed matched delay | 17 | FALSE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 78/0 | 2026-07-26 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 17 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 97/1 | 2026-07-26 | 2026-07 | 2026-08-06 | 2026-08 | 11 | 11 | Yes | No | exact | Observed matched delay | 17 | FALSE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet | TA 601 - DPR - 2026-08-11.xlsx | Erection Compiled
TA 601 | 6xx | Government | ta601 | 52/4 | 2026-07-27 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 16 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 63/1 | 2026-07-27 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 16 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 96/8 | 2026-07-27 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 16 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 80/2 | 2026-07-28 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 15 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 96/7 | 2026-07-30 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 13 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 97/4 | 2026-08-01 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 11 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 82/2 | 2026-08-03 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 9 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 97/3 | 2026-08-03 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 9 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 96/4 | 2026-08-06 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 6 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 101/8 | 2026-08-08 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 4 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 63/3 | 2026-08-09 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 3 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 96/5 | 2026-08-09 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 3 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TA 601 | 6xx | Government | ta601 | 96/6 | 2026-08-11 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 1 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TA 601 - DPR - 2026-08-11.xlsx | Progress Sheet
TB 408 | 4xx | Private | tb408 | 0 | 2023-10-01 | 2023-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 1046 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 408 | 4xx | Private | tb408 | 1 | 2024-09-01 | 2024-09 |  |  |  |  | No | No |  | Unmatched/right-censored | 710 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 408 | 4xx | Private | tb408 | 2 | 2024-11-01 | 2024-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 649 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 408 | 4xx | Private | tb408 | 3 | 2024-11-01 | 2024-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 649 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 408 | 4xx | Private | tb408 | 4 | 2024-11-01 | 2024-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 649 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 408 | 4xx | Private | tb408 | 5 | 2024-12-01 | 2024-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 619 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 408 - DPR - 2026-07-30.xlsx | Foundation
TB 501 | 5xx | Private | tb501 | 20/7 | 2024-08-12 | 2024-08 | 2025-02-19 | 2025-02 | 191 | 191 | Yes | No | exact | Observed matched delay | 730 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 20/5 | 2024-08-16 | 2024-08 | 2025-02-17 | 2025-02 | 185 | 185 | Yes | No | exact | Observed matched delay | 726 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/3 | 2024-08-19 | 2024-08 | 2025-01-05 | 2025-01 | 139 | 139 | Yes | No | exact | Observed matched delay | 723 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 10/3 | 2024-09-09 | 2024-09 | 2025-03-11 | 2025-03 | 183 | 183 | Yes | No | exact | Observed matched delay | 702 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/2 | 2024-09-11 | 2024-09 | 2024-12-24 | 2024-12 | 104 | 104 | Yes | No | exact | Observed matched delay | 700 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/3 | 2024-09-15 | 2024-09 | 2024-12-25 | 2024-12 | 101 | 101 | Yes | No | exact | Observed matched delay | 696 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/6 | 2024-09-19 | 2024-09 | 2025-02-13 | 2025-02 | 147 | 147 | Yes | No | exact | Observed matched delay | 692 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/1 | 2024-09-22 | 2024-09 | 2024-12-19 | 2024-12 | 88 | 88 | Yes | No | exact | Observed matched delay | 689 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/7 | 2024-09-23 | 2024-09 | 2025-02-14 | 2025-02 | 144 | 144 | Yes | No | exact | Observed matched delay | 688 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/8 | 2024-09-28 | 2024-09 | 2025-03-13 | 2025-03 | 166 | 166 | Yes | No | exact | Observed matched delay | 683 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 16/1 | 2024-10-01 | 2024-10 | 2025-02-14 | 2025-02 | 136 | 136 | Yes | No | exact | Observed matched delay | 680 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 19/2 | 2024-10-04 | 2024-10 | 2025-01-20 | 2025-01 | 108 | 108 | Yes | No | exact | Observed matched delay | 677 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 17/3 | 2024-10-06 | 2024-10 | 2025-01-29 | 2025-01 | 115 | 115 | Yes | No | exact | Observed matched delay | 675 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 22/2 | 2024-10-09 | 2024-10 | 2025-02-25 | 2025-02 | 139 | 139 | Yes | No | exact | Observed matched delay | 672 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-16 | 2024-10-10 | 2024-10 | 2025-02-14 | 2025-02 | 127 | 127 | Yes | No | exact | Observed matched delay | 671 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 17/2 | 2024-10-11 | 2024-10 | 2025-02-01 | 2025-02 | 113 | 113 | Yes | No | exact | Observed matched delay | 670 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 16/3 | 2024-10-16 | 2024-10 | 2025-02-18 | 2025-02 | 125 | 125 | Yes | No | exact | Observed matched delay | 665 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/5 | 2024-10-18 | 2024-10 | 2025-01-03 | 2025-01 | 77 | 77 | Yes | No | exact | Observed matched delay | 663 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-12 | 2024-10-19 | 2024-10 | 2025-03-20 | 2025-03 | 152 | 152 | Yes | No | exact | Observed matched delay | 662 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-11 | 2024-10-20 | 2024-10 | 2025-04-30 | 2025-04 | 192 | 192 | Yes | No | exact | Observed matched delay | 661 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-19 | 2024-10-20 | 2024-10 | 2025-01-16 | 2025-01 | 88 | 88 | Yes | No | exact | Observed matched delay | 661 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/12 | 2024-10-21 | 2024-10 | 2025-03-03 | 2025-03 | 133 | 133 | Yes | No | exact | Observed matched delay | 660 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-18 | 2024-10-21 | 2024-10 | 2025-02-21 | 2025-02 | 123 | 123 | Yes | No | exact | Observed matched delay | 660 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 10/4 | 2024-10-22 | 2024-10 | 2025-04-23 | 2025-04 | 183 | 183 | Yes | No | exact | Observed matched delay | 659 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 20/6 | 2024-10-22 | 2024-10 | 2025-03-05 | 2025-03 | 134 | 134 | Yes | No | exact | Observed matched delay | 659 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/4 | 2024-10-24 | 2024-10 | 2025-02-05 | 2025-02 | 104 | 104 | Yes | No | exact | Observed matched delay | 657 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 17/1 | 2024-10-24 | 2024-10 | 2025-02-18 | 2025-02 | 117 | 117 | Yes | No | exact | Observed matched delay | 657 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/11 | 2024-10-24 | 2024-10 | 2025-01-28 | 2025-01 | 96 | 96 | Yes | No | exact | Observed matched delay | 657 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 20/3 | 2024-10-26 | 2024-10 | 2025-02-28 | 2025-02 | 125 | 125 | Yes | No | exact | Observed matched delay | 655 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/3 | 2024-10-26 | 2024-10 | 2025-02-18 | 2025-02 | 115 | 115 | Yes | No | exact | Observed matched delay | 655 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 11/1 | 2024-10-27 | 2024-10 | 2025-03-13 | 2025-03 | 137 | 137 | Yes | No | exact | Observed matched delay | 654 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 16/2 | 2024-10-27 | 2024-10 | 2025-02-22 | 2025-02 | 118 | 118 | Yes | No | exact | Observed matched delay | 654 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 20/4 | 2024-10-30 | 2024-10 | 2025-03-02 | 2025-03 | 123 | 123 | Yes | No | exact | Observed matched delay | 651 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/9 | 2024-10-30 | 2024-10 | 2025-05-19 | 2025-05 | 201 | 201 | Yes | No | exact | Observed matched delay | 651 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-17 | 2024-10-31 | 2024-10 | 2025-02-07 | 2025-02 | 99 | 99 | Yes | No | exact | Observed matched delay | 650 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/7 | 2024-11-03 | 2024-11 | 2025-02-09 | 2025-02 | 98 | 98 | Yes | No | exact | Observed matched delay | 647 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/4 | 2024-11-04 | 2024-11 | 2025-01-02 | 2025-01 | 59 | 59 | Yes | No | exact | Observed matched delay | 646 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 20/2 | 2024-11-05 | 2024-11 | 2025-02-23 | 2025-02 | 110 | 110 | Yes | No | exact | Observed matched delay | 645 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/6 | 2024-11-06 | 2024-11 | 2025-02-11 | 2025-02 | 97 | 97 | Yes | No | exact | Observed matched delay | 644 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 20/1 | 2024-11-08 | 2024-11 | 2025-02-21 | 2025-02 | 105 | 105 | Yes | No | exact | Observed matched delay | 642 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-14 | 2024-11-08 | 2024-11 | 2025-05-08 | 2025-05 | 181 | 181 | Yes | No | exact | Observed matched delay | 642 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/8 | 2024-11-09 | 2024-11 | 2025-02-11 | 2025-02 | 94 | 94 | Yes | No | exact | Observed matched delay | 641 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-21 | 2024-11-09 | 2024-11 | 2025-03-06 | 2025-03 | 117 | 117 | Yes | No | exact | Observed matched delay | 641 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/9 | 2024-11-12 | 2024-11 | 2025-02-16 | 2025-02 | 96 | 96 | Yes | No | exact | Observed matched delay | 638 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-20 | 2024-11-12 | 2024-11 | 2025-02-26 | 2025-02 | 106 | 106 | Yes | No | exact | Observed matched delay | 638 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/6 | 2024-11-14 | 2024-11 | 2025-01-07 | 2025-01 | 54 | 54 | Yes | No | exact | Observed matched delay | 636 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 10/2 | 2024-11-15 | 2024-11 | 2025-03-17 | 2025-03 | 122 | 122 | Yes | No | exact | Observed matched delay | 635 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/5 | 2024-11-15 | 2024-11 | 2025-02-10 | 2025-02 | 87 | 87 | Yes | No | exact | Observed matched delay | 635 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/4 | 2024-11-17 | 2024-11 | 2025-02-07 | 2025-02 | 82 | 82 | Yes | No | exact | Observed matched delay | 633 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 19/3 | 2024-11-18 | 2024-11 | 2025-01-22 | 2025-01 | 65 | 65 | Yes | No | exact | Observed matched delay | 632 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/10 | 2024-11-19 | 2024-11 | 2025-02-23 | 2025-02 | 96 | 96 | Yes | No | exact | Observed matched delay | 631 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/8 | 2024-11-19 | 2024-11 | 2025-02-19 | 2025-02 | 92 | 92 | Yes | No | exact | Observed matched delay | 631 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/7 | 2024-11-20 | 2024-11 | 2025-01-14 | 2025-01 | 55 | 55 | Yes | No | exact | Observed matched delay | 630 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 19/5 | 2024-11-21 | 2024-11 | 2025-05-09 | 2025-05 | 169 | 169 | Yes | No | exact | Observed matched delay | 629 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 19/4 | 2024-11-24 | 2024-11 | 2025-01-24 | 2025-01 | 61 | 61 | Yes | No | exact | Observed matched delay | 626 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/9 | 2024-11-26 | 2024-11 | 2025-01-11 | 2025-01 | 46 | 46 | Yes | No | exact | Observed matched delay | 624 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 19/1 | 2024-11-26 | 2024-11 | 2025-01-18 | 2025-01 | 53 | 53 | Yes | No | exact | Observed matched delay | 624 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-10 | 2024-11-26 | 2024-11 | 2025-03-27 | 2025-03 | 121 | 121 | Yes | No | exact | Observed matched delay | 624 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/1 | 2024-11-29 | 2024-11 | 2024-12-30 | 2024-12 | 31 | 31 | Yes | No | exact | Observed matched delay | 621 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/10 | 2024-11-30 | 2024-11 | 2025-01-12 | 2025-01 | 43 | 43 | Yes | No | exact | Observed matched delay | 620 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/8 | 2024-11-30 | 2024-11 | 2025-01-09 | 2025-01 | 40 | 40 | Yes | No | exact | Observed matched delay | 620 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/9 | 2024-12-04 | 2024-12 | 2025-02-21 | 2025-02 | 79 | 79 | Yes | No | exact | Observed matched delay | 616 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 5/2 | 2024-12-06 | 2024-12 | 2025-03-26 | 2025-03 | 110 | 110 | Yes | No | exact | Observed matched delay | 614 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 5/3 | 2024-12-07 | 2024-12 | 2025-03-29 | 2025-03 | 112 | 112 | Yes | No | exact | Observed matched delay | 613 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/2 | 2024-12-08 | 2024-12 | 2024-12-27 | 2024-12 | 19 | 19 | Yes | No | exact | Observed matched delay | 612 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 15/5 | 2024-12-09 | 2024-12 | 2025-02-07 | 2025-02 | 60 | 60 | Yes | No | exact | Observed matched delay | 611 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8B/0 | 2024-12-11 | 2024-12 | 2025-04-20 | 2025-04 | 130 | 130 | Yes | No | exact | Observed matched delay | 609 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-22 | 2024-12-11 | 2024-12 | 2025-02-26 | 2025-02 | 77 | 77 | Yes | No | exact | Observed matched delay | 609 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 23/4 | 2024-12-15 | 2024-12 | 2025-03-02 | 2025-03 | 77 | 77 | Yes | No | exact | Observed matched delay | 605 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-15 | 2024-12-15 | 2024-12 | 2025-02-04 | 2025-02 | 51 | 51 | Yes | No | exact | Observed matched delay | 605 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 14/9 | 2024-12-19 | 2024-12 | 2025-02-01 | 2025-02 | 44 | 44 | Yes | No | exact | Observed matched delay | 601 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 22/1 | 2024-12-19 | 2024-12 | 2025-02-27 | 2025-02 | 70 | 70 | Yes | No | exact | Observed matched delay | 601 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/14 | 2024-12-19 | 2024-12 | 2025-03-16 | 2025-03 | 87 | 87 | Yes | No | exact | Observed matched delay | 601 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8B/1 | 2024-12-19 | 2024-12 | 2025-04-02 | 2025-04 | 104 | 104 | Yes | No | exact | Observed matched delay | 601 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 29A/2 | 2024-12-20 | 2024-12 | 2025-02-19 | 2025-02 | 61 | 61 | Yes | No | exact | Observed matched delay | 600 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/13 | 2024-12-20 | 2024-12 | 2025-03-13 | 2025-03 | 83 | 83 | Yes | No | exact | Observed matched delay | 600 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 23/2 | 2024-12-23 | 2024-12 | 2025-03-01 | 2025-03 | 68 | 68 | Yes | No | exact | Observed matched delay | 597 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 14/7 | 2024-12-25 | 2024-12 | 2025-01-29 | 2025-01 | 35 | 35 | Yes | No | exact | Observed matched delay | 595 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 29A/3 | 2024-12-25 | 2024-12 | 2025-02-21 | 2025-02 | 58 | 58 | Yes | No | exact | Observed matched delay | 595 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/15 | 2024-12-25 | 2024-12 | 2025-03-23 | 2025-03 | 88 | 88 | Yes | No | exact | Observed matched delay | 595 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 29A/1 | 2024-12-26 | 2024-12 | 2025-02-18 | 2025-02 | 54 | 54 | Yes | No | exact | Observed matched delay | 594 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8B/2 | 2024-12-27 | 2024-12 | 2025-04-03 | 2025-04 | 97 | 97 | Yes | No | exact | Observed matched delay | 593 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 30/1 | 2024-12-28 | 2024-12 | 2025-02-26 | 2025-02 | 60 | 60 | Yes | No | exact | Observed matched delay | 592 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-30 | 2024-12-28 | 2024-12 | 2025-02-23 | 2025-02 | 57 | 57 | Yes | No | exact | Observed matched delay | 592 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 5A/0 | 2024-12-29 | 2024-12 | 2025-03-30 | 2025-03 | 91 | 91 | Yes | No | exact | Observed matched delay | 591 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 30/6 | 2024-12-30 | 2024-12 | 2025-03-02 | 2025-03 | 62 | 62 | Yes | No | exact | Observed matched delay | 590 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 14/8 | 2024-12-31 | 2024-12 | 2025-01-30 | 2025-01 | 30 | 30 | Yes | No | exact | Observed matched delay | 589 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 30/3 | 2024-12-31 | 2024-12 | 2025-01-30 | 2025-01 | 30 | 30 | Yes | No | exact | Observed matched delay | 589 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8A/0 | 2025-01-04 | 2025-01 | 2025-04-28 | 2025-04 | 114 | 114 | Yes | No | exact | Observed matched delay | 585 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 30/4 | 2025-01-05 | 2025-01 | 2025-03-05 | 2025-03 | 59 | 59 | Yes | No | exact | Observed matched delay | 584 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 5/1 | 2025-01-05 | 2025-01 | 2025-04-12 | 2025-04 | 97 | 97 | Yes | No | exact | Observed matched delay | 584 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 30/2 | 2025-01-06 | 2025-01 | 2025-03-02 | 2025-03 | 55 | 55 | Yes | No | exact | Observed matched delay | 583 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-31 | 2025-01-07 | 2025-01 | 2025-02-28 | 2025-02 | 52 | 52 | Yes | No | exact | Observed matched delay | 582 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/4 | 2025-01-08 | 2025-01 | 2025-03-20 | 2025-03 | 71 | 71 | Yes | No | exact | Observed matched delay | 581 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 30/5 | 2025-01-10 | 2025-01 | 2025-03-03 | 2025-03 | 52 | 52 | Yes | No | exact | Observed matched delay | 579 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/11 | 2025-01-12 | 2025-01 | 2025-03-11 | 2025-03 | 58 | 58 | Yes | No | exact | Observed matched delay | 577 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/3 | 2025-01-14 | 2025-01 | 2025-03-18 | 2025-03 | 63 | 63 | Yes | No | exact | Observed matched delay | 575 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/6 | 2025-01-14 | 2025-01 | 2025-03-09 | 2025-03 | 54 | 54 | Yes | No | exact | Observed matched delay | 575 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 31/1 | 2025-01-15 | 2025-01 | 2025-07-11 | 2025-07 | 177 | 177 | Yes | No | exact | Observed matched delay | 574 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8D/0 | 2025-01-16 | 2025-01 | 2025-04-15 | 2025-04 | 89 | 89 | Yes | No | exact | Observed matched delay | 573 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/2 | 2025-01-18 | 2025-01 | 2025-03-21 | 2025-03 | 62 | 62 | Yes | No | exact | Observed matched delay | 571 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 29A/4 | 2025-01-19 | 2025-01 | 2025-02-26 | 2025-02 | 38 | 38 | Yes | No | exact | Observed matched delay | 570 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/5 | 2025-01-19 | 2025-01 | 2025-03-23 | 2025-03 | 63 | 63 | Yes | No | exact | Observed matched delay | 570 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 32/1 | 2025-01-23 | 2025-01 | 2025-05-29 | 2025-05 | 126 | 126 | Yes | No | exact | Observed matched delay | 566 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/1 | 2025-01-24 | 2025-01 | 2025-03-26 | 2025-03 | 61 | 61 | Yes | No | exact | Observed matched delay | 565 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/2 | 2025-01-27 | 2025-01 | 2025-06-09 | 2025-06 | 133 | 133 | Yes | No | exact | Observed matched delay | 562 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-32 | 2025-01-29 | 2025-01 | 2025-07-14 | 2025-07 | 166 | 166 | Yes | No | exact | Observed matched delay | 560 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/9 | 2025-01-30 | 2025-01 | 2025-03-15 | 2025-03 | 44 | 44 | Yes | No | exact | Observed matched delay | 559 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1D/0 | 2025-01-31 | 2025-01 | 2025-03-29 | 2025-03 | 57 | 57 | Yes | No | exact | Observed matched delay | 558 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1A/2 | 2025-02-02 | 2025-02 | 2025-04-14 | 2025-04 | 71 | 71 | Yes | No | exact | Observed matched delay | 556 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 2/0 | 2025-02-02 | 2025-02 | 2025-04-19 | 2025-04 | 76 | 76 | Yes | No | exact | Observed matched delay | 556 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1A/1 | 2025-02-05 | 2025-02 | 2025-04-04 | 2025-04 | 58 | 58 | Yes | No | exact | Observed matched delay | 553 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/0 | 2025-02-05 | 2025-02 | 2025-05-28 | 2025-05 | 112 | 112 | Yes | No | exact | Observed matched delay | 553 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1/2 | 2025-02-06 | 2025-02 | 2025-03-29 | 2025-03 | 51 | 51 | Yes | No | exact | Observed matched delay | 552 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-23 | 2025-02-06 | 2025-02 | 2025-08-17 | 2025-08 | 192 | 192 | Yes | No | exact | Observed matched delay | 552 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/10 | 2025-02-08 | 2025-02 | 2025-03-11 | 2025-03 | 31 | 31 | Yes | No | exact | Observed matched delay | 550 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 0/1 | 2025-02-09 | 2025-02 | 2025-04-02 | 2025-04 | 52 | 52 | Yes | No | exact | Observed matched delay | 549 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 23/1 | 2025-02-10 | 2025-02 | 2025-03-05 | 2025-03 | 23 | 23 | Yes | No | exact | Observed matched delay | 548 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/16 | 2025-02-12 | 2025-02 | 2025-03-21 | 2025-03 | 37 | 37 | Yes | No | exact | Observed matched delay | 546 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 32/2 | 2025-02-15 | 2025-02 | 2025-05-24 | 2025-05 | 98 | 98 | Yes | No | exact | Observed matched delay | 543 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/17 | 2025-02-15 | 2025-02 | 2025-03-19 | 2025-03 | 32 | 32 | Yes | No | exact | Observed matched delay | 543 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1A/0 | 2025-02-17 | 2025-02 | 2025-04-21 | 2025-04 | 63 | 63 | Yes | No | exact | Observed matched delay | 541 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 3/0 | 2025-02-18 | 2025-02 | 2025-05-01 | 2025-05 | 72 | 72 | Yes | No | exact | Observed matched delay | 540 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/11 | 2025-02-19 | 2025-02 | 2025-05-10 | 2025-05 | 80 | 80 | Yes | No | exact | Observed matched delay | 539 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 0/0 | 2025-02-20 | 2025-02 | 2025-04-07 | 2025-04 | 46 | 46 | Yes | No | exact | Observed matched delay | 538 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1D/1 | 2025-02-22 | 2025-02 | 2025-03-27 | 2025-03 | 33 | 33 | Yes | No | exact | Observed matched delay | 536 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1/1 | 2025-02-23 | 2025-02 | 2025-03-31 | 2025-03 | 36 | 36 | Yes | No | exact | Observed matched delay | 535 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1C/1 | 2025-02-25 | 2025-02 | 2025-05-17 | 2025-05 | 81 | 81 | Yes | No | exact | Observed matched delay | 533 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 20/8 | 2025-02-25 | 2025-02 | 2025-11-10 | 2025-11 | 258 | 258 | Yes | No | exact | Observed matched delay | 533 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 23/3 | 2025-02-28 | 2025-02 | 2025-05-26 | 2025-05 | 87 | 87 | Yes | No | exact | Observed matched delay | 530 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1B/0 | 2025-03-05 | 2025-03 | 2025-04-25 | 2025-04 | 51 | 51 | Yes | No | exact | Observed matched delay | 525 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 7/1 | 2025-03-09 | 2025-03 | 2025-04-05 | 2025-04 | 27 | 27 | Yes | No | exact | Observed matched delay | 521 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 7/0 | 2025-03-16 | 2025-03 | 2025-04-08 | 2025-04 | 23 | 23 | Yes | No | exact | Observed matched delay | 514 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 7/2 | 2025-03-16 | 2025-03 | 2025-04-05 | 2025-04 | 20 | 20 | Yes | No | exact | Observed matched delay | 514 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-26 | 2025-03-16 | 2025-03 | 2025-06-04 | 2025-06 | 80 | 80 | Yes | No | exact | Observed matched delay | 514 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1E/0 | 2025-03-22 | 2025-03 | 2025-05-25 | 2025-05 | 64 | 64 | Yes | No | exact | Observed matched delay | 508 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 7/3 | 2025-03-23 | 2025-03 | 2025-04-21 | 2025-04 | 29 | 29 | Yes | No | exact | Observed matched delay | 507 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 1/0 | 2025-03-27 | 2025-03 | 2025-04-11 | 2025-04 | 15 | 15 | Yes | No | exact | Observed matched delay | 503 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 5/0 | 2025-03-28 | 2025-03 | 2025-07-14 | 2025-07 | 108 | 108 | Yes | No | exact | Observed matched delay | 502 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-27 | 2025-04-03 | 2025-04 | 2025-07-24 | 2025-07 | 112 | 112 | Yes | No | exact | Observed matched delay | 496 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-13 | 2025-04-08 | 2025-04 | 2025-05-23 | 2025-05 | 45 | 45 | Yes | No | exact | Observed matched delay | 491 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/1 | 2025-04-15 | 2025-04 | 2025-05-17 | 2025-05 | 32 | 32 | Yes | No | exact | Observed matched delay | 484 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-25 | 2025-04-17 | 2025-04 | 2025-07-24 | 2025-07 | 98 | 98 | Yes | No | exact | Observed matched delay | 482 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 10/1 | 2025-04-19 | 2025-04 | 2025-05-21 | 2025-05 | 32 | 32 | Yes | No | exact | Observed matched delay | 480 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/2 | 2025-04-21 | 2025-04 | 2025-05-14 | 2025-05 | 23 | 23 | Yes | No | exact | Observed matched delay | 478 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/5 | 2025-04-25 | 2025-04 | 2025-06-25 | 2025-06 | 61 | 61 | Yes | No | exact | Observed matched delay | 474 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/4 | 2025-04-26 | 2025-04 | 2025-06-21 | 2025-06 | 56 | 56 | Yes | No | exact | Observed matched delay | 473 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 21/13 | 2025-04-27 | 2025-04 | 2025-05-17 | 2025-05 | 20 | 20 | Yes | No | exact | Observed matched delay | 472 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-24 | 2025-04-29 | 2025-04 | 2025-06-09 | 2025-06 | 41 | 41 | Yes | No | exact | Observed matched delay | 470 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 23/5 | 2025-04-30 | 2025-04 | 2025-05-29 | 2025-05 | 29 | 29 | Yes | No | exact | Observed matched delay | 469 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 29A/0 | 2025-05-10 | 2025-05 | 2025-08-11 | 2025-08 | 93 | 93 | Yes | No | exact | Observed matched delay | 459 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8C/0 | 2025-05-12 | 2025-05 | 2025-06-04 | 2025-06 | 23 | 23 | Yes | No | exact | Observed matched delay | 457 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/12 | 2025-05-13 | 2025-05 | 2025-06-04 | 2025-06 | 22 | 22 | Yes | No | exact | Observed matched delay | 456 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-29 | 2025-05-14 | 2025-05 | 2025-06-13 | 2025-06 | 30 | 30 | Yes | No | exact | Observed matched delay | 455 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/1 | 2025-05-17 | 2025-05 | 2025-07-04 | 2025-07 | 48 | 48 | Yes | No | exact | Observed matched delay | 452 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8/0 | 2025-05-18 | 2025-05 | 2025-06-06 | 2025-06 | 19 | 19 | Yes | No | exact | Observed matched delay | 451 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-9 | 2025-05-18 | 2025-05 | 2025-07-02 | 2025-07 | 45 | 45 | Yes | No | exact | Observed matched delay | 451 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/2 | 2025-05-22 | 2025-05 | 2025-07-01 | 2025-07 | 40 | 40 | Yes | No | exact | Observed matched delay | 447 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/6 | 2025-05-23 | 2025-05 | 2025-06-27 | 2025-06 | 35 | 35 | Yes | No | exact | Observed matched delay | 446 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 28/1 | 2025-05-24 | 2025-05 | 2025-10-18 | 2025-10 | 147 | 147 | Yes | No | exact | Observed matched delay | 445 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/10 | 2025-05-25 | 2025-05 | 2025-06-13 | 2025-06 | 19 | 19 | Yes | No | exact | Observed matched delay | 444 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/5 | 2025-05-25 | 2025-05 | 2025-07-28 | 2025-07 | 64 | 64 | Yes | No | exact | Observed matched delay | 444 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | AP-28 | 2025-05-25 | 2025-05 | 2025-06-15 | 2025-06 | 21 | 21 | Yes | No | exact | Observed matched delay | 444 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/8 | 2025-05-26 | 2025-05 | 2025-06-20 | 2025-06 | 25 | 25 | Yes | No | exact | Observed matched delay | 443 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/12 | 2025-05-27 | 2025-05 | 2025-07-06 | 2025-07 | 40 | 40 | Yes | No | exact | Observed matched delay | 442 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/9 | 2025-05-29 | 2025-05 | 2025-06-17 | 2025-06 | 19 | 19 | Yes | No | exact | Observed matched delay | 440 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/7 | 2025-05-29 | 2025-05 | 2025-07-01 | 2025-07 | 33 | 33 | Yes | No | exact | Observed matched delay | 440 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/11 | 2025-05-30 | 2025-05 | 2025-06-15 | 2025-06 | 16 | 16 | Yes | No | exact | Observed matched delay | 439 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/6 | 2025-06-04 | 2025-06 | 2025-06-20 | 2025-06 | 16 | 16 | Yes | No | exact | Observed matched delay | 434 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/3 | 2025-06-05 | 2025-06 | 2025-07-03 | 2025-07 | 28 | 28 | Yes | No | exact | Observed matched delay | 433 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 9/4 | 2025-06-05 | 2025-06 | 2025-07-07 | 2025-07 | 32 | 32 | Yes | No | exact | Observed matched delay | 433 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/3 | 2025-06-06 | 2025-06 | 2025-06-22 | 2025-06 | 16 | 16 | Yes | No | exact | Observed matched delay | 432 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/1 | 2025-06-08 | 2025-06 | 2025-06-23 | 2025-06 | 15 | 15 | Yes | No | exact | Observed matched delay | 430 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 28/2 | 2025-06-29 | 2025-06 | 2025-08-14 | 2025-08 | 46 | 46 | Yes | No | exact | Observed matched delay | 409 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 17/0 | 2025-07-10 | 2025-07 | 2025-08-28 | 2025-08 | 49 | 49 | Yes | No | exact | Observed matched delay | 398 | TRUE | FALSE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 8D/5 | 2025-08-17 | 2025-08 | 2025-11-03 | 2025-11 | 78 | 78 | Yes | No | exact | Observed matched delay | 360 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8D/6 | 2025-08-23 | 2025-08 | 2025-11-05 | 2025-11 | 74 | 74 | Yes | No | exact | Observed matched delay | 354 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8D/4 | 2025-08-30 | 2025-08 | 2025-11-02 | 2025-11 | 64 | 64 | Yes | No | exact | Observed matched delay | 347 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/8 | 2025-09-03 | 2025-09 | 2025-12-22 | 2025-12 | 110 | 110 | Yes | No | exact | Observed matched delay | 343 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 14/1 | 2025-09-07 | 2025-09 | 2025-10-26 | 2025-10 | 49 | 49 | Yes | No | exact | Observed matched delay | 339 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8D/3 | 2025-09-10 | 2025-09 | 2025-11-26 | 2025-11 | 77 | 77 | Yes | No | exact | Observed matched delay | 336 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 14/3 | 2025-09-12 | 2025-09 | 2025-10-27 | 2025-10 | 45 | 45 | Yes | No | exact | Observed matched delay | 334 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 14/2 | 2025-09-20 | 2025-09 | 2025-10-21 | 2025-10 | 31 | 31 | Yes | No | exact | Observed matched delay | 326 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8E/0 | 2025-09-21 | 2025-09 | 2025-11-07 | 2025-11 | 47 | 47 | Yes | No | exact | Observed matched delay | 325 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/7 | 2025-09-26 | 2025-09 | 2026-01-19 | 2026-01 | 115 | 115 | Yes | No | exact | Observed matched delay | 320 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 14/4 | 2025-09-30 | 2025-09 | 2025-11-14 | 2025-11 | 45 | 45 | Yes | No | exact | Observed matched delay | 316 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 14/5 | 2025-10-08 | 2025-10 | 2025-10-29 | 2025-10 | 21 | 21 | Yes | No | exact | Observed matched delay | 308 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 5A/1 | 2025-10-08 | 2025-10 | 2025-11-23 | 2025-11 | 46 | 46 | Yes | No | exact | Observed matched delay | 308 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 5A/2 | 2025-10-12 | 2025-10 | 2025-11-22 | 2025-11 | 41 | 41 | Yes | No | exact | Observed matched delay | 304 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 5B/0 | 2025-10-17 | 2025-10 | 2025-11-21 | 2025-11 | 35 | 35 | Yes | No | exact | Observed matched delay | 299 | TRUE | FALSE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 16/0 | 2025-10-23 | 2025-10 | 2025-11-12 | 2025-11 | 20 | 20 | Yes | No | exact | Observed matched delay | 293 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 16/1 | 2025-10-27 | 2025-10 | 2025-11-14 | 2025-11 | 18 | 18 | Yes | No | exact | Observed matched delay | 289 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 14/6 | 2025-11-05 | 2025-11 | 2025-11-15 | 2025-11 | 10 | 10 | Yes | No | exact | Observed matched delay | 280 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 18/0 | 2025-11-07 | 2025-11 | 2025-12-15 | 2025-12 | 38 | 38 | Yes | No | exact | Observed matched delay | 278 | TRUE | FALSE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 13/1 | 2025-11-08 | 2025-11 | 2025-11-10 | 2025-11 | 2 | 2 | Yes | No | exact | Observed matched delay | 277 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 16/2 | 2025-11-15 | 2025-11 | 2025-11-17 | 2025-11 | 2 | 2 | Yes | No | exact | Observed matched delay | 270 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 8E/7 | 2025-11-16 | 2025-11 | 2025-11-29 | 2025-11 | 13 | 13 | Yes | No | exact | Observed matched delay | 269 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8D/1 | 2025-11-20 | 2025-11 | 2025-11-27 | 2025-11 | 7 | 7 | Yes | No | exact | Observed matched delay | 265 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 6/0 | 2025-11-26 | 2025-11 | 2025-12-18 | 2025-12 | 22 | 22 | Yes | No | exact | Observed matched delay | 259 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8D/2 | 2025-12-03 | 2025-12 | 2025-12-07 | 2025-12 | 4 | 4 | Yes | No | exact | Observed matched delay | 252 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 8D/0A | 2025-12-07 | 2025-12 | 2025-12-04 | 2025-12 | -3 |  | Yes | Yes | exact | Negative delay excluded | 248 | TRUE | FALSE | TRUE | FALSE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 10/0 | 2025-12-13 | 2025-12 | 2025-12-28 | 2025-12 | 15 | 15 | Yes | No | exact | Observed matched delay | 242 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 15/2 | 2025-12-15 | 2025-12 | 2025-12-27 | 2025-12 | 12 | 12 | Yes | No | exact | Observed matched delay | 240 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 11/0 | 2025-12-16 | 2025-12 | 2026-01-11 | 2026-01 | 26 | 26 | Yes | No | exact | Observed matched delay | 239 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 15/1 | 2025-12-16 | 2025-12 | 2025-12-31 | 2025-12 | 15 | 15 | Yes | No | exact | Observed matched delay | 239 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 12/0 | 2025-12-17 | 2025-12 | 2026-01-06 | 2026-01 | 20 | 20 | Yes | No | exact | Observed matched delay | 238 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 15/3 | 2025-12-19 | 2025-12 | 2025-12-25 | 2025-12 | 6 | 6 | Yes | No | exact | Observed matched delay | 236 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 13/0 | 2025-12-25 | 2025-12 | 2026-01-03 | 2026-01 | 9 | 9 | Yes | No | exact | Observed matched delay | 230 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 14/0 | 2025-12-28 | 2025-12 | 2026-01-08 | 2026-01 | 11 | 11 | Yes | No | exact | Observed matched delay | 227 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 12/1 | 2026-01-10 | 2026-01 | 2026-01-30 | 2026-01 | 20 | 20 | Yes | No | exact | Observed matched delay | 214 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 13/2 | 2026-01-10 | 2026-01 | 2026-01-24 | 2026-01 | 14 | 14 | Yes | No | exact | Observed matched delay | 214 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 13/1 | 2026-01-14 | 2026-01 | 2026-01-28 | 2026-01 | 14 | 14 | Yes | No | exact | Observed matched delay | 210 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 8/0 | 2026-01-21 | 2026-01 | 2026-02-01 | 2026-02 | 11 | 11 | Yes | No | exact | Observed matched delay | 203 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 9/0 | 2026-01-21 | 2026-01 | 2026-02-04 | 2026-02 | 14 | 14 | Yes | No | exact | Observed matched delay | 203 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 7/0 | 2026-01-25 | 2026-01 | 2026-02-06 | 2026-02 | 12 | 12 | Yes | No | exact | Observed matched delay | 199 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 6/2 | 2026-01-27 | 2026-01 | 2026-03-16 | 2026-03 | 48 | 48 | Yes | No | exact | Observed matched delay | 197 | TRUE | FALSE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 6/1 | 2026-01-30 | 2026-01 | 2026-02-09 | 2026-02 | 10 | 10 | Yes | No | exact | Observed matched delay | 194 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 6/3 | 2026-01-31 | 2026-01 | 2026-02-14 | 2026-02 | 14 | 14 | Yes | No | exact | Observed matched delay | 193 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 5/0 | 2026-02-05 | 2026-02 | 2026-03-14 | 2026-03 | 37 | 37 | Yes | No | exact | Observed matched delay | 188 | TRUE | FALSE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 15/0 | 2026-02-10 | 2026-02 | 2026-02-20 | 2026-02 | 10 | 10 | Yes | No | exact | Observed matched delay | 183 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 6/0 | 2026-02-19 | 2026-02 | 2026-02-17 | 2026-02 | -2 |  | Yes | Yes | exact | Negative delay excluded | 174 | TRUE | FALSE | TRUE | FALSE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 1C/0 | 2026-02-24 | 2026-02 | 2026-03-20 | 2026-03 | 24 | 24 | Yes | No | exact | Observed matched delay | 169 | TRUE | TRUE | TRUE | TRUE |  | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 4/0 | 2026-03-08 | 2026-03 | 2026-03-16 | 2026-03 | 8 | 8 | Yes | No | exact | Observed matched delay | 157 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 6/4 | 2026-03-14 | 2026-03 | 2026-03-18 | 2026-03 | 4 | 4 | Yes | No | exact | Observed matched delay | 151 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 4/1 | 2026-03-16 | 2026-03 | 2026-03-20 | 2026-03 | 4 | 4 | Yes | No | exact | Observed matched delay | 149 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 4/2 | 2026-03-17 | 2026-03 | 2026-03-22 | 2026-03 | 5 | 5 | Yes | No | exact | Observed matched delay | 148 | TRUE | TRUE | TRUE | TRUE |  | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 33/0 (New) | 2026-04-09 | 2026-04 | 2026-05-08 | 2026-05 | 29 | 29 | Yes | No | exact | Observed matched delay | 125 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 3/1 | 2026-04-12 | 2026-04 | 2026-04-18 | 2026-04 | 6 | 6 | Yes | No | exact | Observed matched delay | 122 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 3/0 | 2026-04-14 | 2026-04 | 2026-04-24 | 2026-04 | 10 | 10 | Yes | No | exact | Observed matched delay | 120 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 33/1 (New) | 2026-04-20 | 2026-04 | 2026-05-10 | 2026-05 | 20 | 20 | Yes | No | exact | Observed matched delay | 114 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 34/0 (New) | 2026-04-30 | 2026-04 | 2026-05-16 | 2026-05 | 16 | 16 | Yes | No | exact | Observed matched delay | 104 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | 220kV | 220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-220kV
TB 501 | 5xx | Private | tb501 | 2/0 | 2026-06-19 | 2026-06 | 2026-06-17 | 2026-06 | -2 |  | Yes | Yes | exact | Negative delay excluded | 54 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | SC-2 | 2026-06-19 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 54 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | 132kV |  | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | 1/0 | 2026-06-23 | 2026-06 | 2026-06-20 | 2026-06 | -3 |  | Yes | Yes | exact | Negative delay excluded | 50 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | 132kV | 132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 501 | 5xx | Private | tb501 | SC-1 | 2026-07-24 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 19 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | 132kV |  | TB 501 - DPR - 2026-07-30.xlsx | Progress-132kV
TB 507 | 5xx | Private | tb507 | 83/1 | 2025-01-17 | 2025-01 | 2025-08-29 | 2025-08 | 224 | 224 | Yes | No | exact | Observed matched delay | 572 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 75/7 | 2025-01-27 | 2025-01 | 2025-06-29 | 2025-06 | 153 | 153 | Yes | No | exact | Observed matched delay | 562 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 75/6 | 2025-02-02 | 2025-02 | 2025-07-15 | 2025-07 | 163 | 163 | Yes | No | exact | Observed matched delay | 556 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 75/4 | 2025-02-05 | 2025-02 | 2025-07-22 | 2025-07 | 167 | 167 | Yes | No | exact | Observed matched delay | 553 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 75/5 | 2025-02-05 | 2025-02 | 2025-07-19 | 2025-07 | 164 | 164 | Yes | No | exact | Observed matched delay | 553 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 77/1 | 2025-02-06 | 2025-02 | 2025-07-11 | 2025-07 | 155 | 155 | Yes | No | exact | Observed matched delay | 552 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 77/2 | 2025-02-09 | 2025-02 | 2025-06-23 | 2025-06 | 134 | 134 | Yes | No | exact | Observed matched delay | 549 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 75/3 | 2025-02-10 | 2025-02 | 2025-07-25 | 2025-07 | 165 | 165 | Yes | No | exact | Observed matched delay | 548 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 77/3 | 2025-02-14 | 2025-02 | 2025-07-07 | 2025-07 | 143 | 143 | Yes | No | exact | Observed matched delay | 544 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 75/1 | 2025-02-17 | 2025-02 | 2025-08-01 | 2025-08 | 165 | 165 | Yes | No | exact | Observed matched delay | 541 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 77/4 | 2025-02-17 | 2025-02 | 2025-06-28 | 2025-06 | 131 | 131 | Yes | No | exact | Observed matched delay | 541 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 75/2 | 2025-02-18 | 2025-02 | 2025-07-29 | 2025-07 | 161 | 161 | Yes | No | exact | Observed matched delay | 540 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 77/5 | 2025-02-19 | 2025-02 | 2025-07-03 | 2025-07 | 134 | 134 | Yes | No | exact | Observed matched delay | 539 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 73/3 | 2025-02-22 | 2025-02 | 2025-08-01 | 2025-08 | 160 | 160 | Yes | No | exact | Observed matched delay | 536 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 86/2 | 2025-02-22 | 2025-02 | 2026-05-21 | 2026-05 | 453 | 453 | Yes | No | exact | Observed matched delay | 536 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 79/1 | 2025-02-23 | 2025-02 | 2025-11-25 | 2025-11 | 275 | 275 | Yes | No | exact | Observed matched delay | 535 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 73/2 | 2025-02-25 | 2025-02 | 2025-08-08 | 2025-08 | 164 | 164 | Yes | No | exact | Observed matched delay | 533 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 95A/1 | 2025-02-25 | 2025-02 | 2025-08-23 | 2025-08 | 179 | 179 | Yes | No | exact | Observed matched delay | 533 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 80/1 | 2025-02-27 | 2025-02 | 2025-08-23 | 2025-08 | 177 | 177 | Yes | No | exact | Observed matched delay | 531 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 66/1 | 2025-02-28 | 2025-02 | 2026-03-22 | 2026-03 | 387 | 387 | Yes | No | exact | Observed matched delay | 530 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 74/1 | 2025-02-28 | 2025-02 | 2025-07-24 | 2025-07 | 146 | 146 | Yes | No | exact | Observed matched delay | 530 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 96/1 | 2025-02-28 | 2025-02 | 2025-09-01 | 2025-09 | 185 | 185 | Yes | No | exact | Observed matched delay | 530 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 76/1 | 2025-03-02 | 2025-03 | 2025-09-19 | 2025-09 | 201 | 201 | Yes | No | exact | Observed matched delay | 528 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 66/2 | 2025-03-06 | 2025-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 524 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 64/3 | 2025-03-07 | 2025-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 523 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 96/2 | 2025-03-07 | 2025-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 523 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 81/2 | 2025-03-08 | 2025-03 | 2025-09-01 | 2025-09 | 177 | 177 | Yes | No | exact | Observed matched delay | 522 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 86/1 | 2025-03-09 | 2025-03 | 2025-08-23 | 2025-08 | 167 | 167 | Yes | No | exact | Observed matched delay | 521 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 64/4 | 2025-03-10 | 2025-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 520 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 85/1 | 2025-03-10 | 2025-03 | 2025-08-17 | 2025-08 | 160 | 160 | Yes | No | exact | Observed matched delay | 520 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 99/1 | 2025-03-10 | 2025-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 520 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 66/3 | 2025-03-11 | 2025-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 519 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 87/1 | 2025-03-24 | 2025-03 | 2026-06-27 | 2026-06 | 460 | 460 | Yes | No | exact | Observed matched delay | 506 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 64/7 | 2025-03-26 | 2025-03 | 2026-03-17 | 2026-03 | 356 | 356 | Yes | No | exact | Observed matched delay | 504 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 64/6 | 2025-03-30 | 2025-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 500 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 87/2 | 2025-03-30 | 2025-03 | 2026-06-15 | 2026-06 | 442 | 442 | Yes | No | exact | Observed matched delay | 500 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 98A/1 | 2025-03-30 | 2025-03 | 2025-09-23 | 2025-09 | 177 | 177 | Yes | No | exact | Observed matched delay | 500 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 64/5 | 2025-03-31 | 2025-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 499 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 98/1 | 2025-04-04 | 2025-04 | 2025-09-15 | 2025-09 | 164 | 164 | Yes | No | exact | Observed matched delay | 495 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 71/1 | 2025-04-09 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 490 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 91/1 | 2025-04-13 | 2025-04 | 2026-02-25 | 2026-02 | 318 | 318 | Yes | No | exact | Observed matched delay | 486 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 91/2 | 2025-04-16 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 483 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 51/2 | 2025-04-17 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 482 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 119/1 | 2025-04-18 | 2025-04 | 2025-12-18 | 2025-12 | 244 | 244 | Yes | No | exact | Observed matched delay | 481 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 95/2 | 2025-04-20 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 479 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 119/2 | 2025-04-22 | 2025-04 | 2025-12-13 | 2025-12 | 235 | 235 | Yes | No | exact | Observed matched delay | 477 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 51/3 | 2025-04-23 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 476 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 99/2 | 2025-04-25 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 474 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 104B/1 | 2025-04-29 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 470 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 62/4 | 2025-04-29 | 2025-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 470 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 81/4 | 2025-04-29 | 2025-04 | 2025-09-05 | 2025-09 | 129 | 129 | Yes | No | exact | Observed matched delay | 470 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 104B/2 | 2025-05-05 | 2025-05 | 2025-10-18 | 2025-10 | 166 | 166 | Yes | No | exact | Observed matched delay | 464 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 105/1 | 2025-05-15 | 2025-05 | 2026-04-30 | 2026-04 | 350 | 350 | Yes | No | exact | Observed matched delay | 454 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 100/1 | 2025-05-18 | 2025-05 | 2026-06-02 | 2026-06 | 380 | 380 | Yes | No | exact | Observed matched delay | 451 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 81/5 | 2025-05-21 | 2025-05 | 2025-12-17 | 2025-12 | 210 | 210 | Yes | No | exact | Observed matched delay | 448 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 97/0 | 2025-05-23 | 2025-05 | 2025-09-01 | 2025-09 | 101 | 101 | Yes | No | exact | Observed matched delay | 446 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 99C/2 | 2025-05-25 | 2025-05 | 2026-06-17 | 2026-06 | 388 | 388 | Yes | No | exact | Observed matched delay | 444 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 105/0 | 2025-05-28 | 2025-05 | 2026-08-04 | 2026-08 | 433 | 433 | Yes | No | exact | Observed matched delay | 441 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 98A/0 | 2025-05-29 | 2025-05 | 2025-09-26 | 2025-09 | 120 | 120 | Yes | No | exact | Observed matched delay | 440 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 62/5 | 2025-05-31 | 2025-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 438 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 81/3 | 2025-06-04 | 2025-06 | 2025-08-29 | 2025-08 | 86 | 86 | Yes | No | exact | Observed matched delay | 434 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 120/1 | 2025-06-05 | 2025-06 | 2025-12-21 | 2025-12 | 199 | 199 | Yes | No | exact | Observed matched delay | 433 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 96/0 | 2025-06-06 | 2025-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 432 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 75/0 | 2025-06-07 | 2025-06 | 2025-08-04 | 2025-08 | 58 | 58 | Yes | No | exact | Observed matched delay | 431 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/2 | 2025-06-08 | 2025-06 | 2025-10-15 | 2025-10 | 129 | 129 | Yes | No | exact | Observed matched delay | 430 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 82/2 | 2025-06-10 | 2025-06 | 2025-10-19 | 2025-10 | 131 | 131 | Yes | No | exact | Observed matched delay | 428 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/5 | 2025-06-12 | 2025-06 | 2025-10-27 | 2025-10 | 137 | 137 | Yes | No | exact | Observed matched delay | 426 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 79/0 | 2025-06-12 | 2025-06 | 2025-08-17 | 2025-08 | 66 | 66 | Yes | No | exact | Observed matched delay | 426 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 119/0 | 2025-06-15 | 2025-06 | 2026-07-28 | 2026-07 | 408 | 408 | Yes | No | exact | Observed matched delay | 423 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/0 | 2025-06-15 | 2025-06 | 2025-10-10 | 2025-10 | 117 | 117 | Yes | No | exact | Observed matched delay | 423 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 82/1 | 2025-06-15 | 2025-06 | 2025-09-09 | 2025-09 | 86 | 86 | Yes | No | exact | Observed matched delay | 423 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/4 | 2025-06-16 | 2025-06 | 2025-10-28 | 2025-10 | 134 | 134 | Yes | No | exact | Observed matched delay | 422 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 78/0 | 2025-06-16 | 2025-06 | 2025-08-10 | 2025-08 | 55 | 55 | Yes | No | exact | Observed matched delay | 422 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 74/0 | 2025-06-20 | 2025-06 | 2026-07-27 | 2026-07 | 402 | 402 | Yes | No | exact | Observed matched delay | 418 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/1 | 2025-06-21 | 2025-06 | 2025-10-19 | 2025-10 | 120 | 120 | Yes | No | exact | Observed matched delay | 417 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/7 | 2025-06-22 | 2025-06 | 2025-09-30 | 2025-09 | 100 | 100 | Yes | No | exact | Observed matched delay | 416 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 95A/0 | 2025-06-23 | 2025-06 | 2026-01-07 | 2026-01 | 198 | 198 | Yes | No | exact | Observed matched delay | 415 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 146/2 | 2025-06-25 | 2025-06 | 2025-10-03 | 2025-10 | 100 | 100 | Yes | No | exact | Observed matched delay | 413 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/3 | 2025-06-25 | 2025-06 | 2025-10-12 | 2025-10 | 109 | 109 | Yes | No | exact | Observed matched delay | 413 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 73/0 | 2025-06-26 | 2025-06 | 2025-12-19 | 2025-12 | 176 | 176 | Yes | No | exact | Observed matched delay | 412 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 86/0 | 2025-06-27 | 2025-06 | 2025-12-28 | 2025-12 | 184 | 184 | Yes | No | exact | Observed matched delay | 411 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 114/0 | 2025-06-30 | 2025-06 | 2026-01-20 | 2026-01 | 204 | 204 | Yes | No | exact | Observed matched delay | 408 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 146/1 | 2025-06-30 | 2025-06 | 2025-09-30 | 2025-09 | 92 | 92 | Yes | No | exact | Observed matched delay | 408 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/8 | 2025-06-30 | 2025-06 | 2025-10-19 | 2025-10 | 111 | 111 | Yes | No | exact | Observed matched delay | 408 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 72/2 | 2025-06-30 | 2025-06 | 2025-12-06 | 2025-12 | 159 | 159 | Yes | No | exact | Observed matched delay | 408 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 95/1 | 2025-07-04 | 2025-07 | 2025-12-27 | 2025-12 | 176 | 176 | Yes | No | exact | Observed matched delay | 404 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 148/3 | 2025-07-05 | 2025-07 | 2025-08-29 | 2025-08 | 55 | 55 | Yes | No | exact | Observed matched delay | 403 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 106/0 | 2025-07-06 | 2025-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 402 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 146/0 | 2025-07-08 | 2025-07 | 2025-10-05 | 2025-10 | 89 | 89 | Yes | No | exact | Observed matched delay | 400 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 148/1 | 2025-07-08 | 2025-07 | 2025-10-23 | 2025-10 | 107 | 107 | Yes | No | exact | Observed matched delay | 400 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 114/1 | 2025-07-10 | 2025-07 | 2025-09-24 | 2025-09 | 76 | 76 | Yes | No | exact | Observed matched delay | 398 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 148/2 | 2025-07-10 | 2025-07 | 2025-09-05 | 2025-09 | 57 | 57 | Yes | No | exact | Observed matched delay | 398 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 80/0 | 2025-07-10 | 2025-07 | 2025-11-10 | 2025-11 | 123 | 123 | Yes | No | exact | Observed matched delay | 398 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 141/1 | 2025-07-11 | 2025-07 | 2025-09-27 | 2025-09 | 78 | 78 | Yes | No | exact | Observed matched delay | 397 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 95/0 | 2025-07-11 | 2025-07 | 2025-11-29 | 2025-11 | 141 | 141 | Yes | No | exact | Observed matched delay | 397 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 148/4 | 2025-07-12 | 2025-07 | 2025-08-27 | 2025-08 | 46 | 46 | Yes | No | exact | Observed matched delay | 396 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 141/2 | 2025-07-13 | 2025-07 | 2025-09-24 | 2025-09 | 73 | 73 | Yes | No | exact | Observed matched delay | 395 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 145/4 | 2025-07-13 | 2025-07 | 2025-09-20 | 2025-09 | 69 | 69 | Yes | No | exact | Observed matched delay | 395 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 125/1 | 2025-07-14 | 2025-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 394 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 133/6 | 2025-07-14 | 2025-07 | 2025-09-23 | 2025-09 | 71 | 71 | Yes | No | exact | Observed matched delay | 394 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 148/5 | 2025-07-15 | 2025-07 | 2025-09-11 | 2025-09 | 58 | 58 | Yes | No | exact | Observed matched delay | 393 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 109A/0 | 2025-07-16 | 2025-07 | 2025-11-13 | 2025-11 | 120 | 120 | Yes | No | exact | Observed matched delay | 392 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 113A/0 | 2025-07-16 | 2025-07 | 2025-09-14 | 2025-09 | 60 | 60 | Yes | No | exact | Observed matched delay | 392 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 133/5 | 2025-07-16 | 2025-07 | 2025-11-15 | 2025-11 | 122 | 122 | Yes | No | exact | Observed matched delay | 392 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 145/2 | 2025-07-16 | 2025-07 | 2025-09-09 | 2025-09 | 55 | 55 | Yes | No | exact | Observed matched delay | 392 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 142/0 | 2025-07-17 | 2025-07 | 2025-10-01 | 2025-10 | 76 | 76 | Yes | No | exact | Observed matched delay | 391 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 115/0 | 2025-07-18 | 2025-07 | 2025-10-08 | 2025-10 | 82 | 82 | Yes | No | exact | Observed matched delay | 390 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 148/6 | 2025-07-18 | 2025-07 | 2025-09-14 | 2025-09 | 58 | 58 | Yes | No | exact | Observed matched delay | 390 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 77/0 | 2025-07-19 | 2025-07 | 2025-11-01 | 2025-11 | 105 | 105 | Yes | No | exact | Observed matched delay | 389 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 133/4 | 2025-07-21 | 2025-07 | 2025-10-11 | 2025-10 | 82 | 82 | Yes | No | exact | Observed matched delay | 387 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 143/0 | 2025-07-21 | 2025-07 | 2025-09-27 | 2025-09 | 68 | 68 | Yes | No | exact | Observed matched delay | 387 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 145/1 | 2025-07-21 | 2025-07 | 2025-08-27 | 2025-08 | 37 | 37 | Yes | No | exact | Observed matched delay | 387 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 148/7 | 2025-07-23 | 2025-07 | 2025-09-20 | 2025-09 | 59 | 59 | Yes | No | exact | Observed matched delay | 385 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 125/0 | 2025-07-24 | 2025-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 384 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 133/3 | 2025-07-24 | 2025-07 | 2025-09-17 | 2025-09 | 55 | 55 | Yes | No | exact | Observed matched delay | 384 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 94/0 | 2025-07-24 | 2025-07 | 2026-08-08 | 2026-08 | 380 | 380 | Yes | No | exact | Observed matched delay | 384 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 145/3 | 2025-07-25 | 2025-07 | 2025-09-14 | 2025-09 | 51 | 51 | Yes | No | exact | Observed matched delay | 383 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 126/2 | 2025-07-26 | 2025-07 | 2025-12-06 | 2025-12 | 133 | 133 | Yes | No | exact | Observed matched delay | 382 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 143/3 | 2025-07-26 | 2025-07 | 2025-09-21 | 2025-09 | 57 | 57 | Yes | No | exact | Observed matched delay | 382 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 133/8 | 2025-07-27 | 2025-07 | 2025-10-05 | 2025-10 | 70 | 70 | Yes | No | exact | Observed matched delay | 381 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 149B/1 | 2025-07-27 | 2025-07 | 2025-09-24 | 2025-09 | 59 | 59 | Yes | No | exact | Observed matched delay | 381 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 79/2 | 2025-07-27 | 2025-07 | 2025-09-11 | 2025-09 | 46 | 46 | Yes | No | exact | Observed matched delay | 381 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 110/0 | 2025-07-28 | 2025-07 | 2025-10-13 | 2025-10 | 77 | 77 | Yes | No | exact | Observed matched delay | 380 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 143/1 | 2025-07-29 | 2025-07 | 2025-09-22 | 2025-09 | 55 | 55 | Yes | No | exact | Observed matched delay | 379 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 99/3 | 2025-07-29 | 2025-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 379 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 133/1 | 2025-07-30 | 2025-07 | 2025-10-15 | 2025-10 | 77 | 77 | Yes | No | exact | Observed matched delay | 378 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 149B/2 | 2025-07-30 | 2025-07 | 2025-09-27 | 2025-09 | 59 | 59 | Yes | No | exact | Observed matched delay | 378 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 111/0 | 2025-07-31 | 2025-07 | 2025-11-03 | 2025-11 | 95 | 95 | Yes | No | exact | Observed matched delay | 377 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 116/0 | 2025-07-31 | 2025-07 | 2025-09-30 | 2025-09 | 61 | 61 | Yes | No | exact | Observed matched delay | 377 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 129/1 | 2025-07-31 | 2025-07 | 2025-11-01 | 2025-11 | 93 | 93 | Yes | No | exact | Observed matched delay | 377 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 133/7 | 2025-07-31 | 2025-07 | 2025-09-29 | 2025-09 | 60 | 60 | Yes | No | exact | Observed matched delay | 377 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 143/6 | 2025-07-31 | 2025-07 | 2025-09-18 | 2025-09 | 49 | 49 | Yes | No | exact | Observed matched delay | 377 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 145/0 | 2025-07-31 | 2025-07 | 2025-11-12 | 2025-11 | 104 | 104 | Yes | No | exact | Observed matched delay | 377 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 76/0 | 2025-07-31 | 2025-07 | 2025-10-24 | 2025-10 | 85 | 85 | Yes | No | exact | Observed matched delay | 377 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 98B/0 | 2025-07-31 | 2025-07 | 2025-11-22 | 2025-11 | 114 | 114 | Yes | No | exact | Observed matched delay | 377 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 126/1 | 2025-08-02 | 2025-08 | 2025-12-12 | 2025-12 | 132 | 132 | Yes | No | exact | Observed matched delay | 375 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 143/7 | 2025-08-02 | 2025-08 | 2025-09-21 | 2025-09 | 50 | 50 | Yes | No | exact | Observed matched delay | 375 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 130/0 | 2025-08-04 | 2025-08 | 2025-11-28 | 2025-11 | 116 | 116 | Yes | No | exact | Observed matched delay | 373 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 143/5 | 2025-08-04 | 2025-08 | 2025-09-11 | 2025-09 | 38 | 38 | Yes | No | exact | Observed matched delay | 373 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 97/1 | 2025-08-05 | 2025-08 | 2025-09-11 | 2025-09 | 37 | 37 | Yes | No | exact | Observed matched delay | 372 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 143/2 | 2025-08-06 | 2025-08 | 2025-09-18 | 2025-09 | 43 | 43 | Yes | No | exact | Observed matched delay | 371 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 102/2 | 2025-08-07 | 2025-08 | 2026-01-17 | 2026-01 | 163 | 163 | Yes | No | exact | Observed matched delay | 370 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 133/2 | 2025-08-07 | 2025-08 | 2025-08-28 | 2025-08 | 21 | 21 | Yes | No | exact | Observed matched delay | 370 | TRUE | TRUE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 144/0 | 2025-08-07 | 2025-08 | 2025-10-01 | 2025-10 | 55 | 55 | Yes | No | exact | Observed matched delay | 370 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 98/0 | 2025-08-07 | 2025-08 | 2025-11-06 | 2025-11 | 91 | 91 | Yes | No | exact | Observed matched delay | 370 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 112/0 | 2025-08-08 | 2025-08 | 2025-10-19 | 2025-10 | 72 | 72 | Yes | No | exact | Observed matched delay | 369 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 129/0 | 2025-08-08 | 2025-08 | 2025-11-09 | 2025-11 | 93 | 93 | Yes | No | exact | Observed matched delay | 369 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 143/4 | 2025-08-09 | 2025-08 | 2025-09-11 | 2025-09 | 33 | 33 | Yes | No | exact | Observed matched delay | 368 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 83/0 | 2025-08-09 | 2025-08 | 2026-01-02 | 2026-01 | 146 | 146 | Yes | No | exact | Observed matched delay | 368 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 131/1 | 2025-08-12 | 2025-08 | 2025-11-06 | 2025-11 | 86 | 86 | Yes | No | exact | Observed matched delay | 365 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 149B/0 | 2025-08-12 | 2025-08 | 2025-11-23 | 2025-11 | 103 | 103 | Yes | No | exact | Observed matched delay | 365 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 102/1 | 2025-08-14 | 2025-08 | 2026-05-10 | 2026-05 | 269 | 269 | Yes | No | exact | Observed matched delay | 363 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 140/3 | 2025-08-14 | 2025-08 | 2025-10-10 | 2025-10 | 57 | 57 | Yes | No | exact | Observed matched delay | 363 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 99/0 | 2025-08-14 | 2025-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 363 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 115/1 | 2025-08-16 | 2025-08 | 2025-10-27 | 2025-10 | 72 | 72 | Yes | No | exact | Observed matched delay | 361 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 134A/4 | 2025-08-16 | 2025-08 | 2025-11-04 | 2025-11 | 80 | 80 | Yes | No | exact | Observed matched delay | 361 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 140/2 | 2025-08-17 | 2025-08 | 2025-10-08 | 2025-10 | 52 | 52 | Yes | No | exact | Observed matched delay | 360 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 126/0 | 2025-08-19 | 2025-08 | 2026-01-05 | 2026-01 | 139 | 139 | Yes | No | exact | Observed matched delay | 358 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 135/0 | 2025-08-19 | 2025-08 | 2025-10-29 | 2025-10 | 71 | 71 | Yes | No | exact | Observed matched delay | 358 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 149A/0 | 2025-08-19 | 2025-08 | 2025-10-10 | 2025-10 | 52 | 52 | Yes | No | exact | Observed matched delay | 358 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 128/0 | 2025-08-20 | 2025-08 | 2025-11-21 | 2025-11 | 93 | 93 | Yes | No | exact | Observed matched delay | 357 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 131/2 | 2025-08-20 | 2025-08 | 2025-11-11 | 2025-11 | 83 | 83 | Yes | No | exact | Observed matched delay | 357 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 141/0 | 2025-08-20 | 2025-08 | 2025-10-11 | 2025-10 | 52 | 52 | Yes | No | exact | Observed matched delay | 357 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 87/0 | 2025-08-22 | 2025-08 | 2026-07-20 | 2026-07 | 332 | 332 | Yes | No | exact | Observed matched delay | 355 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 99/4 | 2025-08-22 | 2025-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 355 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 129/2 | 2025-08-23 | 2025-08 | 2026-01-07 | 2026-01 | 137 | 137 | Yes | No | exact | Observed matched delay | 354 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 135/1 | 2025-08-23 | 2025-08 | 2025-10-19 | 2025-10 | 57 | 57 | Yes | No | exact | Observed matched delay | 354 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 138/1 | 2025-08-23 | 2025-08 | 2025-10-08 | 2025-10 | 46 | 46 | Yes | No | exact | Observed matched delay | 354 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 137/0 | 2025-08-24 | 2025-08 | 2025-11-06 | 2025-11 | 74 | 74 | Yes | No | exact | Observed matched delay | 353 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 63/1 | 2025-08-24 | 2025-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 353 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 132/1 | 2025-08-25 | 2025-08 | 2025-11-05 | 2025-11 | 72 | 72 | Yes | No | exact | Observed matched delay | 352 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 138/2 | 2025-08-25 | 2025-08 | 2025-10-13 | 2025-10 | 49 | 49 | Yes | No | exact | Observed matched delay | 352 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 134A/2 | 2025-08-26 | 2025-08 | 2025-10-24 | 2025-10 | 59 | 59 | Yes | No | exact | Observed matched delay | 351 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 56/4 | 2025-08-26 | 2025-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 351 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 56/2 | 2025-08-27 | 2025-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 350 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 138/0 | 2025-08-28 | 2025-08 | 2025-10-19 | 2025-10 | 52 | 52 | Yes | No | exact | Observed matched delay | 349 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 149/0 | 2025-08-28 | 2025-08 | 2025-10-03 | 2025-10 | 36 | 36 | Yes | No | exact | Observed matched delay | 349 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 134/0 | 2025-08-29 | 2025-08 | 2025-10-27 | 2025-10 | 59 | 59 | Yes | No | exact | Observed matched delay | 348 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 134A/1 | 2025-08-29 | 2025-08 | 2025-10-29 | 2025-10 | 61 | 61 | Yes | No | exact | Observed matched delay | 348 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 116/1 | 2025-08-31 | 2025-08 | 2025-09-27 | 2025-09 | 27 | 27 | Yes | No | exact | Observed matched delay | 346 | TRUE | TRUE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 132/3 | 2025-08-31 | 2025-08 | 2025-11-01 | 2025-11 | 62 | 62 | Yes | No | exact | Observed matched delay | 346 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 134A/0 | 2025-08-31 | 2025-08 | 2025-10-16 | 2025-10 | 46 | 46 | Yes | No | exact | Observed matched delay | 346 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 138/3 | 2025-08-31 | 2025-08 | 2025-10-16 | 2025-10 | 46 | 46 | Yes | No | exact | Observed matched delay | 346 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 56/5 | 2025-08-31 | 2025-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 346 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 82/0 | 2025-08-31 | 2025-08 | 2025-11-15 | 2025-11 | 76 | 76 | Yes | No | exact | Observed matched delay | 346 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 85/0 | 2025-08-31 | 2025-08 | 2025-12-12 | 2025-12 | 103 | 103 | Yes | No | exact | Observed matched delay | 346 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 99A/0 | 2025-08-31 | 2025-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 346 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 131/0 | 2025-09-04 | 2025-09 | 2026-01-31 | 2026-01 | 149 | 149 | Yes | No | exact | Observed matched delay | 342 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 139/0 | 2025-09-05 | 2025-09 | 2025-10-26 | 2025-10 | 51 | 51 | Yes | No | exact | Observed matched delay | 341 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/6 | 2025-09-05 | 2025-09 | 2025-10-23 | 2025-10 | 48 | 48 | Yes | No | exact | Observed matched delay | 341 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 125/3 | 2025-09-10 | 2025-09 | 2025-12-31 | 2025-12 | 112 | 112 | Yes | No | exact | Observed matched delay | 336 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 57/0 | 2025-09-10 | 2025-09 |  |  |  |  | No | No |  | Unmatched/right-censored | 336 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 59/0 | 2025-09-12 | 2025-09 |  |  |  |  | No | No |  | Unmatched/right-censored | 334 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 81/0 | 2025-09-12 | 2025-09 | 2025-12-06 | 2025-12 | 85 | 85 | Yes | No | exact | Observed matched delay | 334 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 147/9 | 2025-09-14 | 2025-09 | 2025-10-16 | 2025-10 | 32 | 32 | Yes | No | exact | Observed matched delay | 332 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 64/0 | 2025-09-14 | 2025-09 |  |  |  |  | No | No |  | Unmatched/right-censored | 332 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 58/0 | 2025-09-17 | 2025-09 |  |  |  |  | No | No |  | Unmatched/right-censored | 329 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 125/2 | 2025-09-18 | 2025-09 |  |  |  |  | No | No |  | Unmatched/right-censored | 328 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 72/1 | 2025-09-19 | 2025-09 | 2026-08-09 | 2026-08 | 324 | 324 | Yes | No | exact | Observed matched delay | 327 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 56/1 | 2025-09-20 | 2025-09 |  |  |  |  | No | No |  | Unmatched/right-censored | 326 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 136/0 | 2025-09-21 | 2025-09 | 2025-11-03 | 2025-11 | 43 | 43 | Yes | No | exact | Observed matched delay | 325 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 132/4 | 2025-09-25 | 2025-09 | 2025-11-08 | 2025-11 | 44 | 44 | Yes | No | exact | Observed matched delay | 321 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 48/0 | 2025-09-25 | 2025-09 |  |  |  |  | No | No |  | Unmatched/right-censored | 321 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 123/0 | 2025-09-30 | 2025-09 | 2025-12-28 | 2025-12 | 89 | 89 | Yes | No | exact | Observed matched delay | 316 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 133/0 | 2025-09-30 | 2025-09 | 2025-10-24 | 2025-10 | 24 | 24 | Yes | No | exact | Observed matched delay | 316 | TRUE | TRUE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 152/0 | 2025-09-30 | 2025-09 | 2025-11-01 | 2025-11 | 32 | 32 | Yes | No | exact | Observed matched delay | 316 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 153A/0 | 2025-09-30 | 2025-09 | 2025-10-27 | 2025-10 | 27 | 27 | Yes | No | exact | Observed matched delay | 316 | TRUE | TRUE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 135/2 | 2025-10-11 | 2025-10 | 2025-11-25 | 2025-11 | 45 | 45 | Yes | No | exact | Observed matched delay | 305 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 149B/3 | 2025-10-13 | 2025-10 | 2025-11-14 | 2025-11 | 32 | 32 | Yes | No | exact | Observed matched delay | 303 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 135/3 | 2025-10-16 | 2025-10 | 2025-11-28 | 2025-11 | 43 | 43 | Yes | No | exact | Observed matched delay | 300 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 73/1 | 2025-10-16 | 2025-10 | 2026-05-03 | 2026-05 | 199 | 199 | Yes | No | exact | Observed matched delay | 300 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 84/0 | 2025-10-19 | 2025-10 | 2025-12-17 | 2025-12 | 59 | 59 | Yes | No | exact | Observed matched delay | 297 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 150/0 | 2025-10-29 | 2025-10 | 2025-11-28 | 2025-11 | 30 | 30 | Yes | No | exact | Observed matched delay | 287 | TRUE | TRUE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 71/2 | 2025-10-30 | 2025-10 | 2025-01-14 | 2025-01 | -289 |  | Yes | Yes | exact | Negative delay excluded | 286 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 134A/3 | 2025-10-31 | 2025-10 | 2025-11-21 | 2025-11 | 21 | 21 | Yes | No | exact | Observed matched delay | 285 | TRUE | TRUE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 148/0 | 2025-11-04 | 2025-11 | 2025-11-16 | 2025-11 | 12 | 12 | Yes | No | exact | Observed matched delay | 281 | TRUE | TRUE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 71/3 | 2025-11-07 | 2025-11 | 2026-01-08 | 2026-01 | 62 | 62 | Yes | No | exact | Observed matched delay | 278 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 151/0 | 2025-11-08 | 2025-11 | 2025-12-07 | 2025-12 | 29 | 29 | Yes | No | exact | Observed matched delay | 277 | TRUE | TRUE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 78/1 | 2025-11-08 | 2025-11 | 2025-11-21 | 2025-11 | 13 | 13 | Yes | No | exact | Observed matched delay | 277 | TRUE | TRUE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 81/1 | 2025-11-10 | 2025-11 | 2025-12-01 | 2025-12 | 21 | 21 | Yes | No | exact | Observed matched delay | 275 | TRUE | TRUE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 140/1 | 2025-11-11 | 2025-11 | 2025-12-01 | 2025-12 | 20 | 20 | Yes | No | exact | Observed matched delay | 274 | TRUE | TRUE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 89/0 | 2025-11-12 | 2025-11 | 2026-07-16 | 2026-07 | 246 | 246 | Yes | No | exact | Observed matched delay | 273 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 71/0 | 2025-11-14 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 271 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 113/0 | 2025-11-16 | 2025-11 | 2026-01-12 | 2026-01 | 57 | 57 | Yes | No | exact | Observed matched delay | 269 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 139/1 | 2025-11-16 | 2025-11 | 2025-12-06 | 2025-12 | 20 | 20 | Yes | No | exact | Observed matched delay | 269 | TRUE | TRUE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 72/0 | 2025-11-17 | 2025-11 | 2026-05-09 | 2026-05 | 173 | 173 | Yes | No | exact | Observed matched delay | 268 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 89/1 | 2025-11-18 | 2025-11 | 2025-12-31 | 2025-12 | 43 | 43 | Yes | No | exact | Observed matched delay | 267 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 140/0 | 2025-11-22 | 2025-11 | 2025-12-09 | 2025-12 | 17 | 17 | Yes | No | exact | Observed matched delay | 263 | TRUE | TRUE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 154/0 | 2025-11-22 | 2025-11 | 2025-12-14 | 2025-12 | 22 | 22 | Yes | No | exact | Observed matched delay | 263 | TRUE | TRUE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 90/0 | 2025-11-22 | 2025-11 | 2026-02-20 | 2026-02 | 90 | 90 | Yes | No | exact | Observed matched delay | 263 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 90/1 | 2025-11-26 | 2025-11 | 2025-12-12 | 2025-12 | 16 | 16 | Yes | No | exact | Observed matched delay | 259 | TRUE | TRUE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 127/1 | 2025-11-28 | 2025-11 | 2026-01-13 | 2026-01 | 46 | 46 | Yes | No | exact | Observed matched delay | 257 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 153/0 | 2025-11-30 | 2025-11 | 2025-12-21 | 2025-12 | 21 | 21 | Yes | No | exact | Observed matched delay | 255 | TRUE | TRUE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 66/0 | 2025-11-30 | 2025-11 | 2026-02-19 | 2026-02 | 81 | 81 | Yes | No | exact | Observed matched delay | 255 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 118/0 | 2025-12-05 | 2025-12 | 2026-01-27 | 2026-01 | 53 | 53 | Yes | No | exact | Observed matched delay | 250 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 88/0 | 2025-12-05 | 2025-12 | 2026-07-11 | 2026-07 | 218 | 218 | Yes | No | exact | Observed matched delay | 250 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 130/1 | 2025-12-06 | 2025-12 | 2026-02-08 | 2026-02 | 64 | 64 | Yes | No | exact | Observed matched delay | 249 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 98B/2 | 2025-12-08 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 247 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 117/0 | 2025-12-13 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 242 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 128/1 | 2025-12-14 | 2025-12 | 2026-02-05 | 2026-02 | 53 | 53 | Yes | No | exact | Observed matched delay | 241 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 117/1 | 2025-12-19 | 2025-12 | 2026-05-11 | 2026-05 | 143 | 143 | Yes | No | exact | Observed matched delay | 236 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 132/2 | 2025-12-20 | 2025-12 | 2026-02-11 | 2026-02 | 53 | 53 | Yes | No | exact | Observed matched delay | 235 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 91/0 | 2025-12-24 | 2025-12 | 2026-05-19 | 2026-05 | 146 | 146 | Yes | No | exact | Observed matched delay | 231 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 132/0 | 2025-12-28 | 2025-12 | 2026-02-12 | 2026-02 | 46 | 46 | Yes | No | exact | Observed matched delay | 227 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 104A/0 | 2025-12-30 | 2025-12 | 2026-08-09 | 2026-08 | 222 | 222 | Yes | No | exact | Observed matched delay | 225 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 124/0 | 2025-12-30 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 225 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 91/3 | 2025-12-31 | 2025-12 | 2026-05-08 | 2026-05 | 128 | 128 | Yes | No | exact | Observed matched delay | 224 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 104B/0 | 2026-01-04 | 2026-01 | 2026-05-10 | 2026-05 | 126 | 126 | Yes | No | exact | Observed matched delay | 220 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 65/0 | 2026-01-07 | 2026-01 | 2026-03-10 | 2026-03 | 62 | 62 | Yes | No | exact | Observed matched delay | 217 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 122/2 | 2026-01-08 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 216 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 126/3 | 2026-01-15 | 2026-01 | 2026-05-24 | 2026-05 | 129 | 129 | Yes | No | exact | Observed matched delay | 209 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 65/1 | 2026-01-15 | 2026-01 | 2026-03-01 | 2026-03 | 45 | 45 | Yes | No | exact | Observed matched delay | 209 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 69/3 | 2026-01-15 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 209 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 108/0 | 2026-01-20 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 204 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 10/3 | 2026-01-23 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 201 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 109/0 | 2026-01-23 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 201 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 120/0 | 2026-01-25 | 2026-01 | 2026-05-19 | 2026-05 | 114 | 114 | Yes | No | exact | Observed matched delay | 199 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 10/5 | 2026-01-26 | 2026-01 | 2026-04-10 | 2026-04 | 74 | 74 | Yes | No | exact | Observed matched delay | 198 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 10/6 | 2026-01-28 | 2026-01 | 2026-04-17 | 2026-04 | 79 | 79 | Yes | No | exact | Observed matched delay | 196 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 92/0 | 2026-01-28 | 2026-01 | 2026-04-27 | 2026-04 | 89 | 89 | Yes | No | exact | Observed matched delay | 196 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 10/7 | 2026-01-30 | 2026-01 | 2026-04-20 | 2026-04 | 80 | 80 | Yes | No | exact | Observed matched delay | 194 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 93/0 | 2026-01-30 | 2026-01 | 2026-05-14 | 2026-05 | 104 | 104 | Yes | No | exact | Observed matched delay | 194 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 7/7 | 2026-02-04 | 2026-02 | 2026-04-24 | 2026-04 | 79 | 79 | Yes | No | exact | Observed matched delay | 189 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 7/9 | 2026-02-06 | 2026-02 | 2026-04-16 | 2026-04 | 69 | 69 | Yes | No | exact | Observed matched delay | 187 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 7/0 | 2026-02-11 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 182 | TRUE | FALSE | TRUE | FALSE |  | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 10/12 | 2026-02-12 | 2026-02 | 2026-06-02 | 2026-06 | 110 | 110 | Yes | No | exact | Observed matched delay | 181 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 1/1 | 2026-02-14 | 2026-02 | 2026-03-27 | 2026-03 | 41 | 41 | Yes | No | fallback_single_line | Observed matched delay | 179 | TRUE | FALSE | TRUE | TRUE |  | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 6/2 | 2026-02-16 | 2026-02 | 2026-06-19 | 2026-06 | 123 | 123 | Yes | No | fallback_single_line | Observed matched delay | 177 | TRUE | FALSE | TRUE | FALSE |  | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 1/2 | 2026-02-18 | 2026-02 | 2026-04-07 | 2026-04 | 48 | 48 | Yes | No | fallback_single_line | Observed matched delay | 175 | TRUE | FALSE | TRUE | TRUE |  | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 6/1 | 2026-02-20 | 2026-02 | 2026-06-21 | 2026-06 | 121 | 121 | Yes | No | fallback_single_line | Observed matched delay | 173 | TRUE | FALSE | TRUE | FALSE |  | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 1/0 | 2026-02-28 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 165 | TRUE | FALSE | TRUE | FALSE |  | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 117/2 | 2026-02-28 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 165 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 4/0 | 2026-02-28 | 2026-02 | 2026-05-25 | 2026-05 | 86 | 86 | Yes | No | exact | Observed matched delay | 165 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 6/0 | 2026-02-28 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 165 | TRUE | FALSE | TRUE | FALSE |  | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 157/0 | 2026-03-04 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 161 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 156/0 | 2026-03-10 | 2026-03 | 2026-08-08 | 2026-08 | 151 | 151 | Yes | No | exact | Observed matched delay | 155 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 2/1 | 2026-03-11 | 2026-03 | 2026-04-15 | 2026-04 | 35 | 35 | Yes | No | fallback_single_line | Observed matched delay | 154 | TRUE | FALSE | TRUE | TRUE |  | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 98B/1 | 2026-03-11 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 154 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 2/0 | 2026-03-13 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 152 | TRUE | FALSE | TRUE | FALSE |  | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 2/2 | 2026-03-15 | 2026-03 | 2026-06-11 | 2026-06 | 88 | 88 | Yes | No | fallback_single_line | Observed matched delay | 150 | TRUE | FALSE | TRUE | FALSE |  | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 2/3 | 2026-03-16 | 2026-03 | 2026-07-05 | 2026-07 | 111 | 111 | Yes | No | fallback_single_line | Observed matched delay | 149 | TRUE | FALSE | TRUE | FALSE |  | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 2/4 | 2026-03-17 | 2026-03 | 2026-07-07 | 2026-07 | 112 | 112 | Yes | No | fallback_single_line | Observed matched delay | 148 | TRUE | FALSE | TRUE | FALSE |  | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 103/0 | 2026-03-19 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 146 | TRUE | FALSE | TRUE | FALSE |  | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 10/8 | 2026-03-22 | 2026-03 | 2026-04-20 | 2026-04 | 29 | 29 | Yes | No | exact | Observed matched delay | 143 | TRUE | TRUE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 8/2 | 2026-03-25 | 2026-03 | 2026-04-29 | 2026-04 | 35 | 35 | Yes | No | exact | Observed matched delay | 140 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 3/0B | 2026-03-26 | 2026-03 | 2026-08-05 | 2026-08 | 132 | 132 | Yes | No | exact | Observed matched delay | 139 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 7/1 | 2026-03-26 | 2026-03 | 2026-05-02 | 2026-05 | 37 | 37 | Yes | No | exact | Observed matched delay | 139 | TRUE | FALSE | TRUE | TRUE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 2/5 | 2026-03-27 | 2026-03 | 2026-07-11 | 2026-07 | 106 | 106 | Yes | No | fallback_single_line | Observed matched delay | 138 | TRUE | FALSE | TRUE | FALSE |  | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 3/0A | 2026-03-28 | 2026-03 | 2026-08-05 | 2026-08 | 130 | 130 | Yes | No | exact | Observed matched delay | 137 | TRUE | FALSE | TRUE | FALSE |  | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 5/2 | 2026-03-31 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 134 | TRUE | FALSE | TRUE | FALSE |  | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 5/1 | 2026-04-02 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 132 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 3/1 | 2026-04-04 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 130 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 8/1 | 2026-04-06 | 2026-04 | 2026-04-23 | 2026-04 | 17 | 17 | Yes | No | exact | Observed matched delay | 128 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 3/1 | 2026-04-07 | 2026-04 | 2026-08-06 | 2026-08 | 121 | 121 | Yes | No | exact | Observed matched delay | 127 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 2/1B | 2026-04-08 | 2026-04 | 2026-08-04 | 2026-08 | 118 | 118 | Yes | No | exact | Observed matched delay | 126 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 2/1 A | 2026-04-09 | 2026-04 | 2026-08-02 | 2026-08 | 115 | 115 | Yes | No | exact | Observed matched delay | 125 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 103/1 | 2026-04-10 | 2026-04 | 2026-06-27 | 2026-06 | 78 | 78 | Yes | No | exact | Observed matched delay | 124 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 8/0 | 2026-04-11 | 2026-04 | 2026-07-06 | 2026-07 | 86 | 86 | Yes | No | exact | Observed matched delay | 123 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 5/0 | 2026-04-12 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 122 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 9/3 | 2026-04-14 | 2026-04 | 2026-05-02 | 2026-05 | 18 | 18 | Yes | No | exact | Observed matched delay | 120 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 9/4 | 2026-04-15 | 2026-04 | 2026-05-04 | 2026-05 | 19 | 19 | Yes | No | exact | Observed matched delay | 119 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 99C/0 | 2026-04-15 | 2026-04 | 2026-07-16 | 2026-07 | 92 | 92 | Yes | No | exact | Observed matched delay | 119 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 4/5 | 2026-04-16 | 2026-04 | 2026-07-15 | 2026-07 | 90 | 90 | Yes | No | fallback_single_line | Observed matched delay | 118 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 3/3 | 2026-04-18 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 116 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 3/2 | 2026-04-21 | 2026-04 | 2026-08-30 | 2026-08 | 131 | 131 | Yes | No | fallback_single_line | Observed matched delay | 113 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 9/5 | 2026-04-21 | 2026-04 | 2026-05-07 | 2026-05 | 16 | 16 | Yes | No | exact | Observed matched delay | 113 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 10/14 | 2026-04-23 | 2026-04 | 2026-05-13 | 2026-05 | 20 | 20 | Yes | No | exact | Observed matched delay | 111 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 100/0 | 2026-04-24 | 2026-04 | 2026-04-24 | 2026-04 | 0 | 0 | Yes | No | exact | Observed matched delay | 110 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 10/11 | 2026-04-28 | 2026-04 | 2026-05-27 | 2026-05 | 29 | 29 | Yes | No | exact | Observed matched delay | 106 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 3/4 | 2026-04-29 | 2026-04 | 2026-07-18 | 2026-07 | 80 | 80 | Yes | No | fallback_single_line | Observed matched delay | 105 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 10/0 | 2026-05-02 | 2026-05 | 2026-05-12 | 2026-05 | 10 | 10 | Yes | No | exact | Observed matched delay | 102 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 2/0 | 2026-05-02 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 102 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 10/2 | 2026-05-03 | 2026-05 | 2026-05-08 | 2026-05 | 5 | 5 | Yes | No | exact | Observed matched delay | 101 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 155/0 | 2026-05-03 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 101 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 9/2 | 2026-05-03 | 2026-05 | 2026-05-07 | 2026-05 | 4 | 4 | Yes | No | exact | Observed matched delay | 101 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 3/5 | 2026-05-05 | 2026-05 | 2026-07-20 | 2026-07 | 76 | 76 | Yes | No | fallback_single_line | Observed matched delay | 99 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 154/1B | 2026-05-06 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 98 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 10/13 | 2026-05-08 | 2026-05 | 2026-06-07 | 2026-06 | 30 | 30 | Yes | No | exact | Observed matched delay | 96 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 154/2B | 2026-05-08 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 96 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 4/2 | 2026-05-08 | 2026-05 | 2026-07-17 | 2026-07 | 70 | 70 | Yes | No | fallback_single_line | Observed matched delay | 96 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 154/1A | 2026-05-09 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 95 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 154/2A | 2026-05-09 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 95 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 4/4 | 2026-05-10 | 2026-05 | 2026-07-17 | 2026-07 | 68 | 68 | Yes | No | fallback_single_line | Observed matched delay | 94 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 7/6 | 2026-05-11 | 2026-05 | 2026-05-16 | 2026-05 | 5 | 5 | Yes | No | exact | Observed matched delay | 93 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 13/2 | 2026-05-14 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 90 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 4/0 | 2026-05-15 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 89 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 7/8 | 2026-05-16 | 2026-05 | 2026-05-16 | 2026-05 | 0 | 0 | Yes | No | exact | Observed matched delay | 88 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 8/3 | 2026-05-17 | 2026-05 | 2026-05-24 | 2026-05 | 7 | 7 | Yes | No | exact | Observed matched delay | 87 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 4/1 | 2026-05-18 | 2026-05 | 2026-07-23 | 2026-07 | 66 | 66 | Yes | No | fallback_single_line | Observed matched delay | 86 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 4/3 | 2026-05-19 | 2026-05 | 2026-07-26 | 2026-07 | 68 | 68 | Yes | No | fallback_single_line | Observed matched delay | 85 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 8/4 | 2026-05-19 | 2026-05 | 2026-05-28 | 2026-05 | 9 | 9 | Yes | No | exact | Observed matched delay | 85 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 1/0 | 2026-05-27 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 77 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 27/0 | 2026-05-27 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 77 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 1A/0 | 2026-05-30 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 74 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 10/10 | 2026-05-31 | 2026-05 | 2026-06-16 | 2026-06 | 16 | 16 | Yes | No | exact | Observed matched delay | 73 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 3A/1 | 2026-05-31 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 73 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 7/2 | 2026-06-01 | 2026-06 | 2026-06-27 | 2026-06 | 26 | 26 | Yes | No | exact | Observed matched delay | 72 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 5/3 | 2026-06-03 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 70 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 3A/0 | 2026-06-05 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 68 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 5/4 | 2026-06-05 | 2026-06 | 2026-08-03 | 2026-08 | 59 | 59 | Yes | No | exact | Observed matched delay | 68 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 9/0 | 2026-06-05 | 2026-06 | 2026-06-10 | 2026-06 | 5 | 5 | Yes | No | exact | Observed matched delay | 68 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 10/1 | 2026-06-09 | 2026-06 | 2026-07-06 | 2026-07 | 27 | 27 | Yes | No | exact | Observed matched delay | 64 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 5/5 | 2026-06-09 | 2026-06 | 2026-07-15 | 2026-07 | 36 | 36 | Yes | No | exact | Observed matched delay | 64 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 10/4 | 2026-06-15 | 2026-06 | 2026-06-21 | 2026-06 | 6 | 6 | Yes | No | exact | Observed matched delay | 58 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 3B/0 | 2026-06-15 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 58 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 5/0 | 2026-06-15 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 58 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 56/3 | 2026-06-17 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 56 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 7/3 | 2026-06-19 | 2026-06 | 2026-07-13 | 2026-07 | 24 | 24 | Yes | No | exact | Observed matched delay | 54 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 3/0 | 2026-06-24 | 2026-06 | 2026-08-01 | 2026-08 | 38 | 38 | Yes | No | fallback_single_line | Observed matched delay | 49 | TRUE | FALSE | FALSE | TRUE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 5/2 | 2026-06-24 | 2026-06 | 2026-08-07 | 2026-08 | 44 | 44 | Yes | No | exact | Observed matched delay | 49 | TRUE | FALSE | FALSE | TRUE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 10/9 | 2026-06-27 | 2026-06 | 2025-07-10 | 2025-07 | -352 |  | Yes | Yes | exact | Negative delay excluded | 46 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 107/1 | 2026-06-28 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 45 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 43/0 | 2026-06-28 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 45 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 5A/0 | 2026-06-29 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 44 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 121/0 | 2026-06-30 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 43 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 42/0 | 2026-06-30 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 43 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 41/3 | 2026-07-04 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 39 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 6D/5 | 2026-07-06 | 2026-07 | 2026-07-15 | 2026-07 | 9 | 9 | Yes | No | exact | Observed matched delay | 37 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 9A/0 | 2026-07-10 | 2026-07 | 2026-07-16 | 2026-07 | 6 | 6 | Yes | No | exact | Observed matched delay | 33 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 42/1 | 2026-07-11 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 32 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 5/6 | 2026-07-11 | 2026-07 | 2026-08-11 | 2026-08 | 31 | 31 | Yes | No | exact | Observed matched delay | 32 | TRUE | FALSE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 5/1 | 2026-07-13 | 2026-07 | 2026-08-07 | 2026-08 | 25 | 25 | Yes | No | exact | Observed matched delay | 30 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 7/0 | 2026-07-16 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 27 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 41/1 | 2026-07-17 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 26 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 44/0 | 2026-07-18 | 2026-07 | 2026-08-05 | 2026-08 | 18 | 18 | Yes | No | exact | Observed matched delay | 25 | FALSE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) | MAIN | MAIN | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Erection Compiled
TB 507 | 5xx | Private | tb507 | 122/1 | 2026-07-20 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 23 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 122/0 | 2026-07-24 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 19 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 102/0 | 2026-07-28 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 15 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 39/4 | 2026-07-28 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 15 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 2A/0 | 2026-07-30 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 13 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | 765kV |  | TB 507 - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 45/3 | 2026-07-31 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 12 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 5A/0 | 2026-07-31 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 12 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 5B/0 | 2026-08-03 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 9 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 39/3 | 2026-08-04 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 8 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 507 | 5xx | Private | tb507 | 40/0 | 2026-08-06 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 6 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | MAIN |  | TB 507 [MAIN] - DPR - 2026-08-11.xlsx | Foundation
TB 605 | 6xx | Private | tb605 | 29/5 | 2025-08-11 | 2025-08 | 2025-11-27 | 2025-11 | 108 | 108 | Yes | No | exact | Observed matched delay | 366 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 29/4 | 2025-09-06 | 2025-09 | 2025-12-05 | 2025-12 | 90 | 90 | Yes | No | exact | Observed matched delay | 340 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 27/0 | 2025-09-20 | 2025-09 | 2025-12-11 | 2025-12 | 82 | 82 | Yes | No | exact | Observed matched delay | 326 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 29/3 | 2025-09-24 | 2025-09 | 2026-05-05 | 2026-05 | 223 | 223 | Yes | No | exact | Observed matched delay | 322 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 29/1 | 2025-10-10 | 2025-10 | 2026-03-09 | 2026-03 | 150 | 150 | Yes | No | exact | Observed matched delay | 306 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 18/0 | 2025-10-16 | 2025-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 300 | TRUE | FALSE | TRUE | FALSE |  | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | 29/6 | 2025-10-16 | 2025-10 | 2025-12-22 | 2025-12 | 67 | 67 | Yes | No | exact | Observed matched delay | 300 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 117/1 | 2025-10-20 | 2025-10 | 2026-02-07 | 2026-02 | 110 | 110 | Yes | No | exact | Observed matched delay | 296 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 71/3 | 2025-10-23 | 2025-10 | 2026-05-05 | 2026-05 | 194 | 194 | Yes | No | exact | Observed matched delay | 293 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 92/3 | 2025-10-27 | 2025-10 | 2026-02-12 | 2026-02 | 108 | 108 | Yes | No | exact | Observed matched delay | 289 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 22/1 | 2025-10-28 | 2025-10 | 2026-05-30 | 2026-05 | 214 | 214 | Yes | No | exact | Observed matched delay | 288 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 72/2 | 2025-10-28 | 2025-10 | 2026-04-25 | 2026-04 | 179 | 179 | Yes | No | exact | Observed matched delay | 288 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 92/2 | 2025-10-28 | 2025-10 | 2026-02-02 | 2026-02 | 97 | 97 | Yes | No | exact | Observed matched delay | 288 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 117/3 | 2025-10-29 | 2025-10 | 2026-02-03 | 2026-02 | 97 | 97 | Yes | No | exact | Observed matched delay | 287 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 31/1 | 2025-10-30 | 2025-10 | 2026-01-25 | 2026-01 | 87 | 87 | Yes | No | exact | Observed matched delay | 286 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 21/1 | 2025-10-31 | 2025-10 | 2026-06-22 | 2026-06 | 234 | 234 | Yes | No | exact | Observed matched delay | 285 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 22/0 | 2025-10-31 | 2025-10 |  |  |  |  | No | No |  | Unmatched/right-censored | 285 | TRUE | FALSE | TRUE | FALSE |  | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | 89/1 | 2025-10-31 | 2025-10 | 2026-02-02 | 2026-02 | 94 | 94 | Yes | No | exact | Observed matched delay | 285 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 93/1 | 2025-10-31 | 2025-10 | 2026-05-08 | 2026-05 | 189 | 189 | Yes | No | exact | Observed matched delay | 285 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 117/2 | 2025-11-04 | 2025-11 | 2026-02-11 | 2026-02 | 99 | 99 | Yes | No | exact | Observed matched delay | 281 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 93/2 | 2025-11-04 | 2025-11 | 2026-02-17 | 2026-02 | 105 | 105 | Yes | No | exact | Observed matched delay | 281 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 118/1 | 2025-11-06 | 2025-11 | 2026-02-21 | 2026-02 | 107 | 107 | Yes | No | exact | Observed matched delay | 279 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 74/0 | 2025-11-06 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 279 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 95/2 | 2025-11-08 | 2025-11 | 2026-02-08 | 2026-02 | 92 | 92 | Yes | No | exact | Observed matched delay | 277 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 72/0 | 2025-11-09 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 276 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 23/1 | 2025-11-10 | 2025-11 | 2026-02-05 | 2026-02 | 87 | 87 | Yes | No | exact | Observed matched delay | 275 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 92/1 | 2025-11-10 | 2025-11 | 2026-02-25 | 2026-02 | 107 | 107 | Yes | No | exact | Observed matched delay | 275 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 95/3 | 2025-11-10 | 2025-11 | 2026-02-06 | 2026-02 | 88 | 88 | Yes | No | exact | Observed matched delay | 275 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 31/3 | 2025-11-11 | 2025-11 | 2026-02-06 | 2026-02 | 87 | 87 | Yes | No | exact | Observed matched delay | 274 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 97/2 | 2025-11-12 | 2025-11 | 2026-02-05 | 2026-02 | 85 | 85 | Yes | No | exact | Observed matched delay | 273 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 22/2 | 2025-11-13 | 2025-11 | 2026-06-01 | 2026-06 | 200 | 200 | Yes | No | exact | Observed matched delay | 272 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 97/1 | 2025-11-13 | 2025-11 | 2026-02-09 | 2026-02 | 88 | 88 | Yes | No | exact | Observed matched delay | 272 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 76/2 | 2025-11-14 | 2025-11 | 2026-02-22 | 2026-02 | 100 | 100 | Yes | No | exact | Observed matched delay | 271 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 131/1 | 2025-11-15 | 2025-11 | 2026-02-27 | 2026-02 | 104 | 104 | Yes | No | exact | Observed matched delay | 270 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 95/1 | 2025-11-15 | 2025-11 | 2026-03-12 | 2026-03 | 117 | 117 | Yes | No | exact | Observed matched delay | 270 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP118 | 2025-11-16 | 2025-11 | 2026-04-27 | 2026-04 | 162 | 162 | Yes | No | exact | Observed matched delay | 269 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 15/1 | 2025-11-17 | 2025-11 | 2025-12-25 | 2025-12 | 38 | 38 | Yes | No | exact | Observed matched delay | 268 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 76/1 | 2025-11-18 | 2025-11 | 2026-02-17 | 2026-02 | 91 | 91 | Yes | No | exact | Observed matched delay | 267 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 131/3 | 2025-11-19 | 2025-11 | 2026-02-23 | 2026-02 | 96 | 96 | Yes | No | exact | Observed matched delay | 266 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 15/2 | 2025-11-19 | 2025-11 | 2026-01-07 | 2026-01 | 49 | 49 | Yes | No | exact | Observed matched delay | 266 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP93 | 2025-11-19 | 2025-11 | 2026-02-20 | 2026-02 | 93 | 93 | Yes | No | exact | Observed matched delay | 266 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 95/4 | 2025-11-20 | 2025-11 | 2026-02-11 | 2026-02 | 83 | 83 | Yes | No | exact | Observed matched delay | 265 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 97/3 | 2025-11-20 | 2025-11 | 2026-02-12 | 2026-02 | 84 | 84 | Yes | No | exact | Observed matched delay | 265 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP90 | 2025-11-22 | 2025-11 | 2026-05-16 | 2026-05 | 175 | 175 | Yes | No | exact | Observed matched delay | 263 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 17/0 | 2025-11-23 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 262 | TRUE | FALSE | TRUE | FALSE |  | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | 27/1 | 2025-11-23 | 2025-11 | 2026-05-16 | 2026-05 | 174 | 174 | Yes | No | exact | Observed matched delay | 262 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 131/2 | 2025-11-24 | 2025-11 | 2026-04-30 | 2026-04 | 157 | 157 | Yes | No | exact | Observed matched delay | 261 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 30/3 | 2025-11-24 | 2025-11 | 2025-12-29 | 2025-12 | 35 | 35 | Yes | No | exact | Observed matched delay | 261 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP98 | 2025-11-24 | 2025-11 | 2026-02-22 | 2026-02 | 90 | 90 | Yes | No | exact | Observed matched delay | 261 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 98/1 | 2025-11-26 | 2025-11 | 2026-02-17 | 2026-02 | 83 | 83 | Yes | No | exact | Observed matched delay | 259 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP32 | 2025-11-26 | 2025-11 | 2026-02-13 | 2026-02 | 79 | 79 | Yes | No | exact | Observed matched delay | 259 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP94 | 2025-11-27 | 2025-11 | 2026-02-17 | 2026-02 | 82 | 82 | Yes | No | exact | Observed matched delay | 258 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 103/1 | 2025-11-28 | 2025-11 | 2026-03-02 | 2026-03 | 94 | 94 | Yes | No | exact | Observed matched delay | 257 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 30/5 | 2025-11-29 | 2025-11 | 2026-01-09 | 2026-01 | 41 | 41 | Yes | No | exact | Observed matched delay | 256 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP96 | 2025-11-29 | 2025-11 | 2026-02-13 | 2026-02 | 76 | 76 | Yes | No | exact | Observed matched delay | 256 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 131/4 | 2025-11-30 | 2025-11 | 2026-02-12 | 2026-02 | 74 | 74 | Yes | No | exact | Observed matched delay | 255 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 20/0 | 2025-11-30 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 255 | TRUE | FALSE | TRUE | FALSE |  | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | 40/1 | 2025-11-30 | 2025-11 | 2026-02-16 | 2026-02 | 78 | 78 | Yes | No | exact | Observed matched delay | 255 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP116 | 2025-11-30 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 255 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP87 | 2025-11-30 | 2025-11 | 2026-07-05 | 2026-07 | 217 | 217 | Yes | No | fallback_single_line | Observed matched delay | 255 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP99 | 2025-11-30 | 2025-11 | 2026-02-26 | 2026-02 | 88 | 88 | Yes | No | exact | Observed matched delay | 255 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP75 | 2025-12-01 | 2025-12 | 2026-04-21 | 2026-04 | 141 | 141 | Yes | No | exact | Observed matched delay | 254 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 40/0 | 2025-12-03 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 252 | TRUE | FALSE | TRUE | FALSE |  | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | 104/1 | 2025-12-04 | 2025-12 | 2026-03-23 | 2026-03 | 109 | 109 | Yes | No | exact | Observed matched delay | 251 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP28 | 2025-12-04 | 2025-12 | 2026-05-19 | 2026-05 | 166 | 166 | Yes | No | exact | Observed matched delay | 251 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 82/2 | 2025-12-05 | 2025-12 | 2026-05-03 | 2026-05 | 149 | 149 | Yes | No | exact | Observed matched delay | 250 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 18/1 | 2025-12-06 | 2025-12 | 2026-03-05 | 2026-03 | 89 | 89 | Yes | No | exact | Observed matched delay | 249 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 76/3 | 2025-12-06 | 2025-12 | 2026-03-05 | 2026-03 | 89 | 89 | Yes | No | exact | Observed matched delay | 249 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 99/1 | 2025-12-06 | 2025-12 | 2026-04-19 | 2026-04 | 134 | 134 | Yes | No | exact | Observed matched delay | 249 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP100 | 2025-12-07 | 2025-12 | 2026-03-14 | 2026-03 | 97 | 97 | Yes | No | exact | Observed matched delay | 248 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP95 | 2025-12-07 | 2025-12 | 2026-02-21 | 2026-02 | 76 | 76 | Yes | No | exact | Observed matched delay | 248 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 23/0 | 2025-12-09 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 246 | TRUE | FALSE | TRUE | FALSE |  | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP117 | 2025-12-09 | 2025-12 | 2026-02-24 | 2026-02 | 77 | 77 | Yes | No | exact | Observed matched delay | 246 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 29/0 | 2025-12-10 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 245 | TRUE | FALSE | TRUE | FALSE |  | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | 77/2 | 2025-12-10 | 2025-12 | 2026-03-22 | 2026-03 | 102 | 102 | Yes | No | exact | Observed matched delay | 245 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 82/1 | 2025-12-10 | 2025-12 | 2026-04-17 | 2026-04 | 128 | 128 | Yes | No | exact | Observed matched delay | 245 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 30/2 | 2025-12-12 | 2025-12 | 2026-05-15 | 2026-05 | 154 | 154 | Yes | No | exact | Observed matched delay | 243 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 19/2 | 2025-12-13 | 2025-12 | 2026-02-01 | 2026-02 | 50 | 50 | Yes | No | exact | Observed matched delay | 242 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 39/2 | 2025-12-13 | 2025-12 | 2026-02-24 | 2026-02 | 73 | 73 | Yes | No | exact | Observed matched delay | 242 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP104 | 2025-12-13 | 2025-12 | 2026-03-20 | 2026-03 | 97 | 97 | Yes | No | exact | Observed matched delay | 242 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP77 | 2025-12-13 | 2025-12 | 2026-03-11 | 2026-03 | 88 | 88 | Yes | No | exact | Observed matched delay | 242 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP106 | 2025-12-15 | 2025-12 | 2026-03-01 | 2026-03 | 76 | 76 | Yes | No | exact | Observed matched delay | 240 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 77/1 | 2025-12-16 | 2025-12 | 2026-03-17 | 2026-03 | 91 | 91 | Yes | No | exact | Observed matched delay | 239 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 85/1 | 2025-12-16 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 239 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP135 | 2025-12-16 | 2025-12 | 2026-04-18 | 2026-04 | 123 | 123 | Yes | No | exact | Observed matched delay | 239 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 106/1 | 2025-12-17 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 238 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 130/2 | 2025-12-17 | 2025-12 | 2026-03-08 | 2026-03 | 81 | 81 | Yes | No | exact | Observed matched delay | 238 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 102/1 | 2025-12-18 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 237 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP103 | 2025-12-18 | 2025-12 | 2026-03-26 | 2026-03 | 98 | 98 | Yes | No | exact | Observed matched delay | 237 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 136/1 | 2025-12-19 | 2025-12 | 2026-03-21 | 2026-03 | 92 | 92 | Yes | No | exact | Observed matched delay | 236 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 30/4 | 2025-12-19 | 2025-12 | 2026-01-18 | 2026-01 | 30 | 30 | Yes | No | exact | Observed matched delay | 236 | TRUE | TRUE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 116/1 | 2025-12-20 | 2025-12 | 2026-03-07 | 2026-03 | 77 | 77 | Yes | No | exact | Observed matched delay | 235 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 130/1 | 2025-12-20 | 2025-12 | 2026-05-15 | 2026-05 | 146 | 146 | Yes | No | exact | Observed matched delay | 235 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 135/2 | 2025-12-21 | 2025-12 | 2026-06-12 | 2026-06 | 173 | 173 | Yes | No | exact | Observed matched delay | 234 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 23/5 | 2025-12-21 | 2025-12 | 2026-02-15 | 2026-02 | 56 | 56 | Yes | No | exact | Observed matched delay | 234 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP45 | 2025-12-23 | 2025-12 | 2026-05-15 | 2026-05 | 143 | 143 | Yes | No | exact | Observed matched delay | 232 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 131/6 | 2025-12-24 | 2025-12 | 2026-03-13 | 2026-03 | 79 | 79 | Yes | No | exact | Observed matched delay | 231 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 139/1 | 2025-12-24 | 2025-12 | 2026-06-21 | 2026-06 | 179 | 179 | Yes | No | exact | Observed matched delay | 231 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP19 | 2025-12-24 | 2025-12 | 2026-02-13 | 2026-02 | 51 | 51 | Yes | No | exact | Observed matched delay | 231 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP85 | 2025-12-24 | 2025-12 | 2026-04-04 | 2026-04 | 101 | 101 | Yes | No | exact | Observed matched delay | 231 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 46/1 | 2025-12-25 | 2025-12 | 2026-03-23 | 2026-03 | 88 | 88 | Yes | No | exact | Observed matched delay | 230 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP43 | 2025-12-25 | 2025-12 | 2026-04-21 | 2026-04 | 117 | 117 | Yes | No | exact | Observed matched delay | 230 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP80 | 2025-12-25 | 2025-12 | 2026-03-28 | 2026-03 | 93 | 93 | Yes | No | exact | Observed matched delay | 230 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 138/1 | 2025-12-26 | 2025-12 | 2026-06-25 | 2026-06 | 181 | 181 | Yes | No | exact | Observed matched delay | 229 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 156/4 | 2025-12-26 | 2025-12 | 2026-03-07 | 2026-03 | 71 | 71 | Yes | No | exact | Observed matched delay | 229 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 131/5 | 2025-12-27 | 2025-12 | 2026-02-17 | 2026-02 | 52 | 52 | Yes | No | exact | Observed matched delay | 228 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 150/1 | 2025-12-27 | 2025-12 | 2026-04-22 | 2026-04 | 116 | 116 | Yes | No | exact | Observed matched delay | 228 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 31/2 | 2025-12-27 | 2025-12 | 2026-02-01 | 2026-02 | 36 | 36 | Yes | No | exact | Observed matched delay | 228 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 137/1 | 2025-12-28 | 2025-12 | 2026-05-05 | 2026-05 | 128 | 128 | Yes | No | exact | Observed matched delay | 227 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 135/1 | 2025-12-29 | 2025-12 | 2026-04-04 | 2026-04 | 96 | 96 | Yes | No | exact | Observed matched delay | 226 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP102 | 2025-12-29 | 2025-12 | 2026-03-11 | 2026-03 | 72 | 72 | Yes | No | exact | Observed matched delay | 226 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 156/3 | 2025-12-30 | 2025-12 | 2026-04-10 | 2026-04 | 101 | 101 | Yes | No | exact | Observed matched delay | 225 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 80/1 | 2025-12-30 | 2025-12 | 2026-06-15 | 2026-06 | 167 | 167 | Yes | No | exact | Observed matched delay | 225 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 86/1 | 2025-12-30 | 2025-12 | 2026-05-14 | 2026-05 | 135 | 135 | Yes | No | exact | Observed matched delay | 225 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 132/1 | 2025-12-31 | 2025-12 | 2026-03-02 | 2026-03 | 61 | 61 | Yes | No | exact | Observed matched delay | 224 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 138/2 | 2025-12-31 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 224 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 23/4 | 2025-12-31 | 2025-12 | 2026-02-20 | 2026-02 | 51 | 51 | Yes | No | exact | Observed matched delay | 224 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP33 | 2025-12-31 | 2025-12 | 2026-03-12 | 2026-03 | 71 | 71 | Yes | No | exact | Observed matched delay | 224 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 150/2 | 2026-01-04 | 2026-01 | 2026-04-12 | 2026-04 | 98 | 98 | Yes | No | exact | Observed matched delay | 220 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 43/1 | 2026-01-04 | 2026-01 | 2026-04-06 | 2026-04 | 92 | 92 | Yes | No | exact | Observed matched delay | 220 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP146 | 2026-01-05 | 2026-01 | 2026-04-04 | 2026-04 | 89 | 89 | Yes | No | exact | Observed matched delay | 219 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 69/3 | 2026-01-07 | 2026-01 | 2026-03-17 | 2026-03 | 69 | 69 | Yes | No | exact | Observed matched delay | 217 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 156/2 | 2026-01-08 | 2026-01 | 2026-04-04 | 2026-04 | 86 | 86 | Yes | No | exact | Observed matched delay | 216 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 18/2 | 2026-01-08 | 2026-01 | 2026-02-24 | 2026-02 | 47 | 47 | Yes | No | exact | Observed matched delay | 216 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP26 | 2026-01-08 | 2026-01 | 2026-02-22 | 2026-02 | 45 | 45 | Yes | No | exact | Observed matched delay | 216 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 155/1 | 2026-01-09 | 2026-01 | 2026-04-14 | 2026-04 | 95 | 95 | Yes | No | exact | Observed matched delay | 215 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 31/4 | 2026-01-09 | 2026-01 | 2026-02-09 | 2026-02 | 31 | 31 | Yes | No | exact | Observed matched delay | 215 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 46/3 | 2026-01-09 | 2026-01 | 2026-04-18 | 2026-04 | 99 | 99 | Yes | No | exact | Observed matched delay | 215 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 137/2 | 2026-01-10 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 214 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 152/1 | 2026-01-11 | 2026-01 | 2026-04-16 | 2026-04 | 95 | 95 | Yes | No | exact | Observed matched delay | 213 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 90/1 | 2026-01-11 | 2026-01 | 2026-05-10 | 2026-05 | 119 | 119 | Yes | No | exact | Observed matched delay | 213 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP131 | 2026-01-11 | 2026-01 | 2026-06-02 | 2026-06 | 142 | 142 | Yes | No | exact | Observed matched delay | 213 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 43/2 | 2026-01-12 | 2026-01 | 2026-04-02 | 2026-04 | 80 | 80 | Yes | No | exact | Observed matched delay | 212 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 87/2 | 2026-01-12 | 2026-01 | 2026-02-25 | 2026-02 | 44 | 44 | Yes | No | exact | Observed matched delay | 212 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 152/2 | 2026-01-16 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 208 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 90/2 | 2026-01-16 | 2026-01 | 2026-03-09 | 2026-03 | 52 | 52 | Yes | No | exact | Observed matched delay | 208 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP147 | 2026-01-16 | 2026-01 | 2026-04-26 | 2026-04 | 100 | 100 | Yes | No | exact | Observed matched delay | 208 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP157 | 2026-01-17 | 2026-01 | 2026-03-13 | 2026-03 | 55 | 55 | Yes | No | exact | Observed matched delay | 207 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP154 | 2026-01-18 | 2026-01 | 2026-06-16 | 2026-06 | 149 | 149 | Yes | No | exact | Observed matched delay | 206 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP31 | 2026-01-18 | 2026-01 | 2026-03-29 | 2026-03 | 70 | 70 | Yes | No | exact | Observed matched delay | 206 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 145/2 | 2026-01-20 | 2026-01 | 2026-04-19 | 2026-04 | 89 | 89 | Yes | No | exact | Observed matched delay | 204 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 19/1 | 2026-01-20 | 2026-01 | 2026-02-08 | 2026-02 | 19 | 19 | Yes | No | exact | Observed matched delay | 204 | TRUE | TRUE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP129 | 2026-01-20 | 2026-01 | 2026-05-05 | 2026-05 | 105 | 105 | Yes | No | exact | Observed matched delay | 204 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP138 | 2026-01-20 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 204 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 25/2 | 2026-01-21 | 2026-01 | 2026-03-05 | 2026-03 | 43 | 43 | Yes | No | exact | Observed matched delay | 203 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 44/3 | 2026-01-21 | 2026-01 | 2026-03-08 | 2026-03 | 46 | 46 | Yes | No | exact | Observed matched delay | 203 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 45/2 | 2026-01-21 | 2026-01 | 2026-02-17 | 2026-02 | 27 | 27 | Yes | No | exact | Observed matched delay | 203 | TRUE | TRUE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 71/2 | 2026-01-21 | 2026-01 | 2026-02-27 | 2026-02 | 37 | 37 | Yes | No | exact | Observed matched delay | 203 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 156/1 | 2026-01-22 | 2026-01 | 2026-04-27 | 2026-04 | 95 | 95 | Yes | No | exact | Observed matched delay | 202 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 31/5 | 2026-01-22 | 2026-01 | 2026-03-07 | 2026-03 | 44 | 44 | Yes | No | exact | Observed matched delay | 202 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 69/2 | 2026-01-22 | 2026-01 | 2026-03-21 | 2026-03 | 58 | 58 | Yes | No | exact | Observed matched delay | 202 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP115 | 2026-01-22 | 2026-01 | 2026-02-16 | 2026-02 | 25 | 25 | Yes | No | exact | Observed matched delay | 202 | TRUE | TRUE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP16 | 2026-01-25 | 2026-01 | 2026-04-15 | 2026-04 | 80 | 80 | Yes | No | exact | Observed matched delay | 199 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 69/1 | 2026-01-27 | 2026-01 | 2026-03-29 | 2026-03 | 61 | 61 | Yes | No | exact | Observed matched delay | 197 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 155/2 | 2026-01-30 | 2026-01 | 2026-04-18 | 2026-04 | 78 | 78 | Yes | No | exact | Observed matched delay | 194 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 32/1 | 2026-01-30 | 2026-01 | 2026-02-20 | 2026-02 | 21 | 21 | Yes | No | exact | Observed matched delay | 194 | TRUE | TRUE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 115/1 | 2026-01-31 | 2026-01 | 2026-03-26 | 2026-03 | 54 | 54 | Yes | No | exact | Observed matched delay | 193 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 151/1 | 2026-01-31 | 2026-01 | 2026-04-10 | 2026-04 | 69 | 69 | Yes | No | exact | Observed matched delay | 193 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 155/3 | 2026-01-31 | 2026-01 | 2026-04-22 | 2026-04 | 81 | 81 | Yes | No | exact | Observed matched delay | 193 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP30 | 2026-01-31 | 2026-01 | 2026-04-04 | 2026-04 | 63 | 63 | Yes | No | exact | Observed matched delay | 193 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 153/0 | 2026-02-05 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 188 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 45/1 | 2026-02-05 | 2026-02 | 2026-03-16 | 2026-03 | 39 | 39 | Yes | No | exact | Observed matched delay | 188 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP139 | 2026-02-06 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 187 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 151/2 | 2026-02-07 | 2026-02 | 2026-05-07 | 2026-05 | 89 | 89 | Yes | No | exact | Observed matched delay | 186 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 44/2 | 2026-02-07 | 2026-02 | 2026-03-12 | 2026-03 | 33 | 33 | Yes | No | exact | Observed matched delay | 186 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP15 | 2026-02-08 | 2026-02 | 2026-06-26 | 2026-06 | 138 | 138 | Yes | No | exact | Observed matched delay | 185 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP97 | 2026-02-08 | 2026-02 | 2026-03-01 | 2026-03 | 21 | 21 | Yes | No | exact | Observed matched delay | 185 | TRUE | TRUE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP155 | 2026-02-09 | 2026-02 | 2026-05-24 | 2026-05 | 104 | 104 | Yes | No | exact | Observed matched delay | 184 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 136/2 | 2026-02-11 | 2026-02 | 2026-04-13 | 2026-04 | 61 | 61 | Yes | No | exact | Observed matched delay | 182 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 152/4 | 2026-02-12 | 2026-02 | 2026-05-14 | 2026-05 | 91 | 91 | Yes | No | exact | Observed matched delay | 181 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP130 | 2026-02-12 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 181 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 153/1 | 2026-02-13 | 2026-02 | 2026-05-10 | 2026-05 | 86 | 86 | Yes | No | exact | Observed matched delay | 180 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 25/1 | 2026-02-13 | 2026-02 | 2026-03-12 | 2026-03 | 27 | 27 | Yes | No | exact | Observed matched delay | 180 | TRUE | TRUE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP92 | 2026-02-13 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 180 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 50A/7 | 2026-02-14 | 2026-02 | 2026-04-20 | 2026-04 | 65 | 65 | Yes | No | exact | Observed matched delay | 179 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP156 | 2026-02-14 | 2026-02 | 2026-03-21 | 2026-03 | 35 | 35 | Yes | No | exact | Observed matched delay | 179 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 136/3 | 2026-02-15 | 2026-02 | 2026-04-25 | 2026-04 | 69 | 69 | Yes | No | exact | Observed matched delay | 178 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 157/1 | 2026-02-15 | 2026-02 | 2026-03-29 | 2026-03 | 42 | 42 | Yes | No | exact | Observed matched delay | 178 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 72/1 | 2026-02-17 | 2026-02 | 2026-04-21 | 2026-04 | 63 | 63 | Yes | No | exact | Observed matched delay | 176 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 153/2 | 2026-02-18 | 2026-02 | 2026-05-19 | 2026-05 | 90 | 90 | Yes | No | exact | Observed matched delay | 175 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP150 | 2026-02-18 | 2026-02 | 2026-06-09 | 2026-06 | 111 | 111 | Yes | No | exact | Observed matched delay | 175 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP70 | 2026-02-18 | 2026-02 | 2026-03-31 | 2026-03 | 41 | 41 | Yes | No | exact | Observed matched delay | 175 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP111 | 2026-02-19 | 2026-02 | 2026-03-13 | 2026-03 | 22 | 22 | Yes | No | exact | Observed matched delay | 174 | TRUE | TRUE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 136/4 | 2026-02-20 | 2026-02 | 2026-05-28 | 2026-05 | 97 | 97 | Yes | No | exact | Observed matched delay | 173 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP12 | 2026-02-20 | 2026-02 | 2026-07-14 | 2026-07 | 144 | 144 | Yes | No | exact | Observed matched delay | 173 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP44 | 2026-02-20 | 2026-02 | 2026-03-24 | 2026-03 | 32 | 32 | Yes | No | exact | Observed matched delay | 173 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP46 | 2026-02-20 | 2026-02 | 2026-05-10 | 2026-05 | 79 | 79 | Yes | No | exact | Observed matched delay | 173 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 70/2 | 2026-02-21 | 2026-02 | 2026-04-13 | 2026-04 | 51 | 51 | Yes | No | exact | Observed matched delay | 172 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP68 | 2026-02-21 | 2026-02 | 2026-03-24 | 2026-03 | 31 | 31 | Yes | No | exact | Observed matched delay | 172 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP132 | 2026-02-24 | 2026-02 | 2026-06-03 | 2026-06 | 99 | 99 | Yes | No | exact | Observed matched delay | 169 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 50A/8 | 2026-02-25 | 2026-02 | 2026-04-26 | 2026-04 | 60 | 60 | Yes | No | exact | Observed matched delay | 168 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP25 | 2026-02-25 | 2026-02 | 2026-03-16 | 2026-03 | 19 | 19 | Yes | No | exact | Observed matched delay | 168 | TRUE | TRUE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP79 | 2026-02-25 | 2026-02 | 2026-04-06 | 2026-04 | 40 | 40 | Yes | No | exact | Observed matched delay | 168 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 67/3 | 2026-02-26 | 2026-02 | 2026-05-08 | 2026-05 | 71 | 71 | Yes | No | exact | Observed matched delay | 167 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 70/1 | 2026-02-26 | 2026-02 | 2026-06-26 | 2026-06 | 120 | 120 | Yes | No | exact | Observed matched delay | 167 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 44/1 | 2026-02-27 | 2026-02 | 2026-03-16 | 2026-03 | 17 | 17 | Yes | No | exact | Observed matched delay | 166 | TRUE | TRUE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP137 | 2026-02-27 | 2026-02 | 2026-06-05 | 2026-06 | 98 | 98 | Yes | No | exact | Observed matched delay | 166 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP21 | 2026-02-27 | 2026-02 | 2026-05-28 | 2026-05 | 90 | 90 | Yes | No | exact | Observed matched delay | 166 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP91 | 2026-02-27 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 166 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 145/1 | 2026-02-28 | 2026-02 | 2026-03-31 | 2026-03 | 31 | 31 | Yes | No | exact | Observed matched delay | 165 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP114 | 2026-02-28 | 2026-02 | 2026-04-12 | 2026-04 | 43 | 43 | Yes | No | exact | Observed matched delay | 165 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP159 | 2026-02-28 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 165 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP69 | 2026-03-02 | 2026-03 | 2026-04-17 | 2026-04 | 46 | 46 | Yes | No | exact | Observed matched delay | 163 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 46/5 | 2026-03-05 | 2026-03 | 2026-04-05 | 2026-04 | 31 | 31 | Yes | No | exact | Observed matched delay | 160 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 50A/3 | 2026-03-06 | 2026-03 | 2026-04-28 | 2026-04 | 53 | 53 | Yes | No | exact | Observed matched delay | 159 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 29/2 | 2026-03-07 | 2026-03 | 2026-04-19 | 2026-04 | 43 | 43 | Yes | No | exact | Observed matched delay | 158 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 43/3 | 2026-03-08 | 2026-03 | 2026-03-30 | 2026-03 | 22 | 22 | Yes | No | exact | Observed matched delay | 157 | TRUE | TRUE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP14 | 2026-03-08 | 2026-03 | 2026-07-18 | 2026-07 | 132 | 132 | Yes | No | exact | Observed matched delay | 157 | TRUE | FALSE | TRUE | FALSE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 33/2 | 2026-03-09 | 2026-03 | 2026-03-24 | 2026-03 | 15 | 15 | Yes | No | exact | Observed matched delay | 156 | TRUE | TRUE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP149 | 2026-03-10 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 155 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 46/4 | 2026-03-11 | 2026-03 | 2026-03-30 | 2026-03 | 19 | 19 | Yes | No | exact | Observed matched delay | 154 | TRUE | TRUE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 67/2 | 2026-03-13 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 152 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP127 | 2026-03-15 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 150 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP24 | 2026-03-15 | 2026-03 | 2026-03-25 | 2026-03 | 10 | 10 | Yes | No | exact | Observed matched delay | 150 | TRUE | TRUE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP148 | 2026-03-16 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 149 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP136 | 2026-03-18 | 2026-03 | 2026-05-20 | 2026-05 | 63 | 63 | Yes | No | exact | Observed matched delay | 147 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 67/1 | 2026-03-19 | 2026-03 | 2026-04-11 | 2026-04 | 23 | 23 | Yes | No | exact | Observed matched delay | 146 | TRUE | TRUE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 43/4 | 2026-03-21 | 2026-03 | 2026-04-10 | 2026-04 | 20 | 20 | Yes | No | exact | Observed matched delay | 144 | TRUE | TRUE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP71 | 2026-03-23 | 2026-03 | 2026-06-21 | 2026-06 | 90 | 90 | Yes | No | exact | Observed matched delay | 142 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP145 | 2026-03-25 | 2026-03 | 2026-05-05 | 2026-05 | 41 | 41 | Yes | No | exact | Observed matched delay | 140 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP152 | 2026-03-26 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 139 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 46/2 | 2026-03-28 | 2026-03 | 2026-04-14 | 2026-04 | 17 | 17 | Yes | No | exact | Observed matched delay | 137 | TRUE | TRUE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP108 | 2026-03-28 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 137 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 15/3 | 2026-03-30 | 2026-03 | 2026-04-12 | 2026-04 | 13 | 13 | Yes | No | exact | Observed matched delay | 135 | TRUE | TRUE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 38/1 | 2026-03-30 | 2026-03 | 2026-04-30 | 2026-04 | 31 | 31 | Yes | No | exact | Observed matched delay | 135 | TRUE | FALSE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP124 | 2026-03-30 | 2026-03 | 2026-06-08 | 2026-06 | 70 | 70 | Yes | No | exact | Observed matched delay | 135 | TRUE | FALSE | TRUE | FALSE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP67 | 2026-03-30 | 2026-03 | 2026-05-22 | 2026-05 | 53 | 53 | Yes | No | exact | Observed matched delay | 135 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 152/3 | 2026-03-31 | 2026-03 | 2026-05-16 | 2026-05 | 46 | 46 | Yes | No | exact | Observed matched delay | 134 | TRUE | FALSE | TRUE | TRUE |  | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 42/3 | 2026-03-31 | 2026-03 | 2026-04-30 | 2026-04 | 30 | 30 | Yes | No | exact | Observed matched delay | 134 | TRUE | TRUE | TRUE | TRUE |  | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 56/3 | 2026-03-31 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 134 | TRUE | FALSE | TRUE | FALSE |  | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 144/4 | 2026-04-05 | 2026-04 | 2026-04-30 | 2026-04 | 25 | 25 | Yes | No | exact | Observed matched delay | 129 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 47/1 | 2026-04-05 | 2026-04 | 2026-04-24 | 2026-04 | 19 | 19 | Yes | No | exact | Observed matched delay | 129 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP125 | 2026-04-06 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 128 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 144/3 | 2026-04-07 | 2026-04 | 2026-05-28 | 2026-05 | 51 | 51 | Yes | No | exact | Observed matched delay | 127 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 65/2 | 2026-04-07 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 127 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP109 | 2026-04-12 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 122 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 40/2 | 2026-04-13 | 2026-04 | 2026-04-29 | 2026-04 | 16 | 16 | Yes | No | exact | Observed matched delay | 121 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP126 | 2026-04-15 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 119 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 42/2 | 2026-04-16 | 2026-04 | 2026-05-03 | 2026-05 | 17 | 17 | Yes | No | exact | Observed matched delay | 118 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP1 | 2026-04-18 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 116 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP61 | 2026-04-21 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 113 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP165 | 2026-04-22 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 112 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP86 | 2026-04-23 | 2026-04 | 2026-07-31 | 2026-07 | 99 | 99 | Yes | No | fallback_single_line | Observed matched delay | 111 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 56/2 | 2026-04-25 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 109 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP34 | 2026-04-25 | 2026-04 | 2026-05-08 | 2026-05 | 13 | 13 | Yes | No | exact | Observed matched delay | 109 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP123 | 2026-04-26 | 2026-04 | 2026-06-14 | 2026-06 | 49 | 49 | Yes | No | exact | Observed matched delay | 108 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP47 | 2026-04-26 | 2026-04 | 2026-05-03 | 2026-05 | 7 | 7 | Yes | No | exact | Observed matched delay | 108 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP59 | 2026-04-27 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 107 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 55/1 | 2026-04-28 | 2026-04 | 2026-06-30 | 2026-06 | 63 | 63 | Yes | No | exact | Observed matched delay | 106 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 37/1 | 2026-04-29 | 2026-04 | 2026-05-07 | 2026-05 | 8 | 8 | Yes | No | exact | Observed matched delay | 105 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP142 | 2026-04-29 | 2026-04 | 2026-06-03 | 2026-06 | 35 | 35 | Yes | No | exact | Observed matched delay | 105 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP7 | 2026-04-29 | 2026-04 | 2026-07-02 | 2026-07 | 64 | 64 | Yes | No | exact | Observed matched delay | 105 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 122/1 | 2026-04-30 | 2026-04 | 2026-05-25 | 2026-05 | 25 | 25 | Yes | No | exact | Observed matched delay | 104 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP166 | 2026-04-30 | 2026-04 | 2026-06-21 | 2026-06 | 52 | 52 | Yes | No | exact | Observed matched delay | 104 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP41 | 2026-04-30 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 104 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP6 | 2026-04-30 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 104 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP64 | 2026-05-01 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 103 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 33/1 | 2026-05-07 | 2026-05 | 2026-05-17 | 2026-05 | 10 | 10 | Yes | No | exact | Observed matched delay | 97 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 64/1 | 2026-05-07 | 2026-05 | 2026-06-11 | 2026-06 | 35 | 35 | Yes | No | exact | Observed matched delay | 97 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP144 | 2026-05-07 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 97 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP56 | 2026-05-07 | 2026-05 | 2026-06-23 | 2026-06 | 47 | 47 | Yes | No | exact | Observed matched delay | 97 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 142/1 | 2026-05-08 | 2026-05 | 2026-05-31 | 2026-05 | 23 | 23 | Yes | No | exact | Observed matched delay | 96 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 61/1 | 2026-05-08 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 96 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP82 | 2026-05-08 | 2026-05 | 2026-06-03 | 2026-06 | 26 | 26 | Yes | No | exact | Observed matched delay | 96 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 57/1 | 2026-05-09 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 95 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP161 | 2026-05-09 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 95 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP163 | 2026-05-11 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 93 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 56/4 | 2026-05-13 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 91 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 62/2 | 2026-05-14 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 90 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 71/1 | 2026-05-14 | 2026-05 | 2026-06-02 | 2026-06 | 19 | 19 | Yes | No | exact | Observed matched delay | 90 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP110 | 2026-05-14 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 90 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP38 | 2026-05-14 | 2026-05 | 2026-05-21 | 2026-05 | 7 | 7 | Yes | No | exact | Observed matched delay | 90 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP57 | 2026-05-15 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 89 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 159/3 | 2026-05-16 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 88 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 40/3 | 2026-05-16 | 2026-05 | 2026-05-26 | 2026-05 | 10 | 10 | Yes | No | exact | Observed matched delay | 88 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 65/4 | 2026-05-16 | 2026-05 | 2026-05-28 | 2026-05 | 12 | 12 | Yes | No | exact | Observed matched delay | 88 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 50A/2 | 2026-05-17 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 87 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP162 | 2026-05-17 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 87 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP60 | 2026-05-17 | 2026-05 | 2026-06-14 | 2026-06 | 28 | 28 | Yes | No | exact | Observed matched delay | 87 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 62/1 | 2026-05-18 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 86 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP128 | 2026-05-18 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 86 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP143 | 2026-05-18 | 2026-05 | 2026-06-10 | 2026-06 | 23 | 23 | Yes | No | exact | Observed matched delay | 86 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP63 | 2026-05-18 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 86 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 159/2 | 2026-05-19 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 85 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 23/2 | 2026-05-19 | 2026-05 | 2026-05-26 | 2026-05 | 7 | 7 | Yes | No | exact | Observed matched delay | 85 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 57/2 | 2026-05-19 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 85 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP112 | 2026-05-19 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 85 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP70/3 | 2026-05-19 | 2026-05 | 2026-06-10 | 2026-06 | 22 | 22 | Yes | No | exact | Observed matched delay | 85 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 159/1 | 2026-05-22 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 82 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 60/1 | 2026-05-22 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 82 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 143/1 | 2026-05-23 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 81 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 50A/1 | 2026-05-23 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 81 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP113 | 2026-05-23 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 81 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP158 | 2026-05-23 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 81 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP7 | 2026-05-24 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 80 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | LILO |  | TB 605 - DPR - 2026-08-11.xlsx | LILO
TB 605 | 6xx | Private | tb605 | AP84 | 2026-05-24 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 80 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 39/1 | 2026-05-25 | 2026-05 | 2026-06-08 | 2026-06 | 14 | 14 | Yes | No | exact | Observed matched delay | 79 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP39 | 2026-05-25 | 2026-05 | 2026-06-02 | 2026-06 | 8 | 8 | Yes | No | exact | Observed matched delay | 79 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP55 | 2026-05-25 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 79 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 59/1 | 2026-05-26 | 2026-05 | 2026-06-17 | 2026-06 | 22 | 22 | Yes | No | exact | Observed matched delay | 78 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP42 | 2026-05-26 | 2026-05 | 2026-08-09 | 2026-08 | 75 | 75 | Yes | No | fallback_single_line | Observed matched delay | 78 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP66 | 2026-05-26 | 2026-05 | 2026-05-30 | 2026-05 | 4 | 4 | Yes | No | exact | Observed matched delay | 78 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 34/1 | 2026-05-28 | 2026-05 | 2026-06-19 | 2026-06 | 22 | 22 | Yes | No | exact | Observed matched delay | 76 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 65/1 | 2026-05-28 | 2026-05 | 2026-06-07 | 2026-06 | 10 | 10 | Yes | No | exact | Observed matched delay | 76 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP65 | 2026-05-28 | 2026-05 | 2026-06-04 | 2026-06 | 7 | 7 | Yes | No | exact | Observed matched delay | 76 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 65/5 | 2026-05-30 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 74 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP105 | 2026-05-30 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 74 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP168 | 2026-05-30 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 74 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP174 | 2026-05-30 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 74 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP167 | 2026-05-31 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 73 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP81 | 2026-05-31 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 73 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 35/1 | 2026-06-03 | 2026-06 | 2026-06-14 | 2026-06 | 11 | 11 | Yes | No | exact | Observed matched delay | 70 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 65/3 | 2026-06-03 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 70 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP35 | 2026-06-03 | 2026-06 | 2026-06-24 | 2026-06 | 21 | 21 | Yes | No | exact | Observed matched delay | 70 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 144/1 | 2026-06-04 | 2026-06 | 2026-06-21 | 2026-06 | 17 | 17 | Yes | No | exact | Observed matched delay | 69 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP54 | 2026-06-05 | 2026-06 | 2026-06-29 | 2026-06 | 24 | 24 | Yes | No | fallback_single_line | Observed matched delay | 68 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP76 | 2026-06-05 | 2026-06 | 2026-06-15 | 2026-06 | 10 | 10 | Yes | No | exact | Observed matched delay | 68 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP89 | 2026-06-05 | 2026-06 | 2026-07-05 | 2026-07 | 30 | 30 | Yes | No | fallback_single_line | Observed matched delay | 68 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 50A/4 | 2026-06-06 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 67 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP173 | 2026-06-06 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 67 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP58 | 2026-06-06 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 67 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 143/2 | 2026-06-09 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 64 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 23/3 | 2026-06-09 | 2026-06 | 2026-06-16 | 2026-06 | 7 | 7 | Yes | No | exact | Observed matched delay | 64 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 42/1 | 2026-06-09 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 64 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP36 | 2026-06-09 | 2026-06 | 2026-07-26 | 2026-07 | 47 | 47 | Yes | No | fallback_single_line | Observed matched delay | 64 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP88 | 2026-06-09 | 2026-06 | 2026-07-18 | 2026-07 | 39 | 39 | Yes | No | fallback_single_line | Observed matched delay | 64 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP175 | 2026-06-10 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 63 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP78 | 2026-06-10 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 63 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 144/2 | 2026-06-12 | 2026-06 | 2026-06-17 | 2026-06 | 5 | 5 | Yes | No | exact | Observed matched delay | 61 | TRUE | TRUE | TRUE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 77/3 | 2026-06-12 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 61 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 37/2 | 2026-06-14 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 59 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | 47/3 | 2026-06-15 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 58 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP53 | 2026-06-17 | 2026-06 | 2026-07-27 | 2026-07 | 40 | 40 | Yes | No | fallback_single_line | Observed matched delay | 56 | TRUE | FALSE | FALSE | TRUE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 180/1 | 2026-06-19 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 54 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 47/2 | 2026-06-19 | 2026-06 | 2026-07-20 | 2026-07 | 31 | 31 | Yes | No | exact | Observed matched delay | 54 | TRUE | FALSE | FALSE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 50A/5 | 2026-06-19 | 2026-06 | 2026-08-06 | 2026-08 | 48 | 48 | Yes | No | exact | Observed matched delay | 54 | TRUE | FALSE | FALSE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 52/1 | 2026-06-20 | 2026-06 | 2026-08-10 | 2026-08 | 51 | 51 | Yes | No | exact | Observed matched delay | 53 | TRUE | FALSE | FALSE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | 8/1 | 2026-06-22 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 51 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | LILO |  | TB 605 - DPR - 2026-08-11.xlsx | LILO
TB 605 | 6xx | Private | tb605 | AP172 | 2026-06-22 | 2026-06 | 2026-06-28 | 2026-06 | 6 | 6 | Yes | No | exact | Observed matched delay | 51 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP62 | 2026-06-22 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 51 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP48 | 2026-06-23 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 50 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP140 | 2026-06-24 | 2026-06 | 2026-06-29 | 2026-06 | 5 | 5 | Yes | No | exact | Observed matched delay | 49 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP6 | 2026-06-24 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 49 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | LILO |  | TB 605 - DPR - 2026-08-11.xlsx | LILO
TB 605 | 6xx | Private | tb605 | 171/1 | 2026-06-25 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 48 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 50A/9 | 2026-06-25 | 2026-06 | 2026-07-16 | 2026-07 | 21 | 21 | Yes | No | exact | Observed matched delay | 48 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP151 | 2026-06-25 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 48 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | 56/1 | 2026-06-26 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 47 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP180 | 2026-06-27 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 46 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP8 | 2026-06-27 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 46 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | LILO |  | TB 605 - DPR - 2026-08-11.xlsx | LILO
TB 605 | 6xx | Private | tb605 | 50A/10 | 2026-06-30 | 2026-06 | 2026-07-07 | 2026-07 | 7 | 7 | Yes | No | exact | Observed matched delay | 43 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP10 | 2026-06-30 | 2026-06 | 2026-07-06 | 2026-07 | 6 | 6 | Yes | No | exact | Observed matched delay | 43 | TRUE | TRUE | FALSE | TRUE | Q1 2026 (Apr-Jun) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP5 | 2026-06-30 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 43 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) | LILO |  | TB 605 - DPR - 2026-08-11.xlsx | LILO
TB 605 | 6xx | Private | tb605 | AP52 | 2026-07-03 | 2026-07 | 2026-07-07 | 2026-07 | 4 | 4 | Yes | No | exact | Observed matched delay | 40 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) | Punjab | Punjab | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab | TB 605 - DPR - 2026-08-11.xlsx | Erection-Punjab
TB 605 | 6xx | Private | tb605 | AP176 | 2026-07-06 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 37 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP51 | 2026-07-13 | 2026-07 | 2026-07-20 | 2026-07 | 7 | 7 | Yes | No | exact | Observed matched delay | 30 | TRUE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP13 | 2026-07-14 | 2026-07 | 2026-07-19 | 2026-07 | 5 | 5 | Yes | No | exact | Observed matched delay | 29 | FALSE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | 50A/6 | 2026-07-25 | 2026-07 | 2026-07-30 | 2026-07 | 5 | 5 | Yes | No | exact | Observed matched delay | 18 | FALSE | TRUE | FALSE | TRUE | Q2 2026 to date (Jul-Aug) | Jammu | Jammu | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu | TB 605 - DPR - 2026-08-11.xlsx | Erection -Jammu
TB 605 | 6xx | Private | tb605 | AP8 | 2026-07-27 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 16 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | Jammu |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation JS-Line -Jammu
TB 605 | 6xx | Private | tb605 | AP182 | 2026-07-31 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 12 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | Punjab |  | TB 605 - DPR - 2026-08-11.xlsx | Foundation -JS Line- Punjab
TB 605 | 6xx | Private | tb605 | AP4 | 2026-08-11 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 1 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | LILO |  | TB 605 - DPR - 2026-08-11.xlsx | LILO
TB 605 | 6xx | Private | tb605 | AP9 | 2026-08-11 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 1 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) | LILO |  | TB 605 - DPR - 2026-08-11.xlsx | LILO
TB 608 | 6xx | Private | tb608 | 65/3 | 2025-10-18 | 2025-10 | 2026-07-31 | 2026-07 | 286 | 286 | Yes | No | fallback_single_line | Observed matched delay | 298 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 69/2 | 2025-10-18 | 2025-10 | 2026-04-22 | 2026-04 | 186 | 186 | Yes | No | fallback_single_line | Observed matched delay | 298 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 131/2 | 2025-11-09 | 2025-11 | 2026-03-17 | 2026-03 | 128 | 128 | Yes | No | fallback_single_line | Observed matched delay | 276 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 58/1 | 2025-11-10 | 2025-11 | 2025-12-27 | 2025-12 | 47 | 47 | Yes | No | fallback_single_line | Observed matched delay | 275 | TRUE | FALSE | TRUE | TRUE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 69/0 | 2025-11-10 | 2025-11 | 2026-04-11 | 2026-04 | 152 | 152 | Yes | No | fallback_single_line | Observed matched delay | 275 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 58/0 | 2025-11-11 | 2025-11 | 2026-04-03 | 2026-04 | 143 | 143 | Yes | No | fallback_single_line | Observed matched delay | 274 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 75/5 | 2025-11-15 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 270 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 34/3 | 2025-11-18 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 267 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 101/0 | 2025-11-19 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 266 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 71/1 | 2025-11-20 | 2025-11 | 2025-12-28 | 2025-12 | 38 | 38 | Yes | No | fallback_single_line | Observed matched delay | 265 | TRUE | FALSE | TRUE | TRUE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 33/2 | 2025-11-22 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 263 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 90/0 | 2025-11-22 | 2025-11 | 2026-05-31 | 2026-05 | 190 | 190 | Yes | No | fallback_single_line | Observed matched delay | 263 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 29/0 | 2025-11-25 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 260 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 40/0 | 2025-11-25 | 2025-11 | 2026-03-31 | 2026-03 | 126 | 126 | Yes | No | fallback_single_line | Observed matched delay | 260 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 72/6 | 2025-11-28 | 2025-11 | 2026-01-21 | 2026-01 | 54 | 54 | Yes | No | fallback_single_line | Observed matched delay | 257 | TRUE | FALSE | TRUE | TRUE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 88/0 | 2025-11-28 | 2025-11 | 2026-03-25 | 2026-03 | 117 | 117 | Yes | No | fallback_single_line | Observed matched delay | 257 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 100/0 | 2025-11-30 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 255 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 103/0 | 2025-11-30 | 2025-11 | 2026-05-08 | 2026-05 | 159 | 159 | Yes | No | fallback_single_line | Observed matched delay | 255 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 109/0 | 2025-11-30 | 2025-11 | 2026-08-06 | 2026-08 | 249 | 249 | Yes | No | fallback_single_line | Observed matched delay | 255 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 71/0 | 2025-11-30 | 2025-11 |  |  |  |  | No | No |  | Unmatched/right-censored | 255 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 85/0 | 2025-11-30 | 2025-11 | 2026-07-26 | 2026-07 | 238 | 238 | Yes | No | fallback_single_line | Observed matched delay | 255 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 89/0 | 2025-11-30 | 2025-11 | 2026-05-12 | 2026-05 | 163 | 163 | Yes | No | fallback_single_line | Observed matched delay | 255 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 29/1 | 2025-12-02 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 253 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 75/3 | 2025-12-03 | 2025-12 | 2026-02-18 | 2026-02 | 77 | 77 | Yes | No | fallback_single_line | Observed matched delay | 252 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 69/3 | 2025-12-08 | 2025-12 | 2026-05-13 | 2026-05 | 156 | 156 | Yes | No | fallback_single_line | Observed matched delay | 247 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 5/0 | 2025-12-10 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 245 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 80/0 | 2025-12-11 | 2025-12 | 2026-06-19 | 2026-06 | 190 | 190 | Yes | No | fallback_single_line | Observed matched delay | 244 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 108/0 | 2025-12-12 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 243 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 111/0 | 2025-12-12 | 2025-12 | 2026-06-03 | 2026-06 | 173 | 173 | Yes | No | fallback_single_line | Observed matched delay | 243 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 29/4 | 2025-12-14 | 2025-12 | 2026-01-29 | 2026-01 | 46 | 46 | Yes | No | fallback_single_line | Observed matched delay | 241 | TRUE | FALSE | TRUE | TRUE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 48/0 | 2025-12-14 | 2025-12 | 2026-05-08 | 2026-05 | 145 | 145 | Yes | No | fallback_single_line | Observed matched delay | 241 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 29/3 | 2025-12-17 | 2025-12 | 2026-02-25 | 2026-02 | 70 | 70 | Yes | No | fallback_single_line | Observed matched delay | 238 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 75/4 | 2025-12-18 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 237 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 99/0 | 2025-12-18 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 237 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 102/0 | 2025-12-19 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 236 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 84/0 | 2025-12-19 | 2025-12 | 2026-08-11 | 2026-08 | 235 | 235 | Yes | No | fallback_single_line | Observed matched delay | 236 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 111/1 | 2025-12-21 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 234 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 83/0 | 2025-12-21 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 234 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 91/0 | 2025-12-21 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 234 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 93/0 | 2025-12-21 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 234 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 34/1 | 2025-12-22 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 233 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 25/1 | 2025-12-23 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 232 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 70/3 | 2025-12-23 | 2025-12 | 2026-01-31 | 2026-01 | 39 | 39 | Yes | No | fallback_single_line | Observed matched delay | 232 | TRUE | FALSE | TRUE | TRUE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 29/2 | 2025-12-25 | 2025-12 | 2026-03-04 | 2026-03 | 69 | 69 | Yes | No | fallback_single_line | Observed matched delay | 230 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 4/1 | 2025-12-25 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 230 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 112/0 | 2025-12-27 | 2025-12 | 2026-06-14 | 2026-06 | 169 | 169 | Yes | No | fallback_single_line | Observed matched delay | 228 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 49/0 | 2025-12-27 | 2025-12 | 2026-05-17 | 2026-05 | 141 | 141 | Yes | No | fallback_single_line | Observed matched delay | 228 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 91/1 | 2025-12-27 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 228 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 79/1 | 2025-12-28 | 2025-12 | 2026-05-31 | 2026-05 | 154 | 154 | Yes | No | fallback_single_line | Observed matched delay | 227 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 91/2 | 2025-12-28 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 227 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 114/0 | 2025-12-31 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 224 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 70/2 | 2025-12-31 | 2025-12 | 2026-02-10 | 2026-02 | 41 | 41 | Yes | No | fallback_single_line | Observed matched delay | 224 | TRUE | FALSE | TRUE | TRUE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 77/0 | 2025-12-31 | 2025-12 | 2026-03-06 | 2026-03 | 65 | 65 | Yes | No | fallback_single_line | Observed matched delay | 224 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 86/0 | 2025-12-31 | 2025-12 |  |  |  |  | No | No |  | Unmatched/right-censored | 224 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 91/8 | 2025-12-31 | 2025-12 | 2026-03-17 | 2026-03 | 76 | 76 | Yes | No | fallback_single_line | Observed matched delay | 224 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 94/0 | 2025-12-31 | 2025-12 | 2026-06-14 | 2026-06 | 165 | 165 | Yes | No | fallback_single_line | Observed matched delay | 224 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 41/2 | 2026-01-02 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 222 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 11/2 | 2026-01-03 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 221 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 70/0 | 2026-01-04 | 2026-01 | 2026-04-30 | 2026-04 | 116 | 116 | Yes | No | fallback_single_line | Observed matched delay | 220 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 40/1 | 2026-01-07 | 2026-01 | 2026-04-12 | 2026-04 | 95 | 95 | Yes | No | fallback_single_line | Observed matched delay | 217 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 97/0 | 2026-01-09 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 215 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 41/0 | 2026-01-10 | 2026-01 | 2026-04-19 | 2026-04 | 99 | 99 | Yes | No | fallback_single_line | Observed matched delay | 214 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 113/0 | 2026-01-11 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 213 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 76/3 | 2026-01-11 | 2026-01 | 2026-02-28 | 2026-02 | 48 | 48 | Yes | No | fallback_single_line | Observed matched delay | 213 | TRUE | FALSE | TRUE | TRUE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 91/5 | 2026-01-12 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 212 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 110/0 | 2026-01-13 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 211 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 115/0 | 2026-01-14 | 2026-01 | 2026-06-03 | 2026-06 | 140 | 140 | Yes | No | fallback_single_line | Observed matched delay | 210 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 8/0 | 2026-01-14 | 2026-01 | 2026-06-13 | 2026-06 | 150 | 150 | Yes | No | fallback_single_line | Observed matched delay | 210 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 76/0 | 2026-01-15 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 209 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 69/4 | 2026-01-18 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 206 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 75/1 | 2026-01-19 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 205 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 50/0 | 2026-01-21 | 2026-01 | 2026-05-31 | 2026-05 | 130 | 130 | Yes | No | fallback_single_line | Observed matched delay | 203 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 11/1 | 2026-01-24 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 200 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 123/2 | 2026-01-25 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 199 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 129/1 | 2026-01-27 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 197 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 34/2 | 2026-01-27 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 197 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 47/1 | 2026-01-28 | 2026-01 | 2026-06-21 | 2026-06 | 144 | 144 | Yes | No | fallback_single_line | Observed matched delay | 196 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 79/0 | 2026-01-28 | 2026-01 | 2026-06-09 | 2026-06 | 132 | 132 | Yes | No | fallback_single_line | Observed matched delay | 196 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 132/1 | 2026-01-29 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 195 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 69/1 | 2026-01-29 | 2026-01 | 2026-04-09 | 2026-04 | 70 | 70 | Yes | No | fallback_single_line | Observed matched delay | 195 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 91/7 | 2026-01-29 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 195 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 96/0 | 2026-01-30 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 194 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 128/0 | 2026-01-31 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 193 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 131/0 | 2026-01-31 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 193 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 75/2 | 2026-01-31 | 2026-01 | 2026-07-31 | 2026-07 | 181 | 181 | Yes | No | fallback_single_line | Observed matched delay | 193 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 91/4 | 2026-01-31 | 2026-01 |  |  |  |  | No | No |  | Unmatched/right-censored | 193 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 59/1 | 2026-02-05 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 188 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 73/6 | 2026-02-05 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 188 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 76/1 | 2026-02-05 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 188 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 81/0 | 2026-02-05 | 2026-02 | 2026-03-22 | 2026-03 | 45 | 45 | Yes | No | fallback_single_line | Observed matched delay | 188 | TRUE | FALSE | TRUE | TRUE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 96/1 | 2026-02-05 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 188 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 104/0 | 2026-02-08 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 185 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 42/1 | 2026-02-08 | 2026-02 | 2026-06-21 | 2026-06 | 133 | 133 | Yes | No | fallback_single_line | Observed matched delay | 185 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 126/0 | 2026-02-10 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 183 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 43/0 | 2026-02-10 | 2026-02 | 2026-06-04 | 2026-06 | 114 | 114 | Yes | No | fallback_single_line | Observed matched delay | 183 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 72/7 | 2026-02-11 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 182 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 9/1 | 2026-02-11 | 2026-02 | 2026-05-31 | 2026-05 | 109 | 109 | Yes | No | fallback_single_line | Observed matched delay | 182 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 78/2 | 2026-02-12 | 2026-02 | 2026-07-05 | 2026-07 | 143 | 143 | Yes | No | fallback_single_line | Observed matched delay | 181 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 95/3 | 2026-02-14 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 179 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 95/1 | 2026-02-16 | 2026-02 | 2026-07-19 | 2026-07 | 153 | 153 | Yes | No | fallback_single_line | Observed matched delay | 177 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 131/3 | 2026-02-17 | 2026-02 | 2026-04-23 | 2026-04 | 65 | 65 | Yes | No | fallback_single_line | Observed matched delay | 176 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 129/2 | 2026-02-18 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 175 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 6/1 | 2026-02-18 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 175 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 95/0 | 2026-02-18 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 175 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 131/1 | 2026-02-19 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 174 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 44/0 | 2026-02-19 | 2026-02 | 2026-08-09 | 2026-08 | 171 | 171 | Yes | No | fallback_single_line | Observed matched delay | 174 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 30/0 | 2026-02-20 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 173 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 10/3 | 2026-02-22 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 171 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 124/0 | 2026-02-22 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 171 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 71/2 | 2026-02-22 | 2026-02 | 2026-04-11 | 2026-04 | 48 | 48 | Yes | No | fallback_single_line | Observed matched delay | 171 | TRUE | FALSE | TRUE | TRUE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 70/1 | 2026-02-23 | 2026-02 | 2026-05-12 | 2026-05 | 78 | 78 | Yes | No | fallback_single_line | Observed matched delay | 170 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 72/0 | 2026-02-23 | 2026-02 | 2026-04-11 | 2026-04 | 47 | 47 | Yes | No | fallback_single_line | Observed matched delay | 170 | TRUE | FALSE | TRUE | TRUE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 127/0 | 2026-02-25 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 168 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 132/2 | 2026-02-28 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 165 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 132/3 | 2026-02-28 | 2026-02 |  |  |  |  | No | No |  | Unmatched/right-censored | 165 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 95/2 | 2026-02-28 | 2026-02 | 2026-07-11 | 2026-07 | 133 | 133 | Yes | No | fallback_single_line | Observed matched delay | 165 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 31/0 | 2026-03-06 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 159 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 35/0 | 2026-03-08 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 157 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 10/1 | 2026-03-10 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 155 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 129/0 | 2026-03-10 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 155 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 130/0 | 2026-03-10 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 155 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 82/2 | 2026-03-10 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 155 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 82/1 | 2026-03-11 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 154 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 116/0 | 2026-03-12 | 2026-03 | 2026-07-05 | 2026-07 | 115 | 115 | Yes | No | fallback_single_line | Observed matched delay | 153 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 27/0 | 2026-03-14 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 151 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 125/0 | 2026-03-19 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 146 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 47/0 | 2026-03-28 | 2026-03 | 2026-07-05 | 2026-07 | 99 | 99 | Yes | No | fallback_single_line | Observed matched delay | 137 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 6/0 | 2026-03-28 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 137 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 132/0 | 2026-03-29 | 2026-03 | 2026-05-31 | 2026-05 | 63 | 63 | Yes | No | fallback_single_line | Observed matched delay | 136 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 7/0 | 2026-03-30 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 135 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 34/0 | 2026-03-31 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 134 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 7/2 | 2026-03-31 | 2026-03 |  |  |  |  | No | No |  | Unmatched/right-censored | 134 | TRUE | FALSE | TRUE | FALSE |  |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 92/0 | 2026-04-13 | 2026-04 | 2026-06-28 | 2026-06 | 76 | 76 | Yes | No | fallback_single_line | Observed matched delay | 121 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 9/0 | 2026-04-14 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 120 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 107/1 | 2026-04-19 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 115 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 7/1 | 2026-04-21 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 113 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 61A/0 | 2026-04-23 | 2026-04 | 2026-06-09 | 2026-06 | 47 | 47 | Yes | No | fallback_single_line | Observed matched delay | 111 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 106/0 | 2026-04-30 | 2026-04 |  |  |  |  | No | No |  | Unmatched/right-censored | 104 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 1/0 | 2026-05-06 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 98 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 38/0 | 2026-05-06 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 98 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 61/0 | 2026-05-06 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 98 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 105/0 | 2026-05-07 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 97 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 39/0 | 2026-05-12 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 92 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 20/0 | 2026-05-14 | 2026-05 | 2026-06-30 | 2026-06 | 47 | 47 | Yes | No | fallback_single_line | Observed matched delay | 90 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 3/0 | 2026-05-17 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 87 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 4/0 | 2026-05-24 | 2026-05 |  |  |  |  | No | No |  | Unmatched/right-censored | 80 | TRUE | FALSE | TRUE | FALSE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 18/0 | 2026-05-26 | 2026-05 | 2026-07-22 | 2026-07 | 57 | 57 | Yes | No | fallback_single_line | Observed matched delay | 78 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 70/4 | 2026-06-13 | 2026-06 | 2026-07-19 | 2026-07 | 36 | 36 | Yes | No | fallback_single_line | Observed matched delay | 60 | TRUE | FALSE | TRUE | TRUE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 91/9 | 2026-06-18 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 55 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 5/1 | 2026-06-21 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 52 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 118/0 | 2026-06-30 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 43 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 42/0 | 2026-06-30 | 2026-06 |  |  |  |  | No | No |  | Unmatched/right-censored | 43 | TRUE | FALSE | FALSE | FALSE | Q1 2026 (Apr-Jun) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 73/5 | 2026-07-10 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 33 | TRUE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 119/0 | 2026-07-19 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 24 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 14/0 | 2026-07-27 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 16 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 62/3 | 2026-07-29 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 14 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 20/1 | 2026-07-31 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 12 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 68/0 | 2026-07-31 | 2026-07 |  |  |  |  | No | No |  | Unmatched/right-censored | 12 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN
TB 608 | 6xx | Private | tb608 | 37/0 | 2026-08-04 | 2026-08 |  |  |  |  | No | No |  | Unmatched/right-censored | 8 | FALSE | FALSE | FALSE | FALSE | Q2 2026 to date (Jul-Aug) |  |  | TB 608 - DPR - 2026-08-11.xlsm | WIP-FDN

## Analysis
Notes and Presentation Guidance
Point | Detail
Decision | Do not present Q1 vs Q2-to-date matched-delay days as improvement; recent months are right-censored.
Corrected headline | Use fixed 30-day cohort metric: % of foundations erected within 30 days, only for cohorts with full 30-day exposure.
Headline result | Apr-Jun 2025 = 4.5%; Apr-Jun 2026 = 25.8%; 5.7x YoY improvement.
Negative-delay treatment | Negative-delay rows are kept in raw data but counted as not erected within horizon; impact is immaterial and slightly conservative.
Cumulative table treatment | Presentation table now uses project-level monotonic cumulative foundations so totals cannot decrease month to month.
TB 408 treatment | Correct auditable TB 408 foundation count is 6. The 31 running-count value has been removed from caveats; scope total 485 is flagged as non-comparable.
TA 602 concentration | Legacy mixed-snapshot -228 movement excluding TB 408 was dominated by TA 602 (-165). On monotonic corrected basis, total movement is -76 and TA 602 is -13.
TB 408 Reconciliation
Field | TB 408 Value | Use
Raw Project Wise foundation rows | 6 | Correct auditable foundation-location count
Delay Coverage Foundation Locations | 6 | Should match raw sheet
Scope Snapshot fallback foundation done count | 6 | Should match raw sheet
Scope Total / erection-style cumulative count | 485 | Not comparable to parsed foundation-location count
Corrected Headline: Apr-Jun 30D Horizon YoY
Cohort | Horizon Days | Foundation Locations | Eligible Foundation Locations | Erected <= 30D | % Erected <= 30D | Partial Cohort % (Not Chartable) | Full Cohort Exposure | YoY Multiple vs Apr-Jun 2025
Apr-Jun 2025 | 30 | 532 | 532 | 24 | 4.5 |  | Yes | 1
Apr-Jun 2026 | 30 | 466 | 466 | 120 | 25.8 |  | Yes | 5.7
Apr-Jun 2025 vs 2026 by Horizon - Full Exposure Only
Cohort | Horizon Days | Foundation Locations | Eligible Foundation Locations | Erected <= 30D | % Erected <= 30D | Partial Cohort % (Not Chartable) | Full Cohort Exposure | Erected <= 60D | % Erected <= 60D
2025-04 | 30 | 201 | 201 | 7 | 3.5 |  | Yes
2025-05 | 30 | 192 | 192 | 10 | 5.2 |  | Yes
2025-06 | 30 | 139 | 139 | 7 | 5 |  | Yes
2026-04 | 30 | 117 | 117 | 32 | 27.4 |  | Yes
2026-05 | 30 | 179 | 179 | 44 | 24.6 |  | Yes
2026-06 | 30 | 170 | 170 | 44 | 25.9 |  | Yes
2025-04 | 60 | 201 | 201 |  |  |  | Yes | 13 | 6.5
2025-05 | 60 | 192 | 192 |  |  |  | Yes | 23 | 12
2025-06 | 60 | 139 | 139 |  |  |  | Yes | 20 | 14.4
2026-04 | 60 | 117 | 117 |  |  |  | Yes | 43 | 36.8
2026-05 | 60 | 179 | 179 |  |  |  | Yes | 68 | 38
Partial Horizon Rows - Do Not Chart With Full Cohorts
Cohort | Horizon Days | Foundation Locations | Eligible Foundation Locations | Erected <= 60D | % Erected <= 60D | Partial Cohort % (Not Chartable) | Full Cohort Exposure
2026-06 | 60 | 170 | 68 | 30 |  | 44.1 | No
30D Cohort Curve Jan 2025 to Jun 2026
Cohort | Horizon Days | Foundation Locations | Eligible Foundation Locations | Erected <= 30D | % Erected <= 30D | Partial Cohort % (Not Chartable) | Full Cohort Exposure
2025-01 | 30 | 187 | 187 | 6 | 3.2 |  | Yes
2025-02 | 30 | 202 | 202 | 3 | 1.5 |  | Yes
2025-03 | 30 | 156 | 156 | 9 | 5.8 |  | Yes
2025-04 | 30 | 201 | 201 | 7 | 3.5 |  | Yes
2025-05 | 30 | 192 | 192 | 10 | 5.2 |  | Yes
2025-06 | 30 | 139 | 139 | 7 | 5 |  | Yes
2025-07 | 30 | 134 | 134 | 0 | 0 |  | Yes
2025-08 | 30 | 97 | 97 | 3 | 3.1 |  | Yes
2025-09 | 30 | 78 | 78 | 5 | 6.4 |  | Yes
2025-10 | 30 | 104 | 104 | 11 | 10.6 |  | Yes
2025-11 | 30 | 208 | 208 | 33 | 15.9 |  | Yes
2025-12 | 30 | 285 | 285 | 64 | 22.5 |  | Yes
2026-01 | 30 | 229 | 229 | 65 | 28.4 |  | Yes
2026-02 | 30 | 187 | 187 | 34 | 18.2 |  | Yes
2026-03 | 30 | 133 | 133 | 36 | 27.1 |  | Yes
2026-04 | 30 | 117 | 117 | 32 | 27.4 |  | Yes
2026-05 | 30 | 179 | 179 | 44 | 24.6 |  | Yes
2026-06 | 30 | 170 | 170 | 44 | 25.9 |  | Yes
Right-Censoring Diagnostic Jan-Jul 2026
Foundation Month | Foundation Locations | Match % | Median Exposure Days | Average Delay Days (matched only) | P90 Delay Days (matched only)
2026-01 | 229 | 79.5 | 205 | 65.2 | 139.2
2026-02 | 187 | 66.3 | 178 | 64.4 | 125.1
2026-03 | 133 | 66.2 | 149 | 51.7 | 111.3
2026-04 | 117 | 56.4 | 116 | 46.3 | 92
2026-05 | 179 | 43 | 87 | 30.6 | 66.8
2026-06 | 170 | 36.5 | 56 | 22.4 | 41.9
2026-07 | 94 | 31.9 | 27 | 13.2 | 25.1
Corrected Monotonic Cumulative Gap
Month | Basis | Projects Included | Foundations Cumulative | Erections Cumulative | FE Gap Cumulative | Snapshot-Limited Projects | MoM Movement
2026-04 | Monotonic corrected | 16 | 4353 | 3211 | 1142 | 0
2026-04 | Monotonic corrected, excluding TB 408 | 15 | 4322 | 2733 | 1589 | 0
2026-05 | Monotonic corrected | 17 | 4810 | 3580 | 1230 | 1 | 88
2026-05 | Monotonic corrected, excluding TB 408 | 16 | 4779 | 3096 | 1683 | 1 | 94
2026-06 | Monotonic corrected | 18 | 5330 | 3840 | 1490 | 2 | 260
2026-06 | Monotonic corrected, excluding TB 408 | 17 | 5299 | 3356 | 1943 | 2 | 260
2026-07 | Monotonic corrected | 18 | 5460 | 4025 | 1435 | 2 | -55
2026-07 | Monotonic corrected, excluding TB 408 | 17 | 5429 | 3540 | 1889 | 2 | -54
2026-08 | Monotonic corrected | 18 | 5492 | 4079 | 1413 | 2 | -22
2026-08 | Monotonic corrected, excluding TB 408 | 17 | 5461 | 3594 | 1867 | 2 | -22
Legacy Mixed-Snapshot Diagnostic - Do Not Present
Month | Foundations Cumulative (Mixed Snapshot) | Erections Cumulative | FE Gap Cumulative (Mixed Snapshot) | MoM Foundation Movement | Quality Flag
2026-04 | 4353 | 3211 | 1142
2026-05 | 4810 | 3580 | 1230 | 457
2026-06 | 5330 | 3840 | 1490 | 520
2026-07 | 5308 | 4025 | 1283 | -22 | FOUNDATION_CUMULATIVE_DECREASES_DO_NOT_PRESENT
2026-08 | 5340 | 4079 | 1261 | 32
TA 602 Concentration Summary
Basis | Total Movement Jun->Aug | TA 602 Movement | Projects Narrowed | Projects Widened | Projects Unchanged | Use On Slide
Legacy mixed-snapshot excluding TB 408 | -228 | -165 | 11 | 5 | 2 | No - contaminated by TA 602 snapshot decrease
Monotonic corrected excluding TB 408 | -76 | -13 | 11 | 5 | 2 | Only with data-quality caveat
Project Movement Jun to Aug - Corrected
Project | Jun FE Gap | Aug FE Gap | Movement Jun->Aug
TA 601 | 147 | 188 | 41
TA 512 | 70 | 33 | -37
TB 507 | 126 | 102 | -24
TB 605 | 104 | 80 | -24
TA 414 | 69 | 55 | -14
TA 602 | 246 | 233 | -13
TA 513 | 65 | 74 | 9
TA 419 | 50 | 41 | -9
TB 608 | 116 | 108 | -8
TA 418 | 161 | 167 | 6
TA 510 | 50 | 47 | -3
TA 416 | 328 | 331 | 3
TA 505 | 15 | 13 | -2
TA 413 | 12 | 11 | -1
TB 501 | 1 | 2 | 1
TA 509 | 54 | 53 | -1
TA 421 | 329 | 329 | 0
TA 515 | 0 | 0 | 0
Project Movement Jun to Aug - Legacy Diagnostic
Project | Jun FE Gap | Aug FE Gap | Movement Jun->Aug
TA 602 | 246 | 81 | -165
TA 601 | 147 | 188 | 41
TA 512 | 70 | 33 | -37
TB 605 | 104 | 80 | -24
TB 507 | 126 | 102 | -24
TA 414 | 69 | 55 | -14
TA 513 | 65 | 74 | 9
TA 419 | 50 | 41 | -9
TB 608 | 116 | 108 | -8
TA 418 | 161 | 167 | 6
TA 510 | 50 | 47 | -3
TA 416 | 328 | 331 | 3
TA 505 | 15 | 13 | -2
TA 413 | 12 | 11 | -1
TB 501 | 1 | 2 | 1
TA 509 | 54 | 53 | -1
TA 421 | 329 | 329 | 0
TA 515 | 0 | 0 | 0
Snapshot Alignment Audit
Project | Scope Total | Scope Source | Scope Report Date | Fallback Foundation Done Count | Coverage Status | Coverage Reason | Raw Foundation Rows | Staleness Days vs Latest Data Date | Quality Flag
TA 413 | 316 | status_quantity_primary_latest | 2026-08-11 | 314 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | 314 | 0
TA 414 | 352 | status_quantity_primary_latest | 2026-08-11 | 335 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | 335 | 0
TA 416 | 302 | status_quantity_primary_latest | 2026-07-16 | 331 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | 331 | 26 | STALE_SCOPE_SNAPSHOT
TA 418 | 127 | status_quantity_primary_latest | 2026-07-21 | 167 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | 167 | 21 | STALE_SCOPE_SNAPSHOT
TA 419 | 331 | status_quantity_primary_latest | 2026-08-11 | 285 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | 285 | 0
TA 421 | 309 | status_quantity_primary_latest | 2026-07-11 | 319 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | 319 | 31 | STALE_SCOPE_SNAPSHOT
TA 505 | 379 | status_quantity_primary_latest | 2026-07-29 | 378 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | 378 | 13 | STALE_SCOPE_SNAPSHOT
TA 510 | 293 | status_quantity_primary_latest | 2026-08-11 | 95 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | 95 | 0
TA 512 | 319 | status_quantity_primary_latest | 2026-08-11 | 312 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | 312 | 0
TA 513 | 619 | status_quantity_primary_latest | 2026-06-22 | 109 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | 109 | 50 | STALE_SCOPE_SNAPSHOT
TA 601 | 292 | status_quantity_primary_latest | 2026-08-11 | 188 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | 188 | 0
TB 408 | 485 | status_quantity_primary_latest | 2026-07-30 | 6 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | 6 | 12 | STALE_SCOPE_SNAPSHOT;TB408_SCOPE_MISMATCH_RAW_COUNT_6
TB 501 | 238 | status_quantity_primary_latest | 2026-07-30 | 235 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | 235 | 12 | STALE_SCOPE_SNAPSHOT
TB 507 | 556 | status_quantity_primary_latest | 2026-08-11 | 375 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | 375 | 0
TB 605 | 523 | status_quantity_primary_latest | 2026-08-11 | 361 | OK_DETAIL | Detail foundation completion dates parsed from configured sheet(s). | 361 | 0
TB 608 | 472 | status_quantity_primary_latest | 2026-08-11 | 159 | DETAIL_STATUS_MISMATCH | Detail completion dates were parsed, but counts are materially below status cumulative foundation progress; keeping detail source and flagging mapping/status mismatch. | 159 | 0