## Summary
765 KV D/C Beawar Mandsaur T/L (TA-505)
SL No | Description | Unit |  | Remarks
1 | Total Line length | KMS | 139.591 | RAJ- 79.97 KM & MP-56.73 KM
2 | Total Tower | Nos | 379
3 | Total Foundation Completed | Nos | 295 | FDN Gang Moblized-07
4 | Work Front | Nos | 5
5 | Foundation Work in Progress | Nos | 13
6 | Total Number of ROW Locations | Nos | 22
Locations on Hold & Approval to be done By PGCIL
a | FOREST | Nos | 25 | RAJ- 19 & MP-6
b | ULE/RC | Nos | 13 | 22 out of 27 RC/ULE locations are approved by PGCIL. Stub Drawings pending from KEC/PGCIL Engg.
c | PL X-ing | Nos | 6
d | RLY X-ing | Nos | 4
e | NH X-ing | Nos | 8
f | GPL X-ing | Nos | 0
i | TP TOWER | Nos | 1
j | Location on hold due pending drawings of RC/ULE. | Nos | 22 | RC Stub Drawings Pending from KEC Engg. & ULE Foundation drawings pending from PGCIL Engg.
| Total Locations |  | 414
Erection
1 | Foundation Completed till date | Nos | 295
2 | Erection Completed till date | Nos | 152
3 | WIP location | Nos | 10
4 | Balance W.r.t Foundation Completed | Nos | 133
5 | Erection Gang Mobilization | Gang | 10
| RC/Benching/ULE proposal |  | 32 | Remarks
| Total submitted |  | 32 | (27 -RC/ULE/Benching, 5- only Benching)
| Total Approved |  | 27 | Approved all 27 RC/ULE locations except the benching Qty.
| Balance to be Approved |  | 5
| PGCIL Chittorgarh |  | 5
| Jaipur engg. |  | 0
| Gurgaon cc |  | 0
| Proposal making under progress |  | 0
CROSSING DETAILS
Sl.No | Summary |  |  | Total Nos | Proposals Submitted | Approval/NOC Obtained | Balance
1 | Power Line Crossings |  |  | 12 | 12 | 12 | 0
2 | Forest Crossings |  |  | 10 | 10 | 0 | 10
3 | NH Crossings |  |  | 2 | 2 | 0 | 2
4 | Railway Crossing |  |  | 1 | 1 | 1 | 0
5 | Gas Pipe Line |  |  | 1 | 1 | 0 | 1
Total |  |  |  | 26 | 26 | 13 | 13
NB: 1. Civil Aviation & Defence Aviation Propoasal Submitted at Concerned Dept. for final Clearance Certificate.
2. PTCC Proposal Submitted at Concerned Dept. for final Clearance Certificate.

## FDN-ERC Status
Date:-30/10/2025
TA-505 | 765 KV D/C HEXA BEAWAR-MANDSAUR TRANSMISSION LINE
MP SECTION
FOUNDATION
| TOTAL LOCATION | Completed | Balance | WIP | Balance excluding WIP | Locations on Hold | [9 empty] | Available Work front
[6 empty] | ROW | Forest | Power line X-ing | TP tower | NH | Non finalisation of Gantry Route | Common Point | Stub not available | Water Logged Locations/Approach Issue | RC/ULE
| 156 | 120 | 36 | 7 | 29 | 16 | 6 | 0 | 0 | 4 | 0 | 0 |  |  | 1 | 2
RAJASTHAN
FOUNDATION
| TOTAL LOCATION | Completed | Balance | WIP | Balance excluding WIP | Locations on Hold | [9 empty] | Available Work front
[6 empty] | ROW | Forest | Power line X-ing | TP tower | NH | Non finalisation of Gantry Route | Common Point | Stub not available | Water Logged Locations/Approach Issue | RC/ULE
| 223 | 175 | 48 | 3 | 45 | 6 | 24 | 0 | 0 | 6 | 0 | 0 | 2 | 1 | 3 | 3
| 379 | 295 | 84 | 10 | 74 | 22 | 30 | 0 | 0 | 10 | 0 | 0 | 2 | 1 | 4 | 5
Erection
| TOTAL LOCATION | Foundation Completed | Erection Completed | Balance Wrt Foundation | WIP | Balance Tower Parts Available in store | Locations on Hold |  |  | Available Erection front
[7 empty] | Opium | 11 kV/33kV line shifting | Water logged/approach issue
| 379 | 293 | 151 | 142 | 10 | 169 | 7 | 6 | 5 | 114

## Balance Fdn Plan (hidden)
PLAN for Balance Location
Sl.no | Location No | Tower Type | Aug | Sept | Remark
1 | 100/0 | DD45+0 |  |  | Common Point
2 | 103/5 | DA+0 |  |  | RC
3 | 103/9 | DA+3 | Y |  | ROW
4 | 113/0 | DD60+9 |  |  | RC
5 | 114/4 | DA+3 |  |  | Front Available
6 | 117/0 | DD45+6 | Y |  | ROW
7 | 122/0 | DD60+3 |  |  | Water Logged Locs-Appraoch unavailable
8 | 123/0 | DD60+6 |  |  | Water Logged Locs-Appraoch unavailable
9 | 123/1 | DA+0 |  |  | Hold due to NH X-ing
10 | 123/2 | DA+0 |  |  | Hold due to NH X-ing
11 | 123/3 | DA-3 |  |  | Hold due to NH X-ing
12 | 124/0 | DD45+0 |  |  | Hold due to NH X-ing
13 | 125/0 | DD60+0 |  |  | Hold due to NH X-ing
14 | 125/1 | DA+0 |  |  | Hold due to NH X-ing
15 | 126/1 | DA+9 |  |  | RC
16 | 129/0 | DB1+3 |  |  | RC & Forest
17 | 129/1 | DB1+9 |  |  | RC & Forest
18 | 129A/0 | DD45+0 | Y |  | Front Available
19 | 133/0 | DB2+3 |  |  | RC & Forest
20 | 134/0 | DC1+0 |  |  | RC & Forest
21 | 136/3 | DA+0 |  |  | Due to TP Tower
22 | 136/4 | DC1+0 |  |  | Due to TP Tower
23 | 137/0 | DD60+9 |  |  | RC
24 | 137A/0 | DC2+25 |  |  | RC
25 | 138/0 | DB1+3 |  |  | RC
26 | 138/1 | DA-3 |  |  | Forest
27 | 138/2 | DB1+9 |  |  | RC & Forest
28 | 138/3 | DA+3 |  |  | RC & Forest
29 | 139/0 | DB2+0 |  |  | Forest
30 | 139/1 | DB1+3 |  |  | Forest
31 | 142/1 | DA-3 |  |  | RC & Forest
32 | 143/0 | DD45+0 |  |  | RC & Forest
33 | 144/0 | DC1+0 |  |  | RC & Forest
34 | 145/0 | DD60+18 | Y |  | Water Logged Locs-Appraoch unavailable
35 | 146/0 | DD60+18 |  |  | RC & Forest
36 | 146/1 | DA+9 |  |  | Forest
37 | 148B/0 | DB1+0 |  |  | RC
38 | 148B/1 | DA+0 |  |  | RC & Forest
39 | 148B/2 | DA+6 |  |  | Forest
40 | 148C/0 | DB1+9 |  |  | RC & Forest
41 | 149B/0 | DB1+25 |  |  | Stub not Available
42 | 149B/1 | DB1+15 |  |  | Stub not Available
43 | 149B/2 | DA+6 |  |  | RC
44 | 149B/3 | DA+3 |  |  | RC
45 | 149B/4 | DA+0 |  |  | RC
46 | 153/0 | DB1+6 | Y |  | Water Logged Locs-Appraoch unavailable
47 | 154/0 | DB2+9 | Y |  | Water Logged Locs-Appraoch unavailable
48 | 154/4 | DA+3 |  |  | WIP
49 | 155/0 | DC2+0 | Y |  | ROW
50 | 156/2 | DA+3 | Y |  | ROW
51 | 156/5 | DA+0 |  |  | Front Available
52 | 156/6 | DA+0 |  |  | Forest
53 | 157/0 | DB2+9 |  |  | RC & Forest
54 | 149/0 | DD45+3 |  |  | MP-Forest
55 | 149/1 | DA+3 |  |  | MP-Forest
56 | 149/2 | DA+9 |  |  | MP-Forest
57 | 149A/0 | DC1+18 |  |  | MP-Forest
58 | 158/0 | DC2+18 |  |  | MP-Forest
59 | 158/1 | DA+6 |  |  | MP-Forest
60 | 162/0 | DB2+0 | Y |  | ROW
61 | 162/1 | DA+0 |  |  | ROW
62 | 162/2 | DA+0 |  |  | ROW
63 | 163/0 | DB1+18 |  |  | Stub not Available
64 | 164/0 | DC2+18 |  |  | ROW
65 | 164/1 | DA+9 | Y |  | ROW
66 | 165/0 | DB1+6 |  |  | RC
67 | 165/2 | DA+0 |  |  | RC
68 | 168/0 | DC2+0 |  |  | Front Available
69 | 169/0 | DC1+3 |  |  | Front Available
70 | 169/8 | DA+0 |  |  | ROW
71 | 169/9 | DA-3 |  |  | ROW
72 | 171/5 | DA+0 | Y |  | Water Logged Locs-Appraoch unavailable
73 | 174B/0 | DB2+0 |  |  | NH x-ing (MP)
74 | 175/0 | DB1+0 |  |  | NH x-ing (MP)
75 | 175/1 | DA+0 |  |  | NH x-ing (MP)
76 | 175/2 | DA+0 |  |  | NH x-ing (MP)
77 | 178/2 | DA+6 |  |  | RC
78 | 178/4 | DA-3 | Y |  | Front Available
79 | 178/5 | DA+0 |  |  | Front Available
80 | 179/0 | DC2+0 |  |  | ROW
81 | 179/1 | DA+3 |  |  | Water Logged Locs-Appraoch unavailable
82 | 179/2 | DA+3 |  |  | Water Logged Locs-Appraoch unavailable
83 | 179/3 | DA+0 |  |  | Water Logged Locs-Appraoch unavailable
84 | 179/4 | DA-3 |  |  | Water Logged Locs-Appraoch unavailable
85 | 179/5 | DA+0 | Y |  | Water Logged Locs-Appraoch unavailable
86 | 179/6 | DA+0 | Y |  | Water Logged Locs-Appraoch unavailable
87 | 179/7 | DA+0 | Y |  | Water Logged Locs-Appraoch unavailable
88 | 179/8 | DA+0 | Y |  | Water Logged Locs-Appraoch unavailable
89 | 179/9 | DA+3 | Y |  | Water Logged Locs-Appraoch unavailable
90 | 180/0 | DC2+15 |  |  | Water Logged Locs-Appraoch unavailable
91 | 181/0 | DD60+9 |  |  | Water Logged Locs-Appraoch unavailable
92 | 181/1 | DA+0 |  |  | Hold due to Non Finalisation of Gantry
93 | 181/2 | DA-3 |  |  | Hold due to Non Finalisation of Gantry
94 | 181/3 | DA-3 |  |  | Hold due to Non Finalisation of Gantry
95 | 181/4 | DA+0 |  |  | Hold due to Non Finalisation of Gantry
96 | 181/5 | DA-3 |  |  | Hold due to Non Finalisation of Gantry
97 | 181/6 | DA-3 |  |  | Hold due to Non Finalisation of Gantry
98 | 182/0 | DD60+6 |  |  | RC & Hold due to Non Finalisation of Gantry
99 | 182B/0(DE) | DD60+0 |  |  | Hold due to Non Finalisation of Gantry

## Visual Chart (hidden)
V I S U A L C H A R T
| DATE : |  | 2025-04-13
| Name of Line : |  |  | 765 KV D/C HEXA BEAWAR MANDSAUR T/L
| Project Code: |  |  |  | TA505
| Name of Contractor: |  |  |  | M/s. KEC INTERNATIONAL LTD.
[31 empty] | FDN | Ear | ERE | STR
[8 empty] | D |  |  |  | D |  | D | [5 empty] | D |  | D |  | D |  | D |  | D |  | D
[6 empty] | COMMON TOWER |  | 100/0 |  | 101/0 |  | 101/1 |  | 101/2 |  |  |  | 101/3 |  | 101/4 |  | 101/5 |  | 101/6 |  | 101/7 |  | 101/8 |  | 102/0
[12 empty] | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
[6 empty] | 0 |  | 1 |  | 2 |  | 3 |  | 4 |  |  |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11
[7 empty] | 0 | Hold | 418.579 | Hold | 425 | Completed | 312 | Completed |  | 381 |  | Completed | 455 | Completed | 376 | Completed | 401 | Completed | 428 | Completed | 357 | Completed | 335.158 | Completed | 9 | 5 | 8
[8 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
[8 empty] | DD45+0 |  | DC1+3 |  | DA+3 |  | DA+9 |  |  |  | DA+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA-3 |  | DC2+3
[12 empty] | WFR |  | WFR |  |  |  | WFR |  | WFR |  | WFR |  | WFR |  | WFR |  | DRY |  | DRY
RAJASTHAN REGION
|  | 103/0 |  | 103/1 |  | 103/2 |  | 103/3 |  | 103/4 |  | 103/5 |  | 103/5A |  | 103/5A1 |  | 103/6A |  | 103/7 |  | 103/8 |  | 103/9 |  | 104/0 |  | 104/1 |  | 104/2
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  |  |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25
| 461.164 |  | 373 | WIP | 334.67 | WIP | 321.15 | WIP | 391 | WIP | 388 |  | 392 |  | 293 |  | 274 |  | 218 | Completed | 422 |  | 339 |  | 423.633 | Completed | 335.192 | Completed | 326.577 | Completed | 4 | 3 | 0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Completed |  | 0 |  | 0 |  | Completed |  | 0 |  | Completed
|  | DC1+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DD60+0 |  | DA-3 |  | DD45+0 |  | DA+6 |  | DA+3 |  | DA+3 |  | DD45+3 |  | DA-3 |  | DA-3
|  | ROUTE TO BE DIVERTED TO AVOID MINES | [17 empty] | DFR | [5 empty] | DFR |  | DFR |  | WET
|  |  |  | Rajesh Suwalkar |  | Rajesh Suwalkar |  | Rajesh Suwalkar |  | Rajesh Suwalkar
RAJASTHAN REGION
|  | HR |  |  |  |  | GAS PIPE LINE
|  | 105/0 |  | 105/1 |  | 106/0 |  | 108/0 |  | 108/1 |  | 108/2 |  | 108/3 |  |  |  | 108/4 |  | 109/0 |  | 109/1 |  | 109/2 |  | 109/3 |  | 109/4 |  | 110/0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 1 |  | 1 |  | 0 |  | 0 |  | 0
25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  |  |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39
| 304.947 | Completed | 379.11 | Completed | 375.442 | WIP | 212.418 | WIP | 326.001 | Completed | 332 | Completed | 285 | Completed |  | 345 |  | Completed | 380.282 | Completed | 384.998 | Completed | 360 | Completed | 378 | Completed | 387 | Completed | 439.322 | Completed | 12 | 11 | 6
|  | 0 |  | Completed |  | 0 |  | 0 |  | Completed |  | Completed |  | Completed |  |  |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DC1+0 |  | DA+0 |  | DD60+0 |  | DD45+0 |  | DA-3 |  | DA-3 |  | DA-3 |  |  |  | DA+0 |  | DC1+0 |  | DA-1.5 |  | DA-1.5 |  | DA+0 |  | DA+3 |  | DC2+3
|  | WFR |  | WFR |  | SUMIT |  | SUMIT |  | DFR |  | WET |  | WET |  |  |  | WFR |  | DFR |  | WFR |  | WFR |  | WFR |  | WFR |  | WFR
RAJASTHAN REGION
|  | 110/1 |  | 110/2 |  | 110/3 |  | 110/4 |  | 110/5 |  | 110/6 |  | 110/7 |  |  |  | 110/8 |  | 110A/0 |  | 110A/1 |  | 110A/2 |  | 111/0 |  | 111/1 |  | 111/2
|  | Jwala Singh |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 1 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  |  |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 53
| 386.733 | Completed | 358.962 | Completed | 399.964 | Completed | 375.845 | ROW | 417.796 | Completed | 403.677 | Completed | 414.519 | Completed |  | 415.771 |  | Completed | 339.11 | Completed | 398.31 | Completed | 390.626 | Completed | 441.234 | Completed | 415.0029 | Completed | 416.9999 | Completed | 13 | 11 | 8
|  | Completed |  | Completed |  | Completed |  | 0 |  | 0 |  | Completed |  | Completed |  |  |  | Completed |  | 0 |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DA-1.5 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  |  |  | DA+0 |  | DB2+0 |  | DA+3 |  | DA-1.5 |  | DB1+6 |  | DA+3 |  | DA+3
|  | WFR |  | WFR |  | DRY |  |  |  | WET |  | WFR |  | WFR |  |  |  | WFR |  | DFR |  | WFR |  | DFR |  | DFR |  | WFR |  | WFR
RAJASTHAN REGION
400 kV
|  | 111/3 |  | 111/4 |  | 112/0 |  | 113/0 |  | 113/1 |  | 113/2 |  | 113/3 |  |  |  | 113/4 |  | 113/5 |  | 113/6 |  | 114/0 |  | 114/1 |  | 114/2 |  | 114/3
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60 |  |  |  | 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67
| 405.0008 | Completed | 333 | Completed | 383.6369 | Completed | 225.782 | Hold | 390 | Completed | 343 | Completed | 327 | Completed |  | 364 |  | Completed | 308 | Completed | 465 | Completed | 367.662 | Completed | 399.998 | Completed | 426 | Completed | 362 | Completed | 13 | 13 | 3
|  | Completed |  | Completed |  | Completed |  | 0 |  | Completed |  | Completed |  | Completed |  |  |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DA+0 |  | DA+9 |  | DD60+18 |  | DD60+9 |  | DA-3 |  | DA-1.5 |  | DA-3 |  |  |  | DA+0 |  | DA+6 |  | DA+6 |  | DC2+0 |  | DA+3 |  | DA+0 |  | DA+0
|  | WET |  | DFR |  | DFR |  |  |  | DFR |  | WFR |  | DFR |  |  |  | DFR |  | DFR |  | DFR |  | WET |  | DFR |  | WFR |  | WFR
RAJASTHAN REGION
[19 empty] | 132 kV | [7 empty] | 220kV
|  | 114/4 |  | 114/5 |  | 114/6 |  | 114/7 |  | 114/8 |  | 114/9 |  | 114/10 |  |  |  | 115/0 |  | 116/0 |  | 116/1 |  | 116/2 |  | 117/0 |  | 118/0 |  | 119/0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
67 |  | 68 |  | 69 |  | 70 |  | 71 |  | 72 |  | 73 |  | 74 |  |  |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80 |  | 81
| 382 | Hold | 441 | Completed | 309 | Completed | 331 | Completed | 431 | Completed | 396 | Completed | 444 | Completed |  | 381.622 |  |  | 200.194 |  | 323.899 | Completed | 403 | Completed | 419.713 | Hold | 239.882 | Completed | 421.011 | WIP | 11 | 8 | 3
|  | 0 |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  |  |  | 0 |  | 0 |  | Completed |  | Completed |  | 0 |  | 0 |  | 0
|  | DA+3 |  | DA+6 |  | DA-3 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+6 |  |  |  | DD60+3 |  | DD45+3 |  | DA+3 |  | DA+3 |  | DD45+6 |  | DD60+6 |  | DC2+0
|  |  |  | DFR |  | DFR |  | DFR |  | WET |  | WET |  | DFR |  |  |  | SUMIT |  | SUMIT |  | WFR |  | WFR |  |  |  | WFR |  | SUMIT
RAJASTHAN REGION
| 220kV | [23 empty] | NH
|  | 120/0 |  | 120/1 |  | 120/2 |  | 120/3 |  | 121/0 |  | 122/0 |  | 123/0 |  |  |  | 123/1 |  | 123/2 |  | 123/3 |  | 124/0 |  | 125/0 |  | 125/1 |  | 126/0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  |  |  | 89 |  | 90 |  | 91 |  | 92 |  | 93 |  | 94 |  | 95
| 193.168 |  | 416.997 | Completed | 363 | Completed | 339 | Completed | 473.767 | Hold | 360.17 | Hold | 272 | Hold |  | 301.25 |  | Hold | 349 | Hold | 307 | Hold | 310.92 | Hold | 249.658 | Hold | 372.002 | Hold | 367.458 | Completed | 5 | 4 | 0
|  | 0 |  | Completed |  | Completed |  | Completed |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Completed
|  | DD45+3 |  | DA+0 |  | DA-1.5 |  | DA+9 |  | DB1+6 |  | DD60+3 |  | DD60+6 |  |  |  | DA+0 |  | DA+0 |  | DA-3 |  | DD45+0 |  | DD60+0 |  | DA+0 |  | DB2+0
|  | SUMIT |  | WFR |  | WFR |  | WFR | [21 empty] | DFR
RAJASTHAN REGION
RAJ FOREST
Proposed 132kV
|  | 126/1 |  | 126/2 |  | 126/3 |  | 126/4 |  | 127/0 |  | 127/1 |  | 127/2 |  |  |  | 127/3 |  | 128/0 |  | 129/0 |  | 129/1 |  | 129A/0 |  | 129A/1 |  | 129A/2
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100 |  | 101 |  | 102 |  |  |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109
| 412 | Hold | 420 | Completed | 339 | Completed | 461 | Completed | 324.66 | Completed | 342 | Completed | 392 | Completed |  | 371 |  | Completed | 335.587 | Completed | 421.973 | Hold | 330 | Hold | 474.912 | Hold | 321 | Completed | 400.55 | Completed | 10 | 6 | 0
|  | 0 |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | 0 |  |  |  | 0 |  | Completed |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+9 |  | DA-3 |  | DA+3 |  | DA+9 |  | DD45+0 |  | DA+0 |  | DA+0 |  |  |  | DA+6 |  | DC2+9 |  | DB1+3 |  | DB1+9 |  | DD45+0 |  | DA+0 |  | DA+0
|  |  |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  |  |  | DRY |  | DFR | [7 empty] | DFR |  | DFR
RAJASTHAN REGION
[14 empty] | RAJ FOREST | [14 empty] | Temple
|  | 129A/3 |  | 130/0 |  | 130/1 |  | 130/2 |  | 131/0 |  | 132/0 |  | 133/0 |  |  |  | 134/0 |  | 135/0 |  | 135/1 |  | 135/2 |  | 135/3 |  | 136/0 |  | 136/1
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
109 |  | 110 |  | 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  |  |  | 117 |  | 118 |  | 119 |  | 120 |  | 121 |  | 122 |  | 123
| 342 | Completed | 280 | Completed | 387.996 | Completed | 319 | Completed | 429.453 | Completed | 484.387 | WIP | 372.194 | Hold |  | 552.223 |  | Hold | 396.823 | Completed | 357.996 | Completed | 401 | Completed | 395.009 | Completed | 445.379 | WIP | 396.995 | Completed | 10 | 2 | 0
|  | 0 |  | Completed |  | 0 |  | 0 |  | Completed |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+0 |  | DB2+0 |  | DA+0 |  | DA-1.5 |  | DD45+9 |  | DD60+6 |  | DB2+3 |  |  |  | DC1+0 |  | DD45+0 |  | DA+3 |  | DA+9 |  | DA+9 |  | DC2+3 |  | DA+3
|  | WFR |  | WFR |  | WFR |  | WFR |  | WFR |  | RST | [7 empty] | DFR |  | DFR |  | DFR |  | DFR |  | RST |  | DFR
RAJASTHAN REGION
RAJ FOREST
TP Tower
|  | 136/2 |  | 136/3 |  | 136/4 |  | 136/5 |  | 137/0 |  | 137A/0 |  | 138/0 |  |  |  | 138/1 |  | 138/2 |  | 138/3 |  | 139/0 |  | 139/1 |  | 140/0 |  | 140/1
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
123 |  | 124 |  | 125 |  | 126 |  | 127 |  | 128 |  | 129 |  | 130 |  |  |  | 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137
| 374.005 | WIP | 433 | Hold | 390 | Hold | 406.995 | Completed | 411.482 | Hold | 566.681 | Hold | 326.632 | Hold |  | 371.997 |  | Hold | 441 | Hold | 445 | Hold | 332.731 | Hold | 241.999 | Hold | 473.131 |  | 439.999 | Completed | 3 | 0 | 0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+3 |  | DA+0 |  | DC1+0 |  | DA+3 |  | DD60+9 |  | DC2+25 |  | DB1+3 |  |  |  | DA-3 |  | DB1+9 |  | DA+3 |  | DB2+0 |  | DB1+3 |  | DC1+9 |  | DA+3
|  | RST | [5 empty] | DFR | [19 empty] | DFR |  | DFR
RST
RAJASTHAN REGION
[6 empty] | RAJ FOREST | [17 empty] | RAJ FOREST
|  |  | 132 kV | [19 empty] | 400 kV
|  | 141/0 |  | 142/0 |  | 142/1 |  | 143/0 |  | 144/0 |  | 144A/0 |  | 144A/1 |  |  |  | 144A/2 |  | 144A/3 |  | 145/0 |  | 146/0 |  | 146/1 |  | 147/0 |  | 147/1
| ` | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
137 |  | 138 |  | 139 |  | 140 |  | 141 |  | 142 |  | 143 |  | 144 |  |  |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150 |  | 151
| 398.255 | Hold | 211.135 | Hold | 224 | Hold | 293.493 | Hold | 332.856 | Hold | 412.345 |  | 429.003 | Completed |  | 389 |  |  | 418 | Completed | 365.834 | Hold | 236.061 | Hold | 424.998 | Hold | 413.45 |  | 458 | Completed | 6 | 1 | 0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Completed |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DD45+0 |  | DD45+3 |  | DA-3 |  | DD45+0 |  | DC1+0 |  | DD45+6 |  | DA+0 |  |  |  | DA+3 |  | DB1+3 |  | DD60+18 |  | DD60+18 |  | DA+9 |  | DB2+6 |  | DA+9
[12 empty] | WET |  | WFR | [5 empty] | WET | [9 empty] | WET
[12 empty] | RST | [5 empty] | RST | [9 empty] | RST
RAJASTHAN REGION
[24 empty] | RAJ FOREST |  |  |  |  | MP FOREST
|  | 147A/0 |  | 147A/1 |  | 147A/2 |  | 147A/3 |  | 147A/4 |  | 147A/5 |  | 148/0 |  |  |  | 148/1 |  | 148A/0 |  | 148B/0 |  | 148B/1 |  | 148B/2 |  | 148C/0 |  | 149/0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  |  |  | 159 |  | 160 |  | 161 |  | 162 |  | 163 |  | 164 |  | 165
| 378.052 |  | 319 | Completed | 365 | Completed | 441 |  | 394 | Completed | 314 | Completed | 473.22 | Completed |  | 337 |  |  | 337.574 | Completed | 402.808 | Hold | 344 | Hold | 383 | Hold | 376.826 | Hold | 481.108 | Hold | 9 | 1 | 0
|  | 0 |  | Completed |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DB1+0 |  | DA-1.5 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+9 |  | DD60+6 |  |  |  | DA+0 |  | DB1+6 |  | DB1+0 |  | DA+0 |  | DA+6 |  | DB1+9 |  | DD45+9
|  | RST |  | DFR |  | WFR |  | RST |  | DFR |  | WFR |  | WFR | [5 empty] | WET
| RAJASTHAN REGION | [27 empty] | MP REGION
MP FOREST
|  | 149/1 |  | 149/2 |  | 149A/0 |  | 149B/0 |  | 149B/1 |  | 149B/2 |  | 149B/3 |  |  |  | 149B/4 |  | 150/0 |  | 150/1 |  | 150/2 |  | 150/3 |  | 150/4 |  | 150/5
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170 |  | 171 |  | 172 |  |  |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179
| 317 | Hold | 341 | Hold | 329.47 | Hold | 523.193 | Hold | 328 | Hold | 389 | Hold | 396 | Hold |  | 350 |  | Hold | 397.48 | ROW | 323.998 | Completed | 426 | Completed | 374 | Completed | 461 | Completed | 372 | Completed | 5 | 0 | 0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+3 |  | DA+9 |  | DC1+18 |  | DB1+25 |  | DB1+15 |  | DA+6 |  | DA+3 |  |  |  | DA+0 |  | DC1+0 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+6 |  | DA+6
[22 empty] | DFR |  | DFR |  | DFR |  | DRY |  | DFR
| MP REGION | [5 empty] | RAJASTHAN REGION
132 kV
|  | 151/0 |  | 152/0 |  | 152/1 |  | 152/2 |  | 152/3 |  | 152A/0 |  | 152A/1 |  |  |  | 152A/2 |  | 152A/3 |  | 152A/4 |  | 152A/5 |  | 152A/6 |  | 152A/7 |  | 152A/8
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
179 |  | 180 |  | 181 |  | 182 |  | 183 |  | 184 |  | 185 |  | 186 |  |  |  | 187 |  | 188 |  | 189 |  | 190 |  | 191 |  | 192 |  | 193
| 440.645 | Hold | 220.202 | Hold | 386.001 | Completed | 425 | Completed | 380 | Completed | 354.388 | Completed | 357.996 | Completed |  | 300 |  | Completed | 407 | Completed | 373 | Completed | 414 | Completed | 357 | Completed | 423 | Completed | 381 | Completed | 12 | 12 | 0
|  | 0 |  | 0 |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  |  |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DD45+3 |  | DD60+3 |  | DA+6 |  | DA+0 |  | DA-1.5 |  | DB1+0 |  | DA-3 |  |  |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+6
[6 empty] | DFR |  | DRY |  | DRY |  | DRY |  | DRY |  |  |  | DFR |  | DFR |  | DFR |  | DRY |  | DFR |  | DFR |  | WET
RAJASTHAN REGION
220 kV
|  | 152A/9 |  | 152A/10 |  | 152A/11 |  | 152A/12 |  | 153/0 |  | 154/0 |  | 154/1 |  |  |  | 154/2 |  | 154/3 |  | 154/4 |  | 154/5 |  | 155/0 |  | 155/1 |  | 155/2
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
193 |  | 194 |  | 195 |  | 196 |  | 197 |  | 198 |  | 199 |  | 200 |  |  |  | 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207
| 456 | Completed | 381 | Completed | 382 | Completed | 341 | ROW | 352.374 | Hold | 226.42 | Hold |  | Completed |  | 332 |  | Completed | 255 | Completed | 377 | ROW | 325 | Completed | 368.885 | ROW | 351.004 | Completed | 409 | Completed | 9 | 4 | 0
|  | 0 |  | Completed |  | Completed |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Completed |  | Completed
|  | DA+6 |  | DA+0 |  | DA-1.5 |  | DA-3 |  | DB1+6 |  | DB2+9 |  | DA-1.5 |  |  |  | DA-3 |  | DA-3 |  | DA+3 |  | DA+0 |  | DC2+0 |  | DA+0 |  | DA+3
|  | DRY |  | DRY |  | DFR | [7 empty] | DFR |  |  |  | DFR |  | DFR |  |  |  | DRY |  |  |  | DRY |  | DRY
RAJASTHAN REGION
[22 empty] | RAJ FOREST |  |  |  | MP FOREST
|  | 155/3 |  | 155/4 |  | 155/5 |  | 156/0 |  | 156/1 |  | 156/2 |  | 156/3 |  |  |  | 156/4 |  | 156/5 |  | 156/6 |  | 157/0 |  | 158/0 |  | 158/1 |  | 158/2
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
207 |  | 208 |  | 209 |  | 210 |  | 211 |  | 212 |  | 213 |  | 214 |  |  |  | 215 |  | 216 |  | 217 |  | 218 |  | 219 |  | 220 |  | 221
| 405 | Completed | 376 | Completed | 439 | Completed | 326.845 | 0 | 382.999 | Completed | 416 | ROW | 410 | Completed |  | 336 |  | Completed | 353 | Hold | 372 | Hold | 396.128 | Hold | 360.998 | Hold | 466 | Hold | 366 | Hold | 6 | 4 | 0
|  | Completed |  | Completed |  | Completed |  | 0 |  | 0 |  | 0 |  | Completed |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+0 |  | DA+0 |  | DA+3 |  | DC1+0 |  | DA+6 |  | DA+3 |  | DA+0 |  |  |  | DA-3 |  | DA+0 |  | DA+0 |  | DB2+9 |  | DC2+18 |  | DA+6 |  | DA+0
|  | DFR |  | DFR |  | DFR |  | 0 |  | DFR |  |  |  | DFR |  |  |  | DFR
| RAJASTHAN REGION | [24 empty] | MP REGION
|  | 158/3 |  | 159/0 |  | 159/1 |  | 159/2 |  | 159/3 |  | 160/0 |  | 160/1 |  |  |  | 160/2 |  | 160/3 |  | 160/4 |  | 160/5 |  | 161/0 |  | 161/1 |  | 161/2
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  |  |  | 229 |  | 230 |  | 231 |  | 232 |  | 233 |  | 234 |  | 235
| 375 | Hold | 374.761 | Completed | 390.999 |  | 397 | ROW | 336 | Completed | 383.419 | Completed | 323.001 | Completed |  | 335 |  | Completed | 337 | Completed | 339 |  | 351 |  | 377.051 | WIP | 413.999 |  | 418.004 | Completed | 11 | 3 | 0
|  | 0 |  | Completed |  | 0 |  | 0 |  | Completed |  | 0 |  | 0 |  |  |  | 0 |  | Completed |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA-1.5 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA-1.5 |  |  |  | DA-1.5 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+3 |  | DA+3 |  | DA+3
|  |  |  | DRY | [5 empty] | DRY |  | DRY |  | DRY |  |  |  | DRY |  | DRY |  | DRY |  | 0 | [5 empty] | DRY
[6 empty] | Reshmi Devi |  | Reshmi Devi | [13 empty] | Yash |  | Yash |  | Yash |  | Reshmi devi |  | Reshmi Devi
MP REGION
132 & 220 kV
|  | 161/3 |  | 161/4 |  | 161/5 |  | 162/0 |  | 162/1 |  | 162/2 |  | 163/0 |  |  |  | 164/0 |  | 164/1 |  | 164/2 |  | 164/3 |  | 164/4 |  | 164/5 |  | 164/6
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
235 |  | 236 |  | 237 |  | 238 |  | 239 |  | 240 |  | 241 |  | 242 |  |  |  | 243 |  | 244 |  | 245 |  | 246 |  | 247 |  | 248 |  | 249
| 417 |  | 383 | Completed | 426 |  | 410.673 | WIP | 385.997 | ROW | 305 | ROW | 430.97 | Hold |  | 302.489 |  | Hold | 352 | 0 | 370.997 |  | 402.003 |  | 398 |  | 420 | Completed | 400 |  | 8 | 1 | 0
|  | 0 |  | Completed |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+3 |  | DA+0 |  | DA+6 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DB1+18 |  |  |  | DC2+18 |  | DA+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+3
|  |  |  | DRY |  | 0 |  | 0 | [15 empty] | 0 |  | 0 |  | DRY |  | DRY
|  | Reshmi Devi |  |  |  | Reshmi Devi |  | Reshmi Devi | [13 empty] | Punia Const. |  | Punia Const. |  | Punia Const. |  |  |  | Saktawar
MP REGION
RC
|  | 164/7 |  | 164/8 |  | 165/0 |  | 165/1 |  | 165/2 |  | 165/3 |  | 165/4 |  |  |  | 165/5 |  | 165/6 |  | 166/0 |  | 166/1 |  | 166/2 |  | 166/3 |  | 166/4
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
249 |  | 250 |  | 251 |  | 252 |  | 253 |  | 254 |  | 255 |  | 256 |  |  |  | 257 |  | 258 |  | 259 |  | 260 |  | 261 |  | 262 |  | 263
| 419.997 |  | 417.003 | WIP | 422.12 | HOLD | 277.7 | WIP | 384.58 |  | 413.93 | WIP | 387.12 |  |  | 341.06 |  | WIP | 320.95 |  | 330.56 | WIP | 314 | 0 | 341.999 | 0 | 374.001 | WIP | 344 |  | 4 | 0 | 0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+3 |  | DA+6 |  | DB1+6 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA-3 |  |  |  | DA-3 |  | DA-3 |  | DC1+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+3
|  | 0 |  |  |  | ROUTE DIVERTED | [21 empty] | Garg |  | Garg
|  | Saktawar |  | Saktawar |  |  |  | Punia Const. |  |  |  | Punia Const. |  | Reshmi Devi |  |  |  | Reshmi Devi |  | Reshmi Devi |  | Reshmi Devi
MP REGION
132 kV
|  | 166/5 |  | 166/6 |  | 166/7 |  | 166/8 |  | 166/9 |  | 167/0 |  | 167/1 |  |  |  | 167/2 |  | 167/3 |  | 167/4 |  | 167/5 |  | 168/0 |  | 169/0 |  | 169/1
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
263 |  | 264 |  | 265 |  | 266 |  | 267 |  | 268 |  | 269 |  | 270 |  |  |  | 271 |  | 272 |  | 273 |  | 274 |  | 275 |  | 276 |  | 277
| 394 |  | 355 |  | 349 | WIP | 367 |  | 390 | WIP | 388.874 | 0 | 359.996 | 0 |  | 372 |  | 0 | 388 | 0 | 378 | WIP | 284 | WIP | 304.535 | Hold | 212.961 | Hold | 368.004 | WIP | 3 | 0 | 0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DB1+0 |  | DA+0 |  |  |  | DA+0 |  | DA+0 |  | DA+0 |  | DA-3 |  | DC2+0 |  | DC1+3 |  | DA-1.5
|  |  |  | 0 |  | 0 |  | 0 |  | 0 | [11 empty] | Rajaram |  | Rajaram | [5 empty] | MANOJ KUMAR
|  | Garg |  | GARG |  | Shree Shyam |  | Shree Shyam |  | Shree Shyam
MP REGION
|  | 169/2 |  | 169/3 |  | 169/4 |  | 169/5 |  | 169/6 |  | 169/7 |  | 169/8 |  |  |  | 169/9 |  | 170/0 |  | 170/1 |  | 170/2 |  | 170/3 |  | 170/4 |  | 170/5
|  | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
277 |  | 278 |  | 279 |  | 280 |  | 281 |  | 282 |  | 283 |  | 284 |  |  |  | 285 |  | 286 |  | 287 |  | 288 |  | 289 |  | 290 |  | 291
| 378 | WIP | 386 |  | 377 | WIP | 343 | 0 | 384 | 0 | 351 | 0 | 348 | 0 |  | 327 |  | 0 | 326.874 | 0 | 380.002 |  | 383 |  | 370 |  | 355 |  | 350 | WIP | 5 | 0 | 0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA-1.5 |  | DA+0 |  |  |  | DA-3 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA-3 |  | DA+0
|  | Manoj Kumar |  | Manoj Kumar |  | Manoj Kumar | [15 empty] | SHUKLA |  | SHUKLA |  | SHUKLA |  | SHUKLA |  | SHUKLA
MP REGION
|  | 170/6 |  | 170/7 |  | 170/8 |  | 170/9 |  | 170/10 |  | 171/0 |  | 171/1 |  |  |  | 171/2 |  | 171/3 |  | 171/4 |  | 171/5 |  | 171/6 |  | 171/7 |  | 171/8
|  | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
291 |  | 292 |  | 293 |  | 294 |  | 295 |  | 296 |  | 297 |  | 298 |  |  |  | 299 |  | 300 |  | 301 |  | 302 |  | 303 |  | 304 |  | 305
| 352 | 0 | 352 | WIP | 344 |  | 377 |  | 353 |  | 395.454 | WIP | 344.996 | WIP |  | 364 |  | WIP | 366 | 0 | 367 | 0 | 364 | 0 | 353 | 0 | 366 | 0 | 344 | 0 | 3 | 0 | 0 |  | 1
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA-3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA-3 |  |  |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA-3
|  |  |  | JSR |  | JSR |  | JSR |  | JSR |  | JSR |  | JSR |  |  |  | JSR
MP REGION
|  | 171/9 |  | 171/10 |  | 172/0 |  | 172/1 |  | 172/2 |  | 172/3 |  | 172/4 |  |  |  | 172/5 |  | 172/6 |  | 173/0 |  | 173/1 |  | 173/2 |  | 173/3 |  | 173/4
|  | #N/A | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
305 |  | 306 |  | 307 |  | 308 |  | 309 |  | 310 |  | 311 |  | 312 |  |  |  | 313 |  | 314 |  | 315 |  | 316 |  | 317 |  | 318 |  | 319
| 356 | 0 | 375 | 0 | 376.62 | 0 | 353 | WIP | 352 |  | 349 | WIP | 356 | WIP |  | 345 |  | 0 | 400 | 0 | 319.379 | 0 | 343.76 | WIP | 322.5 | WIP | 453.99 |  | 359.96 | WIP | 2 | 0 | 0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+0 |  | DA+0 |  | DB1+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+0 |  |  |  | DA+3 |  | DA+0 |  | DB2+0 |  | DA-3 |  | DA+3 |  | DA+3 |  | DA+3
[8 empty] | RAJARAM |  | RAJARAM |  | RAJARAM |  | RAJARAM | [9 empty] | Surinder |  | Surinder |  | Surinder |  | Surinder
MP REGION
Proposed NH
|  | 174A/0 |  | 174A/1 |  | 174A/2 |  | 174A/3 |  | 174A/4 |  | 174A/5 |  | 174B/0 |  |  |  | 175/0 |  | 175/1 |  | 175/2 |  | 175/3 |  | 175/4 |  | 176/0 |  | 176/1
|  | #N/A | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
319 |  | 320 |  | 321 |  | 322 |  | 323 |  | 324 |  | 325 |  | 326 |  |  |  | 327 |  | 328 |  | 329 |  | 330 |  | 331 |  | 332 |  | 333
| 447.53 | 0 | 399 | 0 | 353 | 0 | 355 | 0 | 331 | 0 | 335 | 0 | 326.811 | 0 |  | 248.908 |  | 0 | 368.001 | 0 | 341 | 0 | 323 | 0 | 333 | 0 | 323.564 | 0 | 414.996 | 0 | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DC1+3 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA-3 |  | DA-3 |  | DB2+0 |  |  |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA-3 |  | DC1+3 |  | DA+3
ROUTE DIVERTED
MP REGION
|  | 176/2 |  | 176/3 |  | 177/0 |  | 177/1 |  | 177/2 |  | 177/3 |  | 177/4 |  |  |  | 177/5 |  | 177/6 |  | 177/7 |  | 177/8 |  | 178/0 |  | 178/1 |  | 178/2
|  | #N/A | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
333 |  | 334 |  | 335 |  | 336 |  | 337 |  | 338 |  | 339 |  | 340 |  |  |  | 341 |  | 342 |  | 343 |  | 344 |  | 345 |  | 346 |  | 347
| 423.004 | 0 | 345 | 0 | 381.403 | 0 | 396.002 | 0 | 371 | 0 | 329 | 0 | 366 | 0 |  | 340 |  |  | 347 | 0 | 352 | 0 | 381 | 0 | 389.734 | 0 | 374.998 | Hold | 365.998 | 0 | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+3 |  | DA+0 |  | DB2+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  |  |  | DA-3 |  | DA-3 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+6
MP REGION
|  | 178/3 |  | 178/4 |  | 178/5 |  | 179/0 |  | 179/1 |  | 179/2 |  | 179/3 |  |  |  | 179/4 |  | 179/5 |  | 179/6 |  | 179/7 |  | 179/8 |  | 179/9 |  | 180/0
|  | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | #N/A |  | #N/A |  | #N/A
347 |  | 348 |  | 349 |  | 350 |  | 351 |  | 352 |  | 353 |  | 354 |  |  |  | 355 |  | 356 |  | 357 |  | 358 |  | 359 |  | 360 |  | 361
| 464 | 0 | 352.004 | Hold | 330 | Hold | 378.94 | 0 | 365 | 0 | 406 | 0 | 408.999 | 0 |  | 383.001 |  | 0 | 311 | 0 | 360 | 0 | 378 | 0 | 339 | 0 | 344.022 | 0 | 340.121 | Hold | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+3 |  | DA-3 |  | DA+0 |  | DC2+0 |  | DA+3 |  | DA+3 |  | DA+0 |  |  |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DC2+15
MP REGION
132 KV
|  | 181/0 |  | 181/1 |  | 181/2 |  | 181/3 |  | 181/4 |  | 181/5 |  | 181/6 |  |  |  | 182/0 |  | 182A/0 |  | 182B/0(DE) |  | GANTRY
|  | 0 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A
361 |  | 362 |  | 363 |  | 364 |  | 365 |  | 366 |  | 367 |  | 368 |  |  |  | 369 |  | 370 |  | 371 |  | 372
| 209.655 | Hold | 339 | 0 | 334 | 0 | 324 | 0 | 338 | 0 | 342 | 0 | 371 | 0 |  | 326.064 |  | Hold | 436.21 | 0 | 223.893 | 0 | 88.412 | 0 | [6 empty] | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0
|  | DD60+9 |  | DA+0 |  | DA-3 |  | DA-3 |  | DA+0 |  | DA-3 |  | DA-3 |  |  |  | DD60+6 |  | DD60+3 |  | DD60+0 |  | GANTRY
MP REGION
[30 empty] | TOTAL | 173 | 89 | 28 | 0
| LEGEND: | [18 empty] | PROGRESS AT A GLANCE :
[6 empty] | Stringing WIP |  | STRINGING COMPLETED |  |  |  | Front Clear For Stringing |  | Check Survey COMP. | [5 empty] | SR. NO. |  | ACTIVITY |  |  | UNIT | TOTAL |  | COMPLETED |  | BALANCE
|  |  |  | EREC. COMP. | [8 empty] | EREC. U/P | [19 empty] | `
|  |  |  | FDN. COMP. |  |  |  | SPAN |  | SPAN |  |  | FDN. U/P | [6 empty] | 1 |  | Foundation |  |  | Nos. | 372 |  | 173 |  | 199
EAR.COMP.
[20 empty] | 2 |  | Erection |  |  | Nos. | 372 |  | 28 |  | 344
[20 empty] | 3 |  | Stringing (Final Sag) |  |  | Km. | 136.594 |  | 0 |  | 136.594
[20 empty] | 4 |  | Earthing |  |  | Nos. | 372 |  | 103 |  | 269
| NH/SH Xing |  | RAILWAY Xing |  |  | 11/33 KV X-ING | [5 empty] | RIVER X-ING |  |  |  |  | METAL ROADS
[9 empty] | 66/132/ 220/400KV CROSSING | [7 empty] | TAR ROAD |  |  | 5 |  | Benching |  |  | Nos. |  |  |  |  | 0
[22 empty] | Revetment |  |  | Nos. |  |  |  |  | 0

## Supply Status (hidden)
Supply Status TA-505
SL | Supply | UOM | Total Qty | Total Supplied Qty. | Supply in L2 (till August-25)
1 | Stub | SET | 371 | 347 | 358
2 | Tower | SET | 371 | 286 | 270
3 | Conductor | KM | 4971 | 243 | 2250
4 | Insulator | NOS | 16332 | 4793 | 6986
5 | Hardware | % | 100% | 50% | 50%
6 | Earthwire | % | 100% | 45% | 45%
7 | OPGW | % | 100% | 0% | 0%

## Survey Details
765 KV D/C Hexa BEAWAR-MANDSAUR TL TA-505
Activity | Section | Length (km) | Site Survey Completed | Submitted to PGCIL | Approved by PGCIL | Remarks |  | Activity | Section | Length (km) | Site Survey Completed | Submitted to PGCIL | Approved by PGCIL | Remarks | A | B | C | D | Total
Route Alignment | AP100-Mndsr Gantry | 136.706 | 136.706 | 136.706 | 136.706 | Approved on Dtd 06-08-2024 | Rajasthan | Check Survey
Details Survey | AP99- AP100 | 3.478 | 3.478 | 3.478 | 3.478 | New Awarded Section. |  |  | AP99- AP100 | 3.478 | 3.478 | 3.478 | 3.478 | New Awarded Section.
| AP100 (CP)-AP103 | 4.3499 | 4.3499 | 4.3499 | 4.3499 | Approved on Dtd 7.09.24 |  |  | AP100 (CP)-AP103 | 4.3499 | 4.3499 | 4.3499 | 4.3499 | Approved on 28.09.24 | 8 |  | 3 | 1 | 12
| AP103-AP104 | 4.164 | 4.164 | 4.164 | 4.164 | Approved on Dtd 05.04.25 (ULE/RC/Benching) |  |  | AP103-AP104 | 4.164 | 4.164 | 4.164 | 4.164 | Approved on 05.04.25 | 9 |  |  | 3 | 12
| AP104-AP108 | 1.934 | 1.934 | 1.934 | 1.934 | Approved on Dtd 7.09.24 |  |  | AP104-AP108 | 1.934 | 1.934 | 1.934 | 1.934 | Approved on 28.09.24 | 3 |  | 1 | 2 | 6
| AP108-AP110 | 3.6176 | 3.6176 | 3.6176 | 3.6176 | Approved on Dtd 25.08.24 |  |  | AP108-AP110 | 3.6176 | 3.6176 | 3.6176 | 3.6176 | Approved on 31.08.24 | 8 |  | 2 |  | 10
| AP110-AP111 | 4.743 | 4.743 | 4.743 | 4.743 | Approved on Dtd 27.09.24 |  |  | AP110-AP111 | 4.743 | 4.743 | 4.743 | 4.743 | Approved on 28.09.24 | 10 | 2 |  |  | 12
| AP111-AP112 | 1.954 | 1.954 | 1.954 | 1.954 | Approved on Dtd 27.09.24 |  |  | AP111-AP112 | 1.954 | 1.954 | 1.954 | 1.954 | Approved on 07.10.24 | 4 |  |  | 1 | 5
| AP112-AP113 | 0.226 | 0.226 | 0.226 | 0.226 | Approved on Dtd 27.09.24 |  |  | AP112-AP113 | 0.226 | 0.226 | 0.226 | 0.226 | Approved on 06.01.25 |  |  |  | 1 | 1
| AP113-AP114 | 2.565 | 2.565 | 2.565 | 2.565 | Approved on Dtd 27.09.24 |  |  | AP113-AP114 | 2.565 | 2.565 | 2.565 | 2.565 | Approved on 07.10.24 | 6 |  | 1 |  | 7
| AP114-AP115 | 4.304 | 4.304 | 4.304 | 4.304 | Approved on Dtd 27.09.24 |  |  | AP114-AP115 | 4.304 | 4.304 | 4.304 | 4.304 | Approved on 14.10.24 | 10 |  |  | 1 | 11
| AP115-AP121 | 3.794 | 3.794 | 3.794 | 3.794 | Approved on Dtd 27.09.24 |  |  | AP115-AP121 | 3.794 | 3.794 | 3.794 | 3.794 | Approved. | 5 | 1 | 1 | 4 | 11
| AP121-AP122 | 0.36 | 0.36 | 0.36 | 0.36 | Approved on 31.05.25 |  |  | AP121-AP122 | 0.36 | 0.36 | 0.36 | 0.36 | Approved on 31.05.25 |  |  |  | 1 | 1
| AP122-AP124 | 1.54 | 1.54 | 1.54 | 1.54 | Approved on 31.05.25 |  |  | AP122-AP124 | 1.54 | 1.54 | 1.54 | 1.54 | Approved on 31.05.25 | 3 |  |  | 2 | 5
| AP124-AP125 | 0.249 | 0.249 | 0.249 | 0.249 | Approved on 31.05.25 |  |  | AP124-AP125 | 0.249 | 0.249 | 0.249 | 0.249 | Approved on 31.05.25 |  |  |  | 1 | 1
| AP125-AP126 | 0.74 | 0.74 | 0.74 | 0.74 | Approved on 31.05.25 |  |  | AP125-AP126 | 0.74 | 0.74 | 0.74 | 0.74 | Approved on 31.05.25 | 1 | 1 |  |  | 2
| AP126-AP128 | 3.397 | 3.397 | 3.397 | 3.397 | Approved on Dtd 21.09.24 |  |  | AP126-AP128 | 3.397 | 3.397 | 3.397 | 3.397 | Approved on 05.12.24 | 7 |  | 1 | 1 | 9
| AP128-AP129 | 0.422 | 0.422 | 0.422 | 0.422 | Approved on 30.08.24 |  |  | AP128-AP129 | 0.422 | 0.422 | 0.422 | 0.422 | Approved on 10.01.25 |  | 1 |  |  | 1
| AP-129- AP-129A | 0.804 | 0.804 | 0.804 | 0.804 | Approved on 31.01.25 |  |  | AP-129- AP-129A | 0.804 | 0.804 | 0.804 | 0.804 | Approved on 10.01.25 |  | 1 |  | 1
| AP129A-AP130 | 1.344 | 1.344 | 1.344 | 1.344 | Approved on 31.01.25 |  |  | AP129A-AP130 | 1.344 | 1.344 | 1.344 | 1.344 | Approved on 31.01.25 | 3 | 1 |  |  | 4
| AP130-AP132 | 1.62 | 1.62 | 1.62 | 1.62 | Approved on 30-08-24 |  |  | AP130-AP132 | 1.62 | 1.62 | 1.62 | 1.62 | Approved on 05.12.24 | 2 |  |  | 2 | 4
| AP132-AP133 | 0.373 | 0.373 | 0.373 | 0.373 | Approved on 30-08-24 |  |  | AP132-AP133 | 0.373 | 0.373 | 0.373 | 0.373 | Approved on 17.04.25 |  | 1 |  |  | 1
| AP133-AP134 | 0.552 | 0.552 | 0.552 | 0.552 | Approved on 30-08-24 |  |  | AP133-AP134 | 0.552 | 0.552 | 0.552 | 0.552 | Approved on 17.04.25 |  |  | 1 |  | 1
| AP134-AP135 | 0.397 | 0.397 | 0.397 | 0.397 | Approved on 31.01.25 |  |  | AP134-AP135 | 0.397 | 0.397 | 0.397 | 0.397 | Approved on 17.04.25 |  |  |  | 1 | 1
| AP135-AP136 | 1.599 | 1.599 | 1.599 | 1.599 | Approved on 31.01.25 |  |  | AP135-AP136 | 1.599 | 1.599 | 1.599 | 1.599 | Approved on 31.01.25 | 3 |  | 1 |  | 4
| AP136-AP137 | 2.412 | 2.412 | 2.412 | 2.412 | Approved on 31.01.25 |  |  | AP136-AP137 | 2.412 | 2.412 | 2.412 | 2.412 | Approved on 31.01.25 |  |  | 1 | 1
| AP137-AP137A | 0.567 | 0.567 | 0.567 | 0.567 | Approved on 31.01.25 |  |  | AP137-AP137A | 0.567 | 0.567 | 0.567 | 0.567 | Approved on 17.04.25 | 5 |  | 1 |  | 6
| AP137A-AP140 | 2.632 | 2.632 | 2.632 | 2.632 | Approved on 30-08-24 |  |  | AP137A-AP140 | 2.632 | 2.632 | 2.632 | 2.632 | Approved on 17.04.25 |  | 4 | 1
| AP140-AP141 | 0.838 | 0.838 | 0.838 | 0.838 | Approved on 30-08-24 |  |  | AP140-AP141 | 0.838 | 0.838 | 0.838 | 0.838 | Approved on 31.01.25 |  |  |  | 1
| AP141-AP144A | 1.474 | 1.474 | 1.474 | 1.474 | Approved on 30-08-24 |  |  | AP141-AP144A | 1.474 | 1.474 | 1.474 | 1.474 | Approved on 17.04.25 | 4 |  | 1 | 3 | 8
| AP144A-AP145 | 1.602 | 1.602 | 1.602 | 1.602 | Approved on 30-08-24 |  |  | AP144A-AP145 | 1.602 | 1.602 | 1.602 | 1.602 | Approved on 05.12.24 | 2 | 1 |  | 1 | 4
| AP145-AP147 | 1.075 | 1.075 | 1.075 | 1.075 | Approved on 03.09.24 |  |  | AP145-AP147 | 1.075 | 1.075 | 1.075 | 1.075 | Approved on 17.04.25 | 1 | 1 |  | 1 | 3
| AP147-AP148 | 3.142 | 3.142 | 3.142 | 3.142 | Approved on 03.09.24 |  |  | AP147-AP148 | 3.142 | 3.142 | 3.142 | 3.142 | Approved on 05.12.24 | 6 | 1 |  | 1 | 8
| AP148-AP148A | 0.675 | 0.675 | 0.675 | 0.675 | Approved on 31.01.25 |  |  | AP148-AP148A | 0.675 | 0.675 | 0.675 | 0.675 | Approved on 31.01.25 |  | 1
| AP148A-AP149 | 1.987 | 1.987 | 1.987 | 1.987 | Approved on 31.01.25 |  |  | AP148A-AP149 | 1.987 | 1.987 | 1.987 | 1.987 | Approved on 17.04.25 | 3 | 2 |  | 1 | 6
| AP149-AP150 | 3.371 | 3.371 | 3.371 | 3.371 | Approved on 31.01.25 | MP & RAJ |  | AP149-AP150 | 3.371 | 3.371 | 3.371 | 3.371 | Approved on 17.04.25 | 5 | 2 | 2 |  | 9
| AP150-AP151 | 2.398 | 2.398 | 2.398 | 2.398 | Approved on Dtd 03.09.24 | Rajasthan |  | AP150-AP151 | 2.398 | 2.398 | 2.398 | 2.398 | Approved on 07.10.24 | 5 |  |  | 1 | 6
| AP151-AP152 | 0.22 | 0.22 | 0.22 | 0.22 | Approved on Dtd 21.09.24 |  |  | AP151-AP152 | 0.22 | 0.22 | 0.22 | 0.22 | Approved on 31.05.25 |  |  |  | 1 | 1
| AP152-AP152A | 1.545 | 1.545 | 1.545 | 1.545 | Approved on Dtd 21.09.24 |  |  | AP152-AP152A | 1.545 | 1.545 | 1.545 | 1.545 | Approved on 07.10.24 | 3 | 1 |  |  | 4
| AP152A-AP153 | 4.925 | 4.925 | 4.925 | 4.925 | Approved on Dtd 21.09.24 |  |  | AP152A-AP153 | 4.925 | 4.925 | 4.925 | 4.925 | Approved on 07.10.24 | 12 | 1 |  |  | 13
| AP153-AP154 | 0.226 | 0.226 | 0.226 | 0.226 | Approved on Dtd 21.09.24 |  |  | AP153-AP154 | 0.226 | 0.226 | 0.226 | 0.226 | Approved on 31.05.25 |  | 1 |  |  | 1
| AP154-AP155 | 2.01 | 2.01 | 2.01 | 2.01 | Approved on Dtd 21.09.24 |  |  | AP154-AP155 | 2.01 | 2.01 | 2.01 | 2.01 | Approved on 05.12.24 | 5 |  | 1 |  | 6
| AP155-AP156 | 2.307 | 2.307 | 2.307 | 2.307 | Approved on Dtd 03.09.24 |  |  | AP155-AP156 | 2.307 | 2.307 | 2.307 | 2.307 | Approved on 05.12.24 | 5 |  | 1 |  | 6
| AP156-AP156/4 | 1.494 | 1.494 | 1.494 | 1.494 | Approved on Dtd 03.09.24 |  |  | AP156-AP156/4 | 1.494 | 1.494 | 1.494 | 1.494 | Approved on 06-01-2025 | 6 |  |  |  | 6
| AP156/4-AP157/0 | 1.172 | 1.172 | 1.172 | 1.172 | Approved on Dtd 03.09.24 |  |  | AP156/4-AP157/0 | 1.172 | 1.172 | 1.172 | 1.172 | Approved. |  | 1
| AP157-AP158 | 0.361 | 0.361 | 0.361 | 0.361 | Approved on 03.09.24 | MP |  | AP157-AP158 | 0.361 | 0.361 | 0.361 | 0.361 | Approved on 17.04.25 |  |  | 1
| AP158-AP159 | 1.582 | 1.582 | 1.582 | 1.582 | Approved on 31.01.25 |  |  | AP158-AP159 | 1.582 | 1.582 | 1.582 | 1.582 | Approved on 17.04.25 |  | 1
| AP159-AP161 | 3.569 | 3.569 | 3.569 | 3.569 | Approved on 31.01.25 |  |  | AP159-AP161 | 3.569 | 3.569 | 3.569 | 3.569 | Approved on 31.01.25 | 11 | 2 |  |  | 13
| AP161-AP162 | 2.469 | 2.469 | 2.469 | 2.469 | Approved on 08.02.25 |  |  | AP161-AP162 | 2.469 | 2.469 | 2.469 | 2.469 | Approved on 08.02.25 | 5 | 1 |  |  | 6
| AP162-AP165 | 5.006 | 5.006 | 5.006 | 5.006 | Approved on 08.02.25 |  |  | AP162-AP165 | 5.006 | 5.006 | 5.006 | 5.006 | Approved on 08.02.25 | 10 | 2 | 1 |  | 13
| AP165-AP166 | 2.551 | 2.551 | 2.551 | 2.551 | Approved on 04.03.25 |  |  | AP165-AP166 | 2.551 | 2.551 | 2.551 | 2.551 | Approved on 04.03.25 | 5 |  | 1 |  | 6
| AP166-AP168 | 5.742 | 5.742 | 5.742 | 5.742 | Approved on 15.02.25 |  |  | AP166-AP168 | 5.742 | 5.742 | 5.742 | 5.742 | Approved on 15.02.25 | 14 | 1 | 1 |  | 16
| AP168-AP169 | 0.213 | 0.213 | 0.213 | 0.213 | Approved on 15.02.25 |  |  | AP168-AP169 | 0.213 | 0.213 | 0.213 | 0.213 | Approved on 15.02.25 |  |  | 1 |  | 1
| AP169-AP170 | 3.589 | 3.589 | 3.589 | 3.589 | Approved on 15.02.25 |  |  | AP169-AP170 | 3.589 | 3.589 | 3.589 | 3.589 | Approved on 15.02.25 | 9 | 1 |  |  | 10
| AP170-AP174A | 11.856 | 11.856 | 11.856 | 11.856 | Approved on 15.02.25 |  |  | AP170-AP174A | 11.856 | 11.856 | 11.856 | 11.856 | Approved on 15.02.25 | 30 | 3 | 1 |  | 34
| AP174A-AP176 | 4.442 | 4.442 | 4.442 | 4.442 | Approved on 04.03.25 |  |  | AP174A-AP176 | 4.442 | 4.442 | 4.442 | 4.442 | Approved on 04.03.25 | 5 | 2 | 1 |  | 8
| AP176-AP178 | 4.837 | 4.837 | 4.837 | 4.837 | Approved on 15.02.25 |  |  | AP176-AP178 | 4.837 | 4.837 | 4.837 | 4.837 | Approved on 15.02.25 | 15 | 2 |  |  | 17
| AP178-AP180 | 5.902 | 5.902 | 5.902 | 5.902 | Approved on 15.02.25 |  |  | AP178-AP180 | 5.902 | 5.902 | 5.902 | 5.902 | Approved on 15.02.25 | 14 |  | 2 |  | 16
| AP180-AP181 | 0.209 | 0.209 | 0.209 | 0.209 | Approved on 05.04.25 |  |  | AP180-AP181 | 0.209 | 0.209 | 0.209 | 0.209 | Approved on 05.04.25 |  |  |  | 1
| AP181-AP182B | 2.576 | 2.576 | 2.576 | 2.576 | Approved on 09.08.25. |  |  | AP181-AP-182B | 2.576 | 2.576 | 2.576 | 2.576 | Approved on 09.08.25. | 6 |  |  | 3 | 9
| AP182B- Mandsaur GSS | 0.088 | 0.088 | 0.088 | 0.088 | Approved. |  |  | AP182B- Mandsaur GSS | 0.088 | 0.088 | 0.088 | 0.088 | Approved.
|  | 139.5905 | 139.5905 | 139.5905 | 139.5905 |  |  |  |  | 139.5905 | 139.5905 | 139.5905 | 139.5905 |  | 268 | 39 | 28 | 37 | 372
|  | Balance DS Approval Pending |  |  | 0 |  |  |  |  | Balance CS to be done at Site |  |  | 0
[10 empty] | Balance CS to Be Submitted To Client |  |  | 0
[10 empty] | Balance CS to be approved By Client |  |  | 0
[10 empty] | Cumm/Total CS Pending |  |  | 0
SL | Description | UOM | Length | Balance Survey Approval Pending | Remarks
1 | Detailed Survey | KM | 139.5905
1A | Completed |  | 139.5905
1B | Submitted |  | 139.5905
1C | Approved |  | 139.5905 | 0
2 | Check Survey |  | 139.5905
2A | Completed |  | 139.5905
2B | Submitted |  | 139.5905
2C | Approved |  | 139.5905 | 0

## Statutory Detail-TA 505 (hidden)
Name of Transmission Line: 765 KV D/C BEAWAR - MANDSAUR TL PKG TL02 (KEC)
Sl No | Power Line Crossing |  |  | National Highway Crossing | Rail Line | Gas Pipe Line | Forest Crossings | Total
| 132KV | 220KV | 400KV
1 | 6 | 4 | 2 | 2 | 1 | 1 | 10 | 26
|  | SL.No | Summary | Total Nos | Proposals Submitted | Approval/NOC Obtained | Balance | Remarks
|  | 1 | Power Line Crossings | 12 | 12 | 0 | 12 | 8 Nos approval awaiting with PGCIL & 4 Nos approval awaiting with the Concerned Authority. Expected by 10.07.2025.
|  | 2 | Forest Crossings | 10 | 10 | 0 | 10 | Raj-7.272 Km (19 Towers) & MP-2.102 Km (6 Towers). PSE-1 approved, PSE-2 U/P.
|  | 4 | NH Crossings | 2 | 2 | 0 | 2 | Approval Awaiting from NHAI. Expected by 15.07.2025. Site Visit Pending for NH in MP Portion.
|  | 5 | Railway Crossing | 1 | 1 | 0 | 1 | Awaiting Approval from DRM- Kota. Expected by 20.07.2025.
|  | 6 | Gas Pipe Line | 1 | 1 | 0 | 1 | Awaiting approval from Concerned Authority. Expected by 22.07.2025.
|  | Total |  | 26 | 26 | 0 | 26
765 kV D/C BEAWAR - MANDSAUR TL
CROSSING PROPOSAL STATUS
Sl No. | Name of Crossing | Crossing Section 765 KV DC BMTL PROPOSED LINE | Type of Tower | Owner | PROPOSAL STATUS
1 | GAS PIPE LINE | AP-106 | DD60+0 | GAIL | Online Submission Completed. Site Visit done.
|  | AP-108 | DD45+0
2 | 400 KV D/C RAP-KNK TL (power line) | AP-112 | DD60+18 | POWERGRID | Site visit Completed,Awaiting for final Approval Of PGCIL.
|  | AP-113 | DD60+9 (WITH 3 M RC)
3 | 132 KV D/C BASSI-AKK TL (power line) | AP-115 | DD60+3 | RVNL | Site visit Completed,Awaiting for final Approval Of RVNL
|  | AP-116 | DD45+3
4 | 220 KV D/C RPB-CGH TL (power line) | AP-117 | DD45+6 | POWERGRID | Site visit Completed,Awaiting for final Approval Of PGCIL
|  | AP-118 | DD60+6
5 | 220 KV S/C RPH-UPD TL (power line) | AP-119 | DC2+0 | POWERGRID | Site visit Completed,Awaiting for final Approval Of PGCIL
|  | AP-120 | DD45+3
6 | SINGLE TRACK RAILWAY LINE CROSSING(WCR,KOTA DIVISION) | AP-122 | DD60+3 | INDIAN RAILWAY | Online Submission Completed. Site Visit done.
|  | AP-123 | DD60+6
7 | NH-27 | AP 124 | DD45+0 | NHAI (UDAIPUR) | Online Submission completed, hardcopy submitted at NHAI office udaipur. After joint visit, NHAI proposed for revision of route with crossing angle of 90 degree.
|  | AP 125 | DD60+0
8 | 132 KV SC VIJAYPUR-NIMBAHERA TL (power line) | AP-141 | DD45+0 | RVNL | Site visit Completed,awaiting for final Approval Of RVNL
|  | AP-142 | DD45+3
9 | 400 KV D/C NMC-CHR TL (power line) | AP-145 | DD60+18 | POWERGRID | Site visit Completed,awaiting for final Approval Of PGCIL |  |  |  | Forest & RC
|  | AP-146 | DD60+18
10 | 132 KV SC KANERA-NIMBAHERA TL (power line) | AP-151 | DD45+3 | RVNL | Site visit Completed,awaiting for final Approval Of RRVNL
|  | AP-152 | DD60+6
11 | 220 kV S/C RAPP-DEBARI TL (power line) | AP-153 | DB1+6 | RVNL | Site visit Completed,awaiting for final Approval Of RVNL
|  | AP-154 | DB2+9
12 | 132 kV D/C NEEMUCH-RATANGARH TL (power line) | AP-163 | DB1+18 | MPPTCL | Document submitted to MPPTCL, joint visit Completed.
|  | AP-164 | DC2+18
13 | 220 kV D/C NEEMUCH-RATANGARH TL (power line) | AP-163 | DB1+18 | MPPTCL | Document submitted to MPPTCL, joint visit completed.
|  | AP-164 | DC2+18
14 | NH CROSSING | AP-174B | DB2+0 | NHAI | Online submission completed, offline hardcopy submission U/P.
|  | AP-175 | DB1+0
15 | 132 KV S/C NEEMUCH-MANASA TL (power line) | AP-168 | DC2+0 | MPPTCL | Document submitted to MPPTCL, joint visit completed.
|  | AP-169 | DC1+3
16 | 132 KV D/C NEEMUCH-BUDHA TL (power line) | AP-180 | DC2+15 | MPPTCL | Document submitted to MPPTCL, joint visit completed.
|  | AP-181 | DD60+9

## X-ing Detail New
Name of Transmission Line: 765 KV D/C BEAWAR - MANDSAUR TL PKG TL02 (KEC)
Sl No | Power Line Crossing |  |  | National Highway Crossing | Rail Line | Gas Pipe Line | Forest Crossings | Total
| 132KV | 220KV | 400KV
1 | 6 | 4 | 2 | 2 | 1 | 1 | 10 | 26
|  | SL.No | Summary | Total Nos | Proposals Submitted | Approval/NOC Obtained | Balance | Remarks
|  | 1 | Power Line Crossings | 12 | 12 | 12 | 0 | All 12 PLCs are approved.
|  | 2 | Forest Crossings | 10 | 10 | 0 | 10 | Stage I approval received. Working Permission Expected by last week of November-25.
|  | 3 | NH Crossings | 2 | 2 | 0 | 2 | Approval Awaited. Expected by 15.11.2025.
|  | 4 | Railway Crossing | 1 | 1 | 1 | 0 | Approved.
|  | 5 | Gas Pipe Line | 1 | 1 | 1 | 0 | Approved.
|  | Total |  | 26 | 26 | 14 | 12
765 kV D/C BEAWAR - MANDSAUR TL
CROSSING PROPOSAL STATUS
Sl No. | Name of Crossing | Crossing Section 765 KV DC BMTL PROPOSED LINE | Type of Tower | Owner | PROPOSAL STATUS
1 | GAS PIPE LINE | AP-106 | DD60+0 | GAIL | Online Submission Completed. Site Visit done.
|  | AP-108 | DD45+0
2 | 400 KV D/C RAP-KNK TL (power line) | AP-112 | DD60+18 | POWERGRID | Site visit Completed,Awaiting for final Approval Of PGCIL.
|  | AP-113 | DD60+9 (WITH 3 M RC)
3 | 132 KV D/C BASSI-AKK TL (power line) | AP-115 | DD60+3 | RVNL | Site visit Completed,Awaiting for final Approval Of RVNL
|  | AP-116 | DD45+3
4 | 220 KV D/C RPB-CGH TL (power line) | AP-117 | DD45+6 | POWERGRID | Site visit Completed,Awaiting for final Approval Of PGCIL
|  | AP-118 | DD60+6
5 | 220 KV S/C RPH-UPD TL (power line) | AP-119 | DC2+0 | POWERGRID | Site visit Completed,Awaiting for final Approval Of PGCIL
|  | AP-120 | DD45+3
6 | SINGLE TRACK RAILWAY LINE CROSSING(WCR,KOTA DIVISION) | AP-122 | DD60+3 | INDIAN RAILWAY | Online Submission Completed. Site Visit done.
|  | AP-123 | DD60+6
7 | NH-27 | AP 124 | DD45+0 | NHAI (UDAIPUR) | Online Submission completed, hardcopy submitted at NHAI office udaipur. After joint visit, NHAI proposed for revision of route with crossing angle of 90 degree.
|  | AP 125 | DD60+0
8 | 132 KV SC VIJAYPUR-NIMBAHERA TL (power line) | AP-141 | DD45+0 | RVNL | Site visit Completed,awaiting for final Approval Of RVNL
|  | AP-142 | DD45+3
9 | 400 KV D/C NMC-CHR TL (power line) | AP-145 | DD60+18 | POWERGRID | Site visit Completed,awaiting for final Approval Of PGCIL |  |  |  | Forest & RC
|  | AP-146 | DD60+18
10 | 132 KV SC KANERA-NIMBAHERA TL (power line) | AP-151 | DD45+3 | RVNL | Site visit Completed,awaiting for final Approval Of RRVNL
|  | AP-152 | DD60+6
11 | 220 kV S/C RAPP-DEBARI TL (power line) | AP-153 | DB1+6 | RVNL | Site visit Completed,awaiting for final Approval Of RVNL
|  | AP-154 | DB2+9
12 | 132 kV D/C NEEMUCH-RATANGARH TL (power line) | AP-163 | DB1+18 | MPPTCL | Document submitted to MPPTCL, joint visit Completed.
|  | AP-164 | DC2+18
13 | 220 kV D/C NEEMUCH-RATANGARH TL (power line) | AP-163 | DB1+18 | MPPTCL | Document submitted to MPPTCL, joint visit completed.
|  | AP-164 | DC2+18
14 | NH CROSSING | AP-174B | DB2+0 | NHAI | Online submission completed, offline hardcopy submission U/P.
|  | AP-175 | DB1+0
15 | 132 KV S/C NEEMUCH-MANASA TL (power line) | AP-168 | DC2+0 | MPPTCL | Document submitted to MPPTCL, joint visit completed.
|  | AP-169 | DC1+3
16 | 132 KV D/C NEEMUCH-BUDHA TL (power line) | AP-180 | DC2+15 | MPPTCL | Document submitted to MPPTCL, joint visit completed.
|  | AP-181 | DD60+9

## RC-ULE & Benching Status (hidden)
765 KV BEAWAR MANDSAUR TRANSMISSION LINE
Sr. No. | Loc No. | TOT | Description | Proposed Drawing | [8 empty] | FOREST,NON-FOREST | REMARKS
|  |  |  | Raised Chimeny Details (M) |  |  |  | ULE Details (M) |  |  |  | Benching Qty in Cu.M
|  |  |  | A | B | C | D | A | B | C | D
1 | 103/5 | DA+3 | Un-equal RC & Benching | [8 empty] | 28.315 | NON-FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
2 | 103/6A | DD45+0 | Benching | [8 empty] | 57.537 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
3 | 110A/2 | DA-1.5 | Benching | [8 empty] | 67.993 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
4 | 113/0 | DD60+9 | Equal - RC | 3 | 3 | 3 | 3 | - | - | - | - |  | NON-FOREST | Approved by PGCIL except the Benching Qty.
5 | 114/5 | DA+6 | Benching | [8 empty] | 21.816 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
6 | 126/1 | DA+9 | Un-equal RC | [8 empty] | 6.749 | NON-FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
7 | 127/1 | DA+0 | Benching | [8 empty] | 24.496 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
8 | 129/0 | DB1+3 | Un-equal RC & Benching | [8 empty] | 29.094 | FOREST | Cross arm strengthening required | bar: Raised Chimeny Details (M) D to ULE Details (M) D
9 | 129/1 | DB1+9 | Un-equal RC,ULE & Benching | 0 | 0 | 3 | 0 | 6 | 9 | 9 | 9 | 29.029 | FOREST | ULE used with+6 Body extn at A LEG
10 | 133/0 | DB2+3 | Un-equal RC & Benching | - | - | 1.5 |  | 1.5 | 3 | 3 | 3 | 13.174 | FOREST | Approved by PGCIL except the Benching Qty.
11 | 134/0 | DC1+0 | Un-Equal RC | [8 empty] | 14.43 | FOREST | Cross arm strengthening required | bar: Raised Chimeny Details (M) A to ULE Details (M) D
12 | 135/3 | DA+9 | Benching | [8 empty] | 28.233 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
13 | 137/0 | DD60+9 | Equal - RC | 4 | 4 | 4 | 4 | - | - | - | - |  | NON-FOREST | Approved by PGCIL except the Benching Qty.
14 | 137A/0 | DC2+25 | Un-equal RC & Benching | 1.5 | - | - | 1.5 | - | - | - | - | 50.169 | NON-FOREST | Cross arm strengthening required
15 | 138/0 | DB1+3 | Un-equal RC & Benching | 2 | - | - | - | 3 | 3 | 1.5 | 3 | 19.466 | NON-FOREST | Approved by PGCIL except the Benching Qty.
16 | 138/2 | DB1+9 | Equal - RC | 2 | 2 | 2 | 2 | - | - | - | - |  | FOREST | Approved by PGCIL except the Benching Qty.
17 | 138/3 | DA+3 | Un-equal RC & Benching | 2 | 1 | - | - | - | - | - | - | 18.894 | FOREST | Approved by PGCIL except the Benching Qty.
18 | 142/1 | DA-3 | Un-equal RC & Benching | [8 empty] | 36.184 | FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
19 | 143/0 | DD45+0 | Un-equal RC & Benching | - | - | 2 | 1 | -1.5 | 0 | 0 | 0 | 11.931 | FOREST | Approved by PGCIL except the Benching Qty.
20 | 144/0 | DC1+0 | Un-equal RC | - | - | - | - | - | - | 3 | 1.5 | 5.491 | FOREST | Approved by PGCIL except the Benching Qty.
21 | 146/0 | DD60+18 | Un-equal RC & Benching | 3 | - | 3 | 3 | - | - | - | - | 95.665 | FOREST | Approved by PGCIL except the Benching Qty.
22 | 148B/0 | DB1+0 | Un-equal RC & Benching | 1 | - | - | - | 1.5 | - | - | 1.5 | 16.606 | NON-FOREST | Approved by PGCIL except the Benching Qty.
23 | 148B/1 | DA+0 | Un-equal RC & Benching | [8 empty] | 28.18 | FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
24 | 148C/0 | DB1+9 | Un-equal RC & Benching | - | - | 2 | - | 7.5 | 9 | 9 | 9 | 4.629 | FOREST | Approved by PGCIL except the Benching Qty.
25 | 149B/2 | DA+6 | Un-equal RC & Benching | - | - | - | 1.5 | - | - | - | - | 20.512 | NON-FOREST | Approved by PGCIL except the Benching Qty.
26 | 149B/3 | DA+3 | Un-equal RC & Benching | - | - | 1 | 1.5 | - | - | - | - | 20.961 | NON-FOREST | Approved by PGCIL except the Benching Qty.
27 | 149B/4 | DA+0 | Un-equal RC | - | - | 2 | 2.5 | - | - | - | - | 7.259 | NON-FOREST | Approved by PGCIL except the Benching Qty.
28 | 157/0 | DB2+9 | Equal - RC | 3 | 3 | 3 | 3 | - | - | - | - | - | FOREST | Cross arm strengthening required
29 | 165/0 | DB1+6 | Un-equal RC | [8 empty] | 6.199 | NON-FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
30 | 178/2 | DA+6 | Un-equal RC | 1 | 1.5 | - | - | - | - | - | - | 4.779 | NON-FOREST | Approved by PGCIL except the Benching Qty.
31 | 182/0 | DD60+6 | Un-equal RC | [8 empty] | 19.489 | NON-FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
32 | 165/2 | DA+0 | Un-equal RC | [8 empty] | 6.408 | NON-FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D

## RC-ULE & Benching status New
765 KV BEAWAR MANDSAUR TRANSMISSION LINE
Sr. No. | Loc No. | TOT | Description | Proposed Drawing | [8 empty] | FOREST,NON-FOREST | REMARKS
|  |  |  | Raised Chimeny Details (M) |  |  |  | ULE Details (M) |  |  |  | Benching Qty in Cu.M
|  |  |  | A | B | C | D | A | B | C | D
1 | 103/5 | DA+3 | Un-equal RC & Benching | [8 empty] | 28.315 | NON-FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
2 | 103/6A | DD45+0 | Benching | [8 empty] | 57.537 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
3 | 110A/2 | DA-1.5 | Benching | [8 empty] | 67.993 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
4 | 113/0 | DD60+9 | Equal - RC | 3 | 3 | 3 | 3 | - | - | - | - |  | NON-FOREST | Approved by PGCIL except the Benching Qty.
5 | 114/5 | DA+6 | Benching | [8 empty] | 21.816 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
6 | 126/1 | DA+9 | Un-equal RC & Benching | [8 empty] | 6.749 | NON-FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
7 | 127/1 | DA+0 | Benching | [8 empty] | 24.496 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
8 | 129/0 | DB1+3 | Un-equal RC & Benching | [8 empty] | 29.094 | FOREST | Cross arm strengthening required | bar: Raised Chimeny Details (M) D to ULE Details (M) D
9 | 129/1 | DB1+9 | Un-equal RC,ULE & Benching | 0 | 0 | 3 | 0 | 6 | 9 | 9 | 9 | 29.029 | FOREST | ULE used with+6 Body extn at A LEG
10 | 133/0 | DB2+3 | Un-equal RC,ULE & Benching | - | - | 1.5 |  | 1.5 | 3 | 3 | 3 | 13.174 | FOREST | Approved by PGCIL except the Benching Qty.
11 | 134/0 | DC1+0 | Un-equal RC & Benching | [8 empty] | 14.43 | FOREST | Cross arm strengthening required | bar: Raised Chimeny Details (M) A to ULE Details (M) D
12 | 135/3 | DA+9 | Benching | [8 empty] | 28.233 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
13 | 137/0 | DD60+9 | Equal - RC | 4 | 4 | 4 | 4 | - | - | - | - |  | NON-FOREST | Approved by PGCIL except the Benching Qty.
14 | 137A/0 | DC2+25 | Un-equal RC & Benching | 1.5 | - | - | 1.5 | - | - | - | - | 50.169 | NON-FOREST | Cross arm strengthening required
15 | 138/0 | DB1+3 | Un-equal RC,ULE & Benching | 2 | - | - | - | 3 | 3 | 1.5 | 3 | 19.466 | NON-FOREST | Approved by PGCIL except the Benching Qty.
16 | 138/2 | DB1+9 | Equal - RC | 2 | 2 | 2 | 2 | - | - | - | - |  | FOREST | Approved by PGCIL except the Benching Qty.
17 | 138/3 | DA+3 | Un-equal RC & Benching | 2 | 1 | - | - | - | - | - | - | 18.894 | FOREST | Approved by PGCIL except the Benching Qty.
18 | 142/1 | DA-3 | Un-equal RC & Benching | [8 empty] | 36.184 | FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
19 | 143/0 | DD45+0 | Un-equal RC,ULE & Benching | - | - | 2 | 1 | -1.5 | 0 | 0 | 0 | 11.931 | FOREST | Approved by PGCIL except the Benching Qty.
20 | 144/0 | DC1+0 | ULE & Benching | - | - | - | - | - | - | 3 | 1.5 | 5.491 | FOREST | Approved by PGCIL except the Benching Qty.
21 | 146/0 | DD60+18 | Un-equal RC & Benching | 3 | - | 3 | 3 | - | - | - | - | 95.665 | FOREST | Approved by PGCIL except the Benching Qty.
22 | 148B/0 | DB1+0 | Un-equal RC,ULE & Benching | 1 | - | - | - | 1.5 | - | - | 1.5 | 16.606 | NON-FOREST | Approved by PGCIL except the Benching Qty.
23 | 148B/1 | DA+0 | Un-equal RC & Benching | [8 empty] | 28.18 | FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
24 | 148C/0 | DB1+9 | Un-equal RC, ULE & Benching | - | - | 2 | - | 7.5 | 9 | 9 | 9 | 4.629 | FOREST | Approved by PGCIL except the Benching Qty.
25 | 149B/2 | DA+6 | Un-equal RC & Benching | - | - | - | 1.5 | - | - | - | - | 20.512 | NON-FOREST | Approved by PGCIL except the Benching Qty.
26 | 149B/3 | DA+3 | Un-equal RC & Benching | - | - | 1 | 1.5 | - | - | - | - | 20.961 | NON-FOREST | Approved by PGCIL except the Benching Qty.
27 | 149B/4 | DA+0 | Un-equal RC & Benching | - | - | 2 | 2.5 | - | - | - | - | 7.259 | NON-FOREST | Approved by PGCIL except the Benching Qty.
28 | 157/0 | DB2+9 | Equal - RC | 3 | 3 | 3 | 3 | - | - | - | - | - | FOREST | Cross arm strengthening required
29 | 165/0 | DB1+6 | Un-equal RC & Benching | [8 empty] | 6.199 | NON-FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
30 | 178/2 | DA+6 | Un-equal RC & Benching | 1 | 1.5 | - | - | - | - | - | - | 4.779 | NON-FOREST | Approved by PGCIL except the Benching Qty.
31 | 182/0 | DD60+6 | Un-equal RC & Benching | [8 empty] | 15.88 | NON-FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to Raised Chimeny Details (M) B; ULE Details (M) A to ULE Details (M) D
32 | 165/2 | DA+0 | Un-equal RC & Benching | [8 empty] | 6.408 | NON-FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
33 | 181/6 | DA+6 | Un-equal RC & Benching | [8 empty] | 6.43 | NON-FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A

## FDN Drgs
765 KV BEAWAR MANDSAUR TRANSMISSION LINE
Required Foundation Drgs
Sr. No. | Loc No. | TOT | Classification | Description | Proposed Drawing | [7 empty] | FOREST,NON-FOREST | Remarks
[5 empty] | Raised Chimeny Details (M) |  |  |  | ULE Details (M)
[5 empty] | A | B | C | D | A | B | C | D
1 | 103/5 | DA+3 | DFR | Un-equal RC & Benching | [8 empty] | NON-FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
2 | 113/0 | DD60+9 | DFR | Equal - RC | 3 | 3 | 3 | 3 | - | - | - | - | NON-FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project.
3 | 126/1 | DA+9 | DFR & WFR | Un-equal RC & Benching | [8 empty] | NON-FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
4 | 129/0 | DB1+3 | DFR | Un-equal RC & Benching | [8 empty] | FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project. | bar: Raised Chimeny Details (M) D to ULE Details (M) D
5 | 129/1 | DB1+9 | DFR/WFR | Un-equal RC,ULE & Benching | 0 | 0 | 3 | 0 | 6 | 9 | 9 | 9 | FOREST | Foundation Drgs not Available.
6 | 133/0 | DB2+3 | DFR/WFR | Un-equal RC,ULE & Benching | - | - | 1.5 |  | 1.5 | 3 | 3 | 3 | FOREST | Foundation Drgs not Available.
7 | 134/0 | DC1+0 | DFR/WFR | Un-equal RC & Benching | [8 empty] | FOREST | Foundation Drgs not Available. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
8 | 137/0 | DD60+9 | DFR/WFR | Equal - RC | 4 | 4 | 4 | 4 | - | - | - | - | NON-FOREST | Foundation Drgs not Available.
9 | 137A/0 | DC2+25 | DFR/WFR | Un-equal RC & Benching | 1.5 | - | - | 1.5 | - | - | - | - | NON-FOREST | Foundation Drgs not Available.
10 | 138/0 | DB1+3 | DFR | Un-equal RC,ULE & Benching | 2 | - | - | - | 3 | 3 | 1.5 | 3 | NON-FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project.
11 | 138/2 | DB1+9 | DFR | Equal - RC | 2 | 2 | 2 | 2 | - | - | - | - | FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project.
12 | 138/3 | DA+3 | DFR | Un-equal RC & Benching | 2 | 1 | - | - | - | - | - | - | FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project.
13 | 142/1 | DA-3 | DFR | Un-equal RC & Benching | [8 empty] | FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
14 | 143/0 | DD45+0 | DFR/WFR | Un-equal RC,ULE & Benching | - | - | 2 | 1 | -1.5 | 0 | 0 | 0 | FOREST | Foundation Drgs not Available.
15 | 144/0 | DC1+0 | DFR | ULE & Benching | - | - | - | - | - | - | 3 | 1.5 | FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project.
16 | 146/0 | DD60+18 | DFR/WFR | Un-equal RC & Benching | 3 | - | 3 | 3 | - | - | - | - | FOREST | Foundation Drgs not Available.
17 | 148B/0 | DB1+0 | DFR | Un-equal RC,ULE & Benching | 1 | - | - | - | 1.5 | - | - | 1.5 | NON-FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project.
18 | 148B/1 | DA+0 | DFR | Un-equal RC & Benching | [8 empty] | FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
19 | 148C/0 | DB1+9 | DFR/WFR | Un-equal RC, ULE & Benching | - | - | 2 | - | 7.5 | 9 | 9 | 9 | FOREST | Foundation Drgs not Available.
20 | 149B/2 | DA+6 | DFR | Un-equal RC & Benching | - | - | - | 1.5 | - | - | - | - | NON-FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project.
21 | 149B/3 | DA+3 | DFR | Un-equal RC & Benching | - | - | 1 | 1.5 | - | - | - | - | NON-FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project.
22 | 149B/4 | DA+0 | DFR | Un-equal RC & Benching | - | - | 2 | 2.5 | - | - | - | - | NON-FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project.
23 | 157/0 | DB2+9 | DRY/DFR | Equal - RC | 3 | 3 | 3 | 3 | - | - | - | - | FOREST | Foundation Drgs not Available.
24 | 165/0 | DB1+6 | DFR | Un-equal RC & Benching | [8 empty] | NON-FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
25 | 178/2 | DA+6 | DFR | Un-equal RC & Benching | 1 | 1.5 | - | - | - | - | - | - | NON-FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project.
26 | 182/0 | DD60+6 | DFR & DRY | Un-equal RC & Benching | [8 empty] | NON-FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project. | bar: Raised Chimeny Details (M) A to Raised Chimeny Details (M) B; ULE Details (M) A to ULE Details (M) D
27 | 165/2 | DA+0 | DFR | Un-equal RC & Benching | [8 empty] | NON-FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
28 | 181/6 | DA+6 | DFR | Un-equal RC & Benching | [8 empty] | NON-FOREST | FDN Drg available, adoption approval required for TA-505, 765 KV BMTL Project. | bar: Raised Chimeny Details (M) A

## PRS-RC Stub (hidden)
765 KV BEAWAR MANDSAUR TRANSMISSION LINE
Sr. No. | Loc No. | TOT | Description | Raised Chimeny Details (M) |  |  |  | ULE Details (M) |  |  |  | REMARKS
|  |  |  | A | B | C | D | A | B | C | D
1 | 103/5 | DA+3 | Un-equal RC & Benching | [8 empty] | Approved by PGCIL except the Benching Qty. | R | bar: Raised Chimeny Details (M) A to ULE Details (M) D
4 | 113/0 | DD60+9 | Equal - RC | 3 | 3 | 3 | 3 | - | - | - | - | Approved by PGCIL except the Benching Qty.
6 | 126/1 | DA+9 | Un-equal RC & Benching | [8 empty] | Approved by PGCIL except the Benching Qty. | R | bar: Raised Chimeny Details (M) A to ULE Details (M) D
10 | 133/0 | DB2+3 | Un-equal RC,ULE & Benching | - | - | 1.5 |  | 1.5 | 3 | 3 | 3 | Approved by PGCIL except the Benching Qty.
13 | 137/0 | DD60+9 | Equal - RC | 4 | 4 | 4 | 4 | - | - | - | - | Approved by PGCIL except the Benching Qty.
15 | 138/0 | DB1+3 | Un-equal RC,ULE & Benching | 2 | - | - | - | 3 | 3 | 1.5 | 3 | Approved by PGCIL except the Benching Qty.
16 | 138/2 | DB1+9 | Equal - RC | 2 | 2 | 2 | 2 | - | - | - | - | Approved by PGCIL except the Benching Qty.
17 | 138/3 | DA+3 | Un-equal RC & Benching | 2 | 1 | - | - | - | - | - | - | Approved by PGCIL except the Benching Qty. | R
18 | 142/1 | DA-3 | Un-equal RC & Benching | [8 empty] | Approved by PGCIL except the Benching Qty. | R | bar: Raised Chimeny Details (M) A to ULE Details (M) D
19 | 143/0 | DD45+0 | Un-equal RC,ULE & Benching | - | - | 2 | 1 | -1.5 | 0 | 0 | 0 | Approved by PGCIL except the Benching Qty.
20 | 144/0 | DC1+0 | ULE & Benching | - | - | - | - | - | - | 3 | 1.5 | Approved by PGCIL except the Benching Qty.
21 | 146/0 | DD60+18 | Un-equal RC & Benching | 3 | - | 3 | 3 | - | - | - | - | Approved by PGCIL except the Benching Qty.
22 | 148B/0 | DB1+0 | Un-equal RC,ULE & Benching | 1 | - | - | - | 1.5 | - | - | 1.5 | Approved by PGCIL except the Benching Qty.
23 | 148B/1 | DA+0 | Un-equal RC & Benching | [8 empty] | Approved by PGCIL except the Benching Qty. | R | bar: Raised Chimeny Details (M) A to ULE Details (M) D
24 | 148C/0 | DB1+9 | Un-equal RC, ULE & Benching | - | - | 2 | - | 7.5 | 9 | 9 | 9 | Approved by PGCIL except the Benching Qty.
25 | 149B/2 | DA+6 | Un-equal RC & Benching | - | - | - | 1.5 | - | - | - | - | Approved by PGCIL except the Benching Qty. | R
26 | 149B/3 | DA+3 | Un-equal RC & Benching | - | - | 1 | 1.5 | - | - | - | - | Approved by PGCIL except the Benching Qty. | R
27 | 149B/4 | DA+0 | Un-equal RC & Benching | - | - | 2 | 2.5 | - | - | - | - | Approved by PGCIL except the Benching Qty. | R
29 | 165/0 | DB1+6 | Un-equal RC & Benching | [8 empty] | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
30 | 178/2 | DA+6 | Un-equal RC & Benching | 1 | 1.5 | - | - | - | - | - | - | Approved by PGCIL except the Benching Qty. | R
31 | 182/0 | DD60+6 | Un-equal RC & Benching | [8 empty] | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
32 | 165/2 | DA+0 | Un-equal RC & Benching | [8 empty] | Approved by PGCIL except the Benching Qty. | R | bar: Raised Chimeny Details (M) A to ULE Details (M) D

## PRS VS Supply
Supply Status TA-505
SL | Supply | UOM | Total Qty | PRS/QCS Raised | Total Supplied Qty. | Balance to be supplied against PRS | Supply in L2 (till Oct-25) | Remarks
1 | Stub | SET | 371 | 371 | 351 | 20 | 358
2 | Tower | SET | 371 | 362 | 330 | 32 | 270 | 1. Balance PRS of 9 Towers can be released after Mapping of BOM in SAP.
3 | Conductor | KM | 4971 | 4971 | 3404 | 1567 | 3000 | RAJ+MP | Insulator
4 | Insulator | NOS | 16332 | 16332 | 8593 | 7739 | 11643 | RAJ+MP | 160 KN | 210 KN | Total | Remarks
5 | Hardware | % | 100% | 100% | 70% | 50% | 75% | RAJ+MP | 1900 | 1900 | 3800 | MP
6 | Earthwire | % | 100% | 100% | 45% | 55% | 75% | RAJ | 1400 | 3393 | 4793 | RAJ
7 | OPGW | % | 100% | 97% | 0% | 97% | 0% |  | 3300 | 5293 | 8593
Balance PRS Detail
SL | Towers |  | Qty (Sets) | Stubs | Qty (Sets) | Remarks
1 | Auxiliary X-arm Tower |  | 1 | All Stubs PRS released. |  | Required Mapping of BOM in SAP, in order to proceed with the balance PRS release for Towers.
2 | X-arm Strengthening Tower |  | 4
3 | ULE Towers |  | 3
4 | DB1+18 |  | 0
5 | DB1+25 |  | 1
6 | DCT |  | 0
8 | Total |  | 9 | Total | 0

## QCS Status
Project | TA-505 | 765 KV D/C Hexa Beawar-Mandsaur T/L
SL | Item Description | Unit | LOA/Final/ LE Quantity | QCS Released Till Date |  |  |  | QCS Balance Release Plan
|  | Unit | Quantity | Released till Jan-25 | Released in Feb-25 | Released in Aug-25 | Balance to release | Sept-25 | Oct-25 | Nov-25
1 | 2 | 3 | 4 | 6 | 7 |  | 8 = (4-6-7) | 10 | 11 | 12
1 | CONDUCTOR (….....) | KM | 4970.6 | 1500 | 3470.6 |  | 0
2 | Insulators | Nos | 16332 | 4105 | 12227 |  | 0
3 | Hardwares & Accessories | % | 100 | 26 | 74 |  | 0
4 | GS EARTHWIRE | KM | 138.05 | 28 | 110.05 |  | 0
5 | OPGW FIBRE OPTIC CABLE | KM | 142.965 | 0 | 0 | 138.438 | 4.527 |  | 4.53
6 | OPGW Hardware | % | 100 | 0 | 0 | 100 | 0

## PRS & Supply-Tower & Stub
TOWER PRS -TA 505
Tower Type | Tower Type With Extn | Tentative Tower | Tower Released in (Rajasthan) | Tower Released in (MP) | Tower PRS Released Till Date | Tower Supplied in (RAJ) | Tower Supplied in (MP) | Total Tower Supplied till Date | Balance to be supplied against release qty. | Balance Tower to be released against Actual Qty. | To be accomodated from TA-504 | Balance | Remarks | Total Tower Tonnage | 17607
DA | DA-BTB | 268 | 141 | 127 | 268 | 133 | 127 | 260 | 8 | 0 |  | 0 |  | TOWER PRS RELEASED IN MT | 15312
| +0M Ext. DA-Type | 148 | 72 | 76 | 148 | 68 | 76 | 144 | 4 | 0 |  | 0 |  | TOTAL TOWERS IN NOS | 372
| +3M Ext. DA-Type | 60 | 39 | 21 | 60 | 36 | 20 | 56 | 4 | 0 |  | 0 |  | TOWER PRS RELEASED IN NOS | 337
| +6M Ext. DA-Type | 27 | 21 | 6 | 27 | 19 | 6 | 25 | 2 | 0 |  | 0
| +9M Ext. DA-Type | 12 | 10 | 2 | 12 | 8 | 2 | 10 | 2 | 0 |  | 0
| -1.5 M Ext. DA-Type | 16 | 11 | 5 | 16 | 11 | 5 | 16 | 0 | 0 |  | 0
| -3M Ext. DA-Type | 44 | 19 | 25 | 44 | 19 | 25 | 44 | 0 | 0 |  | 0
DB1 | DB1-BTB | 23 | 14 | 7 | 21 | 12 | 3 | 15 | 6 | 2 |  | 2
| +0M Ext. DB1-Type | 19 | 9 | 8 | 17 | 7 | 3 | 10 | 7 | 2 |  | 2
| +3M Ext. DB1-Type | 4 | 3 |  | 3 | 2 |  | 2 | 1 | 1 |  | 1
| +6M Ext. DB1-Type | 5 | 4 | 1 | 5 | 3 |  | 3 | 2 | 0 |  | 0
| +9M Ext. DB1-Type | 3 | 3 |  | 3 | 2 |  | 2 | 1 | 0 |  | 0
| +15M Ext. DB1-Type | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0
| +18M Ext. DB1-Type | 1 |  | 1 | 1 |  |  | 0 | 1 | 0 |  | 0 | RELEASED.
| +25M Ext. DB1-Type | 1 | 0 |  | 0 |  |  | 0 | 0 | 1 |  | 1 | MAPPING REQD.
DB2 | DB2-BTB | 16 | 8 | 7 | 15 | 6 | 6 | 12 | 3 | 1 |  | 1 | 1 NOS EXTRA B/B RELEASED IN SAP
| +0M Ext. DB2-Type | 14 | 7 | 6 | 13 | 6 | 4 | 10 | 3 | 1 |  | 1
| +3M Ext. DB2-Type | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 0 | 0 |  | 0
| +6M Ext. DB2-Type | 1 | 2 |  | 2 | 1 |  | 1 | 1 | -1 |  | -1
| +9M Ext. DB2-Type | 2 | 1 |  | 1 | 1 |  | 1 | 0 | 1 |  | 1
| +15M Ext. DB2-Type | 1 | 1 |  | 1 |  |  | 0 | 1 | 0 |  | 0
DC1 | DC1-BTB | 13 | 7 | 4 | 11 | 7 | 2 | 9 | 2 | 2 |  | 2
| +0M Ext. DC1-Type | 9 | 6 | 1 | 7 | 6 |  | 6 | 1 | 2 |  | 2
| +3M Ext. DC1-Type | 4 | 1 | 3 | 4 | 1 | 2 | 3 | 1 | 0 |  | 0
| +6M Ext. DC1-Type | 1 | 1 |  | 1 | 1 |  | 1 | 0 | 0 |  | 0 | To be checked in SAP-OK
| +9M Ext. DC1-Type | 1 | 1 |  | 1 | 1 |  | 1 | 0 | 0 |  | 0
| +18M Ext. DC1-Type | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
DC2 | DC2-BTB | 14 | 8 | 5 | 13 | 7 |  | 7 | 6 | 1 | 0 | 1
| +0M Ext. DC2-Type | 11 | 5 | 5 | 10 | 5 |  | 5 | 5 | 1 |  | 1 | To be Checked
| +3M Ext. DC2-Type | 3 | 3 |  | 3 | 2 |  | 2 | 1 | 0 |  | 0
| +6M Ext. DC2-Type | 0 |  |  | 0 |  |  | 0 | 0 | 0 |  | 0
| +9M Ext. DC2-Type | 1 | 1 |  | 1 | 1 |  | 1 | 0 | 0 |  | 0
| +15M Ext. DC2-Type | 1 |  | 1 | 1 |  |  | 0 | 1 | 0 |  | 0
| +18M Ext. DC2-Type | 3 |  | 2 | 2 |  |  | 0 | 2 | 1 |  | 1
| +25M Ext. DC2-Type | 1 | 1 |  | 1 |  |  | 0 | 1 | 0 |  | 0
| DCT (Full tower Set) | 1 | 1 |  | 1 |  |  |  |  | 0 |  | 0
DD45 | DD45-BTB | 18 | 17 | 0 | 17 | 13 |  | 13 | 4 | 1 |  | 1
| +0M Ext. DD45-Type | 12 | 10 | 0 | 10 | 5 |  | 5 | 5 | 2 |  | 2
| +3M Ext. DD45-Type | 6 | 6 |  | 6 | 5 |  | 5 | 1 | 0 |  | 0
| +6M Ext. DD45-Type | 2 | 2 |  | 2 | 2 |  | 2 | 0 | 0 |  | 0
| +9M Ext. DD45-Type | 2 | 2 | 0 | 2 | 1 |  | 1 | 1 | 0 |  | 0
| +18M Ext. DD45-Type | 0 |  |  | 0 |  |  | 0 | 0 | 0 |  | 0
DD60 | DD60-BTB | 17 | 13 | 3 | 16 | 11 | 3 | 14 | 2 | 1 | 0 | 1
| +0M Ext. DD60-Type | 14 | 11 | 2 | 13 | 10 | 2 | 12 | 1 | 1 |  | 1
| +3M Ext. DD60-Type | 3 | 2 | 1 | 3 | 2 | 1 | 3 | 0 | 0 |  | 0
| +6M Ext. DD60-Type | 6 | 5 |  | 5 |  |  | 0 | 5 | 1 |  | 1
| +9M Ext. DD60-Type | 3 | 2 | 1 | 3 | 2 |  | 2 | 1 | 0 |  | 0
| +18M Ext. DD60-Type | 3 | 3 |  | 3 | 3 |  | 3 | 0 | 0 |  | 0
| +25M Ext. DD60-Type | 0 |  |  | 0 |  |  | 0 | 0 | 0 |  | 0
| DD60+0 (Auxliary X-arm-Full Tower Set) | 1 |  |  | 0 |  |  | 0 | 0 | 1 |  | 1
|  | 371 | 209 | 153 | 362 | 189 | 141 | 330 | 31 | 9 | 0 | 9
STUB PRS - TA 505
Stub Type | Stub Type With Extn | Tentative Tower | Stub released in (Rajasthan) | Stub released in (MP) | Stub PRS Released till Date | Stub Supplied in (RAJ) | Stub Supplied in (MP) | Total Stub Supplied | Balance to be supplied against release qty. | Balance Stub to be released against Actual Qty. | To be accomodated from TA-504 | Balance | Remarks | Total STUB Tonnage | 470
STUB DA | DA UPTO 9 MTR | 268 | 143 | 125 | 268 | 139 | 124 | 263 | 5 | 0 |  | 0 | Additional PRS of 4.5 RC locs released. | STUB PRS RELEASED IN MT | 430
STUB DB1 | DB1 UPTO 9 MTR | 21 | 14 | 7 | 21 | 10 | 6 | 16 | 5 | 0 |  | 0 |  | TOTAL STUB IN NOS | 372
STUB DB2 | DB2 UPTO 9 MTR | 15 | 8 | 7 | 15 | 7 | 8 | 15 | 0 | 0 |  | 0 |  | STUB PRS RELEASED IN NOS | 348
STUB DB1 | DB1 +18/25 MTR | 2 | 1 | 1 | 2 |  |  | 0 | 2 | 0 |  | 0
STUB DB2 | DB2 +15 MTR | 1 | 1 |  | 1 |  |  | 0 | 1 | 0 |  | 0
STUB DC1 | DC1 UPTO 9 MTR | 13 | 9 | 4 | 13 | 9 | 4 | 13 | 0 | 0 |  | 0
STUB DC2 | DC2 UPTO 9 MTR | 10 | 8 | 2 | 10 | 7 | 2 | 9 | 1 | 0 |  | 0
STUB DC1 | DC1 +18/25 MTR | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0
STUB DC2 | DC2 +18/25 MTR | 4 | 1 | 3 | 4 | 1 | 2 | 3 | 1 | 0 |  | 0
STUB DC2 | DC2 +15 MTR | 1 |  | 1 | 1 |  |  | 0 | 1 | 0 |  | 0
STUB DD45 | DD45 UPTO 9 MTR | 18 | 17 | 1 | 18 | 15 | 1 | 16 | 2 | 0 |  | 0
STUB DD45 | DD45 +18/25 MTR |  |  |  | 0 |  |  | 0 | 0 | 0 |  | 0
STUB DD60 | DD60 UPTO 9 MTR | 15 | 12 | 3 | 15 | 12 | 2 | 14 | 1 | 0 |  | 0
STUB DD60 | DD60 +18/+25 MTR | 3 | 3 | 0 | 3 | 2 |  | 2 | 1 | 0 |  | 0
STUB DD60 | DD60 +30/+35 MTR |  |  |  | 0 |  |  | 0 | 0 | 0 |  | 0
|  | 371 | 217 | 154 | 371 | 202 | 149 | 351 | 20 | 0 | 0 | 0

## PRS-RC STUBS
SL. | Stub Type | Raised Chimney | Qty. of RC Extender (Pit Wise)
|  |  | Pit A | Pit B | Pit C | Pit D | Total
1 | DA | 1.0 M | 3 | 4 | 3 | 2 | 12
|  | 1.5 M |  | 1 |  | 2 | 3
|  | 2.0 M | 1 |  | 1 |  | 2
|  | 2.5 M |  |  |  | 1 | 1
2 | DB1 | 1.0 M | 1 |  | 1 | 1 | 3
|  | 2.0 M | 2 | 1 | 2 | 1 | 6
3 | DB2 | 1.5 M |  |  | 1 |  | 1
4 | DC1 | 1.0 M | 1 |  |  |  | 1 | PRS Pending due to SAP mapping issue
5 | DC2+25 | 1.5 M | 1 |  |  | 1 | 2 | PRS Pending due to SAP mapping issue
6 | DD1 | 1.0 M |  |  |  | 1 | 1
|  | 2.0 M |  |  | 1 |  | 1
7 | DD2 | 1.0 M | 1 | 1 |  |  | 2 | PRS pending.
|  | 3.0 M | 1 | 1 | 1 | 1 | 4
|  | 4.0 M | 1 | 1 | 1 | 1 | 4
8 | DD2 +18 | 3.0 M | 1 |  | 1 | 1 | 3
| DA+6 | 1.0 M | 1 |  |  |  | 1 | PRS pending.

## DRGS Req REV
765 KV BEAWAR MANDSAUR TRANSMISSION LINE
Sr. No. | Loc No. | TOT | Description | Proposed Drawing | [8 empty] | FOREST,NON-FOREST | REMARKS
|  |  |  | Raised Chimeny Details (M) |  |  |  | ULE Details (M) |  |  |  | Benching Qty in Cu.M
|  |  |  | A | B | C | D | A | B | C | D
1 | 103/5 | DA+3 | Un-equal RC & Benching | [8 empty] | 28.315 | NON-FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
2 | 103/6A | DD45+0 | Benching | [8 empty] | 57.537 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
3 | 110A/2 | DA-1.5 | Benching | [8 empty] | 67.993 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
4 | 113/0 | DD60+9 | Equal - RC | 3 | 3 | 3 | 3 | - | - | - | - |  | NON-FOREST | Approved by PGCIL except the Benching Qty.
5 | 114/5 | DA+6 | Benching | [8 empty] | 21.816 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
6 | 126/1 | DA+9 | Un-equal RC & Benching | [8 empty] | 6.749 | NON-FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
7 | 127/1 | DA+0 | Benching | [8 empty] | 24.496 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
8 | 129/0 | DB1+3 | Un-equal RC, Benching & X-Arm Strengthening. | [8 empty] | 29.094 | FOREST | Required Tower Structural Drgs & BOM | bar: Raised Chimeny Details (M) D to ULE Details (M) D
11 | 134/0 | DC1+0 | Un-equal RC, Benching & X-Arm Strengthening. | [8 empty] | 14.43 | FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
12 | 135/3 | DA+9 | Benching | [8 empty] | 28.233 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
13 | 137/0 | DD60+9 | Equal - RC | 4 | 4 | 4 | 4 | - | - | - | - |  | NON-FOREST
14 | 137A/0 | DC2+25 | Un-equal RC & Benching | 1.5 | - | - | 1.5 | - | - | - | - | 50.169 | NON-FOREST
15 | 138/0 | DB1+3 | Un-equal RC,ULE & Benching | 2 | - | - | - | 3 | 3 | 1.5 | 3 | 19.466 | NON-FOREST
16 | 138/2 | DB1+9 | Equal - RC | 2 | 2 | 2 | 2 | - | - | - | - |  | FOREST
17 | 138/3 | DA+3 | Un-equal RC & Benching | 2 | 1 | - | - | - | - | - | - | 18.894 | FOREST
18 | 142/1 | DA-3 | Un-equal RC & Benching | [8 empty] | 36.184 | FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
19 | 143/0 | DD45+0 | Un-equal RC,ULE & Benching | - | - | 2 | 1 | -1.5 | 0 | 0 | 0 | 11.931 | FOREST
20 | 144/0 | DC1+0 | ULE & Benching | - | - | - | - | - | - | 3 | 1.5 | 5.491 | FOREST
21 | 146/0 | DD60+18 | Un-equal RC & Benching | 3 | - | 3 | 3 | - | - | - | - | 95.665 | FOREST
25 | 149B/2 | DA+6 | Un-equal RC & Benching | - | - | - | 1.5 | - | - | - | - | 20.512 | NON-FOREST
26 | 149B/3 | DA+3 | Un-equal RC & Benching | - | - | 1 | 1.5 | - | - | - | - | 20.961 | NON-FOREST
27 | 149B/4 | DA+0 | Un-equal RC & Benching | - | - | 2 | 2.5 | - | - | - | - | 7.259 | NON-FOREST
28 | 157/0 | DB2+9 | Equal - RC & X- Arm Strengthening. | 3 | 3 | 3 | 3 | - | - | - | - | - | FOREST
29 | 165/0 | DB1+6 | Un-equal RC & Benching | [8 empty] | 6.199 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
30 | 178/2 | DA+6 | Un-equal RC & Benching | 1 | 1.5 | - | - | - | - | - | - | 4.779 | NON-FOREST
31 | 182/0 | DD60+6 | Un-equal RC & Benching | [8 empty] | 19.489 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
32 | 165/2 | DA+0 | Un-equal RC & Benching | [8 empty] | 6.408 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
| 158/0 | DC2+18 | X-Arm Strengthening.
| 136/4 | DC2+0 | Transposition Tower
| 163/0 | DB1+18 | Angle Tower
| 149B/0 | DB1+25 | Angle Tower
| 182B/0 | DD60+0 | Auxiliary X-arm
| 182B/0 | DD60+0 | Auxiliary X-arm
| 137A/0 | DC2+25 | RC Stub | Raised Chimeny Details (M) A: 1.5; Raised Chimeny Details (M) D: 1.5 |  |  | Required RC Stub drawings & BOM

## RC-ULE_DRGS (hidden)
Sr. No. | Loc No. | TOT | Description | Proposed Drawing | [8 empty] | FOREST,NON-FOREST | REMARKS
|  |  |  | Raised Chimeny Details (M) |  |  |  | ULE Details (M) |  |  |  | Benching Qty in Cu.M
|  |  |  | A | B | C | D | A | B | C | D
1 | 103/5 | DA+3 | Un-equal RC & Benching | [8 empty] | 28.315 | NON-FOREST | Required Stub & Structural Drawings. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
2 | 113/0 | DD60+9 | Equal - RC | 3 | 3 | 3 | 3 | - | - | - | - |  | NON-FOREST | Required Stub & Structural Drawings.
3 | 126/1 | DA+9 | Un-equal RC | [8 empty] | 6.749 | NON-FOREST | Required Stub & Structural Drawings. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
4 | 133/0 | DB2+3 | Un-equal RC & Benching | - | - | 1.5 |  | 1.5 | 3 | 3 | 3 | 13.174 | FOREST | Required Stub & Structural Drawings.
5 | 137/0 | DD60+9 | Equal - RC | 4 | 4 | 4 | 4 | - | - | - | - |  | NON-FOREST | Required Stub & Structural Drawings.
6 | 138/0 | DB1+3 | Un-equal RC & Benching | 2 | - | - | - | 3 | 3 | 1.5 | 3 | 19.466 | NON-FOREST | Required Stub & Structural Drawings.
7 | 138/2 | DB1+9 | Equal - RC | 2 | 2 | 2 | 2 | - | - | - | - |  | FOREST | Required Stub & Structural Drawings.
8 | 138/3 | DA+3 | Un-equal RC & Benching | 2 | 1 | - | - | - | - | - | - | 18.894 | FOREST | Required Stub & Structural Drawings.
9 | 142/1 | DA-3 | Un-equal RC & Benching | [8 empty] | 36.184 | FOREST | Required Stub & Structural Drawings. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
10 | 143/0 | DD45+0 | Un-equal RC & Benching | - | - | 2 | 1 | -1.5 | 0 | 0 | 0 | 11.931 | FOREST | Required Stub & Structural Drawings.
11 | 144/0 | DC1+0 | Un-equal RC | - | - | - | - | - | - | 3 | 1.5 | 5.491 | FOREST | Required Stub & Structural Drawings.
12 | 146/0 | DD60+18 | Un-equal RC & Benching | 3 | - | 3 | 3 | - | - | - | - | 95.665 | FOREST | Required Stub & Structural Drawings.
13 | 148B/0 | DB1+0 | Un-equal RC & Benching | 1 | - | - | - | 1.5 | - | - | 1.5 | 16.606 | NON-FOREST | Required Stub & Structural Drawings.
14 | 148B/1 | DA+0 | Un-equal RC & Benching | [8 empty] | 28.18 | FOREST | Required Stub & Structural Drawings. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
15 | 148C/0 | DB1+9 | Un-equal RC & Benching | - | - | 2 | - | 7.5 | 9 | 9 | 9 | 4.629 | FOREST | Required Stub & Structural Drawings.
16 | 149B/2 | DA+6 | Un-equal RC & Benching | - | - | - | 1.5 | - | - | - | - | 20.512 | NON-FOREST | Required Stub & Structural Drawings.
17 | 149B/3 | DA+3 | Un-equal RC & Benching | - | - | 1 | 1.5 | - | - | - | - | 20.961 | NON-FOREST | Required Stub & Structural Drawings.
18 | 149B/4 | DA+0 | Un-equal RC | - | - | 2 | 2.5 | - | - | - | - | 7.259 | NON-FOREST | Required Stub & Structural Drawings.
19 | 165/0 | DB1+6 | Un-equal RC | [8 empty] | 6.199 | NON-FOREST | Required Stub & Structural Drawings. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
20 | 178/2 | DA+6 | Un-equal RC | 1 | 1.5 | - | - | - | - | - | - | 4.779 | NON-FOREST | Required Stub & Structural Drawings.
21 | 182/0 | DD60+6 | Un-equal RC | [8 empty] | 19.489 | NON-FOREST | Required Stub & Structural Drawings. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
22 | 165/2 | DA+0 | Un-equal RC | [8 empty] | 6.408 | NON-FOREST | Required Stub & Structural Drawings. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
Sr. No. | TOT | Classification | Description | Raised Chimeny Details (M) A: RC detail; Raised Chimeny Details (M) B: Remarks
1 | DA(-3/-1.5/0) | DRY/WET/DFR/WFR/PS/FS | Un-equal RC | Raised Chimeny Details (M) A: upto 2.5 M; Raised Chimeny Details (M) B: Reqd. Foundation Drawings
2 | DA(Upto 9M) | DRY/WET/DFR/WFR/PS/FS | Un-equal RC | Raised Chimeny Details (M) A: upto 2 M; Raised Chimeny Details (M) B: Reqd. Foundation Drawings
3 | DB1( -3/6/-9) | DRY/WET/DFR/WFR/PS/FS | Un-equal RC | Raised Chimeny Details (M) A: upto 1M; Raised Chimeny Details (M) B: Reqd. Foundation Drawings
4 | DB1(Upto 9M) | DRY/WET/DFR/WFR/PS/FS | Un-equal RC | Raised Chimeny Details (M) A: upto 2 M; Raised Chimeny Details (M) B: Reqd. Foundation Drawings
5 | DB2(Upto 9M) | DRY/WET/DFR/WFR/PS/FS | Un-equal RC | Raised Chimeny Details (M) A: upto 1.5 M; Raised Chimeny Details (M) B: Reqd. Foundation Drawings
6 | DD45(-3/-1.5/0) | DRY/WET/DFR/WFR/PS/FS | Un-equal RC | Raised Chimeny Details (M) A: upto 2 M; Raised Chimeny Details (M) B: Reqd. Foundation Drawings
7 | DD60(Upto 9M) | DRY/WET/DFR/WFR/PS/FS | Un-equal RC | Raised Chimeny Details (M) A: upto 1 M; Raised Chimeny Details (M) B: Reqd. Foundation Drawings
8 | DD60(18/25 M) | DRY/WET/DFR/WFR/PS/FS | Un-equal RC | Raised Chimeny Details (M) A: upto 3 M; Raised Chimeny Details (M) B: Reqd. Foundation Drawings
9 | DB1(Upto 9M) | DRY/WET/DFR/WFR/PS/FS | Equal - RC | Raised Chimeny Details (M) A: upto 2 M; Raised Chimeny Details (M) B: Reqd. Foundation Drawings
10 | DD60(Upto 9M) | DRY/WET/DFR/WFR/PS/FS | Equal - RC | Raised Chimeny Details (M) A: upto 4 M; Raised Chimeny Details (M) B: Reqd. Foundation Drawings

## Revised Tower Qty (hidden)
TOWER QTY-REVISED (TA-505)
Tower Type | Tower Type With Extn | Tentative Tower
DA | DA-BTB | 268
| +0M Ext. DA-Type | 109
| +3M Ext. DA-Type | 60
| +6M Ext. DA-Type | 27
| +9M Ext. DA-Type | 12
| -1.5 M Ext. DA-Type | 16
| -3M Ext. DA-Type | 44
DB1 | DB1-BTB | 24
| +0M Ext. DB1-Type | 9
| +3M Ext. DB1-Type | 4
| +6M Ext. DB1-Type | 5
| +9M Ext. DB1-Type | 3
| +15M Ext. DB1-Type | 1
| +18M Ext. DB1-Type | 1
| +25M Ext. DB1-Type | 1
DB2 | DB2-BTB | 15
| +0M Ext. DB2-Type | 10
| +3M Ext. DB2-Type | 2
| +6M Ext. DB2-Type | 1
| +9M Ext. DB2-Type | 2
| +18M Ext. DB2-Type | 0
DC1 | DC1-BTB | 15
| +0M Ext. DC1-Type | 8
| +3M Ext. DC1-Type | 4
| +6M Ext. DC1-Type | 1
| +9M Ext. DC1-Type | 1
| +18M Ext. DC1-Type | 1
DC2 | DC2-BTB | 13
| +0M Ext. DC2-Type | 5
| +3M Ext. DC2-Type | 3
| +6M Ext. DC2-Type | 0
| +9M Ext. DC2-Type | 1
| +15M Ext. DC2-Type | 1
| +18M Ext. DC2-Type | 2
| +25M Ext. DC2-Type | 1
DD45 | DD45-BTB | 18
| +0M Ext. DD45-Type | 9
| +3M Ext. DD45-Type | 5
| +6M Ext. DD45-Type | 2
| +9M Ext. DD45-Type | 2
| +18M Ext. DD45-Type | 0
DD60 | DD60-BTB | 19
| +0M Ext. DD60-Type | 4
| +3M Ext. DD60-Type | 4
| +6M Ext. DD60-Type | 5
| +9M Ext. DD60-Type | 3
| +18M Ext. DD60-Type | 3
| +25M Ext. DD60-Type | 0
| +35M Ext. DD60-Type | 0
372
STUB QTY-REVISED (TA-505)
Stub Type | Tower Type With Extn | Tentative Tower
STUB DA | DA UPTO 9 MTR | 268
STUB DB1 | DB1 UPTO 9 MTR | 22
STUB DB2 | DB2 UPTO 9 MTR | 15
STUB DB1 | DB1 +18/25 MTR | 2
STUB DB2 | DB2 +18/25 MTR
STUB DC1 | DC1 UPTO 9 MTR | 14
STUB DC2 | DC2 UPTO 9 MTR | 10
STUB DC1 | DC1 +18/25 MTR | 1
STUB DC2 | DC2 +18/25 MTR | 3
STUB DD45 | DD45 UPTO 9 MTR | 18
STUB DD45 | DD45 +18/25 MTR
STUB DD60 | DD60 UPTO 9 MTR | 16
STUB DD60 | DD60 +18/+25 MTR | 3
STUB DD60 | DD60 +30/+35 MTR
372

## Comp. Plan (Revised) (hidden)
TA-505 - 765 KV D/C Beawar - Mandsaur TL
Sl No | Description | UOM | LoA Qty | Line Qty | Completed | Balance | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26 | Feb'26 | Mar'25 | Challenges for Completion of project ahead of Schedule
[5 empty] | 31.07.25 | 01.08.25 | Plan
1 | Detail Survey | Kms | 136 | 136 | 136 | 0
2 | Check Survey | Kms | 136 | 136 | 136 | 0
3 | Foundation | Nos. | 356 | 371 | 272 | 99 | 15 | 25 | 45 | 14 |  |  |  |  | Approx 10 kms of Forest Clearance awaited from PGCIL.
| Gang | [5 empty] | 5 | 8 | 12 | 5
4 | Erection | Nos. | 356 | 371 | 90 | 281 | 20 | 41 | 55 | 55 | 55 | 55
| Gang | [5 empty] | 10 | 14 | 14 | 14 | 14 | 14
5 | Stringing | Kms | 136 | 136 |  | 136 |  | 14 | 21 | 21 | 21 | 21 | 20 | 18
| Gang | [6 empty] | TSE2 M2 | TSE2 M2 | TSE2 M2 | TSE2 M2 | TSE2 M2 | TSE2 M2 | TSE2 M2
6 | OPGW | Kms | 136 | 136 |  | 136 |  |  |  | 25 | 30 | 30 | 30 | 21
| Gang | [8 empty] | 2 | 2 | 2 | 2 | 2

## Catch up Plan
400 KV D/C Beawar - Mandsaur TL
SL No. | Description | Approved Qty | Upto 30.09.2025 |  |  | 2025-10-01 |  |  | 2025-11-01 |  |  | 2025-12-02 |  |  | 2026-01-02 |  |  | 2026-02-02 |  |  | 2026-03-05 |  |  | 2026-04-05 |  |  | Total
|  |  | L2 Upto August | Actual | Balance | L2 | Achieved | Cumm. Backlog | L2 | Target | Cumm. Backlog | L2 | Target | Cumm. Backlog | L2 | Target | Cumm. Backlog | L2 | Target | Cumm. Backlog | L2 | Target | Cumm. Backlog | L2 | Target | Cumm. Backlog
A | Foundation | 379 | 295 | 283 | 96 | 25 | 14 | 82 | 20 | 45 | 37 | 15 | 37 | 0 | 3 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 379
Gang Deployment Plan | [6 empty] | 7 |  |  | 15 |  |  | 12
B | Erection | 379 | 218 | 127 | 252 | 30 | 30 | 222 | 30 | 55 | 167 | 30 | 55 | 112 | 30 | 56 | 56 | 20 | 56 | 0 | [6 empty] | 379
Gang Deployment Plan | [6 empty] | 10 |  |  | 15 |  |  | 15 |  |  | 15 |  |  | 15
C | Stringing | 140 | 54 | 0 | 140 | 11 |  | 140 | 11 | 5 | 135 | 11 | 28 | 107 | 11 | 34 | 73 | 10 | 34 | 39 | 10 | 39 | 0 |  |  | 0 | 140
Gang Deployment Plan (TSE+Manual) | [9 empty] | 1+3 |  |  | 3+3 |  |  | 3+3 |  |  | 3+3 |  |  | 3+3
Revenue (in Crores) |  | INR 83/109 | 25 |  |  |  | 6 |  |  | 6 |  |  | 7 |  |  | 7.5 |  |  | 7.5 |  |  | 7 |  |  |  |  | #REF!
Note: Revenue values are in Cr.

## AOT Plan (hidden)
Project Physical Progress: TA-505 765 Kv D/C Beawar-Mandsaur Transmission Line. | [32 empty] | Remarks
|  | Month No |  | M-1 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
Sr No. | Activity | As on 21 Mar 2021 | Total Qty | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-02 | 2024-11-02 | 2024-12-03 | 2025-01-03 | 2025-02-03 | 2025-03-06 | 2025-04-06 | 2025-05-07 | 2025-06-07 | 2025-07-08 | Cummulative Progress upto JULY-25 | 2025-08-08 | 2025-09-08 | 2025-10-09 | 2025-11-09 | 2025-12-10 | 2026-01-10 | 2026-02-10 | 2026-03-13 | 2026-04-13 | 2026-05-14 | 2026-06-14 | 2026-07-15 | 2022-10-01 | Total | Balance
1 | Detailed Survey | Original Plan | 136.581 | [27 empty] | 0 | -0.013 | 136.504/136.581 DS approval completed. Balance portion kept on hold due to non finalization of Gantry Bay Point.
|  | Current Plan | [28 empty] | 0
Month Start Plan
|  | Actual |  | M10: 136.594
No of Teams
2 | Check Survey | Original Plan | 136.581 | [27 empty] | 0 | 0.077 | 136.504/136.581 CS approval completed. Balance portion kept on hold due to non finalization of Gantry Bay Point.
|  | Current Plan | [28 empty] | 0
Month Start Plan
|  | Actual |  | M10: 136.504
No of Teams
1 | Foundation | As per L2 | 371 |  |  | 5 | 20 | 25 | 25 | 30 | 30 | 30 | 30 | 30 | 15 | 15 | 255 | 15 | 25 | 25 | 20 | 15 | 3 | [7 empty] | 613 | 99 | 25 Towers kept on hold due pending forest approval. . 4 Towers kept on hold due to NH X-ing. 2 Towers kept on hold due to Gas Pipe line. 05 Towers kept on hold due to pending approval of RC/ULE. Total Hold -36
|  | Plan | [15 empty] | 15 | 25 | 45 | 14 | [9 empty] | 99
|  | Gangs Required. | [15 empty] | 5 | 8 | 12 | 5
|  | Staff Required. | [15 empty] | 5 | 8 | 12 | 5
|  | Actual |  |  |  |  | 9 | 26 | 36 | 30 | 32 | 22 | 51 | 48 | 15 | 3 | 272
Gangs Available.
Staff Available.
2 | Erection | As per L2 | 371 |  |  |  |  | 5 | 18 | 25 | 25 | 25 | 25 | 25 | 15 | 15 | 178 | 15 | 25 | 30 | 30 | 30 | 30 | 20 | [6 empty] | 536 | 280 | Additional 5 Nos of Erection gangs likely to be mobilized by AUG-25 end.
|  | Plan | [15 empty] | 20 | 41 | 55 | 55 | 55 | 55 | [7 empty] | 281
|  | Gangs Required. | [15 empty] | 10 | 14 | 14 | 14 | 14 | 14
|  | Staff Required. | [15 empty] | 10 | 14 | 14 | 14 | 14 | 14
|  | Actual |  | M6: 4; M7: 7; M8: 11; M9: 19; M10: 24; M11: 16; M12: 9 | 90 | 1
Gangs Available.
Staff Available.
3 | Stringing | As per L2 | 136.581 | M9: 4; M10: 10; M11: 10; M12: 10 |  | 10 | 10 | 11 | 11 | 11 | 11 | 10 | 10 | 8 |  |  |  | 16 | 126 | 136.581 | Stringable Stretch will be ready on availablity of shotages of angle tower.
|  | Plan | [16 empty] | 14 | 21 | 21 | 21 | 21 | 20 | 19 | [5 empty] | 137
|  | TSE Required. | [16 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | Gangs Required. | [16 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | Staff Required. | [16 empty] | 10 | 15 | 15 | 15 | 15 | 15 | 5
Actual
TSE Available.
Gangs Available.
Staff Available.
4 | OPGW Stringing | Original Plan | 136.581 | [17 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 6 |  |  | 16 | 126 | 136.581
|  | Current Plan | [16 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 16 | [5 empty] | 136
|  | Actual |  | M9: 0; M10: 0; M11: 0; M12: 0 |  | 0
|  | No of Teams | [16 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Formulas:
M13 = [M12]+31

## Project Stringing Plan (hidden)
KEC INTERNATIONAL LIMITED
Project Stringing Plan (TA-505)
Section Length | Towers in Section | Section Length (in M) | Balance Foundation | Balance Tower Erection | Tower Required | Tower Supply Month Plan | TSE/Manual | Stringing Plan
101/0-102/0 | 10 | 3470 |  | 101/0-DC1+3 102/0- DC2+3 | 101/0-DC1+3- Shortages Reqd. |  | TSE-1 | 2025-11-01
108/0-109/0 | 6 | 1668 |  | 109/0-DC1+0 | Shortages Reqd. |  | TSE-1 | 2025-11-01
109/0-110/0 | 6 | 1949 |  | 109/0-DC1+0 | Shortages Reqd. |  | TSE-1
110/0-DC2+3
110/0-110A/0 | 10 | 3514 |  | 110/0-DC2+3 |  |  | TSE-1 | 2025-11-01
110A/0-111/0 | 4 | 1230 |  |  |  |  | TSE-1 | 2025-11-01
111/0-112/0 | 6 | 1954 |  |  |  |  | TSE-1
113/0-114/0 | 8 | 2564 | 113/0-RC | 113/0-DD60+9 |  |  | TSE-1 | 2025-12-01
114/0-DC2+0
114/0-115/0 | 12 | 4304 |  | 114/0-DC2+0 |  |  | TSE-1 | 2025-12-01
114/4-DA+3
114/8-DA+6
116/0-117/0 | 4 | 1147 | 117/0-DD45+6 | 117/0-DD45+6 |  |  | TSE-1 | 2025-12-01
120/0-121/0 | 5 | 1593 |  | 121/0-DB1+6 |  |  | TSE-1 | 2025-12-01
126/0-127/0 | 6 | 1957 |  | 126/1- DA+9 126/3- DA+3 |  |  | TSE-1 | 2025-12-01
127/0-128/0 | 5 | 1441 |  |  |  |  | TSE-1 | 2025-12-01
26791
Sr. No. | Section | Section Length (Mtr) | Tower Required | TSE/Manual
1 | 108/0-109/0 | 1668 |  | TSE
2 | 109/0-110/0 | 1949 |  | TSE
3 | 110/0-110A/0 | 3514 |  | TSE
4 | 110A/0-111/0 | 1230 |  | TSE
5 | 111/0-112/0 | 1954 |  | TSE
6 | 113/0-114/0 | 2564 |  | TSE
7 | 114/0-115/0 | 4304 |  | TSE
8 | 116/0-117/0 | 1147 |  | TSE
9 | 120/0-121/0 | 1593 |  | TSE
10 | 101/0-102/0 | 3470 |  | TSE
11 | 126/0-127/0 | 1957 |  | TSE
12 | 127/0-128/0 | 1441 |  | TSE
| Total (in KM) | 26.791

## Priority Stringing Stretches
KEC INTERNATIONAL LIMITED
Project Stringing Plan (TA-505)
Section Length | Towers in Section | Section Length (in M) | Balance Foundation | Balance Tower Erection | Remarks | Tower Supply Month Plan | TSE/Manual | Stringing Plan
101/0-102/0 | 10 | 3470 |  |  |  |  | TSE | 2025-11-01
102/0-103/0 | 2 | 461 |  |  |  |  | Manual
103/5A-103/6A | 3 | 563 |  |  |  |  | TSE
104/0-105/0 | 4 | 967 |  |  |  |  | TSE
105/0-106/0 | 3 | 754 |  |  |  |  | TSE
106/0-108/0 | 2 | 212 |  |  |  |  | Manual
108/0-109/0 | 6 | 1668 |  | 109/0-DC1+0 | Shortages Reqd. |  | TSE | 2025-12-01
109/0-110/0 | 6 | 1949 |  | 109/0-DC1+0 | Shortages Reqd. |  | TSE
|  |  |  | 110/0-DC2+3 | Water Logged |  | TSE
110/0-110A/0 | 10 | 3514 |  | 110/0-DC2+3 | Water Logged |  | TSE
110A/0-111/0 | 4 | 1230 |  |  |  |  | TSE
111/0-112/0 | 6 | 1954 |  |  |  |  | TSE
113/0-114/0 | 8 | 2564 | 113/0-RC | 113/0-DD60+9 | BOM approval awaited. |  | TSE
|  |  |  | 114/0-DC2+0 | WIP |  | TSE
114/0-115/0 | 12 | 4304 |  | 114/0-DC2+0 | WIP |  | TSE
|  |  |  | 114/4-DA+3 |  |  | TSE
116/0-117/0 | 4 | 1147 | 117/0-DD45+6 | 117/0-DD45+6 | Severe RoW-PP reqd. |  | TSE
TSE
120/0-121/0 | 5 | 1593 |  |  |  |  | TSE
126/0-127/0 | 6 | 1957 |  | 126/1- DA+9 |  |  | TSE
|  |  |  | 126/3- DA+3 |  |  | TSE
127/0-128/0 | 5 | 1441 |  |  |  |  | TSE
130/0-131/0 | 4 | 1136 |  | 130/2-DA-1.5 |  |  | TSE | 2025-01-01
131/0-132/0 | 2 | 484 |  | 132/0-DD60+6 | Tower Reqd. |  | Manual
147/0-147A/0 | 3 | 836 |  | 147/0-DB2+6 |  |  | TSE
147A/0-148/0 | 7 | 2306 |  | 148/0-DD60+6 | Tower Reqd. |  | TSE
150/0-151/0 | 7 | 2398 |  | 151/0-DD45+3 |  |  | TSE
159/0-160/0 | 5 | 1507 |  | 159/0-DB2+0 159/3-DA+0 |  |  | TSE
160/0-161/0 | 7 | 2062 |  | 161/0-DB2+3 |  |  | TSE
167/0-168/0 | 7 | 2087 |  | 167/1-DA+0 168/0-DC2+0 |  |  | TSE
Total |  | 42564 | 2 | 18
[5 empty] | TSE/Manual |  | Sections | Length (In KM)
[5 empty] | TSE |  | 27 | 41407
[5 empty] | Manual |  | 3 | 1157
[5 empty] | Total |  | 30 | 42564

## Drgs required
765 KV BEAWAR MANDSAUR TRANSMISSION LINE
Sr. No. | Loc No. | TOT | Description | Proposed Drawing | [8 empty] | FOREST,NON-FOREST | REMARKS
|  |  |  | Raised Chimeny Details (M) |  |  |  | ULE Details (M) |  |  |  | Benching Qty in Cu.M
|  |  |  | A | B | C | D | A | B | C | D
1 | 103/5 | DA+3 | Un-equal RC & Benching | [8 empty] | 28.315 | NON-FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
2 | 103/6A | DD45+0 | Benching | [8 empty] | 57.537 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
3 | 110A/2 | DA-1.5 | Benching | [8 empty] | 67.993 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
4 | 113/0 | DD60+9 | Equal - RC | 3 | 3 | 3 | 3 | - | - | - | - |  | NON-FOREST | Approved by PGCIL except the Benching Qty.
5 | 114/5 | DA+6 | Benching | [8 empty] | 21.816 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
6 | 126/1 | DA+9 | Un-equal RC & Benching | [8 empty] | 6.749 | NON-FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
7 | 127/1 | DA+0 | Benching | [8 empty] | 24.496 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
8 | 129/0 | DB1+3 | Un-equal RC, Benching & X-Arm Strengthening. | [8 empty] | 29.094 | FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
9 | 129/1 | DB1+9 | Un-equal RC,ULE & Benching | 0 | 0 | 3 | 0 | 6 | 9 | 9 | 9 | 29.029 | FOREST | Approved by PGCIL except the benching Qty. ULE used with+6 Body extn at A LEG
10 | 133/0 | DB2+3 | Un-equal RC,ULE & Benching | - | - | 1.5 |  | 1.5 | 3 | 3 | 3 | 13.174 | FOREST | Approved by PGCIL except the Benching Qty.
11 | 134/0 | DC1+0 | Un-equal RC, Benching & X-Arm Strengthening. | [8 empty] | 14.43 | FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released | bar: Raised Chimeny Details (M) A to ULE Details (M) D
12 | 135/3 | DA+9 | Benching | [8 empty] | 28.233 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
13 | 137/0 | DD60+9 | Equal - RC | 4 | 4 | 4 | 4 | - | - | - | - |  | NON-FOREST | Approved by PGCIL except the Benching Qty.
14 | 137A/0 | DC2+25 | Un-equal RC & Benching | 1.5 | - | - | 1.5 | - | - | - | - | 50.169 | NON-FOREST | Cross arm strengthening not required. Approved by PGCIL except the benching Qty.
15 | 138/0 | DB1+3 | Un-equal RC,ULE & Benching | 2 | - | - | - | 3 | 3 | 1.5 | 3 | 19.466 | NON-FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released
16 | 138/2 | DB1+9 | Equal - RC | 2 | 2 | 2 | 2 | - | - | - | - |  | FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released
17 | 138/3 | DA+3 | Un-equal RC & Benching | 2 | 1 | - | - | - | - | - | - | 18.894 | FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released
18 | 142/1 | DA-3 | Un-equal RC & Benching | [8 empty] | 36.184 | FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released | bar: Raised Chimeny Details (M) A to ULE Details (M) D
19 | 143/0 | DD45+0 | Un-equal RC,ULE & Benching | - | - | 2 | 1 | -1.5 | 0 | 0 | 0 | 11.931 | FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released
20 | 144/0 | DC1+0 | ULE & Benching | - | - | - | - | - | - | 3 | 1.5 | 5.491 | FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released
21 | 146/0 | DD60+18 | Un-equal RC & Benching | 3 | - | 3 | 3 | - | - | - | - | 95.665 | FOREST | Approved by PGCIL except the Benching Qty.
22 | 148B/0 | DB1+0 | Un-equal RC,ULE & Benching | 1 | - | - | - | 1.5 | - | - | 1.5 | 16.606 | NON-FOREST | Approved by PGCIL except the Benching Qty.
23 | 148B/1 | DA+0 | Un-equal RC & Benching | [8 empty] | 28.18 | FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
24 | 148C/0 | DB1+9 | Un-equal RC, ULE & Benching | - | - | 2 | - | 7.5 | 9 | 9 | 9 | 4.629 | FOREST | Approved by PGCIL except the Benching Qty.
25 | 149B/2 | DA+6 | Un-equal RC & Benching | - | - | - | 1.5 | - | - | - | - | 20.512 | NON-FOREST | Approved by PGCIL except the Benching Qty.
26 | 149B/3 | DA+3 | Un-equal RC & Benching | - | - | 1 | 1.5 | - | - | - | - | 20.961 | NON-FOREST | Approved by PGCIL except the Benching Qty.
27 | 149B/4 | DA+0 | Un-equal RC & Benching | - | - | 2 | 2.5 | - | - | - | - | 7.259 | NON-FOREST | Approved by PGCIL except the Benching Qty.
28 | 157/0 | DB2+9 | Equal - RC & X- Arm Strengthening. | 3 | 3 | 3 | 3 | - | - | - | - | - | FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released
29 | 165/0 | DB1+6 | Un-equal RC & Benching | [8 empty] | 6.199 | NON-FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released | bar: Raised Chimeny Details (M) A to ULE Details (M) D
30 | 178/2 | DA+6 | Un-equal RC & Benching | 1 | 1.5 | - | - | - | - | - | - | 4.779 | NON-FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released
31 | 182/0 | DD60+6 | Un-equal RC & Benching | [8 empty] | 19.489 | NON-FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released | bar: Raised Chimeny Details (M) A to ULE Details (M) D
32 | 165/2 | DA+0 | Un-equal RC & Benching | [8 empty] | 6.408 | NON-FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released | bar: Raised Chimeny Details (M) A to ULE Details (M) D
| 158/0 | DC2+18 | X-Arm Strengthening. | [10 empty] | Approved by PGCIL. | PRS to be released
| 136/4 | DC2+0 | Transposition Tower | [10 empty] | Approved by PGCIL. | PRS to be released
| 163/0 | DB1+18 | Angle Tower | [10 empty] | Mapping Reqd. | PRS to be released
| 149B/0 | DB1+25 | Angle Tower | [10 empty] | Mapping Reqd. | PRS to be released
| 182B/0 | DD60+0 | Auxiliary X-arm | [10 empty] | Approval pending from PGCIL. | PRS to be released
| 182B/0 | DD60+0 | Auxiliary X-arm | [10 empty] | Approved by PGCIL. | PRS to be released

## ERC_Plan (hidden)
Erection Approachable Locations
SL | Location No | TOT | Remarks
1 | 106/0 | DD60+0
2 | 108/0 | DD45+0
3 | 109/0 | DC1+0
4 | 110/0 | DC2+3
5 | 103/7 | DA+6 | WIP
6 | 103/8 | DA+3
7 | 103/5A1 | DA-3
8 | 110/4 | DA+3
9 | 150/1 | DA+6 | WIP
10 | 160/3 | DA+0 | WIP

## Gang deployment Plan (hidden)
Project | Activity | Current gangs | Aug'25 |  | August'25 | [9 empty] | September'25
|  |  | Target | Gang Plan | Target | Gang Plan | wk-01 (4 aug - 10 aug) |  | wk-02 (11 aug - 17 aug) |  | wk-03 (18 aug - 24 aug) |  | wk-04 (25 aug - 31 aug) |  | Target | Gang Plan | wk-01 (1 sep - 7 sep) |  | wk-02 (8 sep - 14 sep) |  | wk-03 (15 sep - 21 sep) |  | wk-04 (22sep - 28 sep)
[7 empty] | No of gangs | Gang Source | No of gangs | Gang Source | No of gangs | Gang Source | No of gangs | Gang Source |  |  | No of gangs | Gang Source | No of gangs | Gang Source | No of gangs | Gang Source | No of gangs | Gang Source
TB501 | Fdn | 4 | 15 |  | 19 | [9 empty] | 2
| Ern | 2 | 20 |  | 22 | [9 empty] | 9
| Str | 1 | 23 |  | 25 | [9 empty] | 13
TA505 | Fdn | 6 | 15 | 6 | 15 | 6 | 6 | 1. RST Const 2. Neelkamal 3. Garg Const 4. Ram Singh 5. Shaktawat 6.Reshmi Devi | 6 | 1. RST Const 2. Neelkamal 3. Garg Const 4. Ram Singh 5. Shaktawat 6.Reshmi Devi | 6 | 1. RST Const 2. Neelkamal 3. Garg Const 4. Ram Singh 5. Shaktawat 6.Reshmi Devi | 6 | 1. RST Const 2. Neelkamal 3. Garg Const 4. Ram Singh 5. Shaktawat 6.Reshmi Devi | 27 | 8 | 8 | 1. RST Const 2. Neelkamal 3. Garg Const 4. Ram Singh 5. Shaktawat 6.Reshmi Devi 7. Sumit Const 8. Shree Balaji | 8 | 1. RST Const 2. Neelkamal 3. Garg Const 4. Ram Singh 5. Shaktawat 6.Reshmi Devi 7. Sumit Const 8. Shree Balaji | 8 | 1. RST Const 2. Neelkamal 3. Garg Const 4. Ram Singh 5. Shaktawat 6.Reshmi Devi 7. Sumit Const 8. Shree Balaji | 8 | 1. RST Const 2. Neelkamal 3. Garg Const 4. Ram Singh 5. Shaktawat 6.Reshmi Devi 7. Sumit Const 8. Shree Balaji
| Ern | 4 | 15 | 6 | 15 | 6 | 6 | 1. Jwala Singh 2. Parmanand 3. Shila Devi/Ramesh Mandal 4. Gokul Sarkar 5. Anil Kumar 6. Jyoti Enterprises | 8 | 1. Jwala Singh 2. Parmanand 3. Shila Devi/Ramesh Mandal 4. Gokul Sarkar 5. Anil Kumar 6. Jyoti Enterprises 7. Jhemon Mahto 8. Deglal Mahto | 10 | 1. Jwala Singh 2. Parmanand 3. Shila Devi/Ramesh Mandal 4. Gokul Sarkar 5. Anil Kumar 6. Jyoti Enterprises 7. Jhemon Mahto 8. Deglal Mahto 9. Brijesh Mahto 10. Tarakeswar Mahto | 10 | 1. Jwala Singh 2. Parmanand 3. Shila Devi/Ramesh Mandal 4. Gokul Sarkar 5. Anil Kumar 6. Jyoti Enterprises 7. Jhemon Mahto 8. Deglal Mahto 9. Brijesh Mahto 10. Tarakeswar Mahto | 40 | 10 | 10 | 1. Jwala Singh 2. Parmanand 3. Shila Devi/Ramesh Mandal 4. Gokul Sarkar 5. Anil Kumar 6. Jyoti Enterprises 7. Jhemon Mahto 8. Deglal Mahto 9. Brijesh Mahto 10. Tarakeswar Mahto | 10 | 1. Jwala Singh 2. Parmanand 3. Shila Devi/Ramesh Mandal 4. Gokul Sarkar 5. Anil Kumar 6. Jyoti Enterprises 7. Jhemon Mahto 8. Deglal Mahto 9. Brijesh Mahto 10. Tarakeswar Mahto | 10 | 1. Jwala Singh 2. Parmanand 3. Shila Devi/Ramesh Mandal 4. Gokul Sarkar 5. Anil Kumar 6. Jyoti Enterprises 7. Jhemon Mahto 8. Deglal Mahto 9. Brijesh Mahto 10. Tarakeswar Mahto | 10 | 1. Jwala Singh 2. Parmanand 3. Shila Devi/Ramesh Mandal 4. Gokul Sarkar 5. Anil Kumar 6. Jyoti Enterprises 7. Jhemon Mahto 8. Deglal Mahto 9. Brijesh Mahto 10. Tarakeswar Mahto
| Str |  | - |  | 10 | 1 |  |  |  |  | 1 | 1. Alimuddin Khan | 1 | 1. Alimuddin Khan | 14 | 2 | 1 | 1. Alimuddin Khan | 1 | 1. Alimuddin Khan | 2 | 1. Alimuddin Khan 2. Muslimuddin Khan | 2 | 1. Alimuddin Khan 2. Muslimuddin Khan
TA509 | Fdn | 2 | 12 | 3 | 11 | 3 | [8 empty] | 18 | 4
| Ern | 0 | 5 | 1 | 5 | 1 | [8 empty] | 8 | 2
| Str |  | - |  | - | [9 empty] | -

## Gang List (hidden)
Erection Gangs
SL | Sub-Contractor Name | Contact No
1 | Jhemon Mahato | 7903986246
2 | Sintu | 6267625341
3 | Jay Kishor Chaurasia | 8809719623
4 | Subham Yadav | 7909016958
5 | Baidyanath Mahato | 8340522804
6 | Nityanand | 7742446771
7 | Rampukar | 9631668094
8 | Jyoti Construction | 8329882493
9 | Heeralal Mahto | 8340522804
10 | Mohan Saw | 7979965855
11 | Ruplal Sahu | 9162449115
12 | Sheela Devi | 6268829066
13 | Jwala Singh | 6202461569
14 | Parmanand | 9973422181
15 | Gokul Sarkar | 7001950006
16 | Jugal Mahato | 7979869316
17 | Karam Mahato | 9801263101
18 | Pankaj Kumar | 6203097861
19 | Birendra Saw | 7484927816
20 | Balbanda Singh | 7678524046
21 | Shiv Shakti Enterprises | 9827729090
22 | Karni Construction | 9636170005
23 | Shabnam Pravin | 8969543979
24 | Poonam Kumari | 9893941515
25 | Mohan Mahato | 9113752993
26 | Mukkhilal Singh | 7763816767
27 | Daulat Mahato

## Tower Availability at Store
SATKHANDA STORE
Tower Type | BB | -3 | -1.5 | 0 | 3 | 6 | 9 | 18 | Remarks
DA | 30 | 4 | 2 | 14 | 5 | 4 | 3 |  | DA BB-5, -3-1 set, +0-4 set,-1.5-1 set,+3-3 set,+6-1 set at TA-504. +3-2 set at Manasa.
DB1 | 7 |  |  | 5 | 2 | 0 | 3
DB2 | 6 |  |  | 6 | 1 | 2 | 1
DC1 | 2 |  |  | 2 |  |  | 1
DC2 | 3 |  |  | 2 | 1
DD1 | 4 |  |  | 2 | 2 | 2
DD2 | 6 |  |  | 6 |  | 1 | 2 | 2
MANASA STORE
Tower Type | BB | -3 | -1.5 | 0 | 3 | 6 | 9 | 18 | Remarks
DA | 101 | 23 | 1 | 60 | 19 | 6 | 2 |  | 1 BB at Raj Section.
DB1 | 3 |  |  | 4 |  | 1
DB2 | 1 | [7 empty] | 3 sets-110A/0130/0 & 126/0 at Raj Section.
DC1 | 2 |  |  |  | 2
DC2 | 1 |  |  | 1
DD1 | 1 |  |  | 1
DD2 | 3 |  |  | 2 | 1

## Issues & Support reqn
Issues & Support Required for PGCIL
1 | 22 Nos of Location are on hold due to severe ROW.
2 | 30 Nos of location are on hold due to forest (Rajasthan- 7.272 Km, 19 Locations, MP-2.102 Km, 6 Locations) = 9.374 Kms
3 | 06 Nos Locations are on hold due to NH Xing.

## Sheet1 (hidden)
765 KV BEAWAR MANDSAUR TRANSMISSION LINE
Sr. No. | Loc No. | TOT | Description | Proposed Drawing | [8 empty] | FOREST,NON-FOREST | REMARKS
|  |  |  | Raised Chimeny Details (M) |  |  |  | ULE Details (M) |  |  |  | Benching Qty in Cu.M
|  |  |  | A | B | C | D | A | B | C | D
1 | 103/5 | DA+3 | Un-equal RC & Benching | [8 empty] | 28.315 | NON-FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
2 | 103/6A | DD45+0 | Benching | [8 empty] | 57.537 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
3 | 110A/2 | DA-1.5 | Benching | [8 empty] | 67.993 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
4 | 113/0 | DD60+9 | Equal - RC | 3 | 3 | 3 | 3 | - | - | - | - |  | NON-FOREST | Approved by PGCIL except the Benching Qty.
5 | 114/5 | DA+6 | Benching | [8 empty] | 21.816 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
6 | 126/1 | DA+9 | Un-equal RC & Benching | [8 empty] | 6.749 | NON-FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
7 | 127/1 | DA+0 | Benching | [8 empty] | 24.496 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
8 | 129/0 | DB1+3 | Un-equal RC, Benching & X-Arm Strengthening. | [8 empty] | 29.094 | FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) D to ULE Details (M) D
9 | 129/1 | DB1+9 | Un-equal RC,ULE & Benching | 0 | 0 | 3 | 0 | 6 | 9 | 9 | 9 | 29.029 | FOREST | Approved by PGCIL except the benching Qty. ULE used with+6 Body extn at A LEG
10 | 133/0 | DB2+3 | Un-equal RC,ULE & Benching | - | - | 1.5 |  | 1.5 | 3 | 3 | 3 | 13.174 | FOREST | Approved by PGCIL except the Benching Qty.
11 | 134/0 | DC1+0 | Un-equal RC, Benching & X-Arm Strengthening. | [8 empty] | 14.43 | FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released | bar: Raised Chimeny Details (M) A to ULE Details (M) D
12 | 135/3 | DA+9 | Benching | [8 empty] | 28.233 | NON-FOREST | bar: Raised Chimeny Details (M) A to ULE Details (M) D
13 | 137/0 | DD60+9 | Equal - RC | 4 | 4 | 4 | 4 | - | - | - | - |  | NON-FOREST | Approved by PGCIL except the Benching Qty.
14 | 137A/0 | DC2+25 | Un-equal RC & Benching | 1.5 | - | - | 1.5 | - | - | - | - | 50.169 | NON-FOREST | Cross arm strengthening not required. Approved by PGCIL except the benching Qty.
15 | 138/0 | DB1+3 | Un-equal RC,ULE & Benching | 2 | - | - | - | 3 | 3 | 1.5 | 3 | 19.466 | NON-FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released
16 | 138/2 | DB1+9 | Equal - RC | 2 | 2 | 2 | 2 | - | - | - | - |  | FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released
17 | 138/3 | DA+3 | Un-equal RC & Benching | 2 | 1 | - | - | - | - | - | - | 18.894 | FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released
18 | 142/1 | DA-3 | Un-equal RC & Benching | [8 empty] | 36.184 | FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released | bar: Raised Chimeny Details (M) A to ULE Details (M) D
19 | 143/0 | DD45+0 | Un-equal RC,ULE & Benching | - | - | 2 | 1 | -1.5 | 0 | 0 | 0 | 11.931 | FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released
20 | 144/0 | DC1+0 | ULE & Benching | - | - | - | - | - | - | 3 | 1.5 | 5.491 | FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released
21 | 146/0 | DD60+18 | Un-equal RC & Benching | 3 | - | 3 | 3 | - | - | - | - | 95.665 | FOREST | Approved by PGCIL except the Benching Qty.
22 | 148B/0 | DB1+0 | Un-equal RC,ULE & Benching | 1 | - | - | - | 1.5 | - | - | 1.5 | 16.606 | NON-FOREST | Approved by PGCIL except the Benching Qty.
23 | 148B/1 | DA+0 | Un-equal RC & Benching | [8 empty] | 28.18 | FOREST | Approved by PGCIL except the Benching Qty. | bar: Raised Chimeny Details (M) A to ULE Details (M) D
24 | 148C/0 | DB1+9 | Un-equal RC, ULE & Benching | - | - | 2 | - | 7.5 | 9 | 9 | 9 | 4.629 | FOREST | Approved by PGCIL except the Benching Qty.
25 | 149B/2 | DA+6 | Un-equal RC & Benching | - | - | - | 1.5 | - | - | - | - | 20.512 | NON-FOREST | Approved by PGCIL except the Benching Qty.
26 | 149B/3 | DA+3 | Un-equal RC & Benching | - | - | 1 | 1.5 | - | - | - | - | 20.961 | NON-FOREST | Approved by PGCIL except the Benching Qty.
27 | 149B/4 | DA+0 | Un-equal RC & Benching | - | - | 2 | 2.5 | - | - | - | - | 7.259 | NON-FOREST | Approved by PGCIL except the Benching Qty.
28 | 157/0 | DB2+9 | Equal - RC & X- Arm Strengthening. | 3 | 3 | 3 | 3 | - | - | - | - | - | FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released
29 | 165/0 | DB1+6 | Un-equal RC & Benching | [8 empty] | 6.199 | NON-FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released | bar: Raised Chimeny Details (M) A to ULE Details (M) D
30 | 178/2 | DA+6 | Un-equal RC & Benching | 1 | 1.5 | - | - | - | - | - | - | 4.779 | NON-FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released
31 | 182/0 | DD60+6 | Un-equal RC & Benching | [8 empty] | 19.489 | NON-FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released | bar: Raised Chimeny Details (M) A to ULE Details (M) D
32 | 165/2 | DA+0 | Un-equal RC & Benching | [8 empty] | 6.408 | NON-FOREST | Approved by PGCIL except the Benching Qty. | PRS to be released | bar: Raised Chimeny Details (M) A to ULE Details (M) D
| 158/0 | DC2+18 | X-Arm Strengthening. | [10 empty] | Approved by PGCIL. | PRS to be released
| 136/4 | DC2+0 | Transposition Tower | [10 empty] | Approved by PGCIL. | PRS to be released
| 163/0 | DB1+18 | Angle Tower | [10 empty] | Mapping Reqd. | PRS to be released
| 149B/0 | DB1+25 | Angle Tower | [10 empty] | Mapping Reqd. | PRS to be released
| 182B/0 | DD60+0 | Auxiliary X-arm | [10 empty] | Approval pending from PGCIL. | PRS to be released
| 182B/0 | DD60+0 | Auxiliary X-arm | [10 empty] | Approved by PGCIL. | PRS to be released