## Erection Summary
Scope: 2025-04-01 to 2026-02-28 ¦ Projects: 17 ¦ Erections: 2584 ¦ Gangs: 429
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | Avg Tower Weight Overall
3.84 | 4.24 | 4.59 | 4.75 | 4.61 | 3.82 | 3.7 | 3.47 | 3.46 | 3.68 | 3.59 | 3.51 | 3.54 | 3.42 | 3.35 | 3.47 | 3.87 | 3.61 | 3.67 | 3.35 | 3.47 | 3.28 | 3.73 | 3.57 | 3.49 | 3.68 | 3.57 | 3.82 | 3.68 | 3.56 | 3.5 | 3.84 | 3.79 | 3.81 | 3.97 | 3.97 | 4 | 4.15 | 4.37 | 3.82 | 3.81 | 4.1 | 4.45 | 4.77 | 5.34 | 0 | 0 | 0 | 4 | 112898.13 | 2584 | 43.69
Scope: 2025-04-01 to 2026-02-28 ¦ Projects: 17 ¦ Erections: 2584 ¦ Gangs: 429
PCH | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | 3.26 | 3.46 | 3.67 | 3.95 | 4.21 | 2.7 | 2.89 | 2.74 | 2.48 | 2.21 | 2.32 | 2.97 | 3.78 | 3.74 | 3.78 | 3.96 | 4.14 | 3.79 | 3.61 | 3.77 | 4.05 | 3.82 | 3.77 | 3.74 | 3.89 | 4.05 | 3.96 | 3.99 | 3.84 | 3.77 | 3.93 | 4.03 | 4.07 | 4 | 3.92 | 3.78 | 3.77 | 3.65 | 3.89 | 3.41 | 3.3 | 3.75 | 4.77 | 5.12 | 5.18 | 0 | 0 | 0 | 3.99 | 48592.42 | 1141 | 42.59
Mr. Arun Felbin | 3.6 | 4.45 | 4.64 | 5.01 | 4.89 | 4.5 | 3.83 | 3.31 | 3.68 | 4.13 | 3.74 | 3.41 | 3.26 | 3.25 | 3.15 | 3.19 | 3.65 | 3.39 | 3.38 | 2.85 | 2.95 | 2.8 | 3.95 | 3.38 | 2.93 | 2.99 | 2.8 | 3.23 | 2.88 | 2.9 | 2.7 | 3.18 | 3.07 | 3.21 | 3.5 | 3.84 | 3.96 | 4.35 | 4.58 | 3.8 | 3.87 | 4.1 | 3.7 | 4.02 | 4.53 | 0 | 0 | 0 | 3.77 | 40982.95 | 819 | 50.04
Mr. Dheeraj Vashishth | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.83 | 2.65 | 3.27 | 4.39 | 4.86 | 3.79 | 3.94 | 4.24 | 3.93 | 3.71 | 4.28 | 3.47 | 3.91 | 4.12 | 4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.84 | 411.02 | 18 | 22.83
Mr. Nabajit Baruah | 6 | 5.64 | 6.74 | 6.08 | 4.93 | 4.4 | 5.01 | 5.31 | 4.77 | 5.26 | 5.66 | 4.89 | 4.26 | 3 | 2.75 | 2.94 | 3.69 | 3.72 | 4.75 | 3.6 | 3.3 | 3.15 | 3.27 | 3.53 | 3.83 | 4.45 | 4.19 | 4.25 | 4.55 | 4.36 | 4.09 | 4.62 | 4.63 | 4.66 | 4.9 | 4.79 | 4.56 | 4.54 | 4.77 | 4.56 | 4.51 | 4.7 | 4.66 | 4.94 | 6.05 | 0 | 0 | 0 | 4.49 | 22911.74 | 606 | 37.81
[49 empty] | Total | 112898.13 | 2584
Scope: 2025-04-01 to 2026-02-28 ¦ Projects: 17 ¦ Erections: 2584 ¦ Gangs: 429
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD) | Avg Tower Weight Overall
Mr. Sanjay Kumar Gupta | TA413 | 4.8 | 4.21 | 4.72 | 5.07 | 5.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.15 | 3.2 | 3.28 | 3.77 | 4.12 | 5.3 | 5.05 | 4.92 | 4.37 | 4.91 | 5.05 | 4.85 | 5.18 | 4.27 | 4.35 | 3.8 | 3.87 | 3.7 | 4.01 | 4.33 | 4.35 | 4.63 | 4.42 | 3.97 | 3.98 | 5.37 | 4.3 | 3.71 | 3.28 | 3.79 | 5.09 | 0 | 0 | 0 | 0 | 4.43 | 10113.08 | 207 | 48.86
Mr. Sanjay Kumar Gupta | TA419 | 3.1 | 3.76 | 4.33 | 5.37 | 5.93 | 6.03 | 6.28 | 4.58 | 4.58 | 4.82 | 4.31 | 4.79 | 5.79 | 5.25 | 5.63 | 5.87 | 5.96 | 3.3 | 2.94 | 3.22 | 3.28 | 3.13 | 3.08 | 2.87 | 3.97 | 4.24 | 4.5 | 4.77 | 4.09 | 3.54 | 3.6 | 4.05 | 3.6 | 3.15 | 3.44 | 3.69 | 3.65 | 3.65 | 3.32 | 3.03 | 3.43 | 3.42 | 3.56 | 3.52 | 0 | 0 | 0 | 0 | 3.71 | 6805.3 | 127 | 53.59
Mr. Sanjay Kumar Gupta | TA512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.58 | 2.58 | 2.73 | 4.16 | 4.73 | 4.42 | 4.47 | 5.45 | 5.43 | 5.44 | 5.1 | 4.98 | 4.71 | 5.49 | 4.78 | 4.85 | 5.25 | 5.43 | 4 | 4.03 | 3.84 | 3.78 | 3.83 | 3.26 | 3.13 | 3.68 | 4.21 | 5.42 | 6.38 | 0 | 0 | 0 | 4.31 | 5632.04 | 140 | 40.23
Mr. Sanjay Kumar Gupta | TB401 | 1.94 | 5.01 | 5.1 | 4.6 | 3.55 | 3.54 | 4.09 | 2.94 | 2.99 | 2.81 | 3.23 | 4.19 | 5.01 | 4.87 | 5.09 | 5.07 | 5.47 | 5.83 | 5.03 | 4.22 | 4.96 | 4.77 | 4.09 | 3.29 | 2.57 | 2.66 | 3.24 | 3.09 | 3.3 | 3 | 4.52 | 4.62 | 4.55 | 5.08 | 5.03 | 4.62 | 4.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.35 | 11489.47 | 242 | 47.48
Mr. Sanjay Kumar Gupta | TB408 | 6.42 | 4.32 | 4.16 | 4.67 | 6.47 | 1.18 | 1.15 | 3.42 | 2.31 | 1.18 | 1.71 | 2.63 | 3.12 | 3.81 | 3.56 | 4.15 | 5.51 | 5.25 | 4.06 | 4.47 | 4.88 | 4.83 | 4.94 | 4.32 | 4.67 | 4.65 | 4.47 | 4.2 | 4.94 | 4.43 | 4.48 | 4.19 | 4.45 | 4.13 | 4.26 | 3.98 | 4.27 | 4.96 | 4.67 | 4.08 | 4.09 | 6.22 | 8.68 | 7.18 | 5.68 | 0 | 0 | 0 | 4.43 | 11854.96 | 247 | 48
Mr. Sanjay Kumar Gupta | TB507 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.28 | 1.21 | 1.64 | 1.41 | 1.41 | 1.58 | 1.69 | 1.59 | 1.48 | 1.56 | 1.38 | 1.12 | 1.44 | 1.84 | 2.11 | 2.21 | 2.56 | 2.2 | 2.29 | 2.49 | 2.49 | 2.23 | 1.87 | 2.14 | 1.92 | 1.92 | 1.87 | 2.28 | 2.38 | 2.11 | 2.17 | 3.59 | 4.39 | 3.48 | 0 | 0 | 0 | 1.88 | 2697.56 | 178 | 15.15
Mr. Arun Felbin | TA325 | 4.24 | 4.55 | 4.48 | 4.11 | 4.06 | 3.79 | 3.45 | 2.58 | 2.88 | 2.4 | 1.58 | 1.41 | 1.41 | 1.33 | 1.21 | 1.22 | 1.18 | 1.17 | 1.16 | 0.99 | 0.95 | 1.02 | 1.01 | 1.07 | 1.42 | 2.04 | 2.68 | 4.01 | 4.2 | 3.82 | 3.53 | 3.59 | 3.92 | 4.3 | 4.6 | 4.3 | 3.63 | 3.3 | 3.47 | 3.75 | 3.68 | 3.64 | 0 | 0 | 0 | 0 | 0 | 0 | 3.16 | 13361.73 | 190 | 70.32
Mr. Arun Felbin | TA414 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.12 | 4.82 | 5.03 | 2.69 | 2.69 | 0 | 0 | 0 | 4.24 | 4.24 | 4.3 | 4.03 | 4.15 | 4.07 | 5.44 | 3.45 | 2.07 | 1.77 | 0.96 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.96 | 2.65 | 3.52 | 3.32 | 3.63 | 3.3 | 3.48 | 3.79 | 4.46 | 4.24 | 0 | 0 | 0 | 0 | 3.49 | 3869.12 | 77 | 50.25
Mr. Arun Felbin | TA416 | 4.96 | 5.55 | 5.69 | 6.74 | 6.36 | 6.04 | 5.48 | 5.65 | 5.8 | 5.77 | 5.46 | 5.73 | 5.75 | 4.95 | 4.99 | 4.99 | 5.17 | 4.65 | 3.98 | 3.57 | 3.48 | 3.55 | 3.77 | 4.02 | 4.18 | 4.27 | 4.36 | 4.29 | 3.72 | 3.68 | 3.57 | 3.57 | 4.01 | 4.42 | 4.32 | 4.01 | 3.44 | 3.22 | 3.02 | 3.03 | 3.18 | 3.14 | 4.14 | 3.95 | 3.67 | 0 | 0 | 0 | 4.59 | 11398.61 | 168 | 67.85
Mr. Arun Felbin | TA418 | 3.95 | 3.33 | 3.27 | 3.59 | 2.79 | 2.79 | 2.35 | 1.77 | 3.02 | 2.74 | 3.28 | 2.97 | 1.94 | 1.92 | 2.1 | 2.27 | 1.89 | 1.44 | 2.44 | 2.66 | 3.13 | 1.67 | 2.65 | 2.3 | 2.66 | 2.41 | 2.24 | 2.03 | 2.21 | 2.2 | 2.25 | 2.4 | 2.76 | 2.17 | 2.45 | 3.57 | 2.98 | 3.51 | 3.45 | 2.85 | 3.28 | 3.52 | 2.49 | 3.88 | 5.39 | 0 | 0 | 0 | 2.62 | 3287.86 | 86 | 38.23
Mr. Arun Felbin | TA421 | 6.38 | 5.92 | 6.96 | 7.97 | 8.22 | 6.84 | 5.36 | 3.77 | 3.97 | 4.82 | 3.81 | 5.41 | 5.24 | 5.65 | 5.19 | 4.94 | 3.98 | 6.1 | 5.95 | 3.81 | 3.69 | 4.37 | 6.89 | 6.07 | 4.3 | 4.45 | 3.77 | 5.5 | 5.64 | 4.81 | 4.56 | 7.05 | 6.18 | 6.49 | 7.46 | 6.99 | 7.21 | 8.45 | 11.26 | 8.17 | 6.85 | 6.41 | 0 | 0 | 0 | 0 | 0 | 0 | 5.7 | 8109.77 | 187 | 43.37
Mr. Arun Felbin | TA601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1 | 5.75 | 4.03 | 3.13 | 2.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.98 | 182.87 | 5 | 36.57
Mr. Arun Felbin | TB501 | 1.98 | 2.89 | 2.81 | 2.63 | 3.02 | 3.04 | 2.52 | 2.78 | 2.29 | 4.2 | 3.27 | 2.28 | 2.52 | 2.43 | 2.26 | 2.51 | 5.46 | 2.71 | 2.46 | 2.02 | 2.3 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 2.58 | 1.99 | 2.14 | 1.23 | 1.58 | 1.2 | 1.53 | 0.86 | 2.93 | 3.21 | 2.38 | 4.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.38 | 772.99 | 106 | 7.29
Mr. Dheeraj Vashishth | TA513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.83 | 2.65 | 3.27 | 4.39 | 4.86 | 3.79 | 3.94 | 4.24 | 3.93 | 3.71 | 4.28 | 3.47 | 3.91 | 4.12 | 4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.84 | 411.02 | 18 | 22.83
Mr. Nabajit Baruah | TA504 | 7.33 | 5.88 | 7.17 | 6.58 | 4.56 | 4.26 | 4.98 | 6 | 4.5 | 6.03 | 7.04 | 7 | 0 | 2.4 | 2.4 | 2.55 | 3.6 | 3.05 | 2.77 | 2.3 | 2.35 | 2.39 | 2.44 | 2.96 | 3.51 | 4.08 | 4.04 | 4.11 | 4.13 | 3.94 | 3.9 | 4.46 | 4.21 | 4.61 | 4.99 | 5.22 | 5.04 | 5.26 | 5.4 | 4.94 | 4.79 | 4.9 | 4.62 | 5.22 | 8.8 | 0 | 0 | 0 | 4.49 | 3704 | 77 | 48.1
Mr. Nabajit Baruah | TA505 | 4.67 | 5.4 | 6.31 | 5.59 | 5.29 | 4.53 | 5.03 | 4.62 | 5.04 | 4.49 | 4.28 | 2.77 | 4.26 | 3.61 | 3.11 | 3.33 | 3.77 | 4.4 | 6.74 | 4.9 | 4.26 | 3.7 | 3.61 | 3.93 | 4.17 | 4.9 | 4.59 | 4.77 | 4.95 | 4.39 | 3.48 | 3.81 | 3.95 | 4.26 | 4.89 | 4.74 | 4.93 | 5.15 | 5.5 | 5.62 | 5 | 4.58 | 4.73 | 5.26 | 4.89 | 0 | 0 | 0 | 4.61 | 12278.74 | 261 | 47.04
Mr. Nabajit Baruah | TA506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.37 | 3.76 | 3.7 | 3.82 | 4.36 | 3.93 | 3.87 | 4.58 | 4.76 | 4.88 | 5.59 | 5.74 | 5.12 | 4.83 | 4.39 | 3.72 | 3.2 | 3.42 | 3.13 | 3.73 | 4.6 | 4.63 | 4.35 | 4.45 | 0 | 0 | 0 | 4.29 | 6929 | 268 | 25.85
[50 empty] | Total | 112898.12 | 2584

## Review_Format
Scope: 2025-04-01 to 2026-02-28 ¦ Projects: 17 ¦ Erections: 2584 ¦ Gangs: 429
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
PCH: Mr. Sanjay Kumar Gupta
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
Mr. Sanjay Kumar Gupta | TA413 | 4.8 | 4.21 | 4.72 | 5.07 | 5.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.15 | 3.2 | 3.28 | 3.77 | 4.12 | 5.3 | 5.05 | 4.92 | 4.37 | 4.91 | 5.05 | 4.85 | 5.18 | 4.27 | 4.35 | 3.8 | 3.87 | 3.7 | 4.01 | 4.33 | 4.35 | 4.63 | 4.42 | 3.97 | 3.98 | 5.37 | 4.3 | 3.71 | 3.28 | 3.79 | 5.09 | 0 | 0 | 0 | 0 | 4.43 | 10113.08 | 207
Mr. Sanjay Kumar Gupta | TA419 | 3.1 | 3.76 | 4.33 | 5.37 | 5.93 | 6.03 | 6.28 | 4.58 | 4.58 | 4.82 | 4.31 | 4.79 | 5.79 | 5.25 | 5.63 | 5.87 | 5.96 | 3.3 | 2.94 | 3.22 | 3.28 | 3.13 | 3.08 | 2.87 | 3.97 | 4.24 | 4.5 | 4.77 | 4.09 | 3.54 | 3.6 | 4.05 | 3.6 | 3.15 | 3.44 | 3.69 | 3.65 | 3.65 | 3.32 | 3.03 | 3.43 | 3.42 | 3.56 | 3.52 | 0 | 0 | 0 | 0 | 3.71 | 6805.3 | 127
Mr. Sanjay Kumar Gupta | TA512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.58 | 2.58 | 2.73 | 4.16 | 4.73 | 4.42 | 4.47 | 5.45 | 5.43 | 5.44 | 5.1 | 4.98 | 4.71 | 5.49 | 4.78 | 4.85 | 5.25 | 5.43 | 4 | 4.03 | 3.84 | 3.78 | 3.83 | 3.26 | 3.13 | 3.68 | 4.21 | 5.42 | 6.38 | 0 | 0 | 0 | 4.31 | 5632.04 | 140
Mr. Sanjay Kumar Gupta | TB401 | 1.94 | 5.01 | 5.1 | 4.6 | 3.55 | 3.54 | 4.09 | 2.94 | 2.99 | 2.81 | 3.23 | 4.19 | 5.01 | 4.87 | 5.09 | 5.07 | 5.47 | 5.83 | 5.03 | 4.22 | 4.96 | 4.77 | 4.09 | 3.29 | 2.57 | 2.66 | 3.24 | 3.09 | 3.3 | 3 | 4.52 | 4.62 | 4.55 | 5.08 | 5.03 | 4.62 | 4.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.35 | 11489.47 | 242
Mr. Sanjay Kumar Gupta | TB408 | 6.42 | 4.32 | 4.16 | 4.67 | 6.47 | 1.18 | 1.15 | 3.42 | 2.31 | 1.18 | 1.71 | 2.63 | 3.12 | 3.81 | 3.56 | 4.15 | 5.51 | 5.25 | 4.06 | 4.47 | 4.88 | 4.83 | 4.94 | 4.32 | 4.67 | 4.65 | 4.47 | 4.2 | 4.94 | 4.43 | 4.48 | 4.19 | 4.45 | 4.13 | 4.26 | 3.98 | 4.27 | 4.96 | 4.67 | 4.08 | 4.09 | 6.22 | 8.68 | 7.18 | 5.68 | 0 | 0 | 0 | 4.43 | 11854.96 | 247
Mr. Sanjay Kumar Gupta | TB507 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.28 | 1.21 | 1.64 | 1.41 | 1.41 | 1.58 | 1.69 | 1.59 | 1.48 | 1.56 | 1.38 | 1.12 | 1.44 | 1.84 | 2.11 | 2.21 | 2.56 | 2.2 | 2.29 | 2.49 | 2.49 | 2.23 | 1.87 | 2.14 | 1.92 | 1.92 | 1.87 | 2.28 | 2.38 | 2.11 | 2.17 | 3.59 | 4.39 | 3.48 | 0 | 0 | 0 | 1.88 | 2697.56 | 178
[50 empty] | Total | 48592.41 | 1141
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
PCH: Mr. Arun Felbin
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
Mr. Arun Felbin | TA325 | 4.24 | 4.55 | 4.48 | 4.11 | 4.06 | 3.79 | 3.45 | 2.58 | 2.88 | 2.4 | 1.58 | 1.41 | 1.41 | 1.33 | 1.21 | 1.22 | 1.18 | 1.17 | 1.16 | 0.99 | 0.95 | 1.02 | 1.01 | 1.07 | 1.42 | 2.04 | 2.68 | 4.01 | 4.2 | 3.82 | 3.53 | 3.59 | 3.92 | 4.3 | 4.6 | 4.3 | 3.63 | 3.3 | 3.47 | 3.75 | 3.68 | 3.64 | 0 | 0 | 0 | 0 | 0 | 0 | 3.16 | 13361.73 | 190
Mr. Arun Felbin | TA414 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.12 | 4.82 | 5.03 | 2.69 | 2.69 | 0 | 0 | 0 | 4.24 | 4.24 | 4.3 | 4.03 | 4.15 | 4.07 | 5.44 | 3.45 | 2.07 | 1.77 | 0.96 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.96 | 2.65 | 3.52 | 3.32 | 3.63 | 3.3 | 3.48 | 3.79 | 4.46 | 4.24 | 0 | 0 | 0 | 0 | 3.49 | 3869.12 | 77
Mr. Arun Felbin | TA416 | 4.96 | 5.55 | 5.69 | 6.74 | 6.36 | 6.04 | 5.48 | 5.65 | 5.8 | 5.77 | 5.46 | 5.73 | 5.75 | 4.95 | 4.99 | 4.99 | 5.17 | 4.65 | 3.98 | 3.57 | 3.48 | 3.55 | 3.77 | 4.02 | 4.18 | 4.27 | 4.36 | 4.29 | 3.72 | 3.68 | 3.57 | 3.57 | 4.01 | 4.42 | 4.32 | 4.01 | 3.44 | 3.22 | 3.02 | 3.03 | 3.18 | 3.14 | 4.14 | 3.95 | 3.67 | 0 | 0 | 0 | 4.59 | 11398.61 | 168
Mr. Arun Felbin | TA418 | 3.95 | 3.33 | 3.27 | 3.59 | 2.79 | 2.79 | 2.35 | 1.77 | 3.02 | 2.74 | 3.28 | 2.97 | 1.94 | 1.92 | 2.1 | 2.27 | 1.89 | 1.44 | 2.44 | 2.66 | 3.13 | 1.67 | 2.65 | 2.3 | 2.66 | 2.41 | 2.24 | 2.03 | 2.21 | 2.2 | 2.25 | 2.4 | 2.76 | 2.17 | 2.45 | 3.57 | 2.98 | 3.51 | 3.45 | 2.85 | 3.28 | 3.52 | 2.49 | 3.88 | 5.39 | 0 | 0 | 0 | 2.62 | 3287.86 | 86
Mr. Arun Felbin | TA421 | 6.38 | 5.92 | 6.96 | 7.97 | 8.22 | 6.84 | 5.36 | 3.77 | 3.97 | 4.82 | 3.81 | 5.41 | 5.24 | 5.65 | 5.19 | 4.94 | 3.98 | 6.1 | 5.95 | 3.81 | 3.69 | 4.37 | 6.89 | 6.07 | 4.3 | 4.45 | 3.77 | 5.5 | 5.64 | 4.81 | 4.56 | 7.05 | 6.18 | 6.49 | 7.46 | 6.99 | 7.21 | 8.45 | 11.26 | 8.17 | 6.85 | 6.41 | 0 | 0 | 0 | 0 | 0 | 0 | 5.7 | 8109.77 | 187
Mr. Arun Felbin | TA601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1 | 5.75 | 4.03 | 3.13 | 2.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.98 | 182.87 | 5
Mr. Arun Felbin | TB501 | 1.98 | 2.89 | 2.81 | 2.63 | 3.02 | 3.04 | 2.52 | 2.78 | 2.29 | 4.2 | 3.27 | 2.28 | 2.52 | 2.43 | 2.26 | 2.51 | 5.46 | 2.71 | 2.46 | 2.02 | 2.3 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 2.58 | 1.99 | 2.14 | 1.23 | 1.58 | 1.2 | 1.53 | 0.86 | 2.93 | 3.21 | 2.38 | 4.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.38 | 772.99 | 106
[50 empty] | Total | 40982.95 | 819
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
PCH: Mr. Dheeraj Vashishth
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
Mr. Dheeraj Vashishth | TA513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.83 | 2.65 | 3.27 | 4.39 | 4.86 | 3.79 | 3.94 | 4.24 | 3.93 | 3.71 | 4.28 | 3.47 | 3.91 | 4.12 | 4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.84 | 411.02 | 18
[50 empty] | Total | 411.02 | 18
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
PCH: Mr. Nabajit Baruah
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
Mr. Nabajit Baruah | TA504 | 7.33 | 5.88 | 7.17 | 6.58 | 4.56 | 4.26 | 4.98 | 6 | 4.5 | 6.03 | 7.04 | 7 | 0 | 2.4 | 2.4 | 2.55 | 3.6 | 3.05 | 2.77 | 2.3 | 2.35 | 2.39 | 2.44 | 2.96 | 3.51 | 4.08 | 4.04 | 4.11 | 4.13 | 3.94 | 3.9 | 4.46 | 4.21 | 4.61 | 4.99 | 5.22 | 5.04 | 5.26 | 5.4 | 4.94 | 4.79 | 4.9 | 4.62 | 5.22 | 8.8 | 0 | 0 | 0 | 4.49 | 3704 | 77
Mr. Nabajit Baruah | TA505 | 4.67 | 5.4 | 6.31 | 5.59 | 5.29 | 4.53 | 5.03 | 4.62 | 5.04 | 4.49 | 4.28 | 2.77 | 4.26 | 3.61 | 3.11 | 3.33 | 3.77 | 4.4 | 6.74 | 4.9 | 4.26 | 3.7 | 3.61 | 3.93 | 4.17 | 4.9 | 4.59 | 4.77 | 4.95 | 4.39 | 3.48 | 3.81 | 3.95 | 4.26 | 4.89 | 4.74 | 4.93 | 5.15 | 5.5 | 5.62 | 5 | 4.58 | 4.73 | 5.26 | 4.89 | 0 | 0 | 0 | 4.61 | 12278.74 | 261
Mr. Nabajit Baruah | TA506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.37 | 3.76 | 3.7 | 3.82 | 4.36 | 3.93 | 3.87 | 4.58 | 4.76 | 4.88 | 5.59 | 5.74 | 5.12 | 4.83 | 4.39 | 3.72 | 3.2 | 3.42 | 3.13 | 3.73 | 4.6 | 4.63 | 4.35 | 4.45 | 0 | 0 | 0 | 4.29 | 6929 | 268
[50 empty] | Total | 22911.74 | 606
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
PCH: Mr. Sanjay Kumar Gupta
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 4.25 | Week 1: 3.42; Week 2: 3.42; Week 3: 4.62; Week 4: 4.36; Week 5: 4.05; Week 6: 3.8; Week 7: 3.88; Week 8: 3.76; Week 9: 3.65; Week 10: 5.82
No of Gangs engaged (Avg) | 22 | Week 1: 24; Week 2: 40; Week 3: 69; Week 4: 94; Week 5: 76; Week 6: 63; Week 7: 63; Week 8: 70; Week 9: 48; Week 10: 14
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
PCH: Mr. Arun Felbin
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 4.89 | Week 1: 4.43; Week 2: 3.62; Week 3: 2.93; Week 4: 2.88; Week 5: 3.12; Week 6: 3.69; Week 7: 3.97; Week 8: 3.99; Week 9: 3.8; Week 10: 3.95
No of Gangs engaged (Avg) | 45 | Week 1: 48; Week 2: 34; Week 3: 33; Week 4: 39; Week 5: 50; Week 6: 66; Week 7: 68; Week 8: 63; Week 9: 39; Week 10: 7
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
PCH: Mr. Dheeraj Vashishth
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 0 | Week 1: 0; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 2.78; Week 6: 4; Week 7: 4.11; Week 8: 3.9; Week 9: 0; Week 10: 0
No of Gangs engaged (Avg) | 0 | Week 1: 0; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 1; Week 6: 1; Week 7: 1; Week 8: 1; Week 9: 0; Week 10: 0
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
PCH: Mr. Nabajit Baruah
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 5.84 | Week 1: 4.91; Week 2: 4.27; Week 3: 3.32; Week 4: 3.99; Week 5: 3.94; Week 6: 4.36; Week 7: 4.64; Week 8: 4.74; Week 9: 4.73; Week 10: 4.89
No of Gangs engaged (Avg) | 8 | Week 1: 9; Week 2: 7; Week 3: 5; Week 4: 17; Week 5: 43; Week 6: 32; Week 7: 33; Week 8: 41; Week 9: 36; Week 10: 13

## Gang Level Productivity
Scope: 2025-04-01 to 2026-02-28 ¦ Projects: 17 ¦ Erections: 2584 ¦ Gangs: 429
PCH | Project | Gang Name | Avg Productivity (MTD) | Avg Productivity (Overall) | Total MT (MTD) | Total No. of Erections (MTD) | Avg Tower Weight Overall | Idle Counted (days) | Number of Idle Intervals | Prod_Bucket | Productivity Bucket | Output Share | Gang Share
Mr. Sanjay Kumar Gupta | TA413 | Amar Kumar Singh | 3.33 | 3.33 | 223.06 | 4 | 55.77 | 3 | 1 | 0-4 | 0-4 | 32.45% | 48.78%
Mr. Sanjay Kumar Gupta | TA413 | Amit Kumar Singh | 4.38 | 4.38 | 354.72 | 8 | 44.34 | 1 | 1 | 4-6 | 4-6 | 43.08% | 35.57%
Mr. Sanjay Kumar Gupta | TA413 | Bambole Traders | 1.38 | 1.38 | 45.7 | 1 | 45.7 | 0 | 0 | 0-4 | 6-8 | 20.64% | 13.01%
Mr. Sanjay Kumar Gupta | TA413 | Bhairaw Mahto | 4.31 | 4.31 | 318.65 | 5 | 63.73 | 7 | 1 | 4-6 | 8-10 | 3.666% | 2.033%
Mr. Sanjay Kumar Gupta | TA413 | Fouzi Ratto | 5.04 | 5.04 | 669.87 | 12 | 55.82 | 2 | 1 | 4-6 | 10+ | 0.1553% | 0.6098%
Mr. Sanjay Kumar Gupta | TA413 | Govind Mahto 1 | 4.48 | 4.48 | 515.57 | 12 | 42.96 | 11 | 4 | 4-6 | Grand Total | 100% | 100%
Mr. Sanjay Kumar Gupta | TA413 | Govind Mahto 2 | 4.93 | 4.93 | 522.54 | 9 | 58.06 | 4 | 1 | 4-6
Mr. Sanjay Kumar Gupta | TA413 | Jwala Singh 1 | 3.97 | 4.11 | 936.06 | 22 | 42.55 | 15 | 4 | 0-4
Mr. Sanjay Kumar Gupta | TA413 | Jwala Singh 2 | 5.31 | 5.81 | 695.82 | 15 | 46.39 | 28 | 7 | 4-6
Mr. Sanjay Kumar Gupta | TA413 | Kartik Mahto | 4.31 | 4.31 | 241.46 | 5 | 48.29 | 0 | 0 | 4-6 | Productivity Bucket | Gang Share | Output Share
Mr. Sanjay Kumar Gupta | TA413 | Pinki Devi | 4.18 | 4.6 | 83.63 | 2 | 41.81 | 4 | 1 | 4-6 | 0-4 | 48.78% | 32.45%
Mr. Sanjay Kumar Gupta | TA413 | Pritam Enterprises | 4.57 | 3.27 | 105.2 | 2 | 52.6 | 0 | 0 | 4-6 | 4-6 | 35.57% | 43.08%
Mr. Sanjay Kumar Gupta | TA413 | Pritam Enterprises 1 | 3.37 | 3.37 | 390.73 | 9 | 43.41 | 12 | 4 | 0-4 | 6-8 | 13.01% | 20.64%
Mr. Sanjay Kumar Gupta | TA413 | Pritam Enterprises 2 | 3.37 | 3.37 | 619.68 | 13 | 47.67 | 4 | 1 | 0-4 | 8-10 | 2.033% | 3.666%
Mr. Sanjay Kumar Gupta | TA413 | Pritam Enterprises 3 | 5.22 | 5.22 | 428.06 | 9 | 47.56 | 0 | 0 | 4-6 | 10+ | 0.61% | 0.16%
Mr. Sanjay Kumar Gupta | TA413 | Pritam Enterprises 4 | 2.82 | 2.82 | 262.62 | 6 | 43.77 | 8 | 2 | 0-4
Mr. Sanjay Kumar Gupta | TA413 | Punam Devi 1 | 4.31 | 5.83 | 145.97 | 3 | 48.66 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TA413 | Punam Devi 2 | 4.52 | 5.03 | 148.52 | 3 | 49.51 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TA413 | Punam Devi 3 | 5.13 | 1.26 | 129.32 | 3 | 43.11 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TA413 | Punam Devi 4 | 6.53 | 7.87 | 45.7 | 1 | 45.7 | 0 | 0 | 6-8
Mr. Sanjay Kumar Gupta | TA413 | Punam Kumari | 5.6 | 3.84 | 196.11 | 4 | 49.03 | 2 | 1 | 4-6
Mr. Sanjay Kumar Gupta | TA413 | Punam Kumari 1 | 4.38 | 4.48 | 674.27 | 15 | 44.95 | 2 | 1 | 4-6
Mr. Sanjay Kumar Gupta | TA413 | Punam Kumari 2 | 7.56 | 5.33 | 605.17 | 13 | 46.55 | 2 | 1 | 6-8
Mr. Sanjay Kumar Gupta | TA413 | Punam Kumari 3 | 4.66 | 3.88 | 116.52 | 3 | 38.84 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TA413 | Punam Kumari 4 | 4.94 | 4.82 | 182.88 | 4 | 45.72 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TA413 | Sk Samiul 1 | 3.5 | 3.5 | 321.96 | 7 | 45.99 | 7 | 3 | 0-4
Mr. Sanjay Kumar Gupta | TA413 | Sk Samiul 2 | 3.23 | 3.23 | 145.46 | 4 | 36.37 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA413 | Vasu Dev Singh 2 | 4.14 | 3.67 | 57.96 | 1 | 57.96 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TA413 | Ved Prakash | 6.2 | 6.2 | 929.86 | 12 | 77.49 | 0 | 0 | 6-8
Mr. Sanjay Kumar Gupta | TA419 | Amit Yadav | 1.72 | 1.72 | 86.15 | 2 | 43.07 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA419 | Bhairo Mahato | 3 | 3 | 377.81 | 4 | 94.45 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA419 | Dhruv Enterprises | 2.34 | 2.34 | 117.02 | 2 | 58.51 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA419 | Dhruv Enterprises 2 | 2.65 | 2.65 | 42.37 | 1 | 42.37 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA419 | Gagan Enterprises | 4.44 | 4.4 | 197.89 | 4 | 49.47 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TA419 | Ganesh | 3.62 | 3.88 | 97.71 | 2 | 48.86 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA419 | Ganesh 1 | 3.53 | 3.53 | 109.49 | 2 | 54.74 | 3 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TA419 | Ganesh 2 | 1.87 | 1.87 | 196.68 | 4 | 49.17 | 4 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TA419 | Infinedea 1 | 2.26 | 2.26 | 36.16 | 1 | 36.16 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA419 | Infinidea | 1.4 | 1.4 | 204.53 | 4 | 51.13 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA419 | Infinidea 2 | 2.26 | 2.26 | 113 | 3 | 37.67 | 5 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TA419 | Jwala Singh | 5.15 | 6.56 | 541.26 | 13 | 41.64 | 6 | 4 | 4-6
Mr. Sanjay Kumar Gupta | TA419 | Madhu Sah | 4.07 | 2.28 | 1119.03 | 23 | 48.65 | 5 | 2 | 4-6
Mr. Sanjay Kumar Gupta | TA419 | Mukhilal | 3.27 | 3.27 | 78.57 | 2 | 39.28 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA419 | Mukhilal 1 | 1.86 | 1.86 | 37.14 | 1 | 37.14 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA419 | Mukhilal 2 | 5.21 | 5.21 | 124.95 | 1 | 124.95 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TA419 | Poonam Kumari | 4.99 | 4.04 | 124.83 | 2 | 62.41 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TA419 | Poonam Kumari 2 | 3.13 | 3.13 | 43.8 | 1 | 43.8 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA419 | Poornam Kumari | 4.26 | 4.13 | 177.4 | 4 | 44.35 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TA419 | Punam Kumari 1 | 4.57 | 4.48 | 224.11 | 4 | 56.03 | 2 | 1 | 4-6
Mr. Sanjay Kumar Gupta | TA419 | Punam Kumari 2 | 3.93 | 5.33 | 337.72 | 5 | 67.54 | 2 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TA419 | Punam Kumari 4 | 4.38 | 4.82 | 43.8 | 1 | 43.8 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TA419 | Radha Enterprises | 6.66 | 5.61 | 659.6 | 8 | 82.45 | 8 | 2 | 6-8
Mr. Sanjay Kumar Gupta | TA419 | Radha Enterprises 1 | 5.34 | 5.16 | 635.35 | 13 | 48.87 | 10 | 2 | 4-6
Mr. Sanjay Kumar Gupta | TA419 | Raju Kumar | 3.68 | 3.68 | 235.29 | 4 | 58.82 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA419 | Rohit | 3.57 | 3.57 | 224.93 | 4 | 56.23 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA419 | Sanjeet | 4.36 | 4.36 | 305.35 | 5 | 61.07 | 5 | 4 | 4-6
Mr. Sanjay Kumar Gupta | TA419 | Satyam Trading | 3.97 | 3.97 | 313.36 | 7 | 44.77 | 2 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TA512 | M S Company Gang | 1.47 | 1.47 | 278.73 | 8 | 34.84 | 1 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TA512 | M S Ganesh Sinha | 3.96 | 3.96 | 71.2 | 2 | 35.6 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA512 | M S Govind Mahto | 5.91 | 5.91 | 165.36 | 4 | 41.34 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TA512 | M S Govind Mahto 2 | 4.44 | 4.44 | 271.01 | 6 | 45.17 | 1 | 1 | 4-6
Mr. Sanjay Kumar Gupta | TA512 | M S Jirwa Debi | 4.36 | 4.36 | 74.09 | 2 | 37.05 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TA512 | M S Jwala Singh | 5.26 | 5.26 | 898.64 | 21 | 42.79 | 6 | 6 | 4-6
Mr. Sanjay Kumar Gupta | TA512 | M S Jwala Singh 2 | 5.24 | 5.24 | 408.59 | 10 | 40.86 | 9 | 2 | 4-6
Mr. Sanjay Kumar Gupta | TA512 | M S Karni Construction 1 | 2.44 | 2.44 | 80.49 | 2 | 40.24 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA512 | M S Karni Construction 2 | 2.99 | 2.99 | 122.4 | 3 | 40.8 | 1 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TA512 | M S Kartik Mahto | 6.97 | 6.97 | 948.13 | 24 | 39.51 | 0 | 0 | 6-8
Mr. Sanjay Kumar Gupta | TA512 | M S Kavya Enterprises | 3.59 | 3.59 | 486.91 | 12 | 40.58 | 15 | 4 | 0-4
Mr. Sanjay Kumar Gupta | TA512 | M S Mohika Costruction | 2.11 | 2.11 | 18.97 | 1 | 18.97 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA512 | M S Nirmal Mahto | 3.45 | 3.45 | 37.93 | 1 | 37.93 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA512 | M S Punam Kumari | 4.77 | 4.77 | 577.73 | 15 | 38.52 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TA512 | M S Punam Kumari 3 | 4.08 | 4.08 | 305.78 | 8 | 38.22 | 3 | 3 | 4-6
Mr. Sanjay Kumar Gupta | TA512 | M S Punam Kumari 4 | 4.75 | 4.75 | 313.44 | 7 | 44.78 | 5 | 2 | 4-6
Mr. Sanjay Kumar Gupta | TA512 | M S Raju Kumar | 5.06 | 5.06 | 202.36 | 5 | 40.47 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TA512 | M S Shobha Debi | 7.38 | 7.38 | 147.62 | 4 | 36.91 | 2 | 1 | 6-8
Mr. Sanjay Kumar Gupta | TA512 | M S Shree Shyam Construction | 2.82 | 2.82 | 81.86 | 2 | 40.93 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TA512 | M S Sunny Construction | 5.63 | 5.63 | 140.8 | 3 | 46.93 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Anil Kumar Departmental Kewat | 1.34 | 1.34 | 38.85 | 1 | 38.85 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Anil Kumar Departmental Ramayan | 2.33 | 2.33 | 86.13 | 1 | 86.13 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Anil Kumar Ramayan Departmental | 3.19 | 3.19 | 86.13 | 1 | 86.13 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Anjani Enterprises | 1.75 | 1.75 | 45.41 | 1 | 45.41 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Anjani Power Priyanka Devi Sudheer | 0.43 | 0.43 | 38.85 | 1 | 38.85 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Annaya Traders | 2.08 | 2.08 | 37.5 | 1 | 37.5 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Arawali | 4.54 | 4.54 | 45.41 | 1 | 45.41 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Arawali Infra 1 | 6.25 | 6.25 | 37.5 | 1 | 37.5 | 0 | 0 | 6-8
Mr. Sanjay Kumar Gupta | TB401 | Arawali Infra 2 | 5.23 | 5.23 | 230.2 | 4 | 57.55 | 12 | 4 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Bhairo Mahto | 4.32 | 2.37 | 38.85 | 1 | 38.85 | 2 | 2 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Bhairo Mahto Departmental | 1.18 | 1.18 | 121.76 | 3 | 40.59 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Bhairo Mahto Departmental Arawali | 3.74 | 3.74 | 100.96 | 1 | 100.96 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Chinta Devi | 7.7 | 6.34 | 207.8 | 5 | 41.56 | 10 | 5 | 6-8
Mr. Sanjay Kumar Gupta | TB401 | Devi Construction | 5.9 | 5.93 | 47.18 | 1 | 47.18 | 5 | 3 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Ganesg Sinha | 4.54 | 4.54 | 45.41 | 1 | 45.41 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Ganesh Kr Sinha | 3.03 | 4.34 | 45.41 | 1 | 45.41 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Ganesh Sinha | 4.29 | 4.53 | 47.18 | 1 | 47.18 | 14 | 3 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Gourishankar | 6.22 | 6.26 | 236.22 | 5 | 47.24 | 11 | 6 | 6-8
Mr. Sanjay Kumar Gupta | TB401 | Jawala Singh | 4.69 | 4.69 | 37.5 | 1 | 37.5 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Jawala Singh Suraj | 6.49 | 6.49 | 45.41 | 1 | 45.41 | 0 | 0 | 6-8
Mr. Sanjay Kumar Gupta | TB401 | Jirwa Devi | 5.01 | 4.18 | 105.23 | 2 | 52.61 | 14 | 4 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Jwala Singh | 6.47 | 6.56 | 38.85 | 1 | 38.85 | 6 | 4 | 6-8
Mr. Sanjay Kumar Gupta | TB401 | Jwala Singh 1 | 5.62 | 4.11 | 140.51 | 3 | 46.84 | 15 | 4 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Jwala Singh 2 | 6.2 | 5.81 | 216.86 | 5 | 43.37 | 28 | 7 | 6-8
Mr. Sanjay Kumar Gupta | TB401 | Jwala Singh 3 | 8.09 | 8.09 | 283.16 | 5 | 56.63 | 8 | 3 | 8-10
Mr. Sanjay Kumar Gupta | TB401 | Jwala Singh 3 Bhairo Mahto | 1.7 | 1.7 | 129.11 | 1 | 129.11 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Kamlesh | 3.72 | 3.72 | 70.7 | 1 | 70.7 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Kewat Departmental | 1.79 | 1.79 | 37.5 | 1 | 37.5 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Laxmi | 4.24 | 4.24 | 76.35 | 2 | 38.18 | 2 | 2 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Nirmal Mahto | 5.78 | 4.57 | 150.19 | 3 | 50.06 | 2 | 1 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Pankaj | 6.25 | 6.34 | 37.5 | 1 | 37.5 | 7 | 4 | 6-8
Mr. Sanjay Kumar Gupta | TB401 | Panva Devi | 7.49 | 4.19 | 89.91 | 1 | 89.91 | 2 | 1 | 6-8
Mr. Sanjay Kumar Gupta | TB401 | Permanand | 1.85 | 1.85 | 38.85 | 1 | 38.85 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Poonam | 7.19 | 7.19 | 366.88 | 9 | 40.76 | 8 | 3 | 6-8
Mr. Sanjay Kumar Gupta | TB401 | Priyanka Devi | 4.33 | 4.01 | 103.88 | 2 | 51.94 | 10 | 2 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Priyanka Devi 2 | 5.76 | 5.09 | 115.2 | 3 | 38.4 | 13 | 3 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Priyanka Devi Santosh | 1.18 | 1.82 | 38.85 | 1 | 38.85 | 4 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Priyanka Devi Subodh | 3.53 | 3.71 | 38.85 | 1 | 38.85 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Priyanka Devi Sudheer | 4.97 | 5.48 | 437.29 | 10 | 43.73 | 41 | 13 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Priyanka Devi Sudheer 2 | 5.55 | 5.55 | 38.85 | 1 | 38.85 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Pusplata 1 | 7.43 | 7.43 | 282.37 | 6 | 47.06 | 5 | 3 | 6-8
Mr. Sanjay Kumar Gupta | TB401 | Pusplata 2 | 6.4 | 6.4 | 224.04 | 5 | 44.81 | 0 | 0 | 6-8
Mr. Sanjay Kumar Gupta | TB401 | Pusplata 3 | 7.14 | 7.14 | 171.45 | 4 | 42.86 | 14 | 2 | 6-8
Mr. Sanjay Kumar Gupta | TB401 | Pusplata 3 Jwala | 2.25 | 2.25 | 47.18 | 1 | 47.18 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Pusplata 4 | 8.04 | 8.04 | 313.74 | 8 | 39.22 | 2 | 2 | 8-10
Mr. Sanjay Kumar Gupta | TB401 | Pusplata 5 | 5.41 | 5.41 | 162.38 | 4 | 40.6 | 1 | 1 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Pusplata 6 | 5.31 | 5.31 | 212.59 | 5 | 42.52 | 3 | 1 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Pusplata 7 | 4.66 | 4.66 | 116.54 | 3 | 38.85 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Pusplata Ashok | 1.28 | 1.68 | 191.12 | 4 | 47.78 | 3 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Pusplata Deepak | 5.22 | 5.4 | 151.36 | 4 | 37.84 | 12 | 4 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Pusplata Dharamveer | 3.37 | 4.48 | 47.18 | 1 | 47.18 | 1 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Pusplata Pankaj | 6.25 | 6.36 | 37.5 | 1 | 37.5 | 0 | 0 | 6-8
Mr. Sanjay Kumar Gupta | TB401 | Pusplata Praful | 5.62 | 5.32 | 89.91 | 1 | 89.91 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Pusplata Rajaram | 5.62 | 4.87 | 89.91 | 1 | 89.91 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Pusplata Ramchander | 6.27 | 6.27 | 81.49 | 1 | 81.49 | 0 | 0 | 6-8
Mr. Sanjay Kumar Gupta | TB401 | Pusplata Santosh | 7.86 | 7.86 | 47.18 | 1 | 47.18 | 0 | 0 | 6-8
Mr. Sanjay Kumar Gupta | TB401 | Rahul Kumar | 5.57 | 5.35 | 272.83 | 6 | 45.47 | 20 | 10 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Sanjeev Kumar | 4.18 | 4.38 | 213.37 | 4 | 53.34 | 1 | 1 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Satyam Manish | 8.5 | 8.28 | 747.84 | 13 | 57.53 | 11 | 5 | 8-10
Mr. Sanjay Kumar Gupta | TB401 | Satyam Manish 2 Santosh | 2.16 | 2.16 | 38.85 | 1 | 38.85 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Satyam Mondal | 5.05 | 5.05 | 348.59 | 7 | 49.8 | 6 | 4 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Satyam Nitish | 7.81 | 7.81 | 632.23 | 9 | 70.25 | 5 | 3 | 6-8
Mr. Sanjay Kumar Gupta | TB401 | Satyam Santosh | 2.31 | 2.31 | 76.35 | 2 | 38.18 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Satyam Trivedi | 2.29 | 1.52 | 287.81 | 7 | 41.12 | 7 | 3 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Satyam Trivedi Nitish | 4.32 | 4.32 | 38.85 | 1 | 38.85 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Satyam Vijay | 4.88 | 4.88 | 376.1 | 9 | 41.79 | 7 | 3 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Shri Shyam | 3.24 | 3.24 | 45.41 | 1 | 45.41 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Shyam Construction | 2.99 | 2.99 | 38.85 | 1 | 38.85 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Sital Singh | 4.57 | 4.57 | 132.6 | 3 | 44.2 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Sital Singh 1 | 4.63 | 4.63 | 231.74 | 5 | 46.35 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Sital Singh 2 | 4.02 | 4.02 | 76.35 | 2 | 38.18 | 15 | 2 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Sobha Devi | 7.91 | 6.58 | 245.3 | 6 | 40.88 | 3 | 1 | 6-8
Mr. Sanjay Kumar Gupta | TB401 | Sunny Const | 5.33 | 5.74 | 629.41 | 13 | 48.42 | 3 | 2 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Usha Tower | 3.52 | 3.38 | 123.11 | 3 | 41.04 | 6 | 3 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Vedanta Const | 4.46 | 4.46 | 84.69 | 2 | 42.34 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB401 | Vinay Const | 3.81 | 3.81 | 133.22 | 3 | 44.4 | 4 | 2 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Vinay Const 2 | 2.77 | 2.77 | 38.85 | 1 | 38.85 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB401 | Vivek Ganju | 3.76 | 3.61 | 236.96 | 6 | 39.49 | 7 | 5 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Anil Kumar Kewat | 1.23 | 1.23 | 76.35 | 2 | 38.18 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Anvi Construction | 2.29 | 2.29 | 38.85 | 1 | 38.85 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Arawali 1 | 9.57 | 9.57 | 86.13 | 1 | 86.13 | 0 | 0 | 8-10
Mr. Sanjay Kumar Gupta | TB408 | Arawali 2 | 5.18 | 5.18 | 113.86 | 3 | 37.95 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Bhairo Mahto | 2.2 | 2.37 | 229.06 | 6 | 38.18 | 2 | 2 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Bhairo Mahto Kewat | 1.99 | 1.99 | 123.63 | 2 | 61.82 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Bhairo Mahto Priyanka Devi Subodh | 2.97 | 2.97 | 86.13 | 1 | 86.13 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Chinta Devi | 5.75 | 6.34 | 1226.41 | 22 | 55.75 | 10 | 5 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Devi Construction | 5.94 | 5.93 | 421.63 | 6 | 70.27 | 5 | 3 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Dharmendra Munnilal Pusplata | 3.53 | 3.53 | 38.85 | 1 | 38.85 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Dular Chand Patel | 1.34 | 1.34 | 75.01 | 2 | 37.5 | 3 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Ganesh Sinha | 5.01 | 4.53 | 721.44 | 16 | 45.09 | 14 | 3 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Gauri Shankar | 5.89 | 5.89 | 70.7 | 1 | 70.7 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Hazarilal Yadav Poonam Kumari | 9.54 | 9.54 | 76.35 | 2 | 38.18 | 0 | 0 | 8-10
Mr. Sanjay Kumar Gupta | TB408 | Jirwa Devi | 4.51 | 4.18 | 513.86 | 11 | 46.71 | 14 | 4 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Jwala Singh | 5.19 | 6.56 | 374.03 | 9 | 41.56 | 6 | 4 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Jwala Singh 1 | 3.96 | 4.11 | 95.1 | 2 | 47.55 | 15 | 4 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Jwala Singh 2 | 5.55 | 5.81 | 38.85 | 1 | 38.85 | 28 | 7 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Jwala Singh Suraj Kumar | 6.26 | 6.26 | 162.83 | 3 | 54.28 | 0 | 0 | 6-8
Mr. Sanjay Kumar Gupta | TB408 | Kamlesh Kumar | 3.23 | 3.23 | 187.24 | 4 | 46.81 | 2 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Nirmal Mahto | 3.66 | 4.57 | 493.53 | 11 | 44.87 | 2 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Panva Devi | 3.61 | 4.19 | 249.36 | 4 | 62.34 | 2 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Priyanka Devi | 3.82 | 4.01 | 152.7 | 4 | 38.18 | 10 | 2 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Priyanka Devi 2 | 3.75 | 5.09 | 37.5 | 1 | 37.5 | 13 | 3 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Priyanka Devi Santosh | 4.17 | 1.82 | 37.5 | 1 | 37.5 | 4 | 1 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Priyanka Devi Sontosh | 5.76 | 5.76 | 57.6 | 1 | 57.6 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Priyanka Devi Subodh | 3.76 | 3.71 | 142.73 | 3 | 47.58 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Priyanka Devi Sudheer | 8.7 | 5.48 | 121.77 | 3 | 40.59 | 41 | 13 | 8-10
Mr. Sanjay Kumar Gupta | TB408 | Pusplata | 8.3 | 8.3 | 66.38 | 1 | 66.38 | 0 | 0 | 8-10
Mr. Sanjay Kumar Gupta | TB408 | Pusplata Ashok | 8.33 | 1.68 | 75.01 | 2 | 37.5 | 3 | 1 | 8-10
Mr. Sanjay Kumar Gupta | TB408 | Pusplata Deepak | 6.25 | 5.4 | 37.5 | 1 | 37.5 | 12 | 4 | 6-8
Mr. Sanjay Kumar Gupta | TB408 | Pusplata Dharamveer | 5.26 | 4.48 | 105.23 | 2 | 52.61 | 1 | 1 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Pusplata Kailash | 5.47 | 5.47 | 267.9 | 7 | 38.27 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Pusplata Pankaj | 6.47 | 6.36 | 38.85 | 1 | 38.85 | 0 | 0 | 6-8
Mr. Sanjay Kumar Gupta | TB408 | Pusplata Praful | 5 | 5.32 | 75.01 | 2 | 37.5 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Pusplata Praphul | 6.92 | 6.92 | 89.91 | 1 | 89.91 | 0 | 0 | 6-8
Mr. Sanjay Kumar Gupta | TB408 | Pusplata Rajaram | 4.32 | 4.87 | 95.1 | 2 | 47.55 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Pusplata Ramchandra | 2.04 | 2.04 | 77.7 | 2 | 38.85 | 11 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Pusplata Santosh Pankaj Singh | 7.38 | 7.38 | 66.38 | 1 | 66.38 | 0 | 0 | 6-8
Mr. Sanjay Kumar Gupta | TB408 | Rahul Kumar | 5.18 | 5.35 | 77.7 | 2 | 38.85 | 20 | 10 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Sanjeev Kumar | 4.73 | 4.38 | 245.89 | 5 | 49.18 | 1 | 1 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Santosh Singh | 4 | 4 | 103.89 | 2 | 51.94 | 2 | 1 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Santosh Singh Laxmi | 7.86 | 7.86 | 47.18 | 1 | 47.18 | 0 | 0 | 6-8
Mr. Sanjay Kumar Gupta | TB408 | Satyam Enterprises | 7.81 | 7.81 | 492.15 | 10 | 49.21 | 0 | 0 | 6-8
Mr. Sanjay Kumar Gupta | TB408 | Satyam Enterprises Manish | 6.47 | 6.47 | 38.85 | 1 | 38.85 | 0 | 0 | 6-8
Mr. Sanjay Kumar Gupta | TB408 | Satyam Enterprises Pawan | 6.47 | 6.47 | 38.85 | 1 | 38.85 | 0 | 0 | 6-8
Mr. Sanjay Kumar Gupta | TB408 | Satyam Enterprises Santosh | 0.95 | 0.95 | 38.85 | 1 | 38.85 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Satyam Enterprises Vijay | 4.67 | 4.67 | 154.05 | 4 | 38.51 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Satyam Manish | 5.55 | 8.28 | 38.85 | 1 | 38.85 | 11 | 5 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Sheetal Singh | 3.55 | 3.55 | 188.15 | 4 | 47.04 | 2 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Sheetal Singh 1 | 3.82 | 3.82 | 76.35 | 2 | 38.18 | 11 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Sheetal Singh 2 | 2.29 | 2.29 | 38.85 | 1 | 38.85 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Shobha Devi | 7.3 | 7.3 | 1153.97 | 19 | 60.74 | 26 | 5 | 6-8
Mr. Sanjay Kumar Gupta | TB408 | Shri Shyam Construction | 2.51 | 2.51 | 82.92 | 2 | 41.46 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Sintu Pawan Satyam Enterprises | 5.53 | 5.53 | 66.38 | 1 | 66.38 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Sobha Devi | 7.71 | 6.58 | 190.21 | 5 | 38.04 | 3 | 1 | 6-8
Mr. Sanjay Kumar Gupta | TB408 | Sudheer 2 Priyanka Devi | 14.4 | 14.4 | 57.6 | 1 | 57.6 | 0 | 0 | 10+
Mr. Sanjay Kumar Gupta | TB408 | Sunny Const | 2.61 | 5.74 | 86.13 | 1 | 86.13 | 3 | 2 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Sunny Construction | 6.59 | 6.59 | 679.11 | 14 | 48.51 | 2 | 1 | 6-8
Mr. Sanjay Kumar Gupta | TB408 | Usha Tower | 3.18 | 3.38 | 76.35 | 2 | 38.18 | 6 | 3 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Vedanta Construction | 1.97 | 1.97 | 187.52 | 5 | 37.5 | 1 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Vinay Construction | 3.17 | 3.22 | 415.59 | 10 | 41.56 | 3 | 2 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Vinay Construction Chinta Devi | 1.63 | 1.63 | 37.5 | 1 | 37.5 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB408 | Vinay Gupta | 5.05 | 5.05 | 45.41 | 1 | 45.41 | 0 | 0 | 4-6
Mr. Sanjay Kumar Gupta | TB408 | Vivek Ganju | 3.39 | 3.61 | 152.7 | 4 | 38.18 | 7 | 5 | 0-4
Mr. Sanjay Kumar Gupta | TB507 | Ahmed Construction | 1.54 | 1.54 | 101.95 | 8 | 12.74 | 3 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TB507 | Ajay Kumar | 0.96 | 3.77 | 29.87 | 2 | 14.94 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB507 | Ajay Kumar 1 | 1.14 | 1.14 | 41.02 | 3 | 13.67 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB507 | Ajay Kumar 2 | 1.16 | 1.16 | 23.14 | 2 | 11.57 | 1 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TB507 | Ayansh Const | 1.32 | 1.32 | 34.29 | 3 | 11.43 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB507 | Balaji Tour Travels 2 | 1.09 | 1.09 | 12 | 1 | 12 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB507 | Bhoi Enterprises | 1.99 | 1.99 | 253.31 | 19 | 13.33 | 2 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TB507 | Dipak | 2.8 | 2.8 | 483.64 | 31 | 15.6 | 6 | 4 | 0-4
Mr. Sanjay Kumar Gupta | TB507 | Gokul Sarkar | 2.62 | 2.62 | 404.23 | 23 | 17.58 | 2 | 1 | 0-4
Mr. Sanjay Kumar Gupta | TB507 | Namechand Mahto | 0.71 | 0.6 | 278.81 | 17 | 16.4 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB507 | Prayag Saw | 3.33 | 3.33 | 190.05 | 12 | 15.84 | 5 | 3 | 0-4
Mr. Sanjay Kumar Gupta | TB507 | Prayag Saw 1 | 3.38 | 3.38 | 216.25 | 14 | 15.45 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB507 | Prayag Saw 2 | 3.21 | 3.21 | 340.35 | 22 | 15.47 | 4 | 2 | 0-4
Mr. Sanjay Kumar Gupta | TB507 | Pritam Enterprises | 2.8 | 3.27 | 182.18 | 14 | 13.01 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB507 | Rajesh Mahto | 0.63 | 0.63 | 57.11 | 4 | 14.28 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB507 | Srikarni | 1.59 | 1.59 | 11.14 | 1 | 11.14 | 0 | 0 | 0-4
Mr. Sanjay Kumar Gupta | TB507 | Vinay Construction | 3.82 | 3.22 | 38.23 | 2 | 19.11 | 3 | 2 | 0-4
Mr. Arun Felbin | TA325 | Aamir Khan | 3.86 | 3.86 | 77.19 | 2 | 38.59 | 2 | 1 | 0-4
Mr. Arun Felbin | TA325 | Anarul Haque | 4.31 | 3.81 | 175.65 | 2 | 87.83 | 2 | 1 | 4-6
Mr. Arun Felbin | TA325 | Anita Devi | 5.33 | 5.33 | 298.41 | 3 | 99.47 | 4 | 2 | 4-6
Mr. Arun Felbin | TA325 | Anjum | 3.93 | 3.93 | 94.41 | 1 | 94.41 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Barkat Ali | 3.24 | 3 | 276.42 | 7 | 39.49 | 4 | 1 | 0-4
Mr. Arun Felbin | TA325 | Barkat Ali Mithun Kumar Vntl | 0.41 | 0.41 | 37.73 | 1 | 37.73 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Chitra Construction | 1.99 | 1.95 | 37.73 | 1 | 37.73 | 9 | 2 | 0-4
Mr. Arun Felbin | TA325 | Daulat Mahto | 2.56 | 3.74 | 92.15 | 2 | 46.07 | 9 | 1 | 0-4
Mr. Arun Felbin | TA325 | Dhaneshwar | 2.02 | 2.02 | 346.25 | 2 | 173.13 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Dhaneshwar Mahto Modina India 4 Prayag Rupesh Kumar | 2.24 | 2.24 | 156.83 | 1 | 156.83 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Dhaneswar Mahto | 6.2 | 6.96 | 198.27 | 3 | 66.09 | 12 | 2 | 6-8
Mr. Arun Felbin | TA325 | Dildar Electrical 2 4 Pgcil | 3.23 | 3.23 | 129.34 | 1 | 129.34 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Dildar Electrical 2 Pgcil | 2.63 | 2.63 | 39.46 | 1 | 39.46 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Dildar Electrical 3 | 2.36 | 2.36 | 37.73 | 1 | 37.73 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Dildar Electricals | 0.17 | 0.17 | 36.04 | 1 | 36.04 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Dildar Electricals 1 Pgcil | 3.22 | 3.22 | 77.19 | 2 | 38.59 | 12 | 2 | 0-4
Mr. Arun Felbin | TA325 | Dildar Electricals 1 Pgcil Prayag Mahto Nasirudin 2 | 3.73 | 3.73 | 156.83 | 1 | 156.83 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Dk Verma | 2.14 | 3.11 | 723.65 | 8 | 90.46 | 9 | 2 | 0-4
Mr. Arun Felbin | TA325 | Enjamul Haque | 2.33 | 2.33 | 72.24 | 1 | 72.24 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Gokul 1 | 3.59 | 3.59 | 46.62 | 1 | 46.62 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Gokul Sarkar 1 | 4.15 | 4.15 | 120.23 | 3 | 40.08 | 5 | 1 | 4-6
Mr. Arun Felbin | TA325 | Gokul Sarkar 2 | 5.66 | 5.66 | 266.18 | 4 | 66.55 | 7 | 4 | 4-6
Mr. Arun Felbin | TA325 | Gourishankar | 8.34 | 6.26 | 508.76 | 7 | 72.68 | 11 | 6 | 8-10
Mr. Arun Felbin | TA325 | Imadul Haque | 3.22 | 3.22 | 80.41 | 1 | 80.41 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Imadul Haque Enjamul Haque | 4.74 | 4.74 | 56.86 | 1 | 56.86 | 0 | 0 | 4-6
Mr. Arun Felbin | TA325 | Jaman Mahto 1 Ratna Devi | 5.12 | 5.12 | 394.41 | 4 | 98.6 | 5 | 2 | 4-6
Mr. Arun Felbin | TA325 | Javir Hossen | 2.51 | 2.51 | 80.41 | 1 | 80.41 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Javir Hossen Enjamul Haque | 6.86 | 6.86 | 75.45 | 1 | 75.45 | 0 | 0 | 6-8
Mr. Arun Felbin | TA325 | Jwala | 7.5 | 7.68 | 383.77 | 6 | 63.96 | 9 | 6 | 6-8
Mr. Arun Felbin | TA325 | Jwala Singh | 6.46 | 6.56 | 245.36 | 3 | 81.79 | 6 | 4 | 6-8
Mr. Arun Felbin | TA325 | Kamruddin | 2.01 | 2.01 | 80.41 | 1 | 80.41 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Kuduas Ali 2 | 4.26 | 4.26 | 85.23 | 1 | 85.23 | 0 | 0 | 4-6
Mr. Arun Felbin | TA325 | Maa Construction | 3.5 | 4.01 | 80.41 | 1 | 80.41 | 4 | 2 | 0-4
Mr. Arun Felbin | TA325 | Md Akhtar | 5.19 | 5.19 | 409.72 | 4 | 102.43 | 8 | 2 | 4-6
Mr. Arun Felbin | TA325 | Mithun Kumar | 1.68 | 2.25 | 529.52 | 7 | 75.65 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Mjr | 3.36 | 3.8 | 289.47 | 5 | 57.89 | 6 | 1 | 0-4
Mr. Arun Felbin | TA325 | Modina India | 1.94 | 2.38 | 322.23 | 5 | 64.45 | 3 | 2 | 0-4
Mr. Arun Felbin | TA325 | Modina India 1 4 Pgcil | 3.6 | 3.6 | 72.09 | 2 | 36.04 | 2 | 1 | 0-4
Mr. Arun Felbin | TA325 | Modina India 1 Pgcil | 2.26 | 2.26 | 101.85 | 1 | 101.85 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Modina India 2 Pgcil | 2.31 | 2.31 | 131.61 | 3 | 43.87 | 18 | 3 | 0-4
Mr. Arun Felbin | TA325 | Modina India 3 Pgcil | 3.76 | 3.76 | 157.92 | 4 | 39.48 | 14 | 4 | 0-4
Mr. Arun Felbin | TA325 | Modina India 3 Pgcil Dildar Electricals 3 Pgcil Nasirudin Md Akhtar | 3.64 | 3.64 | 123.65 | 1 | 123.65 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Muni Bibi 1 | 4.35 | 4.35 | 139.14 | 2 | 69.57 | 0 | 0 | 4-6
Mr. Arun Felbin | TA325 | Muni Bibi 1 2 | 3.97 | 3.97 | 63.51 | 1 | 63.51 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Muni Bibi 2 | 4.09 | 4.09 | 126.88 | 2 | 63.44 | 0 | 0 | 4-6
Mr. Arun Felbin | TA325 | Nan | 2.51 | 2.51 | 350.7 | 5 | 70.14 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Nasirudin | 7.46 | 7.46 | 74.63 | 1 | 74.63 | 0 | 0 | 6-8
Mr. Arun Felbin | TA325 | Nasirudin 2 | 5.33 | 5.33 | 143.92 | 2 | 71.96 | 1 | 1 | 4-6
Mr. Arun Felbin | TA325 | Pc 2 | 3.54 | 3.54 | 279.55 | 3 | 93.18 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Pc 3 Prabhat Kumar Ranjan | 4.11 | 4.11 | 82.24 | 1 | 82.24 | 0 | 0 | 4-6
Mr. Arun Felbin | TA325 | Pc Construction | 7.53 | 7.53 | 97.93 | 1 | 97.93 | 0 | 0 | 6-8
Mr. Arun Felbin | TA325 | Pc Construction 1 | 6.06 | 6.06 | 211.95 | 2 | 105.98 | 0 | 0 | 6-8
Mr. Arun Felbin | TA325 | Prayag Mahto | 3.19 | 3.57 | 223.2 | 3 | 74.4 | 16 | 2 | 0-4
Mr. Arun Felbin | TA325 | Rahim Khan | 4.76 | 3.22 | 267.91 | 6 | 44.65 | 8 | 4 | 4-6
Mr. Arun Felbin | TA325 | Rahim Khan 1 | 2.63 | 2.63 | 39.46 | 1 | 39.46 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Rahul Kumar | 6.83 | 5.35 | 615.15 | 9 | 68.35 | 20 | 10 | 6-8
Mr. Arun Felbin | TA325 | Ranjan Kumar | 2.57 | 3.2 | 36.04 | 1 | 36.04 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Rupesh | 2.01 | 2.1 | 371.25 | 4 | 92.81 | 16 | 3 | 0-4
Mr. Arun Felbin | TA325 | Sakila Khatun | 6.88 | 7.05 | 336.97 | 3 | 112.32 | 5 | 2 | 6-8
Mr. Arun Felbin | TA325 | Satish Kumar | 3.8 | 3.8 | 129.27 | 2 | 64.63 | 9 | 1 | 0-4
Mr. Arun Felbin | TA325 | Senahul | 3.43 | 2.76 | 119.97 | 2 | 59.98 | 2 | 1 | 0-4
Mr. Arun Felbin | TA325 | Senahul Modina India 3 | 0.27 | 0.27 | 37.73 | 1 | 37.73 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Senaul | 0.99 | 0.99 | 37.73 | 1 | 37.73 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Sk Samiul Dildar Electricals 1 | 4.12 | 4.12 | 98.84 | 1 | 98.84 | 0 | 0 | 4-6
Mr. Arun Felbin | TA325 | Sk Samuil | 3.82 | 3.18 | 294.8 | 7 | 42.11 | 0 | 0 | 0-4
Mr. Arun Felbin | TA325 | Subhash | 5.91 | 5.49 | 496.83 | 5 | 99.37 | 18 | 7 | 4-6
Mr. Arun Felbin | TA325 | Sukhriddin | 4.85 | 3.14 | 179.6 | 2 | 89.8 | 3 | 2 | 4-6
Mr. Arun Felbin | TA325 | Sukhrridin | 4.34 | 4.34 | 73.78 | 2 | 36.89 | 1 | 1 | 4-6
Mr. Arun Felbin | TA325 | Sukruddin | 3.97 | 3.97 | 380.67 | 4 | 95.17 | 6 | 1 | 0-4
Mr. Arun Felbin | TA325 | Sulen Sarkar | 3.63 | 3.64 | 159.81 | 4 | 39.95 | 10 | 1 | 0-4
Mr. Arun Felbin | TA325 | Teklal Mahto | 3 | 3 | 101.98 | 2 | 50.99 | 5 | 1 | 0-4
Mr. Arun Felbin | TA325 | Thanu Mahto | 4.43 | 3.48 | 84.19 | 2 | 42.09 | 0 | 0 | 4-6
Mr. Arun Felbin | TA414 | Anannya Traders | 6.14 | 6.14 | 245.41 | 6 | 40.9 | 0 | 0 | 6-8
Mr. Arun Felbin | TA414 | Anjum Construction | 2.49 | 2.49 | 156.8 | 3 | 52.27 | 3 | 1 | 0-4
Mr. Arun Felbin | TA414 | Chitra Construction | 1.94 | 1.95 | 112.48 | 2 | 56.24 | 9 | 2 | 0-4
Mr. Arun Felbin | TA414 | Crestless Wave Trading Opc | 3.5 | 3.5 | 62.95 | 1 | 62.95 | 0 | 0 | 0-4
Mr. Arun Felbin | TA414 | Dildar Electrical 1 | 1.73 | 1.73 | 45.04 | 1 | 45.04 | 0 | 0 | 0-4
Mr. Arun Felbin | TA414 | Dildar Electrical 2 | 2.68 | 2.68 | 72.46 | 1 | 72.46 | 0 | 0 | 0-4
Mr. Arun Felbin | TA414 | Dk Construction Sarvan Kumar | 7.59 | 7.59 | 204.8 | 3 | 68.27 | 0 | 0 | 6-8
Mr. Arun Felbin | TA414 | Jabir Hussian | 3.1 | 3.1 | 139.63 | 3 | 46.54 | 0 | 0 | 0-4
Mr. Arun Felbin | TA414 | M S Gauri Shankar | 0.1 | 0.1 | 37.73 | 1 | 37.73 | 0 | 0 | 0-4
Mr. Arun Felbin | TA414 | M S Israul Hoque | 5.73 | 5.73 | 80.24 | 1 | 80.24 | 0 | 0 | 4-6
Mr. Arun Felbin | TA414 | M S Mgr | 3.4 | 3.4 | 54.41 | 1 | 54.41 | 0 | 0 | 0-4
Mr. Arun Felbin | TA414 | M S Midhun | 3.56 | 3.56 | 135.29 | 2 | 67.64 | 15 | 2 | 0-4
Mr. Arun Felbin | TA414 | M S Rahul | 4.62 | 4.62 | 120.19 | 3 | 40.06 | 2 | 2 | 4-6
Mr. Arun Felbin | TA414 | M S Sakkurddin | 4.13 | 4.13 | 165.12 | 4 | 41.28 | 15 | 4 | 4-6
Mr. Arun Felbin | TA414 | Md Emdadul Hoque | 2.93 | 2.93 | 38.04 | 1 | 38.04 | 0 | 0 | 0-4
Mr. Arun Felbin | TA414 | Mithun Kumar | 3.72 | 2.25 | 159.95 | 4 | 39.99 | 0 | 0 | 0-4
Mr. Arun Felbin | TA414 | Modina India 1 | 0.51 | 0.51 | 82.46 | 2 | 41.23 | 0 | 0 | 0-4
Mr. Arun Felbin | TA414 | Modina India 2 | 2.42 | 2.42 | 79.74 | 2 | 39.87 | 0 | 0 | 0-4
Mr. Arun Felbin | TA414 | Modina India 3 | 1.9 | 1.9 | 38.04 | 1 | 38.04 | 0 | 0 | 0-4
Mr. Arun Felbin | TA414 | Nasiruddin | 7.06 | 5.96 | 98.84 | 1 | 98.84 | 15 | 2 | 6-8
Mr. Arun Felbin | TA414 | Pramod Kumar | 3.77 | 3.77 | 37.73 | 1 | 37.73 | 0 | 0 | 0-4
Mr. Arun Felbin | TA414 | Prayag Mahto | 5.36 | 3.57 | 80.41 | 1 | 80.41 | 16 | 2 | 4-6
Mr. Arun Felbin | TA414 | Rahul Kumar | 6 | 5.35 | 366.03 | 7 | 52.29 | 20 | 10 | 6-8
Mr. Arun Felbin | TA414 | Ranjan Kumar | 3.38 | 3.2 | 172.14 | 3 | 57.38 | 0 | 0 | 0-4
Mr. Arun Felbin | TA414 | Sakhila Khatun | 7.34 | 7.34 | 168.88 | 3 | 56.29 | 0 | 0 | 6-8
Mr. Arun Felbin | TA414 | Sakila Khatun | 7.29 | 7.05 | 269.72 | 4 | 67.43 | 5 | 2 | 6-8
Mr. Arun Felbin | TA414 | Sk Samirul | 2.72 | 2.72 | 38.04 | 1 | 38.04 | 0 | 0 | 0-4
Mr. Arun Felbin | TA414 | Sk Samiul Sima Khatun | 2.94 | 2.94 | 135.38 | 3 | 45.13 | 0 | 0 | 0-4
Mr. Arun Felbin | TA414 | Srvan Kumar | 5.39 | 5.39 | 37.73 | 1 | 37.73 | 0 | 0 | 4-6
Mr. Arun Felbin | TA414 | Srvan Kumar Dhirendra Kumar Verma | 11.57 | 11.57 | 34.7 | 1 | 34.7 | 0 | 0 | 10+
Mr. Arun Felbin | TA414 | Subhash | 5.28 | 5.49 | 232.19 | 5 | 46.44 | 18 | 7 | 4-6
Mr. Arun Felbin | TA414 | Subhash Kumar | 1.8 | 1.8 | 36.04 | 1 | 36.04 | 0 | 0 | 0-4
Mr. Arun Felbin | TA414 | Tafijul Sk | 3.2 | 3.2 | 92.78 | 2 | 46.39 | 0 | 0 | 0-4
Mr. Arun Felbin | TA414 | Zakir Hussain | 2.52 | 2.52 | 37.73 | 1 | 37.73 | 0 | 0 | 0-4
Mr. Arun Felbin | TA416 | Aloriva Global | 3.37 | 3.37 | 161.58 | 3 | 53.86 | 6 | 2 | 0-4
Mr. Arun Felbin | TA416 | Amar Singh | 5.3 | 5.14 | 545.93 | 11 | 49.63 | 12 | 4 | 4-6
Mr. Arun Felbin | TA416 | Amit Choudhry | 2.99 | 2.99 | 143.46 | 1 | 143.46 | 0 | 0 | 0-4
Mr. Arun Felbin | TA416 | Amit Choudhury | 3.93 | 3.93 | 416.64 | 5 | 83.33 | 0 | 0 | 0-4
Mr. Arun Felbin | TA416 | Amit Const | 4.85 | 4.85 | 145.42 | 3 | 48.47 | 1 | 1 | 4-6
Mr. Arun Felbin | TA416 | Anand Construction | 3.75 | 3.76 | 101.39 | 2 | 50.69 | 0 | 0 | 0-4
Mr. Arun Felbin | TA416 | Ananya Trader | 5.99 | 5.99 | 185.84 | 2 | 92.92 | 0 | 0 | 4-6
Mr. Arun Felbin | TA416 | Ananya Traders 1 | 6.04 | 6.03 | 990.87 | 13 | 76.22 | 12 | 6 | 6-8
Mr. Arun Felbin | TA416 | Ananya Traders 2 | 6.77 | 6.77 | 595.89 | 11 | 54.17 | 1 | 1 | 6-8
Mr. Arun Felbin | TA416 | Asc Heights | 5.5 | 5.45 | 489.8 | 8 | 61.22 | 7 | 3 | 4-6
Mr. Arun Felbin | TA416 | Devine | 3.26 | 3.26 | 42.37 | 1 | 42.37 | 0 | 0 | 0-4
Mr. Arun Felbin | TA416 | Dewi Construction Girendra | 6.96 | 6.64 | 438.43 | 9 | 48.71 | 4 | 2 | 6-8
Mr. Arun Felbin | TA416 | Gagan Enterprise 1 | 6.4 | 6.39 | 952.15 | 13 | 73.24 | 9 | 2 | 6-8
Mr. Arun Felbin | TA416 | Gagan Enterprise 2 | 5.99 | 5.99 | 281.66 | 5 | 56.33 | 5 | 2 | 4-6
Mr. Arun Felbin | TA416 | Gagan Enterprise 2 Kajol | 3.54 | 3.54 | 46.05 | 1 | 46.05 | 0 | 0 | 0-4
Mr. Arun Felbin | TA416 | Gouri Shankar | 5.34 | 5.34 | 176.33 | 2 | 88.17 | 0 | 0 | 4-6
Mr. Arun Felbin | TA416 | Horil Mahto | 3.84 | 4.32 | 46.05 | 1 | 46.05 | 16 | 4 | 0-4
Mr. Arun Felbin | TA416 | Kongres Kumar 1 | 4.56 | 4.56 | 365.08 | 3 | 121.69 | 0 | 0 | 4-6
Mr. Arun Felbin | TA416 | Kongres Kumar 2 | 3.28 | 3.28 | 170.65 | 2 | 85.33 | 0 | 0 | 0-4
Mr. Arun Felbin | TA416 | M K Infra | 2.21 | 2.45 | 176.85 | 4 | 44.21 | 8 | 1 | 0-4
Mr. Arun Felbin | TA416 | Maa Construction | 3.95 | 4.01 | 173.69 | 2 | 86.85 | 4 | 2 | 0-4
Mr. Arun Felbin | TA416 | Mahon Mahto | 4.2 | 4.2 | 625.48 | 5 | 125.1 | 0 | 0 | 4-6
Mr. Arun Felbin | TA416 | Niranjan Singh | 1.75 | 1.75 | 43.78 | 1 | 43.78 | 0 | 0 | 0-4
Mr. Arun Felbin | TA416 | Pankaj Kumar | 4.56 | 4.56 | 615.75 | 6 | 102.62 | 0 | 0 | 4-6
Mr. Arun Felbin | TA416 | Pinky Dewi | 5.74 | 6.08 | 985.96 | 17 | 58 | 8 | 3 | 4-6
Mr. Arun Felbin | TA416 | Punam Kumari | 3.64 | 3.84 | 258.63 | 4 | 64.66 | 2 | 1 | 0-4
Mr. Arun Felbin | TA416 | Punam Kumari 1 | 3.31 | 4.48 | 288.38 | 4 | 72.09 | 2 | 1 | 0-4
Mr. Arun Felbin | TA416 | Punam Kumari 2 | 3.52 | 5.33 | 204.2 | 4 | 51.05 | 2 | 1 | 0-4
Mr. Arun Felbin | TA416 | Punam Kumari 3 | 3.57 | 3.88 | 221.32 | 2 | 110.66 | 0 | 0 | 0-4
Mr. Arun Felbin | TA416 | Radha Construction | 4.09 | 4.09 | 167.79 | 2 | 83.9 | 3 | 2 | 4-6
Mr. Arun Felbin | TA416 | Reeta Bharti | 4.61 | 4.93 | 876.99 | 13 | 67.46 | 6 | 2 | 4-6
Mr. Arun Felbin | TA416 | Rudra Construction | 3.78 | 4.08 | 132.2 | 3 | 44.07 | 8 | 2 | 0-4
Mr. Arun Felbin | TA416 | Sainik Trader | 3.33 | 3.33 | 236.3 | 3 | 78.77 | 1 | 1 | 0-4
Mr. Arun Felbin | TA416 | Spotyfy | 2.05 | 2.05 | 53.32 | 1 | 53.32 | 0 | 0 | 0-4
Mr. Arun Felbin | TA416 | Spotyfy 3 | 1.12 | 1.12 | 42.37 | 1 | 42.37 | 0 | 0 | 0-4
Mr. Arun Felbin | TA418 | Gang 01 Sanjay | 4.28 | 1.63 | 291 | 8 | 36.38 | 15 | 4 | 4-6
Mr. Arun Felbin | TA418 | Gang 02 Sanjay | 4.3 | 1.55 | 503.63 | 14 | 35.97 | 14 | 6 | 4-6
Mr. Arun Felbin | TA418 | Gang 02 Sanjay Kec 02 Barkat Ali | 2.07 | 2.07 | 29 | 1 | 29 | 0 | 0 | 0-4
Mr. Arun Felbin | TA418 | Kec 01 Barkat Ali | 2.17 | 2.17 | 210.63 | 7 | 30.09 | 4 | 1 | 0-4
Mr. Arun Felbin | TA418 | Kec 02 Barkat Ali | 1.26 | 1.13 | 682.9 | 19 | 35.94 | 0 | 0 | 0-4
Mr. Arun Felbin | TA418 | M S Mdpl | 3.34 | 3.34 | 534.3 | 12 | 44.52 | 3 | 3 | 0-4
Mr. Arun Felbin | TA418 | M S Tofit | 4.48 | 4.48 | 631.3 | 15 | 42.09 | 11 | 5 | 4-6
Mr. Arun Felbin | TA418 | Savitha | 1.67 | 1.67 | 102 | 3 | 34 | 14 | 3 | 0-4
Mr. Arun Felbin | TA418 | Subhash | 5.05 | 5.49 | 303.1 | 7 | 43.3 | 18 | 7 | 4-6
Mr. Arun Felbin | TA421 | D K Verma | 5.94 | 5.94 | 956.69 | 22 | 43.49 | 17 | 6 | 4-6
Mr. Arun Felbin | TA421 | Gauri Shankar Mahto | 6.67 | 6.67 | 233.34 | 4 | 58.34 | 13 | 2 | 6-8
Mr. Arun Felbin | TA421 | Gowrishankar | 4.74 | 4.74 | 37.93 | 1 | 37.93 | 0 | 0 | 4-6
Mr. Arun Felbin | TA421 | Hassan | 4.22 | 4.22 | 890.28 | 18 | 49.46 | 9 | 4 | 4-6
Mr. Arun Felbin | TA421 | Hassan 2 | 3.81 | 3.81 | 141.08 | 3 | 47.03 | 0 | 0 | 0-4
Mr. Arun Felbin | TA421 | J Lngh O 1 | 5.86 | 5.84 | 214.73 | 5 | 42.95 | 1 | 1 | 4-6
Mr. Arun Felbin | TA421 | J Lngh O 2 | 5.12 | 3.16 | 148.6 | 4 | 37.15 | 0 | 0 | 4-6
Mr. Arun Felbin | TA421 | Jwala Singh 01 | 6.61 | 6.61 | 72.74 | 2 | 36.37 | 0 | 0 | 6-8
Mr. Arun Felbin | TA421 | Khatun | 8.49 | 7.24 | 1859.31 | 40 | 46.48 | 28 | 10 | 8-10
Mr. Arun Felbin | TA421 | Naziruddin | 4.86 | 4.86 | 461.81 | 11 | 41.98 | 0 | 0 | 4-6
Mr. Arun Felbin | TA421 | Praveen | 2.07 | 2.26 | 511.34 | 12 | 42.61 | 23 | 6 | 0-4
Mr. Arun Felbin | TA421 | Shakila Khatun | 10.38 | 10.38 | 83.03 | 2 | 41.52 | 1 | 1 | 10+
Mr. Arun Felbin | TA421 | Subash | 7.94 | 7.46 | 2460.96 | 62 | 39.69 | 5 | 3 | 6-8
Mr. Arun Felbin | TA421 | Yadhav D K Verma | 2.37 | 2.37 | 37.93 | 1 | 37.93 | 0 | 0 | 0-4
Mr. Arun Felbin | TA601 | Ali Uslam | 3.66 | 3.66 | 36.57 | 1 | 36.57 | 0 | 0 | 0-4
Mr. Arun Felbin | TA601 | Nasiruddin | 5.22 | 5.96 | 109.72 | 3 | 36.57 | 15 | 2 | 4-6
Mr. Arun Felbin | TA601 | Uma Devi | 2.44 | 2.44 | 36.57 | 1 | 36.57 | 0 | 0 | 0-4
Mr. Arun Felbin | TB501 | Dudhnath | 2.3 | 2.3 | 6.91 | 1 | 6.91 | 0 | 0 | 0-4
Mr. Arun Felbin | TB501 | Dudhnath Kumar | 2.72 | 2.51 | 234.14 | 31 | 7.55 | 44 | 12 | 0-4
Mr. Arun Felbin | TB501 | Harsh Vivek | 1.08 | 1.08 | 8.67 | 2 | 4.34 | 0 | 0 | 0-4
Mr. Arun Felbin | TB501 | Munna Singh | 2.06 | 2.06 | 12.39 | 2 | 6.19 | 4 | 1 | 0-4
Mr. Arun Felbin | TB501 | Rames Kumar M | 2.8 | 2.8 | 53.16 | 8 | 6.64 | 29 | 3 | 0-4
Mr. Arun Felbin | TB501 | Ramesh | 1.48 | 1.48 | 11.81 | 2 | 5.9 | 0 | 0 | 0-4
Mr. Arun Felbin | TB501 | Ramesh Kumar | 2.72 | 2.54 | 344.19 | 45 | 7.65 | 81 | 24 | 0-4
Mr. Arun Felbin | TB501 | Ramesh Kumar M | 2.14 | 2.14 | 25.68 | 5 | 5.14 | 6 | 3 | 0-4
Mr. Arun Felbin | TB501 | Shree Karni Entp | 2.02 | 2.02 | 6.05 | 1 | 6.05 | 0 | 0 | 0-4
Mr. Arun Felbin | TB501 | Suman | 1.32 | 1.32 | 70 | 9 | 7.78 | 8 | 2 | 0-4
Mr. Dheeraj Vashishth | TA513 | Anil Construction | 3.84 | 3.84 | 411.02 | 18 | 22.83 | 1 | 1 | 0-4
Mr. Nabajit Baruah | TA504 | Ghyansham Mahto | 3.87 | 3.87 | 565 | 9 | 62.78 | 7 | 5 | 0-4
Mr. Nabajit Baruah | TA504 | Horel Mahto | 4.69 | 4.69 | 136 | 3 | 45.33 | 3 | 1 | 4-6
Mr. Nabajit Baruah | TA504 | Karam Mahto | 2.73 | 2.73 | 259 | 6 | 43.17 | 3 | 2 | 0-4
Mr. Nabajit Baruah | TA504 | Mukhi Lal | 5.47 | 5.47 | 164 | 3 | 54.67 | 6 | 3 | 4-6
Mr. Nabajit Baruah | TA504 | Neha Const | 2.95 | 2.95 | 112 | 3 | 37.33 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA504 | Pankaj | 5.98 | 6.34 | 342 | 9 | 38 | 7 | 4 | 4-6
Mr. Nabajit Baruah | TA504 | Pankaj 2 | 5.81 | 6.37 | 471 | 12 | 39.25 | 0 | 0 | 4-6
Mr. Nabajit Baruah | TA504 | Pinki Devi | 5.39 | 4.6 | 334 | 6 | 55.67 | 4 | 1 | 4-6
Mr. Nabajit Baruah | TA504 | Punam Kumari 1 | 6.13 | 4.48 | 411 | 7 | 58.71 | 2 | 1 | 6-8
Mr. Nabajit Baruah | TA504 | Punam Kumari 2 | 7.39 | 5.33 | 170 | 3 | 56.67 | 2 | 1 | 6-8
Mr. Nabajit Baruah | TA504 | Rajesh Kumar | 3.29 | 3.29 | 92 | 2 | 46 | 1 | 1 | 0-4
Mr. Nabajit Baruah | TA504 | Sainik Traders | 3.86 | 3.91 | 648 | 14 | 46.29 | 12 | 8 | 0-4
Mr. Nabajit Baruah | TA505 | Anil Kumar | 2.71 | 2.71 | 100.38 | 2 | 50.19 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA505 | Anil Kumar Rudra Const | 2 | 2 | 37.93 | 1 | 37.93 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA505 | Crane Erc Team Mp | 2.87 | 2.87 | 405.03 | 10 | 40.5 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA505 | Deglal Mahato | 6.37 | 6.37 | 1070.42 | 18 | 59.47 | 0 | 0 | 6-8
Mr. Nabajit Baruah | TA505 | Deglal Mahato Mp | 4.73 | 4.73 | 705.06 | 18 | 39.17 | 0 | 0 | 4-6
Mr. Nabajit Baruah | TA505 | Eagle Enterprises | 3.48 | 3.83 | 34.79 | 1 | 34.79 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA505 | Eagle Enterprises Paramand | 3.31 | 3.31 | 308.08 | 8 | 38.51 | 2 | 1 | 0-4
Mr. Nabajit Baruah | TA505 | Gokul Rajwanshi | 5.03 | 4.61 | 905.33 | 22 | 41.15 | 6 | 4 | 4-6
Mr. Nabajit Baruah | TA505 | Gokul Sarkar Mp | 4.77 | 4.77 | 391.06 | 9 | 43.45 | 2 | 2 | 4-6
Mr. Nabajit Baruah | TA505 | Gokul Sarkar Mp 2 | 4.37 | 4.37 | 275.49 | 7 | 39.36 | 0 | 0 | 4-6
Mr. Nabajit Baruah | TA505 | Jagannaath Saw Mp | 4.82 | 4.82 | 694.61 | 16 | 43.41 | 0 | 0 | 4-6
Mr. Nabajit Baruah | TA505 | Jhemon Mahato 1 | 5.97 | 5.97 | 483.28 | 7 | 69.04 | 0 | 0 | 4-6
Mr. Nabajit Baruah | TA505 | Jhemon Mahato 2 | 3.61 | 3.61 | 444.32 | 9 | 49.37 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA505 | Jwala Singh | 6.81 | 6.56 | 2038.22 | 42 | 48.53 | 6 | 4 | 6-8
Mr. Nabajit Baruah | TA505 | Jwala Singh 2 | 6.23 | 5.81 | 837.91 | 21 | 39.9 | 28 | 7 | 6-8
Mr. Nabajit Baruah | TA505 | Jyoti Const | 4.04 | 4.04 | 671.2 | 12 | 55.93 | 0 | 0 | 4-6
Mr. Nabajit Baruah | TA505 | Pankaj Singh Mp | 5.36 | 5.36 | 519.88 | 13 | 39.99 | 0 | 0 | 4-6
Mr. Nabajit Baruah | TA505 | Paramanand | 2.13 | 2.13 | 36.16 | 1 | 36.16 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA505 | Paramanand 1 | 1.82 | 1.82 | 357.37 | 9 | 39.71 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA505 | Paramanand 2 | 1.58 | 1.58 | 74.09 | 2 | 37.05 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA505 | Prayag Shah Mp | 3.49 | 3.49 | 338.68 | 8 | 42.34 | 2 | 2 | 0-4
Mr. Nabajit Baruah | TA505 | Shila Devi | 5.97 | 5.97 | 966.64 | 16 | 60.41 | 1 | 1 | 4-6
Mr. Nabajit Baruah | TA505 | Toshan Mahato | 3.71 | 3.71 | 582.83 | 9 | 64.76 | 1 | 1 | 0-4
Mr. Nabajit Baruah | TA506 | A B Const Birendra Panday | 3.4 | 3.4 | 17 | 1 | 17 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA506 | Ab Const | 4.07 | 4.07 | 277 | 10 | 27.7 | 46 | 6 | 4-6
Mr. Nabajit Baruah | TA506 | Ab Const 2 | 3.6 | 3.6 | 18 | 1 | 18 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA506 | Ab Construction | 3.71 | 3.71 | 89 | 4 | 22.25 | 1 | 1 | 0-4
Mr. Nabajit Baruah | TA506 | Akash Prabha | 4.4 | 4.4 | 22 | 1 | 22 | 0 | 0 | 4-6
Mr. Nabajit Baruah | TA506 | Alo Reeva | 3.2 | 3.2 | 16 | 1 | 16 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA506 | Binod Mahto | 4.29 | 4.29 | 313 | 10 | 31.3 | 31 | 8 | 4-6
Mr. Nabajit Baruah | TA506 | Fatima | 4.2 | 4.2 | 21 | 1 | 21 | 0 | 0 | 4-6
Mr. Nabajit Baruah | TA506 | Fatima 1 | 4.5 | 4.5 | 27 | 1 | 27 | 0 | 0 | 4-6
Mr. Nabajit Baruah | TA506 | Govind Mahto | 3.98 | 3.98 | 418 | 17 | 24.59 | 29 | 11 | 0-4
Mr. Nabajit Baruah | TA506 | Gulab Mahto | 4.83 | 4.83 | 169 | 9 | 18.78 | 0 | 0 | 4-6
Mr. Nabajit Baruah | TA506 | Horil | 5.3 | 5.3 | 122 | 5 | 24.4 | 0 | 0 | 4-6
Mr. Nabajit Baruah | TA506 | Horil Mahto | 4.8 | 4.32 | 509 | 19 | 26.79 | 16 | 4 | 4-6
Mr. Nabajit Baruah | TA506 | Jai Prakash Mahto | 4.72 | 4.72 | 458 | 16 | 28.62 | 23 | 7 | 4-6
Mr. Nabajit Baruah | TA506 | Jay Prakash | 4.76 | 4.76 | 100 | 3 | 33.33 | 2 | 1 | 4-6
Mr. Nabajit Baruah | TA506 | Karni Const 1 | 3.86 | 3.86 | 266 | 12 | 22.17 | 26 | 5 | 0-4
Mr. Nabajit Baruah | TA506 | Karni Const 2 | 4.73 | 4.73 | 369 | 13 | 28.38 | 28 | 9 | 4-6
Mr. Nabajit Baruah | TA506 | Karni Const 3 | 4.67 | 4.67 | 322 | 12 | 26.83 | 17 | 7 | 4-6
Mr. Nabajit Baruah | TA506 | Karni Const 4 | 4.7 | 4.7 | 324 | 11 | 29.45 | 15 | 6 | 4-6
Mr. Nabajit Baruah | TA506 | Karni Const 5 | 3.86 | 3.86 | 220 | 8 | 27.5 | 21 | 3 | 0-4
Mr. Nabajit Baruah | TA506 | Karni Const 6 | 4.17 | 4.17 | 121 | 6 | 20.17 | 2 | 1 | 4-6
Mr. Nabajit Baruah | TA506 | Khemlal | 4.56 | 4.56 | 82 | 4 | 20.5 | 0 | 0 | 4-6
Mr. Nabajit Baruah | TA506 | Khemlal Mahto | 4.31 | 4.31 | 418 | 17 | 24.59 | 40 | 10 | 4-6
Mr. Nabajit Baruah | TA506 | Mohan Mahto | 3.91 | 3.91 | 125 | 4 | 31.25 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA506 | Mukkhilal | 3 | 3 | 27 | 1 | 27 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA506 | Mukkhilal 2 | 4 | 4 | 16 | 1 | 16 | 0 | 0 | 4-6
Mr. Nabajit Baruah | TA506 | Pankaj | 4.28 | 6.34 | 248 | 10 | 24.8 | 7 | 4 | 4-6
Mr. Nabajit Baruah | TA506 | Pankaj 1 | 3.69 | 3.69 | 118 | 4 | 29.5 | 2 | 1 | 0-4
Mr. Nabajit Baruah | TA506 | Pankaj 2 | 2.83 | 6.37 | 68 | 2 | 34 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA506 | Pankaj Const | 3.89 | 3.89 | 105 | 4 | 26.25 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA506 | Pappu Kumar | 2.1 | 2.1 | 21 | 1 | 21 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA506 | Prem Kumar | 4.45 | 4.45 | 294 | 8 | 36.75 | 34 | 9 | 4-6
Mr. Nabajit Baruah | TA506 | Radhika Enterprises | 3.86 | 3.86 | 27 | 1 | 27 | 0 | 0 | 0-4
Mr. Nabajit Baruah | TA506 | Sainik Traders | 4.67 | 3.91 | 56 | 2 | 28 | 12 | 8 | 4-6
Mr. Nabajit Baruah | TA506 | Shradha | 7.4 | 7.4 | 37 | 1 | 37 | 0 | 0 | 6-8
Mr. Nabajit Baruah | TA506 | Shri Karni Construction | 4.1 | 4.1 | 725 | 33 | 21.97 | 0 | 0 | 4-6
Mr. Nabajit Baruah | TA506 | Tejal | 3.19 | 3.19 | 83 | 4 | 20.75 | 9 | 2 | 0-4
Mr. Nabajit Baruah | TA506 | Tejal Const | 4 | 4 | 48 | 2 | 24 | 4 | 1 | 4-6
Mr. Nabajit Baruah | TA506 | Tejal Mahto | 5.81 | 5.81 | 122 | 4 | 30.5 | 18 | 3 | 4-6
Mr. Nabajit Baruah | TA506 | Vinod | 3.59 | 3.59 | 61 | 2 | 30.5 | 2 | 1 | 0-4
Mr. Nabajit Baruah | TA506 | Vishal Const | 5.33 | 5.33 | 16 | 1 | 16 | 0 | 0 | 4-6
Mr. Nabajit Baruah | TA506 | Zainab Fatima | 6.8 | 6.8 | 34 | 1 | 34 | 0 | 0 | 6-8

## Idle Intervals
Scope: 2025-04-01 to 2026-02-28 ¦ Projects: 17 ¦ Erections: 2584 ¦ Gangs: 429
Gang | Interval Start | Interval End | Raw Gap (days) | Idle Counted (days)
Aamir Khan | 26-11-2025 | 27-11-2025 | 2 | 2
Ab Const | 04-10-2025 | 18-10-2025 | 15 | 15
Ab Const | 01-11-2025 | 04-11-2025 | 4 | 4
Ab Const | 14-11-2025 | 15-11-2025 | 2 | 2
Ab Const | 20-11-2025 | 24-11-2025 | 5 | 5
Ab Const | 01-12-2025 | 05-12-2025 | 5 | 5
Ab Const | 12-12-2025 | 26-12-2025 | 15 | 15
Ab Construction | 19-01-2026 | 19-01-2026 | 1 | 1
Ahmed Construction | 16-09-2025 | 18-09-2025 | 3 | 3
Ajay Kumar 2 | 22-09-2025 | 22-09-2025 | 1 | 1
Aloriva Global | 14-11-2025 | 14-11-2025 | 1 | 1
Aloriva Global | 01-12-2025 | 05-12-2025 | 5 | 5
Amar Kumar Singh | 21-09-2025 | 23-09-2025 | 3 | 3
Amar Singh | 06-05-2025 | 06-05-2025 | 1 | 1
Amar Singh | 01-06-2025 | 01-06-2025 | 1 | 1
Amar Singh | 11-06-2025 | 11-06-2025 | 1 | 1
Amar Singh | 19-06-2025 | 27-06-2025 | 9 | 9
Amit Const | 19-06-2025 | 19-06-2025 | 1 | 1
Amit Kumar Singh | 06-08-2025 | 06-08-2025 | 1 | 1
Ananya Traders 1 | 27-04-2025 | 28-04-2025 | 2 | 2
Ananya Traders 1 | 25-05-2025 | 27-05-2025 | 3 | 3
Ananya Traders 1 | 03-06-2025 | 03-06-2025 | 1 | 1
Ananya Traders 1 | 01-07-2025 | 04-07-2025 | 4 | 4
Ananya Traders 1 | 19-07-2025 | 19-07-2025 | 1 | 1
Ananya Traders 1 | 09-08-2025 | 09-08-2025 | 1 | 1
Ananya Traders 2 | 14-06-2025 | 14-06-2025 | 1 | 1
Anarul Haque | 12-04-2025 | 13-04-2025 | 2 | 2
Anil Construction | 02-12-2025 | 02-12-2025 | 1 | 1
Anita Devi | 18-10-2025 | 18-10-2025 | 1 | 1
Anita Devi | 02-11-2025 | 04-11-2025 | 3 | 3
Anjum Construction | 26-12-2025 | 28-12-2025 | 3 | 3
Arawali Infra 2 | 07-07-2025 | 07-07-2025 | 1 | 1
Arawali Infra 2 | 17-07-2025 | 17-07-2025 | 1 | 1
Arawali Infra 2 | 25-07-2025 | 31-07-2025 | 7 | 7
Arawali Infra 2 | 01-08-2025 | 03-08-2025 | 3 | 3
Asc Heights | 29-04-2025 | 29-04-2025 | 1 | 1
Asc Heights | 21-05-2025 | 24-05-2025 | 4 | 4
Asc Heights | 22-06-2025 | 23-06-2025 | 2 | 2
Barkat Ali | 12-05-2025 | 15-05-2025 | 4 | 4
Bhairaw Mahto | 05-10-2025 | 11-10-2025 | 7 | 7
Bhairo Mahto | 01-09-2025 | 01-09-2025 | 1 | 1
Bhairo Mahto | 11-09-2025 | 11-09-2025 | 1 | 1
Bhoi Enterprises | 17-12-2025 | 18-12-2025 | 2 | 2
Binod Mahto | 04-11-2025 | 09-11-2025 | 6 | 6
Binod Mahto | 18-11-2025 | 21-11-2025 | 4 | 4
Binod Mahto | 28-11-2025 | 30-11-2025 | 3 | 3
Binod Mahto | 01-12-2025 | 03-12-2025 | 3 | 3
Binod Mahto | 31-12-2025 | 31-12-2025 | 1 | 1
Binod Mahto | 01-01-2026 | 08-01-2026 | 8 | 8
Binod Mahto | 17-01-2026 | 20-01-2026 | 4 | 4
Binod Mahto | 28-01-2026 | 29-01-2026 | 2 | 2
Chinta Devi | 05-04-2025 | 05-04-2025 | 1 | 1
Chinta Devi | 08-09-2025 | 08-09-2025 | 1 | 1
Chinta Devi | 26-09-2025 | 28-09-2025 | 3 | 3
Chinta Devi | 01-12-2025 | 02-12-2025 | 2 | 2
Chinta Devi | 19-01-2026 | 21-01-2026 | 3 | 3
Chitra Construction | 25-11-2025 | 30-11-2025 | 6 | 6
Chitra Construction | 01-12-2025 | 03-12-2025 | 3 | 3
D K Verma | 15-08-2025 | 15-08-2025 | 1 | 1
D K Verma | 11-09-2025 | 12-09-2025 | 2 | 2
D K Verma | 01-10-2025 | 06-10-2025 | 6 | 6
D K Verma | 03-11-2025 | 03-11-2025 | 1 | 1
D K Verma | 30-11-2025 | 30-11-2025 | 1 | 1
D K Verma | 21-12-2025 | 26-12-2025 | 6 | 6
Daulat Mahto | 13-04-2025 | 21-04-2025 | 9 | 9
Devi Construction | 29-11-2025 | 30-11-2025 | 2 | 2
Devi Construction | 01-12-2025 | 01-12-2025 | 1 | 1
Devi Construction | 23-12-2025 | 24-12-2025 | 2 | 2
Dewi Construction Girendra | 11-04-2025 | 11-04-2025 | 1 | 1
Dewi Construction Girendra | 04-05-2025 | 06-05-2025 | 3 | 3
Dhaneswar Mahto | 12-04-2025 | 17-04-2025 | 6 | 6
Dhaneswar Mahto | 07-05-2025 | 12-05-2025 | 6 | 6
Dildar Electricals 1 Pgcil | 25-10-2025 | 31-10-2025 | 7 | 7
Dildar Electricals 1 Pgcil | 01-11-2025 | 05-11-2025 | 5 | 5
Dipak | 06-07-2025 | 06-07-2025 | 1 | 1
Dipak | 22-09-2025 | 23-09-2025 | 2 | 2
Dipak | 11-11-2025 | 12-11-2025 | 2 | 2
Dipak | 21-11-2025 | 21-11-2025 | 1 | 1
Dk Verma | 02-04-2025 | 05-04-2025 | 4 | 4
Dk Verma | 19-05-2025 | 23-05-2025 | 5 | 5
Dudhnath Kumar | 11-04-2025 | 11-04-2025 | 1 | 1
Dudhnath Kumar | 14-04-2025 | 14-04-2025 | 1 | 1
Dudhnath Kumar | 18-04-2025 | 19-04-2025 | 2 | 2
Dudhnath Kumar | 24-04-2025 | 27-04-2025 | 4 | 4
Dudhnath Kumar | 28-05-2025 | 31-05-2025 | 4 | 4
Dudhnath Kumar | 01-06-2025 | 03-06-2025 | 3 | 3
Dudhnath Kumar | 12-06-2025 | 12-06-2025 | 1 | 1
Dudhnath Kumar | 30-06-2025 | 30-06-2025 | 1 | 1
Dudhnath Kumar | 09-07-2025 | 13-07-2025 | 5 | 5
Dudhnath Kumar | 17-07-2025 | 23-07-2025 | 7 | 7
Dudhnath Kumar | 27-07-2025 | 31-07-2025 | 5 | 5
Dudhnath Kumar | 01-08-2025 | 10-08-2025 | 10 | 10
Dular Chand Patel | 01-12-2025 | 03-12-2025 | 3 | 3
Eagle Enterprises Paramand | 24-06-2025 | 25-06-2025 | 2 | 2
Fouzi Ratto | 12-09-2025 | 13-09-2025 | 2 | 2
Gagan Enterprise 1 | 10-05-2025 | 10-05-2025 | 1 | 1
Gagan Enterprise 1 | 01-07-2025 | 08-07-2025 | 8 | 8
Gagan Enterprise 2 | 29-04-2025 | 30-04-2025 | 2 | 2
Gagan Enterprise 2 | 01-05-2025 | 03-05-2025 | 3 | 3
Ganesh 1 | 05-01-2026 | 07-01-2026 | 3 | 3
Ganesh 2 | 15-01-2026 | 18-01-2026 | 4 | 4
Ganesh Sinha | 28-09-2025 | 28-09-2025 | 1 | 1
Ganesh Sinha | 01-12-2025 | 12-12-2025 | 12 | 12
Ganesh Sinha | 20-12-2025 | 20-12-2025 | 1 | 1
Gang 01 Sanjay | 08-05-2025 | 10-05-2025 | 3 | 3
Gang 01 Sanjay | 20-05-2025 | 21-05-2025 | 2 | 2
Gang 01 Sanjay | 03-06-2025 | 11-06-2025 | 9 | 9
Gang 01 Sanjay | 18-06-2025 | 18-06-2025 | 1 | 1
Gang 02 Sanjay | 11-04-2025 | 11-04-2025 | 1 | 1
Gang 02 Sanjay | 04-05-2025 | 04-05-2025 | 1 | 1
Gang 02 Sanjay | 27-05-2025 | 29-05-2025 | 3 | 3
Gang 02 Sanjay | 13-06-2025 | 13-06-2025 | 1 | 1
Gang 02 Sanjay | 25-06-2025 | 30-06-2025 | 6 | 6
Gang 02 Sanjay | 01-07-2025 | 02-07-2025 | 2 | 2
Gauri Shankar Mahto | 11-12-2025 | 12-12-2025 | 2 | 2
Gauri Shankar Mahto | 19-12-2025 | 29-12-2025 | 11 | 11
Ghyansham Mahto | 17-10-2025 | 17-10-2025 | 1 | 1
Ghyansham Mahto | 18-11-2025 | 18-11-2025 | 1 | 1
Ghyansham Mahto | 02-12-2025 | 02-12-2025 | 1 | 1
Ghyansham Mahto | 15-12-2025 | 15-12-2025 | 1 | 1
Ghyansham Mahto | 01-01-2026 | 03-01-2026 | 3 | 3
Gokul Rajwanshi | 01-05-2025 | 01-05-2025 | 1 | 1
Gokul Rajwanshi | 23-06-2025 | 23-06-2025 | 1 | 1
Gokul Rajwanshi | 01-08-2025 | 03-08-2025 | 3 | 3
Gokul Rajwanshi | 17-09-2025 | 17-09-2025 | 1 | 1
Gokul Sarkar | 05-01-2026 | 06-01-2026 | 2 | 2
Gokul Sarkar 1 | 14-11-2025 | 18-11-2025 | 5 | 5
Gokul Sarkar 2 | 17-10-2025 | 17-10-2025 | 1 | 1
Gokul Sarkar 2 | 30-10-2025 | 31-10-2025 | 2 | 2
Gokul Sarkar 2 | 01-11-2025 | 02-11-2025 | 2 | 2
Gokul Sarkar 2 | 18-11-2025 | 19-11-2025 | 2 | 2
Gokul Sarkar Mp | 20-12-2025 | 20-12-2025 | 1 | 1
Gokul Sarkar Mp | 01-01-2026 | 01-01-2026 | 1 | 1
Gourishankar | 14-04-2025 | 15-04-2025 | 2 | 2
Gourishankar | 23-04-2025 | 23-04-2025 | 1 | 1
Gourishankar | 04-05-2025 | 05-05-2025 | 2 | 2
Gourishankar | 25-05-2025 | 27-05-2025 | 3 | 3
Gourishankar | 09-07-2025 | 09-07-2025 | 1 | 1
Gourishankar | 01-08-2025 | 02-08-2025 | 2 | 2
Govind Mahto | 13-09-2025 | 15-09-2025 | 3 | 3
Govind Mahto | 22-09-2025 | 23-09-2025 | 2 | 2
Govind Mahto | 11-10-2025 | 12-10-2025 | 2 | 2
Govind Mahto | 18-10-2025 | 18-10-2025 | 1 | 1
Govind Mahto | 23-10-2025 | 28-10-2025 | 6 | 6
Govind Mahto | 04-11-2025 | 05-11-2025 | 2 | 2
Govind Mahto | 12-11-2025 | 18-11-2025 | 7 | 7
Govind Mahto | 24-11-2025 | 25-11-2025 | 2 | 2
Govind Mahto | 02-12-2025 | 02-12-2025 | 1 | 1
Govind Mahto | 15-12-2025 | 15-12-2025 | 1 | 1
Govind Mahto | 21-01-2026 | 22-01-2026 | 2 | 2
Govind Mahto 1 | 17-09-2025 | 17-09-2025 | 1 | 1
Govind Mahto 1 | 08-10-2025 | 08-10-2025 | 1 | 1
Govind Mahto 1 | 28-11-2025 | 30-11-2025 | 3 | 3
Govind Mahto 1 | 01-12-2025 | 06-12-2025 | 6 | 6
Govind Mahto 2 | 01-10-2025 | 04-10-2025 | 4 | 4
Hassan | 14-09-2025 | 15-09-2025 | 2 | 2
Hassan | 26-09-2025 | 26-09-2025 | 1 | 1
Hassan | 20-10-2025 | 20-10-2025 | 1 | 1
Hassan | 03-11-2025 | 07-11-2025 | 5 | 5
Horel Mahto | 15-12-2025 | 17-12-2025 | 3 | 3
Horil Mahto | 25-10-2025 | 28-10-2025 | 4 | 4
Horil Mahto | 26-11-2025 | 29-11-2025 | 4 | 4
Horil Mahto | 19-01-2026 | 24-01-2026 | 6 | 6
Horil Mahto | 01-02-2026 | 02-02-2026 | 2 | 2
Infinidea 2 | 26-11-2025 | 30-11-2025 | 5 | 5
J Lngh O 1 | 01-05-2025 | 01-05-2025 | 1 | 1
Jai Prakash Mahto | 17-10-2025 | 19-10-2025 | 3 | 3
Jai Prakash Mahto | 10-11-2025 | 12-11-2025 | 3 | 3
Jai Prakash Mahto | 23-11-2025 | 23-11-2025 | 1 | 1
Jai Prakash Mahto | 28-11-2025 | 29-11-2025 | 2 | 2
Jai Prakash Mahto | 01-01-2026 | 03-01-2026 | 3 | 3
Jai Prakash Mahto | 10-01-2026 | 12-01-2026 | 3 | 3
Jai Prakash Mahto | 19-01-2026 | 26-01-2026 | 8 | 8
Jaman Mahto 1 Ratna Devi | 16-10-2025 | 18-10-2025 | 3 | 3
Jaman Mahto 1 Ratna Devi | 16-11-2025 | 17-11-2025 | 2 | 2
Jay Prakash | 18-09-2025 | 19-09-2025 | 2 | 2
Jirwa Devi | 31-08-2025 | 31-08-2025 | 1 | 1
Jirwa Devi | 06-11-2025 | 07-11-2025 | 2 | 2
Jirwa Devi | 13-12-2025 | 15-12-2025 | 3 | 3
Jirwa Devi | 21-12-2025 | 28-12-2025 | 8 | 8
Jwala | 02-04-2025 | 03-04-2025 | 2 | 2
Jwala | 10-04-2025 | 10-04-2025 | 1 | 1
Jwala | 17-04-2025 | 17-04-2025 | 1 | 1
Jwala | 30-04-2025 | 30-04-2025 | 1 | 1
Jwala | 01-05-2025 | 01-05-2025 | 1 | 1
Jwala | 12-05-2025 | 14-05-2025 | 3 | 3
Jwala Singh | 12-05-2025 | 13-05-2025 | 2 | 2
Jwala Singh | 26-06-2025 | 26-06-2025 | 1 | 1
Jwala Singh | 29-07-2025 | 29-07-2025 | 1 | 1
Jwala Singh | 29-09-2025 | 30-09-2025 | 2 | 2
Jwala Singh 1 | 16-06-2025 | 22-06-2025 | 7 | 7
Jwala Singh 1 | 08-11-2025 | 09-11-2025 | 2 | 2
Jwala Singh 1 | 07-12-2025 | 11-12-2025 | 5 | 5
Jwala Singh 1 | 04-01-2026 | 04-01-2026 | 1 | 1
Jwala Singh 2 | 19-06-2025 | 21-06-2025 | 3 | 3
Jwala Singh 2 | 29-06-2025 | 29-06-2025 | 1 | 1
Jwala Singh 2 | 04-07-2025 | 05-07-2025 | 2 | 2
Jwala Singh 2 | 20-07-2025 | 31-07-2025 | 12 | 12
Jwala Singh 2 | 10-08-2025 | 12-08-2025 | 3 | 3
Jwala Singh 2 | 01-10-2025 | 06-10-2025 | 6 | 6
Jwala Singh 2 | 20-12-2025 | 20-12-2025 | 1 | 1
Jwala Singh 3 | 28-06-2025 | 30-06-2025 | 3 | 3
Jwala Singh 3 | 01-07-2025 | 01-07-2025 | 1 | 1
Jwala Singh 3 | 07-07-2025 | 10-07-2025 | 4 | 4
Kamlesh Kumar | 01-12-2025 | 02-12-2025 | 2 | 2
Karam Mahto | 03-11-2025 | 03-11-2025 | 1 | 1
Karam Mahto | 12-11-2025 | 13-11-2025 | 2 | 2
Karni Const 1 | 08-10-2025 | 09-10-2025 | 2 | 2
Karni Const 1 | 17-10-2025 | 31-10-2025 | 15 | 15
Karni Const 1 | 05-11-2025 | 07-11-2025 | 3 | 3
Karni Const 1 | 12-11-2025 | 13-11-2025 | 2 | 2
Karni Const 1 | 24-11-2025 | 27-11-2025 | 4 | 4
Karni Const 2 | 08-10-2025 | 11-10-2025 | 4 | 4
Karni Const 2 | 18-10-2025 | 19-10-2025 | 2 | 2
Karni Const 2 | 02-11-2025 | 02-11-2025 | 1 | 1
Karni Const 2 | 11-11-2025 | 15-11-2025 | 5 | 5
Karni Const 2 | 20-11-2025 | 24-11-2025 | 5 | 5
Karni Const 2 | 02-12-2025 | 04-12-2025 | 3 | 3
Karni Const 2 | 10-12-2025 | 10-12-2025 | 1 | 1
Karni Const 2 | 23-12-2025 | 25-12-2025 | 3 | 3
Karni Const 2 | 01-01-2026 | 04-01-2026 | 4 | 4
Karni Const 3 | 03-10-2025 | 04-10-2025 | 2 | 2
Karni Const 3 | 22-10-2025 | 25-10-2025 | 4 | 4
Karni Const 3 | 01-11-2025 | 03-11-2025 | 3 | 3
Karni Const 3 | 09-11-2025 | 09-11-2025 | 1 | 1
Karni Const 3 | 14-11-2025 | 17-11-2025 | 4 | 4
Karni Const 3 | 24-11-2025 | 25-11-2025 | 2 | 2
Karni Const 3 | 30-11-2025 | 30-11-2025 | 1 | 1
Karni Const 4 | 16-10-2025 | 17-10-2025 | 2 | 2
Karni Const 4 | 25-10-2025 | 29-10-2025 | 5 | 5
Karni Const 4 | 02-11-2025 | 04-11-2025 | 3 | 3
Karni Const 4 | 13-11-2025 | 14-11-2025 | 2 | 2
Karni Const 4 | 19-11-2025 | 20-11-2025 | 2 | 2
Karni Const 4 | 07-12-2025 | 07-12-2025 | 1 | 1
Karni Const 5 | 02-10-2025 | 09-10-2025 | 8 | 8
Karni Const 5 | 02-11-2025 | 06-11-2025 | 5 | 5
Karni Const 5 | 14-11-2025 | 21-11-2025 | 8 | 8
Karni Const 6 | 23-11-2025 | 24-11-2025 | 2 | 2
Kec 01 Barkat Ali | 27-08-2025 | 30-08-2025 | 4 | 4
Khatun | 09-05-2025 | 09-05-2025 | 1 | 1
Khatun | 31-08-2025 | 31-08-2025 | 1 | 1
Khatun | 01-09-2025 | 08-09-2025 | 8 | 8
Khatun | 17-09-2025 | 20-09-2025 | 4 | 4
Khatun | 05-10-2025 | 06-10-2025 | 2 | 2
Khatun | 03-11-2025 | 03-11-2025 | 1 | 1
Khatun | 24-11-2025 | 26-11-2025 | 3 | 3
Khatun | 04-12-2025 | 04-12-2025 | 1 | 1
Khatun | 22-12-2025 | 26-12-2025 | 5 | 5
Khatun | 01-01-2026 | 02-01-2026 | 2 | 2
Khemlal Mahto | 11-10-2025 | 16-10-2025 | 6 | 6
Khemlal Mahto | 23-10-2025 | 31-10-2025 | 9 | 9
Khemlal Mahto | 01-11-2025 | 01-11-2025 | 1 | 1
Khemlal Mahto | 16-11-2025 | 17-11-2025 | 2 | 2
Khemlal Mahto | 26-11-2025 | 28-11-2025 | 3 | 3
Khemlal Mahto | 06-12-2025 | 07-12-2025 | 2 | 2
Khemlal Mahto | 14-12-2025 | 22-12-2025 | 9 | 9
Khemlal Mahto | 10-01-2026 | 14-01-2026 | 5 | 5
Khemlal Mahto | 19-01-2026 | 19-01-2026 | 1 | 1
Khemlal Mahto | 25-01-2026 | 26-01-2026 | 2 | 2
Laxmi | 30-11-2025 | 30-11-2025 | 1 | 1
Laxmi | 01-12-2025 | 01-12-2025 | 1 | 1
M K Infra | 02-06-2025 | 09-06-2025 | 8 | 8
M S Company Gang | 19-11-2025 | 19-11-2025 | 1 | 1
M S Govind Mahto 2 | 28-01-2026 | 28-01-2026 | 1 | 1
M S Jwala Singh | 30-11-2025 | 30-11-2025 | 1 | 1
M S Jwala Singh | 13-12-2025 | 13-12-2025 | 1 | 1
M S Jwala Singh | 19-12-2025 | 19-12-2025 | 1 | 1
M S Jwala Singh | 14-01-2026 | 14-01-2026 | 1 | 1
M S Jwala Singh | 21-01-2026 | 21-01-2026 | 1 | 1
M S Jwala Singh | 28-01-2026 | 28-01-2026 | 1 | 1
M S Jwala Singh 2 | 08-01-2026 | 15-01-2026 | 8 | 8
M S Jwala Singh 2 | 03-02-2026 | 03-02-2026 | 1 | 1
M S Karni Construction 2 | 17-01-2026 | 17-01-2026 | 1 | 1
M S Kavya Enterprises | 19-10-2025 | 26-10-2025 | 8 | 8
M S Kavya Enterprises | 15-11-2025 | 15-11-2025 | 1 | 1
M S Kavya Enterprises | 30-11-2025 | 30-11-2025 | 1 | 1
M S Kavya Enterprises | 01-12-2025 | 05-12-2025 | 5 | 5
M S Mdpl | 30-11-2025 | 30-11-2025 | 1 | 1
M S Mdpl | 16-12-2025 | 16-12-2025 | 1 | 1
M S Mdpl | 19-01-2026 | 19-01-2026 | 1 | 1
M S Midhun | 31-08-2025 | 31-08-2025 | 1 | 1
M S Midhun | 01-09-2025 | 14-09-2025 | 14 | 14
M S Punam Kumari 3 | 23-12-2025 | 23-12-2025 | 1 | 1
M S Punam Kumari 3 | 10-01-2026 | 10-01-2026 | 1 | 1
M S Punam Kumari 3 | 21-01-2026 | 21-01-2026 | 1 | 1
M S Punam Kumari 4 | 09-12-2025 | 10-12-2025 | 2 | 2
M S Punam Kumari 4 | 18-12-2025 | 20-12-2025 | 3 | 3
M S Rahul | 08-06-2025 | 08-06-2025 | 1 | 1
M S Rahul | 15-06-2025 | 15-06-2025 | 1 | 1
M S Sakkurddin | 06-08-2025 | 06-08-2025 | 1 | 1
M S Sakkurddin | 15-08-2025 | 18-08-2025 | 4 | 4
M S Sakkurddin | 29-08-2025 | 31-08-2025 | 3 | 3
M S Sakkurddin | 01-09-2025 | 07-09-2025 | 7 | 7
M S Shobha Debi | 20-01-2026 | 21-01-2026 | 2 | 2
M S Tofit | 01-10-2025 | 03-10-2025 | 3 | 3
M S Tofit | 08-11-2025 | 10-11-2025 | 3 | 3
M S Tofit | 19-11-2025 | 20-11-2025 | 2 | 2
M S Tofit | 28-11-2025 | 29-11-2025 | 2 | 2
M S Tofit | 21-01-2026 | 21-01-2026 | 1 | 1
Maa Construction | 29-09-2025 | 30-09-2025 | 2 | 2
Maa Construction | 01-10-2025 | 02-10-2025 | 2 | 2
Madhu Sah | 25-07-2025 | 25-07-2025 | 1 | 1
Madhu Sah | 18-01-2026 | 21-01-2026 | 4 | 4
Md Akhtar | 09-10-2025 | 11-10-2025 | 3 | 3
Md Akhtar | 12-11-2025 | 16-11-2025 | 5 | 5
Mjr | 07-04-2025 | 12-04-2025 | 6 | 6
Modina India | 09-04-2025 | 10-04-2025 | 2 | 2
Modina India | 23-04-2025 | 23-04-2025 | 1 | 1
Modina India 1 4 Pgcil | 15-10-2025 | 16-10-2025 | 2 | 2
Modina India 2 Pgcil | 24-10-2025 | 31-10-2025 | 8 | 8
Modina India 2 Pgcil | 01-11-2025 | 05-11-2025 | 5 | 5
Modina India 2 Pgcil | 19-11-2025 | 23-11-2025 | 5 | 5
Modina India 3 Pgcil | 16-10-2025 | 16-10-2025 | 1 | 1
Modina India 3 Pgcil | 26-10-2025 | 31-10-2025 | 6 | 6
Modina India 3 Pgcil | 01-11-2025 | 01-11-2025 | 1 | 1
Modina India 3 Pgcil | 15-11-2025 | 20-11-2025 | 6 | 6
Mukhi Lal | 12-01-2026 | 12-01-2026 | 1 | 1
Mukhi Lal | 30-01-2026 | 31-01-2026 | 2 | 2
Mukhi Lal | 01-02-2026 | 03-02-2026 | 3 | 3
Munna Singh | 26-04-2025 | 29-04-2025 | 4 | 4
Nasiruddin | 21-12-2025 | 21-12-2025 | 1 | 1
Nasiruddin | 03-01-2026 | 16-01-2026 | 14 | 14
Nasirudin 2 | 24-10-2025 | 24-10-2025 | 1 | 1
Nirmal Mahto | 08-11-2025 | 09-11-2025 | 2 | 2
Pankaj | 27-05-2025 | 29-05-2025 | 3 | 3
Pankaj | 28-11-2025 | 28-11-2025 | 1 | 1
Pankaj | 13-12-2025 | 14-12-2025 | 2 | 2
Pankaj | 06-01-2026 | 06-01-2026 | 1 | 1
Pankaj 1 | 25-09-2025 | 26-09-2025 | 2 | 2
Panva Devi | 08-12-2025 | 09-12-2025 | 2 | 2
Pinki Devi | 21-08-2025 | 24-08-2025 | 4 | 4
Pinky Dewi | 01-05-2025 | 04-05-2025 | 4 | 4
Pinky Dewi | 10-06-2025 | 11-06-2025 | 2 | 2
Pinky Dewi | 05-12-2025 | 06-12-2025 | 2 | 2
Poonam | 28-06-2025 | 28-06-2025 | 1 | 1
Poonam | 03-07-2025 | 03-07-2025 | 1 | 1
Poonam | 22-07-2025 | 27-07-2025 | 6 | 6
Praveen | 03-08-2025 | 07-08-2025 | 5 | 5
Praveen | 09-09-2025 | 12-09-2025 | 4 | 4
Praveen | 12-10-2025 | 13-10-2025 | 2 | 2
Praveen | 28-10-2025 | 31-10-2025 | 4 | 4
Praveen | 01-11-2025 | 05-11-2025 | 5 | 5
Praveen | 24-11-2025 | 26-11-2025 | 3 | 3
Prayag Mahto | 07-10-2025 | 13-10-2025 | 7 | 7
Prayag Mahto | 20-10-2025 | 28-10-2025 | 9 | 9
Prayag Saw | 26-12-2025 | 27-12-2025 | 2 | 2
Prayag Saw | 12-01-2026 | 12-01-2026 | 1 | 1
Prayag Saw | 25-01-2026 | 26-01-2026 | 2 | 2
Prayag Saw 2 | 25-10-2025 | 26-10-2025 | 2 | 2
Prayag Saw 2 | 04-12-2025 | 05-12-2025 | 2 | 2
Prayag Shah Mp | 01-01-2026 | 01-01-2026 | 1 | 1
Prayag Shah Mp | 26-01-2026 | 26-01-2026 | 1 | 1
Prem Kumar | 30-10-2025 | 31-10-2025 | 2 | 2
Prem Kumar | 01-11-2025 | 09-11-2025 | 9 | 9
Prem Kumar | 17-11-2025 | 23-11-2025 | 7 | 7
Prem Kumar | 02-12-2025 | 02-12-2025 | 1 | 1
Prem Kumar | 17-12-2025 | 18-12-2025 | 2 | 2
Prem Kumar | 30-12-2025 | 31-12-2025 | 2 | 2
Prem Kumar | 01-01-2026 | 02-01-2026 | 2 | 2
Prem Kumar | 11-01-2026 | 17-01-2026 | 7 | 7
Prem Kumar | 23-01-2026 | 24-01-2026 | 2 | 2
Pritam Enterprises 1 | 26-08-2025 | 31-08-2025 | 6 | 6
Pritam Enterprises 1 | 01-09-2025 | 02-09-2025 | 2 | 2
Pritam Enterprises 1 | 28-09-2025 | 30-09-2025 | 3 | 3
Pritam Enterprises 1 | 01-10-2025 | 01-10-2025 | 1 | 1
Pritam Enterprises 2 | 08-11-2025 | 11-11-2025 | 4 | 4
Pritam Enterprises 4 | 01-10-2025 | 07-10-2025 | 7 | 7
Pritam Enterprises 4 | 26-10-2025 | 26-10-2025 | 1 | 1
Priyanka Devi | 06-08-2025 | 13-08-2025 | 8 | 8
Priyanka Devi | 28-08-2025 | 29-08-2025 | 2 | 2
Priyanka Devi 2 | 24-07-2025 | 31-07-2025 | 8 | 8
Priyanka Devi 2 | 01-08-2025 | 04-08-2025 | 4 | 4
Priyanka Devi 2 | 20-08-2025 | 20-08-2025 | 1 | 1
Priyanka Devi Santosh | 04-09-2025 | 07-09-2025 | 4 | 4
Priyanka Devi Sudheer | 12-07-2025 | 12-07-2025 | 1 | 1
Priyanka Devi Sudheer | 20-07-2025 | 21-07-2025 | 2 | 2
Priyanka Devi Sudheer | 29-07-2025 | 31-07-2025 | 3 | 3
Priyanka Devi Sudheer | 01-08-2025 | 03-08-2025 | 3 | 3
Priyanka Devi Sudheer | 10-08-2025 | 10-08-2025 | 1 | 1
Priyanka Devi Sudheer | 23-08-2025 | 23-08-2025 | 1 | 1
Priyanka Devi Sudheer | 31-08-2025 | 31-08-2025 | 1 | 1
Priyanka Devi Sudheer | 01-09-2025 | 01-09-2025 | 1 | 1
Priyanka Devi Sudheer | 08-09-2025 | 08-09-2025 | 1 | 1
Priyanka Devi Sudheer | 13-09-2025 | 18-09-2025 | 6 | 6
Priyanka Devi Sudheer | 23-09-2025 | 29-09-2025 | 7 | 7
Priyanka Devi Sudheer | 05-10-2025 | 09-10-2025 | 5 | 5
Priyanka Devi Sudheer | 22-10-2025 | 30-10-2025 | 9 | 9
Punam Kumari | 23-09-2025 | 24-09-2025 | 2 | 2
Punam Kumari 1 | 17-09-2025 | 18-09-2025 | 2 | 2
Punam Kumari 2 | 08-01-2026 | 09-01-2026 | 2 | 2
Pusplata 1 | 01-07-2025 | 03-07-2025 | 3 | 3
Pusplata 1 | 24-07-2025 | 24-07-2025 | 1 | 1
Pusplata 1 | 31-07-2025 | 31-07-2025 | 1 | 1
Pusplata 3 | 06-07-2025 | 16-07-2025 | 11 | 11
Pusplata 3 | 24-07-2025 | 26-07-2025 | 3 | 3
Pusplata 4 | 01-07-2025 | 01-07-2025 | 1 | 1
Pusplata 4 | 23-07-2025 | 23-07-2025 | 1 | 1
Pusplata 5 | 21-07-2025 | 21-07-2025 | 1 | 1
Pusplata 6 | 01-08-2025 | 03-08-2025 | 3 | 3
Pusplata Ashok | 01-09-2025 | 03-09-2025 | 3 | 3
Pusplata Deepak | 07-08-2025 | 15-08-2025 | 9 | 9
Pusplata Deepak | 20-08-2025 | 20-08-2025 | 1 | 1
Pusplata Deepak | 31-08-2025 | 31-08-2025 | 1 | 1
Pusplata Deepak | 01-09-2025 | 01-09-2025 | 1 | 1
Pusplata Dharamveer | 15-08-2025 | 15-08-2025 | 1 | 1
Pusplata Ramchandra | 18-08-2025 | 28-08-2025 | 11 | 11
Radha Construction | 31-08-2025 | 31-08-2025 | 1 | 1
Radha Construction | 01-09-2025 | 02-09-2025 | 2 | 2
Radha Enterprises | 27-07-2025 | 31-07-2025 | 5 | 5
Radha Enterprises | 01-08-2025 | 03-08-2025 | 3 | 3
Radha Enterprises 1 | 04-06-2025 | 04-06-2025 | 1 | 1
Radha Enterprises 1 | 19-07-2025 | 27-07-2025 | 9 | 9
Rahim Khan | 12-04-2025 | 15-04-2025 | 4 | 4
Rahim Khan | 23-04-2025 | 23-04-2025 | 1 | 1
Rahim Khan | 01-05-2025 | 02-05-2025 | 2 | 2
Rahim Khan | 12-05-2025 | 12-05-2025 | 1 | 1
Rahul Kumar | 12-04-2025 | 14-04-2025 | 3 | 3
Rahul Kumar | 28-04-2025 | 28-04-2025 | 1 | 1
Rahul Kumar | 05-05-2025 | 07-05-2025 | 3 | 3
Rahul Kumar | 23-07-2025 | 23-07-2025 | 1 | 1
Rahul Kumar | 30-07-2025 | 30-07-2025 | 1 | 1
Rahul Kumar | 03-09-2025 | 04-09-2025 | 2 | 2
Rahul Kumar | 17-10-2025 | 17-10-2025 | 1 | 1
Rahul Kumar | 27-10-2025 | 28-10-2025 | 2 | 2
Rahul Kumar | 10-11-2025 | 13-11-2025 | 4 | 4
Rahul Kumar | 06-12-2025 | 07-12-2025 | 2 | 2
Rajesh Kumar | 12-12-2025 | 12-12-2025 | 1 | 1
Rames Kumar M | 09-05-2025 | 22-05-2025 | 14 | 14
Rames Kumar M | 24-10-2025 | 25-10-2025 | 2 | 2
Rames Kumar M | 01-11-2025 | 13-11-2025 | 13 | 13
Ramesh Kumar | 10-04-2025 | 10-04-2025 | 1 | 1
Ramesh Kumar | 17-04-2025 | 18-04-2025 | 2 | 2
Ramesh Kumar | 24-04-2025 | 24-04-2025 | 1 | 1
Ramesh Kumar | 28-04-2025 | 30-04-2025 | 3 | 3
Ramesh Kumar | 04-05-2025 | 08-05-2025 | 5 | 5
Ramesh Kumar | 11-05-2025 | 18-05-2025 | 8 | 8
Ramesh Kumar | 23-05-2025 | 25-05-2025 | 3 | 3
Ramesh Kumar | 01-06-2025 | 03-06-2025 | 3 | 3
Ramesh Kumar | 07-06-2025 | 08-06-2025 | 2 | 2
Ramesh Kumar | 12-06-2025 | 12-06-2025 | 1 | 1
Ramesh Kumar | 18-06-2025 | 19-06-2025 | 2 | 2
Ramesh Kumar | 26-06-2025 | 30-06-2025 | 5 | 5
Ramesh Kumar | 06-07-2025 | 06-07-2025 | 1 | 1
Ramesh Kumar | 08-07-2025 | 10-07-2025 | 3 | 3
Ramesh Kumar | 17-07-2025 | 23-07-2025 | 7 | 7
Ramesh Kumar | 27-07-2025 | 27-07-2025 | 1 | 1
Ramesh Kumar | 23-10-2025 | 31-10-2025 | 9 | 9
Ramesh Kumar | 01-11-2025 | 01-11-2025 | 1 | 1
Ramesh Kumar | 13-11-2025 | 20-11-2025 | 8 | 8
Ramesh Kumar | 25-11-2025 | 25-11-2025 | 1 | 1
Ramesh Kumar | 30-11-2025 | 30-11-2025 | 1 | 1
Ramesh Kumar | 01-12-2025 | 03-12-2025 | 3 | 3
Ramesh Kumar | 09-12-2025 | 17-12-2025 | 9 | 9
Ramesh Kumar | 21-12-2025 | 21-12-2025 | 1 | 1
Ramesh Kumar M | 13-05-2025 | 13-05-2025 | 1 | 1
Ramesh Kumar M | 16-05-2025 | 16-05-2025 | 1 | 1
Ramesh Kumar M | 20-05-2025 | 23-05-2025 | 4 | 4
Reeta Bharti | 22-05-2025 | 22-05-2025 | 1 | 1
Reeta Bharti | 01-08-2025 | 05-08-2025 | 5 | 5
Rudra Construction | 24-04-2025 | 29-04-2025 | 6 | 6
Rudra Construction | 08-05-2025 | 09-05-2025 | 2 | 2
Rupesh | 02-04-2025 | 05-04-2025 | 4 | 4
Rupesh | 24-09-2025 | 30-09-2025 | 7 | 7
Rupesh | 01-10-2025 | 05-10-2025 | 5 | 5
Sainik Trader | 25-09-2025 | 25-09-2025 | 1 | 1
Sainik Traders | 31-07-2025 | 31-07-2025 | 1 | 1
Sainik Traders | 01-09-2025 | 02-09-2025 | 2 | 2
Sainik Traders | 25-11-2025 | 27-11-2025 | 3 | 3
Sainik Traders | 31-12-2025 | 31-12-2025 | 1 | 1
Sainik Traders | 01-01-2026 | 01-01-2026 | 1 | 1
Sainik Traders | 12-01-2026 | 12-01-2026 | 1 | 1
Sainik Traders | 21-01-2026 | 21-01-2026 | 1 | 1
Sainik Traders | 28-01-2026 | 29-01-2026 | 2 | 2
Sakila Khatun | 19-10-2025 | 21-10-2025 | 3 | 3
Sakila Khatun | 14-11-2025 | 15-11-2025 | 2 | 2
Sanjeet | 03-12-2025 | 03-12-2025 | 1 | 1
Sanjeet | 11-12-2025 | 11-12-2025 | 1 | 1
Sanjeet | 31-12-2025 | 31-12-2025 | 1 | 1
Sanjeet | 01-01-2026 | 02-01-2026 | 2 | 2
Sanjeev Kumar | 04-09-2025 | 04-09-2025 | 1 | 1
Santosh Singh | 09-11-2025 | 10-11-2025 | 2 | 2
Satish Kumar | 20-10-2025 | 28-10-2025 | 9 | 9
Satyam Manish | 04-06-2025 | 07-06-2025 | 4 | 4
Satyam Manish | 14-06-2025 | 15-06-2025 | 2 | 2
Satyam Manish | 01-07-2025 | 03-07-2025 | 3 | 3
Satyam Manish | 14-07-2025 | 14-07-2025 | 1 | 1
Satyam Manish | 08-08-2025 | 08-08-2025 | 1 | 1
Satyam Mondal | 26-05-2025 | 26-05-2025 | 1 | 1
Satyam Mondal | 07-06-2025 | 07-06-2025 | 1 | 1
Satyam Mondal | 24-06-2025 | 24-06-2025 | 1 | 1
Satyam Mondal | 07-07-2025 | 09-07-2025 | 3 | 3
Satyam Nitish | 25-05-2025 | 25-05-2025 | 1 | 1
Satyam Nitish | 16-06-2025 | 16-06-2025 | 1 | 1
Satyam Nitish | 01-07-2025 | 03-07-2025 | 3 | 3
Satyam Trading | 01-12-2025 | 02-12-2025 | 2 | 2
Satyam Trivedi | 20-06-2025 | 22-06-2025 | 3 | 3
Satyam Trivedi | 29-06-2025 | 29-06-2025 | 1 | 1
Satyam Trivedi | 06-07-2025 | 08-07-2025 | 3 | 3
Satyam Vijay | 28-05-2025 | 28-05-2025 | 1 | 1
Satyam Vijay | 09-06-2025 | 09-06-2025 | 1 | 1
Satyam Vijay | 01-08-2025 | 05-08-2025 | 5 | 5
Savitha | 08-08-2025 | 08-08-2025 | 1 | 1
Savitha | 23-08-2025 | 31-08-2025 | 9 | 9
Savitha | 01-09-2025 | 04-09-2025 | 4 | 4
Senahul | 27-04-2025 | 28-04-2025 | 2 | 2
Shakila Khatun | 04-09-2025 | 04-09-2025 | 1 | 1
Sheetal Singh | 01-01-2026 | 02-01-2026 | 2 | 2
Sheetal Singh 1 | 14-09-2025 | 24-09-2025 | 11 | 11
Shila Devi | 01-01-2026 | 01-01-2026 | 1 | 1
Shobha Devi | 18-08-2025 | 29-08-2025 | 12 | 12
Shobha Devi | 15-11-2025 | 17-11-2025 | 3 | 3
Shobha Devi | 01-12-2025 | 02-12-2025 | 2 | 2
Shobha Devi | 20-12-2025 | 26-12-2025 | 7 | 7
Shobha Devi | 01-01-2026 | 02-01-2026 | 2 | 2
Sital Singh 2 | 31-08-2025 | 31-08-2025 | 1 | 1
Sital Singh 2 | 01-09-2025 | 14-09-2025 | 14 | 14
Sk Samiul 1 | 11-08-2025 | 11-08-2025 | 1 | 1
Sk Samiul 1 | 19-09-2025 | 23-09-2025 | 5 | 5
Sk Samiul 1 | 05-10-2025 | 05-10-2025 | 1 | 1
Sobha Devi | 12-11-2025 | 14-11-2025 | 3 | 3
Subash | 16-10-2025 | 16-10-2025 | 1 | 1
Subash | 24-11-2025 | 25-11-2025 | 2 | 2
Subash | 05-01-2026 | 06-01-2026 | 2 | 2
Subhash | 02-09-2025 | 02-09-2025 | 1 | 1
Subhash | 08-09-2025 | 08-09-2025 | 1 | 1
Subhash | 14-09-2025 | 15-09-2025 | 2 | 2
Subhash | 12-10-2025 | 12-10-2025 | 1 | 1
Subhash | 25-10-2025 | 28-10-2025 | 4 | 4
Subhash | 10-11-2025 | 10-11-2025 | 1 | 1
Subhash | 20-12-2025 | 27-12-2025 | 8 | 8
Sukhriddin | 29-04-2025 | 30-04-2025 | 2 | 2
Sukhriddin | 01-05-2025 | 01-05-2025 | 1 | 1
Sukhrridin | 04-10-2025 | 04-10-2025 | 1 | 1
Sukruddin | 18-10-2025 | 23-10-2025 | 6 | 6
Sulen Sarkar | 01-05-2025 | 10-05-2025 | 10 | 10
Suman | 14-12-2025 | 14-12-2025 | 1 | 1
Suman | 18-12-2025 | 24-12-2025 | 7 | 7
Sunny Const | 10-05-2025 | 11-05-2025 | 2 | 2
Sunny Const | 08-12-2025 | 08-12-2025 | 1 | 1
Sunny Construction | 01-01-2026 | 02-01-2026 | 2 | 2
Tejal | 02-09-2025 | 02-09-2025 | 1 | 1
Tejal | 19-09-2025 | 26-09-2025 | 8 | 8
Tejal Const | 04-10-2025 | 07-10-2025 | 4 | 4
Tejal Mahto | 07-11-2025 | 11-11-2025 | 5 | 5
Tejal Mahto | 18-11-2025 | 29-11-2025 | 12 | 12
Tejal Mahto | 05-12-2025 | 05-12-2025 | 1 | 1
Teklal Mahto | 18-10-2025 | 22-10-2025 | 5 | 5
Toshan Mahato | 01-01-2026 | 01-01-2026 | 1 | 1
Usha Tower | 01-08-2025 | 03-08-2025 | 3 | 3
Usha Tower | 20-08-2025 | 21-08-2025 | 2 | 2
Usha Tower | 30-08-2025 | 30-08-2025 | 1 | 1
Vedanta Construction | 18-12-2025 | 18-12-2025 | 1 | 1
Vinay Const | 10-07-2025 | 10-07-2025 | 1 | 1
Vinay Const | 21-07-2025 | 23-07-2025 | 3 | 3
Vinay Construction | 01-12-2025 | 02-12-2025 | 2 | 2
Vinay Construction | 11-01-2026 | 11-01-2026 | 1 | 1
Vinod | 12-09-2025 | 13-09-2025 | 2 | 2
Vivek Ganju | 08-10-2025 | 08-10-2025 | 1 | 1
Vivek Ganju | 24-10-2025 | 26-10-2025 | 3 | 3
Vivek Ganju | 17-11-2025 | 17-11-2025 | 1 | 1
Vivek Ganju | 27-11-2025 | 27-11-2025 | 1 | 1
Vivek Ganju | 06-12-2025 | 06-12-2025 | 1 | 1

## Project Gang Rankings
Scope: 2025-04-01 to 2026-02-28 ¦ Projects: 17 ¦ Erections: 2584 ¦ Gangs: 429
Top 3 Gangs
PCH | Project | Gang Name | Avg Productivity (MTD) | Avg Productivity (Overall) | Total MT (MTD) | Total No. of Erections (MTD) | Avg Tower Weight Overall | Idle Counted (days) | Number of Idle Intervals
Mr. Sanjay Kumar Gupta | TA413 | Punam Kumari 2 | 7.56 | 5.33 | 605.17 | 13 | 46.55 | 2 | 1
Mr. Sanjay Kumar Gupta | TA413 | Ved Prakash | 6.2 | 6.2 | 929.86 | 12 | 77.49 | 0 | 0
Mr. Sanjay Kumar Gupta | TA413 | Punam Kumari | 5.6 | 3.84 | 196.11 | 4 | 49.03 | 2 | 1
Mr. Sanjay Kumar Gupta | TA419 | Radha Enterprises | 6.66 | 5.61 | 659.6 | 8 | 82.45 | 8 | 2
Mr. Sanjay Kumar Gupta | TA419 | Radha Enterprises 1 | 5.34 | 5.16 | 635.35 | 13 | 48.87 | 10 | 2
Mr. Sanjay Kumar Gupta | TA419 | Jwala Singh | 5.15 | 6.56 | 541.26 | 13 | 41.64 | 6 | 4
Mr. Sanjay Kumar Gupta | TA512 | M S Shobha Debi | 7.38 | 7.38 | 147.62 | 4 | 36.91 | 2 | 1
Mr. Sanjay Kumar Gupta | TA512 | M S Kartik Mahto | 6.97 | 6.97 | 948.13 | 24 | 39.51 | 0 | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Govind Mahto | 5.91 | 5.91 | 165.36 | 4 | 41.34 | 0 | 0
Mr. Sanjay Kumar Gupta | TB401 | Satyam Manish | 8.5 | 8.28 | 747.84 | 13 | 57.53 | 11 | 5
Mr. Sanjay Kumar Gupta | TB401 | Jwala Singh 3 | 8.09 | 8.09 | 283.16 | 5 | 56.63 | 8 | 3
Mr. Sanjay Kumar Gupta | TB401 | Pusplata 4 | 8.04 | 8.04 | 313.74 | 8 | 39.22 | 2 | 2
Mr. Sanjay Kumar Gupta | TB408 | Satyam Enterprises | 7.81 | 7.81 | 492.15 | 10 | 49.21 | 0 | 0
Mr. Sanjay Kumar Gupta | TB408 | Sobha Devi | 7.71 | 6.58 | 190.21 | 5 | 38.04 | 3 | 1
Mr. Sanjay Kumar Gupta | TB408 | Shobha Devi | 7.3 | 7.3 | 1153.97 | 19 | 60.74 | 26 | 5
Mr. Sanjay Kumar Gupta | TB507 | Prayag Saw 1 | 3.38 | 3.38 | 216.25 | 14 | 15.45 | 0 | 0
Mr. Sanjay Kumar Gupta | TB507 | Prayag Saw | 3.33 | 3.33 | 190.05 | 12 | 15.84 | 5 | 3
Mr. Sanjay Kumar Gupta | TB507 | Prayag Saw 2 | 3.21 | 3.21 | 340.35 | 22 | 15.47 | 4 | 2
Mr. Arun Felbin | TA325 | Gourishankar | 8.34 | 6.26 | 508.76 | 7 | 72.68 | 11 | 6
Mr. Arun Felbin | TA325 | Jwala | 7.5 | 7.68 | 383.77 | 6 | 63.96 | 9 | 6
Mr. Arun Felbin | TA325 | Rahul Kumar | 6.83 | 5.35 | 615.15 | 9 | 68.35 | 20 | 10
Mr. Arun Felbin | TA414 | Sakila Khatun | 7.29 | 7.05 | 269.72 | 4 | 67.43 | 5 | 2
Mr. Arun Felbin | TA414 | Anannya Traders | 6.14 | 6.14 | 245.41 | 6 | 40.9 | 0 | 0
Mr. Arun Felbin | TA414 | Rahul Kumar | 6 | 5.35 | 366.03 | 7 | 52.29 | 20 | 10
Mr. Arun Felbin | TA416 | Dewi Construction Girendra | 6.96 | 6.64 | 438.43 | 9 | 48.71 | 4 | 2
Mr. Arun Felbin | TA416 | Ananya Traders 2 | 6.77 | 6.77 | 595.89 | 11 | 54.17 | 1 | 1
Mr. Arun Felbin | TA416 | Gagan Enterprise 1 | 6.4 | 6.39 | 952.15 | 13 | 73.24 | 9 | 2
Mr. Arun Felbin | TA418 | Subhash | 5.05 | 5.49 | 303.1 | 7 | 43.3 | 18 | 7
Mr. Arun Felbin | TA418 | M S Tofit | 4.48 | 4.48 | 631.3 | 15 | 42.09 | 11 | 5
Mr. Arun Felbin | TA418 | Gang 02 Sanjay | 4.3 | 1.55 | 503.63 | 14 | 35.97 | 14 | 6
Mr. Arun Felbin | TA421 | Khatun | 8.49 | 7.24 | 1859.31 | 40 | 46.48 | 28 | 10
Mr. Arun Felbin | TA421 | Subash | 7.94 | 7.46 | 2460.96 | 62 | 39.69 | 5 | 3
Mr. Arun Felbin | TA421 | Gauri Shankar Mahto | 6.67 | 6.67 | 233.34 | 4 | 58.34 | 13 | 2
Mr. Arun Felbin | TB501 | Rames Kumar M | 2.8 | 2.8 | 53.16 | 8 | 6.64 | 29 | 3
Mr. Arun Felbin | TB501 | Dudhnath Kumar | 2.72 | 2.51 | 234.14 | 31 | 7.55 | 44 | 12
Mr. Arun Felbin | TB501 | Ramesh Kumar | 2.72 | 2.54 | 344.19 | 45 | 7.65 | 81 | 24
Mr. Dheeraj Vashishth | TA513 | Anil Construction | 3.84 | 3.84 | 411.02 | 18 | 22.83 | 1 | 1
Mr. Nabajit Baruah | TA504 | Punam Kumari 1 | 6.13 | 4.48 | 411 | 7 | 58.71 | 2 | 1
Mr. Nabajit Baruah | TA504 | Pankaj | 5.98 | 6.34 | 342 | 9 | 38 | 7 | 4
Mr. Nabajit Baruah | TA504 | Pankaj 2 | 5.81 | 6.37 | 471 | 12 | 39.25 | 0 | 0
Mr. Nabajit Baruah | TA505 | Jwala Singh | 6.81 | 6.56 | 2038.22 | 42 | 48.53 | 6 | 4
Mr. Nabajit Baruah | TA505 | Deglal Mahato | 6.37 | 6.37 | 1070.42 | 18 | 59.47 | 0 | 0
Mr. Nabajit Baruah | TA505 | Jwala Singh 2 | 6.23 | 5.81 | 837.91 | 21 | 39.9 | 28 | 7
Mr. Nabajit Baruah | TA506 | Tejal Mahto | 5.81 | 5.81 | 122 | 4 | 30.5 | 18 | 3
Mr. Nabajit Baruah | TA506 | Horil | 5.3 | 5.3 | 122 | 5 | 24.4 | 0 | 0
Mr. Nabajit Baruah | TA506 | Gulab Mahto | 4.83 | 4.83 | 169 | 9 | 18.78 | 0 | 0
Bottom 3 Gangs
PCH | Project | Gang Name | Avg Productivity (MTD) | Avg Productivity (Overall) | Total MT (MTD) | Total No. of Erections (MTD) | Avg Tower Weight Overall | Idle Counted (days) | Number of Idle Intervals
Mr. Sanjay Kumar Gupta | TA413 | Pritam Enterprises 4 | 2.82 | 2.82 | 262.62 | 6 | 43.77 | 8 | 2
Mr. Sanjay Kumar Gupta | TA413 | Sk Samiul 2 | 3.23 | 3.23 | 145.46 | 4 | 36.37 | 0 | 0
Mr. Sanjay Kumar Gupta | TA413 | Amar Kumar Singh | 3.33 | 3.33 | 223.06 | 4 | 55.77 | 3 | 1
Mr. Sanjay Kumar Gupta | TA419 | Infinidea | 1.4 | 1.4 | 204.53 | 4 | 51.13 | 0 | 0
Mr. Sanjay Kumar Gupta | TA419 | Ganesh 2 | 1.87 | 1.87 | 196.68 | 4 | 49.17 | 4 | 1
Mr. Sanjay Kumar Gupta | TA419 | Bhairo Mahato | 3 | 3 | 377.81 | 4 | 94.45 | 0 | 0
Mr. Sanjay Kumar Gupta | TA512 | M S Company Gang | 1.47 | 1.47 | 278.73 | 8 | 34.84 | 1 | 1
Mr. Sanjay Kumar Gupta | TA512 | M S Kavya Enterprises | 3.59 | 3.59 | 486.91 | 12 | 40.58 | 15 | 4
Mr. Sanjay Kumar Gupta | TA512 | M S Punam Kumari 3 | 4.08 | 4.08 | 305.78 | 8 | 38.22 | 3 | 3
Mr. Sanjay Kumar Gupta | TB401 | Pusplata Ashok | 1.28 | 1.68 | 191.12 | 4 | 47.78 | 3 | 1
Mr. Sanjay Kumar Gupta | TB401 | Satyam Trivedi | 2.29 | 1.52 | 287.81 | 7 | 41.12 | 7 | 3
Mr. Sanjay Kumar Gupta | TB401 | Vivek Ganju | 3.76 | 3.61 | 236.96 | 6 | 39.49 | 7 | 5
Mr. Sanjay Kumar Gupta | TB408 | Vedanta Construction | 1.97 | 1.97 | 187.52 | 5 | 37.5 | 1 | 1
Mr. Sanjay Kumar Gupta | TB408 | Bhairo Mahto | 2.2 | 2.37 | 229.06 | 6 | 38.18 | 2 | 2
Mr. Sanjay Kumar Gupta | TB408 | Vinay Construction | 3.17 | 3.22 | 415.59 | 10 | 41.56 | 3 | 2
Mr. Sanjay Kumar Gupta | TB507 | Rajesh Mahto | 0.63 | 0.63 | 57.11 | 4 | 14.28 | 0 | 0
Mr. Sanjay Kumar Gupta | TB507 | Namechand Mahto | 0.71 | 0.6 | 278.81 | 17 | 16.4 | 0 | 0
Mr. Sanjay Kumar Gupta | TB507 | Ahmed Construction | 1.54 | 1.54 | 101.95 | 8 | 12.74 | 3 | 1
Mr. Arun Felbin | TA325 | Mithun Kumar | 1.68 | 2.25 | 529.52 | 7 | 75.65 | 0 | 0
Mr. Arun Felbin | TA325 | Modina India | 1.94 | 2.38 | 322.23 | 5 | 64.45 | 3 | 2
Mr. Arun Felbin | TA325 | Rupesh | 2.01 | 2.1 | 371.25 | 4 | 92.81 | 16 | 3
Mr. Arun Felbin | TA414 | Mithun Kumar | 3.72 | 2.25 | 159.95 | 4 | 39.99 | 0 | 0
Mr. Arun Felbin | TA414 | M S Sakkurddin | 4.13 | 4.13 | 165.12 | 4 | 41.28 | 15 | 4
Mr. Arun Felbin | TA414 | Subhash | 5.28 | 5.49 | 232.19 | 5 | 46.44 | 18 | 7
Mr. Arun Felbin | TA416 | M K Infra | 2.21 | 2.45 | 176.85 | 4 | 44.21 | 8 | 1
Mr. Arun Felbin | TA416 | Punam Kumari 1 | 3.31 | 4.48 | 288.38 | 4 | 72.09 | 2 | 1
Mr. Arun Felbin | TA416 | Punam Kumari 2 | 3.52 | 5.33 | 204.2 | 4 | 51.05 | 2 | 1
Mr. Arun Felbin | TA418 | Kec 02 Barkat Ali | 1.26 | 1.13 | 682.9 | 19 | 35.94 | 0 | 0
Mr. Arun Felbin | TA418 | Kec 01 Barkat Ali | 2.17 | 2.17 | 210.63 | 7 | 30.09 | 4 | 1
Mr. Arun Felbin | TA418 | M S Mdpl | 3.34 | 3.34 | 534.3 | 12 | 44.52 | 3 | 3
Mr. Arun Felbin | TA421 | Praveen | 2.07 | 2.26 | 511.34 | 12 | 42.61 | 23 | 6
Mr. Arun Felbin | TA421 | Hassan | 4.22 | 4.22 | 890.28 | 18 | 49.46 | 9 | 4
Mr. Arun Felbin | TA421 | Naziruddin | 4.86 | 4.86 | 461.81 | 11 | 41.98 | 0 | 0
Mr. Arun Felbin | TB501 | Suman | 1.32 | 1.32 | 70 | 9 | 7.78 | 8 | 2
Mr. Arun Felbin | TB501 | Ramesh Kumar M | 2.14 | 2.14 | 25.68 | 5 | 5.14 | 6 | 3
Mr. Arun Felbin | TB501 | Dudhnath Kumar | 2.72 | 2.51 | 234.14 | 31 | 7.55 | 44 | 12
Mr. Dheeraj Vashishth | TA513 | Anil Construction | 3.84 | 3.84 | 411.02 | 18 | 22.83 | 1 | 1
Mr. Nabajit Baruah | TA504 | Karam Mahto | 2.73 | 2.73 | 259 | 6 | 43.17 | 3 | 2
Mr. Nabajit Baruah | TA504 | Sainik Traders | 3.86 | 3.91 | 648 | 14 | 46.29 | 12 | 8
Mr. Nabajit Baruah | TA504 | Ghyansham Mahto | 3.87 | 3.87 | 565 | 9 | 62.78 | 7 | 5
Mr. Nabajit Baruah | TA505 | Paramanand 1 | 1.82 | 1.82 | 357.37 | 9 | 39.71 | 0 | 0
Mr. Nabajit Baruah | TA505 | Crane Erc Team Mp | 2.87 | 2.87 | 405.03 | 10 | 40.5 | 0 | 0
Mr. Nabajit Baruah | TA505 | Eagle Enterprises Paramand | 3.31 | 3.31 | 308.08 | 8 | 38.51 | 2 | 1
Mr. Nabajit Baruah | TA506 | Tejal | 3.19 | 3.19 | 83 | 4 | 20.75 | 9 | 2
Mr. Nabajit Baruah | TA506 | Pankaj 1 | 3.69 | 3.69 | 118 | 4 | 29.5 | 2 | 1
Mr. Nabajit Baruah | TA506 | Ab Construction | 3.71 | 3.71 | 89 | 4 | 22.25 | 1 | 1

## Idle Days Buckets
Overall Idle Days Buckets | [13 empty] | MTD Idle Days Buckets
Erections >=1 | [13 empty] | Erections >=1
Scope: 2023-09-13 to 2026-02-09 ¦ Projects: 3 ¦ Erections: 3949 ¦ Gangs: 472 | [13 empty] | Scope: 2025-04-01 to 2026-02-28 ¦ Projects: 17 ¦ Erections: 2584 ¦ Gangs: 429
Metric | 0-1 | 1-2 | 2-3 | 3-4 | 4-5 | 5-6 | 6-7 | 7-8 | 8-9 | 9-10 | 10-11 | 11-12 | >12 | Metric | 0-1 | 1-2 | 2-3 | 3-4 | 4-5 | 5-6 | 6-7 | 7-8 | 8-9 | 9-10 | 10-11 | 11-12 | >12
Days per idle window (severity) | 0 | 1.04 | 1.4 | 1.69 | 1.54 | 1.78 | 1.02 | 1.37 | 1.47 | 0 | 1 | 0 | 0 | Days per idle window (severity) | 0 | 0.89 | 1.41 | 1.65 | 1.51 | 1.6 | 1.12 | 1.53 | 1.73 | 0 | 1 | 0 | 0
Avg Idle Days (Magnitude) | 0 | 1.98 | 5.79 | 4.83 | 6.05 | 7.03 | 5.92 | 6 | 5.25 | 0 | 1 | 0 | 0 | Avg Idle Days (Magnitude) | 0 | 1.37 | 4.4 | 3.38 | 5.2 | 5.31 | 3.11 | 4.65 | 9.8 | 0 | 1 | 0 | 0
Idle windows per gang (Frequency) | 0 | 0.66 | 1.59 | 1.66 | 2.03 | 2.42 | 2.61 | 2.24 | 2.5 | 0 | 1 | 0 | 0 | Idle windows per gang (Frequency) | 0 | 0.44 | 1.15 | 1.09 | 1.67 | 1.93 | 1.14 | 1.75 | 4 | 0 | 1 | 0 | 0
Gang Count | 11 | 50 | 82 | 110 | 94 | 59 | 36 | 21 | 4 | 2 | 1 | 1 | 1 | Gang Count | 11 | 41 | 68 | 98 | 94 | 59 | 28 | 20 | 5 | 2 | 1 | 1 | 1
Weight Erected (MT) - Daily Prod | 720.77 | 7454.8 | 15109.54 | 28396.32 | 36143.12 | 31414.44 | 35838.79 | 13347.5 | 1449.96 | 162.48 | 83.03 | 34.7 | 57.6 | Weight Erected (MT) - Daily Prod | 669.83 | 5234.39 | 8898.57 | 18693 | 28905.64 | 23798.78 | 13720.27 | 8517.93 | 3274.8 | 162.48 | 83.03 | 34.7 | 57.6
Weight Erected (MT) - Tower Weight | 720.77 | 7435.03 | 15109.55 | 28396.32 | 36143.11 | 31414.44 | 35838.79 | 13347.5 | 1449.96 | 162.48 | 83.03 | 34.7 | 57.6 | Weight Erected (MT) - Tower Weight | 712.91 | 5253.77 | 9041.94 | 18836.35 | 29089.03 | 23948.49 | 13745.97 | 8622.56 | 3309.27 | 162.48 | 83.03 | 34.7 | 57.6
Erections >=2 | [13 empty] | Erections >=2
Scope: 2023-09-13 to 2026-02-09 ¦ Projects: 3 ¦ Erections: 3949 ¦ Gangs: 472 | [13 empty] | Scope: 2025-04-01 to 2026-02-28 ¦ Projects: 17 ¦ Erections: 2584 ¦ Gangs: 429
Metric | 0-1 | 1-2 | 2-3 | 3-4 | 4-5 | 5-6 | 6-7 | 7-8 | 8-9 | 9-10 | 10-11 | 11-12 | >12 | Metric | 0-1 | 1-2 | 2-3 | 3-4 | 4-5 | 5-6 | 6-7 | 7-8 | 8-9 | 9-10 | 10-11 | 11-12 | >12
Days per idle window (severity) | 0 | 1.58 | 2.55 | 2.19 | 1.83 | 2.09 | 1.31 | 2.06 | 1.96 | 0 | 1 | 0 | 0 | Days per idle window (severity) | 0 | 1.41 | 2.81 | 2.28 | 1.77 | 1.89 | 1.66 | 2.19 | 2.17 | 0 | 1 | 0 | 0
Avg Idle Days (Magnitude) | 0 | 3 | 10.56 | 6.25 | 7.2 | 8.3 | 7.61 | 9 | 7 | 0 | 1 | 0 | 0 | Avg Idle Days (Magnitude) | 0 | 2.15 | 8.79 | 4.66 | 6.11 | 6.26 | 4.58 | 6.64 | 12.25 | 0 | 1 | 0 | 0
Idle windows per gang (Frequency) | 0 | 1 | 2.89 | 2.15 | 2.42 | 2.86 | 3.36 | 3.36 | 3.33 | 0 | 1 | 0 | 0 | Idle windows per gang (Frequency) | 0 | 0.69 | 2.29 | 1.51 | 1.96 | 2.28 | 1.68 | 2.5 | 5 | 0 | 1 | 0 | 0
Gang Count | 3 | 33 | 45 | 85 | 79 | 50 | 28 | 14 | 3 | 1 | 1 | 0 | 0 | Gang Count | 4 | 26 | 34 | 71 | 80 | 50 | 19 | 14 | 4 | 1 | 1 | 0 | 0
Weight Erected (MT) - Daily Prod | 418.38 | 6731.42 | 13248.75 | 26892.69 | 35447.07 | 30876.58 | 35397.33 | 12932.47 | 1383.58 | 76.35 | 83.03 | 0 | 0 | Weight Erected (MT) - Daily Prod | 445.93 | 4595.92 | 7146.89 | 17109.17 | 28245.83 | 23260.92 | 13239.64 | 8147.63 | 3208.42 | 76.35 | 83.03 | 0 | 0
Weight Erected (MT) - Tower Weight | 418.38 | 6711.65 | 13248.76 | 26892.69 | 35447.06 | 30876.58 | 35397.33 | 12932.47 | 1383.58 | 76.35 | 83.03 | 0 | 0 | Weight Erected (MT) - Tower Weight | 448.25 | 4615.3 | 7290.26 | 17252.52 | 28416.8 | 23410.63 | 13258.81 | 8252.26 | 3242.89 | 76.35 | 83.03 | 0 | 0
Erections >=3 | [13 empty] | Erections >=3
Scope: 2023-09-13 to 2026-02-09 ¦ Projects: 3 ¦ Erections: 3949 ¦ Gangs: 472 | [13 empty] | Scope: 2025-04-01 to 2026-02-28 ¦ Projects: 17 ¦ Erections: 2584 ¦ Gangs: 429
Metric | 0-1 | 1-2 | 2-3 | 3-4 | 4-5 | 5-6 | 6-7 | 7-8 | 8-9 | 9-10 | 10-11 | 11-12 | >12 | Metric | 0-1 | 1-2 | 2-3 | 3-4 | 4-5 | 5-6 | 6-7 | 7-8 | 8-9 | 9-10 | 10-11 | 11-12 | >12
Days per idle window (severity) | 0 | 1.86 | 3.12 | 1.97 | 1.85 | 2.21 | 1.47 | 2.06 | 1.96 | 0 | 0 | 0 | 0 | Days per idle window (severity) | 0 | 1.69 | 3.12 | 2.06 | 1.84 | 1.99 | 1.97 | 2.19 | 2.17 | 0 | 0 | 0 | 0
Avg Idle Days (Magnitude) | 0 | 4.1 | 14.38 | 6.7 | 7.86 | 8.81 | 8.52 | 9 | 7 | 0 | 0 | 0 | 0 | Avg Idle Days (Magnitude) | 0 | 2.82 | 11.96 | 4.94 | 6.92 | 6.64 | 5.44 | 6.64 | 12.25 | 0 | 0 | 0 | 0
Idle windows per gang (Frequency) | 0 | 1.33 | 4 | 2.44 | 2.64 | 3.02 | 3.76 | 3.36 | 3.33 | 0 | 0 | 0 | 0 | Idle windows per gang (Frequency) | 0 | 0.88 | 3.26 | 1.74 | 2.2 | 2.4 | 2 | 2.5 | 5 | 0 | 0 | 0 | 0
Gang Count | 2 | 21 | 32 | 70 | 69 | 47 | 25 | 14 | 3 | 0 | 0 | 0 | 0 | Gang Count | 2 | 17 | 23 | 54 | 66 | 47 | 16 | 14 | 4 | 0 | 0 | 0 | 0
Weight Erected (MT) - Daily Prod | 335.92 | 5930.44 | 11814.86 | 25446.25 | 34476.11 | 30370.49 | 35036.29 | 12932.47 | 1383.58 | 0 | 0 | 0 | 0 | Weight Erected (MT) - Daily Prod | 333.6 | 4040.72 | 5999.65 | 15448.89 | 26765.44 | 22754.83 | 12878.6 | 8147.63 | 3208.42 | 0 | 0 | 0 | 0
Weight Erected (MT) - Tower Weight | 335.92 | 5910.67 | 11814.86 | 25446.25 | 34476.1 | 30370.49 | 35036.29 | 12932.47 | 1383.58 | 0 | 0 | 0 | 0 | Weight Erected (MT) - Tower Weight | 335.92 | 4060.1 | 6143.01 | 15588.4 | 26881.57 | 22904.54 | 12897.77 | 8252.26 | 3242.89 | 0 | 0 | 0 | 0
Idle Days Audit (Erections >=3) | [13 empty] | Idle Days Audit (Erections >=3)
Scope: 2023-09-13 to 2026-02-09 ¦ Projects: 3 ¦ Erections: 3949 ¦ Gangs: 472 | [13 empty] | Scope: 2025-04-01 to 2026-02-28 ¦ Projects: 17 ¦ Erections: 2584 ¦ Gangs: 429
Gang Name | Productivity (MT/day) | Bucket | Idle Days | Idle Intervals | Idle Days per Interval | Towers Erected | Daily Prod Sum (MT) | Tower Weight Sum (MT) | Project Codes |  |  |  |  | Gang Name | Productivity (MT/day) | Bucket | Idle Days | Idle Intervals | Idle Days per Interval | Towers Erected | Daily Prod Sum (MT) | Tower Weight Sum (MT) | Project Codes
Namechand Mahto | 0.6 | 0-1 | 0 | 0 | 0 | 17 | 278.81 | 278.81 | TB507 |  |  |  |  | Namechand Mahto | 0.71 | 0-1 | 0 | 0 | 0 | 17 | 276.49 | 278.81 | TB507
Rajesh Mahto | 0.63 | 0-1 | 0 | 0 | 0 | 4 | 57.11 | 57.11 | TB507 |  |  |  |  | Rajesh Mahto | 0.63 | 0-1 | 0 | 0 | 0 | 4 | 57.11 | 57.11 | TB507
Ahmed Construction | 1.54 | 1-2 | 3 | 1 | 3 | 8 | 101.95 | 101.95 | TB507 |  |  |  |  | Ahmed Construction | 1.54 | 1-2 | 3 | 1 | 3 | 8 | 101.95 | 101.95 | TB507
Ajay Kumar 1 | 1.14 | 1-2 | 0 | 0 | 0 | 3 | 41.02 | 41.02 | TB507 |  |  |  |  | Ajay Kumar 1 | 1.14 | 1-2 | 0 | 0 | 0 | 3 | 41.02 | 41.02 | TB507
Ayansh Const | 1.32 | 1-2 | 0 | 0 | 0 | 3 | 34.29 | 34.29 | TB507 |  |  |  |  | Ayansh Const | 1.32 | 1-2 | 0 | 0 | 0 | 3 | 34.29 | 34.29 | TB507
Bhairo Mahto Departmental | 1.18 | 1-2 | 0 | 0 | 0 | 3 | 121.76 | 121.76 | TB401 |  |  |  |  | Bhairo Mahto Departmental | 1.18 | 1-2 | 0 | 0 | 0 | 3 | 121.76 | 121.76 | TB401
Bhoi Enterprises | 1.99 | 1-2 | 2 | 1 | 2 | 19 | 253.31 | 253.31 | TB507 |  |  |  |  | Bhoi Enterprises | 1.99 | 1-2 | 2 | 1 | 2 | 19 | 253.31 | 253.31 | TB507
Chitra Construction | 1.95 | 1-2 | 9 | 2 | 4.5 | 3 | 150.21 | 150.21 | TA325, TA414 |  |  |  |  | Chitra Construction | 1.95 | 1-2 | 9 | 2 | 4.5 | 3 | 150.21 | 150.21 | TA325, TA414
Ganesh 2 | 1.87 | 1-2 | 4 | 1 | 4 | 4 | 196.68 | 196.68 | TA419 |  |  |  |  | Ganesh 2 | 1.87 | 1-2 | 4 | 1 | 4 | 4 | 196.68 | 196.68 | TA419
Gang 01 Sanjay | 1.63 | 1-2 | 16 | 5 | 3.2 | 30 | 968.84 | 968.84 | TA418 |  |  |  |  | Infinidea | 1.4 | 1-2 | 0 | 0 | 0 | 4 | 204.53 | 204.53 | TA419
Gang 02 Sanjay | 1.55 | 1-2 | 14 | 6 | 2.33 | 26 | 915.1 | 915.1 | TA418 |  |  |  |  | Kec 02 Barkat Ali | 1.26 | 1-2 | 0 | 0 | 0 | 19 | 671.06 | 682.9 | TA418
Infinidea | 1.4 | 1-2 | 0 | 0 | 0 | 4 | 204.53 | 204.53 | TA419 |  |  |  |  | M S Company Gang | 1.47 | 1-2 | 1 | 1 | 1 | 8 | 278.73 | 278.73 | TA512
Kec 02 Barkat Ali | 1.13 | 1-2 | 0 | 0 | 0 | 19 | 682.9 | 682.9 | TA418 |  |  |  |  | Mithun Kumar | 1.92 | 1-2 | 0 | 0 | 0 | 11 | 689.47 | 689.47 | TA325, TA414
Lakhan Singh | 1.64 | 1-2 | 0 | 0 | 0 | 3 | 14.73 | 14.73 | TB501 |  |  |  |  | Modina India | 1.94 | 1-2 | 3 | 2 | 1.5 | 5 | 314.69 | 322.23 | TA325
M S Company Gang | 1.47 | 1-2 | 1 | 1 | 1 | 7 | 278.73 | 258.96 | TA512 |  |  |  |  | Paramanand 1 | 1.82 | 1-2 | 0 | 0 | 0 | 9 | 357.37 | 357.37 | TA505
Paramanand 1 | 1.82 | 1-2 | 0 | 0 | 0 | 9 | 357.37 | 357.37 | TA505 |  |  |  |  | Pusplata Ashok | 1.68 | 1-2 | 3 | 1 | 3 | 6 | 266.13 | 266.13 | TB401, TB408
Punam Devi 3 | 1.26 | 1-2 | 0 | 0 | 0 | 16 | 643.35 | 643.35 | TA413 |  |  |  |  | Savitha | 1.67 | 1-2 | 14 | 3 | 4.67 | 3 | 102 | 102 | TA418
Pusplata Ashok | 1.68 | 1-2 | 3 | 1 | 3 | 6 | 266.13 | 266.13 | TB401, TB408 |  |  |  |  | Suman | 1.32 | 1-2 | 8 | 2 | 4 | 9 | 70 | 70 | TB501
Rabiul Hauq | 1.86 | 1-2 | 4 | 1 | 4 | 10 | 52.21 | 52.21 | TB501 |  |  |  |  | Vedanta Construction | 1.97 | 1-2 | 1 | 1 | 1 | 5 | 187.52 | 187.52 | TB408
Satyam Trivedi | 1.52 | 1-2 | 7 | 3 | 2.33 | 7 | 287.81 | 287.81 | TB401 |  |  |  |  | Anjum Construction | 2.49 | 2-3 | 3 | 1 | 3 | 3 | 156.8 | 156.8 | TA414
Savitha | 1.67 | 1-2 | 14 | 3 | 4.67 | 3 | 102 | 102 | TA418 |  |  |  |  | Bhairo Mahto | 2.37 | 2-3 | 2 | 2 | 1 | 7 | 267.9 | 267.9 | TB401, TB408
Suman | 1.32 | 1-2 | 8 | 2 | 4 | 9 | 70 | 70 | TB501 |  |  |  |  | Crane Erc Team Mp | 2.87 | 2-3 | 0 | 0 | 0 | 10 | 405.03 | 405.03 | TA505
Vedanta Construction | 1.97 | 1-2 | 1 | 1 | 1 | 5 | 187.52 | 187.52 | TB408 |  |  |  |  | Dipak | 2.8 | 2-3 | 6 | 4 | 1.5 | 31 | 483.64 | 483.64 | TB507
Anjum Construction | 2.49 | 2-3 | 3 | 1 | 3 | 3 | 156.8 | 156.8 | TA414 |  |  |  |  | Dk Verma | 2.14 | 2-3 | 9 | 2 | 4.5 | 8 | 654.56 | 723.65 | TA325
Bhairo Mahto | 2.37 | 2-3 | 2 | 2 | 1 | 7 | 267.9 | 267.9 | TB401, TB408 |  |  |  |  | Dudhnath Kumar | 2.72 | 2-3 | 44 | 12 | 3.67 | 31 | 234.14 | 234.14 | TB501
Bhuvneshwar | 2.99 | 2-3 | 8 | 3 | 2.67 | 4 | 152.7 | 152.7 | TB408 |  |  |  |  | Gokul Sarkar | 2.62 | 2-3 | 2 | 1 | 2 | 23 | 404.23 | 404.23 | TB507
Crane Erc Team Mp | 2.87 | 2-3 | 0 | 0 | 0 | 10 | 405.03 | 405.03 | TA505 |  |  |  |  | Infinidea 2 | 2.26 | 2-3 | 5 | 1 | 5 | 3 | 113 | 113 | TA419
Dipak | 2.8 | 2-3 | 6 | 4 | 1.5 | 31 | 483.64 | 483.64 | TB507 |  |  |  |  | Karam Mahto | 2.73 | 2-3 | 3 | 2 | 1.5 | 6 | 259 | 259 | TA504
Dudhnath Kumar | 2.51 | 2-3 | 55 | 18 | 3.06 | 51 | 346.53 | 346.53 | TB501 |  |  |  |  | Kec 01 Barkat Ali | 2.17 | 2-3 | 4 | 1 | 4 | 7 | 210.63 | 210.63 | TA418
Ghanshyam Mahto | 2.52 | 2-3 | 34 | 8 | 4.25 | 14 | 689.52 | 689.52 | TA325 |  |  |  |  | M K Infra | 2.21 | 2-3 | 8 | 1 | 8 | 4 | 176.85 | 176.85 | TA416
Gokul Sarkar | 2.62 | 2-3 | 2 | 1 | 2 | 23 | 404.23 | 404.23 | TB507 |  |  |  |  | M S Karni Construction 2 | 2.99 | 2-3 | 1 | 1 | 1 | 3 | 122.4 | 122.4 | TA512
Infinidea 2 | 2.26 | 2-3 | 5 | 1 | 5 | 3 | 113 | 113 | TA419 |  |  |  |  | Modina India 2 Pgcil | 2.31 | 2-3 | 18 | 3 | 6 | 3 | 131.61 | 131.61 | TA325
Intizer Infratech | 2.63 | 2-3 | 0 | 0 | 0 | 3 | 113.19 | 113.19 | TA325 |  |  |  |  | Nan | 2.51 | 2-3 | 0 | 0 | 0 | 5 | 350.7 | 350.7 | TA325
Karam Mahto | 2.73 | 2-3 | 3 | 2 | 1.5 | 6 | 259 | 259 | TA504 |  |  |  |  | Neha Const | 2.95 | 2-3 | 0 | 0 | 0 | 3 | 112 | 112 | TA504
Kaushalya Const | 2.61 | 2-3 | 15 | 3 | 5 | 3 | 158.98 | 158.98 | TB408 |  |  |  |  | Praveen | 2.07 | 2-3 | 23 | 6 | 3.83 | 12 | 499.85 | 511.34 | TA421
Kec 01 Barkat Ali | 2.17 | 2-3 | 4 | 1 | 4 | 7 | 210.63 | 210.63 | TA418 |  |  |  |  | Pritam Enterprises 4 | 2.82 | 2-3 | 8 | 2 | 4 | 6 | 262.62 | 262.62 | TA413
M K Infra | 2.45 | 2-3 | 8 | 1 | 8 | 5 | 222.9 | 222.9 | TA416 |  |  |  |  | Rames Kumar M | 2.8 | 2-3 | 29 | 3 | 9.67 | 8 | 53.16 | 53.16 | TB501
M S Karni Construction 2 | 2.99 | 2-3 | 1 | 1 | 1 | 3 | 122.4 | 122.4 | TA512 |  |  |  |  | Ramesh Kumar | 2.72 | 2-3 | 81 | 24 | 3.38 | 45 | 342.64 | 344.19 | TB501
Madhu Sah | 2.28 | 2-3 | 20 | 3 | 6.67 | 39 | 1743.13 | 1743.13 | TA419 |  |  |  |  | Ramesh Kumar M | 2.14 | 2-3 | 6 | 3 | 2 | 5 | 25.68 | 25.68 | TB501
Mithun Kumar | 2.25 | 2-3 | 29 | 8 | 3.62 | 21 | 1068.71 | 1068.71 | TA325, TA414 |  |  |  |  | Rupesh | 2.01 | 2-3 | 16 | 3 | 5.33 | 4 | 329.72 | 371.25 | TA325
Modina India | 2.38 | 2-3 | 18 | 6 | 3 | 16 | 790.55 | 790.55 | TA325 |  |  |  |  | Satyam Trivedi | 2.29 | 2-3 | 7 | 3 | 2.33 | 7 | 268.11 | 287.81 | TB401
Modina India 2 Pgcil | 2.31 | 2-3 | 18 | 3 | 6 | 3 | 131.61 | 131.61 | TA325 |  |  |  |  | Sk Samiul Sima Khatun | 2.94 | 2-3 | 0 | 0 | 0 | 3 | 135.38 | 135.38 | TA414
Nan | 2.51 | 2-3 | 0 | 0 | 0 | 5 | 350.7 | 350.7 | TA325 |  |  |  |  | Ab Construction | 3.71 | 3-4 | 1 | 1 | 1 | 4 | 89 | 89 | TA506
Neha Const | 2.95 | 2-3 | 0 | 0 | 0 | 3 | 112 | 112 | TA504 |  |  |  |  | Aloriva Global | 3.37 | 3-4 | 6 | 2 | 3 | 3 | 161.58 | 161.58 | TA416
Praveen | 2.26 | 2-3 | 34 | 10 | 3.4 | 23 | 936.22 | 936.22 | TA421 |  |  |  |  | Amar Kumar Singh | 3.33 | 3-4 | 3 | 1 | 3 | 4 | 223.06 | 223.06 | TA413
Pritam Enterprises 4 | 2.82 | 2-3 | 8 | 2 | 4 | 6 | 262.62 | 262.62 | TA413 |  |  |  |  | Amit Choudhury | 3.93 | 3-4 | 0 | 0 | 0 | 5 | 416.64 | 416.64 | TA416
Rafikul Islam | 2.81 | 2-3 | 0 | 0 | 0 | 8 | 325.5 | 325.5 | TB401, TB408 |  |  |  |  | Anil Construction | 3.84 | 3-4 | 1 | 1 | 1 | 18 | 411.02 | 411.02 | TA513
Rames Kumar M | 2.8 | 2-3 | 29 | 3 | 9.67 | 8 | 53.16 | 53.16 | TB501 |  |  |  |  | Barkat Ali | 3.24 | 3-4 | 4 | 1 | 4 | 7 | 233.38 | 276.42 | TA325
Ramesh Kumar | 2.54 | 2-3 | 88 | 29 | 3.03 | 95 | 632.21 | 632.21 | TB501 |  |  |  |  | Bhairo Mahato | 3 | 3-4 | 0 | 0 | 0 | 4 | 377.81 | 377.81 | TA419
Ramesh Kumar M | 2.14 | 2-3 | 6 | 3 | 2 | 5 | 25.68 | 25.68 | TB501 |  |  |  |  | Eagle Enterprises Paramand | 3.31 | 3-4 | 2 | 1 | 2 | 8 | 308.08 | 308.08 | TA505
Rupesh | 2.1 | 2-3 | 16 | 3 | 5.33 | 4 | 371.25 | 371.25 | TA325 |  |  |  |  | Ghyansham Mahto | 3.87 | 3-4 | 7 | 5 | 1.4 | 9 | 565 | 565 | TA504
Saidur Rahaman | 2.19 | 2-3 | 3 | 1 | 3 | 3 | 19.73 | 19.73 | TB501 |  |  |  |  | Govind Mahto | 3.98 | 3-4 | 29 | 11 | 2.64 | 17 | 418 | 418 | TA506
Senahul | 2.76 | 2-3 | 33 | 8 | 4.12 | 11 | 663.26 | 663.26 | TA325 |  |  |  |  | Hassan 2 | 3.81 | 3-4 | 0 | 0 | 0 | 3 | 141.08 | 141.08 | TA421
Shree Ganesh Sital Enterprice | 2.22 | 2-3 | 12 | 3 | 4 | 14 | 86.7 | 86.7 | TB501 |  |  |  |  | Jabir Hussian | 3.1 | 3-4 | 0 | 0 | 0 | 3 | 139.63 | 139.63 | TA414
Sk Samiul Sima Khatun | 2.94 | 2-3 | 0 | 0 | 0 | 3 | 135.38 | 135.38 | TA414 |  |  |  |  | Jhemon Mahato 2 | 3.61 | 3-4 | 0 | 0 | 0 | 9 | 444.32 | 444.32 | TA505
Ab Construction | 3.71 | 3-4 | 1 | 1 | 1 | 4 | 89 | 89 | TA506 |  |  |  |  | Kamlesh Kumar | 3.23 | 3-4 | 2 | 1 | 2 | 4 | 187.24 | 187.24 | TB408
Ajay Kumar | 3.77 | 3-4 | 6 | 4 | 1.5 | 11 | 644.96 | 644.96 | TA325, TB507 |  |  |  |  | Karni Const 1 | 3.86 | 3-4 | 26 | 5 | 5.2 | 12 | 266 | 266 | TA506
Aloriva Global | 3.37 | 3-4 | 6 | 2 | 3 | 3 | 161.58 | 161.58 | TA416 |  |  |  |  | Karni Const 5 | 3.86 | 3-4 | 21 | 3 | 7 | 8 | 220 | 220 | TA506
Amar Kumar Singh | 3.33 | 3-4 | 3 | 1 | 3 | 4 | 223.06 | 223.06 | TA413 |  |  |  |  | M S Kavya Enterprises | 3.59 | 3-4 | 15 | 4 | 3.75 | 12 | 502.74 | 486.91 | TA512
Amit Choudhury | 3.93 | 3-4 | 0 | 0 | 0 | 5 | 416.64 | 416.64 | TA416 |  |  |  |  | M S Mdpl | 3.34 | 3-4 | 3 | 3 | 1 | 12 | 534.3 | 534.3 | TA418
Anarul Haque | 3.81 | 3-4 | 3 | 2 | 1.5 | 3 | 247.89 | 247.89 | TA325 |  |  |  |  | Maa Construction | 3.85 | 3-4 | 4 | 2 | 2 | 3 | 215.64 | 254.1 | TA325, TA416
Anil Construction | 3.84 | 3-4 | 1 | 1 | 1 | 18 | 411.02 | 411.02 | TA513 |  |  |  |  | Mjr | 3.36 | 3-4 | 6 | 1 | 6 | 5 | 258.39 | 289.47 | TA325
Ashok | 3.44 | 3-4 | 8 | 2 | 4 | 4 | 165.33 | 165.33 | TA421 |  |  |  |  | Modina India 3 Pgcil | 3.76 | 3-4 | 14 | 4 | 3.5 | 4 | 157.92 | 157.92 | TA325
Barkat Ali | 3 | 3-4 | 16 | 6 | 2.67 | 16 | 731.12 | 731.12 | TA325 |  |  |  |  | Mohan Mahto | 3.91 | 3-4 | 0 | 0 | 0 | 4 | 125 | 125 | TA506
Bhairo Mahato | 3 | 3-4 | 0 | 0 | 0 | 4 | 377.81 | 377.81 | TA419 |  |  |  |  | Pankaj 1 | 3.69 | 3-4 | 2 | 1 | 2 | 4 | 118 | 118 | TA506
Bina Devi | 3.86 | 3-4 | 25 | 7 | 3.57 | 17 | 691.22 | 691.22 | TB401, TB408 |  |  |  |  | Pankaj Const | 3.89 | 3-4 | 0 | 0 | 0 | 4 | 105 | 105 | TA506
Daulat Mahto | 3.74 | 3-4 | 31 | 12 | 2.58 | 13 | 594.05 | 594.05 | TA325 |  |  |  |  | Pc 2 | 3.54 | 3-4 | 0 | 0 | 0 | 3 | 279.55 | 279.55 | TA325
Departmental Gang | 3.17 | 3-4 | 1 | 1 | 1 | 6 | 250.09 | 250.09 | TB401 |  |  |  |  | Prayag Mahto | 3.57 | 3-4 | 16 | 2 | 8 | 4 | 303.61 | 303.61 | TA325, TA414
Dk Verma | 3.11 | 3-4 | 17 | 6 | 2.83 | 21 | 1534.65 | 1534.65 | TA325 |  |  |  |  | Prayag Saw | 3.33 | 3-4 | 5 | 3 | 1.67 | 12 | 190.05 | 190.05 | TB507
Eagle Enterprises | 3.83 | 3-4 | 0 | 0 | 0 | 3 | 114.75 | 114.75 | TA505 |  |  |  |  | Prayag Saw 1 | 3.38 | 3-4 | 0 | 0 | 0 | 14 | 216.25 | 216.25 | TB507
Eagle Enterprises Paramand | 3.31 | 3-4 | 2 | 1 | 2 | 8 | 308.08 | 308.08 | TA505 |  |  |  |  | Prayag Saw 2 | 3.21 | 3-4 | 4 | 2 | 2 | 22 | 340.35 | 340.35 | TB507
Ganesh | 3.88 | 3-4 | 0 | 0 | 0 | 4 | 209.51 | 209.51 | TA419, TB408 |  |  |  |  | Prayag Shah Mp | 3.49 | 3-4 | 2 | 2 | 1 | 8 | 338.68 | 338.68 | TA505
Ghyansham Mahto | 3.87 | 3-4 | 7 | 5 | 1.4 | 9 | 565 | 565 | TA504 |  |  |  |  | Pritam Enterprises | 3.27 | 3-4 | 0 | 0 | 0 | 16 | 287.38 | 287.38 | TA413, TB507
Govind Mahto | 3.98 | 3-4 | 29 | 11 | 2.64 | 17 | 418 | 418 | TA506 |  |  |  |  | Pritam Enterprises 1 | 3.37 | 3-4 | 12 | 4 | 3 | 9 | 390.73 | 390.73 | TA413
Hassan 2 | 3.81 | 3-4 | 0 | 0 | 0 | 3 | 141.08 | 141.08 | TA421 |  |  |  |  | Pritam Enterprises 2 | 3.37 | 3-4 | 4 | 1 | 4 | 13 | 619.68 | 619.68 | TA413
J Lngh O 2 | 3.16 | 3-4 | 0 | 0 | 0 | 5 | 186.53 | 186.53 | TA421 |  |  |  |  | Priyanka Devi Subodh | 3.71 | 3-4 | 0 | 0 | 0 | 4 | 181.58 | 181.58 | TB401, TB408
Jabir Hussian | 3.1 | 3-4 | 0 | 0 | 0 | 3 | 139.63 | 139.63 | TA414 |  |  |  |  | Punam Kumari 3 | 3.88 | 3-4 | 0 | 0 | 0 | 5 | 337.85 | 337.85 | TA413, TA416
Jhemon Mahato 2 | 3.61 | 3-4 | 0 | 0 | 0 | 9 | 444.32 | 444.32 | TA505 |  |  |  |  | Raju Kumar | 3.68 | 3-4 | 0 | 0 | 0 | 4 | 235.29 | 235.29 | TA419
Kamlesh Kumar | 3.23 | 3-4 | 2 | 1 | 2 | 4 | 187.24 | 187.24 | TB408 |  |  |  |  | Ranjan Kumar | 3.2 | 3-4 | 0 | 0 | 0 | 4 | 208.18 | 208.18 | TA325, TA414
Karni Const 1 | 3.86 | 3-4 | 26 | 5 | 5.2 | 12 | 266 | 266 | TA506 |  |  |  |  | Rohit | 3.57 | 3-4 | 0 | 0 | 0 | 4 | 224.93 | 224.93 | TA419
Karni Const 5 | 3.86 | 3-4 | 21 | 3 | 7 | 8 | 220 | 220 | TA506 |  |  |  |  | Rudra Construction | 3.78 | 3-4 | 8 | 2 | 4 | 3 | 132.2 | 132.2 | TA416
M S Kavya Enterprises | 3.59 | 3-4 | 15 | 4 | 3.75 | 13 | 502.74 | 502.74 | TA512 |  |  |  |  | Sainik Trader | 3.33 | 3-4 | 1 | 1 | 1 | 3 | 236.3 | 236.3 | TA416
M S Mdpl | 3.34 | 3-4 | 3 | 3 | 1 | 12 | 534.3 | 534.3 | TA418 |  |  |  |  | Sainik Traders | 3.91 | 3-4 | 12 | 8 | 1.5 | 16 | 704 | 704 | TA504, TA506
Maa Const | 3.45 | 3-4 | 1 | 1 | 1 | 7 | 276 | 276 | TA421 |  |  |  |  | Satyam Trading | 3.97 | 3-4 | 2 | 1 | 2 | 7 | 313.36 | 313.36 | TA419
Mjr | 3.8 | 3-4 | 25 | 9 | 2.78 | 13 | 710.38 | 710.38 | TA325 |  |  |  |  | Sheetal Singh | 3.55 | 3-4 | 2 | 1 | 2 | 4 | 188.15 | 188.15 | TB408
Modina India 3 Pgcil | 3.76 | 3-4 | 14 | 4 | 3.5 | 4 | 157.92 | 157.92 | TA325 |  |  |  |  | Sk Samiul 1 | 3.5 | 3-4 | 7 | 3 | 2.33 | 7 | 321.96 | 321.96 | TA413
Mohan Mahto | 3.91 | 3-4 | 0 | 0 | 0 | 4 | 125 | 125 | TA506 |  |  |  |  | Sk Samiul 2 | 3.23 | 3-4 | 0 | 0 | 0 | 4 | 145.46 | 145.46 | TA413
Pankaj 1 | 3.69 | 3-4 | 2 | 1 | 2 | 4 | 118 | 118 | TA506 |  |  |  |  | Sk Samuil | 3.82 | 3-4 | 0 | 0 | 0 | 7 | 252.04 | 294.8 | TA325
Pankaj Const | 3.89 | 3-4 | 0 | 0 | 0 | 4 | 105 | 105 | TA506 |  |  |  |  | Sukruddin | 3.97 | 3-4 | 6 | 1 | 6 | 4 | 380.67 | 380.67 | TA325
Pc 2 | 3.54 | 3-4 | 0 | 0 | 0 | 3 | 279.55 | 279.55 | TA325 |  |  |  |  | Sulen Sarkar | 3.63 | 3-4 | 10 | 1 | 10 | 4 | 159.81 | 159.81 | TA325
Prayag Mahto | 3.57 | 3-4 | 16 | 2 | 8 | 4 | 303.61 | 303.61 | TA325, TA414 |  |  |  |  | Tejal | 3.19 | 3-4 | 9 | 2 | 4.5 | 4 | 83 | 83 | TA506
Prayag Saw | 3.33 | 3-4 | 5 | 3 | 1.67 | 12 | 190.05 | 190.05 | TB507 |  |  |  |  | Toshan Mahato | 3.71 | 3-4 | 1 | 1 | 1 | 9 | 582.83 | 582.83 | TA505
Prayag Saw 1 | 3.38 | 3-4 | 0 | 0 | 0 | 14 | 216.25 | 216.25 | TB507 |  |  |  |  | Usha Tower | 3.38 | 3-4 | 6 | 3 | 2 | 5 | 199.46 | 199.46 | TB401, TB408
Prayag Saw 2 | 3.21 | 3-4 | 4 | 2 | 2 | 22 | 340.35 | 340.35 | TB507 |  |  |  |  | Vinay Const | 3.81 | 3-4 | 4 | 2 | 2 | 3 | 133.22 | 133.22 | TB401
Prayag Shah Mp | 3.49 | 3-4 | 2 | 2 | 1 | 8 | 338.68 | 338.68 | TA505 |  |  |  |  | Vinay Construction | 3.22 | 3-4 | 3 | 2 | 1.5 | 12 | 453.82 | 453.82 | TB408, TB507
Pritam Enterprises | 3.27 | 3-4 | 0 | 0 | 0 | 16 | 287.38 | 287.38 | TA413, TB507 |  |  |  |  | Vivek Ganju | 3.61 | 3-4 | 7 | 5 | 1.4 | 10 | 389.67 | 389.67 | TB401, TB408
Pritam Enterprises 1 | 3.37 | 3-4 | 12 | 4 | 3 | 9 | 390.73 | 390.73 | TA413 |  |  |  |  | Ab Const | 4.07 | 4-5 | 46 | 6 | 7.67 | 10 | 277 | 277 | TA506
Pritam Enterprises 2 | 3.37 | 3-4 | 4 | 1 | 4 | 13 | 619.68 | 619.68 | TA413 |  |  |  |  | Amit Const | 4.85 | 4-5 | 1 | 1 | 1 | 3 | 145.42 | 145.42 | TA416
Priyanka Devi Subodh | 3.71 | 3-4 | 0 | 0 | 0 | 4 | 181.58 | 181.58 | TB401, TB408 |  |  |  |  | Amit Kumar Singh | 4.38 | 4-5 | 1 | 1 | 1 | 8 | 354.72 | 354.72 | TA413
Punam Kumari | 3.84 | 3-4 | 2 | 1 | 2 | 9 | 490.89 | 490.89 | TA413, TA416, TA419 |  |  |  |  | Bhairaw Mahto | 4.31 | 4-5 | 7 | 1 | 7 | 5 | 318.65 | 318.65 | TA413
Punam Kumari 3 | 3.88 | 3-4 | 0 | 0 | 0 | 5 | 337.85 | 337.85 | TA413, TA416 |  |  |  |  | Binod Mahto | 4.29 | 4-5 | 31 | 8 | 3.88 | 10 | 313 | 313 | TA506
Rahim Khan | 3.22 | 3-4 | 10 | 5 | 2 | 13 | 588.7 | 588.7 | TA325 |  |  |  |  | Deglal Mahato Mp | 4.73 | 4-5 | 0 | 0 | 0 | 18 | 705.06 | 705.06 | TA505
Raju Kumar | 3.68 | 3-4 | 0 | 0 | 0 | 4 | 235.29 | 235.29 | TA419 |  |  |  |  | Gagan Enterprises | 4.44 | 4-5 | 0 | 0 | 0 | 4 | 195.3 | 197.89 | TA419
Ranjan Kumar | 3.2 | 3-4 | 0 | 0 | 0 | 4 | 208.18 | 208.18 | TA325, TA414 |  |  |  |  | Ganesh Sinha | 4.96 | 4-5 | 14 | 3 | 4.67 | 17 | 768.63 | 768.63 | TB401, TB408
Rohit | 3.57 | 3-4 | 0 | 0 | 0 | 4 | 224.93 | 224.93 | TA419 |  |  |  |  | Gang 01 Sanjay | 4.28 | 4-5 | 15 | 4 | 3.75 | 8 | 291 | 291 | TA418
S K Janarul Sheikh | 3.52 | 3-4 | 5 | 2 | 2.5 | 3 | 109.11 | 109.11 | TA421 |  |  |  |  | Gang 02 Sanjay | 4.3 | 4-5 | 14 | 6 | 2.33 | 14 | 481.23 | 503.63 | TA418
Sainik Trader | 3.33 | 3-4 | 1 | 1 | 1 | 3 | 236.3 | 236.3 | TA416 |  |  |  |  | Gokul Sarkar 1 | 4.15 | 4-5 | 5 | 1 | 5 | 3 | 120.23 | 120.23 | TA325
Sainik Traders | 3.91 | 3-4 | 12 | 8 | 1.5 | 16 | 704 | 704 | TA504, TA506 |  |  |  |  | Gokul Sarkar Mp | 4.77 | 4-5 | 2 | 2 | 1 | 9 | 391.06 | 391.06 | TA505
Satyam Trading | 3.97 | 3-4 | 2 | 1 | 2 | 7 | 313.36 | 313.36 | TA419 |  |  |  |  | Gokul Sarkar Mp 2 | 4.37 | 4-5 | 0 | 0 | 0 | 7 | 275.49 | 275.49 | TA505
Sheetal Singh | 3.55 | 3-4 | 2 | 1 | 2 | 4 | 188.15 | 188.15 | TB408 |  |  |  |  | Govind Mahto 1 | 4.48 | 4-5 | 11 | 4 | 2.75 | 12 | 515.57 | 515.57 | TA413
Sk Samiul 1 | 3.5 | 3-4 | 7 | 3 | 2.33 | 7 | 321.96 | 321.96 | TA413 |  |  |  |  | Govind Mahto 2 | 4.93 | 4-5 | 4 | 1 | 4 | 9 | 522.54 | 522.54 | TA413
Sk Samiul 2 | 3.23 | 3-4 | 0 | 0 | 0 | 4 | 145.46 | 145.46 | TA413 |  |  |  |  | Gulab Mahto | 4.83 | 4-5 | 0 | 0 | 0 | 9 | 169 | 169 | TA506
Sk Samuil | 3.18 | 3-4 | 11 | 4 | 2.75 | 23 | 937.56 | 937.56 | TA325 |  |  |  |  | Hassan | 4.22 | 4-5 | 9 | 4 | 2.25 | 18 | 890.28 | 890.28 | TA421
Sukhriddin | 3.14 | 3-4 | 33 | 12 | 2.75 | 16 | 869.03 | 869.03 | TA325 |  |  |  |  | Horel Mahto | 4.69 | 4-5 | 3 | 1 | 3 | 3 | 136 | 136 | TA504
Sukruddin | 3.97 | 3-4 | 6 | 1 | 6 | 4 | 380.67 | 380.67 | TA325 |  |  |  |  | Horil Mahto | 4.7 | 4-5 | 16 | 4 | 4 | 20 | 555.05 | 555.05 | TA416, TA506
Sulen Sarkar | 3.64 | 3-4 | 16 | 3 | 5.33 | 7 | 276.46 | 276.46 | TA325 |  |  |  |  | Jagannaath Saw Mp | 4.82 | 4-5 | 0 | 0 | 0 | 16 | 694.61 | 694.61 | TA505
Tejal | 3.19 | 3-4 | 9 | 2 | 4.5 | 4 | 83 | 83 | TA506 |  |  |  |  | Jai Prakash Mahto | 4.72 | 4-5 | 23 | 7 | 3.29 | 16 | 458 | 458 | TA506
Thanu Mahto | 3.48 | 3-4 | 15 | 6 | 2.5 | 14 | 668.09 | 668.09 | TA325 |  |  |  |  | Jay Prakash | 4.76 | 4-5 | 2 | 1 | 2 | 3 | 100 | 100 | TA506
Toshan Mahato | 3.71 | 3-4 | 1 | 1 | 1 | 9 | 582.83 | 582.83 | TA505 |  |  |  |  | Jirwa Devi | 4.59 | 4-5 | 14 | 4 | 3.5 | 13 | 619.08 | 619.08 | TB401, TB408
Usha Tower | 3.38 | 3-4 | 6 | 3 | 2 | 5 | 199.46 | 199.46 | TB401, TB408 |  |  |  |  | Jwala Singh 1 | 4.11 | 4-5 | 15 | 4 | 3.75 | 27 | 1171.67 | 1171.67 | TA413, TB401, TB408
Vasu Dev Singh 1 | 3.34 | 3-4 | 0 | 0 | 0 | 10 | 431.24 | 431.24 | TA413 |  |  |  |  | Jyoti Const | 4.04 | 4-5 | 0 | 0 | 0 | 12 | 671.2 | 671.2 | TA505
Vasu Dev Singh 2 | 3.67 | 3-4 | 9 | 1 | 9 | 12 | 521.26 | 521.26 | TA413 |  |  |  |  | Karni Const 2 | 4.73 | 4-5 | 28 | 9 | 3.11 | 13 | 369 | 369 | TA506
Vinay Const | 3.81 | 3-4 | 4 | 2 | 2 | 3 | 133.22 | 133.22 | TB401 |  |  |  |  | Karni Const 3 | 4.67 | 4-5 | 17 | 7 | 2.43 | 12 | 322 | 322 | TA506
Vinay Construction | 3.22 | 3-4 | 3 | 2 | 1.5 | 12 | 453.82 | 453.82 | TB408, TB507 |  |  |  |  | Karni Const 4 | 4.7 | 4-5 | 15 | 6 | 2.5 | 11 | 324 | 324 | TA506
Vivek Ganju | 3.61 | 3-4 | 7 | 5 | 1.4 | 10 | 389.67 | 389.67 | TB401, TB408 |  |  |  |  | Karni Const 6 | 4.17 | 4-5 | 2 | 1 | 2 | 6 | 121 | 121 | TA506
Ab Const | 4.07 | 4-5 | 46 | 6 | 7.67 | 10 | 277 | 277 | TA506 |  |  |  |  | Kartik Mahto | 4.31 | 4-5 | 0 | 0 | 0 | 5 | 241.46 | 241.46 | TA413
Amit Const | 4.85 | 4-5 | 1 | 1 | 1 | 3 | 145.42 | 145.42 | TA416 |  |  |  |  | Khemlal | 4.56 | 4-5 | 0 | 0 | 0 | 4 | 82 | 82 | TA506
Amit Kumar Singh | 4.38 | 4-5 | 1 | 1 | 1 | 8 | 354.72 | 354.72 | TA413 |  |  |  |  | Khemlal Mahto | 4.31 | 4-5 | 40 | 10 | 4 | 17 | 418 | 418 | TA506
Bhagwan Construction | 4.51 | 4-5 | 0 | 0 | 0 | 7 | 279.72 | 279.72 | TA413 |  |  |  |  | Kongres Kumar 1 | 4.56 | 4-5 | 0 | 0 | 0 | 3 | 365.08 | 365.08 | TA416
Bhairaw Mahto | 4.31 | 4-5 | 7 | 1 | 7 | 5 | 318.65 | 318.65 | TA413 |  |  |  |  | M S Govind Mahto 2 | 4.44 | 4-5 | 1 | 1 | 1 | 6 | 271.01 | 271.01 | TA512
Binod Mahto | 4.29 | 4-5 | 31 | 8 | 3.88 | 10 | 313 | 313 | TA506 |  |  |  |  | M S Punam Kumari | 4.77 | 4-5 | 0 | 0 | 0 | 15 | 577.73 | 577.73 | TA512
Deglal Mahato Mp | 4.73 | 4-5 | 0 | 0 | 0 | 18 | 705.06 | 705.06 | TA505 |  |  |  |  | M S Punam Kumari 3 | 4.08 | 4-5 | 3 | 3 | 1 | 8 | 305.78 | 305.78 | TA512
Gagan Enterprises | 4.4 | 4-5 | 0 | 0 | 0 | 4 | 197.89 | 197.89 | TA419 |  |  |  |  | M S Punam Kumari 4 | 4.75 | 4-5 | 5 | 2 | 2.5 | 7 | 313.44 | 313.44 | TA512
Ganesh Kr Sinha | 4.34 | 4-5 | 9 | 3 | 3 | 23 | 1088.25 | 1088.25 | TB401 |  |  |  |  | M S Rahul | 4.62 | 4-5 | 2 | 2 | 1 | 3 | 120.19 | 120.19 | TA414
Ganesh Sinha | 4.53 | 4-5 | 16 | 5 | 3.2 | 30 | 1313.9 | 1313.9 | TB401, TB408 |  |  |  |  | M S Sakkurddin | 4.13 | 4-5 | 15 | 4 | 3.75 | 4 | 165.12 | 165.12 | TA414
Gokul Rajwanshi | 4.61 | 4-5 | 6 | 4 | 1.5 | 23 | 940.12 | 940.12 | TA505 |  |  |  |  | M S Tofit | 4.48 | 4-5 | 11 | 5 | 2.2 | 15 | 631.3 | 631.3 | TA418
Gokul Sarkar 1 | 4.15 | 4-5 | 5 | 1 | 5 | 3 | 120.23 | 120.23 | TA325 |  |  |  |  | Madhu Sah | 4.07 | 4-5 | 5 | 2 | 2.5 | 23 | 1103.81 | 1119.03 | TA419
Gokul Sarkar Mp | 4.77 | 4-5 | 2 | 2 | 1 | 9 | 391.06 | 391.06 | TA505 |  |  |  |  | Mahon Mahto | 4.2 | 4-5 | 0 | 0 | 0 | 5 | 625.48 | 625.48 | TA416
Gokul Sarkar Mp 2 | 4.37 | 4-5 | 0 | 0 | 0 | 7 | 275.49 | 275.49 | TA505 |  |  |  |  | Naziruddin | 4.86 | 4-5 | 0 | 0 | 0 | 11 | 461.81 | 461.81 | TA421
Govind Mahto 1 | 4.48 | 4-5 | 11 | 4 | 2.75 | 12 | 515.57 | 515.57 | TA413 |  |  |  |  | Nirmal Mahto | 4 | 4-5 | 2 | 1 | 2 | 14 | 643.72 | 643.72 | TB401, TB408
Govind Mahto 2 | 4.93 | 4-5 | 4 | 1 | 4 | 9 | 522.54 | 522.54 | TA413 |  |  |  |  | Pankaj Kumar | 4.56 | 4-5 | 0 | 0 | 0 | 6 | 615.75 | 615.75 | TA416
Gulab Mahto | 4.83 | 4-5 | 0 | 0 | 0 | 9 | 169 | 169 | TA506 |  |  |  |  | Panva Devi | 4.19 | 4-5 | 2 | 1 | 2 | 5 | 339.27 | 339.27 | TB401, TB408
Hassan | 4.22 | 4-5 | 9 | 4 | 2.25 | 18 | 890.28 | 890.28 | TA421 |  |  |  |  | Poornam Kumari | 4.26 | 4-5 | 0 | 0 | 0 | 4 | 157.67 | 177.4 | TA419
Horel Mahto | 4.69 | 4-5 | 3 | 1 | 3 | 3 | 136 | 136 | TA504 |  |  |  |  | Prem Kumar | 4.45 | 4-5 | 34 | 9 | 3.78 | 8 | 294 | 294 | TA506
Horil Mahto | 4.32 | 4-5 | 29 | 10 | 2.9 | 37 | 1347.95 | 1347.95 | TA416, TA506 |  |  |  |  | Priyanka Devi | 4.01 | 4-5 | 10 | 2 | 5 | 6 | 256.59 | 256.59 | TB401, TB408
Jagannaath Saw Mp | 4.82 | 4-5 | 0 | 0 | 0 | 16 | 694.61 | 694.61 | TA505 |  |  |  |  | Punam Devi 1 | 4.31 | 4-5 | 0 | 0 | 0 | 3 | 138.01 | 145.97 | TA413
Jai Prakash Mahto | 4.72 | 4-5 | 23 | 7 | 3.29 | 16 | 458 | 458 | TA506 |  |  |  |  | Punam Devi 2 | 4.52 | 4-5 | 0 | 0 | 0 | 3 | 144.72 | 148.52 | TA413
Jay Prakash | 4.76 | 4-5 | 2 | 1 | 2 | 3 | 100 | 100 | TA506 |  |  |  |  | Punam Kumari | 4.29 | 4-5 | 2 | 1 | 2 | 8 | 454.73 | 454.73 | TA413, TA416
Jirwa Devi | 4.18 | 4-5 | 22 | 7 | 3.14 | 28 | 1317.03 | 1317.03 | TB401, TB408 |  |  |  |  | Punam Kumari 1 | 4.48 | 4-5 | 2 | 1 | 2 | 30 | 1597.76 | 1597.76 | TA413, TA416, TA419, TA504
Jwala Singh 1 | 4.11 | 4-5 | 15 | 4 | 3.75 | 27 | 1171.67 | 1171.67 | TA413, TB401, TB408 |  |  |  |  | Punam Kumari 4 | 4.82 | 4-5 | 0 | 0 | 0 | 5 | 226.69 | 226.69 | TA413, TA419
Jyoti Const | 4.04 | 4-5 | 0 | 0 | 0 | 12 | 671.2 | 671.2 | TA505 |  |  |  |  | Pusplata 7 | 4.66 | 4-5 | 0 | 0 | 0 | 3 | 116.54 | 116.54 | TB401
Karni Const 2 | 4.73 | 4-5 | 28 | 9 | 3.11 | 13 | 369 | 369 | TA506 |  |  |  |  | Pusplata Dharamveer | 4.48 | 4-5 | 1 | 1 | 1 | 3 | 152.41 | 152.41 | TB401, TB408
Karni Const 3 | 4.67 | 4-5 | 17 | 7 | 2.43 | 12 | 322 | 322 | TA506 |  |  |  |  | Pusplata Rajaram | 4.87 | 4-5 | 0 | 0 | 0 | 3 | 185.01 | 185.01 | TB401, TB408
Karni Const 4 | 4.7 | 4-5 | 15 | 6 | 2.5 | 11 | 324 | 324 | TA506 |  |  |  |  | Rahim Khan | 4.76 | 4-5 | 8 | 4 | 2 | 6 | 242.92 | 267.91 | TA325
Karni Const 6 | 4.17 | 4-5 | 2 | 1 | 2 | 6 | 121 | 121 | TA506 |  |  |  |  | Reeta Bharti | 4.61 | 4-5 | 6 | 2 | 3 | 13 | 857.54 | 876.99 | TA416
Kartik Mahto | 4.31 | 4-5 | 0 | 0 | 0 | 5 | 241.46 | 241.46 | TA413 |  |  |  |  | Sanjeet | 4.36 | 4-5 | 5 | 4 | 1.25 | 5 | 305.35 | 305.35 | TA419
Khatan | 4.93 | 4-5 | 8 | 3 | 2.67 | 17 | 621.41 | 621.41 | TA421 |  |  |  |  | Sanjeev Kumar | 4.46 | 4-5 | 1 | 1 | 1 | 9 | 459.26 | 459.26 | TB401, TB408
Khemlal | 4.56 | 4-5 | 0 | 0 | 0 | 4 | 82 | 82 | TA506 |  |  |  |  | Satyam Enterprises Vijay | 4.67 | 4-5 | 0 | 0 | 0 | 4 | 154.05 | 154.05 | TB408
Khemlal Mahto | 4.31 | 4-5 | 40 | 10 | 4 | 17 | 418 | 418 | TA506 |  |  |  |  | Satyam Vijay | 4.88 | 4-5 | 7 | 3 | 2.33 | 9 | 376.1 | 376.1 | TB401
Kongres Kumar 1 | 4.56 | 4-5 | 0 | 0 | 0 | 3 | 365.08 | 365.08 | TA416 |  |  |  |  | Shri Karni Construction | 4.1 | 4-5 | 0 | 0 | 0 | 33 | 725 | 725 | TA506
M S Govind Mahto 2 | 4.44 | 4-5 | 1 | 1 | 1 | 6 | 271.01 | 271.01 | TA512 |  |  |  |  | Sital Singh | 4.57 | 4-5 | 0 | 0 | 0 | 3 | 132.61 | 132.6 | TB401
M S Punam Kumari | 4.77 | 4-5 | 0 | 0 | 0 | 15 | 577.73 | 577.73 | TA512 |  |  |  |  | Sital Singh 1 | 4.63 | 4-5 | 0 | 0 | 0 | 5 | 231.74 | 231.74 | TB401
M S Punam Kumari 3 | 4.08 | 4-5 | 3 | 3 | 1 | 8 | 305.78 | 305.78 | TA512 |  |  |  |  | Amar Singh | 5.3 | 5-6 | 12 | 4 | 3 | 11 | 545.93 | 545.93 | TA416
M S Punam Kumari 4 | 4.75 | 4-5 | 5 | 2 | 2.5 | 7 | 313.44 | 313.44 | TA512 |  |  |  |  | Anita Devi | 5.33 | 5-6 | 4 | 2 | 2 | 3 | 298.41 | 298.41 | TA325
M S Rahul | 4.62 | 4-5 | 2 | 2 | 1 | 3 | 120.19 | 120.19 | TA414 |  |  |  |  | Arawali 2 | 5.18 | 5-6 | 0 | 0 | 0 | 3 | 113.86 | 113.86 | TB408
M S Sakkurddin | 4.13 | 4-5 | 15 | 4 | 3.75 | 4 | 165.12 | 165.12 | TA414 |  |  |  |  | Arawali Infra 2 | 5.23 | 5-6 | 12 | 4 | 3 | 4 | 230.2 | 230.2 | TB401
M S Tofit | 4.48 | 4-5 | 11 | 5 | 2.2 | 15 | 631.3 | 631.3 | TA418 |  |  |  |  | Asc Heights | 5.5 | 5-6 | 7 | 3 | 2.33 | 8 | 489.8 | 489.8 | TA416
Maa Construction | 4.01 | 4-5 | 15 | 8 | 1.88 | 12 | 750.69 | 750.69 | TA325, TA416 |  |  |  |  | Chinta Devi | 5.97 | 5-6 | 10 | 5 | 2 | 27 | 1426.44 | 1434.21 | TB401, TB408
Mahon Mahto | 4.2 | 4-5 | 0 | 0 | 0 | 5 | 625.48 | 625.48 | TA416 |  |  |  |  | D K Verma | 5.94 | 5-6 | 17 | 6 | 2.83 | 22 | 956.69 | 956.69 | TA421
Naziruddin | 4.86 | 4-5 | 0 | 0 | 0 | 11 | 461.81 | 461.81 | TA421 |  |  |  |  | Devi Construction | 5.93 | 5-6 | 5 | 3 | 1.67 | 7 | 468.81 | 468.81 | TB401, TB408
Nirmal Mahto | 4.57 | 4-5 | 11 | 5 | 2.2 | 25 | 1119.41 | 1119.41 | TB401, TB408 |  |  |  |  | Fouzi Ratto | 5.04 | 5-6 | 2 | 1 | 2 | 12 | 669.87 | 669.87 | TA413
Pankaj Kumar | 4.56 | 4-5 | 0 | 0 | 0 | 6 | 615.75 | 615.75 | TA416 |  |  |  |  | Gagan Enterprise 2 | 5.99 | 5-6 | 5 | 2 | 2.5 | 5 | 281.66 | 281.66 | TA416
Panva Devi | 4.19 | 4-5 | 2 | 1 | 2 | 5 | 339.27 | 339.27 | TB401, TB408 |  |  |  |  | Gokul Rajwanshi | 5.03 | 5-6 | 6 | 4 | 1.5 | 22 | 900.46 | 905.33 | TA505
Pinki Devi | 4.6 | 4-5 | 4 | 1 | 4 | 14 | 671.99 | 671.99 | TA413, TA419, TA504 |  |  |  |  | Gokul Sarkar 2 | 5.66 | 5-6 | 7 | 4 | 1.75 | 4 | 266.18 | 266.18 | TA325
Poonam Kumari | 4.04 | 4-5 | 0 | 0 | 0 | 18 | 837.21 | 837.21 | TA325, TA419 |  |  |  |  | Horil | 5.3 | 5-6 | 0 | 0 | 0 | 5 | 122 | 122 | TA506
Poornam Kumari | 4.13 | 4-5 | 0 | 0 | 0 | 4 | 177.4 | 177.4 | TA419 |  |  |  |  | J Lngh O 1 | 5.86 | 5-6 | 1 | 1 | 1 | 5 | 199.14 | 214.73 | TA421
Prem Kumar | 4.45 | 4-5 | 34 | 9 | 3.78 | 8 | 294 | 294 | TA506 |  |  |  |  | J Lngh O 2 | 5.12 | 5-6 | 0 | 0 | 0 | 4 | 138.21 | 148.6 | TA421
Priyanka Devi | 4.01 | 4-5 | 10 | 2 | 5 | 6 | 256.59 | 256.59 | TB401, TB408 |  |  |  |  | Jaman Mahto 1 Ratna Devi | 5.12 | 5-6 | 5 | 2 | 2.5 | 4 | 394.41 | 394.41 | TA325
Punam Kumari 1 | 4.48 | 4-5 | 2 | 1 | 2 | 30 | 1597.76 | 1597.76 | TA413, TA416, TA419, TA504 |  |  |  |  | Jhemon Mahato 1 | 5.97 | 5-6 | 0 | 0 | 0 | 7 | 483.28 | 483.28 | TA505
Punam Kumari 4 | 4.82 | 4-5 | 0 | 0 | 0 | 5 | 226.69 | 226.69 | TA413, TA419 |  |  |  |  | Jwala Singh 2 | 5.82 | 5-6 | 28 | 7 | 4 | 42 | 1779.96 | 1789.44 | TA413, TA505, TB401, TB408
Pusplata 7 | 4.66 | 4-5 | 0 | 0 | 0 | 3 | 116.54 | 116.54 | TB401 |  |  |  |  | M S Govind Mahto | 5.91 | 5-6 | 0 | 0 | 0 | 4 | 165.36 | 165.36 | TA512
Pusplata Dharamveer | 4.48 | 4-5 | 1 | 1 | 1 | 3 | 152.41 | 152.41 | TB401, TB408 |  |  |  |  | M S Jwala Singh | 5.26 | 5-6 | 6 | 6 | 1 | 21 | 898.64 | 898.64 | TA512
Pusplata Rajaram | 4.87 | 4-5 | 0 | 0 | 0 | 3 | 185.01 | 185.01 | TB401, TB408 |  |  |  |  | M S Jwala Singh 2 | 5.24 | 5-6 | 9 | 2 | 4.5 | 10 | 408.59 | 408.59 | TA512
Reeta Bharti | 4.93 | 4-5 | 12 | 5 | 2.4 | 29 | 1648.09 | 1648.09 | TA416 |  |  |  |  | M S Raju Kumar | 5.06 | 5-6 | 0 | 0 | 0 | 5 | 202.36 | 202.36 | TA512
Rudra Construction | 4.08 | 4-5 | 16 | 5 | 3.2 | 7 | 314.12 | 314.12 | TA416 |  |  |  |  | M S Sunny Construction | 5.63 | 5-6 | 0 | 0 | 0 | 3 | 140.8 | 140.8 | TA512
Sanjeet | 4.36 | 4-5 | 5 | 4 | 1.25 | 5 | 305.35 | 305.35 | TA419 |  |  |  |  | Md Akhtar | 5.19 | 5-6 | 8 | 2 | 4 | 4 | 409.72 | 409.72 | TA325
Sanjeev Kumar | 4.38 | 4-5 | 21 | 7 | 3 | 25 | 1168.76 | 1168.76 | TB401, TB408 |  |  |  |  | Mukhi Lal | 5.47 | 5-6 | 6 | 3 | 2 | 3 | 164 | 164 | TA504
Satyam Enterprises Vijay | 4.67 | 4-5 | 0 | 0 | 0 | 4 | 154.05 | 154.05 | TB408 |  |  |  |  | Nasiruddin | 5.96 | 5-6 | 15 | 2 | 7.5 | 4 | 208.56 | 208.56 | TA414, TA601
Satyam Vijay | 4.88 | 4-5 | 7 | 3 | 2.33 | 9 | 376.1 | 376.1 | TB401 |  |  |  |  | Pankaj | 5.17 | 5-6 | 7 | 4 | 1.75 | 20 | 620.3 | 627.5 | TA504, TA506, TB401
Shri Karni Construction | 4.1 | 4-5 | 0 | 0 | 0 | 33 | 725 | 725 | TA506 |  |  |  |  | Pankaj 2 | 5.13 | 5-6 | 0 | 0 | 0 | 14 | 539 | 539 | TA504, TA506
Sital Singh | 4.57 | 4-5 | 0 | 0 | 0 | 3 | 132.61 | 132.6 | TB401 |  |  |  |  | Pankaj Singh Mp | 5.36 | 5-6 | 0 | 0 | 0 | 13 | 519.88 | 519.88 | TA505
Sital Singh 1 | 4.63 | 4-5 | 0 | 0 | 0 | 5 | 231.74 | 231.74 | TB401 |  |  |  |  | Pinki Devi | 5.09 | 5-6 | 4 | 1 | 4 | 8 | 417.63 | 417.63 | TA413, TA504
Uma Const | 4.21 | 4-5 | 2 | 1 | 2 | 8 | 320.31 | 320.31 | TB408 |  |  |  |  | Pinky Dewi | 5.74 | 5-6 | 8 | 3 | 2.67 | 17 | 969.22 | 985.96 | TA416
Yogendra Mahto | 4.03 | 4-5 | 11 | 5 | 2.2 | 15 | 709.09 | 709.09 | TB401, TB408 |  |  |  |  | Pritam Enterprises 3 | 5.22 | 5-6 | 0 | 0 | 0 | 9 | 428.06 | 428.06 | TA413
Amar Singh | 5.14 | 5-6 | 17 | 8 | 2.12 | 25 | 1171.91 | 1171.91 | TA416 |  |  |  |  | Priyanka Devi 2 | 5.09 | 5-6 | 13 | 3 | 4.33 | 4 | 152.7 | 152.7 | TB401, TB408
Anita Devi | 5.33 | 5-6 | 4 | 2 | 2 | 3 | 298.41 | 298.41 | TA325 |  |  |  |  | Priyanka Devi Sudheer | 5.48 | 5-6 | 41 | 13 | 3.15 | 13 | 559.06 | 559.06 | TB401, TB408
Arawali 2 | 5.18 | 5-6 | 0 | 0 | 0 | 3 | 113.86 | 113.86 | TB408 |  |  |  |  | Punam Devi 3 | 5.13 | 5-6 | 0 | 0 | 0 | 3 | 123 | 129.32 | TA413
Arawali Infra 2 | 5.23 | 5-6 | 12 | 4 | 3 | 4 | 230.2 | 230.2 | TB401 |  |  |  |  | Punam Kumari 2 | 5.33 | 5-6 | 2 | 1 | 2 | 25 | 1317.1 | 1317.1 | TA413, TA416, TA419, TA504
Asc Heights | 5.45 | 5-6 | 8 | 4 | 2 | 20 | 1040.7 | 1040.7 | TA416 |  |  |  |  | Pusplata 5 | 5.41 | 5-6 | 1 | 1 | 1 | 4 | 162.38 | 162.38 | TB401
D K Verma | 5.94 | 5-6 | 17 | 6 | 2.83 | 22 | 956.69 | 956.69 | TA421 |  |  |  |  | Pusplata 6 | 5.31 | 5-6 | 3 | 1 | 3 | 5 | 212.59 | 212.59 | TB401
Devi Construction | 5.93 | 5-6 | 5 | 3 | 1.67 | 7 | 468.81 | 468.81 | TB401, TB408 |  |  |  |  | Pusplata Deepak | 5.4 | 5-6 | 12 | 4 | 3 | 5 | 188.86 | 188.86 | TB401, TB408
Fouzi Ratto | 5.04 | 5-6 | 2 | 1 | 2 | 12 | 669.87 | 669.87 | TA413 |  |  |  |  | Pusplata Kailash | 5.47 | 5-6 | 0 | 0 | 0 | 7 | 267.9 | 267.9 | TB408
Gagan Enterprise 2 | 5.99 | 5-6 | 5 | 2 | 2.5 | 5 | 281.66 | 281.66 | TA416 |  |  |  |  | Pusplata Praful | 5.32 | 5-6 | 0 | 0 | 0 | 3 | 164.92 | 164.92 | TB401, TB408
Ganesh Const | 5.51 | 5-6 | 10 | 1 | 10 | 10 | 424.63 | 424.63 | TB408 |  |  |  |  | Radha Enterprises 1 | 5.34 | 5-6 | 10 | 2 | 5 | 13 | 613.59 | 635.35 | TA419
Gokul Sarkar 2 | 5.66 | 5-6 | 7 | 4 | 1.75 | 4 | 266.18 | 266.18 | TA325 |  |  |  |  | Satyam Mondal | 5.05 | 5-6 | 6 | 4 | 1.5 | 7 | 348.59 | 348.59 | TB401
Horil | 5.3 | 5-6 | 0 | 0 | 0 | 5 | 122 | 122 | TA506 |  |  |  |  | Shila Devi | 5.97 | 5-6 | 1 | 1 | 1 | 16 | 966.64 | 966.64 | TA505
J Lngh O 1 | 5.84 | 5-6 | 1 | 1 | 1 | 6 | 251.1 | 251.1 | TA421 |  |  |  |  | Subhash | 5.49 | 5-6 | 18 | 7 | 2.57 | 17 | 1032.12 | 1032.12 | TA325, TA414, TA418
Jailal Ageria | 5.07 | 5-6 | 7 | 6 | 1.17 | 12 | 572.82 | 572.82 | TB401, TB408 |  |  |  |  | Sunny Const | 5.05 | 5-6 | 3 | 2 | 1.5 | 14 | 665.95 | 715.54 | TB401, TB408
Jaman Mahto 1 Ratna Devi | 5.12 | 5-6 | 5 | 2 | 2.5 | 4 | 394.41 | 394.41 | TA325 |  |  |  |  | Tejal Mahto | 5.81 | 5-6 | 18 | 3 | 6 | 4 | 122 | 122 | TA506
Jhemon Mahato 1 | 5.97 | 5-6 | 0 | 0 | 0 | 7 | 483.28 | 483.28 | TA505 |  |  |  |  | Anannya Traders | 6.14 | 6-7 | 0 | 0 | 0 | 6 | 245.41 | 245.41 | TA414
Jwala Singh 2 | 5.81 | 5-6 | 28 | 7 | 4 | 42 | 1789.44 | 1789.44 | TA413, TA505, TB401, TB408 |  |  |  |  | Ananya Traders 1 | 6.04 | 6-7 | 12 | 6 | 2 | 13 | 990.87 | 990.87 | TA416
M S Govind Mahto | 5.91 | 5-6 | 0 | 0 | 0 | 4 | 165.36 | 165.36 | TA512 |  |  |  |  | Ananya Traders 2 | 6.77 | 6-7 | 1 | 1 | 1 | 11 | 595.89 | 595.89 | TA416
M S Jwala Singh | 5.26 | 5-6 | 6 | 6 | 1 | 21 | 898.64 | 898.64 | TA512 |  |  |  |  | Deglal Mahato | 6.37 | 6-7 | 0 | 0 | 0 | 18 | 1070.42 | 1070.42 | TA505
M S Jwala Singh 2 | 5.24 | 5-6 | 9 | 2 | 4.5 | 10 | 408.59 | 408.59 | TA512 |  |  |  |  | Dewi Construction Girendra | 6.96 | 6-7 | 4 | 2 | 2 | 9 | 438.43 | 438.43 | TA416
M S Raju Kumar | 5.06 | 5-6 | 0 | 0 | 0 | 5 | 202.36 | 202.36 | TA512 |  |  |  |  | Dhaneswar Mahto | 6.2 | 6-7 | 12 | 2 | 6 | 3 | 198.27 | 198.27 | TA325
M S Sunny Construction | 5.63 | 5-6 | 0 | 0 | 0 | 3 | 140.8 | 140.8 | TA512 |  |  |  |  | Gagan Enterprise 1 | 6.4 | 6-7 | 9 | 2 | 4.5 | 13 | 947.44 | 952.15 | TA416
Md Akhtar | 5.19 | 5-6 | 8 | 2 | 4 | 4 | 409.72 | 409.72 | TA325 |  |  |  |  | Gauri Shankar Mahto | 6.67 | 6-7 | 13 | 2 | 6.5 | 4 | 233.34 | 233.34 | TA421
Mukesh | 5.28 | 5-6 | 1 | 1 | 1 | 10 | 617.89 | 617.89 | TA325 |  |  |  |  | Jwala Singh | 6.22 | 6-7 | 6 | 4 | 1.5 | 68 | 3223.25 | 3237.71 | TA325, TA419, TA505, TB401, TB408
Mukhi Lal | 5.47 | 5-6 | 6 | 3 | 2 | 3 | 164 | 164 | TA504 |  |  |  |  | Jwala Singh Suraj Kumar | 6.26 | 6-7 | 0 | 0 | 0 | 3 | 162.83 | 162.83 | TB408
Nasiruddin | 5.96 | 5-6 | 15 | 2 | 7.5 | 4 | 208.56 | 208.56 | TA414, TA601 |  |  |  |  | M S Kartik Mahto | 6.97 | 6-7 | 0 | 0 | 0 | 24 | 948.13 | 948.13 | TA512
Pankaj Singh Mp | 5.36 | 5-6 | 0 | 0 | 0 | 13 | 519.88 | 519.88 | TA505 |  |  |  |  | Pusplata 2 | 6.4 | 6-7 | 0 | 0 | 0 | 5 | 224.04 | 224.04 | TB401
Pritam Enterprises 3 | 5.22 | 5-6 | 0 | 0 | 0 | 9 | 428.06 | 428.06 | TA413 |  |  |  |  | Radha Enterprises | 6.66 | 6-7 | 8 | 2 | 4 | 8 | 659.6 | 659.6 | TA419
Priyanka Devi 2 | 5.09 | 5-6 | 13 | 3 | 4.33 | 4 | 152.7 | 152.7 | TB401, TB408 |  |  |  |  | Rahul Kumar | 6.19 | 6-7 | 20 | 10 | 2 | 24 | 1331.71 | 1331.71 | TA325, TA414, TB401, TB408
Priyanka Devi Sudheer | 5.48 | 5-6 | 41 | 13 | 3.15 | 13 | 559.06 | 559.06 | TB401, TB408 |  |  |  |  | Sunny Construction | 6.59 | 6-7 | 2 | 1 | 2 | 14 | 679.11 | 679.11 | TB408
Punam Devi 1 | 5.83 | 5-6 | 3 | 1 | 3 | 20 | 821.67 | 821.67 | TA413 |  |  |  |  | Ved Prakash | 6.2 | 6-7 | 0 | 0 | 0 | 12 | 929.86 | 929.86 | TA413
Punam Devi 2 | 5.03 | 5-6 | 0 | 0 | 0 | 24 | 1026.73 | 1026.73 | TA413 |  |  |  |  | Dk Construction Sarvan Kumar | 7.59 | 7-8 | 0 | 0 | 0 | 3 | 204.8 | 204.8 | TA414
Punam Kumari 2 | 5.33 | 5-6 | 2 | 1 | 2 | 25 | 1317.1 | 1317.1 | TA413, TA416, TA419, TA504 |  |  |  |  | Gourishankar | 7.53 | 7-8 | 11 | 6 | 1.83 | 12 | 744.98 | 744.98 | TA325, TB401
Pusplata 5 | 5.41 | 5-6 | 1 | 1 | 1 | 4 | 162.38 | 162.38 | TB401 |  |  |  |  | Jwala | 7.5 | 7-8 | 9 | 6 | 1.5 | 6 | 314.85 | 383.77 | TA325
Pusplata 6 | 5.31 | 5-6 | 3 | 1 | 3 | 5 | 212.59 | 212.59 | TB401 |  |  |  |  | M S Shobha Debi | 7.38 | 7-8 | 2 | 1 | 2 | 4 | 147.62 | 147.62 | TA512
Pusplata Deepak | 5.4 | 5-6 | 12 | 4 | 3 | 5 | 188.86 | 188.86 | TB401, TB408 |  |  |  |  | Poonam | 7.19 | 7-8 | 8 | 3 | 2.67 | 9 | 366.88 | 366.88 | TB401
Pusplata Kailash | 5.47 | 5-6 | 0 | 0 | 0 | 7 | 267.9 | 267.9 | TB408 |  |  |  |  | Pusplata 1 | 7.43 | 7-8 | 5 | 3 | 1.67 | 6 | 282.37 | 282.37 | TB401
Pusplata Praful | 5.32 | 5-6 | 0 | 0 | 0 | 3 | 164.92 | 164.92 | TB401, TB408 |  |  |  |  | Pusplata 3 | 7.14 | 7-8 | 14 | 2 | 7 | 4 | 171.45 | 171.45 | TB401
Radha Enterprises | 5.61 | 5-6 | 10 | 3 | 3.33 | 28 | 1536.57 | 1536.57 | TA419 |  |  |  |  | Sakhila Khatun | 7.34 | 7-8 | 0 | 0 | 0 | 3 | 168.88 | 168.88 | TA414
Radha Enterprises 1 | 5.16 | 5-6 | 24 | 4 | 6 | 17 | 821.01 | 821.01 | TA419 |  |  |  |  | Sakila Khatun | 7.05 | 7-8 | 5 | 2 | 2.5 | 7 | 606.69 | 606.69 | TA325, TA414
Rahul Kumar | 5.35 | 5-6 | 79 | 24 | 3.29 | 51 | 2984.84 | 2984.84 | TA325, TA414, TB401, TB408 |  |  |  |  | Satyam Enterprises | 7.81 | 7-8 | 0 | 0 | 0 | 10 | 492.15 | 492.15 | TB408
Satyam Mondal | 5.05 | 5-6 | 6 | 4 | 1.5 | 7 | 348.59 | 348.59 | TB401 |  |  |  |  | Satyam Nitish | 7.81 | 7-8 | 5 | 3 | 1.67 | 9 | 632.23 | 632.23 | TB401
Shila Devi | 5.97 | 5-6 | 1 | 1 | 1 | 16 | 966.64 | 966.64 | TA505 |  |  |  |  | Shobha Devi | 7.3 | 7-8 | 26 | 5 | 5.2 | 19 | 1153.97 | 1153.97 | TB408
Subhash | 5.49 | 5-6 | 18 | 7 | 2.57 | 17 | 1032.12 | 1032.12 | TA325, TA414, TA418 |  |  |  |  | Sobha Devi | 7.83 | 7-8 | 3 | 1 | 3 | 11 | 422.56 | 435.51 | TB401, TB408
Sunny Const | 5.74 | 5-6 | 10 | 5 | 2 | 84 | 3869.78 | 3869.78 | TB401, TB408 |  |  |  |  | Subash | 7.94 | 7-8 | 5 | 3 | 1.67 | 62 | 2438.2 | 2460.96 | TA421
Tejal Construction | 5.01 | 5-6 | 0 | 0 | 0 | 3 | 115.2 | 115.2 | TB401 |  |  |  |  | Jwala Singh 3 | 8.09 | 8-9 | 8 | 3 | 2.67 | 5 | 283.16 | 283.16 | TB401
Tejal Mahto | 5.81 | 5-6 | 18 | 3 | 6 | 4 | 122 | 122 | TA506 |  |  |  |  | Khatun | 8.49 | 8-9 | 28 | 10 | 2.8 | 40 | 1824.84 | 1859.31 | TA421
Anannya Traders | 6.14 | 6-7 | 0 | 0 | 0 | 6 | 245.41 | 245.41 | TA414 |  |  |  |  | Pusplata 4 | 8.04 | 8-9 | 2 | 2 | 1 | 8 | 313.74 | 313.74 | TB401
Ananya Traders 1 | 6.03 | 6-7 | 12 | 6 | 2 | 14 | 1036.91 | 1036.91 | TA416 |  |  |  |  | Satyam Manish | 8.28 | 8-9 | 11 | 5 | 2.2 | 14 | 786.68 | 786.68 | TB401, TB408
Ananya Traders 2 | 6.77 | 6-7 | 1 | 1 | 1 | 11 | 595.89 | 595.89 | TA416
Chinta Devi | 6.34 | 6-7 | 16 | 10 | 1.6 | 96 | 4374.86 | 4374.86 | TB401, TB408
Deglal Mahato | 6.37 | 6-7 | 0 | 0 | 0 | 18 | 1070.42 | 1070.42 | TA505
Deglal Mahto | 6.22 | 6-7 | 7 | 4 | 1.75 | 18 | 758.48 | 758.48 | TB401, TB408
Dewi Construction Girendra | 6.64 | 6-7 | 9 | 5 | 1.8 | 40 | 1858.04 | 1858.04 | TA416
Dhaneswar Mahto | 6.96 | 6-7 | 46 | 14 | 3.29 | 22 | 1433.16 | 1433.16 | TA325
Gagan Enterprise 1 | 6.39 | 6-7 | 9 | 2 | 4.5 | 13 | 952.15 | 952.15 | TA416
Gauri Shankar Mahto | 6.67 | 6-7 | 13 | 2 | 6.5 | 4 | 233.34 | 233.34 | TA421
Gourishankar | 6.26 | 6-7 | 54 | 19 | 2.84 | 38 | 2440.69 | 2440.69 | TA325, TB401
J Lngh | 6.41 | 6-7 | 1 | 1 | 1 | 7 | 262.86 | 262.86 | TA421
Jagdish Mahto | 6.31 | 6-7 | 2 | 2 | 1 | 20 | 845.82 | 845.82 | TB401, TB408
Jwala Singh | 6.56 | 6-7 | 8 | 6 | 1.33 | 87 | 3954.83 | 3954.83 | TA325, TA419, TA505, TB401, TB408
Jwala Singh Suraj Kumar | 6.26 | 6-7 | 0 | 0 | 0 | 3 | 162.83 | 162.83 | TB408
Lalan Mahto | 6.36 | 6-7 | 2 | 2 | 1 | 17 | 762.97 | 762.97 | TA325
M S Kartik Mahto | 6.97 | 6-7 | 0 | 0 | 0 | 24 | 948.13 | 948.13 | TA512
Pankaj | 6.34 | 6-7 | 9 | 6 | 1.5 | 60 | 2282.41 | 2282.41 | TA416, TA504, TA506, TB401
Pankaj 2 | 6.37 | 6-7 | 0 | 0 | 0 | 30 | 1134 | 1134 | TA504, TA506
Pinky Dewi | 6.08 | 6-7 | 11 | 5 | 2.2 | 37 | 1921.83 | 1921.83 | TA416
Pusplata 2 | 6.4 | 6-7 | 0 | 0 | 0 | 5 | 224.04 | 224.04 | TB401
Sobha Devi | 6.58 | 6-7 | 11 | 8 | 1.38 | 105 | 4487.37 | 4487.37 | TB401, TB408
Sunny Construction | 6.59 | 6-7 | 2 | 1 | 2 | 14 | 679.11 | 679.11 | TB408
Suraj Const | 6.03 | 6-7 | 0 | 0 | 0 | 36 | 1440.88 | 1440.88 | TB401, TB408
Ved Prakash | 6.2 | 6-7 | 0 | 0 | 0 | 12 | 929.86 | 929.86 | TA413
Dk Construction Sarvan Kumar | 7.59 | 7-8 | 0 | 0 | 0 | 3 | 204.8 | 204.8 | TA414
Jwala | 7.68 | 7-8 | 21 | 12 | 1.75 | 22 | 1229.32 | 1229.32 | TA325
Khatun | 7.24 | 7-8 | 34 | 12 | 2.83 | 68 | 2997.93 | 2997.93 | TA421
M S Shobha Debi | 7.38 | 7-8 | 2 | 1 | 2 | 4 | 147.62 | 147.62 | TA512
Poonam | 7.19 | 7-8 | 8 | 3 | 2.67 | 9 | 366.88 | 366.88 | TB401
Punam Devi 4 | 7.87 | 7-8 | 0 | 0 | 0 | 15 | 621.97 | 621.97 | TA413
Pusplata 1 | 7.43 | 7-8 | 5 | 3 | 1.67 | 6 | 282.37 | 282.37 | TB401
Pusplata 3 | 7.14 | 7-8 | 14 | 2 | 7 | 4 | 171.45 | 171.45 | TB401
Sakhila Khatun | 7.34 | 7-8 | 0 | 0 | 0 | 3 | 168.88 | 168.88 | TA414
Sakila Khatun | 7.05 | 7-8 | 5 | 2 | 2.5 | 7 | 606.69 | 606.69 | TA325, TA414
Satyam Enterprises | 7.81 | 7-8 | 0 | 0 | 0 | 10 | 492.15 | 492.15 | TB408
Satyam Nitish | 7.81 | 7-8 | 5 | 3 | 1.67 | 9 | 632.23 | 632.23 | TB401
Shobha Devi | 7.3 | 7-8 | 26 | 5 | 5.2 | 19 | 1153.97 | 1153.97 | TB408
Subash | 7.46 | 7-8 | 6 | 4 | 1.5 | 97 | 3856.21 | 3856.21 | TA421
Jwala Singh 3 | 8.09 | 8-9 | 8 | 3 | 2.67 | 5 | 283.16 | 283.16 | TB401
Pusplata 4 | 8.04 | 8-9 | 2 | 2 | 1 | 8 | 313.74 | 313.74 | TB401
Satyam Manish | 8.28 | 8-9 | 11 | 5 | 2.2 | 14 | 786.68 | 786.68 | TB401, TB408

## Monthly Gang Buckets
Monthly Gang Production Buckets (All Data)
Scope: 2023-09-13 to 2026-02-09 ¦ Projects: 3 ¦ Erections: 3949 ¦ Gangs: 472
Bucket | Gang-Months | Sum of Tower Weight (MT)
<80 | 967 | 34647.78
80-100 | 144 | 12217.74
100-120 | 146 | 15774.29
120-140 | 139 | 17482.3
140-160 | 108 | 16050.59
160-180 | 88 | 15179.96
180-200 | 64 | 11804.16
200-220 | 60 | 12564.53
220-240 | 42 | 9944.35
240-260 | 36 | 9201.82
>=260 | 48 | 15325.57
Gang Name | Month | Monthly Production (MT) | Monthly Tower Weight (MT) | Project Codes | Towers Erected | Bucket
A B Const Birendra Panday | 2025-09 | 17 | 17 | TA506 | 1 | <80
Aamir Khan | 2025-11 | 52.53 | 37.73 | TA325 | 1 | <80
Aamir Khan | 2025-12 | 24.66 | 39.46 | TA325 | 1 | <80
Ab Const | 2025-09 | 30 | 0 |  | 0 | <80
Ab Const | 2025-10 | 57 | 87 | TA506 | 3 | <80
Ab Const | 2025-11 | 92 | 92 | TA506 | 4 | 80-100
Ab Const | 2025-12 | 68 | 37 | TA506 | 1 | <80
Ab Const | 2026-01 | 30 | 61 | TA506 | 2 | <80
Ab Const 2 | 2025-12 | 14.4 | 0 |  | 0 | <80
Ab Const 2 | 2026-01 | 3.6 | 18 | TA506 | 1 | <80
Ab Construction | 2026-01 | 73 | 73 | TA506 | 3 | <80
Ab Construction | 2026-02 | 16 | 16 | TA506 | 1 | <80
Ahmed Construction | 2025-07 | 11.14 | 11.14 | TB507 | 1 | <80
Ahmed Construction | 2025-08 | 56.55 | 53.98 | TB507 | 4 | <80
Ahmed Construction | 2025-09 | 34.26 | 36.83 | TB507 | 3 | <80
Ajay Kumar | 2024-07 | 95.95 | 80.41 | TA325 | 1 | 80-100
Ajay Kumar | 2024-08 | 31.08 | 46.62 | TA325 | 1 | <80
Ajay Kumar | 2024-09 | 103.71 | 72.24 | TA325 | 1 | 100-120
Ajay Kumar | 2024-10 | 165.84 | 179.64 | TA325 | 2 | 160-180
Ajay Kumar | 2024-11 | 157.35 | 160.68 | TA325 | 2 | 140-160
Ajay Kumar | 2024-12 | 25.11 | 39.46 | TA325 | 1 | <80
Ajay Kumar | 2025-01 | 7.84 | 0 |  | 0 | <80
Ajay Kumar | 2025-02 | 28.21 | 36.04 | TA325 | 1 | <80
Ajay Kumar | 2025-08 | 9.12 | 0 |  | 0 | <80
Ajay Kumar | 2025-09 | 6.71 | 11.14 | TB507 | 1 | <80
Ajay Kumar | 2025-10 | 14.05 | 18.73 | TB507 | 1 | <80
Ajay Kumar 1 | 2025-09 | 41.02 | 41.02 | TB507 | 3 | <80
Ajay Kumar 2 | 2025-09 | 21.9 | 12 | TB507 | 1 | <80
Ajay Kumar 2 | 2025-10 | 1.24 | 11.14 | TB507 | 1 | <80
Akash Prabha | 2026-01 | 22 | 22 | TA506 | 1 | <80
Ali Uslam | 2025-12 | 36.57 | 36.57 | TA601 | 1 | <80
Alo Reeva | 2025-12 | 16 | 16 | TA506 | 1 | <80
Aloriva Global | 2025-11 | 108.26 | 108.26 | TA416 | 2 | 100-120
Aloriva Global | 2025-12 | 53.32 | 53.32 | TA416 | 1 | <80
Amar Kumar Singh | 2025-08 | 39.42 | 0 |  | 0 | <80
Amar Kumar Singh | 2025-09 | 100.24 | 110.58 | TA413 | 2 | 100-120
Amar Kumar Singh | 2025-10 | 83.4 | 112.48 | TA413 | 2 | 80-100
Amar Singh | 2024-11 | 47.96 | 43.78 | TA416 | 1 | <80
Amar Singh | 2024-12 | 152.17 | 134.47 | TA416 | 3 | 140-160
Amar Singh | 2025-01 | 157.76 | 179.65 | TA416 | 4 | 140-160
Amar Singh | 2025-02 | 198.07 | 179.65 | TA416 | 4 | 180-200
Amar Singh | 2025-03 | 70 | 88.42 | TA416 | 2 | <80
Amar Singh | 2025-04 | 168.69 | 156.58 | TA416 | 3 | 160-180
Amar Singh | 2025-05 | 201.17 | 213.27 | TA416 | 5 | 200-220
Amar Singh | 2025-06 | 100.18 | 89.82 | TA416 | 2 | 100-120
Amar Singh | 2025-07 | 75.91 | 86.26 | TA416 | 1 | <80
Amit Choudhry | 2025-12 | 92.65 | 0 |  | 0 | 80-100
Amit Choudhry | 2026-01 | 50.81 | 143.46 | TA416 | 1 | <80
Amit Choudhury | 2025-08 | 59 | 0 |  | 0 | <80
Amit Choudhury | 2025-09 | 121.63 | 153 | TA416 | 2 | 120-140
Amit Choudhury | 2025-10 | 111.39 | 64.48 | TA416 | 1 | 100-120
Amit Choudhury | 2025-11 | 124.62 | 199.16 | TA416 | 2 | 120-140
Amit Const | 2025-05 | 53.32 | 53.32 | TA416 | 1 | <80
Amit Const | 2025-06 | 92.1 | 92.1 | TA416 | 2 | 80-100
Amit Kumar Singh | 2025-07 | 111.4 | 89.5 | TA413 | 2 | 100-120
Amit Kumar Singh | 2025-08 | 138.37 | 132.42 | TA413 | 3 | 120-140
Amit Kumar Singh | 2025-09 | 104.95 | 132.8 | TA413 | 3 | 100-120
Amit Yadav | 2025-11 | 16.42 | 0 |  | 0 | <80
Amit Yadav | 2025-12 | 53.26 | 43.78 | TA419 | 1 | <80
Amit Yadav | 2026-01 | 16.48 | 42.37 | TA419 | 1 | <80
Anand Construction | 2025-03 | 3.84 | 0 |  | 0 | <80
Anand Construction | 2025-04 | 97.55 | 101.39 | TA416 | 2 | 80-100
Anannya Traders | 2025-12 | 19.02 | 0 |  | 0 | <80
Anannya Traders | 2026-01 | 226.39 | 245.41 | TA414 | 6 | 220-240
Ananya Trader | 2025-09 | 94.54 | 42.37 | TA416 | 1 | 80-100
Ananya Trader | 2025-10 | 91.29 | 143.46 | TA416 | 1 | 80-100
Ananya Traders 1 | 2025-03 | 46.05 | 46.05 | TA416 | 1 | <80
Ananya Traders 1 | 2025-04 | 168.25 | 152.91 | TA416 | 3 | 160-180
Ananya Traders 1 | 2025-05 | 192.2 | 176.85 | TA416 | 4 | 180-200
Ananya Traders 1 | 2025-06 | 176.7 | 207.4 | TA416 | 2 | 160-180
Ananya Traders 1 | 2025-07 | 187.77 | 101.69 | TA416 | 1 | 180-200
Ananya Traders 1 | 2025-08 | 150.44 | 143.46 | TA416 | 1 | 140-160
Ananya Traders 1 | 2025-09 | 115.5 | 208.56 | TA416 | 2 | 100-120
Ananya Traders 2 | 2025-04 | 136.85 | 130.8 | TA416 | 3 | 120-140
Ananya Traders 2 | 2025-05 | 253.68 | 219.22 | TA416 | 5 | 240-260
Ananya Traders 2 | 2025-06 | 205.36 | 245.87 | TA416 | 3 | 200-220
Anarul Haque | 2025-02 | 21.99 | 0 |  | 0 | <80
Anarul Haque | 2025-03 | 105.1 | 72.24 | TA325 | 1 | 100-120
Anarul Haque | 2025-04 | 120.81 | 175.65 | TA325 | 2 | 120-140
Anil Construction | 2025-09 | 41.65 | 34.6 | TA513 | 2 | <80
Anil Construction | 2025-10 | 143.95 | 146.48 | TA513 | 6 | 140-160
Anil Construction | 2025-11 | 135.66 | 122.2 | TA513 | 6 | 120-140
Anil Construction | 2025-12 | 89.76 | 107.75 | TA513 | 4 | 80-100
Anil Kumar | 2025-09 | 51.58 | 0 |  | 0 | <80
Anil Kumar | 2025-10 | 48.79 | 100.38 | TA505 | 2 | <80
Anil Kumar Departmental Kewat | 2025-06 | 29.47 | 0 |  | 0 | <80
Anil Kumar Departmental Kewat | 2025-07 | 9.38 | 38.85 | TB401 | 1 | <80
Anil Kumar Departmental Ramayan | 2025-06 | 13.97 | 0 |  | 0 | <80
Anil Kumar Departmental Ramayan | 2025-07 | 72.16 | 86.13 | TB401 | 1 | <80
Anil Kumar Kewat | 2025-06 | 60.28 | 38.85 | TB408 | 1 | <80
Anil Kumar Kewat | 2025-07 | 16.07 | 37.5 | TB408 | 1 | <80
Anil Kumar Ramayan Departmental | 2025-06 | 41.47 | 0 |  | 0 | <80
Anil Kumar Ramayan Departmental | 2025-07 | 44.66 | 86.13 | TB401 | 1 | <80
Anil Kumar Rudra Const | 2025-08 | 37.93 | 37.93 | TA505 | 1 | <80
Anita Devi | 2025-10 | 150.52 | 72.24 | TA325 | 1 | 140-160
Anita Devi | 2025-11 | 128.98 | 84.3 | TA325 | 1 | 120-140
Anita Devi | 2025-12 | 18.92 | 141.87 | TA325 | 1 | <80
Anjani Enterprises | 2025-06 | 3.49 | 0 |  | 0 | <80
Anjani Enterprises | 2025-07 | 41.92 | 45.41 | TB401 | 1 | <80
Anjani Power Priyanka Devi Sudheer | 2025-07 | 0.85 | 0 |  | 0 | <80
Anjani Power Priyanka Devi Sudheer | 2025-08 | 13.23 | 0 |  | 0 | <80
Anjani Power Priyanka Devi Sudheer | 2025-09 | 12.81 | 0 |  | 0 | <80
Anjani Power Priyanka Devi Sudheer | 2025-10 | 11.95 | 38.85 | TB401 | 1 | <80
Anjum | 2025-10 | 23.6 | 0 |  | 0 | <80
Anjum | 2025-11 | 70.81 | 94.41 | TA325 | 1 | <80
Anjum Construction | 2025-11 | 3.24 | 0 |  | 0 | <80
Anjum Construction | 2025-12 | 85.4 | 84.3 | TA414 | 1 | 80-100
Anjum Construction | 2026-01 | 62.35 | 34.7 | TA414 | 1 | <80
Anjum Construction | 2026-02 | 5.82 | 37.8 | TA414 | 1 | <80
Annaya Traders | 2025-04 | 6.25 | 0 |  | 0 | <80
Annaya Traders | 2025-05 | 31.25 | 37.5 | TB401 | 1 | <80
Anvi Construction | 2025-08 | 18.28 | 0 |  | 0 | <80
Anvi Construction | 2025-09 | 20.57 | 38.85 | TB408 | 1 | <80
Arawali | 2025-08 | 45.41 | 45.41 | TB401 | 1 | <80
Arawali 1 | 2025-07 | 66.99 | 0 |  | 0 | <80
Arawali 1 | 2025-08 | 19.14 | 86.13 | TB408 | 1 | <80
Arawali 2 | 2025-07 | 113.86 | 113.86 | TB408 | 3 | 100-120
Arawali Infra 1 | 2025-07 | 37.5 | 37.5 | TB401 | 1 | <80
Arawali Infra 2 | 2025-06 | 46.38 | 0 |  | 0 | <80
Arawali Infra 2 | 2025-07 | 144.98 | 191.36 | TB401 | 3 | 140-160
Arawali Infra 2 | 2025-08 | 38.85 | 38.85 | TB401 | 1 | <80
Asc Heights | 2024-12 | 33.49 | 0 |  | 0 | <80
Asc Heights | 2025-01 | 178.81 | 178.25 | TA416 | 4 | 160-180
Asc Heights | 2025-02 | 164.03 | 198.08 | TA416 | 4 | 160-180
Asc Heights | 2025-03 | 174.57 | 174.57 | TA416 | 4 | 160-180
Asc Heights | 2025-04 | 178.01 | 171.76 | TA416 | 3 | 160-180
Asc Heights | 2025-05 | 158.14 | 128.52 | TA416 | 3 | 140-160
Asc Heights | 2025-06 | 134.46 | 143.46 | TA416 | 1 | 120-140
Asc Heights | 2025-07 | 19.19 | 46.05 | TA416 | 1 | <80
Ashok | 2024-10 | 72.74 | 72.74 | TA421 | 2 | <80
Ashok | 2024-11 | 92.59 | 92.59 | TA421 | 2 | 80-100
Ashok Kumar | 2024-09 | 36.37 | 36.37 | TA421 | 1 | <80
Ashokkumar | 2024-10 | 13.64 | 0 |  | 0 | <80
Ashokkumar | 2024-11 | 22.73 | 36.37 | TA421 | 1 | <80
Ayansh Const | 2025-08 | 4.28 | 0 |  | 0 | <80
Ayansh Const | 2025-09 | 30 | 34.29 | TB507 | 3 | <80
Balaji Tour Travels 2 | 2025-12 | 12 | 12 | TB507 | 1 | <80
Bambole Traders | 2025-07 | 36 | 0 |  | 0 | <80
Bambole Traders | 2025-08 | 9.69 | 45.7 | TA413 | 1 | <80
Barkat Ali | 2024-09 | 36.04 | 36.04 | TA325 | 1 | <80
Barkat Ali | 2024-11 | 24.85 | 0 |  | 0 | <80
Barkat Ali | 2024-12 | 84.14 | 99.55 | TA325 | 2 | 80-100
Barkat Ali | 2025-01 | 193.44 | 132.14 | TA325 | 2 | 180-200
Barkat Ali | 2025-02 | 55.76 | 113.18 | TA325 | 2 | <80
Barkat Ali | 2025-03 | 103.5 | 73.78 | TA325 | 2 | 100-120
Barkat Ali | 2025-04 | 163.72 | 200.96 | TA325 | 5 | 160-180
Barkat Ali | 2025-05 | 69.66 | 75.46 | TA325 | 2 | <80
Barkat Ali Mithun Kumar Vntl | 2025-07 | 3.73 | 0 |  | 0 | <80
Barkat Ali Mithun Kumar Vntl | 2025-08 | 12.85 | 0 |  | 0 | <80
Barkat Ali Mithun Kumar Vntl | 2025-09 | 12.44 | 0 |  | 0 | <80
Barkat Ali Mithun Kumar Vntl | 2025-10 | 8.71 | 37.73 | TA325 | 1 | <80
Bhagwan Construction | 2024-09 | 98.04 | 79.96 | TA413 | 2 | 80-100
Bhagwan Construction | 2024-10 | 181.67 | 199.75 | TA413 | 5 | 180-200
Bhairaw Mahto | 2025-08 | 18.82 | 0 |  | 0 | <80
Bhairaw Mahto | 2025-09 | 112.23 | 112.48 | TA413 | 2 | 100-120
Bhairaw Mahto | 2025-10 | 113.52 | 109.29 | TA413 | 2 | 100-120
Bhairaw Mahto | 2025-11 | 74.08 | 96.88 | TA413 | 1 | <80
Bhairo Mahato | 2025-11 | 90.97 | 0 |  | 0 | 80-100
Bhairo Mahato | 2025-12 | 240.77 | 319.85 | TA419 | 3 | 240-260
Bhairo Mahato | 2026-01 | 46.07 | 57.96 | TA419 | 1 | <80
Bhairo Mahto | 2025-05 | 25.9 | 0 |  | 0 | <80
Bhairo Mahto | 2025-06 | 50.45 | 76.35 | TB408 | 2 | <80
Bhairo Mahto | 2025-07 | 19.53 | 0 |  | 0 | <80
Bhairo Mahto | 2025-08 | 94.32 | 113.86 | TB408 | 3 | 80-100
Bhairo Mahto | 2025-09 | 77.69 | 77.69 | TB401, TB408 | 2 | <80
Bhairo Mahto Departmental | 2025-05 | 66.29 | 0 |  | 0 | <80
Bhairo Mahto Departmental | 2025-06 | 55.47 | 121.76 | TB401 | 3 | <80
Bhairo Mahto Departmental Arawali | 2025-07 | 56.09 | 0 |  | 0 | <80
Bhairo Mahto Departmental Arawali | 2025-08 | 44.87 | 100.96 | TB401 | 1 | <80
Bhairo Mahto Kewat | 2025-07 | 85.35 | 37.5 | TB408 | 1 | 80-100
Bhairo Mahto Kewat | 2025-08 | 38.28 | 86.13 | TB408 | 1 | <80
Bhairo Mahto Priyanka Devi Subodh | 2025-07 | 86.13 | 86.13 | TB408 | 1 | 80-100
Bhoi Enterprises | 2025-08 | 2.23 | 0 |  | 0 | <80
Bhoi Enterprises | 2025-09 | 35.24 | 34.29 | TB507 | 3 | <80
Bhoi Enterprises | 2025-10 | 73.81 | 76.99 | TB507 | 6 | <80
Bhoi Enterprises | 2025-11 | 85.19 | 76.58 | TB507 | 6 | 80-100
Bhoi Enterprises | 2025-12 | 56.84 | 65.45 | TB507 | 4 | <80
Bhuvneshwar | 2024-05 | 8.04 | 0 |  | 0 | <80
Bhuvneshwar | 2024-06 | 66.97 | 75.01 | TB408 | 2 | <80
Bhuvneshwar | 2024-07 | 77.7 | 77.7 | TB408 | 2 | <80
Bina Devi | 2024-09 | 72.32 | 47.18 | TB401 | 1 | <80
Bina Devi | 2024-10 | 127.57 | 152.7 | TB401, TB408 | 4 | 120-140
Bina Devi | 2024-11 | 135.29 | 135.29 | TB401, TB408 | 3 | 120-140
Bina Devi | 2024-12 | 75.01 | 75.01 | TB401 | 2 | <80
Bina Devi | 2025-01 | 81.82 | 77.7 | TB408 | 2 | 80-100
Bina Devi | 2025-02 | 116.29 | 120.42 | TB408 | 3 | 100-120
Bina Devi | 2025-03 | 82.92 | 82.92 | TB401 | 2 | 80-100
Binod Mahto | 2025-09 | 9 | 0 |  | 0 | <80
Binod Mahto | 2025-10 | 68 | 58 | TA506 | 2 | <80
Binod Mahto | 2025-11 | 99 | 118 | TA506 | 3 | 80-100
Binod Mahto | 2025-12 | 44 | 44 | TA506 | 2 | <80
Binod Mahto | 2026-01 | 59.4 | 51 | TA506 | 2 | <80
Binod Mahto | 2026-02 | 33.6 | 42 | TA506 | 1 | <80
Chahanur Bibi | 2024-08 | 2.9 | 0 |  | 0 | <80
Chahanur Bibi | 2024-09 | 29.02 | 0 |  | 0 | <80
Chahanur Bibi | 2024-10 | 5.8 | 37.73 | TA325 | 1 | <80
Chinta Devi | 2023-11 | 100.91 | 75.01 | TB401 | 2 | 100-120
Chinta Devi | 2023-12 | 223.85 | 233.08 | TB401 | 6 | 220-240
Chinta Devi | 2024-01 | 211.88 | 198.54 | TB401 | 5 | 200-220
Chinta Devi | 2024-02 | 218.88 | 243.53 | TB401, TB408 | 6 | 200-220
Chinta Devi | 2024-03 | 228.51 | 226.37 | TB408 | 6 | 220-240
Chinta Devi | 2024-04 | 222.89 | 208.96 | TB408 | 5 | 220-240
Chinta Devi | 2024-05 | 16.07 | 37.5 | TB408 | 1 | <80
Chinta Devi | 2024-08 | 15 | 0 |  | 0 | <80
Chinta Devi | 2024-09 | 189.69 | 170.11 | TB401 | 4 | 180-200
Chinta Devi | 2024-10 | 265.4 | 262.25 | TB401, TB408 | 6 | >=260
Chinta Devi | 2024-11 | 278.79 | 316.53 | TB401, TB408 | 7 | >=260
Chinta Devi | 2024-12 | 284.77 | 284.77 | TB401, TB408 | 5 | >=260
Chinta Devi | 2025-01 | 218.6 | 192.7 | TB408 | 4 | 200-220
Chinta Devi | 2025-02 | 235.58 | 230.4 | TB408 | 6 | 220-240
Chinta Devi | 2025-03 | 237.59 | 260.9 | TB408 | 6 | 220-240
Chinta Devi | 2025-04 | 211.02 | 192.89 | TB401, TB408 | 5 | 200-220
Chinta Devi | 2025-05 | 12.95 | 38.85 | TB408 | 1 | <80
Chinta Devi | 2025-08 | 84.69 | 84.69 | TB408 | 2 | 80-100
Chinta Devi | 2025-09 | 196.81 | 182.45 | TB408 | 2 | 180-200
Chinta Devi | 2025-10 | 247.17 | 237.82 | TB408 | 2 | 240-260
Chinta Devi | 2025-11 | 257.04 | 280.74 | TB401, TB408 | 6 | 240-260
Chinta Devi | 2025-12 | 204.38 | 171.45 | TB408 | 4 | 200-220
Chinta Devi | 2026-01 | 178.33 | 199.9 | TB408 | 4 | 160-180
Chinta Devi | 2026-02 | 34.06 | 45.41 | TB408 | 1 | <80
Chitra Construction | 2025-11 | 37.73 | 37.73 | TA325 | 1 | <80
Chitra Construction | 2025-12 | 61.08 | 38.04 | TA414 | 1 | <80
Chitra Construction | 2026-01 | 51.4 | 74.44 | TA414 | 1 | <80
Crane Erc Team Mp | 2025-10 | 14.14 | 0 |  | 0 | <80
Crane Erc Team Mp | 2025-11 | 102.01 | 107.11 | TA505 | 3 | 100-120
Crane Erc Team Mp | 2025-12 | 163.56 | 168.38 | TA505 | 4 | 160-180
Crane Erc Team Mp | 2026-01 | 125.33 | 129.54 | TA505 | 3 | 120-140
Crestless Wave Trading Opc | 2026-01 | 62.95 | 62.95 | TA414 | 1 | <80
D K Verma | 2025-07 | 88.51 | 75.86 | TA421 | 2 | 80-100
D K Verma | 2025-08 | 149.56 | 162.21 | TA421 | 4 | 140-160
D K Verma | 2025-09 | 182.59 | 182.59 | TA421 | 4 | 180-200
D K Verma | 2025-10 | 182.41 | 153.96 | TA421 | 4 | 180-200
D K Verma | 2025-11 | 185.05 | 213.5 | TA421 | 5 | 180-200
D K Verma | 2025-12 | 154.43 | 130.85 | TA421 | 2 | 140-160
D K Verma | 2026-01 | 14.14 | 37.72 | TA421 | 1 | <80
Daulat Mahto | 2024-11 | 70.81 | 0 |  | 0 | <80
Daulat Mahto | 2024-12 | 75.05 | 132.14 | TA325 | 2 | <80
Daulat Mahto | 2025-01 | 118.48 | 120.19 | TA325 | 3 | 100-120
Daulat Mahto | 2025-02 | 135.11 | 136.34 | TA325 | 3 | 120-140
Daulat Mahto | 2025-03 | 102.45 | 113.23 | TA325 | 3 | 100-120
Daulat Mahto | 2025-04 | 55.87 | 37.73 | TA325 | 1 | <80
Daulat Mahto | 2025-05 | 36.28 | 54.42 | TA325 | 1 | <80
Deglal Mahato | 2025-08 | 33.63 | 0 |  | 0 | <80
Deglal Mahato | 2025-09 | 209.89 | 188.14 | TA505 | 3 | 200-220
Deglal Mahato | 2025-10 | 241.01 | 296.39 | TA505 | 4 | 240-260
Deglal Mahato | 2025-11 | 150.01 | 121.56 | TA505 | 3 | 140-160
Deglal Mahato | 2025-12 | 213.99 | 173.03 | TA505 | 3 | 200-220
Deglal Mahato | 2026-01 | 158.61 | 204.28 | TA505 | 4 | 140-160
Deglal Mahato | 2026-02 | 63.29 | 87.02 | TA505 | 1 | <80
Deglal Mahato Mp | 2025-09 | 76.34 | 72.32 | TA505 | 2 | <80
Deglal Mahato Mp | 2025-10 | 145.15 | 144.08 | TA505 | 4 | 140-160
Deglal Mahato Mp | 2025-11 | 154.12 | 144.08 | TA505 | 4 | 140-160
Deglal Mahato Mp | 2025-12 | 163.04 | 157.5 | TA505 | 3 | 160-180
Deglal Mahato Mp | 2026-01 | 146.32 | 150.91 | TA505 | 4 | 140-160
Deglal Mahato Mp | 2026-02 | 20.09 | 36.16 | TA505 | 1 | <80
Deglal Mahto | 2024-08 | 9.71 | 0 |  | 0 | <80
Deglal Mahto | 2024-09 | 199.92 | 190.21 | TB401, TB408 | 5 | 180-200
Deglal Mahto | 2024-10 | 201.49 | 209.11 | TB401, TB408 | 4 | 200-220
Deglal Mahto | 2024-11 | 186.75 | 198.54 | TB401, TB408 | 5 | 180-200
Deglal Mahto | 2024-12 | 146.49 | 121.76 | TB401, TB408 | 3 | 140-160
Deglal Mahto | 2025-01 | 14.13 | 38.85 | TB408 | 1 | <80
Departmental Gang | 2024-05 | 30.88 | 0 |  | 0 | <80
Departmental Gang | 2024-06 | 76.09 | 84.26 | TB401 | 2 | <80
Departmental Gang | 2024-07 | 139 | 120.42 | TB401 | 3 | 120-140
Departmental Gang | 2024-08 | 4.13 | 45.41 | TB401 | 1 | <80
Devi Construction | 2025-10 | 131.81 | 84.69 | TB401, TB408 | 2 | 120-140
Devi Construction | 2025-11 | 169.04 | 216.16 | TB408 | 3 | 160-180
Devi Construction | 2025-12 | 167.96 | 167.96 | TB408 | 2 | 160-180
Devine | 2025-06 | 42.37 | 42.37 | TA416 | 1 | <80
Dewi Construction Girendra | 2024-09 | 87.55 | 87.55 | TA416 | 2 | 80-100
Dewi Construction Girendra | 2024-10 | 222.02 | 222.02 | TA416 | 5 | 220-240
Dewi Construction Girendra | 2024-11 | 239.08 | 226.57 | TA416 | 5 | 220-240
Dewi Construction Girendra | 2024-12 | 204.97 | 217.48 | TA416 | 5 | 200-220
Dewi Construction Girendra | 2025-01 | 192.81 | 179.65 | TA416 | 4 | 180-200
Dewi Construction Girendra | 2025-02 | 217.1 | 202.63 | TA416 | 4 | 200-220
Dewi Construction Girendra | 2025-03 | 256.07 | 283.7 | TA416 | 6 | 240-260
Dewi Construction Girendra | 2025-04 | 193.85 | 175.43 | TA416 | 3 | 180-200
Dewi Construction Girendra | 2025-05 | 216.33 | 220.62 | TA416 | 5 | 200-220
Dewi Construction Girendra | 2025-06 | 28.25 | 42.37 | TA416 | 1 | <80
Dhaneshwar | 2025-06 | 98.74 | 0 |  | 0 | 80-100
Dhaneshwar | 2025-07 | 127.86 | 0 |  | 0 | 120-140
Dhaneshwar | 2025-08 | 85.74 | 173.13 | TA325 | 1 | 80-100
Dhaneshwar | 2025-09 | 33.91 | 173.13 | TA325 | 1 | <80
Dhaneshwar Mahto Modina India 4 Prayag Rupesh Kumar | 2025-10 | 29.12 | 0 |  | 0 | <80
Dhaneshwar Mahto Modina India 4 Prayag Rupesh Kumar | 2025-11 | 67.21 | 0 |  | 0 | <80
Dhaneshwar Mahto Modina India 4 Prayag Rupesh Kumar | 2025-12 | 60.49 | 156.83 | TA325 | 1 | <80
Dhaneswar Mahto | 2024-09 | 112.42 | 112.42 | TA325 | 1 | 100-120
Dhaneswar Mahto | 2024-10 | 67.07 | 0 |  | 0 | <80
Dhaneswar Mahto | 2024-11 | 169.33 | 221.98 | TA325 | 4 | 160-180
Dhaneswar Mahto | 2024-12 | 204.66 | 183.38 | TA325 | 3 | 200-220
Dhaneswar Mahto | 2025-01 | 176.5 | 193.34 | TA325 | 4 | 160-180
Dhaneswar Mahto | 2025-02 | 256.09 | 223.35 | TA325 | 4 | 240-260
Dhaneswar Mahto | 2025-03 | 248.82 | 300.41 | TA325 | 3 | 240-260
Dhaneswar Mahto | 2025-04 | 121.76 | 37.73 | TA325 | 1 | 120-140
Dhaneswar Mahto | 2025-05 | 76.51 | 160.54 | TA325 | 2 | <80
Dharmendra Munnilal Pusplata | 2025-07 | 38.85 | 38.85 | TB408 | 1 | <80
Dhruv Enterprises | 2025-11 | 48.83 | 0 |  | 0 | <80
Dhruv Enterprises | 2025-12 | 64.82 | 73.24 | TA419 | 1 | <80
Dhruv Enterprises | 2026-01 | 3.37 | 43.78 | TA419 | 1 | <80
Dhruv Enterprises 2 | 2026-01 | 42.37 | 42.37 | TA419 | 1 | <80
Dildar Electrical 1 | 2025-12 | 5.2 | 0 |  | 0 | <80
Dildar Electrical 1 | 2026-01 | 39.84 | 45.04 | TA414 | 1 | <80
Dildar Electrical 2 | 2026-01 | 72.46 | 72.46 | TA414 | 1 | <80
Dildar Electrical 2 4 Pgcil | 2025-10 | 9.7 | 0 |  | 0 | <80
Dildar Electrical 2 4 Pgcil | 2025-11 | 97.01 | 0 |  | 0 | 80-100
Dildar Electrical 2 4 Pgcil | 2025-12 | 22.63 | 129.34 | TA325 | 1 | <80
Dildar Electrical 2 Pgcil | 2025-10 | 39.46 | 39.46 | TA325 | 1 | <80
Dildar Electrical 3 | 2025-10 | 37.73 | 37.73 | TA325 | 1 | <80
Dildar Electricals | 2025-03 | 3.13 | 0 |  | 0 | <80
Dildar Electricals | 2025-04 | 5.22 | 0 |  | 0 | <80
Dildar Electricals | 2025-05 | 5.4 | 0 |  | 0 | <80
Dildar Electricals | 2025-06 | 5.22 | 0 |  | 0 | <80
Dildar Electricals | 2025-07 | 5.4 | 0 |  | 0 | <80
Dildar Electricals | 2025-08 | 5.4 | 0 |  | 0 | <80
Dildar Electricals | 2025-09 | 5.22 | 0 |  | 0 | <80
Dildar Electricals | 2025-10 | 1.04 | 36.04 | TA325 | 1 | <80
Dildar Electricals 1 Pgcil | 2025-10 | 39.46 | 39.46 | TA325 | 1 | <80
Dildar Electricals 1 Pgcil | 2025-11 | 37.73 | 37.73 | TA325 | 1 | <80
Dildar Electricals 1 Pgcil Prayag Mahto Nasirudin 2 | 2025-11 | 3.73 | 0 |  | 0 | <80
Dildar Electricals 1 Pgcil Prayag Mahto Nasirudin 2 | 2025-12 | 115.75 | 0 |  | 0 | 100-120
Dildar Electricals 1 Pgcil Prayag Mahto Nasirudin 2 | 2026-01 | 37.34 | 156.83 | TA325 | 1 | <80
Dipak | 2025-06 | 19.2 | 12 | TB507 | 1 | <80
Dipak | 2025-07 | 97.35 | 104.55 | TB507 | 9 | 80-100
Dipak | 2025-08 | 95.73 | 95.73 | TB507 | 6 | 80-100
Dipak | 2025-09 | 83.95 | 81.27 | TB507 | 6 | 80-100
Dipak | 2025-10 | 95.85 | 83.05 | TB507 | 4 | 80-100
Dipak | 2025-11 | 74.71 | 85.37 | TB507 | 4 | <80
Dipak | 2025-12 | 16.86 | 21.67 | TB507 | 1 | <80
Dk Construction Sarvan Kumar | 2026-01 | 204.8 | 204.8 | TA414 | 3 | 200-220
Dk Verma | 2024-09 | 13.54 | 0 |  | 0 | <80
Dk Verma | 2024-10 | 101.47 | 72.24 | TA325 | 1 | 100-120
Dk Verma | 2024-11 | 44.25 | 0 |  | 0 | <80
Dk Verma | 2024-12 | 126.39 | 181.29 | TA325 | 3 | 120-140
Dk Verma | 2025-01 | 214.29 | 228.28 | TA325 | 3 | 200-220
Dk Verma | 2025-02 | 176.65 | 131.61 | TA325 | 3 | 160-180
Dk Verma | 2025-03 | 203.49 | 197.58 | TA325 | 3 | 200-220
Dk Verma | 2025-04 | 147.86 | 190.14 | TA325 | 2 | 140-160
Dk Verma | 2025-05 | 156.44 | 127.03 | TA325 | 2 | 140-160
Dk Verma | 2025-06 | 141.96 | 112.42 | TA325 | 1 | 140-160
Dk Verma | 2025-07 | 32.77 | 80.41 | TA325 | 1 | <80
Dk Verma | 2025-08 | 19.37 | 0 |  | 0 | <80
Dk Verma | 2025-09 | 18.75 | 0 |  | 0 | <80
Dk Verma | 2025-10 | 19.37 | 0 |  | 0 | <80
Dk Verma | 2025-11 | 103.04 | 84.3 | TA325 | 1 | 100-120
Dk Verma | 2025-12 | 15 | 129.34 | TA325 | 1 | <80
Dudhnath | 2025-08 | 6.91 | 6.91 | TB501 | 1 | <80
Dudhnath Kumar | 2025-02 | 42.12 | 42.12 | TB501 | 8 | <80
Dudhnath Kumar | 2025-03 | 70.27 | 70.27 | TB501 | 12 | <80
Dudhnath Kumar | 2025-04 | 67.84 | 67.84 | TB501 | 10 | <80
Dudhnath Kumar | 2025-05 | 11.99 | 11.99 | TB501 | 1 | <80
Dudhnath Kumar | 2025-06 | 87.45 | 87.45 | TB501 | 12 | 80-100
Dudhnath Kumar | 2025-07 | 50.8 | 50.8 | TB501 | 6 | <80
Dudhnath Kumar | 2025-08 | 16.06 | 16.06 | TB501 | 2 | <80
Dular Chand Patel | 2025-11 | 37.5 | 37.5 | TB408 | 1 | <80
Dular Chand Patel | 2025-12 | 31.82 | 0 |  | 0 | <80
Dular Chand Patel | 2026-01 | 5.68 | 37.5 | TB408 | 1 | <80
Eagle Enterprises | 2025-03 | 79.96 | 79.96 | TA505 | 2 | <80
Eagle Enterprises | 2025-04 | 34.79 | 34.79 | TA505 | 1 | <80
Eagle Enterprises Paramand | 2025-04 | 104.46 | 70.39 | TA505 | 2 | 100-120
Eagle Enterprises Paramand | 2025-05 | 109.1 | 119.67 | TA505 | 3 | 100-120
Eagle Enterprises Paramand | 2025-06 | 62.26 | 72.32 | TA505 | 2 | <80
Eagle Enterprises Paramand | 2025-07 | 32.26 | 45.7 | TA505 | 1 | <80
Enjamul Haque | 2025-10 | 30.29 | 0 |  | 0 | <80
Enjamul Haque | 2025-11 | 41.94 | 72.24 | TA325 | 1 | <80
Fatima | 2025-09 | 21 | 21 | TA506 | 1 | <80
Fatima 1 | 2025-09 | 27 | 27 | TA506 | 1 | <80
Fouzi Ratto | 2025-07 | 50.35 | 0 |  | 0 | <80
Fouzi Ratto | 2025-08 | 232.5 | 253.71 | TA413 | 5 | 220-240
Fouzi Ratto | 2025-09 | 196.73 | 220.42 | TA413 | 5 | 180-200
Fouzi Ratto | 2025-10 | 118.51 | 70.79 | TA413 | 1 | 100-120
Fouzi Ratto | 2025-11 | 71.78 | 124.95 | TA413 | 1 | <80
Gagan Enterprise 1 | 2025-03 | 4.71 | 0 |  | 0 | <80
Gagan Enterprise 1 | 2025-04 | 228.37 | 226.5 | TA416 | 5 | 220-240
Gagan Enterprise 1 | 2025-05 | 244.67 | 251.25 | TA416 | 5 | 240-260
Gagan Enterprise 1 | 2025-06 | 188.38 | 188.38 | TA416 | 1 | 180-200
Gagan Enterprise 1 | 2025-07 | 127.43 | 0 |  | 0 | 120-140
Gagan Enterprise 1 | 2025-08 | 149.72 | 188.38 | TA416 | 1 | 140-160
Gagan Enterprise 1 | 2025-09 | 8.88 | 97.65 | TA416 | 1 | <80
Gagan Enterprise 2 | 2025-04 | 196.91 | 196.91 | TA416 | 3 | 180-200
Gagan Enterprise 2 | 2025-05 | 84.75 | 84.75 | TA416 | 2 | 80-100
Gagan Enterprise 2 Kajol | 2025-08 | 46.05 | 46.05 | TA416 | 1 | <80
Gagan Enterprises | 2025-03 | 2.58 | 0 |  | 0 | <80
Gagan Enterprises | 2025-04 | 131.36 | 114.75 | TA419 | 3 | 120-140
Gagan Enterprises | 2025-05 | 63.95 | 83.13 | TA419 | 1 | <80
Ganesg Sinha | 2025-12 | 45.41 | 45.41 | TB401 | 1 | <80
Ganesh | 2024-05 | 111.79 | 111.79 | TB408 | 2 | 100-120
Ganesh | 2025-11 | 7.06 | 0 |  | 0 | <80
Ganesh | 2025-12 | 90.65 | 97.71 | TA419 | 2 | 80-100
Ganesh 1 | 2025-12 | 25.42 | 0 |  | 0 | <80
Ganesh 1 | 2026-01 | 84.06 | 109.49 | TA419 | 2 | 80-100
Ganesh 2 | 2025-11 | 11.51 | 0 |  | 0 | <80
Ganesh 2 | 2025-12 | 95.46 | 42.37 | TA419 | 1 | 80-100
Ganesh 2 | 2026-01 | 89.71 | 154.31 | TA419 | 3 | 80-100
Ganesh Const | 2024-02 | 180.57 | 176.64 | TB408 | 4 | 180-200
Ganesh Const | 2024-03 | 164.65 | 163.73 | TB408 | 4 | 160-180
Ganesh Const | 2024-04 | 79.4 | 84.26 | TB408 | 2 | <80
Ganesh Kr Sinha | 2023-09 | 12.5 | 0 |  | 0 | <80
Ganesh Kr Sinha | 2023-10 | 105.82 | 115.2 | TB401 | 3 | 100-120
Ganesh Kr Sinha | 2023-11 | 108.19 | 76.35 | TB401 | 2 | 100-120
Ganesh Kr Sinha | 2023-12 | 166.49 | 190.21 | TB401 | 5 | 160-180
Ganesh Kr Sinha | 2024-01 | 160.2 | 152.7 | TB401 | 3 | 160-180
Ganesh Kr Sinha | 2024-02 | 18.75 | 37.5 | TB401 | 1 | <80
Ganesh Kr Sinha | 2024-04 | 87.98 | 69.23 | TB401 | 1 | 80-100
Ganesh Kr Sinha | 2024-05 | 18.75 | 37.5 | TB401 | 1 | <80
Ganesh Kr Sinha | 2024-10 | 57.63 | 47.18 | TB401 | 1 | <80
Ganesh Kr Sinha | 2024-11 | 57.43 | 67.87 | TB401 | 1 | <80
Ganesh Kr Sinha | 2024-12 | 120.79 | 120.79 | TB401 | 2 | 120-140
Ganesh Kr Sinha | 2025-01 | 3.72 | 0 |  | 0 | <80
Ganesh Kr Sinha | 2025-02 | 124.58 | 128.3 | TB401 | 2 | 120-140
Ganesh Kr Sinha | 2025-04 | 6.06 | 0 |  | 0 | <80
Ganesh Kr Sinha | 2025-05 | 39.36 | 45.41 | TB401 | 1 | <80
Ganesh Sinha | 2024-08 | 9.83 | 0 |  | 0 | <80
Ganesh Sinha | 2024-09 | 82.77 | 92.6 | TB408 | 2 | 80-100
Ganesh Sinha | 2024-10 | 84.26 | 84.26 | TB408 | 2 | 80-100
Ganesh Sinha | 2024-11 | 66.61 | 47.18 | TB408 | 1 | <80
Ganesh Sinha | 2024-12 | 19.42 | 38.85 | TB408 | 1 | <80
Ganesh Sinha | 2025-01 | 123.11 | 123.11 | TB408 | 3 | 120-140
Ganesh Sinha | 2025-03 | 159.27 | 159.27 | TB408 | 4 | 140-160
Ganesh Sinha | 2025-04 | 117.89 | 117.89 | TB408 | 2 | 100-120
Ganesh Sinha | 2025-08 | 46.88 | 37.5 | TB408 | 1 | <80
Ganesh Sinha | 2025-09 | 139.72 | 140.51 | TB408 | 3 | 120-140
Ganesh Sinha | 2025-10 | 166.83 | 170.72 | TB401, TB408 | 4 | 160-180
Ganesh Sinha | 2025-11 | 183.46 | 188.15 | TB408 | 4 | 180-200
Ganesh Sinha | 2025-12 | 89.14 | 75.01 | TB408 | 2 | 80-100
Ganesh Sinha | 2026-01 | 24.72 | 38.85 | TB408 | 1 | <80
Gang 01 Sanjay | 2024-01 | 1.88 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-02 | 2.19 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-03 | 2.34 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-04 | 2.26 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-05 | 2.34 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-06 | 2.26 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-07 | 2.34 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-08 | 2.34 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-09 | 2.26 | 0 |  | 0 | <80
Gang 01 Sanjay | 2024-10 | 42.72 | 27.96 | TA418 | 1 | <80
Gang 01 Sanjay | 2024-11 | 124.97 | 111.84 | TA418 | 4 | 120-140
Gang 01 Sanjay | 2024-12 | 131.64 | 142.12 | TA418 | 5 | 120-140
Gang 01 Sanjay | 2025-01 | 108.14 | 140.92 | TA418 | 5 | 100-120
Gang 01 Sanjay | 2025-02 | 182.67 | 165 | TA418 | 5 | 180-200
Gang 01 Sanjay | 2025-03 | 67.5 | 90 | TA418 | 2 | <80
Gang 01 Sanjay | 2025-04 | 105.44 | 99 | TA418 | 2 | 100-120
Gang 01 Sanjay | 2025-05 | 100.76 | 91 | TA418 | 3 | 100-120
Gang 01 Sanjay | 2025-06 | 81.18 | 54 | TA418 | 2 | 80-100
Gang 01 Sanjay | 2025-07 | 3.62 | 47 | TA418 | 1 | <80
Gang 02 Sanjay | 2024-01 | 1.72 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-02 | 2.17 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-03 | 2.32 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-04 | 2.25 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-05 | 2.32 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-06 | 2.25 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-07 | 2.32 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-08 | 2.32 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-09 | 2.25 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-10 | 2.32 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-11 | 2.25 | 0 |  | 0 | <80
Gang 02 Sanjay | 2024-12 | 99.09 | 90.55 | TA418 | 3 | 80-100
Gang 02 Sanjay | 2025-01 | 85.86 | 84.92 | TA418 | 3 | 80-100
Gang 02 Sanjay | 2025-02 | 23.01 | 57 | TA418 | 2 | <80
Gang 02 Sanjay | 2025-03 | 201.4 | 179 | TA418 | 4 | 200-220
Gang 02 Sanjay | 2025-04 | 175.39 | 178 | TA418 | 5 | 160-180
Gang 02 Sanjay | 2025-05 | 123.84 | 134.63 | TA418 | 4 | 120-140
Gang 02 Sanjay | 2025-06 | 128 | 137 | TA418 | 4 | 120-140
Gang 02 Sanjay | 2025-07 | 54 | 54 | TA418 | 1 | <80
Gang 02 Sanjay Kec 02 Barkat Ali | 2025-07 | 16.57 | 0 |  | 0 | <80
Gang 02 Sanjay Kec 02 Barkat Ali | 2025-08 | 12.43 | 29 | TA418 | 1 | <80
Gauri Shankar | 2025-08 | 70.7 | 70.7 | TB408 | 1 | <80
Gauri Shankar Mahto | 2025-11 | 33.97 | 0 |  | 0 | <80
Gauri Shankar Mahto | 2025-12 | 118.56 | 139.83 | TA421 | 2 | 100-120
Gauri Shankar Mahto | 2026-01 | 80.81 | 93.51 | TA421 | 2 | 80-100
Ghanshyam Mahto | 2023-09 | 2.36 | 0 |  | 0 | <80
Ghanshyam Mahto | 2023-10 | 73.1 | 75.46 | TA325 | 2 | <80
Ghanshyam Mahto | 2023-11 | 110.29 | 75.46 | TA325 | 2 | 100-120
Ghanshyam Mahto | 2023-12 | 40.63 | 75.46 | TA325 | 2 | <80
Ghanshyam Mahto | 2024-07 | 18.87 | 0 |  | 0 | <80
Ghanshyam Mahto | 2024-08 | 24.01 | 37.73 | TA325 | 1 | <80
Ghanshyam Mahto | 2024-09 | 68.12 | 64.25 | TA325 | 1 | <80
Ghanshyam Mahto | 2024-10 | 45.9 | 36.04 | TA325 | 1 | <80
Ghanshyam Mahto | 2024-11 | 40.63 | 37.73 | TA325 | 1 | <80
Ghanshyam Mahto | 2024-12 | 80.76 | 97.93 | TA325 | 1 | 80-100
Ghanshyam Mahto | 2025-01 | 109.59 | 64.25 | TA325 | 1 | 100-120
Ghanshyam Mahto | 2025-02 | 75.27 | 125.19 | TA325 | 2 | <80
Ghyansham Mahto | 2025-08 | 13.5 | 0 |  | 0 | <80
Ghyansham Mahto | 2025-09 | 101.5 | 103 | TA504 | 2 | 100-120
Ghyansham Mahto | 2025-10 | 111.88 | 60 | TA504 | 1 | 100-120
Ghyansham Mahto | 2025-11 | 147.66 | 146 | TA504 | 2 | 140-160
Ghyansham Mahto | 2025-12 | 128.46 | 194 | TA504 | 3 | 120-140
Ghyansham Mahto | 2026-01 | 62 | 62 | TA504 | 1 | <80
Gokul 1 | 2025-10 | 46.62 | 46.62 | TA325 | 1 | <80
Gokul Rajwanshi | 2025-03 | 39.66 | 34.79 | TA505 | 1 | <80
Gokul Rajwanshi | 2025-04 | 113.03 | 117.9 | TA505 | 3 | 100-120
Gokul Rajwanshi | 2025-05 | 186.11 | 186.11 | TA505 | 5 | 180-200
Gokul Rajwanshi | 2025-06 | 149.54 | 149.54 | TA505 | 4 | 140-160
Gokul Rajwanshi | 2025-07 | 152.13 | 152.13 | TA505 | 4 | 140-160
Gokul Rajwanshi | 2025-08 | 153.76 | 108.04 | TA505 | 2 | 140-160
Gokul Rajwanshi | 2025-09 | 145.89 | 191.61 | TA505 | 4 | 140-160
Gokul Sarkar | 2025-08 | 15.92 | 11.14 | TB507 | 1 | <80
Gokul Sarkar | 2025-09 | 76.88 | 78.87 | TB507 | 7 | <80
Gokul Sarkar | 2025-10 | 98.63 | 87.4 | TB507 | 6 | 80-100
Gokul Sarkar | 2025-11 | 90.3 | 96 | TB507 | 4 | 80-100
Gokul Sarkar | 2025-12 | 97.42 | 76.84 | TB507 | 3 | 80-100
Gokul Sarkar | 2026-01 | 25.08 | 53.97 | TB507 | 2 | <80
Gokul Sarkar 1 | 2025-10 | 36.04 | 36.04 | TA325 | 1 | <80
Gokul Sarkar 1 | 2025-11 | 84.19 | 84.19 | TA325 | 2 | 80-100
Gokul Sarkar 2 | 2025-10 | 122.62 | 122.62 | TA325 | 2 | 120-140
Gokul Sarkar 2 | 2025-11 | 143.56 | 143.56 | TA325 | 2 | 140-160
Gokul Sarkar Mp | 2025-09 | 34.79 | 34.79 | TA505 | 1 | <80
Gokul Sarkar Mp | 2025-12 | 143.67 | 143.67 | TA505 | 4 | 140-160
Gokul Sarkar Mp | 2026-01 | 174.67 | 174.67 | TA505 | 3 | 160-180
Gokul Sarkar Mp | 2026-02 | 37.93 | 37.93 | TA505 | 1 | <80
Gokul Sarkar Mp 2 | 2025-12 | 119.75 | 107.11 | TA505 | 3 | 100-120
Gokul Sarkar Mp 2 | 2026-01 | 142.99 | 108.88 | TA505 | 3 | 140-160
Gokul Sarkar Mp 2 | 2026-02 | 12.75 | 59.5 | TA505 | 1 | <80
Gouri Shankar | 2025-08 | 35.51 | 0 |  | 0 | <80
Gouri Shankar | 2025-09 | 140.82 | 176.33 | TA416 | 2 | 140-160
Gourishankar | 2024-06 | 148.46 | 118.86 | TA325 | 2 | 140-160
Gourishankar | 2024-07 | 136.72 | 156.42 | TA325 | 3 | 120-140
Gourishankar | 2024-08 | 108.79 | 118.67 | TA325 | 2 | 100-120
Gourishankar | 2024-09 | 108.28 | 108.28 | TA325 | 2 | 100-120
Gourishankar | 2024-10 | 212.93 | 212.93 | TA325 | 3 | 200-220
Gourishankar | 2024-11 | 123.1 | 56.86 | TA325 | 1 | 120-140
Gourishankar | 2024-12 | 227.68 | 238.64 | TA325 | 3 | 220-240
Gourishankar | 2025-01 | 182.9 | 192.83 | TA325 | 2 | 180-200
Gourishankar | 2025-02 | 217.98 | 221.18 | TA325 | 4 | 200-220
Gourishankar | 2025-03 | 228.88 | 271.03 | TA325 | 4 | 220-240
Gourishankar | 2025-04 | 237.22 | 174.82 | TA325 | 2 | 220-240
Gourishankar | 2025-05 | 176.99 | 207.28 | TA325 | 3 | 160-180
Gourishankar | 2025-06 | 99.79 | 126.66 | TA325 | 2 | 80-100
Gourishankar | 2025-07 | 183.8 | 189.04 | TB401 | 4 | 180-200
Gourishankar | 2025-08 | 47.18 | 47.18 | TB401 | 1 | <80
Govind Mahto | 2025-09 | 84 | 75 | TA506 | 3 | 80-100
Govind Mahto | 2025-10 | 106.5 | 99 | TA506 | 4 | 100-120
Govind Mahto | 2025-11 | 93 | 92 | TA506 | 4 | 80-100
Govind Mahto | 2025-12 | 61.5 | 79 | TA506 | 3 | <80
Govind Mahto | 2026-01 | 73 | 73 | TA506 | 3 | <80
Govind Mahto 1 | 2025-08 | 59.04 | 43.8 | TA413 | 1 | <80
Govind Mahto 1 | 2025-09 | 137.11 | 133.3 | TA413 | 3 | 120-140
Govind Mahto 1 | 2025-10 | 146.15 | 154.58 | TA413 | 4 | 140-160
Govind Mahto 1 | 2025-11 | 137.11 | 147.72 | TA413 | 3 | 120-140
Govind Mahto 1 | 2025-12 | 36.16 | 36.16 | TA413 | 1 | <80
Govind Mahto 2 | 2025-08 | 21.33 | 0 |  | 0 | <80
Govind Mahto 2 | 2025-09 | 135.1 | 156.42 | TA413 | 3 | 120-140
Govind Mahto 2 | 2025-10 | 143.37 | 137.05 | TA413 | 1 | 140-160
Govind Mahto 2 | 2025-11 | 167.82 | 149.11 | TA413 | 3 | 160-180
Govind Mahto 2 | 2025-12 | 54.93 | 79.96 | TA413 | 2 | <80
Gowrishankar | 2025-11 | 37.93 | 37.93 | TA421 | 1 | <80
Gulab Mahto | 2025-10 | 98 | 89 | TA506 | 5 | 80-100
Gulab Mahto | 2025-11 | 71 | 80 | TA506 | 4 | <80
Harsh Vivek | 2025-11 | 8.67 | 8.67 | TB501 | 2 | <80
Hassan | 2025-05 | 74.3 | 74.3 | TA421 | 2 | <80
Hassan | 2025-06 | 154.25 | 132.43 | TA421 | 3 | 140-160
Hassan | 2025-07 | 131.78 | 99.53 | TA421 | 2 | 120-140
Hassan | 2025-08 | 143.17 | 184.44 | TA421 | 3 | 140-160
Hassan | 2025-09 | 148.82 | 150.44 | TA421 | 3 | 140-160
Hassan | 2025-10 | 93.88 | 74.3 | TA421 | 2 | 80-100
Hassan | 2025-11 | 144.07 | 174.84 | TA421 | 3 | 140-160
Hassan 2 | 2025-06 | 22.13 | 0 |  | 0 | <80
Hassan 2 | 2025-07 | 118.96 | 141.08 | TA421 | 3 | 100-120
Hazarilal Yadav Poonam Kumari | 2025-07 | 76.35 | 76.35 | TB408 | 2 | <80
Horel Mahto | 2025-12 | 108 | 101 | TA504 | 2 | 100-120
Horel Mahto | 2026-01 | 28 | 35 | TA504 | 1 | <80
Horil | 2025-09 | 122 | 122 | TA506 | 5 | 120-140
Horil Mahto | 2024-09 | 41.04 | 0 |  | 0 | <80
Horil Mahto | 2024-10 | 138.61 | 179.65 | TA416 | 4 | 120-140
Horil Mahto | 2024-11 | 103.04 | 92.1 | TA416 | 2 | 100-120
Horil Mahto | 2024-12 | 124.93 | 135.87 | TA416 | 3 | 120-140
Horil Mahto | 2025-01 | 107.83 | 92.1 | TA416 | 2 | 100-120
Horil Mahto | 2025-02 | 152.38 | 163.25 | TA416 | 3 | 140-160
Horil Mahto | 2025-03 | 125.06 | 129.93 | TA416 | 3 | 120-140
Horil Mahto | 2025-04 | 46.05 | 46.05 | TA416 | 1 | <80
Horil Mahto | 2025-09 | 8.4 | 0 |  | 0 | <80
Horil Mahto | 2025-10 | 168.4 | 166 | TA506 | 7 | 160-180
Horil Mahto | 2025-11 | 172.37 | 177 | TA506 | 6 | 160-180
Horil Mahto | 2025-12 | 30.83 | 37 | TA506 | 1 | <80
Horil Mahto | 2026-01 | 101 | 101 | TA506 | 4 | 100-120
Horil Mahto | 2026-02 | 28 | 28 | TA506 | 1 | <80
Imadul Haque | 2025-10 | 57.89 | 0 |  | 0 | <80
Imadul Haque | 2025-11 | 22.51 | 80.41 | TA325 | 1 | <80
Imadul Haque Enjamul Haque | 2025-11 | 56.86 | 56.86 | TA325 | 1 | <80
Infinedea 1 | 2025-12 | 36.16 | 36.16 | TA419 | 1 | <80
Infinidea | 2025-07 | 2.78 | 0 |  | 0 | <80
Infinidea | 2025-08 | 98.74 | 36.16 | TA419 | 1 | 80-100
Infinidea | 2025-09 | 43.71 | 95.89 | TA419 | 2 | <80
Infinidea | 2025-10 | 51.06 | 0 |  | 0 | <80
Infinidea | 2025-11 | 8.24 | 72.47 | TA419 | 1 | <80
Infinidea 2 | 2025-11 | 37.93 | 37.93 | TA419 | 1 | <80
Infinidea 2 | 2025-12 | 67.77 | 37.14 | TA419 | 1 | <80
Infinidea 2 | 2026-01 | 7.29 | 37.93 | TA419 | 1 | <80
Intizer Infratech | 2024-05 | 78.89 | 75.46 | TA325 | 2 | <80
Intizer Infratech | 2024-06 | 34.3 | 37.73 | TA325 | 1 | <80
J Lngh | 2025-02 | 101.27 | 79.45 | TA421 | 2 | 100-120
J Lngh | 2025-03 | 161.59 | 183.41 | TA421 | 5 | 160-180
J Lngh O 1 | 2025-03 | 51.96 | 36.37 | TA421 | 1 | <80
J Lngh O 1 | 2025-04 | 162.77 | 178.36 | TA421 | 4 | 160-180
J Lngh O 1 | 2025-05 | 36.37 | 36.37 | TA421 | 1 | <80
J Lngh O 2 | 2025-03 | 48.32 | 37.93 | TA421 | 1 | <80
J Lngh O 2 | 2025-04 | 138.21 | 148.6 | TA421 | 4 | 120-140
Jabir Hussian | 2025-12 | 25.36 | 0 |  | 0 | <80
Jabir Hussian | 2026-01 | 114.27 | 139.63 | TA414 | 3 | 100-120
Jagannaath Saw Mp | 2025-09 | 54.24 | 37.93 | TA505 | 1 | <80
Jagannaath Saw Mp | 2025-10 | 126.87 | 91.61 | TA505 | 2 | 120-140
Jagannaath Saw Mp | 2025-11 | 199.4 | 221.76 | TA505 | 4 | 180-200
Jagannaath Saw Mp | 2025-12 | 169.42 | 193.76 | TA505 | 5 | 160-180
Jagannaath Saw Mp | 2026-01 | 144.68 | 149.54 | TA505 | 4 | 140-160
Jagdish Mahto | 2024-08 | 15 | 0 |  | 0 | <80
Jagdish Mahto | 2024-09 | 224.48 | 230.4 | TB401, TB408 | 6 | 220-240
Jagdish Mahto | 2024-10 | 223.71 | 199.46 | TB401, TB408 | 5 | 220-240
Jagdish Mahto | 2024-11 | 223.11 | 251.65 | TB401, TB408 | 6 | 220-240
Jagdish Mahto | 2024-12 | 141.59 | 125.47 | TB401, TB408 | 2 | 140-160
Jagdish Mahto | 2025-01 | 17.93 | 38.85 | TB401 | 1 | <80
Jai Prakash Mahto | 2025-09 | 24.55 | 0 |  | 0 | <80
Jai Prakash Mahto | 2025-10 | 173.95 | 176 | TA506 | 5 | 160-180
Jai Prakash Mahto | 2025-11 | 123.83 | 141 | TA506 | 6 | 120-140
Jai Prakash Mahto | 2025-12 | 50.67 | 56 | TA506 | 2 | <80
Jai Prakash Mahto | 2026-01 | 85 | 85 | TA506 | 3 | 80-100
Jailal Ageria | 2024-08 | 12.5 | 0 |  | 0 | <80
Jailal Ageria | 2024-09 | 120.78 | 113.86 | TB401, TB408 | 3 | 120-140
Jailal Ageria | 2024-10 | 173.77 | 171.61 | TB401, TB408 | 3 | 160-180
Jailal Ageria | 2024-11 | 148.19 | 154.05 | TB401, TB408 | 4 | 140-160
Jailal Ageria | 2024-12 | 117.59 | 133.31 | TB401, TB408 | 2 | 100-120
Jaman Mahto 1 Ratna Devi | 2025-10 | 143.59 | 77.72 | TA325 | 1 | 140-160
Jaman Mahto 1 Ratna Devi | 2025-11 | 167.12 | 141.87 | TA325 | 1 | 160-180
Jaman Mahto 1 Ratna Devi | 2025-12 | 83.7 | 174.82 | TA325 | 2 | 80-100
Javir Hossen | 2025-10 | 57.79 | 0 |  | 0 | <80
Javir Hossen | 2025-11 | 22.61 | 80.41 | TA325 | 1 | <80
Javir Hossen Enjamul Haque | 2025-11 | 68.59 | 0 |  | 0 | <80
Javir Hossen Enjamul Haque | 2025-12 | 6.86 | 75.45 | TA325 | 1 | <80
Jawala Singh | 2025-08 | 37.5 | 37.5 | TB401 | 1 | <80
Jawala Singh Suraj | 2025-08 | 45.41 | 45.41 | TB401 | 1 | <80
Jay Prakash | 2025-09 | 100 | 100 | TA506 | 3 | 100-120
Jhemon Mahato 1 | 2025-08 | 36.62 | 0 |  | 0 | <80
Jhemon Mahato 1 | 2025-09 | 153.06 | 189.68 | TA505 | 3 | 140-160
Jhemon Mahato 1 | 2025-12 | 103.27 | 97.17 | TA505 | 1 | 100-120
Jhemon Mahato 1 | 2026-01 | 190.32 | 196.43 | TA505 | 3 | 180-200
Jhemon Mahato 2 | 2025-08 | 14.75 | 0 |  | 0 | <80
Jhemon Mahato 2 | 2025-09 | 97.23 | 74.09 | TA505 | 2 | 80-100
Jhemon Mahato 2 | 2025-10 | 135.53 | 123.2 | TA505 | 2 | 120-140
Jhemon Mahato 2 | 2025-11 | 121.52 | 171.75 | TA505 | 4 | 120-140
Jhemon Mahato 2 | 2025-12 | 75.28 | 75.28 | TA505 | 1 | <80
Jirwa Devi | 2024-09 | 58.36 | 45.41 | TB401 | 1 | <80
Jirwa Devi | 2024-10 | 106.84 | 86.03 | TB401 | 2 | 100-120
Jirwa Devi | 2024-11 | 106 | 113.86 | TB408 | 3 | 100-120
Jirwa Devi | 2024-12 | 128.09 | 142.73 | TB401, TB408 | 3 | 120-140
Jirwa Devi | 2025-01 | 132.93 | 133.95 | TB401 | 3 | 120-140
Jirwa Devi | 2025-02 | 112.48 | 106.73 | TB401 | 2 | 100-120
Jirwa Devi | 2025-03 | 53.25 | 69.23 | TB408 | 1 | <80
Jirwa Devi | 2025-08 | 47.18 | 47.18 | TB408 | 1 | <80
Jirwa Devi | 2025-09 | 140.9 | 138.01 | TB408 | 3 | 140-160
Jirwa Devi | 2025-10 | 120.88 | 82.92 | TB408 | 2 | 120-140
Jirwa Devi | 2025-11 | 148.84 | 170.27 | TB401, TB408 | 3 | 140-160
Jirwa Devi | 2025-12 | 128.25 | 135.29 | TB401, TB408 | 3 | 120-140
Jirwa Devi | 2026-01 | 33.03 | 45.41 | TB408 | 1 | <80
Jwala | 2024-11 | 55.88 | 37.73 | TA325 | 1 | <80
Jwala | 2024-12 | 186.49 | 195.65 | TA325 | 3 | 180-200
Jwala | 2025-01 | 245.99 | 242.4 | TA325 | 3 | 240-260
Jwala | 2025-02 | 171.87 | 184.44 | TA325 | 4 | 160-180
Jwala | 2025-03 | 254.25 | 185.32 | TA325 | 5 | 240-260
Jwala | 2025-04 | 176.56 | 245.48 | TA325 | 4 | 160-180
Jwala | 2025-05 | 138.29 | 138.29 | TA325 | 2 | 120-140
Jwala Singh | 2025-01 | 165.36 | 165.36 | TA505 | 4 | 160-180
Jwala Singh | 2025-02 | 258.28 | 258.28 | TA505 | 7 | 240-260
Jwala Singh | 2025-03 | 307.94 | 293.48 | TA505 | 8 | >=260
Jwala Singh | 2025-04 | 275.86 | 283.8 | TA505 | 8 | >=260
Jwala Singh | 2025-05 | 230.25 | 229.48 | TA505 | 6 | 220-240
Jwala Singh | 2025-06 | 281.65 | 257.87 | TA505, TB408 | 6 | >=260
Jwala Singh | 2025-07 | 211.97 | 221.87 | TA505, TB408 | 5 | 200-220
Jwala Singh | 2025-08 | 420.04 | 375.02 | TA505, TB408 | 7 | >=260
Jwala Singh | 2025-09 | 223.49 | 289.69 | TA505, TB401, TB408 | 5 | 220-240
Jwala Singh | 2025-10 | 408.34 | 350.8 | TA325, TA419, TA505 | 5 | >=260
Jwala Singh | 2025-11 | 391.88 | 428.6 | TA325, TA419, TA505 | 9 | >=260
Jwala Singh | 2025-12 | 444.74 | 454.05 | TA419, TA505 | 12 | >=260
Jwala Singh | 2026-01 | 335.03 | 346.53 | TA419, TA505 | 5 | >=260
Jwala Singh 01 | 2025-05 | 72.74 | 72.74 | TA421 | 2 | <80
Jwala Singh 1 | 2025-05 | 23.04 | 0 |  | 0 | <80
Jwala Singh 1 | 2025-06 | 117.48 | 140.51 | TB401 | 3 | 100-120
Jwala Singh 1 | 2025-07 | 84.54 | 45.7 | TA413 | 1 | 80-100
Jwala Singh 1 | 2025-08 | 196.41 | 218.83 | TA413 | 5 | 180-200
Jwala Singh 1 | 2025-09 | 248.3 | 240.67 | TA413, TB408 | 5 | 240-260
Jwala Singh 1 | 2025-10 | 116.98 | 110.09 | TA413 | 2 | 100-120
Jwala Singh 1 | 2025-11 | 127.63 | 147.62 | TA413 | 4 | 120-140
Jwala Singh 1 | 2025-12 | 132.55 | 116.12 | TA413 | 3 | 120-140
Jwala Singh 1 | 2026-01 | 124.75 | 152.13 | TA413 | 4 | 120-140
Jwala Singh 2 | 2025-03 | 9.48 | 0 |  | 0 | <80
Jwala Singh 2 | 2025-04 | 206.05 | 191.43 | TA505 | 5 | 200-220
Jwala Singh 2 | 2025-05 | 254.36 | 278.47 | TA505 | 7 | 240-260
Jwala Singh 2 | 2025-06 | 211.27 | 201.89 | TA505, TB401 | 5 | 200-220
Jwala Singh 2 | 2025-07 | 131.14 | 140.51 | TB401 | 3 | 120-140
Jwala Singh 2 | 2025-08 | 174.94 | 110.58 | TA413 | 2 | 160-180
Jwala Singh 2 | 2025-09 | 224.28 | 288.64 | TA413, TB408 | 6 | 220-240
Jwala Singh 2 | 2025-10 | 122.33 | 117.34 | TA413 | 3 | 120-140
Jwala Singh 2 | 2025-11 | 144.21 | 135.28 | TA413 | 3 | 140-160
Jwala Singh 2 | 2025-12 | 190.45 | 180.27 | TA413, TA505 | 4 | 180-200
Jwala Singh 2 | 2026-01 | 120.93 | 145.04 | TA505 | 4 | 120-140
Jwala Singh 3 | 2025-06 | 38.85 | 38.85 | TB401 | 1 | <80
Jwala Singh 3 | 2025-07 | 213.05 | 206.8 | TB401 | 3 | 200-220
Jwala Singh 3 | 2025-08 | 31.25 | 37.5 | TB401 | 1 | <80
Jwala Singh 3 Bhairo Mahto | 2025-08 | 35.68 | 0 |  | 0 | <80
Jwala Singh 3 Bhairo Mahto | 2025-09 | 50.96 | 0 |  | 0 | <80
Jwala Singh 3 Bhairo Mahto | 2025-10 | 42.47 | 129.11 | TB401 | 1 | <80
Jwala Singh Suraj Kumar | 2025-06 | 19.42 | 0 |  | 0 | <80
Jwala Singh Suraj Kumar | 2025-07 | 143.4 | 162.83 | TB408 | 3 | 140-160
Jyoti Const | 2025-08 | 39.58 | 0 |  | 0 | <80
Jyoti Const | 2025-09 | 120.55 | 160.13 | TA505 | 3 | 120-140
Jyoti Const | 2025-10 | 136.8 | 124.95 | TA505 | 1 | 120-140
Jyoti Const | 2025-11 | 87.96 | 81.74 | TA505 | 2 | 80-100
Jyoti Const | 2025-12 | 120.48 | 117.9 | TA505 | 3 | 120-140
Jyoti Const | 2026-01 | 165.82 | 186.48 | TA505 | 3 | 160-180
Kamlesh | 2025-10 | 70.7 | 70.7 | TB401 | 1 | <80
Kamlesh Kumar | 2025-10 | 11.16 | 0 |  | 0 | <80
Kamlesh Kumar | 2025-11 | 98.39 | 109.55 | TB408 | 2 | 80-100
Kamlesh Kumar | 2025-12 | 77.7 | 77.7 | TB408 | 2 | <80
Kamruddin | 2025-08 | 12.06 | 0 |  | 0 | <80
Kamruddin | 2025-09 | 60.31 | 0 |  | 0 | <80
Kamruddin | 2025-10 | 8.04 | 80.41 | TA325 | 1 | <80
Karam Mahto | 2025-08 | 4.97 | 0 |  | 0 | <80
Karam Mahto | 2025-09 | 44.61 | 36 | TA504 | 1 | <80
Karam Mahto | 2025-10 | 100.3 | 74 | TA504 | 2 | 100-120
Karam Mahto | 2025-11 | 99.08 | 82 | TA504 | 2 | 80-100
Karam Mahto | 2025-12 | 10.05 | 67 | TA504 | 1 | <80
Karni Const 1 | 2025-10 | 65 | 65 | TA506 | 4 | <80
Karni Const 1 | 2025-11 | 112.6 | 91 | TA506 | 4 | 100-120
Karni Const 1 | 2025-12 | 88.4 | 110 | TA506 | 4 | 80-100
Karni Const 2 | 2025-10 | 146.4 | 132 | TA506 | 4 | 140-160
Karni Const 2 | 2025-11 | 107.4 | 109 | TA506 | 4 | 100-120
Karni Const 2 | 2025-12 | 95.2 | 108 | TA506 | 4 | 80-100
Karni Const 2 | 2026-01 | 20 | 20 | TA506 | 1 | <80
Karni Const 3 | 2025-09 | 27.75 | 0 |  | 0 | <80
Karni Const 3 | 2025-10 | 121.25 | 149 | TA506 | 6 | 120-140
Karni Const 3 | 2025-11 | 110 | 110 | TA506 | 4 | 100-120
Karni Const 3 | 2025-12 | 63 | 63 | TA506 | 2 | <80
Karni Const 4 | 2025-09 | 4 | 0 |  | 0 | <80
Karni Const 4 | 2025-10 | 127.33 | 120 | TA506 | 5 | 120-140
Karni Const 4 | 2025-11 | 115 | 114 | TA506 | 4 | 100-120
Karni Const 4 | 2025-12 | 77.67 | 90 | TA506 | 2 | <80
Karni Const 5 | 2025-09 | 18.67 | 0 |  | 0 | <80
Karni Const 5 | 2025-10 | 105.33 | 112 | TA506 | 4 | 100-120
Karni Const 5 | 2025-11 | 92.4 | 72 | TA506 | 3 | 80-100
Karni Const 5 | 2025-12 | 3.6 | 36 | TA506 | 1 | <80
Karni Const 6 | 2025-09 | 14.4 | 0 |  | 0 | <80
Karni Const 6 | 2025-10 | 51.6 | 66 | TA506 | 4 | <80
Karni Const 6 | 2025-11 | 55 | 55 | TA506 | 2 | <80
Kartik Mahto | 2025-09 | 116.27 | 112.48 | TA413 | 2 | 100-120
Kartik Mahto | 2025-10 | 125.19 | 128.98 | TA413 | 3 | 120-140
Kaushalya Const | 2024-09 | 56.24 | 47.18 | TB408 | 1 | <80
Kaushalya Const | 2024-10 | 57.33 | 66.38 | TB408 | 1 | <80
Kaushalya Const | 2024-11 | 45.41 | 45.41 | TB408 | 1 | <80
Kec 01 Barkat Ali | 2025-06 | 1.45 | 0 |  | 0 | <80
Kec 01 Barkat Ali | 2025-07 | 106.48 | 84 | TA418 | 3 | 100-120
Kec 01 Barkat Ali | 2025-08 | 70.89 | 91.63 | TA418 | 3 | <80
Kec 01 Barkat Ali | 2025-09 | 31.82 | 35 | TA418 | 1 | <80
Kec 02 Barkat Ali | 2025-01 | 2.53 | 0 |  | 0 | <80
Kec 02 Barkat Ali | 2025-02 | 4.42 | 0 |  | 0 | <80
Kec 02 Barkat Ali | 2025-03 | 4.89 | 0 |  | 0 | <80
Kec 02 Barkat Ali | 2025-04 | 4.74 | 0 |  | 0 | <80
Kec 02 Barkat Ali | 2025-05 | 4.89 | 0 |  | 0 | <80
Kec 02 Barkat Ali | 2025-06 | 4.74 | 0 |  | 0 | <80
Kec 02 Barkat Ali | 2025-07 | 121.09 | 116.2 | TA418 | 3 | 120-140
Kec 02 Barkat Ali | 2025-08 | 90.06 | 82 | TA418 | 2 | 80-100
Kec 02 Barkat Ali | 2025-09 | 145.41 | 114.7 | TA418 | 2 | 140-160
Kec 02 Barkat Ali | 2025-10 | 68.08 | 83 | TA418 | 3 | <80
Kec 02 Barkat Ali | 2025-11 | 102.8 | 85 | TA418 | 3 | 100-120
Kec 02 Barkat Ali | 2025-12 | 82.96 | 88 | TA418 | 3 | 80-100
Kec 02 Barkat Ali | 2026-01 | 46.28 | 114 | TA418 | 3 | <80
Kewat Departmental | 2025-05 | 3.57 | 0 |  | 0 | <80
Kewat Departmental | 2025-06 | 33.93 | 37.5 | TB401 | 1 | <80
Khatan | 2024-07 | 95.47 | 72.74 | TA421 | 2 | 80-100
Khatan | 2024-08 | 214.89 | 218.22 | TA421 | 6 | 200-220
Khatan | 2024-09 | 177 | 181.85 | TA421 | 5 | 160-180
Khatan | 2024-10 | 134.05 | 148.6 | TA421 | 4 | 120-140
Khatun | 2024-10 | 68.24 | 37.93 | TA421 | 1 | <80
Khatun | 2024-11 | 242.78 | 273.09 | TA421 | 6 | 240-260
Khatun | 2024-12 | 223.47 | 191.86 | TA421 | 5 | 220-240
Khatun | 2025-01 | 175.04 | 184.97 | TA421 | 5 | 160-180
Khatun | 2025-02 | 191.74 | 184.97 | TA421 | 5 | 180-200
Khatun | 2025-03 | 271.81 | 265.8 | TA421 | 6 | >=260
Khatun | 2025-04 | 316.35 | 331.85 | TA421 | 6 | >=260
Khatun | 2025-05 | 219.06 | 238.03 | TA421 | 4 | 200-220
Khatun | 2025-07 | 186.38 | 161.34 | TA421 | 5 | 180-200
Khatun | 2025-08 | 205.3 | 230.33 | TA421 | 6 | 200-220
Khatun | 2025-09 | 142.07 | 128.36 | TA421 | 2 | 140-160
Khatun | 2025-10 | 194.96 | 184.42 | TA421 | 5 | 180-200
Khatun | 2025-11 | 244.75 | 224.81 | TA421 | 5 | 240-260
Khatun | 2025-12 | 282.6 | 326.78 | TA421 | 6 | >=260
Khatun | 2026-01 | 33.38 | 33.38 | TA421 | 1 | <80
Khemlal | 2025-09 | 82 | 82 | TA506 | 4 | 80-100
Khemlal Mahto | 2025-10 | 40 | 40 | TA506 | 2 | <80
Khemlal Mahto | 2025-11 | 126.8 | 114 | TA506 | 4 | 120-140
Khemlal Mahto | 2025-12 | 133.41 | 101 | TA506 | 4 | 120-140
Khemlal Mahto | 2026-01 | 109.29 | 146 | TA506 | 6 | 100-120
Khemlal Mahto | 2026-02 | 8.5 | 17 | TA506 | 1 | <80
Khublal Mahto | 2024-09 | 54.39 | 38.85 | TB401 | 1 | <80
Khublal Mahto | 2024-10 | 23.31 | 38.85 | TB408 | 1 | <80
Kongres Kumar 1 | 2025-07 | 29.34 | 0 |  | 0 | <80
Kongres Kumar 1 | 2025-08 | 151.58 | 161.36 | TA416 | 1 | 140-160
Kongres Kumar 1 | 2025-09 | 162.98 | 161.36 | TA416 | 1 | 160-180
Kongres Kumar 1 | 2025-10 | 21.19 | 42.37 | TA416 | 1 | <80
Kongres Kumar 2 | 2025-08 | 100.42 | 97.23 | TA416 | 1 | 100-120
Kongres Kumar 2 | 2025-09 | 70.23 | 73.43 | TA416 | 1 | <80
Kuduas Ali 2 | 2025-11 | 76.71 | 0 |  | 0 | <80
Kuduas Ali 2 | 2025-12 | 8.52 | 85.23 | TA325 | 1 | <80
Lakhan Singh | 2024-12 | 14.73 | 14.73 | TB501 | 3 | <80
Lalan Mahto | 2024-02 | 148.74 | 129.88 | TA325 | 3 | 140-160
Lalan Mahto | 2024-03 | 148.74 | 167.61 | TA325 | 4 | 140-160
Lalan Mahto | 2024-04 | 146.71 | 146.71 | TA325 | 3 | 140-160
Lalan Mahto | 2024-05 | 215.36 | 208.8 | TA325 | 5 | 200-220
Lalan Mahto | 2024-06 | 103.4 | 109.97 | TA325 | 2 | 100-120
Laxmi | 2025-11 | 37.5 | 37.5 | TB401 | 1 | <80
Laxmi | 2025-12 | 38.85 | 38.85 | TB401 | 1 | <80
M K Infra | 2025-03 | 46.05 | 46.05 | TA416 | 1 | <80
M K Infra | 2025-04 | 96.9 | 88.42 | TA416 | 2 | 80-100
M K Infra | 2025-05 | 32.84 | 0 |  | 0 | <80
M K Infra | 2025-06 | 47.11 | 88.42 | TA416 | 2 | <80
M S Company Gang | 2025-11 | 66.18 | 30.49 | TA512 | 1 | <80
M S Company Gang | 2025-12 | 161.12 | 55.13 | TA512 | 2 | 160-180
M S Company Gang | 2026-01 | 51.43 | 173.35 | TA512 | 4 | <80
M S Ganesh Sinha | 2026-01 | 48.95 | 35.6 | TA512 | 1 | <80
M S Ganesh Sinha | 2026-02 | 22.25 | 35.6 | TA512 | 1 | <80
M S Gauri Shankar | 2024-03 | 0.51 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-04 | 3.05 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-05 | 3.15 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-06 | 3.05 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-07 | 3.15 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-08 | 3.15 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-09 | 3.05 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-10 | 3.15 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-11 | 3.05 | 0 |  | 0 | <80
M S Gauri Shankar | 2024-12 | 3.15 | 0 |  | 0 | <80
M S Gauri Shankar | 2025-01 | 3.15 | 0 |  | 0 | <80
M S Gauri Shankar | 2025-02 | 2.85 | 0 |  | 0 | <80
M S Gauri Shankar | 2025-03 | 3.15 | 0 |  | 0 | <80
M S Gauri Shankar | 2025-04 | 0.1 | 37.73 | TA414 | 1 | <80
M S Govind Mahto | 2025-12 | 165.36 | 165.36 | TA512 | 4 | 160-180
M S Govind Mahto 2 | 2025-12 | 43.62 | 37.93 | TA512 | 1 | <80
M S Govind Mahto 2 | 2026-01 | 154.25 | 137.19 | TA512 | 3 | 140-160
M S Govind Mahto 2 | 2026-02 | 73.14 | 95.89 | TA512 | 2 | <80
M S Israul Hoque | 2025-09 | 80.24 | 80.24 | TA414 | 1 | 80-100
M S Jirwa Debi | 2026-01 | 74.09 | 74.09 | TA512 | 2 | <80
M S Jwala Singh | 2025-08 | 66.19 | 36.16 | TA512 | 1 | <80
M S Jwala Singh | 2025-09 | 192.04 | 203.29 | TA512 | 5 | 180-200
M S Jwala Singh | 2025-10 | 141.57 | 154.87 | TA512 | 3 | 140-160
M S Jwala Singh | 2025-11 | 161.54 | 167.01 | TA512 | 4 | 160-180
M S Jwala Singh | 2025-12 | 165.09 | 107.11 | TA512 | 3 | 160-180
M S Jwala Singh | 2026-01 | 150.54 | 192.26 | TA512 | 4 | 140-160
M S Jwala Singh | 2026-02 | 21.67 | 37.93 | TA512 | 1 | <80
M S Jwala Singh 2 | 2025-11 | 66.04 | 45.7 | TA512 | 1 | <80
M S Jwala Singh 2 | 2025-12 | 167.62 | 183.23 | TA512 | 5 | 160-180
M S Jwala Singh 2 | 2026-01 | 126.16 | 103.8 | TA512 | 2 | 120-140
M S Jwala Singh 2 | 2026-02 | 48.77 | 75.86 | TA512 | 2 | <80
M S Karni Construction 1 | 2025-12 | 27.83 | 0 |  | 0 | <80
M S Karni Construction 1 | 2026-01 | 52.65 | 80.49 | TA512 | 2 | <80
M S Karni Construction 2 | 2025-12 | 31.29 | 0 |  | 0 | <80
M S Karni Construction 2 | 2026-01 | 88.19 | 78.59 | TA512 | 2 | 80-100
M S Karni Construction 2 | 2026-02 | 2.92 | 43.8 | TA512 | 1 | <80
M S Kartik Mahto | 2025-10 | 141.24 | 141.24 | TA512 | 3 | 140-160
M S Kartik Mahto | 2025-11 | 284.78 | 270.18 | TA512 | 7 | >=260
M S Kartik Mahto | 2025-12 | 247.37 | 243.9 | TA512 | 6 | 240-260
M S Kartik Mahto | 2026-01 | 232.26 | 218.73 | TA512 | 6 | 220-240
M S Kartik Mahto | 2026-02 | 42.48 | 74.09 | TA512 | 2 | <80
M S Kavya Enterprises | 2025-07 | 18.04 | 0 |  | 0 | <80
M S Kavya Enterprises | 2025-08 | 122.46 | 117.9 | TA512 | 3 | 120-140
M S Kavya Enterprises | 2025-09 | 151.86 | 152.28 | TA512 | 4 | 140-160
M S Kavya Enterprises | 2025-10 | 83.23 | 93.38 | TA512 | 2 | 80-100
M S Kavya Enterprises | 2025-11 | 95.2 | 107.22 | TA512 | 3 | 80-100
M S Kavya Enterprises | 2025-12 | 31.95 | 31.96 | TA512 | 1 | <80
M S Mdpl | 2025-09 | 39.62 | 33.3 | TA418 | 1 | <80
M S Mdpl | 2025-10 | 85.33 | 60 | TA418 | 1 | 80-100
M S Mdpl | 2025-11 | 85.36 | 117 | TA418 | 2 | 80-100
M S Mdpl | 2025-12 | 144.86 | 141 | TA418 | 4 | 140-160
M S Mdpl | 2026-01 | 148.03 | 127 | TA418 | 3 | 140-160
M S Mdpl | 2026-02 | 31.11 | 56 | TA418 | 1 | <80
M S Mgr | 2025-05 | 3.4 | 0 |  | 0 | <80
M S Mgr | 2025-06 | 51.01 | 54.41 | TA414 | 1 | <80
M S Midhun | 2025-08 | 80.24 | 80.24 | TA414 | 1 | 80-100
M S Midhun | 2025-09 | 51.81 | 0 |  | 0 | <80
M S Midhun | 2025-10 | 3.24 | 55.05 | TA414 | 1 | <80
M S Mohika Costruction | 2026-01 | 18.97 | 18.97 | TA512 | 1 | <80
M S Nirmal Mahto | 2026-01 | 37.93 | 37.93 | TA512 | 1 | <80
M S Punam Kumari | 2025-08 | 141.63 | 75.86 | TA512 | 2 | 140-160
M S Punam Kumari | 2025-09 | 283.39 | 302.24 | TA512 | 8 | >=260
M S Punam Kumari | 2025-10 | 152.71 | 199.63 | TA512 | 5 | 140-160
M S Punam Kumari 3 | 2025-11 | 31.03 | 0 |  | 0 | <80
M S Punam Kumari 3 | 2025-12 | 130.18 | 157.6 | TA512 | 4 | 120-140
M S Punam Kumari 3 | 2026-01 | 126.49 | 112.02 | TA512 | 3 | 120-140
M S Punam Kumari 3 | 2026-02 | 18.08 | 36.16 | TA512 | 1 | <80
M S Punam Kumari 4 | 2025-12 | 128.77 | 119.23 | TA512 | 3 | 120-140
M S Punam Kumari 4 | 2026-01 | 146.74 | 156.28 | TA512 | 3 | 140-160
M S Punam Kumari 4 | 2026-02 | 37.93 | 37.93 | TA512 | 1 | <80
M S Rahul | 2025-06 | 120.19 | 120.19 | TA414 | 3 | 120-140
M S Raju Kumar | 2026-01 | 158.56 | 158.56 | TA512 | 4 | 140-160
M S Raju Kumar | 2026-02 | 43.8 | 43.8 | TA512 | 1 | <80
M S Sakkurddin | 2025-07 | 25.43 | 0 |  | 0 | <80
M S Sakkurddin | 2025-08 | 101.96 | 127.39 | TA414 | 3 | 100-120
M S Sakkurddin | 2025-09 | 37.73 | 37.73 | TA414 | 1 | <80
M S Shobha Debi | 2026-01 | 117.28 | 109.69 | TA512 | 3 | 100-120
M S Shobha Debi | 2026-02 | 30.34 | 37.93 | TA512 | 1 | <80
M S Shree Shyam Construction | 2026-01 | 56.93 | 36.16 | TA512 | 1 | <80
M S Shree Shyam Construction | 2026-02 | 24.93 | 45.7 | TA512 | 1 | <80
M S Sunny Construction | 2026-01 | 95.1 | 95.1 | TA512 | 2 | 80-100
M S Sunny Construction | 2026-02 | 45.7 | 45.7 | TA512 | 1 | <80
M S Tofit | 2025-09 | 60.3 | 60.3 | TA418 | 2 | <80
M S Tofit | 2025-10 | 121.91 | 60 | TA418 | 1 | 120-140
M S Tofit | 2025-11 | 107.59 | 163 | TA418 | 3 | 100-120
M S Tofit | 2025-12 | 187.79 | 163 | TA418 | 4 | 180-200
M S Tofit | 2026-01 | 137.14 | 156 | TA418 | 4 | 120-140
M S Tofit | 2026-02 | 16.57 | 29 | TA418 | 1 | <80
Maa Const | 2024-09 | 37.93 | 37.93 | TA421 | 1 | <80
Maa Const | 2024-10 | 74.3 | 74.3 | TA421 | 2 | <80
Maa Const | 2024-11 | 163.77 | 163.77 | TA421 | 4 | 160-180
Maa Construction | 2024-11 | 61.73 | 0 |  | 0 | <80
Maa Construction | 2024-12 | 97.2 | 129.34 | TA325 | 1 | 80-100
Maa Construction | 2025-01 | 170.04 | 199.64 | TA325 | 4 | 160-180
Maa Construction | 2025-02 | 92.15 | 92.15 | TA325 | 2 | 80-100
Maa Construction | 2025-03 | 113.92 | 75.46 | TA325 | 2 | 100-120
Maa Construction | 2025-04 | 41.95 | 80.41 | TA325 | 1 | <80
Maa Construction | 2025-09 | 75.86 | 75.86 | TA416 | 1 | <80
Maa Construction | 2025-10 | 97.83 | 97.83 | TA416 | 1 | 80-100
Madhu Sah | 2024-01 | 2.42 | 0 |  | 0 | <80
Madhu Sah | 2024-02 | 2.7 | 0 |  | 0 | <80
Madhu Sah | 2024-03 | 2.88 | 0 |  | 0 | <80
Madhu Sah | 2024-04 | 2.79 | 0 |  | 0 | <80
Madhu Sah | 2024-05 | 2.88 | 0 |  | 0 | <80
Madhu Sah | 2024-06 | 2.79 | 0 |  | 0 | <80
Madhu Sah | 2024-07 | 2.88 | 0 |  | 0 | <80
Madhu Sah | 2024-08 | 2.88 | 0 |  | 0 | <80
Madhu Sah | 2024-09 | 2.79 | 0 |  | 0 | <80
Madhu Sah | 2024-10 | 2.88 | 0 |  | 0 | <80
Madhu Sah | 2024-11 | 51.95 | 35.6 | TA419 | 1 | <80
Madhu Sah | 2024-12 | 173.27 | 183.95 | TA419 | 5 | 160-180
Madhu Sah | 2025-01 | 147.47 | 150.91 | TA419 | 4 | 140-160
Madhu Sah | 2025-02 | 186.37 | 216.5 | TA419 | 5 | 180-200
Madhu Sah | 2025-03 | 52.36 | 37.14 | TA419 | 1 | <80
Madhu Sah | 2025-04 | 131.48 | 130.45 | TA419 | 3 | 120-140
Madhu Sah | 2025-05 | 58.81 | 75.07 | TA419 | 2 | <80
Madhu Sah | 2025-07 | 151.81 | 119.29 | TA419 | 2 | 140-160
Madhu Sah | 2025-08 | 204.09 | 180.57 | TA419 | 4 | 200-220
Madhu Sah | 2025-09 | 103.04 | 142.63 | TA419 | 2 | 100-120
Madhu Sah | 2025-10 | 62.98 | 79.41 | TA419 | 2 | <80
Madhu Sah | 2025-11 | 122.25 | 111.41 | TA419 | 3 | 120-140
Madhu Sah | 2025-12 | 157.06 | 111.46 | TA419 | 3 | 140-160
Madhu Sah | 2026-01 | 112.3 | 168.73 | TA419 | 2 | 100-120
Mahon Mahto | 2025-09 | 22.16 | 0 |  | 0 | <80
Mahon Mahto | 2025-10 | 192.58 | 78.07 | TA416 | 1 | 180-200
Mahon Mahto | 2025-11 | 152.63 | 285.61 | TA416 | 2 | 140-160
Mahon Mahto | 2025-12 | 114.5 | 0 |  | 0 | 100-120
Mahon Mahto | 2026-01 | 114.24 | 188.38 | TA416 | 1 | 100-120
Mahon Mahto | 2026-02 | 29.37 | 73.43 | TA416 | 1 | <80
Manirul Islam Khatun | 2024-09 | 25.98 | 0 |  | 0 | <80
Manirul Islam Khatun | 2024-10 | 10.39 | 36.37 | TA421 | 1 | <80
Mansukh Lal | 2024-05 | 37.5 | 37.5 | TB408 | 1 | <80
Mansukh Lal | 2024-06 | 37.5 | 37.5 | TB408 | 1 | <80
Md Akhtar | 2025-09 | 44.72 | 0 |  | 0 | <80
Md Akhtar | 2025-10 | 177.23 | 138.51 | TA325 | 2 | 160-180
Md Akhtar | 2025-11 | 150.43 | 129.34 | TA325 | 1 | 140-160
Md Akhtar | 2025-12 | 37.34 | 141.87 | TA325 | 1 | <80
Md Emdadul Hoque | 2025-12 | 38.04 | 38.04 | TA414 | 1 | <80
Mithun Kumar | 2024-09 | 11.18 | 0 |  | 0 | <80
Mithun Kumar | 2024-10 | 33.55 | 44.73 | TA325 | 1 | <80
Mithun Kumar | 2024-11 | 36.04 | 36.04 | TA325 | 1 | <80
Mithun Kumar | 2024-12 | 59.36 | 37.73 | TA325 | 1 | <80
Mithun Kumar | 2025-01 | 101.2 | 111.51 | TA325 | 3 | 100-120
Mithun Kumar | 2025-02 | 100.19 | 111.51 | TA325 | 3 | 100-120
Mithun Kumar | 2025-03 | 37.73 | 37.73 | TA325 | 1 | <80
Mithun Kumar | 2025-04 | 208.12 | 146.71 | TA325 | 3 | 200-220
Mithun Kumar | 2025-05 | 141.42 | 176.68 | TA325 | 2 | 140-160
Mithun Kumar | 2025-06 | 19.61 | 0 |  | 0 | <80
Mithun Kumar | 2025-07 | 20.27 | 0 |  | 0 | <80
Mithun Kumar | 2025-08 | 20.27 | 0 |  | 0 | <80
Mithun Kumar | 2025-09 | 19.61 | 0 |  | 0 | <80
Mithun Kumar | 2025-10 | 20.27 | 0 |  | 0 | <80
Mithun Kumar | 2025-11 | 79.94 | 206.13 | TA325 | 2 | <80
Mithun Kumar | 2025-12 | 25.36 | 0 |  | 0 | <80
Mithun Kumar | 2026-01 | 130.65 | 120.5 | TA414 | 3 | 120-140
Mithun Kumar | 2026-02 | 3.94 | 39.45 | TA414 | 1 | <80
Mjr | 2024-12 | 100.23 | 46.62 | TA325 | 1 | 100-120
Mjr | 2025-01 | 103.99 | 157.6 | TA325 | 3 | 100-120
Mjr | 2025-02 | 115.45 | 115.45 | TA325 | 2 | 100-120
Mjr | 2025-03 | 132.32 | 101.24 | TA325 | 2 | 120-140
Mjr | 2025-04 | 144.27 | 110.88 | TA325 | 2 | 140-160
Mjr | 2025-05 | 114.12 | 178.59 | TA325 | 3 | 100-120
Modina India | 2024-11 | 32.44 | 0 |  | 0 | <80
Modina India | 2024-12 | 117.98 | 120.23 | TA325 | 3 | 100-120
Modina India | 2025-01 | 150.38 | 150.92 | TA325 | 4 | 140-160
Modina India | 2025-02 | 95.14 | 114.92 | TA325 | 3 | 80-100
Modina India | 2025-03 | 79.92 | 82.24 | TA325 | 1 | <80
Modina India | 2025-04 | 94.48 | 82.46 | TA325 | 2 | 80-100
Modina India | 2025-05 | 25.16 | 44.73 | TA325 | 1 | <80
Modina India | 2025-06 | 41.41 | 0 |  | 0 | <80
Modina India | 2025-07 | 44.27 | 0 |  | 0 | <80
Modina India | 2025-08 | 84.08 | 122.81 | TA325 | 1 | 80-100
Modina India | 2025-09 | 25.28 | 72.24 | TA325 | 1 | <80
Modina India 1 | 2025-09 | 6.17 | 0 |  | 0 | <80
Modina India 1 | 2025-10 | 9.56 | 0 |  | 0 | <80
Modina India 1 | 2025-11 | 9.25 | 0 |  | 0 | <80
Modina India 1 | 2025-12 | 14 | 0 |  | 0 | <80
Modina India 1 | 2026-01 | 42.85 | 37.73 | TA414 | 1 | <80
Modina India 1 | 2026-02 | 0.62 | 44.73 | TA414 | 1 | <80
Modina India 1 4 Pgcil | 2025-10 | 72.09 | 72.09 | TA325 | 2 | <80
Modina India 1 Pgcil | 2025-11 | 54.32 | 0 |  | 0 | <80
Modina India 1 Pgcil | 2025-12 | 47.53 | 101.85 | TA325 | 1 | <80
Modina India 2 | 2025-12 | 4.29 | 0 |  | 0 | <80
Modina India 2 | 2026-01 | 75.45 | 79.74 | TA414 | 2 | <80
Modina India 2 Pgcil | 2025-09 | 17.61 | 0 |  | 0 | <80
Modina India 2 Pgcil | 2025-10 | 36.81 | 54.42 | TA325 | 1 | <80
Modina India 2 Pgcil | 2025-11 | 65.87 | 39.46 | TA325 | 1 | <80
Modina India 2 Pgcil | 2025-12 | 11.32 | 37.73 | TA325 | 1 | <80
Modina India 3 | 2025-12 | 3.8 | 0 |  | 0 | <80
Modina India 3 | 2026-01 | 34.24 | 38.04 | TA414 | 1 | <80
Modina India 3 Pgcil | 2025-10 | 75.46 | 75.46 | TA325 | 2 | <80
Modina India 3 Pgcil | 2025-11 | 82.46 | 82.46 | TA325 | 2 | 80-100
Modina India 3 Pgcil Dildar Electricals 3 Pgcil Nasirudin Md Akhtar | 2025-12 | 72.73 | 0 |  | 0 | <80
Modina India 3 Pgcil Dildar Electricals 3 Pgcil Nasirudin Md Akhtar | 2026-01 | 50.91 | 123.65 | TA325 | 1 | <80
Mohan Mahto | 2025-09 | 125 | 125 | TA506 | 4 | 120-140
Mukesh | 2024-10 | 129.59 | 100.3 | TA325 | 2 | 120-140
Mukesh | 2024-11 | 181.97 | 160.35 | TA325 | 3 | 180-200
Mukesh | 2024-12 | 219.65 | 210.75 | TA325 | 3 | 200-220
Mukesh | 2025-01 | 86.68 | 146.49 | TA325 | 2 | 80-100
Mukhi Lal | 2026-01 | 120 | 120 | TA504 | 2 | 120-140
Mukhi Lal | 2026-02 | 44 | 44 | TA504 | 1 | <80
Mukhilal | 2025-12 | 11.6 | 0 |  | 0 | <80
Mukhilal | 2026-01 | 66.97 | 78.57 | TA419 | 2 | <80
Mukhilal 1 | 2025-11 | 22.28 | 0 |  | 0 | <80
Mukhilal 1 | 2025-12 | 14.86 | 37.14 | TA419 | 1 | <80
Mukhilal 2 | 2025-12 | 124.95 | 124.95 | TA419 | 1 | 120-140
Mukkhilal | 2026-01 | 27 | 27 | TA506 | 1 | <80
Mukkhilal 2 | 2026-01 | 16 | 16 | TA506 | 1 | <80
Muni Bibi 1 | 2025-10 | 44.73 | 44.73 | TA325 | 1 | <80
Muni Bibi 1 | 2025-11 | 61.36 | 0 |  | 0 | <80
Muni Bibi 1 | 2025-12 | 33.04 | 94.41 | TA325 | 1 | <80
Muni Bibi 1 2 | 2025-10 | 39.69 | 0 |  | 0 | <80
Muni Bibi 1 2 | 2025-11 | 23.82 | 63.51 | TA325 | 1 | <80
Muni Bibi 2 | 2025-10 | 37.73 | 37.73 | TA325 | 1 | <80
Muni Bibi 2 | 2025-11 | 84.45 | 0 |  | 0 | 80-100
Muni Bibi 2 | 2025-12 | 4.69 | 89.15 | TA325 | 1 | <80
Munna Singh | 2025-04 | 7.78 | 5.48 | TB501 | 1 | <80
Munna Singh | 2025-05 | 4.61 | 6.91 | TB501 | 1 | <80
Namechand Mahto | 2025-01 | 0.54 | 0 |  | 0 | <80
Namechand Mahto | 2025-02 | 0.84 | 0 |  | 0 | <80
Namechand Mahto | 2025-03 | 0.93 | 0 |  | 0 | <80
Namechand Mahto | 2025-04 | 0.9 | 0 |  | 0 | <80
Namechand Mahto | 2025-05 | 0.93 | 0 |  | 0 | <80
Namechand Mahto | 2025-06 | 0.9 | 0 |  | 0 | <80
Namechand Mahto | 2025-07 | 0.93 | 0 |  | 0 | <80
Namechand Mahto | 2025-08 | 0.93 | 0 |  | 0 | <80
Namechand Mahto | 2025-09 | 0.9 | 0 |  | 0 | <80
Namechand Mahto | 2025-10 | 30.81 | 29.87 | TB507 | 2 | <80
Namechand Mahto | 2025-11 | 99.24 | 98.34 | TB507 | 6 | 80-100
Namechand Mahto | 2025-12 | 110.52 | 109.59 | TB507 | 6 | 100-120
Namechand Mahto | 2026-01 | 30.41 | 41.02 | TB507 | 3 | <80
Nan | 2025-06 | 61.52 | 0 |  | 0 | <80
Nan | 2025-07 | 97.64 | 37.73 | TA325 | 1 | 80-100
Nan | 2025-08 | 20.67 | 142.1 | TA325 | 1 | <80
Nan | 2025-09 | 107.91 | 0 |  | 0 | 100-120
Nan | 2025-10 | 62.96 | 170.87 | TA325 | 3 | <80
Nasiruddin | 2025-12 | 101.59 | 73.15 | TA601 | 2 | 100-120
Nasiruddin | 2026-01 | 106.97 | 135.41 | TA414, TA601 | 2 | 100-120
Nasirudin | 2025-10 | 74.63 | 74.63 | TA325 | 1 | <80
Nasirudin 2 | 2025-10 | 110.05 | 80.41 | TA325 | 1 | 100-120
Nasirudin 2 | 2025-11 | 33.87 | 63.51 | TA325 | 1 | <80
Naziruddin | 2025-06 | 48.49 | 0 |  | 0 | <80
Naziruddin | 2025-07 | 180.78 | 213.27 | TA421 | 4 | 180-200
Naziruddin | 2025-08 | 136.58 | 148.4 | TA421 | 4 | 120-140
Naziruddin | 2025-09 | 95.97 | 100.14 | TA421 | 3 | 80-100
Neha Const | 2025-08 | 7.24 | 0 |  | 0 | <80
Neha Const | 2025-09 | 66.76 | 74 | TA504 | 2 | <80
Neha Const | 2025-11 | 14.25 | 0 |  | 0 | <80
Neha Const | 2025-12 | 23.75 | 38 | TA504 | 1 | <80
Niranjan Singh | 2025-11 | 43.78 | 43.78 | TA416 | 1 | <80
Nirmal Mahto | 2024-08 | 17.27 | 0 |  | 0 | <80
Nirmal Mahto | 2024-09 | 165.21 | 163.73 | TB401, TB408 | 4 | 160-180
Nirmal Mahto | 2024-10 | 172.96 | 159.27 | TB408 | 4 | 160-180
Nirmal Mahto | 2024-11 | 120.26 | 152.69 | TB401, TB408 | 3 | 120-140
Nirmal Mahto | 2025-08 | 6.13 | 0 |  | 0 | <80
Nirmal Mahto | 2025-09 | 105.31 | 96.44 | TB408 | 2 | 100-120
Nirmal Mahto | 2025-10 | 170.69 | 179.79 | TB408 | 4 | 160-180
Nirmal Mahto | 2025-11 | 175.59 | 151.97 | TB401, TB408 | 3 | 160-180
Nirmal Mahto | 2025-12 | 186 | 215.52 | TB401, TB408 | 5 | 180-200
Om Construction | 2025-01 | 45.41 | 45.41 | TB401 | 1 | <80
Pankaj | 2024-11 | 74.83 | 46.05 | TA416 | 1 | <80
Pankaj | 2024-12 | 274.67 | 297.7 | TA416, TA504 | 7 | >=260
Pankaj | 2025-01 | 483.41 | 455.65 | TA416, TA504 | 11 | >=260
Pankaj | 2025-02 | 418.98 | 439.6 | TA416, TA504 | 11 | >=260
Pankaj | 2025-03 | 410.21 | 415.91 | TA416, TA504 | 10 | >=260
Pankaj | 2025-04 | 191.24 | 190 | TA504 | 5 | 180-200
Pankaj | 2025-05 | 156.06 | 152 | TA504 | 4 | 140-160
Pankaj | 2025-06 | 25 | 37.5 | TB401 | 1 | <80
Pankaj | 2025-11 | 53.2 | 42 | TA506 | 2 | <80
Pankaj | 2025-12 | 149.24 | 148 | TA506 | 6 | 140-160
Pankaj | 2026-01 | 45.56 | 58 | TA506 | 2 | <80
Pankaj 1 | 2025-08 | 3.4 | 0 |  | 0 | <80
Pankaj 1 | 2025-09 | 114.6 | 118 | TA506 | 4 | 100-120
Pankaj 2 | 2025-01 | 102.4 | 72 | TA504 | 2 | 100-120
Pankaj 2 | 2025-02 | 231.6 | 262 | TA504 | 7 | 220-240
Pankaj 2 | 2025-03 | 261 | 261 | TA504 | 7 | >=260
Pankaj 2 | 2025-04 | 206.5 | 202 | TA504 | 5 | 200-220
Pankaj 2 | 2025-05 | 136 | 118 | TA504 | 3 | 120-140
Pankaj 2 | 2025-06 | 128.5 | 151 | TA504 | 4 | 120-140
Pankaj 2 | 2025-09 | 68 | 68 | TA506 | 2 | <80
Pankaj Const | 2025-09 | 9.71 | 0 |  | 0 | <80
Pankaj Const | 2025-10 | 95.29 | 105 | TA506 | 4 | 80-100
Pankaj Kumar | 2025-09 | 22.71 | 0 |  | 0 | <80
Pankaj Kumar | 2025-10 | 223.97 | 221.39 | TA416 | 2 | 220-240
Pankaj Kumar | 2025-11 | 154.77 | 75.86 | TA416 | 1 | 140-160
Pankaj Kumar | 2025-12 | 170.11 | 221.27 | TA416 | 2 | 160-180
Pankaj Kumar | 2026-01 | 44.19 | 97.23 | TA416 | 1 | <80
Pankaj Singh Mp | 2025-09 | 64.92 | 34.79 | TA505 | 1 | <80
Pankaj Singh Mp | 2025-10 | 157.9 | 163.93 | TA505 | 4 | 140-160
Pankaj Singh Mp | 2025-11 | 166.13 | 181.2 | TA505 | 5 | 160-180
Pankaj Singh Mp | 2025-12 | 130.92 | 139.96 | TA505 | 3 | 120-140
Panva Devi | 2025-10 | 72.12 | 0 |  | 0 | <80
Panva Devi | 2025-11 | 156.46 | 190.88 | TB401, TB408 | 2 | 140-160
Panva Devi | 2025-12 | 110.69 | 148.4 | TB408 | 3 | 100-120
Pappu Kumar | 2025-12 | 21 | 21 | TA506 | 1 | <80
Paramanand | 2025-04 | 19.14 | 0 |  | 0 | <80
Paramanand | 2025-05 | 17.02 | 36.16 | TA505 | 1 | <80
Paramanand 1 | 2025-05 | 55.44 | 36.16 | TA505 | 1 | <80
Paramanand 1 | 2025-06 | 32.28 | 36.16 | TA505 | 1 | <80
Paramanand 1 | 2025-07 | 20.76 | 36.16 | TA505 | 1 | <80
Paramanand 1 | 2025-08 | 13.12 | 0 |  | 0 | <80
Paramanand 1 | 2025-09 | 73.48 | 71.76 | TA505 | 2 | <80
Paramanand 1 | 2025-10 | 97.78 | 71.2 | TA505 | 2 | 80-100
Paramanand 1 | 2025-11 | 49.05 | 62.12 | TA505 | 1 | <80
Paramanand 1 | 2025-12 | 15.46 | 43.8 | TA505 | 1 | <80
Paramanand 2 | 2025-05 | 41.78 | 36.16 | TA505 | 1 | <80
Paramanand 2 | 2025-06 | 32.31 | 37.93 | TA505 | 1 | <80
Parsuram Sai | 2024-08 | 1.83 | 0 |  | 0 | <80
Parsuram Sai | 2024-09 | 27.44 | 0 |  | 0 | <80
Parsuram Sai | 2024-10 | 37.72 | 37.5 | TB401 | 1 | <80
Parsuram Sai | 2024-11 | 17.69 | 47.18 | TB401 | 1 | <80
Pc 2 | 2025-11 | 163.23 | 46.62 | TA325 | 1 | 160-180
Pc 2 | 2025-12 | 116.32 | 232.93 | TA325 | 2 | 100-120
Pc 3 Prabhat Kumar Ranjan | 2025-11 | 57.57 | 0 |  | 0 | <80
Pc 3 Prabhat Kumar Ranjan | 2025-12 | 24.67 | 82.24 | TA325 | 1 | <80
Pc Construction | 2025-11 | 97.93 | 97.93 | TA325 | 1 | 80-100
Pc Construction 1 | 2025-11 | 26.74 | 0 |  | 0 | <80
Pc Construction 1 | 2025-12 | 185.21 | 211.95 | TA325 | 2 | 180-200
Permanand | 2025-06 | 38.85 | 38.85 | TB401 | 1 | <80
Pinki Devi | 2025-01 | 90.3 | 75.07 | TA419 | 2 | 80-100
Pinki Devi | 2025-02 | 153.22 | 141.36 | TA419 | 3 | 140-160
Pinki Devi | 2025-03 | 10.84 | 37.93 | TA419 | 1 | <80
Pinki Devi | 2025-08 | 111.63 | 83.63 | TA413 | 2 | 100-120
Pinki Devi | 2025-09 | 170.9 | 192 | TA504 | 3 | 160-180
Pinki Devi | 2025-10 | 135.1 | 142 | TA504 | 3 | 120-140
Pinky Dewi | 2024-11 | 63.32 | 46.05 | TA416 | 1 | <80
Pinky Dewi | 2024-12 | 231.07 | 222.02 | TA416 | 5 | 220-240
Pinky Dewi | 2025-01 | 198.18 | 184.2 | TA416 | 4 | 180-200
Pinky Dewi | 2025-02 | 206.11 | 246.4 | TA416 | 5 | 200-220
Pinky Dewi | 2025-03 | 253.93 | 237.19 | TA416 | 5 | 240-260
Pinky Dewi | 2025-04 | 222.23 | 238.98 | TA416 | 4 | 220-240
Pinky Dewi | 2025-05 | 213.6 | 181.98 | TA416 | 3 | 200-220
Pinky Dewi | 2025-06 | 223.03 | 254.65 | TA416 | 5 | 220-240
Pinky Dewi | 2025-07 | 46.05 | 46.05 | TA416 | 1 | <80
Pinky Dewi | 2025-11 | 133.52 | 43.78 | TA416 | 1 | 120-140
Pinky Dewi | 2025-12 | 90.19 | 156.05 | TA416 | 2 | 80-100
Pinky Dewi | 2026-01 | 40.6 | 64.48 | TA416 | 1 | <80
Poonam | 2025-06 | 57.6 | 38.85 | TB401 | 1 | <80
Poonam | 2025-07 | 226.36 | 245.12 | TB401 | 6 | 220-240
Poonam | 2025-08 | 37.5 | 37.5 | TB401 | 1 | <80
Poonam | 2025-11 | 20.64 | 0 |  | 0 | <80
Poonam | 2025-12 | 24.77 | 45.41 | TB401 | 1 | <80
Poonam Kumari | 2024-01 | 183.07 | 157.92 | TA325 | 4 | 180-200
Poonam Kumari | 2024-02 | 205.34 | 205.34 | TA325 | 5 | 200-220
Poonam Kumari | 2024-03 | 41.45 | 37.73 | TA325 | 1 | <80
Poonam Kumari | 2024-04 | 10.59 | 39.46 | TA325 | 1 | <80
Poonam Kumari | 2025-01 | 3.71 | 0 |  | 0 | <80
Poonam Kumari | 2025-02 | 165.23 | 139.19 | TA419 | 3 | 160-180
Poonam Kumari | 2025-03 | 102.99 | 132.75 | TA419 | 2 | 100-120
Poonam Kumari | 2025-04 | 16.64 | 0 |  | 0 | <80
Poonam Kumari | 2025-05 | 38.82 | 55.45 | TA419 | 1 | <80
Poonam Kumari | 2025-10 | 69.38 | 69.38 | TA419 | 1 | <80
Poonam Kumari 2 | 2025-10 | 43.8 | 43.8 | TA419 | 1 | <80
Poornam Kumari | 2025-03 | 19.72 | 0 |  | 0 | <80
Poornam Kumari | 2025-04 | 157.67 | 177.4 | TA419 | 4 | 140-160
Pramod Kumar | 2025-12 | 37.73 | 37.73 | TA414 | 1 | <80
Praveen | 2024-10 | 48.63 | 37.93 | TA421 | 1 | <80
Praveen | 2024-11 | 55.7 | 36.37 | TA421 | 1 | <80
Praveen | 2024-12 | 45.83 | 75.86 | TA421 | 2 | <80
Praveen | 2025-01 | 78.8 | 72.74 | TA421 | 2 | <80
Praveen | 2025-02 | 105.21 | 79.45 | TA421 | 2 | 100-120
Praveen | 2025-03 | 102.19 | 122.53 | TA421 | 3 | 100-120
Praveen | 2025-04 | 86.34 | 86.16 | TA421 | 2 | 80-100
Praveen | 2025-05 | 79.17 | 37.93 | TA421 | 1 | <80
Praveen | 2025-06 | 77.97 | 97.48 | TA421 | 2 | <80
Praveen | 2025-07 | 53.51 | 54.66 | TA421 | 1 | <80
Praveen | 2025-08 | 31.14 | 34.95 | TA421 | 1 | <80
Praveen | 2025-09 | 36.22 | 37.93 | TA421 | 1 | <80
Praveen | 2025-10 | 52.71 | 79.45 | TA421 | 2 | <80
Praveen | 2025-11 | 45.11 | 37.93 | TA421 | 1 | <80
Praveen | 2025-12 | 37.67 | 44.85 | TA421 | 1 | <80
Prayag Mahto | 2025-09 | 47.63 | 0 |  | 0 | <80
Prayag Mahto | 2025-10 | 61.2 | 99.55 | TA325 | 2 | <80
Prayag Mahto | 2025-11 | 92.74 | 0 |  | 0 | 80-100
Prayag Mahto | 2025-12 | 21.64 | 123.65 | TA325 | 1 | <80
Prayag Mahto | 2026-01 | 80.41 | 80.41 | TA414 | 1 | 80-100
Prayag Saw | 2025-12 | 58.64 | 56.41 | TB507 | 4 | <80
Prayag Saw | 2026-01 | 99.88 | 98.54 | TB507 | 6 | 80-100
Prayag Saw | 2026-02 | 31.53 | 35.1 | TB507 | 2 | <80
Prayag Saw 1 | 2025-09 | 59.97 | 59.97 | TB507 | 5 | <80
Prayag Saw 1 | 2025-10 | 127.38 | 116.14 | TB507 | 7 | 120-140
Prayag Saw 1 | 2025-11 | 28.9 | 40.14 | TB507 | 2 | <80
Prayag Saw 2 | 2025-09 | 70.52 | 70.52 | TB507 | 5 | <80
Prayag Saw 2 | 2025-10 | 106.53 | 99.25 | TB507 | 6 | 100-120
Prayag Saw 2 | 2025-11 | 119.91 | 127.19 | TB507 | 8 | 100-120
Prayag Saw 2 | 2025-12 | 43.39 | 43.39 | TB507 | 3 | <80
Prayag Shah Mp | 2025-11 | 102.03 | 102.03 | TA505 | 2 | 100-120
Prayag Shah Mp | 2025-12 | 107.11 | 107.11 | TA505 | 3 | 100-120
Prayag Shah Mp | 2026-01 | 97.2 | 74.09 | TA505 | 2 | 80-100
Prayag Shah Mp | 2026-02 | 32.35 | 55.45 | TA505 | 1 | <80
Prem Kumar | 2025-10 | 40 | 40 | TA506 | 1 | <80
Prem Kumar | 2025-11 | 99.38 | 53 | TA506 | 1 | 80-100
Prem Kumar | 2025-12 | 69.63 | 116 | TA506 | 3 | <80
Prem Kumar | 2026-01 | 85 | 85 | TA506 | 3 | 80-100
Pritam Enterprises | 2025-07 | 105.2 | 105.2 | TA413 | 2 | 100-120
Pritam Enterprises | 2025-09 | 15 | 12 | TB507 | 1 | <80
Pritam Enterprises | 2025-10 | 124.47 | 127.47 | TB507 | 10 | 120-140
Pritam Enterprises | 2025-11 | 42.72 | 42.72 | TB507 | 3 | <80
Pritam Enterprises 1 | 2025-08 | 109.88 | 109.88 | TA413 | 3 | 100-120
Pritam Enterprises 1 | 2025-09 | 112.02 | 112.02 | TA413 | 3 | 100-120
Pritam Enterprises 1 | 2025-10 | 102.96 | 102.96 | TA413 | 2 | 100-120
Pritam Enterprises 1 | 2025-11 | 26 | 0 |  | 0 | <80
Pritam Enterprises 1 | 2025-12 | 39.87 | 65.87 | TA413 | 1 | <80
Pritam Enterprises 2 | 2025-08 | 166.11 | 117.62 | TA413 | 3 | 160-180
Pritam Enterprises 2 | 2025-09 | 129.6 | 155.83 | TA413 | 4 | 120-140
Pritam Enterprises 2 | 2025-10 | 76.97 | 66.78 | TA413 | 1 | <80
Pritam Enterprises 2 | 2025-11 | 58.93 | 87.61 | TA413 | 2 | <80
Pritam Enterprises 2 | 2025-12 | 114.83 | 118.6 | TA413 | 2 | 100-120
Pritam Enterprises 2 | 2026-01 | 73.24 | 73.24 | TA413 | 1 | <80
Pritam Enterprises 3 | 2025-08 | 144.58 | 119.29 | TA413 | 2 | 140-160
Pritam Enterprises 3 | 2025-09 | 170.24 | 195.53 | TA413 | 5 | 160-180
Pritam Enterprises 3 | 2025-10 | 113.24 | 113.24 | TA413 | 2 | 100-120
Pritam Enterprises 4 | 2025-08 | 91.44 | 81.74 | TA413 | 2 | 80-100
Pritam Enterprises 4 | 2025-09 | 71.59 | 81.3 | TA413 | 2 | <80
Pritam Enterprises 4 | 2025-10 | 71.73 | 62.44 | TA413 | 1 | <80
Pritam Enterprises 4 | 2025-11 | 27.85 | 37.14 | TA413 | 1 | <80
Priyanka Devi | 2025-08 | 111.39 | 103.89 | TB401, TB408 | 2 | 100-120
Priyanka Devi | 2025-09 | 30 | 37.5 | TB401 | 1 | <80
Priyanka Devi | 2025-11 | 50.45 | 37.5 | TB408 | 1 | <80
Priyanka Devi | 2025-12 | 64.75 | 77.7 | TB408 | 2 | <80
Priyanka Devi 2 | 2025-07 | 37.5 | 37.5 | TB408 | 1 | <80
Priyanka Devi 2 | 2025-08 | 115.2 | 115.2 | TB401 | 3 | 100-120
Priyanka Devi Santosh | 2025-08 | 25 | 0 |  | 0 | <80
Priyanka Devi Santosh | 2025-09 | 39.58 | 37.5 | TB408 | 1 | <80
Priyanka Devi Santosh | 2025-10 | 11.77 | 38.85 | TB401 | 1 | <80
Priyanka Devi Sontosh | 2025-09 | 57.6 | 57.6 | TB408 | 1 | <80
Priyanka Devi Subodh | 2025-07 | 12.45 | 0 |  | 0 | <80
Priyanka Devi Subodh | 2025-08 | 53.93 | 66.38 | TB408 | 1 | <80
Priyanka Devi Subodh | 2025-09 | 67.1 | 38.85 | TB408 | 1 | <80
Priyanka Devi Subodh | 2025-10 | 48.1 | 76.35 | TB401, TB408 | 2 | <80
Priyanka Devi Sudheer | 2025-06 | 30.28 | 0 |  | 0 | <80
Priyanka Devi Sudheer | 2025-07 | 130.34 | 160.61 | TB401 | 4 | 120-140
Priyanka Devi Sudheer | 2025-08 | 161.48 | 161.48 | TB401 | 3 | 160-180
Priyanka Devi Sudheer | 2025-09 | 129.53 | 121.77 | TB408 | 3 | 120-140
Priyanka Devi Sudheer | 2025-10 | 71.57 | 76.35 | TB401 | 2 | <80
Priyanka Devi Sudheer | 2025-11 | 35.86 | 38.85 | TB401 | 1 | <80
Priyanka Devi Sudheer 2 | 2025-07 | 38.85 | 38.85 | TB401 | 1 | <80
Punam Devi 1 | 2024-12 | 62.17 | 34.79 | TA413 | 1 | <80
Punam Devi 1 | 2025-01 | 202.46 | 211.06 | TA413 | 5 | 200-220
Punam Devi 1 | 2025-02 | 212.12 | 230.9 | TA413 | 6 | 200-220
Punam Devi 1 | 2025-03 | 206.92 | 198.96 | TA413 | 5 | 200-220
Punam Devi 1 | 2025-04 | 138.01 | 145.97 | TA413 | 3 | 120-140
Punam Devi 2 | 2024-12 | 208.81 | 192.39 | TA413 | 5 | 200-220
Punam Devi 2 | 2025-01 | 375.11 | 388.3 | TA413 | 9 | >=260
Punam Devi 2 | 2025-02 | 124.59 | 123.21 | TA413 | 3 | 120-140
Punam Devi 2 | 2025-03 | 173.5 | 174.32 | TA413 | 4 | 160-180
Punam Devi 2 | 2025-04 | 144.72 | 148.52 | TA413 | 3 | 140-160
Punam Devi 3 | 2024-03 | 0.6 | 0 |  | 0 | <80
Punam Devi 3 | 2024-04 | 3 | 0 |  | 0 | <80
Punam Devi 3 | 2024-05 | 3.1 | 0 |  | 0 | <80
Punam Devi 3 | 2024-06 | 3 | 0 |  | 0 | <80
Punam Devi 3 | 2024-07 | 3.1 | 0 |  | 0 | <80
Punam Devi 3 | 2024-08 | 3.1 | 0 |  | 0 | <80
Punam Devi 3 | 2024-09 | 3 | 0 |  | 0 | <80
Punam Devi 3 | 2024-10 | 3.1 | 0 |  | 0 | <80
Punam Devi 3 | 2024-11 | 3 | 0 |  | 0 | <80
Punam Devi 3 | 2024-12 | 68.62 | 37.93 | TA413 | 1 | <80
Punam Devi 3 | 2025-01 | 153.91 | 167.26 | TA413 | 4 | 140-160
Punam Devi 3 | 2025-02 | 122.94 | 113 | TA413 | 3 | 120-140
Punam Devi 3 | 2025-03 | 149.84 | 195.83 | TA413 | 5 | 140-160
Punam Devi 3 | 2025-04 | 123 | 129.32 | TA413 | 3 | 120-140
Punam Devi 4 | 2025-01 | 52.4 | 37.93 | TA413 | 1 | <80
Punam Devi 4 | 2025-02 | 248.38 | 262.85 | TA413 | 6 | 240-260
Punam Devi 4 | 2025-03 | 282.02 | 275.49 | TA413 | 7 | >=260
Punam Devi 4 | 2025-04 | 39.17 | 45.7 | TA413 | 1 | <80
Punam Kumari | 2024-11 | 19.72 | 0 |  | 0 | <80
Punam Kumari | 2024-12 | 16.44 | 36.16 | TA419 | 1 | <80
Punam Kumari | 2025-07 | 139.79 | 129.32 | TA413 | 3 | 120-140
Punam Kumari | 2025-08 | 145.41 | 112.83 | TA413, TA416 | 2 | 140-160
Punam Kumari | 2025-09 | 133.4 | 145.46 | TA416 | 2 | 120-140
Punam Kumari | 2025-10 | 36.14 | 67.11 | TA416 | 1 | <80
Punam Kumari 1 | 2025-08 | 134.23 | 126.64 | TA413 | 3 | 120-140
Punam Kumari 1 | 2025-09 | 207.22 | 181.6 | TA413 | 5 | 200-220
Punam Kumari 1 | 2025-10 | 344.17 | 320.9 | TA413, TA416 | 4 | >=260
Punam Kumari 1 | 2025-11 | 357.74 | 398.3 | TA413, TA416, TA419 | 7 | >=260
Punam Kumari 1 | 2025-12 | 370.69 | 340.54 | TA416, TA419, TA504 | 7 | >=260
Punam Kumari 1 | 2026-01 | 183.7 | 229.78 | TA416, TA504 | 4 | 180-200
Punam Kumari 2 | 2025-08 | 210.04 | 192.35 | TA413 | 4 | 200-220
Punam Kumari 2 | 2025-09 | 241.34 | 259.04 | TA413 | 5 | 240-260
Punam Kumari 2 | 2025-10 | 272.58 | 196.16 | TA413, TA416 | 5 | >=260
Punam Kumari 2 | 2025-11 | 182.99 | 189.04 | TA416, TA419 | 3 | 180-200
Punam Kumari 2 | 2025-12 | 230.3 | 285.78 | TA419, TA504 | 4 | 220-240
Punam Kumari 2 | 2026-01 | 179.84 | 194.73 | TA416, TA419, TA504 | 4 | 160-180
Punam Kumari 3 | 2025-08 | 11.95 | 0 |  | 0 | <80
Punam Kumari 3 | 2025-09 | 104.58 | 116.52 | TA413 | 3 | 100-120
Punam Kumari 3 | 2025-11 | 55.35 | 0 |  | 0 | <80
Punam Kumari 3 | 2025-12 | 110.66 | 110.7 | TA416 | 1 | 100-120
Punam Kumari 3 | 2026-01 | 55.31 | 110.63 | TA416 | 1 | <80
Punam Kumari 4 | 2025-09 | 125.48 | 101.15 | TA413 | 2 | 120-140
Punam Kumari 4 | 2025-10 | 57.4 | 81.74 | TA413 | 2 | <80
Punam Kumari 4 | 2025-12 | 43.8 | 43.8 | TA419 | 1 | <80
Pusplata | 2025-08 | 66.38 | 66.38 | TB408 | 1 | <80
Pusplata 1 | 2025-06 | 45.41 | 45.41 | TB401 | 1 | <80
Pusplata 1 | 2025-07 | 179.36 | 179.36 | TB401 | 4 | 160-180
Pusplata 1 | 2025-08 | 57.6 | 57.6 | TB401 | 1 | <80
Pusplata 2 | 2025-06 | 20.18 | 0 |  | 0 | <80
Pusplata 2 | 2025-07 | 203.86 | 224.04 | TB401 | 5 | 200-220
Pusplata 3 | 2025-06 | 14.06 | 0 |  | 0 | <80
Pusplata 3 | 2025-07 | 127.38 | 133.95 | TB401 | 3 | 120-140
Pusplata 3 | 2025-08 | 30 | 37.5 | TB401 | 1 | <80
Pusplata 3 Jwala | 2025-07 | 47.18 | 47.18 | TB401 | 1 | <80
Pusplata 4 | 2025-06 | 38.85 | 38.85 | TB401 | 1 | <80
Pusplata 4 | 2025-07 | 237.39 | 237.39 | TB401 | 6 | 220-240
Pusplata 4 | 2025-08 | 37.5 | 37.5 | TB401 | 1 | <80
Pusplata 5 | 2025-06 | 19.42 | 0 |  | 0 | <80
Pusplata 5 | 2025-07 | 142.96 | 162.38 | TB401 | 4 | 140-160
Pusplata 6 | 2025-06 | 12.39 | 0 |  | 0 | <80
Pusplata 6 | 2025-07 | 162.7 | 175.09 | TB401 | 4 | 160-180
Pusplata 6 | 2025-08 | 37.5 | 37.5 | TB401 | 1 | <80
Pusplata 7 | 2025-07 | 116.54 | 116.54 | TB401 | 3 | 100-120
Pusplata Ashok | 2025-04 | 2.07 | 0 |  | 0 | <80
Pusplata Ashok | 2025-05 | 9.15 | 0 |  | 0 | <80
Pusplata Ashok | 2025-06 | 8.86 | 0 |  | 0 | <80
Pusplata Ashok | 2025-07 | 9.15 | 0 |  | 0 | <80
Pusplata Ashok | 2025-08 | 166.19 | 195.43 | TB401, TB408 | 5 | 160-180
Pusplata Ashok | 2025-09 | 70.7 | 70.7 | TB401 | 1 | <80
Pusplata Deepak | 2025-08 | 151.36 | 151.36 | TB401, TB408 | 4 | 140-160
Pusplata Deepak | 2025-09 | 37.5 | 37.5 | TB401 | 1 | <80
Pusplata Dharamveer | 2025-08 | 135.82 | 86.03 | TB401, TB408 | 2 | 120-140
Pusplata Dharamveer | 2025-09 | 16.6 | 66.38 | TB408 | 1 | <80
Pusplata Kailash | 2025-07 | 38.85 | 38.85 | TB408 | 1 | <80
Pusplata Kailash | 2025-08 | 180.83 | 152.7 | TB408 | 4 | 180-200
Pusplata Kailash | 2025-09 | 48.22 | 76.35 | TB408 | 2 | <80
Pusplata Pankaj | 2025-08 | 38.85 | 38.85 | TB408 | 1 | <80
Pusplata Pankaj | 2025-09 | 37.5 | 37.5 | TB401 | 1 | <80
Pusplata Praful | 2025-07 | 41.25 | 37.5 | TB408 | 1 | <80
Pusplata Praful | 2025-08 | 123.66 | 127.41 | TB401, TB408 | 2 | 120-140
Pusplata Praphul | 2025-08 | 41.5 | 0 |  | 0 | <80
Pusplata Praphul | 2025-09 | 48.41 | 89.91 | TB408 | 1 | <80
Pusplata Rajaram | 2025-08 | 118.71 | 89.91 | TB401 | 1 | 100-120
Pusplata Rajaram | 2025-09 | 66.3 | 95.1 | TB408 | 2 | <80
Pusplata Ramchander | 2025-08 | 81.49 | 81.49 | TB401 | 1 | 80-100
Pusplata Ramchandra | 2025-08 | 42.87 | 38.85 | TB408 | 1 | <80
Pusplata Ramchandra | 2025-09 | 34.83 | 38.85 | TB408 | 1 | <80
Pusplata Santosh | 2025-08 | 47.18 | 47.18 | TB401 | 1 | <80
Pusplata Santosh Pankaj Singh | 2025-08 | 44.25 | 0 |  | 0 | <80
Pusplata Santosh Pankaj Singh | 2025-09 | 22.13 | 66.38 | TB408 | 1 | <80
Rabiul Hauq | 2025-02 | 28.07 | 26.53 | TB501 | 5 | <80
Rabiul Hauq | 2025-03 | 24.14 | 25.68 | TB501 | 5 | <80
Radha Construction | 2025-08 | 78.07 | 78.07 | TA416 | 1 | <80
Radha Construction | 2025-09 | 89.72 | 89.72 | TA416 | 1 | 80-100
Radha Enterprises | 2024-11 | 52.18 | 34.79 | TA419 | 1 | <80
Radha Enterprises | 2024-12 | 300.78 | 318.18 | TA419 | 8 | >=260
Radha Enterprises | 2025-01 | 320.97 | 264.15 | TA419 | 7 | >=260
Radha Enterprises | 2025-02 | 129.79 | 186.6 | TA419 | 3 | 120-140
Radha Enterprises | 2025-03 | 73.24 | 73.24 | TA419 | 1 | <80
Radha Enterprises | 2025-04 | 50.19 | 37.14 | TA419 | 1 | <80
Radha Enterprises | 2025-05 | 123.99 | 137.05 | TA419 | 1 | 120-140
Radha Enterprises | 2025-07 | 55.45 | 55.45 | TA419 | 1 | <80
Radha Enterprises | 2025-08 | 198.33 | 189.98 | TA419 | 2 | 180-200
Radha Enterprises | 2025-09 | 200.49 | 102.94 | TA419 | 2 | 200-220
Radha Enterprises | 2025-10 | 31.15 | 137.05 | TA419 | 1 | <80
Radha Enterprises 1 | 2025-02 | 111.57 | 111.57 | TA419 | 2 | 100-120
Radha Enterprises 1 | 2025-03 | 95.85 | 74.09 | TA419 | 2 | 80-100
Radha Enterprises 1 | 2025-04 | 157.93 | 179.68 | TA419 | 5 | 140-160
Radha Enterprises 1 | 2025-05 | 59.51 | 0 |  | 0 | <80
Radha Enterprises 1 | 2025-06 | 150.91 | 188 | TA419 | 4 | 140-160
Radha Enterprises 1 | 2025-07 | 130.21 | 132.29 | TA419 | 2 | 120-140
Radha Enterprises 1 | 2025-08 | 15.26 | 35.6 | TA419 | 1 | <80
Radha Enterprises 1 | 2025-10 | 99.78 | 99.78 | TA419 | 1 | 80-100
Radha Enterprises 2 | 2025-02 | 74.47 | 66.78 | TA419 | 1 | <80
Radha Enterprises 2 | 2025-03 | 59.57 | 67.26 | TA419 | 1 | <80
Radhika Enterprises | 2025-09 | 27 | 27 | TA506 | 1 | <80
Rafikul Islam | 2024-09 | 13.64 | 0 |  | 0 | <80
Rafikul Islam | 2024-10 | 236.17 | 152.7 | TB401, TB408 | 4 | 220-240
Rafikul Islam | 2024-11 | 75.69 | 172.8 | TB401, TB408 | 4 | <80
Rahim Khan | 2024-11 | 8.93 | 0 |  | 0 | <80
Rahim Khan | 2024-12 | 74.08 | 75.46 | TA325 | 2 | <80
Rahim Khan | 2025-01 | 85.96 | 75.46 | TA325 | 2 | 80-100
Rahim Khan | 2025-02 | 19.69 | 37.73 | TA325 | 1 | <80
Rahim Khan | 2025-03 | 157.13 | 132.14 | TA325 | 2 | 140-160
Rahim Khan | 2025-04 | 169.15 | 194.13 | TA325 | 4 | 160-180
Rahim Khan | 2025-05 | 73.78 | 73.78 | TA325 | 2 | <80
Rahim Khan 1 | 2025-05 | 39.46 | 39.46 | TA325 | 1 | <80
Rahul Kumar | 2024-05 | 114.92 | 114.92 | TA325 | 3 | 100-120
Rahul Kumar | 2024-06 | 157.21 | 150.92 | TA325 | 4 | 140-160
Rahul Kumar | 2024-07 | 171.16 | 177.45 | TA325 | 4 | 160-180
Rahul Kumar | 2024-08 | 192.41 | 192.41 | TA325 | 3 | 180-200
Rahul Kumar | 2024-09 | 121.74 | 64.25 | TA325 | 1 | 120-140
Rahul Kumar | 2024-10 | 108.38 | 129.34 | TA325 | 1 | 100-120
Rahul Kumar | 2024-11 | 191.7 | 164.15 | TA325 | 3 | 180-200
Rahul Kumar | 2024-12 | 91.39 | 151.88 | TA325 | 2 | 80-100
Rahul Kumar | 2025-01 | 128.5 | 103.71 | TA325 | 2 | 120-140
Rahul Kumar | 2025-02 | 184.44 | 141.87 | TA325 | 1 | 180-200
Rahul Kumar | 2025-03 | 191.28 | 262.22 | TA325 | 3 | 180-200
Rahul Kumar | 2025-04 | 182.89 | 170.87 | TA325 | 3 | 180-200
Rahul Kumar | 2025-05 | 88.28 | 100.3 | TA325 | 2 | 80-100
Rahul Kumar | 2025-07 | 128.4 | 121.76 | TB401 | 3 | 120-140
Rahul Kumar | 2025-08 | 174.14 | 144.08 | TB401, TB408 | 3 | 160-180
Rahul Kumar | 2025-09 | 47.99 | 84.69 | TB401 | 2 | <80
Rahul Kumar | 2025-10 | 172.51 | 162.65 | TA325 | 2 | 160-180
Rahul Kumar | 2025-11 | 139.22 | 39.46 | TA325 | 1 | 120-140
Rahul Kumar | 2025-12 | 204.7 | 296.97 | TA325, TA414 | 4 | 200-220
Rahul Kumar | 2026-01 | 193.58 | 210.93 | TA414 | 4 | 180-200
Rajesh Kumar | 2025-12 | 87.62 | 46 | TA504 | 1 | 80-100
Rajesh Kumar | 2026-01 | 4.38 | 46 | TA504 | 1 | <80
Rajesh Mahto | 2025-10 | 2.4 | 0 |  | 0 | <80
Rajesh Mahto | 2025-11 | 5.14 | 0 |  | 0 | <80
Rajesh Mahto | 2025-12 | 37.42 | 42.54 | TB507 | 3 | <80
Rajesh Mahto | 2026-01 | 12.14 | 14.57 | TB507 | 1 | <80
Raju Kumar | 2025-11 | 30.74 | 0 |  | 0 | <80
Raju Kumar | 2025-12 | 135.97 | 145.46 | TA419 | 2 | 120-140
Raju Kumar | 2026-01 | 68.57 | 89.82 | TA419 | 2 | <80
Rames Kumar M | 2025-05 | 17.18 | 17.18 | TB501 | 2 | <80
Rames Kumar M | 2025-10 | 24.45 | 24.45 | TB501 | 4 | <80
Rames Kumar M | 2025-11 | 11.53 | 11.53 | TB501 | 2 | <80
Ramesh | 2025-11 | 8.01 | 5.48 | TB501 | 1 | <80
Ramesh | 2025-12 | 3.8 | 6.33 | TB501 | 1 | <80
Ramesh Kumar | 2024-12 | 10.1 | 10.1 | TB501 | 2 | <80
Ramesh Kumar | 2025-01 | 84.1 | 80.45 | TB501 | 15 | 80-100
Ramesh Kumar | 2025-02 | 100.22 | 100.22 | TB501 | 17 | 100-120
Ramesh Kumar | 2025-03 | 95.14 | 97.25 | TB501 | 16 | 80-100
Ramesh Kumar | 2025-04 | 65.4 | 66.94 | TB501 | 9 | <80
Ramesh Kumar | 2025-05 | 49.45 | 49.45 | TB501 | 8 | <80
Ramesh Kumar | 2025-06 | 66.97 | 66.97 | TB501 | 6 | <80
Ramesh Kumar | 2025-07 | 55.29 | 55.29 | TB501 | 7 | <80
Ramesh Kumar | 2025-10 | 6.2 | 6.2 | TB501 | 1 | <80
Ramesh Kumar | 2025-11 | 64.99 | 64.99 | TB501 | 10 | <80
Ramesh Kumar | 2025-12 | 34.36 | 34.36 | TB501 | 4 | <80
Ramesh Kumar M | 2025-05 | 25.68 | 25.68 | TB501 | 5 | <80
Ramjivan | 2024-08 | 17.29 | 0 |  | 0 | <80
Ramjivan | 2024-09 | 71.16 | 37.73 | TA325 | 1 | <80
Ramjivan | 2024-10 | 78.62 | 129.34 | TA325 | 1 | <80
Ranjan Kumar | 2025-11 | 36.04 | 36.04 | TA325 | 1 | <80
Ranjan Kumar | 2025-12 | 71.51 | 37.73 | TA414 | 1 | <80
Ranjan Kumar | 2026-01 | 100.63 | 134.41 | TA414 | 2 | 100-120
Reeta Bharti | 2024-11 | 62.47 | 46.05 | TA416 | 1 | <80
Reeta Bharti | 2024-12 | 171.88 | 173.7 | TA416 | 4 | 160-180
Reeta Bharti | 2025-01 | 147.07 | 135.87 | TA416 | 3 | 140-160
Reeta Bharti | 2025-02 | 168.61 | 194.41 | TA416 | 4 | 160-180
Reeta Bharti | 2025-03 | 240.52 | 221.06 | TA416 | 4 | 240-260
Reeta Bharti | 2025-04 | 110.58 | 130.03 | TA416 | 2 | 100-120
Reeta Bharti | 2025-05 | 157.76 | 130.8 | TA416 | 3 | 140-160
Reeta Bharti | 2025-06 | 173.58 | 200.55 | TA416 | 4 | 160-180
Reeta Bharti | 2025-07 | 152.57 | 152.57 | TA416 | 2 | 140-160
Reeta Bharti | 2025-08 | 87.4 | 0 |  | 0 | 80-100
Reeta Bharti | 2025-09 | 117.54 | 161.36 | TA416 | 1 | 100-120
Reeta Bharti | 2025-10 | 58.11 | 101.69 | TA416 | 1 | <80
Rejaul | 2024-09 | 20.96 | 0 |  | 0 | <80
Rejaul | 2024-10 | 16.77 | 37.73 | TA325 | 1 | <80
Rohit | 2025-11 | 44.9 | 0 |  | 0 | <80
Rohit | 2025-12 | 120.99 | 149.02 | TA419 | 3 | 120-140
Rohit | 2026-01 | 59.04 | 75.91 | TA419 | 1 | <80
Rudra Construction | 2025-01 | 46.05 | 46.05 | TA416 | 1 | <80
Rudra Construction | 2025-02 | 89.82 | 89.82 | TA416 | 2 | 80-100
Rudra Construction | 2025-03 | 46.05 | 46.05 | TA416 | 1 | <80
Rudra Construction | 2025-04 | 49.53 | 43.78 | TA416 | 1 | <80
Rudra Construction | 2025-05 | 82.67 | 88.42 | TA416 | 2 | 80-100
Rupesh | 2025-03 | 41.53 | 0 |  | 0 | <80
Rupesh | 2025-04 | 67.45 | 108.98 | TA325 | 2 | <80
Rupesh | 2025-05 | 11.26 | 0 |  | 0 | <80
Rupesh | 2025-06 | 42.23 | 0 |  | 0 | <80
Rupesh | 2025-07 | 43.63 | 0 |  | 0 | <80
Rupesh | 2025-08 | 43.63 | 0 |  | 0 | <80
Rupesh | 2025-09 | 32.37 | 173.13 | TA325 | 1 | <80
Rupesh | 2025-10 | 79.92 | 0 |  | 0 | <80
Rupesh | 2025-11 | 9.22 | 89.15 | TA325 | 1 | <80
S K Janarul | 2024-08 | 19.25 | 0 |  | 0 | <80
S K Janarul | 2024-09 | 17.12 | 36.37 | TA421 | 1 | <80
S K Janarul Sheikh | 2024-09 | 59.1 | 36.37 | TA421 | 1 | <80
S K Janarul Sheikh | 2024-10 | 50.01 | 72.74 | TA421 | 2 | <80
Saidur Rahaman | 2025-01 | 6.05 | 6.05 | TB501 | 1 | <80
Saidur Rahaman | 2025-02 | 13.68 | 13.68 | TB501 | 2 | <80
Sainik Trader | 2025-08 | 79.34 | 75.86 | TA416 | 1 | <80
Sainik Trader | 2025-09 | 102.85 | 87.01 | TA416 | 1 | 100-120
Sainik Trader | 2025-10 | 54.1 | 73.43 | TA416 | 1 | <80
Sainik Traders | 2025-07 | 72 | 72 | TA504 | 2 | <80
Sainik Traders | 2025-08 | 74 | 74 | TA504 | 2 | <80
Sainik Traders | 2025-09 | 91.76 | 60 | TA504 | 1 | 80-100
Sainik Traders | 2025-10 | 28.24 | 60 | TA504 | 1 | <80
Sainik Traders | 2025-11 | 117.9 | 96 | TA504 | 2 | 100-120
Sainik Traders | 2025-12 | 192.1 | 214 | TA504 | 4 | 180-200
Sainik Traders | 2026-01 | 113.33 | 106 | TA504, TA506 | 3 | 100-120
Sainik Traders | 2026-02 | 14.67 | 22 | TA506 | 1 | <80
Sakhila Khatun | 2025-12 | 168.88 | 168.88 | TA414 | 3 | 160-180
Sakila Khatun | 2025-10 | 127.44 | 65.76 | TA325 | 1 | 120-140
Sakila Khatun | 2025-11 | 209.53 | 271.22 | TA325 | 2 | 200-220
Sakila Khatun | 2025-12 | 25.18 | 0 |  | 0 | <80
Sakila Khatun | 2026-01 | 244.54 | 269.72 | TA414 | 4 | 240-260
Sanjay Mahto | 2024-07 | 39.32 | 0 |  | 0 | <80
Sanjay Mahto | 2024-08 | 7.86 | 47.18 | TB401 | 1 | <80
Sanjeet | 2025-11 | 39.61 | 0 |  | 0 | <80
Sanjeet | 2025-12 | 175.92 | 215.53 | TA419 | 3 | 160-180
Sanjeet | 2026-01 | 89.82 | 89.82 | TA419 | 2 | 80-100
Sanjeev Kumar | 2024-09 | 3.41 | 0 |  | 0 | <80
Sanjeev Kumar | 2024-10 | 115.96 | 112.51 | TB401, TB408 | 3 | 100-120
Sanjeev Kumar | 2024-11 | 70.84 | 77.69 | TB401, TB408 | 2 | <80
Sanjeev Kumar | 2024-12 | 132.61 | 113.86 | TB401, TB408 | 3 | 120-140
Sanjeev Kumar | 2025-01 | 146.89 | 153.14 | TB401, TB408 | 3 | 140-160
Sanjeev Kumar | 2025-02 | 145.14 | 106.73 | TB401, TB408 | 2 | 140-160
Sanjeev Kumar | 2025-03 | 94.66 | 145.57 | TB401, TB408 | 3 | 80-100
Sanjeev Kumar | 2025-08 | 23.44 | 0 |  | 0 | <80
Sanjeev Kumar | 2025-09 | 128.81 | 131.87 | TB401 | 3 | 120-140
Sanjeev Kumar | 2025-10 | 149.83 | 149.37 | TB401, TB408 | 2 | 140-160
Sanjeev Kumar | 2025-11 | 136.61 | 120.42 | TB408 | 3 | 120-140
Sanjeev Kumar | 2025-12 | 20.57 | 57.6 | TB408 | 1 | <80
Santosh Singh | 2025-10 | 36.88 | 0 |  | 0 | <80
Santosh Singh | 2025-11 | 67.01 | 103.89 | TB408 | 2 | <80
Santosh Singh Laxmi | 2025-12 | 47.18 | 47.18 | TB408 | 1 | <80
Satish Kumar | 2025-10 | 74.83 | 65.76 | TA325 | 1 | <80
Satish Kumar | 2025-11 | 54.44 | 63.51 | TA325 | 1 | <80
Satyam Enterprises | 2025-07 | 244.99 | 159.7 | TB408 | 4 | 240-260
Satyam Enterprises | 2025-08 | 247.16 | 332.45 | TB408 | 6 | 240-260
Satyam Enterprises Manish | 2025-08 | 19.42 | 0 |  | 0 | <80
Satyam Enterprises Manish | 2025-09 | 19.42 | 38.85 | TB408 | 1 | <80
Satyam Enterprises Pawan | 2025-08 | 38.85 | 38.85 | TB408 | 1 | <80
Satyam Enterprises Santosh | 2025-05 | 12.32 | 0 |  | 0 | <80
Satyam Enterprises Santosh | 2025-06 | 26.53 | 38.85 | TB408 | 1 | <80
Satyam Enterprises Vijay | 2025-06 | 38.85 | 38.85 | TB408 | 1 | <80
Satyam Enterprises Vijay | 2025-07 | 77.7 | 77.7 | TB408 | 2 | <80
Satyam Enterprises Vijay | 2025-09 | 37.5 | 37.5 | TB408 | 1 | <80
Satyam Manish | 2025-04 | 6.49 | 0 |  | 0 | <80
Satyam Manish | 2025-05 | 215.55 | 189.01 | TB401 | 2 | 200-220
Satyam Manish | 2025-06 | 230.99 | 264.02 | TB401 | 4 | 220-240
Satyam Manish | 2025-07 | 135.1 | 135.1 | TB401 | 3 | 120-140
Satyam Manish | 2025-08 | 198.54 | 198.54 | TB401, TB408 | 5 | 180-200
Satyam Manish 2 Santosh | 2025-06 | 21.58 | 0 |  | 0 | <80
Satyam Manish 2 Santosh | 2025-07 | 17.27 | 38.85 | TB401 | 1 | <80
Satyam Mondal | 2025-05 | 78.24 | 57.6 | TB401 | 1 | <80
Satyam Mondal | 2025-06 | 137.28 | 157.92 | TB401 | 4 | 120-140
Satyam Mondal | 2025-07 | 133.07 | 133.07 | TB401 | 2 | 120-140
Satyam Nitish | 2025-04 | 5.55 | 0 |  | 0 | <80
Satyam Nitish | 2025-05 | 220.04 | 184.56 | TB401 | 4 | 220-240
Satyam Nitish | 2025-06 | 246.17 | 287.2 | TB401 | 2 | 240-260
Satyam Nitish | 2025-07 | 160.47 | 160.47 | TB401 | 3 | 160-180
Satyam Santosh | 2025-05 | 4.41 | 0 |  | 0 | <80
Satyam Santosh | 2025-06 | 33.09 | 37.5 | TB401 | 1 | <80
Satyam Santosh | 2025-07 | 38.85 | 38.85 | TB401 | 1 | <80
Satyam Trading | 2025-11 | 89.82 | 89.82 | TA419 | 2 | 80-100
Satyam Trading | 2025-12 | 126.22 | 115.28 | TA419 | 3 | 120-140
Satyam Trading | 2026-01 | 97.31 | 108.26 | TA419 | 2 | 80-100
Satyam Trivedi | 2025-01 | 3.56 | 0 |  | 0 | <80
Satyam Trivedi | 2025-02 | 7.66 | 0 |  | 0 | <80
Satyam Trivedi | 2025-03 | 8.48 | 0 |  | 0 | <80
Satyam Trivedi | 2025-04 | 8.21 | 0 |  | 0 | <80
Satyam Trivedi | 2025-05 | 83.49 | 75.01 | TB401 | 2 | 80-100
Satyam Trivedi | 2025-06 | 106.54 | 136.45 | TB401 | 3 | 100-120
Satyam Trivedi | 2025-07 | 69.88 | 76.35 | TB401 | 2 | <80
Satyam Trivedi Nitish | 2025-07 | 38.85 | 38.85 | TB401 | 1 | <80
Satyam Vijay | 2025-05 | 49.44 | 38.85 | TB401 | 1 | <80
Satyam Vijay | 2025-06 | 67.1 | 77.69 | TB401 | 2 | <80
Satyam Vijay | 2025-07 | 112.51 | 112.51 | TB401 | 3 | 100-120
Satyam Vijay | 2025-08 | 147.05 | 147.05 | TB401 | 3 | 140-160
Savitha | 2025-07 | 17.72 | 0 |  | 0 | <80
Savitha | 2025-08 | 39.28 | 57 | TA418 | 2 | <80
Savitha | 2025-09 | 40.34 | 0 |  | 0 | <80
Savitha | 2025-10 | 4.66 | 45 | TA418 | 1 | <80
Senahul | 2024-09 | 54.37 | 39.46 | TA325 | 1 | <80
Senahul | 2024-10 | 24.55 | 39.46 | TA325 | 1 | <80
Senahul | 2024-11 | 67.91 | 54.42 | TA325 | 1 | <80
Senahul | 2024-12 | 150.17 | 150.06 | TA325 | 2 | 140-160
Senahul | 2025-01 | 104.32 | 117.93 | TA325 | 2 | 100-120
Senahul | 2025-02 | 88.17 | 64.25 | TA325 | 1 | 80-100
Senahul | 2025-03 | 53.8 | 77.72 | TA325 | 1 | <80
Senahul | 2025-04 | 89.1 | 82.24 | TA325 | 1 | 80-100
Senahul | 2025-05 | 30.87 | 37.73 | TA325 | 1 | <80
Senahul Modina India 3 | 2025-05 | 5.08 | 0 |  | 0 | <80
Senahul Modina India 3 | 2025-06 | 8.03 | 0 |  | 0 | <80
Senahul Modina India 3 | 2025-07 | 8.3 | 0 |  | 0 | <80
Senahul Modina India 3 | 2025-08 | 8.3 | 0 |  | 0 | <80
Senahul Modina India 3 | 2025-09 | 8.03 | 37.73 | TA325 | 1 | <80
Senaul | 2025-09 | 25.82 | 0 |  | 0 | <80
Senaul | 2025-10 | 11.91 | 37.73 | TA325 | 1 | <80
Shakila Khatun | 2025-08 | 8 | 0 |  | 0 | <80
Shakila Khatun | 2025-09 | 75.03 | 83.03 | TA421 | 2 | <80
Sheetal Singh | 2025-08 | 38.85 | 38.85 | TB408 | 1 | <80
Sheetal Singh | 2025-12 | 111.79 | 111.79 | TB408 | 2 | 100-120
Sheetal Singh | 2026-01 | 37.5 | 37.5 | TB408 | 1 | <80
Sheetal Singh 1 | 2025-09 | 63.85 | 38.85 | TB408 | 1 | <80
Sheetal Singh 1 | 2025-10 | 12.5 | 37.5 | TB408 | 1 | <80
Sheetal Singh 2 | 2025-08 | 18.28 | 0 |  | 0 | <80
Sheetal Singh 2 | 2025-09 | 20.57 | 38.85 | TB408 | 1 | <80
Shila Devi | 2025-08 | 154 | 132.75 | TA505 | 2 | 140-160
Shila Devi | 2025-09 | 162.88 | 184.13 | TA505 | 3 | 160-180
Shila Devi | 2025-10 | 81.83 | 81.83 | TA505 | 1 | 80-100
Shila Devi | 2025-11 | 86.71 | 71.76 | TA505 | 2 | 80-100
Shila Devi | 2025-12 | 217.64 | 232.59 | TA505 | 4 | 200-220
Shila Devi | 2026-01 | 225.66 | 225.66 | TA505 | 3 | 220-240
Shila Devi | 2026-02 | 37.93 | 37.93 | TA505 | 1 | <80
Shobha Devi | 2025-08 | 100.87 | 82.92 | TB408 | 2 | 100-120
Shobha Devi | 2025-09 | 282.53 | 287.2 | TB408 | 2 | >=260
Shobha Devi | 2025-10 | 309.72 | 286.82 | TB408 | 5 | >=260
Shobha Devi | 2025-11 | 217.47 | 253.65 | TB408 | 5 | 200-220
Shobha Devi | 2025-12 | 197.98 | 197.98 | TB408 | 4 | 180-200
Shobha Devi | 2026-01 | 45.41 | 45.41 | TB408 | 1 | <80
Shradha | 2026-01 | 37 | 37 | TA506 | 1 | <80
Shree Ganesh Sital Enterprice | 2025-01 | 3.08 | 0 |  | 0 | <80
Shree Ganesh Sital Enterprice | 2025-02 | 39.25 | 39.85 | TB501 | 7 | <80
Shree Ganesh Sital Enterprice | 2025-03 | 44.36 | 46.85 | TB501 | 7 | <80
Shree Karni Entp | 2025-05 | 6.05 | 6.05 | TB501 | 1 | <80
Shri Karni Construction | 2025-08 | 39.2 | 0 |  | 0 | <80
Shri Karni Construction | 2025-09 | 685.8 | 725 | TA506 | 33 | >=260
Shri Shyam | 2025-11 | 45.41 | 45.41 | TB401 | 1 | <80
Shri Shyam Construction | 2025-09 | 45.41 | 45.41 | TB408 | 1 | <80
Shri Shyam Construction | 2025-10 | 37.5 | 37.5 | TB408 | 1 | <80
Shyam Construction | 2025-10 | 38.85 | 38.85 | TB401 | 1 | <80
Sintu Pawan Satyam Enterprises | 2025-08 | 66.38 | 66.38 | TB408 | 1 | <80
Sital Singh | 2025-08 | 75.01 | 75.01 | TB401 | 2 | <80
Sital Singh | 2025-11 | 41.14 | 0 |  | 0 | <80
Sital Singh | 2025-12 | 16.46 | 57.6 | TB401 | 1 | <80
Sital Singh 1 | 2025-09 | 80.93 | 77.69 | TB401 | 2 | 80-100
Sital Singh 1 | 2025-10 | 150.8 | 154.04 | TB401 | 3 | 140-160
Sital Singh 2 | 2025-08 | 38.85 | 38.85 | TB401 | 1 | <80
Sital Singh 2 | 2025-09 | 37.5 | 37.5 | TB401 | 1 | <80
Sk Samirul | 2025-12 | 38.04 | 38.04 | TA414 | 1 | <80
Sk Samiul 1 | 2025-07 | 52.19 | 0 |  | 0 | <80
Sk Samiul 1 | 2025-08 | 111.98 | 131.31 | TA413 | 3 | 100-120
Sk Samiul 1 | 2025-09 | 85.73 | 89.5 | TA413 | 2 | 80-100
Sk Samiul 1 | 2025-10 | 72.07 | 101.15 | TA413 | 2 | <80
Sk Samiul 2 | 2025-07 | 31.24 | 0 |  | 0 | <80
Sk Samiul 2 | 2025-08 | 114.22 | 145.46 | TA413 | 4 | 100-120
Sk Samiul Dildar Electricals 1 | 2025-11 | 90.6 | 0 |  | 0 | 80-100
Sk Samiul Dildar Electricals 1 | 2025-12 | 8.24 | 98.84 | TA325 | 1 | <80
Sk Samiul Sima Khatun | 2025-12 | 56.62 | 37.73 | TA414 | 1 | <80
Sk Samiul Sima Khatun | 2026-01 | 78.76 | 97.65 | TA414 | 2 | <80
Sk Samuil | 2024-09 | 5.61 | 0 |  | 0 | <80
Sk Samuil | 2024-10 | 24.83 | 0 |  | 0 | <80
Sk Samuil | 2024-11 | 75.25 | 75.5 | TA325 | 2 | <80
Sk Samuil | 2024-12 | 124.27 | 141.73 | TA325 | 3 | 120-140
Sk Samuil | 2025-01 | 58.96 | 39.46 | TA325 | 1 | <80
Sk Samuil | 2025-02 | 194.2 | 226.43 | TA325 | 6 | 180-200
Sk Samuil | 2025-03 | 202.4 | 159.65 | TA325 | 4 | 200-220
Sk Samuil | 2025-04 | 177.67 | 212.34 | TA325 | 5 | 160-180
Sk Samuil | 2025-05 | 74.37 | 82.46 | TA325 | 2 | <80
Sobha Devi | 2023-09 | 106.26 | 75.01 | TB401 | 2 | 100-120
Sobha Devi | 2023-10 | 257.51 | 265.21 | TB401 | 7 | 240-260
Sobha Devi | 2023-11 | 286.49 | 270.59 | TB401 | 7 | >=260
Sobha Devi | 2023-12 | 287.83 | 269.24 | TB401 | 6 | >=260
Sobha Devi | 2024-01 | 200.79 | 258.83 | TB401 | 6 | 200-220
Sobha Devi | 2024-02 | 273.58 | 263.87 | TB401, TB408 | 7 | >=260
Sobha Devi | 2024-03 | 301.06 | 277.58 | TB408 | 7 | >=260
Sobha Devi | 2024-04 | 231.56 | 253.65 | TB401, TB408 | 5 | 220-240
Sobha Devi | 2024-05 | 150.86 | 161.96 | TB408 | 4 | 140-160
Sobha Devi | 2024-08 | 121.6 | 115.2 | TB401, TB408 | 3 | 120-140
Sobha Devi | 2024-09 | 264.02 | 239.34 | TB401, TB408 | 5 | >=260
Sobha Devi | 2024-10 | 250.56 | 281.64 | TB408 | 6 | 240-260
Sobha Devi | 2024-11 | 276.24 | 276.24 | TB408 | 7 | >=260
Sobha Devi | 2024-12 | 268.01 | 245.3 | TB401, TB408 | 6 | >=260
Sobha Devi | 2025-01 | 279.64 | 273.9 | TB401 | 6 | >=260
Sobha Devi | 2025-02 | 240.47 | 268.92 | TB401, TB408 | 4 | 240-260
Sobha Devi | 2025-03 | 268.34 | 255.39 | TB401 | 6 | >=260
Sobha Devi | 2025-04 | 263.29 | 276.24 | TB401, TB408 | 7 | >=260
Sobha Devi | 2025-08 | 76.35 | 76.35 | TB408 | 2 | <80
Sobha Devi | 2025-11 | 82.92 | 82.92 | TB401, TB408 | 2 | 80-100
Spotyfy | 2025-09 | 26.66 | 0 |  | 0 | <80
Spotyfy | 2025-10 | 26.66 | 53.32 | TA416 | 1 | <80
Spotyfy 3 | 2025-08 | 15.61 | 0 |  | 0 | <80
Spotyfy 3 | 2025-09 | 26.76 | 42.37 | TA416 | 1 | <80
Srikarni | 2025-06 | 3.18 | 0 |  | 0 | <80
Srikarni | 2025-07 | 7.96 | 11.14 | TB507 | 1 | <80
Srvan Kumar | 2025-12 | 37.73 | 37.73 | TA414 | 1 | <80
Srvan Kumar Dhirendra Kumar Verma | 2026-01 | 34.7 | 34.7 | TA414 | 1 | <80
Subash | 2024-10 | 72.16 | 37.93 | TA421 | 1 | <80
Subash | 2024-11 | 223.59 | 231.84 | TA421 | 5 | 220-240
Subash | 2024-12 | 310.82 | 294.08 | TA421 | 8 | >=260
Subash | 2025-01 | 249.39 | 277.56 | TA421 | 7 | 240-260
Subash | 2025-02 | 232.34 | 234.76 | TA421 | 6 | 220-240
Subash | 2025-03 | 329.71 | 319.08 | TA421 | 8 | >=260
Subash | 2025-04 | 307.67 | 330.43 | TA421 | 8 | >=260
Subash | 2025-05 | 290.3 | 267.54 | TA421 | 7 | >=260
Subash | 2025-06 | 248.69 | 253.98 | TA421 | 5 | 240-260
Subash | 2025-07 | 236.25 | 253.72 | TA421 | 7 | 220-240
Subash | 2025-08 | 202.38 | 202.38 | TA421 | 5 | 200-220
Subash | 2025-09 | 228.1 | 228.1 | TA421 | 7 | 220-240
Subash | 2025-10 | 181.05 | 175.72 | TA421 | 4 | 180-200
Subash | 2025-11 | 262.97 | 260.76 | TA421 | 7 | >=260
Subash | 2025-12 | 388.78 | 384.54 | TA421 | 10 | >=260
Subash | 2026-01 | 92 | 103.79 | TA421 | 2 | 80-100
Subhash | 2025-08 | 134.26 | 103.2 | TA418 | 2 | 120-140
Subhash | 2025-09 | 184.61 | 149.9 | TA418 | 4 | 180-200
Subhash | 2025-10 | 149.12 | 198.83 | TA325, TA418 | 3 | 140-160
Subhash | 2025-11 | 203.58 | 206.13 | TA325 | 2 | 200-220
Subhash | 2025-12 | 163.1 | 141.87 | TA325 | 1 | 160-180
Subhash | 2026-01 | 197.45 | 232.19 | TA414 | 5 | 180-200
Subhash Kumar | 2025-12 | 36.04 | 36.04 | TA414 | 1 | <80
Sudheer 2 Priyanka Devi | 2025-09 | 57.6 | 57.6 | TB408 | 1 | <80
Sukhriddin | 2024-07 | 48.21 | 37.73 | TA325 | 1 | <80
Sukhriddin | 2024-08 | 64.92 | 37.73 | TA325 | 1 | <80
Sukhriddin | 2024-09 | 73.34 | 92.15 | TA325 | 2 | <80
Sukhriddin | 2024-10 | 78.55 | 92.15 | TA325 | 2 | <80
Sukhriddin | 2024-11 | 83.85 | 82.46 | TA325 | 2 | 80-100
Sukhriddin | 2024-12 | 82.41 | 75.46 | TA325 | 2 | 80-100
Sukhriddin | 2025-01 | 78.54 | 92.15 | TA325 | 2 | <80
Sukhriddin | 2025-02 | 51.03 | 37.73 | TA325 | 1 | <80
Sukhriddin | 2025-03 | 128.57 | 141.87 | TA325 | 1 | 120-140
Sukhriddin | 2025-04 | 141.87 | 141.87 | TA325 | 1 | 140-160
Sukhriddin | 2025-05 | 37.73 | 37.73 | TA325 | 1 | <80
Sukhrridin | 2025-09 | 25.23 | 0 |  | 0 | <80
Sukhrridin | 2025-10 | 48.54 | 73.78 | TA325 | 2 | <80
Sukruddin | 2025-10 | 69.84 | 37.73 | TA325 | 1 | <80
Sukruddin | 2025-11 | 170.75 | 170.17 | TA325 | 2 | 160-180
Sukruddin | 2025-12 | 140.08 | 172.77 | TA325 | 1 | 140-160
Sulen Sarkar | 2025-02 | 19.73 | 0 |  | 0 | <80
Sulen Sarkar | 2025-03 | 96.92 | 116.65 | TA325 | 3 | 80-100
Sulen Sarkar | 2025-04 | 122.08 | 122.08 | TA325 | 3 | 120-140
Sulen Sarkar | 2025-05 | 37.73 | 37.73 | TA325 | 1 | <80
Suman | 2025-08 | 8.41 | 8.41 | TB501 | 1 | <80
Suman | 2025-11 | 5 | 0 |  | 0 | <80
Suman | 2025-12 | 36.87 | 40.42 | TB501 | 5 | <80
Suman | 2026-01 | 19.72 | 21.16 | TB501 | 3 | <80
Sunny Const | 2023-09 | 69.65 | 37.5 | TB401 | 1 | <80
Sunny Const | 2023-10 | 200.25 | 227.71 | TB401 | 6 | 200-220
Sunny Const | 2023-11 | 188.38 | 187.52 | TB401 | 5 | 180-200
Sunny Const | 2023-12 | 180.3 | 171.45 | TB401 | 4 | 180-200
Sunny Const | 2024-01 | 163.3 | 152.7 | TB401 | 3 | 160-180
Sunny Const | 2024-02 | 213.17 | 230.4 | TB401, TB408 | 6 | 200-220
Sunny Const | 2024-03 | 122.97 | 115.2 | TB408 | 3 | 120-140
Sunny Const | 2024-04 | 230.49 | 220.43 | TB401, TB408 | 5 | 220-240
Sunny Const | 2024-05 | 182.01 | 207.61 | TB401, TB408 | 5 | 180-200
Sunny Const | 2024-08 | 32.82 | 0 |  | 0 | <80
Sunny Const | 2024-09 | 240.41 | 258.22 | TB401 | 6 | 240-260
Sunny Const | 2024-10 | 240.08 | 255.08 | TB401 | 5 | 240-260
Sunny Const | 2024-11 | 245.12 | 245.12 | TB401 | 6 | 240-260
Sunny Const | 2024-12 | 247.27 | 247.27 | TB401 | 4 | 240-260
Sunny Const | 2025-01 | 174.1 | 165.8 | TB401, TB408 | 3 | 160-180
Sunny Const | 2025-02 | 218.75 | 210.46 | TB401, TB408 | 4 | 200-220
Sunny Const | 2025-03 | 254.76 | 221.77 | TB401 | 4 | 240-260
Sunny Const | 2025-04 | 164.94 | 207.89 | TB401, TB408 | 4 | 160-180
Sunny Const | 2025-05 | 145.87 | 152.51 | TB401 | 2 | 140-160
Sunny Const | 2025-10 | 102.22 | 86.03 | TB401 | 2 | 100-120
Sunny Const | 2025-11 | 176.56 | 192.75 | TB401 | 4 | 160-180
Sunny Const | 2025-12 | 76.35 | 76.35 | TB401 | 2 | <80
Sunny Construction | 2025-05 | 81.49 | 81.49 | TB408 | 1 | 80-100
Sunny Construction | 2025-08 | 84.69 | 84.69 | TB408 | 2 | 80-100
Sunny Construction | 2025-09 | 243.82 | 238.17 | TB408 | 5 | 240-260
Sunny Construction | 2025-10 | 99.72 | 105.38 | TB408 | 2 | 80-100
Sunny Construction | 2025-12 | 122.19 | 122.19 | TB408 | 3 | 120-140
Sunny Construction | 2026-01 | 47.18 | 47.18 | TB408 | 1 | <80
Suraj Const | 2023-10 | 168.01 | 151.36 | TB401 | 4 | 160-180
Suraj Const | 2023-11 | 230.63 | 231.74 | TB401 | 6 | 220-240
Suraj Const | 2023-12 | 227.81 | 230.4 | TB401 | 6 | 220-240
Suraj Const | 2024-01 | 179.27 | 172.8 | TB401 | 4 | 160-180
Suraj Const | 2024-02 | 208.29 | 227.71 | TB401, TB408 | 6 | 200-220
Suraj Const | 2024-04 | 213.75 | 191.55 | TB408 | 5 | 200-220
Suraj Const | 2024-05 | 213.13 | 235.33 | TB408 | 5 | 200-220
Surender Mahto | 2025-01 | 44.73 | 44.73 | TA325 | 1 | <80
Tafijul Sk | 2026-01 | 85.44 | 37.73 | TA414 | 1 | 80-100
Tafijul Sk | 2026-02 | 7.34 | 55.05 | TA414 | 1 | <80
Tajirul | 2025-01 | 28.18 | 0 |  | 0 | <80
Tajirul | 2025-02 | 45.34 | 39.46 | TA325 | 1 | <80
Tajirul | 2025-03 | 12.55 | 46.62 | TA325 | 1 | <80
Tejal | 2025-08 | 14.17 | 0 |  | 0 | <80
Tejal | 2025-09 | 68.83 | 83 | TA506 | 4 | <80
Tejal Const | 2025-09 | 7.2 | 0 |  | 0 | <80
Tejal Const | 2025-10 | 40.8 | 48 | TA506 | 2 | <80
Tejal Construction | 2024-02 | 115.2 | 115.2 | TB401 | 3 | 100-120
Tejal Mahto | 2025-11 | 76.8 | 70 | TA506 | 2 | <80
Tejal Mahto | 2025-12 | 45.2 | 52 | TA506 | 2 | <80
Teklal Mahto | 2025-10 | 64.02 | 37.73 | TA325 | 1 | <80
Teklal Mahto | 2025-11 | 37.97 | 64.25 | TA325 | 1 | <80
Thanu Mahto | 2024-09 | 1.78 | 0 |  | 0 | <80
Thanu Mahto | 2024-10 | 61.04 | 56.86 | TA325 | 1 | <80
Thanu Mahto | 2024-11 | 75.31 | 37.73 | TA325 | 1 | <80
Thanu Mahto | 2024-12 | 105.73 | 149.26 | TA325 | 2 | 100-120
Thanu Mahto | 2025-01 | 121.15 | 90.46 | TA325 | 2 | 120-140
Thanu Mahto | 2025-02 | 135.98 | 141.44 | TA325 | 3 | 120-140
Thanu Mahto | 2025-03 | 82.9 | 108.13 | TA325 | 3 | 80-100
Thanu Mahto | 2025-04 | 39.46 | 39.46 | TA325 | 1 | <80
Thanu Mahto | 2025-05 | 14.91 | 0 |  | 0 | <80
Thanu Mahto | 2025-06 | 29.82 | 44.73 | TA325 | 1 | <80
Toshan Mahato | 2025-09 | 84.08 | 81.3 | TA505 | 2 | 80-100
Toshan Mahato | 2025-10 | 115.61 | 91.61 | TA505 | 2 | 100-120
Toshan Mahato | 2025-11 | 124.42 | 65.03 | TA505 | 1 | 120-140
Toshan Mahato | 2025-12 | 135.95 | 222.12 | TA505 | 2 | 120-140
Toshan Mahato | 2026-01 | 105.2 | 77.08 | TA505 | 1 | 100-120
Toshan Mahato | 2026-02 | 17.58 | 45.7 | TA505 | 1 | <80
Uma Const | 2024-08 | 11.54 | 0 |  | 0 | <80
Uma Const | 2024-09 | 121.81 | 112.51 | TB408 | 3 | 120-140
Uma Const | 2024-10 | 137.01 | 130.1 | TB408 | 3 | 120-140
Uma Const | 2024-11 | 49.95 | 77.7 | TB408 | 2 | <80
Uma Devi | 2025-12 | 17.07 | 0 |  | 0 | <80
Uma Devi | 2026-01 | 19.51 | 36.57 | TA601 | 1 | <80
Usha Tower | 2025-07 | 38.85 | 38.85 | TB401 | 1 | <80
Usha Tower | 2025-08 | 90.74 | 84.26 | TB401, TB408 | 2 | 80-100
Usha Tower | 2025-09 | 69.88 | 76.35 | TB401, TB408 | 2 | <80
Vasu Dev Singh 1 | 2024-11 | 62.44 | 36.16 | TA413 | 1 | <80
Vasu Dev Singh 1 | 2024-12 | 107.25 | 126.64 | TA413 | 3 | 100-120
Vasu Dev Singh 1 | 2025-01 | 189.36 | 194.35 | TA413 | 4 | 180-200
Vasu Dev Singh 1 | 2025-02 | 62.07 | 36.16 | TA413 | 1 | <80
Vasu Dev Singh 1 | 2025-03 | 10.11 | 37.93 | TA413 | 1 | <80
Vasu Dev Singh 2 | 2024-11 | 48.57 | 37.93 | TA413 | 1 | <80
Vasu Dev Singh 2 | 2024-12 | 105.71 | 108.09 | TA413 | 3 | 100-120
Vasu Dev Singh 2 | 2025-01 | 84.64 | 80.94 | TA413 | 2 | 80-100
Vasu Dev Singh 2 | 2025-02 | 105.95 | 103.3 | TA413 | 2 | 100-120
Vasu Dev Singh 2 | 2025-03 | 130.87 | 133.03 | TA413 | 3 | 120-140
Vasu Dev Singh 2 | 2025-04 | 45.54 | 57.96 | TA413 | 1 | <80
Ved Prakash | 2025-08 | 26.55 | 0 |  | 0 | <80
Ved Prakash | 2025-09 | 212.42 | 222.27 | TA413 | 6 | 200-220
Ved Prakash | 2025-10 | 181.75 | 66.78 | TA413 | 1 | 180-200
Ved Prakash | 2025-11 | 222.4 | 347.12 | TA413 | 2 | 220-240
Ved Prakash | 2025-12 | 219.96 | 226.9 | TA413 | 2 | 200-220
Ved Prakash | 2026-01 | 66.78 | 66.78 | TA413 | 1 | <80
Vedanta Const | 2025-11 | 75.31 | 47.18 | TB401 | 1 | <80
Vedanta Const | 2025-12 | 9.38 | 37.5 | TB401 | 1 | <80
Vedanta Construction | 2025-10 | 15.44 | 0 |  | 0 | <80
Vedanta Construction | 2025-11 | 16.55 | 0 |  | 0 | <80
Vedanta Construction | 2025-12 | 122.72 | 150.02 | TB408 | 4 | 120-140
Vedanta Construction | 2026-01 | 32.82 | 37.5 | TB408 | 1 | <80
Vinay Const | 2025-06 | 22.2 | 0 |  | 0 | <80
Vinay Const | 2025-07 | 111.01 | 133.22 | TB401 | 3 | 100-120
Vinay Const 2 | 2025-07 | 38.85 | 38.85 | TB401 | 1 | <80
Vinay Construction | 2025-07 | 21.19 | 0 |  | 0 | <80
Vinay Construction | 2025-08 | 175.15 | 172.06 | TB408 | 4 | 160-180
Vinay Construction | 2025-09 | 14.57 | 38.85 | TB408 | 1 | <80
Vinay Construction | 2025-10 | 53.72 | 37.5 | TB408 | 1 | <80
Vinay Construction | 2025-11 | 112.11 | 128.33 | TB408 | 3 | 100-120
Vinay Construction | 2025-12 | 38.85 | 38.85 | TB408 | 1 | <80
Vinay Construction | 2026-01 | 38.23 | 38.23 | TB507 | 2 | <80
Vinay Construction Chinta Devi | 2025-09 | 37.5 | 37.5 | TB408 | 1 | <80
Vinay Gupta | 2025-12 | 45.41 | 45.41 | TB408 | 1 | <80
Vinod | 2025-09 | 61 | 61 | TA506 | 2 | <80
Vishal Const | 2026-01 | 16 | 16 | TA506 | 1 | <80
Vivek Ganju | 2025-09 | 58.6 | 37.5 | TB408 | 1 | <80
Vivek Ganju | 2025-10 | 81.24 | 82.92 | TB401, TB408 | 2 | 80-100
Vivek Ganju | 2025-11 | 111.18 | 116.54 | TB401 | 3 | 100-120
Vivek Ganju | 2025-12 | 138.64 | 152.7 | TB401, TB408 | 4 | 120-140
Yadhav D K Verma | 2025-09 | 23.71 | 0 |  | 0 | <80
Yadhav D K Verma | 2025-10 | 14.22 | 37.93 | TA421 | 1 | <80
Yogendra Mahto | 2024-08 | 129.53 | 121.76 | TB401, TB408 | 3 | 120-140
Yogendra Mahto | 2024-09 | 152.88 | 115.2 | TB408 | 3 | 140-160
Yogendra Mahto | 2024-10 | 107.11 | 152.56 | TB401 | 3 | 100-120
Yogendra Mahto | 2024-11 | 144.94 | 133.22 | TB401, TB408 | 3 | 140-160
Yogendra Mahto | 2024-12 | 106.98 | 89.91 | TB401 | 1 | 100-120
Yogendra Mahto | 2025-01 | 67.65 | 96.44 | TB408 | 2 | <80
Zainab Fatima | 2025-11 | 34 | 34 | TA506 | 1 | <80
Zakir Hussain | 2025-12 | 37.73 | 37.73 | TA414 | 1 | <80

## PCH Mr. Sanjay Kumar Gupta
Scope: 2025-04-01 to 2026-02-28 ¦ Projects: 17 ¦ Erections: 2584 ¦ Gangs: 429
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
Mr. Sanjay Kumar Gupta | TA413 | 4.8 | 4.21 | 4.72 | 5.07 | 5.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.15 | 3.2 | 3.28 | 3.77 | 4.12 | 5.3 | 5.05 | 4.92 | 4.37 | 4.91 | 5.05 | 4.85 | 5.18 | 4.27 | 4.35 | 3.8 | 3.87 | 3.7 | 4.01 | 4.33 | 4.35 | 4.63 | 4.42 | 3.97 | 3.98 | 5.37 | 4.3 | 3.71 | 3.28 | 3.79 | 5.09 | 0 | 0 | 0 | 0 | 4.43 | 10113.08 | 207
Mr. Sanjay Kumar Gupta | TA419 | 3.1 | 3.76 | 4.33 | 5.37 | 5.93 | 6.03 | 6.28 | 4.58 | 4.58 | 4.82 | 4.31 | 4.79 | 5.79 | 5.25 | 5.63 | 5.87 | 5.96 | 3.3 | 2.94 | 3.22 | 3.28 | 3.13 | 3.08 | 2.87 | 3.97 | 4.24 | 4.5 | 4.77 | 4.09 | 3.54 | 3.6 | 4.05 | 3.6 | 3.15 | 3.44 | 3.69 | 3.65 | 3.65 | 3.32 | 3.03 | 3.43 | 3.42 | 3.56 | 3.52 | 0 | 0 | 0 | 0 | 3.71 | 6805.3 | 127
Mr. Sanjay Kumar Gupta | TA512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.58 | 2.58 | 2.73 | 4.16 | 4.73 | 4.42 | 4.47 | 5.45 | 5.43 | 5.44 | 5.1 | 4.98 | 4.71 | 5.49 | 4.78 | 4.85 | 5.25 | 5.43 | 4 | 4.03 | 3.84 | 3.78 | 3.83 | 3.26 | 3.13 | 3.68 | 4.21 | 5.42 | 6.38 | 0 | 0 | 0 | 4.31 | 5632.04 | 140
Mr. Sanjay Kumar Gupta | TB401 | 1.94 | 5.01 | 5.1 | 4.6 | 3.55 | 3.54 | 4.09 | 2.94 | 2.99 | 2.81 | 3.23 | 4.19 | 5.01 | 4.87 | 5.09 | 5.07 | 5.47 | 5.83 | 5.03 | 4.22 | 4.96 | 4.77 | 4.09 | 3.29 | 2.57 | 2.66 | 3.24 | 3.09 | 3.3 | 3 | 4.52 | 4.62 | 4.55 | 5.08 | 5.03 | 4.62 | 4.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.35 | 11489.47 | 242
Mr. Sanjay Kumar Gupta | TB408 | 6.42 | 4.32 | 4.16 | 4.67 | 6.47 | 1.18 | 1.15 | 3.42 | 2.31 | 1.18 | 1.71 | 2.63 | 3.12 | 3.81 | 3.56 | 4.15 | 5.51 | 5.25 | 4.06 | 4.47 | 4.88 | 4.83 | 4.94 | 4.32 | 4.67 | 4.65 | 4.47 | 4.2 | 4.94 | 4.43 | 4.48 | 4.19 | 4.45 | 4.13 | 4.26 | 3.98 | 4.27 | 4.96 | 4.67 | 4.08 | 4.09 | 6.22 | 8.68 | 7.18 | 5.68 | 0 | 0 | 0 | 4.43 | 11854.96 | 247
Mr. Sanjay Kumar Gupta | TB507 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.28 | 1.21 | 1.64 | 1.41 | 1.41 | 1.58 | 1.69 | 1.59 | 1.48 | 1.56 | 1.38 | 1.12 | 1.44 | 1.84 | 2.11 | 2.21 | 2.56 | 2.2 | 2.29 | 2.49 | 2.49 | 2.23 | 1.87 | 2.14 | 1.92 | 1.92 | 1.87 | 2.28 | 2.38 | 2.11 | 2.17 | 3.59 | 4.39 | 3.48 | 0 | 0 | 0 | 1.88 | 2697.56 | 178
[50 empty] | Total | 48592.41 | 1141
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
PCH Overall
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 4.25 | Week 1: 3.42; Week 2: 3.42; Week 3: 4.62; Week 4: 4.36; Week 5: 4.05; Week 6: 3.8; Week 7: 3.88; Week 8: 3.76; Week 9: 3.65; Week 10: 5.82
No of Gangs engaged (Avg) | 22 | Week 1: 24; Week 2: 40; Week 3: 69; Week 4: 94; Week 5: 76; Week 6: 63; Week 7: 63; Week 8: 70; Week 9: 48; Week 10: 14
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Project: TA413
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 4.67 | Week 1: 0; Week 2: 0; Week 3: 3.51; Week 4: 4.83; Week 5: 4.99; Week 6: 4.02; Week 7: 4.19; Week 8: 4.39; Week 9: 3.68; Week 10: 0
No of Gangs engaged (Avg) | 5 | Week 1: 0; Week 2: 0; Week 3: 8; Week 4: 21; Week 5: 19; Week 6: 17; Week 7: 11; Week 8: 7; Week 9: 3; Week 10: 0
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Project: TA419
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 4.19 | Week 1: 5.75; Week 2: 4.87; Week 3: 5.4; Week 4: 3.15; Week 5: 3.51; Week 6: 4.07; Week 7: 3.47; Week 8: 3.55; Week 9: 3.35; Week 10: 0
No of Gangs engaged (Avg) | 6 | Week 1: 5; Week 2: 1; Week 3: 4; Week 4: 4; Week 5: 3; Week 6: 9; Week 7: 16; Week 8: 20; Week 9: 15; Week 10: 0
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Project: TA512
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 0 | Week 1: 0; Week 2: 0; Week 3: 2.58; Week 4: 4.23; Week 5: 5.14; Week 6: 4.99; Week 7: 4.83; Week 8: 3.84; Week 9: 3.89; Week 10: 6.15
No of Gangs engaged (Avg) | 0 | Week 1: 0; Week 2: 0; Week 3: 1; Week 4: 3; Week 5: 3; Week 6: 4; Week 7: 6; Week 8: 11; Week 9: 17; Week 10: 12
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Project: TB401
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 4.51 | Week 1: 3.4; Week 2: 3.92; Week 3: 5.2; Week 4: 4.85; Week 5: 3.26; Week 6: 3.35; Week 7: 4.73; Week 8: 4.74; Week 9: 0; Week 10: 0
No of Gangs engaged (Avg) | 9 | Week 1: 14; Week 2: 30; Week 3: 35; Week 4: 31; Week 5: 17; Week 6: 14; Week 7: 13; Week 8: 9; Week 9: 0; Week 10: 0
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Project: TB408
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 5.32 | Week 1: 2.82; Week 2: 2.25; Week 3: 4.61; Week 4: 4.63; Week 5: 4.66; Week 6: 4.55; Week 7: 4.26; Week 8: 4.5; Week 9: 4.6; Week 10: 5.68
No of Gangs engaged (Avg) | 4 | Week 1: 4; Week 2: 6; Week 3: 17; Week 4: 37; Week 5: 31; Week 6: 17; Week 7: 15; Week 8: 18; Week 9: 8; Week 10: 1
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Project: TB507
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 0.03 | Week 1: 0.03; Week 2: 0.57; Week 3: 1.54; Week 4: 1.53; Week 5: 1.65; Week 6: 2.36; Week 7: 2.22; Week 8: 2.02; Week 9: 2.36; Week 10: 3.5
No of Gangs engaged (Avg) | 1 | Week 1: 1; Week 2: 3; Week 3: 4; Week 4: 7; Week 5: 12; Week 6: 10; Week 7: 8; Week 8: 8; Week 9: 5; Week 10: 1

## PCH Mr. Arun Felbin
Scope: 2025-04-01 to 2026-02-28 ¦ Projects: 17 ¦ Erections: 2584 ¦ Gangs: 429
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
Mr. Arun Felbin | TA325 | 4.24 | 4.55 | 4.48 | 4.11 | 4.06 | 3.79 | 3.45 | 2.58 | 2.88 | 2.4 | 1.58 | 1.41 | 1.41 | 1.33 | 1.21 | 1.22 | 1.18 | 1.17 | 1.16 | 0.99 | 0.95 | 1.02 | 1.01 | 1.07 | 1.42 | 2.04 | 2.68 | 4.01 | 4.2 | 3.82 | 3.53 | 3.59 | 3.92 | 4.3 | 4.6 | 4.3 | 3.63 | 3.3 | 3.47 | 3.75 | 3.68 | 3.64 | 0 | 0 | 0 | 0 | 0 | 0 | 3.16 | 13361.73 | 190
Mr. Arun Felbin | TA414 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.12 | 4.82 | 5.03 | 2.69 | 2.69 | 0 | 0 | 0 | 4.24 | 4.24 | 4.3 | 4.03 | 4.15 | 4.07 | 5.44 | 3.45 | 2.07 | 1.77 | 0.96 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.96 | 2.65 | 3.52 | 3.32 | 3.63 | 3.3 | 3.48 | 3.79 | 4.46 | 4.24 | 0 | 0 | 0 | 0 | 3.49 | 3869.12 | 77
Mr. Arun Felbin | TA416 | 4.96 | 5.55 | 5.69 | 6.74 | 6.36 | 6.04 | 5.48 | 5.65 | 5.8 | 5.77 | 5.46 | 5.73 | 5.75 | 4.95 | 4.99 | 4.99 | 5.17 | 4.65 | 3.98 | 3.57 | 3.48 | 3.55 | 3.77 | 4.02 | 4.18 | 4.27 | 4.36 | 4.29 | 3.72 | 3.68 | 3.57 | 3.57 | 4.01 | 4.42 | 4.32 | 4.01 | 3.44 | 3.22 | 3.02 | 3.03 | 3.18 | 3.14 | 4.14 | 3.95 | 3.67 | 0 | 0 | 0 | 4.59 | 11398.61 | 168
Mr. Arun Felbin | TA418 | 3.95 | 3.33 | 3.27 | 3.59 | 2.79 | 2.79 | 2.35 | 1.77 | 3.02 | 2.74 | 3.28 | 2.97 | 1.94 | 1.92 | 2.1 | 2.27 | 1.89 | 1.44 | 2.44 | 2.66 | 3.13 | 1.67 | 2.65 | 2.3 | 2.66 | 2.41 | 2.24 | 2.03 | 2.21 | 2.2 | 2.25 | 2.4 | 2.76 | 2.17 | 2.45 | 3.57 | 2.98 | 3.51 | 3.45 | 2.85 | 3.28 | 3.52 | 2.49 | 3.88 | 5.39 | 0 | 0 | 0 | 2.62 | 3287.86 | 86
Mr. Arun Felbin | TA421 | 6.38 | 5.92 | 6.96 | 7.97 | 8.22 | 6.84 | 5.36 | 3.77 | 3.97 | 4.82 | 3.81 | 5.41 | 5.24 | 5.65 | 5.19 | 4.94 | 3.98 | 6.1 | 5.95 | 3.81 | 3.69 | 4.37 | 6.89 | 6.07 | 4.3 | 4.45 | 3.77 | 5.5 | 5.64 | 4.81 | 4.56 | 7.05 | 6.18 | 6.49 | 7.46 | 6.99 | 7.21 | 8.45 | 11.26 | 8.17 | 6.85 | 6.41 | 0 | 0 | 0 | 0 | 0 | 0 | 5.7 | 8109.77 | 187
Mr. Arun Felbin | TA601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1 | 5.75 | 4.03 | 3.13 | 2.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.98 | 182.87 | 5
Mr. Arun Felbin | TB501 | 1.98 | 2.89 | 2.81 | 2.63 | 3.02 | 3.04 | 2.52 | 2.78 | 2.29 | 4.2 | 3.27 | 2.28 | 2.52 | 2.43 | 2.26 | 2.51 | 5.46 | 2.71 | 2.46 | 2.02 | 2.3 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1.24 | 2.58 | 1.99 | 2.14 | 1.23 | 1.58 | 1.2 | 1.53 | 0.86 | 2.93 | 3.21 | 2.38 | 4.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.38 | 772.99 | 106
[50 empty] | Total | 40982.95 | 819
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
PCH Overall
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 4.89 | Week 1: 4.43; Week 2: 3.62; Week 3: 2.93; Week 4: 2.88; Week 5: 3.12; Week 6: 3.69; Week 7: 3.97; Week 8: 3.99; Week 9: 3.8; Week 10: 3.95
No of Gangs engaged (Avg) | 45 | Week 1: 48; Week 2: 34; Week 3: 33; Week 4: 39; Week 5: 50; Week 6: 66; Week 7: 68; Week 8: 63; Week 9: 39; Week 10: 7
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Project: TA325
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 4.32 | Week 1: 3.55; Week 2: 1.75; Week 3: 1.23; Week 4: 1.06; Week 5: 1.47; Week 6: 3.77; Week 7: 4.05; Week 8: 3.89; Week 9: 3.68; Week 10: 0
No of Gangs engaged (Avg) | 20 | Week 1: 20; Week 2: 10; Week 3: 9; Week 4: 10; Week 5: 16; Week 6: 40; Week 7: 42; Week 8: 23; Week 9: 2; Week 10: 0
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Project: TA414
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 0.1 | Week 1: 3.4; Week 2: 4.18; Week 3: 4.24; Week 4: 4.14; Week 5: 2.88; Week 6: 0.4; Week 7: 0.4; Week 8: 3.35; Week 9: 3.87; Week 10: 2.53
No of Gangs engaged (Avg) | 1 | Week 1: 1; Week 2: 2; Week 3: 1; Week 4: 2; Week 5: 4; Week 6: 2; Week 7: 2; Week 8: 21; Week 9: 21; Week 10: 4
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Project: TA416
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 5.79 | Week 1: 5.75; Week 2: 5.69; Week 3: 4.99; Week 4: 3.68; Week 5: 4.06; Week 6: 4.05; Week 7: 4.05; Week 8: 3.41; Week 9: 3.31; Week 10: 3.67
No of Gangs engaged (Avg) | 13 | Week 1: 12; Week 2: 11; Week 3: 8; Week 4: 12; Week 5: 17; Week 6: 12; Week 7: 9; Week 8: 7; Week 9: 7; Week 10: 1
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Project: TA418
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 3.48 | Week 1: 2.44; Week 2: 2.8; Week 3: 2.01; Week 4: 2.39; Week 5: 2.5; Week 6: 2.16; Week 7: 2.4; Week 8: 3.35; Week 9: 3.13; Week 10: 5.3
No of Gangs engaged (Avg) | 3 | Week 1: 3; Week 2: 4; Week 3: 6; Week 4: 5; Week 5: 6; Week 6: 5; Week 7: 3; Week 8: 3; Week 9: 3; Week 10: 2
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Project: TA421
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 6.83 | Week 1: 5.63; Week 2: 4.88; Week 3: 4.91; Week 4: 4.69; Week 5: 5.33; Week 6: 4.93; Week 7: 6.62; Week 8: 7.92; Week 9: 7.34; Week 10: 0
No of Gangs engaged (Avg) | 5 | Week 1: 6; Week 2: 5; Week 3: 7; Week 4: 7; Week 5: 8; Week 6: 6; Week 7: 7; Week 8: 5; Week 9: 4; Week 10: 0
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Project: TA601
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 0 | Week 1: 0; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 6: 0; Week 7: 0; Week 8: 4.31; Week 9: 2.76; Week 10: 0
No of Gangs engaged (Avg) | 0 | Week 1: 0; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 0; Week 6: 0; Week 7: 0; Week 8: 3; Week 9: 2; Week 10: 0
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Project: TB501
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 2.52 | Week 1: 2.67; Week 2: 3.03; Week 3: 3.03; Week 4: 2.09; Week 5: 0; Week 6: 2.04; Week 7: 1.53; Week 8: 1.97; Week 9: 2.82; Week 10: 0
No of Gangs engaged (Avg) | 3 | Week 1: 6; Week 2: 2; Week 3: 2; Week 4: 3; Week 5: 0; Week 6: 2; Week 7: 5; Week 8: 3; Week 9: 1; Week 10: 0

## PCH Mr. Dheeraj Vashishth
Scope: 2025-04-01 to 2026-02-28 ¦ Projects: 17 ¦ Erections: 2584 ¦ Gangs: 429
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
Mr. Dheeraj Vashishth | TA513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.83 | 2.65 | 3.27 | 4.39 | 4.86 | 3.79 | 3.94 | 4.24 | 3.93 | 3.71 | 4.28 | 3.47 | 3.91 | 4.12 | 4.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.84 | 411.02 | 18
[50 empty] | Total | 411.02 | 18
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
PCH Overall
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 0 | Week 1: 0; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 2.78; Week 6: 4; Week 7: 4.11; Week 8: 3.9; Week 9: 0; Week 10: 0
No of Gangs engaged (Avg) | 0 | Week 1: 0; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 1; Week 6: 1; Week 7: 1; Week 8: 1; Week 9: 0; Week 10: 0
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Project: TA513
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 0 | Week 1: 0; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 2.78; Week 6: 4; Week 7: 4.11; Week 8: 3.9; Week 9: 0; Week 10: 0
No of Gangs engaged (Avg) | 0 | Week 1: 0; Week 2: 0; Week 3: 0; Week 4: 0; Week 5: 1; Week 6: 1; Week 7: 1; Week 8: 1; Week 9: 0; Week 10: 0

## PCH Mr. Nabajit Baruah
Scope: 2025-04-01 to 2026-02-28 ¦ Projects: 17 ¦ Erections: 2584 ¦ Gangs: 429
PCH | Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Avg Productivity (MTD) | Total MT (MTD) | Total No. of Erections (MTD)
Mr. Nabajit Baruah | TA504 | 7.33 | 5.88 | 7.17 | 6.58 | 4.56 | 4.26 | 4.98 | 6 | 4.5 | 6.03 | 7.04 | 7 | 0 | 2.4 | 2.4 | 2.55 | 3.6 | 3.05 | 2.77 | 2.3 | 2.35 | 2.39 | 2.44 | 2.96 | 3.51 | 4.08 | 4.04 | 4.11 | 4.13 | 3.94 | 3.9 | 4.46 | 4.21 | 4.61 | 4.99 | 5.22 | 5.04 | 5.26 | 5.4 | 4.94 | 4.79 | 4.9 | 4.62 | 5.22 | 8.8 | 0 | 0 | 0 | 4.49 | 3704 | 77
Mr. Nabajit Baruah | TA505 | 4.67 | 5.4 | 6.31 | 5.59 | 5.29 | 4.53 | 5.03 | 4.62 | 5.04 | 4.49 | 4.28 | 2.77 | 4.26 | 3.61 | 3.11 | 3.33 | 3.77 | 4.4 | 6.74 | 4.9 | 4.26 | 3.7 | 3.61 | 3.93 | 4.17 | 4.9 | 4.59 | 4.77 | 4.95 | 4.39 | 3.48 | 3.81 | 3.95 | 4.26 | 4.89 | 4.74 | 4.93 | 5.15 | 5.5 | 5.62 | 5 | 4.58 | 4.73 | 5.26 | 4.89 | 0 | 0 | 0 | 4.61 | 12278.74 | 261
Mr. Nabajit Baruah | TA506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.37 | 3.76 | 3.7 | 3.82 | 4.36 | 3.93 | 3.87 | 4.58 | 4.76 | 4.88 | 5.59 | 5.74 | 5.12 | 4.83 | 4.39 | 3.72 | 3.2 | 3.42 | 3.13 | 3.73 | 4.6 | 4.63 | 4.35 | 4.45 | 0 | 0 | 0 | 4.29 | 6929 | 268
[50 empty] | Total | 22911.74 | 606
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
PCH Overall
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 5.84 | Week 1: 4.91; Week 2: 4.27; Week 3: 3.32; Week 4: 3.99; Week 5: 3.94; Week 6: 4.36; Week 7: 4.64; Week 8: 4.74; Week 9: 4.73; Week 10: 4.89
No of Gangs engaged (Avg) | 8 | Week 1: 9; Week 2: 7; Week 3: 5; Week 4: 17; Week 5: 43; Week 6: 32; Week 7: 33; Week 8: 41; Week 9: 36; Week 10: 13
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Project: TA504
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 6.63 | Week 1: 4.9; Week 2: 6.42; Week 3: 2.88; Week 4: 2.46; Week 5: 3.23; Week 6: 4.04; Week 7: 4.51; Week 8: 5.24; Week 9: 4.81; Week 10: 8.8
No of Gangs engaged (Avg) | 2 | Week 1: 2; Week 2: 1; Week 3: 1; Week 4: 5; Week 5: 5; Week 6: 4; Week 7: 4; Week 8: 8; Week 9: 7; Week 10: 1
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Project: TA505
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 5.5 | Week 1: 4.91; Week 2: 3.98; Week 3: 3.42; Week 4: 4.6; Week 5: 4.22; Week 6: 4.51; Week 7: 4.14; Week 8: 5.1; Week 9: 4.99; Week 10: 4.82
No of Gangs engaged (Avg) | 6 | Week 1: 7; Week 2: 6; Week 3: 4; Week 4: 9; Week 5: 14; Week 6: 12; Week 7: 12; Week 8: 16; Week 9: 13; Week 10: 7
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Project: TA506
Erection productivity | Apr'25 | Week 1: May'25; Week 2: Jun'25; Week 3: Jul'25; Week 4: Aug'25; Week 5: Sep'25; Week 6: Oct'25; Week 7: Nov'25; Week 8: Dec'25; Week 9: Jan'26; Week 10: Feb'26
Weight/day (Avg) | 0 | Week 1: 0; Week 2: 0; Week 3: 0; Week 4: 3.34; Week 5: 3.96; Week 6: 4.3; Week 7: 5.27; Week 8: 3.84; Week 9: 4.18; Week 10: 4.2
No of Gangs engaged (Avg) | 0 | Week 1: 0; Week 2: 0; Week 3: 0; Week 4: 3; Week 5: 24; Week 6: 16; Week 7: 17; Week 8: 17; Week 9: 17; Week 10: 5